## Progress Summary
#VALUE! | Project Code - | TB-408 | Date | 2026-02-24 |  | Head - T&D | Rajinder Gupta |  | Head T&D-North | Sanjay K. Gupta | Regional Manager | Sandeep Singh Kumar |  |  | Shortcut for previous of Full description
| Client Name- | Resonia Limited (Formally Sterlite Power Transmission Limited) |  |  |  | Project Manager | Partha Pal |  |  |  | Planning Engineer | Raghav Ranjan |  |  | Link for go through
| Project Name- | 765KV D/C Fatehgarh III- Beawar Transmission Line, PKG F |  |  |  | Effective Date | 2023-12-06 |  | End Date | 2026-02-28 | LOA Value | Rs 283.08 Cr Supply -Rs 209.88 Cr., Service.-Rs 73.20 Cr |  |  | X-ing Status'!A1
Sr. No. | Activity | As per latest Estimate | Cumm. Progress up to last Month | Balance on Starting of this Month, excl. Tata | Plan for this Month | Today Progress | MTD | WIP | Cumulative Progress | Balance | Gangs at present | Remarks | Support Required | % Completion | L2 Schedule'!A1
1 | Check Survey (Kms) | 191.373 | 191.393 | -0.02 | -0.02 |  |  |  | 191.393 | -0.02 | - |  |  | 100.0105 | Hindrance Register (Row)'!A1
2 | Foundation (Nos.) | 485 | 481 | 4 | 4 |  | 3 |  | 484 | 1 | 1 | Gang-1:- Today Completed:- | Request for clearances of locs no 21/1 (last Pit) Pending since long. | 99.7938 | Survey!A1
3 | Earthing (Nos.) | 485 | 481 | 4 | 4 |  | 1 |  | 482 | 3 | 1 |  |  | 99.3814 | Foundation!A1
4 | Tower Erection (Nos) | 485 | 459 | 26 | 22 | 1 | 4 | 3 | 463 | 22 | 3 | WIP- 8/6, 8/7, 22/8 Today Completed - 8/11 |  | 95.4639 | Earthing!A1
5 | Tack Welding (Nos) | 485 | 295 | 190 | 36 |  | 81 |  | 376 | 109 | 4 |  |  | 77.5258 | Erection!A1
6 | Paying Out (Kms) | 191.373 | 81.48 | 76.127 | 23 |  | 2.26 | 3.551 | 83.74 | 73.867 | 3 | AP7-8:- WIP AP55-56:- WIP | 3 phase R/Sag done in AP55-56. Gangs (MC Power) shifted in Package G for rectification. No works will be done until readiness of PKG G based on resonia instructions. | 43.7575 | Tackwelding!A1
7 | Final Sag (Kms) | 191.373 | 76.5567 | 81.0503 | 28 |  | 6.41 | 0.795 | 82.9667 | 74.6403 |  | AP44/8-44/10:- Not Started due to ROW. | Further works not started due to ROW from AP43-44/8. | 43.3534 | Stringing!A1
8 | OPGW (Kms) | 191.373 | 64.067 | 93.54 | 30 |  | 17.003 |  | 81.07 | 76.537 |  |  |  | 42.3623 | Stringing associated works'!A1
OPGW!A1
Workfront Status | [14 empty] | Visual chart'!A1
Page Chart'!A1
A. Foundation | [14 empty] | Benching F'!A1
Balance on 1st of this month | Progress MTD | WIP | Clear/Yet to attempt | ROW | Remarks
4 | 3 | 0 | 0 | 1
B. Erection
Balance on 1st of this month | Progress MTD | WIP | Clear/Yet to attempt | ROW | Linked With Fnd | Remarks
26 | 4 | 3 | 0 | 18 | 1
C. Stringing
STR P/Out Bal. on starting of this month | Progress MTD | WIP | Clear/Yet to attempt | ROW | Readiness awaited due to Erec. | Readiness awaited due to Tower Inspection
76.127 | 2.26 | 3.551

## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Supervisor
TB408 | 765 KV Beawer Transmission Line, PKG F | Resonia Limited | 2023-12-06 | 2025-10-30 | Mr. Raghav Ranjan | Mr. Sanjay Kumar Gupta | Mr. Sandeep Singh Kumar | Mr. Partha Pal | Dev Saran Swarakar | Pradeep Kumar
[8 empty] | Mr. Virendra Gupta | Rajeev Kumar | Vikas Kumar
[9 empty] | Vivek Shukla | Ganesh Singh
[9 empty] | Vijay Yadav | Dineshwar Mahto
[9 empty] | Ram Tirath Singh | Kamla Pal Prasad
[9 empty] | Jitendra Saini | Bisun Saw
Shakib Hussain
Umesh Prasad
Prince Kumar Nirala
Pramod Kumar Sahoo
Jainath Mahto
Rajesh Pal
Ramji Tanti
Rakesh Pramanik
Sam Mahammad
Suresh Kumar Pal
Hulas Kumar Mahto
Akash Dadarao Thul
Vaibhav Sharma
Dasharath Mahto
Mukesh Kumar
Dashrath Mahto
Kartik Mahato
Gangadin Sahu
Dev Narayan Mahto
Ashok Kumar
Debananda Ray
Dev Prakash
Jai Lal Mahto
Jitendra Kumar
Deo Prakash
Tribhuwan Mahto
Umesh Kumar Mahto
Rahul Sharma
Karan Pal Singh
Pritish Kumar Pradhan
Akshay Lal
Laxman Sarkar

## X-ing Status
Progress Summary'!A1
Details of Crossing in 765KV D/C Fatehgarh-III to Beawar Transmission Line
Sr. No. | Name of Crossing | From | To | Span in Mtrs | Submission Date | Appr. Date | Foundation Status | Erection Status | Stringing Status | Plan for Stringing
Power Line Crossing – 9 nos
1 | 400 KV S/C Jaisalmer-Barmer Line | 3/0 | 4/0 | 226.52 | 2024-02-15 |  | AP3:- Completed AP4:- Completed | AP3:- Completed AP4:- Completed | Completed
2 | 220 KV D/C Barmer-Akal Line | 5/0 | 6/0 | 246.019 | 2024-02-15 |  | AP5:- Completed AP6:- Completed | AP5:- Completed AP6:- Completed | Balance
3 | 132 KV S/C Sheo-Jaisalmer Line | 7/0 | 8/0 | 210.755 | 2024-02-15 |  | AP7:- Completed AP8:- Completed | AP7:- Completed AP8:- Completed | WIP
4 | 400 KV D/C Barmer-Jaisalmer-2 Line | 9/0 | 10/0 | 233.076 | 2024-02-15 |  | AP9:- Completed AP10:- Completed | AP9:- Completed AP10:- Balance | Balance
5 | 132 KV S/C Sheo-Undoo Line | 12/0 | 13/0 | 211.914 | 2024-02-15 |  | AP12:- Completed AP13:- Completed | AP12:- Completed AP13:- Balance | Balance
6 | 132 KV S/C Undoo-Baytoo Line | 23/0 | 24/0 | 222.155 | 2024-01-16 | 2024-06-27 | AP23:- Completed AP24:- Completed | AP23:- Balance AP24:- Completed | Balance
7 | 400 KV D/C Mandor-JSW Transmission Line | 46/0 | 47/0 | 197.7 |  |  | AP46:- Completed AP47:- Completed | AP46:- Completed AP47:- Completed | Completed
8 | 400 KV D/C Line | 56/0 | 57/0 | 179.9 |  |  | AP56:- Completed AP57:- Completed | AP56:- Completed AP57:- Completed. | Completed
9 | 220 KV D/C Balotra-Boranada Transmission Line | 66/0 | 67/0 | 207.8 | 2024-03-08 | 2024-07-18 | AP66:- Completed AP67:- Completed | AP66:- Completed AP67:- Completed | Completed
NH Crossings-3 Nos | NH Crossing
1 | NH - 68 (Barmer - Jaisalmer) | 5/0 | 6/0 | 246.019 | 2024-02-15 |  | AP5:- Completed AP6:- Completed | AP5:- Completed AP6:- Completed | Balance
2 | Expressway (Amritsar-Jamnagar) | 58/0 | 59/0 | 238.9 | 2024-03-08 | 2024-06-01 | AP58:- Completed AP59:- Completed | AP58:- Completed AP59:- Completed | Completed
3 | NH | 68/0 | 69/0 | 200.9 | 2024-03-08 | 2024-06-26 | AP68:- Completed AP69:- Completed | AP68:- Completed AP69:- Completed | Completed
Gas Pipe Line-1 Nos | NH Crossing
1 | Gas Pipe Lines | 65/7 | 65/8 | 394.3 |  |  | AP65/7:- Completed AP65/8:- Completed | AP65/7:- Completed AP65/8:- Completed | Completed | Completed

## L2 Schedule
Progress Summary'!A1 | L2 Schedule vs Actual
Line Name: Part F, 765KV D/C Fatehgarh- Beawar Transmission Line
LOI Date: 11-Sep-2023
Effective Date: 06-Dec-2023
| Schedule Completion as per LOA: 05-March-2025 |  |  | Time Extension Extended till- 28.02.2026
| Scope & Discription |  |  |  |  | Before L2 | L2-Approved | [15 empty] | Extension of time (Approved) -1 | [6 empty] | Extension of time (Approved) -2 |  |  |  | Extension of time-3 (Proposed) |  |  |  |  | Remarks
| Sr. No. | Description | Scope of Work | UOM | Qty. | 2023-10-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01
[6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
| 1 | Release of Sag Template Curve & Tower Spotting Data | Sterlite
| 2 | Approval of repeated tower design & its BOMS | Sterlite
| 3 | Approval of repeated foundation design/drawings | Sterlite
| 4 | Supply
| i) | Manufacturing of Stubs with Earthing material(incl. B&N) | KEC
| A. | Inspection of stub | Sterlite | Nos. | 482 | 1: 40; 2: 100; 3: 100; 5: 100; 6: 65; 8: 77
| B. | Dispatch of stub | KEC | Nos. | 482 | 1: 40; 2: 100; 3: 100; 4: 0; 5: 100; 6: 65; 7: 0; 8: 77; 9: 0; 10: 0; 11: 0; 12: 0; 13: 0
| C. | Receipt of stubs at site | KEC | Nos. | 482 | 1: 40; 2: 100; 3: 100; 4: 0; 5: 100; 6: 65; 7: 0; 8: 77; 9: 0; 10: 0; 11: 0; 12: 0; 13: 0
|  | MFC submitted on |  |  |  | 1: 192; 2: 73; 3: 73
|  | MFC received on |  |  |  | 1: 192; 2: 73; 4: 73; 7: 144
|  | Actual |  |  |  | 1: 40; 2: 120; 3: 0; 4: 10; 6: 152; 7: 39; 8: 5; 11: 27
| ii) | Manufacturing of Tower (incl B&N) | KEC
| A. | Inspection of tower | Sterlite | Nos. | 482 | 1: 50; 2: 60; 3: 60; 4: 60; 5: 60; 6: 65; 7: 66; 8: 31; 9: 30
| B. | Dispatch of tower | KEC | Nos. | 482 | 2: 50; 3: 60; 4: 60; 5: 60; 6: 60; 7: 65; 8: 66; 9: 31; 10: 30; 11: 0; 12: 0; 13: 0
| C. | Receipt of complete towers at site | KEC | Nos. | 482 | 2: 50; 3: 60; 4: 60; 5: 60; 6: 60; 7: 65; 8: 66; 9: 31; 10: 30; 11: 0; 12: 0; 13: 0
|  | MFC submitted on |  |  |  | 1: 97; 2: 128; 6: 65; 7: 192
|  | MFC received on |  |  |  | 1: 97; 2: 128; 7: 257
|  | Actual |  |  |  | 2: 50; 3: 60; 4: 45; 5: 74; 6: 9; 7: 99; 10: 54; 12: 10
| iii) | Supply of following Tower accessories
| A. | Danger Plate | KEC | % | 100 | 9: 100%
| B. | Number Plate | KEC | % | 100 | 9: 100%
| C. | Phase Plate (Set of three) | KEC | % | 100 | 9: 100%
| D. | Circuit Plate (Set of Two) | KEC | & | 100 | 9: 100%
| E. | Anti-Climbing Device | KEC | % | 100 | 9: 100%
| F. | Bird Guard (Set of Three) | KEC | % | 100 | 9: 100%
| iv) | Other's Supply
| A. | Span Marker | KEC | % | 100 | 9: 100%
| B. | Aviation Light | KEC | % | 100 | 9: 100%
| v) | OSM
| A. | Supply of AL59 Zebra Conductor & associated Acessories | Sterlite | % | 100 | 4: 25%; 7: 25%; 9: 25%; 11: 25%
| B. | Supply of Insulator & associated Hardwere | Sterlite | % | 100 | 4: 25%; 7: 25%; 9: 25%; 11: 25%
| C. | Supply of Earth Wire & associated Hardwere | Sterlite | % | 100 | 1: 0; 2: 0; 4: 25%; 5: 0; 7: 25%; 8: 0; 9: 25%; 11: 25%
| D. | Supply of OPGW & associated Hardwere | Sterlite | % | 100 | 1: 0; 2: 0; 6: 25%; 9: 25%; 11: 25%; 12: 25%
| 5 | Erection | [36 empty] | 0
| A. | Establishment of Site Office | [36 empty] | 0
| B. | Route Alignment(Date of Start) | Sterlite | Kms | 191 | [33 empty] | 0
| C. | Detail Survey | Sterlite | Kms | 191 | 1: 90; 2: 71; 3: 30 | 191
|  | Actual |  |  |  | 1: 191 | 191
| D. | Check Survey | KEC | Kms | 191 | 1: 20; 2: 65; 3: 65; 4: 41 | 191
|  | Actual date of submission |  |  |  | 1: 128.337; 2: 2.238; 3: 28.252; 7: 10.313; 8: 5.601; 9: 3.788; 10: 3.65; 12: 2.747; 13: 4.966 | 189.892
|  | Actual date of approval |  |  |  | 1: 86.508; 2: 44.067; 3: 14.03; 6: 12.488; 8: 15.914; 9: 3.788; 12: 3.57; 13: 9.446 | 189.811
| E. | Soil Investigation Location approval | Sterlite | Loc | 193 | 1: 193 | 193
|  | Actual |  |  |  | 2: 24 | 24
| F. | Soil Investigation Location at Site | KEC | Loc | 193 | 1: 40; 2: 40; 3: 60; 4: 53 | 193
|  | Actual |  |  |  | 4: 24 | 24
| G. | Foundation | [36 empty] | 0
| G.1 | Foundation(Incl.Earthing) | KEC | Nos | 482 | 1: 20; 2: 40; 3: 45; 4: 45; 5: 45; 6: 40; 7: 30; 8: 35; 9: 35; 10: 35; 11: 45; 12: 45; 13: 22 | 482
|  | Actual |  |  |  | 1 | 22 | 46 | 36 | 16 | 7 | 15 | 9 | 14 | 26 | 38 | 26 | 9 | 31 | 47 | 27 | 17 | 13 | 13 | 19 | 22 | 8 | 9 | 7 | 3 | 0 | 0 | 3 | [5 empty] | 484
|  | Cummulative |  |  |  | 1 | 23 | 69 | 105 | 121 | 128 | 143 | 152 | 166 | 192 | 230 | 256 | 265 | 296 | 343 | 370 | 387 | 400 | 413 | 432 | 454 | 462 | 471 | 478 | 481 | 481 | 481 | 484 | [5 empty] | 8284
| G.2. | Earthing |  |  |  | 0 | 5 | 35 | 58 | 20 | 10 | 11 | 9 | 10 | 19 | 45 | 20 | 2 | 25 | 37 | 53 | 22 | 12 | 15 | 17 | 19 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 451
|  | Cummulative |  |  |  | 0 | 5 | 40 | 98 | 118 | 128 | 139 | 148 | 158 | 177 | 222 | 242 | 244 | 269 | 306 | 359 | 381 | 393 | 408 | 425 | 444 | 449 | 451 | 451 | 451 | 451 | 451 | 451 | [5 empty] | 7859
| H. | Erection | [36 empty] | 0
| H.1 | Erection of towers (Incl. Tack welding & painting of tower) | KEC | Nos | 482 | 3: 25; 4: 30; 5: 45; 6: 45; 7: 35; 8: 35; 9: 35; 10: 35; 11: 50; 12: 50; 13: 50; 14: 47 | 482
|  | Actual | [6 empty] | 22 | 20 | 19 | 14 | 3 | 2 | 3 | 16 | 30 | 30 | 11 | 16 | 14 | 13 | 7 | 2 | 6 | 23 | 52 | 47 | 25 | 33 | 40 | 11 | 4 | [5 empty] | 463
|  | Tonnage | MT | [5 empty] | 879.6247 | 782.8797 | 787.2406 | 641.6864 | 112.5131 | 77.6952 | 116.5428 | 652.8044 | 1312.5266 | 1233.2503 | 484.4793 | 739.5367 | 654.4012 | 567.0935 | 358.0625 | 120.3422 | 231.7424 | 981.9642 | 2382.2999 | 2430.3868 | 1309.1609 | 1672.8395 | 1833.481 | 489.2682 | 165.8348 | [5 empty] | 21017.6569
|  | Cummulative | [6 empty] | 22 | 42 | 61 | 75 | 78 | 80 | 83 | 99 | 129 | 159 | 170 | 186 | 200 | 213 | 220 | 222 | 228 | 251 | 303 | 350 | 375 | 408 | 448 | 459 | 463 | [5 empty] | 5324
| I. | Stringing | [36 empty] | 0
| I.1 | Stringing Conductor & Earthwire | KEC | Kms | 191 | 5: 5; 6: 12; 7: 12; 8: 12; 9: 18; 10: 25; 11: 25; 12: 25; 13: 25; 14: 20; 15: 12 | 191
|  | Actual | [8 empty] | 0 | 0 | 0 | 0 | 0 | 4.877 | 9.431 | 8.629 | 0 | 7.115 | 0 | 9.18 | 1.049 | 3.227 | 0 | 0 | 0 | 3.788 | 0 | 8.949 | 6.1341 | 14.1512 | 6.4065 | [5 empty] | 82.9367
|  | Cummulative | [8 empty] | 0 | 0 | 0 | 0 | 0 | 4.877 | 14.308 | 22.937 | 22.937 | 30.052 | 30.052 | 39.232 | 40.281 | 43.508 | 43.508 | 43.508 | 43.508 | 47.296 | 47.296 | 56.245 | 62.3791 | 76.5303 | 82.9367 | [5 empty] | 751.3911
| I.2 | OPGW Stringing | KEC | Kms | 191 | 8: 5; 9: 15; 10: 20; 11: 25; 12: 35; 13: 45; 14: 30; 15: 16 | 191
|  | Actual | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.423 | 8.629 | 0 | 0 | 0 | 5.493 | 4.058 | 0 | 0 | 0 | 14.057 | 10.6128 | 17.003 | [5 empty] | 81.2758
|  | Cummulative | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.423 | 30.052 | 30.052 | 30.052 | 30.052 | 35.545 | 39.603 | 39.603 | 39.603 | 39.603 | 53.66 | 64.2728 | 81.2758 | [5 empty] | 534.7966
| J. | Fixing Of Tower Accessories, aviation painting & installation of span marker | KEC | % | 100 | 13: 30%; 14: 30%; 15: 40% | 1
| K. | Checking, Testing & Commissioning/Ready for Commissioning | KEC | Kms. | 191 | 14: 50%; 15: 50% | 1
REMARKS
1 | Provisional Tower Quantities are 482 Nos.

## Hindrance Register (Row)
Progress Summary'!A1
HINDRANCE REGISTER (Note:- Day to day hindrance are captured on other sheet and intimate to resonia via DPR on Summary Sheet)
1 | Name of the Substation/TL/Project | 765 KV Fatehgarh-3 Beawer Transmission Line Part-F |  |  |  | 2. Name of Work |  | Transmission & Power Distribution
3 | Name of the Executing Agency | KEC International Limited |  |  |  | 3. LOA No. & Date |  | LOI/EPC/FBTL/PART-F/KEC/01 Dated 11.09.2023
Sr. No. | Activity | Total | Open | Close |  |  |  | Progress Summary'!A1
1 | Survey | 20 | 0 | 20
2 | Foundation | 210 | 1 | 209
3 | Erection | 87 | 17 | 70
4 | Stringing | 13 | 5 | 8
5 | Others | 3 | 0 | 3
Total |  | 333 | 23 | 310
Check Survey
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of 1st attempt | Date of removal (Last attempt) | Period of hindrance | Remarks
1 | Check survey not done due to frequent obstruction by land owner from 38/0 to 39/0. | 38-39 | Survey |  | 2023-12-06 | 2024-10-10 | 310 | Refer KEC letter dated 02-01-24. Reattempted on 09-01-24 but still in ROW. 3rd time attempted on dated 10.07.24 informed to you via mail regarding ROW.
2 | Check survey not done due to frequent obstruction by land owner from 39/0 to 40/0. | 39-40 | Survey |  | 2023-12-06 | 2024-10-10 | 310 | Refer KEC letter dated 02-01-24. Reattempted on 09-01-24 but still in ROW. 3rd time attempted on dated 10.07.24 informed to you via mail regarding ROW.
3 | Check survey is on hold from Gantry to 2/0 due to Non-Finalization of Gantry. | Gty-2 | Survey |  | 2023-12-06 | 2024-07-15 | 223 | Refer KEC letter dated 02-01-24.
4 | Check survey not done due to frequent obstruction by land owner from 10/12 to 11A. | 10/12-11A | Survey |  | 2023-12-06 | 2024-01-16 | 42 | Refer KEC letter dated 02-01-24.
5 | Check survey not done due to ROW from AP 20-AP 21. | 20-21 | Survey |  | 2023-12-06 | 2025-06-23 | 566 | Refer KEC letter dated 02-01-24. SPTL mail dated 20/5/24 having subject Optimization from GTY to AP74 (Part- F). Clearance for check survey received on 17.10.24. however survey team along with machinery idled at this section since 18th. Section is still in ROW. on dated 19.10.2024.
6 | Delay in approval of check survey report from Ap 21 to AP 25. | 21-25 | Survey |  | 2023-12-06 | 2023-12-14 | 9
7 | Delay in approval of check survey report from Ap 14 to AP 20. | 14-20 | Survey |  | 2023-12-06 | 2023-12-14 | 9
8 | ROW in check survey works. | 47-48 | Survey |  | 2023-12-12 | 2023-12-14 | 3
9 | ROW in check survey works. | 70-71 | Survey |  | 2023-12-15 | 2024-12-10 | 362
10 | ROW in check survey works. | 71-72 | Survey |  | 2023-12-15 | 2024-02-09 | 57
11 | ROW in check survey works. | 72-73 | Survey |  | 2023-12-15 | 2024-02-09 | 57
12 | ROW in check survey works. | 73-74 | Survey |  | 2023-12-15 | 2024-07-14 | 213
13 | Delay in approval of check survey report from Ap 32 to AP 37. | 32-37 | Survey |  | 2023-12-21 | 2023-12-29 | 9
14 | Delay in approval of check survey From AP 2-10/12 | 2-10/12 | Survey |  | 2023-12-26 | 2024-01-25 | 31 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
15 | Delay in approval of check survey From AP 11A-14. | 11A-14 | Survey |  | 2023-12-26 | 2024-01-25 | 31 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
16 | Location no 11/5 are on Hold due to ROW during check survey, Centre peg not done for verification of benching and others. | 11/5 | Survey |  | 2024-01-17 | 2024-05-20 | 125 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
17 | Location no 11A/0 are on Hold due to ROW during check survey, Centre peg not done for verification of benching and others. | 11A/0 | Survey |  | 2024-01-17 | 2024-05-20 | 125 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
18 | ROW in check survey works. | 40-41 | Survey |  | 2024-01-27 | 2024-04-08 | 73
19 | ROW in check survey works. | 41-42 | Survey |  | 2024-01-27 | 2024-04-08 | 73
20 | ROW in check survey works. | 42-43 | Survey |  | 2024-01-27 | 2024-04-08 | 73
Foundation
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
0 | ROW due to obstruction by land owner at Loc No 37/2. Post Excavation work was stopped by Land owners. After that cleared on 07/12/2023. | 37/2 | Foundation | Nagana Rai | 2023-12-06 | 2023-12-07 | 2
0 | ROW encountered in Excavation works. | 62/6 | Foundation |  | 2023-12-14 | 2023-12-15 | 2
0 | ROW due to obstruction by land owner at Loc No 26/2. | 26/2 | Foundation | A.B. Construction | 2023-12-16 | 2023-12-17 | 2 | Refer Mail dated 16/12/2023.
0 | Our Whole team of one gang along with its machinery are completely idle at location no 26/2 | 26/2 | Foundation | A.B. Construction | 2023-12-16 | 2023-12-17 | 2 | Idled Resources (Highly Skilled manpower-1, Skilled:- 2, Semi Skilled:- 3, Unskilled:- 4, JCB with operator:- 1, Azax flori with operator:- 1, Tracktor with operator:- 1, Tanker with Operator:- 1, Bolero/Camper with Diesel:- 1)
0 | ROW at Location No 27/11. | 27/11 | Foundation | Nagana Rai | 2023-12-06 | 2024-02-12 | 69 | Email dated 18/1/24 regarding Frequent obstruction by landowners. Your email dated 12.02.24 regarding workfront
0 | ROW at location no 28/1 due to frequent interupption by land owner of PKG F. | 28/1 | Foundation | N.R. Enterprises | 2023-12-26 | 2025-06-11 | 534 | Reference Email dated 26/12/2023.
0 | Gang is idled for full day. During idling attempted 5 nos locations to start the work. But all are found in ROW. |  | Foundation | N.R. Enterprises | 2023-12-26 | 2023-12-29 | 4 | Reference Email dated 26/12/2023. Idled Resources (Highly Skilled manpower-1, Skilled:- 2, Semi Skilled:- 3, Unskilled:- 5, JCB with operator:- 1, Azax flori with operator:- 1, Tracktor with operator:- 1, Tanker with Operator:- 1, Bolero/Camper with Diesel:- 1)
0 | ROW in Foundation work in sawan Moolraj village at Loc No 28/2 | 28/2 | Foundation |  | 2023-12-26 | 2024-01-27 | 33 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 28/3 | 28/3 | Foundation |  | 2023-12-26 | 2025-02-03 | 406 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 28/4 | 28/4 | Foundation |  | 2023-12-26 | 2025-02-03 | 406 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 28/5 | 28/5 | Foundation |  | 2023-12-26 | 2025-01-22 | 394 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 28/6 | 28/6 | Foundation |  | 2023-12-26 | 2024-01-16 | 22 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 28/7 | 28/7 | Foundation |  | 2023-12-26 | 2025-01-30 | 402 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 28/8 | 28/8 | Foundation |  | 2023-12-26 | 2025-01-25 | 397 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 29/0 | 29/0 | Foundation |  | 2023-12-26 | 2025-01-11 | 383 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 29/1 | 29/1 | Foundation |  | 2023-12-26 | 2025-02-22 | 425 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 29/2 | 29/2 | Foundation |  | 2023-12-26 | 2025-03-01 | 432 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 29/3 | 29/3 | Foundation |  | 2023-12-26 | 2025-03-02 | 433 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 29/4 | 29/4 | Foundation |  | 2023-12-26 | 2025-02-20 | 423 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 30/0 | 30/0 | Foundation |  | 2023-12-26 | 2025-02-13 | 416 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 30/1 | 30/1 | Foundation |  | 2023-12-26 | 2025-02-15 | 418 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 30/2 | 30/2 | Foundation |  | 2023-12-26 | 2025-02-28 | 431 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 30/3 | 30/3 | Foundation |  | 2023-12-26 | 2025-02-25 | 428 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 30/4 | 30/4 | Foundation |  | 2023-12-26 | 2025-05-21 | 513 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 30/5 | 30/5 | Foundation |  | 2023-12-26 | 2025-05-30 | 522 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 30/6 | 30/6 | Foundation |  | 2023-12-26 | 2025-06-10 | 533 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 31/0 | 31/0 | Foundation |  | 2023-12-26 | 2025-06-23 | 546 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 31/1 | 31/1 | Foundation |  | 2023-12-26 | 2025-03-05 | 436 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 31/2 | 31/2 | Foundation |  | 2023-12-26 | 2025-03-02 | 433 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW in Foundation work in sawan Moolraj village at Loc No 32/0 | 32/0 | Foundation |  | 2023-12-26 | 2025-02-26 | 429 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
0 | ROW encountered while pit marking. | 59/15 | Foundation |  | 2024-01-11 | 2024-01-15 | 5
0 | ROW encountered while pit marking. | 59/16 | Foundation |  | 2024-01-11 | 2024-01-15 | 5
0 | ROW encountered while pit marking. | 60/3 | Foundation |  | 2024-01-11 | 2024-01-13 | 3
0 | ROW encountered while pit marking. | 60/4 | Foundation |  | 2024-01-11 | 2024-01-13 | 3
0 | ROW encountered while pit marking. | 60/11 | Foundation |  | 2024-01-13 | 2024-01-19 | 7
0 | Shifting of 11 KV Line in Location No 26/4 as 11 KV Line pass through centre of the Pit D. | 26/4 | Foundation |  | 2024-01-20 | 2024-01-23 | 4 | Email dated 20/01/2024 regarding shifting of 11 KV Line. On dated 23/1/24, FDN location 5 Mtr shifted towards 26/3 for execution of Foundation works.
0 | Excavation work stopped at 28/2 after completion of 3 Pit excavation works due to ROW. | 28/2 | Foundation | A.B. Construction | 2024-01-28 | 2024-02-12 | 16 | D.P.R. Dated 28-01-24. 10 Nos Manpower are idled due to this hindrances (confirmed by D.P.R. Dated 29.01.2024), Your email dated 12.02.24 regarding workfront
0 | ROW encountered during excavation . | 64/10 | Foundation |  | 2024-02-01 | 2024-02-07 | 7
0 | Excavation work could not done at 27/5 after completion of 3 Pit excavation works due to ROW. | 27/5 | Foundation | Majisa Construction | 2024-02-02 | 2024-03-05 | 33 | DPR dated 03.02.24. Email dated 22.02.24 Sterlite's Part G & F 765KV Fategarh -III Beawar TL
0 | Excavation work could not done at 27/6 due to ROW. | 27/6 | Foundation | Majisa Construction | 2024-02-08 | 2024-05-07 | 90
0 | Excavation work could not done at 27/7 due to ROW. | 27/7 | Foundation | Majisa Construction | 2024-02-08 | 2025-05-18 | 466
0 | Excavation work could not done at 32/1 due to ROW. | 32/1 | Foundation |  | 2024-02-08 | 2025-02-28 | 387
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 32/2 | Foundation |  | 2024-02-08 | 2025-02-07 | 366
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 32/3 | Foundation |  | 2024-02-08 | 2025-02-03 | 362
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 32/4 | Foundation |  | 2024-02-08 | 2025-02-03 | 362
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 33/0 | Foundation |  | 2024-02-08 | 2025-02-12 | 371
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 33/1 | Foundation |  | 2024-02-08 | 2025-01-31 | 359
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/0 | Foundation |  | 2024-02-08 | 2025-01-27 | 355
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/1 | Foundation |  | 2024-02-08 | 2025-01-05 | 333
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/2 | Foundation |  | 2024-02-08 | 2025-01-16 | 344
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/3 | Foundation |  | 2024-02-08 | 2024-02-14 | 7 | Email dated 14.01.2024 regarding KEC - Sterlite's Part G & F 765KV Fategarh -III Beawar TL
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/4 | Foundation |  | 2024-02-08 | 2025-02-15 | 374
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/0 | Foundation |  | 2024-02-08 | 2025-01-02 | 330
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/1 | Foundation |  | 2024-02-08 | 2025-03-20 | 407
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/2 | Foundation |  | 2024-02-08 | 2025-01-03 | 331
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/3 | Foundation |  | 2024-02-08 | 2025-01-30 | 358 | Your email dated 12.02.24 regarding workfront. This locations is reattempted on 28.01.2024 after verbal communication by SPTL by the location found in ROW. Again SPTL claimed that ROW cleared on 30.01.25.
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/4 | Foundation |  | 2024-02-08 | 2024-02-12 | 5 | Your email dated 12.02.24 regarding workfront
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/5 | Foundation |  | 2024-02-08 | 2025-01-27 | 355
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 36/0 | Foundation |  | 2024-02-08 | 2024-02-12 | 5 | Your email dated 12.02.24 regarding workfront
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 36/2 | Foundation |  | 2024-02-08 | 2025-05-31 | 479
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 36/3 | Foundation |  | 2024-02-08 | 2025-05-31 | 479
0 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 36/4 | Foundation |  | 2024-02-08 | 2025-05-31 | 479
0 | ROW in Excavation as Landowner not allowing for pit marking. | 26/7 | Foundation | Mehai Construction | 2024-02-19 | 2024-12-30 | 316 | DPR of 19.02.24. Email dated Sterlite's Part G & F 765KV Fategarh -III Beawar TL.
0 | ROW in Pit marking as Landowner not allowing for pit marking. | 26/8 | Foundation | Mehai Construction | 2024-02-19 | 2025-10-28 | 618 | DPR of 19.02.24. Email dated Sterlite's Part G & F 765KV Fategarh -III Beawar TL. Cleared on 28.10.2025.
1 | ROW in Pit marking by Landowner. Further nearby location 22/0 excavation not done due to ROW. Excavator machine is standing idle. He committed to increase the gang strength but due to non-availability of clear work front they have planned to reduce the strength if locations not allocated timely. | 22/0 | Foundation |  | 2024-02-18 | 2025-11-07 | 629 | DPR of 19.02.24. Email dated Sterlite's Part G & F 765KV Fategarh -III Beawar TL. Email dated 25.02.24 regarding Workfront Delays and Local Villager Interruptions in PKG G & PKG F. further, Clearances for this locations is received on 20.08.2025 at nearby 04:00 PM under police protection, However on dated 23.08.2025 the locations again falls under ROW when landowners creating issues. Cleared on dated 04.10.2025 with the help of police administration. Excavation WIP in 2nd pit. from 10.10.2025.Further from 11.10.2025 Locs is in ROW. and then cleared on 13.10.2025. against Excavation started in all Pit started from 11.10.2025. further Slow progress due to ROCK encountered. No work done due to ROW from 15.10.2025 Machinery idled. 2nos Poklain idle since 15.10.2025. ROW Cleared on 07.11.2025
1 | ROW encountered during excavation . | 61/10 | Foundation |  | 2024-02-19 | 2024-02-29 | 11
1 | ROW encountered during excavation . | 61/4 | Foundation |  | 2024-02-19 | 2024-02-29 | 11
1 | ROW encountered while pit marking. | 62/0 | Foundation |  | 2024-02-19 | 2024-02-29 | 11
1 | Pit marking not done due to cultivated land and SPTL not allowing for further pit marking. | 21/9 | Foundation |  | 2024-02-22 | 2025-05-13 | 447 | D.P.R. Dated 22.02.24
1 | Gang was shifted after completion of location no 23/1 (G) on dated 22.02.24 but due to non-availability of nearby Workfront gang is shifted at 22/5 after one day idling at 22/5. on a progress front he have not worked any productivity till today after 23rd Feb. his time is lapsed on shifting of gang and machinery. |  | Foundation | A.B. Construction | 2024-02-25 | 2024-02-26 | 2 | Email dated 25.02.24 regarding Workfront Delays and Local Villager Interruptions in PKG G & PKG F
1 | Due to interruptions by landowners works are stopped. and gang is completely idle along with machinery. (this team have ability to execute the works in two locations at a time). | 26/6 | Foundation | Mehai Contruction | 2024-02-25 | 2024-02-26 | 2 | Email dated 25.02.24 regarding Workfront Delays and Local Villager Interruptions in PKG G & PKG F
1 | Gang idled due to clear workfront not available after completion of 26/6. | 26/6 | Foundation | Mehai Construction | 2024-03-01 | 2024-03-04 | 4 | Email dated 02/03/24 regarding Survey & Foundation update (Workfront Delay/Interruptions updates in PKG G & PKG F
1 | 22/1:- Completed today. Machinery idled due to Nearby locations not available. Further Gang left the site due to workfront not available. | 22/1 | Foundation | Swarup Enterprises | 2024-03-02 | 2024-03-03 | 2 | Email dated 02/03/24 regarding Survey & Foundation update (Workfront Delay/Interruptions updates in PKG G & PKG F
1 | ROW encountered while pit marking. | 53/6 | Foundation |  | 2024-03-06 | 2024-05-24 | 80
1 | ROW encountered while pit marking. | 53/7 | Foundation |  | 2024-03-06 | 2024-04-04 | 30
1 | ROW encountered while pit marking. | 53/8 | Foundation |  | 2024-03-06 | 2024-04-04 | 30
1 | ROW encountered while pit marking. | 54/0 | Foundation |  | 2024-03-06 | 2024-05-24 | 80
1 | ROW encountered while pit marking. | 54/1 | Foundation |  | 2024-03-06 | 2024-05-24 | 80
1 | ROW encountered while pit marking. | 54/2 | Foundation |  | 2024-03-06 | 2024-05-24 | 80
2 | SPTL representatives not aggreed to start pit marking along with Excavation against clear workfront shared on may'10 at loc no 8/8 (F) | 8/8 | Foundation | Mateshwari Construction/HS Engineering | 2024-05-17 | 2026-02-08 | 633 | Gang idled from 14.11.2024 to 16.11.2024 after 2nd attampt. After idling SPTL allocate other locations.
2 | Works stopped due to ROW by landowners at location No 10/13. | 10/13 | Foundation | Mateshwari Construction | 2024-05-04 | 2024-05-04 | 1
2 | Works stopped due to ROW by landowners at location No 10/12. | 10/12 | Foundation | Mateshwari Construction | 2024-05-14 | 2024-06-16 | 34 | Reference daily progress report.
2 | Works not started due to ROW. | 10/9 | Foundation | Jai Bhawani | 2024-07-04 | 2024-08-07 | 35
2 | Works not started due to ROW. | 10/10 | Foundation | Jai Bhawani | 2024-07-04 | 2025-10-02 | 456
2 | Works not started due to ROW. | 10/21 | Foundation | Jai Bhawani | 2024-07-04 | 2024-07-07 | 4
2 | Works not started due to ROW. | 14A/2 | Foundation | Majisa Construction | 2024-07-04 | 2024-09-07 | 66
2 | Works not started due to ROW. | 15/0 | Foundation | Majisa Construction | 2024-07-04 | 2024-07-07 | 4
2 | No work-done due to Continuous rain at location | 10/3 | Foundation | Jai Bhawani | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
2 | No work-done due to Continuous rain at location | 10/4 | Foundation | Jai Bhawani | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
2 | No work-done due to Continuous rain at location | 11A/7 | Foundation | Punia Construction | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
2 | No work-done due to Continuous rain at location | 16/3 | Foundation | Majisa Construction | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
2 | No work-done due to Continuous rain at location | 18/2 | Foundation | Vibe infra | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
2 | No work-done due to Continuous rain at location | 17/3 | Foundation | J.P. Infra | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
2 | No work-done due to Continuous rain at location | 43/9 | Foundation | N.R. Enterprises | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
2 | Works stopped due to ROW at loc no 16/1. | 16/1 | Foundation | Om Enterprise | 2024-08-24 | 2024-08-25 | 2 | DPR email on regular basis.
2 | Works stopped due to ROW at loc no 43/7 | 43/7 | Foundation | N.R. Enterprises | 2024-08-27 | 2024-08-30 | 4 | DPR email on regular basis.
2 | Full day ROW. 9 nos manpower alongwith JCB (JCB idled since last 6 days). ROW cleared after 2nd half on dated 29.09.2024 | 19/3 | Foundation | Vibe infra | 2024-09-28 | 2024-09-29 | 2 | DPR email on regular basis.
2 | ROW encountered while pit marking. | 65/7 | Foundation |  | 2024-10-10 | 2024-11-11 | 33
2 | ROW encountered while pit marking. | 65/8 | Foundation |  | 2024-10-10 | 2024-11-11 | 33
2 | ROW encountered while pit marking. | 65/10 | Foundation |  | 2024-10-10 | 2025-01-22 | 105
2 | ROW encountered while pit marking. | 68/0 | Foundation |  | 2024-10-10 | 2025-01-13 | 96
2 | ROW encountered while pit marking. | 55/0 | Foundation |  | 2024-10-10 | 2025-01-13 | 96
2 | ROW encountered while pit marking. | 55/1 | Foundation |  | 2024-10-10 | 2025-01-13 | 96
2 | ROW encountered while pit marking. | 55/2 | Foundation |  | 2024-10-10 | 2025-01-13 | 96
2 | ROW encountered while pit marking. | 71/1 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
2 | ROW encountered while pit marking. | 71/2 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
2 | ROW encountered while pit marking. | 71/3 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
2 | ROW encountered while pit marking. | 71/4 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
2 | ROW encountered while pit marking. | 71/5 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
2 | ROW encountered while pit marking. | 71/8 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
2 | ROW encountered while pit marking. | 72/0 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
2 | ROW encountered while pit marking. | 72/1 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
2 | Machinery stucked at location due to ROW, idled (machinery alongwith Gang) till 3 PM on dated 15.10.24. ROW resolved at 03:00 PM. | 22/12 | Foundation | RBM | 2024-10-14 | 2024-10-15 | 2 | DPR email on regular basis.
2 | Full day ROW from 13/3 G & 12/0 F. | 13/3, 12/0 | Foundation | Punia Construction | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis.
3 | work could not started due to ROW. | 13/4 | Foundation |  | 2024-11-01 | 2025-11-11 | 376 | DPR email on regular basis. During execution post excavation ROW encountered from 14.07.2025 to till date, Thus earlier cleared date is revised. No work done due to ROW post Excavation, ROW since 14.07.25 to 13.10.2025. Row Cleared on 13.10.2025 by late evening. Further when the gang shifted at location, The location is stiil in ROW. Chandrapal Gang is idle from 14.10.2025 to 29.10.2025. They have arranged all the constrcution materials but due to non clearance, Gang demobilized from site. Cleared on dated 11.11.25 with the support of police admin.
3 | work could not started due to ROW. | 14A/0 | Foundation |  | 2024-11-01 | 2025-06-15 | 227 | DPR email on regular basis.
3 | Excavation can't be started due to ROW. | 22/9 | Foundation |  | 2024-11-17 | 2024-12-01 | 15 | DPR email on regular basis.
3 | Excavation can't be started due to ROW in approach road. | 22/4 | Foundation | J.P. Infra | 2024-11-18 | 2024-11-20 | 3 | DPR email on regular basis.
3 | Excavation can't be started due to ROW. | 6/1 & 6/2 | Foundation | H.s Engineering | 2024-11-18 | 2024-11-20 | 3 | DPR email on regular basis.
3 | Works Stopped due to ROW. | 22/10 | Foundation | RBM | 2024-12-09 | 2025-09-10 | 276 | DPR email on regular basis. ROW issues in approach road is resloved on dated 10.09.2025. Post clearance received for work was received on 21.07.2025 during attempeted locs falls under ROW in approach. and approach was cleared on 10.09.2025.
3 | No work done due to ROW by local persons. Gang Idle till 19.12.2024. Further nex location allaocted 8/9 in PKG G. | 6/2 | Foundation | HS Engineering | 2024-12-11 | 2024-12-19 | 9 | DPR email on regular basis.
3 | Works Stopped due to ROW. | 35/4 | Foundation | Parsuram Sahi | 2024-12-30 | 2024-12-30 | 1 | DPR email on regular basis.
3 | Work can't started due to ROW. | 1/0 | Foundation |  | 2024-12-02 | 2025-02-23 | 84 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 1A/0 | Foundation |  | 2024-12-02 | 2025-01-12 | 42 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 1A/1 | Foundation |  | 2024-12-02 | 2025-01-13 | 43 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 1A/2 | Foundation |  | 2024-12-02 | 2025-01-21 | 51 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 1A/3 | Foundation |  | 2024-12-02 | 2025-01-16 | 46 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 1A/4 | Foundation |  | 2024-12-02 | 2025-01-15 | 45 | Informed to SPTL by mail Communications. This locations is reattmpetd in 28.01.25 after pit marking the locations is found under ROW.
3 | Work can't started due to ROW. | 1A/5 | Foundation |  | 2024-12-02 | 2025-01-22 | 52 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 1A/6 | Foundation |  | 2024-12-02 | 2025-01-21 | 51 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 1A/7 | Foundation |  | 2024-12-02 | 2025-02-26 | 87 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 1A/8 | Foundation |  | 2024-12-02 | 2025-05-02 | 152 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 2/0 | Foundation |  | 2024-12-02 | 2025-01-14 | 44 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 2/1 | Foundation |  | 2024-12-03 | 2025-03-12 | 100 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 2/7 | Foundation |  | 2024-12-03 | 2025-06-05 | 185 | Informed to SPTL by mail Communications, Initially ROW resolved on 30th May 2025, Further during execution, ROW encountered on datedx 04.06.2025
3 | Work can't started due to ROW. | 2/8 | Foundation |  | 2024-12-03 | 2025-02-04 | 64 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 2/9 | Foundation |  | 2024-12-03 | 2025-06-03 | 183 | Informed to SPTL by mail Communications. Work stopped after casting of 2 pit.
3 | Work can't started due to ROW. | 3/0 | Foundation |  | 2024-12-03 | 2025-04-12 | 131 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 4/0 | Foundation |  | 2024-12-18 | 2025-02-18 | 63 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 4/1 | Foundation |  | 2024-12-18 | 2025-04-28 | 132 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 4/2 | Foundation |  | 2024-12-18 | 2025-06-23 | 188 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 4/3 | Foundation |  | 2024-12-18 | 2025-05-13 | 147 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 4/4 | Foundation |  | 2024-12-18 | 2025-06-25 | 190 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 5/0 | Foundation |  | 2024-12-18 | 2025-08-17 | 243 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 6/0 | Foundation |  | 2024-12-18 | 2025-07-26 | 221 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 7/0 | Foundation |  | 2024-12-18 | 2025-09-12 | 269 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 8/0 | Foundation |  | 2024-12-07 | 2025-07-09 | 215 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 8/1 | Foundation |  | 2024-12-07 | 2025-07-06 | 212 | Informed to SPTL by mail Communications
3 | Work can't started due to ROW. | 8/2 | Foundation |  | 2024-12-07 | 2025-06-15 | 191 | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
3 | Work can't started due to ROW. | 8/3 | Foundation |  | 2024-12-07 | 2025-10-09 | 307 | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
3 | Work can't started due to ROW. | 8/4 | Foundation |  | 2024-12-07 | 2025-07-22 | 228 | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
3 | Work can't started due to ROW. | 8/5 | Foundation |  | 2024-12-07 | 2025-06-19 | 195 | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
4 | Work can't started due to ROW. | 8/6 | Foundation |  | 2024-12-07 | 2026-02-15 | 436 | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
4 | Work can't started due to ROW. | 8/11 | Foundation |  | 2024-12-07 | 2025-05-12 | 157 | Informed to SPTL by mail Communications
4 | Work can't started due to ROW. | 8/12 | Foundation |  | 2024-12-07 | 2025-05-12 | 157 | Informed to SPTL by mail Communications
4 | Work can't started due to ROW. | 9/0 | Foundation |  | 2024-12-07 | 2025-07-06 | 212 | Informed to SPTL by mail Communications
4 | Work can't started due to ROW. | 10/0 | Foundation |  | 2024-12-07 | 2025-05-14 | 159 | Informed to SPTL by mail Communications
4 | Work can't started due to ROW. | 10/1 | Foundation |  | 2024-12-07 | 2025-05-16 | 161 | Informed to SPTL by mail Communications
5 | Work can't started due to ROW. | 10/2 | Foundation |  | 2024-12-07 | 2026-01-31 | 421 | Informed to SPTL by mail Communications.
5 | Work can't started due to ROW. | 10/7 | Foundation |  | 2024-12-07 | 2025-07-13 | 219 | Informed to SPTL by mail Communications. '10/7 (No work done due to ROW, ROW since 20.07.25)
5 | Work can't started due to ROW. | 10/15 | Foundation |  | 2024-12-07 | 2025-09-14 | 282 | Informed to SPTL by mail Communications
5 | Work can't started due to ROW. | 10/16 | Foundation |  | 2024-12-07 | 2025-09-06 | 274 | Informed to SPTL by mail Communications
6 | Work can't started due to ROW. | 10/22 | Foundation |  | 2024-12-07 | 2025-12-06 | 365 | Informed to SPTL by mail Communications. During work progress got interupputed on dated 05.12.2025. informed via DPR and respective whatsapp group.
6 | Work can't started due to ROW. | 10/23 | Foundation |  | 2024-12-07 | 2025-09-29 | 297 | Informed to SPTL by mail Communications
6 | Work can't started due to ROW. | 11/0 | Foundation |  | 2024-12-07 | 2025-09-06 | 274 | Informed to SPTL by mail Communications
6 | Work can't started due to ROW. | 11/1 | Foundation |  | 2024-12-07 | 2025-08-02 | 239 | Informed to SPTL by mail Communications
6 | Work can't started due to ROW. | 11/2 | Foundation |  | 2024-12-07 | 2025-08-16 | 253 | Informed to SPTL by mail Communications
6 | Work can't started due to ROW. | 11/3 | Foundation |  | 2024-12-07 | 2025-09-15 | 283 | Informed to SPTL by mail Communications
6 | Work can't started due to ROW. | 11/4 | Foundation |  | 2024-12-07 | 2025-06-06 | 182 | Informed to SPTL by mail Communications
6 | Work can't started due to ROW. | 19/4 | Foundation |  | 2024-12-07 | 2025-10-04 | 302 | Informed to SPTL by mail Communications. Cleared on dated 04.10.2025 with the help of police administration.
6 | Work can't started due to ROW. | 19/5 | Foundation |  | 2024-12-07 | 2025-06-01 | 177 | Informed to SPTL by mail Communications
6 | Work can't started due to ROW. | 20/0 | Foundation |  | 2024-12-17 | 2025-07-04 | 200 | Informed to SPTL by mail Communications
6 | Work can't started due to ROW. | 20/1 | Foundation |  | 2024-12-17 | 2025-09-04 | 262 | Informed to SPTL by mail Communications, clearances for this locations is received on 20.08.2025 at nearby 04:00 PM under police protection, However on dated 23.08.2025 the locations again falls under ROW when landowners creating issues. Location resolved on 04.09.2025.
6 | Work can't started due to ROW. | 20/2 | Foundation |  | 2024-12-17 | 2025-07-20 | 216 | Informed to SPTL by mail Communications
6 | Work can't started due to ROW. | 20/3 | Foundation |  | 2024-12-17 | 2025-07-23 | 219 | Informed to SPTL by mail Communications
6 | Work can't started due to ROW. | 21/0 | Foundation |  | 2024-12-17 | 2025-07-21 | 217 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 21/1 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications. All the activity of 2 leg is completed on 01.11.2025, Further last pit not done due to ROW.
7 | Work can't started due to ROW. | 21/2 | Foundation |  | 2024-12-17 | 2025-07-25 | 221 | Informed to SPTL by mail Communications, ROW in approach road when location attempted at 22.06.2025. ROW in approach Road, ROW since 28.06.2025. Final ROW cleared on 25.07.2025.
7 | Work can't started due to ROW. | 21/3 | Foundation |  | 2024-12-17 | 2025-06-21 | 187 | Informed to SPTL by mail Communications. Reattempted on 23.05.2025 but the locations still persist in ROW.
7 | Work can't started due to ROW. | 21/4 | Foundation |  | 2024-12-17 | 2025-06-10 | 176 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 21/5 | Foundation |  | 2024-12-17 | 2025-05-29 | 164 | Informed to SPTL by mail Communications, tried on 07.05.25 also after pit marking location is in ROW then Excavation started on loc no 21/7.
7 | Work can't started due to ROW. | 21/6 | Foundation |  | 2024-12-17 | 2025-10-26 | 314 | Informed to SPTL by mail Communications. Cleared on dated 04.10.2025 with the help of police administration. Excavation in all Pit started from 11.10.2025. further Slow progress due to ROCK encountered. No work done due to ROW from 15.10.2025 Machinery idled. 2nos Poklain idle since 15.10.2025. Finally cleared on 26.10.2025.
7 | Work can't started due to ROW. | 21/7 | Foundation |  | 2024-12-17 | 2025-05-07 | 142 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 21/8 | Foundation |  | 2024-12-17 | 2025-10-03 | 291 | Informed to SPTL by mail Communications. clearances for this locations is received on 20.08.2025 at nearby 04:00 PM under police protection, However on dated 23.08.2025 the locations again falls under ROW when landowners creating issues. Cleared in presence of police administrator on dated 03.10.2025.
7 | Work can't started due to ROW. | 23/0 | Foundation |  | 2024-12-17 | 2025-07-30 | 226 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 24/0 | Foundation |  | 2024-12-13 | 2025-07-20 | 220 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 26/0 | Foundation |  | 2024-12-13 | 2025-07-11 | 211 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 26/1 | Foundation |  | 2024-12-13 | 2025-08-01 | 232 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 27/0 | Foundation |  | 2024-12-13 | 2025-05-06 | 145 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 27/1 | Foundation |  | 2024-12-13 | 2025-05-02 | 141 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 27/2 | Foundation |  | 2024-12-13 | 2025-04-16 | 125 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 27/3 | Foundation |  | 2024-12-13 | 2025-04-11 | 120 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 27/4 | Foundation |  | 2024-12-13 | 2025-05-12 | 151 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 37/0 | Foundation |  | 2024-12-13 | 2025-06-23 | 193 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 37/1 | Foundation |  | 2024-12-13 | 2025-06-28 | 198 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 37/3 | Foundation |  | 2024-12-13 | 2025-04-18 | 127 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 38/0 | Foundation |  | 2024-12-13 | 2025-04-15 | 124 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 38/1 | Foundation |  | 2024-12-13 | 2025-04-21 | 130 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 38/2 | Foundation |  | 2024-12-15 | 2025-04-16 | 123 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 38/3 | Foundation |  | 2024-12-15 | 2025-05-12 | 149 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 38/4 | Foundation |  | 2024-12-15 | 2025-04-05 | 112 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 39/0 | Foundation |  | 2024-12-15 | 2025-04-11 | 118 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 39/1 | Foundation |  | 2024-12-15 | 2025-04-28 | 135 | Informed to SPTL by mail Communications. Reattempted on 25.06.2025.
7 | Work can't started due to ROW. | 40/0 | Foundation |  | 2024-12-15 | 2025-04-28 | 135 | Informed to SPTL by mail Communications. Work started on 26.04.2025 further during excavation works are stopped the land owners.
7 | Work can't started due to ROW. | 40/1 | Foundation |  | 2024-12-15 | 2025-05-02 | 139 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 40/3 | Foundation |  | 2024-12-15 | 2025-05-18 | 155 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 41/0 | Foundation |  | 2024-12-15 | 2025-04-20 | 127 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 41/1 | Foundation |  | 2024-12-15 | 2025-05-21 | 158 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 42/4 | Foundation |  | 2024-12-15 | 2025-05-16 | 153 | Informed to SPTL by mail Communications
7 | Work can't started due to ROW. | 43/10 | Foundation |  | 2024-12-15 | 2025-02-16 | 64 | Informed to SPTL by mail Communications
7
Erection
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
1 | Gang idle due to ROW at 10/19 | 10/19 | Erection | Yogender Mahto | 2024-09-10 | 2024-09-12 | 3 | DPR email on regular basis.
2 | Rafikul Islam:- 11A/0 WIP. No work due to ROW. | 11A/0 | Erection | Rafikul Islam | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis.
3 | Jailal ageria:- 16/0 WIP. No work due to ROW. | 16/0 | Erection | Jailal Ageria | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis.
4 | Nirmal Mahto:- 16/2 WIP. No work due to ROW. | 16/2 | Erection | Nirmal Mahto | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis.
5 | work could not started due to ROW. | 14A/2 | Erection |  | 2024-11-01 | 2025-12-31 | 426 | DPR email on regular basis.
6 | work could not started due to ROW. | 15/0 | Erection |  | 2024-11-01 |  | Awaited | DPR email on regular basis.
7 | work could not started due to ROW. | 17/4 | Erection |  | 2024-11-02 | 2025-04-12 | 162 | DPR email on regular basis.
8 | work could not started due to ROW. | 17/5 | Erection | Bina Devi | 2024-11-02 | 2024-11-23 | 22 | DPR email on regular basis. Gang reattempted on dated 22.11.24 after allocating by SPTL, but ROW is still not resolved. And gang is being idle.
9 | work could not started due to ROW. | 18/0 | Erection |  | 2024-11-02 | 2025-08-16 | 288 | DPR email on regular basis.
10 | 13/1 WIP. No work due to ROW. | 13/1 | Erection | Jailal Ageria | 2024-11-26 | 2025-12-12 | 382 | DPR email on regular basis.
11 | Works Stopped due to ROW. | 13/0 | Erection | Jailal Agerai | 2024-12-30 |  | Awaited | DPR email on regular basis. Work stopped after completion of 1st Section.
12 | Works Stopped due to ROW. | 11A/5 | Erection | Deglal Mahto | 2024-12-30 | 2024-12-31 | 2 | DPR email on regular basis.
13 | Work can't started due to ROW. | 10/5 | Erection |  | 2025-01-01 | 2025-12-23 | 357 | Informed to SPTL by mail Communications
14 | Work can't started due to ROW. | 11A/4 | Erection |  | 2025-01-01 |  | Awaited | Informed to SPTL by mail Communications
15 | Work can't started due to ROW. | 11A/8 | Erection |  | 2025-01-01 | 2025-12-05 | 339 | Informed to SPTL by mail Communications
16 | Work can't started due to ROW. | 12/0 | Erection |  | 2025-01-01 | 2025-07-20 | 201 | Informed to SPTL by mail Communications
17 | Work can't started due to ROW. | 13/3 | Erection |  | 2025-01-01 | 2025-12-16 | 350 | Informed to SPTL by mail Communications
18 | Work can't started due to ROW. | 14/0 | Erection |  | 2025-01-01 | 2025-12-16 | 350 | Informed to SPTL by mail Communications
19 | Work can't started due to ROW. | 18/3 | Erection |  | 2025-01-01 | 2025-07-14 | 195 | Informed to SPTL by mail Communications
20 | Work can't started due to ROW. | 19/1 | Erection |  | 2025-01-01 |  | Awaited | Informed to SPTL by mail Communications
21 | Work can't started due to ROW. | 19/2 | Erection |  | 2025-01-01 | 2025-10-20 | 293 | Informed to SPTL by mail Communications
22 | Work can't started due to ROW. | 1A/5 | Erection | Kewat | 2025-07-24 | 2025-07-25 | 2 | No work done due to ROW. Earlier work is going on Cage. Cleared on 25.07.2025 (Today).
23 | Work can't started due to ROW. | 11/4 | Erection | Anjali Enterprises | 2025-07-25 | 2025-10-20 | 88 | Informed to SPTL by mail Communications, additional mail having subject Frequent obstruction (ROW) in Both the Package (G & F) dated 25.07.2025 sent by partho pal. Gang idle 21 manpower incl truck and T&P.
24 | Work can't started due to ROW. | 27/6 | Erection | Pusplata_Rajaram | 2025-08-06 | 2025-12-02 | 119 | Please refer daily progress report. Email dated 07.08.2025 having subject delay in unloading of tower parts
25 | Work can't started due to ROW. | 19/4 | Erection |  | 2025-11-01 | 2025-12-18 | 48 | Location cleared on 18.12.25 after idling of 5 hours of truck.
26 | Work can't started due to ROW. | 8/7 | Erection |  | 2025-08-12 | 2026-02-24 | 197 | Please refer daily progress report.
27 | Work can't started due to ROW. | 8/11 | Erection |  | 2025-08-12 | 2026-02-18 | 191 | Please refer daily progress report.
28 | Work can't started due to ROW. | 27/10 | Erection | Pusplata_Ramchandra | 2025-08-29 | 2025-12-26 | 120 | Please refer daily progress report.
29 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/11 | Erection |  | 2025-08-30 | 2025-12-26 | 119 | Please refer daily progress report.
30 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/12 | Erection |  | 2025-08-30 |  | Awaited | Please refer daily progress report.
31 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/13 | Erection |  | 2025-08-30 |  | Awaited | Please refer daily progress report.
32 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 23/0 | Erection |  | 2025-08-30 |  | Awaited | Please refer daily progress report.
33 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 25/0 | Erection |  | 2025-08-30 | 2026-01-21 | 145 | Please refer daily progress report.
34 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 25/1 | Erection |  | 2025-08-30 |  | Awaited | Please refer daily progress report.
35 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 25/2 | Erection |  | 2025-08-30 | 2026-01-03 | 127 | Please refer daily progress report.
36 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 26/1 | Erection |  | 2025-08-30 | 2025-09-06 | 8 | Please refer daily progress report.
37 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 26/4 | Erection |  | 2025-08-30 | 2026-01-29 | 153 | Please refer daily progress report.
38 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 26/5 | Erection |  | 2025-08-30 | 2025-11-20 | 83 | Please refer daily progress report.
39 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 26/6 | Erection |  | 2025-08-30 | 2026-01-09 | 133 | Please refer daily progress report. Police support taken on 14.11.25 but the locations remains on under hindrance. After that we again attempted on 03.12 and again ROW encountered on 06.12.25. again attempted today in presence of police administration on dated 17.12.25 and the locations is still unreolved. Cleared on 09.01.2026 with thehelp of police admin.
40 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 26/7 | Erection |  | 2025-08-30 | 2025-12-06 | 99 | Please refer daily progress report.
41 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 27/5 | Erection |  | 2025-08-30 | 2025-11-06 | 69 | Please refer daily progress report.
42 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 27/7 | Erection |  | 2025-08-30 | 2025-12-11 | 104 | Please refer daily progress report.
43 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 27/8 | Erection |  | 2025-08-30 | 2025-11-18 | 81 | Please refer daily progress report.
44 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 27/9 | Erection |  | 2025-08-30 | 2025-12-14 | 107 | Please refer daily progress report.
45 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 27/12 | Erection |  | 2025-08-30 | 2025-11-26 | 89 | Please refer daily progress report.
46 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 28/1 | Erection |  | 2025-08-30 | 2025-11-10 | 73 | Please refer daily progress report. Cleared on 10.11.25.
47 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 28/3 | Erection |  | 2025-08-30 | 2025-12-20 | 113 | Please refer daily progress report.
48 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 28/4 | Erection |  | 2025-08-30 | 2025-12-20 | 113 | Please refer daily progress report. Clearance received via MS teams Call jointly with BCG team.
49 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 28/6 | Erection |  | 2025-08-30 | 2025-12-28 | 121 | Please refer daily progress report. Allocated this location for works on 12.09.2025. while attending location in in ROW.
50 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 28/7 | Erection |  | 2025-08-30 | 2025-12-10 | 103 | Please refer daily progress report.
51 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 28/8 | Erection |  | 2025-08-30 | 2025-12-20 | 113 | Please refer daily progress report.
52 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 29/2 | Erection |  | 2025-08-30 | 2025-11-09 | 72 | Please refer daily progress report. Cleared on 09.11.25 post idling of truck nearby 4 hours.
53 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 29/3 | Erection |  | 2025-08-30 | 2025-09-15 | 17 | Please refer daily progress report.
54 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 29/4 | Erection |  | 2025-08-30 | 2025-10-12 | 44 | Please refer daily progress report.
55 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 30/0 | Erection |  | 2025-08-30 | 2025-11-13 | 76 | Please refer daily progress report.
56 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 30/2 | Erection |  | 2025-08-30 | 2025-09-30 | 32 | Please refer daily progress report.
57 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 30/4 | Erection |  | 2025-08-30 | 2025-12-23 | 116 | Please refer daily progress report.
58 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 31/0 | Erection |  | 2025-08-30 | 2025-12-16 | 109 | Please refer daily progress report.
59 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 32/0 | Erection |  | 2025-08-30 | 2025-11-06 | 69 | Please refer daily progress report.
60 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 32/2 | Erection |  | 2025-08-30 | 2025-11-06 | 69 | Please refer daily progress report.
61 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 32/3 | Erection |  | 2025-08-30 | 2025-10-30 | 62 | Please refer daily progress report.
62 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 32/4 | Erection |  | 2025-08-30 | 2024-11-06 | -296 | Please refer daily progress report.
63 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 33/0 | Erection |  | 2025-08-30 | 2025-10-22 | 54 | Please refer daily progress report.
64 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 9/0 | Erection |  | 2025-08-30 | 2025-12-01 | 94 | Please refer daily progress report.
65 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 10/0 | Erection |  | 2025-08-30 |  | Awaited | Please refer daily progress report.
66 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 20/0 | Erection |  | 2025-08-30 | 2025-09-19 | 21 | Please refer daily progress report.
67 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 20/1 | Erection |  | 2025-09-13 |  | Awaited | Please refer daily progress report.
68 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/2 | Erection |  | 2025-09-13 |  | Awaited | Please refer daily progress report.
69 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/5 | Erection |  | 2025-09-13 | 2025-09-19 | 7 | Please refer daily progress report.
70 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/7 | Erection |  | 2025-09-13 |  | Awaited | Please refer daily progress report.
71 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/9 | Erection |  | 2025-09-13 | 2026-01-28 | 138 | Please refer daily progress report. ROW resolved on 28.01.2025 with police protection. Prior to that there is 2 more incident in which we have shifted the materials at site and due to ROW material return back to store.
72 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/10 | Erection |  | 2025-09-13 |  | Awaited | Please refer daily progress report. Material shifted on 29.09.25 but due to ROW locations falls in ROW. Then the gang moved in PKG G. Police protection availed on 17.12. but not resolved.
73 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/1 | Erection |  | 2025-09-13 |  | Awaited | Please refer daily progress report.
74 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/2 | Erection |  | 2025-09-13 | 2025-12-21 | 100 | Please refer daily progress report.
75 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/3 | Erection |  | 2025-09-13 |  | Awaited | Please refer daily progress report.
76 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/4 | Erection |  | 2025-09-13 |  | Awaited | Please refer daily progress report.
77 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/5 | Erection |  | 2025-09-13 | 2025-12-25 | 104 | Please refer daily progress report.
78 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/6 | Erection |  | 2025-09-13 | 2025-12-21 | 100 | Please refer daily progress report.
79 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/7 | Erection |  | 2025-09-13 | 2025-12-15 | 94 | Please refer daily progress report.
80 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/8 | Erection |  | 2025-09-13 | 2026-02-16 | 157 | Please refer daily progress report.
81 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/9 | Erection |  | 2025-09-13 |  | Awaited | Please refer daily progress report.
82 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 38/3 | Erection | Jwala Singh | 2025-10-13 | 2025-11-06 | 25 | Please refer daily progress report. X-arm WIP. No work due to ROW as per instruction by resonia Ltd. Further the gang shifted at next location 39/0 F.
83 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 19/3 | Erection |  | 2025-12-01 | 2025-12-23 | 23 | Please refer daily progress report.
84 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/6 | Erection |  | 2025-12-01 |  |  | Please refer daily progress report.
85 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/8 | Erection |  | 2025-12-01 |  |  | Please refer daily progress report.
86 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/0 | Erection |  | 2025-12-01 |  |  | Please refer daily progress report.
87 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/10 | Erection |  | 2025-12-01 |  |  | Please refer daily progress report.
Others
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
1 | Delay in finalization of locations for Soil investigation |  | Others |  | 2023-12-06 | 2024-02-24 | 81 | 24 Locations SPT Confirmed on 24th Feb 2024.
2 | Delay in approval of L2 Schedule. |  | Others |  | 2023-12-06 | 2024-01-23 | 49 | Approval reference email dated 23.01.24.
3 | New tower optimization and shifting was proposed by SPTL on dated 18th March 2024. Final confirmation for omit of optimization is received on 15.05.2024. |  | Others |  | 2024-03-18 | 2024-05-15 | 59 | Email dated 15/5/24.
3
Stringing
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
1 | Insulator hoisting not done due to ROW at location no 72/1. | 72/1 | Stringing | JPJ construction | 2025-05-24 | 2025-05-26 | 3
2 | This Months Idling- JPJ Construction was idled 43 manpower with T&P's from 27.05.2025 to 31.05.2025 due to 33 KV shut down not availed on time in AP73-74 (3.788 Kms). | AP72-73 | Stringing | JPJ construction | 2025-05-27 | 2025-06-17 | 22 | Infomed to resonia via daily progress report.
3 | Delay occurred due to the removal of the insulator from the previously completed hoisting, and the subsequent re-hoisting of the platina roller. As a result, a total of 6 days were lost. This was done based on clear instruction of resonia. | AP71-AP72 | Stringing | MC Construction | 2025-10-25 | 2025-10-31 | 7 | Infomed to resonia via email dated 01.11.2025 having subject Plan for the month of Nov-2025 [PKG F]
4 | ROW at location no 71/0. due to this drum was unloded at alternate places. | AP70-71 | Stringing | MC Construction | 2025-11-12 | 2025-11-13 | 2 | informed via daily progress report. Cleared on dated 13.11.2025.
5 | Progress hampered due to ROW in 1st half in AP70-71. | AP70-71 | Stringing | MC Construction | 2025-12-03 | 2025-12-09 | 7 | informed via daily progress report. Cleared on dated 13.11.2025. Email dated 08.12.2025
6 | Shutdown not received for Final Sag in AP2-3 | AP2-3 | Stringing | Devi Power | 2025-11-18 | 2026-01-12 | 56 | Informed via daily progress report. and email Dated 23.12.25, 24.12.25 & 27.12.25 further email having subject ROW & Order Issues Impacting Progress – Immediate Intervention Required [PKG G & F]
7 | Insulator hoisting not done due to ROW at location no 72/1. | 72/1 | Stringing | Deepak | 2025-01-10 | 2025-11-03 | 298 | informed via daily progress report. and email having subject ROW & Order Issues Impacting Progress – Immediate Intervention Required [PKG G & F] dated 10/1/26.
8 | Clipping not done due to ROW. | 70/8 & 70/9 | Stringing | MC Construction | 2026-01-01 |  | Awaited | Informed to you via daily progress report.
9 | Final Sag not done due to ROW in backstay at 10/12 | 10/12-10/20 | Stringing | Deepak | 2026-01-23 | 2026-02-04 | 13 | Informed to you via daily progress report.
10 | Paying out not done due to unavailability of Platina in AP55-56 | 55/0-56/0 | Stringing | MC Construction | 2026-02-01 |  | Awaited | Informed to you via daily progress report. From 19.02.25 based on resonia instructions, No works will be done and gangs shifted in Package G for rectification. No works will be done until readiness of PKG G.
8 | Stringing not started due to ROW. | AP43-44 | Stringing |  | 2026-02-23 |  | Awaited | Informed to you via daily progress report.
9 | Stringing not started due to ROW. | AP44-44/6 | Stringing |  | 2026-02-23 |  | Awaited | Informed to you via daily progress report.
10 | F/Sag not started due to ROW. | AP44/6-44/8 | Stringing | Krishna-1 | 2026-02-23 |  | Awaited | Informed to you via daily progress report.
Formulas:
Period of hindrance = +IF([Date of removal (Last attempt)]="","Awaited",DAYS([Date of removal (Last attempt)],[Date of 1st attempt])+1)

## Page Chart
Progress Summary'!A1 | [11 empty] | Village wise dashboard
Location Wise Status | [7 empty] | Post Stringing work |  |  |  | Foundation | [5 empty] | Erection | [6 empty] | Stringing
Sr. No. | Loc No. | TOT | Village Name | Span | FDN | ERE | Str | Clipp. | Spac. | Jump. | Remarks (if any) | Village wise breakups | Total | Comp. | WIP | Clear | ROW | Total | Comp. | WIP | Clear | ROW | Yet to attempt | Balance | Scope | C | WIP | Clear | ROW | Dep. | Other Fac.
1 | 1/0 | DD60+0 | Mandai | 122 | DRY | E | [5 empty] | Village (49 No's) | 485 | 484 | 0 | 0 | 1 | 485 | 463 | 3 | 0 | 18 | 1 | 22 | 191.3926 | 85.8319 | 0 | 0 | 0 | 8.2619 | 97.2988
2 | 1A/0 | DD60+0 | Mandai | 90 | DRY | E | [5 empty] | Mandai | 16 | 16 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 5.6287 | 5.4167 | 0 | 0 | 0 | 0 | 0.212
3 | 1A/1 | DA+6 | Mandai | 277.7 | DFR | E | C | C | C |  |  | Harwa | 22 | 22 | 0 | 0 | 0 | 22 | 21 | 1 | 0 | 0 | 0 | 1 | 7.9501 | 2.0597 | 0 | 0 | 0 | 0.3932 | 5.4972
4 | 1A/2 | DA+0 | Mandai | 386 | DRY | E | C | C | C |  |  | Chak Goonga | 8 | 8 | 0 | 0 | 0 | 8 | 6 | 1 | 0 | 1 | 0 | 2 | 3.1303 | 0 | 0 | 0 | 0 | 0.6742 | 2.4561
5 | 1A/3 | DA+0 | Mandai | 443.6 | DRY | E | C | C | C |  |  | Goonga | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 2.0524 | 0 | 0 | 0 | 0 | 0 | 2.0524
6 | 1A/4 | DA+3 | Mandai | 333.4 | DFR | E | C | C | C |  |  | Pusar | 14 | 14 | 0 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 5.7155 | 2.8734 | 0 | 0 | 0 | 0 | 2.8421
7 | 1A/5 | DA+0 | Mandai | 431.9 | DRY | E | C | C | C |  |  | Bisoo Khurd | 13 | 13 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 5.1285 | 2.0732 | 0 | 0 | 0 | 0 | 3.0553
8 | 1A/6 | DA+0 | Mandai | 348.7 | Sandy | E | C | C | C |  |  | Bhiyad | 38 | 38 | 0 | 0 | 0 | 38 | 35 | 0 | 0 | 3 | 0 | 3 | 15.0319 | 0 | 0 | 0 | 0 | 1.0173 | 14.0146
9 | 1A/7 | DA+3 | Mandai | 395.7 | Sandy | E | C | C | C |  |  | Kashmir | 29 | 28 | 0 | 0 | 1 | 29 | 16 | 1 | 0 | 11 | 1 | 13 | 11.512 | 0 | 0 | 0 | 0 | 4.9781 | 6.5339
10 | 1A/8 | DA+0 | Mandai | 415 | Sandy | E | C | C | C |  |  | Rateu | 35 | 35 | 0 | 0 | 0 | 35 | 32 | 0 | 0 | 3 | 0 | 3 | 13.7801 | 0 | 0 | 0 | 0 | 1.1991 | 12.581
11 | 2/0 | DC1+0 | Mandai | 394.3 | DRY | E | C |  | C | C |  | Sawau Moolraj | 23 | 23 | 0 | 0 | 0 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 9.072 | 0 | 0 | 0 | 0 | 0 | 9.072
12 | 2/1 | DA+3 | Mandai | 405.3 | Sandy | E | C | C | C |  |  | Neemba Ki Dhani | 23 | 23 | 0 | 0 | 0 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 9.1431 | 0 | 0 | 0 | 0 | 0 | 9.1431
13 | 2/2 | DA+3 | Mandai | 338.5 | Sandy | E | C | C | C |  | 33 KV SHUTDOWN, GANG IDLING SINCE 11.09.2025. | Danpura | 13 | 13 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 5.2985 | 0 | 0 | 0 | 0 | 0 | 5.2985
14 | 2/3 | DA+3 | Mandai | 406 | Sandy | E | C | C | C |  |  | Rampura Kharda | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.4017 | 0 | 0 | 0 | 0 | 0 | 0.4017
15 | 2/4 | DA+3 | Mandai | 429 | Sandy | E | C | C | C |  |  | Manpura Kharda | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.7771 | 0 | 0 | 0 | 0 | 0 | 0.7771
16 | 2/5 | DA+3 | Mandai | 411.6 | Sandy | E | C | C | C |  |  | Kharda Charnan | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.4972 | 0 | 0 | 0 | 0 | 0 | 3.4972
17 | 2/6 | DA+3 | Harwa | 425.7 | Sandy | E | C | C | C |  |  | Beniwalon Ki Dhani | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 2.4504 | 0 | 0 | 0 | 0 | 0 | 2.4504
18 | 2/7 | DA+3 | Harwa | 408.2 | Sandy | E | C | C | C |  |  | Pareu | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 1.5736 | 0 | 0 | 0 | 0 | 0 | 1.5736
19 | 2/8 | DA+0 | Harwa | 354.6 | Sandy | E | C | C | C |  |  | Mahadeo Ka Mandir | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 2.656 | 0 | 0 | 0 | 0 | 0 | 2.656
20 | 2/9 | DA+0 | Harwa | 308.7 | DRY | E | C | C | C |  |  | Chimoniyon Ki Dhani | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 3.1701 | 0.62212 | 0 | 0 | 0 | 0 | 2.548
21 | 3/0 | DD60+6 | Harwa | 336 | DRY | E | C | C | C |  |  | Godaron Ki Dhani | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.4586 | 3.4586 | 0 | 0 | 0 | 0 | 0
22 | 4/0 | DD60+6 | Harwa | 226.5 | DRY | E | C |  | C |  |  | Daukiyon Ki Dhani | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 1.6246 | 1.6246 | 0 | 0 | 0 | 0 | 0
23 | 4/1 | DA+0 | Harwa | 343 | DRY | E | [5 empty] | Nehru Nagar | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 2.4092 | 2.4092 | 0 | 0 | 0 | 0 | 0
24 | 4/2 | DA+0 | Harwa | 358.4 | DRY | E | [5 empty] | Nematpura | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 2.9564 | 2.9564 | 0 | 0 | 0 | 0 | 0
25 | 4/3 | DA+0 | Harwa | 381 | DRY | E | [5 empty] | Gangapura | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 1.6321 | 1.6321 | 0 | 0 | 0 | 0 | 0
26 | 4/4 | DA+0 | Harwa | 367.6 | DRY | E | [5 empty] | Barnama Charnan | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 2.5541 | 2.5541 | 0 | 0 | 0 | 0 | 0
27 | 5/0 | DB1+9 | Harwa | 423.1 | DRY | E | [5 empty] | Khanora | 13 | 13 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 5.3755 | 0 | 0 | 0 | 0 | 0 | 5.3755
28 | 6/0 | DB2+9 | Harwa | 246 | DRY | E |  |  |  |  | attempeted on 10.07.2025 | Sathuni Purohitan | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 1.2327 | 0 | 0 | 0 | 0 | 0 | 1.2327
29 | 6/1 | DA+0 | Harwa | 429.9 | DFR | E | [5 empty] | Sathuni Charnan | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 3.2034 | 0 | 0 | 0 | 0 | 0 | 3.2034
30 | 6/2 | DA+0 | Harwa | 362.4 | DFR | E | [5 empty] | Simarkhiya | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 1.2299 | 0.4049 | 0 | 0 | 0 | 0 | 0.825
31 | 7/0 | DB1+0 | Harwa | 347.9 | DRY | E | [5 empty] | Bagawas | 11 | 11 | 0 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 4.011 | 4.011 | 0 | 0 | 0 | 0 | 0
32 | 8/0 | DB1+0 | Harwa | 210.8 | DRY | E | [5 empty] | Mohanpura | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 2.4074 | 2.4074 | 0 | 0 | 0 | 0 | 0
33 | 8/1 | DA+3 | Harwa | 409.2 | DRY | E | [5 empty] | Meghawas | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 1.9041 | 1.9041 | 0 | 0 | 0 | 0 | 0
34 | 8/2 | DA+3 | Harwa | 413.6 | DRY | E | [5 empty] | Sagaranari | 10 | 10 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 4.1779 | 4.1779 | 0 | 0 | 0 | 0 | 0
35 | 8/3 | DA+0 | Harwa | 393.2 | DRY | E | [5 empty] | Nagana | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 2.5271 | 2.5271 | 0 | 0 | 0 | 0 | 0
36 | 8/4 | DA+3 | Harwa | 416.5 | DRY | E | [5 empty] | Deoriya | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.6251 | 3.6251 | 0 | 0 | 0 | 0 | 0
37 | 8/5 | DA+3 | Harwa | 394.6 | DRY | E | [5 empty] | Bakati | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.7283 | 3.7283 | 0 | 0 | 0 | 0 | 0
38 | 8/6 | DA+3 | Harwa | 393.2 | DRY | WIP | Dep. |  |  |  |  | Gwalnada | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.6749 | 3.6749 | 0 | 0 | 0 | 0 | 0
39 | 8/7 | DB1+0 | Chak Goonga | 441.1 | DRY | WIP | Dep. |  |  |  |  | Godawas Kalan | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.681 | 3.681 | 0 | 0 | 0 | 0 | 0
40 | 8/8 | DA+6 | Chak Goonga | 414.4 | DRY | E | [5 empty] | Doli Kalan | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.3861 | 0.3861 | 0 | 0 | 0 | 0 | 0
41 | 8/9 | DA+3 | Chak Goonga | 395.863 | DFR | E | [5 empty] | Modathali | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 2.0474 | 2.0474 | 0 | 0 | 0 | 0 | 0
42 | 8/10 | DA+3 | Chak Goonga | 413.404 | DFR | E | [5 empty] | Piprali | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 1.2276 | 1.2276 | 0 | 0 | 0 | 0 | 0
43 | 8/11 | DA+0 | Chak Goonga | 402.6 | DRY | E | [5 empty] | Rabariyawas | 11 | 11 | 0 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 4.5078 | 4.5078 | 0 | 0 | 0 | 0 | 0
44 | 8/12 | DA+0 | Chak Goonga | 372.1 | DRY | E | [5 empty] | Loonawas Charna | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 1.5661 | 1.5661 | 0 | 0 | 0 | 0 | 0
45 | 9/0 | DD60+18 | Chak Goonga | 457.7 | DRY | E | [5 empty] | Loonawas Khurd | 12 | 12 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 4.2541 | 4.2541 | 0 | 0 | 0 | 0 | 0
46 | 10/0 | DD60+25 | Chak Goonga | 233.1 | DFR | ROW | Dep. |  |  |  |  | Borapadakhamar | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.769 | 0.769 | 0 | 0 | 0 | 0 | 0
47 | 10/1 | DA+0 | Goonga | 443.7 | DRY | E | [5 empty] | Katarda | 12 | 12 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 4.9329 | 4.9329 | 0 | 0 | 0 | 0 | 0
48 | 10/2 | DA+0 | Goonga | 383.2 | DFR | E | [5 empty] | Karni Nagar | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.8202 | 0.8202 | 0 | 0 | 0 | 0 | 0
49 | 10/3 | DA+0 | Goonga | 398.6 | DFR | E | [5 empty] | Basni Jhoonthan | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.7108 | 3.7108 | 0 | 0 | 0 | 0 | 0
50 | 10/4 | DA+3 | Goonga | 410.7 | DFR | E | [5 empty] | Sardargarh | 10 | 10 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 3.7882 | 3.7882 | 0 | 0 | 0 | 0 | 0
51 | 10/5 | DA+3 | Goonga | 416.2 | DRY | E
52 | 10/6 | DA+0 | Pusar | 403.4 | DFR | E
53 | 10/7 | DA+3 | Pusar | 373.845 | DRY | E
54 | 10/8 | DA+3 | Pusar | 411.823 | DFR | E
55 | 10/9 | DA+0 | Pusar | 414.2 | DRY | E
56 | 10/10 | DA+3 | Pusar | 402.3 | Sandy | E
57 | 10/11 | DA+3 | Pusar | 430.3 | DRY | E
58 | 10/12 | DB1+0 | Pusar | 406.2 | DRY | E
59 | 10/13 | DA+3 | Pusar | 405.3 | DRY | E | C | C | C
60 | 10/14 | DA+3 | Pusar | 427.1 | DRY | E | C | C | C
61 | 10/15 | DA+3 | Pusar | 400 | DRY | E | C | C | C
62 | 10/16 | DA+3 | Pusar | 412.8 | DRY | E | C | C | C
63 | 10/17 | DA+3 | Pusar | 387.8 | DFR | E | C | C | C
64 | 10/18 | DA+3 | Pusar | 436.7 | DFR | E | C | C | C
65 | 10/19 | DA+0 | Pusar | 403.7 | DRY | E | C | C | C
66 | 10/20 | DA+3 | Bisoo Khurd | 409.5 | DFR | E | C | C | C
67 | 10/21 | DA+3 | Bisoo Khurd | 418.6 | DFR | E | C | C | C
68 | 10/22 | DA+0 | Bisoo Khurd | 410.3 | Sandy | E | C | C | C
69 | 10/23 | DA+0 | Bisoo Khurd | 384 | Sandy | E | C | C | C
70 | 11/0 | DB1+0 | Bisoo Khurd | 450.8 | Sandy | E | C | C | C
71 | 11/1 | DA+0 | Bisoo Khurd | 384.2 | Sandy | E
72 | 11/2 | DA+0 | Bisoo Khurd | 338.6 | Sandy | E
73 | 11/3 | DA+0 | Bisoo Khurd | 370.7 | Sandy | E
74 | 11/4 | DA+0 | Bisoo Khurd | 434.1 | Sandy | E
75 | 11/5 | DA+0 | Bisoo Khurd | 368.1 | DFR | E
76 | 11A/0 | DB1+0 | Bisoo Khurd | 342.3 | DRY | E
77 | 11A/1 | DA+3 | Bisoo Khurd | 405.1 | DRY | E
78 | 11A/2 | DA+0 | Bisoo Khurd | 412.2 | DRY | E
79 | 11A/3 | DA+3 | Bhiyad | 412.2 | DRY | E
80 | 11A/4 | DA+3 | Bhiyad | 422.1 | DRY | ROW | Dep.
81 | 11A/5 | DA+3 | Bhiyad | 418.3 | DRY | E
82 | 11A/6 | DA+6 | Bhiyad | 384.3 | DRY | E
83 | 11A/7 | DA+9 | Bhiyad | 434.2 | Sandy | E
84 | 11A/8 | DA+6 | Bhiyad | 390.1 | Sandy | E
85 | 11A/9 | DA+3 | Bhiyad | 426.3 | DRY | E
86 | 12/0 | DD60+0 | Bhiyad | 405.9 | DRY | E
87 | 13/0 | DD60+3 | Bhiyad | 211.9 | DRY | ROW | Dep.
88 | 13/1 | DA+9 | Bhiyad | 464.3 | DRY | E
89 | 13/2 | DA+3 | Bhiyad | 373.7 | DRY | E
90 | 13/3 | DA+3 | Bhiyad | 419.7 | Sandy | E
91 | 13/4 | DA+3 | Bhiyad | 420.3 | DRY | E
92 | 14/0 | DC2+0 | Bhiyad | 400 | Sandy | E
93 | 14A/0 | DC1+0 | Bhiyad | 381.4 | DRY | E
94 | 14A/1 | DA+3 | Bhiyad | 412.765 | DRY | E
95 | 14A/2 | DA+0 | Bhiyad | 396.029 | DRY | E
96 | 15/0 | DC1+0 | Bhiyad | 383.3 | DRY | ROW | Dep.
97 | 15/1 | DA+3 | Bhiyad | 404.6 | DRY | E
98 | 16/0 | DC1+0 | Bhiyad | 413.3 | DRY | E
99 | 16/1 | DA+0 | Bhiyad | 354.283 | DRY | E
100 | 16/2 | DA+0 | Bhiyad | 424.28 | DRY | E
101 | 16/3 | DA+3 | Bhiyad | 340.3 | DRY | E
102 | 16/4 | DA+0 | Bhiyad | 394.7 | DRY | E
103 | 16/5 | DA+3 | Bhiyad | 435.863 | DRY | E
104 | 17/0 | DB2+3 | Bhiyad | 386.8 | DRY | E
105 | 17/1 | DA+3 | Bhiyad | 393.7 | DRY | E
106 | 17/2 | DA+6 | Bhiyad | 415.9 | DRY | E
107 | 17/3 | DA+0 | Bhiyad | 422.8 | DRY | E
108 | 17/4 | DA+3 | Bhiyad | 409.9 | DRY | E
109 | 17/5 | DA+3 | Bhiyad | 425.3 | DRY | E
110 | 18/0 | DC2+0 | Bhiyad | 383.4 | DRY | E
111 | 18/1 | DA+0 | Bhiyad | 372.8 | DRY | E
112 | 18/2 | DA+0 | Bhiyad | 379.8 | DRY | E
113 | 18/3 | DA+0 | Bhiyad | 371 | DRY | E
114 | 18/4 | DA+0 | Bhiyad | 398.7 | DRY | E
115 | 19/0 | DC2+0 | Bhiyad | 380.8 | DRY | E
116 | 19/1 | DA+0 | Bhiyad | 366.9 | DRY | E
117 | 19/2 | DA+0 | Kashmir | 372.5 | DRY | E
118 | 19/3 | DA+0 | Kashmir | 376.5 | DRY | E
119 | 19/4 | DA+0 | Kashmir | 384.3 | DRY | E
120 | 19/5 | DA+0 | Kashmir | 375.4 | DRY | E
121 | 20/0 | DB2+0 | Kashmir | 381.2 | Sandy | E
122 | 20/1 | DA+0 | Kashmir | 386.8 | Sandy | ROW | Dep.
123 | 20/2 | DA+0 | Kashmir | 387 | DRY | E
124 | 20/3 | DA+0 | Kashmir | 348.5 | DRY | E
125 | 21/0 | DB2+0 | Kashmir | 355 | DRY | E
126 | 21/1 | DA+6 | Kashmir | 414.9 | ROW |  | Dep.
127 | 21/2 | DA+0 | Kashmir | 407.2 | Sandy | ROW | Dep.
128 | 21/3 | DA+6 | Kashmir | 432.2 | Sandy | E
129 | 21/4 | DA+3 | Kashmir | 401.9 | Sandy | E
130 | 21/5 | DA+6 | Kashmir | 434.2 | DFR | E
131 | 21/6 | DA+3 | Kashmir | 405.5 | DRY | ROW | Dep.
132 | 21/7 | DA+3 | Kashmir | 426 | DFR | ROW | Dep.
133 | 21/8 | DA+6 | Kashmir | 406.9 | DRY | ROW | Dep.
134 | 21/9 | DA+3 | Kashmir | 433.3 | DFR | ROW | Dep.
135 | 21/10 | DA+6 | Kashmir | 372.9 | DRY | ROW | Dep.
136 | 22/0 | DB2+3 | Kashmir | 443.5 | DRY | ROW | Dep.
137 | 22/1 | DA+9 | Kashmir | 456.3 | Sandy | ROW | Dep.
138 | 22/2 | DA+6 | Kashmir | 379.2 | Sandy | E
139 | 22/3 | DA+9 | Kashmir | 382.6 | Sandy | E
140 | 22/4 | DA+9 | Kashmir | 435.6 | Sandy | ROW | Dep.
141 | 22/5 | DA+9 | Kashmir | 402.1 | DRY | E
142 | 22/6 | DA+0 | Kashmir | 417.3 | Sandy | E
143 | 22/7 | DA+0 | Kashmir | 347.7 | Sandy | E
144 | 22/8 | DB1+0 | Kashmir | 356.3 | Sandy | WIP
145 | 22/9 | DA+6 | Kashmir | 389.2 | Sandy | ROW | Dep.
146 | 22/10 | DA+6 | Rateu | 343.8 | Sandy | ROW | Dep.
147 | 22/11 | DA+6 | Rateu | 395.5 | Sandy | E
148 | 22/12 | DA+3 | Rateu | 408 | Sandy | ROW | Dep.
149 | 22/13 | DA+6 | Rateu | 318 | Sandy | E
150 | 23/0 | DD45+3 | Rateu | 447.3 | DRY | ROW | Dep.
151 | 24/0 | DD45+3 | Rateu | 222.2 | DRY | E
152 | 25/0 | DC1+6 | Rateu | 433.9 | DRY | E |  |  |  |  | 11 KV LINE SHIFTING
153 | 25/1 | DA+3 | Rateu | 422.3 | DRY | E
154 | 25/2 | DA+0 | Rateu | 370.7 | DRY | E
155 | 25/3 | DA+0 | Rateu | 345.7 | Sandy | E
156 | 25/4 | DA+0 | Rateu | 391.1 | Sandy | E
157 | 26/0 | DB1+0 | Rateu | 440.4 | DFR | E
158 | 26/1 | DA+0 | Rateu | 391.4 | DRY | E
159 | 26/2 | DA+3 | Rateu | 406.5 | DFR | E
160 | 26/3 | DA+0 | Rateu | 418 | DRY | E
161 | 26/4 | DA+6 | Rateu | 422.6 | Sandy | E |  |  |  |  | 11 KV LINE SHIFTING
162 | 26/5 | DA+6 | Rateu | 410 | Sandy | E
163 | 26/6 | DA+6 | Rateu | 363.4 | Sandy | E
164 | 26/7 | DA+0 | Rateu | 421.9 | DFR | E
165 | 26/8 | DA+6 | Rateu | 416.7 | DFR | E
166 | 27/0 | DC1+0 | Rateu | 413.8 | DFR | E
167 | 27/1 | DA+3 | Rateu | 399.8 | DFR | E
168 | 27/2 | DA+3 | Rateu | 425.2 | DFR | E
169 | 27/3 | DA+3 | Rateu | 398.6 | DFR | E
170 | 27/4 | DA+3 | Rateu | 430.7 | DFR | E
171 | 27/5 | DA+0 | Rateu | 410 | DRY | E
172 | 27/6 | DA+0 | Rateu | 402.6 | Sandy | E
173 | 27/7 | DB1+0 | Rateu | 343.5 | DFR | E |  |  |  |  | 11 KV LINE+LT LINE SHIFTING
174 | 27/8 | DA+0 | Rateu | 392 | DFR | E
175 | 27/9 | DA+0 | Rateu | 381.1 | DFR | E
176 | 27/10 | DA+3 | Rateu | 366.3 | DFR | E
177 | 27/11 | DA+3 | Rateu | 420.1 | DRY | E
178 | 27/12 | DA+3 | Rateu | 420.8 | Sandy | E
179 | 28/0 | DB2+0 | Rateu | 406.6 | DFR | E
180 | 28/1 | DA+0 | Rateu | 379.6 | DRY | E
181 | 28/2 | DA+0 | Sawau Moolraj | 385 | DFR | E
182 | 28/3 | DA+0 | Sawau Moolraj | 369 | DFR | E
183 | 28/4 | DA+0 | Sawau Moolraj | 409 | Sandy | E |  |  |  |  | 28/4 F, Truck reached by yesterday evening but can't be unload due to ROW, same issues earlier encoutered in 27/2 in which we have materials returned to store post reached at site.
184 | 28/5 | DA+9 | Sawau Moolraj | 422 | Sandy | E
185 | 28/6 | DA+6 | Sawau Moolraj | 370 | Sandy | E
186 | 28/7 | DA+3 | Sawau Moolraj | 464 | Sandy | E
187 | 28/8 | DA+3 | Sawau Moolraj | 375 | Sandy | E
188 | 29/0 | DB1+0 | Sawau Moolraj | 465.5 | DRY | E
189 | 29/1 | DA+3 | Sawau Moolraj | 365.6 | DRY | E
190 | 29/2 | DA+3 | Sawau Moolraj | 424 | DRY | E
191 | 29/3 | DA+0 | Sawau Moolraj | 399 | Sandy | E
192 | 29/4 | DA+6 | Sawau Moolraj | 440 | DRY | E
193 | 30/0 | DC1+0 | Sawau Moolraj | 382.1 | DRY | E
194 | 30/1 | DA+0 | Sawau Moolraj | 388.9 | Sandy | E
195 | 30/2 | DA+0 | Sawau Moolraj | 445 | Sandy | E
196 | 30/3 | DA+3 | Sawau Moolraj | 395 | Sandy | E
197 | 30/4 | DA+3 | Sawau Moolraj | 387 | DRY | E
198 | 30/5 | DA+3 | Sawau Moolraj | 442 | DRY | E
199 | 30/6 | DA+0 | Sawau Moolraj | 314 | DRY | E
200 | 31/0 | DB2+0 | Sawau Moolraj | 347.4 | Sandy | E
201 | 31/1 | DA+0 | Sawau Moolraj | 383.6 | DRY | E
202 | 31/2 | DA+0 | Sawau Moolraj | 366 | DRY | E
203 | 32/0 | DC1+0 | Sawau Moolraj | 332.9 | DRY | E
204 | 32/1 | DA+3 | Neemba Ki Dhani | 402.7 | Sandy | E
205 | 32/2 | DA+3 | Neemba Ki Dhani | 428.8 | DRY | E
206 | 32/3 | DA+0 | Neemba Ki Dhani | 410.9 | Sandy | E
207 | 32/4 | DA+0 | Neemba Ki Dhani | 381.1 | Sandy | E
208 | 33/0 | DC1+0 | Neemba Ki Dhani | 451.5 | DRY | E
209 | 33/1 | DA+0 | Neemba Ki Dhani | 379.6 | DRY | E
210 | 34/0 | DB2+0 | Neemba Ki Dhani | 292.5 | DRY | E
211 | 34/1 | DA+9 | Neemba Ki Dhani | 432.6 | Sandy | E
212 | 34/2 | DA+6 | Neemba Ki Dhani | 407.5 | Sandy | E
213 | 34/3 | DA+0 | Neemba Ki Dhani | 377 | Sandy | E
214 | 34/4 | DA+0 | Neemba Ki Dhani | 451.6 | Sandy | E
215 | 35/0 | DB2+6 | Neemba Ki Dhani | 379.3 | Sandy | E
216 | 35/1 | DA+9 | Neemba Ki Dhani | 265.6 | Sandy | E
217 | 35/2 | DB1+0 | Neemba Ki Dhani | 492.4 | Sandy | E
218 | 35/3 | DB1+6 | Neemba Ki Dhani | 522.2 | Sandy | E
219 | 35/4 | DA+0 | Neemba Ki Dhani | 418.9 | DRY | E
220 | 35/5 | DA+0 | Neemba Ki Dhani | 421.7 | Sandy | E
221 | 36/0 | DB2+0 | Neemba Ki Dhani | 342.7 | Sandy | E
222 | 36/1 | DA+3 | Neemba Ki Dhani | 386.4 | Sandy | E
223 | 36/2 | DA+0 | Neemba Ki Dhani | 309.4 | Sandy | E
224 | 36/3 | DA+0 | Neemba Ki Dhani | 357.8 | Sandy | E
225 | 36/4 | DA+6 | Neemba Ki Dhani | 480.4 | Sandy | E
226 | 37/0 | DB2+0 | Neemba Ki Dhani | 350.5 | Sandy | E
227 | 37/1 | DA+9 | Danpura | 443.3 | Sandy | E
228 | 37/2 | DA+3 | Danpura | 356.7 | Sandy | E
229 | 37/3 | DA+0 | Danpura | 339.9 | Sandy | E
230 | 38/0 | DB2+6 | Danpura | 500.3 | Sandy | E
231 | 38/1 | DA+0 | Danpura | 421.4 | Sandy | E
232 | 38/2 | DA+6 | Danpura | 419 | Sandy | E
233 | 38/3 | DA+9 | Danpura | 420.3 | Sandy | E |  |  |  |  | ROW, 4 -X arm balance, Left the location based on instruction by resonia Ltd.
234 | 38/4 | DA+9 | Danpura | 414.9 | Sandy | E
235 | 39/0 | DB2+6 | Danpura | 425.5 | Sandy | E
236 | 39/1 | DA+0 | Danpura | 412.638 | Sandy | E
237 | 40/0 | DC2+0 | Danpura | 322.61 | Sandy | E
238 | 40/1 | DA+6 | Danpura | 396.2 | Sandy | E
239 | 40/2 | DA+3 | Danpura | 425.8 | Sandy | E
240 | 40/3 | DA+3 | Rampura Kharda | 401.7 | Sandy | E
241 | 41/0 | DC1+6 | Manpura Kharda | 436.3 | Sandy | E
242 | 41/1 | DB1+9 | Manpura Kharda | 340.8 | Sandy | E
243 | 41/2 | DA+0 | Kharda Charnan | 447.8 | Sandy | E
244 | 42/0 | DC1+0 | Kharda Charnan | 382.3 | Sandy | E
245 | 42/1 | DA+6 | Kharda Charnan | 384.7 | Sandy | E
246 | 42/2 | DA+6 | Kharda Charnan | 407.4 | Sandy | E
247 | 42/3 | DA+0 | Kharda Charnan | 414.2 | Sandy | E
248 | 42/4 | DA+0 | Kharda Charnan | 256.4 | Sandy | E
249 | 42/5 | DA+9 | Kharda Charnan | 403.8 | Sandy | E
250 | 42/6 | DA+0 | Kharda Charnan | 396.7 | Sandy | E
251 | 43/0 | DB1+0 | Kharda Charnan | 403.9 | Sandy | E
252 | 43/1 | DA+3 | Beniwalon Ki Dhani | 346 | Sandy | E
253 | 43/2 | DA+0 | Beniwalon Ki Dhani | 475.8 | Sandy | E
254 | 43/3 | DA+0 | Beniwalon Ki Dhani | 363.7 | DRY | E
255 | 43/4 | DA+3 | Beniwalon Ki Dhani | 431.8 | Sandy | E
256 | 43/5 | DA+3 | Beniwalon Ki Dhani | 405.3 | DRY | E
257 | 43/6 | DA+3 | Beniwalon Ki Dhani | 427.8 | Sandy | E
258 | 43/7 | DA+3 | Pareu | 389.8 | Sandy | E
259 | 43/8 | DA+9 | Pareu | 449.5 | Sandy | E
260 | 43/9 | DA+9 | Pareu | 388 | Sandy | E
261 | 43/10 | DA+3 | Pareu | 346.3 | Sandy | E
262 | 43/11 | DA+3 | Mahadeo Ka Mandir | 444.8 | Sandy | E
263 | 44/0 | DB1+3 | Mahadeo Ka Mandir | 383.9 | Sandy | E
264 | 44/1 | DA+0 | Mahadeo Ka Mandir | 384.3 | Sandy | E
265 | 44/2 | DA+0 | Mahadeo Ka Mandir | 359 | Sandy | E
266 | 44/3 | DA+0 | Mahadeo Ka Mandir | 334 | Sandy | E
267 | 44/4 | DA+9 | Mahadeo Ka Mandir | 395 | Sandy | E
268 | 44/5 | DA+9 | Mahadeo Ka Mandir | 355 | Sandy | E
269 | 44/6 | DB1+3 | Chimoniyon Ki Dhani | 485 | Sandy | E
270 | 44/7 | DA+9 | Chimoniyon Ki Dhani | 473 | Sandy | E
271 | 44/8 | DCT+0 | Chimoniyon Ki Dhani | 367 | Sandy | E
272 | 44/9 | DA+9 | Chimoniyon Ki Dhani | 430 | Sandy | E
273 | 44/10 | DB1+9 | Chimoniyon Ki Dhani | 365 | Sandy | E
274 | 44/11 | DA+0 | Chimoniyon Ki Dhani | 428 | Sandy | E
275 | 45/0 | DC2+0 | Chimoniyon Ki Dhani | 327.2 | Sandy | E | C |  | C | C
276 | 45/1 | DA+9 | Chimoniyon Ki Dhani | 294.92 | Sandy | E | C | C | C
277 | 46/0 | DD60+25 | Godaron Ki Dhani | 406.54 | Sandy | E | C |  | C
278 | 47/0 | DD60+25 | Godaron Ki Dhani | 199.08 | Sandy | E | C
279 | 47/1 | DA+3 | Godaron Ki Dhani | 441.2 | Sandy | E | C
280 | 47/2 | DA+9 | Godaron Ki Dhani | 365.93 | Sandy | E | C
281 | 47/3 | DA+9 | Godaron Ki Dhani | 417.4 | Sandy | E | C
282 | 47/4 | DA+3 | Godaron Ki Dhani | 358.4 | Sandy | E | C
283 | 47/5 | DA+0 | Godaron Ki Dhani | 461.2 | Sandy | E | C
284 | 47/6 | DA+3 | Godaron Ki Dhani | 377.3 | Sandy | E | C
285 | 47/7 | DA+3 | Godaron Ki Dhani | 431.5 | Sandy | E | C
286 | 47/8 | DA+0 | Daukiyon Ki Dhani | 398.8 | Sandy | E | C
287 | 47/9 | DA+3 | Daukiyon Ki Dhani | 405.9 | Sandy | E | C
288 | 47/10 | DA+6 | Daukiyon Ki Dhani | 433.7 | Sandy | E | C
289 | 48/0 | DC2+0 | Daukiyon Ki Dhani | 386.2 | Sandy | E | C
290 | 48/1 | DA+9 | Nehru Nagar | 428.9 | Sandy | E | C
291 | 49/0 | DD45+0 | Nehru Nagar | 402.9 | Sandy | E | C
292 | 49/1 | DA+0 | Nehru Nagar | 379.1 | Sandy | E | C |  | C
293 | 49/2 | DA+3 | Nehru Nagar | 386.6 | Sandy | E | C | C | C
294 | 49/3 | DA+3 | Nehru Nagar | 390 | Sandy | E | C | C | C
295 | 49/4 | DA+3 | Nehru Nagar | 421.7 | Sandy | E | C | C | C
296 | 49/5 | DA+3 | Nematpura | 396.6 | Sandy | E | C | C | C
297 | 49/6 | DA+0 | Nematpura | 412.8 | Sandy | E | C | C | C
298 | 49/7 | DA+0 | Nematpura | 340.2 | Sandy | E | C | C | C
299 | 50/0 | DB2+0 | Nematpura | 500.2 | Sandy | E | C |  | C | C
300 | 50/1 | DA+6 | Nematpura | 469.1 | Sandy | E | C | C | C
301 | 50/2 | DA+9 | Nematpura | 367.1 | Sandy | E | C | C | C
302 | 50/3 | DA+6 | Nematpura | 470.4 | Sandy | E | C | C | C
303 | 50/4 | DA+9 | Gangapura | 354.8 | Sandy | E | C | C | C
304 | 50/5 | DA+9 | Gangapura | 442.1 | Sandy | E | C | C | C
305 | 50/6 | DA+9 | Gangapura | 364.4 | Sandy | E | C | C | C
306 | 50/7 | DA+0 | Gangapura | 470.8 | Sandy | E | C | C | C
307 | 50/8 | DA+9 | Barnama Charnan | 345 | Sandy | E | C | C | C
308 | 50/9 | DA+0 | Barnama Charnan | 364.4 | Sandy | E | C | C | C
309 | 50/10 | DA+0 | Barnama Charnan | 394.6 | Sandy | E | C | C | C
310 | 51/0 | DC2+0 | Barnama Charnan | 401.4 | Sandy | E | C |  | C | C
311 | 51/1 | DA+0 | Barnama Charnan | 356.6 | Sandy | E | C | C | C
312 | 51/2 | DA+0 | Barnama Charnan | 307.1 | Sandy | E | C | C | C
313 | 52/0 | DC2+0 | Barnama Charnan | 385 | Sandy | E | C |  | C
314 | 52/1 | DA+6 | Khanora | 402 | Sandy | E
315 | 52/2 | DA+6 | Khanora | 402.6 | Sandy | E
316 | 52/3 | DA+9 | Khanora | 437 | Sandy | E
317 | 52/4 | DA+9 | Khanora | 393.8 | Sandy | E
318 | 52/5 | DA+9 | Khanora | 447 | Sandy | E
319 | 52/6 | DA+6 | Khanora | 373 | Sandy | E
320 | 52/7 | DA+3 | Khanora | 406.8 | Sandy | E
321 | 52/8 | DA+6 | Khanora | 433 | Sandy | E
322 | 52/9 | DA+3 | Khanora | 399.7 | Sandy | E
323 | 52/10 | DA+9 | Khanora | 384.1 | Sandy | E
324 | 53/0 | DB2+9 | Khanora | 455.9 | Sandy | E
325 | 53/1 | DA+9 | Khanora | 433.2 | Sandy | E
326 | 53/2 | DA+0 | Khanora | 407.4 | Sandy | E
327 | 53/3 | DA+6 | Sathuni Purohitan | 394.5 | Sandy | E
328 | 53/4 | DA+0 | Sathuni Purohitan | 410.1 | Sandy | E
329 | 53/5 | DA+3 | Sathuni Purohitan | 428.1 | Sandy | E
330 | 53/6 | DA+6 | Sathuni Charnan | 406.6 | Sandy | E
331 | 53/7 | DA+3 | Sathuni Charnan | 411.3 | Sandy | E
332 | 53/8 | DA+3 | Sathuni Charnan | 427.8 | Sandy | E
333 | 54/0 | DB1+6 | Sathuni Charnan | 371.3 | Sandy | E
334 | 54/1 | DA+3 | Sathuni Charnan | 365.1 | Sandy | E
335 | 54/2 | DA+3 | Sathuni Charnan | 381 | Sandy | E
336 | 54/3 | DA+6 | Sathuni Charnan | 417 | Sandy | E
337 | 54/4 | DA+9 | Sathuni Charnan | 423.3 | Sandy | E
338 | 54/5 | DA+9 | Simarkhiya | 401 | Sandy | E
339 | 55/0 | DB1+6 | Simarkhiya | 424 | Sandy | E
340 | 55/1 | DA+0 | Simarkhiya | 404.9 | WFR | E | C
341 | 55/2 | DA+0 | Bagawas | 343.1 | WFR | E | C
342 | 55/3 | DA+0 | Bagawas | 357.7 | Sandy | E | C
343 | 55/4 | DA+0 | Bagawas | 365.2 | Sandy | E | C
344 | 55/5 | DA+0 | Bagawas | 350.1 | Sandy | E | C
345 | 55/6 | DA+0 | Bagawas | 357.7 | Sandy | E | C
346 | 55/7 | DA+0 | Bagawas | 337.8 | Sandy | E | C
347 | 55/8 | DA+6 | Bagawas | 341.22 | Sandy | E | C
348 | 56/0 | DD60+25 | Bagawas | 460.49 | Sandy | E | C
349 | 57/0 | DD60+25 | Bagawas | 219.76 | Sandy | E | C
350 | 57/1 | DA+0 | Bagawas | 461.1 | Sandy | E | C
351 | 57/2 | DA+3 | Mohanpura | 355.5 | DRY | E | C | C | C
352 | 57/3 | DA+0 | Mohanpura | 405.4 | DRY | E | C | C | C
353 | 57/4 | DA+0 | Mohanpura | 418.2 | Sandy | E | C | C | C
354 | 57/5 | DA+3 | Bagawas | 416.8 | Sandy | E | C | C | C
355 | 57/6 | DA+3 | Mohanpura | 395 | Sandy | E | C | C | C
356 | 57/7 | DA+3 | Meghawas | 401.8 | DFR | E | C | C | C
357 | 58/0 | DC1+3 | Meghawas | 433.9 | DFR | E | C |  | C | C
358 | 59/0 | DC2+0 | Meghawas | 238.9 | DRY | E | C |  | C | c
359 | 59/1 | DA+3 | Meghawas | 411.3 | DRY | E | C | C | C
360 | 59/2 | DA+3 | Meghawas | 418.2 | DFR | E | C | C | C
361 | 59/3 | DA+3 | Mohanpura | 412.3 | DFR | E | C | C | C
362 | 59/4 | DA+3 | Mohanpura | 421 | DFR | E | C | C | C
363 | 59/5 | DA+3 | Sagaranari | 419.7 | DFR | E | C | C | C
364 | 59/6 | DA+3 | Sagaranari | 419.1 | DFR | E | C | C | C
365 | 59/7 | DA+3 | Sagaranari | 408.8 | DRY | E | C | C | C
366 | 59/8 | DB1+3 | Sagaranari | 426.9 | DRY | E | C |  | C | C
367 | 59/9 | DA+3 | Sagaranari | 434.7 | DRY | E | C | C | C
368 | 59/10 | DA+0 | Sagaranari | 400.8 | DRY | E | C | C | C
369 | 59/11 | DA+6 | Sagaranari | 436.3 | DFR | E | C | C | C
370 | 59/12 | DA+6 | Sagaranari | 393.1 | DFR | E | C | C | C
371 | 59/13 | DA+3 | Sagaranari | 447.4 | DRY | E | C | C | C
372 | 59/14 | DA+6 | Sagaranari | 391.1 | DRY | E | C | C | C
373 | 59/15 | DA+6 | Nagana | 448.6 | DRY | E | C | C | C
374 | 59/16 | DA+9 | Nagana | 388 | Dry | E | C | C | C
375 | 60/0 | DC1+0 | Nagana | 438 | DRY | E | C |  | C | C
376 | 60/1 | DA+6 | Nagana | 413.8 | DRY | E | C | C | C
377 | 60/2 | DA+3 | Nagana | 424.2 | DFR | E | C | C | C
378 | 60/3 | DA+3 | Nagana | 414.5 | DFR | E | C | C | C
379 | 60/4 | DA+3 | Deoriya | 425.6 | DFR | E | C | C | C
380 | 60/5 | DA+3 | Deoriya | 412.3 | DRY | E | C | C | C
381 | 60/6 | DA+0 | Deoriya | 374.1 | DRY | E | C | C | C
382 | 60/7 | DA+3 | Deoriya | 410.1 | DRY | E | C | C | C
383 | 60/8 | DA+0 | Deoriya | 400.4 | DRY | E | C | C | C
384 | 60/9 | DA+3 | Deoriya | 409.2 | DRY | E | C | C | C
385 | 60/10 | DA+0 | Deoriya | 401 | DFR | E | C | C | C
386 | 60/11 | DA+3 | Deoriya | 394.5 | DRY | E | C | C | C
387 | 61/0 | DB2+0 | Deoriya | 397.9 | DRY | E | C |  | C | C
388 | 61/1 | DA+6 | Bakati | 405.7 | DFR | E | C | C | C
389 | 61/2 | DA+6 | Bakati | 433.2 | DFR | E | C | C | C
390 | 61/3 | DA+6 | Bakati | 400.9 | DRY | E | C | C | C
391 | 61/4 | DA+3 | Bakati | 427 | DRY | E | C | C | C
392 | 61/5 | DA+3 | Bakati | 413.9 | DRY | E | C | C | C
393 | 61/6 | DA+3 | Bakati | 426.4 | DRY | E | C | C | C
394 | 61/7 | DA+9 | Bakati | 411.5 | Dry | E | C | C | C
395 | 61/8 | DA+6 | Bakati | 376.3 | DRY | E | C | C | C
396 | 61/9 | DA+0 | Bakati | 433.4 | Dry | E | C | C | C
397 | 61/10 | DA+9 | Gwalnada | 405.6 | DRY | E | C | C | C
398 | 62/0 | DB2+0 | Gwalnada | 434.3 | DRY | E | C |  | C | C
399 | 62/1 | DA+3 | Gwalnada | 418 | Sandy | E | C | C | C
400 | 62/2 | DA+3 | Gwalnada | 386 | DRY | E | C | C | C
401 | 62/3 | DA+0 | Gwalnada | 400 | DRY | E | C | C | C
402 | 62/4 | DA+3 | Gwalnada | 401 | DRY | E | C | C | C
403 | 62/5 | DA+0 | Gwalnada | 403 | DRY | E | C | C | C
404 | 62/6 | DA+3 | Gwalnada | 404 | DRY | E | C | C | C
405 | 62/7 | DA+3 | Gwalnada | 423 | DRY | E | C | C | C
406 | 62/8 | DA+0 | Godawas Kalan | 409 | DFR | E | C | C | C
407 | 62/9 | DA+3 | Godawas Kalan | 409 | DFR | E | C | C | C
408 | 62/10 | DA+0 | Godawas Kalan | 411 | DFR | E | C | C | C
409 | 62/11 | DA+3 | Godawas Kalan | 413 | DRY | E | C | C | C
410 | 63/0 | DC1+0 | Doli Kalan | 386.1 | DFR | E | C |  | C | C
411 | 63/1 | DA+3 | Godawas Kalan | 400 | DFR | E | C | C | C
412 | 63/2 | DA+0 | Godawas Kalan | 416 | DFR | E | C | C | C
413 | 63/3 | DA+3 | Godawas Kalan | 411 | DFR | E | C | C | C
414 | 63/4 | DA+0 | Godawas Kalan | 399 | DRY | E | C | C | C
415 | 63/5 | DA+3 | Godawas Kalan | 413 | DFR | E | C | C | C
416 | 63/6 | DA+3 | Modathali | 426 | DRY | E | C | C | C
417 | 63/7 | DA+3 | Modathali | 413 | DRY | E | C | C | C
418 | 63/8 | DA+3 | Modathali | 425 | DRY | E | C | C | C
419 | 64/0 | DB2+0 | Modathali | 408.3 | DRY | E | C |  | C | C
420 | 64/1 | DA+0 | Modathali | 375.1 | DRY | E | C | C | C
421 | 64/2 | DA+3 | Piprali | 408.7 | DRY | E | C | C | C
422 | 64/3 | DA+0 | Piprali | 410.7 | DRY | E | C | C | C
423 | 64/4 | DA+3 | Piprali | 408.2 | DRY | E | C | C | C
424 | 64/5 | DA+3 | Rabariyawas | 426.2 | DRY | E | C | C | C
425 | 64/6 | DA+0 | Rabariyawas | 407.7 | DRY | E | C | C | C
426 | 64/7 | DA+3 | Rabariyawas | 401.6 | DRY | E | C | C | C
427 | 64/8 | DA+3 | Rabariyawas | 425.5 | DRY | E | C | C | C
428 | 64/9 | DA+3 | Rabariyawas | 414.4 | DRY | E | C | C | C
429 | 64/10 | DA+3 | Rabariyawas | 410.6 | DRY | E | C | C | C
430 | 64/11 | DA+3 | Rabariyawas | 428.4 | DRY | E | C | C | C
431 | 65/0 | DB1+0 | Rabariyawas | 400.6 | DRY | E | C |  | C | C
432 | 65/1 | DA+0 | Rabariyawas | 395.4 | DRY | E | C | C | C
433 | 65/2 | DA+0 | Rabariyawas | 393.7 | DRY | E | C | C | C
434 | 65/3 | DA+3 | Rabariyawas | 403.7 | DRY | E | C | C | C
435 | 65/4 | DA+0 | Loonawas Charna | 402.9 | DRY | E | C | C | C
436 | 65/5 | DA+0 | Loonawas Charna | 376.4 | DRY | E | C | C | C
437 | 65/6 | DA+0 | Loonawas Charna | 389.2 | DRY | E | C | C | C
438 | 65/7 | DA+0 | Loonawas Charna | 397.6 | DRY | E | C | C | C
439 | 65/8 | DA+0 | Loonawas Khurd | 394.3 | DRY | E | C | C | C
440 | 65/9 | DA+0 | Loonawas Khurd | 389 | DRY | E | C | C | C
441 | 65/10 | DA+0 | Loonawas Khurd | 379.1 | DRY | E | C | C | C
442 | 65/11 | DA+0 | Loonawas Khurd | 387.6 | DRY | E | C | C | C
443 | 66/0 | DC2+6 | Loonawas Khurd | 426.9 | DRY | E | C |  | C | C
444 | 67/0 | DC1+9 | Loonawas Khurd | 207.8 | DRY | E | C |  | C | C
445 | 67/1 | DA+0 | Loonawas Khurd | 347.1 | DRY | E | C | C | C
446 | 67/2 | DA+0 | Loonawas Khurd | 344.9 | DRY | E | C | C | C
447 | 68/0 | DD45+0 | Loonawas Khurd | 369.2 | DRY | E | C |  | C
448 | 69/0 | DB2+0 | Loonawas Khurd | 200.9 | DFR | E | C |  | C | C
449 | 69/1 | DA+3 | Borapadakhamar | 374.1 | DRY | E | C | C | C
450 | 70/0 | DC1+0 | Borapadakhamar | 394.9 | DRY | E | C |  | C | C
451 | 70/1 | DA+3 | Loonawas Khurd | 388.4 | DRY | E | C | C | C
452 | 70/2 | DA+3 | Loonawas Khurd | 418.9 | DRY | E | C | C | C
453 | 70/3 | DA+3 | Katarda | 418.6 | DRY | E | C | C | C
454 | 70/4 | DA+3 | Katarda | 414 | DRY | E | C | C | C
455 | 70/5 | DA+3 | Katarda | 419.6 | DRY | E | C | C | C
456 | 70/6 | DA+3 | Katarda | 420.3 | DRY | E | C | C | C
457 | 70/7 | DA+3 | Katarda | 419.6 | DRY | E | C | C | WIP
458 | 70/8 | DA+3 | Katarda | 418.2 | DRY | E | C |  | WIP
459 | 70/9 | DA+3 | Karni Nagar | 414.1 | DRY | E | C |  | WIP
460 | 70/10 | DA+3 | Karni Nagar | 406.1 | DRY | E | C | C | WIP
461 | 70/11 | DA+3 | Katarda | 408.6 | DRY | E | C | C | C
462 | 71/0 | DB2+3 | Katarda | 420.4 | DRY | E | C |  | C | C
463 | 71/1 | DA+3 | Katarda | 398.6 | DRY | E | C | C | C
464 | 71/2 | DA+3 | Katarda | 414.3 | DRY | E | C | C | C
465 | 71/3 | DA+6 | Katarda | 413 | DRY | E | C | C | C
466 | 71/4 | DA+3 | Katarda | 367.7 | DRY | E | C | C | C
467 | 71/5 | DA+3 | Basni Jhoonthan | 429.4 | DRY | E | C | C | C
468 | 71/6 | DA+0 | Basni Jhoonthan | 408 | DRY | E | C | C | C
469 | 71/7 | DA+3 | Basni Jhoonthan | 404.9 | DRY | E | C | C | C
470 | 71/8 | DA+3 | Basni Jhoonthan | 431.6 | DRY | E | C | C | C
471 | 72/0 | DB2+3 | Basni Jhoonthan | 408.4 | DRY | E | C |  | C | C
472 | 72/1 | DA+3 | Basni Jhoonthan | 435.3 | DRY | E | C | C | C
473 | 72/2 | DA+0 | Basni Jhoonthan | 403.9 | DRY | E | C | C | C
474 | 72/3 | DA+3 | Basni Jhoonthan | 389.2 | DRY | E | C | C | C
475 | 73/0 | DB2+0 | Basni Jhoonthan | 400.1 | DRY | E | C |  | C | C
476 | 73/1 | DA+0 | Sardargarh | 383.3 | DRY | E | C | C | C
477 | 73/2 | DA+0 | Sardargarh | 379 | DRY | E | C | C | C
478 | 73/3 | DA+0 | Sardargarh | 381.2 | DRY | E | C | C | C
479 | 73/4 | DA+0 | Sardargarh | 384.7 | DRY | E | C | C | C
480 | 73/5 | DA+0 | Sardargarh | 368.8 | DRY | E | C | C | C
481 | 73/6 | DA+0 | Sardargarh | 365.5 | DRY | E | C | C | C
482 | 73/7 | DA+0 | Sardargarh | 392.4 | DRY | E | C | C | C
483 | 73/8 | DA+3 | Sardargarh | 374.9 | DRY | E | C | C | C
484 | 73/9 | DA+0 | Sardargarh | 379.5 | DRY | E | C | C | C
485 | 74/0 | DB2+0 | Sardargarh | 378.9 | Sandy | E | C |  | C
|  |  | Total |  |  |  |  | 397 | 485 | 88
|  |  | Completed |  |  |  |  | 164 | 188 | 20
|  |  | Balance |  |  |  |  | 233 | 297 | 68
|  |  | WIP |  |  |  |  | 0 | 4 | 0

## Survey
Progress Summary'!A1 | KEC International Limited
Survey status at TB-408
Section | Sl. No | Section |  | Section Length (in Mtrs) | Detail Survey received Date | Check Survey | [5 empty] | Total | Susp. | Tens.
|  | From | To |  |  | Status | Date of Submission | Further Modification date | Approved Date | Remarks | Remarks
1 | 1 | Gty | 1/0 | 122 | 2023-10-14 | Approved | 2024-09-20 |  | 2024-11-08 | Clearances received on 15.07.2024 |  | 1 | 0 | 1
1 | 2 | 1/0 | 1A/0 | 90 | 2023-10-14 | Approved | 2024-09-20 |  | 2024-11-08 | Clearances received on 15.07.2024 |  | 1 | 0 | 1
1 | 3 | 1/0 | 2/0 | 3438.766 | 2023-10-14 | Approved | 2024-09-20 |  | 2024-11-08 | Clearances received on 15.07.2024 |  | 1 | 0 | 1
1 | 4 | 2/0 | 3/0 | 3823.508 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 10 | 9 | 1
1 | 5 | 3/0 | 4/0 | 226.52 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 6 | 4/0 | 5/0 | 1873.545 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 5 | 4 | 1
1 | 7 | 5/0 | 6/0 | 246.019 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 8 | 6/0 | 7/0 | 1140.147 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 3 | 2 | 1
1 | 9 | 7/0 | 8/0 | 210.755 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 10 | 8/0 | 8/7 | 2861.372 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 7 | 6 | 1
1 | 11 | 8/7 | 9/0 | 2456.044 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 6 | 5 | 1
1 | 12 | 9/0 | 10/0 | 233.076 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 13 | 10/0 | 10/12 | 4894.437 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 12 | 11 | 1
1 | 14 | 10/12 | 11/0 | 4844.45 | 2023-10-14 | Approved | 2024-02-22 |  | 2024-05-20 | ROW Cleared on 16/01/23. approved on 20.05.2024 having subject Optimization from GTY to AP74 (Part- F) |  | 12 | 11 | 1
1 | 15 | 11/0 | 11A/0 | 2339.993 | 2023-10-14 | Approved | 2024-02-22 |  | 2024-05-20 | Location no 11/5, 11A/0 are on Hold due to ROW during check survey, Centre peg not done for verification of benching and others. approved on 20.05.2024 having subject Optimization from GTY to AP74 (Part- F) |  | 6 | 5 | 1
1 | 16 | 11A/0 | 12/0 | 4110.631 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 10 | 9 | 1
1 | 17 | 12/0 | 13/0 | 211.914 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 18 | 13/0 | 14/0 | 2077.901 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 5 | 4 | 1
1 | 19 | 14/0 | 14A/0 | 381.413 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 1 | 0 | 1
1 | 20 | 14A/0 | 15/0 | 1192.131 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 3 | 2 | 1
1 | 21 | 15/0 | 16/0 | 817.914 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 2 | 1 | 1
1 | 22 | 16/0 | 17/0 | 2336.157 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 6 | 5 | 1
1 | 23 | 17/0 | 18/0 | 2451.083 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 6 | 5 | 1
1 | 24 | 18/0 | 19/0 | 1903.166 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 5 | 4 | 1
1 | 25 | 19/0 | 20/0 | 2256.723 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 6 | 5 | 1
1 | 26 | 20/0 | 21/0 | 1477.254 | 2023-10-14 | Approved | 2025-07-03 |  | 2025-07-12 | ROW Cleared on 23/6/2025, Check survey completed on the same day. |  | 4 | 3 | 1
1 | 27 | 21/0 | 22/0 | 4578.525 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 11 | 10 | 1
1 | 28 | 22/0 | 22/8 | 3184.049 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 8 | 7 | 1
1 | 29 | 22/8 | 23/0 | 2294.809 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 6 | 5 | 1
1 | 30 | 23/0 | 24/0 | 222.155 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 1 | 0 | 1
1 | 31 | 24/0 | 25/0 | 433.889 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 1 | 0 | 1
1 | 32 | 25/0 | 26/0 | 1970.278 | 2023-10-14 | Approved | 2023-11-06 |  | 2023-11-22 |  |  | 5 | 4 | 1
1 | 33 | 26/0 | 27/0 | 3664.173 | 2023-10-14 | Approved | 2023-11-06 |  | 2023-11-22 |  |  | 9 | 8 | 1
1 | 34 | 27/0 | 27/7 | 2810.22 | 2023-10-14 | Approved | 2023-11-06 |  | 2023-11-22 |  |  | 7 | 6 | 1
1 | 35 | 27/7 | 28/0 | 2386.877 | 2023-10-14 | Approved | 2023-11-06 |  | 2023-11-22 |  |  | 6 | 5 | 1
1 | 36 | 28/0 | 29/0 | 3639.092 | 2023-10-14 | Approved | 2023-11-10 | 2023-12-07 | 2023-11-22 | Modifications due to shifting. | Benching approval awaited | 9 | 8 | 1
1 | 37 | 29/0 | 30/0 | 2010.644 | 2023-10-14 | Approved | 2023-11-10 | 2023-12-07 | 2023-11-22 | Modifications due to shifting. | Benching approval awaited | 5 | 4 | 1
1 | 38 | 30/0 | 31/0 | 2719.335 | 2023-10-14 | Approved | 2023-11-10 | 2023-12-07 | 2023-11-22 | Modifications due to shifting. | Benching approval awaited | 7 | 6 | 1
1 | 39 | 31/0 | 32/0 | 1082.475 | 2023-10-14 | Approved | 2023-11-10 | 2023-12-07 | 2023-11-22 | ROW from 21.12.2023 to 29.12.2023 | Benching approval awaited | 3 | 2 | 1
1 | 40 | 32/0 | 33/0 | 2074.99 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | ROW from 21.12.2023 to 29.12.2023 |  | 5 | 4 | 1
1 | 41 | 33/0 | 34/0 | 672.091 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | ROW from 21.12.2023 to 29.12.2023 |  | 2 | 1 | 1
1 | 42 | 34/0 | 35/0 | 2048.196 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 5 | 4 | 1
1 | 43 | 35/0 | 35/2 | 775.496 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 2 | 1 | 1
1 | 44 | 35/2 | 35/3 | 504.678 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 1 | 0 | 1
1 | 45 | 35/3 | 36/0 | 1180.197 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 3 | 2 | 1
1 | 46 | 36/0 | 37/0 | 1883.954 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 5 | 4 | 1
1 | 47 | 37/0 | 37/3 | 1138.536 | 2023-10-14 | Approved | 2024-02-25 |  | 2024-12-11 | Resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 3 | 2 | 1
1 | 48 | 37/3 | 38/0 | 594.059 | 2023-10-14 | Approved | 2024-02-25 |  | 2024-12-11 | Resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 1 | 0 | 1
1 | 49 | 38/0 | 39/0 | 2063.067 | 2023-10-14 | Approved | 2024-11-30 |  | 2024-12-11 | ROW from 06.12.2023 to 10.10.2024 |  | 5 | 4 | 1
1 | 50 | 39/0 | 40/0 | 684.371 | 2023-10-14 | Approved | 2024-11-30 |  | 2024-12-11 | ROW from 06.12.2023 to 10.10.2024 |  | 2 | 1 | 1
1 | 51 | 40/0 | 40/3 | 1183.8 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 3 | 2 | 1
1 | 52 | 40/3 | 41/0 | 478.3 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 1 | 0 | 1
1 | 53 | 41/0 | 41/1 | 312.3 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 1 | 0 | 1
1 | 54 | 41/1 | 42/0 | 818.5 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 2 | 1 | 1
1 | 55 | 42/0 | 43/0 | 2607.2 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 7 | 6 | 1
1 | 56 | 43/0 | 44/0 | 4912.9 |  | Approved | 2024-06-23 |  | 2024-07-03 |  |  | 12 | 11 | 1
2 | 57 | 44/0 | 44/3 | 1258.6 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 3 | 2 | 1
2 | 58 | 44/3 | 44/8 | 1995.5 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 5 | 4 | 1
2 | 59 | 44/8 | 45/0 | 1448.6 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 4 | 3 | 1
2 | 60 | 45/0 | 46/0 | 701.4 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 2 | 1 | 1
2 | 61 | 46/0 | 47/0 | 197.7 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 1 | 0 | 1
2 | 62 | 47/0 | 48/0 | 4479.5 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 11 | 10 | 1
2 | 63 | 48/0 | 49/0 | 809.9 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 2 | 1 | 1
2 | 64 | 49/0 | 50/0 | 3248.6 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 8 | 7 | 1
2 | 65 | 50/0 | 51/0 | 4444.1 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 11 | 10 | 1
2 | 66 | 51/0 | 52/0 | 1048.7 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 3 | 2 | 1
2 | 67 | 52/0 | 53/0 | 4534.9 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 11 | 10 | 1
2 | 68 | 53/0 | 54/0 | 3690.3 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 9 | 8 | 1
2 | 69 | 54/0 | 55/0 | 2411.4 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 6 | 5 | 1
2 | 70 | 55/0 | 56/0 | 3338.2 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 9 | 8 | 1
2 | 71 | 56/0 | 57/0 | 179.9 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 1 | 0 | 1
2 | 72 | 57/0 | 58/0 | 3307.7 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 8 | 7 | 1
2 | 73 | 58/0 | 59/0 | 238.9 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 1 | 0 | 1
2 | 74 | 59/0 | 59/8 | 3337.3 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 8 | 7 | 1
2 | 75 | 59/8 | 60/0 | 3778 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 9 | 8 | 1
2 | 76 | 60/0 | 61/0 | 4877.6 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 12 | 11 | 1
2 | 77 | 61/0 | 62/0 | 4568.1 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 11 | 10 | 1
2 | 78 | 62/0 | 63/0 | 4866.9 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 12 | 11 | 1
2 | 79 | 63/0 | 64/0 | 3664 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 9 | 8 | 1
2 | 80 | 64/0 | 65/0 | 4967.6 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 12 | 11 | 1
2 | 81 | 65/0 | 66/0 | 4735.8 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 12 | 11 | 1
2 | 82 | 66/0 | 67/0 | 207.8 |  | Approved | 2024-01-24 |  | 2024-01-31 |  |  | 1 | 0 | 1
2 | 83 | 67/0 | 68/0 | 1061.2 |  | Approved | 2024-01-24 |  | 2024-01-31 |  |  | 3 | 2 | 1
2 | 84 | 68/0 | 69/0 | 200.9 |  | Approved | 2024-01-24 |  | 2024-01-31 |  |  | 1 | 0 | 1
2 | 85 | 69/0 | 70/0 | 769 |  | Approved | 2024-01-24 |  | 2024-01-31 |  |  | 2 | 1 | 1
2 | 86 | 70/0 | 71/0 | 4966.8 |  | Approved | 2024-12-02 |  | 2024-12-10 | ROW Since 20/1/24. |  | 12 | 11 | 1
2 | 87 | 71/0 | 72/0 | 3676 |  | Approved | 2024-02-22 |  | 2024-05-20 |  |  | 9 | 8 | 1
2 | 88 | 72/0 | 73/0 | 1628.5 |  | Approved | 2024-02-22 |  | 2024-05-20 |  |  | 4 | 3 | 1
2 | 89 | 73/0 | 74/0 | 3788.2 |  | Approved | 2024-08-20 |  | 2024-08-27 | Approved. |  | 10 | 9 | 1
| Total (Part-1 & Part-2) |  |  | 191373.675 | [7 empty] | 477 | 388 | 89

## Foundation
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
List of Completed Foundations
Sr. No. | Completion Months | Loc. No. | Tower Type | Soil Classification | Date of Pit marking Till oct-24/ after Oct casting start date | Fdn Comp. Date | Vendor's Name | KEC Section In-Charge
1 | 2023-10-01 | 36/1 | DA+3 | Sandy | 2023-09-28 | 2023-10-04 | Nagana Ray and company | Kuntal Debnath | 6
2 | 2023-12-01 | 61/3 | DA+6 | DRY | 2023-12-13 | 2023-12-14 | Manoj Sharma | R T Singh | 1
3 | 2023-12-01 | 27/12 | DA+3 | Sandy | 2023-12-06 | 2023-12-18 | Nagana Ray And Company | Ajay Yadav | 12
4 | 2023-12-01 | 62/6 | DA+3 | DRY | 2023-12-16 | 2023-12-18 | Shakti Construction | Rakesh Pathak | 2
5 | 2023-12-01 | 59/14 | DA+6 | DRY | 2023-12-17 | 2023-12-18 | Manoj Sharma | R T Singh | 1
6 | 2023-12-01 | 62/7 | DA+3 | DRY | 2023-12-19 | 2023-12-21 | Shakti Construction | Rakesh Pathak | 2
7 | 2023-12-01 | 59/13 | DA+3 | DRY | 2023-12-21 | 2023-12-21 | Manoj Sharma | R T Singh | 0
8 | 2023-12-01 | 27/10 | DA+3 | DFR | 2023-12-19 | 2023-12-24 | Nagana Ray And Company | Jeetu Sachan | 5
9 | 2023-12-01 | 63/8 | DA+3 | DRY | 2023-12-22 | 2023-12-24 | Mahadev Eng | Rakesh Pathak | 2
10 | 2023-12-01 | 59/10 | DA+0 | DRY | 2023-12-23 | 2023-12-24 | Manoj Sharma | R T Singh | 1
11 | 2023-12-01 | 62/5 | DA+0 | DRY | 2023-12-22 | 2023-12-25 | Shakti Construction | Rakesh Pathak | 3
12 | 2023-12-01 | 59/9 | DA+3 | DRY | 2023-12-25 | 2023-12-26 | Manoj Sharma | R T Singh | 1
13 | 2023-12-01 | 60/9 | DA+3 | DRY | 2023-12-26 | 2023-12-27 | Imran | Sumit | 1
14 | 2023-12-01 | 62/4 | DA+3 | DRY | 2023-12-26 | 2023-12-28 | Shakti Construction | Rakesh Pathak | 2
15 | 2023-12-01 | 59/8 | DB1+3 | DRY | 2023-12-27 | 2023-12-28 | Manoj Sharma | Sumit | 1
16 | 2023-12-01 | 26/2 | DA+3 | DFR | 2023-12-22 | 2023-12-29 | A.B. Construction | Jeetu Sachan | 7
17 | 2023-12-01 | 59/6 | DA+3 | DFR | 2023-12-27 | 2023-12-29 | Om Const | Rakesh Pathak | 2
18 | 2023-12-01 | 63/6 | DA+3 | DRY | 2023-12-27 | 2023-12-29 | Mahadev Eng | Rakesh Pathak | 2
19 | 2023-12-01 | 60/8 | DA+0 | DRY | 2023-12-26 | 2023-12-29 | Imran | Sumit | 3
20 | 2023-12-01 | 27/9 | DA+0 | DFR | 2023-12-25 | 2023-12-30 | Nagana Ray And Company | Jeetu Sachan | 5
21 | 2023-12-01 | 59/7 | DA+3 | DRY | 2023-12-29 | 2023-12-30 | Manoj Sharma | R T Singh | 1
22 | 2023-12-01 | 59/5 | DA+3 | DFR | 2023-12-25 | 2023-12-31 | Om Const | R T Singh | 6
23 | 2023-12-01 | 62/3 | DA+0 | DRY | 2023-12-30 | 2023-12-31 | Shakti Construction | Rakesh Pathak | 1
24 | 2024-01-01 | 59/12 | DA+6 | DFR | 2024-01-04 | 2024-01-05 | Manoj Sharma | R T Singh | 1
25 | 2024-01-01 | 60/7 | DA+3 | DRY | 2024-01-01 | 2024-01-05 | Imran | R T Singh | 4
26 | 2024-01-01 | 62/2 | DA+3 | DRY | 2024-01-02 | 2024-01-05 | Shakti Construction | Rakesh Pathak | 3
27 | 2024-01-01 | 59/3 | DA+3 | DFR | 2024-01-03 | 2024-01-05 | Om Const | R T Singh | 2
28 | 2024-01-01 | 64/0 | DB2+0 | DRY | 2024-01-04 | 2024-01-08 | Mahadev Eng | Rakesh Pathak | 4
29 | 2024-01-01 | 57/3 | DA+0 | DRY | 2024-01-06 | 2024-01-08 | Om Const | R T Singh | 2
30 | 2024-01-01 | 60/5 | DA+3 | DRY | 2024-01-08 | 2024-01-09 | Manoj Sharma | R T Singh | 1
31 | 2024-01-01 | 62/11 | DA+3 | DRY | 2024-01-09 | 2024-01-10 | Shakti Construction | Rakesh Pathak | 1
32 | 2024-01-01 | 65/2 | DA+0 | DRY | 2024-01-08 | 2024-01-10 | Veerteja Enterprises | Rakesh Pathak | 2
33 | 2024-01-01 | 65/11 | DA+0 | DRY | 2024-01-09 | 2024-01-10 | Bhati Const. | Rakesh Pathak | 1
34 | 2024-01-01 | 60/6 | DA+0 | DRY | 2024-01-10 | 2024-01-11 | Manoj Sharma | R T Singh | 1
35 | 2024-01-01 | 57/2 | DA+3 | DRY | 2024-01-09 | 2024-01-11 | Om Const | R T Singh | 2
36 | 2024-01-01 | 62/10 | DA+0 | DFR | 2024-01-11 | 2024-01-13 | Shakti Construction | Rakesh Pathak | 2
37 | 2024-01-01 | 65/9 | DA+0 | DRY | 2024-01-11 | 2024-01-13 | Bhati Const. | Rakesh Pathak | 2
38 | 2024-01-01 | 57/4 | DA+0 | Sandy | 2024-01-12 | 2024-01-14 | Om Const | R T Singh | 2
39 | 2024-01-01 | 64/4 | DA+3 | DRY | 2024-01-13 | 2024-01-14 | Mahadev Eng | Rakesh Pathak | 1
40 | 2024-01-01 | 65/3 | DA+3 | DRY | 2024-01-13 | 2024-01-15 | Veerteja Enterprises | Rakesh Pathak | 2
41 | 2024-01-01 | 55/3 | DA+0 | Sandy | 2024-01-09 | 2024-01-15 | Imran | R T Singh | 6
42 | 2024-01-01 | 60/10 | DA+0 | DFR | 2024-01-14 | 2024-01-15 | Manoj Sharma | R T Singh | 1
43 | 2024-01-01 | 62/8 | DA+0 | DFR | 2024-01-15 | 2024-01-16 | Shakti Construction | Rakesh Pathak | 1
44 | 2024-01-01 | 55/4 | DA+0 | Sandy | 2024-01-12 | 2024-01-17 | Imran | R T Singh | 5
45 | 2024-01-01 | 57/5 | DA+3 | Sandy | 2024-01-14 | 2024-01-17 | Om Const | R T Singh | 3
46 | 2024-01-01 | 26/3 | DA+0 | DRY | 2024-01-12 | 2024-01-18 | A.B. Construction | Jeetu Sachan | 6
47 | 2024-01-01 | 64/1 | DA+0 | DRY | 2024-01-10 | 2024-01-18 | Mahadev Eng | Rakesh Pathak | 8
48 | 2024-01-01 | 64/5 | DA+3 | DRY | 2024-01-16 | 2024-01-18 | Mahadev Eng | Rakesh Pathak | 2
49 | 2024-01-01 | 65/6 | DA+0 | DRY | 2024-01-16 | 2024-01-18 | Bhati Const. | Rakesh Pathak | 2
50 | 2024-01-01 | 61/0 | DB2+0 | DRY | 2024-01-17 | 2024-01-19 | Manoj Sharma | R T Singh | 2
51 | 2024-01-01 | 62/9 | DA+3 | DFR | 2024-01-18 | 2024-01-19 | Shakti Construction | Rakesh Pathak | 1
52 | 2024-01-01 | 65/5 | DA+0 | DRY | 2024-01-20 | 2024-01-21 | Bhati Const. | Rakesh Pathak | 1
53 | 2024-01-01 | 64/2 | DA+3 | DRY | 2024-01-20 | 2024-01-21 | Mahadev Eng | Rakesh Pathak | 1
54 | 2024-01-01 | 57/6 | DA+3 | Sandy | 2024-01-18 | 2024-01-21 | Om Const | R T Singh | 3
55 | 2024-01-01 | 63/1 | DA+3 | DFR | 2024-01-21 | 2024-01-23 | Shakti Construction | Rakesh Pathak | 2
56 | 2024-01-01 | 64/9 | DA+3 | DRY | 2024-01-22 | 2024-01-24 | Veerteja Enterprises | Rakesh Pathak | 2
57 | 2024-01-01 | 60/11 | DA+3 | DRY | 2024-01-23 | 2024-01-24 | Manoj Sharma | R T Singh | 1
58 | 2024-01-01 | 65/4 | DA+0 | DRY | 2024-01-23 | 2024-01-24 | Bhati Const. | Rakesh Pathak | 1
59 | 2024-01-01 | 63/7 | DA+3 | DRY | 2024-01-24 | 2024-01-25 | Mahadev Eng | Rakesh Pathak | 1
60 | 2024-01-01 | 55/5 | DA+0 | Sandy | 2024-01-17 | 2024-01-25 | Imran | R T Singh | 8
61 | 2024-01-01 | 55/6 | DA+0 | Sandy | 2024-01-20 | 2024-01-25 | Imran | R T Singh | 5
62 | 2024-01-01 | 63/2 | DA+0 | DFR | 2024-01-24 | 2024-01-25 | Shakti Construction | Rakesh Pathak | 1
63 | 2024-01-01 | 27/8 | DA+0 | DFR | 2024-01-14 | 2024-01-27 | Nagana Ray And Company | Jeetu Sachan | 13
64 | 2024-01-01 | 61/1 | DA+6 | DFR | 2024-01-27 | 2024-01-28 | Manoj Sharma | R T Singh | 1
65 | 2024-01-01 | 55/7 | DA+0 | Sandy | 2024-01-27 | 2024-01-29 | Imran | R T Singh | 2
66 | 2024-01-01 | 64/3 | DA+0 | DRY | 2024-01-29 | 2024-01-30 | Mahadev Eng | Rakesh Pathak | 1
67 | 2024-01-01 | 63/3 | DA+3 | DFR | 2024-01-29 | 2024-01-30 | Shakti Construction | Rakesh Pathak | 1
68 | 2024-01-01 | 64/8 | DA+3 | DRY | 2024-01-29 | 2024-01-31 | Veerteja Enterprises | Rakesh Pathak | 2
69 | 2024-01-01 | 61/2 | DA+6 | DFR | 2024-01-30 | 2024-01-31 | Manoj Sharma | R T Singh | 1
70 | 2024-02-01 | 64/7 | DA+3 | DRY | 2024-02-01 | 2024-02-02 | Mahadev Eng | Rakesh Pathak | 1
71 | 2024-02-01 | 52/5 | DA+9 | Sandy | 2024-01-31 | 2024-02-02 | Imran | R T Singh | 2
72 | 2024-02-01 | 63/4 | DA+0 | DRY | 2024-02-01 | 2024-02-02 | Shakti Construction | Rakesh Pathak | 1
73 | 2024-02-01 | 26/4 | DA+6 | Sandy | 2024-01-27 | 2024-02-04 | Mehai Construction | Jeetu Sachan | 8
74 | 2024-02-01 | 67/2 | DA+0 | DRY | 2024-02-03 | 2024-02-04 | Bhati Const. | Rakesh Pathak | 1
75 | 2024-02-01 | 52/6 | DA+6 | Sandy | 2024-02-03 | 2024-02-06 | Imran | R T Singh | 3
76 | 2024-02-01 | 64/6 | DA+0 | DRY | 2024-02-03 | 2024-02-07 | Mahadev Eng | Rakesh Pathak | 4
77 | 2024-02-01 | 63/5 | DA+3 | DFR | 2024-02-06 | 2024-02-07 | Shakti Construction | Rakesh Pathak | 1
78 | 2024-02-01 | 59/15 | DA+6 | DRY | 2024-02-05 | 2024-02-07 | Om Const | R T Singh | 2
79 | 2024-02-01 | 61/5 | DA+3 | DRY | 2024-02-07 | 2024-02-09 | Manoj Sharma | R T Singh | 2
80 | 2024-02-01 | 67/1 | DA+0 | DRY | 2024-02-07 | 2024-02-09 | Bhati Const. | Rakesh Pathak | 2
81 | 2024-02-01 | 64/10 | DA+3 | DRY | 2024-02-08 | 2024-02-10 | Veerteja Enterprises | Rakesh Pathak | 2
82 | 2024-02-01 | 61/6 | DA+3 | DRY | 2024-02-09 | 2024-02-11 | Manoj Sharma | R T Singh | 2
83 | 2024-02-01 | 52/7 | DA+3 | Sandy | 2024-02-07 | 2024-02-12 | Imran | R T Singh | 5
84 | 2024-02-01 | 59/16 | DA+9 | Dry | 2024-02-11 | 2024-02-12 | Om Const | R T Singh | 1
85 | 2024-02-01 | 63/0 | DC1+0 | DFR | 2024-02-09 | 2024-02-13 | Shakti Construction | Rakesh Pathak | 4
86 | 2024-02-01 | 52/8 | DA+6 | Sandy | 2024-02-09 | 2024-02-13 | Imran | R T Singh | 4
87 | 2024-02-01 | 61/7 | DA+9 | Dry | 2024-02-11 | 2024-02-13 | Manoj Sharma | R T Singh | 2
88 | 2024-02-01 | 26/5 | DA+6 | Sandy | 2024-02-05 | 2024-02-16 | Mehai Construction | Jeetu Sachan | 11
89 | 2024-02-01 | 61/9 | DA+0 | Dry | 2024-02-14 | 2024-02-16 | Manoj Sharma | R T Singh | 2
90 | 2024-02-01 | 60/1 | DA+6 | DRY | 2024-02-14 | 2024-02-16 | Om Const | R T Singh | 2
91 | 2024-02-01 | 28/0 | DB2+0 | DFR | 2024-02-05 | 2024-02-17 | A.B. Construction | Jeetu Sachan | 12
92 | 2024-02-01 | 52/10 | DA+9 | Sandy | 2024-02-14 | 2024-02-17 | Imran | R T Singh | 3
93 | 2024-02-01 | 27/11 | DA+3 | DRY | 2024-02-10 | 2024-02-18 | A.B. Construction | Jeetu Sachan | 8
94 | 2024-02-01 | 49/2 | DA+3 | Sandy | 2024-02-14 | 2024-02-18 | Veerteja Enterprises | R T Singh | 4
95 | 2024-02-01 | 52/9 | DA+3 | Sandy | 2024-02-17 | 2024-02-19 | Imran | R T Singh | 2
96 | 2024-02-01 | 61/8 | DA+6 | DRY | 2024-02-17 | 2024-02-20 | Manoj Sharma | R T Singh | 3
97 | 2024-02-01 | 62/1 | DA+3 | Sandy | 2024-02-17 | 2024-02-21 | Shakti Construction | Rakesh Pathak | 4
98 | 2024-02-01 | 53/5 | DA+3 | Sandy | 2024-02-21 | 2024-02-22 | Imran | R T Singh | 1
99 | 2024-02-01 | 64/11 | DA+3 | DRY | 2024-02-23 | 2024-02-24 | Bhati Const. | Rakesh Pathak | 1
100 | 2024-02-01 | 60/2 | DA+3 | DFR | 2024-02-20 | 2024-02-24 | Om Const | R T Singh | 4
101 | 2024-02-01 | 21/10 | DA+6 | DRY | 2024-02-19 | 2024-02-25 | Swarup Enterprises | Jeetu Sachan | 6
102 | 2024-02-01 | 60/3 | DA+3 | DFR | 2024-02-25 | 2024-02-28 | Manoj Sharma | R T Singh | 3
103 | 2024-02-01 | 26/6 | DA+6 | Sandy | 2024-02-20 | 2024-02-29 | Mehai Construction | Jeetu Sachan | 9
104 | 2024-02-01 | 65/0 | DB1+0 | DRY | 2024-02-28 | 2024-02-29 | Bhati Const. | Rakesh Pathak | 1
105 | 2024-02-01 | 60/4 | DA+3 | DFR | 2024-02-27 | 2024-02-29 | Manoj Sharma | R T Singh | 2
106 | 2024-03-01 | 22/1 | DA+9 | Sandy | 2024-02-26 | 2024-03-02 | Swarup Enterprises | Jeetu Sachan | 5
107 | 2024-03-01 | 61/10 | DA+9 | DRY | 2024-02-03 | 2024-03-04 | Manoj Sharma | R T Singh | 30
108 | 2024-03-01 | 65/1 | DA+0 | DRY | 2024-03-03 | 2024-03-05 | Bhati Const. | Rakesh Pathak | 2
109 | 2024-03-01 | 22/6 | DA+0 | Sandy | 2024-03-01 | 2024-03-09 | A.B. Construction | Jeetu Sachan | 8
110 | 2024-03-01 | 62/0 | DB2+0 | DRY | 2024-03-06 | 2024-03-10 | Manoj Sharma | R T Singh | 4
111 | 2024-03-01 | 61/4 | DA+3 | DRY | 2024-03-13 | 2024-03-14 | Manoj Sharma | R T Singh | 1
112 | 2024-03-01 | 49/3 | DA+3 | Sandy | 2024-03-13 | 2024-03-15 | Veerteja Enterprises | R T Singh | 2
113 | 2024-03-01 | 27/5 | DA+0 | DRY | 2024-01-31 | 2024-03-17 | Majisa Construction | Jeetu Sachan | 46
114 | 2024-03-01 | 49/6 | DA+0 | Sandy | 2024-03-14 | 2024-03-17 | Shakti Construction | R T Singh | 3
115 | 2024-03-01 | 60/0 | DC1+0 | DRY | 2024-03-15 | 2024-03-19 | Manoj Sharma | R T Singh | 4
116 | 2024-03-01 | 49/4 | DA+3 | Sandy | 2024-03-15 | 2024-03-19 | Veerteja Enterprises | R T Singh | 4
117 | 2024-03-01 | 49/5 | DA+3 | Sandy | 2024-03-18 | 2024-03-20 | Shakti Construction | R T Singh | 2
118 | 2024-03-01 | 47/10 | DA+6 | Sandy | 2024-03-18 | 2024-03-20 | Bhati Const. | R T Singh | 2
119 | 2024-03-01 | 47/9 | DA+3 | Sandy | 2024-03-21 | 2024-03-23 | Bhati Const. | R T Singh | 2
120 | 2024-03-01 | 47/8 | DA+0 | Sandy | 2024-03-26 | 2024-03-29 | Bhati Const. |  | 3
121 | 2024-03-01 | 47/7 | DA+3 | Sandy | 2024-03-30 | 2024-03-31 | Bhati Const. |  | 1
122 | 2024-04-01 | 50/9 | DA+0 | Sandy | 2024-03-22 | 2024-04-01 | Shakti Construction | R T Singh | 10
123 | 2024-04-01 | 48/0 | DC2+0 | Sandy | 2024-04-03 | 2024-04-07 | Bhati Const. | R T Singh | 4
124 | 2024-04-01 | 50/10 | DA+0 | Sandy | 2024-04-03 | 2024-04-08 | Shakti Construction | R T Singh | 5
125 | 2024-04-01 | 51/1 | DA+0 | Sandy | 2024-04-08 | 2024-04-13 | Shakti Construction |  | 5
126 | 2024-04-01 | 48/1 | DA+9 | Sandy | 2024-04-08 | 2024-04-15 | Veerteja Enterprises | R T Singh | 7
127 | 2024-04-01 | 50/8 | DA+9 | Sandy | 2024-04-14 | 2024-04-19 | Shakti Construction | R T Singh | 5
128 | 2024-04-01 | 49/1 | DA+0 | Sandy | 2024-04-17 | 2024-04-20 | Veerteja Enterprises | R T Singh | 3
129 | 2024-05-01 | 49/0 | DD45+0 | Sandy | 2024-04-22 | 2024-05-03 | Veerteja Enterprises | R T Singh | 11
130 | 2024-05-01 | 43/6 | DA+3 | Sandy | 2024-05-02 | 2024-05-08 | Bande Bharat Group | Kuntal Debnath | 6
131 | 2024-05-01 | 8/7 | DB1+0 | DRY | 2024-05-05 | 2024-05-10 | Mateshwari Const. | Abhijit Dutta | 5
132 | 2024-05-01 | 50/7 | DA+0 | Sandy | 2024-05-05 | 2024-05-10 | Veerteja Enterprises | R T Singh | 5
133 | 2024-05-01 | 8/10 | DA+3 | DFR | 2024-05-14 | 2024-05-18 | Mateshwari Const. | Abhijit Dutta | 4
134 | 2024-05-01 | 50/1 | DA+6 | Sandy | 2024-05-14 | 2024-05-18 | Veerteja Enterprises | R T Singh | 4
135 | 2024-05-01 | 47/6 | DA+3 | Sandy | 2024-05-15 | 2024-05-18 | Bhati Const. | R T Singh | 3
136 | 2024-05-01 | 52/3 | DA+9 | Sandy | 2024-05-14 | 2024-05-25 | Sb Mehar Const. | R T Singh | 11
137 | 2024-05-01 | 47/2 | DA+9 | Sandy | 2024-05-23 | 2024-05-26 | Bhati Const. | R T Singh | 3
138 | 2024-05-01 | 10/14 | DA+3 | DRY | 2024-05-19 | 2024-05-27 | Mateshwari Const. | Abhijit Dutta | 8
139 | 2024-05-01 | 10/19 | DA+0 | DRY | 2024-05-18 | 2024-05-28 | Jai Bhawani Construction | Abhijit Dutta | 10
140 | 2024-05-01 | 50/4 | DA+9 | Sandy | 2024-05-20 | 2024-05-28 | Veerteja Enterprises | R T Singh | 8
141 | 2024-05-01 | 51/2 | DA+0 | Sandy | 2024-05-25 | 2024-05-31 | Sb Mehar Const. | R T Singh | 6
142 | 2024-05-01 | 47/5 | DA+0 | Sandy | 2024-05-29 | 2024-05-31 | Bhati Const. | R T Singh | 2
143 | 2024-05-01 | 50/2 | DA+9 | Sandy | 2024-05-26 | 2024-05-31 | Veerteja Enterprises | R T Singh | 5
144 | 2024-06-01 | 10/11 | DA+3 | DRY | 2024-05-29 | 2024-06-02 | Mateshwari Const. | Abhijit Dutta | 4
145 | 2024-06-01 | 10/18 | DA+3 | DFR | 2024-05-29 | 2024-06-05 | Jai Bhawani Construction | Abhijit Dutta | 7
146 | 2024-06-01 | 10/13 | DA+3 | DRY | 2024-05-30 | 2024-06-06 | Mateshwari Const. | Abhijit Dutta | 7
147 | 2024-06-01 | 47/3 | DA+9 | Sandy | 2024-06-03 | 2024-06-08 | Bhati Const. | R T Singh | 5
148 | 2024-06-01 | 51/0 | DC2+0 | Sandy | 2024-06-03 | 2024-06-10 | Sb Mehar Const. | R T Singh | 7
149 | 2024-06-01 | 10/17 | DA+3 | DFR | 2024-06-03 | 2024-06-15 | Jai Bhawani Construction | Abhijit Dutta | 12
150 | 2024-06-01 | 53/7 | DA+3 | Sandy | 2024-06-12 | 2024-06-15 | Bhati Const. | R T Singh | 3
151 | 2024-06-01 | 10/8 | DA+3 | DFR | 2024-06-08 | 2024-06-19 | Mateshwari Const. | Abhijit Dutta | 11
152 | 2024-06-01 | 10/12 | DB1+0 | DRY | 2024-06-10 | 2024-06-27 | Mateshwari Const. | Abhijit Dutta | 17
153 | 2024-07-01 | 15/1 | DA+3 | DRY | 2024-06-29 | 2024-07-06 | Om Enterprise | Jeetu Sachan | 7
154 | 2024-07-01 | 10/20 | DA+3 | DFR | 2024-06-20 | 2024-07-07 | Jai Bhawani Construction | Abhijit Dutta | 17
155 | 2024-07-01 | 11A/5 | DA+3 | DRY | 2024-07-04 | 2024-07-12 | Punia Construction | Abhijit Dutta | 8
156 | 2024-07-01 | 10/21 | DA+3 | DFR | 2024-06-28 | 2024-07-14 | Jai Bhawani Construction | Abhijit Dutta | 16
157 | 2024-07-01 | 18/1 | DA+0 | DRY | 2024-07-07 | 2024-07-14 | J.P. Infra | Abhijit Dutta | 7
158 | 2024-07-01 | 15/0 | DC1+0 | DRY | 2024-07-07 | 2024-07-15 | Om Enterprise | Jeetu Sachan | 8
159 | 2024-07-01 | 14A/1 | DA+3 | DRY | 2024-07-14 | 2024-07-22 | Majisa Construction | Jeetu Sachan | 8
160 | 2024-07-01 | 50/0 | DB2+0 | Sandy | 2024-07-10 | 2024-07-22 | Veerteja Enterprises | R T Singh | 12
161 | 2024-07-01 | 11A/6 | DA+6 | DRY | 2024-07-10 | 2024-07-26 | Punia Construction | Bipin Kumar | 16
162 | 2024-07-01 | 10/6 | DA+0 | DFR | 2024-07-16 | 2024-07-26 | Jai Bhawani Construction | Bipin Kumar | 10
163 | 2024-07-01 | 16/0 | DC1+0 | DRY | 2024-07-03 | 2024-07-26 | Majisa Construction | Jeetu Sachan | 23
164 | 2024-07-01 | 58/0 | DC1+3 | DFR | 2024-07-23 | 2024-07-29 | Bhati Const. | R T Singh | 6
165 | 2024-07-01 | 18/0 | DC2+0 | DRY | 2024-07-20 | 2024-07-31 | J.P. Infra | Jeetu Sachan | 11
166 | 2024-07-01 | 11/5 | DA+0 | DFR | 2024-07-18 | 2024-07-31 | Mci | Bipin Kumar | 13
167 | 2024-08-01 | 10/3 | DA+0 | DFR | 2024-07-22 | 2024-08-03 | Jai Bhawani Construction | Bipin Kumar | 12
168 | 2024-08-01 | 11A/7 | DA+9 | Sandy | 2024-07-27 | 2024-08-07 | Punia Construction | Bipin Kumar | 11
169 | 2024-08-01 | 18/2 | DA+0 | DRY | 2024-07-30 | 2024-08-09 | Vibe Infra | Jeetu Sachan | 10
170 | 2024-08-01 | 17/3 | DA+0 | DRY | 2024-07-30 | 2024-08-10 | J.P. Infra | Jeetu Sachan | 11
171 | 2024-08-01 | 57/7 | DA+3 | DFR | 2024-08-07 | 2024-08-10 | Bhati Const. | R T Singh | 3
172 | 2024-08-01 | 16/3 | DA+3 | DRY | 2024-08-03 | 2024-08-12 | Majisa Construction | Jeetu Sachan | 9
173 | 2024-08-01 | 43/9 | DA+9 | Sandy | 2024-08-07 | 2024-08-13 | N.R. Enterprises | Kuntal Debnath | 6
174 | 2024-08-01 | 17/5 | DA+3 | DRY | 2024-08-07 | 2024-08-14 | J.P. Infra | Jeetu Sachan | 7
175 | 2024-08-01 | 11A/2 | DA+0 | DRY | 2024-08-12 | 2024-08-16 | R.K. Construction | Bipin Kumar | 4
176 | 2024-08-01 | 16/4 | DA+0 | DRY | 2024-08-10 | 2024-08-18 | Om Enterprise | Jeetu Sachan | 8
177 | 2024-08-01 | 18/3 | DA+0 | DRY | 2024-08-10 | 2024-08-18 | Vibe Infra | Jeetu Sachan | 8
178 | 2024-08-01 | 17/4 | DA+3 | DRY | 2024-08-15 | 2024-08-19 | J.P. Infra | Jeetu Sachan | 4
179 | 2024-08-01 | 10/9 | DA+0 | DRY | 2024-08-12 | 2024-08-19 | A.B. Construction | Bipin Kumar | 7
180 | 2024-08-01 | 11A/8 | DA+6 | Sandy | 2024-08-07 | 2024-08-20 | Punia Construction | Bipin Kumar | 13
181 | 2024-08-01 | 11A/9 | DA+3 | DRY | 2024-08-16 | 2024-08-22 | Punia Construction | Bipin Kumar | 6
182 | 2024-08-01 | 43/8 | DA+9 | Sandy | 2024-08-14 | 2024-08-22 | N.R. Enterprises | Kuntal Debnath | 8
183 | 2024-08-01 | 18/4 | DA+0 | DRY | 2024-08-13 | 2024-08-23 | Vibe Infra | Jeetu Sachan | 10
184 | 2024-08-01 | 59/2 | DA+3 | DFR | 2024-08-19 | 2024-08-23 | Bhati Const. | R T Singh | 4
185 | 2024-08-01 | 16/2 | DA+0 | DRY | 2024-08-14 | 2024-08-24 | Om Enterprise | Jeetu Sachan | 10
186 | 2024-08-01 | 11A/0 | DB1+0 | DRY | 2024-08-12 | 2024-08-25 | Mci | Abhijit Dutta | 13
187 | 2024-08-01 | 50/6 | DA+9 | Sandy | 2024-08-14 | 2024-08-28 | Kalpana Const. | R T Singh | 14
188 | 2024-08-01 | 53/8 | DA+3 | Sandy | 2024-08-26 | 2024-08-29 | Bhati Const. | R T Singh | 3
189 | 2024-08-01 | 17/1 | DA+3 | DRY | 2024-08-24 | 2024-08-30 | J.P. Infra | Jeetu Sachan | 6
190 | 2024-08-01 | 43/7 | DA+3 | Sandy | 2024-08-24 | 2024-08-30 | N.R. Enterprises | Kuntal Debnath | 6
191 | 2024-08-01 | 16/5 | DA+3 | DRY | 2024-08-28 | 2024-08-31 | Majisa Construction | Jeetu Sachan | 3
192 | 2024-08-01 | 19/0 | DC2+0 | DRY | 2024-08-22 | 2024-08-31 | Vibe Infra | Jeetu Sachan | 9
193 | 2024-09-01 | 11A/1 | DA+3 | DRY | 2024-08-22 | 2024-09-01 | Mci | Abhijit Dutta | 10
194 | 2024-09-01 | 19/1 | DA+0 | DRY | 2024-08-29 | 2024-09-03 | Vibe Infra | Jeetu Sachan | 5
195 | 2024-09-01 | 17/2 | DA+6 | DRY | 2024-08-27 | 2024-09-03 | J.P. Infra | Jeetu Sachan | 7
196 | 2024-09-01 | 13/2 | DA+3 | DRY | 2024-08-28 | 2024-09-03 | Punia Construction | Abhijit Dutta | 6
197 | 2024-09-01 | 43/5 | DA+3 | DRY | 2024-08-25 | 2024-09-05 | N.R. Enterprises | Kuntal Debnath | 11
198 | 2024-09-01 | 53/6 | DA+6 | Sandy | 2024-08-30 | 2024-09-05 | Bhati Const. | R T Singh | 6
199 | 2024-09-01 | 16/1 | DA+0 | DRY | 2024-08-27 | 2024-09-06 | Sidhi Vinayak | Jeetu Sachan | 10
200 | 2024-09-01 | 11A/4 | DA+3 | DRY | 2024-09-02 | 2024-09-07 | Punia Construction | Jeetu Sachan | 5
201 | 2024-09-01 | 54/1 | DA+3 | Sandy | 2024-09-05 | 2024-09-09 | Bhati Const. | R T Singh | 4
202 | 2024-09-01 | 50/3 | DA+6 | Sandy | 2024-09-01 | 2024-09-10 | Kalpana Const. | R T Singh | 9
203 | 2024-09-01 | 73/0 | DB2+0 | DRY | 2024-09-09 | 2024-09-10 | Shree Shyam Const. |  | 1
204 | 2024-09-01 | 73/9 | DA+0 | DRY | 2024-09-08 | 2024-09-11 | Shakti Construction |  | 3
205 | 2024-09-01 | 73/2 | DA+0 | DRY | 2024-09-12 | 2024-09-13 | Shree Shyam Const. |  | 1
206 | 2024-09-01 | 25/0 | DC1+6 | DRY | 2024-09-05 | 2024-09-14 | J.P. Infra | Jeetu Sachan | 9
207 | 2024-09-01 | 54/2 | DA+3 | Sandy | 2024-09-11 | 2024-09-14 | Bhati Const. | R T Singh | 3
208 | 2024-09-01 | 14A/2 | DA+0 | DRY | 2024-09-08 | 2024-09-16 | Sidhi Vinayak | Jeetu Sachan | 8
209 | 2024-09-01 | 10/4 | DA+3 | DFR | 2024-08-27 | 2024-09-16 | A.B. Construction | Abhijit Dutta | 20
210 | 2024-09-01 | 73/1 | DA+0 | DRY | 2024-09-15 | 2024-09-16 | Shree Shyam Const. | Sk Sil | 1
211 | 2024-09-01 | 14/0 | DC2+0 | Sandy | 2024-09-05 | 2024-09-18 | Om Enterprise | Jeetu Sachan | 13
212 | 2024-09-01 | 11A/3 | DA+3 | DRY | 2024-09-05 | 2024-09-19 | R.K. Construction | Abhijit Dutta | 14
213 | 2024-09-01 | 73/6 | DA+0 | DRY | 2024-09-18 | 2024-09-19 | Shree Shyam Const. | Sk Sil | 1
214 | 2024-09-01 | 42/3 | DA+0 | Sandy | 2024-09-05 | 2024-09-20 | Mahadev Construction | Kuntal Debnath | 15
215 | 2024-09-01 | 69/1 | DA+3 | DRY | 2024-09-19 | 2024-09-20 | Bhati Const. | Sk Sil | 1
216 | 2024-09-01 | 25/4 | DA+0 | Sandy | 2024-09-13 | 2024-09-23 | J.P. Infra | Jeetu Sachan | 10
217 | 2024-09-01 | 73/5 | DA+0 | DRY | 2024-09-22 | 2024-09-23 | Shree Shyam Const. |  | 1
218 | 2024-09-01 | 43/4 | DA+3 | Sandy | 2024-09-10 | 2024-09-25 | N.R. Enterprises | Kuntal Debnath | 15
219 | 2024-09-01 | 13/1 | DA+9 | DRY | 2024-09-19 | 2024-09-25 | Punia Construction | Abhijit Dutta | 6
220 | 2024-09-01 | 40/2 | DA+3 | Sandy | 2024-09-19 | 2024-09-25 | D.R. Construction | Kuntal Debnath | 6
221 | 2024-09-01 | 73/8 | DA+3 | DRY | 2024-09-23 | 2024-09-25 | Shakti Construction |  | 2
222 | 2024-09-01 | 59/1 | DA+3 | DRY | 2024-09-20 | 2024-09-25 | Bhati Const. | R T Singh | 5
223 | 2024-09-01 | 19/2 | DA+0 | DRY | 2024-09-20 | 2024-09-26 | Vibe Infra | Jeetu Sachan | 6
224 | 2024-09-01 | 72/2 | DA+0 | DRY | 2024-09-25 | 2024-09-26 | Shree Shyam Const. |  | 1
225 | 2024-09-01 | 17/0 | DB2+3 | DRY | 2024-09-19 | 2024-09-27 | Om Enterprise | Jeetu Sachan | 8
226 | 2024-09-01 | 66/0 | DC2+6 | DRY | 2024-09-23 | 2024-09-27 | Bhati Const. | Sk Sil | 4
227 | 2024-09-01 | 59/11 | DA+6 | DFR | 2024-09-25 | 2024-09-27 | Mahadev Eng | R T Singh | 2
228 | 2024-09-01 | 19/3 | DA+0 | DRY | 2024-09-28 | 2024-09-30 | Vibe Infra | Jeetu Sachan | 2
229 | 2024-09-01 | 43/3 | DA+0 | DRY | 2024-09-15 | 2024-09-30 | Parsuram Sai | Kuntal Debnath | 15
230 | 2024-09-01 | 73/3 | DA+0 | DRY | 2024-09-25 | 2024-09-30 | Awadh Const. |  | 5
231 | 2024-10-01 | 73/7 | DA+0 | DRY | 2024-09-29 | 2024-10-01 | Shakti Construction |  | 2
232 | 2024-10-01 | 59/0 | DC2+0 | DRY | 2024-09-29 | 2024-10-04 | Bhati Const. | R T Singh | 5
233 | 2024-10-01 | 67/0 | DC1+9 | DRY | 2024-10-04 | 2024-10-05 | Bhati Const. |  | 1
234 | 2024-10-01 | 42/5 | DA+9 | Sandy | 2024-09-23 | 2024-10-07 | Mahadev Construction | Kuntal Debnath | 14
235 | 2024-10-01 | 43/0 | DB1+0 | Sandy | 2024-09-28 | 2024-10-07 | N.R. Enterprises | Kuntal Debnath | 9
236 | 2024-10-01 | 25/3 | DA+0 | Sandy | 2024-09-15 | 2024-10-08 | J.P. Infra | Bipin Kumar | 23
237 | 2024-10-01 | 69/0 | DB2+0 | DFR | 2024-09-28 | 2024-10-09 | Bhati Const. | Sk Sil | 11
238 | 2024-10-01 | 73/4 | DA+0 | DRY | 2024-10-08 | 2024-10-09 | Shree Shyam Const. | Sk Sil | 1
239 | 2024-10-01 | 22/13 | DA+6 | Sandy | 2024-09-25 | 2024-10-10 | Rbm | Bipin Kumar | 15
240 | 2024-10-01 | 74/0 | DB2+0 | Sandy | 2024-10-07 | 2024-10-10 | Shakti Construction | Sk Sil | 3
241 | 2024-10-01 | 25/1 | DA+3 | DRY | 2024-09-28 | 2024-10-12 | J.P. Infra | Bipin Kumar | 14
242 | 2024-10-01 | 43/2 | DA+0 | Sandy | 2024-09-28 | 2024-10-12 | Parsuram Sai | Kuntal Debnath | 14
243 | 2024-10-01 | 72/3 | DA+3 | DRY | 2024-10-14 | 2024-10-15 | Shree Shyam Const. | Sk Sil | 1
244 | 2024-10-01 | 43/11 | DA+3 | Sandy | 2024-09-25 | 2024-10-18 | Jitendra Enterprises | Kuntal Debnath | 23
245 | 2024-10-01 | 13/0 | DD60+3 | DRY | 2024-10-04 | 2024-10-18 | R.K. Construction | Jeetu Sachan | 14
246 | 2024-10-01 | 71/7 | DA+3 | DRY | 2024-10-17 | 2024-10-18 | Shree Shyam Const. | Sk Sil | 1
247 | 2024-10-01 | 59/4 | DA+3 | DFR | 2024-10-14 | 2024-10-19 | Bhati Const. | R T Singh | 5
248 | 2024-10-01 | 22/12 | DA+3 | Sandy | 2024-10-11 | 2024-10-21 | Rbm | Bipin Kumar | 10
249 | 2024-10-01 | 42/1 | DA+6 | Sandy | 2024-10-10 | 2024-10-21 | N.R. Enterprises | Kuntal Debnath | 11
250 | 2024-10-01 | 71/6 | DA+0 | DRY | 2024-10-20 | 2024-10-21 | Shree Shyam Const. | Sk Sil | 1
251 | 2024-10-01 | 49/7 | DA+0 | Sandy | 2024-09-12 | 2024-10-21 | Kalpana Const. | R T Singh | 39
252 | 2024-10-01 | 25/2 | DA+0 | DRY | 2024-10-12 | 2024-10-22 | J.P. Infra | Bipin Kumar | 10
253 | 2024-10-01 | 13/3 | DA+3 | Sandy | 2024-09-28 | 2024-10-25 | Punia Construction | Ashutosh Singh | 27
254 | 2024-10-01 | 22/7 | DA+0 | Sandy | 2024-10-24 | 2024-10-27 | Rbm | Bipin Kumar | 3
255 | 2024-10-01 | 22/3 | DA+9 | Sandy | 2024-10-24 | 2024-10-27 | J.P. Infra | Bipin Kumar | 3
256 | 2024-10-01 | 43/1 | DA+3 | Sandy | 2024-10-16 | 2024-10-30 | Parsuram Sai | Kuntal Debnath | 14
257 | 2024-11-01 | 42/6 | DA+0 | Sandy | 2024-10-22 | 2024-11-07 | D.R. Construction | Kuntal Debnath | 16
258 | 2024-11-01 | 2/4 | DA+3 | Sandy | 2024-11-12 | 2024-11-16 | Laxmi Enterprises | Ashutosh Kumar | 4
259 | 2024-11-01 | 42/2 | DA+6 | Sandy | 2024-11-08 | 2024-11-17 | D.R. Construction | Kuntal Debnath | 9
260 | 2024-11-01 | 22/8 | DB1+0 | Sandy | 2024-11-06 | 2024-11-19 | Rbm | Bipin Kumar | 13
261 | 2024-11-01 | 22/2 | DA+6 | Sandy | 2024-11-11 | 2024-11-20 | J.P. Infra | Bipin Kumar | 9
262 | 2024-11-01 | 54/0 | DB1+6 | Sandy | 2024-11-15 | 2024-11-21 | Bhati Const. | R T Singh | 6
263 | 2024-11-01 | 65/8 | DA+0 | DRY | 2024-11-27 | 2024-11-28 | Bhati Const. | Sk Sil | 1
264 | 2024-11-01 | 42/0 | DC1+0 | Sandy | 2024-11-20 | 2024-11-30 | D.R. Construction | Kuntal Debnath | 10
265 | 2024-11-01 | 65/7 | DA+0 | DRY | 2024-11-29 | 2024-11-30 | Bhati Const. | Sk Sil | 1
266 | 2024-12-01 | 2/3 | DA+3 | Sandy | 2024-11-29 | 2024-12-03 | Laxmi Enterprise | Karan Singh | 4
267 | 2024-12-01 | 22/4 | DA+9 | Sandy | 2024-12-01 | 2024-12-05 | Jp Infra | Bipin Singh | 4
268 | 2024-12-01 | 6/1 | DA+0 | DFR | 2024-12-01 | 2024-12-10 | H.S. Engineering | Jitendra Yadav | 9
269 | 2024-12-01 | 12/0 | DD60+0 | DRY | 2024-12-07 | 2024-12-14 | Vibe Infra Power | Jitendra Yadav | 7
270 | 2024-12-01 | 22/5 | DA+9 | DRY | 2024-12-09 | 2024-12-14 | S.D. Infra | Bipin Singh | 5
271 | 2024-12-01 | 41/2 | DA+0 | Sandy | 2024-10-26 | 2024-12-15 | D.R. Construction | Kuntal Debnath | 50
272 | 2024-12-01 | 2/5 | DA+3 | Sandy | 2024-12-10 | 2024-12-15 | Sri Nagana Ray Enterprise | Jitendra Yadav | 5
273 | 2024-12-01 | 22/9 | DA+6 | Sandy | 2024-12-13 | 2024-12-16 | Rbm | Bipin Singh | 3
274 | 2024-12-01 | 70/8 | DA+3 | DRY | 2024-12-16 | 2024-12-17 | Tantray Construction | Sk Sil | 1
275 | 2024-12-01 | 72/1 | DA+3 | DRY | 2024-12-16 | 2024-12-18 | Meer Const | Sk Sil | 2
276 | 2024-12-01 | 70/7 | DA+3 | DRY | 2024-12-17 | 2024-12-19 | Tantray Construction | Sk Sil | 2
277 | 2024-12-01 | 71/8 | DA+3 | DRY | 2024-12-19 | 2024-12-20 | Meer Const | Sk Sil | 1
278 | 2024-12-01 | 52/1 | DA+6 | Sandy | 2024-12-17 | 2024-12-20 | Tantray Construction |  | 3
279 | 2024-12-01 | 70/9 | DA+3 | DRY | 2024-12-20 | 2024-12-21 | Tantray Construction | Sk Sil | 1
280 | 2024-12-01 | 6/2 | DA+0 | DFR | 2024-12-18 | 2024-12-23 | Hs Engineering | Jitendra Yadav | 5
281 | 2024-12-01 | 72/0 | DB2+3 | DRY | 2024-12-22 | 2024-12-23 | Meer Const | Sk Sil | 1
282 | 2024-12-01 | 70/6 | DA+3 | DRY | 2024-12-22 | 2024-12-23 | Tantray Construction | Sk Sil | 1
283 | 2024-12-01 | 2/6 | DA+3 | Sandy | 2024-12-12 | 2024-12-24 | Sri Nagana Ray Enterprise | Jitendra Yadav | 12
284 | 2024-12-01 | 71/4 | DA+3 | DRY | 2024-12-24 | 2024-12-25 | Meer Const | Sk Sil | 1
285 | 2024-12-01 | 52/2 | DA+6 | Sandy | 2024-12-24 | 2024-12-25 | Tantray Construction | R T Singh | 1
286 | 2024-12-01 | 70/10 | DA+3 | DRY | 2024-12-24 | 2024-12-25 | Tantray Construction |  | 1
287 | 2024-12-01 | 2/2 | DA+3 | Sandy | 2024-12-17 | 2024-12-27 | Laxmi Enterprises | Jitendra Yadav | 10
288 | 2024-12-01 | 71/5 | DA+3 | DRY | 2024-12-26 | 2024-12-27 | Meer Const | Sk Sil | 1
289 | 2024-12-01 | 70/11 | DA+3 | DRY | 2024-12-26 | 2024-12-27 | Tantray Construction | Sk Sil | 1
290 | 2024-12-01 | 53/2 | DA+0 | Sandy | 2024-12-25 | 2024-12-29 | Meer Const | R T Singh | 4
291 | 2024-12-01 | 36/0 | DB2+0 | Sandy | 2024-12-21 | 2024-12-30 | Parsuram Sahi | Kuntal Debnath | 9
292 | 2024-12-01 | 71/3 | DA+6 | DRY | 2024-12-29 | 2024-12-30 | Meer Const | Sk Sil | 1
293 | 2024-12-01 | 52/4 | DA+9 | Sandy | 2024-12-27 | 2024-12-30 | Tantray Construction | R T Singh | 3
294 | 2024-12-01 | 10/5 | DA+3 | DRY | 2024-12-25 | 2024-12-31 | Jsr Infrastructure | Jitendra Yadav | 6
295 | 2024-12-01 | 35/4 | DA+0 | DRY | 2024-12-25 | 2024-12-31 | Parsuram Sahi | Kuntal Debnath | 6
296 | 2024-12-01 | 71/0 | DB2+3 | DRY | 2024-12-29 | 2024-12-31 | Tantray Construction | Sk Sil | 2
297 | 2025-01-01 | 22/11 | DA+6 | Sandy | 2024-12-23 | 2025-01-04 | Rbm | Bipin Singh | 12
298 | 2025-01-01 | 71/2 | DA+3 | DRY | 2024-12-31 | 2025-01-04 | Meer Const | Sk Sil | 4
299 | 2025-01-01 | 71/1 | DA+3 | DRY | 2025-01-04 | 2025-01-06 | Meer Const | Sk Sil | 2
300 | 2025-01-01 | 54/3 | DA+6 | Sandy | 2025-01-02 | 2025-01-06 | Tantray Construction | R T Singh | 4
301 | 2025-01-01 | 44/1 | DA+0 | Sandy | 2025-01-02 | 2025-01-06 | Tantray Construction | R T Singh | 4
302 | 2025-01-01 | 44/2 | DA+0 | Sandy | 2025-01-04 | 2025-01-07 | Tantray Construction | R T Singh | 3
303 | 2025-01-01 | 8/9 | DA+3 | DFR | 2025-01-02 | 2025-01-08 | Jsr Infrastructure | Sumit Kumar | 6
304 | 2025-01-01 | 53/1 | DA+9 | Sandy | 2024-12-29 | 2025-01-08 | Meer Const | R T Singh | 10
305 | 2025-01-01 | 70/3 | DA+3 | DRY | 2025-01-07 | 2025-01-09 | Meer Const | Sk Sil | 2
306 | 2025-01-01 | 54/4 | DA+9 | Sandy | 2025-01-06 | 2025-01-09 | Tantray Construction | R T Singh | 3
307 | 2025-01-01 | 45/0 | DC2+0 | Sandy | 2025-01-06 | 2025-01-09 | Nadeem | R T Singh | 3
308 | 2025-01-01 | 44/11 | DA+0 | Sandy | 2025-01-07 | 2025-01-09 | Nadeem | R T Singh | 2
309 | 2025-01-01 | 53/0 | DB2+9 | Sandy | 2025-01-06 | 2025-01-12 | Meer Const | R T Singh | 6
310 | 2025-01-01 | 44/10 | DB1+9 | Sandy | 2025-01-11 | 2025-01-12 | Nadeem | R T Singh | 1
311 | 2025-01-01 | 44/4 | DA+9 | Sandy | 2025-01-08 | 2025-01-12 | Tantray Construction | R T Singh | 4
312 | 2025-01-01 | 70/4 | DA+3 | DRY | 2025-01-12 | 2025-01-13 | Meer Const | Sk Sil | 1
313 | 2025-01-01 | 34/1 | DA+9 | Sandy | 2025-01-08 | 2025-01-14 | Ymk Construction | Kuntal Debnath | 6
314 | 2025-01-01 | 70/5 | DA+3 | DRY | 2025-01-13 | 2025-01-15 | Meer Const | Sk Sil | 2
315 | 2025-01-01 | 53/3 | DA+6 | Sandy | 2025-01-11 | 2025-01-15 | Meer Const | R T Singh | 4
316 | 2025-01-01 | 35/2 | DB1+0 | Sandy | 2025-01-08 | 2025-01-16 | Parsuram Sahi | Kuntal Debnath | 8
317 | 2025-01-01 | 68/0 | DD45+0 | DRY | 2025-01-13 | 2025-01-17 | Bhati Const. |  | 4
318 | 2025-01-01 | 1A/1 | DA+6 | DFR | 2025-01-11 | 2025-01-18 | Jsr Infrastructure | Sumit Kumar | 7
319 | 2025-01-01 | 53/4 | DA+0 | Sandy | 2025-01-14 | 2025-01-18 | Meer Const | R T Singh | 4
320 | 2025-01-01 | 52/0 | DC2+0 | Sandy | 2025-01-11 | 2025-01-18 | Tantray Construction | R T Singh | 7
321 | 2025-01-01 | 44/5 | DA+9 | Sandy | 2025-01-13 | 2025-01-19 | Tantray Construction | R T Singh | 6
322 | 2025-01-01 | 2/0 | DC1+0 | DRY | 2025-01-04 | 2025-01-20 | Laxmi Enterprises | Sumit Kumar | 16
323 | 2025-01-01 | 44/9 | DA+9 | Sandy | 2025-01-15 | 2025-01-20 | Iqbal | R T Singh | 5
324 | 2025-01-01 | 70/1 | DA+3 | DRY | 2025-01-17 | 2025-01-21 | Meer Const | Sk Sil | 4
325 | 2025-01-01 | 70/2 | DA+3 | DRY | 2025-01-20 | 2025-01-21 | Bhati Const. | Sk Sil | 1
326 | 2025-01-01 | 44/6 | DB1+3 | Sandy | 2025-01-19 | 2025-01-21 | Tantray Construction | R T Singh | 2
327 | 2025-01-01 | 55/2 | DA+0 | WFR | 2025-01-18 | 2025-01-22 | Meer Const | R T Singh | 4
328 | 2025-01-01 | 47/4 | DA+3 | Sandy | 2025-01-19 | 2025-01-23 | Tantray Construction | R T Singh | 4
329 | 2025-01-01 | 50/5 | DA+9 | Sandy | 2025-01-16 | 2025-01-23 | Om Const | R T Singh | 7
330 | 2025-01-01 | 1A/4 | DA+3 | DFR | 2025-01-20 | 2025-01-25 | Naganaray Enterprise | Sumit | 5
331 | 2025-01-01 | 28/6 | DA+6 | Sandy | 2025-01-19 | 2025-01-25 | Vishwakarma Construction | Bipin Kumar | 6
332 | 2025-01-01 | 70/0 | DC1+0 | DRY | 2025-01-20 | 2025-01-25 | Meer Const |  | 5
333 | 2025-01-01 | 44/7 | DA+9 | Sandy | 2025-01-23 | 2025-01-25 | Iqbal | R T Singh | 2
334 | 2025-01-01 | 34/2 | DA+6 | Sandy | 2025-01-20 | 2025-01-27 | Ymk Construction | Kuntal Debnath | 7
335 | 2025-01-01 | 65/10 | DA+0 | DRY | 2025-01-24 | 2025-01-27 | Bhati Const. | Sk Sil | 3
336 | 2025-01-01 | 57/1 | DA+0 | Sandy | 2025-01-24 | 2025-01-27 | Meer Const | R T Singh | 3
337 | 2025-01-01 | 28/5 | DA+9 | Sandy | 2025-01-22 | 2025-01-28 | Vishwakarma Construction | Bipin Kumar | 6
338 | 2025-01-01 | 35/0 | DB2+6 | Sandy | 2025-01-18 | 2025-01-28 | Parsuram Sahi | Kuntal Debnath | 10
339 | 2025-01-01 | 44/3 | DA+0 | Sandy | 2025-01-24 | 2025-01-28 | Tantray Construction | R T Singh | 4
340 | 2025-01-01 | 1A/3 | DA+0 | DRY | 2025-01-21 | 2025-01-29 | Jsr Infrastructure | Sumit | 8
341 | 2025-01-01 | 55/8 | DA+6 | Sandy | 2025-01-28 | 2025-01-30 | Meer Const | R T Singh | 2
342 | 2025-01-01 | 1A/2 | DA+0 | DRY | 2025-01-26 | 2025-01-31 | Jsr Infrastructure | Sumit | 5
343 | 2025-01-01 | 44/8 | DCT+0 | Sandy | 2025-01-27 | 2025-01-31 | Iqbal | R T Singh | 4
344 | 2025-02-01 | 34/0 | DB2+0 | DRY | 2025-01-25 | 2025-02-01 | Ymk Construction | Kuntal Debnath | 7
345 | 2025-02-01 | 28/8 | DA+3 | Sandy | 2025-01-25 | 2025-02-01 | Vishwakarma Construction | Kuntal Debnath | 7
346 | 2025-02-01 | 47/1 | DA+3 | Sandy | 2025-01-25 | 2025-02-01 | Tantray Construction | R T Singh | 7
347 | 2025-02-01 | 1A/5 | DA+0 | DRY | 2025-01-27 | 2025-02-02 | Jsr Infrastructure | Sumit | 6
348 | 2025-02-01 | 28/7 | DA+3 | Sandy | 2025-01-28 | 2025-02-04 | Vishwakarma Construction | Kuntal Debnath | 7
349 | 2025-02-01 | 33/1 | DA+0 | DRY | 2025-02-01 | 2025-02-07 | Ymk Construction | Kuntal Debnath | 6
350 | 2025-02-01 | 28/4 | DA+0 | Sandy | 2025-02-02 | 2025-02-07 | Vishwakarma Construction | Kuntal Debnath | 5
351 | 2025-02-01 | 1A/6 | DA+0 | Sandy | 2025-01-31 | 2025-02-07 | Jsr Infrastructure | Sumit | 7
352 | 2025-02-01 | 35/3 | DB1+6 | Sandy | 2025-02-01 | 2025-02-09 | Parsuram Sahi | Kuntal Debnath | 8
353 | 2025-02-01 | 45/1 | DA+9 | Sandy | 2025-02-01 | 2025-02-09 | Tantray Construction | R T Singh | 8
354 | 2025-02-01 | 54/5 | DA+9 | Sandy | 2025-02-06 | 2025-02-10 | Meer Const | R T Singh | 4
355 | 2025-02-01 | 32/3 | DA+0 | Sandy | 2025-02-05 | 2025-02-11 | Ymk Construction | Kuntal Debnath | 6
356 | 2025-02-01 | 28/3 | DA+0 | DFR | 2025-02-04 | 2025-02-11 | Vishwakarma Construction | Kuntal Debnath | 7
357 | 2025-02-01 | 32/4 | DA+0 | Sandy | 2025-02-09 | 2025-02-13 | Ymk Construction | Kuntal Debnath | 4
358 | 2025-02-01 | 28/2 | DA+0 | DFR | 2025-02-09 | 2025-02-13 | Vishwakarma Construction | Kuntal Debnath | 4
359 | 2025-02-01 | 32/2 | DA+3 | DRY | 2025-02-09 | 2025-02-13 | Ymk Construction | Kuntal Debnath | 4
360 | 2025-02-01 | 29/0 | DB1+0 | DRY | 2025-02-12 | 2025-02-16 | Vishwakarma Construction | Kuntal Debnath | 4
361 | 2025-02-01 | 55/0 | DB1+6 | Sandy | 2025-02-11 | 2025-02-16 | Meer Const | R T Singh | 5
362 | 2025-02-01 | 44/0 | DB1+3 | Sandy | 2025-02-10 | 2025-02-16 | Om Const | R T Singh | 6
363 | 2025-02-01 | 30/0 | DC1+0 | DRY | 2025-02-15 | 2025-02-20 | Vishwakarma Construction | Kuntal Debnath | 5
364 | 2025-02-01 | 33/0 | DC1+0 | DRY | 2025-02-14 | 2025-02-20 | Ymk Construction | Kuntal Debnath | 6
365 | 2025-02-01 | 1A/0 | DD60+0 | DRY | 2025-02-06 | 2025-02-20 | Jsr Infrastructure | Sumit | 14
366 | 2025-02-01 | 30/1 | DA+0 | Sandy | 2025-02-17 | 2025-02-22 | Vishwakarma Construction | Kuntal Debnath | 5
367 | 2025-02-01 | 43/10 | DA+3 | Sandy | 2025-02-18 | 2025-02-23 | Om Const | R T Singh | 5
368 | 2025-02-01 | 29/4 | DA+6 | DRY | 2025-02-22 | 2025-02-25 | Vishwakarma Construction | Kuntal Debnath | 3
369 | 2025-02-01 | 29/1 | DA+3 | DRY | 2025-02-24 | 2025-02-28 | Vishwakarma Construction | Kuntal Debnath | 4
370 | 2025-02-01 | 55/1 | DA+0 | WFR | 2025-02-21 | 2025-02-28 | Bhati | R T Singh | 7
371 | 2025-03-01 | 35/5 | DA+0 | Sandy | 2025-02-10 | 2025-03-02 | Parsuram Sahi | Kuntal Debnath | 20
372 | 2025-03-01 | 32/1 | DA+3 | Sandy | 2025-02-28 | 2025-03-02 | Ymk | Kuntal Debnath | 2
373 | 2025-03-01 | 30/3 | DA+3 | Sandy | 2025-02-28 | 2025-03-03 | Vishwakarma Construction | Kuntal Debnath | 3
374 | 2025-03-01 | 30/2 | DA+0 | Sandy | 2025-03-01 | 2025-03-06 | Vishwakarma Construction | Kuntal Debnath | 5
375 | 2025-03-01 | 1/0 | DD60+0 | DRY | 2025-02-25 | 2025-03-07 | Jsr Infrastructure | Sumit | 10
376 | 2025-03-01 | 32/0 | DC1+0 | DRY | 2025-03-01 | 2025-03-07 | Ymk | Kuntal Debnath | 6
377 | 2025-03-01 | 29/2 | DA+3 | DRY | 2025-03-03 | 2025-03-08 | Vishwakarma Construction | Kuntal Debnath | 5
378 | 2025-03-01 | 1A/7 | DA+3 | Sandy | 2025-03-01 | 2025-03-08 | Jsr Infrastructure | Sumit | 7
379 | 2025-03-01 | 29/3 | DA+0 | Sandy | 2025-03-05 | 2025-03-10 | Vishwakarma Construction | Kuntal Debnath | 5
380 | 2025-03-01 | 31/2 | DA+0 | DRY | 2025-03-05 | 2025-03-10 | Ymk | Kuntal Debnath | 5
381 | 2025-03-01 | 31/1 | DA+0 | DRY | 2025-03-08 | 2025-03-12 | Ymk | Kuntal Debnath | 4
382 | 2025-03-01 | 2/1 | DA+3 | Sandy | 2025-03-14 | 2025-03-20 | Jsr Infrastructure | Sumit | 6
383 | 2025-03-01 | 34/3 | DA+0 | Sandy | 2025-03-19 | 2025-03-25 | Ymk | Kuntal Debnath | 6
384 | 2025-03-01 | 26/7 | DA+0 | DFR | 2025-03-20 | 2025-03-26 | Jsr Infrastructure | Bipin Kumar | 6
385 | 2025-03-01 | 37/3 | DA+0 | Sandy | 2025-03-22 | 2025-03-30 | Vishwakarma Construction | Kuntal Debnath | 8
386 | 2025-03-01 | 34/4 | DA+0 | Sandy | 2025-03-21 | 2025-03-31 | Ymk | Kuntal Debnath | 10
387 | 2025-03-01 | 57/0 | DD60+25 | Sandy | 2025-03-22 | 2025-03-31 | Bhati | R T Singh | 9
388 | 2025-04-01 | 35/1 | DA+9 | Sandy | 2025-03-31 | 2025-04-06 | Ymk | Kuntal Debnath | 6
389 | 2025-04-01 | 46/0 | DD60+25 | Sandy | 2025-03-25 | 2025-04-09 | Om Const | R T Singh | 15
390 | 2025-04-01 | 38/4 | DA+9 | Sandy | 2025-04-07 | 2025-04-11 | Vishwakarma Construction | Kuntal Debnath | 4
391 | 2025-04-01 | 56/0 | DD60+25 | Sandy | 2025-04-02 | 2025-04-12 | Bhati | R T Singh | 10
392 | 2025-04-01 | 39/0 | DB2+6 | Sandy | 2025-04-12 | 2025-04-15 | Vishwakarma Construction | Kuntal Debnath | 3
393 | 2025-04-01 | 27/3 | DA+3 | DFR | 2025-04-12 | 2025-04-17 | YMK | Kuntal Debnath | 5
394 | 2025-04-01 | 47/0 | DD60+25 | Sandy | 2025-04-05 | 2025-04-17 | Om Const | R T Singh | 12
395 | 2025-04-01 | 4/0 | DD60+6 | DRY | 2025-04-13 | 2025-04-19 | Jsr Infrastructure | Sumit | 6
396 | 2025-04-01 | 38/2 | DA+6 | Sandy | 2025-04-18 | 2025-04-22 | Vishwakarma Construction | Kuntal Debnath | 4
397 | 2025-04-01 | 27/2 | DA+3 | DFR | 2025-04-17 | 2025-04-23 | YMK | Kuntal Debnath | 6
398 | 2025-04-01 | 38/1 | DA+0 | Sandy | 2025-04-21 | 2025-04-23 | Vishwakarma Construction | Kuntal Debnath | 2
399 | 2025-04-01 | 38/0 | DB2+6 | Sandy | 2025-04-24 | 2025-04-26 | Vishwakarma Construction | Kuntal Debnath | 2
400 | 2025-04-01 | 39/1 | DA+0 | Sandy | 2025-04-27 | 2025-04-29 | Vishwakarma Construction | Kuntal Debnath | 2
401 | 2025-05-01 | 40/0 | DC2+0 | Sandy | 2025-04-30 | 2025-05-05 | Vishwakarma Construction | Kuntal Debnath | 5
402 | 2025-05-01 | 40/1 | DA+6 | Sandy | 2025-05-02 | 2025-05-10 | Vishwakarma Construction | Kuntal Debnath | 8
403 | 2025-05-01 | 27/6 | DA+0 | Sandy | 2025-05-07 | 2025-05-12 | YMK | Kuntal Debnath | 5
404 | 2025-05-01 | 1A/8 | DA+0 | Sandy | 2025-04-29 | 2025-05-16 | Jsr Infrastructure | Sumit | 17
405 | 2025-05-01 | 27/4 | DA+3 | DFR | 2025-05-12 | 2025-05-18 | YMK | Kuntal Debnath | 6
406 | 2025-05-01 | 38/3 | DA+9 | Sandy | 2025-05-12 | 2025-05-19 | Vishwakarma Construction | Kuntal Debnath | 7
407 | 2025-05-01 | 42/4 | DA+0 | Sandy | 2025-05-16 | 2025-05-20 | Vishwakarma Construction | Kuntal Debnath | 4
408 | 2025-05-01 | 40/3 | DA+3 | Sandy | 2025-05-18 | 2025-05-24 | Vishwakarma Construction | Kuntal Debnath | 6
409 | 2025-05-01 | 21/9 | DA+3 | DFR | 2025-05-13 | 2025-05-26 | M.R. Choudhary | Vivek Shukla | 13
410 | 2025-05-01 | 27/7 | DB1+0 | DFR | 2025-05-18 | 2025-05-27 | YMK | Kuntal Debnath | 9
411 | 2025-05-01 | 4/3 | DA+0 | DRY | 2025-05-13 | 2025-05-28 | Nyce Service & Security | Sumit | 15
412 | 2025-05-01 | 2/8 | DA+0 | Sandy | 2025-05-26 | 2025-05-30 | Jsr Infrastructure | Sumit | 4
413 | 2025-05-01 | 8/11 | DA+0 | DRY | 2025-05-12 | 2025-05-30 | Bhati Construction | Sumit | 18
414 | 2025-06-01 | 41/1 | DB1+9 | Sandy | 2025-05-21 | 2025-06-02 | Vishwakarma Construction | Kuntal Debnath | 12
415 | 2025-06-01 | 30/4 | DA+3 | DRY | 2025-05-21 | 2025-06-03 | Rabbit bright technology pvt. Ltd. | Kuntal Debnath | 13
416 | 2025-06-01 | 21/7 | DA+3 | DFR | 2025-05-07 | 2025-06-06 | M.R. Choudhary | Vivek Shukla | 30
417 | 2025-06-01 | 19/5 | DA+0 | DRY | 2025-06-01 | 2025-06-06 | Shree Ram Construction | Vivek Shukla | 5
418 | 2025-06-01 | 41/0 | DC1+6 | Sandy | 2025-06-01 | 2025-06-08 | Vishwakarma Construction | Kuntal Debnath | 7
419 | 2025-06-01 | 27/1 | DA+3 | DFR | 2025-05-02 | 2025-06-11 | YMK | Kuntal Debnath | 40
420 | 2025-06-01 | 30/5 | DA+3 | DRY | 2025-05-30 | 2025-06-12 | Rabbit bright technology pvt. Ltd. | Kuntal Debnath | 13
421 | 2025-06-01 | 2/7 | DA+3 | Sandy | 2025-05-30 | 2025-06-13 | Jsr Infrastructure | Sumit | 14
422 | 2025-06-01 | 11/4 | DA+0 | Sandy | 2025-06-08 | 2025-06-13 | BR & Sons | Sumit | 5
423 | 2025-06-01 | 36/2 | DA+0 | Sandy | 2025-06-10 | 2025-06-13 | Vishwakarma Construction | Kuntal Debnath | 3
424 | 2025-06-01 | 36/3 | DA+0 | Sandy | 2025-06-10 | 2025-06-15 | Vishwakarma Construction | Kuntal Debnath | 5
425 | 2025-06-01 | 10/0 | DD60+25 | DFR | 2025-05-14 | 2025-06-18 | Bhati Construction | Sumit | 35
426 | 2025-06-01 | 4/1 | DA+0 | DRY | 2025-04-26 | 2025-06-19 | Jsr Infrastructure | Sumit | 54
427 | 2025-06-01 | 21/5 | DA+6 | DFR | 2025-05-29 | 2025-06-21 | M.R. Choudhary | Vivek Shukla | 23
428 | 2025-06-01 | 36/4 | DA+6 | Sandy | 2025-06-13 | 2025-06-23 | Vishwakarma Construction | Kuntal Debnath | 10
429 | 2025-06-01 | 30/6 | DA+0 | DRY | 2025-06-20 | 2025-06-25 | YMK | Kuntal Debnath | 5
430 | 2025-06-01 | 2/9 | DA+0 | DRY | 2025-06-08 | 2025-06-25 | Jsr Infrastructure | Sumit | 17
431 | 2025-06-01 | 37/0 | DB2+0 | Sandy | 2025-06-23 | 2025-06-28 | Vishwakarma Construction | Kuntal Debnath | 5
432 | 2025-06-01 | 21/4 | DA+3 | Sandy | 2025-06-11 | 2025-06-30 | M.R. Choudhary | Vivek Shukla | 19
433 | 2025-07-01 | 31/0 | DB2+0 | Sandy | 2025-06-24 | 2025-07-01 | YMK | Kuntal Debnath | 7
434 | 2025-07-01 | 4/2 | DA+0 | DRY | 2025-06-23 | 2025-07-01 | Nyce Services | Sumit | 8
435 | 2025-07-01 | 3/0 | DD60+6 | DRY | 2025-05-02 | 2025-07-02 | Jsr Infrastructure | Sumit | 61
436 | 2025-07-01 | 4/4 | DA+0 | DRY | 2025-06-27 | 2025-07-02 | Nice Security & Services | Sumit | 5
437 | 2025-07-01 | 21/3 | DA+6 | Sandy | 2025-06-21 | 2025-07-05 | M.R. Choudhary | Vivek Shukla | 14
438 | 2025-07-01 | 8/12 | DA+0 | DRY | 2025-05-12 | 2025-07-06 | Jsr Infrastructure | Sumit | 55
439 | 2025-07-01 | 8/2 | DA+3 | DRY | 2025-06-17 | 2025-07-08 | Dhakad Enterprises | Sumit | 21
440 | 2025-07-01 | 37/1 | DA+9 | Sandy | 2025-06-28 | 2025-07-09 | Vishwakarma Construction | Kuntal Debnath | 11
441 | 2025-07-01 | 8/1 | DA+3 | DRY | 2025-07-08 | 2025-07-12 | Dhakad Enterprises | Sumit | 4
442 | 2025-07-01 | 20/0 | DB2+0 | Sandy | 2025-07-05 | 2025-07-12 | Vishwakarma Construction | Vivek Shukla | 7
443 | 2025-07-01 | 27/0 | DC1+0 | DFR | 2025-07-05 | 2025-07-13 | YMK | Kuntal Debnath | 8
444 | 2025-07-01 | 37/2 | DA+3 | Sandy | 2025-07-07 | 2025-07-13 | Vishwakarma Construction | Vivek Shukla | 6
445 | 2025-07-01 | 9/0 | DD60+18 | DRY | 2025-07-08 | 2025-07-16 | Jsr Infrastructure | Sumit | 8
446 | 2025-07-01 | 8/5 | DA+3 | DRY | 2025-06-20 | 2025-07-22 | Yash Infra | Sumit | 32
447 | 2025-07-01 | 20/2 | DA+0 | DRY | 2025-07-20 | 2025-07-23 | Vishwakarma Construction | Vivek Shukla | 3
448 | 2025-07-01 | 21/0 | DB2+0 | DRY | 2025-07-21 | 2025-07-26 | Vishwakarma Construction | Vivek Shukla | 5
449 | 2025-07-01 | 26/0 | DB1+0 | DFR | 2025-07-11 | 2025-07-26 | YMK | Shymal Sil | 15
450 | 2025-07-01 | 20/3 | DA+0 | DRY | 2025-07-24 | 2025-07-27 | Vishwakarma Construction | Vivek Shukla | 3
451 | 2025-07-01 | 21/2 | DA+0 | Sandy | 2025-06-22 | 2025-07-29 | Vishwakarma Construction | Vivek Shukla | 37
452 | 2025-07-01 | 8/0 | DB1+0 | DRY | 2025-07-10 | 2025-07-30 | Dhakad Enterprises | Sumit | 20
453 | 2025-07-01 | 8/4 | DA+3 | DRY | 2025-07-23 | 2025-07-31 | Jsr Infrastructure | Sumit | 8
454 | 2025-07-01 | 24/0 | DD45+3 | DRY | 2025-07-20 | 2025-07-31 | YMK | Shymal Sil | 11
455 | 2025-08-01 | 14A/0 | DC1+0 | DRY | 2025-06-17 | 2025-08-02 | BR & Sons | Vivek Shukla | 46
456 | 2025-08-01 | 23/0 | DD45+3 | DRY | 2025-07-31 | 2025-08-06 | YMK | Shymal Sil | 6
457 | 2025-08-01 | 10/1 | DA+0 | DRY | 2025-07-16 | 2025-08-09 | Jsr Infrastructure | Sumit | 24
458 | 2025-08-01 | 11/1 | DA+0 | Sandy | 2025-08-02 | 2025-08-10 | Om Construction_Chandrapal | Sumit | 8
459 | 2025-08-01 | 26/1 | DA+0 | DRY | 2025-08-06 | 2025-08-13 | YMK | Shymal Sil | 7
460 | 2025-08-01 | 11/2 | DA+0 | Sandy | 2025-08-16 | 2025-08-20 | Om Construction_Chandrapal | Sumit | 4
461 | 2025-08-01 | 28/1 | DA+0 | DRY | 2025-06-12 | 2025-08-27 | YMK | Shymal Sil | 76
462 | 2025-08-01 | 10/7 | DA+3 | DRY | 2025-07-14 | 2025-08-28 | Jsr Infrastructure | Sumit | 45
463 | 2025-09-01 | 20/1 | DA+0 | Sandy | 2025-08-21 | 2025-09-05 | Vishwakarma Construction | Vivek Shukla | 15
464 | 2025-09-01 | 6/0 | DB2+9 | DRY | 2025-08-28 | 2025-09-08 | Dhakad Enterprises | Sumit | 11
465 | 2025-09-01 | 5/0 | DB1+9 | DRY | 2025-08-18 | 2025-09-12 | Dhakad Enterprises | Sumit | 25
466 | 2025-09-01 | 10/16 | DA+3 | DRY | 2025-09-06 | 2025-09-13 | Jsr Infrastructure | Sumit | 7
467 | 2025-09-01 | 11/0 | DB1+0 | Sandy | 2025-09-06 | 2025-09-15 | Om Construction_Chandrapal | Sumit | 9
468 | 2025-09-01 | 22/10 | DA+6 | Sandy | 2025-07-21 | 2025-09-14 | Vishwakarma Construction | Vivek Shukla | 55
469 | 2025-09-01 | 10/15 | DA+3 | DRY | 2025-09-15 | 2025-09-16 | Jsr Infrastructure | Sumit | 1
470 | 2025-09-01 | 11/3 | DA+0 | Sandy | 2025-09-15 | 2025-09-22 | Om Construction_Chandrapal | Sumit | 7
471 | 2025-09-01 | 7/0 | DB1+0 | DRY | 2025-09-19 | 2025-09-30 | Dhakad Enterprises | Sumit | 11
472 | 2025-10-01 | 10/10 | DA+3 | Sandy | 2025-10-02 | 2025-10-04 | Jsr Infrastructure | Sumit | 2
473 | 2025-10-01 | 10/23 | DA+0 | Sandy | 2025-09-29 | 2025-10-06 | Om Construction_Chandrapal | Sumit | 7
474 | 2025-10-01 | 21/8 | DA+6 | DRY | 2025-10-03 | 2025-10-11 | Vishwakarma Construction | Vivek Shukla | 8
475 | 2025-10-01 | 10/22 | DA+0 | Sandy | 2025-10-06 | 2025-10-12 | Om Construction_Chandrapal | Sumit | 6
476 | 2025-10-01 | 8/3 | DA+0 | DRY | 2025-10-10 | 2025-10-14 | Jsr Infrastructure | Sumit | 4
477 | 2025-10-01 | 19/4 | DA+0 | DRY | 2025-10-13 | 2025-10-14 | Vishwakarma Construction | Vivek Shukla | 1
478 | 2025-10-01 | 21/6 | DA+3 | DRY | 2025-10-11 | 2025-10-28 | Vishwakarma Construction | Vivek Shukla | 17
479 | 2025-11-01 | 26/8 | DA+6 | DFR | 2025-10-28 | 2025-11-04 | Vishwakarma Construction | Vivek Shukla | 7
480 | 2025-11-01 | 22/0 | DB2+3 | DRY | 2025-10-10 | 2025-11-09 | Vishwakarma Construction | Vivek Shukla | 30
481 | 2025-11-01 | 13/4 | DA+3 | DRY | 2025-06-11 | 2025-11-14 | Vishwakarma Construction | Vivek Shukla | 156
482 | 2026-02-01 | 10/2 | DA+0 | DFR | 2026-02-02 | 2026-02-10 | Jsr Infrastructure | Swarankar | 8
483 | 2026-02-01 | 8/8 | DA+6 | DRY | 2026-02-09 | 2026-02-13 | Jsr Infrastructure | Swarankar | 4
484 | 2026-02-01 | 8/6 | DA+3 | DRY | 2026-02-16 | 2026-02-20 | Jsr Infrastructure | Swarankar | 4
| Sr. No. | Loc no | TOT | FDN Status | Classification | Start Date | Gang Name | Section Incharge | Foundation Status | Casting time
| 1 | 21/1 | DA+6 | ROW |  | 2025-10-31 | Vishwakarma Const. | Vivek Shukla | 3 leg Completed. 1 leg is in ROW. Gang idle. |  | 25 Manpower

## Earthing (hidden)
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
List of Completed Earthing
Earthing
SL No. | FDN No. | Location No. | Tower Type | Classification | Type of Earthing | End Date | Gang Name | Earthing Completion Month
1 | 2023-10-01 | 36/1 | DA+3 | Sandy | Pipe | 2023-12-30 | Nagana Ray and company | 2023-12-01
2 | 2023-12-01 | 61/3 | DA+6 | DRY | Pipe | 2023-12-18 | Manoj Sharma | 2023-12-01
3 | 2023-12-01 | 27/12 | DA+3 | Sandy | Pipe | 2024-02-26 | Nagana Ray And Company | 2024-02-01
4 | 2023-12-01 | 62/6 | DA+3 | DRY | Pipe | 2024-01-07 | Shakti Construction | 2024-01-01
5 | 2023-12-01 | 59/14 | DA+6 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01 |  | 3.2 | 2nd Section WIP.
6 | 2023-12-01 | 62/7 | DA+3 | DRY | Pipe | 2024-01-09 | Shakti Construction | 2024-01-01
7 | 2023-12-01 | 59/13 | DA+3 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01 | T&P Shifting WIP
8 | 2023-12-01 | 27/10 | DA+3 | DFR | CP | 2023-12-30 | Nagana Ray And Company | 2023-12-01 |  | 2.5
9 | 2023-12-01 | 63/8 | DA+3 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
10 | 2023-12-01 | 59/10 | DA+0 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
11 | 2023-12-01 | 62/5 | DA+0 | DRY | Pipe | 2024-01-07 | Shakti Construction | 2024-01-01
12 | 2023-12-01 | 59/9 | DA+3 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
13 | 2023-12-01 | 60/9 | DA+3 | DRY | Pipe | 2024-01-06 | Imran | 2024-01-01
14 | 2023-12-01 | 62/4 | DA+3 | DRY | Pipe | 2023-12-31 | Shakti Construction | 2023-12-01
15 | 2023-12-01 | 59/8 | DB1+3 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
16 | 2023-12-01 | 26/2 | DA+3 | DFR | CP | 2025-06-23 | A.B. Construction | 2025-06-01
17 | 2023-12-01 | 59/6 | DA+3 | DFR | CP | 2024-01-05 | Om Const | 2024-01-01
18 | 2023-12-01 | 63/6 | DA+3 | DRY | Pipe | 2024-01-12 | Mahadev Eng | 2024-01-01
19 | 2023-12-01 | 60/8 | DA+0 | DRY | Pipe | 2024-01-06 | Imran | 2024-01-01
20 | 2023-12-01 | 27/9 | DA+0 | DFR | CP | 2023-12-30 | Nagana Ray And Company | 2023-12-01
21 | 2023-12-01 | 59/7 | DA+3 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
22 | 2023-12-01 | 59/5 | DA+3 | DFR | CP | 2024-01-05 | Om Const | 2024-01-01
23 | 2023-12-01 | 62/3 | DA+0 | DRY | Pipe | 2024-01-07 | Shakti Construction | 2024-01-01
24 | 2024-01-01 | 59/12 | DA+6 | DFR | CP | 2024-01-16 | Manoj Sharma | 2024-01-01
25 | 2024-01-01 | 60/7 | DA+3 | DRY | Pipe | 2024-01-06 | Imran | 2024-01-01
26 | 2024-01-01 | 62/2 | DA+3 | DRY | Pipe | 2024-01-07 | Shakti Construction | 2024-01-01
27 | 2024-01-01 | 59/3 | DA+3 | DFR | CP | 2024-02-22 | Om Const | 2024-02-01
28 | 2024-01-01 | 64/0 | DB2+0 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
29 | 2024-01-01 | 57/3 | DA+0 | DRY | Pipe | 2024-02-22 | Om Const | 2024-02-01
30 | 2024-01-01 | 60/5 | DA+3 | DRY | Pipe | 2024-01-16 | Manoj Sharma | 2024-01-01
31 | 2024-01-01 | 62/11 | DA+3 | DRY | Pipe | 2024-01-28 | Shakti Construction | 2024-01-01
32 | 2024-01-01 | 65/2 | DA+0 | DRY | Pipe | 2024-01-12 | Veerteja Enterprises | 2024-01-01
33 | 2024-01-01 | 65/11 | DA+0 | DRY | Pipe | 2024-01-15 | Bhati Const. | 2024-01-01
34 | 2024-01-01 | 60/6 | DA+0 | DRY | Pipe | 2024-01-16 | Manoj Sharma | 2024-01-01
35 | 2024-01-01 | 57/2 | DA+3 | DRY | Pipe | 2024-02-14 | Om Const | 2024-02-01
36 | 2024-01-01 | 62/10 | DA+0 | DFR | CP | 2024-02-22 | Shakti Construction | 2024-02-01
37 | 2024-01-01 | 65/9 | DA+0 | DRY | Pipe | 2024-01-15 | Bhati Const. | 2024-01-01
38 | 2024-01-01 | 57/4 | DA+0 | Sandy | Pipe | 2024-02-14 | Om Const | 2024-02-01
39 | 2024-01-01 | 64/4 | DA+3 | DRY | Pipe | 2024-01-19 | Mahadev Eng | 2024-01-01
40 | 2024-01-01 | 65/3 | DA+3 | DRY | Pipe | 2024-01-20 | Veerteja Enterprises | 2024-01-01
41 | 2024-01-01 | 55/3 | DA+0 | Sandy | Pipe | 2024-02-02 | Imran | 2024-02-01
42 | 2024-01-01 | 60/10 | DA+0 | DFR | CP | 2024-02-02 | Manoj Sharma | 2024-02-01
43 | 2024-01-01 | 62/8 | DA+0 | DFR | CP | 2024-02-21 | Shakti Construction | 2024-02-01
44 | 2024-01-01 | 55/4 | DA+0 | Sandy | Pipe | 2024-01-17 | Imran | 2024-01-01
45 | 2024-01-01 | 57/5 | DA+3 | Sandy | Pipe | 2024-02-14 | Om Const | 2024-02-01
46 | 2024-01-01 | 26/3 | DA+0 | DRY | Pipe | 2025-06-23 | A.B. Construction | 2025-06-01
47 | 2024-01-01 | 64/1 | DA+0 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
48 | 2024-01-01 | 64/5 | DA+3 | DRY | Pipe | 2024-01-25 | Mahadev Eng | 2024-01-01
49 | 2024-01-01 | 65/6 | DA+0 | DRY | Pipe | 2024-02-09 | Bhati Const. | 2024-02-01
50 | 2024-01-01 | 61/0 | DB2+0 | DRY | Pipe | 2024-02-02 | Manoj Sharma | 2024-02-01
51 | 2024-01-01 | 62/9 | DA+3 | DFR | CP | 2024-02-21 | Shakti Construction | 2024-02-01
52 | 2024-01-01 | 65/5 | DA+0 | DRY | Pipe | 2024-02-09 | Bhati Const. | 2024-02-01
53 | 2024-01-01 | 64/2 | DA+3 | DRY | Pipe | 2024-01-25 | Mahadev Eng | 2024-01-01
54 | 2024-01-01 | 57/6 | DA+3 | Sandy | Pipe | 2024-02-22 | Om Const | 2024-02-01
55 | 2024-01-01 | 63/1 | DA+3 | DFR | CP | 2024-01-27 | Shakti Construction | 2024-01-01
56 | 2024-01-01 | 64/9 | DA+3 | DRY | Pipe | 2024-02-20 | Veerteja Enterprises | 2024-02-01
57 | 2024-01-01 | 60/11 | DA+3 | DRY | Pipe | 2024-02-02 | Manoj Sharma | 2024-02-01
58 | 2024-01-01 | 65/4 | DA+0 | DRY | Pipe | 2024-01-25 | Bhati Const. | 2024-01-01
59 | 2024-01-01 | 63/7 | DA+3 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
60 | 2024-01-01 | 55/5 | DA+0 | Sandy | Pipe | 2024-01-29 | Imran | 2024-01-01
61 | 2024-01-01 | 55/6 | DA+0 | Sandy | Pipe | 2024-01-29 | Imran | 2024-01-01
62 | 2024-01-01 | 63/2 | DA+0 | DFR | CP | 2024-01-27 | Shakti Construction | 2024-01-01
63 | 2024-01-01 | 27/8 | DA+0 | DFR | CP | 2024-01-31 | Nagana Ray And Company | 2024-01-01
64 | 2024-01-01 | 61/1 | DA+6 | DFR | CP | 2024-02-02 | Manoj Sharma | 2024-02-01
65 | 2024-01-01 | 55/7 | DA+0 | Sandy | Pipe | 2024-02-02 | Imran | 2024-02-01
66 | 2024-01-01 | 64/3 | DA+0 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
67 | 2024-01-01 | 63/3 | DA+3 | DFR | Pipe | 2024-02-22 | Shakti Construction | 2024-02-01
68 | 2024-01-01 | 64/8 | DA+3 | DRY | Pipe | 2024-02-01 | Veerteja Enterprises | 2024-02-01
69 | 2024-01-01 | 61/2 | DA+6 | DFR | CP | 2024-02-02 | Manoj Sharma | 2024-02-01
70 | 2024-02-01 | 64/7 | DA+3 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
71 | 2024-02-01 | 52/5 | DA+9 | Sandy | Pipe | 2024-02-05 | Imran | 2024-02-01
72 | 2024-02-01 | 63/4 | DA+0 | DRY | Pipe | 2024-02-14 | Shakti Construction | 2024-02-01
73 | 2024-02-01 | 26/4 | DA+6 | Sandy | Pipe | 2024-02-17 | Mehai Construction | 2024-02-01
74 | 2024-02-01 | 67/2 | DA+0 | DRY | Pipe | 2024-02-09 | Bhati Const. | 2024-02-01
75 | 2024-02-01 | 52/6 | DA+6 | Sandy | Pipe | 2024-02-08 | Imran | 2024-02-01
76 | 2024-02-01 | 64/6 | DA+0 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
77 | 2024-02-01 | 63/5 | DA+3 | DFR | CP | 2024-02-15 | Shakti Construction | 2024-02-01
78 | 2024-02-01 | 59/15 | DA+6 | DRY | Pipe | 2024-02-26 | Om Const | 2024-02-01
79 | 2024-02-01 | 61/5 | DA+3 | DRY | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
80 | 2024-02-01 | 67/1 | DA+0 | DRY | Pipe | 2024-02-13 | Bhati Const. | 2024-02-01
81 | 2024-02-01 | 64/10 | DA+3 | DRY | Pipe | 2024-02-11 | Veerteja Enterprises | 2024-02-01
82 | 2024-02-01 | 61/6 | DA+3 | DRY | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
83 | 2024-02-01 | 52/7 | DA+3 | Sandy | Pipe | 2024-02-13 | Imran | 2024-02-01
84 | 2024-02-01 | 59/16 | DA+9 | Dry | Pipe | 2024-02-26 | Om Const | 2024-02-01
85 | 2024-02-01 | 63/0 | DC1+0 | DFR | CP | 2024-02-15 | Shakti Construction | 2024-02-01
86 | 2024-02-01 | 52/8 | DA+6 | Sandy | Pipe | 2024-02-22 | Imran | 2024-02-01
87 | 2024-02-01 | 61/7 | DA+9 | Dry | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
88 | 2024-02-01 | 26/5 | DA+6 | Sandy | Pipe | 2024-02-18 | Mehai Construction | 2024-02-01
89 | 2024-02-01 | 61/9 | DA+0 | Dry | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
90 | 2024-02-01 | 60/1 | DA+6 | DRY | Pipe | 2024-02-23 | Om Const | 2024-02-01
91 | 2024-02-01 | 28/0 | DB2+0 | DFR | CP | 2024-02-18 | A.B. Construction | 2024-02-01
92 | 2024-02-01 | 52/10 | DA+9 | Sandy | Pipe | 2024-02-17 | Imran | 2024-02-01
93 | 2024-02-01 | 27/11 | DA+3 | DRY | Pipe | 2024-02-19 | A.B. Construction | 2024-02-01
94 | 2024-02-01 | 49/2 | DA+3 | Sandy | Pipe | 2024-03-08 | Veerteja Enterprises | 2024-03-01
95 | 2024-02-01 | 52/9 | DA+3 | Sandy | Pipe | 2024-02-22 | Imran | 2024-02-01
96 | 2024-02-01 | 61/8 | DA+6 | DRY | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
97 | 2024-02-01 | 62/1 | DA+3 | Sandy | Pipe | 2024-02-22 | Shakti Construction | 2024-02-01
98 | 2024-02-01 | 53/5 | DA+3 | Sandy | Pipe | 2024-02-25 | Imran | 2024-02-01
99 | 2024-02-01 | 64/11 | DA+3 | DRY | Pipe | 2024-03-06 | Bhati Const. | 2024-03-01
100 | 2024-02-01 | 60/2 | DA+3 | DFR | CP | 2024-02-26 | Om Const | 2024-02-01
101 | 2024-02-01 | 21/10 | DA+6 | DRY | Pipe | 2024-03-03 | Swarup Enterprises | 2024-03-01
102 | 2024-02-01 | 60/3 | DA+3 | DFR | CP | 2024-03-01 | Manoj Sharma | 2024-03-01
103 | 2024-02-01 | 26/6 | DA+6 | Sandy | Pipe | 2024-03-05 | Mehai Construction | 2024-03-01
104 | 2024-02-01 | 65/0 | DB1+0 | DRY | Pipe | 2024-03-06 | Bhati Const. | 2024-03-01
105 | 2024-02-01 | 60/4 | DA+3 | DFR | CP | 2024-03-01 | Manoj Sharma | 2024-03-01
106 | 2024-03-01 | 22/1 | DA+9 | Sandy | Pipe | 2024-03-03 | Swarup Enterprises | 2024-03-01
107 | 2024-03-01 | 61/10 | DA+9 | DRY | Pipe | 2024-03-12 | Manoj Sharma | 2024-03-01
108 | 2024-03-01 | 65/1 | DA+0 | DRY | Pipe | 2024-03-07 | Bhati Const. | 2024-03-01
109 | 2024-03-01 | 22/6 | DA+0 | Sandy | Pipe | 2024-03-23 | A.B. Construction | 2024-03-01
110 | 2024-03-01 | 62/0 | DB2+0 | DRY | Pipe | 2024-03-12 | Manoj Sharma | 2024-03-01
111 | 2024-03-01 | 61/4 | DA+3 | DRY | Pipe | 2024-03-22 | Manoj Sharma | 2024-03-01
112 | 2024-03-01 | 49/3 | DA+3 | Sandy | Pipe | 2024-03-21 | Veerteja Enterprises | 2024-03-01
113 | 2024-03-01 | 27/5 | DA+0 | DRY | Pipe | 2024-03-18 | Majisa Construction | 2024-03-01
114 | 2024-03-01 | 49/6 | DA+0 | Sandy | Pipe | 2024-04-20 | Shakti Construction | 2024-04-01
115 | 2024-03-01 | 60/0 | DC1+0 | DRY | Pipe | 2024-03-19 | Manoj Sharma | 2024-03-01
116 | 2024-03-01 | 49/4 | DA+3 | Sandy | Pipe | 2024-04-22 | Veerteja Enterprises | 2024-04-01
117 | 2024-03-01 | 49/5 | DA+3 | Sandy | Pipe | 2024-03-21 | Shakti Construction | 2024-03-01
118 | 2024-03-01 | 47/10 | DA+6 | Sandy | Pipe | 2024-03-29 | Bhati Const. | 2024-03-01
119 | 2024-03-01 | 47/9 | DA+3 | Sandy | Pipe | 2024-03-29 | Bhati Const. | 2024-03-01
120 | 2024-03-01 | 47/8 | DA+0 | Sandy | Pipe | 2024-03-29 | Bhati Const. | 2024-03-01
121 | 2024-03-01 | 47/7 | DA+3 | Sandy | Pipe | 2024-04-02 | Bhati Const. | 2024-04-01
122 | 2024-04-01 | 50/9 | DA+0 | Sandy | Pipe | 2024-04-19 | Shakti Construction | 2024-04-01
123 | 2024-04-01 | 48/0 | DC2+0 | Sandy | Pipe | 2024-04-07 | Bhati Const. | 2024-04-01
124 | 2024-04-01 | 50/10 | DA+0 | Sandy | Pipe | 2024-04-19 | Shakti Construction | 2024-04-01
125 | 2024-04-01 | 51/1 | DA+0 | Sandy | Pipe | 2024-04-19 | Shakti Construction | 2024-04-01
126 | 2024-04-01 | 48/1 | DA+9 | Sandy | Pipe | 2024-04-16 | Veerteja Enterprises | 2024-04-01
127 | 2024-04-01 | 50/8 | DA+9 | Sandy | Pipe | 2024-04-20 | Shakti Construction | 2024-04-01
128 | 2024-04-01 | 49/1 | DA+0 | Sandy | Pipe | 2024-04-22 | Veerteja Enterprises | 2024-04-01
129 | 2024-05-01 | 49/0 | DD45+0 | Sandy | Pipe | 2024-05-03 | Veerteja Enterprises | 2024-05-01
130 | 2024-05-01 | 43/6 | DA+3 | Sandy | Pipe | 2024-05-09 | Bande Bharat Group | 2024-05-01
131 | 2024-05-01 | 8/7 | DB1+0 | DRY | Pipe | 2024-05-23 | Mateshwari Const. | 2024-05-01
132 | 2024-05-01 | 50/7 | DA+0 | Sandy | Pipe | 2024-05-31 | Veerteja Enterprises | 2024-05-01
133 | 2024-05-01 | 8/10 | DA+3 | DFR | CP | 2024-05-31 | Mateshwari Const. | 2024-05-01
134 | 2024-05-01 | 50/1 | DA+6 | Sandy | Pipe | 2024-05-31 | Veerteja Enterprises | 2024-05-01
135 | 2024-05-01 | 47/6 | DA+3 | Sandy | Pipe | 2024-06-08 | Bhati Const. | 2024-06-01
136 | 2024-05-01 | 52/3 | DA+9 | Sandy | Pipe | 2024-05-23 | Sb Mehar Const. | 2024-05-01
137 | 2024-05-01 | 47/2 | DA+9 | Sandy | Pipe | 2024-05-28 | Bhati Const. | 2024-05-01
138 | 2024-05-01 | 10/14 | DA+3 | DRY | Pipe | 2024-05-31 | Mateshwari Const. | 2024-05-01
139 | 2024-05-01 | 10/19 | DA+0 | DRY | Pipe | 2024-05-31 | Jai Bhawani Construction | 2024-05-01
140 | 2024-05-01 | 50/4 | DA+9 | Sandy | Pipe | 2024-02-03 | Veerteja Enterprises | 2024-02-01
141 | 2024-05-01 | 51/2 | DA+0 | Sandy | Pipe | 2024-05-31 | Sb Mehar Const. | 2024-05-01
142 | 2024-05-01 | 47/5 | DA+0 | Sandy | Pipe | 2024-06-08 | Bhati Const. | 2024-06-01
143 | 2024-05-01 | 50/2 | DA+9 | Sandy | Pipe | 2024-02-04 | Veerteja Enterprises | 2024-02-01
144 | 2024-06-01 | 10/11 | DA+3 | DRY | Pipe | 2024-06-18 | Mateshwari Const. | 2024-06-01
145 | 2024-06-01 | 10/18 | DA+3 | DFR | CP | 2024-06-30 | Jai Bhawani Construction | 2024-06-01
146 | 2024-06-01 | 10/13 | DA+3 | DRY | Pipe | 2024-06-19 | Mateshwari Const. | 2024-06-01
147 | 2024-06-01 | 47/3 | DA+9 | Sandy | Pipe | 2024-06-08 | Bhati Const. | 2024-06-01
148 | 2024-06-01 | 51/0 | DC2+0 | Sandy | Pipe | 2024-06-11 | Sb Mehar Const. | 2024-06-01
149 | 2024-06-01 | 10/17 | DA+3 | DFR | CP | 2024-06-18 | Jai Bhawani Construction | 2024-06-01
150 | 2024-06-01 | 53/7 | DA+3 | Sandy | Pipe | 2024-07-02 | Bhati Const. | 2024-07-01
151 | 2024-06-01 | 10/8 | DA+3 | DFR | CP | 2024-06-20 | Mateshwari Const. | 2024-06-01
152 | 2024-06-01 | 10/12 | DB1+0 | DRY | Pipe | 2024-07-10 | Mateshwari Const. | 2024-07-01
153 | 2024-07-01 | 15/1 | DA+3 | DRY | Pipe | 2024-07-13 | Om Enterprise | 2024-07-01
154 | 2024-07-01 | 10/20 | DA+3 | DFR | CP | 2024-07-13 | Jai Bhawani Construction | 2024-07-01
155 | 2024-07-01 | 11A/5 | DA+3 | DRY | Pipe | 2024-08-26 | Punia Construction | 2024-08-01
156 | 2024-07-01 | 10/21 | DA+3 | DFR | CP | 2024-08-26 | Jai Bhawani Construction | 2024-08-01
157 | 2024-07-01 | 18/1 | DA+0 | DRY | Pipe | 2024-07-18 | J.P. Infra | 2024-07-01
158 | 2024-07-01 | 15/0 | DC1+0 | DRY | Pipe | 2024-07-16 | Om Enterprise | 2024-07-01
159 | 2024-07-01 | 14A/1 | DA+3 | DRY | Pipe | 2024-07-22 | Majisa Construction | 2024-07-01
160 | 2024-07-01 | 50/0 | DB2+0 | Sandy | Pipe | 2024-08-03 | Veerteja Enterprises | 2024-08-01
161 | 2024-07-01 | 11A/6 | DA+6 | DRY | Pipe | 2024-08-26 | Punia Construction | 2024-08-01
162 | 2024-07-01 | 10/6 | DA+0 | DFR | CP | 2024-09-01 | Jai Bhawani Construction | 2024-09-01
163 | 2024-07-01 | 16/0 | DC1+0 | DRY | Pipe | 2024-07-22 | Majisa Construction | 2024-07-01
164 | 2024-07-01 | 58/0 | DC1+3 | DFR | CP | 2024-07-30 | Bhati Const. | 2024-07-01
165 | 2024-07-01 | 18/0 | DC2+0 | DRY | Pipe | 2024-07-31 | J.P. Infra | 2024-07-01
166 | 2024-07-01 | 11/5 | DA+0 | DFR | CP | 2024-08-26 | Mci | 2024-08-01
167 | 2024-08-01 | 10/3 | DA+0 | DFR | CP | 2024-08-07 | Jai Bhawani Construction | 2024-08-01
168 | 2024-08-01 | 11A/7 | DA+9 | Sandy | Pipe | 2024-09-08 | Punia Construction | 2024-09-01
169 | 2024-08-01 | 18/2 | DA+0 | DRY | Pipe | 2024-09-07 | Vibe Infra | 2024-09-01
170 | 2024-08-01 | 17/3 | DA+0 | DRY | Pipe | 2024-09-07 | J.P. Infra | 2024-09-01
171 | 2024-08-01 | 57/7 | DA+3 | DFR | CP | 2024-08-12 | Bhati Const. | 2024-08-01
172 | 2024-08-01 | 16/3 | DA+3 | DRY | Pipe | 2024-09-07 | Majisa Construction | 2024-09-01
173 | 2024-08-01 | 43/9 | DA+9 | Sandy | Pipe | 2024-08-27 | N.R. Enterprises | 2024-08-01
174 | 2024-08-01 | 17/5 | DA+3 | DRY | Pipe | 2024-09-07 | J.P. Infra | 2024-09-01
175 | 2024-08-01 | 11A/2 | DA+0 | DRY | Pipe | 2024-08-18 | R.K. Construction | 2024-08-01
176 | 2024-08-01 | 16/4 | DA+0 | DRY | Pipe | 2024-08-24 | Om Enterprise | 2024-08-01
177 | 2024-08-01 | 18/3 | DA+0 | DRY | Pipe | 2024-09-07 | Vibe Infra | 2024-09-01
178 | 2024-08-01 | 17/4 | DA+3 | DRY | Pipe | 2024-09-05 | J.P. Infra | 2024-09-01
179 | 2024-08-01 | 10/9 | DA+0 | DRY | Pipe | 2024-08-31 | A.B. Construction | 2024-08-01
180 | 2024-08-01 | 11A/8 | DA+6 | Sandy | Pipe | 2024-09-08 | Punia Construction | 2024-09-01
181 | 2024-08-01 | 11A/9 | DA+3 | DRY | Pipe | 2024-09-08 | Punia Construction | 2024-09-01
182 | 2024-08-01 | 43/8 | DA+9 | Sandy | Pipe | 2024-08-27 | N.R. Enterprises | 2024-08-01
183 | 2024-08-01 | 18/4 | DA+0 | DRY | Pipe | 2024-09-03 | Vibe Infra | 2024-09-01
184 | 2024-08-01 | 59/2 | DA+3 | DFR | CP | 2024-08-23 | Bhati Const. | 2024-08-01
185 | 2024-08-01 | 16/2 | DA+0 | DRY | Pipe | 2024-08-31 | Om Enterprise | 2024-08-01
186 | 2024-08-01 | 11A/0 | DB1+0 | DRY | Pipe | 2024-08-26 | Mci | 2024-08-01
187 | 2024-08-01 | 50/6 | DA+9 | Sandy | Pipe | 2024-09-29 | Kalpana Const. | 2024-09-01
188 | 2024-08-01 | 53/8 | DA+3 | Sandy | Pipe | 2024-09-03 | Bhati Const. | 2024-09-01
189 | 2024-08-01 | 17/1 | DA+3 | DRY | Pipe | 2024-08-30 | J.P. Infra | 2024-08-01
190 | 2024-08-01 | 43/7 | DA+3 | Sandy | Pipe | 2024-08-30 | N.R. Enterprises | 2024-08-01
191 | 2024-08-01 | 16/5 | DA+3 | DRY | Pipe | 2024-08-31 | Majisa Construction | 2024-08-01
192 | 2024-08-01 | 19/0 | DC2+0 | DRY | Pipe | 2024-08-31 | Vibe Infra | 2024-08-01
193 | 2024-09-01 | 11A/1 | DA+3 | DRY | Pipe | 2024-09-01 | Mci | 2024-09-01
194 | 2024-09-01 | 19/1 | DA+0 | DRY | Pipe | 2024-09-04 | Vibe Infra | 2024-09-01
195 | 2024-09-01 | 17/2 | DA+6 | DRY | Pipe | 2024-09-04 | J.P. Infra | 2024-09-01
196 | 2024-09-01 | 13/2 | DA+3 | DRY | Pipe | 2024-09-30 | Punia Construction | 2024-09-01
197 | 2024-09-01 | 43/5 | DA+3 | DRY | Pipe | 2024-09-06 | N.R. Enterprises | 2024-09-01
198 | 2024-09-01 | 53/6 | DA+6 | Sandy | Pipe | 2024-09-13 | Bhati Const. | 2024-09-01
199 | 2024-09-01 | 16/1 | DA+0 | DRY | Pipe | 2024-09-10 | Sidhi Vinayak | 2024-09-01
200 | 2024-09-01 | 11A/4 | DA+3 | DRY | Pipe | 2024-09-30 | Punia Construction | 2024-09-01
201 | 2024-09-01 | 54/1 | DA+3 | Sandy | Pipe | 2024-09-14 | Bhati Const. | 2024-09-01
202 | 2024-09-01 | 50/3 | DA+6 | Sandy | Pipe | 2024-09-29 | Kalpana Const. | 2024-09-01
203 | 2024-09-01 | 73/0 | DB2+0 | DRY | Pipe | 2024-09-15 | Shree Shyam Const. | 2024-09-01
204 | 2024-09-01 | 73/9 | DA+0 | DRY | Pipe | 2024-09-19 | Shakti Construction | 2024-09-01
205 | 2024-09-01 | 73/2 | DA+0 | DRY | Pipe | 2024-09-16 | Shree Shyam Const. | 2024-09-01
206 | 2024-09-01 | 25/0 | DC1+6 | DRY | Pipe | 2024-09-26 | J.P. Infra | 2024-09-01
207 | 2024-09-01 | 54/2 | DA+3 | Sandy | Pipe | 2024-09-14 | Bhati Const. | 2024-09-01
208 | 2024-09-01 | 14A/2 | DA+0 | DRY | Pipe | 2024-09-30 | Sidhi Vinayak | 2024-09-01
209 | 2024-09-01 | 10/4 | DA+3 | DFR | CP | 2024-09-30 | A.B. Construction | 2024-09-01
210 | 2024-09-01 | 73/1 | DA+0 | DRY | Pipe | 2024-09-19 | Shree Shyam Const. | 2024-09-01
211 | 2024-09-01 | 14/0 | DC2+0 | Sandy | Pipe | 2024-09-26 | Om Enterprise | 2024-09-01
212 | 2024-09-01 | 11A/3 | DA+3 | DRY | Pipe | 2024-09-23 | R.K. Construction | 2024-09-01
213 | 2024-09-01 | 73/6 | DA+0 | DRY | Pipe | 2024-09-22 | Shree Shyam Const. | 2024-09-01
214 | 2024-09-01 | 42/3 | DA+0 | Sandy | Pipe | 2024-09-22 | Mahadev Construction | 2024-09-01
215 | 2024-09-01 | 69/1 | DA+3 | DRY | Pipe | 2024-09-27 | Bhati Const. | 2024-09-01
216 | 2024-09-01 | 25/4 | DA+0 | Sandy | Pipe | 2024-09-30 | J.P. Infra | 2024-09-01
217 | 2024-09-01 | 73/5 | DA+0 | DRY | Pipe | 2024-10-07 | Shree Shyam Const. | 2024-10-01
218 | 2024-09-01 | 43/4 | DA+3 | Sandy | Pipe | 2024-09-30 | N.R. Enterprises | 2024-09-01
219 | 2024-09-01 | 13/1 | DA+9 | DRY | Pipe | 2024-09-30 | Punia Construction | 2024-09-01
220 | 2024-09-01 | 40/2 | DA+3 | Sandy | Pipe | 2024-09-30 | D.R. Construction | 2024-09-01
221 | 2024-09-01 | 73/8 | DA+3 | DRY | Pipe | 2024-10-07 | Shakti Construction | 2024-10-01
222 | 2024-09-01 | 59/1 | DA+3 | DRY | Pipe | 2024-10-01 | Bhati Const. | 2024-10-01
223 | 2024-09-01 | 19/2 | DA+0 | DRY | Pipe | 2024-09-30 | Vibe Infra | 2024-09-01
224 | 2024-09-01 | 72/2 | DA+0 | DRY | Pipe | 2024-10-07 | Shree Shyam Const. | 2024-10-01
225 | 2024-09-01 | 17/0 | DB2+3 | DRY | Pipe | 2024-09-30 | Om Enterprise | 2024-09-01
226 | 2024-09-01 | 66/0 | DC2+6 | DRY | Pipe | 2024-09-27 | Bhati Const. | 2024-09-01
227 | 2024-09-01 | 59/11 | DA+6 | DFR | CP | 2024-09-28 | Mahadev Eng | 2024-09-01
228 | 2024-09-01 | 19/3 | DA+0 | DRY | Pipe | 2024-10-14 | Vibe Infra | 2024-10-01
229 | 2024-09-01 | 43/3 | DA+0 | DRY | Pipe | 2024-09-30 | Parsuram Sai | 2024-09-01
230 | 2024-09-01 | 73/3 | DA+0 | DRY | Pipe | 2024-10-07 | Awadh Const. | 2024-10-01
231 | 2024-10-01 | 73/7 | DA+0 | DRY | Pipe | 2024-10-07 | Shakti Construction | 2024-10-01
232 | 2024-10-01 | 59/0 | DC2+0 | DRY | Pipe | 2024-10-05 | Bhati Const. | 2024-10-01
233 | 2024-10-01 | 67/0 | DC1+9 | DRY | Pipe | 2024-10-10 | Bhati Const. | 2024-10-01
234 | 2024-10-01 | 42/5 | DA+9 | Sandy | Pipe | 2024-10-28 | Mahadev Construction | 2024-10-01
235 | 2024-10-01 | 43/0 | DB1+0 | Sandy | Pipe | 2024-10-09 | N.R. Enterprises | 2024-10-01
236 | 2024-10-01 | 25/3 | DA+0 | Sandy | Pipe | 2024-10-08 | J.P. Infra | 2024-10-01
237 | 2024-10-01 | 69/0 | DB2+0 | DFR | CP | 2024-10-16 | Bhati Const. | 2024-10-01
238 | 2024-10-01 | 73/4 | DA+0 | DRY | Pipe | 2024-10-10 | Shree Shyam Const. | 2024-10-01
239 | 2024-10-01 | 22/13 | DA+6 | Sandy | Pipe | 2024-12-09 | Rbm | 2024-12-01
240 | 2024-10-01 | 74/0 | DB2+0 | Sandy | Pipe | 2024-10-16 | Shakti Construction | 2024-10-01
241 | 2024-10-01 | 25/1 | DA+3 | DRY | Pipe | 2024-12-17 | J.P. Infra | 2024-12-01
242 | 2024-10-01 | 43/2 | DA+0 | Sandy | Pipe | 2024-12-21 | Parsuram Sai | 2024-12-01
243 | 2024-10-01 | 72/3 | DA+3 | DRY | Pipe | 2024-10-18 | Shree Shyam Const. | 2024-10-01
244 | 2024-10-01 | 43/11 | DA+3 | Sandy | Pipe | 2024-12-17 | Jitendra Enterprises | 2024-12-01
245 | 2024-10-01 | 13/0 | DD60+3 | DRY | Pipe | 2025-01-12 | R.K. Construction | 2025-01-01
246 | 2024-10-01 | 71/7 | DA+3 | DRY | Pipe | 2024-10-22 | Shree Shyam Const. | 2024-10-01
247 | 2024-10-01 | 59/4 | DA+3 | DFR | CP | 2024-10-23 | Bhati Const. | 2024-10-01
248 | 2024-10-01 | 22/12 | DA+3 | Sandy | Pipe | 2024-12-09 | Rbm | 2024-12-01
249 | 2024-10-01 | 42/1 | DA+6 | Sandy | Pipe | 2024-12-18 | N.R. Enterprises | 2024-12-01
250 | 2024-10-01 | 71/6 | DA+0 | DRY | Pipe | 2024-10-22 | Shree Shyam Const. | 2024-10-01
251 | 2024-10-01 | 49/7 | DA+0 | Sandy | Pipe | 2024-10-23 | Kalpana Const. | 2024-10-01
252 | 2024-10-01 | 25/2 | DA+0 | DRY | Pipe | 2024-12-17 | J.P. Infra | 2024-12-01
252 | 2024-10-01 | 13/3 | DA+3 | Sandy | Pipe |  | Punia Construction
253 | 2024-10-01 | 22/7 | DA+0 | Sandy | Pipe | 2024-12-09 | Rbm | 2024-12-01
254 | 2024-10-01 | 22/3 | DA+9 | Sandy | Pipe | 2024-12-09 | J.P. Infra | 2024-12-01
255 | 2024-10-01 | 43/1 | DA+3 | Sandy | Pipe | 2024-12-21 | Parsuram Sai | 2024-12-01
256 | 2024-11-01 | 42/6 | DA+0 | Sandy | Pipe | 2024-12-04 | D.R. Construction | 2024-12-01
257 | 2024-11-01 | 2/4 | DA+3 | Sandy | Pipe | 2024-11-17 | Laxmi Enterprises | 2024-11-01
258 | 2024-11-01 | 42/2 | DA+6 | Sandy | Pipe | 2024-12-01 | D.R. Construction | 2024-12-01
259 | 2024-11-01 | 22/8 | DB1+0 | Sandy | Pipe | 2024-12-09 | Rbm | 2024-12-01
260 | 2024-11-01 | 22/2 | DA+6 | Sandy | Pipe | 2024-12-09 | J.P. Infra | 2024-12-01
261 | 2024-11-01 | 54/0 | DB1+6 | Sandy | Pipe | 2024-11-21 | Bhati Const. | 2024-11-01
262 | 2024-11-01 | 65/8 | DA+0 | DRY | Pipe | 2024-12-06 | Bhati Const. | 2024-12-01
263 | 2024-11-01 | 42/0 | DC1+0 | Sandy | Pipe | 2024-12-04 | D.R. Construction | 2024-12-01
264 | 2024-11-01 | 65/7 | DA+0 | DRY | Pipe | 2024-12-06 | Bhati Const. | 2024-12-01
265 | 2024-12-01 | 2/3 | DA+3 | Sandy | Pipe | 2024-12-13 | Laxmi Enterprise | 2024-12-01
266 | 2024-12-01 | 22/4 | DA+9 | Sandy | Pipe | 2024-12-09 | Jp Infra | 2024-12-01
267 | 2024-12-01 | 6/1 | DA+0 | DFR | CP | 2024-12-19 | H.S. Engineering | 2024-12-01
268 | 2024-12-01 | 12/0 | DD60+0 | DRY | Pipe | 2025-01-04 | Vibe Infra Power | 2025-01-01
269 | 2024-12-01 | 22/5 | DA+9 | DRY | Pipe | 2024-12-21 | S.D. Infra | 2024-12-01
270 | 2024-12-01 | 41/2 | DA+0 | Sandy | Pipe | 2024-12-16 | D.R. Construction | 2024-12-01
271 | 2024-12-01 | 2/5 | DA+3 | Sandy | Pipe | 2024-12-28 | Sri Nagana Ray Enterprise | 2024-12-01
272 | 2024-12-01 | 22/9 | DA+6 | Sandy | Pipe | 2025-01-06 | Rbm | 2025-01-01
273 | 2024-12-01 | 70/8 | DA+3 | DRY | Pipe | 2025-02-01 | Tantray Construction | 2025-02-01
274 | 2024-12-01 | 72/1 | DA+3 | DRY | Pipe | 2025-02-01 | Meer Const | 2025-02-01
275 | 2024-12-01 | 70/7 | DA+3 | DRY | Pipe | 2025-02-01 | Tantray Construction | 2025-02-01
276 | 2024-12-01 | 71/8 | DA+3 | DRY | Pipe | 2025-02-01 | Meer Const | 2025-02-01
277 | 2024-12-01 | 52/1 | DA+6 | Sandy | Pipe | 2025-02-17 | Tantray Construction | 2025-02-01
278 | 2024-12-01 | 70/9 | DA+3 | DRY | Pipe | 2025-02-01 | Tantray Construction | 2025-02-01
279 | 2024-12-01 | 6/2 | DA+0 | DFR | CP | 2025-01-05 | Hs Engineering | 2025-01-01
280 | 2024-12-01 | 72/0 | DB2+3 | DRY | Pipe | 2025-01-28 | Meer Const | 2025-01-01
281 | 2024-12-01 | 70/6 | DA+3 | DRY | Pipe | 2025-01-27 | Tantray Construction | 2025-01-01
282 | 2024-12-01 | 2/6 | DA+3 | Sandy | Pipe | 2025-01-06 | Sri Nagana Ray Enterprise | 2025-01-01
283 | 2024-12-01 | 71/4 | DA+3 | DRY | Pipe | 2025-01-28 | Meer Const | 2025-01-01
284 | 2024-12-01 | 52/2 | DA+6 | Sandy | Pipe | 2025-02-17 | Tantray Construction | 2025-02-01
285 | 2024-12-01 | 70/10 | DA+3 | DRY | Pipe | 2025-02-01 | Tantray Construction | 2025-02-01
286 | 2024-12-01 | 2/2 | DA+3 | Sandy | Pipe | 2025-01-06 | Laxmi Enterprises | 2025-01-01
287 | 2024-12-01 | 71/5 | DA+3 | DRY | Pipe | 2025-02-01 | Meer Const | 2025-02-01
288 | 2024-12-01 | 70/11 | DA+3 | DRY | Pipe | 2025-03-29 | Tantray Construction | 2025-03-01
289 | 2024-12-01 | 53/2 | DA+0 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
290 | 2024-12-01 | 36/0 | DB2+0 | Sandy | Pipe | 2024-12-30 | Parsuram Sahi | 2024-12-01
291 | 2024-12-01 | 71/3 | DA+6 | DRY | Pipe | 2025-01-28 | Meer Const | 2025-01-01
292 | 2024-12-01 | 52/4 | DA+9 | Sandy | Pipe | 2025-02-17 | Tantray Construction | 2025-02-01
293 | 2024-12-01 | 10/5 | DA+3 | DRY | Pipe | 2024-12-20 | Jsr Infrastructure | 2024-12-01
294 | 2024-12-01 | 35/4 | DA+0 | DRY | Pipe | 2025-01-03 | Parsuram Sahi | 2025-01-01
295 | 2024-12-01 | 71/0 | DB2+3 | DRY | Pipe | 2025-01-27 | Tantray Construction | 2025-01-01
296 | 2025-01-01 | 22/11 | DA+6 | Sandy | Pipe | 2025-01-07 | Rbm | 2025-01-01
297 | 2025-01-01 | 71/2 | DA+3 | DRY | Pipe | 2025-01-27 | Meer Const | 2025-01-01
298 | 2025-01-01 | 71/1 | DA+3 | DRY | Pipe | 2025-01-27 | Meer Const | 2025-01-01
299 | 2025-01-01 | 54/3 | DA+6 | Sandy | Pipe | 2025-01-07 | Tantray Construction | 2025-01-01
300 | 2025-01-01 | 44/1 | DA+0 | Sandy | Pipe | 2025-03-16 | Tantray Construction | 2025-03-01
301 | 2025-01-01 | 44/2 | DA+0 | Sandy | Pipe | 2025-03-16 | Tantray Construction | 2025-03-01
302 | 2025-01-01 | 8/9 | DA+3 | DFR | CP | 2025-01-09 | Jsr Infrastructure | 2025-01-01
303 | 2025-01-01 | 53/1 | DA+9 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
304 | 2025-01-01 | 70/3 | DA+3 | DRY | Pipe | 2025-01-25 | Meer Const | 2025-01-01
305 | 2025-01-01 | 54/4 | DA+9 | Sandy | Pipe | 2025-01-10 | Tantray Construction | 2025-01-01
306 | 2025-01-01 | 45/0 | DC2+0 | Sandy | Pipe | 2025-02-26 | Nadeem | 2025-02-01
307 | 2025-01-01 | 44/11 | DA+0 | Sandy | Pipe | 2025-02-27 | Nadeem | 2025-02-01
308 | 2025-01-01 | 53/0 | DB2+9 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
309 | 2025-01-01 | 44/10 | DB1+9 | Sandy | Pipe | 2025-02-27 | Nadeem | 2025-02-01
310 | 2025-01-01 | 44/4 | DA+9 | Sandy | Pipe | 2025-02-28 | Tantray Construction | 2025-02-01
311 | 2025-01-01 | 70/4 | DA+3 | DRY | Pipe | 2025-01-25 | Meer Const | 2025-01-01
312 | 2025-01-01 | 34/1 | DA+9 | Sandy | Pipe | 2025-01-16 | Ymk Construction | 2025-01-01
313 | 2025-01-01 | 70/5 | DA+3 | DRY | Pipe | 2025-01-27 | Meer Const | 2025-01-01
314 | 2025-01-01 | 53/3 | DA+6 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
315 | 2025-01-01 | 35/2 | DB1+0 | Sandy | Pipe | 2025-01-19 | Parsuram Sahi | 2025-01-01
316 | 2025-01-01 | 68/0 | DD45+0 | DRY | Pipe | 2025-02-19 | Bhati Const. | 2025-02-01
317 | 2025-01-01 | 1A/1 | DA+6 | DFR | CP | 2025-01-21 | Jsr Infrastructure | 2025-01-01
318 | 2025-01-01 | 53/4 | DA+0 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
319 | 2025-01-01 | 52/0 | DC2+0 | Sandy | Pipe | 2025-02-17 | Tantray Construction | 2025-02-01
320 | 2025-01-01 | 44/5 | DA+9 | Sandy | Pipe | 2025-02-28 | Tantray Construction | 2025-02-01
321 | 2025-01-01 | 2/0 | DC1+0 | DRY | Pipe | 2025-01-21 | Laxmi Enterprises | 2025-01-01
322 | 2025-01-01 | 44/9 | DA+9 | Sandy | Pipe | 2025-02-27 | Iqbal | 2025-02-01
323 | 2025-01-01 | 70/1 | DA+3 | DRY | Pipe | 2025-01-25 | Meer Const | 2025-01-01
324 | 2025-01-01 | 70/2 | DA+3 | DRY | Pipe | 2025-02-19 | Bhati Const. | 2025-02-01
325 | 2025-01-01 | 44/6 | DB1+3 | Sandy | Pipe | 2025-02-28 | Tantray Construction | 2025-02-01
326 | 2025-01-01 | 55/2 | DA+0 | WFR | Pipe | 2025-02-07 | Meer Const | 2025-02-01
327 | 2025-01-01 | 47/4 | DA+3 | Sandy | Pipe | 2025-01-29 | Tantray Construction | 2025-01-01
328 | 2025-01-01 | 50/5 | DA+9 | Sandy | Pipe | 2025-01-23 | Om Const | 2025-01-01
329 | 2025-01-01 | 1A/4 | DA+3 | DFR | CP | 2025-01-28 | Naganaray Enterprise | 2025-01-01
330 | 2025-01-01 | 28/6 | DA+6 | Sandy | Pipe | 2025-01-29 | Vishwakarma Construction | 2025-01-01
331 | 2025-01-01 | 70/0 | DC1+0 | DRY | Pipe | 2025-01-25 | Meer Const | 2025-01-01
332 | 2025-01-01 | 44/7 | DA+9 | Sandy | Pipe | 2025-02-18 | Iqbal | 2025-02-01
333 | 2025-01-01 | 34/2 | DA+6 | Sandy | Pipe | 2025-01-27 | Ymk Construction | 2025-01-01
334 | 2025-01-01 | 65/10 | DA+0 | DRY | Pipe | 2025-02-19 | Bhati Const. | 2025-02-01
335 | 2025-01-01 | 57/1 | DA+0 | Sandy | Pipe | 2025-01-29 | Meer Const | 2025-01-01
336 | 2025-01-01 | 28/5 | DA+9 | Sandy | Pipe | 2025-01-31 | Vishwakarma Construction | 2025-01-01
337 | 2025-01-01 | 35/0 | DB2+6 | Sandy | Pipe | 2025-01-29 | Parsuram Sahi | 2025-01-01
338 | 2025-01-01 | 44/3 | DA+0 | Sandy | Pipe | 2025-02-18 | Tantray Construction | 2025-02-01
339 | 2025-01-01 | 1A/3 | DA+0 | DRY | Pipe | 2025-01-31 | Jsr Infrastructure | 2025-01-01
340 | 2025-01-01 | 55/8 | DA+6 | Sandy | Pipe | 2025-02-03 | Meer Const | 2025-02-01
341 | 2025-01-01 | 1A/2 | DA+0 | DRY | Pipe | 2025-02-03 | Jsr Infrastructure | 2025-02-01
342 | 2025-01-01 | 44/8 | DCT+0 | Sandy | Pipe | 2025-02-28 | Iqbal | 2025-02-01
343 | 2025-02-01 | 34/0 | DB2+0 | DRY | Pipe | 2025-02-04 | Ymk Construction | 2025-02-01
344 | 2025-02-01 | 28/8 | DA+3 | Sandy | Pipe | 2025-02-04 | Vishwakarma Construction | 2025-02-01
345 | 2025-02-01 | 47/1 | DA+3 | Sandy | Pipe | 2025-01-29 | Tantray Construction | 2025-01-01
346 | 2025-02-01 | 1A/5 | DA+0 | DRY | Pipe | 2025-02-05 | Jsr Infrastructure | 2025-02-01
347 | 2025-02-01 | 28/7 | DA+3 | Sandy | Pipe | 2025-02-07 | Vishwakarma Construction | 2025-02-01
348 | 2025-02-01 | 33/1 | DA+0 | DRY | Pipe | 2025-02-10 | Ymk Construction | 2025-02-01
349 | 2025-02-01 | 28/4 | DA+0 | Sandy | Pipe | 2025-02-10 | Vishwakarma Construction | 2025-02-01
350 | 2025-02-01 | 1A/6 | DA+0 | Sandy | Pipe | 2025-02-10 | Jsr Infrastructure | 2025-02-01
351 | 2025-02-01 | 35/3 | DB1+6 | Sandy | Pipe | 2025-02-13 | Parsuram Sahi | 2025-02-01
352 | 2025-02-01 | 45/1 | DA+9 | Sandy | Pipe | 2025-02-26 | Tantray Construction | 2025-02-01
353 | 2025-02-01 | 54/5 | DA+9 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
354 | 2025-02-01 | 32/3 | DA+0 | Sandy | Pipe | 2025-02-14 | Ymk Construction | 2025-02-01
355 | 2025-02-01 | 28/3 | DA+0 | DFR | CP | 2025-02-14 | Vishwakarma Construction | 2025-02-01
356 | 2025-02-01 | 32/4 | DA+0 | Sandy | Pipe | 2025-02-16 | Ymk Construction | 2025-02-01
357 | 2025-02-01 | 28/2 | DA+0 | DFR | CP | 2025-02-16 | Vishwakarma Construction | 2025-02-01
358 | 2025-02-01 | 32/2 | DA+3 | DRY | Pipe | 2025-03-04 | Ymk Construction | 2025-03-01
359 | 2025-02-01 | 29/0 | DB1+0 | DRY | Pipe | 2025-02-20 | Vishwakarma Construction | 2025-02-01
360 | 2025-02-01 | 55/0 | DB1+6 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
361 | 2025-02-01 | 44/0 | DB1+3 | Sandy | Pipe | 2025-03-16 | Om Const | 2025-03-01
362 | 2025-02-01 | 30/0 | DC1+0 | DRY | Pipe | 2025-02-23 | Vishwakarma Construction | 2025-02-01
363 | 2025-02-01 | 33/0 | DC1+0 | DRY | Pipe | 2025-02-24 | Ymk Construction | 2025-02-01
364 | 2025-02-01 | 1A/0 | DD60+0 | DRY | Pipe | 2025-02-24 | Jsr Infrastructure | 2025-02-01
365 | 2025-02-01 | 30/1 | DA+0 | Sandy | Pipe | 2025-02-25 | Vishwakarma Construction | 2025-02-01
366 | 2025-02-01 | 43/10 | DA+3 | Sandy | Pipe | 2025-03-16 | Om Const | 2025-03-01
367 | 2025-02-01 | 29/4 | DA+6 | DRY | Pipe | 2025-03-01 | Vishwakarma Construction | 2025-03-01
368 | 2025-02-01 | 29/1 | DA+3 | DRY | Pipe | 2025-03-03 | Vishwakarma Construction | 2025-03-01
369 | 2025-02-01 | 55/1 | DA+0 | WFR | Pipe | 2025-03-02 | Bhati | 2025-03-01
370 | 2025-03-01 | 35/5 | DA+0 | Sandy | Pipe | 2025-03-06 | Parsuram Sahi | 2025-03-01
371 | 2025-03-01 | 32/1 | DA+3 | Sandy | Pipe | 2025-03-06 | Ymk | 2025-03-01
372 | 2025-03-01 | 30/3 | DA+3 | Sandy | Pipe | 2025-03-06 | Vishwakarma Construction | 2025-03-01
373 | 2025-03-01 | 30/2 | DA+0 | Sandy | Pipe | 2025-03-10 | Vishwakarma Construction | 2025-03-01
374 | 2025-03-01 | 1/0 | DD60+0 | DRY | Pipe | 2025-02-24 | Jsr Infrastructure | 2025-02-01
375 | 2025-03-01 | 32/0 | DC1+0 | DRY | Pipe | 2025-03-11 | Ymk | 2025-03-01
376 | 2025-03-01 | 29/2 | DA+3 | DRY | Pipe | 2025-03-12 | Vishwakarma Construction | 2025-03-01
377 | 2025-03-01 | 1A/7 | DA+3 | Sandy | Pipe | 2025-03-11 | Jsr Infrastructure | 2025-03-01
378 | 2025-03-01 | 29/3 | DA+0 | Sandy | Pipe | 2025-03-14 | Vishwakarma Construction | 2025-03-01
379 | 2025-03-01 | 31/2 | DA+0 | DRY | Pipe | 2025-03-14 | Ymk | 2025-03-01
380 | 2025-03-01 | 31/1 | DA+0 | DRY | Pipe | 2025-03-15 | Ymk | 2025-03-01
381 | 2025-03-01 | 2/1 | DA+3 | Sandy | Pipe | 2025-03-21 | Jsr Infrastructure | 2025-03-01
382 | 2025-03-01 | 34/3 | DA+0 | Sandy | Pipe | 2025-03-28 | Ymk | 2025-03-01
383 | 2025-03-01 | 26/7 | DA+0 | DFR | CP | 2025-03-28 | Jsr Infrastructure | 2025-03-01
384 | 2025-03-01 | 37/3 | DA+0 | Sandy | Pipe | 2025-04-03 | Vishwakarma Construction | 2025-04-01
385 | 2025-03-01 | 34/4 | DA+0 | Sandy | Pipe | 2025-04-04 | Ymk | 2025-04-01
386 | 2025-03-01 | 57/0 | DD60+25 | Sandy | Pipe | 2025-04-07 | Bhati | 2025-04-01
387 | 2025-04-01 | 35/1 | DA+9 | Sandy | Pipe | 2025-04-06 | Ymk | 2025-04-01
388 | 2025-04-01 | 46/0 | DD60+25 | Sandy | Pipe | 2025-04-10 | Om Const | 2025-04-01
389 | 2025-04-01 | 38/4 | DA+9 | Sandy | Pipe | 2025-04-15 | Vishwakarma Construction | 2025-04-01
390 | 2025-04-01 | 56/0 | DD60+25 | Sandy | Pipe | 2025-04-11 | Bhati | 2025-04-01
391 | 2025-04-01 | 39/0 | DB2+6 | Sandy | Pipe | 2025-04-15 | Vishwakarma Construction | 2025-04-01
392 | 2025-04-01 | 27/3 | DA+3 | DFR | CP | 2025-05-17 | YMK | 2025-05-01
393 | 2025-04-01 | 47/0 | DD60+25 | Sandy | Pipe | 2025-04-17 | Om Const | 2025-04-01
394 | 2025-04-01 | 4/0 | DD60+6 | DRY | Pipe | 2025-05-05 | Jsr Infrastructure | 2025-05-01
395 | 2025-04-01 | 38/2 | DA+6 | Sandy | Pipe | 2025-04-23 | Vishwakarma Construction | 2025-04-01
396 | 2025-04-01 | 27/2 | DA+3 | DFR | CP | 2025-05-19 | YMK | 2025-05-01
397 | 2025-04-01 | 38/1 | DA+0 | Sandy | Pipe | 2025-04-25 | Vishwakarma Construction | 2025-04-01
398 | 2025-04-01 | 38/0 | DB2+6 | Sandy | Pipe | 2025-04-28 | Vishwakarma Construction | 2025-04-01
399 | 2025-04-01 | 39/1 | DA+0 | Sandy | Pipe | 2025-05-01 | Vishwakarma Construction | 2025-05-01
400 | 2025-05-01 | 40/0 | DC2+0 | Sandy | Pipe | 2025-05-18 | Vishwakarma Construction | 2025-05-01
401 | 2025-05-01 | 40/1 | DA+6 | Sandy | Pipe | 2025-05-10 | Vishwakarma Construction | 2025-05-01
402 | 2025-05-01 | 27/6 | DA+0 | Sandy | Pipe | 2025-05-20 | YMK | 2025-05-01
403 | 2025-05-01 | 1A/8 | DA+0 | Sandy | Pipe | 2025-05-17 | Jsr Infrastructure | 2025-05-01
404 | 2025-05-01 | 27/4 | DA+3 | DFR | CP | 2025-05-20 | YMK | 2025-05-01
405 | 2025-05-01 | 38/3 | DA+9 | Sandy | Pipe | 2025-05-20 | Vishwakarma Construction | 2025-05-01
406 | 2025-05-01 | 42/4 | DA+0 | Sandy | Pipe | 2025-05-21 | Vishwakarma Construction | 2025-05-01
407 | 2025-05-01 | 40/3 | DA+3 | Sandy | Pipe | 2025-05-25 | Vishwakarma Construction | 2025-05-01
408 | 2025-05-01 | 21/9 | DA+3 | DFR | CP | 2025-05-27 | M.R. Choudhary | 2025-05-01
409 | 2025-05-01 | 27/7 | DB1+0 | DFR | CP | 2025-05-31 | YMK | 2025-05-01
410 | 2025-05-01 | 4/3 | DA+0 | DRY | Pipe | 2025-05-30 | Nyce Service & Security | 2025-05-01
411 | 2025-05-01 | 2/8 | DA+0 | Sandy | Pipe | 2025-06-04 | Jsr Infrastructure | 2025-06-01
412 | 2025-05-01 | 8/11 | DA+0 | DRY | Pipe | 2025-06-18 | Bhati Construction | 2025-06-01
413 | 2025-06-01 | 41/1 | DB1+9 | Sandy | Pipe | 2025-06-02 | Vishwakarma Construction | 2025-06-01
414 | 2025-06-01 | 30/4 | DA+3 | DRY | Pipe | 2025-06-08 | Rabbit bright technology pvt. Ltd. | 2025-06-01
415 | 2025-06-01 | 21/7 | DA+3 | DFR | CP | 2025-06-08 | M.R. Choudhary | 2025-06-01
416 | 2025-06-01 | 19/5 | DA+0 | DRY | Pipe | 2025-06-08 | Shree Ram Construction | 2025-06-01
417 | 2025-06-01 | 41/0 | DC1+6 | Sandy | Pipe | 2025-06-11 | Vishwakarma Construction | 2025-06-01
418 | 2025-06-01 | 27/1 | DA+3 | DFR | CP | 2025-07-12 | YMK | 2025-06-01
419 | 2025-06-01 | 30/5 | DA+3 | DRY | Pipe | 2025-06-17 | Rabbit bright technology pvt. Ltd. | 2025-06-01
420 | 2025-06-01 | 2/7 | DA+3 | Sandy | Pipe | 2025-06-14 | Jsr Infrastructure | 2025-06-01
421 | 2025-06-01 | 11/4 | DA+0 | Sandy | Pipe | 2025-06-15 | BR & Sons | 2025-06-01
422 | 2025-06-01 | 36/2 | DA+0 | Sandy | Pipe | 2025-06-16 | Vishwakarma Construction | 2025-06-01
423 | 2025-06-01 | 36/3 | DA+0 | Sandy | Pipe | 2025-06-15 | Vishwakarma Construction | 2025-06-01
424 | 2025-06-01 | 10/0 | DD60+25 | DFR | CP | 2025-06-18 | Bhati Construction | 2025-06-01
425 | 2025-06-01 | 4/1 | DA+0 | DRY | Pipe | 2025-07-04 | Jsr Infrastructure | 2025-07-01
426 | 2025-06-01 | 21/5 | DA+6 | DFR | CP | 2025-07-24 | M.R. Choudhary | 2025-07-01
427 | 2025-06-01 | 36/4 | DA+6 | Sandy | Pipe | 2025-06-23 | Vishwakarma Construction | 2025-06-01
428 | 2025-06-01 | 30/6 | DA+0 | DRY | Pipe | 2025-07-02 | YMK | 2025-07-01
429 | 2025-06-01 | 2/9 | DA+0 | DRY | Pipe | 2025-07-04 | Jsr Infrastructure | 2025-07-01
430 | 2025-06-01 | 37/0 | DB2+0 | Sandy | Pipe | 2025-07-03 | Vishwakarma Construction | 2025-07-01
431 | 2025-06-01 | 21/4 | DA+3 | Sandy | Pipe | 2025-07-24 | M.R. Choudhary | 2025-07-01
432 | 2025-07-01 | 31/0 | DB2+0 | Sandy | Pipe | 2025-07-03 | YMK | 2025-07-01
433 | 2025-07-01 | 4/2 | DA+0 | DRY | Pipe | 2025-07-04 | Nyce Services | 2025-07-01
434 | 2025-07-01 | 3/0 | DD60+6 | DRY | Pipe | 2025-07-12 | Jsr Infrastructure | 2025-07-01
435 | 2025-07-01 | 4/4 | DA+0 | DRY | Pipe | 2025-07-12 | Nice Security & Services | 2025-07-01
436 | 2025-07-01 | 21/3 | DA+6 | Sandy | Pipe | 2025-07-24 | M.R. Choudhary | 2025-07-01
436 | 2025-07-01 | 8/12 | DA+0 | DRY | Pipe |  | Jsr Infrastructure
436 | 2025-07-01 | 8/2 | DA+3 | DRY | Pipe |  | Dhakad Enterprises
437 | 2025-07-01 | 37/1 | DA+9 | Sandy | Pipe | 2025-07-18 | Vishwakarma Construction | 2025-07-01
437 | 2025-07-01 | 8/1 | DA+3 | DRY | Pipe |  | Dhakad Enterprises
438 | 2025-07-01 | 20/0 | DB2+0 | Sandy | Pipe | 2025-07-24 | Vishwakarma Construction | 2025-07-01
438 | 2025-07-01 | 27/0 | DC1+0 | DFR | CP |  | YMK
439 | 2025-07-01 | 37/2 | DA+3 | Sandy | Pipe | 2025-07-18 | Vishwakarma Construction | 2025-07-01
440 | 2025-07-01 | 9/0 | DD60+18 | DRY | Pipe | 2025-07-22 | Jsr Infrastructure | 2025-07-01
441 | 2025-07-01 | 8/5 | DA+3 | DRY | Pipe | 2025-07-29 | Yash Infra | 2025-07-01
442 | 2025-07-01 | 20/2 | DA+0 | DRY | Pipe | 2025-07-24 | Vishwakarma Construction | 2025-07-01
442 | 2025-07-01 | 21/0 | DB2+0 | DRY | Pipe |  | Vishwakarma Construction
443 | 2025-07-01 | 26/0 | DB1+0 | DFR | CP | 2025-07-27 | YMK | 2025-07-01
443 | 2025-07-01 | 20/3 | DA+0 | DRY | Pipe |  | Vishwakarma Construction
443 | 2025-07-01 | 21/2 | DA+0 | Sandy | Pipe |  | Vishwakarma Construction
444 | 2025-07-01 | 8/0 | DB1+0 | DRY | Pipe | 2025-07-31 | Dhakad Enterprises | 2025-07-01
444 | 2025-07-01 | 8/4 | DA+3 | DRY | Pipe |  | Jsr Infrastructure
445 | 2025-07-01 | 24/0 | DD45+3 | DRY | Pipe | 2025-08-05 | YMK | 2025-08-01
445 | 2025-08-01 | 14A/0 | DC1+0 | DRY | Pipe |  | BR & Sons
446 | 2025-08-01 | 23/0 | DD45+3 | DRY | Pipe | 2025-08-07 | YMK | 2025-08-01
447 | 2025-08-01 | 10/1 | DA+0 | DRY | Pipe | 2025-08-24 | Jsr Infrastructure | 2025-08-01
447 | 2025-08-01 | 11/1 | DA+0 | Sandy | Pipe |  | Om Construction_Chandrapal
448 | 2025-08-01 | 26/1 | DA+0 | DRY | Pipe | 2025-08-20 | YMK | 2025-08-01
448 | 2025-08-01 | 11/2 | DA+0 | Sandy | Pipe |  | Om Construction_Chandrapal
449 | 2025-08-01 | 28/1 | DA+0 | DRY | Pipe | 2025-08-29 | YMK | 2025-08-01
449 | 2025-08-01 | 10/7 | DA+3 | DRY | Pipe |  | Jsr Infrastructure
449 | 2025-09-01 | 20/1 | DA+0 | Sandy | Pipe |  | Vishwakarma Construction
449 | 2025-09-01 | 6/0 | DB2+9 | DRY | Pipe |  | Dhakad Enterprises
449 | 2025-09-01 | 5/0 | DB1+9 | DRY | Pipe |  | Dhakad Enterprises
450 | 2025-09-01 | 10/16 | DA+3 | DRY | Pipe | 2025-09-20 | Jsr Infrastructure | 2025-09-01
450 | 2025-09-01 | 11/0 | DB1+0 | Sandy | Pipe |  | Om Construction_Chandrapal
450 | 2025-09-01 | 22/10 | DA+6 | Sandy | Pipe |  | Vishwakarma Construction
451 | 2025-09-01 | 10/15 | DA+3 | DRY | Pipe | 2025-09-20 | Jsr Infrastructure | 2025-09-01
451 | 2025-09-01 | 11/3 | DA+0 | Sandy | Pipe |  | Om Construction_Chandrapal
451 | 2025-09-01 | 7/0 | DB1+0 | DRY | Pipe |  | Dhakad Enterprises
451 | 2025-10-01 | 10/10 | DA+3 | Sandy | Pipe |  | Jsr Infrastructure
451 | 2025-10-01 | 10/23 | DA+0 | Sandy | Pipe |  | Om Construction_Chandrapal
451 | 2025-10-01 | 21/8 | DA+6 | DRY | Pipe |  | Vishwakarma Construction
451 | 2025-10-01 | 10/22 | DA+0 | Sandy | Pipe |  | Om Construction_Chandrapal
451 | 2025-10-01 | 8/3 | DA+0 | DRY | Pipe |  | Jsr Infrastructure
451 | 2025-10-01 | 19/4 | DA+0 | DRY | Pipe |  | Vishwakarma Construction
451 | 2025-10-01 | 21/6 | DA+3 | DRY | Pipe |  | Vishwakarma Construction
451 | 2025-11-01 | 26/8 | DA+6 | DFR | CP |  | Vishwakarma Construction
451 | 2025-11-01 | 22/0 | DB2+3 | DRY | Pipe |  | Vishwakarma Construction
451 | 2025-11-01 | 13/4 | DA+3 | DRY | Pipe |  | Vishwakarma Construction
451 | 2026-02-01 | 10/2 | DA+0 | DFR | CP |  | Jsr Infrastructure
451 | 2026-02-01 | 8/8 | DA+6 | DRY | Pipe |  | Jsr Infrastructure
451 | 2026-02-01 | 8/6 | DA+3 | DRY | Pipe |  | Jsr Infrastructure
451 | 0 | 0 | 0 | 0 |  |  | 0
451 | 0 | 0 | 0 | 0 |  |  | 0

## Erection Productivity (hidden)
Sr no | Item | Unit | Total | Comp Qty | Bal Qty | Aug'25 |  |  | Remarks
|  |  | Qty | 31.08.25 | 01.08.25 | Plan | WIP | Actual
1 | Erection | Nos | 485 | 303 | 182 | 87 | 18 | 6
2 | Stringing | KM | 191.3 | 43.51 | 147.79 | 0 | 0 | 0
[44 empty] | 0 | [11 empty] | 0
Gang Wise Output
Sr. No. | Sub-Contractor Name | WIP |  |  | Start Date | Comp Date | Output -01.08.25 | Output -02.08.25 | Output -03.08.25 | Output -04.08.25 | Output -05.08.25 | Output -06.08.25 | Output -07.08.25 | Output -08.08.25 | Output -09.08.25 | Output -10.08.25 | Output -11.08.25 | Output -12.08.25 | Output -13.08.25 | Output -14.08.25 | Output -15.08.25 | Output -16.08.25 | Output -17.08.25 | Output -18.08.25 | Output -19.08.25 | Output -20.08.25 | Output -21.08.25 | Output -22.08.25 | Output -23.08.25 | Output -24.08.25 | Output -25.08.25 | Output -26.08.25 | Output -27.08.25 | Output -28.08.25 | Output -29.08.25 | Output -30.08.25 | Output -31.08.25 | Output -01.09.25 | Output -02.09.25 | Output -03.09.25 | Output -04.09.25 | Output -05.09.25 | Output -06.09.25 | Output -07.09.25 | Output -08.09.25 | Output -09.09.25 | Output -10.09.25 | Output -11.09.25 | Output -12.09.25 | Output -13.09.25 | Output -14.09.25 | Output -15.09.25 | Output -16.09.25 | Output -17.09.25 | Output -18.09.25 | Output -19.09.25 | Output -20.09.25 | Output -21.09.25 | Output -22.09.25 | Output -23.09.25 | Output -24.09.25 | Output -25.09.25 | Output -26.09.25 | Output -27.09.25 | Output -28.09.25 | Output -29.09.25 | Output -30.09.25 | Output -31.09.25 | Cumulative Till dated | Status
|  | Loc. No. | Type of Tower | Tower Weight
1 | Arawali-2 | 12/0 | DD60+0 | 0 | 2025-07-25 | 2025-08-02 | 3.8 | 4.1 | [60 empty] | 7.9 | Completed
2 | Vinay Gupta | 44/7 | DA+9 | 0 | 2025-07-26 | 2025-07-03 | 4.8 | 4.3 | 5.1 | [59 empty] | 14.2 | Completed
3 | Manish (Pawan) | 44/0 | DB1+3 | 0 | 2025-07-29 | 2025-08-03 | 8.4 | 7.8 | 8.4 | [59 empty] | 24.6 | Completed
4 | Jwala Singh | 29/1 | DA+3 | 0 | 2025-07-30 | 2025-08-04 | 7.2 | 7.1 | 6.8 | 8.8 | [58 empty] | 29.9 | Completed
5 | Vinay Gupta | 47/7 | DA+3 | 0 | 2025-07-26 | 2025-08-05 | 3.6 | 3.2 | 3.7 | 3.9 | 4.1 | [57 empty] | 18.5 | Completed
6 | Priyanka Devi | 19/5 | DA+0 | 0 | 2025-08-01 | 2025-08-05 | 7.2 | 8.2 | 8.2 | 6.2 | 7.7 | [57 empty] | 37.5 | Completed
7 | Sintu_Pawan (Satyam Enterprises) | 44/10 | DB1+9 | 0 | 2025-07-28 | 2025-08-06 | 7.9 | 8.2 | 8.3 | 8.1 | 8.6 | [57 empty] | 41.1 | Completed
8 | Pusplata (Kailash) | 30/3 | DA+3 | 0 | 2025-08-01 | 2025-08-06 | 6.2 | 6.2 | 7.2 | 6.9 | 6.5 | 5.8 | [56 empty] | 38.8 | Completed
9 | Bhairo Mahto | 4/1 | DA+0 | 0 | 2025-07-25 | 2025-08-09 | 2.9 | 2.7 | 3.2 | 3.5 | 3.8 | 3.1 | 2.9 | 2.8 | 2.7 | [53 empty] | 27.6 | Completed
10 | Pusplata (Praful) | 25/3 | DA+0 | 0 | 2025-07-31 | 2025-08-09 | 3.3 | 3.8 | 3.2 | 3.8 | 4.2 | 4.5 | 4.1 | 3.8 | 4.1 | [53 empty] | 34.8 | Completed
11 | Nitish (Pawan) | 44/5 | DA+9 | 0 | 2025-08-04 | 2025-08-09 |  |  |  | 5.2 | 8.2 | 8.9 | 9.1 | 8.7 | 7.1 | [53 empty] | 47.2 | Completed
12 | Jwala Singh | 8/12 | DA+0 | 0 | 2025-08-04 | 2025-08-09 |  |  |  | 5.2 | 6.3 | 6.2 | 6.8 | 6.9 | 6.1 | [53 empty] | 37.5 | Completed
13 | Jwala Singh | 29/0 | DB1+0 | 0 | 2025-07-30 | 2025-08-12 | 2.8 | 5.1 | 5.2 | 4.5 | 4.6 | 4.3 | 5.1 | 4.3 | 4.8 | 5.4 | 4.9 | 6.6 | [50 empty] | 57.6 | Completed
14 | Priyanka Devi | 2/0 | DC1+0 | 0 | 2025-07-29 | 2025-08-13 | 3.3 | 3.6 | 3.8 | 4.9 | 5.1 | 5.2 | 5.3 | 5.7 | 5.5 | 5.9 | 6.2 | 5.6 | 6.3 | [49 empty] | 66.4 | Completed
15 | Shobha Devi | 55/8 | DA+6 | 0 | 2025-08-07 | 2025-08-13 | [6 empty] | 5.7 | 6.9 | 6.2 | 6.8 | 6.1 | 7.2 | 6.2 | [49 empty] | 45.1 | Completed
16 | Vinay Gupta | 47/2 | DA+9 | 0 | 2025-08-04 | 2025-08-16 |  |  |  | 3.1 | 3.4 | 4.9 | 2.1 | 3.2 | 3.8 | 4.1 | 4.1 | 4.7 | 4.9 | 4.1 |  | 4.7 | [46 empty] | 47.1 | Completed
17 | Satyam Enterprises | 44/6 | DB1+3 | 0 | 2025-08-09 | 2025-08-16 | [8 empty] | 6.8 | 9.3 | 9.7 | 8.1 | 8.3 | 8.2 |  | 9.7 | [46 empty] | 60.1 | Completed
18 | Sheetal Singh | 2/3 | DA+3 | 0 | 2025-08-04 | 2025-08-17 |  |  |  | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | [45 empty] | 38.8 | Completed
19 | Sintu_Pawan (Satyam Enterprises) | 45/0 | DC2+0 | 0 | 2025-08-06 | 2025-08-17 | [5 empty] | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | [45 empty] | 66.381 | Completed
20 | Pusplata (Kailash) | 30/5 | DA+3 | 0 | 2025-08-06 | 2025-08-17 | [5 empty] | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | [45 empty] | 38.8 | Completed
21 | Pusplata (Ramchandra) | 27/4 | DA+3 | 0 | 2025-08-09 | 2025-08-17 | [8 empty] | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | [45 empty] | 38.8 | Completed
22 | Rahul Kumar | 40/3 | DA+3 | 0 | 2025-08-10 | 2025-08-17 | [9 empty] | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | [45 empty] | 38.8 | Completed
23 | Sobha Devi | 55/7 | DA+0 | 0 | 2025-08-13 | 2025-08-17 | [12 empty] | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | [45 empty] | 37.5 | Completed
24 | Satyam-Manish | 43/11 | DA+3 | 0 | 2025-08-12 | 2025-08-18 | [11 empty] | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | [44 empty] | 38.8 | Completed
25 | Pusplata_Pankaj | 17/4 | DA+3 | 0 | 2025-08-13 | 2025-08-18 | [12 empty] | 6.4667 | 6.4667 | 6.4667 | 6.4667 | 6.4667 | 6.4667 | [44 empty] | 38.8 | Completed
26 | Usha Tower | 2/5 | DA+3 | 0 | 2025-08-04 | 2025-08-19 |  |  |  | 2.2 | 2.5 | 2.5 | 2.8 | 2.9 | 2.1 | 2.7 | 3.1 | 1.9 | 2.4 | 2.7 |  | 2.9 | 2.1 | 2.3 | 2.7 | [43 empty] | 37.8 | Completed
27 | Jwala Singh | 28/5 | DA+9 | 0 | 2025-08-12 | 2025-08-19 | [11 empty] | 6.9 | 6.4 | 7.1 |  | 6.9 | 6.2 | 6.7 | 6.9 | [43 empty] | 47.1 | Completed
28 | Bhairo Mahto | 1/0 | DD60+0 | 0 | 2025-07-07 | 2025-08-20 | 2.9 | 3.1 | 2.8 | 2.2 | 2.5 | 2.5 | 2.8 | 2.9 | 2.1 | 2.7 | 3.1 | 1.9 | 2.4 | 2.7 |  | 2.9 | 2.1 | 2.3 | 2.7 | 2.9 | [42 empty] | 49.5 | Completed
29 | Gauri Shankar | 41/1 | DB1+9 | 0 | 2025-08-10 | 2025-08-10 | [9 empty] | 4.5 | 6.7 | 7.2 | 7.6 | 7.9 |  | 7.1 | 6.9 | 7.5 | 7.2 | 8.1 | [42 empty] | 70.7 | Completed
30 | Bhairo Mahto | 4/2 | DA+0 | 0 | 2025-07-30 | 2025-07-30 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | [40 empty] | 34.379 | Completed
31 | Vinay Gupta | 47/4 | DA+3 | 0 | 2025-08-06 | 2025-08-06 | [5 empty] | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | [40 empty] | 38.8 | Completed
32 | Satyam Enterprises | 44/9 | DA+9 | 0 | Sandy | 2025-08-17 | [16 empty] | 5.898 | 5.898 | 5.898 | 5.898 | 5.898 | 5.898 | 5.898 | 5.898 | [38 empty] | 47.184 | Completed
33 | Pusplata (Kailash) | 30/6 | DA+0 | 0 | DRY | 2025-08-17 | [16 empty] | 7.5009 | 7.5009 | 7.5009 | 7.5009 | 7.5009 | [41 empty] | 37.5044 | Completed
34 | Jwala Singh | 28/2 | DA+0 | 0 | DFR | 2025-08-19 | [18 empty] | 5.3578 | 5.3578 | 5.3578 | 5.3578 | 5.3578 | 5.3578 | 5.3578 | [37 empty] | 37.5044 | Completed
35 | Vinay Construction | 47/3 | DA+9 | 0 | Sandy | 2025-08-17 | [16 empty] | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | [33 empty] | 47.184 | Completed
36 | Rahul Kumar | 40/2 | DA+3 | 0 | Sandy | 2025-08-18 | [17 empty] | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | [38 empty] | 38.8 | Completed
37 | Pusplata | 18/0 | DC2+0 | 0 | DRY | 2025-08-18 | [17 empty] | 8.2976 | 8.2976 | 8.2976 | 8.2976 | 8.2976 | 8.2976 | 8.2976 | 8.2976 | [37 empty] | 66.381 | Completed
38 | Pusplata (Dharamveer) | 27/1 | DA+3 | 0 | DFR | 2025-08-16 | [15 empty] | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | [39 empty] | 38.8 | Completed
39 | Jirwa Devi | 52/3 | DA+9 | 0 | Sandy | 2025-08-17 | [16 empty] | 3.3703 | 3.3703 | 3.3703 | 3.3703 | 3.3703 | 3.3703 | 3.3703 | [39 empty] | 23.592 | Completed
40 | Sunny Construction | 55/1 | DA+0 | 0 | WFR | 2025-08-17 | [16 empty] | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | [38 empty] | 37.5044 | Completed
41 | Chinta Devi | 44/11 | DA+0 | 0 | Sandy | 2025-08-19 | [18 empty] | 5.3578 | 5.3578 | 5.3578 | 5.3578 | 5.3578 | 5.3578 | 5.3578 | [37 empty] | 37.5044 | Completed
42 | Pusplata (Ashok) | 4/4 | DA+0 | 0 | DRY | 2025-08-20 | [19 empty] | 6.2507 | 6.2507 | 6.2507 | 6.2507 | 6.2507 | 6.2507 | [37 empty] | 37.5044 | Completed
43 | Sobha Devi | 57/2 | DA+3 | 0 | DRY | 2025-08-21 | [20 empty] | 7.76 | 7.76 | 7.76 | 7.76 | 7.76 | [37 empty] | 38.8 | Completed
44 | 45895 | 31/1 | DA+0 | 0 | DRY | 2025-08-22 | [21 empty] | 7.5009 | 7.5009 | 7.5009 | 7.5009 | 7.5009 | [36 empty] | 37.5044 | Completed
45 | 45898 | 57/1 | DA+0 | 0 | Sandy | 2025-08-21 | [20 empty] | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | [33 empty] | 37.5044 | Completed
46 | 45899 | 30/1 | DA+0 | 0 | Sandy | 2025-08-25 | [24 empty] | 6.2507 | 6.2507 | 6.2507 | 6.2507 | 6.2507 | 6.2507 | [32 empty] | 37.5044 | Completed
47 | 45899 | 43/10 | DA+3 | 0 | Sandy | 2025-08-25 | [24 empty] | 6.4667 | 6.4667 | 6.4667 | 6.4667 | 6.4667 | 6.4667 | [32 empty] | 38.8 | Completed
48 | 45899 | 36/2 | DA+0 | 0 | Sandy | 2025-08-22 | [21 empty] | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | [32 empty] | 37.5044 | Completed
49 | 45900 | 8/1 | DA+3 | 0 | DRY | 2025-08-23 | [22 empty] | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | [31 empty] | 38.8 | Completed
50 | 45900 | 54/5 | DA+9 | 0 | Sandy | 2025-08-17 | [16 empty] | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | [31 empty] | 47.184 | Completed
51 | 45900 | 4/3 | DA+0 | 0 | DRY | 2025-08-29 | [28 empty] | 12.5015 | 12.5015 | 12.5015 | [31 empty] | 37.5044 | Completed
52 | 45900 | 45/1 | DA+9 | 0 | Sandy | 2025-08-25 | [24 empty] | 6.7406 | 6.7406 | 6.7406 | 6.7406 | 6.7406 | 6.7406 | 6.7406 | [31 empty] | 47.184 | Completed
1 | 45903 | 14A/0 | DC1+0 | 0 | DRY | 2025-08-26 | [25 empty] | 7.3757 | 7.3757 | 7.3757 | 7.3757 | 7.3757 | 7.3757 | 7.3757 | 7.3757 | 7.3757 | [28 empty] | 66.381 | Completed
2 | 45903 | 20/3 | DA+0 | 0 | DRY | 2025-08-26 | [25 empty] | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | [28 empty] | 37.5044 | Completed
3 | 45902 | 31/2 | DA+0 | 0 | DRY | 2025-08-26 | [25 empty] | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | [29 empty] | 37.5044 | Completed
4 | 45903 | 27/0 | DC1+0 | 0 | DFR | 2025-08-23 | [22 empty] | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | [28 empty] | 66.381 | Completed
5 | 45903 | 43/5 | DA+3 | 0 | DRY | 2025-08-29 | [28 empty] | 9.1 | 10.1 | 9.1 |  |  | 10.5 | [28 empty] | 38.8 | Completed
6 | 45904 | 8/4 | DA+3 | 0 | DRY | 2025-08-29 | [28 empty] | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | [27 empty] | 38.8 | Completed
7 | 45905 | 21/0 | DB2+0 | 0 | DRY | 2025-09-02 | [32 empty] | 14.3993 | 14.3993 | 14.3993 | 14.3993 | [26 empty] | 57.5972 | Completed
8 | 45906 | 36/3 | DA+0 | 0 | Sandy | 2025-08-30 | [31 empty] | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | [23 empty] | 37.5044 | Completed
9 | 45906 | 47/6 | DA+3 | 0 | Sandy | 2025-08-22 | [21 empty] | 3.5 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 3.15 | 2.3 | [25 empty] | 38.85 | Completed
10 | 45906 | 54/4 | DA+9 | 0 | Sandy | 2025-09-01 | [31 empty] | 7.8641 | 7.8641 | 7.8641 | 7.8641 | 7.8641 | 7.8641 | [25 empty] | 47.1844 | Completed
11 | 45906 | 26/0 | DB1+0 | 0 | DFR | 2025-08-26 | [25 empty] | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | [25 empty] | 57.5972 | Completed
12 | 45907 | 47/1 | DA+3 | 0 | Sandy | 2025-09-01 | [31 empty] | 5.5497 | 5.5497 | 5.5497 | 5.5497 | 5.5497 | 5.5497 | 5.5497 | [24 empty] | 38.8476 | Completed
13 | 45907 | 20/2 | DA+0 | 0 | DRY | 2025-09-02 | [32 empty] | 6.2507 | 6.2507 | 6.2507 | 6.2507 | 6.2507 | 6.2507 | [24 empty] | 37.5044 | Completed
14 | 45907 | 24/0 | DD45+3 | 0 | DRY | 2025-08-26 | [25 empty] | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | [24 empty] | 89.9096 | Completed
15 | 45909 | 2/4 | DA+3 | 0 | Sandy | 2025-08-24 | [23 empty] | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | [22 empty] | 38.8476 | Completed
16 | 45909 | 2/6 | DA+3 | 0 | Sandy | 2025-08-24 | [23 empty] | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | [22 empty] | 38.8476 | Completed
17 | 45910 | 32/1 | DA+3 | 0 | Sandy | 2025-09-03 | [33 empty] | 4.856 | 4.856 | 4.856 | 4.856 | 4.856 | 4.856 | 4.856 | 4.856 | [21 empty] | 38.8476 | Completed
18 | 45910 | 52/4 | DA+9 | 0 | Sandy | 2025-09-01 | [31 empty] | 4.7184 | 4.7184 | 4.7184 | 4.7184 | 4.7184 | 4.7184 | 4.7184 | 4.7184 | 4.7184 | 4.7184 | [21 empty] | 47.1844 | Completed
19 | 45911 | 34/3 | DA+0 | 0 | Sandy | 2025-09-03 | [33 empty] | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | [20 empty] | 37.5044 | Completed
20 | 45912 | 21/4 | DA+3 | 0 | Sandy | 2025-09-09 | [39 empty] | 9.7119 | 9.7119 | 9.7119 | 9.7119 | [19 empty] | 38.8476 | Completed
21 | 45912 | 28/0 | DB2+0 | 0 | DFR | 2025-09-03 | [33 empty] | 4.3 | 3.6 | 2.9 | 4.1 | 1.2 | 1.1 | 10.1 | 10.3 | 9.9 | 10.1 | [19 empty] | 57.6 | Completed
22 | 45912 | 6/2 | DA+0 | 0 | DFR | 2025-09-05 | [37 empty] | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | [19 empty] | 37.5 | Completed
23 | 45912 | 54/3 | DA+6 | 0 | Sandy | 2025-09-07 | [37 empty] | 7.5688 | 7.5688 | 7.5688 | 7.5688 | 7.5688 | 7.5688 | [19 empty] | 45.413 | Completed
24 | 45913 | 2/1 | DA+3 | 0 | Sandy | 2025-09-03 | [33 empty] | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | [18 empty] | 38.8476 | Completed
25 | 45914 | 56/0 | DD60+25 | 0 | Sandy | 2025-08-30 | [29 empty] | 8.9 | 8.9 | 8.9 | 8.9 | 8.9 | 8.2 | 8.9 | 9.2 | 10.4 | 10.6 | 10.6 | 10.6 | 10.6 | 10.6 | 8.9 | [18 empty] | 143.1 | Completed
26 | 45916 | 26/1 | DA+0 | 0 | DRY | 2025-09-07 | [38 empty] | 1.2 | 1.3 | 1.5 | 1.3 | 1.1 | 2.1 | 9 | 10.1 | 9.9 | [15 empty] | 37.5 | Completed
27 | 45920 | 52/2 | DA+6 | 0 | Sandy | 2025-09-10 | [40 empty] | 5.7 | 6.2 |  |  | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.5985 | 6.2 | 6.2 | [11 empty] | 45.4123 | Completed
28 | 45918 | 54/1 | DA+3 | 0 | Sandy | 2025-09-13 | [42 empty] | 6.47 |  | 6.4746 | 6.4746 | 6.4746 | 6.4746 | 6.4746 | [13 empty] | 38.843 | Completed
29 | 45925 | 47/0 | DD60+25 | 0 | Sandy | 2025-09-09 | [39 empty] | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | [6 empty] | 143.1 | Completed
30 | 45916 | 36/4 | DA+6 | 0 | Sandy | 2025-09-07 | [37 empty] | 3.9 | 4.9 | 4.6 | 4.2 | 5.1 | 5.2 | 5.6 | 4.5413 | 4.5413 | 2.8313 | [15 empty] | 45.4139 | Completed
31 | 45929 | 47/5 | DA+0 | 0 | Sandy | 2025-09-07 | [37 empty] | 2.9 | 3.9 | [16 empty] | 6.35 | 5.1 | 6.4176 | 6.4176 | 6.4176 |  |  | 37.5029 | Completed
32 | 45926 | 27/11 | DA+3 | 0 | DRY | 2025-08-29 | [17 empty] | 4.3 | [10 empty] | 4.6 | 5.1 | 4.5 | 6.6 | 5.2 | [16 empty] | 4.5 | [6 empty] | 4 | [5 empty] | 38.8 | Completed
33 | 45916 | 36/1 | DA+3 | 0 | Sandy | 2025-08-29 | [31 empty] | 3.2 | 3.2 | 3.2 |  | 3.2 | 3.2 | 3.2 | 4.1 | 4.3 | 3.9 | 5.1 | 4.8 | 4.2 | 2.0446 | 2.0446 | 2.0446 | [15 empty] | 51.7338 | Completed
34 | 45922 | 2/2 | DA+3 | 0 | Sandy | 2025-09-09 | [39 empty] | 2.1 | 2.9 | 3.1 | 3.5 | 3.3 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 1.7448 | [9 empty] | 38.8435 | Completed
35 | 45922 | 43/3 | DA+0 | 0 | DRY | 2025-09-09 | [39 empty] | 2.1 | 2.9 | 3.1 | 3.5 | 3.3 | 2.6789 | 2.6789 | 2.1 | 2.1 | 2.1 | 2.6789 | 2.6789 | 2.6789 | 2.9 | [9 empty] | 37.4944 | Completed
36 | 45930 | 21/3 | DA+6 | 0 | Sandy | 2025-09-10 | [39 empty] | 2.6 | 2.8 |  |  |  | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 |  | 3.02 | 3.61 | 3.1 | 3.4 | 3.1 |  | 45.4178 | Completed
37 | 45918 | 8/5 | DA+3 | 0 | DRY | 2025-09-12 | [42 empty] | 2.9 | 4.1 | 6.5 | 6.7 | 6.4 | 6.7 | 5.5497 | [13 empty] | 38.8497 | Completed
38 | 45923 | 8/2 | DA+3 | 0 | DRY | 2025-09-12 | [42 empty] | 2.6 | 3.1 | 3.2373 | 3.2373 | 3.2373 | 3.2373 | 3.2373 | 3.2373 | 3.2373 | 3.2373 | 3.2373 | 4.0073 | [8 empty] | 38.843 | Completed
39 | 45922 | 21/5 | DA+6 | 0 | DFR | 2025-09-19 | [49 empty] | 11.3533 | 11.3533 | 11.3533 | 11.3533 | [9 empty] | 45.413 | Completed
40 | 45922 | 54/2 | DA+3 | 0 | Sandy | 2025-09-19 | [49 empty] | 9.7119 | 9.7119 | 9.7119 | 9.7119 | [9 empty] | 38.8476 | Completed
41 | 45923 | 29/3 | DA+0 | 0 | Sandy | 2025-09-10 | [40 empty] | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 |  |  |  | 2.5 | [8 empty] | 37.5 | Completed
42 | 45927 | 36/0 | DB2+0 | 0 | Sandy | 2025-09-16 | [46 empty] | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 |  |  |  |  | 57.5972 | Completed
43 | 45927 | 37/0 | DB2+0 | 0 | Sandy | 2025-09-16 | [46 empty] | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 |  |  |  |  | 57.5972 | Completed
44 | 45929 | 20/0 | DB2+0 | 0 | Sandy | 2025-09-20 | [50 empty] | 5.76 | 5.76 | 5.76 | 5.76 | 5.76 | 5.76 | 5.76 | 5.76 | 5.76 | 5.76 |  |  | 57.6 | Completed
45 | 45929 | 57/0 | DD60+25 | 0 | Sandy | 2025-09-15 | [45 empty] | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 |  |  | 143.6019 | Completed
46 | 45930 | 52/1 | DA+6 | 0 | Sandy | 2025-09-20 | [50 empty] | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 |  | 45.413 | Completed
47 | 45930 | 54/0 | DB1+6 | 0 | Sandy | 2025-09-22 | [52 empty] | 7.5415 | 7.5415 | 7.5415 | 7.5415 | 7.5415 | 7.5415 | 7.5415 | 7.5415 | 7.5415 |  | 67.8737 | Completed
48 | Shobha Devi | 40/0 | DC2+0 | 66.3811 | 2025-09-29 | WIP | [60 empty] | 3.2 |  | 3.2 | WIP
49 | Vinay Construction/ Chinta Devi | 46/0 | DD60+25 | 143.6019 | 2025-09-29 | WIP | [60 empty] | 2.9 |  | 2.9 | WIP
50 | Nirmal Mahto | 35/5 | DA+0 | 37.5 | 2025-09-27 | WIP | [57 empty] | 1.8 | 2.1 | 2.3 | 2.3 |  | 8.5 | WIP
51 | Vivek Ganju | 42/6 | DA+0 | 37.5 | 2025-09-22 | WIP | [52 empty] | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 |  | 26.1 | WIP
52 | Sheetal Singh-1 | 6/1 | DA+0 | 37.5 | 2025-09-25 | WIP | [55 empty] | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 |  | 30.6 | WIP
53 | Priyanka Devi (Sontosh) | 21/10 | DA+6 | 45.413 | 2025-09-29 | WIP | [60 empty] | 1.8 |  | 1.8 | WIP
Total |  |  |  | 367.896 |  |  | 65.8627 | 68.9627 | 67.4627 | 72.8341 | 71.8341 | 63.2815 | 62.0815 | 63.4815 | 70.9927 | 65.9427 | 68.4427 | 80.1855 | 88.5522 | 76.7522 | 44.0522 | 83.1022 | 94.4345 | 85.8774 | 80.9834 | 78.7341 | 79.6613 | 87.3284 | 92.1263 | 88.4763 | 91.8053 | 86.7282 | 79.2273 | 79.2273 | 110.9717 | 113.575 | 95.0904 | 87.4119 | 106.6619 | 124.1286 | 91.954 | 90.4611 | 76.7118 | 80.6668 | 66.1503 | 91.4918 | 97.5215 | 87.5471 | 89.75 | 50.0492 | 55.4602 | 66.3336 | 73.1443 | 58.6684 | 57.988 | 73.7093 | 75.5978 | 69.3978 | 79.0304 | 56.5904 | 50.0831 | 59.3706 | 56.723 | 56.4306 | 46.6211 | 47.1211 | 32.97 | 0 | 4613.816
Formulas:
Aug'25 = +VLOOKUP([Unit],'Erection Compiled'!$C189:G309,4,FALSE)
Note on AM66: Raghav Ranjan: No work done due to ROW at 47/5.
Note on AN66: Raghav Ranjan: No work done due to ROW at 47/5.
Note on AO82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on AP82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on AQ82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on AR82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on AS82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on AT82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on AT87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AU87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AV87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AW87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AX87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AY87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AU92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AV92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AW92: Raghav Ranjan: No work done due to less manpower
Note on AX92: Raghav Ranjan: No work done due to less manpower
Note on AY92: Raghav Ranjan: No work done due to less manpower
Note on AZ92: Raghav Ranjan: No work done due to less manpower
Note on BA92: Raghav Ranjan: No work done due to less manpower
Note on BB92: Raghav Ranjan: No work done due to less manpower
Note on BC92: Raghav Ranjan: No work done due to less manpower
Note on BD92: Raghav Ranjan: No work done due to less manpower
Note on BE92: Raghav Ranjan: No work done due to less manpower
Note on BF92: Raghav Ranjan: No work done due to less manpower
Note on BG92: Raghav Ranjan: No work done due to less manpower
Note on BH92: Raghav Ranjan: No work done due to less manpower
Note on BI92: Raghav Ranjan: No work done due to less manpower
Note on BJ92: Raghav Ranjan: No work done due to less manpower
Note on AO93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AP93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AQ93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AR93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AS93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AT93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AU93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AV93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AW93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AX93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AY93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AZ93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BA93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BB93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BC93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BD93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on BF93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BG93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BH93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BI93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BJ93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BK93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AP94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done.
Note on AW97: Raghav Ranjan: No work done due to less manpower
Note on AX97: Raghav Ranjan: No work done due to less manpower
Note on AY97: Raghav Ranjan: No work done due to less manpower
Note on BK97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW

## Crane Erection Productivity (hidden)
Sr No | Locs | TOT | Crane Using | [5 empty] | Manual Erection
|  |  | Start Date | Complete Date | No of Days | Weight in MT | Gang | Manpower | Start Date | Complete Date | No of Days | Weight in MT | Manpower | Gangs
1 | 1A/4 | DA+3 | 2025-05-10 | 2025-05-14 | 5 | 14.78 | Bhairo Mahto (Departmental) | 42 | 2025-06-04 | 2025-06-11 | 8 | 24.0676 | 30 | Bhairo Mahto (Departmental) | 38.8476
2 | 1A/6 | DA+0 | 2025-05-28 | 2025-05-31 | 4 | 14.875 | Bhairo Mahto (Departmental) | 42 | 2025-06-12 | 2025-06-20 | 9 | 22.6294 | 30 | Bhairo Mahto (Departmental) | 37.5044
3 | 1A/7 | DA+3 | 2025-06-05 | 2025-06-08 | 4 | 14.78 | Anil Kumar | 42 | 2025-06-23 | 2025-06-30 | 8 | 24.068 | 30 | Kewat (Departmental) | 38.848
4 | 1A/8 | DA+0 | 2025-06-12 | 2025-06-16 | 5 | 14.875 | Anil Kumar | 42 | 2025-07-09 | 2025-07-15 | 7 | 22.625 | 20 | Kewat (Departmental) | 37.5
5 | 1A/0 | DD60+0 | 2025-07-01 | 2025-07-07 | 7 | 41.773 | Bhairo Mahto (Departmental) |  | 2025-07-23 | 2025-07-29 | 7 | 44.3563 | 28 | Priyanka Devi (Subodh) | 86.1293
6 | 1/0 | DD60+0 | 2025-07-07 | 2025-07-11 | 5 | 41.773 | Bhairo Mahto (Departmental) |  | 2025-08-02 | 2025-08-20 | 19 | 44.3563 | 28 | Kewat (Departmental) | 86.1293
7 | 1A/5 | DA+0 | 2025-07-10 |  |  | 14.875 | Bhairo Mahto (Departmental) | 38 | 2025-07-16 | 2025-07-26 | 11 | 22.625 | 20 | Kewat (Departmental) | 37.5
8 | 4/1 | DA+0 | 2025-07-25 | 2025-07-29 | 5 | 14.875 | Bhairo Mahto (Departmental) |  | 2025-08-06 | 2025-08-09 | 4 | 22.625 | 30 | Bhairo Mahto (Departmental) | 37.5
9 | 4/2 | DA+0 | 2025-07-30
Total Weight/Days |  |  |  |  | 35 | 172.606 |  |  |  |  | 73 | 227.3525
Total Average Weight/Days | [5 empty] | 4.9316 | [5 empty] | 3.1144
113.7
59.224
Formulas:
No of Days = +DAYS([Complete Date],[Crane Using])+1

## Erection Compiled
Progress Summary'!A1 | [7 empty] | Total As per LOA | 22212.28
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line | [7 empty] | Total Executed | 21017.6569
List of Completed Erection | [7 empty] | Balance | 1194.6231 | 25.9701
SL No. | Month Sl.No. | Location No. | Tower Type | Classification | Starting Date | Completion Date | Gang Name | Gang Strength | Tower Weight | Status
1 | 2024-02-01 | 60/7 | DA+3 | DRY | 2024-01-28 | 2024-02-04 | Suraj const |  | 38.8476 |  |  | 7 | DA+0 | 37.5044
2 | 2024-02-01 | 59/13 | DA+3 | DRY | 2024-02-01 | 2024-02-07 | Chinta Devi |  | 38.8476 |  |  | 6 | DA+3 | 38.8476
3 | 2024-02-01 | 63/6 | DA+3 | DRY | 2024-02-03 | 2024-02-10 | Sunny Const. |  | 38.8476 |  |  | 7 | DA+6 | 45.413
4 | 2024-02-01 | 59/5 | DA+3 | DFR | 2024-02-05 | 2024-02-11 | Ganesh Const |  | 38.8476 |  |  | 6 | DA+9 | 47.1844 | 2nd Section WIP.
5 | 2024-02-01 | 59/14 | DA+6 | DRY | 2024-02-08 | 2024-02-13 | Chinta Devi |  | 45.413 |  |  | 5 | DB1+0 | 57.5972
6 | 2024-02-01 | 60/8 | DA+0 | DRY | 2024-02-09 | 2024-02-15 | Suraj const |  | 37.5044 |  |  | 6 | DB1+3 | 60.0968
7 | 2024-02-01 | 63/7 | DA+3 | DRY | 2024-02-11 | 2024-02-15 | Sunny Const. |  | 38.8476 |  |  | 4 | DB1+6 | 67.8737
8 | 2024-02-01 | 59/6 | DA+3 | DFR | 2024-02-12 | 2024-02-18 | Ganesh Const |  | 38.8476 |  |  | 6 | DB1+9 | 70.7017
9 | 2024-02-01 | 59/12 | DA+6 | DFR | 2024-02-13 | 2024-02-20 | Chinta Devi |  | 45.413 |  |  | 7 | DB2+0 | 57.5972
10 | 2024-02-01 | 63/8 | DA+3 | DRY | 2024-02-15 | 2024-02-20 | Sunny Const. |  | 38.8476 |  |  | 5 | DB2+3 | 60.0968
11 | 2024-02-01 | 60/10 | DA+0 | DFR | 2024-02-15 | 2024-02-21 | Suraj const |  | 37.5044 |  |  | 6 | DB2+6 | 67.8737
12 | 2024-02-01 | 62/5 | DA+0 | DRY | 2024-02-17 | 2024-02-22 | Sobha Devi |  | 37.5044 |  |  | 5 | DB2+9 | 70.7017
13 | 2024-02-01 | 59/7 | DA+3 | DRY | 2024-02-18 | 2024-02-24 | Ganesh Const |  | 38.8476 |  |  | 6 | DC1+0 | 66.3811
14 | 2024-02-01 | 59/10 | DA+0 | DRY | 2024-02-20 | 2024-02-24 | Chinta Devi |  | 37.5044 |  |  | 4 | DCT+0 | 94.2199
15 | 2024-02-01 | 64/1 | DA+0 | DRY | 2024-02-20 | 2024-02-24 | Sunny Const. |  | 37.5044 |  |  | 4 | DC1+3 | 69.2287
16 | 2024-02-01 | 60/11 | DA+3 | DRY | 2024-02-21 | 2024-02-26 | Suraj const |  | 38.8476 |  |  | 5 | DC1+6 | 78.132
17 | 2024-02-01 | 62/4 | DA+3 | DRY | 2024-02-22 | 2024-02-26 | Sobha Devi |  | 38.8476 |  |  | 4 | DC1+9 | 81.4946
18 | 2024-02-01 | 59/9 | DA+3 | DRY | 2024-02-24 | 2024-02-28 | Chinta Devi |  | 38.8476 |  |  | 4 | DC2+0 | 66.3811
19 | 2024-02-01 | 62/3 | DA+0 | DRY | 2024-02-26 | 2024-02-28 | Sobha Devi |  | 37.5044 |  |  | 2 | DC2+3 | 69.2287
20 | 2024-02-01 | 59/8 | DB1+3 | DRY | 2024-02-24 | 2024-02-29 | Ganesh Const |  | 60.0968 |  |  | 5 | DC2+6 | 78.132
21 | 2024-02-01 | 64/4 | DA+3 | DRY | 2024-02-24 | 2024-02-29 | Sunny Const. |  | 38.8476 |  |  | 5 | DC2+9 | 81.4946
22 | 2024-02-01 | 60/6 | DA+0 | DRY | 2024-02-26 | 2024-02-29 | Suraj const |  | 37.5044 |  |  | 3 | DD45+0 | 86.1293
23 | 2024-03-01 | 62/2 | DA+3 | DRY | 2024-02-29 | 2024-03-03 | Sobha Devi |  | 38.8476 |  |  | 3 | DD45+3 | 89.9096
24 | 2024-03-01 | 64/5 | DA+3 | DRY | 2024-02-29 | 2024-03-04 | Sunny Const. |  | 38.8476 |  |  | 4 | DD60+0 | 86.1293
25 | 2024-03-01 | 65/2 | DA+0 | DRY | 2024-02-29 | 2024-03-06 | Chinta Devi |  | 37.5044 |  |  | 6 | DD60+3 | 89.9096
26 | 2024-03-01 | 62/7 | DA+3 | DRY | 2024-03-04 | 2024-03-07 | Sobha Devi |  | 38.8476 |  |  | 3 | DD60+6 | 100.968
27 | 2024-03-01 | 59/16 | DA+9 | Dry | 2024-02-29 | 2024-03-11 | Ganesh Const. |  | 47.1844 |  |  | 11 | DD60+9 | 105.0682
28 | 2024-03-01 | 65/4 | DA+0 | DRY | 2024-03-06 | 2024-03-11 | Chinta Devi |  | 37.5044 |  |  | 5 | DD60+18 | 129.111
29 | 2024-03-01 | 62/8 | DA+0 | DFR | 2024-03-07 | 2024-03-11 | Sobha Devi |  | 37.5044 |  |  | 4 | DD60+25 | 143.6019
30 | 2024-03-01 | 62/9 | DA+3 | DFR | 2024-03-11 | 2024-03-15 | Sobha Devi |  | 38.8476 |  |  | 4
31 | 2024-03-01 | 65/3 | DA+3 | DRY | 2024-03-11 | 2024-03-16 | Chinta Devi |  | 38.8476 |  |  | 5
32 | 2024-03-01 | 60/5 | DA+3 | DRY | 2024-03-11 | 2024-03-17 | Ganesh Const. |  | 38.8476 |  |  | 6
33 | 2024-03-01 | 62/10 | DA+0 | DFR | 2024-03-15 | 2024-03-18 | Sobha Devi |  | 37.5044 |  |  | 3
34 | 2024-03-01 | 65/5 | DA+0 | DRY | 2024-03-16 | 2024-03-20 | Chinta Devi |  | 37.5044 |  |  | 4
35 | 2024-03-01 | 61/6 | DA+3 | DRY | 2024-03-18 | 2024-03-22 | Sobha Devi |  | 38.8476 |  |  | 4
36 | 2024-03-01 | 60/4 | DA+3 | DFR | 2024-03-18 | 2024-03-23 | Ganesh Const. |  | 38.8476 |  |  | 5
37 | 2024-03-01 | 65/6 | DA+0 | DRY | 2024-03-20 | 2024-03-26 | Chinta Devi |  | 37.5044 |  |  | 6
38 | 2024-03-01 | 64/6 | DA+0 | DRY | 2024-03-21 | 2024-03-26 | Sunny Const. |  | 37.5044 |  |  | 5
39 | 2024-03-01 | 61/7 | DA+9 | Dry | 2024-03-22 | 2024-03-28 | Sobha Devi |  | 47.1844 |  |  | 6
40 | 2024-03-01 | 64/7 | DA+3 | DRY | 2024-03-26 | 2024-03-30 | Sunny Const. |  | 38.8476 |  |  | 4
41 | 2024-03-01 | 60/3 | DA+3 | DFR | 2024-03-23 | 2024-03-31 | Ganesh Const. |  | 38.8476 |  |  | 8
42 | 2024-03-01 | 65/9 | DA+0 | DRY | 2024-03-26 | 2024-03-31 | Chinta Devi |  | 37.5044 |  |  | 5
43 | 2024-04-01 | 64/8 | DA+3 | DRY | 2024-03-30 | 2024-04-03 | Sunny Const. |  | 38.8476 |  |  | 4
44 | 2024-04-01 | 65/11 | DA+0 | DRY | 2024-03-31 | 2024-04-04 | Chinta Devi |  | 37.5044 |  |  | 4
45 | 2024-04-01 | 60/2 | DA+3 | DFR | 2024-03-31 | 2024-04-07 | Ganesh Const. |  | 38.8476 |  |  | 7
46 | 2024-04-01 | 63/5 | DA+3 | DFR | 2024-04-01 | 2024-04-07 | Suraj Const |  | 38.8476 |  |  | 6
47 | 2024-04-01 | 64/9 | DA+3 | DRY | 2024-04-03 | 2024-04-08 | Sunny Const. |  | 38.8476 |  |  | 5
48 | 2024-04-01 | 67/1 | DA+0 | DRY | 2024-04-06 | 2024-04-10 | Chinta Devi |  | 37.5044 |  |  | 4
49 | 2024-04-01 | 61/0 | DB2+0 | DRY | 2024-04-06 | 2024-04-11 | Sobha Devi |  | 57.5972 |  |  | 5
50 | 2024-04-01 | 63/4 | DA+0 | DRY | 2024-04-07 | 2024-04-13 | Suraj Const |  | 37.5044 |  |  | 6
51 | 2024-04-01 | 67/2 | DA+0 | DRY | 2024-04-10 | 2024-04-15 | Chinta Devi |  | 37.5044 |  |  | 5
52 | 2024-04-01 | 63/3 | DA+3 | DFR | 2024-04-13 | 2024-04-17 | Suraj Const |  | 38.8476 |  |  | 4
53 | 2024-04-01 | 64/10 | DA+3 | DRY | 2024-04-15 | 2024-04-20 | Chinta Devi |  | 38.8476 |  |  | 5
54 | 2024-04-01 | 64/2 | DA+3 | DRY | 2024-04-16 | 2024-04-21 | Sunny Const. |  | 38.8476 |  |  | 5
55 | 2024-04-01 | 61/2 | DA+6 | DFR | 2024-04-16 | 2024-04-22 | Sobha Devi |  | 45.413 |  |  | 6
56 | 2024-04-01 | 63/2 | DA+0 | DFR | 2024-04-17 | 2024-04-22 | Suraj const |  | 37.5044 |  |  | 5
57 | 2024-04-01 | 60/1 | DA+6 | DRY | 2024-04-18 | 2024-04-25 | Ganesh Const. |  | 45.413 |  |  | 7
58 | 2024-04-01 | 64/3 | DA+0 | DRY | 2024-04-21 | 2024-04-26 | Sunny Const. |  | 37.5044 |  |  | 5
59 | 2024-04-01 | 65/0 | DB1+0 | DRY | 2024-04-21 | 2024-04-27 | Chinta Devi |  | 57.5972 |  |  | 6
60 | 2024-04-01 | 63/1 | DA+3 | DFR | 2024-04-22 | 2024-04-27 | Suraj const |  | 38.8476 |  |  | 5
61 | 2024-04-01 | 61/1 | DA+6 | DFR | 2024-04-22 | 2024-04-29 | Sobha Devi |  | 45.413 |  |  | 7
62 | 2024-05-01 | 65/1 | DA+0 | DRY | 2024-04-27 | 2024-05-03 | Chinta Devi |  | 37.5044 |  |  | 6
63 | 2024-05-01 | 62/11 | DA+3 | DRY | 2024-04-27 | 2024-05-03 | Suraj const |  | 38.8476 |  |  | 6
64 | 2024-05-01 | 64/0 | DB2+0 | DRY | 2024-04-27 | 2024-05-05 | Sunny Const. |  | 57.5972 |  |  | 8
65 | 2024-05-01 | 60/9 | DA+3 | DRY | 2024-04-29 | 2024-05-05 | Sobha Devi |  | 38.8476 |  |  | 6
66 | 2024-05-01 | 61/3 | DA+6 | DRY | 2024-05-05 | 2024-05-11 | Sobha Devi |  | 45.413 |  |  | 6
67 | 2024-05-01 | 63/0 | DC1+0 | DFR | 2024-05-03 | 2024-05-12 | Suraj const |  | 66.3811 |  |  | 9
68 | 2024-05-01 | 61/4 | DA+3 | DRY | 2024-05-11 | 2024-05-16 | Sobha Devi |  | 38.8476 |  |  | 5
69 | 2024-05-01 | 60/0 | DC1+0 | DRY | 2024-05-05 | 2024-05-18 | Ganesh |  | 66.3811 |  |  | 13
70 | 2024-05-01 | 61/10 | DA+9 | DRY | 2024-05-12 | 2024-05-19 | Suraj const |  | 47.1844 |  |  | 7
71 | 2024-05-01 | 61/5 | DA+3 | DRY | 2024-05-16 | 2024-05-22 | Sobha Devi |  | 38.8476 |  |  | 6
72 | 2024-05-01 | 61/9 | DA+0 | Dry | 2024-05-19 | 2024-05-23 | Suraj const |  | 37.5044 |  |  | 4
73 | 2024-05-01 | 59/15 | DA+6 | DRY | 2024-05-18 | 2024-05-30 | Ganesh |  | 45.413 |  |  | 12
74 | 2024-05-01 | 61/8 | DA+6 | DRY | 2024-05-23 | 2024-05-30 | Suraj const |  | 45.413 |  |  | 7
75 | 2024-05-01 | 55/3 | DA+0 | Sandy | 2024-05-12 | 2024-05-31 | Mansukh lal |  | 37.5044 |  |  | 19
76 | 2024-06-01 | 57/3 | DA+0 | DRY | 2024-05-29 | 2024-06-11 | Bhuvneshwar |  | 37.5044 |  |  | 13
77 | 2024-06-01 | 55/4 | DA+0 | Sandy | 2024-06-01 | 2024-06-19 | Mansukh lal |  | 37.5044 |  |  | 18
78 | 2024-06-01 | 57/4 | DA+0 | Sandy | 2024-06-12 | 2024-06-27 | Bhuvneshwar |  | 37.5044 |  |  | 15
79 | 2024-07-01 | 62/1 | DA+3 | Sandy | 2024-07-04 | 2024-07-12 | Bhuvneshwar |  | 38.8476 |  |  | 8
80 | 2024-07-01 | 62/6 | DA+3 | DRY | 2024-07-15 | 2024-07-26 | Bhuvneshwar |  | 38.8476 |  |  | 11
81 | 2024-08-01 | 57/6 | DA+3 | Sandy | 2024-08-13 | 2024-08-20 | Sobha devi |  | 38.8476 |  |  | 7
82 | 2024-08-01 | 57/5 | DA+3 | Sandy | 2024-08-20 | 2024-08-26 | Sobha devi |  | 38.8476 |  |  | 6
83 | 2024-08-01 | 10/18 | DA+3 | DFR | 2024-08-23 | 2024-08-30 | Yogendra Mahto |  | 38.8476 |  |  | 7
84 | 2024-09-01 | 10/3 | DA+0 | DFR | 2024-08-28 | 2024-09-06 | Jagdish Mahto |  | 37.5044 |  |  | 9
85 | 2024-09-01 | 10/17 | DA+3 | DFR | 2024-08-30 | 2024-09-08 | Yogendra Mahto |  | 38.8476 |  |  | 9
86 | 2024-09-01 | 62/0 | DB2+0 | DRY | 2024-08-31 | 2024-09-08 | Sobha devi |  | 57.5972 |  |  | 8
87 | 2024-09-01 | 50/9 | DA+0 | Sandy | 2024-08-28 | 2024-09-09 | Uma const |  | 37.5044 |  |  | 12
88 | 2024-09-01 | 16/3 | DA+3 | DRY | 2024-09-06 | 2024-09-13 | Nirmal Mahto |  | 38.8476 |  |  | 7
89 | 2024-09-01 | 10/19 | DA+0 | DRY | 2024-09-09 | 2024-09-18 | Yogendra Mahto |  | 37.5044 |  |  | 9
90 | 2024-09-01 | 52/5 | DA+9 | Sandy | 2024-08-27 | 2024-09-19 | Ganesh Sinha |  | 47.1844 |  |  | 23
91 | 2024-09-01 | 50/10 | DA+0 | Sandy | 2024-09-10 | 2024-09-19 | Uma const |  | 37.5044 |  |  | 9
92 | 2024-09-01 | 18/2 | DA+0 | DRY | 2024-09-18 | 2024-09-22 | Deglal Mahto |  | 37.5044 |  |  | 4
93 | 2024-09-01 | 10/20 | DA+3 | DFR | 2024-09-19 | 2024-09-25 | Yogendra Mahto |  | 38.8476 |  |  | 6
94 | 2024-09-01 | 48/1 | DA+9 | Sandy | 2024-09-08 | 2024-09-25 | Kaushalya const |  | 47.1844 |  |  | 17
95 | 2024-09-01 | 15/1 | DA+3 | DRY | 2024-09-21 | 2024-09-26 | Jailal Ageria |  | 38.8476 |  |  | 5
96 | 2024-09-01 | 51/1 | DA+0 | Sandy | 2024-09-19 | 2024-09-26 | Uma const |  | 37.5044 |  |  | 7
97 | 2024-09-01 | 18/4 | DA+0 | DRY | 2024-09-23 | 2024-09-27 | Deglal Mahto |  | 37.5044 |  |  | 4
98 | 2024-09-01 | 10/6 | DA+0 | DFR | 2024-09-25 | 2024-09-29 | Jagdish Mahto |  | 37.5044 |  |  | 4
99 | 2024-09-01 | 52/6 | DA+6 | Sandy | 2024-09-19 | 2024-09-30 | Ganesh Sinha |  | 45.413 |  |  | 11
100 | 2024-10-01 | 57/7 | DA+3 | DFR | 2024-09-27 | 2024-10-01 | Sobha devi |  | 38.8476 |  |  | 4
101 | 2024-10-01 | 16/4 | DA+0 | DRY | 2024-09-28 | 2024-10-03 | Nirmal Mahto |  | 37.5044 |  |  | 5
102 | 2024-10-01 | 14A/1 | DA+3 | DRY | 2024-09-28 | 2024-10-03 | Jailal Ageria |  | 38.8476 |  |  | 5
103 | 2024-10-01 | 51/2 | DA+0 | Sandy | 2024-09-26 | 2024-10-04 | Uma const |  | 37.5044 |  |  | 8
104 | 2024-10-01 | 10/14 | DA+3 | DRY | 2024-09-27 | 2024-10-06 | Khublal Mahto |  | 38.8476 |  |  | 9
105 | 2024-10-01 | 11A/2 | DA+0 | DRY | 2024-09-27 | 2024-10-07 | Rafikul Islam |  | 37.5044 |  |  | 10
106 | 2024-10-01 | 50/0 | DB2+0 | Sandy | 2024-10-02 | 2024-10-07 | Sobha devi |  | 57.5972 |  |  | 5
107 | 2024-10-01 | 52/7 | DA+3 | Sandy | 2024-10-01 | 2024-10-07 | Ganesh Sinha |  | 38.8476 |  |  | 6
108 | 2024-10-01 | 10/9 | DA+0 | DRY | 2024-10-05 | 2024-10-08 | Jagdish Mahto |  | 37.5044 |  |  | 3
109 | 2024-10-01 | 18/1 | DA+0 | DRY | 2024-10-04 | 2024-10-08 | Deglal Mahto |  | 37.5044 |  |  | 4
110 | 2024-10-01 | 10/21 | DA+3 | DFR | 2024-10-07 | 2024-10-10 | Bina Devi |  | 38.8476 |  |  | 3
111 | 2024-10-01 | 17/1 | DA+3 | DRY | 2024-10-05 | 2024-10-10 | Nirmal Mahto |  | 38.8476 |  |  | 5
112 | 2024-10-01 | 50/1 | DA+6 | Sandy | 2024-10-07 | 2024-10-15 | Sobha Devi |  | 45.413 |  |  | 8
113 | 2024-10-01 | 50/8 | DA+9 | Sandy | 2024-10-07 | 2024-10-16 | Uma const |  | 47.1844 |  |  | 9
114 | 2024-10-01 | 10/4 | DA+3 | DFR | 2024-10-12 | 2024-10-17 | Jagdish Mahto |  | 38.8476 |  |  | 5
115 | 2024-10-01 | 50/3 | DA+6 | Sandy | 2024-10-13 | 2024-10-18 | Sobha Devi |  | 45.413 |  |  | 5
116 | 2024-10-01 | 17/2 | DA+6 | DRY | 2024-10-11 | 2024-10-19 | Nirmal Mahto |  | 45.413 |  |  | 8
117 | 2024-10-01 | 48/0 | DC2+0 | Sandy | 2024-09-28 | 2024-10-19 | Kaushalya const |  | 66.3811 |  |  | 21
118 | 2024-10-01 | 52/8 | DA+6 | Sandy | 2024-10-08 | 2024-10-19 | Ganesh Sinha |  | 45.413 |  |  | 11
119 | 2024-10-01 | 73/2 | DA+0 | DRY | 2024-10-10 | 2024-10-20 | Sanjeev Kumar |  | 37.5044 |  |  | 10
120 | 2024-10-01 | 10/8 | DA+3 | DFR | 2024-10-19 | 2024-10-22 | Jagdish Mahto |  | 38.8476 |  |  | 3
121 | 2024-10-01 | 50/2 | DA+9 | Sandy | 2024-10-18 | 2024-10-24 | Sobha Devi |  | 47.1844 |  |  | 6
122 | 2024-10-01 | 64/11 | DA+3 | DRY | 2024-10-20 | 2024-10-24 | Chinta devi |  | 38.8476 |  |  | 4
123 | 2024-10-01 | 16/2 | DA+0 | DRY | 2024-10-20 | 2024-10-26 | Nirmal Mahto |  | 37.5044 |  |  | 6
124 | 2024-10-01 | 19/0 | DC2+0 | DRY | 2024-10-19 | 2024-10-26 | Deglal Mahto |  | 66.3811 |  |  | 7
125 | 2024-10-01 | 59/11 | DA+6 | DFR | 2024-10-17 | 2024-10-26 | Uma const |  | 45.413 |  |  | 9
126 | 2024-10-01 | 16/0 | DC1+0 | DRY | 2024-10-18 | 2024-10-27 | Jailal Ageria |  | 66.3811 |  |  | 9
127 | 2024-10-01 | 17/3 | DA+0 | DRY | 2024-10-21 | 2024-10-27 | Bina Devi |  | 37.5044 |  |  | 6
128 | 2024-10-01 | 73/1 | DA+0 | DRY | 2024-10-21 | 2024-10-29 | Sanjeev Kumar |  | 37.5044 |  |  | 8
129 | 2024-10-01 | 50/4 | DA+9 | Sandy | 2024-10-24 | 2024-10-30 | Sobha Devi |  | 47.1844 |  |  | 6
130 | 2024-11-01 | 55/6 | DA+0 | Sandy | 2024-10-23 | 2024-11-01 | Jirwa Devi |  | 37.5044 |  |  | 9
131 | 2024-11-01 | 11A/0 | DB1+0 | DRY | 2024-10-16 | 2024-11-02 | Rafikul Islam |  | 57.5972 |  |  | 17
132 | 2024-11-01 | 59/3 | DA+3 | DFR | 2024-10-27 | 2024-11-02 | Uma const |  | 38.8476 |  |  | 6
133 | 2024-11-01 | 50/7 | DA+0 | Sandy | 2024-11-01 | 2024-11-04 | Sobha Devi |  | 37.5044 |  |  | 3
134 | 2024-11-01 | 10/11 | DA+3 | DRY | 2024-11-02 | 2024-11-05 | Jagdish Mahto |  | 38.8476 |  |  | 3
135 | 2024-11-01 | 11A/1 | DA+3 | DRY | 2024-10-18 | 2024-11-08 | Rafikul Islam |  | 38.8476 |  |  | 21
136 | 2024-11-01 | 16/5 | DA+3 | DRY | 2024-11-03 | 2024-11-09 | Bina Devi |  | 38.8476 |  |  | 6
137 | 2024-11-01 | 16/1 | DA+0 | DRY | 2024-11-05 | 2024-11-09 | Jailal Ageria |  | 37.5044 |  |  | 4
138 | 2024-11-01 | 59/4 | DA+3 | DFR | 2024-11-01 | 2024-11-09 | Uma const |  | 38.8476 |  |  | 8
139 | 2024-11-01 | 50/6 | DA+9 | Sandy | 2024-11-04 | 2024-11-10 | Sobha Devi |  | 47.1844 |  |  | 6
140 | 2024-11-01 | 55/5 | DA+0 | Sandy | 2024-11-01 | 2024-11-12 | Jirwa Devi |  | 37.5044 |  |  | 11
141 | 2024-11-01 | 73/9 | DA+0 | DRY | 2024-11-09 | 2024-11-13 | Chinta devi |  | 37.5044 |  |  | 4
142 | 2024-11-01 | 17/0 | DB2+3 | DRY | 2024-11-04 | 2024-11-14 | Nirmal Mahto |  | 60.0968 |  |  | 10
143 | 2024-11-01 | 49/7 | DA+0 | Sandy | 2024-11-11 | 2024-11-14 | Sobha Devi |  | 37.5044 |  |  | 3
144 | 2024-11-01 | 73/8 | DA+3 | DRY | 2024-11-13 | 2024-11-17 | Chinta devi |  | 38.8476 |  |  | 4
145 | 2024-11-01 | 11/5 | DA+0 | DFR | 2024-11-10 | 2024-11-18 | Rafikul Islam |  | 37.5044 |  |  | 8
146 | 2024-11-01 | 13/2 | DA+3 | DRY | 2024-11-11 | 2024-11-18 | Jailal Ageria |  | 38.8476 |  |  | 7
147 | 2024-11-01 | 43/9 | DA+9 | Sandy | 2024-11-07 | 2024-11-18 | Yogendra Mahto |  | 47.1844 |  |  | 11
148 | 2024-11-01 | 49/6 | DA+0 | Sandy | 2024-11-15 | 2024-11-18 | Sobha Devi |  | 37.5044 |  |  | 3
149 | 2024-11-01 | 73/6 | DA+0 | DRY | 2024-11-17 | 2024-11-20 | Chinta devi |  | 37.5044 |  |  | 3
150 | 2024-11-01 | 47/10 | DA+6 | Sandy | 2024-11-02 | 2024-11-22 | Kaushalya const |  | 45.413 |  |  | 20
151 | 2024-11-01 | 49/4 | DA+3 | Sandy | 2024-11-18 | 2024-11-22 | Sobha Devi |  | 38.8476 |  |  | 4
152 | 2024-11-01 | 59/2 | DA+3 | DFR | 2024-11-12 | 2024-11-24 | Jirwa Devi |  | 38.8476 |  |  | 12
153 | 2024-11-01 | 52/10 | DA+9 | Sandy | 2024-11-13 | 2024-11-25 | Ganesh Sinha |  | 47.1844 |  |  | 12
154 | 2024-11-01 | 43/8 | DA+9 | Sandy | 2024-11-19 | 2024-11-27 | Yogendra Mahto |  | 47.1844 |  |  | 8
155 | 2024-11-01 | 49/5 | DA+3 | Sandy | 2024-11-23 | 2024-11-27 | Sobha Devi |  | 38.8476 |  |  | 4
156 | 2024-11-01 | 17/5 | DA+3 | DRY | 2024-11-22 | 2024-11-30 | Bina Devi |  | 38.8476 |  |  | 8
157 | 2024-11-01 | 11A/9 | DA+3 | DRY | 2024-11-24 | 2024-11-30 | Deglal Mahto |  | 38.8476 |  |  | 6
158 | 2024-11-01 | 49/2 | DA+3 | Sandy | 2024-11-27 | 2024-11-30 | Sobha Devi |  | 38.8476 |  |  | 3
159 | 2024-11-01 | 72/3 | DA+3 | DRY | 2024-11-24 | 2024-11-30 | Sanjeev Kumar |  | 38.8476 |  |  | 6
160 | 2024-12-01 | 59/1 | DA+3 | DRY | 2024-11-25 | 2024-12-03 | Jirwa Devi |  | 38.8476 |  |  | 8
161 | 2024-12-01 | 52/9 | DA+3 | Sandy | 2024-11-26 | 2024-12-05 | Ganesh Sinha |  | 38.8476 |  |  | 9
162 | 2024-12-01 | 49/3 | DA+3 | Sandy | 2024-12-02 | 2024-12-05 | Sobha Devi |  | 38.8476 |  |  | 3
163 | 2024-12-01 | 11A/7 | DA+9 | Sandy | 2024-11-28 | 2024-12-06 | Jailal Ageria |  | 47.1844 |  |  | 8
164 | 2024-12-01 | 11A/3 | DA+3 | DRY | 2024-12-01 | 2024-12-07 | Deglal Mahto |  | 38.8476 |  |  | 6
165 | 2024-12-01 | 49/1 | DA+0 | Sandy | 2024-12-06 | 2024-12-09 | Sobha Devi |  | 37.5044 |  |  | 3
166 | 2024-12-01 | 10/12 | DB1+0 | DRY | 2024-11-30 | 2024-12-11 | Jagdish Mahto |  | 57.5972 |  |  | 11
167 | 2024-12-01 | 73/3 | DA+0 | DRY | 2024-12-09 | 2024-12-13 | Chinta devi |  | 37.5044 |  |  | 4
168 | 2024-12-01 | 11A/6 | DA+6 | DRY | 2024-12-09 | 2024-12-16 | Deglal Mahto |  | 45.413 |  |  | 7
169 | 2024-12-01 | 59/0 | DC2+0 | DRY | 2024-12-03 | 2024-12-16 | Jirwa Devi |  | 66.3811 |  |  | 13
170 | 2024-12-01 | 65/8 | DA+0 | DRY | 2024-12-20 | 2024-12-27 | Sanjeev Kumar |  | 37.5044 |  |  | 7
171 | 2025-01-01 | 11A/5 | DA+3 | DRY | 2024-12-25 | 2025-01-04 | Deglal Mahto |  | 38.8476 |  |  | 10
172 | 2025-01-01 | 65/7 | DA+0 | DRY | 2024-12-28 | 2025-01-04 | Sanjeev Kumar |  | 37.5044 |  |  | 7
173 | 2025-01-01 | 43/0 | DB1+0 | Sandy | 2024-12-25 | 2025-01-07 | Yogendra Mahto |  | 57.5972 |  |  | 13
174 | 2025-01-01 | 73/0 | DB2+0 | DRY | 2025-01-03 | 2025-01-09 | Chinta devi |  | 57.5972 |  |  | 6
175 | 2025-01-01 | 53/8 | DA+3 | Sandy | 2025-01-04 | 2025-01-09 | Ganesh Sinha |  | 38.8476 |  |  | 5
176 | 2025-01-01 | 74/0 | DB2+0 | Sandy | 2025-01-05 | 2025-01-13 | Sunny Const |  | 57.5972 |  |  | 8
177 | 2025-01-01 | 73/4 | DA+0 | DRY | 2025-01-10 | 2025-01-14 | Chinta devi |  | 37.5044 |  |  | 4
178 | 2025-01-01 | 43/1 | DA+3 | Sandy | 2025-01-08 | 2025-01-17 | Yogendra Mahto |  | 38.8476 |  |  | 9
179 | 2025-01-01 | 43/7 | DA+3 | Sandy | 2025-01-11 | 2025-01-18 | Bina Devi |  | 38.8476 |  |  | 7
180 | 2025-01-01 | 53/7 | DA+3 | Sandy | 2025-01-10 | 2025-01-18 | Ganesh Sinha |  | 38.8476 |  |  | 8
181 | 2025-01-01 | 73/5 | DA+0 | DRY | 2025-01-15 | 2025-01-19 | Chinta devi |  | 37.5044 |  |  | 4
182 | 2025-01-01 | 73/7 | DA+0 | DRY | 2025-01-14 | 2025-01-19 | Sunny Const |  | 37.5044 |  |  | 5
183 | 2025-01-01 | 72/0 | DB2+3 | DRY | 2025-01-21 | 2025-01-27 | Chinta Devi |  | 60.0968 |  |  | 6
184 | 2025-01-01 | 43/6 | DA+3 | Sandy | 2025-01-19 | 2025-01-29 | Bina Devi |  | 38.8476 |  |  | 10
185 | 2025-01-01 | 66/0 | DC2+6 | DRY | 2025-01-11 | 2025-01-29 | Sanjeev Kumar |  | 78.132 |  |  | 18
186 | 2025-01-01 | 53/6 | DA+6 | Sandy | 2025-01-19 | 2025-01-30 | Ganesh Sinha |  | 45.413 |  |  | 11
187 | 2025-02-01 | 72/1 | DA+3 | DRY | 2025-01-28 | 2025-02-02 | Chinta Devi |  | 38.8476 |  |  | 5
188 | 2025-02-01 | 65/10 | DA+0 | DRY | 2025-01-29 | 2025-02-06 | Sanjeev Kumar |  | 37.5044 |  |  | 8
189 | 2025-02-01 | 72/2 | DA+0 | DRY | 2025-02-02 | 2025-02-06 | Chinta Devi |  | 37.5044 |  |  | 4
190 | 2025-02-01 | 51/0 | DC2+0 | Sandy | 2025-01-31 | 2025-02-07 | Sunny Const. |  | 66.3811 |  |  | 7
191 | 2025-02-01 | 1A/1 | DA+6 | DFR | 2025-01-31 | 2025-02-10 | Bina Devi |  | 45.413 |  |  | 10
192 | 2025-02-01 | 71/8 | DA+3 | DRY | 2025-02-07 | 2025-02-10 | Chinta Devi |  | 38.8476 |  |  | 3
193 | 2025-02-01 | 52/0 | DC2+0 | Sandy | 2025-02-08 | 2025-02-14 | Sunny Const. |  | 66.3811 |  |  | 6
194 | 2025-02-01 | 49/0 | DD45+0 | Sandy | 2025-02-05 | 2025-02-14 | Sobha Devi |  | 86.1293 |  |  | 9
195 | 2025-02-01 | 71/7 | DA+3 | DRY | 2025-02-11 | 2025-02-15 | Chinta Devi |  | 38.8476 |  |  | 4
196 | 2025-02-01 | 1A/2 | DA+0 | DRY | 2025-02-11 | 2025-02-18 | Bina Devi |  | 37.5044 |  |  | 7
197 | 2025-02-01 | 71/6 | DA+0 | DRY | 2025-02-16 | 2025-02-19 | Chinta Devi |  | 37.5044 |  |  | 3
198 | 2025-02-01 | 50/5 | DA+9 | Sandy | 2025-02-15 | 2025-02-20 | Sobha Devi |  | 47.1844 |  |  | 5
199 | 2025-02-01 | 71/5 | DA+3 | DRY | 2025-02-20 | 2025-02-24 | Chinta Devi |  | 38.8476 |  |  | 4
200 | 2025-02-01 | 1A/3 | DA+0 | DRY | 2025-02-19 | 2025-02-28 | Bina Devi |  | 37.5044 |  |  | 9
201 | 2025-03-01 | 71/4 | DA+3 | DRY | 2025-02-25 | 2025-03-01 | Chinta Devi |  | 38.8476 |  |  | 4
202 | 2025-03-01 | 53/5 | DA+3 | Sandy | 2025-03-01 | 2025-03-07 | Ganesh Sinha |  | 38.8476 |  |  | 6
203 | 2025-03-01 | 71/3 | DA+6 | DRY | 2025-03-02 | 2025-03-07 | Chinta Devi |  | 45.413 |  |  | 5
204 | 2025-03-01 | 58/0 | DC1+3 | DFR | 2025-02-26 | 2025-03-10 | Jirwa Devi |  | 69.2287 |  |  | 12
205 | 2025-03-01 | 71/2 | DA+3 | DRY | 2025-03-08 | 2025-03-12 | Chinta Devi |  | 38.8476 |  |  | 4
206 | 2025-03-01 | 70/3 | DA+3 | DRY | 2025-03-08 | 2025-03-16 | Sanjeev kumar |  | 38.8476 |  |  | 8
207 | 2025-03-01 | 53/4 | DA+0 | Sandy | 2025-03-09 | 2025-03-17 | Ganesh Sinha |  | 37.5044 |  |  | 8
208 | 2025-03-01 | 71/1 | DA+3 | DRY | 2025-03-13 | 2025-03-18 | Chinta Devi |  | 38.8476 |  |  | 5
209 | 2025-03-01 | 53/3 | DA+6 | Sandy | 2025-03-18 | 2025-03-25 | Ganesh Sinha |  | 45.413 |  |  | 7
210 | 2025-03-01 | 71/0 | DB2+3 | DRY | 2025-03-19 | 2025-03-25 | Chinta Devi |  | 60.0968 |  |  | 6
211 | 2025-03-01 | 70/5 | DA+3 | DRY | 2025-03-20 | 2025-03-29 | Sanjeev kumar |  | 38.8476 |  |  | 9
212 | 2025-03-01 | 53/2 | DA+0 | Sandy | 2025-03-26 | 2025-03-31 | Ganesh Sinha |  | 37.5044 |  |  | 5
213 | 2025-03-01 | 70/11 | DA+3 | DRY | 2025-03-26 | 2025-03-31 | Chinta Devi |  | 38.8476 |  |  | 5
214 | 2025-04-01 | 47/9 | DA+3 | Sandy | 2025-03-31 | 2025-04-02 | Sobha Devi |  | 38.8476 |  |  | 2
215 | 2025-04-01 | 70/10 | DA+3 | DRY | 2025-03-31 | 2025-04-04 | Chinta Devi |  | 38.8476 |  |  | 4
216 | 2025-04-01 | 47/8 | DA+0 | Sandy | 2025-04-03 | 2025-04-06 | Sobha Devi |  | 37.5044 |  |  | 3
217 | 2025-04-01 | 70/9 | DA+3 | DRY | 2025-04-06 | 2025-04-09 | Chinta Devi |  | 38.8476 |  |  | 3
218 | 2025-04-01 | 53/1 | DA+9 | Sandy | 2025-04-02 | 2025-04-11 | Ganesh Sinha |  | 47.1844 |  |  | 9
219 | 2025-04-01 | 68/0 | DD45+0 | DRY | 2025-03-13 | 2025-04-14 | Sunny Const. |  | 86.1293 |  |  | 32
220 | 2025-04-01 | 53/0 | DB2+9 | Sandy | 2025-04-12 | 2025-04-28 | Ganesh Sinha |  | 70.7017 |  |  | 16
221 | 2025-05-01 | 70/4 | DA+3 | DRY | 2025-04-27 | 2025-05-02 | Chinta devi |  | 38.8476 |  |  | 5
222 | 2025-05-01 | 67/0 | DC1+9 | DRY | 2025-05-20 | 2025-05-29 | Sunny Construction |  | 81.4946 |  |  | 9
223 | 2025-06-01 | 1A/4 | DA+3 | DFR | 2025-05-10 | 2025-06-11 | Bhairo Mahto |  | 38.8476 | Crane erection+Derrick Pole |  | 32
224 | 2025-06-01 | 1A/6 | DA+0 | Sandy | 2025-06-11 | 2025-06-20 | Bhairo Mahto |  | 37.5044 | Crane erection+Derrick Pole |  | 9
225 | 2025-06-01 | 70/7 | DA+3 | DRY | 2025-06-17 | 2025-06-22 | Jwala Singh |  | 38.8476 | Derrick |  | 5
226 | 2025-06-01 | 70/6 | DA+3 | DRY | 2025-05-19 | 2025-06-28 | Satyam Enterprises (Santosh) |  | 38.8476 | Derrick |  | 40
227 | 2025-06-01 | 1A/7 | DA+3 | Sandy | 2025-06-04 | 2025-06-30 | Anil Kumar+Kewat |  | 38.8476 | Crane erection+Derrick Pole |  | 26
228 | 2025-06-01 | 70/2 | DA+3 | DRY | 2025-06-22 | 2025-06-30 | Satyam Enterprises (Vijay) |  | 38.8476 | Derrick |  | 8
229 | 2025-07-01 | 8/9 | DA+3 | DFR | 2025-06-27 | 2025-07-01 | Jwala Singh |  | 38.8476 | Derrick |  | 4
230 | 2025-07-01 | 69/1 | DA+3 | DRY | 2025-06-28 | 2025-07-03 | Jwala Singh (Suraj Kumar) |  | 38.8476 | Derrick |  | 5
231 | 2025-07-01 | 70/1 | DA+3 | DRY | 2025-07-01 | 2025-07-08 | Satyam Enterprises (Vijay) |  | 38.8476 | Derrick |  | 7
232 | 2025-07-01 | 8/10 | DA+3 | DFR | 2025-07-07 | 2025-07-19 | Jwala Singh |  | 38.8476 | Derrick |  | 12
233 | 2025-07-01 | 70/0 | DC1+0 | DRY | 2025-07-03 | 2025-07-14 | Jwala Singh (Suraj Kumar) |  | 66.3811 | Derrick |  | 11
234 | 2025-07-01 | 70/8 | DA+3 | DRY | 2025-07-08 | 2025-07-14 | Satyam Enterprises (Vijay) |  | 38.8476 | Derrick |  | 6
235 | 2025-07-01 | 1A/8 | DA+0 | Sandy | 2025-06-11 | 2025-07-15 | Anil Kumar+Kewat |  | 37.5044 | Crane erection+Derrick Pole |  | 34
236 | 2025-07-01 | 2/8 | DA+0 | Sandy | 2025-07-11 | 2025-07-16 | Arawali-2 |  | 37.5044 | Derrick |  | 5
237 | 2025-07-01 | 69/0 | DB2+0 | DFR | 2025-07-14 | 2025-07-21 | Jwala Singh (Suraj Kumar) |  | 57.5972 | Derrick |  | 7
238 | 2025-07-01 | 44/3 | DA+0 | Sandy | 2025-07-19 | 2025-07-22 | Satyam Enterprises |  | 37.5044 | Derrick |  | 3
239 | 2025-07-01 | 2/9 | DA+0 | DRY | 2025-07-16 | 2025-07-23 | Arawali-2 |  | 37.5044 | Derrick |  | 7
240 | 2025-07-01 | 18/3 | DA+0 | DRY | 2025-07-14 | 2025-07-23 | Priyanka Devi-2 |  | 37.5044 | Derrick |  | 9
241 | 2025-07-01 | 26/2 | DA+3 | DFR | 2025-07-21 | 2025-07-24 | Hazarilal Yadav-Poonam Kumari |  | 38.8476 | Derrick |  | 3
242 | 2025-07-01 | 1A/5 | DA+0 | DRY | 2025-07-10 | 2025-07-26 | Bhairo Mahto+Kewat |  | 37.5044 | Derrick |  | 16
243 | 2025-07-01 | 44/2 | DA+0 | Sandy | 2025-07-23 | 2025-07-26 | Satyam Enterprises |  | 37.5044 | Derrick |  | 3
244 | 2025-07-01 | 26/3 | DA+0 | DRY | 2025-07-25 | 2025-07-28 | Hazarilal Yadav-Poonam Kumari |  | 37.5044 | Derrick |  | 3
245 | 2025-07-01 | 44/4 | DA+9 | Sandy | 2025-07-23 | 2025-07-28 | Satyam Enterprises |  | 47.1844 | Derrick |  | 5
246 | 2025-07-01 | 44/1 | DA+0 | Sandy | 2025-07-26 | 2025-07-29 | Satyam Enterprises |  | 37.5044 | Derrick |  | 3
247 | 2025-07-01 | 1A/0 | DD60+0 | DRY | 2025-07-01 | 2025-07-29 | Bhairo Mahto+Priyanka Devi (Subodh) |  | 86.1293 | Crane erection+Derrick |  | 28
248 | 2025-07-01 | 2/7 | DA+3 | Sandy | 2025-07-23 | 2025-07-30 | Arawali-2 |  | 38.8476 | Derrick |  | 7
249 | 2025-07-01 | 25/4 | DA+0 | Sandy | 2025-07-27 | 2025-07-31 | Pusplata (Praful) |  | 37.5044 | Derrick |  | 4
250 | 2025-07-01 | 27/2 | DA+3 | DFR | 2025-07-21 | 2025-07-31 | Dharmendra-Munnilal (Pusplata) |  | 38.8476 | Derrick |  | 10
251 | 2025-07-01 | 27/3 | DA+3 | DFR | 2025-07-27 | 2025-07-31 | Pusplata (Kailash) |  | 38.8476 | Derrick |  | 4
252 | 2025-08-01 | 44/0 | DB1+3 | Sandy | 2025-07-29 | 2025-08-03 | Satyam Enterprises |  | 60.0968 | Derrick |  | 5
253 | 2025-08-01 | 12/0 | DD60+0 | DRY | 2025-07-25 | 2025-08-02 | Arawali-1 |  | 86.1293 | Derrick |  | 8
254 | 2025-08-01 | 29/1 | DA+3 | DRY | 2025-07-30 | 2025-08-04 | Jwala Singh |  | 38.8476 | Derrick |  | 5
255 | 2025-08-01 | 44/7 | DA+9 | Sandy | 2025-07-28 | 2025-08-03 | Satyam Enterprises |  | 47.1844 | Derrick |  | 6
256 | 2025-08-01 | 47/7 | DA+3 | Sandy | 2025-07-26 | 2025-08-05 | Vinay Construction |  | 38.8476 | Derrick |  | 10
257 | 2025-08-01 | 19/5 | DA+0 | DRY | 2025-08-01 | 2025-08-05 | Priyanka Devi |  | 37.5044 | Derrick |  | 4
258 | 2025-08-01 | 30/3 | DA+3 | Sandy | 2025-08-01 | 2025-08-06 | Pusplata (Kailash) |  | 38.8476 | Derrick |  | 5
259 | 2025-08-01 | 44/10 | DB1+9 | Sandy | 2025-07-28 | 2025-08-06 | Satyam Enterprises |  | 70.7017 | Derrick |  | 9
260 | 2025-08-01 | 25/3 | DA+0 | Sandy | 2025-07-31 | 2025-08-09 | Pusplata (Praful) |  | 37.5044 | Derrick |  | 9
261 | 2025-08-01 | 44/5 | DA+9 | Sandy | 2025-08-04 | 2025-08-09 | Satyam Enterprises |  | 47.1844 | Derrick |  | 5
262 | 2025-08-01 | 4/1 | DA+0 | DRY | 2025-07-25 | 2025-08-09 | Bhairo Mahto |  | 37.5044 | Derrick |  | 15
263 | 2025-08-01 | 8/12 | DA+0 | DRY | 2025-08-04 | 2025-08-09 | Jwala Singh |  | 37.5044 | Derrick |  | 5
264 | 2025-08-01 | 29/0 | DB1+0 | DRY | 2025-07-30 | 2025-08-12 | Jwala Singh |  | 57.5972 | Derrick |  | 13
265 | 2025-08-01 | 55/8 | DA+6 | Sandy | 2025-08-07 | 2025-08-13 | Shobha Devi |  | 45.413 | Derrick |  | 6
266 | 2025-08-01 | 2/0 | DC1+0 | DRY | 2025-07-29 | 2025-08-13 | Priyanka Devi (Subodh) |  | 66.3811 | Derrick |  | 15
267 | 2025-08-01 | 44/6 | DB1+3 | Sandy | 2025-08-09 | 2025-08-16 | Satyam Enterprises |  | 60.0968 | Derrick |  | 7
268 | 2025-08-01 | 47/2 | DA+9 | Sandy | 2025-08-04 | 2025-08-16 | Vinay Construction |  | 47.1844 | Derrick |  | 12
269 | 2025-08-01 | 40/3 | DA+3 | Sandy | 2025-08-10 | 2025-08-17 | Rahul Kumar |  | 38.8476 | Derrick |  | 7
270 | 2025-08-01 | 45/0 | DC2+0 | Sandy | 2025-08-06 | 2025-08-17 | Sintu_Pawan (Satyam Enterprises) |  | 66.3811 | Derrick |  | 11
271 | 2025-08-01 | 55/7 | DA+0 | Sandy | 2025-08-13 | 2025-08-17 | Shobha Devi |  | 37.5044 | Derrick |  | 4
272 | 2025-08-01 | 2/3 | DA+3 | Sandy | 2025-08-04 | 2025-08-17 | Sheetal Singh |  | 38.8476 | Derrick |  | 13
273 | 2025-08-01 | 30/5 | DA+3 | DRY | 2025-08-06 | 2025-08-17 | Pusplata (Kailash) |  | 38.8476 | Derrick |  | 11
274 | 2025-08-01 | 27/4 | DA+3 | DFR | 2025-08-09 | 2025-08-17 | Pusplata (Ramchandra) |  | 38.8476 | Derrick |  | 8
275 | 2025-08-01 | 43/11 | DA+3 | Sandy | 2025-08-12 | 2025-08-18 | Satyam-Manish |  | 38.8476 | Derrick |  | 6
276 | 2025-08-01 | 17/4 | DA+3 | DRY | 2025-08-13 | 2025-08-18 | Pusplata_Pankaj |  | 38.8476 | Derrick |  | 5
277 | 2025-08-01 | 28/5 | DA+9 | Sandy | 2025-08-12 | 2025-08-19 | Jwala Singh |  | 47.1844 | Derrick |  | 7
278 | 2025-08-01 | 2/5 | DA+3 | Sandy | 2025-08-04 | 2025-08-19 | Usha Tower |  | 38.8476 | Derrick |  | 15
279 | 2025-08-01 | 1/0 | DD60+0 | DRY | 2025-07-07 | 2025-08-20 | Bhairo Mahto+Kewat |  | 86.1293 | Derrick |  | 44
280 | 2025-08-01 | 41/1 | DB1+9 | Sandy | 2025-08-10 | 2025-08-21 | Gauri Shankar |  | 70.7017 | Derrick |  | 11
281 | 2025-08-01 | 30/6 | DA+0 | DRY | 2025-08-17 | 2025-08-21 | Pusplata (Kailash) |  | 37.5044 | Derrick |  | 4
282 | 2025-08-01 | 4/2 | DA+0 | DRY | 2025-07-30 | 2025-08-22 | Bhairo Mahto |  | 37.5044 | Derrick |  | 23
283 | 2025-08-01 | 47/4 | DA+3 | Sandy | 2025-08-06 | 2025-08-22 | Vinay Construction |  | 38.8476 | Derrick |  | 16
284 | 2025-08-01 | 27/1 | DA+3 | DFR | 2025-08-16 | 2025-08-23 | Pusplata (Dharamveer) |  | 38.8476 | Derrick |  | 7
285 | 2025-08-01 | 44/9 | DA+9 | Sandy | 2025-08-17 | 2025-08-24 | Satyam Enterprises |  | 47.1844 | Derrick |  | 7
286 | 2025-08-01 | 55/1 | DA+0 | WFR | 2025-08-17 | 2025-08-24 | Sunny Construction |  | 37.5044 | Derrick |  | 7
287 | 2025-08-01 | 40/2 | DA+3 | Sandy | 2025-08-18 | 2025-08-24 | Rahul Kumar |  | 38.8476 | Derrick |  | 6
288 | 2025-08-01 | 28/2 | DA+0 | DFR | 2025-08-19 | 2025-08-25 | Jwala Singh |  | 37.5044 | Derrick |  | 6
289 | 2025-08-01 | 18/0 | DC2+0 | DRY | 2025-08-18 | 2025-08-25 | Pusplata |  | 66.3811 | Derrick |  | 7
290 | 2025-08-01 | 4/4 | DA+0 | DRY | 2025-08-20 | 2025-08-25 | Pusplata (Ashok) |  | 37.5044 | Derrick |  | 5
291 | 2025-08-01 | 57/2 | DA+3 | DRY | 2025-08-21 | 2025-08-25 | Sobha Devi |  | 38.8476 | Derrick |  | 4
292 | 2025-08-01 | 44/11 | DA+0 | Sandy | 2025-08-19 | 2025-08-25 | Chinta Devi |  | 37.5044 | Derrick |  | 6
293 | 2025-08-01 | 31/1 | DA+0 | DRY | 2025-08-22 | 2025-08-26 | Pusplata (Kailash) |  | 37.5044 | Derrick |  | 4
294 | 2025-08-01 | 47/3 | DA+9 | Sandy | 2025-08-17 | 2025-08-29 | Vinay Construction |  | 47.1844 | Derrick |  | 12
295 | 2025-08-01 | 57/1 | DA+0 | Sandy | 2025-08-21 | 2025-08-29 | Sobha Devi |  | 37.5044 | Derrick |  | 8
296 | 2025-08-01 | 30/1 | DA+0 | Sandy | 2025-08-25 | 2025-08-30 | Pusplata (Deepak) |  | 37.5044 | Derrick |  | 5
297 | 2025-08-01 | 43/10 | DA+3 | Sandy | 2025-08-25 | 2025-08-30 | Satyam Enterprises (Pawan) |  | 38.8476 | Derrick |  | 5
298 | 2025-08-01 | 36/2 | DA+0 | Sandy | 2025-08-22 | 2025-08-30 | Ganesh Sinha |  | 37.5044 | Derrick |  | 8
299 | 2025-08-01 | 52/3 | DA+9 | Sandy | 2025-08-17 | 2025-08-30 | Jirwa Devi |  | 47.1844 | Derrick |  | 13
300 | 2025-08-01 | 8/1 | DA+3 | DRY | 2025-08-23 | 2025-08-31 | Bhairo Mahto |  | 38.8476 | Derrick |  | 8
301 | 2025-08-01 | 54/5 | DA+9 | Sandy | 2025-08-17 | 2025-08-31 | Sunny Construction |  | 47.1844 | Derrick |  | 14
302 | 2025-08-01 | 4/3 | DA+0 | DRY | 2025-08-29 | 2025-08-31 | Pusplata (Ashok) |  | 37.5044 | Derrick |  | 2
303 | 2025-08-01 | 45/1 | DA+9 | Sandy | 2025-08-25 | 2025-08-31 | Chinta Devi |  | 47.1844 | Derrick |  | 6
304 | 2025-09-01 | 14A/0 | DC1+0 | DRY | 2025-08-26 | 2025-09-03 | Pusplata (Santosh/Pankaj Singh) |  | 66.3811 | Derrick |  | 8
305 | 2025-09-01 | 20/3 | DA+0 | DRY | 2025-08-26 | 2025-09-03 | Priyanka Devi (Santosh) |  | 37.5044 | Derrick |  | 8
306 | 2025-09-01 | 31/2 | DA+0 | DRY | 2025-08-26 | 2025-09-02 | Pusplata (Kailash) |  | 37.5044 | Derrick |  | 7
307 | 2025-09-01 | 27/0 | DC1+0 | DFR | 2025-08-23 | 2025-09-03 | Pusplata (Dharamveer) |  | 66.3811 | Derrick |  | 11
308 | 2025-09-01 | 43/5 | DA+3 | DRY | 2025-08-29 | 2025-09-03 | Satyam Enterprises (Manish) |  | 38.8476 | Derrick |  | 5
309 | 2025-09-01 | 8/4 | DA+3 | DRY | 2025-08-29 | 2025-09-04 | Jwala Singh |  | 38.8476 | Derrick |  | 6
310 | 2025-09-01 | 21/0 | DB2+0 | DRY | 2025-09-02 | 2025-09-05 | Sudheer-2 (Priyanka Devi) |  | 57.5972 | Derrick |  | 3
311 | 2025-09-01 | 36/3 | DA+0 | Sandy | 2025-08-30 | 2025-09-06 | Ganesh Sinha |  | 37.5044 | Derrick |  | 7
312 | 2025-09-01 | 47/6 | DA+3 | Sandy | 2025-08-22 | 2025-09-06 | Vinay Construction |  | 38.8476 | Derrick |  | 15
313 | 2025-09-01 | 54/4 | DA+9 | Sandy | 2025-09-01 | 2025-09-06 | Sunny Construction |  | 47.1844 | Derrick |  | 5
314 | 2025-09-01 | 26/0 | DB1+0 | DFR | 2025-08-26 | 2025-09-06 | Pusplata (rajaram) |  | 57.5972 | Derrick |  | 11
315 | 2025-09-01 | 47/1 | DA+3 | Sandy | 2025-09-01 | 2025-09-07 | Chinta Devi |  | 38.8476 | Derrick |  | 6
316 | 2025-09-01 | 20/2 | DA+0 | DRY | 2025-09-02 | 2025-09-07 | Priyanka Devi (Sudheer) |  | 37.5044 | Derrick |  | 5
317 | 2025-09-01 | 24/0 | DD45+3 | DRY | 2025-08-26 | 2025-09-07 | Pusplata (Praphul) |  | 89.9096 | Derrick |  | 12
318 | 2025-09-01 | 2/4 | DA+3 | Sandy | 2025-08-24 | 2025-09-09 | Sheetal Singh-2 |  | 38.8476 | Derrick |  | 16
319 | 2025-09-01 | 2/6 | DA+3 | Sandy | 2025-08-24 | 2025-09-09 | Anvi Construction |  | 38.8476 | Derrick |  | 16
320 | 2025-09-01 | 32/1 | DA+3 | Sandy | 2025-09-03 | 2025-09-10 | Pusplata (Kailash) |  | 38.8476 | Derrick |  | 7
321 | 2025-09-01 | 52/4 | DA+9 | Sandy | 2025-09-01 | 2025-09-10 | Jirwa Devi |  | 47.1844 | Derrick |  | 9
322 | 2025-09-01 | 34/3 | DA+0 | Sandy | 2025-09-03 | 2025-09-11 | Satyam Enterprises (Vijay) |  | 37.5044 | Derrick |  | 8
323 | 2025-09-01 | 21/4 | DA+3 | Sandy | 2025-09-09 | 2025-09-12 | Priyanka Devi (Sudheer) |  | 38.8476 | Derrick |  | 3
324 | 2025-09-01 | 28/0 | DB2+0 | DFR | 2025-09-03 | 2025-09-12 | Jwala Singh-1 |  | 57.5972 | Derrick |  | 9
325 | 2025-09-01 | 6/2 | DA+0 | DFR | 2025-09-05 | 2025-09-12 | Usha Tower |  | 37.5044 | Derrick |  | 7
326 | 2025-09-01 | 54/3 | DA+6 | Sandy | 2025-09-07 | 2025-09-12 | Sunny Construction |  | 45.413 | Derrick |  | 5
327 | 2025-09-01 | 2/1 | DA+3 | Sandy | 2025-09-03 | 2025-09-13 | Sheetal Singh-1 |  | 38.8476 | Derrick |  | 10
328 | 2025-09-01 | 56/0 | DD60+25 | Sandy | 2025-08-30 | 2025-09-14 | Shobha Devi |  | 143.6019 | Derrick+Crane |  | 15
329 | 2025-09-01 | 26/1 | DA+0 | DRY | 2025-09-07 | 2025-09-16 | Pusplata (rajaram) |  | 37.5044 | Derrick |  | 9
330 | 2025-09-01 | 36/1 | DA+3 | Sandy | 2025-08-29 | 2025-09-16 | Nirmal Mahto |  | 38.8476 | Derrick |  | 18
331 | 2025-09-01 | 36/4 | DA+6 | Sandy | 2025-09-07 | 2025-09-16 | Ganesh Sinha |  | 45.413 | Derrick |  | 9
332 | 2025-09-01 | 54/1 | DA+3 | Sandy | 2025-09-13 | 2025-09-18 | Sunny Construction |  | 38.8476 | Derrick |  | 5
333 | 2025-09-01 | 8/5 | DA+3 | DRY | 2025-09-12 | 2025-09-18 | Jwala Singh-2 |  | 38.8476 | Derrick |  | 6
334 | 2025-09-01 | 52/2 | DA+6 | Sandy | 2025-09-10 | 2025-09-20 | Jirwa Devi |  | 45.413 | Derrick |  | 10
335 | 2025-09-01 | 2/2 | DA+3 | Sandy | 2025-09-09 | 2025-09-22 | Priyanka Devi (Subodh) |  | 38.8476 | Derrick |  | 13
336 | 2025-09-01 | 21/5 | DA+6 | DFR | 2025-09-19 | 2025-09-22 | Priyanka Devi (Sudheer) |  | 45.413 | Derrick |  | 3
337 | 2025-09-01 | 54/2 | DA+3 | Sandy | 2025-09-19 | 2025-09-22 | Sunny Construction |  | 38.8476 | Derrick |  | 3
338 | 2025-09-01 | 43/3 | DA+0 | DRY | 2025-09-09 | 2025-09-22 | Vivek Ganju |  | 37.5044 | Derrick |  | 13
339 | 2025-09-01 | 29/3 | DA+0 | Sandy | 2025-09-10 | 2025-09-23 | Jwala Singh-1 |  | 37.5044 | Derrick |  | 13
340 | 2025-09-01 | 8/2 | DA+3 | DRY | 2025-09-12 | 2025-09-23 | Bhairo Mahto |  | 38.8476 | Derrick |  | 11
341 | 2025-09-01 | 47/0 | DD60+25 | Sandy | 2025-09-09 | 2025-09-25 | Chinta Devi |  | 143.6019 | Derrick+Crane |  | 16
342 | 2025-09-01 | 27/11 | DA+3 | DRY | 2025-08-29 | 2025-09-26 | Pusplata (Ramchandra) |  | 38.8476 | Derrick |  | 28
343 | 2025-09-01 | 36/0 | DB2+0 | Sandy | 2025-09-16 | 2025-09-27 | Nirmal Mahto |  | 57.5972 | Derrick |  | 11
344 | 2025-09-01 | 37/0 | DB2+0 | Sandy | 2025-09-16 | 2025-09-27 | Ganesh Sinha |  | 57.5972 | Derrick |  | 11
345 | 2025-09-01 | 20/0 | DB2+0 | Sandy | 2025-09-20 | 2025-09-29 | Priyanka Devi (Sontosh) |  | 57.5972 | Derrick |  | 9
346 | 2025-09-01 | 47/5 | DA+0 | Sandy | 2025-09-07 | 2025-09-29 | Vinay Construction/ Chinta Devi |  | 37.5044 | Derrick |  | 22
347 | 2025-09-01 | 57/0 | DD60+25 | Sandy | 2025-09-15 | 2025-09-29 | Shobha Devi |  | 143.6019 | Derrick+Crane |  | 14
348 | 2025-09-01 | 52/1 | DA+6 | Sandy | 2025-09-20 | 2025-09-30 | Jirwa Devi |  | 45.413 | Derrick |  | 10
349 | 2025-09-01 | 54/0 | DB1+6 | Sandy | 2025-09-22 | 2025-09-30 | Sunny Construction |  | 67.8737 | Derrick |  | 8
350 | 2025-09-01 | 21/3 | DA+6 | Sandy | 2025-09-10 | 2025-09-30 | Shri Shyam Construction |  | 45.413 | Derrick |  | 20
351 | 2025-10-01 | 6/1 | DA+0 | DFR | 2025-09-25 | 2025-10-03 | Sheetal Singh-1 |  | 37.5044 | Derrick |  | 8
352 | 2025-10-01 | 35/5 | DA+0 | Sandy | 2025-09-27 | 2025-10-06 | Nirmal Mahto |  | 37.5044 | Derrick |  | 9
353 | 2025-10-01 | 42/6 | DA+0 | Sandy | 2025-09-22 | 2025-10-07 | Vivek Ganju |  | 37.5044 | Derrick |  | 15
354 | 2025-10-01 | 40/0 | DC2+0 | Sandy | 2025-09-29 | 2025-10-08 | Shobha Devi |  | 66.3811 | Derrick |  | 9
355 | 2025-10-01 | 10/1 | DA+0 | DRY | 2025-10-03 | 2025-10-10 | Priyanka Devi (Subodh) |  | 37.5044 | Derrick |  | 7
356 | 2025-10-01 | 55/0 | DB1+6 | Sandy | 2025-09-30 | 2025-10-11 | Sunny Construction |  | 67.8737 | Derrick |  | 11
357 | 2025-10-01 | 30/2 | DA+0 | Sandy | 2025-09-30 | 2025-10-12 | Jirwa Devi |  | 37.5044 | Derrick |  | 12
358 | 2025-10-01 | 35/4 | DA+0 | DRY | 2025-10-07 | 2025-10-13 | Nirmal Mahto |  | 37.5044 | Derrick |  | 6
359 | 2025-10-01 | 55/2 | DA+0 | WFR | 2025-10-12 | 2025-10-14 | Sunny Construction |  | 37.5044 | Derrick |  | 2
360 | 2025-10-01 | 37/1 | DA+9 | Sandy | 2025-10-10 | 2025-10-17 | Ganesh Sinha |  | 47.1844 | Derrick |  | 7
361 | 2025-10-01 | 39/0 | DB2+6 | Sandy | 2025-10-14 | 2025-10-18 | Shobha Devi |  | 67.8737 | Derrick |  | 4
362 | 2025-10-01 | 46/0 | DD60+25 | Sandy | 2025-09-29 | 2025-10-18 | Chinta Devi |  | 143.6019 | Derrick |  | 19
363 | 2025-10-01 | 35/2 | DB1+0 | Sandy | 2025-10-14 | 2025-10-22 | Nirmal Mahto |  | 57.5972 | Derrick |  | 8
364 | 2025-10-01 | 39/1 | DA+0 | Sandy | 2025-10-18 | 2025-10-22 | Shobha Devi |  | 37.5044 | Derrick |  | 4
365 | 2025-10-01 | 29/4 | DA+6 | DRY | 2025-10-13 | 2025-10-23 | Jirwa Devi |  | 45.413 | Derrick |  | 10
366 | 2025-10-01 | 37/2 | DA+3 | Sandy | 2025-10-18 | 2025-10-24 | Ganesh Sinha |  | 38.8476 | Derrick |  | 6
367 | 2025-10-01 | 11/4 | DA+0 | Sandy | 2025-10-17 | 2025-10-24 | Devi Construction |  | 37.5044 | Derrick |  | 7
368 | 2025-10-01 | 35/0 | DB2+6 | Sandy | 2025-10-16 | 2025-10-26 | Sanjeev Kumar |  | 67.8737 | Derrick |  | 10
369 | 2025-10-01 | 38/4 | DA+9 | Sandy | 2025-10-22 | 2025-10-26 | Shobha Devi |  | 47.1844 | Derrick |  | 4
370 | 2025-10-01 | 41/2 | DA+0 | Sandy | 2025-10-10 | 2025-10-27 | Vinay Construction |  | 37.5044 | Derrick |  | 17
371 | 2025-10-01 | 37/3 | DA+0 | Sandy | 2025-10-25 | 2025-10-30 | Ganesh Sinha |  | 37.5044 | Derrick |  | 5
372 | 2025-10-01 | 35/1 | DA+9 | Sandy | 2025-10-22 | 2025-10-31 | Nirmal Mahto |  | 47.1844 | Derrick |  | 9
373 | 2025-10-01 | 19/2 | DA+0 | DRY | 2025-10-20 | 2025-10-31 | Shri Shyam Construction |  | 37.5044 | Derrick |  | 11
374 | 2025-10-01 | 44/8 | DCT+0 | Sandy | 2025-10-18 | 2025-10-31 | Chinta Devi |  | 94.2199 | Derrick |  | 13
375 | 2025-10-01 | 38/0 | DB2+6 | Sandy | 2025-10-27 | 2025-10-31 | Shobha Devi |  | 67.8737 | Derrick |  | 4
376 | 2025-11-01 | 34/4 | DA+0 | Sandy | 2025-10-27 | 2025-11-04 | Sanjeev Kumar |  | 37.5044 | Derrick |  | 8
377 | 2025-11-01 | 40/1 | DA+6 | Sandy | 2025-11-01 | 2025-11-06 | Shobha Devi |  | 45.413 | Derrick |  | 5
378 | 2025-11-01 | 38/3 | DA+9 | Sandy | 2025-10-09 | 2025-11-07 | Shobha Devi |  | 47.1844 | Derrick |  | 29
379 | 2025-11-01 | 34/1 | DA+9 | Sandy | 2025-10-31 | 2025-11-07 | Nirmal Mahto |  | 47.1844 | Derrick |  | 7
380 | 2025-11-01 | 32/3 | DA+0 | Sandy | 2025-10-31 | 2025-11-07 | Ganesh Sinha |  | 37.5044 | Derrick |  | 7
381 | 2025-11-01 | 4/0 | DD60+6 | DRY | 2025-10-25 | 2025-11-08 | Devi Construction |  | 100.968 | Derrick |  | 14
382 | 2025-11-01 | 33/0 | DC1+0 | DRY | 2025-10-22 | 2025-11-08 | Santosh Singh |  | 66.3811 | Derrick |  | 17
383 | 2025-11-01 | 42/0 | DC1+0 | Sandy | 2025-10-27 | 2025-11-09 | Chinta Devi |  | 66.3811 | Derrick |  | 13
384 | 2025-11-01 | 42/2 | DA+6 | Sandy | 2025-10-27 | 2025-11-09 | Vinay Construction |  | 45.413 | Derrick |  | 13
385 | 2025-11-01 | 3/0 | DD60+6 | DRY | 2025-10-07 | 2025-11-10 | Panva Devi |  | 100.968 | Derrick |  | 34
386 | 2025-11-01 | 33/1 | DA+0 | DRY | 2025-11-05 | 2025-11-11 | Sanjeev Kumar |  | 37.5044 | Derrick |  | 6
387 | 2025-11-01 | 32/2 | DA+3 | DRY | 2025-11-08 | 2025-11-13 | Ganesh Sinha |  | 38.8476 | Derrick |  | 5
388 | 2025-11-01 | 29/2 | DA+3 | DRY | 2025-11-10 | 2025-11-13 | Chinta Devi |  | 38.8476 | Derrick |  | 3
389 | 2025-11-01 | 42/4 | DA+0 | Sandy | 2025-11-08 | 2025-11-14 | Shobha Devi |  | 37.5044 | Derrick |  | 6
390 | 2025-11-01 | 5/0 | DB1+9 | DRY | 2025-10-29 | 2025-11-16 | Kamlesh Kumar |  | 70.7017 | Derrick |  | 18
391 | 2025-11-01 | 42/3 | DA+0 | Sandy | 2025-11-15 | 2025-11-17 | Sobha Devi |  | 37.5044 | Derrick |  | 2
392 | 2025-11-01 | 28/1 | DA+0 | DRY | 2025-11-10 | 2025-11-17 | Chinta Devi |  | 37.5044 | Derrick |  | 7
393 | 2025-11-01 | 8/0 | DB1+0 | DRY | 2025-11-09 | 2025-11-18 | Devi Construction |  | 57.5972 | Derrick |  | 9
394 | 2025-11-01 | 32/4 | DA+0 | Sandy | 2025-11-11 | 2025-11-18 | Santosh Singh |  | 37.5044 | Derrick |  | 7
395 | 2025-11-01 | 32/0 | DC1+0 | DRY | 2025-11-08 | 2025-11-18 | Jirwa Devi |  | 66.3811 | Derrick |  | 10
396 | 2025-11-01 | 34/2 | DA+6 | Sandy | 2025-11-11 | 2025-11-21 | Sanjeev Kumar |  | 45.413 | Derrick |  | 10
397 | 2025-11-01 | 42/1 | DA+6 | Sandy | 2025-11-10 | 2025-11-21 | Vinay Construction |  | 45.413 | Derrick |  | 11
398 | 2025-11-01 | 38/2 | DA+6 | Sandy | 2025-11-18 | 2025-11-22 | Shobha Devi |  | 45.413 | Derrick |  | 4
399 | 2025-11-01 | 27/8 | DA+0 | DFR | 2025-11-18 | 2025-11-26 | Jirwa Devi |  | 37.5044 | Derrick |  | 8
400 | 2025-11-01 | 30/0 | DC1+0 | DRY | 2025-11-14 | 2025-11-26 | Ganesh Sinha |  | 66.3811 | Derrick |  | 12
401 | 2025-11-01 | 26/5 | DA+6 | Sandy | 2025-11-21 | 2025-11-27 | Chinta Devi |  | 45.413 | Derrick |  | 6
402 | 2025-11-01 | 8/3 | DA+0 | DRY | 2025-11-10 | 2025-11-27 | Priyanka Devi |  | 37.5044 | Derrick |  | 17
403 | 2025-11-01 | 7/0 | DB1+0 | DRY | 2025-11-19 | 2025-11-28 | Devi Construction |  | 57.5972 | Derrick |  | 9
404 | 2025-11-01 | 27/5 | DA+0 | DRY | 2025-11-08 | 2025-11-30 | Dular chand Patel |  | 37.5044 | Derrick |  | 22
405 | 2025-11-01 | 41/0 | DC1+6 | Sandy | 2025-11-23 | 2025-11-30 | Shobha Devi |  | 78.132 | Derrick |  | 7
406 | 2025-11-01 | 43/2 | DA+0 | Sandy | 2025-11-22 | 2025-11-30 | Vinay Construction |  | 37.5044 | Derrick |  | 8
407 | 2025-11-01 | 10/16 | DA+3 | DRY | 2025-11-17 | 2025-11-30 | Kamlesh Kumar |  | 38.8476 | Derrick |  | 13
408 | 2025-11-01 | 26/8 | DA+6 | DFR | 2025-11-26 | 2025-11-30 | Ganesh Sinha |  | 45.413 | Derrick |  | 4
409 | 2025-12-01 | 27/12 | DA+3 | Sandy | 2025-11-27 | 2025-12-04 | Jirwa Devi |  | 38.8476 | Derrick |  | 7
410 | 2025-12-01 | 34/0 | DB2+0 | DRY | 2025-11-22 | 2025-12-05 | Sanjeev Kumar |  | 57.5972 | Derrick |  | 13
411 | 2025-12-01 | 42/5 | DA+9 | Sandy | 2025-12-03 | 2025-12-06 | Shobha Devi |  | 47.1844 | Derrick |  | 3
412 | 2025-12-01 | 10/7 | DA+3 | DRY | 2025-11-28 | 2025-12-06 | Priyanka Devi |  | 38.8476 | Derrick |  | 8
413 | 2025-12-01 | 6/0 | DB2+9 | DRY | 2025-11-23 | 2025-12-07 | Panva Devi |  | 70.7017 | Derrick |  | 14
414 | 2025-12-01 | 43/4 | DA+3 | Sandy | 2025-12-03 | 2025-12-10 | Vinay Construction |  | 38.8476 | Derrick |  | 7
415 | 2025-12-01 | 10/22 | DA+0 | Sandy | 2025-10-04 | 2025-12-10 | Vedanta Construction |  | 37.5044 | Derrick |  | 67
416 | 2025-12-01 | 26/7 | DA+0 | DFR | 2025-12-07 | 2025-12-11 | Chinta Devi |  | 37.5044 | Derrick |  | 4
417 | 2025-12-01 | 38/1 | DA+0 | Sandy | 2025-12-07 | 2025-12-12 | Shobha Devi |  | 37.5044 | Derrick |  | 5
418 | 2025-12-01 | 11/1 | DA+0 | Sandy | 2025-12-05 | 2025-12-12 | Nirmal Mahto |  | 37.5044 | Derrick |  | 7
419 | 2025-12-01 | 10/10 | DA+3 | Sandy | 2025-12-07 | 2025-12-14 | Priyanka Devi |  | 38.8476 | Derrick |  | 7
420 | 2025-12-01 | 10/15 | DA+3 | DRY | 2025-12-03 | 2025-12-14 | Kamlesh Kumar |  | 38.8476 | Derrick |  | 11
421 | 2025-12-01 | 11A/8 | DA+6 | Sandy | 2025-12-05 | 2025-12-16 | Sheetal Singh |  | 45.413 | Derrick |  | 11
422 | 2025-12-01 | 10/23 | DA+0 | Sandy | 2025-12-11 | 2025-12-17 | Vedanta Construction |  | 37.5044 | Derrick |  | 6
423 | 2025-12-01 | 11/2 | DA+0 | Sandy | 2025-12-12 | 2025-12-18 | Nirmal Mahto |  | 37.5044 | Derrick |  | 6
424 | 2025-12-01 | 13/1 | DA+9 | DRY | 2025-12-13 | 2025-12-18 | Santosh Singh / Laxmi |  | 47.1844 | Derrick |  | 5
425 | 2025-12-01 | 27/9 | DA+0 | DFR | 2025-12-13 | 2025-12-19 | Ganesh Sinha |  | 37.5044 | Derrick |  | 6
426 | 2025-12-01 | 35/3 | DB1+6 | Sandy | 2025-12-13 | 2025-12-19 | Shobha Devi |  | 67.8737 | Derrick |  | 6
427 | 2025-12-01 | 27/7 | DB1+0 | DFR | 2025-12-12 | 2025-12-20 | Chinta Devi |  | 57.5972 | Derrick |  | 8
428 | 2025-12-01 | 28/7 | DA+3 | Sandy | 2025-12-10 | 2025-12-20 | Panva Devi |  | 38.8476 | Derrick |  | 10
429 | 2025-12-01 | 31/0 | DB2+0 | Sandy | 2025-12-16 | 2025-12-20 | Jirwa Devi |  | 57.5972 | Derrick |  | 4
430 | 2025-12-01 | 22/7 | DA+0 | Sandy | 2025-12-16 | 2025-12-21 | Sunny Construction |  | 37.5044 | Derrick |  | 5
431 | 2025-12-01 | 9/0 | DD60+18 | DRY | 2025-12-02 | 2025-12-22 | Devi Construction |  | 129.111 | Derrick |  | 20
432 | 2025-12-01 | 13/3 | DA+3 | Sandy | 2025-12-16 | 2025-12-23 | Vivek Ganju |  | 38.8476 | Derrick |  | 7
433 | 2025-12-01 | 19/4 | DA+0 | DRY | 2025-12-19 | 2025-12-24 | Vedanta Construction |  | 37.5044 | Derrick |  | 5
434 | 2025-12-01 | 28/3 | DA+0 | DFR | 2025-12-21 | 2025-12-24 | Chinta Devi |  | 37.5044 | Derrick |  | 3
435 | 2025-12-01 | 11/3 | DA+0 | Sandy | 2025-12-18 | 2025-12-25 | Nirmal Mahto |  | 37.5044 | Derrick |  | 7
436 | 2025-12-01 | 22/6 | DA+0 | Sandy | 2025-12-21 | 2025-12-26 | Sunny Construction |  | 37.5044 | Derrick |  | 5
437 | 2025-12-01 | 28/4 | DA+0 | Sandy | 2025-12-21 | 2025-12-27 | Ganesh Sinha |  | 37.5044 | Derrick |  | 6
438 | 2025-12-01 | 10/13 | DA+3 | DRY | 2025-12-15 | 2025-12-27 | Kamlesh Kumar |  | 38.8476 | Derrick |  | 12
439 | 2025-12-01 | 28/8 | DA+3 | Sandy | 2025-12-21 | 2025-12-28 | Panva Devi |  | 38.8476 | Derrick |  | 7
440 | 2025-12-01 | 13/4 | DA+3 | DRY | 2025-12-24 | 2025-12-30 | Vivek Ganju |  | 38.8476 | Derrick |  | 6
441 | 2025-12-01 | 19/3 | DA+0 | DRY | 2025-12-25 | 2025-12-30 | Vedanta Construction |  | 37.5044 | Derrick |  | 5
442 | 2025-12-01 | 30/4 | DA+3 | DRY | 2025-12-26 | 2025-12-30 | Chinta Devi |  | 38.8476 | Derrick |  | 4
443 | 2025-12-01 | 10/5 | DA+3 | DRY | 2025-12-25 | 2025-12-31 | Devi Construction |  | 38.8476 | Derrick |  | 6
444 | 2025-12-01 | 14/0 | DC2+0 | Sandy | 2025-12-17 | 2025-12-31 | Sheetal Singh |  | 66.3811 | Derrick |  | 14
445 | 2025-12-01 | 22/2 | DA+6 | Sandy | 2025-12-23 | 2025-12-31 | Vinay Gupta |  | 45.413 | Derrick |  | 8
446 | 2025-12-01 | 22/11 | DA+6 | Sandy | 2025-12-27 | 2025-12-31 | Shobha Devi |  | 45.413 | Derrick |  | 4
447 | 2025-12-01 | 22/5 | DA+9 | DRY | 2025-12-27 | 2025-12-31 | Sunny Construction |  | 47.1844 | Derrick |  | 4
448 | 2025-12-01 | 11/0 | DB1+0 | Sandy | 2025-11-25 | 2025-12-31 | Nirmal Mahto |  | 57.5972 | Derrick |  | 36
449 | 2026-01-01 | 27/6 | DA+0 | Sandy | 2025-12-04 | 2026-01-05 | Dular chand Patel |  | 37.5044 | Derrick |  | 32
450 | 2026-01-01 | 19/1 | DA+0 | DRY | 2025-12-31 | 2026-01-07 | Vedanta Construction |  | 37.5044 | Derrick |  | 7
451 | 2026-01-01 | 27/10 | DA+3 | DFR | 2025-12-28 | 2026-01-07 | Ganesh Sinha |  | 38.8476 | Derrick |  | 10
452 | 2026-01-01 | 28/6 | DA+6 | Sandy | 2025-12-29 | 2026-01-08 | Jirwa Devi |  | 45.413 | Derrick |  | 10
453 | 2026-01-01 | 22/3 | DA+9 | Sandy | 2026-01-03 | 2026-01-09 | Sunny Construction |  | 47.1844 | Derrick |  | 6
454 | 2026-01-01 | 22/13 | DA+6 | Sandy | 2026-01-03 | 2026-01-09 | Shobha Devi |  | 45.413 | Derrick |  | 6
455 | 2026-01-01 | 26/6 | DA+6 | Sandy | 2025-12-03 | 2026-01-11 | Chinta Devi |  | 45.413 | Derrick |  | 39
456 | 2026-01-01 | 25/2 | DA+0 | DRY | 2026-01-06 | 2026-01-13 | Chinta Devi |  | 37.5044 | Derrick |  | 7
457 | 2026-01-01 | 14A/2 | DA+0 | DRY | 2026-01-03 | 2026-01-14 | Sheetal Singh |  | 37.5044 | Derrick |  | 11
458 | 2026-01-01 | 25/1 | DA+3 | DRY | 2026-01-14 | 2026-01-18 | Chinta Devi |  | 38.8476 | Derrick |  | 4
459 | 2026-01-01 | 25/0 | DC1+6 | DRY | 2026-01-22 | 2026-01-30 | Chinta Devi |  | 78.132 | Derrick |  | 8
460 | 2026-02-01 | 26/4 | DA+6 | Sandy | 2026-01-30 | 2026-02-06 | Chinta Devi |  | 45.413 | Derrick |  | 7
461 | 2026-02-01 | 10/2 | DA+0 | DFR | 2026-02-16 | 2026-02-19 | Sunny Construction |  | 37.5044 | Derrick |  | 3
462 | 2026-02-01 | 8/8 | DA+6 | DRY | 2026-02-17 | 2026-02-22 | Shobha Devi |  | 45.413 | Derrick |  | 5
463 | 2026-02-01 | 8/11 | DA+0 | DRY | 2026-02-19 | 2026-02-24 | Sunny Construction |  | 37.5044 | Derrick |  | 5
|  |  | Loc No. |  | Start Date | Status | Gang Name |  |  | Erection Method | Status | Manpower
[7 empty] | Sunny Construction |  |  | Derrick | Moved to next locs
|  |  | 22/8 |  | 2026-02-16 |  | Sheetal Singh |  |  | Derrick
|  |  | 8/6 |  | 2026-02-17 |  | Shobha Devi |  |  | Derrick

## Tackwelding
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
List of Tackwelding Progress
Sl.No. | Loc. No. | Type of Tower | Start Date | Completion Date | Name of the Contractor | Tackwelding | Painting
1 | 59/13 | DA+3 | 2024-02-20 | 2024-02-20 | Suraja Ram | Done | Done
2 | 59/14 | DA+6 | 2024-02-22 | 2024-02-22 | Suraja Ram | Done | Done
3 | 62/5 | DA+0 | 2024-02-27 | 2024-02-27 | Suraja Ram | Done | Done
4 | 63/6 | DA+3 | 2024-02-28 | 2024-02-28 | Suraja Ram | Done | Done
5 | 63/8 | DA+3 | 2024-03-01 | 2024-03-02 | Suraja Ram | Done | Done
6 | 62/3 | DA+0 | 2024-02-03 | 2024-02-03 | Suraja Ram | Done | Done
7 | 62/4 | DA+3 | 2024-03-04 | 2024-03-04 | Suraja Ram | Done | Done
8 | 59/12 | DA+6 | 2024-03-05 | 2024-03-05 | Suraja Ram | Done | Done
9 | 59/10 | DA+0 | 2024-03-06 | 2024-03-06 | Suraja Ram | Done | Done
10 | 59/9 | DA+3 | 2024-03-07 | 2024-03-07 | Suraja Ram | Done | Done
11 | 60/7 | DA+3 | 2024-03-09 | 2024-03-09 | Suraja Ram | Done | Done
12 | 62/2 | DA+3 | 2024-03-10 | 2024-03-10 | Suraja Ram | Done | Done
13 | 62/7 | DA+3 | 2024-03-11 | 2024-03-11 | Suraja Ram | Done | Done
14 | 64/1 | DA+0 | 2024-03-12 | 2024-03-12 | Suraja Ram | Done | Done
15 | 59/7 | DA+3 | 2024-03-12 | 2024-03-12 | Ramagora | Done | Done
16 | 64/4 | DA+3 | 2024-03-13 | 2024-03-13 | Suraja Ram | Done | Done
17 | 60/11 | DA+3 | 2024-03-15 | 2024-03-15 | Ramagora | Done | Done
18 | 62/8 | DA+0 | 2024-03-15 | 2024-03-15 | Suraja Ram | Done | Done
19 | 65/2 | DA+0 | 2024-03-16 | 2024-03-16 | Suraja Ram | Done | Done
20 | 60/6 | DA+0 | 2024-03-16 | 2024-03-16 | Ramagora | Done | Done
21 | 65/4 | DA+0 | 2024-03-17 | 2024-03-17 | Suraja Ram | Done | Done
22 | 64/5 | DA+3 | 2024-03-18 | 2024-03-18 | Suraja Ram | Done | Done
23 | 62/9 | DA+3 | 2024-03-19 | 2024-03-19 | Suraja Ram | Done | Done
24 | 60/8 | DA+0 | 2024-03-19 | 2024-03-19 | Ramagora | Done | Done
25 | 62/10 | DA+0 | 2024-03-21 | 2024-03-21 | Suraja Ram | Done | Done
26 | 65/3 | DA+3 | 2024-03-22 | 2024-03-22 | Suraja Ram | Done | Done
27 | 59/6 | DA+3 | 2024-03-22 | 2024-03-22 | Ramagora | Done | Done
28 | 60/10 | DA+0 | 2024-03-24 | 2024-03-24 | Suraja Ram | Done | Done
29 | 61/6 | DA+3 | 2024-03-28 | 2024-03-28 | Suraja Ram | Done | Done
30 | 65/5 | DA+0 | 2024-03-29 | 2024-03-29 | Suraja Ram | Done | Done
31 | 64/6 | DA+0 | 2024-04-01 | 2024-04-01 | Suraja Ram | Done | Done
32 | 61/7 | DA+9 | 2024-04-03 | 2024-04-03 | Suraja Ram | Done | Done
33 | 65/6 | DA+0 | 2024-04-04 | 2024-04-04 | Suraja Ram | Done | Done
34 | 64/7 | DA+3 | 2024-04-06 | 2024-04-06 | Suraja Ram | Done | Done
35 | 63/7 | DA+3 | 2024-04-21 | 2024-04-22 | Suraja Ram | Done | Done
36 | 64/9 | DA+3 | 2024-04-24 | 2024-04-24 | Suraja Ram | Done | Done
37 | 61/0 | DB2+0 | 2024-04-25 | 2024-04-25 | Ramagora | Done | Done
38 | 65/9 | DA+0 | 2024-04-27 | 2024-04-27 | Suraja Ram | Done | Done
39 | 65/11 | DA+0 | 2024-04-28 | 2024-04-28 | Suraja Ram | Done | Done
40 | 67/2 | DA+0 | 2024-04-29 | 2024-04-29 | Suraja Ram | Done | Done
41 | 61/2 | DA+6 | 2024-04-29 | 2024-04-30 | Ramagora | Done | Done
42 | 64/10 | DA+3 | 2024-05-05 | 2024-05-05 | Suraja Ram | Done | Done
43 | 67/1 | DA+0 | 2024-05-07 | 2024-05-07 | Suraja Ram | Done | Done
44 | 64/8 | DA+3 | 2024-05-09 | 2024-05-09 | Suraja Ram | Done | Done
45 | 65/1 | DA+0 | 2024-05-10 | 2024-05-10 | Suraja Ram | Done | Done
46 | 65/0 | DB1+0 | 2024-05-10 | 2024-05-10 | Suraja Ram | Done | Done
47 | 61/1 | DA+6 | 2024-05-10 | 2024-05-10 | Ramagora | Done | Done
48 | 60/9 | DA+3 | 2024-05-11 | 2024-05-11 | Ramagora | Done | Done
49 | 63/4 | DA+0 | 2024-05-14 | 2024-05-14 | Suraja Ram | Done | Done
50 | 63/3 | DA+3 | 2024-05-15 | 2024-05-15 | Suraja Ram | Done | Done
51 | 63/5 | DA+3 | 2024-05-16 | 2024-05-16 | Suraja Ram | Done | Done
52 | 61/3 | DA+6 | 2024-05-17 | 2024-05-17 | Ramagora | Done | Done
53 | 62/11 | DA+3 | 2024-05-19 | 2024-05-19 | Suraja Ram | Done | Done
54 | 61/4 | DA+3 | 2024-05-23 | 2024-05-23 | Suraja Ram | Done | Done
55 | 61/5 | DA+3 | 2024-05-25 | 2024-05-25 | Suraja Ram | Done | Done
56 | 64/2 | DA+3 | 2024-06-03 | 2024-06-03 | Suraja Ram | Done | Done
57 | 64/3 | DA+0 | 2024-06-06 | 2024-06-06 | Suraja Ram | Done | Done
58 | 64/0 | DB2+0 | 2024-06-06 | 2024-06-06 | Suraja Ram | Done | Done
59 | 61/10 | DA+9 | 2024-06-07 | 2024-06-07 | Suraja Ram | Done | Done
60 | 61/8 | DA+6 | 2024-06-08 | 2024-06-08 | Ramagora | Done | Done
61 | 63/2 | DA+0 | 2024-06-08 | 2024-06-08 | Suraja Ram | Done | Done
62 | 61/9 | DA+0 | 2024-06-09 | 2024-06-09 | Ramagora | Done | Done
63 | 63/1 | DA+3 | 2024-06-09 | 2024-06-09 | Suraja Ram | Done | Done
64 | 59/5 | DA+3 | 2024-06-10 | 2024-06-10 | Ramagora | Done | Done
65 | 63/0 | DC1+0 | 2024-06-10 | 2024-06-11 | Suraja Ram | Done | Done
66 | 60/5 | DA+3 | 2024-06-11 | 2024-06-11 | Ramagora | Done | Done
67 | 60/4 | DA+3 | 2024-06-13 | 2024-06-13 | Ramagora | Done | Done
68 | 60/3 | DA+3 | 2024-06-23 | 2024-06-23 | Ramagora | Done | Done
69 | 60/2 | DA+3 | 2024-06-25 | 2024-06-25 | Ramagora | Done | Done
70 | 60/1 | DA+6 | 2024-06-30 | 2024-06-30 | Ramagora | Done | Done
71 | 59/16 | DA+9 | 2024-07-01 | 2024-07-01 | Suraja Ram | Done | Done
72 | 59/15 | DA+6 | 2024-07-02 | 2024-07-02 | Suraja Ram | Done | Done
73 | 60/0 | DC1+0 | 2024-07-24 | 2024-07-24 | Suraja Ram | Done | Done
74 | 59/8 | DB1+3 | 2024-07-27 | 2024-07-27 | Suraja Ram | Done | Done
75 | 55/3 | DA+0 | 2024-08-23 | 2024-08-23 | Suraja Ram | Done | Done
76 | 55/4 | DA+0 | 2024-08-24 | 2024-08-24 | Suraja Ram | Done | Done
77 | 57/6 | DA+3 | 2024-08-27 | 2024-08-27 | Suraja Ram | Done | Done
78 | 57/3 | DA+0 | 2024-08-28 | 2024-08-28 | Suraja Ram | Done | Done
79 | 57/4 | DA+0 | 2024-08-30 | 2024-08-30 | Suraja Ram | Done | Done
80 | 57/5 | DA+3 | 2024-08-30 | 2024-08-30 | Suraja Ram | Done | Done
81 | 62/0 | DB2+0 | 2024-09-15 | 2024-09-15 | Suraja Ram | Done | Done
82 | 62/1 | DA+3 | 2024-09-23 | 2024-09-24 | Suraja Ram | Done | Done
83 | 62/6 | DA+3 | 2024-09-25 | 2024-09-26 | Suraja Ram | Done | Done
84 | 57/7 | DA+3 | 2024-10-05 | 2024-10-06 | Suraja Ram | Done | Done
85 | 50/9 | DA+0 | 2024-10-06 | 2024-10-07 | Suraja Ram | Done | Done
86 | 50/10 | DA+0 | 2024-10-09 | 2024-10-09 | Suraja Ram | Done | Done
87 | 50/0 | DB2+0 | 2024-10-10 | 2024-10-10 | Suraja Ram | Done | Done
88 | 50/3 | DA+6 | 2024-10-24 | 2024-10-24 | Suraja Ram | Done | Done
89 | 50/1 | DA+6 | 2024-10-25 | 2024-10-25 | Suraja Ram | Done | Done
90 | 51/1 | DA+0 | 2024-10-25 | 2024-10-25 | Suraja Ram | Done | Done
91 | 16/3 | DA+3 | 2024-10-26 | 2024-10-26 | R&A | Done
92 | 50/2 | DA+9 | 2024-10-28 | 2024-10-28 | Suraja Ram | Done | Done
93 | 64/11 | DA+3 | 2024-10-29 | 2024-10-29 | Suraja Ram | Done | Done
94 | 15/1 | DA+3 | 2024-10-26 | 2024-10-29 | SB Enterprises | Done
95 | 16/4 | DA+0 | 2024-11-10 | 2024-11-10 | SB Enterprises | Done
96 | 59/11 | DA+6 | 2024-11-11 | 2024-11-11 | Suraja Ram | Done | Done
97 | 18/1 | DA+0 | 2024-11-12 | 2024-11-12 | SB Enterprises | Done
98 | 50/7 | DA+0 | 2024-11-14 | 2024-11-14 | Suraja Ram | Done | Done
99 | 73/1 | DA+0 | 2024-11-14 | 2024-11-14 | Suraja Ram | Done | Done
100 | 73/2 | DA+0 | 2024-11-19 | 2024-11-19 | Suraja Ram | Done | Done
101 | 73/9 | DA+0 | 2024-11-20 | 2024-11-20 | Suraja Ram | Done | Done
102 | 52/7 | DA+3 | 2024-11-25 | 2024-11-25 | Suraja Ram | Done | Done
103 | 52/6 | DA+6 | 2024-11-25 | 2024-11-25 | Suraja Ram | Done | Done
104 | 52/8 | DA+6 | 2024-11-26 | 2024-11-26 | Suraja Ram | Done | Done
105 | 48/0 | DC2+0 | 2024-11-27 | 2024-11-27 | Suraja Ram | Done | Done
106 | 49/4 | DA+3 | 2024-11-27 | 2024-11-27 | Suraja Ram | Done | Done
107 | 48/1 | DA+9 | 2024-11-29 | 2024-11-29 | Suraja Ram | Done | Done
108 | 47/10 | DA+6 | 2024-11-29 | 2024-11-29 | Suraja Ram | Done | Done
109 | 49/7 | DA+0 | 2024-12-02 | 2024-12-02 | Suraja Ram | Done | Done
110 | 49/6 | DA+0 | 2024-12-03 | 2024-12-03 | Suraja Ram | Done | Done
111 | 49/5 | DA+3 | 2024-12-04 | 2024-12-04 | Suraja Ram | Done | Done
112 | 59/3 | DA+3 | 2024-12-05 | 2024-12-05 | Suraja Ram | Done | Done
113 | 59/4 | DA+3 | 2024-12-06 | 2024-12-06 | Suraja Ram | Done | Done
114 | 73/6 | DA+0 | 2024-12-13 | 2024-12-13 | Suraja Ram | Done | Done
115 | 72/3 | DA+3 | 2024-12-17 | 2024-12-17 | Suraja Ram | Done | Done
116 | 59/1 | DA+3 | 2024-12-18 | 2024-12-18 | Suraja Ram | Done | Done
117 | 59/2 | DA+3 | 2024-12-20 | 2024-12-20 | Suraja Ram | Done | Done
118 | 50/8 | DA+9 | 2024-12-23 | 2024-12-23 | Suraja Ram | Done | Done
119 | 73/8 | DA+3 | 2024-12-25 | 2024-12-25 | Suraja Ram | Done | Done
120 | 51/2 | DA+0 | 2024-12-26 | 2024-12-26 | Suraja Ram | Done | Done
121 | 49/2 | DA+3 | 2024-12-26 | 2024-12-26 | Suraja Ram | Done | Done
122 | 49/3 | DA+3 | 2024-12-26 | 2024-12-26 | Suraja Ram | Done | Done
123 | 49/1 | DA+0 | 2024-12-28 | 2024-12-28 | Suraja Ram | Done | Done
124 | 50/4 | DA+9 | 2025-01-06 | 2025-01-06 | Suraja Ram | Done | Done
125 | 59/0 | DC2+0 | 2025-01-07 | 2025-01-07 | Suraja Ram | Done | Done
126 | 50/6 | DA+9 | 2025-01-12 | 2025-01-12 | Suraja Ram | Done | Done
127 | 65/7 | DA+0 | 2025-01-17 | 2025-01-17 | Suraja Ram | Done | Done
128 | 65/8 | DA+0 | 2025-01-18 | 2025-01-18 | Suraja Ram | Done | Done
129 | 73/3 | DA+0 | 2025-01-27 | 2025-01-27 | Suraja Ram | Done | Done
130 | 73/4 | DA+0 | 2025-01-28 | 2025-01-29 | Suraja Ram | Done | Done
131 | 73/7 | DA+0 | 2025-02-13 | 2025-02-13 | Suraja Ram | Done | Done
132 | 74/0 | DB2+0 | 2025-02-14 | 2025-02-14 | Suraja Ram | Done | Done
133 | 73/5 | DA+0 | 2025-02-15 | 2025-02-15 | Suraja Ram | Done | Done
134 | 65/10 | DA+0 | 2025-02-17 | 2025-02-17 | Suraja Ram | Done | Done
135 | 66/0 | DC2+6 | 2025-02-19 | 2025-02-19 | Suraja Ram | Done | Done
136 | 51/0 | DC2+0 | 2025-02-26 | 2025-02-26 | Suraja Ram | Done | Done
137 | 50/5 | DA+9 | 2025-03-02 | 2025-03-02 | Suraja Ram | Done | Done
138 | 52/0 | DC2+0 | 2025-03-05 | 2025-03-05 | Suraja Ram | Done | Done
139 | 49/0 | DD45+0 | 2025-03-10 | 2025-03-10 | Suraja Ram | Done | Done
140 | 52/9 | DA+3 | 2025-03-11 | 2025-03-11 | Suraja Ram | Done | Done
141 | 52/10 | DA+9 | 2025-03-12 | 2025-03-12 | Suraja Ram | Done | Done
142 | 73/0 | DB2+0 | 2025-03-13 | 2025-03-13 | Suraja Ram | Done | Done
143 | 52/5 | DA+9 | 2025-03-17 | 2025-03-17 | Suraja Ram | Done | Done
144 | 47/9 | DA+3 | 2025-04-16 | 2025-04-16 | Suraja Ram | Done
145 | 47/8 | DA+0 | 2025-04-16 | 2025-04-16 | Suraja Ram | Done
146 | 58/0 | DC1+3 | 2025-04-21 | 2025-04-21 | Suraja Ram | Done
147 | 72/2 | DA+0 | 2025-04-28 | 2025-04-28 | Suraja Ram | Done | Done
148 | 72/1 | DA+3 | 2025-04-29 | 2025-04-29 | Suraja Ram | Done | Done
149 | 71/8 | DA+3 | 2025-04-30 | 2025-04-30 | Suraja Ram | Done | Done
150 | 71/7 | DA+3 | 2025-04-30 | 2025-04-30 | Suraja Ram | Done | Done
151 | 70/5 | DA+3 | 2025-05-02 | 2025-05-02 | Suraja Ram | Done | Done
152 | 71/6 | DA+0 | 2025-05-02 | 2025-05-02 | Suraja Ram | Done | Done
153 | 70/3 | DA+3 | 2025-05-03 | 2025-05-03 | Suraja Ram | Done | Done
154 | 55/5 | DA+0 | 2025-05-05 | 2025-05-05 | Suraja Ram | Done | Done
155 | 55/6 | DA+0 | 2025-05-06 | 2025-05-06 | Suraja Ram | Done | Done
156 | 71/5 | DA+3 | 2025-05-10 | 2025-05-10 | Suraja Ram | Done | Done
157 | 70/4 | DA+3 | 2025-05-11 | 2025-05-11 | Suraja Ram | Done | Done
158 | 71/3 | DA+6 | 2025-05-16 | 2025-05-16 | Suraja Ram | Done | Done
159 | 71/4 | DA+3 | 2025-05-17 | 2025-05-17 | Suraja Ram | Done | Done
160 | 71/2 | DA+3 | 2025-05-19 | 2025-05-19 | Suraja Ram | Done | Done
161 | 71/1 | DA+3 | 2025-05-20 | 2025-05-20 | Suraja Ram | Done | Done
162 | 70/11 | DA+3 | 2025-05-24 | 2025-05-24 | Suraja Ram | Done | Done
163 | 71/0 | DB2+3 | 2025-05-26 | 2025-05-26 | Suraja Ram | Done | Done
164 | 70/9 | DA+3 | 2025-05-27 | 2025-05-27 | Suraja Ram | Done | Done
165 | 70/10 | DA+3 | 2025-05-28 | 2025-05-28 | Suraja Ram | Done | Done
166 | 68/0 | DD45+0 | 2025-06-04 | 2025-06-04 | Suraja Ram | Done | Done
167 | 67/0 | DC1+9 | 2025-06-10 | 2025-06-10 | Suraja Ram | Done | Done
168 | 16/2 | DA+0 | 2025-06-10 | 2025-06-10 | Chanda Enterprises | Done
169 | 17/0 | DB2+3 | 2025-06-10 | 2025-06-10 | Chanda Enterprises | Done
170 | 70/6 | DA+3 | 2025-07-13 | 2025-07-14 | Suraja Ram | Done
171 | 53/3 | DA+6 | 2025-07-23 | 2025-07-23 | Suraja Ram | Done
172 | 72/0 | DB2+3 | 2025-07-23 | 2025-07-23 | Suraja Ram | Done | Done
173 | 10/14 | DA+3 | 2025-07-23 | 2025-07-23 | Shiv Power | Done | Done
174 | 55/7 | DA+0 | 2025-08-29 | 2025-08-29 | Suraja Ram | Done | Done
175 | 55/8 | DA+6 | 2025-09-01 | 2025-09-01 | Suraja Ram | Done | Done
176 | 57/1 | DA+0 | 2025-09-02 | 2025-09-02 | Suraja Ram | Done
177 | 57/2 | DA+3 | 2025-09-02 | 2025-09-02 | Suraja Ram | Done
178 | 55/1 | DA+0 | 2025-09-03 | 2025-09-03 | Suraja Ram | Done | Done
179 | 1A/0 | DD60+0 | 2025-09-02 | 2025-09-02 | B.S. Infra | Done | Done
180 | 1A/1 | DA+6 | 2025-09-03 | 2025-09-03 | B.S. Infra | Done | Done
181 | 1A/3 | DA+0 | 2025-09-04 | 2025-09-04 | B.S. Infra | Done | Done
182 | 1A/4 | DA+3 | 2025-09-05 | 2025-09-05 | B.S. Infra | Done | Done
183 | 1A/5 | DA+0 | 2025-09-06 | 2025-09-06 | B.S. Infra | Done | Done
184 | 1A/6 | DA+0 | 2025-09-07 | 2025-09-07 | B.S. Infra | Done | Done
185 | 1A/8 | DA+0 | 2025-09-08 | 2025-09-08 | B.S. Infra | Done | Done
186 | 2/0 | DC1+0 | 2025-09-09 | 2025-09-09 | B.S. Infra | Done | Done
187 | 54/3 | DA+6 | 2025-09-24 | 2025-09-24 | Suraja Ram | Done
188 | 70/8 | DA+3 | 2025-10-08 | 2025-10-08 | Suraja Ram | Done | Done
189 | 70/7 | DA+3 | 2025-10-14 | 2025-10-14 | Suraja Ram | Done | Done
190 | 54/4 | DA+9 | 2025-10-15 | 2025-10-15 | Suraja Ram | Done | Done
191 | 54/5 | DA+9 | 2025-10-16 | 2025-10-16 | Suraja Ram | Done | Done
192 | 44/11 | DA+0 | 2025-10-17 | 2025-10-17 | Suraja Ram | Done | Done
193 | 45/1 | DA+9 | 2025-10-18 | 2025-10-18 | Suraja Ram | Done | Done
194 | 2/1 | DA+3 | 2025-10-19 | 2025-10-19 | Shiv Power | Done | Done
195 | 2/2 | DA+3 | 2025-10-22 | 2025-10-22 | Shiv Power | Done | Done
196 | 2/3 | DA+3 | 2025-10-23 | 2025-10-23 | Shiv Power | Done | Done
197 | 10/3 | DA+0 | 2025-10-25 | 2025-10-25 | Shiv Power | Done | Done
198 | 10/4 | DA+3 | 2025-10-26 | 2025-10-26 | Shiv Power | Done | Done
199 | 10/6 | DA+0 | 2025-10-27 | 2025-10-27 | Shiv Power | Done | Done
200 | 10/12 | DB1+0 | 2025-10-28 | 2025-10-28 | Shiv Power | Done | Done
201 | 11/5 | DA+0 | 2025-10-29 | 2025-10-29 | Shiv Power | Done | Done
202 | 11A/0 | DB1+0 | 2025-10-30 | 2025-10-30 | Shiv Power | Done
203 | 11A/9 | DA+3 | 2025-10-31 | 2025-10-31 | Shiv Power | Done | Done
204 | 52/4 | DA+9 | 2025-11-07 | 2025-11-07 | Suraja Ram | Done
205 | 52/1 | DA+6 | 2025-11-07 | 2025-11-07 | Suraja Ram | Done
206 | 52/2 | DA+6 | 2025-11-07 | 2025-11-07 | Suraja Ram | Done
207 | 38/4 | DA+9 | 2025-11-12 | 2025-11-12 | Suraja Ram | Done
208 | 39/1 | DA+0 | 2025-11-14 | 2025-11-14 | Suraja Ram | Done
209 | 40/0 | DC2+0 | 2025-11-15 | 2025-11-15 | Suraja Ram | Done | Done
210 | 30/1 | DA+0 | 2025-11-16 | 2025-11-16 | Jai Bagrangbali | Done | Done
211 | 29/4 | DA+6 | 2025-11-17 | 2025-11-17 | Jai Bagrangbali | Done | Done
212 | 30/2 | DA+0 | 2025-11-18 | 2025-11-18 | Jai Bagrangbali | Done | Done
213 | 30/3 | DA+3 | 2025-11-18 | 2025-11-18 | Jai Bagrangbali | Done | Done
214 | 30/5 | DA+3 | 2025-11-19 | 2025-11-19 | Jai Bagrangbali | Done | Done
215 | 31/1 | DA+0 | 2025-11-19 | 2025-11-19 | Jai Bagrangbali | Done | Done
216 | 31/2 | DA+0 | 2025-11-19 | 2025-11-19 | Jai Bagrangbali | Done | Done
217 | 32/1 | DA+3 | 2025-11-19 | 2025-11-19 | Jai Bagrangbali | Done | Done
218 | 28/2 | DA+0 | 2025-11-26 | 2025-11-26 | Jai Bagrangbali | Done | Done
219 | 28/0 | DB2+0 | 2025-11-27 | 2025-11-27 | Jai Bagrangbali | Done | Done
220 | 27/3 | DA+3 | 2025-11-27 | 2025-11-27 | Jai Bagrangbali | Done | Done
221 | 27/2 | DA+3 | 2025-11-27 | 2025-11-27 | Jai Bagrangbali | Done | Done
222 | 70/0 | DC1+0 | 2025-11-30 | 2025-11-30 | Suraja Ram | Done | Done
223 | 38/3 | DA+9 | 2025-12-04 | 2025-12-04 | Suraja Ram | Done | Done
224 | 28/5 | DA+9 | 2025-12-07 | 2025-12-07 | Jai Bagrangbali | Done | Done
225 | 33/0 | DC1+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
226 | 33/1 | DA+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
227 | 34/1 | DA+9 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
228 | 34/3 | DA+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
229 | 35/0 | DB2+6 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
230 | 35/1 | DA+9 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
231 | 35/2 | DB1+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
232 | 38/0 | DB2+6 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
233 | 39/0 | DB2+6 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
234 | 41/0 | DC1+6 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
235 | 42/0 | DC1+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
236 | 42/3 | DA+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
237 | 42/4 | DA+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
238 | 42/5 | DA+9 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
239 | 53/2 | DA+0 | 2025-12-09 | 2025-12-09 | Suraja Ram | Done | Done
240 | 54/2 | DA+3 | 2025-12-10 | 2025-12-10 | Suraja Ram | Done | Done
241 | 69/0 | DB2+0 | 2025-12-11 | 2025-12-11 | Suraja Ram | Done | Done
242 | 69/1 | DA+3 | 2025-12-12 | 2025-12-12 | Suraja Ram | Done | Done
243 | 70/1 | DA+3 | 2025-12-13 | 2025-12-13 | Suraja Ram | Done | Done
244 | 70/2 | DA+3 | 2025-12-14 | 2025-12-14 | Suraja Ram | Done | Done
245 | 2/5 | DA+3 | 2025-12-15 | 2025-12-15 | Shiv Power | Done | Done
246 | 2/6 | DA+3 | 2025-12-16 | 2025-12-16 | Shiv Power | Done | Done
247 | 2/8 | DA+0 | 2025-12-17 | 2025-12-17 | Shiv Power | Done | Done
248 | 8/10 | DA+3 | 2025-12-18 | 2025-12-18 | Jai Bagrangbali | Done | Done
249 | 16/5 | DA+3 | 2025-12-19 | 2025-12-19 | Vendor Name not confirmed by Section incharge | Done | Done
250 | 27/1 | DA+3 | 2025-12-20 | 2025-12-20 | Jai Bagrangbali | Done | Done
251 | 27/4 | DA+3 | 2025-12-21 | 2025-12-21 | Jai Bagrangbali | Done | Done
252 | 27/8 | DA+0 | 2025-12-22 | 2025-12-22 | Jai Bagrangbali | Done | Done
253 | 27/11 | DA+3 | 2025-12-23 | 2025-12-23 | Jai Bagrangbali | Done | Done
254 | 28/1 | DA+0 | 2025-12-24 | 2025-12-24 | Jai Bagrangbali | Done | Done
255 | 32/0 | DC1+0 | 2025-12-25 | 2025-12-25 | Jai Bagrangbali | Done | Done
256 | 32/2 | DA+3 | 2025-12-26 | 2025-12-26 | Jai Bagrangbali | Done | Done
257 | 29/2 | DA+3 | 2025-12-27 | 2025-12-27 | Jai Bagrangbali | Done | Done
258 | 6/1 | DA+0 | 2026-01-02 | 2026-01-02 | Jai Bagrangbali | Done | Done
259 | 6/2 | DA+0 | 2026-01-02 | 2026-01-02 | Jai Bagrangbali | Done | Done
260 | 5/0 | DB1+9 | 2026-01-03 | 2026-01-03 | Jai Bagrangbali | Done | Done
261 | 8/0 | DB1+0 | 2026-01-04 | 2026-01-04 | Jai Bagrangbali | Done | Done
262 | 4/1 | DA+0 | 2026-01-05 | 2026-01-05 | Jai Bagrangbali | Done | Done
263 | 4/0 | DD60+6 | 2026-01-06 | 2026-01-06 | Jai Bagrangbali | Done | Done
264 | 10/16 | DA+3 | 2026-01-08 | 2026-01-08 | Jai Bagrangbali | Done | Done
265 | 2/4 | DA+3 | 2026-01-08 | 2026-01-08 | Shiv Power | Done | Done
266 | 2/7 | DA+3 | 2026-01-08 | 2026-01-08 | Shiv Power | Done
267 | 2/9 | DA+0 | 2026-01-08 | 2026-01-08 | Shiv Power | Done | Done
268 | 10/8 | DA+3 | 2026-01-08 | 2026-01-08 | Shiv Power | Done
269 | 10/17 | DA+3 | 2026-01-08 | 2026-01-08 | Jai Bagrangbali | Done | Done
270 | 10/18 | DA+3 | 2026-01-08 | 2026-01-08 | Jai Bagrangbali | Done | Done
271 | 32/3 | DA+0 | 2026-01-09 | 2026-01-09 | The Shraddha Cooperative Multipurpose Society Limited | Done
272 | 32/4 | DA+0 | 2026-01-13 | 2026-01-13 | The Shraddha Cooperative Multipurpose Society Limited | Done
273 | 26/8 | DA+6 | 2026-01-16 | 2026-01-16 | The Shraddha Cooperative Multipurpose Society Limited | Done
274 | 34/0 | DB2+0 | 2026-01-06 | 2026-01-06 | Suraja Ram | Done | Done
275 | 34/2 | DA+6 | 2026-01-07 | 2026-01-07 | Suraja Ram | Done | Done
276 | 44/1 | DA+0 | 2026-01-08 | 2026-01-08 | Suraja Ram | Done | Done
277 | 44/3 | DA+0 | 2026-01-09 | 2026-01-09 | Suraja Ram | Done | Done
278 | 44/4 | DA+9 | 2026-01-10 | 2026-01-10 | Suraja Ram | Done | Done
279 | 44/5 | DA+9 | 2026-01-11 | 2026-01-11 | Suraja Ram | Done | Done
280 | 44/7 | DA+9 | 2026-01-12 | 2026-01-12 | Suraja Ram | Done | Done
281 | 46/0 | DD60+25 | 2026-01-13 | 2026-01-13 | Suraja Ram | Done | Done
282 | 47/0 | DD60+25 | 2026-01-14 | 2026-01-14 | Suraja Ram | Done | Done
283 | 47/1 | DA+3 | 2026-01-15 | 2026-01-15 | Suraja Ram | Done | Done
284 | 47/2 | DA+9 | 2026-01-16 | 2026-01-16 | Suraja Ram | Done | Done
285 | 47/3 | DA+9 | 2026-01-17 | 2026-01-17 | Suraja Ram | Done | Done
286 | 47/4 | DA+3 | 2026-01-18 | 2026-01-18 | Suraja Ram | Done | Done
287 | 47/6 | DA+3 | 2026-01-19 | 2026-01-19 | Suraja Ram | Done | Done
288 | 47/7 | DA+3 | 2026-01-20 | 2026-01-20 | Suraja Ram | Done | Done
289 | 35/3 | DB1+6 | 2026-01-21 | 2026-01-21 | Suraja Ram | Done | Done
290 | 35/4 | DA+0 | 2026-01-22 | 2026-01-22 | Suraja Ram | Done | Done
291 | 35/5 | DA+0 | 2026-01-23 | 2026-01-23 | Suraja Ram | Done | Done
292 | 36/0 | DB2+0 | 2026-01-24 | 2026-01-24 | Suraja Ram | Done | Done
293 | 36/1 | DA+3 | 2026-01-25 | 2026-01-25 | Suraja Ram | Done | Done
294 | 36/2 | DA+0 | 2026-01-27 | 2026-01-27 | Suraja Ram | Done | Done
295 | 40/2 | DA+3 | 2026-01-28 | 2026-01-28 | Suraja Ram | Done | Done
296 | 8/2 | DA+3 | 2026-02-01 | 2026-02-01 | Jai Bagrangbali | Done | Done
297 | 8/3 | DA+0 | 2026-02-02 | 2026-02-02 | Jai Bagrangbali | Done | Done
298 | 25/4 | DA+0 | 2026-02-02 | 2026-02-02 | The Shraddha Cooperative Multipurpose Society Limited | Done
299 | 25/1 | DA+3 | 2026-02-02 | 2026-02-02 | The Shraddha Cooperative Multipurpose Society Limited | Done
300 | 1/0 | DD60+0 | 2026-02-03 | 2026-02-03 | Jai Bagrangbali | Done | Done
301 | 1A/2 | DA+0 | 2026-02-03 | 2026-02-03 | Shiv Power | Done | Done
302 | 1A/7 | DA+3 | 2026-02-03 | 2026-02-03 | Shiv Power | Done | Done
303 | 3/0 | DD60+6 | 2026-02-03 | 2026-02-03 | Jai Bagrangbali | Done | Done
304 | 4/2 | DA+0 | 2026-02-03 | 2026-02-03 | Jai Bagrangbali | Done | Done
305 | 4/3 | DA+0 | 2026-02-04 | 2026-02-04 | Jai Bagrangbali | Done | Done
306 | 4/4 | DA+0 | 2026-02-04 | 2026-02-04 | Jai Bagrangbali | Done | Done
307 | 6/0 | DB2+9 | 2026-02-04 | 2026-02-04 | Jai Bagrangbali | Done | Done
308 | 7/0 | DB1+0 | 2026-02-04 | 2026-02-04 | Jai Bagrangbali | Done | Done
309 | 8/1 | DA+3 | 2026-02-05 | 2026-02-05 | Jai Bagrangbali | Done | Done
310 | 8/9 | DA+3 | 2026-02-05 | 2026-02-05 | Shiv Power | Done | Done
311 | 10/1 | DA+0 | 2026-02-05 | 2026-02-05 | Jai Bagrangbali | Done | Done
312 | 10/5 | DA+3 | 2026-02-05 | 2026-02-05 | Jai Bagrangbali | Done | Done
313 | 10/13 | DA+3 | 2026-02-05 | 2026-02-05 | Jai Bagrangbali | Done | Done
314 | 10/15 | DA+3 | 2026-02-05 | 2026-02-05 | Jai Bagrangbali | Done | Done
315 | 10/19 | DA+0 | 2026-02-06 | 2026-02-06 | Jai Bagrangbali | Done | Done
316 | 10/20 | DA+3 | 2026-02-06 | 2026-02-06 | Jai Bagrangbali | Done | Done
317 | 10/21 | DA+3 | 2026-02-06 | 2026-02-06 | Jai Bagrangbali | Done | Done
318 | 10/22 | DA+0 | 2026-02-06 | 2026-02-06 | Jai Bagrangbali | Done | Done
319 | 10/23 | DA+0 | 2026-02-06 | 2026-02-06 | Jai Bagrangbali | Done | Done
320 | 25/2 | DA+0 | 2026-02-07 | 2026-02-07 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
321 | 27/5 | DA+0 | 2026-02-07 | 2026-02-07 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
322 | 36/3 | DA+0 | 2026-02-07 | 2026-02-07 | Suraja Ram | Done | Done
323 | 36/4 | DA+6 | 2026-02-07 | 2026-02-07 | Suraja Ram | Done | Done
324 | 40/1 | DA+6 | 2026-02-08 | 2026-02-08 | Suraja Ram | Done | Done
325 | 40/3 | DA+3 | 2026-02-08 | 2026-02-08 | Suraja Ram | Done | Done
326 | 41/1 | DB1+9 | 2026-02-08 | 2026-02-08 | Suraja Ram | Done | Done
327 | 41/2 | DA+0 | 2026-02-09 | 2026-02-09 | Suraja Ram | Done | Done
328 | 42/1 | DA+6 | 2026-02-09 | 2026-02-09 | Suraja Ram | Done | Done
329 | 42/2 | DA+6 | 2026-02-09 | 2026-02-09 | Suraja Ram | Done | Done
330 | 42/6 | DA+0 | 2026-02-10 | 2026-02-10 | Suraja Ram | Done | Done
331 | 43/0 | DB1+0 | 2026-02-10 | 2026-02-10 | Suraja Ram | Done | Done
332 | 11/1 | DA+0 | 2026-02-10 | 2026-02-10 | Shiv Power | Done | Done
333 | 11/2 | DA+0 | 2026-02-10 | 2026-02-10 | Shiv Power | Done | Done
334 | 11A/8 | DA+6 | 2026-02-10 | 2026-02-10 | Shiv Power | Done | Done
335 | 12/0 | DD60+0 | 2026-02-10 | 2026-02-10 | Shiv Power | Done | Done
336 | 17/4 | DA+3 | 2026-02-10 | 2026-02-10 | Shiv Power | Done | Done
337 | 18/0 | DC2+0 | 2026-02-11 | 2026-02-11 | Shiv Power | Done | Done
338 | 20/2 | DA+0 | 2026-02-11 | 2026-02-11 | Shiv Power | Done | Done
339 | 20/3 | DA+0 | 2026-02-11 | 2026-02-11 | Shiv Power | Done | Done
340 | 21/4 | DA+3 | 2026-02-11 | 2026-02-11 | Shiv Power | Done | Done
341 | 21/5 | DA+6 | 2026-02-11 | 2026-02-11 | Shiv Power | Done | Done
342 | 22/13 | DA+6 | 2026-02-11 | 2026-02-11 | Shiv Power | Done | Done
343 | 43/1 | DA+3 | 2026-02-11 | 2026-02-11 | Suraja Ram | Done | Done
344 | 43/2 | DA+0 | 2026-02-11 | 2026-02-11 | Suraja Ram | Done | Done
345 | 43/3 | DA+0 | 2026-02-11 | 2026-02-11 | Suraja Ram | Done | Done
346 | 43/4 | DA+3 | 2026-02-12 | 2026-02-12 | Suraja Ram | Done | Done
347 | 43/5 | DA+3 | 2026-02-12 | 2026-02-12 | Suraja Ram | Done | Done
348 | 43/6 | DA+3 | 2026-02-12 | 2026-02-12 | Suraja Ram | Done | Done
349 | 43/7 | DA+3 | 2026-02-13 | 2026-02-13 | Suraja Ram | Done | Done
350 | 44/0 | DB1+3 | 2026-02-13 | 2026-02-13 | Suraja Ram | Done | Done
351 | 44/2 | DA+0 | 2026-02-14 | 2026-02-14 | Suraja Ram | Done | Done
352 | 44/6 | DB1+3 | 2026-02-14 | 2026-02-14 | Suraja Ram | Done | Done
353 | 8/4 | DA+3 | 2026-02-20 | 2026-02-20 | Jai Bagrangbali | Done | Done
354 | 8/5 | DA+3 | 2026-02-20 | 2026-02-20 | Jai Bagrangbali | Done | Done
355 | 10/7 | DA+3 | 2026-02-20 | 2026-02-20 | Jai Bagrangbali | Done | Done
356 | 10/9 | DA+0 | 2026-02-21 | 2026-02-21 | Jai Bagrangbali | Done | Done
357 | 10/10 | DA+3 | 2026-02-21 | 2026-02-21 | Jai Bagrangbali | Done | Done
358 | 10/11 | DA+3 | 2026-02-22 | 2026-02-22 | Jai Bagrangbali | Done | Done
359 | 11/0 | DB1+0 | 2026-02-22 | 2026-02-22 | Shiv Power | Done | Done
360 | 16/1 | DA+0 | 2026-02-22 | 2026-02-22 | Chanda Enterprises | Done | Done
361 | 17/1 | DA+3 | 2026-02-22 | 2026-02-22 | Chanda Enterprises | Done | Done
362 | 27/6 | DA+0 | 2026-02-22 | 2026-02-22 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
363 | 27/7 | DB1+0 | 2026-02-22 | 2026-02-22 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
364 | 27/12 | DA+3 | 2026-02-15 | 2026-02-15 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
365 | 28/6 | DA+6 | 2026-02-16 | 2026-02-16 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
366 | 28/7 | DA+3 | 2026-02-16 | 2026-02-16 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
367 | 29/0 | DB1+0 | 2026-02-17 | 2026-02-17 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
368 | 44/9 | DA+9 | 2026-02-18 | 2026-02-18 | Suraja Ram | Done | Done
369 | 45/0 | DC2+0 | 2026-02-18 | 2026-02-18 | Suraja Ram | Done | Done
370 | 53/0 | DB2+9 | 2026-02-19 | 2026-02-19 | Suraja Ram | Done | Done
371 | 53/1 | DA+9 | 2026-02-19 | 2026-02-19 | Suraja Ram | Done | Done
372 | 53/4 | DA+0 | 2026-02-20 | 2026-02-20 | Suraja Ram | Done | Done
373 | 53/5 | DA+3 | 2026-02-20 | 2026-02-20 | Suraja Ram | Done | Done
374 | 53/6 | DA+6 | 2026-02-21 | 2026-02-21 | Suraja Ram | Done | Done
375 | 53/7 | DA+3 | 2026-02-21 | 2026-02-21 | Suraja Ram | Done | Done
376 | 54/0 | DB1+6 | 2026-02-22 | 2026-02-22 | Suraja Ram | Done | Done

## Stringing
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
STRINGING
SL. No. | Section |  | Type of Sections | Gang Name | Section Length | Paying Out/R-Sag |  |  | Final Sag
| From | To |  |  |  | Section Length | Start Date | End Date | Section Length | Start Date | End Date | Remarks | Completion Month
1 | 60/0 | 61/0 | TSE | Kuddus ali | 4.877 | 4.877 | 2024-08-21 | 2024-08-28 | 4.877 | 2024-09-09 | 2024-09-16 | Final sag completed | 2024-09-01
2 | 61/0 | 62/0 | TSE | Kuddus ali | 4.568 | 4.568 | 2024-09-06 | 2024-09-16 | 4.568 | 2024-09-26 | 2024-10-03 | Final sag completed | 2024-10-01
3 | 62/0 | 63/0 | TSE | Kuddus ali | 4.863 | 4.863 | 2024-09-23 | 2024-10-02 | 4.863 | 2024-10-17 | 2024-10-22 | Final sag completed | 2024-10-01
4 | 63/0 | 64/0 | TSE | Kuddus ali | 3.711 | 3.711 | 2024-10-14 | 2024-10-21 | 3.711 | 2024-10-31 | 2024-11-06 | Final sag completed | 2024-11-01
5 | 64/0 | 65/0 | TSE | Kuddus ali | 4.918 | 4.918 | 2024-10-30 | 2024-11-05 | 4.918 | 2024-11-13 | 2024-11-16 | Final sag completed | 2024-11-01
6 | 59/8 | 60/0 | TSE | Gopal Associate | 3.778 | 3.778 | 2024-12-22 | 2024-12-27 | 3.778 | 2025-01-04 | 2025-01-09 | Final sag completed | 2025-01-01
7 | 59/0 | 59/8 | TSE | Gopal Associate | 3.337 | 3.337 | 2025-01-02 | 2025-01-08 | 3.337 | 2025-01-12 | 2025-01-15 | Final sag completed | 2025-01-01
8 | 65/0 | 66/0 | TSE | MR Power | 4.736 | 4.736 | 2025-02-03 | 2025-03-22 | 4.736 | 2025-03-10 | 2025-03-23 | Final sag completed | 2025-03-01
9 | 50/0 | 51/0 | TSE | Gopal Associate | 4.444 | 4.444 | 2025-03-12 | 2025-03-23 | 4.444 | 2025-03-17 | 2025-03-24 | Final sag completed | 2025-03-01
10 | 49/0 | 50/0 | TSE | Gopal Associate | 3.227 | 3.227 | 2025-02-06 | 2025-02-19 | 3.227 | 2025-05-01 | 2025-05-05 | Final sag completed | 2025-05-01
11 | 51/0 | 52/0 | TSE | Gopal Associate | 1.049 | 1.049 | 2025-04-02 | 2025-04-08 | 1.049 | 2025-04-04 | 2025-04-09 | Final sag completed | 2025-04-01
11 | 73/0 | 74/0 | TSE | JPJ Construction/MC Power | 3.788 | 3.788 | 2025-06-01 | 2025-06-21 | 3.788 | 2025-09-26 | 2025-09-30 | Final sag completed | 2025-09-01
12 | 72/0 | 73/0 | TSE | JPJ Construction/MC Power | 1.628 | 1.628 | 2025-11-03 | 2025-11-08 | 1.628 | 2025-11-21 | 2025-11-25 | Final sag completed. | 2025-11-01
13 | 2/0 | 3/0 | TSE | Devi Power | 3.823 | 3.823 | 2025-11-13 | 2025-11-18 | 3.823 | 2025-12-30 | 2026-01-14 | Final sag completed. | 2026-01-01 | 42
14 | 71/0 | 72/0 | TSE | MC Power | 3.675 | 3.675 | 2025-11-20 | 2025-11-25 | 3.675 | 2025-11-28 | 2025-11-30 | Final sag completed. | 2025-11-01 | 62
15 | 1A/0 | 2/0 | TSE | Devi Power | 3.426 | 3.426 | 2025-11-21 | 2025-11-28 | 3.426 | 2025-11-28 | 2025-11-30 | Final sag completed. | 2025-11-01 | 54
16 | 70/0 | 71/0 | TSE | MC Power | 4.966 | 4.966 | 2025-12-08 | 2025-12-16 | 4.966 | 2025-12-12 | 2025-12-17 | Final sag completed. | 2025-12-01 | 62
17 | 56/0 | 57/0 | M | Gopal Associate, Hotline | 0.22 | 0.22 | 2025-11-20 | 2025-11-26 | 0.22 | 2025-11-20 | 2025-11-26 | Final sag completed. | 2025-11-01
18 | 46/0 | 47/0 | M | Gopal Associate, Hotline | 0.19908 | 0.19908 | 2025-12-06 | 2025-12-11 | 0.19908 | 2025-12-06 | 2025-12-11 | Final sag completed. | 2025-12-01 | 18
19 | 69/0 | 70/0 | TSE | MC Power | 0.769 | 0.769 | 2025-12-18 | 2025-12-24 | 0.769 | 2025-12-21 | 2025-12-25 | Final sag completed. | 2025-12-01
20 | 67/0 | 68/0 | TSE | MC Power | 1.061 | 1.061 | 2025-12-26 | 2025-12-28 | 1.061 | 2026-01-06 | 2026-01-08 | Final sag completed. | 2026-01-01
21 | 68/0 | 69/0 | M | MC Power | 0.2 | 0.2 | 2025-12-29 | 2025-12-29 | 0.2 | 2025-12-29 | 2025-12-29 | Final sag completed. | 2025-12-01
22 | 66/0 | 67/0 | M | MC Power | 0.2078 | 0.2078 | 2026-01-03 | 2026-01-03 | 0.2078 | 2026-01-03 | 2026-01-03 | Final sag completed. | 2026-01-01
23 | 3/0 | 4/0 | M | Gopal Associate, Hotline | 0.2265 | 0.2265 | 2026-01-10 | 2026-01-16 | 0.2265 | 2026-01-11 | 2026-01-16 | Final sag completed. | 2026-01-01
24 | 57/0 | 58/0 | TSE | MC Power | 3.287 | 3.287 | 2026-01-19 | 2026-01-24 | 3.287 | 2026-01-29 | 2026-01-31 | Final sag completed. | 2026-01-01
25 | 10/12 | 11/0 | TSE | Deepak | 4.95 | 4.95 | 2026-01-14 | 2026-01-22 | 4.95 | 2026-02-05 | 2026-02-07 | Final sag completed. | 2026-02-01
26 | 47/0 | 48/0 | TSE | Krishna-1 | 4.477 | 4.477 | 2026-01-26 | 2026-01-31 | 4.477 | 2026-01-28 | 2026-01-31 | Final sag completed. | 2026-01-01
27 | 55/0 | 56/0 | TSE | MC Power | 3.34 |  | 2026-02-12 |  |  |  |  | 3 phase R/Sag done. Gangs shifted in Package G for rectification. No works will be done until readiness of PKG G based on instructions by resonia..
28 | 48/0 | 49/0 | TSE | Krishna-1 | 0.83 | 0.83 | 2026-01-17 | 2026-01-20 | 0.83 | 2026-01-20 | 2026-01-23 | Final sag completed. | 2026-01-01
29 | 58/0 | 59/0 | M | MC Power | 0.2389 | 0.2389 | 2026-01-28 | 2026-01-28 | 0.2389 | 2026-01-28 | 2026-01-28 | Final sag completed. | 2026-01-01
30 | 45/0 | 46/0 | TSE | Krishna-1 | 0.70146 | 0.70146 | 2026-02-07 | 2026-02-08 | 0.70146 | 2026-02-10 | 2026-02-13 | Final sag completed. | 2026-02-01
31 | 44/10 | 45/0 | TSE | Krishna-1 | 0.755 | 0.755 | 2026-02-09 | 2026-02-12 | 0.755 | 2026-02-17 | 2026-02-20 | Final sag completed. | 2026-02-01
32 | 44/8 | 44/10 | TSE | Krishna-1 | 0.795 | 0.795 | 2026-02-16 | 2026-02-19 |  |  |  | WIP.
33 | 7/0 | 8/0 | M | Gopal Associate, Hotline | 0.211 |  | 2026-02-20 |  |  |  |  | WIP.
TOTAL |  |  |  |  | 87.2827 | 83.7317 |  |  | 82.9367
[5 empty] | S. Len-P.O. | 3.551
[5 empty] | P/O-F/S | 0.795 |  |  | 82.9367
Formulas:
Start Date = [End Date]-6

## Stringing associated works
Progress Summary'!A1 | [11 empty] | Moosedorfer
LINE MATERIAL
As per details shared on dated 10.03.2025 | [8 empty] | CLR Insulators |  | Hardware Fittings (Set) |  |  |  | Conductor Accessories for AL59 Zebra |  |  |  |  | Earthwire Accessories | [5 empty] | Remarks
Sl No | Twr No. | Tower Type | Deviation Angle (DMS) | Span (m) |  | Section Length (m) | Conductor (Mtr.) | Earthwire (Mtr.) | 210 KN Insulator Rod for 765KV(2*2975 or 1*5950)mm lenth | 160 KN Insulator Rod for 765KV(2*2975 or 1*5950)mm lenth | 4x210KN Quad Tension for 765KV | 2x160KN Double Suspension Insulator string | 160KN Single "I" Pilot string | Single tension Insulator string | MSCJ | Repair Sleeve | Hexa Spacer Damper for 765KV AL59 Zebra | Rigid Spacer for 765KV AL59 Zebra | T - Connector | Tension Clamp | Suspension Clamp | Flexible Copper bond | MSCJ | Repair Sleeve | VD
| GANTRY | GTY | 00°00'00" | [5 empty] | 48 | 12 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 1 |  |  | 4
|  |  |  | 121.998 | 125 |  | 4500 | 125 | [8 empty] | 12
1 | 1/0 | DE | 11°14'51"LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 89.999 | 90 |  | 3240 | 90 | [8 empty] | 12
2 | 1A/0 | DD60+0 | 52°22'23.88"LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 277.726 | 280 |  | 10080 | 280 | [8 empty] | 30
3 | 1A/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386.044 | 390 |  | 14040 | 390 | [8 empty] | 36
4 | 1A/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 443.632 | 445 |  | 16020 | 445 | [8 empty] | 42
5 | 1A/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 333.393 | 335 |  | 12060 | 335 | [8 empty] | 36
6 | 1A/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 431.848 | 435 |  | 15660 | 435 | [8 empty] | 42
7 | 1A/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 348.735 | 350 |  | 12600 | 350 | [8 empty] | 36
8 | 1A/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 395.693 | 400 |  | 14400 | 400 | [8 empty] | 42
9 | 1A/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.953 | 415 |  | 14940 | 415 | [8 empty] | 42
10 | 1A/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.306 | 395 |  | 14220 | 395 | [8 empty] | 42
11 | 2/0 | DC1+0 | 16° 05' 50.64" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 405.342 | 410 |  | 14760 | 410 | [8 empty] | 42
12 | 2/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 338.507 | 340 |  | 12240 | 340 | [8 empty] | 36
13 | 2/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.023 | 410 |  | 14760 | 410 | [8 empty] | 42
14 | 2/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 428.949 | 430 |  | 15480 | 430 | [8 empty] | 42
15 | 2/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 411.548 | 415 |  | 14940 | 415 | [8 empty] | 42
16 | 2/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.741 | 430 |  | 15480 | 430 | [8 empty] | 42
17 | 2/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.176 | 410 |  | 14760 | 410 | [8 empty] | 42
18 | 2/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 354.581 | 355 |  | 12780 | 355 | [8 empty] | 36
19 | 2/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 308.656 | 310 |  | 11160 | 310 | [8 empty] | 30
20 | 2/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 335.979 | 340 |  | 12240 | 340 | [8 empty] | 36
21 | 3/0 | DD60+6 | 01° 29' 56.04" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 226.52 | 230 |  | 8280 | 230 | [8 empty] | 24
22 | 4/0 | DD60+6 | 07° 48' 05.04" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 343.373 | 345 |  | 12420 | 345 | [8 empty] | 36
23 | 4/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 358.444 | 360 |  | 12960 | 360 | [8 empty] | 36
24 | 4/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 381.012 | 385 |  | 13860 | 385 | [8 empty] | 36
25 | 4/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 367.624 | 370 |  | 13320 | 370 | [8 empty] | 36
26 | 4/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 423.091 | 425 |  | 15300 | 425 | [8 empty] | 42
27 | 5/0 | DB1+9,5RC | 05° 43' 49.08" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 246.019 | 250 |  | 9000 | 250 | [8 empty] | 24
28 | 6/0 | DB2+9,5RC | 10° 20' 7.44" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 429.917 | 430 |  | 15480 | 430 | [8 empty] | 42
29 | 6/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 362.365 | 365 |  | 13140 | 365 | [8 empty] | 36
30 | 6/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 347.864 | 350 |  | 12600 | 350 | [8 empty] | 36
31 | 7/0 | DB1+0 | 04° 51' 39.96" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 210.755 | 215 |  | 7740 | 215 | [8 empty] | 24
32 | 8/0 | DB1+0 | 01° 26' 19.32" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 409.202 | 410 |  | 14760 | 410 | [8 empty] | 42
33 | 8/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.633 | 415 |  | 14940 | 415 | [8 empty] | 42
34 | 8/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 393.241 | 395 |  | 14220 | 395 | [8 empty] | 42
35 | 8/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 416.473 | 420 |  | 15120 | 420 | [8 empty] | 42
36 | 8/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.562 | 395 |  | 14220 | 395 | [8 empty] | 42
37 | 8/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 393.204 | 395 |  | 14220 | 395 | [8 empty] | 42
38 | 8/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 441.058 | 445 |  | 16020 | 445 | [8 empty] | 42
39 | 8/7 | DB1+0 | 00° 00' 00" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 419.392 | 420 |  | 15120 | 420 | [8 empty] | 42
40 | 8/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 390.864 | 395 |  | 14220 | 395 | [8 empty] | 42
41 | 8/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.404 | 415 |  | 14940 | 415 | [8 empty] | 42
42 | 8/10 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.636 | 405 |  | 14580 | 405 | [8 empty] | 42
43 | 8/11 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 372.046 | 375 |  | 13500 | 375 | [8 empty] | 36
44 | 8/12 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 457.703 | 460 |  | 16560 | 460 | [8 empty] | 48
45 | 9/0 | DD60+18 | 20° 13' 33.24" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 233.076 | 235 |  | 8460 | 235 | [8 empty] | 24
46 | 10/0 | DD60+25 | 33° 37' 51.96" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 443.71 | 445 |  | 16020 | 445 | [8 empty] | 42
47 | 10/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 383.235 | 385 |  | 13860 | 385 | [8 empty] | 36
48 | 10/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 398.553 | 400 |  | 14400 | 400 | [8 empty] | 42
49 | 10/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.719 | 415 |  | 14940 | 415 | [8 empty] | 42
50 | 10/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 416.15 | 420 |  | 15120 | 420 | [8 empty] | 42
51 | 10/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403.399 | 405 |  | 14580 | 405 | [8 empty] | 42
52 | 10/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 373.846 | 375 |  | 13500 | 375 | [8 empty] | 36
53 | 10/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 411.824 | 415 |  | 14940 | 415 | [8 empty] | 42
54 | 10/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.2 | 415 |  | 14940 | 415 | [8 empty] | 42
55 | 10/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.294 | 405 |  | 14580 | 405 | [8 empty] | 42
56 | 10/10 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 430.283 | 435 |  | 15660 | 435 | [8 empty] | 42
57 | 10/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.223 | 410 |  | 14760 | 410 | [8 empty] | 42
58 | 10/12 | DB1+0 | 00° 00' 00" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 405.251 | 410 |  | 14760 | 410 | [8 empty] | 42
59 | 10/13 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 427.084 | 430 |  | 15480 | 430 | [8 empty] | 42
60 | 10/14 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.036 | 405 |  | 14580 | 405 | [8 empty] | 42
61 | 10/15 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.79 | 415 |  | 14940 | 415 | [8 empty] | 42
62 | 10/16 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 387.758 | 390 |  | 14040 | 390 | [8 empty] | 36
63 | 10/17 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 436.732 | 440 |  | 15840 | 440 | [8 empty] | 42
64 | 10/18 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403.689 | 405 |  | 14580 | 405 | [8 empty] | 42
65 | 10/19 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409.528 | 410 |  | 14760 | 410 | [8 empty] | 42
66 | 10/20 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.56 | 420 |  | 15120 | 420 | [8 empty] | 42
67 | 10/21 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.253 | 415 |  | 14940 | 415 | [8 empty] | 42
68 | 10/22 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 383.968 | 385 |  | 13860 | 385 | [8 empty] | 36
69 | 10/23 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 450.808 | 455 |  | 16380 | 455 | [8 empty] | 42
70 | 11/0 | DB1+0 | [6 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 384.218 | 385 |  | 13860 | 385 | [8 empty] | 36
71 | 11/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 338.549 | 340 |  | 12240 | 340 | [8 empty] | 36
72 | 11/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 370.74 | 375 |  | 13500 | 375 | [8 empty] | 36
73 | 11/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 434.099 | 435 |  | 15660 | 435 | [8 empty] | 42
74 | 11/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 368.102 | 370 |  | 13320 | 370 | [8 empty] | 36
75 | 11/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 342.28 | 345 |  | 12420 | 345 | [8 empty] | 36
76 | 11A/0 | DB1+0 | 01° 00' 23.04" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 405.114 | 410 |  | 14760 | 410 | [8 empty] | 42
77 | 11A/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.146 | 415 |  | 14940 | 415 | [8 empty] | 42
78 | 11A/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.223 | 415 |  | 14940 | 415 | [8 empty] | 42
79 | 11A/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 422.072 | 425 |  | 15300 | 425 | [8 empty] | 42
80 | 11A/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.268 | 420 |  | 15120 | 420 | [8 empty] | 42
81 | 11A/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 384.308 | 385 |  | 13860 | 385 | [8 empty] | 36
82 | 11A/6 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 434.199 | 435 |  | 15660 | 435 | [8 empty] | 42
83 | 11A/7 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 390.121 | 395 |  | 14220 | 395 | [8 empty] | 42
84 | 11A/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426.314 | 430 |  | 15480 | 430 | [8 empty] | 42
85 | 11A/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 405.867 | 410 |  | 14760 | 410 | [8 empty] | 42
86 | 12/0 | DD60+0 | 52° 09' 12.24" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 211.914 | 215 |  | 7740 | 215 | [8 empty] | 24
87 | 13/0 | DD60+3 | 50° 55' 18.84" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 464.251 | 465 |  | 16740 | 465 | [8 empty] | 48
88 | 13/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 373.688 | 375 |  | 13500 | 375 | [8 empty] | 36
89 | 13/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.672 | 420 |  | 15120 | 420 | [8 empty] | 42
90 | 13/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.252 | 425 |  | 15300 | 425 | [8 empty] | 42
91 | 13/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.037 | 405 |  | 14580 | 405 | [8 empty] | 42
92 | 14/0 | DC2+0 | 23° 35' 02.76" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 381.413 | 385 |  | 13860 | 385 | [8 empty] | 36
93 | 14A/0 | DC1+0 | 17° 04' 19.92" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 412.766 | 415 |  | 14940 | 415 | [8 empty] | 42
94 | 14A/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 396.03 | 400 |  | 14400 | 400 | [8 empty] | 42
95 | 14A/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 383.335 | 385 |  | 13860 | 385 | [8 empty] | 36
96 | 15/0 | DC1+0 | 19° 19' 46.92" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 404.587 | 405 |  | 14580 | 405 | [8 empty] | 42
97 | 15/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.327 | 415 |  | 14940 | 415 | [8 empty] | 42
98 | 16/0 | DC1+0 | 18° 26' 35.88" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 354.282 | 355 |  | 12780 | 355 | [8 empty] | 36
99 | 16/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 424.282 | 425 |  | 15300 | 425 | [8 empty] | 42
100 | 16/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 340.311 | 345 |  | 12420 | 345 | [8 empty] | 36
101 | 16/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 404.648 | 405 |  | 14580 | 405 | [8 empty] | 42
102 | 16/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.863 | 430 |  | 15480 | 430 | [8 empty] | 42
103 | 16/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386.772 | 390 |  | 14040 | 390 | [8 empty] | 36
104 | 17/0 | DB2+3 | 12° 43' 17.04" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 393.724 | 395 |  | 14220 | 395 | [8 empty] | 42
105 | 17/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 415.886 | 420 |  | 15120 | 420 | [8 empty] | 42
106 | 17/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 422.815 | 425 |  | 15300 | 425 | [8 empty] | 42
107 | 17/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409.889 | 410 |  | 14760 | 410 | [8 empty] | 42
108 | 17/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.336 | 430 |  | 15480 | 430 | [8 empty] | 42
109 | 17/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 383.432 | 385 |  | 13860 | 385 | [8 empty] | 36
110 | 18/0 | DC2+0 | 24° 50' 58.2" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 372.844 | 375 |  | 13500 | 375 | [8 empty] | 36
111 | 18/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 379.803 | 380 |  | 13680 | 380 | [8 empty] | 36
112 | 18/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 370.997 | 375 |  | 13500 | 375 | [8 empty] | 36
113 | 18/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 398.701 | 400 |  | 14400 | 400 | [8 empty] | 42
114 | 18/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 380.821 | 385 |  | 13860 | 385 | [8 empty] | 36
115 | 19/0 | DC2+0 | 28° 14' 9.24" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 366.875 | 370 |  | 13320 | 370 | [8 empty] | 36
116 | 19/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 372.501 | 375 |  | 13500 | 375 | [8 empty] | 36
117 | 19/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 376.459 | 380 |  | 13680 | 380 | [8 empty] | 36
118 | 19/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 384.284 | 385 |  | 13860 | 385 | [8 empty] | 36
119 | 19/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 375.36 | 380 |  | 13680 | 380 | [8 empty] | 36
120 | 19/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 381.243 | 385 |  | 13860 | 385 | [8 empty] | 36
121 | 20/0 | DB2+0 | 12° 15' 49.68" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 386.781 | 390 |  | 14040 | 390 | [8 empty] | 36
122 | 20/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 387.041 | 390 |  | 14040 | 390 | [8 empty] | 36
123 | 20/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 348.466 | 350 |  | 12600 | 350 | [8 empty] | 36
124 | 20/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 354.966 | 355 |  | 12780 | 355 | [8 empty] | 36
125 | 21/0 | DB2+0 | 14° 55' 19.2" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 414.903 | 415 |  | 14940 | 415 | [8 empty] | 42
126 | 21/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 407.236 | 410 |  | 14760 | 410 | [8 empty] | 42
127 | 21/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 432.227 | 435 |  | 15660 | 435 | [8 empty] | 42
128 | 21/3 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401.871 | 405 |  | 14580 | 405 | [8 empty] | 42
129 | 21/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 434.179 | 435 |  | 15660 | 435 | [8 empty] | 42
130 | 21/5 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 405.501 | 410 |  | 14760 | 410 | [8 empty] | 42
131 | 21/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426.014 | 430 |  | 15480 | 430 | [8 empty] | 42
132 | 21/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.905 | 410 |  | 14760 | 410 | [8 empty] | 42
133 | 21/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 433.253 | 435 |  | 15660 | 435 | [8 empty] | 42
134 | 21/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 372.897 | 375 |  | 13500 | 375 | [8 empty] | 36
135 | 21/10 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 443.539 | 445 |  | 16020 | 445 | [8 empty] | 42
136 | 22/0 | DB2+3 | 09° 09' 25.92" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 456.348 | 460 |  | 16560 | 460 | [8 empty] | 48
137 | 22/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 379.199 | 380 |  | 13680 | 380 | [8 empty] | 36
138 | 22/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 382.622 | 385 |  | 13860 | 385 | [8 empty] | 36
139 | 22/3 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 435.556 | 440 |  | 15840 | 440 | [8 empty] | 42
140 | 22/4 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.063 | 405 |  | 14580 | 405 | [8 empty] | 42
141 | 22/5 | DA+9,2RC | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 417.315 | 420 |  | 15120 | 420 | [8 empty] | 42
142 | 22/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 347.702 | 350 |  | 12600 | 350 | [8 empty] | 36
143 | 22/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 356.245 | 360 |  | 12960 | 360 | [8 empty] | 36
144 | 22/8 | DB1+0 | 00° 00' 00" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 389.193 | 390 |  | 14040 | 390 | [8 empty] | 36
145 | 22/9 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 343.775 | 345 |  | 12420 | 345 | [8 empty] | 36
146 | 22/10 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 395.488 | 400 |  | 14400 | 400 | [8 empty] | 42
147 | 22/11 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.032 | 410 |  | 14760 | 410 | [8 empty] | 42
148 | 22/12 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 318.002 | 320 |  | 11520 | 320 | [8 empty] | 30
149 | 22/13 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 447.32 | 450 |  | 16200 | 450 | [8 empty] | 42
150 | 23/0 | DD45+3 | 34° 59' 23.64" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 222.155 | 225 |  | 8100 | 225 | [8 empty] | 24
151 | 24/0 | DD45+3 | 32° 40' 24.96" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 433.889 | 435 |  | 15660 | 435 | [8 empty] | 42
152 | 25/0 | DC1+6 | 15° 53' 08.16" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 422.332 | 425 |  | 15300 | 425 | [8 empty] | 42
153 | 25/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 370.741 | 375 |  | 13500 | 375 | [8 empty] | 36
154 | 25/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 345.675 | 350 |  | 12600 | 350 | [8 empty] | 36
155 | 25/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 391.123 | 395 |  | 14220 | 395 | [8 empty] | 42
156 | 25/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 440.407 | 445 |  | 16020 | 445 | [8 empty] | 42
157 | 26/0 | DB1+0 | 00° 51' 11.52" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 391.364 | 395 |  | 14220 | 395 | [8 empty] | 42
158 | 26/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.47 | 410 |  | 14760 | 410 | [8 empty] | 42
159 | 26/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.022 | 420 |  | 15120 | 420 | [8 empty] | 42
160 | 26/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 422.596 | 425 |  | 15300 | 425 | [8 empty] | 42
161 | 26/4 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409.977 | 410 |  | 14760 | 410 | [8 empty] | 42
162 | 26/5 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 363.382 | 365 |  | 13140 | 365 | [8 empty] | 36
163 | 26/6 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 421.855 | 425 |  | 15300 | 425 | [8 empty] | 42
164 | 26/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 416.722 | 420 |  | 15120 | 420 | [8 empty] | 42
165 | 26/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.786 | 415 |  | 14940 | 415 | [8 empty] | 42
166 | 27/0 | DC1+0 | 19° 33' 38.16" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 399.755 | 400 |  | 14400 | 400 | [8 empty] | 42
167 | 27/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.179 | 430 |  | 15480 | 430 | [8 empty] | 42
168 | 27/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 398.561 | 400 |  | 14400 | 400 | [8 empty] | 42
169 | 27/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 430.665 | 435 |  | 15660 | 435 | [8 empty] | 42
170 | 27/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.013 | 415 |  | 14940 | 415 | [8 empty] | 42
171 | 27/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.548 | 405 |  | 14580 | 405 | [8 empty] | 42
172 | 27/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 343.499 | 345 |  | 12420 | 345 | [8 empty] | 36
173 | 27/7 | DB1+0 | 00° 00' 00" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 392.004 | 395 |  | 14220 | 395 | [8 empty] | 42
174 | 27/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 381.088 | 385 |  | 13860 | 385 | [8 empty] | 36
175 | 27/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 366.278 | 370 |  | 13320 | 370 | [8 empty] | 36
176 | 27/10 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.087 | 425 |  | 15300 | 425 | [8 empty] | 42
177 | 27/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.787 | 425 |  | 15300 | 425 | [8 empty] | 42
178 | 27/12 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.635 | 410 |  | 14760 | 410 | [8 empty] | 42
179 | 28/0 | DB2+0 | 12° 53' 28.32" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 379.637 | 380 |  | 13680 | 380 | [8 empty] | 36
180 | 28/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 385 | 385 |  | 13860 | 385 | [8 empty] | 36
181 | 28/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 369 | 370 |  | 13320 | 370 | [8 empty] | 36
182 | 28/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409 | 410 |  | 14760 | 410 | [8 empty] | 42
183 | 28/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 422 | 425 |  | 15300 | 425 | [8 empty] | 42
184 | 28/5 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 370 | 370 |  | 13320 | 370 | [8 empty] | 36
185 | 28/6 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 464 | 465 |  | 16740 | 465 | [8 empty] | 48
186 | 28/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 375 | 375 |  | 13500 | 375 | [8 empty] | 36
187 | 28/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 465.455 | 470 |  | 16920 | 470 | [8 empty] | 48
188 | 29/0 | DB1+0 | 06° 14' 21.84" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 365.545 | 370 |  | 13320 | 370 | [8 empty] | 36
189 | 29/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 424 | 425 |  | 15300 | 425 | [8 empty] | 42
190 | 29/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 399 | 400 |  | 14400 | 400 | [8 empty] | 42
191 | 29/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 440 | 440 |  | 15840 | 440 | [8 empty] | 42
192 | 29/4 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 382.099 | 385 |  | 13860 | 385 | [8 empty] | 36
193 | 30/0 | DC1+0 | 16° 15' 6.12" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 388.901 | 390 |  | 14040 | 390 | [8 empty] | 36
194 | 30/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 445 | 445 |  | 16020 | 445 | [8 empty] | 42
195 | 30/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 395 | 395 |  | 14220 | 395 | [8 empty] | 42
196 | 30/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 377 | 380 |  | 13680 | 380 | [8 empty] | 36
197 | 30/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 444 | 445 |  | 16020 | 445 | [8 empty] | 42
198 | 30/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 322 | 325 |  | 11700 | 325 | [8 empty] | 30
199 | 30/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 347.434 | 350 |  | 12600 | 350 | [8 empty] | 36
200 | 31/0 | DB2+0 | 14° 44' 46.32" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 383.566 | 385 |  | 13860 | 385 | [8 empty] | 36
201 | 31/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 366 | 370 |  | 13320 | 370 | [8 empty] | 36
202 | 31/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 332.909 | 335 |  | 12060 | 335 | [8 empty] | 36
203 | 32/0 | DC1+0 | 21° 35' 19.68" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 402.684 | 405 |  | 14580 | 405 | [8 empty] | 42
204 | 32/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 428.809 | 430 |  | 15480 | 430 | [8 empty] | 42
205 | 32/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.89 | 415 |  | 14940 | 415 | [8 empty] | 42
206 | 32/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 381.106 | 385 |  | 13860 | 385 | [8 empty] | 36
207 | 32/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 451.501 | 455 |  | 16380 | 455 | [8 empty] | 42
208 | 33/0 | DC1+0 | 20° 0' 49.32" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 379.558 | 380 |  | 13680 | 380 | [8 empty] | 36
209 | 33/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 292.533 | 295 |  | 10620 | 295 | [8 empty] | 30
210 | 34/0 | DB2+0 | 9° 34' 3.36" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 432.636 | 435 |  | 15660 | 435 | [8 empty] | 42
211 | 34/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 407.467 | 410 |  | 14760 | 410 | [8 empty] | 42
212 | 34/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 377.043 | 380 |  | 13680 | 380 | [8 empty] | 36
213 | 34/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 451.576 | 455 |  | 16380 | 455 | [8 empty] | 42
214 | 34/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 379.275 | 380 |  | 13680 | 380 | [8 empty] | 36
215 | 35/0 | DB2+6 | 13° 13' 27.12" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 265.554 | 270 |  | 9720 | 270 | [8 empty] | 30
216 | 35/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 492.404 | 495 |  | 17820 | 495 | [8 empty] | 48
217 | 35/2 | DB1+0 | [6 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 522.221 | 525 |  | 18900 | 525 | [8 empty] | 48
218 | 35/3 | DB1+6 | [6 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 418.925 | 420 |  | 15120 | 420 | [8 empty] | 42
219 | 35/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 421.684 | 425 |  | 15300 | 425 | [8 empty] | 42
220 | 35/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 342.697 | 345 |  | 12420 | 345 | [8 empty] | 36
221 | 36/0 | DB2+0 | 14° 55' 10.2" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 386.433 | 390 |  | 14040 | 390 | [8 empty] | 36
222 | 36/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 309.428 | 310 |  | 11160 | 310 | [8 empty] | 30
223 | 36/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 357.809 | 360 |  | 12960 | 360 | [8 empty] | 36
224 | 36/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 480.439 | 485 |  | 17460 | 485 | [8 empty] | 48
225 | 36/4 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 350.468 | 355 |  | 12780 | 355 | [8 empty] | 36
226 | 37/0 | DB2+0 | 14° 56' 10.32" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 443.286 | 445 |  | 16020 | 445 | [8 empty] | 42
227 | 37/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 356.665 | 360 |  | 12960 | 360 | [8 empty] | 36
228 | 37/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 339.878 | 340 |  | 12240 | 340 | [8 empty] | 36
229 | 37/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 500.279 | 505 |  | 18180 | 505 | [8 empty] | 48
230 | 38/0 | DB2+6 | 9° 11' 45.24" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 421.442 | 425 |  | 15300 | 425 | [8 empty] | 42
231 | 38/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.024 | 420 |  | 15120 | 420 | [8 empty] | 42
232 | 38/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.329 | 425 |  | 15300 | 425 | [8 empty] | 42
233 | 38/3 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.895 | 415 |  | 14940 | 415 | [8 empty] | 42
234 | 38/4 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.489 | 430 |  | 15480 | 430 | [8 empty] | 42
235 | 39/0 | DB2+6 | 14° 1' 20.28" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 412.639 | 415 |  | 14940 | 415 | [8 empty] | 42
236 | 39/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 322.554 | 325 |  | 11700 | 325 | [8 empty] | 30
237 | 40/0 | DC2+0 | 21° 42' 13.68" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 396.201 | 400 |  | 14400 | 400 | [8 empty] | 42
238 | 40/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.809 | 430 |  | 15480 | 430 | [8 empty] | 42
239 | 40/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401.688 | 405 |  | 14580 | 405 | [8 empty] | 42
240 | 40/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 436.302 | 440 |  | 15840 | 440 | [8 empty] | 42
241 | 41/0 | DC1+6 | 16° 54' 46" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 340.766 | 345 |  | 12420 | 345 | [8 empty] | 36
242 | 41/1 | DB1+9 | [6 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 447.822 | 450 |  | 16200 | 450 | [8 empty] | 42
243 | 41/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 382.33 | 385 |  | 13860 | 385 | [8 empty] | 36
244 | 42/0 | DC1+0 | 17° 31' 50" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 384.711 | 385 |  | 13860 | 385 | [8 empty] | 36
245 | 42/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 407.363 | 410 |  | 14760 | 410 | [8 empty] | 42
246 | 42/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.174 | 415 |  | 14940 | 415 | [8 empty] | 42
247 | 42/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 256.36 | 260 |  | 9360 | 260 | [8 empty] | 24
248 | 42/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403.84 | 405 |  | 14580 | 405 | [8 empty] | 42
249 | 42/5 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 396.724 | 400 |  | 14400 | 400 | [8 empty] | 42
250 | 42/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403.932 | 405 |  | 14580 | 405 | [8 empty] | 42
251 | 43/0 | DB1+0 | 01° 56' 25" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 345.988 | 350 |  | 12600 | 350 | [8 empty] | 36
252 | 43/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 475.789 | 480 |  | 17280 | 480 | [8 empty] | 48
253 | 43/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 363.648 | 365 |  | 13140 | 365 | [8 empty] | 36
254 | 43/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 431.843 | 435 |  | 15660 | 435 | [8 empty] | 42
255 | 43/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 405.305 | 410 |  | 14760 | 410 | [8 empty] | 42
256 | 43/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 427.816 | 430 |  | 15480 | 430 | [8 empty] | 42
257 | 43/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 389.757 | 390 |  | 14040 | 390 | [8 empty] | 36
258 | 43/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 449.543 | 450 |  | 16200 | 450 | [8 empty] | 42
259 | 43/8 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 387.977 | 390 |  | 14040 | 390 | [8 empty] | 36
260 | 43/9 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 346.332 | 350 |  | 12600 | 350 | [8 empty] | 36
261 | 43/10 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 444.843 | 445 |  | 16020 | 445 | [8 empty] | 42
262 | 43/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 383.925 | 385 |  | 13860 | 385 | [8 empty] | 36
263 | 44/0 | DB1+3 | 6° 14' 24.0" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 384.293 | 385 |  | 13860 | 385 | [8 empty] | 36
264 | 44/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 359 | 360 |  | 12960 | 360 | [8 empty] | 36
265 | 44/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 333.999 | 335 |  | 12060 | 335 | [8 empty] | 36
266 | 44/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 395 | 395 |  | 14220 | 395 | [8 empty] | 42
267 | 44/4 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 355.001 | 360 |  | 12960 | 360 | [8 empty] | 36
268 | 44/5 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 484.999 | 485 |  | 17460 | 485 | [8 empty] | 48
269 | 44/6 | DB1+3 | 0° 0' 0" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 473.001 | 475 |  | 17100 | 475 | [8 empty] | 48
270 | 44/7 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 367 | 370 |  | 13320 | 370 | [8 empty] | 36
271 | 44/8 | DCT1+0 | 0° 0' 0" | [5 empty] | 48 | 4 | 12 |  | 4 | 4 |  |  |  | 30 | 72 | 2 |  | 2 |  |  | 4
|  |  |  | 430 | 430 |  | 15480 | 430 | [8 empty] | 42
272 | 44/9 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 365 | 365 |  | 13140 | 365 | [8 empty] | 36
273 | 44/10 | DB1+9 | 0° 0' 0" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 428 | 430 |  | 15480 | 430 | [8 empty] | 42
274 | 44/11 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 327.231 | 330 |  | 11880 | 330 | [8 empty] | 30
275 | 45/0 | DC2+0 | 24° 55' 38.28" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 294.921 | 295 |  | 10620 | 295 | [8 empty] | 36
276 | 45/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.542 | 410 |  | 14760 | 410 | [8 empty] | 42
277 | 46/0 | DD60+25 | 28° 47' 23" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 199.082 | 200 |  | 7200 | 200 | [8 empty] | 18
278 | 47/0 | DD60+25 | 47° 00' 03" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 441.182 | 445 |  | 16020 | 445 | [8 empty] | 42
279 | 47/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 365.945 | 370 |  | 13320 | 370 | [8 empty] | 42
280 | 47/2 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 417.366 | 420 |  | 15120 | 420 | [8 empty] | 42
281 | 47/3 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 358.36 | 360 |  | 12960 | 360 | [8 empty] | 36
282 | 47/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 461.195 | 465 |  | 16740 | 465 | [8 empty] | 48
283 | 47/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 377.282 | 380 |  | 13680 | 380 | [8 empty] | 36
284 | 47/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 431.516 | 435 |  | 15660 | 435 | [8 empty] | 42
285 | 47/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 398.835 | 400 |  | 14400 | 400 | [8 empty] | 42
286 | 47/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 405.865 | 410 |  | 14760 | 410 | [8 empty] | 42
287 | 47/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 433.704 | 435 |  | 15660 | 435 | [8 empty] | 42
288 | 47/10 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386.154 | 390 |  | 14040 | 390 | [8 empty] | 36
289 | 48/0 | DC2+0 | 29°14'33.0" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 428.901 | 430 |  | 15480 | 430 | [8 empty] | 42
290 | 48/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.922 | 405 |  | 14580 | 405 | [8 empty] | 42
291 | 49/0 | DD45+0 | 33° 51' 14.4" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 379.1 | 380 |  | 13680 | 380 | [8 empty] | 36
292 | 49/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386.636 | 390 |  | 14040 | 390 | [8 empty] | 36
293 | 49/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 390.002 | 395 |  | 14220 | 395 | [8 empty] | 36
294 | 49/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 421.729 | 425 |  | 15300 | 425 | [8 empty] | 42
295 | 49/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 396.643 | 400 |  | 14400 | 400 | [8 empty] | 42
296 | 49/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.789 | 415 |  | 14940 | 415 | [8 empty] | 42
297 | 49/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 340.206 | 345 |  | 12420 | 345 | [8 empty] | 36
298 | 49/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 500.231 | 505 |  | 18180 | 505 | [8 empty] | 48
299 | 50/0 | DB2+0 | 8° 23' 20.04" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 469.069 | 470 |  | 16920 | 470 | [8 empty] | 48
300 | 50/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 367.133 | 370 |  | 13320 | 370 | [8 empty] | 36
301 | 50/2 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 470.387 | 475 |  | 17100 | 475 | [8 empty] | 48
302 | 50/3 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 354.811 | 355 |  | 12780 | 355 | [8 empty] | 36
303 | 50/4 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 442.053 | 445 |  | 16020 | 445 | [8 empty] | 42
304 | 50/5 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 364.426 | 365 |  | 13140 | 365 | [8 empty] | 36
305 | 50/6 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 470.777 | 475 |  | 17100 | 475 | [8 empty] | 48
306 | 50/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 345.004 | 350 |  | 12600 | 350 | [8 empty] | 36
307 | 50/8 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 364.406 | 365 |  | 13140 | 365 | [8 empty] | 36
308 | 50/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.591 | 395 |  | 14220 | 395 | [8 empty] | 42
309 | 50/10 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401.397 | 405 |  | 14580 | 405 | [8 empty] | 42
310 | 51/0 | DC2+0 | 25° 51' 48.24" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 356.579 | 360 |  | 12960 | 360 | [8 empty] | 36
311 | 51/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 307.101 | 310 |  | 11160 | 310 | [8 empty] | 30
312 | 51/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 384.965 | 385 |  | 13860 | 385 | [8 empty] | 36
313 | 52/0 | DC2+0 | 22° 21' 21.96" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 402.021 | 405 |  | 14580 | 405 | [8 empty] | 42
314 | 52/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.64 | 405 |  | 14580 | 405 | [8 empty] | 42
315 | 52/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 436.956 | 440 |  | 15840 | 440 | [8 empty] | 42
316 | 52/3 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 393.809 | 395 |  | 14220 | 395 | [8 empty] | 42
317 | 52/4 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 447.029 | 450 |  | 16200 | 450 | [8 empty] | 42
318 | 52/5 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 373.001 | 375 |  | 13500 | 375 | [8 empty] | 36
319 | 52/6 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.819 | 410 |  | 14760 | 410 | [8 empty] | 42
320 | 52/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 433.034 | 435 |  | 15660 | 435 | [8 empty] | 42
321 | 52/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 399.703 | 400 |  | 14400 | 400 | [8 empty] | 42
322 | 52/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 384.142 | 385 |  | 13860 | 385 | [8 empty] | 36
323 | 52/10 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 455.857 | 460 |  | 16560 | 460 | [8 empty] | 48
324 | 53/0 | DB2+9 | 6° 57' 38.88" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 433.242 | 435 |  | 15660 | 435 | [8 empty] | 42
325 | 53/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 407.406 | 410 |  | 14760 | 410 | [8 empty] | 42
326 | 53/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.498 | 395 |  | 14220 | 395 | [8 empty] | 42
327 | 53/3 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.082 | 415 |  | 14940 | 415 | [8 empty] | 42
328 | 53/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 428.073 | 430 |  | 15480 | 430 | [8 empty] | 42
329 | 53/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.604 | 410 |  | 14760 | 410 | [8 empty] | 42
330 | 53/6 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 411.298 | 415 |  | 14940 | 415 | [8 empty] | 42
331 | 53/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 427.748 | 430 |  | 15480 | 430 | [8 empty] | 42
332 | 53/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 371.307 | 375 |  | 13500 | 375 | [8 empty] | 36
333 | 54/0 | DB1+6 | 6° 44' 37.68" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 365.051 | 370 |  | 13320 | 370 | [8 empty] | 36
334 | 54/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 380.985 | 385 |  | 13860 | 385 | [8 empty] | 36
335 | 54/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 417.041 | 420 |  | 15120 | 420 | [8 empty] | 42
336 | 54/3 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 423.34 | 425 |  | 15300 | 425 | [8 empty] | 42
337 | 54/4 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.981 | 405 |  | 14580 | 405 | [8 empty] | 42
338 | 54/5 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 424.016 | 425 |  | 15300 | 425 | [8 empty] | 42
339 | 55/0 | DB1+6 | 2° 29' 53.88" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 404.939 | 405 |  | 14580 | 405 | [8 empty] | 42
340 | 55/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 343.124 | 345 |  | 12420 | 345 | [8 empty] | 36
341 | 55/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 357.687 | 360 |  | 12960 | 360 | [8 empty] | 36
342 | 55/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 365.158 | 370 |  | 13320 | 370 | [8 empty] | 36
343 | 55/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 350.096 | 355 |  | 12780 | 355 | [8 empty] | 36
344 | 55/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 357.682 | 360 |  | 12960 | 360 | [8 empty] | 36
345 | 55/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 337.791 | 340 |  | 12240 | 340 | [8 empty] | 36
346 | 55/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 341.218 | 345 |  | 12420 | 345 | [8 empty] | 42
347 | 55/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 460.489 | 465 |  | 16740 | 465 | [8 empty] | 48
348 | 56/0 | DD60+25 | 5° 23' 07" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 219.763 | 220 |  | 7920 | 220 | [8 empty] | 24
349 | 57/0 | DD60+25 | 0° 16' 10" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 461.115 | 465 |  | 16740 | 465 | [8 empty] | 48
350 | 57/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 355.491 | 360 |  | 12960 | 360 | [8 empty] | 42
351 | 57/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 405.387 | 410 |  | 14760 | 410 | [8 empty] | 42
352 | 57/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.151 | 420 |  | 15120 | 420 | [8 empty] | 42
353 | 57/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 416.747 | 420 |  | 15120 | 420 | [8 empty] | 42
354 | 57/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.972 | 395 |  | 14220 | 395 | [8 empty] | 42
355 | 57/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401.782 | 405 |  | 14580 | 405 | [8 empty] | 42
356 | 57/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 433.932 | 435 |  | 15660 | 435 | [8 empty] | 42
357 | 58/0 | DC1+3 | 19° 22' 13.08" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 238.897 | 240 |  | 8640 | 240 | [8 empty] | 24
358 | 59/0 | DC2+0 | 27° 51' 8.64" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 411.335 | 415 |  | 14940 | 415 | [8 empty] | 42
359 | 59/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.204 | 420 |  | 15120 | 420 | [8 empty] | 42
360 | 59/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.314 | 415 |  | 14940 | 415 | [8 empty] | 42
361 | 59/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.969 | 425 |  | 15300 | 425 | [8 empty] | 42
362 | 59/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.66 | 420 |  | 15120 | 420 | [8 empty] | 42
363 | 59/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.111 | 420 |  | 15120 | 420 | [8 empty] | 42
364 | 59/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.809 | 410 |  | 14760 | 410 | [8 empty] | 42
365 | 59/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426.933 | 430 |  | 15480 | 430 | [8 empty] | 42
366 | 59/8 | DB1+3 | 0° 0' 0" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 434.725 | 435 |  | 15660 | 435 | [8 empty] | 42
367 | 59/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.826 | 405 |  | 14580 | 405 | [8 empty] | 42
368 | 59/10 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 436.297 | 440 |  | 15840 | 440 | [8 empty] | 42
369 | 59/11 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 393.114 | 395 |  | 14220 | 395 | [8 empty] | 42
370 | 59/12 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 447.361 | 450 |  | 16200 | 450 | [8 empty] | 42
371 | 59/13 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 391.112 | 395 |  | 14220 | 395 | [8 empty] | 42
372 | 59/14 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 448.593 | 450 |  | 16200 | 450 | [8 empty] | 42
373 | 59/15 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 388 | 390 |  | 14040 | 390 | [8 empty] | 36
374 | 59/16 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 437.955 | 440 |  | 15840 | 440 | [8 empty] | 42
375 | 60/0 | DC1+0 | 20° 22' 38.64" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 413.81 | 415 |  | 14940 | 415 | [8 empty] | 42
376 | 60/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 424.2 | 425 |  | 15300 | 425 | [8 empty] | 42
377 | 60/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.521 | 415 |  | 14940 | 415 | [8 empty] | 42
378 | 60/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.581 | 430 |  | 15480 | 430 | [8 empty] | 42
379 | 60/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.27 | 415 |  | 14940 | 415 | [8 empty] | 42
380 | 60/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 374.127 | 375 |  | 13500 | 375 | [8 empty] | 36
381 | 60/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.05 | 415 |  | 14940 | 415 | [8 empty] | 42
382 | 60/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.355 | 405 |  | 14580 | 405 | [8 empty] | 42
383 | 60/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409.166 | 410 |  | 14760 | 410 | [8 empty] | 42
384 | 60/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.967 | 405 |  | 14580 | 405 | [8 empty] | 42
385 | 60/10 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.536 | 395 |  | 14220 | 395 | [8 empty] | 42
386 | 60/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 397.858 | 400 |  | 14400 | 400 | [8 empty] | 42
387 | 61/0 | DB2+0 | 13° 28' 15.24" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 405.656 | 410 |  | 14760 | 410 | [8 empty] | 42
388 | 61/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 433.158 | 435 |  | 15660 | 435 | [8 empty] | 42
389 | 61/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.923 | 405 |  | 14580 | 405 | [8 empty] | 42
390 | 61/3 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 427.004 | 430 |  | 15480 | 430 | [8 empty] | 42
391 | 61/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.927 | 415 |  | 14940 | 415 | [8 empty] | 42
392 | 61/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426.392 | 430 |  | 15480 | 430 | [8 empty] | 42
393 | 61/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 411.448 | 415 |  | 14940 | 415 | [8 empty] | 42
394 | 61/7 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 376.246 | 380 |  | 13680 | 380 | [8 empty] | 36
395 | 61/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 433.371 | 435 |  | 15660 | 435 | [8 empty] | 42
396 | 61/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 405.615 | 410 |  | 14760 | 410 | [8 empty] | 42
397 | 61/10 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 434.245 | 435 |  | 15660 | 435 | [8 empty] | 42
398 | 62/0 | DB2+0 | 7° 27' 29.88" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 418.001 | 420 |  | 15120 | 420 | [8 empty] | 42
399 | 62/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386.002 | 390 |  | 14040 | 390 | [8 empty] | 36
400 | 62/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 399.999 | 400 |  | 14400 | 400 | [8 empty] | 42
401 | 62/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.999 | 405 |  | 14580 | 405 | [8 empty] | 42
402 | 62/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403 | 405 |  | 14580 | 405 | [8 empty] | 42
403 | 62/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 404.001 | 405 |  | 14580 | 405 | [8 empty] | 42
404 | 62/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 423 | 425 |  | 15300 | 425 | [8 empty] | 42
405 | 62/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.999 | 410 |  | 14760 | 410 | [8 empty] | 42
406 | 62/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409 | 410 |  | 14760 | 410 | [8 empty] | 42
407 | 62/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 411.001 | 415 |  | 14940 | 415 | [8 empty] | 42
408 | 62/10 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.998 | 415 |  | 14940 | 415 | [8 empty] | 42
409 | 62/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386.106 | 390 |  | 14040 | 390 | [8 empty] | 36
410 | 63/0 | DC1+0 | 18° 26' 28.68" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 400 | 400 |  | 14400 | 400 | [8 empty] | 42
411 | 63/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 416.001 | 420 |  | 15120 | 420 | [8 empty] | 42
412 | 63/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.999 | 415 |  | 14940 | 415 | [8 empty] | 42
413 | 63/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 398.999 | 400 |  | 14400 | 400 | [8 empty] | 42
414 | 63/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.002 | 415 |  | 14940 | 415 | [8 empty] | 42
415 | 63/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426 | 430 |  | 15480 | 430 | [8 empty] | 42
416 | 63/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.998 | 415 |  | 14940 | 415 | [8 empty] | 42
417 | 63/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.001 | 430 |  | 15480 | 430 | [8 empty] | 42
418 | 63/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.342 | 410 |  | 14760 | 410 | [8 empty] | 42
419 | 64/0 | DB2+0 | 13° 49' 10.2" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 375.075 | 380 |  | 13680 | 380 | [8 empty] | 36
420 | 64/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.721 | 410 |  | 14760 | 410 | [8 empty] | 42
421 | 64/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.741 | 415 |  | 14940 | 415 | [8 empty] | 42
422 | 64/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.233 | 410 |  | 14760 | 410 | [8 empty] | 42
423 | 64/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426.149 | 430 |  | 15480 | 430 | [8 empty] | 42
424 | 64/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 407.715 | 410 |  | 14760 | 410 | [8 empty] | 42
425 | 64/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401.624 | 405 |  | 14580 | 405 | [8 empty] | 42
426 | 64/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.512 | 430 |  | 15480 | 430 | [8 empty] | 42
427 | 64/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.346 | 415 |  | 14940 | 415 | [8 empty] | 42
428 | 64/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.63 | 415 |  | 14940 | 415 | [8 empty] | 42
429 | 64/10 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 428.424 | 430 |  | 15480 | 430 | [8 empty] | 42
430 | 64/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.562 | 405 |  | 14580 | 405 | [8 empty] | 42
431 | 65/0 | DB1+0 | 2° 32' 0.6" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 395.375 | 400 |  | 14400 | 400 | [8 empty] | 42
432 | 65/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 393.737 | 395 |  | 14220 | 395 | [8 empty] | 42
433 | 65/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403.694 | 405 |  | 14580 | 405 | [8 empty] | 42
434 | 65/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.93 | 405 |  | 14580 | 405 | [8 empty] | 42
435 | 65/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 376.376 | 380 |  | 13680 | 380 | [8 empty] | 36
436 | 65/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 389.191 | 390 |  | 14040 | 390 | [8 empty] | 36
437 | 65/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 397.579 | 400 |  | 14400 | 400 | [8 empty] | 42
438 | 65/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.265 | 395 |  | 14220 | 395 | [8 empty] | 42
439 | 65/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 388.953 | 390 |  | 14040 | 390 | [8 empty] | 36
440 | 65/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 379.103 | 380 |  | 13680 | 380 | [8 empty] | 36
441 | 65/10 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 387.628 | 390 |  | 14040 | 390 | [8 empty] | 36
442 | 65/11 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426.927 | 430 |  | 15480 | 430 | [8 empty] | 42
443 | 66/0 | DC2+6 | 22° 23' 34.44" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 207.839 | 210 |  | 7560 | 210 | [8 empty] | 18
444 | 67/0 | DC1+9 | 17° 55' 44.04" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 347.141 | 350 |  | 12600 | 350 | [8 empty] | 36
445 | 67/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 344.931 | 345 |  | 12420 | 345 | [8 empty] | 36
446 | 67/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 369.226 | 370 |  | 13320 | 370 | [8 empty] | 36
447 | 68/0 | DD45+0 | 42° 20' 12.84" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 200.889 | 205 |  | 7380 | 205 | [8 empty] | 18
448 | 69/0 | DB2+0 | 12° 32' 12.12" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 374.132 | 375 |  | 13500 | 375 | [8 empty] | 36
449 | 69/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.886 | 395 |  | 14220 | 395 | [8 empty] | 42
450 | 70/0 | DC1+0 | 19° 34' 30.72" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 388.385 | 390 |  | 14040 | 390 | [8 empty] | 36
451 | 70/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.865 | 420 |  | 15120 | 420 | [8 empty] | 42
452 | 70/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.601 | 420 |  | 15120 | 420 | [8 empty] | 42
453 | 70/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.987 | 415 |  | 14940 | 415 | [8 empty] | 42
454 | 70/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.583 | 420 |  | 15120 | 420 | [8 empty] | 42
455 | 70/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.331 | 425 |  | 15300 | 425 | [8 empty] | 42
456 | 70/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.632 | 420 |  | 15120 | 420 | [8 empty] | 42
457 | 70/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.147 | 420 |  | 15120 | 420 | [8 empty] | 42
458 | 70/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.142 | 415 |  | 14940 | 415 | [8 empty] | 42
459 | 70/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.073 | 410 |  | 14760 | 410 | [8 empty] | 42
460 | 70/10 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.566 | 410 |  | 14760 | 410 | [8 empty] | 42
461 | 70/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.444 | 425 |  | 15300 | 425 | [8 empty] | 42
462 | 71/0 | DB2+3 | 9° 37' 5.52" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 398.637 | 400 |  | 14400 | 400 | [8 empty] | 42
463 | 71/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.33 | 415 |  | 14940 | 415 | [8 empty] | 42
464 | 71/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.012 | 415 |  | 14940 | 415 | [8 empty] | 42
465 | 71/3 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 367.658 | 370 |  | 13320 | 370 | [8 empty] | 36
466 | 71/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 429.409 | 430 |  | 15480 | 430 | [8 empty] | 42
467 | 71/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.031 | 410 |  | 14760 | 410 | [8 empty] | 42
468 | 71/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 404.849 | 405 |  | 14580 | 405 | [8 empty] | 42
469 | 71/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 431.601 | 435 |  | 15660 | 435 | [8 empty] | 42
470 | 71/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.371 | 410 |  | 14760 | 410 | [8 empty] | 42
471 | 72/0 | DB2+3 | 10° 39' 52.92" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 435.269 | 440 |  | 15840 | 440 | [8 empty] | 42
472 | 72/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403.852 | 405 |  | 14580 | 405 | [8 empty] | 42
473 | 72/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 389.167 | 390 |  | 14040 | 390 | [8 empty] | 36
474 | 72/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.085 | 405 |  | 14580 | 405 | [8 empty] | 42
475 | 73/0 | DB2+0 | 13° 10' 26.4" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 383.337 | 385 |  | 13860 | 385 | [8 empty] | 36
476 | 73/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 378.99 | 380 |  | 13680 | 380 | [8 empty] | 36
477 | 73/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 381.209 | 385 |  | 13860 | 385 | [8 empty] | 36
478 | 73/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 384.657 | 385 |  | 13860 | 385 | [8 empty] | 36
479 | 73/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 368.816 | 370 |  | 13320 | 370 | [8 empty] | 36
480 | 73/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 365.477 | 370 |  | 13320 | 370 | [8 empty] | 36
481 | 73/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 392.386 | 395 |  | 14220 | 395 | [8 empty] | 42
482 | 73/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 374.923 | 375 |  | 13500 | 375 | [8 empty] | 36
483 | 73/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 379.526 | 380 |  | 13680 | 380 | [8 empty] | 36
484 | 73/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 378.903 | 380 |  | 13680 | 380 | [8 empty] | 36
485 | 74/0 | DB2+0 | 9° 59' 12.84" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
Total |  |  |  | 191391.82 |  |  | 6932340 | 192565 | 4272 | 4876 | 1068 | 2382 | 106 | 4 | 0 | 0 | 19188 | 2670 | 72 | 178 | 397 | 574 | 0 | 0 | 1150 | 0
Receipt at Mandli | [10 empty] | 1002 | 2394 | 164 | 4 | 3827 | 1276 | 15372 | 1401 | 72 | 83 | 399 | 399 | 100 | 32 | 1130
Receipt at Phalsund | [10 empty] | 102 | 24 |  |  | 60 | 76 | 5124 | 1246 | 5 | 102 | 258 | 179 | 74 | 69 | 70
Total | [6 empty] | 0 | 0 | 0 | 0 | 1104 | 2418 | 164 | 4 | 3887 | 1352 | 20496 | 2647 | 77 | 185 | 657 | 578 | 174 | 101 | 1200
Balance | [6 empty] | 6932340 | 192565 | 4272 | 4876 | -36 | -36 | -58 | 0 | -3887 | -1352 | -1308 | 23 | -5 | -7 | -260 | -4 | -174 | -101 | -50

## Stringing Productivity
765KV D/C Fatehgarh III- Beawar Transmission Line, PKG F, Stringing Status | [39 empty] | Dated | 2026-02-24
Sr. No. | Sub-Contractor Name | Completed in April |  |  | Insulator Hoisting | [30 empty] | Output Upto Yesterdays (Kms) in May | Cumulative Output till today(Kms) | Start Date | Comp Date | Status | Total Manpower
|  | From | To | Span | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
0

## OPGW
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
OPGW
SL. No. | Section |  | Gang Name | Section Length | Paying out |  |  |  | Final Sag |  |  |  | Completion Month | Splicing | Splicing done by
| From | To |  |  | Section Length | Start Date | End Date | Remarks | Section Length | Start Date | End Date | Remarks
1 | 59/0 | 59/8 | Congent Technology | 3.337 | 3.337 | 2025-02-10 | 2025-02-11 |  | 3.337 | 2025-02-10 | 2025-02-11 | Final sag completed | 2025-02-01 | 2025-03-05 | Revant Sharma
2 | 59/8 | 60/0 | Congent Technology | 3.778 | 3.778 | 2025-02-12 | 2025-02-13 |  | 3.778 | 2025-02-12 | 2025-02-13 | Final sag completed | 2025-02-01 | 2025-02-26 | Revant Sharma
3 | 60/0 | 61/0 | Congent Technology | 4.877 | 4.877 | 2025-02-15 | 2025-02-16 |  | 4.877 | 2025-02-15 | 2025-02-16 | Final sag completed | 2025-02-01
4 | 61/0 | 62/0 | Congent Technology | 4.568 | 4.568 | 2025-02-19 | 2025-02-19 |  | 4.568 | 2025-02-19 | 2025-02-19 | Final sag completed | 2025-02-01 | 2025-02-27 | Revant Sharma
5 | 62/0 | 63/0 | Congent Technology | 4.863 | 4.863 | 2025-02-23 | 2025-02-24 |  | 4.863 | 2025-02-23 | 2025-02-24 | Final sag completed | 2025-02-01
6 | 63/0 | 64/0 | Congent Technology | 3.711 | 3.711 | 2025-03-01 | 2025-03-02 |  | 3.711 | 2025-03-01 | 2025-03-02 | Final sag completed | 2025-03-01
7 | 64/0 | 65/0 | Congent Technology | 4.918 | 4.918 | 2025-03-03 | 2025-03-03 |  | 4.918 | 2025-03-03 | 2025-03-03 | Final sag completed | 2025-03-01
8 | 51/0 | 52/0 | Congent Technology | 1.049 | 1.049 | 2025-07-23 | 2025-07-24 |  | 1.049 | 2025-07-23 | 2025-07-24 | Final sag completed | 2025-07-01
9 | 50/0 | 51/0 | Congent Technology | 4.444 | 4.444 | 2025-07-26 | 2025-07-26 |  | 4.444 | 2025-07-26 | 2025-07-26 | Final sag completed | 2025-07-01
10 | 48/0 | 49/0 | Congent Technology | 0.831 | 0.831 | 2025-08-02 | 2025-08-05 |  | 0.831 | 2025-08-02 | 2025-08-05 | Final sag completed | 2025-08-01
11 | 49/0 | 50/0 | Congent Technology | 3.227 | 3.227 | 2025-08-10 | 2025-08-14 |  | 3.227 | 2025-08-10 | 2025-08-14 | Final sag completed | 2025-08-01
12 | 70/0 | 71/0 | Congent Technology | 4.966 | 4.966 | 2025-12-17 | 2025-12-17 |  | 4.966 | 2025-12-17 | 2025-12-18 | Final sag completed | 2025-12-01
13 | 71/0 | 72/0 | Congent Technology | 3.675 | 3.675 | 2025-12-20 | 2025-12-20 |  | 3.675 | 2025-12-21 | 2025-12-21 | Final sag completed | 2025-12-01
14 | 72/0 | 73/0 | Congent Technology | 1.628 | 1.628 | 2025-12-23 | 2025-12-23 |  | 1.628 | 2025-12-24 | 2025-12-24 | Final sag completed | 2025-12-01
15 | 73/0 | 74/0 | Congent Technology | 3.788 | 3.788 | 2025-12-24 | 2025-12-24 |  | 3.788 | 2025-12-24 | 2025-12-24 | Final sag completed | 2025-12-01
16 | 65/0 | 66/0 | Congent Technology | 4.7358 | 4.7358 | 2026-01-04 | 2026-01-04 |  | 4.7358 | 2026-01-04 | 2026-01-04 | Final sag completed | 2026-01-01
17 | 66/0 | 70/0 | Congent Technology | 2.239 | 2.239 | 2026-01-05 | 2026-01-05 |  | 2.239 | 2026-01-07 | 2026-01-07 | Final sag completed | 2026-01-01
18 | Gty | 2/0 | Jai Bagrangbali | 3.638 | 3.638 | 2026-01-07 | 2026-01-07 |  | 3.638 | 2026-01-18 | 2026-01-19 | Final sag completed | 2026-01-01
19 | 47/0 | 48/0 | Congent Technology | 4.477 | 4.477 | 2026-02-05 | 2026-02-05 |  | 4.477 | 2026-02-05 | 2026-02-05 | Final sag completed | 2026-02-01
20 | 2/0 | 4/0 | Jai Bagrangbali | 4.05 | 4.05 | 2026-02-06 | 2026-02-06 |  | 4.05 | 2026-02-06 | 2026-02-06 | Final sag completed | 2026-02-01
21 | 57/0 | 59/0 | Congent Technology | 3.526 | 3.526 | 2026-02-07 | 2026-02-07 |  | 3.526 | 2026-02-07 | 2026-02-07 | Final sag completed | 2026-02-01
22 | 10/12 | 11/0 | Congent Technology | 4.95 | 4.95 | 2026-02-09 | 2026-02-09 |  | 4.95 | 2026-02-09 | 2026-02-09 | Final sag completed | 2026-02-01
TOTAL |  |  |  | 81.2758 |  |  |  |  | 81.2758
Formulas:
Start Date = [Start Date]
End Date = [End Date]

## Accessories details
Owner : M/S Resonai Limited | [25 empty] | Tower Type | Tower Wt. Above Middle Cross Arm | Total Tower | Total Wt. | Colour Specifications
Project : Fatehgarh-3-Beawar 765kV D/C Transmission Line (Hexa AL59 Zebra Conductor) Part-F | [25 empty] | DA | 4.903 | 147 | 720.741 | White & Orange, Berger BR SYN ENL IS2932
Line Name : 765kV DC Fatehgarh3-Beawar TL | [25 empty] | DB | 7.366 | 12 | 88.392
Contractor : - Kec International Limited | [25 empty] | DC | 8.319 | 7 | 58.233
Accessories & Aviation painting details | [25 empty] | DD | 9.255 | 7 | 64.785
|  |  |  | 485 | 485 | Installation of Phase Plate, Sets of Six | [5 empty] | 485 | Installation of Circuit, Sets of two |  |  | 485 | 485 | 397 | 246 | 164 | 7157 | 0 | 7157
|  |  |  | Danger Plate | Number Plate | Phase Plate | [6 empty] | Circuit |  |  | Circuit Plate | Anti Climbing Device | Bird Guard | Aviation requirements
Sl. No | Loc. No. | Tower Type | Span |  |  | Circuit - 1 Left Side when Face is towards Beawer |  |  | Circuit - 2 Right Side when Face is towards Beawer |  |  | Total Required | Circuit - I Left Side when Face is towards Beawer | Circuit - II Right Side when Face is towards Beawer | Set's:- CKT I + CKT II | [15 empty] | TOT | Ext | Concetanate
[19 empty] | Span Markers | Obstruction Light | Bird Flight Divertors (Non LED) |  |  | Painting Normal Towers | Weight of Painting portion
|  |  | m | Set of one | Set of one | Top | Middle | Bottom | Top | Middle | Bottom | Set of Six |  |  |  | Set of two | Set of one | Set of Six | Sets of 1 | 1 medium intensity+2 low intensity, Sets of 1 | E/W | OPGW | Total
| GANTRY | GTY
|  |  | 122 | [17 empty] | 11 |  | 11
1 | 1/0 | DD60+0 |  | 1 | 0001 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DD | 0 | DD+0
|  |  | 90 | [17 empty] | 8 |  | 8
2 | 1A/0 | DD60+0 |  | 1 | 0002 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DD | 0 | DD+0
|  |  | 277.7 | [17 empty] | 27 |  | 27
3 | 1A/1 | DA+6 |  | 1 | 0003 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 386 | [17 empty] | 38 |  | 38
4 | 1A/2 | DA+0 |  | 1 | 0004 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 443.6 | [17 empty] | 43 |  | 43
5 | 1A/3 | DA+0 |  | 1 | 0005 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 333.4 | [17 empty] | 32 |  | 32
6 | 1A/4 | DA+3 |  | 1 | 0006 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 431.9 | [17 empty] | 42 |  | 42
7 | 1A/5 | DA+0 |  | 1 | 0007 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 348.7 | [17 empty] | 34 |  | 34
8 | 1A/6 | DA+0 |  | 1 | 0008 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 395.7 | [17 empty] | 39 |  | 39
9 | 1A/7 | DA+3 |  | 1 | 0009 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 415 | [17 empty] | 41 |  | 41
10 | 1A/8 | DA+0 |  | 1 | 0010 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 394.3 | [17 empty] | 38 |  | 38
11 | 2/0 | DC1+0 |  | 1 | 0011 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 405.3 | [17 empty] | 40 |  | 40
12 | 2/1 | DA+3 |  | 1 | 0012 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 338.5 | [17 empty] | 33 |  | 33
13 | 2/2 | DA+3 |  | 1 | 0013 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 406 | [17 empty] | 40 |  | 40
14 | 2/3 | DA+3 |  | 1 | 0014 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 429 | [17 empty] | 42 |  | 42
15 | 2/4 | DA+3 |  | 1 | 0015 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 411.6 | [17 empty] | 40 |  | 40
16 | 2/5 | DA+3 |  | 1 | 0016 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 425.7 | [17 empty] | 42 |  | 42
17 | 2/6 | DA+3 |  | 1 | 0017 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 408.2 | [17 empty] | 40 |  | 40
18 | 2/7 | DA+3 |  | 1 | 0018 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 354.6 | [17 empty] | 34 |  | 34
19 | 2/8 | DA+0 |  | 1 | 0019 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 308.7 | [17 empty] | 30 |  | 30
20 | 2/9 | DA+0 |  | 1 | 0020 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 336 | [17 empty] | 33 |  | 33
21 | 3/0 | DD60+6 |  | 1 | 0021 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DD | 6 | DD+6
|  |  | 226.5 | [17 empty] | 22 |  | 22
22 | 4/0 | DD60+6 |  | 1 | 0022 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DD | 6 | DD+6
|  |  | 343 | [17 empty] | 33 |  | 33
23 | 4/1 | DA+0 |  | 1 | 0023 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 358.4 | [17 empty] | 35 |  | 35
24 | 4/2 | DA+0 |  | 1 | 0024 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 381 | [17 empty] | 37 |  | 37
25 | 4/3 | DA+0 |  | 1 | 0025 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 367.6 | [17 empty] | 36 |  | 36
26 | 4/4 | DA+0 |  | 1 | 0026 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 423.1 | [17 empty] | 41 |  | 41
27 | 5/0 | DB1+9 |  | 1 | 0027 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 9 | DB+9
|  |  | 246 | [17 empty] | 24 |  | 24
28 | 6/0 | DB2+9 |  | 1 | 0028 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 9 | DB+9
|  |  | 429.9 | [17 empty] | 42 |  | 42
29 | 6/1 | DA+0 |  | 1 | 0029 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 362.4 | [17 empty] | 35 |  | 35
30 | 6/2 | DA+0 |  | 1 | 0030 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 347.9 | [17 empty] | 34 |  | 34
31 | 7/0 | DB1+0 |  | 1 | 0031 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 210.8 | [17 empty] | 20 |  | 20
32 | 8/0 | DB1+0 |  | 1 | 0032 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 409.2 | [17 empty] | 40 |  | 40
33 | 8/1 | DA+3 |  | 1 | 0033 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 413.6 | [17 empty] | 40 |  | 40
34 | 8/2 | DA+3 |  | 1 | 0034 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 393.2 | [17 empty] | 38 |  | 38
35 | 8/3 | DA+0 |  | 1 | 0035 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 416.5 | [17 empty] | 41 |  | 41
36 | 8/4 | DA+3 |  | 1 | 0036 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 394.6 | [17 empty] | 38 |  | 38
37 | 8/5 | DA+3 |  | 1 | 0037 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 393.2 | [17 empty] | 38 |  | 38
38 | 8/6 | DA+3 |  | 1 | 0038 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 441.1 | [17 empty] | 43 |  | 43
39 | 8/7 | DB1+0 |  | 1 | 0039 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 414.4 | [17 empty] | 40 |  | 40
40 | 8/8 | DA+6 |  | 1 | 0040 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 395.863 | [17 empty] | 39 |  | 39
41 | 8/9 | DA+3 |  | 1 | 0041 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 413.404 | [17 empty] | 40 |  | 40
42 | 8/10 | DA+3 |  | 1 | 0042 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 402.6 | [17 empty] | 39 |  | 39
43 | 8/11 | DA+0 |  | 1 | 0043 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 372.1 | [17 empty] | 36 |  | 36
44 | 8/12 | DA+0 |  | 1 | 0044 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 457.7 | [15 empty] | 1 |  | 45 |  | 45
45 | 9/0 | DD60+18 |  | 1 | 0045 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 9.255 | [5 empty] | DD | 18 | DD+18
|  |  | 233.1 | [15 empty] | 1 |  | 15 |  | 15
46 | 10/0 | DD60+25 |  | 1 | 0046 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 9.255 | [5 empty] | DD | 25 | DD+25
|  |  | 443.7 | [15 empty] | 1 |  | 29 |  | 29
47 | 10/1 | DA+0 |  | 1 | 0047 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 383.2 | [17 empty] | 25 |  | 25
48 | 10/2 | DA+0 |  | 1 | 0048 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 398.6 | [17 empty] | 26 |  | 26
49 | 10/3 | DA+0 |  | 1 | 0049 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 410.7 | [17 empty] | 26 |  | 26
50 | 10/4 | DA+3 |  | 1 | 0050 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 416.2 | [17 empty] | 27 |  | 27
51 | 10/5 | DA+3 |  | 1 | 0051 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 403.4 | [17 empty] | 26 |  | 26
52 | 10/6 | DA+0 |  | 1 | 0052 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 373.845 | [17 empty] | 24 |  | 24
53 | 10/7 | DA+3 |  | 1 | 0053 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 411.823 | [17 empty] | 26 |  | 26
54 | 10/8 | DA+3 |  | 1 | 0054 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 414.2 | [17 empty] | 27 |  | 27
55 | 10/9 | DA+0 |  | 1 | 0055 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 402.3 | [17 empty] | 26 |  | 26
56 | 10/10 | DA+3 |  | 1 | 0056 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 430.3 | [17 empty] | 28 |  | 28
57 | 10/11 | DA+3 |  | 1 | 0057 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 406.2 | [17 empty] | 26 |  | 26
58 | 10/12 | DB1+0 |  | 1 | 0058 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 405.3 | [17 empty] | 26 |  | 26
59 | 10/13 | DA+3 |  | 1 | 0059 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 427.1 | [17 empty] | 27 |  | 27
60 | 10/14 | DA+3 |  | 1 | 0060 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 400 | [17 empty] | 26 |  | 26
61 | 10/15 | DA+3 |  | 1 | 0061 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 412.8 | [17 empty] | 27 |  | 27
62 | 10/16 | DA+3 |  | 1 | 0062 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 387.8 | [17 empty] | 25 |  | 25
63 | 10/17 | DA+3 |  | 1 | 0063 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 436.7 | [17 empty] | 28 |  | 28
64 | 10/18 | DA+3 |  | 1 | 0064 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 403.7 | [17 empty] | 26 |  | 26
65 | 10/19 | DA+0 |  | 1 | 0065 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 409.5 | [17 empty] | 26 |  | 26
66 | 10/20 | DA+3 |  | 1 | 0066 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 418.6 | [17 empty] | 27 |  | 27
67 | 10/21 | DA+3 |  | 1 | 0067 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 410.3 | [17 empty] | 26 |  | 26
68 | 10/22 | DA+0 |  | 1 | 0068 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 384 | [17 empty] | 25 |  | 25
69 | 10/23 | DA+0 |  | 1 | 0069 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 450.8 | [17 empty] | 29 |  | 29
70 | 11/0 | DB1+0 |  | 1 | 0070 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 384.2 | [17 empty] | 25 |  | 25
71 | 11/1 | DA+0 |  | 1 | 0071 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 338.6 | [17 empty] | 22 |  | 22
72 | 11/2 | DA+0 |  | 1 | 0072 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 370.7 | [17 empty] | 24 |  | 24
73 | 11/3 | DA+0 |  | 1 | 0073 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 434.1 | [17 empty] | 28 |  | 28
74 | 11/4 | DA+0 |  | 1 | 0074 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 368.1 | [17 empty] | 24 |  | 24
75 | 11/5 | DA+0 |  | 1 | 0075 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 342.3 | [17 empty] | 22 |  | 22
76 | 11A/0 | DB1+0 |  | 1 | 0076 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 405.1 | [17 empty] | 26 |  | 26
77 | 11A/1 | DA+3 |  | 1 | 0077 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 412.2 | [17 empty] | 26 |  | 26
78 | 11A/2 | DA+0 |  | 1 | 0078 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 412.2 | [17 empty] | 26 |  | 26
79 | 11A/3 | DA+3 |  | 1 | 0079 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 422.1 | [17 empty] | 27 |  | 27
80 | 11A/4 | DA+3 |  | 1 | 0080 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 418.3 | [17 empty] | 27 |  | 27
81 | 11A/5 | DA+3 |  | 1 | 0081 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 384.3 | [17 empty] | 25 |  | 25
82 | 11A/6 | DA+6 |  | 1 | 0082 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 434.2 | [17 empty] | 28 |  | 28
83 | 11A/7 | DA+9 |  | 1 | 0083 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 390.1 | [17 empty] | 25 |  | 25
84 | 11A/8 | DA+6 |  | 1 | 0084 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 426.3 | [17 empty] | 27 |  | 27
85 | 11A/9 | DA+3 |  | 1 | 0085 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 405.9 | [17 empty] | 26 |  | 26
86 | 12/0 | DD60+0 |  | 1 | 0086 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DD | 0 | DD+0
|  |  | 211.9 | [17 empty] | 13 |  | 13
87 | 13/0 | DD60+3 |  | 1 | 0087 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DD | 3 | DD+3
|  |  | 464.3 | [17 empty] | 30 |  | 30
88 | 13/1 | DA+9 |  | 1 | 0088 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 373.7 | [17 empty] | 24 |  | 24
89 | 13/2 | DA+3 |  | 1 | 0089 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 419.7 | [17 empty] | 27 |  | 27
90 | 13/3 | DA+3 |  | 1 | 0090 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 420.3 | [17 empty] | 27 |  | 27
91 | 13/4 | DA+3 |  | 1 | 0091 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 400 | [17 empty] | 26 |  | 26
92 | 14/0 | DC2+0 |  | 1 | 0092 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 381.4 | [17 empty] | 24 |  | 24
93 | 14A/0 | DC1+0 |  | 1 | 0093 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 412.765 | [17 empty] | 27 |  | 27
94 | 14A/1 | DA+3 |  | 1 | 0094 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 396.029 | [17 empty] | 25 |  | 25
95 | 14A/2 | DA+0 |  | 1 | 0095 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 383.3 | [17 empty] | 25 |  | 25
96 | 15/0 | DC1+0 |  | 1 | 0096 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 404.6 | [17 empty] | 26 |  | 26
97 | 15/1 | DA+3 |  | 1 | 0097 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 413.3 | [17 empty] | 27 |  | 27
98 | 16/0 | DC1+0 |  | 1 | 0098 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 354.283 | [17 empty] | 23 |  | 23
99 | 16/1 | DA+0 |  | 1 | 0099 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 424.28 | [17 empty] | 27 |  | 27
100 | 16/2 | DA+0 |  | 1 | 0100 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 340.3 | [17 empty] | 22 |  | 22
101 | 16/3 | DA+3 |  | 1 | 0101 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 394.7 | [17 empty] | 25 |  | 25
102 | 16/4 | DA+0 |  | 1 | 0102 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 435.863 | [17 empty] | 28 |  | 28
103 | 16/5 | DA+3 |  | 1 | 0103 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 386.8 | [17 empty] | 25 |  | 25
104 | 17/0 | DB2+3 |  | 1 | 0104 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 3 | DB+3
|  |  | 393.7 | [17 empty] | 25 |  | 25
105 | 17/1 | DA+3 |  | 1 | 0105 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 415.9 | [17 empty] | 27 |  | 27
106 | 17/2 | DA+6 |  | 1 | 0106 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 422.8 | [17 empty] | 27 |  | 27
107 | 17/3 | DA+0 |  | 1 | 0107 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 409.9 | [17 empty] | 26 |  | 26
108 | 17/4 | DA+3 |  | 1 | 0108 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 425.3 | [17 empty] | 27 |  | 27
109 | 17/5 | DA+3 |  | 1 | 0109 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 383.4 | [17 empty] | 25 |  | 25
110 | 18/0 | DC2+0 |  | 1 | 0110 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 372.8 | [17 empty] | 24 |  | 24
111 | 18/1 | DA+0 |  | 1 | 0111 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 379.8 | [17 empty] | 24 |  | 24
112 | 18/2 | DA+0 |  | 1 | 0112 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 371 | [17 empty] | 24 |  | 24
113 | 18/3 | DA+0 |  | 1 | 0113 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 398.7 | [17 empty] | 26 |  | 26
114 | 18/4 | DA+0 |  | 1 | 0114 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 380.8 | [17 empty] | 24 |  | 24
115 | 19/0 | DC2+0 |  | 1 | 0115 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 366.9 | [17 empty] | 23 |  | 23
116 | 19/1 | DA+0 |  | 1 | 0116 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 372.5 | [17 empty] | 24 |  | 24
117 | 19/2 | DA+0 |  | 1 | 0117 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 376.5 | [17 empty] | 24 |  | 24
118 | 19/3 | DA+0 |  | 1 | 0118 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 384.3 | [17 empty] | 25 |  | 25
119 | 19/4 | DA+0 |  | 1 | 0119 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 375.4 | [17 empty] | 24 |  | 24
120 | 19/5 | DA+0 |  | 1 | 0120 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 381.2 | [17 empty] | 24 |  | 24
121 | 20/0 | DB2+0 |  | 1 | 0121 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 386.8 | [17 empty] | 25 |  | 25
122 | 20/1 | DA+0 |  | 1 | 0122 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 387 | [17 empty] | 25 |  | 25
123 | 20/2 | DA+0 |  | 1 | 0123 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 348.5 | [17 empty] | 22 |  | 22
124 | 20/3 | DA+0 |  | 1 | 0124 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 355 | [17 empty] | 23 |  | 23
125 | 21/0 | DB2+0 |  | 1 | 0125 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 414.9 | [17 empty] | 27 |  | 27
126 | 21/1 | DA+6 |  | 1 | 0126 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 407.2 | [17 empty] | 26 |  | 26
127 | 21/2 | DA+0 |  | 1 | 0127 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 432.2 | [17 empty] | 28 |  | 28
128 | 21/3 | DA+6 |  | 1 | 0128 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 401.9 | [17 empty] | 26 |  | 26
129 | 21/4 | DA+3 |  | 1 | 0129 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 434.2 | [17 empty] | 28 |  | 28
130 | 21/5 | DA+6 |  | 1 | 0130 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 405.5 | [17 empty] | 26 |  | 26
131 | 21/6 | DA+3 |  | 1 | 0131 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 426 | [17 empty] | 27 |  | 27
132 | 21/7 | DA+3 |  | 1 | 0132 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 406.9 | [17 empty] | 26 |  | 26
133 | 21/8 | DA+6 |  | 1 | 0133 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 433.3 | [17 empty] | 28 |  | 28
134 | 21/9 | DA+3 |  | 1 | 0134 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 372.9 | [17 empty] | 24 |  | 24
135 | 21/10 | DA+6 |  | 1 | 0135 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 443.5 | [17 empty] | 29 |  | 29
136 | 22/0 | DB2+3 |  | 1 | 0136 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 3 | DB+3
|  |  | 456.3 | [17 empty] | 29 |  | 29
137 | 22/1 | DA+9 |  | 1 | 0137 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 379.2 | [17 empty] | 24 |  | 24
138 | 22/2 | DA+6 |  | 1 | 0138 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 382.6 | [17 empty] | 25 |  | 25
139 | 22/3 | DA+9 |  | 1 | 0139 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 435.6 | [17 empty] | 28 |  | 28
140 | 22/4 | DA+9 |  | 1 | 0140 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 402.1 | [17 empty] | 26 |  | 26
141 | 22/5 | DA+9 |  | 1 | 0141 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 417.3 | [17 empty] | 27 |  | 27
142 | 22/6 | DA+0 |  | 1 | 0142 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 347.7 | [17 empty] | 22 |  | 22
143 | 22/7 | DA+0 |  | 1 | 0143 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 356.3 | [17 empty] | 23 |  | 23
144 | 22/8 | DB1+0 |  | 1 | 0144 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 389.2 | [17 empty] | 25 |  | 25
145 | 22/9 | DA+6 |  | 1 | 0145 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 343.8 | [17 empty] | 22 |  | 22
146 | 22/10 | DA+6 |  | 1 | 0146 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 395.5 | [17 empty] | 25 |  | 25
147 | 22/11 | DA+6 |  | 1 | 0147 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 408 | [17 empty] | 26 |  | 26
148 | 22/12 | DA+3 |  | 1 | 0148 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 318 | [17 empty] | 20 |  | 20
149 | 22/13 | DA+6 |  | 1 | 0149 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 447.3 | [17 empty] | 29 |  | 29
150 | 23/0 | DD45+3 |  | 1 | 0150 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DD | 3 | DD+3
|  |  | 222.2 | [17 empty] | 14 |  | 14
151 | 24/0 | DD45+3 |  | 1 | 0151 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DD | 3 | DD+3
|  |  | 433.9 | [17 empty] | 28 |  | 28
152 | 25/0 | DC1+6 |  | 1 | 0152 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 6 | DC+6
|  |  | 422.3 | [17 empty] | 27 |  | 27
153 | 25/1 | DA+3 |  | 1 | 0153 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 370.7 | [17 empty] | 24 |  | 24
154 | 25/2 | DA+0 |  | 1 | 0154 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 345.7 | [17 empty] | 22 |  | 22
155 | 25/3 | DA+0 |  | 1 | 0155 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 391.1 | [17 empty] | 25 |  | 25
156 | 25/4 | DA+0 |  | 1 | 0156 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 440.4 | [17 empty] | 28 |  | 28
157 | 26/0 | DB1+0 |  | 1 | 0157 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 391.4 | [17 empty] | 25 |  | 25
158 | 26/1 | DA+0 |  | 1 | 0158 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 406.5 | [17 empty] | 26 |  | 26
159 | 26/2 | DA+3 |  | 1 | 0159 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 418 | [17 empty] | 27 |  | 27
160 | 26/3 | DA+0 |  | 1 | 0160 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 422.6 | [17 empty] | 27 |  | 27
161 | 26/4 | DA+6 |  | 1 | 0161 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 410 | [17 empty] | 26 |  | 26
162 | 26/5 | DA+6 |  | 1 | 0162 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 363.4 | [17 empty] | 23 |  | 23
163 | 26/6 | DA+6 |  | 1 | 0163 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 421.9 | [17 empty] | 27 |  | 27
164 | 26/7 | DA+0 |  | 1 | 0164 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 416.7 | [17 empty] | 27 |  | 27
165 | 26/8 | DA+6 |  | 1 | 0165 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 413.8 | [17 empty] | 27 |  | 27
166 | 27/0 | DC1+0 |  | 1 | 0166 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 399.8 | [17 empty] | 26 |  | 26
167 | 27/1 | DA+3 |  | 1 | 0167 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 425.2 | [17 empty] | 27 |  | 27
168 | 27/2 | DA+3 |  | 1 | 0168 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 398.6 | [17 empty] | 26 |  | 26
169 | 27/3 | DA+3 |  | 1 | 0169 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 430.7 | [17 empty] | 28 |  | 28
170 | 27/4 | DA+3 |  | 1 | 0170 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 410 | [17 empty] | 26 |  | 26
171 | 27/5 | DA+0 |  | 1 | 0171 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 402.6 | [17 empty] | 26 |  | 26
172 | 27/6 | DA+0 |  | 1 | 0172 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 343.5 | [17 empty] | 22 |  | 22
173 | 27/7 | DB1+0 |  | 1 | 0173 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 392 | [17 empty] | 25 |  | 25
174 | 27/8 | DA+0 |  | 1 | 0174 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 381.1 | [17 empty] | 24 |  | 24
175 | 27/9 | DA+0 |  | 1 | 0175 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 366.3 | [17 empty] | 23 |  | 23
176 | 27/10 | DA+3 |  | 1 | 0176 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 420.1 | [17 empty] | 27 |  | 27
177 | 27/11 | DA+3 |  | 1 | 0177 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 420.8 | [17 empty] | 27 |  | 27
178 | 27/12 | DA+3 |  | 1 | 0178 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 406.6 | [17 empty] | 26 |  | 26
179 | 28/0 | DB2+0 |  | 1 | 0179 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 379.6 | [17 empty] | 24 |  | 24
180 | 28/1 | DA+0 |  | 1 | 0180 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 385 | [17 empty] | 25 |  | 25
181 | 28/2 | DA+0 |  | 1 | 0181 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 369 | [17 empty] | 24 |  | 24
182 | 28/3 | DA+0 |  | 1 | 0182 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 409 | [17 empty] | 26 |  | 26
183 | 28/4 | DA+0 |  | 1 | 0183 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 422 | [17 empty] | 27 |  | 27
184 | 28/5 | DA+9 |  | 1 | 0184 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 370 | [17 empty] | 24 |  | 24
185 | 28/6 | DA+6 |  | 1 | 0185 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 464 | [17 empty] | 30 |  | 30
186 | 28/7 | DA+3 |  | 1 | 0186 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 375 | [17 empty] | 24 |  | 24
187 | 28/8 | DA+3 |  | 1 | 0187 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 465.5 | [17 empty] | 30 |  | 30
188 | 29/0 | DB1+0 |  | 1 | 0188 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 365.6 | [17 empty] | 23 |  | 23
189 | 29/1 | DA+3 |  | 1 | 0189 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 424 | [17 empty] | 27 |  | 27
190 | 29/2 | DA+3 |  | 1 | 0190 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 399 | [17 empty] | 26 |  | 26
191 | 29/3 | DA+0 |  | 1 | 0191 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 440 | [17 empty] | 28 |  | 28
192 | 29/4 | DA+6 |  | 1 | 0192 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 382.1 | [17 empty] | 24 |  | 24
193 | 30/0 | DC1+0 |  | 1 | 0193 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 388.9 | [17 empty] | 25 |  | 25
194 | 30/1 | DA+0 |  | 1 | 0194 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 445 | [17 empty] | 29 |  | 29
195 | 30/2 | DA+0 |  | 1 | 0195 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 395 | [17 empty] | 25 |  | 25
196 | 30/3 | DA+3 |  | 1 | 0196 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 387 | [17 empty] | 25 |  | 25
197 | 30/4 | DA+3 |  | 1 | 0197 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 442 | [17 empty] | 28 |  | 28
198 | 30/5 | DA+3 |  | 1 | 0198 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 314 | [17 empty] | 20 |  | 20
199 | 30/6 | DA+0 |  | 1 | 0199 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 347.4 | [17 empty] | 22 |  | 22
200 | 31/0 | DB2+0 |  | 1 | 0200 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 383.6 | [17 empty] | 25 |  | 25
201 | 31/1 | DA+0 |  | 1 | 0201 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 366 | [17 empty] | 23 |  | 23
202 | 31/2 | DA+0 |  | 1 | 0202 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 332.9 | [17 empty] | 21 |  | 21
203 | 32/0 | DC1+0 |  | 1 | 0203 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 402.7 | [17 empty] | 26 |  | 26
204 | 32/1 | DA+3 |  | 1 | 0204 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 428.8 | [17 empty] | 28 |  | 28
205 | 32/2 | DA+3 |  | 1 | 0205 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 410.9 | [17 empty] | 26 |  | 26
206 | 32/3 | DA+0 |  | 1 | 0206 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 381.1 | [17 empty] | 24 |  | 24
207 | 32/4 | DA+0 |  | 1 | 0207 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 451.5 | [17 empty] | 29 |  | 29
208 | 33/0 | DC1+0 |  | 1 | 0208 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 379.6 | [17 empty] | 24 |  | 24
209 | 33/1 | DA+0 |  | 1 | 0209 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 292.5 | [17 empty] | 19 |  | 19
210 | 34/0 | DB2+0 |  | 1 | 0210 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 432.6 | [17 empty] | 28 |  | 28
211 | 34/1 | DA+9 |  | 1 | 0211 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 407.5 | [17 empty] | 26 |  | 26
212 | 34/2 | DA+6 |  | 1 | 0212 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 377 | [17 empty] | 24 |  | 24
213 | 34/3 | DA+0 |  | 1 | 0213 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 451.6 | [17 empty] | 29 |  | 29
214 | 34/4 | DA+0 |  | 1 | 0214 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 379.3 | [17 empty] | 24 |  | 24
215 | 35/0 | DB2+6 |  | 1 | 0215 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 6 | DB+6
|  |  | 265.6 | [17 empty] | 17 |  | 17
216 | 35/1 | DA+9 |  | 1 | 0216 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 492.4 | [17 empty] | 32 |  | 32
217 | 35/2 | DB1+0 |  | 1 | 0217 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 522.2 | [17 empty] | 34 |  | 34
218 | 35/3 | DB1+6 |  | 1 | 0218 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 6 | DB+6
|  |  | 418.9 | [17 empty] | 27 |  | 27
219 | 35/4 | DA+0 |  | 1 | 0219 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 421.7 | [17 empty] | 27 |  | 27
220 | 35/5 | DA+0 |  | 1 | 0220 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 342.7 | [17 empty] | 22 |  | 22
221 | 36/0 | DB2+0 |  | 1 | 0221 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 386.4 | [17 empty] | 25 |  | 25
222 | 36/1 | DA+0 |  | 1 | 0222 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 309.4 | [17 empty] | 20 |  | 20
223 | 36/2 | DA+0 |  | 1 | 0223 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 357.8 | [17 empty] | 23 |  | 23
224 | 36/3 | DA+0 |  | 1 | 0224 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 480.4 | [17 empty] | 31 |  | 31
225 | 36/4 | DA+6 |  | 1 | 0225 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 350.5 | [17 empty] | 22 |  | 22
226 | 37/0 | DB2+0 |  | 1 | 0226 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 443.3 | [17 empty] | 29 |  | 29
227 | 37/1 | DA+9 |  | 1 | 0227 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 356.7 | [17 empty] | 23 |  | 23
228 | 37/2 | DA+3 |  | 1 | 0228 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 339.9 | [17 empty] | 22 |  | 22
229 | 37/3 | DA+0 |  | 1 | 0229 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 500.3 | [17 empty] | 32 |  | 32
230 | 38/0 | DB2+6 |  | 1 | 0230 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 6 | DB+6
|  |  | 421.4 | [17 empty] | 27 |  | 27
231 | 38/1 | DA+0 |  | 1 | 0231 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 419 | [17 empty] | 27 |  | 27
232 | 38/2 | DA+6 |  | 1 | 0232 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 420.3 | [17 empty] | 27 |  | 27
233 | 38/3 | DA+9 |  | 1 | 0233 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 414.9 | [17 empty] | 27 |  | 27
234 | 38/4 | DA+9 |  | 1 | 0234 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 425.5 | [17 empty] | 27 |  | 27
235 | 39/0 | DB2+6 |  | 1 | 0235 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 6 | DB+6
|  |  | 412.638 | [17 empty] | 27 |  | 27
236 | 39/1 | DA+0 |  | 1 | 0236 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 322.61 | [17 empty] | 21 |  | 21
237 | 40/0 | DC2+0 |  | 1 | 0237 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 396.2 | [17 empty] | 25 |  | 25
238 | 40/1 | DA+6 |  | 1 | 0238 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 425.8 | [17 empty] | 27 |  | 27
239 | 40/2 | DA+3 |  | 1 | 0239 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 401.7 | [17 empty] | 26 |  | 26
240 | 40/3 | DA+3 |  | 1 | 0240 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 436.3 | [17 empty] | 28 |  | 28
241 | 41/0 | DC1+6 |  | 1 | 0241 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 6 | DC+6
|  |  | 340.8 | [17 empty] | 22 |  | 22
242 | 41/1 | DB1+9 |  | 1 | 0242 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 9 | DB+9
|  |  | 447.8 | [15 empty] | 1 |  | 29 |  | 29
243 | 41/2 | DA+0 |  | 1 | 0243 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 382.3 | [15 empty] | 1 |  | 24 |  | 24
244 | 42/0 | DC1+0 |  | 1 | 0244 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 384.7 | [15 empty] | 1 |  | 25 |  | 25
245 | 42/1 | DA+6 |  | 1 | 0245 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 407.4 | [15 empty] | 1 |  | 26 |  | 26
246 | 42/2 | DA+6 |  | 1 | 0246 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 414.2 | [15 empty] | 1 |  | 27 |  | 27
247 | 42/3 | DA+0 |  | 1 | 0247 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 256.4 | [15 empty] | 1 |  | 16 |  | 16
248 | 42/4 | DA+0 |  | 1 | 0248 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 403.8 | [15 empty] | 1 |  | 26 |  | 26
249 | 42/5 | DA+9 |  | 1 | 0249 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 396.7 | [15 empty] | 1 |  | 25 |  | 25
250 | 42/6 | DA+0 |  | 1 | 0250 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 403.9 | [15 empty] | 1 |  | 26 |  | 26
251 | 43/0 | DB1+0 |  | 1 | 0251 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 346 | [15 empty] | 1 |  | 22 |  | 22
252 | 43/1 | DA+3 |  | 1 | 0252 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 475.8 | [15 empty] | 1 |  | 31 |  | 31
253 | 43/2 | DA+0 |  | 1 | 0253 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 363.7 | [15 empty] | 1 |  | 23 |  | 23
254 | 43/3 | DA+0 |  | 1 | 0254 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 431.8 | [15 empty] | 1 |  | 28 |  | 28
255 | 43/4 | DA+3 |  | 1 | 0255 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 405.3 | [15 empty] | 1 |  | 26 |  | 26
256 | 43/5 | DA+3 |  | 1 | 0256 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 427.8 | [15 empty] | 1 |  | 28 |  | 28
257 | 43/6 | DA+3 |  | 1 | 0257 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 389.8 | [15 empty] | 1 |  | 25 |  | 25
258 | 43/7 | DA+3 |  | 1 | 0258 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 449.5 | [15 empty] | 1 |  | 29 |  | 29
259 | 43/8 | DA+9 |  | 1 | 0259 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 388 | [15 empty] | 1 |  | 25 |  | 25
260 | 43/9 | DA+9 |  | 1 | 0260 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 346.3 | [15 empty] | 1 |  | 22 |  | 22
261 | 43/10 | DA+3 |  | 1 | 0261 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 444.8 | [15 empty] | 1 |  | 29 |  | 29
262 | 43/11 | DA+3 |  | 1 | 0262 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 383.9 | [15 empty] | 1 |  | 25 |  | 25
263 | 44/0 | DB1+3 |  | 1 | 0263 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 3 | DB+3
|  |  | 384.3 | [15 empty] | 1 |  |  |  | 0
264 | 44/1 | DA+0 |  | 1 | 0264 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 359 | [15 empty] | 1 |  |  |  | 0
265 | 44/2 | DA+0 |  | 1 | 0265 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 334 | [15 empty] | 1 |  |  |  | 0
266 | 44/3 | DA+0 |  | 1 | 0266 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 395 | [15 empty] | 1 |  |  |  | 0
267 | 44/4 | DA+9 |  | 1 | 0267 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 355 | [15 empty] | 1 |  |  |  | 0
268 | 44/5 | DA+9 |  | 1 | 0268 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 485 | [15 empty] | 1 |  |  |  | 0
269 | 44/6 | DB1+3 |  | 1 | 0269 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 3 | DB+3
|  |  | 473 | [15 empty] | 1 |  |  |  | 0
270 | 44/7 | DA+9 |  | 1 | 0270 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 367 | [15 empty] | 1 |  |  |  | 0
271 | 44/8 | DCT+0 |  | 1 | 0271 | R | B | Y | R | B | Y | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 430 | [15 empty] | 1 |  |  |  | 0
272 | 44/9 | DA+9 |  | 1 | 0272 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 365 | [15 empty] | 1 |  |  |  | 0
273 | 44/10 | DB1+9 |  | 1 | 0273 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 9 | DB+9
|  |  | 428 | [15 empty] | 1 |  |  |  | 0
274 | 44/11 | DA+0 |  | 1 | 0274 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 327.2 | [15 empty] | 1 |  |  |  | 0
275 | 45/0 | DC2+0 |  | 1 | 0275 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 294.92 | [15 empty] | 1 |  |  |  | 0
276 | 45/1 | DA+9 |  | 1 | 0276 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 406.54 | [15 empty] | 1 |  |  |  | 0
277 | 46/0 | DD60+25 |  | 1 | 0277 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 9.255 | [5 empty] | DD | 25 | DD+25
|  |  | 199.08 | [15 empty] | 1 |  |  |  | 0
278 | 47/0 | DD60+25 |  | 1 | 0278 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 9.255 | [5 empty] | DD | 25 | DD+25
|  |  | 441.2 | [15 empty] | 1 |  |  |  | 0
279 | 47/1 | DA+3 |  | 1 | 0279 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 365.93 | [15 empty] | 1 |  |  |  | 0
280 | 47/2 | DA+9 |  | 1 | 0280 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 417.4 | [15 empty] | 1 |  |  |  | 0
281 | 47/3 | DA+9 |  | 1 | 0281 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 358.4 | [15 empty] | 1 |  |  |  | 0
282 | 47/4 | DA+3 |  | 1 | 0282 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 461.2 | [15 empty] | 1 |  |  |  | 0
283 | 47/5 | DA+0 |  | 1 | 0283 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 377.3 | [15 empty] | 1 |  |  |  | 0
284 | 47/6 | DA+3 |  | 1 | 0284 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 431.5 | [15 empty] | 1 |  |  |  | 0
285 | 47/7 | DA+3 |  | 1 | 0285 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 398.8 | [15 empty] | 1 |  |  |  | 0
286 | 47/8 | DA+0 |  | 1 | 0286 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 405.9 | [15 empty] | 1 |  |  |  | 0
287 | 47/9 | DA+3 |  | 1 | 0287 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 433.7 | [15 empty] | 1 |  |  |  | 0
288 | 47/10 | DA+6 |  | 1 | 0288 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 386.2 | [15 empty] | 1 |  |  |  | 0
289 | 48/0 | DC2+0 |  | 1 | 0289 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 428.9 | [15 empty] | 1 |  |  |  | 0
290 | 48/1 | DA+9 |  | 1 | 0290 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 402.9 | [15 empty] | 1 |  |  |  | 0
291 | 49/0 | DD45+0 |  | 1 | 0291 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | [13 empty] | DD | 0 | DD+0
|  |  | 379.1 | [15 empty] | 1 |  |  |  | 0
292 | 49/1 | DA+0 |  | 1 | 0292 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 386.6 | [15 empty] | 1 |  |  |  | 0
293 | 49/2 | DA+3 |  | 1 | 0293 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 390 | [15 empty] | 1 |  |  |  | 0
294 | 49/3 | DA+3 |  | 1 | 0294 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 421.7 | [15 empty] | 1 |  |  |  | 0
295 | 49/4 | DA+3 |  | 1 | 0295 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 396.6 | [15 empty] | 1 |  |  |  | 0
296 | 49/5 | DA+3 |  | 1 | 0296 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 3 | DA+3
|  |  | 412.8 | [15 empty] | 1 |  |  |  | 0
297 | 49/6 | DA+0 |  | 1 | 0297 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 340.2 | [15 empty] | 1 |  |  |  | 0
298 | 49/7 | DA+0 |  | 1 | 0298 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 500.2 | [15 empty] | 1 |  |  |  | 0
299 | 50/0 | DB2+0 |  | 1 | 0299 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
|  |  | 469.1 | [15 empty] | 1 |  |  |  | 0
300 | 50/1 | DA+6 |  | 1 | 0300 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 367.1 | [15 empty] | 1 |  |  |  | 0
301 | 50/2 | DA+9 |  | 1 | 0301 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 470.4 | [15 empty] | 1 |  |  |  | 0
302 | 50/3 | DA+6 |  | 1 | 0302 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 6 | DA+6
|  |  | 354.8 | [15 empty] | 1 |  |  |  | 0
303 | 50/4 | DA+9 |  | 1 | 0303 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 442.1 | [15 empty] | 1 |  |  |  | 0
304 | 50/5 | DA+9 |  | 1 | 0304 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 364.4 | [15 empty] | 1 |  |  |  | 0
305 | 50/6 | DA+9 |  | 1 | 0305 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 470.8 | [15 empty] | 1 |  |  |  | 0
306 | 50/7 | DA+0 |  | 1 | 0306 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 345 | [15 empty] | 1 |  |  |  | 0
307 | 50/8 | DA+9 |  | 1 | 0307 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 9 | DA+9
|  |  | 364.4 | [15 empty] | 1 |  |  |  | 0
308 | 50/9 | DA+0 |  | 1 | 0308 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 394.6 | [15 empty] | 1 |  |  |  | 0
309 | 50/10 | DA+0 |  | 1 | 0309 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 401.4 | [15 empty] | 1 |  |  |  | 0
310 | 51/0 | DC2+0 |  | 1 | 0310 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 356.6 | [15 empty] | 1 |  |  |  | 0
311 | 51/1 | DA+0 |  | 1 | 0311 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 307.1 | [15 empty] | 1 |  |  |  | 0
312 | 51/2 | DA+0 |  | 1 | 0312 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 385 | [15 empty] | 1 |  |  |  | 0
313 | 52/0 | DC2+0 |  | 1 | 0313 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | [13 empty] | DC | 0 | DC+0
|  |  | 402 | [15 empty] | 1 |  |  |  | 0
314 | 52/1 | DA+6 |  | 1 | 0314 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 402.6 | [15 empty] | 1 |  |  |  | 0
315 | 52/2 | DA+6 |  | 1 | 0315 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 437 | [15 empty] | 1 |  |  |  | 0
316 | 52/3 | DA+9 |  | 1 | 0316 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 9 | DA+9
|  |  | 393.8 | [15 empty] | 1 |  |  |  | 0
317 | 52/4 | DA+9 |  | 1 | 0317 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 9 | DA+9
|  |  | 447 | [15 empty] | 1 |  |  |  | 0
318 | 52/5 | DA+9 |  | 1 | 0318 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 9 | DA+9
|  |  | 373 | [15 empty] | 1 |  |  |  | 0
319 | 52/6 | DA+6 |  | 1 | 0319 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 406.8 | [15 empty] | 1 |  |  |  | 0
320 | 52/7 | DA+3 |  | 1 | 0320 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 433 | [15 empty] | 1 |  |  |  | 0
321 | 52/8 | DA+6 |  | 1 | 0321 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 399.7 | [15 empty] | 1 |  |  |  | 0
322 | 52/9 | DA+3 |  | 1 | 0322 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 384.1 | [15 empty] | 1 |  |  |  | 0
323 | 52/10 | DA+9 |  | 1 | 0323 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 9 | DA+9
|  |  | 455.9 | [15 empty] | 1 |  |  |  | 0
324 | 53/0 | DB2+9 |  | 1 | 0324 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 7.366 | [5 empty] | DB | 9 | DB+9
|  |  | 433.2 | [15 empty] | 1 |  |  |  | 0
325 | 53/1 | DA+9 |  | 1 | 0325 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 9 | DA+9
|  |  | 407.4 | [15 empty] | 1 |  |  |  | 0
326 | 53/2 | DA+0 |  | 1 | 0326 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 394.5 | [15 empty] | 1 |  |  |  | 0
327 | 53/3 | DA+6 |  | 1 | 0327 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 410.1 | [15 empty] | 1 |  |  |  | 0
328 | 53/4 | DA+0 |  | 1 | 0328 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [12 empty] | DA | 0 | DA+0
|  |  | 428.1 | [15 empty] | 1 |  |  |  | 0
329 | 53/5 | DA+3 |  | 1 | 0329 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 406.6 | [15 empty] | 1 |  |  |  | 0
330 | 53/6 | DA+6 |  | 1 | 0330 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 411.3 | [15 empty] | 1 |  |  |  | 0
331 | 53/7 | DA+3 |  | 1 | 0331 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 427.8 | [15 empty] | 1 |  |  |  | 0
332 | 53/8 | DA+3 |  | 1 | 0332 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 371.3 | [15 empty] | 1 |  |  |  | 0
333 | 54/0 | DB1+6 |  | 1 | 0333 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 7.366 | [5 empty] | DB | 6 | DB+6
|  |  | 365.1 | [15 empty] | 1 |  |  |  | 0
334 | 54/1 | DA+3 |  | 1 | 0334 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 381 | [15 empty] | 1 |  |  |  | 0
335 | 54/2 | DA+3 |  | 1 | 0335 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 417 | [15 empty] | 1 |  |  |  | 0
336 | 54/3 | DA+6 |  | 1 | 0336 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 423.3 | [15 empty] | 1 |  |  |  | 0
337 | 54/4 | DA+9 |  | 1 | 0337 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 9 | DA+9
|  |  | 401 | [15 empty] | 1 |  |  |  | 0
338 | 54/5 | DA+9 |  | 1 | 0338 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 9 | DA+9
|  |  | 424 | [15 empty] | 1 |  |  |  | 0
339 | 55/0 | DB1+6 |  | 1 | 0339 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 7.366 | [5 empty] | DB | 6 | DB+6
|  |  | 404.9 | [15 empty] | 1 |  |  |  | 0
340 | 55/1 | DA+0 |  | 1 | 0340 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [5 empty] | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 343.1 | [15 empty] | 1 |  |  |  | 0
341 | 55/2 | DA+0 |  | 1 | 0341 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [5 empty] | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 357.7 | [15 empty] | 1 |  |  |  | 0
342 | 55/3 | DA+0 |  | 1 | 0342 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [5 empty] | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 365.2 | [15 empty] | 1 |  |  |  | 0
343 | 55/4 | DA+0 |  | 1 | 0343 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [5 empty] | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 350.1 | [15 empty] | 1 |  |  |  | 0
344 | 55/5 | DA+0 |  | 1 | 0344 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [5 empty] | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 357.7 | [15 empty] | 1 |  |  |  | 0
345 | 55/6 | DA+0 |  | 1 | 0345 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [5 empty] | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 337.8 | [15 empty] | 1 |  |  |  | 0
346 | 55/7 | DA+0 |  | 1 | 0346 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [5 empty] | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 341.22 | [15 empty] | 1 |  |  |  | 0
347 | 55/8 | DA+6 |  | 1 | 0347 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 460.49 | [15 empty] | 1 |  |  |  | 0
348 | 56/0 | DD60+25 |  | 1 | 0348 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 9.255 | [5 empty] | DD | 25 | DD+25
|  |  | 219.76 | [15 empty] | 1 |  |  |  | 0
349 | 57/0 | DD60+25 |  | 1 | 0349 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 9.255 | [5 empty] | DD | 25 | DD+25
|  |  | 461.1 | [15 empty] | 1 |  |  |  | 0
350 | 57/1 | DA+0 |  | 1 | 0350 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 355.5 | [15 empty] | 1 |  |  |  | 0
351 | 57/2 | DA+3 |  | 1 | 0351 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 405.4 | [15 empty] | 1 |  |  |  | 0
352 | 57/3 | DA+0 |  | 1 | 0352 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [5 empty] | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 418.2 | [15 empty] | 1 |  |  |  | 0
353 | 57/4 | DA+0 |  | 1 | 0353 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 | [5 empty] | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 416.8 | [15 empty] | 1 |  |  |  | 0
354 | 57/5 | DA+3 |  | 1 | 0354 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 395 | [15 empty] | 1 |  |  |  | 0
355 | 57/6 | DA+3 |  | 1 | 0355 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 401.8 | [15 empty] | 1 |  |  |  | 0
356 | 57/7 | DA+3 |  | 1 | 0356 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 433.9 | [15 empty] | 1 |  |  |  | 0
357 | 58/0 | DC1+3 |  | 1 | 0357 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 8.319 | [5 empty] | DC | 3 | DC+3
|  |  | 238.9 | [15 empty] | 1 |  |  |  | 0
358 | 59/0 | DC2+0 |  | 1 | 0358 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 8.319 | [5 empty] | DC | 0 | DC+0
|  |  | 411.3 | [15 empty] | 1 |  |  |  | 0
359 | 59/1 | DA+3 |  | 1 | 0359 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 418.2 | [15 empty] | 1 |  |  |  | 0
360 | 59/2 | DA+3 |  | 1 | 0360 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 412.3 | [15 empty] | 1 |  |  |  | 0
361 | 59/3 | DA+3 |  | 1 | 0361 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 421 | [15 empty] | 1 |  |  |  | 0
362 | 59/4 | DA+3 |  | 1 | 0362 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 419.7 | [15 empty] | 1 |  |  |  | 0
363 | 59/5 | DA+3 |  | 1 | 0363 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 419.1 | [15 empty] | 1 |  |  |  | 0
364 | 59/6 | DA+3 |  | 1 | 0364 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 408.8 | [15 empty] | 1 |  |  |  | 0
365 | 59/7 | DA+3 |  | 1 | 0365 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 426.9 | [15 empty] | 1 |  |  |  | 0
366 | 59/8 | DB1+3 |  | 1 | 0366 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 7.366 | [5 empty] | DB | 3 | DB+3
|  |  | 434.7 | [15 empty] | 1 |  |  |  | 0
367 | 59/9 | DA+3 |  | 1 | 0367 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 400.8 | [15 empty] | 1 |  |  |  | 0
368 | 59/10 | DA+0 |  | 1 | 0368 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 436.3 | [15 empty] | 1 |  |  |  | 0
369 | 59/11 | DA+6 |  | 1 | 0369 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 393.1 | [15 empty] | 1 |  |  |  | 0
370 | 59/12 | DA+6 |  | 1 | 0370 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 447.4 | [15 empty] | 1 |  |  |  | 0
371 | 59/13 | DA+3 |  | 1 | 0371 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 391.1 | [15 empty] | 1 |  |  |  | 0
372 | 59/14 | DA+6 |  | 1 | 0372 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 448.6 | [15 empty] | 1 |  |  |  | 0
373 | 59/15 | DA+6 |  | 1 | 0373 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 388 | [15 empty] | 1 |  |  |  | 0
374 | 59/16 | DA+9 |  | 1 | 0374 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 9 | DA+9
|  |  | 438 | [15 empty] | 1 |  |  |  | 0
375 | 60/0 | DC1+0 |  | 1 | 0375 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 8.319 | [5 empty] | DC | 0 | DC+0
|  |  | 413.8 | [15 empty] | 1 |  |  |  | 0
376 | 60/1 | DA+6 |  | 1 | 0376 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 424.2 | [15 empty] | 1 |  |  |  | 0
377 | 60/2 | DA+3 |  | 1 | 0377 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 414.5 | [15 empty] | 1 |  |  |  | 0
378 | 60/3 | DA+3 |  | 1 | 0378 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 425.6 | [15 empty] | 1 |  |  |  | 0
379 | 60/4 | DA+3 |  | 1 | 0379 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 412.3 | [15 empty] | 1 |  |  |  | 0
380 | 60/5 | DA+3 |  | 1 | 0380 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 374.1 | [15 empty] | 1 |  |  |  | 0
381 | 60/6 | DA+0 |  | 1 | 0381 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 410.1 | [15 empty] | 1 |  |  |  | 0
382 | 60/7 | DA+3 |  | 1 | 0382 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 400.4 | [15 empty] | 1 |  |  |  | 0
383 | 60/8 | DA+0 |  | 1 | 0383 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 409.2 | [15 empty] | 1 |  |  |  | 0
384 | 60/9 | DA+3 |  | 1 | 0384 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 401 | [15 empty] | 1 |  |  |  | 0
385 | 60/10 | DA+0 |  | 1 | 0385 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 394.5 | [15 empty] | 1 |  |  |  | 0
386 | 60/11 | DA+3 |  | 1 | 0386 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 397.9 | [15 empty] | 1 |  |  |  | 0
387 | 61/0 | DB2+0 |  | 1 | 0387 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 7.366 | [5 empty] | DB | 0 | DB+0
|  |  | 405.7 | [15 empty] | 1 |  |  |  | 0
388 | 61/1 | DA+6 |  | 1 | 0388 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 433.2 | [15 empty] | 1 |  |  |  | 0
389 | 61/2 | DA+6 |  | 1 | 0389 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 400.9 | [15 empty] | 1 |  |  |  | 0
390 | 61/3 | DA+6 |  | 1 | 0390 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 427 | [15 empty] | 1 |  |  |  | 0
391 | 61/4 | DA+3 |  | 1 | 0391 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 413.9 | [15 empty] | 1 |  |  |  | 0
392 | 61/5 | DA+3 |  | 1 | 0392 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 426.4 | [15 empty] | 1 |  |  |  | 0
393 | 61/6 | DA+3 |  | 1 | 0393 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 411.5 | [15 empty] | 1 |  |  |  | 0
394 | 61/7 | DA+9 |  | 1 | 0394 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 9 | DA+9
|  |  | 376.3 | [15 empty] | 1 |  |  |  | 0
395 | 61/8 | DA+6 |  | 1 | 0395 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 433.4 | [15 empty] | 1 |  |  |  | 0
396 | 61/9 | DA+0 |  | 1 | 0396 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 405.6 | [15 empty] | 1 |  |  |  | 0
397 | 61/10 | DA+9 |  | 1 | 0397 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 9 | DA+9
|  |  | 434.3 | [15 empty] | 1 |  |  |  | 0
398 | 62/0 | DB2+0 |  | 1 | 0398 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 7.366 | [5 empty] | DB | 0 | DB+0
|  |  | 418 | [15 empty] | 1 |  |  |  | 0
399 | 62/1 | DA+3 |  | 1 | 0399 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 386 | [15 empty] | 1 |  |  |  | 0
400 | 62/2 | DA+3 |  | 1 | 0400 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 400 | [15 empty] | 1 |  |  |  | 0
401 | 62/3 | DA+0 |  | 1 | 0401 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 401 | [15 empty] | 1 |  |  |  | 0
402 | 62/4 | DA+3 |  | 1 | 0402 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 403 | [15 empty] | 1 |  |  |  | 0
403 | 62/5 | DA+0 |  | 1 | 0403 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 404 | [15 empty] | 1 |  |  |  | 0
404 | 62/6 | DA+3 |  | 1 | 0404 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 423 | [15 empty] | 1 |  |  |  | 0
405 | 62/7 | DA+3 |  | 1 | 0405 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 409 | [15 empty] | 1 |  |  |  | 0
406 | 62/8 | DA+0 |  | 1 | 0406 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 409 | [15 empty] | 1 |  |  |  | 0
407 | 62/9 | DA+3 |  | 1 | 0407 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 411 | [15 empty] | 1 |  |  |  | 0
408 | 62/10 | DA+0 |  | 1 | 0408 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 413 | [15 empty] | 1 |  |  |  | 0
409 | 62/11 | DA+3 |  | 1 | 0409 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 386.1 | [15 empty] | 1 |  |  |  | 0
410 | 63/0 | DC1+0 |  | 1 | 0410 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 8.319 | [5 empty] | DC | 0 | DC+0
|  |  | 400 | [15 empty] | 1 |  |  |  | 0
411 | 63/1 | DA+3 |  | 1 | 0411 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 416 | [15 empty] | 1 |  |  |  | 0
412 | 63/2 | DA+0 |  | 1 | 0412 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 411 | [15 empty] | 1 |  |  |  | 0
413 | 63/3 | DA+3 |  | 1 | 0413 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 399 | [15 empty] | 1 |  |  |  | 0
414 | 63/4 | DA+0 |  | 1 | 0414 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 413 | [15 empty] | 1 |  |  |  | 0
415 | 63/5 | DA+3 |  | 1 | 0415 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 426 | [15 empty] | 1 |  |  |  | 0
416 | 63/6 | DA+3 |  | 1 | 0416 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 413 | [15 empty] | 1 |  |  |  | 0
417 | 63/7 | DA+3 |  | 1 | 0417 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 425 | [15 empty] | 1 |  |  |  | 0
418 | 63/8 | DA+3 |  | 1 | 0418 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 408.3 | [15 empty] | 1 |  |  |  | 0
419 | 64/0 | DB2+0 |  | 1 | 0419 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 7.366 | [5 empty] | DB | 0 | DB+0
|  |  | 375.1 | [15 empty] | 1 |  |  |  | 0
420 | 64/1 | DA+0 |  | 1 | 0420 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 408.7 | [15 empty] | 1 |  |  |  | 0
421 | 64/2 | DA+3 |  | 1 | 0421 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 410.7 | [15 empty] | 1 |  |  |  | 0
422 | 64/3 | DA+0 |  | 1 | 0422 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 408.2 | [15 empty] | 1 |  |  |  | 0
423 | 64/4 | DA+3 |  | 1 | 0423 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 426.2 | [15 empty] | 1 |  |  |  | 0
424 | 64/5 | DA+3 |  | 1 | 0424 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 407.7 | [15 empty] | 1 |  |  |  | 0
425 | 64/6 | DA+0 |  | 1 | 0425 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 401.6 | [15 empty] | 1 |  |  |  | 0
426 | 64/7 | DA+3 |  | 1 | 0426 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 425.5 | [15 empty] | 1 |  |  |  | 0
427 | 64/8 | DA+3 |  | 1 | 0427 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 414.4 | [15 empty] | 1 |  |  |  | 0
428 | 64/9 | DA+3 |  | 1 | 0428 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 410.6 | [15 empty] | 1 |  |  |  | 0
429 | 64/10 | DA+3 |  | 1 | 0429 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 428.4 | [15 empty] | 1 |  |  |  | 0
430 | 64/11 | DA+3 |  | 1 | 0430 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 400.6 | [15 empty] | 1 |  |  |  | 0
431 | 65/0 | DB1+0 |  | 1 | 0431 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 7.366 | [5 empty] | DB | 0 | DB+0
|  |  | 395.4 | [15 empty] | 1
432 | 65/1 | DA+0 |  | 1 | 0432 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 393.7 | [15 empty] | 1
433 | 65/2 | DA+0 |  | 1 | 0433 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 403.7 | [15 empty] | 1
434 | 65/3 | DA+3 |  | 1 | 0434 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 402.9 | [15 empty] | 1
435 | 65/4 | DA+0 |  | 1 | 0435 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 376.4 | [15 empty] | 1
436 | 65/5 | DA+0 |  | 1 | 0436 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 389.2 | [15 empty] | 1
437 | 65/6 | DA+0 |  | 1 | 0437 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 397.6 | [15 empty] | 1
438 | 65/7 | DA+0 |  | 1 | 0438 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 394.3 | [15 empty] | 1
439 | 65/8 | DA+0 |  | 1 | 0439 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 389 | [15 empty] | 1
440 | 65/9 | DA+0 |  | 1 | 0440 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 379.1 | [15 empty] | 1
441 | 65/10 | DA+0 |  | 1 | 0441 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 387.6 | [15 empty] | 1
442 | 65/11 | DA+0 |  | 1 | 0442 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 426.9 | [15 empty] | 1
443 | 66/0 | DC2+6 |  | 1 | 0443 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 8.319 | [5 empty] | DC | 6 | DC+6
|  |  | 207.8 | [15 empty] | 1
444 | 67/0 | DC1+9 |  | 1 | 0444 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 8.319 | [5 empty] | DC | 9 | DC+9
|  |  | 347.1 | [15 empty] | 1
445 | 67/1 | DA+0 |  | 1 | 0445 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 344.9 | [15 empty] | 1
446 | 67/2 | DA+0 |  | 1 | 0446 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 369.2 | [15 empty] | 1
447 | 68/0 | DD45+0 |  | 1 | 0447 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 9.255 | [5 empty] | DD | 0 | DD+0
|  |  | 200.9 | [15 empty] | 1
448 | 69/0 | DB2+0 |  | 1 | 0448 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 7.366 | [5 empty] | DB | 0 | DB+0
|  |  | 374.1 | [15 empty] | 1
449 | 69/1 | DA+3 |  | 1 | 0449 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 394.9 | [15 empty] | 1
450 | 70/0 | DC1+0 |  | 1 | 0450 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 8.319 | [5 empty] | DC | 0 | DC+0
|  |  | 388.4 | [15 empty] | 1
451 | 70/1 | DA+3 |  | 1 | 0451 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 418.9 | [15 empty] | 1
452 | 70/2 | DA+3 |  | 1 | 0452 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 418.6 | [15 empty] | 1
453 | 70/3 | DA+3 |  | 1 | 0453 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 414 | [15 empty] | 1
454 | 70/4 | DA+3 |  | 1 | 0454 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 419.6 | [15 empty] | 1
455 | 70/5 | DA+3 |  | 1 | 0455 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 420.3 | [15 empty] | 1
456 | 70/6 | DA+3 |  | 1 | 0456 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 419.6 | [15 empty] | 1
457 | 70/7 | DA+3 |  | 1 | 0457 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 418.2 | [15 empty] | 1
458 | 70/8 | DA+3 |  | 1 | 0458 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 414.1 | [15 empty] | 1
459 | 70/9 | DA+3 |  | 1 | 0459 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 406.1 | [15 empty] | 1
460 | 70/10 | DA+3 |  | 1 | 0460 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 408.6 | [15 empty] | 1
461 | 70/11 | DA+3 |  | 1 | 0461 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 420.4 | [15 empty] | 1
462 | 71/0 | DB2+3 |  | 1 | 0462 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 7.366 | [5 empty] | DB | 3 | DB+3
|  |  | 398.6 | [15 empty] | 1
463 | 71/1 | DA+3 |  | 1 | 0463 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 414.3 | [15 empty] | 1
464 | 71/2 | DA+3 |  | 1 | 0464 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 413 | [15 empty] | 1
465 | 71/3 | DA+6 |  | 1 | 0465 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 6 | DA+6
|  |  | 367.7 | [15 empty] | 1
466 | 71/4 | DA+3 |  | 1 | 0466 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 429.4 | [15 empty] | 1
467 | 71/5 | DA+3 |  | 1 | 0467 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 408 | [15 empty] | 1
468 | 71/6 | DA+0 |  | 1 | 0468 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 404.9 | [15 empty] | 1
469 | 71/7 | DA+3 |  | 1 | 0469 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 431.6 | [15 empty] | 1
470 | 71/8 | DA+3 |  | 1 | 0470 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 408.4 | [15 empty] | 1
471 | 72/0 | DB2+3 |  | 1 | 0471 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 7.366 | [5 empty] | DB | 3 | DB+3
|  |  | 435.3 | [15 empty] | 1
472 | 72/1 | DA+3 |  | 1 | 0472 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 403.9 | [15 empty] | 1
473 | 72/2 | DA+0 |  | 1 | 0473 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 389.2 | [15 empty] | 1
474 | 72/3 | DA+3 |  | 1 | 0474 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 400.1 | [15 empty] | 1
475 | 73/0 | DB2+0 |  | 1 | 0475 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 7.366 | [5 empty] | DB | 0 | DB+0
|  |  | 383.3 | [15 empty] | 1
476 | 73/1 | DA+0 |  | 1 | 0476 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 379 | [15 empty] | 1
477 | 73/2 | DA+0 |  | 1 | 0477 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 381.2 | [15 empty] | 1
478 | 73/3 | DA+0 |  | 1 | 0478 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 384.7 | [15 empty] | 1
479 | 73/4 | DA+0 |  | 1 | 0479 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 368.8 | [15 empty] | 1
480 | 73/5 | DA+0 |  | 1 | 0480 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 365.5 | [15 empty] | 1
481 | 73/6 | DA+0 |  | 1 | 0481 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 392.4 | [15 empty] | 1
482 | 73/7 | DA+0 |  | 1 | 0482 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 374.9 | [15 empty] | 1
483 | 73/8 | DA+3 |  | 1 | 0483 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 3 | DA+3
|  |  | 379.5 | [15 empty] | 1
484 | 73/9 | DA+0 |  | 1 | 0484 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 1 | 4.903 | [5 empty] | DA | 0 | DA+0
|  |  | 378.9 | [15 empty] | 1
485 | 74/0 | DB2+0 |  | 1 | 0485 | Y | R | B | Y | R | B | 1 | I | II | 1 | 1 | 1 | [13 empty] | DB | 0 | DB+0
Total Required |  |  |  | 485 | 485 | [6 empty] | 485 |  |  |  | 485 | 485 | 397 | 246 | 164 | 7157 | 0 | 7157 | 173 | 932.151

## Visual chart
Progress Summary'!A1
| Project Name :- Beawar 765 KV D/C Line, (TB-408 PKG-F) | [15 empty] | Progress Legends
| Progress Status as on dated | [5 empty] | 2026-02-24
| Sr. No. |  | Description |  |  |  | UOM |  | Total qty |  | Completed |  |  | Balance |  | WIP |  |  |  |  | Stringing WIP | [22 empty] | Identification for auto fill linked with Summary of visual chart
| 1 |  | Foundation |  |  |  | Nos |  | 485 |  | 484 |  |  | 1 |  | 0 |  |  |  |  | Erection U/P
| 2 |  | Earthing |  |  |  | Nos |  | 485 |  | 484 |  |  | 1 |  | 0 |  |  |  |  | Tackwelding U/P | [30 empty] | E
| 3 |  | Tower Erection |  |  |  | Nos |  | 485 |  | 463 |  |  | 22 |  | 3 |  |  |  |  | Foundation U/P
| 4 |  | Tack-Welding |  |  |  | Nos |  | 485 |  | 376 |  |  | 109 |  | 0 |  |  |  |  | Earthing U/P
| 5 |  | Rough Sag |  |  |  | KM |  | 191.36 |  | 116.7077 |  |  | 74.6523 |  | 3.3182 | [27 empty] | Sandy | Dry | DFR
| 6 |  | Final Sag |  |  |  | KM |  | 191.36 |  | 116.7077 |  |  | 74.6523 |  | 0 | [34 empty] | C
| Legends & Quantity | [19 empty] | Final Sag Completed
[14 empty] | NH | [6 empty] | Paying out Completed
|  |  | B Type Towers | [6 empty] | Forest |  |  |  | 3 No's/1 No's | [6 empty] | Erection Completed
|  |  | C & D type towers | [17 empty] | Welding Completed
|  | 132/220 KV Line |  |  |  | 400 KV |  |  | Gas Pipe Line | [9 empty] | DFR |  | FDN Completed | [22 empty] | FOUNDATION | [6 empty] | EARTHING | ERECTION | Welding | P/O | FS | Total Section Length | P/0 WIP | Paying out Completed | Final Sag Completed
|  | 3 No's/2 No's |  |  |  | 4 No's |  |  | 1 No's | [9 empty] | C |  | Earthing Completed | [22 empty] | SANDY | DRY | DFR | WFR | FS | Total FDN | FDN WIP | C | E | Done | PO | FS |  | . | .. | ,
[19 empty] | LE |  | Leg Extension A,B,C,D | [22 empty] | 200 | 222 | 60 | 2 | 0 | 484 | 0 | 484 | 463 | 376 | 0 | 0 | 191392.643 | 3318.21 | 0 | 82941.73
| 0 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21
| Gty |  | 1/0 |  | 1A/0 |  | 1A/1 |  | 1A/2 |  | 1A/3 |  | 1A/4 |  | 1A/5 |  | 1A/6 |  | 1A/7 |  | 1A/8 |  | 2/0 |  | 2/1 |  | 2/2 |  | 2/3 |  | 2/4 |  | 2/5 |  | 2/6 |  | 2/7 |  | 2/8 |  | 2/9 |  | 3/0
[6 empty] | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 7249.9
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
|  | 122 | DRY | 90 | DRY | 277.7 | DFR | 386 | DRY | 443.6 | DRY | 333.4 | DFR | 431.9 | DRY | 348.7 | Sandy | 395.7 | Sandy | 415 | Sandy | 394.3 | DRY | 405.3 | Sandy | 338.5 | Sandy | 406 | Sandy | 429 | Sandy | 411.6 | Sandy | 425.7 | Sandy | 408.2 | Sandy | 354.6 | Sandy | 308.7 | DRY | 336 | DRY | 11 | 8 | 2 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 7461.9
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
|  |  | DD60+0 |  | DD60+0 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DC1+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DD60+6
|  |  | ,,, |  | ,,, |  | ,,, |  | ,1,1, |  | ,,, |  | ,,1, |  | 1,1,, |  | 1,,,1 |  | ,1,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,1 |  | 1,,1,1 |  | ,,, |  | ,,1,1 |  | ,,,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42
|  |  | 4/0 |  | 4/1 |  | 4/2 |  | 4/3 |  | 4/4 |  | 5/0 |  | 6/0 |  | 6/1 |  | 6/2 |  | 7/0 |  | 8/0 |  | 8/1 |  | 8/2 |  | 8/3 |  | 8/4 |  | 8/5 |  | 8/6 |  | 8/7 |  | 8/8 |  | 8/9 |  | 8/10
|  | , | [19 empty] | ,, | [34 empty] | 0 | 0 | 226.5
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E | [5 empty] | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done | [7 empty] | Done |  | Done
| FDN | 226.5 | DRY | 343 | DRY | 358.4 | DRY | 381 | DRY | 367.6 | DRY | 423.1 | DRY | 246 | DRY | 429.9 | DFR | 362.4 | DFR | 347.9 | DRY | 210.8 | DRY | 409.2 | DRY | 413.6 | DRY | 393.2 | DRY | 416.5 | DRY | 394.6 | DRY | 393.2 | DRY | 441.1 | DRY | 414.4 | DRY | 395.863 | DFR | 413.404 | DFR | 0 | 17 | 4 | 0 | 0 | 21 | 0 | 21 | 19 | 18 |  |  | 7781.667
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DD60+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+9 |  | DB2+9 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DB1+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+6 |  | DA+3 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 5,5,5,5 |  | 5,5,5,5 |  | ,,, |  | ,,, |  | 2,3,3,2 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60 |  | 61 |  | 62 |  | 63
|  |  | 8/11 |  | 8/12 |  | 9/0 |  | 10/0 |  | 10/1 |  | 10/2 |  | 10/3 |  | 10/4 |  | 10/5 |  | 10/6 |  | 10/7 |  | 10/8 |  | 10/9 |  | 10/10 |  | 10/11 |  | 10/12 |  | 10/13 |  | 10/14 |  | 10/15 |  | 10/16 |  | 10/17
[34 empty] | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 2033
| ERE |  | E |  | E |  | E |  |  |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD | [9 empty] | Done |  |  |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 402.6 | DRY | 372.1 | DRY | 457.7 | DRY | 233.1 | DFR | 443.7 | DRY | 383.2 | DFR | 398.6 | DFR | 410.7 | DFR | 416.2 | DRY | 403.4 | DFR | 373.845 | DRY | 411.823 | DFR | 414.2 | DRY | 402.3 | Sandy | 430.3 | DRY | 406.2 | DRY | 405.3 | DRY | 427.1 | DRY | 400 | DRY | 412.8 | DRY | 387.8 | DFR | 1 | 13 | 7 | 0 | 0 | 21 | 0 | 21 | 20 | 16 |  |  | 8392.968
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+0 |  | DA+0 |  | DD60+18 |  | DD60+25 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80 |  | 81 |  | 82 |  | 83 |  | 84
|  |  | 10/18 |  | 10/19 |  | 10/20 |  | 10/21 |  | 10/22 |  | 10/23 |  | 11/0 |  | 11/1 |  | 11/2 |  | 11/3 |  | 11/4 |  | 11/5 |  | 11A/0 |  | 11A/1 |  | 11A/2 |  | 11A/3 |  | 11A/4 |  | 11A/5 |  | 11A/6 |  | 11A/7 |  | 11A/8
|  | , |  | , |  | , |  | , |  | , |  | , |  | , | [42 empty] | 0 | 0 | 2913.6
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  |  |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done | [5 empty] | Done |  | Done | [15 empty] | Done
| FDN | 436.7 | DFR | 403.7 | DRY | 409.5 | DFR | 418.6 | DFR | 410.3 | Sandy | 384 | Sandy | 450.8 | Sandy | 384.2 | Sandy | 338.6 | Sandy | 370.7 | Sandy | 434.1 | Sandy | 368.1 | DFR | 342.3 | DRY | 405.1 | DRY | 412.2 | DRY | 412.2 | DRY | 422.1 | DRY | 418.3 | DRY | 384.3 | DRY | 434.2 | Sandy | 390.1 | Sandy | 9 | 8 | 4 | 0 | 0 | 21 | 0 | 21 | 20 | 12 |  |  | 8430.1
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+9 |  | DA+6
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 1,3,, |  | ,2,, |  | 1,4,,3 |  | ,,, |  | 2,1,, |  | ,,,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,2,4,1
REM
|  |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100 |  | 101 |  | 102 |  | 103 |  | 104 |  | 105
|  |  | 11A/9 |  | 12/0 |  | 13/0 |  | 13/1 |  | 13/2 |  | 13/3 |  | 13/4 |  | 14/0 |  | 14A/0 |  | 14A/1 |  | 14A/2 |  | 15/0 |  | 15/1 |  | 16/0 |  | 16/1 |  | 16/2 |  | 16/3 |  | 16/4 |  | 16/5 |  | 17/0 |  | 17/1
[57 empty] | 0 | 0 | 0
| ERE |  | E |  | E |  |  |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  |  |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done | [21 empty] | Done |  |  |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 426.3 | DRY | 405.9 | DRY | 211.9 | DRY | 464.3 | DRY | 373.7 | DRY | 419.7 | Sandy | 420.3 | DRY | 400 | Sandy | 381.4 | DRY | 412.765 | DRY | 396.029 | DRY | 383.3 | DRY | 404.6 | DRY | 413.3 | DRY | 354.283 | DRY | 424.28 | DRY | 340.3 | DRY | 394.7 | DRY | 435.863 | DRY | 386.8 | DRY | 393.7 | DRY | 2 | 19 | 0 | 0 | 0 | 21 | 0 | 21 | 19 | 10 |  |  | 8243.42
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DD60+0 |  | DD60+3 |  | DA+9 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC2+0 |  | DC1+0 |  | DA+3 |  | DA+0 |  | DC1+0 |  | DA+3 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB2+3 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,2,4 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 1,,,1 |  | ,,, |  | ,1,, |  | ,,, |  | ,,,1 |  | ,,,
REM
|  |  | 106 |  | 107 |  | 108 |  | 109 |  | 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120 |  | 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126
|  |  | 17/2 |  | 17/3 |  | 17/4 |  | 17/5 |  | 18/0 |  | 18/1 |  | 18/2 |  | 18/3 |  | 18/4 |  | 19/0 |  | 19/1 |  | 19/2 |  | 19/3 |  | 19/4 |  | 19/5 |  | 20/0 |  | 20/1 |  | 20/2 |  | 20/3 |  | 21/0 |  | 21/1
[57 empty] | 0 | 0 | 0
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  |  |  | E |  | E |  | E
| WELD | [5 empty] | Done |  |  |  | Done |  | Done | [23 empty] | Done |  | Done
| FDN | 415.9 | DRY | 422.8 | DRY | 409.9 | DRY | 425.3 | DRY | 383.4 | DRY | 372.8 | DRY | 379.8 | DRY | 371 | DRY | 398.7 | DRY | 380.8 | DRY | 366.9 | DRY | 372.5 | DRY | 376.5 | DRY | 384.3 | DRY | 375.4 | DRY | 381.2 | Sandy | 386.8 | Sandy | 387 | DRY | 348.5 | DRY | 355 | DRY | 414.9 | ROW | 2 | 18 | 0 | 0 | 0 | 20 | 0 | 20 | 19 | 5 |  |  | 8109.4
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DC2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+6
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 127 |  | 128 |  | 129 |  | 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147
|  |  | 21/2 |  | 21/3 |  | 21/4 |  | 21/5 |  | 21/6 |  | 21/7 |  | 21/8 |  | 21/9 |  | 21/10 |  | 22/0 |  | 22/1 |  | 22/2 |  | 22/3 |  | 22/4 |  | 22/5 |  | 22/6 |  | 22/7 |  | 22/8 |  | 22/9 |  | 22/10 |  | 22/11
[57 empty] | 0 | 0 | 0
| ERE |  |  |  | E |  | E |  | E | [15 empty] | E |  | E |  |  |  | E |  | E |  | E | [7 empty] | E
| WELD | [5 empty] | Done |  | Done
| FDN | 407.2 | Sandy | 432.2 | Sandy | 401.9 | Sandy | 434.2 | DFR | 405.5 | DRY | 426 | DFR | 406.9 | DRY | 433.3 | DFR | 372.9 | DRY | 443.5 | DRY | 456.3 | Sandy | 379.2 | Sandy | 382.6 | Sandy | 435.6 | Sandy | 402.1 | DRY | 417.3 | Sandy | 347.7 | Sandy | 356.3 | Sandy | 389.2 | Sandy | 343.8 | Sandy | 395.5 | Sandy | 13 | 5 | 3 | 0 | 0 | 21 | 0 | 21 | 9 | 2 |  |  | 8469.2
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+6 |  | DB2+3 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+6 |  | DA+6 |  | DA+6
| LE |  | ,,, |  | ,,, |  | ,1,2,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,2 |  | ,,,1 |  | ,,, |  | 2,2,2,2 |  | ,,,1 |  | ,1,,1 |  | ,2,1,1 |  | ,,, |  | 1,2,, |  | ,2,,
REM
|  |  | 148 |  | 149 |  | 150 |  | 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168
|  |  | 22/12 |  | 22/13 |  | 23/0 |  | 24/0 |  | 25/0 |  | 25/1 |  | 25/2 |  | 25/3 |  | 25/4 |  | 26/0 |  | 26/1 |  | 26/2 |  | 26/3 |  | 26/4 |  | 26/5 |  | 26/6 |  | 26/7 |  | 26/8 |  | 27/0 |  | 27/1 |  | 27/2
[57 empty] | 0 | 0 | 0
| ERE |  |  |  | E |  |  |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  |  |  | Done | [7 empty] | Done |  | Done |  |  |  | Done | [17 empty] | Done |  |  |  | Done |  | Done
| FDN | 408 | Sandy | 318 | Sandy | 447.3 | DRY | 222.2 | DRY | 433.9 | DRY | 422.3 | DRY | 370.7 | DRY | 345.7 | Sandy | 391.1 | Sandy | 440.4 | DFR | 391.4 | DRY | 406.5 | DFR | 418 | DRY | 422.6 | Sandy | 410 | Sandy | 363.4 | Sandy | 421.9 | DFR | 416.7 | DFR | 413.8 | DFR | 399.8 | DFR | 425.2 | DFR | 7 | 7 | 7 | 0 | 0 | 21 | 0 | 21 | 19 | 7 |  |  | 8288.9
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+6 |  | DD45+3 |  | DD45+3 |  | DC1+6 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+6 |  | DC1+0 |  | DA+3 |  | DA+3
| LE |  | 1,2,, |  | ,,1, |  | 2,2,2,2 |  | 2,2,2,2 |  | ,,, |  | ,,, |  | ,,, |  | 1,2,,2 |  | 1,1,,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 1,,, |  | 1,1,, |  | ,1,1, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189
|  |  | 27/3 |  | 27/4 |  | 27/5 |  | 27/6 |  | 27/7 |  | 27/8 |  | 27/9 |  | 27/10 |  | 27/11 |  | 27/12 |  | 28/0 |  | 28/1 |  | 28/2 |  | 28/3 |  | 28/4 |  | 28/5 |  | 28/6 |  | 28/7 |  | 28/8 |  | 29/0 |  | 29/1
[57 empty] | 0 | 0 | 0
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done | [5 empty] | Done |  | Done |  | Done |  | Done |  | Done | [5 empty] | Done |  | Done |  | Done |  |  |  | Done
| FDN | 398.6 | DFR | 430.7 | DFR | 410 | DRY | 402.6 | Sandy | 343.5 | DFR | 392 | DFR | 381.1 | DFR | 366.3 | DFR | 420.1 | DRY | 420.8 | Sandy | 406.6 | DFR | 379.6 | DRY | 385 | DFR | 369 | DFR | 409 | Sandy | 422 | Sandy | 370 | Sandy | 464 | Sandy | 375 | Sandy | 465.5 | DRY | 365.6 | DRY | 7 | 5 | 9 | 0 | 0 | 21 | 0 | 21 | 21 | 15 |  |  | 8377
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,2,, |  | 1,4,3, |  | 1,3,2, |  | ,,5,3 |  | ,,, |  | ,,,
REM
|  |  | 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  | 210
|  |  | 29/2 |  | 29/3 |  | 29/4 |  | 30/0 |  | 30/1 |  | 30/2 |  | 30/3 |  | 30/4 |  | 30/5 |  | 30/6 |  | 31/0 |  | 31/1 |  | 31/2 |  | 32/0 |  | 32/1 |  | 32/2 |  | 32/3 |  | 32/4 |  | 33/0 |  | 33/1 |  | 34/0
[57 empty] | 0 | 0 | 0
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  |  |  | Done |  |  |  | Done |  | Done |  | Done |  |  |  | Done | [5 empty] | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 424 | DRY | 399 | Sandy | 440 | DRY | 382.1 | DRY | 388.9 | Sandy | 445 | Sandy | 395 | Sandy | 387 | DRY | 442 | DRY | 314 | DRY | 347.4 | Sandy | 383.6 | DRY | 366 | DRY | 332.9 | DRY | 402.7 | Sandy | 428.8 | DRY | 410.9 | Sandy | 381.1 | Sandy | 451.5 | DRY | 379.6 | DRY | 292.5 | DRY | 8 | 13 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 16 |  |  | 8194
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+0 |  | DA+6 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DC1+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DC1+0 |  | DA+0 |  | DB2+0
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 2,,, |  | 1,2,, |  | 1,2,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 1,,, |  | ,1,1, |  | ,,,
REM
|  |  | 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220 |  | 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230 |  | 231
|  |  | 34/1 |  | 34/2 |  | 34/3 |  | 34/4 |  | 35/0 |  | 35/1 |  | 35/2 |  | 35/3 |  | 35/4 |  | 35/5 |  | 36/0 |  | 36/1 |  | 36/2 |  | 36/3 |  | 36/4 |  | 37/0 |  | 37/1 |  | 37/2 |  | 37/3 |  | 38/0 |  | 38/1
[57 empty] | 0 | 0 | 0
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  |  |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done | [9 empty] | Done
| FDN | 432.6 | Sandy | 407.5 | Sandy | 377 | Sandy | 451.6 | Sandy | 379.3 | Sandy | 265.6 | Sandy | 492.4 | Sandy | 522.2 | Sandy | 418.9 | DRY | 421.7 | Sandy | 342.7 | Sandy | 386.4 | Sandy | 309.4 | Sandy | 357.8 | Sandy | 480.4 | Sandy | 350.5 | Sandy | 443.3 | Sandy | 356.7 | Sandy | 339.9 | Sandy | 500.3 | Sandy | 421.4 | Sandy | 20 | 1 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 15 |  |  | 8457.6
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+9 |  | DA+6 |  | DA+0 |  | DA+0 |  | DB2+6 |  | DA+9 |  | DB1+0 |  | DB1+6 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+6 |  | DB2+0 |  | DA+9 |  | DA+3 |  | DA+0 |  | DB2+6 |  | DA+0
| LE |  | ,,, |  | ,,,2 |  | ,3,, |  | ,3,1, |  | 2,,, |  | 2,,,2 |  | 1,1,, |  | 1,,, |  | ,,, |  | ,,4,4 |  | ,,, |  | ,,, |  | 1,1,, |  | ,2,, |  | 2,3,,5 |  | ,,,1 |  | 2,2,2,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240 |  | 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250 |  | 251 |  | 252
|  |  | 38/2 |  | 38/3 |  | 38/4 |  | 39/0 |  | 39/1 |  | 40/0 |  | 40/1 |  | 40/2 |  | 40/3 |  | 41/0 |  | 41/1 |  | 41/2 |  | 42/0 |  | 42/1 |  | 42/2 |  | 42/3 |  | 42/4 |  | 42/5 |  | 42/6 |  | 43/0 |  | 43/1
[57 empty] | 0 | 0 | 0
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  |  |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 419 | Sandy | 420.3 | Sandy | 414.9 | Sandy | 425.5 | Sandy | 412.638 | Sandy | 322.61 | Sandy | 396.2 | Sandy | 425.8 | Sandy | 401.7 | Sandy | 436.3 | Sandy | 340.8 | Sandy | 447.8 | Sandy | 382.3 | Sandy | 384.7 | Sandy | 407.4 | Sandy | 414.2 | Sandy | 256.4 | Sandy | 403.8 | Sandy | 396.7 | Sandy | 403.9 | Sandy | 346 | Sandy | 21 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 20 |  |  | 8258.948
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+6 |  | DA+9 |  | DA+9 |  | DB2+6 |  | DA+0 |  | DC2+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DC1+6 |  | DB1+9 |  | DA+0 |  | DC1+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+0 |  | DB1+0 |  | DA+3
| LE |  | ,,, |  | 2,2,2,2 |  | 1,1,,1 |  | ,,, |  | ,,, |  | 1,1,, |  | 1,2,, |  | ,,, |  | 1,2,, |  | 3,1,,1 |  | 4,5,6,6 |  | ,,1,1 |  | 1,,,2 |  | 1,,, |  | ,,1,3 |  | ,,, |  | ,,, |  | ,,,1 |  | 2,1,,2 |  | ,,, |  | ,,3,3
REM
|  |  | 253 |  | 254 |  | 255 |  | 256 |  | 257 |  | 258 |  | 259 |  | 260 |  | 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270 |  | 271 |  | 272 |  | 273
|  |  | 43/2 |  | 43/3 |  | 43/4 |  | 43/5 |  | 43/6 |  | 43/7 |  | 43/8 |  | 43/9 |  | 43/10 |  | 43/11 |  | 44/0 |  | 44/1 |  | 44/2 |  | 44/3 |  | 44/4 |  | 44/5 |  | 44/6 |  | 44/7 |  | 44/8 |  | 44/9 |  | 44/10
[40 empty] | ,, |  | ,, | [14 empty] | 0 | 0 | 0
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
|  |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done | [9 empty] | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  |  |  | Done
|  | 475.8 | Sandy | 363.7 | DRY | 431.8 | Sandy | 405.3 | DRY | 427.8 | Sandy | 389.8 | Sandy | 449.5 | Sandy | 388 | Sandy | 346.3 | Sandy | 444.8 | Sandy | 383.9 | Sandy | 384.3 | Sandy | 359 | Sandy | 334 | Sandy | 395 | Sandy | 355 | Sandy | 485 | Sandy | 473 | Sandy | 367 | Sandy | 430 | Sandy | 365 | Sandy | 19 | 2 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 15 |  |  | 8454
|  |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
|  |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DB1+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+9 |  | DB1+3 |  | DA+9 |  | DCT+0 |  | DA+9 |  | DB1+9
|  |  | 1,,,1 |  | ,1,, |  | 1,1,, |  | ,,, |  | ,,, |  | ,,, |  | 1,,, |  | ,,, |  | 3,3,, |  | 2,3,,1 |  | 0,1,1,0 |  | 0,0,1,0 |  | 0,0,0,0 |  | 2,0,0,1 |  | 4,3,3,3 |  | 1,3,0,0 |  | 1,0,0,1 |  | 0,0,0,0 |  | 1,2,0,1 |  | 4,0,2,6 |  | 0,1,0,0
REM
|  |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279 |  | 280 |  | 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290 |  | 291 |  | 292 |  | 293 |  | 294
|  |  | 44/11 |  | 45/0 |  | 45/1 |  | 46/0 |  | 47/0 |  | 47/1 |  | 47/2 |  | 47/3 |  | 47/4 |  | 47/5 |  | 47/6 |  | 47/7 |  | 47/8 |  | 47/9 |  | 47/10 |  | 48/0 |  | 48/1 |  | 49/0 |  | 49/1 |  | 49/2 |  | 49/3
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8120.77
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  |  |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 428 | Sandy | 327.2 | Sandy | 294.92 | Sandy | 406.54 | Sandy | 199.08 | Sandy | 441.2 | Sandy | 365.93 | Sandy | 417.4 | Sandy | 358.4 | Sandy | 461.2 | Sandy | 377.3 | Sandy | 431.5 | Sandy | 398.8 | Sandy | 405.9 | Sandy | 433.7 | Sandy | 386.2 | Sandy | 428.9 | Sandy | 402.9 | Sandy | 379.1 | Sandy | 386.6 | Sandy | 390 | Sandy | 21 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 20 |  |  | 8120.77
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+0 |  | DC2+0 |  | DA+9 |  | DD60+25 |  | DD60+25 |  | DA+3 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC2+0 |  | DA+9 |  | DD45+0 |  | DA+0 |  | DA+3 |  | DA+3
| LE |  | 0,1,0,0 |  | 0,1,0,0 |  | 0,0,6,6 |  | 0,6,6,2 |  | 5,5,5,5 |  | 2,0,2,5 |  | 0,0,0,0 |  | 1,2,0,0 |  | ,,, |  | 0,1,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 1,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0
REM
|  |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | 300 |  | 301 |  | 302 |  | 303 |  | 304 |  | 305 |  | 306 |  | 307 |  | 308 |  | 309 |  | 310 |  | 311 |  | 312 |  | 313 |  | 314 |  | 315
|  |  | 49/4 |  | 49/5 |  | 49/6 |  | 49/7 |  | 50/0 |  | 50/1 |  | 50/2 |  | 50/3 |  | 50/4 |  | 50/5 |  | 50/6 |  | 50/7 |  | 50/8 |  | 50/9 |  | 50/10 |  | 51/0 |  | 51/1 |  | 51/2 |  | 52/0 |  | 52/1 |  | 52/2
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [18 empty] | 0 | 0 | 7564.3
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 421.7 | Sandy | 396.6 | Sandy | 412.8 | Sandy | 340.2 | Sandy | 500.2 | Sandy | 469.1 | Sandy | 367.1 | Sandy | 470.4 | Sandy | 354.8 | Sandy | 442.1 | Sandy | 364.4 | Sandy | 470.8 | Sandy | 345 | Sandy | 364.4 | Sandy | 394.6 | Sandy | 401.4 | Sandy | 356.6 | Sandy | 307.1 | Sandy | 385 | Sandy | 402 | Sandy | 402.6 | Sandy | 21 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8368.9
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+0 |  | DA+9 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+6 |  | DA+6
| LE |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,3,2,2 |  | 0,0,0,1 |  | 1,0,0,0 |  | 2,2,2,2 |  | 0,0,1,0 |  | 3,3,4,3 |  | 4,3,4,3 |  | 3,4,3,3 |  | 0,0,0,1 |  | 0,0,0,0 |  | 0,0,1,0 |  | 0,0,1,0 |  | 0,0,0,0 |  | 0,0,1,0 |  | 0,0,0,0 |  | 0,0,3,3 |  | 0,4,0,0 |  | 0,0,0,3
REM
|  |  | 316 |  | 317 |  | 318 |  | 319 |  | 320 |  | 321 |  | 322 |  | 323 |  | 324 |  | 325 |  | 326 |  | 327 |  | 328 |  | 329 |  | 330 |  | 331 |  | 332 |  | 333 |  | 334 |  | 335 |  | 336
|  |  | 52/3 |  | 52/4 |  | 52/5 |  | 52/6 |  | 52/7 |  | 52/8 |  | 52/9 |  | 52/10 |  | 53/0 |  | 53/1 |  | 53/2 |  | 53/3 |  | 53/4 |  | 53/5 |  | 53/6 |  | 53/7 |  | 53/8 |  | 54/0 |  | 54/1 |  | 54/2 |  | 54/3
[57 empty] | 0 | 0 | 0
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  |  |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  |  |  | Done |  |  |  | Done |  | Done
| FDN | 437 | Sandy | 393.8 | Sandy | 447 | Sandy | 373 | Sandy | 406.8 | Sandy | 433 | Sandy | 399.7 | Sandy | 384.1 | Sandy | 455.9 | Sandy | 433.2 | Sandy | 407.4 | Sandy | 394.5 | Sandy | 410.1 | Sandy | 428.1 | Sandy | 406.6 | Sandy | 411.3 | Sandy | 427.8 | Sandy | 371.3 | Sandy | 365.1 | Sandy | 381 | Sandy | 417 | Sandy | 21 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 18 |  |  | 8583.7
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+9 |  | DB2+9 |  | DA+9 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+3 |  | DB1+6 |  | DA+3 |  | DA+3 |  | DA+6
| LE |  | 4,3,3,3 |  | 2,2,0,0 |  | 0,0,0,1 |  | 0,0,0,0 |  | 0,3,1,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 1,2,1,1 |  | 4,4,4,4 |  | 4,4,4,4 |  | 0,0,0,2 |  | 0,4,1,0 |  | 0,2,1,0 |  | 0,0,0,0 |  | 1,1,3,1 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 1,1,0,0 |  | 0,0,0,0 |  | 0,2,0,0
REM
|  |  | 337 |  | 338 |  | 339 |  | 340 |  | 341 |  | 342 |  | 343 |  | 344 |  | 345 |  | 346 |  | 347 |  | 348 |  | 349 |  | 350 |  | 351 |  | 352 |  | 353 |  | 354 |  | 355 |  | 356 |  | 357
|  |  | 54/4 |  | 54/5 |  | 55/0 |  | 55/1 |  | 55/2 |  | 55/3 |  | 55/4 |  | 55/5 |  | 55/6 |  | 55/7 |  | 55/8 |  | 56/0 |  | 57/0 |  | 57/1 |  | 57/2 |  | 57/3 |  | 57/4 |  | 57/5 |  | 57/6 |  | 57/7 |  | 58/0
[8 empty] | . |  | . |  | . |  | . |  | . |  | . |  | . |  | . |  | . |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 3318.21 | 0 | 3507.46
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  |  |  | Done |  |  |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done | [5 empty] | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 423.3 | Sandy | 401 | Sandy | 424 | Sandy | 404.9 | WFR | 343.1 | WFR | 357.7 | Sandy | 365.2 | Sandy | 350.1 | Sandy | 357.7 | Sandy | 337.8 | Sandy | 341.22 | Sandy | 460.49 | Sandy | 219.76 | Sandy | 461.1 | Sandy | 355.5 | DRY | 405.4 | DRY | 418.2 | Sandy | 416.8 | Sandy | 395 | Sandy | 401.8 | DFR | 433.9 | DFR | 15 | 2 | 2 | 2 | 0 | 21 | 0 | 21 | 21 | 17 |  |  | 8073.97
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+9 |  | DA+9 |  | DB1+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DD60+25 |  | DD60+25 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC1+3
| LE |  | 1,2,0,0 |  | 1,3,3,1 |  | 0,1,1,0 |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,1 |  | 0,0,1,3 |  | 0,0,1,2 |  | 0,0,1,0 |  | 0,0,0,0 |  | 3,3,0,2 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,1 |  | 0,1,0,0 |  | ,,, |  | 0,0,0,0
REM
|  |  | 358 |  | 359 |  | 360 |  | 361 |  | 362 |  | 363 |  | 364 |  | 365 |  | 366 |  | 367 |  | 368 |  | 369 |  | 370 |  | 371 |  | 372 |  | 373 |  | 374 |  | 375 |  | 376 |  | 377 |  | 378
|  |  | 59/0 |  | 59/1 |  | 59/2 |  | 59/3 |  | 59/4 |  | 59/5 |  | 59/6 |  | 59/7 |  | 59/8 |  | 59/9 |  | 59/10 |  | 59/11 |  | 59/12 |  | 59/13 |  | 59/14 |  | 59/15 |  | 59/16 |  | 60/0 |  | 60/1 |  | 60/2 |  | 60/3
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8606.7
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 238.9 | DRY | 411.3 | DRY | 418.2 | DFR | 412.3 | DFR | 421 | DFR | 419.7 | DFR | 419.1 | DFR | 408.8 | DRY | 426.9 | DRY | 434.7 | DRY | 400.8 | DRY | 436.3 | DFR | 393.1 | DFR | 447.4 | DRY | 391.1 | DRY | 448.6 | DRY | 388 | Dry | 438 | DRY | 413.8 | DRY | 424.2 | DFR | 414.5 | DFR | 0 | 12 | 9 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8606.7
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DC2+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+9 |  | DC1+0 |  | DA+6 |  | DA+3 |  | DA+3
| LE |  | 0,0,0,0 |  | 0,0,0,1 |  | 0,0,0,0 |  | 0,0,0,1 |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | ,,, |  | 0,0,2,0 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 2,2,0,0 |  | ,,,
REM
|  |  | 379 |  | 380 |  | 381 |  | 382 |  | 383 |  | 384 |  | 385 |  | 386 |  | 387 |  | 388 |  | 389 |  | 390 |  | 391 |  | 392 |  | 393 |  | 394 |  | 395 |  | 396 |  | 397 |  | 398 |  | 399
|  |  | 60/4 |  | 60/5 |  | 60/6 |  | 60/7 |  | 60/8 |  | 60/9 |  | 60/10 |  | 60/11 |  | 61/0 |  | 61/1 |  | 61/2 |  | 61/3 |  | 61/4 |  | 61/5 |  | 61/6 |  | 61/7 |  | 61/8 |  | 61/9 |  | 61/10 |  | 62/0 |  | 62/1
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8611.3
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 425.6 | DFR | 412.3 | DRY | 374.1 | DRY | 410.1 | DRY | 400.4 | DRY | 409.2 | DRY | 401 | DFR | 394.5 | DRY | 397.9 | DRY | 405.7 | DFR | 433.2 | DFR | 400.9 | DRY | 427 | DRY | 413.9 | DRY | 426.4 | DRY | 411.5 | Dry | 376.3 | DRY | 433.4 | Dry | 405.6 | DRY | 434.3 | DRY | 418 | Sandy | 1 | 16 | 4 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8611.3
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB2+0 |  | DA+6 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+6 |  | DA+0 |  | DA+9 |  | DB2+0 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,1 |  | 1,2,1,0 |  | ,,, |  | ,,, |  | 0,0,0,0 |  | 0,0,1,2
REM
|  |  | 400 |  | 401 |  | 402 |  | 403 |  | 404 |  | 405 |  | 406 |  | 407 |  | 408 |  | 409 |  | 410 |  | 411 |  | 412 |  | 413 |  | 414 |  | 415 |  | 416 |  | 417 |  | 418 |  | 419 |  | 420
|  |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | 62/6 |  | 62/7 |  | 62/8 |  | 62/9 |  | 62/10 |  | 62/11 |  | 63/0 |  | 63/1 |  | 63/2 |  | 63/3 |  | 63/4 |  | 63/5 |  | 63/6 |  | 63/7 |  | 63/8 |  | 64/0 |  | 64/1
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8531.5
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 386 | DRY | 400 | DRY | 401 | DRY | 403 | DRY | 404 | DRY | 423 | DRY | 409 | DFR | 409 | DFR | 411 | DFR | 413 | DRY | 386.1 | DFR | 400 | DFR | 416 | DFR | 411 | DFR | 399 | DRY | 413 | DFR | 426 | DRY | 413 | DRY | 425 | DRY | 408.3 | DRY | 375.1 | DRY | 0 | 13 | 8 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8531.5
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB2+0 |  | DA+0
| LE |  | 0,1,0,0 |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 421 |  | 422 |  | 423 |  | 424 |  | 425 |  | 426 |  | 427 |  | 428 |  | 429 |  | 430 |  | 431 |  | 432 |  | 433 |  | 434 |  | 435 |  | 436 |  | 437 |  | 438 |  | 439 |  | 440 |  | 441
|  |  | 64/2 |  | 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | 64/8 |  | 64/9 |  | 64/10 |  | 64/11 |  | 65/0 |  | 65/1 |  | 65/2 |  | 65/3 |  | 65/4 |  | 65/5 |  | 65/6 |  | 65/7 |  | 65/8 |  | 65/9 |  | 65/10
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8463.9
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 408.7 | DRY | 410.7 | DRY | 408.2 | DRY | 426.2 | DRY | 407.7 | DRY | 401.6 | DRY | 425.5 | DRY | 414.4 | DRY | 410.6 | DRY | 428.4 | DRY | 400.6 | DRY | 395.4 | DRY | 393.7 | DRY | 403.7 | DRY | 402.9 | DRY | 376.4 | DRY | 389.2 | DRY | 397.6 | DRY | 394.3 | DRY | 389 | DRY | 379.1 | DRY | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8463.9
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 442 |  | 443 |  | 444 |  | 445 |  | 446 |  | 447 |  | 448 |  | 449 |  | 450 |  | 451 |  | 452 |  | 453 |  | 454 |  | 455 |  | 456 |  | 457 |  | 458 |  | 459 |  | 460 |  | 461 |  | 462
|  |  | 65/11 |  | 66/0 |  | 67/0 |  | 67/1 |  | 67/2 |  | 68/0 |  | 69/0 |  | 69/1 |  | 70/0 |  | 70/1 |  | 70/2 |  | 70/3 |  | 70/4 |  | 70/5 |  | 70/6 |  | 70/7 |  | 70/8 |  | 70/9 |  | 70/10 |  | 70/11 |  | 71/0
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8020.2
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 387.6 | DRY | 426.9 | DRY | 207.8 | DRY | 347.1 | DRY | 344.9 | DRY | 369.2 | DRY | 200.9 | DFR | 374.1 | DRY | 394.9 | DRY | 388.4 | DRY | 418.9 | DRY | 418.6 | DRY | 414 | DRY | 419.6 | DRY | 420.3 | DRY | 419.6 | DRY | 418.2 | DRY | 414.1 | DRY | 406.1 | DRY | 408.6 | DRY | 420.4 | DRY | 0 | 20 | 1 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8020.2
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+0 |  | DC2+6 |  | DC1+9 |  | DA+0 |  | DA+0 |  | DD45+0 |  | DB2+0 |  | DA+3 |  | DC1+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB2+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 463 |  | 464 |  | 465 |  | 466 |  | 467 |  | 468 |  | 469 |  | 470 |  | 471 |  | 472 |  | 473 |  | 474 |  | 475 |  | 476 |  | 477 |  | 478 |  | 479 |  | 480 |  | 481 |  | 482 |  | 483
|  |  | 71/1 |  | 71/2 |  | 71/3 |  | 71/4 |  | 71/5 |  | 71/6 |  | 71/7 |  | 71/8 |  | 72/0 |  | 72/1 |  | 72/2 |  | 72/3 |  | 73/0 |  | 73/1 |  | 73/2 |  | 73/3 |  | 73/4 |  | 73/5 |  | 73/6 |  | 73/7 |  | 73/8
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8334.2
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 398.6 | DRY | 414.3 | DRY | 413 | DRY | 367.7 | DRY | 429.4 | DRY | 408 | DRY | 404.9 | DRY | 431.6 | DRY | 408.4 | DRY | 435.3 | DRY | 403.9 | DRY | 389.2 | DRY | 400.1 | DRY | 383.3 | DRY | 379 | DRY | 381.2 | DRY | 384.7 | DRY | 368.8 | DRY | 365.5 | DRY | 392.4 | DRY | 374.9 | DRY | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8334.2
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB2+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 484 |  | 485
|  |  | 73/9 |  | 74/0
|  | , |  | , | [52 empty] | 0 | 0 | 758.4
| ERE |  | E |  | E
| WELD |  | Done |  | Done
| FDN | 379.5 | DRY | 378.9 | Sandy |  |  |  | Towards Beawar S/S | [34 empty] | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 2 |  |  | 758.4
| EAR |  | C |  | C
| TOT |  | DA+0 |  | DB2+0
| LE |  | ,,, |  | ,,,
REM
Progress overview (Tower wise breakups)
| TOT |  | Total Qty. in No's |  | Wight of individual towers in MT | Progress breakups dashboard | [15 empty] | Notepad:- |  |  | PKG F
[6 empty] | FDN |  | ERE | [12 empty] | JMC Status
[6 empty] | Comp. | Balance | Comp. | Erected Weight (MT) |  | Balance | Balance to erect (MT) | [8 empty] | Description |  |  | Total Completed | Total Approved | Balance | CTQ approved | CTQ approval awaited | CTQ not initiated
| DA+0 |  | 150 |  | 37.5044 | 150 | 0 | 148 | 5550.6471 |  | 2 | 75.0087 | [8 empty] | Foundation |  |  | 484
| DA+3 |  | 161 |  | 38.8476 | 161 | 0 | 155 | 6021.3789 |  | 6 | 233.0856 | [8 empty] | Erection |  |  | 463
| DA+6 |  | 48 |  | 45.413 | 47 | 1 | 43 | 1952.7602 |  | 5 | 227.0651
| DA+9 |  | 38 |  | 47.1844 | 38 | 0 | 36 | 1698.6366 |  | 2 | 94.3687
| DB1+0 |  | 13 |  | 57.5972 | 13 | 0 | 11 | 633.5697 |  | 2 | 115.1945
| DB1+3 |  | 3 |  | 60.0968 | 3 | 0 | 3 | 180.2903 |  | 0 | 0
| DB1+6 |  | 3 |  | 67.8737 | 3 | 0 | 3 | 203.621 |  | 0 | 0
| DB1+9 |  | 3 |  | 70.7017 | 3 | 0 | 3 | 212.1051 |  | 0 | 0
| DB2+0 |  | 14 |  | 57.5972 | 14 | 0 | 14 | 806.3614 |  | 0 | 0
| DB2+3 |  | 4 |  | 60.0968 | 4 | 0 | 3 | 180.2903 |  | 1 | 60.0968
| DB2+6 |  | 3 |  | 67.8737 | 3 | 0 | 3 | 203.621 |  | 0 | 0
| DB2+9 |  | 2 |  | 70.7017 | 2 | 0 | 2 | 141.4034 |  | 0 | 0
| DC1+0 |  | 12 |  | 66.3811 | 12 | 0 | 11 | 730.1922 |  | 1 | 66.3811
| DCT+0 |  | 1 |  | 94.2199 | 1 | 0 | 1 | 94.2199 |  | 0 | 0
| DC1+3 |  | 1 |  | 69.2287 | 1 | 0 | 1 | 69.2287 |  | 0 | 0
| DC1+6 |  | 2 |  | 78.132 | 2 | 0 | 2 | 156.2641 |  | 0 | 0
| DC1+9 |  | 1 |  | 81.4946 | 1 | 0 | 1 | 81.4946 |  | 0 | 0
| DC2+0 |  | 9 |  | 66.3811 | 9 | 0 | 9 | 597.43 |  | 0 | 0
| DC2+3 |  | 0 |  | 69.2287 | 0 | 0 | 0 | 0 |  | 0 | 0
| DC2+6 |  | 1 |  | 78.132 | 1 | 0 | 1 | 78.132 |  | 0 | 0
| DC2+9 |  | 0 |  | 81.4946 | 0 | 0 | 0 | 0 |  | 0 | 0
| DD45+0 |  | 2 |  | 86.1293 | 2 | 0 | 2 | 172.2586 |  | 0 | 0
| DD45+3 |  | 2 |  | 89.9096 | 2 | 0 | 1 | 89.9096 |  | 1 | 89.9096
| DD60+0 |  | 3 |  | 86.1293 | 3 | 0 | 3 | 258.3878 |  | 0 | 0
| DD60+3 |  | 1 |  | 89.9096 | 1 | 0 | 0 | 0 |  | 1 | 89.9096
| DD60+6 |  | 2 |  | 100.968 | 2 | 0 | 2 | 201.936 |  | 0 | 0
| DD60+9 |  | 0 |  | 105.0682 | 0 | 0 | 0 | 0 |  | 0 | 0
| DD60+18 |  | 1 |  | 129.111 | 1 | 0 | 1 | 129.111 |  | 0 | 0
| DD60+25 |  | 5 |  | 143.6019 | 5 | 0 | 4 | 574.4075 |  | 1 | 143.6019
| Total |  | 485 |  |  | 484 | 1 | 463 | 21017.6569 |  | 22 | 1194.6217
Global Footprint in 110+ countries*
*Includes EPC and Supply
TATA PORTION
TATA PORTION
TATA PORTION

## Visual chart Edit
Progress Summary'!A1
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Data taken from Pramanand mail dated 12/12/24.
Sr. No. | PKG G
| Loc No | TOT | A | B | C | D | CONCATANATE (A,B,C,D) | Span length | Remarks | FDN | Erection | Tackwelding
0 | Gty
1 | 1/0 | DD60+0 |  |  |  |  | ,,, | 122 |  | DRY | E | Done
2 | 1A/0 | DD60+0 |  |  |  |  | ,,, | 90 | As per approved 0,0,0,1 | DRY | E | Done
3 | 1A/1 | DA+6 |  |  |  |  | ,,, | 277.7 |  | DFR | E | Done
4 | 1A/2 | DA+0 |  | 1 | 1 |  | ,1,1, | 386 |  | DRY | E | Done
5 | 1A/3 | DA+0 |  |  |  |  | ,,, | 443.6 |  | DRY | E | Done
6 | 1A/4 | DA+3 |  |  | 1 |  | ,,1, | 333.4 |  | DFR | E | Done
7 | 1A/5 | DA+0 | 1 | 1 |  |  | 1,1,, | 431.9 |  | DRY | E | Done
8 | 1A/6 | DA+0 | 1 |  |  | 1 | 1,,,1 | 348.7 |  | Sandy | E | Done
9 | 1A/7 | DA+3 |  | 1 |  |  | ,1,, | 395.7 |  | Sandy | E | Done
10 | 1A/8 | DA+0 |  |  |  |  | ,,, | 415 |  | Sandy | E | Done
11 | 2/0 | DC1+0 |  |  |  |  | ,,, | 394.3 |  | DRY | E | Done
12 | 2/1 | DA+3 |  |  |  |  | ,,, | 405.3 |  | Sandy | E | Done
13 | 2/2 | DA+3 |  |  |  | 1 | ,,,1 | 338.5 |  | Sandy | E | Done
14 | 2/3 | DA+3 | 1 |  | 1 | 1 | 1,,1,1 | 406 |  | Sandy | E | Done
15 | 2/4 | DA+3 |  |  |  |  | ,,, | 429 |  | Sandy | E | Done
16 | 2/5 | DA+3 |  |  | 1 | 1 | ,,1,1 | 411.6 |  | Sandy | E | Done
17 | 2/6 | DA+3 |  |  |  | 1 | ,,,1 | 425.7 |  | Sandy | E | Done
18 | 2/7 | DA+3 |  |  |  |  | ,,, | 408.2 |  | Sandy | E | Done
19 | 2/8 | DA+0 |  |  |  |  | ,,, | 354.6 |  | Sandy | E | Done
20 | 2/9 | DA+0 |  |  |  |  | ,,, | 308.7 |  | DRY | E | Done
21 | 3/0 | DD60+6 |  |  |  |  | ,,, | 336 |  | DRY | E | Done
22 | 4/0 | DD60+6 |  |  |  |  | ,,, | 226.5 |  | DRY | E | Done
23 | 4/1 | DA+0 |  |  |  |  | ,,, | 343 |  | DRY | E | Done
24 | 4/2 | DA+0 |  |  |  |  | ,,, | 358.4 |  | DRY | E | Done
25 | 4/3 | DA+0 |  |  |  |  | ,,, | 381 |  | DRY | E | Done
26 | 4/4 | DA+0 |  |  |  |  | ,,, | 367.6 |  | DRY | E | Done
27 | 5/0 | DB1+9 | 5 | 5 | 5 | 5 | 5,5,5,5 | 423.1 |  | DRY | E | Done
28 | 6/0 | DB2+9 | 5 | 5 | 5 | 5 | 5,5,5,5 | 246 |  | DRY | E | Done
29 | 6/1 | DA+0 |  |  |  |  | ,,, | 429.9 |  | DFR | E | Done
30 | 6/2 | DA+0 |  |  |  |  | ,,, | 362.4 |  | DFR | E | Done
31 | 7/0 | DB1+0 | 2 | 3 | 3 | 2 | 2,3,3,2 | 347.9 |  | DRY | E | Done
32 | 8/0 | DB1+0 |  |  |  |  | ,,, | 210.8 |  | DRY | E | Done
33 | 8/1 | DA+3 |  |  |  |  | ,,, | 409.2 |  | DRY | E | Done
34 | 8/2 | DA+3 |  |  |  |  | ,,, | 413.6 |  | DRY | E | Done
35 | 8/3 | DA+0 |  |  |  |  | ,,, | 393.2 |  | DRY | E | Done
36 | 8/4 | DA+3 |  |  |  |  | ,,, | 416.5 |  | DRY | E | Done
37 | 8/5 | DA+3 |  |  |  | 1 | ,,,1 | 394.6 |  | DRY | E | Done
38 | 8/6 | DA+3 |  |  |  |  | ,,, | 393.2 |  | DRY
39 | 8/7 | DB1+0 |  |  |  |  | ,,, | 441.1 |  | DRY
40 | 8/8 | DA+6 |  |  |  |  | ,,, | 414.4 |  | DRY | E
41 | 8/9 | DA+3 |  |  |  |  | ,,, | 395.863 |  | DFR | E | Done
42 | 8/10 | DA+3 |  |  |  |  | ,,, | 413.404 |  | DFR | E | Done
43 | 8/11 | DA+0 |  |  |  |  | ,,, | 402.6 |  | DRY | E
44 | 8/12 | DA+0 |  |  |  |  | ,,, | 372.1 |  | DRY | E
45 | 9/0 | DD60+18 |  |  |  |  | ,,, | 457.7 |  | DRY | E
46 | 10/0 | DD60+25 |  |  |  |  | ,,, | 233.1 |  | DFR
47 | 10/1 | DA+0 |  |  |  |  | ,,, | 443.7 |  | DRY | E | Done
48 | 10/2 | DA+0 |  |  |  |  | ,,, | 383.2 |  | DFR | E
49 | 10/3 | DA+0 |  |  |  |  | ,,, | 398.6 |  | DFR | E | Done
50 | 10/4 | DA+3 |  |  |  |  | ,,, | 410.7 |  | DFR | E | Done
51 | 10/5 | DA+3 |  |  |  |  | ,,, | 416.2 |  | DRY | E | Done
52 | 10/6 | DA+0 |  |  |  |  | ,,, | 403.4 |  | DFR | E | Done
53 | 10/7 | DA+3 |  |  |  |  | ,,, | 373.845 |  | DRY | E | Done
54 | 10/8 | DA+3 |  |  |  |  | ,,, | 411.823 |  | DFR | E | Done
55 | 10/9 | DA+0 |  |  |  |  | ,,, | 414.2 |  | DRY | E | Done
56 | 10/10 | DA+3 |  |  |  |  | ,,, | 402.3 |  | Sandy | E | Done
57 | 10/11 | DA+3 |  |  |  |  | ,,, | 430.3 |  | DRY | E | Done
58 | 10/12 | DB1+0 |  |  |  |  | ,,, | 406.2 |  | DRY | E | Done
59 | 10/13 | DA+3 |  |  |  |  | ,,, | 405.3 |  | DRY | E | Done
60 | 10/14 | DA+3 |  |  |  |  | ,,, | 427.1 |  | DRY | E | Done
61 | 10/15 | DA+3 |  |  |  |  | ,,, | 400 |  | DRY | E | Done
62 | 10/16 | DA+3 |  |  |  |  | ,,, | 412.8 |  | DRY | E | Done
63 | 10/17 | DA+3 |  |  |  |  | ,,, | 387.8 |  | DFR | E | Done
64 | 10/18 | DA+3 |  |  |  |  | ,,, | 436.7 |  | DFR | E | Done
65 | 10/19 | DA+0 |  |  |  |  | ,,, | 403.7 |  | DRY | E | Done
66 | 10/20 | DA+3 |  |  |  |  | ,,, | 409.5 |  | DFR | E | Done
67 | 10/21 | DA+3 |  |  |  |  | ,,, | 418.6 |  | DFR | E | Done
68 | 10/22 | DA+0 | 1 | 3 |  |  | 1,3,, | 410.3 |  | Sandy | E | Done
69 | 10/23 | DA+0 |  | 2 |  |  | ,2,, | 384 |  | Sandy | E | Done
70 | 11/0 | DB1+0 | 1 | 4 |  | 3 | 1,4,,3 | 450.8 |  | Sandy | E | Done
71 | 11/1 | DA+0 |  |  |  |  | ,,, | 384.2 |  | Sandy | E | Done
72 | 11/2 | DA+0 | 2 | 1 |  |  | 2,1,, | 338.6 |  | Sandy | E | Done
73 | 11/3 | DA+0 |  |  |  | 1 | ,,,1 | 370.7 |  | Sandy | E
74 | 11/4 | DA+0 |  |  |  |  | ,,, | 434.1 |  | Sandy | E
75 | 11/5 | DA+0 |  |  |  |  | ,,, | 368.1 |  | DFR | E | Done
76 | 11A/0 | DB1+0 |  |  |  |  | ,,, | 342.3 |  | DRY | E | Done
77 | 11A/1 | DA+3 |  |  |  |  | ,,, | 405.1 |  | DRY | E
78 | 11A/2 | DA+0 |  |  |  |  | ,,, | 412.2 |  | DRY | E
79 | 11A/3 | DA+3 |  |  |  |  | ,,, | 412.2 |  | DRY | E
80 | 11A/4 | DA+3 |  |  |  |  | ,,, | 422.1 |  | DRY
81 | 11A/5 | DA+3 |  |  |  |  | ,,, | 418.3 |  | DRY | E
82 | 11A/6 | DA+6 |  |  |  |  | ,,, | 384.3 |  | DRY | E
83 | 11A/7 | DA+9 |  |  |  |  | ,,, | 434.2 |  | Sandy | E
84 | 11A/8 | DA+6 |  | 2 | 4 | 1 | ,2,4,1 | 390.1 |  | Sandy | E | Done
85 | 11A/9 | DA+3 |  |  |  |  | ,,, | 426.3 |  | DRY | E | Done
86 | 12/0 | DD60+0 |  |  |  |  | ,,, | 405.9 |  | DRY | E | Done
87 | 13/0 | DD60+3 |  |  |  |  | ,,, | 211.9 |  | DRY
88 | 13/1 | DA+9 |  |  |  |  | ,,, | 464.3 |  | DRY | E
89 | 13/2 | DA+3 |  |  |  |  | ,,, | 373.7 |  | DRY | E
90 | 13/3 | DA+3 |  |  | 2 | 4 | ,,2,4 | 419.7 |  | Sandy | E
91 | 13/4 | DA+3 |  |  |  |  | ,,, | 420.3 |  | DRY | E
92 | 14/0 | DC2+0 |  |  |  |  | ,,, | 400 |  | Sandy | E
93 | 14A/0 | DC1+0 |  |  |  |  | ,,, | 381.4 |  | DRY | E
94 | 14A/1 | DA+3 |  |  |  |  | ,,, | 412.765 |  | DRY | E
95 | 14A/2 | DA+0 |  |  |  |  | ,,, | 396.029 |  | DRY | E
96 | 15/0 | DC1+0 |  |  |  |  | ,,, | 383.3 |  | DRY
97 | 15/1 | DA+3 |  |  |  |  | ,,, | 404.6 |  | DRY | E | Done
98 | 16/0 | DC1+0 |  |  |  |  | ,,, | 413.3 |  | DRY | E
99 | 16/1 | DA+0 |  |  |  |  | ,,, | 354.283 |  | DRY | E | Done
100 | 16/2 | DA+0 | 1 |  |  | 1 | 1,,,1 | 424.28 |  | DRY | E | Done
101 | 16/3 | DA+3 |  |  |  |  | ,,, | 340.3 |  | DRY | E | Done
102 | 16/4 | DA+0 |  | 1 |  |  | ,1,, | 394.7 |  | DRY | E | Done
103 | 16/5 | DA+3 |  |  |  |  | ,,, | 435.863 |  | DRY | E | Done
104 | 17/0 | DB2+3 |  |  |  | 1 | ,,,1 | 386.8 |  | DRY | E | Done
105 | 17/1 | DA+3 |  |  |  |  | ,,, | 393.7 |  | DRY | E | Done
106 | 17/2 | DA+6 |  |  |  |  | ,,, | 415.9 |  | DRY | E
107 | 17/3 | DA+0 |  |  |  |  | ,,, | 422.8 |  | DRY | E
108 | 17/4 | DA+3 |  |  |  |  | ,,, | 409.9 |  | DRY | E | Done
109 | 17/5 | DA+3 |  |  |  |  | ,,, | 425.3 |  | DRY | E
110 | 18/0 | DC2+0 |  |  |  |  | ,,, | 383.4 |  | DRY | E | Done
111 | 18/1 | DA+0 |  |  |  |  | ,,, | 372.8 |  | DRY | E | Done
112 | 18/2 | DA+0 |  |  |  |  | ,,, | 379.8 |  | DRY | E
113 | 18/3 | DA+0 |  |  |  |  | ,,, | 371 |  | DRY | E
114 | 18/4 | DA+0 |  |  |  |  | ,,, | 398.7 |  | DRY | E
115 | 19/0 | DC2+0 |  |  |  |  | ,,, | 380.8 |  | DRY | E
116 | 19/1 | DA+0 |  |  |  |  | ,,, | 366.9 |  | DRY | E
117 | 19/2 | DA+0 |  |  |  |  | ,,, | 372.5 |  | DRY | E
118 | 19/3 | DA+0 |  |  |  |  | ,,, | 376.5 |  | DRY | E
119 | 19/4 | DA+0 |  |  |  |  | ,,, | 384.3 |  | DRY | E
120 | 19/5 | DA+0 |  |  |  |  | ,,, | 375.4 |  | DRY | E
121 | 20/0 | DB2+0 |  |  |  |  | ,,, | 381.2 |  | Sandy | E
122 | 20/1 | DA+0 |  |  |  |  | ,,, | 386.8 |  | Sandy
123 | 20/2 | DA+0 |  |  |  |  | ,,, | 387 |  | DRY | E | Done
124 | 20/3 | DA+0 |  |  |  |  | ,,, | 348.5 |  | DRY | E | Done
125 | 21/0 | DB2+0 |  |  |  |  | ,,, | 355 |  | DRY | E
126 | 21/1 | DA+6 |  |  |  |  | ,,, | 414.9 |  | ROW
127 | 21/2 | DA+0 |  |  |  |  | ,,, | 407.2 |  | Sandy
128 | 21/3 | DA+6 |  |  |  |  | ,,, | 432.2 |  | Sandy | E
129 | 21/4 | DA+3 |  | 1 | 2 | 1 | ,1,2,1 | 401.9 |  | Sandy | E | Done
130 | 21/5 | DA+6 |  |  |  |  | ,,, | 434.2 |  | DFR | E | Done
131 | 21/6 | DA+3 |  |  |  |  | ,,, | 405.5 |  | DRY
132 | 21/7 | DA+3 |  |  |  |  | ,,, | 426 |  | DFR
133 | 21/8 | DA+6 |  |  |  |  | ,,, | 406.9 |  | DRY
134 | 21/9 | DA+3 |  |  |  |  | ,,, | 433.3 |  | DFR
135 | 21/10 | DA+6 |  |  |  |  | ,,, | 372.9 |  | DRY
136 | 22/0 | DB2+3 |  |  |  |  | ,,, | 443.5 |  | DRY
137 | 22/1 | DA+9 |  |  |  |  | ,,, | 456.3 |  | Sandy
138 | 22/2 | DA+6 |  |  |  | 2 | ,,,2 | 379.2 |  | Sandy | E
139 | 22/3 | DA+9 |  |  |  | 1 | ,,,1 | 382.6 |  | Sandy | E
140 | 22/4 | DA+9 |  |  |  |  | ,,, | 435.6 |  | Sandy
141 | 22/5 | DA+9 | 2 | 2 | 2 | 2 | 2,2,2,2 | 402.1 |  | DRY | E
142 | 22/6 | DA+0 |  |  |  | 1 | ,,,1 | 417.3 |  | Sandy | E
143 | 22/7 | DA+0 |  | 1 |  | 1 | ,1,,1 | 347.7 |  | Sandy | E
144 | 22/8 | DB1+0 |  | 2 | 1 | 1 | ,2,1,1 | 356.3 |  | Sandy
145 | 22/9 | DA+6 |  |  |  |  | ,,, | 389.2 |  | Sandy
146 | 22/10 | DA+6 | 1 | 2 |  |  | 1,2,, | 343.8 |  | Sandy
147 | 22/11 | DA+6 |  | 2 |  |  | ,2,, | 395.5 |  | Sandy | E
148 | 22/12 | DA+3 | 1 | 2 |  |  | 1,2,, | 408 |  | Sandy
149 | 22/13 | DA+6 |  |  | 1 |  | ,,1, | 318 |  | Sandy | E | Done
150 | 23/0 | DD45+3 | 2 | 2 | 2 | 2 | 2,2,2,2 | 447.3 |  | DRY
151 | 24/0 | DD45+3 | 2 | 2 | 2 | 2 | 2,2,2,2 | 222.2 |  | DRY | E
152 | 25/0 | DC1+6 |  |  |  |  | ,,, | 433.9 |  | DRY | E
153 | 25/1 | DA+3 |  |  |  |  | ,,, | 422.3 |  | DRY | E | Done
154 | 25/2 | DA+0 |  |  |  |  | ,,, | 370.7 |  | DRY | E | Done
155 | 25/3 | DA+0 | 1 | 2 |  | 2 | 1,2,,2 | 345.7 |  | Sandy | E
156 | 25/4 | DA+0 | 1 | 1 |  | 1 | 1,1,,1 | 391.1 |  | Sandy | E | Done
157 | 26/0 | DB1+0 |  |  |  |  | ,,, | 440.4 |  | DFR | E
158 | 26/1 | DA+0 |  |  |  |  | ,,, | 391.4 |  | DRY | E
159 | 26/2 | DA+3 |  |  |  |  | ,,, | 406.5 |  | DFR | E
160 | 26/3 | DA+0 |  |  |  |  | ,,, | 418 |  | DRY | E
161 | 26/4 | DA+6 | 1 |  |  |  | 1,,, | 422.6 |  | Sandy | E
162 | 26/5 | DA+6 | 1 | 1 |  |  | 1,1,, | 410 |  | Sandy | E
163 | 26/6 | DA+6 |  | 1 | 1 |  | ,1,1, | 363.4 |  | Sandy | E
164 | 26/7 | DA+0 |  |  |  |  | ,,, | 421.9 |  | DFR | E
165 | 26/8 | DA+6 |  |  |  |  | ,,, | 416.7 |  | DFR | E | Done
166 | 27/0 | DC1+0 |  |  |  |  | ,,, | 413.8 |  | DFR | E
167 | 27/1 | DA+3 |  |  |  |  | ,,, | 399.8 |  | DFR | E | Done
168 | 27/2 | DA+3 |  |  |  |  | ,,, | 425.2 |  | DFR | E | Done
169 | 27/3 | DA+3 |  |  |  |  | ,,, | 398.6 |  | DFR | E | Done
170 | 27/4 | DA+3 |  |  |  |  | ,,, | 430.7 |  | DFR | E | Done
171 | 27/5 | DA+0 |  |  |  |  | ,,, | 410 |  | DRY | E | Done
172 | 27/6 | DA+0 |  |  |  |  | ,,, | 402.6 |  | Sandy | E | Done
173 | 27/7 | DB1+0 |  |  |  |  | ,,, | 343.5 |  | DFR | E | Done
174 | 27/8 | DA+0 |  |  |  |  | ,,, | 392 |  | DFR | E | Done
175 | 27/9 | DA+0 |  |  |  |  | ,,, | 381.1 |  | DFR | E
176 | 27/10 | DA+3 |  |  |  |  | ,,, | 366.3 |  | DFR | E
177 | 27/11 | DA+3 |  |  |  |  | ,,, | 420.1 |  | DRY | E | Done
178 | 27/12 | DA+3 |  |  |  |  | ,,, | 420.8 |  | Sandy | E | Done
179 | 28/0 | DB2+0 |  |  |  |  | ,,, | 406.6 |  | DFR | E | Done
180 | 28/1 | DA+0 |  |  |  |  | ,,, | 379.6 |  | DRY | E | Done
181 | 28/2 | DA+0 |  |  |  |  | ,,, | 385 |  | DFR | E | Done
182 | 28/3 | DA+0 |  |  |  |  | ,,, | 369 |  | DFR | E
183 | 28/4 | DA+0 |  |  |  |  | ,,, | 409 |  | Sandy | E
184 | 28/5 | DA+9 |  | 2 |  |  | ,2,, | 422 |  | Sandy | E | Done
185 | 28/6 | DA+6 | 1 | 4 | 3 |  | 1,4,3, | 370 |  | Sandy | E | Done
186 | 28/7 | DA+3 | 1 | 3 | 2 |  | 1,3,2, | 464 |  | Sandy | E | Done
187 | 28/8 | DA+3 |  |  | 5 | 3 | ,,5,3 | 375 |  | Sandy | E
188 | 29/0 | DB1+0 |  |  |  |  | ,,, | 465.5 |  | DRY | E | Done
189 | 29/1 | DA+3 |  |  |  |  | ,,, | 365.6 |  | DRY | E
190 | 29/2 | DA+3 |  |  |  |  | ,,, | 424 |  | DRY | E | Done
191 | 29/3 | DA+0 |  |  |  |  | ,,, | 399 |  | Sandy | E
192 | 29/4 | DA+6 |  |  |  |  | ,,, | 440 |  | DRY | E | Done
193 | 30/0 | DC1+0 |  |  |  |  | ,,, | 382.1 |  | DRY | E
194 | 30/1 | DA+0 | 2 |  |  |  | 2,,, | 388.9 |  | Sandy | E | Done
195 | 30/2 | DA+0 | 1 | 2 |  |  | 1,2,, | 445 |  | Sandy | E | Done
196 | 30/3 | DA+3 | 1 | 2 |  |  | 1,2,, | 395 |  | Sandy | E | Done
197 | 30/4 | DA+3 |  |  |  |  | ,,, | 387 |  | DRY | E
198 | 30/5 | DA+3 |  |  |  |  | ,,, | 442 |  | DRY | E | Done
199 | 30/6 | DA+0 |  |  |  |  | ,,, | 314 |  | DRY | E
200 | 31/0 | DB2+0 |  |  |  |  | ,,, | 347.4 |  | Sandy | E
201 | 31/1 | DA+0 |  |  |  |  | ,,, | 383.6 |  | DRY | E | Done
202 | 31/2 | DA+0 |  |  |  |  | ,,, | 366 |  | DRY | E | Done
203 | 32/0 | DC1+0 |  |  |  |  | ,,, | 332.9 |  | DRY | E | Done
204 | 32/1 | DA+3 |  |  |  |  | ,,, | 402.7 |  | Sandy | E | Done
205 | 32/2 | DA+3 |  |  |  |  | ,,, | 428.8 |  | DRY | E | Done
206 | 32/3 | DA+0 |  |  |  |  | ,,, | 410.9 |  | Sandy | E | Done
207 | 32/4 | DA+0 |  |  |  |  | ,,, | 381.1 |  | Sandy | E | Done
208 | 33/0 | DC1+0 | 1 |  |  |  | 1,,, | 451.5 |  | DRY | E | Done
209 | 33/1 | DA+0 |  | 1 | 1 |  | ,1,1, | 379.6 |  | DRY | E | Done
210 | 34/0 | DB2+0 |  |  |  |  | ,,, | 292.5 |  | DRY | E | Done
211 | 34/1 | DA+9 |  |  |  |  | ,,, | 432.6 |  | Sandy | E | Done
212 | 34/2 | DA+6 |  |  |  | 2 | ,,,2 | 407.5 |  | Sandy | E | Done
213 | 34/3 | DA+0 |  | 3 |  |  | ,3,, | 377 |  | Sandy | E | Done
214 | 34/4 | DA+0 |  | 3 | 1 |  | ,3,1, | 451.6 |  | Sandy | E
215 | 35/0 | DB2+6 | 2 |  |  |  | 2,,, | 379.3 |  | Sandy | E | Done
216 | 35/1 | DA+9 | 2 |  |  | 2 | 2,,,2 | 265.6 |  | Sandy | E | Done
217 | 35/2 | DB1+0 | 1 | 1 |  |  | 1,1,, | 492.4 |  | Sandy | E | Done
218 | 35/3 | DB1+6 | 1 |  |  |  | 1,,, | 522.2 |  | Sandy | E | Done
219 | 35/4 | DA+0 |  |  |  |  | ,,, | 418.9 |  | DRY | E | Done
220 | 35/5 | DA+0 |  |  | 4 | 4 | ,,4,4 | 421.7 |  | Sandy | E | Done
221 | 36/0 | DB2+0 |  |  |  |  | ,,, | 342.7 |  | Sandy | E | Done
222 | 36/1 | DA+3 |  |  |  |  | ,,, | 386.4 |  | Sandy | E | Done
223 | 36/2 | DA+0 | 1 | 1 |  |  | 1,1,, | 309.4 |  | Sandy | E | Done
224 | 36/3 | DA+0 |  | 2 |  |  | ,2,, | 357.8 |  | Sandy | E | Done
225 | 36/4 | DA+6 | 2 | 3 |  | 5 | 2,3,,5 | 480.4 |  | Sandy | E | Done
226 | 37/0 | DB2+0 |  |  |  | 1 | ,,,1 | 350.5 |  | Sandy | E
227 | 37/1 | DA+9 | 2 | 2 | 2 | 1 | 2,2,2,1 | 443.3 |  | Sandy | E
228 | 37/2 | DA+3 |  |  |  |  | ,,, | 356.7 |  | Sandy | E
229 | 37/3 | DA+0 |  |  |  |  | ,,, | 339.9 |  | Sandy | E
230 | 38/0 | DB2+6 |  |  |  |  | ,,, | 500.3 |  | Sandy | E | Done
231 | 38/1 | DA+0 |  |  |  |  | ,,, | 421.4 |  | Sandy | E
232 | 38/2 | DA+6 |  |  |  |  | ,,, | 419 |  | Sandy | E
233 | 38/3 | DA+9 | 2 | 2 | 2 | 2 | 2,2,2,2 | 420.3 |  | Sandy | E | Done
234 | 38/4 | DA+9 | 1 | 1 |  | 1 | 1,1,,1 | 414.9 |  | Sandy | E | Done
235 | 39/0 | DB2+6 |  |  |  |  | ,,, | 425.5 |  | Sandy | E | Done
236 | 39/1 | DA+0 |  |  |  |  | ,,, | 412.638 |  | Sandy | E | Done
237 | 40/0 | DC2+0 | 1 | 1 |  |  | 1,1,, | 322.61 |  | Sandy | E | Done
238 | 40/1 | DA+6 | 1 | 2 |  |  | 1,2,, | 396.2 |  | Sandy | E | Done
239 | 40/2 | DA+3 |  |  |  |  | ,,, | 425.8 |  | Sandy | E | Done
240 | 40/3 | DA+3 | 1 | 2 |  |  | 1,2,, | 401.7 |  | Sandy | E | Done
241 | 41/0 | DC1+6 | 3 | 1 |  | 1 | 3,1,,1 | 436.3 |  | Sandy | E | Done
242 | 41/1 | DB1+9 | 4 | 5 | 6 | 6 | 4,5,6,6 | 340.8 |  | Sandy | E | Done
243 | 41/2 | DA+0 |  |  | 1 | 1 | ,,1,1 | 447.8 |  | Sandy | E | Done
244 | 42/0 | DC1+0 | 1 |  |  | 2 | 1,,,2 | 382.3 |  | Sandy | E | Done
245 | 42/1 | DA+6 | 1 |  |  |  | 1,,, | 384.7 |  | Sandy | E | Done
246 | 42/2 | DA+6 |  |  | 1 | 3 | ,,1,3 | 407.4 |  | Sandy | E | Done
247 | 42/3 | DA+0 |  |  |  |  | ,,, | 414.2 |  | Sandy | E | Done
248 | 42/4 | DA+0 |  |  |  |  | ,,, | 256.4 |  | Sandy | E | Done
249 | 42/5 | DA+9 |  |  |  | 1 | ,,,1 | 403.8 |  | Sandy | E | Done
250 | 42/6 | DA+0 | 2 | 1 |  | 2 | 2,1,,2 | 396.7 |  | Sandy | E | Done
251 | 43/0 | DB1+0 |  |  |  |  | ,,, | 403.9 |  | Sandy | E | Done
252 | 43/1 | DA+3 |  |  | 3 | 3 | ,,3,3 | 346 |  | Sandy | E | Done
253 | 43/2 | DA+0 | 1 |  |  | 1 | 1,,,1 | 475.8 |  | Sandy | E | Done
254 | 43/3 | DA+0 |  | 1 |  |  | ,1,, | 363.7 |  | DRY | E | Done
255 | 43/4 | DA+3 | 1 | 1 |  |  | 1,1,, | 431.8 |  | Sandy | E | Done
256 | 43/5 | DA+3 |  |  |  |  | ,,, | 405.3 |  | DRY | E | Done
257 | 43/6 | DA+3 |  |  |  |  | ,,, | 427.8 |  | Sandy | E | Done
258 | 43/7 | DA+3 |  |  |  |  | ,,, | 389.8 |  | Sandy | E | Done
259 | 43/8 | DA+9 | 1 |  |  |  | 1,,, | 449.5 |  | Sandy | E
260 | 43/9 | DA+9 |  |  |  |  | ,,, | 388 |  | Sandy | E
261 | 43/10 | DA+3 | 3 | 3 |  |  | 3,3,, | 346.3 |  | Sandy | E
262 | 43/11 | DA+3 | 2 | 3 |  | 1 | 2,3,,1 | 444.8 |  | Sandy | E
263 | 44/0 | DB1+3 | 0 | 1 | 1 | 0 | 0,1,1,0 | 383.9 |  | Sandy | E | Done
264 | 44/1 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 384.3 |  | Sandy | E | Done
265 | 44/2 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 359 |  | Sandy | E | Done
266 | 44/3 | DA+0 | 2 | 0 | 0 | 1 | 2,0,0,1 | 334 |  | Sandy | E | Done
267 | 44/4 | DA+9 | 4 | 3 | 3 | 3 | 4,3,3,3 | 395 |  | Sandy | E | Done
268 | 44/5 | DA+9 | 1 | 3 | 0 | 0 | 1,3,0,0 | 355 |  | Sandy | E | Done
269 | 44/6 | DB1+3 | 1 | 0 | 0 | 1 | 1,0,0,1 | 485 |  | Sandy | E | Done
270 | 44/7 | DA+9 | 0 | 0 | 0 | 0 | 0,0,0,0 | 473 |  | Sandy | E | Done
271 | 44/8 | DCT+0 | 1 | 2 | 0 | 1 | 1,2,0,1 | 367 |  | Sandy | E
272 | 44/9 | DA+9 | 4 | 0 | 2 | 6 | 4,0,2,6 | 430 |  | Sandy | E | Done
273 | 44/10 | DB1+9 | 0 | 1 | 0 | 0 | 0,1,0,0 | 365 |  | Sandy | E
274 | 44/11 | DA+0 | 0 | 1 | 0 | 0 | 0,1,0,0 | 428 |  | Sandy | E | Done
275 | 45/0 | DC2+0 | 0 | 1 | 0 | 0 | 0,1,0,0 | 327.2 |  | Sandy | E | Done
276 | 45/1 | DA+9 | 0 | 0 | 6 | 6 | 0,0,6,6 | 294.92 |  | Sandy | E | Done
277 | 46/0 | DD60+25 | 0 | 6 | 6 | 2 | 0,6,6,2 | 406.54 |  | Sandy | E | Done
278 | 47/0 | DD60+25 | 5 | 5 | 5 | 5 | 5,5,5,5 | 199.08 |  | Sandy | E | Done
279 | 47/1 | DA+3 | 2 | 0 | 2 | 5 | 2,0,2,5 | 441.2 |  | Sandy | E | Done
280 | 47/2 | DA+9 | 0 | 0 | 0 | 0 | 0,0,0,0 | 365.93 |  | Sandy | E | Done
281 | 47/3 | DA+9 | 1 | 2 | 0 | 0 | 1,2,0,0 | 417.4 |  | Sandy | E | Done
282 | 47/4 | DA+3 |  |  |  |  | ,,, | 358.4 |  | Sandy | E | Done
283 | 47/5 | DA+0 | 0 | 1 | 0 | 0 | 0,1,0,0 | 461.2 |  | Sandy | E
284 | 47/6 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 377.3 |  | Sandy | E | Done
285 | 47/7 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 431.5 |  | Sandy | E | Done
286 | 47/8 | DA+0 | 1 | 0 | 0 | 0 | 1,0,0,0 | 398.8 |  | Sandy | E | Done
287 | 47/9 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 405.9 |  | Sandy | E | Done
288 | 47/10 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 433.7 |  | Sandy | E | Done
289 | 48/0 | DC2+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 386.2 |  | Sandy | E | Done
290 | 48/1 | DA+9 | 0 | 0 | 0 | 0 | 0,0,0,0 | 428.9 |  | Sandy | E | Done
291 | 49/0 | DD45+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 402.9 |  | Sandy | E | Done
292 | 49/1 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 379.1 |  | Sandy | E | Done
293 | 49/2 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 386.6 |  | Sandy | E | Done
294 | 49/3 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 390 |  | Sandy | E | Done
295 | 49/4 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 421.7 |  | Sandy | E | Done
296 | 49/5 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 396.6 |  | Sandy | E | Done
297 | 49/6 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 412.8 |  | Sandy | E | Done
298 | 49/7 | DA+0 | 0 | 3 | 2 | 2 | 0,3,2,2 | 340.2 |  | Sandy | E | Done
299 | 50/0 | DB2+0 | 0 | 0 | 0 | 1 | 0,0,0,1 | 500.2 |  | Sandy | E | Done
300 | 50/1 | DA+6 | 1 | 0 | 0 | 0 | 1,0,0,0 | 469.1 |  | Sandy | E | Done
301 | 50/2 | DA+9 | 2 | 2 | 2 | 2 | 2,2,2,2 | 367.1 |  | Sandy | E | Done
302 | 50/3 | DA+6 | 0 | 0 | 1 | 0 | 0,0,1,0 | 470.4 |  | Sandy | E | Done
303 | 50/4 | DA+9 | 3 | 3 | 4 | 3 | 3,3,4,3 | 354.8 |  | Sandy | E | Done
304 | 50/5 | DA+9 | 4 | 3 | 4 | 3 | 4,3,4,3 | 442.1 |  | Sandy | E | Done
305 | 50/6 | DA+9 | 3 | 4 | 3 | 3 | 3,4,3,3 | 364.4 |  | Sandy | E | Done
306 | 50/7 | DA+0 | 0 | 0 | 0 | 1 | 0,0,0,1 | 470.8 |  | Sandy | E | Done
307 | 50/8 | DA+9 | 0 | 0 | 0 | 0 | 0,0,0,0 | 345 |  | Sandy | E | Done
308 | 50/9 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 364.4 |  | Sandy | E | Done
309 | 50/10 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 394.6 |  | Sandy | E | Done
310 | 51/0 | DC2+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 401.4 |  | Sandy | E | Done
311 | 51/1 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 356.6 |  | Sandy | E | Done
312 | 51/2 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 307.1 |  | Sandy | E | Done
313 | 52/0 | DC2+0 | 0 | 0 | 3 | 3 | 0,0,3,3 | 385 |  | Sandy | E | Done
314 | 52/1 | DA+6 | 0 | 4 | 0 | 0 | 0,4,0,0 | 402 |  | Sandy | E | Done
315 | 52/2 | DA+6 | 0 | 0 | 0 | 3 | 0,0,0,3 | 402.6 |  | Sandy | E | Done
316 | 52/3 | DA+9 | 4 | 3 | 3 | 3 | 4,3,3,3 | 437 |  | Sandy | E
317 | 52/4 | DA+9 | 2 | 2 | 0 | 0 | 2,2,0,0 | 393.8 |  | Sandy | E | Done
318 | 52/5 | DA+9 | 0 | 0 | 0 | 1 | 0,0,0,1 | 447 |  | Sandy | E | Done
319 | 52/6 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 373 |  | Sandy | E | Done
320 | 52/7 | DA+3 | 0 | 3 | 1 | 0 | 0,3,1,0 | 406.8 |  | Sandy | E | Done
321 | 52/8 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 433 |  | Sandy | E | Done
322 | 52/9 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 399.7 |  | Sandy | E | Done
323 | 52/10 | DA+9 | 1 | 2 | 1 | 1 | 1,2,1,1 | 384.1 |  | Sandy | E | Done
324 | 53/0 | DB2+9 | 4 | 4 | 4 | 4 | 4,4,4,4 | 455.9 |  | Sandy | E | Done
325 | 53/1 | DA+9 | 4 | 4 | 4 | 4 | 4,4,4,4 | 433.2 |  | Sandy | E | Done
326 | 53/2 | DA+0 | 0 | 0 | 0 | 2 | 0,0,0,2 | 407.4 |  | Sandy | E | Done
327 | 53/3 | DA+6 | 0 | 4 | 1 | 0 | 0,4,1,0 | 394.5 |  | Sandy | E | Done
328 | 53/4 | DA+0 | 0 | 2 | 1 | 0 | 0,2,1,0 | 410.1 |  | Sandy | E | Done
329 | 53/5 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 428.1 |  | Sandy | E | Done
330 | 53/6 | DA+6 | 1 | 1 | 3 | 1 | 1,1,3,1 | 406.6 |  | Sandy | E | Done
331 | 53/7 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 411.3 |  | Sandy | E | Done
332 | 53/8 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 427.8 |  | Sandy | E
333 | 54/0 | DB1+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 371.3 |  | Sandy | E | Done
334 | 54/1 | DA+3 | 1 | 1 | 0 | 0 | 1,1,0,0 | 365.1 |  | Sandy | E
335 | 54/2 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 381 |  | Sandy | E | Done
336 | 54/3 | DA+6 | 0 | 2 | 0 | 0 | 0,2,0,0 | 417 |  | Sandy | E | Done
337 | 54/4 | DA+9 | 1 | 2 | 0 | 0 | 1,2,0,0 | 423.3 |  | Sandy | E | Done
338 | 54/5 | DA+9 | 1 | 3 | 3 | 1 | 1,3,3,1 | 401 |  | Sandy | E | Done
339 | 55/0 | DB1+6 | 0 | 1 | 1 | 0 | 0,1,1,0 | 424 |  | Sandy | E
340 | 55/1 | DA+0 |  |  |  |  | ,,, | 404.9 |  | WFR | E | Done
341 | 55/2 | DA+0 |  |  |  |  | ,,, | 343.1 |  | WFR | E
342 | 55/3 | DA+0 |  |  |  |  | ,,, | 357.7 |  | Sandy | E | Done
343 | 55/4 | DA+0 | 0 | 0 | 0 | 1 | 0,0,0,1 | 365.2 |  | Sandy | E | Done
344 | 55/5 | DA+0 | 0 | 0 | 1 | 3 | 0,0,1,3 | 350.1 |  | Sandy | E | Done
345 | 55/6 | DA+0 | 0 | 0 | 1 | 2 | 0,0,1,2 | 357.7 |  | Sandy | E | Done
346 | 55/7 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 337.8 |  | Sandy | E | Done
347 | 55/8 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 341.22 |  | Sandy | E | Done
348 | 56/0 | DD60+25 | 3 | 3 | 0 | 2 | 3,3,0,2 | 460.49 |  | Sandy | E
349 | 57/0 | DD60+25 | 0 | 0 | 0 | 0 | 0,0,0,0 | 219.76 |  | Sandy | E
350 | 57/1 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 461.1 |  | Sandy | E | Done
351 | 57/2 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 355.5 |  | DRY | E | Done
352 | 57/3 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 405.4 |  | DRY | E | Done
353 | 57/4 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 418.2 |  | Sandy | E | Done
354 | 57/5 | DA+3 | 0 | 0 | 0 | 1 | 0,0,0,1 | 416.8 |  | Sandy | E | Done
355 | 57/6 | DA+3 | 0 | 1 | 0 | 0 | 0,1,0,0 | 395 |  | Sandy | E | Done
356 | 57/7 | DA+3 |  |  |  |  | ,,, | 401.8 |  | DFR | E | Done
357 | 58/0 | DC1+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 433.9 |  | DFR | E | Done
358 | 59/0 | DC2+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 238.9 |  | DRY | E | Done
359 | 59/1 | DA+3 | 0 | 0 | 0 | 1 | 0,0,0,1 | 411.3 |  | DRY | E | Done
360 | 59/2 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 418.2 |  | DFR | E | Done
361 | 59/3 | DA+3 | 0 | 0 | 0 | 1 | 0,0,0,1 | 412.3 |  | DFR | E | Done
362 | 59/4 | DA+3 |  |  |  |  | ,,, | 421 |  | DFR | E | Done
363 | 59/5 | DA+3 |  |  |  |  | ,,, | 419.7 |  | DFR | E | Done
364 | 59/6 | DA+3 |  |  |  |  | ,,, | 419.1 |  | DFR | E | Done
365 | 59/7 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 408.8 |  | DRY | E | Done
366 | 59/8 | DB1+3 |  |  |  |  | ,,, | 426.9 |  | DRY | E | Done
367 | 59/9 | DA+3 |  |  |  |  | ,,, | 434.7 |  | DRY | E | Done
368 | 59/10 | DA+0 |  |  |  |  | ,,, | 400.8 |  | DRY | E | Done
369 | 59/11 | DA+6 | 0 | 0 | 2 | 0 | 0,0,2,0 | 436.3 |  | DFR | E | Done
370 | 59/12 | DA+6 |  |  |  |  | ,,, | 393.1 |  | DFR | E | Done
371 | 59/13 | DA+3 |  |  |  |  | ,,, | 447.4 |  | DRY | E | Done
372 | 59/14 | DA+6 |  |  |  |  | ,,, | 391.1 |  | DRY | E | Done
373 | 59/15 | DA+6 |  |  |  |  | ,,, | 448.6 |  | DRY | E | Done
374 | 59/16 | DA+9 |  |  |  |  | ,,, | 388 |  | Dry | E | Done
375 | 60/0 | DC1+0 |  |  |  |  | ,,, | 438 |  | DRY | E | Done
376 | 60/1 | DA+6 |  |  |  |  | ,,, | 413.8 |  | DRY | E | Done
377 | 60/2 | DA+3 | 2 | 2 | 0 | 0 | 2,2,0,0 | 424.2 |  | DFR | E | Done
378 | 60/3 | DA+3 |  |  |  |  | ,,, | 414.5 |  | DFR | E | Done
379 | 60/4 | DA+3 |  |  |  |  | ,,, | 425.6 |  | DFR | E | Done
380 | 60/5 | DA+3 |  |  |  |  | ,,, | 412.3 |  | DRY | E | Done
381 | 60/6 | DA+0 |  |  |  |  | ,,, | 374.1 |  | DRY | E | Done
382 | 60/7 | DA+3 |  |  |  |  | ,,, | 410.1 |  | DRY | E | Done
383 | 60/8 | DA+0 |  |  |  |  | ,,, | 400.4 |  | DRY | E | Done
384 | 60/9 | DA+3 |  |  |  |  | ,,, | 409.2 |  | DRY | E | Done
385 | 60/10 | DA+0 |  |  |  |  | ,,, | 401 |  | DFR | E | Done
386 | 60/11 | DA+3 |  |  |  |  | ,,, | 394.5 |  | DRY | E | Done
387 | 61/0 | DB2+0 |  |  |  |  | ,,, | 397.9 |  | DRY | E | Done
388 | 61/1 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 405.7 |  | DFR | E | Done
389 | 61/2 | DA+6 |  |  |  |  | ,,, | 433.2 |  | DFR | E | Done
390 | 61/3 | DA+6 |  |  |  |  | ,,, | 400.9 |  | DRY | E | Done
391 | 61/4 | DA+3 |  |  |  |  | ,,, | 427 |  | DRY | E | Done
392 | 61/5 | DA+3 |  |  |  |  | ,,, | 413.9 |  | DRY | E | Done
393 | 61/6 | DA+3 |  |  |  |  | ,,, | 426.4 |  | DRY | E | Done
394 | 61/7 | DA+9 | 0 | 0 | 0 | 1 | 0,0,0,1 | 411.5 |  | Dry | E | Done
395 | 61/8 | DA+6 | 1 | 2 | 1 | 0 | 1,2,1,0 | 376.3 |  | DRY | E | Done
396 | 61/9 | DA+0 |  |  |  |  | ,,, | 433.4 |  | Dry | E | Done
397 | 61/10 | DA+9 |  |  |  |  | ,,, | 405.6 |  | DRY | E | Done
398 | 62/0 | DB2+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 434.3 |  | DRY | E | Done
399 | 62/1 | DA+3 | 0 | 0 | 1 | 2 | 0,0,1,2 | 418 |  | Sandy | E | Done
400 | 62/2 | DA+3 | 0 | 1 | 0 | 0 | 0,1,0,0 | 386 |  | DRY | E | Done
401 | 62/3 | DA+0 |  |  |  |  | ,,, | 400 |  | DRY | E | Done
402 | 62/4 | DA+3 |  |  |  |  | ,,, | 401 |  | DRY | E | Done
403 | 62/5 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 403 |  | DRY | E | Done
404 | 62/6 | DA+3 |  |  |  |  | ,,, | 404 |  | DRY | E | Done
405 | 62/7 | DA+3 |  |  |  |  | ,,, | 423 |  | DRY | E | Done
406 | 62/8 | DA+0 |  |  |  |  | ,,, | 409 |  | DFR | E | Done
407 | 62/9 | DA+3 |  |  |  |  | ,,, | 409 |  | DFR | E | Done
408 | 62/10 | DA+0 |  |  |  |  | ,,, | 411 |  | DFR | E | Done
409 | 62/11 | DA+3 |  |  |  |  | ,,, | 413 |  | DRY | E | Done
410 | 63/0 | DC1+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 386.1 |  | DFR | E | Done
411 | 63/1 | DA+3 |  |  |  |  | ,,, | 400 |  | DFR | E | Done
412 | 63/2 | DA+0 |  |  |  |  | ,,, | 416 |  | DFR | E | Done
413 | 63/3 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 411 |  | DFR | E | Done
414 | 63/4 | DA+0 |  |  |  |  | ,,, | 399 |  | DRY | E | Done
415 | 63/5 | DA+3 |  |  |  |  | ,,, | 413 |  | DFR | E | Done
416 | 63/6 | DA+3 |  |  |  |  | ,,, | 426 |  | DRY | E | Done
417 | 63/7 | DA+3 |  |  |  |  | ,,, | 413 |  | DRY | E | Done
418 | 63/8 | DA+3 |  |  |  |  | ,,, | 425 |  | DRY | E | Done
419 | 64/0 | DB2+0 |  |  |  |  | ,,, | 408.3 |  | DRY | E | Done
420 | 64/1 | DA+0 |  |  |  |  | ,,, | 375.1 |  | DRY | E | Done
421 | 64/2 | DA+3 |  |  |  |  | ,,, | 408.7 |  | DRY | E | Done
422 | 64/3 | DA+0 |  |  |  |  | ,,, | 410.7 |  | DRY | E | Done
423 | 64/4 | DA+3 |  |  |  |  | ,,, | 408.2 |  | DRY | E | Done
424 | 64/5 | DA+3 |  |  |  |  | ,,, | 426.2 |  | DRY | E | Done
425 | 64/6 | DA+0 |  |  |  |  | ,,, | 407.7 |  | DRY | E | Done
426 | 64/7 | DA+3 |  |  |  |  | ,,, | 401.6 |  | DRY | E | Done
427 | 64/8 | DA+3 |  |  |  |  | ,,, | 425.5 |  | DRY | E | Done
428 | 64/9 | DA+3 |  |  |  |  | ,,, | 414.4 |  | DRY | E | Done
429 | 64/10 | DA+3 |  |  |  |  | ,,, | 410.6 |  | DRY | E | Done
430 | 64/11 | DA+3 |  |  |  |  | ,,, | 428.4 |  | DRY | E | Done
431 | 65/0 | DB1+0 |  |  |  |  | ,,, | 400.6 |  | DRY | E | Done
432 | 65/1 | DA+0 |  |  |  |  | ,,, | 395.4 |  | DRY | E | Done
433 | 65/2 | DA+0 |  |  |  |  | ,,, | 393.7 |  | DRY | E | Done
434 | 65/3 | DA+3 |  |  |  |  | ,,, | 403.7 |  | DRY | E | Done
435 | 65/4 | DA+0 |  |  |  |  | ,,, | 402.9 |  | DRY | E | Done
436 | 65/5 | DA+0 |  |  |  |  | ,,, | 376.4 |  | DRY | E | Done
437 | 65/6 | DA+0 |  |  |  |  | ,,, | 389.2 |  | DRY | E | Done
438 | 65/7 | DA+0 |  |  |  |  | ,,, | 397.6 |  | DRY | E | Done
439 | 65/8 | DA+0 |  |  |  |  | ,,, | 394.3 |  | DRY | E | Done
440 | 65/9 | DA+0 |  |  |  |  | ,,, | 389 |  | DRY | E | Done
441 | 65/10 | DA+0 |  |  |  |  | ,,, | 379.1 |  | DRY | E | Done
442 | 65/11 | DA+0 |  |  |  |  | ,,, | 387.6 |  | DRY | E | Done
443 | 66/0 | DC2+6 |  |  |  |  | ,,, | 426.9 |  | DRY | E | Done
444 | 67/0 | DC1+9 |  |  |  |  | ,,, | 207.8 |  | DRY | E | Done
445 | 67/1 | DA+0 |  |  |  |  | ,,, | 347.1 |  | DRY | E | Done
446 | 67/2 | DA+0 |  |  |  |  | ,,, | 344.9 |  | DRY | E | Done
447 | 68/0 | DD45+0 |  |  |  |  | ,,, | 369.2 |  | DRY | E | Done
448 | 69/0 | DB2+0 |  |  |  |  | ,,, | 200.9 |  | DFR | E | Done
449 | 69/1 | DA+3 |  |  |  |  | ,,, | 374.1 |  | DRY | E | Done
450 | 70/0 | DC1+0 |  |  |  |  | ,,, | 394.9 |  | DRY | E | Done
451 | 70/1 | DA+3 |  |  |  |  | ,,, | 388.4 |  | DRY | E | Done
452 | 70/2 | DA+3 |  |  |  |  | ,,, | 418.9 |  | DRY | E | Done
453 | 70/3 | DA+3 |  |  |  |  | ,,, | 418.6 |  | DRY | E | Done
454 | 70/4 | DA+3 |  |  |  |  | ,,, | 414 |  | DRY | E | Done
455 | 70/5 | DA+3 |  |  |  |  | ,,, | 419.6 |  | DRY | E | Done
456 | 70/6 | DA+3 |  |  |  |  | ,,, | 420.3 |  | DRY | E | Done
457 | 70/7 | DA+3 |  |  |  |  | ,,, | 419.6 |  | DRY | E | Done
458 | 70/8 | DA+3 |  |  |  |  | ,,, | 418.2 |  | DRY | E | Done
459 | 70/9 | DA+3 |  |  |  |  | ,,, | 414.1 |  | DRY | E | Done
460 | 70/10 | DA+3 |  |  |  |  | ,,, | 406.1 |  | DRY | E | Done
461 | 70/11 | DA+3 |  |  |  |  | ,,, | 408.6 |  | DRY | E | Done
462 | 71/0 | DB2+3 |  |  |  |  | ,,, | 420.4 |  | DRY | E | Done
463 | 71/1 | DA+3 |  |  |  |  | ,,, | 398.6 |  | DRY | E | Done
464 | 71/2 | DA+3 |  |  |  |  | ,,, | 414.3 |  | DRY | E | Done
465 | 71/3 | DA+6 |  |  |  |  | ,,, | 413 |  | DRY | E | Done
466 | 71/4 | DA+3 |  |  |  |  | ,,, | 367.7 |  | DRY | E | Done
467 | 71/5 | DA+3 |  |  |  |  | ,,, | 429.4 |  | DRY | E | Done
468 | 71/6 | DA+0 |  |  |  |  | ,,, | 408 |  | DRY | E | Done
469 | 71/7 | DA+3 |  |  |  |  | ,,, | 404.9 |  | DRY | E | Done
470 | 71/8 | DA+3 |  |  |  |  | ,,, | 431.6 |  | DRY | E | Done
471 | 72/0 | DB2+3 |  |  |  |  | ,,, | 408.4 |  | DRY | E | Done
472 | 72/1 | DA+3 |  |  |  |  | ,,, | 435.3 |  | DRY | E | Done
473 | 72/2 | DA+0 |  |  |  |  | ,,, | 403.9 |  | DRY | E | Done
474 | 72/3 | DA+3 |  |  |  |  | ,,, | 389.2 |  | DRY | E | Done
475 | 73/0 | DB2+0 |  |  |  |  | ,,, | 400.1 |  | DRY | E | Done
476 | 73/1 | DA+0 |  |  |  |  | ,,, | 383.3 |  | DRY | E | Done
477 | 73/2 | DA+0 |  |  |  |  | ,,, | 379 |  | DRY | E | Done
478 | 73/3 | DA+0 |  |  |  |  | ,,, | 381.2 |  | DRY | E | Done
479 | 73/4 | DA+0 |  |  |  |  | ,,, | 384.7 |  | DRY | E | Done
480 | 73/5 | DA+0 |  |  |  |  | ,,, | 368.8 |  | DRY | E | Done
481 | 73/6 | DA+0 |  |  |  |  | ,,, | 365.5 |  | DRY | E | Done
482 | 73/7 | DA+0 |  |  |  |  | ,,, | 392.4 |  | DRY | E | Done
483 | 73/8 | DA+3 |  |  |  |  | ,,, | 374.9 |  | DRY | E | Done
484 | 73/9 | DA+0 |  |  |  |  | ,,, | 379.5 |  | DRY | E | Done
485 | 74/0 | DB2+0 |  |  |  |  | ,,, | 378.9 |  | Sandy | E | Done
Note on F112: Raghav Ranjan: in approved survey 1 mrc in pit C & D. but actual no any RC casted
Note on G372: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AS PER APPROVED CHECK SURVEY, 1 M RC IN PIT A BUT SAME WAS REVISED (PIT d IN PLACE OF PIT A) AS PER INSTRUCTION BY SACHCHIDANAND ON DATED 28.08.24

## Benching F
Progress Summary'!A1 | [7 empty] | Total | 35308.5487 |  | 22312.4407 |  | 24183.155
[8 empty] | No of Locs | 215 |  | 175 |  | 170 | 45
RC, Benching & Revetment Locations
Sr. No. | Loc No. | Tower Type | CP Position Up/Down | Raised Chimney | Chimney Extension |  |  |  | Submitted Benching Volume (Cum) |  | Approved Benching Volume (Cum) during check survey |  | Approved Benching Volume (Cum) after execution
[5 empty] | A | B | C | D | Cutting | Filling | Cutting | Filling | Approved Benching volume in JMC | Soil Type
1 | 1A/0 | DD60+0 |  | 280.663 |  |  |  | 1 | 396.753 |  | 396.753 |  | 396.75 | DRY
2 | 1A/2 | DA+0 |  | 289.355 |  | 1 | 1 |  | 135.475 |  | 126.578 |  | 126.578 | DRY
3 | 1A/4 | DA+3 |  | 279.611 |  |  | 1 |  | 96.198 |  | 84.47 |  | 96.198 | DFR
4 | 1A/5 | DA+0 |  | 283.369 | 1 | 1 |  |  | 90.818 |  | 90.818
5 | 1A/6 | DA+0 |  | 285.088 | 1 |  |  | 1 | 115.601 |  | 95.447
6 | 1A/7 | DA+3 |  | 279.351 |  | 1 |  |  | 16.618 |  | 15.102 |  | 16.618 | Sandy
7 | 2/2 | DA+3 |  | 286.123 |  |  |  | 1 | 32.393 |  | 32.393 |  | 32.393 | Sandy
8 | 2/3 | DA+3 |  | 291.649 | 1 |  | 1 | 1 | 6.352 |  | 6.352 |  | 6.352 | Sandy
9 | 2/5 | DA+3 | -0.3 | 295.847 |  |  | 1 | 1 | 37.105 |  | 37.105 |  | 37.105 | Sandy
10 | 2/6 | DA+3 |  | 295.748 |  |  |  | 1 | 183.868 |  | 183.868
11 | 5/0 | DB1+9 |  | 276.367 | 5 | 5 | 5 | 5
12 | 6/0 | DB2+9 |  | 278.864 | 5 | 5 | 5 | 5
13 | 6/2 | DA+0 |  | 285.435 |  |  |  |  | 62.716 |  | 62.716
14 | 7/0 | DB1+0 |  | 285.258 | 2 | 3 | 3 | 2 | 38.395 |  | 38.395 |  | 38.395 | Sandy
15 | 8/1 | DA+3 |  | 277.532 |  |  |  |  | 95.017 |  | 95.017 |  | 95.017 | Dry
16 | 8/5 | DA+3 |  | 278.292 |  |  |  | 1 | 36.524 |  | 36.524 |  | 36.524 | Dry
17 | 8/11 | DA+0 | 0.1 | 258.784
18 | 10/18 | DA+3 | 0.2 | 263.543
19 | 10/22 | DA+0 | -0.3 | 267.946 | 1 |  |  | 3
20 | 10/23 | DA+0 | -0.3 | 274.896 |  | 2
21 | 11/0 | DB1+0 | -0.3 | 267.684 | 1 | 4 |  | 3
22 | 11/2 | DA+0 |  | 260.632 | 2 | 1
23 | 11/3 | DA+0 | -0.3 | 244.31 |  |  |  | 1
24 | 11A/8 | DA+6 |  | 276.713 |  | 2 | 4 | 1 | 21.332 |  | 21.332 |  | 21.331 | Sandy
25 | 13/3 | DA+3 |  | 259.023 |  |  | 2 | 4 | 263.579 |  | 263.579 |  | 263.579 | DRY
26 | 15/1 | DA+3 | 0.1 | 257.553
27 | 16/2 | DA+0 |  | 231.584 | 1 |  |  | 1 | 103.375 |  | 103.375 |  | 103.375 | DRY
28 | 16/4 | DA+0 |  | 230.932 |  | 1 |  |  | 111.857 |  | 111.857 |  | 111.857 | DRY
29 | 17/0 | DB2+3 |  | 231.525 |  |  |  | 1 | 203.454 |  | 203.454 |  | 203.454 | DRY
30 | 21/4 | DA+3 | -0.17 | 219.398 |  | 1 | 2 | 1 | 32.563 |  | 32.563 |  | 32.563 | Sandy
31 | 22/2 | DA+6 |  | 221.472 |  |  |  | 2 | 150.696 |  | 150.696 |  | 198.696 | Sandy
32 | 22/3 | DA+9 | -0.37 | 229.546 |  |  |  | 1 | 156.167 |  | 156.167 |  | 156.167 | Sandy
33 | 22/5 | DA+9 |  | 237.504 | 2 | 2 | 2 | 2
34 | 22/6 | DA+0 |  | 228.106 |  |  |  | 1 | 134.906 |  | 134.906 |  | 134.906 | Sandy
35 | 22/7 | DA+0 |  | 230.791 |  | 1 |  | 1 | 163.818 |  | 163.818 |  | 163.818 | DRY
36 | 22/8 | DB1+0 | -0.25 | 238.053 |  | 2 | 1 | 1 | 42.317 |  | 42.317 |  | 42.317 | Sandy
37 | 22/10 | DA+6 |  | 226.251 | 1 | 2 |  |  | 141.305 |  | 141.305
38 | 22/11 | DA+6 | -0.2 | 219.64 |  | 2 |  |  | 115.216 |  | 115.216
39 | 22/12 | DA+3 | -0.2 | 219.348 | 1 | 2 |  |  | 273.42 |  | 273.42 |  | 322.43 | Sandy
40 | 22/13 | DA+6 | -0.2 | 228.631 |  |  | 1 |  | 156.896 |  | 156.896 |  | 156.896 | Sandy
41 | 23/0 | DD45+3 |  | 234.317 | 2 | 2 | 2 | 2
42 | 24/0 | DD45+3 |  | 216.73 | 2 | 2 | 2 | 2
43 | 25/3 | DA+0 | -0.12 | 218.505 | 1 | 2 |  | 2 | 66.405 |  | 66.405 |  | 66.405 | Sandy
44 | 25/4 | DA+0 | -0.15 | 214.763 | 1 | 1 |  | 1 | 28.422 |  | 28.422 |  | 28.422 | Sandy
45 | 26/4 | DA+6 |  | 213.407 | 1 |  |  |  | 120.137 |  | 120.137 |  | 120.137 | Sandy
46 | 26/5 | DA+6 |  | 221.414 | 1 | 1 |  |  | 81.488 |  | 81.488 |  | 81.488 | Sandy
47 | 26/6 | DA+6 | 0.6 | 211.524 |  | 1 | 1 |  | 254.213 |  | 254.213 |  | 254.213 | Sandy
48 | 28/5 | DA+9 | -0.18 | 214.138 |  | 2 |  |  | 281.983 |  | 281.983 |  | 359.86 | Sandy
49 | 28/6 | DA+6 |  | 215.881 | 1 | 4 | 3 |  | 148.097 |  | 148.097 |  | 148.097 | Sandy
50 | 28/7 | DA+3 | +0.40 | 205.536 | 1 | 3 | 2 |  | 51.177 |  | 51.177 |  | 51.177 | Sandy
51 | 28/8 | DA+3 | +0.20 | 210.955 |  |  | 5 | 3 | 89.36 |  | 89.36 |  | 172.933 | Sandy
52 | 30/1 | DA+0 | +0.29 | 207.56 | 2 |  |  |  | 25.504 |  | 25.504 |  | 25.504 | Sandy
53 | 30/2 | DA+0 |  | 202.695 | 1 | 2 |  |  | 263.44 |  | 263.44 |  | 263.44 | Sandy
54 | 30/3 | DA+3 |  | 197.067 | 1 | 2 |  |  | 59.056 |  | 59.056 |  | 59.056 | Sandy
55 | 30/5 | DA+3 | [10 empty] | 478.121 | Dry
56 | 31/0 | DB2+0 | -0.7 | 209.344 |  |  |  |  | 120.033 |  | 120.033
57 | 33/0 | DC1+0 | -0.25 | 227.212 | 1 |  |  |  | 119.762 |  | 119.762 |  | 182.96 | Sandy
58 | 33/1 | DA+0 | -0.5 | 241.549 |  | 1 | 1 |  | 182.96 |  | 182.96 |  | 182.96 | Dry
59 | 34/0 | DB2+0 |  | 229.094 |  |  |  |  | 55.9616 |  | 55.9616
60 | 34/2 | DA+6 |  | 234.416 |  |  |  | 2 | 172.507 |  | 172.507
61 | 34/3 | DA+0 |  | 222.158 |  | 3 |  |  | 232.822 |  | 232.822
62 | 34/4 | DA+0 |  | 191.038 |  | 3 | 1 |  | 113.6503 |  | 113.6503
63 | 35/0 | DB2+6 |  | 190.847 | 2 |  |  |  | 163.1337 |  | 163.1337 |  | 163.134 | Sandy
64 | 35/1 | DA+9 |  | 184.479 | 2 |  |  | 2 | 355.4292 |  | 355.4292 |  | 284.41 | Sandy
65 | 35/2 | DB1+0 |  | 196.532 | 1 | 1 |  |  | 44.5475 |  | 44.5475
66 | 35/3 | DB1+6 | +1.0 | 211.007 | 1 |  |  |  | 50.2817 |  | 50.2817 |  | 50.28 | Sandy
67 | 35/5 | DA+0 |  | 192.578 |  |  | 4 | 4 | 625.888 |  | 625.888
68 | 36/2 | DA+0 |  | 185.467 | 1 | 1 |  |  | 83.5731 |  | 83.5731 |  | 64.595 | Sandy
69 | 36/3 | DA+0 |  | 196.493 |  | 2 |  |  | 102.3249 |  | 102.3249 |  | 88.813 | Sandy
70 | 36/4 | DA+6 |  | 216.948 | 2 | 3 |  | 5 | 138.429 |  | 138.429 |  | 93.659 | Sandy
71 | 37/0 | DB2+0 |  | 232.205 |  |  |  | 1 | 162.7886 |  | 162.7886 |  | 159.767 | Sandy
72 | 37/1 | DA+9 | +1.0 | 223.469 | 2 | 2 | 2 | 1 | 94.895 |  | 94.895 |  | 22.5 | Sandy
73 | 37/2 | DA+3 |  | 217.775 |  |  |  |  | 172.4831 |  | 172.4831 |  | 132.116 | Sandy
74 | 37/3 | DA+0 | +1.0 | 218.259 |  |  |  |  | 283.6687 |  | 283.6687 |  | 283.669 | Sandy
75 | 38/0 | DB2+6 |  | 183.041 |  |  |  |  | 63.3033 |  | 63.3033
76 | 38/3 | DA+9 | +1.0 | 195.915 | 2 | 2 | 2 | 2 | 15.318 |  | 15.318 |  | 15.318 | Sandy
77 | 38/4 | DA+9 | +1.0 | 188.108 | 1 | 1 |  | 1 | 128.046 |  | 128.046 |  | 128.046 | Sandy
78 | 40/0 | DC1+0 |  | 189.11 | 1 | 1 |  |  | 91.75 |  | 83.997 |  | 83.997 | Sandy
79 | 40/1 | DA+6 |  | 189.83 | 1 | 2 |  |  | 153.267 |  | 51.543 |  | 51.543 | Sandy
80 | 40/2 | DA+3 |  | 192.04 |  |  |  |  | 48.633 |  | 34.461 |  | 34.4 | Sandy
81 | 40/3 | DA+3 |  | 200.906 | 1 | 2 |  |  | 233.433 |  | 139.125 |  | 139.125 | Sandy
82 | 41/0 | DC1+6 |  | 220.24 | 3 | 1 |  | 1 | 249.833 |  | 139.683 |  | 139.683 | Sandy
83 | 41/1 | DB1+9 |  | 193.1 | 4 | 5 | 6 | 6 | 120.747 |  | 45.165 |  | 918.667 | Sandy
84 | 41/2 | DA+0 |  | 187.77 |  |  | 1 | 1 | 1170.806 |  | 1139.792 |  | 1875.83 | Sandy
85 | 42/0 | DC1+0 |  | 189.212 | 1 |  |  | 2 | 339.457 |  | 328.874 |  | 329.325 | Sandy
86 | 42/1 | DA+6 |  | 200.55 | 1 |  |  |  | 127.8 |  | 83.2 |  | 78.56 | Sandy
87 | 42/2 | DA+6 |  | 189.49 |  |  | 1 | 3 | 91.933 |  | 56.323 |  | 39.17 | Sandy
88 | 42/3 | DA+0 |  | 184.13 |  |  |  |  | 9.463 |  | 3.72 |  | 3.72 | Sandy
89 | 42/4 | DA+0 |  | 184.34 |  |  |  |  | 136.417 |  | 99.463
90 | 42/5 | DA+9 |  | 188.05 |  |  |  | 1 | 106.4 |  | 49.975 |  | 18.096 | Dry
91 | 42/6 | DA+0 |  | 214.42 | 2 | 1 |  | 2 | 144.417 |  | 85.947 |  | 80.2 | Sandy
92 | 43/0 | DB1+0 |  | 210.52 |  |  |  |  | 68.726 |  | 53.162 |  | 33.44 | Sandy
93 | 43/1 | DA+3 |  | 203.87 |  |  | 3 | 3 | 199.917 |  | 73.957 |  | 73.84 | Sandy
94 | 43/2 | DA+0 |  | 185.92 | 1 |  |  | 1 | 189.737 |  | 89.999 |  | 66.4 | Sandy
95 | 43/3 | DA+0 |  | 187.1 |  | 1 |  |  | 275.117 |  | 183.088
96 | 43/4 | DA+3 |  | 191.67 | 1 | 1 |  |  | 108.9 |  | 38.999 |  | 102.72 | Sandy
97 | 43/5 | DA+3 |  | 184 |  |  |  |  | 35.95 |  | 18.096 |  | 18.096 | Sandy
98 | 43/6 | DA+3 |  | 185.22 |  |  |  |  | 17.8 |  | 7.552 |  | 7.552 | Sandy
99 | 43/7 | DA+3 | +0.20 | 184.11 |  |  |  |  | 46.75 |  | 26.32 |  | 26.08 | Sandy
100 | 43/8 | DA+9 |  | 192.68 | 1 |  |  |  | 120.65 |  | 100.624 |  | 104 | Sandy
101 | 43/9 | DA+9 |  | 201.66 |  |  |  |  | 61.583 |  | 42.336 |  | 24.16 | Sandy
102 | 43/10 | DA+3 |  | 219.93 | 3 | 3 |  |  | 70.8 |  | 24.393 |  | 24.393 | Sandy
103 | 43/11 | DA+3 |  | 216.7 | 2 | 3 |  | 1 | 125.717 |  | 24.813 |  | 213.4 | Sandy
104 | 44/0 | DB1+3 |  | 198.375 |  | 1 | 1 |  | 227.336 |  | 145.45
105 | 44/1 | DA+0 |  |  | 0 | 0 | 1 | 0 | 516.62 |  |  |  | 134.696 | Sandy
106 | 44/2 | DA+0 |  |  | 0 | 0 | 0 | 0 | 145.7 |  |  |  | 97.248 | Sandy
107 | 44/3 | DA+0 |  |  | 2 | 0 | 0 | 1 | 35.453 |  |  |  | 5.64 | Sandy
108 | 44/4 | DA+9 | 3.3 | 3 | 4 | 3 | 3 | 3 | 62.367 |  |  |  | 10.487 | Sandy
109 | 44/5 | DA+9 |  |  | 1 | 3 | 0 | 0 | 476.6 |  |  |  | 623.445 | Sandy
110 | 44/6 | DB1+3 |  |  | 1 | 0 | 0 | 1 | 263.667 |  |  |  | 197.423 | Sandy
111 | 44/7 | DA+9 |  |  | 0 | 0 | 0 | 0 | 107.267 |  |  |  | 73.68 | Sandy
112 | 44/8 | DC1+0 |  |  | 1 | 2 | 0 | 1 | 114.075 |  |  |  | 79.401 | Sandy
113 | 44/9 | DA+9 | 3 |  | 4 | 0 | 2 | 6 | 218.923 |  |  |  | 101.028 | Sandy
114 | 44/10 | DA+9 |  |  | 0 | 1 | 0 | 0 | 68.233 |  |  |  | 16.058 | Sandy
115 | 44/11 | DA+0 |  |  | 0 | 1 | 0 | 0 | 148.233 |  |  |  | 67.987 | Sandy
116 | 45/0 | DC2+0 |  |  | 0 | 1 | 0 | 0 | 104.47 |  |  |  | 47.558 | Sandy
117 | 45/1 | DA+0 |  |  | 0 | 0 | 1 | 2 | 329.483
118 | 46/0 | DD60+18 | 3 |  | 0 | 4 | 4 | 0 | 773.08 |  |  |  | 428.908 | Sandy
119 | 47/0 | DD60+18 |  | 2 | 3 | 2 | 2 | 2 | 333.585 |  |  |  | 262.43 | Sandy
120 | 47/1 | DA+6 |  | 1 | 1 | 1 | 2 | 2 | 334.445 |  | 183.244 |  | 653.343 | Sandy
121 | 47/2 | DA+9 |  |  | 0 | 0 | 0 | 0 | 35.008 |  | 14.894 |  | 14.894 | Sandy
122 | 47/3 | DA+9 |  |  | 1 | 2 | 0 | 0 | 351.248 |  | 198.462 |  | 198.051 | Sandy
123 | 47/4 | DA+3
124 | 47/5 | DA+0 |  |  | 0 | 1 | 0 | 0 | 151.406 |  | 50.19 |  | 50.19 | Sandy
125 | 47/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 214.683 |  | 105.461 |  | 105.295 | Sandy
126 | 47/7 | DA+3 |  |  | 0 | 0 | 0 | 0 | 146.833 |  | 85.356 |  | 83.13 | Sandy
127 | 47/8 | DA+0 |  |  | 1 | 0 | 0 | 0 | 186.171 |  | 58.541 |  | 57.389 | Sandy
128 | 47/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 36.917 |  | 21.243 |  | 21.243 | Sandy
129 | 47/10 | DA+6 |  |  | 0 | 0 | 0 | 0 | 105.1 |  | 44.208 |  | 44.128 | Sandy
130 | 48/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 271.371 |  | 121.376 |  | 121.152 | Sandy
131 | 48/1 | DA+9 |  |  | 0 | 0 | 0 | 0 | 83.933 |  | 43.92 |  | 42.432 | Sandy
132 | 49/1 | DA+0 |  |  | 0 | 0 | 0 | 0 | 28.5 |  | 20.37 |  | 20.37 | Sandy
133 | 49/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 237.2 |  | 152.093 |  | 151.986 | Sandy
134 | 49/3 | DA+3 |  |  | 0 | 0 | 0 | 0 | 130.95 |  | 59.392 |  | 59.168 | Sandy
135 | 49/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 52.95 |  | 27.468 |  | 27.342 | Sandy
136 | 49/5 | DA+3 | 0.1 |  | 0 | 0 | 0 | 0 | 68.133 |  | 33.446 |  | 33.173 | Sandy
137 | 49/6 | DA+0 | 0.1 |  | 0 | 0 | 0 | 0 | 29.783 |  | 10.948 |  | 10.948 | Sandy
138 | 49/7 | DA+3 |  |  | 0 | 3 | 2 | 2 | 190.733 |  | 89.935 |  | 92.01 | Sandy
139 | 50/0 | DB2+0 |  |  | 0 | 0 | 0 | 1 | 29.469 |  | 6.775 |  | 6.775 | Sandy
140 | 50/1 | DA+6 |  |  | 1 | 0 | 0 | 0 | 258.417 |  | 126.731 |  | 126.619 | Sandy
141 | 50/2 | DA+9 |  | 2 | 2 | 2 | 2 | 2 | 109.183 |  | 50.596 |  | 50.428 | Sandy
142 | 50/3 | DA+6 |  |  | 0 | 0 | 1 | 0 | 82.817 |  | 40.792 |  | 40.792 | Sandy
143 | 50/4 | DA+9 |  | 3 | 3 | 3 | 4 | 3 | 90.133 |  | 31.88 |  | 31.61 | Sandy
144 | 50/5 | DA+9 |  | 3 | 4 | 3 | 4 | 3 | 82.717 |  | 13.972 |  | 13.972 | Sandy
145 | 50/6 | DA+9 |  | 3 | 3 | 4 | 3 | 3 | 266.417 |  | 133.278 |  | 133.022 | Sandy
146 | 50/7 | DA+0 |  |  | 0 | 0 | 0 | 1 | 58.15 |  | 20.044 |  | 20.044 | Sandy
147 | 50/8 | DA+9 |  |  | 0 | 0 | 0 | 0 | 379.65 |  | 287.607 |  | 287.114 | Sandy
148 | 50/9 | DA+0 |  |  | 0 | 0 | 1 | 0 | 551.811 |  | 283.026
149 | 50/10 | DA+0 |  |  | 0 | 0 | 1 | 0 | 304.834 |  | 114.598 |  | 114.31 | Sandy
150 | 51/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 119.229 |  | 103.624 |  | 103.59 | Sandy
151 | 51/1 | DA+0 |  |  | 0 | 0 | 1 | 0 | 74.897 |  | 10.113 |  | 10.113 | Sandy
152 | 51/2 | DA+0 | -1 |  | 0 | 0 | 0 | 0 | 73.95 |  | 12.784 |  | 12.784 | Sandy
153 | 52/0 | DC2+0 |  |  | 0 | 0 | 3 | 3 | 474.917 |  | 226.626 |  | 226.483 | Sandy
154 | 52/1 | DA+6 |  |  | 0 | 4 | 0 | 0 | 95.517 |  | 20.215 |  | 20.215 | Sandy
155 | 52/2 | DA+6 |  |  | 0 | 0 | 0 | 3 | 74.467 |  | 56.535 |  | 56.468 | Sandy
156 | 52/3 | DA+9 |  | 3 | 4 | 3 | 3 | 3 | 54.25 |  | 21.459 |  | 21.459 | Sandy
157 | 52/4 | DA+9 |  |  | 2 | 2 | 0 | 0 | 35.517 |  | 14.371 |  | 14.371 | Sandy
158 | 52/5 | DA+9 |  |  | 0 | 0 | 0 | 1 | 269.167 |  | 177.797 |  | 177.045 | Sandy
159 | 52/6 | DA+6 |  |  | 0 | 0 | 0 | 0 | 343.483 |  | 239.936 |  | 236.824 | Sandy
160 | 52/7 | DA+3 |  |  | 0 | 3 | 1 | 0 | 464.317 |  | 306.372 |  | 305.292 | Sandy
161 | 52/8 | DA+6 |  |  | 0 | 0 | 0 | 0 | 644.717 |  | 582.599 |  | 579.567 | Sandy
162 | 52/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 192.433 |  | 139.028 |  | 139.116 | Sandy
163 | 52/10 | DA+9 |  | 1 | 1 | 2 | 1 | 1 | 270.567 |  | 123.839 |  | 122.335 | Sandy
164 | 53/0 | DB2+9 |  | 4 | 4 | 4 | 4 | 4 | 102.651 |  | 342.89 |  | 342.823 | Sandy
165 | 53/1 | DA+9 |  | 4 | 4 | 4 | 4 | 4 | 511.767 |  | 302.874 |  | 302.554 | Sandy
166 | 53/2 | DA+0 |  |  | 0 | 0 | 0 | 2 | 121.063 |  | 38.768 |  | 38.755 | Sandy
167 | 53/3 | DA+9 |  |  | 0 | 4 | 1 | 0 | 454.927 |  | 204.813 |  | 204.743 | Sandy
168 | 53/4 | DA+0 |  |  | 0 | 2 | 1 | 0 | 686.16 |  | 280.645 |  | 280.485 | Sandy
169 | 53/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 104.9 |  | 76.75 |  | 76.51 | Sandy
170 | 53/6 | DA+6 |  |  | 1 | 1 | 3 | 1 | 111.483 |  | 14.573 |  | 14.573 | Sandy
171 | 53/7 | DA+0 |  |  | 0 | 0 | 0 | 0 | 245.537 |  | 112.464 |  | 112.304 | Sandy
172 | 53/8 | DA+9 |  | 0 | 0 | 0 | 0 | 0 | 326.55 |  | 334.123 |  | 333.951 | Sandy
173 | 54/0 | DB1+6 |  |  | 0 | 0 | 0 | 0 | 400.8 |  | 293.967 |  | 293.9 | Sandy
174 | 54/1 | DA+9 |  |  | 1 | 1 | 0 | 0 | 74.4 |  | 17.753 |  | 17.753 | Sandy
175 | 54/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 105.35 |  | 63.16 |  | 63.14 | Sandy
176 | 54/3 | DA+6 |  |  | 0 | 2 | 0 | 0 | 106.517 |  | 71.292 |  | 71.275 | Sandy
177 | 54/4 | DA+9 |  | 0 | 1 | 2 | 0 | 0 | 264 |  | 131.156 |  | 283.706 | Sandy
178 | 54/5 | DA+9 |  | 1 | 1 | 3 | 3 | 1 | 210.2 |  | 91.403 |  | 91.345 | Sandy
179 | 55/0 | DB1+6 |  |  | 0 | 1 | 1 | 0 | 375.874 |  | 244.465 |  | 244.015 | Sandy
180 | 55/4 | DA+0 |  |  | 0 | 0 | 0 | 1 | 248.177 |  | 98.757 |  | 96.581 | Sandy
181 | 55/5 | DA+0 |  |  | 0 | 0 | 1 | 3 | 674.16 |  | 250.709 |  | 249.909 | Sandy
182 | 55/6 | DA+0 |  |  | 0 | 0 | 1 | 2 | 100.954 |  | 24.027 |  | 24.027 | Sandy
183 | 55/7 | DA+0 |  |  | 0 | 0 | 1 | 0 | 551.126 |  | 317.518 |  | 316.72 | Sandy
184 | 55/8 | DA+9 |  |  | 0 | 0 | 1 | 0 | 480.283 |  | 241.51 |  | 136.288 | Sandy
185 | 56/0 | DD60+9 |  | 4 | 4 | 6 | 4 | 4 | 454.562 |  | 387.425
186 | 57/0 | DD60+9 |  | 0 | 0 | 1 | 1 | 0 | 715.032 |  | 562.651 |  | 742.695 | Sandy
187 | 57/1 | DA+3 |  |  | 0 | 0 | 0 | 0 | 38.65 |  | 24.155
188 | 57/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 64.033 |  | 20.988 |  | 20.988 | All Kind of Soil
189 | 57/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 91.063 |  | 39.024 |  | 39.024 | All Kind of Soil
190 | 57/4 | DA+0 |  |  | 0 | 0 | 0 | 0 | 165.446 |  | 77.472 |  | 77.408 | sandy
191 | 57/5 | DA+3 |  |  | 0 | 0 | 0 | 1 | 114.817 |  | 54.629 |  | 53.905 | sandy
192 | 57/6 | DA+3 |  |  | 0 | 1 | 0 | 0 | 118.95 |  | 69.342 |  | 68.908 | All Kind of Soil
193 | 58/0 | DC1+3 |  |  | 0 | 0 | 0 | 0 | 16.509
194 | 59/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 97.629 |  | 97.629 |  | 97.594 | All Kind of Soil
195 | 59/1 | DA+3 |  |  | 0 | 0 | 0 | 1 | 30.167
196 | 59/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 74.35 |  | 57.328 |  | 57.216 | All Kind of Soil
197 | 59/3 | DA+3 |  |  | 0 | 0 | 0 | 1 | 29.783
198 | 59/7 | DA+3 |  |  | 0 | 0 | 0 | 0 | 88.917 |  | 67.301 |  | 67.237 | All Kind of Soil
199 | 59/8 | DB1+3 |  |  | 0 | 0 | 0 | 0 | 30.926
200 | 59/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 51.683
201 | 59/11 | DA+6 |  |  | 0 | 0 | 2 | 0 | 609.4 |  | 443.002 |  | 442.55 | FR
202 | 59/12 | DA+6 |  |  | 0 | 0 | 0 | 0 | 69.983
203 | 60/2 | DA+3 |  |  | 2 | 2 | 0 | 0 | 150.115 |  | 67.99 |  | 67.248 | All Kind of Soil
204 | 61/1 | DA+6 |  |  | 0 | 0 | 0 | 0 | 130.228 |  | 98.667 |  | 98.627 | All Kind of Soil
205 | 61/7 | DA+9 |  |  | 0 | 0 | 0 | 1 | 237.78 |  | 155.449 |  | 154.809 | All Kind of Soil
206 | 61/8 | DA+6 |  |  | 1 | 2 | 1 | 0 | 139.242 |  | 18.852 |  | 18.852 | All Kind of Soil
207 | 62/0 | DB2+0 |  |  | 0 | 0 | 0 | 0 | 50.997 |  | 36.79 |  | 36.29 | All Kind of Soil
208 | 62/1 | DA+3 |  |  | 0 | 0 | 1 | 2 | 200.388 |  | 135.911 |  | 135.895 | sandy
209 | 62/2 | DA+3 |  |  | 0 | 1 | 0 | 0 | 22.433
210 | 62/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 27.142
211 | 62/5 | DA+0 |  |  | 0 | 0 | 0 | 0 | 109.341 |  | 45.234 |  | 45.234 | All Kind of Soil
212 | 62/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 23.573
213 | 63/0 | DC1+0 |  |  | 0 | 0 | 0 | 0 | 199.633 |  | 199.633 |  | 199.333 | All Kind of Soil
214 | 63/3 | DA+3 |  |  | 0 | 0 | 0 | 0 | 173.683 |  | 140.624 |  | 140.608 | All Kind of Soil
215 | 63/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 31.908

## Incharge
Details of Section incharge
Sr. No. | Package | From - To | Accountable Personal | Email ID | Contact Number
1 | PKG F | Gty-AP12 | Sumit Singh | kumars7@kecrpg.com | 7082518194
2 |  | AP12-AP22 | Vivek Shukla/Rajiv Kumar | shuklavk@kecrpg.com | 9451783340
3 |  | AP22-AP33 | Shubham Singh/Vijay Singh
4 |  | AP26-AP40 | Ram Tirath Singh | singhrt@kecrpg.com | 8295788759
5 |  | AP40-AP58 | Jitendra Saini | sainij@kecrpg.com | 6005356903
6 |  | AP58-AP74 | Jainath Mahto | jainath.kec@gmail.com | 9998643264
7 | PKG G | Gty-AP12 | Sumit Singh | kumars7@kecrpg.com | 7082518194
8 |  | AP12-AP22 | Vivek Shukla/Rajiv Kumar | shuklavk@kecrpg.com | 9451783340
9 |  | AP22-AP26 | Shubham Singh/Vijay Singh
10 |  | AP26-AP40 | Ram Tirath Singh | singhrt@kecrpg.com | 8295788759
11 |  | AP40-AP58 | Jitendra Saini | sainij@kecrpg.com | 6005356903
12 |  | AP58-73 | Jainath Mahto | jainath.kec@gmail.com | 9998643264