## DailyExpanded
Work Date | Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name
2024-01-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-01-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-02-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-02-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-03-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-03-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-04-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-04-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-05-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-05-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-06-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-06-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-07-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-07-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-08-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-08-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-09-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-09-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-09 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-10 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-11 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-12 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-13 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-14 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-15 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-16 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-17 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-18 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-19 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-20 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-21 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-22 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-23 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-24 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-25 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-26 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-27 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-28 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-10-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-29 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-10-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-30 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-10-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-10-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-10-31 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-10-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-01 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-02 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-03 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-04 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-05 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-05 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-06 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-07 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-08 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-09 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-10 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-11 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-12 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-13 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-14 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-15 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-16 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-17 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-18 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-19 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-19 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-20 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-21 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-22 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-23 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-24 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-26 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-27 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-28 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-29 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-11-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-11-30 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-01 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-12-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-02 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418
2024-12-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-03 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418
2024-12-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-03 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418
2024-12-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-04 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418
2024-12-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-04 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418
2024-12-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-05 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418
2024-12-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-05 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418
2024-12-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-06 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418
2024-12-06 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-12-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-06 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418
2024-12-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-07 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-12-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-07 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418
2024-12-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-08 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-12-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-08 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418
2024-12-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-09 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-12-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-09 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418
2024-12-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-10 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-12-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-10 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418
2024-12-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-11 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-12-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-11 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418
2024-12-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-12 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418
2024-12-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-12 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418
2024-12-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-13 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418
2024-12-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-13 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418
2024-12-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-14 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418
2024-12-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-14 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418
2024-12-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-15 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418
2024-12-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-15 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418
2024-12-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-16 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418
2024-12-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-16 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418
2024-12-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-17 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418
2024-12-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-17 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418
2024-12-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-18 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418
2024-12-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-18 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418
2024-12-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-19 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418
2024-12-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-19 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418
2024-12-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-20 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418
2024-12-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-20 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418
2024-12-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-21 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418
2024-12-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-21 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418
2024-12-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-22 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418
2024-12-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-22 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418
2024-12-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-23 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418
2024-12-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-23 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418
2024-12-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-24 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418
2024-12-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-24 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418
2024-12-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-25 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418
2024-12-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-25 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418
2024-12-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-26 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418
2024-12-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-26 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418
2024-12-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-27 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418
2024-12-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-27 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418
2024-12-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-28 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418
2024-12-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-29 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418
2024-12-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2024-12-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-12-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2025-01-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2025-01-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2025-01-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2025-01-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2025-01-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2025-01-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2025-01-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2025-01-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2025-01-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2025-01-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2025-01-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-13 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-01-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-14 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-01-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-15 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-01-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-16 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-01-16 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418
2025-01-16 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418
2025-01-17 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-01-17 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418
2025-01-17 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418
2025-01-18 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-01-18 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418
2025-01-18 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418
2025-01-19 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418
2025-01-19 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418
2025-01-20 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418
2025-01-20 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418
2025-01-21 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418
2025-01-21 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418
2025-01-22 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418
2025-01-22 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418
2025-01-23 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418
2025-01-23 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418
2025-01-24 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418
2025-01-24 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-01-25 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418
2025-01-25 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-01-25 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418
2025-01-26 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418
2025-01-26 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-01-26 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418
2025-01-27 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418
2025-01-27 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-01-27 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418
2025-01-28 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418
2025-01-28 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-01-28 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418
2025-01-29 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418
2025-01-29 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-01-29 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418
2025-01-30 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418
2025-01-30 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-01-30 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418
2025-01-31 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-01-31 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-01-31 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418
2025-02-01 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-01 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-02-01 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418
2025-02-02 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-02 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-02-02 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418
2025-02-03 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-03 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-02-04 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-04 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-02-05 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-05 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-02-06 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418
2025-02-06 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-02-07 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418
2025-02-07 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-02-08 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418
2025-02-08 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-02-09 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418
2025-02-09 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-02-10 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418
2025-02-10 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-02-11 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418
2025-02-11 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-02-12 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-12 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-02-13 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-13 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-02-14 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-14 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-02-15 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-15 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-02-16 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-16 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-02-17 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-17 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-02-18 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-02-19 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-02-20 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-02-21 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-02-22 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-02-23 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-02-24 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-02-25 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-02-26 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-02-26 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-02-27 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-02-28 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-03-01 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-03-02 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-03-03 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-03-03 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-03-04 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-03-05 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-03-06 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-03-06 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-03-07 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-03-07 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-03-08 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-03-08 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-03-09 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-03-10 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-03-11 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-03-12 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418
2025-03-13 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418
2025-03-14 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418
2025-03-15 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418
2025-03-16 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418
2025-03-17 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418
2025-03-18 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418
2025-03-18 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418
2025-03-19 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418
2025-03-19 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418
2025-03-20 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418
2025-03-20 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418
2025-03-21 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418
2025-03-21 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418
2025-03-22 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418
2025-03-22 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418
2025-03-23 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418
2025-03-23 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418
2025-03-24 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418
2025-03-25 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418
2025-03-26 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418
2025-03-27 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418
2025-03-28 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418
2025-03-28 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418
2025-03-29 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418
2025-03-30 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418
2025-03-31 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418
2025-04-01 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418
2025-04-02 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418
2025-04-03 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418
2025-04-04 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418
2025-04-05 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418
2025-04-05 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418
2025-04-06 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418
2025-04-07 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418
2025-04-08 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418
2025-04-09 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418
2025-04-10 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418
2025-04-11 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418
2025-04-12 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418
2025-04-12 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418
2025-04-13 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418
2025-04-13 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418
2025-04-14 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418
2025-04-14 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418
2025-04-15 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418
2025-04-15 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418
2025-04-16 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418
2025-04-16 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418
2025-04-17 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418
2025-04-17 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418
2025-04-18 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418
2025-04-18 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418
2025-04-18 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418
2025-04-19 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418
2025-04-19 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418
2025-04-20 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418
2025-04-20 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418
2025-04-21 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418
2025-04-21 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418
2025-04-22 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418
2025-04-22 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418
2025-04-23 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418
2025-04-23 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418
2025-04-24 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418
2025-04-24 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418
2025-04-25 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418
2025-04-25 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418
2025-04-26 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418
2025-04-26 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418
2025-04-27 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418
2025-04-27 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418
2025-04-28 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418
2025-04-28 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418
2025-04-29 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418
2025-04-29 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-04-29 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418
2025-04-30 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-04-30 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418
2025-05-01 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-05-01 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418
2025-05-02 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-05-02 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418
2025-05-03 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-05-03 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418
2025-05-04 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-05-05 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-05-05 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-05-06 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-05-06 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-05-07 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-05-07 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-05-08 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-05-08 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418
2025-05-09 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-05-09 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418
2025-05-10 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-05-10 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418
2025-05-11 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418
2025-05-11 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418
2025-05-11 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-12 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418
2025-05-12 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418
2025-05-12 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-13 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418
2025-05-13 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418
2025-05-13 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-14 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418
2025-05-14 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418
2025-05-14 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-15 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418
2025-05-15 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418
2025-05-15 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-16 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418
2025-05-16 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418
2025-05-16 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-17 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418
2025-05-17 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418
2025-05-17 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-18 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418
2025-05-18 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-19 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418
2025-05-19 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-20 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-21 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-22 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418
2025-05-22 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-23 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418
2025-05-23 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-24 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418
2025-05-24 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-25 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418
2025-05-25 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-26 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418
2025-05-26 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-27 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418
2025-05-28 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418
2025-05-29 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418
2025-05-30 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418
2025-05-30 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-05-31 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418
2025-05-31 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-06-01 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418
2025-06-01 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-06-02 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418
2025-06-02 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-06-03 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-06-03 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-06-04 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-06-04 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-06-05 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-06-06 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-06-07 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-06-08 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-06-09 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418
2025-06-10 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418
2025-06-11 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418
2025-06-12 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418
2025-06-12 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418
2025-06-13 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418
2025-06-14 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418
2025-06-14 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418
2025-06-15 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418
2025-06-15 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418
2025-06-16 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418
2025-06-16 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418
2025-06-17 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418
2025-06-17 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418
2025-06-18 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418
2025-06-19 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-06-19 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418
2025-06-20 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-06-20 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418
2025-06-21 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-06-21 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418
2025-06-22 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-06-22 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418
2025-06-23 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-06-23 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418
2025-06-24 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-06-24 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418
2025-06-25 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-06-26 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-06-27 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-06-28 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-06-29 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-06-29 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-06-30 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-06-30 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-01 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-07-01 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-02 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-03 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-03 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-03 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418
2025-07-03 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-04 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-04 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-04 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418
2025-07-04 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-05 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-05 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-05 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418
2025-07-05 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-06 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-06 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-06 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418
2025-07-06 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-07 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-07 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-07 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418
2025-07-07 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-08 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-08 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-08 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418
2025-07-08 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-09 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-09 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-09 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418
2025-07-09 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-10 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-10 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-10 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418
2025-07-10 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-11 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-11 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-11 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418
2025-07-11 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-12 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-12 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-12 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418
2025-07-12 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-13 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-13 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-13 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-14 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-14 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-14 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418
2025-07-14 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-15 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-15 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-15 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418
2025-07-15 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418
2025-07-16 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-16 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-16 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418
2025-07-16 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418
2025-07-17 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-17 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-17 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418
2025-07-17 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418
2025-07-18 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-18 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-18 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418
2025-07-18 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418
2025-07-19 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-19 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-19 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418
2025-07-19 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418
2025-07-20 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-20 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-20 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418
2025-07-20 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418
2025-07-21 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-21 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-21 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418
2025-07-21 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418
2025-07-21 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-07-22 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-22 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-07-22 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418
2025-07-22 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418
2025-07-22 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-07-23 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-23 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-07-23 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418
2025-07-23 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418
2025-07-23 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-07-24 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-24 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-07-24 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418
2025-07-24 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-07-25 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-25 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-07-25 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418
2025-07-25 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-07-26 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-26 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-07-26 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418
2025-07-26 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-07-27 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-27 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-07-27 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418
2025-07-27 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-07-28 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-28 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-07-28 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418
2025-07-28 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-07-29 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-29 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-07-29 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418
2025-07-29 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-07-30 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-30 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-07-30 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418
2025-07-30 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-07-31 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-07-31 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418
2025-07-31 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-08-01 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-08-01 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-08-02 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-08-02 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-08-03 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-08-03 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-08-04 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-08-04 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-08-05 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-08-05 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-08-06 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-08-06 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-06 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-08-07 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-08-07 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418
2025-08-07 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-07 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-08-07 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418
2025-08-08 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418
2025-08-08 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-08 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418
2025-08-09 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418
2025-08-09 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-09 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-09 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418
2025-08-10 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418
2025-08-10 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-10 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-10 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418
2025-08-11 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418
2025-08-11 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-11 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-11 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418
2025-08-12 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418
2025-08-12 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-12 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-12 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418
2025-08-13 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418
2025-08-13 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-13 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-13 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418
2025-08-14 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418
2025-08-14 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-14 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-14 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418
2025-08-15 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418
2025-08-15 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-15 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-15 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418
2025-08-16 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418
2025-08-16 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-16 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-16 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418
2025-08-16 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-17 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418
2025-08-17 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-17 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-17 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-18 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-08-18 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-18 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-18 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-19 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-08-19 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-19 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-19 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-19 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418
2025-08-20 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-08-20 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-20 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-20 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418
2025-08-21 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-08-21 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-21 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-21 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418
2025-08-22 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-08-22 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418
2025-08-22 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-22 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-22 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418
2025-08-23 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-08-23 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418
2025-08-23 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-23 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418
2025-08-24 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-08-24 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418
2025-08-24 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-24 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418
2025-08-25 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-08-25 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418
2025-08-25 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-25 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418
2025-08-26 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-08-26 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418
2025-08-26 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-26 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418
2025-08-27 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-28 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-29 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-30 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-31 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418
2025-08-31 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-09-01 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418
2025-09-01 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-01 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-09-02 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418
2025-09-02 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-03 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418
2025-09-03 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-03 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418
2025-09-04 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418
2025-09-04 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-04 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418
2025-09-05 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418
2025-09-05 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-05 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418
2025-09-06 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418
2025-09-06 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-06 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418
2025-09-07 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418
2025-09-07 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-07 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418
2025-09-08 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418
2025-09-08 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-09 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418
2025-09-09 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-09 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418
2025-09-10 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418
2025-09-10 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-10 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418
2025-09-11 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-11 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418
2025-09-12 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-12 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418
2025-09-13 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418
2025-09-14 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2025-09-15 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2025-09-16 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2025-09-16 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418
2025-09-17 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2025-09-17 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418
2025-09-18 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2025-09-18 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418
2025-09-19 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2025-09-19 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418
2025-09-20 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2025-09-20 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418
2025-09-21 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2025-09-21 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418
2025-09-22 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2025-09-22 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418
2025-09-23 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2025-09-23 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418
2025-09-24 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2025-09-25 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2024-01-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-02-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-03-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-04-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-05-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-06-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-07-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-08-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-09 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-10 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-11 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-12 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-13 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-14 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-15 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-16 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-17 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-18 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-19 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-20 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-21 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-22 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-23 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-24 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-25 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-26 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-27 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-28 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-29 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-30 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-31 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-01 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-02 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-03 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-04 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-05 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-05 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-06 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-07 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-08 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-09 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-10 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-11 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-12 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-13 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-14 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-15 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-16 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-17 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-18 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-19 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-19 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-20 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-21 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-22 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-23 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-24 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-26 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-27 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-28 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-29 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-30 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-01 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-02 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-03 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-03 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-04 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-04 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-05 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-05 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-06 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-06 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-06 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-07 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-07 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-08 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-08 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-09 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-09 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-10 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-10 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-11 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-11 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-12 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-12 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-13 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-13 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-14 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-14 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-15 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-15 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-16 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-16 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-17 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-17 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-18 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-18 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-19 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-19 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-20 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-20 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-21 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-21 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-22 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-22 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-23 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-23 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-24 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-24 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-25 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-25 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-26 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-26 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-27 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-27 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-28 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-29 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-13 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-14 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-15 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-16 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-16 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-16 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-17 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-17 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-17 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-18 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-18 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-18 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-19 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-19 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-20 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-20 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-21 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-21 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-22 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-22 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-23 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-23 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-24 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-24 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-25 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-25 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-25 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-26 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-26 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-26 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-27 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-27 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-27 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-28 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-28 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-28 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-29 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-29 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-29 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-30 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-30 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-30 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-31 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-31 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-31 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-01 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-01 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-01 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-02 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-02 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-02 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-03 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-03 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-04 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-04 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-05 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-05 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-06 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-06 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-07 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-07 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-08 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-08 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-09 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-09 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-10 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-10 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-11 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-11 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-12 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-12 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-13 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-13 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-14 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-14 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-15 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-15 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-16 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-16 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-17 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-17 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-18 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-19 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-20 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-21 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-22 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-23 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-24 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-25 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-26 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-26 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-27 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-28 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-01 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-02 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-03 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-03 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-04 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-05 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-06 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-06 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-07 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-07 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-08 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-08 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-09 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-10 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-11 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-12 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-13 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-14 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-15 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-16 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-17 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-18 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-18 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-19 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-19 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-20 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-20 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-21 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-21 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-22 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-22 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-23 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-23 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-24 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-25 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-26 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-27 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-28 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-28 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-29 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-30 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-31 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-01 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-02 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-03 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-04 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-05 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-05 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-06 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-07 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-08 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-09 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-10 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-11 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-12 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-12 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-13 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-13 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-14 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-14 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-15 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-15 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-16 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-16 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-17 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-17 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-18 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-18 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-18 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-19 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-19 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-20 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-20 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-21 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-21 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-22 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-22 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-23 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-23 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-24 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-24 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-25 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-25 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-26 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-26 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-27 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-27 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-28 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-28 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-29 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-29 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-29 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-30 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-30 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-01 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-01 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-02 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-02 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-03 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-03 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-04 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-05 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-05 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-06 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-06 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-07 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-07 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-08 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-08 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-09 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-09 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-10 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-10 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-11 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-11 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-11 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-12 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-12 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-12 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-13 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-13 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-13 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-14 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-14 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-14 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-15 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-15 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-15 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-16 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-16 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-16 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-17 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-17 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-17 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-18 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-18 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-19 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-19 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-20 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-21 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-22 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-22 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-23 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-23 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-24 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-24 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-25 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-25 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-26 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-26 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-27 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-28 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-29 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-30 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-30 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-31 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-31 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-01 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-01 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-02 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-02 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-03 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-03 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-04 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-04 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-05 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-06 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-07 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-08 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-09 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-10 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-11 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-12 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-12 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-13 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-14 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-14 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-15 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-15 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-16 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-16 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-17 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-17 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-18 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-19 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-19 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-20 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-20 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-21 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-21 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-22 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-22 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-23 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-23 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-24 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-24 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-25 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-26 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-27 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-28 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-29 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-29 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-30 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-30 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-01 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-01 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-02 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-03 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-03 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-03 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-03 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-04 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-04 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-04 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-04 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-05 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-05 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-05 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-05 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-06 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-06 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-06 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-06 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-07 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-07 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-07 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-07 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-08 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-08 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-08 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-08 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-09 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-09 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-09 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-09 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-10 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-10 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-10 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-10 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-11 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-11 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-11 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-11 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-12 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-12 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-12 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-12 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-13 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-13 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-13 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-14 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-14 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-14 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-14 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-15 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-15 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-15 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-15 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-16 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-16 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-16 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-16 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-17 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-17 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-17 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-17 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-18 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-18 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-18 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-18 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-19 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-19 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-19 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-19 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-20 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-20 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-20 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-20 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-21 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-21 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-21 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-21 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-21 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-22 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-22 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-22 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-22 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-22 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-23 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-23 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-23 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-23 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-23 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-24 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-24 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-24 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-24 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-25 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-25 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-25 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-25 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-26 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-26 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-26 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-26 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-27 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-27 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-27 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-27 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-28 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-28 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-28 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-28 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-29 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-29 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-29 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-29 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-30 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-30 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-30 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-30 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-31 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-31 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-31 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-01 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-01 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-02 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-02 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-03 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-03 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-04 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-04 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-05 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-05 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-06 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-06 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-06 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-07 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-07 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-07 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-07 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-07 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-08 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-08 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-08 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-09 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-09 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-09 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-09 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-10 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-10 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-10 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-10 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-11 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-11 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-11 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-11 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-12 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-12 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-12 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-12 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-13 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-13 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-13 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-13 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-14 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-14 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-14 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-14 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-15 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-15 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-15 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-15 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-16 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-16 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-16 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-16 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-16 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-17 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-17 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-17 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-17 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-18 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-18 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-18 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-18 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-19 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-19 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-19 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-19 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-19 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-20 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-20 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-20 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-20 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-21 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-21 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-21 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-21 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-22 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-22 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-22 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-22 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-22 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-23 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-23 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-23 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-23 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-24 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-24 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-24 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-24 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-25 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-25 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-25 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-25 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-26 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-26 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-26 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-26 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-27 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-28 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-29 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-30 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-31 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-31 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-01 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-01 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-01 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-02 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-02 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-03 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-03 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-03 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-04 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-04 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-04 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-05 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-05 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-05 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-06 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-06 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-06 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-07 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-07 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-07 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-08 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-08 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-09 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-09 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-09 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-10 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-10 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-10 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-11 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-11 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-12 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-12 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-13 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-14 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-15 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-16 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-16 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-17 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-17 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-18 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-18 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-19 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-19 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-20 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-20 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-21 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-21 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-22 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-22 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-23 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-23 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-24 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-25 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-01 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-02 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-03 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-04 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-05 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-06 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-07 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-08 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-09 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-10 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-11 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-12 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-13 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-14 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-15 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-16 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-16 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-16 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-17 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-17 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-18 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-18 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-19 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-19 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-20 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-20 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-21 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-21 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-22 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-22 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-23 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-23 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-24 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-24 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-25 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-25 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-26 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-26 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-27 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-27 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-28 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-28 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-29 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-29 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-30 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-10-01 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-01 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-10-02 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-03 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-03 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-04 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-04 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-05 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-05 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-06 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-06 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-07 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-07 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-08 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-08 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-09 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-09 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-10 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-10 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-11 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-11 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-12 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-12 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-13 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-13 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-14 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-14 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-15 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-15 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-15 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-16 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-16 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-17 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-17 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-18 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-18 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-19 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-19 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-20 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2024-10-20 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-21 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2024-10-21 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-22 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2024-10-22 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-23 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2024-10-23 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-24 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2024-10-24 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-24 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-24 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-25 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-25 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-26 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-26 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-27 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-27 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-28 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-28 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-29 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-29 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-30 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-31 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-11-01 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2024-11-01 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-02 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2024-11-02 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-03 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2024-11-03 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-04 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2024-11-04 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-05 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-05 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-06 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-06 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-07 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-07 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-08 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-08 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-09 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-09 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-10 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-10 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-10 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-10 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-10 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-10 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-10 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-11 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-11 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-11 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-11 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-11 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-11 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-12 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-12 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-12 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-12 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-12 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-12 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-13 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-13 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-13 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-13 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-13 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-13 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-14 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-14 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-14 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-14 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-14 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-14 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-14 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-15 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-15 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-15 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-15 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-15 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-15 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-16 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-16 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-16 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-16 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-16 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-16 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-17 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-17 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-17 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-17 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-17 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-17 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-17 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-18 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-18 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-18 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-18 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-18 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-18 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-19 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-19 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-19 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-19 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-19 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-19 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-20 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-20 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-20 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-20 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-20 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-20 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-21 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-21 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-21 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-21 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-21 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-21 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-22 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-22 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-22 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-22 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-22 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-22 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-22 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-23 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-23 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-23 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-23 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-23 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-23 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-24 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-24 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-24 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-24 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-24 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-24 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-25 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-25 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-25 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-25 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-25 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-26 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-26 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-26 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-11-26 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-27 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-27 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-27 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-11-28 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-28 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-28 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-11-28 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-11-28 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-11-29 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-29 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-11-29 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-11-29 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-11-29 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-11-29 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-11-30 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-11-30 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-11-30 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-11-30 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-11-30 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-11-30 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-01 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-01 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-01 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-01 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-12-01 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-01 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-12-01 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-02 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-02 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-02 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-02 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-12-02 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-02 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-12-02 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-03 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-03 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-03 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-03 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-12-03 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-03 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-12-03 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-04 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-04 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-04 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-04 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-04 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-12-04 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-05 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-05 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-05 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-05 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-05 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-12-05 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-06 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-06 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-06 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-06 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-06 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-06 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-06 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-07 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-07 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-07 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-07 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-07 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-07 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-08 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-08 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-08 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-08 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-08 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-08 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-09 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-09 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-09 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-09 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-09 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-09 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-10 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-10 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-10 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-10 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-10 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-10 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-10 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-11 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-11 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-11 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-11 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-11 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-11 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-12 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-12 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-12 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-12 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-12 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-12 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-12 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2024-12-12 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-13 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-13 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-13 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-13 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-13 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2024-12-13 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-13 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-14 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-14 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-14 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-14 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-14 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2024-12-14 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-15 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-15 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-15 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-15 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-15 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2024-12-15 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-16 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-16 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-16 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-16 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-16 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2024-12-16 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-17 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-17 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-17 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-17 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-17 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-18 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-18 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-18 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-18 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-18 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-18 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-19 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-19 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-19 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-19 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-19 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-19 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-20 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-20 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-20 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-20 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-20 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-20 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-21 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-21 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-21 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-21 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-21 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-21 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-22 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-22 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-22 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-22 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-22 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-22 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-23 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-23 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-23 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-23 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-23 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-24 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-24 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-24 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-24 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-24 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-24 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2024-12-24 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-25 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-25 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-25 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-25 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-25 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-25 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2024-12-25 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-26 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-26 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-26 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-26 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-26 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-26 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2024-12-26 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-27 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-27 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-27 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-27 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-27 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-27 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2024-12-27 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-28 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2024-12-28 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-28 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-28 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-28 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-28 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2024-12-28 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2024-12-29 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2024-12-29 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-29 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-29 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-29 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-29 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2024-12-29 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2024-12-30 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2024-12-30 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-30 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-30 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-30 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-30 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2024-12-30 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2024-12-31 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2024-12-31 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-31 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-31 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-31 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2024-12-31 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2024-12-31 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-01 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2025-01-01 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2025-01-01 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-01 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-01 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-01 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-02 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2025-01-02 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2025-01-02 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-02 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-02 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-02 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-03 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2025-01-03 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2025-01-03 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-03 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-03 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-03 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-03 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-04 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2025-01-04 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-04 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-04 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-04 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-04 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-05 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-05 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-05 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-05 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-05 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-06 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-06 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-06 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-06 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-06 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-07 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-07 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-07 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-07 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-07 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-07 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-07 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-08 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-08 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-08 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-08 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-08 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-08 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-08 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-09 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-09 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-09 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-09 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-09 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-09 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-09 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-10 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-10 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-10 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-10 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-10 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-10 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-10 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-10 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-10 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-11 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-11 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-11 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-11 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-11 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-11 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-11 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-11 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-11 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-12 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-12 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-12 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-12 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-12 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-12 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-12 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-12 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-13 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-13 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-13 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-13 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-13 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-13 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-13 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-13 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-14 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-14 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-14 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-14 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-14 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-14 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-14 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-14 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-15 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-15 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-15 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-15 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-15 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-15 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-15 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-15 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-16 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-16 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-16 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-16 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-16 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-16 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-16 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-16 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-17 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-17 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-17 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-17 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-17 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-17 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-17 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-17 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-18 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-18 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-18 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-18 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-18 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-18 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-18 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-18 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-19 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-19 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-19 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-19 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-19 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-19 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-19 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-19 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-20 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-20 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-20 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-20 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-20 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-20 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-20 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-21 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-21 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-21 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-21 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-21 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-21 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-21 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-22 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-22 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-22 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-22 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-22 | 2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2025-01-22 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-22 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-23 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-23 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-23 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-23 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-23 | 2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2025-01-23 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-23 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-24 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-24 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-24 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-24 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-24 | 2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2025-01-24 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-24 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-25 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-25 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-25 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-25 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-25 | 2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2025-01-25 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-25 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-26 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-26 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-26 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-26 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-26 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-26 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-26 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-26 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-27 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-27 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-27 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-27 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-27 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-27 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-27 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-27 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-28 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-28 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-28 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-28 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-28 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-28 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-28 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-01-28 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-29 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-29 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-29 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-29 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-01-29 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-29 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-29 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-01-29 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-30 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-30 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-30 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-01-30 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-01-30 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-30 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-30 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-01-30 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-31 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-31 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-01-31 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-01-31 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-01-31 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-31 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-01-31 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-02-01 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-01 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-02-01 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-01 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-01 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-01 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-02 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-02-02 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-02 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-02-02 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-02 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-02 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-02 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-03 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-02-03 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-03 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-02-03 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-03 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-03 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-03 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-04 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-02-04 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-04 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-02-04 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-04 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-04 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-04 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-05 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-02-05 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-05 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-02-05 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-05 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-05 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-05 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-06 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-02-06 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-06 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-06 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-06 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-06 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-07 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-02-07 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-07 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-07 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-07 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-08 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-08 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-08 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-08 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-09 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-09 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-09 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-09 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-10 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-10 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-10 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-10 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-11 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-11 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-12 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-12 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-12 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-12 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-13 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-13 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-13 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-13 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-14 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-14 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-14 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-14 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-14 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-14 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-15 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-15 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-15 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-15 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-15 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-15 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-16 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-16 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-16 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-16 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-16 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-16 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-16 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-17 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-17 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-17 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-17 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-17 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-17 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-17 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-18 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-18 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-18 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-18 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-18 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-18 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-18 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-19 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-19 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-19 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-19 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-19 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-19 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-19 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-20 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-20 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-20 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-20 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-20 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-20 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-20 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-21 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-21 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-21 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416
2025-02-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-21 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-21 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-21 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-21 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-22 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-22 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416
2025-02-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-22 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-22 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-22 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-23 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-23 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416
2025-02-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-23 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-23 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-23 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-24 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-24 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416
2025-02-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-24 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-24 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-25 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-25 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416
2025-02-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-25 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-25 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-26 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-26 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-02-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-27 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-27 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416
2025-02-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-27 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-02-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-27 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-02-27 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-02-28 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-28 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416
2025-02-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-28 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-02-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-28 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-02-28 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-02-28 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-01 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-01 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416
2025-03-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-01 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-01 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-01 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-01 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-01 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-01 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-01 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416
2025-03-01 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-02 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-02 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416
2025-03-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-02 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-02 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-02 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-02 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-02 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-02 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-02 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416
2025-03-02 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-03 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-03 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416
2025-03-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-03 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-03 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-03 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-03 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-03 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-03 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-03 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416
2025-03-03 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-04 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-04 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-04 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-04 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-04 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-04 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-04 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-04 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416
2025-03-04 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-05 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-05 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-05 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-05 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-05 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-05 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-05 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-05 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416
2025-03-05 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-06 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-06 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-06 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-06 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-06 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-06 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-06 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-06 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-07 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-07 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-07 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-07 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-07 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-07 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-07 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-07 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-08 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-08 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-08 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2025-03-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-08 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-08 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-08 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-08 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2025-03-08 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-08 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-09 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-09 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-09 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2025-03-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-09 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-09 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2025-03-09 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-09 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-10 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-10 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-10 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2025-03-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-10 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-10 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-10 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2025-03-10 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-10 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-11 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-11 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-11 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2025-03-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-11 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-11 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-11 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2025-03-11 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-11 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-12 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-12 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-12 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-12 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-12 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-12 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2025-03-12 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-13 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-13 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-13 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-13 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-13 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-13 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-13 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-14 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-14 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-14 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-14 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-14 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-14 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-15 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-15 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-15 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-15 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-15 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-15 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-16 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-16 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-16 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-16 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-16 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-16 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-16 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-16 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-17 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-17 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-17 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-17 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-17 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-17 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-17 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-18 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-18 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-18 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-18 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-18 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-18 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-18 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-19 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-19 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-19 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-03-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-19 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-19 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-19 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-20 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-20 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-20 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-03-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-20 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-20 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-20 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-20 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-21 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-21 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-21 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-03-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-21 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-21 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-21 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-21 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-22 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-22 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-22 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-03-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-22 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-22 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416
2025-03-22 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-22 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416
2025-03-23 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-23 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-23 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-23 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-03-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-23 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-23 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416
2025-03-23 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-23 | 2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416
2025-03-23 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-23 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416
2025-03-24 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-24 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-24 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-24 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-24 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-24 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416
2025-03-24 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-24 | 2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416
2025-03-24 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-24 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416
2025-03-25 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-25 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-25 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-25 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-25 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-25 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416
2025-03-25 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-25 | 2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416
2025-03-25 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-25 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416
2025-03-26 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-26 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-26 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-26 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-26 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-26 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416
2025-03-26 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-26 | 2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416
2025-03-26 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-26 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416
2025-03-27 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-27 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-27 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-27 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-27 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-27 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416
2025-03-27 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-27 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-27 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416
2025-03-28 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-28 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-28 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-28 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-28 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-28 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416
2025-03-28 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-28 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-03-28 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416
2025-03-28 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-03-29 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-29 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-29 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-29 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-29 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-29 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416
2025-03-29 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-29 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-03-29 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416
2025-03-29 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-03-30 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-30 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-30 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-30 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-30 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-30 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416
2025-03-30 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-30 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-03-30 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-03-31 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-31 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-31 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-03-31 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-31 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-03-31 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-03-31 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416
2025-03-31 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-31 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-03-31 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-04-01 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-01 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-01 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-01 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-01 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-01 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-01 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-01 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-01 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-01 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-04-02 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-02 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-02 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-02 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-02 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-02 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-02 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-02 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-02 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-02 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-04-03 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-03 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-03 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-03 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-03 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-03 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-03 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-03 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-03 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-03 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-03 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-03 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-04-04 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-04 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-04 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-04 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-04 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-04 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-04 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-04 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-04 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-04 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-04 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-04 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-04-05 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-05 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-05 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-05 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-05 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-05 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-05 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-05 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-05 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-05 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-05 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-05 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-04-06 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-06 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-06 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-06 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-06 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-06 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-06 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-06 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-06 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-06 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-06 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-06 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-07 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-07 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-07 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-07 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-07 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-07 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-07 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-07 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-07 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-07 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-07 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-07 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-08 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-08 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-08 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-08 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-08 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-08 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-08 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-08 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-08 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-08 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-08 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-09 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-09 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-09 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-09 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-09 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-09 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-09 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-09 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-09 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-09 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-09 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-10 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-10 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-10 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-10 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-10 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-10 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-10 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-10 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-10 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-10 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-10 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-11 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-11 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-11 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-11 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-11 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-11 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-11 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-11 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-11 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-11 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-12 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-12 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-12 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-12 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-12 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-12 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-12 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-12 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-12 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-12 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-12 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-12 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-12 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-12 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-13 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-13 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-13 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-13 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-13 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-13 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-13 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-13 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-13 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-13 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-13 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-13 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-13 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-14 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-14 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-14 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-14 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-14 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-14 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-14 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-14 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-14 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-14 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-14 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-14 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-14 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-15 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-15 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-15 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-15 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-15 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-15 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-15 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-15 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-15 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-15 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-15 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-16 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-16 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-16 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-16 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-16 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-16 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-16 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-16 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-16 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-16 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-16 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-17 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-17 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-17 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-17 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-17 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-17 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-17 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-17 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-17 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-17 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-17 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-17 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-17 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-18 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-18 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-18 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-18 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-18 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-18 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-18 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-18 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-18 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-18 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-19 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-19 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-19 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-19 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-19 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-19 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-19 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-19 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-19 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-19 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-20 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-20 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-20 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-20 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-20 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-20 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-20 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-20 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-20 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-20 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-21 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-21 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-21 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-21 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-21 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-21 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-21 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-21 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-21 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-21 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-22 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-22 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-22 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-22 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-22 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-22 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-22 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-22 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-22 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-23 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-23 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-23 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-23 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-23 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-23 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-23 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-23 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-23 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-23 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-24 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-24 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-24 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-24 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-24 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-24 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-24 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-24 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-24 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-25 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-25 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-25 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-25 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-25 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-25 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-25 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-25 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-25 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-26 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-26 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-26 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416
2025-04-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-26 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-26 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-26 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-26 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-26 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-26 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-27 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-27 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-04-27 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416
2025-04-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-27 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-27 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-27 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-27 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-27 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-27 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-27 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-04-28 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-28 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-04-28 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416
2025-04-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-28 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-28 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-28 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-28 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-28 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-28 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-28 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-04-29 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-04-29 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-04-29 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416
2025-04-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-29 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-04-29 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-29 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-29 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-29 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-04-30 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-04-30 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-04-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-04-30 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-04-30 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-04-30 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-30 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-01 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-05-01 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-01 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-01 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-05-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-01 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-02 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-05-02 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-02 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416
2025-05-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-02 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-02 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-05-02 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416
2025-05-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-02 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-03 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-05-03 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-03 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416
2025-05-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-03 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-03 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-05-03 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416
2025-05-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-03 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-04 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-05-04 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-04 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416
2025-05-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-04 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-04 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416
2025-05-04 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-04 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-04 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-05 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-05-05 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-05 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416
2025-05-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-05 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-05 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416
2025-05-05 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-05 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-05 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-05 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-06 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-06 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416
2025-05-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-06 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-06 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416
2025-05-06 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-05-06 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-06 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-06 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-06 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-07 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-07 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-07 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-07 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-07 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-07 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-05-07 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-07 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-07 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-07 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-08 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-08 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-08 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-08 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-08 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-08 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-05-08 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-08 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-08 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-09 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-09 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-09 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-09 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-09 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-09 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-05-09 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-09 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-09 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-10 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-10 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-10 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-10 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-10 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-10 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-10 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-10 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-10 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-11 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-11 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-11 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-11 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-11 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-11 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416
2025-05-11 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-11 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-11 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-11 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-12 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-12 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-12 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-12 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-12 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-12 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-12 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416
2025-05-12 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-12 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-12 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-12 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-13 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-13 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-13 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-13 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-13 | 2025-05-13 | 2025-05-15 | Ananya Traders 2 | 42.3742 | 14.1247 | TA416
2025-05-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-13 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-13 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-13 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416
2025-05-13 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-13 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-13 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-13 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-14 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-14 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-14 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-14 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-14 | 2025-05-13 | 2025-05-15 | Ananya Traders 2 | 42.3742 | 14.1247 | TA416
2025-05-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-14 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-14 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-14 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-14 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416
2025-05-14 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-14 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-14 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-14 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-15 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-15 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-15 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-15 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-15 | 2025-05-13 | 2025-05-15 | Ananya Traders 2 | 42.3742 | 14.1247 | TA416
2025-05-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-15 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-15 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-15 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416
2025-05-15 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-15 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-15 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-15 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-16 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-16 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-16 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-16 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-16 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-16 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-16 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-16 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-16 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-16 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-16 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-16 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-17 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-17 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-17 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-17 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-17 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-17 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-17 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-17 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-17 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-17 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-17 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-17 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-18 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-18 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-18 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-18 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-18 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-18 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-18 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-18 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-18 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-18 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-18 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-18 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-19 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-19 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-19 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-19 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-19 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-19 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-19 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-19 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-19 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-19 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-19 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-19 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-20 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416
2025-05-20 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-20 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-20 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-20 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-20 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-20 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-20 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-20 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-20 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-20 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-21 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416
2025-05-21 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-21 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-21 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-21 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-21 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-21 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-21 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-21 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-21 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-21 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-22 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416
2025-05-22 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-22 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-22 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-22 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-22 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-22 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-22 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-22 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-22 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-22 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-23 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416
2025-05-23 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-23 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-23 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-23 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-23 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-23 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-23 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-23 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-24 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416
2025-05-24 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-24 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-24 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-24 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-24 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-24 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-24 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-24 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-24 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-24 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-25 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-25 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-25 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-25 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-25 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-25 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-25 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-25 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-25 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-25 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-26 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-26 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-26 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-26 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-26 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-26 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-26 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-26 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-27 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-27 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-27 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-05-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-27 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-27 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-27 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-27 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-27 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-27 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-28 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-28 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-05-28 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-05-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-28 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-28 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-28 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-05-28 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-28 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-28 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-05-28 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-28 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-29 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-29 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-05-29 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-05-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-29 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-29 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-05-29 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-29 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-05-29 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-29 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-30 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-30 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-05-30 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-05-30 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-05-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-30 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-30 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-05-30 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-05-30 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-30 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-05-30 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-30 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-31 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-31 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-05-31 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-05-31 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-05-31 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-05-31 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-31 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-05-31 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-05-31 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-31 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-05-31 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-05-31 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-06-01 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-01 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-06-01 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-01 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-01 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-06-01 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-01 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-06-01 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-06-02 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-02 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-06-02 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-02 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-02 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-06-02 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-02 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-06-02 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-06-03 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-03 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-03 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-03 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-03 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-03 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-06-03 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-03 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-06-03 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-06-04 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-04 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-04 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-04 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-04 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-04 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-06-04 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-04 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416
2025-06-04 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-06-05 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-05 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-05 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-05 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-05 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-05 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-05 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416
2025-06-05 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-05 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-06 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-06 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-06 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-06 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-06 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-06 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-06 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-06 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416
2025-06-06 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-06 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-07 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-07 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-07 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-07 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-07 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-07 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-07 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-07 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416
2025-06-07 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-07 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-08 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-08 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-08 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-08 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416
2025-06-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-08 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-08 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-08 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-08 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416
2025-06-08 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-08 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-09 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-09 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-09 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-09 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416
2025-06-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-09 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-09 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-09 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-09 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-09 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-09 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-10 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-10 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-10 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-10 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416
2025-06-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-10 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-10 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-10 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-10 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-10 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-10 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-11 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-11 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-11 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-11 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416
2025-06-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-11 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-11 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-11 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-11 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-11 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-12 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-12 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-12 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-12 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416
2025-06-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-12 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-12 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-12 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-12 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-12 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-13 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-13 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-13 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-13 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-13 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-13 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-13 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-13 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-14 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-14 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-14 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-14 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-14 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-14 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-14 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-14 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-14 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-15 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-15 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-15 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-15 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-15 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-15 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-15 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-15 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-15 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-16 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-16 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-16 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-16 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-16 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-16 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-16 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-16 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-16 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-17 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-17 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-17 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-17 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-17 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-17 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-17 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-17 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-17 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-18 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-18 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-18 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-18 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-18 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-18 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-18 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-19 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-19 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-19 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-19 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-19 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-19 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-19 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-20 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-20 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416
2025-06-20 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-20 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-20 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-20 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-20 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-20 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-20 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-21 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-21 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416
2025-06-21 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-21 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-21 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-21 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-21 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-21 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-21 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-22 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-22 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416
2025-06-22 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-22 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-22 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-22 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-22 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-22 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-22 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-23 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-23 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416
2025-06-23 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-23 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-23 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-23 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-23 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-23 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-23 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-24 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-24 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416
2025-06-24 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-24 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-24 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-24 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-24 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-24 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-24 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-25 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-25 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416
2025-06-25 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-25 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-25 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-25 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-25 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-25 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-25 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-26 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-26 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416
2025-06-26 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-26 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-26 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-26 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-26 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-26 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-26 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-27 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-27 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416
2025-06-27 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-27 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-27 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-27 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-27 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-28 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-28 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416
2025-06-28 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-28 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-28 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-28 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-28 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-29 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-29 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-29 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-29 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-06-29 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-30 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-06-30 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-30 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-01 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-01 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-07-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-02 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-02 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-07-02 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-02 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-02 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-03 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-03 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-07-03 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-03 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-03 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-04 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-04 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-07-04 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-04 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-04 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-05 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-05 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-05 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-07-05 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-05 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-05 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-06 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-06 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-06 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-06 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-06 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-07 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-07 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-07 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-07 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-07 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-08 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-08 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-08 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-08 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-09 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-09 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-09 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-09 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-10 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-10 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-10 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-10 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-11 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-11 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-11 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-11 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-12 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-12 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-12 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-12 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-13 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-13 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-13 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-13 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-14 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-14 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-14 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-14 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-15 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-15 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-15 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-15 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-16 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-16 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-16 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-16 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-17 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-17 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-17 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-17 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-18 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-18 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-18 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-18 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-19 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-19 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-19 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-19 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-20 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-20 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-20 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-20 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-21 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-21 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-21 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-21 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-22 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-22 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-22 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-22 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-23 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-23 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-23 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-24 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-24 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-24 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-25 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-25 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-25 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-26 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-26 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-26 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-27 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-27 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-27 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-28 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-28 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-28 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-07-28 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-29 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-29 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-29 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-07-29 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-30 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-30 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-30 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-07-30 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-31 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-31 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-07-31 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-31 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-07-31 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-07-31 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-08-01 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-01 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-01 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-02 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-02 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-02 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-03 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-03 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-03 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-04 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-04 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-04 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-05 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-05 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-05 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-06 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-06 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-06 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-07 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-07 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-07 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-08 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-08 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-08 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-09 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-09 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-10 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-10 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-11 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-11 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-12 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-12 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-13 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-13 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-14 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-14 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-15 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-15 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-16 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-16 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-16 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-17 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-17 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-17 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-18 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-18 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-18 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-19 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-19 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-19 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-20 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-20 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-20 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-21 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-21 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-21 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-22 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-22 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-22 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-23 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-23 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-23 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-24 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-24 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-24 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-25 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-25 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-25 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-26 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-26 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-26 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-27 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-27 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-27 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-28 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-28 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-28 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-29 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-29 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-29 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-30 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-30 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-30 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-31 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-31 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-08-31 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-31 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-08-31 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-09-01 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-01 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-09-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-01 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-09-02 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-02 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-09-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-02 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-09-03 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-03 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-09-04 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-04 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-09-05 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-06 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-07 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-08 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-09 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-10 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-11 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-12 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-13 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-14 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-09-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-09-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-10-31 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-10-31 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-11-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-11-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2023-09-13 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401
2023-09-14 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401
2023-09-15 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401
2023-09-16 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401
2023-09-17 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401
2023-09-18 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401
2023-09-18 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401
2023-09-19 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401
2023-09-19 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401
2023-09-20 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401
2023-09-20 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401
2023-09-21 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401
2023-09-21 | 2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-09-21 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401
2023-09-22 | 2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-09-22 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401
2023-09-23 | 2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-09-23 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401
2023-09-24 | 2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-09-24 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401
2023-09-25 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-09-25 | 2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-09-25 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401
2023-09-25 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401
2023-09-26 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-09-26 | 2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-09-26 | 2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-09-26 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401
2023-09-27 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-09-27 | 2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-09-27 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401
2023-09-28 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-09-28 | 2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-09-28 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401
2023-09-29 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-09-29 | 2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-09-29 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401
2023-09-30 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-09-30 | 2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-09-30 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401
2023-10-01 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-01 | 2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-01 | 2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-01 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401
2023-10-01 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401
2023-10-02 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-02 | 2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-02 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401
2023-10-03 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-03 | 2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-03 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401
2023-10-03 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401
2023-10-04 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-04 | 2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-04 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401
2023-10-04 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401
2023-10-05 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-05 | 2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-05 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401
2023-10-05 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401
2023-10-06 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-06 | 2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-06 | 2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-10-06 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401
2023-10-06 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401
2023-10-07 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-07 | 2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-10-07 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401
2023-10-07 | 2023-10-07 | 2023-10-11 | Sunny Const | 37.504 | 7.5008 | TB401
2023-10-07 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401
2023-10-08 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-08 | 2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-10-08 | 2023-10-07 | 2023-10-11 | Sunny Const | 37.504 | 7.5008 | TB401
2023-10-08 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401
2023-10-09 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-09 | 2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-10-09 | 2023-10-07 | 2023-10-11 | Sunny Const | 37.504 | 7.5008 | TB401
2023-10-09 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401
2023-10-10 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-10 | 2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-10-10 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-10 | 2023-10-07 | 2023-10-11 | Sunny Const | 37.504 | 7.5008 | TB401
2023-10-10 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401
2023-10-10 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401
2023-10-10 | 2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401
2023-10-11 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-11 | 2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-10-11 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-11 | 2023-10-07 | 2023-10-11 | Sunny Const | 37.504 | 7.5008 | TB401
2023-10-11 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401
2023-10-11 | 2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401
2023-10-12 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-12 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401
2023-10-12 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-12 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-12 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401
2023-10-12 | 2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401
2023-10-13 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401
2023-10-13 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-13 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-13 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401
2023-10-13 | 2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401
2023-10-14 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401
2023-10-14 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-14 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-14 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401
2023-10-14 | 2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401
2023-10-15 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401
2023-10-15 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-15 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-15 | 2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-15 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401
2023-10-15 | 2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401
2023-10-15 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401
2023-10-16 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401
2023-10-16 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-16 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-16 | 2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-16 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401
2023-10-16 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401
2023-10-17 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401
2023-10-17 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-17 | 2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-17 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401
2023-10-17 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401
2023-10-17 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401
2023-10-18 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401
2023-10-18 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-18 | 2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-18 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401
2023-10-18 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401
2023-10-19 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401
2023-10-19 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-19 | 2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-19 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401
2023-10-19 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401
2023-10-20 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401
2023-10-20 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-20 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-20 | 2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-20 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-20 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401
2023-10-20 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401
2023-10-20 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401
2023-10-21 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401
2023-10-21 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-21 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-21 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-21 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401
2023-10-21 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401
2023-10-21 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401
2023-10-22 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401
2023-10-22 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-22 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-22 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-22 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401
2023-10-22 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401
2023-10-23 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-23 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-23 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-23 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401
2023-10-23 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401
2023-10-23 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401
2023-10-24 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-24 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-24 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-24 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401
2023-10-24 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401
2023-10-25 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-25 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-25 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-25 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401
2023-10-25 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401
2023-10-26 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-26 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-26 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-26 | 2023-10-26 | 2023-10-30 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-10-26 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401
2023-10-26 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401
2023-10-27 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-27 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-27 | 2023-10-26 | 2023-10-30 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-10-27 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401
2023-10-27 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401
2023-10-28 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-28 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-28 | 2023-10-26 | 2023-10-30 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-10-28 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401
2023-10-28 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401
2023-10-29 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-29 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-29 | 2023-10-26 | 2023-10-30 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-10-29 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401
2023-10-29 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401
2023-10-29 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401
2023-10-30 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-30 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-30 | 2023-10-26 | 2023-10-30 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-10-30 | 2023-10-30 | 2023-11-03 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-10-30 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401
2023-10-30 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401
2023-10-31 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-31 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-10-31 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-10-31 | 2023-10-30 | 2023-11-03 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-10-31 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401
2023-10-31 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401
2023-10-31 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401
2023-11-01 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-11-01 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-01 | 2023-10-30 | 2023-11-03 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-11-01 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401
2023-11-01 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401
2023-11-02 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-11-02 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-02 | 2023-10-30 | 2023-11-03 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-11-02 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401
2023-11-02 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401
2023-11-03 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-11-03 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-03 | 2023-10-30 | 2023-11-03 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-11-03 | 2023-11-03 | 2023-11-07 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-11-03 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401
2023-11-03 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401
2023-11-04 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-11-04 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-04 | 2023-11-03 | 2023-11-07 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-11-04 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401
2023-11-04 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401
2023-11-04 | 2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401
2023-11-05 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-11-05 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-05 | 2023-11-03 | 2023-11-07 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-11-05 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401
2023-11-05 | 2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401
2023-11-06 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-11-06 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-06 | 2023-11-03 | 2023-11-07 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-11-06 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401
2023-11-06 | 2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401
2023-11-07 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-11-07 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-07 | 2023-11-03 | 2023-11-07 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-11-07 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401
2023-11-07 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401
2023-11-07 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-07 | 2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401
2023-11-08 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-11-08 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-08 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401
2023-11-08 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-08 | 2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401
2023-11-09 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-11-09 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-09 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401
2023-11-09 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-09 | 2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401
2023-11-10 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-11-10 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-10 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401
2023-11-10 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-10 | 2023-11-10 | 2023-11-14 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-11 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-11-11 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-11 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401
2023-11-11 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-11 | 2023-11-10 | 2023-11-14 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-12 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-12 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401
2023-11-12 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-12 | 2023-11-10 | 2023-11-14 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-13 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2023-11-13 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-13 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401
2023-11-13 | 2023-11-13 | 2023-11-16 | Sobha Devi | 38.847 | 9.7118 | TB401
2023-11-13 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-13 | 2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401
2023-11-13 | 2023-11-10 | 2023-11-14 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-14 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2023-11-14 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-14 | 2023-11-13 | 2023-11-16 | Sobha Devi | 38.847 | 9.7118 | TB401
2023-11-14 | 2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401
2023-11-14 | 2023-11-10 | 2023-11-14 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-15 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401
2023-11-15 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2023-11-15 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-15 | 2023-11-13 | 2023-11-16 | Sobha Devi | 38.847 | 9.7118 | TB401
2023-11-15 | 2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401
2023-11-15 | 2023-11-15 | 2023-11-19 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-16 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401
2023-11-16 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2023-11-16 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-16 | 2023-11-13 | 2023-11-16 | Sobha Devi | 38.847 | 9.7118 | TB401
2023-11-16 | 2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-11-16 | 2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401
2023-11-16 | 2023-11-15 | 2023-11-19 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-17 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401
2023-11-17 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2023-11-17 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-17 | 2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-11-17 | 2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401
2023-11-17 | 2023-11-15 | 2023-11-19 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-18 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401
2023-11-18 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2023-11-18 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-18 | 2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-11-18 | 2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401
2023-11-18 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-18 | 2023-11-15 | 2023-11-19 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-19 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401
2023-11-19 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2023-11-19 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-19 | 2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-11-19 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-19 | 2023-11-15 | 2023-11-19 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-19 | 2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-20 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401
2023-11-20 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2023-11-20 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-20 | 2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-11-20 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-20 | 2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-21 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401
2023-11-21 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2023-11-21 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-21 | 2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-11-21 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-21 | 2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-22 | 2023-11-22 | 2023-11-26 | Chinta Devi | 37.504 | 7.5008 | TB401
2023-11-22 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401
2023-11-22 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-22 | 2023-11-22 | 2023-11-24 | Sobha Devi | 38.847 | 12.949 | TB401
2023-11-22 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-22 | 2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-23 | 2023-11-22 | 2023-11-26 | Chinta Devi | 37.504 | 7.5008 | TB401
2023-11-23 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401
2023-11-23 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-23 | 2023-11-22 | 2023-11-24 | Sobha Devi | 38.847 | 12.949 | TB401
2023-11-23 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-23 | 2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-24 | 2023-11-22 | 2023-11-26 | Chinta Devi | 37.504 | 7.5008 | TB401
2023-11-24 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401
2023-11-24 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-24 | 2023-11-22 | 2023-11-24 | Sobha Devi | 38.847 | 12.949 | TB401
2023-11-24 | 2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-11-24 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-24 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-24 | 2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-24 | 2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-25 | 2023-11-22 | 2023-11-26 | Chinta Devi | 37.504 | 7.5008 | TB401
2023-11-25 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401
2023-11-25 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-25 | 2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-11-25 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-25 | 2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-26 | 2023-11-22 | 2023-11-26 | Chinta Devi | 37.504 | 7.5008 | TB401
2023-11-26 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401
2023-11-26 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-26 | 2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-11-26 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-26 | 2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-27 | 2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-11-27 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401
2023-11-27 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-27 | 2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-11-27 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-27 | 2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-28 | 2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-11-28 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401
2023-11-28 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-28 | 2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-11-28 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-28 | 2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-29 | 2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-11-29 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401
2023-11-29 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-29 | 2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-11-29 | 2023-11-29 | 2023-12-02 | Sobha Devi | 38.847 | 9.7118 | TB401
2023-11-29 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-29 | 2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-29 | 2023-11-29 | 2023-12-03 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-30 | 2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-11-30 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401
2023-11-30 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-11-30 | 2023-11-29 | 2023-12-02 | Sobha Devi | 38.847 | 9.7118 | TB401
2023-11-30 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-30 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401
2023-11-30 | 2023-11-29 | 2023-12-03 | Suraj Const | 38.847 | 7.7694 | TB401
2023-12-01 | 2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-01 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401
2023-12-01 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-01 | 2023-11-29 | 2023-12-02 | Sobha Devi | 38.847 | 9.7118 | TB401
2023-12-01 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401
2023-12-01 | 2023-11-29 | 2023-12-03 | Suraj Const | 38.847 | 7.7694 | TB401
2023-12-02 | 2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-02 | 2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-02 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-02 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-02 | 2023-11-29 | 2023-12-02 | Sobha Devi | 38.847 | 9.7118 | TB401
2023-12-02 | 2023-12-02 | 2023-12-06 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-12-02 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401
2023-12-02 | 2023-11-29 | 2023-12-03 | Suraj Const | 38.847 | 7.7694 | TB401
2023-12-03 | 2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-03 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-03 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-03 | 2023-12-02 | 2023-12-06 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-12-03 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401
2023-12-03 | 2023-11-29 | 2023-12-03 | Suraj Const | 38.847 | 7.7694 | TB401
2023-12-03 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-04 | 2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-04 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-04 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-04 | 2023-12-02 | 2023-12-06 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-12-04 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401
2023-12-04 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-05 | 2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-05 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-05 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-05 | 2023-12-02 | 2023-12-06 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-12-05 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401
2023-12-05 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-06 | 2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-06 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-06 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-06 | 2023-12-02 | 2023-12-06 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-12-06 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401
2023-12-06 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401
2023-12-06 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401
2023-12-06 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-07 | 2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-07 | 2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-07 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-07 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-07 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401
2023-12-07 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401
2023-12-07 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-07 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-08 | 2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-08 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-08 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-08 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401
2023-12-08 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401
2023-12-08 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-08 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-09 | 2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-09 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-09 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401
2023-12-09 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-09 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401
2023-12-09 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401
2023-12-09 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-09 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-09 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-10 | 2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-10 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401
2023-12-10 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-10 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401
2023-12-10 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401
2023-12-10 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-10 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-11 | 2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-11 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401
2023-12-11 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-11 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401
2023-12-11 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401
2023-12-11 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-11 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-12 | 2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-12 | 2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-12 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401
2023-12-12 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-12 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401
2023-12-12 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401
2023-12-12 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-12 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-13 | 2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-13 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401
2023-12-13 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-13 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401
2023-12-13 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401
2023-12-13 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401
2023-12-13 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-13 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-14 | 2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-14 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401
2023-12-14 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-14 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401
2023-12-14 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401
2023-12-14 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-14 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401
2023-12-14 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-15 | 2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-15 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401
2023-12-15 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-15 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401
2023-12-15 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-15 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401
2023-12-15 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-16 | 2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-16 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401
2023-12-16 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401
2023-12-16 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-16 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401
2023-12-16 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-16 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401
2023-12-16 | 2023-12-16 | 2023-12-19 | Suraj Const | 37.504 | 9.376 | TB401
2023-12-17 | 2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-17 | 2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-17 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401
2023-12-17 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-17 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401
2023-12-17 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-17 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401
2023-12-17 | 2023-12-16 | 2023-12-19 | Suraj Const | 37.504 | 9.376 | TB401
2023-12-18 | 2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-18 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401
2023-12-18 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-18 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401
2023-12-18 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-18 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401
2023-12-18 | 2023-12-16 | 2023-12-19 | Suraj Const | 37.504 | 9.376 | TB401
2023-12-19 | 2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-19 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401
2023-12-19 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-19 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401
2023-12-19 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-19 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401
2023-12-19 | 2023-12-16 | 2023-12-19 | Suraj Const | 37.504 | 9.376 | TB401
2023-12-20 | 2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-20 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401
2023-12-20 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-20 | 2023-12-20 | 2023-12-24 | Sobha Devi | 37.504 | 7.5008 | TB401
2023-12-20 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-20 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401
2023-12-20 | 2023-12-20 | 2023-12-24 | Suraj Const | 37.504 | 7.5008 | TB401
2023-12-21 | 2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-21 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401
2023-12-21 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-21 | 2023-12-20 | 2023-12-24 | Sobha Devi | 37.504 | 7.5008 | TB401
2023-12-21 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-21 | 2023-12-20 | 2023-12-24 | Suraj Const | 37.504 | 7.5008 | TB401
2023-12-22 | 2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-22 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401
2023-12-22 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401
2023-12-22 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-22 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-22 | 2023-12-20 | 2023-12-24 | Sobha Devi | 37.504 | 7.5008 | TB401
2023-12-22 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-22 | 2023-12-20 | 2023-12-24 | Suraj Const | 37.504 | 7.5008 | TB401
2023-12-23 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401
2023-12-23 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-23 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-23 | 2023-12-20 | 2023-12-24 | Sobha Devi | 37.504 | 7.5008 | TB401
2023-12-23 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-23 | 2023-12-20 | 2023-12-24 | Suraj Const | 37.504 | 7.5008 | TB401
2023-12-24 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401
2023-12-24 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-24 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-24 | 2023-12-20 | 2023-12-24 | Sobha Devi | 37.504 | 7.5008 | TB401
2023-12-24 | 2023-12-24 | 2023-12-28 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-12-24 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-24 | 2023-12-20 | 2023-12-24 | Suraj Const | 37.504 | 7.5008 | TB401
2023-12-24 | 2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-12-25 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401
2023-12-25 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-25 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-25 | 2023-12-24 | 2023-12-28 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-12-25 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-25 | 2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-12-26 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401
2023-12-26 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-26 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-26 | 2023-12-24 | 2023-12-28 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-12-26 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-26 | 2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-12-27 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401
2023-12-27 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-27 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-27 | 2023-12-24 | 2023-12-28 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-12-27 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-27 | 2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-12-28 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401
2023-12-28 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401
2023-12-28 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-28 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-28 | 2023-12-24 | 2023-12-28 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-12-28 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401
2023-12-28 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-28 | 2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-12-29 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401
2023-12-29 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-29 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2023-12-29 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-29 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401
2023-12-29 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-29 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2023-12-29 | 2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-12-29 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401
2023-12-30 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401
2023-12-30 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2023-12-30 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-30 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401
2023-12-30 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2023-12-30 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401
2023-12-31 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401
2023-12-31 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2023-12-31 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2023-12-31 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401
2023-12-31 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2023-12-31 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401
2024-01-01 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401
2024-01-01 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-01-01 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-01 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401
2024-01-01 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2024-01-01 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401
2024-01-02 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401
2024-01-02 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-01-02 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-02 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401
2024-01-02 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2024-01-02 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401
2024-01-03 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401
2024-01-03 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-01-03 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-03 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401
2024-01-03 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2024-01-03 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401
2024-01-04 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401
2024-01-04 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-01-04 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-04 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401
2024-01-04 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2024-01-04 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401
2024-01-05 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401
2024-01-05 | 2024-01-05 | 2024-01-09 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-01-05 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-01-05 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-05 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401
2024-01-05 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401
2024-01-05 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2024-01-05 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401
2024-01-06 | 2024-01-05 | 2024-01-09 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-01-06 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-01-06 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-06 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401
2024-01-06 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2024-01-06 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401
2024-01-06 | 2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401
2024-01-07 | 2024-01-05 | 2024-01-09 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-01-07 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-01-07 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-07 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-07 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401
2024-01-07 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2024-01-07 | 2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401
2024-01-08 | 2024-01-05 | 2024-01-09 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-01-08 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-08 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-08 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401
2024-01-08 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2024-01-08 | 2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401
2024-01-09 | 2024-01-05 | 2024-01-09 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-01-09 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401
2024-01-09 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-09 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-09 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401
2024-01-09 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2024-01-09 | 2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401
2024-01-10 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401
2024-01-10 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-10 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-10 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401
2024-01-10 | 2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401
2024-01-11 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401
2024-01-11 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-11 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-11 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401
2024-01-11 | 2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401
2024-01-12 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401
2024-01-12 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-12 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-12 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401
2024-01-12 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401
2024-01-12 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401
2024-01-13 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401
2024-01-13 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-13 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-13 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401
2024-01-13 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401
2024-01-14 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401
2024-01-14 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-14 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-14 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401
2024-01-14 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401
2024-01-15 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401
2024-01-15 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401
2024-01-15 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-15 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-15 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401
2024-01-15 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401
2024-01-16 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401
2024-01-16 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-16 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-16 | 2024-01-16 | 2024-01-20 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-01-16 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401
2024-01-16 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401
2024-01-17 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401
2024-01-17 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-17 | 2024-01-16 | 2024-01-20 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-01-17 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401
2024-01-17 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401
2024-01-18 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401
2024-01-18 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-18 | 2024-01-16 | 2024-01-20 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-01-18 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401
2024-01-18 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401
2024-01-19 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401
2024-01-19 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-19 | 2024-01-16 | 2024-01-20 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-01-19 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401
2024-01-19 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401
2024-01-20 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401
2024-01-20 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401
2024-01-20 | 2024-01-16 | 2024-01-20 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-01-20 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401
2024-01-20 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401
2024-01-21 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401
2024-01-21 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401
2024-01-21 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401
2024-01-21 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401
2024-01-22 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401
2024-01-22 | 2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-01-22 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401
2024-01-22 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401
2024-01-22 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401
2024-01-23 | 2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-01-23 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401
2024-01-23 | 2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401
2024-01-23 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401
2024-01-23 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401
2024-01-24 | 2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-01-24 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401
2024-01-24 | 2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401
2024-01-24 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401
2024-01-24 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401
2024-01-25 | 2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-01-25 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401
2024-01-25 | 2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401
2024-01-25 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401
2024-01-25 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401
2024-01-26 | 2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-01-26 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401
2024-01-26 | 2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401
2024-01-26 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401
2024-01-26 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401
2024-01-27 | 2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-01-27 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401
2024-01-27 | 2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401
2024-01-27 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401
2024-01-27 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401
2024-01-28 | 2024-01-28 | 2024-02-01 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-01-28 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401
2024-01-28 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2024-01-28 | 2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401
2024-01-28 | 2024-01-28 | 2024-01-31 | Sobha Devi | 37.504 | 9.376 | TB401
2024-01-28 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401
2024-01-28 | 2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401
2024-01-28 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401
2024-01-29 | 2024-01-28 | 2024-02-01 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-01-29 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2024-01-29 | 2024-01-28 | 2024-01-31 | Sobha Devi | 37.504 | 9.376 | TB401
2024-01-29 | 2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401
2024-01-30 | 2024-01-28 | 2024-02-01 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-01-30 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2024-01-30 | 2024-01-28 | 2024-01-31 | Sobha Devi | 37.504 | 9.376 | TB401
2024-01-30 | 2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401
2024-01-31 | 2024-01-28 | 2024-02-01 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-01-31 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2024-01-31 | 2024-01-28 | 2024-01-31 | Sobha Devi | 37.504 | 9.376 | TB401
2024-01-31 | 2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401
2024-02-01 | 2024-01-28 | 2024-02-01 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-02-01 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2024-02-01 | 2024-02-01 | 2024-02-05 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-01 | 2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401
2024-02-02 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2024-02-02 | 2024-02-01 | 2024-02-05 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-02 | 2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401
2024-02-03 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2024-02-03 | 2024-02-01 | 2024-02-05 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-03 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401
2024-02-04 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2024-02-04 | 2024-02-01 | 2024-02-05 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-04 | 2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401
2024-02-04 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401
2024-02-05 | 2024-02-01 | 2024-02-05 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-05 | 2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401
2024-02-05 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401
2024-02-06 | 2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401
2024-02-06 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401
2024-02-07 | 2024-02-07 | 2024-02-09 | Sobha Devi | 37.504 | 12.5013 | TB401
2024-02-07 | 2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401
2024-02-07 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401
2024-02-08 | 2024-02-07 | 2024-02-09 | Sobha Devi | 37.504 | 12.5013 | TB401
2024-02-08 | 2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401
2024-02-08 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401
2024-02-09 | 2024-02-07 | 2024-02-09 | Sobha Devi | 37.504 | 12.5013 | TB401
2024-02-09 | 2024-02-09 | 2024-02-13 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-09 | 2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401
2024-02-09 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401
2024-02-10 | 2024-02-09 | 2024-02-13 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-10 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401
2024-02-11 | 2024-02-09 | 2024-02-13 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-11 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401
2024-02-12 | 2024-02-09 | 2024-02-13 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-12 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401
2024-02-13 | 2024-02-09 | 2024-02-13 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-13 | 2024-02-13 | 2024-02-17 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-13 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401
2024-02-14 | 2024-02-13 | 2024-02-17 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-14 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401
2024-02-15 | 2024-02-13 | 2024-02-17 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-15 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401
2024-02-16 | 2024-02-13 | 2024-02-17 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-16 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401
2024-02-17 | 2024-02-13 | 2024-02-17 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-17 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401
2024-02-18 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401
2024-02-18 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401
2024-02-19 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401
2024-02-20 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401
2024-02-21 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401
2024-02-22 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401
2024-02-23 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401
2024-02-24 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401
2024-03-28 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401
2024-03-29 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401
2024-03-30 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401
2024-03-31 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401
2024-04-01 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401
2024-04-02 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401
2024-04-03 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401
2024-04-04 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401
2024-04-08 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401
2024-04-08 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401
2024-04-09 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401
2024-04-09 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401
2024-04-10 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401
2024-04-10 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401
2024-04-11 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401
2024-04-11 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401
2024-04-12 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401
2024-04-12 | 2024-04-12 | 2024-04-16 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-04-12 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401
2024-04-13 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401
2024-04-13 | 2024-04-12 | 2024-04-16 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-04-13 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401
2024-04-14 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401
2024-04-14 | 2024-04-12 | 2024-04-16 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-04-14 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401
2024-04-15 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401
2024-04-15 | 2024-04-12 | 2024-04-16 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-04-15 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401
2024-04-16 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401
2024-04-16 | 2024-04-12 | 2024-04-16 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-04-16 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401
2024-04-17 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401
2024-04-18 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401
2024-04-26 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-04-27 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-04-28 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-04-29 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-04-30 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-05-01 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-05-02 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-05-03 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-05-04 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-05-05 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-05-05 | 2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-06 | 2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-07 | 2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-08 | 2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-09 | 2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-10 | 2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-10 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401
2024-05-11 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401
2024-05-12 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401
2024-05-13 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401
2024-05-14 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401
2024-05-15 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-15 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401
2024-05-16 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-16 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401
2024-05-16 | 2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-16 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401
2024-05-17 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-17 | 2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-17 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401
2024-05-18 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-18 | 2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-18 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401
2024-05-19 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-19 | 2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-19 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401
2024-05-20 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-20 | 2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-20 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401
2024-05-21 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-21 | 2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-21 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401
2024-05-22 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-22 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401
2024-05-23 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-23 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401
2024-05-24 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-24 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401
2024-05-25 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-25 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401
2024-05-26 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-26 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401
2024-05-27 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-28 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-29 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-30 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-05-31 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-06-01 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-06-02 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-06-03 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-06-04 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-06-05 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-06-06 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-06-07 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-06-08 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-06-10 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-11 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-12 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-13 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-14 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-15 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-16 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-17 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-18 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-19 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-20 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-21 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-22 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-23 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-24 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
2024-06-25 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-06-26 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-06-27 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-06-28 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-06-29 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-06-30 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-07-01 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-07-02 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-07-03 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-07-04 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-07-05 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-07-06 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-07-07 | 2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401
2024-07-08 | 2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401
2024-07-09 | 2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401
2024-07-10 | 2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401
2024-07-11 | 2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401
2024-07-12 | 2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401
2024-07-13 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401
2024-07-14 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401
2024-07-15 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401
2024-07-16 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401
2024-07-17 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401
2024-07-18 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401
2024-07-19 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401
2024-07-20 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401
2024-07-21 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401
2024-07-22 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401
2024-07-22 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401
2024-07-23 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401
2024-07-24 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401
2024-07-25 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401
2024-07-26 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401
2024-07-27 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401
2024-07-28 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401
2024-07-29 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401
2024-07-30 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401
2024-07-31 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401
2024-08-01 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401
2024-08-02 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401
2024-08-03 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401
2024-08-04 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401
2024-08-05 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401
2024-08-06 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401
2024-08-07 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401
2024-08-08 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401
2024-08-09 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401
2024-08-10 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401
2024-08-11 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401
2024-08-12 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401
2024-08-13 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401
2024-08-14 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401
2024-08-15 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401
2024-08-16 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401
2024-08-17 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401
2024-08-18 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401
2024-08-19 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401
2024-08-20 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401
2024-08-25 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401
2024-08-26 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401
2024-08-27 | 2024-08-27 | 2024-08-30 | Sobha Devi | 37.504 | 9.376 | TB401
2024-08-27 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401
2024-08-28 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401
2024-08-28 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-08-28 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401
2024-08-28 | 2024-08-27 | 2024-08-30 | Sobha Devi | 37.504 | 9.376 | TB401
2024-08-28 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401
2024-08-29 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401
2024-08-29 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-08-29 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401
2024-08-29 | 2024-08-27 | 2024-08-30 | Sobha Devi | 37.504 | 9.376 | TB401
2024-08-29 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401
2024-08-30 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401
2024-08-30 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401
2024-08-30 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-08-30 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401
2024-08-30 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-08-30 | 2024-08-27 | 2024-08-30 | Sobha Devi | 37.504 | 9.376 | TB401
2024-08-30 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401
2024-08-31 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401
2024-08-31 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401
2024-08-31 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-08-31 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401
2024-08-31 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-08-31 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401
2024-09-01 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401
2024-09-01 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401
2024-09-01 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-09-01 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401
2024-09-01 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-01 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401
2024-09-01 | 2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-09-01 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401
2024-09-02 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401
2024-09-02 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401
2024-09-02 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-09-02 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401
2024-09-02 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-02 | 2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-09-02 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401
2024-09-03 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401
2024-09-03 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401
2024-09-03 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-09-03 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401
2024-09-03 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-03 | 2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-09-03 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401
2024-09-04 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401
2024-09-04 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401
2024-09-04 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-09-04 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401
2024-09-04 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-04 | 2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-09-04 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401
2024-09-05 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401
2024-09-05 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401
2024-09-05 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-09-05 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401
2024-09-05 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-05 | 2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-09-05 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401
2024-09-06 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-06 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401
2024-09-06 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401
2024-09-06 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401
2024-09-06 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-09-06 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-06 | 2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-09-06 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401
2024-09-07 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-07 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401
2024-09-07 | 2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-09-07 | 2024-09-07 | 2024-09-11 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-07 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-09-07 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-07 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401
2024-09-08 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-08 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401
2024-09-08 | 2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-09-08 | 2024-09-07 | 2024-09-11 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-08 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-09-08 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-08 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401
2024-09-09 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-09 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401
2024-09-09 | 2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-09-09 | 2024-09-07 | 2024-09-11 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-09 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-09 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-09 | 2024-09-09 | 2024-09-12 | Sobha Devi | 37.504 | 9.376 | TB401
2024-09-09 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401
2024-09-10 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-10 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401
2024-09-10 | 2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-09-10 | 2024-09-07 | 2024-09-11 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-10 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401
2024-09-10 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-10 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-10 | 2024-09-09 | 2024-09-12 | Sobha Devi | 37.504 | 9.376 | TB401
2024-09-10 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401
2024-09-11 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-11 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401
2024-09-11 | 2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-09-11 | 2024-09-07 | 2024-09-11 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-11 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401
2024-09-11 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-11 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-11 | 2024-09-09 | 2024-09-12 | Sobha Devi | 37.504 | 9.376 | TB401
2024-09-11 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401
2024-09-11 | 2024-09-11 | 2024-09-15 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-12 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-12 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401
2024-09-12 | 2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-09-12 | 2024-09-12 | 2024-09-16 | Deglal Mahto | 38.847 | 7.7694 | TB401
2024-09-12 | 2024-09-12 | 2024-09-16 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-12 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401
2024-09-12 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-12 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-12 | 2024-09-09 | 2024-09-12 | Sobha Devi | 37.504 | 9.376 | TB401
2024-09-12 | 2024-09-12 | 2024-09-16 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-09-12 | 2024-09-11 | 2024-09-15 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-13 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-13 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401
2024-09-13 | 2024-09-12 | 2024-09-16 | Deglal Mahto | 38.847 | 7.7694 | TB401
2024-09-13 | 2024-09-12 | 2024-09-16 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-13 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401
2024-09-13 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-13 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-13 | 2024-09-12 | 2024-09-16 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-09-13 | 2024-09-11 | 2024-09-15 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-14 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-14 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401
2024-09-14 | 2024-09-12 | 2024-09-16 | Deglal Mahto | 38.847 | 7.7694 | TB401
2024-09-14 | 2024-09-12 | 2024-09-16 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-14 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401
2024-09-14 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-14 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-14 | 2024-09-12 | 2024-09-16 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-09-14 | 2024-09-11 | 2024-09-15 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-15 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-15 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401
2024-09-15 | 2024-09-12 | 2024-09-16 | Deglal Mahto | 38.847 | 7.7694 | TB401
2024-09-15 | 2024-09-12 | 2024-09-16 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-15 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401
2024-09-15 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-15 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-15 | 2024-09-12 | 2024-09-16 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-09-15 | 2024-09-11 | 2024-09-15 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-15 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401
2024-09-16 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-16 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401
2024-09-16 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401
2024-09-16 | 2024-09-12 | 2024-09-16 | Deglal Mahto | 38.847 | 7.7694 | TB401
2024-09-16 | 2024-09-12 | 2024-09-16 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-16 | 2024-09-16 | 2024-09-20 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-16 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401
2024-09-16 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-16 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-16 | 2024-09-12 | 2024-09-16 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-09-16 | 2024-09-16 | 2024-09-20 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-09-16 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401
2024-09-17 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-17 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401
2024-09-17 | 2024-09-16 | 2024-09-20 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-17 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401
2024-09-17 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-17 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-17 | 2024-09-16 | 2024-09-20 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-09-17 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401
2024-09-18 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-18 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401
2024-09-18 | 2024-09-16 | 2024-09-20 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-18 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401
2024-09-18 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-18 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-18 | 2024-09-16 | 2024-09-20 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-09-18 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401
2024-09-19 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-19 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401
2024-09-19 | 2024-09-16 | 2024-09-20 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-19 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401
2024-09-19 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-19 | 2024-09-19 | 2024-09-21 | Nirmal Mahto | 47.148 | 15.716 | TB401
2024-09-19 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-19 | 2024-09-16 | 2024-09-20 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-09-19 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401
2024-09-19 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-09-20 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-09-20 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401
2024-09-20 | 2024-09-16 | 2024-09-20 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-20 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401
2024-09-20 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-20 | 2024-09-19 | 2024-09-21 | Nirmal Mahto | 47.148 | 15.716 | TB401
2024-09-20 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-20 | 2024-09-16 | 2024-09-20 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-09-20 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401
2024-09-20 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401
2024-09-20 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-09-21 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-09-21 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401
2024-09-21 | 2024-09-21 | 2024-09-25 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-21 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-21 | 2024-09-19 | 2024-09-21 | Nirmal Mahto | 47.148 | 15.716 | TB401
2024-09-21 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-21 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401
2024-09-21 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401
2024-09-21 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-09-22 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-09-22 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401
2024-09-22 | 2024-09-22 | 2024-09-26 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-09-22 | 2024-09-21 | 2024-09-25 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-22 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-22 | 2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401
2024-09-22 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-22 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401
2024-09-22 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401
2024-09-22 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-09-23 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-09-23 | 2024-09-22 | 2024-09-26 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-09-23 | 2024-09-21 | 2024-09-25 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-23 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-23 | 2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401
2024-09-23 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-23 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401
2024-09-23 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401
2024-09-23 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-09-24 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-09-24 | 2024-09-22 | 2024-09-26 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-09-24 | 2024-09-21 | 2024-09-25 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-24 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-24 | 2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401
2024-09-24 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-24 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401
2024-09-24 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401
2024-09-24 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-09-25 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-09-25 | 2024-09-22 | 2024-09-26 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-09-25 | 2024-09-21 | 2024-09-25 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-25 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-25 | 2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401
2024-09-25 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-25 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401
2024-09-25 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401
2024-09-25 | 2024-09-25 | 2024-09-29 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-25 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-09-26 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-09-26 | 2024-09-22 | 2024-09-26 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-09-26 | 2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-09-26 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-26 | 2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401
2024-09-26 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-26 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401
2024-09-26 | 2024-09-25 | 2024-09-29 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-26 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-09-26 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401
2024-09-27 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-09-27 | 2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-09-27 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-09-27 | 2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401
2024-09-27 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-27 | 2024-09-25 | 2024-09-29 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-27 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-09-27 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401
2024-09-28 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-09-28 | 2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-09-28 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-09-28 | 2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401
2024-09-28 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-09-28 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-28 | 2024-09-25 | 2024-09-29 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-28 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-09-28 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401
2024-09-29 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-09-29 | 2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-09-29 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-09-29 | 2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401
2024-09-29 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-09-29 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-29 | 2024-09-25 | 2024-09-29 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-29 | 2024-09-29 | 2024-10-03 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-29 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-09-29 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401
2024-09-30 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-09-30 | 2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-09-30 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-09-30 | 2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401
2024-09-30 | 2024-09-30 | 2024-10-04 | Jagdish Mahto | 45.413 | 9.0826 | TB401
2024-09-30 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-09-30 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-09-30 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401
2024-09-30 | 2024-09-29 | 2024-10-03 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-30 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-09-30 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401
2024-10-01 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-10-01 | 2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-10-01 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-01 | 2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401
2024-10-01 | 2024-09-30 | 2024-10-04 | Jagdish Mahto | 45.413 | 9.0826 | TB401
2024-10-01 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-10-01 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-10-01 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401
2024-10-01 | 2024-09-29 | 2024-10-03 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-01 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-10-01 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401
2024-10-02 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-10-02 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-02 | 2024-10-02 | 2024-10-05 | Chinta Devi | 38.847 | 9.7118 | TB401
2024-10-02 | 2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401
2024-10-02 | 2024-09-30 | 2024-10-04 | Jagdish Mahto | 45.413 | 9.0826 | TB401
2024-10-02 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-10-02 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-10-02 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401
2024-10-02 | 2024-09-29 | 2024-10-03 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-02 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-10-02 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401
2024-10-03 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-10-03 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-03 | 2024-10-02 | 2024-10-05 | Chinta Devi | 38.847 | 9.7118 | TB401
2024-10-03 | 2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401
2024-10-03 | 2024-09-30 | 2024-10-04 | Jagdish Mahto | 45.413 | 9.0826 | TB401
2024-10-03 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-10-03 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-10-03 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401
2024-10-03 | 2024-09-29 | 2024-10-03 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-03 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-03 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-10-03 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401
2024-10-04 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-10-04 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-04 | 2024-10-02 | 2024-10-05 | Chinta Devi | 38.847 | 9.7118 | TB401
2024-10-04 | 2024-09-30 | 2024-10-04 | Jagdish Mahto | 45.413 | 9.0826 | TB401
2024-10-04 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-10-04 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-10-04 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401
2024-10-04 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-04 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-10-04 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401
2024-10-05 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-10-05 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-05 | 2024-10-02 | 2024-10-05 | Chinta Devi | 38.847 | 9.7118 | TB401
2024-10-05 | 2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401
2024-10-05 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-05 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-10-05 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-10-05 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401
2024-10-05 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-05 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-10-06 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-10-06 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-06 | 2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401
2024-10-06 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-06 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-10-06 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-10-06 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401
2024-10-06 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-06 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-10-07 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-07 | 2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401
2024-10-07 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-07 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-10-07 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-10-07 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401
2024-10-07 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-07 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-10-08 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-08 | 2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401
2024-10-08 | 2024-10-08 | 2024-10-11 | Jagdish Mahto | 38.847 | 9.7118 | TB401
2024-10-08 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-08 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-10-08 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-08 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-10-08 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401
2024-10-08 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401
2024-10-08 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401
2024-10-08 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-08 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-10-09 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-09 | 2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401
2024-10-09 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401
2024-10-09 | 2024-10-08 | 2024-10-11 | Jagdish Mahto | 38.847 | 9.7118 | TB401
2024-10-09 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-09 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-09 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-10-09 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401
2024-10-09 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401
2024-10-09 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401
2024-10-09 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-09 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-10-10 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-10 | 2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401
2024-10-10 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401
2024-10-10 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401
2024-10-10 | 2024-10-08 | 2024-10-11 | Jagdish Mahto | 38.847 | 9.7118 | TB401
2024-10-10 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-10 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-10 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401
2024-10-10 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401
2024-10-10 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401
2024-10-10 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-10 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-10-11 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401
2024-10-11 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-11 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401
2024-10-11 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401
2024-10-11 | 2024-10-08 | 2024-10-11 | Jagdish Mahto | 38.847 | 9.7118 | TB401
2024-10-11 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-11 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-11 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401
2024-10-11 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401
2024-10-11 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-11 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-10-12 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401
2024-10-12 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-12 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401
2024-10-12 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401
2024-10-12 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-12 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-12 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-12 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401
2024-10-12 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401
2024-10-12 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-13 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401
2024-10-13 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-13 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401
2024-10-13 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401
2024-10-13 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-13 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-13 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-13 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401
2024-10-13 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401
2024-10-13 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-13 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-13 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-14 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401
2024-10-14 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-14 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401
2024-10-14 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401
2024-10-14 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-14 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-14 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-14 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401
2024-10-14 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401
2024-10-14 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-14 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-14 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-15 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401
2024-10-15 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-15 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401
2024-10-15 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401
2024-10-15 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-15 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-15 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-15 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401
2024-10-15 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401
2024-10-15 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-15 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-15 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-16 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401
2024-10-16 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-16 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401
2024-10-16 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401
2024-10-16 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-16 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-16 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-16 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401
2024-10-16 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-16 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-16 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-17 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401
2024-10-17 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-17 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401
2024-10-17 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401
2024-10-17 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-17 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-17 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401
2024-10-17 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-17 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-17 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-18 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401
2024-10-18 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-18 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401
2024-10-18 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401
2024-10-18 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-18 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-18 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-18 | 2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401
2024-10-18 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-19 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401
2024-10-19 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-19 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401
2024-10-19 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-19 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-19 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-19 | 2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401
2024-10-19 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-20 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-20 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-20 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-20 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-20 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-10-20 | 2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401
2024-10-20 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-21 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-21 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-21 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-21 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-21 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-10-21 | 2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401
2024-10-21 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-22 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-22 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-22 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-22 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-22 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-10-22 | 2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401
2024-10-22 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-23 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-23 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401
2024-10-23 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-23 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-23 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-10-23 | 2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401
2024-10-23 | 2024-10-23 | 2024-10-27 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-23 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-24 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-24 | 2024-10-24 | 2024-10-28 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-10-24 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401
2024-10-24 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401
2024-10-24 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-24 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-24 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-10-24 | 2024-10-23 | 2024-10-27 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-24 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-25 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-25 | 2024-10-24 | 2024-10-28 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-10-25 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401
2024-10-25 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401
2024-10-25 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-25 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-25 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-10-25 | 2024-10-23 | 2024-10-27 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-25 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-26 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-26 | 2024-10-24 | 2024-10-28 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-10-26 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401
2024-10-26 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401
2024-10-26 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-26 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-26 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-10-26 | 2024-10-23 | 2024-10-27 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-26 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-27 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-27 | 2024-10-24 | 2024-10-28 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-10-27 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401
2024-10-27 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401
2024-10-27 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401
2024-10-27 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401
2024-10-27 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-27 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-27 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-10-27 | 2024-10-23 | 2024-10-27 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-27 | 2024-10-27 | 2024-10-31 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-27 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-28 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-28 | 2024-10-24 | 2024-10-28 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-10-28 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401
2024-10-28 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401
2024-10-28 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401
2024-10-28 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401
2024-10-28 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-28 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
2024-10-28 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-10-28 | 2024-10-27 | 2024-10-31 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-28 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-29 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-29 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401
2024-10-29 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401
2024-10-29 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401
2024-10-29 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401
2024-10-29 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-29 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-10-29 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-10-29 | 2024-10-27 | 2024-10-31 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-30 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-30 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401
2024-10-30 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-10-30 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401
2024-10-30 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401
2024-10-30 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401
2024-10-30 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-30 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-10-30 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-10-30 | 2024-10-27 | 2024-10-31 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-31 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-10-31 | 2024-10-31 | 2024-11-03 | Deglal Mahto | 47.148 | 11.787 | TB401
2024-10-31 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-10-31 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401
2024-10-31 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401
2024-10-31 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401
2024-10-31 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-10-31 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-10-31 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-10-31 | 2024-10-27 | 2024-10-31 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-01 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-11-01 | 2024-11-01 | 2024-11-05 | Chinta Devi | 38.847 | 7.7694 | TB401
2024-11-01 | 2024-10-31 | 2024-11-03 | Deglal Mahto | 47.148 | 11.787 | TB401
2024-11-01 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-11-01 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401
2024-11-01 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401
2024-11-01 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401
2024-11-01 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-01 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-11-01 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-01 | 2024-11-01 | 2024-11-05 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-02 | 2024-11-01 | 2024-11-05 | Chinta Devi | 38.847 | 7.7694 | TB401
2024-11-02 | 2024-10-31 | 2024-11-03 | Deglal Mahto | 47.148 | 11.787 | TB401
2024-11-02 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-11-02 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401
2024-11-02 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401
2024-11-02 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-02 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-11-02 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-02 | 2024-11-01 | 2024-11-05 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-02 | 2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401
2024-11-03 | 2024-11-01 | 2024-11-05 | Chinta Devi | 38.847 | 7.7694 | TB401
2024-11-03 | 2024-10-31 | 2024-11-03 | Deglal Mahto | 47.148 | 11.787 | TB401
2024-11-03 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-11-03 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401
2024-11-03 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-03 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-11-03 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-03 | 2024-11-01 | 2024-11-05 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-03 | 2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401
2024-11-04 | 2024-11-01 | 2024-11-05 | Chinta Devi | 38.847 | 7.7694 | TB401
2024-11-04 | 2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-04 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-11-04 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401
2024-11-04 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-04 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-11-04 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-04 | 2024-11-01 | 2024-11-05 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-04 | 2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401
2024-11-05 | 2024-11-01 | 2024-11-05 | Chinta Devi | 38.847 | 7.7694 | TB401
2024-11-05 | 2024-11-05 | 2024-11-09 | Chinta Devi | 38.847 | 7.7694 | TB401
2024-11-05 | 2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-05 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-11-05 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-05 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-11-05 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-05 | 2024-11-01 | 2024-11-05 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-05 | 2024-11-05 | 2024-11-09 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-05 | 2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401
2024-11-06 | 2024-11-05 | 2024-11-09 | Chinta Devi | 38.847 | 7.7694 | TB401
2024-11-06 | 2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-06 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-11-06 | 2024-11-06 | 2024-11-10 | Jagdish Mahto | 60.096 | 12.0192 | TB401
2024-11-06 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-06 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-11-06 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-06 | 2024-11-05 | 2024-11-09 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-06 | 2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401
2024-11-07 | 2024-11-05 | 2024-11-09 | Chinta Devi | 38.847 | 7.7694 | TB401
2024-11-07 | 2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-07 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-11-07 | 2024-11-06 | 2024-11-10 | Jagdish Mahto | 60.096 | 12.0192 | TB401
2024-11-07 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-07 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-11-07 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-07 | 2024-11-05 | 2024-11-09 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-07 | 2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401
2024-11-08 | 2024-11-05 | 2024-11-09 | Chinta Devi | 38.847 | 7.7694 | TB401
2024-11-08 | 2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-08 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-11-08 | 2024-11-06 | 2024-11-10 | Jagdish Mahto | 60.096 | 12.0192 | TB401
2024-11-08 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-08 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-11-08 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-08 | 2024-11-05 | 2024-11-09 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-09 | 2024-11-05 | 2024-11-09 | Chinta Devi | 38.847 | 7.7694 | TB401
2024-11-09 | 2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-09 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-11-09 | 2024-11-06 | 2024-11-10 | Jagdish Mahto | 60.096 | 12.0192 | TB401
2024-11-09 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-09 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-11-09 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-09 | 2024-11-05 | 2024-11-09 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-09 | 2024-11-09 | 2024-11-13 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-10 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-10 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-11-10 | 2024-11-06 | 2024-11-10 | Jagdish Mahto | 60.096 | 12.0192 | TB401
2024-11-10 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-10 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-11-10 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-10 | 2024-11-09 | 2024-11-13 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-11 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-11 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401
2024-11-11 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-11-11 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401
2024-11-11 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-11 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-11 | 2024-11-09 | 2024-11-13 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-12 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-12 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401
2024-11-12 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401
2024-11-12 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-12 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-12 | 2024-11-09 | 2024-11-13 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-13 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-13 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401
2024-11-13 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401
2024-11-13 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-13 | 2024-11-09 | 2024-11-13 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-13 | 2024-11-13 | 2024-11-17 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-14 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-14 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401
2024-11-14 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401
2024-11-14 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-14 | 2024-11-13 | 2024-11-17 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-15 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-15 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401
2024-11-15 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401
2024-11-15 | 2024-11-13 | 2024-11-17 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-16 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-16 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401
2024-11-16 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401
2024-11-16 | 2024-11-13 | 2024-11-17 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-17 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-17 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401
2024-11-17 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401
2024-11-17 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-17 | 2024-11-13 | 2024-11-17 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-18 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-18 | 2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-18 | 2024-11-18 | 2024-11-21 | Jagdish Mahto | 38.847 | 9.7118 | TB401
2024-11-18 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-18 | 2024-11-18 | 2024-11-22 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-19 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-19 | 2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-19 | 2024-11-18 | 2024-11-21 | Jagdish Mahto | 38.847 | 9.7118 | TB401
2024-11-19 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401
2024-11-19 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-19 | 2024-11-18 | 2024-11-22 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-20 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-20 | 2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-20 | 2024-11-18 | 2024-11-21 | Jagdish Mahto | 38.847 | 9.7118 | TB401
2024-11-20 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401
2024-11-20 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-20 | 2024-11-18 | 2024-11-22 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-21 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-21 | 2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-21 | 2024-11-18 | 2024-11-21 | Jagdish Mahto | 38.847 | 9.7118 | TB401
2024-11-21 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401
2024-11-21 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-21 | 2024-11-18 | 2024-11-22 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-22 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-11-22 | 2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-22 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401
2024-11-22 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401
2024-11-22 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-22 | 2024-11-18 | 2024-11-22 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-23 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-11-23 | 2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-23 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401
2024-11-23 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401
2024-11-23 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-23 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401
2024-11-24 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-11-24 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401
2024-11-24 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401
2024-11-24 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-24 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401
2024-11-25 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-11-25 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401
2024-11-25 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401
2024-11-25 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-25 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401
2024-11-26 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-11-26 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401
2024-11-26 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-26 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401
2024-11-27 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-11-27 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401
2024-11-27 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-27 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401
2024-11-28 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-11-28 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401
2024-11-28 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-28 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401
2024-11-28 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-11-29 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-11-29 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401
2024-11-29 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401
2024-11-29 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-11-30 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401
2024-11-30 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-01 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-12-01 | 2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-12-01 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-02 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-12-02 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401
2024-12-02 | 2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-12-02 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-03 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-12-03 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401
2024-12-03 | 2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-12-03 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-04 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-12-04 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401
2024-12-04 | 2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-12-04 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-05 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-12-05 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401
2024-12-05 | 2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-12-05 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-06 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-12-06 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401
2024-12-06 | 2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-12-06 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-07 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-07 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-12-07 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-07 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401
2024-12-07 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401
2024-12-07 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-08 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-08 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-12-08 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-08 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401
2024-12-08 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401
2024-12-08 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-09 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-09 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2024-12-09 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-09 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401
2024-12-09 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-10 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-10 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2024-12-10 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-10 | 2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401
2024-12-10 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401
2024-12-10 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-11 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-11 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2024-12-11 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-11 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-11 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401
2024-12-11 | 2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401
2024-12-11 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401
2024-12-11 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-12 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-12 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2024-12-12 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-12 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-12 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401
2024-12-12 | 2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401
2024-12-12 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401
2024-12-12 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-13 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-13 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2024-12-13 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-13 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-13 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401
2024-12-13 | 2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401
2024-12-13 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401
2024-12-13 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-14 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-14 | 2024-12-14 | 2024-12-18 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-12-14 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2024-12-14 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-14 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-14 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401
2024-12-14 | 2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401
2024-12-14 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401
2024-12-14 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-15 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-15 | 2024-12-14 | 2024-12-18 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-12-15 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2024-12-15 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-15 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-15 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401
2024-12-15 | 2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401
2024-12-15 | 2024-12-15 | 2024-12-19 | Sobha Devi | 45.413 | 9.0826 | TB401
2024-12-15 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401
2024-12-15 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-16 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-16 | 2024-12-14 | 2024-12-18 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-12-16 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2024-12-16 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-16 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-16 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401
2024-12-16 | 2024-12-15 | 2024-12-19 | Sobha Devi | 45.413 | 9.0826 | TB401
2024-12-16 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401
2024-12-16 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-17 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-17 | 2024-12-14 | 2024-12-18 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-12-17 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401
2024-12-17 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2024-12-17 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-17 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-17 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401
2024-12-17 | 2024-12-15 | 2024-12-19 | Sobha Devi | 45.413 | 9.0826 | TB401
2024-12-17 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401
2024-12-17 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-18 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-18 | 2024-12-14 | 2024-12-18 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-12-18 | 2024-12-18 | 2024-12-22 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-12-18 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401
2024-12-18 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-18 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-18 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401
2024-12-18 | 2024-12-15 | 2024-12-19 | Sobha Devi | 45.413 | 9.0826 | TB401
2024-12-18 | 2024-12-18 | 2024-12-22 | Sunny Const | 37.504 | 7.5008 | TB401
2024-12-18 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-19 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-19 | 2024-12-18 | 2024-12-22 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-12-19 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401
2024-12-19 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-19 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-19 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-19 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401
2024-12-19 | 2024-12-15 | 2024-12-19 | Sobha Devi | 45.413 | 9.0826 | TB401
2024-12-19 | 2024-12-18 | 2024-12-22 | Sunny Const | 37.504 | 7.5008 | TB401
2024-12-19 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-20 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-20 | 2024-12-18 | 2024-12-22 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-12-20 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401
2024-12-20 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-20 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-20 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-20 | 2024-12-20 | 2024-12-24 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-12-20 | 2024-12-18 | 2024-12-22 | Sunny Const | 37.504 | 7.5008 | TB401
2024-12-20 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-21 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-21 | 2024-12-18 | 2024-12-22 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-12-21 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401
2024-12-21 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-21 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-21 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-21 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401
2024-12-21 | 2024-12-20 | 2024-12-24 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-12-21 | 2024-12-18 | 2024-12-22 | Sunny Const | 37.504 | 7.5008 | TB401
2024-12-22 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-22 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401
2024-12-22 | 2024-12-18 | 2024-12-22 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-12-22 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401
2024-12-22 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401
2024-12-22 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-22 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-22 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-22 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401
2024-12-22 | 2024-12-20 | 2024-12-24 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-12-22 | 2024-12-18 | 2024-12-22 | Sunny Const | 37.504 | 7.5008 | TB401
2024-12-22 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401
2024-12-23 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401
2024-12-23 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401
2024-12-23 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401
2024-12-23 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-23 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-23 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-23 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401
2024-12-23 | 2024-12-20 | 2024-12-24 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-12-23 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401
2024-12-24 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401
2024-12-24 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401
2024-12-24 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401
2024-12-24 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-24 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-24 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-24 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401
2024-12-24 | 2024-12-20 | 2024-12-24 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-12-24 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401
2024-12-25 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401
2024-12-25 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401
2024-12-25 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-25 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2024-12-25 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401
2024-12-25 | 2024-12-25 | 2024-12-28 | Sobha Devi | 37.504 | 9.376 | TB401
2024-12-25 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401
2024-12-26 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401
2024-12-26 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401
2024-12-26 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-26 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2024-12-26 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401
2024-12-26 | 2024-12-25 | 2024-12-28 | Sobha Devi | 37.504 | 9.376 | TB401
2024-12-26 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401
2024-12-27 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401
2024-12-27 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401
2024-12-27 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-27 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2024-12-27 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401
2024-12-27 | 2024-12-25 | 2024-12-28 | Sobha Devi | 37.504 | 9.376 | TB401
2024-12-27 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401
2024-12-28 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401
2024-12-28 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401
2024-12-28 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-28 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2024-12-28 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401
2024-12-28 | 2024-12-25 | 2024-12-28 | Sobha Devi | 37.504 | 9.376 | TB401
2024-12-28 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401
2024-12-29 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401
2024-12-29 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401
2024-12-29 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-29 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2024-12-29 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401
2024-12-29 | 2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401
2024-12-29 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401
2024-12-30 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401
2024-12-30 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401
2024-12-30 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-30 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2024-12-30 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401
2024-12-30 | 2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401
2024-12-30 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401
2024-12-31 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401
2024-12-31 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-31 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2024-12-31 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401
2024-12-31 | 2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401
2024-12-31 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401
2025-01-01 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2025-01-01 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401
2025-01-01 | 2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401
2025-01-02 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2025-01-02 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401
2025-01-02 | 2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401
2025-01-03 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2025-01-03 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401
2025-01-03 | 2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401
2025-01-04 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2025-01-04 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401
2025-01-04 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-01-05 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2025-01-05 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401
2025-01-05 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-01-06 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
2025-01-06 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401
2025-01-06 | 2025-01-06 | 2025-01-10 | Sanjeev Kumar | 37.504 | 7.5008 | TB401
2025-01-06 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-01-07 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401
2025-01-07 | 2025-01-06 | 2025-01-10 | Sanjeev Kumar | 37.504 | 7.5008 | TB401
2025-01-07 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-01-08 | 2025-01-06 | 2025-01-10 | Sanjeev Kumar | 37.504 | 7.5008 | TB401
2025-01-08 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-01-09 | 2025-01-06 | 2025-01-10 | Sanjeev Kumar | 37.504 | 7.5008 | TB401
2025-01-09 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-01-10 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401
2025-01-10 | 2025-01-06 | 2025-01-10 | Sanjeev Kumar | 37.504 | 7.5008 | TB401
2025-01-10 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-01-10 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401
2025-01-10 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-11 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401
2025-01-11 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401
2025-01-11 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-12 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401
2025-01-12 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401
2025-01-12 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-13 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401
2025-01-13 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401
2025-01-13 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-14 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401
2025-01-14 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401
2025-01-14 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-15 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401
2025-01-15 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401
2025-01-15 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-16 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401
2025-01-16 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401
2025-01-16 | 2025-01-16 | 2025-01-20 | Sobha Devi | 45.413 | 9.0826 | TB401
2025-01-16 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-17 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401
2025-01-17 | 2025-01-16 | 2025-01-20 | Sobha Devi | 45.413 | 9.0826 | TB401
2025-01-17 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-18 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-18 | 2025-01-16 | 2025-01-20 | Sobha Devi | 45.413 | 9.0826 | TB401
2025-01-18 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-19 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-19 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-19 | 2025-01-16 | 2025-01-20 | Sobha Devi | 45.413 | 9.0826 | TB401
2025-01-19 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-20 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-20 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-20 | 2025-01-16 | 2025-01-20 | Sobha Devi | 45.413 | 9.0826 | TB401
2025-01-20 | 2025-01-20 | 2025-01-24 | Sobha Devi | 38.847 | 7.7694 | TB401
2025-01-20 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-21 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-21 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-21 | 2025-01-20 | 2025-01-24 | Sobha Devi | 38.847 | 7.7694 | TB401
2025-01-21 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-22 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-22 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-22 | 2025-01-20 | 2025-01-24 | Sobha Devi | 38.847 | 7.7694 | TB401
2025-01-22 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-23 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-23 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-23 | 2025-01-20 | 2025-01-24 | Sobha Devi | 38.847 | 7.7694 | TB401
2025-01-23 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-24 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-24 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-24 | 2025-01-20 | 2025-01-24 | Sobha Devi | 38.847 | 7.7694 | TB401
2025-01-24 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-25 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-25 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-25 | 2025-01-25 | 2025-01-28 | Sobha Devi | 37.504 | 9.376 | TB401
2025-01-25 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-26 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-26 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-26 | 2025-01-25 | 2025-01-28 | Sobha Devi | 37.504 | 9.376 | TB401
2025-01-26 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-27 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-27 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-27 | 2025-01-25 | 2025-01-28 | Sobha Devi | 37.504 | 9.376 | TB401
2025-01-27 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-28 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-28 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-28 | 2025-01-25 | 2025-01-28 | Sobha Devi | 37.504 | 9.376 | TB401
2025-01-28 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-29 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-29 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401
2025-01-29 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-29 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401
2025-01-29 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-30 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401
2025-01-30 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-30 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401
2025-01-30 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2025-01-31 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-01-31 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401
2025-01-31 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-01-31 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401
2025-02-01 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-01 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401
2025-02-01 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-01 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401
2025-02-02 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-02 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401
2025-02-02 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-02 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401
2025-02-03 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-03 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401
2025-02-03 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-03 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401
2025-02-04 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-04 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401
2025-02-04 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-04 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401
2025-02-05 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-05 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401
2025-02-05 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-06 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-06 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401
2025-02-06 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-07 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-07 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401
2025-02-07 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-07 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-08 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-08 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401
2025-02-08 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-08 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-09 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-09 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-09 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-09 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-10 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-10 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-10 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-10 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-11 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-11 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-11 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-11 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-12 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-12 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-12 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-12 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-13 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-13 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-13 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-13 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-14 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-14 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-14 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-14 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-15 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-15 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-15 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-15 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-15 | 2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-16 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-16 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-16 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-16 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-16 | 2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-17 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-17 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-17 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-17 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-17 | 2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-18 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-18 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-18 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-18 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-18 | 2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-19 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401
2025-02-19 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-19 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-19 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-19 | 2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-20 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401
2025-02-20 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-20 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-02-20 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-20 | 2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-21 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401
2025-02-21 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-21 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-02-21 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-21 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401
2025-02-21 | 2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-22 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401
2025-02-22 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-22 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-02-22 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-22 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401
2025-02-22 | 2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-23 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401
2025-02-23 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-23 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-02-23 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-23 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401
2025-02-23 | 2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-24 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401
2025-02-24 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-02-24 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-24 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401
2025-02-24 | 2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-25 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401
2025-02-25 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-02-25 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-25 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401
2025-02-25 | 2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-26 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401
2025-02-26 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-02-26 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-26 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401
2025-02-26 | 2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-27 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401
2025-02-27 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-02-27 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-27 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401
2025-02-27 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401
2025-02-28 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401
2025-02-28 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-02-28 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-02-28 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401
2025-02-28 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401
2025-03-01 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401
2025-03-01 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-03-01 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-01 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-03-01 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401
2025-03-02 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401
2025-03-02 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-03-02 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-02 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-03-02 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401
2025-03-03 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401
2025-03-03 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-03-03 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-03 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-03-03 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401
2025-03-04 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401
2025-03-04 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-04 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-03-04 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401
2025-03-05 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401
2025-03-05 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-05 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-03-05 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401
2025-03-06 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401
2025-03-06 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-06 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-03-06 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401
2025-03-07 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401
2025-03-07 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-07 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-03-08 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401
2025-03-08 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-08 | 2025-03-08 | 2025-03-11 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-08 | 2025-03-08 | 2025-03-12 | Sunny Const | 37.504 | 7.5008 | TB401
2025-03-09 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401
2025-03-09 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-09 | 2025-03-08 | 2025-03-11 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-09 | 2025-03-08 | 2025-03-12 | Sunny Const | 37.504 | 7.5008 | TB401
2025-03-10 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-10 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-10 | 2025-03-08 | 2025-03-11 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-10 | 2025-03-08 | 2025-03-12 | Sunny Const | 37.504 | 7.5008 | TB401
2025-03-11 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-11 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-11 | 2025-03-08 | 2025-03-11 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-11 | 2025-03-08 | 2025-03-12 | Sunny Const | 37.504 | 7.5008 | TB401
2025-03-12 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-12 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-12 | 2025-03-08 | 2025-03-12 | Sunny Const | 37.504 | 7.5008 | TB401
2025-03-13 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-13 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-13 | 2025-03-13 | 2025-03-17 | Sobha Devi | 37.504 | 7.5008 | TB401
2025-03-13 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401
2025-03-14 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-14 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-14 | 2025-03-13 | 2025-03-17 | Sobha Devi | 37.504 | 7.5008 | TB401
2025-03-14 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401
2025-03-15 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-15 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-15 | 2025-03-13 | 2025-03-17 | Sobha Devi | 37.504 | 7.5008 | TB401
2025-03-15 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401
2025-03-16 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-16 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-16 | 2025-03-13 | 2025-03-17 | Sobha Devi | 37.504 | 7.5008 | TB401
2025-03-16 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401
2025-03-17 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-17 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-17 | 2025-03-13 | 2025-03-17 | Sobha Devi | 37.504 | 7.5008 | TB401
2025-03-17 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401
2025-03-18 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-18 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-18 | 2025-03-18 | 2025-03-21 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-18 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401
2025-03-19 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-19 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-19 | 2025-03-18 | 2025-03-21 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-19 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401
2025-03-20 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-20 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-20 | 2025-03-18 | 2025-03-21 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-20 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401
2025-03-21 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-21 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-21 | 2025-03-18 | 2025-03-21 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-21 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401
2025-03-22 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-22 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-22 | 2025-03-22 | 2025-03-25 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-22 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401
2025-03-23 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-23 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-23 | 2025-03-22 | 2025-03-25 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-23 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401
2025-03-24 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-24 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-24 | 2025-03-22 | 2025-03-25 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-24 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401
2025-03-25 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-25 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-25 | 2025-03-22 | 2025-03-25 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-25 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401
2025-03-26 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-26 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-26 | 2025-03-26 | 2025-03-29 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-26 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401
2025-03-27 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
2025-03-27 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-27 | 2025-03-26 | 2025-03-29 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-27 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401
2025-03-28 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-28 | 2025-03-26 | 2025-03-29 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-28 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401
2025-03-29 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-29 | 2025-03-26 | 2025-03-29 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-30 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-03-31 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-01 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-02 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-03 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-04 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-05 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-06 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-06 | 2025-04-06 | 2025-04-10 | Sobha Devi | 38.847 | 7.7694 | TB401
2025-04-07 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-07 | 2025-04-06 | 2025-04-10 | Sobha Devi | 38.847 | 7.7694 | TB401
2025-04-08 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-08 | 2025-04-06 | 2025-04-10 | Sobha Devi | 38.847 | 7.7694 | TB401
2025-04-09 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-09 | 2025-04-06 | 2025-04-10 | Sobha Devi | 38.847 | 7.7694 | TB401
2025-04-10 | 2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-10 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-10 | 2025-04-06 | 2025-04-10 | Sobha Devi | 38.847 | 7.7694 | TB401
2025-04-11 | 2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-11 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-11 | 2025-04-11 | 2025-04-14 | Sobha Devi | 37.504 | 9.376 | TB401
2025-04-12 | 2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-12 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-12 | 2025-04-11 | 2025-04-14 | Sobha Devi | 37.504 | 9.376 | TB401
2025-04-13 | 2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-13 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-13 | 2025-04-11 | 2025-04-14 | Sobha Devi | 37.504 | 9.376 | TB401
2025-04-14 | 2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-14 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-14 | 2025-04-11 | 2025-04-14 | Sobha Devi | 37.504 | 9.376 | TB401
2025-04-15 | 2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-15 | 2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-15 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-15 | 2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401
2025-04-15 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401
2025-04-16 | 2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-16 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-16 | 2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401
2025-04-16 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401
2025-04-17 | 2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-17 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-17 | 2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401
2025-04-17 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401
2025-04-18 | 2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-18 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-18 | 2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401
2025-04-18 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401
2025-04-19 | 2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-19 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-19 | 2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401
2025-04-19 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401
2025-04-20 | 2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-20 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-20 | 2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401
2025-04-20 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401
2025-04-21 | 2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401
2025-04-21 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-21 | 2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401
2025-04-21 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401
2025-04-21 | 2025-04-21 | 2025-04-25 | Sunny Const | 37.504 | 7.5008 | TB401
2025-04-22 | 2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401
2025-04-22 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-22 | 2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401
2025-04-22 | 2025-04-21 | 2025-04-25 | Sunny Const | 37.504 | 7.5008 | TB401
2025-04-23 | 2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401
2025-04-23 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-23 | 2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401
2025-04-23 | 2025-04-21 | 2025-04-25 | Sunny Const | 37.504 | 7.5008 | TB401
2025-04-24 | 2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401
2025-04-24 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-04-24 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-24 | 2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401
2025-04-24 | 2025-04-21 | 2025-04-25 | Sunny Const | 37.504 | 7.5008 | TB401
2025-04-25 | 2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401
2025-04-25 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-04-25 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-25 | 2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401
2025-04-25 | 2025-04-21 | 2025-04-25 | Sunny Const | 37.504 | 7.5008 | TB401
2025-04-26 | 2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401
2025-04-26 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-04-26 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-26 | 2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401
2025-04-26 | 2025-04-26 | 2025-04-30 | Sobha Devi | 37.504 | 7.5008 | TB401
2025-04-26 | 2025-04-26 | 2025-04-30 | Sunny Const | 38.847 | 7.7694 | TB401
2025-04-27 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-04-27 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-27 | 2025-04-26 | 2025-04-30 | Sobha Devi | 37.504 | 7.5008 | TB401
2025-04-27 | 2025-04-26 | 2025-04-30 | Sunny Const | 38.847 | 7.7694 | TB401
2025-04-28 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-04-28 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-28 | 2025-04-26 | 2025-04-30 | Sobha Devi | 37.504 | 7.5008 | TB401
2025-04-28 | 2025-04-26 | 2025-04-30 | Sunny Const | 38.847 | 7.7694 | TB401
2025-04-29 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-04-29 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-04-29 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-29 | 2025-04-26 | 2025-04-30 | Sobha Devi | 37.504 | 7.5008 | TB401
2025-04-29 | 2025-04-26 | 2025-04-30 | Sunny Const | 38.847 | 7.7694 | TB401
2025-04-30 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-04-30 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-04-30 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401
2025-04-30 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401
2025-04-30 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-04-30 | 2025-04-26 | 2025-04-30 | Sobha Devi | 37.504 | 7.5008 | TB401
2025-04-30 | 2025-04-26 | 2025-04-30 | Sunny Const | 38.847 | 7.7694 | TB401
2025-04-30 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401
2025-05-01 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-01 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-01 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401
2025-05-01 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401
2025-05-01 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-01 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401
2025-05-02 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-02 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-02 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401
2025-05-02 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401
2025-05-02 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-02 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401
2025-05-03 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-03 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-03 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401
2025-05-03 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401
2025-05-03 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-03 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401
2025-05-04 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-04 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-04 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-04 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401
2025-05-04 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401
2025-05-04 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-04 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401
2025-05-05 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-05 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-05 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-05 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401
2025-05-05 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401
2025-05-05 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-05 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401
2025-05-06 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-06 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-06 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-06 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401
2025-05-06 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401
2025-05-06 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-06 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401
2025-05-07 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-07 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-07 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-07 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-07 | 2025-05-07 | 2025-05-11 | Satyam Nitish | 37.504 | 7.5008 | TB401
2025-05-07 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-07 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401
2025-05-08 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-08 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-08 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-08 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-08 | 2025-05-07 | 2025-05-11 | Satyam Nitish | 37.504 | 7.5008 | TB401
2025-05-08 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-08 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401
2025-05-09 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-09 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-09 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-09 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-09 | 2025-05-07 | 2025-05-11 | Satyam Nitish | 37.504 | 7.5008 | TB401
2025-05-09 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-09 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401
2025-05-10 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-10 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-10 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-10 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-10 | 2025-05-07 | 2025-05-11 | Satyam Nitish | 37.504 | 7.5008 | TB401
2025-05-10 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-11 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-11 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-11 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-11 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-11 | 2025-05-07 | 2025-05-11 | Satyam Nitish | 37.504 | 7.5008 | TB401
2025-05-11 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-12 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-12 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-12 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-12 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-12 | 2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401
2025-05-12 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-12 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-12 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401
2025-05-13 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-13 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-05-13 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-13 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-13 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-13 | 2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401
2025-05-13 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-13 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-13 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401
2025-05-14 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-14 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-14 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-14 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-14 | 2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401
2025-05-14 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-14 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-14 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401
2025-05-15 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-15 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-15 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-15 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-15 | 2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401
2025-05-15 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-15 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-15 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-15 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401
2025-05-16 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-16 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-16 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-16 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-16 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-16 | 2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401
2025-05-16 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-16 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-16 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-16 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401
2025-05-17 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-17 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-17 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-17 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-17 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-17 | 2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401
2025-05-17 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401
2025-05-17 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-17 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-17 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-17 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401
2025-05-18 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-18 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-18 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-18 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-18 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-18 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401
2025-05-18 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-18 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-18 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-18 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401
2025-05-19 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-19 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-19 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-19 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-19 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-19 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401
2025-05-19 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-19 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-19 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-19 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401
2025-05-20 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-20 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-20 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-05-20 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-20 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-20 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-20 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401
2025-05-20 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-20 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-20 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-21 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-21 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-21 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-05-21 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-21 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-21 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-21 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401
2025-05-21 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-21 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-21 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-22 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-22 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-22 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-05-22 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-22 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-22 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-22 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401
2025-05-22 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-22 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-22 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-23 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-23 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-23 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-05-23 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-23 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-23 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-23 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401
2025-05-23 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-23 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-23 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-24 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-24 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-24 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-05-24 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-24 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401
2025-05-24 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-24 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401
2025-05-24 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-24 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401
2025-05-24 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-25 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-25 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-25 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-05-25 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-25 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401
2025-05-25 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-25 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-25 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401
2025-05-25 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-26 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-26 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-26 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-05-26 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-26 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401
2025-05-26 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-05-26 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-26 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401
2025-05-26 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-27 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-27 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-27 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-05-27 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-27 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401
2025-05-27 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401
2025-05-27 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-05-27 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-27 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401
2025-05-27 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-28 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-28 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-28 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-05-28 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401
2025-05-28 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-28 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401
2025-05-28 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401
2025-05-28 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-05-28 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-28 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401
2025-05-29 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-29 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-29 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-05-29 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401
2025-05-29 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-29 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401
2025-05-29 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401
2025-05-29 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-05-29 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-29 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401
2025-05-29 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401
2025-05-30 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-30 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-30 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-05-30 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401
2025-05-30 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-30 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401
2025-05-30 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401
2025-05-30 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-05-30 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-05-30 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-30 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401
2025-05-30 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401
2025-05-31 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-31 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-05-31 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-05-31 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401
2025-05-31 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-05-31 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401
2025-05-31 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401
2025-05-31 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-05-31 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-05-31 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-05-31 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401
2025-05-31 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401
2025-06-01 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-06-01 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-01 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-01 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401
2025-06-01 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-01 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401
2025-06-01 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401
2025-06-01 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-01 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-01 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-06-01 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401
2025-06-02 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-06-02 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-02 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-02 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401
2025-06-02 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-02 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401
2025-06-02 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401
2025-06-02 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-02 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-02 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-06-02 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401
2025-06-03 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-06-03 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-03 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-03 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401
2025-06-03 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-03 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401
2025-06-03 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401
2025-06-03 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-03 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-03 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-06-03 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401
2025-06-04 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-06-04 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-04 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-04 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401
2025-06-04 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-04 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401
2025-06-04 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-04 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-04 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-06-04 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401
2025-06-05 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-06-05 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-05 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-05 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401
2025-06-05 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-05 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401
2025-06-05 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-05 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-05 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-06-05 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401
2025-06-06 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-06 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-06 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401
2025-06-06 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-06 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401
2025-06-06 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-06 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-06 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-06-06 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401
2025-06-07 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-07 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-07 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401
2025-06-07 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-07 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-07 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-07 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-06-07 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401
2025-06-08 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-08 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-08 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401
2025-06-08 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-08 | 2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401
2025-06-08 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-08 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-08 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-08 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-06-08 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401
2025-06-09 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-09 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-09 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401
2025-06-09 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401
2025-06-09 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-09 | 2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401
2025-06-09 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-09 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-09 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-09 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-06-10 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-10 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-10 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401
2025-06-10 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401
2025-06-10 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-10 | 2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401
2025-06-10 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-10 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-10 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-10 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401
2025-06-10 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-11 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-11 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-11 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401
2025-06-11 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401
2025-06-11 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-11 | 2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401
2025-06-11 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-11 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-11 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-11 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401
2025-06-11 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-12 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-12 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-12 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401
2025-06-12 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401
2025-06-12 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-12 | 2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401
2025-06-12 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-12 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-12 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-12 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401
2025-06-12 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-13 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-13 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-13 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401
2025-06-13 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401
2025-06-13 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-13 | 2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401
2025-06-13 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-13 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-13 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-13 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401
2025-06-13 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-14 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-14 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-14 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401
2025-06-14 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401
2025-06-14 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-14 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-14 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-14 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-14 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401
2025-06-14 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-15 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-15 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-15 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401
2025-06-15 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401
2025-06-15 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-15 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-15 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-15 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-06-15 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401
2025-06-15 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-16 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-16 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401
2025-06-16 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-16 | 2025-06-16 | 2025-06-18 | Satyam Manish | 37.504 | 12.5013 | TB401
2025-06-16 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-16 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401
2025-06-16 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-17 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-17 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401
2025-06-17 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-17 | 2025-06-16 | 2025-06-18 | Satyam Manish | 37.504 | 12.5013 | TB401
2025-06-17 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-17 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-17 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401
2025-06-17 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-18 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-18 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401
2025-06-18 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401
2025-06-18 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-18 | 2025-06-16 | 2025-06-18 | Satyam Manish | 37.504 | 12.5013 | TB401
2025-06-18 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-18 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-18 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-18 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401
2025-06-18 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-19 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-19 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401
2025-06-19 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-19 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-19 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-19 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-19 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401
2025-06-19 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-20 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-20 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401
2025-06-20 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-20 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-20 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-20 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-20 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-21 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-21 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401
2025-06-21 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-21 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-21 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-21 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-21 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-22 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-22 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401
2025-06-22 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401
2025-06-22 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-22 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-22 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-22 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-22 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-23 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-23 | 2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401
2025-06-23 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401
2025-06-23 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401
2025-06-23 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-06-23 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-23 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-23 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-23 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-23 | 2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401
2025-06-23 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-06-24 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-06-24 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-24 | 2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401
2025-06-24 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401
2025-06-24 | 2025-06-24 | 2025-06-27 | Jwala Singh 3 | 38.847 | 9.7118 | TB401
2025-06-24 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401
2025-06-24 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-06-24 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-24 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-24 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-24 | 2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401
2025-06-24 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-06-25 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-06-25 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-25 | 2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401
2025-06-25 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401
2025-06-25 | 2025-06-24 | 2025-06-27 | Jwala Singh 3 | 38.847 | 9.7118 | TB401
2025-06-25 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401
2025-06-25 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-06-25 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-25 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-25 | 2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401
2025-06-25 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-25 | 2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401
2025-06-25 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-06-26 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-06-26 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-26 | 2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401
2025-06-26 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401
2025-06-26 | 2025-06-24 | 2025-06-27 | Jwala Singh 3 | 38.847 | 9.7118 | TB401
2025-06-26 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401
2025-06-26 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-06-26 | 2025-06-26 | 2025-06-30 | Pusplata 4 | 38.847 | 7.7694 | TB401
2025-06-26 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-26 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-26 | 2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401
2025-06-26 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-26 | 2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401
2025-06-26 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-06-27 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-06-27 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-27 | 2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401
2025-06-27 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401
2025-06-27 | 2025-06-24 | 2025-06-27 | Jwala Singh 3 | 38.847 | 9.7118 | TB401
2025-06-27 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401
2025-06-27 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-06-27 | 2025-06-27 | 2025-06-30 | Pusplata 1 | 45.413 | 11.3532 | TB401
2025-06-27 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401
2025-06-27 | 2025-06-26 | 2025-06-30 | Pusplata 4 | 38.847 | 7.7694 | TB401
2025-06-27 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401
2025-06-27 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-27 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-27 | 2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401
2025-06-27 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-27 | 2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401
2025-06-27 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-06-28 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-06-28 | 2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401
2025-06-28 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401
2025-06-28 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-06-28 | 2025-06-27 | 2025-06-30 | Pusplata 1 | 45.413 | 11.3532 | TB401
2025-06-28 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401
2025-06-28 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401
2025-06-28 | 2025-06-26 | 2025-06-30 | Pusplata 4 | 38.847 | 7.7694 | TB401
2025-06-28 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401
2025-06-28 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401
2025-06-28 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-28 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-28 | 2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401
2025-06-28 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-28 | 2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401
2025-06-28 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-06-29 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-06-29 | 2025-06-29 | 2025-07-02 | Poonam | 37.504 | 9.376 | TB401
2025-06-29 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-06-29 | 2025-06-27 | 2025-06-30 | Pusplata 1 | 45.413 | 11.3532 | TB401
2025-06-29 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401
2025-06-29 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401
2025-06-29 | 2025-06-26 | 2025-06-30 | Pusplata 4 | 38.847 | 7.7694 | TB401
2025-06-29 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401
2025-06-29 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401
2025-06-29 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-29 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-29 | 2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401
2025-06-29 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-29 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-06-30 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-06-30 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401
2025-06-30 | 2025-06-30 | 2025-07-03 | Jwala Singh 2 | 37.504 | 9.376 | TB401
2025-06-30 | 2025-06-29 | 2025-07-02 | Poonam | 37.504 | 9.376 | TB401
2025-06-30 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-06-30 | 2025-06-27 | 2025-06-30 | Pusplata 1 | 45.413 | 11.3532 | TB401
2025-06-30 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401
2025-06-30 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401
2025-06-30 | 2025-06-26 | 2025-06-30 | Pusplata 4 | 38.847 | 7.7694 | TB401
2025-06-30 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401
2025-06-30 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401
2025-06-30 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-06-30 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-30 | 2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401
2025-06-30 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-30 | 2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401
2025-06-30 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-07-01 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-07-01 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401
2025-07-01 | 2025-06-30 | 2025-07-03 | Jwala Singh 2 | 37.504 | 9.376 | TB401
2025-07-01 | 2025-06-29 | 2025-07-02 | Poonam | 37.504 | 9.376 | TB401
2025-07-01 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-07-01 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401
2025-07-01 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401
2025-07-01 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401
2025-07-01 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401
2025-07-01 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-01 | 2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401
2025-07-01 | 2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401
2025-07-01 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-07-02 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-07-02 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401
2025-07-02 | 2025-06-30 | 2025-07-03 | Jwala Singh 2 | 37.504 | 9.376 | TB401
2025-07-02 | 2025-07-02 | 2025-07-06 | Jwala Singh 3 | 38.847 | 7.7694 | TB401
2025-07-02 | 2025-06-29 | 2025-07-02 | Poonam | 37.504 | 9.376 | TB401
2025-07-02 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-07-02 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401
2025-07-02 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401
2025-07-02 | 2025-07-02 | 2025-07-06 | Pusplata 4 | 38.847 | 7.7694 | TB401
2025-07-02 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401
2025-07-02 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401
2025-07-02 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-02 | 2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401
2025-07-02 | 2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401
2025-07-02 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-07-03 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-07-03 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401
2025-07-03 | 2025-06-30 | 2025-07-03 | Jwala Singh 2 | 37.504 | 9.376 | TB401
2025-07-03 | 2025-07-02 | 2025-07-06 | Jwala Singh 3 | 38.847 | 7.7694 | TB401
2025-07-03 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-07-03 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401
2025-07-03 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401
2025-07-03 | 2025-07-02 | 2025-07-06 | Pusplata 4 | 38.847 | 7.7694 | TB401
2025-07-03 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401
2025-07-03 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401
2025-07-03 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401
2025-07-03 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-03 | 2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401
2025-07-03 | 2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401
2025-07-03 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-07-04 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-07-04 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401
2025-07-04 | 2025-07-02 | 2025-07-06 | Jwala Singh 3 | 38.847 | 7.7694 | TB401
2025-07-04 | 2025-07-04 | 2025-07-07 | Poonam | 37.504 | 9.376 | TB401
2025-07-04 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-07-04 | 2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401
2025-07-04 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401
2025-07-04 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401
2025-07-04 | 2025-07-02 | 2025-07-06 | Pusplata 4 | 38.847 | 7.7694 | TB401
2025-07-04 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401
2025-07-04 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401
2025-07-04 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401
2025-07-04 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-04 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401
2025-07-04 | 2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401
2025-07-04 | 2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401
2025-07-04 | 2025-07-04 | 2025-07-08 | Satyam Nitish | 45.413 | 9.0826 | TB401
2025-07-04 | 2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401
2025-07-04 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-07-05 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-07-05 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401
2025-07-05 | 2025-07-02 | 2025-07-06 | Jwala Singh 3 | 38.847 | 7.7694 | TB401
2025-07-05 | 2025-07-04 | 2025-07-07 | Poonam | 37.504 | 9.376 | TB401
2025-07-05 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-05 | 2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401
2025-07-05 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401
2025-07-05 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401
2025-07-05 | 2025-07-02 | 2025-07-06 | Pusplata 4 | 38.847 | 7.7694 | TB401
2025-07-05 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401
2025-07-05 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401
2025-07-05 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401
2025-07-05 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-05 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401
2025-07-05 | 2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401
2025-07-05 | 2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401
2025-07-05 | 2025-07-04 | 2025-07-08 | Satyam Nitish | 45.413 | 9.0826 | TB401
2025-07-05 | 2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401
2025-07-05 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-07-06 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-07-06 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401
2025-07-06 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401
2025-07-06 | 2025-07-02 | 2025-07-06 | Jwala Singh 3 | 38.847 | 7.7694 | TB401
2025-07-06 | 2025-07-04 | 2025-07-07 | Poonam | 37.504 | 9.376 | TB401
2025-07-06 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-06 | 2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401
2025-07-06 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-06 | 2025-07-02 | 2025-07-06 | Pusplata 4 | 38.847 | 7.7694 | TB401
2025-07-06 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401
2025-07-06 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401
2025-07-06 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401
2025-07-06 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-06 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401
2025-07-06 | 2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401
2025-07-06 | 2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401
2025-07-06 | 2025-07-04 | 2025-07-08 | Satyam Nitish | 45.413 | 9.0826 | TB401
2025-07-06 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-07-07 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401
2025-07-07 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401
2025-07-07 | 2025-07-04 | 2025-07-07 | Poonam | 37.504 | 9.376 | TB401
2025-07-07 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-07 | 2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401
2025-07-07 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-07 | 2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401
2025-07-07 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401
2025-07-07 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401
2025-07-07 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401
2025-07-07 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-07 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401
2025-07-07 | 2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401
2025-07-07 | 2025-07-04 | 2025-07-08 | Satyam Nitish | 45.413 | 9.0826 | TB401
2025-07-07 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-07-08 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401
2025-07-08 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401
2025-07-08 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401
2025-07-08 | 2025-07-08 | 2025-07-11 | Poonam | 37.504 | 9.376 | TB401
2025-07-08 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-08 | 2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401
2025-07-08 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-08 | 2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401
2025-07-08 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401
2025-07-08 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401
2025-07-08 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401
2025-07-08 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-08 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401
2025-07-08 | 2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401
2025-07-08 | 2025-07-04 | 2025-07-08 | Satyam Nitish | 45.413 | 9.0826 | TB401
2025-07-08 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-07-09 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401
2025-07-09 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401
2025-07-09 | 2025-07-08 | 2025-07-11 | Poonam | 37.504 | 9.376 | TB401
2025-07-09 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-09 | 2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401
2025-07-09 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-09 | 2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401
2025-07-09 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401
2025-07-09 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-09 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401
2025-07-09 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-09 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401
2025-07-09 | 2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401
2025-07-09 | 2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401
2025-07-09 | 2025-07-09 | 2025-07-13 | Satyam Trivedi | 37.504 | 7.5008 | TB401
2025-07-09 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-07-10 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401
2025-07-10 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401
2025-07-10 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401
2025-07-10 | 2025-07-08 | 2025-07-11 | Poonam | 37.504 | 9.376 | TB401
2025-07-10 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-10 | 2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401
2025-07-10 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-10 | 2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401
2025-07-10 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401
2025-07-10 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-10 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401
2025-07-10 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-10 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401
2025-07-10 | 2025-07-10 | 2025-07-13 | Satyam Manish | 37.504 | 9.376 | TB401
2025-07-10 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-10 | 2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401
2025-07-10 | 2025-07-09 | 2025-07-13 | Satyam Trivedi | 37.504 | 7.5008 | TB401
2025-07-11 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401
2025-07-11 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401
2025-07-11 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401
2025-07-11 | 2025-07-11 | 2025-07-15 | Jwala Singh 3 | 38.847 | 7.7694 | TB401
2025-07-11 | 2025-07-08 | 2025-07-11 | Poonam | 37.504 | 9.376 | TB401
2025-07-11 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-11 | 2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401
2025-07-11 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-11 | 2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401
2025-07-11 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401
2025-07-11 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-11 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401
2025-07-11 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-11 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401
2025-07-11 | 2025-07-10 | 2025-07-13 | Satyam Manish | 37.504 | 9.376 | TB401
2025-07-11 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-11 | 2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401
2025-07-11 | 2025-07-09 | 2025-07-13 | Satyam Trivedi | 37.504 | 7.5008 | TB401
2025-07-11 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-11 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401
2025-07-12 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401
2025-07-12 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401
2025-07-12 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401
2025-07-12 | 2025-07-11 | 2025-07-15 | Jwala Singh 3 | 38.847 | 7.7694 | TB401
2025-07-12 | 2025-07-12 | 2025-07-16 | Poonam | 57.597 | 11.5194 | TB401
2025-07-12 | 2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401
2025-07-12 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-12 | 2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401
2025-07-12 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401
2025-07-12 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-12 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401
2025-07-12 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-12 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401
2025-07-12 | 2025-07-10 | 2025-07-13 | Satyam Manish | 37.504 | 9.376 | TB401
2025-07-12 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-12 | 2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401
2025-07-12 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-12 | 2025-07-09 | 2025-07-13 | Satyam Trivedi | 37.504 | 7.5008 | TB401
2025-07-12 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-12 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401
2025-07-13 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401
2025-07-13 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401
2025-07-13 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401
2025-07-13 | 2025-07-11 | 2025-07-15 | Jwala Singh 3 | 38.847 | 7.7694 | TB401
2025-07-13 | 2025-07-12 | 2025-07-16 | Poonam | 57.597 | 11.5194 | TB401
2025-07-13 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-13 | 2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401
2025-07-13 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-13 | 2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401
2025-07-13 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401
2025-07-13 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-13 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401
2025-07-13 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-13 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401
2025-07-13 | 2025-07-10 | 2025-07-13 | Satyam Manish | 37.504 | 9.376 | TB401
2025-07-13 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-13 | 2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401
2025-07-13 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-13 | 2025-07-09 | 2025-07-13 | Satyam Trivedi | 37.504 | 7.5008 | TB401
2025-07-13 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-13 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401
2025-07-14 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401
2025-07-14 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401
2025-07-14 | 2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401
2025-07-14 | 2025-07-11 | 2025-07-15 | Jwala Singh 3 | 38.847 | 7.7694 | TB401
2025-07-14 | 2025-07-12 | 2025-07-16 | Poonam | 57.597 | 11.5194 | TB401
2025-07-14 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-14 | 2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401
2025-07-14 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-14 | 2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401
2025-07-14 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401
2025-07-14 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-14 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401
2025-07-14 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-14 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401
2025-07-14 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-14 | 2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401
2025-07-14 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-14 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-14 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401
2025-07-15 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401
2025-07-15 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401
2025-07-15 | 2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401
2025-07-15 | 2025-07-11 | 2025-07-15 | Jwala Singh 3 | 38.847 | 7.7694 | TB401
2025-07-15 | 2025-07-12 | 2025-07-16 | Poonam | 57.597 | 11.5194 | TB401
2025-07-15 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-15 | 2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401
2025-07-15 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-15 | 2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401
2025-07-15 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401
2025-07-15 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-15 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401
2025-07-15 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-15 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401
2025-07-15 | 2025-07-15 | 2025-07-18 | Satyam Manish | 37.504 | 9.376 | TB401
2025-07-15 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-15 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401
2025-07-15 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-15 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-15 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401
2025-07-16 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401
2025-07-16 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401
2025-07-16 | 2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401
2025-07-16 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-16 | 2025-07-12 | 2025-07-16 | Poonam | 57.597 | 11.5194 | TB401
2025-07-16 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-16 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-07-16 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-16 | 2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401
2025-07-16 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401
2025-07-16 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-16 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401
2025-07-16 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-16 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401
2025-07-16 | 2025-07-15 | 2025-07-18 | Satyam Manish | 37.504 | 9.376 | TB401
2025-07-16 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-16 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401
2025-07-16 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-16 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-16 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401
2025-07-17 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401
2025-07-17 | 2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401
2025-07-17 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-17 | 2025-07-17 | 2025-07-21 | Poonam | 37.504 | 7.5008 | TB401
2025-07-17 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-17 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-07-17 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-17 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401
2025-07-17 | 2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401
2025-07-17 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401
2025-07-17 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-17 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401
2025-07-17 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-17 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401
2025-07-17 | 2025-07-15 | 2025-07-18 | Satyam Manish | 37.504 | 9.376 | TB401
2025-07-17 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-17 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401
2025-07-17 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-17 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-17 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401
2025-07-18 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401
2025-07-18 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401
2025-07-18 | 2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401
2025-07-18 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-18 | 2025-07-17 | 2025-07-21 | Poonam | 37.504 | 7.5008 | TB401
2025-07-18 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-18 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-07-18 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-18 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401
2025-07-18 | 2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401
2025-07-18 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401
2025-07-18 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-18 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401
2025-07-18 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-18 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401
2025-07-18 | 2025-07-15 | 2025-07-18 | Satyam Manish | 37.504 | 9.376 | TB401
2025-07-18 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-18 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401
2025-07-18 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-18 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-18 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401
2025-07-19 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401
2025-07-19 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401
2025-07-19 | 2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401
2025-07-19 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-19 | 2025-07-17 | 2025-07-21 | Poonam | 37.504 | 7.5008 | TB401
2025-07-19 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-19 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-07-19 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-19 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401
2025-07-19 | 2025-07-19 | 2025-07-22 | Pusplata 4 | 37.504 | 9.376 | TB401
2025-07-19 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401
2025-07-19 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-19 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401
2025-07-19 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-19 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401
2025-07-19 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-19 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401
2025-07-19 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-19 | 2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-19 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-19 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401
2025-07-20 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401
2025-07-20 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401
2025-07-20 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-20 | 2025-07-17 | 2025-07-21 | Poonam | 37.504 | 7.5008 | TB401
2025-07-20 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-07-20 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-20 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401
2025-07-20 | 2025-07-19 | 2025-07-22 | Pusplata 4 | 37.504 | 9.376 | TB401
2025-07-20 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401
2025-07-20 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-20 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401
2025-07-20 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-20 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401
2025-07-20 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-20 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401
2025-07-20 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-20 | 2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-20 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-20 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401
2025-07-21 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401
2025-07-21 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401
2025-07-21 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-21 | 2025-07-17 | 2025-07-21 | Poonam | 37.504 | 7.5008 | TB401
2025-07-21 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-07-21 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-21 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401
2025-07-21 | 2025-07-19 | 2025-07-22 | Pusplata 4 | 37.504 | 9.376 | TB401
2025-07-21 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-21 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401
2025-07-21 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-21 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401
2025-07-21 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-21 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401
2025-07-21 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-21 | 2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-21 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-22 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401
2025-07-22 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401
2025-07-22 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-22 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401
2025-07-22 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-07-22 | 2025-07-22 | 2025-07-26 | Pusplata 2 | 38.847 | 7.7694 | TB401
2025-07-22 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401
2025-07-22 | 2025-07-19 | 2025-07-22 | Pusplata 4 | 37.504 | 9.376 | TB401
2025-07-22 | 2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401
2025-07-22 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-22 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401
2025-07-22 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-22 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401
2025-07-22 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-22 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401
2025-07-22 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-22 | 2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-22 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-23 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401
2025-07-23 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401
2025-07-23 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-23 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401
2025-07-23 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-07-23 | 2025-07-22 | 2025-07-26 | Pusplata 2 | 38.847 | 7.7694 | TB401
2025-07-23 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401
2025-07-23 | 2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401
2025-07-23 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-23 | 2025-07-23 | 2025-07-27 | Pusplata 7 | 38.847 | 7.7694 | TB401
2025-07-23 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-23 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-23 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401
2025-07-23 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-23 | 2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-23 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-24 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401
2025-07-24 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401
2025-07-24 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-24 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401
2025-07-24 | 2025-07-22 | 2025-07-26 | Pusplata 2 | 38.847 | 7.7694 | TB401
2025-07-24 | 2025-07-24 | 2025-07-26 | Pusplata 4 | 37.504 | 12.5013 | TB401
2025-07-24 | 2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401
2025-07-24 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-24 | 2025-07-23 | 2025-07-27 | Pusplata 7 | 38.847 | 7.7694 | TB401
2025-07-24 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-24 | 2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401
2025-07-24 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-24 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-24 | 2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-24 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-24 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401
2025-07-25 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401
2025-07-25 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-25 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401
2025-07-25 | 2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401
2025-07-25 | 2025-07-22 | 2025-07-26 | Pusplata 2 | 38.847 | 7.7694 | TB401
2025-07-25 | 2025-07-24 | 2025-07-26 | Pusplata 4 | 37.504 | 12.5013 | TB401
2025-07-25 | 2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401
2025-07-25 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-25 | 2025-07-23 | 2025-07-27 | Pusplata 7 | 38.847 | 7.7694 | TB401
2025-07-25 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-25 | 2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401
2025-07-25 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-25 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-25 | 2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-25 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-25 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401
2025-07-26 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401
2025-07-26 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-26 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401
2025-07-26 | 2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401
2025-07-26 | 2025-07-22 | 2025-07-26 | Pusplata 2 | 38.847 | 7.7694 | TB401
2025-07-26 | 2025-07-24 | 2025-07-26 | Pusplata 4 | 37.504 | 12.5013 | TB401
2025-07-26 | 2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401
2025-07-26 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-26 | 2025-07-23 | 2025-07-27 | Pusplata 7 | 38.847 | 7.7694 | TB401
2025-07-26 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-26 | 2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401
2025-07-26 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-26 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-26 | 2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-26 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-26 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401
2025-07-27 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401
2025-07-27 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-27 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401
2025-07-27 | 2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401
2025-07-27 | 2025-07-27 | 2025-07-31 | Pusplata 2 | 45.413 | 9.0826 | TB401
2025-07-27 | 2025-07-27 | 2025-07-30 | Pusplata 3 | 38.847 | 9.7118 | TB401
2025-07-27 | 2025-07-27 | 2025-07-31 | Pusplata 4 | 37.504 | 7.5008 | TB401
2025-07-27 | 2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401
2025-07-27 | 2025-07-27 | 2025-07-31 | Pusplata 6 | 38.847 | 7.7694 | TB401
2025-07-27 | 2025-07-23 | 2025-07-27 | Pusplata 7 | 38.847 | 7.7694 | TB401
2025-07-27 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-27 | 2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401
2025-07-27 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-27 | 2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-27 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-27 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401
2025-07-28 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401
2025-07-28 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-28 | 2025-07-28 | 2025-07-31 | Poonam | 37.504 | 9.376 | TB401
2025-07-28 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401
2025-07-28 | 2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401
2025-07-28 | 2025-07-27 | 2025-07-31 | Pusplata 2 | 45.413 | 9.0826 | TB401
2025-07-28 | 2025-07-27 | 2025-07-30 | Pusplata 3 | 38.847 | 9.7118 | TB401
2025-07-28 | 2025-07-27 | 2025-07-31 | Pusplata 4 | 37.504 | 7.5008 | TB401
2025-07-28 | 2025-07-27 | 2025-07-31 | Pusplata 6 | 38.847 | 7.7694 | TB401
2025-07-28 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-28 | 2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401
2025-07-28 | 2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-28 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-28 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401
2025-07-29 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401
2025-07-29 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-29 | 2025-07-28 | 2025-07-31 | Poonam | 37.504 | 9.376 | TB401
2025-07-29 | 2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401
2025-07-29 | 2025-07-27 | 2025-07-31 | Pusplata 2 | 45.413 | 9.0826 | TB401
2025-07-29 | 2025-07-27 | 2025-07-30 | Pusplata 3 | 38.847 | 9.7118 | TB401
2025-07-29 | 2025-07-27 | 2025-07-31 | Pusplata 4 | 37.504 | 7.5008 | TB401
2025-07-29 | 2025-07-27 | 2025-07-31 | Pusplata 6 | 38.847 | 7.7694 | TB401
2025-07-29 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-29 | 2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401
2025-07-29 | 2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-29 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-29 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401
2025-07-30 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401
2025-07-30 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-30 | 2025-07-28 | 2025-07-31 | Poonam | 37.504 | 9.376 | TB401
2025-07-30 | 2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401
2025-07-30 | 2025-07-27 | 2025-07-31 | Pusplata 2 | 45.413 | 9.0826 | TB401
2025-07-30 | 2025-07-27 | 2025-07-30 | Pusplata 3 | 38.847 | 9.7118 | TB401
2025-07-30 | 2025-07-27 | 2025-07-31 | Pusplata 4 | 37.504 | 7.5008 | TB401
2025-07-30 | 2025-07-27 | 2025-07-31 | Pusplata 6 | 38.847 | 7.7694 | TB401
2025-07-30 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-30 | 2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-30 | 2025-07-30 | 2025-07-31 | Satyam Vijay | 37.504 | 18.752 | TB401
2025-07-30 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-30 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401
2025-07-31 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401
2025-07-31 | 2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401
2025-07-31 | 2025-07-28 | 2025-07-31 | Poonam | 37.504 | 9.376 | TB401
2025-07-31 | 2025-07-27 | 2025-07-31 | Pusplata 2 | 45.413 | 9.0826 | TB401
2025-07-31 | 2025-07-31 | 2025-08-04 | Pusplata 3 | 37.504 | 7.5008 | TB401
2025-07-31 | 2025-07-27 | 2025-07-31 | Pusplata 4 | 37.504 | 7.5008 | TB401
2025-07-31 | 2025-07-27 | 2025-07-31 | Pusplata 6 | 38.847 | 7.7694 | TB401
2025-07-31 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-07-31 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401
2025-07-31 | 2025-07-30 | 2025-07-31 | Satyam Vijay | 37.504 | 18.752 | TB401
2025-07-31 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-31 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401
2025-08-01 | 2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401
2025-08-01 | 2025-08-01 | 2025-08-04 | Poonam | 37.504 | 9.376 | TB401
2025-08-01 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-08-01 | 2025-07-31 | 2025-08-04 | Pusplata 3 | 37.504 | 7.5008 | TB401
2025-08-01 | 2025-08-01 | 2025-08-05 | Pusplata 4 | 37.504 | 7.5008 | TB401
2025-08-01 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-01 | 2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401
2025-08-01 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401
2025-08-02 | 2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401
2025-08-02 | 2025-08-01 | 2025-08-04 | Poonam | 37.504 | 9.376 | TB401
2025-08-02 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-08-02 | 2025-07-31 | 2025-08-04 | Pusplata 3 | 37.504 | 7.5008 | TB401
2025-08-02 | 2025-08-01 | 2025-08-05 | Pusplata 4 | 37.504 | 7.5008 | TB401
2025-08-02 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-02 | 2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401
2025-08-02 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401
2025-08-03 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401
2025-08-03 | 2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401
2025-08-03 | 2025-08-01 | 2025-08-04 | Poonam | 37.504 | 9.376 | TB401
2025-08-03 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-08-03 | 2025-07-31 | 2025-08-04 | Pusplata 3 | 37.504 | 7.5008 | TB401
2025-08-03 | 2025-08-01 | 2025-08-05 | Pusplata 4 | 37.504 | 7.5008 | TB401
2025-08-03 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-03 | 2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401
2025-08-03 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401
2025-08-04 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-04 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401
2025-08-04 | 2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401
2025-08-04 | 2025-08-01 | 2025-08-04 | Poonam | 37.504 | 9.376 | TB401
2025-08-04 | 2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401
2025-08-04 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-08-04 | 2025-07-31 | 2025-08-04 | Pusplata 3 | 37.504 | 7.5008 | TB401
2025-08-04 | 2025-08-01 | 2025-08-05 | Pusplata 4 | 37.504 | 7.5008 | TB401
2025-08-04 | 2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401
2025-08-04 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-04 | 2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401
2025-08-04 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401
2025-08-04 | 2025-08-04 | 2025-08-07 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-05 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-05 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401
2025-08-05 | 2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401
2025-08-05 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401
2025-08-05 | 2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401
2025-08-05 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-08-05 | 2025-08-01 | 2025-08-05 | Pusplata 4 | 37.504 | 7.5008 | TB401
2025-08-05 | 2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401
2025-08-05 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-05 | 2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401
2025-08-05 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401
2025-08-05 | 2025-08-04 | 2025-08-07 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-06 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-06 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401
2025-08-06 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401
2025-08-06 | 2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401
2025-08-06 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-08-06 | 2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401
2025-08-06 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-06 | 2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401
2025-08-06 | 2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401
2025-08-06 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401
2025-08-06 | 2025-08-04 | 2025-08-07 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-06 | 2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-08-07 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-07 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401
2025-08-07 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401
2025-08-07 | 2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401
2025-08-07 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-08-07 | 2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401
2025-08-07 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-07 | 2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401
2025-08-07 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401
2025-08-07 | 2025-08-04 | 2025-08-07 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-07 | 2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-08-08 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-08 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401
2025-08-08 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401
2025-08-08 | 2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401
2025-08-08 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-08-08 | 2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401
2025-08-08 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-08 | 2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401
2025-08-08 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401
2025-08-08 | 2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-08-09 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-09 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401
2025-08-09 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401
2025-08-09 | 2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401
2025-08-09 | 2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401
2025-08-09 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-09 | 2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401
2025-08-09 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401
2025-08-09 | 2025-08-09 | 2025-08-12 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-09 | 2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-08-10 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-10 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401
2025-08-10 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-10 | 2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401
2025-08-10 | 2025-08-09 | 2025-08-12 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-10 | 2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-08-11 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-11 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401
2025-08-11 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-11 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-11 | 2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401
2025-08-11 | 2025-08-09 | 2025-08-12 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-11 | 2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-08-12 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-12 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401
2025-08-12 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-12 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-12 | 2025-08-09 | 2025-08-12 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-12 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-13 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-13 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401
2025-08-13 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-13 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-13 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-14 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-14 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-14 | 2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401
2025-08-14 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-14 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-14 | 2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401
2025-08-14 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-15 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-15 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-15 | 2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401
2025-08-15 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-15 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-15 | 2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401
2025-08-15 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-16 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-16 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-16 | 2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401
2025-08-16 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-16 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-16 | 2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401
2025-08-16 | 2025-08-16 | 2025-08-19 | Pusplata Deepak | 38.847 | 9.7118 | TB401
2025-08-16 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-17 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-17 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-17 | 2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401
2025-08-17 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-17 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-17 | 2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401
2025-08-17 | 2025-08-16 | 2025-08-19 | Pusplata Deepak | 38.847 | 9.7118 | TB401
2025-08-17 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-17 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401
2025-08-18 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-18 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-18 | 2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401
2025-08-18 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-18 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-18 | 2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401
2025-08-18 | 2025-08-16 | 2025-08-19 | Pusplata Deepak | 38.847 | 9.7118 | TB401
2025-08-18 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-18 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401
2025-08-19 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-19 | 2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401
2025-08-19 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-19 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-19 | 2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401
2025-08-19 | 2025-08-16 | 2025-08-19 | Pusplata Deepak | 38.847 | 9.7118 | TB401
2025-08-19 | 2025-08-19 | 2025-08-22 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-19 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-19 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401
2025-08-20 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-20 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-20 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-20 | 2025-08-19 | 2025-08-22 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-20 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-20 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401
2025-08-21 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-21 | 2025-08-21 | 2025-08-25 | Priyanka Devi 2 | 37.504 | 7.5008 | TB401
2025-08-21 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-21 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-21 | 2025-08-21 | 2025-08-24 | Pusplata Deepak | 37.504 | 9.376 | TB401
2025-08-21 | 2025-08-19 | 2025-08-22 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-21 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-21 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401
2025-08-21 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401
2025-08-22 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-22 | 2025-08-21 | 2025-08-25 | Priyanka Devi 2 | 37.504 | 7.5008 | TB401
2025-08-22 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-22 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-22 | 2025-08-21 | 2025-08-24 | Pusplata Deepak | 37.504 | 9.376 | TB401
2025-08-22 | 2025-08-19 | 2025-08-22 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-22 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-22 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401
2025-08-22 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401
2025-08-22 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401
2025-08-23 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-23 | 2025-08-21 | 2025-08-25 | Priyanka Devi 2 | 37.504 | 7.5008 | TB401
2025-08-23 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-23 | 2025-08-21 | 2025-08-24 | Pusplata Deepak | 37.504 | 9.376 | TB401
2025-08-23 | 2025-08-23 | 2025-08-27 | Satyam Manish |  |  | TB401
2025-08-23 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-23 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401
2025-08-23 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401
2025-08-23 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401
2025-08-24 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-24 | 2025-08-21 | 2025-08-25 | Priyanka Devi 2 | 37.504 | 7.5008 | TB401
2025-08-24 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401
2025-08-24 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-24 | 2025-08-21 | 2025-08-24 | Pusplata Deepak | 37.504 | 9.376 | TB401
2025-08-24 | 2025-08-23 | 2025-08-27 | Satyam Manish |  |  | TB401
2025-08-24 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-24 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401
2025-08-24 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401
2025-08-24 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401
2025-08-25 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-25 | 2025-08-21 | 2025-08-25 | Priyanka Devi 2 | 37.504 | 7.5008 | TB401
2025-08-25 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401
2025-08-25 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-25 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401
2025-08-25 | 2025-08-23 | 2025-08-27 | Satyam Manish |  |  | TB401
2025-08-25 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-25 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401
2025-08-25 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401
2025-08-25 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401
2025-08-26 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-26 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401
2025-08-26 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-26 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401
2025-08-26 | 2025-08-23 | 2025-08-27 | Satyam Manish |  |  | TB401
2025-08-26 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-26 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401
2025-08-26 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401
2025-08-26 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401
2025-08-27 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-08-27 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401
2025-08-27 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-27 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401
2025-08-27 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401
2025-08-27 | 2025-08-23 | 2025-08-27 | Satyam Manish |  |  | TB401
2025-08-27 | 2025-08-27 | 2025-08-31 | Satyam Vijay | 38.847 | 7.7694 | TB401
2025-08-27 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401
2025-08-27 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401
2025-08-27 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401
2025-08-28 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401
2025-08-28 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-28 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401
2025-08-28 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401
2025-08-28 | 2025-08-27 | 2025-08-31 | Satyam Vijay | 38.847 | 7.7694 | TB401
2025-08-28 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401
2025-08-28 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401
2025-08-28 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401
2025-08-29 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401
2025-08-29 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401
2025-08-29 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401
2025-08-29 | 2025-08-27 | 2025-08-31 | Satyam Vijay | 38.847 | 7.7694 | TB401
2025-08-29 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401
2025-08-29 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401
2025-08-29 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401
2025-08-30 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401
2025-08-30 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401
2025-08-30 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401
2025-08-30 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401
2025-08-30 | 2025-08-27 | 2025-08-31 | Satyam Vijay | 38.847 | 7.7694 | TB401
2025-08-30 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401
2025-08-30 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401
2025-08-31 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401
2025-08-31 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401
2025-08-31 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401
2025-08-31 | 2025-08-27 | 2025-08-31 | Satyam Vijay | 38.847 | 7.7694 | TB401
2025-08-31 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401
2025-08-31 | 2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401
2025-09-01 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401
2025-09-01 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401
2025-09-01 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401
2025-09-01 | 2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401
2025-09-02 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401
2025-09-02 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-02 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401
2025-09-02 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401
2025-09-02 | 2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401
2025-09-03 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401
2025-09-03 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-03 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401
2025-09-03 | 2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401
2025-09-04 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401
2025-09-04 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401
2025-09-04 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-04 | 2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401
2025-09-05 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401
2025-09-05 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401
2025-09-05 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-05 | 2025-09-05 | 2025-09-09 | Rahul Kumar | 37.504 | 7.5008 | TB401
2025-09-05 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401
2025-09-05 | 2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401
2025-09-06 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401
2025-09-06 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401
2025-09-06 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-06 | 2025-09-05 | 2025-09-09 | Rahul Kumar | 37.504 | 7.5008 | TB401
2025-09-06 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401
2025-09-07 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401
2025-09-07 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401
2025-09-07 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-07 | 2025-09-05 | 2025-09-09 | Rahul Kumar | 37.504 | 7.5008 | TB401
2025-09-07 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401
2025-09-08 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401
2025-09-08 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401
2025-09-08 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-08 | 2025-09-05 | 2025-09-09 | Rahul Kumar | 37.504 | 7.5008 | TB401
2025-09-08 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401
2025-09-09 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401
2025-09-09 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-09 | 2025-09-05 | 2025-09-09 | Rahul Kumar | 37.504 | 7.5008 | TB401
2025-09-09 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401
2025-09-10 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401
2025-09-10 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-10 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401
2025-09-11 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401
2025-09-11 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-11 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401
2025-09-11 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401
2025-09-12 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401
2025-09-12 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-12 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401
2025-09-12 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401
2025-09-13 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401
2025-09-13 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-13 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401
2025-09-13 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401
2025-09-14 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-14 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401
2025-09-14 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401
2025-09-15 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-15 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401
2025-09-15 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401
2025-09-15 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401
2025-09-16 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-16 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401
2025-09-16 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401
2025-09-17 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401
2025-09-17 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401
2025-09-18 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401
2025-09-18 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401
2025-09-19 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401
2025-09-19 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401
2025-09-20 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401
2025-09-20 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401
2025-09-21 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401
2025-09-21 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401
2025-09-22 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401
2025-09-22 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401
2025-09-23 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401
2025-09-23 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401
2025-09-24 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401
2025-09-25 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401
2025-09-26 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401
2025-09-27 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401
2025-09-28 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401
2025-09-29 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401
2023-09-30 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-01 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-02 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-03 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-04 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-05 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-06 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-07 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-08 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-09 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-10 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-11 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-12 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-13 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-14 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-15 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-16 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-17 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-18 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-19 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-20 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-21 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-22 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-23 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-24 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-25 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-26 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-27 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-28 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-29 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-11-01 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-02 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-03 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-04 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-05 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-06 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-07 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-08 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-09 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-11 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-12 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-13 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-14 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-15 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-16 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-17 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-19 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-20 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-21 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-22 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-23 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-24 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-25 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-26 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-27 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-28 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-29 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-30 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-12-01 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-12-02 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-03 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-04 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-05 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-06 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-07 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-08 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-09 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-10 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-11 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-12 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-13 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-14 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-15 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-01-04 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-05 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-06 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-07 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-08 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-09 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-10 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-11 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-12 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-12 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-13 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-14 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-15 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-16 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-17 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-18 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-18 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-19 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-20 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-21 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-22 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-23 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-23 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-24 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-25 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-26 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-27 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-28 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-28 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-29 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-30 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-31 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-01 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-02 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-02 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-03 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-04 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-04 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-04 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-05 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-05 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-05 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-06 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-06 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-06 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-07 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-07 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-07 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-08 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-08 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-08 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-09 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-09 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-09 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-10 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-10 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-11 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-11 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-12 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-12 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-13 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-13 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-13 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-14 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-14 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-15 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-15 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-15 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-16 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-16 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-17 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-17 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-18 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-18 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-19 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-19 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-20 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-20 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-20 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-20 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-21 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-21 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-21 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-22 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-22 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-23 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-23 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-24 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-24 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-25 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-25 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-26 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-26 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-26 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-27 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-27 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-02-27 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-28 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-28 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-02-28 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-29 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-02-29 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-03-01 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-01 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-03-02 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-02 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-03-02 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-03 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-03 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-03 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-04 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-04 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-05 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-05 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-06 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-06 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-07 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-07 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-08 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-08 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-08 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-09 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-09 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-10 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-10 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-11 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-11 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-12 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-12 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-13 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-13 | 2024-03-13 | 2024-03-13 | Lalan Mahto | 37.73 | 37.73 | TA325
2024-03-13 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-14 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-15 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-16 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-17 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-18 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-19 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-20 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-21 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-22 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-23 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-24 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-25 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-26 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-27 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-28 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-29 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-30 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-31 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-01 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-02 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-03 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-04 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-05 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-06 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-07 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-08 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-09 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-10 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-11 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-13 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-14 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-15 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-16 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-17 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-18 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-19 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-20 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325
2024-04-21 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325
2024-04-22 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325
2024-04-23 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325
2024-04-24 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325
2024-04-25 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-04-26 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-04-27 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-04-28 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-04-29 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-04-30 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-05-01 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-02 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-02 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-03 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-03 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-04 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-04 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-05 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-05 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-06 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-06 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-07 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-07 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-07 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-07 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-07 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-08 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-08 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-08 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-08 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-09 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-09 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-09 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-09 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-10 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-10 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-10 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-10 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-11 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-11 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-11 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-11 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-12 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-12 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-12 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-12 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-13 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-13 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-13 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-14 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-14 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-14 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-15 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-15 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-15 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-16 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-16 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-16 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-17 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-17 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-17 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-18 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-18 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-18 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-19 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-19 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-19 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-19 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-20 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-20 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-20 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-21 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-21 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-21 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-22 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-22 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-22 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-23 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-23 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-23 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-24 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-24 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-24 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-25 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-25 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-25 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-05-26 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-26 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-26 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-05-27 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-27 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-27 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-05-28 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-28 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-28 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-05-29 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-29 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-29 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-05-30 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-30 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-30 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-05-31 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-31 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-05-31 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-31 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-05-31 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-06-01 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-01 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-02 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-02 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-03 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-03 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-04 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-04 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-05 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-05 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-05 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-06 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-06 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-06 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-07 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-07 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-07 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-08 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-08 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-08 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-09 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-09 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-09 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-10 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-10 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-10 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-11 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-11 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-12 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-12 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-12 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-13 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-13 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-13 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-13 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325
2024-06-14 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-14 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-14 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-14 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325
2024-06-15 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-15 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-15 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-15 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325
2024-06-16 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-16 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-16 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-17 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-17 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-17 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-18 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-18 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-18 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-19 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-19 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-20 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-20 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-21 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-21 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-22 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-22 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-23 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-23 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-24 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-24 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-25 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-25 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-26 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-26 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-27 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-28 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-29 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-30 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-30 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-01 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-07-01 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-02 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-07-02 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-02 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-03 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-03 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-04 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-04 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-05 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-05 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-06 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-07 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-08 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-08 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-08 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-07-08 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-09 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-09 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-09 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-07-09 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-10 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-10 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-10 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-10 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-07-10 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-11 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-11 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-11 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-11 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-07-11 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-12 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-12 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-12 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-12 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-07-12 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-13 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-13 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-13 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-13 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-13 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-14 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-14 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-14 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-14 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-14 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-15 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-15 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-15 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-15 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-15 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-16 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-16 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-16 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-16 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-16 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-17 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-17 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-17 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-17 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-17 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-18 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-18 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-18 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-18 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-18 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-19 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-19 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-19 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-19 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-20 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-20 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-20 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-20 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-20 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-21 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-21 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-21 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-21 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-21 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-22 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-22 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-22 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-22 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-22 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-23 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-23 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-23 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-23 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-23 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-24 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-24 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-24 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-24 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-25 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-25 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-25 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-25 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-26 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-26 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-26 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-27 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-27 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-27 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-27 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-07-28 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-07-28 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-28 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-28 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-28 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-07-29 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-07-29 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-29 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-29 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-29 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-07-30 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-07-30 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-30 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-07-30 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-30 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-07-31 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-07-31 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-31 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-07-31 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-31 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-01 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-01 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-01 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-01 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-01 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-02 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-02 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-02 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-02 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-02 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-03 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-03 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-03 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-03 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-03 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-04 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-04 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-04 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-04 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-04 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-05 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-05 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-05 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-05 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-05 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-06 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-06 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-06 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-06 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-06 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-07 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-07 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-07 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-07 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-07 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-08 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-08 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-08 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-08 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-08 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-08 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-09 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-09 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-09 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-09 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-09 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-10 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-10 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-10 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-10 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-10 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-11 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-11 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-11 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-11 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-11 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-11 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-12 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-12 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-12 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-12 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-12 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-13 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-13 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-13 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-13 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-13 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-14 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-14 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-14 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-14 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-14 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-15 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-15 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-15 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-15 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-15 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-16 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-16 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-16 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-16 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-16 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-17 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-17 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-17 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-17 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-17 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-18 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-18 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-18 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-18 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-18 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-18 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-19 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-19 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-19 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-19 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-19 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-19 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-20 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-20 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-20 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-20 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-20 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-20 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-21 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-21 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-21 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-21 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-21 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-21 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-22 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-22 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-22 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-22 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-22 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-22 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-23 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-23 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-23 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-23 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-23 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-24 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-24 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-24 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-24 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-25 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-25 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-25 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-26 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-26 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-26 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-27 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-27 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-27 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-28 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-28 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-28 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-29 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-29 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-29 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-30 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-08-30 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-30 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-30 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-31 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-08-31 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-31 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-31 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-01 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-01 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-01 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-02 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-02 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-02 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-02 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-03 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-03 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-03 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-03 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-04 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-04 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-04 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-04 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-05 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-05 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-05 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-05 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-06 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-06 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-06 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-06 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-07 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-07 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-07 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-07 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-08 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-08 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-08 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-08 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-09 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-09 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-09 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-09 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-09 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-10 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-10 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-10 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-10 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-10 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-10 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-11 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-11 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-11 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-11 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-11 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-11 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-11 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-12 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-12 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-12 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-12 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-12 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-12 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-12 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-12 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-13 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-13 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-13 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-13 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-13 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-13 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-13 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-13 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-14 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-14 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-14 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-14 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-14 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-14 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-14 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-14 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-15 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-15 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-15 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-15 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-15 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-15 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-15 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-15 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-16 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-16 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-16 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-16 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-16 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-16 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-16 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-16 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-16 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-16 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-17 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-17 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-17 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-17 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-17 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-17 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-17 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-17 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-17 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-17 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-18 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-18 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-18 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-18 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-18 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-18 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-18 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-18 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-18 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-18 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-19 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-19 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-19 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-19 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-19 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-19 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-19 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-19 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-19 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-19 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-20 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-20 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-20 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-20 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-20 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-20 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-20 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-20 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-20 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-20 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-21 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-21 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-21 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-21 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-21 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-21 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-21 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-21 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-21 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-22 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-22 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-22 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-22 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-22 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-22 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-22 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-22 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-22 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-23 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-23 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-23 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-23 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-23 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-23 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-23 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-23 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-23 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-23 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-23 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-24 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-24 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-24 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-24 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-24 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-24 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-24 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-24 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-24 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-24 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-25 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-25 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-25 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-25 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-25 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-25 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-25 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-25 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-25 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-26 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-09-26 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-26 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-26 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-26 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-26 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-26 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-26 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-26 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-26 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-27 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-09-27 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-09-27 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-27 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-09-27 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-27 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-27 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-27 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-27 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-27 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-28 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-09-28 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-09-28 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-28 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-09-28 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-28 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-28 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-28 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-28 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-28 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-29 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-09-29 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-09-29 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-29 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-09-29 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-29 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-29 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-29 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-29 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-29 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-30 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-09-30 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-09-30 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-30 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-09-30 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-30 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-30 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-30 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-30 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-30 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-30 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-01 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-01 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-01 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-01 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-01 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-01 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-01 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-01 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-01 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-01 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-01 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-02 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-02 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-02 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-02 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-02 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-02 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-02 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-02 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-02 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-02 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-02 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-03 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-03 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-03 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-03 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-03 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-03 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-03 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-03 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-03 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-03 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-03 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-04 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-04 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-04 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-04 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-04 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-04 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-04 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-04 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-04 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-04 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-04 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-04 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-05 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-05 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-05 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-05 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-05 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-05 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-05 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-05 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-05 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-05 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-05 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-05 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-06 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-06 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-06 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-06 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-06 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-06 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-06 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-06 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-06 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-06 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-06 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-06 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-07 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-07 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-07 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-07 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-07 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-07 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-07 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-07 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-07 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-07 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-07 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-07 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-08 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-08 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-08 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-08 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-08 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-08 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-08 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-08 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-08 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-08 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-08 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-08 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-08 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-09 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-09 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-09 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-09 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-09 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-09 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-09 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-09 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-09 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-09 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-09 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-09 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-09 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-09 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-09 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-10 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-10 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-10 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-10 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-10 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-10 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-10 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-10 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-10 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-10 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-10 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-10 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-10 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-10 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-11 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-11 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-11 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-11 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-11 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-11 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-11 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-11 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-11 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-11 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-11 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-11 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-12 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-12 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-12 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-12 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-12 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-12 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-12 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-12 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-12 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-12 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-12 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-12 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-13 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-13 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-13 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-13 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-13 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-13 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-13 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-13 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-13 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-13 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-13 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-13 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-14 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-14 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-14 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-14 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-14 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-14 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-14 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-14 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-14 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-14 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-14 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-15 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-15 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-15 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-15 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-15 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-15 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-15 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-15 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-15 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-15 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-15 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-15 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-15 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-16 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-16 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-16 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-16 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-16 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-16 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-16 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-16 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-16 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-16 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-16 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-16 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-17 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-17 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-17 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-17 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-17 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-17 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-17 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-17 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-17 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-17 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-17 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-17 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-17 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-18 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-18 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-18 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-18 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-18 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-18 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-18 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-18 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-18 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-18 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-18 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-18 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-18 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-19 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-19 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-19 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-19 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-19 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-19 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-19 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-19 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-19 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-19 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-19 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-19 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-19 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-20 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-20 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-20 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-20 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-20 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-20 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-20 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-20 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-20 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-20 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-20 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-20 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-20 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-21 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-21 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-21 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-21 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-21 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-21 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-21 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-21 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-21 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-21 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-21 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-21 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-21 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-22 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-22 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-22 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-22 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-22 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-22 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-22 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-22 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-22 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-22 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-22 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-22 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-22 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-23 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-23 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-23 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-23 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-23 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-23 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-23 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-23 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-23 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-23 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-23 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-23 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-23 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-23 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-24 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-24 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-24 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-24 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-24 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-24 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-24 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-24 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-24 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-24 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-24 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-24 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-24 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-24 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-25 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-25 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-25 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-25 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-25 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-25 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-25 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-25 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-25 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-25 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-25 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-25 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-25 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-26 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-26 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-26 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-26 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-26 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-26 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-26 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-26 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-26 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-26 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-26 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-26 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-26 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-27 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-27 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-27 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-27 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-27 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-27 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-27 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-27 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-27 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-27 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-27 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-27 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-27 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-28 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-28 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-10-28 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-28 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-28 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-28 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-28 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-28 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-28 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-28 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-28 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-28 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-28 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-28 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-29 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-29 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-10-29 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-29 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-29 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-29 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-29 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-29 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-29 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-29 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-29 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-29 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-29 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-10-30 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-30 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-10-30 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-30 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-30 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-30 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-30 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-30 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-30 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-30 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-30 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-30 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-10-30 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-30 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-10-31 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-31 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-10-31 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-10-31 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-31 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-31 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-31 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-31 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-31 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-31 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-31 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-31 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-10-31 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-31 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-01 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-01 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-11-01 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-01 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-01 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-01 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-01 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-01 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-01 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-02 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-02 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-11-02 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-02 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-02 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-02 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-02 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2024-11-02 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-02 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-02 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-02 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-03 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-03 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-11-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-03 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-03 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-03 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-03 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2024-11-03 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-03 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-03 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-03 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-04 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-04 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-04 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-04 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-04 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2024-11-04 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-04 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-04 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-04 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-04 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-05 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-05 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325
2024-11-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-05 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-05 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-05 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-05 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2024-11-05 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-05 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-05 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-05 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-05 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-06 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-06 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325
2024-11-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-06 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-06 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-06 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-06 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2024-11-06 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-06 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-06 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-06 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-06 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-07 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-07 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325
2024-11-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-07 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-07 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-07 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-07 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2024-11-07 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-07 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-07 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-07 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-07 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-08 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-08 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325
2024-11-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-08 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-08 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-08 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-08 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-08 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-08 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-09 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-09 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325
2024-11-09 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-09 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-09 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-09 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-09 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-09 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-09 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-10 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-10 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-10 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325
2024-11-10 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-10 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-10 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-10 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-10 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-10 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-10 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-10 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-10 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-11 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-11 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-11 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325
2024-11-11 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-11 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-11 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-11 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-11 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-11 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-11 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-11 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-11 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-12 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-12 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325
2024-11-12 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-12 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-12 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-12 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-12 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-12 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-12 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-12 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-12 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-13 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-13 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-13 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325
2024-11-13 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-13 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-13 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-13 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-13 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-13 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-13 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-13 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-13 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-13 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-14 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-14 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-14 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325
2024-11-14 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-14 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-14 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-14 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-14 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-14 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-14 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-14 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-14 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-15 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-15 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-15 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325
2024-11-15 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-15 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-15 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-15 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-15 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-15 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-15 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-15 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-15 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-16 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-16 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-16 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325
2024-11-16 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-16 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-16 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-16 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-16 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-16 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-16 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-16 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-16 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-16 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-16 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-16 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-17 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-17 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-17 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325
2024-11-17 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-17 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-17 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-17 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-17 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-17 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-17 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-17 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-17 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-17 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-17 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-18 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-18 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-18 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325
2024-11-18 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-18 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-18 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-18 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-18 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-18 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-18 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-18 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-18 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-18 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-18 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-18 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-18 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-19 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-19 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-19 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325
2024-11-19 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-19 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-19 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-19 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-19 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-19 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-19 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-19 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-19 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-19 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-19 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-19 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-19 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-20 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-20 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-20 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325
2024-11-20 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325
2024-11-20 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-20 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-20 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-20 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-20 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-20 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-20 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-20 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-20 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-20 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-20 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-20 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-20 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-20 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-21 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-21 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-21 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325
2024-11-21 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-21 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-21 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-21 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-21 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-21 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-21 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-21 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-21 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-21 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-21 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-21 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-21 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-21 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-22 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-22 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-22 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-22 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325
2024-11-22 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-22 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-22 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325
2024-11-22 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-22 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-22 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-22 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-22 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-22 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-22 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-22 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-22 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-22 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-22 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-22 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-23 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-23 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-23 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-23 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325
2024-11-23 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-23 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-23 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-23 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325
2024-11-23 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-23 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-23 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-23 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-23 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-23 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-23 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-23 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-23 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-23 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-23 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-24 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-24 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-24 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-24 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325
2024-11-24 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-24 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-24 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-24 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325
2024-11-24 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-24 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-24 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-24 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-24 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-24 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-24 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-24 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-24 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-24 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-24 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-25 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-25 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-25 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-25 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325
2024-11-25 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-25 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-25 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-25 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325
2024-11-25 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-25 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-25 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-25 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-25 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-25 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-25 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-25 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-25 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-25 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-26 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-26 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-26 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-26 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325
2024-11-26 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-26 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-26 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-26 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325
2024-11-26 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-26 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-26 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-26 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-26 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-26 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-26 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-26 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-26 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-26 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-27 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-11-27 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-27 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-27 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325
2024-11-27 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-27 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-27 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-27 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-11-27 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-27 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-27 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-27 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-27 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-27 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-27 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-27 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-11-27 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-27 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-27 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-28 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-11-28 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-28 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-28 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325
2024-11-28 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-28 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-28 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-28 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-11-28 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-28 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-28 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-28 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-28 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-11-28 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-11-28 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-28 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-28 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-28 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-11-28 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-28 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-11-28 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-29 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-11-29 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-29 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-29 | 2024-11-29 | 2024-12-03 | Dhaneshwar Mahto | 36.045 | 7.209 | TA325
2024-11-29 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-29 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-29 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-29 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-11-29 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-29 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-29 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-29 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-29 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-11-29 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-11-29 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-29 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-29 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-29 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-11-29 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-29 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-11-29 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-30 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-11-30 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-30 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-30 | 2024-11-29 | 2024-12-03 | Dhaneshwar Mahto | 36.045 | 7.209 | TA325
2024-11-30 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-30 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-30 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-30 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-11-30 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-30 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-30 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-30 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-30 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-11-30 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-11-30 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-30 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-30 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-30 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-11-30 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-30 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-11-30 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-01 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-01 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-01 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-01 | 2024-11-29 | 2024-12-03 | Dhaneshwar Mahto | 36.045 | 7.209 | TA325
2024-12-01 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-01 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-01 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-12-01 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-01 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-01 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-12-01 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-01 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-01 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-01 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-01 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-01 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-01 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-12-01 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-01 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-02 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-02 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-02 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-02 | 2024-11-29 | 2024-12-03 | Dhaneshwar Mahto | 36.045 | 7.209 | TA325
2024-12-02 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-02 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-02 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-12-02 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-02 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-02 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-02 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-12-02 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-02 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-02 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-02 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-02 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-02 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-02 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-12-02 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-02 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-03 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-03 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-03 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-03 | 2024-11-29 | 2024-12-03 | Dhaneshwar Mahto | 36.045 | 7.209 | TA325
2024-12-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-03 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-03 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-12-03 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-03 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-03 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-03 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-03 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-03 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-03 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-03 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-03 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-03 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-03 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-03 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-03 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-04 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-04 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-04 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-04 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-04 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-04 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-04 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-04 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-04 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-04 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-04 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-04 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-04 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-04 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-04 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-04 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-04 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-04 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-04 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-05 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-05 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-05 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-05 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-05 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-05 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-05 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-05 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-05 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-05 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-05 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-05 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-05 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-05 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-05 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-05 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-05 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-05 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-05 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-06 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-06 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-06 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-06 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-06 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-06 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-06 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-06 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-06 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-06 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-06 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-06 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-06 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-06 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-06 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-06 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-06 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-06 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-06 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-07 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-07 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-07 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-07 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-07 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-07 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-07 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-07 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-07 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-07 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-07 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-07 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-07 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-07 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-07 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-07 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-07 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-07 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-07 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-08 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-08 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-08 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-08 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-08 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-08 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-08 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-08 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-08 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-08 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-08 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-08 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-08 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-08 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-08 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-08 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-08 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-08 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-09 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-09 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-09 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-09 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-09 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-09 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-09 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-09 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-09 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-09 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-09 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-09 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-09 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-09 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-09 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-09 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-09 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-09 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-09 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-09 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-10 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-10 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-10 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-10 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-10 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-10 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-10 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-10 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-10 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-10 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-10 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-10 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-10 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-10 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-10 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-10 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-10 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-10 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-10 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-10 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-10 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-11 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-11 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-11 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-11 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-11 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-11 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-11 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-11 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-11 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-11 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-11 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-11 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-11 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-11 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-11 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-11 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-11 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-11 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-11 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-11 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-11 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-11 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-12 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-12 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-12 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-12 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-12 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-12 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-12 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-12 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-12 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-12 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-12 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-12 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-12 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-12 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-12 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-12 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-12 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-12 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-12 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-12 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-12 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-12 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-13 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-13 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-13 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-13 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-13 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-13 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-13 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-13 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-13 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-13 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-13 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-13 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-13 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-13 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-13 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-13 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-13 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-13 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-13 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-13 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-13 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-14 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-14 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-14 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-14 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-14 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-14 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-14 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-14 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-14 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-14 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-14 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-14 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-14 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-14 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-14 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-14 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-14 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-14 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-14 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-14 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-14 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-14 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-15 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-15 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-15 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-15 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-15 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-15 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-15 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-15 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-15 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-15 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-15 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-15 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-15 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-15 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-15 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-15 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-15 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-15 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-15 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-15 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-16 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-16 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-16 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-16 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-16 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-16 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-16 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-16 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-16 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-16 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-16 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-16 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-16 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-16 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-16 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-16 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-16 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-16 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-16 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-16 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-17 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-17 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-17 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-17 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-17 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-17 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-17 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-17 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-17 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-17 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-17 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-17 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-17 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-17 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-17 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-17 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-17 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-17 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-17 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-18 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-18 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-18 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-18 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-18 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-18 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-18 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-18 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-18 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-18 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-18 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-18 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-18 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-18 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-18 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-18 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-18 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-18 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-18 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-19 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-19 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-19 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-19 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-19 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-19 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-19 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-19 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-19 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-19 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-19 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-19 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-19 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-19 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-19 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-19 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-19 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-19 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-19 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-20 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-20 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-20 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2024-12-20 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-20 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-20 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-20 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-20 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-20 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-20 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-20 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-20 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-20 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-20 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-20 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-20 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-20 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-20 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-20 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-21 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-21 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-21 | 2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2024-12-21 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-21 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-21 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-21 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-21 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-21 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-21 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-21 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-21 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-21 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-21 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-21 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-21 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-21 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-21 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-21 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-21 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-22 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-22 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-22 | 2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2024-12-22 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-22 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-22 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-22 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-22 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-22 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-22 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-22 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-22 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-22 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-22 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-22 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-22 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-22 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-22 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-22 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-22 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-23 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-23 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-23 | 2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2024-12-23 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-23 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-23 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-23 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-23 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-23 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-23 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-23 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-23 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-23 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-23 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-23 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-23 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-23 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-23 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-23 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-23 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-23 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-24 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-24 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-24 | 2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2024-12-24 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-24 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-24 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-24 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-24 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-24 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-24 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-24 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-24 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-24 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-24 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-24 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-24 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-24 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-24 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-24 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-25 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-25 | 2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2024-12-25 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-25 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-25 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-25 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-25 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-25 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-25 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-25 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-25 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-25 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-25 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-25 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-25 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-25 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-25 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-25 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-26 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-26 | 2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2024-12-26 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-26 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-26 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-26 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-26 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-26 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-12-26 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-12-26 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-26 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-26 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-26 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-26 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-26 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-26 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-26 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-26 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-27 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-27 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325
2024-12-27 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-27 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-27 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-27 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-27 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-27 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-12-27 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-12-27 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-27 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-27 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-27 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-27 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-27 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-27 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-27 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-27 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-28 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-28 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2024-12-28 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325
2024-12-28 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-28 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-28 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-28 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-28 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-12-28 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-12-28 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-28 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-28 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2024-12-28 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-28 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-28 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-28 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-28 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2024-12-28 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-28 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-28 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2024-12-28 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-29 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2024-12-29 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325
2024-12-29 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2024-12-29 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-29 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-29 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-12-29 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-12-29 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-29 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-29 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2024-12-29 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-29 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-29 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-29 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2024-12-29 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-29 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-29 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2024-12-29 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-30 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2024-12-30 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2024-12-30 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325
2024-12-30 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2024-12-30 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-30 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-12-30 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-12-30 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-30 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-30 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2024-12-30 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-30 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2024-12-30 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-30 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2024-12-30 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-30 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-30 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2024-12-30 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-31 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2024-12-31 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2024-12-31 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325
2024-12-31 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2024-12-31 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2024-12-31 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-31 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2024-12-31 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-12-31 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-12-31 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-31 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-31 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2024-12-31 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-31 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2024-12-31 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2024-12-31 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2024-12-31 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-31 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2024-12-31 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2025-01-01 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-01 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-01 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325
2025-01-01 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2025-01-01 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-01 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2025-01-01 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-01 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2025-01-01 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2025-01-01 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2025-01-01 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-01-01 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-01 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2025-01-01 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-01 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-01 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-01 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-01 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-01 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-02 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-02 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-02 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325
2025-01-02 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2025-01-02 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-02 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2025-01-02 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-02 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2025-01-02 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2025-01-02 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2025-01-02 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-01-02 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-02 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2025-01-02 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-02 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-02 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-02 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-02 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-02 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-03 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-03 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-03 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325
2025-01-03 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2025-01-03 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-03 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2025-01-03 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-03 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-03 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2025-01-03 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2025-01-03 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-01-03 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-03 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2025-01-03 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-03 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-03 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-03 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-03 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-03 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-04 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-04 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-04 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325
2025-01-04 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-04 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2025-01-04 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-04 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-04 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2025-01-04 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2025-01-04 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-01-04 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-04 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-04 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-04 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-04 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-04 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-04 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-04 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-05 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-05 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-05 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-05 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2025-01-05 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-05 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-05 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2025-01-05 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-01-05 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-05 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-05 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-05 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-05 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-05 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-05 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-05 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-06 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-06 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-06 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-06 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-06 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-06 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-01-06 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-06 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-06 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-06 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-06 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-06 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-06 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-06 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-07 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-07 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-07 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-07 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-07 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-07 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-07 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-07 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-07 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-07 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-07 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-07 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-07 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-07 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-08 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-08 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-08 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-08 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-08 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-08 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-08 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-08 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-08 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-08 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-08 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-08 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-08 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-09 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-09 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-09 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-09 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-09 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-09 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-09 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-09 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-09 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-09 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-09 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-09 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-09 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-09 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-09 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-09 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-10 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-10 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-10 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-10 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-10 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-10 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-10 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-10 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-10 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-10 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-10 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-10 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-10 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-10 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-10 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-10 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-10 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-10 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-11 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-11 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-11 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-11 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-11 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-11 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-11 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-11 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-11 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-11 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-11 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-11 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-11 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-11 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-11 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-11 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-12 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-12 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-12 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-12 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-12 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-12 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-12 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-12 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-12 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-12 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-12 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-12 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-12 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-12 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-12 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-12 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-12 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-13 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-13 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-13 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-13 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-13 | 2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-01-13 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-13 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-13 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-13 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-13 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-13 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-13 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-13 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-13 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-13 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-13 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-13 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-13 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-14 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-14 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-14 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-14 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-14 | 2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-01-14 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-14 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-14 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-14 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-14 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-14 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-14 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-14 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-14 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-14 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-14 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-14 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-15 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-15 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-15 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-15 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-15 | 2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-01-15 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-15 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-15 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-15 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-15 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-15 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-15 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-15 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-15 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-15 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-15 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-15 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-16 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-16 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-16 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-16 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-16 | 2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-01-16 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-16 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-16 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-16 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-16 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-16 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-16 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-16 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-16 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-16 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-16 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-16 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-16 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-16 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-17 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-17 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-17 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-17 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-17 | 2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-01-17 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-17 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-17 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-17 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-17 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-17 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-17 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-17 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-17 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-17 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-17 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-17 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-17 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-17 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-18 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-18 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-18 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-18 | 2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-01-18 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-18 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-18 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-18 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-18 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-18 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-18 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-18 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-18 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-18 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-18 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-18 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-18 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-18 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-18 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-19 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-19 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-19 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-19 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-19 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-19 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-19 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-19 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-19 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-19 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-19 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-19 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-19 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-19 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-19 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-19 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-19 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-20 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-20 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-20 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-20 | 2025-01-20 | 2025-01-24 | Dhaneshwar Mahto | 46.623 | 9.3246 | TA325
2025-01-20 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-20 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-20 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-20 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-20 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-20 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-20 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-20 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-20 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-20 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-20 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-20 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-20 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-21 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-21 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-21 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-21 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-21 | 2025-01-20 | 2025-01-24 | Dhaneshwar Mahto | 46.623 | 9.3246 | TA325
2025-01-21 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-21 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-21 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-21 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-21 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-21 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-21 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-21 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-21 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-21 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-21 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-21 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-21 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-21 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-21 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-21 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-22 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-22 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-22 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-22 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-22 | 2025-01-20 | 2025-01-24 | Dhaneshwar Mahto | 46.623 | 9.3246 | TA325
2025-01-22 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-22 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-22 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-22 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-22 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-22 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-22 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-22 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-22 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-22 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-22 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-22 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-22 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-22 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-22 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-23 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-23 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-23 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-23 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-23 | 2025-01-20 | 2025-01-24 | Dhaneshwar Mahto | 46.623 | 9.3246 | TA325
2025-01-23 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-23 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-23 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-23 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-23 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-23 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-23 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-23 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-23 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-23 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-23 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-23 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-23 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-23 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-24 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-24 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-24 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-24 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-24 | 2025-01-20 | 2025-01-24 | Dhaneshwar Mahto | 46.623 | 9.3246 | TA325
2025-01-24 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-24 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-24 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-24 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-24 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-24 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-24 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-24 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-24 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-24 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-24 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-24 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-24 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-25 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-25 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-25 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-25 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-25 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-25 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-25 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-25 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-25 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-25 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-25 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-25 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-25 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-25 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-25 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-25 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-25 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-25 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-25 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-26 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-26 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-26 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-26 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-26 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-26 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-26 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-26 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-26 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-26 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-26 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-26 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-26 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-26 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-26 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-26 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-26 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-27 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-01-27 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-27 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-27 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-27 | 2025-01-27 | 2025-01-29 | Dhaneshwar Mahto | 44.728 | 14.9093 | TA325
2025-01-27 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-27 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-27 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-01-27 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-27 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-27 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-27 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-27 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-27 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-27 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-27 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-27 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-27 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-01-27 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-27 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-27 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-28 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-01-28 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-28 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-28 | 2025-01-27 | 2025-01-29 | Dhaneshwar Mahto | 44.728 | 14.9093 | TA325
2025-01-28 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-28 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-28 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-01-28 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-28 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-28 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-28 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-28 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-28 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-28 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-01-28 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-28 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-28 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-01-28 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-28 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-28 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-29 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-01-29 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-29 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-29 | 2025-01-27 | 2025-01-29 | Dhaneshwar Mahto | 44.728 | 14.9093 | TA325
2025-01-29 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-29 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-29 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-01-29 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-29 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-29 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-29 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-29 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-29 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-29 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-29 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-01-29 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-29 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-29 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-01-29 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-29 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-29 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-30 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-01-30 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-30 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-30 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-01-30 | 2025-01-30 | 2025-02-02 | Dhaneshwar Mahto | 37.73 | 9.4325 | TA325
2025-01-30 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-01-30 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-30 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-01-30 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-01-30 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-30 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-30 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-30 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-30 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-30 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-01-30 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-30 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-01-30 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-30 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-31 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-01-31 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-31 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-31 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-01-31 | 2025-01-30 | 2025-02-02 | Dhaneshwar Mahto | 37.73 | 9.4325 | TA325
2025-01-31 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-01-31 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-31 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-01-31 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-01-31 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-31 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-31 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-31 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-31 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-01-31 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-31 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-01-31 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-31 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-02-01 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-01 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-01 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-02-01 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-02-01 | 2025-01-30 | 2025-02-02 | Dhaneshwar Mahto | 37.73 | 9.4325 | TA325
2025-02-01 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-02-01 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-01 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-02-01 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-02-01 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-01 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-01 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-02-01 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-01 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-01 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-01 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-01 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-01 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-01 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-02-01 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-02-02 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-02 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-02 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-02-02 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-02-02 | 2025-01-30 | 2025-02-02 | Dhaneshwar Mahto | 37.73 | 9.4325 | TA325
2025-02-02 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-02-02 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-02 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-02-02 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-02 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-02 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-02-02 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-02 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-02 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-02 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-02 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-02 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-02 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-02-02 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-02-03 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-03 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-03 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-02-03 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-02-03 | 2025-02-03 | 2025-02-07 | Dhaneshwar Mahto | 39.459 | 7.8918 | TA325
2025-02-03 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-02-03 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-03 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-03 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-02-03 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-03 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-03 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-02-03 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-03 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-03 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-03 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-03 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-03 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-03 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-02-04 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-04 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-04 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-02-04 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-02-04 | 2025-02-03 | 2025-02-07 | Dhaneshwar Mahto | 39.459 | 7.8918 | TA325
2025-02-04 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-02-04 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-04 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-04 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-02-04 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-04 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-04 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-04 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-04 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-04 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-04 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-04 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-04 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-04 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-02-04 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-05 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-05 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-05 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-02-05 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-05 | 2025-02-03 | 2025-02-07 | Dhaneshwar Mahto | 39.459 | 7.8918 | TA325
2025-02-05 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-05 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-05 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-05 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325
2025-02-05 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-05 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-05 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-05 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-05 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-05 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-05 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-05 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-05 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-05 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-02-05 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-06 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-06 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-06 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-06 | 2025-02-03 | 2025-02-07 | Dhaneshwar Mahto | 39.459 | 7.8918 | TA325
2025-02-06 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-06 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-06 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-06 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325
2025-02-06 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-06 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-06 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-06 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-06 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-06 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-06 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-06 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-06 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-06 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-02-06 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-07 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-07 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-07 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-07 | 2025-02-03 | 2025-02-07 | Dhaneshwar Mahto | 39.459 | 7.8918 | TA325
2025-02-07 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-07 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-07 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-07 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325
2025-02-07 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-07 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-07 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-07 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-07 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-07 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-07 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-07 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-07 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-07 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-08 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-08 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-08 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-08 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-08 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-08 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-08 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325
2025-02-08 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-08 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-08 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-08 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-08 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-08 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-08 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-08 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-09 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-09 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-09 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-09 | 2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325
2025-02-09 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-09 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-09 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-09 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325
2025-02-09 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-09 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-09 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-09 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-09 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-09 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-09 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-09 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-09 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-10 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-10 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-10 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-10 | 2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325
2025-02-10 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-10 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-10 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325
2025-02-10 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-10 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-10 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-10 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-10 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-10 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-10 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-10 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-11 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-11 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-11 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-11 | 2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325
2025-02-11 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-11 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-11 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325
2025-02-11 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-11 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-11 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-11 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-11 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-11 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-11 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-11 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-11 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-11 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-12 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-12 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-12 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-12 | 2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325
2025-02-12 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-12 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325
2025-02-12 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-12 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-12 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-12 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-12 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-12 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-12 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-12 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-12 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-12 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-13 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-13 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-13 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-13 | 2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325
2025-02-13 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-13 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325
2025-02-13 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-13 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-13 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-13 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-13 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-13 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-13 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-13 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-13 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-13 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-14 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-14 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-14 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-14 | 2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325
2025-02-14 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-14 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-14 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325
2025-02-14 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-14 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-14 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-14 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-14 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-14 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-14 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-14 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-14 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-14 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-14 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-15 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-15 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-15 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-15 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-15 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-15 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-15 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-15 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-15 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-15 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-15 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-15 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-15 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-15 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-15 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-15 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-16 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-16 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-16 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325
2025-02-16 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-16 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-16 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-16 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-16 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-16 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-16 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-16 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-16 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-16 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-16 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-16 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-16 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-17 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-17 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-17 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-17 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325
2025-02-17 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-17 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-17 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-17 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-17 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-17 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-17 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-17 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-17 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-17 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-17 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-17 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-17 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-18 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-18 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-18 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-18 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325
2025-02-18 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-18 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-18 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-18 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-18 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-18 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-18 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-18 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-18 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-18 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-18 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-19 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-19 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-19 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325
2025-02-19 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-19 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-19 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-19 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-19 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-19 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-19 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-19 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-19 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-19 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-19 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-20 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-20 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-20 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325
2025-02-20 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-20 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-20 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-20 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-20 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-20 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-20 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-20 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-20 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-20 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-20 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-20 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-21 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-21 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325
2025-02-21 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-21 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-21 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-21 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-21 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-21 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-21 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-21 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-21 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-21 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-21 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-21 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-21 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-22 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-22 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-22 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325
2025-02-22 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-22 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-22 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-22 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-22 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-22 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-22 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-22 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-22 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-22 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-22 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-22 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-22 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-02-23 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-23 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-02-23 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-23 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-23 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-23 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-23 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-23 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-23 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-23 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-23 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-23 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-23 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-23 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-23 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-23 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-02-24 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-24 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-02-24 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325
2025-02-24 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-24 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-24 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325
2025-02-24 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-24 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-24 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-24 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-24 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-24 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-24 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-24 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-24 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-02-25 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-25 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-02-25 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325
2025-02-25 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-25 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-25 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325
2025-02-25 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-25 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-25 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-25 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-25 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-25 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-25 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325
2025-02-25 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-25 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-25 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-02-26 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-26 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-02-26 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325
2025-02-26 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-26 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-26 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325
2025-02-26 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-26 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-26 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-26 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-02-26 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-26 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-26 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325
2025-02-26 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-02-26 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-26 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-26 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-02-27 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-27 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-02-27 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-02-27 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325
2025-02-27 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-27 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-27 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325
2025-02-27 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-27 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-27 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-02-27 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-27 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-27 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325
2025-02-27 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-02-27 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-27 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-27 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-02-28 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-28 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-02-28 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-02-28 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325
2025-02-28 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-28 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-28 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325
2025-02-28 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-28 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-02-28 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-28 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-28 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325
2025-02-28 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-02-28 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-28 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-28 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-01 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-01 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-01 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-03-01 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325
2025-03-01 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-03-01 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-03-01 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-01 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-01 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-01 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-01 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-01 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-01 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-01 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-01 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-02 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-02 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-02 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-03-02 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325
2025-03-02 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-03-02 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-03-02 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325
2025-03-02 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-02 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-02 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-02 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-02 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-02 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-02 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-02 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-02 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-02 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-03 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-03 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-03 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-03-03 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-03-03 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-03-03 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325
2025-03-03 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-03 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-03 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-03 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-03 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-03 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-03 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-03 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-03 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-03 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-03 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-04 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-04 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-04 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-03-04 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-04 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-03-04 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325
2025-03-04 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-04 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-04 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-04 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-04 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-04 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-04 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-04 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-04 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-04 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-05 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-05 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-05 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-03-05 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-05 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2025-03-05 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-05 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325
2025-03-05 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-05 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-05 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-05 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-05 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-05 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-05 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-05 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-05 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-05 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-06 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-06 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-06 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-06 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2025-03-06 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-06 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325
2025-03-06 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-06 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-06 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-06 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-06 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-06 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-06 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-06 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-06 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-06 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-07 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-07 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-07 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-07 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-07 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2025-03-07 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-07 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325
2025-03-07 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-07 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-07 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-07 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-07 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-07 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-07 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-07 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-07 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-07 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-08 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-08 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-08 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-08 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-08 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2025-03-08 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-08 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325
2025-03-08 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-08 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-08 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-08 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-08 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-08 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-08 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-08 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-08 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-08 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-09 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-09 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-09 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-09 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-09 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2025-03-09 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-09 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325
2025-03-09 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-09 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-09 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-09 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-09 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-09 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-09 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-09 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-09 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-09 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-09 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-10 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-10 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-10 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-10 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-10 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2025-03-10 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-10 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325
2025-03-10 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-10 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-10 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-10 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-10 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-10 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-10 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-10 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-10 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-11 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-11 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-11 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-11 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-11 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-11 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-11 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-11 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-11 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-11 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-11 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-11 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-11 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-11 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-12 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-12 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-12 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-12 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-12 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-12 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-12 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-12 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-12 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-12 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-12 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-12 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-12 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-12 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-13 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-13 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-13 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-13 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-13 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-13 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-13 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-13 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-13 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-13 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-13 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-03-13 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-13 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-13 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-13 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-14 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-14 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-14 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-14 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-14 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-14 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-14 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-14 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-14 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-14 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-14 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-03-14 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-14 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-14 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-14 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-15 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-15 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-15 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-15 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-15 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-15 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-15 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-15 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-15 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-15 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-15 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-15 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-15 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-03-15 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-15 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-15 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-15 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-16 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-16 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-16 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-16 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-16 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325
2025-03-16 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-16 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-16 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-16 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-16 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-16 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-16 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-16 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-03-16 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-16 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-16 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-16 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-17 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-17 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-17 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-17 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325
2025-03-17 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325
2025-03-17 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-17 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-17 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-17 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-17 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-17 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-17 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-03-17 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-17 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-17 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-17 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-18 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-18 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-18 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-18 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325
2025-03-18 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325
2025-03-18 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-18 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-18 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-18 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-18 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-18 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-18 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-03-18 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-18 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-18 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-18 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325
2025-03-18 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-19 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-19 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-19 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-19 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-19 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325
2025-03-19 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325
2025-03-19 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-19 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-19 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-19 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-19 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-19 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-19 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-19 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-19 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325
2025-03-19 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-19 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-19 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-20 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-20 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-20 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-20 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-20 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325
2025-03-20 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325
2025-03-20 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-20 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-20 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-20 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-20 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-20 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-20 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-20 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-20 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-20 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325
2025-03-20 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-20 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-20 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-21 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-21 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-21 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-21 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-21 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-21 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325
2025-03-21 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-21 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-21 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-21 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-21 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-21 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-21 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-21 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-21 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-21 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325
2025-03-21 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-21 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-21 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-22 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-22 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-22 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-22 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325
2025-03-22 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-22 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-22 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325
2025-03-22 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-22 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-22 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-22 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-22 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-22 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-22 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-22 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-22 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-22 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-22 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325
2025-03-22 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-22 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-22 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-23 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-23 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-23 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-23 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325
2025-03-23 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-23 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325
2025-03-23 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-23 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-23 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-23 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-23 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-23 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-23 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-23 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-23 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-23 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-23 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-23 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-24 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-24 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-24 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325
2025-03-24 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-24 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-24 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325
2025-03-24 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-24 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-24 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-24 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-24 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-24 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-24 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-24 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-24 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-24 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-24 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-24 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-25 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-25 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-25 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325
2025-03-25 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-25 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-25 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325
2025-03-25 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-25 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-25 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-25 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-25 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-25 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-25 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-25 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-25 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-25 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-25 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-25 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-25 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-26 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-26 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-03-26 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-26 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325
2025-03-26 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-26 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-26 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-03-26 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-26 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-26 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-26 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-26 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-26 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-26 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-26 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-26 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-26 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-26 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-26 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-26 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-27 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-27 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-03-27 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-27 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325
2025-03-27 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-27 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-27 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-03-27 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-27 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-27 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-27 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-27 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-27 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-27 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-27 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-27 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-27 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-27 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-27 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-27 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-28 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-28 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-03-28 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-03-28 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-28 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325
2025-03-28 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-28 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-03-28 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-28 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-28 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-28 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-28 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-28 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-28 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-28 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-28 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-28 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-29 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-29 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-03-29 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-03-29 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-29 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325
2025-03-29 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-29 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-03-29 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-29 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-29 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-29 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-29 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-29 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-30 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-30 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-03-30 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-03-30 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-30 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325
2025-03-30 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-30 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-03-30 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-30 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-30 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-03-30 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-30 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-30 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-31 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-31 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-03-31 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-03-31 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325
2025-03-31 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-31 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-03-31 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-31 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-31 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-03-31 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-31 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-31 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-01 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-01 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-04-01 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-01 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-04-01 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-04-01 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-01 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-01 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-01 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-04-01 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-01 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-01 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-04-01 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-01 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-01 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-02 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-02 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-04-02 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-02 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-02 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-02 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-02 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-04-02 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-02 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-02 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-02 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-02 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-02 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-02 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-02 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-03 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-03 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-04-03 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-03 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-03 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-03 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-03 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-04-03 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-03 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-03 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-03 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-03 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-03 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-03 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-03 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-03 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-03 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-04 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-04 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-04 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-04 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-04-04 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-04 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-04 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-04 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-04-04 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-04 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-04 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-04 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-04 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-04 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-04 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-04 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-04 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-04 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-05 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-05 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-05 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-05 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325
2025-04-05 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-04-05 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-05 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-05 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-05 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-04-05 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-05 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-05 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-05 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-05 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-05 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-05 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-05 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-05 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-05 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-06 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-06 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-06 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-06 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325
2025-04-06 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-06 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-06 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-04-06 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-06 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-06 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-06 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-04-06 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-06 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-06 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-06 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-06 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-06 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-06 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-06 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-06 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-06 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-06 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-07 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-07 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-07 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-07 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325
2025-04-07 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-07 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-07 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-04-07 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-07 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-07 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-07 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-07 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-07 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-07 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-07 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-07 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-07 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-07 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-07 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-07 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-08 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-08 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-08 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-08 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-08 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325
2025-04-08 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-08 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-08 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-04-08 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-08 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-08 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-08 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-08 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-08 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-08 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-08 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-08 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-08 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-08 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-08 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-08 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-09 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-09 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-09 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-09 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-09 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325
2025-04-09 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-09 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-09 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-04-09 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-09 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-09 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-09 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-09 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-09 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-09 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-09 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-09 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-09 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-09 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-09 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-10 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-10 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-10 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-10 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-10 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325
2025-04-10 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-10 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-10 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-10 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-10 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-10 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-10 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-10 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-10 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-10 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-10 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-10 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-10 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-10 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-11 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-11 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-11 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-11 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-11 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325
2025-04-11 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-11 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-11 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-04-11 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-11 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-11 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-11 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-11 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-11 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-11 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-11 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-11 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-11 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-11 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-11 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-12 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-12 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-12 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-12 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-12 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-12 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-04-12 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-12 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-12 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-12 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-12 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-12 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-12 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-12 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-12 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-12 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-13 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-13 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-13 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-13 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-13 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-04-13 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-13 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-13 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-13 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-13 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-13 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-13 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-13 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-13 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-14 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-14 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-14 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-14 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-14 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-04-14 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-14 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-14 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-14 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-14 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-14 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-14 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-14 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-14 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-15 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-15 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-15 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-15 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-15 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-04-15 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-15 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-15 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-15 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-15 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-15 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-15 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-15 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-15 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-15 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-16 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-16 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-16 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-16 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-16 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-16 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-04-16 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-16 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-16 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-16 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-16 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-16 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-16 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-16 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-16 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-16 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-17 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-17 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-17 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-17 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-17 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-17 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-17 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-17 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-17 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-17 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-17 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-17 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-17 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-17 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-17 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-17 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-18 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-18 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-18 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-18 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-18 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-18 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-18 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-18 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-18 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-18 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-18 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-18 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-18 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-18 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-18 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-18 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-18 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-18 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-18 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-18 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-18 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-19 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-19 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-19 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-19 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-19 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-19 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-19 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-19 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-19 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-19 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-19 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-19 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-19 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-19 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-19 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-19 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-19 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-19 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-19 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-19 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-20 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-20 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-20 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-20 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-20 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-20 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-20 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-20 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-20 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-20 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-20 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-20 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-20 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-20 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-20 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-20 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-20 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-20 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-20 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-20 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-20 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-21 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-21 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-21 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-21 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-21 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-21 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-21 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-21 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-21 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-21 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-21 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-21 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-21 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-21 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-21 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-21 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-21 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-21 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-21 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-21 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-21 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-22 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-22 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-22 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-22 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-22 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-22 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-22 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-22 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-22 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-22 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-22 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-22 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-22 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-22 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-22 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-22 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-22 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-22 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-22 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-22 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-22 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-22 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-23 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-23 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-23 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-23 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-23 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-23 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-23 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-23 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-23 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-23 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-23 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-23 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-23 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325
2025-04-23 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-23 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-23 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-23 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-23 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-24 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-24 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-24 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-24 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-24 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-24 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-24 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-24 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-24 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-24 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-24 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-24 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-24 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-24 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-24 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-24 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325
2025-04-24 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-24 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-24 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-24 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-24 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-25 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-25 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-25 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-25 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-25 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-25 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-25 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-25 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-25 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-25 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-25 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-25 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-25 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-25 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-25 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-25 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325
2025-04-25 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-25 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-25 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-25 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-25 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-26 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-26 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-26 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-26 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-26 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-26 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-26 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-26 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-26 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-26 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-26 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-26 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-26 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-26 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325
2025-04-26 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-26 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-26 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-26 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-26 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-27 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-27 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-27 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-27 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-27 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-27 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-27 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-27 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-27 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-27 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-27 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-27 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-27 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-27 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325
2025-04-27 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-27 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-27 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-27 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-28 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-28 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-28 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-28 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-28 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-04-28 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-28 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-28 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-28 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-04-28 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-28 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-28 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-28 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-28 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-28 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-28 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-28 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-04-28 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-28 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-29 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-29 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-29 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-04-29 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-29 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-29 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-04-29 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-29 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-29 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-29 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-04-29 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-29 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-29 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-29 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-29 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-04-29 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-29 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-04-29 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-04-29 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-30 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-30 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-04-30 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-30 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-04-30 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-04-30 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-30 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-30 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-04-30 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-30 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-30 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-30 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-30 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-04-30 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-30 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-04-30 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-04-30 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-05-01 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-01 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-01 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-05-01 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-05-01 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-05-01 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-01 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-01 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-05-01 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-01 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-01 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-05-01 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-05-01 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-01 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-02 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-02 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-02 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-05-02 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-05-02 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-05-02 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-02 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-02 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-02 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-05-02 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-02 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-02 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-05-02 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-05-02 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-02 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-02 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-02 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-03 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-03 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-03 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-05-03 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-05-03 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-05-03 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-03 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-03 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-03 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-05-03 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-03 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-03 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-03 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-05-03 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-05-03 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-03 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-03 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-03 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-04 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-04 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-04 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-04 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-05-04 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-05-04 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-04 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-04 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-04 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-05-04 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-04 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-04 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-04 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-04 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-05-04 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-05-04 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-04 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-04 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-04 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-05 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-05 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-05 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-05 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-05-05 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-05-05 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-05 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-05 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-05 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-05-05 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-05 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-05 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-05 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-05 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-05-05 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-05 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-05 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-05 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-06 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-06 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-06 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-06 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
2025-05-06 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-05-06 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-06 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-06 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-06 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-06 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-06 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-06 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-06 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-06 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-06 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-06 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-06 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-06 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-07 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-07 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-07 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-07 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-07 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-07 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-07 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-07 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-07 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-07 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-07 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-07 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-07 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-07 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-07 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-07 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-08 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-08 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-08 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-08 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-08 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-08 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-08 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-08 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-08 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-08 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-08 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-08 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-08 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-08 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-08 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-08 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-08 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-09 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-09 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-09 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-09 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-09 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-09 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-09 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-09 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-09 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-09 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-09 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-09 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-09 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-09 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-09 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-09 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-09 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-09 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-10 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-10 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-10 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-10 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-10 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-10 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-10 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-10 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-10 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-10 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-10 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-10 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-10 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-10 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-10 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-10 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-11 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-11 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-11 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-11 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-11 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-11 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-11 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-11 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-11 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-11 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-11 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-11 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-11 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-11 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-11 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-11 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-11 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-12 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-12 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-12 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-12 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-12 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-12 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-12 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-12 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-12 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-12 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-13 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-13 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-13 | 2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-05-13 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-13 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-13 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-13 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-13 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-13 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-13 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-13 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-13 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-14 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-14 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-14 | 2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-05-14 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-14 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-14 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-14 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-14 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-14 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-14 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-14 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-14 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-15 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-15 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-15 | 2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-05-15 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-15 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-15 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-15 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-15 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-15 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-15 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-15 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-15 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-15 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-16 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-16 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-16 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-16 | 2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-05-16 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-16 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-16 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-16 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-16 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-16 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-16 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-16 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-16 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-17 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-17 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-17 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-17 | 2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-05-17 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-17 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-17 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-17 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-17 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-17 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-17 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-17 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-18 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-18 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-18 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-18 | 2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-05-18 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-18 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-18 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-18 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-18 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-18 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-18 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-18 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-19 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-19 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-19 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-19 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-19 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-19 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-19 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-19 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-20 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-20 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-20 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-20 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-20 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-20 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-21 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-21 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-21 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-21 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-22 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-22 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-22 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-23 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-23 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-24 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-24 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-24 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-05-25 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-25 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-05-26 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-05-27 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-05-28 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-28 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-05-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-05-29 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-29 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-05-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-05-29 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-05-30 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-30 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-05-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-05-30 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-05-31 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-31 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-05-31 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-05-31 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-01 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-01 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-06-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-01 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-02 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-02 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-06-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-02 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-03 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-03 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-06-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-03 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-04 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-04 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-06-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-04 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-05 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-05 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-06-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-05 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-06 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-06 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-06 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-07 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-07 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-08 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-08 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-09 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-10 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-11 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-11 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-12 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-12 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-13 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-13 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-14 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-15 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-16 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-17 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-18 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-19 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-20 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-21 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-22 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-23 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-24 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-25 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-26 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-27 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-28 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-29 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-06-30 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-01 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-07-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-02 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-07-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-03 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-07-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-04 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-07-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-07-31 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-06 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-07 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-08 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-09 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-10 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-11 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-12 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-13 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-14 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-15 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-16 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-17 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-18 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-19 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-20 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-21 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-22 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-23 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-24 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-25 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-26 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-27 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-28 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-29 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-30 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-08-31 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-08-31 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-01 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-02 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-03 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-04 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-05 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-06 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-07 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-08 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-09 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-10 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-11 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-12 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-13 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-14 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
2025-09-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2025-09-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2024-01-28 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-01-29 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-01-30 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-01-31 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-01 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-01 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-02 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-02 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-03 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-03 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-03 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-04 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-04 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-04 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-05 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-05 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-05 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-06 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-06 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-06 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-07 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-07 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-07 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-08 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-08 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-08 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-09 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-09 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-09 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-09 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-10 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-10 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-10 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-10 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-11 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-11 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-11 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-11 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-12 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-12 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-12 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-12 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-13 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-13 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-13 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-13 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-13 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-14 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-14 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-14 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-14 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-15 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-15 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-15 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-15 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-15 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-15 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-16 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-16 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-16 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-16 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-17 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-17 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-17 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-17 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-17 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-18 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-18 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-18 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-18 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-18 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-18 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-19 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-19 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-19 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-19 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-19 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-20 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-20 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-20 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-20 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-20 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-20 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-20 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-21 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-21 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-21 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-21 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-21 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-21 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-22 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-22 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-22 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-22 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-22 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-22 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-23 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-23 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-23 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-23 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-23 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-24 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-24 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-24 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-24 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-24 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-24 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-24 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-24 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-25 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-25 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-25 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-25 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-25 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-26 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-26 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-26 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-26 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408
2024-02-26 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-26 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-26 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-02-27 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-27 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-27 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408
2024-02-27 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-27 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-02-28 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-28 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-28 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408
2024-02-28 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-28 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-02-29 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-02-29 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-29 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-02-29 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-02-29 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-29 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-29 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-03-01 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-01 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-01 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-01 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-02 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-02 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-02 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-02 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-03 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-03 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-03 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-03 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-04 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-04 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-04 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-04 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-05 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-05 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-05 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-06 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-06 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-06 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-06 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-07 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-07 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-07 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-07 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-08 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-08 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-08 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-09 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-09 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-09 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-10 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-10 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-10 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-11 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-11 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-11 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-11 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-11 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-11 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-12 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-12 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-12 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-13 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-13 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-13 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-14 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-14 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-14 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-15 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-15 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-15 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-15 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-16 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-16 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-16 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-16 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-17 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-17 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-17 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-18 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-18 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-18 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-18 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-19 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-19 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-19 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-20 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-20 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-20 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-20 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-21 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-21 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-21 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-21 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-22 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-22 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-22 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-22 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-22 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-23 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-23 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-23 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-23 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-23 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-24 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-24 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-24 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-24 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-25 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-25 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-25 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-25 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-26 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-26 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-26 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-26 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-26 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-26 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-27 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-27 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-27 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-27 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-28 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-28 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-28 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-28 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-29 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-29 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-29 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-30 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-30 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-30 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-30 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-31 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-31 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-31 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-31 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-03-31 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-04-01 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-01 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-01 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-04-01 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-02 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-02 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-02 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-04-02 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-03 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-03 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-03 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-04-03 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-03 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-04 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-04 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-04 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-04 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-05 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-05 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-05 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-06 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-06 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-06 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-06 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-06 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-07 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-07 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-07 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-07 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-07 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-07 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-08 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-08 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-08 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-08 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-09 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-09 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-09 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-10 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-10 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-10 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-10 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-11 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-11 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-11 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-12 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-12 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-13 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-13 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-13 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-14 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-14 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-15 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-15 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-15 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-16 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-16 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-16 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-16 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-17 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-17 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-17 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-17 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-17 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-18 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-18 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-18 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-18 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-18 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-19 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-19 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-19 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-19 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-19 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-20 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-20 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-20 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-20 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-20 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-21 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-21 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-21 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-21 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-21 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-21 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-22 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-22 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-22 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-22 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-22 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-22 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-22 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-23 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-23 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-23 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-23 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-23 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-24 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-24 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-24 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-24 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-24 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-25 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-25 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-25 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-25 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-25 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-26 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-26 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-26 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-26 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-27 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-27 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-27 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-27 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-27 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-27 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-28 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-28 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-28 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-28 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-29 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-29 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-29 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-04-29 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-29 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-30 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-30 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-04-30 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-30 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-05-01 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-05-01 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-01 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-01 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-05-02 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-05-02 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-02 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-02 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-05-03 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-05-03 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-03 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-03 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-05-03 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-04 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-04 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-04 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-05 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-05 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-05 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-05 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-05 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-06 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-06 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-06 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-07 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-07 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-07 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-08 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-08 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-08 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-09 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-09 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-09 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-10 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-10 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-10 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-11 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-11 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-11 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-11 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-12 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-12 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-12 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-12 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-12 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-13 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-13 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-13 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-13 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-14 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-14 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-14 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-14 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-15 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-15 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-15 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-15 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-16 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-16 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-16 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-16 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-16 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-17 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-17 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-17 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-17 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-18 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-18 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-18 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-18 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-18 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-19 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-19 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-19 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-19 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-19 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-20 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-20 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-20 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-20 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-21 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-21 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-21 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-21 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-22 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-22 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-22 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-22 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-23 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-23 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-23 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-23 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-24 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-24 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-24 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-25 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-25 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-25 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-26 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-26 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-26 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-27 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-27 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-27 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-28 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-28 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-28 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-29 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-05-29 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-29 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-29 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-30 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-05-30 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-30 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-30 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-31 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-05-31 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-06-01 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-01 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-02 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-02 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-03 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-03 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-04 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-04 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-05 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-05 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-06 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-06 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-07 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-07 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-08 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-08 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-09 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-09 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-10 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-10 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-11 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-11 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-12 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-12 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-13 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-13 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-14 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-14 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-15 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-15 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-16 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-16 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-17 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-17 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-18 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-18 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-19 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-19 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-20 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-21 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-22 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-23 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-24 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-25 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-26 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-27 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-07-04 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-05 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-06 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-07 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-08 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-09 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-10 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-11 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-12 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-15 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-16 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-17 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-18 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-19 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-20 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-21 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-22 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-23 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-24 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-25 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-26 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-08-13 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-14 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-15 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-16 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-17 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-18 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-19 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-20 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-20 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-21 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-22 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-23 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-23 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-24 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-24 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-25 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-25 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-26 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-26 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-27 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-27 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-28 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-28 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-28 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-08-28 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-29 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-29 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-29 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-08-29 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-30 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-30 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-30 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-08-30 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-30 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-08-31 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-31 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-31 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-08-31 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-08-31 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-01 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-01 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-01 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-01 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-01 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-02 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-02 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-02 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-02 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-02 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-03 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-03 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-03 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-03 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-03 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-04 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-04 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-04 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-04 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-04 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-05 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-05 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-05 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-05 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-05 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-06 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-06 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-06 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-06 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-06 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-06 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-07 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-07 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-07 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-07 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-07 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-08 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-08 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-08 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-08 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-08 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-08 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-09 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-09 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-09 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-09 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-09 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-10 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-10 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-10 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-10 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-10 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-11 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-11 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-11 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-11 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-11 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-12 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-12 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-12 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-12 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-12 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-13 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-13 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-13 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-13 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-13 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-14 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-14 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-14 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-14 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-15 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-15 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-15 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-15 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-16 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-16 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-16 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-16 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-17 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-17 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-17 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-17 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-18 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-18 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-18 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-18 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-18 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-19 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-19 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-19 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-19 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-19 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-19 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-19 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-20 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-20 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-20 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-20 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-20 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-21 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-21 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-21 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-21 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-21 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-21 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-22 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-22 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-22 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-22 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-22 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-22 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-23 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-23 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-23 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-23 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-23 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-23 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-24 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-24 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-24 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-24 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-24 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-24 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-25 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-25 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-25 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-25 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-25 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-25 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-25 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-26 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-26 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-26 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-26 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-26 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-26 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-27 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-27 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-27 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-27 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-09-27 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-27 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-28 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-28 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-28 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-28 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-09-28 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-09-28 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-09-28 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-28 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-29 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-29 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-29 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-29 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-09-29 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-09-29 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-09-29 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-29 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-30 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-30 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-30 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-09-30 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-09-30 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-09-30 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-30 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-01 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-01 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-10-01 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-01 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-10-01 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-01 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-10-01 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-02 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-02 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-10-02 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-02 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-10-02 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-02 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-02 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-03 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-03 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-10-03 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-03 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-10-03 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-03 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-03 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-04 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-04 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-04 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-04 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-04 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-04 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-05 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-05 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-05 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-05 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-05 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-05 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-05 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-06 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-06 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-06 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-06 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-06 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-06 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-06 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-07 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-07 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-07 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-07 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-07 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-07 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-07 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-07 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-07 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-07 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-08 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-08 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-08 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-08 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-08 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-08 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-08 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-08 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-09 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-09 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-09 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-09 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-09 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-09 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-10 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-10 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-10 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-10 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-10 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-10 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-10 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-11 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-11 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-11 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-11 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-11 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-11 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-12 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-12 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-12 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-12 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-12 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-12 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-12 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-13 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-13 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-13 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-13 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-13 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-13 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-13 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-13 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-14 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-14 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-14 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-14 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-14 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-14 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-14 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-14 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-15 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-15 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-15 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-15 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-15 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-15 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-15 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-15 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-16 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-16 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-16 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-16 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-16 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-16 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-16 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-16 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-17 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-17 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-17 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-17 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-17 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-17 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-17 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-17 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-18 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-18 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-18 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-18 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-18 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-18 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-18 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-18 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-18 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-18 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-19 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-19 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-19 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-19 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-19 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-19 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-19 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-19 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-19 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-19 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-19 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-20 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-20 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-20 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-20 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-20 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-20 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-20 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-20 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-20 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-20 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-21 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-21 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-21 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-21 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-21 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-21 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-21 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-21 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-21 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-21 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-21 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-22 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-22 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-22 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-22 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-22 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-22 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-22 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-22 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-22 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-22 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-22 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-23 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-23 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-23 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-23 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-23 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-23 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-23 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-23 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-23 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-23 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-23 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-24 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-24 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-24 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-24 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-24 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-24 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-24 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-24 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-24 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-24 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-24 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-24 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-25 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-25 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-25 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-25 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-25 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-25 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-25 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-25 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-25 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-25 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-26 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-26 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-26 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-26 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-26 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-26 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-26 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-26 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-26 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-26 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-27 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-27 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-27 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-27 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-27 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-27 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-27 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-27 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-10-28 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-28 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-28 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-28 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-28 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-28 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-10-29 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-29 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-29 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-29 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-29 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-29 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-10-30 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-30 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-30 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-30 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-30 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-10-31 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-31 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-31 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-31 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-11-01 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-11-01 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-01 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-11-01 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-01 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-01 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-11-01 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-02 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-11-02 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-02 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-02 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-11-02 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-02 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-02 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-11-02 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-03 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-03 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-11-03 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-03 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-03 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-03 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-03 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-04 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-04 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-11-04 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-04 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-04 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-04 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-04 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-04 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-04 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-05 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-05 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-11-05 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-05 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-05 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-05 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-05 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-05 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-05 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-06 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-06 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-06 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-06 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-06 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-06 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-06 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-06 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-07 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-07 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-07 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-07 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-07 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-07 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-07 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-07 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-07 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-08 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-08 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-08 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-08 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-08 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-08 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-08 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-08 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-08 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-09 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-09 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-09 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-09 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-09 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-09 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-09 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-09 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-09 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-10 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-10 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-10 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-10 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-10 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-10 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-10 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-11 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-11 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-11 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-11 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-11 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-11 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-11 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-11 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-12 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-12 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-12 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-12 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-12 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-12 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-12 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-12 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-12 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-13 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-13 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-13 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-13 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-13 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-13 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-13 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-13 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-13 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-13 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-14 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-14 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-14 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-14 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-14 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-14 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-14 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-14 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-14 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-15 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-15 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-15 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-15 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-15 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-15 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-15 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-15 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-16 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-16 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-16 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-16 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-16 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-16 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-16 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-16 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-17 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-17 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-17 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-17 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-17 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-17 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-17 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-17 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-17 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-18 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-18 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-18 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-18 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-18 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-18 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-18 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-18 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-18 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-19 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-19 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-19 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-19 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-19 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-19 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-20 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-20 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-20 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-20 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-20 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-20 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-21 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-21 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-21 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-21 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-21 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-22 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-22 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-22 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-22 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-22 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-22 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-23 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-23 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-23 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-23 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-23 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-24 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-24 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-24 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-24 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-24 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-24 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-24 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-25 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-25 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-25 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-25 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-25 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-25 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-25 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-26 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-26 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-26 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-26 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-26 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-26 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-26 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-27 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-27 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-27 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-27 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-27 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-27 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-27 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-27 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-28 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-28 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-28 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-28 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-11-28 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-28 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-28 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-29 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-29 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-29 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-29 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-11-29 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-29 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-29 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-30 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-30 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-30 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-30 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-11-30 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-11-30 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-30 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-30 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-01 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-01 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-01 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-01 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-01 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-12-02 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-02 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-02 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-02 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-02 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-12-02 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-03 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-03 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-03 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-03 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-03 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-12-03 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-03 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-04 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-04 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-04 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-04 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-04 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-04 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-05 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-05 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-05 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-05 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-05 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-05 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-06 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-06 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-06 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-06 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-06 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-12-07 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-07 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-07 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-07 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-12-08 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-08 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-08 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-12-09 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-09 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-09 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-09 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-09 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-12-10 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-10 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-10 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-10 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-11 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-11 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-11 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-11 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-12 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-12 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-12 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-13 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-13 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-13 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-14 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-14 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-15 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-15 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-16 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-16 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-20 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-21 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-22 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-23 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-24 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-25 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-25 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-25 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-26 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-26 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-26 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-27 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-27 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-27 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-28 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-28 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-28 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-29 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-29 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-29 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-30 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-30 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-30 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-31 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-31 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-31 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-01 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2025-01-01 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2025-01-01 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-02 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2025-01-02 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2025-01-02 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-03 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-03 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2025-01-03 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2025-01-03 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-04 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-04 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2025-01-04 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-04 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2025-01-04 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-05 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-05 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-05 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-05 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-06 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-06 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-06 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-06 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-07 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-07 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-07 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-07 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-08 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-08 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-08 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-08 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-09 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-09 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-09 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-09 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-10 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-10 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-10 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-10 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-11 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-11 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-11 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-11 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-11 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-11 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-12 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-12 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-12 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-12 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-12 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-12 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-13 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-13 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-13 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-13 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-13 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-13 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-14 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-14 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-14 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-14 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-14 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-14 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-15 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-15 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-15 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-15 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-15 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-15 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-16 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-16 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-16 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-16 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-16 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-16 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-17 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-17 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-17 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-17 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-17 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-17 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-18 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-18 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-18 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-18 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-18 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-19 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-19 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-19 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-19 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-19 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-20 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-20 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-20 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-21 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-21 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-21 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-21 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-22 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-22 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-22 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-22 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-23 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-23 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-23 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-23 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-24 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-24 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-24 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-24 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-25 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-25 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-25 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-25 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-26 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-26 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-26 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-26 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-27 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-27 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-27 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-27 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-28 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-28 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-28 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-28 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-29 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-29 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-29 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-29 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-29 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-01-30 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-30 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-30 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-01-31 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-01-31 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-31 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-01-31 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-01 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-01 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-02-01 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-01 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-02 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-02 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-02-02 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-02 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-02 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-03 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-03 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-03 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-03 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-04 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-04 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-04 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-04 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-05 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-05 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-05 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-05 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-05 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-06 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-06 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-06 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-06 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-06 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-07 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-07 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-07 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-07 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-08 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-08 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-08 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-08 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-09 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-09 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-09 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-09 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-10 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-10 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-10 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-10 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-11 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-11 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-11 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-11 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-12 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-12 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-12 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-12 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-13 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-13 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-13 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-13 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-14 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-14 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-14 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-14 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-15 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-15 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-15 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-16 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-16 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-16 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-17 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-17 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-17 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-18 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-18 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-18 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-19 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-19 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-19 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-20 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-20 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-20 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-21 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-21 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-22 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-22 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-23 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-23 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-24 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-24 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-25 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-25 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-26 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-26 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-26 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-02-27 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-27 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-27 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-02-28 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-28 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-28 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-01 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-01 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-01 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-02 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-02 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-02 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-03 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-03 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-03 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-04 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-04 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-04 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-05 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-05 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-05 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-06 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-06 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-06 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-07 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-07 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-07 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-08 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-08 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-08 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-09 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-09 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-09 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-09 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-10 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-10 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-10 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-10 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-11 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-11 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-11 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-12 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-12 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-12 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-13 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-13 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-13 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-13 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-14 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-14 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-14 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-14 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-15 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-15 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-15 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-15 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-16 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-16 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-16 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-16 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-17 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-17 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-17 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-18 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-18 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-18 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-19 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-19 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-19 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-20 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-20 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-20 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-20 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-21 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-21 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-21 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-21 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-22 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-22 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-22 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-22 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-23 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-23 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-23 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-23 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-24 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-24 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-24 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-24 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-25 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-25 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-25 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-25 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-26 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-26 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-26 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-26 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-27 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-27 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-27 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-27 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-28 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-28 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-28 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-28 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-29 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-29 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-29 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-29 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-30 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-30 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-30 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-31 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-31 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-31 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-31 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408
2025-03-31 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-01 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-01 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408
2025-04-01 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-02 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-02 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-02 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408
2025-04-02 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-03 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-03 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-03 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-03 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-04 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-04 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-04 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-04 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-05 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-05 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-05 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-06 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-06 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-06 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-06 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-07 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-07 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-07 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-08 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-08 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-08 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-09 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-09 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-09 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-10 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-10 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-11 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-11 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-12 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-12 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-13 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-13 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-14 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-14 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-15 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-16 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-17 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-18 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-19 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-20 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-21 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-22 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-23 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-24 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-25 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-26 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-27 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-04-27 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-28 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-04-28 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-29 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-04-30 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-05-01 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-05-02 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-07-10 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-11 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-12 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-13 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-14 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-15 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-16 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-17 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-18 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-18 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-19 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-19 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-20 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-21 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-22 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-23 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-24 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-25 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-26 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-27 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-27 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-07-28 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-28 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-07-29 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-07-30 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-07-31 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-08-01 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-08-02 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-08-02 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-03 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-08-03 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-04 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-05 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-06 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-07 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-08 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-09 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-09 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-10 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-11 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-12 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-13 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-14 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-16 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421
2024-08-17 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421
2024-08-18 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421
2024-08-19 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-20 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-21 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-22 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-22 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-23 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-23 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-24 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-24 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-25 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-26 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-27 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-28 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-29 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-29 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-08-29 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-08-30 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-08-30 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-08-31 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-08-31 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-01 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-09-01 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-02 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-09-02 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-03 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-09-03 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-04 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-09-04 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-05 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-09-05 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-06 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-09-06 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-07 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-08 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-09 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-09 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-10 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-10 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-11 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-11 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-12 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-12 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-13 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-14 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-14 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-14 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-15 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-15 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-15 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-16 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-16 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-16 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-17 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-17 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-17 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-18 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-18 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-18 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-19 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-19 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421
2024-09-19 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-19 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-20 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421
2024-09-20 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-20 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-21 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421
2024-09-21 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-21 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-22 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421
2024-09-22 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-23 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421
2024-09-23 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-24 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421
2024-09-24 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-25 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421
2024-09-25 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-26 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421
2024-09-26 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-26 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-09-27 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421
2024-09-27 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-27 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-09-28 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421
2024-09-28 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-28 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-09-29 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421
2024-09-29 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-29 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-09-30 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421
2024-09-30 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-30 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-10-01 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-01 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421
2024-10-01 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-01 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-01 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-10-02 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-02 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421
2024-10-02 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-02 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-02 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-10-03 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-03 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421
2024-10-03 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421
2024-10-03 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-03 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-03 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-10-04 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-04 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421
2024-10-04 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-04 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-05 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-05 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421
2024-10-05 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-05 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-05 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-05 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-06 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-06 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421
2024-10-06 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-06 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-06 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-06 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-07 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-07 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421
2024-10-07 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-07 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-07 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-07 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-08 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-08 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-08 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-08 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-08 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-09 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-09 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-09 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-09 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-09 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-10 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-10 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-10 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-10 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-10 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-11 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-11 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-11 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-11 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-11 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-12 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-12 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-12 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-12 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-12 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-13 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-13 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-13 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-13 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-13 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-14 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-14 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-14 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-14 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-14 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-15 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-15 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-15 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-16 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-16 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-16 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-16 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-16 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-17 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-17 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-17 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-17 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-17 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-17 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-18 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-18 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-18 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-18 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-18 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-18 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-19 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-19 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-19 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-19 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-19 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-19 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-19 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-20 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-20 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-20 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-20 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-20 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-20 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-21 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-21 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-21 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-21 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-21 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-21 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-21 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-22 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-22 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-22 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-22 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-22 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-22 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-23 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-23 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-23 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-23 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-23 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-23 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-24 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-24 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-24 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-24 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-24 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-24 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-25 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-25 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-25 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-25 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-25 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-25 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-26 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-26 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-26 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-26 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-26 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-26 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-27 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-27 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-10-27 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-27 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-10-27 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-27 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-28 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-10-28 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-28 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-10-28 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-29 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-10-29 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-29 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-10-29 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-30 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-10-30 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-30 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-10-30 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-31 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-10-31 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-10-31 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-11-01 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-11-01 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-01 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-01 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-11-02 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-11-02 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-02 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-02 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-03 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-11-03 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-03 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-03 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-04 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-11-04 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-04 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-04 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-05 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-05 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-11-05 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-05 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-05 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-06 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-06 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-11-06 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-06 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-06 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-07 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-07 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-11-07 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-07 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-07 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-07 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-08 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-08 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-08 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-08 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-09 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-09 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-09 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-09 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-09 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-10 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-10 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-10 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-10 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-10 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-11 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-11 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-11 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-11 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-11 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-12 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-12 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-12 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-12 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-12 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-12 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-13 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-13 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-13 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-13 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-13 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-13 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-14 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-14 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-14 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-14 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-14 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-14 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-15 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-15 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-15 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-15 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-15 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-16 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-16 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-16 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-16 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-16 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-17 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-17 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-17 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-17 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-17 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-18 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-18 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-18 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-18 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-18 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-19 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-19 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-19 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-19 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-19 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-20 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-20 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-20 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-20 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-20 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-21 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-21 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-21 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-21 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-21 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-22 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-22 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-22 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-22 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-22 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-23 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-23 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-23 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-23 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-23 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-24 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-24 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-24 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-24 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-24 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-24 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-25 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-25 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-25 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-25 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-25 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-26 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-26 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-26 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-26 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-26 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-11-27 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-27 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-27 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-27 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-11-28 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-28 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-28 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-28 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-11-29 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-29 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-29 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-29 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-11-30 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-30 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-30 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-30 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-12-01 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-12-01 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-12-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-02 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-12-02 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-12-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-03 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-03 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-12-03 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421
2024-12-03 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-04 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-04 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-12-04 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421
2024-12-04 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-05 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-05 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-12-05 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421
2024-12-05 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-06 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-06 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421
2024-12-06 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-07 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-07 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-07 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-08 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-08 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-08 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-09 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-09 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421
2024-12-09 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-10 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-10 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421
2024-12-10 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-11 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-11 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421
2024-12-11 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-11 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421
2024-12-12 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-12 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421
2024-12-12 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-12 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421
2024-12-13 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-13 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421
2024-12-13 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-13 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421
2024-12-14 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-14 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-14 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421
2024-12-15 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-15 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421
2024-12-15 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-15 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421
2024-12-16 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-16 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421
2024-12-16 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-16 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421
2024-12-17 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-17 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421
2024-12-17 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-17 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421
2024-12-18 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-18 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421
2024-12-18 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-18 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421
2024-12-19 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-19 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421
2024-12-19 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-19 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421
2024-12-20 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-20 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-20 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-20 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421
2024-12-21 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-21 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-21 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-21 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421
2024-12-22 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-22 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-22 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-22 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421
2024-12-23 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-23 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-23 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-23 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421
2024-12-24 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-24 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-24 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-24 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421
2024-12-25 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-25 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-25 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-25 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421
2024-12-26 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-26 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-26 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-26 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421
2024-12-27 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-27 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-27 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-27 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421
2024-12-27 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2024-12-28 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-28 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-28 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-28 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421
2024-12-28 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2024-12-28 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2024-12-29 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-29 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-29 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2024-12-29 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2024-12-30 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-30 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-30 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2024-12-30 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2024-12-31 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-31 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-31 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2024-12-31 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-01 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-01 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2025-01-01 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-02 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-02 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2025-01-02 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-03 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-03 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2025-01-03 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-03 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2025-01-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-04 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-04 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-04 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-04 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2025-01-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-05 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-05 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-05 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-05 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2025-01-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-06 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-06 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-06 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-06 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2025-01-07 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-07 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-07 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-07 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2025-01-08 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-08 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-08 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-08 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2025-01-09 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-09 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-09 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-10 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-10 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-10 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-11 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-11 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-11 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-12 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-12 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-12 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-13 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-13 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-13 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-14 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-14 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-14 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421
2025-01-15 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-15 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-15 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421
2025-01-16 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421
2025-01-16 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-16 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421
2025-01-17 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421
2025-01-17 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-17 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421
2025-01-18 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421
2025-01-18 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-18 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421
2025-01-18 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421
2025-01-19 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421
2025-01-19 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421
2025-01-19 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-19 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421
2025-01-20 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421
2025-01-20 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-20 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421
2025-01-21 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421
2025-01-21 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-21 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421
2025-01-22 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421
2025-01-22 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-22 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421
2025-01-22 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-22 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-23 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421
2025-01-23 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-23 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-23 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-23 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-24 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-24 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-24 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-24 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-25 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-25 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-25 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-25 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-26 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-26 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-26 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-26 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-27 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-27 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-27 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-27 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-28 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-28 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-01-28 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-28 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-29 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-01-29 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-29 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-30 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-01-30 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-30 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-01-30 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-30 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421
2025-01-31 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-01-31 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-01-31 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421
2025-02-01 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-02-01 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-01 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421
2025-02-02 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-02-02 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-02 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421
2025-02-03 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-02-03 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-03 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421
2025-02-04 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-02-04 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-04 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421
2025-02-05 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-02-05 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-05 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421
2025-02-06 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-02-06 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-06 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421
2025-02-07 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-02-07 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-07 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421
2025-02-08 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-02-08 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-08 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421
2025-02-09 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-02-09 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-09 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421
2025-02-10 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-10 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421
2025-02-10 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-10 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421
2025-02-11 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-11 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421
2025-02-11 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-11 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421
2025-02-12 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-12 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421
2025-02-12 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-12 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421
2025-02-13 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-13 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421
2025-02-13 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-13 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-14 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-14 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421
2025-02-14 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-14 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-15 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-15 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-15 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-15 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-16 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-16 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-16 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-16 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-17 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-17 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-17 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-17 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-18 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-18 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-18 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-18 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-19 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-19 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-19 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-19 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-19 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421
2025-02-20 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-20 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-20 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-20 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421
2025-02-21 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-21 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421
2025-02-21 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-21 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421
2025-02-22 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-22 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421
2025-02-22 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-22 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421
2025-02-23 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-23 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421
2025-02-23 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-23 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421
2025-02-24 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-24 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421
2025-02-24 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-24 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421
2025-02-25 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-25 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421
2025-02-25 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-25 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421
2025-02-26 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421
2025-02-26 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421
2025-02-26 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-26 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421
2025-02-27 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421
2025-02-27 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421
2025-02-27 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-27 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421
2025-02-28 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421
2025-02-28 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421
2025-02-28 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-28 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421
2025-03-01 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421
2025-03-01 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-01 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421
2025-03-01 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-03-01 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421
2025-03-02 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421
2025-03-02 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-02 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-02 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421
2025-03-03 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-03 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-03 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-03 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-03 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421
2025-03-04 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-04 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-04 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-04 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-04 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421
2025-03-05 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-05 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-05 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-05 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-05 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421
2025-03-06 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-06 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-06 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-06 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-06 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421
2025-03-07 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-07 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-07 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-07 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-07 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421
2025-03-08 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-08 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-08 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421
2025-03-08 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-08 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421
2025-03-09 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-09 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-09 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421
2025-03-09 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-09 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421
2025-03-10 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-10 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-10 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421
2025-03-10 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-10 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421
2025-03-11 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-11 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-11 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421
2025-03-11 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-11 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421
2025-03-12 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-12 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-12 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421
2025-03-12 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-12 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421
2025-03-13 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-13 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-13 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421
2025-03-13 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-13 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421
2025-03-14 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-14 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421
2025-03-14 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-14 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421
2025-03-15 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421
2025-03-15 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-15 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421
2025-03-15 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-15 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421
2025-03-16 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421
2025-03-16 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-16 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421
2025-03-16 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-16 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421
2025-03-16 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421
2025-03-17 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421
2025-03-17 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-17 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421
2025-03-17 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-17 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-17 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421
2025-03-18 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421
2025-03-18 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-18 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-18 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-18 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421
2025-03-19 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421
2025-03-19 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-19 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-19 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-19 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421
2025-03-20 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-20 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-20 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-20 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-20 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421
2025-03-21 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-21 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-21 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-21 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-21 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421
2025-03-22 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-22 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-22 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-22 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-22 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421
2025-03-23 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-23 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-23 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-23 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421
2025-03-23 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-23 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421
2025-03-24 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-24 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-24 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421
2025-03-24 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-24 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421
2025-03-25 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-25 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-25 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421
2025-03-25 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-25 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421
2025-03-26 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-26 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-26 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421
2025-03-26 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-26 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421
2025-03-27 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-27 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-27 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421
2025-03-27 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-27 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421
2025-03-28 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-28 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-28 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421
2025-03-28 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-03-28 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421
2025-03-29 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-29 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-03-29 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-29 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421
2025-03-29 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-03-29 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421
2025-03-29 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421
2025-03-30 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-03-30 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-30 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-03-30 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421
2025-03-30 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-03-30 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421
2025-03-31 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-03-31 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-03-31 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421
2025-03-31 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-03-31 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421
2025-04-01 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-01 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-04-01 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421
2025-04-01 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-01 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421
2025-04-02 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-02 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-04-02 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-02 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-02 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421
2025-04-03 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-03 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-04-03 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-03 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-03 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-04 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-04 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-04-04 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-04 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-04 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-05 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-05 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-04-05 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-05 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-05 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-06 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-06 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-06 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-06 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-06 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-07 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-07 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-07 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-07 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-07 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-08 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-08 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-08 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-08 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-08 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-09 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-09 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-09 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-09 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-09 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-10 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-10 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-10 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421
2025-04-10 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-10 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-11 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-11 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-11 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421
2025-04-11 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-11 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421
2025-04-12 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-12 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-12 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421
2025-04-12 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-12 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421
2025-04-13 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-13 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-13 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421
2025-04-13 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-13 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421
2025-04-14 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-14 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-14 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421
2025-04-14 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-14 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421
2025-04-15 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-15 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-15 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421
2025-04-15 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-15 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421
2025-04-16 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-16 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-16 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421
2025-04-16 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-16 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421
2025-04-17 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-17 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-17 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421
2025-04-17 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-17 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421
2025-04-18 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-18 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-18 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421
2025-04-18 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-18 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421
2025-04-19 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-19 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-19 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421
2025-04-19 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-19 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421
2025-04-19 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421
2025-04-20 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-20 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-20 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421
2025-04-20 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-20 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421
2025-04-21 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-21 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-21 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421
2025-04-21 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-21 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421
2025-04-22 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-22 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-22 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421
2025-04-22 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-22 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421
2025-04-23 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-23 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-23 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421
2025-04-23 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-23 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421
2025-04-24 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-24 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-24 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421
2025-04-24 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-24 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421
2025-04-25 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-25 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-25 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421
2025-04-25 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-25 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421
2025-04-26 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-26 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-26 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421
2025-04-26 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-26 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421
2025-04-27 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-27 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-27 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421
2025-04-27 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-04-27 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421
2025-04-28 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-28 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421
2025-04-28 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-04-28 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421
2025-04-29 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-29 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421
2025-04-29 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-04-29 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421
2025-04-30 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-30 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421
2025-04-30 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-04-30 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421
2025-05-01 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421
2025-05-01 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-01 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421
2025-05-02 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421
2025-05-02 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421
2025-05-02 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-02 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421
2025-05-03 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421
2025-05-03 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-05-03 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-03 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421
2025-05-04 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421
2025-05-04 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-05-04 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-04 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421
2025-05-05 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421
2025-05-05 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-05-05 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-05 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421
2025-05-06 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421
2025-05-06 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-05-06 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-06 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421
2025-05-07 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421
2025-05-07 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-05-07 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-07 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421
2025-05-08 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-08 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421
2025-05-08 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-05-08 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-08 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421
2025-05-09 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-09 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421
2025-05-09 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-09 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421
2025-05-10 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-10 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421
2025-05-10 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421
2025-05-10 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-10 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421
2025-05-10 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421
2025-05-11 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-11 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-11 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-11 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421
2025-05-11 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-11 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421
2025-05-12 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-12 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-12 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-12 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421
2025-05-12 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-12 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421
2025-05-13 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-13 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-13 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-13 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421
2025-05-13 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-13 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421
2025-05-14 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-14 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-14 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-14 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421
2025-05-14 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-14 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421
2025-05-15 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-15 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-15 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-15 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-15 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-15 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421
2025-05-16 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-16 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-16 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-16 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-16 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-16 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421
2025-05-17 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-17 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-17 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-17 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-17 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421
2025-05-18 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-18 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-18 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-18 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-18 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421
2025-05-19 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-19 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-19 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-19 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-19 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421
2025-05-20 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-20 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-20 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-20 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-20 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421
2025-05-21 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-21 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-21 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-21 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-21 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-22 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-22 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-22 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-22 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-22 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-23 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-23 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-23 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-23 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-24 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-24 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-24 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-24 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-25 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-25 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-25 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-26 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-26 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-26 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-27 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-27 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-27 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-28 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-28 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-28 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-29 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-29 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-29 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421
2025-05-30 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-30 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-30 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421
2025-05-31 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-31 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-31 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421
2025-06-01 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-01 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-06-01 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421
2025-06-02 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-02 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-06-02 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421
2025-06-03 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-03 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-06-03 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-04 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-04 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-06-04 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-05 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-05 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-05 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-05 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-06 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-06 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-06 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-06 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-06 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-07 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-07 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-07 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-07 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-08 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-08 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-08 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-08 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-09 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-09 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-09 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-09 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-10 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-10 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-10 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-10 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-11 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-11 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-11 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-11 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-12 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-12 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-12 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-13 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-13 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-13 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-14 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-14 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-14 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-15 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-15 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-15 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-16 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-16 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-16 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-17 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-17 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-17 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-18 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-18 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-18 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-19 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-19 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-19 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-20 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-20 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-20 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-21 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-21 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-21 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-22 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-22 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-22 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-23 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-23 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-23 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-24 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-24 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-24 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-24 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-24 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-25 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-25 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-25 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-25 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-25 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-25 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421
2025-06-26 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-26 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-26 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-26 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-26 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421
2025-06-27 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-27 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-27 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-27 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-27 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421
2025-06-28 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-28 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-28 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-28 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-28 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421
2025-06-29 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-29 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-29 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-29 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-29 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421
2025-06-30 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-30 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-30 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-30 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-30 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421
2025-07-01 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-07-01 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-07-01 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-07-01 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-01 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421
2025-07-02 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-07-02 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-07-02 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-07-02 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-02 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421
2025-07-03 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-07-03 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-07-03 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-07-03 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-03 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421
2025-07-04 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-07-04 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-07-04 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-04 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-07-04 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-04 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421
2025-07-05 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-05 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-07-05 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-05 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-05 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421
2025-07-06 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-06 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-06 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-06 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-06 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421
2025-07-07 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-07 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-07 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-07 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-07 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421
2025-07-08 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-08 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-08 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-08 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-09 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-09 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-09 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-09 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-10 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-10 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-10 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-10 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-11 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-11 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-11 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421
2025-07-11 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-12 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-12 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-12 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-12 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421
2025-07-12 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-13 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-13 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-13 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-13 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421
2025-07-13 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-13 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421
2025-07-14 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-14 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-14 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-14 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421
2025-07-14 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-14 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-14 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421
2025-07-15 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-15 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-15 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-15 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421
2025-07-15 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421
2025-07-15 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-15 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-15 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421
2025-07-16 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-16 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-16 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-16 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421
2025-07-16 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-16 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-16 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421
2025-07-17 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-17 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-17 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-17 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421
2025-07-17 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-17 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-17 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421
2025-07-18 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-18 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-18 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-18 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421
2025-07-18 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-18 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-18 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421
2025-07-19 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-19 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-19 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-19 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421
2025-07-19 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-19 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-19 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421
2025-07-20 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-20 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-20 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-20 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421
2025-07-20 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-20 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-20 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421
2025-07-21 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-21 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-21 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-21 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421
2025-07-21 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-21 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-21 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421
2025-07-22 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-22 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-22 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-22 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-22 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-22 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-22 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421
2025-07-23 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-23 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-23 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-23 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-23 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-23 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-23 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421
2025-07-24 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-24 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-24 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-24 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-24 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-24 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-24 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421
2025-07-25 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-25 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-25 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-25 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-25 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-25 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-25 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421
2025-07-26 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-26 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-26 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-26 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-26 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-26 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-26 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-07-27 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-27 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-27 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-27 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-27 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-27 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-27 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-07-28 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-28 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-28 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-28 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-28 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-28 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-28 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-07-29 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-29 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-29 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-29 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421
2025-07-29 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-29 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-29 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-07-30 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-07-30 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-30 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-30 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421
2025-07-30 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421
2025-07-30 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-30 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-07-31 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-07-31 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-31 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421
2025-07-31 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421
2025-07-31 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-31 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-08-01 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-08-01 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-08-01 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421
2025-08-01 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421
2025-08-01 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-08-01 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-02 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-08-02 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-08-02 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421
2025-08-02 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421
2025-08-02 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-08-02 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-03 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-08-03 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-08-03 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421
2025-08-03 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421
2025-08-03 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-04 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-08-04 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-04 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421
2025-08-04 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421
2025-08-04 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-05 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-05 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-05 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421
2025-08-05 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421
2025-08-05 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-06 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-06 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-06 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421
2025-08-06 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421
2025-08-06 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-07 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-07 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-07 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421
2025-08-07 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421
2025-08-07 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-08 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-08 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-08 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421
2025-08-08 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-08 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-09 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-09 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-09 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421
2025-08-09 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-09 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-09 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-10 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-10 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-10 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421
2025-08-10 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-10 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-10 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-11 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-11 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-11 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421
2025-08-11 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-11 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-11 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-12 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-12 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-12 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-12 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-12 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-12 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-13 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-13 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-13 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-13 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-13 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-13 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-14 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-14 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-14 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-14 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-14 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-14 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-15 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-15 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-15 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-15 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-15 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-16 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-16 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-16 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-16 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-16 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-16 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-17 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-17 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-17 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-17 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-17 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-17 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-18 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-18 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-18 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-18 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-18 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-18 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-19 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-19 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-19 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-19 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-19 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-19 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-20 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-20 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-20 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-20 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-20 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-20 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-21 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-21 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-21 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-21 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-21 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-21 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-22 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-22 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-22 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-22 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-22 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-22 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-23 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-23 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-23 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-23 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-23 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-23 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-23 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-24 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-24 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-24 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-24 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-24 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-24 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-24 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-25 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-25 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-25 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-25 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-25 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-25 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-25 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-26 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-26 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-26 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-26 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-26 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-26 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-26 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-27 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-27 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-27 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-27 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-27 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-27 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-27 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-28 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-28 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-28 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-28 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-28 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-28 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-28 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-29 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-29 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-29 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-29 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-29 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-29 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-29 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-30 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-30 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-08-30 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-30 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-30 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-30 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-31 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-31 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-08-31 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-08-31 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-31 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421
2025-08-31 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-09-01 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-09-01 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-09-01 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-01 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-01 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421
2025-09-01 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421
2025-09-02 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-09-02 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-09-02 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-02 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-02 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421
2025-09-02 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421
2025-09-03 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-09-03 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-09-03 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-03 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-03 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421
2025-09-03 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421
2025-09-04 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-09-04 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-09-04 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-04 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-04 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421
2025-09-05 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-09-05 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-09-05 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-05 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-05 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421
2025-09-05 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421
2025-09-06 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-09-06 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-06 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-06 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-06 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421
2025-09-06 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421
2025-09-07 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421
2025-09-07 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-07 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-07 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-07 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421
2025-09-07 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421
2025-09-08 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421
2025-09-08 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-08 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-08 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421
2025-09-08 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421
2025-09-09 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421
2025-09-09 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-09 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-09 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-09 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421
2025-09-10 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421
2025-09-10 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-10 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-10 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-10 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421
2025-09-11 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-11 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-11 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-11 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421
2025-09-12 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-12 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-12 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-12 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421
2025-09-13 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-13 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-13 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-13 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-13 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421
2025-09-14 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-14 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-14 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-14 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421
2025-09-14 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-15 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-15 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-15 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-15 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-16 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-16 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-16 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-16 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-17 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-17 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-17 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-18 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-18 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-18 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-19 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-19 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-19 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-20 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-20 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-20 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-21 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-21 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-21 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-21 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421
2025-09-22 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-22 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-22 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-22 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421
2025-09-23 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-23 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-23 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-23 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421
2025-09-24 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-24 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-24 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-24 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421
2025-09-25 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-25 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-25 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-25 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2025-09-26 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-26 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-26 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2025-09-27 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-27 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-27 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2025-09-28 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-28 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-28 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2025-09-29 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-29 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-29 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2025-09-30 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-30 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2024-01-28 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-01-29 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-01-30 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-01-31 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-01 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-01 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-02 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-02 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-03 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-03 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-03 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-04 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-04 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-04 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-05 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-05 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-05 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-06 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-06 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-06 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-07 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-07 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-07 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-08 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-08 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-08 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-09 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-09 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-09 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-09 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-10 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-10 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-10 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-10 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-11 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-11 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-11 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-11 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-12 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-12 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-12 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-12 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-13 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-13 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-13 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-13 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-13 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-14 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-14 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-14 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-14 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-15 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-15 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-15 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-15 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-15 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-15 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-16 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-16 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-16 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-16 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-17 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-17 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-17 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-17 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-17 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-18 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-18 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-18 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-18 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-18 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-18 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-19 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-19 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-19 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-19 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-19 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-20 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-20 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-20 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-20 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-20 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-20 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-20 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-21 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-21 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-21 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-21 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-21 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-21 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-22 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-22 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-22 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-22 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-22 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-22 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-23 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-23 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-23 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-23 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-23 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-24 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-24 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-24 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-24 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-24 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-24 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-24 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-24 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-25 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-25 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-25 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-25 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-25 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-26 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-26 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-26 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-26 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408
2024-02-26 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-26 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-26 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-02-27 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-27 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-27 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408
2024-02-27 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-27 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-02-28 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-28 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-28 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408
2024-02-28 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-28 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-02-29 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-02-29 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-29 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-02-29 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-02-29 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-29 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-29 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-03-01 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-01 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-01 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-01 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-02 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-02 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-02 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-02 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-03 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-03 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-03 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-03 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-04 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-04 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-04 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-04 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-05 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-05 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-05 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-06 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-06 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-06 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-06 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-07 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-07 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-07 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-07 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-08 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-08 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-08 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-09 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-09 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-09 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-10 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-10 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-10 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-11 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-11 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-11 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-11 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-11 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-11 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-12 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-12 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-12 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-13 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-13 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-13 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-14 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-14 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-14 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-15 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-15 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-15 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-15 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-16 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-16 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-16 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-16 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-17 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-17 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-17 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-18 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-18 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-18 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-18 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-19 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-19 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-19 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-20 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-20 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-20 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-20 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-21 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-21 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-21 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-21 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-22 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-22 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-22 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-22 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-22 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-23 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-23 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-23 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-23 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-23 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-24 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-24 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-24 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-24 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-25 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-25 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-25 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-25 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-26 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-26 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-26 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-26 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-26 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-26 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-27 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-27 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-27 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-27 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-28 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-28 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-28 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-28 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-29 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-29 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-29 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-30 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-30 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-30 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-30 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-31 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-31 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-31 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-31 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-03-31 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-04-01 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-01 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-01 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-04-01 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-02 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-02 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-02 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-04-02 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-03 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-03 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-03 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-04-03 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-03 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-04 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-04 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-04 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-04 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-05 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-05 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-05 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-06 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-06 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-06 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-06 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-06 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-07 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-07 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-07 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-07 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-07 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-07 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-08 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-08 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-08 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-08 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-09 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-09 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-09 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-10 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-10 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-10 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-10 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-11 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-11 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-11 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-12 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-12 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-13 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-13 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-13 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-14 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-14 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-15 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-15 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-15 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-16 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-16 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-16 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-16 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-17 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-17 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-17 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-17 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-17 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-18 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-18 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-18 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-18 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-18 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-19 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-19 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-19 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-19 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-19 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-20 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-20 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-20 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-20 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-20 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-21 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-21 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-21 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-21 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-21 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-21 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-22 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-22 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-22 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-22 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-22 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-22 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-22 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-23 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-23 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-23 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-23 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-23 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-24 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-24 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-24 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-24 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-24 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-25 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-25 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-25 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-25 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-25 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-26 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-26 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-26 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-26 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-27 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-27 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-27 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-27 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-27 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-27 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-28 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-28 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-28 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-28 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-29 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-29 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-29 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-04-29 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-29 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-30 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-30 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-04-30 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-30 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-05-01 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-05-01 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-01 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-01 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-05-02 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-05-02 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-02 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-02 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-05-03 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-05-03 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-03 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-03 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-05-03 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-04 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-04 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-04 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-05 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-05 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-05 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-05 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-05 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-06 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-06 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-06 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-07 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-07 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-07 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-08 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-08 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-08 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-09 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-09 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-09 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-10 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-10 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-10 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-11 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-11 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-11 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-11 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-12 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-12 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-12 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-12 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-12 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-13 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-13 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-13 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-13 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-14 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-14 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-14 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-14 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-15 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-15 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-15 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-15 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-16 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-16 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-16 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-16 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-16 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-17 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-17 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-17 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-17 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-18 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-18 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-18 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-18 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-18 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-19 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-19 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-19 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-19 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-19 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-20 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-20 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-20 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-20 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-21 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-21 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-21 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-21 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-22 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-22 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-22 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-22 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-23 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-23 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-23 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-23 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-24 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-24 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-24 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-25 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-25 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-25 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-26 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-26 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-26 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-27 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-27 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-27 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-28 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-28 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-28 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-29 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-05-29 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-29 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-29 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-30 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-05-30 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-30 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-30 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-31 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-05-31 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-06-01 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-01 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-02 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-02 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-03 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-03 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-04 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-04 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-05 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-05 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-06 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-06 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-07 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-07 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-08 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-08 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-09 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-09 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-10 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-10 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-11 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-11 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-12 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-12 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-13 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-13 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-14 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-14 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-15 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-15 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-16 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-16 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-17 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-17 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-18 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-18 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-19 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-19 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-20 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-21 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-22 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-23 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-24 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-25 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-26 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-27 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-07-04 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-05 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-06 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-07 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-08 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-09 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-10 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-11 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-12 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-15 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-16 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-17 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-18 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-19 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-20 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-21 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-22 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-23 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-24 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-25 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-26 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-08-13 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-14 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-15 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-16 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-17 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-18 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-19 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-20 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-20 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-21 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-22 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-23 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-23 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-24 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-24 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-25 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-25 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-26 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-26 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-27 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-27 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-28 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-28 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-28 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-08-28 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-29 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-29 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-29 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-08-29 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-30 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-30 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-30 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-08-30 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-30 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-08-31 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-31 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-31 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-08-31 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-08-31 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-01 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-01 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-01 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-01 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-01 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-02 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-02 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-02 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-02 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-02 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-03 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-03 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-03 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-03 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-03 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-04 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-04 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-04 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-04 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-04 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-05 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-05 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-05 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-05 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-05 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-06 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-06 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-06 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-06 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-06 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-06 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-07 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-07 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-07 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-07 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-07 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-08 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-08 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-08 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-08 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-08 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-08 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-09 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-09 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-09 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-09 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-09 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-10 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-10 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-10 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-10 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-10 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-11 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-11 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-11 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-11 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-11 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-12 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-12 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-12 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-12 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-12 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-13 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-13 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-13 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-13 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-13 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-14 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-14 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-14 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-14 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-15 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-15 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-15 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-15 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-16 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-16 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-16 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-16 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-17 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-17 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-17 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-17 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-18 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-18 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-18 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-18 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-18 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-19 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-19 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-19 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-19 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-19 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-19 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-19 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-20 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-20 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-20 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-20 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-20 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-21 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-21 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-21 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-21 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-21 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-21 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-22 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-22 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-22 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-22 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-22 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-22 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-23 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-23 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-23 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-23 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-23 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-23 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-24 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-24 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-24 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-24 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-24 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-24 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-25 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-25 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-25 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-25 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-25 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-25 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-25 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-26 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-26 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-26 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-26 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-26 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-26 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-27 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-27 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-27 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-27 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-09-27 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-27 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-28 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-28 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-28 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-28 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-09-28 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-09-28 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-09-28 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-28 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-29 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-29 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-29 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-29 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-09-29 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-09-29 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-09-29 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-29 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-30 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-30 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-30 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-09-30 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-09-30 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-09-30 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-30 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-01 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-01 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-10-01 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-01 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-10-01 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-01 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-10-01 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-02 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-02 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-10-02 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-02 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-10-02 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-02 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-02 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-03 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-03 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-10-03 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-03 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-10-03 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-03 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-03 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-04 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-04 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-04 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-04 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-04 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-04 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-05 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-05 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-05 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-05 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-05 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-05 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-05 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-06 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-06 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-06 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-06 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-06 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-06 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-06 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-07 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-07 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-07 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-07 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-07 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-07 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-07 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-07 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-07 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-07 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-08 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-08 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-08 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-08 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-08 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-08 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-08 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-08 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-09 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-09 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-09 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-09 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-09 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-09 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-10 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-10 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-10 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-10 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-10 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-10 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-10 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-11 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-11 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-11 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-11 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-11 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-11 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-12 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-12 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-12 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-12 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-12 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-12 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-12 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-13 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-13 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-13 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-13 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-13 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-13 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-13 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-13 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-14 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-14 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-14 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-14 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-14 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-14 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-14 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-14 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-15 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-15 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-15 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-15 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-15 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-15 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-15 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-15 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-16 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-16 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-16 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-16 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-16 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-16 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-16 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-16 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-17 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-17 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-17 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-17 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-17 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-17 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-17 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-17 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-18 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-18 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-18 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-18 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-18 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-18 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-18 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-18 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-18 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-18 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-19 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-19 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-19 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-19 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-19 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-19 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-19 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-19 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-19 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-19 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-19 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-20 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-20 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-20 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-20 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-20 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-20 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-20 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-20 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-20 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-20 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-21 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-21 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-21 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-21 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-21 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-21 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-21 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-21 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-21 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-21 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-21 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-22 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-22 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-22 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-22 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-22 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-22 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-22 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-22 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-22 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-22 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-22 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-23 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-23 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-23 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-23 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-23 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-23 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-23 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-23 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-23 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-23 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-23 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-24 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-24 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-24 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-24 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-24 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-24 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-24 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-24 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-24 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-24 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-24 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-24 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-25 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-25 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-25 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-25 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-25 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-25 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-25 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-25 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-25 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-25 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-26 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-26 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-26 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-26 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-26 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-26 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-26 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-26 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-26 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-26 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-27 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-27 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-27 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-27 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-27 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-27 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-27 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-27 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-10-28 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-28 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-28 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-28 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-28 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-28 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-10-29 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-29 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-29 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-29 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-29 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-29 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-10-30 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-30 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-30 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-30 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-30 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-10-31 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-31 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-31 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-31 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-11-01 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-11-01 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-01 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-11-01 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-01 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-01 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-11-01 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-02 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-11-02 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-02 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-02 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-11-02 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-02 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-02 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-11-02 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-03 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-03 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-11-03 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-03 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-03 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-03 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-03 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-04 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-04 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-11-04 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-04 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-04 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-04 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-04 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-04 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-04 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-05 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-05 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-11-05 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-05 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-05 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-05 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-05 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-05 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-05 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-06 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-06 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-06 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-06 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-06 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-06 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-06 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-06 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-07 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-07 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-07 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-07 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-07 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-07 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-07 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-07 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-07 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-08 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-08 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-08 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-08 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-08 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-08 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-08 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-08 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-08 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-09 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-09 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-09 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-09 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-09 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-09 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-09 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-09 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-09 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-10 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-10 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-10 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-10 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-10 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-10 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-10 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-11 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-11 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-11 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-11 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-11 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-11 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-11 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-11 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-12 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-12 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-12 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-12 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-12 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-12 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-12 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-12 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-12 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-13 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-13 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-13 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-13 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-13 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-13 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-13 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-13 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-13 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-13 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-14 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-14 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-14 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-14 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-14 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-14 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-14 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-14 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-14 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-15 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-15 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-15 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-15 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-15 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-15 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-15 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-15 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-16 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-16 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-16 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-16 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-16 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-16 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-16 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-16 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-17 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-17 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-17 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-17 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-17 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-17 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-17 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-17 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-17 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-18 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-18 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-18 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-18 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-18 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-18 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-18 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-18 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-18 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-19 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-19 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-19 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-19 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-19 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-19 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-20 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-20 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-20 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-20 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-20 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-20 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-21 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-21 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-21 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-21 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-21 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-22 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-22 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-22 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-22 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-22 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-22 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-23 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-23 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-23 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-23 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-23 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-24 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-24 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-24 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-24 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-24 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-24 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-24 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-25 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-25 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-25 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-25 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-25 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-25 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-25 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-26 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-26 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-26 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-26 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-26 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-26 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-26 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-27 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-27 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-27 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-27 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-27 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-27 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-27 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-27 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-28 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-28 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-28 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-28 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-11-28 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-28 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-28 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-29 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-29 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-29 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-29 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-11-29 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-29 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-29 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-30 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-30 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-30 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-30 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-11-30 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-11-30 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-30 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-30 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-01 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-01 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-01 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-01 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-01 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-12-02 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-02 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-02 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-02 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-02 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-12-02 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-03 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-03 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-03 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-03 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-03 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-12-03 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-03 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-04 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-04 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-04 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-04 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-04 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-04 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-05 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-05 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-05 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-05 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-05 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-05 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-06 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-06 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-06 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-06 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-06 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-12-07 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-07 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-07 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-07 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-12-08 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-08 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-08 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-12-09 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-09 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-09 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-09 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-09 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-12-10 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-10 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-10 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-10 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-11 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-11 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-11 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-11 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-12 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-12 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-12 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-13 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-13 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-13 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-14 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-14 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-15 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-15 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-16 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-16 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-20 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-21 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-22 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-23 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-24 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-25 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-25 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-25 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-26 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-26 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-26 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-27 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-27 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-27 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-28 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-28 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-28 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-29 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-29 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-29 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-30 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-30 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-30 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-31 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-31 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-31 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-01 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2025-01-01 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2025-01-01 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-02 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2025-01-02 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2025-01-02 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-03 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-03 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2025-01-03 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2025-01-03 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-04 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-04 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2025-01-04 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-04 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2025-01-04 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-05 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-05 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-05 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-05 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-06 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-06 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-06 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-06 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-07 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-07 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-07 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-07 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-08 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-08 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-08 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-08 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-09 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-09 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-09 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-09 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-10 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-10 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-10 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-10 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-11 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-11 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-11 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-11 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-11 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-11 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-12 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-12 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-12 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-12 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-12 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-12 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-13 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-13 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-13 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-13 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-13 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-13 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-14 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-14 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-14 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-14 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-14 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-14 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-15 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-15 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-15 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-15 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-15 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-15 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-16 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-16 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-16 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-16 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-16 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-16 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-17 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-17 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-17 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-17 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-17 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-17 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-18 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-18 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-18 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-18 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-18 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-19 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-19 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-19 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-19 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-19 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-20 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-20 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-20 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-21 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-21 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-21 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-21 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-22 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-22 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-22 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-22 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-23 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-23 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-23 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-23 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-24 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-24 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-24 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-24 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-25 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-25 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-25 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-25 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-26 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-26 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-26 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-26 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-27 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-27 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-27 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-27 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-28 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-28 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-28 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-28 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-29 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-29 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-29 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-29 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-29 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-01-30 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-30 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-30 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-01-31 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-01-31 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-31 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-01-31 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-01 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-01 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-02-01 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-01 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-02 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-02 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-02-02 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-02 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-02 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-03 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-03 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-03 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-03 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-04 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-04 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-04 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-04 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-05 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-05 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-05 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-05 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-05 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-06 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-06 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-06 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-06 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-06 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-07 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-07 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-07 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-07 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-08 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-08 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-08 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-08 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-09 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-09 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-09 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-09 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-10 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-10 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-10 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-10 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-11 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-11 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-11 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-11 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-12 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-12 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-12 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-12 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-13 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-13 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-13 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-13 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-14 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-14 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-14 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-14 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-15 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-15 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-15 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-16 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-16 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-16 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-17 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-17 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-17 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-18 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-18 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-18 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-19 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-19 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-19 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-20 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-20 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-20 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-21 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-21 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-22 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-22 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-23 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-23 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-24 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-24 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-25 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-25 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-26 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-26 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-26 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-02-27 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-27 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-27 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-02-28 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-28 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-28 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-01 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-01 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-01 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-02 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-02 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-02 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-03 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-03 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-03 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-04 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-04 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-04 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-05 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-05 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-05 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-06 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-06 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-06 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-07 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-07 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-07 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-08 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-08 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-08 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-09 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-09 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-09 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-09 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-10 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-10 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-10 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-10 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-11 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-11 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-11 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-12 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-12 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-12 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-13 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-13 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-13 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-13 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-14 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-14 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-14 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-14 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-15 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-15 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-15 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-15 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-16 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-16 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-16 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-16 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-17 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-17 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-17 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-18 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-18 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-18 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-19 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-19 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-19 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-20 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-20 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-20 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-20 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-21 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-21 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-21 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-21 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-22 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-22 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-22 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-22 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-23 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-23 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-23 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-23 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-24 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-24 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-24 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-24 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-25 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-25 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-25 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-25 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-26 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-26 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-26 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-26 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-27 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-27 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-27 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-27 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-28 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-28 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-28 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-28 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-29 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-29 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-29 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-29 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-30 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-30 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-30 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-31 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-31 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-31 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-31 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408
2025-03-31 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-01 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-01 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408
2025-04-01 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-02 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-02 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-02 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408
2025-04-02 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-03 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-03 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-03 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-03 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-04 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-04 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-04 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-04 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-05 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-05 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-05 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-06 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-06 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-06 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-06 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-07 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-07 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-07 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-08 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-08 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-08 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-09 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-09 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-09 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-10 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-10 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-11 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-11 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-12 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-12 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-13 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-13 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-14 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-14 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-15 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-16 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-17 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-18 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-19 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-20 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-21 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-22 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-23 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-24 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-25 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-26 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-27 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-04-27 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-28 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-04-28 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-29 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-04-30 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-05-01 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-05-02 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-05-10 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-11 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-12 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-13 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-14 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-15 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-16 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-17 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-18 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-19 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-20 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-20 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
2025-05-21 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-21 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
2025-05-22 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-22 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
2025-05-23 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-23 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
2025-05-24 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-24 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
2025-05-25 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-25 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
2025-05-26 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-26 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
2025-05-27 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-27 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
2025-05-28 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-28 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
2025-05-29 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-29 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
2025-05-30 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-05-31 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-01 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-02 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-03 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-04 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-04 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-05 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-05 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-06 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-06 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-07 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-07 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-08 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-08 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-09 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-09 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-10 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-10 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-11 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-11 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-11 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-11 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TA408
2025-06-12 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-12 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-12 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TA408
2025-06-13 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-13 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-13 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TA408
2025-06-14 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-14 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-14 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TA408
2025-06-15 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-15 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-15 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TA408
2025-06-16 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-16 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-16 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TA408
2025-06-17 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-17 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-17 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TA408
2025-06-17 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-06-18 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-18 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-18 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TA408
2025-06-18 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-06-19 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-19 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-19 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TA408
2025-06-19 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-06-20 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-20 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-20 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TA408
2025-06-20 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-06-21 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-21 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-21 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-06-22 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-22 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-22 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-06-22 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TA408
2025-06-23 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-23 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-23 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TA408
2025-06-24 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-24 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-24 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TA408
2025-06-25 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-25 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-25 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TA408
2025-06-26 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-26 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-26 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TA408
2025-06-27 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-27 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-27 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TA408
2025-06-27 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TA408
2025-06-28 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-28 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-28 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TA408
2025-06-28 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TA408
2025-06-28 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TA408
2025-06-29 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-29 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-29 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TA408
2025-06-29 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TA408
2025-06-29 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TA408
2025-06-30 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-30 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-06-30 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TA408
2025-06-30 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TA408
2025-06-30 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TA408
2025-07-01 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-01 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TA408
2025-07-01 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TA408
2025-07-01 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TA408
2025-07-02 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-02 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TA408
2025-07-02 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TA408
2025-07-03 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-03 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TA408
2025-07-03 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-03 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TA408
2025-07-04 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-04 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-04 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TA408
2025-07-05 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-05 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-05 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TA408
2025-07-06 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-06 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-06 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TA408
2025-07-07 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-07 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-07 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-07 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-07 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TA408
2025-07-08 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-08 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-08 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-08 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-08 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TA408
2025-07-08 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TA408
2025-07-09 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-09 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-09 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-09 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-09 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TA408
2025-07-10 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-10 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-10 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-10 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-10 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-10 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TA408
2025-07-11 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-11 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TA408
2025-07-11 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-11 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-11 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-11 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-11 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TA408
2025-07-12 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-12 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TA408
2025-07-12 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-12 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-12 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-12 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-12 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TA408
2025-07-13 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-13 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TA408
2025-07-13 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-13 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-13 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-13 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-13 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TA408
2025-07-14 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-14 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TA408
2025-07-14 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-14 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-14 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-14 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-14 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TA408
2025-07-14 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TA408
2025-07-15 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-15 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TA408
2025-07-15 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-15 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-15 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-15 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TA408
2025-07-16 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TA408
2025-07-16 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TA408
2025-07-16 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-16 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-16 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-16 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TA408
2025-07-17 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TA408
2025-07-17 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-17 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-17 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-17 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TA408
2025-07-18 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TA408
2025-07-18 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-18 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-18 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-18 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TA408
2025-07-19 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TA408
2025-07-19 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-19 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-19 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-19 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TA408
2025-07-19 | 2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-20 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TA408
2025-07-20 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-20 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-20 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TA408
2025-07-20 | 2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-21 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TA408
2025-07-21 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-21 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-21 | 2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TA408
2025-07-21 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TA408
2025-07-21 | 2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-22 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TA408
2025-07-22 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-22 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-22 | 2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TA408
2025-07-22 | 2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-23 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TA408
2025-07-23 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TA408
2025-07-23 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-23 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-23 | 2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TA408
2025-07-23 | 2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-23 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-07-24 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TA408
2025-07-24 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-24 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-24 | 2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TA408
2025-07-24 | 2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-24 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-07-25 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TA408
2025-07-25 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-07-25 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-25 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-25 | 2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TA408
2025-07-25 | 2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-25 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-07-26 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TA408
2025-07-26 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-07-26 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-26 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-26 | 2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TA408
2025-07-26 | 2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-26 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-07-26 | 2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-26 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TA408
2025-07-27 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TA408
2025-07-27 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-07-27 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-27 | 2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TA408
2025-07-27 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TA408
2025-07-27 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TA408
2025-07-27 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-07-27 | 2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-27 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TA408
2025-07-28 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TA408
2025-07-28 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-07-28 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-28 | 2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TA408
2025-07-28 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TA408
2025-07-28 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TA408
2025-07-28 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-07-28 | 2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-28 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TA408
2025-07-28 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TA408
2025-07-28 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TA408
2025-07-29 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TA408
2025-07-29 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-07-29 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-29 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-07-29 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TA408
2025-07-29 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TA408
2025-07-29 | 2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-29 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TA408
2025-07-29 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TA408
2025-07-29 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TA408
2025-07-29 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TA408
2025-07-30 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TA408
2025-07-30 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-07-30 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-07-30 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-30 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-07-30 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-07-30 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-07-30 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TA408
2025-07-30 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TA408
2025-07-30 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TA408
2025-07-30 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TA408
2025-07-30 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TA408
2025-07-30 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TA408
2025-07-31 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-07-31 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-07-31 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-07-31 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-07-31 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-07-31 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-07-31 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TA408
2025-07-31 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TA408
2025-07-31 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TA408
2025-07-31 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TA408
2025-07-31 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TA408
2025-07-31 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TA408
2025-07-31 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TA408
2025-08-01 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-08-01 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-01 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-01 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-08-01 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-01 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-01 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TA408
2025-08-01 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TA408
2025-08-01 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TA408
2025-08-01 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TA408
2025-08-01 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TA408
2025-08-01 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TA408
2025-08-02 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-08-02 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-02 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-02 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-08-02 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-02 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-02 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TA408
2025-08-02 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TA408
2025-08-02 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TA408
2025-08-02 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TA408
2025-08-02 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TA408
2025-08-02 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TA408
2025-08-03 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-08-03 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-03 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-03 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-08-03 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-03 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-03 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TA408
2025-08-03 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TA408
2025-08-03 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TA408
2025-08-03 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TA408
2025-08-03 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TA408
2025-08-03 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TA408
2025-08-04 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-08-04 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-04 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-04 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-08-04 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-04 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TA408
2025-08-04 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-04 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TA408
2025-08-04 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TA408
2025-08-04 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TA408
2025-08-04 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-08-04 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-04 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TA408
2025-08-04 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-05 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-08-05 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-05 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-05 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-05 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TA408
2025-08-05 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-05 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TA408
2025-08-05 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TA408
2025-08-05 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TA408
2025-08-05 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-08-05 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-05 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TA408
2025-08-05 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-06 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-08-06 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-06 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-06 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-06 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TA408
2025-08-06 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-06 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TA408
2025-08-06 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-06 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TA408
2025-08-06 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TA408
2025-08-06 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-08-06 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-06 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-06 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-07 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-08-07 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-07 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-07 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-07 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TA408
2025-08-07 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-07 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-07 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TA408
2025-08-07 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-08-07 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TA408
2025-08-07 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-07 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-07 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-08 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-08-08 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-08 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-08 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-08 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TA408
2025-08-08 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-08 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-08 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TA408
2025-08-08 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-08-08 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TA408
2025-08-08 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-08 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-08 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-09 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-08-09 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-09 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-09 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-09 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TA408
2025-08-09 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-09 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-09 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TA408
2025-08-09 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TA408
2025-08-09 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-08-09 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TA408
2025-08-09 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TA408
2025-08-09 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-09 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-09 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-10 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-10 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-10 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-10 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-10 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-10 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TA408
2025-08-10 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TA408
2025-08-10 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TA408
2025-08-10 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TA408
2025-08-10 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-10 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-10 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-11 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-11 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-11 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-11 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-11 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-11 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TA408
2025-08-11 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TA408
2025-08-11 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TA408
2025-08-11 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TA408
2025-08-11 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-11 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-11 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-12 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-12 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-12 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-12 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TA408
2025-08-12 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-12 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-12 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TA408
2025-08-12 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TA408
2025-08-12 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TA408
2025-08-12 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TA408
2025-08-12 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-12 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-12 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-13 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-13 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-13 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TA408
2025-08-13 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-13 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-13 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TA408
2025-08-13 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TA408
2025-08-13 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TA408
2025-08-13 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TA408
2025-08-13 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TA408
2025-08-13 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-13 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-13 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-14 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-14 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-14 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TA408
2025-08-14 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-14 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TA408
2025-08-14 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TA408
2025-08-14 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TA408
2025-08-14 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TA408
2025-08-14 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-14 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-14 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-15 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-15 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-15 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TA408
2025-08-15 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-15 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TA408
2025-08-15 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TA408
2025-08-15 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TA408
2025-08-15 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TA408
2025-08-15 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-15 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-15 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-16 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-16 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-16 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TA408
2025-08-16 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TA408
2025-08-16 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-16 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TA408
2025-08-16 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TA408
2025-08-16 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TA408
2025-08-16 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TA408
2025-08-16 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-16 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-16 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-17 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-17 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-17 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-17 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TA408
2025-08-17 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TA408
2025-08-17 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-17 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TA408
2025-08-17 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TA408
2025-08-17 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TA408
2025-08-17 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TA408
2025-08-17 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TA408
2025-08-17 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TA408
2025-08-17 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-17 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-17 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-17 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-18 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-18 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-18 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-18 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TA408
2025-08-18 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TA408
2025-08-18 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TA408
2025-08-18 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TA408
2025-08-18 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TA408
2025-08-18 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TA408
2025-08-18 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-18 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-18 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-18 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-19 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-19 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-19 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TA408
2025-08-19 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-19 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TA408
2025-08-19 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TA408
2025-08-19 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TA408
2025-08-19 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TA408
2025-08-19 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TA408
2025-08-19 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TA408
2025-08-19 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TA408
2025-08-19 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-19 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-08-19 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-19 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-20 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-20 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-20 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TA408
2025-08-20 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-20 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TA408
2025-08-20 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TA408
2025-08-20 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TA408
2025-08-20 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TA408
2025-08-20 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TA408
2025-08-20 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TA408
2025-08-20 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TA408
2025-08-20 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-20 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-20 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-21 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-21 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TA408
2025-08-21 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-21 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TA408
2025-08-21 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TA408
2025-08-21 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TA408
2025-08-21 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TA408
2025-08-21 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TA408
2025-08-21 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TA408
2025-08-21 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TA408
2025-08-21 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TA408
2025-08-21 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TA408
2025-08-21 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-21 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-21 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-22 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-22 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TA408
2025-08-22 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-08-22 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-22 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TA408
2025-08-22 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TA408
2025-08-22 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TA408
2025-08-22 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TA408
2025-08-22 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TA408
2025-08-22 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TA408
2025-08-22 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TA408
2025-08-22 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TA408
2025-08-22 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TA408
2025-08-22 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-22 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-22 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-22 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-08-23 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TA408
2025-08-23 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TA408
2025-08-23 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-08-23 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-23 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TA408
2025-08-23 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TA408
2025-08-23 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TA408
2025-08-23 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-08-23 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TA408
2025-08-23 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TA408
2025-08-23 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TA408
2025-08-23 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TA408
2025-08-23 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TA408
2025-08-23 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TA408
2025-08-23 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-23 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-23 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-08-24 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TA408
2025-08-24 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TA408
2025-08-24 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-08-24 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-24 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TA408
2025-08-24 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TA408
2025-08-24 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-08-24 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TA408
2025-08-24 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TA408
2025-08-24 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TA408
2025-08-24 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TA408
2025-08-24 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TA408
2025-08-24 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TA408
2025-08-24 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-24 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-24 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-08-25 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TA408
2025-08-25 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TA408
2025-08-25 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TA408
2025-08-25 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-08-25 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-25 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TA408
2025-08-25 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TA408
2025-08-25 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-08-25 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TA408
2025-08-25 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TA408
2025-08-25 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TA408
2025-08-25 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-25 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-25 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-08-26 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TA408
2025-08-26 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TA408
2025-08-26 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-08-26 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-26 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-08-26 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TA408
2025-08-26 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TA408
2025-08-26 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-08-26 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TA408
2025-08-26 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-26 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-26 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-08-27 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TA408
2025-08-27 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TA408
2025-08-27 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-08-27 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-27 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-08-27 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TA408
2025-08-27 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-08-27 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TA408
2025-08-27 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-27 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-27 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-08-28 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TA408
2025-08-28 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TA408
2025-08-28 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-08-28 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-28 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-08-28 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TA408
2025-08-28 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-08-28 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TA408
2025-08-28 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-28 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-28 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-08-29 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TA408
2025-08-29 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TA408
2025-08-29 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-08-29 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-29 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TA408
2025-08-29 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-08-29 | 2025-08-29 | 2025-08-31 | Pusplata Ashok | 37.5044 | 12.5015 | TA408
2025-08-29 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-08-29 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TA408
2025-08-29 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-08-29 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-08-29 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TA408
2025-08-29 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-29 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-29 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-08-30 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TA408
2025-08-30 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TA408
2025-08-30 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-08-30 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TA408
2025-08-30 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-30 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TA408
2025-08-30 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-08-30 | 2025-08-29 | 2025-08-31 | Pusplata Ashok | 37.5044 | 12.5015 | TA408
2025-08-30 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-08-30 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TA408
2025-08-30 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-08-30 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-08-30 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-08-30 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-30 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-08-31 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TA408
2025-08-31 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TA408
2025-08-31 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TA408
2025-08-31 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TA408
2025-08-31 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-08-31 | 2025-08-29 | 2025-08-31 | Pusplata Ashok | 37.5044 | 12.5015 | TA408
2025-08-31 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-08-31 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TA408
2025-08-31 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-08-31 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-08-31 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-08-31 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-31 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-09-01 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2025-09-01 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TA408
2025-09-01 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TA408
2025-09-01 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TA408
2025-09-01 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-01 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-09-01 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TA408
2025-09-01 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-09-01 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-01 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-01 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TA408
2025-09-01 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-09-02 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2025-09-02 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TA408
2025-09-02 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TA408
2025-09-02 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TA408
2025-09-02 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-02 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TA408
2025-09-02 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-09-02 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TA408
2025-09-02 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-09-02 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-02 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-02 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TA408
2025-09-02 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-09-03 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2025-09-03 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TA408
2025-09-03 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TA408
2025-09-03 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TA408
2025-09-03 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TA408
2025-09-03 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-03 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TA408
2025-09-03 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-09-03 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TA408
2025-09-03 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-09-03 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-03 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TA408
2025-09-03 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-03 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TA408
2025-09-03 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-09-04 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2025-09-04 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TA408
2025-09-04 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TA408
2025-09-04 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TA408
2025-09-04 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TA408
2025-09-04 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-04 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TA408
2025-09-04 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TA408
2025-09-04 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-09-04 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-04 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TA408
2025-09-04 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-04 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TA408
2025-09-04 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-09-05 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2025-09-05 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TA408
2025-09-05 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TA408
2025-09-05 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TA408
2025-09-05 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-05 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TA408
2025-09-05 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TA408
2025-09-05 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-09-05 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-05 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TA408
2025-09-05 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-05 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TA408
2025-09-05 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TA408
2025-09-05 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-09-06 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2025-09-06 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TA408
2025-09-06 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TA408
2025-09-06 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TA408
2025-09-06 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-06 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TA408
2025-09-06 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TA408
2025-09-06 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-09-06 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-06 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TA408
2025-09-06 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-06 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TA408
2025-09-06 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TA408
2025-09-06 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-09-07 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2025-09-07 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TA408
2025-09-07 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TA408
2025-09-07 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TA408
2025-09-07 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-07 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TA408
2025-09-07 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TA408
2025-09-07 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TA408
2025-09-07 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-07 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TA408
2025-09-07 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-07 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TA408
2025-09-07 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TA408
2025-09-08 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TA408
2025-09-08 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TA408
2025-09-08 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TA408
2025-09-08 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-08 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TA408
2025-09-08 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TA408
2025-09-08 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-08 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TA408
2025-09-08 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-08 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TA408
2025-09-08 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TA408
2025-09-09 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-09 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TA408
2025-09-09 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TA408
2025-09-09 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TA408
2025-09-09 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-09 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-09 | 2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TA408
2025-09-09 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TA408
2025-09-09 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TA408
2025-09-09 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-09 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TA408
2025-09-09 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-09 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TA408
2025-09-09 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TA408
2025-09-10 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-10 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TA408
2025-09-10 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TA408
2025-09-10 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TA408
2025-09-10 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TA408
2025-09-10 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-10 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-10 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-10 | 2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TA408
2025-09-10 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TA408
2025-09-10 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TA408
2025-09-10 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-10 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TA408
2025-09-10 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-10 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TA408
2025-09-10 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TA408
2025-09-11 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-11 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TA408
2025-09-11 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TA408
2025-09-11 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TA408
2025-09-11 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-11 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-11 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-11 | 2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TA408
2025-09-11 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TA408
2025-09-11 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-11 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TA408
2025-09-11 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-11 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TA408
2025-09-11 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TA408
2025-09-12 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-12 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-12 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TA408
2025-09-12 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TA408
2025-09-12 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TA408
2025-09-12 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-12 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-12 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-12 | 2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TA408
2025-09-12 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TA408
2025-09-12 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-12 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-12 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TA408
2025-09-12 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TA408
2025-09-13 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-13 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-13 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TA408
2025-09-13 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TA408
2025-09-13 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-13 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-13 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-13 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TA408
2025-09-13 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-13 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-13 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TA408
2025-09-14 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-14 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-14 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TA408
2025-09-14 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TA408
2025-09-14 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-14 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-14 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-14 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TA408
2025-09-14 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-14 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-14 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TA408
2025-09-15 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-15 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-15 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TA408
2025-09-15 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TA408
2025-09-15 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-15 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-15 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-15 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TA408
2025-09-15 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-15 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-15 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TA408
2025-09-16 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-16 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-16 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TA408
2025-09-16 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-16 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TA408
2025-09-16 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-16 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-16 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-16 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-16 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TA408
2025-09-16 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-16 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-16 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TA408
2025-09-17 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-17 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-17 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-17 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TA408
2025-09-17 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-17 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-17 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-17 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-17 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-17 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TA408
2025-09-18 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-18 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-18 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-18 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TA408
2025-09-18 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-18 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-18 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-18 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-18 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-18 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TA408
2025-09-19 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-19 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-19 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-19 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TA408
2025-09-19 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-19 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-19 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-19 | 2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TA408
2025-09-19 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-19 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-19 | 2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TA408
2025-09-20 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-20 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-20 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-20 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TA408
2025-09-20 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-20 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-20 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-20 | 2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TA408
2025-09-20 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-20 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-20 | 2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TA408
2025-09-21 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-21 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-21 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-21 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-21 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-21 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-21 | 2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TA408
2025-09-21 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-21 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-21 | 2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TA408
2025-09-22 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-22 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-22 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-22 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-22 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-22 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-22 | 2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TA408
2025-09-22 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-22 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-22 | 2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TA408
2025-09-23 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-23 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-23 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-23 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-23 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-23 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-23 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-24 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-24 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-24 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-24 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-24 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-25 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-09-25 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-25 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-25 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-25 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-26 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-26 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-26 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-26 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-27 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-27 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-27 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-28 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
2025-09-29 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408

## RawData
Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name
2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418
2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418
2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418
2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418
2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418
2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418
2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418
2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418
2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418
2024-12-29 | 2024-01-05 | Gang 01 Sanjay | 27.96 |  | TA418
2024-12-30 | 2024-01-07 | Gang 02 Sanjay | 27.96 |  | TA418
2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418
2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418
2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418
2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418
2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418
2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418
2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418
2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418
2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418
2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418
2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418
2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418
2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418
2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418
2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418
2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418
2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418
2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418
2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418
2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418
2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418
2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418
2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418
2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418
2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418
2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418
2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418
2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418
2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418
2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418
2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418
2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418
2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418
2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418
2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418
2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418
2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418
2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418
2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418
2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418
2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418
2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418
2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418
2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418
2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418
2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418
2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418
2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418
2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418
2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418
2025-08-26 |  | Savitha | 28 |  | TA418
2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418
2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418
2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418
2025-09-05 |  | Savitha | 45 |  | TA418
2025-09-08 |  | Subhash | 33 |  | TA418
2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418
2025-09-09 |  | M S Mdpl | 33.3 |  | TA418
2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418
2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418
2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418
2025-09-22 |  | M S Tofit | 27 |  | TA418
2025-09-25 |  | Subhash | 50 |  | TA418
2025-09-28 |  | Kec 02 Barkat Ali | 27 |  | TA418
2025-09-29 |  | M S Mdpl | 60 |  | TA418
2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-29 | 2024-01-05 | Gang 01 Sanjay | 27.96 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-12-30 | 2024-01-07 | Gang 02 Sanjay | 27.96 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-26 |  | Savitha | 28 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-05 |  | Savitha | 45 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-08 |  | Subhash | 33 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-09 |  | M S Mdpl | 33.3 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-22 |  | M S Tofit | 27 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-25 |  | Subhash | 50 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-28 |  | Kec 02 Barkat Ali | 27 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2025-09-29 |  | M S Mdpl | 60 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1)
2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416
2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416
2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-10-20 | 2025-01-25 | Asc Heights | 46.0492 |  | TA416
2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-02 |  | Rudra Construction | 46.0492 |  | TA416
2025-02-06 |  | Dewi Construction | 64.482 |  | TA416
2025-02-07 |  | Reeta Bharti | 43.7758 |  | TA416
2025-02-08 |  | Amar Singh | 46.0492 |  | TA416
2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416
2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416
2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416
|  | Reeta Bharti |  |  | TA416
|  | Dewi Construction |  |  | TA416
|  | Pankaj |  |  | TA416
|  | Pinky Dewi |  |  | TA416
2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416
2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416
2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416
2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416
2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416
2025-03-24 | 2025-03-31 | Ananya Traders | 46.0492 | 5.7561 | TA416
2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-03-31 | 2025-04-11 | Anand Const | 46.0492 | 3.8374 | TA416
2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-08 | 2025-04-12 | Pinky Dewi 1 | 42.3742 | 8.4748 | TA416
2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-02-12 18:37 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416
2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416
2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416
2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416
2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-13 | 2025-05-15 | Ananya Traders 2 | 42.3742 | 14.1247 | TA416
2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416
2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416
2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416
2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416
2025-06-02 | 2025-06-12 | Devine | 42.374 | 3.8522 | TA416
2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416
2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416
1935-06-27 | 2025-06-29 | Pinki Dewi | 42.374 | 0.0012889 | TA416
2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-14 | 2025-08-26 | Kajal Const | 46.049 | 3.5422 | TA416
2025-07-26 | 2025-08-27 | Kangresh 1 | 161.355 | 4.8895 | TA416
2025-08-09 | 2025-08-30 | Radha Const | 78.073 | 3.5488 | TA416
2025-08-04 | 2025-08-30 | Sainik Ent | 75.85 | 2.8093 | TA416
2025-08-02 | 2025-08-30 | Kangresh 2 | 97.229 | 3.3527 | TA416
2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-10 | 2025-09-07 | Ananya | 118.43 | 4.0838 | TA416
2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-09-08 |  | Ananya | 90.125 |  | TA416
2025-08-18 |  | Mk Infra | 42.374 |  | TA416
2025-08-18 |  | Spotify Pvt Ltd 2 | 53.324 |  | TA416
2025-08-18 |  | Spotify Pvt Ltd 3 | 42.374 |  | TA416
2025-08-31 |  | Sainik Ent | 87.01 |  | TA416
2025-08-31 |  | Kangresh 2 | 73.426 |  | TA416
2025-08-31 |  | Radha Const | 89.7 |  | TA416
2025-08-24 | 2025-09-14 | Gouri Shankar | 97.65 | 4.4386 | TA416
2025-09-04 |  | Gagan |  |  | TA416
2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-28 |  | Kangresh 1 | 161.355 |  | TA416
2025-08-06 |  | Reeta Bharti | 161.355 |  | TA416
2025-09-08 |  | Punam Kumari |  |  | TA416
2025-09-11 |  | Maa Const |  |  | TA416
|  | Nan |  |  | TB401
|  | Nan |  |  | TB401
2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401
2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401
2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401
|  | Nan |  |  | TB401
2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401
2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401
2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401
2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-10-07 | 2023-10-11 | Sunny Const | 37.504 | 7.5008 | TB401
2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401
2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401
2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401
2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401
2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401
2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401
2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401
2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401
2023-10-26 | 2023-10-30 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401
2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401
|  | Nan |  |  | TB401
2023-10-30 | 2023-11-03 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401
2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401
2023-11-03 | 2023-11-07 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401
2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401
2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401
2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-10 | 2023-11-14 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-13 | 2023-11-16 | Sobha Devi | 38.847 | 9.7118 | TB401
2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401
2023-11-15 | 2023-11-19 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401
2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401
2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401
2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-22 | 2023-11-24 | Sobha Devi | 38.847 | 12.949 | TB401
2023-11-22 | 2023-11-26 | Chinta Devi | 37.504 | 7.5008 | TB401
2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401
2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401
2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401
|  | Nan |  |  | TB401
2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401
2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-11-29 | 2023-12-02 | Sobha Devi | 38.847 | 9.7118 | TB401
2023-11-29 | 2023-12-03 | Suraj Const | 38.847 | 7.7694 | TB401
2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401
2023-12-02 | 2023-12-06 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401
2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401
2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401
2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401
2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401
2023-12-16 | 2023-12-19 | Suraj Const | 37.504 | 9.376 | TB401
2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401
2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401
2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401
2023-12-20 | 2023-12-24 | Sobha Devi | 37.504 | 7.5008 | TB401
2023-12-20 | 2023-12-24 | Suraj Const | 37.504 | 7.5008 | TB401
2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401
2023-12-24 | 2023-12-28 | Sobha Devi | 38.847 | 7.7694 | TB401
2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401
2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401
|  | Nan |  |  | TB401
2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401
2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401
2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401
2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401
2024-01-05 | 2024-01-09 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401
2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401
2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401
2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401
2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401
2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401
2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401
2024-01-16 | 2024-01-20 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401
2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401
2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401
2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401
2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401
2024-01-28 | 2024-01-31 | Sobha Devi | 37.504 | 9.376 | TB401
|  | Nan |  |  | TB401
2024-01-28 | 2024-02-01 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401
2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401
2024-02-01 | 2024-02-05 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401
2024-02-07 | 2024-02-09 | Sobha Devi | 37.504 | 12.5013 | TB401
2024-02-09 | 2024-02-13 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-13 | 2024-02-17 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401
2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401
2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401
|  | Nan |  |  | TB401
2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401
2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401
2024-04-12 | 2024-04-16 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401
|  | Nan |  |  | TB401
2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401
2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401
2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401
2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401
|  | Nan |  |  | TB401
2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401
2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401
|  | Nan |  |  | TB401
2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401
2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401
2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401
|  | Nan |  |  | TB401
2024-08-27 | 2024-08-30 | Sobha Devi | 37.504 | 9.376 | TB401
2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401
2024-07-12 | 2024-08-04 | Sanjay Mahto | 47.148 | 1.9645 | TB401
2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401
2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401
|  | Nan |  |  | TB401
2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401
2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401
2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401
2024-09-09 | 2024-09-12 | Sobha Devi | 37.504 | 9.376 | TB401
2024-09-11 | 2024-09-15 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401
2024-09-12 | 2024-09-16 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-09-16 | 2024-09-20 | Sobha Devi | 37.504 | 7.5008 | TB401
2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401
2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401
2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401
2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401
2024-09-22 | 2024-09-26 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-09-25 | 2024-09-29 | Sunny Const | 37.504 | 7.5008 | TB401
2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401
2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401
2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401
2024-09-07 | 2024-09-11 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-09-12 | 2024-09-16 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-12 | 2024-09-16 | Deglal Mahto | 38.847 | 7.7694 | TB401
2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401
2024-09-16 | 2024-09-20 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401
2024-09-19 | 2024-09-21 | Nirmal Mahto | 47.148 | 15.716 | TB401
2024-09-21 | 2024-09-25 | Jagdish Mahto | 38.847 | 7.7694 | TB401
2024-09-10 | 2024-09-26 | Khublal Mahto | 38.847 | 2.2851 | TB401
2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401
|  | Nan |  |  | TB401
2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401
2024-09-29 | 2024-10-03 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-02 | 2024-10-05 | Chinta Devi | 38.847 | 9.7118 | TB401
2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401
2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401
2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401
2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401
2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401
2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401
2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401
2024-10-23 | 2024-10-27 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-24 | 2024-10-28 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401
2024-10-27 | 2024-10-31 | Sunny Const | 37.504 | 7.5008 | TB401
2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401
2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401
2024-09-30 | 2024-10-04 | Jagdish Mahto | 45.413 | 9.0826 | TB401
2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401
2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401
2024-10-08 | 2024-10-11 | Jagdish Mahto | 38.847 | 9.7118 | TB401
2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401
2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401
2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401
2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401
2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401
2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401
2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401
2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401
|  | Nan |  |  | TB401
2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401
2024-11-01 | 2024-11-05 | Chinta Devi | 38.847 | 7.7694 | TB401
2024-11-01 | 2024-11-05 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-05 | 2024-11-09 | Chinta Devi | 38.847 | 7.7694 | TB401
2024-11-05 | 2024-11-09 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401
2024-11-09 | 2024-11-13 | Sunny Const | 37.504 | 7.5008 | TB401
2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401
2024-11-13 | 2024-11-17 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-18 | 2024-11-22 | Sunny Const | 37.504 | 7.5008 | TB401
2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401
2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401
2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401
2024-10-31 | 2024-11-03 | Deglal Mahto | 47.148 | 11.787 | TB401
2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401
2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401
2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401
2024-11-06 | 2024-11-10 | Jagdish Mahto | 60.096 | 12.0192 | TB401
2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401
2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401
2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401
2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401
2024-11-18 | 2024-11-21 | Jagdish Mahto | 38.847 | 9.7118 | TB401
2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401
2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401
2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401
2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401
|  | Nan |  |  | TB401
2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401
2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401
2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401
2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401
2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401
2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401
2024-12-14 | 2024-12-18 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401
2024-12-15 | 2024-12-19 | Sobha Devi | 45.413 | 9.0826 | TB401
2024-12-18 | 2024-12-22 | Sunny Const | 37.504 | 7.5008 | TB401
2024-12-18 | 2024-12-22 | Chinta Devi | 37.504 | 7.5008 | TB401
2024-12-20 | 2024-12-24 | Sobha Devi | 38.847 | 7.7694 | TB401
2024-12-25 | 2024-12-28 | Sobha Devi | 37.504 | 9.376 | TB401
2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401
2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401
2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401
2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401
2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401
2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401
2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401
2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401
2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401
2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401
|  | Nan |  |  | TB401
2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401
2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401
2025-01-06 | 2025-01-10 | Sanjeev Kumar | 37.504 | 7.5008 | TB401
2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401
2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401
2025-01-16 | 2025-01-20 | Sobha Devi | 45.413 | 9.0826 | TB401
2025-01-20 | 2025-01-24 | Sobha Devi | 38.847 | 7.7694 | TB401
2025-01-19 | 2025-01-28 | Om Construction | 45.413 | 4.5413 | TB401
2025-01-25 | 2025-01-28 | Sobha Devi | 37.504 | 9.376 | TB401
2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401
2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401
2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401
|  | Nan |  |  | TB401
2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401
2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401
2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401
2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401
2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401
2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401
2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401
2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401
|  | Nan |  |  | TB401
2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401
2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401
2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401
2025-03-08 | 2025-03-11 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-08 | 2025-03-12 | Sunny Const | 37.504 | 7.5008 | TB401
2025-03-13 | 2025-03-17 | Sobha Devi | 37.504 | 7.5008 | TB401
2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401
2025-03-18 | 2025-03-21 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-22 | 2025-03-25 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401
2025-03-26 | 2025-03-29 | Sobha Devi | 37.504 | 9.376 | TB401
2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401
2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401
|  | Nan |  |  | TB401
2025-04-06 | 2025-04-10 | Sobha Devi | 38.847 | 7.7694 | TB401
2025-04-11 | 2025-04-14 | Sobha Devi | 37.504 | 9.376 | TB401
2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401
2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401
2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401
2025-04-21 | 2025-04-25 | Sunny Const | 37.504 | 7.5008 | TB401
2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401
2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401
2025-04-26 | 2025-04-30 | Sunny Const | 38.847 | 7.7694 | TB401
2025-04-26 | 2025-04-30 | Sobha Devi | 37.504 | 7.5008 | TB401
|  | Nan |  |  | TB401
2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401
2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401
2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401
2025-05-07 | 2025-05-11 | Satyam Nitish | 37.504 | 7.5008 | TB401
2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401
2025-04-28 | 2025-05-15 | Annaya Traders | 37.504 | 2.0836 | TB401
2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401
2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401
2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401
2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401
2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401
2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401
2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401
|  | Nan |  |  | TB401
2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401
2025-05-30 | 2025-06-04 | Pankaj | 37.504 | 6.2507 | TB401
2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401
2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401
2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401
2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401
2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401
2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401
2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401
2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401
2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401
2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401
2025-06-16 | 2025-06-18 | Satyam Manish | 37.504 | 12.5013 | TB401
2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401
2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401
2025-05-30 | 2025-06-19 | Kewat Departmental | 37.504 | 1.7859 | TB401
2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401
2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401
2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401
2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401
2025-06-24 | 2025-06-27 | Jwala Singh 3 | 38.847 | 9.7118 | TB401
2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401
2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401
2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401
2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401
2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401
2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401
2025-06-10 | 2025-06-30 | Permanand | 38.847 | 1.8499 | TB401
2025-06-27 | 2025-06-30 | Pusplata 1 | 45.413 | 11.3532 | TB401
2025-06-26 | 2025-06-30 | Pusplata 4 | 38.847 | 7.7694 | TB401
|  | Nan |  |  | TB401
2025-06-29 | 2025-07-02 | Poonam | 37.504 | 9.376 | TB401
2025-06-30 | 2025-07-03 | Jwala Singh 2 | 37.504 | 9.376 | TB401
2025-06-26 |  | Arawali Infra 1 | 37.504 |  | TB401
2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401
2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401
2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401
2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401
2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401
2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401
2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401
2025-07-02 | 2025-07-06 | Pusplata 4 | 38.847 | 7.7694 | TB401
2025-07-02 | 2025-07-06 | Jwala Singh 3 | 38.847 | 7.7694 | TB401
2025-06-09 | 2025-07-07 | Anil Kumar Departmental Kewat | 38.847 | 1.3396 | TB401
2025-07-04 | 2025-07-07 | Poonam | 37.504 | 9.376 | TB401
2025-06-21 | 2025-07-08 | Satyam Manish 2 Santosh | 38.847 | 2.1582 | TB401
2025-07-04 | 2025-07-08 | Satyam Nitish | 45.413 | 9.0826 | TB401
2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401
2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401
2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401
2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401
2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401
2025-07-05 | 2025-07-10 | Arawali Infra 1 | 37.504 | 6.2507 | TB401
2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401
2025-07-08 | 2025-07-11 | Poonam | 37.504 | 9.376 | TB401
2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401
2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401
2025-07-10 | 2025-07-13 | Satyam Manish | 37.504 | 9.376 | TB401
2025-07-09 | 2025-07-13 | Satyam Trivedi | 37.504 | 7.5008 | TB401
2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401
2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401
2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401
2025-06-18 | 2025-07-14 | Anil Kumar Ramayan Departmental | 86.129 | 3.19 | TB401
2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401
2025-07-11 | 2025-07-15 | Jwala Singh 3 | 38.847 | 7.7694 | TB401
2025-07-12 | 2025-07-16 | Poonam | 57.597 | 11.5194 | TB401
2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401
2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401
2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-15 | 2025-07-18 | Satyam Manish | 37.504 | 9.376 | TB401
2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401
2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401
2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401
2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401
2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401
2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401
2025-07-17 | 2025-07-21 | Poonam | 37.504 | 7.5008 | TB401
2025-07-14 | 2025-07-22 | Satyam Trivedi Nitish | 38.847 | 4.3163 | TB401
2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401
2025-07-19 | 2025-07-22 | Pusplata 4 | 37.504 | 9.376 | TB401
2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401
2025-07-10 | 2025-07-23 | Vinay Const 2 | 38.847 | 2.7748 | TB401
2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401
2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401
2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401
2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401
2025-06-29 | 2025-07-24 | Anjani Enterprises | 45.413 | 1.7467 | TB401
2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401
2025-07-22 | 2025-07-26 | Pusplata 2 | 38.847 | 7.7694 | TB401
2025-07-24 | 2025-07-26 | Pusplata 4 | 37.504 | 12.5013 | TB401
2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401
2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401
2025-07-23 | 2025-07-27 | Pusplata 7 | 38.847 | 7.7694 | TB401
2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401
2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401
2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401
2025-07-27 | 2025-07-30 | Pusplata 3 | 38.847 | 9.7118 | TB401
2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-10 | 2025-07-30 | Pusplata 3 Jwala | 47.148 | 2.2451 | TB401
2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401
2025-07-24 | 2025-07-30 | Priyanka Devi Sudheer 2 | 38.847 | 5.5496 | TB401
2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401
2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401
2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401
2025-07-27 | 2025-07-31 | Pusplata 2 | 45.413 | 9.0826 | TB401
2025-07-27 | 2025-07-31 | Pusplata 4 | 37.504 | 7.5008 | TB401
2025-07-27 | 2025-07-31 | Pusplata 6 | 38.847 | 7.7694 | TB401
2025-08-30 | 2025-07-31 | Priyanka Devi Sudheer | 38.847 |  | TB401
2025-06-25 | 2025-07-31 | Anil Kumar Departmental Ramayan | 86.129 | 2.3278 | TB401
2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401
2025-07-30 | 2025-07-31 | Satyam Vijay | 37.504 | 18.752 | TB401
2025-07-28 | 2025-07-31 | Poonam | 37.504 | 9.376 | TB401
|  | Nan |  |  | TB401
2025-07-31 | 2025-08-04 | Pusplata 3 | 37.504 | 7.5008 | TB401
2025-08-01 | 2025-08-04 | Poonam | 37.504 | 9.376 | TB401
2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401
2025-08-01 | 2025-08-05 | Pusplata 4 | 37.504 | 7.5008 | TB401
2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401
2025-08-04 | 2025-08-07 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401
2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401
2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401
2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401
2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401
2025-08-05 | 2025-08-10 | Pusplata Santosh | 47.184 | 7.864 | TB401
2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401
2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401
2025-07-17 | 2025-08-12 | Bhairo Mahto Departmental Arawali | 100.96 | 3.7393 | TB401
2025-08-09 | 2025-08-12 | Satyam Manish | 37.504 | 9.376 | TB401
| 2025-08-13 | Satyam Santosh | 37.504 |  | TB401
2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401
2025-08-01 | 2025-08-14 | Pusplata Dharamveer | 47.184 | 3.3703 | TB401
2025-08-27 | 2025-08-16 | Bhairo Mahto Departmental Bharo | 37.504 |  | TB401
2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401
2025-08-16 | 2025-08-19 | Pusplata Deepak | 38.847 | 9.7118 | TB401
2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401
2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401
2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401
2025-08-13 | 2025-08-22 | Arawali | 45.413 | 4.5413 | TB401
2025-08-19 | 2025-08-22 | Satyam Manish | 37.504 | 9.376 | TB401
2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401
2025-08-21 | 2025-08-24 | Pusplata Deepak | 37.504 | 9.376 | TB401
2025-08-10 | 2025-08-25 | Pusplata Rajaram | 89.909 | 5.6193 | TB401
2025-08-10 | 2025-08-25 | Pusplata Praful | 89.909 | 5.6193 | TB401
2025-08-21 | 2025-08-25 | Priyanka Devi 2 | 37.504 | 7.5008 | TB401
2025-08-14 | 2025-08-26 | Pusplata Ramchander | 81.494 | 6.2688 | TB401
2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401
2025-08-23 | 2025-08-27 | Satyam Manish |  |  | TB401
2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401
2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401
2025-08-21 | 2025-08-28 | Jawala Singh | 37.504 | 4.688 | TB401
2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401
2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401
2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401
2025-08-25 | 2025-08-31 | Jawala Singh Suraj | 37.504 | 5.3577 | TB401
2025-08-27 | 2025-08-31 | Satyam Vijay | 38.847 | 7.7694 | TB401
2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401
|  | Nan |  |  | TB401
2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401
2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401
2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401
2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401
2025-09-05 | 2025-09-09 | Rahul Kumar | 37.504 | 7.5008 | TB401
2025-09-02 | 2025-09-10 | Bhairo Mahto | 38.847 | 4.3163 | TB401
2025-09-05 | 2025-09-10 | Pusplata Pankaj | 37.504 | 6.2507 | TB401
2025-09-06 | 2025-09-11 | Jwala Singh | 38.847 | 6.4745 | TB401
2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401
2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401
2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401
2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401
2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401
2025-09-16 |  | Sanjeev Kumar | 47.184 |  | TB401
2025-07-30 |  | Anjani Power | 38.847 |  | TB401
2025-08-11 |  | Jwala Singh 3 Bhairo Mahto | 129.11 |  | TB401
2025-09-26 |  | Sanjeev Kumar | 81.945 |  | TB401
2025-09-08 |  | Priyanka Devi Santosh | 38.847 |  | TB401
2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401
|  | Sital Singh 1 |  |  | TB401
2025-09-23 |  | Priyanka Devi Subodh | 38.847 |  | TB401
|  | Bhairo Mahto | 57.597 |  | TB401
|  | Ganesh Sinha |  |  | TB401
| 2025-09-19 | Dhaneshwar Mahto | 171.017 |  | TA325
| 2025-11-09 | Dhaneshwar Mahto | 156.901 |  | TA325
| 2025-08-13 | Dhaneshwar Mahto | 172.151 |  | TA325
2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325
2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325
2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325
2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-13 | 2024-03-13 | Lalan Mahto | 37.73 | 37.73 | TA325
2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325
2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325
2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325
2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325
2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325
2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2025-02-03 | 2025-02-07 | Dhaneshwar Mahto | 39.459 | 7.8918 | TA325
2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-27 | 2025-01-29 | Dhaneshwar Mahto | 44.728 | 14.9093 | TA325
2025-01-30 | 2025-02-02 | Dhaneshwar Mahto | 37.73 | 9.4325 | TA325
2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325
2024-11-29 | 2024-12-03 | Dhaneshwar Mahto | 36.045 | 7.209 | TA325
2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325
2025-01-20 | 2025-01-24 | Dhaneshwar Mahto | 46.623 | 9.3246 | TA325
2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325
2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325
2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325
2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325
2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325
2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325
2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325
2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325
2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325
2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325
2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325
| 2025-08-08 | Nan | 141.874 |  | TA325
2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
| 2025-07-20 | Nan | 37.73 |  | TA325
2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325
2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325
2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325
| 2025-08-26 | Modina India | 122.808 |  | TA325
2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325
2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325
2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
| 2025-10-05 | Modina India 3 Pgcil | 37.73 |  | TA325
| 2025-10-05 | Muni Bibi 2 | 37.73 |  | TA325
| 2025-10-15 | Rupesh | 89.146 |  | TA325
| 2025-10-08 | Dildar Electrical 2 Pgcil | 39.459 |  | TA325
2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325
2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325
2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2035-03-04 | 2025-03-11 | Thanu Mahto | 36.045 |  | TA325
2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325
2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325
2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325
2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325
2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325
2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325
|  | Nan | 20932.97 |  | TA325
|  | Nan |  |  | TA325
|  | Nan |  |  | TA325
|  | Nan | 40 |  | TA325
|  | Nan | 146 |  | TA325
|  | Nan | 40 |  | TA325
|  | Nan | 30 |  | TA325
|  | Nan | 11 |  | TA325
|  | Nan | 267 |  | TA325
|  | Nan | 25 |  | TA325
|  | Nan | 6 |  | TA325
|  | Nan | 8 |  | TA325
|  | Nan | 9 |  | TA325
|  | Nan | 6 |  | TA325
|  | Nan | 1 |  | TA325
|  | Nan | 55 |  | TA325
|  | Nan | 26 |  | TA325
|  | Nan | 3 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 7 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 3 |  | TA325
|  | Nan | 47 |  | TA325
|  | Nan | 16 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 3 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 6 |  | TA325
|  | Nan | 5 |  | TA325
|  | Nan | 2 |  | TA325
|  | Nan | 40 |  | TA325
|  | Nan | 19 |  | TA325
|  | Nan | 8 |  | TA325
|  | Nan | 11 |  | TA325
|  | Nan | 7 |  | TA325
|  | Nan | 7 |  | TA325
|  | Nan | 15 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 2 |  | TA325
|  | Nan | 73 |  | TA325
|  | Nan | 1 |  | TA325
|  | Nan | 1 |  | TA325
|  | Nan | 483 |  | TA325
|  | Nan |  |  | TA408
|  | Nan |  |  | TA408
|  | Nan |  |  | TA408
2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408
2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TA408
2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408
2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
|  | Nan |  |  | TA408
2025-05-10 |  | Bhairo Mahto |  |  | TA408
2025-05-19 |  | Sonakshi Manish 2 |  |  | TA408
2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421
2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421
2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421
2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421
2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421
2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421
2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421
2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421
2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421
2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421
2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421
2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421
2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421
2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421
2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421
2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421
2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421
2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421
2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421
2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421
2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421
2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421
2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421
2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421
2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421
2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421
2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421
2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421
2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421
2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421
2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421
2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421
2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421
2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421
2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421
2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421
2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421
2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421
2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421
2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421
2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421
2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421
2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421
2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421
2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421
2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421
2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421
2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421
2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421
2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421
2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421
2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421
2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421
2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421
2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421
2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421
2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421
2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421
2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421
2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421
2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421
2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421
2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421
2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421
2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421
2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421
2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421
2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421
2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
| 2025-07-12 | Subash | 33.38 |  | TA421
2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
| 2025-07-13 | Naziruddin | 71.706 |  | TA421
2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421
2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421
2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421
2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421
2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421
2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421
2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421
2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421
2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421
2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421
2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421
2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421
2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421
2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421
2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421
2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421
2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421
2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421
2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421
2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421
2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2025-09-13 |  | Praveen | 36.37 |  | TA421
2025-09-21 |  | Yadhav | 37.931 |  | TA421
2025-09-27 |  | Hassan | 36.37 |  | TA421
2025-09-28 |  | Khatun | 31.99 |  | TA421
2025-10-01 |  | Subash |  |  | TA421
2025-10-01 |  | D K Verma |  |  | TA421
|  | Nan |  |  | TA408
|  | Nan |  |  | TA408
|  | Nan |  |  | TA408
2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408
2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TA408
2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408
2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TA408
2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TA408
2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TA408
2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TA408
2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TA408
2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TA408
2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TA408
2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TA408
2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TA408
2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TA408
2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TA408
2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TA408
2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TA408
2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TA408
2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TA408
2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TA408
2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TA408
2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TA408
2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TA408
2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TA408
2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TA408
2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TA408
2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TA408
2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TA408
2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TA408
2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TA408
2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TA408
2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TA408
2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TA408
2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TA408
2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TA408
2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TA408
2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TA408
2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TA408
2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TA408
2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TA408
2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TA408
2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TA408
2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TA408
2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TA408
2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TA408
2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TA408
2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TA408
2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TA408
2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TA408
2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TA408
2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TA408
2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TA408
2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TA408
2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TA408
2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TA408
2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TA408
2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TA408
2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TA408
2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TA408
2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TA408
2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TA408
2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TA408
2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TA408
2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TA408
2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TA408
2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TA408
2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TA408
2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TA408
2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TA408
2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TA408
2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TA408
2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TA408
2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TA408
2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TA408
2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TA408
2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TA408
2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TA408
2025-08-29 | 2025-08-31 | Pusplata Ashok | 37.5044 | 12.5015 | TA408
2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TA408
2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TA408
2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TA408
2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TA408
2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TA408
2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TA408
2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TA408
2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TA408
2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TA408
2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TA408
2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TA408
2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TA408
2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TA408
2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TA408
2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TA408
2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TA408
2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TA408
2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TA408
2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TA408
2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TA408
2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TA408
2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TA408
2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TA408
2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TA408
2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TA408
2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TA408
2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TA408
2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TA408
2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TA408
2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TA408
2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TA408
2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TA408
2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TA408
2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TA408
2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TA408
2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TA408
2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TA408
2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TA408
2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TA408
2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TA408
2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TA408
2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TA408
2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TA408
2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TA408
|  | Nan |  |  | TA408
|  | Gang Name |  |  | TA408
2025-09-29 |  | Shobha Devi |  |  | TA408
2025-09-20 |  | Jirwa Devi |  |  | TA408
2025-09-22 |  | Sunny Construction |  |  | TA408
2025-09-29 |  | Vinay Construction Chinta Devi |  |  | TA408
2025-09-27 |  | Nirmal Mahto |  |  | TA408
2025-09-22 |  | Vivek Ganju |  |  | TA408
2025-09-10 |  | Shri Shyam Construction |  |  | TA408
2025-09-25 |  | Sheetal Singh 1 |  |  | TA408
|  | Priyanka Devi Sudheer |  |  | TA408
2025-09-29 |  | Priyanka Devi Sontosh |  |  | TA408

## Data Issues
Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Issues
2025-08-26 |  | Savitha | 28 |  | TA418 | Missing start/end date (not expanded)
2025-09-05 |  | Savitha | 45 |  | TA418 | Missing start/end date (not expanded)
2025-09-08 |  | Subhash | 33 |  | TA418 | Missing start/end date (not expanded)
2025-09-09 |  | M S Mdpl | 33.3 |  | TA418 | Missing start/end date (not expanded)
2025-09-22 |  | M S Tofit | 27 |  | TA418 | Missing start/end date (not expanded)
2025-09-25 |  | Subhash | 50 |  | TA418 | Missing start/end date (not expanded)
2025-09-28 |  | Kec 02 Barkat Ali | 27 |  | TA418 | Missing start/end date (not expanded)
2025-09-29 |  | M S Mdpl | 60 |  | TA418 | Missing start/end date (not expanded)
2024-12-29 | 2024-01-05 | Gang 01 Sanjay | 27.96 |  | TA418 | Non-positive duration (Start > End or 0) (not expanded)
2024-12-30 | 2024-01-07 | Gang 02 Sanjay | 27.96 |  | TA418 | Non-positive duration (Start > End or 0) (not expanded)
2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | Single-occurrence gang (not expanded)
2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | Single-occurrence gang (not expanded)
2025-08-26 |  | Savitha | 28 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Missing start/end date (not expanded)
2025-09-05 |  | Savitha | 45 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Missing start/end date (not expanded)
2025-09-08 |  | Subhash | 33 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Missing start/end date (not expanded)
2025-09-09 |  | M S Mdpl | 33.3 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Missing start/end date (not expanded)
2025-09-22 |  | M S Tofit | 27 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Missing start/end date (not expanded)
2025-09-25 |  | Subhash | 50 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Missing start/end date (not expanded)
2025-09-28 |  | Kec 02 Barkat Ali | 27 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Missing start/end date (not expanded)
2025-09-29 |  | M S Mdpl | 60 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Missing start/end date (not expanded)
2024-12-29 | 2024-01-05 | Gang 01 Sanjay | 27.96 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Non-positive duration (Start > End or 0) (not expanded)
2024-12-30 | 2024-01-07 | Gang 02 Sanjay | 27.96 |  | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Non-positive duration (Start > End or 0) (not expanded)
2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Single-occurrence gang (not expanded)
2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Single-occurrence gang (not expanded)
2025-02-02 |  | Rudra Construction | 46.0492 |  | TA416 | Missing start/end date (not expanded)
2025-02-06 |  | Dewi Construction | 64.482 |  | TA416 | Missing start/end date (not expanded)
2025-02-07 |  | Reeta Bharti | 43.7758 |  | TA416 | Missing start/end date (not expanded)
2025-02-08 |  | Amar Singh | 46.0492 |  | TA416 | Missing start/end date (not expanded)
|  | Reeta Bharti |  |  | TA416 | Missing start/end date (not expanded)
|  | Dewi Construction |  |  | TA416 | Missing start/end date (not expanded)
|  | Pankaj |  |  | TA416 | Missing start/end date (not expanded)
|  | Pinky Dewi |  |  | TA416 | Missing start/end date (not expanded)
2025-09-08 |  | Ananya | 90.125 |  | TA416 | Missing start/end date (not expanded)
2025-08-18 |  | Mk Infra | 42.374 |  | TA416 | Missing start/end date (not expanded)
2025-08-18 |  | Spotify Pvt Ltd 2 | 53.324 |  | TA416 | Missing start/end date (not expanded)
2025-08-18 |  | Spotify Pvt Ltd 3 | 42.374 |  | TA416 | Missing start/end date (not expanded)
2025-08-31 |  | Sainik Ent | 87.01 |  | TA416 | Missing start/end date (not expanded)
2025-08-31 |  | Kangresh 2 | 73.426 |  | TA416 | Missing start/end date (not expanded)
2025-08-31 |  | Radha Const | 89.7 |  | TA416 | Missing start/end date (not expanded)
2025-09-04 |  | Gagan |  |  | TA416 | Missing start/end date (not expanded)
2025-08-28 |  | Kangresh 1 | 161.355 |  | TA416 | Missing start/end date (not expanded)
2025-08-06 |  | Reeta Bharti | 161.355 |  | TA416 | Missing start/end date (not expanded)
2025-09-08 |  | Punam Kumari |  |  | TA416 | Missing start/end date (not expanded)
2025-09-11 |  | Maa Const |  |  | TA416 | Missing start/end date (not expanded)
2025-10-20 | 2025-01-25 | Asc Heights | 46.0492 |  | TA416 | Non-positive duration (Start > End or 0) (not expanded)
1935-06-27 | 2025-06-29 | Pinki Dewi | 42.374 | 0.0012889 | TA416 | Start before 2021-01-01 (not expanded)
2025-03-24 | 2025-03-31 | Ananya Traders | 46.0492 | 5.7561 | TA416 | Single-occurrence gang (not expanded)
2025-03-31 | 2025-04-11 | Anand Const | 46.0492 | 3.8374 | TA416 | Single-occurrence gang (not expanded)
2025-04-08 | 2025-04-12 | Pinky Dewi 1 | 42.3742 | 8.4748 | TA416 | Single-occurrence gang (not expanded)
2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | Single-occurrence gang (not expanded)
2025-06-02 | 2025-06-12 | Devine | 42.374 | 3.8522 | TA416 | Single-occurrence gang (not expanded)
2025-08-14 | 2025-08-26 | Kajal Const | 46.049 | 3.5422 | TA416 | Single-occurrence gang (not expanded)
2025-07-26 | 2025-08-27 | Kangresh 1 | 161.355 | 4.8895 | TA416 | Single-occurrence gang (not expanded)
2025-08-09 | 2025-08-30 | Radha Const | 78.073 | 3.5488 | TA416 | Single-occurrence gang (not expanded)
2025-08-04 | 2025-08-30 | Sainik Ent | 75.85 | 2.8093 | TA416 | Single-occurrence gang (not expanded)
2025-08-02 | 2025-08-30 | Kangresh 2 | 97.229 | 3.3527 | TA416 | Single-occurrence gang (not expanded)
2025-08-10 | 2025-09-07 | Ananya | 118.43 | 4.0838 | TA416 | Single-occurrence gang (not expanded)
2025-08-24 | 2025-09-14 | Gouri Shankar | 97.65 | 4.4386 | TA416 | Single-occurrence gang (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
2025-06-26 |  | Arawali Infra 1 | 37.504 |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
| 2025-08-13 | Satyam Santosh | 37.504 |  | TB401 | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 | Missing start/end date (not expanded)
2025-09-16 |  | Sanjeev Kumar | 47.184 |  | TB401 | Missing start/end date (not expanded)
2025-07-30 |  | Anjani Power | 38.847 |  | TB401 | Missing start/end date (not expanded)
2025-08-11 |  | Jwala Singh 3 Bhairo Mahto | 129.11 |  | TB401 | Missing start/end date (not expanded)
2025-09-26 |  | Sanjeev Kumar | 81.945 |  | TB401 | Missing start/end date (not expanded)
2025-09-08 |  | Priyanka Devi Santosh | 38.847 |  | TB401 | Missing start/end date (not expanded)
|  | Sital Singh 1 |  |  | TB401 | Missing start/end date (not expanded)
2025-09-23 |  | Priyanka Devi Subodh | 38.847 |  | TB401 | Missing start/end date (not expanded)
|  | Bhairo Mahto | 57.597 |  | TB401 | Missing start/end date (not expanded)
|  | Ganesh Sinha |  |  | TB401 | Missing start/end date (not expanded)
2025-08-30 | 2025-07-31 | Priyanka Devi Sudheer | 38.847 |  | TB401 | Non-positive duration (Start > End or 0) (not expanded)
2025-08-27 | 2025-08-16 | Bhairo Mahto Departmental Bharo | 37.504 |  | TB401 | Non-positive duration (Start > End or 0) (not expanded)
2024-07-12 | 2024-08-04 | Sanjay Mahto | 47.148 | 1.9645 | TB401 | Single-occurrence gang (not expanded)
2024-09-10 | 2024-09-26 | Khublal Mahto | 38.847 | 2.2851 | TB401 | Single-occurrence gang (not expanded)
2025-01-19 | 2025-01-28 | Om Construction | 45.413 | 4.5413 | TB401 | Single-occurrence gang (not expanded)
2025-04-28 | 2025-05-15 | Annaya Traders | 37.504 | 2.0836 | TB401 | Single-occurrence gang (not expanded)
2025-05-30 | 2025-06-04 | Pankaj | 37.504 | 6.2507 | TB401 | Single-occurrence gang (not expanded)
2025-05-30 | 2025-06-19 | Kewat Departmental | 37.504 | 1.7859 | TB401 | Single-occurrence gang (not expanded)
2025-06-10 | 2025-06-30 | Permanand | 38.847 | 1.8499 | TB401 | Single-occurrence gang (not expanded)
2025-06-09 | 2025-07-07 | Anil Kumar Departmental Kewat | 38.847 | 1.3396 | TB401 | Single-occurrence gang (not expanded)
2025-06-21 | 2025-07-08 | Satyam Manish 2 Santosh | 38.847 | 2.1582 | TB401 | Single-occurrence gang (not expanded)
2025-07-05 | 2025-07-10 | Arawali Infra 1 | 37.504 | 6.2507 | TB401 | Single-occurrence gang (not expanded)
2025-06-18 | 2025-07-14 | Anil Kumar Ramayan Departmental | 86.129 | 3.19 | TB401 | Single-occurrence gang (not expanded)
2025-07-14 | 2025-07-22 | Satyam Trivedi Nitish | 38.847 | 4.3163 | TB401 | Single-occurrence gang (not expanded)
2025-07-10 | 2025-07-23 | Vinay Const 2 | 38.847 | 2.7748 | TB401 | Single-occurrence gang (not expanded)
2025-06-29 | 2025-07-24 | Anjani Enterprises | 45.413 | 1.7467 | TB401 | Single-occurrence gang (not expanded)
2025-07-10 | 2025-07-30 | Pusplata 3 Jwala | 47.148 | 2.2451 | TB401 | Single-occurrence gang (not expanded)
2025-07-24 | 2025-07-30 | Priyanka Devi Sudheer 2 | 38.847 | 5.5496 | TB401 | Single-occurrence gang (not expanded)
2025-06-25 | 2025-07-31 | Anil Kumar Departmental Ramayan | 86.129 | 2.3278 | TB401 | Single-occurrence gang (not expanded)
2025-08-05 | 2025-08-10 | Pusplata Santosh | 47.184 | 7.864 | TB401 | Single-occurrence gang (not expanded)
2025-07-17 | 2025-08-12 | Bhairo Mahto Departmental Arawali | 100.96 | 3.7393 | TB401 | Single-occurrence gang (not expanded)
2025-08-01 | 2025-08-14 | Pusplata Dharamveer | 47.184 | 3.3703 | TB401 | Single-occurrence gang (not expanded)
2025-08-13 | 2025-08-22 | Arawali | 45.413 | 4.5413 | TB401 | Single-occurrence gang (not expanded)
2025-08-10 | 2025-08-25 | Pusplata Rajaram | 89.909 | 5.6193 | TB401 | Single-occurrence gang (not expanded)
2025-08-10 | 2025-08-25 | Pusplata Praful | 89.909 | 5.6193 | TB401 | Single-occurrence gang (not expanded)
2025-08-14 | 2025-08-26 | Pusplata Ramchander | 81.494 | 6.2688 | TB401 | Single-occurrence gang (not expanded)
2025-08-21 | 2025-08-28 | Jawala Singh | 37.504 | 4.688 | TB401 | Single-occurrence gang (not expanded)
2025-08-25 | 2025-08-31 | Jawala Singh Suraj | 37.504 | 5.3577 | TB401 | Single-occurrence gang (not expanded)
2025-09-02 | 2025-09-10 | Bhairo Mahto | 38.847 | 4.3163 | TB401 | Single-occurrence gang (not expanded)
2025-09-05 | 2025-09-10 | Pusplata Pankaj | 37.504 | 6.2507 | TB401 | Single-occurrence gang (not expanded)
2025-09-06 | 2025-09-11 | Jwala Singh | 38.847 | 6.4745 | TB401 | Single-occurrence gang (not expanded)
| 2025-09-19 | Dhaneshwar Mahto | 171.017 |  | TA325 | Missing start/end date (not expanded)
| 2025-11-09 | Dhaneshwar Mahto | 156.901 |  | TA325 | Missing start/end date (not expanded)
| 2025-08-13 | Dhaneshwar Mahto | 172.151 |  | TA325 | Missing start/end date (not expanded)
| 2025-08-08 | Nan | 141.874 |  | TA325 | Missing start/end date (not expanded)
| 2025-07-20 | Nan | 37.73 |  | TA325 | Missing start/end date (not expanded)
| 2025-08-26 | Modina India | 122.808 |  | TA325 | Missing start/end date (not expanded)
| 2025-10-05 | Modina India 3 Pgcil | 37.73 |  | TA325 | Missing start/end date (not expanded)
| 2025-10-05 | Muni Bibi 2 | 37.73 |  | TA325 | Missing start/end date (not expanded)
| 2025-10-15 | Rupesh | 89.146 |  | TA325 | Missing start/end date (not expanded)
| 2025-10-08 | Dildar Electrical 2 Pgcil | 39.459 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 20932.97 |  | TA325 | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 40 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 146 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 40 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 30 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 11 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 267 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 25 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 6 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 8 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 9 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 6 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 1 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 55 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 26 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 3 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 7 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 3 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 47 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 16 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 3 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 6 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 5 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 2 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 40 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 19 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 8 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 11 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 7 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 7 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 15 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 2 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 73 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 1 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 1 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 483 |  | TA325 | Missing start/end date (not expanded)
2035-03-04 | 2025-03-11 | Thanu Mahto | 36.045 |  | TA325 | Non-positive duration (Start > End or 0) (not expanded)
|  | Nan | 20932.97 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 267 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 6 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 8 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 9 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 6 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 1 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 3 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 7 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 3 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 3 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 6 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 5 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 2 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 8 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 7 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 7 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 2 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 1 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 1 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 483 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325 | Single-occurrence gang (not expanded)
2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | Single-occurrence gang (not expanded)
2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | Single-occurrence gang (not expanded)
|  | Nan |  |  | TA408 | Missing start/end date (not expanded)
|  | Nan |  |  | TA408 | Missing start/end date (not expanded)
|  | Nan |  |  | TA408 | Missing start/end date (not expanded)
|  | Nan |  |  | TA408 | Missing start/end date (not expanded)
2025-05-10 |  | Bhairo Mahto |  |  | TA408 | Missing start/end date (not expanded)
2025-05-19 |  | Sonakshi Manish 2 |  |  | TA408 | Missing start/end date (not expanded)
2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TA408 | Single-occurrence gang (not expanded)
2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408 | Single-occurrence gang (not expanded)
| 2025-07-12 | Subash | 33.38 |  | TA421 | Missing start/end date (not expanded)
| 2025-07-13 | Naziruddin | 71.706 |  | TA421 | Missing start/end date (not expanded)
2025-09-13 |  | Praveen | 36.37 |  | TA421 | Missing start/end date (not expanded)
2025-09-21 |  | Yadhav | 37.931 |  | TA421 | Missing start/end date (not expanded)
2025-09-27 |  | Hassan | 36.37 |  | TA421 | Missing start/end date (not expanded)
2025-09-28 |  | Khatun | 31.99 |  | TA421 | Missing start/end date (not expanded)
2025-10-01 |  | Subash |  |  | TA421 | Missing start/end date (not expanded)
2025-10-01 |  | D K Verma |  |  | TA421 | Missing start/end date (not expanded)
2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | Single-occurrence gang (not expanded)
2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | Single-occurrence gang (not expanded)
2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | Single-occurrence gang (not expanded)
2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | Single-occurrence gang (not expanded)
|  | Nan |  |  | TA408 | Missing start/end date (not expanded)
|  | Nan |  |  | TA408 | Missing start/end date (not expanded)
|  | Nan |  |  | TA408 | Missing start/end date (not expanded)
|  | Nan |  |  | TA408 | Missing start/end date (not expanded)
|  | Gang Name |  |  | TA408 | Missing start/end date (not expanded)
2025-09-29 |  | Shobha Devi |  |  | TA408 | Missing start/end date (not expanded)
2025-09-20 |  | Jirwa Devi |  |  | TA408 | Missing start/end date (not expanded)
2025-09-22 |  | Sunny Construction |  |  | TA408 | Missing start/end date (not expanded)
2025-09-29 |  | Vinay Construction Chinta Devi |  |  | TA408 | Missing start/end date (not expanded)
2025-09-27 |  | Nirmal Mahto |  |  | TA408 | Missing start/end date (not expanded)
2025-09-22 |  | Vivek Ganju |  |  | TA408 | Missing start/end date (not expanded)
2025-09-10 |  | Shri Shyam Construction |  |  | TA408 | Missing start/end date (not expanded)
2025-09-25 |  | Sheetal Singh 1 |  |  | TA408 | Missing start/end date (not expanded)
|  | Priyanka Devi Sudheer |  |  | TA408 | Missing start/end date (not expanded)
2025-09-29 |  | Priyanka Devi Sontosh |  |  | TA408 | Missing start/end date (not expanded)
2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TA408 | Single-occurrence gang (not expanded)
2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TA408 | Single-occurrence gang (not expanded)
2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TA408 | Single-occurrence gang (not expanded)
2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TA408 | Single-occurrence gang (not expanded)
2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TA408 | Single-occurrence gang (not expanded)
2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TA408 | Single-occurrence gang (not expanded)
2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TA408 | Single-occurrence gang (not expanded)
2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TA408 | Single-occurrence gang (not expanded)
2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TA408 | Single-occurrence gang (not expanded)
2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TA408 | Single-occurrence gang (not expanded)
2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TA408 | Single-occurrence gang (not expanded)
2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TA408 | Single-occurrence gang (not expanded)
2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TA408 | Single-occurrence gang (not expanded)
2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TA408 | Single-occurrence gang (not expanded)
2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TA408 | Single-occurrence gang (not expanded)
2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TA408 | Single-occurrence gang (not expanded)
2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TA408 | Single-occurrence gang (not expanded)
2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TA408 | Single-occurrence gang (not expanded)
2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TA408 | Single-occurrence gang (not expanded)
2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TA408 | Single-occurrence gang (not expanded)
2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TA408 | Single-occurrence gang (not expanded)
2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TA408 | Single-occurrence gang (not expanded)
2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TA408 | Single-occurrence gang (not expanded)
2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TA408 | Single-occurrence gang (not expanded)
2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TA408 | Single-occurrence gang (not expanded)
2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TA408 | Single-occurrence gang (not expanded)
2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TA408 | Single-occurrence gang (not expanded)

## Issues
file | issue
TA413-PBNTL-20.08.2025.xlsx | Excel open error: Unable to read workbook: could not assign names from C:\Users\HIMANI\git\Office-work-\Office-work-\Test\TA413-PBNTL-20.08.2025.xlsx. This is most probably because the workbook source files contain some invalid XML. Please see the exception for more details.

## Diagnostics
file | project | sheet | detected_header_row | columns_detected
DPR TA-418 __ Dt.-29-09-25 (PGCIL) (1).xlsx | TA418 | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, nan, nan, nan, completion date, gang name, gang strength, remark, nan, nan, 1.0, 2.0, 3.0, 4.0
DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1).xlsx | DPR - TA.418 __Dt.-29-09-25 (PGCIL) (1) | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, nan, nan, nan, completion date, gang name, gang strength, remark, nan, nan, 1.0, 2.0, 3.0, 4.0
DPR TA-416,14-09-25.xlsx | TA416 | Erection Compiled | 0 | sl no, location no, tower type, tower weight, starting date, completion date, work status, gang name, gang strength, gang type(subcontractor/company), nan, tac welding, remark
DPR TB401 Sterlite 765KV F3BTL 29.09.25.xlsx | TB401 | Erection Compiled | 3 | cum sl. no, month sl. no, location no, tower type, starting date, completion date, gang name, ramarks, tower weight, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan
Latest TA-325-DPR-ANTL-30-09-2025.xlsx | TA325 | Erection Compiled | 0 | sl. no, location no, type, type of tower, starting date, revenue, tower weight, todays status, completion date, gang name
TA 408.xlsx | TA408 | Erection Compiled | 3 | sl.no, month sl.no, location no, type of tower, starting date, completion date, gang name, staff's engaged, tower weight, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan
TA 421 Latest BMTL-30-09-2025.xlsx | TA421 | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, nan, nan, nan, completion date, gang name, gang strength, remark, tackwelding, tower tightening
TA408 PKG F Progress.xlsx | TA408 | Erection Compiled | 3 | sl.no, month sl.no, location no, type of tower, starting date, completion date, gang name, staff's engaged, tower weight, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan
TA413-PBNTL-20.08.2025.xlsx | TA413

## README_Assumptions
Notes
Assumptions & Cleaning Rules:
- Start date cutoff: rows with Start Date before 2021-01-01 are not expanded and logged in 'Data Issues'.
- Tower Weight range: only [10, 200] MT is considered valid for expansion; out-of-range rows go to 'Data Issues'.
- Missing or non-positive durations (Start/End missing or Start > End or 0) are logged to 'Data Issues' and not expanded.
- Gangs that performed erection only once (per Project+Gang) are not expanded and are logged in 'Data Issues'.
- Gang name normalization: remove special characters (digits kept), Title Case words, and insert a space before trailing digits (e.g., 'xyz4' → 'Xyz 4').
- Sheets:
• DailyExpanded : per-day expanded rows used by the dashboard
• RawData : per-erection rows (unexpanded), for traceability
• Data Issues : row-level data problems (reason in 'Issues' column)
• Issues : file-level problems (missing sheet/headers, read/open errors, etc.)
• Diagnostics : which sheet used, detected header row, and normalized header text
- Dashboard note: a 15-day productivity loss cap is used in downstream analytics.