## StatusActivityFact
project_code | project_display | project_scope_key | line_name | report_date | month | section_label | activity_raw | activity_norm | activity_group | core_activity | quantity_primary | cumulative_last_month | plan_for_month | progress_for_month | today_progress | cumulative_progress | balance_progress | gangs_working | remarks | source_file | source_sheet | configured_sheet | template_sheet | stringing_resolution_policy
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | Progress Status | Soil Investigation | soil_investigation | Other | FALSE | 31 | 16 | 0 |  |  | 17 | 14 |  |  | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 480 | 154 | 30 | 8 | 0 | 162 | 318 | 3.0 |  | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 480 | 96 | 30 | 10 | 1 | 106 | 374 |  |  | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 480 | 52 | 35 | 17 | 2 | 69 | 411 | 4.0 |  | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | Progress Status | Tack welding | tack_welding | Other | FALSE | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0 |  | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | Progress Status | Stringing(Km) | stringing | Stringing | TRUE | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0 |  | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Route Alignment (Km) | route_alignment | Other | FALSE | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661 |  |  | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Detailed Survey (Km) | detailed_survey | Other | FALSE | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001 |  |  | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Check Survey (Km) | check_survey | Other | FALSE | 122.071 | 122.07 |  |  |  | 1 | 121.071 |  |  | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 31 | 31 | 0 |  |  | 31 |  |  |  | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Excavation (Nos) | excavation | Other | FALSE | 330 | 167 |  |  |  | 167 | 163 |  |  | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Foundation (Nos) | foundation | Foundation | TRUE | 330 | 255 | 49 | 9 |  | 264 | 66 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Earthing (Nos) | earthing | Other | FALSE | 330 | 217 | 50 | 0 |  | 217 | 113 |  |  | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 330 | 207 | 50 | 5 |  | 212 | 118 | 12 | 36/4, 37/0, 38/3, 41/2, 42/0 ,52/1, 54/0, 62/0, 65/0, 65/1 64/4, 71/0, 76/0 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Tack Welding (Nos) | tack_welding | Other | FALSE | 330 | 35 | 50 |  |  | 35 | 295 | 1 |  | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Stringing (Km) | stringing | Stringing | TRUE | 122.071 |  |  | 0.447 |  |  | 122.071 |  |  | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Paying Out (Km) | paying_out | Other | FALSE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 |  |  | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Final Sag (Km) | stringing | Stringing | TRUE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | ` |  | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | OPGW Stringing (Km) | opgw_stringing | OPGW Stringing | TRUE | 122.071 | 0 |  |  |  | 0 | 122.071 |  |  | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-12 | 2026-06-01 | Completed Days | Power Line Crossings | power_line_crossings | Other | FALSE | [9 empty] | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 512 | TA 512 | ta512 |  | 2026-06-12 | 2026-06-01 | Office : Hansera, Lunkaransar | Route Alignment (Km) | route_alignment | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-12 | 2026-06-01 | Office : Hansera, Lunkaransar | Detailed Survey (Km) | detailed_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-12 | 2026-06-01 | Office : Hansera, Lunkaransar | Check Survey (Km) | check_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-12 | 2026-06-01 | Office : Hansera, Lunkaransar | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 | 0 | 0 | 0 | 28 | 0 |  |  | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-12 | 2026-06-01 | Office : Hansera, Lunkaransar | Excavation | excavation | Other | FALSE | 319 | 308 | 18 | 4 | 0 | 312 | 7 |  |  | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-12 | 2026-06-01 | Office : Hansera, Lunkaransar | Foundation (Nos.) | foundation | Foundation | TRUE | 319 | 306 | 18 | 4 | 1 | 310 | 9 | 02/20 |  | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-12 | 2026-06-01 | Office : Hansera, Lunkaransar | Earthing (Nos.) | earthing | Other | FALSE | 319 | 269 |  |  |  | 269 | 50 |  |  | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-12 | 2026-06-01 | Office : Hansera, Lunkaransar | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 319 | 221 | 30 | 3 | 1 | 224 | 95 | 06/206 |  | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-12 | 2026-06-01 | Office : Hansera, Lunkaransar | Tack Welding | tack_welding | Other | FALSE | 319 | 79 |  | 14 | 1 | 93 | 226 |  |  | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-12 | 2026-06-01 | Office : Hansera, Lunkaransar | Paying Out | paying_out | Other | FALSE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-12 | 2026-06-01 | Office : Hansera, Lunkaransar | Final Sag | stringing | Stringing | TRUE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-12 | 2026-06-01 | Office : Hansera, Lunkaransar | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 124.568 | 0 | 20 | 0 |  | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026) | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 399 | 64 | 25 | 4 |  | 68 | 331 | 3 | Loc-51/1-Casting WIP Loc-62/0-3Pit Casting compl(ROW) Loc-61/0-Casting WIP Loc-74/7-Casting WIP Loc-54/2-Pit Collapse. | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 399 | 7 |  |  |  | 7 | 392 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 399 | 24 | 11 | 2 |  | 26 | 373 | 2 | Loc-56/3-Material Shifting U/P | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 399 | 0 |  |  |  | 0 | 399 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 147.584 | 0 |  |  |  |  | 147.584 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 82.803 | 82.803 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.796 |  |  |  | 82.796 | 0.007 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025) | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 220 | 25 | 10 | 1 |  | 26 | 194 | 1 |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 220 | 10 |  |  | 0 | 10 | 210 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 220 | 7 | 5 |  |  | 7 | 213 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 220 |  |  |  |  | 0 | 220 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 82.803 | [5 empty] | 82.803 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-13 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status
TB 605 | TB 605 | tb605 |  | 2026-06-12 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Check Survey | check_survey | Other | FALSE | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3 |  | TB 605 - DPR - 2026-06-12.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-12 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Foundation | foundation | Foundation | TRUE | 523 | 370 | 0 | 20 | 2 | 390 | 133 | 25 |  | TB 605 - DPR - 2026-06-12.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-12 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Earthing | earthing | Other | FALSE | 523 | 308 | 0 | 0 | 0 | 308 | 215 | 0 |  | TB 605 - DPR - 2026-06-12.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-12 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tower Erection | tower_erection | Tower Erection | TRUE | 523 | 203 | 0 | 16 | 1 | 219 | 304 | 11 |  | TB 605 - DPR - 2026-06-12.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-12 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tack welding | tack_welding | Other | FALSE | 523 | 0 | 0 | 0 | 0 | 0 | 523 | 0 |  | TB 605 - DPR - 2026-06-12.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-12 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Stringing | stringing | Stringing | TRUE | 175.719 | 0 | 0 | 0 | 0 | 0 | 175.719 | 1 |  | TB 605 - DPR - 2026-06-12.xlsx | TB-605 | TB-605 | TB 605 Status
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Route Alignment | route_alignment | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Route Alignment - Main Line | route_alignment | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Route Alignment - Loop In | route_alignment | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Route Alignment - Loop Out | route_alignment | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Detail Survey | detail_survey | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Detailed Survey - Main Line | detailed_survey | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Detailed Survey - Loop In | detailed_survey | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Detailed Survey - Loop Out | detailed_survey | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Check Survey | check_survey | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Check Survey - Main Line | check_survey | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Check Survey - Loop In | check_survey | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Check Survey - Loop Out | check_survey | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Normal Open Cast Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Normal Foundation - Main Line | foundation | Foundation | TRUE | 266 | 131 | 8 | 1 | 0 | 132 | 134 | 7.0 |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Normal Foundation - Loop In (Incld. Stone Column) | foundation | Foundation | TRUE | 20 | 0 | 0 | 0 | 0 | 0 | 20 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | Foundation | TRUE | 15 | 1 | 0 | 0 | 0 | 1 | 14 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Pile Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Pile Foundation_River_Main Line | foundation | Foundation | TRUE | 2 | 1 | 0 | 0 | 0 | 1 | 1 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Pile Foundation_Non River_Loop In | foundation | Foundation | TRUE | 7 | 7 | 0 | 0 | 0 | 7 | 0 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Pile Foundation_Non River_Loop Out | foundation | Foundation | TRUE | 8 | 6 | 0 | 0 | 0 | 6 | 2 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Pile Cap Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Earthing | earthing | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Erection | tower_erection | Tower Erection | TRUE | [9 empty] | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Tower Erection - Main Line | tower_erection | Tower Erection | TRUE | 268 | 31 | 20 | 2 | 0 | 33 | 235 | 7.0 |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Tower Erection - loop In | tower_erection | Tower Erection | TRUE | 27 | 0 | 0 | 0 | 0 | 0 | 27 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Tower Erection - Loop Out | tower_erection | Tower Erection | TRUE | 23 | 0 | 0 | 1 | 1 | 1 | 22 | 1.0 |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Tack welding | tack_welding | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Tack welding - Main Line | tack_welding | Other | FALSE | 268 | 0 | 0 | 0 | 0 | 0 | 268 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Tack welding - Loop In | tack_welding | Other | FALSE | 27 | 0 | 0 | 0 | 0 | 0 | 27 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Tack welding - Loop Out | tack_welding | Other | FALSE | 23 | 0 | 0 | 0 | 0 | 0 | 23 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Final Sag - Main Line | stringing | Stringing | TRUE | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Final Sag - Loop In | stringing | Stringing | TRUE | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | Final Sag - Loop Out | stringing | Stringing | TRUE | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | [9 empty] | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | OPGW Stringing - Main Line | opgw_stringing | OPGW Stringing | TRUE | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | OPGW Stringing - Loop In | opgw_stringing | OPGW Stringing | TRUE | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-12 | 2026-06-01 | LOA | OPGW Stringing - Loop Out | opgw_stringing | OPGW Stringing | TRUE | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134 |  |  | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TA 418 | TA 418 | ta418 |  | 2026-06-10 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-10 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-10 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-10 | 2026-06-01 | Progress Status | Stringing - RS | stringing | Stringing | TRUE | 47.84 | 29.582 | 18.258 | 1.6442 | 0 | 31.2262 | 16.6138 | 4 | *Work Front Required for Hotline Gang | TA 418 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 421 | TA 421 | ta421 |  | 2026-06-10 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-10 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 309 | 303 | 6 | 0 |  | 303 | 6 |  |  | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-10 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-10 | 2026-06-01 | Progress Status | Tackwelding | tack_welding | Other | FALSE | 309 | 283 | 26 |  |  | 283 | 26 | 1.0 |  | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-10 | 2026-06-01 | Progress Status | Tower Tightening | tower_tightening | Other | FALSE | 309 | 309 |  |  |  | 309 | 0 | 2.0 |  | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-10 | 2026-06-01 | Progress Status | Stringing -F/S | stringing | Stringing | TRUE | 121.342 | 115.467 | 5.878 | 0.678 |  | 116.145 | 5.197 | 1.0 | WIP - 33/0- 34/0 | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-10 | 2026-06-01 | Progress Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67 |  |  | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-10 | 2026-06-01 | Progress Status | NH Crossing | nh_crossing | Other | FALSE | 3 | 3 |  |  |  | 3 |  |  |  | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-10 | 2026-06-01 | Progress Status | Power Line Crossing | power_line_crossing | Other | FALSE | 5 | 5 |  |  |  | 5 |  |  |  | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 504 | TA 504 | ta504 |  | 2026-06-10 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Detail Survey | detail_survey | Other | FALSE | 69 | 69 |  |  |  | 69 | 0 |  |  | TA 504 - DPR - 2026-06-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-10 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Check Survey | check_survey | Other | FALSE | 69 | 67 | 2 |  |  | 67 | 2 |  |  | TA 504 - DPR - 2026-06-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-10 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | FOUNDATION | foundation | Foundation | TRUE | 186 | 144 | 6 | 1 |  | 145 | 42 |  |  | TA 504 - DPR - 2026-06-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-10 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 186 | 121 | 6 |  |  | 121 | 65 |  |  | TA 504 - DPR - 2026-06-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-10 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Stringing | stringing | Stringing | TRUE | 69 | 13.422 | 8 | 1.574 |  | 14.996 | 55.578 |  |  | TA 504 - DPR - 2026-06-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-10 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 69 |  |  |  |  | 0 | 69 |  |  | TA 504 - DPR - 2026-06-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 505 | TA 505 | ta505 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Detail Survey | detail_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-09.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Check Survey | check_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-09.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | FOUNDATION | foundation | Foundation | TRUE | 379 | 375 | 4 | 0 |  | 375 | 4 |  | 1 Locations are under severe RoW. | TA 505 - DPR - 2026-06-09.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 379 | 357 | 7 | 3 |  | 360 | 22 |  | Tack Welding Completed- 132/354, Gangs Engaged-3. | TA 505 - DPR - 2026-06-09.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Stringing (Final Sag) | stringing | Stringing | TRUE | 139.6 | 15.462 | 23.008 | 0 |  | 15.462 | 124.138 |  |  | TA 505 - DPR - 2026-06-09.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 506 | TA 506 | ta506 |  | 2026-06-10 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Detail Survey | detail_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-10 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Check Survey | check_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-10 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | FOUNDATION | foundation | Foundation | TRUE | 602 | 492 | 40 | 1 |  | 493 | 110 |  |  | TA 506 - DPR - 2026-06-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-10 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 602 | 405 | 25 | 2 |  | 407 | 197 |  |  | TA 506 - DPR - 2026-06-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-10 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Stringing | stringing | Stringing | TRUE | 223 | 55.632 | 30 | 2.32 |  | 57.952 | 167.368 |  |  | TA 506 - DPR - 2026-06-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-10 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 231 | [8 empty] | TA 506 - DPR - 2026-06-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 510 | TA 510 | ta510 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: | Route Alignment (Km) | route_alignment | Other | FALSE | 114.516 | 114.516 | 0 |  |  | 114.516 | 0 |  |  | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: | Detailed Survey (Km) | detailed_survey | Other | FALSE | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024 |  |  | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: | Check Survey (Km) | check_survey | Other | FALSE | 114.516 | 93.542 | 0 |  |  | 93.542 | 20.974 |  |  | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 30 | 30 | 0 |  |  | 30 | 0 |  |  | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: | Excavation | excavation | Other | FALSE | 293 | 88 | 16 |  |  | 92 | 201 |  |  | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: | Foundation (Nos.) | foundation | Foundation | TRUE | 293 | 85 | 16 | 3 | 1 | 88 | 205 | 5.0 |  | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: | Earthing (Nos.) | earthing | Other | FALSE | 293 | 78 | 16 |  |  | 80 | 213 |  |  | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 293 | 40 | 30 | 4 |  | 44 | 249 | 2.0 |  | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: | Tack Welding | tack_welding | Other | FALSE | 293 | 13 | 30 |  |  | 13 | 280 |  |  | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: | Paying Out | paying_out | Other | FALSE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: | Final Sag | stringing | Stringing | TRUE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 114.516 | 0 | 20 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-09 | 2026-06-01 | Office : Hansera, Lunkaransar | Route Alignment (Km) | route_alignment | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-09 | 2026-06-01 | Office : Hansera, Lunkaransar | Detailed Survey (Km) | detailed_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-09 | 2026-06-01 | Office : Hansera, Lunkaransar | Check Survey (Km) | check_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-09 | 2026-06-01 | Office : Hansera, Lunkaransar | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 | 0 | 0 | 0 | 28 | 0 |  |  | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-09 | 2026-06-01 | Office : Hansera, Lunkaransar | Excavation | excavation | Other | FALSE | 319 | 308 | 18 | 2 | 0 | 310 | 9 |  |  | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-09 | 2026-06-01 | Office : Hansera, Lunkaransar | Foundation (Nos.) | foundation | Foundation | TRUE | 319 | 306 | 18 | 2 | 0 | 308 | 11 | 02/20 |  | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-09 | 2026-06-01 | Office : Hansera, Lunkaransar | Earthing (Nos.) | earthing | Other | FALSE | 319 | 269 |  |  |  | 269 | 50 |  |  | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-09 | 2026-06-01 | Office : Hansera, Lunkaransar | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 319 | 221 | 30 | 2 |  | 223 | 96 | 06/185 |  | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-09 | 2026-06-01 | Office : Hansera, Lunkaransar | Tack Welding | tack_welding | Other | FALSE | 319 | 79 |  | 9 | 2 | 88 | 231 |  |  | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-09 | 2026-06-01 | Office : Hansera, Lunkaransar | Paying Out | paying_out | Other | FALSE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-09 | 2026-06-01 | Office : Hansera, Lunkaransar | Final Sag | stringing | Stringing | TRUE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-09 | 2026-06-01 | Office : Hansera, Lunkaransar | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 124.568 | 0 | 20 | 0 |  | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026) | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 399 | 64 | 25 | 4 | 1 | 68 | 331 | 4 | Loc-51/1-2 Pit PCC Done Loc-54/2-Steel Binding WIP(Pit Collapse) Loc-62/0-3Pit Casting compl(ROW) Loc-62/1-Casting compl Loc-74/7-4 pit PCC Compl | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 399 | 7 |  |  |  | 7 | 392 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 399 | 24 | 11 | 1 |  | 25 | 374 | 1 | Loc-56/4-Tower erection WIP | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 399 | 0 |  |  |  | 0 | 399 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 147.584 | 0 |  |  |  |  | 147.584 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 82.803 | 82.803 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.796 |  |  |  | 82.796 | 0.007 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025) | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 220 | 25 | 10 | 1 | 1 | 26 | 194 | 1 | Loc-55/1-Casting compl | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 220 | 10 |  |  | 0 | 10 | 210 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 220 | 7 | 5 |  |  | 7 | 213 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 220 |  |  |  |  | 0 | 220 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 82.803 | [5 empty] | 82.803 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-09 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status
TA 601 | TA 601 | ta601 |  | 2026-06-10 | 2026-06-01 | Foundation Status | Foundation | foundation | Foundation | TRUE | 292 | 124 | 35 | 5 | 0 | 129 | 163 | 6 |  | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-10 | 2026-06-01 | Foundation Status | Earthing | earthing | Other | FALSE | 292 | 102 | 35 | 2 | 0 | 104 | 188 |  |  | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-10 | 2026-06-01 | Foundation Status | Tower Erection | tower_erection | Tower Erection | TRUE | 292 | 71 | 25 | 1 | 0 | 72 | 220 | 5 |  | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-10 | 2026-06-01 | Foundation Status | Stringing -R/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-10 | 2026-06-01 | Foundation Status | Stringing -F/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-10 | 2026-06-01 | Foundation Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-10 | 2026-06-01 | Foundation Status | NH Crossing | nh_crossing | Other | FALSE | 3 | [5 empty] | 3 |  |  | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-10 | 2026-06-01 | Foundation Status | SH Crossing | sh_crossing | Other | FALSE | 1 | [5 empty] | 1 |  |  | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-10 | 2026-06-01 | Foundation Status | Railway crossing | railway_crossing | Other | FALSE | 2 | [5 empty] | 2 |  |  | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-10 | 2026-06-01 | Foundation Status | Power Line Crossing | power_line_crossing | Other | FALSE | 6 | [5 empty] | 6 |  |  | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-10 | 2026-06-01 | Foundation Status | WIP - Foundations | foundation | Foundation | TRUE | [7 empty] | Gang |  | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 602 | TA 602 | ta602 |  | 2026-06-09 | 2026-06-01 | ¦ ROUTE ALIGNMENT | ¦ ROUTE ALIGNMENT | route_alignment | Other | FALSE | 184.986 | 185.149 |  | 0 |  | 185.149 | 0 |  |  | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-09 | 2026-06-01 | ¦ SOIL INVESTIGATION | ¦ SOIL INVESTIGATION | soil_investigation | Other | FALSE | 31 | 17 |  | 1 |  | 18 | 13 |  |  | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-09 | 2026-06-01 | ¦ DETAILED SURVEY | ¦ DETAILED SURVEY | detailed_survey | Other | FALSE | 184.986 | 166.531 |  | 0 |  | 166.531 | 18.455 |  |  | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-09 | 2026-06-01 | ¦ CHECK SURVEY | ¦ CHECK SURVEY | check_survey | Other | FALSE | 184.986 | 136.139 |  | 0 |  | 136.139 | 48.847 |  |  | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-09 | 2026-06-01 | ¦ FOUNDATION | ¦ FOUNDATION | foundation | Foundation | TRUE | 480 | 154 |  | 7 |  | 161 | 319 |  |  | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-09 | 2026-06-01 | ¦ EARTHING | ¦ EARTHING | earthing | Other | FALSE | 480 | 96 |  | 8 |  | 104 | 376 |  |  | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-09 | 2026-06-01 | ¦ TOWER ERECTION | ¦ TOWER ERECTION | tower_erection | Tower Erection | TRUE | 480 | 52 |  | 9 |  | 61 | 419 |  |  | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-09 | 2026-06-01 | ¦ STRINGING | ¦ STRINGING | stringing | Stringing | TRUE | 184.986 | 0 |  | 0 |  | 0 | 184.986 |  |  | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-09 | 2026-06-01 | ¦ OPGW STRINGING | ¦ OPGW STRINGING | opgw_stringing | OPGW Stringing | TRUE | 184.986 | 0 |  | 0 |  | 0 | 184.986 |  |  | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TB 605 | TB 605 | tb605 |  | 2026-06-09 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Check Survey | check_survey | Other | FALSE | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3 |  | TB 605 - DPR - 2026-06-09.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-09 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Foundation | foundation | Foundation | TRUE | 523 | 370 | 0 | 16 | 6 | 386 | 137 | 27 |  | TB 605 - DPR - 2026-06-09.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-09 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Earthing | earthing | Other | FALSE | 523 | 308 | 0 | 0 | 0 | 308 | 215 | 0 |  | TB 605 - DPR - 2026-06-09.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-09 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tower Erection | tower_erection | Tower Erection | TRUE | 523 | 203 | 0 | 11 | 0 | 214 | 309 | 13 |  | TB 605 - DPR - 2026-06-09.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-09 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tack welding | tack_welding | Other | FALSE | 523 | 0 | 0 | 0 | 0 | 0 | 523 | 0 |  | TB 605 - DPR - 2026-06-09.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-09 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Stringing | stringing | Stringing | TRUE | 175.719 | 0 | 0 | 0 | 0 | 0 | 175.719 | 1 |  | TB 605 - DPR - 2026-06-09.xlsx | TB-605 | TB-605 | TB 605 Status
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Route Alignment | route_alignment | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Route Alignment - Main Line | route_alignment | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Route Alignment - Loop In | route_alignment | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Route Alignment - Loop Out | route_alignment | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Detail Survey | detail_survey | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Detailed Survey - Main Line | detailed_survey | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Detailed Survey - Loop In | detailed_survey | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Detailed Survey - Loop Out | detailed_survey | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Check Survey | check_survey | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Check Survey - Main Line | check_survey | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Check Survey - Loop In | check_survey | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Check Survey - Loop Out | check_survey | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Normal Open Cast Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Normal Foundation - Main Line | foundation | Foundation | TRUE | 266 | 131 | 8 | 0 | 0 | 131 | 135 | 7.0 |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Normal Foundation - Loop In (Incld. Stone Column) | foundation | Foundation | TRUE | 20 | 0 | 0 | 0 | 0 | 0 | 20 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | Foundation | TRUE | 15 | 1 | 0 | 0 | 0 | 1 | 14 | 1.0 |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Pile Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Pile Foundation_River_Main Line | foundation | Foundation | TRUE | 2 | 1 | 0 | 0 | 0 | 1 | 1 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Pile Foundation_Non River_Loop In | foundation | Foundation | TRUE | 7 | 7 | 0 | 0 | 0 | 7 | 0 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Pile Foundation_Non River_Loop Out | foundation | Foundation | TRUE | 8 | 6 | 0 | 0 | 0 | 6 | 2 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Pile Cap Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Earthing | earthing | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Erection | tower_erection | Tower Erection | TRUE | [9 empty] | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Tower Erection - Main Line | tower_erection | Tower Erection | TRUE | 268 | 31 | 20 | 2 | 1 | 33 | 235 | 7.0 |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Tower Erection - loop In | tower_erection | Tower Erection | TRUE | 27 | 0 | 0 | 0 | 0 | 0 | 27 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Tower Erection - Loop Out | tower_erection | Tower Erection | TRUE | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 1.0 |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Tack welding | tack_welding | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Tack welding - Main Line | tack_welding | Other | FALSE | 268 | 0 | 0 | 0 | 0 | 0 | 268 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Tack welding - Loop In | tack_welding | Other | FALSE | 27 | 0 | 0 | 0 | 0 | 0 | 27 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Tack welding - Loop Out | tack_welding | Other | FALSE | 23 | 0 | 0 | 0 | 0 | 0 | 23 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Final Sag - Main Line | stringing | Stringing | TRUE | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Final Sag - Loop In | stringing | Stringing | TRUE | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | Final Sag - Loop Out | stringing | Stringing | TRUE | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | [9 empty] | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | OPGW Stringing - Main Line | opgw_stringing | OPGW Stringing | TRUE | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | OPGW Stringing - Loop In | opgw_stringing | OPGW Stringing | TRUE | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-09 | 2026-06-01 | LOA | OPGW Stringing - Loop Out | opgw_stringing | OPGW Stringing | TRUE | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134 |  |  | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Detail Survey (Km) | detail_survey_km | Other | FALSE | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Check Survey approved(Km) | check_survey | Other | FALSE | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Excavation | excavation | Other | FALSE | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Foundation (Nos.) | foundation | Foundation | TRUE | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Earthing (Nos.) | earthing | Other | FALSE | 309 | 307 | 2 | 0 | 0 | 307 | 2 |  |  | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 306 | 302 | 4 | 0 | 0 | 302 | 4 |  | G_1:- Amit Kumar Singh (WIP 16/0) | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Tack Welding | tack_welding | Other | FALSE | 306 | 255 | 47 | 2 | 0 | 257 | 49 | 1.0 | G_1:- M.S Enterprises (WIP 35/3 ) | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Stringing (Km) | stringing | Stringing | TRUE | 117.8509 | 77.189 | 21.51 | 0.243 | 0.243 | 77.432 | 40.4189 | 2.0 | G_1:- Rahim Khan (AP 15/0 to AP 16/0) | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Paying Out | paying_out | Other | FALSE | 117.8509 | 77.189 | 21.51 | 0.243 | 0.243 | 77.432 | 40.4189 |  | G_2:- SK infra (AP 35/0 to AP 36/0) | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Final Sag | final_sag | Other | FALSE | 117.8509 | 77.189 | 21.51 | 0.243 | 0.243 | 77.432 | 40.4189 | 1.0 | G_3:- Gopal Associate (AP 14/0 to AP 15/0) | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889 |  |  | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Route Alignment (Km) | route_alignment | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Detailed Survey (Km) | detailed_survey | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Check Survey (Km) | check_survey | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 |  |  |  | 28 | 0 |  |  | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Excavation | excavation | Other | FALSE | 352 | 319 | 31 | 6 | 2 | 325 | 27 |  |  | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Foundation (Nos.) | foundation | Foundation | TRUE | 352 | 319 | 31 | 6 | 2 | 325 | 27 | 7.0 |  | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Earthing (Nos.) | earthing | Other | FALSE | 352 | 296 | 31 | 20 | 2 | 316 | 36 |  |  | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 352 | 235 | 44 | 10 | 1 | 245 | 107 | 14.0 | 1 gang arrived on 08.06.26 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Tack Welding | tack_welding | Other | FALSE | 352 | 120 | 55 | 22 | 4 | 142 | 210 | 3.0 |  | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Stringing (Km) | stringing | Stringing | TRUE | 127.799 | 15.944 | 20 | 4.4432 |  | 20.3872 | 107.4118 | 6.0 |  | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Paying Out | paying_out | Other | FALSE | 127.799 | 21.618 | 20 | 0.226 |  | 21.844 | 105.955 |  |  | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Final Sag | final_sag | Other | FALSE | 127.799 | 15.944 | 20 | 4.4432 |  | 20.3872 | 107.4118 |  |  | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-09 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 127.799 | 0 | 20 |  |  | 0 | 127.799 |  |  | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 416 | TA 416 | ta416 |  | 2026-06-08 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0 |  | TA 416 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 416 | TA 416 | ta416 |  | 2026-06-08 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0 |  | TA 416 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 416 | TA 416 | ta416 |  | 2026-06-08 | 2026-06-01 | Progress Status | Erection | tower_erection | Tower Erection | TRUE | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0 |  | TA 416 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 416 | TA 416 | ta416 |  | 2026-06-08 | 2026-06-01 | Progress Status | Stringing | stringing | Stringing | TRUE | 115.134 | 111.1 | 4 | 0.807 | 0.282 | 111.94 | 3.194 | 5 |  | TA 416 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 418 | TA 418 | ta418 |  | 2026-06-08 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-08 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-08 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-08 | 2026-06-01 | Progress Status | Stringing - RS | stringing | Stringing | TRUE | 47.84 | 29.582 | 18.258 | 1.3677 | 0.27649 | 30.9497 | 16.8903 | 3 | *Work Front Required for Hotline Gang | TA 418 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Route Alignment (Km) | route_alignment | Other | FALSE | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661 |  |  | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Detailed Survey (Km) | detailed_survey | Other | FALSE | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001 |  |  | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Check Survey (Km) | check_survey | Other | FALSE | 122.071 | 122.07 |  |  |  | 1 | 121.071 |  |  | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 31 | 31 | 0 |  |  | 31 |  |  |  | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Excavation (Nos) | excavation | Other | FALSE | 330 | 167 |  |  |  | 167 | 163 |  |  | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Foundation (Nos) | foundation | Foundation | TRUE | 330 | 255 | 49 | 7 |  | 262 | 68 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 52/2, 59/0, 63B/3, 66/0, 74/0, 76/1, 82/0, 87/1, 96/0, 96/2 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Earthing (Nos) | earthing | Other | FALSE | 330 | 217 | 50 | 0 |  | 217 | 113 |  |  | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 330 | 207 | 50 | 4 |  | 211 | 119 | 11 | 36/4, 38/3, 41/2, 42/0 ,52/1, 53/0, 62/0, 65/0 64/4, 71/0, 81/0 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Tack Welding (Nos) | tack_welding | Other | FALSE | 330 | 35 | 50 |  |  | 35 | 295 | 1 |  | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Stringing (Km) | stringing | Stringing | TRUE | 122.071 |  |  | 0.447 |  |  | 122.071 |  |  | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Paying Out (Km) | paying_out | Other | FALSE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 |  |  | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Final Sag (Km) | stringing | Stringing | TRUE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 |  |  | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | OPGW Stringing (Km) | opgw_stringing | OPGW Stringing | TRUE | 122.071 | 0 |  |  |  | 0 | 122.071 |  |  | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-08 | 2026-06-01 | Completed Days | Power Line Crossings | power_line_crossings | Other | FALSE | [9 empty] | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 421 | TA 421 | ta421 |  | 2026-06-07 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-07 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 309 | 303 | 6 | 0 |  | 303 | 6 |  |  | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-07 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-07 | 2026-06-01 | Progress Status | Tackwelding | tack_welding | Other | FALSE | 309 | 283 | 26 |  |  | 283 | 26 | 1.0 |  | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-07 | 2026-06-01 | Progress Status | Tower Tightening | tower_tightening | Other | FALSE | 309 | 309 |  |  |  | 309 | 0 | 2.0 |  | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-07 | 2026-06-01 | Progress Status | Stringing -F/S | stringing | Stringing | TRUE | 121.342 | 115.467 | 5.878 |  |  | 115.467 | 5.875 |  | 43A/1-43B/0 - Rough sag done & 33/0- 34/0 | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-07 | 2026-06-01 | Progress Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67 |  |  | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-07 | 2026-06-01 | Progress Status | NH Crossing | nh_crossing | Other | FALSE | 3 | 3 |  |  |  | 3 |  |  |  | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-07 | 2026-06-01 | Progress Status | Power Line Crossing | power_line_crossing | Other | FALSE | 5 | 5 |  |  |  | 5 |  |  |  | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 504 | TA 504 | ta504 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Detail Survey | detail_survey | Other | FALSE | 69 | 69 |  |  |  | 69 | 0 |  |  | TA 504 - DPR - 2026-06-09.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Check Survey | check_survey | Other | FALSE | 69 | 67 | 2 |  |  | 67 | 2 |  |  | TA 504 - DPR - 2026-06-09.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | FOUNDATION | foundation | Foundation | TRUE | 186 | 144 | 6 | 1 |  | 145 | 42 |  |  | TA 504 - DPR - 2026-06-09.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 186 | 121 | 6 |  |  | 121 | 65 |  |  | TA 504 - DPR - 2026-06-09.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Stringing | stringing | Stringing | TRUE | 69 | 13.422 | 8 | 1.574 |  | 14.996 | 55.578 |  |  | TA 504 - DPR - 2026-06-09.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 69 |  |  |  |  | 0 | 69 |  |  | TA 504 - DPR - 2026-06-09.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 505 | TA 505 | ta505 |  | 2026-06-08 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Detail Survey | detail_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-08 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Check Survey | check_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-08 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | FOUNDATION | foundation | Foundation | TRUE | 379 | 375 | 4 | 0 |  | 375 | 4 |  | 1 Locations are under severe RoW. | TA 505 - DPR - 2026-06-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-08 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 379 | 357 | 7 | 3 |  | 360 | 22 |  | Tack Welding Completed- 132/354, Gangs Engaged-3. | TA 505 - DPR - 2026-06-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-08 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Stringing (Final Sag) | stringing | Stringing | TRUE | 139.6 | 15.462 | 23.008 | 0 |  | 15.462 | 124.138 |  |  | TA 505 - DPR - 2026-06-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 506 | TA 506 | ta506 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Detail Survey | detail_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-09.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Check Survey | check_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-09.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | FOUNDATION | foundation | Foundation | TRUE | 602 | 492 | 40 | 1 |  | 493 | 110 |  |  | TA 506 - DPR - 2026-06-09.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 602 | 405 | 25 | 2 |  | 407 | 197 |  |  | TA 506 - DPR - 2026-06-09.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Stringing | stringing | Stringing | TRUE | 223 | 55.632 | 30 | 2.32 |  | 57.952 | 167.368 |  |  | TA 506 - DPR - 2026-06-09.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-09 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 231 | [8 empty] | TA 506 - DPR - 2026-06-09.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 510 | TA 510 | ta510 |  | 2026-06-08 | 2026-06-01 | NOA Ref. No.: | Route Alignment (Km) | route_alignment | Other | FALSE | 114.516 | 114.516 | 0 |  |  | 114.516 | 0 |  |  | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-08 | 2026-06-01 | NOA Ref. No.: | Detailed Survey (Km) | detailed_survey | Other | FALSE | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024 |  |  | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-08 | 2026-06-01 | NOA Ref. No.: | Check Survey (Km) | check_survey | Other | FALSE | 114.516 | 93.542 | 0 |  |  | 93.542 | 20.974 |  |  | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-08 | 2026-06-01 | NOA Ref. No.: | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 30 | 30 | 0 |  |  | 30 | 0 |  |  | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-08 | 2026-06-01 | NOA Ref. No.: | Excavation | excavation | Other | FALSE | 293 | 88 | 16 |  |  | 88 | 205 |  |  | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-08 | 2026-06-01 | NOA Ref. No.: | Foundation (Nos.) | foundation | Foundation | TRUE | 293 | 85 | 16 | 2 |  | 87 | 206 | 5.0 |  | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-08 | 2026-06-01 | NOA Ref. No.: | Earthing (Nos.) | earthing | Other | FALSE | 293 | 78 | 16 |  |  | 80 | 213 |  |  | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-08 | 2026-06-01 | NOA Ref. No.: | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 293 | 40 | 30 | 3 | 1 | 43 | 250 | 3.0 |  | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-08 | 2026-06-01 | NOA Ref. No.: | Tack Welding | tack_welding | Other | FALSE | 293 | 13 | 30 |  |  | 13 | 280 |  |  | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-08 | 2026-06-01 | NOA Ref. No.: | Paying Out | paying_out | Other | FALSE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-08 | 2026-06-01 | NOA Ref. No.: | Final Sag | stringing | Stringing | TRUE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-08 | 2026-06-01 | NOA Ref. No.: | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 114.516 | 0 | 20 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-08 | 2026-06-01 | Office : Hansera, Lunkaransar | Route Alignment (Km) | route_alignment | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-08 | 2026-06-01 | Office : Hansera, Lunkaransar | Detailed Survey (Km) | detailed_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-08 | 2026-06-01 | Office : Hansera, Lunkaransar | Check Survey (Km) | check_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-08 | 2026-06-01 | Office : Hansera, Lunkaransar | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 | 0 | 0 | 0 | 28 | 0 |  |  | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-08 | 2026-06-01 | Office : Hansera, Lunkaransar | Excavation | excavation | Other | FALSE | 319 | 308 | 18 | 2 | 0 | 310 | 9 |  |  | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-08 | 2026-06-01 | Office : Hansera, Lunkaransar | Foundation (Nos.) | foundation | Foundation | TRUE | 319 | 306 | 18 | 2 | 0 | 308 | 11 | 02/20 |  | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-08 | 2026-06-01 | Office : Hansera, Lunkaransar | Earthing (Nos.) | earthing | Other | FALSE | 319 | 269 |  |  |  | 269 | 50 |  |  | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-08 | 2026-06-01 | Office : Hansera, Lunkaransar | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 319 | 221 | 30 | 2 |  | 223 | 96 | 05/144 |  | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-08 | 2026-06-01 | Office : Hansera, Lunkaransar | Tack Welding | tack_welding | Other | FALSE | 319 | 79 |  | 7 | 2 | 86 | 233 |  |  | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-08 | 2026-06-01 | Office : Hansera, Lunkaransar | Paying Out | paying_out | Other | FALSE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-08 | 2026-06-01 | Office : Hansera, Lunkaransar | Final Sag | stringing | Stringing | TRUE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-08 | 2026-06-01 | Office : Hansera, Lunkaransar | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 124.568 | 0 | 20 | 0 |  | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026) | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 399 | 64 | 25 | 3 | 2 | 67 | 332 | 5 | Loc-54/1-Casting compl Loc-54/2-Steel Binding WIP Loc-62/0-3Pit Casting compl Loc-62/1-2 Pit steel binding Compl Loc-74/8-Casting compl | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 399 | 7 |  |  |  | 7 | 392 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 399 | 24 | 11 | 1 |  | 25 | 374 | 1 | Loc-56/4-Tower erection WIP | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 399 | 0 |  |  |  | 0 | 399 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 147.584 | 0 |  |  |  |  | 147.584 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 82.803 | 82.803 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.796 |  |  |  | 82.796 | 0.007 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025) | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 220 | 25 | 10 |  |  | 25 | 195 | 1 | Loc-55/1-Casting WIP | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 220 | 10 |  |  | 0 | 10 | 210 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 220 | 7 | 5 |  |  | 7 | 213 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 220 |  |  |  |  | 0 | 220 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 82.803 | [5 empty] | 82.803 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-07 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status
TA 601 | TA 601 | ta601 |  | 2026-06-08 | 2026-06-01 | Foundation Status | Foundation | foundation | Foundation | TRUE | 292 | 124 | 35 | 4 | 0 | 128 | 164 | 6 |  | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-08 | 2026-06-01 | Foundation Status | Earthing | earthing | Other | FALSE | 292 | 102 | 35 | 2 | 1 | 104 | 188 |  |  | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-08 | 2026-06-01 | Foundation Status | Tower Erection | tower_erection | Tower Erection | TRUE | 292 | 71 | 25 | 1 | 0 | 72 | 220 | 5 |  | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-08 | 2026-06-01 | Foundation Status | Stringing -R/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-08 | 2026-06-01 | Foundation Status | Stringing -F/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-08 | 2026-06-01 | Foundation Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-08 | 2026-06-01 | Foundation Status | NH Crossing | nh_crossing | Other | FALSE | 3 | [5 empty] | 3 |  |  | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-08 | 2026-06-01 | Foundation Status | SH Crossing | sh_crossing | Other | FALSE | 1 | [5 empty] | 1 |  |  | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-08 | 2026-06-01 | Foundation Status | Railway crossing | railway_crossing | Other | FALSE | 2 | [5 empty] | 2 |  |  | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-08 | 2026-06-01 | Foundation Status | Power Line Crossing | power_line_crossing | Other | FALSE | 6 | [5 empty] | 6 |  |  | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-08 | 2026-06-01 | Foundation Status | WIP - Foundations | foundation | Foundation | TRUE | [7 empty] | Gang |  | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-08 | 2026-06-01 | 220kV Line | Detailed Survey | detailed_survey | Other | FALSE | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0 |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-08 | 2026-06-01 | 220kV Line | Check Survey | check_survey | Other | FALSE | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 |  |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-08 | 2026-06-01 | 220kV Line | Foundation | foundation | Foundation | TRUE | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-08 | 2026-06-01 | 220kV Line | Earthing | earthing | Other | FALSE | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-08 | 2026-06-01 | 220kV Line | Tower Erection | tower_erection | Tower Erection | TRUE | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0 |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-08 | 2026-06-01 | 220kV Line | Tack Welding | tack_welding | Other | FALSE | 199 | 195 | 4 | 0 | 0 | 195 | 4 | 0.0 |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-08 | 2026-06-01 | 220kV Line | Paying Out | paying_out | Other | FALSE | 64 | 61.2 | 2.8 | 0.95161 | 0 | 62.1516 | 1.8484 | 0.0 |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-08 | 2026-06-01 | 220kV Line | Final Sag | stringing | Stringing | TRUE | 64 | 61.2 | 2.8 | 0.95161 | 0 | 62.1516 | 1.8484 |  |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-08 | 2026-06-01 | 220kV Line | OPGW | opgw_stringing | OPGW Stringing | TRUE | 64 | 53.7218 | 10.2782 | 10.389 | 0 | 64.1108 | -0.11079 | 0.0 |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-08 | 2026-06-01 | 132kV Line | Detailed Survey | detailed_survey | Other | FALSE | 9 | 9 |  | 0 | 0 | 9 | 0 |  |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-08 | 2026-06-01 | 132kV Line | Check Survey | check_survey | Other | FALSE | 9 | 9 |  | 0 | 0 | 9 | 0 |  |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-08 | 2026-06-01 | 132kV Line | Foundation | foundation | Foundation | TRUE | 39 | 36 | 5 | 0 | 0 | 36 | 3 | 1.0 | SC-2 and SC-4 Foundation WIP | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-08 | 2026-06-01 | 132kV Line | Earthing | earthing | Other | FALSE | 39 | 34 | 5 | 2 | 0 | 36 | 3 | 1.0 |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-08 | 2026-06-01 | 132kV Line | Tower Erection | tower_erection | Tower Erection | TRUE | 39 | 31 | 5 | 0 | 0 | 31 | 8 | 1.0 | 2/1 and 1/0 Erection WIP | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-08 | 2026-06-01 | 132kV Line | Tack Welding | tack_welding | Other | FALSE | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0 |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-08 | 2026-06-01 | 132kV Line | Paying Out | paying_out | Other | FALSE | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0 |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-08 | 2026-06-01 | 132kV Line | Final Sag | stringing | Stringing | TRUE | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 |  |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-08 | 2026-06-01 | 132kV Line | OPGW | opgw_stringing | OPGW Stringing | TRUE | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0 |  | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Route Alignment (Kms) | route_alignment | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Detailed Survey (Kms) | detailed_survey | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Check Survey (Kms) | check_survey | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 73 | 73 | 0 | 0 | 0 | 73 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Foundation (Nos) | foundation | Foundation | TRUE | 513 | 308 | 34 | 4 |  | 312 | 201 | 5.0 | 45.0 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Earthing (Nos) | earthing | Other | FALSE | 513 | 266 |  |  |  | 266 | 247 |  |  | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 513 | 218 | 39 | 3 |  | 221 | 292 | 4.0 | 79.0 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Tack Welding (Nos) | tack_welding | Other | FALSE | 513 | 104 | 153 |  |  | 104 | 409 | 1.0 | 3.0 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Stringing (Kms) | stringing | Stringing | TRUE | [9 empty] | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 188.678 | 21.797 | 21.084 |  |  | 21.797 | 166.881 | 2.0 | 40.0 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318 |  |  | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | OPGW Stringing (Kms) | opgw_stringing | OPGW Stringing | TRUE | 188.678 | 0 | [7 empty] | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 188.678 |  |  |  |  | 0 | 188.678 |  |  | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-08 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 188.678 |  |  |  |  | 0 | 188.678 |  |  | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-08 | 2026-06-01 | Progress Summary | Route Alignment (Kms) | route_alignment | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-08 | 2026-06-01 | Progress Summary | Detailed Survey (Kms) | detailed_survey | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-08 | 2026-06-01 | Progress Summary | Check Survey (Kms) | check_survey | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-08 | 2026-06-01 | Progress Summary | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 26 | 26 | 0 | 0 | 0 | 26 | 0 |  |  | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-08 | 2026-06-01 | Progress Summary | Foundation (Nos) | foundation | Foundation | TRUE | 43 | 34 | 8 | 1 |  | 35 | 5 | 2.0 | 20.0 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-08 | 2026-06-01 | Progress Summary | Earthing (Nos) | earthing | Other | FALSE | 43 | 3 |  |  | 0 | 3 | 40 |  |  | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-08 | 2026-06-01 | Progress Summary | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 43 | 3 | 12 |  | 0 | 3 | 40 |  |  | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-08 | 2026-06-01 | Progress Summary | Tack Welding (Nos) | tack_welding | Other | FALSE | 43 |  |  |  |  | 0 | 43 |  |  | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-08 | 2026-06-01 | Progress Summary | Stringing (Kms) | stringing | Stringing | TRUE | [6 empty] | 0 |  |  | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-08 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-08 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-08 | 2026-06-01 | Progress Summary | OPGW Stringing (Kms) | opgw_stringing | OPGW Stringing | TRUE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 605 | TB 605 | tb605 |  | 2026-06-07 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Check Survey | check_survey | Other | FALSE | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3 |  | TB 605 - DPR - 2026-06-07.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-07 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Foundation | foundation | Foundation | TRUE | 523 | 370 | 88 | 10 | 0 | 380 | 143 | 27 |  | TB 605 - DPR - 2026-06-07.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-07 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Earthing | earthing | Other | FALSE | 523 | 308 | 82 | 0 | 0 | 308 | 215 | 0 |  | TB 605 - DPR - 2026-06-07.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-07 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tower Erection | tower_erection | Tower Erection | TRUE | 523 | 203 | 80 | 9 | 1 | 212 | 311 | 13 |  | TB 605 - DPR - 2026-06-07.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-07 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tack welding | tack_welding | Other | FALSE | 523 | 0 | 80 | 0 | 0 | 0 | 523 | 0 |  | TB 605 - DPR - 2026-06-07.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-07 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Stringing | stringing | Stringing | TRUE | 175.719 | 0 | 14.92 | 0 | 0 | 0 | 175.719 | 1 |  | TB 605 - DPR - 2026-06-07.xlsx | TB-605 | TB-605 | TB 605 Status
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Route Alignment | route_alignment | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Route Alignment - Main Line | route_alignment | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Route Alignment - Loop In | route_alignment | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Route Alignment - Loop Out | route_alignment | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Detail Survey | detail_survey | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Detailed Survey - Main Line | detailed_survey | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Detailed Survey - Loop In | detailed_survey | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Detailed Survey - Loop Out | detailed_survey | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Check Survey | check_survey | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Check Survey - Main Line | check_survey | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Check Survey - Loop In | check_survey | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Check Survey - Loop Out | check_survey | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Normal Open Cast Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Normal Foundation - Main Line | foundation | Foundation | TRUE | 266 | 131 | 8 | 0 | 0 | 131 | 135 | 7.0 |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Normal Foundation - Loop In (Incld. Stone Column) | foundation | Foundation | TRUE | 20 | 0 | 0 | 0 | 0 | 0 | 20 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | Foundation | TRUE | 15 | 1 | 0 | 0 | 0 | 1 | 14 | 1.0 |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Pile Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Pile Foundation_River_Main Line | foundation | Foundation | TRUE | 2 | 1 | 0 | 0 | 0 | 1 | 1 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Pile Foundation_Non River_Loop In | foundation | Foundation | TRUE | 7 | 7 | 0 | 0 | 0 | 7 | 0 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Pile Foundation_Non River_Loop Out | foundation | Foundation | TRUE | 8 | 6 | 0 | 0 | 0 | 6 | 2 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Pile Cap Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Earthing | earthing | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Erection | tower_erection | Tower Erection | TRUE | [9 empty] | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Tower Erection - Main Line | tower_erection | Tower Erection | TRUE | 268 | 31 | 20 | 1 | 0 | 32 | 236 | 7.0 |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Tower Erection - loop In | tower_erection | Tower Erection | TRUE | 27 | 0 | 0 | 0 | 0 | 0 | 27 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Tower Erection - Loop Out | tower_erection | Tower Erection | TRUE | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 1.0 |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Tack welding | tack_welding | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Tack welding - Main Line | tack_welding | Other | FALSE | 268 | 0 | 0 | 0 | 0 | 0 | 268 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Tack welding - Loop In | tack_welding | Other | FALSE | 27 | 0 | 0 | 0 | 0 | 0 | 27 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Tack welding - Loop Out | tack_welding | Other | FALSE | 23 | 0 | 0 | 0 | 0 | 0 | 23 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Final Sag - Main Line | stringing | Stringing | TRUE | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Final Sag - Loop In | stringing | Stringing | TRUE | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | Final Sag - Loop Out | stringing | Stringing | TRUE | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | [9 empty] | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | OPGW Stringing - Main Line | opgw_stringing | OPGW Stringing | TRUE | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | OPGW Stringing - Loop In | opgw_stringing | OPGW Stringing | TRUE | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-07 | 2026-06-01 | LOA | OPGW Stringing - Loop Out | opgw_stringing | OPGW Stringing | TRUE | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134 |  |  | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Detail Survey (Km) | detail_survey_km | Other | FALSE | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Check Survey approved(Km) | check_survey | Other | FALSE | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Excavation | excavation | Other | FALSE | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Foundation (Nos.) | foundation | Foundation | TRUE | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Earthing (Nos.) | earthing | Other | FALSE | 309 | 307 | 2 | 1 | 1 | 308 | 1 |  |  | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 306 | 302 | 4 | 0 | 0 | 302 | 4 | 1.0 | G_1:- Amit Kumar Singh (WIP 16/0) | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Tack Welding | tack_welding | Other | FALSE | 306 | 255 | 47 | 5 | 1 | 260 | 46 | 1.0 | G_1:- M.S Enterprises (WIP 22/0 ) | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Stringing (Km) | stringing | Stringing | TRUE | 117.8509 | 77.189 | 21.51 | 0.243 | 0 | 77.432 | 40.4189 | 2.0 | G_1:- Rahim Khan (AP 15/0 to AP 16/0) | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Paying Out | paying_out | Other | FALSE | 117.8509 | 77.189 | 21.51 | 0.243 | 0 | 77.432 | 40.4189 |  | G_2:- SK infra (AP 35/0 to AP 36/0) | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Final Sag | final_sag | Other | FALSE | 117.8509 | 77.189 | 21.51 | 0.243 | 0 | 77.432 | 40.4189 | 1.0 | G_3:- Gopal Associate (AP 14/0 to AP 15/0) | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889 |  |  | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Detail Survey (Km) | detail_survey_km | Other | FALSE | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Check Survey approved(Km) | check_survey | Other | FALSE | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Excavation | excavation | Other | FALSE | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Foundation (Nos.) | foundation | Foundation | TRUE | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Earthing (Nos.) | earthing | Other | FALSE | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | LOC no 36A/0 ROW | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 306 | 302 | 4 | 0 | 0 | 302 | 4 | 1.0 | G_1:- Amit Kumar Singh (WIP 16/0) | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Tack Welding | tack_welding | Other | FALSE | 306 | 255 | 47 | 7 | 1 | 262 | 44 | 1.0 | G_1:- M.S Enterprises | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Stringing (Km) | stringing | Stringing | TRUE | 117.8509 | 77.189 | 21.51 | 0.243 | 0 | 77.432 | 40.4189 | 2.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Paying Out | paying_out | Other | FALSE | 117.8509 | 77.189 | 21.51 | 0.243 | 0 | 77.432 | 40.4189 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ROW ) | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Final Sag | final_sag | Other | FALSE | 117.8509 | 77.189 | 21.51 | 0.243 | 0 | 77.432 | 40.4189 | 1.0 | G_3:- Gopal Associate (AP 14/0 to AP 15/0) | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889 |  |  | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Route Alignment (Km) | route_alignment | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Detailed Survey (Km) | detailed_survey | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Check Survey (Km) | check_survey | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 |  |  |  | 28 | 0 |  |  | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Excavation | excavation | Other | FALSE | 352 | 319 | 31 | 6 |  | 325 | 27 |  |  | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Foundation (Nos.) | foundation | Foundation | TRUE | 352 | 319 | 31 | 6 |  | 325 | 27 | 7.0 |  | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Earthing (Nos.) | earthing | Other | FALSE | 352 | 296 | 31 | 21 | 1 | 317 | 35 |  |  | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 352 | 235 | 44 | 10 | 1 | 245 | 107 | 14.0 | 1 gang arrived on 08.06.26 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Tack Welding | tack_welding | Other | FALSE | 352 | 120 | 55 | 26 | 3 | 146 | 206 | 3.0 |  | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Stringing (Km) | stringing | Stringing | TRUE | 127.799 | 15.944 | 20 | 4.4432 |  | 20.3872 | 107.4118 | 6.0 |  | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Paying Out | paying_out | Other | FALSE | 127.799 | 21.618 | 20 | 0.226 |  | 21.844 | 105.955 |  |  | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Final Sag | final_sag | Other | FALSE | 127.799 | 15.944 | 20 | 4.4432 |  | 20.3872 | 107.4118 |  |  | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-10 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 127.799 | 0 | 20 |  |  | 0 | 127.799 |  |  | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 418 | TA 418 | ta418 |  | 2026-06-11 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-11.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-11 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-11.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-11 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-11.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-11 | 2026-06-01 | Progress Status | Stringing - RS | stringing | Stringing | TRUE | 47.84 | 29.582 | 18.258 | 1.6442 | 1.8367 | 31.2262 | 16.6138 | 4 | *Work Front Required for Hotline Gang | TA 418 - DPR - 2026-06-11.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Route Alignment (Km) | route_alignment | Other | FALSE | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661 |  |  | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Detailed Survey (Km) | detailed_survey | Other | FALSE | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001 |  |  | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Check Survey (Km) | check_survey | Other | FALSE | 122.071 | 122.07 |  |  |  | 1 | 121.071 |  |  | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 31 | 31 | 0 |  |  | 31 |  |  |  | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Excavation (Nos) | excavation | Other | FALSE | 330 | 167 |  |  |  | 167 | 163 |  |  | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Foundation (Nos) | foundation | Foundation | TRUE | 330 | 255 | 49 | 9 |  | 264 | 66 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Earthing (Nos) | earthing | Other | FALSE | 330 | 217 | 50 | 0 |  | 217 | 113 |  |  | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 330 | 207 | 50 | 5 |  | 212 | 118 | 11 | 36/4, 37/0, 38/3, 41/2, 42/0 ,52/1, 54/0, 62/0, 65/0 64/4, 71/0, 76/0 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Tack Welding (Nos) | tack_welding | Other | FALSE | 330 | 35 | 50 |  |  | 35 | 295 | 1 |  | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Stringing (Km) | stringing | Stringing | TRUE | 122.071 |  |  | 0.447 |  |  | 122.071 |  |  | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Paying Out (Km) | paying_out | Other | FALSE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 |  |  | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Final Sag (Km) | stringing | Stringing | TRUE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | ` |  | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | OPGW Stringing (Km) | opgw_stringing | OPGW Stringing | TRUE | 122.071 | 0 |  |  |  | 0 | 122.071 |  |  | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-11 | 2026-06-01 | Completed Days | Power Line Crossings | power_line_crossings | Other | FALSE | [9 empty] | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 504 | TA 504 | ta504 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Detail Survey | detail_survey | Other | FALSE | 69 | 69 |  |  |  | 69 | 0 |  |  | TA 504 - DPR - 2026-06-11.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Check Survey | check_survey | Other | FALSE | 69 | 67 | 2 |  |  | 67 | 2 |  |  | TA 504 - DPR - 2026-06-11.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | FOUNDATION | foundation | Foundation | TRUE | 186 | 144 | 6 | 1 |  | 145 | 42 |  |  | TA 504 - DPR - 2026-06-11.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 186 | 121 | 6 |  |  | 121 | 65 |  |  | TA 504 - DPR - 2026-06-11.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Stringing | stringing | Stringing | TRUE | 69 | 13.422 | 8 | 1.574 |  | 14.996 | 55.578 |  |  | TA 504 - DPR - 2026-06-11.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 69 |  |  |  |  | 0 | 69 |  |  | TA 504 - DPR - 2026-06-11.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 505 | TA 505 | ta505 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Detail Survey | detail_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-11.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Check Survey | check_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-11.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | FOUNDATION | foundation | Foundation | TRUE | 379 | 375 | 4 | 0 |  | 375 | 4 |  |  | TA 505 - DPR - 2026-06-11.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 132/354, Gangs Engaged-3. | TA 505 - DPR - 2026-06-11.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Stringing (Final Sag) | stringing | Stringing | TRUE | 139.6 | 15.462 | 23.008 | 4.304 |  | 19.766 | 124.138 |  |  | TA 505 - DPR - 2026-06-11.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 506 | TA 506 | ta506 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Detail Survey | detail_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-11.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Check Survey | check_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-11.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | FOUNDATION | foundation | Foundation | TRUE | 602 | 492 | 40 | 1 |  | 493 | 110 |  |  | TA 506 - DPR - 2026-06-11.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 602 | 405 | 25 | 4 |  | 409 | 197 |  |  | TA 506 - DPR - 2026-06-11.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Stringing | stringing | Stringing | TRUE | 223 | 55.632 | 30 | 2.32 |  | 57.952 | 167.368 |  |  | TA 506 - DPR - 2026-06-11.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-11 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 231 | [8 empty] | TA 506 - DPR - 2026-06-11.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 510 | TA 510 | ta510 |  | 2026-06-11 | 2026-06-01 | NOA Ref. No.: | Route Alignment (Km) | route_alignment | Other | FALSE | 114.516 | 114.516 | 0 |  |  | 114.516 | 0 |  |  | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-11 | 2026-06-01 | NOA Ref. No.: | Detailed Survey (Km) | detailed_survey | Other | FALSE | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024 |  |  | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-11 | 2026-06-01 | NOA Ref. No.: | Check Survey (Km) | check_survey | Other | FALSE | 114.516 | 93.542 | 0 |  |  | 93.542 | 20.974 |  |  | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-11 | 2026-06-01 | NOA Ref. No.: | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 30 | 30 | 0 |  |  | 30 | 0 |  |  | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-11 | 2026-06-01 | NOA Ref. No.: | Excavation | excavation | Other | FALSE | 293 | 88 | 16 |  |  | 92 | 201 |  |  | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-11 | 2026-06-01 | NOA Ref. No.: | Foundation (Nos.) | foundation | Foundation | TRUE | 293 | 85 | 16 | 4 | 1 | 89 | 204 | 5.0 |  | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-11 | 2026-06-01 | NOA Ref. No.: | Earthing (Nos.) | earthing | Other | FALSE | 293 | 78 | 16 |  |  | 80 | 213 |  |  | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-11 | 2026-06-01 | NOA Ref. No.: | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 293 | 40 | 30 | 4 |  | 44 | 249 | 2.0 |  | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-11 | 2026-06-01 | NOA Ref. No.: | Tack Welding | tack_welding | Other | FALSE | 293 | 13 | 30 |  |  | 13 | 280 |  |  | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-11 | 2026-06-01 | NOA Ref. No.: | Paying Out | paying_out | Other | FALSE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-11 | 2026-06-01 | NOA Ref. No.: | Final Sag | stringing | Stringing | TRUE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-11 | 2026-06-01 | NOA Ref. No.: | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 114.516 | 0 | 20 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-11 | 2026-06-01 | Office : Hansera, Lunkaransar | Route Alignment (Km) | route_alignment | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-11 | 2026-06-01 | Office : Hansera, Lunkaransar | Detailed Survey (Km) | detailed_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-11 | 2026-06-01 | Office : Hansera, Lunkaransar | Check Survey (Km) | check_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-11 | 2026-06-01 | Office : Hansera, Lunkaransar | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 | 0 | 0 | 0 | 28 | 0 |  |  | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-11 | 2026-06-01 | Office : Hansera, Lunkaransar | Excavation | excavation | Other | FALSE | 319 | 308 | 18 | 4 | 1 | 312 | 7 |  |  | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-11 | 2026-06-01 | Office : Hansera, Lunkaransar | Foundation (Nos.) | foundation | Foundation | TRUE | 319 | 306 | 18 | 3 | 0 | 309 | 10 | 02/20 |  | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-11 | 2026-06-01 | Office : Hansera, Lunkaransar | Earthing (Nos.) | earthing | Other | FALSE | 319 | 269 |  |  |  | 269 | 50 |  |  | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-11 | 2026-06-01 | Office : Hansera, Lunkaransar | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 319 | 221 | 30 | 2 |  | 223 | 96 | 06/206 |  | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-11 | 2026-06-01 | Office : Hansera, Lunkaransar | Tack Welding | tack_welding | Other | FALSE | 319 | 79 |  | 13 | 2 | 92 | 227 |  |  | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-11 | 2026-06-01 | Office : Hansera, Lunkaransar | Paying Out | paying_out | Other | FALSE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-11 | 2026-06-01 | Office : Hansera, Lunkaransar | Final Sag | stringing | Stringing | TRUE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-11 | 2026-06-01 | Office : Hansera, Lunkaransar | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 124.568 | 0 | 20 | 0 |  | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026) | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 399 | 64 | 25 | 4 |  | 68 | 331 | 3 | Loc-51/1-Casting WIP Loc-62/0-3Pit Casting compl(ROW) Loc-61/0-Casting WIP Loc-74/7-Casting WIP | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 399 | 7 |  |  |  | 7 | 392 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 399 | 24 | 11 | 1 |  | 25 | 374 | 2 | Loc-56/4-Tower erection U/P Loc-56/3-Material Shifting U/P | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 399 | 0 |  |  |  | 0 | 399 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 147.584 | 0 |  |  |  |  | 147.584 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 82.803 | 82.803 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.796 |  |  |  | 82.796 | 0.007 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025) | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 220 | 25 | 10 | 1 |  | 26 | 194 | 1 |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 220 | 10 |  |  | 0 | 10 | 210 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 220 | 7 | 5 |  |  | 7 | 213 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 220 |  |  |  |  | 0 | 220 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 82.803 | [5 empty] | 82.803 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-11 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status
TA 601 | TA 601 | ta601 |  | 2026-06-11 | 2026-06-01 | Foundation Status | Foundation | foundation | Foundation | TRUE | 292 | 124 | 35 | 5 | 0 | 129 | 163 | 6 |  | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-11 | 2026-06-01 | Foundation Status | Earthing | earthing | Other | FALSE | 292 | 102 | 35 | 2 | 0 | 104 | 188 |  |  | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-11 | 2026-06-01 | Foundation Status | Tower Erection | tower_erection | Tower Erection | TRUE | 292 | 71 | 25 | 1 | 0 | 72 | 220 | 5 |  | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-11 | 2026-06-01 | Foundation Status | Stringing -R/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-11 | 2026-06-01 | Foundation Status | Stringing -F/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-11 | 2026-06-01 | Foundation Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-11 | 2026-06-01 | Foundation Status | NH Crossing | nh_crossing | Other | FALSE | 3 | [5 empty] | 3 |  |  | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-11 | 2026-06-01 | Foundation Status | SH Crossing | sh_crossing | Other | FALSE | 1 | [5 empty] | 1 |  |  | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-11 | 2026-06-01 | Foundation Status | Railway crossing | railway_crossing | Other | FALSE | 2 | [5 empty] | 2 |  |  | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-11 | 2026-06-01 | Foundation Status | Power Line Crossing | power_line_crossing | Other | FALSE | 6 | [5 empty] | 6 |  |  | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-11 | 2026-06-01 | Foundation Status | WIP - Foundations | foundation | Foundation | TRUE | [7 empty] | Gang |  | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 602 | TA 602 | ta602 |  | 2026-06-11 | 2026-06-01 | ROUTE ALIGNMENT | ROUTE ALIGNMENT | route_alignment | Other | FALSE | 184.986 | 185.149 |  | 0 |  | 185.149 | 0 |  |  | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-11 | 2026-06-01 | SOIL INVESTIGATION | SOIL INVESTIGATION | soil_investigation | Other | FALSE | 31 | 17 |  | 1 |  | 18 | 13 |  |  | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-11 | 2026-06-01 | DETAILED SURVEY | DETAILED SURVEY | detailed_survey | Other | FALSE | 184.986 | 166.531 |  | 0 |  | 166.531 | 18.455 |  |  | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-11 | 2026-06-01 | CHECK SURVEY | CHECK SURVEY | check_survey | Other | FALSE | 184.986 | 136.139 |  | 0 |  | 136.139 | 48.847 |  |  | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-11 | 2026-06-01 | FOUNDATION | FOUNDATION | foundation | Foundation | TRUE | 480 | 154 |  | 7 |  | 161 | 319 |  |  | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-11 | 2026-06-01 | EARTHING | EARTHING | earthing | Other | FALSE | 480 | 96 |  | 9 |  | 105 | 375 |  |  | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-11 | 2026-06-01 | TOWER ERECTION | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 480 | 52 |  | 11 |  | 63 | 417 |  |  | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-11 | 2026-06-01 | STRINGING | STRINGING | stringing | Stringing | TRUE | 184.986 | 0 |  | 0 |  | 0 | 184.986 |  |  | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-11 | 2026-06-01 | OPGW STRINGING | OPGW STRINGING | opgw_stringing | OPGW Stringing | TRUE | 184.986 | 0 |  | 0 |  | 0 | 184.986 |  |  | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-09 | 2026-06-01 | 220kV Line | Detailed Survey | detailed_survey | Other | FALSE | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0 |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-09 | 2026-06-01 | 220kV Line | Check Survey | check_survey | Other | FALSE | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 |  |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-09 | 2026-06-01 | 220kV Line | Foundation | foundation | Foundation | TRUE | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-09 | 2026-06-01 | 220kV Line | Earthing | earthing | Other | FALSE | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-09 | 2026-06-01 | 220kV Line | Tower Erection | tower_erection | Tower Erection | TRUE | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0 |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-09 | 2026-06-01 | 220kV Line | Tack Welding | tack_welding | Other | FALSE | 199 | 195 | 4 | 0 | 0 | 195 | 4 | 0.0 |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-09 | 2026-06-01 | 220kV Line | Paying Out | paying_out | Other | FALSE | 64 | 61.2 | 2.8 | 1.5681 | 0 | 62.7681 | 1.2319 | 0.0 |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-09 | 2026-06-01 | 220kV Line | Final Sag | stringing | Stringing | TRUE | 64 | 61.2 | 2.8 | 1.5681 | 0 | 62.7681 | 1.2319 |  |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-09 | 2026-06-01 | 220kV Line | OPGW | opgw_stringing | OPGW Stringing | TRUE | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0 |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-09 | 2026-06-01 | 132kV Line | Detailed Survey | detailed_survey | Other | FALSE | 9 | 9 |  | 0 | 0 | 9 | 0 |  |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-09 | 2026-06-01 | 132kV Line | Check Survey | check_survey | Other | FALSE | 9 | 9 |  | 0 | 0 | 9 | 0 |  |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-09 | 2026-06-01 | 132kV Line | Foundation | foundation | Foundation | TRUE | 39 | 36 | 5 | 0 | 0 | 36 | 3 | 1.0 | SC-4 Pit-A,C,D Steel Binding Done | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-09 | 2026-06-01 | 132kV Line | Earthing | earthing | Other | FALSE | 39 | 34 | 5 | 2 | 0 | 36 | 3 | 1.0 |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-09 | 2026-06-01 | 132kV Line | Tower Erection | tower_erection | Tower Erection | TRUE | 39 | 31 | 5 | 0 | 0 | 31 | 8 | 1.0 | 2/1 Erection second section WIP | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-09 | 2026-06-01 | 132kV Line | Tack Welding | tack_welding | Other | FALSE | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0 |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-09 | 2026-06-01 | 132kV Line | Paying Out | paying_out | Other | FALSE | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0 |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-09 | 2026-06-01 | 132kV Line | Final Sag | stringing | Stringing | TRUE | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 |  |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-09 | 2026-06-01 | 132kV Line | OPGW | opgw_stringing | OPGW Stringing | TRUE | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0 |  | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Route Alignment (Kms) | route_alignment | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Detailed Survey (Kms) | detailed_survey | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Check Survey (Kms) | check_survey | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 73 | 73 | 0 | 0 | 0 | 73 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Foundation (Nos) | foundation | Foundation | TRUE | 513 | 308 | 34 | 6 |  | 314 | 199 | 5.0 | 45.0 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Earthing (Nos) | earthing | Other | FALSE | 513 | 266 |  |  |  | 266 | 247 |  |  | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 513 | 218 | 39 | 5 |  | 223 | 290 | 4.0 | 79.0 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Tack Welding (Nos) | tack_welding | Other | FALSE | 513 | 104 | 153 | 8 |  | 112 | 401 | 1.0 | 3.0 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Stringing (Kms) | stringing | Stringing | TRUE | [9 empty] | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 188.678 | 21.797 | 21.084 |  |  | 21.797 | 166.881 | 2.0 | 40.0 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318 |  |  | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | OPGW Stringing (Kms) | opgw_stringing | OPGW Stringing | TRUE | 188.678 | 0 | [7 empty] | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 188.678 |  |  |  |  | 0 | 188.678 |  |  | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-11 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 188.678 |  |  |  |  | 0 | 188.678 |  |  | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-11 | 2026-06-01 | Progress Summary | Route Alignment (Kms) | route_alignment | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-11 | 2026-06-01 | Progress Summary | Detailed Survey (Kms) | detailed_survey | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-11 | 2026-06-01 | Progress Summary | Check Survey (Kms) | check_survey | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-11 | 2026-06-01 | Progress Summary | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 26 | 26 | 0 | 0 | 0 | 26 | 0 |  |  | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-11 | 2026-06-01 | Progress Summary | Foundation (Nos) | foundation | Foundation | TRUE | 43 | 34 | 8 | 1 |  | 35 | 8 | 2.0 | 20.0 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-11 | 2026-06-01 | Progress Summary | Earthing (Nos) | earthing | Other | FALSE | 43 | 3 |  |  | 0 | 3 | 40 |  |  | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-11 | 2026-06-01 | Progress Summary | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 43 | 3 | 12 |  | 0 | 3 | 40 | 1.0 | 24.0 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-11 | 2026-06-01 | Progress Summary | Tack Welding (Nos) | tack_welding | Other | FALSE | 43 |  |  |  |  | 0 | 43 |  |  | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-11 | 2026-06-01 | Progress Summary | Stringing (Kms) | stringing | Stringing | TRUE | [6 empty] | 0 |  |  | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-11 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-11 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-11 | 2026-06-01 | Progress Summary | OPGW Stringing (Kms) | opgw_stringing | OPGW Stringing | TRUE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 605 | TB 605 | tb605 |  | 2026-06-11 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Check Survey | check_survey | Other | FALSE | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3 |  | TB 605 - DPR - 2026-06-11.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-11 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Foundation | foundation | Foundation | TRUE | 523 | 370 | 0 | 18 | 0 | 388 | 135 | 26 |  | TB 605 - DPR - 2026-06-11.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-11 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Earthing | earthing | Other | FALSE | 523 | 308 | 0 | 0 | 0 | 308 | 215 | 0 |  | TB 605 - DPR - 2026-06-11.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-11 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tower Erection | tower_erection | Tower Erection | TRUE | 523 | 203 | 0 | 15 | 1 | 218 | 305 | 11 |  | TB 605 - DPR - 2026-06-11.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-11 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tack welding | tack_welding | Other | FALSE | 523 | 0 | 0 | 0 | 0 | 0 | 523 | 0 |  | TB 605 - DPR - 2026-06-11.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-11 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Stringing | stringing | Stringing | TRUE | 175.719 | 0 | 0 | 0 | 0 | 0 | 175.719 | 1 |  | TB 605 - DPR - 2026-06-11.xlsx | TB-605 | TB-605 | TB 605 Status
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Route Alignment | route_alignment | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Route Alignment - Main Line | route_alignment | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Route Alignment - Loop In | route_alignment | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Route Alignment - Loop Out | route_alignment | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Detail Survey | detail_survey | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Detailed Survey - Main Line | detailed_survey | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Detailed Survey - Loop In | detailed_survey | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Detailed Survey - Loop Out | detailed_survey | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Check Survey | check_survey | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Check Survey - Main Line | check_survey | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Check Survey - Loop In | check_survey | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Check Survey - Loop Out | check_survey | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Normal Open Cast Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Normal Foundation - Main Line | foundation | Foundation | TRUE | 266 | 131 | 8 | 1 | 1 | 132 | 134 | 6.0 |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Normal Foundation - Loop In (Incld. Stone Column) | foundation | Foundation | TRUE | 20 | 0 | 0 | 0 | 0 | 0 | 20 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | Foundation | TRUE | 15 | 1 | 0 | 0 | 0 | 1 | 14 | 1.0 |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Pile Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Pile Foundation_River_Main Line | foundation | Foundation | TRUE | 2 | 1 | 0 | 0 | 0 | 1 | 1 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Pile Foundation_Non River_Loop In | foundation | Foundation | TRUE | 7 | 7 | 0 | 0 | 0 | 7 | 0 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Pile Foundation_Non River_Loop Out | foundation | Foundation | TRUE | 8 | 6 | 0 | 0 | 0 | 6 | 2 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Pile Cap Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Earthing | earthing | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Erection | tower_erection | Tower Erection | TRUE | [9 empty] | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Tower Erection - Main Line | tower_erection | Tower Erection | TRUE | 268 | 31 | 20 | 2 | 0 | 33 | 235 | 7.0 |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Tower Erection - loop In | tower_erection | Tower Erection | TRUE | 27 | 0 | 0 | 0 | 0 | 0 | 27 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Tower Erection - Loop Out | tower_erection | Tower Erection | TRUE | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 1.0 |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Tack welding | tack_welding | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Tack welding - Main Line | tack_welding | Other | FALSE | 268 | 0 | 0 | 0 | 0 | 0 | 268 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Tack welding - Loop In | tack_welding | Other | FALSE | 27 | 0 | 0 | 0 | 0 | 0 | 27 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Tack welding - Loop Out | tack_welding | Other | FALSE | 23 | 0 | 0 | 0 | 0 | 0 | 23 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Final Sag - Main Line | stringing | Stringing | TRUE | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Final Sag - Loop In | stringing | Stringing | TRUE | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | Final Sag - Loop Out | stringing | Stringing | TRUE | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | [9 empty] | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | OPGW Stringing - Main Line | opgw_stringing | OPGW Stringing | TRUE | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | OPGW Stringing - Loop In | opgw_stringing | OPGW Stringing | TRUE | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-10 | 2026-06-01 | LOA | OPGW Stringing - Loop Out | opgw_stringing | OPGW Stringing | TRUE | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134 |  |  | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Detail Survey (Km) | detail_survey_km | Other | FALSE | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Check Survey approved(Km) | check_survey | Other | FALSE | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Excavation | excavation | Other | FALSE | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Foundation (Nos.) | foundation | Foundation | TRUE | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Earthing (Nos.) | earthing | Other | FALSE | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | LOC no 36A/0 ROW | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 306 | 302 | 4 | 0 | 0 | 302 | 4 | 1.0 | G_1:- Amit Kumar Singh (WIP 16/0) | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Tack Welding | tack_welding | Other | FALSE | 306 | 255 | 47 | 7 | 0 | 262 | 44 | 1.0 | G_1:- M.S Enterprises | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Stringing (Km) | stringing | Stringing | TRUE | 117.8509 | 77.189 | 21.51 | 0.467 | 0.224 | 77.656 | 40.1949 | 2.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (13A/0 to 14/0) | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Paying Out | paying_out | Other | FALSE | 117.8509 | 77.189 | 21.51 | 0.467 | 0.224 | 77.656 | 40.1949 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ROW ) | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Final Sag | final_sag | Other | FALSE | 117.8509 | 77.189 | 21.51 | 0.467 | 0.224 | 77.656 | 40.1949 | 1.0 | G_3:- Gopal Associate (AP 14/0 to AP 15/0 Spacering work) | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889 |  |  | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 416 | TA 416 | ta416 |  | 2026-06-10 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0 |  | TA 416 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 416 | TA 416 | ta416 |  | 2026-06-10 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0 |  | TA 416 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 416 | TA 416 | ta416 |  | 2026-06-10 | 2026-06-01 | Progress Status | Erection | tower_erection | Tower Erection | TRUE | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0 |  | TA 416 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 416 | TA 416 | ta416 |  | 2026-06-10 | 2026-06-01 | Progress Status | Stringing | stringing | Stringing | TRUE | 115.134 | 111.1 | 4 | 0.807 | 0 | 111.94 | 3.194 | 5 |  | TA 416 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 505 | TA 505 | ta505 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Detail Survey | detail_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Check Survey | check_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | FOUNDATION | foundation | Foundation | TRUE | 379 | 375 | 4 | 0 |  | 375 | 4 |  |  | TA 505 - DPR - 2026-06-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 132/354, Gangs Engaged-3. | TA 505 - DPR - 2026-06-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Stringing (Final Sag) | stringing | Stringing | TRUE | 139.6 | 15.462 | 23.008 | 4.504 |  | 19.966 | 124.138 |  |  | TA 505 - DPR - 2026-06-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 418 | TA 418 | ta418 |  | 2026-06-13 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-13.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-13 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-13.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-13 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-13.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-13 | 2026-06-01 | Progress Status | Stringing - RS | stringing | Stringing | TRUE | 47.84 | 29.582 | 18.258 | 1.6442 | 2.0953 | 31.2262 | 16.6138 | 4 | *Work Front Required for Hotline Gang | TA 418 - DPR - 2026-06-13.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Route Alignment (Km) | route_alignment | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Detailed Survey (Km) | detailed_survey | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Check Survey (Km) | check_survey | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 |  |  |  | 28 | 0 |  |  | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Excavation | excavation | Other | FALSE | 352 | 319 | 31 | 8 |  | 327 | 25 |  |  | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Foundation (Nos.) | foundation | Foundation | TRUE | 352 | 319 | 31 | 8 |  | 327 | 25 | 7.0 |  | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Earthing (Nos.) | earthing | Other | FALSE | 352 | 296 | 31 | 29 |  | 325 | 27 |  |  | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 352 | 235 | 44 | 14 | 2 | 249 | 103 | 15.0 | 1 gang arrived on 14.06.26 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Tack Welding | tack_welding | Other | FALSE | 352 | 120 | 55 | 35 | 3 | 155 | 197 | 3.0 |  | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Stringing (Km) | stringing | Stringing | TRUE | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438 | 6.0 |  | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Paying Out | paying_out | Other | FALSE | 127.799 | 21.618 | 20 | 1.893 |  | 23.511 | 104.288 |  |  | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Final Sag | final_sag | Other | FALSE | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438 |  |  | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 127.799 | 0 | 20 |  |  | 0 | 127.799 |  |  | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 418 | TA 418 | ta418 |  | 2026-06-14 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-14.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-14 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-14.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-14 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-14.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-14 | 2026-06-01 | Progress Status | Stringing - RS | stringing | Stringing | TRUE | 47.84 | 29.582 | 18.258 | 1.6442 | 2.0953 | 31.2262 | 16.6138 | 4 | *Work Front Required for Hotline Gang | TA 418 - DPR - 2026-06-14.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Route Alignment (Km) | route_alignment | Other | FALSE | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661 |  |  | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Detailed Survey (Km) | detailed_survey | Other | FALSE | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001 |  |  | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Check Survey (Km) | check_survey | Other | FALSE | 122.071 | 122.07 |  |  |  | 1 | 121.071 |  |  | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 31 | 31 | 0 |  |  | 31 |  |  |  | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Excavation (Nos) | excavation | Other | FALSE | 330 | 167 |  |  |  | 167 | 163 |  |  | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Foundation (Nos) | foundation | Foundation | TRUE | 330 | 255 | 49 | 9 |  | 264 | 66 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Earthing (Nos) | earthing | Other | FALSE | 330 | 217 | 50 | 0 |  | 217 | 113 |  |  | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 330 | 207 | 50 | 6 |  | 213 | 117 | 12 | 36/4, 37/0, 38/2, 41/2, 42/0 ,52/1, 54/0, 62/0, 65/0, 65/2, 64/4, 71/0, 76/0 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Tack Welding (Nos) | tack_welding | Other | FALSE | 330 | 35 | 50 |  |  | 35 | 295 | 1 |  | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Stringing (Km) | stringing | Stringing | TRUE | 122.071 |  |  | 0.447 |  |  | 122.071 |  |  | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Paying Out (Km) | paying_out | Other | FALSE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0D/0-0D/5 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Final Sag (Km) | stringing | Stringing | TRUE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | ` |  | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | OPGW Stringing (Km) | opgw_stringing | OPGW Stringing | TRUE | 122.071 | 0 |  |  |  | 0 | 122.071 |  |  | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-14 | 2026-06-01 | Completed Days | Power Line Crossings | power_line_crossings | Other | FALSE | [9 empty] | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 504 | TA 504 | ta504 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Detail Survey | detail_survey | Other | FALSE | 69 | 69 |  |  |  | 69 | 0 |  |  | TA 504 - DPR - 2026-06-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Check Survey | check_survey | Other | FALSE | 69 | 67 | 2 |  |  | 67 | 2 |  |  | TA 504 - DPR - 2026-06-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | FOUNDATION | foundation | Foundation | TRUE | 186 | 144 | 6 | 1 |  | 145 | 42 |  |  | TA 504 - DPR - 2026-06-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 186 | 121 | 6 | 1 |  | 122 | 65 |  |  | TA 504 - DPR - 2026-06-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Stringing | stringing | Stringing | TRUE | 69 | 13.422 | 8 | 1.574 |  | 14.996 | 55.578 |  |  | TA 504 - DPR - 2026-06-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 69 |  |  |  |  | 0 | 69 |  |  | TA 504 - DPR - 2026-06-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 505 | TA 505 | ta505 |  | 2026-06-14 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Detail Survey | detail_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-14 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Check Survey | check_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-14 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | FOUNDATION | foundation | Foundation | TRUE | 379 | 375 | 4 | 0 |  | 375 | 4 |  |  | TA 505 - DPR - 2026-06-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-14 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 132/354, Gangs Engaged-3. | TA 505 - DPR - 2026-06-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-14 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Stringing (Final Sag) | stringing | Stringing | TRUE | 139.6 | 15.462 | 23.008 | 4.504 |  | 19.966 | 124.138 |  |  | TA 505 - DPR - 2026-06-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 506 | TA 506 | ta506 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Detail Survey | detail_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Check Survey | check_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | FOUNDATION | foundation | Foundation | TRUE | 602 | 492 | 40 | 2 |  | 494 | 110 |  |  | TA 506 - DPR - 2026-06-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 602 | 405 | 25 | 5 |  | 410 | 197 |  |  | TA 506 - DPR - 2026-06-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Stringing | stringing | Stringing | TRUE | 223 | 55.632 | 30 | 3.288 |  | 58.92 | 167.368 |  |  | TA 506 - DPR - 2026-06-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-13 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 231 | [8 empty] | TA 506 - DPR - 2026-06-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 510 | TA 510 | ta510 |  | 2026-06-14 | 2026-06-01 | NOA Ref. No.: | Route Alignment (Km) | route_alignment | Other | FALSE | 114.516 | 114.516 | 0 |  |  | 114.516 | 0 |  |  | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-14 | 2026-06-01 | NOA Ref. No.: | Detailed Survey (Km) | detailed_survey | Other | FALSE | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024 |  |  | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-14 | 2026-06-01 | NOA Ref. No.: | Check Survey (Km) | check_survey | Other | FALSE | 114.516 | 93.542 | 0 |  |  | 93.542 | 20.974 |  |  | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-14 | 2026-06-01 | NOA Ref. No.: | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 30 | 30 | 0 |  |  | 30 | 0 |  |  | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-14 | 2026-06-01 | NOA Ref. No.: | Excavation | excavation | Other | FALSE | 293 | 88 | 16 |  |  | 92 | 201 |  |  | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-14 | 2026-06-01 | NOA Ref. No.: | Foundation (Nos.) | foundation | Foundation | TRUE | 293 | 85 | 16 | 6 | 2 | 91 | 202 | 5 |  | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-14 | 2026-06-01 | NOA Ref. No.: | Earthing (Nos.) | earthing | Other | FALSE | 293 | 78 | 16 |  |  | 82 | 211 |  |  | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-14 | 2026-06-01 | NOA Ref. No.: | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 293 | 40 | 30 | 5 |  | 45 | 248 |  |  | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-14 | 2026-06-01 | NOA Ref. No.: | Tack Welding | tack_welding | Other | FALSE | 293 | 13 | 30 |  |  | 13 | 280 |  |  | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-14 | 2026-06-01 | NOA Ref. No.: | Paying Out | paying_out | Other | FALSE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-14 | 2026-06-01 | NOA Ref. No.: | Final Sag | stringing | Stringing | TRUE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-14 | 2026-06-01 | NOA Ref. No.: | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 114.516 | 0 | 20 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-14 | 2026-06-01 | Office : Hansera, Lunkaransar | Route Alignment (Km) | route_alignment | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-14 | 2026-06-01 | Office : Hansera, Lunkaransar | Detailed Survey (Km) | detailed_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-14 | 2026-06-01 | Office : Hansera, Lunkaransar | Check Survey (Km) | check_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-14 | 2026-06-01 | Office : Hansera, Lunkaransar | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 | 0 | 0 | 0 | 28 | 0 |  |  | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-14 | 2026-06-01 | Office : Hansera, Lunkaransar | Excavation | excavation | Other | FALSE | 319 | 308 | 18 | 4 | 0 | 312 | 7 |  |  | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-14 | 2026-06-01 | Office : Hansera, Lunkaransar | Foundation (Nos.) | foundation | Foundation | TRUE | 319 | 306 | 18 | 4 | 0 | 310 | 9 | 02/20 |  | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-14 | 2026-06-01 | Office : Hansera, Lunkaransar | Earthing (Nos.) | earthing | Other | FALSE | 319 | 269 |  |  |  | 269 | 50 |  |  | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-14 | 2026-06-01 | Office : Hansera, Lunkaransar | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 319 | 221 | 30 | 4 | 1 | 225 | 94 | 06/206 |  | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-14 | 2026-06-01 | Office : Hansera, Lunkaransar | Tack Welding | tack_welding | Other | FALSE | 319 | 79 |  | 14 | 0 | 93 | 226 |  |  | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-14 | 2026-06-01 | Office : Hansera, Lunkaransar | Paying Out | paying_out | Other | FALSE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-14 | 2026-06-01 | Office : Hansera, Lunkaransar | Final Sag | stringing | Stringing | TRUE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-14 | 2026-06-01 | Office : Hansera, Lunkaransar | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 124.568 | 0 | 20 | 0 |  | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026) | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 399 | 64 | 25 | 6 | 2 | 70 | 329 | 3 | Loc-51/1-Casting WIP Loc-62/0-3Pit Casting compl(ROW) Loc-61/0-Casting Compl Loc-61/1-Excavation WIP Loc-74/7-Casting Compl Loc-74/6-Excavation (Farmer Stop the Work) Loc-54/2-Boring & Dewatering WIP. | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 399 | 7 |  |  |  | 7 | 392 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 399 | 24 | 11 | 2 |  | 26 | 373 | 2 | Loc-56/3-Material Shifting U/P | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 399 | 0 |  |  |  | 0 | 399 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 147.584 | 0 |  |  |  |  | 147.584 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 82.803 | 82.803 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.796 |  |  |  | 82.796 | 0.007 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025) | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 220 | 25 | 10 | 1 |  | 26 | 194 | 1 |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 220 | 10 |  |  | 0 | 10 | 210 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 220 | 7 | 5 |  |  | 7 | 213 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 220 |  |  |  |  | 0 | 220 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 82.803 | [5 empty] | 82.803 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-14 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status
TA 601 | TA 601 | ta601 |  | 2026-06-14 | 2026-06-01 | Foundation Status | Foundation | foundation | Foundation | TRUE | 292 | 124 | 35 | 7 | 0 | 131 | 161 | 7 |  | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-14 | 2026-06-01 | Foundation Status | Earthing | earthing | Other | FALSE | 292 | 102 | 35 | 2 | 0 | 104 | 188 |  |  | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-14 | 2026-06-01 | Foundation Status | Tower Erection | tower_erection | Tower Erection | TRUE | 292 | 71 | 25 | 3 | 0 | 74 | 218 | 5 |  | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-14 | 2026-06-01 | Foundation Status | Stringing -R/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-14 | 2026-06-01 | Foundation Status | Stringing -F/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-14 | 2026-06-01 | Foundation Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-14 | 2026-06-01 | Foundation Status | NH Crossing | nh_crossing | Other | FALSE | 3 | [5 empty] | 3 |  |  | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-14 | 2026-06-01 | Foundation Status | SH Crossing | sh_crossing | Other | FALSE | 1 | [5 empty] | 1 |  |  | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-14 | 2026-06-01 | Foundation Status | Railway crossing | railway_crossing | Other | FALSE | 2 | [5 empty] | 2 |  |  | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-14 | 2026-06-01 | Foundation Status | Power Line Crossing | power_line_crossing | Other | FALSE | 6 | [5 empty] | 6 |  |  | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-14 | 2026-06-01 | Foundation Status | WIP - Foundations | foundation | Foundation | TRUE | [7 empty] | Gang |  | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 602 | TA 602 | ta602 |  | 2026-06-12 | 2026-06-01 | ROUTE ALIGNMENT | ROUTE ALIGNMENT | route_alignment | Other | FALSE | 184.986 | 185.149 |  | 0 |  | 185.149 | 0 |  |  | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-12 | 2026-06-01 | SOIL INVESTIGATION | SOIL INVESTIGATION | soil_investigation | Other | FALSE | 31 | 17 |  | 1 |  | 18 | 13 |  |  | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-12 | 2026-06-01 | DETAILED SURVEY | DETAILED SURVEY | detailed_survey | Other | FALSE | 184.986 | 166.531 |  | 0 |  | 166.531 | 18.455 |  |  | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-12 | 2026-06-01 | CHECK SURVEY | CHECK SURVEY | check_survey | Other | FALSE | 184.986 | 136.139 |  | 0 |  | 136.139 | 48.847 |  |  | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-12 | 2026-06-01 | FOUNDATION | FOUNDATION | foundation | Foundation | TRUE | 480 | 154 |  | 7 |  | 161 | 319 |  |  | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-12 | 2026-06-01 | EARTHING | EARTHING | earthing | Other | FALSE | 480 | 96 |  | 9 |  | 105 | 375 |  |  | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-12 | 2026-06-01 | TOWER ERECTION | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 480 | 52 |  | 12 |  | 64 | 416 |  |  | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-12 | 2026-06-01 | STRINGING | STRINGING | stringing | Stringing | TRUE | 184.986 | 0 |  | 0 |  | 0 | 184.986 |  |  | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-12 | 2026-06-01 | OPGW STRINGING | OPGW STRINGING | opgw_stringing | OPGW Stringing | TRUE | 184.986 | 0 |  | 0 |  | 0 | 184.986 |  |  | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-13 | 2026-06-01 | 220kV Line | Detailed Survey | detailed_survey | Other | FALSE | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0 |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-13 | 2026-06-01 | 220kV Line | Check Survey | check_survey | Other | FALSE | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 |  |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-13 | 2026-06-01 | 220kV Line | Foundation | foundation | Foundation | TRUE | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-13 | 2026-06-01 | 220kV Line | Earthing | earthing | Other | FALSE | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-13 | 2026-06-01 | 220kV Line | Tower Erection | tower_erection | Tower Erection | TRUE | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0 |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-13 | 2026-06-01 | 220kV Line | Tack Welding | tack_welding | Other | FALSE | 199 | 195 | 4 | 0 | 0 | 195 | 4 | 0.0 |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-13 | 2026-06-01 | 220kV Line | Paying Out | paying_out | Other | FALSE | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 | 0.0 |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-13 | 2026-06-01 | 220kV Line | Final Sag | stringing | Stringing | TRUE | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 |  |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-13 | 2026-06-01 | 220kV Line | OPGW | opgw_stringing | OPGW Stringing | TRUE | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0 |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-13 | 2026-06-01 | 132kV Line | Detailed Survey | detailed_survey | Other | FALSE | 9 | 9 |  | 0 | 0 | 9 | 0 |  |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-13 | 2026-06-01 | 132kV Line | Check Survey | check_survey | Other | FALSE | 9 | 9 |  | 0 | 0 | 9 | 0 |  |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-13 | 2026-06-01 | 132kV Line | Foundation | foundation | Foundation | TRUE | 39 | 36 | 5 | 1 | 0 | 37 | 2 | 1.0 | SC-2 Foundation PCC completed, | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-13 | 2026-06-01 | 132kV Line | Earthing | earthing | Other | FALSE | 39 | 34 | 5 | 2 | 0 | 36 | 3 | 1.0 |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-13 | 2026-06-01 | 132kV Line | Tower Erection | tower_erection | Tower Erection | TRUE | 39 | 31 | 5 | 1 | 0 | 32 | 7 | 1.0 | 2/1 Erection Completed | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-13 | 2026-06-01 | 132kV Line | Tack Welding | tack_welding | Other | FALSE | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0 |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-13 | 2026-06-01 | 132kV Line | Paying Out | paying_out | Other | FALSE | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0 |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-13 | 2026-06-01 | 132kV Line | Final Sag | stringing | Stringing | TRUE | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 |  |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-13 | 2026-06-01 | 132kV Line | OPGW | opgw_stringing | OPGW Stringing | TRUE | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0 |  | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Route Alignment (Kms) | route_alignment | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Detailed Survey (Kms) | detailed_survey | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Check Survey (Kms) | check_survey | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 73 | 73 | 0 | 0 | 0 | 73 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Foundation (Nos) | foundation | Foundation | TRUE | 513 | 308 | 34 | 6 |  | 314 | 199 | 6.0 | 45.0 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Earthing (Nos) | earthing | Other | FALSE | 513 | 266 |  |  |  | 266 | 247 |  |  | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 513 | 218 | 39 | 5 |  | 223 | 290 | 4.0 | 79.0 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Tack Welding (Nos) | tack_welding | Other | FALSE | 513 | 104 | 153 | 12 | 1 | 116 | 397 | 1.0 | 3.0 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Stringing (Kms) | stringing | Stringing | TRUE | [9 empty] | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 188.678 | 21.797 | 21.084 |  |  | 21.797 | 166.881 | 2.0 | 54.0 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318 |  |  | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | OPGW Stringing (Kms) | opgw_stringing | OPGW Stringing | TRUE | 188.678 | 0 | [7 empty] | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 188.678 |  |  |  |  | 0 | 188.678 |  |  | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-12 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 188.678 |  |  |  |  | 0 | 188.678 |  |  | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-12 | 2026-06-01 | Progress Summary | Route Alignment (Kms) | route_alignment | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-12 | 2026-06-01 | Progress Summary | Detailed Survey (Kms) | detailed_survey | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-12 | 2026-06-01 | Progress Summary | Check Survey (Kms) | check_survey | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-12 | 2026-06-01 | Progress Summary | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 26 | 26 | 0 | 0 | 0 | 26 | 0 |  |  | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-12 | 2026-06-01 | Progress Summary | Foundation (Nos) | foundation | Foundation | TRUE | 43 | 34 | 8 | 1 |  | 35 | 8 | 2.0 | 20.0 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-12 | 2026-06-01 | Progress Summary | Earthing (Nos) | earthing | Other | FALSE | 43 | 3 |  |  | 0 | 3 | 40 |  |  | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-12 | 2026-06-01 | Progress Summary | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 43 | 3 | 12 |  | 0 | 3 | 40 | 1.0 | 24.0 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-12 | 2026-06-01 | Progress Summary | Tack Welding (Nos) | tack_welding | Other | FALSE | 43 |  |  |  |  | 0 | 43 |  |  | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-12 | 2026-06-01 | Progress Summary | Stringing (Kms) | stringing | Stringing | TRUE | [6 empty] | 0 |  |  | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-12 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-12 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-12 | 2026-06-01 | Progress Summary | OPGW Stringing (Kms) | opgw_stringing | OPGW Stringing | TRUE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 605 | TB 605 | tb605 |  | 2026-06-14 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Check Survey | check_survey | Other | FALSE | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3 |  | TB 605 - DPR - 2026-06-14.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-14 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Foundation | foundation | Foundation | TRUE | 523 | 370 | 0 | 21 | 1 | 391 | 132 | 26 |  | TB 605 - DPR - 2026-06-14.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-14 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Earthing | earthing | Other | FALSE | 523 | 308 | 0 | 17 | 0 | 325 | 198 | 0 |  | TB 605 - DPR - 2026-06-14.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-14 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tower Erection | tower_erection | Tower Erection | TRUE | 523 | 203 | 0 | 21 | 0 | 224 | 299 | 12 |  | TB 605 - DPR - 2026-06-14.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-14 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tack welding | tack_welding | Other | FALSE | 523 | 0 | 0 | 0 | 0 | 0 | 523 | 0 |  | TB 605 - DPR - 2026-06-14.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-14 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Stringing | stringing | Stringing | TRUE | 175.719 | 0 | 0 | 0 | 0 | 0 | 175.719 | 2 |  | TB 605 - DPR - 2026-06-14.xlsx | TB-605 | TB-605 | TB 605 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Route Alignment (Km) | route_alignment | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Detailed Survey (Km) | detailed_survey | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Check Survey (Km) | check_survey | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 |  |  |  | 28 | 0 |  |  | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Excavation | excavation | Other | FALSE | 352 | 319 | 31 | 8 |  | 327 | 25 |  |  | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Foundation (Nos.) | foundation | Foundation | TRUE | 352 | 319 | 31 | 9 | 1 | 328 | 24 | 6.0 |  | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Earthing (Nos.) | earthing | Other | FALSE | 352 | 296 | 31 | 28 | 1 | 324 | 28 |  |  | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 352 | 235 | 44 | 17 | 3 | 252 | 100 | 15.0 | 1 gang arrived on 14.06.26 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Tack Welding | tack_welding | Other | FALSE | 352 | 120 | 55 | 40 | 3 | 160 | 192 | 3.0 |  | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Stringing (Km) | stringing | Stringing | TRUE | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438 | 6.0 |  | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Paying Out | paying_out | Other | FALSE | 127.799 | 21.618 | 20 | 1.893 |  | 23.511 | 104.288 |  |  | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Final Sag | final_sag | Other | FALSE | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438 |  |  | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 127.799 | 0 | 20 |  |  | 0 | 127.799 |  |  | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 418 | TA 418 | ta418 |  | 2026-06-15 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-15 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-15 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-15 | 2026-06-01 | Progress Status | Stringing - RS | stringing | Stringing | TRUE | 47.84 | 29.582 | 18.258 | 1.6442 | 2.0953 | 31.2262 | 16.6138 | 4 | *Work Front Required for Hotline Gang | TA 418 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 421 | TA 421 | ta421 |  | 2026-06-11 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-11 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 309 | 303 | 6 | 0 |  | 303 | 6 |  |  | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-11 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-11 | 2026-06-01 | Progress Status | Tackwelding | tack_welding | Other | FALSE | 309 | 283 | 26 |  |  | 283 | 26 | 1.0 |  | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-11 | 2026-06-01 | Progress Status | Tower Tightening | tower_tightening | Other | FALSE | 309 | 309 |  |  |  | 309 | 0 | 2.0 |  | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-11 | 2026-06-01 | Progress Status | Stringing -F/S | stringing | Stringing | TRUE | 121.342 | 115.467 | 5.878 | 0.678 |  | 116.145 | 5.197 | 1.0 | WIP - 33/0- 34/0 | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-11 | 2026-06-01 | Progress Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67 |  |  | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-11 | 2026-06-01 | Progress Status | NH Crossing | nh_crossing | Other | FALSE | 3 | 3 |  |  |  | 3 |  |  |  | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-11 | 2026-06-01 | Progress Status | Power Line Crossing | power_line_crossing | Other | FALSE | 5 | 5 |  |  |  | 5 |  |  |  | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-15 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Detail Survey | detail_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-15.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-15 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Check Survey | check_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-15.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-15 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | FOUNDATION | foundation | Foundation | TRUE | 379 | 375 | 4 | 1 |  | 376 | 4 |  | Earthing-261/376. | TA 505 - DPR - 2026-06-15.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-15 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 162/362, Gangs Engaged-3. | TA 505 - DPR - 2026-06-15.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-15 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Stringing (Final Sag) | stringing | Stringing | TRUE | 139.6 | 15.462 | 23.008 | 4.504 |  | 19.966 | 124.138 |  |  | TA 505 - DPR - 2026-06-15.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: | Route Alignment (Km) | route_alignment | Other | FALSE | 114.516 | 114.516 | 0 |  |  | 114.516 | 0 |  |  | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: | Detailed Survey (Km) | detailed_survey | Other | FALSE | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024 |  |  | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: | Check Survey (Km) | check_survey | Other | FALSE | 114.516 | 93.542 | 0 |  |  | 93.542 | 20.974 |  |  | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 30 | 30 | 0 |  |  | 30 | 0 |  |  | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: | Excavation | excavation | Other | FALSE | 293 | 88 | 16 |  |  | 92 | 201 |  |  | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: | Foundation (Nos.) | foundation | Foundation | TRUE | 293 | 85 | 16 | 7 | 1 | 92 | 201 | 5 |  | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: | Earthing (Nos.) | earthing | Other | FALSE | 293 | 78 | 16 |  |  | 82 | 211 |  |  | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 293 | 40 | 30 | 5 |  | 45 | 248 |  |  | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: | Tack Welding | tack_welding | Other | FALSE | 293 | 13 | 30 |  |  | 13 | 280 |  |  | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: | Paying Out | paying_out | Other | FALSE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: | Final Sag | stringing | Stringing | TRUE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-15 | 2026-06-01 | NOA Ref. No.: | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 114.516 | 0 | 20 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-15 | 2026-06-01 | Office : Hansera, Lunkaransar | Route Alignment (Km) | route_alignment | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-15 | 2026-06-01 | Office : Hansera, Lunkaransar | Detailed Survey (Km) | detailed_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-15 | 2026-06-01 | Office : Hansera, Lunkaransar | Check Survey (Km) | check_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-15 | 2026-06-01 | Office : Hansera, Lunkaransar | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 | 0 | 0 | 0 | 28 | 0 |  |  | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-15 | 2026-06-01 | Office : Hansera, Lunkaransar | Excavation | excavation | Other | FALSE | 319 | 308 | 18 | 4 | 0 | 312 | 7 |  |  | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-15 | 2026-06-01 | Office : Hansera, Lunkaransar | Foundation (Nos.) | foundation | Foundation | TRUE | 319 | 306 | 18 | 4 | 0 | 310 | 9 | 02/20 |  | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-15 | 2026-06-01 | Office : Hansera, Lunkaransar | Earthing (Nos.) | earthing | Other | FALSE | 319 | 269 |  |  |  | 269 | 50 |  |  | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-15 | 2026-06-01 | Office : Hansera, Lunkaransar | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 319 | 221 | 30 | 4 | 1 | 225 | 94 | 06/206 |  | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-15 | 2026-06-01 | Office : Hansera, Lunkaransar | Tack Welding | tack_welding | Other | FALSE | 319 | 79 |  | 15 | 1 | 94 | 225 |  |  | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-15 | 2026-06-01 | Office : Hansera, Lunkaransar | Paying Out | paying_out | Other | FALSE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-15 | 2026-06-01 | Office : Hansera, Lunkaransar | Final Sag | stringing | Stringing | TRUE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-15 | 2026-06-01 | Office : Hansera, Lunkaransar | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 124.568 | 0 | 20 | 0 |  | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 601 | TA 601 | ta601 |  | 2026-06-15 | 2026-06-01 | Foundation Status | Foundation | foundation | Foundation | TRUE | 292 | 124 | 35 | 8 | 1 | 132 | 160 | 7 |  | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-15 | 2026-06-01 | Foundation Status | Earthing | earthing | Other | FALSE | 292 | 102 | 35 | 3 | 0 | 105 | 187 |  |  | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-15 | 2026-06-01 | Foundation Status | Tower Erection | tower_erection | Tower Erection | TRUE | 292 | 71 | 25 | 3 | 0 | 74 | 218 | 7 |  | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-15 | 2026-06-01 | Foundation Status | Stringing -R/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-15 | 2026-06-01 | Foundation Status | Stringing -F/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-15 | 2026-06-01 | Foundation Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-15 | 2026-06-01 | Foundation Status | NH Crossing | nh_crossing | Other | FALSE | 3 | [5 empty] | 3 |  |  | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-15 | 2026-06-01 | Foundation Status | SH Crossing | sh_crossing | Other | FALSE | 1 | [5 empty] | 1 |  |  | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-15 | 2026-06-01 | Foundation Status | Railway crossing | railway_crossing | Other | FALSE | 2 | [5 empty] | 2 |  |  | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-15 | 2026-06-01 | Foundation Status | Power Line Crossing | power_line_crossing | Other | FALSE | 6 | [5 empty] | 6 |  |  | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-15 | 2026-06-01 | Foundation Status | WIP - Foundations | foundation | Foundation | TRUE | [7 empty] | Gang |  | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | ROUTE ALIGNMENT | ROUTE ALIGNMENT | route_alignment | Other | FALSE | 184.986 | 185.149 |  | 0 |  | 185.149 | 0 |  |  | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | SOIL INVESTIGATION | SOIL INVESTIGATION | soil_investigation | Other | FALSE | 31 | 17 |  | 0 |  | 17 | 14 |  |  | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | DETAILED SURVEY | DETAILED SURVEY | detailed_survey | Other | FALSE | 184.986 | 178.3635 |  | 11.83 |  | 178.3635 | 6.6225 |  |  | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | CHECK SURVEY | CHECK SURVEY | check_survey | Other | FALSE | 184.986 | 136.139 |  | 0 |  | 136.139 | 48.847 |  |  | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | FOUNDATION | FOUNDATION | foundation | Foundation | TRUE | 480 | 154 |  | 8 |  | 162 | 318 |  |  | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | EARTHING | EARTHING | earthing | Other | FALSE | 480 | 96 |  | 10 |  | 106 | 374 |  |  | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | TOWER ERECTION | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 480 | 52 |  | 17 |  | 69 | 411 |  |  | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | STRINGING | STRINGING | stringing | Stringing | TRUE | 184.986 | 0 |  | 0 |  | 0 | 184.986 |  |  | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-15 | 2026-06-01 | OPGW STRINGING | OPGW STRINGING | opgw_stringing | OPGW Stringing | TRUE | 184.986 | 0 |  | 0 |  | 0 | 184.986 |  |  | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing
TB 605 | TB 605 | tb605 |  | 2026-06-15 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Check Survey | check_survey | Other | FALSE | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3 |  | TB 605 - DPR - 2026-06-15.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-15 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Foundation | foundation | Foundation | TRUE | 523 | 370 | 0 | 23 | 2 | 393 | 130 | 26 |  | TB 605 - DPR - 2026-06-15.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-15 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Earthing | earthing | Other | FALSE | 523 | 308 | 0 | 23 | 0 | 331 | 192 | 0 |  | TB 605 - DPR - 2026-06-15.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-15 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tower Erection | tower_erection | Tower Erection | TRUE | 523 | 203 | 0 | 23 | 2 | 226 | 297 | 12 |  | TB 605 - DPR - 2026-06-15.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-15 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tack welding | tack_welding | Other | FALSE | 523 | 0 | 0 | 0 | 0 | 0 | 523 | 0 |  | TB 605 - DPR - 2026-06-15.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-15 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Stringing | stringing | Stringing | TRUE | 175.719 | 0 | 0 | 0 | 0 | 0 | 175.719 | 2 |  | TB 605 - DPR - 2026-06-15.xlsx | TB-605 | TB-605 | TB 605 Status
TA 413 | TA 413 | ta413 |  | 2026-06-14 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Detail Survey (Km) | detail_survey_km | Other | FALSE | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-14 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-14 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Check Survey approved(Km) | check_survey | Other | FALSE | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-14 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Excavation | excavation | Other | FALSE | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-14 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Foundation (Nos.) | foundation | Foundation | TRUE | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-14 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Earthing (Nos.) | earthing | Other | FALSE | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-14 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 306 | 302 | 4 | 0 | 0 | 302 | 4 | 1.0 | G_1:- Amit Kumar Singh (WIP 16/0) | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-14 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Tack Welding | tack_welding | Other | FALSE | 306 | 255 | 47 | 10 | 3 | 265 | 41 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-14 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Stringing (Km) | stringing | Stringing | TRUE | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 | 2.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (13/0 to 14/0) | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-14 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Paying Out | paying_out | Other | FALSE | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ROW ) | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-14 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Final Sag | final_sag | Other | FALSE | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 | 1.0 | G_3:- Gopal Associate (AP 24/0 to AP 25/0) | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-14 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889 |  |  | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Route Alignment (Km) | route_alignment | Other | FALSE | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661 |  |  | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Detailed Survey (Km) | detailed_survey | Other | FALSE | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001 |  |  | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Check Survey (Km) | check_survey | Other | FALSE | 122.071 | 122.07 |  |  |  | 1 | 121.071 |  |  | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 31 | 31 | 0 |  |  | 31 |  |  |  | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Excavation (Nos) | excavation | Other | FALSE | 330 | 167 |  |  |  | 167 | 163 |  |  | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Foundation (Nos) | foundation | Foundation | TRUE | 330 | 255 | 49 | 10 |  | 265 | 65 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Earthing (Nos) | earthing | Other | FALSE | 330 | 217 | 50 | 0 |  | 217 | 113 |  |  | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 330 | 207 | 50 | 6 |  | 213 | 117 | 12 | 36/4, 37/0, 38/2, 41/2, 42/0 ,52/1, 54/0, 62/0, 65/0, 65/2, 64/4, 71/0, 76/0 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Tack Welding (Nos) | tack_welding | Other | FALSE | 330 | 35 | 50 |  |  | 35 | 295 | 1 |  | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Stringing (Km) | stringing | Stringing | TRUE | 122.071 |  |  | 0.447 |  |  | 122.071 |  |  | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Paying Out (Km) | paying_out | Other | FALSE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Final Sag (Km) | stringing | Stringing | TRUE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | ` |  | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | OPGW Stringing (Km) | opgw_stringing | OPGW Stringing | TRUE | 122.071 | 0 |  |  |  | 0 | 122.071 |  |  | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-15 | 2026-06-01 | Completed Days | Power Line Crossings | power_line_crossings | Other | FALSE | [9 empty] | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 509 | TA 509 | ta509 |  | 2026-05-31 | 2026-05-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Foundation (Loc) | foundation | Foundation | TRUE | 309 | 258 | 25 | 10 |  | 268 | 41 | 3.0 |  | TA 509 - DPR - 2026-05-31.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 509 | TA 509 | ta509 |  | 2026-05-31 | 2026-05-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Earthing (Loc) | earthing | Other | FALSE | 309 | 228 | 25 | 19 |  | 247 | 62 |  |  | TA 509 - DPR - 2026-05-31.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 509 | TA 509 | ta509 |  | 2026-05-31 | 2026-05-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Erection (Loc) | erection_loc | Other | FALSE | 309 | 180 | 45 | 28 |  | 208 | 101 | 3.0 |  | TA 509 - DPR - 2026-05-31.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 509 | TA 509 | ta509 |  | 2026-05-31 | 2026-05-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Stringing (Km) | stringing | Stringing | TRUE | 118.397 |  |  |  |  | 0 | 118.397 | 0.0 |  | TA 509 - DPR - 2026-05-31.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 504 | TA 504 | ta504 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Detail Survey | detail_survey | Other | FALSE | 69 | 69 |  |  |  | 69 | 0 |  |  | TA 504 - DPR - 2026-06-16.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Check Survey | check_survey | Other | FALSE | 69 | 67 | 2 |  |  | 67 | 2 |  |  | TA 504 - DPR - 2026-06-16.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | FOUNDATION | foundation | Foundation | TRUE | 186 | 144 | 6 | 2 |  | 146 | 42 |  |  | TA 504 - DPR - 2026-06-16.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 186 | 121 | 6 | 1 |  | 122 | 65 |  |  | TA 504 - DPR - 2026-06-16.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Stringing | stringing | Stringing | TRUE | 69 | 13.422 | 8 | 4.407 |  | 17.829 | 55.578 |  |  | TA 504 - DPR - 2026-06-16.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 69 |  |  |  |  | 0 | 69 |  |  | TA 504 - DPR - 2026-06-16.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 506 | TA 506 | ta506 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Detail Survey | detail_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-16.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Check Survey | check_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-16.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | FOUNDATION | foundation | Foundation | TRUE | 602 | 492 | 40 | 3 |  | 495 | 110 |  |  | TA 506 - DPR - 2026-06-16.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 602 | 405 | 25 | 6 |  | 411 | 197 |  |  | TA 506 - DPR - 2026-06-16.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Stringing | stringing | Stringing | TRUE | 223 | 55.632 | 30 | 3.53 |  | 59.162 | 167.368 |  |  | TA 506 - DPR - 2026-06-16.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 231 | [8 empty] | TA 506 - DPR - 2026-06-16.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Route Alignment (Km) | route_alignment | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Detailed Survey (Km) | detailed_survey | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Check Survey (Km) | check_survey | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 |  |  |  | 28 | 0 |  |  | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Excavation | excavation | Other | FALSE | 352 | 319 | 31 | 9 |  | 328 | 24 |  |  | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Foundation (Nos.) | foundation | Foundation | TRUE | 352 | 319 | 31 | 9 |  | 328 | 24 | 6.0 |  | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Earthing (Nos.) | earthing | Other | FALSE | 352 | 296 | 31 | 28 |  | 324 | 28 |  |  | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 352 | 235 | 44 | 18 | 1 | 253 | 99 | 15.0 | 1 gang arrived on 14.06.26 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Tack Welding | tack_welding | Other | FALSE | 352 | 120 | 55 | 41 | 1 | 161 | 191 | 3.0 |  | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Stringing (Km) | stringing | Stringing | TRUE | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438 | 6.0 |  | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Paying Out | paying_out | Other | FALSE | 127.799 | 21.618 | 20 | 1.893 |  | 23.511 | 104.288 |  |  | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Final Sag | final_sag | Other | FALSE | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438 |  |  | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 127.799 | 0 | 20 |  |  | 0 | 127.799 |  |  | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 416 | TA 416 | ta416 |  | 2026-06-15 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0 |  | TA 416 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 416 | TA 416 | ta416 |  | 2026-06-15 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0 |  | TA 416 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 416 | TA 416 | ta416 |  | 2026-06-15 | 2026-06-01 | Progress Status | Erection | tower_erection | Tower Erection | TRUE | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0 |  | TA 416 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 416 | TA 416 | ta416 |  | 2026-06-15 | 2026-06-01 | Progress Status | Stringing | stringing | Stringing | TRUE | 115.134 | 111.1 | 4 | 0.807 | 0 | 111.94 | 3.194 | 5 |  | TA 416 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 418 | TA 418 | ta418 |  | 2026-06-16 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-16.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-16 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-16.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-16 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-16.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-16 | 2026-06-01 | Progress Status | Stringing - RS | stringing | Stringing | TRUE | 47.84 | 29.582 | 18.258 | 1.6442 | 2.0953 | 31.2262 | 16.6138 | 4 | *Work Front Required for Hotline Gang | TA 418 - DPR - 2026-06-16.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Route Alignment (Km) | route_alignment | Other | FALSE | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661 |  |  | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Detailed Survey (Km) | detailed_survey | Other | FALSE | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001 |  |  | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Check Survey (Km) | check_survey | Other | FALSE | 122.071 | 122.07 |  |  |  | 1 | 121.071 |  |  | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 31 | 31 | 0 |  |  | 31 |  |  |  | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Excavation (Nos) | excavation | Other | FALSE | 330 | 167 |  |  |  | 167 | 163 |  |  | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Foundation (Nos) | foundation | Foundation | TRUE | 330 | 255 | 49 | 10 |  | 265 | 65 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Earthing (Nos) | earthing | Other | FALSE | 330 | 217 | 50 | 0 |  | 217 | 113 |  |  | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 330 | 207 | 50 | 7 |  | 214 | 116 | 12 | 36/4, 37/0, 38/2, 41/2 ,52/1, 54/0, 62/0, 65/0, 65/2, 64/4, 71/0, 76/0 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Tack Welding (Nos) | tack_welding | Other | FALSE | 330 | 35 | 50 |  |  | 35 | 295 | 1 |  | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Stringing (Km) | stringing | Stringing | TRUE | 122.071 |  |  | 0.447 |  |  | 122.071 |  |  | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Paying Out (Km) | paying_out | Other | FALSE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Final Sag (Km) | stringing | Stringing | TRUE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | ` |  | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | OPGW Stringing (Km) | opgw_stringing | OPGW Stringing | TRUE | 122.071 | 0 |  |  |  | 0 | 122.071 |  |  | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-16 | 2026-06-01 | Completed Days | Power Line Crossings | power_line_crossings | Other | FALSE | [9 empty] | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 421 | TA 421 | ta421 |  | 2026-06-16 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-16 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 309 | 303 | 6 | 0 |  | 303 | 6 |  |  | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-16 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-16 | 2026-06-01 | Progress Status | Tackwelding | tack_welding | Other | FALSE | 309 | 283 | 26 | 13 |  | 296 | 13 | 1.0 |  | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-16 | 2026-06-01 | Progress Status | Tower Tightening | tower_tightening | Other | FALSE | 309 | 309 |  |  |  | 309 | 0 | 2.0 |  | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-16 | 2026-06-01 | Progress Status | Stringing -F/S | stringing | Stringing | TRUE | 121.342 | 115.467 | 5.878 | 1.644 |  | 117.111 | 4.231 | 1.0 | 43A/0 - 43A/1 - WIP | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-16 | 2026-06-01 | Progress Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67 |  |  | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-16 | 2026-06-01 | Progress Status | NH Crossing | nh_crossing | Other | FALSE | 3 | 3 |  |  |  | 3 |  |  |  | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-16 | 2026-06-01 | Progress Status | Power Line Crossing | power_line_crossing | Other | FALSE | 5 | 5 |  |  |  | 5 |  |  |  | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: | Route Alignment (Km) | route_alignment | Other | FALSE | 114.516 | 114.516 | 0 |  |  | 114.516 | 0 |  |  | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: | Detailed Survey (Km) | detailed_survey | Other | FALSE | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024 |  |  | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: | Check Survey (Km) | check_survey | Other | FALSE | 114.516 | 93.542 | 0 |  |  | 93.542 | 20.974 |  |  | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 30 | 30 | 0 |  |  | 30 | 0 |  |  | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: | Excavation | excavation | Other | FALSE | 293 | 88 | 16 |  |  | 92 | 201 |  |  | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: | Foundation (Nos.) | foundation | Foundation | TRUE | 293 | 85 | 16 | 7 |  | 92 | 201 | 5 |  | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: | Earthing (Nos.) | earthing | Other | FALSE | 293 | 78 | 16 | 7 | 1 | 85 | 208 |  |  | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 293 | 40 | 30 | 5 |  | 45 | 248 |  |  | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: | Tack Welding | tack_welding | Other | FALSE | 293 | 13 | 30 |  |  | 13 | 280 |  |  | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: | Paying Out | paying_out | Other | FALSE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: | Final Sag | stringing | Stringing | TRUE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-16 | 2026-06-01 | NOA Ref. No.: | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 114.516 | 0 | 20 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-16 | 2026-06-01 | Office : Hansera, Lunkaransar | Route Alignment (Km) | route_alignment | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-16 | 2026-06-01 | Office : Hansera, Lunkaransar | Detailed Survey (Km) | detailed_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-16 | 2026-06-01 | Office : Hansera, Lunkaransar | Check Survey (Km) | check_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-16 | 2026-06-01 | Office : Hansera, Lunkaransar | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 | 0 | 0 | 0 | 28 | 0 |  |  | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-16 | 2026-06-01 | Office : Hansera, Lunkaransar | Excavation | excavation | Other | FALSE | 319 | 308 | 18 | 4 | 0 | 312 | 7 |  |  | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-16 | 2026-06-01 | Office : Hansera, Lunkaransar | Foundation (Nos.) | foundation | Foundation | TRUE | 319 | 306 | 18 | 4 | 0 | 310 | 9 | 02/18 |  | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-16 | 2026-06-01 | Office : Hansera, Lunkaransar | Earthing (Nos.) | earthing | Other | FALSE | 319 | 269 |  |  |  | 269 | 50 |  |  | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-16 | 2026-06-01 | Office : Hansera, Lunkaransar | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 319 | 221 | 30 | 5 | 0 | 226 | 93 | 06/195 |  | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-16 | 2026-06-01 | Office : Hansera, Lunkaransar | Tack Welding | tack_welding | Other | FALSE | 319 | 79 |  | 17 | 2 | 96 | 223 |  |  | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-16 | 2026-06-01 | Office : Hansera, Lunkaransar | Paying Out | paying_out | Other | FALSE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-16 | 2026-06-01 | Office : Hansera, Lunkaransar | Final Sag | stringing | Stringing | TRUE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-16 | 2026-06-01 | Office : Hansera, Lunkaransar | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 124.568 | 0 | 20 | 0 |  | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026) | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 399 | 64 | 25 | 6 |  | 70 | 329 | 4 | Loc-51/1-Casting WIP Loc-62/0-3Pit Casting compl(ROW) Loc-61/1-Casting WIP Loc-74/6-Excavation (ROW) Loc-54/2-Boring & Dewatering WIP. | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 399 | 7 |  |  |  | 7 | 392 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 399 | 24 | 11 | 2 |  | 26 | 373 | 2 | Loc-56/3-Material Shifting U/P | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 399 | 0 |  |  |  | 0 | 399 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 147.584 | 0 |  |  |  |  | 147.584 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 82.803 | 82.803 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.796 |  |  |  | 82.796 | 0.007 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025) | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 220 | 25 | 10 | 1 |  | 26 | 194 | 1 |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 220 | 10 |  |  | 0 | 10 | 210 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 220 | 7 | 5 |  |  | 7 | 213 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 220 |  |  |  |  | 0 | 220 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 82.803 | [5 empty] | 82.803 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-15 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status
TA 601 | TA 601 | ta601 |  | 2026-06-16 | 2026-06-01 | Foundation Status | Foundation | foundation | Foundation | TRUE | 292 | 124 | 35 | 8 | 0 | 132 | 160 | 7 |  | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-16 | 2026-06-01 | Foundation Status | Earthing | earthing | Other | FALSE | 292 | 102 | 35 | 3 | 0 | 105 | 187 |  |  | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-16 | 2026-06-01 | Foundation Status | Tower Erection | tower_erection | Tower Erection | TRUE | 292 | 71 | 25 | 4 | 1 | 75 | 217 | 7 |  | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-16 | 2026-06-01 | Foundation Status | Stringing -R/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-16 | 2026-06-01 | Foundation Status | Stringing -F/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-16 | 2026-06-01 | Foundation Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-16 | 2026-06-01 | Foundation Status | NH Crossing | nh_crossing | Other | FALSE | 3 | [5 empty] | 3 |  |  | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-16 | 2026-06-01 | Foundation Status | SH Crossing | sh_crossing | Other | FALSE | 1 | [5 empty] | 1 |  |  | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-16 | 2026-06-01 | Foundation Status | Railway crossing | railway_crossing | Other | FALSE | 2 | [5 empty] | 2 |  |  | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-16 | 2026-06-01 | Foundation Status | Power Line Crossing | power_line_crossing | Other | FALSE | 6 | [5 empty] | 6 |  |  | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-16 | 2026-06-01 | Foundation Status | WIP - Foundations | foundation | Foundation | TRUE | [7 empty] | Gang |  | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-15 | 2026-06-01 | 220kV Line | Detailed Survey | detailed_survey | Other | FALSE | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0 |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-15 | 2026-06-01 | 220kV Line | Check Survey | check_survey | Other | FALSE | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 |  |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-15 | 2026-06-01 | 220kV Line | Foundation | foundation | Foundation | TRUE | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-15 | 2026-06-01 | 220kV Line | Earthing | earthing | Other | FALSE | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-15 | 2026-06-01 | 220kV Line | Tower Erection | tower_erection | Tower Erection | TRUE | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0 |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-15 | 2026-06-01 | 220kV Line | Tack Welding | tack_welding | Other | FALSE | 199 | 195 | 4 | 0 | 0 | 195 | 4 | 0.0 |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-15 | 2026-06-01 | 220kV Line | Paying Out | paying_out | Other | FALSE | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 | 0.0 |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-15 | 2026-06-01 | 220kV Line | Final Sag | stringing | Stringing | TRUE | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 |  |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-15 | 2026-06-01 | 220kV Line | OPGW | opgw_stringing | OPGW Stringing | TRUE | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0 |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-15 | 2026-06-01 | 132kV Line | Detailed Survey | detailed_survey | Other | FALSE | 9 | 9 |  | 0 | 0 | 9 | 0 |  |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-15 | 2026-06-01 | 132kV Line | Check Survey | check_survey | Other | FALSE | 9 | 9 |  | 0 | 0 | 9 | 0 |  |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-15 | 2026-06-01 | 132kV Line | Foundation | foundation | Foundation | TRUE | 39 | 36 | 5 | 1 | 0 | 37 | 2 | 1.0 | SC-2 Foundation pit-B,C &D steel binding wip | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-15 | 2026-06-01 | 132kV Line | Earthing | earthing | Other | FALSE | 39 | 34 | 5 | 2 | 0 | 36 | 3 | 1.0 |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-15 | 2026-06-01 | 132kV Line | Tower Erection | tower_erection | Tower Erection | TRUE | 39 | 31 | 5 | 1 | 0 | 32 | 7 | 1.0 | 2/1 Erection Tighting wip and one side insulator hosting done | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-15 | 2026-06-01 | 132kV Line | Tack Welding | tack_welding | Other | FALSE | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0 |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-15 | 2026-06-01 | 132kV Line | Paying Out | paying_out | Other | FALSE | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0 |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-15 | 2026-06-01 | 132kV Line | Final Sag | stringing | Stringing | TRUE | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 |  |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-15 | 2026-06-01 | 132kV Line | OPGW | opgw_stringing | OPGW Stringing | TRUE | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0 |  | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Route Alignment | route_alignment | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Route Alignment - Main Line | route_alignment | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Route Alignment - Loop In | route_alignment | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Route Alignment - Loop Out | route_alignment | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Detail Survey | detail_survey | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Detailed Survey - Main Line | detailed_survey | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Detailed Survey - Loop In | detailed_survey | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Detailed Survey - Loop Out | detailed_survey | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Check Survey | check_survey | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Check Survey - Main Line | check_survey | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Check Survey - Loop In | check_survey | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Check Survey - Loop Out | check_survey | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Normal Open Cast Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Normal Foundation - Main Line | foundation | Foundation | TRUE | 266 | 131 | 8 | 2 | 0 | 133 | 133 | 6.0 |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Normal Foundation - Loop In (Incld. Stone Column) | foundation | Foundation | TRUE | 20 | 0 | 0 | 0 | 0 | 0 | 20 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | Foundation | TRUE | 15 | 1 | 0 | 0 | 0 | 1 | 14 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Pile Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Pile Foundation_River_Main Line | foundation | Foundation | TRUE | 2 | 1 | 0 | 0 | 0 | 1 | 1 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Pile Foundation_Non River_Loop In | foundation | Foundation | TRUE | 7 | 7 | 0 | 0 | 0 | 7 | 0 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Pile Foundation_Non River_Loop Out | foundation | Foundation | TRUE | 8 | 6 | 0 | 0 | 0 | 6 | 2 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Pile Cap Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Earthing | earthing | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Erection | tower_erection | Tower Erection | TRUE | [9 empty] | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Tower Erection - Main Line | tower_erection | Tower Erection | TRUE | 268 | 31 | 20 | 4 | 2 | 35 | 233 | 7.0 |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Tower Erection - loop In | tower_erection | Tower Erection | TRUE | 27 | 0 | 0 | 0 | 0 | 0 | 27 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Tower Erection - Loop Out | tower_erection | Tower Erection | TRUE | 23 | 0 | 0 | 1 | 0 | 1 | 22 | 1.0 |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Tack welding | tack_welding | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Tack welding - Main Line | tack_welding | Other | FALSE | 268 | 0 | 0 | 0 | 0 | 0 | 268 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Tack welding - Loop In | tack_welding | Other | FALSE | 27 | 0 | 0 | 0 | 0 | 0 | 27 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Tack welding - Loop Out | tack_welding | Other | FALSE | 23 | 0 | 0 | 0 | 0 | 0 | 23 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Final Sag - Main Line | stringing | Stringing | TRUE | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Final Sag - Loop In | stringing | Stringing | TRUE | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | Final Sag - Loop Out | stringing | Stringing | TRUE | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | [9 empty] | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | OPGW Stringing - Main Line | opgw_stringing | OPGW Stringing | TRUE | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | OPGW Stringing - Loop In | opgw_stringing | OPGW Stringing | TRUE | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-14 | 2026-06-01 | LOA | OPGW Stringing - Loop Out | opgw_stringing | OPGW Stringing | TRUE | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134 |  |  | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Detail Survey | detail_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-16.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Check Survey | check_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-16.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | FOUNDATION | foundation | Foundation | TRUE | 379 | 375 | 4 | 1 |  | 376 | 4 |  | Earthing-261/376. | TA 505 - DPR - 2026-06-16.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 162/362, Gangs Engaged-3. | TA 505 - DPR - 2026-06-16.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-16 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Stringing (Final Sag) | stringing | Stringing | TRUE | 139.6 | 15.462 | 23.008 | 8.364 |  | 23.826 | 124.138 |  |  | TA 505 - DPR - 2026-06-16.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 509 | TA 509 | ta509 |  | 2026-06-16 | 2026-06-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Foundation (Loc) | foundation | Foundation | TRUE | 309 | 268 | 13 | 4 |  | 272 | 37 | 2.0 |  | TA 509 - DPR - 2026-06-16.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 509 | TA 509 | ta509 |  | 2026-06-16 | 2026-06-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Earthing (Loc) | earthing | Other | FALSE | 309 | 247 | 20 | 1 |  | 248 | 61 |  |  | TA 509 - DPR - 2026-06-16.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 509 | TA 509 | ta509 |  | 2026-06-16 | 2026-06-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Erection (Loc) | tower_erection | Tower Erection | TRUE | 309 | 208 | 30 | 7 |  | 215 | 94 | 5.0 |  | TA 509 - DPR - 2026-06-16.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 509 | TA 509 | ta509 |  | 2026-06-16 | 2026-06-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Stringing (Km) | stringing | Stringing | TRUE | 119.178 |  |  |  |  | 0 | 119.178 | 1.0 |  | TA 509 - DPR - 2026-06-16.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 602 | TA 602 | ta602 |  | 2026-06-16 | 2026-06-01 | Progress Status | Soil Investigation | soil_investigation | Other | FALSE | 31 | 16 | 0 |  |  | 17 | 14 |  |  | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-16 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 480 | 154 | 30 | 8 | 0 | 162 | 318 | 3.0 |  | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-16 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 480 | 96 | 30 | 10 | 0 | 106 | 374 |  |  | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-16 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 480 | 52 | 35 | 17 | 2 | 69 | 411 | 4.0 |  | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-16 | 2026-06-01 | Progress Status | Tack welding | tack_welding | Other | FALSE | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0 |  | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-16 | 2026-06-01 | Progress Status | Stringing(Km) | stringing | Stringing | TRUE | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0 |  | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Route Alignment (Kms) | route_alignment | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Detailed Survey (Kms) | detailed_survey | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Check Survey (Kms) | check_survey | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 73 | 73 | 0 | 0 | 0 | 73 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Foundation (Nos) | foundation | Foundation | TRUE | 513 | 308 | 34 | 8 | 2 | 316 | 197 | 4.0 | 45.0 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Earthing (Nos) | earthing | Other | FALSE | 513 | 266 |  |  |  | 266 | 247 |  |  | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 513 | 218 | 39 | 7 | 1 | 225 | 288 | 5.0 | 79.0 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Tack Welding (Nos) | tack_welding | Other | FALSE | 513 | 104 | 153 | 12 | 1 | 116 | 397 | 1.0 | 3.0 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Stringing (Kms) | stringing | Stringing | TRUE | [9 empty] | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 188.678 | 21.797 | 21.084 |  |  | 21.797 | 166.881 | 2.0 | 54.0 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318 |  |  | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | OPGW Stringing (Kms) | opgw_stringing | OPGW Stringing | TRUE | 188.678 | 0 | [7 empty] | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 188.678 |  |  |  |  | 0 | 188.678 |  |  | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-15 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 188.678 |  |  |  |  | 0 | 188.678 |  |  | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-15 | 2026-06-01 | Progress Summary | Route Alignment (Kms) | route_alignment | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-15 | 2026-06-01 | Progress Summary | Detailed Survey (Kms) | detailed_survey | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-15 | 2026-06-01 | Progress Summary | Check Survey (Kms) | check_survey | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-15 | 2026-06-01 | Progress Summary | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 26 | 26 | 0 | 0 | 0 | 26 | 0 |  |  | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-15 | 2026-06-01 | Progress Summary | Foundation (Nos) | foundation | Foundation | TRUE | 43 | 34 | 8 | 2 | 1 | 36 | 7 | 2.0 | 20.0 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-15 | 2026-06-01 | Progress Summary | Earthing (Nos) | earthing | Other | FALSE | 43 | 3 |  |  | 0 | 3 | 40 |  |  | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-15 | 2026-06-01 | Progress Summary | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 43 | 3 | 12 |  | 0 | 3 | 40 | 1.0 | 24.0 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-15 | 2026-06-01 | Progress Summary | Tack Welding (Nos) | tack_welding | Other | FALSE | 43 |  |  |  |  | 0 | 43 |  |  | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-15 | 2026-06-01 | Progress Summary | Stringing (Kms) | stringing | Stringing | TRUE | [6 empty] | 0 |  |  | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-15 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-15 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-15 | 2026-06-01 | Progress Summary | OPGW Stringing (Kms) | opgw_stringing | OPGW Stringing | TRUE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 605 | TB 605 | tb605 |  | 2026-06-16 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Check Survey | check_survey | Other | FALSE | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3 |  | TB 605 - DPR - 2026-06-16.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-16 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Foundation | foundation | Foundation | TRUE | 523 | 370 | 65 | 23 | 0 | 393 | 130 | 26 |  | TB 605 - DPR - 2026-06-16.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-16 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Earthing | earthing | Other | FALSE | 523 | 308 | 65 | 34 | 0 | 342 | 181 | 0 |  | TB 605 - DPR - 2026-06-16.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-16 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tower Erection | tower_erection | Tower Erection | TRUE | 523 | 203 | 60 | 24 | 1 | 227 | 296 | 12 |  | TB 605 - DPR - 2026-06-16.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-16 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tack welding | tack_welding | Other | FALSE | 523 | 0 | 60 | 0 | 0 | 0 | 523 | 0 |  | TB 605 - DPR - 2026-06-16.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-16 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Stringing | stringing | Stringing | TRUE | 175.719 | 0 | 11.63 | 0 | 0 | 0 | 175.719 | 2 |  | TB 605 - DPR - 2026-06-16.xlsx | TB-605 | TB-605 | TB 605 Status
TA 504 | TA 504 | ta504 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Detail Survey | detail_survey | Other | FALSE | 69 | 69 |  |  |  | 69 | 0 |  |  | TA 504 - DPR - 2026-06-17.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Check Survey | check_survey | Other | FALSE | 69 | 67 | 2 |  |  | 67 | 2 |  |  | TA 504 - DPR - 2026-06-17.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | FOUNDATION | foundation | Foundation | TRUE | 186 | 144 | 6 | 2 |  | 146 | 42 |  |  | TA 504 - DPR - 2026-06-17.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 186 | 121 | 6 | 1 |  | 122 | 65 |  |  | TA 504 - DPR - 2026-06-17.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Stringing | stringing | Stringing | TRUE | 69 | 13.422 | 8 | 4.407 |  | 17.829 | 55.578 |  |  | TA 504 - DPR - 2026-06-17.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 69 |  |  |  |  | 0 | 69 |  |  | TA 504 - DPR - 2026-06-17.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 506 | TA 506 | ta506 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Detail Survey | detail_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-17.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Check Survey | check_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-17.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | FOUNDATION | foundation | Foundation | TRUE | 602 | 492 | 40 | 3 |  | 495 | 110 |  |  | TA 506 - DPR - 2026-06-17.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 602 | 405 | 25 | 6 |  | 411 | 197 |  |  | TA 506 - DPR - 2026-06-17.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Stringing | stringing | Stringing | TRUE | 223 | 55.632 | 30 | 3.53 |  | 59.162 | 167.368 |  |  | TA 506 - DPR - 2026-06-17.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 231 | [8 empty] | TA 506 - DPR - 2026-06-17.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 421 | TA 421 | ta421 |  | 2026-06-17 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-17 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 309 | 303 | 6 | 0 |  | 303 | 6 |  |  | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-17 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-17 | 2026-06-01 | Progress Status | Tackwelding | tack_welding | Other | FALSE | 309 | 283 | 26 | 13 |  | 296 | 13 | 1.0 |  | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-17 | 2026-06-01 | Progress Status | Tower Tightening | tower_tightening | Other | FALSE | 309 | 309 |  |  |  | 309 | 0 | 2.0 |  | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-17 | 2026-06-01 | Progress Status | Stringing -F/S | stringing | Stringing | TRUE | 121.342 | 115.467 | 5.878 | 1.644 |  | 117.111 | 4.231 | 1.0 | 43A/0 - 43A/1 - WIP | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-17 | 2026-06-01 | Progress Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67 |  |  | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-17 | 2026-06-01 | Progress Status | NH Crossing | nh_crossing | Other | FALSE | 3 | 3 |  |  |  | 3 |  |  |  | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-17 | 2026-06-01 | Progress Status | Power Line Crossing | power_line_crossing | Other | FALSE | 5 | 5 |  |  |  | 5 |  |  |  | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: | Route Alignment (Km) | route_alignment | Other | FALSE | 114.516 | 114.516 | 0 |  |  | 114.516 | 0 |  |  | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: | Detailed Survey (Km) | detailed_survey | Other | FALSE | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024 |  |  | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: | Check Survey (Km) | check_survey | Other | FALSE | 114.516 | 98.032 | 0 |  |  | 98.032 | 16.484 |  |  | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 30 | 30 | 0 |  |  | 30 | 0 |  |  | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: | Excavation | excavation | Other | FALSE | 293 | 88 | 16 |  |  | 92 | 201 |  |  | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: | Foundation (Nos.) | foundation | Foundation | TRUE | 293 | 85 | 16 | 7 |  | 92 | 201 | 5 |  | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: | Earthing (Nos.) | earthing | Other | FALSE | 293 | 78 | 16 | 7 |  | 85 | 208 |  |  | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 293 | 40 | 30 | 5 |  | 45 | 248 |  |  | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: | Tack Welding | tack_welding | Other | FALSE | 293 | 13 | 30 |  |  | 13 | 280 |  |  | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: | Paying Out | paying_out | Other | FALSE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: | Final Sag | stringing | Stringing | TRUE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-17 | 2026-06-01 | NOA Ref. No.: | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 114.516 | 0 | 20 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-17 | 2026-06-01 | Office : Hansera, Lunkaransar | Route Alignment (Km) | route_alignment | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-17 | 2026-06-01 | Office : Hansera, Lunkaransar | Detailed Survey (Km) | detailed_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-17 | 2026-06-01 | Office : Hansera, Lunkaransar | Check Survey (Km) | check_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-17 | 2026-06-01 | Office : Hansera, Lunkaransar | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 | 0 | 0 | 0 | 28 | 0 |  |  | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-17 | 2026-06-01 | Office : Hansera, Lunkaransar | Excavation | excavation | Other | FALSE | 319 | 308 | 18 | 4 | 0 | 312 | 7 |  |  | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-17 | 2026-06-01 | Office : Hansera, Lunkaransar | Foundation (Nos.) | foundation | Foundation | TRUE | 319 | 306 | 18 | 4 | 0 | 310 | 9 | 02/18 |  | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-17 | 2026-06-01 | Office : Hansera, Lunkaransar | Earthing (Nos.) | earthing | Other | FALSE | 319 | 269 |  |  |  | 269 | 50 |  |  | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-17 | 2026-06-01 | Office : Hansera, Lunkaransar | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 319 | 221 | 30 | 5 | 0 | 226 | 93 | 07/220 |  | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-17 | 2026-06-01 | Office : Hansera, Lunkaransar | Tack Welding | tack_welding | Other | FALSE | 319 | 79 |  | 19 | 2 | 98 | 221 |  |  | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-17 | 2026-06-01 | Office : Hansera, Lunkaransar | Paying Out | paying_out | Other | FALSE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-17 | 2026-06-01 | Office : Hansera, Lunkaransar | Final Sag | stringing | Stringing | TRUE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-17 | 2026-06-01 | Office : Hansera, Lunkaransar | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 124.568 | 0 | 20 | 0 |  | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026) | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 399 | 64 | 25 | 7 | 1 | 71 | 328 | 4 | Loc-51/1-Casting compl Loc-62/0-3Pit Casting compl(ROW) Loc-61/1-Casting WIP Loc-74/6-Excavation (ROW) Loc-54/2-Boring & Dewatering WIP. | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 399 | 7 |  |  |  | 7 | 392 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 399 | 24 | 11 | 3 | 1 | 27 | 372 | 2 | Loc-56/3-Tower Erection completed | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 399 | 0 |  |  |  | 0 | 399 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 147.584 | 0 |  |  |  |  | 147.584 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 82.803 | 82.803 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.796 |  |  |  | 82.796 | 0.007 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025) | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 220 | 25 | 10 | 1 |  | 26 | 194 | 1 |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 220 | 10 |  |  | 0 | 10 | 210 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 220 | 7 | 5 |  |  | 7 | 213 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 220 |  |  |  |  | 0 | 220 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 82.803 | [5 empty] | 82.803 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-17 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status
TA 601 | TA 601 | ta601 |  | 2026-06-17 | 2026-06-01 | Foundation Status | Foundation | foundation | Foundation | TRUE | 292 | 124 | 35 | 9 | 1 | 133 | 159 | 7 |  | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-17 | 2026-06-01 | Foundation Status | Earthing | earthing | Other | FALSE | 292 | 102 | 35 | 3 | 0 | 105 | 187 |  |  | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-17 | 2026-06-01 | Foundation Status | Tower Erection | tower_erection | Tower Erection | TRUE | 292 | 71 | 25 | 4 | 0 | 75 | 217 | 7 |  | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-17 | 2026-06-01 | Foundation Status | Stringing -R/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-17 | 2026-06-01 | Foundation Status | Stringing -F/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-17 | 2026-06-01 | Foundation Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-17 | 2026-06-01 | Foundation Status | NH Crossing | nh_crossing | Other | FALSE | 3 | [5 empty] | 3 |  |  | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-17 | 2026-06-01 | Foundation Status | SH Crossing | sh_crossing | Other | FALSE | 1 | [5 empty] | 1 |  |  | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-17 | 2026-06-01 | Foundation Status | Railway crossing | railway_crossing | Other | FALSE | 2 | [5 empty] | 2 |  |  | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-17 | 2026-06-01 | Foundation Status | Power Line Crossing | power_line_crossing | Other | FALSE | 6 | [5 empty] | 6 |  |  | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-17 | 2026-06-01 | Foundation Status | WIP - Foundations | foundation | Foundation | TRUE | [7 empty] | Gang |  | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 602 | TA 602 | ta602 |  | 2026-06-17 | 2026-06-01 | Progress Status | Soil Investigation | soil_investigation | Other | FALSE | 31 | 16 | 0 |  |  | 17 | 14 |  |  | TA 602 - DPR - 2026-06-17.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-17 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 480 | 154 | 30 | 8 | 0 | 162 | 318 | 3.0 |  | TA 602 - DPR - 2026-06-17.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-17 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 480 | 96 | 30 | 10 | 0 | 106 | 374 |  |  | TA 602 - DPR - 2026-06-17.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-17 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 480 | 52 | 35 | 18 | 2 | 70 | 410 | 4.0 |  | TA 602 - DPR - 2026-06-17.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-17 | 2026-06-01 | Progress Status | Tack welding | tack_welding | Other | FALSE | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0 |  | TA 602 - DPR - 2026-06-17.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-17 | 2026-06-01 | Progress Status | Stringing(Km) | stringing | Stringing | TRUE | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0 |  | TA 602 - DPR - 2026-06-17.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-17 | 2026-06-01 | 220kV Line | Detailed Survey | detailed_survey | Other | FALSE | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0 |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-17 | 2026-06-01 | 220kV Line | Check Survey | check_survey | Other | FALSE | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 |  |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-17 | 2026-06-01 | 220kV Line | Foundation | foundation | Foundation | TRUE | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-17 | 2026-06-01 | 220kV Line | Earthing | earthing | Other | FALSE | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-17 | 2026-06-01 | 220kV Line | Tower Erection | tower_erection | Tower Erection | TRUE | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0 |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-17 | 2026-06-01 | 220kV Line | Tack Welding | tack_welding | Other | FALSE | 199 | 195 | 4 | 0 | 0 | 195 | 4 | 0.0 |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-17 | 2026-06-01 | 220kV Line | Paying Out | paying_out | Other | FALSE | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 | 0.0 |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-17 | 2026-06-01 | 220kV Line | Final Sag | stringing | Stringing | TRUE | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 |  |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-17 | 2026-06-01 | 220kV Line | OPGW | opgw_stringing | OPGW Stringing | TRUE | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0 |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-17 | 2026-06-01 | 132kV Line | Detailed Survey | detailed_survey | Other | FALSE | 9 | 9 |  | 0 | 0 | 9 | 0 |  |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-17 | 2026-06-01 | 132kV Line | Check Survey | check_survey | Other | FALSE | 9 | 9 |  | 0 | 0 | 9 | 0 |  |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-17 | 2026-06-01 | 132kV Line | Foundation | foundation | Foundation | TRUE | 39 | 36 | 5 | 1 | 0 | 37 | 2 | 1.0 | SC-2 Foundation pit-A,B,C &D steel binding done | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-17 | 2026-06-01 | 132kV Line | Earthing | earthing | Other | FALSE | 39 | 34 | 5 | 2 | 0 | 36 | 3 | 1.0 |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-17 | 2026-06-01 | 132kV Line | Tower Erection | tower_erection | Tower Erection | TRUE | 39 | 31 | 5 | 1 | 0 | 32 | 7 | 1.0 | 2/0 Erection wip | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-17 | 2026-06-01 | 132kV Line | Tack Welding | tack_welding | Other | FALSE | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0 |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-17 | 2026-06-01 | 132kV Line | Paying Out | paying_out | Other | FALSE | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0 |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-17 | 2026-06-01 | 132kV Line | Final Sag | stringing | Stringing | TRUE | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 |  |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-17 | 2026-06-01 | 132kV Line | OPGW | opgw_stringing | OPGW Stringing | TRUE | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0 |  | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Route Alignment (Km) | route_alignment | Other | FALSE | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661 |  |  | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Detailed Survey (Km) | detailed_survey | Other | FALSE | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001 |  |  | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Check Survey (Km) | check_survey | Other | FALSE | 122.071 | 122.07 |  |  |  | 1 | 121.071 |  |  | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 31 | 31 | 0 |  |  | 31 |  |  |  | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Excavation (Nos) | excavation | Other | FALSE | 330 | 167 |  |  |  | 167 | 163 |  |  | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Foundation (Nos) | foundation | Foundation | TRUE | 330 | 255 | 49 | 10 |  | 265 | 65 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Earthing (Nos) | earthing | Other | FALSE | 330 | 217 | 50 | 0 |  | 217 | 113 |  |  | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 330 | 207 | 50 | 7 |  | 214 | 116 | 12 | 36/4, 37/0, 38/2, 41/2 ,52/1, 54/0, 62/0, 65/0, 65/2, 64/4, 71/0, 76/0 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Tack Welding (Nos) | tack_welding | Other | FALSE | 330 | 35 | 50 |  |  | 35 | 295 | 1 |  | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Stringing (Km) | stringing | Stringing | TRUE | 122.071 |  |  | 0.447 |  |  | 122.071 |  |  | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Paying Out (Km) | paying_out | Other | FALSE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Final Sag (Km) | stringing | Stringing | TRUE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | ` |  | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | OPGW Stringing (Km) | opgw_stringing | OPGW Stringing | TRUE | 122.071 | 0 |  |  |  | 0 | 122.071 |  |  | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-17 | 2026-06-01 | Completed Days | Power Line Crossings | power_line_crossings | Other | FALSE | [9 empty] | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 505 | TA 505 | ta505 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Detail Survey | detail_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-17.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Check Survey | check_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-17.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | FOUNDATION | foundation | Foundation | TRUE | 379 | 375 | 4 | 1 |  | 376 | 4 |  | Earthing-261/376. | TA 505 - DPR - 2026-06-17.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 162/362, Gangs Engaged-3. | TA 505 - DPR - 2026-06-17.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-17 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Stringing (Final Sag) | stringing | Stringing | TRUE | 139.6 | 15.462 | 23.008 | 8.364 |  | 23.826 | 124.138 |  |  | TA 505 - DPR - 2026-06-17.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 509 | TA 509 | ta509 |  | 2026-06-17 | 2026-06-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Foundation (Loc) | foundation | Foundation | TRUE | 309 | 268 | 13 | 4 |  | 272 | 37 | 2.0 |  | TA 509 - DPR - 2026-06-17.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 509 | TA 509 | ta509 |  | 2026-06-17 | 2026-06-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Earthing (Loc) | earthing | Other | FALSE | 309 | 247 | 20 | 1 |  | 248 | 61 |  |  | TA 509 - DPR - 2026-06-17.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 509 | TA 509 | ta509 |  | 2026-06-17 | 2026-06-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Erection (Loc) | tower_erection | Tower Erection | TRUE | 309 | 208 | 30 | 7 |  | 215 | 94 | 5.0 |  | TA 509 - DPR - 2026-06-17.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 509 | TA 509 | ta509 |  | 2026-06-17 | 2026-06-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Stringing (Km) | stringing | Stringing | TRUE | 119.178 |  |  |  |  | 0 | 119.178 | 1.0 |  | TA 509 - DPR - 2026-06-17.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Detail Survey (Km) | detail_survey_km | Other | FALSE | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Check Survey approved(Km) | check_survey | Other | FALSE | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Excavation | excavation | Other | FALSE | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Foundation (Nos.) | foundation | Foundation | TRUE | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Earthing (Nos.) | earthing | Other | FALSE | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 306 | 302 | 4 | 0 | 0 | 302 | 4 | 1.0 | G_1:- Amit Kumar Singh (WIP 16/0) | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Tack Welding | tack_welding | Other | FALSE | 306 | 255 | 47 | 12 | 0 | 267 | 39 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Stringing (Km) | stringing | Stringing | TRUE | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 | 2.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (13/0 to 14/0) | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Paying Out | paying_out | Other | FALSE | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ROW ) | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | Final Sag | final_sag | Other | FALSE | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 | 1.0 | G_3:- Gopal Associate (AP 24/0 to AP 25/0) | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 | Office: Hansera, Bikaner, Rajasthan. | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889 |  |  | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Route Alignment (Km) | route_alignment | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Detailed Survey (Km) | detailed_survey | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Check Survey (Km) | check_survey | Other | FALSE | 127.799 | 127.799 |  |  |  | 127.799 | 0 |  |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 |  |  |  | 28 | 0 |  |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Excavation | excavation | Other | FALSE | 352 | 319 | 31 | 10 |  | 329 | 23 |  |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Foundation (Nos.) | foundation | Foundation | TRUE | 352 | 319 | 31 | 10 | 1 | 329 | 23 | 6.0 |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Earthing (Nos.) | earthing | Other | FALSE | 352 | 296 | 31 | 28 |  | 324 | 28 |  |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 352 | 235 | 44 | 20 | 2 | 255 | 97 | 16.0 | 1 gang arrived on 14.06.26 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Tack Welding | tack_welding | Other | FALSE | 352 | 120 | 55 | 43 | 2 | 163 | 189 | 3.0 |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Stringing (Km) | stringing | Stringing | TRUE | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438 | 6.0 |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Paying Out | paying_out | Other | FALSE | 127.799 | 21.618 | 20 | 1.893 |  | 23.511 | 104.288 |  |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | Final Sag | final_sag | Other | FALSE | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438 |  |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 414 | TA 414 | ta414 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 127.799 | 0 | 20 |  |  | 0 | 127.799 |  |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status
TA 416 | TA 416 | ta416 |  | 2026-06-17 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0 |  | TA 416 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 416 | TA 416 | ta416 |  | 2026-06-17 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0 |  | TA 416 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 416 | TA 416 | ta416 |  | 2026-06-17 | 2026-06-01 | Progress Status | Erection | tower_erection | Tower Erection | TRUE | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0 |  | TA 416 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 416 | TA 416 | ta416 |  | 2026-06-17 | 2026-06-01 | Progress Status | Stringing | stringing | Stringing | TRUE | 115.134 | 111.1 | 4 | 2.061 | 1.254 | 113.2 | 1.934 | 5 |  | TA 416 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status
TA 418 | TA 418 | ta418 |  | 2026-06-17 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-17 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-17 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0 |  | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 418 | TA 418 | ta418 |  | 2026-06-17 | 2026-06-01 | Progress Status | Stringing - RS | stringing | Stringing | TRUE | 47.84 | 29.582 | 18.258 | 1.6442 | 3.6311 | 31.2262 | 16.6138 | 5 |  | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Route Alignment (Km) | route_alignment | Other | FALSE | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661 |  |  | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Detailed Survey (Km) | detailed_survey | Other | FALSE | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001 |  |  | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Check Survey (Km) | check_survey | Other | FALSE | 122.071 | 122.07 |  |  |  | 122.07 | 0.001 |  |  | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 31 | 31 | 0 |  |  | 31 |  |  |  | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Excavation (Nos) | excavation | Other | FALSE | 330 | 167 |  |  |  | 167 | 163 |  |  | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Foundation (Nos) | foundation | Foundation | TRUE | 330 | 255 | 49 | 11 |  | 266 | 64 | 15 | 38/4, 39/0, 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Earthing (Nos) | earthing | Other | FALSE | 330 | 217 | 50 | 0 |  | 217 | 113 |  |  | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 330 | 207 | 50 | 7 |  | 214 | 116 | 13 | 36/4, 37/0, 38/2, 41/2 ,52/1, 52/2, 54/0, 62/0, 65/0, 65/2, 64/4, 71/0, 73/0, 76/0 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Tack Welding (Nos) | tack_welding | Other | FALSE | 330 | 35 | 50 |  |  | 60 | 270 | 2 |  | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Stringing (Km) | stringing | Stringing | TRUE | 122.071 |  |  | 0.447 |  |  | 122.071 |  |  | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Paying Out (Km) | paying_out | Other | FALSE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Final Sag (Km) | stringing | Stringing | TRUE | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | ` |  | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | OPGW Stringing (Km) | opgw_stringing | OPGW Stringing | TRUE | 122.071 | 0 |  |  |  | 0 | 122.071 |  |  | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 | Completed Days | Power Line Crossings | power_line_crossings | Other | FALSE | [9 empty] | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 309 | 303 | 6 | 0 |  | 303 | 6 |  |  | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | Progress Status | Tackwelding | tack_welding | Other | FALSE | 309 | 283 | 26 | 13 |  | 296 | 13 | 1 |  | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | Progress Status | Tower Tightening | tower_tightening | Other | FALSE | 309 | 309 |  |  |  | 309 | 0 | 2 |  | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | Progress Status | Stringing -F/S | stringing | Stringing | TRUE | 121.342 | 115.467 | 5.878 | 2.129 | 0.485 | 117.596 | 3.746 |  |  | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | Progress Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67 |  |  | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | Progress Status | NH Crossing | nh_crossing | Other | FALSE | 3 | 3 |  |  |  | 3 |  |  |  | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | Progress Status | Power Line Crossing | power_line_crossing | Other | FALSE | 5 | 5 |  |  |  | 5 |  |  |  | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Detail Survey | detail_survey | Other | FALSE | 69 | 69 |  |  |  | 69 | 0 |  |  | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Check Survey | check_survey | Other | FALSE | 69 | 67 | 2 |  |  | 67 | 2 |  |  | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | FOUNDATION | foundation | Foundation | TRUE | 186 | 144 | 6 | 2 |  | 146 | 42 |  |  | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 186 | 121 | 6 | 1 |  | 122 | 65 |  |  | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | Stringing | stringing | Stringing | TRUE | 69 | 13.422 | 8 | 4.407 |  | 17.829 | 55.578 |  |  | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 212.95 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 69 |  |  |  |  | 0 | 69 |  |  | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Detail Survey | detail_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-18.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Check Survey | check_survey | Other | FALSE | 139.6 | 139.6 |  |  |  |  | 0 |  |  | TA 505 - DPR - 2026-06-18.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | FOUNDATION | foundation | Foundation | TRUE | 379 | 375 | 4 | 1 |  | 376 | 4 |  | Earthing-261/376. | TA 505 - DPR - 2026-06-18.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 164/362, Gangs Engaged-3. | TA 505 - DPR - 2026-06-18.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 458.32 Cr. | Stringing (Final Sag) | stringing | Stringing | TRUE | 139.6 | 15.462 | 23.008 | 8.364 |  | 23.826 | 124.138 |  |  | TA 505 - DPR - 2026-06-18.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Detail Survey | detail_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Check Survey | check_survey | Other | FALSE | 223 | 223 |  |  |  | 223 | 0 |  |  | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | FOUNDATION | foundation | Foundation | TRUE | 602 | 492 | 40 | 3 |  | 495 | 110 |  |  | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | TOWER ERECTION | tower_erection | Tower Erection | TRUE | 602 | 405 | 25 | 7 |  | 412 | 197 |  |  | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | Stringing | stringing | Stringing | TRUE | 223 | 55.632 | 30 | 3.53 |  | 59.162 | 167.368 |  |  | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 | SUPPLY VALUE = 477.03 Cr. | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | 231 | [8 empty] | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status
TA 509 | TA 509 | ta509 |  | 2026-06-18 | 2026-06-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Foundation (Loc) | foundation | Foundation | TRUE | 309 | 268 | 13 | 4 |  | 272 | 37 | 2.0 |  | TA 509 - DPR - 2026-06-18.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 509 | TA 509 | ta509 |  | 2026-06-18 | 2026-06-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Earthing (Loc) | earthing | Other | FALSE | 309 | 247 | 20 | 2 |  | 249 | 60 |  |  | TA 509 - DPR - 2026-06-18.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 509 | TA 509 | ta509 |  | 2026-06-18 | 2026-06-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Erection (Loc) | tower_erection | Tower Erection | TRUE | 309 | 208 | 30 | 8 |  | 216 | 93 | 5.0 |  | TA 509 - DPR - 2026-06-18.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 509 | TA 509 | ta509 |  | 2026-06-18 | 2026-06-01 | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | Stringing (Km) | stringing | Stringing | TRUE | 119.178 |  |  |  |  | 0 | 119.178 | 1.0 |  | TA 509 - DPR - 2026-06-18.xlsx | SUMMARY | SUMMARY | TA 509 Status
TA 510 | TA 510 | ta510 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: | Route Alignment (Km) | route_alignment | Other | FALSE | 114.516 | 114.516 | 0 |  |  | 114.516 | 0 |  |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: | Detailed Survey (Km) | detailed_survey | Other | FALSE | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024 |  |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: | Check Survey (Km) | check_survey | Other | FALSE | 114.516 | 98.032 | 0 |  |  | 98.032 | 16.484 |  |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 30 | 30 | 0 |  |  | 30 | 0 |  |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: | Excavation | excavation | Other | FALSE | 293 | 88 | 16 |  |  | 92 | 201 |  |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: | Foundation (Nos.) | foundation | Foundation | TRUE | 293 | 85 | 16 | 7 |  | 92 | 201 | 5 |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: | Earthing (Nos.) | earthing | Other | FALSE | 293 | 78 | 16 | 7 |  | 85 | 208 |  |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 293 | 40 | 30 | 5 |  | 45 | 248 |  |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: | Tack Welding | tack_welding | Other | FALSE | 293 | 13 | 30 |  |  | 13 | 280 |  |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: | Paying Out | paying_out | Other | FALSE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: | Final Sag | stringing | Stringing | TRUE | 114.516 | 0 | 11 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 510 | TA 510 | ta510 |  | 2026-06-18 | 2026-06-01 | NOA Ref. No.: | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 114.516 | 0 | 20 |  |  | 0 | 114.516 |  |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 | Office : Hansera, Lunkaransar | Route Alignment (Km) | route_alignment | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 | Office : Hansera, Lunkaransar | Detailed Survey (Km) | detailed_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 | Office : Hansera, Lunkaransar | Check Survey (Km) | check_survey | Other | FALSE | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0 |  |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 | Office : Hansera, Lunkaransar | Soil Investigation (Nos.) | soil_investigation | Other | FALSE | 28 | 28 | 0 | 0 | 0 | 28 | 0 |  |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 | Office : Hansera, Lunkaransar | Excavation | excavation | Other | FALSE | 319 | 308 | 18 | 4 | 0 | 312 | 7 |  |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 | Office : Hansera, Lunkaransar | Foundation (Nos.) | foundation | Foundation | TRUE | 319 | 306 | 18 | 4 | 0 | 310 | 9 | 02/18 |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 | Office : Hansera, Lunkaransar | Earthing (Nos.) | earthing | Other | FALSE | 319 | 269 |  |  |  | 269 | 50 |  |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 | Office : Hansera, Lunkaransar | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 319 | 221 | 30 | 6 | 1 | 227 | 92 | 07/220 |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 | Office : Hansera, Lunkaransar | Tack Welding | tack_welding | Other | FALSE | 319 | 79 |  | 20 | 1 | 99 | 220 |  |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 | Office : Hansera, Lunkaransar | Paying Out | paying_out | Other | FALSE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 | Office : Hansera, Lunkaransar | Final Sag | stringing | Stringing | TRUE | 124.568 | 0 |  | 0 | 0 | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 | Office : Hansera, Lunkaransar | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 124.568 | 0 | 20 | 0 |  | 0 | 124.568 |  |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026) | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 399 | 64 | 25 | 8 | 1 | 72 | 327 | 3 | Loc-62/0-3Pit Casting compl(ROW) Loc-61/1-Casting compl Loc-54/2-Boring & Dewatering WIP. Loc-58/2-Trial Pit | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 399 | 7 |  |  |  | 7 | 392 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 399 | 24 | 11 | 3 |  | 27 | 372 | 2 | Loc-55/2-Tower Erection WIP | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 399 | 0 |  |  |  | 0 | 399 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 147.584 | 0 |  |  |  |  | 147.584 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 147.69 | 0 |  | 0 |  |  | 147.69 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Detailed Survey Completed | detailed_survey | Other | FALSE | 82.803 | 82.803 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Submission of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.796 |  |  |  | 82.796 | 0.007 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Approval of Detailed Survey | detailed_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.803 | 0 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Submision | check_survey | Other | FALSE | 82.803 | 82.795 |  |  |  | 82.795 | 0.008 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Check Survey Approved | check_survey | Other | FALSE | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025) | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Foundation (No) | foundation | Foundation | TRUE | 220 | 25 | 10 | 1 |  | 26 | 194 | 1 |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Earthing | earthing | Other | FALSE | 220 | 10 |  |  | 0 | 10 | 210 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 220 | 7 | 5 |  |  | 7 | 213 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Tack Welding | tack_welding | Other | FALSE | 220 |  |  |  |  | 0 | 220 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Stringing (Km) | stringing | Stringing | TRUE | 82.803 | [5 empty] | 82.803 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Paying Out | paying_out | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | Final Sag | final_sag | Other | FALSE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 513 | TA 513 | ta513 |  | 2026-06-18 | 2026-06-01 | 400 KV Siwani To Patran TL | OPGW (Km) | opgw_stringing | OPGW Stringing | TRUE | 82.97 | [5 empty] | 82.97 |  |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 | Foundation Status | Foundation | foundation | Foundation | TRUE | 292 | 124 | 35 | 9 | 0 | 133 | 159 | 7 |  | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 | Foundation Status | Earthing | earthing | Other | FALSE | 292 | 102 | 35 | 3 | 0 | 105 | 187 |  |  | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 | Foundation Status | Tower Erection | tower_erection | Tower Erection | TRUE | 292 | 71 | 25 | 5 | 1 | 76 | 216 | 7 |  | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 | Foundation Status | Stringing -R/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 | Foundation Status | Stringing -F/S | stringing | Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 | Foundation Status | OPGW | opgw_stringing | OPGW Stringing | TRUE | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286 |  |  | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 | Foundation Status | NH Crossing | nh_crossing | Other | FALSE | 3 | [5 empty] | 3 |  |  | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 | Foundation Status | SH Crossing | sh_crossing | Other | FALSE | 1 | [5 empty] | 1 |  |  | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 | Foundation Status | Railway crossing | railway_crossing | Other | FALSE | 2 | [5 empty] | 2 |  |  | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 | Foundation Status | Power Line Crossing | power_line_crossing | Other | FALSE | 6 | [5 empty] | 6 |  |  | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 | Foundation Status | WIP - Foundations | foundation | Foundation | TRUE | [7 empty] | Gang |  | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status
TA 602 | TA 602 | ta602 |  | 2026-06-18 | 2026-06-01 | Progress Status | Soil Investigation | soil_investigation | Other | FALSE | 31 | 16 | 0 |  |  | 17 | 14 |  |  | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-18 | 2026-06-01 | Progress Status | Foundation | foundation | Foundation | TRUE | 480 | 154 | 30 | 8 | 0 | 162 | 318 | 3.0 |  | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-18 | 2026-06-01 | Progress Status | Earthing | earthing | Other | FALSE | 480 | 96 | 30 | 10 | 0 | 106 | 374 |  |  | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-18 | 2026-06-01 | Progress Status | Tower Erection | tower_erection | Tower Erection | TRUE | 480 | 52 | 35 | 18 | 2 | 70 | 410 | 4.0 |  | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-18 | 2026-06-01 | Progress Status | Tack welding | tack_welding | Other | FALSE | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0 |  | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TA 602 | TA 602 | ta602 |  | 2026-06-18 | 2026-06-01 | Progress Status | Stringing(Km) | stringing | Stringing | TRUE | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0 |  | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 | Project Name- | Foundation (Nos.) | foundation | Foundation | TRUE | 485 | 485 | 0 |  |  | 485 | 0 | - |  | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 | Project Name- | Earthing (Nos.) | earthing | Other | FALSE | 485 | 485 | 0 |  |  | 485 | 0 | - |  | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 | Project Name- | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 485 | 484 | 1 |  |  | 484 | 1 | - |  | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 | Project Name- | Tack Welding (Nos) | tack_welding | Other | FALSE | 485 | 433 | 52 |  |  | 433 | 52 | 1 |  | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 | Project Name- | Paying Out (Kms) | paying_out | Other | FALSE | 191.392 | 125.953 | 25 |  |  | 125.953 | 31.673 | 2 | AP12-13:- WIP. | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 | Project Name- | Final Sag (Kms) | stringing | Stringing | TRUE | 191.392 | 125.9367 | 25 |  |  | 125.9367 | 31.6893 |  | AP11A-12:- Completed AP12-13:- WIP. | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 | Project Name- | OPGW (Kms) | opgw_stringing | OPGW Stringing | TRUE | 191.392 | 88.466 | 30 |  |  | 88.466 | 69.16 |  |  | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | Route Alignment (Km) | route_alignment | Other | FALSE | 150.833 | 150.833 | 0 | 0 |  | 150.833 | 0 | 0.0 | Completed | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | Detailed Survey (Km) | detailed_survey | Other | FALSE | 150.833 | 149.21 | 1.623 | 0 |  | 149.21 | 1.623 | 0.0 |  | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | Detailed Survey Profiling (Km) | detailed_survey | Other | FALSE | 150.833 | 147.635 | 3.198 | 0 |  | 147.635 | 3.198 | 0.0 |  | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | Check Survey (Km) | check_survey | Other | FALSE | 150.833 | 119.962 | 25.288 | 0 |  | 119.962 | 30.871 | 0.0 | U/P | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | Approved check survey ( Km) | check_survey | Other | FALSE | 150.833 | 102.416 | 36.061 | 0 |  | 102.416 | 48.417 | 0.0 |  | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 147 | 147 | 0 | 0 |  | 147 | 0 | 0.0 | Completed | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | Excavation (Nos) | excavation | Other | FALSE | 505 | 274 | 80 | 20 |  | 294 | 211 | 0.0 |  | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | Foundation (Nos) | foundation | Foundation | TRUE | 505 | 264 | 80 | 13 |  | 277 | 214 | 14.0 |  | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | Earthing (Nos) | earthing | Other | FALSE | 505 | 185 | 87 | 17 |  | 202 | 303 | 0.0 |  | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 505 | 87 | 70 | 18 |  | 105 | 391 | 9.0 |  | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | Tack Welding (Nos) | tack_welding | Other | FALSE | 505 | 9 | 55 | 0 |  | 9 | 496 | 1.0 |  | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | Stringing (Km) | stringing | Stringing | TRUE | 150.833 | 0 | 12 | 0 |  | 0 | 147.643 | 1.0 |  | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 412 | TB 412 | tb412 |  | 2026-06-14 | 2026-06-01 | NOA Service: | OPGW Stringing (Km) | opgw_stringing | OPGW Stringing | TRUE | 150.833 | 0 | 0 | 0 |  | 0 | 150.833 | 0.0 |  | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-18 | 2026-06-01 | 220kV Line | Detailed Survey | detailed_survey | Other | FALSE | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0 |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-18 | 2026-06-01 | 220kV Line | Check Survey | check_survey | Other | FALSE | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 |  |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-18 | 2026-06-01 | 220kV Line | Foundation | foundation | Foundation | TRUE | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-18 | 2026-06-01 | 220kV Line | Earthing | earthing | Other | FALSE | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-18 | 2026-06-01 | 220kV Line | Tower Erection | tower_erection | Tower Erection | TRUE | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0 |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-18 | 2026-06-01 | 220kV Line | Tack Welding | tack_welding | Other | FALSE | 199 | 195 | 4 | 0 | 0 | 195 | 4 | 0.0 |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-18 | 2026-06-01 | 220kV Line | Paying Out | paying_out | Other | FALSE | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 | 0.0 |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-18 | 2026-06-01 | 220kV Line | Final Sag | stringing | Stringing | TRUE | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 |  |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-18 | 2026-06-01 | 220kV Line | OPGW | opgw_stringing | OPGW Stringing | TRUE | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0 |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-18 | 2026-06-01 | 132kV Line | Detailed Survey | detailed_survey | Other | FALSE | 9 | 9 |  | 0 | 0 | 9 | 0 |  |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-18 | 2026-06-01 | 132kV Line | Check Survey | check_survey | Other | FALSE | 9 | 9 |  | 0 | 0 | 9 | 0 |  |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-18 | 2026-06-01 | 132kV Line | Foundation | foundation | Foundation | TRUE | 39 | 36 | 5 | 1 | 0 | 37 | 2 | 1.0 | SC-2 Foundation wip | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-18 | 2026-06-01 | 132kV Line | Earthing | earthing | Other | FALSE | 39 | 34 | 5 | 2 | 0 | 36 | 3 | 1.0 |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-18 | 2026-06-01 | 132kV Line | Tower Erection | tower_erection | Tower Erection | TRUE | 39 | 31 | 5 | 1 | 0 | 32 | 7 | 1.0 | 2/0 Erection wip | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-18 | 2026-06-01 | 132kV Line | Tack Welding | tack_welding | Other | FALSE | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0 |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-18 | 2026-06-01 | 132kV Line | Paying Out | paying_out | Other | FALSE | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0 |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-18 | 2026-06-01 | 132kV Line | Final Sag | stringing | Stringing | TRUE | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 |  |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-18 | 2026-06-01 | 132kV Line | OPGW | opgw_stringing | OPGW Stringing | TRUE | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0 |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Route Alignment (Kms) | route_alignment | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Detailed Survey (Kms) | detailed_survey | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Check Survey (Kms) | check_survey | Other | FALSE | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 73 | 73 | 0 | 0 | 0 | 73 | 0 |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Foundation (Nos) | foundation | Foundation | TRUE | 513 | 308 | 34 | 9 | 1 | 317 | 196 | 5.0 | 30.0 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Earthing (Nos) | earthing | Other | FALSE | 513 | 266 |  |  |  | 266 | 247 |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 513 | 218 | 39 | 9 |  | 227 | 286 | 3.0 | 60.0 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Tack Welding (Nos) | tack_welding | Other | FALSE | 513 | 104 | 153 | 12 |  | 116 | 397 | 2.0 | 5.0 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Stringing (Kms) | stringing | Stringing | TRUE | [9 empty] | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 188.678 | 21.797 | 21.084 | 0.425 |  | 22.222 | 166.456 | 2.0 | 54.0 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318 |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | OPGW Stringing (Kms) | opgw_stringing | OPGW Stringing | TRUE | 188.678 | 0 | [7 empty] | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 188.678 |  |  |  |  | 0 | 188.678 |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-17 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 188.678 |  |  |  |  | 0 | 188.678 |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-17 | 2026-06-01 | Progress Summary | Route Alignment (Kms) | route_alignment | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-17 | 2026-06-01 | Progress Summary | Detailed Survey (Kms) | detailed_survey | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-17 | 2026-06-01 | Progress Summary | Check Survey (Kms) | check_survey | Other | FALSE | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0 |  |  | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-17 | 2026-06-01 | Progress Summary | Soil Investigation (Nos) | soil_investigation | Other | FALSE | 26 | 26 | 0 | 0 | 0 | 26 | 0 |  |  | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-17 | 2026-06-01 | Progress Summary | Foundation (Nos) | foundation | Foundation | TRUE | 43 | 34 | 8 | 2 |  | 36 | 7 | 2.0 | 20.0 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-17 | 2026-06-01 | Progress Summary | Earthing (Nos) | earthing | Other | FALSE | 43 | 3 |  |  | 0 | 3 | 40 |  |  | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-17 | 2026-06-01 | Progress Summary | Tower Erection (Nos) | tower_erection | Tower Erection | TRUE | 43 | 3 | 12 |  | 0 | 3 | 40 | 1.0 | 24.0 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-17 | 2026-06-01 | Progress Summary | Tack Welding (Nos) | tack_welding | Other | FALSE | 43 |  |  |  |  | 0 | 43 |  |  | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-17 | 2026-06-01 | Progress Summary | Stringing (Kms) | stringing | Stringing | TRUE | [6 empty] | 0 |  |  | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-17 | 2026-06-01 | Progress Summary | Paying Out (Kms) | paying_out | Other | FALSE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-17 | 2026-06-01 | Progress Summary | Final Sag (Kms) | stringing | Stringing | TRUE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-17 | 2026-06-01 | Progress Summary | OPGW Stringing (Kms) | opgw_stringing | OPGW Stringing | TRUE | 15.478 | 0 |  |  |  | 0 | 15.478 |  |  | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status
TB 605 | TB 605 | tb605 |  | 2026-06-17 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Check Survey | check_survey | Other | FALSE | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3 |  | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-17 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Foundation | foundation | Foundation | TRUE | 523 | 370 | 65 | 25 | 2 | 395 | 128 | 26 |  | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-17 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Earthing | earthing | Other | FALSE | 523 | 308 | 65 | 35 | 0 | 343 | 180 | 0 |  | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-17 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tower Erection | tower_erection | Tower Erection | TRUE | 523 | 203 | 60 | 26 | 2 | 229 | 294 | 13 |  | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-17 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Tack welding | tack_welding | Other | FALSE | 523 | 0 | 60 | 0 | 0 | 0 | 523 | 0 |  | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | TB 605 Status
TB 605 | TB 605 | tb605 |  | 2026-06-17 | 2026-06-01 | Progress Summary - Ratle Kiru Power Transmission Ltd | Stringing | stringing | Stringing | TRUE | 175.719 | 0 | 11.63 | 0 | 0 | 0 | 175.719 | 2 |  | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | TB 605 Status
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Route Alignment | route_alignment | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Route Alignment - Main Line | route_alignment | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Route Alignment - Loop In | route_alignment | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Route Alignment - Loop Out | route_alignment | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Detail Survey | detail_survey | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Detailed Survey - Main Line | detailed_survey | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Detailed Survey - Loop In | detailed_survey | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Detailed Survey - Loop Out | detailed_survey | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Check Survey | check_survey | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Check Survey - Main Line | check_survey | Other | FALSE | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Check Survey - Loop In | check_survey | Other | FALSE | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Check Survey - Loop Out | check_survey | Other | FALSE | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Normal Open Cast Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Normal Foundation - Main Line | foundation | Foundation | TRUE | 266 | 131 | 8 | 2 | 0 | 133 | 133 | 6.0 |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Normal Foundation - Loop In (Incld. Stone Column) | foundation | Foundation | TRUE | 20 | 0 | 0 | 0 | 0 | 0 | 20 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | Foundation | TRUE | 15 | 1 | 0 | 0 | 0 | 1 | 14 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Pile Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Pile Foundation_River_Main Line | foundation | Foundation | TRUE | 2 | 1 | 0 | 0 | 0 | 1 | 1 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Pile Foundation_Non River_Loop In | foundation | Foundation | TRUE | 7 | 7 | 0 | 0 | 0 | 7 | 0 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Pile Foundation_Non River_Loop Out | foundation | Foundation | TRUE | 8 | 6 | 0 | 0 | 0 | 6 | 2 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Pile Cap Foundation | foundation | Foundation | TRUE | [9 empty] | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Earthing | earthing | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Erection | tower_erection | Tower Erection | TRUE | [9 empty] | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Tower Erection - Main Line | tower_erection | Tower Erection | TRUE | 268 | 31 | 20 | 7 | 2 | 38 | 230 | 7.0 |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Tower Erection - loop In | tower_erection | Tower Erection | TRUE | 27 | 0 | 0 | 0 | 0 | 0 | 27 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Tower Erection - Loop Out | tower_erection | Tower Erection | TRUE | 23 | 0 | 0 | 1 | 0 | 1 | 22 | 1.0 |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Tack welding | tack_welding | Other | FALSE | [9 empty] | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Tack welding - Main Line | tack_welding | Other | FALSE | 268 | 0 | 0 | 0 | 0 | 0 | 268 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Tack welding - Loop In | tack_welding | Other | FALSE | 27 | 0 | 0 | 0 | 0 | 0 | 27 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Tack welding - Loop Out | tack_welding | Other | FALSE | 23 | 0 | 0 | 0 | 0 | 0 | 23 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Final Sag - Main Line | stringing | Stringing | TRUE | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Final Sag - Loop In | stringing | Stringing | TRUE | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Final Sag - Loop Out | stringing | Stringing | TRUE | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | OPGW Stringing | opgw_stringing | OPGW Stringing | TRUE | [9 empty] | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | OPGW Stringing - Main Line | opgw_stringing | OPGW Stringing | TRUE | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | OPGW Stringing - Loop In | opgw_stringing | OPGW Stringing | TRUE | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | OPGW Stringing - Loop Out | opgw_stringing | OPGW Stringing | TRUE | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134 |  |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Foundation | foundation | Foundation | TRUE | 142 | [8 empty] | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing
TB 608 | TB 608 | tb608 |  | 2026-06-17 | 2026-06-01 | LOA | Erection | tower_erection | Tower Erection | TRUE | 31 | [8 empty] | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing

## StatusSnapshotProject
project_code | project_display | project_scope_key | line_name | month | report_date_max | activities_total | quantity_primary_sum | cumulative_last_month_sum | plan_for_month_sum | progress_for_month_sum | today_progress_sum | cumulative_progress_sum | balance_progress_sum | completion_pct | foundation_cumulative_progress | tower_erection_cumulative_progress | stringing_cumulative_progress | opgw_stringing_cumulative_progress
TA 413 | TA 413 | ta413 |  | 2026-06-01 | 2026-06-16 | 12 | 13734.6306 | 12294.1842 | 825.18 | 54.39 | 7.401 | 12348.5742 | 1368.0564 | 89.9083 | 1896 | 1812 | 465.264 | 358.572
TA 414 | TA 414 | ta414 |  | 2026-06-01 | 2026-06-18 | 13 | 16095.558 | 10523.418 | 1632 | 611.6867 | 36 | 11135.1047 | 4960.4533 | 69.1812 | 1962 | 1499 | 124.9953 | 0
TA 416 | TA 416 | ta416 |  | 2026-06-01 | 2026-06-17 | 4 | 4084.536 | 4068.4 | 16 | 4.482 | 1.536 | 4073.02 | 11.516 | 99.7181 | 1208 | 1208 | 449.02 | 0
TA 418 | TA 418 | ta418 |  | 2026-06-01 | 2026-06-17 | 4 | 3430.72 | 3284.656 | 146.064 | 12.877 | 14.1255 | 3297.533 | 133.187 | 96.1178 | 1016 | 1016 | 249.533 | 0
TA 419 | TA 419 | ta419 |  | 2026-06-01 | 2026-06-18 | 13 | 20283.976 | 10220.4 | 1592 | 132.728 | 0 | 9527.062 | 10756.914 | 46.9684 | 2115 | 1703 | 3.576 | 0
TA 421 | TA 421 | ta421 |  | 2026-06-01 | 2026-06-18 | 9 | 10774.104 | 10404.834 | 369.288 | 45.773 | 0.485 | 10450.607 | 323.497 | 96.9975 | 1854 | 1854 | 699.575 | 586.032
TA 504 | TA 504 | ta504 |  | 2026-06-01 | 2026-06-18 | 6 | 4536 | 2900.954 | 154 | 33.517 | 0 | 2934.471 | 1635.046 | 64.6929 | 1018 | 851 | 113.471 | 0
TA 505 | TA 505 | ta505 |  | 2026-06-01 | 2026-06-18 | 5 | 10591.2 | 9239.958 | 306.072 | 87.908 | 0 | 6815.066 | 1351.242 | 64.3465 | 3379 | 3254 | 182.066 | 0
TA 506 | TA 506 | ta506 |  | 2026-06-01 | 2026-06-18 | 6 | 14728 | 9790.424 | 665 | 66.838 | 0 | 9857.262 | 3320.576 | 66.9287 | 3458 | 2867 | 410.262 | 0
TA 509 | TA 509 | ta509 |  | 2026-05-01 | 2026-05-31 | 4 | 1045.397 | 666 | 95 | 57 | 0 | 723 | 322.397 | 69.1603 | 268 | 0 | 0 | 0
TA 509 | TA 509 | ta509 |  | 2026-06-01 | 2026-06-18 | 4 | 3138.534 | 2169 | 189 | 38 | 0 | 2207 | 931.534 | 70.3195 | 816 | 646 | 0 | 0
TA 510 | TA 510 | ta510 |  | 2026-06-01 | 2026-06-18 | 12 | 17456.768 | 5205.38 | 1200 | 100 | 7 | 5347.38 | 12109.388 | 30.6321 | 723 | 356 | 0 | 0
TA 512 | TA 512 | ta512 |  | 2026-06-01 | 2026-06-18 | 12 | 21333.672 | 14262.336 | 774 | 224 | 19 | 14486.336 | 6847.336 | 67.9036 | 2785 | 2022 | 0 | 0
TA 513 | TA 513 | ta513 |  | 2026-06-01 | 2026-06-18 | 10 | 38245.512 | 12046.912 | 408 | 64 | 9 | 12110.976 | 26134.536 | 31.6664 | 761 | 263 | 0 | 0
TA 601 | TA 601 | ta601 |  | 2026-06-01 | 2026-06-18 | 9 | 9822.864 | 2376 | 760 | 97 | 5 | 2473 | 7349.864 | 25.176 | 1047 | 590 | 0 | 0
TA 602 | TA 602 | ta602 |  | 2026-06-01 | 2026-06-18 | 10 | 18127.664 | 4511.1085 | 520 | 270.83 | 9 | 4774.1085 | 13354.2075 | 26.336 | 1293 | 535 | 0 | 0
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 | 7 | 2514.176 | 2227.3557 | 133 | 0 | 0 | 2227.3557 | 185.5223 | 88.5919 | 485 | 484 | 125.9367 | 88.466
TB 412 | TB 412 | tb412 |  | 2026-06-01 | 2026-06-14 | 11 | 3727.831 | 1636.056 | 450.17 | 68 | 0 | 1704.056 | 1997.585 | 45.7117 | 277 | 105 | 0 | 0
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-06-01 | 2026-06-18 | 9 | 1210.32 | 962.772 | 180.108 | 57.3919 | 0 | 1020.1639 | 190.1561 | 84.2888 | 220 | 190 | 37.388 | 37.388
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-01 | 2026-06-18 | 9 | 6696 | 6578.867 | 119.269 | 77.2155 | 0 | 6656.0825 | 39.9175 | 99.4039 | 1194 | 1194 | 376.8201 | 380.3063
TB 507 | TB 507 - 400kV | tb507400kv | 400kV | 2026-06-01 | 2026-06-17 | 11 | 18172.12 | 7890.955 | 1340.84 | 106.425 | 6 | 7997.38 | 9231.35 | 44.0091 | 1573 | 1119 | 106.8 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | 2026-06-01 | 2026-06-17 | 11 | 1454.34 | 562.17 | 100 | 7 | 1 | 569.17 | 882.17 | 39.136 | 177 | 15 | 0 | 0
TB 605 | TB 605 | tb605 |  | 2026-06-01 | 2026-06-17 | 6 | 19547.504 | 8453.752 | 868.18 | 410 | 21 | 8863.752 | 10683.752 | 45.3447 | 3116 | 1769 | 0 | 0
TB 608 | TB 608 | tb608 |  | 2026-06-01 | 2026-06-17 | 10 | 9016.193 | 2933.5158 | 168 | 27 | 7 | 2960.5158 | 5882.6772 | 32.8355 | 882 | 207 | 0 | 0

## StatusSnapshotOverall
month | projects_total | activities_total | quantity_primary_sum | cumulative_last_month_sum | plan_for_month_sum | progress_for_month_sum | today_progress_sum | cumulative_progress_sum | balance_progress_sum | foundation_cumulative_progress | tower_erection_cumulative_progress | stringing_cumulative_progress | opgw_stringing_cumulative_progress | completion_pct
2025-12-01 | 1 | 6 | 2488 | 2042.592 | 164 | 80.773 | 0 | 2123.365 | 364.635 | 520 | 514 | 136.089 | 71.276 | 85.3443
2026-01-01 | 2 | 17 | 2534.99 | 2323.549 | 57.581 | 36.924 | 17 | 2125.693 | 163.6893 | 487 | 484 | 173.693 | 0 | 83.8541
2026-05-01 | 1 | 4 | 1045.397 | 666 | 95 | 57 | 0 | 723 | 322.397 | 268 | 0 | 0 | 0 | 69.1603
2026-06-01 | 23 | 203 | 268722.2226 | 144543.4082 | 12916.171 | 2597.0621 | 143.5475 | 143835.9763 | 119680.4833 | 33255 | 25559 | 3344.7071 | 1450.7642 | 53.5259

## StretchSectionFact
project_code | project_display | project_scope_key | line_name | report_date | month | section_label | section_id | from_ap | to_ap | length_km | readiness_state | is_ready | is_partial | is_not_ready | is_unknown | balance_towers | remarks | source_file | source_sheet | configured_sheet | template_sheet
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | Gantry - AP-1 |  |  | 0.15001 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | pending due to gy not yet ready | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-1 - AP-2A |  |  | 0.29021 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP/2A - AP/3A |  |  | 2.837 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP3A/0-AP3B/0 |  |  | 2.6915 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP3B/0-AP4/0 |  |  | 1.6271 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-4 - AP-4A/0 |  |  | 0.70916 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-4A/0 - AP-5 |  |  | 2.6816 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-5 - AP-5A/0 |  |  | 4.4184 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-5A/0 - AP-6 |  |  | 0.41948 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-6 - AP-7 |  |  | 4.9012 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-7 - AP-7A/0 |  |  | 2.6993 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-7A/0 - AP-8/0 |  |  | 2.4348 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-8/0 - AP-8A/0 |  |  | 4.455 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-8A/0 - AP-9/0 |  |  | 0.46663 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-9/0 - AP-10/0 |  |  | 4.9649 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-10/0 - AP-11/0 |  |  | 1.0042 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-11/0 - AP-12/0 |  |  | 0.24289 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-12/0 - AP-13/0 |  |  | 0.32973 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Ready for stringing | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-13/0 - AP-13A/0 |  |  | 0.41688 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | wip | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-13A/0 - AP-14/0 |  |  | 0.48027 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | wip | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-14/0 - AP-15/0 |  |  | 0.22382 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-15/0 - AP-16/0 |  |  | 5.0193 | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | wip | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-16/0 - AP-17/0 |  |  | 0.39269 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-17/0 - AP-18/0 |  |  | 0.3984 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-18/0 - AP-19/0 |  |  | 3.03 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | WIP | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-19/0 - AP-20/0 |  |  | 0.27936 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-20/0 - AP-21/0 |  |  | 2.5502 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-21/0 - AP-22/0 |  |  | 2.2835 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-22/0 - AP-23/0 |  |  | 0.25905 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-23/0 - AP-23A/0 |  |  | 0.44046 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-23A/0 - AP-24/0 |  |  | 0.49669 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-24/0 - AP-25/0 |  |  | 0.24403 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-25/0 - AP-26/0 |  |  | 0.23743 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-26/0 - AP-27/0 |  |  | 0.20348 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-27/0 - AP-28/0 |  |  | 2.5483 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-28/0 - AP-29/0 |  |  | 0.21121 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-29/0 - AP-29A/0 |  |  | 2.3792 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-29A/0 - AP-30/0 |  |  | 2.669 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-30/0 - AP-31/0 |  |  | 4.1242 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-31/0 - AP-32/0 |  |  | 4.3334 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-32/0 - AP-32A/0 |  |  | 3.2835 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-32A/0 - AP-33/0 |  |  | 0.84044 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-33/0 - AP-34/0 |  |  | 4.0498 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-34/0 - AP-35/0 |  |  | 4.8986 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-35/0 - AP-36/0 |  |  | 4.9163 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | WIP | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-36/0 - AP-36A/0 |  |  | 0.454 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-36A/0 - AP 36B/0 |  |  | 0.8267 | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-36B/0 N - AP-36C/0 N |  |  | 0.42081 | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-36C/0 N - AP-37/0 N |  |  | 0.46933 | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-37/0 N - AP-37A/0 |  |  | 2.0763 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-37A/0 - AP-38/0 |  |  | 2.5836 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-38/0 - AP-39/0 |  |  | 4.1637 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-39/0 - AP-40/0 |  |  | 4.7168 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Completed | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-40/0 - AP-40A/0 |  |  | 4.6659 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-40A/0 - AP-41/0 |  |  | 0.41061 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-41/0 - AP-42/0 |  |  | 0.82378 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-42/0 - AP-42/3 |  |  | 1.259 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-42/3 - AP-43/0 |  |  | 0.42489 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-43/0 - AP-43/5 |  |  | 1.8519 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-43/5-AP-44/0 |  |  | 1.5845 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-44/0-AP45/0 |  |  | 2.3832 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | AP-45/0-AP-46/0 |  |  | 0.20853 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  |  |  |  | 0.11786 | NOT_READY | FALSE | FALSE | TRUE | FALSE | 4 |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | Type |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | TSE |  |  | 0.10929 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 413 | TA 413 | ta413 |  | 2026-06-16 | 2026-06-01 |  | Manual |  |  | 0.0085709 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0A/0 (CT) |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 447.467 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0B/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0B/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 4 | 1596.096 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0B/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0B/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0C/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0C/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 793.337 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0D/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0D/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 5 | 2099.0 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0D/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0D/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0D/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0D/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0E/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 449.716 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0E/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 3 | 1238.287 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0E/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0F/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0G/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 283.529 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0G/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 799.931 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 0H/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 1/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 245.359 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 2/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 199.438 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 3/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 263.425 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 3/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 6 | 2405.616 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 3/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 3/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 3/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 3/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 4/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 4/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 775.254 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 5/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 5/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 5 | 1991.808 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 5/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 5/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 5/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 13 | 4994.034 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/6 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/7 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/8 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/9 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/10 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/11 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 6/12 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 7/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 7/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 840.298 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 8/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 9/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 339.22 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 10/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 473.565 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 11/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 263.996 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 11/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 380.093 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 11/2 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 485.0 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 11/3 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 3 | 1185.862 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 11/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 12/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 12/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 3 | 1141.136 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 12/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 12A/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 12A/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 838.654 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 13/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 14/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 277.649 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 14/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 701.587 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 15/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 15A/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 282.522 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 16/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 247.475 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 17/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 363.497 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 17/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 3 | 1083.04 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 17/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 18/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 19/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 357.699 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 19/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 6 | 2321.094 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 19/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 19/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 19/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 19/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 20/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 20/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 3 | 1081.613 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 20/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 20/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 21/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 350.242 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 22/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 243.717 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 22/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 4 | 1531.617 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 22/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 22/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 23/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 23/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 4 | 1521.685 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 23/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 23/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 24/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 24/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 4 | 1524.2939999999999 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 24/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 24/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 25/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 26/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 222.366 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 26/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 7 | 2760.124 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 26/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 26/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 26/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 26/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 26/6 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 27/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 27/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 4 | 1507.5030000000002 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 27/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 27/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 28/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 28/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 740.033 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 29/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 30/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 206.6 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 30/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 786.177 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 31/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 31/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 3 | 1169.322 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 31/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 32/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 33/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 270.019 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 33/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 708.875 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 34/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 34/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 774.5709999999999 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 35/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 36/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 247.071 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 36/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 4 | 1617.671 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 36/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 36/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 36/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 36/5 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 7 | 2789.059 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 36/6 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 36/7 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 36/8 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 36/9 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 36/10 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 37/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 38/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 262.543 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 38/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 12 | 4947.104 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 38/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 38/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 38/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 38/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 38/6 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 38/7 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 38/8 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 38/9 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 38/10 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 38/11 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 39/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 40/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 203.091 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 40/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 10 | 4059.189 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 40/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 40/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 40/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 40/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 40/6 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 40/7 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 40/8 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 40/9 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 41/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 41/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 9 | 3475.276 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 41/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 41/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 41/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 41/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 41/6 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 41/7 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 41/8 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 42/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 43/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 219.878 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 43/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 7 | 2622.3039999999996 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 43/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 43/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 43/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 43/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 43/6 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 44/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 45/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 446.77 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 46/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 232.356 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 46/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 5 | 2072.371 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 46/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 46/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 46/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 47/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 48/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 349.437 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 48/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 808.5930000000001 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 49/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 50/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 207.14 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 50/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 482.866 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 51/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 370.419 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 52/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 252.501 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 52/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 3 | 1015.8820000000001 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 52/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 53/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 54/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 219.617 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 54/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 8 | 3182.615 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 54/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 54/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 54/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 54/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 54/6 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 54/7 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 55/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 55/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 7 | 2583.042 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 55/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 55/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 55/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 55/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 55/6 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 56/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 57/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 221.817 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 57/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 819.678 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 58/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 59/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 294.636 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 59/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 620.125 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 60/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 61/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 193.896 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 61/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 817.134 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 62/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 62/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 6 | 2453.77 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 62/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 62/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 62/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 62/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 7 | 2625.925 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63/6 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63A/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63B/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 350.509 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63B/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 7 | 2759.292 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63B/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63B/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63B/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63B/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 63B/6 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 64/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 64/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 774.0 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 64/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 64/3 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 4 | 1622.488 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 64/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 64/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 64A/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 65/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 454.351 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 65/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 3 | 1169.04 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 65/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 66/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 66/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 775.692 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 67/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 68/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 368.455 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 69/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 349.573 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 70/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 420.909 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 71/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 309.862 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 72/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 364.166 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 73/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 208.46 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 74/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 395.522 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 75/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 266.464 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 76/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 209.254 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 76/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 4 | 1639.1239999999998 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 76/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 76/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 77/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 78/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 394.721 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 78/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 5 | 2033.805 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 78/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 78/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 78/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 78A/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 79/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 430.808 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 80/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 240.544 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 81/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 255.715 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 82/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 188.957 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 83/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 397.91 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 83/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 10 | 3875.869 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 83/2 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 83/3 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 83/4 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 83/5 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 83/6 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 83/7 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 83/8 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 83/9 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 84/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 84/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 6 | 1830.829 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 84/2 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 84/3 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 84/4 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 84/5 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 84A/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 84A/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 779.7850000000001 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 85/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 85A/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 244.482 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 86/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 289.816 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 86/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 3 | 1242.489 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 86/2 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 86A/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 86A/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 4 | 1571.274 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 86A/2 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 86A/3 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 86A/4 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 86A/5 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 808.896 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 87/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 87/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 3 | 1180.237 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 87/2 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 88/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 88/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 3 | 1071.874 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 88/2 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 89/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 90/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 295.94 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 90A/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 326.696 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 90A/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 637.6659999999999 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 90B/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 91/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 215.08 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 92/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 381.667 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 93/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 255.587 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 93A/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 351.254 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 93B/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 369.958 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 93C/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 260.002 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 94/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 166.604 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 95/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 486.779 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 95A/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 179.001 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 96/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 153.586 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 96/1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 373.0 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 96/2 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 2 | 807.652 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 97/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 98/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 292.635 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 99/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 103.101 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 100/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 183.667 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | 101/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 147.684 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | GANTRY-2 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 78.283 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 419 | TA 419 | ta419 |  | 2026-06-18 | 2026-06-01 |  | GANTRY-1 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE | 1 | 115.31 | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB2+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB2+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB2+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DC1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DC1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DD45+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA-3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB2+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB1+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DC1+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA-3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB2+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DD45+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB2+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB2+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DC1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DD45+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB2+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DB1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA-3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DC1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DCT+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DC1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DC1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB2+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DC1+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DD60+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DB1+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DB2+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DB1+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DB1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DD45+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DB2+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DB2+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DB2+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DD45+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DD45+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DB1+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DB1+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DB1+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA-3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DD45+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DD45+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DC2+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB2+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB1+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DD60+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DD60+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 2DD45+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA-3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DD45+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA-3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB1+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB2+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DD45+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DC1+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | 3DB1+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+6 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+0 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+3 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 421 | TA 421 | ta421 |  | 2026-06-18 | 2026-06-01 | [5 empty] | PARTIAL | FALSE | TRUE | FALSE | FALSE |  | 3DA+9 | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 |  | Bhinder | 11/0 | 12/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing | TA 504 Stretch
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 |  | Bhinder | 12/0 | 13/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing | TA 504 Stretch
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 |  | Bhinder | 15/0 | 16/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing | TA 504 Stretch
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 |  | Bhinder | 16/0 | 16/3 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing | TA 504 Stretch
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 |  | Bhinder | 16/3 | 17/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing | TA 504 Stretch
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 |  | Bhinder | 17/0 | 17/4 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing | TA 504 Stretch
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 |  | Bhinder | 17/4 | 18/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing | TA 504 Stretch
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 |  | Bhinder | 18/0 | 18/1 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing | TA 504 Stretch
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 |  | Bhinder | 18/1 | 19/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing | TA 504 Stretch
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 |  | Bhinder | 19/0 | 20/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing | TA 504 Stretch
TA 504 | TA 504 | ta504 |  | 2026-06-18 | 2026-06-01 |  | Bhinder | 20/0 | 21/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing | TA 504 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 100/0 To 101/0 | 100/0 | 101/0 | 0.419 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 101/0 To 102/0 | 101/0 | 102/0 | 3.47 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 102/0 To 103/0 | 102/0 | 103/0 | 0.461 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 103/0 To 103/5A | 103/0 | 103/5A | 2.2 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 103/5A To 103/6A | 103/5A | 103/6A | 0.567 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 103/6A To 104/0 | 103/6A | 104/0 | 1.403 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 104/0 To 105/0 | 104/0 | 105/0 | 0.967 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 111/0 To 112/0 | 111/0 | 112/0 | 1.954 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 113/0 To 114/0 | 113/0 | 114/0 | 2.565 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 114/0 To 115/0 | 114/0 | 115/0 | 4.304 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 110A/0 To 111/0 | 110A/0 | 111/0 | 1.23 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 110/0 To 110A/0 | 110/0 | 110A/0 | 3.86 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 112/0 To 113/0 | 112/0 | 113/0 | 0.226 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 126/0 To 127/0 | 126/0 | 127/0 | 1.957 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 127/0 To 128/0 | 127/0 | 128/0 | 1.441 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 108/0 To 109/0 | 108/0 | 109/0 | 1.668 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 109/0 To 110/0 | 109/0 | 110/0 | 1.949 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 115/0 To 116/0 | 115/0 | 116/0 | 0.2 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 105/0 To 106/0 | 105/0 | 106/0 | 0.754 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 106/0 To 108/0 | 106/0 | 108/0 | 0.212 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 109/0 To 110/0 | 109/0 | 110/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 117/0 To 118/0 | 117/0 | 118/0 | 0.24 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 147/0 To 147A/0 | 147/0 | 147A/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 147A/0 To148/0 | 147A/0 | 148/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 175/0 To 176/0 | 175/0 | 176/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 176/0 To 177/0 | 176/0 | 177/0 | 1.564 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 177/0 To 178/0 | 177/0 | 178/0 |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 116/0 To 117/0 | 116/0 | 117/0 | 1.147 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 505 | TA 505 | ta505 |  | 2026-06-18 | 2026-06-01 |  | 120/0 To 121/0 | 120/0 | 121/0 | 1.593 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 1/0 | 2/0 | 4.4241 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 5/0 | 6/0 | 4.9493 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 48/0 | 50/0 | 0.68847 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 50/0 | 51/0 | 1.1601 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 2/0 | 2A/0 | 3.3186 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 51/0 | 51A/0 | 1.2449 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 51A/0 | 51C/0 | 1.2348 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 51C/0 | 52/0 | 1.9682 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 52/0 | 53/0 | 0.99208 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 4/0 | 5/0 | 2.809 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 18/0 | 19/0 | 3.934 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 68/0 | 68/1 | 0.504 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 67/0 | 68/0 | 0.17673 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 6/0 | 9/0 | 1.2107 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 66/0 | 67/0 | 0.74377 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 10/0 | 11/0 | 1.2563 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 11/0 | 11/3 | 1.114 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 11/3 | 12/0 | 0.53015 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 65A/3 | 66/0 | 0.24426 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Udaipur | 213/0 | 214/0 | 2.3513 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 17/0 | 18/0 | 2.733 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 9/0 | 10/0 | 0.27218 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Gogunda | 139/0 | 139A/0 | 0.65583 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Gogunda | 139A/0 | 140/0 | 0.24266 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Udaipur | 212/0 | 213/0 | 2.3931 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 12/0 | 13/0 | 3.3153 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 65/0 | 65A/0 | 0.19507 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 65A/0 | 65A/3 | 0.919 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 15/0 | 16/0 | 1.6749 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 64/0 | 64A/0 | 0.47196 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Udaipur | 211/0 | 212/0 | 3.2545 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 63/0 | 64/0 | 0.77897 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 13/0 | 14/0 | 2.4545 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 64A/0 | 65/0 | 1.6591 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 38/0 | 39/0 | 0.76252 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 37/0 | 38/0 | 2.04 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 14/0 | 15/0 | 0.28 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 61/0 | 62/0 | 0.79522 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Gogunda | 140/0 | 141/0 | 1.1527 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Sirohi | 16/0 | 17/0 | 0.20497 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 506 | TA 506 | ta506 |  | 2026-06-18 | 2026-06-01 |  | Gogunda | 141/0 | 142/0 | 0.72038 | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | TA 506 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 20/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 20/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 20/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 20/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 20/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 20/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 20/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 20/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 11/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 11/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 11/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 11/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 11/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 19/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 19/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 18/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 18/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 18/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 18/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 19/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 19/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 19/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 19/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 19/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 28/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 28/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 28/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 29/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 29/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 11/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 29/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 29/15 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 29/20 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 7/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 7/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 7/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 2/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 7/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 7/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 7/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 11/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 12/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 5/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 5/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 2/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 5/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 7/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 3A/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 3A/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 3/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 3/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 3/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 3/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 3/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 7/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 7/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 7/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 35/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 35/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 35/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 8/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 8/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 35/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 35/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 8/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 29/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 29/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 29/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 29/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 33/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 8/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 29/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 34/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 33/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 36/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 36/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 34/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 36/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 8/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 6/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 6/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 6/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 6/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 7/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 6/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 6/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 5/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 5/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 8/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 8/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 8/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 6/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 6/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 23/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 23/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 6/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 6/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 5/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 512 | TA 512 | ta512 |  | 2026-06-18 | 2026-06-01 |  | 23/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | TA 512 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP48 |  | AP49 | 3.3066 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP49 |  | AP50 | 4.5818 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP50 |  | AP51 | 1.519 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP51 |  | AP52 | 4.3004 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP52 |  | AP53 | 1.9959 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP53 |  | AP54 | 2.7717 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP54 |  | AP55 | 0.23844 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP55 |  | AP56 | 1.4365 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP56 |  | AP57 | 5.2326 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP57 |  | AP58 | 0.21474 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP58 |  | AP59 | 1.5881 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP59 |  | AP60 | 2.3158 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP60 |  | AP61 | 3.8451 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP61 |  | AP62 | 0.24749 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP62 |  | AP63 | 1.82 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP63 |  | AP64 | 1.6119 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP64 |  | AP65 | 0.43905 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP65 |  | AP66 | 1.3995 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP66 |  | AP67 | 0.88682 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP67 |  | AP68 | 1.8412 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP68 |  | AP69 | 1.1609 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP69 |  | AP70 | 1.2616 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP70 |  | AP71 | 1.967 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP71 |  | AP72 | 0.24852 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP72 |  | AP73 | 0.82768 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP73 |  | AP74 | 1.2134 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP74 |  | AP75 | 0.25012 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP75 |  | AP76 | 1.6107 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP76 |  | AP77 | 0.19645 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP77 |  | AP78 | 4.2606 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP78 |  | AP79 | 1.5551 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP79 |  | AP80 | 1.5776 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP80 |  | AP81 | 2.4962 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP81 |  | AP82 | 1.6443 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP82 |  | AP83 | 1.2808 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP83 |  | AP84 | 1.1533 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP84 |  | AP85 | 2.7389 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP85 |  | AP86 | 1.8152 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP86 |  | AP87 | 0.75885 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP87 |  | AP88 | 0.46849 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP88 |  | AP89 | 0.292 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP89 |  | AP90 | 0.7625 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP90 |  | AP91 | 2.4599 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP91 |  | AP92 | 1.1419 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP92 |  | AP93 | 1.2207 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP93 |  | AP94 | 1.7272 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP94 |  | AP95 | 1.7948 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP95 |  | AP96 | 0.26547 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP96 |  | AP97 | 3.6581 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP97 |  | AP98 | 1.9377 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP98 |  | AP99 | 2.328 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP99 |  | AP100 | 4.9858 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP100 |  | AP101 | 3.6492 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP101 |  | AP102 | 3.924 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP102 |  | AP103 | 2.7046 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP103 |  | AP104 | 1.5241 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP104 |  | AP105 | 4.6981 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP105 |  | AP106 | 1.5484 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  | Row | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP106 |  | AP107 | 0.26332 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP107 |  | AP108 | 0.78081 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP108 |  | AP109 | 1.1265 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP109 |  | AP110 | 0.19463 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | AP110 |  | AP111 | 0.20314 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TA 601 | TA 601 | ta601 |  | 2026-06-18 | 2026-06-01 |  | Grand Total |  |  | 113.2692 | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/13 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/14 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 62/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 63/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 63/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 62/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 62/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/12 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 60/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 62/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 62/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 64/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 64/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 60/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 62/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 65/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 60/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 65/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 64/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 62/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 60/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 62/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 65/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 60/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 61/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 65/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 64/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 61/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 65/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 64/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 63/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 64/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 61/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 65/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 65/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 67/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 61/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 64/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 67/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 64/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 65/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 65/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 61/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 60/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 63/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 63/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 63/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 61/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 62/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 61/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 61/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 64/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 64/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 64/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 61/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 61/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 63/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 61/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 63/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 63/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 60/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 60/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 60/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 60/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 60/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Ramagora | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/16 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/15 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 60/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 55/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 55/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 57/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 57/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 57/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 57/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 62/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 62/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 62/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 57/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 50/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 50/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 50/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 50/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 50/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 51/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 16/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | R&A | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 50/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 64/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 15/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | SB Enterprises | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 16/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | SB Enterprises | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 18/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | SB Enterprises | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 50/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 73/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 73/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 73/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 52/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 52/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 52/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 48/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 49/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 48/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 47/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 49/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 49/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 49/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 73/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 72/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 50/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 73/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 51/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 49/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 49/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 49/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 50/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 59/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 50/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 65/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 65/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 73/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 73/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 73/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 74/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 73/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 65/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 66/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 51/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 50/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 52/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 49/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 52/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 52/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 73/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 52/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 47/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 47/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 58/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 72/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 72/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 71/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 71/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 70/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 71/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 70/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 55/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 55/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 71/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 70/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 71/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 71/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 71/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 71/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 70/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 71/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 70/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 70/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 68/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 67/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 16/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Chanda Enterprises | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 17/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Chanda Enterprises | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 70/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 53/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 72/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/14 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 55/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 55/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 57/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 57/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 55/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 1A/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | B.S. Infra | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 1A/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | B.S. Infra | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 1A/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | B.S. Infra | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 1A/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | B.S. Infra | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 1A/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | B.S. Infra | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 1A/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | B.S. Infra | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 1A/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | B.S. Infra | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 2/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | B.S. Infra | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 54/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 70/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 70/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 54/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 54/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 44/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 45/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 2/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 2/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 2/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/12 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11A/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11A/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 52/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 52/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 52/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 38/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 39/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 40/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 30/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 29/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 30/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 30/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 30/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 31/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 31/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 32/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 28/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 28/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 27/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 27/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 70/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 38/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 28/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 33/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 33/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 34/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 34/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 35/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 35/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 35/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 38/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 39/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 41/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 42/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 42/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 42/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 42/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 53/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 54/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 69/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 69/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 70/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 70/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 2/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 2/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 2/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 16/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Vendor Name not confirmed by Section incharge | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 27/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 27/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 27/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 27/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 28/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 32/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 32/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 29/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 6/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 6/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 5/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 4/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 4/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/16 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 2/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 2/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 2/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/17 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/18 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 32/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 32/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 26/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 34/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 34/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 44/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 44/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 44/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 44/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 44/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 46/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 47/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 47/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 47/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 47/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 47/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 47/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 47/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 35/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 35/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 35/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 36/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 36/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 36/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 40/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 25/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 25/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 1/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 1A/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 1A/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 3/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 4/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 4/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 4/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 6/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 7/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/13 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/15 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/19 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/20 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/21 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/22 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/23 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 25/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 27/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 36/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 36/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 40/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 40/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 41/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 41/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 42/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 42/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 42/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 43/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11A/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 12/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 17/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 18/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 20/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 20/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 21/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 21/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 22/13 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 43/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 43/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 43/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 43/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 43/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 43/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 43/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 44/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 44/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 44/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 16/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Chanda Enterprises | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 17/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Chanda Enterprises | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 27/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 27/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 27/12 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 28/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 28/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 29/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | The Shraddha Cooperative Multipurpose Society Limited | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 44/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 45/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 53/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 53/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 53/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 53/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 53/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 53/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 54/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/12 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 44/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 44/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 52/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 54/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 55/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 55/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 56/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 57/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 13/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 13/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Yet to be confirm | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11A/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11A/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11A/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11A/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11A/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11A/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 11A/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 13/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 13/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 15/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/6 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/7 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 8/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 9/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 10/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 14/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Shiv Power | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 19/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 21/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 21/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 24/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 18/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 14A/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 14A/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 53/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 43/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 43/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 43/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 43/11 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 47/5 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 37/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 34/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Suraja Ram | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 19/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 18/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 21/2 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 27/9 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 28/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 28/4 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 27/10 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 29/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 28/8 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 29/1 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 16/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 26/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 31/0 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Jai Bagrangbali | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 408 | TB 408 | tb408 |  | 2026-06-01 | 2026-06-01 |  | 13/3 |  |  |  | READY | TRUE | FALSE | FALSE | FALSE |  | Gang name not confimed | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 65/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 65/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 66/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 72/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 72/2 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 75/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 75/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 75/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 75/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 75/4 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 75/5 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 75/6 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 75/7 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 76/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 76/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 77/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 77/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 77/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 77/4 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 79/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 78/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 78/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 80/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 80/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 81/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 81/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 81/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 81/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 81/4 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 81/5 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 82/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 82/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 82/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 83/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 83/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 84/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 85/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 85/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 86/0 |  |  |  | NOT_READY | FALSE | FALSE | TRUE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 86/1 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 89/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 90/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 90/1 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 98B/0 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 98A/1 |  |  |  | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 109A/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 110/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 111/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 112/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 113/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 113A/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 114/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 114/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 115/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 115/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 116/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 116/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 127/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 128/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 128/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 129/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 129/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 129/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 130/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 130/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 131/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 131/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 131/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 132/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 132/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 132/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 132/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 132/4 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 133/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 133/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 133/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 133/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 133/4 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 133/5 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 133/6 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 133/7 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 133/8 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 134/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 134A/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 134A/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 134A/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 134A/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 134A/4 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 135/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 135/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 135/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 135/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 136/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 137/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 138/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 138/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 138/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 138/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 139/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 139/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 140/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 140/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 140/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 140/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 141/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 141/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 141/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 142/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 143/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 143/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 143/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 143/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 143/4 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 143/5 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 143/6 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 143/7 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 144/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 145/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 145/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 145/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 145/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 145/4 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 146/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 146/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 146/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 147/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 147/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 147/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 147/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 147/4 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 147/5 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 147/6 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 147/7 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 147/8 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 147/9 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 148/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 148/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 148/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 148/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 148/4 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 148/5 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 148/6 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 148/7 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 149/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 149A/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 149B/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 149B/1 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 149B/2 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 149B/3 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 150/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 151/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 152/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 153/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 153A/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 |  | 154/0 |  |  |  | PARTIAL | FALSE | TRUE | FALSE | FALSE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch
TB 507 | TB 507 | tb507 |  | 2026-06-17 | 2026-06-01 | [5 empty] | UNKNOWN | FALSE | FALSE | FALSE | TRUE |  |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch

## ManpowerProductivityFact
project_code | project_display | project_scope_key | line_name | date | month | gang_name | from_ap | to_ap | span_key | method | section_readiness | daily_km | po_km | manpower_gang_strength | manpower_fitters | manpower_signal_type | manpower_status | expected_manpower | expected_match | availability | availability_reason
TA 413 | TA 413 | ta413 |  | 2025-02-21 | 2025-02-01 |  | AP-34 | AP-35 | 34¦35 | TSE |  | 0.40822 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-02-22 | 2025-02-01 |  | AP-34 | AP-35 | 34¦35 | TSE |  | 0.40822 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-02-23 | 2025-02-01 |  | AP-34 | AP-35 | 34¦35 | TSE |  | 0.40822 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-02-24 | 2025-02-01 |  | AP-34 | AP-35 | 34¦35 | TSE |  | 0.40822 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-02-25 | 2025-02-01 |  | AP-34 | AP-35 | 34¦35 | TSE |  | 0.40822 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-02-26 | 2025-02-01 |  | AP-34 | AP-35 | 34¦35 | TSE |  | 0.40822 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-02-27 | 2025-02-01 |  | AP-34 | AP-35 | 34¦35 | TSE |  | 0.40822 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-02-28 | 2025-02-01 |  | AP-34 | AP-35 | 34¦35 | TSE |  | 0.40822 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-01 | 2025-03-01 |  | AP-34 | AP-35 | 34¦35 | TSE |  | 0.40822 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-02 | 2025-03-01 |  | AP-34 | AP-35 | 34¦35 | TSE |  | 0.40822 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-03 | 2025-03-01 |  | AP-34 | AP-35 | 34¦35 | TSE |  | 0.40822 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-04 | 2025-03-01 |  | AP-34 | AP-35 | 34¦35 | TSE |  | 0.40822 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-17 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-18 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-19 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-20 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-21 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-22 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-23 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-24 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-25 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-26 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-27 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-28 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-29 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-29 | 2025-03-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-30 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-30 | 2025-03-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-31 | 2025-03-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-03-31 | 2025-03-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-01 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-01 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-02 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-02 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-03 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-03 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-04 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-04 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-05 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-05 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-06 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-06 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-07 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-07 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-08 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-08 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-09 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-09 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-10 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-10 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-11 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-11 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-12 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-12 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-13 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-13 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-14 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-14 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-15 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-15 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-16 | 2025-04-01 |  | 37A/0 | AP-38/0 | 37A/0¦38/0 | TSE |  | 0.083342 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-16 | 2025-04-01 |  | AP-38 | AP-39 | 38¦39 | TSE |  | 0.21914 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-25 | 2025-04-01 |  | AP-39 | AP-40 | 39¦40 | TSE |  | 0.786 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-26 | 2025-04-01 |  | AP-39 | AP-40 | 39¦40 | TSE |  | 0.786 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-27 | 2025-04-01 |  | AP-39 | AP-40 | 39¦40 | TSE |  | 0.786 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-28 | 2025-04-01 |  | AP-39 | AP-40 | 39¦40 | TSE |  | 0.786 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-29 | 2025-04-01 |  | AP-39 | AP-40 | 39¦40 | TSE |  | 0.786 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-04-30 | 2025-04-01 |  | AP-39 | AP-40 | 39¦40 | TSE |  | 0.786 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-08-27 | 2025-08-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-08-28 | 2025-08-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-08-29 | 2025-08-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-08-30 | 2025-08-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-08-31 | 2025-08-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-01 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-02 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-03 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-04 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-05 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-06 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-07 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-08 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-09 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-10 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-11 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-12 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-12 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-13 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-13 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-14 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-14 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-15 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-15 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-16 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-16 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-17 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-17 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-18 | 2025-09-01 |  | AP-7 | AP-7A | 7¦7A | TSE |  | 0.11736 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-18 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-19 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-20 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-21 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-22 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-23 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-24 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-09-25 | 2025-09-01 |  | AP-7A | AP-8 | 7A¦8 | TSE |  | 0.17391 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-03 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-04 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-05 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-05 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-06 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-06 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-07 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-07 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-08 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-08 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-09 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-09 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-10 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-10 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-11 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-11 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-12 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-12 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-13 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-13 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-14 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-14 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-15 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-15 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-16 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-16 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-17 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-17 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-18 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-18 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-19 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-19 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-20 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-20 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-21 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-21 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-22 | 2025-10-01 |  | AP-8 | AP-8A | 8¦8A | TSE |  | 0.2475 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-22 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-23 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-24 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-25 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-26 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-10-27 | 2025-10-01 |  | AP-8A | AP-9/0 | 8A¦9/0 | Manual |  | 0.018665 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-05 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-06 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-07 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-08 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-09 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-10 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-11 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-12 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-13 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-14 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-15 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-16 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-17 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-18 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-19 | 2025-11-01 |  | AP-6 | AP-7 | 6¦7 | TSE |  | 0.49012 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-19 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-20 | 2025-11-01 |  | AP-6 | AP-7 | 6¦7 | TSE |  | 0.49012 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-20 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-21 | 2025-11-01 |  | AP-6 | AP-7 | 6¦7 | TSE |  | 0.49012 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-21 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-22 | 2025-11-01 |  | AP-6 | AP-7 | 6¦7 | TSE |  | 0.49012 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-22 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-23 | 2025-11-01 |  | AP-6 | AP-7 | 6¦7 | TSE |  | 0.49012 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-23 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-24 | 2025-11-01 |  | AP-6 | AP-7 | 6¦7 | TSE |  | 0.49012 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-24 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-25 | 2025-11-01 |  | AP-6 | AP-7 | 6¦7 | TSE |  | 0.49012 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-25 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-26 | 2025-11-01 |  | AP-6 | AP-7 | 6¦7 | TSE |  | 0.49012 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-26 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-27 | 2025-11-01 |  | AP-6 | AP-7 | 6¦7 | TSE |  | 0.49012 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-27 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-28 | 2025-11-01 |  | AP-6 | AP-7 | 6¦7 | TSE |  | 0.49012 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-28 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-29 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-11-30 | 2025-11-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-01 | 2025-12-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-02 | 2025-12-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-03 | 2025-12-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-04 | 2025-12-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-05 | 2025-12-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-06 | 2025-12-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-07 | 2025-12-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-07 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-08 | 2025-12-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-08 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-09 | 2025-12-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-09 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-10 | 2025-12-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-10 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-11 | 2025-12-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-11 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-12 | 2025-12-01 |  | AP-5A | AP-6 | 5A¦6 | Manual |  | 0.011039 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-12 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-13 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-14 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-15 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-15 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-16 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-16 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-17 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-17 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-18 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-18 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-19 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-19 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-20 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-20 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-21 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-21 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-22 | 2025-12-01 |  | AP-5 | AP-5A | 5¦5A | TSE |  | 0.27615 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-22 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-23 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-24 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-25 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-26 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-27 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-27 | 2025-12-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-28 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-28 | 2025-12-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-29 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-29 | 2025-12-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-30 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-30 | 2025-12-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-31 | 2025-12-01 |  | AP-4A | AP-5/0 | 4A¦5/0 | TSE |  | 0.15774 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2025-12-31 | 2025-12-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-01 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-02 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-03 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-04 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-05 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-06 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-07 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-07 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-08 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-08 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-09 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-09 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-10 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-10 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-11 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-11 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-12 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-12 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-13 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-13 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-14 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-14 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-14 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-15 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-15 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-15 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-16 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-16 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-16 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-16 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-17 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-17 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-17 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-17 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-18 | 2026-01-01 |  | AP-4 | AP4A/0 | 4¦4A/0 | TSE |  | 0.030833 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-18 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-18 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-18 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-19 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-19 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-19 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-20 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-20 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-20 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-21 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-21 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-21 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-22 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-22 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-22 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-23 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-23 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-23 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-24 | 2026-01-01 |  | AP-33 | AP-34 | 33¦34 | TSE |  | 0.22499 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-24 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-24 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-25 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-25 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-25 | 2026-01-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-26 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-26 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-26 | 2026-01-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-27 | 2026-01-01 |  | AP3B/0 | AP4/0 | 3B/0¦4/0 | TSE |  | 0.11621 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-27 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-27 | 2026-01-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-28 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-28 | 2026-01-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-29 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-29 | 2026-01-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-30 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-30 | 2026-01-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-31 | 2026-01-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-01-31 | 2026-01-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-01 | 2026-02-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-01 | 2026-02-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-02 | 2026-02-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-02 | 2026-02-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-03 | 2026-02-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-03 | 2026-02-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-04 | 2026-02-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-04 | 2026-02-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-05 | 2026-02-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-05 | 2026-02-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-06 | 2026-02-01 |  | AP-32A | AP-33 | 32A¦33 | TSE |  | 0.038182 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-06 | 2026-02-01 |  | AP32/0 | AP32A/0 | 32/0¦32A/0 | TSE |  | 0.25262 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-08 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-09 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-10 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-10 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-11 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-11 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-12 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-12 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-13 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-13 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-14 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-14 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-14 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-15 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-15 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-15 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-16 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-16 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-16 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-17 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-17 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-17 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-18 | 2026-02-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-18 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-18 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-18 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-19 | 2026-02-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-19 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-19 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-19 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-20 | 2026-02-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-20 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-20 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-20 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-21 | 2026-02-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-21 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-21 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-21 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-22 | 2026-02-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-22 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-22 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-22 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-23 | 2026-02-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-23 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-23 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-23 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-24 | 2026-02-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-24 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-24 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-24 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-25 | 2026-02-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-25 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-25 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-25 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-26 | 2026-02-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-26 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-26 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-26 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-27 | 2026-02-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-27 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-27 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-27 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-27 | 2026-02-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-28 | 2026-02-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-28 | 2026-02-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-28 | 2026-02-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-28 | 2026-02-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-02-28 | 2026-02-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-01 | 2026-03-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-01 | 2026-03-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-01 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-01 | 2026-03-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-01 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-02 | 2026-03-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-02 | 2026-03-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-02 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-02 | 2026-03-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-02 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-03 | 2026-03-01 |  | 2A/0 | 3A/0 | 2A/0¦3A/0 | TSE |  | 0.20264 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-03 | 2026-03-01 |  | 3A/0 | 3B/0 | 3A/0¦3B/0 | TSE |  | 0.11214 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-03 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-03 | 2026-03-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-03 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-04 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-04 | 2026-03-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-04 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-05 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-05 | 2026-03-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-05 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-06 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-06 | 2026-03-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-06 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-07 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-07 | 2026-03-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-07 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-08 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-08 | 2026-03-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-08 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-09 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-09 | 2026-03-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-09 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-10 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-10 | 2026-03-01 |  | 31/0 | 32/0 | 31/0¦32/0 | TSE |  | 0.14941 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-10 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-11 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-11 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-12 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-12 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-13 | 2026-03-01 |  | 1/0 | 2A/0 | 1/0¦2A/0 | Manual |  | 0.010357 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-13 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-14 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-15 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-16 | 2026-03-01 |  | 30/0 | 31/0 | 30/0¦31/0 | TSE |  | 0.22911 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-28 | 2026-03-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-29 | 2026-03-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-30 | 2026-03-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-03-31 | 2026-03-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-01 | 2026-04-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-02 | 2026-04-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-03 | 2026-04-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-04 | 2026-04-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-05 | 2026-04-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-06 | 2026-04-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-07 | 2026-04-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-07 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-08 | 2026-04-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-08 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-09 | 2026-04-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-09 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-10 | 2026-04-01 |  | 9/0 | 10/0 | 10/0¦9/0 | TSE |  | 0.35464 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-10 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-11 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-12 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-13 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-14 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-15 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-16 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-17 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-18 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-19 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-20 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-21 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-22 | 2026-04-01 |  | 29A/0 | 30/0 | 29A/0¦30/0 | TSE |  | 0.22242 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-22 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-23 | 2026-04-01 |  | 29A/0 | 30/0 | 29A/0¦30/0 | TSE |  | 0.22242 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-23 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-24 | 2026-04-01 |  | 29A/0 | 30/0 | 29A/0¦30/0 | TSE |  | 0.22242 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-24 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-25 | 2026-04-01 |  | 29A/0 | 30/0 | 29A/0¦30/0 | TSE |  | 0.22242 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-25 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-26 | 2026-04-01 |  | 29A/0 | 30/0 | 29A/0¦30/0 | TSE |  | 0.22242 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-26 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-27 | 2026-04-01 |  | 29A/0 | 30/0 | 29A/0¦30/0 | TSE |  | 0.22242 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-27 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-28 | 2026-04-01 |  | 29A/0 | 30/0 | 29A/0¦30/0 | TSE |  | 0.22242 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-28 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-29 | 2026-04-01 |  | 29A/0 | 30/0 | 29A/0¦30/0 | TSE |  | 0.22242 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-29 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-30 | 2026-04-01 |  | 29A/0 | 30/0 | 29A/0¦30/0 | TSE |  | 0.22242 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-04-30 | 2026-04-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-01 | 2026-05-01 |  | 29A/0 | 30/0 | 29A/0¦30/0 | TSE |  | 0.22242 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-01 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-02 | 2026-05-01 |  | 29A/0 | 30/0 | 29A/0¦30/0 | TSE |  | 0.22242 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-02 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-03 | 2026-05-01 |  | 29A/0 | 30/0 | 29A/0¦30/0 | TSE |  | 0.22242 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-03 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-04 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-05 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-06 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-07 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-08 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-08 | 2026-05-01 |  | 29/0 | 29A/0 | 29/0¦29A/0 | TSE |  | 0.26436 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-09 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-09 | 2026-05-01 |  | 29/0 | 29A/0 | 29/0¦29A/0 | TSE |  | 0.26436 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-10 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-10 | 2026-05-01 |  | 29/0 | 29A/0 | 29/0¦29A/0 | TSE |  | 0.26436 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-11 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-11 | 2026-05-01 |  | 29/0 | 29A/0 | 29/0¦29A/0 | TSE |  | 0.26436 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-12 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-12 | 2026-05-01 |  | 29/0 | 29A/0 | 29/0¦29A/0 | TSE |  | 0.26436 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-13 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-13 | 2026-05-01 |  | 29/0 | 29A/0 | 29/0¦29A/0 | TSE |  | 0.26436 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-14 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-14 | 2026-05-01 |  | 29/0 | 29A/0 | 29/0¦29A/0 | TSE |  | 0.26436 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-15 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-15 | 2026-05-01 |  | 29/0 | 29A/0 | 29/0¦29A/0 | TSE |  | 0.26436 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-16 | 2026-05-01 |  | 10/0 | 11/0 | 10/0¦11/0 | TSE |  | 0.025105 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-16 | 2026-05-01 |  | 29/0 | 29A/0 | 29/0¦29A/0 | TSE |  | 0.26436 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-20 | 2026-05-01 |  | 27/0 | 28/0 | 27/0¦28/0 | TSE |  | 0.31853 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-21 | 2026-05-01 |  | 27/0 | 28/0 | 27/0¦28/0 | TSE |  | 0.31853 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-22 | 2026-05-01 |  | 27/0 | 28/0 | 27/0¦28/0 | TSE |  | 0.31853 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-23 | 2026-05-01 |  | 27/0 | 28/0 | 27/0¦28/0 | TSE |  | 0.31853 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-24 | 2026-05-01 |  | 27/0 | 28/0 | 27/0¦28/0 | TSE |  | 0.31853 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-25 | 2026-05-01 |  | 27/0 | 28/0 | 27/0¦28/0 | TSE |  | 0.31853 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-26 | 2026-05-01 |  | 27/0 | 28/0 | 27/0¦28/0 | TSE |  | 0.31853 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-05-27 | 2026-05-01 |  | 27/0 | 28/0 | 27/0¦28/0 | TSE |  | 0.31853 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-06-05 | 2026-06-01 |  | 11/0 | 12/0 | 11/0¦12/0 | Manual |  | 0.12144 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-06-06 | 2026-06-01 |  | 11/0 | 12/0 | 11/0¦12/0 | Manual |  | 0.12144 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-06-07 | 2026-06-01 |  | 14/0 | 15/0 | 14/0¦15/0 | Manual |  | 0.037303 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-06-08 | 2026-06-01 |  | 14/0 | 15/0 | 14/0¦15/0 | Manual |  | 0.037303 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-06-09 | 2026-06-01 |  | 14/0 | 15/0 | 14/0¦15/0 | Manual |  | 0.037303 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-06-10 | 2026-06-01 |  | 14/0 | 15/0 | 14/0¦15/0 | Manual |  | 0.037303 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-06-11 | 2026-06-01 |  | 14/0 | 15/0 | 14/0¦15/0 | Manual |  | 0.037303 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 413 | TA 413 | ta413 |  | 2026-06-12 | 2026-06-01 |  | 14/0 | 15/0 | 14/0¦15/0 | Manual |  | 0.037303 |  |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-04-05 | 2026-04-01 | Sanjay Singh | 182/0 | 183/0 | 182/0¦183/0 | Hotline | Complete | 0.029844 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-06 | 2026-04-01 | Alam Construction | 180/2 | 182/0 | 180/2¦182/0 | TSE | Complete | 0.21933 |  | 68 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-06 | 2026-04-01 | Maa Singhvahini | 175/1 | 176/0 | 175/1¦176/0 | Manual | Complete | 0.063647 |  | 27 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-06 | 2026-04-01 | Sanjay Singh | 182/0 | 183/0 | 182/0¦183/0 | Hotline | Complete | 0.029844 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-07 | 2026-04-01 | Alam Construction | 180/2 | 182/0 | 180/2¦182/0 | TSE | Complete | 0.21933 |  | 68 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-07 | 2026-04-01 | Maa Singhvahini | 175/1 | 176/0 | 175/1¦176/0 | Manual | Complete | 0.063647 |  | 27 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-07 | 2026-04-01 | Sanjay Singh | 182/0 | 183/0 | 182/0¦183/0 | Hotline | Complete | 0.029844 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-08 | 2026-04-01 | Alam Construction | 180/2 | 182/0 | 180/2¦182/0 | TSE | Complete | 0.21933 |  | 68 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-08 | 2026-04-01 | Maa Singhvahini | 175/1 | 176/0 | 175/1¦176/0 | Manual | Complete | 0.063647 |  | 27 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-08 | 2026-04-01 | Sanjay Singh | 182/0 | 183/0 | 182/0¦183/0 | Hotline | Complete | 0.029844 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-09 | 2026-04-01 | Alam Construction | 180/2 | 182/0 | 180/2¦182/0 | TSE | Complete | 0.21933 |  | 68 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-09 | 2026-04-01 | Maa Singhvahini | 175/1 | 176/0 | 175/1¦176/0 | Manual | Complete | 0.063647 |  | 27 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-09 | 2026-04-01 | Sanjay Singh | 182/0 | 183/0 | 182/0¦183/0 | Hotline | Complete | 0.029844 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-10 | 2026-04-01 | Alam Construction | 180/2 | 182/0 | 180/2¦182/0 | TSE | Complete | 0.21933 |  | 68 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-10 | 2026-04-01 | Maa Singhvahini | 175/1 | 176/0 | 175/1¦176/0 | Manual | Complete | 0.063647 |  | 27 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-10 | 2026-04-01 | Sanjay Singh | 182/0 | 183/0 | 182/0¦183/0 | Hotline | Complete | 0.029844 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-11 | 2026-04-01 | Alam Construction | 180/2 | 182/0 | 180/2¦182/0 | TSE | Complete | 0.21933 |  | 68 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-11 | 2026-04-01 | Bhola prasad+ Deepak Sarkar | 245/0 | 246/0 | 245/0¦246/0 | Manual | Complete | 0.15833 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-11 | 2026-04-01 | Maa Singhvahini | 175/1 | 176/0 | 175/1¦176/0 | Manual | Complete | 0.063647 |  | 27 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-11 | 2026-04-01 | Sanjay Singh | 182/0 | 183/0 | 182/0¦183/0 | Hotline | Complete | 0.029844 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-12 | 2026-04-01 | Alam Construction | 180/2 | 182/0 | 180/2¦182/0 | TSE | Complete | 0.21933 |  | 68 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-12 | 2026-04-01 | Bhola prasad+ Deepak Sarkar | 245/0 | 246/0 | 245/0¦246/0 | Manual | Complete | 0.15833 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-12 | 2026-04-01 | Maa Singhvahini | 175/1 | 176/0 | 175/1¦176/0 | Manual | Complete | 0.063647 |  | 27 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-13 | 2026-04-01 | Alam Construction | 180/2 | 182/0 | 180/2¦182/0 | TSE | Complete | 0.21933 |  | 68 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-13 | 2026-04-01 | Bhola prasad+ Deepak Sarkar | 245/0 | 246/0 | 245/0¦246/0 | Manual | Complete | 0.15833 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-13 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-14 | 2026-04-01 | Alam Construction | 180/2 | 182/0 | 180/2¦182/0 | TSE | Complete | 0.21933 |  | 68 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-14 | 2026-04-01 | Bhola prasad+ Deepak Sarkar | 245/0 | 246/0 | 245/0¦246/0 | Manual | Complete | 0.15833 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-14 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-15 | 2026-04-01 | Alam Construction | 180/2 | 182/0 | 180/2¦182/0 | TSE | Complete | 0.21933 |  | 68 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-15 | 2026-04-01 | Bhola prasad+ Deepak Sarkar | 245/0 | 246/0 | 245/0¦246/0 | Manual | Complete | 0.15833 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-15 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-16 | 2026-04-01 | Alam Construction | 180/2 | 182/0 | 180/2¦182/0 | TSE | Complete | 0.21933 |  | 68 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-16 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-17 | 2026-04-01 |  | 198/0 | 199/0 | 198/0¦199/0 | Hotline | Complete | 0.035249 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-04-17 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-18 | 2026-04-01 |  | 198/0 | 199/0 | 198/0¦199/0 | Hotline | Complete | 0.035249 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-04-18 | 2026-04-01 | Alam Construction | 183/0 | 184/0 | 183/0¦184/0 | TSE | Complete | 0.29588 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-18 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-19 | 2026-04-01 |  | 198/0 | 199/0 | 198/0¦199/0 | Hotline | Complete | 0.035249 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-04-19 | 2026-04-01 | Alam Construction | 183/0 | 184/0 | 183/0¦184/0 | TSE | Complete | 0.29588 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-19 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-20 | 2026-04-01 |  | 198/0 | 199/0 | 198/0¦199/0 | Hotline | Complete | 0.035249 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-04-20 | 2026-04-01 | Alam Construction | 183/0 | 184/0 | 183/0¦184/0 | TSE | Complete | 0.29588 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-20 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-21 | 2026-04-01 |  | 198/0 | 199/0 | 198/0¦199/0 | Hotline | Complete | 0.035249 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-04-21 | 2026-04-01 | Alam Construction | 183/0 | 184/0 | 183/0¦184/0 | TSE | Complete | 0.29588 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-21 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-22 | 2026-04-01 |  | 198/0 | 199/0 | 198/0¦199/0 | Hotline | Complete | 0.035249 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-04-22 | 2026-04-01 | Alam Construction | 183/0 | 184/0 | 183/0¦184/0 | TSE | Complete | 0.29588 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-22 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-23 | 2026-04-01 |  | 198/0 | 199/0 | 198/0¦199/0 | Hotline | Complete | 0.035249 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-04-23 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-24 | 2026-04-01 | Alam Construction | 176/0 | 177/0 | 176/0¦177/0 | TSE | Complete | 0.20867 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-24 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-25 | 2026-04-01 | Alam Construction | 176/0 | 177/0 | 176/0¦177/0 | TSE | Complete | 0.20867 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-25 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-26 | 2026-04-01 | Alam Construction | 176/0 | 177/0 | 176/0¦177/0 | TSE | Complete | 0.20867 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-26 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-27 | 2026-04-01 | Alam Construction | 176/0 | 177/0 | 176/0¦177/0 | TSE | Complete | 0.20867 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-27 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-28 | 2026-04-01 | Alam Construction | 176/0 | 177/0 | 176/0¦177/0 | TSE | Complete | 0.20867 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-28 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-29 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-04-30 | 2026-04-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-01 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-02 | 2026-05-01 | Alam Construction | 175/0 | 175/1 | 175/0¦175/1 | Hotline | Complete | 0.078 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-02 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-03 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-03 | 2026-05-01 | Alam Construction | 175/0 | 175/1 | 175/0¦175/1 | Hotline | Complete | 0.078 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-03 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-03 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-04 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-04 | 2026-05-01 | Alam Construction | 175/0 | 175/1 | 175/0¦175/1 | Hotline | Complete | 0.078 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-04 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-04 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-05 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-05 | 2026-05-01 | Alam Construction | 175/0 | 175/1 | 175/0¦175/1 | Hotline | Complete | 0.078 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-05 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-05 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-06 | 2026-05-01 |  | 184/0 | 185/0 | 184/0¦185/0 | Hotline | Complete | 0.026271 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-05-06 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-06 | 2026-05-01 | Alam Construction | 175/0 | 175/1 | 175/0¦175/1 | Hotline | Complete | 0.078 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-06 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-06 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-07 | 2026-05-01 |  | 184/0 | 185/0 | 184/0¦185/0 | Hotline | Complete | 0.026271 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-05-07 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-07 | 2026-05-01 | Alam Construction | 175/0 | 175/1 | 175/0¦175/1 | Hotline | Complete | 0.078 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-07 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-07 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-08 | 2026-05-01 |  | 184/0 | 185/0 | 184/0¦185/0 | Hotline | Complete | 0.026271 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-05-08 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-08 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-08 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-09 | 2026-05-01 |  | 184/0 | 185/0 | 184/0¦185/0 | Hotline | Complete | 0.026271 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-05-09 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-09 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-09 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-10 | 2026-05-01 |  | 184/0 | 185/0 | 184/0¦185/0 | Hotline | Complete | 0.026271 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-05-10 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-10 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-10 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-11 | 2026-05-01 |  | 184/0 | 185/0 | 184/0¦185/0 | Hotline | Complete | 0.026271 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-05-11 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-11 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-11 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-12 | 2026-05-01 |  | 184/0 | 185/0 | 184/0¦185/0 | Hotline | Complete | 0.026271 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-05-12 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-12 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-12 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-13 | 2026-05-01 |  | 184/0 | 185/0 | 184/0¦185/0 | Hotline | Complete | 0.026271 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | NO_DATA | No manpower values found for this span/day.
TA 414 | TA 414 | ta414 |  | 2026-05-13 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-13 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-13 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-14 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-14 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-14 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-15 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-15 | 2026-05-01 | Enamul Haque | 120/0 | 121/0 | 120/0¦121/0 | TSE | Complete | 0.22013 |  | 49 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-15 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-15 | 2026-05-01 | Sanjay singh 2 | 177/0 | 178/0 | 177/0¦178/0 | Hotline | Complete | 0.038015 |  | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-16 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-16 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-16 | 2026-05-01 | Sanjay singh 2 | 177/0 | 178/0 | 177/0¦178/0 | Hotline | Complete | 0.038015 |  | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-17 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-17 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-17 | 2026-05-01 | Sanjay singh 2 | 177/0 | 178/0 | 177/0¦178/0 | Hotline | Complete | 0.038015 |  | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-18 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-18 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-18 | 2026-05-01 | Sanjay singh 2 | 177/0 | 178/0 | 177/0¦178/0 | Hotline | Complete | 0.038015 |  | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-19 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-19 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-19 | 2026-05-01 | Sanjay singh 2 | 177/0 | 178/0 | 177/0¦178/0 | Hotline | Complete | 0.038015 |  | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-20 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-20 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-20 | 2026-05-01 | Sanjay singh 2 | 177/0 | 178/0 | 177/0¦178/0 | Hotline | Complete | 0.038015 |  | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-21 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-21 | 2026-05-01 | Enamul Haque | 121/1 | 121/7 | 121/1¦121/7 | TSE | Complete | 0.058564 |  | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-22 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-23 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-24 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-25 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-26 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-27 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-28 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-29 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-30 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-05-31 | 2026-05-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-06-01 | 2026-06-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-06-02 | 2026-06-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-06-03 | 2026-06-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 414 | TA 414 | ta414 |  | 2026-06-04 | 2026-06-01 | Alam Construction | 174/0 | 175/0 | 174/0¦175/0 | TSE | Complete | 0.079799 |  | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | unknown | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 416 | TA 416 | ta416 |  | 2025-05-03 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-04 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-05 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-06 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-07 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-08 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-09 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-10 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-11 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-12 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-13 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-14 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-14 | 2025-05-01 | ANARUL ISLAM | AP6/0 | AP7/0 | 6/0¦7/0 | TSE | Ready | 0.15429 | 1.2343 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-15 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-15 | 2025-05-01 | ANARUL ISLAM | AP6/0 | AP7/0 | 6/0¦7/0 | TSE | Ready | 0.15429 | 1.2343 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-16 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-16 | 2025-05-01 | ANARUL ISLAM | AP6/0 | AP7/0 | 6/0¦7/0 | TSE | Ready | 0.15429 | 1.2343 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-17 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-17 | 2025-05-01 | ANARUL ISLAM | AP6/0 | AP7/0 | 6/0¦7/0 | TSE | Ready | 0.15429 | 1.2343 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-18 | 2025-05-01 | ANARUL ISLAM | AP7/0 | AP8/0 | 7/0¦8/0 | TSE | Ready | 0.30117 | 4.8187 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-18 | 2025-05-01 | ANARUL ISLAM | AP6/0 | AP7/0 | 6/0¦7/0 | TSE | Ready | 0.15429 | 1.2343 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-18 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-19 | 2025-05-01 | ANARUL ISLAM | AP6/0 | AP7/0 | 6/0¦7/0 | TSE | Ready | 0.15429 | 1.2343 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-19 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-20 | 2025-05-01 | ANARUL ISLAM | AP6/0 | AP7/0 | 6/0¦7/0 | TSE | Ready | 0.15429 | 1.2343 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-20 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-21 | 2025-05-01 | ANARUL ISLAM | AP6/0 | AP7/0 | 6/0¦7/0 | TSE | Ready | 0.15429 | 1.2343 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-21 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-22 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-23 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-24 | 2025-05-01 | ANARUL ISLAM | AP8/0 | AP8A/0 | 8/0¦8A/0 | TSE | Ready | 0.25209 | 2.0167 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-24 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-25 | 2025-05-01 | ANARUL ISLAM | AP8/0 | AP8A/0 | 8/0¦8A/0 | TSE | Ready | 0.25209 | 2.0167 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-25 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-26 | 2025-05-01 | ANARUL ISLAM | AP8/0 | AP8A/0 | 8/0¦8A/0 | TSE | Ready | 0.25209 | 2.0167 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-26 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-27 | 2025-05-01 | ANARUL ISLAM | AP8/0 | AP8A/0 | 8/0¦8A/0 | TSE | Ready | 0.25209 | 2.0167 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-27 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-28 | 2025-05-01 | ANARUL ISLAM | AP8/0 | AP8A/0 | 8/0¦8A/0 | TSE | Ready | 0.25209 | 2.0167 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-28 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-29 | 2025-05-01 | ANARUL ISLAM | AP8/0 | AP8A/0 | 8/0¦8A/0 | TSE | Ready | 0.25209 | 2.0167 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-29 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-30 | 2025-05-01 | ANARUL ISLAM | AP8/0 | AP8A/0 | 8/0¦8A/0 | TSE | Ready | 0.25209 | 2.0167 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-30 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-31 | 2025-05-01 | ANARUL ISLAM | AP8/0 | AP8A/0 | 8/0¦8A/0 | TSE | Ready | 0.25209 | 2.0167 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-05-31 | 2025-05-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-01 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-02 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-02 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-03 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-03 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-04 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-04 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-05 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-05 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-06 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-06 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-07 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-07 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-08 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-08 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-09 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-09 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-10 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-10 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-11 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-11 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-12 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-12 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-13 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-13 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-14 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-14 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-15 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-15 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-16 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-16 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-17 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-17 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-17 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-18 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-18 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-18 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-18 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-19 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-19 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-19 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-19 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-20 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-20 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-20 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-20 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-21 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-21 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-21 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-21 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-22 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-22 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-22 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-22 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-23 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-23 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-23 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-23 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-24 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-24 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-24 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-24 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-25 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-25 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-25 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-25 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-26 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-26 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-26 | 2025-06-01 | S K INFRA | AP31/0 | AP32/0 | 31/0¦32/0 | TSE | Ready | 0.17135 | 4.2837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-26 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-27 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-27 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-27 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-28 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-28 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-28 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-29 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-29 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-29 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-30 | 2025-06-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-30 | 2025-06-01 | S K INFRA | AP35/0 | AP36/0 | 35/0¦36/0 | TSE | Ready | 0.089933 | 3.9571 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-06-30 | 2025-06-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-01 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-01 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-02 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-02 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-03 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-03 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-04 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-04 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-05 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-05 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-06 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-06 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-07 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-07 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-08 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-08 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-09 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-09 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-10 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-10 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-11 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-11 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-12 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-12 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-13 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-13 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-14 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-14 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-15 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-15 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-15 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-16 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-16 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-16 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-17 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-17 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-17 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-17 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-18 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-18 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-18 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-18 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-19 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-19 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-19 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-19 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-20 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-20 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-20 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-20 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-21 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-21 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-21 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-21 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-22 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-22 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-22 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-22 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-23 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-23 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-23 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-23 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-24 | 2025-07-01 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 8A/0¦8B/0 | Manual | Ready | 0.0058845 | 0.22361 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-24 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-24 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-24 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-25 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-25 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-25 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-26 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-26 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-26 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-27 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-27 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-27 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-28 | 2025-07-01 | ANARUL ISLAM | AP8B/0 | AP9/0 | 8B/0¦9/0 | TSE | Ready | 0.15902 | 2.2262 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-28 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-28 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-29 | 2025-07-01 | S K INFRA | AP32/0 | AP33/0 | 32/0¦33/0 | Manual | Ready | 0.0096945 | 0.40717 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-07-29 | 2025-07-01 | S K INFRA | AP33/0 | AP34/0 | 33/0¦34/0 | TSE | Ready | 0.36781 | 4.7815 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-05 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-06 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-07 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-08 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-09 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-10 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-11 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-11 | 2025-08-01 | ANARUL ISLAM | AP9/0 | AP10/0 | 10/0¦9/0 | Manual | Ready | 0.14172 | 0.28343 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-11 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-12 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-12 | 2025-08-01 | ANARUL ISLAM | AP9/0 | AP10/0 | 10/0¦9/0 | Manual | Ready | 0.14172 | 0.28343 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-12 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-13 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-13 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-14 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-14 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-15 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-15 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-16 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-16 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-17 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-17 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-18 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-18 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-19 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-19 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-20 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-20 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-21 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-21 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-22 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-22 | 2025-08-01 | ANARUL ISLAM | AP4/0 | AP5/0 | 4/0¦5/0 | TSE | Ready | 0.44157 | 4.4157 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-22 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-23 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-23 | 2025-08-01 | ANARUL ISLAM | AP4/0 | AP5/0 | 4/0¦5/0 | TSE | Ready | 0.44157 | 4.4157 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-23 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-24 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-24 | 2025-08-01 | ANARUL ISLAM | AP4/0 | AP5/0 | 4/0¦5/0 | TSE | Ready | 0.44157 | 4.4157 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-24 | 2025-08-01 | S K INFRA | AP34/0 | AP35/0 | 34/0¦35/0 | TSE | Ready | 0.22809 | 3.1932 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-25 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-25 | 2025-08-01 | ANARUL ISLAM | AP4/0 | AP5/0 | 4/0¦5/0 | TSE | Ready | 0.44157 | 4.4157 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-26 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-26 | 2025-08-01 | ANARUL ISLAM | AP4/0 | AP5/0 | 4/0¦5/0 | TSE | Ready | 0.44157 | 4.4157 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-27 | 2025-08-01 | ANARUL ISLAM | AP5/0 | AP6/0 | 5/0¦6/0 | TSE | Ready | 0.03146 | 0.72357 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-27 | 2025-08-01 | ANARUL ISLAM | AP4/0 | AP5/0 | 4/0¦5/0 | TSE | Ready | 0.44157 | 4.4157 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-28 | 2025-08-01 | ANARUL ISLAM | AP4/0 | AP5/0 | 4/0¦5/0 | TSE | Ready | 0.44157 | 4.4157 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-29 | 2025-08-01 | ANARUL ISLAM | AP4/0 | AP5/0 | 4/0¦5/0 | TSE | Ready | 0.44157 | 4.4157 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-30 | 2025-08-01 | ANARUL ISLAM | AP4/0 | AP5/0 | 4/0¦5/0 | TSE | Ready | 0.44157 | 4.4157 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-08-31 | 2025-08-01 | ANARUL ISLAM | AP4/0 | AP5/0 | 4/0¦5/0 | TSE | Ready | 0.44157 | 4.4157 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-05 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-05 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-06 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-06 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-07 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-07 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-08 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-08 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-09 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-09 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-10 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-10 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-11 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-11 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-12 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-12 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-13 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-13 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-14 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-14 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-15 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-15 | 2025-09-01 | ANARUL ISLAM | AP3/0 | AP4/0 | 3/0¦4/0 | Manual | Ready | 0.14 | 0.28 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-15 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-16 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-16 | 2025-09-01 | ANARUL ISLAM | AP3/0 | AP4/0 | 3/0¦4/0 | Manual | Ready | 0.14 | 0.28 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-16 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-17 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-17 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-18 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-18 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-19 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-19 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-20 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-20 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-21 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-21 | 2025-09-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-21 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-21 | 2025-09-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-22 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-22 | 2025-09-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-22 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-22 | 2025-09-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-23 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-23 | 2025-09-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-23 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-23 | 2025-09-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-24 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-24 | 2025-09-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-24 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-24 | 2025-09-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-25 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-25 | 2025-09-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-25 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-25 | 2025-09-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-26 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-26 | 2025-09-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-26 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-26 | 2025-09-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-27 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-27 | 2025-09-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-27 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-27 | 2025-09-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-28 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-28 | 2025-09-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-28 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-28 | 2025-09-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-29 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-29 | 2025-09-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-29 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-29 | 2025-09-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-30 | 2025-09-01 | ANARUL ISLAM | AP14/0 | AP15/0 | 14/0¦15/0 | TSE | Ready | 0.13888 | 3.611 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-30 | 2025-09-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-30 | 2025-09-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-09-30 | 2025-09-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-01 | 2025-10-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-01 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-01 | 2025-10-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-02 | 2025-10-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-02 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-02 | 2025-10-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-03 | 2025-10-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-03 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-03 | 2025-10-01 | S K INFRA | AP30/0 | AP31/0 | 30/0¦31/0 | TSE | Ready | 0.21157 | 2.7505 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-04 | 2025-10-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-04 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-05 | 2025-10-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-05 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-06 | 2025-10-01 | J PG CON | AP20/0 | AP21/0 | 20/0¦21/0 | TSE | Ready | 0.30987 | 4.958 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-06 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-07 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-08 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-09 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-10 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-11 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-12 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-12 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-13 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-13 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-14 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-14 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-14 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-15 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-15 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-15 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-16 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-16 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-16 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-17 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-17 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-17 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-18 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-18 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-18 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-19 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-19 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-19 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-20 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-20 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-20 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-21 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-21 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-21 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-22 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-22 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-22 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-23 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-23 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-23 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-24 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-24 | 2025-10-01 | J PG CON | AP21/0 | AP22/0 | 21/0¦22/0 | TSE | Ready | 0.3212 | 1.606 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-24 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-24 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-25 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-25 | 2025-10-01 | J PG CON | AP21/0 | AP22/0 | 21/0¦22/0 | TSE | Ready | 0.3212 | 1.606 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-25 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-25 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-26 | 2025-10-01 | ANARUL ISLAM | AP12/0 | AP13/0 | 12/0¦13/0 | TSE | Ready | 0.26133 | 3.92 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-26 | 2025-10-01 | J PG CON | AP21/0 | AP22/0 | 21/0¦22/0 | TSE | Ready | 0.3212 | 1.606 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-26 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-26 | 2025-10-01 | S K INFRA | AP39/0 | AP40/0 | 39/0¦40/0 | TSE | Ready | 0.34312 | 4.4605 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-27 | 2025-10-01 | J PG CON | AP21/0 | AP22/0 | 21/0¦22/0 | TSE | Ready | 0.3212 | 1.606 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-27 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-28 | 2025-10-01 | J PG CON | AP21/0 | AP22/0 | 21/0¦22/0 | TSE | Ready | 0.3212 | 1.606 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-28 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-29 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-30 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-10-31 | 2025-10-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-01 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-02 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-02 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-03 | 2025-11-01 | ANARUL ISLAM | AP13/0 | AP14/0 | 13/0¦14/0 | Manual | Ready | 0.15957 | 0.31913 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-03 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-03 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-04 | 2025-11-01 | ANARUL ISLAM | AP13/0 | AP14/0 | 13/0¦14/0 | Manual | Ready | 0.15957 | 0.31913 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-04 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-04 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-05 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-05 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-06 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-06 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-06 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-07 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-07 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-07 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-08 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-08 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-08 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-09 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-09 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-09 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-10 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-10 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-10 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-11 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-11 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-11 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-12 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-12 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-12 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-13 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-13 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-13 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-14 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-14 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-14 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-15 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-15 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-15 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-16 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-16 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-16 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-17 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-17 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-17 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-17 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-18 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-18 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-18 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-18 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-19 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-19 | 2025-11-01 | J PG CON | AP19/0 | AP20/0 | 19/0¦20/0 | TSE | Ready | 0.35646 | 4.9905 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-19 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-19 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-20 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-20 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-20 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-21 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-21 | 2025-11-01 | J PG CON | AP18/0 | AP19/0 | 18/0¦19/0 | Manual | Ready | 0.0646 | 0.323 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-21 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-21 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-22 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-22 | 2025-11-01 | ANARUL ISLAM | AP15/0 | AP16/0 | 15/0¦16/0 | Manual | Ready | 0.0775 | 0.465 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-22 | 2025-11-01 | J PG CON | AP18/0 | AP19/0 | 18/0¦19/0 | Manual | Ready | 0.0646 | 0.323 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-22 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-22 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-23 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-23 | 2025-11-01 | ANARUL ISLAM | AP15/0 | AP16/0 | 15/0¦16/0 | Manual | Ready | 0.0775 | 0.465 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-23 | 2025-11-01 | J PG CON | AP18/0 | AP19/0 | 18/0¦19/0 | Manual | Ready | 0.0646 | 0.323 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-23 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-23 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-24 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-24 | 2025-11-01 | ANARUL ISLAM | AP15/0 | AP16/0 | 15/0¦16/0 | Manual | Ready | 0.0775 | 0.465 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-24 | 2025-11-01 | J PG CON | AP18/0 | AP19/0 | 18/0¦19/0 | Manual | Ready | 0.0646 | 0.323 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-24 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-24 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-25 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-25 | 2025-11-01 | ANARUL ISLAM | AP15/0 | AP16/0 | 15/0¦16/0 | Manual | Ready | 0.0775 | 0.465 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-25 | 2025-11-01 | J PG CON | AP18/0 | AP19/0 | 18/0¦19/0 | Manual | Ready | 0.0646 | 0.323 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-25 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-25 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-26 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-26 | 2025-11-01 | ANARUL ISLAM | AP15/0 | AP16/0 | 15/0¦16/0 | Manual | Ready | 0.0775 | 0.465 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-26 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-26 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-27 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-27 | 2025-11-01 | ANARUL ISLAM | AP15/0 | AP16/0 | 15/0¦16/0 | Manual | Ready | 0.0775 | 0.465 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-27 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-27 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-28 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-28 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-28 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-29 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-29 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-29 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-30 | 2025-11-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-30 | 2025-11-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-11-30 | 2025-11-01 | S K INFRA | AP38/0 | AP39/0 | 38/0¦39/0 | TSE | Ready | 0.1663 | 4.8228 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-01 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-01 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-02 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-02 | 2025-12-01 | ANARUL ISLAM | AP10/0 | AP11/0 | 10/0¦11/0 | TSE | Ready | 0.1644 | 0.822 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-02 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-03 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-03 | 2025-12-01 | ANARUL ISLAM | AP10/0 | AP11/0 | 10/0¦11/0 | TSE | Ready | 0.1644 | 0.822 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-03 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-04 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-04 | 2025-12-01 | ANARUL ISLAM | AP10/0 | AP11/0 | 10/0¦11/0 | TSE | Ready | 0.1644 | 0.822 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-04 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-05 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-05 | 2025-12-01 | ANARUL ISLAM | AP10/0 | AP11/0 | 10/0¦11/0 | TSE | Ready | 0.1644 | 0.822 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-05 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-05 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-06 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-06 | 2025-12-01 | ANARUL ISLAM | AP10/0 | AP11/0 | 10/0¦11/0 | TSE | Ready | 0.1644 | 0.822 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-06 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-06 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-07 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-07 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-07 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-08 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-08 | 2025-12-01 | ANARUL ISLAM | AP11/0 | AP12/0 | 11/0¦12/0 | Manual | Ready | 0.0626 | 0.313 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-08 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-08 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-09 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-09 | 2025-12-01 | ANARUL ISLAM | AP11/0 | AP12/0 | 11/0¦12/0 | Manual | Ready | 0.0626 | 0.313 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-09 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-09 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-10 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-10 | 2025-12-01 | ANARUL ISLAM | AP11/0 | AP12/0 | 11/0¦12/0 | Manual | Ready | 0.0626 | 0.313 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-10 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-10 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-11 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-11 | 2025-12-01 | ANARUL ISLAM | AP11/0 | AP12/0 | 11/0¦12/0 | Manual | Ready | 0.0626 | 0.313 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-11 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-11 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-12 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-12 | 2025-12-01 | ANARUL ISLAM | AP11/0 | AP12/0 | 11/0¦12/0 | Manual | Ready | 0.0626 | 0.313 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-12 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-12 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-13 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-13 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-13 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-14 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-14 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-14 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-15 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-15 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-15 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-16 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-16 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-16 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-17 | 2025-12-01 | AE Solution | AP1/0 | AP2/0 | 1/0¦2/0 | Manual | Ready | 0.041 | 0.246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-17 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-17 | 2025-12-01 | S K INFRA | AP36/0 | AP37/0 | 36/0¦37/0 | TSE | Ready | 0.04757 | 4.9473 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-17 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-18 | 2025-12-01 | AE Solution | AP1/0 | AP2/0 | 1/0¦2/0 | Manual | Ready | 0.041 | 0.246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-18 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-18 | 2025-12-01 | S K INFRA | AP37/0 | AP38/0 | 37/0¦38/0 | Manual | Ready | 0.034 | 0.476 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-19 | 2025-12-01 | AE Solution | AP1/0 | AP2/0 | 1/0¦2/0 | Manual | Ready | 0.041 | 0.246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-19 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-20 | 2025-12-01 | AE Solution | AP1/0 | AP2/0 | 1/0¦2/0 | Manual | Ready | 0.041 | 0.246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-20 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-21 | 2025-12-01 | AE Solution | AP1/0 | AP2/0 | 1/0¦2/0 | Manual | Ready | 0.041 | 0.246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-21 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-21 | 2025-12-01 | ANARUL ISLAM | AP0/0 | AP1/0 | 0/0¦1/0 | TSE | Ready | 0.17473 | 1.922 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-22 | 2025-12-01 | AE Solution | AP1/0 | AP2/0 | 1/0¦2/0 | Manual | Ready | 0.041 | 0.246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-22 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-22 | 2025-12-01 | ANARUL ISLAM | AP0/0 | AP1/0 | 0/0¦1/0 | TSE | Ready | 0.17473 | 1.922 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-23 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-23 | 2025-12-01 | ANARUL ISLAM | AP0/0 | AP1/0 | 0/0¦1/0 | TSE | Ready | 0.17473 | 1.922 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-24 | 2025-12-01 | AE Solution | AP24/0 | AP25/0 | 24/0¦25/0 | Manual | Ready | 0.033076 | 0.23153 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-24 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-24 | 2025-12-01 | ANARUL ISLAM | AP0/0 | AP1/0 | 0/0¦1/0 | TSE | Ready | 0.17473 | 1.922 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-24 | 2025-12-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-25 | 2025-12-01 | AE Solution | AP24/0 | AP25/0 | 24/0¦25/0 | Manual | Ready | 0.033076 | 0.23153 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-25 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-25 | 2025-12-01 | ANARUL ISLAM | AP0/0 | AP1/0 | 0/0¦1/0 | TSE | Ready | 0.17473 | 1.922 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-25 | 2025-12-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-26 | 2025-12-01 | AE Solution | AP24/0 | AP25/0 | 24/0¦25/0 | Manual | Ready | 0.033076 | 0.23153 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-26 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-26 | 2025-12-01 | ANARUL ISLAM | AP0/0 | AP1/0 | 0/0¦1/0 | TSE | Ready | 0.17473 | 1.922 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-26 | 2025-12-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-26 | 2025-12-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-27 | 2025-12-01 | AE Solution | AP24/0 | AP25/0 | 24/0¦25/0 | Manual | Ready | 0.033076 | 0.23153 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-27 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-27 | 2025-12-01 | ANARUL ISLAM | AP0/0 | AP1/0 | 0/0¦1/0 | TSE | Ready | 0.17473 | 1.922 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-27 | 2025-12-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-27 | 2025-12-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-28 | 2025-12-01 | AE Solution | AP24/0 | AP25/0 | 24/0¦25/0 | Manual | Ready | 0.033076 | 0.23153 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-28 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-28 | 2025-12-01 | ANARUL ISLAM | AP0/0 | AP1/0 | 0/0¦1/0 | TSE | Ready | 0.17473 | 1.922 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-28 | 2025-12-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-28 | 2025-12-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-29 | 2025-12-01 | AE Solution | AP24/0 | AP25/0 | 24/0¦25/0 | Manual | Ready | 0.033076 | 0.23153 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-29 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-29 | 2025-12-01 | ANARUL ISLAM | AP0/0 | AP1/0 | 0/0¦1/0 | TSE | Ready | 0.17473 | 1.922 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-29 | 2025-12-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-29 | 2025-12-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-30 | 2025-12-01 | AE Solution | AP24/0 | AP25/0 | 24/0¦25/0 | Manual | Ready | 0.033076 | 0.23153 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-30 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-30 | 2025-12-01 | ANARUL ISLAM | AP0/0 | AP1/0 | 0/0¦1/0 | TSE | Ready | 0.17473 | 1.922 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-30 | 2025-12-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-30 | 2025-12-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-31 | 2025-12-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-31 | 2025-12-01 | ANARUL ISLAM | AP0/0 | AP1/0 | 0/0¦1/0 | TSE | Ready | 0.17473 | 1.922 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-31 | 2025-12-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-31 | 2025-12-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2025-12-31 | 2025-12-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-01 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-01 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-01 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-01 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-02 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-02 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-02 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-02 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-03 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-03 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-03 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-03 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-04 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-04 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-04 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-04 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-05 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-05 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-05 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-05 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-06 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-06 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-06 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-06 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-07 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-07 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-07 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-07 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-08 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-08 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-08 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-08 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-09 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-09 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-09 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-09 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-09 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-10 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-10 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-10 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-10 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-10 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-11 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-11 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-11 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-11 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-11 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-12 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-12 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-12 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-12 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-12 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-13 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-13 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-13 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-13 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-13 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-13 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-14 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-14 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-14 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-14 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-14 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-14 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-15 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-15 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-15 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-15 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-15 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-15 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-16 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-16 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-16 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-16 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-16 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-16 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-17 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-17 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-17 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-17 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-17 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-17 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-18 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-18 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-18 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-18 | 2026-01-01 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 40/0¦41/0 | Manual | Ready | 0.0092038 | 0.2393 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-18 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-18 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-19 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-19 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-19 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-19 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-19 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-20 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-20 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-20 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-20 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-20 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-21 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-21 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-21 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-21 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-21 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-22 | 2026-01-01 | AE Solution(Company) | AP26/0 | AP27/0 | 26/0¦27/0 | Manual | Ready | 0.031489 | 0.44084 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-22 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-22 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-22 | 2026-01-01 | Jahangir(Company) | AP23/0 | AP24/0 | 23/0¦24/0 | TSE | Ready | 0.079545 | 2.2273 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-22 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-23 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-23 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-23 | 2026-01-01 | Bhola prasad(Company)+Sing Bahini | AP25/0 | AP26/0 | 25/0¦26/0 | TSE | Ready | 0.18516 | 1.6664 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-23 | 2026-01-01 | Ramawat-Hot line | AP16/0 | AP17/0 | 16/0¦17/0 | Manual | Ready | 0.011041 | 0.26498 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-24 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-24 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-24 | 2026-01-01 | Bhola prasad(Company)+Sing Bahini | AP25/0 | AP26/0 | 25/0¦26/0 | TSE | Ready | 0.18516 | 1.6664 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-25 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-25 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-25 | 2026-01-01 | Babloo Haque/Anarul-2 | AP42/0 | AP43/0 | 42/0¦43/0 | Manual | Ready | 0.061846 | 0.30923 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-25 | 2026-01-01 | Bhola prasad(Company)+Sing Bahini | AP25/0 | AP26/0 | 25/0¦26/0 | TSE | Ready | 0.18516 | 1.6664 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-26 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-26 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-26 | 2026-01-01 | Babloo Haque/Anarul-2 | AP42/0 | AP43/0 | 42/0¦43/0 | Manual | Ready | 0.061846 | 0.30923 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-26 | 2026-01-01 | Bhola prasad(Company)+Sing Bahini | AP25/0 | AP26/0 | 25/0¦26/0 | TSE | Ready | 0.18516 | 1.6664 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-27 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-27 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-27 | 2026-01-01 | Babloo Haque/Anarul-2 | AP42/0 | AP43/0 | 42/0¦43/0 | Manual | Ready | 0.061846 | 0.30923 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-27 | 2026-01-01 | Bhola prasad(Company)+Sing Bahini | AP25/0 | AP26/0 | 25/0¦26/0 | TSE | Ready | 0.18516 | 1.6664 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-28 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-28 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-28 | 2026-01-01 | Babloo Haque/Anarul-2 | AP42/0 | AP43/0 | 42/0¦43/0 | Manual | Ready | 0.061846 | 0.30923 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-28 | 2026-01-01 | Bhola prasad(Company)+Sing Bahini | AP25/0 | AP26/0 | 25/0¦26/0 | TSE | Ready | 0.18516 | 1.6664 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-29 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-29 | 2026-01-01 | ANARUL ISLAM | AP2/0 | AP3/0 | 2/0¦3/0 | TSE | Ready | 0.21669 | 3.6837 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-29 | 2026-01-01 | Babloo Haque/Anarul-2 | AP42/0 | AP43/0 | 42/0¦43/0 | Manual | Ready | 0.061846 | 0.30923 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-29 | 2026-01-01 | Bhola prasad(Company)+Sing Bahini | AP25/0 | AP26/0 | 25/0¦26/0 | TSE | Ready | 0.18516 | 1.6664 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-30 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-30 | 2026-01-01 | Bhola prasad(Company)+Sing Bahini | AP25/0 | AP26/0 | 25/0¦26/0 | TSE | Ready | 0.18516 | 1.6664 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-31 | 2026-01-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-01-31 | 2026-01-01 | Bhola prasad(Company)+Sing Bahini | AP25/0 | AP26/0 | 25/0¦26/0 | TSE | Ready | 0.18516 | 1.6664 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-01 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-02 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-03 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-03 | 2026-02-01 | Babloo Haque/Anarul-2 | AP41/0 | AP42/0 | 41/0¦42/0 | TSE | Ready | 0.12684 | 1.1416 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-04 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-04 | 2026-02-01 | Babloo Haque/Anarul-2 | AP41/0 | AP42/0 | 41/0¦42/0 | TSE | Ready | 0.12684 | 1.1416 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-05 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-05 | 2026-02-01 | Babloo Haque/Anarul-2 | AP41/0 | AP42/0 | 41/0¦42/0 | TSE | Ready | 0.12684 | 1.1416 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-05 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-06 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-06 | 2026-02-01 | Babloo Haque/Anarul-2 | AP41/0 | AP42/0 | 41/0¦42/0 | TSE | Ready | 0.12684 | 1.1416 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-06 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-07 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-07 | 2026-02-01 | Babloo Haque/Anarul-2 | AP41/0 | AP42/0 | 41/0¦42/0 | TSE | Ready | 0.12684 | 1.1416 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-07 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-08 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-08 | 2026-02-01 | Babloo Haque/Anarul-2 | AP41/0 | AP42/0 | 41/0¦42/0 | TSE | Ready | 0.12684 | 1.1416 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-08 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-09 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-09 | 2026-02-01 | Babloo Haque/Anarul-2 | AP41/0 | AP42/0 | 41/0¦42/0 | TSE | Ready | 0.12684 | 1.1416 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-09 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-10 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-10 | 2026-02-01 | Babloo Haque/Anarul-2 | AP41/0 | AP42/0 | 41/0¦42/0 | TSE | Ready | 0.12684 | 1.1416 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-10 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-11 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-11 | 2026-02-01 | Babloo Haque/Anarul-2 | AP41/0 | AP42/0 | 41/0¦42/0 | TSE | Ready | 0.12684 | 1.1416 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-11 | 2026-02-01 | Bhola+Sing bahini(Company) | AP27/0 | AP28/0 | 27/0¦28/0 | Manual | Ready | 0.14974 | 0.29947 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-11 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-12 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-12 | 2026-02-01 | Bhola+Sing bahini(Company) | AP27/0 | AP28/0 | 27/0¦28/0 | Manual | Ready | 0.14974 | 0.29947 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-12 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-13 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-13 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-14 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-14 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-14 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-15 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-15 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-15 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-16 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-16 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-16 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-17 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-17 | 2026-02-01 | ANARUL ISLAM | AP22/0 | AP22A/0 | 22/0¦22A/0 | Manual | Ready | 0.095475 | 0.19095 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-17 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-17 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-18 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-18 | 2026-02-01 | ANARUL ISLAM | AP22/0 | AP22A/0 | 22/0¦22A/0 | Manual | Ready | 0.095475 | 0.19095 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-18 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-18 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-19 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-19 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-19 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-20 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-20 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-20 | 2026-02-01 | Jahangir(Company) | AP28/0 | AP29/0 | 28/0¦29/0 | TSE | Ready | 0.042979 | 0.68767 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-21 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-21 | 2026-02-01 | ANARUL ISLAM | AP22A/0 | AP23/0 | 22A/0¦23/0 | Manual | Ready | 0.13371 | 0.26742 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-21 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-22 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-22 | 2026-02-01 | ANARUL ISLAM | AP22A/0 | AP23/0 | 22A/0¦23/0 | Manual | Ready | 0.13371 | 0.26742 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-22 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-22 | 2026-02-01 | Babloo Haque/Anarul-2 | AP45/0 | AP46/0 | 45/0¦46/0 | TSE | Ready | 0.20827 | 1.4579 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-23 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-23 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-23 | 2026-02-01 | Babloo Haque/Anarul-2 | AP45/0 | AP46/0 | 45/0¦46/0 | TSE | Ready | 0.20827 | 1.4579 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-24 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-24 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-24 | 2026-02-01 | Babloo Haque/Anarul-2 | AP45/0 | AP46/0 | 45/0¦46/0 | TSE | Ready | 0.20827 | 1.4579 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-25 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-25 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-25 | 2026-02-01 | Babloo Haque/Anarul-2 | AP45/0 | AP46/0 | 45/0¦46/0 | TSE | Ready | 0.20827 | 1.4579 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-25 | 2026-02-01 | SADIK Con(company) | AP53/0 | AP53A/0 | 53/0¦53A/0 | TSE | Ready | 0.20794 | 0.83178 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-26 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-26 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-26 | 2026-02-01 | Babloo Haque/Anarul-2 | AP45/0 | AP46/0 | 45/0¦46/0 | TSE | Ready | 0.20827 | 1.4579 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-26 | 2026-02-01 | SADIK Con(company) | AP53/0 | AP53A/0 | 53/0¦53A/0 | TSE | Ready | 0.20794 | 0.83178 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-27 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-27 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-27 | 2026-02-01 | Babloo Haque/Anarul-2 | AP45/0 | AP46/0 | 45/0¦46/0 | TSE | Ready | 0.20827 | 1.4579 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-27 | 2026-02-01 | SADIK Con(company) | AP53/0 | AP53A/0 | 53/0¦53A/0 | TSE | Ready | 0.20794 | 0.83178 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-28 | 2026-02-01 | ANARUL ISLAM | AP17/0 | AP18/0 | 17/0¦18/0 | TSE | Ready | 0.033236 | 3.4566 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-28 | 2026-02-01 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 46/0¦47/0 | TSE | Ready | 0.077041 | 1.1556 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-28 | 2026-02-01 | Babloo Haque/Anarul-2 | AP45/0 | AP46/0 | 45/0¦46/0 | TSE | Ready | 0.20827 | 1.4579 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-02-28 | 2026-02-01 | SADIK Con(company) | AP53/0 | AP53A/0 | 53/0¦53A/0 | TSE | Ready | 0.20794 | 0.83178 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-10 | 2026-03-01 | Astharul (company) | AP52/0 | AP52/1 | 52/0¦52/1 | Manual | Ready | 0.065857 | 0.461 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-10 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-11 | 2026-03-01 | Astharul (company) | AP52/0 | AP52/1 | 52/0¦52/1 | Manual | Ready | 0.065857 | 0.461 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-11 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-12 | 2026-03-01 | Anarul-2 | AP43/0 | AP44/0 | 43/0¦44/0 | Manual | Ready | 0.057459 | 0.45967 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-12 | 2026-03-01 | Astharul (company) | AP52/0 | AP52/1 | 52/0¦52/1 | Manual | Ready | 0.065857 | 0.461 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-12 | 2026-03-01 | Dharmendra Hot line | AP44/0 | AP45/0 | 44/0¦45/0 | Manual | Ready | 0.0375 | 0.3 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-12 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-12 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-12 | 2026-03-01 | SADIK Con(company) | AP70/0 | Gantry | 70/0¦GANTRY | Manual | Ready | 0.021167 | 0.127 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-13 | 2026-03-01 | Anarul-2 | AP43/0 | AP44/0 | 43/0¦44/0 | Manual | Ready | 0.057459 | 0.45967 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-13 | 2026-03-01 | Astharul (company) | AP52/0 | AP52/1 | 52/0¦52/1 | Manual | Ready | 0.065857 | 0.461 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-13 | 2026-03-01 | Dharmendra Hot line | AP44/0 | AP45/0 | 44/0¦45/0 | Manual | Ready | 0.0375 | 0.3 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-13 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-13 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-13 | 2026-03-01 | SADIK Con(company) | AP70/0 | Gantry | 70/0¦GANTRY | Manual | Ready | 0.021167 | 0.127 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-14 | 2026-03-01 | Anarul-2 | AP43/0 | AP44/0 | 43/0¦44/0 | Manual | Ready | 0.057459 | 0.45967 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-14 | 2026-03-01 | Astharul (company) | AP52/0 | AP52/1 | 52/0¦52/1 | Manual | Ready | 0.065857 | 0.461 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-14 | 2026-03-01 | Dharmendra Hot line | AP44/0 | AP45/0 | 44/0¦45/0 | Manual | Ready | 0.0375 | 0.3 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-14 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-14 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-14 | 2026-03-01 | SADIK Con(company) | AP70/0 | Gantry | 70/0¦GANTRY | Manual | Ready | 0.021167 | 0.127 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-15 | 2026-03-01 | Anarul-2 | AP43/0 | AP44/0 | 43/0¦44/0 | Manual | Ready | 0.057459 | 0.45967 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-15 | 2026-03-01 | Astharul (company) | AP52/0 | AP52/1 | 52/0¦52/1 | Manual | Ready | 0.065857 | 0.461 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-15 | 2026-03-01 | Dharmendra Hot line | AP44/0 | AP45/0 | 44/0¦45/0 | Manual | Ready | 0.0375 | 0.3 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-15 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-15 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-15 | 2026-03-01 | SADIK Con(company) | AP70/0 | Gantry | 70/0¦GANTRY | Manual | Ready | 0.021167 | 0.127 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-16 | 2026-03-01 | ANARUL ISLAM | AP29/0 | AP30/0 | 29/0¦30/0 | Manual | Ready | 0.13504 | 0.27008 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-16 | 2026-03-01 | Anarul-2 | AP43/0 | AP44/0 | 43/0¦44/0 | Manual | Ready | 0.057459 | 0.45967 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-16 | 2026-03-01 | Astharul (company) | AP52/0 | AP52/1 | 52/0¦52/1 | Manual | Ready | 0.065857 | 0.461 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-16 | 2026-03-01 | Dharmendra Hot line | AP44/0 | AP45/0 | 44/0¦45/0 | Manual | Ready | 0.0375 | 0.3 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-16 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-16 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-16 | 2026-03-01 | SADIK Con(company) | AP70/0 | Gantry | 70/0¦GANTRY | Manual | Ready | 0.021167 | 0.127 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-17 | 2026-03-01 | ANARUL ISLAM | AP29/0 | AP30/0 | 29/0¦30/0 | Manual | Ready | 0.13504 | 0.27008 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-17 | 2026-03-01 | Anarul-2 | AP43/0 | AP44/0 | 43/0¦44/0 | Manual | Ready | 0.057459 | 0.45967 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-17 | 2026-03-01 | Dharmendra Hot line | AP44/0 | AP45/0 | 44/0¦45/0 | Manual | Ready | 0.0375 | 0.3 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-17 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-17 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-17 | 2026-03-01 | SADIK Con(company) | AP70/0 | Gantry | 70/0¦GANTRY | Manual | Ready | 0.021167 | 0.127 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-18 | 2026-03-01 | Anarul-2 | AP43/0 | AP44/0 | 43/0¦44/0 | Manual | Ready | 0.057459 | 0.45967 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-18 | 2026-03-01 | Dharmendra Hot line | AP44/0 | AP45/0 | 44/0¦45/0 | Manual | Ready | 0.0375 | 0.3 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-18 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-18 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-19 | 2026-03-01 | Anarul-2 | AP43/0 | AP44/0 | 43/0¦44/0 | Manual | Ready | 0.057459 | 0.45967 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-19 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-19 | 2026-03-01 | Dharmendra Hot line | AP44/0 | AP45/0 | 44/0¦45/0 | Manual | Ready | 0.0375 | 0.3 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-19 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-19 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-19 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-20 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-20 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-20 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-20 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-21 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-21 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-21 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-21 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-22 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-22 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-22 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-22 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-23 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-23 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-23 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-23 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-24 | 2026-03-01 | Astharul (company) | AP52/1 | AP53/0 | 52/1¦53/0 | TSE | Ready | 0.4768 | 3.8144 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-24 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-24 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-24 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-24 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-25 | 2026-03-01 | Astharul (company) | AP52/1 | AP53/0 | 52/1¦53/0 | TSE | Ready | 0.4768 | 3.8144 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-25 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-25 | 2026-03-01 | Dharmendra Hot line | AP65/0 | AP66 | 65/0¦66 | Manual | Ready | 0.042577 | 0.29804 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-25 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-25 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-25 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-25 | 2026-03-01 | SADIK Con(company) | AP68/0 | AP69/0 | 68/0¦69/0 | Manual | Ready | 0.10126 | 0.30377 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-26 | 2026-03-01 | Astharul (company) | AP52/1 | AP53/0 | 52/1¦53/0 | TSE | Ready | 0.4768 | 3.8144 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-26 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-26 | 2026-03-01 | Dharmendra Hot line | AP65/0 | AP66 | 65/0¦66 | Manual | Ready | 0.042577 | 0.29804 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-26 | 2026-03-01 | Jahangir(Company) | AP53A/0 | AP54/0 | 53A/0¦54/0 | TSE | Ready | 0.18624 | 3.166 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-26 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-26 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-26 | 2026-03-01 | SADIK Con(company) | AP68/0 | AP69/0 | 68/0¦69/0 | Manual | Ready | 0.10126 | 0.30377 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-27 | 2026-03-01 | Astharul (company) | AP52/1 | AP53/0 | 52/1¦53/0 | TSE | Ready | 0.4768 | 3.8144 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-27 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-27 | 2026-03-01 | Dharmendra Hot line | AP65/0 | AP66 | 65/0¦66 | Manual | Ready | 0.042577 | 0.29804 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-27 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-27 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-27 | 2026-03-01 | SADIK Con(company) | AP68/0 | AP69/0 | 68/0¦69/0 | Manual | Ready | 0.10126 | 0.30377 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-28 | 2026-03-01 | Anarul-2 | AP67/0 | AP68/0 | 67/0¦68/0 | Manual | Ready | 0.079603 | 0.31841 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-28 | 2026-03-01 | Astharul (company) | AP52/1 | AP53/0 | 52/1¦53/0 | TSE | Ready | 0.4768 | 3.8144 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-28 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-28 | 2026-03-01 | Dharmendra Hot line | AP65/0 | AP66 | 65/0¦66 | Manual | Ready | 0.042577 | 0.29804 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-28 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-28 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-29 | 2026-03-01 | Anarul-2 | AP67/0 | AP68/0 | 67/0¦68/0 | Manual | Ready | 0.079603 | 0.31841 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-29 | 2026-03-01 | Astharul (company) | AP52/1 | AP53/0 | 52/1¦53/0 | TSE | Ready | 0.4768 | 3.8144 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-29 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-29 | 2026-03-01 | Dharmendra Hot line | AP65/0 | AP66 | 65/0¦66 | Manual | Ready | 0.042577 | 0.29804 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-29 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-29 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-30 | 2026-03-01 | Anarul-2 | AP67/0 | AP68/0 | 67/0¦68/0 | Manual | Ready | 0.079603 | 0.31841 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-30 | 2026-03-01 | Astharul (company) | AP52/1 | AP53/0 | 52/1¦53/0 | TSE | Ready | 0.4768 | 3.8144 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-30 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-30 | 2026-03-01 | Dharmendra Hot line | AP65/0 | AP66 | 65/0¦66 | Manual | Ready | 0.042577 | 0.29804 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-30 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-30 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-31 | 2026-03-01 | Anarul-2 | AP67/0 | AP68/0 | 67/0¦68/0 | Manual | Ready | 0.079603 | 0.31841 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-31 | 2026-03-01 | Astharul (company) | AP52/1 | AP53/0 | 52/1¦53/0 | TSE | Ready | 0.4768 | 3.8144 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-31 | 2026-03-01 | Astharul (company) | AP66/0 | AP67/0 | 66/0¦67/0 | TSE | Ready | 0.062489 | 0.81236 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-31 | 2026-03-01 | Dharmendra Hot line | AP65/0 | AP66 | 65/0¦66 | Manual | Ready | 0.042577 | 0.29804 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-31 | 2026-03-01 | SADIK Con(company) | AP69A/0 | AP70/0 | 69A/0¦70/0 | Manual | Ready | 0.010123 | 0.20246 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-03-31 | 2026-03-01 | SADIK Con(company) | AP69/0 | AP69A | 69/0¦69A | Manual | Ready | 0.017892 | 0.2326 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-02 | 2026-04-01 | Jahangir(Company) | AP54/0 | AP55/0 | 54/0¦55/0 | TSE | Ready | 0.1318 | 1.1862 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-03 | 2026-04-01 | Jahangir(Company) | AP54/0 | AP55/0 | 54/0¦55/0 | TSE | Ready | 0.1318 | 1.1862 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-04 | 2026-04-01 | Jahangir(Company) | AP54/0 | AP55/0 | 54/0¦55/0 | TSE | Ready | 0.1318 | 1.1862 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-05 | 2026-04-01 | Jahangir(Company) | AP54/0 | AP55/0 | 54/0¦55/0 | TSE | Ready | 0.1318 | 1.1862 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-06 | 2026-04-01 | Jahangir(Company) | AP54/0 | AP55/0 | 54/0¦55/0 | TSE | Ready | 0.1318 | 1.1862 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-07 | 2026-04-01 | Jahangir(Company) | AP54/0 | AP55/0 | 54/0¦55/0 | TSE | Ready | 0.1318 | 1.1862 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-08 | 2026-04-01 | Jahangir(Company) | AP54/0 | AP55/0 | 54/0¦55/0 | TSE | Ready | 0.1318 | 1.1862 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-09 | 2026-04-01 | Jahangir(Company) | AP54/0 | AP55/0 | 54/0¦55/0 | TSE | Ready | 0.1318 | 1.1862 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-10 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-10 | 2026-04-01 | Jahangir(Company) | AP54/0 | AP55/0 | 54/0¦55/0 | TSE | Ready | 0.1318 | 1.1862 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-11 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-12 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-12 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-13 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-13 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-14 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-14 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-14 | 2026-04-01 | Khosibur Ali(Company) | AP62/0 | AP63/0 | 62/0¦63/0 | Manual | Ready | 0.1164 | 0.34919 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-15 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-15 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-15 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-15 | 2026-04-01 | Khosibur Ali(Company) | AP62/0 | AP63/0 | 62/0¦63/0 | Manual | Ready | 0.1164 | 0.34919 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-16 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-16 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-16 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-16 | 2026-04-01 | Khosibur Ali(Company) | AP62/0 | AP63/0 | 62/0¦63/0 | Manual | Ready | 0.1164 | 0.34919 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-17 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-17 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-17 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-18 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-18 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-18 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-19 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-19 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-19 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-20 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-20 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-20 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-21 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-21 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-21 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-22 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-22 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-22 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-23 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-23 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-23 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-24 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-24 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-24 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-25 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-25 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-25 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-26 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-26 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-26 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-27 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-27 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-27 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-28 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-28 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-28 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-29 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-29 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-29 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-30 | 2026-04-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-30 | 2026-04-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-04-30 | 2026-04-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-01 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-01 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-01 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-02 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-02 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-02 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-03 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-03 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-03 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-04 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-04 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-04 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-05 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-05 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-05 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-06 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-06 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-06 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-07 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-07 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-07 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-08 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-08 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-08 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-09 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-09 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-09 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-10 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-10 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-10 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-10 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-11 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-11 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-11 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-11 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-12 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-12 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-12 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-12 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-13 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-13 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-13 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-13 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-14 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-14 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-14 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-14 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-15 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-15 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-15 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-15 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-16 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-16 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-16 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-16 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-17 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-17 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-17 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-17 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-17 | 2026-05-01 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 55/0¦56/0 | TSE | Ready | 0.016867 | 0.60721 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-18 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-18 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-18 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-18 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-19 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-19 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-19 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-19 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-20 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-20 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-20 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-20 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-20 | 2026-05-01 | Kunal Hot line | AP47/0 | AP48/0 | 47/0¦48/0 | Manual | Ready | 0.044829 | 0.35863 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-21 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-21 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-21 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-21 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-21 | 2026-05-01 | Kunal Hot line | AP47/0 | AP48/0 | 47/0¦48/0 | Manual | Ready | 0.044829 | 0.35863 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-22 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-22 | 2026-05-01 | ANARUL ISLAM | AP56/0 | AP57/0 | 56/0¦57/0 | TSE | Ready | 0.25954 | 3.374 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-22 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-22 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-22 | 2026-05-01 | Kunal Hot line | AP47/0 | AP48/0 | 47/0¦48/0 | Manual | Ready | 0.044829 | 0.35863 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-23 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-23 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-23 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-23 | 2026-05-01 | Kunal Hot line | AP47/0 | AP48/0 | 47/0¦48/0 | Manual | Ready | 0.044829 | 0.35863 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-24 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-24 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-24 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-24 | 2026-05-01 | Kunal Hot line | AP47/0 | AP48/0 | 47/0¦48/0 | Manual | Ready | 0.044829 | 0.35863 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-25 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-25 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-25 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-25 | 2026-05-01 | Kunal Hot line | AP47/0 | AP48/0 | 47/0¦48/0 | Manual | Ready | 0.044829 | 0.35863 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-26 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-26 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-26 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-26 | 2026-05-01 | Kunal Hot line | AP47/0 | AP48/0 | 47/0¦48/0 | Manual | Ready | 0.044829 | 0.35863 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-27 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-27 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-27 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-27 | 2026-05-01 | Kunal Hot line | AP47/0 | AP48/0 | 47/0¦48/0 | Manual | Ready | 0.044829 | 0.35863 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-28 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-28 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-28 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-29 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-29 | 2026-05-01 | ANARUL ISLAM | AP57/0 | AP58/0 | 57/0¦58/0 | TSE | Ready | 0.052098 | 0.67728 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-29 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-30 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-30 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-31 | 2026-05-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-05-31 | 2026-05-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-01 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-01 | 2026-06-01 | ANARUL ISLAM | AP63/0 | AP64/0 | 63/0¦64/0 | Manual | Ready | 0.0715 | 0.286 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-01 | 2026-06-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-01 | 2026-06-01 | Kunal Hot line | AP51/0 | AP52/0 | 51/0¦52/0 | Manual | Ready | 0.039822 | 0.23893 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-02 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-02 | 2026-06-01 | ANARUL ISLAM | AP63/0 | AP64/0 | 63/0¦64/0 | Manual | Ready | 0.0715 | 0.286 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-02 | 2026-06-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-02 | 2026-06-01 | Kunal Hot line | AP51/0 | AP52/0 | 51/0¦52/0 | Manual | Ready | 0.039822 | 0.23893 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-03 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-03 | 2026-06-01 | ANARUL ISLAM | AP63/0 | AP64/0 | 63/0¦64/0 | Manual | Ready | 0.0715 | 0.286 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-03 | 2026-06-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-03 | 2026-06-01 | Kunal Hot line | AP51/0 | AP52/0 | 51/0¦52/0 | Manual | Ready | 0.039822 | 0.23893 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-04 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-04 | 2026-06-01 | ANARUL ISLAM | AP63/0 | AP64/0 | 63/0¦64/0 | Manual | Ready | 0.0715 | 0.286 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-04 | 2026-06-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-04 | 2026-06-01 | Kunal Hot line | AP51/0 | AP52/0 | 51/0¦52/0 | Manual | Ready | 0.039822 | 0.23893 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-05 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-05 | 2026-06-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-05 | 2026-06-01 | Kunal Hot line | AP51/0 | AP52/0 | 51/0¦52/0 | Manual | Ready | 0.039822 | 0.23893 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-06 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-06 | 2026-06-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-06 | 2026-06-01 | Kunal Hot line | AP51/0 | AP52/0 | 51/0¦52/0 | Manual | Ready | 0.039822 | 0.23893 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-07 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-07 | 2026-06-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-08 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-08 | 2026-06-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-09 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-09 | 2026-06-01 | Astharul (company) | AP64/0 | AP65/0 | 64/0¦65/0 | TSE | Ready | 0.025429 | 1.5512 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-10 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-11 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-12 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-13 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-14 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-15 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 416 | TA 416 | ta416 |  | 2026-06-16 | 2026-06-01 | (Kunal Hot line | AP61/0 | AP62/0 | 61/0¦62/0 | Manual | Ready | 0.0075884 | 0.47807 |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TA 418 | TA 418 | ta418 |  | 2025-09-25 | 2025-09-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-09-26 | 2025-09-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-09-27 | 2025-09-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-09-28 | 2025-09-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-09-29 | 2025-09-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-09-30 | 2025-09-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-01 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-02 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-03 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-03 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-04 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-04 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-05 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-05 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-06 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-06 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-07 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-07 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-08 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-08 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-09 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-09 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-10 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-10 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-11 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-11 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-12 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-12 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-13 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-13 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-14 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-14 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-15 | 2025-10-01 | SUFIYAN | AP42 | AP43 | 42¦43 | TSE | Ready | 0.052656 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-15 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-16 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-17 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-18 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-19 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-20 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-21 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-22 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-23 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-24 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-25 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-26 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-27 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-28 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-29 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-30 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-10-31 | 2025-10-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-01 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-01 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-02 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-02 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-03 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-03 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-04 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-04 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-05 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-05 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-06 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-06 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-07 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-07 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-07 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-08 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-08 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-08 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-09 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-09 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-09 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-10 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-10 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-10 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-11 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-11 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-11 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-12 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-12 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-12 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-13 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-13 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-13 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-14 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-14 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-14 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-15 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-15 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-15 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-16 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-16 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-16 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-17 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-17 | 2025-11-01 | SUFIYAN | AP36 | 36/1 | 36¦36/1 | Manual | Ready | 0.028235 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-17 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-18 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-18 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-19 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-19 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-20 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-20 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-21 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-21 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-22 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-22 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-23 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-23 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-24 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-24 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-25 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-25 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-26 | 2025-11-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-26 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-26 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-27 | 2025-11-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-27 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-27 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-28 | 2025-11-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-28 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-28 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-29 | 2025-11-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-29 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-29 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-30 | 2025-11-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-30 | 2025-11-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-11-30 | 2025-11-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-01 | 2025-12-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-01 | 2025-12-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-01 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-02 | 2025-12-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-02 | 2025-12-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-02 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-03 | 2025-12-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-03 | 2025-12-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-03 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-04 | 2025-12-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-04 | 2025-12-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-04 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-05 | 2025-12-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-05 | 2025-12-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-05 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-06 | 2025-12-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-06 | 2025-12-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-06 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-07 | 2025-12-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-07 | 2025-12-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-07 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-08 | 2025-12-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-08 | 2025-12-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-08 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-09 | 2025-12-01 | SUFIYAN | 34/0 | AP35 | 34/0¦35 | TSE | Ready | 0.14168 |  | 60 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-09 | 2025-12-01 | SUFIYAN | AP35 | AP36 | 35¦36 | TSE | Ready | 0.13576 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-09 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-10 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-11 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-12 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-13 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-14 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-15 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-16 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-17 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-18 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-19 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-20 | 2025-12-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-20 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-21 | 2025-12-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-21 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-22 | 2025-12-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-22 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-23 | 2025-12-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-23 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-24 | 2025-12-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-24 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-25 | 2025-12-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-25 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-26 | 2025-12-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-26 | 2025-12-01 | SUFIYAN / Haque | AP41 | AP42 | 41¦42 | TSE | Ready | 0.029097 |  | 55 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-27 | 2025-12-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-28 | 2025-12-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-29 | 2025-12-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-30 | 2025-12-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2025-12-31 | 2025-12-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-01 | 2026-01-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-02 | 2026-01-01 | SUFIYAN / Haque | AP40 | AP41 | 40¦41 | TSE | Ready | 0.17332 |  | 65 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-18 | 2026-01-01 | SUFIYAN / Haque | 33/6 | 34/0 | 33/6¦34/0 | TSE | Ready | 0.23067 |  | 58 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-19 | 2026-01-01 | Ramawat | 33/5 | 33/6 | 33/5¦33/6 | HotLine | Ready | 0.031667 |  | 20 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-19 | 2026-01-01 | SUFIYAN / Haque | 33/6 | 34/0 | 33/6¦34/0 | TSE | Ready | 0.23067 |  | 58 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-20 | 2026-01-01 | Ramawat | 33/5 | 33/6 | 33/5¦33/6 | HotLine | Ready | 0.031667 |  | 20 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-20 | 2026-01-01 | SUFIYAN / Haque | 33/6 | 34/0 | 33/6¦34/0 | TSE | Ready | 0.23067 |  | 58 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-21 | 2026-01-01 | Ramawat | 33/5 | 33/6 | 33/5¦33/6 | HotLine | Ready | 0.031667 |  | 20 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-21 | 2026-01-01 | SUFIYAN / Haque | 33/6 | 34/0 | 33/6¦34/0 | TSE | Ready | 0.23067 |  | 58 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-22 | 2026-01-01 | Ramawat | 33/5 | 33/6 | 33/5¦33/6 | HotLine | Ready | 0.031667 |  | 20 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-22 | 2026-01-01 | SUFIYAN / Haque | 33/6 | 34/0 | 33/6¦34/0 | TSE | Ready | 0.23067 |  | 58 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-23 | 2026-01-01 | Ramawat | 33/5 | 33/6 | 33/5¦33/6 | HotLine | Ready | 0.031667 |  | 20 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-23 | 2026-01-01 | SUFIYAN / Haque | 33/6 | 34/0 | 33/6¦34/0 | TSE | Ready | 0.23067 |  | 58 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-24 | 2026-01-01 | Ramawat | 33/5 | 33/6 | 33/5¦33/6 | HotLine | Ready | 0.031667 |  | 20 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-24 | 2026-01-01 | SUFIYAN / Haque | 33/6 | 34/0 | 33/6¦34/0 | TSE | Ready | 0.23067 |  | 58 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-25 | 2026-01-01 | Ramawat | 33/5 | 33/6 | 33/5¦33/6 | HotLine | Ready | 0.031667 |  | 20 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-25 | 2026-01-01 | SUFIYAN / Haque | 33/6 | 34/0 | 33/6¦34/0 | TSE | Ready | 0.23067 |  | 58 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-26 | 2026-01-01 | Ramawat | 33/5 | 33/6 | 33/5¦33/6 | HotLine | Ready | 0.031667 |  | 20 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-26 | 2026-01-01 | SUFIYAN / Haque | 33/6 | 34/0 | 33/6¦34/0 | TSE | Ready | 0.23067 |  | 58 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-27 | 2026-01-01 | Ramawat | 33/5 | 33/6 | 33/5¦33/6 | HotLine | Ready | 0.031667 |  | 20 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-27 | 2026-01-01 | SUFIYAN / Haque | 33/6 | 34/0 | 33/6¦34/0 | TSE | Ready | 0.23067 |  | 58 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-28 | 2026-01-01 | Ramawat | 33/5 | 33/6 | 33/5¦33/6 | HotLine | Ready | 0.031667 |  | 20 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-28 | 2026-01-01 | SUFIYAN / Haque | 33/6 | 34/0 | 33/6¦34/0 | TSE | Ready | 0.23067 |  | 58 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-29 | 2026-01-01 | Ramawat | 33/5 | 33/6 | 33/5¦33/6 | HotLine | Ready | 0.031667 |  | 20 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-01-30 | 2026-01-01 | Ramawat | 33/5 | 33/6 | 33/5¦33/6 | HotLine | Ready | 0.031667 |  | 20 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-02-05 | 2026-02-01 | SUFIYAN / Haque | AP33 | 33/5 | 33¦33/5 | TSE | Ready | 0.403 |  | 73 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-02-06 | 2026-02-01 | SUFIYAN / Haque | AP33 | 33/5 | 33¦33/5 | TSE | Ready | 0.403 |  | 73 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-02-07 | 2026-02-01 | Ramawat | AP39 | AP40 | 39¦40 | HotLine | Ready | 0.046174 |  | 22 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-02-07 | 2026-02-01 | SUFIYAN / Haque | AP33 | 33/5 | 33¦33/5 | TSE | Ready | 0.403 |  | 73 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-02-08 | 2026-02-01 | Ramawat | AP39 | AP40 | 39¦40 | HotLine | Ready | 0.046174 |  | 22 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-02-08 | 2026-02-01 | SUFIYAN / Haque | AP33 | 33/5 | 33¦33/5 | TSE | Ready | 0.403 |  | 73 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-02-09 | 2026-02-01 | Ramawat | AP39 | AP40 | 39¦40 | HotLine | Ready | 0.046174 |  | 22 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-02-09 | 2026-02-01 | SUFIYAN / Haque | AP33 | 33/5 | 33¦33/5 | TSE | Ready | 0.403 |  | 73 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-02-10 | 2026-02-01 | Ramawat | AP39 | AP40 | 39¦40 | HotLine | Ready | 0.046174 |  | 22 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-02-11 | 2026-02-01 | Ramawat | AP39 | AP40 | 39¦40 | HotLine | Ready | 0.046174 |  | 22 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-02-16 | 2026-02-01 | Ramawat | AP32 | AP33 | 32¦33 | HotLine | Ready | 0.035662 |  |  |  | READ_FAIL | READ_FAIL | yes | FALSE | NO_DATA | No manpower values found for this span/day.
TA 418 | TA 418 | ta418 |  | 2026-02-17 | 2026-02-01 | Ramawat | AP32 | AP33 | 32¦33 | HotLine | Ready | 0.035662 |  |  |  | READ_FAIL | READ_FAIL | yes | FALSE | NO_DATA | No manpower values found for this span/day.
TA 418 | TA 418 | ta418 |  | 2026-02-18 | 2026-02-01 | Ramawat | AP32 | AP33 | 32¦33 | HotLine | Ready | 0.035662 |  |  |  | READ_FAIL | READ_FAIL | yes | FALSE | NO_DATA | No manpower values found for this span/day.
TA 418 | TA 418 | ta418 |  | 2026-02-19 | 2026-02-01 | Ramawat | AP32 | AP33 | 32¦33 | HotLine | Ready | 0.035662 |  |  |  | READ_FAIL | READ_FAIL | yes | FALSE | NO_DATA | No manpower values found for this span/day.
TA 418 | TA 418 | ta418 |  | 2026-02-20 | 2026-02-01 | Ramawat | AP32 | AP33 | 32¦33 | HotLine | Ready | 0.035662 |  |  |  | READ_FAIL | READ_FAIL | yes | FALSE | NO_DATA | No manpower values found for this span/day.
TA 418 | TA 418 | ta418 |  | 2026-02-21 | 2026-02-01 | Ramawat | AP32 | AP33 | 32¦33 | HotLine | Ready | 0.035662 |  |  |  | READ_FAIL | READ_FAIL | yes | FALSE | NO_DATA | No manpower values found for this span/day.
TA 418 | TA 418 | ta418 |  | 2026-02-22 | 2026-02-01 | Ramawat | AP32 | AP33 | 32¦33 | HotLine | Ready | 0.035662 |  |  |  | READ_FAIL | READ_FAIL | yes | FALSE | NO_DATA | No manpower values found for this span/day.
TA 418 | TA 418 | ta418 |  | 2026-02-28 | 2026-02-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-01 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-02 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-03 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-04 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-05 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-06 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-06 | 2026-03-01 | Ramawat | AP45 | 45/1 | 45¦45/1 | Manual | Ready | 0.034571 |  | 22 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-07 | 2026-03-01 | Haque | AP44 | AP45 | 44¦45 | TSE | Ready | 0.05813 |  | 35 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-07 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-07 | 2026-03-01 | Ramawat | AP45 | 45/1 | 45¦45/1 | Manual | Ready | 0.034571 |  | 22 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-07 | 2026-03-01 | SUFIYAN | AP43 | AP44 | 43¦44 | TSE | Ready | 0.2408 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-08 | 2026-03-01 | Haque | AP44 | AP45 | 44¦45 | TSE | Ready | 0.05813 |  | 35 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-08 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-08 | 2026-03-01 | Ramawat | AP45 | 45/1 | 45¦45/1 | Manual | Ready | 0.034571 |  | 22 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-08 | 2026-03-01 | SUFIYAN | AP43 | AP44 | 43¦44 | TSE | Ready | 0.2408 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-09 | 2026-03-01 | Haque | AP44 | AP45 | 44¦45 | TSE | Ready | 0.05813 |  | 35 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-09 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-09 | 2026-03-01 | Ramawat | AP45 | 45/1 | 45¦45/1 | Manual | Ready | 0.034571 |  | 22 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-09 | 2026-03-01 | SUFIYAN | AP43 | AP44 | 43¦44 | TSE | Ready | 0.2408 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-10 | 2026-03-01 | Haque | AP44 | AP45 | 44¦45 | TSE | Ready | 0.05813 |  | 35 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-10 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-10 | 2026-03-01 | Ramawat | AP45 | 45/1 | 45¦45/1 | Manual | Ready | 0.034571 |  | 22 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-10 | 2026-03-01 | SUFIYAN | AP43 | AP44 | 43¦44 | TSE | Ready | 0.2408 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-11 | 2026-03-01 | Haque | AP44 | AP45 | 44¦45 | TSE | Ready | 0.05813 |  | 35 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-11 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-11 | 2026-03-01 | Ramawat | AP45 | 45/1 | 45¦45/1 | Manual | Ready | 0.034571 |  | 22 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-11 | 2026-03-01 | SUFIYAN | AP43 | AP44 | 43¦44 | TSE | Ready | 0.2408 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-12 | 2026-03-01 | Haque | AP44 | AP45 | 44¦45 | TSE | Ready | 0.05813 |  | 35 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-12 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-12 | 2026-03-01 | Ramawat | AP45 | 45/1 | 45¦45/1 | Manual | Ready | 0.034571 |  | 22 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-12 | 2026-03-01 | SUFIYAN | AP43 | AP44 | 43¦44 | TSE | Ready | 0.2408 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-13 | 2026-03-01 | Haque | AP44 | AP45 | 44¦45 | TSE | Ready | 0.05813 |  | 35 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-13 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-14 | 2026-03-01 | Haque | AP44 | AP45 | 44¦45 | TSE | Ready | 0.05813 |  | 35 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-14 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-15 | 2026-03-01 | Haque | AP44 | AP45 | 44¦45 | TSE | Ready | 0.05813 |  | 35 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-15 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-16 | 2026-03-01 | Haque | AP44 | AP45 | 44¦45 | TSE | Ready | 0.05813 |  | 35 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-16 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-17 | 2026-03-01 | Haque | AP44 | AP45 | 44¦45 | TSE | Ready | 0.05813 |  | 35 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-17 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-18 | 2026-03-01 | Haque | AP44 | AP45 | 44¦45 | TSE | Ready | 0.05813 |  | 35 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-18 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-19 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-20 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-21 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-22 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-23 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-24 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-25 | 2026-03-01 | Haque | 45/1 | AP46 | 45/1¦46 | TSE | Ready | 0.048943 |  | 33 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-26 | 2026-03-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-27 | 2026-03-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-28 | 2026-03-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-29 | 2026-03-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-30 | 2026-03-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-03-31 | 2026-03-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-01 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-02 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-03 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-04 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-05 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-06 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-07 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-08 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-09 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-10 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-11 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-12 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-13 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-14 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-15 | 2026-04-01 | M/s Kamrudhin | 63/0 | GNTY | 63/0¦GNTY | Manual | Ready | 0.027 |  | 32 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-15 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-16 | 2026-04-01 | M/s Kamrudhin | 63/0 | GNTY | 63/0¦GNTY | Manual | Ready | 0.027 |  | 32 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-16 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-17 | 2026-04-01 | M/s Kamrudhin | 63/0 | GNTY | 63/0¦GNTY | Manual | Ready | 0.027 |  | 32 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-17 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-18 | 2026-04-01 | M/s Kamrudhin | 63/0 | GNTY | 63/0¦GNTY | Manual | Ready | 0.027 |  | 32 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-18 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-19 | 2026-04-01 | M/s Kamrudhin | 63/0 | GNTY | 63/0¦GNTY | Manual | Ready | 0.027 |  | 32 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-19 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-20 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-21 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-22 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-23 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-24 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-25 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-26 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-27 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-28 | 2026-04-01 | SUFIYAN | AP55 | AP56 | 55¦56 | TSE | Ready | 0.38636 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-28 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-29 | 2026-04-01 | SUFIYAN | AP55 | AP56 | 55¦56 | TSE | Ready | 0.38636 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-29 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-30 | 2026-04-01 | SUFIYAN | AP55 | AP56 | 55¦56 | TSE | Ready | 0.38636 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-04-30 | 2026-04-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-01 | 2026-05-01 | SUFIYAN | AP55 | AP56 | 55¦56 | TSE | Ready | 0.38636 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-01 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-02 | 2026-05-01 | SUFIYAN | AP55 | AP56 | 55¦56 | TSE | Ready | 0.38636 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-02 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-03 | 2026-05-01 | SUFIYAN | AP55 | AP56 | 55¦56 | TSE | Ready | 0.38636 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-03 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-04 | 2026-05-01 | SUFIYAN | AP55 | AP56 | 55¦56 | TSE | Ready | 0.38636 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-04 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-05 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-06 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-07 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-08 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-09 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-10 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-10 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-11 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-11 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-12 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-12 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-13 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-13 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-14 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-14 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-15 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-15 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-16 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-16 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-17 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-17 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-18 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-18 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-19 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-19 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-20 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-20 | 2026-05-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-20 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-21 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-21 | 2026-05-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-21 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-22 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-22 | 2026-05-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-22 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-23 | 2026-05-01 | Dharmendar | 36/1 | 37/0 | 36/1¦37/0 | Manual | Ready | 0.042474 |  | 30 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-23 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-23 | 2026-05-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-23 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-24 | 2026-05-01 | Dharmendar | 36/1 | 37/0 | 36/1¦37/0 | Manual | Ready | 0.042474 |  | 30 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-24 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-24 | 2026-05-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-24 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-25 | 2026-05-01 | Dharmendar | 36/1 | 37/0 | 36/1¦37/0 | Manual | Ready | 0.042474 |  | 30 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-25 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-25 | 2026-05-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-25 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-26 | 2026-05-01 | Dharmendar | 36/1 | 37/0 | 36/1¦37/0 | Manual | Ready | 0.042474 |  | 30 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-26 | 2026-05-01 | SUFIYAN | 37/0 | AP38 | 37/0¦38 | TSE | Ready | 0.074046 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-26 | 2026-05-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-26 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-27 | 2026-05-01 | Dharmendar | 36/1 | 37/0 | 36/1¦37/0 | Manual | Ready | 0.042474 |  | 30 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-27 | 2026-05-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-27 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-28 | 2026-05-01 | Dharmendar | 36/1 | 37/0 | 36/1¦37/0 | Manual | Ready | 0.042474 |  | 30 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-28 | 2026-05-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-28 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-29 | 2026-05-01 | Dharmendar | 36/1 | 37/0 | 36/1¦37/0 | Manual | Ready | 0.042474 |  | 30 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-29 | 2026-05-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-29 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-30 | 2026-05-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-30 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-31 | 2026-05-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-05-31 | 2026-05-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-01 | 2026-06-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-01 | 2026-06-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-02 | 2026-06-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-02 | 2026-06-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-03 | 2026-06-01 | SUFIYAN | AP38 | AP39 | 38¦39 | TSE | Ready | 0.086717 |  | 43 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-03 | 2026-06-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-04 | 2026-06-01 | M/s Dharmander | 56/3 | 57/0 | 56/3¦57/0 | Manual | Pending | 0.046082 |  | 24 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-04 | 2026-06-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-05 | 2026-06-01 | M/s Dharmander | 56/3 | 57/0 | 56/3¦57/0 | Manual | Pending | 0.046082 |  | 24 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-05 | 2026-06-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-06 | 2026-06-01 | M/s Dharmander | 56/3 | 57/0 | 56/3¦57/0 | Manual | Pending | 0.046082 |  | 24 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-06 | 2026-06-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-07 | 2026-06-01 | M/s Dharmander | 56/3 | 57/0 | 56/3¦57/0 | Manual | Pending | 0.046082 |  | 24 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-07 | 2026-06-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-08 | 2026-06-01 | M/s Dharmander | 56/3 | 57/0 | 56/3¦57/0 | Manual | Pending | 0.046082 |  | 24 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-08 | 2026-06-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-09 | 2026-06-01 | M/s Dharmander | 56/3 | 57/0 | 56/3¦57/0 | Manual | Pending | 0.046082 |  | 24 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 418 | TA 418 | ta418 |  | 2026-06-09 | 2026-06-01 | SUFIYAN | AP56 | 56/3 | 56¦56/3 | TSE | Ready | 0.016184 |  | 31 |  | PRESENT_WITH_VALUES | READ_FAIL | yes | FALSE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-12 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-13 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-14 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-15 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-16 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-17 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-18 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-19 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-20 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-21 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-22 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-23 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-24 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-24 | 2025-02-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-25 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-25 | 2025-02-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-26 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-26 | 2025-02-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-27 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-27 | 2025-02-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-28 | 2025-02-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-02-28 | 2025-02-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-01 | 2025-03-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-01 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-02 | 2025-03-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-02 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-03 | 2025-03-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-03 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-04 | 2025-03-01 | M R Constructions | 23/0 | 24/0 | 23/0¦24/0 | TSE | Ready | 0.086952 | 1.826 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-04 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-05 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-06 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-07 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-08 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-08 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-09 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-09 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-10 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-10 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-11 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-11 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-12 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-12 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-13 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-13 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-14 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-14 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-15 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-15 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-16 | 2025-03-01 | M R Constructions | 24/0 | 25/0 | 24/0¦25/0 | TSE | Ready | 0.16219 | 3.406 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-16 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-17 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-18 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-19 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-20 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-21 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-22 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-23 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-23 | 2025-03-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-24 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-24 | 2025-03-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-25 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-25 | 2025-03-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-26 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-26 | 2025-03-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-27 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-27 | 2025-03-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-28 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-28 | 2025-03-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-29 | 2025-03-01 | M R Constructions | 25/0 | 26/0 | 25/0¦26/0 | TSE | Ready | 0.10359 | 2.279 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-29 | 2025-03-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-30 | 2025-03-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-03-31 | 2025-03-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-01 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-02 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-03 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-04 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-05 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-06 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-07 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-07 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-08 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-08 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-09 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-09 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-10 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-10 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-11 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-11 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-12 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-12 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-13 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-13 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-14 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-14 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-15 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-15 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-16 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-16 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-17 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-17 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-18 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-18 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-19 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-19 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-20 | 2025-04-01 | M R Constructions | 26/0 | 27/0 | 26/0¦27/0 | TSE | Ready | 0.066 | 1.914 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-20 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-21 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-22 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-23 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-04-24 | 2025-04-01 | M R Constructions | 22/0 | 23/0 | 22/0¦23/0 | TSE | Ready | 0.12989 | 2.338 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-05 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-06 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-07 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-08 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-09 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-10 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-11 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-12 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-13 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-14 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-15 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-16 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-17 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-18 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-19 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-20 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-21 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-22 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-22 | 2025-05-01 | M R Constructions | 32/0 | 33/0 | 32/0¦33/0 | TSE | Ready | 0.18422 | 1.658 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-23 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-23 | 2025-05-01 | M R Constructions | 32/0 | 33/0 | 32/0¦33/0 | TSE | Ready | 0.18422 | 1.658 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-24 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-24 | 2025-05-01 | M R Constructions | 32/0 | 33/0 | 32/0¦33/0 | TSE | Ready | 0.18422 | 1.658 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-25 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-25 | 2025-05-01 | M R Constructions | 32/0 | 33/0 | 32/0¦33/0 | TSE | Ready | 0.18422 | 1.658 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-26 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-26 | 2025-05-01 | M R Constructions | 32/0 | 33/0 | 32/0¦33/0 | TSE | Ready | 0.18422 | 1.658 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-27 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-27 | 2025-05-01 | M R Constructions | 32/0 | 33/0 | 32/0¦33/0 | TSE | Ready | 0.18422 | 1.658 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-28 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-28 | 2025-05-01 | M R Constructions | 32/0 | 33/0 | 32/0¦33/0 | TSE | Ready | 0.18422 | 1.658 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-29 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-29 | 2025-05-01 | M R Constructions | 32/0 | 33/0 | 32/0¦33/0 | TSE | Ready | 0.18422 | 1.658 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-30 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-30 | 2025-05-01 | M R Constructions | 32/0 | 33/0 | 32/0¦33/0 | TSE | Ready | 0.18422 | 1.658 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-05-31 | 2025-05-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-01 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-02 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-03 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-04 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-05 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-06 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-07 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-08 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-09 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-10 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-11 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-12 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-12 | 2025-06-01 | M R Constructions | 31/0 | 32/0 | 31/0¦32/0 | TSE | Ready | 0.44817 | 2.689 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-13 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-13 | 2025-06-01 | M R Constructions | 31/0 | 32/0 | 31/0¦32/0 | TSE | Ready | 0.44817 | 2.689 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-14 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-14 | 2025-06-01 | M R Constructions | 31/0 | 32/0 | 31/0¦32/0 | TSE | Ready | 0.44817 | 2.689 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-15 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-15 | 2025-06-01 | M R Constructions | 31/0 | 32/0 | 31/0¦32/0 | TSE | Ready | 0.44817 | 2.689 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-16 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-16 | 2025-06-01 | M R Constructions | 31/0 | 32/0 | 31/0¦32/0 | TSE | Ready | 0.44817 | 2.689 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-17 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-17 | 2025-06-01 | M R Constructions | 31/0 | 32/0 | 31/0¦32/0 | TSE | Ready | 0.44817 | 2.689 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-18 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-19 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-20 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-21 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-22 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-22 | 2025-06-01 | M R Constructions | 30/0 | 31/0 | 30/0¦31/0 | TSE | Ready | 0.21664 | 2.383 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-23 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-23 | 2025-06-01 | M R Constructions | 30/0 | 31/0 | 30/0¦31/0 | TSE | Ready | 0.21664 | 2.383 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-24 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-24 | 2025-06-01 | M R Constructions | 30/0 | 31/0 | 30/0¦31/0 | TSE | Ready | 0.21664 | 2.383 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-25 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-25 | 2025-06-01 | M R Constructions | 30/0 | 31/0 | 30/0¦31/0 | TSE | Ready | 0.21664 | 2.383 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-26 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-26 | 2025-06-01 | M R Constructions | 30/0 | 31/0 | 30/0¦31/0 | TSE | Ready | 0.21664 | 2.383 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-27 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-27 | 2025-06-01 | M R Constructions | 30/0 | 31/0 | 30/0¦31/0 | TSE | Ready | 0.21664 | 2.383 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-28 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-28 | 2025-06-01 | M R Constructions | 30/0 | 31/0 | 30/0¦31/0 | TSE | Ready | 0.21664 | 2.383 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-29 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-29 | 2025-06-01 | M R Constructions | 30/0 | 31/0 | 30/0¦31/0 | TSE | Ready | 0.21664 | 2.383 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-30 | 2025-06-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-06-30 | 2025-06-01 | M R Constructions | 30/0 | 31/0 | 30/0¦31/0 | TSE | Ready | 0.21664 | 2.383 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-01 | 2025-07-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-01 | 2025-07-01 | M R Constructions | 30/0 | 31/0 | 30/0¦31/0 | TSE | Ready | 0.21664 | 2.383 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-02 | 2025-07-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-02 | 2025-07-01 | M R Constructions | 30/0 | 31/0 | 30/0¦31/0 | TSE | Ready | 0.21664 | 2.383 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-03 | 2025-07-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-04 | 2025-07-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-05 | 2025-07-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-06 | 2025-07-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-06 | 2025-07-01 | M R Constructions | 29/9 | 30/0 | 29/9¦30/0 | Manual | Ready | 0.084667 | 0.508 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-07 | 2025-07-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-07 | 2025-07-01 | M R Constructions | 29/9 | 30/0 | 29/9¦30/0 | Manual | Ready | 0.084667 | 0.508 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-08 | 2025-07-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-08 | 2025-07-01 | M R Constructions | 29/9 | 30/0 | 29/9¦30/0 | Manual | Ready | 0.084667 | 0.508 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-09 | 2025-07-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-09 | 2025-07-01 | M R Constructions | 29/9 | 30/0 | 29/9¦30/0 | Manual | Ready | 0.084667 | 0.508 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-10 | 2025-07-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-10 | 2025-07-01 | M R Constructions | 29/9 | 30/0 | 29/9¦30/0 | Manual | Ready | 0.084667 | 0.508 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-11 | 2025-07-01 | M R Constructions | 29/0 | 29/9 | 29/0¦29/9 | TSE | Ready | 0.052279 | 3.555 | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-11 | 2025-07-01 | M R Constructions | 29/9 | 30/0 | 29/9¦30/0 | Manual | Ready | 0.084667 | 0.508 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-17 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-18 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-19 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-20 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-21 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-22 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-23 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-24 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-25 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-26 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-27 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-28 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-29 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-30 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-07-31 | 2025-07-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-01 | 2025-08-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-02 | 2025-08-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-03 | 2025-08-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-04 | 2025-08-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-05 | 2025-08-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-06 | 2025-08-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-07 | 2025-08-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-08 | 2025-08-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-09 | 2025-08-01 | M R Constructions | 21/0 | 22/0 | 21/0¦22/0 | Manual | Ready | 0.16112 | 3.867 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-22 | 2025-08-01 | M R Constructions | 20/0 | 20A/0 | 20/0¦20A/0 | TSE | Ready | 0.021909 | 0.241 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-23 | 2025-08-01 | M R Constructions | 20A/0 | 21/0 | 20A/0¦21/0 | Manual | Ready | 0.019111 | 0.172 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-23 | 2025-08-01 | M R Constructions | 20/0 | 20A/0 | 20/0¦20A/0 | TSE | Ready | 0.021909 | 0.241 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-24 | 2025-08-01 | M R Constructions | 20A/0 | 21/0 | 20A/0¦21/0 | Manual | Ready | 0.019111 | 0.172 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-24 | 2025-08-01 | M R Constructions | 20/0 | 20A/0 | 20/0¦20A/0 | TSE | Ready | 0.021909 | 0.241 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-25 | 2025-08-01 | M R Constructions | 20A/0 | 21/0 | 20A/0¦21/0 | Manual | Ready | 0.019111 | 0.172 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-25 | 2025-08-01 | M R Constructions | 20/0 | 20A/0 | 20/0¦20A/0 | TSE | Ready | 0.021909 | 0.241 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-26 | 2025-08-01 | M R Constructions | 20A/0 | 21/0 | 20A/0¦21/0 | Manual | Ready | 0.019111 | 0.172 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-26 | 2025-08-01 | M R Constructions | 20/0 | 20A/0 | 20/0¦20A/0 | TSE | Ready | 0.021909 | 0.241 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-27 | 2025-08-01 | M R Constructions | 20A/0 | 21/0 | 20A/0¦21/0 | Manual | Ready | 0.019111 | 0.172 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-27 | 2025-08-01 | M R Constructions | 20/0 | 20A/0 | 20/0¦20A/0 | TSE | Ready | 0.021909 | 0.241 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-28 | 2025-08-01 | M R Constructions | 20A/0 | 21/0 | 20A/0¦21/0 | Manual | Ready | 0.019111 | 0.172 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-28 | 2025-08-01 | M R Constructions | 20/0 | 20A/0 | 20/0¦20A/0 | TSE | Ready | 0.021909 | 0.241 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-29 | 2025-08-01 | M R Constructions | 20A/0 | 21/0 | 20A/0¦21/0 | Manual | Ready | 0.019111 | 0.172 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-29 | 2025-08-01 | M R Constructions | 20/0 | 20A/0 | 20/0¦20A/0 | TSE | Ready | 0.021909 | 0.241 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-30 | 2025-08-01 | M R Constructions | 20A/0 | 21/0 | 20A/0¦21/0 | Manual | Ready | 0.019111 | 0.172 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-30 | 2025-08-01 | M R Constructions | 20/0 | 20A/0 | 20/0¦20A/0 | TSE | Ready | 0.021909 | 0.241 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-31 | 2025-08-01 | M R Constructions | 20A/0 | 21/0 | 20A/0¦21/0 | Manual | Ready | 0.019111 | 0.172 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-08-31 | 2025-08-01 | M R Constructions | 20/0 | 20A/0 | 20/0¦20A/0 | TSE | Ready | 0.021909 | 0.241 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-01 | 2025-09-01 | M R Constructions | 20/0 | 20A/0 | 20/0¦20A/0 | TSE | Ready | 0.021909 | 0.241 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-01 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-02 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-03 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-04 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-05 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-06 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-07 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-08 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-09 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-10 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-11 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-12 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-13 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-14 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-15 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-15 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-16 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-16 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-17 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-17 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-18 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-18 | 2025-09-01 | Nasiruddin | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.27664 | 4.9795 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-19 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-20 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-21 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-21 | 2025-09-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-22 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-22 | 2025-09-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-23 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-23 | 2025-09-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-24 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-24 | 2025-09-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-25 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-25 | 2025-09-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-26 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-26 | 2025-09-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-27 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-27 | 2025-09-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-28 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-28 | 2025-09-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-28 | 2025-09-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-29 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-29 | 2025-09-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-29 | 2025-09-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-30 | 2025-09-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-30 | 2025-09-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-09-30 | 2025-09-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-01 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-01 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-01 | 2025-10-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-02 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-02 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-02 | 2025-10-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-03 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-03 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-03 | 2025-10-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-04 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-04 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-04 | 2025-10-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-05 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-05 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-05 | 2025-10-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-06 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-06 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-06 | 2025-10-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-07 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-07 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-07 | 2025-10-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-08 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-08 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-08 | 2025-10-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-09 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-09 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-09 | 2025-10-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-10 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-10 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-10 | 2025-10-01 | Nasiruddin | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.31727 | 4.1245 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-11 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-11 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-12 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-12 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-13 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-13 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-14 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-14 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-15 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-15 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-16 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-16 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-16 | 2025-10-01 | M R Constructions | 9/0 | 10/0 | 10/0¦9/0 | TSE | Ready | 0.418 | 4.598 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-17 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-17 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-17 | 2025-10-01 | M R Constructions | 9/0 | 10/0 | 10/0¦9/0 | TSE | Ready | 0.418 | 4.598 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-18 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-18 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-18 | 2025-10-01 | M R Constructions | 9/0 | 10/0 | 10/0¦9/0 | TSE | Ready | 0.418 | 4.598 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-19 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-19 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-19 | 2025-10-01 | M R Constructions | 9/0 | 10/0 | 10/0¦9/0 | TSE | Ready | 0.418 | 4.598 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-20 | 2025-10-01 | M R Constructions | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.045545 | 1.6396 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-20 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-20 | 2025-10-01 | M R Constructions | 9/0 | 10/0 | 10/0¦9/0 | TSE | Ready | 0.418 | 4.598 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-21 | 2025-10-01 | M R Constructions | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.050452 | 1.564 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-21 | 2025-10-01 | M R Constructions | 9/0 | 10/0 | 10/0¦9/0 | TSE | Ready | 0.418 | 4.598 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-22 | 2025-10-01 | M R Constructions | 9/0 | 10/0 | 10/0¦9/0 | TSE | Ready | 0.418 | 4.598 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-23 | 2025-10-01 | M R Constructions | 9/0 | 10/0 | 10/0¦9/0 | TSE | Ready | 0.418 | 4.598 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-24 | 2025-10-01 | M R Constructions | 9/0 | 10/0 | 10/0¦9/0 | TSE | Ready | 0.418 | 4.598 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-25 | 2025-10-01 | M R Constructions | 9/0 | 10/0 | 10/0¦9/0 | TSE | Ready | 0.418 | 4.598 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-10-26 | 2025-10-01 | M R Constructions | 9/0 | 10/0 | 10/0¦9/0 | TSE | Ready | 0.418 | 4.598 | 45 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-10 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-11 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-12 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-13 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-13 | 2025-11-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.49 | 4.9 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-14 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-14 | 2025-11-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.49 | 4.9 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-15 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-15 | 2025-11-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.49 | 4.9 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-16 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-16 | 2025-11-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.49 | 4.9 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-17 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-17 | 2025-11-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.49 | 4.9 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-18 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-18 | 2025-11-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.49 | 4.9 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-19 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-19 | 2025-11-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.49 | 4.9 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-20 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-20 | 2025-11-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.49 | 4.9 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-21 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-21 | 2025-11-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.49 | 4.9 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-22 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-22 | 2025-11-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.49 | 4.9 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-23 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-24 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-25 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-26 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-27 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-27 | 2025-11-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-28 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-28 | 2025-11-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-29 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-29 | 2025-11-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-30 | 2025-11-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-11-30 | 2025-11-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-01 | 2025-12-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-01 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-02 | 2025-12-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-02 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-03 | 2025-12-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-03 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-03 | 2025-12-01 | Nasiruddin | 11/0 | 12/0 | 11/0¦12/0 | TSE | Ready | 0.67871 | 4.751 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-04 | 2025-12-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-04 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-04 | 2025-12-01 | Nasiruddin | 11/0 | 12/0 | 11/0¦12/0 | TSE | Ready | 0.67871 | 4.751 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-05 | 2025-12-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-05 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-05 | 2025-12-01 | Nasiruddin | 11/0 | 12/0 | 11/0¦12/0 | TSE | Ready | 0.67871 | 4.751 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-06 | 2025-12-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-06 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-06 | 2025-12-01 | Nasiruddin | 11/0 | 12/0 | 11/0¦12/0 | TSE | Ready | 0.67871 | 4.751 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-07 | 2025-12-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-07 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-07 | 2025-12-01 | Nasiruddin | 11/0 | 12/0 | 11/0¦12/0 | TSE | Ready | 0.67871 | 4.751 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-08 | 2025-12-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-08 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-08 | 2025-12-01 | Nasiruddin | 11/0 | 12/0 | 11/0¦12/0 | TSE | Ready | 0.67871 | 4.751 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-09 | 2025-12-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-09 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-09 | 2025-12-01 | Nasiruddin | 11/0 | 12/0 | 11/0¦12/0 | TSE | Ready | 0.67871 | 4.751 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-10 | 2025-12-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-10 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-11 | 2025-12-01 | M R Constructions | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.048094 | 1.539 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-11 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-12 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-13 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-14 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-15 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-15 | 2025-12-01 | Nasiruddin | 14/0 | 15/0 | 14/0¦15/0 | Manual | Ready | 0.166 | 0.498 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-16 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-16 | 2025-12-01 | Nasiruddin | 14/0 | 15/0 | 14/0¦15/0 | Manual | Ready | 0.166 | 0.498 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-17 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-17 | 2025-12-01 | Nasiruddin | 14/0 | 15/0 | 14/0¦15/0 | Manual | Ready | 0.166 | 0.498 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-18 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-19 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-19 | 2025-12-01 | M R Constructions | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.15917 | 1.91 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-20 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-20 | 2025-12-01 | M R Constructions | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.15917 | 1.91 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-21 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-21 | 2025-12-01 | M R Constructions | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.15917 | 1.91 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-22 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-22 | 2025-12-01 | M R Constructions | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.15917 | 1.91 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-23 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-23 | 2025-12-01 | M R Constructions | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.15917 | 1.91 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-24 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-24 | 2025-12-01 | M R Constructions | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.15917 | 1.91 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-25 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-25 | 2025-12-01 | M R Constructions | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.15917 | 1.91 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-26 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-26 | 2025-12-01 | M R Constructions | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.15917 | 1.91 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-27 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-27 | 2025-12-01 | M R Constructions | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.15917 | 1.91 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-28 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-28 | 2025-12-01 | M R Constructions | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.15917 | 1.91 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-29 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-29 | 2025-12-01 | M R Constructions | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.15917 | 1.91 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-30 | 2025-12-01 | M R Constructions | 16/0 | 17/0 | 16/0¦17/0 | TSE | Ready | 0.14006 | 4.762 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-30 | 2025-12-01 | M R Constructions | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.15917 | 1.91 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2025-12-31 | 2025-12-01 | Nasiruddin | 8/4 | 9/0 | 8/4¦9/0 | TSE | Ready | 0.61662 | 4.933 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-01 | 2026-01-01 | Nasiruddin | 8/4 | 9/0 | 8/4¦9/0 | TSE | Ready | 0.61662 | 4.933 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-02 | 2026-01-01 | Nasiruddin | 8/4 | 9/0 | 8/4¦9/0 | TSE | Ready | 0.61662 | 4.933 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-03 | 2026-01-01 | Nasiruddin | 8/4 | 9/0 | 8/4¦9/0 | TSE | Ready | 0.61662 | 4.933 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-04 | 2026-01-01 | Nasiruddin | 8/4 | 9/0 | 8/4¦9/0 | TSE | Ready | 0.61662 | 4.933 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-05 | 2026-01-01 | Nasiruddin | 8/4 | 9/0 | 8/4¦9/0 | TSE | Ready | 0.61662 | 4.933 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-06 | 2026-01-01 | Nasiruddin | 8/4 | 9/0 | 8/4¦9/0 | TSE | Ready | 0.61662 | 4.933 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-07 | 2026-01-01 | Nasiruddin | 8/4 | 9/0 | 8/4¦9/0 | TSE | Ready | 0.61662 | 4.933 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-12 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-12 | 2026-01-01 | Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE | Ready | 0.41175 | 3.294 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-13 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-13 | 2026-01-01 | Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE | Ready | 0.41175 | 3.294 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-14 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-14 | 2026-01-01 | Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE | Ready | 0.41175 | 3.294 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-15 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-15 | 2026-01-01 | Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE | Ready | 0.41175 | 3.294 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-16 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-16 | 2026-01-01 | Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE | Ready | 0.41175 | 3.294 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-17 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-17 | 2026-01-01 | Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE | Ready | 0.41175 | 3.294 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-18 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-18 | 2026-01-01 | Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE | Ready | 0.41175 | 3.294 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-19 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-19 | 2026-01-01 | Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE | Ready | 0.41175 | 3.294 | 53 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-20 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-20 | 2026-01-01 | Ramavath Electricals | 8/3 | 8/4 | 8/3¦8/4 | Hotline | Ready | 0.037444 | 0.337 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-21 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-21 | 2026-01-01 | Ramavath Electricals | 8/3 | 8/4 | 8/3¦8/4 | Hotline | Ready | 0.037444 | 0.337 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-22 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-22 | 2026-01-01 | Ramavath Electricals | 8/3 | 8/4 | 8/3¦8/4 | Hotline | Ready | 0.037444 | 0.337 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-23 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-23 | 2026-01-01 | Ramavath Electricals | 8/3 | 8/4 | 8/3¦8/4 | Hotline | Ready | 0.037444 | 0.337 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-24 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-24 | 2026-01-01 | Ramavath Electricals | 8/3 | 8/4 | 8/3¦8/4 | Hotline | Ready | 0.037444 | 0.337 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-25 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-25 | 2026-01-01 | Ramavath Electricals | 8/3 | 8/4 | 8/3¦8/4 | Hotline | Ready | 0.037444 | 0.337 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-26 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-26 | 2026-01-01 | Ramavath Electricals | 8/3 | 8/4 | 8/3¦8/4 | Hotline | Ready | 0.037444 | 0.337 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-27 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-27 | 2026-01-01 | Ramavath Electricals | 8/3 | 8/4 | 8/3¦8/4 | Hotline | Ready | 0.037444 | 0.337 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-28 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-28 | 2026-01-01 | Ramavath Electricals | 8/3 | 8/4 | 8/3¦8/4 | Hotline | Ready | 0.037444 | 0.337 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-29 | 2026-01-01 | M R Constructions | 27/3 | 28/0 | 27/3¦28/0 | TSE | Ready | 0.14889 | 2.68 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-30 | 2026-01-01 | Kamruddin | Gantry | 1/0 | 1/0¦GANTRY | Manual | Ready | 0.033323 | 0.09997 | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-30 | 2026-01-01 | Nasiruddin | 7/0 | 8/0 | 7/0¦8/0 | Manual | Ready | 0.113 | 0.226 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-31 | 2026-01-01 | Kamruddin | Gantry | 1/0 | 1/0¦GANTRY | Manual | Ready | 0.033323 | 0.09997 | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-01-31 | 2026-01-01 | Nasiruddin | 7/0 | 8/0 | 7/0¦8/0 | Manual | Ready | 0.113 | 0.226 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-01 | 2026-02-01 | Kamruddin | Gantry | 1/0 | 1/0¦GANTRY | Manual | Ready | 0.033323 | 0.09997 | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-01 | 2026-02-01 | M R Constructions | 28/0 | 29/0 | 28/0¦29/0 | TSE | Ready | 0.131 | 0.786 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-02 | 2026-02-01 | M R Constructions | 28/0 | 29/0 | 28/0¦29/0 | TSE | Ready | 0.131 | 0.786 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-03 | 2026-02-01 | Kamruddin | 1A/0 | 1B/0 | 1A/0¦1B/0 | Manual | Ready | 0.044134 |  | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-03 | 2026-02-01 | M R Constructions | 28/0 | 29/0 | 28/0¦29/0 | TSE | Ready | 0.131 | 0.786 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-03 | 2026-02-01 | Nasiruddin | 8/2 | 8/3 | 8/2¦8/3 | Manual | Ready | 0.203 | 0.406 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-04 | 2026-02-01 | Kamruddin | 1A/0 | 1B/0 | 1A/0¦1B/0 | Manual | Ready | 0.044134 |  | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-04 | 2026-02-01 | M R Constructions | 28/0 | 29/0 | 28/0¦29/0 | TSE | Ready | 0.131 | 0.786 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-04 | 2026-02-01 | Nasiruddin | 8/2 | 8/3 | 8/2¦8/3 | Manual | Ready | 0.203 | 0.406 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-05 | 2026-02-01 | Kamruddin | 1A/0 | 1B/0 | 1A/0¦1B/0 | Manual | Ready | 0.044134 |  | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-05 | 2026-02-01 | M R Constructions | 28/0 | 29/0 | 28/0¦29/0 | TSE | Ready | 0.131 | 0.786 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-06 | 2026-02-01 | Kamruddin | 1A/0 | 1B/0 | 1A/0¦1B/0 | Manual | Ready | 0.044134 |  | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-06 | 2026-02-01 | M R Constructions | 28/0 | 29/0 | 28/0¦29/0 | TSE | Ready | 0.131 | 0.786 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-06 | 2026-02-01 | Nasiruddin | 4/12 | 5/0 | 4/12¦5/0 | TSE | Ready | 0.70914 | 4.964 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-07 | 2026-02-01 | Kamruddin | 1/0 | 1A/0 | 1/0¦1A/0 | Manual | Ready | 0.1175 |  | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-07 | 2026-02-01 | Kamruddin | 1A/0 | 1B/0 | 1A/0¦1B/0 | Manual | Ready | 0.044134 |  | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-07 | 2026-02-01 | Nasiruddin | 4/12 | 5/0 | 4/12¦5/0 | TSE | Ready | 0.70914 | 4.964 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-08 | 2026-02-01 | Kamruddin | 1/0 | 1A/0 | 1/0¦1A/0 | Manual | Ready | 0.1175 |  | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-08 | 2026-02-01 | Kamruddin | 1A/0 | 1B/0 | 1A/0¦1B/0 | Manual | Ready | 0.044134 |  | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-08 | 2026-02-01 | Nasiruddin | 4/12 | 5/0 | 4/12¦5/0 | TSE | Ready | 0.70914 | 4.964 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-09 | 2026-02-01 | Kamruddin | 1A/0 | 1B/0 | 1A/0¦1B/0 | Manual | Ready | 0.044134 |  | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-09 | 2026-02-01 | Nasiruddin | 4/12 | 5/0 | 4/12¦5/0 | TSE | Ready | 0.70914 | 4.964 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-09 | 2026-02-01 | Ramavath Electricals 2 | 8/0 | 8/1 | 8/0¦8/1 | Hotline | Ready | 0.037636 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-09 | 2026-02-01 | Ramavath Electricals 1 | 8/1 | 8/2 | 8/1¦8/2 | Hotline | Ready | 0.024727 | 0.272 | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-10 | 2026-02-01 | Kamruddin | 1A/0 | 1B/0 | 1A/0¦1B/0 | Manual | Ready | 0.044134 |  | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-10 | 2026-02-01 | Nasiruddin | 4/12 | 5/0 | 4/12¦5/0 | TSE | Ready | 0.70914 | 4.964 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-10 | 2026-02-01 | Ramavath Electricals 2 | 8/0 | 8/1 | 8/0¦8/1 | Hotline | Ready | 0.037636 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-10 | 2026-02-01 | Ramavath Electricals 1 | 8/1 | 8/2 | 8/1¦8/2 | Hotline | Ready | 0.024727 | 0.272 | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-11 | 2026-02-01 | Kamruddin | 1A/0 | 1B/0 | 1A/0¦1B/0 | Manual | Ready | 0.044134 |  | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-11 | 2026-02-01 | Nasiruddin | 4/12 | 5/0 | 4/12¦5/0 | TSE | Ready | 0.70914 | 4.964 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-11 | 2026-02-01 | Ramavath Electricals 2 | 8/0 | 8/1 | 8/0¦8/1 | Hotline | Ready | 0.037636 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-11 | 2026-02-01 | Ramavath Electricals 1 | 8/1 | 8/2 | 8/1¦8/2 | Hotline | Ready | 0.024727 | 0.272 | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-12 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-12 | 2026-02-01 | Nasiruddin | 4/12 | 5/0 | 4/12¦5/0 | TSE | Ready | 0.70914 | 4.964 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-12 | 2026-02-01 | Ramavath Electricals 2 | 8/0 | 8/1 | 8/0¦8/1 | Hotline | Ready | 0.037636 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-12 | 2026-02-01 | Ramavath Electricals 1 | 8/1 | 8/2 | 8/1¦8/2 | Hotline | Ready | 0.024727 | 0.272 | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-13 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-13 | 2026-02-01 | Ramavath Electricals 2 | 8/0 | 8/1 | 8/0¦8/1 | Hotline | Ready | 0.037636 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-13 | 2026-02-01 | Ramavath Electricals 1 | 8/1 | 8/2 | 8/1¦8/2 | Hotline | Ready | 0.024727 | 0.272 | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-14 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-14 | 2026-02-01 | Ramavath Electricals 2 | 8/0 | 8/1 | 8/0¦8/1 | Hotline | Ready | 0.037636 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-14 | 2026-02-01 | Ramavath Electricals 1 | 8/1 | 8/2 | 8/1¦8/2 | Hotline | Ready | 0.024727 | 0.272 | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-15 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-15 | 2026-02-01 | Ramavath Electricals 2 | 8/0 | 8/1 | 8/0¦8/1 | Hotline | Ready | 0.037636 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-15 | 2026-02-01 | Ramavath Electricals 1 | 8/1 | 8/2 | 8/1¦8/2 | Hotline | Ready | 0.024727 | 0.272 | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-16 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-16 | 2026-02-01 | Ramavath Electricals 2 | 8/0 | 8/1 | 8/0¦8/1 | Hotline | Ready | 0.037636 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-16 | 2026-02-01 | Ramavath Electricals 1 | 8/1 | 8/2 | 8/1¦8/2 | Hotline | Ready | 0.024727 | 0.272 | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-17 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-17 | 2026-02-01 | Ramavath Electricals 2 | 8/0 | 8/1 | 8/0¦8/1 | Hotline | Ready | 0.037636 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-17 | 2026-02-01 | Ramavath Electricals 1 | 8/1 | 8/2 | 8/1¦8/2 | Hotline | Ready | 0.024727 | 0.272 | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-18 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-18 | 2026-02-01 | Ramavath Electricals 2 | 8/0 | 8/1 | 8/0¦8/1 | Hotline | Ready | 0.037636 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-18 | 2026-02-01 | Ramavath Electricals 1 | 8/1 | 8/2 | 8/1¦8/2 | Hotline | Ready | 0.024727 | 0.272 | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-19 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-19 | 2026-02-01 | Ramavath Electricals 2 | 8/0 | 8/1 | 8/0¦8/1 | Hotline | Ready | 0.037636 |  | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-19 | 2026-02-01 | Ramavath Electricals 1 | 8/1 | 8/2 | 8/1¦8/2 | Hotline | Ready | 0.024727 | 0.272 | 20 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-20 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-20 | 2026-02-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-21 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-21 | 2026-02-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-22 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-22 | 2026-02-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-23 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-23 | 2026-02-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-24 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-24 | 2026-02-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-24 | 2026-02-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-24 | 2026-02-01 | Ramavath Electricals | 1C/0 | 2/0 | 1C/0¦2/0 | Hotline | Ready | 0.31 | 0.31 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-25 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-25 | 2026-02-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-25 | 2026-02-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-26 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-26 | 2026-02-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-26 | 2026-02-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-27 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-27 | 2026-02-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-27 | 2026-02-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-28 | 2026-02-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-28 | 2026-02-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-02-28 | 2026-02-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-01 | 2026-03-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-01 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-01 | 2026-03-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-01 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-01 | 2026-03-01 | Ramavath Electricals | 5/0 | 6/0 | 5/0¦6/0 | Hotline | Ready | 0.091 | 0.182 | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-02 | 2026-03-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-02 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-02 | 2026-03-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-02 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-02 | 2026-03-01 | Ramavath Electricals | 5/0 | 6/0 | 5/0¦6/0 | Hotline | Ready | 0.091 | 0.182 | 36 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-03 | 2026-03-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-03 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-03 | 2026-03-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-03 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-04 | 2026-03-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-04 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-04 | 2026-03-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-04 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-05 | 2026-03-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-05 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-05 | 2026-03-01 | Nasiruddin | 4/0 | 4/12 | 4/0¦4/12 | TSE | Ready | 0.35486 | 4.968 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-05 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-06 | 2026-03-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-06 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-06 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-07 | 2026-03-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-07 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-07 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-08 | 2026-03-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-08 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-08 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-09 | 2026-03-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-09 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-09 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-10 | 2026-03-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-10 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-10 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-11 | 2026-03-01 | M R Constructions | 38/0 | 39/0 | 38/0¦39/0 | TSE | Ready | 0.10843 | 3.036 | 69 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-11 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-11 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-12 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-12 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-13 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-13 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-14 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-14 | 2026-03-01 | Nasiruddin | 3/0 | 4/0 | 3/0¦4/0 | TSE | Ready | 0.12007 | 1.681 | 46 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-15 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-16 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-16 | 2026-03-01 | Nasiruddin | 2/0 | 3/0 | 2/0¦3/0 | TSE | Ready | 0.473 | 2.365 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-17 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-17 | 2026-03-01 | Nasiruddin | 2/0 | 3/0 | 2/0¦3/0 | TSE | Ready | 0.473 | 2.365 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-18 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-18 | 2026-03-01 | Nasiruddin | 2/0 | 3/0 | 2/0¦3/0 | TSE | Ready | 0.473 | 2.365 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-19 | 2026-03-01 | M R Constructions | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.11579 | 2.779 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-19 | 2026-03-01 | Nasiruddin | 2/0 | 3/0 | 2/0¦3/0 | TSE | Ready | 0.473 | 2.365 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-20 | 2026-03-01 | Nasiruddin | 2/0 | 3/0 | 2/0¦3/0 | TSE | Ready | 0.473 | 2.365 | 56 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-26 | 2026-03-01 | Kamruddin | 39/0 | 40/0 | 39/0¦40/0 | TSE | Ready | 0.52625 | 4.21 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-26 | 2026-03-01 | Nasiruddin | 1B/0 | 1C/0 | 1B/0¦1C/0 | TSE | Ready | 0.4215 | 1.686 | 50 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-27 | 2026-03-01 | Kamruddin | 39/0 | 40/0 | 39/0¦40/0 | TSE | Ready | 0.52625 | 4.21 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-27 | 2026-03-01 | Nasiruddin | 1B/0 | 1C/0 | 1B/0¦1C/0 | TSE | Ready | 0.4215 | 1.686 | 50 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-28 | 2026-03-01 | Kamruddin | 39/0 | 40/0 | 39/0¦40/0 | TSE | Ready | 0.52625 | 4.21 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-28 | 2026-03-01 | Nasiruddin | 1B/0 | 1C/0 | 1B/0¦1C/0 | TSE | Ready | 0.4215 | 1.686 | 50 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-29 | 2026-03-01 | Kamruddin | 39/0 | 40/0 | 39/0¦40/0 | TSE | Ready | 0.52625 | 4.21 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-29 | 2026-03-01 | Nasiruddin | 1B/0 | 1C/0 | 1B/0¦1C/0 | TSE | Ready | 0.4215 | 1.686 | 50 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-30 | 2026-03-01 | Kamruddin | 39/0 | 40/0 | 39/0¦40/0 | TSE | Ready | 0.52625 | 4.21 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-03-31 | 2026-03-01 | Kamruddin | 39/0 | 40/0 | 39/0¦40/0 | TSE | Ready | 0.52625 | 4.21 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-01 | 2026-04-01 | Kamruddin | 39/0 | 40/0 | 39/0¦40/0 | TSE | Ready | 0.52625 | 4.21 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-02 | 2026-04-01 | Kamruddin | 39/0 | 40/0 | 39/0¦40/0 | TSE | Ready | 0.52625 | 4.21 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-13 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-14 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-15 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-16 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-17 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-18 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-19 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-20 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-21 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-22 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-23 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-24 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-25 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-26 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-27 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-28 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-29 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-30 | 2026-04-01 | Kamruddin | 36/0 | 37/0 | 36/0¦37/0 | TSE | Ready | 0.20044 | 3.608 | 42 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-04-30 | 2026-04-01 | Nasiruddin | 42/0 | 43/0 | 42/0¦43/0 | TSE | Ready | 0.359 | 3.949 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-01 | 2026-05-01 | Nasiruddin | 42/0 | 43/0 | 42/0¦43/0 | TSE | Ready | 0.359 | 3.949 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-02 | 2026-05-01 | Nasiruddin | 42/0 | 43/0 | 42/0¦43/0 | TSE | Ready | 0.359 | 3.949 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-03 | 2026-05-01 | Nasiruddin | 42/0 | 43/0 | 42/0¦43/0 | TSE | Ready | 0.359 | 3.949 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-04 | 2026-05-01 | Nasiruddin | 42/0 | 43/0 | 42/0¦43/0 | TSE | Ready | 0.359 | 3.949 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-05 | 2026-05-01 | Nasiruddin | 42/0 | 43/0 | 42/0¦43/0 | TSE | Ready | 0.359 | 3.949 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-06 | 2026-05-01 | Nasiruddin | 42/0 | 43/0 | 42/0¦43/0 | TSE | Ready | 0.359 | 3.949 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-07 | 2026-05-01 | Nasiruddin | 42/0 | 43/0 | 42/0¦43/0 | TSE | Ready | 0.359 | 3.949 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-08 | 2026-05-01 | Nasiruddin | 42/0 | 43/0 | 42/0¦43/0 | TSE | Ready | 0.359 | 3.949 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-09 | 2026-05-01 | Nasiruddin | 42/0 | 43/0 | 42/0¦43/0 | TSE | Ready | 0.359 | 3.949 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-10 | 2026-05-01 | Nasiruddin | 42/0 | 43/0 | 42/0¦43/0 | TSE | Ready | 0.359 | 3.949 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-14 | 2026-05-01 | Nasiruddin | 43/0 | 43A/0 | 43/0¦43A/0 | TSE | Ready | 0.4524 | 2.262 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-15 | 2026-05-01 | Nasiruddin | 43/0 | 43A/0 | 43/0¦43A/0 | TSE | Ready | 0.4524 | 2.262 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-16 | 2026-05-01 | Nasiruddin | 43/0 | 43A/0 | 43/0¦43A/0 | TSE | Ready | 0.4524 | 2.262 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-17 | 2026-05-01 | Nasiruddin | 43/0 | 43A/0 | 43/0¦43A/0 | TSE | Ready | 0.4524 | 2.262 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-18 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-18 | 2026-05-01 | Nasiruddin | 43/0 | 43A/0 | 43/0¦43A/0 | TSE | Ready | 0.4524 | 2.262 | 43 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-18 | 2026-05-01 | Ramavath | 34/2 | 35/0 | 34/2¦35/0 | Hotline | Ready | 0.027556 | 0.248 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-19 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-19 | 2026-05-01 | Ramavath | 34/2 | 35/0 | 34/2¦35/0 | Hotline | Ready | 0.027556 | 0.248 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-20 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-20 | 2026-05-01 | Ramavath | 34/2 | 35/0 | 34/2¦35/0 | Hotline | Ready | 0.027556 | 0.248 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-21 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-21 | 2026-05-01 | Ramavath | 34/2 | 35/0 | 34/2¦35/0 | Hotline | Ready | 0.027556 | 0.248 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-22 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-22 | 2026-05-01 | Ramavath | 34/2 | 35/0 | 34/2¦35/0 | Hotline | Ready | 0.027556 | 0.248 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-23 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-23 | 2026-05-01 | Ramavath | 34/2 | 35/0 | 34/2¦35/0 | Hotline | Ready | 0.027556 | 0.248 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-24 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-24 | 2026-05-01 | Ramavath | 34/2 | 35/0 | 34/2¦35/0 | Hotline | Ready | 0.027556 | 0.248 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-25 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-25 | 2026-05-01 | Ramavath | 34/2 | 35/0 | 34/2¦35/0 | Hotline | Ready | 0.027556 | 0.248 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-26 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-26 | 2026-05-01 | Ramavath | 34/2 | 35/0 | 34/2¦35/0 | Hotline | Ready | 0.027556 | 0.248 | 17 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-27 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-28 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-29 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-05-30 | 2026-05-01 | Kamruddin | 35/0 | 36/0 | 35/0¦36/0 | TSE | Ready | 0.14292 | 1.858 | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 421 | TA 421 | ta421 |  | 2026-06-10 | 2026-06-01 |  | 43A/0 | 43A/1 | 43A/0¦43A/1 | Manual | Ready | 0.485 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | NO_DATA | No manpower values found for this span/day.
TA 504 | TA 504 | ta504 |  | 2026-02-04 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-05 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-06 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-07 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-08 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-09 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-10 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-11 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-11 | 2026-02-01 | Lamba Construction | 17/0 | 17/4 | 17/0¦17/4 | TSE | Ready | 0.13725 | 1.647 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-12 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-12 | 2026-02-01 | Lamba Construction | 17/0 | 17/4 | 17/0¦17/4 | TSE | Ready | 0.13725 | 1.647 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-13 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-13 | 2026-02-01 | Lamba Construction | 17/0 | 17/4 | 17/0¦17/4 | TSE | Ready | 0.13725 | 1.647 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-14 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-14 | 2026-02-01 | Lamba Construction | 17/0 | 17/4 | 17/0¦17/4 | TSE | Ready | 0.13725 | 1.647 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-15 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-15 | 2026-02-01 | Lamba Construction | 17/0 | 17/4 | 17/0¦17/4 | TSE | Ready | 0.13725 | 1.647 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-16 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-16 | 2026-02-01 | Lamba Construction | 17/0 | 17/4 | 17/0¦17/4 | TSE | Ready | 0.13725 | 1.647 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-17 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-17 | 2026-02-01 | Lamba Construction | 17/0 | 17/4 | 17/0¦17/4 | TSE | Ready | 0.13725 | 1.647 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-17 | 2026-02-01 | Lamba Construction | 17/4 | 18/0 | 17/4¦18/0 | TSE | Ready | 0.20948 | 2.3042 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-18 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-18 | 2026-02-01 | Lamba Construction | 17/0 | 17/4 | 17/0¦17/4 | TSE | Ready | 0.13725 | 1.647 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-18 | 2026-02-01 | Lamba Construction | 17/4 | 18/0 | 17/4¦18/0 | TSE | Ready | 0.20948 | 2.3042 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-19 | 2026-02-01 | Lamba Construction | 16/3 | 17/0 | 16/3¦17/0 | TSE | Ready | 0.091663 | 1.4666 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-19 | 2026-02-01 | Lamba Construction | 17/0 | 17/4 | 17/0¦17/4 | TSE | Ready | 0.13725 | 1.647 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-19 | 2026-02-01 | Lamba Construction | 17/4 | 18/0 | 17/4¦18/0 | TSE | Ready | 0.20948 | 2.3042 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-19 | 2026-02-01 | Lamba Construction | 18/0 | 18/1 | 18/0¦18/1 | Manual | Ready | 0.0503 | 0.503 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-19 | 2026-02-01 | Lamba Construction | 18/1 | 19/0 | 18/1¦19/0 | TSE | Ready | 0.30252 | 3.025 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-20 | 2026-02-01 | Lamba Construction | 17/0 | 17/4 | 17/0¦17/4 | TSE | Ready | 0.13725 | 1.647 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-20 | 2026-02-01 | Lamba Construction | 17/4 | 18/0 | 17/4¦18/0 | TSE | Ready | 0.20948 | 2.3042 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-20 | 2026-02-01 | Lamba Construction | 18/0 | 18/1 | 18/0¦18/1 | Manual | Ready | 0.0503 | 0.503 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-20 | 2026-02-01 | Lamba Construction | 18/1 | 19/0 | 18/1¦19/0 | TSE | Ready | 0.30252 | 3.025 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-21 | 2026-02-01 | Lamba Construction | 17/0 | 17/4 | 17/0¦17/4 | TSE | Ready | 0.13725 | 1.647 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-21 | 2026-02-01 | Lamba Construction | 17/4 | 18/0 | 17/4¦18/0 | TSE | Ready | 0.20948 | 2.3042 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-21 | 2026-02-01 | Lamba Construction | 18/0 | 18/1 | 18/0¦18/1 | Manual | Ready | 0.0503 | 0.503 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-21 | 2026-02-01 | Lamba Construction | 18/1 | 19/0 | 18/1¦19/0 | TSE | Ready | 0.30252 | 3.025 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-22 | 2026-02-01 | Lamba Construction | 17/0 | 17/4 | 17/0¦17/4 | TSE | Ready | 0.13725 | 1.647 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-22 | 2026-02-01 | Lamba Construction | 17/4 | 18/0 | 17/4¦18/0 | TSE | Ready | 0.20948 | 2.3042 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-22 | 2026-02-01 | Lamba Construction | 18/0 | 18/1 | 18/0¦18/1 | Manual | Ready | 0.0503 | 0.503 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-22 | 2026-02-01 | Lamba Construction | 18/1 | 19/0 | 18/1¦19/0 | TSE | Ready | 0.30252 | 3.025 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-23 | 2026-02-01 | Lamba Construction | 17/4 | 18/0 | 17/4¦18/0 | TSE | Ready | 0.20948 | 2.3042 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-23 | 2026-02-01 | Lamba Construction | 18/0 | 18/1 | 18/0¦18/1 | Manual | Ready | 0.0503 | 0.503 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-23 | 2026-02-01 | Lamba Construction | 18/1 | 19/0 | 18/1¦19/0 | TSE | Ready | 0.30252 | 3.025 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-24 | 2026-02-01 | Lamba Construction | 17/4 | 18/0 | 17/4¦18/0 | TSE | Ready | 0.20948 | 2.3042 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-24 | 2026-02-01 | Lamba Construction | 18/0 | 18/1 | 18/0¦18/1 | Manual | Ready | 0.0503 | 0.503 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-24 | 2026-02-01 | Lamba Construction | 18/1 | 19/0 | 18/1¦19/0 | TSE | Ready | 0.30252 | 3.025 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-25 | 2026-02-01 | Lamba Construction | 17/4 | 18/0 | 17/4¦18/0 | TSE | Ready | 0.20948 | 2.3042 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-25 | 2026-02-01 | Lamba Construction | 18/0 | 18/1 | 18/0¦18/1 | Manual | Ready | 0.0503 | 0.503 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-25 | 2026-02-01 | Lamba Construction | 18/1 | 19/0 | 18/1¦19/0 | TSE | Ready | 0.30252 | 3.025 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-26 | 2026-02-01 | Lamba Construction | 17/4 | 18/0 | 17/4¦18/0 | TSE | Ready | 0.20948 | 2.3042 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-26 | 2026-02-01 | Lamba Construction | 18/0 | 18/1 | 18/0¦18/1 | Manual | Ready | 0.0503 | 0.503 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-26 | 2026-02-01 | Lamba Construction | 18/1 | 19/0 | 18/1¦19/0 | TSE | Ready | 0.30252 | 3.025 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-27 | 2026-02-01 | Lamba Construction | 17/4 | 18/0 | 17/4¦18/0 | TSE | Ready | 0.20948 | 2.3042 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-27 | 2026-02-01 | Lamba Construction | 18/0 | 18/1 | 18/0¦18/1 | Manual | Ready | 0.0503 | 0.503 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-27 | 2026-02-01 | Lamba Construction | 18/1 | 19/0 | 18/1¦19/0 | TSE | Ready | 0.30252 | 3.025 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-28 | 2026-02-01 | Lamba Construction | 18/0 | 18/1 | 18/0¦18/1 | Manual | Ready | 0.0503 | 0.503 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-02-28 | 2026-02-01 | Lamba Construction | 18/1 | 19/0 | 18/1¦19/0 | TSE | Ready | 0.30252 | 3.025 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-03-25 | 2026-03-01 | Lamba Construction | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.29361 | 3.2297 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-03-26 | 2026-03-01 | Lamba Construction | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.29361 | 3.2297 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-03-27 | 2026-03-01 | Lamba Construction | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.29361 | 3.2297 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-03-28 | 2026-03-01 | Lamba Construction | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.29361 | 3.2297 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-03-29 | 2026-03-01 | Lamba Construction | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.29361 | 3.2297 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-03-30 | 2026-03-01 | Lamba Construction | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.29361 | 3.2297 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-03-31 | 2026-03-01 | Lamba Construction | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.29361 | 3.2297 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-01 | 2026-04-01 | Lamba Construction | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.29361 | 3.2297 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-01 | 2026-04-01 | Lamba Construction | 16/0 | 16/3 | 16/0¦16/3 | TSE | Ready | 0.13844 | 1.246 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-02 | 2026-04-01 | Lamba Construction | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.29361 | 3.2297 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-02 | 2026-04-01 | Lamba Construction | 16/0 | 16/3 | 16/0¦16/3 | TSE | Ready | 0.13844 | 1.246 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-03 | 2026-04-01 | Lamba Construction | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.29361 | 3.2297 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-03 | 2026-04-01 | Lamba Construction | 16/0 | 16/3 | 16/0¦16/3 | TSE | Ready | 0.13844 | 1.246 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-04 | 2026-04-01 | Lamba Construction | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.29361 | 3.2297 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-04 | 2026-04-01 | Lamba Construction | 16/0 | 16/3 | 16/0¦16/3 | TSE | Ready | 0.13844 | 1.246 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-05 | 2026-04-01 | Lamba Construction | 16/0 | 16/3 | 16/0¦16/3 | TSE | Ready | 0.13844 | 1.246 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-06 | 2026-04-01 | Lamba Construction | 16/0 | 16/3 | 16/0¦16/3 | TSE | Ready | 0.13844 | 1.246 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-07 | 2026-04-01 | Lamba Construction | 16/0 | 16/3 | 16/0¦16/3 | TSE | Ready | 0.13844 | 1.246 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-08 | 2026-04-01 | Lamba Construction | 16/0 | 16/3 | 16/0¦16/3 | TSE | Ready | 0.13844 | 1.246 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-04-09 | 2026-04-01 | Lamba Construction | 16/0 | 16/3 | 16/0¦16/3 | TSE | Ready | 0.13844 | 1.246 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-16 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-16 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-17 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-17 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-18 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-18 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-19 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-19 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-20 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-20 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-21 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-21 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-22 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-22 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-23 | 2026-05-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-23 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-23 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-24 | 2026-05-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-24 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-24 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-25 | 2026-05-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-25 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-25 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-26 | 2026-05-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-26 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-26 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-27 | 2026-05-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-27 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-27 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-28 | 2026-05-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-28 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-28 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-29 | 2026-05-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-29 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-29 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-30 | 2026-05-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-30 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-30 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-31 | 2026-05-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-31 | 2026-05-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-05-31 | 2026-05-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-01 | 2026-06-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-01 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-01 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-02 | 2026-06-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-02 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-02 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-03 | 2026-06-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-03 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-03 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-04 | 2026-06-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-04 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-04 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-05 | 2026-06-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-05 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-05 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-06 | 2026-06-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-06 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-06 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-07 | 2026-06-01 | Lamba Construction | 19/0 | 20/0 | 19/0¦20/0 | TSE | Ready | 0.098347 | 1.5736 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-07 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-07 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-08 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-08 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-09 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-09 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-10 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-10 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-11 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-11 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-12 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-12 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-13 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-13 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-14 | 2026-06-01 | Lamba Construction | 20/0 | 21/0 | 20/0¦21/0 | Manual | Ready | 0.015356 | 0.46068 | 50 | 13 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-14 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 504 | TA 504 | ta504 |  | 2026-06-15 | 2026-06-01 | Tanjira Bibi | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.07653 | 2.3724 | 40 | 10 | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-20 | 2026-01-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-21 | 2026-01-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-22 | 2026-01-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-23 | 2026-01-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-24 | 2026-01-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-25 | 2026-01-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-26 | 2026-01-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-27 | 2026-01-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-27 | 2026-01-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-28 | 2026-01-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-28 | 2026-01-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-29 | 2026-01-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-29 | 2026-01-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-30 | 2026-01-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-30 | 2026-01-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-31 | 2026-01-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-01-31 | 2026-01-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-01 | 2026-02-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-01 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-02 | 2026-02-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-02 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-03 | 2026-02-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-03 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-04 | 2026-02-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-04 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-05 | 2026-02-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-05 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-06 | 2026-02-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-06 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-07 | 2026-02-01 | Alimuddin | 100/0 | 101/0 | 100/0¦101/0 | Manual | Ready | 0.022053 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-07 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-08 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-08 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-09 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-09 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-10 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-10 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-11 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-11 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-12 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-12 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-13 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-13 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-14 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-14 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-15 | 2026-02-01 | Alimuddin | 101/0 | 102/0 | 101/0¦102/0 | TSE | Ready | 0.1735 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-15 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-16 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-16 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-17 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-17 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-18 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-18 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-19 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-19 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-20 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-20 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-21 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-21 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-22 | 2026-02-01 | Alimuddin | 102/0 | 103/0 | 102/0¦103/0 | Manual | Ready | 0.030733 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-22 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-23 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-24 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-24 | 2026-02-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-25 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-25 | 2026-02-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-26 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-26 | 2026-02-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-27 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-27 | 2026-02-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-28 | 2026-02-01 | Alimuddin | 103/0 | 103/5A | 103/0¦103/5A | TSE | Ready | 0.16923 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-02-28 | 2026-02-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-01 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-02 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-03 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-04 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-05 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-06 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-07 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-07 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-08 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-08 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-09 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-09 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-10 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-10 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-11 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-11 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-12 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-12 | 2026-03-01 | Alimuddin | 103/6A | 104/0 | 103/6A¦104/0 | TSE | Ready | 0.15589 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-12 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-13 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-13 | 2026-03-01 | Alimuddin | 103/6A | 104/0 | 103/6A¦104/0 | TSE | Ready | 0.15589 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-13 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-14 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-14 | 2026-03-01 | Alimuddin | 103/6A | 104/0 | 103/6A¦104/0 | TSE | Ready | 0.15589 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-14 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-15 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-15 | 2026-03-01 | Alimuddin | 103/6A | 104/0 | 103/6A¦104/0 | TSE | Ready | 0.15589 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-15 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-16 | 2026-03-01 | Alimuddin | 103/5A | 103/6A | 103/5A¦103/6A | TSE | Ready | 0.027 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-16 | 2026-03-01 | Alimuddin | 103/6A | 104/0 | 103/6A¦104/0 | TSE | Ready | 0.15589 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-16 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-17 | 2026-03-01 | Alimuddin | 103/6A | 104/0 | 103/6A¦104/0 | TSE | Ready | 0.15589 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-17 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-18 | 2026-03-01 | Alimuddin | 103/6A | 104/0 | 103/6A¦104/0 | TSE | Ready | 0.15589 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-18 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-19 | 2026-03-01 | Alimuddin | 103/6A | 104/0 | 103/6A¦104/0 | TSE | Ready | 0.15589 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-19 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-20 | 2026-03-01 | Alimuddin | 103/6A | 104/0 | 103/6A¦104/0 | TSE | Ready | 0.15589 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-20 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-21 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-22 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-23 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-24 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-25 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-25 | 2026-03-01 | Jahangir Alam | 113/0 | 114/0 | 113/0¦114/0 | TSE | Ready | 0.36643 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-26 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-26 | 2026-03-01 | Jahangir Alam | 113/0 | 114/0 | 113/0¦114/0 | TSE | Ready | 0.36643 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-27 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-27 | 2026-03-01 | Jahangir Alam | 113/0 | 114/0 | 113/0¦114/0 | TSE | Ready | 0.36643 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-28 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-28 | 2026-03-01 | Alimuddin | 111/0 | 112/0 | 111/0¦112/0 | TSE | Ready | 0.4885 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-28 | 2026-03-01 | Jahangir Alam | 113/0 | 114/0 | 113/0¦114/0 | TSE | Ready | 0.36643 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-29 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-29 | 2026-03-01 | Alimuddin | 111/0 | 112/0 | 111/0¦112/0 | TSE | Ready | 0.4885 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-29 | 2026-03-01 | Jahangir Alam | 113/0 | 114/0 | 113/0¦114/0 | TSE | Ready | 0.36643 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-30 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-30 | 2026-03-01 | Alimuddin | 111/0 | 112/0 | 111/0¦112/0 | TSE | Ready | 0.4885 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-30 | 2026-03-01 | Jahangir Alam | 113/0 | 114/0 | 113/0¦114/0 | TSE | Ready | 0.36643 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-31 | 2026-03-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-31 | 2026-03-01 | Alimuddin | 111/0 | 112/0 | 111/0¦112/0 | TSE | Ready | 0.4885 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-03-31 | 2026-03-01 | Jahangir Alam | 113/0 | 114/0 | 113/0¦114/0 | TSE | Ready | 0.36643 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-01 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-02 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-03 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-04 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-05 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-06 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-07 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-08 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-09 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-10 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-11 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-12 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-13 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-14 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-15 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-16 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-04-17 | 2026-04-01 | Alimuddin | 104/0 | 105/0 | 104/0¦105/0 | TSE | Ready | 0.023024 |  | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-14 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-15 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-16 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-17 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-18 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-19 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-20 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-21 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-22 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-22 | 2026-05-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-23 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-23 | 2026-05-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-24 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-24 | 2026-05-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-24 | 2026-05-01 | Ram Singh | 112/0 | 113/0 | 112/0¦113/0 | Hot Line | Ready | 0.032286 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-25 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-25 | 2026-05-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-25 | 2026-05-01 | Ram Singh | 112/0 | 113/0 | 112/0¦113/0 | Hot Line | Ready | 0.032286 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-26 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-26 | 2026-05-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-26 | 2026-05-01 | Ram Singh | 112/0 | 113/0 | 112/0¦113/0 | Hot Line | Ready | 0.032286 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-27 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-27 | 2026-05-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-27 | 2026-05-01 | Ram Singh | 112/0 | 113/0 | 112/0¦113/0 | Hot Line | Ready | 0.032286 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-28 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-28 | 2026-05-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-28 | 2026-05-01 | Ram Singh | 112/0 | 113/0 | 112/0¦113/0 | Hot Line | Ready | 0.032286 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-29 | 2026-05-01 | Alimuddin | 110A/0 | 111/0 | 110A/0¦111/0 | TSE | Ready | 0.076875 |  | 35 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-29 | 2026-05-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-29 | 2026-05-01 | Ram Singh | 112/0 | 113/0 | 112/0¦113/0 | Hot Line | Ready | 0.032286 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-30 | 2026-05-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-30 | 2026-05-01 | Ram Singh | 112/0 | 113/0 | 112/0¦113/0 | Hot Line | Ready | 0.032286 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-05-31 | 2026-05-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-01 | 2026-06-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-01 | 2026-06-01 | Ram Singh | 115/0 | 116/0 | 115/0¦116/0 | Hot Line | Ready | 0.016667 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-02 | 2026-06-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-02 | 2026-06-01 | Ram Singh | 115/0 | 116/0 | 115/0¦116/0 | Hot Line | Ready | 0.016667 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-03 | 2026-06-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-03 | 2026-06-01 | Ram Singh | 115/0 | 116/0 | 115/0¦116/0 | Hot Line | Ready | 0.016667 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-04 | 2026-06-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-04 | 2026-06-01 | Ram Singh | 115/0 | 116/0 | 115/0¦116/0 | Hot Line | Ready | 0.016667 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-05 | 2026-06-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-05 | 2026-06-01 | Ram Singh | 115/0 | 116/0 | 115/0¦116/0 | Hot Line | Ready | 0.016667 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-06 | 2026-06-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-06 | 2026-06-01 | Ram Singh | 115/0 | 116/0 | 115/0¦116/0 | Hot Line | Ready | 0.016667 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-07 | 2026-06-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-07 | 2026-06-01 | Ram Singh | 115/0 | 116/0 | 115/0¦116/0 | Hot Line | Ready | 0.016667 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-08 | 2026-06-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-08 | 2026-06-01 | Nasiruddin | 110/0 | 110A/0 | 110/0¦110A/0 | TSE | Ready | 0.42889 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-08 | 2026-06-01 | Ram Singh | 115/0 | 116/0 | 115/0¦116/0 | Hot Line | Ready | 0.016667 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-09 | 2026-06-01 | Jahangir Alam | 114/0 | 115/0 | 114/0¦115/0 | TSE | Ready | 0.22653 |  | 38 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-09 | 2026-06-01 | Nasiruddin | 110/0 | 110A/0 | 110/0¦110A/0 | TSE | Ready | 0.42889 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-09 | 2026-06-01 | Ram Singh | 115/0 | 116/0 | 115/0¦116/0 | Hot Line | Ready | 0.016667 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-10 | 2026-06-01 | Nasiruddin | 110/0 | 110A/0 | 110/0¦110A/0 | TSE | Ready | 0.42889 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-10 | 2026-06-01 | Ram Singh | 115/0 | 116/0 | 115/0¦116/0 | Hot Line | Ready | 0.016667 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-11 | 2026-06-01 | Nasiruddin | 110/0 | 110A/0 | 110/0¦110A/0 | TSE | Ready | 0.42889 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-11 | 2026-06-01 | Ram Singh | 115/0 | 116/0 | 115/0¦116/0 | Hot Line | Ready | 0.016667 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-12 | 2026-06-01 | Nasiruddin | 110/0 | 110A/0 | 110/0¦110A/0 | TSE | Ready | 0.42889 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-12 | 2026-06-01 | Ram Singh | 115/0 | 116/0 | 115/0¦116/0 | Hot Line | Ready | 0.016667 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-13 | 2026-06-01 | Nasiruddin | 110/0 | 110A/0 | 110/0¦110A/0 | TSE | Ready | 0.42889 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-14 | 2026-06-01 | Nasiruddin | 110/0 | 110A/0 | 110/0¦110A/0 | TSE | Ready | 0.42889 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-15 | 2026-06-01 | Nasiruddin | 110/0 | 110A/0 | 110/0¦110A/0 | TSE | Ready | 0.42889 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 505 | TA 505 | ta505 |  | 2026-06-16 | 2026-06-01 | Nasiruddin | 110/0 | 110A/0 | 110/0¦110A/0 | TSE | Ready | 0.42889 |  | 25 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-19 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-19 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-20 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-20 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-21 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-21 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-22 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-22 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-23 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-23 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-24 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-24 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-25 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-25 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-26 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-26 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-27 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-27 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-28 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-28 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-29 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-29 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-30 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-30 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-31 | 2025-12-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2025-12-31 | 2025-12-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-01 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-01 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-02 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-02 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-03 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-03 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-04 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-04 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-05 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-05 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-06 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-06 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-07 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-07 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-08 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-08 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-09 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-09 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-10 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-10 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-11 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-11 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-12 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-12 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-13 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-13 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-14 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-14 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-15 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-15 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-16 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-16 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-17 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-17 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-17 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-18 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-18 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-18 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-18 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-19 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-19 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-19 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-19 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-20 | 2026-01-01 | Jahangir Alam | 48/0 | 50/0 | 48/0¦50/0 | TSE | Ready | 0.020863 | 0.68847 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-20 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-20 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-20 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-21 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-21 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-21 | 2026-01-01 | Jahangir Alam | 51A/0 | 51C/0 | 51A/0¦51C/0 | TSE | Ready | 0.11226 | 1.2348 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-21 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-22 | 2026-01-01 | Jahangir Alam | 50/0 | 51/0 | 50/0¦51/0 | TSE | Ready | 0.033145 | 1.1601 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-22 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-22 | 2026-01-01 | Jahangir Alam | 51A/0 | 51C/0 | 51A/0¦51C/0 | TSE | Ready | 0.11226 | 1.2348 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-22 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-22 | 2026-01-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-23 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-23 | 2026-01-01 | Jahangir Alam | 51A/0 | 51C/0 | 51A/0¦51C/0 | TSE | Ready | 0.11226 | 1.2348 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-23 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-23 | 2026-01-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-24 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-24 | 2026-01-01 | Jahangir Alam | 51A/0 | 51C/0 | 51A/0¦51C/0 | TSE | Ready | 0.11226 | 1.2348 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-24 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-24 | 2026-01-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-25 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-25 | 2026-01-01 | Jahangir Alam | 51A/0 | 51C/0 | 51A/0¦51C/0 | TSE | Ready | 0.11226 | 1.2348 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-25 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-25 | 2026-01-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-26 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-26 | 2026-01-01 | Jahangir Alam | 51A/0 | 51C/0 | 51A/0¦51C/0 | TSE | Ready | 0.11226 | 1.2348 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-26 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-26 | 2026-01-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-27 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-27 | 2026-01-01 | Jahangir Alam | 51A/0 | 51C/0 | 51A/0¦51C/0 | TSE | Ready | 0.11226 | 1.2348 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-27 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-27 | 2026-01-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-28 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-28 | 2026-01-01 | Jahangir Alam | 51A/0 | 51C/0 | 51A/0¦51C/0 | TSE | Ready | 0.11226 | 1.2348 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-28 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-28 | 2026-01-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-29 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-29 | 2026-01-01 | Jahangir Alam | 51A/0 | 51C/0 | 51A/0¦51C/0 | TSE | Ready | 0.11226 | 1.2348 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-29 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-29 | 2026-01-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-30 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-30 | 2026-01-01 | Jahangir Alam | 51A/0 | 51C/0 | 51A/0¦51C/0 | TSE | Ready | 0.11226 | 1.2348 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-30 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-30 | 2026-01-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-31 | 2026-01-01 | Jahangir Alam | 51/0 | 51A/0 | 51/0¦51A/0 | TSE | Ready | 0.08299 | 1.2449 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-31 | 2026-01-01 | Jahangir Alam | 51A/0 | 51C/0 | 51A/0¦51C/0 | TSE | Ready | 0.11226 | 1.2348 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-31 | 2026-01-01 | National Construction | 1/0 | 2/0 | 1/0¦2/0 | TSE | Ready | 0.31601 | 4.4241 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-01-31 | 2026-01-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-01 | 2026-02-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-02 | 2026-02-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-03 | 2026-02-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-04 | 2026-02-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-05 | 2026-02-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | TSE | Ready | 0.32996 | 4.9493 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-13 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-14 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-15 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-15 | 2026-02-01 | National Construction | 2/0 | 2A/0 | 2/0¦2A/0 | TSE | Ready | 0.36873 | 3.3186 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-16 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-16 | 2026-02-01 | National Construction | 2/0 | 2A/0 | 2/0¦2A/0 | TSE | Ready | 0.36873 | 3.3186 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-17 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-17 | 2026-02-01 | Jahangir Alam | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.32783 | 3.934 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-17 | 2026-02-01 | National Construction | 2/0 | 2A/0 | 2/0¦2A/0 | TSE | Ready | 0.36873 | 3.3186 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-18 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-18 | 2026-02-01 | Jahangir Alam | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.32783 | 3.934 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-18 | 2026-02-01 | National Construction | 2/0 | 2A/0 | 2/0¦2A/0 | TSE | Ready | 0.36873 | 3.3186 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-19 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-19 | 2026-02-01 | Jahangir Alam | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.32783 | 3.934 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-19 | 2026-02-01 | National Construction | 2/0 | 2A/0 | 2/0¦2A/0 | TSE | Ready | 0.36873 | 3.3186 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-20 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-20 | 2026-02-01 | Jahangir Alam | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.32783 | 3.934 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-20 | 2026-02-01 | National Construction | 2/0 | 2A/0 | 2/0¦2A/0 | TSE | Ready | 0.36873 | 3.3186 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-21 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-21 | 2026-02-01 | Jahangir Alam | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.32783 | 3.934 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-21 | 2026-02-01 | National Construction | 2/0 | 2A/0 | 2/0¦2A/0 | TSE | Ready | 0.36873 | 3.3186 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-22 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-22 | 2026-02-01 | Jahangir Alam | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.32783 | 3.934 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-22 | 2026-02-01 | National Construction | 2/0 | 2A/0 | 2/0¦2A/0 | TSE | Ready | 0.36873 | 3.3186 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-23 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-23 | 2026-02-01 | Jahangir Alam | 52/0 | 53/0 | 52/0¦53/0 | TSE | Ready | 0.19842 | 0.99208 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-23 | 2026-02-01 | Jahangir Alam | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.32783 | 3.934 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-23 | 2026-02-01 | National Construction | 2/0 | 2A/0 | 2/0¦2A/0 | TSE | Ready | 0.36873 | 3.3186 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-23 | 2026-02-01 | National Construction | 4/0 | 5/0 | 4/0¦5/0 | TSE | Ready | 0.46817 | 2.809 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-24 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-24 | 2026-02-01 | Jahangir Alam | 52/0 | 53/0 | 52/0¦53/0 | TSE | Ready | 0.19842 | 0.99208 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-24 | 2026-02-01 | Jahangir Alam | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.32783 | 3.934 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-24 | 2026-02-01 | National Construction | 4/0 | 5/0 | 4/0¦5/0 | TSE | Ready | 0.46817 | 2.809 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-25 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-25 | 2026-02-01 | Jahangir Alam | 52/0 | 53/0 | 52/0¦53/0 | TSE | Ready | 0.19842 | 0.99208 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-25 | 2026-02-01 | Jahangir Alam | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.32783 | 3.934 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-25 | 2026-02-01 | National Construction | 4/0 | 5/0 | 4/0¦5/0 | TSE | Ready | 0.46817 | 2.809 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-26 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-26 | 2026-02-01 | Jahangir Alam | 52/0 | 53/0 | 52/0¦53/0 | TSE | Ready | 0.19842 | 0.99208 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-26 | 2026-02-01 | Jahangir Alam | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.32783 | 3.934 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-26 | 2026-02-01 | National Construction | 4/0 | 5/0 | 4/0¦5/0 | TSE | Ready | 0.46817 | 2.809 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-27 | 2026-02-01 | Jahangir Alam | 51C/0 | 52/0 | 51C/0¦52/0 | TSE | Ready | 0.13121 | 1.9682 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-27 | 2026-02-01 | Jahangir Alam | 52/0 | 53/0 | 52/0¦53/0 | TSE | Ready | 0.19842 | 0.99208 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-27 | 2026-02-01 | Jahangir Alam | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.32783 | 3.934 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-27 | 2026-02-01 | National Construction | 4/0 | 5/0 | 4/0¦5/0 | TSE | Ready | 0.46817 | 2.809 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-28 | 2026-02-01 | Jahangir Alam | 18/0 | 19/0 | 18/0¦19/0 | TSE | Ready | 0.32783 | 3.934 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-02-28 | 2026-02-01 | National Construction | 4/0 | 5/0 | 4/0¦5/0 | TSE | Ready | 0.46817 | 2.809 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-02 | 2026-03-01 | Taimoor Ali | 68/0 | 68/1 | 68/0¦68/1 | Manual | Ready | 0.056 | 0.504 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-03 | 2026-03-01 | Taimoor Ali | 68/0 | 68/1 | 68/0¦68/1 | Manual | Ready | 0.056 | 0.504 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-04 | 2026-03-01 | Taimoor Ali | 68/0 | 68/1 | 68/0¦68/1 | Manual | Ready | 0.056 | 0.504 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-05 | 2026-03-01 | Taimoor Ali | 68/0 | 68/1 | 68/0¦68/1 | Manual | Ready | 0.056 | 0.504 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-05 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-06 | 2026-03-01 | Taimoor Ali | 68/0 | 68/1 | 68/0¦68/1 | Manual | Ready | 0.056 | 0.504 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-06 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-07 | 2026-03-01 | Taimoor Ali | 68/0 | 68/1 | 68/0¦68/1 | Manual | Ready | 0.056 | 0.504 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-07 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-08 | 2026-03-01 | Taimoor Ali | 68/0 | 68/1 | 68/0¦68/1 | Manual | Ready | 0.056 | 0.504 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-08 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-09 | 2026-03-01 | Taimoor Ali | 68/0 | 68/1 | 68/0¦68/1 | Manual | Ready | 0.056 | 0.504 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-09 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-10 | 2026-03-01 | Taimoor Ali | 68/0 | 68/1 | 68/0¦68/1 | Manual | Ready | 0.056 | 0.504 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-10 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-11 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-12 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-13 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-14 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-15 | 2026-03-01 | National Construction | 6/0 | 9/0 | 6/0¦9/0 | TSE | Ready | 0.30267 | 1.2107 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-15 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-16 | 2026-03-01 | National Construction | 6/0 | 9/0 | 6/0¦9/0 | TSE | Ready | 0.30267 | 1.2107 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-16 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-17 | 2026-03-01 | National Construction | 6/0 | 9/0 | 6/0¦9/0 | TSE | Ready | 0.30267 | 1.2107 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-17 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-18 | 2026-03-01 | National Construction | 6/0 | 9/0 | 6/0¦9/0 | TSE | Ready | 0.30267 | 1.2107 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-18 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-18 | 2026-03-01 | Taimoor Ali | 66/0 | 67/0 | 66/0¦67/0 | Manual | Ready | 0.061981 | 0.74377 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-19 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-19 | 2026-03-01 | Taimoor Ali | 66/0 | 67/0 | 66/0¦67/0 | Manual | Ready | 0.061981 | 0.74377 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-20 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-20 | 2026-03-01 | Taimoor Ali | 66/0 | 67/0 | 66/0¦67/0 | Manual | Ready | 0.061981 | 0.74377 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-21 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-21 | 2026-03-01 | Taimoor Ali | 66/0 | 67/0 | 66/0¦67/0 | Manual | Ready | 0.061981 | 0.74377 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-22 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-22 | 2026-03-01 | Taimoor Ali | 66/0 | 67/0 | 66/0¦67/0 | Manual | Ready | 0.061981 | 0.74377 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-23 | 2026-03-01 | National Construction | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.11421 | 1.2563 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-23 | 2026-03-01 | Taimoor Ali | 67/0 | 68/0 | 67/0¦68/0 | Manual | Ready | 0.0093016 | 0.17673 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-23 | 2026-03-01 | Taimoor Ali | 66/0 | 67/0 | 66/0¦67/0 | Manual | Ready | 0.061981 | 0.74377 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-24 | 2026-03-01 | National Construction | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.11421 | 1.2563 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-24 | 2026-03-01 | Taimoor Ali | 66/0 | 67/0 | 66/0¦67/0 | Manual | Ready | 0.061981 | 0.74377 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-25 | 2026-03-01 | National Construction | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.11421 | 1.2563 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-25 | 2026-03-01 | Taimoor Ali | 66/0 | 67/0 | 66/0¦67/0 | Manual | Ready | 0.061981 | 0.74377 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-25 | 2026-03-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-26 | 2026-03-01 | National Construction | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.11421 | 1.2563 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-26 | 2026-03-01 | Taimoor Ali | 66/0 | 67/0 | 66/0¦67/0 | Manual | Ready | 0.061981 | 0.74377 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-26 | 2026-03-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-27 | 2026-03-01 | National Construction | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.11421 | 1.2563 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-27 | 2026-03-01 | Taimoor Ali | 66/0 | 67/0 | 66/0¦67/0 | Manual | Ready | 0.061981 | 0.74377 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-27 | 2026-03-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-28 | 2026-03-01 | National Construction | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.11421 | 1.2563 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-28 | 2026-03-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-28 | 2026-03-01 | Taimoor Ali | 66/0 | 67/0 | 66/0¦67/0 | Manual | Ready | 0.061981 | 0.74377 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-28 | 2026-03-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-29 | 2026-03-01 | National Construction | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.11421 | 1.2563 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-29 | 2026-03-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-29 | 2026-03-01 | Taimoor Ali | 66/0 | 67/0 | 66/0¦67/0 | Manual | Ready | 0.061981 | 0.74377 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-29 | 2026-03-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-30 | 2026-03-01 | National Construction | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.11421 | 1.2563 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-30 | 2026-03-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-30 | 2026-03-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-31 | 2026-03-01 | National Construction | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.11421 | 1.2563 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-31 | 2026-03-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-03-31 | 2026-03-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-01 | 2026-04-01 | Bilkish Rehena | 213/0 | 214/0 | 213/0¦214/0 | TSE | Ready | 0.3359 | 2.3513 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-01 | 2026-04-01 | National Construction | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.11421 | 1.2563 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-01 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-01 | 2026-04-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-02 | 2026-04-01 | Bilkish Rehena | 213/0 | 214/0 | 213/0¦214/0 | TSE | Ready | 0.3359 | 2.3513 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-02 | 2026-04-01 | National Construction | 10/0 | 11/0 | 10/0¦11/0 | TSE | Ready | 0.11421 | 1.2563 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-02 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-02 | 2026-04-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-03 | 2026-04-01 | Bilkish Rehena | 213/0 | 214/0 | 213/0¦214/0 | TSE | Ready | 0.3359 | 2.3513 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-03 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-03 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-03 | 2026-04-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-04 | 2026-04-01 | Bilkish Rehena | 213/0 | 214/0 | 213/0¦214/0 | TSE | Ready | 0.3359 | 2.3513 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-04 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-04 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-04 | 2026-04-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-05 | 2026-04-01 | Bilkish Rehena | 213/0 | 214/0 | 213/0¦214/0 | TSE | Ready | 0.3359 | 2.3513 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-05 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-05 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-05 | 2026-04-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-06 | 2026-04-01 | Bilkish Rehena | 213/0 | 214/0 | 213/0¦214/0 | TSE | Ready | 0.3359 | 2.3513 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-06 | 2026-04-01 | Jahangir Alam | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.30366 | 2.733 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-06 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-06 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-06 | 2026-04-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-07 | 2026-04-01 | Bilkish Rehena | 213/0 | 214/0 | 213/0¦214/0 | TSE | Ready | 0.3359 | 2.3513 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-07 | 2026-04-01 | Jahangir Alam | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.30366 | 2.733 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-07 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-07 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-07 | 2026-04-01 | Taimoor Ali | 65A/3 | 66/0 | 65A/3¦66/0 | Manual | Ready | 0.017447 | 0.24426 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-08 | 2026-04-01 | Jahangir Alam | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.30366 | 2.733 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-08 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-08 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-09 | 2026-04-01 | Jahangir Alam | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.30366 | 2.733 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-09 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-09 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-09 | 2026-04-01 | National Construction | 9/0 | 10/0 | 10/0¦9/0 | Manual | Ready | 0.27218 | 0.27218 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-10 | 2026-04-01 | Jahangir Alam | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.30366 | 2.733 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-10 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-10 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-11 | 2026-04-01 | Jahangir Alam | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.30366 | 2.733 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-11 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-11 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-11 | 2026-04-01 | National Construction | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.36836 | 3.3153 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-12 | 2026-04-01 | Jahangir Alam | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.30366 | 2.733 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-12 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-12 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-12 | 2026-04-01 | National Construction | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.36836 | 3.3153 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-12 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-13 | 2026-04-01 | Bilkish Rehena | 212/0 | 213/0 | 212/0¦213/0 | TSE | Ready | 0.47862 | 2.3931 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-13 | 2026-04-01 | Jahangir Alam | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.30366 | 2.733 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-13 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-13 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-13 | 2026-04-01 | National Construction | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.36836 | 3.3153 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-13 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-14 | 2026-04-01 | Bilkish Rehena | 212/0 | 213/0 | 212/0¦213/0 | TSE | Ready | 0.47862 | 2.3931 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-14 | 2026-04-01 | Jahangir Alam | 17/0 | 18/0 | 17/0¦18/0 | TSE | Ready | 0.30366 | 2.733 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-14 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-14 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-14 | 2026-04-01 | National Construction | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.36836 | 3.3153 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-14 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-15 | 2026-04-01 | Bilkish Rehena | 212/0 | 213/0 | 212/0¦213/0 | TSE | Ready | 0.47862 | 2.3931 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-15 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-15 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-15 | 2026-04-01 | National Construction | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.36836 | 3.3153 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-15 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-15 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-16 | 2026-04-01 | Bilkish Rehena | 212/0 | 213/0 | 212/0¦213/0 | TSE | Ready | 0.47862 | 2.3931 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-16 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-16 | 2026-04-01 | National Construction | 11/0 | 11/3 | 11/0¦11/3 | TSE | Ready | 0.079571 | 1.114 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-16 | 2026-04-01 | National Construction | 11/3 | 12/0 | 11/3¦12/0 | Manual | Ready | 0.026508 | 0.53015 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-16 | 2026-04-01 | National Construction | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.36836 | 3.3153 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-16 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-16 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-17 | 2026-04-01 | Bilkish Rehena | 212/0 | 213/0 | 212/0¦213/0 | TSE | Ready | 0.47862 | 2.3931 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-17 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-17 | 2026-04-01 | National Construction | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.36836 | 3.3153 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-17 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-17 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-18 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-18 | 2026-04-01 | National Construction | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.36836 | 3.3153 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-18 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-18 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-19 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-19 | 2026-04-01 | National Construction | 12/0 | 13/0 | 12/0¦13/0 | TSE | Ready | 0.36836 | 3.3153 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-19 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-19 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-20 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-20 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-20 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-21 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-21 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-21 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-22 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-22 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-22 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-22 | 2026-04-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-23 | 2026-04-01 | Bilkish Rehena | 211/0 | 212/0 | 211/0¦212/0 | TSE | Ready | 0.32545 | 3.2545 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-23 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-23 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-23 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-23 | 2026-04-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-24 | 2026-04-01 | Bilkish Rehena | 211/0 | 212/0 | 211/0¦212/0 | TSE | Ready | 0.32545 | 3.2545 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-24 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-24 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-24 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-24 | 2026-04-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-24 | 2026-04-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-25 | 2026-04-01 | Bilkish Rehena | 211/0 | 212/0 | 211/0¦212/0 | TSE | Ready | 0.32545 | 3.2545 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-25 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-25 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-25 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-25 | 2026-04-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-25 | 2026-04-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-26 | 2026-04-01 | Bilkish Rehena | 211/0 | 212/0 | 211/0¦212/0 | TSE | Ready | 0.32545 | 3.2545 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-26 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-26 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-26 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-26 | 2026-04-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-26 | 2026-04-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-27 | 2026-04-01 | Bilkish Rehena | 211/0 | 212/0 | 211/0¦212/0 | TSE | Ready | 0.32545 | 3.2545 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-27 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-27 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-27 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-27 | 2026-04-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-27 | 2026-04-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-28 | 2026-04-01 | Bilkish Rehena | 211/0 | 212/0 | 211/0¦212/0 | TSE | Ready | 0.32545 | 3.2545 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-28 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-28 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-28 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-28 | 2026-04-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-28 | 2026-04-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-29 | 2026-04-01 | Bilkish Rehena | 211/0 | 212/0 | 211/0¦212/0 | TSE | Ready | 0.32545 | 3.2545 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-29 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-29 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-29 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-29 | 2026-04-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-29 | 2026-04-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-30 | 2026-04-01 | Bilkish Rehena | 211/0 | 212/0 | 211/0¦212/0 | TSE | Ready | 0.32545 | 3.2545 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-30 | 2026-04-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-30 | 2026-04-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-30 | 2026-04-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-30 | 2026-04-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-04-30 | 2026-04-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-01 | 2026-05-01 | Bilkish Rehena | 211/0 | 212/0 | 211/0¦212/0 | TSE | Ready | 0.32545 | 3.2545 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-01 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-01 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-01 | 2026-05-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-01 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-01 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-02 | 2026-05-01 | Bilkish Rehena | 211/0 | 212/0 | 211/0¦212/0 | TSE | Ready | 0.32545 | 3.2545 | 33 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-02 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-02 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-02 | 2026-05-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-02 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-02 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-03 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-03 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-03 | 2026-05-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-03 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-03 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-04 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-04 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-04 | 2026-05-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-04 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-04 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-05 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-05 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-05 | 2026-05-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-05 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-05 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-06 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-06 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-06 | 2026-05-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-06 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-06 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-07 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-07 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-07 | 2026-05-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-07 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-07 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-08 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-08 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-08 | 2026-05-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-08 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-08 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-09 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-09 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-09 | 2026-05-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-09 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-09 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-10 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-10 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-10 | 2026-05-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-10 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-10 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-11 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-11 | 2026-05-01 | National Construction | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.35064 | 2.4545 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-11 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-11 | 2026-05-01 | Taimoor Ali | 65A/0 | 65A/3 | 65A/0¦65A/3 | TSE | Ready | 0.034037 | 0.919 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-11 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-11 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-12 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-12 | 2026-05-01 | National Construction | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.35064 | 2.4545 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-12 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-12 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-12 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-13 | 2026-05-01 | Jahangir Alam | 15/0 | 16/0 | 15/0¦16/0 | TSE | Ready | 0.059819 | 1.6749 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-13 | 2026-05-01 | National Construction | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.35064 | 2.4545 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-13 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-13 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-13 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-13 | 2026-05-01 | Taimoor Ali | 64A/0 | 65/0 | 64A/0¦65/0 | TSE | Ready | 0.23702 | 1.6591 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-14 | 2026-05-01 | National Construction | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.35064 | 2.4545 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-14 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-14 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-14 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-14 | 2026-05-01 | Taimoor Ali | 64A/0 | 65/0 | 64A/0¦65/0 | TSE | Ready | 0.23702 | 1.6591 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-15 | 2026-05-01 | National Construction | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.35064 | 2.4545 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-15 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-15 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-15 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-15 | 2026-05-01 | Taimoor Ali | 64A/0 | 65/0 | 64A/0¦65/0 | TSE | Ready | 0.23702 | 1.6591 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-16 | 2026-05-01 | National Construction | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.35064 | 2.4545 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-16 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-16 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-16 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-16 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-16 | 2026-05-01 | Taimoor Ali | 64A/0 | 65/0 | 64A/0¦65/0 | TSE | Ready | 0.23702 | 1.6591 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-17 | 2026-05-01 | National Construction | 13/0 | 14/0 | 13/0¦14/0 | TSE | Ready | 0.35064 | 2.4545 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-17 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-17 | 2026-05-01 | Taimoor Ali | 65/0 | 65A/0 | 65/0¦65A/0 | Manual | Ready | 0.0054186 | 0.19507 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-17 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-17 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-17 | 2026-05-01 | Taimoor Ali | 64A/0 | 65/0 | 64A/0¦65/0 | TSE | Ready | 0.23702 | 1.6591 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-18 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-18 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-18 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-18 | 2026-05-01 | Taimoor Ali | 64A/0 | 65/0 | 64A/0¦65/0 | TSE | Ready | 0.23702 | 1.6591 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-19 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-19 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-19 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-19 | 2026-05-01 | Taimoor Ali | 64A/0 | 65/0 | 64A/0¦65/0 | TSE | Ready | 0.23702 | 1.6591 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-20 | 2026-05-01 | Rejaul Sekh | 139/0 | 139A/0 | 139/0¦139A/0 | Manual | Ready | 0.065583 | 0.65583 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-20 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-20 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-20 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-21 | 2026-05-01 | Rejaul Sekh | 139/0 | 139A/0 | 139/0¦139A/0 | Manual | Ready | 0.065583 | 0.65583 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-21 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-21 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-21 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-22 | 2026-05-01 | Rejaul Sekh | 139/0 | 139A/0 | 139/0¦139A/0 | Manual | Ready | 0.065583 | 0.65583 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-22 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-22 | 2026-05-01 | Taimoor Ali | 64/0 | 64A/0 | 64/0¦64A/0 | TSE | Ready | 0.015225 | 0.47196 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-22 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-23 | 2026-05-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-23 | 2026-05-01 | Rejaul Sekh | 139/0 | 139A/0 | 139/0¦139A/0 | Manual | Ready | 0.065583 | 0.65583 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-23 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-23 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-24 | 2026-05-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-24 | 2026-05-01 | Rejaul Sekh | 139/0 | 139A/0 | 139/0¦139A/0 | Manual | Ready | 0.065583 | 0.65583 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-24 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-24 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-25 | 2026-05-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-25 | 2026-05-01 | Rejaul Sekh | 139/0 | 139A/0 | 139/0¦139A/0 | Manual | Ready | 0.065583 | 0.65583 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-25 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-25 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-26 | 2026-05-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-26 | 2026-05-01 | Rejaul Sekh | 139/0 | 139A/0 | 139/0¦139A/0 | Manual | Ready | 0.065583 | 0.65583 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-26 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-26 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-27 | 2026-05-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-27 | 2026-05-01 | Rejaul Sekh | 139/0 | 139A/0 | 139/0¦139A/0 | Manual | Ready | 0.065583 | 0.65583 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-27 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-27 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-28 | 2026-05-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-28 | 2026-05-01 | Rejaul Sekh | 139/0 | 139A/0 | 139/0¦139A/0 | Manual | Ready | 0.065583 | 0.65583 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-28 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-28 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-29 | 2026-05-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-29 | 2026-05-01 | Jahangir Alam | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.22667 | 2.04 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-29 | 2026-05-01 | Rejaul Sekh | 139/0 | 139A/0 | 139/0¦139A/0 | Manual | Ready | 0.065583 | 0.65583 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-29 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-29 | 2026-05-01 | Taimoor Ali | 63/0 | 64/0 | 63/0¦64/0 | TSE | Ready | 0.021638 | 0.77897 | 22 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-30 | 2026-05-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-30 | 2026-05-01 | Jahangir Alam | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.22667 | 2.04 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-30 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-31 | 2026-05-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-31 | 2026-05-01 | Jahangir Alam | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.22667 | 2.04 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-05-31 | 2026-05-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-01 | 2026-06-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-01 | 2026-06-01 | Jahangir Alam | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.22667 | 2.04 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-01 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-02 | 2026-06-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-02 | 2026-06-01 | Jahangir Alam | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.22667 | 2.04 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-02 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-03 | 2026-06-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-03 | 2026-06-01 | Jahangir Alam | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.22667 | 2.04 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-03 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-04 | 2026-06-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-04 | 2026-06-01 | Jahangir Alam | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.22667 | 2.04 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-04 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-05 | 2026-06-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-05 | 2026-06-01 | Jahangir Alam | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.22667 | 2.04 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-05 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-06 | 2026-06-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-06 | 2026-06-01 | Jahangir Alam | 37/0 | 38/0 | 37/0¦38/0 | TSE | Ready | 0.22667 | 2.04 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-06 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-07 | 2026-06-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-07 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-08 | 2026-06-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-08 | 2026-06-01 | National Construction | 14/0 | 15/0 | 14/0¦15/0 | Manual | Ready | 0.28 | 0.28 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-08 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-09 | 2026-06-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-09 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-10 | 2026-06-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-10 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-11 | 2026-06-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-11 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-12 | 2026-06-01 | Jahangir Alam | 38/0 | 39/0 | 38/0¦39/0 | Manual | Ready | 0.03631 | 0.76252 | 39 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-12 | 2026-06-01 | National Construction | 16/0 | 17/0 | 16/0¦17/0 | Manual | Ready | 0.20497 | 0.20497 | 40 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-12 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TA 506 | TA 506 | ta506 |  | 2026-06-13 | 2026-06-01 | Rejaul Sekh | 139A/0 | 140/0 | 139A/0¦140/0 | Manual | Ready | 0.0083676 | 0.24266 | 30 |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | yes | TRUE | AVAILABLE | Manpower values mapped from stringing compiled sheet.
TB 408 | TB 408 | tb408 |  | 2024-08-21 | 2024-08-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-08-22 | 2024-08-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-08-23 | 2024-08-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-08-24 | 2024-08-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-08-25 | 2024-08-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-08-26 | 2024-08-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-08-27 | 2024-08-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-08-28 | 2024-08-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-08-29 | 2024-08-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-08-30 | 2024-08-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-08-31 | 2024-08-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-01 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-02 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-03 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-04 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-05 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-06 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-06 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-07 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-07 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-08 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-08 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-09 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-09 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-10 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-10 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-11 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-11 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-12 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-12 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-13 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-13 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-14 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-14 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-15 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-15 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-16 | 2024-09-01 | Kuddus ali | 60/0 | 61/0 | 60/0¦61/0 | TSE |  | 0.18063 | 4.877 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-16 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-17 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-18 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-19 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-20 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-21 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-22 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-23 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-23 | 2024-09-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-24 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-24 | 2024-09-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-25 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-25 | 2024-09-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-26 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-26 | 2024-09-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-27 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-27 | 2024-09-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-28 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-28 | 2024-09-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-29 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-29 | 2024-09-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-30 | 2024-09-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-09-30 | 2024-09-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-01 | 2024-10-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-01 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-02 | 2024-10-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-02 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-03 | 2024-10-01 | Kuddus ali | 61/0 | 62/0 | 61/0¦62/0 | TSE |  | 0.16314 | 4.568 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-03 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-04 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-05 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-06 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-07 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-08 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-09 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-10 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-11 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-12 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-13 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-14 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-14 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-15 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-15 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-16 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-16 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-17 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-17 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-18 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-18 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-19 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-19 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-20 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-20 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-21 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-21 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-22 | 2024-10-01 | Kuddus ali | 62/0 | 63/0 | 62/0¦63/0 | TSE |  | 0.1621 | 4.863 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-22 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-23 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-24 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-25 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-26 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-27 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-28 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-29 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-30 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-30 | 2024-10-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-31 | 2024-10-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-10-31 | 2024-10-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-01 | 2024-11-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-01 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-02 | 2024-11-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-02 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-03 | 2024-11-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-03 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-04 | 2024-11-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-04 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-05 | 2024-11-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-05 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-06 | 2024-11-01 | Kuddus ali | 63/0 | 64/0 | 63/0¦64/0 | TSE |  | 0.15463 | 3.711 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-06 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-07 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-08 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-09 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-10 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-11 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-12 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-13 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-14 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-15 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-11-16 | 2024-11-01 | Kuddus ali | 64/0 | 65/0 | 64/0¦65/0 | TSE |  | 0.27322 | 4.918 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-12-22 | 2024-12-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-12-23 | 2024-12-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-12-24 | 2024-12-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-12-25 | 2024-12-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-12-26 | 2024-12-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-12-27 | 2024-12-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-12-28 | 2024-12-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-12-29 | 2024-12-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-12-30 | 2024-12-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2024-12-31 | 2024-12-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-01 | 2025-01-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-02 | 2025-01-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-02 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-03 | 2025-01-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-03 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-04 | 2025-01-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-04 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-05 | 2025-01-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-05 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-06 | 2025-01-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-06 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-07 | 2025-01-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-07 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-08 | 2025-01-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-08 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-09 | 2025-01-01 | Gopal Associate | 59/8 | 60/0 | 59/8¦60/0 | TSE |  | 0.19884 | 3.778 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-09 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-10 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-11 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-12 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-13 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-14 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-01-15 | 2025-01-01 | Gopal Associate | 59/0 | 59/8 | 59/0¦59/8 | TSE |  | 0.23836 | 3.337 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-03 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-04 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-05 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-06 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-06 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-07 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-07 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-08 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-08 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-09 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-09 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-10 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-10 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-11 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-11 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-12 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-12 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-13 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-13 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-14 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-14 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-15 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-15 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-16 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-16 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-17 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-17 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-18 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-18 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-19 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-19 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-20 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-20 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-21 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-21 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-22 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-22 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-23 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-23 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-24 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-24 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-25 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-25 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-26 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-26 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-27 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-27 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-28 | 2025-02-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-02-28 | 2025-02-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-01 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-01 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-02 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-02 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-03 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-03 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-04 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-04 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-05 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-05 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-06 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-06 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-07 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-07 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-08 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-08 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-09 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-09 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-10 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-10 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-11 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-11 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-12 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-12 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-12 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-13 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-13 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-13 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-14 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-14 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-14 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-15 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-15 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-15 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-16 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-16 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-16 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-17 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-17 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-17 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-18 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-18 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-18 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-19 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-19 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-19 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-19 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-20 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-20 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-20 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-20 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-21 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-21 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-21 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-21 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-22 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-22 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-22 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-22 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-23 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-23 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-23 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-23 | 2025-03-01 | MR Power | 65/0 | 66/0 | 65/0¦66/0 | TSE |  | 0.096653 | 4.736 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-24 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-24 | 2025-03-01 | Gopal Associate | 50/0 | 51/0 | 50/0¦51/0 | TSE |  | 0.34185 | 4.444 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-24 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-25 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-25 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-26 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-26 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-27 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-27 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-28 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-28 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-29 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-29 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-30 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-30 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-31 | 2025-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-03-31 | 2025-03-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-01 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-01 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-02 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-02 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-02 | 2025-04-01 | Gopal Associate | 51/0 | 52/0 | 51/0¦52/0 | TSE |  | 0.13112 | 1.049 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-03 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-03 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-03 | 2025-04-01 | Gopal Associate | 51/0 | 52/0 | 51/0¦52/0 | TSE |  | 0.13112 | 1.049 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-04 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-04 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-04 | 2025-04-01 | Gopal Associate | 51/0 | 52/0 | 51/0¦52/0 | TSE |  | 0.13112 | 1.049 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-05 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-05 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-05 | 2025-04-01 | Gopal Associate | 51/0 | 52/0 | 51/0¦52/0 | TSE |  | 0.13112 | 1.049 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-06 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-06 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-06 | 2025-04-01 | Gopal Associate | 51/0 | 52/0 | 51/0¦52/0 | TSE |  | 0.13112 | 1.049 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-07 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-07 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-07 | 2025-04-01 | Gopal Associate | 51/0 | 52/0 | 51/0¦52/0 | TSE |  | 0.13112 | 1.049 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-08 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-08 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-08 | 2025-04-01 | Gopal Associate | 51/0 | 52/0 | 51/0¦52/0 | TSE |  | 0.13112 | 1.049 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-09 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-09 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-09 | 2025-04-01 | Gopal Associate | 51/0 | 52/0 | 51/0¦52/0 | TSE |  | 0.13112 | 1.049 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-10 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-10 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-11 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-11 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-12 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-12 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-13 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-13 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-14 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-14 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-15 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-15 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-16 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-16 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-17 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-17 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-18 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-18 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-18 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-19 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-19 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-19 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-20 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-20 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-20 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-21 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-21 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-21 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-22 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-22 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-22 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-23 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-23 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-23 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-24 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-24 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-24 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-25 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-25 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-25 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-26 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-26 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-26 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-27 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-27 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-27 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-28 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-28 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-28 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-29 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-29 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-29 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-30 | 2025-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-30 | 2025-04-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-04-30 | 2025-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-01 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-01 | 2025-05-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-01 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-02 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-02 | 2025-05-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-02 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-03 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-03 | 2025-05-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-03 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-04 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-04 | 2025-05-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-04 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-05 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-05 | 2025-05-01 | Gopal Associate | 49/0 | 50/0 | 49/0¦50/0 | TSE |  | 0.036258 | 3.227 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-05 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-06 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-06 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-07 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-07 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-08 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-08 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-09 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-09 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-10 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-10 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-11 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-11 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-12 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-12 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-13 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-13 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-14 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-14 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-15 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-15 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-16 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-16 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-17 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-17 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-18 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-18 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-19 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-19 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-20 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-20 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-21 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-21 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-22 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-22 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-23 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-23 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-24 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-24 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-25 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-25 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-26 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-26 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-27 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-27 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-28 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-28 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-29 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-29 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-30 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-30 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-31 | 2025-05-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-05-31 | 2025-05-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-01 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-01 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-01 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-02 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-02 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-02 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-03 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-03 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-03 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-04 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-04 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-04 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-05 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-05 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-05 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-06 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-06 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-06 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-07 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-07 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-07 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-08 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-08 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-08 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-09 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-09 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-09 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-10 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-10 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-10 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-11 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-11 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-11 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-12 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-12 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-12 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-13 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-13 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-13 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-14 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-14 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-14 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-15 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-15 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-15 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-16 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-16 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-16 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-17 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-17 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-17 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-18 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-18 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-18 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-19 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-19 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-19 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-20 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-20 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-20 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-21 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-21 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-21 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-22 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-22 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-22 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-23 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-23 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-23 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-24 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-24 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-24 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-25 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-25 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-25 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-26 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-26 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-26 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-27 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-27 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-27 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-28 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-28 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-28 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-29 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-29 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-29 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-30 | 2025-06-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-30 | 2025-06-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-06-30 | 2025-06-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-01 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-01 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-01 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-02 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-02 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-02 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-03 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-03 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-03 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-04 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-04 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-04 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-05 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-05 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-05 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-06 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-06 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-06 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-07 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-07 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-07 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-08 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-08 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-08 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-09 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-09 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-09 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-10 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-10 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-10 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-11 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-11 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-11 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-12 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-12 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-12 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-13 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-13 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-13 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-14 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-14 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-14 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-15 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-15 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-15 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-16 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-16 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-16 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-17 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-17 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-17 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-18 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-18 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-18 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-19 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-19 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-19 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-20 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-20 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-20 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-21 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-21 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-21 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-22 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-22 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-22 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-23 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-23 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-23 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-24 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-24 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-24 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-25 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-25 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-25 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-26 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-26 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-26 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-27 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-27 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-27 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-28 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-28 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-28 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-29 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-29 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-29 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-30 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-30 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-30 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-31 | 2025-07-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-31 | 2025-07-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-07-31 | 2025-07-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-01 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-01 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-01 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-02 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-02 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-02 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-03 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-03 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-03 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-04 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-04 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-04 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-05 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-05 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-05 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-06 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-06 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-06 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-07 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-07 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-07 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-08 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-08 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-08 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-09 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-09 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-09 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-10 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-10 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-10 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-11 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-11 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-11 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-12 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-12 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-12 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-13 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-13 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-13 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-14 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-14 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-14 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-15 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-15 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-15 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-16 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-16 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-16 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-17 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-17 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-17 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-18 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-18 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-18 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-19 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-19 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-19 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-20 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-20 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-20 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-21 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-21 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-21 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-22 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-22 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-22 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-23 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-23 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-23 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-24 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-24 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-24 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-25 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-25 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-25 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-26 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-26 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-26 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-27 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-27 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-27 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-28 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-28 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-28 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-29 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-29 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-29 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-30 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-30 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-30 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-31 | 2025-08-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-31 | 2025-08-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-08-31 | 2025-08-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-01 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-01 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-01 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-02 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-02 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-02 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-03 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-03 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-03 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-04 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-04 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-04 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-05 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-05 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-05 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-06 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-06 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-06 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-07 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-07 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-07 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-08 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-08 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-08 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-09 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-09 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-09 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-10 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-10 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-10 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-11 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-11 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-11 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-12 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-12 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-12 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-13 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-13 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-13 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-14 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-14 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-14 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-15 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-15 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-15 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-16 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-16 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-16 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-17 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-17 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-17 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-18 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-18 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-18 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-19 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-19 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-19 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-20 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-20 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-20 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-21 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-21 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-21 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-22 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-22 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-22 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-23 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-23 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-23 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-24 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-24 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-24 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-25 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-25 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-25 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-26 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-26 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-26 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-27 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-27 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-27 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-28 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-28 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-28 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-29 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-29 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-29 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-30 | 2025-09-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-30 | 2025-09-01 | JPJ Construction/MC Power | 73/0 | 74/0 | 73/0¦74/0 | TSE |  | 0.031049 | 3.788 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-09-30 | 2025-09-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-01 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-01 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-02 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-02 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-03 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-03 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-04 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-04 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-05 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-05 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-06 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-06 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-07 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-07 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-08 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-08 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-09 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-09 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-10 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-10 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-11 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-11 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-12 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-12 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-13 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-13 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-14 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-14 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-15 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-15 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-16 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-16 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-17 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-17 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-18 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-18 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-19 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-19 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-20 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-20 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-21 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-21 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-22 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-22 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-23 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-23 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-24 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-24 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-25 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-25 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-26 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-26 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-27 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-27 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-28 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-28 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-29 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-29 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-30 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-30 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-31 | 2025-10-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-10-31 | 2025-10-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-01 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-01 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-02 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-02 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-03 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-03 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-03 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-04 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-04 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-04 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-05 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-05 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-05 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-06 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-06 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-06 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-07 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-07 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-07 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-08 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-08 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-08 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-09 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-09 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-09 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-10 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-10 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-10 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-11 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-11 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-11 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-12 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-12 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-12 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-13 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-13 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-13 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-13 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-14 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-14 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-14 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-14 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-15 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-15 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-15 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-15 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-16 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-16 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-16 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-16 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-17 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-17 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-17 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-17 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-18 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-18 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-18 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-18 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-19 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-19 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-19 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-19 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-20 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-20 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-20 | 2025-11-01 | Gopal Associate, Hotline | 56/0 | 57/0 | 56/0¦57/0 | M |  | 0.031429 | 0.22 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-20 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-20 | 2025-11-01 | MC Power | 71/0 | 72/0 | 71/0¦72/0 | TSE |  | 0.33409 | 3.675 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-20 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-21 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-21 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-21 | 2025-11-01 | Devi Power | 1A/0 | 2/0 | 1A/0¦2/0 | TSE |  | 0.3426 | 3.426 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-21 | 2025-11-01 | Gopal Associate, Hotline | 56/0 | 57/0 | 56/0¦57/0 | M |  | 0.031429 | 0.22 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-21 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-21 | 2025-11-01 | MC Power | 71/0 | 72/0 | 71/0¦72/0 | TSE |  | 0.33409 | 3.675 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-21 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-22 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-22 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-22 | 2025-11-01 | Devi Power | 1A/0 | 2/0 | 1A/0¦2/0 | TSE |  | 0.3426 | 3.426 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-22 | 2025-11-01 | Gopal Associate, Hotline | 56/0 | 57/0 | 56/0¦57/0 | M |  | 0.031429 | 0.22 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-22 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-22 | 2025-11-01 | MC Power | 71/0 | 72/0 | 71/0¦72/0 | TSE |  | 0.33409 | 3.675 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-22 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-23 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-23 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-23 | 2025-11-01 | Devi Power | 1A/0 | 2/0 | 1A/0¦2/0 | TSE |  | 0.3426 | 3.426 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-23 | 2025-11-01 | Gopal Associate, Hotline | 56/0 | 57/0 | 56/0¦57/0 | M |  | 0.031429 | 0.22 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-23 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-23 | 2025-11-01 | MC Power | 71/0 | 72/0 | 71/0¦72/0 | TSE |  | 0.33409 | 3.675 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-23 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-24 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-24 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-24 | 2025-11-01 | Devi Power | 1A/0 | 2/0 | 1A/0¦2/0 | TSE |  | 0.3426 | 3.426 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-24 | 2025-11-01 | Gopal Associate, Hotline | 56/0 | 57/0 | 56/0¦57/0 | M |  | 0.031429 | 0.22 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-24 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-24 | 2025-11-01 | MC Power | 71/0 | 72/0 | 71/0¦72/0 | TSE |  | 0.33409 | 3.675 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-24 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-25 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-25 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-25 | 2025-11-01 | Devi Power | 1A/0 | 2/0 | 1A/0¦2/0 | TSE |  | 0.3426 | 3.426 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-25 | 2025-11-01 | Gopal Associate, Hotline | 56/0 | 57/0 | 56/0¦57/0 | M |  | 0.031429 | 0.22 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-25 | 2025-11-01 | JPJ Construction/MC Power | 72/0 | 73/0 | 72/0¦73/0 | TSE |  | 0.070783 | 1.628 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-25 | 2025-11-01 | MC Power | 71/0 | 72/0 | 71/0¦72/0 | TSE |  | 0.33409 | 3.675 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-25 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-26 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-26 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-26 | 2025-11-01 | Devi Power | 1A/0 | 2/0 | 1A/0¦2/0 | TSE |  | 0.3426 | 3.426 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-26 | 2025-11-01 | Gopal Associate, Hotline | 56/0 | 57/0 | 56/0¦57/0 | M |  | 0.031429 | 0.22 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-26 | 2025-11-01 | MC Power | 71/0 | 72/0 | 71/0¦72/0 | TSE |  | 0.33409 | 3.675 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-26 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-27 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-27 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-27 | 2025-11-01 | Devi Power | 1A/0 | 2/0 | 1A/0¦2/0 | TSE |  | 0.3426 | 3.426 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-27 | 2025-11-01 | MC Power | 71/0 | 72/0 | 71/0¦72/0 | TSE |  | 0.33409 | 3.675 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-27 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-28 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-28 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-28 | 2025-11-01 | Devi Power | 1A/0 | 2/0 | 1A/0¦2/0 | TSE |  | 0.3426 | 3.426 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-28 | 2025-11-01 | MC Power | 71/0 | 72/0 | 71/0¦72/0 | TSE |  | 0.33409 | 3.675 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-28 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-29 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-29 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-29 | 2025-11-01 | Devi Power | 1A/0 | 2/0 | 1A/0¦2/0 | TSE |  | 0.3426 | 3.426 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-29 | 2025-11-01 | MC Power | 71/0 | 72/0 | 71/0¦72/0 | TSE |  | 0.33409 | 3.675 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-29 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-30 | 2025-11-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-30 | 2025-11-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-30 | 2025-11-01 | Devi Power | 1A/0 | 2/0 | 1A/0¦2/0 | TSE |  | 0.3426 | 3.426 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-30 | 2025-11-01 | MC Power | 71/0 | 72/0 | 71/0¦72/0 | TSE |  | 0.33409 | 3.675 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-11-30 | 2025-11-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-01 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-01 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-01 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-02 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-02 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-02 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-03 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-03 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-03 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-04 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-04 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-04 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-05 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-05 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-05 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-06 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-06 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-06 | 2025-12-01 | Gopal Associate, Hotline | 46/0 | 47/0 | 46/0¦47/0 | M |  | 0.03318 | 0.19908 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-06 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-07 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-07 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-07 | 2025-12-01 | Gopal Associate, Hotline | 46/0 | 47/0 | 46/0¦47/0 | M |  | 0.03318 | 0.19908 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-07 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-08 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-08 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-08 | 2025-12-01 | Gopal Associate, Hotline | 46/0 | 47/0 | 46/0¦47/0 | M |  | 0.03318 | 0.19908 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-08 | 2025-12-01 | MC Power | 70/0 | 71/0 | 70/0¦71/0 | TSE |  | 0.4966 | 4.966 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-08 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-09 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-09 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-09 | 2025-12-01 | Gopal Associate, Hotline | 46/0 | 47/0 | 46/0¦47/0 | M |  | 0.03318 | 0.19908 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-09 | 2025-12-01 | MC Power | 70/0 | 71/0 | 70/0¦71/0 | TSE |  | 0.4966 | 4.966 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-09 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-10 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-10 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-10 | 2025-12-01 | Gopal Associate, Hotline | 46/0 | 47/0 | 46/0¦47/0 | M |  | 0.03318 | 0.19908 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-10 | 2025-12-01 | MC Power | 70/0 | 71/0 | 70/0¦71/0 | TSE |  | 0.4966 | 4.966 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-10 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-11 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-11 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-11 | 2025-12-01 | Gopal Associate, Hotline | 46/0 | 47/0 | 46/0¦47/0 | M |  | 0.03318 | 0.19908 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-11 | 2025-12-01 | MC Power | 70/0 | 71/0 | 70/0¦71/0 | TSE |  | 0.4966 | 4.966 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-11 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-12 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-12 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-12 | 2025-12-01 | MC Power | 70/0 | 71/0 | 70/0¦71/0 | TSE |  | 0.4966 | 4.966 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-12 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-13 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-13 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-13 | 2025-12-01 | MC Power | 70/0 | 71/0 | 70/0¦71/0 | TSE |  | 0.4966 | 4.966 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-13 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-14 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-14 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-14 | 2025-12-01 | MC Power | 70/0 | 71/0 | 70/0¦71/0 | TSE |  | 0.4966 | 4.966 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-14 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-15 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-15 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-15 | 2025-12-01 | MC Power | 70/0 | 71/0 | 70/0¦71/0 | TSE |  | 0.4966 | 4.966 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-15 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-16 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-16 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-16 | 2025-12-01 | MC Power | 70/0 | 71/0 | 70/0¦71/0 | TSE |  | 0.4966 | 4.966 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-16 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-17 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-17 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-17 | 2025-12-01 | MC Power | 70/0 | 71/0 | 70/0¦71/0 | TSE |  | 0.4966 | 4.966 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-17 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-18 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-18 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-18 | 2025-12-01 | MC Power | 69/0 | 70/0 | 69/0¦70/0 | TSE |  | 0.096125 | 0.769 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-18 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-19 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-19 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-19 | 2025-12-01 | MC Power | 69/0 | 70/0 | 69/0¦70/0 | TSE |  | 0.096125 | 0.769 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-19 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-20 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-20 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-20 | 2025-12-01 | MC Power | 69/0 | 70/0 | 69/0¦70/0 | TSE |  | 0.096125 | 0.769 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-20 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-21 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-21 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-21 | 2025-12-01 | MC Power | 69/0 | 70/0 | 69/0¦70/0 | TSE |  | 0.096125 | 0.769 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-21 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-22 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-22 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-22 | 2025-12-01 | MC Power | 69/0 | 70/0 | 69/0¦70/0 | TSE |  | 0.096125 | 0.769 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-22 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-23 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-23 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-23 | 2025-12-01 | MC Power | 69/0 | 70/0 | 69/0¦70/0 | TSE |  | 0.096125 | 0.769 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-23 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-24 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-24 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-24 | 2025-12-01 | MC Power | 69/0 | 70/0 | 69/0¦70/0 | TSE |  | 0.096125 | 0.769 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-24 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-25 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-25 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-25 | 2025-12-01 | MC Power | 69/0 | 70/0 | 69/0¦70/0 | TSE |  | 0.096125 | 0.769 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-25 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-26 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-26 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-26 | 2025-12-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-26 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-27 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-27 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-27 | 2025-12-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-27 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-28 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-28 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-28 | 2025-12-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-28 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-29 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-29 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-29 | 2025-12-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-29 | 2025-12-01 | MC Power | 68/0 | 69/0 | 68/0¦69/0 | M |  | 0.2 | 0.2 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-29 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-30 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-30 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-30 | 2025-12-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-30 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-31 | 2025-12-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-31 | 2025-12-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-31 | 2025-12-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2025-12-31 | 2025-12-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-01 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-01 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-01 | 2026-01-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-01 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-02 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-02 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-02 | 2026-01-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-02 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-03 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-03 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-03 | 2026-01-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-03 | 2026-01-01 | MC Power | 66/0 | 67/0 | 66/0¦67/0 | M |  | 0.2078 | 0.2078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-03 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-04 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-04 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-04 | 2026-01-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-04 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-05 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-05 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-05 | 2026-01-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-05 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-06 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-06 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-06 | 2026-01-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-06 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-07 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-07 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-07 | 2026-01-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-07 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-08 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-08 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-08 | 2026-01-01 | MC Power | 67/0 | 68/0 | 67/0¦68/0 | TSE |  | 0.075786 | 1.061 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-08 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-09 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-09 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-09 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-10 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-10 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-10 | 2026-01-01 | Gopal Associate, Hotline | 3/0 | 4/0 | 3/0¦4/0 | M |  | 0.032357 | 0.2265 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-10 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-11 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-11 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-11 | 2026-01-01 | Gopal Associate, Hotline | 3/0 | 4/0 | 3/0¦4/0 | M |  | 0.032357 | 0.2265 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-11 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-12 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-12 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-12 | 2026-01-01 | Gopal Associate, Hotline | 3/0 | 4/0 | 3/0¦4/0 | M |  | 0.032357 | 0.2265 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-12 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-13 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-13 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-13 | 2026-01-01 | Gopal Associate, Hotline | 3/0 | 4/0 | 3/0¦4/0 | M |  | 0.032357 | 0.2265 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-13 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-14 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-14 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-14 | 2026-01-01 | Devi Power | 2/0 | 3/0 | 2/0¦3/0 | TSE |  | 0.060683 | 3.823 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-14 | 2026-01-01 | Gopal Associate, Hotline | 3/0 | 4/0 | 3/0¦4/0 | M |  | 0.032357 | 0.2265 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-14 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-15 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-15 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-15 | 2026-01-01 | Gopal Associate, Hotline | 3/0 | 4/0 | 3/0¦4/0 | M |  | 0.032357 | 0.2265 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-15 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-16 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-16 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-16 | 2026-01-01 | Gopal Associate, Hotline | 3/0 | 4/0 | 3/0¦4/0 | M |  | 0.032357 | 0.2265 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-16 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-17 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-17 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-17 | 2026-01-01 | Krishna-1 | 48/0 | 49/0 | 48/0¦49/0 | TSE |  | 0.11857 | 0.83 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-17 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-18 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-18 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-18 | 2026-01-01 | Krishna-1 | 48/0 | 49/0 | 48/0¦49/0 | TSE |  | 0.11857 | 0.83 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-18 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-19 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-19 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-19 | 2026-01-01 | Krishna-1 | 48/0 | 49/0 | 48/0¦49/0 | TSE |  | 0.11857 | 0.83 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-19 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-19 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-20 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-20 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-20 | 2026-01-01 | Krishna-1 | 48/0 | 49/0 | 48/0¦49/0 | TSE |  | 0.11857 | 0.83 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-20 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-20 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-21 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-21 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-21 | 2026-01-01 | Krishna-1 | 48/0 | 49/0 | 48/0¦49/0 | TSE |  | 0.11857 | 0.83 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-21 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-21 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-22 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-22 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-22 | 2026-01-01 | Krishna-1 | 48/0 | 49/0 | 48/0¦49/0 | TSE |  | 0.11857 | 0.83 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-22 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-22 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-23 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-23 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-23 | 2026-01-01 | Krishna-1 | 48/0 | 49/0 | 48/0¦49/0 | TSE |  | 0.11857 | 0.83 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-23 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-23 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-24 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-24 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-24 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-24 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-25 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-25 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-25 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-25 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-26 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-26 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-26 | 2026-01-01 | Krishna-1 | 47/0 | 48/0 | 47/0¦48/0 | TSE |  | 0.74617 | 4.477 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-26 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-26 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-27 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-27 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-27 | 2026-01-01 | Krishna-1 | 47/0 | 48/0 | 47/0¦48/0 | TSE |  | 0.74617 | 4.477 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-27 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-27 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-28 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-28 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-28 | 2026-01-01 | Krishna-1 | 47/0 | 48/0 | 47/0¦48/0 | TSE |  | 0.74617 | 4.477 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-28 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-28 | 2026-01-01 | MC Power | 58/0 | 59/0 | 58/0¦59/0 | M |  | 0.2389 | 0.2389 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-28 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-29 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-29 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-29 | 2026-01-01 | Krishna-1 | 47/0 | 48/0 | 47/0¦48/0 | TSE |  | 0.74617 | 4.477 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-29 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-29 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-30 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-30 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-30 | 2026-01-01 | Krishna-1 | 47/0 | 48/0 | 47/0¦48/0 | TSE |  | 0.74617 | 4.477 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-30 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-30 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-31 | 2026-01-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-31 | 2026-01-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-31 | 2026-01-01 | Krishna-1 | 47/0 | 48/0 | 47/0¦48/0 | TSE |  | 0.74617 | 4.477 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-31 | 2026-01-01 | MC Power | 57/0 | 58/0 | 57/0¦58/0 | TSE |  | 0.25285 | 3.287 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-01-31 | 2026-01-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-01 | 2026-02-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-01 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-01 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-02 | 2026-02-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-02 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-02 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-03 | 2026-02-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-03 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-03 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-04 | 2026-02-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-04 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-04 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-05 | 2026-02-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-05 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-05 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-06 | 2026-02-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-06 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-06 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-07 | 2026-02-01 | Deepak Sarkar | 10/12 | 11/0 | 10/12¦11/0 | TSE |  | 0.198 | 4.95 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-07 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-07 | 2026-02-01 | Krishna-1 | 45/0 | 46/0 | 45/0¦46/0 | TSE |  | 0.10021 | 0.70146 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-07 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-08 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-08 | 2026-02-01 | Krishna-1 | 45/0 | 46/0 | 45/0¦46/0 | TSE |  | 0.10021 | 0.70146 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-08 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-09 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-09 | 2026-02-01 | Krishna-1 | 45/0 | 46/0 | 45/0¦46/0 | TSE |  | 0.10021 | 0.70146 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-09 | 2026-02-01 | Krishna-1 | 44/10 | 45/0 | 44/10¦45/0 | TSE |  | 0.062917 | 0.755 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-09 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-10 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-10 | 2026-02-01 | Krishna-1 | 45/0 | 46/0 | 45/0¦46/0 | TSE |  | 0.10021 | 0.70146 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-10 | 2026-02-01 | Krishna-1 | 44/10 | 45/0 | 44/10¦45/0 | TSE |  | 0.062917 | 0.755 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-10 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-11 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-11 | 2026-02-01 | Krishna-1 | 45/0 | 46/0 | 45/0¦46/0 | TSE |  | 0.10021 | 0.70146 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-11 | 2026-02-01 | Krishna-1 | 44/10 | 45/0 | 44/10¦45/0 | TSE |  | 0.062917 | 0.755 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-11 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-12 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-12 | 2026-02-01 | Krishna-1 | 45/0 | 46/0 | 45/0¦46/0 | TSE |  | 0.10021 | 0.70146 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-12 | 2026-02-01 | Krishna-1 | 44/10 | 45/0 | 44/10¦45/0 | TSE |  | 0.062917 | 0.755 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-12 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-12 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-13 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-13 | 2026-02-01 | Krishna-1 | 45/0 | 46/0 | 45/0¦46/0 | TSE |  | 0.10021 | 0.70146 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-13 | 2026-02-01 | Krishna-1 | 44/10 | 45/0 | 44/10¦45/0 | TSE |  | 0.062917 | 0.755 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-13 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-13 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-14 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-14 | 2026-02-01 | Krishna-1 | 44/10 | 45/0 | 44/10¦45/0 | TSE |  | 0.062917 | 0.755 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-14 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-14 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-15 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-15 | 2026-02-01 | Krishna-1 | 44/10 | 45/0 | 44/10¦45/0 | TSE |  | 0.062917 | 0.755 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-15 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-15 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-16 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-16 | 2026-02-01 | Krishna-1 | 44/10 | 45/0 | 44/10¦45/0 | TSE |  | 0.062917 | 0.755 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-16 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-16 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-16 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-17 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-17 | 2026-02-01 | Krishna-1 | 44/10 | 45/0 | 44/10¦45/0 | TSE |  | 0.062917 | 0.755 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-17 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-17 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-17 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-18 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-18 | 2026-02-01 | Krishna-1 | 44/10 | 45/0 | 44/10¦45/0 | TSE |  | 0.062917 | 0.755 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-18 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-18 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-18 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-19 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-19 | 2026-02-01 | Krishna-1 | 44/10 | 45/0 | 44/10¦45/0 | TSE |  | 0.062917 | 0.755 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-19 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-19 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-19 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-20 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-20 | 2026-02-01 | Gopal Associate, Hotline | 7/0 | 8/0 | 7/0¦8/0 | M |  | 0.030143 | 0.211 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-20 | 2026-02-01 | Krishna-1 | 44/10 | 45/0 | 44/10¦45/0 | TSE |  | 0.062917 | 0.755 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-20 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-20 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-20 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-21 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-21 | 2026-02-01 | Gopal Associate, Hotline | 7/0 | 8/0 | 7/0¦8/0 | M |  | 0.030143 | 0.211 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-21 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-21 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-21 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-22 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-22 | 2026-02-01 | Gopal Associate, Hotline | 7/0 | 8/0 | 7/0¦8/0 | M |  | 0.030143 | 0.211 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-22 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-22 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-22 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-23 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-23 | 2026-02-01 | Gopal Associate, Hotline | 7/0 | 8/0 | 7/0¦8/0 | M |  | 0.030143 | 0.211 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-23 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-23 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-23 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-24 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-24 | 2026-02-01 | Gopal Associate, Hotline | 7/0 | 8/0 | 7/0¦8/0 | M |  | 0.030143 | 0.211 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-24 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-24 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-24 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-25 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-25 | 2026-02-01 | Gopal Associate, Hotline | 7/0 | 8/0 | 7/0¦8/0 | M |  | 0.030143 | 0.211 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-25 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-25 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-25 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-26 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-26 | 2026-02-01 | Gopal Associate, Hotline | 7/0 | 8/0 | 7/0¦8/0 | M |  | 0.030143 | 0.211 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-26 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-26 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-26 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-27 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-27 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-27 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-27 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-28 | 2026-02-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-28 | 2026-02-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-28 | 2026-02-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-02-28 | 2026-02-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-01 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-01 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-01 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-01 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-02 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-02 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-02 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-02 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-03 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-03 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-03 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-03 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-04 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-04 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-04 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-04 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-05 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-05 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-05 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-05 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-06 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-06 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-06 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-06 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-07 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-07 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-07 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-07 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-08 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-08 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-08 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-08 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-09 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-09 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-09 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-09 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-09 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-10 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-10 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-10 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-10 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-10 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-11 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-11 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-11 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-11 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-11 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-12 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-12 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-12 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-12 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-12 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-13 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-13 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-13 | 2026-03-01 | Krishna-1 | 44/8 | 44/10 | 44/10¦44/8 | TSE |  | 0.030577 | 0.795 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-13 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-13 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-14 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-14 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-14 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-14 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-15 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-15 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-15 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-15 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-16 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-16 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-16 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-16 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-17 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-17 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-17 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-17 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-18 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-18 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-18 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-18 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-19 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-19 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-19 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-19 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-20 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-20 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-20 | 2026-03-01 | Krishna-1 | 44/6 | 44/8 | 44/6¦44/8 | TSE |  | 0.07 | 0.84 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-20 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-20 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-21 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-21 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-21 | 2026-03-01 | Krishna-1 | 44/6 | 44/8 | 44/6¦44/8 | TSE |  | 0.07 | 0.84 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-21 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-21 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-22 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-22 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-22 | 2026-03-01 | Krishna-1 | 44/6 | 44/8 | 44/6¦44/8 | TSE |  | 0.07 | 0.84 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-22 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-22 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-23 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-23 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-23 | 2026-03-01 | Krishna-1 | 44/6 | 44/8 | 44/6¦44/8 | TSE |  | 0.07 | 0.84 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-23 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-23 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-24 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-24 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-24 | 2026-03-01 | Devi Power | 1/0 | 1A/0 | 1/0¦1A/0 | M |  | 0.01125 | 0.09 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-24 | 2026-03-01 | Krishna-1 | 44/6 | 44/8 | 44/6¦44/8 | TSE |  | 0.07 | 0.84 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-24 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-24 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-25 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-25 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-25 | 2026-03-01 | Devi Power | 1/0 | 1A/0 | 1/0¦1A/0 | M |  | 0.01125 | 0.09 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-25 | 2026-03-01 | Krishna-1 | 44/6 | 44/8 | 44/6¦44/8 | TSE |  | 0.07 | 0.84 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-25 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-25 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-26 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-26 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-26 | 2026-03-01 | Devi Power | 1/0 | 1A/0 | 1/0¦1A/0 | M |  | 0.01125 | 0.09 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-26 | 2026-03-01 | Krishna-1 | 44/6 | 44/8 | 44/6¦44/8 | TSE |  | 0.07 | 0.84 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-26 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-26 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-27 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-27 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-27 | 2026-03-01 | Devi Power | 1/0 | 1A/0 | 1/0¦1A/0 | M |  | 0.01125 | 0.09 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-27 | 2026-03-01 | Devi Power | Gty | 1/0 | 1/0¦GTY | M |  | 0.0305 | 0.122 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-27 | 2026-03-01 | Krishna-1 | 44/6 | 44/8 | 44/6¦44/8 | TSE |  | 0.07 | 0.84 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-27 | 2026-03-01 | Krishna-1 | 44/0 | 44/6 | 44/0¦44/6 | TSE |  | 0.4624 | 2.312 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-27 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-27 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-28 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-28 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-28 | 2026-03-01 | Devi Power | 1/0 | 1A/0 | 1/0¦1A/0 | M |  | 0.01125 | 0.09 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-28 | 2026-03-01 | Devi Power | Gty | 1/0 | 1/0¦GTY | M |  | 0.0305 | 0.122 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-28 | 2026-03-01 | Krishna-1 | 44/6 | 44/8 | 44/6¦44/8 | TSE |  | 0.07 | 0.84 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-28 | 2026-03-01 | Krishna-1 | 44/0 | 44/6 | 44/0¦44/6 | TSE |  | 0.4624 | 2.312 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-28 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-28 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-29 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-29 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-29 | 2026-03-01 | Devi Power | 1/0 | 1A/0 | 1/0¦1A/0 | M |  | 0.01125 | 0.09 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-29 | 2026-03-01 | Devi Power | Gty | 1/0 | 1/0¦GTY | M |  | 0.0305 | 0.122 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-29 | 2026-03-01 | Krishna-1 | 44/6 | 44/8 | 44/6¦44/8 | TSE |  | 0.07 | 0.84 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-29 | 2026-03-01 | Krishna-1 | 44/0 | 44/6 | 44/0¦44/6 | TSE |  | 0.4624 | 2.312 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-29 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-29 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-30 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-30 | 2026-03-01 | Deepak Sarkar | 8/7 | 9/0 | 8/7¦9/0 | TSE |  | 0.2456 | 2.456 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-30 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-30 | 2026-03-01 | Devi Power | 1/0 | 1A/0 | 1/0¦1A/0 | M |  | 0.01125 | 0.09 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-30 | 2026-03-01 | Devi Power | Gty | 1/0 | 1/0¦GTY | M |  | 0.0305 | 0.122 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-30 | 2026-03-01 | Krishna-1 | 44/6 | 44/8 | 44/6¦44/8 | TSE |  | 0.07 | 0.84 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-30 | 2026-03-01 | Krishna-1 | 44/0 | 44/6 | 44/0¦44/6 | TSE |  | 0.4624 | 2.312 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-30 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-30 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-30 | 2026-03-01 | Nasiruddin | 14/0 | 14A/0 | 14/0¦14A/0 | M |  | 0.047625 | 0.381 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-30 | 2026-03-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-31 | 2026-03-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-31 | 2026-03-01 | Deepak Sarkar | 8/7 | 9/0 | 8/7¦9/0 | TSE |  | 0.2456 | 2.456 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-31 | 2026-03-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-31 | 2026-03-01 | Devi Power | 1/0 | 1A/0 | 1/0¦1A/0 | M |  | 0.01125 | 0.09 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-31 | 2026-03-01 | Krishna-1 | 44/6 | 44/8 | 44/6¦44/8 | TSE |  | 0.07 | 0.84 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-31 | 2026-03-01 | Krishna-1 | 44/0 | 44/6 | 44/0¦44/6 | TSE |  | 0.4624 | 2.312 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-31 | 2026-03-01 | MC Power | 55/0 | 56/0 | 55/0¦56/0 | TSE |  | 0.069583 | 3.34 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-31 | 2026-03-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-31 | 2026-03-01 | Nasiruddin | 14/0 | 14A/0 | 14/0¦14A/0 | M |  | 0.047625 | 0.381 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-03-31 | 2026-03-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-01 | 2026-04-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-01 | 2026-04-01 | Deepak Sarkar | 8/7 | 9/0 | 8/7¦9/0 | TSE |  | 0.2456 | 2.456 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-01 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-01 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-01 | 2026-04-01 | Nasiruddin | 14/0 | 14A/0 | 14/0¦14A/0 | M |  | 0.047625 | 0.381 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-01 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-02 | 2026-04-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-02 | 2026-04-01 | Deepak Sarkar | 8/7 | 9/0 | 8/7¦9/0 | TSE |  | 0.2456 | 2.456 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-02 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-02 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-02 | 2026-04-01 | Nasiruddin | 14/0 | 14A/0 | 14/0¦14A/0 | M |  | 0.047625 | 0.381 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-02 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-03 | 2026-04-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-03 | 2026-04-01 | Deepak Sarkar | 8/7 | 9/0 | 8/7¦9/0 | TSE |  | 0.2456 | 2.456 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-03 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-03 | 2026-04-01 | Gopal Associate, Hotline | 9/0 | 10/0 | 10/0¦9/0 | M |  | 0.029125 | 0.233 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-03 | 2026-04-01 | MC Power | 54/0 | 55/0 | 54/0¦55/0 | TSE |  | 0.26789 | 2.411 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-03 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-03 | 2026-04-01 | Nasiruddin | 14/0 | 14A/0 | 14/0¦14A/0 | M |  | 0.047625 | 0.381 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-03 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-04 | 2026-04-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-04 | 2026-04-01 | Deepak Sarkar | 8/7 | 9/0 | 8/7¦9/0 | TSE |  | 0.2456 | 2.456 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-04 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-04 | 2026-04-01 | Gopal Associate, Hotline | 9/0 | 10/0 | 10/0¦9/0 | M |  | 0.029125 | 0.233 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-04 | 2026-04-01 | MC Power | 54/0 | 55/0 | 54/0¦55/0 | TSE |  | 0.26789 | 2.411 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-04 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-04 | 2026-04-01 | Nasiruddin | 14/0 | 14A/0 | 14/0¦14A/0 | M |  | 0.047625 | 0.381 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-04 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-05 | 2026-04-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-05 | 2026-04-01 | Deepak Sarkar | 8/7 | 9/0 | 8/7¦9/0 | TSE |  | 0.2456 | 2.456 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-05 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-05 | 2026-04-01 | Gopal Associate, Hotline | 9/0 | 10/0 | 10/0¦9/0 | M |  | 0.029125 | 0.233 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-05 | 2026-04-01 | MC Power | 54/0 | 55/0 | 54/0¦55/0 | TSE |  | 0.26789 | 2.411 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-05 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-05 | 2026-04-01 | Nasiruddin | 14/0 | 14A/0 | 14/0¦14A/0 | M |  | 0.047625 | 0.381 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-05 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-06 | 2026-04-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-06 | 2026-04-01 | Deepak Sarkar | 8/7 | 9/0 | 8/7¦9/0 | TSE |  | 0.2456 | 2.456 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-06 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-06 | 2026-04-01 | Devi Power | 8/0 | 8/7 | 8/0¦8/7 | TSE |  | 0.47683 | 2.861 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-06 | 2026-04-01 | Gopal Associate, Hotline | 9/0 | 10/0 | 10/0¦9/0 | M |  | 0.029125 | 0.233 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-06 | 2026-04-01 | MC Power | 54/0 | 55/0 | 54/0¦55/0 | TSE |  | 0.26789 | 2.411 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-06 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-06 | 2026-04-01 | Nasiruddin | 14/0 | 14A/0 | 14/0¦14A/0 | M |  | 0.047625 | 0.381 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-06 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-07 | 2026-04-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-07 | 2026-04-01 | Deepak Sarkar | 8/7 | 9/0 | 8/7¦9/0 | TSE |  | 0.2456 | 2.456 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-07 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-07 | 2026-04-01 | Devi Power | 8/0 | 8/7 | 8/0¦8/7 | TSE |  | 0.47683 | 2.861 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-07 | 2026-04-01 | Gopal Associate, Hotline | 9/0 | 10/0 | 10/0¦9/0 | M |  | 0.029125 | 0.233 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-07 | 2026-04-01 | MC Power | 54/0 | 55/0 | 54/0¦55/0 | TSE |  | 0.26789 | 2.411 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-07 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-07 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-08 | 2026-04-01 | Deepak Sarkar | 10/0 | 10/12 | 10/0¦10/12 | TSE |  | 0.15787 | 4.894 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-08 | 2026-04-01 | Deepak Sarkar | 8/7 | 9/0 | 8/7¦9/0 | TSE |  | 0.2456 | 2.456 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-08 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-08 | 2026-04-01 | Devi Power | 8/0 | 8/7 | 8/0¦8/7 | TSE |  | 0.47683 | 2.861 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-08 | 2026-04-01 | Gopal Associate, Hotline | 9/0 | 10/0 | 10/0¦9/0 | M |  | 0.029125 | 0.233 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-08 | 2026-04-01 | Krishna-1 | 43/0 | 44/0 | 43/0¦44/0 | TSE |  | 0.44115 | 4.8527 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-08 | 2026-04-01 | MC Power | 54/0 | 55/0 | 54/0¦55/0 | TSE |  | 0.26789 | 2.411 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-08 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-08 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-09 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-09 | 2026-04-01 | Devi Power | 8/0 | 8/7 | 8/0¦8/7 | TSE |  | 0.47683 | 2.861 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-09 | 2026-04-01 | Gopal Associate, Hotline | 9/0 | 10/0 | 10/0¦9/0 | M |  | 0.029125 | 0.233 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-09 | 2026-04-01 | Krishna-1 | 43/0 | 44/0 | 43/0¦44/0 | TSE |  | 0.44115 | 4.8527 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-09 | 2026-04-01 | MC Power | 54/0 | 55/0 | 54/0¦55/0 | TSE |  | 0.26789 | 2.411 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-09 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-09 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-10 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-10 | 2026-04-01 | Devi Power | 8/0 | 8/7 | 8/0¦8/7 | TSE |  | 0.47683 | 2.861 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-10 | 2026-04-01 | Gopal Associate, Hotline | 9/0 | 10/0 | 10/0¦9/0 | M |  | 0.029125 | 0.233 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-10 | 2026-04-01 | Krishna-1 | 43/0 | 44/0 | 43/0¦44/0 | TSE |  | 0.44115 | 4.8527 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-10 | 2026-04-01 | MC Power | 54/0 | 55/0 | 54/0¦55/0 | TSE |  | 0.26789 | 2.411 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-10 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-10 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-11 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-11 | 2026-04-01 | Devi Power | 8/0 | 8/7 | 8/0¦8/7 | TSE |  | 0.47683 | 2.861 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-11 | 2026-04-01 | Krishna-1 | 43/0 | 44/0 | 43/0¦44/0 | TSE |  | 0.44115 | 4.8527 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-11 | 2026-04-01 | MC Power | 54/0 | 55/0 | 54/0¦55/0 | TSE |  | 0.26789 | 2.411 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-11 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-11 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-12 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-12 | 2026-04-01 | Krishna-1 | 43/0 | 44/0 | 43/0¦44/0 | TSE |  | 0.44115 | 4.8527 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-12 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-12 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-13 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-13 | 2026-04-01 | Krishna-1 | 43/0 | 44/0 | 43/0¦44/0 | TSE |  | 0.44115 | 4.8527 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-13 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-13 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-14 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-14 | 2026-04-01 | Krishna-1 | 43/0 | 44/0 | 43/0¦44/0 | TSE |  | 0.44115 | 4.8527 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-14 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-14 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-15 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-15 | 2026-04-01 | Krishna-1 | 43/0 | 44/0 | 43/0¦44/0 | TSE |  | 0.44115 | 4.8527 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-15 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-15 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-16 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-16 | 2026-04-01 | Krishna-1 | 43/0 | 44/0 | 43/0¦44/0 | TSE |  | 0.44115 | 4.8527 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-16 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-16 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-17 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-17 | 2026-04-01 | Krishna-1 | 43/0 | 44/0 | 43/0¦44/0 | TSE |  | 0.44115 | 4.8527 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-17 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-17 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-18 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-18 | 2026-04-01 | Krishna-1 | 43/0 | 44/0 | 43/0¦44/0 | TSE |  | 0.44115 | 4.8527 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-18 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-18 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-19 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-19 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-19 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-20 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-20 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-20 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-21 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-21 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-21 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-22 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-22 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-22 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-23 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-23 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-23 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-24 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-24 | 2026-04-01 | Gopal Associate, Hotline | 5/0 | 6/0 | 5/0¦6/0 | M |  | 0.035143 | 0.246 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-24 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-24 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-25 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-25 | 2026-04-01 | Gopal Associate, Hotline | 5/0 | 6/0 | 5/0¦6/0 | M |  | 0.035143 | 0.246 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-25 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-25 | 2026-04-01 | Nasiruddin | 14A/0 | 15/0 | 14A/0¦15/0 | TSE |  | 0.1192 | 1.192 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-25 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-26 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-26 | 2026-04-01 | Gopal Associate, Hotline | 5/0 | 6/0 | 5/0¦6/0 | M |  | 0.035143 | 0.246 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-26 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-26 | 2026-04-01 | Nasiruddin | 14A/0 | 15/0 | 14A/0¦15/0 | TSE |  | 0.1192 | 1.192 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-26 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-27 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-27 | 2026-04-01 | Gopal Associate, Hotline | 5/0 | 6/0 | 5/0¦6/0 | M |  | 0.035143 | 0.246 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-27 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-27 | 2026-04-01 | Nasiruddin | 14A/0 | 15/0 | 14A/0¦15/0 | TSE |  | 0.1192 | 1.192 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-27 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-28 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-28 | 2026-04-01 | Gopal Associate, Hotline | 5/0 | 6/0 | 5/0¦6/0 | M |  | 0.035143 | 0.246 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-28 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-28 | 2026-04-01 | Nasiruddin | 14A/0 | 15/0 | 14A/0¦15/0 | TSE |  | 0.1192 | 1.192 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-28 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-29 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-29 | 2026-04-01 | Gopal Associate, Hotline | 5/0 | 6/0 | 5/0¦6/0 | M |  | 0.035143 | 0.246 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-29 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-29 | 2026-04-01 | Nasiruddin | 14A/0 | 15/0 | 14A/0¦15/0 | TSE |  | 0.1192 | 1.192 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-29 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-30 | 2026-04-01 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 6/0¦7/0 | TSE |  | 0.0027941 | 1.14 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-30 | 2026-04-01 | Gopal Associate, Hotline | 5/0 | 6/0 | 5/0¦6/0 | M |  | 0.035143 | 0.246 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-30 | 2026-04-01 | MC Power | 53/0 | 54/0 | 53/0¦54/0 | TSE |  | 0.0097619 | 3.69 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-30 | 2026-04-01 | Nasiruddin | 14A/0 | 15/0 | 14A/0¦15/0 | TSE |  | 0.1192 | 1.192 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-04-30 | 2026-04-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-01 | 2026-05-01 | Nasiruddin | 14A/0 | 15/0 | 14A/0¦15/0 | TSE |  | 0.1192 | 1.192 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-01 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-02 | 2026-05-01 | Nasiruddin | 14A/0 | 15/0 | 14A/0¦15/0 | TSE |  | 0.1192 | 1.192 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-02 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-03 | 2026-05-01 | Nasiruddin | 14A/0 | 15/0 | 14A/0¦15/0 | TSE |  | 0.1192 | 1.192 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-03 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-04 | 2026-05-01 | Nasiruddin | 14A/0 | 15/0 | 14A/0¦15/0 | TSE |  | 0.1192 | 1.192 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-04 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-05 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-06 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-07 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-08 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-09 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-10 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-10 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-11 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-11 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-12 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-12 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-13 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-13 | 2026-05-01 | Nasiruddin | 13/0 | 14/0 | 13/0¦14/0 | TSE |  | 0.046178 | 2.078 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-14 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-15 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-16 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-17 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-18 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-18 | 2026-05-01 | Nasiruddin | 11A/0 | 12/0 | 11A/0¦12/0 | TSE |  | 0.3425 | 4.11 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-19 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-19 | 2026-05-01 | Nasiruddin | 11A/0 | 12/0 | 11A/0¦12/0 | TSE |  | 0.3425 | 4.11 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-20 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-20 | 2026-05-01 | Nasiruddin | 11A/0 | 12/0 | 11A/0¦12/0 | TSE |  | 0.3425 | 4.11 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-21 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-21 | 2026-05-01 | Nasiruddin | 11A/0 | 12/0 | 11A/0¦12/0 | TSE |  | 0.3425 | 4.11 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-22 | 2026-05-01 | MC Power | 52/0 | 53/0 | 52/0¦53/0 | TSE |  | 0.34877 | 4.534 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-22 | 2026-05-01 | Nasiruddin | 11A/0 | 12/0 | 11A/0¦12/0 | TSE |  | 0.3425 | 4.11 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-23 | 2026-05-01 | Nasiruddin | 11A/0 | 12/0 | 11A/0¦12/0 | TSE |  | 0.3425 | 4.11 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-24 | 2026-05-01 | Nasiruddin | 11A/0 | 12/0 | 11A/0¦12/0 | TSE |  | 0.3425 | 4.11 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-25 | 2026-05-01 | Nasiruddin | 11A/0 | 12/0 | 11A/0¦12/0 | TSE |  | 0.3425 | 4.11 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-26 | 2026-05-01 | Gopal Associate, Hotline | 12/0 | 13/0 | 12/0¦13/0 | M |  | 0.035317 | 0.2119 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-26 | 2026-05-01 | Nasiruddin | 11A/0 | 12/0 | 11A/0¦12/0 | TSE |  | 0.3425 | 4.11 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-27 | 2026-05-01 | Gopal Associate, Hotline | 12/0 | 13/0 | 12/0¦13/0 | M |  | 0.035317 | 0.2119 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-27 | 2026-05-01 | Nasiruddin | 11A/0 | 12/0 | 11A/0¦12/0 | TSE |  | 0.3425 | 4.11 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-28 | 2026-05-01 | Gopal Associate, Hotline | 12/0 | 13/0 | 12/0¦13/0 | M |  | 0.035317 | 0.2119 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-28 | 2026-05-01 | Nasiruddin | 11A/0 | 12/0 | 11A/0¦12/0 | TSE |  | 0.3425 | 4.11 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-29 | 2026-05-01 | Gopal Associate, Hotline | 12/0 | 13/0 | 12/0¦13/0 | M |  | 0.035317 | 0.2119 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-29 | 2026-05-01 | Nasiruddin | 11A/0 | 12/0 | 11A/0¦12/0 | TSE |  | 0.3425 | 4.11 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-30 | 2026-05-01 | Gopal Associate, Hotline | 12/0 | 13/0 | 12/0¦13/0 | M |  | 0.035317 | 0.2119 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 408 | TB 408 | tb408 |  | 2026-05-31 | 2026-05-01 | Gopal Associate, Hotline | 12/0 | 13/0 | 12/0¦13/0 | M |  | 0.035317 | 0.2119 |  |  | ABSENT | ABSENT | no | TRUE | NO_DATA | No manpower values found for this span/day.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-02-20 | 2026-02-01 | SK Basirul | 18/0 | Gantry | 18/0¦GANTRY | tse | C | 0.019999 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-02-21 | 2026-02-01 | SK Basirul | 18/0 | Gantry | 18/0¦GANTRY | tse | C | 0.019999 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-02-23 | 2026-02-01 | SK Basirul | 16/2 | 17/0 | 16/2¦17/0 | tse | C | 0.03752 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-02 | 2026-03-01 | SK Basirul | 17/0 | 18/0 | 17/0¦18/0 | tse | C | 0.082573 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-03 | 2026-03-01 | SK Basirul | 16/1 | 16/2 | 16/1¦16/2 | tse | C | 0.071 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-03 | 2026-03-01 | SK Basirul | 17/0 | 18/0 | 17/0¦18/0 | tse | C | 0.082573 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-05 | 2026-03-01 | SK Basirul | 16/0 | 16/1 | 16/0¦16/1 | tse | C | 0.01871 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-06 | 2026-03-01 | SK Basirul | 16/0 | 16/1 | 16/0¦16/1 | tse | C | 0.01871 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-07 | 2026-03-01 | Sawariya seth | 15/0 | 15/1 | 15/0¦15/1 | tse | C | 0.08765 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-07 | 2026-03-01 | Sawariya seth | 15/1 | 15/2 | 15/1¦15/2 | tse | C | 0.083857 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-07 | 2026-03-01 | Sawariya seth | 15/2 | 15/3 | 15/2¦15/3 | tse | C | 0.090587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-07 | 2026-03-01 | Sawariya seth | 15/3 | 16/0 | 15/3¦16/0 | tse | C | 0.087013 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-08 | 2026-03-01 | Sawariya seth | 15/0 | 15/1 | 15/0¦15/1 | tse | C | 0.08765 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-08 | 2026-03-01 | Sawariya seth | 15/1 | 15/2 | 15/1¦15/2 | tse | C | 0.083857 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-08 | 2026-03-01 | Sawariya seth | 15/2 | 15/3 | 15/2¦15/3 | tse | C | 0.090587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-08 | 2026-03-01 | Sawariya seth | 15/3 | 16/0 | 15/3¦16/0 | tse | C | 0.087013 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-09 | 2026-03-01 | Sawariya seth | 15/0 | 15/1 | 15/0¦15/1 | tse | C | 0.08765 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-09 | 2026-03-01 | Sawariya seth | 15/1 | 15/2 | 15/1¦15/2 | tse | C | 0.083857 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-09 | 2026-03-01 | Sawariya seth | 15/2 | 15/3 | 15/2¦15/3 | tse | C | 0.090587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-09 | 2026-03-01 | Sawariya seth | 15/3 | 16/0 | 15/3¦16/0 | tse | C | 0.087013 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-12 | 2026-03-01 | Sawariya seth | 13/0 | 13/1 | 13/0¦13/1 | tse | C | 0.04842 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-12 | 2026-03-01 | Sawariya seth | 13/1 | 13/2 | 13/1¦13/2 | tse | C | 0.019413 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-13 | 2026-03-01 | Sawariya seth | 12/0 | 12/1 | 12/0¦12/1 | tse | C | 0.0685 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-13 | 2026-03-01 | Sawariya seth | 12/1 | 13/0 | 12/1¦13/0 | tse | C | 0.07332 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-13 | 2026-03-01 | Sawariya seth | 13/1 | 13/2 | 13/1¦13/2 | tse | C | 0.019413 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-14 | 2026-03-01 | Sawariya seth | 12/0 | 12/1 | 12/0¦12/1 | tse | C | 0.0685 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-14 | 2026-03-01 | Sawariya seth | 12/1 | 13/0 | 12/1¦13/0 | tse | C | 0.07332 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-14 | 2026-03-01 | Sawariya seth | 13/1 | 13/2 | 13/1¦13/2 | tse | C | 0.019413 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-15 | 2026-03-01 | Sawariya seth | 12/0 | 12/1 | 12/0¦12/1 | tse | C | 0.0685 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-15 | 2026-03-01 | Sawariya seth | 12/1 | 13/0 | 12/1¦13/0 | tse | C | 0.07332 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-15 | 2026-03-01 | Sawariya seth | 13/2 | 14/0 | 13/2¦14/0 | tse | C | 0.07013 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-16 | 2026-03-01 | Sawariya seth | 12/0 | 12/1 | 12/0¦12/1 | tse | C | 0.0685 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-16 | 2026-03-01 | Sawariya seth | 12/1 | 13/0 | 12/1¦13/0 | tse | C | 0.07332 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-17 | 2026-03-01 | Sawariya seth | 8/0 | 9/0 | 8/0¦9/0 | tse | C | 0.09649 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-17 | 2026-03-01 | Sawariya seth | 9/0 | 10/0 | 10/0¦9/0 | tse | C | 0.06498 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-18 | 2026-03-01 | Sawariya seth | 8/0 | 9/0 | 8/0¦9/0 | tse | C | 0.09649 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-18 | 2026-03-01 | Sawariya seth | 9/0 | 10/0 | 10/0¦9/0 | tse | C | 0.06498 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-19 | 2026-03-01 | Sawariya seth | 8/0 | 9/0 | 8/0¦9/0 | tse | C | 0.09649 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-19 | 2026-03-01 | Sawariya seth | 9/0 | 10/0 | 10/0¦9/0 | tse | C | 0.06498 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-20 | 2026-03-01 | Sawariya seth | 8/0 | 9/0 | 8/0¦9/0 | tse | C | 0.09649 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-20 | 2026-03-01 | Sawariya seth | 9/0 | 10/0 | 10/0¦9/0 | tse | C | 0.06498 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-23 | 2026-03-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.039731 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-24 | 2026-03-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.039731 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-25 | 2026-03-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | tse | C | 0.031827 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-25 | 2026-03-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.039731 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-26 | 2026-03-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | tse | C | 0.031827 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-26 | 2026-03-01 | National Construction | 6/0 | 6/1 | 6/0¦6/1 | tse | C | 0.0634 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-26 | 2026-03-01 | National Construction | 6/1 | 6/2 | 6/1¦6/2 | tse | C | 0.0656 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-26 | 2026-03-01 | National Construction | 6/2 | 6/3 | 6/2¦6/3 | tse | C | 0.0594 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-26 | 2026-03-01 | National Construction | 6/3 | 6/4 | 6/3¦6/4 | tse | C | 0.0502 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-26 | 2026-03-01 | National Construction | 6/4 | 7/0 | 6/4¦7/0 | tse | C | 0.061646 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-26 | 2026-03-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.039731 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-27 | 2026-03-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | tse | C | 0.031827 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-27 | 2026-03-01 | National Construction | 6/0 | 6/1 | 6/0¦6/1 | tse | C | 0.0634 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-27 | 2026-03-01 | National Construction | 6/1 | 6/2 | 6/1¦6/2 | tse | C | 0.0656 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-27 | 2026-03-01 | National Construction | 6/2 | 6/3 | 6/2¦6/3 | tse | C | 0.0594 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-27 | 2026-03-01 | National Construction | 6/3 | 6/4 | 6/3¦6/4 | tse | C | 0.0502 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-27 | 2026-03-01 | National Construction | 6/4 | 7/0 | 6/4¦7/0 | tse | C | 0.061646 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-27 | 2026-03-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.039731 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-28 | 2026-03-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | tse | C | 0.031827 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-28 | 2026-03-01 | National Construction | 6/0 | 6/1 | 6/0¦6/1 | tse | C | 0.0634 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-28 | 2026-03-01 | National Construction | 6/1 | 6/2 | 6/1¦6/2 | tse | C | 0.0656 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-28 | 2026-03-01 | National Construction | 6/2 | 6/3 | 6/2¦6/3 | tse | C | 0.0594 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-28 | 2026-03-01 | National Construction | 6/3 | 6/4 | 6/3¦6/4 | tse | C | 0.0502 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-28 | 2026-03-01 | National Construction | 6/4 | 7/0 | 6/4¦7/0 | tse | C | 0.061646 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-28 | 2026-03-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.039731 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-29 | 2026-03-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | tse | C | 0.031827 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-29 | 2026-03-01 | National Construction | 6/0 | 6/1 | 6/0¦6/1 | tse | C | 0.0634 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-29 | 2026-03-01 | National Construction | 6/1 | 6/2 | 6/1¦6/2 | tse | C | 0.0656 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-29 | 2026-03-01 | National Construction | 6/2 | 6/3 | 6/2¦6/3 | tse | C | 0.0594 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-29 | 2026-03-01 | National Construction | 6/3 | 6/4 | 6/3¦6/4 | tse | C | 0.0502 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-29 | 2026-03-01 | National Construction | 6/4 | 7/0 | 6/4¦7/0 | tse | C | 0.061646 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-29 | 2026-03-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.039731 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-30 | 2026-03-01 |  | 4/1 | 4/2 | 4/1¦4/2 | tse | C | 0.026 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-30 | 2026-03-01 | National Construction | 4/2 | 5/0 | 4/2¦5/0 | tse | C | 0.011765 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-30 | 2026-03-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | tse | C | 0.031827 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-30 | 2026-03-01 | National Construction | 6/0 | 6/1 | 6/0¦6/1 | tse | C | 0.0634 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-30 | 2026-03-01 | National Construction | 6/1 | 6/2 | 6/1¦6/2 | tse | C | 0.0656 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-30 | 2026-03-01 | National Construction | 6/2 | 6/3 | 6/2¦6/3 | tse | C | 0.0594 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-30 | 2026-03-01 | National Construction | 6/3 | 6/4 | 6/3¦6/4 | tse | C | 0.0502 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-30 | 2026-03-01 | National Construction | 6/4 | 7/0 | 6/4¦7/0 | tse | C | 0.061646 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-30 | 2026-03-01 | Sammirul Sekh | 4/0 | 4/1 | 4/0¦4/1 | tse | C | 0.010905 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-31 | 2026-03-01 |  | 4/1 | 4/2 | 4/1¦4/2 | tse | C | 0.026 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-31 | 2026-03-01 | National Construction | 4/2 | 5/0 | 4/2¦5/0 | tse | C | 0.011765 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-31 | 2026-03-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | tse | C | 0.031827 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-03-31 | 2026-03-01 | Sammirul Sekh | 4/0 | 4/1 | 4/0¦4/1 | tse | C | 0.010905 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-04-01 | 2026-04-01 | National Construction | 4/2 | 5/0 | 4/2¦5/0 | tse | C | 0.011765 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-04-01 | 2026-04-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | tse | C | 0.031827 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-04-01 | 2026-04-01 | Sammirul Sekh | 4/0 | 4/1 | 4/0¦4/1 | tse | C | 0.010905 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-04-02 | 2026-04-01 | National Construction | 4/2 | 5/0 | 4/2¦5/0 | tse | C | 0.011765 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-04-02 | 2026-04-01 | National Construction | 5/0 | 6/0 | 5/0¦6/0 | tse | C | 0.031827 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-04-02 | 2026-04-01 | Sammirul Sekh | 4/0 | 4/1 | 4/0¦4/1 | tse | C | 0.010905 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-05-07 | 2026-05-01 | Sammirul Sekh | 3/0 | 3/1 | 3/0¦3/1 | tse | C | 0.085333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-05-07 | 2026-05-01 | Sammirul Sekh | 3/1 | 4/0 | 3/1¦4/0 | tse | C | 0.075507 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-05-08 | 2026-05-01 | Sammirul Sekh | 3/0 | 3/1 | 3/0¦3/1 | tse | C | 0.085333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-05-08 | 2026-05-01 | Sammirul Sekh | 3/1 | 4/0 | 3/1¦4/0 | tse | C | 0.075507 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-05-09 | 2026-05-01 | Sammirul Sekh | 3/0 | 3/1 | 3/0¦3/1 | tse | C | 0.085333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-05-09 | 2026-05-01 | Sammirul Sekh | 3/1 | 4/0 | 3/1¦4/0 | tse | C | 0.075507 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-05-10 | 2026-05-01 | Sammirul Sekh | 11/0 | 12/0 | 11/0¦12/0 | tse | C | 0.079037 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-05-11 | 2026-05-01 | Sammirul Sekh | 11/0 | 12/0 | 11/0¦12/0 | tse | C | 0.079037 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-05-12 | 2026-05-01 | Sammirul Sekh | 11/0 | 12/0 | 11/0¦12/0 | tse | C | 0.079037 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-05-13 | 2026-05-01 | Sammirul Sekh | 11/0 | 12/0 | 11/0¦12/0 | tse | C | 0.079037 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-05-14 | 2026-05-01 | Sammirul Sekh | 14/0 | 15/0 | 14/0¦15/0 | tse | C | 0.11035 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 2026-05-15 | 2026-05-01 | Sammirul Sekh | 14/0 | 15/0 | 14/0¦15/0 | tse | C | 0.11035 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-19 | 2025-05-01 | National Construction | 0/0 | 1/0 | 0/0¦1/0 | tse | C | 0.03927 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-19 | 2025-05-01 | National Construction | 1/0 | 1A/0 | 1/0¦1A/0 | tse | C | 0.10373 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-20 | 2025-05-01 | National Construction | 0/0 | 1/0 | 0/0¦1/0 | tse | C | 0.03927 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-20 | 2025-05-01 | National Construction | 1/0 | 1A/0 | 1/0¦1A/0 | tse | C | 0.10373 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-21 | 2025-05-01 | National Construction | 0/0 | 1/0 | 0/0¦1/0 | tse | C | 0.03927 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-21 | 2025-05-01 | National Construction | 1/0 | 1A/0 | 1/0¦1A/0 | tse | C | 0.10373 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-22 | 2025-05-01 | National Construction | 0/0 | 1/0 | 0/0¦1/0 | tse | C | 0.03927 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-22 | 2025-05-01 | National Construction | 1/0 | 1A/0 | 1/0¦1A/0 | tse | C | 0.10373 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-23 | 2025-05-01 | National Construction | 0/0 | 1/0 | 0/0¦1/0 | tse | C | 0.03927 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-23 | 2025-05-01 | National Construction | 1/0 | 1A/0 | 1/0¦1A/0 | tse | C | 0.10373 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-24 | 2025-05-01 | National Construction | 0/0 | 1/0 | 0/0¦1/0 | tse | C | 0.03927 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-24 | 2025-05-01 | National Construction | 1/0 | 1A/0 | 1/0¦1A/0 | tse | C | 0.10373 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-25 | 2025-05-01 | National Construction | 0/0 | 1/0 | 0/0¦1/0 | tse | C | 0.03927 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-25 | 2025-05-01 | National Construction | 1/0 | 1A/0 | 1/0¦1A/0 | tse | C | 0.10373 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-26 | 2025-05-01 | National Construction | 0/0 | 1/0 | 0/0¦1/0 | tse | C | 0.03927 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-26 | 2025-05-01 | National Construction | 1/0 | 1A/0 | 1/0¦1A/0 | tse | C | 0.10373 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-27 | 2025-05-01 | National Construction | 0/0 | 1/0 | 0/0¦1/0 | tse | C | 0.03927 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-27 | 2025-05-01 | National Construction | 1/0 | 1A/0 | 1/0¦1A/0 | tse | C | 0.10373 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-28 | 2025-05-01 | National Construction | 0/0 | 1/0 | 0/0¦1/0 | tse | C | 0.03927 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-05-28 | 2025-05-01 | National Construction | 1/0 | 1A/0 | 1/0¦1A/0 | tse | C | 0.10373 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-17 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-18 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-19 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-20 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-21 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-22 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-23 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-24 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-25 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-26 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-27 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-28 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-29 | 2025-06-01 | National Construction | 1A/0 | 1A/2 | 1A/0¦1A/2 | tse | C | 0.3045 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-29 | 2025-06-01 | National Construction | 1A/2 | 1B/0 | 1A/2¦1B/0 | tse | C | 0.2321 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-29 | 2025-06-01 | Nemchand | AP-15 | AP-16 | 15¦16 | tse | C | 0.26327 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-30 | 2025-06-01 | National Construction | 1A/0 | 1A/2 | 1A/0¦1A/2 | tse | C | 0.3045 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-30 | 2025-06-01 | National Construction | AP-16 | AP-17 | 16¦17 | tse | C | 0.10897 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-06-30 | 2025-06-01 | National Construction | AP-17 | AP-18 | 17¦18 | tse | C | 0.11966 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-01 | 2025-07-01 | National Construction | AP-16 | AP-17 | 16¦17 | tse | C | 0.10897 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-01 | 2025-07-01 | National Construction | AP-17 | AP-18 | 17¦18 | tse | C | 0.11966 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-02 | 2025-07-01 | National Construction | AP-16 | AP-17 | 16¦17 | tse | C | 0.10897 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-02 | 2025-07-01 | National Construction | AP-17 | AP-18 | 17¦18 | tse | C | 0.11966 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-03 | 2025-07-01 | National Construction | AP-16 | AP-17 | 16¦17 | tse | C | 0.10897 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-03 | 2025-07-01 | National Construction | AP-17 | AP-18 | 17¦18 | tse | C | 0.11966 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-04 | 2025-07-01 | National Construction | AP-16 | AP-17 | 16¦17 | tse | C | 0.10897 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-04 | 2025-07-01 | National Construction | AP-17 | AP-18 | 17¦18 | tse | C | 0.11966 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-05 | 2025-07-01 | National Construction | AP-16 | AP-17 | 16¦17 | tse | C | 0.10897 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-05 | 2025-07-01 | National Construction | AP-17 | AP-18 | 17¦18 | tse | C | 0.11966 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-06 | 2025-07-01 | National Construction | AP-16 | AP-17 | 16¦17 | tse | C | 0.10897 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-06 | 2025-07-01 | National Construction | AP-17 | AP-18 | 17¦18 | tse | C | 0.11966 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-07 | 2025-07-01 | National Construction | AP-16 | AP-17 | 16¦17 | tse | C | 0.10897 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-07 | 2025-07-01 | National Construction | AP-17 | AP-18 | 17¦18 | tse | C | 0.11966 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-08 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-08 | 2025-07-01 | National Construction | AP-16 | AP-17 | 16¦17 | tse | C | 0.10897 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-08 | 2025-07-01 | National Construction | AP-17 | AP-18 | 17¦18 | tse | C | 0.11966 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-09 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-09 | 2025-07-01 | National Construction | AP-16 | AP-17 | 16¦17 | tse | C | 0.10897 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-09 | 2025-07-01 | National Construction | AP-17 | AP-18 | 17¦18 | tse | C | 0.11966 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-10 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-10 | 2025-07-01 | National Construction | AP-16 | AP-17 | 16¦17 | tse | C | 0.10897 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-10 | 2025-07-01 | National Construction | AP-17 | AP-18 | 17¦18 | tse | C | 0.11966 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-11 | 2025-07-01 | Dilruba Bibi | 4/0 | 4/5 | 4/0¦4/5 | tse | C | 0.21663 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-11 | 2025-07-01 | Dilruba Bibi | 4/5 | 4/6 | 4/5¦4/6 | tse | C | 0.043625 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-11 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-11 | 2025-07-01 | National Construction | AP-16 | AP-17 | 16¦17 | tse | C | 0.10897 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-11 | 2025-07-01 | National Construction | AP-17 | AP-18 | 17¦18 | tse | C | 0.11966 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-12 | 2025-07-01 | Dilruba Bibi | 4/0 | 4/5 | 4/0¦4/5 | tse | C | 0.21663 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-12 | 2025-07-01 | Dilruba Bibi | 4/5 | 4/6 | 4/5¦4/6 | tse | C | 0.043625 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-12 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-13 | 2025-07-01 | Dilruba Bibi | 4/0 | 4/5 | 4/0¦4/5 | tse | C | 0.21663 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-13 | 2025-07-01 | Dilruba Bibi | 4/5 | 4/6 | 4/5¦4/6 | tse | C | 0.043625 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-13 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-14 | 2025-07-01 | Dilruba Bibi | 4/0 | 4/5 | 4/0¦4/5 | tse | C | 0.21663 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-14 | 2025-07-01 | Dilruba Bibi | 4/5 | 4/6 | 4/5¦4/6 | tse | C | 0.043625 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-14 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-14 | 2025-07-01 | National Construction | AP-18 | AP-19 | 18¦19 | tse | C | 0.84203 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-15 | 2025-07-01 | Dilruba Bibi | 4/0 | 4/5 | 4/0¦4/5 | tse | C | 0.21663 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-15 | 2025-07-01 | Dilruba Bibi | 4/5 | 4/6 | 4/5¦4/6 | tse | C | 0.043625 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-15 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-15 | 2025-07-01 | National Construction | AP-18 | AP-19 | 18¦19 | tse | C | 0.84203 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-16 | 2025-07-01 | Dilruba Bibi | 4/0 | 4/5 | 4/0¦4/5 | tse | C | 0.21663 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-16 | 2025-07-01 | Dilruba Bibi | 4/5 | 4/6 | 4/5¦4/6 | tse | C | 0.043625 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-16 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-16 | 2025-07-01 | National Construction | AP-18 | AP-19 | 18¦19 | tse | C | 0.84203 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-16 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-17 | 2025-07-01 | Dilruba Bibi | 4/0 | 4/5 | 4/0¦4/5 | tse | C | 0.21663 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-17 | 2025-07-01 | Dilruba Bibi | 4/5 | 4/6 | 4/5¦4/6 | tse | C | 0.043625 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-17 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-17 | 2025-07-01 | National Construction | AP-18 | AP-19 | 18¦19 | tse | C | 0.84203 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-17 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-18 | 2025-07-01 | Dilruba Bibi | 4/0 | 4/5 | 4/0¦4/5 | tse | C | 0.21663 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-18 | 2025-07-01 | Dilruba Bibi | 4/5 | 4/6 | 4/5¦4/6 | tse | C | 0.043625 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-18 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-18 | 2025-07-01 | National Construction | AP-18 | AP-19 | 18¦19 | tse | C | 0.84203 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-18 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-19 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-19 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-20 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-20 | 2025-07-01 | National Construction | AP-19 | AP-20 | 19¦20 | tse | C | 0.64885 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-20 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-21 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-21 | 2025-07-01 | National Construction | AP-19 | AP-20 | 19¦20 | tse | C | 0.64885 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-21 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-22 | 2025-07-01 | Kohinoor | AP-30 | AP-31 | 30¦31 | tse | C | 0.15553 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-22 | 2025-07-01 | National Construction | AP-19 | AP-20 | 19¦20 | tse | C | 0.64885 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-22 | 2025-07-01 | National Construction | AP-20 | AP-21 | 20¦21 | tse | C | 0.49913 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-22 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-23 | 2025-07-01 | National Construction | AP-20 | AP-21 | 20¦21 | tse | C | 0.49913 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-23 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-24 | 2025-07-01 | National Construction | AP-20 | AP-21 | 20¦21 | tse | C | 0.49913 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-24 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-25 | 2025-07-01 | National Construction | AP-20 | AP-21 | 20¦21 | tse | C | 0.49913 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-25 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-26 | 2025-07-01 | Dilruba Bibi | 1E/0 | 2/0 | 1E/0¦2/0 | tse | C | 0.039633 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-26 | 2025-07-01 | National Construction | AP-20 | AP-21 | 20¦21 | tse | C | 0.49913 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-26 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-27 | 2025-07-01 | Dilruba Bibi | 1E/0 | 2/0 | 1E/0¦2/0 | tse | C | 0.039633 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-27 | 2025-07-01 | National Construction | AP-20 | AP-21 | 20¦21 | tse | C | 0.49913 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-27 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-28 | 2025-07-01 | Dilruba Bibi | 1E/0 | 2/0 | 1E/0¦2/0 | tse | C | 0.039633 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-28 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-29 | 2025-07-01 | Dilruba Bibi | 1E/0 | 2/0 | 1E/0¦2/0 | tse | C | 0.039633 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-29 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-30 | 2025-07-01 | Dilruba Bibi | 1E/0 | 2/0 | 1E/0¦2/0 | tse | C | 0.039633 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-30 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-31 | 2025-07-01 | Dilruba Bibi | 1E/0 | 2/0 | 1E/0¦2/0 | tse | C | 0.039633 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-07-31 | 2025-07-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-01 | 2025-08-01 | Dilruba Bibi | 1D/0 | 1E/0 | 1D/0¦1E/0 | tse | C | 0.099989 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-01 | 2025-08-01 | Dilruba Bibi | 1E/0 | 2/0 | 1E/0¦2/0 | tse | C | 0.039633 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-01 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-02 | 2025-08-01 | Dilruba Bibi | 1D/0 | 1E/0 | 1D/0¦1E/0 | tse | C | 0.099989 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-02 | 2025-08-01 | Dilruba Bibi | 1E/0 | 2/0 | 1E/0¦2/0 | tse | C | 0.039633 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-02 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-03 | 2025-08-01 | Dilruba Bibi | 1D/0 | 1E/0 | 1D/0¦1E/0 | tse | C | 0.099989 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-03 | 2025-08-01 | Dilruba Bibi | 1E/0 | 2/0 | 1E/0¦2/0 | tse | C | 0.039633 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-03 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-04 | 2025-08-01 | Dilruba Bibi | 1D/0 | 1E/0 | 1D/0¦1E/0 | tse | C | 0.099989 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-04 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-04 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-05 | 2025-08-01 | Dilruba Bibi | 1D/0 | 1E/0 | 1D/0¦1E/0 | tse | C | 0.099989 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-05 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-05 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-06 | 2025-08-01 | Dilruba Bibi | 1D/0 | 1E/0 | 1D/0¦1E/0 | tse | C | 0.099989 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-06 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-06 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-07 | 2025-08-01 | Dilruba Bibi | 1D/0 | 1E/0 | 1D/0¦1E/0 | tse | C | 0.099989 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-07 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-07 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-08 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-08 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-08 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-09 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-09 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-09 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-10 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-10 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-10 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-11 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-11 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-11 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-12 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-12 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-12 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-13 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-13 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-13 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-14 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-14 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-14 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-15 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-15 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-15 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-16 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-16 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-16 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-17 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-17 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-17 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-18 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-18 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-18 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-19 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-19 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-19 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-20 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-20 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-20 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-21 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-21 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-21 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-22 | 2025-08-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-22 | 2025-08-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-22 | 2025-08-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-22 | 2025-08-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-22 | 2025-08-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-22 | 2025-08-01 | National Construction | AP-21 | AP-22 | 21¦22 | tse | C | 0.26183 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-22 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-22 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-23 | 2025-08-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-23 | 2025-08-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-23 | 2025-08-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-23 | 2025-08-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-23 | 2025-08-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-23 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-23 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-24 | 2025-08-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-24 | 2025-08-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-24 | 2025-08-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-24 | 2025-08-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-24 | 2025-08-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-24 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-24 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-25 | 2025-08-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-25 | 2025-08-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-25 | 2025-08-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-25 | 2025-08-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-25 | 2025-08-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-25 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-25 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-26 | 2025-08-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-26 | 2025-08-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-26 | 2025-08-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-26 | 2025-08-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-26 | 2025-08-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-26 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-26 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-27 | 2025-08-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-27 | 2025-08-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-27 | 2025-08-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-27 | 2025-08-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-27 | 2025-08-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-27 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-27 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-28 | 2025-08-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-28 | 2025-08-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-28 | 2025-08-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-28 | 2025-08-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-28 | 2025-08-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-28 | 2025-08-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-28 | 2025-08-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-28 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-28 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-29 | 2025-08-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-29 | 2025-08-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-29 | 2025-08-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-29 | 2025-08-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-29 | 2025-08-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-29 | 2025-08-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-29 | 2025-08-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-29 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-29 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-30 | 2025-08-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-30 | 2025-08-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-30 | 2025-08-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-30 | 2025-08-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-30 | 2025-08-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-30 | 2025-08-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-30 | 2025-08-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-30 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-30 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-31 | 2025-08-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-31 | 2025-08-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-31 | 2025-08-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-31 | 2025-08-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-31 | 2025-08-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-31 | 2025-08-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-31 | 2025-08-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-31 | 2025-08-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-08-31 | 2025-08-01 | National Construction | 29A/0 | AP-30 | 29A/0¦30 | tse | C | 0.039587 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-01 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-01 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-01 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-01 | 2025-09-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-01 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-01 | 2025-09-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-01 | 2025-09-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-01 | 2025-09-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-02 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-02 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-02 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-02 | 2025-09-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-02 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-02 | 2025-09-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-02 | 2025-09-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-02 | 2025-09-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-03 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-03 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-03 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-03 | 2025-09-01 | National Construction | 4/15 | 4/16 | 4/15¦4/16 | tse | C | 0.031923 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-03 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-03 | 2025-09-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-03 | 2025-09-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-03 | 2025-09-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-04 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-04 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-04 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-04 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-04 | 2025-09-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-04 | 2025-09-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-04 | 2025-09-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-04 | 2025-09-01 | National Construction | AP-23 | AP-24 | 23¦24 | tse | C | 0.38535 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-05 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-05 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-05 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-05 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-05 | 2025-09-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-05 | 2025-09-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-05 | 2025-09-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-05 | 2025-09-01 | National Construction | AP-23 | AP-24 | 23¦24 | tse | C | 0.38535 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-06 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-06 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-06 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-06 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-06 | 2025-09-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-06 | 2025-09-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-06 | 2025-09-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-06 | 2025-09-01 | National Construction | AP-23 | AP-24 | 23¦24 | tse | C | 0.38535 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-07 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-07 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-07 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-07 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-07 | 2025-09-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-07 | 2025-09-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-07 | 2025-09-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-07 | 2025-09-01 | National Construction | AP-23 | AP-24 | 23¦24 | tse | C | 0.38535 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-08 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-08 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-08 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-08 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-08 | 2025-09-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-08 | 2025-09-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-08 | 2025-09-01 | National Construction | AP-22 | AP-23 | 22¦23 | tse | C | 0.029601 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-08 | 2025-09-01 | National Construction | AP-23 | AP-24 | 23¦24 | tse | C | 0.38535 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-09 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-09 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-09 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-09 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-09 | 2025-09-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-09 | 2025-09-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-10 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-10 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-10 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-10 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-10 | 2025-09-01 | National Construction | 4/17 | 5/0 | 4/17¦5/0 | tse | C | 0.013464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-10 | 2025-09-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-11 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-11 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-11 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-11 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-11 | 2025-09-01 | National Construction | 5/0 | 5/1 | 5/0¦5/1 | tse | C | 0.025533 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-12 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-12 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-12 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-12 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-13 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-13 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-13 | 2025-09-01 | National Construction | 4/11 | 4/15 | 4/11¦4/15 | tse | C | 0.058043 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-13 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-13 | 2025-09-01 | National Construction | AP-25 | AP-26 | 25¦26 | tse | C | 0.044575 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-14 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-14 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-14 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-14 | 2025-09-01 | National Construction | AP-25 | AP-26 | 25¦26 | tse | C | 0.044575 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-15 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-15 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-15 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-15 | 2025-09-01 | National Construction | AP-25 | AP-26 | 25¦26 | tse | C | 0.044575 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-15 | 2025-09-01 | National Construction | AP-29 | 29A/0 | 29¦29A/0 | tse | C | 0.17225 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-16 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-16 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-16 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-16 | 2025-09-01 | National Construction | AP-25 | AP-26 | 25¦26 | tse | C | 0.044575 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-16 | 2025-09-01 | National Construction | 28/2 | AP-29 | 28/2¦29 | tse | C | 0.020943 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-16 | 2025-09-01 | National Construction | AP-29 | 29A/0 | 29¦29A/0 | tse | C | 0.17225 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-17 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-17 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-17 | 2025-09-01 | National Construction | 4/16 | 4/17 | 4/16¦4/17 | tse | C | 0.0087778 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-17 | 2025-09-01 | National Construction | 28/2 | AP-29 | 28/2¦29 | tse | C | 0.020943 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-18 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-18 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-19 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-19 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-20 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-20 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-21 | 2025-09-01 | National Construction | 4/9 | 4/10 | 4/10¦4/9 | tse | C | 0.011984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-21 | 2025-09-01 | National Construction | 4/10 | 4/11 | 4/10¦4/11 | tse | C | 0.010725 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-22 | 2025-09-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.19202 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-23 | 2025-09-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.19202 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-24 | 2025-09-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.19202 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-25 | 2025-09-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.19202 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-26 | 2025-09-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.19202 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-26 | 2025-09-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-27 | 2025-09-01 | National Construction | 7/0 | 8/0 | 7/0¦8/0 | tse | C | 0.19202 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-27 | 2025-09-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-28 | 2025-09-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-29 | 2025-09-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-09-30 | 2025-09-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-01 | 2025-10-01 | National Construction | 8/0 | 8A/0 | 8/0¦8A/0 | tse | C | 0.03414 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-01 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-01 | 2025-10-01 | National Construction | AP-12 | AP-13 | 12¦13 | tse | C | 0.035628 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-02 | 2025-10-01 | National Construction | 8/0 | 8A/0 | 8/0¦8A/0 | tse | C | 0.03414 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-02 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-02 | 2025-10-01 | National Construction | AP-12 | AP-13 | 12¦13 | tse | C | 0.035628 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-03 | 2025-10-01 | National Construction | 8/0 | 8A/0 | 8/0¦8A/0 | tse | C | 0.03414 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-03 | 2025-10-01 | National Construction | 8A/0 | 8B/0 | 8A/0¦8B/0 | tse | C | 0.048071 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-03 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-03 | 2025-10-01 | National Construction | AP-12 | AP-13 | 12¦13 | tse | C | 0.035628 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-04 | 2025-10-01 | National Construction | 8/0 | 8A/0 | 8/0¦8A/0 | tse | C | 0.03414 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-04 | 2025-10-01 | National Construction | 8A/0 | 8B/0 | 8A/0¦8B/0 | tse | C | 0.048071 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-04 | 2025-10-01 | National Construction | 8B/0 | 8C/0 | 8B/0¦8C/0 | tse | C | 0.15002 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-04 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-04 | 2025-10-01 | National Construction | AP-12 | AP-13 | 12¦13 | tse | C | 0.035628 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-04 | 2025-10-01 | National Construction | AP-24 | AP-25 | 24¦25 | tse | C | 0.19052 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-05 | 2025-10-01 | National Construction | 8/0 | 8A/0 | 8/0¦8A/0 | tse | C | 0.03414 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-05 | 2025-10-01 | National Construction | 8A/0 | 8B/0 | 8A/0¦8B/0 | tse | C | 0.048071 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-05 | 2025-10-01 | National Construction | 8B/0 | 8C/0 | 8B/0¦8C/0 | tse | C | 0.15002 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-05 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-05 | 2025-10-01 | National Construction | AP-12 | AP-13 | 12¦13 | tse | C | 0.035628 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-06 | 2025-10-01 | National Construction | 8A/0 | 8B/0 | 8A/0¦8B/0 | tse | C | 0.048071 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-06 | 2025-10-01 | National Construction | 8B/0 | 8C/0 | 8B/0¦8C/0 | tse | C | 0.15002 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-06 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-06 | 2025-10-01 | National Construction | AP-12 | AP-13 | 12¦13 | tse | C | 0.035628 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-06 | 2025-10-01 | National Construction | AP-26 | AP-27 | 26¦27 | tse | C | 0.1484 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-07 | 2025-10-01 | National Construction | 8A/0 | 8B/0 | 8A/0¦8B/0 | tse | C | 0.048071 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-07 | 2025-10-01 | National Construction | 8B/0 | 8C/0 | 8B/0¦8C/0 | tse | C | 0.15002 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-07 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-07 | 2025-10-01 | National Construction | AP-12 | AP-13 | 12¦13 | tse | C | 0.035628 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-08 | 2025-10-01 | National Construction | 8A/0 | 8B/0 | 8A/0¦8B/0 | tse | C | 0.048071 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-08 | 2025-10-01 | National Construction | 8B/0 | 8C/0 | 8B/0¦8C/0 | tse | C | 0.15002 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-08 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-08 | 2025-10-01 | National Construction | AP-12 | AP-13 | 12¦13 | tse | C | 0.035628 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-09 | 2025-10-01 | National Construction | 8A/0 | 8B/0 | 8A/0¦8B/0 | tse | C | 0.048071 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-09 | 2025-10-01 | National Construction | 8B/0 | 8C/0 | 8B/0¦8C/0 | tse | C | 0.15002 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-09 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-09 | 2025-10-01 | National Construction | AP-12 | AP-13 | 12¦13 | tse | C | 0.035628 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-10 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-10 | 2025-10-01 | National Construction | AP-10 | AP-11 | 10¦11 | tse | C | 0.32002 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-10 | 2025-10-01 | National Construction | AP-11 | AP-12 | 11¦12 | tse | C | 0.10518 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-10 | 2025-10-01 | National Construction | AP-12 | AP-13 | 12¦13 | tse | C | 0.035628 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-11 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-11 | 2025-10-01 | National Construction | AP-10 | AP-11 | 10¦11 | tse | C | 0.32002 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-11 | 2025-10-01 | National Construction | AP-11 | AP-12 | 11¦12 | tse | C | 0.10518 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-12 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-12 | 2025-10-01 | National Construction | AP-10 | AP-11 | 10¦11 | tse | C | 0.32002 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-12 | 2025-10-01 | National Construction | AP-11 | AP-12 | 11¦12 | tse | C | 0.10518 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-13 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-13 | 2025-10-01 | National Construction | AP-10 | AP-11 | 10¦11 | tse | C | 0.32002 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-13 | 2025-10-01 | National Construction | AP-11 | AP-12 | 11¦12 | tse | C | 0.10518 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-14 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-14 | 2025-10-01 | National Construction | AP-10 | AP-11 | 10¦11 | tse | C | 0.32002 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-14 | 2025-10-01 | National Construction | AP-11 | AP-12 | 11¦12 | tse | C | 0.10518 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-15 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-16 | 2025-10-01 | National Construction | 5/1 | 5A/0 | 5/1¦5A/0 | tse | C | 0.238 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-16 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-17 | 2025-10-01 | National Construction | 5/1 | 5A/0 | 5/1¦5A/0 | tse | C | 0.238 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-17 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-18 | 2025-10-01 | National Construction | 5/1 | 5A/0 | 5/1¦5A/0 | tse | C | 0.238 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-18 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-19 | 2025-10-01 | National Construction | 5/1 | 5A/0 | 5/1¦5A/0 | tse | C | 0.238 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-19 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-20 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-21 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-22 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-23 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-24 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-25 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-26 | 2025-10-01 | National Construction | 9/4 | 9/5 | 9/4¦9/5 | tse | C | 0.0617 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-26 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-27 | 2025-10-01 | National Construction | 9/4 | 9/5 | 9/4¦9/5 | tse | C | 0.0617 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-27 | 2025-10-01 | National Construction | 9/5 | AP-10 | 10¦9/5 | tse | C | 0.053041 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-28 | 2025-10-01 | National Construction | 9/4 | 9/5 | 9/4¦9/5 | tse | C | 0.0617 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-10-29 | 2025-10-01 | National Construction | 9/4 | 9/5 | 9/4¦9/5 | tse | C | 0.0617 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-02 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-02 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-02 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-03 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-03 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-03 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-04 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-04 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-04 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-05 | 2025-11-01 | National Construction | 8E/11 | 8E/12 | 8E/11¦8E/12 | tse | C | 0.054333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-05 | 2025-11-01 | National Construction | 8E/12 | AP-9 | 8E/12¦9 | tse | C | 0.05464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-05 | 2025-11-01 | National Construction | AP-9 | 9/4 | 9¦9/4 | tse | C | 0.17862 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-05 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-05 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-05 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-06 | 2025-11-01 | National Construction | 8E/11 | 8E/12 | 8E/11¦8E/12 | tse | C | 0.054333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-06 | 2025-11-01 | National Construction | 8E/12 | AP-9 | 8E/12¦9 | tse | C | 0.05464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-06 | 2025-11-01 | National Construction | AP-9 | 9/4 | 9¦9/4 | tse | C | 0.17862 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-06 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-06 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-06 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-07 | 2025-11-01 | National Construction | 8E/11 | 8E/12 | 8E/11¦8E/12 | tse | C | 0.054333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-07 | 2025-11-01 | National Construction | 8E/12 | AP-9 | 8E/12¦9 | tse | C | 0.05464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-07 | 2025-11-01 | National Construction | AP-9 | 9/4 | 9¦9/4 | tse | C | 0.17862 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-07 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-07 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-07 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-08 | 2025-11-01 | National Construction | 8E/11 | 8E/12 | 8E/11¦8E/12 | tse | C | 0.054333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-08 | 2025-11-01 | National Construction | 8E/12 | AP-9 | 8E/12¦9 | tse | C | 0.05464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-08 | 2025-11-01 | National Construction | AP-9 | 9/4 | 9¦9/4 | tse | C | 0.17862 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-08 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-08 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-08 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-09 | 2025-11-01 | National Construction | 8E/11 | 8E/12 | 8E/11¦8E/12 | tse | C | 0.054333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-09 | 2025-11-01 | National Construction | 8E/12 | AP-9 | 8E/12¦9 | tse | C | 0.05464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-09 | 2025-11-01 | National Construction | AP-9 | 9/4 | 9¦9/4 | tse | C | 0.17862 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-09 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-09 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-09 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-10 | 2025-11-01 | National Construction | 8E/11 | 8E/12 | 8E/11¦8E/12 | tse | C | 0.054333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-10 | 2025-11-01 | National Construction | 8E/12 | AP-9 | 8E/12¦9 | tse | C | 0.05464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-10 | 2025-11-01 | National Construction | AP-9 | 9/4 | 9¦9/4 | tse | C | 0.17862 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-10 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-10 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-10 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-11 | 2025-11-01 | National Construction | 8E/1 | 8E/2 | 8E/1¦8E/2 | tse | C | 0.052375 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-11 | 2025-11-01 | National Construction | 8E/2 | 8E/5 | 8E/2¦8E/5 | tse | C | 0.1125 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-11 | 2025-11-01 | National Construction | 8E/5 | 8E/6 | 8E/5¦8E/6 | tse | C | 0.042984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-11 | 2025-11-01 | National Construction | 8E/11 | 8E/12 | 8E/11¦8E/12 | tse | C | 0.054333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-11 | 2025-11-01 | National Construction | 8E/12 | AP-9 | 8E/12¦9 | tse | C | 0.05464 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-11 | 2025-11-01 | National Construction | AP-9 | 9/4 | 9¦9/4 | tse | C | 0.17862 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-11 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-11 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-11 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-12 | 2025-11-01 | National Construction | 8E/1 | 8E/2 | 8E/1¦8E/2 | tse | C | 0.052375 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-12 | 2025-11-01 | National Construction | 8E/2 | 8E/5 | 8E/2¦8E/5 | tse | C | 0.1125 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-12 | 2025-11-01 | National Construction | 8E/5 | 8E/6 | 8E/5¦8E/6 | tse | C | 0.042984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-12 | 2025-11-01 | National Construction | 8E/11 | 8E/12 | 8E/11¦8E/12 | tse | C | 0.054333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-12 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-12 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-12 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-13 | 2025-11-01 | National Construction | 8E/1 | 8E/2 | 8E/1¦8E/2 | tse | C | 0.052375 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-13 | 2025-11-01 | National Construction | 8E/2 | 8E/5 | 8E/2¦8E/5 | tse | C | 0.1125 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-13 | 2025-11-01 | National Construction | 8E/5 | 8E/6 | 8E/5¦8E/6 | tse | C | 0.042984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-13 | 2025-11-01 | National Construction | 8E/11 | 8E/12 | 8E/11¦8E/12 | tse | C | 0.054333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-13 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-13 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-13 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-14 | 2025-11-01 | National Construction | 8E/1 | 8E/2 | 8E/1¦8E/2 | tse | C | 0.052375 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-14 | 2025-11-01 | National Construction | 8E/2 | 8E/5 | 8E/2¦8E/5 | tse | C | 0.1125 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-14 | 2025-11-01 | National Construction | 8E/5 | 8E/6 | 8E/5¦8E/6 | tse | C | 0.042984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-14 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-14 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-14 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-15 | 2025-11-01 | National Construction | 8E/1 | 8E/2 | 8E/1¦8E/2 | tse | C | 0.052375 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-15 | 2025-11-01 | National Construction | 8E/2 | 8E/5 | 8E/2¦8E/5 | tse | C | 0.1125 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-15 | 2025-11-01 | National Construction | 8E/5 | 8E/6 | 8E/5¦8E/6 | tse | C | 0.042984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-15 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-15 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-15 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-16 | 2025-11-01 | National Construction | 8E/1 | 8E/2 | 8E/1¦8E/2 | tse | C | 0.052375 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-16 | 2025-11-01 | National Construction | 8E/2 | 8E/5 | 8E/2¦8E/5 | tse | C | 0.1125 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-16 | 2025-11-01 | National Construction | 8E/5 | 8E/6 | 8E/5¦8E/6 | tse | C | 0.042984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-16 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-16 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-16 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-17 | 2025-11-01 | National Construction | 8E/1 | 8E/2 | 8E/1¦8E/2 | tse | C | 0.052375 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-17 | 2025-11-01 | National Construction | 8E/2 | 8E/5 | 8E/2¦8E/5 | tse | C | 0.1125 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-17 | 2025-11-01 | National Construction | 8E/5 | 8E/6 | 8E/5¦8E/6 | tse | C | 0.042984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-17 | 2025-11-01 | National Construction | 8E/8 | 8E/11 | 8E/11¦8E/8 | tse | C | 0.13129 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-17 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-17 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-17 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-18 | 2025-11-01 | National Construction | 8E/1 | 8E/2 | 8E/1¦8E/2 | tse | C | 0.052375 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-18 | 2025-11-01 | National Construction | 8E/2 | 8E/5 | 8E/2¦8E/5 | tse | C | 0.1125 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-18 | 2025-11-01 | National Construction | 8E/5 | 8E/6 | 8E/5¦8E/6 | tse | C | 0.042984 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-18 | 2025-11-01 | National Construction | 8E/8 | 8E/11 | 8E/11¦8E/8 | tse | C | 0.13129 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-18 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-18 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-18 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-19 | 2025-11-01 | National Construction | 8E/8 | 8E/11 | 8E/11¦8E/8 | tse | C | 0.13129 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-19 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-19 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-19 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-20 | 2025-11-01 | National Construction | 8E/8 | 8E/11 | 8E/11¦8E/8 | tse | C | 0.13129 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-20 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-20 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-20 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-21 | 2025-11-01 | National Construction | 8E/8 | 8E/11 | 8E/11¦8E/8 | tse | C | 0.13129 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-21 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-21 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-21 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-22 | 2025-11-01 | National Construction | 8E/8 | 8E/11 | 8E/11¦8E/8 | tse | C | 0.13129 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-22 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-22 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-22 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-23 | 2025-11-01 | National Construction | 8E/8 | 8E/11 | 8E/11¦8E/8 | tse | C | 0.13129 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-23 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-23 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-23 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-24 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-24 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-24 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-25 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-25 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-25 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-26 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-26 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-26 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-27 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-27 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-27 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-28 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-28 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-28 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-29 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-29 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-29 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-30 | 2025-11-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-30 | 2025-11-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-11-30 | 2025-11-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-01 | 2025-12-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-01 | 2025-12-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-01 | 2025-12-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-02 | 2025-12-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-02 | 2025-12-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-02 | 2025-12-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-03 | 2025-12-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-03 | 2025-12-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-03 | 2025-12-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-04 | 2025-12-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-04 | 2025-12-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-04 | 2025-12-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-05 | 2025-12-01 | National Construction | AP-27 | AP-28 | 27¦28 | tse | C | 0.0018 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-05 | 2025-12-01 | National Construction | AP-28 | 28/1 | 28¦28/1 | tse | C | 0.0012431 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-05 | 2025-12-01 | National Construction | 28/1 | 28/2 | 28/1¦28/2 | tse | C | 0.0016051 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-13 | 2025-12-01 | National Construction | 14/3 | AP-15 | 14/3¦15 | tse | C | 0.23056 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-14 | 2025-12-01 | National Construction | 14/3 | AP-15 | 14/3¦15 | tse | C | 0.23056 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-15 | 2025-12-01 | National Construction | 14/3 | AP-15 | 14/3¦15 | tse | C | 0.23056 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-16 | 2025-12-01 | National Construction | 14/3 | AP-15 | 14/3¦15 | tse | C | 0.23056 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-17 | 2025-12-01 | National Construction | 14/3 | AP-15 | 14/3¦15 | tse | C | 0.23056 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-18 | 2025-12-01 | National Construction | AP-13 | AP-14 | 13¦14 | tse | C | 0.066759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-18 | 2025-12-01 | National Construction | AP-14 | 14/1 | 14¦14/1 | tse | C | 0.0362 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-18 | 2025-12-01 | National Construction | 14/1 | 14/3 | 14/1¦14/3 | tse | C | 0.0752 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-18 | 2025-12-01 | National Construction | 14/3 | AP-15 | 14/3¦15 | tse | C | 0.23056 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-19 | 2025-12-01 | National Construction | AP-13 | AP-14 | 13¦14 | tse | C | 0.066759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-19 | 2025-12-01 | National Construction | AP-14 | 14/1 | 14¦14/1 | tse | C | 0.0362 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-19 | 2025-12-01 | National Construction | 14/1 | 14/3 | 14/1¦14/3 | tse | C | 0.0752 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-19 | 2025-12-01 | National Construction | 14/3 | AP-15 | 14/3¦15 | tse | C | 0.23056 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-20 | 2025-12-01 | National Construction | AP-13 | AP-14 | 13¦14 | tse | C | 0.066759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-20 | 2025-12-01 | National Construction | AP-14 | 14/1 | 14¦14/1 | tse | C | 0.0362 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-20 | 2025-12-01 | National Construction | 14/1 | 14/3 | 14/1¦14/3 | tse | C | 0.0752 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-20 | 2025-12-01 | National Construction | 14/3 | AP-15 | 14/3¦15 | tse | C | 0.23056 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-21 | 2025-12-01 | National Construction | AP-13 | AP-14 | 13¦14 | tse | C | 0.066759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-21 | 2025-12-01 | National Construction | AP-14 | 14/1 | 14¦14/1 | tse | C | 0.0362 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-21 | 2025-12-01 | National Construction | 14/1 | 14/3 | 14/1¦14/3 | tse | C | 0.0752 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-21 | 2025-12-01 | National Construction | 14/3 | AP-15 | 14/3¦15 | tse | C | 0.23056 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-22 | 2025-12-01 | National Construction | AP-13 | AP-14 | 13¦14 | tse | C | 0.066759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-22 | 2025-12-01 | National Construction | AP-14 | 14/1 | 14¦14/1 | tse | C | 0.0362 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-22 | 2025-12-01 | National Construction | 14/1 | 14/3 | 14/1¦14/3 | tse | C | 0.0752 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-22 | 2025-12-01 | National Construction | 14/3 | AP-15 | 14/3¦15 | tse | C | 0.23056 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-23 | 2025-12-01 | National Construction | AP-13 | AP-14 | 13¦14 | tse | C | 0.066759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-23 | 2025-12-01 | National Construction | AP-14 | 14/1 | 14¦14/1 | tse | C | 0.0362 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-23 | 2025-12-01 | National Construction | 14/1 | 14/3 | 14/1¦14/3 | tse | C | 0.0752 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-23 | 2025-12-01 | National Construction | 14/3 | AP-15 | 14/3¦15 | tse | C | 0.23056 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-24 | 2025-12-01 | National Construction | AP-13 | AP-14 | 13¦14 | tse | C | 0.066759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-24 | 2025-12-01 | National Construction | AP-14 | 14/1 | 14¦14/1 | tse | C | 0.0362 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-24 | 2025-12-01 | National Construction | 14/1 | 14/3 | 14/1¦14/3 | tse | C | 0.0752 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-25 | 2025-12-01 | National Construction | AP-13 | AP-14 | 13¦14 | tse | C | 0.066759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-25 | 2025-12-01 | National Construction | AP-14 | 14/1 | 14¦14/1 | tse | C | 0.0362 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-25 | 2025-12-01 | National Construction | 14/1 | 14/3 | 14/1¦14/3 | tse | C | 0.0752 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-26 | 2025-12-01 | National Construction | AP-13 | AP-14 | 13¦14 | tse | C | 0.066759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-26 | 2025-12-01 | National Construction | AP-14 | 14/1 | 14¦14/1 | tse | C | 0.0362 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-26 | 2025-12-01 | National Construction | 14/1 | 14/3 | 14/1¦14/3 | tse | C | 0.0752 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-27 | 2025-12-01 | National Construction | AP-13 | AP-14 | 13¦14 | tse | C | 0.066759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-27 | 2025-12-01 | National Construction | AP-14 | 14/1 | 14¦14/1 | tse | C | 0.0362 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2025-12-27 | 2025-12-01 | National Construction | 14/1 | 14/3 | 14/1¦14/3 | tse | C | 0.0752 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-01-28 | 2026-01-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-01-28 | 2026-01-01 | National Construction | 6/0 | 7/0 | 6/0¦7/0 | tse | C | 0.031804 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-01-29 | 2026-01-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-01-29 | 2026-01-01 | National Construction | 6/0 | 7/0 | 6/0¦7/0 | tse | C | 0.031804 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-01-30 | 2026-01-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-01-30 | 2026-01-01 | National Construction | 6/0 | 7/0 | 6/0¦7/0 | tse | C | 0.031804 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-01-31 | 2026-01-01 | Harshvivek | Gnty | 0/0 | 0/0¦GNTY | tse | C | 0.015667 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-01-31 | 2026-01-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-01-31 | 2026-01-01 | National Construction | 6/0 | 7/0 | 6/0¦7/0 | tse | C | 0.031804 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-01 | 2026-02-01 | Harshvivek | Gnty | 0/0 | 0/0¦GNTY | tse | C | 0.015667 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-01 | 2026-02-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-01 | 2026-02-01 | National Construction | 6/0 | 7/0 | 6/0¦7/0 | tse | C | 0.031804 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-02 | 2026-02-01 | Harshvivek | Gnty | 0/0 | 0/0¦GNTY | tse | C | 0.015667 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-02 | 2026-02-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-02 | 2026-02-01 | National Construction | 6/0 | 7/0 | 6/0¦7/0 | tse | C | 0.031804 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-03 | 2026-02-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-03 | 2026-02-01 | National Construction | 6/0 | 7/0 | 6/0¦7/0 | tse | C | 0.031804 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-04 | 2026-02-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-04 | 2026-02-01 | National Construction | 6/0 | 7/0 | 6/0¦7/0 | tse | C | 0.031804 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-05 | 2026-02-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-05 | 2026-02-01 | National Construction | 6/0 | 7/0 | 6/0¦7/0 | tse | C | 0.031804 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-06 | 2026-02-01 | National Construction | 5A/2 | 5B/0 | 5A/2¦5B/0 | tse | C | 0.056548 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-06 | 2026-02-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-06 | 2026-02-01 | National Construction | 6/0 | 7/0 | 6/0¦7/0 | tse | C | 0.031804 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-07 | 2026-02-01 | National Construction | 5A/2 | 5B/0 | 5A/2¦5B/0 | tse | C | 0.056548 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-07 | 2026-02-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-08 | 2026-02-01 | National Construction | 5A/2 | 5B/0 | 5A/2¦5B/0 | tse | C | 0.056548 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-08 | 2026-02-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-09 | 2026-02-01 | National Construction | 5A/1 | 5A/2 | 5A/1¦5A/2 | tse | C | 0.037714 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-09 | 2026-02-01 | National Construction | 5A/2 | 5B/0 | 5A/2¦5B/0 | tse | C | 0.056548 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-09 | 2026-02-01 | National Construction | 5B/0 | 6/0 | 5B/0¦6/0 | tse | C | 0.035546 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-10 | 2026-02-01 | National Construction | 5A/0 | 5A/1 | 5A/0¦5A/1 | tse | C | 0.0684 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-10 | 2026-02-01 | National Construction | 5A/1 | 5A/2 | 5A/1¦5A/2 | tse | C | 0.037714 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-10 | 2026-02-01 | National Construction | 5A/2 | 5B/0 | 5A/2¦5B/0 | tse | C | 0.056548 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-11 | 2026-02-01 | National Construction | 5A/0 | 5A/1 | 5A/0¦5A/1 | tse | C | 0.0684 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-11 | 2026-02-01 | National Construction | 5A/1 | 5A/2 | 5A/1¦5A/2 | tse | C | 0.037714 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-12 | 2026-02-01 | National Construction | 5A/0 | 5A/1 | 5A/0¦5A/1 | tse | C | 0.0684 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-12 | 2026-02-01 | National Construction | 5A/1 | 5A/2 | 5A/1¦5A/2 | tse | C | 0.037714 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-13 | 2026-02-01 | National Construction | 5A/0 | 5A/1 | 5A/0¦5A/1 | tse | C | 0.0684 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-13 | 2026-02-01 | National Construction | 5A/1 | 5A/2 | 5A/1¦5A/2 | tse | C | 0.037714 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-14 | 2026-02-01 | National Construction | 5A/0 | 5A/1 | 5A/0¦5A/1 | tse | C | 0.0684 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-14 | 2026-02-01 | National Construction | 5A/1 | 5A/2 | 5A/1¦5A/2 | tse | C | 0.037714 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-15 | 2026-02-01 | National Construction | 5A/1 | 5A/2 | 5A/1¦5A/2 | tse | C | 0.037714 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-15 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-15 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-15 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-15 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-15 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-16 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-16 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-16 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-16 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-16 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-17 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-17 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-17 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-17 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-17 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-18 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-18 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-18 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-18 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-18 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-19 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-19 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-19 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-19 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-19 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-20 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-20 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-20 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-20 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-20 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-20 | 2026-02-01 | National Construction | 8E/6 | 8E/7 | 8E/6¦8E/7 | tse | C | 0.099826 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-20 | 2026-02-01 | National Construction | 8E/7 | 8E/8 | 8E/7¦8E/8 | tse | C | 0.072333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-21 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-21 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-21 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-21 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-21 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-21 | 2026-02-01 | National Construction | 8E/6 | 8E/7 | 8E/6¦8E/7 | tse | C | 0.099826 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-21 | 2026-02-01 | National Construction | 8E/7 | 8E/8 | 8E/7¦8E/8 | tse | C | 0.072333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-22 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-22 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-22 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-22 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-22 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-22 | 2026-02-01 | National Construction | 8E/6 | 8E/7 | 8E/6¦8E/7 | tse | C | 0.099826 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-22 | 2026-02-01 | National Construction | 8E/7 | 8E/8 | 8E/7¦8E/8 | tse | C | 0.072333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-23 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-23 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-23 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-23 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-23 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-23 | 2026-02-01 | National Construction | 8E/6 | 8E/7 | 8E/6¦8E/7 | tse | C | 0.099826 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-23 | 2026-02-01 | National Construction | 8E/7 | 8E/8 | 8E/7¦8E/8 | tse | C | 0.072333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-24 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-24 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-24 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-24 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-24 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-24 | 2026-02-01 | National Construction | 8E/6 | 8E/7 | 8E/6¦8E/7 | tse | C | 0.099826 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-24 | 2026-02-01 | National Construction | 8E/7 | 8E/8 | 8E/7¦8E/8 | tse | C | 0.072333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-25 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-25 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-25 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-25 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-25 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-25 | 2026-02-01 | National Construction | 8E/7 | 8E/8 | 8E/7¦8E/8 | tse | C | 0.072333 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-26 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-26 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-26 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-26 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-26 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-27 | 2026-02-01 | National Construction | 8D/3 | 8D/4 | 8D/3¦8D/4 | tse | C | 0.035308 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-27 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-27 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-27 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-27 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-28 | 2026-02-01 | National Construction | 8D/4 | 8D/5 | 8D/4¦8D/5 | tse | C | 0.013929 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-28 | 2026-02-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-28 | 2026-02-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-02-28 | 2026-02-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-01 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-01 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-01 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-02 | 2026-03-01 | National Construction | 8D/1 | 8D/3 | 8D/1¦8D/3 | tse | C | 0.082135 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-02 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-02 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-02 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-03 | 2026-03-01 | National Construction | 8D/1 | 8D/3 | 8D/1¦8D/3 | tse | C | 0.082135 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-03 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-03 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-03 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-04 | 2026-03-01 | National Construction | 8D/1 | 8D/3 | 8D/1¦8D/3 | tse | C | 0.082135 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-04 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-04 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-04 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-05 | 2026-03-01 | National Construction | 8D/0 | 8D/1 | 8D/0¦8D/1 | tse | C | 0.10902 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-05 | 2026-03-01 | National Construction | 8D/1 | 8D/3 | 8D/1¦8D/3 | tse | C | 0.082135 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-05 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-05 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-05 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-06 | 2026-03-01 | National Construction | 8D/0 | 8D/1 | 8D/0¦8D/1 | tse | C | 0.10902 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-06 | 2026-03-01 | National Construction | 8D/1 | 8D/3 | 8D/1¦8D/3 | tse | C | 0.082135 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-06 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-06 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-06 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-07 | 2026-03-01 | National Construction | 8D/0 | 8D/1 | 8D/0¦8D/1 | tse | C | 0.10902 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-07 | 2026-03-01 | National Construction | 8D/1 | 8D/3 | 8D/1¦8D/3 | tse | C | 0.082135 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-07 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-07 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-07 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-08 | 2026-03-01 | National Construction | 8D/0 | 8D/1 | 8D/0¦8D/1 | tse | C | 0.10902 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-08 | 2026-03-01 | National Construction | 8D/1 | 8D/3 | 8D/1¦8D/3 | tse | C | 0.082135 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-08 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-08 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-08 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-09 | 2026-03-01 | National Construction | 8D/1 | 8D/3 | 8D/1¦8D/3 | tse | C | 0.082135 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-09 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-09 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-09 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-10 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-10 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-10 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-11 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-11 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-11 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-12 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-12 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-12 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-13 | 2026-03-01 | National Construction | 8C/0 | 8D/0 | 8C/0¦8D/0 | tse | C | 0.15938 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-13 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-13 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-13 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-14 | 2026-03-01 | National Construction | 8C/0 | 8D/0 | 8C/0¦8D/0 | tse | C | 0.15938 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-14 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-14 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-14 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-15 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-15 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-15 | 2026-03-01 | National Construction | 8E/0 | 8E/1 | 8E/0¦8E/1 | tse | C | 0.014759 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-16 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-16 | 2026-03-01 | National Construction | 8D/6 | 8E/0 | 8D/6¦8E/0 | tse | C | 0.012675 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-17 | 2026-03-01 | National Construction | 8D/5 | 8D/6 | 8D/5¦8D/6 | tse | C | 0.0095161 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-20 | 2026-03-01 | National Construction | 2/0 | 3/0 | 2/0¦3/0 | tse | C | 0.087102 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-03-21 | 2026-03-01 | National Construction | 2/0 | 3/0 | 2/0¦3/0 | tse | C | 0.087102 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-04-06 | 2026-04-01 | National Construction | 3/0 | 4/0 | 3/0¦4/0 | tse | C | 0.11486 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-04-07 | 2026-04-01 | National Construction | 3/0 | 4/0 | 3/0¦4/0 | tse | C | 0.11486 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-04-09 | 2026-04-01 | National Construction | 1B/0 | 1C/0 | 1B/0¦1C/0 | tse | C | 0.10275 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-04-10 | 2026-04-01 | National Construction | 1B/0 | 1C/0 | 1B/0¦1C/0 | tse | C | 0.10275 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-04-11 | 2026-04-01 | National Construction | 1C/0 | 1D/0 | 1C/0¦1D/0 | tse | C | 0.18227 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-04-12 | 2026-04-01 | National Construction | 1C/0 | 1D/0 | 1C/0¦1D/0 | tse | C | 0.18227 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-04-13 | 2026-04-01 | National Construction | 1C/0 | 1D/0 | 1C/0¦1D/0 | tse | C | 0.18227 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-04-14 | 2026-04-01 | National Construction | 1C/0 | 1D/0 | 1C/0¦1D/0 | tse | C | 0.18227 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-01 | 2026-06-01 | Ram singh | 33/0 | 34/0 | 33/0¦34/0 | tse | C | 0.076 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-02 | 2026-06-01 | Ram singh | 33/0 | 34/0 | 33/0¦34/0 | tse | C | 0.076 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-03 | 2026-06-01 | Ram singh | 33/0 | 34/0 | 33/0¦34/0 | tse | C | 0.076 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-04 | 2026-06-01 | GKFS Enterprises | AP-31 | AP-32 | 31¦32 | tse | C | 0.18584 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-04 | 2026-06-01 | Ram singh | 33/0 | 34/0 | 33/0¦34/0 | tse | C | 0.076 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-05 | 2026-06-01 | GKFS Enterprises | AP-31 | AP-32 | 31¦32 | tse | C | 0.18584 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-05 | 2026-06-01 | Ram singh | 33/0 | 34/0 | 33/0¦34/0 | tse | C | 0.076 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-06 | 2026-06-01 | GKFS Enterprises | AP-31 | AP-32 | 31¦32 | tse | C | 0.18584 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-06 | 2026-06-01 | Ram singh | 33/0 | 34/0 | 33/0¦34/0 | tse | C | 0.076 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-07 | 2026-06-01 | GKFS Enterprises | AP-31 | AP-32 | 31¦32 | tse | C | 0.18584 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-07 | 2026-06-01 | Ram singh | 33/0 | 34/0 | 33/0¦34/0 | tse | C | 0.076 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-08 | 2026-06-01 |  | AP-32 | 33/0 | 32¦33/0 | tse | C | 0.14155 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-08 | 2026-06-01 |  | 34/0 | 35/0 | 34/0¦35/0 | tse | C | 0.05175 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-09 | 2026-06-01 |  | AP-32 | 33/0 | 32¦33/0 | tse | C | 0.14155 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-09 | 2026-06-01 |  | 34/0 | 35/0 | 34/0¦35/0 | tse | C | 0.05175 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-10 | 2026-06-01 |  | 34/0 | 35/0 | 34/0¦35/0 | tse | C | 0.05175 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2026-06-11 | 2026-06-01 |  | 34/0 | 35/0 | 34/0¦35/0 | tse | C | 0.05175 |  |  |  | HEADER_ONLY | HEADER_ONLY | no | TRUE | HEADER_ONLY | Manpower header exists but values are blank in source DPR.
TB 507 | TB 507 | tb507 |  | 2026-02-01 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-02 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-03 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-04 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-05 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-06 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-07 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-08 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-09 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-10 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-11 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-12 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-13 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-14 | 2026-02-01 | Mahadev Enterprises | 146/0 | 145/0 | 145/0¦146/0 | TSE | Ready | 0.21889 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-14 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-15 | 2026-02-01 | Mahadev Enterprises | 146/0 | 145/0 | 145/0¦146/0 | TSE | Ready | 0.21889 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-15 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-16 | 2026-02-01 | Mahadev Enterprises | 146/0 | 145/0 | 145/0¦146/0 | TSE | Ready | 0.21889 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-16 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-17 | 2026-02-01 | Mahadev Enterprises | 146/0 | 145/0 | 145/0¦146/0 | TSE | Ready | 0.21889 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-17 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-18 | 2026-02-01 | Mahadev Enterprises | 146/0 | 145/0 | 145/0¦146/0 | TSE | Ready | 0.21889 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-18 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-18 | 2026-02-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-19 | 2026-02-01 | Mahadev Enterprises | 146/0 | 145/0 | 145/0¦146/0 | TSE | Ready | 0.21889 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-19 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-19 | 2026-02-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-20 | 2026-02-01 | Mahadev Enterprises | 146/0 | 145/0 | 145/0¦146/0 | TSE | Ready | 0.21889 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-20 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-20 | 2026-02-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-21 | 2026-02-01 | Mahadev Enterprises | 146/0 | 145/0 | 145/0¦146/0 | TSE | Ready | 0.21889 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-21 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-21 | 2026-02-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-22 | 2026-02-01 | Mahadev Enterprises | 146/0 | 145/0 | 145/0¦146/0 | TSE | Ready | 0.21889 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-22 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-22 | 2026-02-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-23 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-23 | 2026-02-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-24 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-24 | 2026-02-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-25 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-25 | 2026-02-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-26 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-26 | 2026-02-01 | Mahadev Enterprises | 150/0 | 149B/3 | 149B/3¦150/0 | Manual | Ready | 0.044455 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-26 | 2026-02-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-27 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-27 | 2026-02-01 | Mahadev Enterprises | 150/0 | 149B/3 | 149B/3¦150/0 | Manual | Ready | 0.044455 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-27 | 2026-02-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-28 | 2026-02-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-28 | 2026-02-01 | Mahadev Enterprises | 150/0 | 149B/3 | 149B/3¦150/0 | Manual | Ready | 0.044455 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-02-28 | 2026-02-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-01 | 2026-03-01 | Mahadev Enterprises | 149A/0 | 149/0 | 149/0¦149A/0 | Manual | Ready | 0.062667 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-01 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-01 | 2026-03-01 | Mahadev Enterprises | 150/0 | 149B/3 | 149B/3¦150/0 | Manual | Ready | 0.044455 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-01 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-02 | 2026-03-01 | Mahadev Enterprises | 149A/0 | 149/0 | 149/0¦149A/0 | Manual | Ready | 0.062667 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-02 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-02 | 2026-03-01 | Mahadev Enterprises | 150/0 | 149B/3 | 149B/3¦150/0 | Manual | Ready | 0.044455 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-02 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-03 | 2026-03-01 | Mahadev Enterprises | 149A/0 | 149/0 | 149/0¦149A/0 | Manual | Ready | 0.062667 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-03 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-03 | 2026-03-01 | Mahadev Enterprises | 150/0 | 149B/3 | 149B/3¦150/0 | Manual | Ready | 0.044455 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-03 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-04 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-04 | 2026-03-01 | Mahadev Enterprises | 150/0 | 149B/3 | 149B/3¦150/0 | Manual | Ready | 0.044455 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-04 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-05 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-05 | 2026-03-01 | Mahadev Enterprises | 150/0 | 149B/3 | 149B/3¦150/0 | Manual | Ready | 0.044455 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-05 | 2026-03-01 | Mahadev Enterprises | 149B/0 | 149A/0 | 149A/0¦149B/0 | Manual | Ready | 0.066 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-05 | 2026-03-01 | Mahadev Enterprises | 149B/3 | 149B/0 | 149B/0¦149B/3 | TSE | Ready | 0.21083 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-05 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-06 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-06 | 2026-03-01 | Mahadev Enterprises | 150/0 | 149B/3 | 149B/3¦150/0 | Manual | Ready | 0.044455 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-06 | 2026-03-01 | Mahadev Enterprises | 149B/0 | 149A/0 | 149A/0¦149B/0 | Manual | Ready | 0.066 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-06 | 2026-03-01 | Mahadev Enterprises | 149B/3 | 149B/0 | 149B/0¦149B/3 | TSE | Ready | 0.21083 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-06 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-07 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-07 | 2026-03-01 | Mahadev Enterprises | 150/0 | 149B/3 | 149B/3¦150/0 | Manual | Ready | 0.044455 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-07 | 2026-03-01 | Mahadev Enterprises | 149B/0 | 149A/0 | 149A/0¦149B/0 | Manual | Ready | 0.066 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-07 | 2026-03-01 | Mahadev Enterprises | 149B/3 | 149B/0 | 149B/0¦149B/3 | TSE | Ready | 0.21083 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-07 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-08 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-08 | 2026-03-01 | Mahadev Enterprises | 150/0 | 149B/3 | 149B/3¦150/0 | Manual | Ready | 0.044455 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-08 | 2026-03-01 | Mahadev Enterprises | 149B/0 | 149A/0 | 149A/0¦149B/0 | Manual | Ready | 0.066 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-08 | 2026-03-01 | Mahadev Enterprises | 149B/3 | 149B/0 | 149B/0¦149B/3 | TSE | Ready | 0.21083 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-08 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-09 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-09 | 2026-03-01 | Mahadev Enterprises | 149B/0 | 149A/0 | 149A/0¦149B/0 | Manual | Ready | 0.066 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-09 | 2026-03-01 | Mahadev Enterprises | 149B/3 | 149B/0 | 149B/0¦149B/3 | TSE | Ready | 0.21083 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-09 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-10 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-10 | 2026-03-01 | Mahadev Enterprises | 149B/0 | 149A/0 | 149A/0¦149B/0 | Manual | Ready | 0.066 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-10 | 2026-03-01 | Mahadev Enterprises | 149B/3 | 149B/0 | 149B/0¦149B/3 | TSE | Ready | 0.21083 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-10 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-11 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-11 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-12 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-12 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-13 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-13 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-14 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-14 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-15 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-15 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-16 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-16 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-17 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-17 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-18 | 2026-03-01 | Mahadev Enterprises | 149/0 | 148/0 | 148/0¦149/0 | TSE | Ready | 0.065891 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-18 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-19 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-20 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-21 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-21 | 2026-03-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-22 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-22 | 2026-03-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-23 | 2026-03-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-23 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-23 | 2026-03-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-24 | 2026-03-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-24 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-24 | 2026-03-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-25 | 2026-03-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-25 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-25 | 2026-03-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-26 | 2026-03-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-26 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-26 | 2026-03-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-27 | 2026-03-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-27 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-27 | 2026-03-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-28 | 2026-03-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-28 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-28 | 2026-03-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-29 | 2026-03-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-29 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-29 | 2026-03-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-30 | 2026-03-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-30 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-30 | 2026-03-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-31 | 2026-03-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-31 | 2026-03-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-03-31 | 2026-03-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-01 | 2026-04-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-01 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-01 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-02 | 2026-04-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-02 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-02 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-03 | 2026-04-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-03 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-03 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-04 | 2026-04-01 | Mahadev Enterprises | 144/0 | 143/0 | 143/0¦144/0 | TSE | Ready | 0.25192 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-04 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-04 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-05 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-05 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-06 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-06 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-07 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-07 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-08 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-08 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-09 | 2026-04-01 | Mahadev Enterprises | 145/0 | 144/0 | 144/0¦145/0 | Manual | Ready | 0.116 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-09 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-09 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-09 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-09 | 2026-04-01 | Mahadev Maan Construction | 113/0 | 112/0 | 112/0¦113/0 | Manual | Ready | 0.022571 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-10 | 2026-04-01 | Mahadev Enterprises | 145/0 | 144/0 | 144/0¦145/0 | Manual | Ready | 0.116 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-10 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-10 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-10 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-10 | 2026-04-01 | Mahadev Maan Construction | 113/0 | 112/0 | 112/0¦113/0 | Manual | Ready | 0.022571 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-10 | 2026-04-01 | Mahadev Maan Construction | 113A/0 | 113/0 | 113/0¦113A/0 | Manual | Ready | 0.022333 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-11 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-11 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-11 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-11 | 2026-04-01 | Mahadev Maan Construction | 113/0 | 112/0 | 112/0¦113/0 | Manual | Ready | 0.022571 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-11 | 2026-04-01 | Mahadev Maan Construction | 113A/0 | 113/0 | 113/0¦113A/0 | Manual | Ready | 0.022333 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-12 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-12 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-12 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-12 | 2026-04-01 | Mahadev Maan Construction | 113/0 | 112/0 | 112/0¦113/0 | Manual | Ready | 0.022571 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-12 | 2026-04-01 | Mahadev Maan Construction | 113A/0 | 113/0 | 113/0¦113A/0 | Manual | Ready | 0.022333 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-13 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-13 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-13 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-13 | 2026-04-01 | Mahadev Maan Construction | 113/0 | 112/0 | 112/0¦113/0 | Manual | Ready | 0.022571 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-13 | 2026-04-01 | Mahadev Maan Construction | 113A/0 | 113/0 | 113/0¦113A/0 | Manual | Ready | 0.022333 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-14 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-14 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-14 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-14 | 2026-04-01 | Mahadev Maan Construction | 113/0 | 112/0 | 112/0¦113/0 | Manual | Ready | 0.022571 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-14 | 2026-04-01 | Mahadev Maan Construction | 113A/0 | 113/0 | 113/0¦113A/0 | Manual | Ready | 0.022333 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-15 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-15 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-15 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-15 | 2026-04-01 | Mahadev Maan Construction | 113/0 | 112/0 | 112/0¦113/0 | Manual | Ready | 0.022571 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-15 | 2026-04-01 | Mahadev Maan Construction | 113A/0 | 113/0 | 113/0¦113A/0 | Manual | Ready | 0.022333 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-16 | 2026-04-01 | Mahadev Enterprises | 153/0 | 152/0 | 152/0¦153/0 | Manual | Ready | 0.1215 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-16 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-16 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-16 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-16 | 2026-04-01 | Mahadev Maan Construction | 113A/0 | 113/0 | 113/0¦113A/0 | Manual | Ready | 0.022333 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-17 | 2026-04-01 | Mahadev Enterprises | 153/0 | 152/0 | 152/0¦153/0 | Manual | Ready | 0.1215 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-17 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-17 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-17 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-17 | 2026-04-01 | Mahadev Maan Construction | 113A/0 | 113/0 | 113/0¦113A/0 | Manual | Ready | 0.022333 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-18 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-18 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-18 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-18 | 2026-04-01 | Mahadev Maan Construction | 113A/0 | 113/0 | 113/0¦113A/0 | Manual | Ready | 0.022333 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-19 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-19 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-19 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-20 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-20 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-20 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-21 | 2026-04-01 | Mahadev Enterprises | 147/0 | 146/0 | 146/0¦147/0 | TSE | Ready | 0.019413 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-21 | 2026-04-01 | Mahadev Enterprises | 148/0 | 147/0 | 147/0¦148/0 | TSE | Ready | 0.282 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-21 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-22 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-23 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-24 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-25 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-26 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-27 | 2026-04-01 | Mahadev Enterprises | 151/0 | 150/0 | 150/0¦151/0 | Manual | Ready | 0.145 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-27 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-28 | 2026-04-01 | Mahadev Enterprises | 151/0 | 150/0 | 150/0¦151/0 | Manual | Ready | 0.145 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-28 | 2026-04-01 | Mahadev Enterprises | 152/0 | 151/0 | 151/0¦152/0 | Manual | Ready | 0.2095 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-28 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-29 | 2026-04-01 | Mahadev Enterprises | 152/0 | 151/0 | 151/0¦152/0 | Manual | Ready | 0.2095 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-29 | 2026-04-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-29 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-30 | 2026-04-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-04-30 | 2026-04-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-01 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-01 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-02 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-02 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-03 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-03 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-04 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-04 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-05 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-05 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-06 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-06 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-07 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-07 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-08 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-08 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-09 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-09 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-10 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-10 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-11 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-11 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-12 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-12 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-12 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-13 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-13 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-13 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-13 | 2026-05-01 | SK Tajirul | 114/0 | 113A/0 | 113A/0¦114/0 | Manual | Ready | 0.0165 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-14 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-14 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-14 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-14 | 2026-05-01 | SK Tajirul | 114/0 | 113A/0 | 113A/0¦114/0 | Manual | Ready | 0.0165 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-15 | 2026-05-01 | Mahadev Enterprises | 134/0 | 133/0 | 133/0¦134/0 | TSE | Ready | 0.20506 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-15 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-15 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-15 | 2026-05-01 | SK Tajirul | 114/0 | 113A/0 | 113A/0¦114/0 | Manual | Ready | 0.0165 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-16 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-16 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-16 | 2026-05-01 | SK Tajirul | 114/0 | 113A/0 | 113A/0¦114/0 | Manual | Ready | 0.0165 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-17 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-17 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-17 | 2026-05-01 | SK Tajirul | 114/0 | 113A/0 | 113A/0¦114/0 | Manual | Ready | 0.0165 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-18 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-18 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-18 | 2026-05-01 | SK Tajirul | 114/0 | 113A/0 | 113A/0¦114/0 | Manual | Ready | 0.0165 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-19 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-19 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-19 | 2026-05-01 | SK Tajirul | 114/0 | 113A/0 | 113A/0¦114/0 | Manual | Ready | 0.0165 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-20 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-20 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-20 | 2026-05-01 | SK Tajirul | 114/0 | 113A/0 | 113A/0¦114/0 | Manual | Ready | 0.0165 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-21 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-21 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-21 | 2026-05-01 | SK Tajirul | 114/0 | 113A/0 | 113A/0¦114/0 | Manual | Ready | 0.0165 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-22 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-22 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-22 | 2026-05-01 | SK Tajirul | 114/0 | 113A/0 | 113A/0¦114/0 | Manual | Ready | 0.0165 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-23 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-23 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-24 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-24 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-25 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-25 | 2026-05-01 | SK Tajirul | 134/0 | 134A/0 | 134/0¦134A/0 | Manual | Ready | 0.016143 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-26 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-27 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-28 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-29 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.
TB 507 | TB 507 | tb507 |  | 2026-05-30 | 2026-05-01 | Mahadev Enterprises | 142/0 | 143/0 | 142/0¦143/0 | Manual | Ready | 0.0061549 |  |  |  | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES | no | FALSE | NO_DATA | No manpower values found for this span/day.

## Coverage
project_code | project_display | project_scope_key | category | status | reason_code | reason | workbook | configured_sheet | resolved_sheet | rows
TA 413 | TA 413 | ta413 | manpower | ABSENT | ABSENT |  | TA 413 - DPR - 2026-06-16.xlsx | Stringing | Stringing | 39
TA 413 | TA 413 | ta413 | manpower_productivity | NO_DATA | NO_DATA | No manpower values were mapped. |  |  |  | 523
TA 413 | TA 413 | ta413 | status | OK | OK |  | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | 12
TA 413 | TA 413 | ta413 | stretch | OK | OK |  | TA 413 - DPR - 2026-06-16.xlsx | Stretch readiness | Stretch readiness | 66
TA 413 | TA 413 | ta413 | stringing | OK | OK | Non-critical missing headers: Section Readiness, Gang Name Method inferred via erection span depth: rows=6, manual=0, tse=6, unresolved=6. | TA 413 - DPR - 2026-05-31.xlsx | Stringing | Stringing | 38
TA 414 | TA 414 | ta414 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TA 414 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | 172
TA 414 | TA 414 | ta414 | manpower_productivity | AVAILABLE | AVAILABLE | Manpower mapped to productivity rows. |  |  |  | 152
TA 414 | TA 414 | ta414 | status | OK | OK |  | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | 13
TA 414 | TA 414 | ta414 | stretch | MISSING_SOURCE | MISSING_SOURCE | No dedicated stretch readiness sheet configured. | TA 414 - DPR - 2026-06-18.xlsx |  |  | 0
TA 414 | TA 414 | ta414 | stringing | OK | OK |  | TA 414 - DPR - 2026-06-01.xlsx | Stringing Compiled | Stringing Compiled | 172
TA 416 | TA 416 | ta416 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TA 416 - DPR - 2026-06-17.xlsx | Stringing compiled | Stringing compiled | 79
TA 416 | TA 416 | ta416 | manpower_productivity | NO_DATA | NO_DATA | No manpower values were mapped. |  |  |  | 1171
TA 416 | TA 416 | ta416 | status | OK | OK |  | TA 416 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | 4
TA 416 | TA 416 | ta416 | stretch | MISSING_SOURCE | MISSING_SOURCE | No dedicated stretch readiness sheet configured. | TA 416 - DPR - 2026-06-17.xlsx |  |  | 0
TA 416 | TA 416 | ta416 | stringing | OK | OK | Method inferred via erection span depth: rows=5, manual=0, tse=5, unresolved=5. | TA 416 - DPR - 2026-05-30.xlsx | Stringing compiled | Stringing compiled | 79
TA 418 | TA 418 | ta418 | manpower | READ_FAIL | READ_FAIL | NO_TARGET_SHEET | TA 418 - DPR - 2026-06-17.xlsx | Stringing Compiled |  | 0
TA 418 | TA 418 | ta418 | manpower_productivity | AVAILABLE | AVAILABLE | Manpower mapped to productivity rows. |  |  |  | 408
TA 418 | TA 418 | ta418 | status | OK | OK |  | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | 4
TA 418 | TA 418 | ta418 | stretch | MISSING_SOURCE | MISSING_SOURCE | Configured stretch readiness sheet not found in selected workbook. | TA 418 - DPR - 2026-06-17.xlsx | Stringing Compiled |  | 0
TA 418 | TA 418 | ta418 | stringing | OK | OK | Method inferred via erection span depth: rows=4, manual=0, tse=4, unresolved=4. | TA 418 - DPR - 2026-05-30.xlsx | Stringing Completed | Stringing Completed | 43
TA 419 | TA 419 | ta419 | manpower | NO_SHEET_CONFIG | NO_SHEET_CONFIG | No daily stringing sheet configured for manpower audit. | TA 419 - DPR - 2026-06-18.xlsx |  |  | 0
TA 419 | TA 419 | ta419 | status | OK | OK |  | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | 14
TA 419 | TA 419 | ta419 | stretch | OK | OK |  | TA 419 - DPR - 2026-06-18.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | 332
TA 419 | TA 419 | ta419 | stringing | SKIPPED_NO_STRINGING_CONFIG | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | TA 419 - DPR - 2026-05-31.xlsx |  |  | 0
TA 421 | TA 421 | ta421 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TA 421 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | 76
TA 421 | TA 421 | ta421 | manpower_productivity | AVAILABLE | AVAILABLE | Manpower mapped to productivity rows. |  |  |  | 715
TA 421 | TA 421 | ta421 | status | OK | OK |  | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | 10
TA 421 | TA 421 | ta421 | stretch | OK | OK |  | TA 421 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | 298
TA 421 | TA 421 | ta421 | stringing | OK | OK | Method inferred via erection span depth: rows=16, manual=0, tse=16, unresolved=16. | TA 421 - DPR - 2026-05-31.xlsx | Stringing Compiled | Stringing Compiled | 76
TA 504 | TA 504 | ta504 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing | Stringing Compiled | 11
TA 504 | TA 504 | ta504 | manpower_productivity | AVAILABLE | AVAILABLE | Manpower mapped to productivity rows. |  |  |  | 156
TA 504 | TA 504 | ta504 | status | OK | OK |  | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | 6
TA 504 | TA 504 | ta504 | stretch | OK | OK |  | TA 504 - DPR - 2026-06-18.xlsx | Stringing | Stringing Compiled | 11
TA 504 | TA 504 | ta504 | stringing | OK | OK |  | TA 504 - DPR - 2026-05-31.xlsx | Stringing Compiled | Stringing Compiled | 53
TA 505 | TA 505 | ta505 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | 232
TA 505 | TA 505 | ta505 | manpower_productivity | AVAILABLE | AVAILABLE | Manpower mapped to productivity rows. |  |  |  | 213
TA 505 | TA 505 | ta505 | status | OK | OK |  | TA 505 - DPR - 2026-06-18.xlsx | DPR-Summary | DPR-Summary | 6
TA 505 | TA 505 | ta505 | stretch | OK | OK |  | TA 505 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | 29
TA 505 | TA 505 | ta505 | stringing | OK | OK | Method inferred via erection span depth: rows=220, manual=0, tse=220, unresolved=220. | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | Stringing Compiled | 232
TA 506 | TA 506 | ta506 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | 230
TA 506 | TA 506 | ta506 | manpower_productivity | AVAILABLE | AVAILABLE | Manpower mapped to productivity rows. |  |  |  | 557
TA 506 | TA 506 | ta506 | status | OK | OK |  | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | 6
TA 506 | TA 506 | ta506 | stretch | OK | OK |  | TA 506 - DPR - 2026-06-18.xlsx | Stringing | Stringing | 41
TA 506 | TA 506 | ta506 | stringing | OK | OK | Method inferred via erection span depth: rows=194, manual=0, tse=194, unresolved=194. | TA 506 - DPR - 2026-05-31.xlsx | Stringing | Stringing | 230
TA 509 | TA 509 | ta509 | status | OK | OK |  | TA 509 - DPR - 2026-06-18.xlsx | SUMMARY | SUMMARY | 4
TA 509 | TA 509 | ta509 | stringing | SKIPPED_NO_STRINGING_CONFIG | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | TA 509 - DPR - 2026-05-31.xlsx |  |  | 0
TA 510 | TA 510 | ta510 | status | OK | OK |  | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | 13
TA 510 | TA 510 | ta510 | stringing | SKIPPED_NO_STRINGING_CONFIG | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | TA 510 - DPR - 2026-05-31.xlsx |  |  | 0
TA 512 | TA 512 | ta512 | manpower | NO_SHEET_CONFIG | NO_SHEET_CONFIG | No daily stringing sheet configured for manpower audit. | TA 512 - DPR - 2026-06-18.xlsx |  |  | 0
TA 512 | TA 512 | ta512 | status | OK | OK |  | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | 13
TA 512 | TA 512 | ta512 | stretch | OK | OK |  | TA 512 - DPR - 2026-06-18.xlsx | Tack Welding | Tack Welding | 99
TA 512 | TA 512 | ta512 | stringing | SKIPPED_NO_STRINGING_CONFIG | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | TA 512 - DPR - 2026-05-31.xlsx |  |  | 0
TA 513 | TA 513 | ta513 | status | OK | OK |  | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | 28
TA 513 | TA 513 | ta513 | stringing | SKIPPED_NO_STRINGING_CONFIG | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | TA 513 - DPR - 2026-05-31.xlsx |  |  | 0
TA 515 | TA 515 | ta515 | status | TEMPLATE_CONFIG_ERROR | TEMPLATE_CONFIG_ERROR | Status Template Check is Yes but no mapping tab matching project 'TA 515' was found. | TA 515 - DPR - 2026-06-18.xlsx | DPR | DPR | 0
TA 515 | TA 515 | ta515 | stringing | SKIPPED_NO_STRINGING_CONFIG | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | TA 515 - DPR - 2026-05-11.xlsx |  |  | 0
TA 601 | TA 601 | ta601 | manpower | HEADER_ONLY | HEADER_ONLY |  | TA 601 - DPR - 2026-06-18.xlsx | Stringing Compiled | Stringing Compiled | 0
TA 601 | TA 601 | ta601 | status | OK | OK |  | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | 11
TA 601 | TA 601 | ta601 | stretch | OK | OK |  | TA 601 - DPR - 2026-06-18.xlsx | STRG Stretch | STRG Stretch | 64
TA 601 | TA 601 | ta601 | stringing | READ_FAIL | READ_FAIL | Resolved sheet is empty. | TA 601 - DPR - 2026-05-30.xlsx | Stringing Compiled | Stringing Compiled | 0
TA 602 | TA 602 | ta602 | status | OK | OK |  | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | 6
TA 602 | TA 602 | ta602 | stringing | SKIPPED_NO_STRINGING_CONFIG | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | TA 602 - DPR - 2026-05-30.xlsx |  |  | 0
TB 408 | TB 408 | tb408 | manpower | ABSENT | ABSENT |  | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Stringing | 65
TB 408 | TB 408 | tb408 | manpower_productivity | NO_DATA | NO_DATA | No manpower values were mapped. |  |  |  | 1745
TB 408 | TB 408 | tb408 | status | OK | OK |  | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | 7
TB 408 | TB 408 | tb408 | stretch | OK | OK |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | 434
TB 408 | TB 408 | tb408 | stringing | OK | OK | Non-critical missing headers: Section Readiness Method inferred via erection span depth: rows=11, manual=0, tse=11, unresolved=11. | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Stringing | 65
TB 412 | TB 412 | tb412 | status | OK | OK |  | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | 13
TB 501 | TB 501 - 132kV | tb501 | manpower | HEADER_ONLY | HEADER_ONLY |  | TB 501 - DPR - 2026-06-18.xlsx | Stringing-132KV | Stringing-132KV | 47
TB 501 | TB 501 - 220kV | tb501 | manpower | HEADER_ONLY | HEADER_ONLY |  | TB 501 - DPR - 2026-06-18.xlsx | Stringing-220kV | Stringing-220kV | 226
TB 501 | TB 501 - 132kV | tb501 | manpower_productivity | HEADER_ONLY | HEADER_ONLY | Manpower headers present without values. |  |  |  | 104
TB 501 | TB 501 - 220kV | tb501 | manpower_productivity | HEADER_ONLY | HEADER_ONLY | Manpower headers present without values. |  |  |  | 881
TB 501 | TB 501 | tb501 | status | OK | OK |  | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | 20
TB 501 | TB 501 | tb501 | stretch | MISSING_SOURCE | MISSING_SOURCE | No dedicated stretch readiness sheet configured. | TB 501 - DPR - 2026-06-18.xlsx |  |  | 0
TB 501 | TB 501 - 220kV | tb501 | stringing | OK | OK | Non-critical missing headers: Method Method inferred via erection span depth: rows=47, manual=0, tse=47, unresolved=47.; Non-critical missing headers: Method Method inferred via erection span depth: rows=226, manual=0, tse=226, unresolved=226. | TB 501 - DPR - 2026-05-28.xlsx | Stringing-132KV; Stringing-220kV | Stringing-132KV; Stringing-220kV | 226
TB 507 | TB 507 - MAIN | tb507 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Stringing Compiled | Stringing Compiled | 27
TB 507 | TB 507 | tb507 | manpower_productivity | NO_DATA | NO_DATA | No manpower values were mapped. |  |  |  | 306
TB 507 | TB 507 - MAIN | tb507 | status | OK | OK |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | 14
TB 507 | TB 507 - 765kV | tb507 | status | OK | OK |  | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | 12
TB 507 | TB 507 - MAIN | tb507 | stretch | MISSING_SOURCE | MISSING_SOURCE | Configured stretch readiness sheet not found in selected workbook. | TB 507 - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding |  | 0
TB 507 | TB 507 | tb507 | stretch | MISSING_SOURCE | MISSING_SOURCE | No dedicated stretch readiness sheet configured for this project line variant. | TB 507 - DPR - 2026-06-17.xlsx |  |  | 0
TB 507 | TB 507 - MAIN | tb507 | stretch | OK | OK |  | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | 156
TB 507 | TB 507 - MAIN | tb507 | stringing | OK | OK | Method inferred via erection span depth: rows=2, manual=0, tse=2, unresolved=2.; Method inferred via erection span depth: rows=6, manual=0, tse=6, unresolved=6. | TB 507 - DPR - 2026-05-30.xlsx; TB 507 [MAIN] - DPR - 2026-05-30.xlsx | Stringing Compiled | Stringing Compiled | 26
TB 605 | TB 605 | tb605 | status | OK | OK |  | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | 6
TB 605 | TB 605 | tb605 | stringing | SKIPPED_NO_STRINGING_CONFIG | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | TB 605 - DPR - 2026-05-31.xlsx |  |  | 0
TB 608 | TB 608 | tb608 | status | OK | OK |  | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | 41
TB 608 | TB 608 | tb608 | stringing | SKIPPED_NO_STRINGING_CONFIG | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | TB 608 - DPR - 2026-05-31.xlsm |  |  | 0

## Diagnostics
component | status | rows | distinct_report_dates | distinct_months
StringingDailySource | AVAILABLE | 6931 | 612 | 23
ProgressStatusRawSource | AVAILABLE | 1691 | 18 | 4
StretchReadinessRawSource | AVAILABLE | 1530 | 4 | 1
StretchManpowerAuditSource | AVAILABLE | 15
StatusActivityFact | AVAILABLE | 1615 | 15 | 2
StretchSectionFact | AVAILABLE | 1530 | 4 | 1
ManpowerProductivityFact | AVAILABLE | 6931 | 612 | 23

## Issues
severity | component | code | message