## Stringing Compiled
s no | sec | from_ap |  | to_ap | span m | method | balance fdn | balance erc | section_readiness | starting date | completion date | po_start_date | po_completion_date | po | fs_starting_date | fs_complete_date | length_m | status | completion month | jmc no | gang_name | hindrance | remarks | district | project_name | project | source_file
1 | JMB | 112/0 | ~ | 113/0 | 375.84 | Manual | 0 | 0 | Ready |  |  | 2024-08-12 | 2024-08-15 | 375.84 | 2024-08-17 | 2024-08-19 | 375.84 | Completed | 2024-08-01 | 1 | Muslehuddin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
2 | JMB | 111/0 | ~ | 112/0 | 341.9 | Manual | 0 | 0 | Ready |  |  | 2024-09-23 | 2024-09-24 | 341.9 | 2024-10-02 | 2024-10-04 | 341.9 | Completed | 2024-10-01 | 4 | Gokul Sarkar |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
3 | JMB | 110/0 | ~ | 111/0 | 312.14 | Manual | 0 | 0 | Ready |  |  | 2024-09-11 | 2024-09-12 | 312.14 | 2024-10-04 | 2024-10-06 | 312.14 | Completed | 2024-10-01 | 3 | Gokul Sarkar |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
4 | JMB | 113/0 | ~ | 114/0 | 297.05 | Manual | 0 | 0 | Ready |  |  | 2024-09-26 | 2024-09-29 | 297.05 | 2024-10-01 | 2024-10-06 | 297.05 | Completed | 2024-10-01 | 6 | Muslehuddin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
5 | JMB | 109/0 | ~ | 110/0 | 342.42 | Manual | 0 | 0 | Ready |  |  | 2024-09-06 | 2024-09-09 | 342.42 | 2024-10-10 | 2024-10-13 | 342.42 | Completed | 2024-10-01 | 2 | Gokul Sarkar |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
6 | JMB | 116/0 | ~ | 116A/0 | 243.41 | Manual | 0 | 0 | Ready |  |  | 2024-10-15 | 2024-10-18 | 243.41 | 2024-10-26 | 2024-10-27 | 243.41 | Completed | 2024-10-01 | 7 | Gokul Sarkar |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
7 | JMB | 108/0 | ~ | 109/0 | 277.2 | Manual | 0 | 0 | Ready |  |  | 2024-10-17 | 2024-10-20 | 277.2 | 2024-10-25 | 2024-10-28 | 277.2 | Completed | 2024-10-01 | 8 | Muslehuddin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
8 | JMB | 107/0 | ~ | 108/0 | 558.88 | Manual | 0 | 0 | Ready |  |  | 2024-10-30 | 2024-11-02 | 558.88 | 2024-11-04 | 2024-11-07 | 558.88 | Completed | 2024-11-01 | 9 | Muslehuddin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
9 | JMB | 133/0 | ~ | 133A/0 | 2267.72 | TSE | 0 | 0 | Ready |  |  | 2024-10-29 | 2024-11-02 | 2267.72 | 2024-11-03 | 2024-11-07 | 2267.72 | Completed | 2024-11-01 | 5 | Rejaul |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
10 | JMB | 121/0 | ~ | 122/0 | 525.49 | Manual | 0 | 0 | Ready |  |  | 2024-11-02 | 2024-11-03 | 525.49 | 2024-11-18 | 2024-11-19 | 525.49 | Completed | 2024-11-01 | 10 | Gokul Sarkar |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
11 | JMB | 129A/0 | ~ | 130/0 | 1182.12 | TSE | 0 | 0 | Ready |  |  | 2024-11-16 | 2024-11-18 | 1182.12 | 2024-11-21 | 2024-11-22 | 1182.12 | Completed | 2024-11-01 | 12 | Rejaul |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
12 | JMB | 106B/0 | ~ | 107/0 | 1148.24 | TSE | 0 | 0 | Ready |  |  | 2024-11-15 | 2024-11-16 | 1148.24 | 2024-11-20 | 2024-11-23 | 1148.24 | Completed | 2024-11-01 | 11 | Muslehuddin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
13 | JMB | 122/0 | ~ | 123/0 | 328.32 | Hotline | 0 | 0 | Ready |  |  | 2024-11-23 | 2024-11-26 | 328.32 | 2024-11-28 | 2024-11-30 | 328.32 | Completed | 2024-11-01 | 13 | Dhervendra Electricals |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
14 | JMB | 118/0 | ~ | 119/0 | 294.43 | Manual | 0 | 0 | Ready |  |  | 2024-11-23 | 2024-11-25 | 294.43 | 2024-12-02 | 2024-12-03 | 294.43 | Completed | 2024-12-01 | 14 | Enamul Haque |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
15 | JMB | 117/0 | ~ | 118/0 | 285.24 | Manual | 0 | 0 | Ready |  |  | 2024-12-08 | 2024-12-13 | 285.24 | 2024-12-18 | 2024-12-20 | 285.24 | Completed | 2025-01-01 | 16 | Enamul Haque |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
16 | JMB | 119/0 | ~ | 120/0 | 1372.87 | TSE | 0 | 0 | Ready |  |  | 2024-12-19 | 2024-12-20 | 1372.87 | 2024-12-21 | 2024-12-22 | 1372.87 | Completed | 2025-02-01 | 18 | Muslehuddin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
17 | JMB | 116B/0 | ~ | 117/0 | 437 | Manual | 0 | 0 | Ready |  |  | 2024-11-17 | 2024-12-18 | 437 | 2024-12-23 | 2024-12-24 | 437 | Completed | 2025-03-01 | 17 | Yakub Ali + Enamul |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
18 | JMB | 144/0 | ~ | 144A/0 | 2391.06 | TSE | 0 | 0 | Ready |  |  | 2024-12-16 | 2024-12-19 | 2391.06 | 2024-12-22 | 2024-12-24 | 2391.06 | Completed | 2025-04-01 | 15 | Gokul Sarkar |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
19 | JMB | 120/0 | ~ | 121/0 | 264.71 | Hotline | 0 | 0 | Ready |  |  | 2024-12-28 | 2025-01-01 | 264.71 | 2024-12-28 | 2025-01-01 | 264.71 | Completed | 2025-01-01 | 19 | Dhervendra Electricals |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
20 | JMB | 114/0 | ~ | 115/0 | 374 | Manual | 0 | 0 | Ready |  |  | 2024-12-26 | 2024-12-28 | 374 | 2024-12-30 | 2025-01-02 | 374 | Completed | 2025-01-01 | 20 | Muslehuddin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
21 | JMB | 115/0 | ~ | 116/0 | 226 | Manual | 0 | 0 | Ready |  |  | 2024-12-26 | 2024-12-28 | 226 | 2024-12-31 | 2025-01-02 | 226 | Completed | 2025-01-01 | 21 | Muslehuddin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
22 | JMB | 133A/0 | ~ | 134/0 | 2037.5 | TSE | 0 | 0 | Ready |  |  | 2024-12-27 | 2025-01-01 | 2037.5 | 2025-01-02 | 2025-01-04 | 2037.5 | Completed | 2025-01-01 | 22 | Rejaul + Rafikul |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
23 | JMB | 123/0 | ~ | 124/0 | 843 | Manual | 0 | 0 | Ready |  |  | 2024-12-29 | 2024-12-30 | 843 | 2025-01-05 | 2025-01-06 | 843 | Completed | 2025-01-01 | 23 | Enamul Haque |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
24 | JMB | 116A/0 | ~ | 116B/0 | 675 | Manual | 0 | 0 | Ready |  |  | 2025-01-09 | 2025-01-11 | 675 | 2025-01-12 | 2025-01-13 | 675 | Completed | 2025-01-01 | 24 | Muslehuddin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
25 | JMB | 144A/0 | ~ | 145/0 | 397.58 | Hotline | 0 | 0 | Ready |  |  | 2024-01-08 | 2025-01-13 | 397.58 | 2024-01-08 | 2025-01-13 | 397.58 | Completed | 2025-01-01 | 25 | Dhervendra Electricals |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
26 | JMB | 147/1 | ~ | 147/2 | 330 | Manual | 0 | 0 | Ready |  |  | 2025-01-15 | 2025-01-16 | 330 | 2025-01-15 | 2025-01-16 | 330 | Completed | 2025-01-01 | 26 | Gokul Sarkar |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
27 | JMB | 127/0 | ~ | 128/0 | 2399.38 | TSE | 0 | 0 | Ready |  |  | 2024-12-11 | 2024-12-13 | 2399.38 | 2025-01-17 | 2025-01-19 | 2399.38 | Completed | 2025-01-01 | 27 | Muslehuddin + Enamul |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
28 | JMB | 126/0 | ~ | 127/0 | 808.43 | Manual | 0 | 0 | Ready |  |  | 2025-01-09 | 2025-01-11 | 808.43 | 2025-01-23 | 2025-01-24 | 808.43 | Completed | 2025-01-01 | 28 | Enamul Haque |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
29 | JMB | 132/0 | ~ | 133/0 | 1280.12 | TSE | 0 | 0 | Ready |  |  | 2025-01-12 | 2025-01-14 | 1280.12 | 2025-01-21 | 2025-01-24 | 1280.12 | Completed | 2025-01-01 | 29 | Rejaul + enamul |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
30 | BAR | 259/0 | ~ | 260/0 | 256 | Hotline | 0 | 0 | Ready |  | 2025-01-18 | 2025-01-23 | 2025-01-24 | 256 | 2025-01-26 | 2025-01-28 | 256 | Completed | 2025-01-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
31 | BAR | 260/0 | ~ | 261/0 | 338 | Manual | 0 | 0 | Ready |  | 2025-01-17 | 2025-01-23 | 2025-01-25 | 338 | 2025-01-26 | 2025-01-28 | 338 | Completed | 2025-01-01 |  | Monera |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
32 | JMB | 125A/0 | ~ | 126/0 | 380.08 | Manual | 0 | 0 | Ready |  |  | 2025-01-16 | 2025-01-18 | 380.08 | 2025-02-04 | 2025-02-05 | 380.08 | Completed | 2025-02-01 | 30 | Enamul Haque |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
33 | JMB | 106A/0 | ~ | 106B/0 | 2016.36 | TSE | 0 | 0 | Ready |  |  | 2025-01-28 | 2025-02-01 | 2016.36 | 2025-02-04 | 2025-02-06 | 2016.36 | Completed | 2025-02-01 | 31 | Muslehuddin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
34 | JMB | 125/0 | ~ | 125A/0 | 401.32 | Manual | 0 | 0 | Ready |  |  | 2025-01-31 | 2025-02-02 | 401.32 | 2025-02-06 | 2025-02-07 | 401.32 | Completed | 2025-02-01 | 32 | Enamul Haque |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
35 | JMB | 128/0 | ~ | 129/0 | 253.25 | Manual | 0 | 0 | Ready |  |  | 2025-02-10 | 2025-02-10 | 253.25 | 2025-02-12 | 2025-02-12 | 253.25 | Completed | 2025-02-01 | 33 | Alam Construction |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
36 | JMB | 129/0 | ~ | 129A/0 | 305.53 | Manual | 0 | 0 | Ready |  |  | 2025-02-10 | 2025-02-10 | 305.53 | 2025-02-12 | 2025-02-13 | 305.53 | Completed | 2025-02-01 | 34 | Alam Construction |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
37 | JMB | 135A/0 | ~ | 135A/1 | 339.83 | Manual | 0 | 0 | Ready |  |  | 2025-01-20 | 2025-01-21 | 339.83 | 2025-02-06 | 2025-02-14 | 339.83 | Completed | 2025-02-01 | 35 | SK Zenarul |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
38 | JMB | 135A/2 | ~ | 135B/0 | 2234.39 | TSE | 0 | 0 | Ready |  |  | 2025-02-04 | 2025-02-06 | 2234.39 | 2025-02-12 | 2025-02-14 | 2234.39 | Completed | 2025-02-01 | 36 | Rafikul Alam construction + Enamul |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
39 | JMB | 135B/0 | ~ | 136/0 | 2985.99 | TSE | 0 | 0 | Ready |  |  | 2025-01-25 | 2025-01-29 | 2985.99 | 2025-02-12 | 2025-02-14 | 2985.99 | Completed | 2025-02-01 | 37 | Rafikul Alam construction + Enamul |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
40 | JMB | 106/0 | ~ | 106A/0 | 411.25 | Manual | 0 | 0 | Ready |  |  | 2025-02-02 | 2025-02-05 | 411.25 | 2025-02-14 | 2025-02-15 | 411.25 | Completed | 2025-02-01 | 38 | Muslehuddin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
41 | BAR | 164/0 | ~ | 165/0 | 2980.78 | TSE | 0 | 0 | Ready |  |  | 2025-02-07 | 2025-02-10 | 2980.78 | 2025-02-12 | 2025-02-15 | 2980.78 | Completed | 2025-02-01 | 39 | Manik Sarkar |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
42 | JMB | 135A/1 | ~ | 135A/2 | 451.85 | Manual | 0 | 0 | Ready |  |  | 2025-01-29 | 2025-02-02 | 451.85 | 2025-02-07 | 2025-02-16 | 451.85 | Completed | 2025-02-01 | 40 | SK Zenarul |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
43 | JMB | 124/0 | ~ | 124A/0 | 395.28 | Manual | 0 | 0 | Ready |  |  | 2025-02-10 | 2025-02-13 | 395.28 | 2025-02-16 | 2025-02-19 | 395.28 | Completed | 2025-02-01 | 41 | Enamul Haque |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
44 | JMB | 124A/0 | ~ | 124A/1 | 253 | Manual | 0 | 0 | Ready |  |  | 2025-02-15 | 2025-02-19 | 253 | 2025-02-15 | 2025-02-19 | 253 | Completed | 2025-02-01 | 42 | Enamul Haque |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
45 | JMB | 124A/1 | ~ | 125/0 | 203.134 | Hotline | 0 | 0 | Ready |  |  | 2025-02-15 | 2025-02-19 | 203.134 | 2025-02-15 | 2025-02-19 | 203.134 | Completed | 2025-02-01 | 42 | Dhervendra Electricals |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
46 | BAR | 257/0 | ~ | 259/0 | 1809 | TSE | 0 | 0 | Ready |  | 2025-02-10 | 2025-02-11 | 2025-02-13 | 1809 | 2025-02-21 | 2025-02-24 | 1809 | Completed | 2025-02-01 |  | Monera |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
47 | JMB | 137A/0 | ~ | 138/0 | 2729.901 | TSE | 0 | 0 | Ready |  |  | 2025-02-21 | 2025-02-25 | 2729.901 | 2025-02-28 | 2025-03-03 | 2729.901 | Completed | 2025-03-01 | 43 | Alam Construction |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
48 | JMB | 138/0 | ~ | 139/0 | 1238.994 | TSE | 0 | 0 | Ready |  |  | 2025-02-27 | 2025-03-01 | 1238.994 | 2025-03-02 | 2025-03-04 | 1238.994 | Completed | 2025-03-01 | 44 | Enamul Haque |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
49 | BAR | 261/0 | ~ | 262/0 | 242 | Hotline | 0 | 0 | Ready |  | 2025-02-28 | 2025-03-02 | 2025-03-04 | 242 | 2025-03-06 | 2025-03-08 | 242 | Completed | 2025-03-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
50 | JMB | 139/0 | ~ | 139A/0 | 1211.03 | TSE | 0 | 0 | Ready |  |  | 2025-03-02 | 2025-03-04 | 1211.03 | 2025-03-07 | 2025-03-09 | 1211.03 | Completed | 2025-03-01 | 45 | SK Zenarul |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
51 | JMB | 130/0 | ~ | 131/0 | 2041.128 | TSE | 0 | 0 | Ready |  |  | 2025-03-03 | 2025-03-05 | 2041.128 | 2025-03-07 | 2025-03-10 | 2041.128 | Completed | 2025-03-01 | 46 | Muslehuddin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
52 | JMB | 131/0 | ~ | 132/0 | 236.46 | Hotline | 0 | 0 | Ready |  |  | 2025-03-06 | 2025-03-10 | 236.46 | 2025-03-06 | 2025-03-10 | 236.46 | Completed | 2025-03-01 | 47 | Dhervendra Electricals |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
53 | JMB | 139A/0 | ~ | 140/0 | 427.14 | Manual | 0 | 0 | Ready |  |  | 2025-02-27 | 2025-03-05 | 427.14 | 2025-03-07 | 2025-03-13 | 427.14 | Completed | 2025-03-01 | 48 | SK Zenarul |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
54 | BAR | 262/0 | ~ | 263/0 | 686 | Manual | 0 | 0 | Ready |  | 2025-02-16 | 2025-02-17 | 2025-02-19 | 686 | 2025-03-12 | 2025-03-15 | 686 | Completed | 2025-03-01 |  | Monera |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
55 | BAR | 263/0 | ~ | 264/0 | 243 | Hotline | 0 | 0 | Ready |  | 2025-03-09 | 2025-03-11 | 2025-03-12 | 243 | 2025-03-13 | 2025-03-15 | 243 | Completed | 2025-03-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
56 | JMB | 142/0 | ~ | 143/0 | 223.38 | Manual | 0 | 0 | Ready |  |  | 2025-03-18 | 2025-03-18 | 223.38 | 2025-03-18 | 2025-03-18 | 223.38 | Completed | 2025-03-01 |  | Enamul + Alam Constrution |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
57 | JMB | 143/0 | ~ | 143A/0 | 393.22 | Manual | 0 | 0 | Ready |  |  | 2025-03-08 | 2025-03-09 | 393.22 | 2025-03-20 | 2025-03-21 | 393.22 | Completed | 2025-03-01 |  | Alam Construction |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
58 | BAR | 255/0 | ~ | 257/0 | 1839 | TSE | 0 | 0 | Ready |  | 2025-02-13 | 2025-02-12 | 2025-02-25 | 1839 | 2025-03-20 | 2025-03-21 | 1839 | Completed | 2025-03-01 |  | Kamruddin |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
59 | BAR | 265/0 | ~ | 266/0 | 223 | Hotline | 0 | 0 | Ready |  |  | 2025-03-16 | 2025-03-18 | 223 | 2025-03-19 | 2025-03-21 | 223 | Completed | 2025-03-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
60 | JMB | 134/0 | ~ | 135/0 | 235.87 | Hotline | 0 | 0 | Ready |  |  | 2025-03-18 | 2025-03-22 | 235.87 | 2025-03-18 | 2025-03-22 | 235.87 | Completed | 2025-03-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
61 | BAR | 163/0 | ~ | 163/5 | 1894 | TSE | 0 | 0 | Ready |  |  | 2025-02-24 | 2025-02-28 | 1894 | 2025-03-21 | 2025-03-22 | 1894 | Completed | 2025-03-01 |  | Manik Sarkar |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
62 | BAR | 163/5 | ~ | 163/6 | 339 | Hotline | 0 | 0 | Ready |  |  | 2025-03-21 | 2025-03-22 | 339 | 2025-03-21 | 2025-03-22 | 339 | Completed | 2025-03-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
63 | BAR | 163/6 | ~ | 164/0 | 343 | TSE | 0 | 0 | Ready |  |  | 2025-03-04 | 2025-03-08 | 343 | 2025-03-21 | 2025-03-22 | 343 | Completed | 2025-03-01 |  | Manik Sarkar |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
64 | BAR | 264/0 | ~ | 265/0 | 441 | Manual | 0 | 0 | Ready |  |  | 2025-03-16 | 2025-03-18 | 441 | 2025-03-19 | 2025-03-22 | 441 | Completed | 2025-03-01 |  | Monera |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
65 | JMB | 143A/0 | ~ | 143A/2 | 841.2 | Manual | 0 | 0 | Ready |  |  | 2025-03-19 | 2025-03-21 | 841.2 | 2025-03-23 | 2025-03-26 | 841.2 | Completed | 2025-03-01 |  | Alam Construction |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
66 | JMB | 143A/2 | ~ | 143A/3 | 413.09 | Manual | 0 | 0 | Ready |  |  | 2025-03-23 | 2025-03-24 | 413.09 | 2025-03-23 | 2025-03-26 | 413.09 | Completed | 2025-03-01 |  | Enamul Haque |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
67 | JMB | 143A/3 | ~ | 144/0 | 1246.06 | TSE | 0 | 0 | Ready |  |  | 2025-03-18 | 2025-03-20 | 1246.06 | 2025-03-23 | 2025-03-26 | 1246.06 | Completed | 2025-03-01 |  | Enamul Haque |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
68 | BAR | 266/0 | ~ | 266/1 | 340 | Hotline | 0 | 0 | Ready |  |  | 2025-03-23 | 2025-03-24 | 340 | 2025-03-25 | 2025-03-28 | 340 | Completed | 2025-03-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
69 | BAR | 266/1 | ~ | 267/0 | 835 | Manual | 0 | 0 | Ready |  |  | 2025-03-22 | 2025-03-24 | 835 | 2025-03-25 | 2025-03-28 | 835 | Completed | 2025-03-01 |  | Monera |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
70 | JMB | 136/0 | ~ | 137/0 | 425.58 | Hotline | 0 | 0 | Ready |  |  | 2025-03-26 | 2025-04-01 | 425.58 | 2025-03-26 | 2025-04-01 | 425.58 | Completed | 2025-04-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
71 | JMB | 137/0 | ~ | 137A/0 | 2827.097 | TSE | 0 | 0 | Ready |  |  | 2025-03-05 | 2025-03-09 | 2827.097 | 2025-03-26 | 2025-04-01 | 2827.097 | Completed | 2025-04-01 |  | Rafikul Alam construction |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
72 | JMB | 145A/0 | ~ | 146/0 | 1620.89 | TSE | 0 | 0 | Ready |  |  | 2025-04-02 | 2025-04-04 | 1620.89 | 2025-04-07 | 2025-04-08 | 1620.89 | Completed | 2025-04-01 |  | Enamul Haque |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
73 | BAR | 253/0 | ~ | 254/0 | 246 | Hotline | 0 | 0 | Ready |  |  | 2025-04-04 | 2025-04-06 | 246 | 2025-04-07 | 2025-04-08 | 246 | Completed | 2025-04-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
74 | BAR | 254/0 | ~ | 255/0 | 300 | Manual | 0 | 0 | Ready |  |  | 2025-02-26 | 2025-02-28 | 300 | 2025-04-07 | 2025-04-08 | 300 | Completed | 2025-04-01 |  | Monera |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
75 | BAR | 267/0 | ~ | 267A/0 | 511 | Manual | 0 | 0 | Ready |  |  | 2025-04-01 | 2025-04-03 | 511 | 2025-04-07 | 2025-04-10 | 511 | Completed | 2025-04-01 |  | Kamruddin Deepak Sarkar |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
76 | BAR | 267A/0 | ~ | 268/0 | 1440 | TSE | 0 | 0 | Ready |  | 2025-03-25 | 2025-03-27 | 2025-03-29 | 1440 | 2025-04-07 | 2025-04-10 | 1440 | Completed | 2025-04-01 |  | Kamruddin |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
77 | JMB | 141/0 | ~ | 141/1 | 390 | TSE | 0 | 0 | Ready |  |  | 2025-04-05 | 2025-04-09 | 390 | 2025-04-11 | 2025-04-13 | 390 | Completed | 2025-04-01 |  | Alam Construction |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
78 | JMB | 141/1 | ~ | 141/2 | 370 | Hotline | 0 | 0 | Ready |  |  | 2025-04-05 | 2025-04-09 | 370 | 2025-04-11 | 2025-04-13 | 370 | Completed | 2025-04-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
79 | JMB | 141/2 | ~ | 142/0 | 805.06 | TSE | 0 | 0 | Ready |  |  | 2025-04-05 | 2025-04-09 | 805.06 | 2025-04-11 | 2025-04-13 | 805.06 | Completed | 2025-04-01 |  | Alam Construction |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
80 | JMB | 146/0 | ~ | 147/0 | 475.02 | Hotline | 0 | 0 | Ready |  |  | 2025-04-12 | 2025-04-15 | 475.02 | 2025-04-12 | 2025-04-15 | 475.02 | Completed | 2025-04-01 |  | Enamul Haque |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
81 | JMB | 147/0 | ~ | 147/1 | 425.52 | Hotline | 0 | 0 | Ready |  |  | 2025-04-11 | 2025-04-15 | 425.52 | 2025-04-11 | 2025-04-15 | 425.52 | Completed | 2025-04-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
82 | JMB | 147B/0 | ~ | 148/0 | 827.56 | TSE | 0 | 0 | Ready |  |  | 2025-04-04 | 2025-04-05 | 827.56 | 2025-04-13 | 2025-04-15 | 827.56 | Completed | 2025-04-01 |  | Muslehuddinn + GPJ |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
83 | JMB | 152/0 | ~ | 152A/0 | 1779.94 | TSE | 0 | 0 | Ready |  |  | 2025-04-03 | 2025-04-09 | 1779.94 | 2025-04-13 | 2025-04-15 | 1779.94 | Completed | 2025-04-01 |  | Alongir |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
84 | BAR | 270/0 | ~ | 270A/0 | 2821 | TSE | 0 | 0 | Ready |  |  | 2025-04-12 | 2025-04-14 | 2821 | 2025-04-14 | 2025-04-15 | 2821 | Completed | 2025-04-01 |  | Kamruddin & Deepak |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
85 | JMB | 145/0 | ~ | 145A/0 | 398 | Hotline | 0 | 0 | Ready |  |  | 2025-04-18 | 2025-04-23 | 398 | 2025-04-18 | 2025-04-23 | 398 | Completed | 2025-04-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
86 | BAR | 268/0 | ~ | 269/0 | 292 | Hotline | 0 | 0 | Ready |  |  | 2025-04-17 | 2025-04-19 | 292 | 2025-04-21 | 2025-04-23 | 292 | Completed | 2025-04-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
87 | BAR | 269/0 | ~ | 270/0 | 1237 | TSE | 0 | 0 | Ready |  |  | 2025-04-05 | 2025-04-08 | 1237 | 2025-04-18 | 2025-04-23 | 1237 | Completed | 2025-04-01 |  | Kamruddin & Maidul rahman |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
88 | BAR | 270A/0 | ~ | 271/0 | 268 | Manual | 0 | 0 | Ready |  |  | 2025-04-12 | 2025-04-15 | 268 | 2025-04-21 | 2025-04-25 | 268 | Completed | 2025-04-01 |  | Alamgir |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
89 | BAR | 271/0 | ~ | 272/0 | 2108 | TSE | 0 | 0 | Ready |  |  | 2025-04-18 | 2025-04-20 | 2108 | 2025-04-21 | 2025-04-25 | 2108 | Completed | 2025-04-01 |  | Kamruddin & Deepak |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
90 | JMB | 148/0 | ~ | 149/0 | 2993.72 | TSE | 0 | 0 | Ready |  |  | 2025-04-18 | 2025-04-21 | 2993.72 | 2025-04-24 | 2025-04-26 | 2993.72 | Completed | 2025-04-01 |  | Muslehuddin |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
91 | JMB | 149/0 | ~ | 150/0 | 808.76 | TSE | 0 | 0 | Ready |  |  | 2025-04-22 | 2025-04-23 | 808.76 | 2025-04-24 | 2025-04-26 | 808.76 | Completed | 2025-04-01 |  | Enamul Haque |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
92 | BAR | 162/0 | ~ | 163/0 | 401.68 | Manual | 0 | 0 | Ready |  |  | 2025-04-07 | 2025-04-13 | 401.68 | 2025-04-23 | 2025-04-26 | 401.68 | Completed | 2025-04-01 |  | Manik Sarkar |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
93 | JMB | 147A/0 | ~ | 147B/0 | 263 | Manual | 0 | 0 | Ready |  |  | 2025-04-30 | 2025-04-30 | 263 | 2025-04-30 | 2025-04-30 | 263 | Completed | 2025-04-01 |  | Enamul Haque | U/C 220 KV |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
94 | JMB | 135/0 | ~ | 135A/0 | 2997.64 | TSE | 0 | 0 | Ready |  |  | 2025-03-21 | 2025-03-24 | 2997.64 | 2025-04-28 | 2025-05-01 | 2997.64 | Completed | 2025-05-01 |  | RafikulAlam Construction |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
95 | BAR | 251/0 | ~ | 252/0 | 222 | Hotline | 0 | 0 | Ready |  |  | 2025-04-29 | 2025-05-01 | 222 | 2025-05-02 | 2025-05-04 | 222 | Completed | 2025-05-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
96 | JMB | 161/0 | ~ | 162/0 | 279.05 | Hotline | 0 | 0 | Ready |  |  | 2025-04-28 | 2025-05-06 | 279.05 | 2025-04-28 | 2025-05-06 | 279.05 | Completed | 2025-05-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
97 | BAR | 252/0 | ~ | 253/0 | 317 | Manual | 0 | 0 | Ready |  |  | 2025-04-17 | 2025-04-19 | 317 | 2025-05-04 | 2025-05-06 | 317 | Completed | 2025-05-01 |  | Deepak Sarkar |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
98 | BAR | 250/0 | ~ | 251/0 | 737 | Manual | 0 | 0 | Ready |  |  | 2025-05-04 | 2025-05-05 | 737 | 2025-05-08 | 2025-05-10 | 737 | Completed | 2025-05-01 |  | Deepak Sarkar |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
99 | BAR | 249/0 | ~ | 250/0 | 1368 | TSE | 0 | 0 | Ready |  |  | 2025-04-29 | 2025-05-03 | 1368 | 2025-05-09 | 2025-05-12 | 1368 | Completed | 2025-05-01 |  | Kamruddin |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
100 | JMB | 150A/0 | ~ | 151/0 | 1252.42 | TSE | 0 | 0 | Ready |  |  | 2025-04-26 | 2025-04-29 | 1252.42 | 2025-05-12 | 2025-05-15 | 1252.42 | Completed | 2025-05-01 |  | Alam Construction |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
101 | JMB | 151/0 | ~ | 152/0 | 403.35 | Manual | 0 | 0 | Ready |  |  | 2025-05-11 | 2025-05-15 | 403.35 | 2025-05-11 | 2025-05-15 | 403.35 | Completed | 2025-05-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
102 | JMB | 147/2 | ~ | 147A/0 | 2020.89 | TSE | 0 | 0 | Ready |  |  | 2025-05-16 | 2025-05-18 | 2020.89 | 2025-05-16 | 2025-05-18 | 2020.89 | Completed | 2025-05-01 |  | Rafikul Alam + Alam Const. + Enamul |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
103 | JMB | 140/0 | ~ | 141/0 | 249 | Manual | 0 | 0 | Ready |  |  | 2025-05-22 | 2025-05-22 | 249 | 2025-05-23 | 2025-05-23 | 249 | Completed | 2025-05-01 |  | Rafikul Alam + Alam Const. + Enamul + Manik sarkar |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
104 | JMB | 150/0 | ~ | 150/1 | 367 | Hotline | 0 | 0 | Ready |  |  | 2025-05-23 | 2025-05-25 | 367 | 2025-05-23 | 2025-05-26 | 367 | Completed | 2025-05-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
105 | JMB | 150/1 | ~ | 150A/0 | 1266.03 | TSE | 0 | 0 | Ready |  |  | 2025-05-06 | 2025-05-11 | 1266.03 | 2025-05-23 | 2025-05-26 | 1266.03 | Completed | 2025-05-01 |  | Alam Construction |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
106 | BAR | 156/0 | ~ | 157/0 | 240.53 | Manual | 0 | 0 | Ready |  |  | 2025-06-03 | 2025-06-04 | 240.53 | 2025-06-03 | 2025-06-04 | 240.53 | Completed | 2025-06-01 |  | Deepak Sarkar + Manik Sarkar |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
107 | BAR | 272/0 | ~ | 272/5 | 2053 | TSE | 0 | 0 | Ready |  | 2025-03-01 | 2025-03-12 | 2025-03-15 | 2053 | 2025-06-13 | 2025-06-15 | 2053 | Completed | 2025-06-01 |  | Kamruddin & Deepak Sarkar |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
108 | BAR | 155/0 | ~ | 156/0 | 2733.13 | TSE | 0 | 0 | Ready |  |  | 2025-06-06 | 2025-06-11 | 2733.13 | 2025-06-14 | 2025-06-20 | 2733.13 | Completed | 2025-06-01 |  | Deepak Sarkar + Manik Sarkar |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
109 | JMB | 152A/0 | ~ | 153/0 | 370.34 | Manual | 0 | 0 | Ready | 2025-08-25 | 2025-08-25 | 2025-09-02 | 2025-09-10 | 370.34 | 2025-09-06 | 2025-09-10 | 370.34 | Completed | 2025-09-01 |  | Alam Construction |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
110 | BAR | 158B/0 | ~ | 159/0 | 1253.83 | TSE | 0 | 0 | Ready |  |  | 2025-09-16 | 2025-09-27 | 1253.83 | 2025-10-02 | 2025-10-05 | 1253.83 | Completed | 2025-10-01 |  | Deepak Sarkar |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
111 | BAR | 158A/0 | ~ | 158B/0 | 481.57 | Hotline | 0 | 0 | Ready |  |  | 2025-10-07 | 2025-10-21 | 481.57 | 2025-10-07 | 2025-10-21 | 481.57 | Completed | 2025-10-01 |  | Dharmendra 1 |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
112 | BAR | 276/0 | ~ | Gty | 160 | Manual | 0 | 0 | Ready |  |  | 2025-10-18 | 2025-10-21 | 160 | 2025-10-18 | 2025-10-21 | 160 | Completed | 2025-10-01 |  | Bhola |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
113 | BAR | 158/0 | ~ | 158A/0 | 1130.57 | TSE | 0 | 0 | Ready |  |  | 2025-10-09 | 2025-10-13 | 1130.57 | 2025-10-17 | 2025-10-23 | 1130.57 | Completed | 2025-10-01 |  | Deepak Sarkar |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
114 | BAR | 192/0 | ~ | 193/0 | 376 | Manual | 0 | 0 | Ready |  |  | 2025-10-15 | 2025-10-23 | 376 | 2025-10-19 | 2025-10-23 | 376 | Completed | 2025-10-01 |  | Teklal Saw |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
115 | BAR | 193/0 | ~ | 194/0 | 241 | Hotline | 0 | 0 | Ready |  |  | 2025-10-21 | 2025-10-25 | 241 | 2025-10-21 | 2025-10-25 | 241 | Completed | 2025-10-01 |  | Upendra Giri 1 |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
116 | BAR | 194/0 | ~ | 195/0 | 182 | Manual | 0 | 0 | Ready |  |  | 2025-10-24 | 2025-10-29 | 182 | 2025-10-24 | 2025-10-29 | 182 | Completed | 2025-10-01 |  | Enamul Haque |  |  | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
117 | BAR | 157/0 | ~ | 158/0 | 1575.8 | TSE | 0 | 0 | Ready | [8 empty] | WIP |  |  | Deepak Sarkar |  |  | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
118 | BAR | 168/0 | ~ | 169/0 | 1044 | TSE | 0 | 0 | Ready | [8 empty] | WIP |  |  | Sindhu Const. |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
119 | BAR | 177/0 | ~ | 178/0 | 405 | Manual | 0 | 0 | Ready | [8 empty] | WIP |  |  | Ruhul Amin |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
120 | BAR | 178/0 | ~ | 179/0 | 278 | Manual | 0 | 0 | Ready | [8 empty] | WIP |  |  | Ruhul Amin |  |  | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
121 | BAR | 189/0 | ~ | 190/0 | 829 | Manual | 0 | 0 | Ready | [8 empty] | WIP |  |  | Md Anwar |  |  | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
122 | BAR | 191/0 | ~ | 191A/0 | 1477 | TSE | 0 | 0 | Ready |  |  | 2025-10-22 | 2025-10-25 | 1477 | 2025-10-25 |  |  | WIP |  |  | Alam Construction |  |  | Vadodara | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
123 | BAR | 191A/0 | ~ | 192/0 | 612 | Manual | 0 | 0 | Ready |  |  | 2025-10-12 | 2025-10-19 | 612 | 2025-10-24 |  |  | WIP |  |  | Md Anwar |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
124 | BAR | 195/0 | ~ | 195A/0 | 2481 | TSE | 0 | 0 | Ready |  |  | 2025-10-19 | 2025-10-26 | 2481 |  |  |  | WIP |  |  | Enamul Haque |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
125 | BAR | 195A/0 | ~ | 196/0 | 1542 | TSE | 0 | 0 | Ready |  |  | 2025-10-12 | 2025-10-18 | 1542 |  |  |  | WIP |  |  | Muslehuddin |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
126 | BAR | 196/0 | ~ | 197/0 | 246 | Manual | 0 | 0 | Ready | [8 empty] | WIP |  |  | Giyash |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
127 | BAR | 197/0 | ~ | 198/0 | 1740 | TSE | 0 | 0 | Ready | [8 empty] | WIP |  |  | Muslehuddin |  |  | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
128 | BAR | 204/0 | ~ | 205/0 | 198 | Hotline | 0 | 0 | Ready | [8 empty] | WIP |  |  | Dharmendra 2 |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
129 | BAR | 248/0 | ~ | 249/0 | 2525 | TSE | 0 | 0 | Ready | [8 empty] | WIP |  |  | Kamaruddin |  |  | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
130 | BAR | 274/0 | ~ | 275/0 | 402 | Manual | 0 | 0 | Ready |  |  | 2025-10-23 | 2025-10-27 | 402 |  |  |  | WIP |  |  | Bhola |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
131 | BAR | 275/0 | ~ | 276/0 | 177 | Hotline | 0 | 0 | Ready | [8 empty] | WIP |  |  | Dharmendra 1 |  |  | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
132 | JMB | 101/0 | ~ | 102/0 | 665 | Manual | 0 | 102/0, | Not Ready | [14 empty] | Bharuch | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
133 | JMB | 102/0 | ~ | 103/0 | 685 | Manual | 0 | 102/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
134 | JMB | 103/0 | ~ | 104/0 | 680.12 | Manual | 103/0, | 103/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
135 | JMB | 104/0 | ~ | 105/0 | 386.59 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
136 | JMB | 105/0 | ~ | 106/0 | 256.45 | Manual | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
137 | BAR | 153/0 | ~ | 154/0 | 620 | Manual | 154/0, | 154/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
138 | BAR | 154/0 | ~ | 154/1 | 620 | Manual | 0 | 154/1 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
139 | BAR | 154/1 | ~ | 155/0 | 415 | Manual | 0 | 154/1 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
140 | BAR | 159/0 | ~ | 159/2 | 720 | Manual | 0 | 159/2 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
141 | BAR | 159/2 | ~ | 160/0 | 1152.2 | TSE | 0 | 160/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
142 | BAR | 160/0 | ~ | 161/0 | 229.82 | Hotline | 0 | 160/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
143 | BAR | 165/0 | ~ | 165/4 | 1613 | TSE | 165/4 | 165/4 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
144 | BAR | 165/4 | ~ | 165/5 | 538 | Manual | 165/5 | 165/5 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
145 | BAR | 165/5 | ~ | 166/0 | 423 | Manual | 166/0, | 166/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
146 | BAR | 166/0 | ~ | 167/0 | 270 | Hotline | 167/0, | 167/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
147 | BAR | 167/0 | ~ | 167/1 | 342 | Manual | 167/1 | 167/1 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
148 | BAR | 167/1 | ~ | 168/0 | 1338 | TSE | 167/1 | 167/1 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
149 | BAR | 169/0 | ~ | 171/0 | 433 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
150 | BAR | 171/0 | ~ | 172/0 | 274 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
151 | BAR | 172/0 | ~ | 173/0 | 1123 | TSE |  | 172/1,173/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
152 | BAR | 173/0 | ~ | 174/0 | 232 | Hotline |  | 173/0, ,174/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
153 | BAR | 174/0 | ~ | 174/1 | 381 | Manual |  | 174/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
154 | BAR | 174/1 | ~ | 175/0 | 289 | Manual | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
155 | BAR | 175/0 | ~ | 176/0 | 979 | TSE |  | 175/1 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
156 | BAR | 176/0 | ~ | 177/0 | 232 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
157 | BAR | 179/0 | ~ | 180/0 | 264 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
158 | BAR | 180/0 | ~ | 181/0 | 263 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
159 | BAR | 181/0 | ~ | 182/0 | 1778 | TSE | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
160 | BAR | 182/0 | ~ | 182A/0 | 246 | Hotline | 0 | 182A/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
161 | BAR | 182A/0 | ~ | 183/0 | 430 | Manual | 0 | 182A/0, ,183/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
162 | BAR | 183/0 | ~ | 184/0 | 234 | Hotline | 0 | 183/0, ,184/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
163 | BAR | 184/0 | ~ | 184/1 | 468 | Manual | 0 | 184/0, ,184/1 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
164 | BAR | 184/1 | ~ | 185/0 | 412 | Manual | 0 | 184/1,185/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
165 | BAR | 185/0 | ~ | 186/0 | 820 | Manual | 0 | 185/1,185/0, 1,86/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
166 | BAR | 186/0 | ~ | 187/0 | 399 | Hotline | 0 | 186/0, ,187/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
167 | BAR | 187/0 | ~ | 188/0 | 1510 | TSE | 0 | 187/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
168 | BAR | 188/0 | ~ | 189/0 | 218 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
169 | BAR | 190/0 | ~ | 191/0 | 329 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
170 | BAR | 198/0 | ~ | 199/0 | 1149 | TSE | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
171 | BAR | 199/0 | ~ | 200/0 | 221 | Hotline | 0 | 200/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
172 | BAR | 200/0 | ~ | 201/0 | 204 | Hotline | 0 | 200/0, ,201/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
173 | BAR | 201/0 | ~ | 201/1 | 532 | Manual | 0 | 201/0, ,201/1 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
174 | BAR | 201/1 | ~ | 202/0 | 367 | Manual | 0 | 201/1,202/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
175 | BAR | 202/0 | ~ | 203/0 | 788 | Manual | 0 | 202/0, ,203/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
176 | BAR | 203/0 | ~ | 203/1 | 460 | Manual | 0 | 203/0, ,203/1 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
177 | BAR | 203/1 | ~ | 204/0 | 425 | Manual | 0 | 203/1 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
178 | BAR | 205/0 | ~ | 206/0 | 1063 | TSE | 0 | 206/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
179 | BAR | 206/0 | ~ | 208/0 | 412 | Hotline | 0 | 206/0, ,208/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
180 | BAR | 208/0 | ~ | 209/0 | 410 | Manual | 0 | 208/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
181 | BAR | 209/0 | ~ | 210/0 | 699 | Manual | 0 | 209/1,210/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
182 | BAR | 210/0 | ~ | 211/0 | 223 | Hotline | 0 | 210/0, ,211/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
183 | BAR | 211/0 | ~ | 211A/0 | 1158 | TSE | 0 | 211/0, ,211A/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
184 | BAR | 211A/0 | ~ | 212/0 | 1024 | TSE | 0 | 211A/0, 211A/1, 211A/2, 212/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
185 | BAR | 212/0 | ~ | 213/0 | 248 | Hotline | 0 | 212/0, ,213/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
186 | BAR | 213/0 | ~ | 214/0 | 771 | Manual | 0 | 213/1,213/0, ,214/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
187 | BAR | 214/0 | ~ | 215/0 | 713 | Manual | 0 | 214/0,214/1 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
188 | BAR | 215/0 | ~ | 216/0 | 632 | Hotline | 0 | 215/1, ,216/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
189 | BAR | 216/0 | ~ | 217/0 | 456 | Hotline | 0 | 216/0, ,217/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
190 | BAR | 217/0 | ~ | 217A/0 | 347 | Hotline | 0 | 217/0, ,217A/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
191 | BAR | 217A/0 | ~ | 218/0 | 1174 | TSE | 0 | 217A/0, ,218/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
192 | BAR | 218/0 | ~ | 219/0 | 822 | Manual | 0 | 218/1, 218/0, 219/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
193 | BAR | 219/0 | ~ | 220/0 | 242 | Hotline | 0 | 219/0, 220/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
194 | BAR | 220/0 | ~ | 221/0 | 735 | Manual | 0 | 220/1,222/0, ,221/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
195 | BAR | 221/0 | ~ | 222/0 | 222 | Hotline | 0 | 221/0, ,222/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
196 | BAR | 222/0 | ~ | 222/1 | 388 | Manual | 0 | 222/0, 222/1 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
197 | BAR | 222/1 | ~ | 223/0 | 183 | Hotline | 0 | 222/1,223/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
198 | BAR | 223/0 | ~ | 224/0 | 1398 | TSE | 0 | 223/0, 223/2, 223/3 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
199 | BAR | 224/0 | ~ | 225/0 | 235 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
200 | BAR | 225/0 | ~ | 226/0 | 678 | Manual | 0 | 225/1, 226/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
201 | BAR | 226/0 | ~ | 227/0 | 417 | Manual | 0 | 226/0, ,227/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
202 | BAR | 227/0 | ~ | 228/0 | 239 | Manual | 0 | 227/0, ,228/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
203 | BAR | 228/0 | ~ | 229/0 | 196 | Hotline | 0 | 228/0, ,229/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
204 | BAR | 229/0 | ~ | 229/1 | 549 | Manual | 0 | 229/0, ,229/1 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
205 | BAR | 229/1 | ~ | 230/0 | 1884 | TSE | 0 | 229/1230/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
206 | BAR | 230/0 | ~ | 231/0 | 227 | Hotline | 0 | 230/0 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
207 | BAR | 231/0 | ~ | 232/0 | 419 | Manual | 0 | 232/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
208 | BAR | 232/0 | ~ | 233/0 | 195 | Hotline | 0 | 232/0 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
209 | BAR | 233/0 | ~ | 234/0 | 305 | Manual | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
210 | BAR | 234/0 | ~ | 235/0 | 328 | Hotline | 0 | 235/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
211 | BAR | 235/0 | ~ | 236/0 | 305 | Manual | 0 | 235/0 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
212 | BAR | 236/0 | ~ | 237/0 | 280 | Hotline | 0 | 237/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
213 | BAR | 237/0 | ~ | 239/0 | 2519 | TSE | 0 | 239/0 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
214 | BAR | 239/0 | ~ | 240/0 | 248 | Hotline | 0 | 239/0, 240/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
215 | BAR | 240/0 | ~ | 241/0 | 207 | Manual | 0 | 240/0 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
216 | BAR | 241/0 | ~ | 242/0 | 246 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
217 | BAR | 242/0 | ~ | 243/0 | 1335 | TSE | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
218 | BAR | 243/0 | ~ | 244/0 | 250 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
219 | BAR | 244/0 | ~ | 244/1 | 494 | Manual | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
220 | BAR | 244/1 | ~ | 245/0 | 427 | Manual | 0 | 245/0, | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
221 | BAR | 245/0 | ~ | 246/0 | 569 | Manual | 0 | 245/0 | Not Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
222 | BAR | 246/0 | ~ | 247/0 | 240 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
223 | BAR | 247/0 | ~ | 248/0 | 1957 | TSE | 0 | 0 | Ready | [14 empty] | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
224 | BAR | 272/5 | ~ | 272A/0 | 1202 | TSE | 0 | 0 | Ready | [14 empty] | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
225 | BAR | 272A/0 | ~ | 273/0 | 2944 | TSE | 0 | 0 | Ready | [14 empty] | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
226 | BAR | 273/0 | ~ | 274/0 | 1153 | TSE | 0 | 0 | Ready | [14 empty] | Navsari | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
[25 empty] | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
|  |  |  | Total | 177.3447 | [19 empty] | TA 325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx

## Daily
project | gang_name | date | month | from_ap | to_ap | method | section_readiness | po_id | fs_start_date | fs_complete_date | status | length_km | daily_km | row_id | project_name | source_file
TA 325 | Muslehuddin | 2024-08-12 | 2024-08-01 | 112/0 | 113/0 | Manual | Ready | 375.84 | 2024-08-17 | 2024-08-19 | Completed | 0.37584 | 0.04698 | stringing:bd83deececd68898 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-08-13 | 2024-08-01 | 112/0 | 113/0 | Manual | Ready | 375.84 | 2024-08-17 | 2024-08-19 | Completed | 0.37584 | 0.04698 | stringing:95f6218bb552c202 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-08-14 | 2024-08-01 | 112/0 | 113/0 | Manual | Ready | 375.84 | 2024-08-17 | 2024-08-19 | Completed | 0.37584 | 0.04698 | stringing:996209f04f75ff9e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-08-15 | 2024-08-01 | 112/0 | 113/0 | Manual | Ready | 375.84 | 2024-08-17 | 2024-08-19 | Completed | 0.37584 | 0.04698 | stringing:deac67b7ff435e0d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-08-16 | 2024-08-01 | 112/0 | 113/0 | Manual | Ready | 375.84 | 2024-08-17 | 2024-08-19 | Completed | 0.37584 | 0.04698 | stringing:4884e0e776b10593 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-08-17 | 2024-08-01 | 112/0 | 113/0 | Manual | Ready | 375.84 | 2024-08-17 | 2024-08-19 | Completed | 0.37584 | 0.04698 | stringing:3f011fea2788659e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-08-18 | 2024-08-01 | 112/0 | 113/0 | Manual | Ready | 375.84 | 2024-08-17 | 2024-08-19 | Completed | 0.37584 | 0.04698 | stringing:0f92d395bfc04906 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-08-19 | 2024-08-01 | 112/0 | 113/0 | Manual | Ready | 375.84 | 2024-08-17 | 2024-08-19 | Completed | 0.37584 | 0.04698 | stringing:e65fb67d58bd3aec | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-23 | 2024-09-01 | 111/0 | 112/0 | Manual | Ready | 341.9 | 2024-10-02 | 2024-10-04 | Completed | 0.3419 | 0.028492 | stringing:58987f982e6a3edf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-24 | 2024-09-01 | 111/0 | 112/0 | Manual | Ready | 341.9 | 2024-10-02 | 2024-10-04 | Completed | 0.3419 | 0.028492 | stringing:fd0ddf5d8bbe6ddf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-25 | 2024-09-01 | 111/0 | 112/0 | Manual | Ready | 341.9 | 2024-10-02 | 2024-10-04 | Completed | 0.3419 | 0.028492 | stringing:8d540f397eb8352c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-26 | 2024-09-01 | 111/0 | 112/0 | Manual | Ready | 341.9 | 2024-10-02 | 2024-10-04 | Completed | 0.3419 | 0.028492 | stringing:fcd76faf957ed47f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-27 | 2024-09-01 | 111/0 | 112/0 | Manual | Ready | 341.9 | 2024-10-02 | 2024-10-04 | Completed | 0.3419 | 0.028492 | stringing:e103def7608f4242 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-28 | 2024-09-01 | 111/0 | 112/0 | Manual | Ready | 341.9 | 2024-10-02 | 2024-10-04 | Completed | 0.3419 | 0.028492 | stringing:c201f97c05b99b19 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-29 | 2024-09-01 | 111/0 | 112/0 | Manual | Ready | 341.9 | 2024-10-02 | 2024-10-04 | Completed | 0.3419 | 0.028492 | stringing:2372671f80cfef8c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-30 | 2024-09-01 | 111/0 | 112/0 | Manual | Ready | 341.9 | 2024-10-02 | 2024-10-04 | Completed | 0.3419 | 0.028492 | stringing:fdec9ae21e6d211d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-01 | 2024-10-01 | 111/0 | 112/0 | Manual | Ready | 341.9 | 2024-10-02 | 2024-10-04 | Completed | 0.3419 | 0.028492 | stringing:8b6bde0438ed67c5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-02 | 2024-10-01 | 111/0 | 112/0 | Manual | Ready | 341.9 | 2024-10-02 | 2024-10-04 | Completed | 0.3419 | 0.028492 | stringing:eab707bf22ef1df2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-03 | 2024-10-01 | 111/0 | 112/0 | Manual | Ready | 341.9 | 2024-10-02 | 2024-10-04 | Completed | 0.3419 | 0.028492 | stringing:9ef0bb2255cead0b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-04 | 2024-10-01 | 111/0 | 112/0 | Manual | Ready | 341.9 | 2024-10-02 | 2024-10-04 | Completed | 0.3419 | 0.028492 | stringing:6063ad0a103785d0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-11 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:2464a44be040a9d1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-12 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:548279fb26afee96 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-13 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:9540c5a526cb4db6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-14 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:3840dbcae89f6380 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-15 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:c2a287cbb21d9730 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-16 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:f459c67bc8c41c48 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-17 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:b3cada873bba93a5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-18 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:1944bac4f5536abb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-19 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:b2c8b63eb72214cf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-20 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:9ca2912e8c594281 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-21 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:af50297a102a1814 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-22 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:d9021265e8d4f352 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-23 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:6e471a677d3ce185 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-24 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:9e645e6c5c52671a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-25 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:1c8036eaf56a9c71 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-26 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:e8a645e25d4a447a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-27 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:30eaf349ac744ed5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-28 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:efc3f171bcd1fd4d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-29 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:97588ee02cf2d2b5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-30 | 2024-09-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:20e60f734747220d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-01 | 2024-10-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:641e471f9811a7be | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-02 | 2024-10-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:7370677a729d0753 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-03 | 2024-10-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:a2c2e27b20d253a5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-04 | 2024-10-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:4b598872825c904c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-05 | 2024-10-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:1e519ffa251f2dd2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-06 | 2024-10-01 | 110/0 | 111/0 | Manual | Ready | 312.14 | 2024-10-04 | 2024-10-06 | Completed | 0.31214 | 0.012005 | stringing:4a59e22630643a06 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-09-26 | 2024-09-01 | 113/0 | 114/0 | Manual | Ready | 297.05 | 2024-10-01 | 2024-10-06 | Completed | 0.29705 | 0.027005 | stringing:1073f2ef0c4a6a2a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-09-27 | 2024-09-01 | 113/0 | 114/0 | Manual | Ready | 297.05 | 2024-10-01 | 2024-10-06 | Completed | 0.29705 | 0.027005 | stringing:5a5afd1c3bf5b334 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-09-28 | 2024-09-01 | 113/0 | 114/0 | Manual | Ready | 297.05 | 2024-10-01 | 2024-10-06 | Completed | 0.29705 | 0.027005 | stringing:18458d2f75a4a6e4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-09-29 | 2024-09-01 | 113/0 | 114/0 | Manual | Ready | 297.05 | 2024-10-01 | 2024-10-06 | Completed | 0.29705 | 0.027005 | stringing:5715acc0fe8172ae | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-09-30 | 2024-09-01 | 113/0 | 114/0 | Manual | Ready | 297.05 | 2024-10-01 | 2024-10-06 | Completed | 0.29705 | 0.027005 | stringing:d6716d5a7509909c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-01 | 2024-10-01 | 113/0 | 114/0 | Manual | Ready | 297.05 | 2024-10-01 | 2024-10-06 | Completed | 0.29705 | 0.027005 | stringing:62354582ad63db2a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-02 | 2024-10-01 | 113/0 | 114/0 | Manual | Ready | 297.05 | 2024-10-01 | 2024-10-06 | Completed | 0.29705 | 0.027005 | stringing:2176b59954187e64 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-03 | 2024-10-01 | 113/0 | 114/0 | Manual | Ready | 297.05 | 2024-10-01 | 2024-10-06 | Completed | 0.29705 | 0.027005 | stringing:2dbb4fa6bd74fa64 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-04 | 2024-10-01 | 113/0 | 114/0 | Manual | Ready | 297.05 | 2024-10-01 | 2024-10-06 | Completed | 0.29705 | 0.027005 | stringing:24233d0246779327 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-05 | 2024-10-01 | 113/0 | 114/0 | Manual | Ready | 297.05 | 2024-10-01 | 2024-10-06 | Completed | 0.29705 | 0.027005 | stringing:b55112220371965a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-06 | 2024-10-01 | 113/0 | 114/0 | Manual | Ready | 297.05 | 2024-10-01 | 2024-10-06 | Completed | 0.29705 | 0.027005 | stringing:c620b9ca8ea6db71 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-06 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:7faf9122d09d8df2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-07 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:3eb764155521f4ce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-08 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:c525b545d0c814a3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-09 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:72104f950f6a9efe | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-10 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:3078629663d3cba4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-11 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:b352ab3c7c4b6b12 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-12 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:5c0c072374cc234a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-13 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:c62dcd1705eb42d7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-14 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:7beb07ce1a014dd9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-15 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:6b1a3f1124b04047 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-16 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:9cf9df3dcc572b79 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-17 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:5e2d8d2e80d37a81 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-18 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:d88cdffa389cf9d2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-19 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:c785334d6ff65ea4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-20 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:26971d91687b29d8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-21 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:79c1499d45abeea4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-22 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:5128a1c244a88eb4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-23 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:a58be34d425d126a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-24 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:38e78a14a84f2a90 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-25 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:4e5b5cab969d068e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-26 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:3fa049bcc29a4b91 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-27 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:e2341e2fd383de4a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-28 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:45abadb5a793eff0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-29 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:da6e82366c407ce6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-09-30 | 2024-09-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:1d1875e32efda915 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-01 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:a4cf16998cbbf1d0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-02 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:7b44f853c61d9a69 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-03 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:0d51ad32cbd4d177 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-04 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:568b93c48597fd20 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-05 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:1fb1635ac83bb1b2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-06 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:5bfec52cd6ac1518 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-07 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:93d12f6ffc48e132 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-08 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:5733721d6a478259 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-09 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:2a1f3a4a36ea422f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-10 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:cc17c6d97f8cea47 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-11 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:8b8b03319046113c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-12 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:b6ec68f57c367a5f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-13 | 2024-10-01 | 109/0 | 110/0 | Manual | Ready | 342.42 | 2024-10-10 | 2024-10-13 | Completed | 0.34242 | 0.0090111 | stringing:2329a8aad6896d95 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-15 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:10b9c2b99e547ac5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-16 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:0221bbc3c27fd3ec | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-17 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:cc251a62b14db3ec | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-18 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:aa35f8c726fa126d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-19 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:91b4cb163bf304aa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-20 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:7fe60fafb1f5a8fe | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-21 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:2505da76baec899c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-22 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:bf0a051dc6e33784 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-23 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:e5c8a7612aa75c54 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-24 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:ff674570d0476a15 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-25 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:068e0f5b16f907ba | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-26 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:14cf319233b4647f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-10-27 | 2024-10-01 | 116/0 | 116A/0 | Manual | Ready | 243.41 | 2024-10-26 | 2024-10-27 | Completed | 0.24341 | 0.018724 | stringing:5afa98fb598ff90e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-17 | 2024-10-01 | 108/0 | 109/0 | Manual | Ready | 277.2 | 2024-10-25 | 2024-10-28 | Completed | 0.2772 | 0.0231 | stringing:d6f35ef6e6cb6f13 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-18 | 2024-10-01 | 108/0 | 109/0 | Manual | Ready | 277.2 | 2024-10-25 | 2024-10-28 | Completed | 0.2772 | 0.0231 | stringing:99335f735ecafd01 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-19 | 2024-10-01 | 108/0 | 109/0 | Manual | Ready | 277.2 | 2024-10-25 | 2024-10-28 | Completed | 0.2772 | 0.0231 | stringing:583828e78e445b9b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-20 | 2024-10-01 | 108/0 | 109/0 | Manual | Ready | 277.2 | 2024-10-25 | 2024-10-28 | Completed | 0.2772 | 0.0231 | stringing:98bdb38e8aa17294 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-21 | 2024-10-01 | 108/0 | 109/0 | Manual | Ready | 277.2 | 2024-10-25 | 2024-10-28 | Completed | 0.2772 | 0.0231 | stringing:4f9f33d84bb2d812 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-22 | 2024-10-01 | 108/0 | 109/0 | Manual | Ready | 277.2 | 2024-10-25 | 2024-10-28 | Completed | 0.2772 | 0.0231 | stringing:a14cf04dfc9ef590 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-23 | 2024-10-01 | 108/0 | 109/0 | Manual | Ready | 277.2 | 2024-10-25 | 2024-10-28 | Completed | 0.2772 | 0.0231 | stringing:b81fe96f45b8cef9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-24 | 2024-10-01 | 108/0 | 109/0 | Manual | Ready | 277.2 | 2024-10-25 | 2024-10-28 | Completed | 0.2772 | 0.0231 | stringing:11a9f17031516162 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-25 | 2024-10-01 | 108/0 | 109/0 | Manual | Ready | 277.2 | 2024-10-25 | 2024-10-28 | Completed | 0.2772 | 0.0231 | stringing:d7626f135e7bc323 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-26 | 2024-10-01 | 108/0 | 109/0 | Manual | Ready | 277.2 | 2024-10-25 | 2024-10-28 | Completed | 0.2772 | 0.0231 | stringing:23e9a120df547f71 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-27 | 2024-10-01 | 108/0 | 109/0 | Manual | Ready | 277.2 | 2024-10-25 | 2024-10-28 | Completed | 0.2772 | 0.0231 | stringing:bd04485271cdf9cd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-28 | 2024-10-01 | 108/0 | 109/0 | Manual | Ready | 277.2 | 2024-10-25 | 2024-10-28 | Completed | 0.2772 | 0.0231 | stringing:54084c9d8cfa51f0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-30 | 2024-10-01 | 107/0 | 108/0 | Manual | Ready | 558.88 | 2024-11-04 | 2024-11-07 | Completed | 0.55888 | 0.062098 | stringing:1b95cc53b0f4c52b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-10-31 | 2024-10-01 | 107/0 | 108/0 | Manual | Ready | 558.88 | 2024-11-04 | 2024-11-07 | Completed | 0.55888 | 0.062098 | stringing:3c3b8b6931884a22 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-01 | 2024-11-01 | 107/0 | 108/0 | Manual | Ready | 558.88 | 2024-11-04 | 2024-11-07 | Completed | 0.55888 | 0.062098 | stringing:6ef7e3470c9c564f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-02 | 2024-11-01 | 107/0 | 108/0 | Manual | Ready | 558.88 | 2024-11-04 | 2024-11-07 | Completed | 0.55888 | 0.062098 | stringing:3f4bfca93f2e160e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-03 | 2024-11-01 | 107/0 | 108/0 | Manual | Ready | 558.88 | 2024-11-04 | 2024-11-07 | Completed | 0.55888 | 0.062098 | stringing:e17fd0105be24110 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-04 | 2024-11-01 | 107/0 | 108/0 | Manual | Ready | 558.88 | 2024-11-04 | 2024-11-07 | Completed | 0.55888 | 0.062098 | stringing:4e505f0f5126508d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-05 | 2024-11-01 | 107/0 | 108/0 | Manual | Ready | 558.88 | 2024-11-04 | 2024-11-07 | Completed | 0.55888 | 0.062098 | stringing:d506b1631d551147 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-06 | 2024-11-01 | 107/0 | 108/0 | Manual | Ready | 558.88 | 2024-11-04 | 2024-11-07 | Completed | 0.55888 | 0.062098 | stringing:1f0fef0dae0278dd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-07 | 2024-11-01 | 107/0 | 108/0 | Manual | Ready | 558.88 | 2024-11-04 | 2024-11-07 | Completed | 0.55888 | 0.062098 | stringing:cca896d3dbdb8e34 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-10-29 | 2024-10-01 | 133/0 | 133A/0 | TSE | Ready | 2267.72 | 2024-11-03 | 2024-11-07 | Completed | 2.2677 | 0.22677 | stringing:e167fc9202fbf12e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-10-30 | 2024-10-01 | 133/0 | 133A/0 | TSE | Ready | 2267.72 | 2024-11-03 | 2024-11-07 | Completed | 2.2677 | 0.22677 | stringing:1cc8590001204491 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-10-31 | 2024-10-01 | 133/0 | 133A/0 | TSE | Ready | 2267.72 | 2024-11-03 | 2024-11-07 | Completed | 2.2677 | 0.22677 | stringing:c0c15dd0236a4f6a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-01 | 2024-11-01 | 133/0 | 133A/0 | TSE | Ready | 2267.72 | 2024-11-03 | 2024-11-07 | Completed | 2.2677 | 0.22677 | stringing:356d10c7f9a4ee31 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-02 | 2024-11-01 | 133/0 | 133A/0 | TSE | Ready | 2267.72 | 2024-11-03 | 2024-11-07 | Completed | 2.2677 | 0.22677 | stringing:dad16a4f03a20c03 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-03 | 2024-11-01 | 133/0 | 133A/0 | TSE | Ready | 2267.72 | 2024-11-03 | 2024-11-07 | Completed | 2.2677 | 0.22677 | stringing:115541fca5618b30 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-04 | 2024-11-01 | 133/0 | 133A/0 | TSE | Ready | 2267.72 | 2024-11-03 | 2024-11-07 | Completed | 2.2677 | 0.22677 | stringing:fc9ecde5bc4db6ec | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-05 | 2024-11-01 | 133/0 | 133A/0 | TSE | Ready | 2267.72 | 2024-11-03 | 2024-11-07 | Completed | 2.2677 | 0.22677 | stringing:17debe54fb9a5dce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-06 | 2024-11-01 | 133/0 | 133A/0 | TSE | Ready | 2267.72 | 2024-11-03 | 2024-11-07 | Completed | 2.2677 | 0.22677 | stringing:ca8c742117aaeb2c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-07 | 2024-11-01 | 133/0 | 133A/0 | TSE | Ready | 2267.72 | 2024-11-03 | 2024-11-07 | Completed | 2.2677 | 0.22677 | stringing:2f980d43e1c70134 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-02 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:d5d61536d2e36088 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-03 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:6d403f93102281bb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-04 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:dcca7a0bbce80acf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-05 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:ba3f1e1214226f9d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-06 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:c7eb9bce6406c88a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-07 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:cc7db1f737159160 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-08 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:7e988df815ec1f6c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-09 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:9dc4a1810566a79b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-10 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:72c588cb0e478c83 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-11 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:57863cbfff595a2c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-12 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:18a2f7fa36bbb73e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-13 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:a178d61804a833ec | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-14 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:8284f7c2101a5f0c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-15 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:f7d40e29f634dd71 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-16 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:abf38ae5f51a7002 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-17 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:e4d94581d09f87bc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-18 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:f164f697e2e5fbcb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-11-19 | 2024-11-01 | 121/0 | 122/0 | Manual | Ready | 525.49 | 2024-11-18 | 2024-11-19 | Completed | 0.52549 | 0.029194 | stringing:382d8073bf8b5510 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-16 | 2024-11-01 | 129A/0 | 130/0 | TSE | Ready | 1182.12 | 2024-11-21 | 2024-11-22 | Completed | 1.1821 | 0.16887 | stringing:02874d52a606c1ca | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-17 | 2024-11-01 | 129A/0 | 130/0 | TSE | Ready | 1182.12 | 2024-11-21 | 2024-11-22 | Completed | 1.1821 | 0.16887 | stringing:7f566021e6e93c74 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-18 | 2024-11-01 | 129A/0 | 130/0 | TSE | Ready | 1182.12 | 2024-11-21 | 2024-11-22 | Completed | 1.1821 | 0.16887 | stringing:caf15f1c99c027bc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-19 | 2024-11-01 | 129A/0 | 130/0 | TSE | Ready | 1182.12 | 2024-11-21 | 2024-11-22 | Completed | 1.1821 | 0.16887 | stringing:f0e10d63f1e0a28a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-20 | 2024-11-01 | 129A/0 | 130/0 | TSE | Ready | 1182.12 | 2024-11-21 | 2024-11-22 | Completed | 1.1821 | 0.16887 | stringing:17d0192a31c3cb0a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-21 | 2024-11-01 | 129A/0 | 130/0 | TSE | Ready | 1182.12 | 2024-11-21 | 2024-11-22 | Completed | 1.1821 | 0.16887 | stringing:3aa0250cd6db9a48 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul | 2024-11-22 | 2024-11-01 | 129A/0 | 130/0 | TSE | Ready | 1182.12 | 2024-11-21 | 2024-11-22 | Completed | 1.1821 | 0.16887 | stringing:b91888241481e20c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-15 | 2024-11-01 | 106B/0 | 107/0 | TSE | Ready | 1148.24 | 2024-11-20 | 2024-11-23 | Completed | 1.1482 | 0.12758 | stringing:8c3996342128920d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-16 | 2024-11-01 | 106B/0 | 107/0 | TSE | Ready | 1148.24 | 2024-11-20 | 2024-11-23 | Completed | 1.1482 | 0.12758 | stringing:e4a37763a7605c49 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-17 | 2024-11-01 | 106B/0 | 107/0 | TSE | Ready | 1148.24 | 2024-11-20 | 2024-11-23 | Completed | 1.1482 | 0.12758 | stringing:4b5eb9dcb8343c2b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-18 | 2024-11-01 | 106B/0 | 107/0 | TSE | Ready | 1148.24 | 2024-11-20 | 2024-11-23 | Completed | 1.1482 | 0.12758 | stringing:10174ba6f61d8b18 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-19 | 2024-11-01 | 106B/0 | 107/0 | TSE | Ready | 1148.24 | 2024-11-20 | 2024-11-23 | Completed | 1.1482 | 0.12758 | stringing:8efba79fb1e15ae9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-20 | 2024-11-01 | 106B/0 | 107/0 | TSE | Ready | 1148.24 | 2024-11-20 | 2024-11-23 | Completed | 1.1482 | 0.12758 | stringing:0228b2d116353d9e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-21 | 2024-11-01 | 106B/0 | 107/0 | TSE | Ready | 1148.24 | 2024-11-20 | 2024-11-23 | Completed | 1.1482 | 0.12758 | stringing:c7a0dd59234f7e72 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-22 | 2024-11-01 | 106B/0 | 107/0 | TSE | Ready | 1148.24 | 2024-11-20 | 2024-11-23 | Completed | 1.1482 | 0.12758 | stringing:0b2bae5e2e377fd4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-11-23 | 2024-11-01 | 106B/0 | 107/0 | TSE | Ready | 1148.24 | 2024-11-20 | 2024-11-23 | Completed | 1.1482 | 0.12758 | stringing:1ce1791f7c6bb45a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-23 | 2024-11-01 | 122/0 | 123/0 | Hotline | Ready | 328.32 | 2024-11-28 | 2024-11-30 | Completed | 0.32832 | 0.04104 | stringing:bb0954a88a651079 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-24 | 2024-11-01 | 122/0 | 123/0 | Hotline | Ready | 328.32 | 2024-11-28 | 2024-11-30 | Completed | 0.32832 | 0.04104 | stringing:257dbf858fe4cd4c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-25 | 2024-11-01 | 122/0 | 123/0 | Hotline | Ready | 328.32 | 2024-11-28 | 2024-11-30 | Completed | 0.32832 | 0.04104 | stringing:12616d05e6ccd0c1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-26 | 2024-11-01 | 122/0 | 123/0 | Hotline | Ready | 328.32 | 2024-11-28 | 2024-11-30 | Completed | 0.32832 | 0.04104 | stringing:57adcee35ba671c3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-27 | 2024-11-01 | 122/0 | 123/0 | Hotline | Ready | 328.32 | 2024-11-28 | 2024-11-30 | Completed | 0.32832 | 0.04104 | stringing:04bdad5f95950a2a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-28 | 2024-11-01 | 122/0 | 123/0 | Hotline | Ready | 328.32 | 2024-11-28 | 2024-11-30 | Completed | 0.32832 | 0.04104 | stringing:a28d37f2bd71a7a2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-29 | 2024-11-01 | 122/0 | 123/0 | Hotline | Ready | 328.32 | 2024-11-28 | 2024-11-30 | Completed | 0.32832 | 0.04104 | stringing:be01119be9dd59ed | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-30 | 2024-11-01 | 122/0 | 123/0 | Hotline | Ready | 328.32 | 2024-11-28 | 2024-11-30 | Completed | 0.32832 | 0.04104 | stringing:7193d811603a5084 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-11-23 | 2024-11-01 | 118/0 | 119/0 | Manual | Ready | 294.43 | 2024-12-02 | 2024-12-03 | Completed | 0.29443 | 0.026766 | stringing:1e7c340546d090ab | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-11-24 | 2024-11-01 | 118/0 | 119/0 | Manual | Ready | 294.43 | 2024-12-02 | 2024-12-03 | Completed | 0.29443 | 0.026766 | stringing:07ecc6b84b08644c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-11-25 | 2024-11-01 | 118/0 | 119/0 | Manual | Ready | 294.43 | 2024-12-02 | 2024-12-03 | Completed | 0.29443 | 0.026766 | stringing:39a945ad58429d3e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-11-26 | 2024-11-01 | 118/0 | 119/0 | Manual | Ready | 294.43 | 2024-12-02 | 2024-12-03 | Completed | 0.29443 | 0.026766 | stringing:ea83a2d5b5345e4a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-11-27 | 2024-11-01 | 118/0 | 119/0 | Manual | Ready | 294.43 | 2024-12-02 | 2024-12-03 | Completed | 0.29443 | 0.026766 | stringing:31f766335833b02e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-11-28 | 2024-11-01 | 118/0 | 119/0 | Manual | Ready | 294.43 | 2024-12-02 | 2024-12-03 | Completed | 0.29443 | 0.026766 | stringing:20ba042fac1d1d11 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-11-29 | 2024-11-01 | 118/0 | 119/0 | Manual | Ready | 294.43 | 2024-12-02 | 2024-12-03 | Completed | 0.29443 | 0.026766 | stringing:cbf0318a83ac6eea | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-11-30 | 2024-11-01 | 118/0 | 119/0 | Manual | Ready | 294.43 | 2024-12-02 | 2024-12-03 | Completed | 0.29443 | 0.026766 | stringing:7e166eb08140400b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-01 | 2024-12-01 | 118/0 | 119/0 | Manual | Ready | 294.43 | 2024-12-02 | 2024-12-03 | Completed | 0.29443 | 0.026766 | stringing:b27bd49db78a2a8b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-02 | 2024-12-01 | 118/0 | 119/0 | Manual | Ready | 294.43 | 2024-12-02 | 2024-12-03 | Completed | 0.29443 | 0.026766 | stringing:8093668b3b74f650 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-03 | 2024-12-01 | 118/0 | 119/0 | Manual | Ready | 294.43 | 2024-12-02 | 2024-12-03 | Completed | 0.29443 | 0.026766 | stringing:4e0c9a3ee87c68f3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-08 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:6b35e566056b5d30 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-09 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:5ff54fe4be331255 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-10 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:4166a3f3814a59ea | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-11 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:7663154447d7e3f5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-12 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:497d16d0e1858647 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-13 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:ae1888bfb6ca0802 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-14 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:9ef31bd95ef266bd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-15 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:2506c04214a10fbf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-16 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:33e3654d422fc2d4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-17 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:ab1137ef4d5a8192 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-18 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:8b95a9dfaa3313af | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-19 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:17575d05ae95ce41 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-20 | 2024-12-01 | 117/0 | 118/0 | Manual | Ready | 285.24 | 2024-12-18 | 2024-12-20 | Completed | 0.28524 | 0.021942 | stringing:225723223030b253 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-19 | 2024-12-01 | 119/0 | 120/0 | TSE | Ready | 1372.87 | 2024-12-21 | 2024-12-22 | Completed | 1.3729 | 0.34322 | stringing:1ac984ca5600c3e1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-20 | 2024-12-01 | 119/0 | 120/0 | TSE | Ready | 1372.87 | 2024-12-21 | 2024-12-22 | Completed | 1.3729 | 0.34322 | stringing:ac82373a7471b30f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-21 | 2024-12-01 | 119/0 | 120/0 | TSE | Ready | 1372.87 | 2024-12-21 | 2024-12-22 | Completed | 1.3729 | 0.34322 | stringing:5f3ea81d0e732830 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-22 | 2024-12-01 | 119/0 | 120/0 | TSE | Ready | 1372.87 | 2024-12-21 | 2024-12-22 | Completed | 1.3729 | 0.34322 | stringing:eeae9cb5e248738a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-17 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:ef2c189ab06395c7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-18 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:8425afb53bb4be6b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-19 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:f073bc9d4dccdd67 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-20 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:aa390045b1cdcb25 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-21 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:9c4d7a5731242304 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-22 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:247eb6eb2de26172 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-23 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:6919167d41ea3887 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-24 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:8d8a03595118dcb0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-25 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:27cd5f84caed19d6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-26 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:4525f1f27c1bc1d4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-27 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:ac6e0c17ce5f6afc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-28 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:fd3ba7bd1aed5266 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-29 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:1fdfa25c38259748 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-11-30 | 2024-11-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:8b1fa77fe2144464 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-01 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:5ee6313b9f8ffa23 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-02 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:649aa88777178123 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-03 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:aaa23dd61a9f0e3a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-04 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:de78e3fdf47b2319 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-05 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:51550fc18698df9d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-06 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:956364c1664d7100 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-07 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:b26f2ac04a14a8c3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-08 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:2e82ae76bcfcf753 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-09 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:065160e2dc68a53b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-10 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:7157201899e20dbb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-11 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:73d948745f89f643 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-12 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:57e348d1e50789a7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-13 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:79fd5b119f5b4139 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-14 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:611ff9d7711fc130 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-15 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:c9cc53929ba62980 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-16 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:674bd8a7e60cf5b8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-17 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:cbb65ccaaf274e64 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-18 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:88da8c6f47e1464c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-19 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:cadfe86af01d76e7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-20 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:f216ff784a624869 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-21 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:b7d88055314c58c7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-22 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:58022a294d0092ee | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-23 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:779f436f1e5583fe | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Yakub Ali + Enamul | 2024-12-24 | 2024-12-01 | 116B/0 | 117/0 | Manual | Ready | 437 | 2024-12-23 | 2024-12-24 | Completed | 0.437 | 0.0115 | stringing:eff0fc9660a7cd6e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-12-16 | 2024-12-01 | 144/0 | 144A/0 | TSE | Ready | 2391.06 | 2024-12-22 | 2024-12-24 | Completed | 2.3911 | 0.26567 | stringing:06068bc32fe726c3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-12-17 | 2024-12-01 | 144/0 | 144A/0 | TSE | Ready | 2391.06 | 2024-12-22 | 2024-12-24 | Completed | 2.3911 | 0.26567 | stringing:5e4279557b4fcca7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-12-18 | 2024-12-01 | 144/0 | 144A/0 | TSE | Ready | 2391.06 | 2024-12-22 | 2024-12-24 | Completed | 2.3911 | 0.26567 | stringing:46be64364b4c7295 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-12-19 | 2024-12-01 | 144/0 | 144A/0 | TSE | Ready | 2391.06 | 2024-12-22 | 2024-12-24 | Completed | 2.3911 | 0.26567 | stringing:66677121ffc5e4ad | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-12-20 | 2024-12-01 | 144/0 | 144A/0 | TSE | Ready | 2391.06 | 2024-12-22 | 2024-12-24 | Completed | 2.3911 | 0.26567 | stringing:02da9848a8e7a1a4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-12-21 | 2024-12-01 | 144/0 | 144A/0 | TSE | Ready | 2391.06 | 2024-12-22 | 2024-12-24 | Completed | 2.3911 | 0.26567 | stringing:160bdabd68a95f32 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-12-22 | 2024-12-01 | 144/0 | 144A/0 | TSE | Ready | 2391.06 | 2024-12-22 | 2024-12-24 | Completed | 2.3911 | 0.26567 | stringing:eec63c8851a32f81 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-12-23 | 2024-12-01 | 144/0 | 144A/0 | TSE | Ready | 2391.06 | 2024-12-22 | 2024-12-24 | Completed | 2.3911 | 0.26567 | stringing:e8a99276fadf4c04 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2024-12-24 | 2024-12-01 | 144/0 | 144A/0 | TSE | Ready | 2391.06 | 2024-12-22 | 2024-12-24 | Completed | 2.3911 | 0.26567 | stringing:ed1654a497008f18 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-28 | 2024-12-01 | 120/0 | 121/0 | Hotline | Ready | 264.71 | 2024-12-28 | 2025-01-01 | Completed | 0.26471 | 0.052942 | stringing:7c0776807a338b93 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-29 | 2024-12-01 | 120/0 | 121/0 | Hotline | Ready | 264.71 | 2024-12-28 | 2025-01-01 | Completed | 0.26471 | 0.052942 | stringing:adaf9f0367e6ac4f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-30 | 2024-12-01 | 120/0 | 121/0 | Hotline | Ready | 264.71 | 2024-12-28 | 2025-01-01 | Completed | 0.26471 | 0.052942 | stringing:b56e8e12658730e0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-31 | 2024-12-01 | 120/0 | 121/0 | Hotline | Ready | 264.71 | 2024-12-28 | 2025-01-01 | Completed | 0.26471 | 0.052942 | stringing:ab5792b65ff62949 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-01 | 2025-01-01 | 120/0 | 121/0 | Hotline | Ready | 264.71 | 2024-12-28 | 2025-01-01 | Completed | 0.26471 | 0.052942 | stringing:5d1f1e20ad52db6b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-26 | 2024-12-01 | 114/0 | 115/0 | Manual | Ready | 374 | 2024-12-30 | 2025-01-02 | Completed | 0.374 | 0.04675 | stringing:a7a4af0f6bf699a8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-27 | 2024-12-01 | 114/0 | 115/0 | Manual | Ready | 374 | 2024-12-30 | 2025-01-02 | Completed | 0.374 | 0.04675 | stringing:20111156318c8c55 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-28 | 2024-12-01 | 114/0 | 115/0 | Manual | Ready | 374 | 2024-12-30 | 2025-01-02 | Completed | 0.374 | 0.04675 | stringing:dd36f7196ec0245a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-29 | 2024-12-01 | 114/0 | 115/0 | Manual | Ready | 374 | 2024-12-30 | 2025-01-02 | Completed | 0.374 | 0.04675 | stringing:368a311159d81160 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-30 | 2024-12-01 | 114/0 | 115/0 | Manual | Ready | 374 | 2024-12-30 | 2025-01-02 | Completed | 0.374 | 0.04675 | stringing:0a1ce47180fb7b6f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-31 | 2024-12-01 | 114/0 | 115/0 | Manual | Ready | 374 | 2024-12-30 | 2025-01-02 | Completed | 0.374 | 0.04675 | stringing:7a637fbd83e67d54 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-01 | 2025-01-01 | 114/0 | 115/0 | Manual | Ready | 374 | 2024-12-30 | 2025-01-02 | Completed | 0.374 | 0.04675 | stringing:d8405f0fb3f29e50 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-02 | 2025-01-01 | 114/0 | 115/0 | Manual | Ready | 374 | 2024-12-30 | 2025-01-02 | Completed | 0.374 | 0.04675 | stringing:162adf5d8a31f491 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-26 | 2024-12-01 | 115/0 | 116/0 | Manual | Ready | 226 | 2024-12-31 | 2025-01-02 | Completed | 0.226 | 0.02825 | stringing:2b0370106731f925 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-27 | 2024-12-01 | 115/0 | 116/0 | Manual | Ready | 226 | 2024-12-31 | 2025-01-02 | Completed | 0.226 | 0.02825 | stringing:00aaab852eaed3e5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-28 | 2024-12-01 | 115/0 | 116/0 | Manual | Ready | 226 | 2024-12-31 | 2025-01-02 | Completed | 0.226 | 0.02825 | stringing:2d071ecc3cc51dad | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-29 | 2024-12-01 | 115/0 | 116/0 | Manual | Ready | 226 | 2024-12-31 | 2025-01-02 | Completed | 0.226 | 0.02825 | stringing:76158c9aeec4e111 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-30 | 2024-12-01 | 115/0 | 116/0 | Manual | Ready | 226 | 2024-12-31 | 2025-01-02 | Completed | 0.226 | 0.02825 | stringing:beec1efad4f824f5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2024-12-31 | 2024-12-01 | 115/0 | 116/0 | Manual | Ready | 226 | 2024-12-31 | 2025-01-02 | Completed | 0.226 | 0.02825 | stringing:bd311c49388a3a2a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-01 | 2025-01-01 | 115/0 | 116/0 | Manual | Ready | 226 | 2024-12-31 | 2025-01-02 | Completed | 0.226 | 0.02825 | stringing:5ef68066c7c7d96b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-02 | 2025-01-01 | 115/0 | 116/0 | Manual | Ready | 226 | 2024-12-31 | 2025-01-02 | Completed | 0.226 | 0.02825 | stringing:6cef98c8b2798696 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + Rafikul | 2024-12-27 | 2024-12-01 | 133A/0 | 134/0 | TSE | Ready | 2037.5 | 2025-01-02 | 2025-01-04 | Completed | 2.0375 | 0.22639 | stringing:baab60e3a89ea7d1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + Rafikul | 2024-12-28 | 2024-12-01 | 133A/0 | 134/0 | TSE | Ready | 2037.5 | 2025-01-02 | 2025-01-04 | Completed | 2.0375 | 0.22639 | stringing:f2973bf78144fa73 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + Rafikul | 2024-12-29 | 2024-12-01 | 133A/0 | 134/0 | TSE | Ready | 2037.5 | 2025-01-02 | 2025-01-04 | Completed | 2.0375 | 0.22639 | stringing:bdd4ee6a1aed3753 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + Rafikul | 2024-12-30 | 2024-12-01 | 133A/0 | 134/0 | TSE | Ready | 2037.5 | 2025-01-02 | 2025-01-04 | Completed | 2.0375 | 0.22639 | stringing:ad1cc835f779af55 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + Rafikul | 2024-12-31 | 2024-12-01 | 133A/0 | 134/0 | TSE | Ready | 2037.5 | 2025-01-02 | 2025-01-04 | Completed | 2.0375 | 0.22639 | stringing:64c7395f7c06f479 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + Rafikul | 2025-01-01 | 2025-01-01 | 133A/0 | 134/0 | TSE | Ready | 2037.5 | 2025-01-02 | 2025-01-04 | Completed | 2.0375 | 0.22639 | stringing:07560d49dc0ddca7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + Rafikul | 2025-01-02 | 2025-01-01 | 133A/0 | 134/0 | TSE | Ready | 2037.5 | 2025-01-02 | 2025-01-04 | Completed | 2.0375 | 0.22639 | stringing:e2e967cd6e7ee155 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + Rafikul | 2025-01-03 | 2025-01-01 | 133A/0 | 134/0 | TSE | Ready | 2037.5 | 2025-01-02 | 2025-01-04 | Completed | 2.0375 | 0.22639 | stringing:a00009c483107c91 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + Rafikul | 2025-01-04 | 2025-01-01 | 133A/0 | 134/0 | TSE | Ready | 2037.5 | 2025-01-02 | 2025-01-04 | Completed | 2.0375 | 0.22639 | stringing:5967dc8e5ff71222 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-29 | 2024-12-01 | 123/0 | 124/0 | Manual | Ready | 843 | 2025-01-05 | 2025-01-06 | Completed | 0.843 | 0.093667 | stringing:aacf2936f03b8cdc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-30 | 2024-12-01 | 123/0 | 124/0 | Manual | Ready | 843 | 2025-01-05 | 2025-01-06 | Completed | 0.843 | 0.093667 | stringing:0e34917d1179f264 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2024-12-31 | 2024-12-01 | 123/0 | 124/0 | Manual | Ready | 843 | 2025-01-05 | 2025-01-06 | Completed | 0.843 | 0.093667 | stringing:7e66032ad17ad94d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-01 | 2025-01-01 | 123/0 | 124/0 | Manual | Ready | 843 | 2025-01-05 | 2025-01-06 | Completed | 0.843 | 0.093667 | stringing:d430121979fbfc02 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-02 | 2025-01-01 | 123/0 | 124/0 | Manual | Ready | 843 | 2025-01-05 | 2025-01-06 | Completed | 0.843 | 0.093667 | stringing:2ec9f9c52704942a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-03 | 2025-01-01 | 123/0 | 124/0 | Manual | Ready | 843 | 2025-01-05 | 2025-01-06 | Completed | 0.843 | 0.093667 | stringing:9ec65b0da2b23a77 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-04 | 2025-01-01 | 123/0 | 124/0 | Manual | Ready | 843 | 2025-01-05 | 2025-01-06 | Completed | 0.843 | 0.093667 | stringing:3ca701d27b43aa3b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-05 | 2025-01-01 | 123/0 | 124/0 | Manual | Ready | 843 | 2025-01-05 | 2025-01-06 | Completed | 0.843 | 0.093667 | stringing:7601d7923c0247b1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-06 | 2025-01-01 | 123/0 | 124/0 | Manual | Ready | 843 | 2025-01-05 | 2025-01-06 | Completed | 0.843 | 0.093667 | stringing:dab41b5d124a0320 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-09 | 2025-01-01 | 116A/0 | 116B/0 | Manual | Ready | 675 | 2025-01-12 | 2025-01-13 | Completed | 0.675 | 0.135 | stringing:19777da0032b9449 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-10 | 2025-01-01 | 116A/0 | 116B/0 | Manual | Ready | 675 | 2025-01-12 | 2025-01-13 | Completed | 0.675 | 0.135 | stringing:b2234cc865b05c26 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-11 | 2025-01-01 | 116A/0 | 116B/0 | Manual | Ready | 675 | 2025-01-12 | 2025-01-13 | Completed | 0.675 | 0.135 | stringing:beb01ca4e8a3348b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-12 | 2025-01-01 | 116A/0 | 116B/0 | Manual | Ready | 675 | 2025-01-12 | 2025-01-13 | Completed | 0.675 | 0.135 | stringing:5fceb54952a74d6f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-13 | 2025-01-01 | 116A/0 | 116B/0 | Manual | Ready | 675 | 2025-01-12 | 2025-01-13 | Completed | 0.675 | 0.135 | stringing:ee1349029383db67 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-08 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b2103e744c064564 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-09 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4cc3457d9db61fc8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-10 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:cab630889e5423bf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-11 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f79ec2c952fe9df9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-12 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:20e73d3bf130b237 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-13 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e5c5e44e8509c9c8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-14 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c43c5d79f01ed532 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-15 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:44762cf36cccb9f4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-16 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:18566050d956210b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-17 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c3d80df2181ea0fe | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-18 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:2da1307a1c7d9d00 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-19 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6400f74ff0641186 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-20 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:aaa0d8334954df25 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-21 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:10275416a39cb66f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-22 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e3d5cbb9cfe9dfd6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-23 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b496bb15c05cd78a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-24 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b926294081871ac5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-25 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:ab86353f73de6737 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-26 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:08ac7941d7d83f99 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-27 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:31c3271e0fbef011 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-28 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:16ebb4ca34c33521 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-29 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:41e8afaf2db6867c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-30 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:bdc5d114c4736aa1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-01-31 | 2024-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:64ae34b0243576d1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-01 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:63d84ebe5bb0b000 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-02 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:65de7a000d68bc97 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-03 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f8610b5ec6c01087 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-04 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:36277679e1e39270 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-05 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6e64aa451af1d545 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-06 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:a023dfc000323c71 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-07 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:fe2ad9f6b8650dd0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-08 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:99cfa0ee20405b43 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-09 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6079fd7926411098 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-10 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6b5c213cf3c0fedb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-11 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b8f48133735ee356 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-12 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:679f803cb212e915 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-13 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:5367ffbef5cf3562 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-14 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:04c71e292873651b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-15 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b7f03caf1efd39d0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-16 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:2cda66d032e574dd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-17 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:44e91785257aedde | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-18 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4c7e29b7c0a19cbf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-19 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d952347c835398e0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-20 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:8b4c7c114ee17932 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-21 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:0cb54a4bf46414a1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-22 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:2c754f017361aedb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-23 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6a9a40c27cdb7f2c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-24 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:785f2b62558daf59 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-25 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6def1ea3b94fc8b4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-26 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:fbd092b772169437 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-27 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6f97808482617d52 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-28 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:31bea77f980b560b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-02-29 | 2024-02-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:93b8b46378e4f824 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-01 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:1d4a50e4c866dcfa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-02 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e97281683d602ee5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-03 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:002982a117a00caa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-04 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:9c5d9da04796f42b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-05 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:71c3a1d6e48ded95 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-06 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d8fd82896933f5af | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-07 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:42e90b0d90866750 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-08 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4d357af6a373333d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-09 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:1d2547269bdf3f22 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-10 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:3bf19fe75025b782 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-11 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d959162fb76d5020 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-12 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:daaec7a00c03771a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-13 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d9cfaf3d4db33132 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-14 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:0ebe15c590b99785 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-15 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e67e06e9009cb88a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-16 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:16f5a4d0aade90b4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-17 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b02e144e5c68f472 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-18 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:009397afb2afc5d5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-19 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:97915e74aca2a036 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-20 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:9c076e145f505741 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-21 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:7a720bc6c6595af1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-22 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:94eec0f644c5edce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-23 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:7e2e4ab039cf743b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-24 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:eec45bd2983d4599 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-25 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:259cd668e8f9d6bc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-26 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:210022ae5c0d9f15 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-27 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:ff23b887025549b6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-28 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:8f0927c4a8afae27 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-29 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:30b6c50ebae4cc80 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-30 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:9dd82f7a78d4f433 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-03-31 | 2024-03-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:46be26d1210e4aa1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-01 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4aeaeaef2fb87ab4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-02 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d26ed525615ae0b6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-03 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:3044c3a8b41086ff | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-04 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b3ea98ab604f968e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-05 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:a4372a4009ec106e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-06 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:45a45329862245e8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-07 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b6931517da797e6b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-08 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6ed5cb18ab537133 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-09 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:dd6fcb450641b540 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-10 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4128cd035f2700d0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-11 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:dd662d9eb145dbcd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-12 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:74d50c3ed96ba9c1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-13 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4aa062dcd9a93627 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-14 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4d5deb133b449ee0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-15 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b4639b169d058adc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-16 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:eebf6a26d2759d8d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-17 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b9a3bf8807f5a750 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-18 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b6e0f13d9bb4af91 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-19 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:546b241efd1e57fe | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-20 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:8a738cb898b2bccd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-21 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:8057fb1da4e255e0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-22 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:479575f6d091466e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-23 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c32948f5ac9119f7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-24 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:70c99f376018e74c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-25 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f360a4c7255ee5e3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-26 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:94f2211f08ba8395 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-27 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:51dd6c93ba8d60de | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-28 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b0dcbdfd235e1921 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-29 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b8eebee7f1a83ee7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-04-30 | 2024-04-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d60b98755b06abce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-01 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d705db8d953c68e3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-02 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f8b09e56d50f0bdd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-03 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6109f5decdde69e9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-04 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:81a9b0b37dfb6916 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-05 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4e64ba57e42a9619 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-06 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:a7023433a692a1b5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-07 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:041dc1c5be43a3dd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-08 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:9d0422ffcb14bd31 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-09 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6d03f0da168170cd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-10 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:9c6de2d47487a55a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-11 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:27e0b6f4204dfe7d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-12 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e6fdfa10d0072344 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-13 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:29f1a96e7e267cf5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-14 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:5b8d3b92639f5530 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-15 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:212b9333bebe9730 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-16 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c3d2cb5d02094802 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-17 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c6da2b1eb0c65276 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-18 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:3149c7b2c5a2b233 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-19 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:92c77bae866e2ec0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-20 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:422963c1f40885cd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-21 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f739df9a3ff7d2f7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-22 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:cfe2e578e0ad426e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-23 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4d3f98b7eb14c19c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-24 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:309b91668021ba43 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-25 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:12aa368af4837061 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-26 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e2c126c9a634f0b2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-27 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:381080223307b708 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-28 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:dd0fbd491a3622dd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-29 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:177b6de5e6db29f0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-30 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c8b1d575f9ec60eb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-05-31 | 2024-05-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:afbcdc6644a42afa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-01 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:2f46636f2dcea4cf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-02 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:7f34592d11bd8c93 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-03 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e039a85c41850c9e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-04 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f6b1dcee3504d434 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-05 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:cb241d50424fd0d7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-06 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f720ca5f9f545f50 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-07 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:aef49dcd1cdaf9aa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-08 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:725f0775c2d5aaff | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-09 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:8ff2729f5bad7fa7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-10 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:957441e025331871 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-11 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:649036afec0fe207 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-12 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:3ffad53216c5ec01 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-13 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:dbcb6ab933463138 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-14 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b48106632d081b20 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-15 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:09bc1f8fac9f3b56 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-16 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:35c980789968b04d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-17 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:2a17cca49c733aaa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-18 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:54438f8d8f266959 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-19 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:2eed363546dd1273 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-20 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:8502819e5981d355 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-21 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:7a11d811e43a42fb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-22 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:5eab87518c1cffd3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-23 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:27d1e7d6142a214f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-24 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:035372bb43677914 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-25 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4661dc77702b8d40 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-26 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c16bbfed1f9367b6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-27 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:5e3da36e0961d677 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-28 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:94dc3fcdef0abab1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-29 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:ec830d91762863c0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-06-30 | 2024-06-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:85ee5c3385029983 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-01 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:710206c340f238e7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-02 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:7ab613179132be52 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-03 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:68301851451561f1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-04 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:23f531b33e23416a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-05 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:fb2a739a50c3ee17 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-06 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:a53d2d640404bea2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-07 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:aa87e23ec5765fb0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-08 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6aca7376de837713 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-09 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:2c1ef1ede50915b4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-10 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:3413917808324745 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-11 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:2862aff9fb5f861a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-12 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f5c2db537821c726 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-13 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:66f7b2c41fec28c5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-14 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:a17420f9bf23eb75 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-15 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:07f882189e148c8a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-16 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d9b81161e31bf9d8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-17 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c7b2f1694775ce61 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-18 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:5f8ed8a88f1e7320 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-19 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:10c3ebdf0599633e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-20 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:1e337e60d50ed168 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-21 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e1de4f1bf1b57e7c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-22 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:cee663dbd8d31be2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-23 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:9df689710aadc99e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-24 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:a79cba81b9763666 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-25 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d2dd0655dc13fcef | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-26 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f81d873961abfe63 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-27 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:cc02b9b4dc48d541 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-28 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:66b87da535be91c1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-29 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:a1f4b8505906ea41 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-30 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f1fa0d75466cbe3b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-07-31 | 2024-07-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f42ee5aaee053bc9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-01 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6e1eb284231afb68 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-02 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:17b9f25b515405ce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-03 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f0b8d1b45222ded0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-04 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:11c8fdd25ba5cdad | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-05 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:036f839e9a27d4e3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-06 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:1876e6f30eda4b62 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-07 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:220770e43896bc36 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-08 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:22bb0752a8d7c81b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-09 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c4b4602cf955b10c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-10 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:9c17c7f3d5f09959 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-11 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:378c84c52e9d75c5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-12 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:cc8be4b695fa1a57 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-13 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d5b620e4c340caa3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-14 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d7f1fc910f702f00 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-15 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b5d8e9d405f5e47e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-16 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:ed2a13e45e9ed4f5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-17 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:7f1d0cddc1bac8c8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-18 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:83ae3c98ff3abe33 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-19 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4141f9d866c00ba7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-20 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6e8ad68d32d0cbe2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-21 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4b41b988cdbfc15d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-22 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:28bdf8e5ea4cba2b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-23 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:bbbb8bdfcc770ff3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-24 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b0c2878b511ff325 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-25 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e37630db95533e6d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-26 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c2c3f9ca0648a056 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-27 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c23e334546541507 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-28 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b33894240053df23 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-29 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:867eebe103044a01 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-30 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f66be364518c42ca | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-08-31 | 2024-08-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:be8350e331b0517b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-01 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:451b6b0dab70aa5f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-02 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:1e99f73c3729cdce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-03 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:0d1c1fed62b3bf82 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-04 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4d55aa95f0cfb558 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-05 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:12b12ad0e9615cd7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-06 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:88ce969666dce863 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-07 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d43ef2972488b7a2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-08 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:587c5b83430b189a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-09 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:37c94596a1fb00b9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-10 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:78b15f0102793a18 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-11 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:ac254511f2b51783 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-12 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:51a4bbda42d2e394 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-13 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:db0e599cd22a62bb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-14 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:49b40fe5fa9fd770 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-15 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:705e00da3b69fe61 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-16 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e238686e05f4894e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-17 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:7e7b922dd19c3d8a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-18 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f025ec43f1f4e5a3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-19 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:61cbd0797f6c445f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-20 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:bc060d69035210b7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-21 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:9db3de393846d45d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-22 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:01f726204ca6b776 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-23 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:85ec7872ec2907c6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-24 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:124334e08dc44a3a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-25 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:70cbe62509fdd8e8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-26 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:77afa3408dc9c69e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-27 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:aead40b453eca157 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-28 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:614ec5052e417c99 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-29 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d1611e1cc1d9770d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-09-30 | 2024-09-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:791db7fe6b2028e4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-01 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:3e5de1c38e08ca4e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-02 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:a0b333c65f57f7b3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-03 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:bc39cc8019020547 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-04 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e2590d1b93b5c085 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-05 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:fde77c6f7a2e3890 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-06 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6dd2d56dc6d854f7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-07 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:9d30d85cad56a4a9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-08 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6bc79c25be825fc7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-09 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f4bc954bdd0de20d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-10 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:5530d73d0db61430 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-11 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:bf3d97876e1a4a81 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-12 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:76b8eab4f97bb122 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-13 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:730daca8639b23bf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-14 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6eb57c938a5c94c9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-15 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:87984216b4e699f4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-16 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:31c19cefd80f3fec | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-17 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:3a10d60e4349425c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-18 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:da0f64e671920297 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-19 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:0dddc3361c3fb747 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-20 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:49a235bee88002e2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-21 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6dd49b891deb0709 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-22 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:42f13cbc0761b3c4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-23 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:ab6601881709690c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-24 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:677146e7da3ba10d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-25 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:10de6a7a9959cedc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-26 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:7d1ca48bc2f1f743 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-27 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e496119856ebaff7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-28 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4133f27a45016f82 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-29 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:0cd5af026560d42d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-30 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:29006849e4127722 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-10-31 | 2024-10-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:a409164f23ee7c2a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-01 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:6f4d2208fe4b41cb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-02 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4d80e9147426f96a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-03 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:74fb10e67df693e2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-04 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b4fc38d935a2ba29 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-05 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:65aa0d1964e622f5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-06 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:8741f2048b58efab | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-07 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:50a95b6d6733c66e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-08 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:fe52edf52d33c207 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-09 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:0893be1fb709b5d5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-10 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:56e51525292d53cf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-11 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d700c8a142190ab8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-12 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:df7b752740e6497d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-13 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:986ac9a726743cb4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-14 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:f11c86fccf3ec8d5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-15 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:74c0526a7e49a117 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-16 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:343dbd9e52516019 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-17 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:42ebf755cb34f6db | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-18 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:2da8ee975a28ef35 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-19 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:66b5e8e1434fb81f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-20 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e339d9791e52ba1c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-21 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:9f6a5823c678a111 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-22 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:92b4f66eab3f3c0d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-23 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:3c96c83678857d9f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-24 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:9f182d6466934ddd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-25 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:a9e15e9b437e8d18 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-26 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:03190650a7c34075 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-27 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d728232133725d89 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-28 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:fa341e65991e8711 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-29 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:af3247daedca8597 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-11-30 | 2024-11-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c9c69a78c1e3ad79 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-01 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d89531bcac6da50e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-02 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:0d04945fa8d44f73 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-03 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e2800244be0bbe4a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-04 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:881b5a6132701d88 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-05 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:886842f83a47f68c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-06 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:69a4db127d0d62a4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-07 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:3c2d7c370182bacd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-08 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:cbb284966b02aeb0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-09 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:5a7bba4913f68717 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-10 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:ce1b2c0fca4757a3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-11 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:92879214f6063430 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-12 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:22d68b3406f3cb83 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-13 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e64edfcfd4bd1719 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-14 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:18cc593181bbd2cb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-15 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:dde185bff90b44c9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-16 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:88d134ee06b2248c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-17 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:40d88e4e1aaa8504 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-18 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:e7c569d116bbc843 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-19 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:1b4f045b0359dd6a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-20 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b0fe6f5857071c22 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-21 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:a4da21d2ec4d7af3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-22 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:4856997f0b2ecb0b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-23 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:93d439bbdeda14ea | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-24 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:53bcaafe7465964c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-25 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b7b62b8950a1a962 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-26 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:b78463e059da6ae7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-27 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:133bec2a2967b180 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-28 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:97cecf6a2bdf3aa8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-29 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:2d6b906c10089dfd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-30 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:85c030019a442ae4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2024-12-31 | 2024-12-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:cdcbf26d61442349 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-01 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:ef3f2d66daa03d17 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-02 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:29d1781567877494 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-03 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:420590cec2a49183 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-04 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c8240359bf28dede | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-05 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:02f2b4f822d28491 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-06 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:d97dab20fc8b8189 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-07 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:c992e2609a88c2db | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-08 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:a42a77432da97c56 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-09 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:482525d68610dd4f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-10 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:845225ea500d40ce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-11 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:0854572bb42df537 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-12 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:0e68c5a892562632 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-01-13 | 2025-01-01 | 144A/0 | 145/0 | Hotline | Ready | 397.58 | 2024-01-08 | 2025-01-13 | Completed | 0.39758 | 0.0010688 | stringing:7a341d9096b644d5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2025-01-15 | 2025-01-01 | 147/1 | 147/2 | Manual | Ready | 330 | 2025-01-15 | 2025-01-16 | Completed | 0.33 | 0.165 | stringing:390a9193c2a548d9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Gokul Sarkar | 2025-01-16 | 2025-01-01 | 147/1 | 147/2 | Manual | Ready | 330 | 2025-01-15 | 2025-01-16 | Completed | 0.33 | 0.165 | stringing:c47517e7dc4a4e38 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-11 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:cbfec22342e64ce6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-12 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:4bcb181dceb589b8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-13 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:4c2463e35cf24b25 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-14 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:97c72297adad3632 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-15 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:4073ee3fb9acb167 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-16 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:c8cea7a91f720dcd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-17 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:bdf36eca41fd999a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-18 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:e7852fecef63f92a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-19 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:1bc223fca2f79a33 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-20 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:dd16d9d9bb08a9c4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-21 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:ac73485190c01523 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-22 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:62884b7052ba8415 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-23 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:6c52f7b140b5b910 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-24 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:5574d27fc9e5a491 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-25 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:c95243bc471f891b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-26 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:e9cac44b1a8bf572 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-27 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:1d94e318e85864ec | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-28 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:bb60b17c2db79ad6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-29 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:a8011c3a4dea8e43 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-30 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:8439121b71163456 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2024-12-31 | 2024-12-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:e470ba7144ca98e1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-01 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:12c822f8b4d779ea | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-02 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:ebf8f85a7195eb4d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-03 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:b863a65df6ec3bc4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-04 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:6fab562f421024e3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-05 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:f2d029297e7e9217 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-06 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:9719166a91c6de5b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-07 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:2fb4184ef8ccb010 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-08 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:bc943f4bc0ff4eb1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-09 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:4427dfc24007ac83 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-10 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:82d1b04a1a09c939 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-11 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:dbb649c03ed67a79 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-12 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:83bdf28924464cc4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-13 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:36fed6fae727d02b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-14 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:71a6a45f5a468c5f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-15 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:8c2a924449c44120 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-16 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:c254f7e57d7299af | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-17 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:16d5447c3415032c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-18 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:caddbd4352f52747 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin + Enamul | 2025-01-19 | 2025-01-01 | 127/0 | 128/0 | TSE | Ready | 2399.38 | 2025-01-17 | 2025-01-19 | Completed | 2.3994 | 0.059985 | stringing:98e36caff7cbb2c6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-09 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:ddb958170c275a61 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-10 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:75b9f4b553a148e4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-11 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:57345be8264de6de | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-12 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:d6e313c18594a8f0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-13 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:85ea6a175b8137af | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-14 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:a03dbc4a715ece64 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-15 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:f1100ca6875083a7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-16 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:34498f85a6cf7384 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-17 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:4ee39328c661943f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-18 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:5de362ffb205fcfc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-19 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:7ad9d214008b7453 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-20 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:789a56a3b8c67863 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-21 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:035c9dfa2c541f11 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-22 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:d7e679f3c3a404f8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-23 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:49e308ed5e6e70a8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-24 | 2025-01-01 | 126/0 | 127/0 | Manual | Ready | 808.43 | 2025-01-23 | 2025-01-24 | Completed | 0.80843 | 0.050527 | stringing:0ae94b265880b5b6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-12 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:e5e6644e81125a83 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-13 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:9a046170f5e096bf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-14 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:e0e602ecdaa06097 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-15 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:76ab9cb86268ea88 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-16 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:e7fc646a5af3cb68 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-17 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:903978bf363d0531 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-18 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:d437b225d98f8259 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-19 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:dfaef8056a91a995 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-20 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:5c1d0048beeb7ec4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-21 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:cbc5735723b03183 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-22 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:b890933425c1ca69 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-23 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:f7ff6c3cd0f74385 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rejaul + enamul | 2025-01-24 | 2025-01-01 | 132/0 | 133/0 | TSE | Ready | 1280.12 | 2025-01-21 | 2025-01-24 | Completed | 1.2801 | 0.098471 | stringing:65dda18353e41121 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-01-23 | 2025-01-01 | 259/0 | 260/0 | Hotline | Ready | 256 | 2025-01-26 | 2025-01-28 | Completed | 0.256 | 0.042667 | stringing:da3241f33a81d267 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-01-24 | 2025-01-01 | 259/0 | 260/0 | Hotline | Ready | 256 | 2025-01-26 | 2025-01-28 | Completed | 0.256 | 0.042667 | stringing:ecdd742a044fe8be | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-01-25 | 2025-01-01 | 259/0 | 260/0 | Hotline | Ready | 256 | 2025-01-26 | 2025-01-28 | Completed | 0.256 | 0.042667 | stringing:a8a0a29643b0c555 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-01-26 | 2025-01-01 | 259/0 | 260/0 | Hotline | Ready | 256 | 2025-01-26 | 2025-01-28 | Completed | 0.256 | 0.042667 | stringing:361885503f42bf08 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-01-27 | 2025-01-01 | 259/0 | 260/0 | Hotline | Ready | 256 | 2025-01-26 | 2025-01-28 | Completed | 0.256 | 0.042667 | stringing:4c8693ce2410a343 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-01-28 | 2025-01-01 | 259/0 | 260/0 | Hotline | Ready | 256 | 2025-01-26 | 2025-01-28 | Completed | 0.256 | 0.042667 | stringing:899f43bceb720a4d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-01-23 | 2025-01-01 | 260/0 | 261/0 | Manual | Ready | 338 | 2025-01-26 | 2025-01-28 | Completed | 0.338 | 0.056333 | stringing:69d5dd15c5f893b9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-01-24 | 2025-01-01 | 260/0 | 261/0 | Manual | Ready | 338 | 2025-01-26 | 2025-01-28 | Completed | 0.338 | 0.056333 | stringing:a8d7ff19676c7c5a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-01-25 | 2025-01-01 | 260/0 | 261/0 | Manual | Ready | 338 | 2025-01-26 | 2025-01-28 | Completed | 0.338 | 0.056333 | stringing:b949f93353ffa8c5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-01-26 | 2025-01-01 | 260/0 | 261/0 | Manual | Ready | 338 | 2025-01-26 | 2025-01-28 | Completed | 0.338 | 0.056333 | stringing:7d17cd2904344d74 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-01-27 | 2025-01-01 | 260/0 | 261/0 | Manual | Ready | 338 | 2025-01-26 | 2025-01-28 | Completed | 0.338 | 0.056333 | stringing:9596e914fd4fdd01 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-01-28 | 2025-01-01 | 260/0 | 261/0 | Manual | Ready | 338 | 2025-01-26 | 2025-01-28 | Completed | 0.338 | 0.056333 | stringing:6c38a272e3ddcfe5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-16 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:e1a275f6fb45e1cc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-17 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:46d7dd683fdbf36d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-18 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:9eadb0eecbf8a25d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-19 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:bf693d7c997d96a6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-20 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:36dcfae56eab6319 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-21 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:9a11cb7ea214f8e6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-22 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:a7a9b8083ed3606d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-23 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:98a5b8f6ae07ba74 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-24 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:f7a58dbb101770fc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-25 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:e0a474ccf967f310 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-26 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:bce9c5338fd5d1d2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-27 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:23487af5f7e66f03 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-28 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:45dbb962e93725ac | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-29 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:84c2cde99ca535b0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-30 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:e2e811e7e5a6a4a0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-31 | 2025-01-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:6cacee3173ac2304 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-01 | 2025-02-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:f1aa0f8f6c7d085d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-02 | 2025-02-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:89da31365e6e5068 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-03 | 2025-02-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:16c479fd01042bc4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-04 | 2025-02-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:b7c32490ff2f5ea2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-05 | 2025-02-01 | 125A/0 | 126/0 | Manual | Ready | 380.08 | 2025-02-04 | 2025-02-05 | Completed | 0.38008 | 0.018099 | stringing:40613636e64dc3d8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-28 | 2025-01-01 | 106A/0 | 106B/0 | TSE | Ready | 2016.36 | 2025-02-04 | 2025-02-06 | Completed | 2.0164 | 0.20164 | stringing:be149fdb1cd74ead | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-29 | 2025-01-01 | 106A/0 | 106B/0 | TSE | Ready | 2016.36 | 2025-02-04 | 2025-02-06 | Completed | 2.0164 | 0.20164 | stringing:b8ed89cf18106189 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-30 | 2025-01-01 | 106A/0 | 106B/0 | TSE | Ready | 2016.36 | 2025-02-04 | 2025-02-06 | Completed | 2.0164 | 0.20164 | stringing:6f134c163cf0b0b8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-01-31 | 2025-01-01 | 106A/0 | 106B/0 | TSE | Ready | 2016.36 | 2025-02-04 | 2025-02-06 | Completed | 2.0164 | 0.20164 | stringing:21d115d10606aeff | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-01 | 2025-02-01 | 106A/0 | 106B/0 | TSE | Ready | 2016.36 | 2025-02-04 | 2025-02-06 | Completed | 2.0164 | 0.20164 | stringing:09ff89b5456f7937 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-02 | 2025-02-01 | 106A/0 | 106B/0 | TSE | Ready | 2016.36 | 2025-02-04 | 2025-02-06 | Completed | 2.0164 | 0.20164 | stringing:4271b0586e533ec7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-03 | 2025-02-01 | 106A/0 | 106B/0 | TSE | Ready | 2016.36 | 2025-02-04 | 2025-02-06 | Completed | 2.0164 | 0.20164 | stringing:3fb77abcac12a41e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-04 | 2025-02-01 | 106A/0 | 106B/0 | TSE | Ready | 2016.36 | 2025-02-04 | 2025-02-06 | Completed | 2.0164 | 0.20164 | stringing:ce6a570242abf02d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-05 | 2025-02-01 | 106A/0 | 106B/0 | TSE | Ready | 2016.36 | 2025-02-04 | 2025-02-06 | Completed | 2.0164 | 0.20164 | stringing:666024bb5e67aacf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-06 | 2025-02-01 | 106A/0 | 106B/0 | TSE | Ready | 2016.36 | 2025-02-04 | 2025-02-06 | Completed | 2.0164 | 0.20164 | stringing:e1bf400d012e030d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-01-31 | 2025-01-01 | 125/0 | 125A/0 | Manual | Ready | 401.32 | 2025-02-06 | 2025-02-07 | Completed | 0.40132 | 0.050165 | stringing:d5cb12a39b76ba6f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-01 | 2025-02-01 | 125/0 | 125A/0 | Manual | Ready | 401.32 | 2025-02-06 | 2025-02-07 | Completed | 0.40132 | 0.050165 | stringing:cc3026c3d23e0089 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-02 | 2025-02-01 | 125/0 | 125A/0 | Manual | Ready | 401.32 | 2025-02-06 | 2025-02-07 | Completed | 0.40132 | 0.050165 | stringing:152079afcde84412 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-03 | 2025-02-01 | 125/0 | 125A/0 | Manual | Ready | 401.32 | 2025-02-06 | 2025-02-07 | Completed | 0.40132 | 0.050165 | stringing:d2ed9f9cd74747c9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-04 | 2025-02-01 | 125/0 | 125A/0 | Manual | Ready | 401.32 | 2025-02-06 | 2025-02-07 | Completed | 0.40132 | 0.050165 | stringing:54f7c051c3196dad | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-05 | 2025-02-01 | 125/0 | 125A/0 | Manual | Ready | 401.32 | 2025-02-06 | 2025-02-07 | Completed | 0.40132 | 0.050165 | stringing:51bc6a37bb64460d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-06 | 2025-02-01 | 125/0 | 125A/0 | Manual | Ready | 401.32 | 2025-02-06 | 2025-02-07 | Completed | 0.40132 | 0.050165 | stringing:e0a6cd39f14871ab | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-07 | 2025-02-01 | 125/0 | 125A/0 | Manual | Ready | 401.32 | 2025-02-06 | 2025-02-07 | Completed | 0.40132 | 0.050165 | stringing:365924ed181b7c92 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-10 | 2025-02-01 | 128/0 | 129/0 | Manual | Ready | 253.25 | 2025-02-12 | 2025-02-12 | Completed | 0.25325 | 0.084417 | stringing:6f957995a766c4c6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-11 | 2025-02-01 | 128/0 | 129/0 | Manual | Ready | 253.25 | 2025-02-12 | 2025-02-12 | Completed | 0.25325 | 0.084417 | stringing:f9f2563b291d0ea3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-12 | 2025-02-01 | 128/0 | 129/0 | Manual | Ready | 253.25 | 2025-02-12 | 2025-02-12 | Completed | 0.25325 | 0.084417 | stringing:9ec6d4ec1abbebb0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-10 | 2025-02-01 | 129/0 | 129A/0 | Manual | Ready | 305.53 | 2025-02-12 | 2025-02-13 | Completed | 0.30553 | 0.076382 | stringing:2d9a68d1ea1f015f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-11 | 2025-02-01 | 129/0 | 129A/0 | Manual | Ready | 305.53 | 2025-02-12 | 2025-02-13 | Completed | 0.30553 | 0.076382 | stringing:b6d237c9caea2d1c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-12 | 2025-02-01 | 129/0 | 129A/0 | Manual | Ready | 305.53 | 2025-02-12 | 2025-02-13 | Completed | 0.30553 | 0.076382 | stringing:9fbd6dcf512dc4cb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-13 | 2025-02-01 | 129/0 | 129A/0 | Manual | Ready | 305.53 | 2025-02-12 | 2025-02-13 | Completed | 0.30553 | 0.076382 | stringing:16660055f0e8ca8c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-20 | 2025-01-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:03097291e109915c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-21 | 2025-01-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:4c1811bdc7b38011 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-22 | 2025-01-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:00e6cd63ca76adbe | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-23 | 2025-01-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:83ef11ccec1b5876 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-24 | 2025-01-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:46828697206abd12 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-25 | 2025-01-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:8818990d66efaf19 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-26 | 2025-01-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:2c5972d97a5f81cb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-27 | 2025-01-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:f028f6c172fd7e72 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-28 | 2025-01-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:93875ed18bb96b2c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-29 | 2025-01-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:c69fa507c616becc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-30 | 2025-01-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:f5e09a433ad44032 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-31 | 2025-01-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:be5cd2df3fc3bdb0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-01 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:c60d6de1b0718748 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-02 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:0488ebaacb4e26df | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-03 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:7e54224a5a697304 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-04 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:5d17db1d82c40bf9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-05 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:0ef1324f2b0ce039 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-06 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:1043e32cf25a28ab | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-07 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:1195c22978b90d36 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-08 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:eeeddb252f597866 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-09 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:2d41edeef787e77e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-10 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:13425cd28fefafaa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-11 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:8ff8984f94b61c97 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-12 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:5c355160a97e731f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-13 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:cb7f87fae57c4052 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-14 | 2025-02-01 | 135A/0 | 135A/1 | Manual | Ready | 339.83 | 2025-02-06 | 2025-02-14 | Completed | 0.33983 | 0.01307 | stringing:4e0b10baa744bcd1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-04 | 2025-02-01 | 135A/2 | 135B/0 | TSE | Ready | 2234.39 | 2025-02-12 | 2025-02-14 | Completed | 2.2344 | 0.20313 | stringing:dd2779d4e8871124 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-05 | 2025-02-01 | 135A/2 | 135B/0 | TSE | Ready | 2234.39 | 2025-02-12 | 2025-02-14 | Completed | 2.2344 | 0.20313 | stringing:1d5a7f7322a818df | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-06 | 2025-02-01 | 135A/2 | 135B/0 | TSE | Ready | 2234.39 | 2025-02-12 | 2025-02-14 | Completed | 2.2344 | 0.20313 | stringing:5299e72898bcd886 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-07 | 2025-02-01 | 135A/2 | 135B/0 | TSE | Ready | 2234.39 | 2025-02-12 | 2025-02-14 | Completed | 2.2344 | 0.20313 | stringing:4b4194c4f730aa42 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-08 | 2025-02-01 | 135A/2 | 135B/0 | TSE | Ready | 2234.39 | 2025-02-12 | 2025-02-14 | Completed | 2.2344 | 0.20313 | stringing:b23715665517bc37 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-09 | 2025-02-01 | 135A/2 | 135B/0 | TSE | Ready | 2234.39 | 2025-02-12 | 2025-02-14 | Completed | 2.2344 | 0.20313 | stringing:1502ced9b7855173 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-10 | 2025-02-01 | 135A/2 | 135B/0 | TSE | Ready | 2234.39 | 2025-02-12 | 2025-02-14 | Completed | 2.2344 | 0.20313 | stringing:ac661ce2e18b2229 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-11 | 2025-02-01 | 135A/2 | 135B/0 | TSE | Ready | 2234.39 | 2025-02-12 | 2025-02-14 | Completed | 2.2344 | 0.20313 | stringing:49231af5562aae1f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-12 | 2025-02-01 | 135A/2 | 135B/0 | TSE | Ready | 2234.39 | 2025-02-12 | 2025-02-14 | Completed | 2.2344 | 0.20313 | stringing:1b49e532064fef8d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-13 | 2025-02-01 | 135A/2 | 135B/0 | TSE | Ready | 2234.39 | 2025-02-12 | 2025-02-14 | Completed | 2.2344 | 0.20313 | stringing:725e28e0fd131ad5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-14 | 2025-02-01 | 135A/2 | 135B/0 | TSE | Ready | 2234.39 | 2025-02-12 | 2025-02-14 | Completed | 2.2344 | 0.20313 | stringing:6949d4bcebcab8d6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-01-25 | 2025-01-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:07f6af977eee3d80 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-01-26 | 2025-01-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:b3b42cc441ae6603 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-01-27 | 2025-01-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:57cdf04d502f7efe | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-01-28 | 2025-01-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:f89472f220bd7e61 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-01-29 | 2025-01-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:3b0b245c850d39ce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-01-30 | 2025-01-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:81f863f1c1b1e9b6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-01-31 | 2025-01-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:e4ad6f57b075fa46 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-01 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:c757ce7acab5a9a3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-02 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:723e97744e6ed57d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-03 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:3cff0efeda4c079f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-04 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:ae5024d1562633d4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-05 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:6f77269e881d4ad7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-06 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:6a0d877eb5becd67 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-07 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:42459d0db959f28c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-08 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:25a431f55d0a5ed0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-09 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:e02d6d9b1e2e4be2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-10 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:c4edc792fa5ad950 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-11 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:0d458ea72d5ff69f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-12 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:d0788ca8e1b4da0e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-13 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:01abac8ccf146998 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction + Enamul | 2025-02-14 | 2025-02-01 | 135B/0 | 136/0 | TSE | Ready | 2985.99 | 2025-02-12 | 2025-02-14 | Completed | 2.986 | 0.14219 | stringing:287375ae40ff114b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-02 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:7d5167920f1b0ec7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-03 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:879f13394fd53d51 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-04 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:2d6790add5a6b030 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-05 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:c8feba1240c34e5c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-06 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:cb559e959eca2dba | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-07 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:59eb5c9d29c5d276 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-08 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:a61abd42b9e904e3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-09 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:556b35f7435b3694 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-10 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:8614af2af4a422db | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-11 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:11edf67627c2f3bd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-12 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:13e64d595e963fc0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-13 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:2b8483b896b28f9a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-14 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:81ea3f492b259ca3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-02-15 | 2025-02-01 | 106/0 | 106A/0 | Manual | Ready | 411.25 | 2025-02-14 | 2025-02-15 | Completed | 0.41125 | 0.029375 | stringing:b3cd8bbcc64dd57b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-07 | 2025-02-01 | 164/0 | 165/0 | TSE | Ready | 2980.78 | 2025-02-12 | 2025-02-15 | Completed | 2.9808 | 0.3312 | stringing:3bea95d69ed25f23 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-08 | 2025-02-01 | 164/0 | 165/0 | TSE | Ready | 2980.78 | 2025-02-12 | 2025-02-15 | Completed | 2.9808 | 0.3312 | stringing:fb56e3552317bad5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-09 | 2025-02-01 | 164/0 | 165/0 | TSE | Ready | 2980.78 | 2025-02-12 | 2025-02-15 | Completed | 2.9808 | 0.3312 | stringing:1f06cf9ac40f0d6c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-10 | 2025-02-01 | 164/0 | 165/0 | TSE | Ready | 2980.78 | 2025-02-12 | 2025-02-15 | Completed | 2.9808 | 0.3312 | stringing:4ae3a4a999c6ff31 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-11 | 2025-02-01 | 164/0 | 165/0 | TSE | Ready | 2980.78 | 2025-02-12 | 2025-02-15 | Completed | 2.9808 | 0.3312 | stringing:53b2524c0f07c534 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-12 | 2025-02-01 | 164/0 | 165/0 | TSE | Ready | 2980.78 | 2025-02-12 | 2025-02-15 | Completed | 2.9808 | 0.3312 | stringing:435a37576e6b7bf4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-13 | 2025-02-01 | 164/0 | 165/0 | TSE | Ready | 2980.78 | 2025-02-12 | 2025-02-15 | Completed | 2.9808 | 0.3312 | stringing:ceb485735a523bad | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-14 | 2025-02-01 | 164/0 | 165/0 | TSE | Ready | 2980.78 | 2025-02-12 | 2025-02-15 | Completed | 2.9808 | 0.3312 | stringing:c787d087dadb8865 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-15 | 2025-02-01 | 164/0 | 165/0 | TSE | Ready | 2980.78 | 2025-02-12 | 2025-02-15 | Completed | 2.9808 | 0.3312 | stringing:85d6a74ff4321361 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-29 | 2025-01-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:4a410938717dd7b2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-30 | 2025-01-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:ecc0d87ce900d177 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-01-31 | 2025-01-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:af9282688138bd5b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-01 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:ab051844d0eed53e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-02 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:f088a688dfcf814c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-03 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:13d47e2955b6c07b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-04 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:202dbcfce8a0deef | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-05 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:993c0bbcb938dcf8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-06 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:ba3fed0cb34af197 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-07 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:79faa8209281a7d1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-08 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:4671cf4ff1d72631 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-09 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:73982b968c3d8505 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-10 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:daf9ae543d488d56 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-11 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:6c68af4dc94491c6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-12 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:ef6c4c59aa3cf308 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-13 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:26c1e16afd36ccb2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-14 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:9820cbe04dea5823 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-15 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:5b44267fefe56468 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-16 | 2025-02-01 | 135A/1 | 135A/2 | Manual | Ready | 451.85 | 2025-02-07 | 2025-02-16 | Completed | 0.45185 | 0.023782 | stringing:a86c9c6485acdcd6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-10 | 2025-02-01 | 124/0 | 124A/0 | Manual | Ready | 395.28 | 2025-02-16 | 2025-02-19 | Completed | 0.39528 | 0.039528 | stringing:12503d9a693a5737 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-11 | 2025-02-01 | 124/0 | 124A/0 | Manual | Ready | 395.28 | 2025-02-16 | 2025-02-19 | Completed | 0.39528 | 0.039528 | stringing:37feece5600c09c6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-12 | 2025-02-01 | 124/0 | 124A/0 | Manual | Ready | 395.28 | 2025-02-16 | 2025-02-19 | Completed | 0.39528 | 0.039528 | stringing:d9d1ce4a7c8ee5a6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-13 | 2025-02-01 | 124/0 | 124A/0 | Manual | Ready | 395.28 | 2025-02-16 | 2025-02-19 | Completed | 0.39528 | 0.039528 | stringing:5df1c48d5f0bdf2d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-14 | 2025-02-01 | 124/0 | 124A/0 | Manual | Ready | 395.28 | 2025-02-16 | 2025-02-19 | Completed | 0.39528 | 0.039528 | stringing:009183506397f5c3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-15 | 2025-02-01 | 124/0 | 124A/0 | Manual | Ready | 395.28 | 2025-02-16 | 2025-02-19 | Completed | 0.39528 | 0.039528 | stringing:4c3116329cdbe40a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-16 | 2025-02-01 | 124/0 | 124A/0 | Manual | Ready | 395.28 | 2025-02-16 | 2025-02-19 | Completed | 0.39528 | 0.039528 | stringing:6209c7a24ae28447 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-17 | 2025-02-01 | 124/0 | 124A/0 | Manual | Ready | 395.28 | 2025-02-16 | 2025-02-19 | Completed | 0.39528 | 0.039528 | stringing:ecc079bf9c901c95 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-18 | 2025-02-01 | 124/0 | 124A/0 | Manual | Ready | 395.28 | 2025-02-16 | 2025-02-19 | Completed | 0.39528 | 0.039528 | stringing:a0a26ff5f89b4674 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-19 | 2025-02-01 | 124/0 | 124A/0 | Manual | Ready | 395.28 | 2025-02-16 | 2025-02-19 | Completed | 0.39528 | 0.039528 | stringing:753ef677096252e9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-15 | 2025-02-01 | 124A/0 | 124A/1 | Manual | Ready | 253 | 2025-02-15 | 2025-02-19 | Completed | 0.253 | 0.0506 | stringing:3e2dc434c4ec2ed9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-16 | 2025-02-01 | 124A/0 | 124A/1 | Manual | Ready | 253 | 2025-02-15 | 2025-02-19 | Completed | 0.253 | 0.0506 | stringing:035ed8922b4ff2c2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-17 | 2025-02-01 | 124A/0 | 124A/1 | Manual | Ready | 253 | 2025-02-15 | 2025-02-19 | Completed | 0.253 | 0.0506 | stringing:3c9b7e596ce2451a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-18 | 2025-02-01 | 124A/0 | 124A/1 | Manual | Ready | 253 | 2025-02-15 | 2025-02-19 | Completed | 0.253 | 0.0506 | stringing:726f0fe80a488347 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-19 | 2025-02-01 | 124A/0 | 124A/1 | Manual | Ready | 253 | 2025-02-15 | 2025-02-19 | Completed | 0.253 | 0.0506 | stringing:505aa806372f8f82 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-02-15 | 2025-02-01 | 124A/1 | 125/0 | Hotline | Ready | 203.134 | 2025-02-15 | 2025-02-19 | Completed | 0.20313 | 0.040627 | stringing:16e9eb094e6b6e43 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-02-16 | 2025-02-01 | 124A/1 | 125/0 | Hotline | Ready | 203.134 | 2025-02-15 | 2025-02-19 | Completed | 0.20313 | 0.040627 | stringing:22558bb41f08f982 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-02-17 | 2025-02-01 | 124A/1 | 125/0 | Hotline | Ready | 203.134 | 2025-02-15 | 2025-02-19 | Completed | 0.20313 | 0.040627 | stringing:d8116334241cf49a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-02-18 | 2025-02-01 | 124A/1 | 125/0 | Hotline | Ready | 203.134 | 2025-02-15 | 2025-02-19 | Completed | 0.20313 | 0.040627 | stringing:d68850881eb82673 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-02-19 | 2025-02-01 | 124A/1 | 125/0 | Hotline | Ready | 203.134 | 2025-02-15 | 2025-02-19 | Completed | 0.20313 | 0.040627 | stringing:963e1d62fd730676 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-11 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:bf858bcbd4cd6a8a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-12 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:f4985a783dc3baad | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-13 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:518a039888ea2466 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-14 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:3889f2b5aa342207 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-15 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:5700b0ecb6a8fee7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-16 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:b929f8aea4386891 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-17 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:fef81c9d3adbd321 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-18 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:2ec2b277d32fedce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-19 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:580e4d15feca498d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-20 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:4caaf283627ccb88 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-21 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:2979cc08d2c90a47 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-22 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:c8ef71ff1026a7dd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-23 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:6a1752d209689ac6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-24 | 2025-02-01 | 257/0 | 259/0 | TSE | Ready | 1809 | 2025-02-21 | 2025-02-24 | Completed | 1.809 | 0.12921 | stringing:3100735d51367921 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-21 | 2025-02-01 | 137A/0 | 138/0 | TSE | Ready | 2729.901 | 2025-02-28 | 2025-03-03 | Completed | 2.7299 | 0.24817 | stringing:9172efbfc0705456 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-22 | 2025-02-01 | 137A/0 | 138/0 | TSE | Ready | 2729.901 | 2025-02-28 | 2025-03-03 | Completed | 2.7299 | 0.24817 | stringing:928bfda4400d558d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-23 | 2025-02-01 | 137A/0 | 138/0 | TSE | Ready | 2729.901 | 2025-02-28 | 2025-03-03 | Completed | 2.7299 | 0.24817 | stringing:4c2f3ff579cc757d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-24 | 2025-02-01 | 137A/0 | 138/0 | TSE | Ready | 2729.901 | 2025-02-28 | 2025-03-03 | Completed | 2.7299 | 0.24817 | stringing:122400d7968ec84b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-25 | 2025-02-01 | 137A/0 | 138/0 | TSE | Ready | 2729.901 | 2025-02-28 | 2025-03-03 | Completed | 2.7299 | 0.24817 | stringing:c23c4be215fee3d4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-26 | 2025-02-01 | 137A/0 | 138/0 | TSE | Ready | 2729.901 | 2025-02-28 | 2025-03-03 | Completed | 2.7299 | 0.24817 | stringing:7349664732032b76 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-27 | 2025-02-01 | 137A/0 | 138/0 | TSE | Ready | 2729.901 | 2025-02-28 | 2025-03-03 | Completed | 2.7299 | 0.24817 | stringing:9400f7cd68045c1d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-02-28 | 2025-02-01 | 137A/0 | 138/0 | TSE | Ready | 2729.901 | 2025-02-28 | 2025-03-03 | Completed | 2.7299 | 0.24817 | stringing:83b29597401ab9fc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-01 | 2025-03-01 | 137A/0 | 138/0 | TSE | Ready | 2729.901 | 2025-02-28 | 2025-03-03 | Completed | 2.7299 | 0.24817 | stringing:0daf1b32853ff5e6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-02 | 2025-03-01 | 137A/0 | 138/0 | TSE | Ready | 2729.901 | 2025-02-28 | 2025-03-03 | Completed | 2.7299 | 0.24817 | stringing:4be94791d42f2fdb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-03 | 2025-03-01 | 137A/0 | 138/0 | TSE | Ready | 2729.901 | 2025-02-28 | 2025-03-03 | Completed | 2.7299 | 0.24817 | stringing:ec14fe8588ddc6d5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-27 | 2025-02-01 | 138/0 | 139/0 | TSE | Ready | 1238.994 | 2025-03-02 | 2025-03-04 | Completed | 1.239 | 0.2065 | stringing:820ff6ab2916d13a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-02-28 | 2025-02-01 | 138/0 | 139/0 | TSE | Ready | 1238.994 | 2025-03-02 | 2025-03-04 | Completed | 1.239 | 0.2065 | stringing:d34e51193a11763b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-01 | 2025-03-01 | 138/0 | 139/0 | TSE | Ready | 1238.994 | 2025-03-02 | 2025-03-04 | Completed | 1.239 | 0.2065 | stringing:e253c9ff21dc50c0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-02 | 2025-03-01 | 138/0 | 139/0 | TSE | Ready | 1238.994 | 2025-03-02 | 2025-03-04 | Completed | 1.239 | 0.2065 | stringing:b52fdf6aefed88bc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-03 | 2025-03-01 | 138/0 | 139/0 | TSE | Ready | 1238.994 | 2025-03-02 | 2025-03-04 | Completed | 1.239 | 0.2065 | stringing:f608b928324d3b0c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-04 | 2025-03-01 | 138/0 | 139/0 | TSE | Ready | 1238.994 | 2025-03-02 | 2025-03-04 | Completed | 1.239 | 0.2065 | stringing:cbb85e4c344580ad | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-02 | 2025-03-01 | 261/0 | 262/0 | Hotline | Ready | 242 | 2025-03-06 | 2025-03-08 | Completed | 0.242 | 0.034571 | stringing:31995368688ae355 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-03 | 2025-03-01 | 261/0 | 262/0 | Hotline | Ready | 242 | 2025-03-06 | 2025-03-08 | Completed | 0.242 | 0.034571 | stringing:0ffbb376db6410e5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-04 | 2025-03-01 | 261/0 | 262/0 | Hotline | Ready | 242 | 2025-03-06 | 2025-03-08 | Completed | 0.242 | 0.034571 | stringing:1838a3ca7b0393ae | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-05 | 2025-03-01 | 261/0 | 262/0 | Hotline | Ready | 242 | 2025-03-06 | 2025-03-08 | Completed | 0.242 | 0.034571 | stringing:79091d57fbc35669 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-06 | 2025-03-01 | 261/0 | 262/0 | Hotline | Ready | 242 | 2025-03-06 | 2025-03-08 | Completed | 0.242 | 0.034571 | stringing:251ceb72885ac8dd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-07 | 2025-03-01 | 261/0 | 262/0 | Hotline | Ready | 242 | 2025-03-06 | 2025-03-08 | Completed | 0.242 | 0.034571 | stringing:bdf05be16cca5fe7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-08 | 2025-03-01 | 261/0 | 262/0 | Hotline | Ready | 242 | 2025-03-06 | 2025-03-08 | Completed | 0.242 | 0.034571 | stringing:77464298c1e8a014 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-02 | 2025-03-01 | 139/0 | 139A/0 | TSE | Ready | 1211.03 | 2025-03-07 | 2025-03-09 | Completed | 1.211 | 0.15138 | stringing:941c5044d69b8738 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-03 | 2025-03-01 | 139/0 | 139A/0 | TSE | Ready | 1211.03 | 2025-03-07 | 2025-03-09 | Completed | 1.211 | 0.15138 | stringing:54c725fd87e8ec43 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-04 | 2025-03-01 | 139/0 | 139A/0 | TSE | Ready | 1211.03 | 2025-03-07 | 2025-03-09 | Completed | 1.211 | 0.15138 | stringing:b368711b2a8fee0c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-05 | 2025-03-01 | 139/0 | 139A/0 | TSE | Ready | 1211.03 | 2025-03-07 | 2025-03-09 | Completed | 1.211 | 0.15138 | stringing:c76623c57698a951 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-06 | 2025-03-01 | 139/0 | 139A/0 | TSE | Ready | 1211.03 | 2025-03-07 | 2025-03-09 | Completed | 1.211 | 0.15138 | stringing:578c971d4f2f0105 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-07 | 2025-03-01 | 139/0 | 139A/0 | TSE | Ready | 1211.03 | 2025-03-07 | 2025-03-09 | Completed | 1.211 | 0.15138 | stringing:3a3b48ad1f8a94fe | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-08 | 2025-03-01 | 139/0 | 139A/0 | TSE | Ready | 1211.03 | 2025-03-07 | 2025-03-09 | Completed | 1.211 | 0.15138 | stringing:174b7f55fa510a63 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-09 | 2025-03-01 | 139/0 | 139A/0 | TSE | Ready | 1211.03 | 2025-03-07 | 2025-03-09 | Completed | 1.211 | 0.15138 | stringing:fbdc2c67f204df76 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-03-03 | 2025-03-01 | 130/0 | 131/0 | TSE | Ready | 2041.128 | 2025-03-07 | 2025-03-10 | Completed | 2.0411 | 0.25514 | stringing:bd977285632bb23e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-03-04 | 2025-03-01 | 130/0 | 131/0 | TSE | Ready | 2041.128 | 2025-03-07 | 2025-03-10 | Completed | 2.0411 | 0.25514 | stringing:c38ec8bf6ac21673 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-03-05 | 2025-03-01 | 130/0 | 131/0 | TSE | Ready | 2041.128 | 2025-03-07 | 2025-03-10 | Completed | 2.0411 | 0.25514 | stringing:8b1b71dee529d967 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-03-06 | 2025-03-01 | 130/0 | 131/0 | TSE | Ready | 2041.128 | 2025-03-07 | 2025-03-10 | Completed | 2.0411 | 0.25514 | stringing:32038ab31abfcbd7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-03-07 | 2025-03-01 | 130/0 | 131/0 | TSE | Ready | 2041.128 | 2025-03-07 | 2025-03-10 | Completed | 2.0411 | 0.25514 | stringing:2bf1608f3442f8b2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-03-08 | 2025-03-01 | 130/0 | 131/0 | TSE | Ready | 2041.128 | 2025-03-07 | 2025-03-10 | Completed | 2.0411 | 0.25514 | stringing:e9344cba28fb5793 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-03-09 | 2025-03-01 | 130/0 | 131/0 | TSE | Ready | 2041.128 | 2025-03-07 | 2025-03-10 | Completed | 2.0411 | 0.25514 | stringing:afa68689b2a0b997 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-03-10 | 2025-03-01 | 130/0 | 131/0 | TSE | Ready | 2041.128 | 2025-03-07 | 2025-03-10 | Completed | 2.0411 | 0.25514 | stringing:6b1f5b2b7d3d17dd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-06 | 2025-03-01 | 131/0 | 132/0 | Hotline | Ready | 236.46 | 2025-03-06 | 2025-03-10 | Completed | 0.23646 | 0.047292 | stringing:0bdc50ba64f3c662 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-07 | 2025-03-01 | 131/0 | 132/0 | Hotline | Ready | 236.46 | 2025-03-06 | 2025-03-10 | Completed | 0.23646 | 0.047292 | stringing:d6cf8f93b2b5dcad | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-08 | 2025-03-01 | 131/0 | 132/0 | Hotline | Ready | 236.46 | 2025-03-06 | 2025-03-10 | Completed | 0.23646 | 0.047292 | stringing:47412ae580134d7b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-09 | 2025-03-01 | 131/0 | 132/0 | Hotline | Ready | 236.46 | 2025-03-06 | 2025-03-10 | Completed | 0.23646 | 0.047292 | stringing:edb24d13992a6bfe | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-10 | 2025-03-01 | 131/0 | 132/0 | Hotline | Ready | 236.46 | 2025-03-06 | 2025-03-10 | Completed | 0.23646 | 0.047292 | stringing:ffa5c07a0728f92d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-27 | 2025-02-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:0cf8d0e0a9eef856 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-02-28 | 2025-02-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:9e2ffb9dfcdbbe73 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-01 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:01f5ad125ea92f7d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-02 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:073902f7c330d1d3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-03 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:45ba1500deb8ed8b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-04 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:67b39214b2c0269a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-05 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:be0efd29d467af63 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-06 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:1eb3dbe5af071360 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-07 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:f5319b5d5d683bc4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-08 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:90c13757a6fa886d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-09 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:7ba910ac6a2f58d1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-10 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:64e3427ef1bc5131 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-11 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:5c33efd9bd8975f8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-12 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:1d3ad9f68178d385 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | SK Zenarul | 2025-03-13 | 2025-03-01 | 139A/0 | 140/0 | Manual | Ready | 427.14 | 2025-03-07 | 2025-03-13 | Completed | 0.42714 | 0.028476 | stringing:f97caa31b191cd84 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-17 | 2025-02-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:ca6fdfc6819dd843 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-18 | 2025-02-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:f142624f6269c05f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-19 | 2025-02-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:4748afaf3e1bc537 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-20 | 2025-02-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:c43aab59862aaaf5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-21 | 2025-02-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:c24044cab76653aa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-22 | 2025-02-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:5d4550a269f13eb6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-23 | 2025-02-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:1c7b67b8f28dcfc9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-24 | 2025-02-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:dc610b54e8216afd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-25 | 2025-02-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:b0406b292b0cc516 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-26 | 2025-02-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:ea20920522fcb2b4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-27 | 2025-02-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:769afc822b00817a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-28 | 2025-02-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:839cbebd1fb625e9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-01 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:936a3fc474197c64 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-02 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:6cd9df7976fcdd4f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-03 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:f544bb7195409b22 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-04 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:1d9b6c2240c6c1a9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-05 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:153537f5289f617b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-06 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:f512d2e372a89cc4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-07 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:357f674518e9bf06 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-08 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:61f31a897aacbe2c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-09 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:2def162c31fda613 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-10 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:237a41e7d8c77180 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-11 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:cb3048593dcc7db6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-12 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:0ba6c77038608a11 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-13 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:e944d2be25265338 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-14 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:4a21838b3720ae3b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-15 | 2025-03-01 | 262/0 | 263/0 | Manual | Ready | 686 | 2025-03-12 | 2025-03-15 | Completed | 0.686 | 0.025407 | stringing:c3f80cc6b2390787 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-11 | 2025-03-01 | 263/0 | 264/0 | Hotline | Ready | 243 | 2025-03-13 | 2025-03-15 | Completed | 0.243 | 0.0486 | stringing:7ac6a21ff86fd193 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-12 | 2025-03-01 | 263/0 | 264/0 | Hotline | Ready | 243 | 2025-03-13 | 2025-03-15 | Completed | 0.243 | 0.0486 | stringing:4dbdb961117e5ecb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-13 | 2025-03-01 | 263/0 | 264/0 | Hotline | Ready | 243 | 2025-03-13 | 2025-03-15 | Completed | 0.243 | 0.0486 | stringing:d8e08476926dd679 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-14 | 2025-03-01 | 263/0 | 264/0 | Hotline | Ready | 243 | 2025-03-13 | 2025-03-15 | Completed | 0.243 | 0.0486 | stringing:fda1ac6a4a3eb8f5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-15 | 2025-03-01 | 263/0 | 264/0 | Hotline | Ready | 243 | 2025-03-13 | 2025-03-15 | Completed | 0.243 | 0.0486 | stringing:00673bda1c1c5262 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul + Alam Constrution | 2025-03-18 | 2025-03-01 | 142/0 | 143/0 | Manual | Ready | 223.38 | 2025-03-18 | 2025-03-18 | Completed | 0.22338 | 0.22338 | stringing:5badf0868a857ff5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-08 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:344736473ada5f18 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-09 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:a35eb6c6793dba23 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-10 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:4e7b42f7897a781c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-11 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:e9d20bc919024f0f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-12 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:7e5f59aacc325de7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-13 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:7544a8366a87c738 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-14 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:c8c7b2afe70476e1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-15 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:517c394be4b8fc89 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-16 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:7184f14f7eb5167e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-17 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:4a3e5190442713a2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-18 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:eb41c2782ae31629 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-19 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:b5119329d073fe3f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-20 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:701f6b6470b5619f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-21 | 2025-03-01 | 143/0 | 143A/0 | Manual | Ready | 393.22 | 2025-03-20 | 2025-03-21 | Completed | 0.39322 | 0.028087 | stringing:5ab9fff46e17b9b9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-12 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:a7aa8130af05ecca | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-13 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:7cbe91cf42629e50 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-14 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:6dffea7e1fc5a091 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-15 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:2155fbe7d354065d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-16 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:21698436268b69fc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-17 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:f1ae8a2d916e0111 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-18 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:319a59b234325a35 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-19 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:f502aab224c0635c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-20 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:18b8531de7be0811 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-21 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:511ef8690da272f4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-22 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:4b1cc8404e7acfe0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-23 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:5886179bcb3f758f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-24 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:31b87f1640c2733e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-25 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:9bd7f39ef452abb4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-26 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:37d05691736865f6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-27 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:9893852af09ba69e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-02-28 | 2025-02-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:63e008d788b420fa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-01 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:f423c009c4373282 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-02 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:f11a5e223c36150f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-03 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:28b327d7920dfbcc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-04 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:5780c97545fe8446 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-05 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:c78c8a626a1606cc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-06 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:5349a28981249ff9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-07 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:beed59c9d7d4b4fa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-08 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:acb9ed6c3b74a9ec | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-09 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:f4c732c06072650d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-10 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:23b92d97bd496688 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-11 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:bbfa54242ea7498b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-12 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:d3d2636aa06ca567 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-13 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:a9dacc48c09b561e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-14 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:96ad70742ba08ea8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-15 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:6fd8bd372cef19fd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-16 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:3109788a57f6b4b7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-17 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:85bfe828e7338274 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-18 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:c24b943eb283df4d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-19 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:6d7f3482b4b926b2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-20 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:4f6cb182f04e344f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-21 | 2025-03-01 | 255/0 | 257/0 | TSE | Ready | 1839 | 2025-03-20 | 2025-03-21 | Completed | 1.839 | 0.048395 | stringing:b2870e6e2edbfe7f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-16 | 2025-03-01 | 265/0 | 266/0 | Hotline | Ready | 223 | 2025-03-19 | 2025-03-21 | Completed | 0.223 | 0.037167 | stringing:774383b13e0c6fb1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-17 | 2025-03-01 | 265/0 | 266/0 | Hotline | Ready | 223 | 2025-03-19 | 2025-03-21 | Completed | 0.223 | 0.037167 | stringing:e3e0dc385732cc76 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-18 | 2025-03-01 | 265/0 | 266/0 | Hotline | Ready | 223 | 2025-03-19 | 2025-03-21 | Completed | 0.223 | 0.037167 | stringing:1ceef45c1cc458c6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-19 | 2025-03-01 | 265/0 | 266/0 | Hotline | Ready | 223 | 2025-03-19 | 2025-03-21 | Completed | 0.223 | 0.037167 | stringing:59d0825421eba9a1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-20 | 2025-03-01 | 265/0 | 266/0 | Hotline | Ready | 223 | 2025-03-19 | 2025-03-21 | Completed | 0.223 | 0.037167 | stringing:2e9f1d3f3fb81169 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-21 | 2025-03-01 | 265/0 | 266/0 | Hotline | Ready | 223 | 2025-03-19 | 2025-03-21 | Completed | 0.223 | 0.037167 | stringing:1eab76fd65c2ad2a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-18 | 2025-03-01 | 134/0 | 135/0 | Hotline | Ready | 235.87 | 2025-03-18 | 2025-03-22 | Completed | 0.23587 | 0.047174 | stringing:0fabd13fbb668278 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-19 | 2025-03-01 | 134/0 | 135/0 | Hotline | Ready | 235.87 | 2025-03-18 | 2025-03-22 | Completed | 0.23587 | 0.047174 | stringing:455ee956d6015c25 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-20 | 2025-03-01 | 134/0 | 135/0 | Hotline | Ready | 235.87 | 2025-03-18 | 2025-03-22 | Completed | 0.23587 | 0.047174 | stringing:8f1a0562205c7e0d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-21 | 2025-03-01 | 134/0 | 135/0 | Hotline | Ready | 235.87 | 2025-03-18 | 2025-03-22 | Completed | 0.23587 | 0.047174 | stringing:4107a59847dc7a30 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-22 | 2025-03-01 | 134/0 | 135/0 | Hotline | Ready | 235.87 | 2025-03-18 | 2025-03-22 | Completed | 0.23587 | 0.047174 | stringing:c2b0d2852525dc97 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-24 | 2025-02-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:4a8ac7a1d5e08bf6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-25 | 2025-02-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:d6bbb6f2cf8963fa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-26 | 2025-02-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:09b62df4236e85d8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-27 | 2025-02-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:3f1f8e55049e4427 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-02-28 | 2025-02-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:f3ea096cf81c7329 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-01 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:c50eee64cfbdd8c7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-02 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:2b52142f3dcd3a9c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-03 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:d6dbc8b5593c9104 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-04 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:46cffbe167e61652 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-05 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:f5d5077df3e60a86 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-06 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:aaa8bfcdd75136e8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-07 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:96028056e62dd5e1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-08 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:26b2bdf20053120e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-09 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:84d1b89ebf124666 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-10 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:da3923c1a5c5beac | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-11 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:c91dafff24a28040 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-12 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:f305213695150d5a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-13 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:0b1a98722d3f6bca | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-14 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:0d43ef844df8f3dc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-15 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:f2e4fac525e5195a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-16 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:6069497e044ba7e6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-17 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:35a9eb8bfe1c2969 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-18 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:41b456e8579e3899 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-19 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:4c74672787e0eded | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-20 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:a47769aab0c74b61 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-21 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:78e207e8d4b04472 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-22 | 2025-03-01 | 163/0 | 163/5 | TSE | Ready | 1894 | 2025-03-21 | 2025-03-22 | Completed | 1.894 | 0.070148 | stringing:839fc158270dfb41 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-21 | 2025-03-01 | 163/5 | 163/6 | Hotline | Ready | 339 | 2025-03-21 | 2025-03-22 | Completed | 0.339 | 0.1695 | stringing:46c05d35fd54892a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-22 | 2025-03-01 | 163/5 | 163/6 | Hotline | Ready | 339 | 2025-03-21 | 2025-03-22 | Completed | 0.339 | 0.1695 | stringing:3cd60e26f040e95e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-04 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:23e805cf3b1afb86 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-05 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:dd0f0888597107da | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-06 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:078c677d0d12103d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-07 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:43f2ec0e99ea0ec9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-08 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:11ab9fb6775557c7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-09 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:80aef16c655ba5b9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-10 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:8530e221a63b10e7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-11 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:e06cd0f6838c9d5d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-12 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:87f4d74229c0168c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-13 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:30d06a9041db6ccb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-14 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:a3153b6aed19ca09 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-15 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:fecc0a0fac48d19c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-16 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:8ffa0287fb639378 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-17 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:9e1a68704fdcea98 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-18 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:2c19b02f8f2b1563 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-19 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:c54e5e36f0d8be83 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-20 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:80569783f8b15e6a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-21 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:8c9eddd6a8642a30 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-03-22 | 2025-03-01 | 163/6 | 164/0 | TSE | Ready | 343 | 2025-03-21 | 2025-03-22 | Completed | 0.343 | 0.018053 | stringing:d40b41a5613c0724 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-16 | 2025-03-01 | 264/0 | 265/0 | Manual | Ready | 441 | 2025-03-19 | 2025-03-22 | Completed | 0.441 | 0.063 | stringing:66ce1f27395d4f64 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-17 | 2025-03-01 | 264/0 | 265/0 | Manual | Ready | 441 | 2025-03-19 | 2025-03-22 | Completed | 0.441 | 0.063 | stringing:12f78de0e7e7def7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-18 | 2025-03-01 | 264/0 | 265/0 | Manual | Ready | 441 | 2025-03-19 | 2025-03-22 | Completed | 0.441 | 0.063 | stringing:0e41c63631d4c51f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-19 | 2025-03-01 | 264/0 | 265/0 | Manual | Ready | 441 | 2025-03-19 | 2025-03-22 | Completed | 0.441 | 0.063 | stringing:0b9088e55598b4bf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-20 | 2025-03-01 | 264/0 | 265/0 | Manual | Ready | 441 | 2025-03-19 | 2025-03-22 | Completed | 0.441 | 0.063 | stringing:9bee6c6258f9f8ce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-21 | 2025-03-01 | 264/0 | 265/0 | Manual | Ready | 441 | 2025-03-19 | 2025-03-22 | Completed | 0.441 | 0.063 | stringing:a2877bba689590a1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-22 | 2025-03-01 | 264/0 | 265/0 | Manual | Ready | 441 | 2025-03-19 | 2025-03-22 | Completed | 0.441 | 0.063 | stringing:5c271bc74c88a8bb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-19 | 2025-03-01 | 143A/0 | 143A/2 | Manual | Ready | 841.2 | 2025-03-23 | 2025-03-26 | Completed | 0.8412 | 0.10515 | stringing:f895f03beca58353 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-20 | 2025-03-01 | 143A/0 | 143A/2 | Manual | Ready | 841.2 | 2025-03-23 | 2025-03-26 | Completed | 0.8412 | 0.10515 | stringing:8d582e03fff23d41 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-21 | 2025-03-01 | 143A/0 | 143A/2 | Manual | Ready | 841.2 | 2025-03-23 | 2025-03-26 | Completed | 0.8412 | 0.10515 | stringing:87ab98875b10b0b6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-22 | 2025-03-01 | 143A/0 | 143A/2 | Manual | Ready | 841.2 | 2025-03-23 | 2025-03-26 | Completed | 0.8412 | 0.10515 | stringing:61a8ebf53a855866 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-23 | 2025-03-01 | 143A/0 | 143A/2 | Manual | Ready | 841.2 | 2025-03-23 | 2025-03-26 | Completed | 0.8412 | 0.10515 | stringing:5a55b411985e17f4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-24 | 2025-03-01 | 143A/0 | 143A/2 | Manual | Ready | 841.2 | 2025-03-23 | 2025-03-26 | Completed | 0.8412 | 0.10515 | stringing:5d23aa8e07e8c291 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-25 | 2025-03-01 | 143A/0 | 143A/2 | Manual | Ready | 841.2 | 2025-03-23 | 2025-03-26 | Completed | 0.8412 | 0.10515 | stringing:4303901cd28eb9b5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-03-26 | 2025-03-01 | 143A/0 | 143A/2 | Manual | Ready | 841.2 | 2025-03-23 | 2025-03-26 | Completed | 0.8412 | 0.10515 | stringing:84152ab1c9d20e9e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-23 | 2025-03-01 | 143A/2 | 143A/3 | Manual | Ready | 413.09 | 2025-03-23 | 2025-03-26 | Completed | 0.41309 | 0.10327 | stringing:aae20594fbae9159 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-24 | 2025-03-01 | 143A/2 | 143A/3 | Manual | Ready | 413.09 | 2025-03-23 | 2025-03-26 | Completed | 0.41309 | 0.10327 | stringing:beced95b8170e99c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-25 | 2025-03-01 | 143A/2 | 143A/3 | Manual | Ready | 413.09 | 2025-03-23 | 2025-03-26 | Completed | 0.41309 | 0.10327 | stringing:cb377fe6e44ffc67 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-26 | 2025-03-01 | 143A/2 | 143A/3 | Manual | Ready | 413.09 | 2025-03-23 | 2025-03-26 | Completed | 0.41309 | 0.10327 | stringing:6788ba9c96fb8583 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-18 | 2025-03-01 | 143A/3 | 144/0 | TSE | Ready | 1246.06 | 2025-03-23 | 2025-03-26 | Completed | 1.2461 | 0.13845 | stringing:78897048b306864e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-19 | 2025-03-01 | 143A/3 | 144/0 | TSE | Ready | 1246.06 | 2025-03-23 | 2025-03-26 | Completed | 1.2461 | 0.13845 | stringing:8b7b4229d134c876 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-20 | 2025-03-01 | 143A/3 | 144/0 | TSE | Ready | 1246.06 | 2025-03-23 | 2025-03-26 | Completed | 1.2461 | 0.13845 | stringing:0cefe484b0011bb7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-21 | 2025-03-01 | 143A/3 | 144/0 | TSE | Ready | 1246.06 | 2025-03-23 | 2025-03-26 | Completed | 1.2461 | 0.13845 | stringing:c7415a9575a3a155 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-22 | 2025-03-01 | 143A/3 | 144/0 | TSE | Ready | 1246.06 | 2025-03-23 | 2025-03-26 | Completed | 1.2461 | 0.13845 | stringing:b71a72110ab43200 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-23 | 2025-03-01 | 143A/3 | 144/0 | TSE | Ready | 1246.06 | 2025-03-23 | 2025-03-26 | Completed | 1.2461 | 0.13845 | stringing:a5fb9f98a3cc2bb2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-24 | 2025-03-01 | 143A/3 | 144/0 | TSE | Ready | 1246.06 | 2025-03-23 | 2025-03-26 | Completed | 1.2461 | 0.13845 | stringing:0ba94e69ed7f15b9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-25 | 2025-03-01 | 143A/3 | 144/0 | TSE | Ready | 1246.06 | 2025-03-23 | 2025-03-26 | Completed | 1.2461 | 0.13845 | stringing:61927c6b8c56c42c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-03-26 | 2025-03-01 | 143A/3 | 144/0 | TSE | Ready | 1246.06 | 2025-03-23 | 2025-03-26 | Completed | 1.2461 | 0.13845 | stringing:e1a9958336ad9546 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-23 | 2025-03-01 | 266/0 | 266/1 | Hotline | Ready | 340 | 2025-03-25 | 2025-03-28 | Completed | 0.34 | 0.056667 | stringing:82f648833c0d0bbb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-24 | 2025-03-01 | 266/0 | 266/1 | Hotline | Ready | 340 | 2025-03-25 | 2025-03-28 | Completed | 0.34 | 0.056667 | stringing:6916eeb041fa3f1c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-25 | 2025-03-01 | 266/0 | 266/1 | Hotline | Ready | 340 | 2025-03-25 | 2025-03-28 | Completed | 0.34 | 0.056667 | stringing:76440c0d2cb08b1f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-26 | 2025-03-01 | 266/0 | 266/1 | Hotline | Ready | 340 | 2025-03-25 | 2025-03-28 | Completed | 0.34 | 0.056667 | stringing:157e89b5ab65838f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-27 | 2025-03-01 | 266/0 | 266/1 | Hotline | Ready | 340 | 2025-03-25 | 2025-03-28 | Completed | 0.34 | 0.056667 | stringing:358dbfdb91ba1689 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-03-28 | 2025-03-01 | 266/0 | 266/1 | Hotline | Ready | 340 | 2025-03-25 | 2025-03-28 | Completed | 0.34 | 0.056667 | stringing:d0b003982cf3ec53 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-22 | 2025-03-01 | 266/1 | 267/0 | Manual | Ready | 835 | 2025-03-25 | 2025-03-28 | Completed | 0.835 | 0.11929 | stringing:71a495c01d757c48 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-23 | 2025-03-01 | 266/1 | 267/0 | Manual | Ready | 835 | 2025-03-25 | 2025-03-28 | Completed | 0.835 | 0.11929 | stringing:d94ca2e038abd929 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-24 | 2025-03-01 | 266/1 | 267/0 | Manual | Ready | 835 | 2025-03-25 | 2025-03-28 | Completed | 0.835 | 0.11929 | stringing:1873825938f7ff7b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-25 | 2025-03-01 | 266/1 | 267/0 | Manual | Ready | 835 | 2025-03-25 | 2025-03-28 | Completed | 0.835 | 0.11929 | stringing:ff829ebc3c855cef | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-26 | 2025-03-01 | 266/1 | 267/0 | Manual | Ready | 835 | 2025-03-25 | 2025-03-28 | Completed | 0.835 | 0.11929 | stringing:4a853d709ff392aa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-27 | 2025-03-01 | 266/1 | 267/0 | Manual | Ready | 835 | 2025-03-25 | 2025-03-28 | Completed | 0.835 | 0.11929 | stringing:eb7071aeaa71aaa0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-28 | 2025-03-01 | 266/1 | 267/0 | Manual | Ready | 835 | 2025-03-25 | 2025-03-28 | Completed | 0.835 | 0.11929 | stringing:939c35486be0a3d2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-26 | 2025-03-01 | 136/0 | 137/0 | Hotline | Ready | 425.58 | 2025-03-26 | 2025-04-01 | Completed | 0.42558 | 0.060797 | stringing:be4a52d8bd2673d8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-27 | 2025-03-01 | 136/0 | 137/0 | Hotline | Ready | 425.58 | 2025-03-26 | 2025-04-01 | Completed | 0.42558 | 0.060797 | stringing:257c51ca0c31778a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-28 | 2025-03-01 | 136/0 | 137/0 | Hotline | Ready | 425.58 | 2025-03-26 | 2025-04-01 | Completed | 0.42558 | 0.060797 | stringing:7069dea2adcc1160 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-29 | 2025-03-01 | 136/0 | 137/0 | Hotline | Ready | 425.58 | 2025-03-26 | 2025-04-01 | Completed | 0.42558 | 0.060797 | stringing:9084c75284ecbb94 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-30 | 2025-03-01 | 136/0 | 137/0 | Hotline | Ready | 425.58 | 2025-03-26 | 2025-04-01 | Completed | 0.42558 | 0.060797 | stringing:bc75009c1acb6d56 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-03-31 | 2025-03-01 | 136/0 | 137/0 | Hotline | Ready | 425.58 | 2025-03-26 | 2025-04-01 | Completed | 0.42558 | 0.060797 | stringing:655e5794785330d7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-01 | 2025-04-01 | 136/0 | 137/0 | Hotline | Ready | 425.58 | 2025-03-26 | 2025-04-01 | Completed | 0.42558 | 0.060797 | stringing:f728bcf16c6396a7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-05 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:2c26ec36b9a50d55 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-06 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:ebc164b7d71cbe68 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-07 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:5abf763a0a1c99fe | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-08 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:da56cccf70cf9cfa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-09 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:88181fad8eb4bfa8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-10 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:cbe4032967af7078 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-11 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:60580bfd075f2839 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-12 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:2bd99af02d80626b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-13 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:f9551c5cd58b5547 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-14 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:575c782acead639f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-15 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:2b2478a53b51e7cd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-16 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:7c235559a24cd896 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-17 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:7f54ae57d715b36a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-18 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:baf960501560d8ce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-19 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:1a9db84d21334efc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-20 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:0c5ef3bbdd0f082b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-21 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:4190cbcf629dd943 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-22 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:95edc459cfc496e4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-23 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:f7390944f621d9e4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-24 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:f05c36f75ef4877f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-25 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:9d80337967509a85 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-26 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:427f74214094e1e1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-27 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:54009c1d43c1a2f5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-28 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:6237b42505938359 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-29 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:8ca1e678eae85495 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-30 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:00caa762ea8d9179 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-03-31 | 2025-03-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:387437d797f15747 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam construction | 2025-04-01 | 2025-04-01 | 137/0 | 137A/0 | TSE | Ready | 2827.097 | 2025-03-26 | 2025-04-01 | Completed | 2.8271 | 0.10097 | stringing:d5632b2d76fdd06b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-02 | 2025-04-01 | 145A/0 | 146/0 | TSE | Ready | 1620.89 | 2025-04-07 | 2025-04-08 | Completed | 1.6209 | 0.23156 | stringing:e313e8f93d8bc939 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-03 | 2025-04-01 | 145A/0 | 146/0 | TSE | Ready | 1620.89 | 2025-04-07 | 2025-04-08 | Completed | 1.6209 | 0.23156 | stringing:94d91b67e2987a3d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-04 | 2025-04-01 | 145A/0 | 146/0 | TSE | Ready | 1620.89 | 2025-04-07 | 2025-04-08 | Completed | 1.6209 | 0.23156 | stringing:5abbff3956da551a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-05 | 2025-04-01 | 145A/0 | 146/0 | TSE | Ready | 1620.89 | 2025-04-07 | 2025-04-08 | Completed | 1.6209 | 0.23156 | stringing:ef4846d610f135ed | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-06 | 2025-04-01 | 145A/0 | 146/0 | TSE | Ready | 1620.89 | 2025-04-07 | 2025-04-08 | Completed | 1.6209 | 0.23156 | stringing:be314af3785c42fb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-07 | 2025-04-01 | 145A/0 | 146/0 | TSE | Ready | 1620.89 | 2025-04-07 | 2025-04-08 | Completed | 1.6209 | 0.23156 | stringing:74e2524ee5b7118e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-08 | 2025-04-01 | 145A/0 | 146/0 | TSE | Ready | 1620.89 | 2025-04-07 | 2025-04-08 | Completed | 1.6209 | 0.23156 | stringing:2304660bfa5e6313 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-04 | 2025-04-01 | 253/0 | 254/0 | Hotline | Ready | 246 | 2025-04-07 | 2025-04-08 | Completed | 0.246 | 0.0492 | stringing:5f294bfc7b07b25f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-05 | 2025-04-01 | 253/0 | 254/0 | Hotline | Ready | 246 | 2025-04-07 | 2025-04-08 | Completed | 0.246 | 0.0492 | stringing:c85d71f285c64ad2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-06 | 2025-04-01 | 253/0 | 254/0 | Hotline | Ready | 246 | 2025-04-07 | 2025-04-08 | Completed | 0.246 | 0.0492 | stringing:581c888ef360bed3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-07 | 2025-04-01 | 253/0 | 254/0 | Hotline | Ready | 246 | 2025-04-07 | 2025-04-08 | Completed | 0.246 | 0.0492 | stringing:8d9957756034c5fa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-08 | 2025-04-01 | 253/0 | 254/0 | Hotline | Ready | 246 | 2025-04-07 | 2025-04-08 | Completed | 0.246 | 0.0492 | stringing:d8460bcc08724d1f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-26 | 2025-02-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:460b94c08d5a1f14 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-27 | 2025-02-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:07dcfe6ebe8dfd6e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-02-28 | 2025-02-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:f1dbb1558a95db0d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-01 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:637e93ef067a664b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-02 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:fe54b0c6714c4428 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-03 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:1e05f70433ea6c97 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-04 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:54e8f787969b5f08 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-05 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:3dc8102dfb97c08b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-06 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:5fa19a96e6591c1a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-07 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:640f1e1cc3054121 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-08 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:e696faf1e31111ec | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-09 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:0263bad569fe6412 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-10 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:1ebe311e568b8863 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-11 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:7d88b591e4d85d59 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-12 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:e42c4adcdc0b062a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-13 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:b55d7ed3e3ac9f57 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-14 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:94a48e7fcc9b0728 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-15 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:1455b56fd784d014 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-16 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:54b602bab174f467 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-17 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:813c168c12b1a13f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-18 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:874c7a4342187256 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-19 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:8ed1b893be38d09d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-20 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:6c2b5e2538c31b68 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-21 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:49e86f7b48daaf0d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-22 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:981ca8b026848fe0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-23 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:b809093eb5aea924 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-24 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:c2b54b341712e73d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-25 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:a456548122e11025 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-26 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:3bb905082b75a585 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-27 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:07fa379063f8de9d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-28 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:591220415727126c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-29 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:859e2a7621546c61 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-30 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:582d9052d43410cf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-03-31 | 2025-03-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:e83b80730adc1fd6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-04-01 | 2025-04-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:d9732093406c5d4d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-04-02 | 2025-04-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:2064b612991e579b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-04-03 | 2025-04-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:893ac93ec94ef47a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-04-04 | 2025-04-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:d9210e7a9546883a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-04-05 | 2025-04-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:4f96beadbd36ddc9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-04-06 | 2025-04-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:fb8e6f6616e17872 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-04-07 | 2025-04-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:bab12233e5306ed9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Monera | 2025-04-08 | 2025-04-01 | 254/0 | 255/0 | Manual | Ready | 300 | 2025-04-07 | 2025-04-08 | Completed | 0.3 | 0.0071429 | stringing:c769e5a43baea8e8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin Deepak Sarkar | 2025-04-01 | 2025-04-01 | 267/0 | 267A/0 | Manual | Ready | 511 | 2025-04-07 | 2025-04-10 | Completed | 0.511 | 0.0511 | stringing:f53694986ffbff30 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin Deepak Sarkar | 2025-04-02 | 2025-04-01 | 267/0 | 267A/0 | Manual | Ready | 511 | 2025-04-07 | 2025-04-10 | Completed | 0.511 | 0.0511 | stringing:6014f6b9fde8a55b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin Deepak Sarkar | 2025-04-03 | 2025-04-01 | 267/0 | 267A/0 | Manual | Ready | 511 | 2025-04-07 | 2025-04-10 | Completed | 0.511 | 0.0511 | stringing:65ef538f6a38b874 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin Deepak Sarkar | 2025-04-04 | 2025-04-01 | 267/0 | 267A/0 | Manual | Ready | 511 | 2025-04-07 | 2025-04-10 | Completed | 0.511 | 0.0511 | stringing:5b134f9cce1619a3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin Deepak Sarkar | 2025-04-05 | 2025-04-01 | 267/0 | 267A/0 | Manual | Ready | 511 | 2025-04-07 | 2025-04-10 | Completed | 0.511 | 0.0511 | stringing:fe1d87f47326bdde | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin Deepak Sarkar | 2025-04-06 | 2025-04-01 | 267/0 | 267A/0 | Manual | Ready | 511 | 2025-04-07 | 2025-04-10 | Completed | 0.511 | 0.0511 | stringing:49634fd263768801 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin Deepak Sarkar | 2025-04-07 | 2025-04-01 | 267/0 | 267A/0 | Manual | Ready | 511 | 2025-04-07 | 2025-04-10 | Completed | 0.511 | 0.0511 | stringing:5986416d254e9f7d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin Deepak Sarkar | 2025-04-08 | 2025-04-01 | 267/0 | 267A/0 | Manual | Ready | 511 | 2025-04-07 | 2025-04-10 | Completed | 0.511 | 0.0511 | stringing:fc993b14e6e8ff5b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin Deepak Sarkar | 2025-04-09 | 2025-04-01 | 267/0 | 267A/0 | Manual | Ready | 511 | 2025-04-07 | 2025-04-10 | Completed | 0.511 | 0.0511 | stringing:a8f3ce2f991fafba | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin Deepak Sarkar | 2025-04-10 | 2025-04-01 | 267/0 | 267A/0 | Manual | Ready | 511 | 2025-04-07 | 2025-04-10 | Completed | 0.511 | 0.0511 | stringing:51736412972466fd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-27 | 2025-03-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:c95a6dc4e45bdaf1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-28 | 2025-03-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:2251d915e84d6a10 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-29 | 2025-03-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:b8d6fcca1d1b36fb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-30 | 2025-03-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:cde61772e806f662 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-03-31 | 2025-03-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:b019974d57c25a93 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-04-01 | 2025-04-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:d3998b0467ed310a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-04-02 | 2025-04-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:9910e9422ff54a02 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-04-03 | 2025-04-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:93bc99c2640605b8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-04-04 | 2025-04-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:5967f03d1dad827d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-04-05 | 2025-04-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:ac7ddd7d9e41a273 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-04-06 | 2025-04-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:943afa19334c15ea | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-04-07 | 2025-04-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:f9fbed51fff1f4ff | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-04-08 | 2025-04-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:7aee845260467d10 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-04-09 | 2025-04-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:8cf3b28adb536028 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-04-10 | 2025-04-01 | 267A/0 | 268/0 | TSE | Ready | 1440 | 2025-04-07 | 2025-04-10 | Completed | 1.44 | 0.096 | stringing:2e4c61fda86096d4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-05 | 2025-04-01 | 141/0 | 141/1 | TSE | Ready | 390 | 2025-04-11 | 2025-04-13 | Completed | 0.39 | 0.043333 | stringing:0f51862918cbad41 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-06 | 2025-04-01 | 141/0 | 141/1 | TSE | Ready | 390 | 2025-04-11 | 2025-04-13 | Completed | 0.39 | 0.043333 | stringing:b059b5b60dc5f9f9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-07 | 2025-04-01 | 141/0 | 141/1 | TSE | Ready | 390 | 2025-04-11 | 2025-04-13 | Completed | 0.39 | 0.043333 | stringing:dc37012ab2cbe1af | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-08 | 2025-04-01 | 141/0 | 141/1 | TSE | Ready | 390 | 2025-04-11 | 2025-04-13 | Completed | 0.39 | 0.043333 | stringing:e330050e0c64b995 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-09 | 2025-04-01 | 141/0 | 141/1 | TSE | Ready | 390 | 2025-04-11 | 2025-04-13 | Completed | 0.39 | 0.043333 | stringing:9d9337cfdc47d4d4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-10 | 2025-04-01 | 141/0 | 141/1 | TSE | Ready | 390 | 2025-04-11 | 2025-04-13 | Completed | 0.39 | 0.043333 | stringing:66def8b6cc8ef1c0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-11 | 2025-04-01 | 141/0 | 141/1 | TSE | Ready | 390 | 2025-04-11 | 2025-04-13 | Completed | 0.39 | 0.043333 | stringing:fa94edd140ce2167 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-12 | 2025-04-01 | 141/0 | 141/1 | TSE | Ready | 390 | 2025-04-11 | 2025-04-13 | Completed | 0.39 | 0.043333 | stringing:394d2a9f2d8e7604 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-13 | 2025-04-01 | 141/0 | 141/1 | TSE | Ready | 390 | 2025-04-11 | 2025-04-13 | Completed | 0.39 | 0.043333 | stringing:91bd23c2b7548877 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-05 | 2025-04-01 | 141/1 | 141/2 | Hotline | Ready | 370 | 2025-04-11 | 2025-04-13 | Completed | 0.37 | 0.041111 | stringing:aba1125833a78d43 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-06 | 2025-04-01 | 141/1 | 141/2 | Hotline | Ready | 370 | 2025-04-11 | 2025-04-13 | Completed | 0.37 | 0.041111 | stringing:3dbb4c7821e855fb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-07 | 2025-04-01 | 141/1 | 141/2 | Hotline | Ready | 370 | 2025-04-11 | 2025-04-13 | Completed | 0.37 | 0.041111 | stringing:b1abc595d956ef0a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-08 | 2025-04-01 | 141/1 | 141/2 | Hotline | Ready | 370 | 2025-04-11 | 2025-04-13 | Completed | 0.37 | 0.041111 | stringing:cffd85a049fa596a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-09 | 2025-04-01 | 141/1 | 141/2 | Hotline | Ready | 370 | 2025-04-11 | 2025-04-13 | Completed | 0.37 | 0.041111 | stringing:c76446ff02b58c41 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-10 | 2025-04-01 | 141/1 | 141/2 | Hotline | Ready | 370 | 2025-04-11 | 2025-04-13 | Completed | 0.37 | 0.041111 | stringing:eb7d09fecc1ac28c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-11 | 2025-04-01 | 141/1 | 141/2 | Hotline | Ready | 370 | 2025-04-11 | 2025-04-13 | Completed | 0.37 | 0.041111 | stringing:7cb233b8d409973f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-12 | 2025-04-01 | 141/1 | 141/2 | Hotline | Ready | 370 | 2025-04-11 | 2025-04-13 | Completed | 0.37 | 0.041111 | stringing:93b7bbaf72303e0b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-13 | 2025-04-01 | 141/1 | 141/2 | Hotline | Ready | 370 | 2025-04-11 | 2025-04-13 | Completed | 0.37 | 0.041111 | stringing:7a93ef2d510dbfb4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-05 | 2025-04-01 | 141/2 | 142/0 | TSE | Ready | 805.06 | 2025-04-11 | 2025-04-13 | Completed | 0.80506 | 0.089451 | stringing:934d0b819f0abf83 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-06 | 2025-04-01 | 141/2 | 142/0 | TSE | Ready | 805.06 | 2025-04-11 | 2025-04-13 | Completed | 0.80506 | 0.089451 | stringing:05a2d0a4e17af6ba | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-07 | 2025-04-01 | 141/2 | 142/0 | TSE | Ready | 805.06 | 2025-04-11 | 2025-04-13 | Completed | 0.80506 | 0.089451 | stringing:5e37442e60f19138 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-08 | 2025-04-01 | 141/2 | 142/0 | TSE | Ready | 805.06 | 2025-04-11 | 2025-04-13 | Completed | 0.80506 | 0.089451 | stringing:b5acea93f3805004 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-09 | 2025-04-01 | 141/2 | 142/0 | TSE | Ready | 805.06 | 2025-04-11 | 2025-04-13 | Completed | 0.80506 | 0.089451 | stringing:b9401ba23dfd090a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-10 | 2025-04-01 | 141/2 | 142/0 | TSE | Ready | 805.06 | 2025-04-11 | 2025-04-13 | Completed | 0.80506 | 0.089451 | stringing:c7822385e5414e68 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-11 | 2025-04-01 | 141/2 | 142/0 | TSE | Ready | 805.06 | 2025-04-11 | 2025-04-13 | Completed | 0.80506 | 0.089451 | stringing:77c1e13105d065f5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-12 | 2025-04-01 | 141/2 | 142/0 | TSE | Ready | 805.06 | 2025-04-11 | 2025-04-13 | Completed | 0.80506 | 0.089451 | stringing:7bb57b0aafd44f7b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-13 | 2025-04-01 | 141/2 | 142/0 | TSE | Ready | 805.06 | 2025-04-11 | 2025-04-13 | Completed | 0.80506 | 0.089451 | stringing:e588530130c5951a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-12 | 2025-04-01 | 146/0 | 147/0 | Hotline | Ready | 475.02 | 2025-04-12 | 2025-04-15 | Completed | 0.47502 | 0.11875 | stringing:42e0bd8514c3d53b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-13 | 2025-04-01 | 146/0 | 147/0 | Hotline | Ready | 475.02 | 2025-04-12 | 2025-04-15 | Completed | 0.47502 | 0.11875 | stringing:7d5d9be939a60f25 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-14 | 2025-04-01 | 146/0 | 147/0 | Hotline | Ready | 475.02 | 2025-04-12 | 2025-04-15 | Completed | 0.47502 | 0.11875 | stringing:60eb0b32eacd94f2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-15 | 2025-04-01 | 146/0 | 147/0 | Hotline | Ready | 475.02 | 2025-04-12 | 2025-04-15 | Completed | 0.47502 | 0.11875 | stringing:bb12a1deac13b7e0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-11 | 2025-04-01 | 147/0 | 147/1 | Hotline | Ready | 425.52 | 2025-04-11 | 2025-04-15 | Completed | 0.42552 | 0.085104 | stringing:8263f02caec8b404 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-12 | 2025-04-01 | 147/0 | 147/1 | Hotline | Ready | 425.52 | 2025-04-11 | 2025-04-15 | Completed | 0.42552 | 0.085104 | stringing:639a9c8aa4f0b5ab | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-13 | 2025-04-01 | 147/0 | 147/1 | Hotline | Ready | 425.52 | 2025-04-11 | 2025-04-15 | Completed | 0.42552 | 0.085104 | stringing:bfd10ce018fa1e7e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-14 | 2025-04-01 | 147/0 | 147/1 | Hotline | Ready | 425.52 | 2025-04-11 | 2025-04-15 | Completed | 0.42552 | 0.085104 | stringing:f9938498f250d0de | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-15 | 2025-04-01 | 147/0 | 147/1 | Hotline | Ready | 425.52 | 2025-04-11 | 2025-04-15 | Completed | 0.42552 | 0.085104 | stringing:e8095791221cdd93 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddinn + GPJ | 2025-04-04 | 2025-04-01 | 147B/0 | 148/0 | TSE | Ready | 827.56 | 2025-04-13 | 2025-04-15 | Completed | 0.82756 | 0.068963 | stringing:321c73508a7c2cd5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddinn + GPJ | 2025-04-05 | 2025-04-01 | 147B/0 | 148/0 | TSE | Ready | 827.56 | 2025-04-13 | 2025-04-15 | Completed | 0.82756 | 0.068963 | stringing:5c39566c8ea82b69 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddinn + GPJ | 2025-04-06 | 2025-04-01 | 147B/0 | 148/0 | TSE | Ready | 827.56 | 2025-04-13 | 2025-04-15 | Completed | 0.82756 | 0.068963 | stringing:3718739d3b69ebd8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddinn + GPJ | 2025-04-07 | 2025-04-01 | 147B/0 | 148/0 | TSE | Ready | 827.56 | 2025-04-13 | 2025-04-15 | Completed | 0.82756 | 0.068963 | stringing:d7a987bff9053bd7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddinn + GPJ | 2025-04-08 | 2025-04-01 | 147B/0 | 148/0 | TSE | Ready | 827.56 | 2025-04-13 | 2025-04-15 | Completed | 0.82756 | 0.068963 | stringing:0a2c728b1917b478 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddinn + GPJ | 2025-04-09 | 2025-04-01 | 147B/0 | 148/0 | TSE | Ready | 827.56 | 2025-04-13 | 2025-04-15 | Completed | 0.82756 | 0.068963 | stringing:159484a3a62b2b08 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddinn + GPJ | 2025-04-10 | 2025-04-01 | 147B/0 | 148/0 | TSE | Ready | 827.56 | 2025-04-13 | 2025-04-15 | Completed | 0.82756 | 0.068963 | stringing:546f4cbac1fd29d6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddinn + GPJ | 2025-04-11 | 2025-04-01 | 147B/0 | 148/0 | TSE | Ready | 827.56 | 2025-04-13 | 2025-04-15 | Completed | 0.82756 | 0.068963 | stringing:6e9930f3ccafe6d9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddinn + GPJ | 2025-04-12 | 2025-04-01 | 147B/0 | 148/0 | TSE | Ready | 827.56 | 2025-04-13 | 2025-04-15 | Completed | 0.82756 | 0.068963 | stringing:ce1ed517cd0fbf27 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddinn + GPJ | 2025-04-13 | 2025-04-01 | 147B/0 | 148/0 | TSE | Ready | 827.56 | 2025-04-13 | 2025-04-15 | Completed | 0.82756 | 0.068963 | stringing:d0cb811ecebd035d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddinn + GPJ | 2025-04-14 | 2025-04-01 | 147B/0 | 148/0 | TSE | Ready | 827.56 | 2025-04-13 | 2025-04-15 | Completed | 0.82756 | 0.068963 | stringing:31f39ea6c8ee6d34 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddinn + GPJ | 2025-04-15 | 2025-04-01 | 147B/0 | 148/0 | TSE | Ready | 827.56 | 2025-04-13 | 2025-04-15 | Completed | 0.82756 | 0.068963 | stringing:342d481408d79afb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-03 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:5407dd681e23ea77 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-04 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:49b88e50544f77a3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-05 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:f888d158ddc35e6a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-06 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:a537a36020631b15 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-07 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:e33d301405c175ee | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-08 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:18ca82a1149fbdd1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-09 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:55ec8e2ddf2ba486 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-10 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:94694f47cf74e186 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-11 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:a29db3f46627a1c5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-12 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:4a058c8a2ba6e51c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-13 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:5b224712eb0e83dd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-14 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:bfeb011d5706a408 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alongir | 2025-04-15 | 2025-04-01 | 152/0 | 152A/0 | TSE | Ready | 1779.94 | 2025-04-13 | 2025-04-15 | Completed | 1.7799 | 0.13692 | stringing:498e65289275b0e8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak | 2025-04-12 | 2025-04-01 | 270/0 | 270A/0 | TSE | Ready | 2821 | 2025-04-14 | 2025-04-15 | Completed | 2.821 | 0.70525 | stringing:59bdf7fc40efa65a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak | 2025-04-13 | 2025-04-01 | 270/0 | 270A/0 | TSE | Ready | 2821 | 2025-04-14 | 2025-04-15 | Completed | 2.821 | 0.70525 | stringing:3e8b2c2fb0592b39 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak | 2025-04-14 | 2025-04-01 | 270/0 | 270A/0 | TSE | Ready | 2821 | 2025-04-14 | 2025-04-15 | Completed | 2.821 | 0.70525 | stringing:4b4471ac83f79ccb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak | 2025-04-15 | 2025-04-01 | 270/0 | 270A/0 | TSE | Ready | 2821 | 2025-04-14 | 2025-04-15 | Completed | 2.821 | 0.70525 | stringing:692861c10b71fefb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-18 | 2025-04-01 | 145/0 | 145A/0 | Hotline | Ready | 398 | 2025-04-18 | 2025-04-23 | Completed | 0.398 | 0.066333 | stringing:40654b157e12fef0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-19 | 2025-04-01 | 145/0 | 145A/0 | Hotline | Ready | 398 | 2025-04-18 | 2025-04-23 | Completed | 0.398 | 0.066333 | stringing:25cebae742bafaba | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-20 | 2025-04-01 | 145/0 | 145A/0 | Hotline | Ready | 398 | 2025-04-18 | 2025-04-23 | Completed | 0.398 | 0.066333 | stringing:3ccfd91abb001e8d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-21 | 2025-04-01 | 145/0 | 145A/0 | Hotline | Ready | 398 | 2025-04-18 | 2025-04-23 | Completed | 0.398 | 0.066333 | stringing:c7d5dd64cb478a80 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-22 | 2025-04-01 | 145/0 | 145A/0 | Hotline | Ready | 398 | 2025-04-18 | 2025-04-23 | Completed | 0.398 | 0.066333 | stringing:0ef25c9cd4bd2a9d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-23 | 2025-04-01 | 145/0 | 145A/0 | Hotline | Ready | 398 | 2025-04-18 | 2025-04-23 | Completed | 0.398 | 0.066333 | stringing:30d80de605a96657 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-17 | 2025-04-01 | 268/0 | 269/0 | Hotline | Ready | 292 | 2025-04-21 | 2025-04-23 | Completed | 0.292 | 0.041714 | stringing:e0bf8e0eda4fb9e5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-18 | 2025-04-01 | 268/0 | 269/0 | Hotline | Ready | 292 | 2025-04-21 | 2025-04-23 | Completed | 0.292 | 0.041714 | stringing:98511b36b8748ed2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-19 | 2025-04-01 | 268/0 | 269/0 | Hotline | Ready | 292 | 2025-04-21 | 2025-04-23 | Completed | 0.292 | 0.041714 | stringing:866c0024c8c3a31e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-20 | 2025-04-01 | 268/0 | 269/0 | Hotline | Ready | 292 | 2025-04-21 | 2025-04-23 | Completed | 0.292 | 0.041714 | stringing:72777971a7bf0a6e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-21 | 2025-04-01 | 268/0 | 269/0 | Hotline | Ready | 292 | 2025-04-21 | 2025-04-23 | Completed | 0.292 | 0.041714 | stringing:9830174f428f1768 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-22 | 2025-04-01 | 268/0 | 269/0 | Hotline | Ready | 292 | 2025-04-21 | 2025-04-23 | Completed | 0.292 | 0.041714 | stringing:750be9f47c662716 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-23 | 2025-04-01 | 268/0 | 269/0 | Hotline | Ready | 292 | 2025-04-21 | 2025-04-23 | Completed | 0.292 | 0.041714 | stringing:c7831d15b6650f1d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-05 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:d98787b4911e1358 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-06 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:23b364d4c7ccb0a4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-07 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:8e9e62cf97c53f5c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-08 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:4040447b3c106a28 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-09 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:ef8c95e0c3edc57c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-10 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:be2a0e52fe8b0e53 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-11 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:b59ce0e7ed75bfb5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-12 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:0489e3b344ee742e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-13 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:1e5446bff74e74ec | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-14 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:67edee64185c750c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-15 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:598e8032bcd8dda6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-16 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:95e23700ce727dfe | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-17 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:30abd68302c312e1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-18 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:ae363be3879b4077 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-19 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:51b6a50897307513 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-20 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:453a51217a39a07a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-21 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:af50efd341b9f49a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-22 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:4513ff6904f1e62e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Maidul rahman | 2025-04-23 | 2025-04-01 | 269/0 | 270/0 | TSE | Ready | 1237 | 2025-04-18 | 2025-04-23 | Completed | 1.237 | 0.065105 | stringing:75d6f7f2fe9ab5ed | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-12 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:7915dff68f0280c0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-13 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:17327276c03c389a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-14 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:1aafb4887c5b9b37 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-15 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:a8f9fb25f507cc3a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-16 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:d5d1b80b4a6fe0a2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-17 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:225597cbec78d6aa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-18 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:064bf2fa5ac7f223 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-19 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:d13d949d6b9d1f9a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-20 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:6a1e5b22bb66cfb2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-21 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:1d500dc594fbc20b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-22 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:6f0dc9eac779d408 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-23 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:1d7d2537226dd2ac | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-24 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:49f4673a01e3f7a9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alamgir | 2025-04-25 | 2025-04-01 | 270A/0 | 271/0 | Manual | Ready | 268 | 2025-04-21 | 2025-04-25 | Completed | 0.268 | 0.019143 | stringing:1bb05def1d351642 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak | 2025-04-18 | 2025-04-01 | 271/0 | 272/0 | TSE | Ready | 2108 | 2025-04-21 | 2025-04-25 | Completed | 2.108 | 0.2635 | stringing:d4603698299cdea4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak | 2025-04-19 | 2025-04-01 | 271/0 | 272/0 | TSE | Ready | 2108 | 2025-04-21 | 2025-04-25 | Completed | 2.108 | 0.2635 | stringing:892ad943cf5cbfa5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak | 2025-04-20 | 2025-04-01 | 271/0 | 272/0 | TSE | Ready | 2108 | 2025-04-21 | 2025-04-25 | Completed | 2.108 | 0.2635 | stringing:a7fe38592dfa90f0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak | 2025-04-21 | 2025-04-01 | 271/0 | 272/0 | TSE | Ready | 2108 | 2025-04-21 | 2025-04-25 | Completed | 2.108 | 0.2635 | stringing:42e555c9fa467358 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak | 2025-04-22 | 2025-04-01 | 271/0 | 272/0 | TSE | Ready | 2108 | 2025-04-21 | 2025-04-25 | Completed | 2.108 | 0.2635 | stringing:83c4512fda8d9851 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak | 2025-04-23 | 2025-04-01 | 271/0 | 272/0 | TSE | Ready | 2108 | 2025-04-21 | 2025-04-25 | Completed | 2.108 | 0.2635 | stringing:6f3098d917109911 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak | 2025-04-24 | 2025-04-01 | 271/0 | 272/0 | TSE | Ready | 2108 | 2025-04-21 | 2025-04-25 | Completed | 2.108 | 0.2635 | stringing:dbd4403d4db3cf16 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak | 2025-04-25 | 2025-04-01 | 271/0 | 272/0 | TSE | Ready | 2108 | 2025-04-21 | 2025-04-25 | Completed | 2.108 | 0.2635 | stringing:9750aad31d813596 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-04-18 | 2025-04-01 | 148/0 | 149/0 | TSE | Ready | 2993.72 | 2025-04-24 | 2025-04-26 | Completed | 2.9937 | 0.33264 | stringing:80ad4609043f4601 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-04-19 | 2025-04-01 | 148/0 | 149/0 | TSE | Ready | 2993.72 | 2025-04-24 | 2025-04-26 | Completed | 2.9937 | 0.33264 | stringing:c8fc3e76aeffc760 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-04-20 | 2025-04-01 | 148/0 | 149/0 | TSE | Ready | 2993.72 | 2025-04-24 | 2025-04-26 | Completed | 2.9937 | 0.33264 | stringing:efb64d0e18993ed9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-04-21 | 2025-04-01 | 148/0 | 149/0 | TSE | Ready | 2993.72 | 2025-04-24 | 2025-04-26 | Completed | 2.9937 | 0.33264 | stringing:c9bd46b45c9dc8cc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-04-22 | 2025-04-01 | 148/0 | 149/0 | TSE | Ready | 2993.72 | 2025-04-24 | 2025-04-26 | Completed | 2.9937 | 0.33264 | stringing:26f475b23d71b179 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-04-23 | 2025-04-01 | 148/0 | 149/0 | TSE | Ready | 2993.72 | 2025-04-24 | 2025-04-26 | Completed | 2.9937 | 0.33264 | stringing:c502e3447216dd99 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-04-24 | 2025-04-01 | 148/0 | 149/0 | TSE | Ready | 2993.72 | 2025-04-24 | 2025-04-26 | Completed | 2.9937 | 0.33264 | stringing:edc22f1f666739ef | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-04-25 | 2025-04-01 | 148/0 | 149/0 | TSE | Ready | 2993.72 | 2025-04-24 | 2025-04-26 | Completed | 2.9937 | 0.33264 | stringing:318a30153312ef8d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Muslehuddin | 2025-04-26 | 2025-04-01 | 148/0 | 149/0 | TSE | Ready | 2993.72 | 2025-04-24 | 2025-04-26 | Completed | 2.9937 | 0.33264 | stringing:23c047ee310a9320 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-22 | 2025-04-01 | 149/0 | 150/0 | TSE | Ready | 808.76 | 2025-04-24 | 2025-04-26 | Completed | 0.80876 | 0.16175 | stringing:1cb0f6798e5183e1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-23 | 2025-04-01 | 149/0 | 150/0 | TSE | Ready | 808.76 | 2025-04-24 | 2025-04-26 | Completed | 0.80876 | 0.16175 | stringing:69172c73b47957d9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-24 | 2025-04-01 | 149/0 | 150/0 | TSE | Ready | 808.76 | 2025-04-24 | 2025-04-26 | Completed | 0.80876 | 0.16175 | stringing:734d0f774d9aff77 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-25 | 2025-04-01 | 149/0 | 150/0 | TSE | Ready | 808.76 | 2025-04-24 | 2025-04-26 | Completed | 0.80876 | 0.16175 | stringing:0e7dfd9822393ebe | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-26 | 2025-04-01 | 149/0 | 150/0 | TSE | Ready | 808.76 | 2025-04-24 | 2025-04-26 | Completed | 0.80876 | 0.16175 | stringing:2a08f10770d85f28 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-07 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:4cabcc8912937b4e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-08 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:cb9d8b664dde3b9c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-09 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:fba4073417e72f84 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-10 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:2f5aa28105f93505 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-11 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:67fc4d9d0c329314 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-12 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:3922c54b14c2f9b3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-13 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:98f9b077057a2aa1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-14 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:12b0b34b0e3bb3f6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-15 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:9ab852a01faf0440 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-16 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:cbd669f862de3c6f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-17 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:7651abb10ce92bad | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-18 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:e40b45805f43def8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-19 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:4042f0b34f53c1f4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-20 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:b826a7c54ba97d9f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-21 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:47f1549f46902444 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-22 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:5735f836a848ce5f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-23 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:9eced7cea7009248 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-24 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:038d866ebee43288 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-25 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:c933c63d61030df5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Manik Sarkar | 2025-04-26 | 2025-04-01 | 162/0 | 163/0 | Manual | Ready | 401.68 | 2025-04-23 | 2025-04-26 | Completed | 0.40168 | 0.020084 | stringing:cdc33913ff2cf791 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-04-30 | 2025-04-01 | 147A/0 | 147B/0 | Manual | Ready | 263 | 2025-04-30 | 2025-04-30 | Completed | 0.263 | 0.263 | stringing:ed8c27523ac86ee0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-03-21 | 2025-03-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:e1d50270988b9421 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-03-22 | 2025-03-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:8cf80440764f031a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-03-23 | 2025-03-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:0981c62b8c1df91c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-03-24 | 2025-03-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:472736272a2a7d93 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-03-25 | 2025-03-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:39d6d7f64bc0dcb0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-03-26 | 2025-03-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:08d3d03332c7ab75 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-03-27 | 2025-03-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:57ea2d92a5b36673 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-03-28 | 2025-03-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:debccbea2ca05d1a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-03-29 | 2025-03-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:e6a6857a32212544 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-03-30 | 2025-03-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:e1387d2d9c935c56 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-03-31 | 2025-03-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:8bb69b54e13fe567 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-01 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:0f608216aa5d110f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-02 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:f40761e033257c52 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-03 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:84b39d12854d7178 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-04 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:bf043fe4552ba32b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-05 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:8338f2cda6f4435c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-06 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:2bf27e866446b3ed | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-07 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:f29fb4678f1db4af | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-08 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:fa352abee1ff3020 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-09 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:7cc3d5be7144c792 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-10 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:abea812c4e6168bd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-11 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:4c0a24535ecff798 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-12 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:d71c90365944b812 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-13 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:1d0824d9d081f7ab | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-14 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:1b87ebbb51be20e0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-15 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:4d6ac2138bcc6c70 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-16 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:505f0aa447a4c4df | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-17 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:15f6dfad0e3c6f9f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-18 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:17424914c0ab9e1e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-19 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:5ec7e63a09f6141f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-20 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:2665ce94f030e077 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-21 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:4207aaac20fd9322 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-22 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:99efb205fb350d19 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-23 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:07184f5c1cb45010 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-24 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:60ca10e0e1ffc27e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-25 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:2e8df4e16cebe6a6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-26 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:db1aad7ebe840502 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-27 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:789e100f16eec1ed | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-28 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:83f38709b637a444 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-29 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:56cfaae1806333ee | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-04-30 | 2025-04-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:f4ad1966c95c1b68 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | RafikulAlam Construction | 2025-05-01 | 2025-05-01 | 135/0 | 135A/0 | TSE | Ready | 2997.64 | 2025-04-28 | 2025-05-01 | Completed | 2.9976 | 0.071372 | stringing:238ab1d52a9f2848 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-29 | 2025-04-01 | 251/0 | 252/0 | Hotline | Ready | 222 | 2025-05-02 | 2025-05-04 | Completed | 0.222 | 0.037 | stringing:6ff166ef10786400 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-04-30 | 2025-04-01 | 251/0 | 252/0 | Hotline | Ready | 222 | 2025-05-02 | 2025-05-04 | Completed | 0.222 | 0.037 | stringing:ac3871749c31c514 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-05-01 | 2025-05-01 | 251/0 | 252/0 | Hotline | Ready | 222 | 2025-05-02 | 2025-05-04 | Completed | 0.222 | 0.037 | stringing:90cb548bc8620851 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-05-02 | 2025-05-01 | 251/0 | 252/0 | Hotline | Ready | 222 | 2025-05-02 | 2025-05-04 | Completed | 0.222 | 0.037 | stringing:1ab6219660ab6398 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-05-03 | 2025-05-01 | 251/0 | 252/0 | Hotline | Ready | 222 | 2025-05-02 | 2025-05-04 | Completed | 0.222 | 0.037 | stringing:468422376bc1f8df | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra Electrical | 2025-05-04 | 2025-05-01 | 251/0 | 252/0 | Hotline | Ready | 222 | 2025-05-02 | 2025-05-04 | Completed | 0.222 | 0.037 | stringing:d90208d5ee098b85 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-28 | 2025-04-01 | 161/0 | 162/0 | Hotline | Ready | 279.05 | 2025-04-28 | 2025-05-06 | Completed | 0.27905 | 0.031006 | stringing:b18539da10f586bd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-29 | 2025-04-01 | 161/0 | 162/0 | Hotline | Ready | 279.05 | 2025-04-28 | 2025-05-06 | Completed | 0.27905 | 0.031006 | stringing:daf3b82b27ff5334 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-04-30 | 2025-04-01 | 161/0 | 162/0 | Hotline | Ready | 279.05 | 2025-04-28 | 2025-05-06 | Completed | 0.27905 | 0.031006 | stringing:2070bfa77ed8d49a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-01 | 2025-05-01 | 161/0 | 162/0 | Hotline | Ready | 279.05 | 2025-04-28 | 2025-05-06 | Completed | 0.27905 | 0.031006 | stringing:75a31c040a4782b9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-02 | 2025-05-01 | 161/0 | 162/0 | Hotline | Ready | 279.05 | 2025-04-28 | 2025-05-06 | Completed | 0.27905 | 0.031006 | stringing:73a93e67d1b7a0b8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-03 | 2025-05-01 | 161/0 | 162/0 | Hotline | Ready | 279.05 | 2025-04-28 | 2025-05-06 | Completed | 0.27905 | 0.031006 | stringing:5d7bcb346e1dcd42 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-04 | 2025-05-01 | 161/0 | 162/0 | Hotline | Ready | 279.05 | 2025-04-28 | 2025-05-06 | Completed | 0.27905 | 0.031006 | stringing:a609e5e15ac566d4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-05 | 2025-05-01 | 161/0 | 162/0 | Hotline | Ready | 279.05 | 2025-04-28 | 2025-05-06 | Completed | 0.27905 | 0.031006 | stringing:b3313bd70ec92052 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-06 | 2025-05-01 | 161/0 | 162/0 | Hotline | Ready | 279.05 | 2025-04-28 | 2025-05-06 | Completed | 0.27905 | 0.031006 | stringing:bd959032f857c5fc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-17 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:0134cc2f7a7a5033 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-18 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:420cb0b5aaff7d4f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-19 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:1db5844cfaddce40 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-20 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:46cccfe50024c427 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-21 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:0fee6bda24d034b6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-22 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:980c0514fd3ec4f3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-23 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:75b9c40b0d5c4b2c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-24 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:02a0e29946d93f97 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-25 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:4eda424ce161fe1c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-26 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:a0cacf9b4e400510 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-27 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:49dd1e55249c09ee | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-28 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:282c3393258fd37e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-29 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:706e5eb7e396a554 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-04-30 | 2025-04-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:ef8ec34fd011048e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-01 | 2025-05-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:6754b7c0f10d8522 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-02 | 2025-05-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:c5310cb0c28f079d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-03 | 2025-05-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:e8499183104e0a0b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-04 | 2025-05-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:9ab0f95bb9abeb5a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-05 | 2025-05-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:e9e5f538875e9d92 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-06 | 2025-05-01 | 252/0 | 253/0 | Manual | Ready | 317 | 2025-05-04 | 2025-05-06 | Completed | 0.317 | 0.01585 | stringing:06047eb557beb9dd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-04 | 2025-05-01 | 250/0 | 251/0 | Manual | Ready | 737 | 2025-05-08 | 2025-05-10 | Completed | 0.737 | 0.10529 | stringing:adcd692fd8c4a2ce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-05 | 2025-05-01 | 250/0 | 251/0 | Manual | Ready | 737 | 2025-05-08 | 2025-05-10 | Completed | 0.737 | 0.10529 | stringing:4f8e565811eef944 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-06 | 2025-05-01 | 250/0 | 251/0 | Manual | Ready | 737 | 2025-05-08 | 2025-05-10 | Completed | 0.737 | 0.10529 | stringing:43ab9245fb9b8c00 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-07 | 2025-05-01 | 250/0 | 251/0 | Manual | Ready | 737 | 2025-05-08 | 2025-05-10 | Completed | 0.737 | 0.10529 | stringing:af8c09a645114612 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-08 | 2025-05-01 | 250/0 | 251/0 | Manual | Ready | 737 | 2025-05-08 | 2025-05-10 | Completed | 0.737 | 0.10529 | stringing:1074e1bd32c25f51 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-09 | 2025-05-01 | 250/0 | 251/0 | Manual | Ready | 737 | 2025-05-08 | 2025-05-10 | Completed | 0.737 | 0.10529 | stringing:180fe17fa61ed332 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-05-10 | 2025-05-01 | 250/0 | 251/0 | Manual | Ready | 737 | 2025-05-08 | 2025-05-10 | Completed | 0.737 | 0.10529 | stringing:5001952c90ca5856 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-04-29 | 2025-04-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:ff1d75af8acc6340 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-04-30 | 2025-04-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:f366b0c62de13c9c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-05-01 | 2025-05-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:f8e4c000280d8a11 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-05-02 | 2025-05-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:f618c92d49eebbf7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-05-03 | 2025-05-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:a0a512e116e7a99c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-05-04 | 2025-05-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:0110eda9bca6d5ce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-05-05 | 2025-05-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:3a59b5799019d834 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-05-06 | 2025-05-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:674e824653d24d97 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-05-07 | 2025-05-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:b4ab3a8490d03acb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-05-08 | 2025-05-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:7d2cd6aa1072053a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-05-09 | 2025-05-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:24c40baf124e45bd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-05-10 | 2025-05-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:aed61634f5675765 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-05-11 | 2025-05-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:f71f950d7c5eff07 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin | 2025-05-12 | 2025-05-01 | 249/0 | 250/0 | TSE | Ready | 1368 | 2025-05-09 | 2025-05-12 | Completed | 1.368 | 0.097714 | stringing:4b75b9d706bacf64 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-26 | 2025-04-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:dcc39ee959b0a519 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-27 | 2025-04-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:27d727b290dd5972 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-28 | 2025-04-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:d237b199d318aca0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-29 | 2025-04-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:ddabda6a8f133a32 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-04-30 | 2025-04-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:78a1b9974b7e4979 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-01 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:594b9a544ca69b3c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-02 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:52fcb53069d4add2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-03 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:5cc989814294458e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-04 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:ff3c69c851e217a5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-05 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:1073f3968d8d6816 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-06 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:e1813e74189520d2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-07 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:8ceff4a40269f43e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-08 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:d5da6b3c19d3cbbd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-09 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:8de592c38bf1aba2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-10 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:d350b4faf7a3e7ef | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-11 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:ef6047c84c1b75aa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-12 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:2a5b6894f3ebecd0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-13 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:9649d5ed151e3211 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-14 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:1c0e9b7ce4208d7d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-15 | 2025-05-01 | 150A/0 | 151/0 | TSE | Ready | 1252.42 | 2025-05-12 | 2025-05-15 | Completed | 1.2524 | 0.062621 | stringing:2987e9d21b87617d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-11 | 2025-05-01 | 151/0 | 152/0 | Manual | Ready | 403.35 | 2025-05-11 | 2025-05-15 | Completed | 0.40335 | 0.08067 | stringing:42bc3e7401dc0e91 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-12 | 2025-05-01 | 151/0 | 152/0 | Manual | Ready | 403.35 | 2025-05-11 | 2025-05-15 | Completed | 0.40335 | 0.08067 | stringing:c6b721b0d5392e48 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-13 | 2025-05-01 | 151/0 | 152/0 | Manual | Ready | 403.35 | 2025-05-11 | 2025-05-15 | Completed | 0.40335 | 0.08067 | stringing:7bbe5f7164babee9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-14 | 2025-05-01 | 151/0 | 152/0 | Manual | Ready | 403.35 | 2025-05-11 | 2025-05-15 | Completed | 0.40335 | 0.08067 | stringing:a57978b24762abd3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-15 | 2025-05-01 | 151/0 | 152/0 | Manual | Ready | 403.35 | 2025-05-11 | 2025-05-15 | Completed | 0.40335 | 0.08067 | stringing:7e43d3817fe00fca | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam + Alam Const. + Enamul | 2025-05-16 | 2025-05-01 | 147/2 | 147A/0 | TSE | Ready | 2020.89 | 2025-05-16 | 2025-05-18 | Completed | 2.0209 | 0.67363 | stringing:ae673cb84083bbcb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam + Alam Const. + Enamul | 2025-05-17 | 2025-05-01 | 147/2 | 147A/0 | TSE | Ready | 2020.89 | 2025-05-16 | 2025-05-18 | Completed | 2.0209 | 0.67363 | stringing:7d7d958717c5637c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam + Alam Const. + Enamul | 2025-05-18 | 2025-05-01 | 147/2 | 147A/0 | TSE | Ready | 2020.89 | 2025-05-16 | 2025-05-18 | Completed | 2.0209 | 0.67363 | stringing:e78be23de240d00e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam + Alam Const. + Enamul + Manik sarkar | 2025-05-22 | 2025-05-01 | 140/0 | 141/0 | Manual | Ready | 249 | 2025-05-23 | 2025-05-23 | Completed | 0.249 | 0.1245 | stringing:8c0360e5c4b7fdef | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Rafikul Alam + Alam Const. + Enamul + Manik sarkar | 2025-05-23 | 2025-05-01 | 140/0 | 141/0 | Manual | Ready | 249 | 2025-05-23 | 2025-05-23 | Completed | 0.249 | 0.1245 | stringing:aad3747ad47f37ad | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-23 | 2025-05-01 | 150/0 | 150/1 | Hotline | Ready | 367 | 2025-05-23 | 2025-05-26 | Completed | 0.367 | 0.09175 | stringing:4161098371c3b4a9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-24 | 2025-05-01 | 150/0 | 150/1 | Hotline | Ready | 367 | 2025-05-23 | 2025-05-26 | Completed | 0.367 | 0.09175 | stringing:6ea093bae33541f3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-25 | 2025-05-01 | 150/0 | 150/1 | Hotline | Ready | 367 | 2025-05-23 | 2025-05-26 | Completed | 0.367 | 0.09175 | stringing:b508dd2ab2e74ed3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dhervendra Electricals | 2025-05-26 | 2025-05-01 | 150/0 | 150/1 | Hotline | Ready | 367 | 2025-05-23 | 2025-05-26 | Completed | 0.367 | 0.09175 | stringing:709965e75f6c8fa9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-06 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:052b2d0f1d2c0172 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-07 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:9501849a9447ded3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-08 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:f8d3b9f9bb5c5faa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-09 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:beac6232d2d69376 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-10 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:4afc887381a1511e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-11 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:4218816721f08143 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-12 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:7f559db1a7e58f75 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-13 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:d3e9a5a2ddef3712 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-14 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:a6dac23a1e6ecdd7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-15 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:3510e5ea8db5ac80 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-16 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:b107307599960279 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-17 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:5cdb0614d7e101a7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-18 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:9afc7cf91c3f77e8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-19 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:4959cd75604dcb8c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-20 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:53f1716974175997 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-21 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:cb059ab5a178e82f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-22 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:79ce31095aa8b103 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-23 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:839eaba487187e7a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-24 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:da96e1b4d860c744 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-25 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:b526d6c0f9826965 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-05-26 | 2025-05-01 | 150/1 | 150A/0 | TSE | Ready | 1266.03 | 2025-05-23 | 2025-05-26 | Completed | 1.266 | 0.060287 | stringing:e3de160c40f03bbf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-03 | 2025-06-01 | 156/0 | 157/0 | Manual | Ready | 240.53 | 2025-06-03 | 2025-06-04 | Completed | 0.24053 | 0.12026 | stringing:0419baba9550b316 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-04 | 2025-06-01 | 156/0 | 157/0 | Manual | Ready | 240.53 | 2025-06-03 | 2025-06-04 | Completed | 0.24053 | 0.12026 | stringing:8f7eb7c46ebf5608 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-12 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:d1be18d9d8bd2743 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-13 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:075c46008292705d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-14 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:885397e884cd14e1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-15 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:d974221d31dc9ec5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-16 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:da21c2810de8f8be | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-17 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:3f509b55bc755474 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-18 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:f46eeba441ab4e0d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-19 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:670b8f85f0493c4c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-20 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:655ffb2ad5b772bf | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-21 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:4ef706a77f4db209 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-22 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:ac8309f3dfc2c784 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-23 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:b082afc1bced5fc4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-24 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:c99904b8f351d08f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-25 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:3961632e92611ac7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-26 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:c29cba7fde0b24df | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-27 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:28166f11b36bbdfc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-28 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:38e105702c9946ee | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-29 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:8330ea76fcbd9128 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-30 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:eda010a4366a0f69 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-03-31 | 2025-03-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:fc7d05aa0c8bc38b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-01 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:ef24ac232a26fd85 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-02 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:0a9e3b23ac05ad8f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-03 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:d3b0c5678f0747c6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-04 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:0ca886e31c30527c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-05 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:aa371453f086163c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-06 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:1ae39b2d268873ad | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-07 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:3ba64b2143c70197 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-08 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:eb30925cfe3d7252 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-09 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:9f4ad877941a39c3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-10 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:6cb1f91c94b1339e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-11 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:c9d6e5fc421a3d5e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-12 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:ced8b16686d19e06 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-13 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:a80c46ad4825eb2c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-14 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:841a341c80f3ec8f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-15 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:cf60466ad697991d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-16 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:eb41ce42873c18e4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-17 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:aaaf3035ebeca47f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-18 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:eb27cb2dcebda68b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-19 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:f8113f37268fa904 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-20 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:b967fb769ffe8bca | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-21 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:b298042cbf1536ea | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-22 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:1da19601b0e9b739 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-23 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:719c83a9234d9bf8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-24 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:e8d6ac3b5ceb6a96 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-25 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:48dc3c1ff55c9b94 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-26 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:fb901143ff8610b6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-27 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:fa99fc7d5bd475fd | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-28 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:cd94b094c8f5b997 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-29 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:1101d4cc1462675f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-04-30 | 2025-04-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:2a04f8660cdaae41 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-01 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:037b38941df88056 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-02 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:84219da0057f26f1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-03 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:05f3d521fcd6c3a8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-04 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:274e7c8b477e0d2e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-05 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:945e867223336780 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-06 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:b23df5308a197b09 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-07 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:e7d3c51781026b99 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-08 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:e4f9235fd4a277b4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-09 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:819e9ab8e5e43435 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-10 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:bf76c7ba6075cc34 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-11 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:2edbb87809e82cb6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-12 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:f9853201a7fb6604 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-13 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:fdf38e98e413ed42 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-14 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:56f6f0addbd7c84c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-15 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:ec855505aaca569e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-16 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:6924ce7f3ec0c2d6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-17 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:643da5bf563823d1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-18 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:0c83b4e1ca0976ef | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-19 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:e1f49a155f643aaa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-20 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:4a0d77d2d7fe411a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-21 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:57408884086755b6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-22 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:e6dbb5fbfb5973b7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-23 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:72515c905d041f68 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-24 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:d50c6f559c3445cb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-25 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:f7b44808d7991f3c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-26 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:96ef97109087023c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-27 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:1c3904b958625064 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-28 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:8b00df523fdb02a4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-29 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:32d514a034f57a35 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-30 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:55f36345f86c6193 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-05-31 | 2025-05-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:8f8b035921d5c029 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-01 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:87fa5a15b7a3ef0e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-02 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:c4d2cb9c799618f7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-03 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:b12762cbf8b90a6c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-04 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:f43e6277f0ab4d2b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-05 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:b38871fbbe07cfd1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-06 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:71b827c889dc6ee1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-07 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:884ce39c1f67c37f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-08 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:272ebcb32ca9f7a5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-09 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:e3514b450fb20b0c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-10 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:3d64877077a68db1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-11 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:0b06f5743b7e8a24 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-12 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:250c599f208f3589 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-13 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:d4962219a790ce17 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-14 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:20dd5795fd68fc3e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Kamruddin & Deepak Sarkar | 2025-06-15 | 2025-06-01 | 272/0 | 272/5 | TSE | Ready | 2053 | 2025-06-13 | 2025-06-15 | Completed | 2.053 | 0.021385 | stringing:3c61dfa555925ad2 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-06 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:a810ecc303bee65f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-07 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:5500b96cfe4bba09 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-08 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:bc7129014b83b97c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-09 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:12d9243a1d0df2b4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-10 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:b5a735e2e956dfc4 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-11 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:180b849074d8a393 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-12 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:eb561939ec20c63c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-13 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:cf8747386863dcea | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-14 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:ba2fa823dcaacd16 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-15 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:73338a21ca8e20ad | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-16 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:74e44c93c61a7d5b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-17 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:f570669dc8974695 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-18 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:de1c9421b88952c6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-19 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:ea582b9eda89bbcc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar + Manik Sarkar | 2025-06-20 | 2025-06-01 | 155/0 | 156/0 | TSE | Ready | 2733.13 | 2025-06-14 | 2025-06-20 | Completed | 2.7331 | 0.18221 | stringing:85581e2bde390cf1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-09-02 | 2025-09-01 | 152A/0 | 153/0 | Manual | Ready | 370.34 | 2025-09-06 | 2025-09-10 | Completed | 0.37034 | 0.041149 | stringing:a4b0b52ba615776d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-09-03 | 2025-09-01 | 152A/0 | 153/0 | Manual | Ready | 370.34 | 2025-09-06 | 2025-09-10 | Completed | 0.37034 | 0.041149 | stringing:5b4936bd019fa0af | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-09-04 | 2025-09-01 | 152A/0 | 153/0 | Manual | Ready | 370.34 | 2025-09-06 | 2025-09-10 | Completed | 0.37034 | 0.041149 | stringing:5fb08869a1201fd1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-09-05 | 2025-09-01 | 152A/0 | 153/0 | Manual | Ready | 370.34 | 2025-09-06 | 2025-09-10 | Completed | 0.37034 | 0.041149 | stringing:5d0dd160f20c6fe0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-09-06 | 2025-09-01 | 152A/0 | 153/0 | Manual | Ready | 370.34 | 2025-09-06 | 2025-09-10 | Completed | 0.37034 | 0.041149 | stringing:f2a5f571831ed97f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-09-07 | 2025-09-01 | 152A/0 | 153/0 | Manual | Ready | 370.34 | 2025-09-06 | 2025-09-10 | Completed | 0.37034 | 0.041149 | stringing:9fe73495045ca440 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-09-08 | 2025-09-01 | 152A/0 | 153/0 | Manual | Ready | 370.34 | 2025-09-06 | 2025-09-10 | Completed | 0.37034 | 0.041149 | stringing:283fb4655792614b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-09-09 | 2025-09-01 | 152A/0 | 153/0 | Manual | Ready | 370.34 | 2025-09-06 | 2025-09-10 | Completed | 0.37034 | 0.041149 | stringing:a5a70b6fdb53c340 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Alam Construction | 2025-09-10 | 2025-09-01 | 152A/0 | 153/0 | Manual | Ready | 370.34 | 2025-09-06 | 2025-09-10 | Completed | 0.37034 | 0.041149 | stringing:d7e27dfa34ed8588 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-16 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:9040bae7d33abd8f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-17 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:a5117039d76db753 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-18 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:6a9c1330c0a15c97 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-19 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:0748c7d4bdad3c2d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-20 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:5b9eb476d98e3291 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-21 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:bcd7e05188c42a55 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-22 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:624678c6dbf2c4b8 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-23 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:9ebdaa9952c58995 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-24 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:244a7d8a7bb46eb1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-25 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:0e672e7f9d7bedf9 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-26 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:c6dd806055779e7d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-27 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:9166cf3740283671 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-28 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:3b5f90ffdb6ad442 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-29 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:8d41a488167e571b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-09-30 | 2025-09-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:3dc33c9d62990a8e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-01 | 2025-10-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:efa9cecfd3ab4ee1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-02 | 2025-10-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:29b1946a34667de6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-03 | 2025-10-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:53a2526e29b9037b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-04 | 2025-10-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:a120008b95363d23 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-05 | 2025-10-01 | 158B/0 | 159/0 | TSE | Ready | 1253.83 | 2025-10-02 | 2025-10-05 | Completed | 1.2538 | 0.062691 | stringing:6abcba132d259b1c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-07 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:d5f185994f022bc6 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-08 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:63cddc97ead894b5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-09 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:f2fd58e797ce97b5 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-10 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:da8049ab00aa76f1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-11 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:50332cc705dc7935 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-12 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:be3d546598825e55 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-13 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:23ccc35881396e00 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-14 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:091c0f0751d2e1aa | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-15 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:2147a4a9089a4bc3 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-16 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:321e7b759e97177c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-17 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:e5d47747eaa8c993 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-18 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:f8e73cb7186e7392 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-19 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:ff7d908f4df29c15 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-20 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:3e1f9496cc894823 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Dharmendra 1 | 2025-10-21 | 2025-10-01 | 158A/0 | 158B/0 | Hotline | Ready | 481.57 | 2025-10-07 | 2025-10-21 | Completed | 0.48157 | 0.032105 | stringing:8b3f697c8d5ac909 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Bhola | 2025-10-18 | 2025-10-01 | 276/0 | Gty | Manual | Ready | 160 | 2025-10-18 | 2025-10-21 | Completed | 0.16 | 0.04 | stringing:228d4c0a5703f19f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Bhola | 2025-10-19 | 2025-10-01 | 276/0 | Gty | Manual | Ready | 160 | 2025-10-18 | 2025-10-21 | Completed | 0.16 | 0.04 | stringing:b5fb2cad9c33b53a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Bhola | 2025-10-20 | 2025-10-01 | 276/0 | Gty | Manual | Ready | 160 | 2025-10-18 | 2025-10-21 | Completed | 0.16 | 0.04 | stringing:74fe7b863ca7e02e | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Bhola | 2025-10-21 | 2025-10-01 | 276/0 | Gty | Manual | Ready | 160 | 2025-10-18 | 2025-10-21 | Completed | 0.16 | 0.04 | stringing:f69806e820774b16 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-09 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:a8659e589a035ada | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-10 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:20fdea323ae19a82 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-11 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:849df88d8bfc7fa7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-12 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:061e377304792564 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-13 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:3c9a1f3179ec916f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-14 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:6296107c8bee54d0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-15 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:95a790529baa35fc | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-16 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:3d3369a1658ace11 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-17 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:77df095307020cce | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-18 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:3652710136ab744c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-19 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:738f242957fa6d49 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-20 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:4c0ed0ea680861bb | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-21 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:1db84d20227cb0a1 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-22 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:8946a880f08ed476 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Deepak Sarkar | 2025-10-23 | 2025-10-01 | 158/0 | 158A/0 | TSE | Ready | 1130.57 | 2025-10-17 | 2025-10-23 | Completed | 1.1306 | 0.075371 | stringing:308a4de7f6d9bde0 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Teklal Saw | 2025-10-15 | 2025-10-01 | 192/0 | 193/0 | Manual | Ready | 376 | 2025-10-19 | 2025-10-23 | Completed | 0.376 | 0.041778 | stringing:2b806536bc88680f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Teklal Saw | 2025-10-16 | 2025-10-01 | 192/0 | 193/0 | Manual | Ready | 376 | 2025-10-19 | 2025-10-23 | Completed | 0.376 | 0.041778 | stringing:ae1cc726c7fa645b | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Teklal Saw | 2025-10-17 | 2025-10-01 | 192/0 | 193/0 | Manual | Ready | 376 | 2025-10-19 | 2025-10-23 | Completed | 0.376 | 0.041778 | stringing:f535e8890852ae7d | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Teklal Saw | 2025-10-18 | 2025-10-01 | 192/0 | 193/0 | Manual | Ready | 376 | 2025-10-19 | 2025-10-23 | Completed | 0.376 | 0.041778 | stringing:35e3dc129a4c8e23 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Teklal Saw | 2025-10-19 | 2025-10-01 | 192/0 | 193/0 | Manual | Ready | 376 | 2025-10-19 | 2025-10-23 | Completed | 0.376 | 0.041778 | stringing:9a49030cf8b37f82 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Teklal Saw | 2025-10-20 | 2025-10-01 | 192/0 | 193/0 | Manual | Ready | 376 | 2025-10-19 | 2025-10-23 | Completed | 0.376 | 0.041778 | stringing:bb2373db1e41c23a | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Teklal Saw | 2025-10-21 | 2025-10-01 | 192/0 | 193/0 | Manual | Ready | 376 | 2025-10-19 | 2025-10-23 | Completed | 0.376 | 0.041778 | stringing:6988cddd565d4836 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Teklal Saw | 2025-10-22 | 2025-10-01 | 192/0 | 193/0 | Manual | Ready | 376 | 2025-10-19 | 2025-10-23 | Completed | 0.376 | 0.041778 | stringing:0fe8a67b4aec5df7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Teklal Saw | 2025-10-23 | 2025-10-01 | 192/0 | 193/0 | Manual | Ready | 376 | 2025-10-19 | 2025-10-23 | Completed | 0.376 | 0.041778 | stringing:0ff875bcefd9b6c7 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Upendra Giri 1 | 2025-10-21 | 2025-10-01 | 193/0 | 194/0 | Hotline | Ready | 241 | 2025-10-21 | 2025-10-25 | Completed | 0.241 | 0.0482 | stringing:b2a6a9017af0a17f | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Upendra Giri 1 | 2025-10-22 | 2025-10-01 | 193/0 | 194/0 | Hotline | Ready | 241 | 2025-10-21 | 2025-10-25 | Completed | 0.241 | 0.0482 | stringing:ecae5266a350a529 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Upendra Giri 1 | 2025-10-23 | 2025-10-01 | 193/0 | 194/0 | Hotline | Ready | 241 | 2025-10-21 | 2025-10-25 | Completed | 0.241 | 0.0482 | stringing:2402661f979e7f25 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Upendra Giri 1 | 2025-10-24 | 2025-10-01 | 193/0 | 194/0 | Hotline | Ready | 241 | 2025-10-21 | 2025-10-25 | Completed | 0.241 | 0.0482 | stringing:7eae567a9019c06c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Upendra Giri 1 | 2025-10-25 | 2025-10-01 | 193/0 | 194/0 | Hotline | Ready | 241 | 2025-10-21 | 2025-10-25 | Completed | 0.241 | 0.0482 | stringing:5e7b26292103c149 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-10-24 | 2025-10-01 | 194/0 | 195/0 | Manual | Ready | 182 | 2025-10-24 | 2025-10-29 | Completed | 0.182 | 0.030333 | stringing:72377bd7e5221555 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-10-25 | 2025-10-01 | 194/0 | 195/0 | Manual | Ready | 182 | 2025-10-24 | 2025-10-29 | Completed | 0.182 | 0.030333 | stringing:9f6103fd63a09341 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-10-26 | 2025-10-01 | 194/0 | 195/0 | Manual | Ready | 182 | 2025-10-24 | 2025-10-29 | Completed | 0.182 | 0.030333 | stringing:b968264fd5ee7005 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-10-27 | 2025-10-01 | 194/0 | 195/0 | Manual | Ready | 182 | 2025-10-24 | 2025-10-29 | Completed | 0.182 | 0.030333 | stringing:303fc0b8b2c03b08 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-10-28 | 2025-10-01 | 194/0 | 195/0 | Manual | Ready | 182 | 2025-10-24 | 2025-10-29 | Completed | 0.182 | 0.030333 | stringing:a23941b132371c8c | TA 325 | TA 325 - DPR - 2025-10-29.xlsx
TA 325 | Enamul Haque | 2025-10-29 | 2025-10-01 | 194/0 | 195/0 | Manual | Ready | 182 | 2025-10-24 | 2025-10-29 | Completed | 0.182 | 0.030333 | stringing:7fc103cc32ee1768 | TA 325 | TA 325 - DPR - 2025-10-29.xlsx

## Diagnostics
Workbook | Project | Rows | DailyRows | Status
DPR - TB - 408 10-10-2025.xlsx | TB 408 | 0 | 0 | NO_TARGET_SHEET
DPR TA 421 .xlsx | TA 421 | 0 | 0 | NO_TARGET_SHEET
TA 325 - DPR - 2025-10-29.xlsx | TA 325 | 228 | 1797 | OK
TA 413 - DPR - 2025-10-29.xlsx | TA 413 | 0 | 0 | NO_TARGET_SHEET
TA 416 - DPR - 2025-10-28.xlsx | TA 416 | 0 | 0 | NO_TARGET_SHEET
TA 418 - DPR - 2025-10-28.xlsx | TA 418 | 0 | 0 | NO_TARGET_SHEET
TA 419 - DPR - 2025-10-29.xlsx | TA 419 | 0 | 0 | NO_TARGET_SHEET
TA 505 - DPR - 2025-10-28.xlsx | TA 505 | 0 | 0 | NO_TARGET_SHEET