## Detail Survey-220kV (hidden)
220kV - Detailed Survey Progress
Sl. No. | LOC NO | TowerType | Deviation of Angle | CP | Leg Extension |  |  |  | RC | Chimney Extension |  |  |  | Span Length (m) | Section Length | Detail Survey completion status |  |  | Detail Survey Report Submision |  |  | Detail Survey Approval |  |  | Remarks
|  |  | DMS | m | A | B | C | D | m | A | B | C | D | m | m | Surveyed | DOC | Re-survey | Submitted | Date | Re-submitted | Approved | Date | Re-apprpved
| GANTRY | GANTRY | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed
[14 empty] | 126.19 |  | Completed
1 | 0/0 | DD+0 | 16° 50' 9"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 126.19 | Completed
[14 empty] | 292 |  | Completed
2 | 0/1 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed
[14 empty] | 360.47 |  | Completed
3 | 1/0 | DC+0 | 15° 52' 12"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 652.47 | Completed
[14 empty] | 293 |  | Completed
4 | 1/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed
[14 empty] | 390.88 |  | Completed
5 | 1/2 | DA+3 | 19° 5' 19"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 683.88 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 351 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
6 | 1A/0 | DC+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 258 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
7 | 1A/1 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 322.492 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
8 | 1A/2 | DC+0 | 57° 12' 54"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 930.56 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 248 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
9 | 1B/0 | DD+3 | 44° 32' 20"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 249.73 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 294 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
10 | 1C/0 | DD+9 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 294.431 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
11 | 1C/1 | DA+6 | 28° 26' 27"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 588.43 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 306 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
12 | 1D/0 | DC+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 393.921 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
13 | 1D/1 | DA+0 | 42° 49' 3"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 699.92 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 356.664 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
14 | 1E/0 | DD+6 | 27° 13' 43"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 356.66 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 174.205 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
15 | 2/0 | DC+6 | 49° 56' 13"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 174.21 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 229.73 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
16 | 3/0 | DD+3 | 7° 56' 47"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 229.73 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 391 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
17 | 4/0 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 328 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
18 | 4/1 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 333 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
19 | 4/2 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 350 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
20 | 4/3 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 331 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
21 | 4/4 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 1732.41 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 349 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
22 | 4/5 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 349.2 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 360 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
23 | 4/6 | DB+9 | [6 empty] | 1 | 0 | 0 | 0 | 0 |  | 360.27 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 460 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
24 | 4/7 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  | 460.04 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 230 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
25 | 4/8 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  | 229.26 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 371.51 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
26 | 4/9 | DB+6 | [7 empty] | 1 | 1 | 1 | 1 |  | 351.41 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 332.47 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
27 | 4/10 | DB+6 | [7 empty] | 0 | 0 | 0 | 0 |  | 338.77 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 424.431 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
28 | 4/11 | DB+0 | [6 empty] | 3 | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 326.731 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
29 | 4/12 | DA+9 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 291.858 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
30 | 4/13 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 292 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
31 | 4/14 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 1349.09 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 415 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
32 | 4/15 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 414.59 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 253 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
33 | 4/16 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 253.29 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 172.454 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
34 | 4/17 | DB+0 | 11° 50' 16"RT | [6 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 323 |  | Completed |  |  | Submitted |  |  | Approved
35 | 5/0 | DB+6 | [7 empty] | 0 | 0 | 0 | 0 |  | 323 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 371 |  | Completed |  |  | Submitted |  |  | Approved
36 | 5/1 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 350 |  | Completed |  |  | Submitted |  |  | Approved
37 | 5/2 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 291 |  | Completed |  |  | Submitted |  |  | Approved
38 | 5/3 | DA+3 | 24° 44' 29"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 1012 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 322 |  | Completed |  |  | Submitted |  |  | Approved
39 | 5A/0 | DC+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 322 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 284 |  | Completed |  |  | Submitted |  |  | Approved
40 | 5A/1 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 284 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 282.743 |  | Completed |  |  | Submitted |  |  | Approved
41 | 5A/2 | DB+0 | 7° 28' 45"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 282.74 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 462.058 |  | Completed |  |  | Submitted |  |  | Approved
42 | 5B/0 | DB+3 | 15° 37' 24"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 462.06 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 328.624 |  | Completed |  |  | Submitted |  |  | Approved
43 | 6/0 | DC+0 | 23° 4' 48"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 328.62 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 364.056 |  | Completed |  |  | Submitted |  |  | Approved
44 | 7/0 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 278.883 |  | Completed |  |  | Submitted |  |  | Approved
45 | 7/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 252.06 |  | Completed |  |  | Submitted |  |  | Approved
46 | 7/2 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 279.246 |  | Completed |  |  | Submitted |  |  | Approved
47 | 7/3 | DA+0 | 54° 40' 18"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 1174.25 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 134.216 |  | Completed |  |  | Submitted |  |  | Approved
48 | 8/0 | DD+0 | 38° 34' 26"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 134.22 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 336.503 |  | Completed |  |  | Submitted |  |  | Approved
49 | 8A/0 | DD+0 | 23° 30' 1"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 336.5 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 365 |  | Completed |  |  | Submitted |  |  | Approved
50 | 8B/0 | DC+9 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 280 |  | Completed |  |  | Submitted |  |  | Approved
51 | 8B/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 255.14 |  | Completed |  |  | Submitted |  |  | Approved
52 | 8B/2 | DA+0 | 50° 17' 26"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 900.14 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 318.758 |  | Completed |  |  | Submitted |  |  | Approved
53 | 8C/0 | DD+0 | 43° 40' 17"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 318.76 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 307 |  | Completed |  |  | Submitted |  |  | Approved
54 | 8D/0 | DD+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 312 |  | Completed |  |  | Submitted |  |  | Approved
55 | 8D/1 | DD+9 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 440 |  | Completed |  |  | Submitted |  |  | Approved
56 | 8D/2 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  | 1059 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 459 |  | Completed |  |  | Submitted |  |  | Approved
57 | 8D/3 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 459 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 195 |  | Completed |  |  | Submitted |  |  | Approved
58 | 8D/4 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 195 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 295 |  | Completed |  |  | Submitted |  |  | Approved
59 | 8D/5 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 295 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 380.248 |  | Completed |  |  | Submitted |  |  | Approved
60 | 8D/6 | DB+0 | 26° 29' 57"RT | [5 empty] | 1 | 1 | 1 | 1 | 1 |  | 380.25 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 428 |  | Completed |  |  | Submitted |  |  | Approved
61 | 8E/0 | DC+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 428 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 404 |  | Completed |  |  | Submitted |  |  | Approved
62 | 8E/1 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 404 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 360 |  | Completed |  |  | Submitted |  |  | Approved
63 | 8E/2 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 296 |  | Completed |  |  | Submitted |  |  | Approved
64 | 8E/3 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 259 |  | Completed |  |  | Submitted |  |  | Approved
65 | 8E/4 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 915 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 357 |  | Completed |  |  | Submitted |  |  | Approved
66 | 8E/5 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  | 357 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 486 |  | Completed |  |  | Submitted |  |  | Approved
67 | 8E/6 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  | 486 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 434 |  | Completed |  |  | Submitted |  |  | Approved
68 | 8E/7 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 434 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 295 |  | Completed |  |  | Submitted |  |  | Approved
69 | 8E/8 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 326 |  | Completed |  |  | Submitted |  |  | Approved
70 | 8E/9 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 298 |  | Completed |  |  | Submitted |  |  | Approved
71 | 8E/10 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  | 919 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 489 |  | Completed |  |  | Submitted |  |  | Approved
72 | 8E/11 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 489 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 382.474 |  | Completed |  |  | Submitted |  |  | Approved
73 | 8E/12 | DB+3 | 21° 0' 5"LT | [12 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 372.4 |  | Completed |  |  | Submitted |  |  | Approved
74 | AP-9 | DC+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 350.02 |  | Completed |  |  | Submitted |  |  | Approved
75 | 9/1 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 303.57 |  | Completed |  |  | Submitted |  |  | Approved
76 | 9/2 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 224.33 |  | Completed |  |  | Submitted |  |  | Approved
77 | 9/3 | DA+0 | [12 empty] | 1250.32 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 246.76 |  | Completed |  |  | Submitted |  |  | Approved
78 | 9/4 | DB+0 | [12 empty] | 246.76 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 418.18 |  | Completed |  |  | Submitted |  |  | Approved
79 | 9/5 | DB+6 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 298.66 |  | Completed |  |  | Submitted |  |  | Approved
80 | 9/6 | DA+9 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 358.67 |  | Completed |  |  | Submitted |  |  | Approved
81 | 9/7 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 366.13 |  | Completed |  |  | Submitted |  |  | Approved
82 | 9/8 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 255.6 |  | Completed |  |  | Submitted |  |  | Approved
83 | 9/9 | DA+3 | 38° 36' 12"LT | [11 empty] | 1697.24 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 229.72 |  | Completed |  |  | Submitted |  |  | Approved
84 | AP-10 | DD+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 359.36 |  | Completed |  |  | Submitted |  |  | Approved
85 | 10/1 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 365.87 |  | Completed |  |  | Submitted |  |  | Approved
86 | 10/2 | DA+9 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 345.78 |  | Completed |  |  | Submitted |  |  | Approved
87 | 10/3 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 299.34 |  | Completed |  |  | Submitted |  |  | Approved
88 | 10/4 | DA+3 | 25° 10' 25"RT | [11 empty] | 1600.07 | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 295.985 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
89 | AP-11 | DC+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 229.905 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
90 | 11/1 | DA+0 | 40° 29' 60"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 525.89 | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 356.279 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
91 | AP-12 | DD+0 | 24° 1' 33"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 356.28 | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 313.984 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
92 | AP-13 | DC+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 353.605 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
93 | 13/1 | DA+3 | 25° 35' 30"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 667.59 | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 362 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
94 | AP-14 | DC+6 | [7 empty] | 0 | 0 | 0 | 0 |  | 362 | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 387 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
95 | 14/1 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 365 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
96 | 14/2 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  | 752 | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 419 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
97 | 14/3 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 331 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
98 | 14/4 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 390 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
99 | 14/5 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 349 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
100 | 14/6 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 324 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
101 | 14/7 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 413 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
102 | 14/8 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 310.18 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
103 | 14/9 | DA+0 | 37° 6' 34"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 2536.18 | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 378.482 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
104 | AP-15 | DD+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 304.518 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
105 | 15/1 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 332.966 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
106 | 15/2 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 362.716 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
107 | 15/3 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 383.831 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
108 | 15/4 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 361.488 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
109 | 15/5 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 310.703 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
110 | 15/6 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 381.297 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
111 | 15/7 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 316 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
112 | 15/8 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 290.452 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
113 | 15/9 | DA+0 | 29° 42' 12"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 3422.45 | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 306 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
114 | AP-16 | DC+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 336 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
115 | 16/1 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 337 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
116 | 16/2 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 328.65 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
117 | 16/3 | DA+3 | 20° 7' 26"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 1307.65 | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 362 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
118 | AP-17 | DC+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 364 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
119 | 17/1 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 388 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
120 | 17/2 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 321.97 |  | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
121 | 17/3 | DA+6 | 16° 0' 26"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 1435.97 | Completed |  |  | Submitted |  |  | Approved | 2024-08-21
[14 empty] | 365.484 |  | Completed |  |  | Submitted |  |  | Approved
122 | AP-18 | DC+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 373.966 |  | Completed |  |  | Submitted |  |  | Approved
123 | 18/1 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 356.054 |  | Completed |  |  | Submitted |  |  | Approved
124 | 18/2 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 349.663 |  | Completed |  |  | Submitted |  |  | Approved
125 | 18/3 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 353.115 |  | Completed |  |  | Submitted |  |  | Approved
126 | 18/4 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 374.201 |  | Completed |  |  | Submitted |  |  | Approved
127 | 18/5 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 341.321 |  | Completed |  |  | Submitted |  |  | Approved
128 | 18/6 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 347.958 |  | Completed |  |  | Submitted |  |  | Approved
129 | 18/7 | DA+6 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 384.02 |  | Completed |  |  | Submitted |  |  | Approved
130 | 18/8 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 269.694 |  | Completed |  |  | Submitted |  |  | Approved
131 | 18/9 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 394.041 |  | Completed |  |  | Submitted |  |  | Approved
132 | 18/10 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 300.614 |  | Completed |  |  | Submitted |  |  | Approved
133 | 18/11 | DA+3 | 06°13'44"RT | [11 empty] | 4210.131 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 315.423 |  | Completed |  |  | Submitted |  |  | Approved
134 | AP-19 | DB+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 329.642 |  | Completed |  |  | Submitted |  |  | Approved
135 | 19/1 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 382.971 |  | Completed |  |  | Submitted |  |  | Approved
136 | 19/2 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 323.74 |  | Completed |  |  | Submitted |  |  | Approved
137 | 19/3 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 328.78 |  | Completed |  |  | Submitted |  |  | Approved
138 | 19/4 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 266.002 |  | Completed |  |  | Submitted |  |  | Approved
139 | 19/5 | DA+0 | 08°51'36"RT | [11 empty] | 1946.558 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 321.891 |  | Completed |  |  | Submitted |  |  | Approved
140 | AP-20 | DB+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 352.135 |  | Completed |  |  | Submitted |  |  | Approved
141 | 20/1 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 347.315 |  | Completed |  |  | Submitted |  |  | Approved
142 | 20/2 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 339.419 |  | Completed |  |  | Submitted |  |  | Approved
143 | 20/3 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 330.881 |  | Completed |  |  | Submitted |  |  | Approved
144 | 20/4 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 279.994 |  | Completed |  |  | Submitted |  |  | Approved
145 | 20/5 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 369.479 |  | Completed |  |  | Submitted |  |  | Approved
146 | 20/6 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 379.648 |  | Completed |  |  | Submitted |  |  | Approved
147 | 20/7 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 273.995 |  | Completed |  |  | Submitted |  |  | Approved
148 | 20/8 | DA+3 | 14°34'48"LT | [11 empty] | 2994.757 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 345.876 |  | Completed |  |  | Submitted |  |  | Approved
149 | AP-21 | DB+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 310.865 |  | Completed |  |  | Submitted |  |  | Approved
150 | 21/1 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 380.033 |  | Completed |  |  | Submitted |  |  | Approved
151 | 21/2 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 358.179 |  | Completed |  |  | Submitted |  |  | Approved
152 | 21/3 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 311.051 |  | Completed |  |  | Submitted |  |  | Approved
153 | 21/4 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 375.154 |  | Completed |  |  | Submitted |  |  | Approved
154 | 21/5 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 369.132 |  | Completed |  |  | Submitted |  |  | Approved
155 | 21/6 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 370.97 |  | Completed |  |  | Submitted |  |  | Approved
156 | 21/7 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 356.464 |  | Completed |  |  | Submitted |  |  | Approved
157 | 21/8 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 363.334 |  | Completed |  |  | Submitted |  |  | Approved
158 | 21/9 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 370.254 |  | Completed |  |  | Submitted |  |  | Approved
159 | 21/10 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 330.023 |  | Completed |  |  | Submitted |  |  | Approved
160 | 21/11 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 390.077 |  | Completed |  |  | Submitted |  |  | Approved
161 | 21/12 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 343.376 |  | Completed |  |  | Submitted |  |  | Approved
162 | 21/13 | DA+3 | 20° 2' 24"RT | [12 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 326.53 |  | Completed |  |  | Submitted |  |  | Approved
163 | AP-22 | DC+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 302.5 |  | Completed |  |  | Submitted |  |  | Approved
164 | 22/1 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 318.2 |  | Completed |  |  | Submitted |  |  | Approved
165 | 22/2 | DA+3 | 19° 37' 2"LT | [12 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 315.48 |  | Completed |  |  | Submitted |  |  | Approved
166 | AP-23 | DC+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 249.29 |  | Completed |  |  | Submitted |  |  | Approved
167 | 23/1 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 288.05 |  | Completed |  |  | Submitted |  |  | Approved
168 | 23/2 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 369.86 |  | Completed |  |  | Submitted |  |  | Approved
169 | 23/3 | DA+0 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 320.21 |  | Completed |  |  | Submitted |  |  | Approved
170 | 23/4 | DA+3 | [13 empty] | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 383.86 |  | Completed |  |  | Submitted |  |  | Approved
171 | 23/5 | DA+0 | 31° 13' 23"LT | [5 empty] | 3 | 3 | 3 | 3 | 3 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 190.524 |  | Completed |  |  | Submitted |  |  | Approved
172 | AP-24 | DD+9 | 5° 43' 47"RT | [5 empty] | 2 | 2 | 2 | 2 | 2 |  | 190.52 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 173.541 |  | Completed |  |  | Submitted |  |  | Approved
173 | AP-25 | DD+18 | 17° 37' 36"LT | [5 empty] | 2 | 2 | 2 | 2 | 2 |  | 173.54 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 142.384 |  | Completed |  |  | Submitted |  |  | Approved
174 | AP-26 | DD+18 | 24° 41' 6"LT | [5 empty] | 1 | 1 | 1 | 1 | 1 |  | 142.38 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 77.015 |  | Completed |  |  | Submitted |  |  | Approved
175 | AP-27 | DD+18 | 22° 6' 42"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 77.02 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 42.266 |  | Completed |  |  | Submitted |  |  | Approved
176 | AP-28 | DD+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 48 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 54.573 |  | Completed |  |  | Submitted |  |  | Approved
177 | 28/1 | GANTRY UC | [7 empty] | 0 | 0 | 0 | 0 |  | 44 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 41.886 |  | Completed |  |  | Submitted |  |  | Approved
178 | 28/2 | GANTRY UC | 28° 4' 46"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 46.73 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 353.284 |  | Completed |  |  | Submitted |  |  | Approved
179 | AP-29 | DD+3 | 11° 39' 27"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 353.28 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 393 |  | Completed |  |  | Submitted |  |  | Approved
180 | 29A/0 | DC+9 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 359 |  | Completed |  |  | Submitted |  |  | Approved
181 | 29A/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 387 |  | Completed |  |  | Submitted |  |  | Approved
182 | 29A/2 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 346 |  | Completed |  |  | Submitted |  |  | Approved
183 | 29A/3 | DA+9 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 375.545 |  | Completed |  |  | Submitted |  |  | Approved
184 | 29A/4 | DA+3 | 10° 21' 46"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 1860.55 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 353 |  | Completed |  |  | Submitted |  |  | Approved
185 | AP-30 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 321.512 |  | Completed |  |  | Submitted |  |  | Approved
186 | 30/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 312.394 |  | Completed |  |  | Submitted |  |  | Approved
187 | 30/2 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 358.351 |  | Completed |  |  | Submitted |  |  | Approved
188 | 30/3 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 319.206 |  | Completed |  |  | Submitted |  |  | Approved
189 | 30/4 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 342.401 |  | Completed |  |  | Submitted |  |  | Approved
190 | 30/5 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 337.31 |  | Completed |  |  | Submitted |  |  | Approved
191 | 30/6 | DA+3 | 12° 12' 46"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 2332.92 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 371.809 |  | Completed |  |  | Submitted |  |  | Approved
192 | AP-31 | DB+3 |  | 5 | [5 empty] | 5 | 5 | 5 | 5 |  |  | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 371.541 |  | Completed |  |  | Submitted
193 | 31/1 | DA+6 | 20° 20' 13"RT | 5 | [5 empty] | 5 | 5 | 5 | 5 |  | 743.35 | Completed |  |  | Submitted
[14 empty] | 303 |  | Completed |  |  | Submitted
194 | AP-32 | DC+0 |  | 2 | [5 empty] | 2 | 2 | 2 | 2 |  |  | Completed |  |  | Submitted
[14 empty] | 303 |  | Completed |  |  | Submitted
195 | 32/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted
[14 empty] | 303.217 |  | Completed |  |  | Submitted
196 | 32/2 | DA+0 | 37° 48' 15"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 909.22 | Completed |  |  | Submitted
197 | 33/0 | DD+0
198 | 34/0 | DD+0
[14 empty] | 63.8768 |  | 63.8768 |  |  | 62.4143 |  |  | 61.1335

## Check Survey-220kV (hidden)
Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc
220kV - Check Survey Progress
Sl. No. | LOC NO | TowerType | Deviation of Angle | CP | Leg Extension |  |  |  | RC | Chimney Extension |  |  |  | Span Length (m) | Section Length | Detail Survey completion status |  |  | Detail Survey Report Submision |  |  | Detail Survey Approval |  |  | Remarks
|  |  | DMS | m | A | B | C | D | m | A | B | C | D | m | m | Surveyed | DOC | Re-survey | Submitted | Date | Re-submitted | Approved | Date | Re-apprpved
| GANTRY | GANTRY | [7 empty] | 0 | 0 | 0 | 0
47
1 | 0/0 | DD+0 | 16° 50' 9"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 126.19
196
2 | 0/1 | DA+3 | [7 empty] | 0 | 0 | 0 | 0
196.743
3 | 1/0 | DC+0 | 15° 52' 12"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 652.47 | [6 empty] | Approved
[14 empty] | 334 | [7 empty] | Approved
4 | 1/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 319 | [7 empty] | Approved
| 1/2 | DA+3
384.318
5 | 1A/0 | DC+3 | 18° 59' 57"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 683.88 | [6 empty] | Approved
[14 empty] | 329 | [7 empty] | Approved
6 | 1A/1 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 280 | [7 empty] | Approved
7 | 1A/2 | DC+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 232.098 | [7 empty] | Approved
8 | 1B/0 | DD+3 | 57° 18' 17"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 930.56 | [6 empty] | Approved
[14 empty] | 237.783 | [7 empty] | Approved
9 | 1C/0 | DD+9 | 44° 32' 20"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 249.73 | [6 empty] | Approved
[14 empty] | 334 | [7 empty] | Approved
10 | 1C/1 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 341.209 | [7 empty] | Approved
11 | 1D/0 | DC+0 | 28° 26' 27"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 588.43 | [6 empty] | Approved
[14 empty] | 306.001 | [7 empty] | Approved
12 | 1D/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 393.92 | [7 empty] | Approved
13 | 1E/0 | DD+6 | 42° 49' 3"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 699.92 | [6 empty] | Approved
[14 empty] | 356.664 | [7 empty] | Approved
14 | 2/0 | DC+6 | 27° 13' 43"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 356.66 | [6 empty] | Approved
[14 empty] | 174.205 | [7 empty] | Approved
15 | 3/0 | DD+3 | 49° 56' 13"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 174.21 | [6 empty] | Approved
[14 empty] | 229.73 | [7 empty] | Approved
16 | 4/0 | DB+9 | 7° 56' 47"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 229.73 | [6 empty] | Approved
[14 empty] | 391 | [7 empty] | Approved
17 | 4/1 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 328 | [7 empty] | Approved
18 | 4/2 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 333 | [7 empty] | Approved
19 | 4/3 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 349.999 | [7 empty] | Approved
20 | 4/4 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 331.001 | [7 empty] | Approved
21 | 4/5 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 1732.41 | [6 empty] | Approved
[14 empty] | 349 | [7 empty] | Approved
22 | 4/6 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  | 349.2 | [6 empty] | Approved
[14 empty] | 360 | [7 empty] | Approved
23 | 4/7 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  | 360.27 | [6 empty] | Approved
[14 empty] | 460 | [7 empty] | Approved
24 | 4/8 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  | 460.04 | [6 empty] | Approved
[14 empty] | 230 | [7 empty] | Approved
25 | 4/9 | DB+6 | [7 empty] | 0 | 0 | 0 | 0 |  | 229.26 | [6 empty] | Approved
[14 empty] | 371.51 | [7 empty] | Approved
26 | 4/10 | DB+6 | [6 empty] | 1 | 1 | 1 | 1 | 1 |  | 351.41 | [6 empty] | Approved
[14 empty] | 332.471 | [7 empty] | Approved
27 | 4/11 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 338.77 | [6 empty] | Approved
[14 empty] | 424.43 | [7 empty] | Approved
28 | 4/12 | DA+9 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 326.731 | [7 empty] | Approved
29 | 4/13 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 291.857 | [7 empty] | Approved
30 | 4/14 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 292.001 | [7 empty] | Approved
31 | 4/15 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 1349.09 | [6 empty] | Approved
[14 empty] | 415 | [7 empty] | Approved
32 | 4/16 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 414.59 | [6 empty] | Approved
[14 empty] | 237 | [7 empty] | Approved
33 | 4/17 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 253.29 | [6 empty] | Approved
[14 empty] | 188.454 | [7 empty] | Approved
34 | 5/0 | DB+6 | 11° 47' 59"RT | [6 empty] | 0 | 0 | 0 | 0 |  |  | Completed | 2024-08-28 |  |  |  |  | Approved
[14 empty] | 383 |  | Completed | 2024-08-28 |  |  |  |  | Approved
35 | 5/1 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 383 | Completed | 2024-08-28 |  |  |  |  | Approved
[14 empty] | 311 |  | Completed | 2024-08-28 |  |  |  |  | Approved
36 | 5/2 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | 2024-08-28 |  |  |  |  | Approved
[14 empty] | 350 |  | Completed | 2024-08-28 |  |  |  |  | Approved
37 | 5/3 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | 2024-08-28 |  |  |  |  | Approved
[14 empty] | 291 |  | Completed | 2024-08-28 |  |  |  |  | Approved
38 | 5A/0 | DC+0 | 24° 44' 29"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 952 | Completed | 2024-08-28 |  |  |  |  | Approved
[14 empty] | 322 | [7 empty] | Approved
39 | 5A/1 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 322 | [6 empty] | Approved
[14 empty] | 284 | [7 empty] | Approved
40 | 5A/2 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 284 | [6 empty] | Approved
[14 empty] | 282.743 | [7 empty] | Approved
41 | 5B/0 | DB+3 | 7° 28' 45"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 282.743 | [6 empty] | Approved
[14 empty] | 462.058 | [7 empty] | Approved
42 | 6/0 | DC+0 | 15° 37' 24"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 462.058 | [6 empty] | Approved
[14 empty] | 328.624 | [7 empty] | Approved
43 | 7/0 | DB+9 | 23° 4' 48"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 328.624 | [6 empty] | Approved
[14 empty] | 364.001 | [7 empty] | Approved
44 | 7/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 279 | [7 empty] | Approved
45 | 7/2 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 251.999 | [7 empty] | Approved
46 | 7/3 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 279.246 | [7 empty] | Approved
47 | 8/0 | DD+0 | 54° 40' 18"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 1174.246 | [6 empty] | Approved
[14 empty] | 134.216 | [7 empty] | Approved
48 | 8A/0 | DD+0 | 38° 34' 26"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 134.216 | [6 empty] | Approved
[14 empty] | 336.503 | [7 empty] | Approved
49 | 8B/0 | DC+9 | 23° 30' 1"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 336.503 | [6 empty] | Approved
[14 empty] | 365 | [7 empty] | Approved
50 | 8B/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 279.999 | [7 empty] | Approved
51 | 8B/2 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 255.141 | [7 empty] | Approved
52 | 8C/0 | DD+0 | 50° 17' 26"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 900.14 | [6 empty] | Approved
[14 empty] | 318.758 | [7 empty] | Approved
53 | 8D/0 | DD+0 | 43° 40' 17"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 318.758 | Completed | 2024-08-28 |  |  |  |  | Approved
[14 empty] | 307 |  | Completed | 2024-08-28 |  |  |  |  | Approved
54 | 8D/1 | DD+9 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | 2024-08-28 |  |  |  |  | Approved
[14 empty] | 312 |  | Completed | 2024-08-28 |  |  |  |  | Approved
55 | 8D/2 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | 2024-08-28 |  |  |  |  | Approved
[14 empty] | 440 |  | Completed | 2024-08-28 |  |  |  |  | Approved
56 | 8D/3 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 1059 | Completed | 2024-08-28 |  |  |  |  | Approved
[14 empty] | 459 |  | Completed | 2024-08-28 |  |  |  |  | Approved
57 | 8D/4 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 459 | Completed | 2024-08-28 |  |  |  |  | Approved
[14 empty] | 195 |  | Completed | 2024-08-28 |  |  |  |  | Approved
58 | 8D/5 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 195 | Completed | 2024-08-28 |  |  |  |  | Approved
[14 empty] | 295 |  | Completed | 2024-08-28 |  |  |  |  | Approved
59 | 8D/6 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 295 | Completed | 2024-08-28 |  |  |  |  | Approved
[14 empty] | 380.248 | [7 empty] | Approved
60 | 8E/0 | DC+0 | 26° 29' 57"RT | [5 empty] | 1 | 1 | 1 | 1 | 1 |  | 380.248 | [6 empty] | Approved
[14 empty] | 428 | [7 empty] | Approved
61 | 8E/1 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 428 | [6 empty] | Approved
[14 empty] | 419 | [7 empty] | Approved
62 | 8E/2 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  | 419 | [6 empty] | Approved
[14 empty] | 345 | [7 empty] | Approved
63 | 8E/3 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 296 | [7 empty] | Approved
64 | 8E/4 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 259 | [7 empty] | Approved
65 | 8E/5 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  | 900 | [6 empty] | Approved
[14 empty] | 343.874 | [7 empty] | Approved
66 | 8E/6 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  | 343.874 | [6 empty] | Approved
[14 empty] | 499.126 | [7 empty] | Approved
67 | 8E/7 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 499.126 | [6 empty] | Approved
[14 empty] | 434 | [7 empty] | Approved
68 | 8E/8 | DB+9 | [7 empty] | 0 | 0 | 0 | 0 |  | 434 | [6 empty] | Approved
[14 empty] | 295 | [7 empty] | Approved
69 | 8E/9 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 326 | [7 empty] | Approved
70 | 8E/10 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 298 | [7 empty] | Approved
71 | 8E/11 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 919 | [6 empty] | Approved
[14 empty] | 489 | [7 empty] | Approved
72 | 8E/12 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 489 | [6 empty] | Approved
[14 empty] | 382.474 | [7 empty] | Approved
73 | AP-9 | DC+3 | 21° 0' 5"LT | [12 empty] | Completed | [5 empty] | Approved
[14 empty] | 372.4 |  | Completed | [5 empty] | Approved
74 | 9/1 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 350.02 |  | Completed | [5 empty] | Approved
75 | 9/2 | DA+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 303.57 |  | Completed | [5 empty] | Approved
76 | 9/3 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 224.33 |  | Completed | [5 empty] | Approved
77 | 9/4 | DB+0 | [12 empty] | 1250.32 | Completed | [5 empty] | Approved
[14 empty] | 246.76 |  | Completed | [5 empty] | Approved
78 | 9/5 | DB+6 | [12 empty] | 246.76 | Completed | [5 empty] | Approved
[14 empty] | 418.18 |  | Completed | [5 empty] | Approved
79 | 9/6 | DA+9 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 298.66 |  | Completed | [5 empty] | Approved
80 | 9/7 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 358.67 |  | Completed | [5 empty] | Approved
81 | 9/8 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 366.13 |  | Completed | [5 empty] | Approved
82 | 9/9 | DA+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 255.6 |  | Completed | [5 empty] | Approved
83 | AP-10 | DD+0 | 38° 36' 12"LT | [11 empty] | 1697.24 | Completed | [5 empty] | Approved
[14 empty] | 229.724 |  | Completed | [5 empty] | Approved
84 | 10/1 | DA+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 359.356 |  | Completed | [5 empty] | Approved
85 | 10/2 | DA+9 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 365.874 |  | Completed | [5 empty] | Approved
86 | 10/3 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 345.784 |  | Completed | [5 empty] | Approved
87 | 10/4 | DA+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 299.34 |  | Completed | [5 empty] | Approved
88 | AP-11 | DC+0 | 25° 37' 10"RT | [11 empty] | 1600.07 | Completed | [5 empty] | Approved
[14 empty] | 296 | [7 empty] | Approved
89 | 11/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 229.889 | [7 empty] | Approved
90 | AP-12 | DD+0 | 40° 29' 60"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 525.889 | [6 empty] | Approved
[14 empty] | 356.279 | [7 empty] | Approved
91 | AP-13 | DC+3 | 24° 1' 33"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 356.28 | [6 empty] | Approved
[14 empty] | 314 | [7 empty] | Approved
92 | 13/1 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 353.589 | [7 empty] | Approved
93 | AP-14 | DC+6 | 25° 35' 30"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 667.59 | [6 empty] | Approved
[14 empty] | 362 | [7 empty] | Approved
94 | 14/1 | DB+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 362 | [6 empty] | Approved
[14 empty] | 387 | [7 empty] | Approved
95 | 14/2 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 365 | [7 empty] | Approved
96 | 14/3 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 752 | [6 empty] | Approved
[14 empty] | 419 | [7 empty] | Approved
97 | 14/4 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 331 | [7 empty] | Approved
98 | 14/5 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 390 | [7 empty] | Approved
99 | 14/6 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 349 | [7 empty] | Approved
100 | 14/7 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 324 | [7 empty] | Approved
101 | 14/8 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 413 | [7 empty] | Approved
102 | 14/9 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved
[14 empty] | 310.18 | [7 empty] | Approved
103 | AP-15 | DD+0 | 37° 6' 34"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 2536.18 | [6 empty] | Approved | 2024-09-06
[14 empty] | 379 | [7 empty] | Approved | 2024-09-06
104 | 15/1 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 304 | [7 empty] | Approved | 2024-09-06
105 | 15/2 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 333 | [7 empty] | Approved | 2024-09-06
106 | 15/3 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 363 | [7 empty] | Approved | 2024-09-06
107 | 15/4 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 384 | [7 empty] | Approved | 2024-09-06
108 | 15/5 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 361 | [7 empty] | Approved | 2024-09-06
109 | 15/6 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 311 | [7 empty] | Approved | 2024-09-06
110 | 15/7 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 381 | [7 empty] | Approved | 2024-09-06
111 | 15/8 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 316 | [7 empty] | Approved | 2024-09-06
112 | 15/9 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 290.45 | [7 empty] | Approved | 2024-09-06
113 | AP-16 | DC+0 | 29° 42' 12"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 3422.45 | [6 empty] | Approved | 2024-09-06
[14 empty] | 306 | [7 empty] | Approved | 2024-09-06
114 | 16/1 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 336 | [7 empty] | Approved | 2024-09-06
115 | 16/2 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 337 | [7 empty] | Approved | 2024-09-06
116 | 16/3 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 328.65 | [7 empty] | Approved | 2024-09-06
117 | AP-17 | DC+3 | 20° 7' 26"LT | [6 empty] | 0 | 0 | 0 | 0 |  | 1307.65 | [6 empty] | Approved | 2024-09-06
[14 empty] | 362 | [7 empty] | Approved | 2024-09-06
118 | 17/1 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 364 | [7 empty] | Approved | 2024-09-06
119 | 17/2 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 388 | [7 empty] | Approved | 2024-09-06
120 | 17/3 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 | [8 empty] | Approved | 2024-09-06
[14 empty] | 321.97 | [7 empty] | Approved | 2024-09-06
121 | AP-18 | DC+0 | 25° 10' 25"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 1435.97 | [6 empty] | Approved
[14 empty] | 365.484 | [7 empty] | Approved
122 | 18/1 | DA+0 | [19 empty] | Approved
[14 empty] | 373.966 | [7 empty] | Approved
123 | 18/2 | DA+3 | 40° 29' 60"LT | [18 empty] | Approved
[14 empty] | 356.054 | [7 empty] | Approved
124 | 18/3 | DA+0 | 24° 1' 33"RT | [18 empty] | Approved
[14 empty] | 349.663 | [7 empty] | Approved
125 | 18/4 | DA+0 | [19 empty] | Approved
[14 empty] | 353.115 | [7 empty] | Approved
126 | 18/5 | DA+3 | 25° 35' 30"LT | [18 empty] | Approved
[14 empty] | 374.201 | [7 empty] | Approved
127 | 18/6 | DA+3 | [19 empty] | Approved
[14 empty] | 341.321 | [7 empty] | Approved
128 | 18/7 | DA+6 | [19 empty] | Approved
[14 empty] | 347.958 | [7 empty] | Approved
129 | 18/8 | DA+3 | [19 empty] | Approved
[14 empty] | 384.02 | [7 empty] | Approved
130 | 18/9 | DA+3 | [19 empty] | Approved
[14 empty] | 269.694 | [7 empty] | Approved
131 | 18/10 | DA+3 | [19 empty] | Approved
[14 empty] | 394.041 | [7 empty] | Approved
132 | 18/11 | DA+3 | [19 empty] | Approved
[14 empty] | 300.614 | [7 empty] | Approved
133 | AP-19 | DB+3 | [12 empty] | 4210.131 | [6 empty] | Approved
[14 empty] | 315.42 | [7 empty] | Approved
134 | 19/1 | DA+0 | [19 empty] | Approved
[14 empty] | 329.64 | [7 empty] | Approved
135 | 19/2 | DA+3 | [19 empty] | Approved
[14 empty] | 382.97 | [7 empty] | Approved
136 | 19/3 | DA+3 | 37° 6' 34"RT | [18 empty] | Approved
[14 empty] | 323.74 | [7 empty] | Approved
137 | 19/4 | DA+0 | [19 empty] | Approved
[14 empty] | 328.78 | [7 empty] | Approved
138 | 19/5 | DA+0 | [19 empty] | Approved
[14 empty] | 266 | [7 empty] | Approved
139 | AP-20 | DB+0 | [12 empty] | 1946.558 | [6 empty] | Approved
[14 empty] | 321.89 | [7 empty] | Approved
140 | 20/1 | DA+0 | [19 empty] | Approved
[14 empty] | 352.14 | [7 empty] | Approved
141 | 20/2 | DA+3 | [19 empty] | Approved
[14 empty] | 347.32 | [7 empty] | Approved
142 | 20/3 | DA+0 | [19 empty] | Approved
[14 empty] | 339.42 | [7 empty] | Approved
143 | 20/4 | DA+0 | [19 empty] | Approved
[14 empty] | 330.88 | [7 empty] | Approved
144 | 20/5 | DA+0 | [19 empty] | Approved
[14 empty] | 279.99 | [7 empty] | Approved
145 | 20/6 | DA+3 | [19 empty] | Approved
[14 empty] | 369.48 | [7 empty] | Approved
146 | 20/7 | DA+3 | 29° 42' 12"RT | [18 empty] | Approved
[14 empty] | 369.65 | [7 empty] | Approved
147 | 20/8 | DA+3 | [19 empty] | Approved
[14 empty] | 284 | [7 empty] | Approved
148 | AP-21 | DB+0 | [12 empty] | 2994.757 | [6 empty] | Approved
[14 empty] | 345.88 | [7 empty] | Approved
149 | 21/1 | DA+3 | [19 empty] | Approved
[14 empty] | 310.87 | [7 empty] | Approved
150 | 21/2 | DA+3 | 20° 7' 26"LT | [18 empty] | Approved
[14 empty] | 380.03 | [7 empty] | Approved
151 | 21/3 | DA+3 | [19 empty] | Approved
[14 empty] | 358.18 | [7 empty] | Approved
152 | 21/4 | DA+0 | [19 empty] | Approved
[14 empty] | 311.05 | [7 empty] | Approved
153 | 21/5 | DA+3 | [19 empty] | Approved
[14 empty] | 375.15 | [7 empty] | Approved
154 | 21/6 | DA+3 | 16° 0' 26"LT | [12 empty] | Completed | [5 empty] | Approved
[14 empty] | 369.13 |  | Completed | [5 empty] | Approved
155 | 21/7 | DA+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 370.97 |  | Completed | [5 empty] | Approved
156 | 21/8 | DA+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 356.46 |  | Completed | [5 empty] | Approved
157 | 21/9 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 363.33 |  | Completed | [5 empty] | Approved
158 | 21/10 | DA+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 370.25 |  | Completed | [5 empty] | Approved
159 | 21/11 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 330.02 |  | Completed | [5 empty] | Approved
160 | 21/12 | DA+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 390.08 |  | Completed | [5 empty] | Approved
161 | 21/13 | DA+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 343.38 |  | Completed | [5 empty] | Approved
162 | AP-22 | DC+3 | 20° 2' 24"RT | [12 empty] | Completed | [5 empty] | Approved
[14 empty] | 326.53 |  | Completed | [5 empty] | Approved
163 | 22/1 | DA+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 302.5 |  | Completed | [5 empty] | Approved
164 | 22/2 | DA+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 318.2 |  | Completed | [5 empty] | Approved
165 | AP-23 | DC+0 | 19° 37' 2"LT | [12 empty] | Completed | [5 empty] | Approved
[14 empty] | 315.48 |  | Completed | [5 empty] | Approved
166 | 23/1 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 249.29 |  | Completed | [5 empty] | Approved
167 | 23/2 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 288.05 |  | Completed | [5 empty] | Approved
168 | 23/3 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 369.86 |  | Completed | [5 empty] | Approved
169 | 23/4 | DA+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 320.21 |  | Completed | [5 empty] | Approved
170 | 23/5 | DA+0 | [13 empty] | Completed | [5 empty] | Approved |  |  |  | P.NEW AP90/0
[14 empty] | 383.86 |  | Completed | [5 empty] | Approved
171 | AP-24 | DD+9 | 31° 13' 23"LT | [5 empty] | 3 | 3 | 3 | 3 | 3 |  |  | Completed | [5 empty] | Approved
[14 empty] | 190.524 |  | Completed | [5 empty] | Approved
| AP-25 | DD+18 | 5° 43' 47"RT | [5 empty] | 2 | 2 | 2 | 2 | 2 |  | 190.52 | Completed | [5 empty] | Approved
[14 empty] | 173.541 |  | Completed | [5 empty] | Approved
| AP-26 | DD+18 | 17° 37' 36"LT | [5 empty] | 2 | 2 | 2 | 2 | 2 |  | 173.54 | Completed | [5 empty] | Approved
[14 empty] | 142.384 |  | Completed | [5 empty] | Approved
| AP-27 | DD+18 | 24° 41' 6"LT | [5 empty] | 1 | 1 | 1 | 1 | 1 |  | 142.38 | Completed | [5 empty] | Approved
[14 empty] | 77.015 |  | Completed | [5 empty] | Approved
| AP-28 | DD+0 | 22° 6' 42"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 77.02 | Completed | [5 empty] | Approved
[14 empty] | 42.266 |  | Completed | [5 empty] | Approved
| 28/1 | GANTRY UC | [7 empty] | 0 | 0 | 0 | 0 |  | 42.27 | Completed | [5 empty] | Approved
[14 empty] | 54.573 |  | Completed | [5 empty] | Approved
| 28/2 | GANTRY UC | [7 empty] | 0 | 0 | 0 | 0 |  | 54.57 | Completed | [5 empty] | Approved
[14 empty] | 41.886 |  | Completed | [5 empty] | Approved
| AP-29 | DD+3 | 28° 4' 46"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 41.89 | Completed | [5 empty] | Approved
[14 empty] | 353.284 |  | Completed | [5 empty] | Approved
| 29A/0 | DC+9 | 11° 39' 27"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 353.28 | Completed | [5 empty] | Approved
[14 empty] | 393 |  | Completed | [5 empty] | Approved
| 29A/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 359 |  | Completed | [5 empty] | Approved
| 29A/2 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 387 |  | Completed | [5 empty] | Approved
| 29A/3 | DA+9 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 346 |  | Completed | [5 empty] | Approved
| 29A/4 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 375.545 |  | Completed | [5 empty] | Approved
| AP-30 | DB+3 | 10° 21' 46"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 1860.55 | Completed | [5 empty] | Approved
341.74
#REF! | 30/1 | DA+0 | [7 empty] | 0 | 0 | 0 | 0
321.51
#REF! | 30/2 | DA+0 | [7 empty] | 0 | 0 | 0 | 0
312.39
#REF! | 30/3 | DA+0 | [7 empty] | 0 | 0 | 0 | 0
358.35
#REF! | 30/4 | DA+0 | [7 empty] | 0 | 0 | 0 | 0
319.21
#REF! | 30/5 | DA+0 | [7 empty] | 0 | 0 | 0 | 0
342.4
#REF! | 30/6 | DA+3 | [7 empty] | 0 | 0 | 0 | 0
337.31
#REF! | AP-31 | DB+3 | 12° 12' 46"LT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 3217.91
371.81
| 31/1 | DA+6 |  | 5 | 5 | 5 | 5 | 5
371.54
| AP-32 | DC+0 | 20° 20' 13"RT | 5 | 5 | 5 | 5 | 5
303
| 32/1 | DA+0 |  | 2 | 2 | 2 | 2 | 2
303
| 32/2 | DA+0 |  |  | 0 | 0 | 0 | 0
303.22
| 33/0 | DD+0 | 37° 48' 15"RT |  | 0 | 0 | 0 | 0
| 34/0 | DD+0
[14 empty] | 63.8662 |  | 16.841 |  |  | 0 |  |  | 59.0567

## Detail Survey-132kV (hidden)
Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc
132kV - Detailed Survey Progress
Sl. No. | LOC NO | TowerType | Deviation of Angle | CP | Leg Extension |  |  |  | RC | Chimney Extension |  |  |  | Span Length (m) | Section Length | Detail Survey completion status |  |  | Detail Survey Report Submision |  |  | Detail Survey Approval |  |  | Remarks
|  |  | DMS | m | A | B | C | D | m | A | B | C | D | m | m | Surveyed | DOC | Re-survey | Submitted | Date | Re-submitted | Approved | Date | Re-apprpved
| Tapping Tower | DD+0 | 2° 10' 33"LT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | Completed
[14 empty] | 25.917 |  | Completed
1 | DE | DD+0 | 44° 51' 5"RT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 25.92 | Completed
[14 empty] | 261.985 |  | Completed
2 | 1/0 | DB+0 | 6° 49' 55"RT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 261.99 | Completed
[14 empty] | 339.331 |  | Completed
3 | 2/0 | DC+6 | 26° 16' 38"LT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 339.33 | Completed
[14 empty] | 379.175 |  | Completed
4 | 3/0 | DB+6 | 13° 55' 42"RT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 379.18 | Completed
[14 empty] | 238 |  | Completed
5 | 3/1 | DA+6 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 260 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
6 | 3/2 | DA+3 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 256.018 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
7 | 4/0 | DB+0 | 2° 10' 59"RT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 754.02 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 321.753 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
8 | 4/1 | DB+0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 321.75 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 161.247 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
9 | 4/2 | DA+3 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 327.381 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
10 | 5/0 | DD+3 | 23° 16' 52"RT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 488.63 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 36.276 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
11 | 5/1 | GANTRY UC (+2M) |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 29 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 61.139 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
12 | 5/2 | GANTRY UC (+2M) |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 81 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 38.566 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
13 | 6/0 | DD+0 | 25° 0' 0"LT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 25.98 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 182.043 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
14 | 6A/0 | DD+0 | 53° 55' 29"LT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 182.04 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 204.148 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
15 | 7/0 | DB+0 | 12° 53' 30"LT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 204.15 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 254 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
16 | 7/1 | DA+3 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 294 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
17 | 7/2 | DA+3 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 249.824 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
18 | 8/0 | DD+3 | 49° 20' 19"RT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 797.82 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 329.657 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
19 | 9/0 | DD+3 | 33° 26' 28"RT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 329.66 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 170 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
20 | 9/1 | DA+6 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 312 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
21 | 9/2 | DA+6 |  |  | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 259.919 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
22 | 10/0 | DD+6 | 16° 17' 32"RT |  | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 |  | 741.92 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 215.125 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
23 | 11/0 | DD+6 | 21° 26' 57"RT |  | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 |  | 215.13 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 316.145 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
24 | 12/0 | DB+0 | 2° 8' 42"LT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 316.15 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 267 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
25 | 12/1 | DA+3 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 267.185 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
26 | 13/0 | DD+0 | 23° 12' 4"LT |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 |  | 534.19 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 87.412 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
27 | 13/1 | GANTRY UC (+2M) |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 85 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 66.461 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
28 | 13/2 | GANTRY UC (+2M) |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 70 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 56.382 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
29 | 14/0 | DD+6 | 29° 21' 6"RT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 55.25 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 224.231 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
30 | 15/0 | DD+3 | 33° 34' 25"LT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 224.23 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 276 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
31 | 15/1 | DA+0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 244 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
32 | 15/2 | DA+0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 241 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
33 | 15/3 | DA+0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 240.727 |  | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
34 | 16/0 | DD+0 | 5° 27' 59"RT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1001.73 | Completed |  |  | Submitted |  | 2024-08-29 | Approved | 2024-09-10
[14 empty] | 48 |  | Completed |  |  | Submitted |  |  | Approved
35 | 16/1 | GANTRY UC (+2M) |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 48 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 49 |  | Completed |  |  | Submitted |  |  | Approved
36 | 16/2 | GANTRY UC (+2M) |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 49 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 48.938 |  | Completed |  |  | Submitted |  |  | Approved
37 | 17/0 | DD+0 | 29° 14' 60"LT |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 48.94 | Completed |  |  | Submitted |  |  | Approved
[14 empty] | 165.147 |  | Completed |  |  | Submitted |  |  | Approved
#REF! | 18/0 | DE+0 (AUX) | 89° 59' 59"RT |  | 0 | 0 | 0 | 0 | [6 empty] | 165.15
39.999
#REF! | GANTRY | GANTRY |  |  | 0 | 0 | 0 | 0 | [6 empty] | 40
[14 empty] | 7.8151 |  | 7.7751 |  |  | 6.5307 |  |  | 6.5307

## Check Survey-132kV (hidden)
Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc
220kV - Check Survey Progress
Sl. No. | LOC NO | TowerType | Deviation of Angle | CP | Leg Extension |  |  |  | RC | Chimney Extension |  |  |  | Span Length (m) | Section Length | Detail Survey completion status |  |  | Detail Survey Report Submision |  |  | Detail Survey Approval |  |  | Remarks
|  |  | DMS | m | A | B | C | D | m | A | B | C | D | m | m | Surveyed | DOC | Re-survey | Submitted | Date | Re-submitted | Approved | Date | Re-apprpved
| GANTRY | GANTRY | [7 empty] | 0 | 0 | 0 | 0
#REF! | 1/0 | DE+0 | 42° 49' 3"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 699.92
230.15
#REF! | 2/0 | DB+0 | 27° 13' 43"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 356.66
234.56
#REF! | 2/1 | DB+6 | 49° 56' 13"RT | [6 empty] | 0 | 0 | 0 | 0 |  | 174.21
251.12
#REF! | 3/0 | DD+0 | 7° 56' 47"LT | [6 empty] | 0 | 0 | 0 | 0
183
#REF! | 3/1 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 321.75
182.07
#REF! | 4/0 | DC+0 | [7 empty] | 0 | 0 | 0 | 0
328.09
#REF! | 5/0 | DD+3 | [7 empty] | 0 | 0 | 0 | 0 |  | 488.63 | Completed | [5 empty] | Approved
[14 empty] | 40 |  | Completed | [5 empty] | Approved
#REF! | 5/1 | GANTRY UC (+2M) | [7 empty] | 0 | 0 | 0 | 0 |  | 40 | Completed | [5 empty] | Approved
[14 empty] | 57.415 |  | Completed | [5 empty] | Approved
#REF! | 5/2 | GANTRY UC (+2M) | [7 empty] | 0 | 0 | 0 | 0 |  | 57.42 | Completed | [5 empty] | Approved
[14 empty] | 38.566 |  | Completed | [5 empty] | Approved
#REF! | 6/0 | DD+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 38.57 | Completed | [5 empty] | Approved
[14 empty] | 182.043 |  | Completed | [5 empty] | Approved
#REF! | 6A/0 | DD+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 182.04 | Completed | [5 empty] | Approved
[14 empty] | 204.148 |  | Completed | [5 empty] | Approved
#REF! | 7/0 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  | 204.15 | Completed | [5 empty] | Approved
[14 empty] | 230 |  | Completed | [5 empty] | Approved
#REF! | 7/1 | DA+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 294 |  | Completed | [5 empty] | Approved
#REF! | 7/2 | DA+3 | [6 empty] | 1 | 1 | 1 | 1 | 1 |  |  | Completed | [5 empty] | Approved
[14 empty] | 249.82 |  | Completed | [5 empty] | Approved
#REF! | 8/0 | DD+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 329.66 |  | Completed | [5 empty] | Approved
#REF! | 9/0 | DD+3 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 170 |  | Completed | [5 empty] | Approved
#REF! | 9/1 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 312 |  | Completed | [5 empty] | Approved
#REF! | 9/2 | DA+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 259.92 |  | Completed | [5 empty] | Approved
#REF! | 10/0 | DD+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 215.13 |  | Completed | [5 empty] | Approved
#REF! | 11/0 | DD+6 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 316.15 |  | Completed | [5 empty] | Approved
#REF! | 12/0 | DB+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 267 | 267 | Completed | [5 empty] | Approved
#REF! | 12/1 | DA+3 | 11° 47' 59"RT | [6 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 267.185 | 267.185 | Completed | [5 empty] | Approved
#REF! | 13/0 | DD+0 | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 87.412 | 87.412 | Completed | [5 empty] | Approved
#REF! | 13/1 | GANTRY UC (+2M) | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 66.461 | 66.461 | Completed | [5 empty] | Approved
#REF! | 13/2 | GANTRY UC (+2M) | [7 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 56.381 | 56.381 | Completed | [5 empty] | Approved
#REF! | 14/0 | DD+6 | 24° 44' 29"LT | [6 empty] | 0 | 0 | 0 | 0 |  |  | Completed | [5 empty] | Approved
[14 empty] | 224.231 | 224.231 | Completed | [5 empty] | Approved
| 15/0 | DD+3 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 276 | 276 | Completed | [5 empty] | Approved
| 15/1 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 244 | 244 | Completed | [5 empty] | Approved
| 15/2 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 241 | 241 | Completed | [5 empty] | Approved
| 15/3 | DA+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 240.727 | 240.727 | Completed | [5 empty] | Approved
| 16/0 | DD+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 48 | 48 | Completed | [5 empty] | Approved
| 16/1 | GANTRY UC (+2M) | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 49 | 49 | Completed | [5 empty] | Approved
| 16/2 | GANTRY UC (+2M) | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 48.938 | 48.938 | Completed | [5 empty] | Approved
| 17/0 | DD+0 | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 165.147 | 165.147 | Completed | [5 empty] | Approved
| 18/0 | DE+0 (AUX) | [13 empty] | Completed | [5 empty] | Approved
[14 empty] | 39.999 | 39.999 | Completed | [5 empty] | Approved
| GANTRY | GANTRY | [19 empty] | Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
Approved
[14 empty] | 6.6293 |  | 5.2203 |  |  | 0

## Summary
Client: M/S STERLITE POWER TRANSMISSION LIMITED
Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc | [13 empty] | Contractual Start Date : |  |  | 2024-06-06
Name of Document : Daily Progress Report (DPR) | [13 empty] | Contractual Completion Date: |  |  | 2025-05-25
Office: Neemuch | [13 empty] | Revised Completion Date : |  |  | 2026-03-31
Progress of 220kV Line | [15 empty] | Date: | 2026-04-14
Sr. No. | Activity | UoM | Total Quantity | As per L2 |  | Cumm. Progress up to last Month |  | Progress of Current Month (April'26) |  |  | Cumulative till current month |  |  | Resources Status |  |  | Critical Issues, if any & Remark
|  |  |  | Start Date | End Date | L2 | Actual | Plan | Today | Progress in Month | Target (L2) | Completed | Balance | Targeted Gang | Available Gang | Shortfall Gang
1 | Detailed Survey | Kms | 64 | 2024-06-18 | 2024-08-31 | 64 | 64.178 | 0 | 0 | 0 | 64 | 64.178 | -0.178 | 0 | 0 | 0
2 | Check Survey | Kms | 64 | 2024-07-01 | 2024-09-30 | 64 | 64.178 | 0 | 0 | 0 | 64 | 64.178 | -0.178 |  |  | 0
3 | Foundation | Nos. | 199 | 2024-08-01 | 2025-01-31 | 199 | 195 | 4 | 0 | 1 | 199 | 196 | 3 | 1 | 1 | 0 | RCC of Location no. 33/1 Underprogress
4 | Earthing | Nos. | 199 | 2024-08-01 | 2025-01-31 | 199 | 195 | 4 | 0 | 0 | 199 | 195 | 4
5 | Tower Erection | Nos. | 199 | 2024-09-20 | 2025-02-28 | 199 | 195 | 4 | 0 | 0 | 199 | 195 | 4 | 0 | 0 | 0 |  | 12500
6 | Tack Welding | Nos. | 199 | 2024-09-20 | 2025-02-28 | 199 | 182 | 27 | 2 | 9 | 199 | 191 | 8 | 0 | 0 | 0 | 8D/0 Tackwelding completed
7 | Stringing | Kms | [7 empty] | 0 | [6 empty] | Conductor final sag for Section 1C/0 to 1D/0 Completed | 9
i | Paying Out | Kms | 64 | 2024-11-11 | 2025-04-30 | 64 | 60.06 | 3.94 | 0 | 1.1393 | 64 | 61.1993 | 2.8007 | 1 | 1 | 0 |  | 15
ii | Final Sag | Kms | 64 | 2024-11-11 | 2025-04-30 | 64 | 60.06 | 3.94 | 0.675 | 1.1393 | 64 | 61.1993 | 2.8007
iii | OPGW | Kms | 64 | 2024-12-01 | 2025-04-30 | 64 | 53.7218 | 10.2782 | 0 | 0 | 64 | 53.7218 | 10.2782 | 0 | 0 | 0
Progress of 132kV Line | [15 empty] | Date: | 2026-04-14
Sr. No. | Activity | UoM | Total Quantity | As per L2 |  | Cumm. Progress up to last Month |  | Progress of Current Month (April'26) |  |  | Cumulative till current month |  |  | Resources Status |  |  | Critical Issues, if any & Remark
|  |  |  | Start Date | End Date | L2 | Actual | Plan | Today | Progress in Month | Target (L2) | Completed | Balance | Targeted Gang | Available Gang | Shortfall Gang
1 | Detailed Survey | Kms | 9 | 2024-06-18 | 2024-08-31 | 9 | 9 |  | 0 | 0 | 9 | 9 | 0 |  |  | 0
2 | Check Survey | Kms | 9 | 2024-07-01 | 2024-09-30 | 9 | 9 |  | 0 | 0 | 9 | 9 | 0 |  |  | 0
3 | Foundation | Nos. | 39 | 2024-08-01 | 2025-01-31 | 39 | 31 | 5 | 1 | 3 | 39 | 34 | 5 | 2 | 2 | 0 | 3/0 RCC completed SC-1 Excavation Completed
4 | Earthing | Nos. | 39 | 2024-08-01 | 2025-01-31 | 39 | 31 | 5 | 0 | 2 | 39 | 33 | 6 | 2 | 2 | 0
5 | Tower Erection | Nos. | 39 | 2024-09-20 | 2025-02-28 | 39 | 29 | 5 | 0 | 0 | 39 | 29 | 10 | 0 | 0 | 0
6 | Tack Welding | Nos. | 39 | 2024-09-20 | 2025-02-28 | 39 | 29 | 0 | 0 | 0 | 39 | 29 | 10 | 0 | 0 | 0
7 | Stringing
i | Paying Out | Kms | 9 | 2024-11-11 | 2025-04-30 | 9 | 5 | 1.483 | 0 | -0.003174 | 9 | 4.9968 | 4.0032 | 0 | 0 | 0
ii | Final Sag | Kms | 9 | 2024-11-11 | 2025-04-30 | 9 | 4.62 | 1.483 | 0 | 0.37683 | 9 | 4.9968 | 4.0032 | 0 | 0
iii | OPGW | Kms | 9 | 2024-12-01 | 2025-04-30 | 9 | 0 | 9 | 0 | 0 | 9 |  | 9 |  |  | 0

## Statutory
Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc
SI No | Name of Existing Line/Croccing | Name of the owner of existing line | Crossing Type | Existing Crossing Span (M) | Existing Tower/K MP No | AP | Tower Type | RC if any | Crossing Angle | Crossing Span Length | Electrical Clearance | Proposal Preparation | Proposal Submission to Sterlite on | Submission to concerned office | Joint site inspection | Submission of charges (if any) | NOC Received on | Remarks
Statutory/Crossing Tracker - 220KV D/C Line
1 | NH-27 | NHAI | NH |  |  | 1B/0-1C/0 | 1B/0(DD+3)-1C/0(DD+3) | - |  | 248
2 | NH-27 | NHAI | NH |  |  | 3/0-4/0 | 3/0(DD+3)-4/0(DB+9) | - |  | 229.73
3 | 220KV S/C LINE | PGCIL | PLC | 179-180 |  | 24/0-25/0 | 24/0(DD+9)-25/0(DD+18) | 3M & 2M |  | 190.52
4 | 220KV D/C RPB-CGH LINE | PGCIL | PLC | 179-180 |  | 26/0-27/0 | 26/0(DD+18)-27/0(DD+18) | 3M & 0M |  | 142.38
5 | 400KV T/L |  | PLC |  |  | 28/1-28/2 | 28/1(Gantry)-28/2(Gantry) | - |  | 44
6 | WATER RESERVOIR BOUNDARY |  |  |  |  | 31/0-31/1 | 31/0(DB+0)-31/1(DA+6) | 0M & 4M |  | 361
Statutory/Crossing Tracker - 132KV D/C Line
1 | Gas Pipeline |  | Pipeline |  |  | Tapping Tower -DE | Tapping Tower(DD+0 ) - DE (DD+0) | - |  | 25.92
2 | Pipeline, Cable |  | Pipeline |  |  | 3/1-3/2 | 3/1(DA+6)-3/2(DA+3) | - |  | 260
3 | River |  | River |  |  | 4/0-4/1 | 4/0(DB-3)-4/1(DB-3) | - |  | 302
4 | 220KV D/C LINE |  | PLC |  |  | 5/1-5/2 | 5/1(Gantry)-5/2(Gantry) | - |  | 50
5 | RAILWAY TRACK |  | Railway |  |  | 10/0-11/0 | 10/0(DD+6)-11/0(DD+6) | - |  | 215.13
6 | 220KV S/C LINE |  | PLC |  |  | 13/1-13/2 | 13/1(Gantry)-13/2(Gantry) | - |  | 53
7 | NH-27 | NHAI | NH |  |  | 14/0-15/0 | 14/0(DD+6)-15/0(DD-3) | - |  | 250
Name of Existing Line/Croccing | Name of the owner of existing line | Crossing Type | Section | Submission | JVR | Remarks
NH-27 | NHAI | NH | 1B/0-1C/0 |  | 2024-12-28 | Approval Recieved
NH-27 | NHAI | NH | 3/0-4/0 |  | 2024-10-21 | Approval Recieved
220KV S/C LINE | PGCIL | PLC | 24/0-25/0 | 06-01-2025 (2nd Submission) |  | Approval Recieved
220KV D/C RPB-CGH LINE | PGCIL | PLC | 26/0-27/0 | 06-01-2025 (2nd Submission) |  | Approval Recieved
400KV T/L | PGCIL | PLC | 28/1-28/2 | 06-01-2025 (2nd Submission) |  | Approval Recieved
220KV S/C RUMS Line | PGCIL | PLC | 33/1-34/0 |  |  | Proposal Submitted Awaiting for approval
132KV S/C RUMS Line | PGCIL | PLC | 34/0-35/0 |  |  | Proposal Submitted Awaiting for approval
132KV
Name of Existing Line/Croccing | Name of the owner of existing line | Crossing Type | Section | Submission | JVR | Remarks
220KV D/C LINE | PLC |  | 4/1-4/2 | 2025-01-10 | 2025-01-10 | Proposal will be submitted in Chittorgarh.
RAILWAY TRACK | Railway |  | 10/0-11/0 | 2025-01-02 | 2025-01-09 | Approval Recieved
220KV S/C LINE | PLC |  | 13/1-13/2 |  | 2024-12-22 | Approval Recieved
765KV S/C LINE | PLC |  | 16/1-16/2 | 2024-12-11 |  | Approval Recieved
NH-27 | NHAI | NH | 14/0-15/0 |  |  | Approval Recieved

## Progress-132kV
Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc
Progress of 220kV Line
220 KV D/C Neemuch - TS | [18 empty] | Foundation | [17 empty] | Earthing |  |  |  |  | Erection |  |  |  | Tower Checking-1 | Tack-Welding |  |  |  |  | Tower Checking-2
Sl. No. | LOC NO | Tower Type |  |  |  | Tower Weight |  |  |  | Stub Weight |  |  |  | Chimney Extension |  |  |  | Span Length(m) | Classification | Excavation Volume (m3) | Concreting Volume |  |  | 8mm Steel | 10mm Steel | 12mm Steel | 16mm Steel | 20mm Steel | 25mmSteel | Total Steel (MT) | Status (C/WIP) | Excavation |  | Concreting |  | Sub-Contractor Name | Status C/WIP | Type | DOS | DOC | Sub-Contractor Name | Status C/WIP | DOS | DOC | Sub-Contractor Name |  | Status C/WIP | DOS | DOC | Painting | Sub-Contractor Name
[6 empty] | HT | MS | BnA | Total | HT | MS | BnA | Total | A | B | C | D | m |  |  | M10 (1:3:6) (m3) | M20 (1:1.5:3) (m3) | Total | [8 empty] | DOS | DOC | DOS | DOC
Existing Tower
1 | SC-4 | DD+9(220KV) | 11.987 | 47.948 | 383.584 | 6.058 | 5.874 | 0.0077 | 0.563 | 12.5027 | 0.557 | 0.01 | 0.567 | [5 empty] | DFR | 119.36 | 2.05 | 18.37 | 20.42 | 157.1642 | 7858.21 | 89.9 |  | 1115.34 | 198.68
2 | Sc-3 | DD+9 (220KV) | 11.987 | 47.948 | 383.584 | 6.058 | 5.874 | 0.0077 | 0.563 | 12.5027 | 0.557 | 0.01 | 0.567 | [5 empty] | DFR | 119.36 | 2.05 | 18.37 | 20.42 | 157.1642 | 7858.21 | 89.9 |  | 1115.34 | 198.68
3 | SC-2 | DD+9 (220KV) | 11.987 | 47.948 | 383.584 | 6.058 | 5.874 | 0.0077 | 0.563 | 12.5027 | 0.557 | 0.01 | 0.567 | [5 empty] | DFR | 119.36 | 2.05 | 18.37 | 20.42 | 157.1642 | 7858.21 | 89.9 |  | 1115.34 | 198.68
4 | SC-1 | DD+6 | 11.987 | 47.948 | 383.584 | Tower Weight HT: 9.926; Tower Weight MS: 1.391; Tower Weight BnA: 0.498; Tower Weight Total: 11.815; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 89.9 |  | 1287.27 | 193.64 |  |  | 1.571
Tapping Tower
25.92
5 | 1/0 | DD+0 | 9.654 | 38.616 | 308.928 | Tower Weight HT: 6.958; Tower Weight MS: 1.055; Tower Weight BnA: 0.4; Tower Weight Total: 8.413; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 89.9 |  | 1287.27 | 193.64 |  |  | 1.571 | C |  |  |  |  | New Tech Engineer | C
230.15
6 | 2/0 | DD+0 | 9.654 | 38.616 | 308.928 | Tower Weight HT: 6.958; Tower Weight MS: 1.055; Tower Weight BnA: 0.4; Tower Weight Total: 8.413; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 89.9 |  | 1287.27 | 193.64 |  |  | 1.571 | C |  |  |  |  | New Tech Engineer | C | CP
234.56
7 | 2/1 | DD+6 | 11.987 | 47.948 | 383.584 | Tower Weight HT: 9.926; Tower Weight MS: 1.391; Tower Weight BnA: 0.498; Tower Weight Total: 11.815; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 89.9 |  | 1287.27 | 193.64 |  |  | 1.571 | C |  |  |  |  | New Tech Engineer | C | CP
251.12
8 | 3/0 | DD+0 | 9.654 | 38.616 | 308.928 | Tower Weight HT: 6.958; Tower Weight MS: 1.055; Tower Weight BnA: 0.4; Tower Weight Total: 8.413; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 89.9 |  | 1287.27 | 193.64 |  |  | 1.571 | C | 2026-04-09 | 2026-04-10 | 2026-04-12 | 2026-04-14 | Navya Associate
183
9 | 3/1 | DA+3 | 6.992 | 27.968 | 223.744 | Tower Weight HT: 2.777; Tower Weight MS: 1.897; Tower Weight BnA: 0.288; Tower Weight Total: 4.962; Stub Weight HT: 0.271; Stub Weight BnA: 0.007; Stub Weight Total: 0.278 | DFR | 41.44 | 0.8 | 7.73 | 8.53 | 73.75 | 235.38 |  | 201.4 |  |  | 0.51 | C | 2026-04-06 | 2026-04-07 | 2026-04-11 | 2026-04-12 | Navya Associate | C
182.07
10 | 4/0 | DD+0 | 9.654 | 38.616 | 308.928 | Tower Weight HT: 6.958; Tower Weight MS: 1.055; Tower Weight BnA: 0.4; Tower Weight Total: 8.413; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 89.9 |  | 1287.27 | 193.64 |  |  | 1.571 | C | 2026-03-01 | 2026-03-02 | 2026-03-06 | 2026-03-08 | Yash Infra | C | CP |  |  |  | C | 2026-03-16 | 2026-03-19 | Tokhan Mahto |  | C
328.09
11 | 4/1 | GANTRY UC(+2) | 10.82 | 43.28 | 346.24 | Tower Weight HT: 7.986; Tower Weight MS: 1.382; Tower Weight BnA: 0.449; Tower Weight Total: 9.817; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 89.9 |  | 1287.27 | 193.64 |  |  | 1.571 | C |  |  | 2026-03-03 | 2026-03-16 | Yash Infra | C | CP |  |  |  | C | 2026-03-20 | 2026-03-22 | Tokhan Mahto |  | C
40
12 | 4/2 | GANTRY UC(+2) |  |  | 54 | Tower Weight MS: 4.106; Tower Weight BnA: 0.23; Tower Weight Total: 4.336; Stub Weight MS: 0.339; Stub Weight BnA: 0.006; Stub Weight Total: 0.345 | DFR | 315 | 4.1 | 42 | 46.1 | [6 empty] | 3.95 | C |  |  | 19/2/2026 | 2026-03-17 | Yash Infra | C | CP |  |  |  | C | 2026-03-22 | 2026-03-23 | Tokhan Mahto |  | C
57.415
13 | 5/0 | DD+0 |  |  | 54 | Tower Weight MS: 4.106; Tower Weight BnA: 0.23; Tower Weight Total: 4.336; Stub Weight MS: 0.339; Stub Weight BnA: 0.006; Stub Weight Total: 0.345 | DFR | 315 | 4.1 | 42 | 46.1 | [6 empty] | 3.95 | C | 2026-01-28 | 2026-01-29 | 2026-02-03 | 2026-02-05 | Yash Infra | C | CP |  |  |  | C | 2026-03-14 | 2026-03-16 | Jyoti Construction |  | C
38.566
14 | 6/0 | DD+3 | 9.654 | 38.616 | 308.928 | Tower Weight HT: 6.958; Tower Weight MS: 1.055; Tower Weight BnA: 0.4; Tower Weight Total: 8.413; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 89.9 |  | 1287.27 | 193.64 |  |  | 1.571 | C | 2026-01-30 | 2/2/22026 | 2026-02-05 | 2/8/206 | Shree Shyam Construction | C | CP |  |  |  | C | 2026-02-17 | 2026-02-19 | Suman |  | C
182.043
15 | 6/1 | DA+6 | 9.654 | 38.616 | 308.928 | Tower Weight HT: 6.958; Tower Weight MS: 1.055; Tower Weight BnA: 0.4; Tower Weight Total: 8.413; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 89.9 |  | 1287.27 | 193.64 |  |  | 1.571 | C | 2026-01-23 | 2025-01-24 | 2026-01-28 | 2026-01-30 | Yash Infra | C | CP |  |  |  | C | 2026-02-09 | 2026-02-11 | Suman |  | C
204.148
16 | 6/2 | DA+6 | 9.654 | 38.616 | 308.928 | Tower Weight HT: 6.958; Tower Weight MS: 1.055; Tower Weight BnA: 0.4; Tower Weight Total: 8.413; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 89.9 |  | 1287.27 | 193.64 |  |  | 1.571 | C | 2026-01-21 | 2026-01-23 | 2026-01-25 | 2026-01-27 | Shree Shyam Construction | C | CP |  |  |  | C | 2026-03-16 | 2026-03-18 | Jyoti Construction |  | C
254
17 | 6/3 | DA+0 | 6.992 | 27.968 | 223.744 | Tower Weight HT: 2.777; Tower Weight MS: 1.897; Tower Weight BnA: 0.288; Tower Weight Total: 4.962; Stub Weight HT: 0.271; Stub Weight BnA: 0.007; Stub Weight Total: 0.278 | WFR | 41.44 | 0.8 | 7.73 | 8.53 | 73.75 | 235.38 |  | 201.4 |  |  | 0.51 | C | 2026-01-10 | 2026-01-16 | 1/16/206 | 2026-01-31 | Shree Shyam Construction | C | CP |  |  |  | C | 2026-02-14 | 2026-02-16 | Suman |  | C
294
18 | 6/4 | DA+3 | 6.992 | 27.968 | 223.744 | Tower Weight HT: 2.777; Tower Weight MS: 1.897; Tower Weight BnA: 0.288; Tower Weight Total: 4.962; Stub Weight HT: 0.271; Stub Weight BnA: 0.007; Stub Weight Total: 0.278 | DFR | 41.44 | 0.8 | 7.73 | 8.53 | 73.75 | 235.38 |  | 201.4 |  |  | 0.51 | C | 2026-03-08 | 2026-03-11 | 2026-03-13 | 2026-03-14 | Yash Infra | C | CP |  |  |  | C | 2026-03-18 | 2026-03-20 | Jyoti Construction |  | C
249.82
19 | 7/0 | DD+0 | 10.82 | 43.28 | 346.24 | Tower Weight HT: 7.986; Tower Weight MS: 1.382; Tower Weight BnA: 0.449; Tower Weight Total: 9.817; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 89.9 |  | 1287.27 | 193.64 |  |  | 1.571 | C | 2026-01-19 | 2026-01-20 | 2026-01-23 | 2026-01-25 | Yash Infra | C | CP |  |  |  | C | 2026-02-06 | 2026-02-08 | Suman |  | C
329.66
20 | 8/0 | DD+3 | 10.82 | 43.28 | 346.24 | Tower Weight HT: 7.986; Tower Weight MS: 1.382; Tower Weight BnA: 0.449; Tower Weight Total: 9.817; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 89.9 |  | 1287.27 | 193.64 |  |  | 1.571 | C | 2026-01-11 | 2026-01-13 | 2026-01-14 | 2026-01-21 | Yash Infra | C | CP |  |  |  | C | 2026-02-01 | 2026-02-03 | Suman |  | C
170
21 | 9/0 | DD+3 | 7.622 | 30.488 | 243.904 | Tower Weight HT: 3.346; Tower Weight MS: 2.056; Tower Weight BnA: 0.305; Tower Weight Total: 5.707; Stub Weight HT: 0.271; Stub Weight BnA: 0.007; Stub Weight Total: 0.278 | WFR | 41.44 | 0.8 | 7.73 | 8.53 | 73.75 | 235.38 |  | 201.4 |  |  | 0.51 | C | 2026-01-14 | 2026-01-16 | 2026-01-18 | 2026-01-21 | Yash Infra | C | CP |  |  |  | C | 2026-02-04 | 2026-02-06 | Suman |  | C
312
22 | 10/0 | DD+6 | 11.987 | 47.948 | 383.584 | 9.926 | 1.391 | 0.498 | 11.815 | 0.532 |  | 0.011 | 0.543 | 3 | 3 | 3 | 3 |  | SFR | 230.76 | 3.77 | 38.65 | 42.42 | 184.2 | 1264.59 |  |  | 832.39 |  | 2.281 | C | 2025-11-27 | 2025-12-01 | 2025-12-05 | 2025-12-13 | Krishna Construction | C | CP |  |  |  | C | 28/12/25 | 30/12/25 | Suman |  | C
215.13
23 | 11/0 | DD+6 | 11.987 | 47.948 | 383.584 | 9.926 | 1.391 | 0.498 | 11.815 | 0.532 |  | 0.011 | 0.543 | 3 | 3 | 3 | 3 |  | WFR | 230.76 | 3.77 | 38.65 | 42.42 | 184.2 | 1264.59 |  |  | 832.39 |  | 2.281 | C | 2025-12-07 | 2025-12-10 | 2025-12-12 | 2025-12-16 | Krishna Construction | C | CP |  |  |  | C | 2026-01-11 | 2026-01-17 | Suman |  | C
316.15
24 | 12/0 | DD+0 | 9.654 | 38.616 | 308.928 | Tower Weight HT: 6.958; Tower Weight MS: 1.055; Tower Weight BnA: 0.4; Tower Weight Total: 8.413; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | WFR | 75.36 | 1.35 | 13.06 | 14.41 | 70.93 | 900.95 |  | 96.82 | 151.27 |  | 1.22 | C | 2025-12-01 | 2025-12-10 | 2025-12-16 | 2025-12-17 | Krishna Construction | C | CP |  |  |  | C | 2026-01-06 | 2026-01-07 | Suman |  | C
267
25 | 12/1 | DA+3 | 6.992 | 27.968 | 223.744 | Tower Weight HT: 2.777; Tower Weight MS: 1.897; Tower Weight BnA: 0.288; Tower Weight Total: 4.962; Stub Weight HT: 0.271; Stub Weight BnA: 0.007; Stub Weight Total: 0.278 | WFR | 41.44 | 0.8 | 7.73 | 8.53 | 73.75 | 564.37 |  | 201.4 |  |  | 0.84 | C | 2026-01-06 | 2026-01-07 | 2026-01-09 | 2026-01-10 | Yash Infra | C | CP |  |  |  | C | 2026-01-30 | 2026-01-31 | Suman |  | C
267.185
26 | 13/0 | DD+0 | 9.654 | 38.616 | 308.928 | Tower Weight HT: 6.958; Tower Weight MS: 1.055; Tower Weight BnA: 0.4; Tower Weight Total: 8.413; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 70.93 | 900.95 |  | 96.82 | 151.27 |  | 1.22 | C | 2025-12-19 | 2025-12-22 | 2025-12-24 | 2025-12-25 | Krishna Construction | C | CP |  |  |  | C | 2026-01-03 | 2026-01-05 | Suman |  | C
87.412
27 | 13/1 | GANTRY UC(+2) |  |  | 54 | Tower Weight MS: 4.106; Tower Weight BnA: 0.23; Tower Weight Total: 4.336; Stub Weight MS: 0.339; Stub Weight BnA: 0.006; Stub Weight Total: 0.345 | WFR | 315 | 4.1 | 42 | 46.1 | [6 empty] | 3.95 | C | 2025-12-25 | 2025-12-29 | 2026-01-10 | 2026-01-14 | Krishna Construction | C | CP |  |  |  | C | 2026-01-28 | 2026-01-29 | Suman |  | C
66.461
28 | 13/2 | GANTRY UC(+2) |  |  | 54 | Tower Weight MS: 4.106; Tower Weight BnA: 0.23; Tower Weight Total: 4.336; Stub Weight MS: 0.339; Stub Weight BnA: 0.006; Stub Weight Total: 0.345 | WFR | 315 | 4.1 | 42 | 46.1 | [6 empty] | 3.95 | C | 2025-12-29 | 2026-01-02 | 2026-01-03 | 2026-01-10 | Shree Shyam Construction | C | CP |  |  |  | C | 2026-01-24 | 2026-01-27 | Suman |  | C
56.381
29 | 14/0 | DD+6 | 11.987 | 47.948 | 383.584 | Tower Weight HT: 9.926; Tower Weight MS: 1.391; Tower Weight BnA: 0.498; Tower Weight Total: 11.815; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 70.93 | 900.95 |  | 96.82 | 151.27 |  | 1.22 | C | 2025-12-22 | 2025-12-24 | 2025-12-27 | 2025-12-28 | Shree Shyam Construction | C | CP |  |  |  | C | 2026-01-08 | 2026-01-10 | Suman |  | C
224.231
30 | 15/0 | DD+3 | 10.82 | 43.28 | 346.24 | Tower Weight HT: 7.986; Tower Weight MS: 1.382; Tower Weight BnA: 0.449; Tower Weight Total: 9.817; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 70.93 | 900.95 |  | 96.82 | 151.27 |  | 1.22 | C | 2026-02-01 | 2026-02-03 | 2026-02-08 | 2026-02-10 | Yash Infra | C |  |  |  |  | C | 2026-02-20 | 2026-02-24 | Suman |  | C
276
31 | 15/1 | DA+0 | 6.362 | 25.448 | 203.584 | Tower Weight HT: 2.43; Tower Weight MS: 1.641; Tower Weight BnA: 0.268; Tower Weight Total: 4.339; Stub Weight HT: 0.271; Stub Weight BnA: 0.007; Stub Weight Total: 0.278 | WFR | 41.44 | 0.8 | 7.73 | 8.53 | 73.75 | 564.37 |  | 201.4 |  |  | 0.84 | C | 2025-12-09 | 2025-12-13 | 2025-12-14 | 2025-12-16 | Yash Infra | C | CP |  |  |  | C | 31/12/25 | 2026-01-02 | Suman |  | C
244
32 | 15/2 | DA+0 | 6.362 | 25.448 | 203.584 | Tower Weight HT: 2.43; Tower Weight MS: 1.641; Tower Weight BnA: 0.268; Tower Weight Total: 4.339; Stub Weight HT: 0.271; Stub Weight BnA: 0.007; Stub Weight Total: 0.278 | DFR | 41.44 | 0.8 | 7.73 | 8.53 | 73.75 | 564.37 |  | 201.4 |  |  | 0.84 | C | 2025-12-13 | 14/12/25 | 2025-12-14 | 2025-12-15 | Krishna Construction | C | CP |  |  |  | C | 2025-12-27 | 2025-12-27 | Suman |  | C
241
33 | 15/3 | DA+0 | 6.362 | 25.448 | 203.584 | Tower Weight HT: 2.43; Tower Weight MS: 1.641; Tower Weight BnA: 0.268; Tower Weight Total: 4.339; Stub Weight HT: 0.271; Stub Weight BnA: 0.007; Stub Weight Total: 0.278 | WFR | 41.44 | 0.8 | 7.73 | 8.53 | 73.75 | 564.37 |  | 201.4 |  |  | 0.84 | C | 2025-11-26 |  | 17/12/25 | 19/12/25 | Yash Infra | C | CP |  |  |  | C | 2025-12-25 | 2025-12-26 | Suman |  | C
240.727
34 | 16/0 | DD+0 | 9.654 | 38.616 | 308.928 | Tower Weight HT: 6.958; Tower Weight MS: 1.055; Tower Weight BnA: 0.4; Tower Weight Total: 8.413; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 70.93 | 900.95 |  | 96.82 | 151.27 |  | 1.22 | C | 2025-10-16 | 2025-10-19 | 2025-10-21 | 2025-10-23 | Krishna Construction | C | CP |  |  |  | C | 2025-11-12 | 13/12/25 | Suman |  | C
48
35 | 16/1 | GANTRY UC(+2) |  |  | 54 | Tower Weight MS: 4.106; Tower Weight BnA: 0.23; Tower Weight Total: 4.336; Stub Weight MS: 0.339; Stub Weight BnA: 0.006; Stub Weight Total: 0.345 | WFR | 315 | 4.1 | 42 | 46.1 | [6 empty] | 3.95 | C | 2025-10-20 | 2025-10-23 | 2025-10-25 | 2025-10-27 | Krishna Construction | C | CP |  |  |  | C | 2025-11-14 | 2025-11-17 | Harsh vivek |  | C
36 | 16/2 | GANTRY UC(+2) |  |  | 54 | Tower Weight MS: 4.106; Tower Weight BnA: 0.23; Tower Weight Total: 4.336; Stub Weight MS: 0.339; Stub Weight BnA: 0.006; Stub Weight Total: 0.345 | WFR | 315 | 4.1 | 42 | 46.1 | [6 empty] | 3.95 | C | 2025-11-08 | 2025-11-10 | 2025-11-13 | 2025-11-15 | Krishna Construction | C | CP |  |  |  | C | 2025-11-17 | 2025-11-20 | Harsh vivek |  | C
48.938
37 | 17/0 | DD+0 | 9.654 | 38.616 | 308.928 | Tower Weight HT: 6.958; Tower Weight MS: 1.055; Tower Weight BnA: 0.4; Tower Weight Total: 8.413; Stub Weight HT: 0.532; Stub Weight BnA: 0.011; Stub Weight Total: 0.543 | DFR | 75.36 | 1.35 | 13.06 | 14.41 | 70.93 | 900.95 |  | 96.82 | 151.27 |  | 1.22 | C | 2025-07-04 | 2025-07-06 | 2025-07-08 | 2025-07-10 | Viki Entp | C | CP | 2025-07-15 | 2025-07-15 | Viki Entp | C | 2025-08-28 | 2025-08-31 | Suman |  | C
165.147
38 | 18/0 | DD AUX | 9.654 | 38.616 | 308.928 | Tower Weight HT: 9.913; Tower Weight MS: 0.874; Tower Weight BnA: 0.73; Tower Weight Total: 11.517; Stub Weight HT: 0.845; Stub Weight BnA: 0.009; Stub Weight Total: 0.854 | WFR | 315 | 4.1 | 42 | 46.1 | [6 empty] | 3.95 | C | 2025-10-31 | 2025-11-03 | 2025-11-05 | 2025-11-07 | Krishna Construction | C | CP |  |  |  | C | 15/12/25 | 17/12/2025 | Suman |  | C
39.999
[5 empty] | 8944 | Span Length(m) m: 6.3703 | Completed | [11 empty] | 34 | [5 empty] | 33 |  |  |  |  | 29 |  |  |  |  | 29
[6 empty] | Stub Weight MS: 15 | [5 empty] | 2.3729 | 11.1339 | 14.16 | 4.3222 | 2.5724 | 0 | 62.213
42.952
Formulas:
DOC = [Excavation]+3
DOC = [Concreting]-2
Excavation = [DOC]-3
DOS = [DOC]-3
DOS = [DOC]
Concreting = [DOC]-2

## Progress-220kV
[24 empty] | 280.916 | 2556.335 | 2837.251 | 19254.0806 | 850780.47 | 16158.37 | 75630.58 | 33623.1 | 34567.35 | 14833.6 | 3104.4 | 177917.4 | 177.8274
Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc
Progress of 220kV Line
220 KV D/C Neemuch - TS | [6 empty] | RC Portion |  |  |  | Tower Weight |  |  |  |  | Stub Weight | [5 empty] | Foundation | [22 empty] | Earthing |  |  |  |  | Erection | [5 empty] | Tack-Welding |  |  |  |  | Remarks | Remarks
[15 empty] | 1367.3216 |  |  | 72.173 |  |  | 64047.149 |  | 17952.97 | 280.916 | 2556.335 | 2837.251 | 19254.0806 | [8 empty] | 179.1897 | 0 | [7 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0
Sl. No. | LOC NO | Tower Type |  |  |  |  | A | B | C | D | HT | MS | pack Washar | BnA | Total Tower Weight | HT | BnA | Total Stub Weight | Deviation of Angle | State | Span Length(m) | Classification | Excavation Volume (m3) | Concreting Volume |  |  | Cement Required |  | Total Steel (Kgs) per Tower | [7 empty] | Fnd Status (C/WIP) | Manual Checklist | JMC | Excavation |  | Concreting |  | Sub-Contractor Name | Earthing Status C/WIP | Earthing Type | DOS | DOC | S/C | Erection Status C/WIP | Manual Checklist | JMC | DOS | DOC | S/C | Status C/WIP | DOS | DOC | NB qty | Sub-Contractor Name
|  |  | B2B | B2B x 4 | Barbed Wire | RC Portion |  |  |  |  | MT | MT | MT | MT | MT | MT | MT | MT | DMS |  | m |  |  | M10 (1:3:6) (m3) | M20 (1:1.5:3) (m3) | Total | nos of bags | in kg | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm | Total Steel (Kgs) | Total Steel (MT) |  |  |  | DOS | DOC | DOS | 9
0 | GANTRY | GANTRY | [12 empty] | 13 | [13 empty] | 70.93 | 1040.06 |  | 98.08 | 153.24 |  | 1362.31 | 1.3623
47
1 | 0/0 | DD+0 | 9.654 | 38.616 | 308.928 | [5 empty] | 4.807 | 4.016 | 0.007 | 0.431 | 9.261 | 0.557 | 0.01 | 0.567 | 16° 50' 9"RT | RJ |  |  | 220.64 | 3.61 | 27.92 | 31.53 | 241.0636 | 12053.18 | 77.93 |  | 1601.75 | 96.72 | 151.11 |  | 1927.51 | 1.9275 | C | D | D | 2025-02-15 | 2025-02-16 | 2025-02-18 | 2025-02-20 | Ram Singh | C | CP | 2025-03-21 | 2025-03-21 | Ram Singh-1 | C | EE | D | 2025-04-07 | 2025-04-09 | Ramesh Kumar | C | 2025-06-16 | 2025-06-16 | 1202 | Asit Baran Pal
[21 empty] | 196 | WFR
2 | 0/1 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 121.84 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.803 | C | D | D | 2025-02-05 | 2025-02-07 | 2025-02-08 | 2025-02-09 | Ram Singh | C | CP | 2025-02-21 | 2025-02-21 | Ram Singh-1 | C | EE | D | 2025-04-02 | 2025-04-04 | Ramesh Kumar | C | 2025-06-16 | 2025-06-16 | 1330 | Asit Baran Pal
[21 empty] | 196.743 | DFR
3 | 1/0 | DC+0 | 7.708 | 30.832 | 246.656 | [5 empty] | 4.057 | 2.48 | 0.006 | 0.365 | 6.908 | 0.436 | 0.01 | 0.446 | 15° 52' 12"RT | RJ |  |  | 75.36 | 1.35 | 12.85 | 14.2 | 109.565 | 5478.25 | 81.82 | 599.6 |  | 201.4 |  |  | 882.82 | 0.88282 | C | D | D | 2025-03-20 | 2025-03-23 | 2025-03-25 | 2025-03-27 | Ram Singh | C | CP | 2025-02-21 | 2025-02-21 | Ram Singh-1 | C | EE SUB | D | 2025-04-11 | 2025-04-13 | Ramesh Kumar | C | 2025-06-16 | 2025-06-16 | 1001 | Asit Baran Pal
[21 empty] | 334 | DFR
4 | 1/1 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 121.84 | 0.88 | 8.12 | 9 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.803 | C | D | D | 2025-02-18 | 2025-02-20 | 2025-02-21 | 2025-02-23 | Ram Singh | C | Pipe | 2025-02-21 | 2025-02-21 | Ram Singh-1 | C | EE | D | 2025-03-31 | 2025-04-02 | Ramesh Kumar | C | 2025-06-17 | 2025-06-17 | 980 | Asit Baran Pal
[21 empty] | 319 | Sandy Dry
5 | 1/2 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | Ram Singh | C | CP | 2025-02-21 | 2025-02-21 | Ram Singh-1 | C | EE SUB | D | 2025-03-29 | 2025-03-31 | Ramesh Kumar | C | 2025-06-17 | 2025-06-17 | 1330 | Asit Baran Pal
[21 empty] | 384.318 | DFR
6 | 1A/0 | DC+3 | 8.626 | 34.504 | 276.032 | [5 empty] | 4.538 | 3.229 | 0.0064 | 0.429 | 8.2024 | 0.436 | 0.01 | 0.446 | 18° 59' 57"LT | RJ |  |  | 75.36 | 1.35 | 12.85 | 14.2 | 109.565 | 5478.25 | 81.82 | 599.6 |  | 201.4 |  |  | 882.82 | 0.88282 | C | D | D | 2025-02-10 | 2025-02-13 | 2025-02-15 | 2025-02-17 | Ram Singh | C | CP | 2025-03-17 | 2025-03-17 | Ram Singh-1 | C | EE SUB | D | 2025-04-21 | 2025-04-23 | Ramesh Kumar | C | 2025-06-19 | 2025-06-19 | 1433 | Asit Baran Pal
[21 empty] | 329 | DFR
7 | 1A/1 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2025-01-31 | 2025-02-02 | 2025-02-03 | 2025-02-05 | Ram Singh-1 | C | CP | 2025-02-21 | 2025-02-21 | Ram Singh-1 | C | EE | D | 2025-04-04 | 2025-04-06 | Ramesh Kumar | C | 2025-06-19 | 2025-06-19 | 1330 | Asit Baran Pal
[21 empty] | 280 | DFR
8 | 1A/2 | DC+0 | 7.708 | 30.832 | 246.656 | [5 empty] | 4.057 | 2.48 | 0.006 | 0.365 | 6.908 | 0.436 | 0.01 | 0.446 |  | RJ |  |  | 148.8 | 2.51 | 19.47 | 21.98 | 168.0726 | 8403.63 | 70.93 | 914.33 |  | 98.08 | 153.24 |  | 1236.58 | 1.2366 | C | D | D | 2025-01-24 | 2025-01-26 | 2025-01-31 | 2025-02-02 | Ram Singh-1 | C | CP | 2025-03-17 | 2025-03-17 | Ram Singh-1 | C | EE SUB | D | 2025-04-14 | 2025-04-16 | Ramesh Kumar | C | 2025-06-22 | 2025-06-22 | 1001 | Asit Baran Pal
[21 empty] | 232.098 | WFR
9 | 1B/0 | DD+3 | 10.82 | 43.28 | 346.24 | [5 empty] | 5.492 | 5.097 | 0.0074 | 0.502 | 11.0984 | 0.557 | 0.01 | 0.567 | 57° 18' 17"LT | RJ |  |  | 220.64 | 3.61 | 27.92 | 31.53 | 241.0636 | 12053.18 | 77.93 |  | 1601.75 | 96.72 | 151.11 |  | 1927.51 | 1.9275 | C | D | D | 2025-03-01 | 2025-03-03 | 2025-03-04 | 2025-03-05 | Ram Singh-1 | C | CP | 2025-03-17 | 2025-03-17 | Ram Singh-1 | C | EE | D | 2025-04-25 | 2025-04-27 | Ramesh Kumar | C | 2025-06-22 | 2025-06-22 | 1552 | Asit Baran Pal
[21 empty] | 237.783 | WFR
10 | 1C/0 | DD+9 | 13.258 | 53.032 | 424.256 | [5 empty] | 6.059 | 5.874 | 0.0077 | 0.563 | 12.5037 | 0.557 | 0.01 | 0.567 | 44° 32' 20"RT | RJ |  |  | 119.36 | 2.05 | 18.37 | 20.42 | 157.1642 | 7858.21 | 89.9 |  | 1115.34 | 198.68 |  |  | 1403.92 | 1.4039 | C |  |  | 2026-02-04 | 2026-02-21 |  | 2026-02-24 | Yash Infra | C | CP |  |  |  | C |  |  | 2026-03-20 | 2026-03-25 | Jyoti Construction |  |  |  | 2008
[21 empty] | 334 | WFR
11 | 1C/1 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2025-02-19 | 2025-02-21 | 2025-02-23 | 2025-02-25 | Shree Shyam | C | Pipe | 2025-03-04 | 2025-03-04 | Ram Singh-1 | C | EE | D | 2025-05-17 | 2025-05-19 | Shree Karni Entp | C | 2025-06-22 | 2025-06-22 | 1545 | Asit Baran Pal
[21 empty] | 341.209 | Sandy Wet
12 | 1D/0 | DC+0 | 7.708 | 30.832 | 246.656 | [5 empty] | 4.057 | 2.48 | 0.006 | 0.365 | 6.908 | 0.436 | 0.01 | 0.446 | 28° 26' 27"RT | RJ |  |  | 229.64 | 2.81 | 21.11 | 23.92 | 182.623 | 9131.15 | 70.93 | 1040.06 |  | 98.08 | 153.24 |  | 1362.31 | 1.3623 | C | EG | D | 2025-01-22 | 2025-01-27 | 2025-01-29 | 2025-01-31 | Ram Singh-1 | C | Pipe | 2025-02-15 | 2025-02-15 | Ram Singh-1 | C | EE | D | 2025-03-29 | 2025-03-30 | Ramesh Kumar | C | 2025-06-23 | 2025-06-23 | 1001 | Asit Baran Pal
[21 empty] | 306.001 | Sandy Wet
13 | 1D/1 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2025-02-16 | 2025-02-18 | 2025-02-20 | 2025-02-22 | Shree Shyam | C | Pipe | 2025-02-15 | 2025-02-15 | Ram Singh-1 | C | EE | D | 2025-03-27 | 2025-03-28 | Ramesh Kumar | C | 2025-06-23 | 2025-06-23 | 980 | Asit Baran Pal
[21 empty] | 393.92 | Sandy Wet
14 | 1E/0 | DD+6 | 11.987 | 47.948 | 383.584 | [5 empty] | 5.904 | 5.541 | 0.0079 | 0.535 | 11.9879 | 0.557 | 0.01 | 0.567 | 42° 49' 3"RT | RJ |  |  | 220.64 | 3.61 | 27.92 | 31.53 | 241.0636 | 12053.18 | 77.93 |  | 1601.75 | 96.72 | 151.11 |  | 1927.51 | 1.9275 | C | D | D | 2025-03-15 | 2025-03-17 | 2025-03-19 | 2025-03-22 | Shree Shyam | C | CP | 2025-01-04 | 2025-01-04 | Ram Singh-1 | C | EE | D | 2025-05-25 | 2025-05-27 | Dudhnath Kumar | C | 2025-06-29 | 2025-06-29 | 1750 | Asit Baran Pal
[21 empty] | 356.664 | WFR
15 | 2/0 | DC+6 | 9.544 | 38.176 | 305.408 | [5 empty] | 4.938 | 3.609 | 0.0063 | 0.424 | 8.9773 | 0.436 | 0.01 | 0.446 | 27° 13' 43"RT | RJ |  |  | 184.48 | 2.22 | 17.65 | 19.87 |  |  | 70.93 | 848.79 |  | 98.08 | 153.24 |  | 1171.04 | 0.88282 | C | D | D | 2025-01-22 | 2025-01-24 | 2025-01-31 | 2025-02-02 | Shree Shyam | C | Pipe | 2025-02-15 | 2025-02-15 | Ram Singh-1 | C | EE SUB | D | 2025-04-19 | 2025-04-21 | Ramesh Kumar | C | 2025-06-23 | 2025-06-23 | 1657 | Asit Baran Pal
[21 empty] | 174.205 | WET
16 | 3/0 | DD+3 | 10.82 | 43.28 | 346.24 | [5 empty] | 5.492 | 5.097 | 0.0078 | 0.502 | 11.0988 | 0.557 | 0.01 | 0.567 | 49° 56' 13"RT | RJ |  |  | 268.58 | 3.33 | 26.1 | 29.43 | 225.1512 | 11257.56 | 77.93 |  | 1484.97 | 96.72 | 151.11 |  | 1810.73 | 1.8107 | C | D | D | 2025-02-12 | 2025-02-14 | 2025-02-16 | 2025-02-18 | Shree Shyam | C | Pipe | 2025-02-15 | 2025-02-15 | Ram Singh-1 | C | EE SUB | D | 2025-05-01 | 2025-05-03 | Ramesh Kumar | C | 2025-05-25 | 2025-05-25 | 1552 | Asit Baran Pal
[21 empty] | 229.73 | WET
17 | 4/0 | DB+9 | 10.468 | 41.872 | 334.976 | [5 empty] | 4.351 | 4.222 | 0.005 | 0.321 | 8.899 | 0.363 | 0.006 | 0.369 | 7° 56' 47"LT | RJ |  |  | 103.6 | 1.8 | 13.84 | 15.64 |  |  | 70.93 | 613.55 |  | 99.34 | 155.21 |  | 939.03 | 0.69466 | C | D | D | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-05 | Shree Shyam | C | CP | 2025-01-04 | 2025-01-04 | Ram Singh-1 | C | EE SUB | D | 2025-05-28 | 2025-05-30 | Ramesh Kumar | C | 2025-05-25 | 2025-05-25 | 2144 | Asit Baran Pal
[21 empty] | 391 | WFR
18 | 4/1 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 121.84 | 1.4 | 10.63 | 12.03 | 91.8938 | 4594.69 | 63.93 | 481.99 |  | 100.6 | 157.18 |  | 803.7 | 0.8037 | C | D | D | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-24 | Shree Shyam | C | Pipe | 2025-02-15 | 2025-02-15 | Ram Singh-1 | C | EE | D | 2025-03-26 | 2025-03-26 | Ramesh Kumar | C | 2025-06-10 | 2025-06-10 | 1545 | Asit Baran Pal
[21 empty] | 328 | WET
19 | 4/2 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 121.84 | 1.4 | 10.63 | 12.03 | 91.8938 | 4594.69 | 63.93 | 481.99 |  | 100.6 | 157.18 |  | 803.7 | 0.8037 | C | D | D | 2025-01-09 | 2025-01-12 | 2025-01-16 | 2025-01-18 | Shree Shyam | C | Pipe | 2025-02-15 | 2025-02-15 | Ram Singh-1 | C | EE | D | 2025-03-21 | 2025-03-23 | Ramesh Kumar | C | 2025-06-10 | 2025-06-10 | 1330 | Asit Baran Pal
[21 empty] | 333 | WET
20 | 4/3 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 121.84 | 1.4 | 10.63 | 12.03 | 91.8938 | 4594.69 | 63.93 | 481.99 |  | 100.6 | 157.18 |  | 803.7 | 0.8037 | C | D | D | 2025-01-09 | 2025-01-10 | 2025-01-12 | 2025-01-14 | Shree Shyam | C | Pipe | 2025-02-15 | 2025-02-15 | Ram Singh-1 | C | EE | D | 2025-03-18 | 2025-03-20 | Ramesh Kumar | C | 2025-06-13 | 2025-06-13 | 1545 | Asit Baran Pal
[21 empty] | 349.999 | WET
21 | 4/4 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 0.88 | 8.12 | 9 | 69.3544 | 3467.72 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2025-01-03 | 2025-01-04 | 2025-01-06 | 2025-01-08 | Ram Singh-1 | C | Pipe | 2025-02-15 | 2025-02-15 | Ram Singh-1 | C | EE | D | 2025-03-20 | 2025-03-22 | Ramesh Kumar | C | 2025-06-16 | 2025-06-16 | 1330 | Asit Baran Pal
[21 empty] | 331.001 | Sandy Dry
22 | 4/5 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | D | D | 2025-01-15 | 2025-01-16 | 2025-01-18 | 2025-01-19 | Ram Singh-1 | C | CP | 2025-02-10 | 2025-02-10 | Shree shyam | C | EE SUB (Rejected due to step bolt missing) | D | 2025-03-23 | 2025-03-25 | Ramesh Kumar | C | 2025-06-20 | 2025-06-20 | 1252 | Asit Baran Pal
[21 empty] | 349 | DFR
23 | 4/6 | DB+9 | 10.468 | 41.872 | 334.976 | [5 empty] | 4.351 | 4.222 | 0.005 | 0.321 | 8.899 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | D | D | 2025-01-10 | 2025-01-11 | 2025-01-13 | 2025-01-14 | Ram Singh-1 | C | CP | 2025-02-10 | 2025-02-10 | Shree shyam | C | EE SUB (Rejected due to nut bolt missing) | D | 2025-03-09 | 2025-03-10 | Ramesh Kumar | C | 2025-07-02 | 2025-07-02 | 2144 | Asit Baran Pal | Tower Strengthening check is required
[21 empty] | 360 | DFR
24 | 4/7 | DB+9 | 10.468 | 41.872 | 334.976 | 1 | 2 | 2 | 2 | 2 | 4.351 | 4.222 | 0.005 | 0.321 | 8.899 | 0.428 | 0.011 | 0.439 |  | RJ |  |  | 103.6 | 0.97 | 14.75 | 15.72 |  |  | 130.54 | 602.37 |  |  | 725.9 |  | 1458.81 | 1.4588 | C |  |  | 2025-09-15 | 2025-09-19 | 2025-09-22 | 2025-09-26 | Vinod | C | CP |  |  |  | C |  |  | 2026-01-19 | 2026-01-23 | Ramesh Kumar |  |  |  | 2144 |  | Tower Strengthening check is required |  | got
[21 empty] | 460 | DFR
25 | 4/8 | DB+9 | 10.468 | 41.872 | 334.976 | [5 empty] | 4.351 | 4.222 | 0.005 | 0.321 | 8.899 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C |  |  | 2025-08-28 | 2025-08-30 | 2025-09-01 | 2025-09-03 | Shree shyam | C | CP | 2025-09-05 | 2025-09-05 | Shree shyam | C |  |  | 2025-12-22 | 2025-12-24 | Ramesh Kumar |  |  |  | 2144
[21 empty] | 230 | DFR
26 | 4/9 | DB+6 | 9.549 | 38.196 | 305.568 | [5 empty] | 4.144 | 3.695 | 0.0047 | 0.298 | 8.1417 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | EE | D | 2025-01-28 | 2025-01-29 | 2025-01-29 | 2025-01-30 | Shree shyam | C | CP | 2025-02-10 | 2025-02-10 | Shree shyam | C | EE | D | 2025-03-15 | 2025-03-17 | Ramesh Kumar | C | 2025-07-08 | 2025-07-08 | 1812 | Asit Baran Pal | Tower Strengthening check is required |  | got
[21 empty] | 371.51 | DFR
27 | 4/10 | DB+6 | 9.549 | 38.196 | 305.568 | [5 empty] | 4.144 | 3.695 | 0.0047 | 0.298 | 8.1417 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C |  |  | 2025-01-31 | 2025-02-04 | 2025-02-06 | 2025-02-08 | Shree shyam | C | CP | 2025-03-05 | 2025-03-05 | Shree shyam | C | EE | D | 2025-03-11 | 2025-03-13 | Ramesh Kumar | C | 2025-07-09 | 2025-07-09 | 1812 | Asit Baran Pal
[21 empty] | 332.471 | DFR
28 | 4/11 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | D | D | 2024-12-30 | 2025-01-06 | 2025-01-10 | 2025-01-12 | Shree shyam | C | CP | 2025-03-05 | 2025-03-05 | Shree shyam | C | EE SUB | D | 2025-03-11 | 2025-03-12 | Dudhnath Kumar | C | 2025-07-10 | 2025-07-10 | 1252 | Asit Baran Pal
[21 empty] | 424.43 | DFR
29 | 4/12 | DA+9 | 8.252 | 33.008 | 264.064 | 1 | 3 | 3 | 3 | 3 | 3.078 | 3.659 | 0.0027 | 0.266 | 7.0057 | 0.428 | 0.011 | 0.439 |  | RJ |  |  | 41.44 | 0.8 | 15.93 | 16.73 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2025-05-07 | 2025-05-09 | 2025-05-11 | 2025-05-13 | Shree shyam | C | CP | 2025-05-20 | 2025-05-20 | Shree shyam | C | EE SUB (Backfilling not proper as per TC) | D | 2025-06-04 | 2025-06-04 | Dudhnath Kumar | C | 2025-07-11 | 2025-07-11 | 1588 | Asit Baran Pal
[21 empty] | 326.731 | DFR
30 | 4/13 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-13 | 2024-12-16 | 2024-12-18 | 2024-12-20 | Shree shyam | C | CP | 2025-02-20 | 2025-02-20 | Shree shyam | C | EE SUB (Backfilling Observation must be cleared in TC) | D | 2025-03-13 | 2025-03-16 | Dudhnath Kumar | C | 2025-07-12 | 2025-07-12 | 1545 | Asit Baran Pal
[21 empty] | 291.857 | DFR
31 | 4/14 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-12 | 2024-12-15 | 2024-12-17 | 2024-12-19 | Shree shyam | C | CP | 2025-01-20 | 2025-01-20 | Shree shyam | C | EE SUB | D | 2025-03-16 | 2025-03-18 | Dudhnath Kumar | C | 2025-07-13 | 2025-07-13 | 980 | Asit Baran Pal
[21 empty] | 292.001 | DFR
32 | 4/15 | DB+3 | 8.63 | 34.52 | 276.16 | [5 empty] | 3.867 | 3.306 | 0.005 | 0.276 | 7.454 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | D | D | 2024-12-18 | 2024-12-21 | 2024-12-23 | 2024-12-25 | Shree shyam | C | CP | 2025-01-20 | 2025-01-20 | Shree shyam | C | EE SUB | D | 2025-03-23 | 2025-03-25 | Dudhnath Kumar | C | 2025-07-14 | 2025-07-14 | 1560 | Asit Baran Pal
[21 empty] | 415 | DFR
33 | 4/16 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | D | D | 2025-01-20 | 2025-02-08 | 2025-02-10 | 2025-02-12 | Ram Singh | C | CP | 2025-02-20 | 2025-02-20 | Shree shyam | C | Form need to be fill up | D | 2025-03-21 | 2025-03-23 | Dudhnath Kumar | C | 2025-07-15 | 2025-07-15 | 1252 | Asit Baran Pal | Tower Strengthening check is required |  | got
[21 empty] | 237 | DFR
34 | 4/17 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | D | D | 2025-02-09 | 2025-02-12 | 2025-02-14 | 2025-02-15 | Ram Singh | C | CP | 2025-02-20 | 2025-02-20 | Shree shyam | C | EE SUB | D | 2025-03-19 | 2025-03-20 | Dudhnath Kumar | C | 2025-07-16 | 2025-07-16 | 1252 | Asit Baran Pal | Tower Strengthening check is required |  | got
[21 empty] | 188.454 | DFR
35 | 5/0 | DB+6 | 9.549 | 38.196 | 305.568 | 1 |  |  | 4 | 2 | 4.144 | 3.695 | 0.0047 | 0.298 | 8.1417 | 0.363 | 0.006 | 0.369 | 11° 47' 59"RT | RJ |  |  | 55.22 | 1.028 | 14.568 | 15.596 |  |  | 126.88 | 414.8 |  | 332.12 | 139.71 |  | 1013.51 | 1.0135 | C | EE | D | 2025-03-22 | 2025-03-24 | 2025-03-26 | 2025-03-28 | Shree shyam | C | CP | 2025-01-04 | 2025-01-04 | Ram Singh-1 | C | EE SUB (All CTQ forms not submitted yet. Also updated TC required which is not given) | Fab | 2025-07-14 | 2025-07-16 | Dudhnath Kumar | C | 2025-08-26 | 2025-08-26 | 1812 | Asit Baran Pal | Tower Strengthening check is required |  | got
[21 empty] | 383 | DFR
36 | 5/1 | DB+3 | 8.63 | 34.52 | 276.16 | [5 empty] | 3.867 | 3.306 | 0.005 | 0.276 | 7.454 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | EE | D | 2025-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-05 | Shree shyam | C | CP | 2024-12-18 | 2024-12-18 | Viki Enterprises | C | EE | D | 2025-04-12 | 2025-04-13 | Dudhnath Kumar | C | 2025-08-26 | 2025-08-26 | 1560 | Asit Baran Pal
[21 empty] | 311 | DFR
37 | 5/2 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-11-30 | 2024-12-02 | 2024-12-04 | 2024-12-06 | Shree shyam | C | CP | 2024-12-18 | 2024-12-18 | Viki Enterprises | C | EE SUB (Updated TC clearing backfilling point not given yet) | D | 2025-03-26 | 2025-03-28 | Dudhnath Kumar | C | 2025-08-26 | 2025-08-26 | 1545 | Asit Baran Pal
[21 empty] | 350 | DFR
38 | 5/3 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-01 | 2024-12-03 | 2024-12-05 | 2024-12-07 | Shree shyam | C | CP | 2024-12-19 | 2024-12-19 | Viki Enterprises | C | Form need to be fill up | D | 2025-03-29 | 2025-03-31 | Dudhnath Kumar | C | 2025-08-28 | 2025-08-28 | 1330 | Asit Baran Pal
[21 empty] | 291 | DFR
39 | 5A/0 | DC+0 | 7.708 | 30.832 | 246.656 | [5 empty] | 4.057 | 2.48 | 0.006 | 0.365 | 6.908 | 0.436 | 0.01 | 0.446 | 24° 44' 29"LT | RJ |  |  | 75.36 | 1.35 | 12.85 | 14.2 | 109.565 | 5478.25 | 81.82 | 599.6 |  | 201.4 |  |  | 882.82 | 0.88282 | C | D | D | 2024-12-22 | 2024-12-24 | 2024-12-27 | 2024-12-29 | Shree shyam | C | CP | 2025-02-07 | 2025-02-07 | Ram Singh-1 | C | Form need to be fill up | D | 2025-03-30 | 2025-03-30 | Dudhnath Kumar | C | 2025-08-28 | 2025-08-28 | 1001 | Asit Baran Pal | Tower Strengthening check is required
[21 empty] | 322 | DFR
40 | 5A/1 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C |  |  | 2025-09-29 | 2025-10-02 | 2025-10-05 | 2025-10-08 | Vinod | C | CP |  |  |  | C |  |  | 2025-11-23 | 2025-11-24 |  | C | 2026-01-09 | 2026-01-09 | 1252 | Jai Swami | Tower Strengthening check is required |  | got
[21 empty] | 284 | DFR
41 | 5A/2 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C |  |  | 2025-10-05 | 2025-10-08 | 2025-10-10 | 2025-10-12 | Vinod | C | CP |  |  |  | C |  |  | 2025-11-22 | 2025-11-23 |  | C | 2026-01-10 | 2026-01-10 | 1252 | Jai Swami
[21 empty] | 282.74 | DFR
42 | 5B/0 | DB+3 | 8.63 | 34.52 | 276.16 | [5 empty] | 3.867 | 3.306 | 0.005 | 0.276 | 7.454 | 0.363 | 0.006 | 0.369 | 7° 28' 45"RT | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C |  |  | 2025-10-12 | 2025-10-13 | 2025-10-15 | 2025-10-17 | Vinod | C | CP |  |  |  | C |  |  | 2025-11-21 | 2025-11-22 |  | C | 2026-01-11 | 2026-01-11 | 1560 | Jai Swami | Tower Strengthening check is required
[21 empty] | 462.06 | DFR
43 | 6/0 | DC+0 | 7.708 | 30.832 | 246.656 | 1 |  | 5 | 2 |  | 4.057 | 2.48 | 0.006 | 0.365 | 6.908 | 0.566 | 0.01 | 0.576 | 15° 37' 24"RT | RJ |  |  | 78.75 | 1.503 | 20.967 | 22.47 |  |  | 118.51 | 500.21 | 114.33 | 151.02 | 318.71 |  | 1202.78 | 1.2028 | C |  |  | 2025-11-21 | 2025-11-22 | 2025-11-24 | 2025-11-26 | Vinod | C | CP |  |  |  | C |  |  | 2025-12-18 | 2025-12-20 |  | C | 2026-01-12 | 2026-01-12 | 1001 | Jai Swami
[21 empty] | 318.04 | DFR
44 | 7/0 | DB+9 | 10.468 | 41.872 | 334.976 | [5 empty] | 4.351 | 4.222 | 0.005 | 0.321 | 8.899 | 0.363 | 0.006 | 0.369 | 23° 4' 48"RT | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | D | D | 2025-03-09 | 2025-03-11 | 2025-03-14 | 2025-03-16 | Ram Singh | C | CP | 2025-03-20 | 2025-03-20 | Ram Singh-1 | C | EE SUB | D | 2025-04-08 | 2025-04-10 | Dudhnath Kumar | C | 2025-08-09 | 2025-08-09 | 2144 | Asit Baran Pal
[21 empty] | 364 | DFR
45 | 7/1 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2025-03-04 | 2025-03-06 | 2025-03-07 | 2025-03-09 | Shree shyam | C | CP | 2025-03-20 | 2025-03-20 | Ram Singh-1 | C | EE SUB | D | 2025-04-05 | 2025-04-06 | Dudhnath Kumar | C | 2025-08-09 | 2025-08-09 | 980 | Asit Baran Pal
[21 empty] | 279 | DFR
46 | 7/2 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2025-03-09 | 2025-03-11 | 2025-03-13 | 2025-03-16 | Ram Singh | C | CP | 2025-03-20 | 2025-03-20 | Ram Singh-1 | C | Form need to be fill up | D | 2025-04-05 | 2025-04-07 | Dudhnath Kumar | C | 2025-08-09 | 2025-08-09 | 980 | Asit Baran Pal
[21 empty] | 252 | DFR
47 | 7/3 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 80.64 | 0.88 | 8.12 | 9 | 69.3544 | 3467.72 | 73.73 | 313.64 |  | 201.4 |  |  | 588.77 | 0.58877 | C | D | D | 2025-03-17 | 2025-03-19 | 2025-03-21 | 2025-03-23 | Ram Singh | C | Pipe | 2025-03-27 | 2025-03-27 | Ram Singh-1 | C |  | D | 2025-04-21 | 2025-04-23 | Dudhnath Kumar | C | 2025-08-09 | 2025-08-09 | 980 | Asit Baran Pal
[21 empty] | 252.05 | Sandy Dry
48 | 8/0 | DD+0 | 9.654 | 38.616 | 308.928 | [5 empty] | 4.807 | 4.016 | 0.007 | 0.431 | 9.261 | 0.557 | 0.01 | 0.567 | 54° 40' 18"LT | RJ |  |  | 207.52 | 2.52 | 21.09 | 23.61 |  | 7858.21 | 89.9 |  | 1287.27 | 193.64 |  |  | 1570.81 | 1.5708 | C | EG | D | 2025-05-13 | 2025-05-15 | 2025-05-16 | 2025-05-18 | Ram Singh | C | Pipe | 2025-05-21 | 2025-05-21 | Ram Singh-1 | C | EE | D | 2025-06-06 | 2025-06-08 | Dudhnath Kumar | C | 2025-08-13 | 2025-08-13 | 1202 | Asit Baran Pal
[21 empty] | 173.57 | Sandy Dry
49 | 8A/0 | DD+0 | 9.654 | 38.616 | 308.928 | [5 empty] | 4.807 | 4.016 | 0.007 | 0.431 | 9.261 | 0.557 | 0.01 | 0.567 | 38° 34' 26"RT | RJ |  |  | 268.58 | 3.33 | 26.1 | 29.43 | 225.1512 | 11257.56 | 77.93 |  | 1484.97 | 96.72 | 151.11 |  | 1810.73 | 1.8107 | C | D | D | 2024-12-26 | 2024-12-29 | 2025-01-02 | 2025-01-04 | Viki Enterprises | C | Pipe | 2025-01-03 | 2025-01-03 | Viki Enterprises | C |  | Submitted | 2025-04-28 | 2025-04-30 | Dudhnath Kumar | C | 2025-08-17 | 2025-08-17 | 1202 | Asit Baran Pal
[21 empty] | 336.5 | WET
50 | 8B/0 | DC+9 | 10.462 | 41.848 | 334.784 | [5 empty] | 5.201 | 4.146 | 0.0067 | 0.503 | 9.8567 | 0.436 | 0.01 | 0.446 | 23° 30' 1"RT | RJ |  |  | 229.64 | 2.81 | 21.11 | 23.92 | 182.623 | 9131.15 | 70.93 | 1040.06 |  | 98.08 | 153.24 |  | 1362.31 | 1.3623 | C | D | D | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-11 | Viki Enterprises | C | Pipe | 2024-12-21 | 2024-12-21 | Viki Enterprises | C |  | D | 2025-04-20 | 2025-04-22 | Dudhnath Kumar | C |  |  | 1657
[21 empty] | 365 | Sandy Wet
51 | 8B/1 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 147.88 | 1.74 | 12.26 | 14 | 106.5412 | 5327.06 | 63.93 | 558.32 |  | 100.6 | 157.18 |  | 880.03 | 0.88003 | C | D | D | 2024-12-05 | 2024-12-17 | 2024-12-18 | 2024-12-19 | Viki Enterprises | C | Pipe | 2024-12-21 | 2024-12-21 | Viki Enterprises | C |  | D | 2025-04-02 | 2025-04-03 | Dudhnath Kumar | C | 2025-08-17 | 2025-08-17 | 980 | Asit Baran Pal
[21 empty] | 280 | PS
52 | 8B/2 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 147.88 | 1.74 | 12.26 | 14 | 106.5412 | 5327.06 | 63.93 | 558.32 |  | 100.6 | 157.18 |  | 880.03 | 0.88003 | C | D | D | 2024-12-17 | 2024-12-22 | 2024-12-25 | 2024-12-27 | Viki Enterprises | C | Pipe | 2025-01-03 | 2025-01-03 | Viki Enterprises | C |  | D | 2025-04-03 | 2025-04-04 | Dudhnath Kumar | C | 2025-08-18 | 2025-08-18 | 980 | Asit Baran Pal
[21 empty] | 255.14 | PS
53 | 8C/0 | DD+0 | 9.654 | 38.616 | 308.928 | [5 empty] | 4.807 | 4.016 | 0.007 | 0.431 | 9.261 | 0.557 | 0.01 | 0.567 | 50° 17' 26"LT | RJ |  |  | 119.36 | 4.05 | 30.54 | 34.59 | 157.1642 | 7858.21 | 89.9 |  | 1115.34 | 198.68 |  |  | 1403.92 | 1.4039 | C | EG | D | 2025-05-05 | 2025-05-08 | 2025-05-10 | 2025-05-12 | Ram Singh | C | CP | 2025-05-20 | 2025-05-20 | Ram Singh | C |  | D | 2025-06-04 | 2025-06-06 | Dudhnath Kumar | C |  |  | 1202
[21 empty] | 318.76 | Sandy Wet
54 | 8D/0 | DD+0 | 9.654 | 38.616 | 308.928 | [5 empty] | 4.807 | 4.016 | 0.007 | 0.431 | 9.261 | 0.557 | 0.01 | 0.567 | 43° 40' 17"LT | RJ |  |  | 220.64 | 3.61 | 27.92 | 31.53 | 241.0636 | 12053.18 | 77.93 |  | 1601.75 | 96.72 | 151.11 |  | 1927.51 | 1.9275 | C | D | D | 2024-12-10 | 2025-01-13 | 2025-01-15 | 2025-01-16 | Viki Enterprises | C | CP | 2025-01-03 | 2025-01-03 | Viki Enterprises | C |  | Submitted | 2025-04-15 | 2025-04-17 | Dudhnath Kumar | C |  |  | 1202 | Jai Swami
[21 empty] | 403.71 | WFR
55 | 8D/0A | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 119.36 | 1.51 | 11.15 | 12.66 | 157.1642 | 7858.21 | 89.9 |  | 1115.34 | 198.68 |  |  | 1403.92 | 1.4039 | C |  |  | 2025-11-18 | 2025-11-23 |  |  | Krishna Enterprises | C |  |  |  |  | C |  |  | 2025-12-04 | 2025-12-07 |  | C |  |  | 2008 | Jai Swami
WFR
56 | 8D/1 | DD+9 | 13.258 | 53.032 | 424.256 | [5 empty] | 6.059 | 5.874 | 0.0077 | 0.563 | 12.5037 | 0.557 | 0.01 | 0.567 |  | RJ |  |  | 41.44 | 3.61 | 27.92 | 31.53 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C |  |  | 2025-11-16 | 2025-11-18 | 2025-11-20 | 2025-11-20 | Krishna Enterprises | C |  |  |  |  | C |  |  | 2025-11-27 | 2025-11-29 |  | C |  |  | 1545 | Jai Swami
[21 empty] | 302.58 | WFR
57 | 8D/2 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 1.51 | 11.15 | 12.66 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C |  |  | 2025-11-25 | 2025-12-01 | 2025-11-27 | 2025-12-03 | Krishna Enterprises | C |  |  |  |  | C |  |  | 2025-12-07 | 2025-12-08 |  | C |  |  | 1330 | Jai Swami
[21 empty] | 393.04 | WFR
58 | 8D/3 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C |  |  | 2025-09-03 | 2025-09-06 | 2025-09-08 | 2025-09-10 | Ram Singh | C | CP | 2025-09-12 | 2025-09-12 | Ram Singh | C |  |  | 2025-11-26 | 2025-11-27 | Ramesh Kumar | C |  |  | 1252 | Jai Swami
[21 empty] | 459 | DFR
59 | 8D/4 | DB+3 | 8.63 | 34.52 | 276.16 | [5 empty] | 3.867 | 3.306 | 0.005 | 0.276 | 7.454 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C |  |  | 2025-08-24 | 2025-08-26 | 2025-08-28 | 2025-08-30 | Ram Singh | C | CP | 2025-09-01 | 2025-09-01 | Ram Singh | C |  |  | 2025-11-02 | 2025-11-04 | Ramesh Kumar | C |  |  | 1560 | Jai Swami | Tower Strengthening check is required
[21 empty] | 195 | DFR
60 | 8D/5 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 102.06 | 0.97 | 9.82 | 10.79 | 91.4286 | 4571.43 | 81.82 | 427.95 |  | 198.88 |  |  | 708.65 | 0.70865 | C |  |  | 2025-08-06 | 2025-08-12 | 2025-08-15 | 2025-08-17 | Ram Singh | C | CP | 2025-08-19 | 2025-08-19 | Ram Singh | C |  |  | 2025-11-03 | 2025-11-05 | Ramesh Kumar | C |  |  | 1252 | Jai Swami
[21 empty] | 295 | DFR
61 | 8D/6 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C |  |  | 2025-08-12 | 2025-08-18 | 2025-08-21 | 2025-08-23 | Ram Singh | C | CP | 2025-08-25 | 2025-08-25 | Ram Singh | C |  |  | 2025-11-05 | 2025-11-07 | Ramesh Kumar | C |  |  | 1252 | Jai Swami
[21 empty] | 380.25 | DFR
62 | 8E/0 | DC+0 | 7.708 | 30.832 | 246.656 | 1 |  | 2 | 2 |  | 4.057 | 2.48 | 0.006 | 0.365 | 6.908 | 0.436 | 0.01 | 0.446 | 26° 29' 57"RT | MP |  |  | 80.4 | 1.43 | 15.88 | 17.31 |  |  | 121.84 | 399.08 | 214.82 | 397.78 |  |  | 1133.52 | 1.1335 | C |  |  | 2025-09-15 | 2025-09-17 | 2025-09-19 | 2025-09-21 | Ram Singh | C | CP |  |  |  | C |  |  | 2025-11-07 | 2025-11-09 | Ramesh Kumar | C |  |  | 1001 | Jai Swami | Tower Strengthening check is required
[21 empty] | 428 | DFR
63 | 8E/1 | DB+3 | 8.63 | 34.52 | 276.16 | [5 empty] | 3.867 | 3.306 | 0.005 | 0.276 | 7.454 | 0.363 | 0.006 | 0.369 |  | MP |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | EG | D | 2025-06-03 | 2025-06-05 | 2025-06-06 | 2025-06-08 | Shree shyam | C | CP | 2025-06-12 | 2025-06-12 | Shree shyam | C |  | Checling not done | 2025-06-23 | 2025-06-25 | Ramesh Kumar | C |  |  | 1560 |  | Tower Strengthening check is required
[21 empty] | 419 | DFR
64 | 8E/2 | DB+9 | 10.468 | 41.872 | 334.976 | [5 empty] | 4.351 | 4.222 | 0.005 | 0.321 | 8.899 | 0.363 | 0.006 | 0.369 |  | MP |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | D | D | 2025-01-21 | 2025-01-22 | 2025-01-25 | 2025-01-27 | Viki Enterprises | C | CP | 2025-01-05 | 2025-01-05 | Ram Singh-1 | C |  | Checling not done | 2025-06-09 | 2025-06-11 | Dudhnath Kumar | C |  |  | 2144
[21 empty] | 345 | DFR
65 | 8E/3 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | EG | D | 2025-06-01 | 2025-06-02 | 2025-06-04 | 2025-06-06 | Ram Singh-1 | C | CP | 2025-06-12 | 2025-06-12 | Ram Singh-1 | C |  | 1st stage done, need to upload in EE | 2025-06-22 | 2025-06-24 | Dudhnath Kumar | C |  |  | 1330
[21 empty] | 296 | DFR
66 | 8E/4 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | EG | D | 2025-04-20 | 2025-04-22 | 2025-04-24 | 2025-04-26 | Ram Singh-1 | C | CP | 2025-01-04 | 2025-01-04 | Ram Singh-1 | C |  | 1st stage done, need to upload in EE | 2025-06-21 | 2025-06-23 | Dudhnath Kumar | C |  |  | 980
[21 empty] | 259 | DFR
67 | 8E/5 | DB+9 | 10.468 | 41.872 | 334.976 | [5 empty] | 4.351 | 4.222 | 0.005 | 0.321 | 8.899 | 0.363 | 0.006 | 0.369 |  | MP |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | EG | D | 2025-04-19 | 2025-04-21 | 2025-04-23 | 2025-04-25 | Ram Singh-1 | C | CP | 2025-01-04 | 2025-01-04 | Ram Singh-1 | C |  | Checling not done | 2025-06-25 | 2025-06-27 | Dudhnath Kumar | C |  |  | 2144
[21 empty] | 343.87 | DFR
68 | 8E/6 | DB+9 | 10.468 | 41.872 | 334.976 | [5 empty] | 4.351 | 4.222 | 0.005 | 0.321 | 8.899 | 0.363 | 0.006 | 0.369 |  | MP |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | EG | D | 2025-05-30 | 2025-06-01 | 2025-06-03 | 2025-06-04 | Ram Singh-1 | C | CP | 2025-06-06 | 2025-06-06 | Ram Singh-1 | C |  | Checling not done | 2025-06-20 | 2025-06-22 | Ramesh Kumar | C |  |  | 2144 |  | Tower Strengthening check is required
[21 empty] | 499.13 | DFR
69 | 8E/7 | DB+0 | 7.71 | 30.84 | 246.72 | 1 | 5 | 4 |  |  | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 |  | MP |  |  | 58.8 | 1.085 | 18.73 | 19.815 |  |  | 162.25 | 420.68 |  | 255.96 | 440.49 |  | 1279.38 | 1.2794 | C |  |  | 2025-11-11 | 2025-11-13 | 2025-11-15 | 2025-11-16 | Vinod | C | CP |  |  |  | C |  |  | 2025-11-29 | 2025-12-03 | Ramesh |  |  |  | 1252 |  | Tower Strengthening check is required |  | got
[21 empty] | 434 | DFR
70 | 8E/8 | DB+9 | 10.468 | 41.872 | 334.976 | [5 empty] | 4.351 | 4.222 | 0.005 | 0.321 | 8.899 | 0.363 | 0.006 | 0.369 |  | MP |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | EG | D | 2025-05-21 | 2025-05-22 | 2025-05-24 | 2025-05-26 | Ram Singh-1 | C | CP | 2025-06-06 | 2025-06-06 | Ram Singh-1 | C |  | Checling not done | 2025-06-20 | 2025-06-22 | Dudhnath Kumar | C | 2026-01-14 | 2026-01-14 | 2144 | Jai Swami | Tower Strengthening check is required
[21 empty] | 295 | DFR
71 | 8E/9 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | EG | D | 2025-05-23 | 2025-05-25 | 2025-05-27 | 2025-05-29 | Ram Singh-1 | C | CP | 2025-06-06 | 2025-06-06 | Ram Singh-1 | C |  | Checling not done | 2025-06-17 | 2025-06-19 | Dudhnath Kumar | C |  |  | 980
[21 empty] | 326 | DFR
72 | 8E/10 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | EG | D | 2025-05-20 | 2025-05-21 | 2025-05-23 | 2025-05-25 | Ram Singh-1 | C | CP | 2025-06-06 | 2025-06-06 | Ram Singh-1 | C |  | Checling not done | 2025-06-13 | 2025-06-14 | Dudhnath Kumar | C |  |  | 1545
[21 empty] | 298 | DFR
73 | 8E/11 | DB+3 | 8.63 | 34.52 | 276.16 | [5 empty] | 3.867 | 3.306 | 0.005 | 0.276 | 7.454 | 0.363 | 0.006 | 0.369 |  | MP |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | EG | D | 2025-05-25 | 2025-05-26 | 2025-05-28 | 2025-05-30 | Ram Singh-1 | C | CP | 2025-06-06 | 2025-06-06 | Ram Singh-1 | C |  | Checling not done | 2025-06-15 | 2025-06-17 | Dudhnath Kumar | C | 2026-01-15 | 2026-01-15 | 1560 | Jai Swami | Tower Strengthening check is required
[21 empty] | 489 | DFR
74 | 8E/12 | DB+3 | 8.63 | 34.52 | 276.16 | [5 empty] | 3.867 | 3.306 | 0.005 | 0.276 | 7.454 | 0.363 | 0.006 | 0.369 |  | MP |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C |  |  | 2025-05-21 | 2025-05-23 | 2025-05-25 | 2025-05-27 | Viki Enterprice | C | CP | 2025-06-06 | 2025-06-06 | Viki Enterprice | C |  | Checling not done | 2025-07-06 | 2025-07-08 | Dudhnath Kumar | C |  |  | 1560 |  | Tower Strengthening check is required |  | got
[21 empty] | 382.48 | DFR
75 | AP-9 | DC+3 | 8.626 | 34.504 | 276.032 | [5 empty] | 4.538 | 3.229 | 0.0064 | 0.429 | 8.2024 | 0.436 | 0.01 | 0.446 | 21° 0' 5"LT | MP |  |  | 75.36 | 1.35 | 12.85 | 14.2 | 109.565 | 5478.25 | 81.82 | 599.6 |  | 201.4 |  |  | 882.82 | 0.88282 | C | EG | D | 2025-05-13 | 2025-05-14 | 2025-05-16 | 2025-05-18 | Viki Enterprice | C | CP | 2025-06-06 | 2025-06-06 | Viki Enterprice | C |  | Checling not done | 2025-07-02 | 2025-07-04 | Dudhnath Kumar | C |  |  | 1433 | Asit Baran Pal
[21 empty] | 372.4 | DFR
76 | 9/1 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | EG | D | 2025-05-12 | 2025-05-13 | 2025-05-15 | 2025-05-17 | Viki Enterprice | C | CP | 2025-05-28 | 2025-05-28 | Viki Enterprice | C |  | Checling not done | 2025-07-04 | 2025-07-06 | Dudhnath Kumar | C |  |  | 980 | Asit Baran Pal
[21 empty] | 350.02 | DFR
77 | 9/2 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | EG | D | 2025-05-16 | 2025-05-18 | 2025-05-20 | 2025-05-22 | Shree Shyam Cont | C | CP | 2025-06-06 | 2025-06-06 | Shree Shyam Cont | C |  | Checling not done | 2025-07-01 | 2025-07-03 | Ramesh Kumar | C |  |  | 1330 | Asit Baran Pal
[21 empty] | 303.57 | DFR
78 | 9/3 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | EG | D | 2025-05-30 | 2025-06-01 | 2025-06-03 | 2025-06-05 | Viki Enterprice | C | CP | 2025-06-06 | 2025-06-06 | Viki Enterprice | C |  | Checling not done | 2025-07-03 | 2025-07-05 | Ramesh Kumar | C |  |  | 980 | Asit Baran Pal
[21 empty] | 224.33 | DFR
79 | 9/4 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 |  | MP |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | EG | D | 2025-05-30 | 2025-06-01 | 2025-06-03 | 2025-06-05 | Viki Enterprice | C | CP | 2025-06-06 | 2025-06-06 | Viki Enterprice | C |  | Checling not done | 2025-07-07 | 2025-07-07 | Ramesh Kumar | C |  |  | 1252 | Asit Baran Pal | Tower Strengthening check is required
[21 empty] | 246.76 | DFR
80 | 9/5 | DB+6 | 9.549 | 38.196 | 305.568 | [5 empty] | 4.144 | 3.695 | 0.0047 | 0.298 | 8.1417 | 0.363 | 0.006 | 0.369 |  | MP |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | EG | D | 2025-05-19 | 2025-05-21 | 2025-05-23 | 2025-05-25 | Shree Shyam | C | CP | 2025-05-28 | 2025-05-28 | Shree Shyam | C |  | Fab | 2025-07-28 | 2025-07-30 | Ramesh Kumar | C |  |  | 1812 | Asit Baran Pal
[21 empty] | 418.18 | DFR
81 | 9/6 | DA+9 | 8.252 | 33.008 | 264.064 | [5 empty] | 3.078 | 3.659 | 0.0027 | 0.266 | 7.0057 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | EG | D | 2025-05-17 | 2025-05-19 | 2025-05-21 | 2025-05-23 | Shree Shyam | C | CP | 2025-05-28 | 2025-05-28 | Shree Shyam | C |  | 1st stage done, need to upload in EE | 2025-06-27 | 2025-06-29 | Dudhnath Kumar | C |  |  | 1588 | Asit Baran Pal
[21 empty] | 298.66 | DFR
82 | 9/7 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | EG | D | 2025-05-24 | 2025-05-25 | 2025-05-27 | 2025-05-29 | Shree Shyam | C | CP | 2025-06-03 | 2025-06-03 | Shree Shyam | C |  | 1st stage done, need to upload in EE | 2025-07-01 | 2025-07-01 | Dudhnath Kumar | C |  |  | 980 | Asit Baran Pal
[21 empty] | 358.67 | DFR
83 | 9/8 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-08-23 | 2024-09-01 | 2024-09-23 | 2024-09-28 | RST Construction | C | CP | 2025-01-05 | 2025-01-05 | Ram Singh-1 | C |  | D | 2025-03-13 | 2025-03-15 | Shree Ganesh Sital Enterprice | C |  |  | 980 | Asit Baran Pal
[21 empty] | 366.13 | DFR
84 | 9/9 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 85.44 | 1.51 | 11.15 | 12.66 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2024-09-12 | 2024-09-15 | 2024-10-29 | 2024-10-30 | RST Construction | C | CP | 2025-01-05 | 2025-01-05 | Ram Singh-1 | C |  | D | 2025-05-19 | 2025-05-20 | Ramesh Kumar | C |  |  | 1330 | Asit Baran Pal
[21 empty] | 255.6 | WFR
85 | AP-10 | DD+0 | 9.654 | 38.616 | 308.928 | [5 empty] | 4.807 | 4.016 | 0.007 | 0.431 | 9.261 | 0.557 | 0.01 | 0.567 | 38° 36' 12"LT | MP |  |  | 220.64 | 3.61 | 27.92 | 31.53 | 241.0636 | 12053.18 | 77.93 |  | 1601.75 | 96.72 | 151.11 |  | 1927.51 | 1.9275 | C | D | D | 2024-11-08 | 2024-11-18 | 2024-11-22 | 2024-11-26 | RST Construction | C | CP | 2025-02-18 | 2025-02-18 | Ram Singh-1 | C | EE | D | 2025-03-27 | 2025-03-29 | Shree Ganesh Sital Enterprice | C |  |  | 1202 | Asit Baran Pal
[21 empty] | 229.724 | WFR
86 | 10/1 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2025-04-13 | 2025-04-15 | 2025-04-17 | 2025-04-19 | Shree shyam | C | CP | 2025-01-04 | 2025-01-04 | Ram Singh-1 | C |  | D | 2025-05-21 | 2025-05-22 | Ramesh Kumar | C |  |  | 1330
[21 empty] | 359.356 | DFR
87 | 10/2 | DA+9 | 8.252 | 33.008 | 264.064 | [5 empty] | 3.078 | 3.659 | 0.0027 | 0.266 | 7.0057 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-11-06 | 2024-11-11 | 2024-11-13 | 2024-11-15 | RST Construction | C | CP | 2025-02-18 | 2025-02-18 | Ram Singh-1 | C |  | D | 2025-03-17 | 2025-03-19 | Shree Ganesh Sital Enterprice | C |  |  | 1588
[21 empty] | 365.874 | DFR
88 | 10/3 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-08-24 | 2024-08-27 | 2024-09-01 | 2024-09-09 | RST Construction | C | CP | 2025-02-18 | 2025-02-18 | Ram Singh-1 | C |  | D | 2025-03-11 | 2025-03-13 | Shree Ganesh Sital Enterprice | C |  |  | 980
[21 empty] | 345.784 | DFR
89 | 10/4 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 80.64 | 0.88 | 8.12 | 9 | 69.3544 | 3467.72 | 73.73 | 313.64 |  | 201.4 |  |  | 588.77 | 0.58877 | C | D | D | 1900-01-14 02:24 | 1900-01-17 02:24 | 2024-10-21 | 2024-10-22 | RST Construction | C | Pipe | 2025-01-03 | 2025-01-03 | Ram Singh-1 | C |  | D | 2025-04-23 | 2025-04-25 | Munna Singh | C |  |  | 1330
[21 empty] | 299.34 | Sandy DRY
90 | AP-11 | DC+0 | 7.708 | 30.832 | 246.656 | [5 empty] | 4.057 | 2.48 | 0.006 | 0.365 | 6.908 | 0.436 | 0.01 | 0.446 | 25° 37' 10"RT | MP |  |  | 75.36 | 1.35 | 12.85 | 14.2 | 109.565 | 5478.25 | 81.82 | 599.6 |  | 201.4 |  |  | 882.82 | 0.88282 | C | D | D | 2024-10-10 | 2024-10-13 | 2024-10-18 | 2024-10-20 | RST Construction | C | CP | 2025-02-18 | 2025-02-18 | Ram Singh-1 | C |  | 1st stage done, need to upload in EE | 2025-04-30 | 2025-05-02 | Munna Singh | C |  |  | 1001
[21 empty] | 296 | DFR
91 | 11/1 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-10-20 | 2024-10-23 | 2024-10-25 | 2024-10-27 | RST Construction | C | CP | 2025-03-02 | 2025-03-04 | Ram Singh-1 | C |  | D | 2025-03-13 | 2025-03-14 | Rabiul Hauq | C |  |  | 980
[21 empty] | 229.889 | DFR
92 | AP-12 | DD+0 | 9.654 | 38.616 | 308.928 | [5 empty] | 4.807 | 4.016 | 0.007 | 0.431 | 9.261 | 0.557 | 0.01 | 0.567 | 40° 29' 60"LT | RJ |  |  | 119.36 | 2.05 | 18.37 | 20.42 | 157.1642 | 7858.21 | 89.9 |  | 1115.34 | 198.68 |  |  | 1403.92 | 1.4039 | C | D | D | 2024-10-01 | 2024-10-02 | 2024-10-10 | 2024-10-19 | RST Construction | C | CP | 2025-02-18 | 2025-02-18 | Ram Singh-1 | C | EE | D | 2025-03-20 | 2025-03-22 | Shree Ganesh Sital Enterprice | C |  |  | 1202
[21 empty] | 356.279 | DFR
93 | AP-13 | DC+3 | 8.626 | 34.504 | 276.032 | [5 empty] | 4.538 | 3.229 | 0.0064 | 0.429 | 8.2024 | 0.436 | 0.01 | 0.446 | 24° 1' 33"RT | RJ |  |  | 143.36 | 1.68 | 14.73 | 16.41 |  |  | 81.82 | 659.71 |  | 196.36 |  |  | 937.89 | 0.93789 | C | D | D | 2025-04-02 | 2025-04-04 | 2025-04-06 | 2025-04-08 | Shree shyam | C | Pipe | 2025-01-04 | 2025-01-04 | Ram Singh-1 | C | EE | D | 2025-05-23 | 2025-05-24 | Rames Kumar (M) | C |  |  | 1433
[21 empty] | 314 | Sandy Dry
94 | 13/1 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 1.51 | 11.15 | 12.66 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2025-11-02 | 2025-11-04 | 2025-11-06 | 2025-11-08 | Ram Singh | C |  | 2025-11-12 | 2025-11-14 | Ramesh Kumar | C |  |  | 2025-11-10 | 2025-11-12 | Ramesh | C |  |  | 1330 | Jai Sawami
[21 empty] | 353.589 | WFR
95 | AP-14 | DC+6 | 9.544 | 38.176 | 305.408 | [5 empty] | 4.938 | 3.609 | 0.0063 | 0.424 | 8.9773 | 0.436 | 0.01 | 0.446 | 25° 35' 30"LT | RJ |  |  | 75.36 | 1.35 | 12.85 | 14.2 | 109.565 | 5478.25 | 81.82 | 599.6 |  | 201.4 |  |  | 882.82 | 0.88282 | C | D | D | 2024-10-28 | 2024-11-03 | 2024-11-06 | 2024-11-08 | RST Construction | C | CP | 2025-02-18 | 2025-02-18 | Ram Singh-1 | C | EE | Checking not done | 2025-05-08 | 2025-05-08 | Rames Kumar (M) | C |  |  | 1657 | Jai Sawami
[21 empty] | 362 | DFR
96 | 14/1 | DB+3 | 8.63 | 34.52 | 276.16 | [5 empty] | 3.867 | 3.306 | 0.005 | 0.276 | 7.454 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C |  |  | 2025-08-31 | 2025-09-02 | 2025-09-05 | 2025-09-07 | Ramesh | C | CP | 2025-09-09 | 2025-09-09 | Department | C |  |  | 2025-10-26 | 2025-10-26 | Rames Kumar (M) | C |  |  | 1560 |  | Tower Strengthening check is required |  | got
[21 empty] | 387 | DFR
97 | 14/2 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C |  |  | 2025-09-12 | 2025-09-15 | 2025-09-18 | 2025-09-20 | Ramesh | C |  |  |  |  | C |  |  | 2025-10-21 | 2025-10-23 | Rames Kumar (M) | C |  |  | 1545
[21 empty] | 365 | DFR
98 | 14/3 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 |  | RJ |  |  | 51.64 | 0.97 | 9.82 | 10.79 | 83.456 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C |  |  | 2025-09-06 | 2025-09-08 | 2025-09-10 | 2025-09-12 | Ramesh | C | CP | 2025-09-14 | 2025-09-14 | Department | C |  |  | 2025-10-27 | 2025-10-29 | Rames Kumar (M) | C |  |  | 1252
[21 empty] | 419 | DFR
99 | 14/4 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 1.51 | 11.15 | 12.66 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C |  |  | 2025-09-22 | 2025-09-24 | 2025-09-27 | 2025-09-30 | Vinod | C | CP | 2025-10-02 | 2025-10-02 | Department | C |  |  | 2025-11-14 | 2025-11-16 | Rames Kumar (M) | C |  |  | 1545
[21 empty] | 331 | WFR
100 | 14/5 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C |  |  | 2025-09-22 | 2025-09-29 | 2025-10-05 | 2025-10-08 | Ram Singh | C | CP | 2025-10-10 | 2025-10-10 | Department | C |  |  | 2025-10-29 | 2025-10-31 | Rames Kumar (M) | C |  |  | 980
[21 empty] | 390 | DFR
101 | 14/6 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 1.51 | 11.15 | 12.66 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C |  |  | 2025-10-27 | 2025-10-30 | 2025-11-02 | 2025-11-05 | Vinod | C | CP | 2025-11-07 | 2025-11-07 | Department | C |  |  | 2025-11-15 | 2025-11-17 | Rames Kumar (M) | C |  |  | 1330
[21 empty] | 349 | WFR
102 | 14/7 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-18 | 2024-12-20 | 2024-12-23 | 2024-12-25 | Ram Singh-1 | C | CP | 2024-12-18 | 2024-12-18 | Ram Singh-1 | C |  | D | 2025-01-29 | 2025-01-31 | Ramesh Kumar | C |  |  | 980 | Jai Sawami
[21 empty] | 324 | DFR
103 | 14/8 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-30 | 2024-12-30 | 2024-12-31 | 2024-12-31 | Ram Singh-1 | C | CP | 2024-12-18 | 2024-12-18 | Ram Singh-1 | C |  | D | 2025-01-30 | 2025-02-01 | Ramesh Kumar | C |  |  | 1330 | Jai Sawami
[21 empty] | 413 | DFR
104 | 14/9 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-11 | 2024-12-14 | 2024-12-17 | 2024-12-19 | Ram Singh-1 | C | CP | 2024-12-18 | 2024-12-18 | Ram Singh-1 | C |  | D | 2025-02-01 | 2025-02-02 | Ramesh Kumar | C |  |  | 980 | Jai Sawami
[21 empty] | 310.18 | DFR
105 | AP-15 | DD+0 | 9.654 | 38.616 | 308.928 | [5 empty] | 4.807 | 4.016 | 0.007 | 0.431 | 9.261 | 0.557 | 0.01 | 0.567 | 37° 6' 34"RT | RJ |  |  | 119.36 | 2.05 | 18.37 | 20.42 | 157.1642 | 7858.21 | 89.9 |  | 1115.34 | 198.68 |  |  | 1403.92 | 1.4039 | C | D | D | 2024-12-08 | 2024-12-11 | 2024-12-13 | 2024-12-15 | Ram Singh-1 | C | CP | 2024-12-18 | 2024-12-18 | Ram Singh-1 | C |  | D | 2025-02-04 | 2025-02-05 | Ramesh Kumar | C | 2025-04-05 | 2025-04-05 | 1202 | Asit Baran Pal
[21 empty] | 379 | DFR
106 | 15/1 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-09-12 | 2024-09-15 | 2024-09-16 | 2024-09-22 | Ram Singh-1 | C | CP | 2024-12-18 | 2024-12-18 | Ram Singh-1 | C |  | D | 2024-12-19 | 2024-12-23 | Lakhan Singh | C | 2025-04-11 | 2025-04-11 | 1330 | Asit Baran Pal
[21 empty] | 304 | DFR
107 | 15/2 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-08-27 | 2024-09-07 | 2024-09-07 | 2024-09-11 | Ram Singh-1 | C | CP | 2024-12-20 | 2024-12-20 | Ram Singh-1 | C |  | D | 2024-12-24 | 2024-12-25 | Lakhan Singh | C | 2025-04-12 | 2025-04-12 | 980 | Asit Baran Pal
[21 empty] | 333 | DFR
108 | 15/3 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-09-08 | 2024-09-11 | 2024-09-12 | 2024-09-15 | Ram Singh-1 | C | CP | 2024-12-24 | 2024-12-24 | Ram Singh-1 | C |  | D | 2024-12-25 | 2024-12-26 | Lakhan Singh | C | 2025-03-30 | 2025-03-30 | 980 | Asit Baran Pal
[21 empty] | 363 | DFR
109 | 15/4 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 85.44 | 1.51 | 11.15 | 12.66 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2024-08-27 | 2024-09-16 | 2024-10-19 | 2024-10-24 | Ram Singh-1 | C | CP | 2024-12-24 | 2024-12-24 | Ram Singh-1 | C |  | D | 2025-02-05 | 2025-02-07 | Ramesh Kumar | C | 2025-03-31 | 2025-03-31 | 1545 | Asit Baran Pal
[21 empty] | 384 | WFR
110 | 15/5 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 85.44 | 1.51 | 11.15 | 12.66 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2024-12-02 | 2024-12-05 | 2024-12-07 | 2024-12-09 | Ram Singh-2 | C | CP | 2024-12-22 | 2024-12-22 | Ram Singh-1 | C |  | D | 2025-02-07 | 2025-02-09 | Ramesh Kumar | C | 2025-03-31 | 2025-03-31 | 1330 | Asit Baran Pal
[21 empty] | 361 | WFR
111 | 15/6 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 85.44 | 1.51 | 11.15 | 12.66 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2024-10-23 | 2024-10-25 | 2024-11-04 | 2024-11-06 | Ram Singh-2 | C | CP | 2024-12-22 | 2024-12-22 | Ram Singh-1 | C |  | D | 2025-02-11 | 2025-02-12 | Ramesh Kumar | C | 2025-04-02 | 2025-04-02 | 980 | Asit Baran Pal
[21 empty] | 311 | WFR
112 | 15/7 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 0.88 | 8.12 | 9 | 69.3544 | 3467.72 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-10-29 | 2024-10-31 | 2024-11-02 | 2024-11-03 | Ram Singh-1 | C | Pipe | 2024-12-22 | 2024-12-22 | Ram Singh-1 | C |  | D | 2025-02-09 | 2025-02-11 | Ramesh Kumar | C | 2025-04-02 | 2025-04-02 | 1330 | Asit Baran Pal
[21 empty] | 381 | Sandy Dry
113 | 15/8 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-11-03 | 2024-11-06 | 2024-11-09 | 2024-11-09 | Ram Singh-1 | C | Pipe | 2024-12-22 | 2024-12-22 | Ram Singh-1 | C |  | D | 2025-02-11 | 2025-02-13 | Ramesh Kumar | C | 2025-05-29 | 2025-05-29 | 980 | Asit Baran Pal
[21 empty] | 316 | Sandy WET
114 | 15/9 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-11-07 | 2024-11-08 | 2024-11-10 | 2024-11-12 | Ram Singh-2 | C | Pipe | 2024-12-22 | 2024-12-22 | Ram Singh-1 | C |  | D | 2025-02-16 | 2025-02-17 | Ramesh Kumar | C | 2025-04-13 | 2025-04-13 | 980 | Asit Baran Pal
[21 empty] | 290.45 | Sandy WET
115 | AP-16 | DC+0 | 7.708 | 30.832 | 246.656 | [5 empty] | 4.057 | 2.48 | 0.006 | 0.365 | 6.908 | 0.436 | 0.01 | 0.446 | 29° 42' 12"RT | RJ |  |  | 75.36 | 1.35 | 12.85 | 14.2 | 109.565 | 5478.25 | 81.82 | 599.6 |  | 201.4 |  |  | 882.82 | 0.88282 | C | D | D | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-10 | Ram Singh-1 | C | CP | 2024-12-22 | 2024-12-22 | Ram Singh-1 | C |  | D | 2025-02-14 | 2025-02-15 | Ramesh Kumar | C | 2025-03-24 | 2025-03-24 | 1001 | Asit Baran Pal
[21 empty] | 306 | DFR
116 | 16/1 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 85.44 | 1.51 | 11.15 | 12.66 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2024-09-22 | 2024-09-23 | 2024-09-26 | 2024-10-01 | Ram Singh-1 | C | CP | 2024-12-22 | 2024-12-22 | Ram Singh-1 | C |  | D | 2025-02-14 | 2025-02-16 | Ramesh Kumar | C | 2025-03-25 | 2025-03-25 | 1330 | Asit Baran Pal
[21 empty] | 336 | WFR
117 | 16/2 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-09-22 | 2024-10-10 | 2024-10-11 | 2024-10-27 | Ram Singh-2 | C | Pipe | 2024-12-22 | 2024-12-22 | Ram Singh-1 | C |  | D | 2025-02-22 | 2025-02-24 | Ramesh Kumar | C | 2025-03-25 | 2025-03-25 | 1330 | Asit Baran Pal
[21 empty] | 337 | Sandy WET
118 | 16/3 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 85.44 | 1.51 | 11.15 | 12.66 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2024-10-07 | 2024-10-09 | 2024-10-12 | 2024-10-16 | Ram Singh-1 | C | CP | 2025-02-20 | 2025-02-20 | Ram Singh-1 | C |  | D | 2025-02-18 | 2025-02-19 | Ramesh Kumar | C | 2025-03-25 | 2025-03-25 | 1330 | Asit Barhampal
[21 empty] | 328.65 | WFR
119 | AP-17 | DC+3 | 8.626 | 34.504 | 276.032 | [5 empty] | 4.538 | 3.229 | 0.0064 | 0.429 | 8.2024 | 0.436 | 0.01 | 0.446 | 20° 7' 26"LT | RJ |  |  | 148.8 | 2.51 | 19.47 | 21.98 | 168.0726 | 8403.63 | 70.93 | 914.33 |  | 98.08 | 153.24 |  | 1236.58 | 1.2366 | C | D | D | 2024-10-19 | 2024-10-27 | 2024-10-29 | 2024-10-31 | Viki Enterprises | C | CP | 2025-02-05 | 2025-02-05 | Ram Singh-1 | C |  | D | 2025-02-07 | 2025-02-09 | Saidur Rahaman | C | 2025-04-29 | 2025-04-29 | 1433 | Asit Barhampal
[21 empty] | 362 | WFR
120 | 17/1 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-10-11 | 2024-10-19 | 2024-10-23 | 2024-10-24 | Viki Enterprises | C | CP | 2025-02-05 | 2025-02-05 | Ram Singh-1 | C |  | D | 2025-02-18 | 2025-02-20 | Ramesh Kumar | C | 2025-04-29 | 2025-04-29 | 1545 | Asit Barhampal
[21 empty] | 364 | DFR
121 | 17/2 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-10-07 | 2024-10-08 | 2024-10-10 | 2024-10-11 | Viki Enterprises | C | CP | 2024-12-31 | 2024-12-31 | Ram Singh-1 | C |  | D | 2025-02-01 | 2025-02-03 | Saidur Rahaman | C | 2025-04-30 | 2025-04-30 | 1330 | Asit Barhampal
[21 empty] | 388 | DFR
122 | 17/3 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-10-30 | 2024-10-01 | 2024-10-02 | 2024-10-06 | Viki Enterprises | C | Pipe | 2024-12-31 | 2024-12-31 | Ram Singh-1 | C |  | D | 2025-01-29 | 2025-01-31 | Saidur Rahaman | C | 2025-04-30 | 2025-04-30 | 1545 | Asit Barhampal
[21 empty] | 321.97 | Sandy WET
123 | AP-18 | DC+0 | 7.708 | 30.832 | 246.656 | [5 empty] | 4.057 | 2.48 | 0.006 | 0.365 | 6.908 | 0.436 | 0.01 | 0.446 | 16° 0' 26"LT | RJ |  |  | 75.36 | 1.35 | 12.85 | 14.2 | 109.565 | 5478.25 | 81.82 | 599.6 |  | 201.4 |  |  | 882.82 | 0.88282 | C | D | D | 2024-10-12 | 2024-10-14 | 2024-10-18 | 2024-10-21 | Viki Enterprises | C | CP | 2024-12-31 | 2024-12-31 | Ram Singh-1 | C |  | D | 2025-02-21 | 2025-02-23 | Ramesh Kumar | C | 2025-03-26 | 2025-03-26 | 1001 | Asit Barhampal
[21 empty] | 365.484 | DFR
124 | 18/1 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-11-09 | 2024-11-22 | 2024-11-26 | 2024-11-29 | Shree Bayo | C | Pipe | 2024-12-31 | 2024-12-31 | Ram Singh-1 | C |  | D | 2024-12-30 | 2024-12-31 | Ramesh Kumar | C | 2025-03-26 | 2025-03-26 | 980 | Asit Barhampal
[21 empty] | 373.966 | Sandy WET
125 | 18/2 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 145.16 | 2.45 | 15.71 | 18.16 | 137.5006 | 6875.03 | 63.93 | 822.63 |  | 100.6 | 157.18 |  | 1144.34 | 1.1443 | C | D | D | 2024-11-09 | 2024-12-02 | 2024-12-05 | 2024-12-08 | Shree Bayo | C | CP | 2024-12-09 | 2024-12-09 | Shree Ram Bio | C |  | D | 2024-12-27 | 2024-12-29 | Ramesh Kumar | C | 2025-03-27 | 2025-03-27 | 1330 | Asit Barhampal
[21 empty] | 356.054 | SFR
126 | 18/3 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 80.64 | 0.88 | 8.12 | 9 | 69.3544 | 3467.72 | 73.73 | 313.64 |  | 201.4 |  |  | 588.77 | 0.58877 | C | D | D | 2024-08-14 | 2024-08-17 | 2024-08-18 | 2024-08-19 | Ram Singh-1 | C | Pipe | 2025-01-04 | 2025-01-04 | Ram Singh-1 | C |  | D | 2025-01-05 | 2025-01-06 | Ramesh Kumar | C | 2025-03-27 | 2025-03-27 | 980 | Asit Barhampal
[21 empty] | 349.663 | Sandy Dry
127 | 18/4 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-10-29 | 2024-11-02 | 2024-11-03 | 2024-11-04 | Viki Enterprises | C | CP | 2025-01-01 | 2025-01-01 | Ram Singh-1 | C |  | D | 2025-01-02 | 2025-01-03 | Ramesh Kumar | C | 2025-03-28 | 2025-03-28 | 980 | Asit Barhampal
[21 empty] | 353.115 | DFR
128 | 18/5 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-08-22 | 2024-10-14 | 2024-10-15 | 2024-10-18 | Ram Singh-3 | C | CP | 2025-01-02 | 2025-01-02 | Ram Singh-1 | C |  | D | 2025-01-03 | 2025-01-05 | Ramesh Kumar | C | 2025-04-03 | 2025-04-03 | 1330 | Asit Barhampal
[21 empty] | 374.201 | DFR
129 | 18/6 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 85.44 | 1.51 | 11.15 | 12.66 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2024-11-07 | 2024-11-10 | 2024-11-12 | 2024-11-14 | Viki Enterprises | C | CP | 2025-01-06 | 2025-01-06 | Ram Singh-1 | C |  | D | 2025-01-07 | 2025-01-08 | Ramesh Kumar | C | 2025-04-04 | 2025-04-04 | 1330 | Asit Barhampal
[21 empty] | 341.321 | WFR
130 | 18/7 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 85.44 | 1.51 | 11.15 | 12.66 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-20 | Viki Enterprises | C | CP | 2024-11-27 | 2024-11-27 | Viki Enterprises | C |  | D | 2025-01-14 | 2025-01-16 | Ramesh Kumar | C | 2025-04-16 | 2025-04-16 | 1545 | Asit Barhampal
[21 empty] | 347.958 | WFR
131 | 18/8 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-11-24 | 2024-11-26 | 2024-11-28 | 2024-11-30 | Viki Enterprises | C | CP | 2024-12-02 | 2024-12-02 | Viki Enterprises | C |  | D | 2025-01-09 | 2025-01-10 | Ramesh Kumar | C | 2025-04-26 | 2025-04-26 | 1330 | Asit Barhampal
[21 empty] | 384.02 | DFR
132 | 18/9 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-11-08 | 2024-11-19 | 2024-11-22 | 2024-11-26 | Viki Enterprises | C | CP | 2024-12-01 | 2024-12-01 | Viki Enterprises | C |  | D | 2025-01-11 | 2025-01-12 | Ramesh Kumar | C | 2025-04-24 | 2025-04-26 | 1330 | Asit Barhampal
[21 empty] | 269.694 | DFR
133 | 18/10 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-10-24 | 2024-11-21 | 2024-11-26 | 2024-11-30 | Ram Singh-3 | C | CP | 2025-01-10 | 2025-01-10 | Ram Singh-1 | C |  | D | 2025-01-12 | 2025-01-13 | Ramesh Kumar | C | 2025-04-24 | 2025-04-26 | 1330 | Asit Barhampal
[21 empty] | 394.041 | DFR
134 | 18/11 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-10-19 | 2024-10-22 | 2024-10-20 | 2024-10-24 | Ram Singh-3 | C | Pipe | 2025-01-10 | 2025-01-10 | Ram Singh-3 | C |  | D | 2025-01-28 | 2025-01-29 | Ramesh Kumar | C | 2025-04-24 | 2025-04-26 | 1330 | Asit Barhampal
[21 empty] | 300.614 | Sandy WET
135 | AP-19 | DB+3 | 8.63 | 34.52 | 276.16 | [5 empty] | 3.867 | 3.306 | 0.005 | 0.276 | 7.454 | 0.363 | 0.006 | 0.369 | 06°13'44"RT | RJ |  |  | 102.06 | 1.15 | 10.71 | 11.86 | 91.4286 | 4571.43 | 81.82 | 427.95 |  | 198.88 |  |  | 708.65 | 0.70865 | C | D | D | 2024-10-09 | 2024-10-16 | 2024-10-17 | 2024-10-20 | Ram Singh-3 | C | Pipe | 2025-01-02 | 2025-01-02 | Ram Singh-1 | C |  | D | 2025-01-16 | 2025-01-17 | Ramesh Kumar | C | 2025-04-25 | 2025-04-27 | 1560 | Asit Barhampal
[21 empty] | 315.42 | Sandy Dry
136 | 19/1 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-08-10 | 2024-08-16 | 2024-11-22 | 2024-11-26 | Ram Singh-1 | C | Pipe | 2025-01-03 | 2025-01-03 | Ram Singh-1 | C |  | D | 2025-01-18 | 2025-01-19 | Ramesh Kumar | C | 2025-04-25 | 2025-04-27 | 980 | Asit Barhampal
[21 empty] | 329.64 | Sandy WET
137 | 19/2 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-08-17 | 2024-08-23 | 2024-08-24 | 2024-10-04 | Ram Singh-1 | C | Pipe | 2025-01-19 | 2025-01-19 | Ram Singh-1 | C |  | D | 2025-01-20 | 2025-01-21 | Ramesh Kumar | C | 2025-04-25 | 2025-04-27 | 1330 | Asit Barhampal
[21 empty] | 382.97 | Sandy WET
138 | 19/3 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-11-12 | 2024-11-14 | 2024-11-16 | 2024-11-18 | Ram Singh-1 | C | Pipe | 2025-01-04 | 2025-01-04 | Ram Singh-1 | C |  | D | 2025-01-22 | 2025-01-23 | Ramesh Kumar | C | 2025-04-25 | 2025-04-27 | 1330 | Asit Barhampal
[21 empty] | 323.74 | Sandy WET
139 | 19/4 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-11-17 | 2024-11-19 | 2024-11-21 | 2024-11-24 | Ram Singh-1 | C | Pipe | 2025-01-10 | 2025-01-10 | Ram Singh-1 | C |  | D | 2025-01-24 | 2025-01-25 | Ramesh Kumar | C | 2025-04-25 | 2025-04-27 | 980 | Asit Barhampal
[21 empty] | 328.78 | Sandy WET
140 | 19/5 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-10-24 | 2024-11-13 | 2024-11-18 | 2024-11-21 | Ram Singh-2 | C | Pipe | 2025-01-05 | 2025-01-05 | Ram Singh-1 | C |  | D | 2025-05-09 | 2025-05-10 | Ramesh Kumar | C | 2025-04-25 | 2025-04-27 | 980 | Asit Barhampal
[21 empty] | 266 | Sandy WET
141 | AP-20 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 | 08°51'36"RT | RJ |  |  | 143.36 | 1.68 | 13.27 | 14.95 | 114.4154 | 5720.77 | 70.93 | 596.29 |  | 99.34 | 155.21 |  | 921.77 | 0.92177 | C | D | D | 2024-11-06 | 2024-11-08 | 2024-11-10 | 2024-11-12 | Shree Bayo | C | Pipe | 2025-01-02 | 2025-01-02 | Ram Singh-1 | C |  | D | 2025-02-26 | 2025-02-28 | Rabiul Hauq | C | 2025-05-03 | 2025-05-03 | 1252 | Asit Barhampal
[21 empty] | 321.89 | WET
142 | 20/1 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 121.84 | 1.4 | 10.63 | 12.03 | 91.8938 | 4594.69 | 63.93 | 481.99 |  | 100.6 | 157.18 |  | 803.7 | 0.8037 | C | D | D | 2024-11-02 | 2024-11-04 | 2024-11-06 | 2024-11-08 | Shree Bayo | C | Pipe | 2025-01-02 | 2025-01-02 | Ram Singh-1 | C |  | D | 2025-02-21 | 2025-02-23 | Rabiul Hauq | C | 2025-05-03 | 2025-05-03 | 980 | Asit Barhampal
[21 empty] | 352.14 | WET
143 | 20/2 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 147.88 | 1.74 | 12.26 | 14 | 106.5412 | 5327.06 | 63.93 | 558.32 |  | 100.6 | 157.18 |  | 880.03 | 0.88003 | C | D | D | 2024-10-31 | 2024-11-01 | 2024-11-03 | 2024-11-05 | Shree Bayo | C | Pipe | 2025-01-02 | 2025-01-02 | Ram Singh-1 | C |  | D | 2025-02-23 | 2025-02-25 | Rabiul Hauq | C | 2025-05-03 | 2025-05-03 | 1330 | Asit Barhampal
[21 empty] | 347.32 | PS
144 | 20/3 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 147.88 | 1.74 | 12.26 | 14 | 106.5412 | 5327.06 | 63.93 | 558.32 |  | 100.6 | 157.18 |  | 880.03 | 0.88003 | C | D | D | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-26 | Shree Bayo | C | Pipe | 2025-01-02 | 2025-01-02 | Ram Singh-1 | C |  | D | 2025-02-28 | 2025-03-02 | Rabiul Hauq | C | 2025-05-03 | 2025-05-03 | 980 | Asit Barhampal
[21 empty] | 339.42 | PS
145 | 20/4 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 147.88 | 1.74 | 12.26 | 14 | 106.5412 | 5327.06 | 63.93 | 558.32 |  | 100.6 | 157.18 |  | 880.03 | 0.88003 | C | D | D | 2024-10-26 | 2024-10-27 | 2024-10-29 | 2024-10-30 | Shree Bayo | C | Pipe | 2025-01-02 | 2025-01-02 | Ram Singh-1 | C |  | D | 2025-03-02 | 2025-03-04 | Rabiul Hauq | C | 2025-05-03 | 2025-05-03 | 980 | Asit Barhampal
[21 empty] | 330.88 | PS
146 | 20/5 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 80.64 | 0.88 | 8.12 | 9 | 69.3544 | 3467.72 | 73.73 | 313.64 |  | 201.4 |  |  | 588.77 | 0.58877 | C | D | D | 2024-08-09 | 2024-08-10 | 2024-08-12 | 2024-08-16 | Ram Singh-2 | C | Pipe | 2025-01-02 | 2025-01-02 | Ram Singh-1 | C |  | D | 2025-02-17 | 2025-02-19 | Rabiul Hauq | C | 2025-05-03 | 2025-05-03 | 980 | Asit Barhampal
[21 empty] | 279.99 | Sandy Dry
147 | 20/6 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 121.84 | 1.4 | 10.63 | 12.03 | 91.8938 | 4594.69 | 63.93 | 481.99 |  | 100.6 | 157.18 |  | 803.7 | 0.8037 | C | D | D | 2024-09-22 | 2024-10-17 | 2024-10-18 | 2024-10-22 | Shree Bayo | C | Pipe | 2025-01-04 | 2025-01-04 | Ram Singh-1 | C |  | D | 2025-03-05 | 2025-03-06 | Rabiul Hauq | C | 2025-05-04 | 2025-05-04 | 1330 | Asit Barhampal
[21 empty] | 369.48 | WET
148 | 20/7 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 80.64 | 0.88 | 8.12 | 9 | 69.3544 | 3467.72 | 73.73 | 313.64 |  | 201.4 |  |  | 588.77 | 0.58877 | C | D | D | 2024-08-01 | 2024-08-06 | 2024-08-08 | 2024-08-12 | Ram Singh-1 | C | Pipe | 2025-01-04 | 2025-01-04 | Ram Singh-1 | C |  | D | 2025-02-19 | 2025-02-21 | Rabiul Hauq | C | 2025-05-04 | 2025-05-04 | 1330 | Asit Barhampal
[21 empty] | 369.65 | Sandy Dry
149 | 20/8 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 0.88 | 8.12 | 9 | 69.3544 | 3467.72 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2025-02-19 | 2025-02-21 | 2025-02-23 | 2025-02-25 | Shree Bayo | C | Pipe | 2025-03-07 | 2025-03-07 | Shree Ram Bio | C |  |  | 2025-11-10 | 2025-11-12 | Ramesh Kumar | C |  |  |  | Jai Swami
[21 empty] | 284 | Sandy Dry
150 | AP-21 | DB+0 | 7.71 | 30.84 | 246.72 | [5 empty] | 3.452 | 2.633 | 0.004 | 0.241 | 6.33 | 0.363 | 0.006 | 0.369 | 14°34'48"LT | RJ |  |  |  | 1.68 | 13.27 | 14.95 | [10 empty] | C | D | D | 2024-10-23 | 2024-10-27 | 2024-11-06 | 2024-11-09 | Gauri Construction | C | Pipe | 2025-01-04 | 2025-01-04 | Gauri Construction | C |  | D | 2025-03-06 | 2025-03-08 | Rabiul Hauq | C | 2025-05-07 | 2025-05-07 | 1252 | Asit Barhampal
[21 empty] | 345.88 | WET
151 | 21/1 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 0.88 | 8.12 | 9 | 114.4154 | 5720.77 | 70.93 | 596.29 |  | 99.34 | 155.21 |  | 921.77 | 0.92177 | C | D | D | 2025-04-09 | 2025-04-11 | 2025-04-13 | 2025-04-15 | Viki Enterprises | C | Pipe | 2025-05-10 | 2025-05-10 | Viki Enterprises | C |  | D | 2025-05-17 | 2025-05-17 | Ramesh Kumar (M) | C | 2025-06-04 | 2025-06-04 | 1330 | Asit Barhampal
[21 empty] | 310.87 | Sandy Dry
152 | 21/2 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 80.64 | 0.88 | 8.12 | 9 | 69.3544 | 3467.72 | 73.73 | 313.64 |  | 201.4 |  |  | 588.77 | 0.58877 | C | D | D | 2025-04-15 | 2025-04-17 | 2025-04-19 | 2025-04-21 | Viki Enterprises | C | Pipe | 2025-05-01 | 2025-05-02 | Viki Enterprises | C |  | D | 2025-05-14 | 2025-05-15 | Ramesh Kumar (M) | C | 2025-05-30 | 2025-05-30 | 1330 | Asit Barhampal
[21 empty] | 380.03 | Sandy Dry
153 | 21/3 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 80.64 | 1.51 | 11.15 | 12.66 | 69.3544 | 3467.72 | 73.73 | 313.64 |  | 201.4 |  |  | 588.77 | 0.58877 | C | D | D | 2024-10-23 | 2024-10-25 | 2024-10-26 | 2024-10-26 | Gauri Construction | C | CP | 2025-01-27 | 2025-01-28 | Ram Singh-1 | C |  | D | 2025-02-18 | 2025-02-19 | Dudhnath Kumar | C | 2025-05-30 | 2025-05-30 | 1330 | Asit Barhampal
[21 empty] | 358.18 | WFR
154 | 21/4 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 85.44 | 0.88 | 8.12 | 9 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2024-11-11 | 2024-11-13 | 2024-11-15 | 2024-11-17 | Shree Bayo | C | Pipe | 2025-01-27 | 2025-01-28 | Ram Singh-1 | C |  | D | 2025-02-07 | 2025-02-09 | Dudhnath Kumar | C | 2025-05-30 | 2025-05-30 | 980 | Asit Barhampal
[21 empty] | 311.05 | Sandy Dry
155 | 21/5 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 80.64 | 0.88 | 8.12 | 9 | 69.3544 | 3467.72 | 73.73 | 313.64 |  | 201.4 |  |  | 588.77 | 0.58877 | C | D | D | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | Shree Bayo | C | Pipe | 2025-02-03 | 2025-02-03 | Ram Singh-1 | C |  | D | 2025-02-10 | 2025-02-11 | Dudhnath Kumar | C | 2025-06-14 | 2025-06-14 | 1330 | Asit Barhampal
[21 empty] | 375.15 | Sandy Dry
156 | 21/6 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 80.64 | 0.8 | 7.8 | 8.6 | 69.3544 | 3467.72 | 73.73 | 313.64 |  | 201.4 |  |  | 588.77 | 0.58877 | C | D | D | 2024-08-30 | 2024-09-01 | 2024-09-01 | 2024-09-19 | Gauri Construction | C | CP | 2025-02-03 | 2025-02-03 | Ram Singh-1 | C |  | D | 2025-02-13 | 2025-02-14 | Dudhnath Kumar | C | 2025-05-07 | 2025-05-07 | 1330 | Asit Barhampal
[21 empty] | 369.13 | DFR
157 | 21/7 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-09-03 | 2024-09-13 | 2024-09-21 | 2024-09-23 | Gauri Construction | C | CP | 2025-02-03 | 2025-02-03 | Ram Singh-1 | C |  | D | 2025-02-14 | 2025-02-16 | Dudhnath Kumar | C | 2025-05-07 | 2025-05-07 | 1330 | Asit Barhampal
[21 empty] | 370.97 | DFR
158 | 21/8 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.88 | 8.12 | 9 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-11-12 | 2024-11-15 | 2024-11-17 | 2024-11-19 | Shree Bayo | C | Pipe | 2025-02-03 | 2025-02-03 | Ram Singh-1 | C |  | D | 2025-02-19 | 2025-02-21 | Dudhnath Kumar | C | 2025-05-26 | 2025-05-26 | 1330 | Asit Barhampal
[21 empty] | 356.46 | Sandy Dry
159 | 21/9 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 80.64 | 1.68 | 11.97 | 13.65 | 69.3544 | 3467.72 | 73.73 | 313.64 |  | 201.4 |  |  | 588.77 | 0.58877 | C | D | D | 2024-11-07 | 2024-11-26 | 2024-12-01 | 2024-12-04 | Gauri Construction | C | Pipe | 2025-02-03 | 2025-02-03 | Ram Singh-1 | C |  | D | 2025-02-21 | 2025-02-23 | Dudhnath Kumar | C | 2025-05-26 | 2025-05-26 | 980 | Asit Barhampal
[21 empty] | 363.33 | Sandy WET
160 | 21/10 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 1.68 | 11.97 | 13.65 | 103.9374 | 5196.87 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2024-08-28 | 2024-11-11 | 2024-11-15 | 2024-11-19 | Gauri Construction | C | Pipe | 2025-02-03 | 2025-02-03 | Ram Singh-1 | C |  | D | 2025-02-23 | 2025-02-25 | Dudhnath Kumar | C | 2025-05-27 | 2025-05-27 | 1330 | Asit Barhampal
[21 empty] | 370.25 | Sandy WET
161 | 21/11 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 143.36 | 0.88 | 8.12 | 9 | 69.3544 | 3467.72 | 63.93 | 535.23 |  | 100.6 | 157.18 |  | 856.94 | 0.85694 | C | D | D | 2025-02-07 | 2025-02-13 | 2025-02-16 | 2025-02-19 | Shree Bayo | C | Pipe | 2025-03-03 | 2025-03-03 | Shree Bayo | C |  | D | 2025-05-10 | 2025-05-12 | Ramesh Kumar (M) | C | 2025-05-27 | 2025-05-27 | 980 | Asit Barhampal
[21 empty] | 330.02 | Sandy Dry
162 | 21/12 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 80.64 | 1.51 | 11.15 | 12.66 | 69.3544 | 3467.72 | 73.73 | 313.64 |  | 201.4 |  |  | 588.77 | 0.58877 | C | D | D | 2024-09-22 | 2024-10-13 | 2024-10-17 | 2024-10-21 | Gauri Construction | C | CP | 2025-01-05 | 2025-01-05 | Shree Bayo | C |  | D | 2025-03-03 | 2025-03-05 | Ramesh Kumar | C | 2025-05-30 | 2025-05-30 | 1330 | Asit Barhampal
[21 empty] | 390.08 | WFR
163 | 21/13 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 85.44 | 0.8 | 7.8 | 8.6 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2025-04-21 | 2025-04-23 | 2025-04-25 | 2025-04-27 | Viki Enterprises | C | CP | 2025-05-05 | 2025-05-05 | Viki Enterprises | C |  | D | 2025-05-17 | 2025-05-19 | Ramesh Kumar (M) | C | 2025-05-30 | 2025-05-30 | 1330 | Asit Barhampal
[21 empty] | 343.38 | DFR
164 | AP-22 | DC+3 | 8.626 | 34.504 | 276.032 | [5 empty] | 4.538 | 3.229 | 0.0064 | 0.429 | 8.2024 | 0.436 | 0.01 | 0.446 | 20° 2' 24"RT | RJ |  |  | 41.44 | 2.51 | 19.47 | 21.98 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | EG | D | 2024-12-06 | 2024-12-08 | 2024-12-09 | 2024-12-11 | Gauri Construction | C | CP | 2025-01-03 | 2025-01-03 | Gauri Construction | C |  | D | 2025-02-26 | 2025-02-28 | Ramesh Kumar | C | 2025-05-31 | 2025-05-31 | 1433 | Asit Barhampal
[21 empty] | 326.53 | WFR
165 | 22/1 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 148.8 | 1.51 | 11.15 | 12.66 | 168.0726 | 8403.63 | 70.93 | 914.33 |  | 98.08 | 153.24 |  | 1236.58 | 1.2366 | C | D | D | 2024-12-13 | 2024-12-15 | 2024-12-17 | 2024-12-19 | Gauri Construction | C | CP | 2025-01-03 | 2025-01-03 | Gauri Construction | C |  | D | 2025-02-27 | 2025-03-01 | Ramesh Kumar | C | 2025-05-31 | 2025-05-31 | 1330 | Asit Barhampal
[21 empty] | 302.5 | WFR
166 | 22/2 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 85.44 | 1.51 | 11.15 | 12.66 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2024-08-22 | 2024-09-25 | 2024-10-05 | 2024-10-09 | Gauri Construction | C | CP | 2025-01-05 | 2025-01-05 | Shree Bayo | C |  | D | 2025-02-25 | 2025-02-26 | Ramesh Kumar | C | 2025-05-31 | 2025-05-31 | 1330 | Asit Barhampal
[21 empty] | 318.2 | WFR
167 | AP-23 | DC+0 | 7.708 | 30.832 | 246.656 | [5 empty] | 4.057 | 2.48 | 0.006 | 0.365 | 6.908 | 0.436 | 0.01 | 0.446 | 19° 37' 2"LT | RJ |  |  | 85.44 | 1.35 | 12.85 | 14.2 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2025-01-31 | 2025-02-03 | 2025-02-04 | 2025-02-06 | Shree Bayo | C | CP | 2025-02-16 | 2025-02-16 | Shree Ram Bio | C |  | 1st stage done, need to upload in EE | 2025-08-17 | 2025-08-19 | Dudhnath | C |  |  | 1001
[21 empty] | 315.48 | DFR
168 | 23/1 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 75.36 | 0.8 | 7.8 | 8.6 | 109.565 | 5478.25 | 81.82 | 599.6 |  | 201.4 |  |  | 882.82 | 0.88282 | C | D | D | 2025-02-04 | 2025-02-07 | 2025-02-08 | 2025-02-10 | Shree Bayo | C | CP | 2025-01-05 | 2025-01-05 | Shree Ram Bio | C |  | D | 2025-03-05 | 2025-03-06 | Ramesh Kumar | C | 2025-06-01 | 2025-06-01 | 980 | Asit Barhampal
[21 empty] | 249.29 | DFR
169 | 23/2 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-16 | 2024-12-19 | 2024-12-21 | 2024-12-23 | Gauri Construction | C | CP | 2025-02-25 | 2025-02-25 | Gauri Construction | C |  | D | 2025-03-01 | 2025-03-02 | Ramesh Kumar | C | 2025-06-01 | 2025-06-01 | 980 | Asit Barhampal
[21 empty] | 288.05 | DFR
170 | 23/3 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | RJ |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2025-02-23 | 2025-02-25 | 2025-02-27 | 2025-02-28 | Shree Bayo | C | CP | 2025-03-02 | 2025-03-02 | Shree Bayo | C |  | D | 2025-05-26 | 2025-05-28 | Ramesh Kumar | C | 2025-06-01 | 2025-06-01 | 980 | Asit Barhampal
[21 empty] | 369.86 | DFR
171 | 23/4 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 1.51 | 11.15 | 12.66 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-15 | Shree Bayo | C | CP | 2024-12-20 | 2024-12-20 | Shree Ram Bio | C |  | D | 2025-03-02 | 2025-03-03 | Ramesh Kumar | C | 2025-06-02 | 2025-06-02 | 1330 | Asit Barhampal
[21 empty] | 320.21 | WFR
172 | 23/5 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 85.44 | 0.8 | 7.8 | 8.6 | 96.5734 | 4828.67 | 63.93 | 524.79 |  | 100.6 | 157.18 |  | 846.5 | 0.8465 | C | D | D | 2025-04-24 | 2025-04-26 | 2025-04-28 | 2025-04-30 | Ram Singh | C | CP | 2025-05-06 | 2025-05-06 | Ram Singh | C | EE | D | 2025-05-29 | 2025-05-31 | Ramesh Kumar | C | 2025-08-16 | 2025-08-16 | 980 | Asit Barhampal
[21 empty] | 383.86 | DFR
173 | AP-24 | DD+9 | 13.258 | 53.032 | 424.256 | [5 empty] | 6.059 | 5.874 | 0.0077 | 0.563 | 12.5037 | 1.116 | 0.032 | 1.148 | 29° 40' 34"LT | MP |  |  | 41.44 | 3.53 | 38.97 | 42.5 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | EE | D | 2025-04-23 | 2025-04-25 | 2025-04-27 | 2025-04-29 | Ram Singh | C | CP | 2025-05-01 | 2025-05-01 | Shree Bayo | C | EE | D | 2025-06-09 | 2025-06-11 | Ramesh Kumar | C | 2025-08-16 | 2025-08-16 | 2008 | Asit Barhampal
[21 empty] | 190.524 | WFR
174 | AP-25 | DD+18 | 16.654 | 66.616 | 532.928 | 1 | 3 | 3 | 3 | 3 | 8.897 | 8.801 | 0.0093 | 0.752 | 18.4593 | 1.116 | 0.032 | 1.148 | 11° 2' 4"RT | MP |  |  | 215.12 | 2.31 | 27.89 | 30.2 | 235.0498 |  | 237.43 |  | 1520.85 | 690.12 | 0 |  | 2448.4 | 2.4484 | C | EE | D | 2025-04-11 | 2025-04-13 | 2025-04-15 | 2025-04-17 | Shree Bayo | C | CP | 2025-04-20 | 2025-04-20 | Ram Singh-1 | C |  | 1st stage done, need to upload in EE | 2025-07-24 | 2025-07-26 | Ramesh Kumar | C
[21 empty] | 173.541 | DFR |  |  |  |  | 0
175 | AP-26 | DD+18 | 16.654 | 66.616 | 532.928 | 1 | 3 | 3 | 3 | 3 | 8.897 | 8.801 | 0.0093 | 0.752 | 18.4593 | 1.116 | 0.032 | 1.148 |  | MP |  |  | 136.28 | 3.53 | 38.97 | 42.5 | 329.7714 |  | 171.11 |  | 1373.57 |  | 831.91 |  | 2376.59 | 2.3766 | C | EG | D | 2025-03-09 | 2025-03-11 | 2025-03-14 | 2025-03-16 | Shree Bayo | C | CP | 2025-04-07 | 2025-04-07 | Ram Singh-1 | C | EE | 2nd stage done, need to upload on EE | 2025-06-04 | 2025-06-06 | Ramesh Kumar | C
[21 empty] | 142.384 | WFR |  |  |  |  | 0
176 | AP-27 | DD+18 | 16.654 | 66.616 | 532.928 | 1 | 3 | 3 | 3 | 3 | 8.897 | 8.801 | 0.0093 | 0.752 | 18.4593 | 1.116 | 0.032 | 1.148 |  | MP |  |  | 231.88 | 2.31 | 27.89 | 30.2 | 235.0498 |  | 171.11 |  | 1849.49 |  | 831.91 |  | 2852.51 | 2.8525 | C | EE | D | 2025-03-27 | 2025-03-29 | 2025-04-01 | 2025-04-03 | Shree Bayo | C | CP | 2025-04-07 | 2025-04-07 | Ram Singh-1 | C |  | 1st stage done, need to upload in EE | 2025-07-24 | 2025-07-26 | Dudhnath Kumar | C
[21 empty] | 77.015 | DFR |  |  |  |  | 0
177 | AP-28 | DD+0 | 9.654 | 38.616 | 308.928 | 1 | 3 | 3 | 3 | 3 | 4.807 | 4.016 | 0.007 | 0.431 | 9.261 | 0.557 | 0.01 | 0.567 |  | MP |  |  | 231.88 | 2.05 | 18.37 | 20.42 | 157.1642 |  | 171.11 |  | 1849.49 |  | 831.91 |  | 2852.51 | 2.8525 | C | EE | D | 2025-05-20 | 2025-05-21 | 2025-05-23 | 2025-05-25 | Shree Bayo | C | CP | 2025-06-05 | 2025-06-05 | Shree Bayo | C | EE | D | 2025-06-15 | 2025-06-17 | Ramesh Kumar | C |  |  | 1202 |  | Tower Strengthening check is required
[21 empty] | 42.266 | DFR |  |  |  |  | 0
178 | 28/1 | GANTRY UC |  | 0 | 54 | [5 empty] | 3.738 | 1.944 | 0.015 | 0.367 | 6.064 | 0.683 | 0.015 | 0.698 |  | MP |  |  | 119.36 | 4.5 | 43.8 | 48.3 | 373.008 | 7858.21 | 89.9 |  | 1115.34 | 198.68 |  |  | 1403.92 | 1.4039 | C |  |  | 2025-05-06 | 2025-05-12 | 2025-05-21 | 2025-05-24 | Ram Singh-1 | C |  |  |  |  | C |  |  | 2025-10-18 | 2025-10-22 | Ramesh Kumar | C |  |  |  | Jai Swami | Tower Strengthening check is required
[21 empty] | 54.573 | WFR |  |  |  |  | 0
179 | 28/2 | GANTRY UC |  | 0 | 54 | [5 empty] | 3.738 | 1.944 | 0.015 | 0.367 | 6.064 | 0.683 | 0.015 | 0.698 |  | MP |  |  | 351 | 4.5 | 43.8 | 48.3 | 373.008 |  | 211.2 |  | 2410.4 |  |  | 1552.2 | 4173.8 | 4.1738 | C |  |  | 2025-06-16 | 2025-06-21 | 2025-06-26 | 2025-06-29 | Ram Singh-1 | C |  | 2025-07-09 | 2025-07-09 | Ram Singh-1 | C |  |  | 2025-08-14 | 2025-08-17 | Dudhnath Kumar | C
[21 empty] | 41.886 | WFR |  |  |  |  | 0
180 | AP-29 | DD+3 | 10.82 | 43.28 | 346.24 | [5 empty] | 5.492 | 5.097 | 0.0078 | 0.502 | 11.0988 | 0.557 | 0.01 | 0.567 |  | MP |  |  | 351 | 2.05 | 18.37 | 20.42 | 157.1642 |  | 211.2 |  | 2410.4 |  |  | 1552.2 | 4173.8 | 4.1738 | C | D | D | 2025-05-07 | 2025-05-10 | 2025-05-12 | 2025-05-14 | Ram Singh-1 | C | CP | 2025-05-21 | 2025-05-21 | Ram Singh-1 | C | EE | Fab | 2025-06-13 | 2025-06-15 | Ramesh Kumar | C |  |  | 1552
[21 empty] | 353.284 | DFR |  |  |  |  | 0
181 | 29A/0 | DC+9 | 10.462 | 41.848 | 334.784 | [5 empty] | 5.201 | 4.146 | 0.0067 | 0.503 | 9.8567 | 0.436 | 0.01 | 0.446 |  | MP |  |  | 119.36 | 1.35 | 12.85 | 14.2 | 109.565 | 7858.21 | 89.9 |  | 1115.34 | 198.68 |  |  | 1403.92 | 1.4039 | C | EE | D | 2025-05-03 | 2025-05-06 | 2025-05-08 | 2025-05-10 | Ram Singh-1 | C |  | 2025-05-20 | 2025-05-20 | Ram Singh-1 | C |  | Fab | 2025-08-11 | 2025-08-14 | Dudhnath Kumar | C |  |  | 1657 | Asit Barhampal | Tower Strengthening check is required
[21 empty] | 393 | DFR |  |  |  |  | 0
182 | 29A/1 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 75.36 | 0.8 | 7.8 | 8.6 | 66.42 | 5478.25 | 81.82 | 599.6 |  | 201.4 |  |  | 882.82 | 0.88282 | C | EG | D | 2024-12-20 | 2024-12-22 | 2024-12-24 | 2024-12-26 | Ram Singh-1 | C | CP | 2025-01-20 | 2025-01-20 | Ram Singh-1 | C | EE | D | 2025-02-18 | 2025-02-19 | Shree Ganesh Sital Enterprice | C | 2025-06-02 | 2025-06-02 | 980 | Asit Barhampal
[21 empty] | 359 | DFR |  |  |  |  | 0
183 | 29A/2 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.244 | 0.005 | 0.249 | 15° 48' 52"RT | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-10 | 2024-12-16 | 2024-12-18 | 2024-12-20 | Shree Bayo | C | CP | 2024-12-22 | 2024-12-22 | Shree Ram Bio | C |  | D | 2025-02-19 | 2025-02-21 | Shree Ganesh Sital Enterprice | C | 2025-06-02 | 2025-06-02 | 1545 | Asit Barhampal
[21 empty] | 387 | DFR |  |  |  |  | 0
184 | 29A/3 | DA+9 | 8.252 | 33.008 | 264.064 | [5 empty] | 3.078 | 3.659 | 0.0027 | 0.266 | 7.0057 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-19 | 2024-12-21 | 2024-12-23 | 2024-12-25 | Shree Bayo | C | CP | 2024-12-22 | 2024-12-22 | Shree Ram Bio | C |  | D | 2025-02-21 | 2025-02-23 | Shree Ganesh Sital Enterprice | C | 2025-05-03 | 2025-05-03 | 1588 | Asit Barhampal
[21 empty] | 346 | DFR |  |  |  |  | 0
185 | 29A/4 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-22 | 2025-01-15 | 2025-01-18 | 2025-01-19 | Gauri Enterprice | C | CP | 2025-03-07 | 2025-03-07 | Gauri Construction | C |  | D | 2025-02-26 | 2025-02-27 | Shree Ganesh Sital Enterprice | C | 2025-05-03 | 2025-05-03 | 1330 | Asit Barhampal
[21 empty] | 375.545 | DFR |  |  |  |  | 0
186 | AP-30 | DB+3 | 8.63 | 34.52 | 276.16 | [5 empty] | 3.867 | 3.306 | 0.005 | 0.276 | 7.454 | 0.363 | 0.006 | 0.369 |  | MP |  |  | 41.44 | 0.97 | 9.82 | 10.79 | 83.456 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-24 | 2024-12-26 | 2024-12-27 | 2024-12-28 | Ram Singh | C | CP | 2024-12-29 | 2024-12-29 | Ram Singh-1 | C |  | D | 2025-02-23 | 2025-02-25 | Shree Ganesh Sital Enterprice | C | 2025-06-07 | 2025-06-07 | 1560 | Asit Barhampal
[21 empty] | 341.74 | DFR |  |  |  |  | 0
187 | 30/1 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 51.64 | 0.8 | 7.8 | 8.6 | 66.42 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | D | D | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | Gauri Entp. | C | CP | 2024-12-29 | 2024-12-29 | Gauri Construction | C |  | D | 2025-02-26 | 2025-02-28 | Shree Ganesh Sital Enterprice | C | 2025-06-07 | 2025-06-07 | 980 | Asit Barhampal
[21 empty] | 321.51 | DFR |  |  |  |  | 0
188 | 30/2 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-26 | 2025-01-03 | 2025-01-04 | 2025-01-06 | Gauri Entp. | C | CP | 2025-03-05 | 2025-03-05 | Gauri Construction | C |  | D | 2025-03-02 | 2025-03-03 | Shree Ganesh Sital Enterprice | C | 2025-06-08 | 2025-06-08 | 980 | Asit Barhampal
[21 empty] | 312.39 | DFR |  |  |  |  | 0
189 | 30/3 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-28 | 2024-12-29 | 2024-12-30 | 2024-12-31 | Ram Singh-1 | C | CP | 2024-12-29 | 2024-12-29 | Ram Singh-1 | C |  | D | 2025-01-30 | 2025-02-01 | Shree Ganesh Sital Enterprice | C | 2025-06-08 | 2025-06-08 | 980 | Asit Barhampal
[21 empty] | 358.35 | DFR |  |  |  |  | 0
190 | 30/4 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | Ram Singh-1 | C | CP | 2024-12-29 | 2024-12-29 | Ram Singh-1 | C |  | D | 2025-03-05 | 2025-03-06 | Dudhnath Kumar | C | 2025-05-15 | 2025-05-15 | 980 | Asit Barhampal
[21 empty] | 319.21 | DFR |  |  |  |  | 0
191 | 30/5 | DA+0 | 6.362 | 25.448 | 203.584 | [5 empty] | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2025-01-02 | 2025-01-05 | 2025-01-08 | 2025-01-10 | Ram Singh-1 | C | CP | 2024-12-29 | 2024-12-29 | Ram Singh-1 | C |  | D | 2025-03-03 | 2025-03-05 | Dudhnath Kumar | C | 2025-05-15 | 2025-05-15 | 980 | Asit Barhampal
[21 empty] | 342.4 | DFR |  |  |  |  | 0
192 | 30/6 | DA+3 | 6.992 | 27.968 | 223.744 | [5 empty] | 2.607 | 2.657 | 0.002 | 0.213 | 5.479 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 41.44 | 0.8 | 7.8 | 8.6 | 66.42 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2024-12-28 | 2024-12-28 | 2024-12-29 | 2024-12-30 | Shree Bayo | C | CP | 2024-12-29 | 2024-12-29 | Shree Ram Bio | C |  | D | 2025-03-02 | 2025-03-03 | Dudhnath Kumar | C | 2025-05-15 | 2025-05-15 | 1330 | Asit Barhampal
[21 empty] | 337.31 | DFR |  |  |  |  | 0
193 | AP-31 | DB+3 | 8.63 | 34.52 | 276.16 | [5 empty] | 3.867 | 3.306 | 0.005 | 0.276 | 7.454 | 0.363 | 0.006 | 0.369 |  | MP |  |  | 41.44 | 0.97 | 9.82 | 10.79 | 83.456 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | D | D | 2025-01-01 | 2025-01-03 | 2025-01-05 | 2025-01-07 | Shree Bayo | C | CP | 2024-12-29 | 2024-12-29 | Shree Ram Bio | C |  | D | 2025-02-28 | 2025-03-02 | Shree Ganesh Sital Enterprice | C | 2025-05-15 | 2025-05-15 | 1560 | Asit Barhampal
[21 empty] | 371.81 | DFR |  |  |  |  | 0
194 | 31/1 | DA+6 | 7.622 | 30.488 | 243.904 | [5 empty] | 2.679 | 3.133 | 0.0025 | 0.233 | 6.0475 | 0.537 | 0.011 | 0.548 |  | MP |  |  | 51.64 | 0.8 | 23.14 | 23.94 | 190.0604 | 4172.8 | 81.82 | 408.9 |  | 203.94 |  |  | 694.66 | 0.69466 | C | EG | D | 2025-01-10 | 2025-01-12 | 2025-01-13 | 2025-01-15 | Shree Bayo | C | CP | 2025-02-12 | 2025-02-12 | Shree Bayo | C |  | Checling not done | 2025-07-11 | 2025-07-13 | Ramesh Kumar | C |  |  |  | Jai Swami
[21 empty] | 371.54 | DFR |  |  |  |  | 0
195 | AP-32 | DC+0 | 7.708 | 30.832 | 246.656 | 1 | 5 | 5 | 5 | 5 | 4.057 | 2.48 | 0.006 | 0.365 | 6.908 | 0.966 | 0.02 | 0.986 |  | MP |  |  | 41.44 | 2.51 | 37.05 | 39.56 | 309.7674 |  | 287.31 | 331.4 |  | 917.68 |  |  | 1536.39 | 1.5364 | C | EG | D | 2025-01-20 | 2025-01-22 | 2025-01-27 | 2025-01-29 | Shree Bayo | C | CP | 2025-02-12 | 2025-02-12 | Shree Bayo | C |  | Checling not done | 2025-07-14 | 2025-07-16 | Ramesh Kumar | C |  |  | 1001 | Jai Swami
[21 empty] | 280 | WFR |  |  |  |  | 0
| 32/1 | DA+0 | 6.362 | 25.448 | 203.584 | 1 | 5 | 5 | 5 | 5 | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.428 | 0.011 | 0.439 |  | MP |  |  | 148.8 | 1.61 | 17.58 | 19.19 | 148.8432 |  | 255.02 | 289.23 | 691.07 |  | 1432.6 |  | 2667.92 | 2.6679 | C | D | D | 2025-01-17 | 2025-01-19 | 2025-01-21 | 2025-01-23 | Shree Bayo | C | CP | 2025-02-12 | 2025-02-12 | Shree Bayo | C |  | D | 2025-05-29 | 2025-05-30 | Ramesh Kumar
[22 empty] | WFR |  |  |  |  | 0
| 32/2 | DA+0 | 6.362 | 25.448 | 203.584 | 1 | 2 | 2 | 2 | 2 | 2.25 | 2.188 | 0.002 | 0.183 | 4.623 | 0.244 | 0.005 | 0.249 |  | MP |  |  | 91.76 | 0.8 | 7.8 | 8.6 | 66.42 |  | 130.54 | 491.04 |  | 302.15 | 236.06 |  | 1159.79 | 1.1598 | C | D | D | 2025-02-10 | 2025-02-12 | 2025-02-14 | 2025-02-15 | Shree Bayo | C | CP | 2025-03-03 | 2025-03-03 | Shree Ram Bio | C |  | D | 2025-05-24 | 2025-05-26 | Ramesh Kumar (M)
[22 empty] | DFR |  |  |  |  | 0
196 | 33/0 (New) | DB+6 | 9.654 | 38.616 | 308.928 | [5 empty] | 4.144 | 3.695 | 0.0047 | 0.298 | 8.1417 | 0.481 | 0.012 | 0.493 |  | MP |  |  | 41.44 | 0.97 | 14.75 | 15.72 | 123.1918 | 3321 | 73.73 | 301.5 |  | 206.46 |  |  | 581.69 | 0.58169 | C | [5 empty] | 2026-04-09 | Yash infra
[21 empty] | 373.16 | DFR |  |  |  |  | 0
197 | 33/1 (New) | DD+18 | 16.654 | 66.616 | 532.928 | [5 empty] | 8.897 | 8.801 | 0.0093 | 0.752 | 18.4593 | 1.116 | 0.032 | 1.148 |  | MP |  |  | 119.36 | 2.31 | 27.89 | 30.2 | 235.0498 | 7858.21 | 89.9 |  | 1115.34 | 198.68 |  |  | 1403.92 | 1.4039 | U/P | [6 empty] | SB
|  |  | 16.654 | [17 empty] | 159.04 | DFR |  |  |  |  | 0
198 | 34/0 (New) | DD+18 | 16.654 | 66.616 | 532.928 | [5 empty] | 8.897 | 8.801 | 0.0093 | 0.752 | 18.4593 | 1.116 | 0.032 | 1.148 |  | MP |  |  |  | 2.31 | 27.89 | 30.2
|  |  | 16.654 | [17 empty] | 236.01 | DFR
199 | 35/0 (New) | DD+18 | 16.654 | 66.616 | 532.928 | [5 empty] | 8.897 | 8.801 | 0.0093 | 0.752 | 18.4593 | 1.116 | 0.032 | 1.148 |  | MP |  |  |  | 2.31 | 36.66 | 38.97
[21 empty] | 49.95 | [15 empty] | 198 |  | 171 | [5 empty] | 197 |  |  |  |  | 197 |  | 139 |  |  |  | 191
[35 empty] | 0 | [18 empty] | 16
Formulas:
Excavation = [DOC]-1
Excavation = [Concreting]-15
DOC = [Concreting]-2
DOC = [DOS]
DOS = [DOC]-2
DOS = [DOC]
Concreting = [DOC]
Concreting = [DOC]+1

## Stringing-220kV
Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc
Progress of 220kV Line |  |  |  |  | Stringing Progress (Conductor & Earthwire) | [11 empty] | OPGW Progress
Stringing Section |  |  | 2026-04-14 | 61.1993 |  |  | 0 | 61.1993 |  | 0 | 61.1993 | [6 empty] | 0 | 53.7218 |  | 0 | 53.7218
Sl. No. | Section |  | Section Length (m) | Stretch Readiness | Insulator Hoisting | Conductor Paying Out |  |  | Final Sag |  |  | Clipping | Jumper | Sub-Contractor Name | MP | Remarks | OPGW Paying Out |  |  | OPGW Final Sag |  |  | Sub-Contractor Name
| From | To |  |  |  | Status | DOS | DOC | Status | DOS | DOC | Status | Status |  |  |  | Status | DOS | DOC | Status | DOS | DOC
1 | Gnty | 0/0 | 0.047 | C | C | C | 2026-01-31 | 2026-02-02 | C | 2026-01-31 | 2026-02-02 |  |  | Harshvivek
2 | 0/0 | 1/0 | 439.47 | C | C | C | 2025-05-19 | 2025-05-24 | C | 2025-05-26 | 2025-05-28 | C | C | National
3 | 1/0 | 1A/0 | 1037.32 | C | C | C | 2025-05-19 | 2025-05-24 | C | 2025-05-26 | 2025-05-28 | C | C | National
4 | 1A/0 | 1A/2 | 609 | C | C | C | 2025-06-29 | 2025-06-29 | C | 2025-06-30 | 2025-06-30 | C | C | National
5 | 1A/2 | 1B/0 | 232.098 | C | C | C | 2025-06-29 | 2025-06-29 | C | 2025-06-29 | 2025-06-29 | C |  | National
6 | 1B/0 | 1C/0 | 237.783 | C | C | C | 2026-04-09 | 2026-04-09 | C | 2026-04-10 | 2026-04-10 |  |  | National
7 | 1C/0 | 1D/0 | 675.21 | C | C | C | 2026-04-11 | 2026-04-13 | C | 2026-04-14 | 2026-04-14 |  |  | National
8 | 1D/0 | 1E/0 | 699.92 | C | C | C | 2025-08-01 | 2025-08-02 | C | 2025-08-04 | 2025-08-07 | C | C | Dilruba Bibi
9 | 1E/0 | 2/0 | 356.664 | C | C | C | 2025-07-26 | 2025-07-29 | C | 2025-07-31 | 2025-08-03 | C | C | Dilruba Bibi
10 | 2/0 | 3/0 | 174.205 | C | C | C | 2026-03-20 | 2026-03-20 | C | 2026-03-21 | 2026-03-21 | C | C | National Construction
11 | 3/0 | 4/0 | 229.73 | C | C | C | 2026-04-06 | 2026-04-06 | C | 2026-04-07 | 2026-04-07 | C | C | National Construction
12 | 4/0 | 4/5 | 1733 | C | C | C | 2025-07-11 | 2025-07-14 | C | 2025-07-16 | 2025-07-18 | C | C | Dilruba Bibi
13 | 4/5 | 4/6 | 349 | C | C | C | 2025-07-11 | 2025-07-14 | C | 2025-07-16 | 2025-07-18 | C |  | Dilruba Bibi
14 | 4/6 | 4/7 | 360
15 | 4/7 | 4/8 | 460
16 | 4/8 | 4/9 | 230
17 | 4/9 | 4/10 | 371.51 | C | C | C | 2025-08-22 | 2025-08-25 | C | 2025-09-19 | 2025-09-21 | C | C | National
18 | 4/10 | 4/11 | 332.471 | C | C | C | 2025-08-22 | 2025-08-25 | C | 2025-09-19 | 2025-09-21 | C | C | National
19 | 4/11 | 4/15 | 1335.05 | C | C | C | 2025-08-22 | 2025-08-25 | C | 2025-09-10 | 2025-09-13 | C | C | National |  |  | C | 2026-03-24 | 2026-03-28 | C | 2026-03-28 | 2026-03-28
20 | 4/15 | 4/16 | 415 | C | C | C | 2025-08-22 | 2025-08-25 | C | 2025-08-31 | 2025-09-03 | C | C | National |  |  | C | 2026-03-24 | 2026-03-28 | C | 2026-03-28 | 2026-03-28
21 | 4/16 | 4/17 | 237 | C | C | C | 2025-08-22 | 2025-08-25 | C | 2025-09-16 | 2025-09-17 | C | C | National |  |  | C | 2026-03-24 | 2026-03-28 | C | 2026-03-28 | 2026-03-28
22 | 4/17 | 5/0 | 188.454 | C | C | C | 2025-08-28 | 2025-08-31 | C | 2025-09-07 | 2025-09-10 | C | C | National |  |  | C | 2026-03-24 | 2026-03-28 | C | 2026-03-28 | 2026-03-28
23 | 5/0 | 5/1 | 383 | C | C | C | 2025-08-28 | 2025-08-31 | C | 2025-09-08 | 2025-09-11 | C | C | National |  |  | C | 2026-03-24 | 2026-03-28 | C | 2026-03-28 | 2026-03-28
24 | 5/1 | 5A/0 | 952 | C | C | C | 2025-10-16 | 2025-10-16 | C | 2025-10-17 | 2025-10-19 | C | C | National |  |  | C | 2026-03-24 | 2026-03-28 | C | 2026-03-28 | 2026-03-28
25 | 5A/0 | 5A/1 | 322 | C | C | C | 2026-02-10 | 2026-02-12 | C | 2026-02-13 | 2026-02-14 | C | C | National |  |  | C | 2026-03-24 | 2026-03-28 | C | 2026-03-28 | 2026-03-28
26 | 5A/1 | 5A/2 | 284 | C | C | C | 2026-02-09 | 2026-02-10 | C | 2026-02-14 | 2026-02-15 | C | C | National |  |  | C | 2026-03-24 | 2026-03-28 | C | 2026-03-28 | 2026-03-28
27 | 5A/2 | 5B/0 | 282.74 | C | C | C | 2026-02-06 | 2026-02-09 | C | 2026-02-09 | 2026-02-10 | C | C | National |  |  | C | 2026-03-24 | 2026-03-28 | C | 2026-03-28 | 2026-03-28
28 | 5B/0 | 6/0 | 462.06 | C | C | C | 2026-01-28 | 2026-02-04 | C | 2026-02-07 | 2026-02-09 | C | C | National |  |  | C | 2026-03-24 | 2026-03-28 | C | 2026-03-28 | 2026-03-28
29 | 6/0 | 7/0 | 318.04 | C | C | C | 2026-01-28 | 2026-02-04 | C | 2026-02-04 | 2026-02-06 | C | C | National |  |  | C | 2026-03-19 | 2026-03-22 | C | 2026-03-23 | 2026-03-23
30 | 7/0 | 8/0 | 1147.05 | C | C | C | 2025-09-22 | 2025-09-24 | C | 2025-09-25 | 2025-09-27 | C | C | National |  |  | C | 2026-03-19 | 2026-03-22 | C | 2026-03-23 | 2026-03-23
31 | 8/0 | 8A/0 | 173.57 | C | C | C | 2025-10-01 | 2025-10-01 | C | 2025-10-04 | 2025-10-05 | C | C | National |  |  | C | 2026-03-19 | 2026-03-22 | C | 2026-03-23 | 2026-03-23
32 | 8A/0 | 8B/0 | 336.5 | C | C | C | 2025-10-03 | 2025-10-03 | C | 2025-10-08 | 2025-10-09 | C | C | National |  |  | C | 2026-03-19 | 2026-03-22 | C | 2026-03-23 | 2026-03-23
33 | 8B/0 | 8C/0 | 900.14 | C | C | C | 2025-10-04 | 2025-10-04 | C | 2025-10-08 | 2025-10-09 | C | C | National |  |  | C | 2026-03-19 | 2026-03-22 | C | 2026-03-23 | 2026-03-23
34 | 8C/0 | 8D/0 | 318.76 | C | C | C | 2026-03-13 | 2026-03-13 | C | 2026-03-14 | 2026-03-14 | C | C | National |  |  | C | 2026-03-19 | 2026-03-22 | C | 2026-03-23 | 2026-03-23
35 | 8D/0 | 8D/1 | 436.1 | C | C | C | 2026-03-05 | 2026-03-06 | C | 2026-03-07 | 2026-03-08 | C | C | National |  |  | C | 2026-03-19 | 2026-03-22 | C | 2026-03-23 | 2026-03-23
36 | 8D/1 | 8D/3 | 657.08 | C | C | C | 2026-03-02 | 2026-03-05 | C | 2026-03-08 | 2026-03-09 | C | C | National |  |  | C | 2026-03-19 | 2026-03-22 | C | 2026-03-23 | 2026-03-23
37 | 8D/3 | 8D/4 | 459 | C | C | C | 2026-02-15 | 2026-02-19 | C | 2026-02-27 | 2026-02-27 | C | C | National |  |  | C | 2026-03-19 | 2026-03-22 | C | 2026-03-23 | 2026-03-23
38 | 8D/4 | 8D/5 | 195 | C | C | C | 2026-02-15 | 2026-02-19 | C | 2026-02-28 | 2026-02-28 | C | C | National |  |  | C | 2026-03-11 | 2026-03-16 | C | 2026-03-17 | 2026-03-18
39 | 8D/5 | 8D/6 | 295 | C | C | C | 2026-02-15 | 2026-02-19 | C | 2026-03-17 | 2026-03-17 | C | C | National |  |  | C | 2026-03-11 | 2026-03-16 | C | 2026-03-17 | 2026-03-18
40 | 8D/6 | 8E/0 | 380.25 | C | C | C | 2026-02-15 | 2026-02-19 | C | 2026-03-16 | 2026-03-16 | C | C | National |  |  | C | 2026-03-11 | 2026-03-16 | C | 2026-03-17 | 2026-03-18
41 | 8E/0 | 8E/1 | 428 | C | C | C | 2026-02-15 | 2026-02-19 | C | 2026-03-15 | 2026-03-15 | C | C | National |  |  | C | 2026-03-11 | 2026-03-16 | C | 2026-03-17 | 2026-03-18
42 | 8E/1 | 8E/2 | 419 | C | C | C | 2025-11-11 | 2025-11-14 | C | 2025-11-15 | 2025-11-18 | C | C | National |  |  | C | 2026-03-11 | 2026-03-16 | C | 2026-03-17 | 2026-03-18
43 | 8E/2 | 8E/5 | 900 | C | C | C | 2025-11-11 | 2025-11-14 | C | 2025-11-15 | 2025-11-18 | C | C | National |  |  | C | 2026-03-11 | 2026-03-16 | C | 2026-03-17 | 2026-03-18
44 | 8E/5 | 8E/6 | 343.87 | C | C | C | 2025-11-11 | 2025-11-14 | C | 2025-11-15 | 2025-11-18 | C | C | National |  |  | C | 2026-03-11 | 2026-03-16 | C | 2026-03-17 | 2026-03-18
45 | 8E/6 | 8E/7 | 499.13 | C | C | C | 2026-02-20 | 2026-02-22 | C | 2026-02-24 | 2026-02-24 | C | C | National |  |  | C | 2026-03-11 | 2026-03-16 | C | 2026-03-17 | 2026-03-18
46 | 8E/7 | 8E/8 | 434 | C | C | C | 2026-02-20 | 2026-02-23 | C | 2026-02-25 | 2026-02-25 | C | C | National |  |  | C | 2026-03-11 | 2026-03-16 | C | 2026-03-17 | 2026-03-18
47 | 8E/8 | 8E/11 | 919 | C | C | C | 2025-11-17 | 2025-11-19 | C | 2025-11-22 | 2025-11-23 | C | C | National |  |  | C | 2026-03-11 | 2026-03-16 | C | 2026-03-17 | 2026-03-18
48 | 8E/11 | 8E/12 | 489 | C | C | C | 2025-11-05 | 2025-11-09 | C | 2025-11-11 | 2025-11-13 | C | C | National |  |  | C | 2025-12-17 | 2025-12-20 | C | 2025-12-21 | 2025-12-21
49 | 8E/12 | AP-9 | 382.48 | C | C | C | 2025-11-05 | 2025-11-09 | C | 2025-11-09 | 2025-11-11 | C | C | National |  |  | C | 2025-12-17 | 2025-12-20 | C | 2025-12-21 | 2025-12-21
50 | AP-9 | 9/4 | 1250.32 | C | C | C | 2025-11-05 | 2025-11-09 | C | 2025-11-09 | 2025-11-11 | C | C | National |  |  | C | 2025-12-17 | 2025-12-20 | C | 2025-12-21 | 2025-12-21
51 | 9/4 | 9/5 | 246.76 | C | C | C | 2025-10-26 | 2025-10-27 | C | 2025-10-28 | 2025-10-29 | C | C | National |  |  | C | 2025-12-17 | 2025-12-20 | C | 2025-12-21 | 2025-12-21
52 | 9/5 | AP-10 | 1697.24 | C | C | C | 2025-09-26 | 2025-09-30 | C | 2025-10-26 | 2025-10-27 | C | C | National |  |  | C | 2025-12-17 | 2025-12-20 | C | 2025-12-21 | 2025-12-21
53 | AP-10 | AP-11 | 1600.078 | C | C | C | 2025-10-10 | 2025-10-12 | C | 2025-10-12 | 2025-10-14 | C | C | National |  |  | C | 2025-12-26 | 2025-12-27 | C | 2025-12-28 | 2025-12-28
54 | AP-11 | AP-12 | 525.89 | C | C | C | 2025-10-10 | 2025-10-12 | C | 2025-10-12 | 2025-10-14 | C | C | National |  |  | C | 2025-12-26 | 2025-12-27 | C | 2025-12-28 | 2025-12-28
55 | AP-12 | AP-13 | 356.279 | C | C | C | 2025-10-01 | 2025-10-01 | C | 2025-10-08 | 2025-10-10 | C | C | National |  |  | C | 2025-12-26 | 2025-12-27 | C | 2025-12-28 | 2025-12-28
56 | AP-13 | AP-14 | 667.59 | C | C | C | 2025-12-18 | 2025-12-20 | C | 2025-12-24 | 2025-12-27 | C | C | National |  |  | C | 2025-12-26 | 2025-12-27 | C | 2025-12-28 | 2025-12-28
57 | AP-14 | 14/1 | 362 | C | C | C | 2025-12-18 | 2025-12-20 | C | 2025-12-24 | 2025-12-27 | C | C | National |  |  | C | 2025-12-26 | 2025-12-27 | C | 2025-12-28 | 2025-12-28
58 | 14/1 | 14/3 | 752 | C | C | C | 2025-12-18 | 2025-12-20 | C | 2025-12-21 | 2025-12-27 | C | C | National |  |  | C | 2025-12-26 | 2025-12-27 | C | 2025-12-28 | 2025-12-28
59 | 14/3 | AP-15 | 2536.18 | C | C | C | 2025-12-13 | 2025-12-15 | C | 2025-12-22 | 2025-12-23 | C |  | National |  |  | C | 2025-12-22 | 2025-12-24 | C | 2025-12-25 | 2025-12-25
60 | AP-15 | AP-16 | 3422.45 | C | C | C | 2025-06-17 | 2025-06-25 | C | 2025-06-20 | 2025-06-29 | C | C | Nemchand |  |  | C | 2025-09-28 | 2025-09-30 | C | 2025-10-01 | 2025-10-02
61 | AP-16 | AP-17 | 1307.65 | C | C | C | 2025-06-30 | 2025-07-06 | C | 2025-07-08 | 2025-07-11 | C | C | National |  |  | C | 2025-09-30 | 2025-10-02 | C | 2025-10-03 | 2025-10-04
62 | AP-17 | AP-18 | 1435.97 | C | C | C | 2025-06-30 | 2025-07-06 | C | 2025-07-08 | 2025-07-11 | C | C | National |  |  | C | 2025-10-02 | 2025-10-04 | C | 2025-10-05 | 2025-10-07
63 | AP-18 | AP-19 | 4210.131 | C | C | C | 2025-07-14 | 2025-07-15 | C | 2025-07-16 | 2025-07-18 | C | C | National |  |  | C | 2025-10-08 | 2025-10-09 | C | 2025-10-10 | 2025-10-11
64 | AP-19 | AP-20 | 1946.55 | C | C | C | 2025-07-20 | 2025-07-21 | C | 2025-07-21 | 2025-07-22 | C | C | National |  |  | C | 2025-12-07 | 2025-12-08 | C | 2025-12-08 | 2025-12-09
65 | AP-20 | AP-21 | 2994.77 | C | C | C | 2025-07-22 | 2025-07-24 | C |  |  | C | C | National |  |  | C | 2025-12-07 | 2025-12-08 | C | 2025-12-08 | 2025-12-09
66 | AP-21 | AP-22 | 4974.78 | C | C | C | 2025-08-04 | 2025-08-12 | C | 2025-08-18 | 2025-08-22 | C | C | National |  |  | C | 2025-11-26 | 2025-11-27 | C | 2025-11-27 | 2025-11-27
67 | AP-22 | AP-23 | 947.23 | C | C | C | 2025-08-08 | 2025-08-12 | C | 2025-09-07 | 2025-09-08 | C | C | National |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15
68 | AP-23 | AP-24 | 1926.75 | C | C | C | 2025-09-04 | 2025-09-06 | C | 2025-09-07 | 2025-09-08 | C | C | National |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15
69 | AP-24 | AP-25 | 190.524 | C | C | C | 2025-10-04 | 2025-10-04 | C | 2025-10-04 | 2025-10-04 | C | C | National |  | PLC | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15
70 | AP-25 | AP-26 | 173.541 | C | C | C | 2025-09-13 | 2025-09-15 | C | 2025-09-15 | 2025-09-16 | C | C | National |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15
71 | AP-26 | AP-27 | 142.384 | C | C | C | 2025-10-06 | 2025-10-06 | C | 2025-10-06 | 2025-10-06 | C | C | National |  | PLC | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15
72 | AP-27 | AP-28 | 77.015 | C | C | C | 2025-11-02 | 2025-11-02 | C | 2025-12-03 | 2025-12-05 | C | C | National |  | PLC | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15
73 | AP-28 | 28/1 | 42.266 | C | C | C | 2025-11-02 | 2025-11-02 | C | 2025-12-03 | 2025-12-05 | C | C | National |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15
74 | 28/1 | 28/2 | 54.573 | C | C | C | 2025-11-02 | 2025-11-02 | C | 2025-12-03 | 2025-12-05 | C | C | National |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15
75 | 28/2 | AP-29 | 41.886 | C | C | C | 2025-09-16 | 2025-09-16 | C | 2025-09-17 | 2025-09-17 | C | C | National |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15
76 | AP-29 | 29A/0 | 353.284 | C | C | C | 2025-09-15 | 2025-09-15 | C | 2025-09-16 | 2025-09-16 | C | C | National |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15
77 | 29A/0 | AP-30 | 1860.55 | C | C | C | 2025-07-16 | 2025-07-20 | C | 2025-08-28 | 2025-08-31 | C | C | National |  |  | C | 2025-11-28 | 2025-12-01 | C | 2025-11-28 | 2025-12-01
78 | AP-30 | AP-31 | 2332.92 | C | C | C | 2025-07-08 | 2025-07-13 | C | 2025-07-16 | 2025-07-22 | C |  | Kohinoor |  |  | C | 2025-11-28 | 2025-12-01 | C | 2025-11-28 | 2025-12-01
79 | AP-31 | AP-32 | 743.35
80 | AP-32 | 33/0 | 909.22
81 | 33/0 | 34/0 | 209
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
4
[7 empty] | 16 |  |  |  | 0
7
[6 empty] | 952 | 0.952
[6 empty] | 173.57 | 0.17357
[6 empty] | 336.5 | 0.3365
[6 empty] | 900.14 | 0.90014
[6 empty] | 1697.24 | 1.6972
[6 empty] | 1600.078 | 1.6001
[6 empty] | 525.89 | 0.52589
[6 empty] | 356.279 | 0.35628
[6 empty] | 190.524 | 0.19052
[6 empty] | 142.384 | 0.14238
Formulas:
DOC = [DOS]+2
DOC = [DOS]
DOS = [DOC]
DOS = [DOC]-1

## Stringing-132KV
Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc
Progress of 220kV Line |  |  |  |  | Stringing Progress (Conductor & Earthwire) | [12 empty] | OPGW Progress
Stringing Section |  |  | 2026-04-14 | 4.9968 |  |  | 0 | 4.9968 |  | 0 | 4.9968 | [7 empty] | 0 | 0 |  | 0 | 0
Sl. No. | Section |  | Section Length (m) | Stretch Readiness | Insulator Hoisting | Conductor Paying Out |  |  | Final Sag |  |  | Clipping | Spacer | Jumper | Sub-Contractor Name | MP | Remarks | OPGW Paying Out |  |  | OPGW Final Sag |  |  | Sub-Contractor Name
| From | To |  |  |  | Status | DOS | DOC | Status | DOS | DOC | Status | Status | Status |  |  |  | Status | DOS | DOC | Status | DOS | DOC
1 | Hydro GTY | Existing Tower-1 | 58.79
2 | Existing Tower-1 | Exting Tower-2 | 149.12
3 | Exting Tower-2 | Exting Tower-3 | 128.1
4 | Exting Tower-3 | Exting Tower-4 | 252.72
5 | Exting Tower-4 | Exting Tower-5 | 146.74
6 | Exting Tower-5 | Exting Tapping Tower-6 | 190.05
7 | Exting Tapping Tower-6 | Exting Tower-7 | 83.39
8 | Exiting Tower-7 | SC-5 | 120.53
9 | SC-5 | SC-4 | 259.51
10 | SC-4 | Sc-3 | 256.61
11 | Sc-3 | SC-2 | 277.95
12 | SC-2 | SC-1 | 202.25
13 | SC-1 | 1/0 | 62.76
14 | 1/0 | 2/0 | 278.15
15 | 2/0 | 2/1 | 234.56
16 | 2/1 | 3/0 | 249.04
17 | 3/0 | 3/1 | 256
18 | 3/1 | 4/0 | 226.52
19 | 4/0 | 4/1 | 43.62 | C | C | C | 2026-03-30 | 2026-03-31 | C | 2026-04-01 | 2026-04-02
20 | 4/1 | 4/2 | 52 | C | C | C | 2026-03-30 | 2026-03-31 | C | 2026-03-31 | 2026-03-31 | C | C | C
21 | 4/2 | 5/0 | 47.06 | C | C | C | 2026-03-30 | 2026-03-31 | C | 2026-04-01 | 2026-04-02 | C | C | C | National Construction
22 | 5/0 | 6/0 | 286.44 | C | C | C | 2026-03-25 | 2026-03-25 | C | 2026-04-01 | 2026-04-02 | C | C | C | National Construction
23 | 6/0 | 6/1 | 317 | C | C | C | 2026-03-26 | 2026-03-27 | C | 2026-03-30 | 2026-03-30 | C | C | C | National Construction
24 | 6/1 | 6/2 | 328 | C | C | C | 2026-03-26 | 2026-03-27 | C | 2026-03-30 | 2026-03-30 | C | C | C | National Construction
25 | 6/2 | 6/3 | 297 | C | C | C | 2026-03-26 | 2026-03-27 | C | 2026-03-30 | 2026-03-30 | C | C | C | National Construction
26 | 6/3 | 6/4 | 251 | C | C | C | 2026-03-26 | 2026-03-27 | C | 2026-03-30 | 2026-03-30 | C | C | C | National Construction
27 | 6/4 | 7/0 | 308.23 | C | C | C | 2026-03-26 | 2026-03-27 | C | 2026-03-30 | 2026-03-30 | C | C | C | National Construction
28 | 7/0 | 8/0 | 278.12 | C | C | C | 2026-03-23 | 2026-03-24 | C | 2026-03-29 | 2026-03-29 | C | C | C | National Construction
29 | 8/0 | 9/0 | 385.96 | C | C | C | 2026-03-17 | 2026-03-18 | C | 2026-03-19 | 2026-03-20 | C | C | C | Sawariya seth
30 | 9/0 | 10/0 | 259.92 | C | C | C | 2026-03-17 | 2026-03-18 | C | 2026-03-19 | 2026-03-20 |  |  |  | Sawariya seth
31 | 10/0 | 11/0 | 215.13
32 | 11/0 | 12/0 | 316.15
33 | 12/0 | 12/1 | 274 | C | C | C | 2026-03-13 | 2026-03-13 | C | 2026-03-16 | 2026-03-16 |  |  |  | Sawariya seth
34 | 12/1 | 13/0 | 293.28 | C | C | C | 2026-03-13 | 2026-03-13 | C | 2026-03-16 | 2026-03-16 | C | C |  | Sawariya seth
35 | 13/0 | 13/1 | 48.42 | C | C | C | 2026-03-12 | 2026-03-12 | C | 2026-03-12 | 2026-03-12 | C | C | C | Sawariya seth
36 | 13/1 | 13/2 | 58.24 | C | C | C | 2026-03-12 | 2026-03-12 | C | 2026-03-14 | 2026-03-14 | C | C | C | Sawariya seth
37 | 13/2 | 14/0 | 70.13 | C | C | C | 2026-03-15 | 2026-03-15 | C | 2026-03-15 | 2026-03-15 | C | C | C | Sawariya seth
38 | 14/0 | 15/0 | 220.7
39 | 15/0 | 15/1 | 262.95 | C | C | C | 2026-03-07 | 2026-03-09 | C | 2026-03-08 | 2026-03-09 | C | C | C | Sawariya seth
40 | 15/1 | 15/2 | 251.57 | C | C | C | 2026-03-07 | 2026-03-09 | C | 2026-03-08 | 2026-03-09 | C | C | C | Sawariya seth
41 | 15/2 | 15/3 | 271.76 | C | C | C | 2026-03-07 | 2026-03-09 | C | 2026-03-08 | 2026-03-09 | C | C | C | Sawariya seth
42 | 15/3 | 16/0 | 261.04 | C | C | C | 2026-03-07 | 2026-03-09 | C | 2026-03-08 | 2026-03-09 | C | C | C | Sawariya seth
43 | 16/0 | 16/1 | 37.42 | C | C | C | 2026-03-05 | 2026-03-06 | C | 2026-03-05 | 2026-03-06 |  |  |  | SK Basirul
44 | 16/1 | 16/2 | 71 | C | C | C | 2026-03-03 | 2026-03-03 | C | 2026-03-03 | 2026-03-03 |  |  |  | SK Basirul
45 | 16/2 | 17/0 | 37.52 | C | C | C | 2026-02-23 | 2026-02-23 | C | 2026-02-23 | 2026-02-23 |  |  |  | SK Basirul
46 | 17/0 | 18/0 | 165.147 | C | C | C | 2026-03-02 | 2026-03-03 | C | 2026-03-02 | 2026-03-03 |  |  |  | SK Basirul
47 | 18/0 | Gantry | 39.999 | C | C | C | 2026-02-20 | 2026-02-21 | C | 2026-02-20 | 2026-02-21 |  |  |  | SK Basirul

## VC-220kV
Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc | [35 empty] | 2026-04-14
[16 empty] | Visual Chart of 220kV Line | [10 empty] | Date |  | 2026-04-14 | [6 empty] | Fnd | Ear | Ere | T/W | Strng |  | OPGW
[40 empty] | P/O | FS
[36 empty] | 14 | 14 | 14 | 13 | 4.2407 | 4.2407
| 0/0 |  | 0/1 |  |  | 1/0 |  |  | 1/1 |  | 1/2 |  | 1A/0 |  |  | 1A/1 |  | 1A/2 |  | 1B/0 |  | 1C/0 |  | 1C/1 |  | 1D/0 |  | 1D/1 |  | 1E/0
| DD+0 |  | DA+3 |  |  | DC+0 |  |  | DA+0 |  | DA+3 |  | DC+3 |  |  | DA+3 |  | DC+0 |  | DD+3 |  | DD+9 |  | DA+6 |  | DC+0 |  | DA+0 |  | DD+6
|  | 196 |  |  | 196.7 |  |  | 334 |  | 319 |  | 384.3 |  |  | 329 |  | 280 |  | 232.1 |  | 237.8 |  | 334 |  | 341.2 |  | 306 |  | 393.9 |  | 356.7 |  |  | 4240.7
|  |  | RJ |  |  | RJ |  |  | RJ |  | RJ |  | RJ |  |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ
[36 empty] | 14 | 14 | 14 | 12 | 3.6143 | 3.6143
| 2/0 |  | 3/0 |  |  | 4/0 |  |  | 4/1 |  | 4/2 |  | 4/3 |  |  | 4/4 |  | 4/5 |  | 4/6 |  | 4/7 |  | 4/8 |  | 4/9 |  | 4/10 |  | 4/11
| DC+6 |  | DD+3 |  |  | DB+9 |  |  | DA+6 |  | DA+3 |  | DA+6 |  |  | DA+3 |  | DB+0 |  | DB+9 |  | DB+9 |  | DB+9 |  | DB+6 |  | DB+6 |  | DB+0
|  | 174.2 |  |  | 229.7 |  |  | 391 |  | 328 |  | 333 |  |  | 350 |  | 331 |  | 349 |  | 360 |  | 460 |  | 230 |  | 371.5 |  | 332.5 |  | 424.4 |  |  | 4664.3
| RJ |  | RJ |  |  | RJ |  |  | RJ |  | RJ |  | RJ |  |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ
[36 empty] | 14 | 14 | 14 | 14 | 4.4369 | 4.4369
| 4/12 |  | 4/13 |  |  | 4/14 |  |  | 4/15 |  | 4/16 |  | 4/17 |  |  | 5/0 |  | 5/1 |  | 5/2 |  | 5/3 |  | 5A/0 |  | 5A/1 |  | 5A/2 |  | 5B/0
| DA+9 |  | DA+6 |  |  | DA+0 |  |  | DB+3 |  | DB+0 |  | DB+0 |  |  | DB+6 |  | DB+3 |  | DA+6 |  | DA+3 |  | DC+0 |  | DB+0 |  | DB+0 |  | DB+3
|  | 326.7 |  |  | 291.9 |  |  | 292 |  | 415 |  | 237 |  |  | 188.5 |  | 383 |  | 311 |  | 350 |  | 291 |  | 342 |  | 264 |  | 282.7 |  | 462.1 |  |  | 4436.9
| RJ |  | RJ |  |  | RJ |  |  | RJ |  | RJ |  | RJ |  |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ
[36 empty] | 15 | 15 | 15 | 15 | 4.2901 | 4.2901
| 6/0 |  | 7/0 |  |  | 7/1 |  |  | 7/2 |  | 7/3 |  | 8/0 |  |  | 8A/0 |  | 8B/0 |  | 8B/1 |  | 8B/2 |  | 8C/0 |  | 8D/0 |  | 8D/0A |  | 8D/1 |  | 8D/2
| DC+0 |  | DB+9 |  |  | DA+0 |  |  | DA+0 |  | DA+0 |  | DD+0 |  |  | DD+0 |  | DC+9 |  | DA+0 |  | DA+0 |  | DD+0 |  | DD+0 |  | DA+3 |  | DD+6 |  | DA+6
|  | 318 |  |  | 364 |  |  | 279 |  | 252 |  | 257.1 |  |  | 170.7 |  | 336.5 |  | 365 |  | 280 |  | 255.1 |  | 318.8 |  | 311.6 |  | 124.5 |  | 264.8 |  | 393 | 4290.1 | 393393
| RJ |  | RJ |  |  | RJ |  |  | RJ |  | RJ |  | RJ |  |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ
[36 empty] | 14 | 14 | 14 | 13 | 4.9742 | 4.9742
| 8D/3 |  | 8D/4 |  |  | 8D/5 |  |  | 8D/6 |  | 8E/0 |  | 8E/1 |  |  | 8E/2 |  | 8E/3 |  | 8E/4 |  | 8E/5 |  | 8E/6 |  | 8E/7 |  | 8E/8 |  | 8E/9
| DB+0 |  | DB+3 |  |  | DB+0 |  |  | DB+0 |  | DC+0 |  | DB+3 |  |  | DB+9 |  | DA+3 |  | DA+0 |  | DB+9 |  | DB+9 |  | DB+3 |  | DB+9 |  | DA+0
|  | 459 |  |  | 195 |  |  | 295 |  | 380.2 |  | 428 |  |  | 419 |  | 345 |  | 296 |  | 259 |  | 343.9 |  | 499.1 |  | 434 |  | 295 |  | 326
| RJ |  | RJ |  |  | RJ |  |  | RJ |  | RJ |  | MP |  |  | MP |  | MP |  | MP |  | MP |  | MP |  | MP |  | MP |  | MP
4974.2
[36 empty] | 14 | 14 | 14 | 14 | 4.5814 | 4.5814
| 8E/10 |  | 8E/11 |  |  | 8E/12 |  |  | AP-9 |  | 9/1 |  | 9/2 |  |  | 9/3 |  | 9/4 |  | 9/5 |  | 9/6 |  | 9/7 |  | 9/8 |  | 9/9 |  | AP-10
| DA+6 |  | DB+3 |  |  | DB+0 |  |  | DC+9 |  | DA+0 |  | DA+3 |  |  | DA+0 |  | DB+0 |  | DB+6 |  | DA+9 |  | DA+0 |  | DA+0 |  | DA+3 |  | DD+0
|  | 298 |  |  | 489 |  |  | 382.5 |  | 372.4 |  | 350 |  |  | 303.6 |  | 224.3 |  | 246.8 |  | 418.2 |  | 298.7 |  | 358.7 |  | 366.1 |  | 255.6 |  | 217.5 |  |  | 4581.4
| MP |  | MP |  |  | MP |  |  | MP |  | MP |  | MP |  |  | MP |  | MP |  | MP |  | MP |  | MP |  | MP |  | MP |  | MP
[36 empty] | 14 | 14 | 14 | 14 | 4.7964 | 4.7964
| 10/1 |  | 10/2 |  |  | 10/3 |  |  | 10/4 |  | AP-11 |  | 11/1 |  |  | AP-12 |  | AP-13 |  | 13/1 |  | AP-14 |  | 14/1 |  | 14/2 |  | 14/3 |  | 14/4
| DA+3 |  | DA+9 |  |  | DA+0 |  |  | DA+3 |  | DC+0 |  | DA+0 |  |  | DD+0 |  | DC+3 |  | DA+3 |  | DC+3 |  | DB+0 |  | DA+6 |  | DB+0 |  | DA+6
|  | 371.6 |  |  | 365.9 |  |  | 345.8 |  | 299.3 |  | 296 |  |  | 229.9 |  | 356.3 |  | 314 |  | 353.6 |  | 362 |  | 387 |  | 365 |  | 419 |  | 331 |  |  | 4796.4
| MP |  | MP |  |  | MP |  |  | MP |  | MP |  | RJ |  |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ
[36 empty] | 14 | 14 | 14 | 14 | 4.9182 | 4.9182
| 14/5 |  | 14/6 |  |  | 14/7 |  |  | 14/8 |  | 14/9 |  | AP-15 |  |  | 15/1 |  | 15/2 |  | 15/3 |  | 15/4 |  | 15/5 |  | 15/6 |  | 15/7 |  | 15/8
| DA+0 |  | DA+3 |  |  | DA+0 |  |  | DA+3 |  | DA+0 |  | DD+0 |  |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0
|  | 390 |  |  | 349 |  |  | 324 |  | 413 |  | 310.2 |  |  | 379 |  | 304 |  | 333 |  | 363 |  | 384 |  | 361 |  | 311 |  | 381 |  | 316 |  |  | 4918.2
| RJ |  | RJ |  |  | RJ |  |  | RJ |  | RJ |  | RJ |  |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ
[36 empty] | 14 | 14 | 14 | 14 | 4.8325 | 4.8325
| 15/9 |  | AP-16 |  |  | 16/1 |  |  | 16/2 |  | 16/3 |  | AP-17 |  |  | 17/1 |  | 17/2 |  | 17/3 |  | AP-18 |  | 18/1 |  | 18/2 |  | 18/3 |  | 18/4
| DA+0 |  | DC+0 |  |  | DA+3 |  |  | DA+3 |  | DA+3 |  | DC+3 |  |  | DA+6 |  | DA+3 |  | DA+6 |  | DC+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0
|  | 290.5 |  |  | 306 |  |  | 336 |  | 337 |  | 328.6 |  |  | 362 |  | 364 |  | 388 |  | 322 |  | 365.5 |  | 374 |  | 356.1 |  | 349.7 |  | 353.1 |  |  | 4832.5
| RJ |  | RJ |  |  | RJ |  |  | RJ |  | RJ |  | RJ |  |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ
[36 empty] | 14 | 14 | 14 | 14 | 4.6802 | 4.6802
| 18/5 |  | 18/6 |  |  | 18/7 |  |  | 18/8 |  | 18/9 |  | 18/10 |  |  | 18/11 |  | AP-19 |  | 19/1 |  | 19/2 |  | 19/3 |  | 19/4 |  | 19/5 |  | AP-20
| DA+3 |  | DA+3 |  |  | DA+6 |  |  | DA+3 |  | DA+3 |  | DA+3 |  |  | DA+3 |  | DB+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB+0
|  | 374.2 |  |  | 341.3 |  |  | 348 |  | 384 |  | 269.7 |  |  | 394 |  | 300.6 |  | 315.4 |  | 329.6 |  | 383 |  | 323.7 |  | 328.8 |  | 266 |  | 321.9 |  |  | 4680.2
| RJ |  | RJ |  |  | RJ |  |  | RJ |  | RJ |  | RJ |  |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ
[36 empty] | 14 | 14 | 14 | 14 | 4.7541 | 4.7541
| 20/1 |  | 20/2 |  |  | 20/3 |  |  | 20/4 |  | 20/5 |  | 20/6 |  |  | 20/7 |  | 20/8 |  | AP-21 |  | 21/1 |  | 21/2 |  | 21/3 |  | 21/4 |  | 21/5
| DA+0 |  | DA+3 |  |  | DA+0 |  |  | DA+0 |  | DA+0 |  | DA+3 |  |  | DA+3 |  | DA+3 |  | DB+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3
|  | 352.1 |  |  | 347.3 |  |  | 339.4 |  | 330.9 |  | 280 |  |  | 369.5 |  | 360.6 |  | 293 |  | 345.9 |  | 310.9 |  | 380 |  | 358.2 |  | 311.1 |  | 375.2 |  |  | 4754.1
| RJ |  | RJ |  |  | RJ |  |  | RJ |  | RJ |  | RJ |  |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ
[36 empty] | 14 | 14 | 14 | 14 | 4.7088 | 4.7088
| 21/6 |  | 21/7 |  |  | 21/8 |  |  | 21/9 |  | 21/10 |  | 21/11 |  |  | 21/12 |  | 21/13 |  | AP-22 |  | 22/1 |  | 22/2 |  | AP-23 |  | 23/1 |  | 23/2
| DA+3 |  | DA+3 |  |  | DA+3 |  |  | DA+0 |  | DA+3 |  | DA+0 |  |  | DA+3 |  | DA+3 |  | DC+3 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+0 |  | DA+0
|  | 369.1 |  |  | 371 |  |  | 356.5 |  | 363.3 |  | 370.3 |  |  | 330 |  | 390.1 |  | 343.4 |  | 326.5 |  | 302.5 |  | 318.2 |  | 315.5 |  | 249.3 |  | 303.1 |  |  | 4708.8
| RJ |  | RJ |  |  | RJ |  |  | RJ |  | RJ |  | RJ |  |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ |  | RJ
[36 empty] | 14 | 14 | 14 | 14 | 3.2597 | 3.2597
| 23/3 |  | 23/4 |  |  | 23/5 |  |  | AP-24 |  | AP-25 |  | AP-26 |  |  | AP-27 |  | AP-28 |  | 28/1 |  | 28/2 |  | AP-29 |  | 29A/0 |  | 29A/1 |  | 29A/2
| DA+0 |  | DA+3 |  |  | DA+0 |  |  | DD+9 |  | DD+18 |  | DD+18 |  |  | DD+18 |  | DD+0 |  | Gantry |  | Gantry |  | DD+3 |  | DC+6 |  | DA+0 |  | DA+6
|  | 354.9 |  |  | 320.2 |  |  | 383.9 |  | 190.5 |  | 178.3 |  |  | 148.4 |  | 61.2 |  | 42.3 |  | 54.6 |  | 41.9 |  | 344.5 |  | 393 |  | 359 |  | 387 |  |  | 3259.7
| RJ |  | MP |  |  | MP |  |  | MP |  | MP |  | MP |  |  | MP |  | MP |  | MP |  | MP |  | MP |  | MP |  | MP |  | MP
[36 empty] | 12 | 12 | 12 | 12 | 3.0545 | 3.0545
| 29A/3 |  | 29A/4 |  |  | AP-30 |  |  | 30/1 |  | 30/2 |  | 30/3 |  |  | 30/4 |  | 30/5 |  | 30/6 |  | 31/0 |  | 31/1 |  | AP-32 |  | 32/1 |  | 32/2
| DA+6 |  | DA+3 |  |  | DB+0 |  |  | DA+0 |  | DA+0 |  | DA+0 |  |  | DA+0 |  | DA+0 |  | DA+0 |  | DB+0 |  | DA+6 |  | DC+0 |  | DA+0 |  | DA+0
|  | 346 |  |  | 375.6 |  |  | 341.7 |  | 321.5 |  | 312.4 |  |  | 358.4 |  | 319.2 |  | 342.4 |  | 337.3 |  | 371.8 |  | 371.5 |  | 280 | [6 empty] | 4077.8
| MP |  | MP |  |  | MP |  |  | MP |  | MP |  | MP |  |  | MP |  | MP |  | MP |  | MP |  | MP |  | MP |  | MP |  | MP
| 33/0 |  | 33/1 |  |  | 34/0 |  |  | 35/0
| DB+6 |  | DD+18 |  |  | DD+18 |  |  | DD+18
|  | 373.16 |  | 159.04 |  | 236.01 |  | 49.95 | [25 empty] | 818.16
| MP |  | MP |  |  | MP |  |  | MP | [24 empty] | 64.0335
| Legend | [9 empty] | Crossing | [6 empty] | Progress at a Glance (220kV Line) | [17 empty] | 195 | 195 | 195 | 191 | 61.142 | 61.142 | 54
| Tack-Welding |  |  | final sag |  |  | rough sag |  |  |  | LT Line |  |  | NH/SH |  |  |  | Sl. No. | Activity |  |  | Unit | Total Qty |  | Completed |  | Balance |  | Remarks
[18 empty] | 1 | Detailed Survey |  |  | Kms | 64.0335 |  | 64.0335 |  | 0
| Erection | [9 empty] | 11kV Line | [6 empty] | 2 | Check Survey |  |  | Kms | 64.0335 |  | 64.0335 |  | 0
[18 empty] | 3 | Foundation |  |  | Nos | 199 |  | 195 |  | 4
[11 empty] | 33kV Line |  |  | Railway |  |  |  | 4 | Earthing |  |  | Nos | 199 |  | 195 |  | 4
[18 empty] | 5 | Erection |  |  | Nos | 199 |  | 195 |  | 4
| Foundation | [9 empty] | 220kV Line | [6 empty] | 6 | Tack-welding |  |  | Nos | 199 |  | 191 |  | 8
| Location No |  | 1/0 |  | 293 | 1/1 |  | 391 | 1A/0 | [8 empty] | 7 | Stringing (P/O) |  |  | Kms | 64.0335 |  | 61.142 |  | 2.8915
| Tower Type |  | DC+0 |  |  | DA+3 |  |  | DC+3 |  | 400kV Line |  |  | Water Reservior |  |  |  | 8 | Stringing (F/O) |  |  | Kms | 64.0335 |  | 61.142 |  | 2.8915
|  |  |  | Earthing |  |  |  | Forest | [9 empty] | 9 | OPGW |  |  | Kms | 64.0335 |  | 54 |  | 10.0335

## VC-132kV
Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc | [32 empty] | 2026-04-14
[13 empty] | Visual Chart of 132kV Line | [14 empty] | Date |  | 2026-04-14 |  |  | Fnd | Ear | Ere | T/W | Strng | Strng
4 Tower After Tapping toward CPP
Tapping Tower
[33 empty] | 9 | 9 | 7 | 7 | 1.3711 | 1.3711
|  |  | TT |  | 26 | 1/0 |  | 230.15 | 2/0 | 234.56 | 2/1 | 249.04 | 3/0 |  | 256 | 3/1 | 226.52 | 4/0 |  | 43.62 | 4/1 | 52 | 4/2 | 47.06 | 5/0 | 286.44 | 6/0 | 317 | 6/1 | 328 | 6/2 | 297
|  |  | DD+0 |  |  | DD+0 |  |  | DD+0 |  | DD+6 |  | DD+0 |  |  | DA+3 |  | DD+0 |  |  | Gantry |  | Gantry |  | DD+0 |  | DD+3 |  | DA+6 |  | DA+6
[33 empty] | 14 | 14 | 14 | 14 | 2.4903 | 2.4903
| 6/3 | 251 | 6/4 |  | 308.23 | 7/0 |  | 278.12 | 8/0 | 385.96 | 9/0 | 259.92 | 10/0 |  | 215.13 | 11/0 | 316.15 | 12/0 |  | 274 | 12/1 | 293.28 | 13/0 | 48.42 | 13/1 | 58.24 | 13/2 | 70.13 | 14/0 | 220.7 | 15/0 | 262.95
| DA+3 |  | DA+0 |  |  | DD+0 |  |  | DD+3 |  | DD+3 |  | DD+6 |  |  | DD+6 |  | DD+0 |  |  | DA+3 |  | DD+0 |  | Gantry |  | Gantry |  | DD+6 |  | DD+3
[19 empty] | rc |  | rc
Gantry
[33 empty] | 8 | 8 | 8 | 8 | 1.1355 | 1.1355
| 15/1 | 251.57 | 15/2 |  | 271.76 | 15/3 |  | 261.04 | 16/0 | 37.42 | 16/1 | 71 | 16/2 |  | 37.52 | 17/0 | 165.147 | 18/0 |  | 39.999
| DA+0 |  | DA+0 |  |  | DA+0 |  |  | DD+0 |  | Gantry |  | Gantry |  |  | DD+0 |  | DD (Aux)
[33 empty] | 31 | 31 | 29 | 29 | 4.9968 | 4.9968
| Legend | [9 empty] | Crossing | [6 empty] | Progress at a Glance (132kV Line) | [11 empty] | Date:
2026-04-14
| Tack-Welding |  |  | final sag |  |  | rough sag |  |  |  | LT Line |  |  | NH/SH |  |  |  | Sl. No. |  | Activity |  |  | Unit | Total Qty |  | Completed |  | Balance |  | Remarks
[18 empty] | 1 |  | Detailed Survey |  |  | Kms | 9.23 |  | 9.23 |  | 0
| Erection | [9 empty] | 11kV Line | [6 empty] | 2 |  | Check Survey |  |  | Kms | 9.23 |  | 9.23 |  | 0
[18 empty] | 3 |  | Foundation |  |  | Nos | 39 |  | 31 |  | 8
[11 empty] | 33kV Line |  |  | Railway |  |  |  | 4 |  | Earthing |  |  | Nos | 39 |  | 31 |  | 8
[18 empty] | 5 |  | Erection |  |  | Nos | 39 |  | 29 |  | 10
| Foundation | [9 empty] | 220kV Line | [6 empty] | 6 |  | Tack-welding |  |  | Nos | 39 |  | 29 |  | 10
| Location No |  | 1/0 |  | 293 | 1/1 |  | 391 | 1A/0 | [8 empty] | 7 |  | Stringing (P/O) |  |  | Kms | 9.23 |  | 4.9968 |  | 4.2332
| Tower Type |  | DC+0 |  |  | DA+3 |  |  | DC+3 |  | 765kV Line |  |  | Gas Pipeline |  |  |  | 8 |  | Stringing (F/S) |  |  | Kms | 9.23 |  | 4.9968 |  | 4.2332
|  |  |  | Earthing |  |  |  | Forest | [9 empty] | 9 |  | OPGW |  |  | Kms | 9.23 |  | 0 |  | 9.23

## Supply
Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc
Supply Progress of 220kV Line | [6 empty] | 2026-04-14
Sl. No. | Item | UoM | Scope | MFC Given | Received | Balance | Remarks
1 | Stub | Nos. | 199 | 201 | 201 | 0
| DA | Nos. |  | 117 | 117 | 0
| DB | Nos. |  | 39 | 39 | 0
| DC | Nos. |  | 20 | 20 | 0
| DD | Nos. |  | 17 | 17 | 0
| DD+18 | Nos. |  | 6 | 6 | 0
| Gantry UC | Nos. |  | 2 | 2 | 0
2 | Tower | Nos. | 201 | 201 | 197 | 4
| DA | Nos. |  | 117 | 117 | 0
| DB | Nos. |  | 39 | 38 | 1
| DC | Nos. |  | 20 | 20 | 0
| DD | Nos. |  | 17 | 17 | 0
| DD+18 | Nos. |  | 6 | 3 | 3
| Gantry UC | Nos. |  | 2 | 2 | 0
3 | Insulator | % | 100% |  | 100% | 0%
4 | Hardware Fittings | % | 100% |  | 100% | 0%
5 | OPGW | % | 100% |  | 100% | 0%
Supply Progress of 132kV Line | [6 empty] | 2026-04-14
Sl. No. | Item | UoM | Scope | MFC Given | Received | Balance | Remarks
1 | Stub | Nos. | 38 | 38 | 38 | 0
| A | Nos. | 9 | 9 | 9 | 0
| D | Nos. | 20 | 20 | 20 | 0
| Gantry | Nos. | 6 | 6 | 6 | 0
| DD Aux | Nos. | 1 | 1 | 1 | 0
| DD220KV | Nos. | 3 | 3 | 3 | 0
2 | Tower | Nos. | 38 | 38 | 38 | 0
| A | Nos. | 9 | 9 | 9 | 0
| D | Nos. | 20 | 20 | 19 | 1
| Gantry | Nos. | 6 | 6 | 6 | 0
| DD Aux | Nos. | 1 | 1 | 1 | 0
| DD220KV | Nos. | 3 | 3 | 2 | 1
3 | Insulator | % | 100% |  | 100% | 0%
4 | Hardware Fittings | % | 100% |  | 100% | 0%
5 | OPGW | % | 100% |  | 100% | 0%

## Mail Body
Progress of 220kV Line | [13 empty] | Date : | 2026-04-14
Sr. No. | Description | UoM | Total Qty. | Previous month |  | Progress of Current Month (April'26) |  |  | Cumulative till current month |  |  | Resources Status |  |  | Remarks
|  |  |  | Cum. Target as per L2 | Cum. Progress | Target as per L2 | Today's Progress | Progress | Target as per L2 | Completed | Balance | Targeted Gang | Available Gang | Shortfall Gang
1 | Detailed Survey | KM | 64 | 64 | 64.178 | 0 | 0 | - | 64 | 64.178 | -0.178 | - | - | 0
2 | Check Survey | KM | 64 | 64 | 62.39 | 0 | 0 | 0 | 64 | 62.39 | -0.178 | 0 | 0 | 0
3 | Foundation | Nos | 199 | 199 | 195 | 4 | 0 | 1 | 199 | 196 | 3 | 1 | 1 | 0 | RCC of Location no. 33/1 Underprogress
4 | Earthing | Nos | 199 | 199 | 195 | 4 | 0 | 0 | 199 | 195 | 4
5 | Tower Erection | Nos | 199 | 199 | 195 | 4 | 0 | 0 | 199 | 195 | 4 | 0 | 0 | 0 | 0
6 | Tack-Welding | Nos | 199 | 199 | 182 | 27 | 2 | 9 | 199 | 191 | 8 | 0 | 0 | 0 | 8D/0 Tackwelding completed
7 | Stringing | [13 empty] | Conductor final sag for Section 1C/0 to 1D/0 Completed
i | Paying Out | KMs | 0 | 64 | 60.06 | 3.94 | 0 | 1.1393 | 0 | 61.1993 | 2.8007 | 1 | 1 | 0
ii | Final Sag | KMs | 64 | 64 | 60.06 | 3.94 | 0.675 | 1.1393 | 0 | 61.1993 | 2.8007 | 0 | 0 | 0
iii | OPGW | KMs | 64 | 64 | 53.7218 | 10.2782 | 0 | 0 | 64 | 53.7218 | 10.2782 | 0 | 0 | 0
Progress of 132kV Line | [13 empty] | Date : | 2026-04-14
Sr. No. | Description | UoM | Total Qty. | Previous month |  | Progress of Current Month (April'26) |  |  | Cumulative till current month |  |  | Resources Status |  |  | Remarks
|  |  |  | Cum. Target as per L2 | Cum. Progress | Target as per L2 | Today's Progress | Progress | Target as per L2 | Completed | Balance | Targeted Gang | Available Gang | Shortfall Gang
1 | Detailed Survey | KM | 9 | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0
2 | Check Survey | KM | 9 | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0
3 | Foundation | Nos | 39 | 39 | 31 | 5 | 1 | 3 | 39 | 34 | 5 | 2 | 2 | 0 | 3/0 RCC completed SC-1 Excavation Completed
4 | Earthing | Nos | 39 | 39 | 31 | 5 | 0 | 2 | 39 | 33 | 6
5 | Tower Erection | Nos | 39 | 39 | 29 | 5 | 0 | 0 | 39 | 29 | 10 | 0 | 0 | 0 | 0
6 | Tack-Welding | Nos | 39 | 39 | 29 | 0 | 0 | 0 | 39 | 29 | 10 | 0 | 0 | 0
7 | Stringing | [13 empty] | 0
i | Paying Out | KMs | 9 | 9 | 5 | 1.483 | 0 | -0.003174 | 9 | 4.9968 | 4.0032 | 0 | 0 | 0 | 0
ii | Final Sag | KMs | 9 | 9 | 4.62 | 1.483 | 0 | 0.37683 | 9 | 4.9968 | 4.0032 | 0 | 0 | 0
iii | OPGW | KMs | 9 | 9 | 0 | 9 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0