## Stringing Nov'25
S. No. | From AP | To AP | Span (m) | Tower Erection Status | Towers in section | Insulator Hoisting | Paying Out Start | Paying Out Completed | Final Sag Complete | Method | Gang Name | Gang Strength | Supervisor | Section Incharge
1 | 17/0 | 18/0 | 1.539 | Completed | 5 | 2025-10-31 | 2025-11-10 | 2025-11-13 | 2025-11-15 | TSE 1 | M R Constructions | 40 | Mr. Manoj Mahto/Mr.Chandrasekharan | Mr. Satyam Tiwari
2 | 16/0 | 17/0 | 4.762 | 16/11- TE Balance | 12 | 2025-11-15 | 2025-11-16 | 2025-11-20 | 2025-11-23 | TSE 1 | M R Constructions | 40 | Mr. Manoj Mahto/Mr.Chandrasekharan | Mr. Satyam Tiwari
3 | 15/0 | 16/0 | 1.909 | Completed | 5 | 2025-11-20 | 2025-11-21 | 2025-11-24 | 2025-11-27 | TSE 1 | M R Constructions | 40 | Mr. Manoj Mahto/Mr.Chandrasekharan | Mr. Satyam Tiwari
4 | 34/0 | 34/1 | 0.248 | Completed | 2 | 2025-11-25 | 2025-11-26 | 2025-11-30 | 2025-11-30 | Manual | M R Constructions | 40 | Mr. Manoj Mahto/Mr.Chandrasekharan | Mr. Satyam Tiwari
5 | 34/1 | 34/2 | 0.43 | Completed | 1 | 2025-11-25 | 2025-11-26 | 2025-11-30 | 2025-11-30 | Manual | M R Constructions | 40 | Mr. Manoj Mahto/Mr.Chandrasekharan | Mr. Satyam Tiwari
6 | 34/2 | 35/0 | 0.248 | Completed | 1 | 2025-11-25 | 2025-11-26 | 2025-11-30 | 2025-11-30 | Manual | M R Constructions | 40 | Mr. Manoj Mahto/Mr.Chandrasekharan | Mr. Satyam Tiwari
7 | 13/0 | 14/0 | 4.91 | Completed | 12 | 2025-10-31 | 2025-11-11 | 2025-11-15 | 2025-11-18 | TSE 2 | Nasiruddin | 45 | Mr.Susanth Pal | Mr. Godvin John
8 | 14/0 | 15/0 | 0.498 | Completed | 1 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-20 | TSE 2 | Nasiruddin | 45 | Mr.Susanth Pal | Mr. Godvin John
9 | 11/0 | 12/0 | 4.751 | 11/8 - TE Balance | 11 | 2025-11-24 | 2025-11-25 | 2025-11-30 | 2025-11-30 | TSE 2 | Nasiruddin | 45 | Mr.Susanth Pal | Mr. Godvin John