## DPR_TA-413
LINE NAME- : 765 KV D/C BIKANER III - NEEMRANA II TL02
CLIENT-POWERGRID BIKANER NEEMRANA TRANSMISSION LIMITED (POWER GRID CORPORATION OF INDIA)
DAILY PROGRESS REPORT (TA-413)
NOA Date :- 12-March-2024 |  |  |  | Completion Date :- 11-December-2025 |  |  |  |  | Date :-11 Nov 2025.
SUPPLY VALUE = 331.89 Cr. |  |  |  | SERVICE VALUE = 58.06 Cr. |  |  |  |  | F&I VALUE = 6.86 Cr.
PARTICULARS | UOM | Total | Comp | Balance | 2025-11-01 |  | WIP | Cumulative | 2025-12-01 | 2026-01-01 | Remarks
|  | Qty | Till | as on | Plan | Actual |  |  | Plan | Plan
|  |  | 2025-10-01 | 1 Nov'25
Detail Survey | KM | 117.8509 | 117.8509 | 0 |  |  |  | 117.8509
Check Survey | KM | 117.8509 | 117.8509 | 0 |  |  |  | 117.8509
Stub Supply | SET | 313 | 313 | 0 |  |  |  | 313
FOUNDATION | NOS | 313 | 313 | 0 |  |  |  | 313
No of Gangs | [7 empty] | 0
Tower Supply | SETS | 306 | 306 | 0 |  |  |  | 306
TOWER ERECTION | NOS | 306 | 257 | 49 | 49 | 6 | 16 | 263 |  |  |  | 43 | 33
No of Gangs |  |  |  |  | 16 | 16 | 16 | 16
AL-59 Zebra Conductor | KM | 4285.056 | 4094.985 | 190.071 |  |  |  | 4094.985
G S Earthwire 7/3.66mm size | KM | 121.471 | 113.92 | 7.551 |  |  |  | 113.92 |  |  | Balance Supply 08 KM
Insulator Supply | EA | 11844 | 10480 | 1364 |  |  |  | 10480 |  |  | Balance Supply 160KN- 116 Balance Supply 210KN- 1248
Hardware Fittings Supply | % | 100% | 100% | 0% |  |  |  | 100%
Stringing | KM | 117.8509 | 26.417 | 91.4339 | 20 |  | 5.321 | 26.417 | 35 | 36.4326
TSE - Section | No | 37 | 7 | 30 | 7 |  | 1 | 7 | 12 | 11
Manual - Section | No | 23 | 1 | 22 | 3 |  | 1 | 1 | 15 | 4
No of Gangs |  |  |  |  | 2 |  | 1 | 2 | 4 | 5
OPGW Stringing | KM | 117.8509 | 18.212 | 99.6389 | 30 |  |  | 18.212 | 30 | 40
No of Gangs |  |  |  |  | 2 |  |  | 1 | 2 | 3

## Visual Chart
KEC INTERNATIONAL LIMITED
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 | [19 empty] | Visual Chart | [20 empty] | 2025-10-28
| S. No. |  | Description |  |  |  | UOM |  | Total qty |  | Completed |  |  | Balance |  |  |  | Power Line Crossing | [8 empty] | Stringing U/P | [8 empty] | Stringing completed
| 1 |  | Foundation |  |  |  | Nos |  | 313 |  | 313 |  |  | 0 | [12 empty] | Tack Welding U/P | [8 empty] | Tack Welding completed
| 2 |  | Earthing |  |  |  | Nos |  | 306 |  | 292 |  |  | 14 |  |  |  | NH / SH Crossing | [8 empty] | Erection U/P | [6 empty] | 4 |  | Erection completed
| 3 |  | Tower Erection |  |  |  | Nos |  | 306 |  | 263 |  |  | 43 | [10 empty] | 1 |  | Foundation U/P | [8 empty] | Foundation completed
| 4 |  | Rough Sag |  |  |  | KM |  | 117.8509 |  | 26.417 |  |  | 91.4339 |  |  |  | Railway Crossing | [15 empty] | 3
| 5 |  | Final Sag |  |  |  | KM |  | 117.8509 |  | 26.417 |  |  | 91.4339 | [10 empty] | 1 |  | Excavation U/P | [6 empty] | 2 |  | Excavation completed
[18 empty] | Canal | [17 empty] | Earthing completed
[15 empty] | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15
|  | Hold | [10 empty] | Gantry |  | 1/0 |  | 2A/0 |  | 2A/1 |  | 2A/2 |  | 2A/3 |  | 2A/4 |  | 2A/5 |  | 2A/6 |  | 3A/0 |  | 3A/1 |  | 3A/2 |  | 3A/3 |  | 3A/4 |  | 3A/5 |  | 3A/6
Foundation ROW
[9 empty] | Bikaner III Gantry |  |  |  |  | 150 | 3 | 290.21 | 3 | 378 | 3 | 381 | 3 | 419 | 3 | 422 | 3 | 399 | 3 | 423 | 3 | 414.992 | 3 | 409 | 3 | 402 | 3 | 409 | 3 | 337 | 3 | 365 | 3 | 378 | 3 | 391.467
|  | Erection ROW | [12 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
[13 empty] | Gantry |  | DD60+0 |  | DD45+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+6 |  | DD45+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0
ROW
| 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37
| 3B/0 |  | 3B/1 |  | 3B/2 |  | 3B/3 |  | 4/0 |  | 4/5 |  | 4A/0 |  | 4A/1 |  | 4A/2 |  | 4A/3 |  | 4A/4 |  | 4A/5 |  | 4A/6 |  | 5/0 |  | 5/1 |  | 5/2 |  | 5/3 |  | 5/4 |  | 5/5 |  | 5/6 |  | 5/7 |  | 5/8
| 3 | 356 | 3 | 439 | 3 | 377 | 3 | 455.07 | 3 | 344.163 | 3 | 365 | 3 | 340 | 3 | 419.999 | 3 | 415 | 3 | 365 | 3 | 330 | 3 | 457 | 3 | 354.612 | 3 | 428.389 | 3 | 340 | 3 | 375 | 3 | 365 | 3 | 460 | 3 | 380 | 3 | 410 | 3 | 400 | 3 | 420
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DB1+9 |  | DA+3 |  | DA+9 |  | DA+6 |  | DB2+9 |  | DA+6 |  | DB1+3 |  | DA+6 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+9 |  | DB1+6 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA-1.5 |  | DA+6 |  | DA+3 |  | DA+9 |  | DA+6
| 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59
| 5/9 |  | 5/10 |  | 5A/0 |  | 6/0 |  | 6/1 |  | 6/2 |  | 6/3 |  | 6/4 |  | 6/5 |  | 6/6 |  | 6/7 |  | 6/8 |  | 6/9 |  | 6/10 |  | 6/11 |  | 6/12 |  | 7/0 |  | 7/1 |  | 7/2 |  | 7/3 |  | 7/4 |  | 7/5
| 3 | 345 | 3 | 495 | 3 | 419.48 | 3 | 350.52 | 3 | 445 | 3 | 390 | 3 | 350 | 3 | 490 | 3 | 350 | 3 | 347 | 3 | 373 | 3 | 380 | 3 | 335 | 3 | 315 | 3 | 410 | 3 | 365.716 | 3 | 319.284 | 3 | 465 | 3 | 375 | 3 | 355 | 3 | 420 | 3 | 315
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+6 |  | DA+9 |  | DB1+12 |  | DB1+9 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+9 |  | DA+9 |  | DA-3 |  | DA+1.5 |  | DA+3 |  | DA+6 |  | DA+1.5 |  | DA-1.5 |  | DA+1.5 |  | DB2+0 |  | DA-3 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+6
| 60 |  | 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80 |  | 81
| 7/6 |  | 7A/0 |  | 7A/1 |  | 7A/2 |  | 7A/3 |  | 7A/4 |  | 7A/5 |  | 8/0 |  | 8/1 |  | 8/2 |  | 8/3 |  | 8/4 |  | 8/5 |  | 8/6 |  | 8/7 |  | 8/8 |  | 8/9 |  | 8/10 |  | 8/11 |  | 8A/0 |  | 9/0 |  | 9/1
| 3 | 450 | 3 | 435 | 3 | 385 | 3 | 390 | 3 | 405 | 3 | 390 | 3 | 429.77 | 3 | 350 | 3 | 330 | 3 | 390 | 3 | 400 | 3 | 345 | 3 | 350 | 3 | 335 | 3 | 415 | 3 | 375 | 3 | 375 | 3 | 375 | 3 | 415 | 3 | 466.629 | 3 | 418.372 | 3 | 410
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA-1.5 |  | DB1+6 |  | DA+1.5 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA-3 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+3 |  | DA+0 |  | DA+9 |  | DB1+12 |  | DB1+12 |  | DA+3
| 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100 |  | 101 |  | 102 |  | 103
| 9/2 |  | 9/3 |  | 9/4 |  | 9/5 |  | 9/6 |  | 9/7 |  | 9/8 |  | 9/9 |  | 9/10 |  | 9/11 |  | 10/0 |  | 10/1 |  | 10/2 |  | 11/0 |  | 12/0 |  | 13/0 |  | 13A/0 |  | 14/0 |  | 15/0 |  | 15/1 |  | 15/2 |  | 15/3
[30 empty] | 132kV | [5 empty] | 400kV
| 3 | 395 | 3 | 395 | 3 | 425 | 3 | 415 | 3 | 405 | 3 | 435 | 3 | 405 | 3 | 435 | 3 | 395 | 3 | 431.548 | 3 | 363.452 | 3 | 295 | 3 | 345.731 | 3 | 242.893 | 3 | 329.728 | 3 | 416.878 | 3 | 480.269 | 3 | 223.816 | 3 | 405.915 | 3 | 405 | 3 | 420 | 3 | 415
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+3 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB1+6 |  | DA+3 |  | DA+3 |  | DD45+0 |  | DB1+9 |  | DD60+9 |  | DB1+9 |  | DD60+18 |  | DD60+25 |  | DA+6 |  | DA+3 |  | DA+3
[27 empty] | NH-62 | [6 empty] | RC 4 Leg
| 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120 |  | 121 |  | 122 |  | 123 |  | 124 |  | 125
| 15/4 |  | 15/5 |  | 15/6 |  | 15/7 |  | 15/8 |  | 15/9 |  | 15/10 |  | 15/11 |  | 15/12 |  | 16/0 |  | 17/0 |  | 18/0 |  | 18/1 |  | 18/2 |  | 18/3 |  | 18/4 |  | 18/5 |  | 18/6 |  | 18/7 |  | 19/0 |  | 20/0 |  | 20/1
| 3 | 410 | 3 | 285 | 3 | 355 | 3 | 355 | 3 | 410 | 3 | 430 | 3 | 385 | 3 | 455 | 3 | 288.425 | 3 | 392.694 | 3 | 398.404 | 3 | 307.595 | 3 | 390 | 3 | 380 | 3 | 405 | 3 | 335 | 3 | 425 | 3 | 402 | 3 | 385.434 | 3 | 279.36 | 3 | 388.515 | 3 | 330
[5 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+6 |  | DA+3 |  | DA+9 |  | DA+0 |  | DA+1.5 |  | DA+0 |  | DA-1.5 |  | DA+0 |  | DA+6 |  | DC2+0 |  | DC1+3 |  | DB2+6 |  | DA+3 |  | DA+1.5 |  | DA+6 |  | DA-3 |  | DA+0 |  | DA+9 |  | DA+1.5 |  | DD60+3 |  | DD60+3 |  | DA-3
[9 empty] | Canal |  |  | ROW | [25 empty] | RLY
| 126 |  | 127 |  | 128 |  | 129 |  | 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147
| 20/2 |  | 20/3 |  | 20/4 |  | 20/5 |  | 20/6 |  | 21/0 |  | 21/1 |  | 21/2 |  | 21/3 |  | 21/4 |  | 21/5 |  | 22/0 |  | 23/0 |  | 23A/0 |  | 24/0 |  | 25/0 |  | 26/0 |  | 27/0 |  | 27/1 |  | 27/2 |  | 27/3 |  | 27/4
[24 empty] | 220kV | [5 empty] | 400kV |  |  |  | 765kV
| 3 | 340 | 3 | 420 | 3 | 375 | 3 | 355 | 3 | 341.652 | 3 | 326.348 | 3 | 427 | 3 | 410 | 3 | 405 | 3 | 300 | 3 | 415.187 | 3 | 259.048 | 3 | 440.455 | 3 | 496.685 | 3 | 244.029 | 3 | 237.428 | 3 | 203.479 | 3 | 453.688 | 3 | 345 | 3 | 360 | 3 | 410 | 3 | 350
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA-3 |  | DA+1.5 |  | DA+3 |  | DA+0 |  | DA-3 |  | DB1+0 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+0 |  | DC2+15 |  | DB2+9 |  | DB1+9 |  | DD60+18 |  | DD60+18 |  | DD60+35 |  | DD60+35 |  | DA+9 |  | DA-1.5 |  | DA+1.5 |  | DA+1.5
ROW
| 148 |  | 149 |  | 150 |  | 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169
| 27/5 |  | 27/6 |  | 28/0 |  | 29/0 |  | 29/1 |  | 29/2 |  | 29/3 |  | 29/4 |  | 29/5 |  | 29A/0 |  | 29A/1 |  | 29A/2 |  | 29A/3 |  | 29A/4 |  | 29A/5 |  | 29A/6 |  | 30/0 |  | 30/1 |  | 30/2 |  | 30/3 |  | 30/4 |  | 30/5
| 3 | 355 | 3 | 274.587 | 3 | 211.209 | 3 | 384.204 | 3 | 430 | 3 | 370 | 3 | 390 | 3 | 435 | 3 | 370 | 3 | 455 | 3 | 325 | 3 | 395 | 3 | 345 | 3 | 365 | 3 | 420 | 3 | 364.007 | 3 | 295.993 | 3 | 425 | 3 | 315 | 3 | 380 | 3 | 430 | 3 | 380
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA-1.5 |  | DA-3 |  | DC2-3 |  | DC1+0 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DB1+0 |  | DA+6 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+9 |  | DB1+0 |  | DA+0 |  | DA+9 |  | DA+3 |  | DA+9 |  | DA+0
[5 empty] | Exp. Way | [19 empty] | ROW
| 170 |  | 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189 |  | 190 |  | 191
| 30/6 |  | 30/7 |  | 30/8 |  | 30/9 |  | 30/10 |  | 31/0 |  | 31/1 |  | 31/2 |  | 31/3 |  | 31/4 |  | 31/5 |  | 31/6 |  | 31/7 |  | 31/8 |  | 31/9 |  | 31/10 |  | 32/0 |  | 32/1 |  | 32/2 |  | 32/3 |  | 32/4 |  | 32/5
| 3 | 335 | 3 | 395 | 3 | 390 | 3 | 350 | 3 | 428.239 | 3 | 376.761 | 3 | 410 | 3 | 430 | 3 | 380 | 3 | 445 | 3 | 385 | 3 | 420 | 3 | 415 | 3 | 310 | 3 | 445 | 3 | 316.608 | 3 | 385.51 | 3 | 390 | 3 | 410 | 3 | 430 | 3 | 390 | 3 | 439
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+6 |  | DA-3 |  | DA+3 |  | DA-3 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+1.5 |  | DA+3 |  | DA-1.5 |  | DA+6 |  | DA+9 |  | DA+0 |  | DA+0 |  | DA+1.5 |  | DA+4.5 |  | DB2+0 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+9
RC 4 Leg
| 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  | 210 |  | 211 |  | 212 |  | 213
| 32/6 |  | 32/7 |  | 32A/0 |  | 32A/1 |  | 33/0 |  | 33/1 |  | 33/2 |  | 33/3 |  | 33/4 |  | 33/5 |  | 33/6 |  | 33/7 |  | 33/8 |  | 33/9 |  | 34/0 |  | 34/1 |  | 34/2 |  | 34/3 |  | 34/4 |  | 34/5 |  | 34/6 |  | 34/7
[30 empty] | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5
| 3 | 360 | 3 | 479 | 3 | 402 | 3 | 438.439 | 3 | 441.561 | 3 | 395 | 3 | 435 | 3 | 405 | 3 | 420 | 3 | 405 | 3 | 415 | 3 | 355 | 3 | 380 | 3 | 398.203 | 3 | 441.798 | 3 | 395 | 3 | 375 | 3 | 445 | 3 | 395 | 3 | 435 | 3 | 330 | 3 | 330
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+9 |  | DA+3 |  | DB1+9 |  | DA+6 |  | DB1+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+1.5 |  | DB1+6 |  | DA+9 |  | DA+9 |  | DA+1.5 |  | DA+6 |  | DA+9 |  | DA+3 |  | DA+0
| RC 4 Leg | [7 empty] | RC 4 Leg |  | RC 4 Leg
| 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220 |  | 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230 |  | 231 |  | 232 |  | 233 |  | 234 |  | 235
| 34/8 |  | 34/9 |  | 34/10 |  | 34/11 |  | 34/12 |  | 35/0 |  | 35/1 |  | 35/2 |  | 35/3 |  | 35/4 |  | 35/5 |  | 35/6 |  | 35/7 |  | 35/8 |  | 35/9 |  | 35/10 |  | 35/11 |  | 36/0 |  | 36A/0 |  | 36A/1 |  | 36A/2 |  | 37/0
|  | 5 |  | 5 |  | 5 |  | 5
| 3 | 400 | 3 | 310 | 3 | 315 | 3 | 375 | 3 | 351.79 | 3 | 393.209 | 3 | 435 | 3 | 390 | 3 | 405 | 3 | 435 | 3 | 360 | 3 | 395 | 3 | 440 | 3 | 400 | 3 | 440 | 3 | 330 | 3 | 493.084 | 3 | 453.999 | 3 | 451 | 3 | 389 | 3 | 451.523 | 3 | 401.394
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+0 |  | DA+1.5 |  | DA-3 |  | DA+1.5 |  | DA+3 |  | DB2+0 |  | DA+6 |  | DA+6 |  | DA-3 |  | DA+9 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+1.5 |  | DA+3 |  | DA+3 |  | DB2+3 |  | DB1+9 |  | DA+3 |  | DA+9 |  | DB2+3
[17 empty] | ROW | [12 empty] | ROW |  |  |  |  | ROW | [5 empty] | HMPL OIL PIPE LINE
| 236 |  | 237 |  | 238 |  | 239 |  | 240 |  | 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250 |  | 251 |  | 252 |  | 253 |  | 254 |  | 255 |  | 256 |  | 257
| 37/1 |  | 37/2 |  | 37/3 |  | 37/4 |  | 37/5 |  | 37A/0 |  | 37A/1 |  | 37A/2 |  | 37A/3 |  | 37A/4 |  | 37A/5 |  | 37A/6 |  | 38/0 |  | 38/1 |  | 38/2 |  | 38/3 |  | 38/4 |  | 38/5 |  | 38/6 |  | 38/7 |  | 38/8 |  | 38/9
[12 empty] | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5
| 3 | 430 | 3 | 405 | 3 | 430 | 3 | 410 | 3 | 420 | 3 | 280 | 3 | 345 | 3 | 330 | 3 | 455 | 3 | 340 | 3 | 435 | 3 | 398.589 | 3 | 426.411 | 3 | 390 | 3 | 335 | 3 | 440 | 3 | 280 | 3 | 450 | 3 | 285 | 3 | 445 | 3 | 360 | 3 | 430
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+3 |  | DA+3 |  | DA-1.5 |  | DA+9 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+1.5 |  | DA+3 |  | DA+9 |  | DA+3 |  | DA+3 |  | DB1+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+1.5 |  | DA+3 |  | DA+6 |  | DA+9 |  | DA+1.5 |  | DA+0
| 258 |  | 259 |  | 260 |  | 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270 |  | 271 |  | 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279
| 38/10 |  | 39/0 |  | 39/1 |  | 39/2 |  | 39/3 |  | 39/4 |  | 39/5 |  | 39/6 |  | 39/7 |  | 39/8 |  | 39/9 |  | 39/10 |  | 39/11 |  | 40/0 |  | 40/1 |  | 40/2 |  | 40/3 |  | 40/4 |  | 40/5 |  | 40/6 |  | 40/7 |  | 40/8
5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5
| 3 | 322.266 | 3 | 392.73 | 3 | 395 | 3 | 385 | 3 | 340 | 3 | 395 | 3 | 410 | 3 | 415 | 3 | 415 | 3 | 350 | 3 | 425 | 3 | 350 | 3 | 444.081 | 3 | 260.918 | 3 | 385 | 3 | 435 | 3 | 385 | 3 | 455 | 3 | 370 | 3 | 400 | 3 | 350 | 3 | 470
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+3 |  | DB2+0 |  | DA-1.5 |  | DA+3 |  | DA+1.5 |  | DA+3 |  | DA+1.5 |  | DA+1.5 |  | DA+3 |  | DA+1.5 |  | DA+6 |  | DA+3 |  | DA+6 |  | DB1+6 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA-1.5
RC 4 Leg
| 280 |  | 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290 |  | 291 |  | 292 |  | 293 |  | 294 |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | 300 |  | 301
| 40/9 |  | 40/10 |  | 40/11 |  | 40A/0 |  | 41/0 |  | 41/1 |  | 42/0 |  | 42/1 |  | 42/2 |  | 42/3 |  | 43/0 |  | 43/1 |  | 43/2 |  | 43/3 |  | 43/4 |  | 43/5 |  | 43/6 |  | 43/7 |  | 43/8 |  | 44/0 |  | 44/1 |  | 44/2
| 3 | 355 | 3 | 485 | 3 | 315 | 3 | 410.607 | 3 | 358 | 3 | 465.782 | 3 | 419.998 | 3 | 375 | 3 | 464 | 3 | 424.891 | 3 | 341.866 | 3 | 375 | 3 | 375 | 3 | 355 | 3 | 405 | 3 | 375 | 3 | 385 | 3 | 415 | 3 | 409.546 | 3 | 400 | 3 | 427 | 3 | 366
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+9 |  | DA+3 |  | DA+9 |  | DB1+9 |  | DB1+9 |  | DA+9 |  | DB2+0 |  | DA+3 |  | DA+9 |  | DB1+9 |  | DB1+0 |  | DA-1.5 |  | DA+6 |  | DA-1.5 |  | DA+0 |  | DC2+0 |  | DA+3 |  | DA+0 |  | DA+9 |  | DB1+6 |  | DA+3 |  | DA+3
[21 empty] | ROW | [8 empty] | TP TWR
| 302 |  | 303 |  | 304 |  | 305 |  | 306 |  | Common Point
| 44/3 |  | 44/4 |  | 44/5 |  | 45/0 |  | 46/0
132KV
| 3 | 350 | 3 | 383 | 3 | 457.155 | 3 | 208.53 | 3
| 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+3 |  | DA+0 |  | DA+0 |  | DB1+9 |  | DB1+12
CP
Progress overview (Tower wise breakups)
| TOT |  | Total Qty in No's |  | FDN |  |  | ERE
[5 empty] | Comp. |  | Bal. | Comp. |  | Balance |  |  |  | SUNSURE(SOLAR) ROUTE DIVERTED AREA
| DA-3 |  | 12 |  | 12 |  | 0 | 10 |  | 2
| DA-1.5 |  | 12 |  | 12 |  | 0 | 8 |  | 4 |  |  |  | Existing (Approved ) route | [7 empty] | Modified Diverted route
| DA+0 |  | 33 |  | 33 |  | 0 | 24 |  | 9 |  |  |  | DA |  |  |  |  | 15 |  |  | DA | [5 empty] | 15
| DA+1.5 |  | 24 |  | 24 |  | 0 | 22 |  | 2 |  |  |  | DB1 |  |  |  |  | 1 |  |  | DB1 | [5 empty] | 1
| DA+3 |  | 70 |  | 70 |  | 0 | 67 |  | 3 |  |  |  | DB2 |  |  |  |  | 1 |  |  | DB2 | [5 empty] | 1
| DA+4.5 |  | 1 |  | 1 |  | 0 | 1 |  | 0 |  |  |  | DC1 |  |  |  |  | 0 |  |  | DC1 | [5 empty] | 0
| DA+6 |  | 47 |  | 47 |  | 0 | 42 |  | 5 |  |  |  | DC2 |  |  |  |  | 0 |  |  | DC2 | [5 empty] | 0
| DA+9 |  | 47 |  | 47 |  | 0 | 46 |  | 1 |  |  |  | DD45 |  |  |  |  | 1 |  |  | DD45 | [5 empty] | 2
| DB1+0 |  | 7 |  | 7 |  | 0 | 6 |  | 1 |  |  |  | DD60 |  |  |  |  | 1 |  |  | DD60 | [5 empty] | 1
| DB1+3 |  | 2 |  | 2 |  | 0 | 2 |  | 0 |  |  |  | Total |  |  |  |  | 19 |  |  | Total | [5 empty] | 20
| DB1+6 |  | 6 |  | 6 |  | 0 | 6 |  | 0
| DB1+9 |  | 12 |  | 12 |  | 0 | 10 |  | 2 |  |  |  |  | Foundation Dismentling required
| DB1+12 |  | 4 |  | 4 |  | 0 | 4 |  | 0
| DB2+0 |  | 5 |  | 5 |  | 0 | 5 |  | 0 | [5 empty] | 1 | 3/4 | DA+6 |  | Due to sunsure objection change in Route
| DB2+3 |  | 2 |  | 2 |  | 0 | 0 |  | 2 | [5 empty] | 2 | 3/6 | DA+3 |  | Due to sunsure objection change in Route
| DB2+6 |  | 1 |  | 1 |  | 0 | 1 |  | 0 | [5 empty] | 3 | 3/7 | DA+3 |  | Due to sunsure objection change in Route
| DB2+9 |  | 2 |  | 2 |  | 0 | 1 |  | 1 | [5 empty] | 4 | 3/8 | DA+0 |  | Due to sunsure objection change in Route
| DC1+0 |  | 1 |  | 1 |  | 0 | 1 |  | 0 | [5 empty] | 5 | 3/9 | DA+0 |  | Due to sunsure objection change in Route
| DC1+3 |  | 1 |  | 1 |  | 0 | 0 |  | 1 | [5 empty] | 6 | 3/10 | DA+9 |  | Due to sunsure objection change in Route
| DC2+0 |  | 2 |  | 2 |  | 0 | 0 |  | 2 | [5 empty] | 7 | 3/11 | DA+0 |  | Due to sunsure objection change in Route
| DC2-3 |  | 1 |  | 1 |  | 0 | 0 |  | 1
| DC2+15 |  | 1 |  | 1 |  | 0 | 1 |  | 0
| DD45+0 |  | 2 |  | 2 |  | 0 | 0 |  | 2
| DD45+3 |  | 1 |  | 1 |  | 0 | 1 |  | 0
| DD60+0 |  | 1 |  | 1 |  | 0 | 1 |  | 0
| DD60+3 |  | 2 |  | 2 |  | 0 | 2 |  | 0
| DD60+9 |  | 1 |  | 1 |  | 0 | 0 |  | 1
| DD60+18 |  | 3 |  | 3 |  | 0 | 0 |  | 3
| DD60+25 |  | 1 |  | 1 |  | 0 | 1 |  | 0
| DD60+35 |  | 2 |  | 2 |  | 0 | 1 |  | 1
| Total |  | 306 |  | 306 |  | 0 | 263 |  | 43
Global Footprint in 110+ countries*
*Includes EPC and Supply
Location Summary

## Erection Compiled
KEC International Limited
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Details of Erection | [6 empty] | 11483.7004 | 1069.918 |  | 2025-11-04
CUMM. SR.NO | MONTH SR.NO. | Location No | Type of Tower | Starting Date | Completion date | Gang name | Tower Weight | Revenue | Name of Supervisor | Status | Prop. Name
1 | 1 | 29A/2 | DA+6 | 2024-09-12 | 2024-09-21 | Bhagwan construction | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed
2 | 2 | 29/5 | DA+0 | 2024-09-21 | 2024-09-27 | Bhagwan construction | 36.1598 | 3.3689 | Manoj Kumar Gupta | Completed
3 | 1 | 29/3 | DA+0 | 2024-09-28 | 2024-10-03 | Bhagwan construction | 36.1598 | 3.3689 | Manoj Kumar Gupta | Completed
4 | 2 | 29/4 | DA+3 | 2024-10-03 | 2024-10-08 | Bhagwan construction | 37.9311 | 3.534 | Manoj Kumar Gupta | Completed
5 | 3 | 29A/6 | DA+9 | 2024-10-03 | 2024-10-14 | Bhagwan construction | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed
6 | 4 | 30/1 | DA+0 | 2024-10-09 | 2024-10-17 | Bhagwan construction | 36.1598 | 3.3689 | Kartik Mahto | Completed
7 | 5 | 29A/1 | DA+6 | 2024-10-14 | 2024-10-25 | Bhagwan construction | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed
8 | 1 | 34/8 | DA+0 | 2024-11-12 | 2024-11-24 | Vasu dev singh-1 | 36.1598 | 3.3689 | Raju Mahto | Completed
9 | 2 | 34/12 | DA+3 | 2024-11-14 | 2024-11-25 | Vasu dev singh-2 | 37.9311 | 3.534 | Mustak | Completed
10 | 1 | 34/4 | DA+6 | 2024-11-25 | 2024-12-04 | Vasu dev singh-1 | 43.8044 | 4.0812 | Raju Mahto | Completed
11 | 2 | 34/7 | DA+0 | 2024-11-26 | 2024-12-12 | Vasu dev singh-2 | 36.1598 | 3.3689 | Raju Mahto | Completed
12 | 3 | 34/3 | DA+1.5 | 2024-12-05 | 2024-12-16 | Vasu dev singh-1 | 37.1383 | 3.4601 | Manoj Kumar Gupta | Completed
13 | 4 | 8/1 | DA-3 | 2024-12-07 | 2024-12-16 | Punam Devi-2 | 34.7898 | 3.2413 | Sanjay Kumar | Completed
14 | 5 | 34/9 | DA+1.5 | 2024-12-13 | 2024-12-21 | Vasu dev singh-2 | 37.1383 | 3.4601 | Mustak & Abul | Completed
15 | 6 | 35/7 | DA+3 | 2024-12-13 | 2024-12-22 | Punam Devi-2 | 37.9311 | 3.534 | Kartik Mahto | Completed
16 | 7 | 7A/5 | DA+3 | 2024-12-17 | 2024-12-24 | Punam Devi-2 | 37.9311 | 3.534 | Sanjay Kumar | Completed
17 | 8 | 36A/1 | DA+3 | 2024-12-13 | 2024-12-25 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Sachinder
18 | 9 | 7/1 | DA-3 | 2024-12-15 | 2024-12-26 | Punam Devi-1 | 34.7898 | 3.2413 | Raju Mahto | Completed | Hazari Yadav
19 | 10 | 35/8 | DA+6 | 2024-12-23 | 2024-12-28 | Punam Devi-2 | 43.8044 | 4.0812 | Kartik Mahto | Completed | Gulshan Kumar
20 | 11 | 34/5 | DA+9 | 2024-12-17 | 2024-12-29 | Vasu dev singh-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Pawan
21 | 12 | 34/10 | DA-3 | 2024-12-22 | 2024-12-29 | Vasu dev singh-2 | 34.7898 | 3.2413 | Mustak & Abul | Completed | Praveen Kumar
22 | 13 | 7A/4 | DA+3 | 2024-12-24 | 2024-12-31 | Punam Devi-2 | 37.9311 | 3.534 | Raju Mahto | Completed | Dharmendra Das
23 | 1 | 7/2 | DA+6 | 2024-12-27 | 2025-01-03 | Punam Devi-1 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Hazari Yadav
24 | 2 | 35/11 | DA+3 | 2024-12-24 | 2025-01-03 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Sachinder
25 | 3 | 35/6 | DA+6 | 2024-12-29 | 2025-01-05 | Punam Devi-2 | 43.8044 | 4.0812 | Kartik Mahto | Completed | Gulshan Kumar
26 | 4 | 34/11 | DA+1.5 | 2024-12-30 | 2025-01-07 | Vasu dev singh-2 | 37.1383 | 3.4601 | Mustak & Abul | Completed | Praveen Kumar
27 | 5 | 7A/3 | DA+3 | 2025-01-01 | 2025-01-08 | Punam Devi-2 | 37.9311 | 3.534 | Raju Mahto | Completed | Dharmendra Das
28 | 6 | 34/6 | DA+3 | 2024-12-30 | 2025-01-09 | Vasu dev singh-1 | 37.9311 | 3.534 | Manoj Kumar Gupta | Completed | Pawan
29 | 7 | 8/5 | DA+9 | 2025-01-04 | 2025-01-09 | Punam Devi-1 | 45.697 | 4.2575 | Gangadin sahoo | Completed | Hazari Yadav
30 | 8 | 36A/2 | DA+9 | 2025-01-04 | 2025-01-11 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Sachinder
31 | 9 | 35/5 | DA+9 | 2025-01-06 | 2025-01-13 | Punam Devi-2 | 45.697 | 4.2575 | Kartik Mahto | Completed | Gulshan Kumar
32 | 10 | 8/6 | DA+3 | 2025-01-10 | 2025-01-15 | Punam Devi-1 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
33 | 11 | 7A/2 | DA+3 | 2025-01-08 | 2025-01-16 | Punam Devi-2 | 37.9311 | 3.534 | Raju Mahto | Completed | Dharmendra Das
34 | 12 | 35/1 | DA+6 | 2025-01-07 | 2025-01-19 | Vasu dev singh-2 | 43.8044 | 4.0812 | Mustak & Abul | Completed | Praveen Kumar
35 | 13 | 35/4 | DA+9 | 2025-01-14 | 2025-01-19 | Punam Devi-2 | 45.697 | 4.2575 | Kartik Mahto | Completed | Gulshan Kumar
36 | 14 | 8/7 | DA+3 | 2025-01-16 | 2025-01-20 | Punam Devi-1 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
37 | 15 | 34/2 | DA+9 | 2025-01-10 | 2025-01-21 | Vasu dev singh-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Pawan
38 | 16 | 37/4 | DA+9 | 2025-01-11 | 2025-01-22 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Sachinder
39 | 17 | 7A/1 | DA+1.5 | 2025-01-17 | 2025-01-22 | Punam Devi-2 | 37.1383 | 3.4601 | Raju Mahto | Completed | Dharmendra Das
40 | 18 | 35/9 | DA+1.5 | 2025-01-17 | 2025-01-24 | Punam Devi-2 | 37.1383 | 3.4601 | Kartik Mahto | Completed | Gulshan Kumar
41 | 19 | 8/8 | DA+9 | 2025-01-20 | 2025-01-25 | Punam Devi-1 | 45.697 | 4.2575 | Gangadin sahoo | Completed | Hazari Yadav
42 | 20 | 34/1 | DA+9 | 2025-01-21 | 2025-01-29 | Vasu dev singh-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Pawan
43 | 21 | 38/3 | DA+3 | 2025-01-24 | 2025-01-29 | Punam Devi-2 | 37.9311 | 3.534 | Kartik Mahto | Completed | Gulshan Kumar
44 | 22 | 8/9 | DA+3 | 2025-01-25 | 2025-01-30 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
45 | 23 | 37/5 | DA+3 | 2025-01-22 | 2025-01-30 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Sachinder
46 | 24 | 7A/0 | DB1+6 | 2025-01-22 | 2025-01-31 | Punam Devi-2 | 65.0278 | 6.0585 | Raju Mahto | Completed | Gopal Muni
47 | 25 | 34/0 | DB1+6 | 2025-01-17 | 2025-01-31 | Vasu dev singh-1 | 65.0278 | 6.0585 | Mustak & Abul | Completed | Praveen Kumar
48 | 1 | 8/10 | DA+0 | 2025-01-30 | 2025-02-03 | Punam Devi-4 | 36.1598 | 3.3689 | Gangadin sahoo | Completed | Hazari Yadav
49 | 2 | 38/6 | DA+6 | 2025-01-29 | 2025-02-04 | Punam Devi-1 | 43.8044 | 4.0812 | Kartik Mahto | Completed | Mithilesh
50 | 3 | 37A/2 | DA+1.5 | 2025-01-29 | 2025-02-07 | Punam Devi-3 | 37.1383 | 3.4601 | Haridas | Completed | Sachinder
51 | 4 | 33/6 | DA+6 | 2025-01-29 | 2025-02-08 | Vasu dev singh-2 | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed | Pawan
52 | 5 | 8/2 | DA+6 | 2025-02-03 | 2025-02-08 | Punam Devi-4 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Hazari Yadav
53 | 6 | 7/6 | DA-1.5 | 2025-01-31 | 2025-02-10 | Punam Devi-2 | 35.6018 | 3.317 | Raju Mahto | Completed | Gopal Muni
54 | 7 | 38/4 | DA+1.5 | 2025-02-05 | 2025-02-10 | Punam Devi-1 | 37.1383 | 3.4601 | Kartik Mahto | Completed | Mithilesh
55 | 8 | 8/0 | DB1+0 | 2025-02-09 | 2025-02-14 | Punam Devi-4 | 55.4509 | 5.1663 | Gangadin sahoo | Completed | Hazari Yadav
56 | 9 | 38/5 | DA+3 | 2025-02-11 | 2025-02-15 | Punam Devi-1 | 37.9311 | 3.534 | Kartik Mahto | Completed | Mithilesh
57 | 10 | 37A/1 | DA+3 | 2025-02-08 | 2025-02-16 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Sachinder
58 | 11 | 33/5 | DA+0 | 2025-01-31 | 2025-02-18 | Vasu dev singh-1 | 36.1598 | 3.3689 | Mustak & Abul | Completed | Praveen Kumar
59 | 12 | 38/9 | DA+0 | 2025-02-15 | 2025-02-18 | Punam Devi-1 | 36.1598 | 3.3689 | Kartik Mahto | Completed | Mithilesh
60 | 13 | 7/5 | DA+6 | 2025-02-11 | 2025-02-19 | Punam Devi-2 | 43.8044 | 4.0812 | Raju Mahto | Completed | Gopal Muni
61 | 14 | 8/3 | DA+9 | 2025-02-14 | 2025-02-19 | Punam Devi-4 | 45.697 | 4.2575 | Gangadin sahoo | Completed | Hazari Yadav
62 | 15 | 35/0 | DB2+0 | 2025-02-09 | 2025-02-23 | Vasu dev singh-2 | 59.5006 | 5.5436 | Manoj Kumar Gupta | Completed | Pawan
63 | 16 | 38/10 | DA+3 | 2025-02-18 | 2025-02-24 | Punam Devi-1 | 37.9311 | 3.534 | Kartik Mahto | Completed | Mithilesh
64 | 17 | 8/4 | DA+6 | 2025-02-20 | 2025-02-24 | Punam Devi-4 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Hazari Yadav
65 | 18 | 37A/3 | DA+3 | 2025-02-16 | 2025-02-25 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Sachinder
66 | 19 | 7/4 | DA+6 | 2025-02-20 | 2025-02-27 | Punam Devi-2 | 43.8044 | 4.0812 | Raju Mahto | Completed | Gopal Muni
67 | 20 | 9/1 | DA+3 | 2025-02-24 | 2025-02-28 | Punam Devi-4 | 37.9311 | 3.534 | Raju Mahto | Completed | Hazari Yadav
68 | 21 | 37A/5 | DA+3 | 2025-02-24 | 2025-02-28 | Punam Devi-1 | 37.9311 | 3.534 | Prabhakar | Completed | Mithilesh
69 | 1 | 33/8 | DA+3 | 2025-02-18 | 2025-03-04 | Vasu dev singh-1 | 37.9311 | 3.534 | Kartik Mahto | Completed | Praveen Kumar
70 | 2 | 9/3 | DA+0 | 2025-03-01 | 2025-03-04 | Punam Devi-4 | 36.1598 | 3.3689 | Raju Mahto | Completed | Hazari Yadav
71 | 3 | 38/1 | DA+0 | 2025-03-01 | 2025-03-06 | Punam Devi-1 | 36.1598 | 3.3689 | Prabhakar | Completed | Mithilesh
72 | 4 | 37A/4 | DA+9 | 2025-02-25 | 2025-03-06 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Sachinder
73 | 5 | 37A/6 | DA+3 | 2025-02-24 | 2025-03-08 | Vasu dev singh-2 | 37.9311 | 3.534 | Prabhakar | Completed | Pawan
74 | 6 | 9/4 | DA+6 | 2025-03-05 | 2025-03-09 | Punam Devi-4 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Hazari Yadav
75 | 7 | 37A/0 | DB1+0 | 2025-02-28 | 2025-03-11 | Punam Devi-2 | 55.4509 | 5.1663 | Kartik Mahto | Completed | Gopal Muni
76 | 8 | 38/2 | DA+0 | 2025-03-07 | 2025-03-11 | Punam Devi-1 | 36.1598 | 3.3689 | Manoj Kumar Gupta | Completed | Mithilesh
77 | 9 | 39/7 | DA+3 | 2025-03-07 | 2025-03-13 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Sachinder
78 | 10 | 9/2 | DA+3 | 2025-03-10 | 2025-03-13 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
79 | 11 | 15/2 | DA+3 | 2025-03-14 | 2025-03-18 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
80 | 12 | 38/7 | DA+9 | 2025-03-12 | 2025-03-18 | Punam Devi-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Mithilesh
81 | 13 | 39/2 | DA+3 | 2025-03-12 | 2025-03-19 | Punam Devi-2 | 37.9311 | 3.534 | Kartik Mahto | Completed | Gopal Muni
82 | 14 | 39/5 | DA+1.5 | 2025-03-14 | 2025-03-20 | Punam Devi-3 | 37.1383 | 3.4601 | Haridas | Completed | Gulshan Kumar
83 | 15 | 39/0 | DB2+0 | 2025-03-09 | 2025-03-21 | Vasu dev singh-2 | 59.5006 | 5.5436 | Raju Mahto | Completed | Pawan
84 | 16 | 15/3 | DA+3 | 2025-03-19 | 2025-03-22 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
85 | 17 | 38/8 | DA+1.5 | 2025-03-19 | 2025-03-24 | Punam Devi-1 | 37.1383 | 3.4601 | Manoj Kumar Gupta | Completed | Mithilesh
86 | 18 | 39/3 | DA+1.5 | 2025-03-20 | 2025-03-25 | Punam Devi-2 | 37.1383 | 3.4601 | Kartik Mahto | Completed | Gopal Muni
87 | 19 | 39/4 | DA+3 | 2025-03-21 | 2025-03-27 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Gulshan Kumar
88 | 20 | 15/4 | DA+6 | 2025-03-23 | 2025-03-27 | Punam Devi-4 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Hazari Yadav
89 | 21 | 39/1 | DA-1.5 | 2025-03-22 | 2025-03-29 | Vasu dev singh-2 | 35.6018 | 3.317 | Raju Mahto | Completed | Pawan
90 | 22 | 39/9 | DA+6 | 2025-03-25 | 2025-03-30 | Punam Devi-1 | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed | Gulshan Kumar
91 | 23 | 40/2 | DA+6 | 2025-03-26 | 2025-03-31 | Punam Devi-2 | 43.8044 | 4.0812 | Kartik Mahto | Completed | Gopal Muni
92 | 24 | 15/5 | DA+3 | 2025-03-26 | 2025-03-31 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Hazari Yadav
93 | 25 | 39/8 | DA+1.5 | 2024-03-26 | 2025-03-31 | Punam Devi-3 | 37.1383 | 3.4601 | Haridas | Completed | Gulshan Kumar
94 | 1 | 39/10 | DA+3 | 2025-03-31 | 2025-04-05 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Mithilesh
95 | 2 | 15/6 | DA+9 | 2025-03-31 | 2025-04-06 | Punam Devi-4 | 45.697 | 4.2575 | Gangadin sahoo | Completed | Hazari Yadav
96 | 3 | 39/11 | DA+6 | 2025-03-30 | 2025-04-09 | Punam Devi-1 | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed | Gulshan Kumar
97 | 4 | 40/3 | DA+3 | 2025-03-31 | 2025-04-09 | Punam Devi-2 | 37.9311 | 3.534 | Kartik Mahto | Completed | Gopal Muni
98 | 5 | 38/0 | DB1+3 | 2025-03-29 | 2025-04-11 | Vasu dev singh-2 | 57.9632 | 5.4003 | Manoj Gupta | Completed | Pawan
99 | 6 | 40/5 | DA+9 | 2025-04-05 | 2025-04-14 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Mithilesh
100 | 7 | 40/4 | DA+6 | 2025-04-09 | 2025-04-18 | Punam Devi-2 | 43.8044 | 4.0812 | Raju Mahto | Completed | Gopal Muni
101 | 8 | 39/6 | DA+1.5 | 2025-04-09 | 2025-04-18 | Punam Devi-1 | 37.1383 | 3.4601 | Haridas | Completed | Gulshan Kumar
102 | 9 | 40/6 | DA+9 | 2025-04-14 | 2025-04-22 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Mithilesh
103 | 10 | 36A/0 | DB1+9 | 2025-04-18 | 2025-04-30 | Punam Devi-2 | 66.7809 | 6.2219 | Raju Mahto | Completed | Gopal Muni
104 | 11 | 40/0 | DB1+6 | 2025-04-18 | 2025-04-30 | Punam Devi-1 | 65.0278 | 6.0585 | Haridas | Completed | Gulshan Kumar
105 | 1 | 32/6 | DA+9 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.2575 | Manoj Gupta | Completed
106 | 2 | 32/1 | DA+6 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 4.0812 | Raju Mahto | Completed
107 | 3 | 7/3 | DA+9 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 4.2575 | Sanjay Kumar | Completed
108 | 4 | 32/5 | DA+9 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.2575 | Manoj Gupta | Completed
109 | 5 | 6/1 | DA+9 | 2025-07-16 | 2025-07-26 | Jwala Singh-1 | 45.697 | 4.2575 | Aman Singh | Completed
110 | 6 | 32/2 | DA+9 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 4.2575 | Suraj Kumar | Completed
111 | 7 | 7/0 | DB2+0 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.5436 | Sanjay Kumar | Completed
112 | 8 | 32/7 | DA+3 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 3.534 | Manoj Gupta | Completed
113 | 1 | 31/0 | DB1+0 | 2025-07-16 | 2025-08-01 | SK Samiul -1 | 55.4509 | 5.1663 | Haridas | Completed
114 | 2 | 42/0 | DB2+0 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 5.5436 | Manirul | Completed
115 | 3 | 8/11 | DA+9 | 2025-07-15 | 2025-08-03 | Jwala Singh-1 | 45.697 | 4.2575 | Rudra Prasad | Completed
116 | 4 | 30/10 | DA+3 | 2025-07-18 | 2025-08-03 | SK.Samiul -2 | 37.9311 | 3.534 | Haridas | Completed
117 | 5 | 32/3 | DA+6 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.0812 | Suraj Kumar | Completed
118 | 6 | 42/1 | DA+3 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 3.534 | Manirul | Completed
119 | 7 | 40/1 | DA+9 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 4.2575 | Susheel Kumar | Completed
120 | 8 | 6/2 | DA+6 | 2025-08-04 | 2025-08-08 | Jwala Singh-1 | 43.8044 | 4.0812 | Sanjay Kumar | Completed
121 | 9 | 32A/0 | DB1+9 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 6.2219 | Manoj Kumar Gupta | Completed
122 | 10 | 35/2 | DA+6 | 2025-08-01 | 2025-08-09 | Jwala Singh-2 | 43.8044 | 4.0812 | Rudra Prasad | Completed
123 | 11 | 6/12 | DA+1.5 | 2025-08-01 | 2025-08-09 | Pritam Enterprises-1 | 37.1383 | 3.4601 | Sanjay Kumar | Completed
124 | 12 | 31/1 | DA+3 | 2025-08-02 | 2025-08-10 | SK Samiul -1 | 37.9311 | 3.534 | Haridas | Completed
125 | 13 | 31/2 | DA+1.5 | 2025-08-04 | 2025-08-11 | SK.Samiul -2 | 37.1383 | 3.4601 | Haridas | Completed
126 | 14 | 42/2 | DA+9 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 4.2575 | Manirul | Completed
127 | 15 | 40/9 | DA+9 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 4.2575 | Manirul | Completed
128 | 16 | 6/5 | DA+9 | 2025-08-02 | 2025-08-13 | Pritam Enterprises-2 | 45.697 | 4.2575 | Sanjay Kumar | Completed
129 | 17 | 32/4 | DA+9 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 4.2575 | Suraj Kumar | Completed
130 | 18 | 6/3 | DA+3 | 2025-08-08 | 2025-08-14 | Jwala Singh-1 | 37.9311 | 3.534 | Sanjay Kumar | Completed | Sanjay
131 | 19 | 8A/0 | DB1+12 | 2025-08-07 | 2025-08-14 | Punam Kumari-2 | 70.7883 | 6.5952 | Sanjay Kumar | Completed | Hazari Yadav
132 | 20 | 33/2 | DA+9 | 2025-08-09 | 2025-08-17 | Punam Kumari-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed
133 | 21 | 6/10 | DA+1.5 | 2025-08-09 | 2025-08-18 | Pritam Enterprises-1 | 37.1383 | 3.4601 | Sanjay Kumar | Completed
134 | 22 | 9/5 | DA+3 | 2025-08-15 | 2025-08-19 | Punam Kumari-2 | 37.9311 | 3.534 | Narayan Mahto | Completed
135 | 23 | 42/3 | DB1+9 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 6.2219 | Manirul | Completed
136 | 24 | 5/6 | DA+3 | 2025-08-08 | 2025-08-20 | Pritam Enterprises-4 | 37.9311 | 3.534 | Deshraj | Completed | Sanjay
137 | 25 | 40/7 | DA+3 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 3.534 | Susheel Kumar | Completed
138 | 26 | 1/0 | DD60+0 | 2025-08-07 | 2025-08-21 | Pritam Enterprises-3 | 83.1335 | 7.7454 | Nishit Mondal | Completed | Suraj
139 | 27 | 6/0 | DB1+9 | 2025-08-13 | 2025-08-21 | Jwala Singh-2 | 66.7809 | 6.2219 | Rudra Prasad | Completed
140 | 28 | 6/6 | DA-3 | 2025-08-14 | 2025-08-21 | Pritam Enterprises-2 | 34.7898 | 3.2413 | Indrajeet Patel | Completed
141 | 29 | 6/4 | DA+9 | 2025-08-15 | 2025-08-21 | Jwala Singh-1 | 45.697 | 4.2575 |  | Completed
142 | 30 | 30/9 | DA-3 | 2025-08-12 | 2025-08-21 | SK.Samiul -2 | 34.7898 | 3.2413 | Haridas | Completed
143 | 31 | 31/3 | DA+3 | 2025-08-12 | 2025-08-22 | SK Samiul -1 | 37.9311 | 3.534 | Khooblal Mahto | Completed
144 | 32 | 33/9 | DA+1.5 | 2025-08-18 | 2025-08-22 | Punam Kumari-1 | 37.1383 | 3.4601 | Manoj Kumar Gupta | Completed
145 | 33 | 6/11 | DA-1.5 | 2025-08-19 | 2025-08-25 | Pritam Enterprises-1 | 35.6018 | 3.317 | Sanjay Kumar | Completed
146 | 34 | 9/6 | DA+3 | 2025-08-20 | 2025-08-25 | Punam Kumari-2 | 37.9311 | 3.534 | Narayan Mahto | Completed
147 | 35 | 43/2 | DA+6 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 4.0812 | Manirul | Completed
148 | 36 | 31/10 | DA+4.5 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.999 | Suraj Kumar | Completed
149 | 37 | 2A/1 | DA+0 | 2025-08-21 | 2025-08-27 | Pritam Enterprises-3 | 36.1598 | 3.3689 | Nishit Mondal | Completed
150 | 38 | 4A/4 | DA+6 | 2025-08-18 | 2025-08-28 | Govind Mahto-1 | 43.8044 | 4.0812 | Aman Singh | Completed
151 | 39 | 5/5 | DA+6 | 2025-08-20 | 2025-08-28 | Pritam Enterprises-4 | 43.8044 | 4.0812 | Deshraj | Completed | Sanjay
152 | 40 | 6/7 | DA+1.5 | 2025-08-22 | 2025-08-28 | Pritam Enterprises-2 | 37.1383 | 3.4601 | Indrajeet Patel | Completed
153 | 41 | 5/10 | DA+9 | 2025-08-22 | 2025-08-28 | Jwala Singh-1 | 45.697 | 4.2575 | Aman Singh | Completed
154 | 42 | 9/7 | DA+9 | 2025-08-23 | 2025-08-29 | Punam Kumari-2 | 45.697 | 4.2575 | Narayan Mahto | Completed
155 | 43 | 33/7 | DA+6 | 2025-08-23 | 2025-08-30 | Punam Kumari-1 | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed
156 | 44 | 31/4 | DA-1.5 | 2025-08-22 | 2025-08-31 | SK.Samiul -2 | 35.6018 | 3.317 | Haridas | Completed
157 | 1 | 5A/0 | DB1+12 | 2025-08-22 | 2025-09-01 | Jwala Singh-2 | 70.7883 | 6.5952 | Rudra Prasad | Completed
158 | 2 | 32A/1 | DA+6 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 4.0812 | Raju Mahto | Completed
159 | 3 | 6/9 | DA+6 | 2025-08-23 | 2025-09-02 | Pritam Enterprises-2 | 43.8044 | 4.0812 | Sanjay Kumar | Completed
160 | 4 | 2A/2 | DA+3 | 2025-08-28 | 2025-09-02 | Pritam Enterprises-3 | 37.9311 | 3.534 | Nishit Mondal | Completed
161 | 5 | 43/3 | DA-1.5 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.317 | Manirul | Completed
162 | 6 | 31/5 | DA+6 | 2025-08-23 | 2025-09-03 | SK Samiul -1 | 43.8044 | 4.0812 | Khooblal Mahto | Completed
163 | 7 | 31/9 | DA+1.5 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.4601 | Suraj Kumar | Completed
164 | 8 | 44/1 | DA+3 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.534 | Susheel Kumar | Completed
165 | 9 | 33/3 | DA+3 | 2025-08-31 | 2025-09-04 | Punam Kumari-1 | 37.9311 | 3.534 | Manoj Kumar Gupta | Completed
166 | 10 | 5/9 | DA+6 | 2025-08-29 | 2025-09-05 | Jwala Singh-1 | 43.8044 | 4.0812 | Indrajeet Patel | Completed
167 | 11 | 6/8 | DA+3 | 2025-08-29 | 2025-09-06 | Pritam Enterprises-2 | 37.9311 | 3.534 | Aman Singh | Completed
168 | 12 | 9/0 | DB1+12 | 2025-08-30 | 2025-09-06 | Punam Kumari-2 | 70.7883 | 6.5952 | Narayan Mahto | Completed
169 | 13 | 4A/3 | DA+9 | 2025-08-29 | 2025-09-06 | Govind Mahto-1 | 45.697 | 4.2575 | Aman Singh | Completed
170 | 14 | 43/4 | DA+0 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 3.3689 | Manirul | Completed
171 | 15 | 5/4 | DA-1.5 | 2025-08-29 | 2025-09-08 | Pritam Enterprises-4 | 35.6018 | 3.317 | Deshraj | Completed
172 | 16 | 2A/3 | DA+3 | 2025-09-03 | 2025-09-08 | Pritam Enterprises-3 | 37.9311 | 3.534 | Nishit Mondal | Completed
173 | 17 | 4A/5 | DA+9 | 2025-08-25 | 2025-09-08 | Govind Mahto-2 | 45.697 | 4.2575 | Aman Singh | Completed
174 | 18 | 30/6 | DA+6 | 2025-08-29 | 2025-09-08 | Punam Kumari-3 | 43.8044 | 4.0812 | kartik | Completed
175 | 19 | 5/7 | DA+9 | 2025-09-02 | 2025-09-09 | Jwala Singh-2 | 45.697 | 4.2575 | Rudra Prasad | Completed
176 | 20 | 44/2 | DA+3 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 3.534 | Susheel Kumar | Completed
177 | 21 | 33/4 | DA+3 | 2025-09-05 | 2025-09-09 | Punam Kumari-1 | 37.9311 | 3.534 | Manoj Kumar Gupta | Completed
178 | 22 | 33/1 | DA+9 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 4.2575 | Bhupendra choudhary | Completed
179 | 23 | 3A/1 | DA+3 | 2025-09-03 | 2025-09-11 | Pritam Enterprises-1 | 37.9311 | 3.534 | Sanjay Kumar | Completed
180 | 24 | 43/6 | DA+3 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 3.534 | Susheel Kumar | Completed
181 | 25 | 4/5 | DA+6 | 2025-09-06 | 2025-09-12 | Jwala Singh-1 | 43.8044 | 4.0812 | Kamal Ravidas | Completed
182 | 26 | 30/7 | DA-3 | 2025-09-09 | 2025-09-13 | Punam Kumari-3 | 34.7898 | 3.2413 | Kartik | Completed
183 | 27 | 32/0 | DB2+0 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.5436 | Suraj Kumar | Completed
184 | 28 | 30/4 | DA+9 | 2025-09-09 | 2025-09-15 | Punam Kumari-4 | 45.697 | 4.2575 | Kartik | Completed
185 | 29 | 18/0 | DB2+6 | 2025-09-07 | 2025-09-15 | Punam Kumari-2 | 69.376 | 6.4637 | Kamal Ravidas | Completed
186 | 30 | 2A/4 | DA+3 | 2025-09-09 | 2025-09-15 | Pritam Enterprises-3 | 37.9311 | 3.534 | Nishit Mondal | Completed
187 | 31 | 5/8 | DA+6 | 2025-09-10 | 2025-09-15 | Jwala Singh-2 | 43.8044 | 4.0812 | Rudra Prasad | Completed
188 | 32 | 44/3 | DA+3 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 3.534 | Khooblal Mahto | Completed
189 | 33 | 3A/5 | DA+3 | 2025-09-07 | 2025-09-15 | Pritam Enterprises-2 | 37.9311 | 3.534 | Akabar Ali | Completed
190 | 34 | 4A/2 | DA+6 | 2025-09-07 | 2025-09-16 | Govind Mahto-1 | 43.8044 | 4.0812 | Aman Singh | Completed
191 | 35 | 31/7 | DA+0 | 2025-09-10 | 2025-09-16 | Punam Kumari-1 | 36.1598 | 3.3689 | Manoj Kumar Gupta | Completed
192 | 36 | 31/6 | DA+9 | 2025-09-04 | 2025-09-18 | SK Samiul -1 | 45.697 | 4.2575 | Haridas | Completed
193 | 37 | 4A/6 | DA+9 | 2025-09-09 | 2025-09-18 | Govind Mahto-2 | 45.697 | 4.2575 | Aman Singh | Completed
194 | 38 | 43/8 | DA+9 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 4.2575 | Khooblal Mahto | Completed
195 | 39 | 44/4 | DA+0 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 3.3689 | Khooblal Mahto | Completed
196 | 40 | 3A/2 | DA+3 | 2025-09-12 | 2025-09-19 | Pritam Enterprises-1 | 37.9311 | 3.534 | Sanjay Kumar | Completed
197 | 41 | 40A/0 | DB1+9 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 6.2219 | Susheel Kumar | Completed
198 | 42 | 33/0 | DB1+9 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 6.2219 | Raju Mahto | Completed
199 | 43 | 18/1 | DA+3 | 2025-09-16 | 2025-09-20 | Punam Kumari-2 | 37.9311 | 3.534 | Kamal Ravidas | Completed
200 | 44 | 31/8 | DA+0 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 3.3689 | Suraj Kumar | Completed
201 | 45 | 30/8 | DA+3 | 2025-09-14 | 2025-09-22 | Punam Kumari-3 | 37.9311 | 3.534 | Abrar Ali | Completed
202 | 46 | 2A/5 | DA+3 | 2025-09-16 | 2025-09-23 | Pritam Enterprises-3 | 37.9311 | 3.534 | Nishit Mondal | Completed
203 | 47 | 44/5 | DA+0 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 3.3689 | Khooblal Mahto | Completed
204 | 48 | 3A/6 | DA+0 | 2025-09-16 | 2025-09-24 | Pritam Enterprises-2 | 36.1598 | 3.3689 | Akabar Ali | Completed
205 | 49 | 4A/0 | DB1+3 | 2025-09-13 | 2025-09-24 | Jwala Singh-1 | 57.9632 | 5.4003 | Kamal Ravidas | Completed
206 | 50 | 30/0 | DB1+0 | 2025-09-11 | 2025-09-25 | Punam Kumari-4 | 55.4509 | 5.1663 | Manoj Gupta | Completed | Mithilesh
207 | 51 | 5/1 | DA+6 | 2025-09-13 | 2025-09-25 | Jwala Singh-2 | 43.8044 | 4.0812 | Rudra Prasad | Completed
208 | 52 | 4A/1 | DA+6 | 2025-09-18 | 2025-09-25 | Govind Mahto-1 | 43.8044 | 4.0812 | Rahul Ravidas | Completed
209 | 53 | 20/1 | DA-3 | 2025-09-19 | 2025-09-25 | Punam Kumari-1 | 34.7898 | 3.2413 | Manoj Kumar Gupta | Completed
210 | 54 | 18/2 | DA+1.5 | 2025-09-21 | 2025-09-25 | Punam Kumari-2 | 37.1383 | 3.4601 | Narayan Mahto | Completed
211 | 55 | 12/0 | DB1+9 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 6.2219 | Bhupendra choudhary | Completed
212 | 56 | 3A/3 | DA+0 | 2025-09-20 | 2025-09-27 | Pritam Enterprises-1 | 36.1598 | 3.3689 | Sanjay Kumar | Completed | Sintu
213 | 57 | 43/7 | DA+0 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 3.3689 | Khooblal Mahto | Completed
214 | 58 | 44/0 | DB1+6 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.0585 | Manoj Kumar Choudhary | Completed
215 | 59 | 40/11 | DA+9 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 4.2575 | Susheel Kumar | Completed
216 | 60 | 5/0 | DB1+6 | 2025-09-19 | 2025-09-30 | Govind Mahto-2 | 65.0278 | 6.0585 | Aman Singh | Completed
217 | 61 | 20/2 | DA-3 | 2025-09-26 | 2025-09-30 | Punam Kumari-1 | 34.7898 | 3.2413 | Rahul Ravidas | Completed
218 | 62 | 18/3 | DA+6 | 2025-09-26 | 2025-09-30 | Punam Kumari-2 | 43.8044 | 4.0812 | Najirul | Completed
219 | 63 | 2A/6 | DA+6 | 2025-09-24 | 2025-09-30 | Pritam Enterprises-3 | 43.8044 | 4.0812 | Narayan Mahto | Completed
220 | 64 | 5/3 | DA+9 | 2025-09-09 | 2025-09-30 | Pritam Enterprises-4 | 45.697 | 4.2575 | Sanjay Kumar | Completed
221 | 65 | 5/2 | DA+9 | 2025-09-26 | 2025-09-30 | Jwala Singh-2 | 45.697 | 4.2575 | Rudra Prasad | Completed
222 | 1 | 30/2 | DA+9 | 2025-09-24 | 2025-10-04 | SK Samiul -1 | 45.697 | 4.2575 | Haridas | Completed
223 | 2 | 41/1 | DA+9 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.2575 | Suraj Kumar | Completed
224 | 3 | 29A/5 | DA+6 | 2025-09-26 | 2025-10-04 | Punam Kumari-4 | 43.8044 | 4.0812 | Manoj Gupta | Completed
225 | 4 | 15/8 | DA+1.5 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 3.4601 | Bhupendra choudhary | Completed
226 | 5 | 18/4 | DA-3 | 2025-10-01 | 2025-10-06 | Punam Kumari-2 | 34.7898 | 3.2413 | Najirul | Completed
227 | 6 | 3B/2 | DA+9 | 2025-09-26 | 2025-10-07 | Govind Mahto-1 | 45.697 | 4.2575 | Aman Singh | Completed | Tulshi
228 | 7 | 45/0 | DB1+9 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 6.2219 | Khooblal Mahto | Completed
229 | 8 | 40/10 | DA+3 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.534 | Susheel Kumar | Completed
230 | 9 | 29A/4 | DA+3 | 2025-10-05 | 2025-10-10 | Punam Kumari-4 | 37.9311 | 3.534 | Manoj Gupta | Completed | Mithilesh
231 | 10 | 3A/4 | DA+0 | 2025-10-01 | 2025-10-10 | Pritam Enterprises-3 | 36.1598 | 3.3689 | Abhiya | Completed | Suraj
232 | 11 | 18/5 | DA+0 | 2025-10-07 | 2025-10-10 | Punam Kumari-2 | 36.1598 | 3.3689 | Najirul | Completed | Hazari Yadav
233 | 12 | 3B/0 | DB1+9 | 2025-09-25 | 2025-10-12 | Pritam Enterprises-2 | 66.7809 | 6.2219 | Akabar Ali | Completed | Laxman
234 | 13 | 4/0 | DB2+9 | 2025-09-25 | 2025-10-12 | Jwala Singh-1 | 72.1555 | 6.7226 | Kamal Ravidas | Completed | Dharmendra Das
235 | 14 | 46/0 | DB1+12 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 6.5952 | Manoj Kumar Choudhary | Completed
236 | 15 | 29/1 | DA+6 | 2025-10-07 | 2025-10-12 | Jwala Singh-2 | 43.8044 | 4.0812 | Raju Mahto | Completed | Mukesh
237 | 16 | 18/6 | DA+9 | 2025-10-11 | 2025-10-15 | Punam Kumari-2 | 45.697 | 4.2575 | Najirul | Completed | Hazari Yadav
238 | 17 | 20/0 | DD60+3 | 2025-10-01 | 2025-10-15 | Punam Kumari-1 | 87.0213 | 8.1076 | Rahul Ravidas | Completed | Gulshan Kumar
239 | 18 | 3B/1 | DA+3 | 2025-10-09 | 2025-10-16 | Govind Mahto-1 | 37.9311 | 3.534 | Rundra | Completed | Tulshi
240 | 19 | 10/0 | DB1+6 | 2025-10-02 | 2025-10-17 | Pritam Enterprises-1 | 65.0278 | 6.0585 | Sanjay Kumar | Completed | Sintu
241 | 20 | 40/8 | DA-1.5 | 2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.317 | Susheel Kumar | Completed
242 | 21 | 41/0 | DB1+9 | 2025-10-05 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 6.2219 | Suraj Kumar | Completed | 03 days delay due to 11kv pole shiting
243 | 22 | 29A/0 | DB1+0 | 2025-10-06 | 2025-10-22 | SK Samiul -1 | 55.4509 | 5.1663 | Haridas | Completed | Tajirul
244 | 23 | 30/3 | DA+3 | 2025-10-12 | 2025-10-22 | Jwala Singh-2 | 37.9311 | 3.534 | Raju Mahto | Completed | Mukesh
245 | 24 | 18/7 | DA+1.5 | 2025-10-16 | 2025-10-22 | Punam Kumari-2 | 37.1383 | 3.4601 | Najirul | Completed | Hazari Yadav
246 | 25 | 20/6 | DA-3 | 2025-10-17 | 2025-10-23 | Govind Mahto-1 | 34.7898 | 3.2413 | Rundra | Completed | Tulshi
247 | 26 | 29/0 | DC1+0 | 2025-10-08 | 2025-10-25 | Pritam Enterprises-4 | 62.4437 | 5.8178 | Raju Mahto | Completed | Gautam
248 | 27 | 3A/0 | DD45+3 | 2025-10-11 | 2025-10-26 | Pritam Enterprises-3 | 77.0769 | 7.1811 | Abhiya | Completed | Suraj
249 | 28 | 23/0 | DB2+9 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 6.7226 | Dhalchand | Completed
250 | 29 | 19/0 | DD60+3 | 2025-10-16 | 2025-10-27 | Punam Kumari-1 | 87.0213 | 8.1076 | Manoj Kumar Choudhary | Completed | Gulshan Kumar
251 | 30 | 9/11 | DA+3 | 2025-10-18 | 2025-10-28 | Pritam Enterprises-1 | 37.9311 | 3.534 | Saheb Khan | Completed | Sintu
252 | 31 | 21/0 | DB1+0 | 2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.1663 | Akbar Ali | Completed
253 | 32 | 21/1 | DA+0 | 2025-10-24 | 2025-10-29 | Govind Mahto-1 | 36.1598 | 3.3689 | Rundra | Completed | Tulshi
254 | 33 | 15/0 | DD60+25 | 2025-10-05 | 2025-10-30 | Govind Mahto-2 | 137.0461 | 12.7684 | Aman Singh | Completed | Gangadhar
255 | 34 | 27/5 | DA-1.5 | 2025-10-23 | 2025-10-30 | Jwala Singh-2 | 35.6018 | 3.317 | Haridas | Completed | Mukesh
256 | 35 | 10/1 | DA+3 | 2025-10-12 | 2025-10-31 | Jwala Singh-1 | 37.9311 | 3.534 | Kamal Ravidas | Completed | Dharmendra Das
257 | 36 | 20/5 | DA+0 | 2025-10-28 | 2025-10-31 | Punam Kumari-1 | 36.1598 | 3.3689 | Manoj Kumar Choudhary | Completed | Gulshan Kumar
258 | 1 | 20/3 | DA+1.5 | 2025-10-30 | 2025-11-05 | Govind Mahto-1 | 37.1383 | 3.4601 | Rundra | Completed | Tulshi
259 | 2 | 9/10 | DA+3 | 2025-10-31 | 2025-11-05 | Govind Mahto-2 | 37.9311 | 3.534 | Aman Singh | Completed | Gangadhar
260 | 3 | 20/4 | DA+3 | 2025-10-01 | 2025-11-06 | Punam Kumari-1 | 37.9311 | 3.534 | Manoj Kumar Choudhary | Completed | Gulshan Kumar
261 | 4 | 26/0 | DD60+35 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 16.1704 | Khooblal Mahto | Completed
262 | 5 | 10/2 | DA+3 | 2025-10-01 | 2025-11-07 | Jwala Singh-1 | 37.9311 | 3.534 | Kamal Ravidas | Completed | Dharmendra Das
263 | 6 | 3B/3 | DA+6 | 2025-10-12 | 2025-11-07 | Pritam Enterprises-2 | 43.8044 | 4.0812 | Abhiya | Completed | Laxman
264 |  | 17/0 | DC1+3 | 2025-10-10 |  | Punam Kumari-4 | 65.8725 | 6.1372 | Manoj Kumar Gupta | ROW | Mithilesh
265 |  | 24/0 | DD60+18 | 2025-10-12 |  | Fouzi Ratto | 124.95 | 11.6414 | Raju Mahto | WIP
266 |  | 43/0 | DB1+0 | 2025-10-23 |  | Amar Kumar Singh | 55.4509 | 5.1663 | Narayan Mahto | ROW
267 |  | 29A/3 | DA+6 | 2025-10-23 |  | SK Samiul -1 | 43.8044 | 4.0812 | Raju Mahto | ROW | Tajirul
268 |  | 21/3 | DA+6 | 2025-10-23 |  | Punam Kumari-2 | 43.8044 | 4.0812 | Rahul Ravidas | ROW | Hazari Yadav
269 |  | 27/4 | DA+1.5 | 2025-10-27 |  | Pritam Enterprises-4 | 37.1383 | 3.4601 | Nabirul Islam | WIP
270 |  | 3B/3 | DA+6 | 2025-10-27 |  | Pritam Enterprises-3 | 43.8044 | 4.0812 | Abhiya | WIP
271 |  | 22/0 | DC2+15 | 2025-10-28 |  | Bhairaw Mahto | 96.8799 | 9.0261 | Dhalchand | WIP
272 |  | 21/4 | DA+0 | 2025-10-30 |  | Kartik Mahto | 36.1598 | 3.3689 | Akbar Ali | WIP
273 |  | 28/0 | DC2-3 | 2025-10-31 |  | Jwala Singh-2 | 64.8843 | 6.0452 | Haridas | WIP | Mukesh
274 |  | 21/2 | DA+6 | 2025-11-06 |  | Govind Mahto-1 | 43.8044 | 4.0812 | Rundra | WIP | Tulshi
275 |  | 9/9 | DA+0 | 2025-11-06 |  | Govind Mahto-2 | 37.9311 | 3.534 | Aman Singh | WIP | Gangadhar
276 |  | 21/5 | DA+0 | 2025-11-07 |  | Punam Kumari-1 | 37.9311 | 3.534 | Manoj Kumar Choudhary | WIP | Gulshan Kumar
277 |  | 27/0 | DD60+35 | 2025-11-08 |  | Ved Prakash | 173.5609 | 16.1704 | Khooblal Mahto | WIP
278 |  | 15/7 | DA+0 | 2025-11-10 |  | Jwala Singh-1 | 37.9311 | 3.534 | Kamal Ravidas | WIP | Dharmendra Das
279 |  | 25/0 | DD60+18 | 2025-11-12 |  | Pritam Enterprises-2 | 43.8044 | 4.0812 | Abhiya | WIP | Laxman

## Stringing Compiled
Number of TSE |  |  | 37
Number of Manual |  |  | 23
S.no | From AP | To AP | Span (M) | Method | No. of Locations for end twr) | Section Readiness | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Length | Status | Gang Name | Hindrance | Remarks
1 | 34/0 | 35/0 | 4898.588 | TSE | 13 | Ready | 2025-02-21 | 2025-02-26 | 4898.588 | 2025-02-27 | 2025-03-04 | 4898.588 | Completed | SK Infratech
2 | 37A/0 | 38/0 | 2583.589 | TSE | 7 | Ready | 2025-03-17 | 2025-03-20 | 2583.589 | 2025-03-21 | 2025-04-16 | 2583.589 | Completed | SK Infratech
3 | 38/0 | 39/0 | 4163.677 | TSE | 11 | Ready | 2025-03-29 | 2025-04-05 | 4163.677 | 2025-04-06 | 2025-04-16 | 4163.677 | Completed | SK Infratech
4 | 39/0 | 40/0 | 4716.811 | TSE | 12 | Ready | 2025-04-25 | 2025-04-29 | 4716.811 | 2025-04-30 | 2025-04-30 | 4716.811 | Completed | SK Infratech
5 | 7/0 | 7A/0 | 2699.284 | TSE | 7 | Ready | 2025-08-27 | 2025-09-04 | 2699.284 | 2025-09-05 | 2025-09-18 | 2699.284 | Completed | Rahim Khan
6 | 7A/0 | 8/0 | 2434.77 | TSE | 6 | Ready | 2025-09-12 | 2025-09-16 | 2434.77 | 2025-09-17 | 2025-09-25 | 2434.77 | Completed | Rahim Khan
7 | 8/0 | 8A/0 | 4455 | TSE | 12 | Ready | 2025-10-05 | 2025-10-15 | 4455 | 2025-10-16 | 2025-10-22 | 4455 | Completed | Rahim Khan
8 | 8A/0 | 9/0 | 466.629 | Manual | 1 | Ready | 2025-10-03 | 2025-10-05 | 466.629 | 2025-10-06 | 2025-10-27 | 466.629 | Completed | Rahim Khan
9 | GY | 1/0 | 150.014 | Manual | 1 | Not Ready |  |  | 150.014
10 | 1/0 | 2A/0 | 290.21 | Manual | 1 | Not Ready |  |  | 290.21
11 | 2A/0 | 3A/0 | 2836.992 | TSE | 7 | Ready |  |  | 2836.992
12 | 3A/0 | 3B/0 | 2691.467 | TSE | 7 | Ready |  |  | 2691.467
13 | 3B/0 | 4/0 | 1627.07 | TSE | 4 | Ready |  |  | 1627.07
14 | 4/0 | 4A/0 | 709.163 | TSE | 2 | Ready |  |  | 709.163
15 | 4A/0 | 5/0 | 2681.611 | TSE | 7 | Ready |  |  | 2681.611
16 | 5/0 | 5A/0 | 4418.389 | TSE | 11 | Ready |  |  | 4418.389
17 | 5A/0 | 6/0 | 419.48 | Manual | 1 | Ready | 2025-11-05 | 2025-11-09 | 419.48 |  |  |  | WIP | Rahim Khan |  | Rough sag completed
18 | 6/0 | 7/0 | 4901.236 | TSE | 13 | Ready |  |  | 4901.236 |  |  |  | WIP | Rahim Khan |  | Insulator hoisting done 6/0,6/1,6/2,6/3,6/4,6/8,6/9,6/10,6/11,6/12
19 | 9/0 | 10/0 | 4964.92 | TSE | 12 | Not Ready |  |  | 4964.92
20 | 10/0 | 11/0 | 1004.183 | TSE | 3 | Not Ready |  |  | 1004.183
21 | 11/0 | 12/0 | 242.893 | Manual | 1 | Not Ready |  |  | 242.893
22 | 12/0 | 13/0 | 329.728 | Manual | 1 | Not Ready |  |  | 329.728
23 | 13/0 | 13A/0 | 416.878 | Manual | 1 | Not Ready |  |  | 416.878
24 | 13A/0 | 14/0 | 480.269 | Manual | 1 | Not Ready |  |  | 480.269
25 | 14/0 | 15/0 | 223.816 | Manual | 1 | Not Ready |  |  | 223.816
26 | 15/0 | 16/0 | 5019.34 | TSE | 13 | Not Ready |  |  | 5019.34
27 | 16/0 | 17/0 | 392.694 | Manual | 1 | Not Ready |  |  | 392.694
28 | 17/0 | 18/0 | 398.404 | Manual | 1 | Not Ready |  |  | 398.404
29 | 18/0 | 19/0 | 3030.029 | TSE | 8 | Ready |  |  | 3030.029
30 | 19/0 | 20/0 | 279.36 | Manual | 1 | Ready |  |  | 279.36
31 | 20/0 | 21/0 | 2550.167 | TSE | 7 | Not Ready |  |  | 2550.167
32 | 21/0 | 22/0 | 2283.535 | TSE | 6 | Not Ready |  |  | 2283.535
33 | 22/0 | 23/0 | 259.048 | Manual | 1 | Not Ready |  |  | 259.048
34 | 23/0 | 23A/0 | 440.455 | Manual | 1 | Not Ready |  |  | 440.455
35 | 23A/0 | 24/0 | 496.685 | Manual | 1 | Not Ready |  |  | 496.685
36 | 24/0 | 25/0 | 244.029 | Manual | 1 | Not Ready |  |  | 244.029
37 | 25/0 | 26/0 | 237.428 | Manual | 1 | Not Ready |  |  | 237.428
38 | 26/0 | 27/0 | 203.479 | Manual | 1 | Not Ready |  |  | 203.479
39 | 27/0 | 28/0 | 2548.275 | TSE | 7 | Not Ready |  |  | 2548.275
40 | 28/0 | 29/0 | 211.209 | Manual | 1 | Not Ready |  |  | 211.209
41 | 29/0 | 29A/0 | 2379.204 | TSE | 6 | Not Ready |  |  | 2379.204
42 | 29A/0 | 30/0 | 2669.007 | TSE | 7 | Not Ready |  |  | 2669.007
43 | 30/0 | 31/0 | 4124.232 | TSE | 11 | Not Ready |  |  | 4124.232
44 | 31/0 | 32/0 | 4333.369 | TSE | 11 | Ready |  |  | 4333.369
45 | 32/0 | 32A/0 | 3283.51 | TSE | 8 | Ready |  |  | 3283.51
46 | 32A/0 | 33/0 | 840.439 | TSE | 2 | Ready |  |  | 840.439 |  |  |  | WIP | Tanjira Bibi
47 | 33/0 | 34/0 | 4049.764 | TSE | 10 | Ready |  |  | 4049.764 |  |  |  | WIP | Tanjira Bibi |  | Insulator hoisting done 33/1,33/2,33/3,33/4,33/8,33/9
48 | 35/0 | 36/0 | 4916.293 | TSE | 12 | Not Ready |  |  | 4916.293
49 | 36/0 | 36A/0 | 453.999 | Manual | 1 | Not Ready |  |  | 453.999
50 | 36A/0 | 37/0 | 1291.523 | TSE | 3 | Not Ready |  |  | 1291.523
51 | 37/0 | 37A/0 | 2496.394 | TSE | 6 | Not Ready |  |  | 2496.394
52 | 40/0 | 40A/0 | 4665.918 | TSE | 12 | Ready |  |  | 4665.918
53 | 40A/0 | 41/0 | 410.607 | Manual | 1 | Ready |  |  | 410.607
54 | 41/0 | 42/0 | 823.782 | TSE | 2 | Ready |  |  | 823.782
55 | 42/0 | 42/3 | 1258.998 | TSE | 3 | Ready |  |  | 1258.998
56 | 42/3 | 43/0 | 424.891 | Manual | 1 | Not Ready |  |  | 424.891
57 | 43/0 | 43/5 | 1851.866 | TSE | 5 | Not Ready |  |  | 1851.866
58 | 43/5 | 44/0 | 1584.546 | TSE | 4 | Not Ready |  |  | 1584.546
59 | 44/0 | 45/0 | 2383.155 | TSE | 6 | Ready |  |  | 2383.155
60 | 45/0 | 46/0 | 208.53 | Manual | 1 | Ready |  |  | 208.53
|  |  | 117850.831 |  | 306
Formulas:
F/S Starting Date = [P/O Completion Date]+1

## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Engineer/Supervisor
TA 413 | 765kv D/C Bikaner II to Neemrana II TL-02 | PGCIL | 2024-03-12 | 2025-12-11 | Mr. Santosh Mishra | Mr. Sanjay Gupta | Mr. Tushar Grover | Mr. Anil Kumar Sharma | Surendra Kumar Patel | Rudra Prasad
[9 empty] | Kartik Jhorar | Aman Kumar Singh
[9 empty] | Shuvam Gupta | Manoj Gupta
[9 empty] | Govind Bhardwaj | Raju Mahto
Khublal Mahto
Sushil Kumar
Haridashn
Manoj Kumar chaudhary
Nabirul Islam
Sanjay Kumar
Rahul Ravidas
Narayan Mahto
Akbar Ali
Kamal Ravidas
Manirul Islam
Tarique Anwar
Raju Prasad
Abhay Ojha

## Location Summary
Over all Tower Location details
S. No. | No of | Location | Type of |  | RC |  | Span | Cumm. | DS Status as on | 306 | 298 | 263 | 102 | 26 | Remarks
| AP | Tower No. | Tower |  |  |  | Length (m) | Span (km) | 2025-11-01 | Foundation | Earthing | Tower Erection | Tack welding | SPT
0 |  | Gantry | Gantry |  |  |  |  | 0
[6 empty] | Gantry | 150.014
3 | AP-1 | 1/0 | DD60+0 | T |  |  |  | 0.15 | Approved | Completed | Completed | Completed
[6 empty] | 1/0 | 290.21
2 | AP-2A | 2A/0 | DD45+0 | T |  |  |  | 0.4402 | Approved | Completed | Completed
[6 empty] | 2A/0 | 378
3 | AP-3 | 2A/1 | DA+0 |  |  |  |  | 0.8182 | Approved | Completed | Completed | Completed
[6 empty] | 2A/1 | 381
4 |  | 2A/2 | DA+3 |  |  |  |  | 1.1992 | Approved | Completed | Completed | Completed
[6 empty] | 2A/2 | 419
5 |  | 2A/3 | DA+3 |  |  |  |  | 1.6182 | Approved | Completed | Completed | Completed
[6 empty] | 2A/3 | 422
6 |  | 2A/4 | DA+3 |  |  |  |  | 2.0402 | Approved | Completed | Completed | Completed
[6 empty] | 2A/4 | 399
7 |  | 2A/5 | DA+3 |  |  |  |  | 2.4392 | Approved | Completed | Completed | Completed
[6 empty] | 2A/5 | 423
8 |  | 2A/6 | DA+6 |  |  |  |  | 2.8622 | Approved | Completed | Completed | Completed
[6 empty] | 2A/6 | 414.992
9 |  | 3A/0 | DD45+3 | T |  |  |  | 3.2772 | Approved | Completed | Completed | Completed
[6 empty] | 3A/0 | 409
10 |  | 3A/1 | DA+3 |  |  |  |  | 3.6862 | Approved | Completed | Completed | Completed
[6 empty] | 3A/1 | 402
11 |  | 3A/2 | DA+3 |  |  |  |  | 4.0882 | Approved | Completed | Completed | Completed
[6 empty] | 3A/2 | 409
12 |  | 3A/3 | DA+0 |  |  |  |  | 4.4972 | Approved | Completed | Completed | Completed |  | Completed |  | 274
[6 empty] | 3A/3 | 337
13 |  | 3A/4 | DA+0 |  |  |  |  | 4.8342 | Approved | Completed | Completed | Completed
[6 empty] | 3A/4 | 365
14 |  | 3A/5 | DA+3 |  |  |  |  | 5.1992 | Approved | Completed | Completed | Completed
[6 empty] | 3A/5 | 378
15 | AP-4 | 3A/6 | DA+0 |  |  |  |  | 5.5772 | Approved | Completed | Completed | Completed
[6 empty] | 3A/6 | 391.467
16 |  | 3B/0 | DB1+9 |  |  |  |  | 5.9687 | Approved | Completed | Completed | Completed
[6 empty] | 3B/0 | 356
17 |  | 3B/1 | DA+3 |  |  |  |  | 6.3247 | Approved | Completed | Completed | Completed
[6 empty] | 3B/1 | 439
18 |  | 3B/2 | DA+9 |  |  |  |  | 6.7637 | Approved | Completed | Completed | Completed
[6 empty] | 3B/2 | 377
19 |  | 3B/3 | DA+6 |  |  |  |  | 7.1407 | Approved | Completed | Completed | Completed
[6 empty] | 3B/3 | 455.07 | [8 empty] | 39
20 |  | 4/0 | DB2+9 |  |  |  |  | 7.5958 | Approved | Completed | Completed | Completed
[6 empty] | 4/0 | 344.163
21 |  | 4/5 | DA+6 |  |  |  |  | 7.94 | Approved | Completed | Completed | Completed |  |  | NO CHANGE S
[6 empty] | 4/5 | 365
22 | AP- 4A/0 | 4A/0 | DB1+3 |  |  |  |  | 8.305 | Approved | Completed | Completed | Completed
[6 empty] | 4A/0 | 340
23 |  | 4A/1 | DA+6 |  |  |  |  | 8.645 | Approved | Completed | Completed | Completed
[6 empty] | 4A/1 | 419.999
24 |  | 4A/2 | DA+6 |  |  |  |  | 9.065 | Approved | Completed | Completed | Completed
[6 empty] | 4A/2 | 415
25 |  | 4A/3 | DA+9 |  |  |  |  | 9.48 | Approved | Completed | Completed | Completed
[6 empty] | 4A/3 | 365
26 |  | 4A/4 | DA+6 |  |  |  |  | 9.845 | Approved | Completed | Completed | Completed
[6 empty] | 4A/4 | 330
27 |  | 4A/5 | DA+9 |  |  |  |  | 10.175 | Approved | Completed | Completed | Completed
[6 empty] | 4A/5 | 457
28 |  | 4A/6 | DA+9 |  |  |  |  | 10.632 | Approved | Completed | Completed | Completed
[6 empty] | 4A/6 | 354.612
29 | AP5 | 5/0 | DB1+6 |  |  |  |  | 10.9866 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 5/0 | 428.389
30 |  | 5/1 | DA+6 |  |  |  |  | 11.415 | Approved | Completed | Completed | Completed
[6 empty] | 5/1 | 340
31 |  | 5/2 | DA+9 |  |  |  |  | 11.755 | Approved | Completed | Completed | Completed
[6 empty] | 5/2 | 375
32 |  | 5/3 | DA+9 |  |  |  |  | 12.13 | Approved | Completed | Completed | Completed
[6 empty] | 5/3 | 365
33 |  | 5/4 | DA-1.5 |  |  |  |  | 12.495 | Approved | Completed | Completed | Completed
[6 empty] | 5/4 | 460
34 |  | 5/5 | DA+6 |  |  |  |  | 12.955 | Approved | Completed | Completed | Completed
[6 empty] | 5/5 | 380
35 |  | 5/6 | DA+3 |  |  |  |  | 13.335 | Approved | Completed | Completed | Completed
[6 empty] | 5/6 | 410
36 |  | 5/7 | DA+9 |  |  |  |  | 13.745 | Approved | Completed | Completed | Completed
[6 empty] | 5/7 | 400
37 |  | 5/8 | DA+6 |  |  |  |  | 14.145 | Approved | Completed | Completed | Completed
[6 empty] | 5/8 | 420
38 |  | 5/9 | DA+6 |  |  |  |  | 14.565 | Approved | Completed | Completed | Completed
[6 empty] | 5/9 | 345
39 |  | 5/10 | DA+9 |  |  |  |  | 14.91 | Approved | Completed | Completed | Completed
[6 empty] | 5/10 | 495
40 | AP-5A | 5A/0 | DB1+12 |  |  |  |  | 15.405 | Approved | Completed | Completed | Completed
[6 empty] | 5A/0 | 419.48
41 | AP-6 | 6/0 | DB1+9 |  |  |  |  | 15.8245 | Approved | Completed | Completed | Completed
[6 empty] | 6/0 | 350.52
42 |  | 6/1 | DA+9 |  |  |  |  | 16.175 | Approved | Completed | Completed | Completed
[6 empty] | 6/1 | 445
43 |  | 6/2 | DA+6 |  |  |  |  | 16.62 | Approved | Completed | Completed | Completed
[6 empty] | 6/2 | 390
44 |  | 6/3 | DA+3 |  |  |  |  | 17.01 | Approved | Completed | Completed | Completed
[6 empty] | 6/3 | 350
45 |  | 6/4 | DA+9 |  |  |  |  | 17.36 | Approved | Completed | Completed | Completed
[6 empty] | 6/4 | 490
46 |  | 6/5 | DA+9 |  |  |  |  | 17.85 | Approved | Completed | Completed | Completed
[6 empty] | 6/5 | 350
47 |  | 6/6 | DA-3 |  |  |  |  | 18.2 | Approved | Completed | Completed | Completed
[6 empty] | 6/6 | 347
48 |  | 6/7 | DA+1.5 |  |  |  |  | 18.547 | Approved | Completed | Completed | Completed
[6 empty] | 6/7 | 373
49 |  | 6/8 | DA+3 |  |  |  |  | 18.92 | Approved | Completed | Completed | Completed
[6 empty] | 6/8 | 380
50 |  | 6/9 | DA+6 |  |  |  |  | 19.3 | Approved | Completed | Completed | Completed
[6 empty] | 6/9 | 335
51 |  | 6/10 | DA+1.5 |  |  |  |  | 19.635 | Approved | Completed | Completed | Completed
[6 empty] | 6/10 | 315
52 |  | 6/11 | DA-1.5 |  |  |  |  | 19.95 | Approved | Completed | Completed | Completed
[6 empty] | 6/11 | 410
53 |  | 6/12 | DA+1.5 |  |  |  |  | 20.36 | Approved | Completed | Completed | Completed
[6 empty] | 6/12 | 365.716
54 | AP-7 | 7/0 | DB2+0 |  |  |  |  | 20.7257 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 7/0 | 319.284
55 |  | 7/1 | DA-3 |  |  |  |  | 21.045 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/1 | 465
56 |  | 7/2 | DA+6 |  |  |  |  | 21.51 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/2 | 375
57 |  | 7/3 | DA+9 |  |  |  |  | 21.885 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/3 | 355
58 |  | 7/4 | DA+6 |  |  |  |  | 22.24 | Approved | Completed | Completed | Completed
[6 empty] | 7/4 | 420
59 |  | 7/5 | DA+6 |  |  |  |  | 22.66 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/5 | 315
60 |  | 7/6 | DA-1.5 |  |  |  |  | 22.975 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/6 | 450
61 | AP-7A | 7A/0 | DB1+6 |  |  |  |  | 23.425 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/0 | 435
62 |  | 7A/1 | DA+1.5 |  |  |  |  | 23.86 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/1 | 385
63 |  | 7A/2 | DA+3 |  |  |  |  | 24.245 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/2 | 390
64 |  | 7A/3 | DA+3 |  |  |  |  | 24.635 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/3 | 405
65 |  | 7A/4 | DA+3 |  |  |  |  | 25.04 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 7A/4 | 390
66 |  | 7A/5 | DA+3 |  |  |  |  | 25.43 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/5 | 429.77
67 | AP-8 | 8/0 | DB1+0 |  |  |  |  | 25.8598 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/0 | 350
68 |  | 8/1 | DA-3 |  |  |  |  | 26.2098 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/1 | 330
69 |  | 8/2 | DA+6 |  |  |  |  | 26.5398 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/2 | 390
70 |  | 8/3 | DA+9 |  |  |  |  | 26.9298 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/3 | 400
71 |  | 8/4 | DA+6 |  |  |  |  | 27.3298 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/4 | 345
72 |  | 8/5 | DA+9 |  |  |  |  | 27.6748 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/5 | 350
73 |  | 8/6 | DA+3 |  |  |  |  | 28.0248 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/6 | 335
74 |  | 8/7 | DA+3 |  |  |  |  | 28.3598 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/7 | 415
75 |  | 8/8 | DA+9 |  |  |  |  | 28.7748 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/8 | 375
76 |  | 8/9 | DA+3 |  |  |  |  | 29.1498 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/9 | 375
77 |  | 8/10 | DA+0 |  |  |  |  | 29.5248 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/10 | 375
78 |  | 8/11 | DA+9 |  |  |  |  | 29.8998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/11 | 415
79 | AP-8A | 8A/0 | DB1+12 |  |  |  |  | 30.3148 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8A/0 | 466.629
80 | AP-9 | 9/0 | DB1+12 |  |  |  |  | 30.7814 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 9/0 | 418.372
81 |  | 9/1 | DA+3 |  |  |  |  | 31.1998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/1 | 410
82 |  | 9/2 | DA+3 |  |  |  |  | 31.6098 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/2 | 395
83 |  | 9/3 | DA+0 |  |  |  |  | 32.0048 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/3 | 395
84 |  | 9/4 | DA+6 |  |  |  |  | 32.3998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/4 | 425
85 |  | 9/5 | DA+3 |  |  |  |  | 32.8248 | Approved | Completed | Completed | Completed
[6 empty] | 9/5 | 415
86 |  | 9/6 | DA+3 |  |  |  |  | 33.2398 | Approved | Completed | Completed | Completed
[6 empty] | 9/6 | 405
87 |  | 9/7 | DA+9 |  |  |  |  | 33.6448 | Approved | Completed | Completed | Completed
[6 empty] | 9/7 | 435
90 |  | 9/8 | DA+0 |  |  |  |  | 34.0798 | Approved | Completed | Completed
[6 empty] | 9/8 | 405
89 |  | 9/9 | DA+0 |  |  |  |  | 34.4848 | Approved | Completed | Completed
[6 empty] | 9/9 | 435
90 |  | 9/10 | DA+3 |  |  |  |  | 34.9198 | Approved | Completed | Completed | Completed
[6 empty] | 9/10 | 395
91 |  | 9/11 | DA+3 |  |  |  |  | 35.3148 | Approved | Completed | Completed | Completed
[6 empty] | 9/11 | 431.548
92 | AP-10 | 10/0 | DB1+6 |  |  |  |  | 35.7463 | Approved | Completed | Completed | Completed
[6 empty] | 10/0 | 363.452
93 |  | 10/1 | DA+3 |  |  |  |  | 36.1098 | Approved | Completed | Completed | Completed
[6 empty] | 10/1 | 295
94 |  | 10/2 | DA+3 |  |  |  |  | 36.4048 | Approved | Completed | Completed | Completed
[6 empty] | 10/2 | 345.731
95 | AP-11 | 11/0 | DD45+0 |  |  |  |  | 36.7505 | Approved | Completed | Completed
[6 empty] | 11/0 | 242.893 | [7 empty] | NH
96 | AP-12 | 12/0 | DB1+9 |  |  |  |  | 36.9934 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 12/0 | 329.728 | [7 empty] | 132 KV PL
97 | AP-13 | 13/0 | DD60+9 |  |  |  |  | 37.3231 | Approved | Completed | Completed |  |  | Completed
[6 empty] | 13/0 | 416.878
98 | AP-13A | 13A/0 | DB1+9 |  |  |  |  | 37.74 | Approved | Completed | Completed
[6 empty] | 13A/0 | 480.269
99 | AP-14 | 14/0 | DD60+18 |  | 2 |  |  | 38.2203 | Approved | Completed | Completed
[6 empty] | 14/0 | 223.816 | [7 empty] | 400 KV PL
100 | AP-15 | 15/0 | DD60+25 |  |  |  |  | 38.4441 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 15/0 | 405.915
101 |  | 15/1 | DA+6 |  |  |  |  | 38.85 | Approved | Completed | Completed
[6 empty] | 15/1 | 405
102 |  | 15/2 | DA+3 |  |  |  |  | 39.255 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/2 | 420
103 |  | 15/3 | DA+3 |  |  |  |  | 39.675 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/3 | 415
104 |  | 15/4 | DA+6 |  |  |  |  | 40.09 | Approved | Completed | Completed | Completed
[6 empty] | 15/4 | 410
105 |  | 15/5 | DA+3 |  |  |  |  | 40.5 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/5 | 285
106 |  | 15/6 | DA+9 |  |  |  |  | 40.785 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/6 | 355
107 |  | 15/7 | DA+0 |  |  |  |  | 41.14 | Approved | Completed | Completed
[6 empty] | 15/7 | 355
108 |  | 15/8 | DA+1.5 |  |  |  |  | 41.495 | Approved | Completed | Completed | Completed
[6 empty] | 15/8 | 410
109 |  | 15/9 | DA+0 |  |  |  |  | 41.905 | Approved | Completed | Completed
[6 empty] | 15/9 | 430
110 |  | 15/10 | DA-1.5 |  |  |  |  | 42.335 | Approved | Completed | Completed
[6 empty] | 15/10 | 385
111 |  | 15/11 | DA+0 |  |  |  |  | 42.72 | Approved | Completed | Completed
[6 empty] | 15/11 | 455
112 |  | 15/12 | DA+6 |  |  |  |  | 43.175 | Approved | Completed
[6 empty] | 15/12 | 288.425
113 | AP-16 | 16/0 | DC2+0 |  |  |  |  | 43.4634 | Approved | Completed
[6 empty] | 16/0 | 392.694 | [7 empty] | 11KV LINE
114 | AP-17 | 17/0 | DC1+3 |  |  |  |  | 43.8561 | Approved | Completed | Completed
[6 empty] | 17/0 | 398.404 | [7 empty] | 11KV LINE
115 | AP-18 | 18/0 | DB2+6 |  |  |  |  | 44.2545 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 18/0 | 307.595
116 |  | 18/1 | DA+3 |  |  |  |  | 44.5621 | Approved | Completed | Completed | Completed
[6 empty] | 18/1 | 390
117 |  | 18/2 | DA+1.5 |  |  |  |  | 44.9521 | Approved | Completed | Completed | Completed
[6 empty] | 18/2 | 380
118 |  | 18/3 | DA+6 |  |  |  |  | 45.3321 | Approved | Completed | Completed | Completed
[6 empty] | 18/3 | 405
119 |  | 18/4 | DA-3 |  |  |  |  | 45.7371 | Approved | Completed | Completed | Completed
[6 empty] | 18/4 | 335
120 |  | 18/5 | DA+0 |  |  |  |  | 46.0721 | Approved | Completed | Completed | Completed
[6 empty] | 18/5 | 425
121 |  | 18/6 | DA+9 |  |  |  |  | 46.4971 | Approved | Completed | Completed | Completed
[6 empty] | 18/6 | 402
122 |  | 18/7 | DA+1.5 |  |  |  |  | 46.8991 | Approved | Completed | Completed | Completed
[6 empty] | 18/7 | 385.434
123 | AP-19 | 19/0 | DD60+3 |  |  |  |  | 47.2845 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 19/0 | 279.36 | [7 empty] | Rly
124 | AP-20 | 20/0 | DD60+3 |  |  |  |  | 47.5639 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 20/0 | 388.515
125 |  | 20/1 | DA-3 |  |  |  |  | 47.9524 | Approved | Completed | Completed | Completed
[6 empty] | 20/1 | 330
126 |  | 20/2 | DA-3 |  |  |  |  | 48.2824 | Approved | Completed | Completed | Completed
[6 empty] | 20/2 | 340
127 |  | 20/3 | DA+1.5 |  |  |  |  | 48.6224 | Approved | Completed | Completed | Completed
[6 empty] | 20/3 | 420
128 |  | 20/4 | DA+3 |  |  |  |  | 49.0424 | Approved | Completed | Completed | Completed
[6 empty] | 20/4 | 375
129 |  | 20/5 | DA+0 |  |  |  |  | 49.4174 | Approved | Completed | Completed | Completed
[6 empty] | 20/5 | 355
130 |  | 20/6 | DA-3 |  |  |  |  | 49.7724 | Approved | Completed | Completed | Completed
[6 empty] | 20/6 | 341.652
131 | AP-21 | 21/0 | DB1+0 |  |  |  |  | 50.1141 | Approved | Completed | Completed | Completed
[6 empty] | 21/0 | 326.348
132 |  | 21/1 | DA+0 |  |  |  |  | 50.4404 | Approved | Completed | Completed | Completed
[6 empty] | 21/1 | 427
133 |  | 21/2 | DA+6 |  |  |  |  | 50.8674 | Approved | Completed | Completed
[6 empty] | 21/2 | 410
134 |  | 21/3 | DA+6 |  |  |  |  | 51.2774 | Approved | Completed | Completed
[6 empty] | 21/3 | 405
135 |  | 21/4 | DA+0 |  |  |  |  | 51.6824 | Approved | Completed | Completed
[6 empty] | 21/4 | 300
136 |  | 21/5 | DA+0 |  |  |  |  | 51.9824 | Approved | Completed | Completed
[6 empty] | 21/5 | 415.187
137 | AP-22 | 22/0 | DC2+15 |  |  |  |  | 52.3976 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 22/0 | 259.048 | [7 empty] | 220 kv PL
138 | AP-23 | 23/0 | DB2+9 |  |  |  |  | 52.6566 | Approved | Completed | Completed
[6 empty] | 23/0 | 440.455
139 | AP-23A | 23A/0 | DB1+9 |  |  |  |  | 53.0971 | Approved | Completed | Completed
[6 empty] | 23A/0 | 496.685
140 | AP-24 | 24/0 | DD60+18 |  |  |  |  | 53.5938 | Approved | Completed | Completed
[6 empty] | 24/0 | 244.029 | [7 empty] | 400 kv PL
141 | AP-25 | 25/0 | DD60+18 |  |  |  |  | 53.8378 | Approved | Completed | Completed
[6 empty] | 25/0 | 237.428
142 | AP-26 | 26/0 | DD60+35 |  |  |  |  | 54.0752 | Approved | Completed | Completed | Completed
[6 empty] | 26/0 | 203.479 | [7 empty] | 765 kv PL
143 | AP-27 | 27/0 | DD60+35 |  |  |  |  | 54.2787 | Approved | Completed | Completed |  |  | Completed
[6 empty] | 27/0 | 453.688
144 |  | 27/1 | DA+9 |  |  |  |  | 54.7324 | Approved | Completed | Completed
[6 empty] | 27/1 | 345
145 |  | 27/2 | DA-1.5 |  |  |  |  | 55.0774 | Approved | Completed | Completed
[6 empty] | 27/2 | 360
146 |  | 27/3 | DA+1.5 |  |  |  |  | 55.4374 | Approved | Completed | Completed
[6 empty] | 27/3 | 410
147 |  | 27/4 | DA+1.5 |  |  |  |  | 55.8474 | Approved | Completed | Completed
[6 empty] | 27/4 | 350
148 |  | 27/5 | DA-1.5 |  |  |  |  | 56.1974 | Approved | Completed | Completed | Completed
[6 empty] | 27/5 | 355
149 |  | 27/6 | DA-3 |  |  |  |  | 56.5524 | Approved | Completed | Completed
[6 empty] | 27/6 | 274.587
150 | AP-28 | 28/0 | DC2-3 |  |  |  |  | 56.827 | Approved | Completed | Completed
[6 empty] | 28/0 | 211.209 | [7 empty] | NH
151 | AP-29 | 29/0 | DC1+0 |  |  |  |  | 57.0382 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 29/0 | 384.204
152 |  | 29/1 | DA+6 |  |  |  |  | 57.4224 | Approved | Completed | Completed | Completed
[6 empty] | 29/1 | 430
153 |  | 29/2 | DA+0 |  |  |  |  | 57.8524 | Approved | Completed | Completed
[6 empty] | 29/2 | 370
154 |  | 29/3 | DA+0 |  |  |  |  | 58.2224 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29/3 | 390
155 |  | 29/4 | DA+3 |  |  |  |  | 58.6124 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29/4 | 435
156 |  | 29/5 | DA+0 |  |  |  |  | 59.0474 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29/5 | 370
157 | AP-29A/0 | 29A/0 | DB1+0 |  |  |  |  | 59.4174 | Approved | Completed | Completed | Completed
[6 empty] | 29A/0 | 455
158 |  | 29A/1 | DA+6 |  |  |  |  | 59.8724 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29A/1 | 325
159 |  | 29A/2 | DA+6 |  |  |  |  | 60.1974 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29A/2 | 395
160 |  | 29A/3 | DA+6 |  |  |  |  | 60.5924 | Approved | Completed | Completed
[6 empty] | 29A/3 | 345
161 |  | 29A/4 | DA+3 |  |  |  |  | 60.9374 | Approved | Completed | Completed | Completed
[6 empty] | 29A/4 | 365
162 |  | 29A/5 | DA+6 |  |  |  |  | 61.3024 | Approved | Completed | Completed | Completed
[6 empty] | 29A/5 | 420
163 |  | 29A/6 | DA+9 |  |  |  |  | 61.7224 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29A/6 | 364.007
164 | AP-30 | 30/0 | DB1+0 |  |  |  |  | 62.0864 | Approved | Completed | Completed | Completed
[6 empty] | 30/0 | 295.993
165 |  | 30/1 | DA+0 |  |  |  |  | 62.3824 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 30/1 | 425
166 |  | 30/2 | DA+9 |  |  |  |  | 62.8074 | Approved | Completed | Completed | Completed
[6 empty] | 30/2 | 315
167 |  | 30/3 | DA+3 |  |  |  |  | 63.1224 | Approved | Completed | Completed | Completed
[6 empty] | 30/3 | 380
168 |  | 30/4 | DA+9 |  |  |  |  | 63.5024 | Approved | Completed | Completed | Completed
[6 empty] | 30/4 | 430
169 |  | 30/5 | DA+0 |  |  |  |  | 63.9324 | Approved | Completed | Completed
[6 empty] | 30/5 | 380
170 |  | 30/6 | DA+6 |  |  |  |  | 64.3124 | Approved | Completed | Completed | Completed
[6 empty] | 30/6 | 335
171 |  | 30/7 | DA-3 |  |  |  |  | 64.6474 | Approved | Completed | Completed | Completed
[6 empty] | 30/7 | 395
172 |  | 30/8 | DA+3 |  |  |  |  | 65.0424 | Approved | Completed | Completed | Completed
[6 empty] | 30/8 | 390
173 |  | 30/9 | DA-3 |  |  |  |  | 65.4324 | Approved | Completed | Completed | Completed
[6 empty] | 30/9 | 350
174 |  | 30/10 | DA+3 |  |  |  |  | 65.7824 | Approved | Completed | Completed | Completed
[6 empty] | 30/10 | 428.239
175 | AP-31 | 31/0 | DB1+0 |  |  |  |  | 66.2106 | Approved | Completed | Completed | Completed
[6 empty] | 31/0 | 376.761
176 |  | 31/1 | DA+3 |  |  |  |  | 66.5874 | Approved | Completed | Completed | Completed
[6 empty] | 31/1 | 410
177 |  | 31/2 | DA+1.5 |  |  |  |  | 66.9974 | Approved | Completed | Completed | Completed
[6 empty] | 31/2 | 430
178 |  | 31/3 | DA+3 |  |  |  |  | 67.4274 | Approved | Completed | Completed | Completed
[6 empty] | 31/3 | 380
179 |  | 31/4 | DA-1.5 |  |  |  |  | 67.8074 | Approved | Completed | Completed | Completed
[6 empty] | 31/4 | 445
180 |  | 31/5 | DA+6 |  |  |  |  | 68.2524 | Approved | Completed | Completed | Completed
[6 empty] | 31/5 | 385
181 |  | 31/6 | DA+9 |  |  |  |  | 68.6374 | Approved | Completed | Completed | Completed
[6 empty] | 31/6 | 420
182 |  | 31/7 | DA+0 |  |  |  |  | 69.0574 | Approved | Completed | Completed | Completed
[6 empty] | 31/7 | 415
183 |  | 31/8 | DA+0 |  |  |  |  | 69.4724 | Approved | Completed | Completed | Completed
[6 empty] | 31/8 | 310
184 |  | 31/9 | DA+1.5 |  |  |  |  | 69.7824 | Approved | Completed | Completed | Completed
[6 empty] | 31/9 | 445
185 |  | 31/10 | DA+4.5 |  |  |  |  | 70.2274 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 31/10 | 316.608
186 | AP-32 | 32/0 | DB2+0 |  |  |  |  | 70.544 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/0 | 385.51
187 |  | 32/1 | DA+6 |  |  |  |  | 70.9295 | Approved | Completed | Completed | Completed
[6 empty] | 32/1 | 390
188 |  | 32/2 | DA+9 |  |  |  |  | 71.3195 | Approved | Completed | Completed | Completed
[6 empty] | 32/2 | 410
189 |  | 32/3 | DA+6 |  |  |  |  | 71.7295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/3 | 430
190 |  | 32/4 | DA+9 |  |  |  |  | 72.1595 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/4 | 390
191 |  | 32/5 | DA+9 |  | 2 |  |  | 72.5495 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/5 | 439
192 |  | 32/6 | DA+9 |  | 2 |  |  | 72.9885 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/6 | 360
193 |  | 32/7 | DA+3 |  |  |  |  | 73.3485 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/7 | 479
194 | AP-32A/0 | 32A/0 | DB1+9 |  |  |  |  | 73.8275 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32A/0 | 402
195 |  | 32A/1 | DA+6 |  |  |  |  | 74.2295 | Approved | Completed | Completed | Completed
[6 empty] | 32A/1 | 438.439
196 | AP-33 | 33/0 | DB1+9 |  | 2 |  |  | 74.6679 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 33/0 | 441.561
197 |  | 33/1 | DA+9 |  | 2 |  |  | 75.1095 | Approved | Completed | Completed | Completed
[6 empty] | 33/1 | 395
198 |  | 33/2 | DA+9 |  |  |  |  | 75.5045 | Approved | Completed | Completed | Completed
[6 empty] | 33/2 | 435
199 |  | 33/3 | DA+3 |  |  |  |  | 75.9395 | Approved | Completed | Completed | Completed
[6 empty] | 33/3 | 405
200 |  | 33/4 | DA+3 |  |  |  |  | 76.3445 | Approved | Completed | Completed | Completed
[6 empty] | 33/4 | 420
201 |  | 33/5 | DA+0 |  |  |  |  | 76.7645 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 33/5 | 405
202 |  | 33/6 | DA+6 |  |  |  |  | 77.1695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 33/6 | 415
203 |  | 33/7 | DA+6 |  |  |  |  | 77.5845 | Approved | Completed | Completed | Completed
[6 empty] | 33/7 | 355
204 |  | 33/8 | DA+3 |  |  |  |  | 77.9395 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 33/8 | 380
205 |  | 33/9 | DA+1.5 |  |  |  |  | 78.3195 | Approved | Completed | Completed | Completed
[6 empty] | 33/9 | 398.203
206 | AP-34 | 34/0 | DB1+6 |  |  |  |  | 78.7177 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 34/0 | 441.798
207 |  | 34/1 | DA+9 |  |  |  |  | 79.1595 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/1 | 395
208 |  | 34/2 | DA+9 |  |  |  |  | 79.5545 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/2 | 375
209 |  | 34/3 | DA+1.5 |  |  |  |  | 79.9295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/3 | 445
210 |  | 34/4 | DA+6 |  |  |  |  | 80.3745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/4 | 395
211 |  | 34/5 | DA+9 |  |  |  |  | 80.7695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/5 | 435
212 |  | 34/6 | DA+3 |  |  |  |  | 81.2045 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/6 | 330
213 |  | 34/7 | DA+0 |  |  |  |  | 81.5345 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/7 | 330
214 |  | 34/8 | DA+0 |  |  |  |  | 81.8645 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/8 | 400
215 |  | 34/9 | DA+1.5 |  |  |  |  | 82.2645 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/9 | 310
216 |  | 34/10 | DA-3 |  |  |  |  | 82.5745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/10 | 315
217 |  | 34/11 | DA+1.5 |  |  |  |  | 82.8895 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/11 | 375
218 |  | 34/12 | DA+3 |  |  |  |  | 83.2645 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/12 | 351.79
219 | AP-35 | 35/0 | DB2+0 |  |  |  |  | 83.6163 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 35/0 | 393.209
220 |  | 35/1 | DA+6 |  |  |  |  | 84.0095 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/1 | 435
221 |  | 35/2 | DA+6 |  |  |  |  | 84.4445 | Approved | Completed |  | Completed
[6 empty] | 35/2 | 390
222 |  | 35/3 | DA-3 |  |  |  |  | 84.8345 | Approved | Completed
[6 empty] | 35/3 | 405
223 |  | 35/4 | DA+9 |  |  |  |  | 85.2395 | Approved | Completed | Completed | Completed
[6 empty] | 35/4 | 435
224 |  | 35/5 | DA+9 |  |  |  |  | 85.6745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/5 | 360
225 |  | 35/6 | DA+6 |  |  |  |  | 86.0345 | Approved | Completed | Completed | Completed
[6 empty] | 35/6 | 395
226 |  | 35/7 | DA+3 |  |  |  |  | 86.4295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/7 | 440
227 |  | 35/8 | DA+6 |  |  |  |  | 86.8695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/8 | 400
228 |  | 35/9 | DA+1.5 |  |  |  |  | 87.2695 | Approved | Completed | Completed | Completed
[6 empty] | 35/9 | 440
229 |  | 35/10 | DA+3 |  |  |  |  | 87.7095 | Approved | Completed
[6 empty] | 35/10 | 330
230 |  | 35/11 | DA+3 |  |  |  |  | 88.0395 | Approved | Completed | Completed | Completed
[6 empty] | 35/11 | 493.084
231 | AP-36 | 36/0 | DB2+3 |  |  |  |  | 88.5326 | Approved | Completed | Completed |  |  | Completed
[6 empty] | 36/0 | 453.999
232 |  | 36A/0 | DB1+9 |  |  |  |  | 88.9866 | Approved | Completed |  | Completed
[6 empty] | 36A/0 | 451
233 |  | 36A/1 | DA+3 |  |  |  |  | 89.4376 | Approved | Completed | Completed | Completed
[6 empty] | 36A/1 | 389
234 |  | 36A/2 | DA+9 |  |  |  |  | 89.8266 | Approved | Completed | Completed | Completed
[6 empty] | 36A/2 | 451.523
235 | AP-37 | 37/0 | DB2+3 |  |  |  |  | 90.2781 | Approved | Completed | Completed
[6 empty] | 37/0 | 401.394
236 |  | 37/1 | DA+3 |  |  |  |  | 90.6795 | Approved | Completed | Completed
[6 empty] | 37/1 | 430
237 |  | 37/2 | DA+3 |  |  |  |  | 91.1095 | Approved | Completed | Completed
[6 empty] | 37/2 | 405
238 |  | 37/3 | DA-1.5 |  |  |  |  | 91.5145 | Approved | Completed | Completed
[6 empty] | 37/3 | 430
239 |  | 37/4 | DA+9 |  |  |  |  | 91.9445 | Approved | Completed | Completed | Completed
[6 empty] | 37/4 | 410
240 |  | 37/5 | DA+3 |  |  |  |  | 92.3545 | Approved | Completed | Completed | Completed
[6 empty] | 37/5 | 420
241 | AP-37A | 37A/0 | DB1+0 |  |  |  |  | 92.7745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/0 | 280
242 |  | 37A/1 | DA+3 |  |  |  |  | 93.0545 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/1 | 345
243 |  | 37A/2 | DA+1.5 |  |  |  |  | 93.3995 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/2 | 330
244 |  | 37A/3 | DA+3 |  |  |  |  | 93.7295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/3 | 455
245 |  | 37A/4 | DA+9 |  |  |  |  | 94.1845 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 37A/4 | 340
246 |  | 37A/5 | DA+3 |  |  |  |  | 94.5245 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/5 | 435
247 |  | 37A/6 | DA+3 |  |  |  |  | 94.9595 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/6 | 398.589
248 | AP-38 | 38/0 | DB1+3 |  |  |  |  | 95.3581 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/0 | 426.411
249 |  | 38/1 | DA+0 |  |  |  |  | 95.7845 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/1 | 390
250 |  | 38/2 | DA+0 |  |  |  |  | 96.1745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/2 | 335
251 |  | 38/3 | DA+3 |  |  |  |  | 96.5095 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/3 | 440
252 |  | 38/4 | DA+1.5 |  |  |  |  | 96.9495 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/4 | 280
253 |  | 38/5 | DA+3 |  |  |  |  | 97.2295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/5 | 450
254 |  | 38/6 | DA+6 |  |  |  |  | 97.6795 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/6 | 285
255 |  | 38/7 | DA+9 |  |  |  |  | 97.9645 | Approved | Completed | Completed | Completed
[6 empty] | 38/7 | 445
256 |  | 38/8 | DA+1.5 |  |  |  |  | 98.4095 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/8 | 360
257 |  | 38/9 | DA+0 |  |  |  |  | 98.7695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/9 | 430
258 |  | 38/10 | DA+3 |  |  |  |  | 99.1995 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/10 | 322.266
259 | AP-39 | 39/0 | DB2+0 |  |  |  |  | 99.5218 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 39/0 | 392.73
260 |  | 39/1 | DA-1.5 |  |  |  |  | 99.9145 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/1 | 395
261 |  | 39/2 | DA+3 |  |  |  |  | 100.3095 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/2 | 385
262 |  | 39/3 | DA+1.5 |  |  |  |  | 100.6945 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/3 | 340
263 |  | 39/4 | DA+3 |  |  |  |  | 101.0345 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/4 | 395
264 |  | 39/5 | DA+1.5 |  |  |  |  | 101.4295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/5 | 410
265 |  | 39/6 | DA+1.5 |  |  |  |  | 101.8395 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/6 | 415
266 |  | 39/7 | DA+3 |  |  |  |  | 102.2545 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/7 | 415
267 |  | 39/8 | DA+1.5 |  |  |  |  | 102.6695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/8 | 350
268 |  | 39/9 | DA+6 |  |  |  |  | 103.0195 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/9 | 425
269 |  | 39/10 | DA+3 |  |  |  |  | 103.4445 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/10 | 350
270 |  | 39/11 | DA+6 |  |  |  |  | 103.7945 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/11 | 444.081
271 | AP-40 | 40/0 | DB1+6 |  |  |  |  | 104.2386 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 40/0 | 260.918
272 |  | 40/1 | DA+9 |  | 2 |  |  | 104.4995 | Approved | Completed | Completed | Completed
[6 empty] | 40/1 | 385
273 |  | 40/2 | DA+6 |  |  |  |  | 104.8845 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/2 | 435
274 |  | 40/3 | DA+3 |  |  |  |  | 105.3195 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/3 | 385
275 |  | 40/4 | DA+6 |  |  |  |  | 105.7045 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/4 | 455
276 |  | 40/5 | DA+9 |  |  |  |  | 106.1595 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/5 | 370
277 |  | 40/6 | DA+9 |  |  |  |  | 106.5295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/6 | 400
278 |  | 40/7 | DA+3 |  |  |  |  | 106.9295 | Approved | Completed | Completed | Completed
[6 empty] | 40/7 | 350
279 |  | 40/8 | DA-1.5 |  |  |  |  | 107.2795 | Approved | Completed | Completed | Completed
[6 empty] | 40/8 | 470
280 |  | 40/9 | DA+9 |  |  |  |  | 107.7495 | Approved | Completed | Completed | Completed
[6 empty] | 40/9 | 355
281 |  | 40/10 | DA+3 |  |  |  |  | 108.1045 | Approved | Completed | Completed | Completed
[6 empty] | 40/10 | 485
282 |  | 40/11 | DA+9 |  |  |  |  | 108.5895 | Approved | Completed | Completed | Completed
[6 empty] | 40/11 | 315
283 | AP-40A | 40A/0 | DB1+9 |  |  |  |  | 108.9045 | Approved | Completed | Completed | Completed
[6 empty] | 40A/0 | 410.607
284 | AP-41 | 41/0 | DB1+9 |  |  |  |  | 109.3151 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 41/0 | 358
285 |  | 41/1 | DA+9 |  |  |  |  | 109.6731 | Approved | Completed | Completed | Completed
[6 empty] | 41/1 | 465.782
286 | AP-42 | 42/0 | DB2+0 |  |  |  |  | 110.1389 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 42/0 | 419.998
287 |  | 42/1 | DA+3 |  |  |  |  | 110.5589 | Approved | Completed | Completed | Completed
[6 empty] | 42/1 | 375
288 |  | 42/2 | DA+9 |  |  |  |  | 110.9339 | Approved | Completed | Completed | Completed
[6 empty] | 42/2 | 464
289 |  | 42/3 | DB1+9 |  |  |  |  | 111.3979 | Approved | Completed | Completed | Completed
[6 empty] | 42/3 | 424.891
290 | AP-43 | 43/0 | DB1+0 |  |  |  |  | 111.8228 | Approved | Completed
[6 empty] | 43/0 | 341.866
291 |  | 43/1 | DA-1.5 |  |  |  |  | 112.1647 | Approved | Completed
[6 empty] | 43/1 | 375
292 |  | 43/2 | DA+6 |  |  |  |  | 112.5397 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 43/2 | 375
293 |  | 43/3 | DA-1.5 |  |  |  |  | 112.9147 | Approved | Completed | Completed | Completed
[6 empty] | 43/3 | 355
294 |  | 43/4 | DA+0 |  |  |  |  | 113.2697 | Approved | Completed | Completed | Completed
[6 empty] | 43/4 | 405
295 |  | 43/5 | DC2+0 |  |  |  |  | 113.6747 | Approved | Completed | Completed |  |  |  | TP tower modified cross arms
[6 empty] | 43/5 | 375
296 |  | 43/6 | DA+3 |  |  |  |  | 114.0497 | Approved | Completed | Completed | Completed
[6 empty] | 43/6 | 385
297 |  | 43/7 | DA+0 |  |  |  |  | 114.4347 | Approved | Completed | Completed | Completed
[6 empty] | 43/7 | 415
298 |  | 43/8 | DA+9 |  |  |  |  | 114.8497 | Approved | Completed | Completed | Completed
[6 empty] | 43/8 | 409.546
299 | AP-44 | 44/0 | DB1+6 |  |  |  |  | 115.2592 | Approved | Completed | Completed | Completed
[6 empty] | 44/0 | 400
300 |  | 44/1 | DA+3 |  |  |  |  | 115.6592 | Approved | Completed | Completed | Completed
[6 empty] | 44/1 | 427
301 |  | 44/2 | DA+3 |  |  |  |  | 116.0862 | Approved | Completed | Completed | Completed
[6 empty] | 44/2 | 366
302 |  | 44/3 | DA+3 |  |  |  |  | 116.4522 | Approved | Completed | Completed | Completed
[6 empty] | 44/3 | 350
303 |  | 44/4 | DA+0 |  |  |  |  | 116.8022 | Approved | Completed | Completed | Completed
[6 empty] | 44/4 | 383
304 |  | 44/5 | DA+0 |  |  |  |  | 117.1852 | Approved | Completed | Completed | Completed
[6 empty] | 44/5 | 457.155
305 | AP45 | 45/0 | DB1+9 |  |  |  |  | 117.6424 | Approved | Completed | Completed | Completed |  |  | PLC
[6 empty] | 45/0 | 208.53
306 | AP46 | 46/0 | DB1+12 | [5 empty] | Approved | Completed | Completed | Completed |  |  | PLC
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD60+0 to gantry
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DC2+0 to DD60+0
Note on D202: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD60+25 to DD60+18