## Stringing
S.no | Sec | from_ap | to_ap | length_m | unnamed_col_6 | method | unnamed_col_8 | Insulator Hoisting | po_start_date | po_completion_date | fs_starting_date | fs_complete_date | unnamed_col_14 | Jumpering | Spacering | Clipping | 7 484585479944454 | project_code | line_name | project_name | project_display | project_scope_key | project | _source_file | source_sheet | method_inferred | method_inference_reason | erection_locations_for_method | number_of_tse | s no | sec | location nos | section_readiness | insulator hoisting | po | jumpering | spacering | clipping | status | gang_name | gang strength | number of fitters | hindrance | remarks | unnamed_col_25 | unnamed_col_26 | revenue | tackwelding status | section | unnamed_col_1 | unnamed_col_7 | e rthwire | Remarks | towers in section | no of fitters | t l name | mp | status__2 | unnamed_col_17 | unnamed_col_19 | status__6 | dos__3 | doc__3 | status__7 | dos__4 | doc__4 | unnamed_col_16 | status__5 | specering | manpower | rough sag | unnamed_col_11
|  | From | To | Length in Km's | Cum. Length in Km's | TSE/Manual | Insulator hoisting Start | Insulator Hoisting Complete | Paying Out Start | Paying Out Completed | Final sag start | Final sag complete | Earthwire Final Sag | Jumpuring | Spacering | Clipping | Revenue | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
1 | 1 | AP-34 | AP-35 | 4.8986 | 4.8986 | TSE | 2025-02-06 | 2025-02-08 | 2025-02-21 | 2025-02-26 | 2025-03-01 | 2025-03-04 | 2025-03-05 | complete | complete | complete | 4696115.5929 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
2 | 1 | 37A/0 | AP-38/0 | 2.5836 | 7.4822 | TSE | 2025-03-11 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 2025-04-13 | 2025-04-16 | 2025-04-17 | 2025-04-21 | 2025-05-06 | complete | 2476802.0067 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
3 | 2 | AP-38 | AP-39 | 4.1637 | 11.6459 | TSE | 2025-03-26 | 2025-03-28 | 2025-03-29 | 2025-04-05 | 2025-04-15 | 2025-04-16 | 2025-04-17 | complete | complete | complete | 3991580.5297 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
4 | 3 | AP-39 | AP-40 | 4.716 | 16.3619 | TSE | 2025-04-04 | 2025-04-06 | 2025-04-25 | 2025-04-29 | 2025-04-29 | 2025-04-30 | 2025-05-27 | complete | 2025-12-23 | 2025-12-23 | 4521074.468 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
5 | 4 | AP-7 | AP-7A | 2.6993 | 19.0611 | TSE | 2025-08-21 | 2025-08-23 | 2025-08-27 | 2025-09-04 | 2025-09-17 | 2025-09-18 | 2025-09-18 | complete | complete | complete | 2587715.0073 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
6 | 4 | AP-7A | AP-8 | 2.4348 | 21.4959 | TSE | 2025-09-08 | 2025-09-10 | 2025-09-12 | 2025-09-16 | 2025-09-24 | 2025-09-25 | 2025-09-25 | complete | complete | complete | 2334134.1142 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
7 | 5 | AP-8 | AP-8A | 4.455 | 25.9509 | TSE | 2025-09-29 | 2025-10-01 | 2025-10-05 | 2025-10-15 | 2025-10-21 | 2025-10-22 | 2025-10-22 | 2025-10-28 | complete | complete | 4270862.3314 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
8 | 6 | AP-8A | AP-9/0 | 0.46663 | 26.4175 | Manual | 2025-09-29 | 2025-10-01 | 2025-10-03 | 2025-10-05 | 2025-10-26 | 2025-10-27 | 2025-10-27 | 9/0 Balance | complete | complete | 447341.9122 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
9 | 7 | AP-6 | AP-7 | 4.9012 | 31.3188 | TSE | 2025-11-12 | 2025-11-14 | 2025-11-19 | 2025-11-23 | 2025-11-27 | 2025-11-28 | 2025-11-30 | 2025-12-24 | 2025-12-19 | complete | 4698654.1436 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
10 | 8 | AP-5A | AP-6 | 0.41948 | 31.7383 | Manual | 2025-11-25 | 2025-11-27 | 2025-11-05 | 2025-11-09 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2026-01-11 | 2025-12-19 | complete | 402141.7129 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
11 | 9 | AP-5 | AP-5A | 4.4184 | 36.1566 | TSE | 2025-11-24 | 2025-12-05 | 2025-12-07 | 2025-12-12 | 2025-12-21 | 2025-12-22 | 2026-01-05 | 2026-02-16 | 2026-01-09 | complete | 4235764.567 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
12 | 10 | AP-4A | AP-5/0 | 2.6816 | 38.8383 | TSE | 2025-12-12 | 2025-12-14 | 2025-12-15 | 2025-12-22 | 2025-12-30 | 2025-12-31 | 2026-01-02 | 2026-02-21 | 2026-01-19 | 2026-01-11 | 2570772.482 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
13 | 1 | AP-4 | AP4A/0 | 0.70916 | 39.5474 | TSE | 2025-12-23 | 2025-12-25 | 2025-12-27 | 2025-12-31 | 2026-01-14 | 2026-01-18 | 2026-01-18 | complete | complete | complete | 679851.3005 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
14 | 2 | AP-33 | AP-34 | 4.0498 | 43.5972 | TSE | 2025-12-30 | 2026-01-04 | 2026-01-07 | 2026-01-13 | 2026-01-21 | 2026-01-24 | 2026-01-25 | complete | complete | complete | 3882375.874 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
15 | 3 | AP3B/0 | AP4/0 | 1.627 | 45.2242 | TSE | 2026-01-10 | 2026-01-12 | 2026-01-14 | 2026-01-17 | 2026-01-24 | 2026-01-27 | 2026-01-28 | complete | complete | 2026-02-01 | 1559751.5181 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
16 | 4 | AP-32A | AP-33 | 0.84 | 46.0642 | TSE | 2026-01-16 | 2026-01-19 | 2026-01-16 | 2026-01-19 | 2026-01-31 | 2026-02-06 | 2026-02-07 | complete | complete | complete | 805280.4396 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
17 | 5 | AP32/0 | AP32A/0 | 3.284 | 49.3482 | TSE | 2026-01-21 | 2026-01-24 | 2026-01-25 | 2026-01-30 | 2026-01-31 | 2026-02-06 | 2026-02-07 | complete | complete | complete | 3148263.052 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
18 | 1 | 2A/0 | 3A/0 | 2.837 | 52.1852 | TSE | 2026-02-09 | 2026-02-15 | 2026-02-18 | 2026-02-26 | 2026-02-27 | 2026-03-03 | 2026-03-05 | Half side balance | complete | complete | 2719738.818 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
19 | 2 | 3A/0 | 3B/0 | 2.6915 | 54.8766 | TSE | 2026-01-31 | 2026-02-06 | 2026-02-08 | 2026-02-13 | 2026-02-27 | 2026-03-03 | 2026-03-05 | complete | complete | complete | 2580221.1059 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
20 | 4 | 1/0 | 2A/0 | 0.29 | 55.1666 | Manual | 2026-02-10 | 2026-02-12 | 2026-02-14 | 2026-02-18 | 2026-03-09 | 2026-03-13 | 2026-03-14 | Balance | complete | complete | 278013.4851 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
21 | 3 | 31/0 | 32/0 | 4.333 | 59.4996 | TSE | 2026-01-02 | 2026-02-08 | 2026-02-10 | 2026-02-15 | 2026-03-02 | 2026-03-10 | 2026-03-11 | complete | complete | complete | 4153904.9343 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
22 | 1 | 30/0 | 31/0 | 4.124 | 63.6236 | TSE | 2026-02-16 | 2026-02-25 | 2026-02-27 | 2026-03-06 | 2026-03-12 | 2026-03-16 | 2026-03-17 | complete | complete | complete | 3953543.4916 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
23 | 1 | 9/0 | 10/0 | 4.9649 | 68.5886 | TSE | 2026-03-03 | 2026-03-20 | 2026-03-28 | 2026-04-02 | 2026-04-06 | 2026-04-10 | 2026-04-10 | complete | complete | complete | 4759705.905 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
24 | 1 | 29A/0 | 30/0 | 2.669 | 71.2576 | TSE | 2026-04-06 | 2026-04-09 | 2026-04-22 | 2026-04-28 | 2026-04-30 | 2026-05-03 | 2026-05-04 | complete | complete | complete | 2558689.4408 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
25 | 2 | 10/0 | 11/0 | 1.0042 | 72.2618 | TSE | 2026-03-31 | 2026-04-04 | 2026-04-07 | 2026-04-09 | 2026-05-12 | 2026-05-16 | 2026-05-16 |  | complete | complete | 962677.2949 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
26 | 3 | 29/0 | 29A/0 | 2.3792 | 74.641 | TSE | 2026-04-28 | 2026-05-02 | 2026-05-08 | 2026-05-12 | 2026-05-13 | 2026-05-16 | 2026-05-16 | complete | complete | complete | 2280864.8131 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
27 | 4 | 27/0 | 28/0 | 2.5483 | 77.1892 | TSE | 2026-05-17 | 2026-05-20 | 2026-05-20 | 2026-05-23 | 2026-05-24 | 2026-05-27 | 2026-05-28 |  | complete | complete | 2442947.6336 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
28 | 1 | 11/0 | 12/0 | 0.24289 | 77.4321 | Manual | 2026-06-01 | 2026-06-03 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-06 | 2026-06-06 |  | complete | complete | 232850.6738 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
29 | 2 | 14/0 | 15/0 | 0.22382 | 77.6559 | Manual | 2026-06-01 | 2026-06-03 | 2026-06-07 | 2026-06-12 | 2026-06-07 | 2026-06-12 | 2026-06-12 |  | complete |  | 214568.8905 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
30 | 3 | 13/0 | 13A/0 | 0.41688 | 78.0728 | Manual | 2026-03-01 | 2026-03-06 | 2026-06-19 | 2026-06-23 | 2026-06-19 | 2026-06-23 | 2026-06-23 |  | complete |  | 399647.2608 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
31 | 4 | 13A/0 | 14/0 | 0.48027 | 78.5531 | Manual | 2026-03-01 | 2026-03-06 | 2026-06-19 | 2026-06-23 | 2026-06-19 | 2026-06-23 | 2026-06-23 |  | complete |  | 460419.0913 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
32 | 5 | 18/0 | 19/0 | 3.03 | 81.5831 | TSE | 2026-06-07 | 2026-06-11 | 2026-06-13 | 2026-06-18 | 2026-06-25 | 2026-06-28 | 2026-06-28 |  |  | complete | 2904789.387 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
33 | 6 | 35/0 | 36/0 | 4.9163 | 86.4994 | TSE | 2026-06-02 | 2026-06-07 | 2026-06-13 | 2026-06-26 | 2026-06-26 | 2026-06-27 | 2026-06-27 |  |  | complete 35/3 ROW | 4713088.7955 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
34 | 7 | 24/0 | 25/0 | 0.24403 | 86.7434 | Manual | 2026-06-17 | 2026-06-18 | 2026-06-21 | 2026-06-26 | 2026-06-22 | 2026-06-26 | 2026-06-26 |  | complete |  | 233943.5544 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
35 | 8 | 23A/0 | 24/0 | 0.49669 | 87.2401 | Manual | 2026-06-19 | 2026-06-20 | 2026-06-22 | 2026-06-26 | 2026-06-22 | 2026-06-26 | 2026-07-05 |  | complete |  | 476160.4066 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
36 | 1 | 28/0 | 29/0 | 0.21121 | 87.4513 | Manual | 2025-06-27 | 2026-06-28 | 2026-07-01 | 2026-07-02 | 2026-07-01 | 2026-07-02 | 2026-07-02 | complete | complete |  | 202480.0972 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
37 | 2 | 23/0 | 23A/0 | 0.44046 | 87.8918 | Manual | 2026-06-28 | 2026-06-29 | 2026-07-01 | 2026-07-04 | 2026-07-01 | 2026-07-04 | 2026-07-05 |  | complete |  | 422254.5505 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
38 | 3 | 36/0 | 36A/0 | 0.454 | 88.3458 | Manual | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-09 | 2026-07-11 | 2026-07-12 |  | complete |  | 435234.9043 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
39 | 4 | 25/0 | 26/0 | 0.23743 | 88.5832 | Manual | 2026-07-07 | 2026-07-07 | 2026-07-01 | 2026-07-16 | 2026-07-14 | 2026-07-16 | 2026-07-16 |  |  |  | 227616.3509 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
40 | 5 | 15/0 | 16/0 | 5.0193 | 93.6026 | TSE | 2026-06-06 | 2026-06-14 | 2026-07-09 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-21 |  |  |  | 4811876.5735 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
41 | 6 | 40/0 | 40A/0 | 4.6659 | 98.2685 | TSE | 2026-06-21 | 2026-07-11 | 2026-07-15 | 2026-07-22 | 2026-07-23 | 2026-07-26 | 2026-07-27 | complete |  |  | 4473062.4978 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
42 | 7 | 22/0 | 23/0 | 0.25905 | 98.5275 | Manual | 2026-07-21 | 2026-07-24 | 2026-07-27 | 2026-07-28 | 2026-07-27 | 2026-07-28 | 2026-07-28 |  |  |  | 248342.7356 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
43 | 8 | 20/0 | 21/0 | 2.5502 | 101.0777 | TSE | 2026-06-21: 2026-07-13; 2026-07-11: 2026-07-23; 2026-07-15: 2026-07-25; 2026-07-22: 2026-07-29 |  |  |  | 2444761.4319 | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
44 |  | 43A/0 | 44/0 | 1.5845 | 102.6623 | TSE | 2026-06-21: 2026-07-25; 2026-07-11: 2026-07-31; 2026-07-15: 2026-08-01; 2026-07-22: 2026-08-04 |  |  |  |  | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
45 |  | 26/0 | 27/0 | 0.20348 | 102.8657 | Manual | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-07 | 2026-08-01 | 2026-08-07 | [5 empty] | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
46 |  | 44/0 | 45/0 | 2.383 | 105.2487 | TSE | 2026-06-21: 2026-08-05 |  |  |  |  | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
47 |  | 21/0 | 22/0 | 2.2835 | 107.5323 | TSE | 2026-06-21: 2026-07-31; 2026-07-11: 21/2 ROW |  |  |  |  | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
48 |  | 12/0 | 13/0 | 0.32973 | 107.862 | Manual | 2026-06-21: 2026-08-04 |  |  |  |  | TA 413 |  | TA 413 | TA 413 | ta413 | TA 413 | TA 413 - DPR - 2026-08-07.xlsx | Stringing | FALSE
|  | 117/0 | 118/0 | 1142.762 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 1 |  | 117/1,117/2 | Ready
|  | 118/0 | 119/0 | 243.824 |  | Manual | 2026-07-15: 2026-05-23; 2026-07-22: 2026-05-29; 2026-07-23: 2026-05-23; 2026-07-26: 2026-05-29 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 2 |  |  | Complete | Done | Completed | Completed | Completed |  | Completed | Dharmendra | 24
|  | 119/0 | 120/0 | 1421.595 |  | TSE | 2026-07-15: 2026-04-16; 2026-07-22: 2026-05-18; 2026-07-23: 2026-05-29; 2026-07-26: 2026-05-31 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 3 |  | 119/1,119/2,119/3 | Complete | Done | Completed | Completed | Completed | Completed | Completed | Enamul Haque | 49
|  | 120/0 | 121/0 | 2861.678 |  | TSE | 2026-07-15: 2026-05-03; 2026-07-22: 2026-05-08; 2026-07-23: 2026-05-10; 2026-07-26: 2026-05-15 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 4 |  | 120/1,120/2,120/3,120/4,120/5,120/6,120/7 | Complete | Done | Completed |  | Completed | Completed | Completed | Enamul Haque | 49
|  | 121/0 | 121/1 | 276.141 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 5 |  |  | Ready | [6 empty] | Enamul Haque | 49
|  | 121/1 | 121/7 | 2284 |  | TSE | 2026-07-15: 2026-04-13; 2026-07-22: 2026-04-16; 2026-07-23: 2026-05-19; 2026-07-26: 2026-05-21 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 6 |  | 121/2,121/3,121/4,121/5,121/6 | Complete | Done | Completed |  | Completed | Completed | Completed | Enamul Haque | 45
|  | 121/7 | 124/0 | 1937.394 |  | TSE/Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 7 |  | 121/8,121/9,121/10,121/11 | Complete | Done
|  | 124/0 | 125/0 | 1472.589 |  | TSE | 2026-07-15: 2026-06-09; 2026-07-22: 2026-06-13; 2026-07-23: 2026-06-16; 2026-07-26: 2026-06-19 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 8 |  | 124/1,124/2,124/3 | Complete | Done | Completed |  |  |  |  | Enamul Haque | 45
|  | 125/0 | 126/0 | 1288.931 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 9 |  | 125/1,125/2 | Ready
|  | 126/0 | 127/0 | 1584.22 |  | TSE | 2026-07-15: 2026-05-24; 2026-07-22: 2026-05-27; 2026-07-23: 2026-06-03; 2026-07-26: 2026-06-05 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 10 |  | 126/1,126/2,126/3 | Complete | Done | Completed |  | Completed | Completed | Completed | Enamul Haque | 45
|  | 127/0 | 127/2 | 709.979 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 11 |  | 127/1 | Not Ready
|  | 127/2 | 128/0 | 339.13 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 12 |  |  | Not Ready
|  | 128/0 | 129/0 | 620 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 13 |  |  | Not Ready
|  | 129/0 | 130/0 | 620.06 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 14 |  |  | Not Ready
|  | 130/0 | 131/0 | 535.07 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 15 |  |  | Not Ready
|  | 131/0 | 132/0 | 2201.62 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 16 |  | 131/1,131/2,131/3,131/4,131/5 | Not Ready
|  | 132/0 | 133/0 | 1217.54 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 17 |  | 132/1,132/2,132/3 | Not Ready
|  | 133/0 | 133/2 | 767 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 18 |  | 133/1 | Not Ready
|  | 133/2 | 133/3 | 250 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 19 |  |  | Ready
|  | 133/3 | 134/0 | 833.85 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 20 |  | 133/4 | Ready
|  | 134/0 | 135/0 | 360.67 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 21 |  |  | Not Ready
|  | 135/0 | 136/0 | 247.871 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 22 |  |  | Not Ready
|  | 136/0 | 136/1 | 459.998 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 23 |  |  | Ready
|  | 136/1 | 137/0 | 455.963 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 24 |  |  | Ready
|  | 137/0 | 138/0 | 1116.114 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 25 |  | 137/1,137/2 | Ready
|  | 138/0 | 139/0 | 460.541 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 26 |  |  | Ready
|  | 139/0 | 139/2 | 716.09 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 27 |  | 139/1 | Ready
|  | 139/2 | 139/3 | 340 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 28 |  |  | Ready
|  | 139/3 | 140/0 | 360.1 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 29 |  |  | Ready
|  | 140/0 | 141/0 | 204 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 30 |  |  | Ready
|  | 141/0 | 142/0 | 2659.63 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 31 |  | 141/1,141/2,141/3,141/4,141/5,141/6 | WIP
|  | 142/0 | 143/0 | 164.303 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 32 |  |  | Ready
|  | 143/0 | 144/0 | 277.27 |  | Hotline | 2026-07-15: 2026-06-08; 2026-07-22: 2026-06-13; 2026-07-23: 2026-06-08; 2026-07-26: 2026-06-13 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 33 |  |  | Complete | Done | Completed
|  | 144/0 | 145/0 | 451.679 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 34 |  |  | Ready
|  | 145/0 | 145/7 | 2776 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 35 |  | 145/1,145/2,145/3,145/4,145/5,145/6 | Not Ready
|  | 145/7 | 147/0 | 344.268 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 36 |  |  | Ready
|  | 147/0 | 148/0 | 251.645 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 37 |  |  | Ready
|  | 148/0 | 148/5 | 2077.997 |  | TSE | 2026-07-15: 2026-06-18; 2026-07-22: 2026-06-22; 2026-07-23: 2026-06-26; 2026-07-26: 2026-06-28 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 38 |  | 148/1,148/2,148/3,148/4 | Complete | Done | Completed
|  | 148/5 | 149/0 | 508.088 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 39 |  |  | Ready
|  | 149/0 | 150/0 | 258.002 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 40 |  |  | Not Ready
|  | 150/0 | 150/1 | 281 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 41 |  |  | Not Ready
|  | 150/1 | 151/0 | 367.61 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 42 |  |  | Not Ready
|  | 151/0 | 151A/0 | 266.99 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 43 |  |  | Not Ready
|  | 151A/0 | 152/0 | 500.05 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 44 |  |  | Not Ready
|  | 152/0 | 153/0 | 295 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 45 |  |  | Not Ready
|  | 153/0 | 153A/0 | 1184.01 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 46 |  | 153/1,153/2 | Not Ready
|  | 153A/0 | 154/0 | 490.15 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 47 |  |  | Not Ready
|  | 154/0 | 155/0 | 295.36 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 48 |  |  | Not Ready
|  | 155/0 | 156/0 | 257.34 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 49 |  |  | Not Ready
|  | 156/0 | 156/1 | 342.99 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 50 |  |  | Not Ready
|  | 156/1 | 157/0 | 335.33 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 51 |  |  | Not Ready
|  | 157/0 | 158/0 | 230 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 52 |  |  | Not Ready
|  | 158/0 | 159/0 | 253.62 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 53 |  |  | Not Ready
|  | 159/0 | 160/0 | 333.34 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 54 |  |  | Not Ready
|  | 160/0 | 161/0 | 392.23 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 55 |  |  | Ready
|  | 161/0 | 162/0 | 248.002 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 56 |  |  | Not Ready
|  | 162/0 | 163/0 | 328.496 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 57 |  |  | Not Ready
|  | 163/0 | 163/1 | 382.995 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 58 |  |  | Not Ready
|  | 163/1 | 164/0 | 401.589 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 59 |  |  | Not Ready
|  | 164/0 | 165/0 | 285.055 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 60 |  |  | Not Ready
|  | 165/0 | 165/6 | 2297.996 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 61 |  | 165/1,165/2,165/3,165/4,165/5 | Not Ready
|  | 165/6 | 166/0 | 730.096 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 62 |  | 165/7 | Not Ready
|  | 166/0 | 167/0 | 280 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 63 |  |  | Ready
|  | 167/0 | 168/0 | 576.145 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 64 |  |  | Not Ready
|  | 168/0 | 169/0 | 255.601 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 65 |  |  | Not Ready
|  | 169/0 | 170/0 | 521.312 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 66 |  |  | Not Ready
|  | 170/0 | 171/0 | 261.446 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 67 |  |  | Not Ready
|  | 171/0 | 172/0 | 186.772 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 68 |  |  | Not Ready
|  | 172/0 | 173/0 | 689.629 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 69 |  | 172/1 | Not Ready
|  | 173/0 | 174/0 | 215.227 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 70 |  |  | Not Ready
|  | 174/0 | 175/0 | 2633.369 |  | TSE | 2026-07-15: 2026-05-03; 2026-07-22: 2026-05-09; 2026-07-23: 2026-05-30; 2026-07-26: 2026-06-04 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 71 |  | 174/1,174/2,174/3,174/4,174/5,174/6 | Complete | Done | Completed |  | Completed | Completed |  | Alam Construction | 40
|  | 175/0 | 175/1 | 468.001 |  | Hotline | 2026-07-15: 2026-05-02; 2026-07-22: 2026-05-07; 2026-07-23: 2026-05-03; 2026-07-26: 2026-05-07 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 72 |  |  | Complete | Done | Completed |  | Completed |  |  | Alam Construction | 40 |  |  | Hotline
|  | 175/1 | 176/0 | 445.528 |  | Manual | 2026-07-15: 2026-04-06; 2026-07-22: 2026-04-12; 2026-07-23: 2026-04-07; 2026-07-26: 2026-04-12 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 73 |  |  | Complete | Done | Completed |  | Completed | Completed | Completed | Maa Singhvahini | 27
|  | 176/0 | 177/0 | 1043.334 |  | TSE | 2026-07-15: 2026-04-24; 2026-07-22: 2026-04-27; 2026-07-23: 2026-04-24; 2026-07-26: 2026-04-28 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 74 |  | 176/1,176/2 | Complete | Done | Completed |  | Completed | Completed | Completed | Alam Construction | 40
|  | 177/0 | 178/0 | 228.09 |  | Hotline | 2026-07-15: 2026-05-15; 2026-07-22: 2026-05-20; 2026-07-23: 2026-05-20; 2026-07-26: 2026-05-20 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 75 |  |  | Complete | Done | Completed |  | Completed |  | Completed | Sanjay singh 2 | 33
|  | 178/0 | 179/0 | 1326.507 |  | TSE | 2026-07-15: 2026-05-14; 2026-07-22: 2026-05-26; 2026-07-23: 2026-05-17; 2026-07-26: 2026-05-26 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 76 |  | 178/1,178/2,178/3 | Complete | Done | Completed |  | Completed |  | Completed
|  | 179/0 | 180/0 | 1582.474 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 77 |  | 179/1,179/2,179/3 | Not Ready
|  | 180/0 | 180/2 | 821.997 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 78 |  | 180/1 | Not Ready
|  | 180/2 | 182/0 | 2412.62 |  | TSE | 2026-07-15: 2026-04-06; 2026-07-22: 2026-04-13; 2026-07-23: 2026-04-14; 2026-07-26: 2026-04-16 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 79 |  | 180/3,180/4,180/5,180/6,180/7 | Complete | Done | Completed |  | Completed | Completed | Completed | Alam Construction | 68 |  | 5
|  | 182/0 | 183/0 | 208.909 |  | Hotline | 2026-07-15: 2026-04-05; 2026-07-22: 2026-04-11; 2026-07-23: 2026-04-05; 2026-07-26: 2026-04-11 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 80 |  |  | Complete | Done | Completed |  | Completed | Completed | Completed | Sanjay Singh | 20 |  |  | Hotline
|  | 183/0 | 184/0 | 1479.41 |  | TSE | 2026-07-15: 2026-04-18; 2026-07-22: 2026-04-21; 2026-07-23: 2026-04-20; 2026-07-26: 2026-04-22 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 81 |  | 183/1,183/2,183/3 | Complete | Done | Completed |  | Completed | Completed | Completed | Alam Construction | 40 |  | 1
|  | 184/0 | 185/0 | 210.17 |  | Hotline | 2026-07-15: 2026-05-06; 2026-07-22: 2026-05-13; 2026-07-23: 2026-05-06; 2026-07-26: 2026-05-13 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 82 |  |  | Complete | Done | Completed |  | Completed |  | Completed | Sanjay Singh 1 | 20
|  | 185/0 | 186/0 | 271 |  | Hotline | 2026-07-15: 2026-05-24; 2026-07-22: 2026-05-31; 2026-07-23: 2026-05-24; 2026-07-26: 2026-05-31 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 83 |  |  | Complete | Done | Completed |  | Completed |  | Completed | Sanjay Singh 2 | 33
|  | 186/0 | 187/0 | 390.65 |  | Hotline | 2026-07-15: 2026-06-05; 2026-07-22: 2026-06-12; 2026-07-23: 2026-06-05; 2026-07-26: 2026-06-12 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 84 |  |  | Complete | Done | Completed |  | Completed
|  | 187/0 | 188/0 | 428.21 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 85 |  |  | Not Ready
|  | 188/0 | 189/0 | 672.59 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 86 |  |  | Not Ready
|  | 189/0 | 190/0 | 807.98 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 87 |  | 189/1 | Not Ready
|  | 190/0 | 191/0 | 226.48 |  | Hotline | 2026-07-15: 2026-05-28; 2026-07-22: 2026-06-01; 2026-07-23: 2026-05-28; 2026-07-26: 2026-06-01 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 88 |  |  | Complete | Done | Completed
|  | 191/0 | 191/1 | 465.47 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 89 |  |  | Ready | Done
|  | 191/1 | 192/0 | 389.51 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 90 |  |  | Ready | Done
|  | 192/0 | 193/0 | 222.83 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 91 |  |  | Not Ready
|  | 193/0 | 194/0 | 277.42 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 92 |  |  | Not Ready
|  | 194/0 | 194/1 | 470 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 93 |  |  | Not Ready
|  | 194/1 | 195/0 | 479.7 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 94 |  |  | Not Ready
|  | 195/0 | 196/0 | 239.69 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 95 |  |  | Not Ready
|  | 196/0 | 197/0 | 1148.42 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 96 |  | 196/1,196/2 | Ready
|  | 197/0 | 198/0 | 983.72 |  | Manual | 2026-07-15: 2026-05-18; 2026-07-22: 2026-06-01; 2026-07-23: 2026-06-29; 2026-07-26: 2026-07-05 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 97 |  | 197/1,197/2 | Complete | Done | Completed |  | Completed | Completed | Completed | Abdul adut
|  | 198/0 | 199/0 | 246.74 |  | Hotline | 2026-07-15: 2026-04-17; 2026-07-22: 2026-04-23; 2026-07-23: 2026-04-17; 2026-07-26: 2026-04-23 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 98 |  |  | Complete | Done | Completed |  | Completed |  | Completed
|  | 199/0 | 200/0 | 1266.29 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 99 |  | 199/1,199/2 | Not Ready
|  | 200/0 | 201/0 | 709.98 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 100 |  | 200/1 | Not Ready
|  | 201/0 | 202/0 | 513.96 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 101 |  |  | Not Ready
|  | 202/0 | 203/0 | 233.14 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 102 |  |  | Not Ready
|  | 203/0 | 203A/0 | 128.02 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 103 |  |  | Not Ready
|  | 203A/0 | 203B/0 | 282.82 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 104 |  |  | Not Ready
|  | 203B/0 | 204/0 | 339.95 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 105 |  |  | Not Ready
|  | 204/0 | 205/0 | 172.64 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 106 |  |  | Not Ready
|  | 205/0 | 205/1 | 555.17 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 107 |  |  | Not Ready
|  | 205/1 | 206/0 | 811.52 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 108 |  | 205/2 | Not Ready
|  | 206/0 | 206/1 | 184.81 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 109 |  |  | Not Ready
|  | 206/1 | 207/0 | 214.27 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 110 |  |  | Not Ready
|  | 207/0 | 208/0 | 272.3 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 111 |  |  | Not Ready
|  | 208/0 | 209/0 | 284.64 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 112 |  |  | Not Ready
|  | 209/0 | 210/0 | 1036.29 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 113 |  | 209/1,209/2 | Ready
|  | 210/0 | 211/0 | 397.66 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 114 |  |  | Not Ready
|  | 211/0 | 211/5 | 1872 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 115 |  | 211/1,211/2,211/3,211/4 | Not Ready
|  | 211/5 | 212/0 | 266.961 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 116 |  |  | Not Ready
|  | 212/0 | 213/0 | 378.221 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 117 |  |  | Not Ready
|  | 213/0 | 214/0 | 325.229 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 118 |  |  | Not Ready
|  | 214/0 | 215/0 | 2987.2165 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 119 |  | 214/1,214/2,214/3,214/4,214/5,214/6,214/7 | Ready
|  | 215/0 | 216/0 | 231.41 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 120 |  |  | Ready
|  | 216/0 | 216/2 | 803 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 121 |  | 216/1 | Not Ready
|  | 216/2 | 217/0 | 749.12 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 122 |  | 216/3 | Not Ready
|  | 217/0 | 218/0 | 2245.811 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 123 |  | 217/1,217/2,217/3,217/4,217/5 | Not Ready
|  | 218/0 | 219/0 | 239.47 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 124 |  |  | Not Ready
|  | 219/0 | 220/0 | 798.41 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 125 |  | 219/1 | Not Ready
|  | 220/0 | 221/0 | 819.27 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 126 |  | 220/1 | Ready
|  | 221/0 | 222/0 | 191.81 |  | Hotline | 2026-07-15: 2026-06-19; 2026-07-22: 2026-06-25; 2026-07-23: 2026-06-19; 2026-07-26: 2026-06-25 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 127 |  |  | Complete | Done | Completed |  | Completed |  |  | Sanjay Singh 1 | 20
|  | 222/0 | 223/0 | 248.6 |  | Hotline | 2026-07-15: 2026-06-19; 2026-07-22: 2026-06-25; 2026-07-23: 2026-06-19; 2026-07-26: 2026-06-25 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 128 |  |  | Complete | Done | Completed |  | Completed |  |  | Sanjay Singh 2 | 33
|  | 223/0 | 224/0 | 1386.17 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 129 |  | 223/1,223/2,223/3 | Not Ready
|  | 224/0 | 224/2 | 714 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 130 |  | 224/1 | Not Ready
|  | 224/2 | 225/0 | 431.2 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 131 |  |  | Ready
|  | 225/0 | 226/0 | 2965.43 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 132 |  | 225/1,225/2,225/3,225/4,225/5,225/6,225/7 | Not Ready
|  | 226/0 | 227/0 | 1574.68 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 133 |  | 226/1,226/2,226/3 | Ready
|  | 227/0 | 228/0 | 1238.74 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 134 |  | 227/1,227/2 | Ready
|  | 228/0 | 229/0 | 767.07 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 135 |  | 228/1 | Not Ready
|  | 229/0 | 229A/0 | 791.5 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 136 |  | 229/1 | Not Ready
|  | 229A/0 | 229B/0 | 179.98 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 137 |  |  | Not Ready
|  | 229B/0 | 230/0 | 390.65 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 138 |  |  | Not Ready
|  | 230/0 | 230A/0 | 786.67 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 139 |  | 230/1 | Not Ready
|  | 230A/0 | 231/0 | 239.51 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 140 |  |  | Not Ready
|  | 231/0 | 232/0 | 246.98 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 141 |  |  | Not Ready
|  | 232/0 | 233/0 | 1728.185 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 142 |  | 232/1,232/2,232/3,232/4 | Not Ready
|  | 233/0 | 234/0 | 411.1429 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 143 |  |  | Not Ready
|  | 234/0 | 235/0 | 295 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 144 |  |  | Not Ready
|  | 235/0 | 236/0 | 1763.541 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 145 |  | 235/1,235/2,235/3,235/4 | Not Ready
|  | 236/0 | 237/0 | 200.821 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 146 |  |  | Not Ready
|  | 237/0 | 238/0 | 202.277 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 147 |  |  | Not Ready
|  | 238/0 | 239/0 | 363.321 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 148 |  |  | Not Ready
|  | 239/0 | 240/0 | 737.403 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 149 |  | 239/1 | Ready
|  | 240/0 | 241/0 | 734.048 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 150 |  | 240/1 | Ready
|  | 241/0 | 242/0 | 1835.738 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 151 |  | 241/1,241/2,241/3,241/4 | Ready
|  | 242/0 | 243/0 | 280.015 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 152 |  |  | Ready
|  | 243/0 | 244/0 | 1372.6 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 153 |  | 243/1,243/2,243/3 | Ready
|  | 244/0 | 245/0 | 2778.121 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 154 |  | 244/1,244/2,244/3,244/4,244/5,244/6 | Ready
|  | 245/0 | 246/0 | 791.626 |  | Manual | 2026-07-15: 2026-04-11; 2026-07-22: 2026-04-14; 2026-07-23: 2026-04-14; 2026-07-26: 2026-04-15 |  |  |  |  | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 155 |  | 245/1 | Complete | Done | Completed |  | Completed | Completed | Completed | Bhola prasad+ Deepak Sarkar | 30
|  | 246/0 | 247/0 | 463.1 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 156 |  |  | Not Ready
|  | 247/0 | 248/0 | 256.45 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 157 |  |  | Not Ready
|  | 248/0 | 248/1 | 425.57 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 158 |  |  | Not Ready
|  | 248/1 | 249/0 | 566.9 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 159 |  | 248/2 | Not Ready
|  | 249/0 | 250/0 | 1620.626 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 160 |  | 249/1,249/2,249/3 | Not Ready
|  | 250/0 | 250A/0 | 1630.951 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 161 |  | 250/1,250/2,250/3 | Ready
|  | 250A/0 | 251/0 | 1133.974 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 162 |  | 250A/1,250A/2 | Ready
|  | 251/0 | 252/0 | 840.868 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 163 |  | 251/1 | Ready
|  | 252/0 | 252/5 | 2021.996 |  | TSE | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 164 |  | 252/1,252/2,252/3,252/4 | Ready
|  | 252/5 | 253/0 | 487.454 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 165 |  |  | Not Ready
|  | 253/0 | 254/0 | 304.46 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 166 |  |  | Not Ready
|  | 254/0 | 254/1 | 353.19 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 167 |  |  | Not Ready
|  | 254/1 | 255/0 | 263.06 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 168 |  |  | Ready
|  | 255/0 | 256/0 | 736.76 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 169 |  | 255/1 | Ready
|  | 256/0 | 257/0 | 583.35 |  | Hotline | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 170 |  | 256/1 | Not Ready
|  | 257/0 | 258/0 | 94.77 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 171 |  |  | Not Ready
|  | 258/0 | Gantry | 79 |  | Manual | [11 empty] | TA 414 |  | TA 414 | TA 414 | ta414 | TA 414 | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 172 |  |  | Not Ready
|  | AP7/0 | AP8/0 | 4818.75 |  | TSE | 2026-07-15: 2025-05-03; 2026-07-22: 2025-05-12; 2026-07-23: 2025-05-15; 2026-07-26: 2025-05-18 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 1 | UP | 7/0,1,2,3,4,5,6,7,8,9,10,11,8/0 | Ready | Completed | 4818.75 | Completed | Completed | Completed | Completed | ANARUL ISLAM | [6 empty] | 4364881.575
|  | AP6/0 | AP7/0 | 1234.28 |  | TSE | 2026-07-15: 2025-05-14; 2026-07-22: 2025-05-17; 2026-07-23: 2025-05-19; 2026-07-26: 2025-05-21 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 2 | UP | 6/0,1,2,7/0 | Ready | Completed | 1234.28 | Completed | Completed | Completed | Completed | ANARUL ISLAM | [6 empty] | 1118025.6354
|  | AP35/0 | AP36/0 | 3957.05 |  | TSE | 2026-07-15: 2025-05-18; 2026-07-22: 2025-05-25; 2026-07-23: 2025-06-27; 2026-07-26: 2025-06-30 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 3 | UP | 35/0,1,2,3,4,5,6,7,8,9,36/0 | Ready | Completed | 3957.05 | Completed | Completed | Completed | Completed | S K INFRA | [6 empty] | 3584343.3746
|  | AP8/0 | AP8A/0 | 2016.72 |  | TSE | 2026-07-15: 2025-05-24; 2026-07-22: 2025-05-29; 2026-07-23: 2025-05-30; 2026-07-26: 2025-05-31 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 4 | UP | 8/0,1,2,3,4,8A/0 | Ready | Completed | 2016.72 | Completed | Completed | Completed | Completed | ANARUL ISLAM | [6 empty] | 1826769.1766
|  | AP31/0 | AP32/0 | 4283.67 |  | TSE | 2026-07-15: 2025-06-02; 2026-07-22: 2025-06-09; 2026-07-23: 2025-06-22; 2026-07-26: 2025-06-26 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 5 | UP | 31/0,1,2,3,4,5,6,7,8,9,10,32/0 | Ready | Completed | 4283.67 | Completed | Completed | Completed | Completed | S K INFRA | [6 empty] | 3880199.69
|  | AP8A/0 | AP8B/0 | 223.61 |  | Manual | 2026-07-15: 2025-06-17; 2026-07-22: 2025-06-19; 2026-07-23: 2025-07-22; 2026-07-26: 2025-07-24 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 6 | UP | 8A,8B | Ready | Completed | 223.61 | Completed | Completed | Completed | Completed | ANARUL ISLAM | [6 empty] | 202548.6213
|  | AP32/0 | AP33/0 | 407.17 |  | Manual | 2026-07-15: 2025-06-18; 2026-07-22: 2025-06-19; 2026-07-23: 2025-07-25; 2026-07-26: 2025-07-29 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 7 | UP | 32/0,33/0 | Ready | Completed | 407.17 | Completed | Completed | Completed | Completed | S K INFRA | [6 empty] | 368819.472
|  | AP8B/0 | AP9/0 | 2226.22 |  | TSE | 2026-07-15: 2025-07-15; 2026-07-22: 2025-07-21; 2026-07-23: 2025-07-26; 2026-07-26: 2025-07-28 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 8 | UP | 8B/0,1,2,3,4,5,9/0 | Ready | Completed | 2226.22 | Completed | Completed | Completed | Completed | ANARUL ISLAM | [6 empty] | 2016536.7906
|  | AP33/0 | AP34/0 | 4781.5 |  | TSE | 2026-07-15: 2025-07-17; 2026-07-22: 2025-07-21; 2026-07-23: 2025-07-25; 2026-07-26: 2025-07-29 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 9 | UP | 33/0,1,2,3,4,5,6,7,8,9,10,11,34/0 | Ready | Completed | 4781.5 | Completed | Completed | Completed | Completed | S K INFRA | [6 empty] | 4331140.078
|  | AP5/0 | AP6/0 | 723.57 |  | TSE | 2026-07-15: 2025-08-05; 2026-07-22: 2025-08-08; 2026-07-23: 2025-08-26; 2026-07-26: 2025-08-27 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 10 | UP | 5/0,1,6/0 | Ready | Completed | 723.57 | Completed | Completed | Completed | Completed | ANARUL ISLAM | [6 empty] | 655418.3888
|  | AP9/0 | AP10/0 | 283.43 |  | Manual | 2026-07-15: 2025-08-11; 2026-07-22: 2025-08-11; 2026-07-23: 2025-08-11; 2026-07-26: 2025-08-12 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 11 | UP | 9/0,10/0 | Ready | Completed | 283.43 | Completed | Completed | Completed | Completed | ANARUL ISLAM | [6 empty] | 256734.2952
|  | AP34/0 | AP35/0 | 3193.23 |  | TSE | 2026-07-15: 2025-08-11; 2026-07-22: 2025-08-20; 2026-07-23: 2025-08-21; 2026-07-26: 2025-08-24 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 12 | UP | 34/0,1,2,3,4,5,6,7,35/0 | Ready | Completed | 3193.23 | Completed | Completed | Completed | Completed | S K INFRA | [6 empty] | 2892466.0528
|  | AP4/0 | AP5/0 | 4415.745 |  | TSE | 2026-07-15: 2025-08-22; 2026-07-22: 2025-08-25; 2026-07-23: 2025-08-27; 2026-07-26: 2025-08-31 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 13 | UP | 4/0,1,2,3,4,5,6,7,8,9,10,5/0 | Ready | Completed | 4415.745 | Completed | Completed | Completed | Completed | ANARUL ISLAM | [6 empty] | 3999834.8099
|  | AP14/0 | AP15/0 | 3611 |  | TSE | 2026-07-15: 2025-09-05; 2026-07-22: 2025-09-10; 2026-07-23: 2025-09-28; 2026-07-26: 2025-09-30 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 14 | UP | 14/0,1,2,3,4,5,6,7,8,15/0 | Ready | Completed | 3611 | Completed | Completed | Completed | Completed | ANARUL ISLAM | [6 empty] | 3270887.132
|  | AP36/0 | AP37/0 | 4947.31 |  | TSE | 2026-07-15: 2025-09-05; 2026-07-22: 2025-09-11; 2026-07-23: 2025-12-06; 2026-07-26: 2025-12-17 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 15 | UP | 36/0,1,2,3,4,5,6,7,8,9,10,11,12,37/0 | Ready | Completed | 4947.31 | Completed |  |  | Completed | S K INFRA | [6 empty] | 4481332.7657
|  | AP3/0 | AP4/0 | 280 |  | Manual | 2026-07-15: 2025-09-15; 2026-07-22: 2025-09-15; 2026-07-23: 2025-09-16; 2026-07-26: 2025-09-16 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 16 | UP | 3/0,4/0 | Ready | Completed | 280 | Completed | Completed | Completed | Completed | ANARUL ISLAM | [6 empty] | 253627.36
|  | AP30/0 | AP31/0 | 2750.46 |  | TSE | 2026-07-15: 2025-09-21; 2026-07-22: 2025-09-28; 2026-07-23: 2025-09-30; 2026-07-26: 2025-10-03 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 17 | UP | 30/0,1,2,3,4,5,6,31/0 | Ready | Completed | 2750.46 | Completed | Completed | Completed | Completed | S K INFRA | [6 empty] | 2491399.6735
|  | AP20/0 | AP21/0 | 4957.98 |  | TSE | 2026-07-15: 2025-09-21; 2026-07-22: 2025-09-30; 2026-07-23: 2025-10-01; 2026-07-26: 2025-10-06 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 18 | UP | 20/0,1,2,3,4,5,6,7,8,9,10,11,12,21/0 | Ready | Completed | 4957.98 | Completed | Completed | Completed | Completed | J PG CON | [6 empty] | 4490997.7798
|  | AP12/0 | AP13/0 | 3919.97 |  | TSE | 2026-07-15: 2025-10-12; 2026-07-22: 2025-10-16; 2026-07-23: 2025-10-24; 2026-07-26: 2025-10-26 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 19 | UP | 12/0,1,2,3,4,5,6,7,8,9,13/0 | Ready | Completed | 3919.97 | Completed | Completed | Completed | Completed | ANARUL ISLAM | [6 empty] | 3550755.8656
|  | AP39/0 | AP40/0 | 4460.53 |  | TSE | 2026-07-15: 2025-10-14; 2026-07-22: 2025-10-19; 2026-07-23: 2025-10-23; 2026-07-26: 2025-10-26 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 20 | UP | 39/0,1,2,3,4,5,6,7,8,9,10,40/0 | Ready | Completed | 4460.53 |  |  | Completed | Completed | S K INFRA |  |  |  | Gang shift to Chatri Narela line on PGCIL request |  |  | 4040401.6004
|  | AP21/0 | AP22/0 | 1606 |  | TSE | 2026-07-15: 2025-10-24; 2026-07-22: 2025-10-26; 2026-07-23: 2025-10-27; 2026-07-26: 2025-10-28 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 21 | UP | 21/0,1,2,3,22/0 | Ready | Completed | 1606 | Completed | Completed | Completed | Completed | J PG CON | [6 empty] | 1454734.072
|  | AP13/0 | AP14/0 | 319.13 |  | Manual | 2026-07-15: 2025-11-03; 2026-07-22: 2025-11-03; 2026-07-23: 2025-11-03; 2026-07-26: 2025-11-04 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 22 | UP | 13/0,14/0 | Ready | Completed | 319.13 | Completed | Completed | Completed | Completed | ANARUL ISLAM |  |  |  | INSULATOR HOISTING |  |  | 289071.7836
|  | AP38/0 | AP39/0 | 4822.84 |  | TSE | 2026-07-15: 2025-11-02; 2026-07-22: 2025-11-10; 2026-07-23: 2025-11-25; 2026-07-26: 2025-11-30 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 23 | UP | 38/0,1,2,3,4,5,6,7,8,9,10,11,39/0 | Ready | Completed | 4822.84 | Completed |  | Completed | Completed | S K INFRA |  |  |  | TSE-2
|  | AP19/0 | AP20/0 | 4990.45 |  | TSE | 2026-07-15: 2025-11-06; 2026-07-22: 2025-11-13; 2026-07-23: 2025-11-15; 2026-07-26: 2025-11-19 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 24 | UP | 19/0,1,2,3,4,5,6,7,8,9,10,11,12,20/0 | Ready | Completed | 4990.45 | Completed | Completed | Completed | Completed | J PG CON |  |  |  | TSE-1
|  | AP17/0 | AP18/0 | 3456.56 |  | TSE | 2026-07-15: 2025-11-17; 2026-07-22: 2026-02-28; 2026-07-23: 2026-02-28; 2026-07-26: 2026-02-28 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 25 | UP | 17/0,1,2,3,4,5,6,7,8,18/0 | Ready | Completed | 3456.56 | Completed | Completed | Completed | Completed | ANARUL ISLAM |  |  | Row from 17.11.2025 | TSE-2
|  | AP18/0 | AP19/0 | 323 |  | Manual | 2026-07-15: 2025-11-21; 2026-07-22: 2025-11-24; 2026-07-23: 2025-11-24; 2026-07-26: 2025-11-25 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 26 | UP | 18/0,19/0 | Ready | Completed | 323 | Completed | Completed | Completed | Completed | J PG CON
|  | AP15/0 | AP16/0 | 465 |  | Manual | 2026-07-15: 2025-11-22; 2026-07-22: 2025-11-25; 2026-07-23: 2025-11-26; 2026-07-26: 2025-11-27 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 27 | UP | 15/0,16/0 | Ready | Completed | 465 | Completed | Completed | Completed | Completed | ANARUL ISLAM
|  | AP10/0 | AP11/0 | 822 |  | TSE | 2026-07-15: 2025-12-02; 2026-07-22: 2025-12-04; 2026-07-23: 2025-12-05; 2026-07-26: 2025-12-06 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 28 | UP | 10/0,1,11/0 | Ready | Completed | 822 | Completed | Completed | Completed | Completed | ANARUL ISLAM
|  | AP37/0 | AP38/0 | 476 |  | Manual | 2026-07-15: 2025-12-05; 2026-07-22: 2025-12-10; 2026-07-23: 2025-12-06; 2026-07-26: 2025-12-18 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 29 | UP | 37/0,38/0 | Ready | Completed | 476 |  |  |  | Completed | S K INFRA
|  | AP11/0 | AP12/0 | 313 |  | Manual | 2026-07-15: 2025-12-08; 2026-07-22: 2025-12-10; 2026-07-23: 2025-12-11; 2026-07-26: 2025-12-12 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 30 | UP | 11/0,12/0 | Ready | Completed | 313 | Completed | Completed | Completed | Completed | ANARUL ISLAM
|  | AP1/0 | AP2/0 | 246 |  | Manual | 2026-07-15: 2025-12-17; 2026-07-22: 2025-12-19; 2026-07-23: 2025-12-21; 2026-07-26: 2025-12-22 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 31 | UP | 1/0,2/0 | Ready | Completed | 246 | Completed | Completed | Completed | Completed | AE Solution
|  | AP0/0 | AP1/0 | 1922 |  | TSE | 2026-07-15: 2025-12-21; 2026-07-22: 2025-12-30; 2026-07-23: 2025-12-31; 2026-07-26: 2025-12-31 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 32 | UP | 0/0,1,2,3,4,2/0 | Ready | Completed | 1922 |  | Completed | Completed | Completed | ANARUL ISLAM
|  | AP24/0 | AP25/0 | 231.53 |  | Manual | 2026-07-15: 2025-12-24; 2026-07-22: 2025-12-30; 2026-07-23: 2025-12-29; 2026-07-26: 2025-12-30 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 33 | UP | 24/0,25/0 | Ready | Completed | 231.53 | Completed | Completed | Completed | Completed | AE Solution
|  | AP23/0 | AP24/0 | 2227.27 |  | TSE | 2026-07-15: 2025-12-26; 2026-07-22: 2026-01-15; 2026-07-23: 2026-01-16; 2026-07-26: 2026-01-22 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 34 | UP | 23/0,1,2,3,4,5,24/0 | Ready | Completed | 2227.27 | Completed | Completed | Completed | Completed | Jahangir(Company)
|  | AP40/0 | AP41/0 | 239.3 |  | Manual | 2026-07-15: 2025-12-24; 2026-07-22: 2026-01-16; 2026-07-23: 2026-01-16; 2026-07-26: 2026-01-18 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 35 | UP | 40/0,41/0 | Ready | Completed | 239.3 |  | Completed | Completed | Completed | Babloo Haque/Anarul-2
|  | AP16/0 | AP17/0 | 264.98 |  | Manual | 2026-07-15: 2025-12-31; 2026-07-22: 2026-01-10; 2026-07-23: 2026-01-11; 2026-07-26: 2026-01-23 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 36 | UP | 16/0,17/0 | Ready | Completed | 264.98 | Completed | Completed | Completed | Completed | Ramawat-Hot line
|  | AP2/0 | AP3/0 | 3683.7 |  | TSE | 2026-07-15: 2026-01-13; 2026-07-22: 2026-01-22; 2026-07-23: 2026-01-23; 2026-07-26: 2026-01-29 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 37 | UP | 2/0,1,2,3,4,5,6,7,8,2/0 | Ready | Completed | 3683.7 | Completed | Completed | Completed | Completed | ANARUL ISLAM
|  | AP26/0 | AP27/0 | 440.84 |  | Manual | 2026-07-15: 2026-01-09; 2026-07-22: 2026-01-15; 2026-07-23: 2026-01-16; 2026-07-26: 2026-01-22 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 38 | UP | 26/0,27/0 | Ready | Completed | 440.84 | Completed | Completed | Completed | Completed | AE Solution(Company)
|  | AP25/0 | AP26/0 | 1666.43 |  | TSE | 2026-07-15: 2026-01-23; 2026-07-22: 2026-01-31; 2026-07-23: 2026-01-27; 2026-07-26: 2026-01-31 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 39 | UP | 25/0,1,2,3,26/0 | Ready | Completed | 1666.43 | Completed | Completed | Completed | Completed | Bhola prasad(Company)+Sing Bahini
|  | AP42/0 | AP43/0 | 309.23 |  | Manual | 2026-07-15: 2026-01-25; 2026-07-22: 2026-01-27; 2026-07-23: 2026-01-27; 2026-07-26: 2026-01-29 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 40 | UP | 42/0,43/0 | Ready | Completed | 309.23 |  | Completed | Completed | Completed | Babloo Haque/Anarul-2
|  | AP29/0 | AP30/0 | 270.08 |  | Manual | 2026-07-15: 2026-03-16; 2026-07-22: 2026-03-16; 2026-07-23: 2026-03-16; 2026-07-26: 2026-03-17 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 41 | UP | 29/0,30/0 | Ready | Completed | 270.08 | Completed | Completed | Completed | Completed | ANARUL ISLAM |  |  | Shutdown postponed
|  | AP41/0 | AP42/0 | 1141.56 |  | TSE | 2026-07-15: 2026-02-03; 2026-07-22: 2026-02-06; 2026-07-23: 2026-02-08; 2026-07-26: 2026-02-11 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 42 | UP | 41/0,1,2,42/0 | Ready | Completed | 1141.56 | Completed | Completed | Completed | Completed | Babloo Haque/Anarul-2
|  | AP28/0 | AP29/0 | 687.67 |  | TSE | 2026-07-15: 2026-02-05; 2026-07-22: 2026-02-06; 2026-07-23: 2026-02-17; 2026-07-26: 2026-02-20 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 43 | UP | 28/0,1,29/0 | Ready | Completed | 687.67 | Completed | Completed | Completed | Completed | Jahangir(Company)
|  | AP22/0 | AP22A/0 | 190.95 |  | Manual | 2026-07-15: 2026-02-17; 2026-07-22: 2026-02-18; 2026-07-23: 2026-02-18; 2026-07-26: 2026-02-18 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 44 | UP | 22/0,22/0 | Ready | Completed | 190.95 | Completed | Completed | Completed | Completed | ANARUL ISLAM
|  | AP27/0 | AP28/0 | 299.47 |  | Manual | 2026-07-15: 2026-02-11; 2026-07-22: 2026-02-12; 2026-07-23: 2026-02-12; 2026-07-26: 2026-02-12 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 45 | UP | 27/0,28/0 | Ready | Completed | 299.47 | Completed | Completed | Completed | Completed | Bhola+Sing bahini(Company)
|  | AP52/1 | AP53/0 | 3814.44 |  | TSE | 2026-07-15: 2026-03-24; 2026-07-22: 2026-03-31; 2026-07-23: 2026-03-28; 2026-07-26: 2026-03-31 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 46 | UP | 52/1,2,3,4,5,6,7,8,9,10,53/0 | Ready | Completed | 3814.44 | Completed | Completed | Completed | Completed | Astharul (company) |  |  | Forest tree cutting
|  | AP46/0 | AP47/0 | 1155.61 |  | TSE | 2026-07-15: 2026-02-14; 2026-07-22: 2026-02-16; 2026-07-23: 2026-02-28; 2026-07-26: 2026-02-28 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 47 | UP | 46/0,1,2,47/0 | Ready | Completed | 1155.61 | Completed | Completed | Completed | Completed | Babloo Haque/Anarul-2
|  | AP22A/0 | AP23/0 | 267.42 |  | Manual | 2026-07-15: 2026-02-21; 2026-07-22: 2026-02-22; 2026-07-23: 2026-02-22; 2026-07-26: 2026-02-22 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 48 | UP | 22A/0,23/0 | Ready | Completed | 267.42 | Completed | Completed | Completed | Completed | ANARUL ISLAM
|  | AP53/0 | AP53A/0 | 831.78 |  | TSE | 2026-07-15: 2026-02-25; 2026-07-22: 2026-02-28; 2026-07-23: 2026-02-28; 2026-07-26: 2026-02-28 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 49 | UP | 53/0,1,53A/0 | Ready | Completed | 831.78 | Completed | Completed | Completed | Completed | SADIK Con(company)
|  | AP45/0 | AP46/0 | 1457.88 |  | TSE | 2026-07-15: 2026-02-22; 2026-07-22: 2026-02-25; 2026-07-23: 2026-02-26; 2026-07-26: 2026-02-28 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 50 | UP | 45/0,1,2,3,46/0 | Ready | Completed | 1457.88 |  | Completed | Completed | Completed | Babloo Haque/Anarul-2
|  | AP53A/0 | AP54/0 | 3166 |  | TSE | 2026-07-15: 2026-03-10; 2026-07-22: 2026-03-20; 2026-07-23: 2026-03-24; 2026-07-26: 2026-03-26 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 51 | UP | 53A/0,1,2,3,4,5,6,7,54/0 | Ready | Completed | 3166 |  | Completed | Completed | Completed | Jahangir(Company)
|  | AP52/0 | AP52/1 | 461 |  | Manual | 2026-07-15: 2026-03-10; 2026-07-22: 2026-03-13; 2026-07-23: 2026-03-14; 2026-07-26: 2026-03-16 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 52 | UP | 52/0,52/1 | Ready | Completed | 461 | Completed | Completed | Completed | Completed | Astharul (company)
|  | AP44/0 | AP45/0 | 300 |  | Manual | 2026-07-15: 2026-03-12; 2026-07-22: 2026-03-15; 2026-07-23: 2026-03-16; 2026-07-26: 2026-03-19 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 53 | UP | 44/0,45/0 | Ready | Completed | 300 | Completed | Completed | Completed | Completed | Dharmendra Hot line
|  | AP69A/0 | AP70/0 | 202.46 |  | Manual | 2026-07-15: 2026-03-12; 2026-07-22: 2026-03-15; 2026-07-23: 2026-03-16; 2026-07-26: 2026-03-31 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 54 | UP | 69A/0,70/0 | Ready | Completed | 202.46 | Completed | Completed | Completed | Completed | SADIK Con(company)
|  | AP70/0 | Gantry | 127 |  | Manual | 2026-07-15: 2026-03-12; 2026-07-22: 2026-03-15; 2026-07-23: 2026-03-16; 2026-07-26: 2026-03-17 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 55 | UP | 70/0,Gantry/0 | Ready | Completed | 127 |  | Completed | Completed | Completed | SADIK Con(company)
|  | AP43/0 | AP44/0 | 459.67 |  | Manual | 2026-07-15: 2026-03-12; 2026-07-22: 2026-03-15; 2026-07-23: 2026-03-16; 2026-07-26: 2026-03-19 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 56 | UP | 43/0,44/0 | Ready | Completed | 459.67 |  | Completed | Completed | Completed | Anarul-2
|  | AP66/0 | AP67/0 | 812.36 |  | TSE | 2026-07-15: 2026-03-19; 2026-07-22: 2026-03-28; 2026-07-23: 2026-03-29; 2026-07-26: 2026-03-31 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 57 | UP | 66/0,1,67/0 | Ready | Completed | 812.36 | Completed | Completed | Completed | Completed | Astharul (company)
|  | AP69/0 | AP69A | 232.6 |  | Manual | 2026-07-15: 2026-03-19; 2026-07-22: 2026-03-24; 2026-07-23: 2026-03-29; 2026-07-26: 2026-03-31 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 58 | UP | 69/0,69A/0 | Ready | Completed | 232.6 | Completed | Completed | Completed | Completed | SADIK Con(company)
|  | AP65/0 | AP66 | 298.04 |  | Manual | 2026-07-15: 2026-03-25; 2026-07-22: 2026-03-28; 2026-07-23: 2026-03-29; 2026-07-26: 2026-03-31 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 59 | UP | 65/0,66/0 | Ready | Completed | 298.04 |  | Completed | Completed | Completed | Dharmendra Hot line
|  | AP68/0 | AP69/0 | 303.77 |  | Manual | 2026-07-15: 2026-03-25; 2026-07-22: 2026-03-26; 2026-07-23: 2026-03-26; 2026-07-26: 2026-03-27 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 60 | UP | 68/0,69/0 | Ready | Completed | 303.77 | Completed | Completed | Completed | Completed | SADIK Con(company)
|  | AP67/0 | AP68/0 | 318.41 |  | Manual | 2026-07-15: 2026-03-28; 2026-07-22: 2026-03-29; 2026-07-23: 2026-03-30; 2026-07-26: 2026-03-31 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 61 | UP | 67/0,68/0 | Ready | Completed | 318.41 | Completed | Completed | Completed | Completed | Anarul-2
|  | AP62/0 | AP63/0 | 349.19 |  | Manual | 2026-07-15: 2026-04-14; 2026-07-22: 2026-04-15; 2026-07-23: 2026-04-15; 2026-07-26: 2026-04-16 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 62 | UP | 62/0,63/0 | Ready | Completed | 349.19 |  | Completed | Completed | Completed | Khosibur Ali(Company)
|  | AP54/0 | AP55/0 | 1186.16 |  | TSE | 2026-07-15: 2026-04-02; 2026-07-22: 2026-04-06; 2026-07-23: 2026-04-08; 2026-07-26: 2026-04-10 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 63 | UP | 54/0,1,2,55/0 | Ready | Completed | 1186.16 | Completed | Completed | Completed | Completed | Jahangir(Company)
|  | AP61/0 | AP62/0 | 478.07 |  | Manual | 2026-07-15: 2026-04-15; 2026-07-22: 2026-04-20; 2026-07-23: 2026-06-11; 2026-07-26: 2026-06-16 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 64 | UP | 61/0,62/0 | Ready | Completed | 478.07 |  | Completed | Completed | Completed | (Kunal Hot line |  |  |  | Final sag completed
|  | AP64/0 | AP65/0 | 1551.15 |  | TSE | 2026-07-15: 2026-04-10; 2026-07-22: 2026-04-17; 2026-07-23: 2026-06-07; 2026-07-26: 2026-06-09 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 65 | UP | 64/0,65/0 | Ready | Completed | 1551.15 | Completed | Completed | Completed | Completed | Astharul (company) |  |  |  | Final sag completed
|  | AP55/0 | AP56/0 | 607.21 |  | TSE | 2026-07-15: 2026-04-12; 2026-07-22: 2026-04-14; 2026-07-23: 2026-05-16; 2026-07-26: 2026-05-17 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 66 | UP | 55/0,1,56/0 | Ready | Completed | 607.21 | Completed |  | Completed | Completed | Jahangir(Company)FS-Anarul
|  | AP47/0 | AP48/0 | 358.63 |  | Manual | 2026-07-15: 2026-05-20; 2026-07-22: 2026-05-25; 2026-07-23: 2026-05-21; 2026-07-26: 2026-05-27 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 67 | UP | 47/0,48/0 | Ready | Completed | 358.63 |  | Completed | Completed | Completed | Kunal Hot line
|  | AP56/0 | AP57/0 | 3374 |  | TSE | 2026-07-15: 2026-05-10; 2026-07-22: 2026-05-14; 2026-07-23: 2026-05-19; 2026-07-26: 2026-05-22 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 68 | UP | 56/0,1,2,3,4,5,6,7,8,57/0 | Ready | Completed | 3374 | Completed |  | Completed | Completed | ANARUL ISLAM |  |  |  | Final sag completed
|  | AP57/0 | AP58/0 | 677.28 |  | TSE | 2026-07-15: 2026-05-17; 2026-07-22: 2026-05-18; 2026-07-23: 2026-05-26; 2026-07-26: 2026-05-29 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 69 | UP | 57/0,1,58/0 | Ready | Completed | 677.28 | Completed | Completed | Completed | Completed | ANARUL ISLAM |  |  |  | Final sag completed
|  | AP59/0 | AP60/0 | 418 |  | Manual | 2026-07-15: 2026-06-03; 2026-07-22: 2026-06-05; 2026-07-23: 2026-06-11; 2026-07-26: 2026-06-19 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 70 | UP | 59/0, 60/0 | Ready | Completed | 418 |  |  | Completed | Completed | RK Enterprise |  |  |  | Final sag completed
|  | AP63/0 | AP64/0 | 285 |  | Manual | 2026-07-15: 2026-06-01; 2026-07-22: 2026-06-02; 2026-07-23: 2026-06-03; 2026-07-26: 2026-06-04 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 71 | UP | 63/0,64/0 | Ready | Completed | 285 | Completed |  | Completed | Completed | ANARUL ISLAM |  |  |  | Final sag completed
|  | AP58/0 | AP59/0 | 281.56 |  | Manual | 2026-07-15: 2026-06-01; 2026-07-22: 2026-06-03; 2026-07-23: 2026-06-03; 2026-07-26: 2025-06-07 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 72 | UP | 58/0,59/0 | Ready | Completed | 281.56 |  | Completed | Completed | Completed | Dharmendra Hot line |  |  |  | Final sag completed
|  | AP51/0 | AP52/0 | 238.93 |  | Manual | 2026-07-15: 2026-06-01; 2026-07-22: 2026-06-03; 2026-07-23: 2026-06-03; 2026-07-26: 2026-06-06 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 73 | UP | 51/0,52/0 | Ready | Completed | 238.93 | Completed | Completed | Completed | Completed | Kunal Hot line |  |  |  | Final sag completed
|  | AP48/0 | AP49/0 | 775.94 |  | TSE | 2026-07-15: 2026-06-11; 2026-07-22: 2026-06-15; 2026-07-23: 2026-06-18; 2026-07-26: 2026-06-24 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 74 | UP | 48/0-49/0 | Ready | Completed | 775.94 |  |  |  | Completed | ANARUL ISLAM | 40 | 12 |  | Final sag completed
|  | AP49/0 | AP50/0 | 372 |  | Manual | 2026-07-15: 2026-06-12; 2026-07-22: 2026-06-15; 2026-07-23: 2026-06-14; 2026-07-26: 2026-06-25 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 75 | UP | 49/0,50/0 | Ready | Completed | 372 |  |  | Completed | Completed | Dharmendra Hot line | 20 | 12 |  | Final sag completed
|  | AP60/0 | AP61/0 | 468 |  | Manual | 2026-07-15: 2026-06-10; 2026-07-22: 2026-06-13; 2026-07-23: 2026-06-14; 2026-07-26: 2026-06-19 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 76 | UP | 60/0,61/0 | Ready | Completed | 468 |  |  |  | Completed | ANARUL ISLAM | 36 | 18 |  | Final sag completed
|  | AP50/0 | AP51/0 | 678 |  | TSE | 2026-07-15: 2026-06-29; 2026-07-22: 2026-07-10; 2026-07-23: 2026-07-06; 2026-07-26: 2026-07-11 |  |  |  |  | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | FALSE |  |  |  | 77 | UP | 50/0,51/0 | Ready | Completed | 678 |  |  |  | Completed | SADIK Con(company) | 16 | 6 |  | Pilot paying
[6 empty] | tse | [11 empty] | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
|  |  | Total | 115.2147 |  | tse | [11 empty] | TA 416 |  | TA 416 | TA 416 | ta416 | TA 416 | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [6 empty] | 115.2147 |  |  |  | 0
|  | AP32 | AP33 | 249.635 |  | HotLine | 2026-07-15: 2026-02-16; 2026-07-22: 2026-02-22; 2026-07-23: 2026-02-16; 2026-07-26: 2026-02-22 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 1 | KA | 32/0, 33/0 | Ready | 2026-02-14 |  | 2026-02-24 | 2026-02-23 | 2026-02-23 | Completed | Ramawat | [7 empty] | Completed
|  | AP33 | 33/5 | 2015 |  | TSE | 2026-07-15: 2026-02-05; 2026-07-22: 2026-02-09; 2026-07-23: 2026-02-07; 2026-07-26: 2026-02-09 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 2 | KA | 33/0, 33/1, 33/2, 33/3, 33/4, 33/5 | Ready | 2025-12-20 |  | 2026-02-12 | 2026-02-13 | 2026-02-11 | Completed | SUFIYAN / Haque | 73 | [6 empty] | Completed
|  | 33/5 | 33/6 | 380 |  | HotLine | 2026-07-15: 2026-01-19; 2026-07-22: 2026-01-30; 2026-07-23: 2026-01-26; 2026-07-26: 2026-01-30 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 3 | KA | 33/5, 33/6 | Ready | 2025-12-21 |  | 2026-01-31 | 2026-01-31 | 2026-01-30 | Completed | Ramawat | 20 | [6 empty] | Completed
|  | 33/6 | 34/0 | 2537.42 |  | TSE | 2026-07-15: 2026-01-18; 2026-07-22: 2026-01-27; 2026-07-23: 2026-01-26; 2026-07-26: 2026-01-28 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 4 | KA | 33/6, 33/7, 33/8, 33/9, 33/10, 33/11, 33/12, 34/0 | Ready | 2025-12-21 |  | 2026-02-01 | 2026-02-02 | 2026-02-01 | Completed | SUFIYAN / Haque | 58 | [6 empty] | Completed
|  | 34/0 | AP35 | 1983.46 |  | TSE | 2026-07-15: 2025-11-26; 2026-07-22: 2025-11-30; 2026-07-23: 2025-12-05; 2026-07-26: 2025-12-09 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 5 | KA | 34/0, 34/1, 34/2, 34/3, 34/4, 35/0 | Ready | 2025-10-29 |  | 2025-12-11 | 2025-12-13 | 2025-12-12 | Completed | SUFIYAN | 60 | [6 empty] | Completed
|  | AP35 | AP36 | 4480.02 |  | TSE | 2026-07-15: 2025-11-07; 2026-07-22: 2025-11-17; 2026-07-23: 2025-12-05; 2026-07-26: 2025-12-09 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 6 | KA | 35/0, 35/1, 35/2,35/3,35/4, 35/5, 35/6,35/7,35/8, 35/9, 35/10,35/11,36/0 | Ready | 2025-10-24 |  | 2025-12-13 | 2025-12-19 | 2025-12-18 | Completed | SUFIYAN | 55 | [6 empty] | Completed
|  | AP36 | 36/1 | 480 |  | Manual | 2026-07-15: 2025-11-01; 2026-07-22: 2025-11-03; 2026-07-23: 2025-11-10; 2026-07-26: 2025-11-17 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 7 | KA | 36/0, 36/1 | Ready | 2025-10-24 |  | 2025-11-18 | 2025-11-20 | 2025-11-19 | Completed | SUFIYAN | 65 | [6 empty] | Completed
|  | 36/1 | 37/0 | 297.32 |  | Manual | 2026-07-15: 2026-05-23; 2026-07-22: 2026-05-29; 2026-07-23: 2026-05-29; 2026-07-26: 2026-05-29 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 8 | KA | 36/1, 37/0 | Ready | 2026-05-23 |  | 2026-06-16 | 2026-05-29 | 2026-05-29 | wip | Dharmendar | 30 | [6 empty] | Completed
|  | 37/0 | AP38 | 1258.78 |  | TSE | 2026-07-15: 2026-05-10; 2026-07-22: 2026-05-12; 2026-07-23: 2026-05-22; 2026-07-26: 2026-05-26 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 9 | KA | 37/0, 37/1, 37/2, 38/0 | Ready | 2026-05-05 |  | 2026-06-14 | 2026-06-11 | 2026-06-05 | Completed | SUFIYAN | 43 | [6 empty] | Completed
|  | AP38 | AP39 | 1300.76 |  | TSE | 2026-07-15: 2026-05-20; 2026-07-22: 2026-05-26; 2026-07-23: 2026-05-30; 2026-07-26: 2026-06-03 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 10 | KA | 38/0, 38/1, 38/2, 39/0 | Ready | 2026-05-14 |  | 2026-06-09 | 2026-06-08 | 2026-06-04 | wip | SUFIYAN | 43 | [6 empty] | Completed
|  | AP39 | AP40 | 230.87 |  | HotLine | 2026-07-15: 2026-02-07; 2026-07-22: 2026-02-10; 2026-07-23: 2026-02-09; 2026-07-26: 2026-02-11 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 11 | KA | 39/0,40/0 | Ready | 2026-02-02 |  | 2026-02-12 | 2026-02-13 | 2026-02-12 | Completed | Ramawat | 22 | [6 empty] | Completed
|  | AP40 | AP41 | 2426.45 |  | TSE | 2026-07-15: 2025-12-20; 2026-07-22: 2025-12-26; 2026-07-23: 2025-12-30; 2026-07-26: 2026-01-02 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 12 | KA | 40/0,40/1,40/2,40/3,40/4,40/5,41/0 | Ready | 2025-10-10 |  | 2026-01-03 | 2026-01-05 | 2026-01-04 | Completed | SUFIYAN / Haque | 65 | [6 empty] | Completed
|  | AP41 | AP42 | 2473.21 |  | TSE | 2026-07-15: 2025-10-03; 2026-07-22: 2025-10-06; 2026-07-23: 2025-12-22; 2026-07-26: 2025-12-26 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 13 | KA | 41/0,41/1,41/2,41/3,41/4,41/5,42/0 | Ready | 2025-09-30 |  | 2025-12-28 | 2026-01-02 | 2026-01-01 | Completed | SUFIYAN / Haque | 55 | [6 empty] | Completed
|  | AP42 | AP43 | 1105.78 |  | TSE | 2026-07-15: 2025-09-25; 2026-07-22: 2025-09-28; 2026-07-23: 2025-10-13; 2026-07-26: 2025-10-15 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 14 | KA | 42/0,42/1,42/2,43/0 | Ready | 2025-09-20 |  | 2025-10-17 | 2025-10-19 | 2025-10-18 | Completed | SUFIYAN | 55 | [6 empty] | Completed
|  | AP43 | AP44 | 1444.8 |  | TSE | 2026-07-15: 2026-03-07; 2026-07-22: 2026-03-11; 2026-07-23: 2026-03-09; 2026-07-26: 2026-03-12 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 15 | KA | 43/0,43/1,43/2,43/3,44/0 | Ready | 2026-02-16 |  | 2026-03-27 | 2026-03-15 | 2026-03-14 | Completed | SUFIYAN | 31 | [6 empty] | Completed
|  | AP44 | AP45 | 697.56 |  | TSE | 2026-07-15: 2026-03-07; 2026-07-22: 2026-03-18; 2026-07-23: 2026-03-14; 2026-07-26: 2026-03-18 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 16 | KA | 44/0,44/1,45/0 | Ready | 2026-02-14 |  | 2026-03-27 | 2026-03-30 | 2026-03-28 | Completed | Haque | 35 | [6 empty] | Completed
|  | AP45 | 45/1 | 242 |  | Manual | 2026-07-15: 2026-03-06; 2026-07-22: 2026-03-12; 2026-07-23: 2026-03-06; 2026-07-26: 2026-03-12 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 17 | KA | 45/0, 45/1 | Ready | 2026-02-15 |  | 2026-03-14 | 2026-03-14 | 2026-03-13 | Completed | Ramawat | 22 | [6 empty] | Completed
|  | 45/1 | AP46 | 1272.52 |  | TSE | 2026-07-15: 2026-02-28; 2026-07-22: 2026-03-03; 2026-07-23: 2026-03-22; 2026-07-26: 2026-03-25 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 18 | KA | 45/0,45/1,45/2,46/0 | Ready | 2026-02-16 |  | 2026-03-26 | 2026-03-31 | 2026-03-29 | Completed | Haque | 33 | [6 empty] | Completed
|  | AP46 | 46/7 | 2745 |  | TSE | 2026-07-15: 2026-07-17; 2026-07-22: 2026-07-21 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 19 | KA | 46/0,46/1,46/2,46/3,46/4,46/5,46/6,46/7 | Pending | 2026-07-13 | [13 empty] | Pending @ 46/2
|  | 46/7 | AP47/0 | 3547.25 |  | TSE | [11 empty] | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 20 | KA | 46/7,46/8,46/9,46/10,46/11,46/12,46/13,46/14,46/15,47/0 | Pending | 2026-07-16 | [13 empty] | Pending @ 46/9
|  | AP47/0 | AP48 | 813.45 |  | TSE | 2026-07-15: 2026-07-09; 2026-07-22: 2026-07-12 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 21 | KA | 47/0,47/1,48/0 | Ready | 2026-07-03 | [13 empty] | Completed
|  | AP48 | 48A/0 | 1257.06 |  | TSE | 2026-07-15: 2026-03-02; 2026-07-22: 2026-07-05; 2026-07-23: 2026-07-15; 2026-07-26: 2026-07-17 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 22 | KA | 48/0,48/1,48/2,48A/0 | Ready | 2026-06-27 |  |  | 2026-07-17 | 2026-07-17 | [9 empty] | Completed
|  | 48A/0 | 49/0 | 1101.05 |  | TSE | 2026-07-15: 2026-06-23; 2026-07-22: 2026-06-26; 2026-07-23: 2026-07-09; 2026-07-26: 2026-07-15 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 23 | KA | 48A/0,48A/1,48A/2,49/0 | Ready | 2026-06-20 |  |  | 2026-07-16 | 2026-07-16 | [9 empty] | Completed
|  | 49/0 | AP50 | 417.22 |  | Manual | 2026-07-15: 2026-07-09; 2026-07-22: 2026-07-12; 2026-07-23: 2026-07-09; 2026-07-26: 2026-07-15 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 24 | KA | 49/0,50/0 | Ready | 2026-07-09 |  | 2026-07-20 | 2026-07-17 | 2026-07-17 | [9 empty] | Completed
|  | AP50 | AP51 | 249.6 |  | Manual | 2026-07-15: 2026-07-09; 2026-07-22: 2026-07-12; 2026-07-23: 2026-07-09; 2026-07-26: 2026-07-12 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 25 | KA | 50/0,51/0 | Ready | 2026-07-06 |  | 2026-07-20 | 2026-07-15 | 2026-07-14 | Completed | [8 empty] | Completed
|  | AP51 | AP52 | 333.6 |  | Manual | 2026-07-15: 2026-06-02; 2026-07-22: 2026-06-06; 2026-07-23: 2026-07-09; 2026-07-26: 2026-07-12 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 26 | KA | 51/0,52/0 | Ready | 2026-06-02 |  |  |  |  | Completed | M/s Akram | 30 | [6 empty] | Completed
|  | AP52 | AP53 | 1034.1 |  | TSE | 2026-07-15: 2026-06-03; 2026-07-22: 2026-06-05; 2026-07-23: 2026-06-15; 2026-07-26: 2026-06-20 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 27 | KA | 52/0,52/1,52/2,53/0 | Ready | 2026-05-18 |  |  | 2026-06-25 | 2026-06-22 | Completed | M/s Ranveer | 18 | [6 empty] | Completed
|  | AP53 | AP54 | 258.62 |  | Manual | 2026-07-15: 2026-06-12; 2026-07-22: 2026-06-20; 2026-07-23: 2026-06-15; 2026-07-26: 2026-06-20 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 28 | KA | 53/0,54/0 | Ready | 2026-06-12 |  |  | 2026-06-28 | 2026-06-23 | Completed | [8 empty] | Completed
|  | AP54 | AP55 | 1836.69 |  | TSE | 2026-07-15: 2026-06-14; 2026-07-22: 2026-06-19; 2026-07-23: 2026-06-24; 2026-07-26: 2026-06-26 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 29 | KA | 54/0,54/1,54/2,54/3,54/4,55/0 | Ready | 2026-06-08 |  | 2026-06-29 | 2026-06-30 | 2026-06-28 | Completed | M/s Akram | 30 | [6 empty] | Completed
|  | AP55 | AP56 | 2704.49 |  | TSE | 2026-07-15: 2026-04-28; 2026-07-22: 2026-05-03; 2026-07-23: 2026-05-02; 2026-07-26: 2026-05-04 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 30 | KA | 55/0,55/1,55/2,55/3,55/4,55/5,55/6,56/0 | Ready | 2026-04-01 |  | 2026-06-28 | 2026-05-09 | 2026-05-07 | Completed | SUFIYAN | 31 | [6 empty] | Completed
|  | AP56 | 56/3 | 1230 |  | TSE | 2026-07-15: 2026-03-26; 2026-07-22: 2026-03-31; 2026-07-23: 2026-06-05; 2026-07-26: 2026-06-09 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 31 | KA | 56/0,56/1,56/2,56/3 | Ready | 2026-03-17 |  | 2026-06-26 | 2026-06-23 | 2026-06-21 | Completed | SUFIYAN | 31 | [6 empty] | Completed
|  | 56/3 | 57/0 | 276.49 |  | Manual | 2026-07-15: 2026-06-04; 2026-07-22: 2026-06-09; 2026-07-23: 2026-06-05; 2026-07-26: 2026-06-09 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 32 | KA | 56/3,57/0 | Pending | 2026-06-03 |  |  | 2026-06-15 | 2026-06-13 | Completed | M/s Dharmander | 24 | [6 empty] | Pending @ 57/0
|  | 57/0 | 58/0 | 1535.81 |  | TSE | 2026-07-15: 2026-06-17; 2026-07-22: 2026-06-23; 2026-07-23: 2026-06-24; 2026-07-26: 2026-06-27 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 33 | KA | 57/0,57/1,57/2,57/3,58/0 | Pending | 2026-06-12 |  |  | 2026-06-30 | 2026-06-28 | Completed | M/s Kamrudhin | 36 | [6 empty] | Pending @ 57/0
|  | 58/0 | 59/0 | 203.9 |  | Manual | 2026-07-15: 2026-06-24; 2026-07-22: 2026-06-28; 2026-07-23: 2026-06-24; 2026-07-26: 2026-06-28 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 34 | KA | 58/0,59/0 | Ready | 2026-06-15 |  | 2026-07-11 | 2026-06-30 | 2026-06-29 | Completed | [8 empty] | Completed
|  | 59/0 | 60/0 | 702.8 |  | TSE | 2026-07-15: 2026-06-24; 2026-07-22: 2026-06-27; 2026-07-23: 2026-07-02; 2026-07-26: 2026-07-04 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 35 | KA | 59/0,59/1,60/0 | Ready | 2026-06-23 |  | 2026-07-11 | 2026-07-05 | 2026-07-04 | Completed | [8 empty] | Completed
|  | 60/0 | 61/0 | 1942 |  | TSE | 2026-07-15: 2026-07-01; 2026-07-22: 2026-07-04; 2026-07-23: 2026-07-02; 2026-07-26: 2026-07-04 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 36 | KA | 60/0,60/1,60/2,60/3,60/4,61/0 | Ready | 2026-06-28 |  | 2026-07-09 | 2026-07-09 | 2026-07-08 | Completed | [8 empty] | Completed
|  | 61/0 | 62/0 | 358.1 |  | Manual | 2026-07-15: 2026-04-08; 2026-07-22: 2026-04-15; 2026-07-23: 2026-06-15; 2026-07-26: 2026-06-23 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 37 | KA | 61/0,62/0 | Ready | 2026-04-06 |  | 2026-07-10 | 2026-07-08 | 2026-07-09 | Completed | M/s Kamrudhin | 34 | [6 empty] | Completed
|  | 62/0 | 63/0 | 278.7 |  | Manual | 2026-07-15: 2026-05-23; 2026-07-22: 2026-05-24; 2026-07-23: 2026-06-15; 2026-07-26: 2026-07-03 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 38 | KA | 62/0,63/0 | Ready | 2026-04-06 |  | 2026-07-10 | 2026-07-04 | 2026-07-03 | Completed | M/s Kamrudhin | 22 | [6 empty] | Completed
|  | 63/0 | GNTY | 135 |  | Manual | 2026-07-15: 2026-04-15; 2026-07-22: 2026-04-18; 2026-07-23: 2026-04-16; 2026-07-26: 2026-04-19 |  |  |  |  | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | FALSE |  |  |  | 39 | KA | 63/0,GNTY | Ready | 2026-04-06 |  | 2026-07-08 | 2026-04-20 | 2026-04-20 | Completed | M/s Kamrudhin | 32 | [6 empty] | Completed
[6 empty] | tse | [11 empty] | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
|  |  | Total | 47.8365 |  | tse | [11 empty] | TA 418 |  | TA 418 | TA 418 | ta418 | TA 418 | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
|  | 0A/0 | 0B/0 | 447.34 |  | Manual | 2026-07-26: 2026-05-22 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 1 | Manual |  | Ready |  |  |  |  | 2026-05-25 | Completed | Saheb Enterprises | [8 empty] | TSE 1
|  | 0B/0 | 0C/0 | 1594.82 |  | TSE | 2026-07-26: 2026-07-26 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 2 | TSE |  | Ready | [5 empty] | Completed | Saheb Enterprises | [8 empty] | TSE 1
|  | 0C/0 | 0D/0 | 793.45 |  | TSE | 2026-07-26: 2026-07-12 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 3 | TSE |  | Ready | [5 empty] | Completed | Saheb Enterprises
|  | 0D/0 | 0D/5 | 2099 |  | TSE | 2026-07-15: 2026-06-12; 2026-07-22: 2026-06-18; 2026-07-23: 2026-06-19; 2026-07-26: 2026-06-24 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 4 | TSE |  | Ready |  |  | 2026-06-25 | 2026-06-25 | 2026-06-26 | Completed | Saheb Enterprises | 50 | [7 empty] | TSE 1
|  | 0D/5 | 0E/0 | 449.69 |  | Manual | 2026-07-26: 2026-06-24 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 5 | Manual |  | Ready |  |  |  |  | 2026-06-27 | Completed | Alimuddin | 28 | [7 empty] | Manual 1
|  | 0E/0 | 0F/0 | 1238.46 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 6 | TSE | [7 empty] | WIP | Saheb Enterprises | [8 empty] | TSE 1
|  | 0F/0 | 0G/0 | 283.43 |  | Manual | 2026-07-26: 2026-07-27 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 7 | Manual |  | Ready | [5 empty] | Completed | Alimuddin
|  | 0G/0 | 0H/0 | 799.95 |  | TSE | 2026-07-26: 2026-07-29 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 8 | TSE |  | Ready | [5 empty] | Completed | Alimuddin | [8 empty] | Manual 1
|  | 0H/0 | 1/0 | 245.33 |  | Manual | 2026-07-26: 2026-08-04 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 9 | Manual | [7 empty] | Completed | Dharmendra | [8 empty] | Hotline
|  | 1/0 | 2/0 | 199.37 |  | Manual | 2026-07-22: 2026-07-28 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 10 | Manual | [7 empty] | WIP | Enamul | [8 empty] | Manual 2
|  | 2/0 | 3/0 | 263.38 |  | Manual | 2026-07-26: 2026-07-30 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 11 | Manual |  | Ready | [5 empty] | Completed | Enamul
|  | 3/0 | 4/0 | 2405.48 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 12 | TSE
|  | 4/0 | 5/0 | 775.24 |  | TSE | 2026-07-26: 2026-07-01 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 13 | TSE |  | Ready | [5 empty] | Completed | Mussoluddin | 87 | [7 empty] | TSE 2
|  | 5/0 | 6/0 | 1991.87 |  | TSE | 2026-07-26: 2026-07-11 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 14 | TSE |  | Ready | [5 empty] | Completed | Mussoluddin | [8 empty] | TSE 2
|  | 6/0 | 7/0 | 4993.95 |  | TSE | 2026-07-15: 2026-07-12 |  |  |  |  | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 15 | TSE |  |  | 2026-07-06 |  |  |  |  | WIP | Mussoluddin | [8 empty] | TSE 2
|  | 7/0 | 8/0 | 840.03 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 16 | TSE
|  | 8/0 | 9/0 | 339.15 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 17 | Manual
|  | 9/0 | 10/0 | 473.56 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 18 | Manual
|  | 10/0 | 11/0 | 264.19 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 19 | Manual
|  | 11/0 | 11/1 | 378.01 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 20 | Manual
|  | 11/1 | 11/2 | 484.94 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 21 | Manual
|  | 11/2 | 12/0 | 1185.91 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 22 | TSE
|  | 12/0 | 12A/0 | 1141.1 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 23 | TSE
|  | 12A/0 | 13/0 | 840.33 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 24 | TSE
|  | 13/0 | 14/0 | 277.65 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 25 | Manual
|  | 14/0 | 15/0 | 700.36 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 26 | TSE
|  | 15/0 | 15A/0 | 282.44 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 27 | Manual
|  | 15A/0 | 16/0 | 247.43 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 28 | Manual
|  | 16/0 | 17/0 | 364.22 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 29 | Manual
|  | 17/0 | 18/0 | 1084.26 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 30 | TSE
|  | 18/0 | 19/0 | 357.44 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 31 | Manual
|  | 19/0 | 20/0 | 2321.07 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 32 | TSE
|  | 20/0 | 20/3 | 1081.63 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 33 | TSE
|  | 20/3 | 21/0 | 358.52 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 34 | Manual
|  | 21/0 | 22/0 | 238.09 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 35 | Manual
|  | 22/0 | 23/0 | 1531.84 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 36 | TSE
|  | 23/0 | 24/0 | 1521.57 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 37 | TSE
|  | 24/0 | 25/0 | 1524.48 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 38 | TSE
|  | 25/0 | 26/0 | 221.32 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 39 | Manual
|  | 26/0 | 27/0 | 2761.28 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 40 | TSE
|  | 27/0 | 28/0 | 1507.39 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 41 | TSE
|  | 28/0 | 29/0 | 739.92 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 42 | TSE
|  | 29/0 | 30/0 | 207.12 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 43 | Manual
|  | 30/0 | 31/0 | 785.64 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 44 | TSE
|  | 31/0 | 32/0 | 1169.33 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 45 | TSE
|  | 32/0 | 33/0 | 269.5 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 46 | Manual
|  | 33/0 | 34/0 | 708.89 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 47 | TSE
|  | 34/0 | 35/0 | 774.54 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 48 | TSE
|  | 35/0 | 36/0 | 246.98 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 49 | Manual
|  | 36/0 | 36/4 | 1617.64 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 50 | TSE
|  | 36/4 | 37/0 | 2789.12 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 51 | TSE
|  | 37/0 | 38/0 | 262.38 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 52 | Manual
|  | 38/0 | 39/0 | 4947 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 53 | TSE
|  | 39/0 | 40/0 | 200.61 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 54 | Manual
|  | 40/0 | 41/0 | 4067.61 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 55 | TSE
|  | 41/0 | 42/0 | 3468.86 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 56 | TSE
|  | 42/0 | 43/0 | 219.42 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 57 | Manual
|  | 43/0 | 44/0 | 2622.21 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 58 | TSE
|  | 44/0 | 45/0 | 446.79 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 59 | Manual
|  | 45/0 | 46/0 | 233.98 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 60 | Manual
|  | 46/0 | 47/0 | 2072.07 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 61 | TSE
|  | 47/0 | 48/0 | 349.44 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 62 | Manual
|  | 48/0 | 49/0 | 808.59 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 63 | TSE
|  | 49/0 | 50/0 | 207.14 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 64 | Manual
|  | 50/0 | 50/1 | 482.87 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 65 | Manual
|  | 50/1 | 51/0 | 370.42 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 66 | Manual
|  | 51/0 | 52/0 | 252.5 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 67 | Manual
|  | 52/0 | 53/0 | 1015.88 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 68 | TSE
|  | 53/0 | 54/0 | 219.62 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 69 | Manual
|  | 54/0 | 55/0 | 3182.59 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 70 | TSE
|  | 55/0 | 56/0 | 2583.14 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 71 | TSE
|  | 56/0 | 57/0 | 221.82 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 72 | Manual
|  | 57/0 | 58/0 | 819.68 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 73 | TSE
|  | 58/0 | 59/0 | 294.64 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 74 | Manual
|  | 59/0 | 60/0 | 620.1 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 75 | TSE
|  | 60/0 | 61/0 | 193.99 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 76 | Manual
|  | 61/0 | 62/0 | 817.16 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 77 | TSE
|  | 62/0 | 63/0 | 2455.63 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 78 | TSE
|  | 63/0 | 63A/0 | 2624.87 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 79 | TSE
|  | 63A/0 | 63B/0 | 350.46 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 80 | Manual
|  | 63B/0 | 64/0 | 2771.42 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 81 | TSE
|  | 64/0 | 64/2 | 769.94 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 82 | TSE
|  | 64/2 | 64A/0 | 1614.14 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 83 | TSE
|  | 64A/0 | 65/0 | 454.37 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 84 | Manual
|  | 65/0 | 66/0 | 1169.06 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 85 | TSE
|  | 66/0 | 67/0 | 775.69 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 86 | TSE
|  | 67/0 | 68/0 | 368.45 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 87 | Manual
|  | 68/0 | 69/0 | 349.57 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 88 | Manual
|  | 69/0 | 70/0 | 420.91 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 89 | Manual
|  | 70/0 | 71/0 | 309.86 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 90 | Manual
|  | 71/0 | 72/0 | 364.16 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 91 | Manual
|  | 72/0 | 73/0 | 208.46 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 92 | Manual
|  | 73/0 | 74/0 | 395.52 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 93 | Manual | [11 empty] | U/C 220 KV
|  | 74/0 | 75/0 | 266.46 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 94 | Manual
|  | 75/0 | 76/0 | 209.25 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 95 | Manual
|  | 76/0 | 77/0 | 1639.09 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 96 | TSE
|  | 77/0 | 78/0 | 394.65 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 97 | Manual
|  | 78/0 | 78A/0 | 2033.85 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 98 | TSE
|  | 78A/0 | 79/0 | 430.8 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 99 | Manual
|  | 79/0 | 80/0 | 240.54 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 100 | Manual
|  | 80/0 | 81/0 | 255.15 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 101 | Manual
|  | 81/0 | 82/0 | 188.84 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 102 | Manual
|  | 82/0 | 83/0 | 397.99 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 103 | Manual
|  | 83/0 | 84/0 | 3875.28 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 104 | TSE
|  | 84/0 | 84A/0 | 2169.66 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 105 | TSE
|  | 84A/0 | 85/0 | 670.06 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 106 | TSE
|  | 85/0 | 85A/0 | 289.67 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 107 | Manual
|  | 85A/0 | 86/0 | 385.12 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 108 | Manual
|  | 86/0 | 86A/0 | 348.96 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 109 | Manual
|  | 86A/0 | 86A/4 | 1032.86 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 110 | TSE
|  | 86A/4 | 87/0 | 1650 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 111 | TSE
|  | 87/0 | 88/0 | 804.23 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 112 | TSE
|  | 88/0 | 89/0 | 1081.94 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 113 | TSE
|  | 89/0 | 90/0 | 1071.87 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 114 | TSE
|  | 90/0 | 90A/0 | 324.41 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 115 | Manual
|  | 90A/0 | 90B/0 | 284.15 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 116 | Manual
|  | 90B/0 | 91/0 | 637.67 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 117 | TSE
|  | 91/0 | 92/0 | 215.08 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 118 | Manual
|  | 92/0 | 93/0 | 381.67 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 119 | Manual
|  | 93/0 | 93A/0 | 255.59 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 120 | Manual
|  | 93A/0 | 93B/0 | 351.25 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 121 | Manual
|  | 93B/0 | 93C/0 | 369.96 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 122 | Manual
|  | 93C/0 | 94/0 | 260 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 123 | Manual
|  | 94/0 | 95/0 | 166.6 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 124 | Manual
|  | 95/0 | 95A/0 | 486.78 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 125 | Manual
|  | 95A/0 | 96/0 | 179 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 126 | Manual
|  | 96/0 | 96/1 | 153.59 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 127 | Manual
|  | 96/1 | 97/0 | 367.88 |  | TSE | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 128 | Manual
|  | 97/0 | 98/0 | 814.93 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 129 | TSE
|  | 98/0 | 99/0 | 292.64 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 130 | Manual
|  | 99/0 | 100/0 | 103.1 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 131 | Manual
|  | 100/0 | 101/0 | 183.67 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 132 | Manual
|  | 101/0 | GANTRY | 115.31 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 133 | Manual
|  | GNT 1 | GNT 2 | 78.28 |  | Manual | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 134 | Manual
|  | 100/0 |  | 0 |  | tse | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  | Manual
|  | GNT 2 |  | 147.68 |  | tse | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  | Manual
|  |  | Total | 122206.18 |  | tse | [11 empty] | TA 419 |  | TA 419 | TA 419 | ta419 | TA 419 | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
1 |  | 23/0 | 24/0 | 1.826 |  | tse | 2026-07-15: 12-02-2025 to 16-02-2025; 2026-07-26: 27-02-2025 to 04-03-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 35 | [7 empty] | 23/0-24/0 |  |  | 17-02-2025 & 04-03-2025
2 |  | 24/0 | 25/0 | 3.406 |  | tse | 2026-07-15: 24-02-2025 to 04-03-2025; 2026-07-26: 09-03-2025 to 16-03-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 35 | [7 empty] | 24/0-25/0 |  |  | 04-03-2025 & 16-03-2025
3 |  | 25/0 | 26/0 | 2.279 |  | tse | 2026-07-15: 08-03-2025 to 13-03-2025; 2026-07-26: 24-03-2025 to 29-03-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 35 | [7 empty] | 25/0-26/0 |  |  | & 29-03-2025
4 |  | 26/0 | 27/0 | 1.914 |  | tse | 2026-07-15: 23-03-2025 to 28-03-2025; 2026-07-26: 18-04-2025 & 20-04-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 35 | [7 empty] | 26/0-27/0 |  |  | 28-03-2025 &
5 |  | 22/0 | 23/0 | 2.338 |  | tse | 2026-07-15: 07-04-2025 to 11-04-2025; 2026-07-26: 22-04-2025 & 24-04-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 35 | [7 empty] | 22/0 - 23/0 |  |  | 11-04-2025 & 25-04-2025
6 |  | 29/0 | 29/9 | 3.555 |  | tse | 2026-07-15: 05-05-2025 to 16-05-2025; 2026-07-26: 06- 07-2025 to 11-07-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 35 | [7 empty] | 29/0 - 29/9 |  |  | 17-05-2025 & 12-07-2025
7 |  | 32/0 | 33/0 | 1.658 |  | tse | 2026-07-15: 22-05-2025 to 25-05-2025; 2026-07-26: 28-05-2025 -30-05-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 35 | [7 empty] | 32/0-33/0 |  |  | 25-05-2025 & 31-05-2025
8 |  | 31/0 | 32/0 | 2.689 |  | tse | 2026-07-15: 12-06-2025 to 17-06-2025; 2026-07-26: 13-06-2025 to 17-06-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 35 | [7 empty] | 31/0-32/0 |  |  | 2025-06-17
9 |  | 30/0 | 31/0 | 2.383 |  | tse | 2026-07-15: 22-06-2025 to 02-07-2025; 2026-07-26: 23-06-2025 to 02-07-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 45 | [7 empty] | 30/0-31/0 |  |  | 02-07-2025 to 03-07-2025
10 |  | 29/9 | 30/0 | 0.508 |  | tse | 2026-07-15: 06-07-2025 to 11-07-2025; 2026-07-26: 07-07-2025 to 11-07-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 45 | [7 empty] | 29/9-30/0 |  |  | 2025-07-12
11 |  | 21/0 | 22/0 | 3.867 |  | tse | 2026-07-15: 17-07-2025 to 24-07-2025; 2026-07-26: 06-08-2025 to 09-08-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 45 | [7 empty] | 21/0-22/0 |  |  | 2025-05-25
12 |  | 20A/0 | 21/0 | 0.172 |  | tse | 2026-07-15: 23-08-2025 to 31-08-2025; 2026-07-26: 24--08-2025 to 31-08-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 45 | [7 empty] | 20A/0 - 21/0 |  |  | 2025-09-01
13 |  | 20/0 | 20A/0 | 0.241 |  | tse | 2026-07-15: 22-08-2025 to 01-09-2025; 2026-07-26: 24--08-2025 to 01-09-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 45 | [7 empty] | 20/0- 20A/0 |  |  | 2025-09-01
14 |  | 12/0 | 13/0 | 4.9795 |  | tse | 2026-07-15: 01-09-2025 to 07-09-2025; 2026-07-26: 15-09-2025 to 18-09-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 40 | [7 empty] | 12/0-13/0 |  |  | 08-09-2025 & 19-09-2025
15 |  | 10/0 | 11/0 | 4.125 |  | tse | 2026-07-15: 28-09-2025 to 05-10-2025; 2026-07-26: 08-10-2025 to 10-10-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 40 | [7 empty] | 10/0-11/0 |  |  | 05-10-2025 & 10-10-2025
16 |  | 19/0 | 20/0 | 1.6396 |  | tse | 2026-07-15: 15-09-2025 to 20-10-2025; 2026-07-26: 2025-10-19 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 45 | [7 empty] | 19/0-20/0 |  |  | 2025-09-07
17 |  | 18/0 | 19/0 | 1.564 |  | tse | 2026-07-15: 21-09-2025 to 20-10-2025; 2026-07-26: 2025-10-21 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 45 | [7 empty] | 18/0-19/0 |  |  | 2025-10-23
18 |  | 9/10 | 10/0 | 4.598 |  | tse | 2026-07-15: 16-10-2025 to 23-10-2025; 2026-07-26: 24-10-2025 to 26-10-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 40 | [7 empty] | 9/10-10/0 | ` |  | 2025-10-26
19 |  | 13/0 | 14/0 | 4.9 |  | tse | 2026-07-15: 13-11-2025 to 19-11-2025; 2026-07-26: 20-11-2025 to 22-11-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 45 | [7 empty] | 13/0- 14/0 |  |  | 10-11-2025 & 19-11-2025 &22-11-2025
20 |  | 11/0 | 12/0 | 4.751 |  | tse | 2026-07-15: 03-12-2025 to 07-12-2025; 2026-07-26: 07-12-2025 to 09-12-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 53 | [7 empty] | 11/0-12/0 |  |  | 07-12-2025 to 09-12-2025
21 |  | 17/0 | 18/0 | 1.539 |  | tse | 2026-07-15: 10-11-2025 to 15-11-2025; 2026-07-26: 08-12-2025 to 11-12-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 40 | [7 empty] | 17/0 -18/0 |  |  | 16-11-2025 to 12-12-2025
22 |  | 14/0 | 15/0 | 0.498 |  | tse | 2026-07-15: 15-12-2025 to 17-12-2025; 2026-07-26: 15-12-2025 to 17-12-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 53 | [7 empty] | 14/0 - 15/0 |  |  | 2025-12-18
23 |  | 16/0 | 17/0 | 4.762 |  | tse | 2026-07-15: 27-11-2025 to 08-12-2025; 2026-07-26: 24-12-2025 to 30-12-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 40 | [7 empty] | 16/0-17/0 |  |  | 09-12-2025 & 31-12-2025
24 |  | 15/0 | 16/0 | 1.9095 |  | tse | 2026-07-15: 19-12-2025 to 23-12-2025; 2026-07-26: 24-12-2025 to 30-12-2025 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 49 | [7 empty] | 15/0 - 16/0 |  |  | 23-12-2025 & 31-12-2025
25 |  | 8/4 | 9/0 | 4.933 |  | tse | 2026-07-15: 31-12-2025 to 06-01-2026; 2026-07-26: 06-01-2026 to 07-01-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 53 | [7 empty] | 8/4 - 9/0 |  |  | 2026-01-07
26 |  | 6/0 | 7/0 | 3.2936 |  | tse | 2026-07-15: 12-01-2026 to 15-01-2026; 2026-07-26: 18-01-2026 to 19-01-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 53 | [7 empty] | 6/0-7/0 |  |  | 2026-01-19
27 |  | 27/0 | 27/3 | 1.179 |  | tse | 2026-07-15: 09-01-2025 to 12-01-2026; 2026-07-26: 22-01-2026 to 29-01-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed + Rectification work under Progress | M.R. Const | 50 | [7 empty] | 27/0 - 27/3 |  |  | 2026-01-30
28 |  | 27/3 | 28/0 | 2.68 |  | tse | 2026-07-15: 17-01-2026 to 28-01-2026; 2026-07-26: 22-01-2026 to 29-01-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed + Rectification work under Progress | M.R. Const | 67 | [7 empty] | 27/3 - 28/0 |  |  | 2026-01-30
29 |  | 8/3 | 8/4 | 0.337 |  | tse | 2026-07-15: 2026-01-20; 2026-07-26: 22-01-2026 to 28-01-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Ramvath | 20 | [7 empty] | 8/3-8/4 |  |  | 2026-01-29
30 |  | 7/0 | 8/0 | 0.22568 |  | tse | 2026-07-15: 2026-01-30; 2026-07-26: 2026-01-31 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 56 | [7 empty] | 7/0 - 8/0 |  |  | 2026-01-31
31 |  | Gantry | 1/0 | 0.09997 |  | tse | 2026-07-15: 30-01-2026 to 01-02-2026; 2026-07-26: 01-02-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Kamruddin | 36 | [7 empty] | Gantry - 1/0 |  |  | 2026-02-01
32 |  | 8/2 | 8/3 | 0.406 |  | tse | 2026-07-15: 03-02-2026 to 04-02-2026; 2026-07-26: 2026-02-04 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 56 | [7 empty] | 8/2 - 8/3 |  |  | 2026-02-04
33 |  | 28/0 | 29/0 | 0.786 |  | tse | 2026-07-15: 01-02-2026 to 04-02-2026; 2026-07-26: 04-02-2026 to 06-02-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 69 | [7 empty] | 28/0 -29/0 |  |  | 2026-01-31
34 |  | 1/0 | 1A/0 | 0.23453 |  | tse | 2026-07-15: 07-02-2026 to 08-02-2026; 2026-07-26: 2026-02-08 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Kamruddin | 36 | [7 empty] | 1/0-1A/0 |  |  | 2026-02-08
35 |  | 1A/0 | 1B/0 | 0.397 |  | tse | 2026-07-15: 2026-02-02; 2026-07-26: 2026-02-11 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Kamruddin | 36 | [7 empty] | 1A/0 - 1B/0 |  |  | 2026-02-11
36 |  | 4/12 | 5/0 | 4.964 |  | tse | 2026-07-15: 06-02-2026 to 12-02-2026; 2026-07-26: 2026-02-12 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 56 | [7 empty] | 4/12 - 5/0 |  |  | 2026-02-12
37 |  | 8/1 | 8/2 | 0.272 |  | tse | 2026-07-15: 2026-02-09; 2026-07-26: 2026-02-19 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Ramvath | 20 | [7 empty] | 8/1-8/2 |  |  | 2026-02-07
38 |  | 8/0 | 8/1 | 0.414 |  | tse | 2026-07-15: 2026-02-09; 2026-07-26: 2026-02-19 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Ramvath - 02 | 20 | [7 empty] | 8/0 - 8/1 |  |  | 2026-02-20
39 |  | 1C/0 | 2/0 | 0.31 |  | tse | 2026-07-15: 24-02-2026 to 25-02-2026; 2026-07-26: 2026-02-25 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Kamruddin | 36 | [7 empty] | 1C/0 - 2/0 |  |  | 2026-02-25
40 |  | 5/0 | 6/0 | 0.182 |  | tse | 2026-07-15: 2026-03-01; 2026-07-26: 2026-03-02 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Kamruddin | 36 | [7 empty] | 5/0 - 6/0 |  |  | 2026-03-02
41 |  | 4/0 | 4/12 | 4.968 |  | tse | 2026-07-15: 20-02-2026 to 26-02-2026; 2026-07-26: 02-03-2026 to 05-03-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 56 | [7 empty] | 4/0 - 4/12 |  |  | 2026-03-05
42 |  | 38/0 | 39/0 | 3.036 |  | tse | 2026-07-15: 12-02-2026 to 19-02-2026; 2026-07-26: 01-03-2026 to 11-03-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 69 | [7 empty] | 38/0 - 39/0 |  |  | 2026-02-19
43 |  | 3/0 | 4/0 | 1.681 |  | tse | 2026-07-15: 01-03-2026 to 05.03.2026; 2026-07-26: 2026-03-14 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 56 | [7 empty] | 3/0-4/0
44 |  | 37/0 | 38/0 | 2.779 |  | tse | 2026-07-15: 24-02-2026 to 10-03-2026; 2026-07-26: 16-03-2026 to 19-03-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | M.R. Const | 17 | [7 empty] | 37/0 - 38/0 |  |  | 2026-03-21
45 |  | 2/0 | 3/0 | 2.365 |  | tse | 2026-07-15: 17-03-2026 to 20-3-2026; 2026-07-26: 18-03-2026 to 20-03-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 55 | [7 empty] | 2/0 - 3/0 |  |  | 2026-03-20
46 |  | 1B/0 | 1C/0 | 1.686 |  | tse | 2026-07-15: 26-03-2026 to 28-03-2026; 2026-07-26: 28-03-2026 to 29-03-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 55 | [7 empty] | 1B/0 - 1C/0 |  |  | 2026-03-29
47 |  | 39/0 | 40/0 | 4.21 |  | tse | 2026-07-15: 26-03-2026 to 31-03-2026; 2026-07-26: 29-03-2026 to 02-04-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Kamruddin | 43 | [7 empty] | 39/0 - 40/0 |  |  | 01-04-2026 & 02-04-2026
48 |  | 36/0 | 37/0 | 3.608 |  | tse | 2026-07-15: 13-04-2026 to 17-04-2026; 2026-07-26: 29-04-2026 to 30-04-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Kamruddin | 43 | [7 empty] | 36/0 - 37/0 |  |  | 2026-04-17
49 |  | 42/0 | 43/0 | 3.949 |  | tse | 2026-07-15: 30-04-2026 to 05-05-2026; 2026-07-26: 08-05-2026 to 10-05-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 42 | [7 empty] | 42/0 - 43/0 |  |  | 2026-05-05
50 |  | 43/0 | 43A/0 | 2.2618 |  | tse | 2026-07-15: 14-05-2026 to 17-05-2026; 2026-07-26: 15-05-2026 to 18-05-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 42 | [7 empty] | 43/0 - 43A/0 |  |  | 2026-05-18
51 |  | 34/2 | 35/0 | 0.248 |  | tse | 2026-07-15: 18-05-2026 to 26-05-2026; 2026-07-26: 19-05-2026 to 26-05-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Ramavath | 17 | [7 empty] | 34/2-35/0 |  |  | 2026-05-26
52 |  | 35/0 | 36/0 | 1.858 |  | tse | 2026-07-15: 18-05-2026 to 24-05-2026; 2026-07-26: 21-05-2026 to 30-05-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Kamruddin | 25 | [7 empty] | 35/0 - 36/0 |  |  | 2026-05-31
53 |  | 34/1 | 34/2 | 0.43 |  | tse | 2026-07-15: 2026-06-02; 2026-07-26: 02-06-2026 to 08-06-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Pankaj | 43 | [7 empty] | 34/1 - 34/2
54 |  | 34/0 | 34/1 | 0.248 |  | tse | 2026-07-15: 2026-06-02; 2026-07-26: 02-06-2026 to 08-06-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Ramavath | 17 | [7 empty] | 34/0 - 34/1 |  |  | 2026-05-29
55 |  | 33/0 | 34/0 | 0.966 |  | tse | 2026-07-15: 26-05-2026 to 29-05-2026; 2026-07-26: 09-06-2026 to 12-06-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Pankaj | 43 | [7 empty] | 33/0 - 34/0 |  |  | 2026-06-12
56 |  | 43A/0 | 43A/1 | 0.485 |  | tse | 2026-07-15: 2026-06-10; 2026-07-26: 2026-06-18 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 34 | [7 empty] | 43A/0 - 43A/1 |  |  | 2026-06-18
57 |  | 43A/1 | 43B/0 | 1.814 |  | tse | 2026-07-15: 31-05-2026 to 02-06-2026; 2026-07-26: 2026-06-21 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 20 | [7 empty] | 43A/1 - 43B/0 |  |  | 03-06-2026 & 25-06-2026
58 |  | 43B/0 | 44/0 | 0.45969 |  | tse | 2026-07-15: 2026-06-20; 2026-07-26: 2026-06-24 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Nasiruddin | 34 | [7 empty] | 43B/0 - 44/0 |  |  | 2026-06-25
59 |  | 40/0 | 41/0 | 0.713 |  | tse | 2026-07-15: 24-06-2026 to 29-06-2026; 2026-07-26: 29-06-206 to 30-06-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Pankaj | 40 | [7 empty] | 40/0 - 41/0
60 |  | 41/0 | 42/0 | 0.762 |  | tse | 2026-07-15: 24-06-2026 to 29-06-2026; 2026-07-26: 29-06-2026 to 30-06-2026 |  |  |  |  | TA 421 |  | TA 421 | TA 421 | ta421 | TA 421 | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Final Sag Completed | Pankaj | 40 | [7 empty] | 41/0 - 42/0
|  | 11/0 | 12/0 | 2732.9 |  | TSE | 2026-07-15: 2026-05-09; 2026-07-22: 2026-05-12; 2026-07-23: 2026-06-18; 2026-07-26: 2026-06-19 |  |  |  |  | TA 504 |  | TA 504 | TA 504 | ta504 | TA 504 | TA 504 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 1 | Bhinder | 11/1, 11/2, 11/3, 11/4, 11/5, 11/6, 12/0 | Ready |  | 2732.9 | Completed | Completed | Completed | Completed | Tanjira Bibi | 40 | 10
|  | 12/0 | 13/0 | 2372.426 |  | TSE | 2026-07-15: 2026-05-16; 2026-07-22: 2026-05-20; 2026-07-23: 2026-06-13; 2026-07-26: 2026-06-15 |  |  |  |  | TA 504 |  | TA 504 | TA 504 | ta504 | TA 504 | TA 504 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 2 | Bhinder | 12/1, 12/2, 12/3, 12/4, 12/5, 13/0 | Ready |  | 2372.426 | Completed | Completed | Completed | Completed | Tanjira Bibi | 40 | 10
|  | 15/0 | 16/0 | 3229.725 |  | TSE | 2026-07-15: 2026-03-25; 2026-07-22: 2026-03-29; 2026-07-23: 2026-04-01; 2026-07-26: 2026-04-04 |  |  |  |  | TA 504 |  | TA 504 | TA 504 | ta504 | TA 504 | TA 504 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 3 | Bhinder | 15/1, 15/2, 15/3, 15/4, 15/5, 15/6, 15/7, 16/0 | Ready |  | 3229.73 | Completed | Completed | Completed | Completed | Lamba Construction | 50 | 13
|  | 16/0 | 16/3 | 1245.996 |  | TSE | 2026-07-15: 2026-04-01; 2026-07-22: 2026-04-04; 2026-07-23: 2026-04-06; 2026-07-26: 2026-04-09 |  |  |  |  | TA 504 |  | TA 504 | TA 504 | ta504 | TA 504 | TA 504 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 4 | Bhinder | 16/1, 16/2, 16/3 | Ready |  | 1246 | Completed | Completed | Completed | Completed | Lamba Construction | 50 | 13
|  | 16/3 | 17/0 | 1466.604 |  | TSE | 2026-07-15: 2026-02-04; 2026-07-22: 2026-02-07; 2026-07-23: 2026-02-19; 2026-07-26: 2026-02-19 |  |  |  |  | TA 504 |  | TA 504 | TA 504 | ta504 | TA 504 | TA 504 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 5 | Bhinder | 16/4, 16/5, 16/6, 17/0 | Ready |  | 1466.6 | Completed | Completed | Completed | Completed | Lamba Construction | 50 | 13
|  | 17/0 | 17/4 | 1646.996 |  | TSE | 2026-07-15: 2026-02-11; 2026-07-22: 2026-02-14; 2026-07-23: 2026-02-19; 2026-07-26: 2026-02-22 |  |  |  |  | TA 504 |  | TA 504 | TA 504 | ta504 | TA 504 | TA 504 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 6 | Bhinder | 17/1, 17/2, 17/3, 17/4 | Ready |  | 1647 | Completed | Completed | Completed | Completed | Lamba Construction | 50 | 13
|  | 17/4 | 18/0 | 2304.228 |  | TSE | 2026-07-15: 2026-02-17; 2026-07-22: 2026-02-21; 2026-07-23: 2026-02-25; 2026-07-26: 2026-02-27 |  |  |  |  | TA 504 |  | TA 504 | TA 504 | ta504 | TA 504 | TA 504 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 7 | Bhinder | 17/5, 17/6, 17/7, 17/8, 17/9, 18/0 | Ready |  | 2304.23 | Completed | Completed | Completed | Completed | Lamba Construction | 50 | 13
|  | 18/0 | 18/1 | 503.002 |  | Manual | 2026-07-15: 2026-02-19; 2026-07-22: 2026-02-24; 2026-07-23: 2026-02-25; 2026-07-26: 2026-02-28 |  |  |  |  | TA 504 |  | TA 504 | TA 504 | ta504 | TA 504 | TA 504 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 8 | Bhinder | 18/1, | Ready |  | 503 | Completed | Completed | Completed | Completed | Lamba Construction | 50 | 13
|  | 18/1 | 19/0 | 3025.206 |  | TSE | 2026-07-15: 2026-02-19; 2026-07-22: 2026-02-24; 2026-07-23: 2026-02-25; 2026-07-26: 2026-02-28 |  |  |  |  | TA 504 |  | TA 504 | TA 504 | ta504 | TA 504 | TA 504 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 9 | Bhinder | 18/2, 18/3, 18/4, 18/5, 18/6, 18/7, 18/8,19/0, | Ready |  | 3025 | Completed | Completed | Completed | Completed | Lamba Construction | 50 | 13
|  | 19/0 | 20/0 | 1573.56 |  | TSE | 2026-07-15: 2026-05-23; 2026-07-22: 2026-05-27; 2026-07-23: 2026-06-02; 2026-07-26: 2026-06-07 |  |  |  |  | TA 504 |  | TA 504 | TA 504 | ta504 | TA 504 | TA 504 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 10 | Bhinder | 19/1, 19/2, 19/3, 20/0 | Ready |  | 1573.56 | Completed | Completed | Completed | Completed | Lamba Construction | 50 | 13
|  | 20/0 | 21/0 | 460.684 |  | Manual | 2026-07-15: 2026-05-16; 2026-07-22: 2026-05-17; 2026-07-23: 2026-06-12; 2026-07-26: 2026-06-14 |  |  |  |  | TA 504 |  | TA 504 | TA 504 | ta504 | TA 504 | TA 504 - DPR - 2026-08-07.xlsx | Stringing Compiled | FALSE |  |  |  | 11 | Bhinder | 21/0 | Ready |  | 460.684 | Completed | Completed | Completed | Completed | Lamba Construction | 50 | 13
|  | 100/0 | 101/0 | 419 |  | Manual | 2026-07-15: 20.01.2026; 2026-07-22: 25.01.2026; 2026-07-23: 05.02.2026; 2026-07-26: 07.02.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 1 | 100/0 To 101/0 |  | Ready | Done | Done |  |  |  | Done | Alimuddin | 30 | [12 empty] | 100/0, 101/0
|  | 101/0 | 102/0 | 3470 |  | TSE | 2026-07-15: 27.01.2026; 2026-07-22: 02.02.2026; 2026-07-23: 10.02.2026; 2026-07-26: 15.02.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 2 | 101/0 To 102/0 |  | Ready | Done | Done |  |  |  | Done | Alimuddin | 30 | [12 empty] | 101/0,101/1, 101/2, 101/3, 101/4, 101/5, 101/6, 101/7, 101/8 & 102/0
|  | 102/0 | 103/0 | 461 |  | Manual | 2026-07-15: 08.02.2026; 2026-07-22: 12.02.2026; 2026-07-23: 18.02.2026; 2026-07-26: 22.02.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 3 | 102/0 To 103/0 |  | Ready | Done | Done |  |  |  | Done | Alimuddin | 30 | [12 empty] | 102/0 & 103/0
|  | 103/0 | 103/5A | 2200 |  | TSE | 2026-07-15: 16.02.2026; 2026-07-22: 22.02.2026; 2026-07-23: 26.02.2026; 2026-07-26: 28.02.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 4 | 103/0 To 103/5A |  | Ready | Done | Done |  |  |  | Done | Alimuddin | 30 | [12 empty] | 103/0, 103/1, 103/2, 103/4, 103/5 & 103/5A
|  | 103/5A | 103/6A | 567 |  | TSE | 2026-07-15: 24.02.2026; 2026-07-22: 26.02.2026; 2026-07-23: 12.03.2026; 2026-07-26: 16.03.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 5 | 103/5A To 103/6A |  | Ready | Done | Done |  |  |  | Done | Alimuddin | 30 | [12 empty] | 103/5A,103/5A1 & 103/6A
|  | 103/6A | 104/0 | 1403 |  | TSE | 2026-07-15: 12.03.2026; 2026-07-22: 16.03.2026; 2026-07-23: 17.03.2026; 2026-07-26: 20.03.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 6 | 103/6A To 104/0 |  | Ready | Done | Done |  |  |  | Done | Alimuddin | 30 | [12 empty] | 103/6A ,103/7, 103/8, 103/9 & 104/0.
|  | 104/0 | 105/0 | 967 |  | TSE | 2026-07-15: 07.03.2026; 2026-07-22: 10.02.2026; 2026-07-23: 12.04.2026; 2026-07-26: 17.04.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 7 | 104/0 To 105/0 |  | Ready | Done | Done |  |  |  | Done | Alimuddin | 30 | [12 empty] | 104/0, 104/1, 104/2 & 105/0
|  | 111/0 | 112/0 | 1954 |  | TSE | 2026-07-15: 28.03.2026; 2026-07-22: 29.03.2026; 2026-07-23: 29.03.2026; 2026-07-26: 31.03.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 8 | 111/0 To 112/0 |  | Ready | Done | Done |  |  |  | Done | Alimuddin | 30 | [12 empty] | 111/0, 111/1, 111/2, 111/3, 111/4 & 112/0
|  | 113/0 | 114/0 | 2565 |  | TSE | 2026-07-15: 25.03.2026; 2026-07-22: 27.03.2026; 2026-07-23: 28.03.2026; 2026-07-26: 31.03.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 9 | 113/0 To 114/0 |  | Ready | Done | Done |  |  |  | Done | Jahangir Alam | 38 | [12 empty] | 113/0, 113/1, 113/2 , 113/3, 113/4, 113/5, 113/6 & 114/0
|  | 114/0 | 115/0 | 4304 |  | TSE | 2026-07-15: 22.05.2026; 2026-07-22: 05.06.2026; 2026-07-23: 06.06.2026; 2026-07-26: 09.06.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 10 | 114/0 To 115/0 |  | Ready | Done | Done |  |  |  | Done | Jahangir Alam | 38 | [12 empty] | 114/0, 114/1, 114/2, 114/3, 114/4, 114/5, 114/6, 114/7, 114/8, 114/9, 114/10 & 115/0
|  | 110A/0 | 111/0 | 1230 |  | TSE | 2026-07-15: 14.05.2026; 2026-07-22: 18.05.2026; 2026-07-23: 25.05.2026; 2026-07-26: 29.05.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 11 | 110A/0 To 111/0 |  | Ready | Done | Done |  |  |  | Done | Alimuddin | 35 | [12 empty] | 110A/0 , 110A/1, 110A/2 & 111/0.
|  | 110/0 | 110A/0 | 3512 |  | TSE | 2026-07-15: 08.06.2026; 2026-07-22: 12.06.2026; 2026-07-23: 13.06.2026; 2026-07-26: 16.06.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 12 | 110/0 To 110A/0 |  | Ready | Done | Done |  |  |  | Done | Nasiruddin | 25 | [12 empty] | 110/0,110/1,110/2,110/2,110/3,110/3,110/4,110/5,110/6,110/7,110/8,110A/0
|  | 112/0 | 113/0 | 226 |  | Hot Line | 2026-07-15: 24.05.2026; 2026-07-22: 30.05.2026; 2026-07-23: 24.05.2026; 2026-07-26: 30.05.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 13 | 112/0 To 113/0 |  | Ready | Done | Done |  |  |  | Done | Ram Singh | 25 | [12 empty] | 112/0, 113/0
|  | 126/0 | 127/0 | 1957 |  | TSE | 2026-07-15: 10.07.2026; 2026-07-22: 14.07.2026; 2026-07-23: 2026-07-18; 2026-07-26: 24.07.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 14 | 126/0 To 127/0 |  | Ready | Done | Done |  |  |  | Done | Jahangir Alam | 55 | [12 empty] | 126/0,126/1,126/2,126/3,126/4, 127/0
|  | 127/0 | 128/0 | 1441 |  | TSE | 2026-07-15: 30.06.2026; 2026-07-22: 05.07.2026; 2026-07-23: 14.07.2026; 2026-07-26: 17.07.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 15 | 127/0 To 128/0 |  | Ready | Done | Done |  |  |  | Done | Jahangir Alam | 55 | [12 empty] | 127/0,127/1,127/2 , 127/3,128/0
|  | 108/0 | 109/0 | 1668 |  | TSE | 2026-07-15: 24.06.2026; 2026-07-22: 29.06.2026; 2026-07-23: 03.07.2026; 2026-07-26: 06.07.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 16 | 108/0 To 109/0 |  | Ready | Done | Done |  |  |  | Done | Nasiruddin | 53 | [12 empty] | 108/0,108/1 , 108/2 ,108/3,108/4, 108/5
|  | 109/0 | 110/0 | 1949 |  | TSE | 2026-07-15: 18.06.2026; 2026-07-22: 21.06.2026; 2026-07-23: 24.06.2026; 2026-07-26: 29.06.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 17 | 109/0 To 110/0 |  | Ready | Done | Done |  |  |  | Done | Nasiruddin | 50 | [12 empty] | 109/0,109/1,109/2,109/3,109/4, 110/0
|  | 115/0 | 116/0 | 200 |  | Hot Line | 2026-07-15: 01.06.2026; 2026-07-22: 12.06.2026; 2026-07-23: 01.06.2026; 2026-07-26: 12.06.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 18 | 115/0 To 116/0 |  | Ready | Done | Done |  |  |  | Done | Ram Singh | 25 | [12 empty] | 115/0,116/0
|  | 105/0 | 106/0 | 755 |  | TSE | 2026-07-15: 09.07.2026; 2026-07-22: 11.07.2026; 2026-07-23: 12.07.2026; 2026-07-26: 14.07.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 19 | 105/0 To 106/0 |  | Ready | Done | Done |  |  |  | Done | [14 empty] | 105/0,105/1,106/0
|  | 106/0 | 108/0 | 212 |  | Manual | 2026-07-15: 09.07.2026; 2026-07-22: 11.07.2026; 2026-07-23: 09.07.2026; 2026-07-26: 11.07.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 20 | 106/0 To 108/0 |  | Ready | Done | Done |  |  |  | Done | Nasiruddin | 50 | [12 empty] | 106/0,108/0
|  | 117/0 | 118/0 | 240 |  | Hot Line | 2026-07-15: 15.06.2026; 2026-07-22: 19.06.2026; 2026-07-23: 15.06.2026; 2026-07-26: 19.06.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 21 | 117/0 To 118/0 |  | Ready | Done | Done |  |  |  | Done | Ram Singh | 41 | [12 empty] | 117/0 ,118/0
|  | 147/0 | 147A/0 |  |  | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1 | 22 | 147/0 To 147A/0
|  | 147A/0 | 148/0 |  |  | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1 | 23 | 147A/0 To148/0
|  | 175/0 | 176/0 | 1675 |  | TSE | 2026-07-15: 2026-07-18; 2026-07-22: 2026-07-21; 2026-07-23: 24.07.2026; 2026-07-26: 27.07.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 24 | 175/0 To 176/0 |  | Ready | Done | Done |  |  |  | Done | Sk infra | 65 | [12 empty] | 175/0,175/1,175/2,175/3,175/4, 176/0
|  | 176/0 | 177/0 | 1564 |  | TSE | 2026-07-15: 19.06.2026; 2026-07-22: 23.06.2026; 2026-07-23: 03.07.2026; 2026-07-26: 09.07.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 25 | 176/0 To 177/0 |  | Ready | Done | Done |  |  |  | Done | Sk infra | 67 | [12 empty] | 176/0,176/1, 176/2,176/3,177/0
|  | 177/0 | 178/0 | 3272 |  | TSE | 2026-07-15: 01.07.2026; 2026-07-22: 11.07.2026; 2026-07-23: 12.07.2026; 2026-07-26: 17.07.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 26 | 177/0 To 178/0 |  | Ready | Done | Done |  |  |  | Done | Sk infra | 67 | [12 empty] | 177/0,177/1,177/2,177/3,177/4,177/5,177/6,177/7,177/8,178/0
|  | 116/0 | 117/0 | 1147 |  | TSE | 2026-07-15: 12.06.2026; 2026-07-22: 15.06.2026; 2026-07-23: 16.06.2026; 2026-07-26: 19.06.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 27 | 116/0 To 117/0 |  | Ready | Done | Done |  |  |  | Done | Jahangir Alam | 38 | [12 empty] | 116/0,116/1, 116//2 117/0
|  | 120/0 | 121/0 | 1593 |  | TSE | 2026-07-15: 23.06.2026; 2026-07-22: 26.06.2026; 2026-07-23: 24.06.2026; 2026-07-26: 07.07.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 28 | 120/0 To 121/0 |  | Ready | Done | Done |  |  |  | Done | Jahangir Alam | 55 | [12 empty] | 120/0,120/1,120/2,120/3,121/0
|  | 119/0 | 120/0 | 193 |  | Hot Line | 2026-07-15: 26.06.2026; 2026-07-22: 30.06.2026; 2026-07-23: 26.06.2026; 2026-07-26: 30.06.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 29 | 119/0 To 120/0 |  | Ready | Done | Done |  |  |  | Done | Ram Singh | 41 | [12 empty] | 119/0,120/0
|  | 118/0 | 119/0 | 421 |  | Manual | 2026-07-15: 21.06.2026; 2026-07-22: 02.07.2026; 2026-07-23: 21.06.2026; 2026-07-26: 02.07.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 30 | 118/0 To 119/0 |  | Ready | Done | Done |  |  |  | Done | Ram Singh | 41 | [12 empty] | 118/0, 119/0
|  | 99/0 | 100/0 | 3478 |  | TSE | 2026-07-15: 16.07.2026 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 31 | 99/0 - 100/0 |  | Ready | Done |  |  |  |  | Wip | [14 empty] | 99/0/1/2/3/4/5/6/7/8, 100/0
|  | 125/0 | 126/0 | 742.55 |  | TSE | 2026-07-15: 2026-07-16 |  |  |  |  | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 32 | 125/0 To126/0 |  | Ready | Done | Done |  |  |  | Wip | [14 empty] | 125/0,125/1,126/1
|  | 155/0 | 156/0 | 2306.85 |  | TSE | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | FALSE |  |  | 1 | 33 | 155/0 To 156/0 |  | Ready | [20 empty] | 155/0, 155/1,155/2 , 155/3, 155/3,155/4 ,155/5 , 156/0
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
[6 empty] | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
|  |  | Total | 48.0924 |  | tse | [11 empty] | TA 505 |  | TA 505 | TA 505 | ta505 | TA 505 | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | 1
|  | 1/0 | 2/0 | 4424.083 |  | TSE | 2026-07-15: 2026-01-18; 2026-07-22: 2026-01-22; 2026-07-23: 2026-01-26; 2026-07-26: 2026-01-31 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 1 | Sirohi |  | Ready |  | 4424.083 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 5/0 | 6/0 | 4949.33 |  | TSE | 2026-07-15: 2026-01-22; 2026-07-22: 2026-01-27; 2026-07-23: 2026-01-27; 2026-07-26: 2026-02-05 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 2 | Sirohi |  | Ready |  | 4949.33 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 48/0 | 50/0 | 688.47 |  | TSE | 2026-07-15: 2025-12-19; 2026-07-22: 2025-12-30; 2026-07-23: 2026-01-15; 2026-07-26: 2026-01-20 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 3 | Sirohi |  | Ready |  | 688.47 | Completed | Completed | Completed | Completed | Jahangir Alam | 39 | [13 empty] | 16
|  | 50/0 | 51/0 | 1160.08 |  | TSE | 2026-07-15: 2025-12-19; 2026-07-22: 2025-12-30; 2026-07-23: 2026-01-17; 2026-07-26: 2026-01-22 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 4 | Sirohi |  | Ready |  | 1160.08 | Completed | Completed | Completed | Completed | Jahangir Alam | 39 | [13 empty] | 16
|  | 2/0 | 2A/0 | 3318.603 |  | TSE | 2026-07-15: 2026-02-15; 2026-07-22: 2026-02-19; 2026-07-23: 2026-02-22; 2026-07-26: 2026-02-23 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 5 | Sirohi |  | Ready |  | 3318.603 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 51/0 | 51A/0 | 1244.855 |  | TSE | 2026-07-15: 2026-01-17; 2026-07-22: 2026-01-20; 2026-07-23: 2026-01-27; 2026-07-26: 2026-01-31 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 6 | Sirohi |  | Ready |  | 1244.855 | Completed | Completed | Completed | Completed | Jahangir Alam | 39 | [13 empty] | 16
|  | 51A/0 | 51C/0 | 1234.81 |  | TSE | 2026-07-15: 2026-01-21; 2026-07-22: 2026-01-26; 2026-07-23: 2026-01-27; 2026-07-26: 2026-01-31 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 7 | Sirohi |  | Ready |  | 1234.81 | Completed | Completed | Completed | Completed | Jahangir Alam | 39 | [13 empty] | 16
|  | 51C/0 | 52/0 | 1968.185 |  | TSE | 2026-07-15: 2026-02-13; 2026-07-22: 2026-02-16; 2026-07-23: 2026-02-26; 2026-07-26: 2026-02-27 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 8 | Sirohi |  | Ready |  | 1968.185 | Completed | Completed | Completed | Completed | Jahangir Alam | 39 | [13 empty] | 16
|  | 52/0 | 53/0 | 992.08 |  | TSE | 2026-07-15: 2026-02-23; 2026-07-22: 2026-02-25; 2026-07-23: 2026-02-24; 2026-07-26: 2026-02-27 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 9 | Sirohi |  | Ready |  | 992.08 | Completed | Completed | Completed | Completed | Jahangir Alam | 39 | [13 empty] | 16
|  | 4/0 | 5/0 | 2809.04 |  | TSE | 2026-07-15: 2026-02-23; 2026-07-22: 2026-02-25; 2026-07-23: 2026-02-24; 2026-07-26: 2026-02-28 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 10 | Sirohi |  | Ready |  | 2809.04 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 18/0 | 19/0 | 3934.01 |  | TSE | 2026-07-15: 2026-02-17; 2026-07-22: 2026-02-23; 2026-07-23: 2026-02-24; 2026-07-26: 2026-02-28 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 11 | Sirohi |  | Ready |  | 3934.01 | Completed | Completed | Completed | Completed | Jahangir Alam | 39 | [13 empty] | 16
|  | 68/0 | 68/1 | 504 |  | Manual | 2026-07-15: 2026-03-02; 2026-07-22: 2026-03-05; 2026-07-23: 2026-03-08; 2026-07-26: 2026-03-10 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 12 | Sirohi |  | Ready |  | 504 | Completed | Completed | Completed | Completed | Taimoor Ali | 22 | [13 empty] | 10
|  | 67/0 | 68/0 | 176.73 |  | Manual | 2026-07-15: 2026-03-05; 2026-07-22: 2026-03-05; 2026-07-23: 2026-03-20; 2026-07-26: 2026-03-23 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 13 | Sirohi |  | Ready |  | 176.73 | Completed | Completed | Completed | Completed | Taimoor Ali | 22 | [13 empty] | 10
|  | 6/0 | 9/0 | 1210.68 |  | TSE | 2026-07-15: 2026-03-15; 2026-07-22: 17-03-2026; 2026-07-23: 2026-03-17; 2026-07-26: 2026-03-18 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 14 | Sirohi |  | Ready |  | 1210.68 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 66/0 | 67/0 | 743.77 |  | Manual | 2026-07-15: 2026-03-18; 2026-07-22: 2026-03-22; 2026-07-23: 2026-03-28; 2026-07-26: 2026-03-29 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 15 | Sirohi |  | Ready |  | 743.77 | Completed | Completed | Completed | Completed | Taimoor Ali | 22 | [13 empty] | 10
|  | 10/0 | 11/0 | 1256.34 |  | TSE | 2026-07-15: 2026-03-23; 2026-07-22: 2026-03-24; 2026-07-23: 2026-04-01; 2026-07-26: 2026-04-02 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 16 | Sirohi |  | Ready |  | 1256.34 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 11/0 | 11/3 | 1114 |  | TSE | 2026-07-15: 2026-04-03; 2026-07-22: 2026-04-04; 2026-07-23: 2026-04-15; 2026-07-26: 2026-04-16 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 17 | Sirohi |  | Ready |  | 1114 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 11/3 | 12/0 | 530.153 |  | Manual | 2026-07-15: 2026-03-28; 2026-07-22: 2026-03-28; 2026-07-23: 2026-04-15; 2026-07-26: 2026-04-16 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 18 | Sirohi |  | Ready |  | 530.153 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 65A/3 | 66/0 | 244.262 |  | Manual | 2026-07-15: 2026-03-25; 2026-07-22: 2026-03-25; 2026-07-23: 2026-04-06; 2026-07-26: 2026-04-07 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 19 | Sirohi |  | Ready |  | 244.262 | Completed | Completed | Completed | Completed | Taimoor Ali | 22 | [13 empty] | 10
|  | 213/0 | 214/0 | 2351.3 |  | TSE | 2026-07-15: 2026-04-01; 2026-07-22: 2026-04-04; 2026-07-23: 2026-04-06; 2026-07-26: 2026-04-07 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 20 | Udaipur |  | Ready |  | 2351.3 | Completed | Completed | Completed | Completed | Bilkish Rehena | 33 | [13 empty] | 10
|  | 17/0 | 18/0 | 2732.97 |  | TSE | 2026-07-15: 2026-04-06; 2026-07-22: 2026-04-09; 2026-07-23: 2026-04-13; 2026-07-26: 2026-04-14 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 21 | Sirohi |  | Ready |  | 2732.97 | Completed | Completed | Completed | Completed | Jahangir Alam | 39 | [13 empty] | 16
|  | 9/0 | 10/0 | 272.18 |  | Manual | 2026-07-15: 2026-04-09; 2026-07-22: 2026-04-09; 2026-07-23: 2026-04-09; 2026-07-26: 2026-04-09 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 22 | Sirohi |  | Ready |  | 272.18 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 139/0 | 139A/0 | 655.83 |  | Manual | 2026-07-15: 2026-05-20; 2026-07-22: 2026-05-23; 2026-07-23: 2026-05-26; 2026-07-26: 2026-05-29 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 23 | Gogunda |  | Ready |  | 655.83 | Completed | Completed | Completed | Completed | Rejaul Sekh | 30 | [13 empty] | 10
|  | 139A/0 | 140/0 | 242.66 |  | Manual | 2026-07-15: 2026-05-16; 2026-07-22: 2026-05-19; 2026-07-23: 2026-06-11; 2026-07-26: 2026-06-13 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 24 | Gogunda |  | Ready |  | 242.66 | Completed | Completed | Completed | Completed | Rejaul Sekh | 30 | [13 empty] | 10
|  | 212/0 | 213/0 | 2393.12 |  | TSE | 2026-07-15: 2026-04-13; 2026-07-22: 2026-04-15; 2026-07-23: 2026-04-16; 2026-07-26: 2026-04-17 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 25 | Udaipur |  | Ready |  | 2393.12 | Completed | Completed | Completed | Completed | Bilkish Rehena | 33 | [13 empty] | 10
|  | 12/0 | 13/0 | 3315.27 |  | TSE | 2026-07-15: 2026-04-11; 2026-07-22: 2026-04-14; 2026-07-23: 2026-04-18; 2026-07-26: 2026-04-19 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 26 | Sirohi |  | Ready |  | 3315.27 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 65/0 | 65A/0 | 195.07 |  | Manual | 2026-07-15: 2026-04-12; 2026-07-22: 2026-04-12; 2026-07-23: 2026-05-13; 2026-07-26: 2026-05-17 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 27 | Sirohi |  | Ready |  | 195.07 | Completed | Completed | Completed | Completed | Taimoor Ali | 22 | [13 empty] | 10
|  | 65A/0 | 65A/3 | 919 |  | TSE | 2026-07-15: 2026-04-15; 2026-07-22: 2026-04-17; 2026-07-23: 2026-05-10; 2026-07-26: 2026-05-11 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 28 | Sirohi |  | Ready |  | 919 | Completed | Completed | Completed | Completed | Taimoor Ali | 22 | [13 empty] | 10
|  | 15/0 | 16/0 | 1674.936 |  | TSE | 2026-07-15: 2026-04-16; 2026-07-22: 2026-04-18; 2026-07-23: 2026-05-12; 2026-07-26: 2026-05-13 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 29 | Sirohi |  | Ready |  | 1674.936 | Completed | Completed | Completed | Completed | Jahangir Alam | 39 | [13 empty] | 16
|  | 64/0 | 64A/0 | 471.96 |  | TSE | 2026-07-15: 2026-04-22; 2026-07-22: 2026-04-23; 2026-07-23: 2026-05-21; 2026-07-26: 2026-05-22 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 30 | Sirohi |  | Ready |  | 471.96 | Completed | Completed | Completed | Completed | Taimoor Ali | 22 | [13 empty] | 10
|  | 211/0 | 212/0 | 3254.51 |  | TSE | 2026-07-15: 2026-04-23; 2026-07-22: 2026-04-29; 2026-07-23: 2026-05-02; 2026-07-26: 2026-05-02 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 31 | Udaipur |  | Ready |  | 3254.51 | Completed | Completed | Completed | Completed | Bilkish Rehena | 33 | [13 empty] | 10
|  | 63/0 | 64/0 | 778.97 |  | TSE | 2026-07-15: 2026-04-24; 2026-07-22: 2026-05-03; 2026-07-23: 2026-05-27; 2026-07-26: 2026-05-29 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 32 | Sirohi |  | Ready |  | 778.97 | Completed | Completed | Completed | Completed | Taimoor Ali | 22 | [13 empty] | 10
|  | 13/0 | 14/0 | 2454.45 |  | TSE | 2026-07-15: 2026-05-11; 2026-07-22: 2026-05-14; 2026-07-23: 2026-05-16; 2026-07-26: 2026-05-17 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 33 | Sirohi |  | Ready |  | 2454.45 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 64A/0 | 65/0 | 1659.14 |  | TSE | 2026-07-15: 2026-05-13; 2026-07-22: 2026-05-16; 2026-07-23: 2026-05-18; 2026-07-26: 2026-05-19 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 34 | Sirohi |  | Ready |  | 1659.14 | Completed | Completed | Completed | Completed | Taimoor Ali | 22 | [13 empty] | 10
|  | 38/0 | 39/0 | 762.52 |  | Manual | 2026-07-15: 2026-05-23; 2026-07-22: 2026-05-24; 2026-07-23: 2026-06-10; 2026-07-26: 2026-06-12 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 35 | Sirohi |  | Ready |  | 762.52 | Completed | Completed | Completed | Completed | Jahangir Alam | 39 | [13 empty] | 16
|  | 37/0 | 38/0 | 2040.002 |  | TSE | 2026-07-15: 2026-05-29; 2026-07-22: 2026-06-02; 2026-07-23: 2026-06-03; 2026-07-26: 2026-06-06 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 36 | Sirohi |  | Ready |  | 2040.002 | Completed | Completed | Completed | Completed | Jahangir Alam | 39 | [13 empty] | 16
|  | 14/0 | 15/0 | 280 |  | Manual | 2026-07-15: 2026-06-08; 2026-07-22: 2026-06-08; 2026-07-23: 2026-06-08; 2026-07-26: 2026-06-08 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 37 | Sirohi |  | Ready |  | 280 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 61/0 | 62/0 | 795.22 |  | Manual | 2026-07-15: 2026-06-10; 2026-07-22: 2026-06-12; 2026-07-23: 2026-06-22; 2026-07-26: 2026-06-22 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 38 | Sirohi |  | Ready |  | 795.22 | Completed | Completed | Completed | Completed | Taimoor Ali | 22 | [13 empty] | 10
|  | 140/0 | 141/0 | 1152.71 |  | TSE | 2026-07-15: 2026-06-10; 2026-07-22: 2026-06-13; 2026-07-23: 2026-06-17; 2026-07-26: 2026-06-19 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 39 | Gogunda |  | Ready |  | 1152.71 | Completed | Completed | Completed | Completed | Rejaul Sekh | 30 | [13 empty] | 10
|  | 16/0 | 17/0 | 204.967 |  | Manual | 2026-07-15: 2026-06-12; 2026-07-22: 2026-06-12; 2026-07-23: 2026-06-12; 2026-07-26: 2026-06-12 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 40 | Sirohi |  | Ready |  | 204.967 | Completed | Completed | Completed | Completed | National Construction | 40 | [13 empty] | 12
|  | 141/0 | 142/0 | 720.38 |  | Manual | 2026-07-15: 2026-06-16; 2026-07-22: 2026-06-19; 2026-07-23: 2026-06-22; 2026-07-26: 2026-06-23 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 41 | Gogunda |  | Ready |  | 720.38 | Completed | Completed | Completed | Completed | Rejaul Sekh | 30 | [13 empty] | 10
|  | 60/0 | 61/0 | 1279.5 |  | TSE | 2026-07-15: 2026-06-18; 2026-07-22: 2026-06-21; 2026-07-23: 2026-06-25; 2026-07-26: 2026-06-26 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 42 | Sirohi |  | Ready |  | 1279.5 | Completed | Completed | Completed | Completed | Taimoor Ali | 22 | [13 empty] | 10
|  | 210/0 | 211/0 | 4052.317 |  | TSE | 2026-07-15: 2026-06-24; 2026-07-22: 2026-06-29; 2026-07-23: 2026-07-01; 2026-07-26: 2026-07-01 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 43 | Udaipur |  | Ready |  | 4052.317 | Completed | Completed | Completed | Completed | National Construction | 45 | [13 empty] | 15
|  | 223/0 | 224/0 | 730.94 |  | Manual | 2026-07-15: 2026-06-24; 2026-07-22: 2026-06-28; 2026-07-23: 2026-06-30; 2026-07-26: 2026-07-01 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 44 | Udaipur |  | Ready |  | 730.94 | Completed | Completed | Completed | Completed | Samirul Sekh | 35 | [13 empty] | 12
|  | 138/0 | 139/0 | 777.08 |  | Manual | 2026-07-15: 2026-06-28; 2026-07-22: 2026-07-02; 2026-07-23: 2026-07-10; 2026-07-26: 2026-07-12 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 45 | Gogunda |  | Ready |  | 777.08 | Completed | Completed | Completed | Completed | Rejaul Sekh | 30 | [13 empty] | 10
|  | 137/0 | 138/0 | 1056.753 |  | TSE | 2026-07-15: 2026-07-02; 2026-07-22: 2026-07-07; 2026-07-23: 2026-07-09; 2026-07-26: 2026-07-09 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 46 | Gogunda |  | Ready |  | 1056.753 | Completed | Completed | Completed | Completed | Rejaul Sekh | 30 | [13 empty] | 10
|  | 40/0 | 41/0 | 373.355 |  | Manual | 2026-07-15: 2026-07-06; 2026-07-22: 2026-07-06; 2026-07-23: 2026-07-15; 2026-07-26: 2026-07-17 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 47 | Sirohi |  | Ready |  | 373.355 | Completed | Completed | Completed | Completed | Taimoor Ali | 25 | [13 empty] | 10
|  | 39/0 | 40/0 | 392.674 |  | Manual | 2026-07-15: 2026-07-07; 2026-07-22: 2026-07-08; 2026-07-23: 2026-07-09; 2026-07-26: 2026-07-11 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 48 | Sirohi |  | Ready |  | 392.674 | Completed | Completed | Completed | Completed | Taimoor Ali | 25 | [13 empty] | 10
|  | 200/0 | 201/0 | 1587.001 |  | TSE | 2026-07-15: 2026-07-10; 2026-07-22: 2026-07-11; 2026-07-23: 2026-07-19; 2026-07-26: 2026-07-21 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 49 | Udaipur |  | Ready |  | 1587.001 | Completed | Completed | Completed | Completed | National Construction | 45 | [13 empty] | 15
|  | 187A/0 | 188/0 | 840 |  | Manual | 2026-07-15: 2026-07-11; 2026-07-22: 2026-07-11; 2026-07-23: 2026-08-01; 2026-07-26: 2026-08-02 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 50 | Udaipur |  | Ready |  | 840 |  |  | Completed | Completed | Samirul Sekh | 35 | [13 empty] | 12
|  | 41/0 | 42/0 | 457.079 |  | Manual | 2026-07-15: 2026-07-14; 2026-07-22: 2026-07-14; 2026-07-23: 2026-07-15; 2026-07-26: 2026-07-19 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 51 | Sirohi |  | Ready |  | 457.079 | Completed | Completed | Completed | Completed | Taimoor Ali | 25 | [13 empty] | 10
|  | 199/0 | 200/0 | 2506.34 |  | TSE | 2026-07-15: 2026-07-17; 2026-07-22: 2026-07-20; 2026-07-23: 2026-07-24; 2026-07-26: 2026-07-25 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 52 | Udaipur |  | Ready |  | 2506.34 | Completed | Completed | Completed | Completed | National Construction | 45 | [13 empty] | 15
|  | 187/0 | 187A/0 | 1204.128 |  | TSE | 2026-07-15: 2026-07-23; 2026-07-22: 2026-07-25; 2026-07-23: 2026-08-03; 2026-07-26: 2026-08-04 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 53 | Udaipur |  | Ready |  | 1204.128 |  |  | Completed | Completed | Samirul Sekh | 35 | [13 empty] | 12
|  | 59/0 | 60/0 | 361.808 |  | Manual | 2026-07-15: 2026-07-26; 2026-07-22: 2026-07-27; 2026-07-23: 2026-07-28; 2026-07-26: 2026-07-29 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 54 | Sirohi |  | Ready |  | 361.808 | Completed | Completed | Completed | Completed | Taimoor Ali | 25 | [13 empty] | 10
|  | 134/0 | 135/0 | 841.878 |  | Manual | 2026-07-15: 2026-07-27; 2026-07-22: 2026-08-01 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 55 | Gogunda |  | Ready |  | 841.878 |  |  |  |  | Rejaul Sekh | 30 | [13 empty] | 10
|  | 25/0 | 26/0 | 1168.067 |  | TSE | 2026-07-15: 2026-08-01; 2026-07-22: 2026-08-04 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 56 | Sirohi |  | Ready |  | 1168.067 |  |  |  |  | MA Traders | 26 | [13 empty] | 10
|  | 202/0 | 203/0 | 1255.763 |  | TSE | 2026-07-15: 2026-08-04; 2026-07-22: 2026-08-06; 2026-07-23: 2026-08-07 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 57 | Udaipur |  | Ready |  | 1255.763 |  |  |  |  | National Construction | 35 | [13 empty] | 13
|  | 35/0 | 35A/0 | 378.85 |  | Manual | 2026-07-15: 2026-08-04; 2026-07-22: 2026-08-05 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 58 | Sirohi |  | Ready |  | 378.85 |  |  |  |  | Afajal hossain | 26 | [13 empty] | 10
|  | 201/0 | 202/0 | 462.456 |  | Manual | 2026-07-15: 2026-08-06; 2026-07-22: 2026-08-06; 2026-07-23: 2026-08-07 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 59 | Udaipur |  | Ready |  | 462.456 |  |  |  |  | National Construction | 35 | [13 empty] | 13
|  | 26/0 | 27/0 | 764.386 |  | Manual | 2026-07-15: 2026-08-07; 2026-07-22: 2026-08-07 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 60 | Sirohi |  | Ready |  | 764.386 |  |  |  |  | MA Traders | 26 | [13 empty] | 10
|  | 135/0 | 135/2 | 831 |  | Manual | 2026-07-15: 2026-08-07 |  |  |  |  | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | FALSE |  |  |  | 61 | Gogunda |  | Ready | [6 empty] | Rejaul Sekh | 30 | [13 empty] | 10
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [14 empty] | U/C 220 KV
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
|  |  | Total | 83.152 |  | tse | [11 empty] | TA 506 |  | TA 506 | TA 506 | ta506 | TA 506 | TA 506 - DPR - 2026-08-07.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
|  | From | To | Section Length |  | tse | 2026-07-15: Start Date; 2026-07-22: End Date; 2026-07-23: Start Date; 2026-07-26: End Date |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [6 empty] | Section Length
1 |  | 60/0 | 61/0 | 4.877 |  | TSE | 2026-07-15: 2024-08-21; 2026-07-22: 2024-08-28; 2026-07-23: 2024-09-09; 2026-07-26: 2024-09-16 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.877 |  |  |  |  | Kuddus ali
2 |  | 61/0 | 62/0 | 4.568 |  | TSE | 2026-07-15: 2024-09-06; 2026-07-22: 2024-09-16; 2026-07-23: 2024-09-26; 2026-07-26: 2024-10-03 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.568 |  |  |  |  | Kuddus ali
3 |  | 62/0 | 63/0 | 4.863 |  | TSE | 2026-07-15: 2024-09-23; 2026-07-22: 2024-10-02; 2026-07-23: 2024-10-17; 2026-07-26: 2024-10-22 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.863 |  |  |  |  | Kuddus ali
4 |  | 63/0 | 64/0 | 3.711 |  | TSE | 2026-07-15: 2024-10-14; 2026-07-22: 2024-10-21; 2026-07-23: 2024-10-31; 2026-07-26: 2024-11-06 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 3.711 |  |  |  |  | Kuddus ali
5 |  | 64/0 | 65/0 | 4.918 |  | TSE | 2026-07-15: 2024-10-30; 2026-07-22: 2024-11-05; 2026-07-23: 2024-11-13; 2026-07-26: 2024-11-16 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.918 |  |  |  |  | Kuddus ali
6 |  | 59/8 | 60/0 | 3.778 |  | TSE | 2026-07-15: 2024-12-22; 2026-07-22: 2024-12-27; 2026-07-23: 2025-01-04; 2026-07-26: 2025-01-09 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 3.778 |  |  |  |  | Gopal Associate
7 |  | 59/0 | 59/8 | 3.337 |  | TSE | 2026-07-15: 2025-01-02; 2026-07-22: 2025-01-08; 2026-07-23: 2025-01-12; 2026-07-26: 2025-01-15 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 3.337 |  |  |  |  | Gopal Associate
8 |  | 65/0 | 66/0 | 4.736 |  | TSE | 2026-07-15: 2025-02-03; 2026-07-22: 2025-03-22; 2026-07-23: 2025-03-10; 2026-07-26: 2025-03-23 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.736 |  |  |  |  | MR Power
9 |  | 50/0 | 51/0 | 4.444 |  | TSE | 2026-07-15: 2025-03-12; 2026-07-22: 2025-03-23; 2026-07-23: 2025-03-17; 2026-07-26: 2025-03-24 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.444 |  |  |  |  | Gopal Associate
10 |  | 49/0 | 50/0 | 3.227 |  | TSE | 2026-07-15: 2025-02-06; 2026-07-22: 2025-02-19; 2026-07-23: 2025-05-01; 2026-07-26: 2025-05-05 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 3.227 |  |  |  |  | Gopal Associate
11 |  | 51/0 | 52/0 | 1.049 |  | TSE | 2026-07-15: 2025-04-02; 2026-07-22: 2025-04-08; 2026-07-23: 2025-04-04; 2026-07-26: 2025-04-09 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 1.049 |  |  |  |  | Gopal Associate
12 |  | 73/0 | 74/0 | 3.788 |  | TSE | 2026-07-15: 2025-06-01; 2026-07-22: 2025-06-21; 2026-07-23: 2025-09-26; 2026-07-26: 2025-09-30 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 3.788 |  |  |  |  | JPJ Construction/MC Power
13 |  | 72/0 | 73/0 | 1.628 |  | TSE | 2026-07-15: 2025-11-03; 2026-07-22: 2025-11-08; 2026-07-23: 2025-11-21; 2026-07-26: 2025-11-25 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 1.628 |  |  |  |  | JPJ Construction/MC Power
14 |  | 2/0 | 3/0 | 3.823 |  | TSE | 2026-07-15: 2025-11-13; 2026-07-22: 2025-11-18; 2026-07-23: 2025-12-30; 2026-07-26: 2026-01-14 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 3.823 |  |  |  |  | Devi Power
15 |  | 71/0 | 72/0 | 3.675 |  | TSE | 2026-07-15: 2025-11-20; 2026-07-22: 2025-11-25; 2026-07-23: 2025-11-28; 2026-07-26: 2025-11-30 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 3.675 |  |  |  |  | MC Power
16 |  | 1A/0 | 2/0 | 3.426 |  | TSE | 2026-07-15: 2025-11-21; 2026-07-22: 2025-11-28; 2026-07-23: 2025-11-28; 2026-07-26: 2025-11-30 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 3.426 |  |  |  |  | Devi Power
17 |  | 70/0 | 71/0 | 4.966 |  | TSE | 2026-07-15: 2025-12-08; 2026-07-22: 2025-12-16; 2026-07-23: 2025-12-12; 2026-07-26: 2025-12-17 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.966 |  |  |  |  | MC Power
18 |  | 56/0 | 57/0 | 0.22 |  | M | 2026-07-15: 2025-11-20; 2026-07-22: 2025-11-26; 2026-07-23: 2025-11-20; 2026-07-26: 2025-11-26 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.22 |  |  |  |  | Gopal Associate, Hotline
19 |  | 46/0 | 47/0 | 0.19908 |  | M | 2026-07-15: 2025-12-06; 2026-07-22: 2025-12-11; 2026-07-23: 2025-12-06; 2026-07-26: 2025-12-11 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.19908 |  |  |  |  | Gopal Associate, Hotline
20 |  | 69/0 | 70/0 | 0.769 |  | TSE | 2026-07-15: 2025-12-18; 2026-07-22: 2025-12-24; 2026-07-23: 2025-12-21; 2026-07-26: 2025-12-25 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.769 |  |  |  |  | MC Power
21 |  | 67/0 | 68/0 | 1.061 |  | TSE | 2026-07-15: 2025-12-26; 2026-07-22: 2025-12-28; 2026-07-23: 2026-01-06; 2026-07-26: 2026-01-08 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 1.061 |  |  |  |  | MC Power
22 |  | 68/0 | 69/0 | 0.2 |  | M | 2026-07-15: 2025-12-29; 2026-07-22: 2025-12-29; 2026-07-23: 2025-12-29; 2026-07-26: 2025-12-29 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.2 |  |  |  |  | MC Power
23 |  | 66/0 | 67/0 | 0.2078 |  | M | 2026-07-15: 2026-01-03; 2026-07-22: 2026-01-03; 2026-07-23: 2026-01-03; 2026-07-26: 2026-01-03 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.2078 |  |  |  |  | MC Power
24 |  | 3/0 | 4/0 | 0.2265 |  | M | 2026-07-15: 2026-01-10; 2026-07-22: 2026-01-16; 2026-07-23: 2026-01-11; 2026-07-26: 2026-01-16 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.2265 |  |  |  |  | Gopal Associate, Hotline
25 |  | 57/0 | 58/0 | 3.287 |  | TSE | 2026-07-15: 2026-01-19; 2026-07-22: 2026-01-24; 2026-07-23: 2026-01-29; 2026-07-26: 2026-01-31 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 3.287 |  |  |  |  | MC Power
26 |  | 10/12 | 11/0 | 4.95 |  | TSE | 2026-07-15: 2026-01-14; 2026-07-22: 2026-01-22; 2026-07-23: 2026-02-05; 2026-07-26: 2026-02-07 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.95 |  |  |  |  | Deepak Sarkar
27 |  | 47/0 | 48/0 | 4.477 |  | TSE | 2026-07-15: 2026-01-26; 2026-07-22: 2026-01-31; 2026-07-23: 2026-01-28; 2026-07-26: 2026-01-31 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.477 |  |  |  |  | Krishna-1
28 |  | 48/0 | 49/0 | 0.83 |  | TSE | 2026-07-15: 2026-01-17; 2026-07-22: 2026-01-20; 2026-07-23: 2026-01-20; 2026-07-26: 2026-01-23 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.83 |  |  |  |  | Krishna-1
29 |  | 58/0 | 59/0 | 0.2389 |  | M | 2026-07-15: 2026-01-28; 2026-07-22: 2026-01-28; 2026-07-23: 2026-01-28; 2026-07-26: 2026-01-28 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.2389 |  |  |  |  | MC Power
30 |  | 45/0 | 46/0 | 0.70146 |  | TSE | 2026-07-15: 2026-02-07; 2026-07-22: 2026-02-08; 2026-07-23: 2026-02-10; 2026-07-26: 2026-02-13 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.70146 |  |  |  |  | Krishna-1
31 |  | 44/10 | 45/0 | 0.755 |  | TSE | 2026-07-15: 2026-02-09; 2026-07-22: 2026-02-12; 2026-07-23: 2026-02-17; 2026-07-26: 2026-02-20 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.755 |  |  |  |  | Krishna-1
32 |  | 7/0 | 8/0 | 0.211 |  | M | 2026-07-15: 2026-02-20; 2026-07-22: 2026-02-26; 2026-07-23: 2026-02-20; 2026-07-26: 2026-02-26 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.211 |  |  |  |  | Gopal Associate, Hotline
33 |  | 55/0 | 56/0 | 3.318 |  | TSE | 2026-07-15: 2026-02-12; 2026-07-22: 2026-03-25; 2026-07-23: 2026-03-27; 2026-07-26: 2026-03-31 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 3.318 |  |  |  |  | MC Power
34 |  | 44/8 | 44/10 | 0.795 |  | TSE | 2026-07-15: 2026-02-16; 2026-07-22: 2026-02-19; 2026-07-23: 2026-03-10; 2026-07-26: 2026-03-13 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.795 |  |  |  |  | Krishna-1
35 |  | 44/6 | 44/8 | 0.84 |  | TSE | 2026-07-15: 2026-03-20; 2026-07-22: 2026-03-23; 2026-07-23: 2026-03-28; 2026-07-26: 2026-03-31 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.84 |  |  |  |  | Krishna-1
36 |  | 1/0 | 1A/0 | 0.09 |  | M | 2026-07-15: 2026-03-24; 2026-07-22: 2026-03-31; 2026-07-23: 2026-03-24; 2026-07-26: 2026-03-31 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.09 |  |  |  |  | Devi Power
37 |  | 44/0 | 44/6 | 2.312 |  | TSE | 2026-07-15: 2026-03-27; 2026-07-22: 2026-03-31; 2026-07-23: 2026-03-28; 2026-07-26: 2026-03-31 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.312 |  |  |  |  | Krishna-1
38 |  | Gty | 1/0 | 0.122 |  | M | 2026-07-15: 2026-03-27; 2026-07-22: 2026-03-30; 2026-07-23: 2026-03-27; 2026-07-26: 2026-03-30 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.122 |  |  |  |  | Devi Power
39 |  | 10/0 | 10/12 | 4.894 |  | TSE | 2026-07-15: 2026-03-09; 2026-07-22: 2026-03-15; 2026-07-23: 2026-04-04; 2026-07-26: 2026-04-08 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.894 |  |  |  |  | Deepak Sarkar
40 |  | 14/0 | 14A/0 | 0.381 |  | M | 2026-07-15: 2026-03-30; 2026-07-22: 2026-04-06; 2026-07-23: 2026-04-05; 2026-07-26: 2026-04-06 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.381 |  |  |  |  | Nasiruddin
41 |  | 8/7 | 9/0 | 2.456 |  | TSE | 2026-07-15: 2026-03-30; 2026-07-22: 2026-04-03; 2026-07-23: 2026-04-06; 2026-07-26: 2026-04-08 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.456 |  |  |  |  | Deepak Sarkar
42 |  | 9/0 | 10/0 | 0.233 |  | M | 2026-07-15: 2026-04-03; 2026-07-22: 2026-04-09; 2026-07-23: 2026-04-03; 2026-07-26: 2026-04-10 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.233 |  |  |  |  | Gopal Associate, Hotline
43 |  | 54/0 | 55/0 | 2.411 |  | TSE | 2026-07-15: 2026-04-03; 2026-07-22: 2026-04-09; 2026-07-23: 2026-04-08; 2026-07-26: 2026-04-11 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.411 |  |  |  |  | MC Power
44 |  | 8/0 | 8/7 | 2.861 |  | TSE | 2026-07-15: 2026-04-06; 2026-07-22: 2026-04-09; 2026-07-23: 2026-04-08; 2026-07-26: 2026-04-11 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.861 |  |  |  |  | Devi Power
45 |  | 43/0 | 44/0 | 4.8527 |  | TSE | 2026-07-15: 2026-04-08; 2026-07-22: 2026-04-15; 2026-07-23: 2026-04-16; 2026-07-26: 2026-04-18 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.8527 |  |  |  |  | Krishna-1
46 |  | 6/0 | 7/0 | 1.14 |  | TSE | 2026-07-15: 2025-03-19; 2026-07-22: 2026-04-15; 2026-07-23: 2026-03-24; 2026-07-26: 2026-04-30 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 1.14 |  |  |  |  | Deepak Sarkar / Nasiruddin
47 |  | 53/0 | 54/0 | 3.69 |  | TSE | 2026-07-15: 2025-04-18; 2026-07-22: 2026-04-26; 2026-07-23: 2026-04-30; 2026-07-26: 2026-04-30 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 3.69 |  |  |  |  | MC Power
48 |  | 5/0 | 6/0 | 0.246 |  | M | 2026-07-15: 2026-04-24; 2026-07-22: 2026-04-30; 2026-07-23: 2026-04-24; 2026-07-26: 2026-04-30 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.246 |  |  |  |  | Gopal Associate, Hotline
49 |  | 14A/0 | 15/0 | 1.192 |  | TSE | 2026-07-15: 2026-04-25; 2026-07-22: 2026-05-04; 2026-07-23: 2026-05-02; 2026-07-26: 2026-05-04 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 1.192 |  |  |  |  | Nasiruddin
50 |  | 13/0 | 14/0 | 2.078 |  | TSE | 2026-07-15: 2026-03-30; 2026-07-22: 2026-04-04; 2026-07-23: 2026-05-12; 2026-07-26: 2026-05-13 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.078 |  |  |  |  | Nasiruddin
51 |  | 52/0 | 53/0 | 4.534 |  | TSE | 2026-07-15: 2026-05-10; 2026-07-22: 2026-05-16; 2026-07-23: 2026-05-18; 2026-07-26: 2026-05-22 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.534 |  |  |  |  | MC Power
52 |  | 11A/0 | 12/0 | 4.11 |  | TSE | 2026-07-15: 2026-05-18; 2026-07-22: 2026-05-16; 2026-07-23: 2026-05-27; 2026-07-26: 2026-05-29 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 4.11 |  |  |  |  | Nasiruddin
53 |  | 12/0 | 13/0 | 0.2119 |  | M | 2026-07-15: 2026-05-26; 2026-07-22: 2026-05-31; 2026-07-23: 2026-05-26; 2026-07-26: 2026-05-31 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.2119 |  |  |  |  | Gopal Associate, Hotline
54 |  | 23/0 | 24/0 | 0.2222 |  | M | 2026-07-15: 2026-06-09; 2026-07-22: 2026-06-16; 2026-07-23: 2026-06-09; 2026-07-26: 2026-06-16 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.2222 |  |  |  |  | Gopal Associate, Hotline
55 |  | 24/0 | 25/0 | 0.434 |  | M | 2026-07-15: 2026-06-21; 2026-07-22: 2026-06-26; 2026-07-23: 2026-06-21; 2026-07-26: 2026-06-26 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.434 |  |  |  |  | MC Power
56 |  | 11/0 | 11A/0 | 2.238 |  | TSE | 2026-07-15: 2026-06-17; 2026-07-22: 2026-06-22; 2026-07-23: 2026-06-23; 2026-07-26: 2026-06-26 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.238 |  |  |  |  | Nasiruddin
57 |  | 27/0 | 27/7 | 2.8104 |  | TSE | 2026-07-15: 2026-06-22; 2026-07-22: 2026-06-29; 2026-07-23: 2026-07-01; 2026-07-26: 2026-07-05 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.8104 |  |  |  |  | Mohammad Construction / Furkhan
58 |  | 22/8 | 23/0 | 2.3018 |  | TSE | 2026-07-15: 2026-06-30; 2026-07-22: 2026-07-04; 2026-07-23: 2026-07-05; 2026-07-26: 2026-07-09 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.3018 |  |  |  |  | MC Power
59 |  | 29/0 | 30/0 | 2.0107 |  | TSE | 2026-07-15: 2026-06-23; 2026-07-22: 2026-06-29; 2026-07-23: 2026-07-02; 2026-07-26: 2026-07-06 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.0107 |  |  |  |  | Jamera Bibi
60 |  | 15/0 | 16/0 | 0.8179 |  | TSE | 2026-07-15: 2026-07-04; 2026-07-22: 2026-07-06; 2026-07-23: 2026-07-11; 2026-07-26: 2026-07-15 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.8179 |  |  |  |  | Nasiruddin
61 |  | 4/0 | 5/0 | 1.8731 |  | TSE | 2026-07-15: 2026-07-17; 2026-07-22: 2026-07-19; 2026-07-23: 2026-07-20; 2026-07-26: 2026-07-21 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 1.8731 |  |  |  |  | Nasiruddin
63 |  | 27/7 | 28/0 | 2.3869 |  | TSE | 2026-07-15: 2026-07-11; 2026-07-22: 2026-07-16; 2026-07-23: 2026-07-20; 2026-07-26: 2026-07-23 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.3869 |  |  |  |  | Mohammad Construction / Furkhan
64 |  | 22/0 | 22/8 | 3.1771 |  | TSE | 2026-07-15: 2026-08-21; 2026-07-22: 2026-07-26; 2026-07-23: 2026-07-23; 2026-07-26: 2026-07-27 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 3.1771 |  |  |  |  | MC Power
65 |  | 30/0 | 31/0 | 2.7193 |  | TSE | 2026-07-15: 2026-07-11; 2026-07-22: 2026-07-22; 2026-07-23: 2026-07-26; 2026-07-26: 2026-07-28 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.7193 |  |  |  |  | Jamera Bibi
66 |  | 31/0 | 32/0 | 1.0825 |  | TSE | 2026-07-15: Platina P/out |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [13 empty] | Jamera Bibi
67 |  | 16/0 | 17/0 | 2.3362 |  | TSE | 2026-07-15: 2026-07-11; 2026-07-22: 2026-07-15; 2026-07-23: 2026-07-28 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.3362 |  |  |  |  | Nasiruddin
68 |  | 28/0 | 29/0 | 3.6391 |  | TSE | 2026-07-15: 2026-07-27 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [13 empty] | Mohammad Construction / Furkhan
69 |  | 17/0 | 18/0 | 2.451 |  | TSE | 2026-07-15: 2026-07-27; 2026-07-23: 2026-07-29 |  |  |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [13 empty] | Nasiruddin
70 |  | 25/0 | 26/0 | 1.97 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [13 empty] | MC Power
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
TOTAL |  |  |  | 158.3855 |  | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [6 empty] | 149.2429
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
|  |  |  | S. Len-P.O. |  | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [6 empty] | 9.1426
|  |  |  | P/O-F/S |  | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [6 empty] | 2.3362
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [6 empty] | 9.7195
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
1 |  | 20/0 | 21/0 | 1.48 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [13 empty] | Gang Not Allocated
2 |  | 21/0 | 22/0 | 4.58 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [13 empty] | Gang Not Allocated
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
4 |  | 26/0 | 27/0 | 3.66 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [13 empty] | Gang Not Allocated
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
1 |  | 32/0 | 33/0 | 2.075 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.075 |  |  |  |  | Tata Projects Limited
2 |  | 33/0 | 34/0 | 0.672 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.672 |  |  |  |  | Tata Projects Limited
3 |  | 34/0 | 35/0 | 2.048 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.048 |  |  |  |  | Tata Projects Limited
4 |  | 35/0 | 35/2 | 0.758 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.758 |  |  |  |  | Tata Projects Limited
5 |  | 35/2 | 35/3 | 0.522 |  | M | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.522 |  |  |  |  | Tata Projects Limited
6 |  | 35/3 | 36/0 | 1.183 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 1.183 |  |  |  |  | Tata Projects Limited
7 |  | 36/0 | 37/0 | 1.8845 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 1.8845 |  |  |  |  | Tata Projects Limited
8 |  | 37/0 | 38/0 | 1.64 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 1.64 |  |  |  |  | Tata Projects Limited
9 |  | 38/0 | 39/0 | 2.101 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.101 |  |  |  |  | Tata Projects Limited
10 |  | 39/0 | 40/0 | 0.735 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 0.735 |  |  |  |  | Tata Projects Limited
11 |  | 40/0 | 41/0 | 1.66 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 1.66 |  |  |  |  | Tata Projects Limited
12 |  | 41/0 | 42/0 | 1.1709 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 1.1709 |  |  |  |  | Tata Projects Limited
13 |  | 42/0 | 43/0 | 2.667 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [8 empty] | 2.667 |  |  |  |  | Tata Projects Limited
14 |  | 18/0 | 19/0 | 1.91 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [13 empty] | Tata Projects Limited
15 |  | 19/0 | 20/0 | 2.26 |  | TSE | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | FALSE | [13 empty] | Tata Projects Limited
|  |  |  | 23.2864 |  | tse | [11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-07-30.xlsx | Stringing | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [6 empty] | 19.1164
1 |  | 7/0 | DB+0 | PS |  | tse | 2026-07-15: 2026-08-02; 2026-07-26: 2026-08-07 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Completed | Rajeshwar | [15 empty] | 400 KV LOOP OUT
2 |  | 46/0 | DD+3 | FS |  | tse | 2026-07-15: 2026-08-02 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | RCC WIP | Nav Durga Traders | [15 empty] | 400 KV LOOP OUT
3 |  | 33/0 | DD+0 | PS |  | tse | 2026-07-15: 2026-08-08 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Pit Marking Completed | Rajeshwar | [15 empty] | 400 KV LOOP OUT
[6 empty] | tse | [11 empty] | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [27 empty] | 220 TM Chapra-Amnour
[6 empty] | tse | [11 empty] | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
1 |  | 143/0 | DC+3 | FS |  | tse | 2026-07-15: 2026-07-14 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | ROW & Material Shifting | Anmol | [15 empty] | 220 SZ Chapra-Gopalganj | 7
2 |  | 74/0 | DD+3 | FS |  | tse | 2026-07-15: 2026-07-09 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Excavation WIP | Dharmendra Mishra | [16 empty] | 8
3 |  | 70/2 | DA+3 1MRC | FS |  | tse | 2026-07-15: 2026-07-13 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | 03 Pit RCC Done | MAA | [16 empty] | 8
4 |  | 61/2 | DA+9 | FS |  | tse | 2026-07-15: 2026-07-23 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Material & Gang Shifting WIP | Shakti | [16 empty] | 8
[6 empty] | tse | [11 empty] | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [27 empty] | ERECTION
SR.NO. |  | LOC. NO. | T.O.T | D.O.S |  | tse | 2026-07-15: D.O.C; 2026-07-26: MP |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [11 empty] | GANG | [15 empty] | T/L Name | Remarks
1 |  | 151/2 | DA+6 | 2026-07-30 |  | tse | 2026-07-15: 2026-08-02 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [11 empty] | Sonakshi Mobile | [15 empty] | 220 SZ Chapra-Gopalganj | Completed
2 |  | 106/0 | DD+9 | 2026-07-28 |  | tse | 2026-07-15: 2026-08-02 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [11 empty] | Sanjeev Kumar | [15 empty] | 220 SZ Chapra-Gopalganj | Completed
3 |  | 152/3 | DA+6 | 2026-08-02 |  | tse | 2026-07-15: 2026-08-05 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [11 empty] | Sonakshi Mobile | [15 empty] | 220 SZ Chapra-Gopalganj | Completed
4 |  | 104/5 | DA+3 | 2026-08-02 |  | tse | 2026-07-15: 2026-08-05 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [11 empty] | Sanjeev Kumar | [15 empty] | 220 SZ Chapra-Gopalganj | Completed
5 |  | 132/5 | DA+3 | 2026-08-02 |  | tse | 2026-07-15: 2026-08-06 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [11 empty] | Asfak Ahmad | [15 empty] | 220 SZ Chapra-Gopalganj | Completed
6 |  | 104/4 | DA+0 | 2026-08-05 |  | tse | 2026-07-15: 2026-08-07 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [11 empty] | Sanjeev Kumar | [15 empty] | 220 SZ Chapra-Gopalganj | Completed
7 |  | 3/0 | 2TNMD+0 | 2026-08-02 |  | tse | 2026-07-26: 17 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [11 empty] | Yashoda Devi | [15 empty] | 220 TM Chapra-Amnour | 2nd Section WIP
8 |  | 113/1 | DA+6 | 2026-08-02 |  | tse | 2026-07-26: 17 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [11 empty] | Kumkum Devi | [15 empty] | 220 SZ Chapra-Gopalganj | 2nd Section WIP
9 |  | 150/0 | DD+0 | 2026-08-06 |  | tse | 2026-07-26: 18 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [11 empty] | Sonakshi Mobile | [15 empty] | 220 SZ Chapra-Gopalganj | Bottom Section WIP
10 |  | 8/0 | DD+0 | 2026-08-06 |  | tse | 2026-07-26: 26 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [11 empty] | Rang | [15 empty] | 400 KV LOOP OUT | 1st Section WIP
11 |  | 132/3 | DA+6 | 2026-08-06 |  | tse | 2026-07-26: 17 |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [11 empty] | Asfak Ahmad | [15 empty] | 220 SZ Chapra-Gopalganj | 1st Section WIP
[6 empty] | tse | [11 empty] | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [27 empty] | Stringing
SR.NO. |  | FROM | TO | Section (Km) |  | tse | 2026-07-15: D.O.S; 2026-07-26: D.O.C |  |  |  |  | TB 412 |  | TB 412 | TB 412 | tb412 | TB 412 | TB 412 - DPR - 2026-08-07.xlsx | WIP | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | Remarks | GANG | [15 empty] | T/L Name | MP
1 |  | Hydro GTY | Existing Tower-1 | 58.79 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
2 |  | Existing Tower-1 | Exting Tower-2 | 149.12 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
3 |  | Exting Tower-2 | Exting Tower-3 | 128.1 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
4 |  | Exting Tower-3 | Exting Tower-4 | 252.72 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
5 |  | Exting Tower-4 | Exting Tower-5 | 146.74 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
6 |  | Exting Tower-5 | Exting Tapping Tower-6 | 190.05 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
7 |  | Exting Tapping Tower-6 | Exting Tower-7 | 84.7 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
8 |  | Exiting Tower-7 | SC-5 | 122.5 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
9 |  | SC-5 | SC-4 | 259.5 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
10 |  | SC-4 | Sc-3 | 256.6 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
11 |  | Sc-3 | SC-2 | 278 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
12 |  | SC-2 | SC-1 | 201.9 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
13 |  | SC-1 | 1/0 | 62.76 |  | tse | [11 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
|  | CPP | 1/0 | 48 |  | tse |  | C | 2026-06-29 | 2026-06-29 | 30-07-026 | 2026-07-01 | [5 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | [18 empty] | C |  |  | C |  |  | C
14 |  | 1/0 | 2/0 | 226.7 |  | tse |  | C | 2026-06-29 | 2026-06-29 | 30-07-026 | 2026-07-01 | [5 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | [18 empty] | C |  |  | C |  |  | C
15 |  | 2/0 | 2/1 | 234.6 |  | tse |  | C | 2026-06-27 | 2026-06-28 | 30-07-026 | 2026-07-01 | [5 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | [18 empty] | C |  |  | C |  |  | C
16 |  | 2/1 | 3/0 | 285.2 |  | tse |  | C | 2026-06-27 | 2026-06-28 | 30-07-026 | 2026-07-01 | [5 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | [18 empty] | C |  |  | C |  |  | C
17 |  | 3/0 | 3/1 | 235.8 |  | tse |  | C | 2026-05-07 | 2026-05-08 | 2026-05-08 | 2026-05-09 |  |  | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sammirul Sekh | [17 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
18 |  | 3/1 | 4/0 | 197.4 |  | tse |  | C | 2026-05-07 | 2026-05-08 | 2026-05-08 | 2026-05-09 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sammirul Sekh | [17 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
19 |  | 4/0 | 4/1 | 43.6 |  | tse |  | C | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sammirul Sekh | [17 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
20 |  | 4/1 | 4/2 | 52 |  | tse |  | C | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | [18 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
21 |  | 4/2 | 5/0 | 47.1 |  | tse |  | C | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
22 |  | 5/0 | 6/0 | 286.4 |  | tse |  | C | 2026-03-25 | 2026-03-25 | 2026-04-01 | 2026-04-02 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
23 |  | 6/0 | 6/1 | 312 |  | tse |  | C | 2026-03-26 | 2026-03-27 | 2026-03-30 | 2026-03-30 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
24 |  | 6/1 | 6/2 | 333 |  | tse |  | C | 2026-03-26 | 2026-03-27 | 2026-03-30 | 2026-03-30 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
25 |  | 6/2 | 6/3 | 297 |  | tse |  | C | 2026-03-26 | 2026-03-27 | 2026-03-30 | 2026-03-30 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
26 |  | 6/3 | 6/4 | 238.5 |  | tse |  | C | 2026-03-26 | 2026-03-27 | 2026-03-30 | 2026-03-30 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
27 |  | 6/4 | 7/0 | 320.8 |  | tse |  | C | 2026-03-26 | 2026-03-27 | 2026-03-30 | 2026-03-30 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
28 |  | 7/0 | 8/0 | 278.1 |  | tse |  | C | 2026-03-23 | 2026-03-24 | 2026-03-29 | 2026-03-29 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
29 |  | 8/0 | 9/0 | 386 |  | tse |  | C | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sawariya seth | [17 empty] | C |  |  | C | 2026-05-14 | 2026-05-14 | C | 2026-05-15 | 2026-05-15
30 |  | 9/0 | 10/0 | 259.9 |  | tse |  | C | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | [5 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sawariya seth | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
31 |  | 10/0 | 11/0 | 215.1 |  | tse | 2026-07-11: C; 2026-07-23: 2026-05-18; 2026-07-26: 2026-05-19 | C |  |  |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | [18 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
32 |  | 11/0 | 12/0 | 316.1 |  | tse |  | C | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sammirul Sekh | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
33 |  | 12/0 | 12/1 | 274 |  | tse |  | C | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | [5 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sawariya seth | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
34 |  | 12/1 | 13/0 | 293.3 |  | tse |  | C | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 |  |  | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sawariya seth | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
35 |  | 13/0 | 13/1 | 48 |  | tse |  | C | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sawariya seth | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
36 |  | 13/1 | 13/2 | 58.7 |  | tse |  | C | 2026-03-12 | 2026-03-12 | 2026-03-14 | 2026-03-14 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sawariya seth | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
37 |  | 13/2 | 14/0 | 70.1 |  | tse |  | C | 2026-03-15 | 2026-03-15 | 2026-03-15 | 2026-03-15 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sawariya seth | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
38 |  | 14/0 | 15/0 | 220.7 |  | tse |  | C | 2026-05-14 | 2026-05-14 | 2026-05-15 | 2026-05-15 |  |  | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sammirul Sekh | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
39 |  | 15/0 | 15/1 | 263 |  | tse |  | C | 2026-03-07 | 2026-03-09 | 2026-03-08 | 2026-03-09 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sawariya seth | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
40 |  | 15/1 | 15/2 | 251.6 |  | tse |  | C | 2026-03-07 | 2026-03-09 | 2026-03-08 | 2026-03-09 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sawariya seth | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
41 |  | 15/2 | 15/3 | 271.8 |  | tse |  | C | 2026-03-07 | 2026-03-09 | 2026-03-08 | 2026-03-09 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sawariya seth | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
42 |  | 15/3 | 16/0 | 261 |  | tse |  | C | 2026-03-07 | 2026-03-09 | 2026-03-08 | 2026-03-09 |  | C | C | C |  | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Sawariya seth | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
43 |  | 16/0 | 16/1 | 37.4 |  | tse |  | C | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | [5 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | SK Basirul | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
44 |  | 16/1 | 16/2 | 71 |  | tse |  | C | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 | [5 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | SK Basirul | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
45 |  | 16/2 | 17/0 | 37.5 |  | tse |  | C | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | [5 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | SK Basirul | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
46 |  | 17/0 | 18/0 | 165.2 |  | tse |  | C | 2026-03-02 | 2026-03-03 | 2026-03-02 | 2026-03-03 | [5 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | SK Basirul | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
47 |  | 18/0 | Gantry | 40 |  | tse |  | C | 2026-02-20 | 2026-02-21 | 2026-02-20 | 2026-02-21 | [5 empty] | TB 501 | 132kV | TB 501 - 132kV | TB 501 - 132kV | tb501132kv | TB 501 - 132kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | SK Basirul | [17 empty] | C |  |  | C | 2026-05-16 | 2026-05-18 | C | 2026-05-19 | 2026-05-19
1 |  | Gnty | 0/0 | 47 |  | tse |  | C | 2026-01-31 | 2026-02-02 | 2026-01-31 | 2026-02-02 | [5 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Harshvivek | [17 empty] | C |  |  | C | 2026-05-05 | 2026-05-07 |  | 2026-05-08 | 2026-05-08 |  | C
2 |  | 0/0 | 1/0 | 392.7 |  | tse |  | C | 2025-05-19 | 2025-05-24 | 2025-05-26 | 2025-05-28 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-05 | 2026-05-07 |  | 2026-05-08 | 2026-05-08 |  | C
3 |  | 1/0 | 1A/0 | 1037.32 |  | tse |  | C | 2025-05-19 | 2025-05-24 | 2025-05-26 | 2025-05-28 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-05 | 2026-05-07 |  | 2026-05-08 | 2026-05-08 |  | C
4 |  | 1A/0 | 1A/2 | 609 |  | tse |  | C | 2025-06-29 | 2025-06-29 | 2025-06-30 | 2025-06-30 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-05 | 2026-05-07 |  | 2026-05-08 | 2026-05-08 |  | C
5 |  | 1A/2 | 1B/0 | 232.098 |  | tse |  | C | 2025-06-29 | 2025-06-29 | 2025-06-29 | 2025-06-29 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-05 | 2026-05-07 |  | 2026-05-08 | 2026-05-08 |  | C
6 |  | 1B/0 | 1C/0 | 205.5 |  | tse |  | C | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-05 | 2026-05-07 |  | 2026-05-08 | 2026-05-08 |  | C
7 |  | 1C/0 | 1D/0 | 729.1 |  | tse |  | C | 2026-04-11 | 2026-04-13 | 2026-04-14 | 2026-04-14 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-05 | 2026-05-07 |  | 2026-05-08 | 2026-05-08 |  | C
8 |  | 1D/0 | 1E/0 | 699.92 |  | tse |  | C | 2025-08-01 | 2025-08-02 | 2025-08-04 | 2025-08-07 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Dilruba Bibi | [17 empty] | C |  |  | C | 2026-05-05 | 2026-05-07 |  | 2026-05-08 | 2026-05-08 |  | C
9 |  | 1E/0 | 2/0 | 356.7 |  | tse |  | C | 2025-07-26 | 2025-07-29 | 2025-07-31 | 2025-08-03 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Dilruba Bibi | [17 empty] | C |  |  | C | 2026-05-05 | 2026-05-07 |  | 2026-05-08 | 2026-05-08 |  | C
10 |  | 2/0 | 3/0 | 174.205 |  | tse |  | C | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-05 | 2026-05-07 |  | 2026-05-08 | 2026-05-08 |  | C
11 |  | 3/0 | 4/0 | 229.73 |  | tse |  | C | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-09 | 2026-05-10 |  | 2026-05-10 | 2026-05-11 |  | C
12 |  | 4/0 | 4/5 | 1733 |  | tse |  | C | 2025-07-11 | 2025-07-14 | 2025-07-16 | 2025-07-18 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Dilruba Bibi | [17 empty] | C |  |  | C | 2026-05-09 | 2026-05-10 |  | 2026-05-10 | 2026-05-11 |  | C
13 |  | 4/5 | 4/6 | 349 |  | tse |  | C | 2025-07-11 | 2025-07-14 | 2025-07-16 | 2025-07-18 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Dilruba Bibi | [17 empty] | C |  |  | C | 2026-05-09 | 2026-05-10 |  | 2026-05-10 | 2026-05-11 |  | C
14 |  | 4/6 | 4/7 | 360 |  | tse |  | C | 2026-06-27 | 2026-06-27 | 2026-07-28 | 2025-07-28 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | [18 empty] | C |  |  | C | 2026-05-09 | 2026-05-10 |  | 2026-05-10 | 2026-05-11 |  | C
15 |  | 4/7 | 4/8 | 460 |  | tse |  | C | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-26 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | [18 empty] | C |  |  | C | 2026-05-09 | 2026-05-10 |  | 2026-05-10 | 2026-05-11 |  | C
16 |  | 4/8 | 4/9 | 230 |  | tse |  | C | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-26 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | [18 empty] | C |  |  | C | 2026-05-09 | 2026-05-10 |  | 2026-05-10 | 2026-05-11 |  | C
17 |  | 4/9 | 4/10 | 371.51 |  | tse |  | C | 2025-08-22 | 2025-08-25 | 2025-09-19 | 2025-09-21 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-09 | 2026-05-10 |  | 2026-05-10 | 2026-05-11 |  | C
18 |  | 4/10 | 4/11 | 332.471 |  | tse |  | C | 2025-08-22 | 2025-08-25 | 2025-09-19 | 2025-09-21 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-05-09 | 2026-05-10 |  | 2026-05-10 | 2026-05-11 |  | C
19 |  | 4/11 | 4/15 | 1335 |  | tse |  | C | 2025-08-22 | 2025-08-25 | 2025-09-10 | 2025-09-13 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-24 | 2026-03-28 |  | 2026-03-28 | 2026-03-28 |  | C
20 |  | 4/15 | 4/16 | 415 |  | tse |  | C | 2025-08-22 | 2025-08-25 | 2025-08-31 | 2025-09-03 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-24 | 2026-03-28 |  | 2026-03-28 | 2026-03-28 |  | C
21 |  | 4/16 | 4/17 | 237 |  | tse |  | C | 2025-08-22 | 2025-08-25 | 2025-09-16 | 2025-09-17 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-24 | 2026-03-28 |  | 2026-03-28 | 2026-03-28 |  | C
22 |  | 4/17 | 5/0 | 188.5 |  | tse |  | C | 2025-08-28 | 2025-08-31 | 2025-09-07 | 2025-09-10 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-24 | 2026-03-28 |  | 2026-03-28 | 2026-03-28 |  | C
23 |  | 5/0 | 5/1 | 383 |  | tse |  | C | 2025-08-28 | 2025-08-31 | 2025-09-08 | 2025-09-11 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-24 | 2026-03-28 |  | 2026-03-28 | 2026-03-28 |  | C
24 |  | 5/1 | 5A/0 | 952 |  | tse |  | C | 2025-10-16 | 2025-10-16 | 2025-10-17 | 2025-10-19 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-24 | 2026-03-28 |  | 2026-03-28 | 2026-03-28 |  | C
25 |  | 5A/0 | 5A/1 | 342 |  | tse |  | C | 2026-02-10 | 2026-02-12 | 2026-02-13 | 2026-02-14 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-24 | 2026-03-28 |  | 2026-03-28 | 2026-03-28 |  | C
26 |  | 5A/1 | 5A/2 | 264 |  | tse |  | C | 2026-02-09 | 2026-02-10 | 2026-02-14 | 2026-02-15 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-24 | 2026-03-28 |  | 2026-03-28 | 2026-03-28 |  | C
27 |  | 5A/2 | 5B/0 | 282.74 |  | tse |  | C | 2026-02-06 | 2026-02-09 | 2026-02-09 | 2026-02-10 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-24 | 2026-03-28 |  | 2026-03-28 | 2026-03-28 |  | C
28 |  | 5B/0 | 6/0 | 462.1 |  | tse |  | C | 2026-01-28 | 2026-02-04 | 2026-02-07 | 2026-02-09 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-24 | 2026-03-28 |  | 2026-03-28 | 2026-03-28 |  | C
29 |  | 6/0 | 7/0 | 318.04 |  | tse |  | C | 2026-01-28 | 2026-02-04 | 2026-02-04 | 2026-02-06 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-19 | 2026-03-22 |  | 2026-03-23 | 2026-03-23 |  | C
30 |  | 7/0 | 8/0 | 1152.1 |  | tse |  | C | 2025-09-22 | 2025-09-24 | 2025-09-25 | 2025-09-27 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-19 | 2026-03-22 |  | 2026-03-23 | 2026-03-23 |  | C
31 |  | 8/0 | 8A/0 | 170.7 |  | tse |  | C | 2025-10-01 | 2025-10-01 | 2025-10-04 | 2025-10-05 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-19 | 2026-03-22 |  | 2026-03-23 | 2026-03-23 |  | C
32 |  | 8A/0 | 8B/0 | 336.5 |  | tse |  | C | 2025-10-03 | 2025-10-03 | 2025-10-08 | 2025-10-09 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-19 | 2026-03-22 |  | 2026-03-23 | 2026-03-23 |  | C
33 |  | 8B/0 | 8C/0 | 900.14 |  | tse |  | C | 2025-10-04 | 2025-10-04 | 2025-10-08 | 2025-10-09 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-19 | 2026-03-22 |  | 2026-03-23 | 2026-03-23 |  | C
34 |  | 8C/0 | 8D/0 | 318.76 |  | tse |  | C | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-14 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-19 | 2026-03-22 |  | 2026-03-23 | 2026-03-23 |  | C
35 |  | 8D/0 | 8D/1 | 436.1 |  | tse |  | C | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-19 | 2026-03-22 |  | 2026-03-23 | 2026-03-23 |  | C
36 |  | 8D/1 | 8D/3 | 657.08 |  | tse |  | C | 2026-03-02 | 2026-03-05 | 2026-03-08 | 2026-03-09 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-19 | 2026-03-22 |  | 2026-03-23 | 2026-03-23 |  | C
37 |  | 8D/3 | 8D/4 | 459 |  | tse |  | C | 2026-02-15 | 2026-02-19 | 2026-02-27 | 2026-02-27 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-19 | 2026-03-22 |  | 2026-03-23 | 2026-03-23 |  | C
38 |  | 8D/4 | 8D/5 | 195 |  | tse |  | C | 2026-02-15 | 2026-02-19 | 2026-02-28 | 2026-02-28 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-11 | 2026-03-16 |  | 2026-03-17 | 2026-03-18 |  | C
39 |  | 8D/5 | 8D/6 | 295 |  | tse |  | C | 2026-02-15 | 2026-02-19 | 2026-03-17 | 2026-03-17 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-11 | 2026-03-16 |  | 2026-03-17 | 2026-03-18 |  | C
40 |  | 8D/6 | 8E/0 | 380.25 |  | tse |  | C | 2026-02-15 | 2026-02-19 | 2026-03-16 | 2026-03-16 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-11 | 2026-03-16 |  | 2026-03-17 | 2026-03-18 |  | C
41 |  | 8E/0 | 8E/1 | 428 |  | tse |  | C | 2026-02-15 | 2026-02-19 | 2026-03-15 | 2026-03-15 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-11 | 2026-03-16 |  | 2026-03-17 | 2026-03-18 |  | C
42 |  | 8E/1 | 8E/2 | 419 |  | tse |  | C | 2025-11-11 | 2025-11-14 | 2025-11-15 | 2025-11-18 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-11 | 2026-03-16 |  | 2026-03-17 | 2026-03-18 |  | C
43 |  | 8E/2 | 8E/5 | 900 |  | tse |  | C | 2025-11-11 | 2025-11-14 | 2025-11-15 | 2025-11-18 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-11 | 2026-03-16 |  | 2026-03-17 | 2026-03-18 |  | C
44 |  | 8E/5 | 8E/6 | 343.87 |  | tse |  | C | 2025-11-11 | 2025-11-14 | 2025-11-15 | 2025-11-18 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-11 | 2026-03-16 |  | 2026-03-17 | 2026-03-18 |  | C
45 |  | 8E/6 | 8E/7 | 499.13 |  | tse |  | C | 2026-02-20 | 2026-02-22 | 2026-02-24 | 2026-02-24 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-11 | 2026-03-16 |  | 2026-03-17 | 2026-03-18 |  | C
46 |  | 8E/7 | 8E/8 | 434 |  | tse |  | C | 2026-02-20 | 2026-02-23 | 2026-02-25 | 2026-02-25 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-11 | 2026-03-16 |  | 2026-03-17 | 2026-03-18 |  | C
47 |  | 8E/8 | 8E/11 | 919 |  | tse |  | C | 2025-11-17 | 2025-11-19 | 2025-11-22 | 2025-11-23 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2026-03-11 | 2026-03-16 |  | 2026-03-17 | 2026-03-18 |  | C
48 |  | 8E/11 | 8E/12 | 489 |  | tse |  | C | 2025-11-05 | 2025-11-09 | 2025-11-11 | 2025-11-13 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-17 | 2025-12-20 |  | 2025-12-21 | 2025-12-21 |  | C
49 |  | 8E/12 | AP-9 | 382.48 |  | tse |  | C | 2025-11-05 | 2025-11-09 | 2025-11-09 | 2025-11-11 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-17 | 2025-12-20 |  | 2025-12-21 | 2025-12-21 |  | C
50 |  | AP-9 | 9/4 | 1250.32 |  | tse |  | C | 2025-11-05 | 2025-11-09 | 2025-11-09 | 2025-11-11 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-17 | 2025-12-20 |  | 2025-12-21 | 2025-12-21 |  | C
51 |  | 9/4 | 9/5 | 246.8 |  | tse |  | C | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-17 | 2025-12-20 |  | 2025-12-21 | 2025-12-21 |  | C
52 |  | 9/5 | AP-10 | 1697.3 |  | tse |  | C | 2025-09-26 | 2025-09-30 | 2025-10-26 | 2025-10-27 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-17 | 2025-12-20 |  | 2025-12-21 | 2025-12-21 |  | C
53 |  | AP-10 | AP-11 | 1600.078 |  | tse |  | C | 2025-10-10 | 2025-10-12 | 2025-10-12 | 2025-10-14 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-26 | 2025-12-27 |  | 2025-12-28 | 2025-12-28 |  | C
54 |  | AP-11 | AP-12 | 525.89 |  | tse |  | C | 2025-10-10 | 2025-10-12 | 2025-10-12 | 2025-10-14 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-26 | 2025-12-27 |  | 2025-12-28 | 2025-12-28 |  | C
55 |  | AP-12 | AP-13 | 356.279 |  | tse |  | C | 2025-10-01 | 2025-10-01 | 2025-10-08 | 2025-10-10 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-26 | 2025-12-27 |  | 2025-12-28 | 2025-12-28 |  | C
56 |  | AP-13 | AP-14 | 667.59 |  | tse |  | C | 2025-12-18 | 2025-12-20 | 2025-12-24 | 2025-12-27 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-26 | 2025-12-27 |  | 2025-12-28 | 2025-12-28 |  | C
57 |  | AP-14 | 14/1 | 362 |  | tse |  | C | 2025-12-18 | 2025-12-20 | 2025-12-24 | 2025-12-27 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-26 | 2025-12-27 |  | 2025-12-28 | 2025-12-28 |  | C
58 |  | 14/1 | 14/3 | 752 |  | tse |  | C | 2025-12-18 | 2025-12-20 | 2025-12-21 | 2025-12-27 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-26 | 2025-12-27 |  | 2025-12-28 | 2025-12-28 |  | C
59 |  | 14/3 | AP-15 | 2536.2 |  | tse |  | C | 2025-12-13 | 2025-12-15 | 2025-12-22 | 2025-12-23 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-22 | 2025-12-24 |  | 2025-12-25 | 2025-12-25 |  | C
60 |  | AP-15 | AP-16 | 3422.45 |  | tse |  | C | 2025-06-17 | 2025-06-25 | 2025-06-20 | 2025-06-29 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Nemchand | [17 empty] | C |  |  | C | 2025-09-28 | 2025-09-30 |  | 2025-10-01 | 2025-10-02 |  | C
61 |  | AP-16 | AP-17 | 1307.65 |  | tse |  | C | 2025-06-30 | 2025-07-06 | 2025-07-08 | 2025-07-11 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-09-30 | 2025-10-02 |  | 2025-10-03 | 2025-10-04 |  | C
62 |  | AP-17 | AP-18 | 1435.97 |  | tse |  | C | 2025-06-30 | 2025-07-06 | 2025-07-08 | 2025-07-11 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-10-02 | 2025-10-04 |  | 2025-10-05 | 2025-10-07 |  | C
63 |  | AP-18 | AP-19 | 4210.131 |  | tse |  | C | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-18 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-10-08 | 2025-10-09 |  | 2025-10-10 | 2025-10-11 |  | C
64 |  | AP-19 | AP-20 | 1946.55 |  | tse |  | C | 2025-07-20 | 2025-07-21 | 2025-07-21 | 2025-07-22 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-07 | 2025-12-08 |  | 2025-12-08 | 2025-12-09 |  | C
65 |  | AP-20 | AP-21 | 2994.77 |  | tse |  | C | 2025-07-22 | 2025-07-24 | 2025-07-25 | 2025-07-27 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-07 | 2025-12-08 |  | 2025-12-08 | 2025-12-09 |  | C
66 |  | AP-21 | AP-22 | 4974.78 |  | tse |  | C | 2025-08-04 | 2025-08-12 | 2025-08-18 | 2025-08-22 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-11-26 | 2025-11-27 |  | 2025-11-27 | 2025-11-27 |  | C
67 |  | AP-22 | AP-23 | 947.23 |  | tse |  | C | 2025-08-08 | 2025-08-12 | 2025-09-07 | 2025-09-08 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-10 | 2025-12-13 |  | 2025-12-14 | 2025-12-15 |  | C
68 |  | AP-23 | AP-24 | 1926.75 |  | tse |  | C | 2025-09-04 | 2025-09-06 | 2025-09-07 | 2025-09-08 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-10 | 2025-12-13 |  | 2025-12-14 | 2025-12-15 |  | C
69 |  | AP-24 | AP-25 | 190.524 |  | tse |  | C | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-04 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C | PLC |  | C | 2025-12-10 | 2025-12-13 |  | 2025-12-14 | 2025-12-15 |  | C
70 |  | AP-25 | AP-26 | 178.3 |  | tse |  | C | 2025-09-13 | 2025-09-15 | 2025-09-15 | 2025-09-16 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-10 | 2025-12-13 |  | 2025-12-14 | 2025-12-15 |  | C
71 |  | AP-26 | AP-27 | 148.4 |  | tse |  | C | 2025-10-06 | 2025-10-06 | 2025-10-06 | 2025-10-06 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C | PLC |  | C | 2025-12-10 | 2025-12-13 |  | 2025-12-14 | 2025-12-15 |  | C
72 |  | AP-27 | AP-28 | 61.2 |  | tse |  | C | 2025-11-02 | 2025-11-02 | 2025-12-03 | 2025-12-05 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C | PLC |  | C | 2025-12-10 | 2025-12-13 |  | 2025-12-14 | 2025-12-15 |  | C
73 |  | AP-28 | 28/1 | 42.266 |  | tse |  | C | 2025-11-02 | 2025-11-02 | 2025-12-03 | 2025-12-05 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-10 | 2025-12-13 |  | 2025-12-14 | 2025-12-15 |  | C
74 |  | 28/1 | 28/2 | 54.573 |  | tse |  | C | 2025-11-02 | 2025-11-02 | 2025-12-03 | 2025-12-05 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-10 | 2025-12-13 |  | 2025-12-14 | 2025-12-15 |  | C
75 |  | 28/2 | AP-29 | 41.886 |  | tse |  | C | 2025-09-16 | 2025-09-16 | 2025-09-17 | 2025-09-17 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-10 | 2025-12-13 |  | 2025-12-14 | 2025-12-15 |  | C
76 |  | AP-29 | 29A/0 | 344.5 |  | tse |  | C | 2025-09-15 | 2025-09-15 | 2025-09-16 | 2025-09-16 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-12-10 | 2025-12-13 |  | 2025-12-14 | 2025-12-15 |  | C
77 |  | 29A/0 | AP-30 | 1860.6 |  | tse |  | C | 2025-07-16 | 2025-07-20 | 2025-08-28 | 2025-08-31 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | National Construction | [17 empty] | C |  |  | C | 2025-11-28 | 2025-12-01 |  | 2025-11-28 | 2025-12-01 |  | C
78 |  | AP-30 | AP-31 | 2332.92 |  | tse |  | C | 2025-07-08 | 2025-07-13 | 2025-07-16 | 2025-07-22 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Kohinoor | [17 empty] | C |  |  | C | 2025-11-28 | 2025-12-01 |  | 2025-11-28 | 2025-12-01 |  | C
79 |  | AP-31 | AP-32 | 743.35 |  | tse |  | C | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | GKFS Enterprises | [17 empty] | C |  |  | C | [6 empty] | C
80 |  | AP-32 | 33/0 | 283.1 |  | tse |  | C | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-09 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | [18 empty] | C |  |  | C | [6 empty] | C
81 |  | 33/0 | 34/0 | 532 |  | tse |  | C | 2026-06-01 | 2026-06-05 | 2026-06-06 | 2026-06-07 |  | C |  | C |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | Ram singh | [17 empty] | C |  |  | C | [6 empty] | C
82 |  | 34/0 | 35/0 | 207 |  | tse |  | C | 2026-06-08 | 2026-06-08 | 2026-06-09 | 2026-06-11 | [5 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  |  |  |  | C | [5 empty] | C | [18 empty] | C |  |  | C | [6 empty] | C
83 |  | 35/0 | Gantry | 80 |  | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [32 empty] | C | [6 empty] | C
84 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
85 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
86 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
87 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
88 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
89 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
90 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
91 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
92 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
93 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
94 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
95 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
96 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
97 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
98 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
99 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
100 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
101 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
102 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
103 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
104 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
105 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
106 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
107 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
108 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
109 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
110 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
111 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
112 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
113 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
114 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
115 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
116 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
117 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
118 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
119 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
120 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
121 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
122 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
123 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
124 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
125 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
126 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
127 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
128 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
129 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
130 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
131 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
132 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
133 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
134 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
135 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
136 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
137 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
138 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
139 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
140 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
141 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
142 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
143 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
144 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
145 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
146 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
147 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
148 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
149 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
150 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
151 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
152 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
153 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
154 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
155 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
156 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
157 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
158 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
159 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
160 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
161 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
162 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
163 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
164 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
165 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
166 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
178 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
179 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
180 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
181 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
182 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
183 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
184 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
185 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
186 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
187 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
188 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
189 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
190 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
191 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
192 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
193 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
194 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
195 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
196 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
197 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
198 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
199 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
200 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
201 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
202 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
203 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
204 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
205 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
206 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
207 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
208 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
209 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
210 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
211 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
212 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
213 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
214 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
215 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
216 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
217 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
218 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
219 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
220 | [5 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | 2026-07-15: 4 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | 2026-07-15: 16; 2026-07-26: 0 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | 2026-07-15: 7 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | 2026-07-15: 0.952 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | 952
[6 empty] | tse | 2026-07-15: 0.17357 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | 173.57
[6 empty] | tse | 2026-07-15: 0.3365 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | 336.5
[6 empty] | tse | 2026-07-15: 0.90014 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | 900.14
[6 empty] | tse | 2026-07-15: 1.6972 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | 1697.24
[6 empty] | tse | 2026-07-15: 1.6001 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | 1600.078
[6 empty] | tse | 2026-07-15: 0.52589 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | 525.89
[6 empty] | tse | 2026-07-15: 0.35628 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | 356.279
[6 empty] | tse | 2026-07-15: 0.19052 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | 190.524
[6 empty] | tse | 2026-07-15: 0.14238 |  |  |  |  | TB 501 | 220kV | TB 501 - 220kV | TB 501 - 220kV | tb501220kv | TB 501 - 220kV | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [10 empty] | 142.384
[6 empty] | tse | [11 empty] | TB 507 |  | TB 507 | TB 507 | tb507 | TB 507 | TB 507 - DPR - 2026-08-06.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
|  |  | Total |  |  | tse | [11 empty] | TB 507 |  | TB 507 | TB 507 | tb507 | TB 507 | TB 507 - DPR - 2026-08-06.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
|  | 146/0 | 145/0 | 1970 |  | TSE | 2026-07-15: 2026-02-14; 2026-07-22: 2026-02-16; 2026-07-23: 2026-02-20; 2026-07-26: 2026-02-22 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 1 | Bhinmal | 145/1,2,3,4,5 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete | [24 empty] | Completed
|  | 149A/0 | 149/0 | 188 |  | Manual | 2026-07-15: 2026-03-01; 2026-07-22: 2026-03-03; 2026-07-23: 2026-03-03; 2026-07-26: 2026-03-03 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 2 | Bhinmal | 149/0 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete | [24 empty] | Completed
|  | 149/0 | 148/0 | 3031 |  | TSE | 2026-07-15: 2026-02-01; 2026-07-22: 2026-02-06; 2026-07-23: 2026-03-16; 2026-07-26: 2026-03-18 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 3 | Bhinmal | 148/1,2,3,4,5,6,7 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete | [24 empty] | Completed
|  | 150/0 | 149B/3 | 489 |  | Manual | 2026-07-15: 2026-02-26; 2026-07-22: 2026-02-27; 2026-07-23: 2026-03-08; 2026-07-26: 2026-03-08 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 4 | Bhinmal | 149B/3 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete | [24 empty] | Completed
|  | 149B/0 | 149A/0 | 396 |  | Manual | 2026-07-15: 2026-03-05; 2026-07-22: 2026-03-05; 2026-07-23: 2026-03-10; 2026-07-26: 2026-03-10 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 5 | Bhinmal | 149A/0 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete | [24 empty] | Completed
|  | 149B/3 | 149B/0 | 1265 |  | TSE | 2026-07-15: 2026-03-05; 2026-07-22: 2026-03-09; 2026-07-23: 2026-03-08; 2026-07-26: 2026-03-10 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 6 | Bhinmal | 149B/0,1,2 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete | [24 empty] | Completed
|  | 144/0 | 143/0 | 3275 |  | TSE | 2026-07-15: 2026-03-23; 2026-07-22: 2026-04-04; 2026-07-26: 2026-04-04 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 7 | Bhinmal | 143/0,1,2,3,45,6,7 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete | [24 empty] | Completed
|  | 145/0 | 144/0 | 232 |  | Manual | 2026-07-15: 2026-04-09; 2026-07-26: 2026-04-10 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 8 | Bhinmal | 144/0 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete (132 kv PLC ) | [24 empty] | Completed
|  | 113/0 | 112/0 | 158 |  | Manual | 2026-07-15: 2026-04-09; 2026-07-22: 2026-04-10; 2026-07-26: 2026-04-15 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 9 | Sindhari | 113/0 | Ready |  |  | Completed |  | Completed | complete | Mahadev Maan Construction |  |  |  | Final Sag Complete | [24 empty] | Completed
|  | 153/0 | 152/0 | 243 |  | Manual | 2026-07-15: 2026-04-16; 2026-07-26: 2026-04-17 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 10 | Bhinmal | 152/0 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete (220 kv PLC ) | [24 empty] | Completed
|  | 113A/0 | 113/0 | 201 |  | Manual | 2026-07-15: 2026-04-10; 2026-07-22: 2026-04-10; 2026-07-26: 2026-04-18 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 11 | Sindhari | 113A/0 | Ready |  |  | Completed |  | Completed | complete | Mahadev Maan Construction |  |  |  | Final Sag Complete | [24 empty] | Completed
|  | 147/0 | 146/0 | 1223 |  | TSE | 2026-07-15: 2026-02-18; 2026-07-22: 2026-02-23; 2026-07-23: 2026-03-20; 2026-07-26: 2026-04-21 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 12 | Bhinmal | 146/0,1,2 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete | [24 empty] | Completed
|  | 148/0 | 147/0 | 3666 |  | TSE | 2026-07-15: 2026-04-09; 2026-07-22: 2026-04-20; 2026-07-23: 2026-04-19; 2026-07-26: 2026-04-21 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 13 | Bhinmal | 147/0,1,2,3,4,5,6,7,8,9 | Ready |  |  | Completed |  | Pending | complete | Mahadev Enterprises |  |  |  | Final Sag Complete | [24 empty] | Completed
|  | 151/0 | 150/0 | 290 |  | Manual | 2026-07-15: 2026-04-27; 2026-07-23: 2026-04-25; 2026-07-26: 2026-04-28 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 14 | Bhinmal | 150/0 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete, Rly Crossing | [24 empty] | Completed
|  | 152/0 | 151/0 | 419 |  | Manual | 2026-07-15: 2026-04-28; 2026-07-26: 2026-04-29 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 15 | Bhinmal | 151/0 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete/ Clipping, Specering | [24 empty] | Completed | 15
|  | 134/0 | 133/0 | 3486 |  | TSE | 2026-07-15: 2026-04-29; 2026-07-22: 2026-05-13; 2026-07-26: 2026-05-15 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 16 | Bhinmal | 133/1,2,3,4,5,6,7,8 | Ready |  |  | Completed |  | Completed | complete | Mahadev Enterprises |  |  |  | Final Sag Complete | [24 empty] | Completed | 25
|  | 134/0 | 134A/0 | 226 |  | Manual | 2026-07-15: 2026-05-12; 2026-07-22: 2026-05-13; 2026-07-23: 2026-05-23; 2026-07-26: 2026-05-25 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 17 | Bhinmal |  | Ready |  |  | Completed |  | Completed | complete | SK Tajirul |  |  |  | Final Sag Complete | [24 empty] | Completed
|  | 114/0 | 113A/0 | 165 |  | Manual | 2026-07-15: 2026-05-13; 2026-07-22: 2026-05-20; 2026-07-23: 2026-05-21; 2026-07-26: 2026-05-22 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 18 | Sindhari |  | Ready |  |  | Completed |  | Completed | complete | SK Tajirul |  |  |  | Final Sag Complete | [24 empty] | Completed | 40
|  | 142/0 | 143/0 | 437 |  | Manual | 2026-07-15: 2026-03-21; 2026-07-22: 2026-03-22; 2026-07-23: 2026-05-29; 2026-07-26: 2026-05-30 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 19 | Bhinmal |  | Ready | [5 empty] | complete | Mahadev Enterprises |  |  |  | Final Sag Complete
|  | 115/0 | 115/1 | 425 |  | Manual | 2026-07-15: 2026-05-25; 2026-07-23: ROW |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 20 | Sindhari |  | Ready |  | Completed |  |  |  | ROW | SK Tajirul |  |  |  | Paying out ROW SINCE 3-6-26
|  | 75/0 | 76/0 | 2920 |  | TSE | 2026-07-15: 2026-06-10; 2026-07-22: 2026-06-24; 2026-07-23: 2026-06-25; 2026-07-26: 2026-06-29 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 21 | Sindhari | 75/1,2,3,4,5,6,7 | Ready |  | Completed | Pending |  | WIP | complete | SK Tajirul |  |  |  | Final Sag Complete | [24 empty] | WIP | 28
|  | 76/0 | 77/0 | 835 |  | Manual | 2026-07-15: 2026-06-24 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 22 | Sindhari | 76/1 | Ready |  | ROW |  |  |  | ROW | SK Tajirul |  |  |  | Insulator Hoisting, Pilot PO/ROW | [25 empty] | 28
|  | 77/0 | 78/0 | 2306 |  | TSE | [11 empty] | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 23 | Sindhari | 77/1,2,3,4,5 | Ready |  | ROW |  |  |  | ROW |  |  |  |  | Insulator Hoisting, Pilot PO/ROW
|  | 131/0 | 132/0 | 1159 |  | TSE | [11 empty] | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 24 | Bhinmal | 131/1,2 | Ready |  |  |  |  | WIP | WIP | Mahadev Enterprises |  |  |  | Preparation For Paving out | [25 empty] | 47
|  | 132/0 | 133/0 | 1934 |  | TSE | 2026-07-15: 2026-07-19; 2026-07-22: 2026-07-22; 2026-07-23: 2027-07-23; 2026-07-26: 2026-07-28 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 25 | Bhinmal | 132/1,2,3.4 | Ready |  | Completed |  |  | WIP | WIP | KP Group |  |  |  | Final Sag Completed | [25 empty] | 32
|  | 83/0 | 84/0 | 837 |  | Manual | 2026-07-15: 2026-07-16; 2026-07-22: 2026-07-18; 2026-07-23: 2026-07-20; 2026-07-26: 2026-07-20 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 26 | Sindhari | 83/1 | Ready |  | Completed |  |  | Completed | WIP | SK Tajirul |  |  |  | Final Sag Complete/ ROW for Balance Work | [24 empty] | WIP | 29
|  | 84/0 | 85/0 | 361 |  | Manual | 2026-07-15: 2026-07-09; 2026-07-22: 2026-07-09; 2026-07-23: 2026-07-20; 2026-07-26: 2026-08-03 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 27 | Sindhari |  | Ready |  | Completed |  |  |  | complete | SK Tajirul |  |  |  | Final Sag Comleted | [25 empty] | 33
|  | 85/0 | 86/0 | 736 |  | Manual | 2026-07-15: 2026-07-27; 2026-07-22: 2026-08-03; 2026-07-23: 2026-08-04; 2026-07-26: 2026-08-06 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 28 | Sindhari | 85/1 | Ready |  | Completed |  |  |  | WIP | SK Tajirul |  |  |  | Final Sag WIP | [25 empty] | 29
|  | 90/0 | 91/0 | 815 |  | Manual | 2026-07-15: ROW |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 29 | Sindhari | 90/1 | Ready | [5 empty] | ROW | Mahadev Enterprises-2 |  |  |  | Gang Shifting WIP/Insulator Hoisting | [25 empty] | 20
|  | 131/0 | 132/0 | 1159 |  | TSE | 2026-07-15: ROW |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE | [5 empty] | 131/1,2 | Ready
|  | 134A/0 | 135/0 | 2119 |  | TSE | 2026-07-15: 2026-07-14; 2026-07-22: 2026-07-18; 2026-07-23: 2026-07-22; 2026-07-26: 2026-07-24 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 30 | Bhinmal | 134A/1,2,3,4 | Ready |  | Completed |  |  | WIP | complete | Mahadev Enterprises |  |  |  | Final Sag Completed | [25 empty] | 47
|  | 135/0 | 136/0 | 1531 |  | TSE | 2026-07-15: 2026-07-26; 2026-07-22: 2026-07-30; 2026-07-23: 2026-07-27; 2026-07-26: 2026-07-30 |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 31 | Bhinmal | 135/1,2,3 | Ready |  | Completed |  |  |  | WIP | Mahadev Enterprises |  |  |  | Paving out/Final sag WIP | [25 empty] | 45
|  | 136/0 | 137/0 | 356 |  | Manual | 2026-07-15: 2026-07-18; 2026-07-22: 2026-07-21; 2026-07-23: ROW; 2026-07-26: ROW |  |  |  |  | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 32 | Bhinmal |  | Ready |  | Completed |  |  |  | WIP | Mahadev Enterprises |  |  |  | Paving out WIP | [25 empty] | 47
|  | 137/0 | 138/0 | 427 |  | Manual | [11 empty] | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 33 | Bhinmal |  | Ready | [6 empty] | Mahadev Enterprises |  |  |  | PO arrangement | [25 empty] | 47
|  | 138/0 | 139/0 | 1438 |  | TSE | [11 empty] | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | FALSE |  |  |  | 34 | Bhinmal | 138/1,2,3 | Ready | [5 empty] | WIP | Mahadev Enterprises |  |  |  | PO arrangement | [25 empty] | 47
|  |  | Total |  |  | tse | [11 empty] | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | [11 empty] | TB 507 | MAIN | TB 507 - MAIN | TB 507 - MAIN | tb507main | TB 507 - MAIN | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[6 empty] | tse | 2026-07-15: Start Date; 2026-07-22: End Date; 2026-07-23: Start Date; 2026-07-26: End Date |  |  |  |  | TB 605 |  | TB 605 | TB 605 | tb605 | TB 605 | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 | [5 empty] | Start Date | [16 empty] | End Date | [19 empty] | Start Date | End Date
1 |  | AP25 | AP26 | 1.028 |  | TSE | 2026-07-15: 2026-06-17; 2026-07-22: 2026-06-21; 2026-07-23: 2026-06-23; 2026-07-26: 2026-06-24 |  |  |  |  | TB 605 |  | TB 605 | TB 605 | tb605 | TB 605 | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | FALSE | [7 empty] | 2026-06-10 |  |  |  |  | F/S Completed | Tariq | [8 empty] | AP25-AP26 |  | 2026-06-12 | [18 empty] | 32 | 2026-06-17 | 2026-06-21
2 |  | AP26 | AP27 | 0.442 |  | Manual | 2026-07-15: 2026-06-14; 2026-07-22: 2026-06-16; 2026-07-23: 2026-06-17; 2026-07-26: 2026-06-22 |  |  |  |  | TB 605 |  | TB 605 | TB 605 | tb605 | TB 605 | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | FALSE | [7 empty] | 2026-06-14 |  |  |  |  | F/S Completed | Tariq | [8 empty] | AP26-AP27 |  | 2026-06-14 | [19 empty] | 2026-06-14 | 2026-06-16
3 |  | AP18 | AP19 | 1.06 |  | TSE | 2026-07-15: 2026-07-07; 2026-07-22: 2026-07-12; 2026-07-23: 2026-07-16; 2026-07-26: 2026-07-20 |  |  |  |  | TB 605 |  | TB 605 | TB 605 | tb605 | TB 605 | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | FALSE | [7 empty] | 2026-06-20 |  |  |  |  | F/S Completed | Janual Sheik | [8 empty] | AP18-AP19 |  | 2026-06-28 | [18 empty] | 25 | 2026-07-08 | 2026-07-12
4 |  | AP24 | AP25 | 0.366 |  | Manual | 2026-07-15: 2026-06-26; 2026-07-22: 2026-07-05; 2026-07-23: 2026-07-04; 2026-07-26: 2026-07-06 |  |  |  |  | TB 605 |  | TB 605 | TB 605 | tb605 | TB 605 | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | FALSE | [7 empty] | 2026-06-25 |  |  |  |  | F/S Completed | Tariq | [8 empty] | AP24-AP25 |  | 2026-06-26 | [18 empty] | 35 | 2026-06-27 | 2026-07-05
5 |  | AP20 | AP21 | 0.486 |  | Manual | 2026-07-15: 2026-07-01; 2026-07-22: 2026-07-02; 2026-07-23: 2026-08-03; 2026-07-26: 2026-08-05 |  |  |  |  | TB 605 |  | TB 605 | TB 605 | tb605 | TB 605 | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | FALSE | [7 empty] | 2026-06-30 |  |  |  |  | F/S Completed | Janual Sheik | [8 empty] | AP20-AP21 |  | 2026-07-01 | [18 empty] | 25 | 2026-07-03 | 2026-07-05
6 |  | AP27 | AP28 | 0.739 |  | Manual | 2026-07-15: 2026-07-11; 2026-07-22: 2026-07-14; 2026-07-23: 2026-07-17; 2026-07-26: 2026-07-18 |  |  |  |  | TB 605 |  | TB 605 | TB 605 | tb605 | TB 605 | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | FALSE | [7 empty] | 2026-07-07 |  |  |  |  | F/S Completed | Tariq | [8 empty] | AP27-AP28 |  | 2026-07-10 | [18 empty] | 35 | 2026-07-12 | 2026-07-14
7 |  | AP19 | AP20 | 1.089 |  | TSE | 2026-07-15: 2026-07-15; 2026-07-22: 2026-07-19; 2026-07-23: 2026-07-23; 2026-07-26: 2026-07-25 |  |  |  |  | TB 605 |  | TB 605 | TB 605 | tb605 | TB 605 | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | FALSE | [7 empty] | 2026-07-08 |  |  |  |  | F/S Completed | Janual Sheik | [8 empty] | AP19-AP20 |  | 2026-07-10 | [18 empty] | 25 | 2026-07-16 | 2026-07-19
8 |  | AP28 | AP29 | 0.446 |  | Manual | 2026-07-15: 2026-07-15; 2026-07-22: 2026-07-16; 2026-07-23: 2026-07-31; 2026-07-26: 2026-08-02 |  |  |  |  | TB 605 |  | TB 605 | TB 605 | tb605 | TB 605 | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | FALSE | [7 empty] | 2026-07-15 |  |  |  |  | F/S Completed | Tariq | [8 empty] | AP28-AP29 |  | 2026-07-16 | [18 empty] | 35 | 2026-07-17 | 2026-07-29
9 |  | AP46 | AP47 | 2.216 |  | TSE | [11 empty] | TB 605 |  | TB 605 | TB 605 | tb605 | TB 605 | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | FALSE | [7 empty] | 17-07-026 |  |  |  |  | Pilot Paying out / Due to non availabilty of shutdown gang idle for last 2 days | Musludin | [8 empty] | AP46-AP47 |  | 2026-08-02 | [18 empty] | 80
10 |  | AP29 | AP30 | 2.57 |  | TSE | [11 empty] | TB 605 |  | TB 605 | TB 605 | tb605 | TB 605 | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | FALSE | [7 empty] | 2026-07-26 |  |  |  |  | Insulator Hoisting | Tariq | [8 empty] | AP29-AP30 |  | 2026-08-04 | [18 empty] | 35

## Diagnostics
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | DetectedHeaderRow | ColumnsDetected | NormalizedColumnsOk | PresentColumns | MissingColumns | AppliedMap | Rows | DailyRows | Status | FallbackNote | TemplateSheet | TemplateApplied | TemplateFallbackUsed | TemplateChanges | MethodInferenceRows
TA 413 - DPR - 2026-08-07.xlsx | TA413 | Stringing | Stringing |  |  | 3 | S.no, Sec, From AP, To AP, Span (M), unnamed_col_6, Method, unnamed_col_8, Insulator Hoisting, P/O Starting Date, P/O Completion Date, F/S Starting Date, F/S/ Completion Date, unnamed_col_14, Jumpering, Spacering, Clipping, 7 484585479944454, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | FALSE | From AP, To AP, Method, P/O Starting Date, P/O Completion Date, F/S Starting Date, F/S/ Completion Date, Length | Section Readiness, P/O, Gang Name | From AP->from_ap, To AP->to_ap, Span (M)->length_m, Method->method, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date | 49 | 633 | FALLBACK | XML scrub fallback used for sheet 'Stringing' | TA 413 Stringing | TRUE | FALSE | C1:cumm sr no->S.no; C2:month sr no->Sec; C3:Section->From AP; C4:unnamed_col_4->To AP; C5:unnamed_col_5->Span (M); C7:unnamed_col_7->Method; C9:unnamed_col_9->Insulator Hoisting; C10:unnamed_col_10->P/O Starting Date; C11:unnamed_col_11->P/O Completion Date; C12:unnamed_col_12->F/S Starting Date; C13:unnamed_col_13->F/S/ Completion Date; C15:unnamed_col_15->Jumpering; C16:unnamed_col_16->Spacering; C17:unnamed_col_17->Clipping | 0
TA 414 - DPR - 2026-08-07.xlsx | TA414 | Stringing Compiled | Stringing Compiled |  |  | 1 | s no, sec, From AP, To AP, location nos, span m, Method, Section Readiness, insulator hoisting, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, jumpering, spacering, clipping, Length, Status, Gang Name, gang strength, number of fitters, hindrance, remarks, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | TRUE | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name |  | From AP->from_ap, To AP->to_ap, span m->length_m, Method->method, Section Readiness->section_readiness, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, P/O->po, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Length->length_m, Status->status, Gang Name->gang_name | 172 | 343 | FALLBACK | XML scrub fallback used for sheet 'Stringing Compiled' |  | FALSE | FALSE |  | 0
TA 416 - DPR - 2026-07-16.xlsx | TA416 | Stringing compiled | Stringing compiled |  |  | 2 | s no, sec, From AP, To AP, location nos, span m, Method, Section Readiness, insulator hoisting, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, jumpering, spacering, clipping, Length, Status, Gang Name, gang strength, number of fitters, hindrance, remarks, unnamed_col_25, unnamed_col_26, revenue, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | TRUE | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name |  | From AP->from_ap, To AP->to_ap, span m->length_m, Method->method, Section Readiness->section_readiness, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, P/O->po, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Length->length_m, Status->status, Gang Name->gang_name | 79 | 1239 | OK |  |  | FALSE | FALSE |  | 2
TA 418 - DPR - 2026-07-21.xlsx | TA418 | Stringing Completed | Stringing Completed |  |  | 2 | s no, sec, From AP, To AP, location nos, span m, Method, Section Readiness, tackwelding status, insulator hoisting, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, jumpering, spacering, clipping, Length, Status, Gang Name, gang strength, number of fitters, hindrance, remarks, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | TRUE | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name |  | From AP->from_ap, To AP->to_ap, span m->length_m, Method->method, Section Readiness->section_readiness, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, P/O->po, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Length->length_m, Status->status, Gang Name->gang_name | 43 | 811 | OK |  |  | FALSE | FALSE |  | 4
TA 419 - DPR - 2026-08-06.xlsx | TA419 | Stringing Compiled | Stringing Compiled |  |  | 2 | s no, sec, From AP, To AP, span m, Method, Section Readiness, insulator hoisting, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, jumpering, spacering, clipping, Length, Status, Gang Name, Section, gang strength, number of fitters, hindrance, remarks, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | TRUE | Section, From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name |  | From AP->from_ap, To AP->to_ap, span m->length_m, Method->method, Section Readiness->section_readiness, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, P/O->po, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Length->length_m, Status->status, Gang Name->gang_name, Section->section | 137 | 13 | FALLBACK | XML scrub fallback used for sheet 'Stringing Compiled' |  | FALSE | FALSE |  | 3
TA 421 - DPR - 2026-07-11.xlsx | TA421 | ProGress Sheet | ProGress Sheet |  |  | 1 | unnamed_col_1, S.no, Section, Length, Status, unnamed_col_6, unnamed_col_7, unnamed_col_8, Gang Name, gang strength, P/O Starting Date, F/S/ Completion Date, e rthwire, Remarks, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | FALSE | Section, From AP, To AP, P/O Starting Date, F/S/ Completion Date, Length, Status, Gang Name | Method, Section Readiness, P/O Completion Date, P/O, F/S Starting Date | Section->section, Length->length_m, Status->status, Gang Name->gang_name, P/O Starting Date->po_start_date, F/S/ Completion Date->fs_complete_date | 60 | 1016 | OK |  | TA 421 Stringing | TRUE | FALSE | C2:s no->S.no; C11:rough sag->P/O Starting Date; C12:f n l sag->F/S/ Completion Date | 60
TA 504 - DPR - 2026-08-07.xlsx | TA504 | Stringing Compiled | Stringing Compiled |  |  | 1 | s no, sec, From AP, To AP, location nos, span m, Method, Section Readiness, insulator hoisting, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, jumpering, spacering, clipping, Length, Status, Gang Name, gang strength, number of fitters, hindrance, remarks, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | TRUE | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name |  | From AP->from_ap, To AP->to_ap, span m->length_m, Method->method, Section Readiness->section_readiness, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, P/O->po, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Length->length_m, Status->status, Gang Name->gang_name | 11 | 198 | FALLBACK | XML scrub fallback used for sheet 'Stringing Compiled' |  | FALSE | FALSE |  | 0
TA 505 - DPR - 2026-07-29.xlsx | TA505 | Stringing Compiled | Stringing Compiled |  |  | 3 | s no, sec, From AP, To AP, span m, towers in section, Method, Section Readiness, insulator hoisting, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, jumpering, spacering, clipping, Length, Status, Gang Name, gang strength, number of fitters, hindrance, remarks, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | TRUE | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name |  | From AP->from_ap, To AP->to_ap, span m->length_m, Method->method, Section Readiness->section_readiness, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, P/O->po, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Length->length_m, Status->status, Gang Name->gang_name | 47 | 373 | OK |  |  | FALSE | FALSE |  | 16
TA 506 - DPR - 2026-08-07.xlsx | TA506 | Stringing | Stringing |  |  | 1 | s no, sec, From AP, To AP, span m, Method, Section Readiness, insulator hoisting, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, jumpering, spacering, clipping, Length, Status, Gang Name, gang strength, no of fitters, hindrance, remarks, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | TRUE | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name |  | From AP->from_ap, To AP->to_ap, span m->length_m, Method->method, Section Readiness->section_readiness, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, P/O->po, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Length->length_m, Status->status, Gang Name->gang_name | 229 | 720 | FALLBACK | XML scrub fallback used for sheet 'Stringing' |  | FALSE | FALSE |  | 168
TA 601 - DPR - 2026-08-07.xlsx | TA601 | Stringing Compiled | Stringing Compiled |  |  | 0 | s no, sec, From AP, To AP, span m, Method, Section Readiness, insulator hoisting, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, jumpering, spacering, clipping, Length, Status, Gang Name, gang strength, number of fitters, hindrance, remarks |  |  |  |  | 0 | 0 | EMPTY_SHEET
TB 408 - DPR - 2026-07-30.xlsx | TB408 | Stringing | Stringing |  |  | 3 | S.no, From AP, To AP, Method, Gang Name, Span (M), P/O, P/O Starting Date, P/O Completion Date, Length, F/S Starting Date, F/S/ Completion Date, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | FALSE | From AP, To AP, Method, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Gang Name | Section Readiness | From AP->from_ap, To AP->to_ap, Method->method, Gang Name->gang_name, Span (M)->length_m, P/O->po, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, Length->length_m, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date | 105 | 1855 | OK |  | TB 408 Stringing | TRUE | FALSE | C1:sl no->S.no; C2:Section->From AP; C3:unnamed_col_3->To AP; C4:type of sections->Method; C6:section length->Span (M); C7:paying out r sag->P/O; C8:unnamed_col_8->P/O Starting Date; C9:unnamed_col_9->P/O Completion Date; C10:final sag->Length; C11:unnamed_col_11->F/S Starting Date; C12:unnamed_col_12->F/S/ Completion Date | 18
TB 412 - DPR - 2026-08-07.xlsx | TB412 | WIP | WIP |  |  | 5 | t l name, S.no, Gang Name, From AP, To AP, Length, P/O Starting Date, F/S/ Completion Date, mp, Status, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | FALSE | From AP, To AP, P/O Starting Date, F/S/ Completion Date, Length, Status, Gang Name | Method, Section Readiness, P/O Completion Date, P/O, F/S Starting Date | Gang Name->gang_name, From AP->from_ap, To AP->to_ap, Length->length_m, P/O Starting Date->po_start_date, F/S/ Completion Date->fs_complete_date, Status->status | 29 | 6 | OK |  | TB 412 Stringing | TRUE | FALSE | C2:sr no->S.no; C4:loc no->From AP; C5:t o t->To AP; C6:t o cl->Length; C7:d o s->P/O Starting Date; C8:d o c->F/S/ Completion Date; C10:remarks->Status | 29
TB 501 - DPR - 2026-07-30.xlsx | TB501 | Stringing-132KV | Stringing-132KV | 132kV | config | 4 | S.no, From AP, To AP, Span (M), Section Readiness, Insulator Hoisting, Status, P/O Starting Date, P/O Completion Date, status__2, F/S Starting Date, F/S/ Completion Date, Clipping, Spacering, Jumpering, Gang Name, unnamed_col_17, Remarks, unnamed_col_19, status__6, dos__3, doc__3, status__7, dos__4, doc__4, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | FALSE | From AP, To AP, Section Readiness, P/O Starting Date, P/O Completion Date, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name | Method, P/O | From AP->from_ap, To AP->to_ap, Span (M)->length_m, Section Readiness->section_readiness, Status->status, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Gang Name->gang_name | 48 | 120 | OK |  | TB 501 132kV Stringing | TRUE | FALSE | C1:unnamed_col_1->S.no; C2:from->From AP; C3:to->To AP; C4:unnamed_col_4->Span (M); C5:unnamed_col_5->Section Readiness; C6:unnamed_col_6->Insulator Hoisting; C8:dos->P/O Starting Date; C9:doc->P/O Completion Date; C11:dos__2->F/S Starting Date; C12:doc__2->F/S/ Completion Date; C13:status__3->Clipping; C14:status__4->Spacering; C15:status__5->Jumpering; C16:unnamed_col_16->Gang Name; C18:unnamed_col_18->Remarks | 48
TB 501 - DPR - 2026-07-30.xlsx | TB501 | Stringing-220kV | Stringing-220kV | 220kV | config | 4 | S.no, From AP, To AP, Span (M), Section Readiness, Insulator Hoisting, Status, P/O Starting Date, P/O Completion Date, status__2, F/S Starting Date, F/S/ Completion Date, Clipping, Jumpering, Gang Name, unnamed_col_16, unnamed_col_17, Remarks, status__5, dos__3, doc__3, status__6, dos__4, doc__4, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | FALSE | From AP, To AP, Section Readiness, P/O Starting Date, P/O Completion Date, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name | Method, P/O | From AP->from_ap, To AP->to_ap, Span (M)->length_m, Section Readiness->section_readiness, Status->status, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Gang Name->gang_name | 226 | 891 | OK |  | TB 501 220kV Stringing | TRUE | FALSE | C1:unnamed_col_1->S.no; C2:from->From AP; C3:to->To AP; C4:unnamed_col_4->Span (M); C5:unnamed_col_5->Section Readiness; C6:unnamed_col_6->Insulator Hoisting; C8:dos->P/O Starting Date; C9:doc->P/O Completion Date; C11:dos__2->F/S Starting Date; C12:doc__2->F/S/ Completion Date; C13:status__3->Clipping; C14:status__4->Jumpering; C15:unnamed_col_15->Gang Name; C18:unnamed_col_18->Remarks | 226
TB 507 - DPR - 2026-08-06.xlsx | TB507 | Stringing Compiled | Stringing Compiled |  |  | 2 | s no, sec, From AP, To AP, span m, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name, hindrance, remarks, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | TRUE | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name |  | From AP->from_ap, To AP->to_ap, span m->length_m, Method->method, Section Readiness->section_readiness, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, P/O->po, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Length->length_m, Status->status, Gang Name->gang_name | 2 | 0 | NO_DAILY |  |  | FALSE | FALSE |  | 2
TB 507 [MAIN] - DPR - 2026-08-06.xlsx | TB507 | Stringing Compiled | Stringing Compiled | MAIN |  | 2 | s no, sec, From AP, To AP, location nos, span m, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, jumpering, specering, clipping, Length, Status, Gang Name, manpower, no of fitters, hindrance, remarks, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | TRUE | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name |  | From AP->from_ap, To AP->to_ap, span m->length_m, Method->method, Section Readiness->section_readiness, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, P/O->po, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Length->length_m, Status->status, Gang Name->gang_name | 40 | 394 | OK |  |  | FALSE | FALSE |  | 5
TB 605 - DPR - 2026-08-05.xlsx | TB605 | Stringing JS-Jammu | Stringing JS-Jammu |  |  | 2 | unnamed_col_1, S.no, Section, Length, Method, insulator hoisting, unnamed_col_7, P/O Starting Date, P/O Completion Date, rough sag, unnamed_col_11, F/S Starting Date, F/S/ Completion Date, Status, Gang Name, manpower, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | FALSE | Section, From AP, To AP, Method, P/O Starting Date, P/O Completion Date, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name | Section Readiness, P/O | Section->section, Length->length_m, Method->method, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Status->status, Gang Name->gang_name | 11 | 116 | OK |  | TB 605 Stringing | TRUE | FALSE | C2:s no->S.no; C4:length km->Length; C5:tse manual->Method; C8:paying out->P/O Starting Date; C9:unnamed_col_9->P/O Completion Date; C12:final sag->F/S Starting Date; C13:unnamed_col_13->F/S/ Completion Date; C14:remarks->Status; C15:gang->Gang Name | 1

## Data Issues
project_name | from_ap | to_ap | gang_name | method | status | po_start_date | po_completion_date | fs_starting_date | fs_complete_date | length_m | length_km | po_km | source_file | source_sheet | Issues
TA 413 | From | To |  | TSE/Manual | [8 empty] | TA 413 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 413 | 20/0 | 21/0 |  | TSE |  | 2026-07-25 | 2026-07-29 |  |  | 2550.167 | 2.5502 |  | TA 413 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 413 | 43A/0 | 44/0 |  | TSE |  | 2026-08-01 | 2026-08-04 |  |  | 1584.546 | 1.5845 |  | TA 413 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 413 | 44/0 | 45/0 |  | TSE | [5 empty] | 2383 | 2.383 |  | TA 413 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 413 | 21/0 | 22/0 |  | TSE | [5 empty] | 2283.535 | 2.2835 |  | TA 413 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 413 | 12/0 | 13/0 |  | Manual | [5 empty] | 329.73 | 0.32973 |  | TA 413 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 117/0 | 118/0 |  | TSE | [5 empty] | 1142.762 | 1.1428 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 121/0 | 121/1 | Enamul Haque | Hotline | [5 empty] | 276.141 | 0.27614 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 121/7 | 124/0 |  | TSE/Hotline | [5 empty] | 1937.394 | 1.9374 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 125/0 | 126/0 |  | TSE | [5 empty] | 1288.931 | 1.2889 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 127/0 | 127/2 |  | Manual | [5 empty] | 709.979 | 0.70998 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 127/2 | 128/0 |  | Manual | [5 empty] | 339.13 | 0.33913 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 128/0 | 129/0 |  | Manual | [5 empty] | 620 | 0.62 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 129/0 | 130/0 |  | Manual | [5 empty] | 620.06 | 0.62006 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 130/0 | 131/0 |  | Manual | [5 empty] | 535.07 | 0.53507 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 131/0 | 132/0 |  | TSE | [5 empty] | 2201.62 | 2.2016 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 132/0 | 133/0 |  | TSE | [5 empty] | 1217.54 | 1.2175 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 133/0 | 133/2 |  | Manual | [5 empty] | 767 | 0.767 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 133/2 | 133/3 |  | Hotline | [5 empty] | 250 | 0.25 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 133/3 | 134/0 |  | Manual | [5 empty] | 833.85 | 0.83385 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 134/0 | 135/0 |  | Manual | [5 empty] | 360.67 | 0.36067 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 135/0 | 136/0 |  | Hotline | [5 empty] | 247.871 | 0.24787 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 136/0 | 136/1 |  | Manual | [5 empty] | 459.998 | 0.46 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 136/1 | 137/0 |  | Hotline | [5 empty] | 455.963 | 0.45596 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 137/0 | 138/0 |  | TSE | [5 empty] | 1116.114 | 1.1161 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 138/0 | 139/0 |  | Manual | [5 empty] | 460.541 | 0.46054 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 139/0 | 139/2 |  | Manual | [5 empty] | 716.09 | 0.71609 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 139/2 | 139/3 |  | Manual | [5 empty] | 340 | 0.34 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 139/3 | 140/0 |  | Manual | [5 empty] | 360.1 | 0.3601 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 140/0 | 141/0 |  | Hotline | [5 empty] | 204 | 0.204 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 141/0 | 142/0 |  | TSE | [5 empty] | 2659.63 | 2.6596 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 142/0 | 143/0 |  | Manual | [5 empty] | 164.303 | 0.1643 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 144/0 | 145/0 |  | Hotline | [5 empty] | 451.679 | 0.45168 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 145/0 | 145/7 |  | TSE | [5 empty] | 2776 | 2.776 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 145/7 | 147/0 |  | Manual | [5 empty] | 344.268 | 0.34427 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 147/0 | 148/0 |  | Hotline | [5 empty] | 251.645 | 0.25165 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 148/5 | 149/0 |  | Manual | [5 empty] | 508.088 | 0.50809 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 149/0 | 150/0 |  | Hotline | [5 empty] | 258.002 | 0.258 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 150/0 | 150/1 |  | Manual | [5 empty] | 281 | 0.281 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 150/1 | 151/0 |  | Manual | [5 empty] | 367.61 | 0.36761 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 151/0 | 151A/0 |  | Manual | [5 empty] | 266.99 | 0.26699 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 151A/0 | 152/0 |  | Manual | [5 empty] | 500.05 | 0.50005 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 152/0 | 153/0 |  | Hotline | [5 empty] | 295 | 0.295 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 153/0 | 153A/0 |  | TSE | [5 empty] | 1184.01 | 1.184 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 153A/0 | 154/0 |  | Manual | [5 empty] | 490.15 | 0.49015 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 154/0 | 155/0 |  | Manual | [5 empty] | 295.36 | 0.29536 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 155/0 | 156/0 |  | Hotline | [5 empty] | 257.34 | 0.25734 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 156/0 | 156/1 |  | Manual | [5 empty] | 342.99 | 0.34299 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 156/1 | 157/0 |  | Manual | [5 empty] | 335.33 | 0.33533 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 157/0 | 158/0 |  | Hotline | [5 empty] | 230 | 0.23 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 158/0 | 159/0 |  | Manual | [5 empty] | 253.62 | 0.25362 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 159/0 | 160/0 |  | Hotline | [5 empty] | 333.34 | 0.33334 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 160/0 | 161/0 |  | Manual | [5 empty] | 392.23 | 0.39223 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 161/0 | 162/0 |  | Hotline | [5 empty] | 248.002 | 0.248 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 162/0 | 163/0 |  | Hotline | [5 empty] | 328.496 | 0.3285 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 163/0 | 163/1 |  | Hotline | [5 empty] | 382.995 | 0.38299 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 163/1 | 164/0 |  | Manual | [5 empty] | 401.589 | 0.40159 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 164/0 | 165/0 |  | Hotline | [5 empty] | 285.055 | 0.28506 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 165/0 | 165/6 |  | TSE | [5 empty] | 2297.996 | 2.298 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 165/6 | 166/0 |  | Manual | [5 empty] | 730.096 | 0.7301 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 166/0 | 167/0 |  | Manual | [5 empty] | 280 | 0.28 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 167/0 | 168/0 |  | Manual | [5 empty] | 576.145 | 0.57615 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 168/0 | 169/0 |  | Hotline | [5 empty] | 255.601 | 0.2556 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 169/0 | 170/0 |  | Manual | [5 empty] | 521.312 | 0.52131 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 170/0 | 171/0 |  | Hotline | [5 empty] | 261.446 | 0.26145 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 171/0 | 172/0 |  | Hotline | [5 empty] | 186.772 | 0.18677 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 172/0 | 173/0 |  | Manual | [5 empty] | 689.629 | 0.68963 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 173/0 | 174/0 |  | Hotline | [5 empty] | 215.227 | 0.21523 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 179/0 | 180/0 |  | TSE | [5 empty] | 1582.474 | 1.5825 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 180/0 | 180/2 |  | Manual | [5 empty] | 821.997 | 0.822 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 187/0 | 188/0 |  | Manual | [5 empty] | 428.21 | 0.42821 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 188/0 | 189/0 |  | Manual | [5 empty] | 672.59 | 0.67259 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 189/0 | 190/0 |  | Manual | [5 empty] | 807.98 | 0.80798 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 191/0 | 191/1 |  | Manual | [5 empty] | 465.47 | 0.46547 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 191/1 | 192/0 |  | Manual | [5 empty] | 389.51 | 0.38951 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 192/0 | 193/0 |  | Hotline | [5 empty] | 222.83 | 0.22283 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 193/0 | 194/0 |  | Hotline | [5 empty] | 277.42 | 0.27742 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 194/0 | 194/1 |  | Manual | [5 empty] | 470 | 0.47 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 194/1 | 195/0 |  | Manual | [5 empty] | 479.7 | 0.4797 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 195/0 | 196/0 |  | Hotline | [5 empty] | 239.69 | 0.23969 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 196/0 | 197/0 |  | TSE | [5 empty] | 1148.42 | 1.1484 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 199/0 | 200/0 |  | TSE | [5 empty] | 1266.29 | 1.2663 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 200/0 | 201/0 |  | Hotline | [5 empty] | 709.98 | 0.70998 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 201/0 | 202/0 |  | Manual | [5 empty] | 513.96 | 0.51396 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 202/0 | 203/0 |  | Hotline | [5 empty] | 233.14 | 0.23314 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 203/0 | 203A/0 |  | Manual | [5 empty] | 128.02 | 0.12802 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 203A/0 | 203B/0 |  | Manual | [5 empty] | 282.82 | 0.28282 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 203B/0 | 204/0 |  | Manual | [5 empty] | 339.95 | 0.33995 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 204/0 | 205/0 |  | Hotline | [5 empty] | 172.64 | 0.17264 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 205/0 | 205/1 |  | Manual | [5 empty] | 555.17 | 0.55517 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 205/1 | 206/0 |  | Manual | [5 empty] | 811.52 | 0.81152 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 206/0 | 206/1 |  | Manual | [5 empty] | 184.81 | 0.18481 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 206/1 | 207/0 |  | Manual | [5 empty] | 214.27 | 0.21427 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 207/0 | 208/0 |  | Hotline | [5 empty] | 272.3 | 0.2723 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 208/0 | 209/0 |  | Hotline | [5 empty] | 284.64 | 0.28464 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 209/0 | 210/0 |  | TSE | [5 empty] | 1036.29 | 1.0363 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 210/0 | 211/0 |  | Hotline | [5 empty] | 397.66 | 0.39766 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 211/0 | 211/5 |  | TSE | [5 empty] | 1872 | 1.872 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 211/5 | 212/0 |  | Manual | [5 empty] | 266.961 | 0.26696 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 212/0 | 213/0 |  | Hotline | [5 empty] | 378.221 | 0.37822 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 213/0 | 214/0 |  | Hotline | [5 empty] | 325.229 | 0.32523 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 214/0 | 215/0 |  | TSE | [5 empty] | 2987.2165 | 2.9872 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 215/0 | 216/0 |  | Hotline | [5 empty] | 231.41 | 0.23141 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 216/0 | 216/2 |  | Hotline | [5 empty] | 803 | 0.803 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 216/2 | 217/0 |  | Manual | [5 empty] | 749.12 | 0.74912 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 217/0 | 218/0 |  | TSE | [5 empty] | 2245.811 | 2.2458 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 218/0 | 219/0 |  | Hotline | [5 empty] | 239.47 | 0.23947 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 219/0 | 220/0 |  | Manual | [5 empty] | 798.41 | 0.79841 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 220/0 | 221/0 |  | Manual | [5 empty] | 819.27 | 0.81927 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 223/0 | 224/0 |  | TSE | [5 empty] | 1386.17 | 1.3862 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 224/0 | 224/2 |  | Manual | [5 empty] | 714 | 0.714 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 224/2 | 225/0 |  | Manual | [5 empty] | 431.2 | 0.4312 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 225/0 | 226/0 |  | TSE | [5 empty] | 2965.43 | 2.9654 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 226/0 | 227/0 |  | TSE | [5 empty] | 1574.68 | 1.5747 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 227/0 | 228/0 |  | TSE | [5 empty] | 1238.74 | 1.2387 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 228/0 | 229/0 |  | Manual | [5 empty] | 767.07 | 0.76707 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 229/0 | 229A/0 |  | Manual | [5 empty] | 791.5 | 0.7915 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 229A/0 | 229B/0 |  | Hotline | [5 empty] | 179.98 | 0.17998 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 229B/0 | 230/0 |  | Manual | [5 empty] | 390.65 | 0.39065 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 230/0 | 230A/0 |  | Manual | [5 empty] | 786.67 | 0.78667 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 230A/0 | 231/0 |  | Manual | [5 empty] | 239.51 | 0.23951 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 231/0 | 232/0 |  | Hotline | [5 empty] | 246.98 | 0.24698 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 232/0 | 233/0 |  | TSE | [5 empty] | 1728.185 | 1.7282 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 233/0 | 234/0 |  | Manual | [5 empty] | 411.1429 | 0.41114 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 234/0 | 235/0 |  | Hotline | [5 empty] | 295 | 0.295 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 235/0 | 236/0 |  | TSE | [5 empty] | 1763.541 | 1.7635 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 236/0 | 237/0 |  | Hotline | [5 empty] | 200.821 | 0.20082 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 237/0 | 238/0 |  | Hotline | [5 empty] | 202.277 | 0.20228 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 238/0 | 239/0 |  | Manual | [5 empty] | 363.321 | 0.36332 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 239/0 | 240/0 |  | Manual | [5 empty] | 737.403 | 0.7374 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 240/0 | 241/0 |  | Manual | [5 empty] | 734.048 | 0.73405 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 241/0 | 242/0 |  | TSE | [5 empty] | 1835.738 | 1.8357 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 242/0 | 243/0 |  | Hotline | [5 empty] | 280.015 | 0.28002 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 243/0 | 244/0 |  | TSE | [5 empty] | 1372.6 | 1.3726 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 244/0 | 245/0 |  | TSE | [5 empty] | 2778.121 | 2.7781 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 246/0 | 247/0 |  | Manual | [5 empty] | 463.1 | 0.4631 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 247/0 | 248/0 |  | Hotline | [5 empty] | 256.45 | 0.25645 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 248/0 | 248/1 |  | Manual | [5 empty] | 425.57 | 0.42557 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 248/1 | 249/0 |  | Manual | [5 empty] | 566.9 | 0.5669 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 249/0 | 250/0 |  | TSE | [5 empty] | 1620.626 | 1.6206 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 250/0 | 250A/0 |  | TSE | [5 empty] | 1630.951 | 1.631 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 250A/0 | 251/0 |  | TSE | [5 empty] | 1133.974 | 1.134 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 251/0 | 252/0 |  | Manual | [5 empty] | 840.868 | 0.84087 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 252/0 | 252/5 |  | TSE | [5 empty] | 2021.996 | 2.022 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 252/5 | 253/0 |  | Manual | [5 empty] | 487.454 | 0.48745 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 253/0 | 254/0 |  | Hotline | [5 empty] | 304.46 | 0.30446 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 254/0 | 254/1 |  | Manual | [5 empty] | 353.19 | 0.35319 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 254/1 | 255/0 |  | Manual | [5 empty] | 263.06 | 0.26306 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 255/0 | 256/0 |  | Manual | [5 empty] | 736.76 | 0.73676 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 256/0 | 257/0 |  | Hotline | [5 empty] | 583.35 | 0.58335 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 257/0 | 258/0 |  | Manual | [5 empty] | 94.77 | 0.09477 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 414 | 258/0 | Gantry |  | Manual | [5 empty] | 79 | 0.079 |  | TA 414 - DPR - 2026-08-07.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 416 | AP58/0 | AP59/0 | Dharmendra Hot line | Manual | Completed | 2026-06-01 | 2026-06-03 | 2026-06-03 | 2025-06-07 | 281.56 | 0.28156 |  | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled
TA 416 |  |  |  | tse | [8 empty] | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 416 |  | Total |  | tse | 0 |  |  |  |  | 115.2147 | 0.11521 |  | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 418 | AP46 | 46/7 |  | TSE |  | 2026-07-17 | 2026-07-21 |  |  | 2745 | 2.745 |  | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 418 | 46/7 | AP47/0 |  | TSE | [5 empty] | 3547.25 | 3.5473 |  | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 418 | AP47/0 | AP48 |  | TSE |  | 2026-07-09 | 2026-07-12 |  |  | 813.45 | 0.81345 |  | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 418 |  |  |  | tse | [8 empty] | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 418 |  |  |  | tse | [8 empty] | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 418 |  |  |  | tse | [8 empty] | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 418 |  | Total |  | tse | [5 empty] | 47.8365 | 0.047837 |  | TA 418 - DPR - 2026-07-21.xlsx | Stringing Completed | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 0A/0 | 0B/0 | Saheb Enterprises | Manual | Completed |  |  |  | 2026-05-22 | 447.34 | 0.44734 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TA 419 | 0B/0 | 0C/0 | Saheb Enterprises | TSE | Completed |  |  |  | 2026-07-26 | 1594.82 | 1.5948 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TA 419 | 0C/0 | 0D/0 | Saheb Enterprises | TSE | Completed |  |  |  | 2026-07-12 | 793.45 | 0.79345 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TA 419 | 0D/5 | 0E/0 | Alimuddin | Manual | Completed |  |  |  | 2026-06-24 | 449.69 | 0.44969 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TA 419 | 0E/0 | 0F/0 | Saheb Enterprises | TSE | WIP |  |  |  |  | 1238.46 | 1.2385 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 0F/0 | 0G/0 | Alimuddin | Manual | Completed |  |  |  | 2026-07-27 | 283.43 | 0.28343 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TA 419 | 0G/0 | 0H/0 | Alimuddin | TSE | Completed |  |  |  | 2026-07-29 | 799.95 | 0.79995 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TA 419 | 0H/0 | 1/0 | Dharmendra | Manual | Completed |  |  |  | 2026-08-04 | 245.33 | 0.24533 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TA 419 | 1/0 | 2/0 | Enamul | Manual | WIP |  | 2026-07-28 |  |  | 199.37 | 0.19937 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 2/0 | 3/0 | Enamul | Manual | Completed |  |  |  | 2026-07-30 | 263.38 | 0.26338 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TA 419 | 3/0 | 4/0 |  | TSE | [5 empty] | 2405.48 | 2.4055 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 4/0 | 5/0 | Mussoluddin | TSE | Completed |  |  |  | 2026-07-01 | 775.24 | 0.77524 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TA 419 | 5/0 | 6/0 | Mussoluddin | TSE | Completed |  |  |  | 2026-07-11 | 1991.87 | 1.9919 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TA 419 | 6/0 | 7/0 | Mussoluddin | TSE | WIP | 2026-07-12 |  |  |  | 4993.95 | 4.9939 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 7/0 | 8/0 |  | TSE | [5 empty] | 840.03 | 0.84003 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 8/0 | 9/0 |  | Manual | [5 empty] | 339.15 | 0.33915 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 9/0 | 10/0 |  | Manual | [5 empty] | 473.56 | 0.47356 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 10/0 | 11/0 |  | Manual | [5 empty] | 264.19 | 0.26419 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 11/0 | 11/1 |  | TSE | [5 empty] | 378.01 | 0.37801 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 11/1 | 11/2 |  | TSE | [5 empty] | 484.94 | 0.48494 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 11/2 | 12/0 |  | TSE | [5 empty] | 1185.91 | 1.1859 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 12/0 | 12A/0 |  | TSE | [5 empty] | 1141.1 | 1.1411 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 12A/0 | 13/0 |  | TSE | [5 empty] | 840.33 | 0.84033 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 13/0 | 14/0 |  | Manual | [5 empty] | 277.65 | 0.27765 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 14/0 | 15/0 |  | TSE | [5 empty] | 700.36 | 0.70036 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 15/0 | 15A/0 |  | Manual | [5 empty] | 282.44 | 0.28244 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 15A/0 | 16/0 |  | Manual | [5 empty] | 247.43 | 0.24743 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 16/0 | 17/0 |  | Manual | [5 empty] | 364.22 | 0.36422 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 17/0 | 18/0 |  | TSE | [5 empty] | 1084.26 | 1.0843 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 18/0 | 19/0 |  | Manual | [5 empty] | 357.44 | 0.35744 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 19/0 | 20/0 |  | TSE | [5 empty] | 2321.07 | 2.3211 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 20/0 | 20/3 |  | TSE | [5 empty] | 1081.63 | 1.0816 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 20/3 | 21/0 |  | Manual | [5 empty] | 358.52 | 0.35852 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 21/0 | 22/0 |  | Manual | [5 empty] | 238.09 | 0.23809 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 22/0 | 23/0 |  | TSE | [5 empty] | 1531.84 | 1.5318 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 23/0 | 24/0 |  | TSE | [5 empty] | 1521.57 | 1.5216 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 24/0 | 25/0 |  | TSE | [5 empty] | 1524.48 | 1.5245 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 25/0 | 26/0 |  | Manual | [5 empty] | 221.32 | 0.22132 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 26/0 | 27/0 |  | TSE | [5 empty] | 2761.28 | 2.7613 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 27/0 | 28/0 |  | TSE | [5 empty] | 1507.39 | 1.5074 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 28/0 | 29/0 |  | TSE | [5 empty] | 739.92 | 0.73992 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 29/0 | 30/0 |  | Manual | [5 empty] | 207.12 | 0.20712 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 30/0 | 31/0 |  | TSE | [5 empty] | 785.64 | 0.78564 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 31/0 | 32/0 |  | TSE | [5 empty] | 1169.33 | 1.1693 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 32/0 | 33/0 |  | Manual | [5 empty] | 269.5 | 0.2695 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 33/0 | 34/0 |  | TSE | [5 empty] | 708.89 | 0.70889 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 34/0 | 35/0 |  | TSE | [5 empty] | 774.54 | 0.77454 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 35/0 | 36/0 |  | Manual | [5 empty] | 246.98 | 0.24698 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 36/0 | 36/4 |  | TSE | [5 empty] | 1617.64 | 1.6176 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 36/4 | 37/0 |  | TSE | [5 empty] | 2789.12 | 2.7891 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 37/0 | 38/0 |  | Manual | [5 empty] | 262.38 | 0.26238 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 38/0 | 39/0 |  | TSE | [5 empty] | 4947 | 4.947 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 39/0 | 40/0 |  | Manual | [5 empty] | 200.61 | 0.20061 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 40/0 | 41/0 |  | TSE | [5 empty] | 4067.61 | 4.0676 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 41/0 | 42/0 |  | TSE | [5 empty] | 3468.86 | 3.4689 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 42/0 | 43/0 |  | Manual | [5 empty] | 219.42 | 0.21942 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 43/0 | 44/0 |  | TSE | [5 empty] | 2622.21 | 2.6222 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 44/0 | 45/0 |  | Manual | [5 empty] | 446.79 | 0.44679 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 45/0 | 46/0 |  | Manual | [5 empty] | 233.98 | 0.23398 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 46/0 | 47/0 |  | TSE | [5 empty] | 2072.07 | 2.0721 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 47/0 | 48/0 |  | Manual | [5 empty] | 349.44 | 0.34944 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 48/0 | 49/0 |  | TSE | [5 empty] | 808.59 | 0.80859 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 49/0 | 50/0 |  | Manual | [5 empty] | 207.14 | 0.20714 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 50/0 | 50/1 |  | Manual | [5 empty] | 482.87 | 0.48287 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 50/1 | 51/0 |  | Manual | [5 empty] | 370.42 | 0.37042 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 51/0 | 52/0 |  | Manual | [5 empty] | 252.5 | 0.2525 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 52/0 | 53/0 |  | TSE | [5 empty] | 1015.88 | 1.0159 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 53/0 | 54/0 |  | Manual | [5 empty] | 219.62 | 0.21962 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 54/0 | 55/0 |  | TSE | [5 empty] | 3182.59 | 3.1826 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 55/0 | 56/0 |  | TSE | [5 empty] | 2583.14 | 2.5831 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 56/0 | 57/0 |  | Manual | [5 empty] | 221.82 | 0.22182 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 57/0 | 58/0 |  | TSE | [5 empty] | 819.68 | 0.81968 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 58/0 | 59/0 |  | Manual | [5 empty] | 294.64 | 0.29464 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 59/0 | 60/0 |  | TSE | [5 empty] | 620.1 | 0.6201 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 60/0 | 61/0 |  | Manual | [5 empty] | 193.99 | 0.19399 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 61/0 | 62/0 |  | TSE | [5 empty] | 817.16 | 0.81716 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 62/0 | 63/0 |  | TSE | [5 empty] | 2455.63 | 2.4556 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 63/0 | 63A/0 |  | TSE | [5 empty] | 2624.87 | 2.6249 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 63A/0 | 63B/0 |  | Manual | [5 empty] | 350.46 | 0.35046 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 63B/0 | 64/0 |  | TSE | [5 empty] | 2771.42 | 2.7714 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 64/0 | 64/2 |  | TSE | [5 empty] | 769.94 | 0.76994 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 64/2 | 64A/0 |  | TSE | [5 empty] | 1614.14 | 1.6141 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 64A/0 | 65/0 |  | Manual | [5 empty] | 454.37 | 0.45437 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 65/0 | 66/0 |  | TSE | [5 empty] | 1169.06 | 1.1691 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 66/0 | 67/0 |  | TSE | [5 empty] | 775.69 | 0.77569 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 67/0 | 68/0 |  | Manual | [5 empty] | 368.45 | 0.36845 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 68/0 | 69/0 |  | Manual | [5 empty] | 349.57 | 0.34957 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 69/0 | 70/0 |  | Manual | [5 empty] | 420.91 | 0.42091 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 70/0 | 71/0 |  | Manual | [5 empty] | 309.86 | 0.30986 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 71/0 | 72/0 |  | Manual | [5 empty] | 364.16 | 0.36416 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 72/0 | 73/0 |  | Manual | [5 empty] | 208.46 | 0.20846 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 73/0 | 74/0 |  | Manual | [5 empty] | 395.52 | 0.39552 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 74/0 | 75/0 |  | Manual | [5 empty] | 266.46 | 0.26646 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 75/0 | 76/0 |  | Manual | [5 empty] | 209.25 | 0.20925 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 76/0 | 77/0 |  | TSE | [5 empty] | 1639.09 | 1.6391 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 77/0 | 78/0 |  | Manual | [5 empty] | 394.65 | 0.39465 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 78/0 | 78A/0 |  | TSE | [5 empty] | 2033.85 | 2.0339 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 78A/0 | 79/0 |  | Manual | [5 empty] | 430.8 | 0.4308 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 79/0 | 80/0 |  | Manual | [5 empty] | 240.54 | 0.24054 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 80/0 | 81/0 |  | Manual | [5 empty] | 255.15 | 0.25515 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 81/0 | 82/0 |  | Manual | [5 empty] | 188.84 | 0.18884 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 82/0 | 83/0 |  | Manual | [5 empty] | 397.99 | 0.39799 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 83/0 | 84/0 |  | TSE | [5 empty] | 3875.28 | 3.8753 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 84/0 | 84A/0 |  | TSE | [5 empty] | 2169.66 | 2.1697 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 84A/0 | 85/0 |  | TSE | [5 empty] | 670.06 | 0.67006 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 85/0 | 85A/0 |  | Manual | [5 empty] | 289.67 | 0.28967 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 85A/0 | 86/0 |  | Manual | [5 empty] | 385.12 | 0.38512 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 86/0 | 86A/0 |  | TSE | [5 empty] | 348.96 | 0.34896 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 86A/0 | 86A/4 |  | TSE | [5 empty] | 1032.86 | 1.0329 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 86A/4 | 87/0 |  | TSE | [5 empty] | 1650 | 1.65 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 87/0 | 88/0 |  | TSE | [5 empty] | 804.23 | 0.80423 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 88/0 | 89/0 |  | TSE | [5 empty] | 1081.94 | 1.0819 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 89/0 | 90/0 |  | Manual | [5 empty] | 1071.87 | 1.0719 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 90/0 | 90A/0 |  | Manual | [5 empty] | 324.41 | 0.32441 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 90A/0 | 90B/0 |  | TSE | [5 empty] | 284.15 | 0.28415 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 90B/0 | 91/0 |  | Manual | [5 empty] | 637.67 | 0.63767 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 91/0 | 92/0 |  | Manual | [5 empty] | 215.08 | 0.21508 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 92/0 | 93/0 |  | Manual | [5 empty] | 381.67 | 0.38167 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 93/0 | 93A/0 |  | Manual | [5 empty] | 255.59 | 0.25559 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 93A/0 | 93B/0 |  | Manual | [5 empty] | 351.25 | 0.35125 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 93B/0 | 93C/0 |  | Manual | [5 empty] | 369.96 | 0.36996 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 93C/0 | 94/0 |  | Manual | [5 empty] | 260 | 0.26 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 94/0 | 95/0 |  | Manual | [5 empty] | 166.6 | 0.1666 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 95/0 | 95A/0 |  | Manual | [5 empty] | 486.78 | 0.48678 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 95A/0 | 96/0 |  | Manual | [5 empty] | 179 | 0.179 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 96/0 | 96/1 |  | Manual | [5 empty] | 153.59 | 0.15359 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 96/1 | 97/0 |  | TSE | [5 empty] | 367.88 | 0.36788 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 97/0 | 98/0 |  | Manual | [5 empty] | 814.93 | 0.81493 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 98/0 | 99/0 |  | Manual | [5 empty] | 292.64 | 0.29264 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 99/0 | 100/0 |  | Manual | [5 empty] | 103.1 | 0.1031 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 100/0 | 101/0 |  | Manual | [5 empty] | 183.67 | 0.18367 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 101/0 | GANTRY |  | Manual | [5 empty] | 115.31 | 0.11531 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | GNT 1 | GNT 2 |  | Manual | [5 empty] | 78.28 | 0.07828 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | 100/0 |  |  | tse | [5 empty] | 0 | 0 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 | GNT 2 |  |  | tse | [5 empty] | 147.68 | 0.14768 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 419 |  | Total |  | tse | [5 empty] | 122206.18 | 122.2062 |  | TA 419 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 | 104/0 | 105/0 | Alimuddin | TSE | Done | 2026-03-07 | 2026-02-10 | 2026-04-12 | 2026-04-17 | 967 | 0.967 |  | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | PO Start > PO Complete (non-positive duration)
TA 505 | 147/0 | 147A/0 |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 | 147A/0 | 148/0 |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 | 99/0 | 100/0 |  | TSE | Wip | 2026-07-16 |  |  |  | 3478 | 3.478 |  | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 | 125/0 | 126/0 |  | TSE | Wip | 2026-07-16 |  |  |  | 742.55 | 0.74255 |  | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 | 155/0 | 156/0 |  | TSE | [5 empty] | 2306.85 | 2.3068 |  | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  |  |  | tse | [8 empty] | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 505 |  | Total |  | tse | [5 empty] | 48.0924 | 0.048092 |  | TA 505 - DPR - 2026-07-29.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 | 134/0 | 135/0 | Rejaul Sekh | Manual |  | 2026-07-27 | 2026-08-01 |  |  | 841.878 | 0.84188 |  | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 | 25/0 | 26/0 | MA Traders | TSE |  | 2026-08-01 | 2026-08-04 |  |  | 1168.067 | 1.1681 |  | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 | 202/0 | 203/0 | National Construction | TSE |  | 2026-08-04 | 2026-08-06 | 2026-08-07 |  | 1255.763 | 1.2558 |  | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid F/S Complete Date
TA 506 | 35/0 | 35A/0 | Afajal hossain | Manual |  | 2026-08-04 | 2026-08-05 |  |  | 378.85 | 0.37885 |  | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 | 201/0 | 202/0 | National Construction | Manual |  | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | 462.456 | 0.46246 |  | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid F/S Complete Date
TA 506 | 26/0 | 27/0 | MA Traders | Manual |  | 2026-08-07 | 2026-08-07 |  |  | 764.386 | 0.76439 |  | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 | 135/0 | 135/2 | Rejaul Sekh | Manual |  | 2026-08-07 |  |  |  | 831 | 0.831 |  | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  |  |  | tse | [8 empty] | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TA 506 |  | Total |  | tse | [5 empty] | 83.152 | 0.083152 |  | TA 506 - DPR - 2026-08-07.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | From | To |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 11A/0 | 12/0 | Nasiruddin | TSE |  | 2026-05-18 | 2026-05-16 | 2026-05-27 | 2026-05-29 | 4110 | 4.11 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | PO Start > PO Complete (non-positive duration)
TB 408 | 22/0 | 22/8 | MC Power | TSE |  | 2026-08-21 | 2026-07-26 | 2026-07-23 | 2026-07-27 | 3177.1 | 3.1771 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | PO Start > PO Complete (non-positive duration)
TB 408 | 31/0 | 32/0 | Jamera Bibi | TSE | [5 empty] | 1082.5 | 1.0825 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 16/0 | 17/0 | Nasiruddin | TSE |  | 2026-07-11 | 2026-07-15 | 2026-07-28 |  | 2336.2 | 2.3362 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid F/S Complete Date
TB 408 | 28/0 | 29/0 | Mohammad Construction / Furkhan | TSE |  | 2026-07-27 |  |  |  | 3639.1 | 3.6391 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 17/0 | 18/0 | Nasiruddin | TSE |  | 2026-07-27 |  | 2026-07-29 |  | 2451 | 2.451 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Complete Date; Missing/Invalid F/S Complete Date
TB 408 | 25/0 | 26/0 | MC Power | TSE | [5 empty] | 1970 | 1.97 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [5 empty] | 158385.54 | 158.3855 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 20/0 | 21/0 | Gang Not Allocated | TSE | [5 empty] | 1480 | 1.48 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 21/0 | 22/0 | Gang Not Allocated | TSE | [5 empty] | 4580 | 4.58 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 26/0 | 27/0 | Gang Not Allocated | TSE | [5 empty] | 3660 | 3.66 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 32/0 | 33/0 | Tata Projects Limited | TSE | [5 empty] | 2075 | 2.075 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 33/0 | 34/0 | Tata Projects Limited | TSE | [5 empty] | 672 | 0.672 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 34/0 | 35/0 | Tata Projects Limited | TSE | [5 empty] | 2048 | 2.048 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 35/0 | 35/2 | Tata Projects Limited | TSE | [5 empty] | 758 | 0.758 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 35/2 | 35/3 | Tata Projects Limited | M | [5 empty] | 522 | 0.522 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 35/3 | 36/0 | Tata Projects Limited | TSE | [5 empty] | 1183 | 1.183 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 36/0 | 37/0 | Tata Projects Limited | TSE | [5 empty] | 1884.5 | 1.8845 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 37/0 | 38/0 | Tata Projects Limited | TSE | [5 empty] | 1640 | 1.64 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 38/0 | 39/0 | Tata Projects Limited | TSE | [5 empty] | 2101 | 2.101 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 39/0 | 40/0 | Tata Projects Limited | TSE | [5 empty] | 735 | 0.735 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 40/0 | 41/0 | Tata Projects Limited | TSE | [5 empty] | 1660 | 1.66 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 41/0 | 42/0 | Tata Projects Limited | TSE | [5 empty] | 1170.9 | 1.1709 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 42/0 | 43/0 | Tata Projects Limited | TSE | [5 empty] | 2667 | 2.667 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 18/0 | 19/0 | Tata Projects Limited | TSE | [5 empty] | 1910 | 1.91 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 19/0 | 20/0 | Tata Projects Limited | TSE | [5 empty] | 2260 | 2.26 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [5 empty] | 23286.4 | 23.2864 |  | TB 408 - DPR - 2026-07-30.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 412 | 46/0 | DD+3 | Nav Durga Traders | tse | RCC WIP | 2026-08-02 | [6 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid F/S Complete Date
TB 412 | 33/0 | DD+0 | Rajeshwar | tse | Pit Marking Completed | 2026-08-08 | [6 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid F/S Complete Date
TB 412 |  |  |  | tse | [8 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date; Missing/Invalid F/S Complete Date
TB 412 |  |  |  | tse | [8 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date; Missing/Invalid F/S Complete Date
TB 412 |  |  |  | tse | [8 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date; Missing/Invalid F/S Complete Date
TB 412 |  |  |  | tse | [8 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date; Missing/Invalid F/S Complete Date
TB 412 |  |  |  | tse | [8 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date; Missing/Invalid F/S Complete Date
TB 412 |  |  |  | tse | [8 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date; Missing/Invalid F/S Complete Date
TB 412 | 143/0 | DC+3 | Anmol | tse | ROW & Material Shifting | 2026-07-14 | [6 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid F/S Complete Date
TB 412 | 74/0 | DD+3 | Dharmendra Mishra | tse | Excavation WIP | 2026-07-09 | [6 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid F/S Complete Date
TB 412 | 70/2 | DA+3 1MRC | MAA | tse | 03 Pit RCC Done | 2026-07-13 | [6 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid F/S Complete Date
TB 412 | 61/2 | DA+9 | Shakti | tse | Material & Gang Shifting WIP | 2026-07-23 | [6 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid F/S Complete Date
TB 412 |  |  |  | tse | [8 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date; Missing/Invalid F/S Complete Date
TB 412 |  |  |  | tse | [8 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date; Missing/Invalid F/S Complete Date
TB 412 | LOC. NO. | T.O.T | GANG | tse | [8 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date; Missing/Invalid F/S Complete Date
TB 412 | 151/2 | DA+6 | Sonakshi Mobile | tse |  | 2026-08-02 | [6 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid F/S Complete Date
TB 412 | 106/0 | DD+9 | Sanjeev Kumar | tse |  | 2026-08-02 | [6 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid F/S Complete Date
TB 412 | 152/3 | DA+6 | Sonakshi Mobile | tse |  | 2026-08-05 | [6 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid F/S Complete Date
TB 412 | 104/5 | DA+3 | Sanjeev Kumar | tse |  | 2026-08-05 | [6 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid F/S Complete Date
TB 412 | 132/5 | DA+3 | Asfak Ahmad | tse |  | 2026-08-06 | [6 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid F/S Complete Date
TB 412 | 104/4 | DA+0 | Sanjeev Kumar | tse |  | 2026-08-07 | [6 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid F/S Complete Date
TB 412 | 3/0 | 2TNMD+0 | Yashoda Devi | tse |  |  |  |  | 1900-01-15 |  |  |  | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date
TB 412 | 113/1 | DA+6 | Kumkum Devi | tse |  |  |  |  | 1900-01-15 |  |  |  | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date
TB 412 | 150/0 | DD+0 | Sonakshi Mobile | tse |  |  |  |  | 1900-01-16 |  |  |  | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date
TB 412 | 8/0 | DD+0 | Rang | tse |  |  |  |  | 1900-01-24 |  |  |  | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date
TB 412 | 132/3 | DA+6 | Asfak Ahmad | tse |  |  |  |  | 1900-01-15 |  |  |  | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date
TB 412 |  |  |  | tse | [8 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date; Missing/Invalid F/S Complete Date
TB 412 | FROM | TO | GANG | tse | Remarks | [7 empty] | TB 412 - DPR - 2026-08-07.xlsx | WIP | Missing/Invalid PO Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | Hydro GTY | Existing Tower-1 |  | tse | [5 empty] | 58.79 | 0.05879 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | Existing Tower-1 | Exting Tower-2 |  | tse | [5 empty] | 149.12 | 0.14912 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | Exting Tower-2 | Exting Tower-3 |  | tse | [5 empty] | 128.1 | 0.1281 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | Exting Tower-3 | Exting Tower-4 |  | tse | [5 empty] | 252.72 | 0.25272 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | Exting Tower-4 | Exting Tower-5 |  | tse | [5 empty] | 146.74 | 0.14674 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | Exting Tower-5 | Exting Tapping Tower-6 |  | tse | [5 empty] | 190.05 | 0.19005 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | Exting Tapping Tower-6 | Exting Tower-7 |  | tse | [5 empty] | 84.7 | 0.0847 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | Exiting Tower-7 | SC-5 |  | tse | [5 empty] | 122.5 | 0.1225 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | SC-5 | SC-4 |  | tse | [5 empty] | 259.5 | 0.2595 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | SC-4 | Sc-3 |  | tse | [5 empty] | 256.6 | 0.2566 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | Sc-3 | SC-2 |  | tse | [5 empty] | 278 | 0.278 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | SC-2 | SC-1 |  | tse | [5 empty] | 201.9 | 0.2019 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | SC-1 | 1/0 |  | tse | [5 empty] | 62.76 | 0.06276 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 132kV | CPP | 1/0 |  | tse | C | 2026-06-29 | 2026-06-29 |  | 2026-07-01 | 48 | 0.048 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid F/S Start Date
TB 501 - 132kV | 1/0 | 2/0 |  | tse | C | 2026-06-29 | 2026-06-29 |  | 2026-07-01 | 226.7 | 0.2267 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid F/S Start Date
TB 501 - 132kV | 2/0 | 2/1 |  | tse | C | 2026-06-27 | 2026-06-28 |  | 2026-07-01 | 234.6 | 0.2346 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid F/S Start Date
TB 501 - 132kV | 2/1 | 3/0 |  | tse | C | 2026-06-27 | 2026-06-28 |  | 2026-07-01 | 285.2 | 0.2852 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid F/S Start Date
TB 501 - 132kV | 10/0 | 11/0 |  | tse | C |  |  | 2026-05-18 | 2026-05-19 | 215.1 | 0.2151 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-132KV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date
TB 501 - 220kV | 4/6 | 4/7 |  | tse | C | 2026-06-27 | 2026-06-27 | 2026-07-28 | 2025-07-28 | 360 | 0.36 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV
TB 501 - 220kV | 35/0 | Gantry |  | tse | [5 empty] | 80 | 0.08 |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | [8 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse |  | 1900-01-02 | [6 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse |  | 1900-01-14 |  |  | 0 |  |  |  | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TB 501 - 220kV |  |  |  | tse |  | 1900-01-05 | [6 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | 952 | 0 | [6 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | 173.57 | 0 | [6 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | 336.5 | 0 | [6 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | 900.14 | 0 | [6 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | 1697.24 | 0 | [6 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | 1600.078 | 0 | [6 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | 525.89 | 0 | [6 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | 356.279 | 0 | [6 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | 190.524 | 0 | [6 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 501 - 220kV |  |  |  | tse | 142.384 | 0 | [6 empty] | TB 501 - DPR - 2026-07-30.xlsx | Stringing-220kV | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 |  |  |  | tse | [8 empty] | TB 507 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 |  | Total |  | tse | [8 empty] | TB 507 - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN | 144/0 | 143/0 | Mahadev Enterprises | TSE | complete | 2026-03-23 | 2026-04-04 |  | 2026-04-04 | 3275 | 3.275 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid F/S Start Date
TB 507 - MAIN | 145/0 | 144/0 | Mahadev Enterprises | Manual | complete | 2026-04-09 |  |  | 2026-04-10 | 232 | 0.232 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TB 507 - MAIN | 113/0 | 112/0 | Mahadev Maan Construction | Manual | complete | 2026-04-09 | 2026-04-10 |  | 2026-04-15 | 158 | 0.158 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid F/S Start Date
TB 507 - MAIN | 153/0 | 152/0 | Mahadev Enterprises | Manual | complete | 2026-04-16 |  |  | 2026-04-17 | 243 | 0.243 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TB 507 - MAIN | 113A/0 | 113/0 | Mahadev Maan Construction | Manual | complete | 2026-04-10 | 2026-04-10 |  | 2026-04-18 | 201 | 0.201 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid F/S Start Date
TB 507 - MAIN | 151/0 | 150/0 | Mahadev Enterprises | Manual | complete | 2026-04-27 |  | 2026-04-25 | 2026-04-28 | 290 | 0.29 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Complete Date
TB 507 - MAIN | 152/0 | 151/0 | Mahadev Enterprises | Manual | complete | 2026-04-28 |  |  | 2026-04-29 | 419 | 0.419 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date
TB 507 - MAIN | 134/0 | 133/0 | Mahadev Enterprises | TSE | complete | 2026-04-29 | 2026-05-13 |  | 2026-05-15 | 3486 | 3.486 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid F/S Start Date
TB 507 - MAIN | 115/0 | 115/1 | SK Tajirul | Manual | ROW | 2026-05-25 |  |  |  | 425 | 0.425 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN | 76/0 | 77/0 | SK Tajirul | Manual | ROW | 2026-06-24 |  |  |  | 835 | 0.835 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN | 77/0 | 78/0 |  | TSE | ROW |  |  |  |  | 2306 | 2.306 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN | 131/0 | 132/0 | Mahadev Enterprises | TSE | WIP |  |  |  |  | 1159 | 1.159 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN | 132/0 | 133/0 | KP Group | TSE | WIP | 2026-07-19 | 2026-07-22 | 2027-07-23 | 2026-07-28 | 1934 | 1.934 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled
TB 507 - MAIN | 90/0 | 91/0 | Mahadev Enterprises-2 | Manual | ROW |  |  |  |  | 815 | 0.815 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN | 131/0 | 132/0 |  | TSE | [5 empty] | 1159 | 1.159 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN | 136/0 | 137/0 | Mahadev Enterprises | Manual | WIP | 2026-07-18 | 2026-07-21 |  |  | 356 | 0.356 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN | 137/0 | 138/0 | Mahadev Enterprises | Manual | [5 empty] | 427 | 0.427 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN | 138/0 | 139/0 | Mahadev Enterprises | TSE | WIP |  |  |  |  | 1438 | 1.438 |  | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN |  | Total |  | tse | [8 empty] | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN |  |  |  | tse | [8 empty] | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN |  |  |  | tse | [8 empty] | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN |  |  |  | tse | [8 empty] | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 507 - MAIN |  |  |  | tse | [8 empty] | TB 507 [MAIN] - DPR - 2026-08-06.xlsx | Stringing Compiled | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 605 |  |  |  | tse | [8 empty] | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 605 | AP46 | AP47 | Musludin | TSE | Pilot Paying out / Due to non availabilty of shutdown gang idle for last 2 days |  |  |  |  | 2216 | 2.216 |  | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 605 | AP29 | AP30 | Tariq | TSE | Insulator Hoisting |  |  |  |  | 2570 | 2.57 |  | TB 605 - DPR - 2026-08-05.xlsx | Stringing JS-Jammu | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date

## May Exclusions
target_month | workbook | project | project_code | project_name | configured_sheet | resolved_sheet | line_name | from_ap | to_ap | gang_name | method | status | length_m | length_km | po_start_date | po_completion_date | fs_starting_date | fs_complete_date | exclusion_reason
2026-08 | TA 413 - DPR - 2026-08-07.xlsx | TA413 | TA 413 | TA 413 | Stringing | Stringing |  | 43A/0 | 44/0 |  | TSE |  | 1584.546 | 1.5845 | 2026-08-01 | 2026-08-04 |  |  | Missing/invalid F/S completion date
2026-08 | TA 419 - DPR - 2026-08-06.xlsx | TA419 | TA 419 | TA 419 | Stringing Compiled | Stringing Compiled |  | 0H/0 | 1/0 | Dharmendra | Manual | Completed | 245.33 | 0.24533 |  |  |  | 2026-08-04 | Missing/invalid PO start date
2026-08 | TA 506 - DPR - 2026-08-07.xlsx | TA506 | TA 506 | TA 506 | Stringing | Stringing |  | 134/0 | 135/0 | Rejaul Sekh | Manual |  | 841.878 | 0.84188 | 2026-07-27 | 2026-08-01 |  |  | Missing/invalid F/S completion date
2026-08 | TA 506 - DPR - 2026-08-07.xlsx | TA506 | TA 506 | TA 506 | Stringing | Stringing |  | 25/0 | 26/0 | MA Traders | TSE |  | 1168.067 | 1.1681 | 2026-08-01 | 2026-08-04 |  |  | Missing/invalid F/S completion date
2026-08 | TA 506 - DPR - 2026-08-07.xlsx | TA506 | TA 506 | TA 506 | Stringing | Stringing |  | 202/0 | 203/0 | National Construction | TSE |  | 1255.763 | 1.2558 | 2026-08-04 | 2026-08-06 | 2026-08-07 |  | Missing/invalid F/S completion date
2026-08 | TA 506 - DPR - 2026-08-07.xlsx | TA506 | TA 506 | TA 506 | Stringing | Stringing |  | 35/0 | 35A/0 | Afajal hossain | Manual |  | 378.85 | 0.37885 | 2026-08-04 | 2026-08-05 |  |  | Missing/invalid F/S completion date
2026-08 | TA 506 - DPR - 2026-08-07.xlsx | TA506 | TA 506 | TA 506 | Stringing | Stringing |  | 201/0 | 202/0 | National Construction | Manual |  | 462.456 | 0.46246 | 2026-08-06 | 2026-08-06 | 2026-08-07 |  | Missing/invalid F/S completion date
2026-08 | TA 506 - DPR - 2026-08-07.xlsx | TA506 | TA 506 | TA 506 | Stringing | Stringing |  | 26/0 | 27/0 | MA Traders | Manual |  | 764.386 | 0.76439 | 2026-08-07 | 2026-08-07 |  |  | Missing/invalid F/S completion date
2026-08 | TA 506 - DPR - 2026-08-07.xlsx | TA506 | TA 506 | TA 506 | Stringing | Stringing |  | 135/0 | 135/2 | Rejaul Sekh | Manual |  | 831 | 0.831 | 2026-08-07 |  |  |  | Missing/invalid F/S completion date
2026-08 | TB 408 - DPR - 2026-07-30.xlsx | TB408 | TB 408 | TB 408 | Stringing | Stringing |  | 22/0 | 22/8 | MC Power | TSE |  | 3177.1 | 3.1771 | 2026-08-21 | 2026-07-26 | 2026-07-23 | 2026-07-27 | PO start after F/S completion
2026-08 | TB 412 - DPR - 2026-08-07.xlsx | TB412 | TB 412 | TB 412 | WIP | WIP |  | 46/0 | DD+3 | Nav Durga Traders | tse | RCC WIP |  |  | 2026-08-02 |  |  |  | Missing/invalid F/S completion date
2026-08 | TB 412 - DPR - 2026-08-07.xlsx | TB412 | TB 412 | TB 412 | WIP | WIP |  | 33/0 | DD+0 | Rajeshwar | tse | Pit Marking Completed |  |  | 2026-08-08 |  |  |  | Missing/invalid F/S completion date
2026-08 | TB 412 - DPR - 2026-08-07.xlsx | TB412 | TB 412 | TB 412 | WIP | WIP |  | 151/2 | DA+6 | Sonakshi Mobile | tse |  |  |  | 2026-08-02 |  |  |  | Missing/invalid F/S completion date
2026-08 | TB 412 - DPR - 2026-08-07.xlsx | TB412 | TB 412 | TB 412 | WIP | WIP |  | 106/0 | DD+9 | Sanjeev Kumar | tse |  |  |  | 2026-08-02 |  |  |  | Missing/invalid F/S completion date
2026-08 | TB 412 - DPR - 2026-08-07.xlsx | TB412 | TB 412 | TB 412 | WIP | WIP |  | 152/3 | DA+6 | Sonakshi Mobile | tse |  |  |  | 2026-08-05 |  |  |  | Missing/invalid F/S completion date
2026-08 | TB 412 - DPR - 2026-08-07.xlsx | TB412 | TB 412 | TB 412 | WIP | WIP |  | 104/5 | DA+3 | Sanjeev Kumar | tse |  |  |  | 2026-08-05 |  |  |  | Missing/invalid F/S completion date
2026-08 | TB 412 - DPR - 2026-08-07.xlsx | TB412 | TB 412 | TB 412 | WIP | WIP |  | 132/5 | DA+3 | Asfak Ahmad | tse |  |  |  | 2026-08-06 |  |  |  | Missing/invalid F/S completion date
2026-08 | TB 412 - DPR - 2026-08-07.xlsx | TB412 | TB 412 | TB 412 | WIP | WIP |  | 104/4 | DA+0 | Sanjeev Kumar | tse |  |  |  | 2026-08-07 |  |  |  | Missing/invalid F/S completion date

## Issues
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | Issue | MissingColumns | Rows | DailyRows
TA 413 - DPR - 2026-08-07.xlsx | TA413 | Stringing | Stringing |  |  | MISSING_NONCRITICAL_COLUMNS | Section Readiness, Gang Name | 49 | 0
TA 421 - DPR - 2026-07-11.xlsx | TA421 | ProGress Sheet | ProGress Sheet |  |  | MISSING_NONCRITICAL_COLUMNS | Method, Section Readiness, P/O Completion Date, F/S Starting Date | 60 | 0
TA 601 - DPR - 2026-08-07.xlsx | TA601 | Stringing Compiled | Stringing Compiled |  |  | EMPTY_SHEET |  | 0 | 0
TB 408 - DPR - 2026-07-30.xlsx | TB408 | Stringing | Stringing |  |  | MISSING_NONCRITICAL_COLUMNS | Section Readiness | 105 | 0
TB 412 - DPR - 2026-08-07.xlsx | TB412 | WIP | WIP |  |  | MISSING_NONCRITICAL_COLUMNS | Method, Section Readiness, P/O Completion Date, F/S Starting Date | 29 | 0
TB 501 - DPR - 2026-07-30.xlsx | TB501 | Stringing-132KV | Stringing-132KV | 132kV | config | MISSING_NONCRITICAL_COLUMNS | Method | 48 | 0
TB 501 - DPR - 2026-07-30.xlsx | TB501 | Stringing-220kV | Stringing-220kV | 220kV | config | MISSING_NONCRITICAL_COLUMNS | Method | 226 | 0
TB 507 - DPR - 2026-08-06.xlsx | TB507 | Stringing Compiled | Stringing Compiled |  |  | NO_DAILY |  | 2 | 0
TB 605 - DPR - 2026-08-05.xlsx | TB605 | Stringing JS-Jammu | Stringing JS-Jammu |  |  | MISSING_NONCRITICAL_COLUMNS | Section Readiness | 11 | 0

## README_Assumptions
Note | Rules
Compiled from DPR files: stringing sheet consolidation. | Preserve raw columns; diagnostics include column presence and date parsing; configured stringing sheets are processed independently with per-sheet line identity before concatenation; PO start to F/S complete inclusive for daily expansion.
Method fallback assumption | If Method is missing, infer using erection span depth: erection_locations<=2 => manual, >2 => tse, unresolved => tse fallback. Current inferred rows: 582.

## MicroPlanResponsibilities
project_key | project_name | plan_month | entity_type | entity_name | location_no | revenue_planned | revenue_realised | tower_weight | tower_type | manpower | power_tools_issued | material_feeding | starting_date | completion_date | tack_welding | final_checking
ta504 | TA504 | 2025-12-01 | Gang | None | AP11 → AP12 | 0 | 0 | 2745.5 | [5 empty] | 2025-12-01
ta504 | TA504 | 2025-12-01 | Gang | None | AP12 → AP13 | 0 | 0 | 2390.4 | [5 empty] | 2025-12-01
ta504 | TA504 | 2025-12-01 | Gang | None | AP17 → AP18 | 0 | 0 | 4054.2 | [5 empty] | 2025-12-01
ta506 | TA506 | 2025-12-01 | Gang | None | AP5-AP6 | 0 | 0 | 4932.33 | [5 empty] | 2025-12-01
ta506 | TA506 | 2025-12-01 | Gang | None | AP2-AP2A | 0 | 0 | 3291.6 | [5 empty] | 2025-12-01
ta506 | TA506 | 2025-12-01 | Gang | None | None | 0 | 0 | 8.2239 | [5 empty] | 2025-12-01
ta413 | TA413 | 2025-11-01 | Gang | Rahim Khan | 6/0 → 7/0 | 0 | 0 | 4901.236 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Gang | Rahim Khan | 5/0 → 5A/0 | 0 | 0 | 4418.389 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Gang | Rahim Khan | 5A/0 → 6/0 | 0 | 0 | 419.48 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Gang | Tanjira Bibi | 32A/0 → 33/0 | 0 | 0 | 840.439 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Gang | Tanjira Bibi | 32/0 → 32A/0 | 0 | 0 | 3283.51 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Gang | Tanjira Bibi | 33/0 → 34/0 | 0 | 0 | 4049.764 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Section Incharge | D | 6/0 → 7/0 | 0 | 0 | 4901.236 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Section Incharge | D | 5/0 → 5A/0 | 0 | 0 | 4418.389 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Section Incharge | D | 5A/0 → 6/0 | 0 | 0 | 419.48 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Section Incharge | E | 32A/0 → 33/0 | 0 | 0 | 840.439 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Section Incharge | E | 32/0 → 32A/0 | 0 | 0 | 3283.51 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Section Incharge | E | 33/0 → 34/0 | 0 | 0 | 4049.764 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Supervisor | A | 6/0 → 7/0 | 0 | 0 | 4901.236 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Supervisor | A | 5/0 → 5A/0 | 0 | 0 | 4418.389 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Supervisor | B | 5A/0 → 6/0 | 0 | 0 | 419.48 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Supervisor | B | 32A/0 → 33/0 | 0 | 0 | 840.439 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Supervisor | C | 32/0 → 32A/0 | 0 | 0 | 3283.51 | [5 empty] | 2025-11-01
ta413 | TA413 | 2025-11-01 | Supervisor | C | 33/0 → 34/0 | 0 | 0 | 4049.764 | [5 empty] | 2025-11-01
ta418 | TA418 | 2025-11-01 | Gang | M/s SUFIYAN | 36/0 → 36/1 | 0 | 0 | 480 | [5 empty] | 2025-11-01
ta418 | TA418 | 2025-11-01 | Gang | M/s SUFIYAN | 35/0 → 36/0 | 0 | 0 | 4480 | [5 empty] | 2025-11-01
ta418 | TA418 | 2025-11-01 | Gang | M/s SUFIYAN | 34/0 → 35/0 | 0 | 0 | 1980 | [5 empty] | 2025-11-01
ta418 | TA418 | 2025-11-01 | Gang | M/s SUFIYAN | 40/0 → 41/0 | 0 | 0 | 2460 | [5 empty] | 2025-11-01
ta418 | TA418 | 2025-11-01 | Section Incharge | D | 36/0 → 36/1 | 0 | 0 | 480 | [5 empty] | 2025-11-01
ta418 | TA418 | 2025-11-01 | Section Incharge | D | 35/0 → 36/0 | 0 | 0 | 4480 | [5 empty] | 2025-11-01
ta418 | TA418 | 2025-11-01 | Section Incharge | D | 34/0 → 35/0 | 0 | 0 | 1980 | [5 empty] | 2025-11-01
ta418 | TA418 | 2025-11-01 | Section Incharge | D | 40/0 → 41/0 | 0 | 0 | 2460 | [5 empty] | 2025-11-01
ta418 | TA418 | 2025-11-01 | Supervisor | A | 36/0 → 36/1 | 0 | 0 | 480 | [5 empty] | 2025-11-01
ta418 | TA418 | 2025-11-01 | Supervisor | A | 35/0 → 36/0 | 0 | 0 | 4480 | [5 empty] | 2025-11-01
ta418 | TA418 | 2025-11-01 | Supervisor | B | 34/0 → 35/0 | 0 | 0 | 1980 | [5 empty] | 2025-11-01
ta418 | TA418 | 2025-11-01 | Supervisor | B | 40/0 → 41/0 | 0 | 0 | 2460 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Gang | M R Constructions | 17/0 → 18/0 | 0 | 0 | 1539 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Gang | M R Constructions | 16/0 → 17/0 | 0 | 0 | 4762 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Gang | M R Constructions | 15/0 → 16/0 | 0 | 0 | 1909 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Gang | M R Constructions | 34/0 → 34/1 | 0 | 0 | 248 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Gang | M R Constructions | 34/1 → 34/2 | 0 | 0 | 430 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Gang | M R Constructions | 34/2 → 35/0 | 0 | 0 | 248 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Gang | Nasiruddin | 13/0 → 14/0 | 0 | 0 | 4910 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Gang | Nasiruddin | 14/0 → 15/0 | 0 | 0 | 498 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Gang | Nasiruddin | 11/0 → 12/0 | 0 | 0 | 4751 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Satyam Tiwari | 17/0 → 18/0 | 0 | 0 | 1539 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Satyam Tiwari | 16/0 → 17/0 | 0 | 0 | 4762 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Satyam Tiwari | 15/0 → 16/0 | 0 | 0 | 1909 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Satyam Tiwari | 34/0 → 34/1 | 0 | 0 | 248 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Satyam Tiwari | 34/1 → 34/2 | 0 | 0 | 430 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Satyam Tiwari | 34/2 → 35/0 | 0 | 0 | 248 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Godvin John | 13/0 → 14/0 | 0 | 0 | 4910 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Godvin John | 14/0 → 15/0 | 0 | 0 | 498 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Section Incharge | Mr. Godvin John | 11/0 → 12/0 | 0 | 0 | 4751 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Manoj Mahto/Mr.Chandrasekharan | 17/0 → 18/0 | 0 | 0 | 1539 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Manoj Mahto/Mr.Chandrasekharan | 16/0 → 17/0 | 0 | 0 | 4762 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Manoj Mahto/Mr.Chandrasekharan | 15/0 → 16/0 | 0 | 0 | 1909 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Manoj Mahto/Mr.Chandrasekharan | 34/0 → 34/1 | 0 | 0 | 248 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Manoj Mahto/Mr.Chandrasekharan | 34/1 → 34/2 | 0 | 0 | 430 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Supervisor | Mr. Manoj Mahto/Mr.Chandrasekharan | 34/2 → 35/0 | 0 | 0 | 248 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Supervisor | Mr.Susanth Pal | 13/0 → 14/0 | 0 | 0 | 4910 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Supervisor | Mr.Susanth Pal | 14/0 → 15/0 | 0 | 0 | 498 | [5 empty] | 2025-11-01
ta421 | TA421 | 2025-11-01 | Supervisor | Mr.Susanth Pal | 11/0 → 12/0 | 0 | 0 | 4751 | [5 empty] | 2025-11-01

## MicroPlanIndex
file_path | project_name | project_key | rows_cleaned | status | error | plan_month
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\December 2025\Micro Plan - Dec'25 - TA418.xlsx | TA418 | ta418 | 0 | error | Header row not found on sheet 'Stringing' (best_score=1). | 2025-12-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\December 2025\Micro Plan - TA-416 Dec'25.xlsx | TA416 | ta416 | 0 | error | Header row not found on sheet 'FDN-June25' (best_score=0). | 2025-12-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\December 2025\Micro Plan - TA-504 Dec'25.xlsx | TA504 | ta504 | 3 | ok |  | 2025-12-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\December 2025\Micro Plan - TA-506 Dec'25.xlsx | TA506 | ta506 | 3 | ok |  | 2025-12-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-325 Nov 25.xlsx | TA325 | ta325 | 0 | error | Header row not found on sheet 'FDN-June25' (best_score=0). | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-413 Nov'25.xlsx | TA413 | ta413 | 6 | ok |  | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-416 Nov'25.xlsx | TA416 | ta416 | 0 | error | Header row not found on sheet 'FDN-June25' (best_score=0). | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-418 Nov'25.xlsx | TA418 | ta418 | 4 | ok |  | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-419 Nov'25.xlsx | TA419 | ta419 | 0 | error | Header row not found on sheet 'Stub dispatch' (best_score=0). | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-421 Nov'25.xlsx | TA421 | ta421 | 9 | ok |  | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-504 Nov'25.xlsx | TA504 | ta504 | 0 | error | Header row not found on sheet 'FDN-June25' (best_score=0). | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-506 Nov'25.xlsx | TA506 | ta506 | 0 | error | Header row not found on sheet 'FDN-June25' (best_score=0). | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\November 2025\Micro Plan - TA-509 Nov'25.xlsx | TA509 | ta509 | 0 | error | 'location_no' | 2025-11-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-413 Oct'25.xlsx | TA413 | ta413 | 0 | error | Header row not found on sheet 'FDN-June25' (best_score=0). | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-416 Oct'25.xlsx | TA416 | ta416 | 0 | error | Header row not found on sheet 'FDN-June25' (best_score=0). | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-419 Oct'25.xlsx | TA419 | ta419 | 0 | error | Header row not found on sheet 'Stub dispatch' (best_score=0). | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TA-421 Oct'25.xlsx | TA421 | ta421 | 0 | error | Header row not found on sheet 'Stub dispatch' (best_score=0). | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan - TB-408 Oct'25.xlsx | TB408 | tb408 | 0 | error | Header row not found on sheet 'FDN-June25' (best_score=0). | 2025-10-01
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\October 2025\Micro Plan TA-505 Oct '25.xlsx | TA505 | ta505 | 0 | error | Header row not found on sheet 'Summary' (best_score=1). | 2025-10-01