## Erection Summary
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
4.34 | 4.23 | 4.4 | 4.82 | 5.1 | 4.45 | 16247.62 | 339 | 218 | 35.15 | 41 | 48.48 | 25 | 61.88 | 55 | 91.81 | 0 | 0 | 47.93
PCH | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | 4.12 | 4.12 | 4.18 | 4.41 | 4.59 | 4.17 | 6373.75 | 149 | 115 | 37.03 | 12 | 43.18 | 9 | 48.46 | 13 | 89.31 | 0 | 0 | 42.78
Mr. Arun Felbin | 4.78 | 4.51 | 4.6 | 5.46 | 5.78 | 4.72 | 9710.04 | 183 | 97 | 33.69 | 28 | 51.52 | 16 | 69.43 | 42 | 92.59 | 0 | 0 | 53.06
Mr. Dheeraj Vashishth | 3.21 | 3.46 | 4.12 | 3.28 | 2.43 | 3.38 | 163.83 | 7 | 6 | 22.79 | 1 | 27.09 | 0 | 0 | 0 | 0 | 0 | 0 | 23.4
[6 empty] | Total | 16247.62 | 339
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA413 | 4.54 | 3.99 | 3.87 | 5.24 | 5.44 | 4.39 | 726.46 | 13 | 9 | 38.96 | 0 | 0 | 2 | 74.44 | 2 | 113.45 | 0 | 0 | 55.88
Mr. Sanjay Kumar Gupta | TA419 | 3.66 | 3.74 | 3.82 | 3.71 | 3.23 | 3.72 | 2240.6 | 41 | 33 | 41.27 | 0 | 0 | 2 | 85.98 | 6 | 117.79 | 0 | 0 | 54.65
Mr. Sanjay Kumar Gupta | TA512 | 4.96 | 4.8 | 4.97 | 4.78 | 4.43 | 4.83 | 1082.47 | 28 | 26 | 38.27 | 1 | 55.45 | 1 | 31.96 | 0 | 0 | 0 | 0 | 38.66
Mr. Sanjay Kumar Gupta | TB401 | 4.64 | 4.92 | 4.17 | 0 | 0 | 4.74 | 460.39 | 11 | 10 | 40.28 | 1 | 57.6 | 0 | 0 | 0 | 0 | 0 | 0 | 41.85
Mr. Sanjay Kumar Gupta | TB408 | 4.68 | 5.03 | 6.01 | 5.32 | 0 | 5.3 | 1417.45 | 31 | 25 | 39.08 | 5 | 62.27 | 0 | 0 | 1 | 129.11 | 0 | 0 | 45.72
Mr. Sanjay Kumar Gupta | TB507 | 2.26 | 2.21 | 2.23 | 3 | 5.28 | 2.45 | 446.39 | 25 | 12 | 14.25 | 5 | 18.76 | 4 | 20.84 | 4 | 24.56 | 0 | 0 | 17.86
Mr. Arun Felbin | TA325 | 4.41 | 3.66 | 3.24 | 3.19 | 4.67 | 3.92 | 2603.48 | 24 | 2 | 38.59 | 2 | 86.65 | 1 | 101.85 | 19 | 118.48 | 0 | 0 | 108.48
Mr. Arun Felbin | TA414 | 3.04 | 3.48 | 3.74 | 4.49 | 4.4 | 3.88 | 692.65 | 15 | 11 | 37.69 | 1 | 62.95 | 1 | 61.55 | 2 | 76.79 | 0 | 0 | 46.18
Mr. Arun Felbin | TA416 | 4.54 | 4.02 | 3.78 | 2.81 | 0 | 4.1 | 585.11 | 7 | 3 | 46.49 | 0 | 0 | 2 | 117.37 | 2 | 105.45 | 0 | 0 | 83.59
Mr. Arun Felbin | TA418 | 4.83 | 3.83 | 4.65 | 5.02 | 4.38 | 4.54 | 392 | 11 | 8 | 29.62 | 1 | 51 | 2 | 52 | 0 | 0 | 0 | 0 | 35.64
Mr. Arun Felbin | TA421 | 6.84 | 7.38 | 7.9 | 13.81 | 11.94 | 8.08 | 1026.86 | 21 | 12 | 34.87 | 5 | 57.37 | 1 | 101.9 | 3 | 73.24 | 0 | 0 | 48.9
Mr. Arun Felbin | TA504 | 5.25 | 5 | 5.24 | 5.4 | 5.13 | 5.21 | 951.33 | 17 | 7 | 38.28 | 5 | 64.97 | 3 | 66.67 | 2 | 79.25 | 0 | 0 | 55.96
Mr. Arun Felbin | TA505 | 4.8 | 4.88 | 5.1 | 5.43 | 5.86 | 5.11 | 2343.85 | 49 | 37 | 37.62 | 4 | 57.48 | 3 | 69.47 | 5 | 102.73 | 0 | 0 | 47.83
Mr. Arun Felbin | TA506 | 4.52 | 3.88 | 3.18 | 3.54 | 4.08 | 3.92 | 1114.76 | 39 | 17 | 18.91 | 10 | 31.36 | 3 | 32.83 | 9 | 42.35 | 0 | 0 | 28.58
Mr. Dheeraj Vashishth | TA513 | 3.58 | 3.87 | 4.12 | 4.12 | 0 | 3.9 | 107.75 | 4 | 3 | 26.89 | 1 | 27.09 | 0 | 0 | 0 | 0 | 0 | 0 | 26.94
Mr. Dheeraj Vashishth | TB605 | 2.84 | 3.05 | 0 | 2.43 | 2.43 | 2.68 | 56.08 | 3 | 3 | 18.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.69
[7 empty] | Total | 16247.63 | 339

## Project Gang Rankings
Top 3 Gangs
PCH | Project | Gang Name | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA419 | Jwala Singh | 5.99 | 185.64 | 5 | 5 | 37.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.13
Mr. Sanjay Kumar Gupta | TA512 | M S Kartik Mahto | 7.28 | 243.9 | 6 | 5 | 37.69 | 1 | 55.45 | 0 | 0 | 0 | 0 | 0 | 0 | 40.65
Mr. Sanjay Kumar Gupta | TA512 | M S Govind Mahto | 5.91 | 165.36 | 4 | 4 | 41.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.34
Mr. Sanjay Kumar Gupta | TA512 | M S Jwala Singh 2 | 5.25 | 183.23 | 5 | 5 | 36.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.65
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw | 3.65 | 65.67 | 4 | 3 | 15.65 | 0 | 0 | 1 | 18.73 | 0 | 0 | 0 | 0 | 16.42
Mr. Sanjay Kumar Gupta | TB507 | Namechand Mahto | 3.4 | 118.84 | 6 | 2 | 17.05 | 1 | 21.67 | 2 | 20.84 | 1 | 21.41 | 0 | 0 | 19.81
Mr. Sanjay Kumar Gupta | TB507 | Bhoi Enterprises | 2.47 | 65.45 | 4 | 2 | 12.84 | 1 | 16.82 | 1 | 22.95 | 0 | 0 | 0 | 0 | 16.36
Mr. Arun Felbin | TA418 | M S Tofit | 5.8 | 163 | 4 | 2 | 30 | 1 | 51 | 1 | 52 | 0 | 0 | 0 | 0 | 40.75
Mr. Arun Felbin | TA418 | M S Mdpl | 4.7 | 141 | 4 | 3 | 29.67 | 0 | 0 | 1 | 52 | 0 | 0 | 0 | 0 | 35.25
Mr. Arun Felbin | TA421 | Khatun | 11.3 | 326.78 | 6 | 2 | 32.69 | 2 | 58.94 | 0 | 0 | 2 | 71.76 | 0 | 0 | 54.46
Mr. Arun Felbin | TA421 | Subash | 11.11 | 384.54 | 10 | 8 | 33.78 | 2 | 57.16 | 0 | 0 | 0 | 0 | 0 | 0 | 38.45
Mr. Arun Felbin | TA504 | Punam Kumari 1 | 6.23 | 224.44 | 4 | 1 | 36.16 | 2 | 63.14 | 1 | 62 | 0 | 0 | 0 | 0 | 56.11
Mr. Arun Felbin | TA504 | Sainik Traders | 6 | 214.11 | 4 | 2 | 37.05 | 1 | 66.78 | 0 | 0 | 1 | 73.24 | 0 | 0 | 53.53
Mr. Arun Felbin | TA505 | Jwala Singh | 7.87 | 268.41 | 7 | 7 | 38.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.34
Mr. Arun Felbin | TA505 | Shila Devi | 7.02 | 232.59 | 4 | 2 | 39.98 | 1 | 55.45 | 0 | 0 | 1 | 97.17 | 0 | 0 | 58.15
Mr. Arun Felbin | TA505 | Jagannaath Saw Mp | 5.49 | 193.76 | 5 | 5 | 38.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.75
Mr. Arun Felbin | TA506 | Khemlal Mahto | 4.88 | 100.62 | 4 | 1 | 16.97 | 2 | 25.9 | 1 | 31.86 | 0 | 0 | 0 | 0 | 25.16
Mr. Arun Felbin | TA506 | Pankaj | 4.29 | 148.7 | 6 | 3 | 19.72 | 3 | 29.85 | 0 | 0 | 0 | 0 | 0 | 0 | 24.78
Mr. Arun Felbin | TA506 | Karni Const 2 | 4.01 | 108.81 | 4 | 2 | 16.99 | 1 | 28.37 | 0 | 0 | 1 | 46.47 | 0 | 0 | 27.2
Mr. Dheeraj Vashishth | TA513 | Anil Construction | 3.9 | 107.75 | 4 | 3 | 26.89 | 1 | 27.09 | 0 | 0 | 0 | 0 | 0 | 0 | 26.94
Bottom 3 Gangs
PCH | Project | Gang Name | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA419 | Jwala Singh | 5.99 | 185.64 | 5 | 5 | 37.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.13
Mr. Sanjay Kumar Gupta | TA512 | M S Punam Kumari 3 | 4.08 | 157.6 | 4 | 4 | 39.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.4
Mr. Sanjay Kumar Gupta | TA512 | M S Jwala Singh 2 | 5.25 | 183.23 | 5 | 5 | 36.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.65
Mr. Sanjay Kumar Gupta | TA512 | M S Govind Mahto | 5.91 | 165.36 | 4 | 4 | 41.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.34
Mr. Sanjay Kumar Gupta | TB507 | Bhoi Enterprises | 2.47 | 65.45 | 4 | 2 | 12.84 | 1 | 16.82 | 1 | 22.95 | 0 | 0 | 0 | 0 | 16.36
Mr. Sanjay Kumar Gupta | TB507 | Namechand Mahto | 3.4 | 118.84 | 6 | 2 | 17.05 | 1 | 21.67 | 2 | 20.84 | 1 | 21.41 | 0 | 0 | 19.81
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw | 3.65 | 65.67 | 4 | 3 | 15.65 | 0 | 0 | 1 | 18.73 | 0 | 0 | 0 | 0 | 16.42
Mr. Arun Felbin | TA418 | M S Mdpl | 4.7 | 141 | 4 | 3 | 29.67 | 0 | 0 | 1 | 52 | 0 | 0 | 0 | 0 | 35.25
Mr. Arun Felbin | TA418 | M S Tofit | 5.8 | 163 | 4 | 2 | 30 | 1 | 51 | 1 | 52 | 0 | 0 | 0 | 0 | 40.75
Mr. Arun Felbin | TA421 | Subash | 11.11 | 384.54 | 10 | 8 | 33.78 | 2 | 57.16 | 0 | 0 | 0 | 0 | 0 | 0 | 38.45
Mr. Arun Felbin | TA421 | Khatun | 11.3 | 326.78 | 6 | 2 | 32.69 | 2 | 58.94 | 0 | 0 | 2 | 71.76 | 0 | 0 | 54.46
Mr. Arun Felbin | TA504 | Sainik Traders | 6 | 214.11 | 4 | 2 | 37.05 | 1 | 66.78 | 0 | 0 | 1 | 73.24 | 0 | 0 | 53.53
Mr. Arun Felbin | TA504 | Punam Kumari 1 | 6.23 | 224.44 | 4 | 1 | 36.16 | 2 | 63.14 | 1 | 62 | 0 | 0 | 0 | 0 | 56.11
Mr. Arun Felbin | TA505 | Gokul Sarkar Mp | 5.13 | 143.67 | 4 | 4 | 35.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.92
Mr. Arun Felbin | TA505 | Crane Erc Team Mp | 5.31 | 168.38 | 4 | 3 | 36.29 | 1 | 59.5 | 0 | 0 | 0 | 0 | 0 | 0 | 42.1
Mr. Arun Felbin | TA505 | Jagannaath Saw Mp | 5.49 | 193.76 | 5 | 5 | 38.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.75
Mr. Arun Felbin | TA506 | Karni Const 1 | 2.84 | 109.42 | 4 | 2 | 16.99 | 0 | 0 | 0 | 0 | 2 | 37.72 | 0 | 0 | 27.35
Mr. Arun Felbin | TA506 | Karni Const 2 | 4.01 | 108.81 | 4 | 2 | 16.99 | 1 | 28.37 | 0 | 0 | 1 | 46.47 | 0 | 0 | 27.2
Mr. Arun Felbin | TA506 | Pankaj | 4.29 | 148.7 | 6 | 3 | 19.72 | 3 | 29.85 | 0 | 0 | 0 | 0 | 0 | 0 | 24.78
Mr. Dheeraj Vashishth | TA513 | Anil Construction | 3.9 | 107.75 | 4 | 3 | 26.89 | 1 | 27.09 | 0 | 0 | 0 | 0 | 0 | 0 | 26.94