## Erection Summary
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
3.79 | 4.19 | 4.1 | 3.91 | 3.97 | 4.28 | 4.3 | 4.32 | 4.4 | 4.3 | 4.23 | 4.4 | 4.84 | 5.26 | 4.21 | 44414.61 | 983 | 607 | 33.03 | 134 | 50.72 | 102 | 56.06 | 140 | 84.65 | 0 | 0 | 45.18
PCH | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | 3.99 | 4.05 | 3.83 | 3.86 | 3.96 | 4.12 | 4.13 | 4.1 | 4.2 | 4.11 | 4.16 | 4.23 | 4.58 | 4.31 | 4.01 | 18077.16 | 429 | 298 | 35.18 | 50 | 48.27 | 41 | 47.51 | 40 | 80.8 | 0 | 0 | 42.14
Mr. Arun Felbin | 3.71 | 4.22 | 4.25 | 3.99 | 3.94 | 4.45 | 4.51 | 4.6 | 4.77 | 4.7 | 4.47 | 4.79 | 5.39 | 6.02 | 4.38 | 25904.95 | 535 | 295 | 31.44 | 82 | 52.8 | 58 | 63.47 | 100 | 86.18 | 0 | 0 | 48.42
Mr. Dheeraj Vashishth | 3.21 | 4.76 | 4.7 | 3.63 | 4.19 | 4.11 | 3.86 | 3.72 | 3.49 | 3.26 | 3.5 | 3.28 | 3.28 | 0 | 3.77 | 432.5 | 19 | 14 | 20.64 | 2 | 27.09 | 3 | 29.78 | 0 | 0 | 0 | 0 | 22.76
[15 empty] | Total | 44414.61 | 983
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA413 | 4.18 | 4.26 | 3.8 | 3.89 | 3.63 | 4.21 | 4.22 | 4.41 | 4.68 | 4.31 | 3.94 | 4.09 | 5.52 | 5.44 | 4.13 | 4055.38 | 73 | 47 | 38.72 | 10 | 65.82 | 5 | 74.62 | 11 | 109.47 | 0 | 0 | 55.55
Mr. Sanjay Kumar Gupta | TA419 | 4.55 | 4.68 | 3.99 | 3.56 | 3.6 | 4.13 | 3.54 | 3.15 | 3.42 | 3.82 | 3.67 | 3.86 | 3.66 | 2.24 | 3.69 | 3432.83 | 63 | 48 | 40.62 | 1 | 69.38 | 5 | 83.9 | 9 | 110.45 | 0 | 0 | 54.49
Mr. Sanjay Kumar Gupta | TA512 | 5.13 | 4.87 | 4.81 | 5.33 | 4.84 | 4.71 | 5.48 | 5.67 | 5.09 | 4.89 | 4.86 | 4.82 | 4.77 | 4.22 | 4.98 | 2296.13 | 57 | 51 | 39.14 | 3 | 56.8 | 3 | 43.24 | 0 | 0 | 0 | 0 | 40.28
Mr. Sanjay Kumar Gupta | TB401 | 3.18 | 3.19 | 3.2 | 3.12 | 4.65 | 4.69 | 4.65 | 4.96 | 5.03 | 4.65 | 4.99 | 0 | 0 | 0 | 4.09 | 2230.61 | 46 | 36 | 41.52 | 6 | 61.49 | 2 | 73.94 | 2 | 109.51 | 0 | 0 | 48.49
Mr. Sanjay Kumar Gupta | TB408 | 4.4 | 4.43 | 4.74 | 4.5 | 4.39 | 4.27 | 4.39 | 4.15 | 4.53 | 4.8 | 5.39 | 5.95 | 5.07 | 0 | 4.66 | 4399.45 | 89 | 65 | 39.91 | 13 | 63.57 | 7 | 72.04 | 4 | 118.66 | 0 | 0 | 49.43
Mr. Sanjay Kumar Gupta | TB507 | 2.49 | 2.88 | 2.42 | 2.77 | 2.65 | 2.74 | 2.5 | 2.23 | 2.45 | 2.22 | 2.12 | 2.41 | 3.86 | 5.35 | 2.55 | 1662.77 | 101 | 51 | 12.33 | 17 | 18.85 | 19 | 19.66 | 14 | 24.29 | 0 | 0 | 16.46
Mr. Arun Felbin | TA325 | 2.93 | 4.1 | 4.09 | 3.81 | 3.54 | 3.62 | 3.96 | 4.36 | 4.62 | 4.25 | 3.57 | 3.12 | 3.53 | 0 | 3.92 | 7657.89 | 102 | 34 | 38.78 | 17 | 64.94 | 9 | 78.79 | 42 | 107.77 | 0 | 0 | 75.08
Mr. Arun Felbin | TA414 | 3.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.24 | 3.2 | 3.53 | 3.94 | 4.48 | 4.53 | 3.88 | 747.7 | 16 | 11 | 37.69 | 2 | 59 | 1 | 61.55 | 2 | 76.79 | 0 | 0 | 46.73
Mr. Arun Felbin | TA416 | 4.38 | 4.27 | 3.61 | 3.68 | 3.56 | 3.59 | 4.11 | 4.42 | 4.39 | 4.34 | 4.02 | 3.55 | 2.81 | 0 | 4.06 | 2643.72 | 32 | 10 | 45.12 | 4 | 67.98 | 10 | 97.97 | 8 | 117.6 | 0 | 0 | 82.62
Mr. Arun Felbin | TA418 | 2.65 | 2.66 | 2.81 | 2.89 | 2.99 | 3.08 | 3.48 | 2.87 | 3.65 | 4.57 | 3.96 | 4.75 | 4.92 | 0 | 3.4 | 1055 | 26 | 16 | 28.88 | 3 | 47 | 5 | 54.8 | 2 | 89 | 0 | 0 | 40.58
Mr. Arun Felbin | TA421 | 4.02 | 5.61 | 5.51 | 4.72 | 5.02 | 6.92 | 6.12 | 6.5 | 7.4 | 7.03 | 7.17 | 9.19 | 12.76 | 11.79 | 6.43 | 2682.41 | 61 | 45 | 36.11 | 10 | 57.96 | 1 | 101.9 | 5 | 75.23 | 0 | 0 | 43.97
Mr. Arun Felbin | TA504 | 4.03 | 4.13 | 4.1 | 3.91 | 4.02 | 4.46 | 4.17 | 4.63 | 5.07 | 5.23 | 5.02 | 5.28 | 5.39 | 3.75 | 4.71 | 1610.53 | 30 | 14 | 38.06 | 9 | 63.64 | 3 | 66.67 | 4 | 76.25 | 0 | 0 | 53.68
Mr. Arun Felbin | TA505 | 4.55 | 4.83 | 4.94 | 4.16 | 3.52 | 3.83 | 4 | 4.34 | 4.95 | 4.67 | 5 | 5.18 | 5.6 | 5.69 | 4.62 | 5271.62 | 109 | 75 | 37.23 | 13 | 59.3 | 11 | 67.94 | 10 | 96.12 | 0 | 0 | 48.36
Mr. Arun Felbin | TA506 | 3.84 | 3.97 | 4.68 | 4.79 | 4.95 | 5.63 | 5.72 | 5.05 | 4.88 | 4.27 | 3.52 | 3.29 | 3.64 | 4.35 | 4.54 | 4236.09 | 159 | 90 | 18.67 | 24 | 32.13 | 18 | 33.76 | 27 | 43.6 | 0 | 0 | 26.64
Mr. Dheeraj Vashishth | TA513 | 3.21 | 4.76 | 4.7 | 3.63 | 4.19 | 4.11 | 3.86 | 3.72 | 4.37 | 3.53 | 3.94 | 4.12 | 4.12 | 0 | 4.01 | 376.42 | 16 | 11 | 21.17 | 2 | 27.09 | 3 | 29.78 | 0 | 0 | 0 | 0 | 23.53
Mr. Dheeraj Vashishth | TB605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.62 | 2.98 | 3.05 | 2.43 | 2.43 | 0 | 2.67 | 56.08 | 3 | 3 | 18.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.69
[16 empty] | Total | 44414.63 | 983

## Project Gang Rankings
Top 3 Gangs
PCH | Project | Gang Name | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall | Manpower | Number of fitters | Total
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari 2 | 6.99 | 153.78 | 4 | 4 | 38.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.45 | 22 | 8 | 30 | Skill also high
Mr. Sanjay Kumar Gupta | TA413 | Ved Prakash | 6.78 | 640.81 | 5 | 0 | 0 | 1 | 66.78 | 0 | 0 | 4 | 143.51 | 0 | 0 | 128.16 | 28 | 13 | 41
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari 4 | 5.74 | 81.74 | 2 | 2 | 40.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.87 | 23 | 7 | 30
Mr. Sanjay Kumar Gupta | TA419 | Radha Enterprises 1 | 7.68 | 99.78 | 1 | 0 | 0 | 0 | 0 | 1 | 99.78 | 0 | 0 | 0 | 0 | 99.78 |  |  | 0
Mr. Sanjay Kumar Gupta | TA419 | Radha Enterprises | 6.23 | 137.05 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 137.05 | 0 | 0 | 137.05 |  |  | 0 |  | Jwala singh | 20 | 10 | Skill
Mr. Sanjay Kumar Gupta | TA419 | Mukhilal 2 | 5.83 | 139.97 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 139.97 | 0 | 0 | 139.97 | 19 | 10 | 29 |  | Poonam Kumari | 19 | 8 | Skill
Mr. Sanjay Kumar Gupta | TA512 | M S Kartik Mahto | 7.16 | 655.31 | 16 | 14 | 38.6 | 2 | 57.48 | 0 | 0 | 0 | 0 | 0 | 0 | 40.96 |  |  | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Govind Mahto | 5.91 | 165.36 | 4 | 4 | 41.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.34 |  |  | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Govind Mahto 2 | 5.42 | 37.93 | 1 | 1 | 37.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.93 |  |  | 0
Mr. Sanjay Kumar Gupta | TB401 | Chinta Devi | 10.29 | 92.6 | 2 | 2 | 46.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.3 |  |  | 0
Mr. Sanjay Kumar Gupta | TB401 | Sobha Devi | 9.08 | 45.41 | 1 | 1 | 45.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.41 |  |  | 0
Mr. Sanjay Kumar Gupta | TB401 | Panva Devi | 7.49 | 89.91 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 89.91 | 0 | 0 | 89.91 |  |  | 0
Mr. Sanjay Kumar Gupta | TB408 | Sobha Devi | 12.5 | 37.5 | 1 | 1 | 37.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.5 |  |  | 0
Mr. Sanjay Kumar Gupta | TB408 | Santosh Singh Laxmi | 7.86 | 47.18 | 1 | 1 | 47.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.18 |  |  | 0
Mr. Sanjay Kumar Gupta | TB408 | Shobha Devi | 6.73 | 693.03 | 13 | 8 | 43.11 | 3 | 67.87 | 2 | 72.26 | 0 | 0 | 0 | 0 | 53.31 |  |  | 0
Mr. Sanjay Kumar Gupta | TB507 | Rajesh Mahto | 4.2 | 16.82 | 1 | 0 | 0 | 1 | 16.82 | 0 | 0 | 0 | 0 | 0 | 0 | 16.82 |  |  | 0
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw | 3.65 | 65.67 | 4 | 3 | 15.65 | 0 | 0 | 1 | 18.73 | 0 | 0 | 0 | 0 | 16.42 |  |  | 0
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw 1 | 3.63 | 156.28 | 9 | 3 | 12 | 0 | 0 | 4 | 19.37 | 2 | 21.41 | 0 | 0 | 17.36 |  |  | 0
Mr. Arun Felbin | TA325 | Pc Construction | 7.53 | 97.93 | 1 | 0 | 0 | 0 | 0 | 1 | 97.93 | 0 | 0 | 0 | 0 | 97.93 |  |  | 0
Mr. Arun Felbin | TA325 | Nasirudin | 7.46 | 74.63 | 1 | 0 | 0 | 0 | 0 | 1 | 74.63 | 0 | 0 | 0 | 0 | 74.63 |  |  | 0
Mr. Arun Felbin | TA325 | Sakila Khatun | 6.88 | 336.97 | 3 | 0 | 0 | 1 | 65.76 | 0 | 0 | 2 | 135.61 | 0 | 0 | 112.32 |  |  | 0
Mr. Arun Felbin | TA414 | Sakhila Khatun | 7.34 | 168.88 | 3 | 1 | 38.04 | 0 | 0 | 1 | 61.55 | 1 | 69.29 | 0 | 0 | 56.29 |  |  | 0
Mr. Arun Felbin | TA414 | Rahul Kumar | 6.21 | 100.67 | 2 | 1 | 37.73 | 1 | 62.95 | 0 | 0 | 0 | 0 | 0 | 0 | 50.34 |  |  | 0
Mr. Arun Felbin | TA414 | Subhash | 5.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Mr. Arun Felbin | TA416 | Ananya Trader | 6.52 | 143.46 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 143.46 | 0 | 0 | 143.46 |  |  | 0
Mr. Arun Felbin | TA416 | Punam Kumari | 5.16 | 67.11 | 1 | 0 | 0 | 1 | 67.11 | 0 | 0 | 0 | 0 | 0 | 0 | 67.11 |  |  | 0
Mr. Arun Felbin | TA416 | Reeta Bharti | 4.84 | 101.69 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 101.69 | 0 | 0 | 101.69 |  |  | 0
Mr. Arun Felbin | TA418 | Subhash | 7.14 | 50 | 1 | 0 | 0 | 0 | 0 | 1 | 50 | 0 | 0 | 0 | 0 | 50 |  |  | 0
Mr. Arun Felbin | TA418 | M S Tofit | 4.82 | 386 | 8 | 3 | 29.67 | 2 | 48 | 2 | 56 | 1 | 89 | 0 | 0 | 48.25 |  |  | 0
Mr. Arun Felbin | TA418 | M S Mdpl | 3.12 | 318 | 7 | 4 | 29.25 | 0 | 0 | 2 | 56 | 1 | 89 | 0 | 0 | 45.43 |  |  | 0
Mr. Arun Felbin | TA421 | Khatun | 8.92 | 736.01 | 16 | 10 | 35.45 | 4 | 59.49 | 0 | 0 | 2 | 71.76 | 0 | 0 | 46 |  |  | 0
Mr. Arun Felbin | TA421 | Subash | 8.59 | 821.02 | 21 | 17 | 34.17 | 3 | 55.81 | 0 | 0 | 1 | 72.63 | 0 | 0 | 39.1 |  |  | 0
Mr. Arun Felbin | TA421 | Gauri Shankar Mahto | 6.66 | 139.83 | 2 | 1 | 37.93 | 0 | 0 | 1 | 101.9 | 0 | 0 | 0 | 0 | 69.92 |  |  | 0
Mr. Arun Felbin | TA504 | Punam Kumari 2 | 6.68 | 66.78 | 1 | 0 | 0 | 1 | 66.78 | 0 | 0 | 0 | 0 | 0 | 0 | 66.78 |  |  | 0
Mr. Arun Felbin | TA504 | Punam Kumari 1 | 6.23 | 224.44 | 4 | 1 | 36.16 | 2 | 63.14 | 1 | 62 | 0 | 0 | 0 | 0 | 56.11 |  |  | 0
Mr. Arun Felbin | TA504 | Pinki Devi | 5.63 | 142.1 | 3 | 2 | 36.36 | 1 | 69.38 | 0 | 0 | 0 | 0 | 0 | 0 | 47.37 |  |  | 0
Mr. Arun Felbin | TA505 | Jhemon Mahato 1 | 6.94 | 97.17 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 97.17 | 0 | 0 | 97.17 |  |  | 0
Mr. Arun Felbin | TA505 | Deglal Mahato | 6.58 | 590.98 | 10 | 5 | 39.48 | 1 | 65.03 | 1 | 67.26 | 3 | 87.09 | 0 | 0 | 59.1 |  |  | 0
Mr. Arun Felbin | TA505 | Shila Devi | 6.23 | 386.17 | 7 | 4 | 37.93 | 1 | 55.45 | 1 | 81.83 | 1 | 97.17 | 0 | 0 | 55.17 |  |  | 0
Mr. Arun Felbin | TA506 | Zainab Fatima | 6.83 | 34.17 | 1 | 0 | 0 | 1 | 34.17 | 0 | 0 | 0 | 0 | 0 | 0 | 34.17 |  |  | 0
Mr. Arun Felbin | TA506 | Tejal Mahto | 5.79 | 121.69 | 4 | 1 | 18.12 | 1 | 34.17 | 2 | 34.7 | 0 | 0 | 0 | 0 | 30.42 |  |  | 0
Mr. Arun Felbin | TA506 | Karni Const 2 | 4.95 | 351.3 | 12 | 7 | 18.78 | 1 | 28.37 | 0 | 0 | 4 | 47.87 | 0 | 0 | 29.27 |  |  | 0
Mr. Dheeraj Vashishth | TA513 | Anil Construction | 4.01 | 376.42 | 16 | 11 | 21.17 | 2 | 27.09 | 3 | 29.78 | 0 | 0 | 0 | 0 | 23.53 |  |  | 0
Mr. Dheeraj Vashishth | TB605 | Raj Labour Suppliers | 2.67 | 56.08 | 3 | 3 | 18.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.69 |  |  | 0
Bottom 3 Gangs
PCH | Project | Gang Name | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA413 | Pritam Enterprises 1 | 2.6 | 168.83 | 3 | 1 | 37.93 | 1 | 65.03 | 1 | 65.87 | 0 | 0 | 0 | 0 | 56.28 | 23 | 7 | 30 | ROW | Scattered Locations
Mr. Sanjay Kumar Gupta | TA413 | Pritam Enterprises 4 | 2.62 | 99.58 | 2 | 1 | 37.14 | 0 | 0 | 1 | 62.44 | 0 | 0 | 0 | 0 | 49.79 | 23 | 7 | 30
Mr. Sanjay Kumar Gupta | TA413 | Pritam Enterprises 2 | 2.82 | 272.99 | 5 | 2 | 39.7 | 1 | 66.78 | 1 | 83 | 1 | 43.8 | 0 | 0 | 54.6 | 23 | 7 | 30
Mr. Sanjay Kumar Gupta | TA419 | Ganesh 2 | 1.55 | 88.42 | 2 | 2 | 44.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.21 | 19 | 9 | 28
Mr. Sanjay Kumar Gupta | TA419 | Infinidea | 1.65 | 72.47 | 1 | 0 | 0 | 0 | 0 | 1 | 72.47 | 0 | 0 | 0 | 0 | 72.47 | 18 | 8 | 26
Mr. Sanjay Kumar Gupta | TA419 | Mukhilal 1 | 1.86 | 37.14 | 1 | 1 | 37.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.14 | 18 | 9 | 27
Mr. Sanjay Kumar Gupta | TA512 | M S Karni Construction 1 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Kavya Enterprises | 2.96 | 216.73 | 5 | 3 | 43.11 | 1 | 55.45 | 1 | 31.96 | 0 | 0 | 0 | 0 | 43.35 |  |  | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Karni Construction 2 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Mr. Sanjay Kumar Gupta | TB401 | Anjani Power Priyanka Devi Sudheer | 0.43 | 38.85 | 1 | 1 | 38.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.85 |  |  | 0
Mr. Sanjay Kumar Gupta | TB401 | Priyanka Devi Santosh | 1.18 | 38.85 | 1 | 1 | 38.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.85 |  |  | 0
Mr. Sanjay Kumar Gupta | TB401 | Jwala Singh 3 Bhairo Mahto | 1.7 | 129.11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 129.11 | 0 | 0 | 129.11 |  |  | 0
Mr. Sanjay Kumar Gupta | TB408 | Vedanta Construction | 1.39 | 112.51 | 3 | 3 | 37.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.5 |  |  | 0
Mr. Sanjay Kumar Gupta | TB408 | Dular Chand Patel | 1.63 | 37.5 | 1 | 1 | 37.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.5 |  |  | 0
Mr. Sanjay Kumar Gupta | TB408 | Shri Shyam Construction | 3.13 | 37.5 | 1 | 1 | 37.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.5 |  |  | 0
Mr. Sanjay Kumar Gupta | TB507 | Namechand Mahto 2 | 0.32 | 25.72 | 2 | 2 | 12.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.86 |  |  | 0
Mr. Sanjay Kumar Gupta | TB507 | Ajay Kumar | 0.94 | 18.73 | 1 | 0 | 0 | 0 | 0 | 1 | 18.73 | 0 | 0 | 0 | 0 | 18.73 |  |  | 0
Mr. Sanjay Kumar Gupta | TB507 | Balaji Tour Travels 2 | 1.09 | 12 | 1 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 |  |  | 0
Mr. Arun Felbin | TA325 | Dildar Electricals | 0.17 | 36.04 | 1 | 1 | 36.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.04 |  |  | 0
Mr. Arun Felbin | TA325 | Barkat Ali Mithun Kumar Vntl | 0.41 | 37.73 | 1 | 1 | 37.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.73 |  |  | 0
Mr. Arun Felbin | TA325 | Senaul | 0.99 | 37.73 | 1 | 1 | 37.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.73 |  |  | 0
Mr. Arun Felbin | TA414 | Subhash Kumar | 1.8 | 36.04 | 1 | 1 | 36.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.04 |  |  | 0
Mr. Arun Felbin | TA414 | Chitra Construction | 2.38 | 38.04 | 1 | 1 | 38.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.04 |  |  | 0
Mr. Arun Felbin | TA414 | Zakir Hussain | 2.52 | 37.73 | 1 | 1 | 37.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.73 |  |  | 0
Mr. Arun Felbin | TA416 | Niranjan Singh | 1.75 | 43.78 | 1 | 1 | 43.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.78 |  |  | 0
Mr. Arun Felbin | TA416 | Spotyfy | 2.05 | 53.32 | 1 | 1 | 53.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.32 |  |  | 0
Mr. Arun Felbin | TA416 | Kongres Kumar 1 | 3.03 | 42.37 | 1 | 1 | 42.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.37 |  |  | 0
Mr. Arun Felbin | TA418 | Savitha | 1.55 | 45 | 1 | 0 | 0 | 1 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 45 |  |  | 0
Mr. Arun Felbin | TA418 | Kec 02 Barkat Ali | 2.49 | 256 | 9 | 9 | 28.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.44 |  |  | 0
Mr. Arun Felbin | TA418 | M S Mdpl | 3.12 | 318 | 7 | 4 | 29.25 | 0 | 0 | 2 | 56 | 1 | 89 | 0 | 0 | 45.43 |  |  | 0
Mr. Arun Felbin | TA421 | Praveen | 1.99 | 162.23 | 4 | 4 | 40.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.56 |  |  | 0
Mr. Arun Felbin | TA421 | Yadhav D K Verma | 2.37 | 37.93 | 1 | 1 | 37.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.93 |  |  | 0
Mr. Arun Felbin | TA421 | Hassan | 4.67 | 249.14 | 5 | 3 | 36.89 | 1 | 54.66 | 0 | 0 | 1 | 83.81 | 0 | 0 | 49.83 |  |  | 0
Mr. Arun Felbin | TA504 | Rajesh Kumar | 3.35 | 45.7 | 1 | 1 | 45.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.7 |  |  | 0
Mr. Arun Felbin | TA504 | Karam Mahto | 3.44 | 223.21 | 5 | 4 | 38.99 | 0 | 0 | 1 | 67.26 | 0 | 0 | 0 | 0 | 44.64 |  |  | 0
Mr. Arun Felbin | TA504 | Ghyansham Mahto | 4.41 | 399.93 | 6 | 1 | 37.93 | 1 | 59.5 | 1 | 70.74 | 3 | 77.25 | 0 | 0 | 66.65 |  |  | 0
Mr. Arun Felbin | TA505 | Paramanand 1 | 2.19 | 177.12 | 4 | 3 | 38.34 | 1 | 62.12 | 0 | 0 | 0 | 0 | 0 | 0 | 44.28 |  |  | 0
Mr. Arun Felbin | TA505 | Anil Kumar | 2.71 | 100.38 | 2 | 1 | 37.93 | 0 | 0 | 1 | 62.44 | 0 | 0 | 0 | 0 | 50.19 |  |  | 0
Mr. Arun Felbin | TA505 | Crane Erc Team Mp | 2.93 | 275.49 | 7 | 6 | 36 | 1 | 59.5 | 0 | 0 | 0 | 0 | 0 | 0 | 39.36 |  |  | 0
Mr. Arun Felbin | TA506 | Pappu Kumar | 2.11 | 21.1 | 1 | 1 | 21.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.1 |  |  | 0
Mr. Arun Felbin | TA506 | Alo Reeva | 3.29 | 16.45 | 1 | 1 | 16.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.45 |  |  | 0
Mr. Arun Felbin | TA506 | Karni Const 1 | 3.83 | 264.04 | 12 | 9 | 16.55 | 0 | 0 | 1 | 39.62 | 2 | 37.72 | 0 | 0 | 22 |  |  | 0
Mr. Dheeraj Vashishth | TA513 | Anil Construction | 4.01 | 376.42 | 16 | 11 | 21.17 | 2 | 27.09 | 3 | 29.78 | 0 | 0 | 0 | 0 | 23.53 |  |  | 0
Mr. Dheeraj Vashishth | TB605 | Raj Labour Suppliers | 2.67 | 56.08 | 3 | 3 | 18.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.69 |  |  | 0