## MonthlySummary
Month | Erections Completed | Total Tower Weight (MT) | Avg Tower Weight (MT) | Avg Productivity (MT/day) | Active Gangs | Top 3 Gangs (Avg Productivity)
Sep 2024 | 2 | 87.55 | 43.78 | 2.93 | Dewi Construction Girendra | Dewi Construction Girendra (2.93)
Oct 2024 | 9 | 401.67 | 44.63 | 6 | Dewi Construction Girendra, Horil Mahto | Dewi Construction Girendra (7.50), Horil Mahto (4.12)
Nov 2024 | 11 | 500.59 | 45.51 | 5.11 | Amar Singh, Dewi Construction Girendra, Horil Mahto, Pankaj, Pinky Dewi, Reeta Bharti | Dewi Construction Girendra (7.66), Pinky Dewi (3.84), Horil Mahto (3.08)
Dec 2024 | 25 | 1109.25 | 44.37 | 6.12 | Amar Singh, Dewi Construction Girendra, Horil Mahto, Pankaj, Pinky Dewi, Reeta Bharti | Pinky Dewi (7.86), Dewi Construction Girendra (6.48), Pankaj (6.23)
Jan 2025 | 26 | 1175.42 | 45.21 | 5.42 | Amar Singh, Asc Heights, Dewi Construction Girendra, Horil Mahto, Pankaj, Pinky Dewi, Reeta Bharti, Rudra Construction | Pinky Dewi (6.38), Dewi Construction Girendra (6.00), Amar Singh (5.66)
Feb 2025 | 29 | 1407.85 | 48.55 | 6.18 | Amar Singh, Asc Heights, Dewi Construction Girendra, Horil Mahto, Pankaj, Pinky Dewi, Reeta Bharti, Rudra Construction | Dewi Construction Girendra (7.61), Pinky Dewi (7.08), Amar Singh (6.55)
Mar 2025 | 30 | 1425.93 | 47.53 | 6.55 | Amar Singh, Ananya Traders 1, Asc Heights, Dewi Construction Girendra, Horil Mahto, M K Infra, Pankaj, Pinky Dewi, Reeta Bharti, Rudra Construction | Dewi Construction Girendra (8.60), Reeta Bharti (7.48), Pinky Dewi (7.05)
Apr 2025 | 35 | 1859.53 | 53.13 | 6.29 | Amar Singh, Anand Construction, Ananya Traders 1, Ananya Traders 2, Asc Heights, Dewi Construction Girendra, Gagan Enterprise 1, Gagan Enterprise 2, Horil Mahto, M K Infra, Pinky Dewi, Reeta Bharti, Rudra Construction | Gagan Enterprise 1 (8.02), Gagan Enterprise 2 (7.31), Pinky Dewi (7.18)
May 2025 | 38 | 1749 | 46.03 | 6.67 | Amar Singh, Amit Const, Ananya Traders 1, Ananya Traders 2, Asc Heights, Dewi Construction Girendra, Gagan Enterprise 1, Gagan Enterprise 2, Pinky Dewi, Reeta Bharti, Rudra Construction | Gagan Enterprise 1 (8.10), Ananya Traders 2 (7.39), Pinky Dewi (7.36)
Jun 2025 | 24 | 1595.41 | 66.48 | 6.03 | Amar Singh, Amit Const, Ananya Traders 1, Ananya Traders 2, Asc Heights, Devine, Dewi Construction Girendra, Gagan Enterprise 1, M K Infra, Pinky Dewi, Reeta Bharti | Pinky Dewi (8.19), Ananya Traders 2 (7.46), Dewi Construction Girendra (7.06)
Jul 2025 | 6 | 432.61 | 72.1 | 4.97 | Amar Singh, Ananya Traders 1, Asc Heights, Pinky Dewi, Reeta Bharti | Ananya Traders 1 (7.26), Pinky Dewi (6.58), Reeta Bharti (4.33)
Aug 2025 | 8 | 836.45 | 104.56 | 4.12 | Ananya Traders 1, Gagan Enterprise 1, Gagan Enterprise 2 Kajol, Kongres Kumar 1, Kongres Kumar 2, Punam Kumari, Radha Construction, Sainik Trader | Ananya Traders 1 (7.17), Gagan Enterprise 1 (5.54), Kongres Kumar 1 (4.89)
Sep 2025 | 17 | 1514.48 | 89.09 | 4.21 | Amit Choudhury, Ananya Trader, Ananya Traders 1, Gagan Enterprise 1, Gouri Shankar, Kongres Kumar 1, Kongres Kumar 2, Maa Construction, Punam Kumari, Radha Construction, Reeta Bharti, Sainik Trader, Spotyfy 3 | Gouri Shankar (5.80), Ananya Traders 1 (4.93), Kongres Kumar 1 (4.89)
Oct 2025 | 13 | 1096.24 | 84.33 | 4.41 | Amit Choudhury, Ananya Trader, Kongres Kumar 1, Maa Construction, Mahon Mahto, Pankaj Kumar, Punam Kumari, Punam Kumari 1, Punam Kumari 2, Reeta Bharti, Sainik Trader, Spotyfy | Ananya Trader (6.52), Mahon Mahto (6.51), Punam Kumari 1 (5.53)
Nov 2025 | 12 | 962.36 | 80.2 | 3.88 | Aloriva Global, Amit Choudhury, Mahon Mahto, Niranjan Singh, Pankaj Kumar, Pinky Dewi, Punam Kumari 1, Punam Kumari 2 | Mahon Mahto (5.09), Pankaj Kumar (5.06), Amit Choudhury (3.94)
Dec 2025 | 6 | 531.79 | 88.63 | 4.7 | Pankaj Kumar, Pinky Dewi, Punam Kumari 1, Punam Kumari 3 | Pankaj Kumar (5.72), Pinky Dewi (4.40), Punam Kumari 1 (3.98)

## MonthlyDetails
Completion Month | Completion Date | Location No. | Project Name | Tower Type | Tower Weight (MT) | Gang Name | Status | Starting Date | Productivity (MT/day) | Source
Sep 2024 | 2024-09-16 | 2/8 | TA416 | DA+0 | 43.78 | Dewi Construction Girendra | COMPLETED | 2024-09-01 | 2.74 | ErectionCompiled_Output.xlsx
Sep 2024 | 2024-09-29 | 2/4 | TA416 | DA+0 | 43.78 | Dewi Construction Girendra | COMPLETED | 2024-09-16 | 3.13 | ErectionCompiled_Output.xlsx
Oct 2024 | 2024-10-01 | 39/10 | TA416 | DA+0 | 43.78 | Horil Mahto | COMPLETED | 2024-09-16 | 2.74 | ErectionCompiled_Output.xlsx
Oct 2024 | 2024-10-07 | 20/8 | TA416 | DA+0 | 43.78 | Dewi Construction Girendra | COMPLETED | 2024-10-01 | 6.25 | ErectionCompiled_Output.xlsx
Oct 2024 | 2024-10-13 | 20/6 | TA416 | DA+0 | 43.78 | Dewi Construction Girendra | COMPLETED | 2024-10-08 | 7.3 | ErectionCompiled_Output.xlsx
Oct 2024 | 2024-10-15 | 39/8 | TA416 | DA+0 | 43.78 | Horil Mahto | COMPLETED | 2024-10-03 | 3.37 | ErectionCompiled_Output.xlsx
Oct 2024 | 2024-10-19 | 20/9 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2024-10-14 | 7.67 | ErectionCompiled_Output.xlsx
Oct 2024 | 2024-10-24 | 20/5 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2024-10-20 | 9.21 | ErectionCompiled_Output.xlsx
Oct 2024 | 2024-10-24 | 39/7 | TA416 | DA+3 | 46.05 | Horil Mahto | COMPLETED | 2024-10-15 | 4.6 | ErectionCompiled_Output.xlsx
Oct 2024 | 2024-10-29 | 20/7 | TA416 | DA-3 | 42.37 | Dewi Construction Girendra | COMPLETED | 2024-10-24 | 7.06 | ErectionCompiled_Output.xlsx
Oct 2024 | 2024-10-31 | 39/9 | TA416 | DA+3 | 46.05 | Horil Mahto | COMPLETED | 2024-10-24 | 5.76 | ErectionCompiled_Output.xlsx
Nov 2024 | 2024-11-04 | 20/12 | TA416 | DA-3 | 42.37 | Dewi Construction Girendra | COMPLETED | 2024-11-01 | 10.59 | ErectionCompiled_Output.xlsx
Nov 2024 | 2024-11-10 | 14/6 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2024-11-05 | 7.67 | ErectionCompiled_Output.xlsx
Nov 2024 | 2024-11-14 | 39/6 | TA416 | DA+3 | 46.05 | Horil Mahto | COMPLETED | 2024-11-01 | 3.29 | ErectionCompiled_Output.xlsx
Nov 2024 | 2024-11-17 | 14/5 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2024-11-10 | 5.76 | ErectionCompiled_Output.xlsx
Nov 2024 | 2024-11-22 | 14/4 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2024-11-17 | 7.67 | ErectionCompiled_Output.xlsx
Nov 2024 | 2024-11-24 | 2/5 | TA416 | DA+3 | 46.05 | Pankaj | COMPLETED | 2024-11-10 | 3.07 | ErectionCompiled_Output.xlsx
Nov 2024 | 2024-11-25 | 38/3 | TA416 | DA+3 | 46.05 | Horil Mahto | COMPLETED | 2024-11-10 | 2.88 | ErectionCompiled_Output.xlsx
Nov 2024 | 2024-11-25 | 6/2 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2024-11-14 | 3.84 | ErectionCompiled_Output.xlsx
Nov 2024 | 2024-11-26 | 19/3 | TA416 | DA+3 | 46.05 | Reeta Bharti | COMPLETED | 2024-11-10 | 2.71 | ErectionCompiled_Output.xlsx
Nov 2024 | 2024-11-28 | 14/8 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2024-11-22 | 6.58 | ErectionCompiled_Output.xlsx
Nov 2024 | 2024-11-29 | 41/1 | TA416 | DA+0 | 43.78 | Amar Singh | COMPLETED | 2024-11-10 | 2.19 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-03 | 2/7 | TA416 | DA+3 | 46.05 | Pankaj | COMPLETED | 2024-11-26 | 5.76 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-05 | 14/7 | TA416 | DA+0 | 43.78 | Dewi Construction Girendra | COMPLETED | 2024-11-29 | 6.25 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-05 | 19/2 | TA416 | DA+0 | 43.78 | Reeta Bharti | COMPLETED | 2024-11-28 | 5.47 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-05 | 4/3 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2024-11-28 | 5.76 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-06 | 36/12 | TA416 | DA+0 | 43.78 | Horil Mahto | COMPLETED | 2024-11-29 | 5.47 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-09 | 2/6 | TA416 | DA+0 | 43.78 | Pankaj | COMPLETED | 2024-12-01 | 4.86 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-10 | 41/2 | TA416 | DA+3 | 46.05 | Amar Singh | COMPLETED | 2024-11-30 | 4.19 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-12 | 14/3 | TA416 | DA+0 | 43.78 | Dewi Construction Girendra | COMPLETED | 2024-12-06 | 6.25 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-12 | 4/4 | TA416 | DA+0 | 43.78 | Pinky Dewi | COMPLETED | 2024-12-06 | 6.25 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-13 | 19/4 | TA416 | DA+0 | 43.78 | Reeta Bharti | COMPLETED | 2024-12-06 | 5.47 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-16 | 2/3 | TA416 | DA+3 | 46.05 | Pankaj | COMPLETED | 2024-12-10 | 6.58 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-16 | 4/2 | TA416 | DA-3 | 42.37 | Pinky Dewi | COMPLETED | 2024-12-12 | 8.47 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-17 | 14/2 | TA416 | DA+0 | 43.78 | Dewi Construction Girendra | COMPLETED | 2024-12-12 | 7.3 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-19 | 38/2 | TA416 | DA+3 | 46.05 | Horil Mahto | COMPLETED | 2024-12-06 | 3.29 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-20 | 45/3 | TA416 | DA-3 | 42.37 | Amar Singh | COMPLETED | 2024-12-10 | 3.85 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-21 | 19/1 | TA416 | DA+0 | 43.78 | Reeta Bharti | COMPLETED | 2024-12-13 | 4.86 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-22 | 4/8 | TA416 | DA+0 | 43.78 | Pinky Dewi | COMPLETED | 2024-12-17 | 7.3 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-23 | 14/1 | TA416 | DA+0 | 43.78 | Dewi Construction Girendra | COMPLETED | 2024-12-18 | 7.3 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-23 | 7/10 | TA416 | DA+3 | 46.05 | Pankaj | COMPLETED | 2024-12-18 | 7.67 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-27 | 19/5 | TA416 | DA-3 | 42.37 | Reeta Bharti | COMPLETED | 2024-12-22 | 7.06 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-27 | 4/7 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2024-12-24 | 11.51 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-27 | 45/2 | TA416 | DA+3 | 46.05 | Amar Singh | COMPLETED | 2024-12-21 | 6.58 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-30 | 7/9 | TA416 | DA+0 | 43.78 | Pankaj | COMPLETED | 2024-12-24 | 6.25 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-31 | 17/1 | TA416 | DA-3 | 42.37 | Dewi Construction Girendra | COMPLETED | 2024-12-24 | 5.3 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-31 | 38/4 | TA416 | DA+3 | 46.05 | Horil Mahto | COMPLETED | 2024-12-20 | 3.84 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-03 | 31/3 | TA416 | DA+3 | 46.05 | Asc Heights | COMPLETED | 2024-12-24 | 4.19 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-03 | 4/5 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2024-12-28 | 6.58 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-04 | 46/1 | TA416 | DA+0 | 43.78 | Amar Singh | COMPLETED | 2024-12-28 | 5.47 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-07 | 7/2 | TA416 | DA+3 | 46.05 | Pankaj | COMPLETED | 2024-12-31 | 5.76 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-08 | 19/6 | TA416 | DA+0 | 43.78 | Reeta Bharti | COMPLETED | 2024-12-28 | 3.65 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-10 | 17/4 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2025-01-01 | 4.6 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-11 | 12/2 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2025-01-03 | 5.12 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-11 | 31/4 | TA416 | DA-3 | 42.37 | Asc Heights | COMPLETED | 2025-01-04 | 5.3 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-14 | 7/8 | TA416 | DA+3 | 46.05 | Pankaj | COMPLETED | 2025-01-08 | 6.58 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-15 | 36/3 | TA416 | DA+3 | 46.05 | Amar Singh | COMPLETED | 2025-01-07 | 5.12 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-17 | 17/3 | TA416 | DA+0 | 43.78 | Dewi Construction Girendra | COMPLETED | 2025-01-10 | 5.47 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-17 | 19/7 | TA416 | DA+3 | 46.05 | Reeta Bharti | COMPLETED | 2025-01-09 | 5.12 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-17 | 38/1 | TA416 | DA+3 | 46.05 | Horil Mahto | COMPLETED | 2025-01-07 | 4.19 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-19 | 31/2 | TA416 | DA+0 | 43.78 | Asc Heights | COMPLETED | 2025-01-11 | 4.86 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-21 | 12/3 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2025-01-12 | 4.6 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-22 | 7/7 | TA416 | DA+0 | 43.78 | Pankaj | COMPLETED | 2025-01-15 | 5.47 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-23 | 17/2 | TA416 | DA+0 | 43.78 | Dewi Construction Girendra | COMPLETED | 2025-01-17 | 6.25 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-24 | 36/5 | TA416 | DA+0 | 43.78 | Amar Singh | COMPLETED | 2025-01-15 | 4.38 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-25 | 12/4 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2025-01-21 | 9.21 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-25 | 31/6 | TA416 | DA+3 | 46.05 | Asc Heights | COMPLETED | 2025-01-20 | 7.67 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-27 | 19/9 | TA416 | DA+3 | 46.05 | Reeta Bharti | COMPLETED | 2025-01-16 | 3.84 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-28 | 35/1 | TA416 | DA+3 | 46.05 | Horil Mahto | COMPLETED | 2025-01-16 | 3.54 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-29 | 17/5 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2025-01-24 | 7.67 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-30 | 36/1 | TA416 | DA+3 | 46.05 | Amar Singh | COMPLETED | 2025-01-25 | 7.67 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-30 | 7/6 | TA416 | DA+0 | 43.78 | Pankaj | COMPLETED | 2025-01-21 | 4.38 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-31 | 33/10 | TA416 | DA+3 | 46.05 | Rudra Construction | COMPLETED | 2025-01-21 | 4.19 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-01 | 12/5 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2025-01-25 | 5.76 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-02 | 31/1 | TA416 | DA+0 | 43.78 | Asc Heights | COMPLETED | 2025-01-25 | 4.86 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-05 | 17/7 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2025-01-30 | 6.58 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-06 | 20/0 | TA416 | DB+0 | 64.48 | Reeta Bharti | COMPLETED | 2025-01-28 | 6.45 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-07 | 36/2 | TA416 | DA+0 | 43.78 | Amar Singh | COMPLETED | 2025-02-02 | 7.3 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-08 | 12/9 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2025-02-02 | 6.58 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-09 | 7/5 | TA416 | DA+3 | 46.05 | Pankaj | COMPLETED | 2025-01-29 | 3.84 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-10 | 31/7 | TA416 | DA+0 | 43.78 | Asc Heights | COMPLETED | 2025-02-03 | 5.47 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-11 | 35/0 | TA416 | DC+0 | 73.43 | Horil Mahto | COMPLETED | 2025-01-29 | 5.24 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-12 | 33/11 | TA416 | DA+3 | 46.05 | Rudra Construction | COMPLETED | 2025-02-02 | 4.19 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-13 | 20/2 | TA416 | DA+0 | 43.78 | Reeta Bharti | COMPLETED | 2025-02-07 | 6.25 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-13 | 21/0 | TA416 | DB+0 | 64.48 | Dewi Construction Girendra | COMPLETED | 2025-02-06 | 8.06 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-15 | 35/9 | TA416 | DA+3 | 46.05 | Amar Singh | COMPLETED | 2025-02-08 | 5.76 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-15 | 8/1 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2025-02-09 | 6.58 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-18 | 7/4 | TA416 | DA+0 | 43.78 | Pankaj | COMPLETED | 2025-02-10 | 4.86 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-19 | 20/3 | TA416 | DA+0 | 43.78 | Reeta Bharti | COMPLETED | 2025-02-12 | 5.47 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-20 | 31/9 | TA416 | DA+3 | 46.05 | Asc Heights | COMPLETED | 2025-02-11 | 4.6 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-20 | 33/6 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2025-02-14 | 6.58 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-20 | 34/7 | TA416 | DA+3 | 46.05 | Horil Mahto | COMPLETED | 2025-02-12 | 5.12 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-21 | 35/7 | TA416 | DA+3 | 46.05 | Amar Singh | COMPLETED | 2025-02-16 | 7.67 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-21 | 8/2 | TA416 | DA+0 | 43.78 | Pinky Dewi | COMPLETED | 2025-02-16 | 7.3 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-22 | 33/9 | TA416 | DA+0 | 43.78 | Rudra Construction | COMPLETED | 2025-02-14 | 4.86 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-25 | 20/4 | TA416 | DA-3 | 42.37 | Reeta Bharti | COMPLETED | 2025-02-20 | 7.06 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-25 | 33/7 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2025-02-21 | 9.21 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-25 | 7/1 | TA416 | DA+0 | 43.78 | Pankaj | COMPLETED | 2025-02-19 | 6.25 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-27 | 34/6 | TA416 | DA+0 | 43.78 | Horil Mahto | COMPLETED | 2025-02-21 | 6.25 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-27 | 35/4 | TA416 | DA+0 | 43.78 | Amar Singh | COMPLETED | 2025-02-20 | 5.47 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-28 | 31/0 | TA416 | DB+0 | 64.48 | Asc Heights | COMPLETED | 2025-02-19 | 6.45 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-28 | 8/0 | TA416 | DB+0 | 64.48 | Pinky Dewi | COMPLETED | 2025-02-22 | 9.21 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-02 | 33/3 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2025-02-26 | 9.21 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-03 | 35/5 | TA416 | DA+3 | 46.05 | Amar Singh | COMPLETED | 2025-02-27 | 9.21 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-05 | 4/10 | TA416 | DA+3 | 46.05 | Reeta Bharti | COMPLETED | 2025-03-01 | 9.21 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-07 | 33/8 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2025-03-03 | 9.21 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-08 | 35/3 | TA416 | DA+0 | 43.78 | Horil Mahto | COMPLETED | 2025-02-28 | 4.86 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-08 | 7/0 | TA416 | DB+0 | 64.48 | Pankaj | COMPLETED | 2025-02-27 | 6.45 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-08 | 7/11 | TA416 | DA+0 | 43.78 | Pinky Dewi | COMPLETED | 2025-03-01 | 5.47 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-09 | 30/4 | TA416 | DA+3 | 46.05 | Asc Heights | COMPLETED | 2025-03-01 | 5.12 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-11 | 33/4 | TA416 | DA-3 | 42.37 | Dewi Construction Girendra | COMPLETED | 2025-03-08 | 10.59 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-11 | 34/1 | TA416 | DA+3 | 46.05 | Rudra Construction | COMPLETED | 2025-03-01 | 4.19 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-12 | 8/3 | TA416 | DA-3 | 42.37 | Pinky Dewi | COMPLETED | 2025-03-08 | 8.47 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-13 | 5/0 | TA416 | DB+0 | 64.48 | Reeta Bharti | COMPLETED | 2025-03-01 | 4.96 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-16 | 30/5 | TA416 | DA+0 | 43.78 | Asc Heights | COMPLETED | 2025-03-10 | 6.25 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-18 | 33/1 | TA416 | DA-3 | 42.37 | Dewi Construction Girendra | COMPLETED | 2025-03-12 | 6.05 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-18 | 35/6 | TA416 | DA+0 | 43.78 | Horil Mahto | COMPLETED | 2025-03-10 | 4.86 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-19 | 6/1 | TA416 | DA+3 | 46.05 | Pankaj | COMPLETED | 2025-03-09 | 4.19 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-21 | 5/1 | TA416 | DA+3 | 46.05 | Reeta Bharti | COMPLETED | 2025-03-16 | 7.67 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-21 | 8/4 | TA416 | DA+9 | 55.34 | Pinky Dewi | COMPLETED | 2025-03-13 | 6.15 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-23 | 31/8 | TA416 | DA-3 | 42.37 | Asc Heights | COMPLETED | 2025-03-16 | 5.3 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-23 | 33/2 | TA416 | DA-3 | 42.37 | Dewi Construction Girendra | COMPLETED | 2025-03-19 | 8.47 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-26 | 8B/1 | TA416 | DA-3 | 42.37 | Pinky Dewi | COMPLETED | 2025-03-22 | 8.47 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-27 | 7/3 | TA416 | DA-3 | 42.37 | Pankaj | COMPLETED | 2025-03-20 | 5.3 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-29 | 6/0 | TA416 | DB+0 | 64.48 | Reeta Bharti | COMPLETED | 2025-03-22 | 8.06 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-30 | 31/10 | TA416 | DA-3 | 42.37 | Asc Heights | COMPLETED | 2025-03-24 | 6.05 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-30 | 35/2 | TA416 | DA-3 | 42.37 | Horil Mahto | COMPLETED | 2025-03-20 | 3.85 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-31 | 34/0 | TA416 | DB+0 | 64.48 | Dewi Construction Girendra | COMPLETED | 2025-03-24 | 8.06 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-31 | 35/8 | TA416 | DA-3 | 42.37 | Amar Singh | COMPLETED | 2025-03-22 | 4.24 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-31 | 38/8 | TA416 | DA+3 | 46.05 | M K Infra | COMPLETED | 2025-03-21 | 4.19 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-31 | 39/3 | TA416 | DA+3 | 46.05 | Ananya Traders 1 | COMPLETED | 2025-03-24 | 5.76 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-31 | 8B/5 | TA416 | DA+6 | 53.32 | Pinky Dewi | COMPLETED | 2025-03-24 | 6.67 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-05 | 4/6 | TA416 | DA+0 | 43.78 | Reeta Bharti | COMPLETED | 2025-03-28 | 4.86 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-07 | 8B/3 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2025-03-28 | 4.19 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-08 | 20/11 | TA416 | DA-3 | 42.37 | Gagan Enterprise 1 | COMPLETED | 2025-03-31 | 4.71 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-10 | 34/4 | TA416 | DA-3 | 42.37 | Dewi Construction Girendra | COMPLETED | 2025-04-03 | 5.3 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-11 | 32/0 | TA416 | DC+6 | 87.01 | Asc Heights | COMPLETED | 2025-04-01 | 7.91 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-11 | 38/6 | TA416 | DA+3 | 46.05 | M K Infra | COMPLETED | 2025-04-01 | 4.19 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-11 | 4/1 | TA416 | DA+3 | 46.05 | Anand Construction | COMPLETED | 2025-03-31 | 3.84 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-11 | 9/0 | TA416 | DB+6 | 75.86 | Gagan Enterprise 2 | COMPLETED | 2025-04-01 | 6.9 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-12 | 39/1 | TA416 | DA+3 | 46.05 | Ananya Traders 1 | COMPLETED | 2025-04-01 | 3.84 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-12 | 53A/4 | TA416 | DA+3 | 46.05 | Horil Mahto | COMPLETED | 2025-04-01 | 3.84 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-13 | 8B/2 | TA416 | DA-3 | 42.37 | Pinky Dewi | COMPLETED | 2025-04-08 | 7.06 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-14 | 36/0 | TA416 | DB+0 | 64.48 | Amar Singh | COMPLETED | 2025-04-02 | 4.96 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-15 | 20/10 | TA416 | DA+3 | 46.05 | Gagan Enterprise 1 | COMPLETED | 2025-04-09 | 6.58 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-16 | 10/1 | TA416 | DA-3 | 42.37 | Gagan Enterprise 2 | COMPLETED | 2025-04-12 | 8.47 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-16 | 52/6 | TA416 | DA+3 | 46.05 | Ananya Traders 2 | COMPLETED | 2025-04-05 | 3.84 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-17 | 4/0 | TA416 | DD45+0 | 86.26 | Reeta Bharti | COMPLETED | 2025-04-06 | 7.19 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-19 | 39/0 | TA416 | DB+0 | 64.48 | Ananya Traders 1 | COMPLETED | 2025-04-12 | 8.06 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-21 | 31/5 | TA416 | DA-3 | 42.37 | Asc Heights | COMPLETED | 2025-04-12 | 4.24 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-21 | 8B/4 | TA416 | DA+6 | 53.32 | Pinky Dewi | COMPLETED | 2025-04-14 | 6.67 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-22 | 20/1 | TA416 | DA+6 | 53.32 | Gagan Enterprise 1 | COMPLETED | 2025-04-16 | 7.62 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-22 | 33/0 | TA416 | DC+6 | 87.01 | Dewi Construction Girendra | COMPLETED | 2025-04-12 | 7.91 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-22 | 36/6 | TA416 | DA+3 | 46.05 | Amar Singh | COMPLETED | 2025-04-12 | 4.19 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-22 | 38/7 | TA416 | DA-3 | 42.37 | M K Infra | COMPLETED | 2025-04-12 | 3.85 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-23 | 25/2 | TA416 | DA+0 | 43.78 | Rudra Construction | COMPLETED | 2025-04-15 | 4.86 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-25 | 52/5 | TA416 | DA-3 | 42.37 | Ananya Traders 2 | COMPLETED | 2025-04-17 | 4.71 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-26 | 0/4 | TA416 | DA+9 | 55.34 | Anand Construction | COMPLETED | 2025-04-12 | 3.69 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-26 | 19/12 | TA416 | DA-3 | 42.37 | Gagan Enterprise 1 | COMPLETED | 2025-04-23 | 10.59 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-26 | 39/2 | TA416 | DA-3 | 42.37 | Ananya Traders 1 | COMPLETED | 2025-04-20 | 6.05 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-28 | 10/0 | TA416 | DB+9 | 78.68 | Gagan Enterprise 2 | COMPLETED | 2025-04-17 | 6.56 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-28 | 30/6 | TA416 | DA-3 | 42.37 | Asc Heights | COMPLETED | 2025-04-22 | 6.05 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-28 | 34/2 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2025-04-23 | 7.67 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-28 | 36/7 | TA416 | DA+3 | 46.05 | Amar Singh | COMPLETED | 2025-04-23 | 7.67 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-29 | 52/4 | TA416 | DA-3 | 42.37 | Ananya Traders 2 | COMPLETED | 2025-04-26 | 10.59 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-30 | 19/11 | TA416 | DA-3 | 42.37 | Gagan Enterprise 1 | COMPLETED | 2025-04-27 | 10.59 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-30 | 8A/0 | TA416 | DD60+0 | 97.23 | Pinky Dewi | COMPLETED | 2025-04-22 | 10.8 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-03 | 34/3 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2025-04-29 | 9.21 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-04 | 39/4 | TA416 | DA+3 | 46.05 | Ananya Traders 1 | COMPLETED | 2025-04-29 | 7.67 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-05 | 36/8 | TA416 | DA-3 | 42.37 | Amar Singh | COMPLETED | 2025-04-29 | 6.05 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-06 | 19/10 | TA416 | DA+3 | 46.05 | Gagan Enterprise 1 | COMPLETED | 2025-04-30 | 6.58 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-06 | 30/3 | TA416 | DA+0 | 43.78 | Asc Heights | COMPLETED | 2025-04-30 | 6.25 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-06 | 52/3 | TA416 | DA-3 | 42.37 | Ananya Traders 2 | COMPLETED | 2025-04-30 | 6.05 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-07 | 25/3 | TA416 | DA+3 | 46.05 | Rudra Construction | COMPLETED | 2025-04-30 | 5.76 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-09 | 19/8 | TA416 | DA-3 | 42.37 | Gagan Enterprise 1 | COMPLETED | 2025-05-06 | 10.59 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-10 | 12/1 | TA416 | DA-3 | 42.37 | Gagan Enterprise 2 | COMPLETED | 2025-05-04 | 6.05 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-11 | 39/5 | TA416 | DA-3 | 42.37 | Ananya Traders 1 | COMPLETED | 2025-05-05 | 6.05 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-11 | 4/9 | TA416 | DA-3 | 42.37 | Reeta Bharti | COMPLETED | 2025-05-04 | 5.3 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-12 | 52/2 | TA416 | DA+3 | 46.05 | Ananya Traders 2 | COMPLETED | 2025-05-07 | 7.67 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-13 | 30/1 | TA416 | DA-3 | 42.37 | Asc Heights | COMPLETED | 2025-05-07 | 6.05 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-13 | 36/4 | TA416 | DA+0 | 43.78 | Amar Singh | COMPLETED | 2025-05-07 | 6.25 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-14 | 56/2 | TA416 | DA+3 | 46.05 | Dewi Construction Girendra | COMPLETED | 2025-05-07 | 5.76 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-14 | 8B/0 | TA416 | DD60+0 | 97.23 | Pinky Dewi | COMPLETED | 2025-05-05 | 9.72 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-15 | 17/8 | TA416 | DA-3 | 42.37 | Gagan Enterprise 1 | COMPLETED | 2025-05-11 | 8.47 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-17 | 52/9 | TA416 | DA-3 | 42.37 | Ananya Traders 2 | COMPLETED | 2025-05-13 | 8.47 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-19 | 36/11 | TA416 | DA-3 | 42.37 | Amar Singh | COMPLETED | 2025-05-14 | 7.06 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-19 | 38/11 | TA416 | DA+3 | 46.05 | Ananya Traders 1 | COMPLETED | 2025-05-12 | 5.76 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-19 | 56/1 | TA416 | DA+0 | 43.78 | Dewi Construction Girendra | COMPLETED | 2025-05-14 | 7.3 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-20 | 30/2 | TA416 | DA-3 | 42.37 | Asc Heights | COMPLETED | 2025-05-14 | 6.05 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-21 | 2/1 | TA416 | DA+3 | 46.05 | Reeta Bharti | COMPLETED | 2025-05-12 | 4.6 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-21 | 52/10 | TA416 | DA+3 | 46.05 | Ananya Traders 2 | COMPLETED | 2025-05-16 | 7.67 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-22 | 12/6 | TA416 | DA-3 | 42.37 | Gagan Enterprise 2 | COMPLETED | 2025-05-11 | 3.53 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-22 | 23/3 | TA416 | DA-3 | 42.37 | Pinky Dewi | COMPLETED | 2025-05-15 | 5.3 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-22 | 53/1 | TA416 | DA+6 | 53.32 | Amit Const | COMPLETED | 2025-05-12 | 4.85 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-24 | 36/9 | TA416 | DA-3 | 42.37 | Amar Singh | COMPLETED | 2025-05-20 | 8.47 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-24 | 38/10 | TA416 | DA-3 | 42.37 | Ananya Traders 1 | COMPLETED | 2025-05-20 | 8.47 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-24 | 56/3 | TA416 | DA-3 | 42.37 | Dewi Construction Girendra | COMPLETED | 2025-05-20 | 8.47 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-25 | 15/0 | TA416 | DC+3 | 78.07 | Gagan Enterprise 1 | COMPLETED | 2025-05-16 | 7.81 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-27 | 23/5 | TA416 | DA-3 | 42.37 | Rudra Construction | COMPLETED | 2025-05-10 | 2.35 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-27 | 52/8 | TA416 | DA-3 | 42.37 | Ananya Traders 2 | COMPLETED | 2025-05-22 | 7.06 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-28 | 23/4 | TA416 | DA-3 | 42.37 | Pinky Dewi | COMPLETED | 2025-05-23 | 7.06 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-30 | 0/2 | TA416 | DA-3 | 42.37 | Reeta Bharti | COMPLETED | 2025-05-23 | 5.3 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-30 | 56/4 | TA416 | DA-3 | 42.37 | Dewi Construction Girendra | COMPLETED | 2025-05-23 | 5.3 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-31 | 12/8 | TA416 | DA-3 | 42.37 | Gagan Enterprise 1 | COMPLETED | 2025-05-26 | 7.06 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-31 | 36/10 | TA416 | DA-3 | 42.37 | Amar Singh | COMPLETED | 2025-05-25 | 6.05 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-01 | 38/9 | TA416 | DA-3 | 42.37 | M K Infra | COMPLETED | 2025-04-23 | 1.06 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-02 | 38/5 | TA416 | DA+3 | 46.05 | Ananya Traders 1 | COMPLETED | 2025-05-28 | 7.67 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-03 | 23/1 | TA416 | DA+9 | 55.34 | Pinky Dewi | COMPLETED | 2025-05-28 | 7.91 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-04 | 0/3 | TA416 | DA-3 | 42.37 | Reeta Bharti | COMPLETED | 2025-05-25 | 3.85 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-04 | 56/5 | TA416 | DA-3 | 42.37 | Dewi Construction Girendra | COMPLETED | 2025-05-30 | 7.06 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-07 | 51/0 | TA416 | DD60+0 | 97.23 | Ananya Traders 2 | COMPLETED | 2025-05-27 | 8.1 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-09 | 23/2 | TA416 | DA+0 | 43.78 | Pinky Dewi | COMPLETED | 2025-06-04 | 7.3 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-10 | 33/5 | TA416 | DA+3 | 46.05 | Amar Singh | COMPLETED | 2025-06-02 | 5.12 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-11 | 0/1 | TA416 | DA-3 | 42.37 | Reeta Bharti | COMPLETED | 2025-06-04 | 5.3 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-13 | 50/1 | TA416 | DA+0 | 43.78 | Ananya Traders 2 | COMPLETED | 2025-06-08 | 7.3 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-14 | 53A/5 | TA416 | DA-3 | 42.37 | Devine | COMPLETED | 2025-06-02 | 3.26 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-18 | 34/5 | TA416 | DA+0 | 43.78 | Amar Singh | COMPLETED | 2025-06-12 | 6.25 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-18 | 53A/2 | TA416 | DA+3 | 46.05 | Amit Const | COMPLETED | 2025-06-10 | 5.12 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-20 | 22/0 | TA416 | DB+3 | 67.11 | Pinky Dewi | COMPLETED | 2025-06-12 | 7.46 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-21 | 30/0 | TA416 | DD60+18 | 143.46 | Asc Heights | COMPLETED | 2025-05-25 | 5.12 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-23 | 3/0 | TA416 | DC+0 | 73.43 | Reeta Bharti | COMPLETED | 2025-06-12 | 6.12 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-26 | 21/2 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2025-06-21 | 7.67 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-27 | 45/1 | TA416 | DA+3 | 46.05 | M K Infra | COMPLETED | 2025-06-10 | 2.56 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-29 | 48/0 | TA416 | DD45+9 | 104.87 | Ananya Traders 2 | COMPLETED | 2025-06-15 | 6.99 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-29 | 53A/3 | TA416 | DA+3 | 46.05 | Amit Const | COMPLETED | 2025-06-20 | 4.6 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-30 | 12/7 | TA416 | DA-3 | 42.37 | Reeta Bharti | COMPLETED | 2025-06-24 | 6.05 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-30 | 14/0 | TA416 | DD60+30 | 188.38 | Gagan Enterprise 1 | COMPLETED | 2025-06-01 | 6.28 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-30 | 21/1 | TA416 | DA-3 | 42.37 | Pinky Dewi | COMPLETED | 2025-06-27 | 10.59 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-30 | 40/0 | TA416 | DD60+25 | 161.36 | Ananya Traders 1 | COMPLETED | 2025-06-04 | 5.98 | ErectionCompiled_Output.xlsx
Jul 2025 | 2025-07-05 | 28/1 | TA416 | DA+3 | 46.05 | Asc Heights | COMPLETED | 2025-06-24 | 3.84 | ErectionCompiled_Output.xlsx
Jul 2025 | 2025-07-07 | 21/3 | TA416 | DA+3 | 46.05 | Pinky Dewi | COMPLETED | 2025-07-01 | 6.58 | ErectionCompiled_Output.xlsx
Jul 2025 | 2025-07-12 | 25/1 | TA416 | DA+9 | 55.34 | Reeta Bharti | COMPLETED | 2025-07-01 | 4.61 | ErectionCompiled_Output.xlsx
Jul 2025 | 2025-07-18 | 44/0 | TA416 | DD60+3 | 101.69 | Ananya Traders 1 | COMPLETED | 2025-07-05 | 7.26 | ErectionCompiled_Output.xlsx
Jul 2025 | 2025-07-22 | 56/0 | TA416 | DD45+0 | 86.26 | Amar Singh | COMPLETED | 2025-06-28 | 3.45 | ErectionCompiled_Output.xlsx
Jul 2025 | 2025-07-31 | 28/0 | TA416 | DD60+0 | 97.23 | Reeta Bharti | COMPLETED | 2025-07-08 | 4.05 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-08 | 41/0 | TA416 | DD60+18 | 143.46 | Ananya Traders 1 | COMPLETED | 2025-07-20 | 7.17 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-11 | 13/0 | TA416 | DD60+30 | 188.38 | Gagan Enterprise 1 | COMPLETED | 2025-07-09 | 5.54 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-17 | 53A/6 | TA416 | DA+3 | 46.05 | Punam Kumari | COMPLETED | 2025-07-27 | 2.09 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-26 | 46/2 | TA416 | DA+3 | 46.05 | Gagan Enterprise 2 Kajol | COMPLETED | 2025-08-14 | 3.54 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-27 | 24/0 | TA416 | DD60+25 | 161.36 | Kongres Kumar 1 | COMPLETED | 2025-07-26 | 4.89 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-30 | 1/0 | TA416 | DC+3 | 78.07 | Radha Construction | COMPLETED | 2025-08-09 | 3.55 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-30 | 18/0 | TA416 | DB+6 | 75.86 | Sainik Trader | COMPLETED | 2025-08-04 | 2.81 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-30 | 65/0 | TA416 | DD60+0 | 97.23 | Kongres Kumar 2 | COMPLETED | 2025-08-02 | 3.35 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-02 | 12/0 | TA416 | DB+18 | 97.65 | Gagan Enterprise 1 | COMPLETED | 2025-08-12 | 4.44 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-04 | 54/1 | TA416 | DA+9 | 55.34 | Punam Kumari | COMPLETED | 2025-08-18 | 3.07 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-06 | 43/0 | TA416 | DD60+9 | 118.43 | Ananya Traders 1 | COMPLETED | 2025-08-10 | 4.23 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-14 | 11/0 | TA416 | DB+18 | 97.65 | Gouri Shankar | COMPLETED | 2025-08-24 | 4.44 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-14 | 16/0 | TA416 | DB+25 | 110.63 | Amit Choudhury | COMPLETED | 2025-08-16 | 3.69 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-21 | 2/0 | TA416 | DD45+3 | 89.72 | Radha Construction | COMPLETED | 2025-09-03 | 4.72 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-22 | 29/0 | TA416 | DD60+25 | 161.36 | Reeta Bharti | COMPLETED | 2025-08-06 | 3.36 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-22 | 47/0 | TA416 | DC+9 | 90.13 | Ananya Traders 1 | COMPLETED | 2025-09-07 | 5.63 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-22 | 52/0 | TA416 | DC+9 | 90.13 | Punam Kumari | COMPLETED | 2025-09-05 | 5.01 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-22 | 64/0 | TA416 | DC+0 | 73.43 | Kongres Kumar 2 | COMPLETED | 2025-08-31 | 3.19 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-23 | 48/1 | TA416 | DA-3 | 42.37 | Ananya Trader | COMPLETED | 2025-09-15 | 4.71 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-24 | 17/6 | TA416 | DA-3 | 42.37 | Amit Choudhury | COMPLETED | 2025-09-15 | 4.24 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-24 | 19/0 | TA416 | DC+6 | 87.01 | Sainik Trader | COMPLETED | 2025-08-31 | 3.48 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-24 | 56/8 | TA416 | DA-3 | 42.37 | Spotyfy 3 | COMPLETED | 2025-08-18 | 1.12 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-25 | 26/0 | TA416 | DB+9 | 78.68 | Gouri Shankar | COMPLETED | 2025-09-15 | 7.15 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-28 | 17/0 | TA416 | DB+6 | 75.86 | Maa Construction | COMPLETED | 2025-09-11 | 4.21 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-29 | 25/0 | TA416 | DD60+25 | 161.36 | Kongres Kumar 1 | COMPLETED | 2025-08-28 | 4.89 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-07 | 54/0 | TA416 | DB+3 | 67.11 | Punam Kumari | COMPLETED | 2025-09-25 | 5.16 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-07 | 64/3 | TA416 | DA-3 | 42.37 | Kongres Kumar 1 | COMPLETED | 2025-09-24 | 3.03 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-08 | 46/0 | TA416 | DB+0 | 64.48 | Amit Choudhury | COMPLETED | 2025-09-25 | 4.61 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-12 | 27/0 | TA416 | DD60+3 | 101.69 | Reeta Bharti | COMPLETED | 2025-09-22 | 4.84 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-12 | 63/0 | TA416 | DC+3 | 78.07 | Mahon Mahto | COMPLETED | 2025-10-01 | 6.51 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-13 | 53A/1 | TA416 | DA+6 | 53.32 | Spotyfy | COMPLETED | 2025-09-18 | 2.05 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-14 | 42/0 | TA416 | DD60+18 | 143.46 | Ananya Trader | COMPLETED | 2025-09-23 | 6.52 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-14 | 50/0 | TA416 | DC+18 | 110.7 | Punam Kumari 1 | COMPLETED | 2025-09-25 | 5.53 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-14 | 53/0 | TA416 | DC+0 | 73.43 | Sainik Trader | COMPLETED | 2025-09-26 | 3.86 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-22 | 54/2 | TA416 | DA-3 | 42.37 | Punam Kumari 2 | COMPLETED | 2025-10-08 | 2.82 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-26 | 38/0 | TA416 | DC+18 | 110.7 | Pankaj Kumar | COMPLETED | 2025-10-08 | 5.83 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-28 | 0/0 | TA416 | DCT+0 | 97.83 | Maa Construction | COMPLETED | 2025-10-03 | 3.76 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-31 | 37/0 | TA416 | DC+18 | 110.7 | Pankaj Kumar | COMPLETED | 2025-09-23 | 2.84 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-07 | 45/0 | TA416 | DD60+0 | 97.23 | Amit Choudhury | COMPLETED | 2025-10-09 | 3.24 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-07 | 55/0 | TA416 | DC+0 | 73.43 | Punam Kumari 2 | COMPLETED | 2025-10-15 | 3.06 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-10 | 52/1 | TA416 | DB+6 | 75.86 | Pankaj Kumar | COMPLETED | 2025-10-27 | 5.06 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-13 | 2/2 | TA416 | DA+0 | 43.78 | Aloriva Global | COMPLETED | 2025-11-01 | 3.37 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-14 | 61/0 | TA416 | DD2+30 | 188.38 | Mahon Mahto | COMPLETED | 2025-09-25 | 3.69 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-15 | 56/6 | TA416 | DA+0 | 43.78 | Pinky Dewi | COMPLETED | 2025-11-01 | 2.92 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-17 | 55/1 | TA416 | DA-3 | 42.37 | Punam Kumari 2 | COMPLETED | 2025-11-09 | 4.71 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-29 | 60/0 | TA416 | DD45+6 | 101.93 | Amit Choudhury | COMPLETED | 2025-11-08 | 4.63 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-29 | 69A/0 | TA416 | DD60+0 | 97.23 | Mahon Mahto | COMPLETED | 2025-11-15 | 6.48 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-30 | 49/0 | TA416 | DC+9 | 90.13 | Punam Kumari 1 | COMPLETED | 2025-11-06 | 3.61 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-30 | 53A/0 | TA416 | DB+0 | 64.48 | Aloriva Global | COMPLETED | 2025-11-15 | 4.03 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-30 | 64/1 | TA416 | DA+0 | 43.78 | Niranjan Singh | COMPLETED | 2025-11-06 | 1.75 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-04 | 59/0 | TA416 | DD60+6 | 113.68 | Pinky Dewi | COMPLETED | 2025-11-16 | 5.98 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-04 | 62/0 | TA416 | DC+25 | 124.04 | Pankaj Kumar | COMPLETED | 2025-11-10 | 4.96 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-07 | 66/1 | TA416 | DA+0 | 43.78 | Punam Kumari 1 | COMPLETED | 2025-11-27 | 3.98 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-14 | 23/0 | TA416 | DC+18 | 110.7 | Punam Kumari 3 | COMPLETED | 2025-11-17 | 3.95 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-19 | 66/0 | TA416 | DD60+0 | 97.23 | Pankaj Kumar | COMPLETED | 2025-12-05 | 6.48 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-21 | 57/1 | TA416 | DA-3 | 42.37 | Pinky Dewi | COMPLETED | 2025-12-07 | 2.82 | ErectionCompiled_Output.xlsx

## SelectionContext
Project Code | Project Names | Dataset Path | Range Start | Range End | Months Covered | Total Completions
TA416 | TA416 | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Parquets\Erection\ErectionCompiled_Output.xlsx | 2024-09-16 | 2025-12-21 | 16 | 291