## Erection Summary
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
4.12 | 4.26 | 4.32 | 4.28 | 4.47 | 4.24 | 14458.64 | 322 | 194 | 33.03 | 46 | 45.6 | 34 | 55.09 | 48 | 85 | 0 | 0 | 44.9
PCH | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | 3.88 | 4.06 | 4.18 | 4.12 | 4.31 | 4 | 5860.8 | 138 | 92 | 35.96 | 17 | 34.51 | 15 | 55.08 | 14 | 81.41 | 0 | 0 | 42.47
Mr. Arun Felbin | 4.24 | 4.49 | 4.54 | 4.7 | 4.82 | 4.41 | 8475.64 | 178 | 97 | 31.01 | 29 | 52.1 | 18 | 56.5 | 34 | 86.48 | 0 | 0 | 47.62
Mr. Dheeraj Vashishth | 4.66 | 3.93 | 3.67 | 3.28 | 3.56 | 3.95 | 122.2 | 6 | 5 | 18.48 | 0 | 0 | 1 | 29.78 | 0 | 0 | 0 | 0 | 20.37
[6 empty] | Total | 14458.64 | 322
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA413 | 3.51 | 4.59 | 4.17 | 4.53 | 4.77 | 4.19 | 1429.26 | 24 | 16 | 38.22 | 1 | 66.78 | 2 | 80.88 | 5 | 117.82 | 0 | 0 | 59.55
Mr. Sanjay Kumar Gupta | TA419 | 3.75 | 3.92 | 3.26 | 3.32 | 3.59 | 3.48 | 690.5 | 14 | 10 | 39.24 | 0 | 0 | 2 | 73.87 | 2 | 75.16 | 0 | 0 | 49.32
Mr. Sanjay Kumar Gupta | TA512 | 5.15 | 4.23 | 6 | 5.22 | 5.13 | 5.24 | 624.55 | 16 | 15 | 39.6 | 0 | 0 | 1 | 30.49 | 0 | 0 | 0 | 0 | 39.03
Mr. Sanjay Kumar Gupta | TB401 | 3.98 | 4.64 | 5.08 | 4.85 | 5.33 | 4.73 | 877.32 | 18 | 14 | 42.54 | 2 | 62.74 | 1 | 66.38 | 1 | 89.91 | 0 | 0 | 48.74
Mr. Sanjay Kumar Gupta | TB408 | 4.12 | 4.35 | 4.26 | 4.43 | 4.6 | 4.31 | 1672.84 | 33 | 23 | 40.93 | 3 | 61.97 | 5 | 68.73 | 2 | 100.97 | 0 | 0 | 50.69
Mr. Sanjay Kumar Gupta | TB507 | 2.77 | 2.6 | 2.3 | 2.37 | 2.46 | 2.52 | 566.34 | 33 | 14 | 12.37 | 11 | 18.96 | 4 | 19.05 | 4 | 27.13 | 0 | 0 | 17.16
Mr. Arun Felbin | TA325 | 3.56 | 3.72 | 4.15 | 4.47 | 4.75 | 4.05 | 2808.11 | 38 | 12 | 39.93 | 6 | 61.26 | 5 | 77.73 | 15 | 104.85 | 0 | 0 | 73.9
Mr. Arun Felbin | TA414 | 0 | 0 | 0 | 0 | 3.24 | 3.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA416 | 3.48 | 3.72 | 4.4 | 4.41 | 4.23 | 4.05 | 962.36 | 12 | 4 | 43.43 | 2 | 70.17 | 2 | 81.78 | 4 | 121.19 | 0 | 0 | 80.2
Mr. Arun Felbin | TA418 | 3.04 | 3.26 | 3.2 | 2.92 | 3.52 | 3.13 | 365 | 8 | 5 | 28.4 | 1 | 45 | 0 | 0 | 2 | 89 | 0 | 0 | 45.62
Mr. Arun Felbin | TA421 | 6.28 | 6.75 | 6.12 | 7.13 | 7.43 | 6.62 | 949.77 | 22 | 16 | 35.82 | 5 | 58.55 | 0 | 0 | 1 | 83.81 | 0 | 0 | 43.17
Mr. Arun Felbin | TA504 | 4.31 | 4.39 | 4.35 | 4.69 | 5.22 | 4.51 | 324.01 | 6 | 3 | 39.34 | 1 | 59.5 | 0 | 0 | 2 | 73.24 | 0 | 0 | 54
Mr. Arun Felbin | TA505 | 3.66 | 3.88 | 4.11 | 4.57 | 5.12 | 4.14 | 1501.99 | 34 | 25 | 37.13 | 5 | 61.93 | 3 | 63.59 | 1 | 73.24 | 0 | 0 | 44.18
Mr. Arun Felbin | TA506 | 5.34 | 5.67 | 5.45 | 4.73 | 5.05 | 5.27 | 1564.4 | 58 | 32 | 18.54 | 9 | 32.88 | 8 | 34.25 | 9 | 44.57 | 0 | 0 | 26.97
Mr. Dheeraj Vashishth | TA513 | 4.66 | 3.93 | 3.67 | 3.94 | 4.5 | 4.11 | 122.2 | 6 | 5 | 18.48 | 0 | 0 | 1 | 29.78 | 0 | 0 | 0 | 0 | 20.37
Mr. Dheeraj Vashishth | TB605 | 0 | 0 | 0 | 2.62 | 2.62 | 2.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Total | 14458.65 | 322

## Project Gang Rankings
Top 3 Gangs
PCH | Project | Gang Name | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA413 | Jwala Singh 1 | 4.4 | 147.62 | 4 | 4 | 36.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.91
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari 1 | 3.1 | 155.83 | 4 | 4 | 38.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.96
Mr. Sanjay Kumar Gupta | TA419 | Jwala Singh | 5.17 | 153.26 | 4 | 4 | 38.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.32
Mr. Sanjay Kumar Gupta | TA512 | M S Kartik Mahto | 6.95 | 270.18 | 7 | 7 | 38.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.6
Mr. Sanjay Kumar Gupta | TA512 | M S Jwala Singh | 5.38 | 167.01 | 4 | 4 | 41.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.75
Mr. Sanjay Kumar Gupta | TB401 | Sunny Const | 3.76 | 192.75 | 4 | 3 | 41.63 | 1 | 67.87 | 0 | 0 | 0 | 0 | 0 | 0 | 48.19
Mr. Sanjay Kumar Gupta | TB408 | Shobha Devi | 6.59 | 253.65 | 5 | 4 | 43.88 | 0 | 0 | 1 | 78.13 | 0 | 0 | 0 | 0 | 50.73
Mr. Sanjay Kumar Gupta | TB408 | Ganesh Sinha | 5.92 | 188.15 | 4 | 3 | 40.59 | 0 | 0 | 1 | 66.38 | 0 | 0 | 0 | 0 | 47.04
Mr. Sanjay Kumar Gupta | TB408 | Chinta Devi | 5.87 | 188.15 | 4 | 3 | 40.59 | 0 | 0 | 1 | 66.38 | 0 | 0 | 0 | 0 | 47.04
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw 2 | 3.33 | 127.19 | 8 | 5 | 13.19 | 2 | 17.46 | 0 | 0 | 1 | 26.29 | 0 | 0 | 15.9
Mr. Sanjay Kumar Gupta | TB507 | Namechand Mahto | 2.98 | 98.34 | 6 | 2 | 13.28 | 3 | 17.68 | 1 | 18.73 | 0 | 0 | 0 | 0 | 16.39
Mr. Sanjay Kumar Gupta | TB507 | Gokul Sarkar | 2.74 | 96 | 4 | 0 | 0 | 3 | 18.87 | 0 | 0 | 1 | 39.4 | 0 | 0 | 24
Mr. Arun Felbin | TA421 | Khatun | 9.41 | 224.81 | 5 | 3 | 34.91 | 2 | 60.04 | 0 | 0 | 0 | 0 | 0 | 0 | 44.96
Mr. Arun Felbin | TA421 | Subash | 8.22 | 260.76 | 7 | 6 | 34.6 | 1 | 53.13 | 0 | 0 | 0 | 0 | 0 | 0 | 37.25
Mr. Arun Felbin | TA421 | D K Verma | 6.17 | 213.5 | 5 | 4 | 37.15 | 1 | 64.89 | 0 | 0 | 0 | 0 | 0 | 0 | 42.7
Mr. Arun Felbin | TA505 | Jagannaath Saw Mp | 6.65 | 221.76 | 4 | 1 | 34.79 | 2 | 62.26 | 1 | 62.44 | 0 | 0 | 0 | 0 | 55.44
Mr. Arun Felbin | TA505 | Pankaj Singh Mp | 5.54 | 181.2 | 5 | 5 | 36.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.24
Mr. Arun Felbin | TA505 | Deglal Mahato Mp | 5.14 | 144.08 | 4 | 4 | 36.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.02
Mr. Arun Felbin | TA506 | Horil Mahto | 5.97 | 178.01 | 6 | 3 | 21.03 | 1 | 36.59 | 1 | 31.86 | 1 | 46.47 | 0 | 0 | 29.67
Mr. Arun Felbin | TA506 | Karni Const 3 | 5.78 | 109.74 | 4 | 2 | 17.88 | 0 | 0 | 0 | 0 | 2 | 36.99 | 0 | 0 | 27.43
Mr. Arun Felbin | TA506 | Karni Const 1 | 5.31 | 90.08 | 4 | 3 | 16.82 | 0 | 0 | 1 | 39.62 | 0 | 0 | 0 | 0 | 22.52
Mr. Dheeraj Vashishth | TA513 | Anil Construction | 4.11 | 122.2 | 6 | 5 | 18.48 | 0 | 0 | 1 | 29.78 | 0 | 0 | 0 | 0 | 20.37
Bottom 3 Gangs
PCH | Project | Gang Name | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari 1 | 3.1 | 155.83 | 4 | 4 | 38.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.96
Mr. Sanjay Kumar Gupta | TA413 | Jwala Singh 1 | 4.4 | 147.62 | 4 | 4 | 36.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.91
Mr. Sanjay Kumar Gupta | TA419 | Jwala Singh | 5.17 | 153.26 | 4 | 4 | 38.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.32
Mr. Sanjay Kumar Gupta | TA512 | M S Jwala Singh | 5.38 | 167.01 | 4 | 4 | 41.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.75
Mr. Sanjay Kumar Gupta | TA512 | M S Kartik Mahto | 6.95 | 270.18 | 7 | 7 | 38.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.6
Mr. Sanjay Kumar Gupta | TB401 | Sunny Const | 3.76 | 192.75 | 4 | 3 | 41.63 | 1 | 67.87 | 0 | 0 | 0 | 0 | 0 | 0 | 48.19
Mr. Sanjay Kumar Gupta | TB408 | Chinta Devi | 5.87 | 188.15 | 4 | 3 | 40.59 | 0 | 0 | 1 | 66.38 | 0 | 0 | 0 | 0 | 47.04
Mr. Sanjay Kumar Gupta | TB408 | Ganesh Sinha | 5.92 | 188.15 | 4 | 3 | 40.59 | 0 | 0 | 1 | 66.38 | 0 | 0 | 0 | 0 | 47.04
Mr. Sanjay Kumar Gupta | TB408 | Shobha Devi | 6.59 | 253.65 | 5 | 4 | 43.88 | 0 | 0 | 1 | 78.13 | 0 | 0 | 0 | 0 | 50.73
Mr. Sanjay Kumar Gupta | TB507 | Bhoi Enterprises | 2.58 | 76.58 | 6 | 5 | 11.32 | 0 | 0 | 1 | 20.01 | 0 | 0 | 0 | 0 | 12.76
Mr. Sanjay Kumar Gupta | TB507 | Dipak | 2.67 | 85.37 | 4 | 0 | 0 | 3 | 21.32 | 0 | 0 | 1 | 21.41 | 0 | 0 | 21.34
Mr. Sanjay Kumar Gupta | TB507 | Gokul Sarkar | 2.74 | 96 | 4 | 0 | 0 | 3 | 18.87 | 0 | 0 | 1 | 39.4 | 0 | 0 | 24
Mr. Arun Felbin | TA421 | D K Verma | 6.17 | 213.5 | 5 | 4 | 37.15 | 1 | 64.89 | 0 | 0 | 0 | 0 | 0 | 0 | 42.7
Mr. Arun Felbin | TA421 | Subash | 8.22 | 260.76 | 7 | 6 | 34.6 | 1 | 53.13 | 0 | 0 | 0 | 0 | 0 | 0 | 37.25
Mr. Arun Felbin | TA421 | Khatun | 9.41 | 224.81 | 5 | 3 | 34.91 | 2 | 60.04 | 0 | 0 | 0 | 0 | 0 | 0 | 44.96
Mr. Arun Felbin | TA505 | Jhemon Mahato 2 | 4.05 | 171.75 | 4 | 3 | 37.93 | 1 | 57.96 | 0 | 0 | 0 | 0 | 0 | 0 | 42.94
Mr. Arun Felbin | TA505 | Deglal Mahato Mp | 5.14 | 144.08 | 4 | 4 | 36.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.02
Mr. Arun Felbin | TA505 | Pankaj Singh Mp | 5.54 | 181.2 | 5 | 5 | 36.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.24
Mr. Arun Felbin | TA506 | Govind Mahto | 4.65 | 92.25 | 4 | 3 | 18.56 | 1 | 36.59 | 0 | 0 | 0 | 0 | 0 | 0 | 23.06
Mr. Arun Felbin | TA506 | Gulab Mahto | 4.7 | 79.33 | 4 | 3 | 17.41 | 1 | 27.09 | 0 | 0 | 0 | 0 | 0 | 0 | 19.83
Mr. Arun Felbin | TA506 | Jai Prakash Mahto | 4.75 | 140.26 | 6 | 4 | 17.72 | 0 | 0 | 1 | 29.78 | 1 | 39.6 | 0 | 0 | 23.38
Mr. Dheeraj Vashishth | TA513 | Anil Construction | 4.11 | 122.2 | 6 | 5 | 18.48 | 0 | 0 | 1 | 29.78 | 0 | 0 | 0 | 0 | 20.37