## Erection Summary
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
3.79 | 4.19 | 4.1 | 3.91 | 3.98 | 3.98 | 13708.35 | 322 | 195 | 30.65 | 47 | 57.7 | 43 | 53.45 | 37 | 73.54 | 0 | 0 | 42.57
PCH | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | 3.99 | 4.05 | 3.83 | 3.86 | 4.26 | 3.88 | 5842.61 | 142 | 91 | 32.05 | 21 | 62.32 | 17 | 40.33 | 13 | 71.64 | 0 | 0 | 41.15
Mr. Arun Felbin | 3.71 | 4.22 | 4.25 | 3.99 | 3.82 | 4.07 | 7719.27 | 174 | 101 | 29.71 | 25 | 55.04 | 24 | 64.73 | 24 | 74.56 | 0 | 0 | 44.36
Mr. Dheeraj Vashishth | 3.21 | 4.76 | 4.7 | 3.63 | 3.39 | 4 | 146.48 | 6 | 3 | 19.94 | 1 | 27.09 | 2 | 29.78 | 0 | 0 | 0 | 0 | 24.41
[6 empty] | Total | 13708.36 | 322
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA413 | 4.18 | 4.26 | 3.8 | 3.89 | 3.81 | 4.02 | 1899.66 | 36 | 22 | 38.99 | 9 | 65.71 | 1 | 62.44 | 4 | 97.04 | 0 | 0 | 52.77
Mr. Sanjay Kumar Gupta | TA419 | 4.55 | 4.68 | 3.99 | 3.56 | 3.55 | 4.07 | 501.73 | 8 | 5 | 39.11 | 1 | 69.38 | 1 | 99.78 | 1 | 137.05 | 0 | 0 | 62.72
Mr. Sanjay Kumar Gupta | TA512 | 5.13 | 4.87 | 4.81 | 5.33 | 4.67 | 4.99 | 589.12 | 13 | 10 | 40.69 | 2 | 57.48 | 1 | 67.26 | 0 | 0 | 0 | 0 | 45.32
Mr. Sanjay Kumar Gupta | TB401 | 3.18 | 3.19 | 3.2 | 3.12 | 6.18 | 3.35 | 892.9 | 17 | 12 | 41.37 | 3 | 61.96 | 1 | 81.5 | 1 | 129.11 | 0 | 0 | 52.52
Mr. Sanjay Kumar Gupta | TB408 | 4.4 | 4.43 | 4.74 | 4.5 | 4.68 | 4.55 | 1309.16 | 25 | 17 | 39.76 | 5 | 65.82 | 2 | 80.3 | 1 | 143.6 | 0 | 0 | 52.37
Mr. Sanjay Kumar Gupta | TB507 | 2.49 | 2.88 | 2.42 | 2.77 | 2.65 | 2.64 | 650.04 | 43 | 25 | 11.38 | 1 | 18.11 | 11 | 19.46 | 6 | 22.22 | 0 | 0 | 15.12
Mr. Arun Felbin | TA325 | 2.93 | 4.1 | 4.09 | 3.81 | 3.54 | 3.77 | 2246.3 | 40 | 20 | 38.11 | 9 | 62.57 | 3 | 72.87 | 8 | 87.8 | 0 | 0 | 56.16
Mr. Arun Felbin | TA414 | 3.24 | 0 | 0 | 0 | 0 | 3.24 | 55.05 | 1 | 0 | 0 | 1 | 55.04 | 0 | 0 | 0 | 0 | 0 | 0 | 55.04
Mr. Arun Felbin | TA416 | 4.38 | 4.27 | 3.61 | 3.68 | 3.58 | 4.05 | 1096.24 | 13 | 3 | 46.02 | 2 | 65.8 | 6 | 96.9 | 2 | 122.58 | 0 | 0 | 84.33
Mr. Arun Felbin | TA418 | 2.65 | 2.66 | 2.81 | 2.89 | 2.99 | 2.77 | 298 | 7 | 3 | 27.67 | 1 | 45 | 3 | 56.67 | 0 | 0 | 0 | 0 | 42.57
Mr. Arun Felbin | TA421 | 4.02 | 5.61 | 5.51 | 4.72 | 4.46 | 4.93 | 705.78 | 18 | 17 | 37.24 | 0 | 0 | 0 | 0 | 1 | 72.63 | 0 | 0 | 39.21
Mr. Arun Felbin | TA504 | 4.03 | 4.13 | 4.1 | 3.91 | 3.81 | 4.03 | 335.19 | 7 | 4 | 36.7 | 3 | 62.79 | 0 | 0 | 0 | 0 | 0 | 0 | 47.88
Mr. Arun Felbin | TA505 | 4.55 | 4.83 | 4.94 | 4.16 | 3.47 | 4.51 | 1425.78 | 26 | 13 | 36.3 | 4 | 57.85 | 5 | 69.63 | 4 | 93.58 | 0 | 0 | 54.84
Mr. Arun Felbin | TA506 | 3.84 | 3.97 | 4.68 | 4.79 | 4.87 | 4.31 | 1556.93 | 62 | 41 | 18.66 | 5 | 32.31 | 7 | 33.6 | 9 | 43.89 | 0 | 0 | 25.11
Mr. Dheeraj Vashishth | TA513 | 3.21 | 4.76 | 4.7 | 3.63 | 3.39 | 4 | 146.48 | 6 | 3 | 19.94 | 1 | 27.09 | 2 | 29.78 | 0 | 0 | 0 | 0 | 24.41
[7 empty] | Total | 13708.36 | 322

## Project Gang Rankings
Top 3 Gangs
PCH | Project | Gang Name | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari 2 | 6.99 | 153.78 | 4 | 4 | 38.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.45
Mr. Sanjay Kumar Gupta | TA413 | Govind Mahto 1 | 4.87 | 154.58 | 4 | 4 | 38.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.64
Mr. Sanjay Kumar Gupta | TA512 | M S Punam Kumari | 4.93 | 199.63 | 5 | 5 | 39.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.93
Mr. Sanjay Kumar Gupta | TB408 | Shobha Devi | 6.07 | 286.82 | 5 | 2 | 42.34 | 2 | 67.87 | 1 | 66.38 | 0 | 0 | 0 | 0 | 57.36
Mr. Sanjay Kumar Gupta | TB408 | Nirmal Mahto | 5.17 | 179.79 | 4 | 3 | 40.73 | 1 | 57.6 | 0 | 0 | 0 | 0 | 0 | 0 | 44.95
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw 1 | 3.64 | 116.14 | 7 | 3 | 12 | 0 | 0 | 3 | 19.58 | 1 | 21.41 | 0 | 0 | 16.59
Mr. Sanjay Kumar Gupta | TB507 | Pritam Enterprises | 3.28 | 127.47 | 10 | 8 | 11.25 | 0 | 0 | 2 | 18.73 | 0 | 0 | 0 | 0 | 12.75
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw 2 | 3.13 | 99.25 | 6 | 3 | 11.15 | 1 | 18.11 | 0 | 0 | 2 | 23.85 | 0 | 0 | 16.54
Mr. Arun Felbin | TA421 | D K Verma | 7.3 | 153.96 | 4 | 4 | 38.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.49
Mr. Arun Felbin | TA421 | Khatun | 6.5 | 184.42 | 5 | 5 | 36.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.88
Mr. Arun Felbin | TA421 | Subash | 6.04 | 175.72 | 4 | 3 | 34.36 | 0 | 0 | 0 | 0 | 1 | 72.63 | 0 | 0 | 43.93
Mr. Arun Felbin | TA505 | Deglal Mahato | 7.77 | 296.39 | 4 | 0 | 0 | 1 | 65.03 | 1 | 67.26 | 2 | 82.05 | 0 | 0 | 74.1
Mr. Arun Felbin | TA505 | Pankaj Singh Mp | 4.93 | 163.93 | 4 | 3 | 36.16 | 1 | 55.45 | 0 | 0 | 0 | 0 | 0 | 0 | 40.98
Mr. Arun Felbin | TA505 | Deglal Mahato Mp | 4.54 | 144.08 | 4 | 4 | 36.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.02
Mr. Arun Felbin | TA506 | Karni Const 2 | 5.65 | 132.92 | 4 | 2 | 18.12 | 0 | 0 | 0 | 0 | 2 | 48.34 | 0 | 0 | 33.23
Mr. Arun Felbin | TA506 | Jai Prakash Mahto | 5.29 | 176.76 | 5 | 1 | 22.49 | 1 | 34.17 | 2 | 33.49 | 1 | 53.12 | 0 | 0 | 35.35
Mr. Arun Felbin | TA506 | Gulab Mahto | 4.91 | 89.44 | 5 | 5 | 17.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.89
Mr. Dheeraj Vashishth | TA513 | Anil Construction | 4 | 146.48 | 6 | 3 | 19.94 | 1 | 27.09 | 2 | 29.78 | 0 | 0 | 0 | 0 | 24.41
Bottom 3 Gangs
PCH | Project | Gang Name | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | DA | DA Avg Tower Weight | DB | DB Avg Tower Weight | DC | DC Avg Tower Weight | DD | DD Avg Tower Weight | Exception | Exception Avg Tower Weight | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA413 | Govind Mahto 1 | 4.87 | 154.58 | 4 | 4 | 38.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.64
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari 2 | 6.99 | 153.78 | 4 | 4 | 38.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.45
Mr. Sanjay Kumar Gupta | TA512 | M S Punam Kumari | 4.93 | 199.63 | 5 | 5 | 39.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.93
Mr. Sanjay Kumar Gupta | TB408 | Nirmal Mahto | 5.17 | 179.79 | 4 | 3 | 40.73 | 1 | 57.6 | 0 | 0 | 0 | 0 | 0 | 0 | 44.95
Mr. Sanjay Kumar Gupta | TB408 | Shobha Devi | 6.07 | 286.82 | 5 | 2 | 42.34 | 2 | 67.87 | 1 | 66.38 | 0 | 0 | 0 | 0 | 57.36
Mr. Sanjay Kumar Gupta | TB507 | Bhoi Enterprises | 2.05 | 76.99 | 6 | 5 | 11.65 | 0 | 0 | 1 | 18.73 | 0 | 0 | 0 | 0 | 12.83
Mr. Sanjay Kumar Gupta | TB507 | Gokul Sarkar | 2.82 | 87.4 | 6 | 4 | 11.14 | 0 | 0 | 0 | 0 | 2 | 21.41 | 0 | 0 | 14.57
Mr. Sanjay Kumar Gupta | TB507 | Dipak | 2.9 | 83.05 | 4 | 0 | 0 | 0 | 0 | 3 | 20.55 | 1 | 21.41 | 0 | 0 | 20.76
Mr. Arun Felbin | TA421 | Subash | 6.04 | 175.72 | 4 | 3 | 34.36 | 0 | 0 | 0 | 0 | 1 | 72.63 | 0 | 0 | 43.93
Mr. Arun Felbin | TA421 | Khatun | 6.5 | 184.42 | 5 | 5 | 36.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.88
Mr. Arun Felbin | TA421 | D K Verma | 7.3 | 153.96 | 4 | 4 | 38.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.49
Mr. Arun Felbin | TA505 | Deglal Mahato Mp | 4.54 | 144.08 | 4 | 4 | 36.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.02
Mr. Arun Felbin | TA505 | Pankaj Singh Mp | 4.93 | 163.93 | 4 | 3 | 36.16 | 1 | 55.45 | 0 | 0 | 0 | 0 | 0 | 0 | 40.98
Mr. Arun Felbin | TA505 | Deglal Mahato | 7.77 | 296.39 | 4 | 0 | 0 | 1 | 65.03 | 1 | 67.26 | 2 | 82.05 | 0 | 0 | 74.1
Mr. Arun Felbin | TA506 | Karni Const 6 | 3.53 | 67.48 | 4 | 4 | 16.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.87
Mr. Arun Felbin | TA506 | Horil Mahto | 3.68 | 167.01 | 7 | 5 | 19.59 | 0 | 0 | 2 | 34.54 | 0 | 0 | 0 | 0 | 23.86
Mr. Arun Felbin | TA506 | Karni Const 1 | 3.8 | 64.54 | 4 | 4 | 16.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.14
Mr. Dheeraj Vashishth | TA513 | Anil Construction | 4 | 146.48 | 6 | 3 | 19.94 | 1 | 27.09 | 2 | 29.78 | 0 | 0 | 0 | 0 | 24.41