## Erection Summary
Week 1 | Week 2 | Week 3 | Week 4 | Avg Productivity (MTD) | Total MT (For this month) (MTD) | Total No. of Erections (For this month) (MTD)
3.66 | 3.68 | 3.64 | 3.92 | 3.83 | 15190.52 | 370
PCH | Week 1 | Week 2 | Week 3 | Week 4 | Avg Productivity (MTD) | Total MT (For this month) (MTD) | Total No. of Erections (For this month) (MTD)
Mr. Sanjay Kumar Gupta | 3.56 | 3.43 | 3.79 | 4.1 | 4.17 | 6116.87 | 155
Mr. Arun Felbin | 3.47 | 3.58 | 3.44 | 3.83 | 3.62 | 6927.2 | 160
Unassigned | 4.08 | 4.11 | 3.79 | 3.9 | 3.74 | 2146.44 | 55
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Avg Productivity (MTD) | Total MT (For this month) (MTD) | Total No. of Erections (For this month) (MTD)
Mr. Sanjay Kumar Gupta | TA413 | 4.84 | 5.08 | 4.84 | 5.15 | 4.99 | 2888.61 | 65
Mr. Sanjay Kumar Gupta | TA419 | 3.12 | 2.74 | 3.87 | 4.23 | 3.51 | 341.46 | 6
Mr. Sanjay Kumar Gupta | TB408 | 5.02 | 4.33 | 4.53 | 4.7 | 4.66 | 2430.39 | 47
Mr. Sanjay Kumar Gupta | TB507 | 1.27 | 1.55 | 1.92 | 2.3 | 1.82 | 456.41 | 37
Mr. Arun Felbin | TA325 | 1.06 | 1.11 | 1.43 | 2.1 | 1.55 | 456.22 | 4
Mr. Arun Felbin | TA416 | 3.71 | 3.97 | 4.21 | 4.25 | 4.06 | 1514.48 | 17
Mr. Arun Felbin | TA418 | 3.24 | 2.75 | 2.96 | 2.85 | 2.93 | 393.2 | 10
Mr. Arun Felbin | TA421 | 6.48 | 6.71 | 4.23 | 4.41 | 5.33 | 910.59 | 22
Mr. Arun Felbin | TA504 | 2.42 | 2.87 | 3.38 | 4.03 | 3.23 | 463.99 | 9
Mr. Arun Felbin | TA505 | 3.62 | 3.91 | 4.07 | 4.85 | 4.22 | 1532.68 | 30
Mr. Arun Felbin | TA506 | 3.73 | 3.72 | 3.82 | 4.32 | 3.97 | 1656.05 | 68
Unassigned | DPR-T513_Dated_15.12.2025 | 0 | 0 | 3.83 | 3.6 | 3.68 | 46 | 2
Unassigned | TA414 | 5.73 | 4.58 | 3.51 | 3.24 | 4.14 | 117.97 | 2
Unassigned | TA509 | 2.2 | 2.91 | 3.68 | 4.5 | 3.36 | 693.14 | 19
Unassigned | TA512 | 4.37 | 5.41 | 5.37 | 5.43 | 5.14 | 657.82 | 17
Unassigned | TB401 | 4.04 | 3.53 | 2.56 | 2.74 | 3.26 | 631.51 | 15