## WeeklySummary
Week | Week Range | Erections Completed | Total Tower Weight (MT) | Avg Tower Weight (MT) | Avg Manpower | Avg Productivity (MT/day) | Active Gangs
Week 1 | 01-Dec-2025 - 07-Dec-2025 | 0 | 0 | 0 | 0 | 0
Week 2 | 08-Dec-2025 - 14-Dec-2025 | 2 | 75.77 | 37.88 | 29.5 | 5.69 | Pramod Kumar, Sakhila Khatun
Week 3 | 15-Dec-2025 - 21-Dec-2025 | 5 | 175.05 | 43.76 | 27.6 | 4.42 | Rahul Kumar, Sakhila Khatun, Sk Samirul, Zakir Hussain
Week 4 | 22-Dec-2025 - 28-Dec-2025 | 1 | 37.73 | 37.73 | 35 | 3.77 | Ranjan Kumar

## WeeklyDetails
Week | Completion Date | Location No. | Tower Type | Tower Weight (MT) | Manpower | Gang Name | Status | Starting Date | Productivity (MT/day) | DPR File
Week 2 | 2025-12-12 | 179/1 | DA+3 | 38.038 | 24 | Sakhila Khatun | Tower Erection Completed | 2025-12-08 | 7.61 | TA 414 - DPR - 2025-12-25.xlsx
Week 2 | 2025-12-13 | 244/1 | DA+0 | 37.729 | 35 | Pramod Kumar | Tower Erection Completed | 2025-12-04 | 3.77 | TA 414 - DPR - 2025-12-25.xlsx
Week 3 | 2025-12-15 | 132/0 | DB2+0 |  | 22 | Rahul Kumar | Tower Erection Completed | 2025-12-08 |  | TA 414 - DPR - 2025-12-25.xlsx
Week 3 | 2025-12-19 | 241/4 | DA+3 | 38.038 | 23 | Sk Samirul | Tower Erection Completed | 2025-12-06 | 2.72 | TA 414 - DPR - 2025-12-25.xlsx
Week 3 | 2025-12-20 | 131/2 | DA+0 | 37.729 | 33 | Rahul Kumar | Tower Erection Completed | 2025-12-15 | 6.29 | TA 414 - DPR - 2025-12-25.xlsx
Week 3 | 2025-12-20 | 148/2 | DA+0 | 37.729 | 25 | Zakir Hussain | Tower Erection Completed | 2025-12-06 | 2.52 | TA 414 - DPR - 2025-12-25.xlsx
Week 3 | 2025-12-20 | 187/0 | DC1+0 | 61.551 | 35 | Sakhila Khatun | Tower Erection Completed | 2025-12-11 | 6.16 | TA 414 - DPR - 2025-12-25.xlsx
Week 4 | 2025-12-23 | 244/5 | DA+0 | 37.729 | 35 | Ranjan Kumar | Tower Erection Completed | 2025-12-14 | 3.77 | TA 414 - DPR - 2025-12-25.xlsx

## GangWeekly
Gang Name | Week 1 | Week 2 | Week 3 | Week 4 | Avg Productivity (MT/day) | Erections Completed
Pramod Kumar | 0 | 3.77 | 0 | 0 | 3.77 | 1
Rahul Kumar | 0 | 0 | 6.29 | 0 | 6.29 | 2
Ranjan Kumar | 0 | 0 | 0 | 3.77 | 3.77 | 1
Sakhila Khatun | 0 | 7.61 | 6.16 | 0 | 6.88 | 2
Sk Samirul | 0 | 0 | 2.72 | 0 | 2.72 | 1
Zakir Hussain | 0 | 0 | 2.52 | 0 | 2.52 | 1

## SelectionContext
Project Code | Analysis Month | Month Start | Month End | As Of Date | Source DPR Files | Total Completions (Month) | Unique Locations | Unique Gangs
TA414 | December 2025 | 2025-12-01 | 2025-12-31 | 2025-12-23 | TA 414 - DPR - 2025-12-25.xlsx | 8 | 8 | 6