## WeeklySummary
Week | Week Range | Erections Completed | Total Tower Weight (MT) | Avg Tower Weight (MT) | Avg Manpower | Avg Productivity (MT/day) | Active Gangs
Week 1 | 01-Dec-2025 - 07-Dec-2025 | 3 | 281.5 | 93.83 | 0 | 4.97 | Pankaj Kumar, Pinky Dewi, Punam Kumari 1
Week 2 | 08-Dec-2025 - 14-Dec-2025 | 1 | 110.7 | 110.7 | 0 | 3.95 | Punam Kumari 3
Week 3 | 15-Dec-2025 - 21-Dec-2025 | 2 | 139.6 | 69.8 | 0 | 4.65 | Pankaj Kumar, Pinky Dewi
Week 4 | 22-Dec-2025 - 28-Dec-2025 | 0 | 0 | 0 | 0 | 0

## WeeklyDetails
Week | Completion Date | Location No. | Tower Type | Tower Weight (MT) | Manpower | Gang Name | Status | Starting Date | Productivity (MT/day) | Source
Week 1 | 2025-12-04 | 59/0 | DD60+6 | 113.68 |  | Pinky Dewi | COMPLETED | 2025-11-16 | 5.98 | ProdDailyExpandedSingles.parquet
Week 1 | 2025-12-04 | 62/0 | DC+25 | 124.04 |  | Pankaj Kumar | COMPLETED | 2025-11-10 | 4.96 | ProdDailyExpandedSingles.parquet
Week 1 | 2025-12-07 | 66/1 | DA+0 | 43.776 |  | Punam Kumari 1 | COMPLETED | 2025-11-27 | 3.98 | ProdDailyExpandedSingles.parquet
Week 2 | 2025-12-14 | 23/0 | DC+18 | 110.696 |  | Punam Kumari 3 | COMPLETED | 2025-11-17 | 3.95 | ProdDailyExpandedSingles.parquet
Week 3 | 2025-12-19 | 66/0 | DD60+0 | 97.229 |  | Pankaj Kumar | COMPLETED | 2025-12-05 | 6.48 | ProdDailyExpandedSingles.parquet
Week 3 | 2025-12-21 | 57/1 | DA-3 | 42.374 |  | Pinky Dewi | COMPLETED | 2025-12-07 | 2.82 | ProdDailyExpandedSingles.parquet

## GangWeekly
Gang Name | Week 1 | Week 2 | Week 3 | Week 4 | Avg Productivity (MT/day) | Erections Completed
Pankaj Kumar | 4.96 | 0 | 6.48 | 0 | 5.72 | 2
Pinky Dewi | 5.98 | 0 | 2.82 | 0 | 4.4 | 2
Punam Kumari 1 | 3.98 | 0 | 0 | 0 | 3.98 | 1
Punam Kumari 3 | 0 | 3.95 | 0 | 0 | 3.95 | 1

## SelectionContext
Project Code | Analysis Month | Month Start | Month End | As Of Date | Source DPR Files | Total Completions (Month) | Unique Locations | Unique Gangs
TA416 | December 2025 | 2025-12-01 | 2025-12-31 | 2025-12-21 | ProdDailyExpandedSingles.parquet (compiled) | 6 | 6 | 4