## TB401 DPR..... (hidden)
| Project Code |  | TB-401 |  | Date |  | 2026-03-16 | LOA Start Date |  |  | 2023-04-25 | Business Head (T&D)- India & Sri Lanka |  |  | Rajinder Gupta
| Project Name |  | 765KV D/C Fategarh-III Beawar Transmission Line |  |  |  |  | LOA End Date |  |  | 2024-07-25 | PCH |  |  | Sivaraman Nataraajan
| Client Name |  | Strelite Power |  |  |  |  | Time Extn |  |  | 2024-07-25 | Regional Manager |  |  | Sandeep Singh Kumar
| LE Value |  | Rs 312 Cr -Supply -Rs 227.5 Cr.; Service.-Rs 84.4 Cr |  |  |  |  | Planning |  |  | Shah Ali Khan | Project Manager |  |  | Virender Gupta
Activity | Unit | LOA Qty. | LE Qty | Progress till Last Month | Balance | L2 for Dec'23 | Plan for Dec.'23 | Today's Progress | Month Progress | WIP | Gangs at Present | L2 Till Month-Dec.23 | Progress Till Date | Balance Work | Remarks
Route Alignment | km | 215 | 202 | 167 | 35 | 0 | 35 |  |  |  |  | 215 | 167 | 35 | 35 Km is hold due to ROW issues
Detailed Survey | km | 215 | 202 | 202 | 0 | 0 | [5 empty] | 215 | 202 | 0 | SPTL Approved -202/202-Kms
Check Survey | km | 215 | 202 | 92.704 | 109.296 | 20 | 50 |  | 17.852 |  |  | 160 | 110.556 | 91.444 | 1. Total 7.854 Km is under review of SPTL. 2. Total check survey completed (Field work) 167 Km. 3. Total 60 Km check survey is hold due to row issues & Other issues.
Foundation | Nos | 534 | 521 | 109 | 412 | 75 | 30 |  | 1 | 4 | 3 | 399 | 110 | 411 |  | 12.48% | -2.434% | -13 | 48 | 306
Earthing | Nos | 534 | 521 | 106 | 415 | 75 | 30 |  | 2 |  |  | 399 | 108 | 413 |  | 12.48%
Tower Erection | Nos | 534 | 521 | 45 | 476 | 75 | 40 | 2 | 6 | 5 | 5 | 260 | 51 | 470 | 56/2 58/15 Complete | 12.48%
Tack welding | Nos | 534 | 521 | 15 | 506 | 75 | 40 | 1 | 3 | 1 | 1 | 260 | 18 | 503 | 56/7 complete | 12.48%
Stringing | Km | 215 | 202 | 0 | 202 | 20 | [5 empty] | 25 | 0 | 202 |  | 10.22% |  | 68.21%
#DIV/0!

## Eng. (hidden)
Tower | Tower Design |  | Test Tower |  | Balance Structural Drawing. |  | Tower | Stub & Template Drawings | Foundation
Types |  |  | Structural Drawing(BTB+0) |  | (3M/6M/9M) |  | Testing |  | Design/Drg
| Target | Status | Target | Status | Target | Status |  |  | Target | Status
DA Tower | 2023-05-12 | Approved | 2023-06-04 | Approved | 2023-06-24 | Approved for proto | Completed | Approved | 15-July | Approved
DB Tower | 2023-05-30 | Approved | 2023-07-30 | Approved | 2023-07-19 | Approvedin Cat-B | Completed | Approved for Proto | DB all Fdn. By 25 -July | Approved
DD Tower | 2023-06-21 | Approved | 30-Sept. | Approved in Cat -B | 2023-08-20 | Approved in Cat -B | Completed | Approved in Cat -B | 2023-07-31 | Approved
DC Tower | 2023-07-16 | Approved | 2023-10-08 | Approved in Cat -B | 2023-09-19 | Approved in Cat -B | Completed | Approved in Cat -B | 2023-08-25 | Approved

## Fdn (Pkg -G Section -I) (hidden)
KEC INTERNATIONAL LIMITED | [10 empty] | Date: | 2026-03-16
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
FOUNDATION
Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Classification | Excavation Start | Dt. of Start | Dt. of Concrete | Name of Sub-Contractor | KEC representative | KEC Section In-Charge | Remarks
1 | 1 |  | 32/7 | DA+0 | SANDY | 23.10.23 | 25.10.23 | 28.10.23 | Shakti Construction | Kumar Nayak | Jish C Verghese | Complete
2 | 2 |  | 32/5 | DA+6 | SANDY | 29.10.23 | 31.10.23 | 04.11.2023 | Shakti Construction | Kumar Nayak | Jish C Verghese | Complete
3 | 3 |  | 32/1 | DA+9 | SANDY | 03.11.23 | 06.11.23 | 10.11.23 | Shakti Construction | Kumar Nayak | Jish C Verghese | Complete
4 | 4 |  | 30/2 | DA+0 | SANDY | 13.11.23 | 15.11.23 | 16.11.23 | Shakti Construction | Kumar Nayak | Jish C Verghese | Complete
5 | 5 |  | 32/0 | DB2+6 | SANDY | 18.11.23 | 20.11.23 | 28.11.23 | Shakti Construction | Dipesh | Jish C Verghese | Complete
Dec-23
1 | 6 |  | 31/3 | DA+0 | SANDY | 28.11.23 | 30.11.23 | 04.12.23 | Shakti Construction | Dipesh | Jish C Verghese | Complete

## TB401 DPR (hidden)
Project Progress for TB-401/408,Section-II
765KV D/C Fategarh-III Beawar Transmission Line |  |  | TB-401 |  |  | LOA Date |  | Pkg-G -26.04.23 |  |  | Completion Period |  | 2025-03-31 |  |  | Date: | 2026-03-16
|  |  | TB-408 |  |  |  |  | Pkg-F - 11.09.23 |  |  | Completion Period |  | 2025-03-31
.
Activity | Qty as per LOA | Qty Received | L2 |  | Overall Progress |  | Mar'25 |  | Balance | Apr'25 |  |  |  | Plan |  | Remarks
|  |  | 2024-12-30 | Till Mar-25 | As on date | Till Mar-25 | Plan | Actual | As on date | Plan | WIP | Today comp | Actual | 2024-09-01 | 2024-07-01
Details Survey | 215 | 189.53 |  | 203 | 199.841 | 199.841
Pkg-G (Section-II) |  | 101.1 |  | 107.5 | 101.1 | 101.1
Pkg-F (Section-II) |  | 88.43 |  | 95.5 | 98.741 | 98.741
Check Survey | 215 | 189.53 | 0 | 203 | 189.526 | 184.552 | 14.88 | 6.08 | 0.004 | 0 | 0 |  | 4.974 | 0
Pkg-G (Section-II) |  | 101.1 |  | 107.5 | 101.096 | 101.096 | 6.08 | 6.08 | 0.004
Pkg-F (Section-II) |  | 88.43 |  | 95.5 | 88.43 | 83.456 | 8.8 |  | 0 |  |  |  | 4.974
Foundation | 534 | 488 | 0 | 488 | 486 | 485 | 9 | 6 | 2 | 0 | 2 |  | 1 | 0 | 0
Pkg-G (Section-II) |  | 265 |  | 265 | 265 | 265 | 5 | 5 | 0 | [8 empty] | 9649905358 | D S Jangid
Pkg-F (Section-II) |  | 223 |  | 223 | 221 | 220 | 4 | 1 | 2 |  | 2 | 1 | 1 |  |  | 46/0 Complete |  | 7014675307 | jangid
Gang / Worker | [9 empty] | 10/180 | 02/55
Erection | 534 | 488 | 0 | 488 | 369 | 365 | 36 | 24 | 119 | 0 | 4 | 1 | 4 | 0 | 0
Pkg-G (Section-II) |  | 265 |  | 265 | 201 | 201 | 20 | 11 | 64 |  | 2
Pkg-F (Section-II) |  | 223 |  | 223 | 168 | 164 | 16 | 13 | 55 |  | 2 | 1 | 4 |  |  | 70/9 Complete
Gang / Worker | [9 empty] | 7/240 | 4/241
Stringing Payout | 215 | 189.53 | 0 | 189.53 | 95.792 | 94.743 | 0 | 9.18 | 93.738 | 0 | 0.832 | 0 | 1.049 | 0 | 15
Pkg-G (Section-II) |  | 101.1 |  | 101.1 | 52.284 | 52.284 |  |  | 48.816
Pkg-F (Section-II) |  | 88.43 |  | 88.43 | 43.508 | 42.459 |  | 9.18 | 44.922 |  | 0.832 |  | 1.049
Gang / Worker | [10 empty] | 2/154
Stringing Final sag | 215 | 189.53 | 0 | 189.53 | 89.984 | 88.935 | 0 | 14.161 | 99.546 | 0 | 5.808 | 1.049 | 1.049 | 0 | 15
Pkg-G (Section-II) |  | 101.1 |  | 101.1 | 49.703 | 49.703 |  | 4.981 | 51.397 |  | 2.581
Pkg-F (Section-II) |  | 88.43 |  | 88.43 | 40.281 | 39.232 |  | 9.18 | 48.149 |  | 3.227 | 1.049 | 1.049 |  |  | 51/0 to 52/0 Complete
Gang / Worker | [10 empty] | 2/154

## Foundation (Pkg-F) (hidden)
KEC INTERNATIONAL LIMITED | [10 empty] | Date: | 2026-03-16
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
FOUNDATION Pkg -F (Section -II)
Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Classification | Excavation Start | Dt. of Start | Dt. of Concrete | Name of Sub-Contractor | KEC representative | KEC Section In-Charge | Remarks
2023-12-01
1 | 1 |  | 61/3 | DA+6 | DRY | 11.12.23 | 13.12.23 | 14.12.23 | Manoj Sharma | Dipesh | RT Singh | Complete
2 | 2 |  | 62/6 | DA+3 | DRY | 08.12.23 | 16.12.23 | 18.12.23 | Shakti Construction | sanjay | Rakesh Pathak | Complete
3 | 3 |  | 59/14 | DA+6 | DRY | 13.12.23 | 17.12.23 | 18.12.23 | Manoj Sharma | Dipesh | RT Singh | Complete
4 | 4 |  | 62/7 | DA+3 | DRY | 08.12.23 | 19.12.23 | 21.12.23 | Shakti Construction | Umesh Kumar | Rakesh Pathak | Complete
5 | 5 |  | 59/13 | DA+3 | DRY | 17.12.23 | 21.12.23 | 21.12.23 | Manoj Sharma | Dipesh | RT Singh | Complete
6 | 6 |  | 63/8 | DA+3 | DRY | 08.12.23 | 22.12..23 | 24.12.23 | Mahadev Eng | Dipesh | Rakesh Pathak | Complete
7 | 7 |  | 59/10 | DA+0 | DRY | 20.12.23 | 23.12.23 | 24.12.23 | Manoj Sharma | Dipesh | RT Singh | Complete
8 | 8 |  | 62/5 | DA+0 | DRY | 18.12.23 | 22.12..23 | 25.12.23 | Shakti Construction | sanjay | Rakesh Pathak | Complete
9 | 9 |  | 59/9 | DA+3 | DRY | 21.12.23 | 25.12.23 | 26.12.23 | Manoj Sharma | Dipesh | RT Singh | Complete
10 | 10 |  | 60/9 | DA+3 | DRY | 20.12.23 | 26.12.23 | 27.12.23 | Imran | Ganesh | Sumit | Complete
11 | 11 |  | 62/4 | DA+3 | DRY | 08.12.23 | 26.12.23 | 28.12.23 | Shakti Construction | sanjay | Rakesh Pathak | Complete | Excavation & Rod binding - Amirul
12 | 12 |  | 59/8 | DB+3 | DRY | 24.12.23 | 27.12.23 | 28.12.23 | Manoj Sharma | Kumar nayak | Sumit | Complete
13 | 13 |  | 59/6 | DA+3 | DFR | 17.12.23 | 27.12.23 | 29.12.23 | OM Const | Umesh Kumar | Rakesh Pathak | Complete
14 | 14 |  | 63/6 | DA+3 | DRY | 18.12.23 | 27.12.23 | 29.12.23 | Mahadev Eng | Dipesh | Rakesh Pathak | Complete
15 | 15 |  | 60/8 | DA+0 | DRY | 24.12.23 | 26.12.23 | 29.12.23 | Imran | Ganesh | Sumit | Complete
16 | 16 |  | 59/7 | DA+3 | DRY | 25.12.23 | 29.12.23 | 30.12.23 | Manoj Sharma | Kumar nayak | RT Singh | Complete
17 | 17 |  | 59/5 | DA+3 | DFR | 15.12.23 | 25.12.23 | 31.12.23 | OM Const | Umesh Kumar | RT Singh | Complete
18 | 18 |  | 62/3 | DA+0 | DRY | 25.12.23 | 30.12.23 | 31.12.23 | Shakti Construction | sanjay | Rakesh Pathak | Complete
2024-01-01
19 | 1 |  | 59/12 | DA+6 | DFR | 19.12.23 | 04.01.24 | 05.01.24 | Manoj Sharma | Kumar nayak | RT Singh | Complete | 284
20 | 2 |  | 60/7 | DA+3 | DRY | 24.12.23 | 01.01.24 | 05.01.24 | Imran | Ganesh | RT Singh | Complete
21 | 3 |  | 62/2 | DA+3(RC) | DRY | 29.12.23 | 02.01.24 | 05.01.24 | Shakti Construction | sanjay | Rakesh Pathak | Complete
22 | 4 |  | 59/3 | DA+3(RC) | DFR | 30.12.23 | 03.01.24 | 05.01.24 | OM Const | Umesh Kumar | RT Singh | Complete
23 | 5 |  | 64/0 | DB2+0 | DRY | 20.12.23 | 04.01.24 | 08.01.24 | Mahadev Eng | Dipesh | Rakesh Pathak | Complete
24 | 6 |  | 57/3 | DA+0 | DRY | 04.01.24 | 06.01.24 | 08.01.24 | OM Const |  | RT Singh | Complete
25 | 7 |  | 60/5 | DA+3 | DRY | 02.01.24 | 08.01.24 | 09.01.24 | Manoj Sharma | Kumar nayak | RT Singh | Complete | 249
26 | 8 |  | 65/2 | DA+0 | DRY | 30.12.23 | 08.01.24 | 10.01.24 | Veerteja Enterprises | Rakesh Pathak | Rakesh Pathak | Complete
27 | 9 |  | 62/11 | DA+3 | DRY | 05.01.24 | 09.01.24 | 10..01.24 | Shakti Construction | Rakesh Pathak | Rakesh Pathak | Complete
28 | 10 |  | 65/11 | DA+0 | DRY | 05.01.24 | 09.01.24 | 10.01.24 | Bhati Const. | R Pandey | Rakesh Pathak | Complete
29 | 11 |  | 60/6 | DA+0 | DRY | 7.0124 | 10.01.24 | 11.01.24 | Manoj Sharma | Kumar nayak | RT Singh | Complete
30 | 12 |  | 57/2 | DA+3 | DRY | 07.01.24 | 09.01.24 | 11.01.24 | OM Const | RT Singh | RT Singh | Complete | 323
31 | 13 |  | 62/10 | DA+0 | DFR | 06.01.24 | 11.01.24 | 13.01.24 | Shakti Construction | Rakesh Pathak | Rakesh Pathak | Complete
32 | 14 |  | 65/9 | DA+0 | DRY | 05.01.24 | 11.01.24 | 13.01.24 | Bhati Const. | Rakesh Pathak | Rakesh Pathak | Complete
33 | 15 |  | 57/4 | DA+0 | SANDY | 07.01.24 | 12.01.24 | 2024-01-14 | OM Const | RT Singh | RT Singh | Complete
34 | 16 |  | 64/4 | DA+3 | DRY | 09.01.24 | 2024-01-13 | 2024-01-14 | Mahadev Eng |  | Rakesh Pathak | Complete
35 | 17 |  | 65/3 | DA+3 | DRY | 03.01.24 | 13.01.24 | 15.01.2024 | Veerteja Enterprises | Dipesh | Rakesh Pathak | Complete
36 | 18 |  | 55/3 | DA+0 | SANDY | 06.01.24 | 09.01.24 | 15.01.2024 | Imran | RT Singh | RT Singh | Complete | 348
37 | 19 |  | 60/10 | DA+0 | DFR | 10.01.24 | 14.01.2024 | 15.01.2024 | Manoj Sharma |  | RT Singh | Complete | 252
38 | 20 |  | 62/8 | DA+0 | DFR | 11.01.24 | 15.01.2024 | 16.01.2024 | Shakti Construction |  | Rakesh Pathak | Complete | 270
39 | 21 |  | 55/4 | DA+0(RC) | SANDY | 11.01.24 | 12.01.24 | 17.01.2024 | Imran | RT Singh | RT Singh | Complete | 215
40 | 22 |  | 57/5 | DA+3 RC | SANDY | 10.01.24 | 14.01.2024 | 17.01.2024 | OM Const |  | RT Singh | Complete | 134
41 | 23 |  | 64/1 | DA+0 | DRY | 31.12.23 | 10.01.24 | 18.01.24 | Mahadev Eng | Mahesh | Rakesh Pathak | Complete | 215
42 | 24 |  | 64/5 | DA+3 | DRY |  | 16.01.2024 | 18.01.24 | Mahadev Eng |  | Rakesh Pathak | Complete | 249
43 | 25 |  | 65/6 | DA+0 | DRY | 11.01.24 | 16.01.2024 | 18.01.24 | Bhati Const. |  | Rakesh Pathak | Complete | 249
44 | 26 |  | 61/0 | DB2+0 | DRY | 14.01.24 | 17.01.2024 | 19.01.24 | Manoj Sharma | Kumar nayak | RT Singh | Complete | 426
45 | 27 |  | 62/9 | DA+3 | DFR |  | 18.01.24 | 19.01.24 | Shakti Construction | Rakesh Pathak | Rakesh Pathak | Complete | 254
46 | 28 |  | 65/5 | DA+0 | DRY | 17.01.24 | 20.01.24 | 21.01.2024 | Bhati Const. |  | Rakesh Pathak | Complete |  | 249
47 | 29 |  | 64/2 | DA+3 | DRY | 16.01.2024 | 20.01.24 | 21.01.2024 | Mahadev Eng | Dipesh | Rakesh Pathak | Complete |  | 249
48 | 30 |  | 57/6 | DA+3 RC | SANDY |  | 18.01.24 | 21.01.2024 | OM Const |  | RT Singh | Complete |  | 249
49 | 31 |  | 63/1 | DA+3 | DFR | 16.01.2024 | 21.01.24 | 23.01.24 | Shakti Construction |  | Rakesh Pathak | Complete | 100 | 149
50 | 32 |  | 64/9 | DA+3 | DRY | 10.01.24 | 22.01.24 | 24.01.24 | Veerteja Enterprises |  | Rakesh Pathak | Complete |  | 249
51 | 33 |  | 60/11 | DA+3 | DRY | 19.01.24 | 23.01.24 | 24.01.24 | Manoj Sharma |  | RT Singh | Complete
52 | 34 |  | 65/4 | DA+0 | DRY | 17.01.24 | 23.01.24 | 24.01.24 | Bhati Const. |  | Rakesh Pathak | Complete
53 | 35 |  | 63/7 | DA+3 | DRY | 23.12.23 | 24.01.24 | 25.01.24 | Mahadev Eng | Dipesh | Rakesh Pathak | Complete |  | 249
54 | 36 |  | 55/5 | DA+0 RC | SANDY |  | 17.01.24 | 25.01.24 | Imran | RT Singh | RT Singh | Complete | 310
55 | 37 |  | 55/6 | DA+0 RC | SANDY | 18.01.24 | 20.01.24 | 25.01.24 | Imran | RT Singh | RT Singh | Complete
56 | 38 |  | 63/2 | DA+0 | DFR | 20.01.24 | 24.01.24 | 25.01.24 | Shakti Construction |  | Rakesh Pathak | Complete
57 | 39 |  | 61/1 | DA+6 | DFR | 16.01.2024 | 27.01.24 | 28.01.24 | Manoj Sharma |  | RT Singh | Complete |  | 249
58 | 40 |  | 55/7 | DA+0 RC | SANDY | 23.01.24 | 27.01.24 | 29.01.24 | Imran | RT Singh | RT Singh | Complete
59 | 41 |  | 64/3 | DA+0 | DRY | 20.01.24 | 29.01.24 | 30.01.24 | Mahadev Eng |  | Rakesh Pathak | Complete
60 | 42 |  | 63/3 | DA+3 | DFR | 23.01.24 | 29.01.24 | 30.01.24 | Shakti Construction |  | Rakesh Pathak | Complete
61 | 43 |  | 64/8 | DA+3 | DRY | 20.01.24 | 29.01.24 | 31.01.24 | Veerteja Enterprises |  | Rakesh Pathak | Complete
62 | 44 |  | 61/2 | DA+6 | DFR | 22.01.24 | 30.01.24 | 31.01.24 | Manoj Sharma |  | RT Singh | Complete
Feb-24
63 | 1 |  | 64/7 | DA+3 | DRY | 23.01.24 | 01.02.24 | 02.02.24 | Mahadev Eng |  | Rakesh Pathak | Complete
64 | 2 |  | 52/5 | DA+9 RC | SANDY | 28.01.24 | 31.01.24 | 02.02.24 | Imran | RT Singh | RT Singh | Complete
65 | 3 |  | 63/4 | DA+0 | DRY | 28.01.24 | 01.02.24 | 02.02.24 | Shakti Construction |  | Rakesh Pathak | Complete
66 | 4 |  | 67/2 | DA+0 | DRY | 01.02.24 | 03.02.24 | 04.02.24 | Bhati Const. |  | Rakesh Pathak | Complete |  |  | JMC not done
67 | 5 |  | 52/6 | DA+6 | SANDY | 30.01.24 | 03.02.24 | 06.02.24 | Imran | RT Singh | RT Singh | Complete
68 | 6 |  | 64/6 | DA+0 | DRY | 29.01.24 | 03.02.24 | 07.02.24 | Mahadev Eng |  | Rakesh Pathak | Complete
69 | 7 |  | 63/5 | DA+3 | DFR | 01.02.24 | 06.02.24 | 07.02.24 | Shakti Construction |  | Rakesh Pathak | Complete
70 | 8 |  | 59/15 | DA+6 | DRY | 03.02.24 | 05.02.24 | 07.02.24 | OM Const |  | RT Singh | Complete
71 | 9 |  | 61/5 | DA+3 | DRY | 03.02.24 | 07.02.24 | 09.02.24 | Manoj Sharma |  | RT Singh | Complete
72 | 10 |  | 67/1 | DA+0 | DRY | 03.01.24 | 07.02.24 | 09.02.24 | Bhati Const. |  | Rakesh Pathak | Complete
73 | 11 |  | 64/10 | DA+3 | DRY | 28.01.24 | 08.02.24 | 10.02.24 | Veerteja Enterprises |  | Rakesh Pathak | Complete
74 | 12 |  | 61/6 | DA+3 | DRY | 06.02.24 | 09.02.24 | 11.02.24 | Manoj Sharma |  | RT Singh | Complete | 100
75 | 13 |  | 52/7 | DA+3 RC | SANDY |  | 07.02.24 | 12.02.24 | Imran |  | RT Singh | Complete
76 | 14 |  | 59/16 | DA+9 | Dry | 08.02.24 | 11.02.24 | 12.02.2024 | OM Const |  | RT Singh | Complete
77 | 15 |  | 63/0 | DC1+0 | DFR | 25.01.24 | 09.02.24 | 13.02.24 | Shakti Construction | Sanjay Thakur | Rakesh Pathak | Complete
78 | 16 |  | 52/8 | DA+6 | SANDY | 06.02.24 | 09.02.24 | 13.02.24 | Imran |  | RT Singh | Complete
79 | 17 |  | 61/7 | DA+9 RC | Dry | 09.02.24 | 11.02.24 | 13.02.24 | Manoj Sharma |  | RT Singh | Complete
80 | 18 |  | 61/9 | DA+0 | Dry | 12.02.24 | 14.02.24 | 16.02.24 | Manoj Sharma |  | RT Singh | Complete
81 | 19 |  | 60/1 | DA+6 | DRY |  | 14.02.24 | 16.02.24 | OM Const |  | RT Singh | Complete |  |  | JMC not done | 7.5
82 | 20 |  | 52/10 | DA+9 RC | SANDY |  | 14.02.24 | 17.02.24 | Imran |  | RT Singh | Complete
83 | 21 |  | 49/2 | DA+3 | SANDY | 12.02.24 | 14.02.24 | 18.02.24 | Veerteja Enterprises | Manoj | RT Singh | Complete
84 | 22 |  | 52/9 | DA+3 | SANDY | 13.02.24 | 17.02.24 | 19.02.24 | Imran |  | RT Singh | Complete
85 | 23 |  | 61/8 | DA+6 RC | DRY | 14.02.24 | 17.02.24 | 20.02.24 | Manoj Sharma |  | RT Singh | Complete |  |  | JMC not done
86 | 24 |  | 62/1 | DA+3 RC | SANDY | 15.02.24 | 17.02.24 | 21.02.24 | Shakti Construction | Sanjay Thakur | Rakesh Pathak | Complete |  |  | JMC not done
87 | 25 |  | 53/5 | DA+3 | SANDY | 18.02.24 | 21.02.24 | 22.02.24 | Imran |  | RT Singh | Complete
88 | 26 |  | 64/11 | DA+3 | DRY | 17.02.24 | 23.02.24 | 24.02.24 | Bhati Const. | Sanjay Thakur | Rakesh Pathak | Complete
89 | 27 |  | 60/2 | DA+3 RC | DFR | 16.02.24 | 20.02.24 | 24.02.24 | OM Const | RT Singh | RT Singh | Complete |  |  |  | 31
90 | 28 |  | 60/3 | DA+3 | DFR | 20.02.24 | 25.02.24 | 28.02.24 | Manoj Sharma | RT Singh | RT Singh | Complete
91 | 29 |  | 65/0 | DB1+0 | DRY | 19.02.24 | 28.02.24 | 29.02.24 | Bhati Const. | Sanjay Thakur | Rakesh Pathak | Complete
92 | 30 |  | 60/4 | DA+3 | DFR | 18.02.24 | 27.02.24 | 29.02.24 | Manoj Sharma | RT Singh | RT Singh | Complete
March'24
93 | 1 | 1 | 61/10 | DA+9 | DRY | 29.02.24 | 03.02.24 | 04.03.24 | Manoj Sharma |  | RT Singh | Complete
94 | 2 | 2 | 65/1 | DA+0 | DRY | 29.02.24 | 03.03.24 | 05.03.24 | Bhati Const. | Sanjay Thakur | Rakesh Pathak | Complete
95 | 3 | 3 | 62/0 | DB2+0 | DRY | 29.02.24 | 06.03.24 | 10.03.24 | Manoj Sharma | RT Singh | RT Singh | Complete
96 | 4 |  | 61/4 | DA+3 | DRY | 29.02.24 | 13.03.24 | 14.03.24 | Manoj Sharma |  | RT Singh | Complete
97 | 5 |  | 49/3 | DA+3 | SANDY | 11.03.24 | 13.03.24 | 15.03.24 | Veerteja Enterprises |  | RT Singh | Complete
98 | 6 |  | 49/6 | DA+0 | SANDY | 13.03.24 | 14.03.24 | 17.03.24 | Shakti Construction |  | RT Singh | Complete
99 | 7 |  | 60/0 | DC1+0 | DRY | 28.02.24 | 15.03.24 | 19.03.24 | Manoj Sharma | RT Singh | RT Singh | Complete |  |  |  |  | 22
100 | 8 |  | 49/4 | DA+3 | SANDY | 14.03.24 | 15.03.24 | 19.03.24 | Veerteja Enterprises | Ganesh | RT Singh | Complete
101 | 9 |  | 49/5 | DA+3 | SANDY | 15.03.24 | 18.03.24 | 20.03.24 | Shakti Construction |  | RT Singh | Complete
102 | 10 |  | 47/10 | DA+6 | SANDY | 16.03.24 | 18.03.24 | 20.03.24 | Bhati Const. |  | RT Singh | Complete
103 | 11 |  | 47/9 | DA+3 | SANDY | 19.03.24 | 21.03.24 | 23.03.24 | Bhati Const. |  | RT Singh | Complete
104 | 12 |  | 47/8 | DA+0 RC | SANDY | 22.03.24 | 26.03.24 | 29.03.24 | Bhati Const. |  |  | Complete
105 | 13 |  | 47/7 | DA+3 | SANDY | 27.03.24 | 30.03.24 | 31.03.24 | Bhati Const. |  |  | Complete
Apr'24
106 | 1 |  | 50/9 | DA+0 RC | SANDY | 21.03.24 | 22.03.24 | 01.04.24 | Shakti Construction |  | RT Singh | Complete
107 | 2 |  | 48/0 | DC2+0 | SANDY | 31.03.24 | 03.04.24 | 07.04.24 | Bhati Const. |  | RT Singh | Complete
108 | 3 |  | 50/10 | DA+0 RC | SANDY | 29.03.24 | 03.04.24 | 08.04.24 | Shakti Construction |  | RT Singh | Complete
109 | 4 |  | 51/1 | DA+0 RC | SANDY | 07.04.24 | 08.04.24 | 13.04.24 | Shakti Construction |  |  | Complete
110 | 5 |  | 48/1 | DA+9 | SANDY | 04.04.24 | 08.04.24 | 15.04.24 | Veerteja Enterprises | Ganesh | R TSingh | Complete
111 | 6 |  | 50/8 | DA+9 | SANDY | 14.04.24 | 14.04.24 | 19.04.24 | Shakti Construction | Rajiv | R TSingh | Complete
112 | 7 |  | 49/1 | DA+0 | SANDY | 16.04.24 | 17.04.214 | 20.04.24 | Veerteja Enterprises | Ganesh | R TSingh | Complete
May'24
113 | 1 |  | 49/0 | DD45+0 | SANDY | 21.04.24 | 22.04.24 | 03.05.24 | Veerteja Enterprises | Ganesh | R TSingh | Complete
114 | 2 |  | 50/7 | DA+0 RC | SANDY | 04.05.24 | 05.05.24 | 10.05.24 | Veerteja Enterprises | Ganesh | R TSingh | Complete
115 | 3 |  | 50/1 | DA+6 RC | SANDY | 12.05.24 | 14.05.24 | 18.05.24 | Veerteja Enterprises | Ganesh | R TSingh | Complete
116 | 4 |  | 47/6 | DA+3 | SANDY | 14.05.24 | 15.05.24 | 18.05.24 | Bhati Const. | Jitender | R TSingh | Complete
117 | 5 |  | 52/3 | DA+9 RC | SANDY | 12.05.24 | 14.05.24 | 25.05.24 | SB MEHAR CONST. | Rajiv | R TSingh | Complete
118 | 6 |  | 47/2 | DA+9 | SANDY | 19.05.24 | 23.05.24 | 26.05.24 | Bhati Const. | Ganesh | R TSingh | Complete
119 | 7 |  | 50/4 | DA+9 RC | SANDY | 19.05.24 | 20.05.24 | 28.05.24 | Veerteja Enterprises | Nayak | R TSingh | Complete
120 | 8 |  | 51/2 | DA+0 | SANDY | 24.05.24 | 25.05.24 | 31.05.24 | SB MEHAR CONST. | Rajiv | R TSingh | Complete
121 | 9 |  | 47/5 | DA+0 RC | SANDY | 26.05.24 | 29.05.24 | 31.05.24 | Bhati Const. | Ganesh | R TSingh | Complete
122 | 10 |  | 50/2 | DA+9 RC | SANDY | 24.05.24 | 26.05.24 | 31.05.24 | Veerteja Enterprises | Nayak | R TSingh | Complete | [7 empty] | 1 pit RC chimney WIP & 1 pit pyramid done & 1 pit frustum done
June'24
123 | 1 |  | 47/3 | DA+9 RC | SANDY | 02.06.24 | 03.06.24 | 08.06.24 | Bhati Const. |  | R TSingh | Complete
124 | 2 |  | 51/0 | DC2+0 | SANDY | 02.06.24 | 03.06.24 | 10.06.24 | SB MEHAR CONST. |  | R TSingh | Complete
125 | 3 |  | 53/7 | DA+3 | SANDY | 10.06.24 | 12.06.24 | 15.06.24 | Bhati Const. |  | R TSingh | Complete
| July'24 | [16 empty] | 153
126 | 1 |  | 50/0 | DB2+0 RC | SANDY | 06.07.24 | 10.07.24 | 22.07.24 | Veerteja Enterprises |  | R TSingh | Complete |  |  |  |  | 4
127 | 2 |  | 58/0 | DC1+3 | DFR | 09.07.24 | 23.07.24 | 29.07.24 | Bhati Const. |  | R TSingh | Complete |  |  |  |  | 11
Aug'24
128 | 1 |  | 57/7 | DA+3 | DFR | 18.07.24 | 07.08.24 | 10.08.24 | Bhati Const. |  | R TSingh | Complete
129 | 2 |  | 59/2 | DA+3 | DFR | 10.08.24 | 19.08.24 | 23.08.24 | Bhati Const. |  | R TSingh | Complete
130 | 3 |  | 50/6 | DA+9 RC | Sandy | 08.08.24 | 14.08.24 | 28.08.24 | Kalpana Const. |  | R TSingh | Complete
131 | 4 |  | 53/8 | DA+3 | Sandy | 21.08.24 | 26.08.24 | 29.08.24 | Bhati Const. |  | R TSingh | Complete
Sept'24
132 | 1 |  | 53/6 | DA+6 RC | Sandy | 26.08.24 | 30.08.24 | 05.09.24 | Bhati Const. |  | R TSingh | Complete
133 | 2 |  | 54/1 | DA+3 RC | Sandy | 02.09.24 | 05.09.24 | 09.09.24 | Bhati Const. | Ganesh | R TSingh | Complete
134 | 3 |  | 50/3 | DA+6 | Sandy | 29.08.24 | 01.09.24 | 10.09.24 | Kalpana Const. |  | R TSingh | Complete |  |  |  | JMC Balance | Classification approved
135 | 4 |  | 73/0 | DB2+0 | DRY | 02.09.24 | 09.09.24 | 10.09.24 | Shree Shyam Const. |  |  | Complete
136 | 5 |  | 73/9 | DA+0 | DRY | 02.09.24 | 08.09.24 | 11.09.24 | Shakti Construction |  |  | Complete
137 | 6 |  | 73/2 | DA+0 | DRY | 09.09.24 | 12.09.24 | 13.09.24 | Shree Shyam Const. |  |  | Complete
138 | 7 |  | 54/2 | DA+3 | Sandy | 09.09.24 | 11.09.24 | 14.09.24 | Bhati Const. | Ganesh | R TSingh | Complete
139 | 8 |  | 73/1 | DA+0 | DRY | 10.09.24 | 15.09.24 | 16.09.24 | Shree Shyam Const. |  | SK Sil | Complete
140 | 9 |  | 73/6 | DA+0 | DRY | 28.08.24 | 18.09.24 | 19.09.24 | Shree Shyam Const. |  | SK Sil | Complete
141 | 10 |  | 69/1 | DA+3 | DRY | 15.09.24 | 19.09.24 | 20.09.24 | Bhati Const. |  | SK Sil | Complete |  |  |  | JMC Balance | Classification approved conc. Form submitted
142 | 11 |  | 73/5 | DA+0 | DRY | 19.09.24 | 22.09.24 | 23.09.24 | Shree Shyam Const. |  |  | Complete
143 | 12 |  | 73/8 | DA+3 | DRY | 20.09.24 | 23.09.24 | 25.09.24 | Shakti Construction |  |  | Complete
144 | 13 |  | 59/1 | DA+3 RC | DRY | 18.09.24 | 20.09.24 | 25.09.24 | Bhati Const. |  | R TSingh | Complete |  |  |  | JMC Balance | Classification submitted
145 | 14 |  | 72/2 | DA+0 | DRY | 21.09.24 | 25.09.24 | 26.9.24 | Shree Shyam Const. |  |  | Complete
146 | 15 |  | 66/0 | DC2+6 | DRY | 19.09.24 | 23.09.24 | 27.09.24 | Bhati Const. |  | SK Sil | Complete |  |  |  | JMC Balance | Classification approved conc. Form submitted
147 | 16 |  | 59/11 | DA+6 | DFR | 02.09.24 | 25.09.24 | 27.09.24 | Mahadev Eng |  | R TSingh | Complete |  |  |  | JMC Balance | Today received
148 | 17 |  | 73/3 | DA+0 | DRY | 23.09.24 | 25.09.24 | 30.09.24 | Awadh Const. |  |  | Complete
Oct'24
149 | 1 |  | 73/7 | DA+0 | DRY | 25.09.24 | 29.09.24 | 01.10.24 | Shakti Construction |  |  | Complete
150 | 2 |  | 59/0 | DC2+0 | DRY | 21.09.24 | 29.09.24 | 04.10.24 | Bhati Const. |  | R TSingh | Complete
151 | 3 |  | 67/0 | DC1+9 | DRY | 26.9.24 | 04.10.24 | 05.10.24 | Bhati Const. |  |  | Complete
152 | 4 |  | 69/0 | DB2+0 | DFR | 10.09.24 | 28.09.24 | 09.10.24 | Bhati Const. |  | SK Sil | Complete
153 | 5 |  | 73/4 | DA+0 | DRY | 07.10.24 | 08.10.24 | 09.10.24 | Shree Shyam Const. |  | SK Sil | Complete
154 | 6 |  | 74/0 | DB2+0 | SANDY | 03.10.24 | 07.10.24 | 10.10.24 | Shakti Construction |  | SK Sil | Complete
155 | 7 |  | 72/3 | DA+3 | DRY | 12.10.24 | 14.10.24 | 15.10.24 | Shree Shyam Const. |  | SK Sil | Complete
156 | 8 |  | 71/7 | DA+3 | DRY | 15.10.24 | 17.10.24 | 18.10.24 | Shree Shyam Const. |  | SK Sil | Complete |  |  |  | 0.92
157 | 9 |  | 59/4 | DA+3 | DFR | 11.10.24 | 14.10.24 | 19.10.24 | Bhati Const. |  | R TSingh | Complete
158 | 10 |  | 71/6 | DA+0 | DRY | 18.10.24 | 20.10.24 | 21.10.24 | Shree Shyam Const. |  | SK Sil | Complete
159 | 11 |  | 49/7 | DA+0 RC | Sandy | 11.09.24 | 12.09.24 | 21.10.24 | Kalpana Const. |  | R TSingh | Complete
Nov'24
160 | 1 |  | 54/0 | DB1+6 | Sandy | 10.11.24 |  | 21.11.24 | Bhati Const. |  | R TSingh | Complete
161 | 2 |  | 65/8 | DA+0 | DRY | 12.11.24 | 27.11.24 | 28.11.24 | Bhati Const. |  | SK Sil | Complete
162 | 3 |  | 65/7 | DA+0 | DRY | 12.11.24 | 29.11.24 | 30.11.24 | Bhati Const. |  | SK Sil | Complete
2024-12-24
163 | 1 |  | 70/8 | DA+3 | DRY | 09.12.24 | 16.12.24 | 17.12.24 | Tantray Construction |  | SK Sil | Complete
164 | 2 |  | 72/1 | DA+3 | DRY | 09.12.23 | 16.12.24 | 18.12.24 | Meer const |  | SK Sil | Complete
165 | 3 |  | 70/7 | DA+3 | DRY | 10.12.24 | 17.12.24 | 19.12.24 | Tantray Construction |  | SK Sil | Complete
166 | 4 |  | 71/8 | DA+3 | DRY | 08.12.24 | 19.12.24 | 20.12.24 | Meer const |  | SK Sil | Complete
167 | 5 |  | 52/1 | DA+6 RC | Sandy | 17.12.24 | 17.12.24 | 20.12.24 | Tantray Construction |  |  | Complete |  |  |  | Ganesh Ji
168 | 6 |  | 70/9 | DA+3 | DRY | 14.12.24 | 20.12.24 | 21.12.24 | Tantray Construction |  | SK Sil | Complete
169 | 7 |  | 72/0 | DB2+3 | DRY | 09.12.24 | 22.12.24 | 23.12.24 | Meer const |  | SK Sil | Complete |  |  |  | 12
170 | 8 |  | 70/6 | DA+3 | DRY | 13.12.24 | 22.12.24 | 23.12.24 | Tantray Construction |  | SK Sil | Complete
171 | 9 |  | 71/4 | DA+3 | DRY | 15.12.24 | 24.12.24 | 25.12.24 | Meer const |  | SK Sil | Complete
172 | 10 |  | 52/2 | DA+6 RC | Sandy | 21.12.24 | 24.12.24 | 25.12.24 | Tantray Construction |  | R TSingh | Complete
173 | 11 |  | 70/10 | DA+3 | DRY | 23.12.24 | 24.12.24 | 25.12.24 | Tantray Construction |  | SK Sil | Complete
174 | 12 |  | 71/5 | DA+3 | DRY | 24.12.24 | 26.12.24 | 27.12.24 | Meer const |  | SK Sil | Complete |  |  |  | 8
175 | 13 |  | 70/11 | DA+3 | DRY | 26.12.24 | 26.12.24 | 27.12.24 | Tantray Construction |  | SK Sil | Complete |  |  |  | 11
176 | 14 |  | 53/2 | DA+0 RC | Sandy | 25.12.24 | 25.12.24 | 29.12.24 | Meer const |  | R TSingh | Complete |  |  |  | 1
177 | 15 |  | 71/3 | DA+6 | DRY | 26.12.24 | 29.12.24 | 30.12.24 | Meer const |  | SK Sil | Complete |  |  |  | 9
178 | 16 |  | 52/4 | DA+9 RC | Sandy | 25.12.24 | 27.12.24 | 30.12.24 | Tantray Construction |  | R TSingh | Complete |  |  |  | 2
179 | 17 |  | 71/0 | DB2+3 | DRY | 23.12.24 | 29.12.24 | 31.12.24 | Tantray Construction |  | SK Sil | Complete |  |  |  | 10
Jan'25
180 | 1 | -178 | 71/2 | DA+3 | DRY | 29.12.24 | 31.12.24 | 04.01.25 | Meer const |  | SK Sil | Complete
181 | 2 | -177 | 71/1 | DA+3 | DRY | 03.01.25 | 04.01.25 | 06.01.25 | Meer const |  | SK Sil | Complete
182 | 3 |  | 54/3 | DA+6 RC | Sandy | 30.12.24 | 02.01.25 | 06.01.25 | Tantray Construction |  | R TSingh | Complete
183 | 4 |  | 44/1 | DA+0 RC | Sandy | 02.01.25 | 02.01.25 | 06.01.25 | Tantray Construction |  | R TSingh | Complete
184 | 5 |  | 44/2 | DA+0 | Sandy | 03.01.25 | 04.01.25 | 07.01.25 | Tantray Construction |  | R TSingh | Complete
185 | 6 |  | 53/1 | DA+9 RC | Sandy | 27.12.24 | 29.12.24 | 08.01.25 | Meer const |  | R TSingh | Complete
186 | 7 |  | 70/3 | DA+3 | DRY | 04.01.25 | 07.01.25 | 09.01.25 | Meer const |  | SK Sil | Complete | [5 empty] | 2000
187 | 8 |  | 54/4 | DA+9 RC | Sandy | 04.01.25 | 06.01.25 | 09.01.25 | Tantray Construction |  | R TSingh | Complete |  |  |  |  | 2520 | 480
188 | 9 |  | 45/0 | DC2+0 RC | Sandy | 02.01.25 | 06.01.25 | 09.01.25 | Nadeem |  | R TSingh | Complete
189 | 10 |  | 44/11 | DA+0 RC | Sandy | 07.01.25 | 07.01.25 | 09.01.25 | Nadeem |  | R TSingh | Complete
190 | 11 |  | 53/0 | DB2+9 RC | Sandy | 02.01.25 | 06.01.25 | 12.01.25 | Meer const |  | R TSingh | Complete | [5 empty] | 3000
191 | 12 |  | 44/10 | DB1+9 RC | Sandy | 09.01.25 | 11.01.25 | 12.01.25 | Nadeem |  | R TSingh | Complete
192 | 13 |  | 44/4 | DA+9 RC | Sandy | 08.01.25 | 08.01.25 | 12.01.25 | Tantray Construction |  | R TSingh | Complete
193 | 14 |  | 70/4 | DA+3 | DRY | 03.01.25 | 12.01.25 | 13.01.25 | Meer const |  | SK Sil | Complete |  |  |  |  | 1680 | 320
194 | 15 |  | 70/5 | DA+3 | DRY | 07.01.25 | 13.01.25 | 15.01.25 | Meer const |  | SK Sil | Complete
195 | 16 |  | 53/3 | DA+6 RC | Sandy | 10.01.24 | 11.01.25 | 15.01.25 | Meer const |  | R TSingh | Complete
196 | 17 |  | 68/0 | DD45+0 | DRY | 06.01.25 | 13.01.25 | 17.01.25 | Bhati Const. |  | SK Sil | Complete |  |  |  | 70/2
197 | 18 |  | 53/4 | DA+0 RC | Sandy | 13.01.25 | 14.01.25 | 18.01.25 | Meer const |  | R TSingh | Complete
198 | 19 |  | 52/0 | DC2+0 RC | Sandy | 10.01.24 | 11.01.25 | 18.01.25 | Tantray Construction |  | R TSingh | Complete
199 | 20 |  | 44/5 | DA+9 RC | Sandy | 12.01.25 | 13.01.25 | 19.01.25 | Tantray Construction |  | R TSingh | Complete
200 | 21 |  | 44/9 | DA+9 RC | Sandy | 13.01.25 | 15.01.25 | 20.01.25 | Iqbal |  | R TSingh | Complete
201 | 22 |  | 70/1 | DA+3 | DRY | 15.01.25 | 17.01.25 | 21.01.25 | Meer const |  | SK Sil | Complete
202 | 23 |  | 70/2 | DA+3 | DRY | 18.01.25 | 20.01.25 | 21.01.25 | Bhati Const. |  | SK Sil | Complete
203 | 24 |  | 44/6 | DB1+3 RC | SANDY | 18.01.25 | 19.01.25 | 21.01.25 | Tantray Construction |  | RT Singh | Complete
204 | 25 |  | 55/2 | DA+0 | WFR | 18.01.25 | 18.01.25 | 22.01.25 | Meer const |  | R TSingh | Complete
205 | 26 |  | 47/4 | DA+3 | Sandy | 18.01.25 | 19.01.25 | 23.01.25 | Tantray Construction |  | R TSingh | Complete
206 | 27 |  | 50/5 | DA+9 RC | Sandy | 13.01.25 | 16.01.25 | 23.01.25 | OM Const |  | R TSingh | Complete
207 | 28 |  | 70/0 | DC1+0 | DRY | 18.01.25 | 20.01.25 | 25.01.25 | Meer const |  | SK Sil | Complete
208 | 29 |  | 44/7 | DA+9 | SANDY | 19.01.25 | 23.01.25 | 25.01.25 | Iqbal |  | R TSingh | Complete
209 | 30 |  | 65/10 | DA+0 | DRY | 22.01.25 | 24.01.25 | 27.01.25 | Bhati Const. |  | SK Sil | Complete
210 | 31 |  | 57/1 | DA+0 | SANDY | 23.01.25 | 24.01.25 | 27.01.25 | Meer const |  | R TSingh | Complete
211 | 32 |  | 44/3 | DA+0 RC | SANDY | 23.01.25 | 24.01.25 | 28.01.25 | Tantray Construction |  | R TSingh | Complete
212 | 33 |  | 55/8 | DA+6 | SANDY | 25.01.25 | 28.01.25 | 30.01.25 | Meer const |  | R TSingh | Complete
213 | 34 |  | 44/8 | DCT1+0 | SANDY | 23.01.25 | 27.01.25 | 31.01.25 | Iqbal |  | R TSingh | Complete
Feb'25
214 | 1 |  | 47/1 | DA+3 RC | SANDY | 24.01.25 | 25.01.25 | 01.02.25 | Tantray Construction |  | R TSingh | Complete
215 | 2 |  | 45/1 | DA+9 RC | SANDY | 01.02.25 | 01.02.25 | 09.02.25 | Tantray Construction |  | R TSingh | Complete
216 | 3 |  | 54/5 | DA+9 RC | SANDY | 03.02.25 | 06.02.25 | 10.02.25 | Meer const |  | R TSingh | Complete
217 | 4 |  | 55/0 | DB1+6 RC | SANDY | 08.02.25 | 11.02.25 | 16.02.25 | Meer const |  | R TSingh | Complete
218 | 5 |  | 44/0 | DB1+3 RC | SANDY | 08.02.25 | 10.02.25 | 16.02.25 | OM Const |  | R TSingh | Complete
219 | 6 |  | 55/1 | DA+0 | WFR | 19.02.25 | 21.02.25 | 28.02.25 | Bhati |  | R TSingh | Complete | [6 empty] | ROW since 19.01.25
220 | 7 |  | 43/10 | DA+3 RC | SANDY | 15.02.25 | 18.02.25 | 23.02.24 | OM Const |  | R TSingh | Complete
Mar'25
220 | 1 |  | 57/0 | DD60+25 | SANDY | 18.03.25 | 22.03.25 | 31.03.25 | Bhati |  | R TSingh | Complete
April'25
221 | 1 |  | 46/0 | DD60+25 RC | SANDY | 25.03.25 |  | 09.04.25 | Om Const |  | R TSingh | Complete
222 | 2 |  | 56/0 | DD60+25 RC | SANDY | 30.03.25 |  |  | Bhati |  | R TSingh | 1 pit done& 1 pit RC chimney wip & 1 pit P&C done & 1 pit rod binding wip
223 | 3 |  | 47/0 | DD60+25 RC | SANDY | 04.04.25 | 07.04.25 |  | Om Const |  | R TSingh | 1 pit RC chimney wip & 1 pit Rod binding done & 1 pit stub setting done

## Earthing (PKG-F) (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Earthing
Sl. No. | Cum S No | Location No. | Tower Type | Classification | Type of Earthing | Earthing | Name of Sub-Contractor | Check list
2023-12-01
1 | 1 | 61/3 | DA+6 | DRY | Pipe Type | 18.12.23 | Manoj Sharma
2 | 2 | 62/4 | DA+3 | DRY | Pipe Type | 31.12.23 | Shakti Const.
2024-01-01
3 | 1 | 59/7 | DA+3 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
4 | 2 | 59/8 | DB+3 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
5 | 3 | 59/9 | DA+3 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
6 | 4 | 59/10 | DA+0 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
7 | 5 | 59/13 | DA+3 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
8 | 6 | 59/14 | DA+6 | DRY | Pipe Type | 03.01.24 | Manoj Sharma
9 | 7 | 59/5 | DA+3 | DFR | Counter Poise | 05.01.24 | om Const.
10 | 8 | 59/6 | DA+3 | DFR | Counter Poise | 05.01.24 | om Const.
11 | 9 | 60/7 | DA+3 | DRY | Pipe Type | 06.01.24 | Imran
12 | 10 | 60/8 | DA+0 | DRY | Pipe Type | 06.01.24 | Imran
13 | 11 | 60/9 | DA+3 | DRY | Pipe Type | 06.01.24 | Imran
14 | 12 | 62/2 | DA+3(RC) | DRY | Pipe Type | 07.01.24 | Shakti Const.
15 | 13 | 62/5 | DA+0 | DRY | Pipe Type | 07.01.24 | Shakti Const.
16 | 14 | 62/6 | DA+3 | DRY | Pipe Type | 07.01.24 | Shakti Const.
17 | 15 | 62/3 | DA+0 | DRY | Pipe Type | 07.01.24 | Shakti Const.
18 | 16 | 62/7 | DA+3 | DRY | Pipe Type | 09.01.24 | Shakti Const.
19 | 17 | 63/6 | DA+3 | DRY | Pipe Type | 12.01.24 | Mahadev Eng
20 | 18 | 65/2 | DA+0 | DRY | Pipe Type | 12.01.24 | Veerteja
21 | 19 | 65/11 | DA+0 | DRY | Pipe Type | 15.1.24 | Bhati Const.
22 | 20 | 65/9 | DA+0 | DRY | Pipe Type | 15.1.24 | Bhati Const.
23 | 21 | 60/5 | DA+3 | DRY | Pipe Type | 16.01.2024 | Manoj Sharma
24 | 22 | 60/6 | DA+0 | DRY | Pipe Type | 16.01.2024 | Manoj Sharma
25 | 23 | 59/12 | DA+6 | DFR | Counter Poise | 16.01.2024 | Manoj Sharma
26 | 24 | 55/4 | DA+0(RC) | SANDY | Pipe Type | 17.01.2024 | Imran
27 | 25 | 64/4 | DA+3 | DRY | Pipe Type | 19.01.24 | Mahadev Eng
28 | 26 | 65/3 | DA+3 | DRY | Pipe Type | 20.01.24 | Veerteja
29 | 27 | 63/1 | DA+3 | DFR | Counter Poise | 27.01.24 | Shakti Const.
30 | 28 | 63/2 | DA+0 | DFR | Counter Poise | 27.01.24 | Shakti Const.
31 | 29 | 64/2 | DA+3 | DRY | Pipe Type | 25.01.24 | Mahadev Eng
32 | 30 | 64/5 | DA+3 | DRY | Pipe Type | 25.01.24 | Mahadev Eng
33 | 31 | 65/4 | DA+0 | DRY | Pipe Type | 25.01.24 | Bhati Const.
34 | 32 | 62/11 | DA+3 | DRY | Pipe Type | 28.01.24 | Shakti Const.
35 | 33 | 55/5 | DA+0 RC | SANDY | Pipe Type | 29.01.24 | Imran
36 | 34 | 55/6 | DA+0 RC | SANDY | Pipe Type | 29.01.24 | Imran
Feb-24
37 | 1 | 64/8 | DA+3 | DRY | Pipe Type | 01.02.24 | Veerteja
38 | 2 | 60/10 | DA+0 | DFR | Counter Poise | 02.02.24 | Manoj Sharma
39 | 3 | 60/11 | DA+3 | DRY | Pipe Type | 02.02.24 | Manoj Sharma
40 | 4 | 61/0 | DB2+0 | DRY | Pipe Type | 02.02.24 | Manoj Sharma
41 | 5 | 61/1 | DA+6 | DFR | Counter Poise | 02.02.24 | Manoj Sharma
42 | 6 | 61/2 | DA+6 | DFR | Counter Poise | 02.02.24 | Manoj Sharma
43 | 7 | 55/3 | DA+0 | SANDY | Pipe Type | 02.02.24 | Imran
44 | 8 | 55/7 | DA+0 | SANDY | Pipe Type | 02.02.24 | Imran
45 | 9 | 52/5 | DA+9 RC | SANDY | Pipe Type | 05.02.24 | Imran
46 | 10 | 52/6 | DA+6 | SANDY | Pipe Type | 08.02.24 | Imran
47 | 11 | 65/6 | DA+0 | DRY | Pipe Type | 09.02.24 | Bhati Const.
48 | 12 | 65/5 | DA+0 | DRY | Pipe Type | 09.02.24 | Bhati Const.
49 | 13 | 67/2 | DA+0 | DRY | Pipe Type | 09.02.24 | Bhati Const.
50 | 14 | 64/10 | DA+3 | DRY | Pipe Type | 11.02.24 | Veerteja Enterprises
51 | 15 | 52/7 | DA+3 RC | SANDY | Pipe Type | 13.02.24 | Imran
52 | 16 | 64/7 | DA+3 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
53 | 17 | 64/6 | DA+0 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
54 | 18 | 64/3 | DA+0 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
55 | 19 | 64/1 | DA+0 | DRY | Counter Poise | 14.02.24 | Mahadev Eng
56 | 20 | 64/0 | DB2+0 | DRY | Counter Poise | 14.02.24 | Mahadev Eng
57 | 21 | 63/8 | DA+3 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
58 | 22 | 63/7 | DA+3 | DRY | Pipe Type | 14.02.24 | Mahadev Eng
59 | 23 | 63/4 | DA+0 | DRY | Pipe Type | 14.02.24 | Shakti Const.
60 | 24 | 57/2 | DA+3 | DRY | Pipe Type | 14.02.24 | om Const.
61 | 25 | 57/4 | DA+0 | SANDY | Pipe Type | 14.02.24 | om Const.
62 | 26 | 57/5 | DA+3 RC | SANDY | Pipe Type | 14.02.24 | om Const.
63 | 27 | 63/0 | DC1+0 | DFR | Counter Poise | 15.02.24 | Shakti Const.
64 | 28 | 63/5 | DA+3 | DFR | Counter Poise | 15.02.24 | Shakti Const.
65 | 29 | 52/10 | DA+9 RC | SANDY | Pipe Type | 17.02.24 | Imran
66 | 30 | 64/9 | DA+3 | DRY | Pipe Type | 20.02.24 | Veerteja Enterprises
67 | 31 | 57/3 | DA+0 | DRY | Pipe Type | 22.02.24 | om Const.
68 | 32 | 57/6 | DA+3 RC | SANDY | Pipe Type | 22.02.24 | om Const.
69 | 33 | 59/3 | DA+3(RC) | DFR | Counter Poise | 22.02.24 | om Const.
70 | 34 | 61/9 | DA+0 | Dry | Pipe Type | 22.02.24 | Manoj Sharma
71 | 35 | 61/8 | DA+6 RC | DRY | Pipe Type | 22.02.24 | Manoj Sharma
72 | 36 | 61/7 | DA+9 RC | Dry | Pipe Type | 22.02.24 | Manoj Sharma
73 | 37 | 61/6 | DA+3 | DRY | Pipe Type | 22.02.24 | Manoj Sharma
74 | 38 | 61/5 | DA+3 | DRY | Pipe Type | 22.02.24 | Manoj Sharma
75 | 39 | 62/10 | DA+0 | DFR | Counter Poise | 22.02.24 | Shakti Const.
76 | 40 | 62/1 | DA+3 RC | SANDY | Pipe Type | 22.02.24 | Shakti Const.
77 | 41 | 62/9 | DA+3 | DFR | Counter Poise | 21.02.24 | Shakti Const.
78 | 42 | 62/8 | DA+0 | DFR | Counter Poise | 21.02.24 | Shakti Const.
79 | 43 | 52/9 | DA+3 | SANDY | Pipe Type | 22.02.24 | Imran
80 | 44 | 52/8 | DA+6 | SANDY | Pipe Type | 22.02.24 | Imran |  | 210
81 | 45 | 63/3 | DA+3 | DFR | Pipe Type | 22.02.24 | Shakti Const.
82 | 46 | 67/1 | DA+0 | DRY | Pipe Type | 13.02.24 | Bhati Const.
83 | 47 | 60/1 | DA+6 | DRY | Pipe Type | 23.02.24 | om Const.
84 | 48 | 53/5 | DA+3 | SANDY | Pipe Type | 25.02.24 | Imran
85 | 49 | 60/2 | DA+3 | DFR | Counter Poise | 26.02.24 | om Const.
March'24
86 | 1 | 60/3 | DA+3 | DFR | Counter Poise | 01.03.24 | Manoj Sharma
87 | 2 | 60/4 | DA+3 | DFR | Counter Poise | 01.03.24 | Manoj Sharma
88 | 3 | 64/11 | DA+3 | DRY | Pipe Type | 06.03.24 | Bhati Const.
89 | 4 | 65/0 | DB1+0 | DRY | Pipe Type | 06.03.24 | Bhati Const.
90 | 5 | 65/1 | DA+0 | DRY | Pipe Type | 07.03.24 | Bhati Const.
91 | 6 | 59/16 | DA+9 | Dry | Pipe Type | 26.02.24 | om Const.
92 | 7 | 59/15 | DA+6 | DRY | Pipe Type | 26.02.24 | om Const.
93 | 8 | 49/2 | DA+3 | SANDY | Pipe Type | 08.03.24 | Veerteja Enterprises
94 | 9 | 61/10 | DA+9 | DRY | Pipe Type | 12.03.24 | Manoj Sharma
95 | 10 | 62/0 | DB2+0 | DRY | Pipe Type | 12.03.24 | Manoj Sharma
96 | 11 | 60/0 | DC1+0 | DRY | Pipe Type | 19.03.24 | Manoj Sharma
97 | 12 | 49/3 | DA+3 | SANDY | Pipe Type | 21.03.24 | Veerteja Enterprises
98 | 13 | 49/5 | DA+3 | SANDY | Pipe Type | 21.03.24 | Shakti Const.
99 | 14 | 61/4 | DA+3 | DRY | Pipe Type | 22.03.24 | Manoj Sharma
100 | 15 | 47/10 | DA+6 | SANDY | Pipe Type | 29.03.24 | Bhati Const.
101 | 16 | 47/9 | DA+3 | SANDY | Pipe Type | 29.03.24 | Bhati Const.
102 | 17 | 47/8 | DA+0 RC | SANDY | Pipe Type | 29.03.24 | Bhati Const.
April'24
103 | 1 | 47/7 | DA+3 | SANDY | Pipe Type | 02.04.24 | Bhati Const.
104 | 2 | 48/0 | DC2+0 | SANDY | Pipe Type | 07.04.24 | Bhati Const.
105 | 3 | 48/1 | DA+9 | SANDY | Pipe Type | 16.04.24 | Veerteja Enterprises
106 | 4 | 50/9 | DA+0 RC | SANDY | Pipe Type | 19.04.24 | Shakti Const.
107 | 5 | 50/10 | DA+0 RC | SANDY | Pipe Type | 19.04.24 | Shakti Const.
108 | 6 | 51/1 | DA+0 RC | SANDY | Pipe Type | 19.04.24 | Shakti Const.
109 | 7 | 50/8 | DA+9 | SANDY | Pipe Type | 20.04.24 | Shakti Const.
110 | 8 | 49/6 | DA+0 | SANDY | Pipe Type | 20.04.24 | Shakti Const.
111 | 9 | 49/4 | DA+3 | SANDY | Pipe Type | 22.04.24 | Veerteja
112 | 10 | 49/1 | DA+0 | SANDY | Pipe Type | 22.04.24 | Veerteja
May'24
113 | 1 | 49/0 | DD45+0 | SANDY | Pipe Type | 03.05.24 | Veerteja Enterprises
114 | 2 | 52/3 | DA+9 | SANDY | Pipe Type | 23.05.24 | SB MEHAR CONST.
115 | 3 | 47/2 | DA+9 | SANDY | Pipe Type | 28.05.24 | Bhati Const.
116 | 4 | 50/7 | DA+0 RC | SANDY | Pipe Type | 31.05.24 | Veerteja Enterprises
117 | 5 | 50/1 | DA+6 | SANDY | Pipe Type | 31.05.24 | Veerteja Enterprises
118 | 6 | 51/2 | DA+0 | SANDY | Pipe Type | 31.05.24 | SB MEHAR CONST. |  | 41.96 | 41.82
June'24
119 | 1 | 50/4 | DA+9 RC | SANDY | Pipe Type | 03.02.24 | Veerteja Enterprises
120 | 2 | 50/2 | DA+9 RC | SANDY | Pipe Type | 04.02.24 | Veerteja Enterprises
121 | 3 | 47/3 | DA+9 RC | SANDY | Pipe Type | 08.06.24 | Bhati Const.
122 | 4 | 47/5 | DA+0 RC | SANDY | Pipe Type | 08.06.24 | Bhati Const.
123 | 5 | 47/6 | DA+3 | SANDY | Pipe Type | 08.06.24 | Bhati Const.
124 | 6 | 51/0 | DC2+0 | SANDY | Pipe Type | 11.06.24 | SB MEHAR CONST.
July'24
125 | 1 | 53/7 | DA+3 | SANDY | Pipe Type | 02.07.24 | Bhati Const.
126 | 2 | 58/0 | DC1+3 | DFR | Counter Poise | 30.07.24 | Bhati Const.
Aug'24
127 | 1 | 50/0 | DB2+0 RC | SANDY | Pipe Type | 03.08.24 | Veerteja Enterprises
128 | 2 | 57/7 | DA+3 | DFR | Counter Poise | 12.08.24 | Bhati Const.
129 | 3 | 59/2 | DA+3 | DFR | Counter Poise | 23.08.24 | Bhati Const.
Sept'24
130 | 1 | 53/8 | DA+3 | Sandy | Pipe Type | 03.09.24 | Bhati Const.
131 | 2 | 53/6 | DA+6 RC | Sandy | Pipe Type | 13.09.24 | Bhati Const.
132 | 3 | 54/1 | DA+3 RC | Sandy | Pipe Type | 14.09.24 | Bhati Const.
133 | 4 | 54/2 | DA+3 | Sandy | Pipe Type | 14.09.24 | Bhati Const.
134 | 5 | 73/0 | DB2+0 | DRY | Pipe Type | 15.09.24 | Shree Shyam Const.
135 | 6 | 73/2 | DA+0 | DRY | Pipe Type | 16.09.24 | Shree Shyam Const.
136 | 7 | 73/1 | DA+0 | DRY | Pipe Type | 19.09.24 | Shree Shyam Const.
137 | 8 | 73/9 | DA+0 | DRY | Pipe Type | 19.09.24 | Shakti Const.
138 | 9 | 73/6 | DA+0 | DRY | Pipe Type | 22.09.24 | Shree Shyam Const.
139 | 10 | 66/0 | DC2+6 | DFR | Pipe Type | 27.09.24 | Bhati Const.
140 | 11 | 69/1 | DA+3 | DRY | Pipe Type | 27.09.24 | Bhati Const.
141 | 12 | 59/11 | DA+6 | DFR | Counter Poise | 28.09.24 | Mahadev Eng
142 | 13 | 50/3 | DA+6 | Sandy | Pipe Type | 29.09.24 | Kalpana Const.
143 | 14 | 50/6 | DA+9 RC | Sandy | Pipe Type | 29.09.24 | Kalpana Const.
Oct'24
144 | 1 | 59/1 | DA+3 RC | DRY | Pipe Type | 01.10.24 | Bhati Const.
145 | 2 | 59/0 | DC2+0 | DRY | Pipe Type | 5.10.24 | Bhati Const.
146 | 3 | 72/2 | DA+0 | DRY | Pipe Type | 07.10.24 | Shree Shyam Const.
147 | 4 | 73/3 | DA+0 | DRY | Pipe Type | 07.10.24 | Awadh Const
148 | 5 | 73/5 | DA+0 | DRY | Pipe Type | 07.10.24 | Shree Shyam Const.
149 | 6 | 73/7 | DA+0 | DRY | Pipe Type | 07.10.24 | Shakti Const.
150 | 7 | 73/8 | DA+3 | DRY | Pipe Type | 07.10.24 | Shakti Const.
151 | 8 | 73/4 | DA+0 | DRY | Pipe Type | 10.10.24 | Shree Shyam Const.
152 | 9 | 67/0 | DC1+9 | DRY | Pipe Type | 10.10.24 | Bhati Const.
153 | 10 | 69/0 | DB2+0 | DFR | Counter Poise | 16.10.24 | Bhati Const.
154 | 11 | 74/0 | DB2+0 | SANDY | Pipe Type | 16.10.24 | Shakti Const.
155 | 12 | 72/3 | DA+3 | DRY | Pipe Type | 18.10.24 | Shree Shyam Const.
156 | 13 | 71/6 | DA+0 | DRY | Pipe Type | 22.10.24 | Shree Shyam Const.
157 | 14 | 71/7 | DA+3 | DRY | Pipe Type | 22.10.24 | Shree Shyam Const.
158 | 15 | 49/7 | DA+0 RC | Sandy | Pipe Type | 23.10.24 | Kalpana Const.
159 | 16 | 59/4 | DA+3 | DFR | Counter Poise | 23.10.24 | Bhati Const.
Nov'24
160 | 1 | 54/0 | DB1+6 | Sandy | Pipe Type | 21.11.24 | Bhati Const.
Dec'24
161 | 1 | 65/8 | DA+0 | DRY | Pipe Type | 06.12.24 | Bhati Const.
162 | 2 | 65/7 | DA+0 | DRY | Pipe Type | 06.12.24 | Bhati Const.
2025-01-25
163 | 1 | 54/3 | DA+6 RC | Sandy | Pipe Type | 07.01.25 | Tantray Construction
164 | 2 | 54/4 | DA+9 RC | Sandy | Pipe Type | 10.01.25 | Tantray Construction
165 | 3 | 50/5 | DA+9 RC | SANDY | Pipe Type | 23.01.25 | om Const.
166 | 4 | 70/1 | DA+3 | DRY | Pipe Type | 25.01.25 | Meer Cost.
167 | 5 | 70/3 | DA+3 | DRY | Pipe Type | 25.01.25 | Meer Cost.
168 | 6 | 70/4 | DA+3 | DRY | Pipe Type | 25.01.25 | Meer Cost.
169 | 7 | 70/0 | DA+3 | DRY | Pipe Type | 25.01.25 | Meer Cost.
170 | 8 | 70/5 | DA+3 | DRY | Pipe Type | 27.01.25 | Meer Cost.
171 | 9 | 70/6 | DA+3 | DRY | Pipe Type | 27.01.25 | Tantray Construction
172 | 10 | 71/0 | DB2+3 | DRY | Pipe Type | 27.01.25 | Tantray Construction
173 | 11 | 71/1 | DA+3 | DRY | Pipe Type | 27.01.25 | Meer Cost.
174 | 12 | 71/2 | DA+3 | DRY | Pipe Type | 27.01.25 | Meer Cost.
175 | 13 | 71/3 | DA+6 | DRY | Pipe Type | 28.01.25 | Meer Cost.
176 | 14 | 71/4 | DA+3 | DRY | Pipe Type | 28.01.25 | Meer Cost.
177 | 15 | 72/0 | DB2+3 | DRY | Pipe Type | 28.01.25 | Meer Cost.
178 | 16 | 47/4 | DA+3 | SANDY | Pipe Type | 29.01.25 | Tantray Construction
179 | 17 | 47/1 | DA+3 | SANDY | Pipe Type | 29.01.25 | Tantray Construction
180 | 18 | 57/1 | DA | SANDY | Pipe Type | 29.01.25 | Meer Cost.
Feb-25
181 | 1 | 70/7 | DA+3 | DRY | Pipe Type | 01.02.25 | Tantray Construction
182 | 2 | 70/8 | DA+3 | DRY | Pipe Type | 01.02.25 | Tantray Construction
183 | 3 | 70/9 | DA+3 | DRY | Pipe Type | 01.02.25 | Tantray Construction
184 | 4 | 70/10 | DA+3 | DRY | Pipe Type | 01.02.25 | Tantray Construction
185 | 5 | 71/5 | DA+3 | DRY | Pipe Type | 01.02.25 | Meer Cost.
186 | 6 | 71/8 | DA+3 | DRY | Pipe Type | 01.02.25 | Meer Cost.
187 | 7 | 72/1 | DA+3 | DRY | Pipe Type | 01.02.25 | Meer Cost.
188 | 8 | 55/8 | DA+6 | SANDY | Pipe Type | 03.02.25 | Meer Cost.
189 | 9 | 55/2 | DA+0 | WFR | Counter Poise | 07.02.25 | Meer Cost.
190 | 10 | 52/0 | DC2+0 RC | Sandy | Pipe Type | 17.02.25 | Tantray Construction
191 | 11 | 52/1 | DA+6 RC | Sandy | Pipe Type | 17.02.25 | Tantray Construction
192 | 12 | 52/2 | DA+6 RC | Sandy | Pipe Type | 17.02.25 | Tantray Construction
193 | 13 | 52/4 | DA+9 RC | Sandy | Pipe Type | 17.02.25 | Tantray Construction
194 | 14 | 44/3 | DA+0 RC | SANDY | Pipe Type | 18.02.25 | Tantray Construction
195 | 15 | 44/7 | DA+9 | SANDY | Pipe Type | 18.02.25 | Iqbal
196 | 16 | 70/2 | DA+3 | DRY | Pipe Type | 19.02.25 | Bhati Const.
197 | 17 | 68/0 | DD45+0 | DRY | Pipe Type | 19.02.25 | Bhati Const.
198 | 18 | 65/10 | DA+0 | DRY | Pipe Type | 19.02.25 | Bhati Const.
199 | 19 | 54/5 | DA+9 RC | SANDY | Pipe Type | 23.02.25 | Meer const
200 | 20 | 55/0 | DB1+6 RC | SANDY | Pipe Type | 23.02.25 | Meer const
201 | 21 | 53/0 | DB2+9 RC | Sandy | Pipe Type | 23.02.25 | Meer const
202 | 22 | 53/1 | DA+9 RC | Sandy | Pipe Type | 23.02.25 | Meer const
203 | 23 | 53/2 | DA+0 RC | Sandy | Pipe Type | 23.02.25 | Meer const
204 | 24 | 53/3 | DA+6 RC | Sandy | Pipe Type | 23.02.25 | Meer const
205 | 25 | 53/4 | DA+0 RC | Sandy | Pipe Type | 23.02.25 | Meer const
206 | 26 | 45/1 | DA+9 RC | SANDY | Pipe Type | 26.02.25 | Tantray Construction
207 | 27 | 45/0 | DC2+0 RC | Sandy | Pipe Type | 26.02.25 | Nadeem
208 | 28 | 44/11 | DA+0 RC | Sandy | Pipe Type | 27.02.25 | Nadeem
209 | 29 | 44/10 | DB1+9 RC | Sandy | Pipe Type | 27.02.25 | Nadeem
210 | 30 | 44/9 | DA+9 RC | Sandy | Pipe Type | 27.02.25 | Iqbal
211 | 31 | 44/8 | DCT1+0 | SANDY | Pipe Type | 28.02.25 | Iqbal
212 | 32 | 44/5 | DA+9 RC | Sandy | Pipe Type | 28.02.25 | Tantray Construction
213 | 33 | 44/6 | DB1+3 RC | SANDY | Pipe Type | 28.02.25 | Tantray Construction
214 | 34 | 44/4 | DA+9 RC | Sandy | Pipe Type | 28.02.25 | Tantray Construction
| Mar-25 |  |  | 1 | 1 |  | 1
215 | 1 | 55/1 | DA+0 | WFR | Counter Poise | 02.03.25 | Bhati
216 | 2 | 44/0 | DB1+3 RC | SANDY | Pipe Type | 16.03.25 | OM Const
217 | 3 | 44/1 | DA+0 RC | Sandy | Pipe Type | 16.03.25 | OM Const
218 | 4 | 44/2 | DA+0 | Sandy | Pipe Type | 16.03.25 | OM Const
219 | 5 | 43/10 | DA+3 RC | SANDY | Pipe Type | 16.03.25 | OM Const
219 | 5 | 70/11 | DA+3 | DRY | Pipe Type | 29.03.25 | Bhati Const.
April-25
220 | 1 | 57/0 | DD60+25 | SANDY | Pipe Type | 07.4.25 | Bhati
|  | 56/0 | DD60+25 RC | SANDY

## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Supervisor
TB401 | 765 KV Fatehgarh III to Beawer 2nd Transmission Line, PKG G | Resonia Limited | 26/4/2023 | 2025-12-31 | Mr Santosh Pandey | Mr. Sanjay Kumar Gupta | Mr. Sandeep Singh Kumar | Mr. Virender Gupta | Sumit Kumar | Pradeep Kumar
[9 empty] | Rajeev Kumar | Vikas Kumar
[9 empty] | Vivek Shukla | Ganesh Singh
[9 empty] | Vijay Yadav | Dineshwar Mahto
[9 empty] | Ram Tirath Singh | Kamla Pal Prasad
[9 empty] | Jitendra Saini | Bisun Saw
Shakib Hussain
Umesh Prasad
Prince Kumar Nirala
Pramod Kumar Sahoo
Jainath Mahto
Rajesh Pal
Ramji Tanti
Rakesh Pramanik
Sam Mahammad
Suresh Kumar Pal
Hulas Kumar Mahto
Akash Dadarao Thul
Vaibhav Sharma
Dasharath Mahto
Mukesh Kumar
Dashrath Mahto
Kartik Mahato
Gangadin Sahu
Dev Narayan Mahto
Ashok Kumar
Debananda Ray
Dev Prakash
Jai Lal Mahto
Jitendra Kumar
Deo Prakash
Tribhuwan Mahto
Umesh Kumar Mahto
Rahul Sharma
Karan Pal Singh
Pritish Kumar Pradhan
Akshay Lal
Laxman
Jaylal Mahto

## Progress
Project Code | TB401 |  |  | LOA Start Date | 26.04.23 | SBU Head | Mr. Rajender Gupta | Head T&D-North | Sanjay K. Gupta
Project Name | 765KV DC Fateggarh III to Beawar (2nd) TL |  |  | LOA Completion Date | 31.03.25 | Regional Manager | Mr Sandeep Kumar Singh | Planning Engineer | Santosh Pandey
Client Name | RESONIA LIMITED |  |  | Expected Completion | 31.12.25 | Project Manager | Mr Virender Gupta | Date | 2026-03-16
Activity | Final Estimated Quantity | Cumulative L2 Till Last Month | Cumulative Progress Till last Month | L2 For Present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 Till Current Month | Completed Till Date | Balance Work | Under Progress | Gangs at present | Remarks
FOUNDATION | 521 | 521 | 521 | 0 | 0 |  |  | 0 | 521 | 0 |  |  |  | 100%
EARTHING | 521 | 521 | 521 | 0 | 0 |  |  | 0 | 521 | 0
ERECTION | 521 | 521 | 521 | 0 | 0 |  |  | 0 | 521 | 0 |  |  |  | 100%
TACK WELDING | 521 | 521 | 507 | 0 | 14 |  | 2 | 0 | 509 | 12
Strg (Pay-Out) | 202.13 | 202 | 191.539 | 0 | 10.59 |  | 6.049 | 0 | 197.588 | 4.542 | 4.543 | 3 |  | 97.75%
Strg (Final Sag) | 202.13 | 202 | 189.1 | 0 | 13.03 | 3.172 | 8.489 | 0 | 197.589 | 4.541 | 4.543 | 3
Stringing OPGW | 202.13 | 202 | 191.399 | 0 | 10.69 | 4.543 | 10.731 | 0 | 202.13 | 0 |  |  |  | 99.25%
99.25%
[7 empty] | 11.02.26 |  |  |  | 4th Phase WIP& Top Phase Final Sag

## Foundation (Pkg-G)
KEC INTERNATIONAL LIMITED | [9 empty] | Date: | 2026-03-16
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
FOUNDATION Pkg -G (Section -II)
Sl. No. | Month Sl. No. | Location No. | Tower Type | Classification | Excavation Start | Dt. of Start | Dt. of complete | Name of Sub-Contractor | KEC representative | KEC Section In-Charge | Remarks
July-23
1 | 1 | 58/12 | DA+0 | DRY |  | 14.07.2023 | 15.07.2023 | Mahadev engg. | Mr. Mahamaya | Mr. Shah Ali Khan | Complete
2 | 2 | 59/1 | DA+0 | DRY |  | 19.07.2023 | 20.07.2023 | Manoj Sharma | Mr Manoj | Mr. Shah Ali Khan | Complete
3 | 3 | 58/14 | DA+0 | DRY |  | 17.07.2023 | 20.07.2023 | Mahadev engg. | Mr Manoj | Mr. Shah Ali Khan | Complete
4 | 4 | 59/3 | DA+0 | DRY |  | 17.07.2023 | 29.07.2023 | Manoj Sharma | Mr. Mahamaya | Mr. Shah Ali Khan | Complete
5 | 5 | 58/9 | DA+0 | DRY |  | 26.07.2023 | 30.07.2023 | Mahadev engg. | RT Singh | Mr. Shah Ali Khan | Complete
Aug-23
6 | 1 | 59/2 | DA+0 | DRY |  | 01.08.23 | 03.08.23 | Manoj Sharma | Mr. Mahamaya | Mr. Shah Ali Khan | Complete
7 | 2 | 58/1 | DA+0 | DRY |  | 02.08.2023 | 04.08.2023 | Mahadev engg. | RT Singh | Mr. Shah Ali Khan | Complete
8 | 3 | 59/6 | DA+0 | DRY |  | 04.08.2023 | 06.08.2023 | Manoj Sharma | Mr. Mahamaya | Mr. Shah Ali Khan | Complete
9 | 4 | 58/3 | DA+3 | DRY |  | 04.08.2023 | 06.08.2023 | Mahadev engg. | RT Singh | Mr. Rajesh Yadav | Complete
10 | 5 | 51/7 | DA+3 | DFR |  | 08.08.23 | 09.08.23 | Vaishali Const | Dipesh Das | Mr. Ujjawal Nirala | Complete
11 | 6 | 58/10 | DA+3 | DRY |  | 09.08.23 | 10.08.2023 | Mahadev engg. | RT Singh | RT Singh | Complete
12 | 7 | 57/9 | DA+0 | DRY |  | 09.08.23 | 11.08.2023 | Manoj Sharma | Mr. Mahamaya | RT Singh | Complete
13 | 8 | 58/5 | DA+3 | DRY |  | 12.08.23 | 13.08.2023 | Mahadev engg. | RT Singh | RT Singh | Complete
14 | 9 | 57/10 | DA+0 | DRY |  | 11.08.23 | 13.08.2023 | Manoj Sharma | RT Singh | RT Singh | Complete
15 | 10 | 51/5 | DA+0 | DRY |  | 13.08.23 | 14.08.23 | Vaishali Const | Dipesh Das | Mr. Ujjawal Nirala | Complete
16 | 11 | 52/2 | DA+3 | DFR |  | 13.08.23 | 16.08.23 | Khewanjrai Electrical | Dipesh Das | Mr. Ujjawal Nirala | Complete
17 | 12 | 57/13 | DA+0 | DRY |  | 14.08.23 | 16.08.23 | Manoj Sharma | RT Singh | RT Singh | Complete
18 | 13 | 58/11 | DA+3 | DRY |  | 16.08.23 | 17.08.23 | Mahadev engg. | RT Singh | RT Singh | Complete
19 | 14 | 57/11 | DA+0 | DRY |  | 17.08.23 | 18.08.23 | Manoj Sharma | RT Singh | RT Singh | Complete
20 | 15 | 51/2 | DA+0 | DRY |  | 14.08.23 | 19.08.23 | B S Electrical | Dipesh Das | Mr. Ujjawal Nirala | Complete
21 | 16 | 58/15 | DA+3 | DRY |  | 18.08.23 | 20.08.23 | Mahadev engg. | RT Singh | RT Singh | Complete
22 | 17 | 57/12 | DA+3 | DRY |  | 19.08.23 | 21.08.23 | Manoj Sharma | RT Singh | RT Singh | Complete
23 | 18 | 53/2 | DA+3 | DFR |  | 21.08.23 | 22.08.23 | Vaishali Const | Dipesh Das | Mr. Ujjawal Nirala | Complete
24 | 19 | 58/6 | DA+3 | DRY |  | 21.08.23 | 22.08.23 | Mahadev engg. | RT Singh | RT Singh | Complete
25 | 20 | 57/8 | DA+3 | DRY |  | 21.08.23 | 23.08.23 | Manoj Sharma | Jitendra Saini | RT Singh | Complete
26 | 21 | 57/7 | DA+3 | DRY |  | 23.08.23 | 24.08.23 | Manoj Sharma | Jitendra Saini | RT Singh | Complete
27 | 22 | 58/16 | DA+0 | DRY |  | 24.08.23 | 25.08.23 | Mahadev engg. | RT Singh | RT Singh | Complete
28 | 23 | 52/1 | DA+0 | DFR |  | 23.08.23 | 25.08.23 | Khewanjrai Electrical | Dipesh Das | Mr. Ujjawal Nirala | Complete
29 | 24 | 57/4 | DA+0 | DRY |  | 26.08.23 | 27.08.23 | Manoj Sharma | Jitendra Saini | RT Singh | Complete
30 | 25 | 53/3 | DA+3 | DRY |  | 26.08.23 | 27.08.23 | Vaishali Const | Dipesh Das | Mr. Ujjawal Nirala | Complete
31 | 26 | 51/4 | DA+3 | DFR |  | 25.08.23 | 27.08.23 | B S Electrical | Dipesh Das | Mr. Ujjawal Nirala | Complete
32 | 27 | 55/7 | DA+0 | DRY |  | 26.08.23 | 28.8.23 | Nurul Amin | Ganesh Rajput | RT Singh | Complete
33 | 28 | 58/8 | DA+0 | DRY |  | 27.08.23 | 28.08.23 | Mahadev engg. | Mr. Mahamaya | RT Singh | Complete
34 | 29 | 57/5 | DA+3 | DRY |  | 27.08.23 | 28.8.23 | Manoj Sharma | Jitendra Saini | RT Singh | Complete
35 | 30 | 55/1 | DA+3 | DRY |  | 28.8.23 | 30.08.23 | Amirul Islam | RT Singh | RT Singh | Complete
36 | 31 | 51/3 | DA+0 | DFR |  | 30.08.23 | 31.08.23 | B S Electrical | Dipesh Das | Mr. Ujjawal Nirala | Complete
37 | 32 | 52/4 | DA+0 | DFR |  | 30.08.23 | 31.08.23 | Khewanjrai Electrical | Dipesh Das | Mr. Ujjawal Nirala | Complete
38 | 33 | 55/8 | DA+3 | DRY |  | 30.08.23 | 31.08.23 | Nurul Amin | Ganesh Rajput | RT Singh | Complete
39 | 34 | 59/5 | DA+0 | DRY |  | 30.08.23 | 31.08.23 | Mahadev engg. | Mahmya Pratap | Mr. Shah Ali Khan | Complete
2023-09-01
40 | 1 | 57/2 | DA+0 | DRY | 27.08.23 | 30.08.23 | 01.09.23 | Manoj Sharma | Jitendra Saini | RT Singh | Complete
41 | 2 | 61/1 | DA+0 | DRY | 29.08.23 | 02.09.23 | 03.09.23 | Mahadev engg. |  | Mr. Shah Ali Khan | Complete
42 | 3 | 53/4 | DA+3 | DRY | 30.08.23 | 02.09.23 | 05.09.23 | Vaishali Const | Dipesh Das | Mr. Ujjawal Nirala | Complete
43 | 4 | 61/2 | DA+0 | DRY | 02.09.23 | 04.09.23 | 05.09.23 | Mahadev engg. |  | Mr. Shah Ali Khan | Complete
44 | 5 | 48/1 | DA+0 | DRY | 31.08.23 | 04.09.23 | 06.09.23 | Shri Bhadariyarai Enterprises | Dipesh Das | Mr. Ujjawal Nirala | Complete
45 | 6 | 55/9 | DA+3 | DRY | 31.08.23 | 03.09.23 | 06.09.23 | Nurul Amin | Ganesh Rajput | RT Singh | Complete
46 | 7 | 58/2 | DA+0 | DRY | 04.09.23 | 08.09.23 | 09.09.23 | Mahadev engg. | RT Singh | RT Singh | Complete
47 | 8 | 47/2 | DA+0 | DFR | 04.09.23 | 06.09.23 | 09.09.23 | B S Electrical | Dipesh Das | Mr. Ujjawal Nirala | Complete
48 | 9 | 57/1 | DA+3 | DRY | 01.09.23 | 09.09.23 | 11.09.23 | Manoj Sharma | Jitendra Saini | RT Singh | Complete
49 | 10 | 48/2 | DA+3 | DRY | 05.09.23 | 10.09.23 | 11.09.23 | Shri Bhadariyarai Enterprises | Dipesh Das | Mr. Ujjawal Nirala | Complete
50 | 11 | 51/10 | DA+3 | DFR | 08.09.23 | 10.09.23 | 12.09.23 | Amirul Islam | Ganesh Rajput | RT Singh | Complete
51 | 12 | 57/3 | DA+0 | DRY | 04.09.23 | 12.09.23 | 14.09.23 | Manoj Sharma | RT Singh | RT Singh | Complete
52 | 13 | 72/3 | DA+0 | DRY | 08.09.23 | 13.09.23 | 14.09.23 | Mahadev engg. | Manoj | Mr. Shah Ali Khan | Complete
53 | 14 | 43/4 | DA+9 | DRY | 09.09.23 | 12.09.23 | 14.09.23 | Shakti Construction | Dipesh Das | Rakesh Pathak | Complete
54 | 15 | 50/4 | DA+3 | DRY | 11.09.23 | 15.09.23 | 16.09.23 | Shri Bhadariyarai Enterprises | Dipesh Das | Mr. Ujjawal Nirala | Complete
55 | 16 | 55/2 | DA+3 | DFR | 26.08.23 | 03.09.23 | 16.09.23 | Amirul Islam | Kumar Nayak | RT Singh | Complete
56 | 17 | 52/5 | DA+3 | DRY | 10.09.23 | 14.09.23 | 16.09.23 | Nurul Amin | Ganesh Rajput | RT Singh | Complete
57 | 18 | 47/3 | DA+0 | DFR | 06.09.23 | 14.09.23 | 16.09.23 | B S Electrical | Dipesh Das | Mr. Ujjawal Nirala | Complete
58 | 19 | 72/4 | DA+0 | DRY | 11.09.23 | 16.09.23 | 18.09.23 | Mahadev engg. | Manoj | Sumit mishra | Complete
59 | 20 | 43/5 | DA+0 | SANDY | 08.09.23 | 16.09.23 | 18.09.23 | Shakti Construction | Dipesh Das | Rakesh Pathak | Complete
60 | 21 | 55/3 | DA+0 | DFR | 03.09.23 | 16.09.23 | 20.09.23 | Amirul Islam | Kumar Nayak | RT Singh | Complete
61 | 22 | 56/9 | DA+3 | DRY | 10.09.23 | 16.09.23 | 21.09.23 | Manoj Sharma | RT Singh | RT Singh | Complete
62 | 23 | 71/1 | DA+0 | DRY | 05.09.23 | 21.09.23 | 22.09.23 | Mahadev engg. | Manoj | Sumit mishra | Complete
63 | 24 | 56/8 | DA+3 | DRY | 14.09.23 | 19.09.23 | 22.09.23 | Manoj Sharma | RT Singh | RT Singh | Complete
64 | 25 | 55/10 | DA+3 | DRY | 18.09.23 | 21.09.23 | 22.09.23 | Nurul Amin | Ganesh Rajput | RT Singh | Complete
65 | 26 | 56/7 | DA+3 | DRY | 19.09.23 | 21.09.23 | 22.09.23 | Manoj Sharma | RT Singh | RT Singh | Complete
66 | 27 | 55/4 | DA+3 | DFR | 18.09.23 | 23.09.23 | 24.09.23 | Amirul Islam | Kumar Nayak | RT Singh | Complete
67 | 28 | 56/3 | DA+0 | DFR | 14.09.23 | 23.09.23 | 25.09.23 | Vaishali Const | RT Singh | RT Singh | Complete
68 | 29 | 44/1 | DA+0 | WFR | 16.09.23 | 20.09.23 | 25.09.23 | Shakti Construction | Dipesh Das | Rakesh Pathak | Complete
69 | 30 | 72/5 | DA+0 | DRY | 19.09.23 | 24.09.23 | 25.09.23 | Mahadev engg. | Manoj | Sumit mishra | Complete
70 | 31 | 41/10 | DA+3 | SANDY | 19.09.23 | 22.09.23 | 25.09.23 | Om Const | Dipesh Das | Rakesh Pathak | Complete
71 | 32 | 56/6 | DA+3 | DRY | 21.09.23 | 24.09.23 | 25.09.23 | Manoj Sharma | RT Singh | RT Singh | Complete
72 | 33 | 72/2 | DA+0 | DRY | 15.09.23 | 20.09.23 | 26.09.23 | Mahadev engg. | Manoj | Sumit mishra | Complete
73 | 34 | 50/3 | DA+0 | DFR | 18.09.23 | 21.09.23 | 27.09.23 | Shri Bhadariyarai Enterprises | Dipesh Das | Mr. Ujjawal Nirala | Complete
74 | 35 | 44/4 | DA+0 | WFR | 19.09.23 | 23.09.23 | 27.09.23 | B S Electrical | Dipesh Das | Mr. Ujjawal Nirala | Complete
75 | 36 | 55/5 | DA+0 | DFR | 22.09.23 | 26.09.23 | 28.09.23 | Amirul Islam | Kumar Nayak | RT Singh | Complete
76 | 37 | 71/3 | DA+0 | DRY | 21.09.23 | 28.09.23 | 29.09.23 | Mahadev engg. | Manoj | Sumit mishra | Complete
77 | 38 | 44/2 | DA+0 | SANDY | 24.9.23 | 27.09.23 | 29.09.23 | Shakti Construction | Dipesh Das | Rakesh Pathak | Complete
78 | 39 | 56/4 | DA+3 | DFR | 24.9.23 | 29.09.23 | 30.09.23 | Manoj Sharma | RT Singh | RT Singh | Complete
79 | 40 | 71/4 | DA+0 | DRY | 23.09.23 | 29.09.23 | 30.09.23 | Mahadev engg. | Manoj | Sumit mishra | Complete
80 | 41 | 41/11 | DA+3 | SANDY | 23.09.23 | 27.09.23 | 30.09.23 | Om Const | Dipesh Das | Rakesh Pathak | Complete
2023-10-01
81 | 1 | 55/11 | DA+3 | DFR | 22.09.23 | 30.09.23 | 04.10.23 | Nurul Amin | Ganesh Rajput | RT Singh | Complete
82 | 2 | 56/5 | DA+0 | DRY | 27.09.23 | 03.10.23 | 04.10.23 | Manoj Sharma | RT Singh | RT Singh | Complete
83 | 3 | 72/1 | DA+0 | DRY | 29.09.23 | 03.10.23 | 04.10.23 | Mahadev engg. | Manoj | Sumit mishra | Complete
84 | 4 | 56/1 | DA+3 | DFR | 21.09.23 | 03.10.23 | 05.10.23 | Vaishali Const | RT Singh | RT Singh | Complete
85 | 5 | 71/5 | DA+0 | DRY | 26.09.23 | 04.10.23 | 06.10.23 | Mahadev engg. | Manoj | Sumit mishra | Complete
86 | 6 | 41/7 | DA+3 | SANDY | 29.09.23 | 04.10.23 | 08.10.23 | Om Const | Dipesh Das | Rakesh Pathak | Complete
87 | 7 | 44/3 | DA+3 | WFR | 29.09.23 | 06.10.23 | 09.10.23 | Shakti Construction | Dipesh Das | Mr. Ujjawal Nirala | Complete
88 | 8 | 58/4 | DA+0 | DRY | 06.10.23 | 06.10.23 | 10.10.23 | Mahadev engg. | Manoj | Sumit mishra | Complete
89 | 9 | 56/2 | DA+3 | DFR | 05.10.23 | 13.10.23 | 14.10.23 | Vaishali Const | jintender | RT Singh | Complete
90 | 10 | 58/7 | DB1+0 | DRY | 10.10.23 | 17.10.23 | 19.10.23 | Mahadev engg. | Manoj | Sumit mishra | Complete
91 | 11 | 43/1 | DA+9 | SANDY | 11.10.23 |  | 19.10.23 | Om Const | Dipesh Das | Rakesh Pathak | Complete
92 | 12 | 57/6 | DB1+0 | DRY | 16.10.23 | 18.10.23 | 20.10.23 | Manoj Sharma |  | RT Singh | Complete
93 | 13 | 55/6 | DA+3 | DRY | 30.09.23 | 17.10.23 | 21.10.23 | Amirul Islam | Kumar Nayak | RT Singh | Complete
94 | 14 | 33/1 | DA+0 | SANDY | 15.10.23 |  | 22.10.23 | Shakti Construction | Dipesh Das | Mr. Ujjawal Nirala | Complete
95 | 15 | 47/0 | DB1+0 | SANDY | 19.10.23 | 23.10.23 | 26.10.23 | Om Const | Dipesh Das | RT Singh | Complete
96 | 16 | 59/0 | DB2+0 | DRY | 18.10.23 | 23.10.23 | 26.10.23 | Mahadev engg. | Manoj | Sumit mishra | Complete
97 | 17 | 57/0 | DB2+0 | DRY | 21.10.23 | 25.10.23 | 27.10.23 | Manoj Sharma |  | Sumit mishra | Complete
98 | 18 | 46/2 | DA+0 | DRY | 26.09.23 | 29.09.23 | 29.10.23 | Shri Bhadariyarai Enterprises/Om Const | Ganesh | RT Singh | Complete
99 | 19 | 56/0 | DB1+0 | DFR | 19.10.23 | 28.10.23 | 31.10.23 | Vaishali Const | jintender | Sumit mishra | Complete
100 | 20 | 51/0 | DB2+0 | DFR | 26.10.23 | 30.10.23 | 31.10.23 | Manoj Sharma | jintender | Sumit mishra | Complete
101 | 21 | 32/7 | DA+0 | Sandy |  | 2023-10-23 | 2023-10-28 | Shakti Construction | Kumar Nayak |  | Complete
2023-11-01
102 | 1 | 48/0 | DB2+0 | SANDY | 29.10.23 | 01.11.23 | 06.11.23 | Om Const | Ganesh | Sumit mishra | Complete
103 | 2 | 52/0 | DB2+0 | DRY | 01.11.23 | 05.11.23 | 06.11.23 | Manoj Sharma | Ganesh | Sumit mishra | Complete
104 | 3 | 51/9 | DA+3 | DRY | 07.11.23 | 09.11.23 | 13.11.23 | Om Const | Ganesh | Sumit mishra | Complete
105 | 4 | 51/6 | DA+0 RC | DRY | 17.11.23 | 21.11.23 | 30.11.23 | Om Const | Ganesh | RT Singh | Complete
106 | 5 | 32/5 | DA+6 | Sandy |  | 2023-10-29 | 2023-11-04 | Shakti Construction |  | Kumar Nayak | Complete
107 | 6 | 32/1 | DA+9 | Sandy |  | 2023-11-03 | 2023-11-10 | Shakti Construction |  | Kumar Nayak | Complete
108 | 7 | 30/2 | DA+0 | Sandy |  | 2023-11-13 | 2023-11-16 | Shakti Construction |  | Kumar Nayak | Complete
109 | 8 | 32/0 | DB2+6 | Sandy |  | 2023-11-18 | 2023-11-28 | Shakti Construction |  | Dipesh | Complete
2023-12-01
110 | 1 | 46/3 | DA+0 | SANDY | 27.11.23 | 05.12.23 | 07.12.23 | Manoj Sharma | Umesh Kumar | RT Singh | Complete
111 | 2 | 51/1 | DA+0 | DFR | 10.09.23 | 15.11.23 | 06.12.23 | Amirul Islam/Om Const | Umesh Kumar | RT Singh | Complete
112 | 3 | 51/8 | DA+3 | DFR | 20.11.23 | 06.12.23 | 09.12.23 | Om Const | Umesh Kumar | RT Singh | Complete
113 | 4 | 41/5 | DA+0 (RC) | SANDY | 05.12.23 | 07.12.23 | 13.12.23 | Shakti Construction | Dipesh | Jish C Verghese | Complete | 157
114 | 5 | 53/1 | DA+0 (RC) | DRY | 09.12.23 | 11.12.23 | 14.12.23 | Om Const | Umesh Kumar | RT Singh | Complete
115 | 6 | 52/3 | DA+0 (RC) | SANDY | 13.12.23 | 16.12.23 | 21.12.23 | Om Const | Umesh Kumar | RT Singh | Complete
116 | 7 | 41/6 | DA+0(RC) | SANDY | 23.12.23 | 28.12.23 | 31.12.23 | Riddhika Tech. | Manoj | Jish C Verghese | Complete
117 | 8 | 31/3 | DA+0 | Sandy |  | 2023-11-28 | 2023-12-04 | Shakti Construction |  | Dipesh | Complete
118 | 9 | 24/3 | DA+0 | Sandy |  | 2023-12-19 | 2023-12-26 | N.R. Enterprises |  | Ullas Mahto | Complete
119 | 10 | 21/8 | DA+0 | DFR |  | 2023-12-23 | 2023-12-29 | Mehai Construction |  | Jeetu Sachan | Complete
120 | 11 | 29/8 | DA+3 | Sandy |  | 2023-12-23 | 2023-12-28 | Bande Bharat Group |  | Jeetu Sachan | Complete
121 | 12 | 29/3 | DA+6 | Sandy |  | 2023-12-27 | 2023-12-30 | N.R. Enterprises |  | Jeetu Sachan | Complete
122 | 13 | 29/7 | DA+3 | Sandy |  | 2023-12-28 | 2023-12-30 | Bande Bharat Group |  | Jeetu Sachan | Complete
123 | 14 | 29/5 | DA+0 | Sandy |  | 2023-12-29 | 2023-12-31 | N.R. Enterprises |  | Kuntal Debnath | Complete
124 | 15 | 21/9 | DA+6 | DRY |  | 2023-12-27 | 2023-12-31 | Mehai Construction |  | Jeetu Sachan | Complete
2024-01-01
125 | 1 | 41/4 | DA+0(RC) | SANDY | 30.12.23 | 03.01.24 | 06.01.24 | Riddhika Tech. | Rajiv | Jish C Verghese | Complete
126 | 2 | 41/9 | DA+0(RC) | SANDY | 04.01.24 | 08.01.24 | 12.01.24 | Riddhika Tech. | Rajiv | Jish C Verghese | Complete
127 | 3 | 41/8 | DA+0 (RC) | SANDY | 08.01.24 | 13.01.24 | 18.01.24 | Riddhika Tech. | Rajiv | Jish C Verghese | Complete
128 | 4 | 41/12 | DA+3 RC | SANDY | 19.01.24 | 21.01.24 | 25.01.24 | Riddhika Tech. | Rajiv | Jish C Verghese | Complete
129 | 5 | 46/4 | DA+0 (RC) | SANDY |  | 23.01.24 | 28.01.24 | Om Const |  | Jish C Verghese | Complete
130 | 6 | 43/2 | DA+9 RC | SANDY | 19.01.24 | 24.01.24 | 30.01.24 | Sai Infra | Manoj | Jish C Verghese | Complete
131 | 7 | 63/5 | DA+3 | DRY | 23.01.24 | 29.01.24 | 30.01.24 | Bhati Const. |  | Rakesh Pathak | Complete
132 | 8 | 63/6 | DA+3 | DRY | 30.01.24 | 30.01.24 | 31.01.24 | Bhati Const. |  | Rakesh Pathak | Complete
133 | 9 | 23/2 | DA+0 | DFR |  | 2024-01-01 | 2024-01-13 | Nagana Rai & Company |  | Jeetu Sachan | Complete
134 | 10 | 30/1 | DA+3 | Sandy |  | 2024-01-04 | 2024-01-14 | Bande Bharat Group |  | Kuntal Debnath | Complete
135 | 11 | 31/4 | DA+9 | Sandy |  | 2024-01-12 | 2024-01-19 | Bande Bharat Group |  | Kuntal Debnath | Complete
136 | 12 | 21/10 | DA+9 | Sandy |  | 2024-01-11 | 2024-01-25 | Mehai Construction |  | Jeetu Sachan | Complete
137 | 13 | 32/2 | DA+0 | Sandy |  | 2024-01-20 | 2024-01-28 | Bande Bharat Group |  | Kuntal Debnath | Complete
138 | 14 | 23/5 | DA+0 | DFR |  | 2024-01-25 | 2024-01-30 | A.B. Construction |  | Jeetu Sachan | Complete
139 | 15 | 29/6 | DA+6 | Sandy |  | 2024-01-20 | 2024-01-31 | N.R. Enterprises |  | Kuntal Debnath | Complete
140 | 16 | 32/3 | DA+3 | Sandy |  | 2024-01-27 | 2024-01-31 | Bande Bharat Group |  | Kuntal Debnath | Complete
Feb-24
141 | 1 | 40/11 | DA+9 RC | SANDY | 20.01.24 | 28.01.24 | 01.02.24 | Riddhika Tech. |  | Jish C Verghese | Complete
142 | 2 | 53/0 | DC2+3 | DRY | 27.01.24 | 29.01.24 | 02.02.24 | Om Const |  | RT Singh | Complete
143 | 3 | 55/0 | DC1+0 | DRY | 27.01.24 | 03.01.24 | 05.02.24 | Manoj Sharma |  | RT Singh | Complete
144 | 4 | 43/3 | DA+3 RC | SANDY | 27.01.24 | 31.01.24 | 05.02.24 | Sai Infra | Manoj | Jish C Verghese | Complete
145 | 5 | 40/10 | DB1+6 | SANDY | 24.01.24 | 02.02.24 | 06.02.24 | Riddhika Tech. |  | Jish C Verghese | Complete
146 | 6 | 65/5 | DA+0 | DRY |  | 13.02.24 | 14.02.24 | Bhati Const. | Sanjay Thakur | Rakesh Pathak | Complete
147 | 7 | 40/5 | DB1+9 | SANDY | 04.02.24 | 08.02.24 | 15.02.24 | Riddhika Tech. | Rajiv |  | Complete
148 | 8 | 58/0 | DC2+0 | DRY | 03.02.24 | 11.02.24 | 15.02.24 | Mahadev engg. |  | Rakesh Pathak | Complete
149 | 9 | 65/4 | DA+0 | DRY | 14.02.24 | 15.02.24 | 16.02.24 | Bhati Const. | Sanjay Thakur | Rakesh Pathak | Complete
150 | 10 | 38/3 | DA+9 RC | SANDY | 05.02.24 | 08.02.24 | 17.02.24 | Sai Infra | Manoj |  | Complete
151 | 11 | 65/1 | DA+3 | DRY | 15.02.24 | 17.02.24 | 18.02.24 | Bhati Const. | Sanjay Thakur | Rakesh Pathak | Complete
152 | 12 | 38/2 | DA+6 | SANDY | 14.02.24 | 17.02.24 | 20.02.24 | Sai Infra | Manoj |  | Complete
153 | 13 | 40/6 | DA+3 RC | SANDY | 14.02.24 | 16.02.24 | 21.02.24 | Riddhika Tech. | Rajiv |  | Complete
154 | 14 | 65/3 | DA+0 | DRY | 17.02.24 | 21.2.24 | 22.02.24 | Bhati Const. |  | Rakesh Pathak | Complete
155 | 15 | 37/2 | DB1+6 | SANDY | 17.02.24 | 21.02.24 | 26.02.24 | Veerteja Enterprises | Manoj | RT Singh | Complete
156 | 16 | 40/3 | DA+3 RC | SANDY | 21.02.24 | 23.02.24 | 27.02.24 | Riddhika Tech. | Rajiv |  | Complete
157 | 17 | 38/6 | DA+0 RC | SANDY | 25.02.24 | 26.02.24 | 29.02.24 | Shakti Construction |  |  | Complete
158 | 18 | 37/3 | DA+0 | SANDY | 26.02.24 | 28.02.24 | 29.02.24 | Veerteja Enterprises | Manoj | RT Singh | Complete
159 | 19 | 23/3 | DA+0 | DFR |  | 2024-01-31 | 2024-02-05 | A.B. Construction |  | Jeetu Sachan | Complete
160 | 20 | 22/5 | DA+3 | DFR |  | 2024-01-16 | 2024-02-10 | Mateshwari Const. |  | Jeetu Sachan | Complete
161 | 21 | 31/2 | DA+0 | Sandy |  | 2024-02-03 | 2024-02-11 | Bande Bharat Group |  | Kuntal Debnath | Complete
162 | 22 | 29/9 | DA+3 | Sandy |  | 2024-02-02 | 2024-02-12 | N.R. Enterprises |  | Kuntal Debnath | Complete
163 | 23 | 22/4 | DA+3 | DFR |  | 2024-02-05 | 2024-02-18 | Jai Bhawani Construction |  | Jeetu Sachan | Complete
164 | 24 | 21/12 | DA+9 | Sandy |  | 2024-02-14 | 2024-02-19 | Mehai Construction |  | Jeetu Sachan | Complete
165 | 25 | 22/9 | DA+6 | DRY |  | 2024-02-10 | 2024-02-20 | Majisa Construction |  | Jeetu Sachan | Complete
166 | 26 | 23/1 | DA+0 | Sandy |  | 2024-02-14 | 2024-02-22 | A.B. Construction |  | Jeetu Sachan | Complete
167 | 27 | 31/1 | DA+9+3 | Sandy |  | 2024-02-12 | 2024-02-22 | Bande Bharat Group |  | Kuntal Debnath | Complete
168 | 28 | 22/8 | DA+6 | DRY |  | 2024-02-18 | 2024-02-25 | Majisa Construction |  | Jeetu Sachan | Complete
169 | 29 | 29/10 | DA+6 | Sandy |  | 2024-02-18 | 2024-02-27 | Bande Bharat Group |  | Jeetu Sachan | Complete
170 | 30 | 22/2 | DA+0 | DFR |  | 2024-02-20 | 2024-02-29 | Jai Bhawani Construction |  | Jeetu Sachan | Complete
171 | 31 | 28/1 | DA+6 | Sandy |  | 2024-02-20 | 2024-02-29 | R.D. Enterprises |  | Kuntal Debnath | Complete
172 | 32 | 27/4 | DA+0 | Sandy |  | 2024-02-22 | 2024-02-29 | N.R. Enterprises |  | Kuntal Debnath | Complete
March'24
173 | 1 | 65/2 | DA+0 | SANDY | 22.02.24 | 26.02.24 | 02.03.24 | Bhati Const. | Sanjay Thakur | Rakesh Pathak | Complete
174 | 2 | 40/4 | DA+9 RC | SANDY | 29.02.24 | 29.02.24 | 06.03.24 | Riddhika Tech. | Rajiv |  | Complete |  | 45
175 | 3 | 38/8 | DA+0 RC | SANDY | 01.03.24 | 01.03.24 | 06.03.24 | Shakti Construction |  | RT Singh | Complete
176 | 4 | 65/6 | DA+0 | Dry | 06.03.24 | 08.03.24 | 09.03.24 | Bhati Const. | Sanjay Thakur | Rakesh Pathak | Complete
177 | 5 | 38/1 | DA+3 RC | SANDY | 07.03.24 | 08.03.24 | 12.03.24 | Shakti Construction | Jitendra Kumar | RT Singh | Complete
178 | 6 | 37/4 | DA+6 RC | SANDY | 01.03.24 | 01.03.24 | 13.03.24 | Veerteja Enterprises |  |  | Complete
179 | 7 | 39/1 | DA+6 RC | SANDY | 06.03.24 | 07.03.24 | 13.03.24 | Riddhika Tech. |  |  | Complete
180 | 8 | 63/2 | DA+0 | DRY | 10.03.24 | 12.03.24 | 13.03.24 | Bhati Const. |  |  | Complete
181 | 9 | 39/3 | DA+3 RC | SANDY | 13.03.24 | 17.03.24 | 21.03.24 | Riddhika Tech. |  |  | Complete
182 | 10 | 10/12 | DB1+3 | DRY |  | 2024-02-24 | 2024-03-06 | Om Construction |  | Abhijit Dutta | Complete
183 | 11 | 27/5 | DA+0 | Sandy |  | 2024-03-02 | 2024-03-07 | N.R. Enterprises |  | Kuntal Debnath | Complete
184 | 12 | 30/0 | DC2+0 | Sandy |  | 2024-02-28 | 2024-03-09 | Bande Bharat Group |  | Abhijit Dutta | Complete
185 | 13 | 28/0 | DB1+0 | Sandy |  | 2024-03-02 | 2024-03-11 | R.D. Enterprises |  | Kuntal Debnath | Complete
186 | 14 | 8/10 | DA+3 | DFR |  | 2024-02-28 | 2024-03-12 | Mateshwari Const. |  | Abhijit Dutta | Complete
187 | 15 | 6/2 | DA+3 | DFR |  | 2024-03-02 | 2024-03-13 | Majisa Construction |  | Abhijit Dutta | Complete
188 | 16 | 8/11 | DA+3 | DFR |  | 2024-03-02 | 2024-03-14 | Jai Bhawani Construction |  | Abhijit Dutta | Complete
189 | 17 | 26/4 | DA+9 | Sandy |  | 2024-03-13 | 2024-03-23 | Bande Bharat Group |  | Kuntal Debnath | Complete
190 | 18 | 10/7 | DA+6 | DRY |  | 2024-03-02 | 2024-03-30 | Shri Degrai Enterprises |  | Abhijit Dutta | Complete
April'24
191 | 1 | 8/8 | DA+6 | DFR |  | 2024-03-30 | 2024-04-06 | Mateshwari Const. |  | Abhijit Dutta | Complete
192 | 2 | 10/14 | DA+3 | DRY |  | 2024-03-31 | 2024-04-10 | Shri Degrai Enterprises |  | Abhijit Dutta | Complete
193 | 3 | 8/6 | DA+3 | DRY |  | 2024-04-06 | 2024-04-12 | Mateshwari Const. |  | Jeetu Sachan | Complete
194 | 4 | 10/10 | DA+3 | DRY |  | 2024-04-08 | 2024-04-14 | Shri Degrai Enterprises |  | Jeetu Sachan | Complete
195 | 5 | 32/4 | DA+0+3 | Sandy |  | 2024-04-08 | 2024-04-18 | Bande Bharat Group |  | Kuntal Debnath | Complete
196 | 6 | 10/6 | DA+3 | DFR |  | 2024-04-15 | 2024-04-24 | Shri Degrai Enterprises |  | Jeetu Sachan | Complete
197 | 7 | 8/1 | DA+3 | DRY |  | 2024-04-10 | 2024-04-25 | Mateshwari Const. |  | Jeetu Sachan | Complete
198 | 8 | 10/13 | DA+3 | DRY |  | 2024-04-15 | 2024-04-28 | Shri Degrai Enterprises |  | Jeetu Sachan | Complete
May'24
199 | 1 | 39/4 | DA+0(RC) | SANDY | 14.04.24 | 29.04.24 | 09.05.24 | SB MEHAR CONST. | Rajiv | RT Singh | Complete
200 | 2 | 32/6 | DA+6 | DRY |  | 2024-04-22 | 2024-05-02 | Bande Bharat Group |  | Kuntal Debnath | Complete
201 | 3 | 10/9 | DA+3 | DRY |  | 2024-04-28 | 2024-05-02 | Shri Degrai Enterprises |  | Abhijit Dutta | Complete
202 | 4 | 8/7 | DB1+0 | DRY |  | 2024-04-27 | 2024-05-05 | Mateshwari Const. |  | Abhijit Dutta | Complete
203 | 5 | 10/3 | DA+3 | DFR |  | 2024-04-03 | 2024-05-05 | Shri Degrai Enterprises |  | Abhijit Dutta | Complete
204 | 6 | 10/5 | DA+3 | DFR |  | 2024-05-06 | 2024-05-10 | Shri Degrai Enterprises |  | Abhijit Dutta | Complete
205 | 7 | 13/4 | DA+0 | DRY |  | 2024-05-15 | 2024-05-24 | Majisa Construction |  | Jeetu Sachan | Complete
206 | 8 | 15/8 | DA+0 | DRY |  | 2024-05-09 | 2024-05-27 | Brads Infratech |  | Jeetu Sachan | Complete
207 | 9 | 14/1 | DA+3 | DRY |  | 2024-05-15 | 2024-05-28 | Mehai Construction |  | Jeetu Sachan | Complete
June'24
208 | 1 | 14/2 | DA+3 | DRY |  | 2024-05-29 | 2024-06-01 | Mehai Construction |  | Jeetu Sachan | Complete
209 | 2 | 14/3 | DA+0 | DRY |  | 2024-06-01 | 2024-06-04 | Majisa Construction |  | Jeetu Sachan | Complete
210 | 3 | 15/9 | DA+9 | DRY |  | 2024-05-28 | 2024-06-10 | Mehai Construction |  | Jeetu Sachan | Complete
211 | 4 | 16/3 | DA+0 | DRY |  | 2024-05-27 | 2024-06-13 | Vibe Infra |  | Jeetu Sachan | Complete
212 | 5 | 14/4 | DA+0 | DRY |  | 2024-06-06 | 2024-06-13 | Majisa Construction |  | Jeetu Sachan | Complete
213 | 6 | 16/4 | DA+3 | DRY |  | 2024-06-05 | 2024-06-15 | Vibe Infra |  | Jeetu Sachan | Complete
214 | 7 | 25/10 | DA+0 | Sandy |  | 2024-06-06 | 2024-06-19 | Departmental Gang |  | Kuntal Debnath | Complete
215 | 8 | 10/19 | DA+9 | DRY |  | 2024-06-12 | 2024-06-20 | Jai Bhawani Construction |  | Abhijit Dutta | Complete
216 | 9 | 14/5 | DA+0 | DRY |  | 2024-06-16 | 2024-06-22 | Majisa Construction |  | Jeetu Sachan | Complete
217 | 10 | 15/0 | DC2+0 | DRY |  | 2024-06-12 | 2024-06-24 | Mehai Construction |  | Jeetu Sachan | Complete
218 | 11 | 16/5 | DA+3 | DRY |  | 2024-06-17 | 2024-06-25 | Vibe Infra |  | Jeetu Sachan | Complete
219 | 12 | 10/20 | DB1+6 | DFR |  | 2024-06-19 | 2024-06-29 | Jai Bhawani Construction |  | Abhijit Dutta | Complete
220 | 13 | 15/1 | DA+6 | DRY |  | 2024-06-14 | 2024-06-30 | Majisa Construction |  | Jeetu Sachan | Complete
221 | 14 | 16/6 | DA+0 | DRY |  | 2024-06-02 | 2024-06-30 | Vibe Infra |  | Jeetu Sachan | Complete
July'24
222 | 1 | 40/2 | DB1+9 RC | SANDY | 02.07.24 | 07.07.24 | 14.07.24 | Bhati Const. | Rajiv | RT Singh | Complete
223 | 2 | 49/0 | DC1+3 | DFR | 08.07.24 | 16.07.24 | 17.07.24 | Mahadev engg. |  | Shah Ali Khan | Complete
224 | 3 | 50/0 | DC2+3 | DFR | 10.07.24 | 21.07.24 | 22.07.24 | Mahadev engg. |  |  | Complete | 16
225 | 4 | 72/0 | DB1+0 | DRY | 18.07.24 | 25.07.24 | 27.07.24 | Mahadev engg. |  |  | Complete
226 | 5 | 71/2 | DA+0 | DRY | 14.07.24 | 27.07.24 | 28.07.24 | Mahadev engg. |  |  | Complete | 8
227 | 6 | 44/0 | DB1+0 | SANDY | 18.07.24 | 23.07.24 | 28.07.24 | Om Const |  |  | Complete | 20
228 | 7 | 43/6 | DA+6 RC | SANDY | 26.07.24 | 28.07.24 | 31.07.24 | Om Const |  |  | Complete
229 | 8 | 72/6 | DA+0 RC | SANDY | 26.07.24 | 31.07.24 | 31.07.24 | Mahadev engg. |  |  | Complete
230 | 9 | 11/14 | DA+0 | DRY |  | 2024-06-21 | 2024-07-03 | Punia Construction |  | Abhijit Dutta | Complete
231 | 10 | 10/21 | DA+0 | DFR |  | 2024-06-19 | 2024-07-04 | Jai Bhawani Construction |  | Abhijit Dutta | Complete
232 | 11 | 25/9 | DA+6 | DRY |  | 2024-06-16 | 2024-07-07 | Krishna Projects India |  | Kuntal Debnath | Complete
233 | 12 | 16/2 | DA+3 | DRY |  | 2024-07-02 | 2024-07-08 | Vibe Infra |  | Jeetu Sachan | Complete
234 | 13 | 10/18 | DA+0 | DFR |  | 2024-07-03 | 2024-07-16 | Jai Bhawani Construction |  | Abhijit Dutta | Complete
235 | 14 | 25/8 | DA+9+4 | DRY |  | 2024-06-14 | 2024-07-17 | Krishna Projects India |  | Kuntal Debnath | Complete
236 | 15 | 16/1 | DA+3 | DRY |  | 2024-07-14 | 2024-07-21 | J.P. Infra |  | Jeetu Sachan | Complete
237 | 16 | 11/4 | DA+6 | DFR |  | 2024-07-18 | 2024-07-26 | MCI |  | Bipin Kumar | Complete
238 | 17 | 11/11 | DA+0 | Sandy |  | 2024-07-10 | 2024-07-27 | R.K. Construction |  | Bipin Kumar | Complete
239 | 18 | 26/7 | DA+3 | Sandy |  | 2024-06-17 | 2024-07-27 | Company Gangs |  | Kuntal Debnath | Complete
240 | 19 | 17/0 | DC1+0 | DRY |  | 2024-07-10 | 2024-07-30 | Vibe Infra |  | Jeetu Sachan | Complete
241 | 20 | 15/3 | DA+3 | DRY |  | 2024-07-22 | 2024-07-30 | Majisa Construction |  | Jeetu Sachan | Complete
242 | 21 | 10/4 | DA+3 | DFR |  | 2024-07-18 | 2024-07-31 | Jai Bhawani Construction |  | Abhijeet | Complete
Aug'24
243 | 1 | 50/2 | DA+0 | DFR | 01.08.24 | 06.08.24 | 08.08.24 | Bhati Const. |  | RT Sing | Complete
244 | 2 | 69/2 | DA+0 | DRY | 18.07.24 | 04.03.24 | 08.08.24 | Bhati Const. |  | Shyamal Sil | Complete | 6
245 | 3 | 72/7 | DB1+9 RC | SANDY | 31.07.24 | 04.03.24 | 08.08.24 | Mahadev engg. |  | Shyamal Sil | Complete
246 | 4 | 69/3 | DA+0 | Sandy | 14.07.24 | 08.08.24 | 10.08.24 | Bhati Const. |  | Shyamal Sil | Complete
247 | 5 | 42/0 | DC2+9 RC | SANDY | 31.07.24 | 03.08.24 | 11.8.24 | Om Const |  | RT Sing | Complete
248 | 6 | 66/2 | DA+0 | DRY |  | 10.08.24 | 11.8.24 | Shree Shyam Const. |  | Shyamal Sil | Complete
249 | 7 | 69/6 | DA+0 | DRY | 09.08.24 | 11.8.24 | 13.08.24 | Mahadev engg. |  | Shyamal Sil | Complete
250 | 8 | 47/1 | DA+0 | DRY | 27.07.24 | 10.8.24 | 13.08.24 | Bhati Const. |  | RT Sing | Complete
251 | 9 | 68/4 | DA+3 | DRY | 30.07.24 | 12.08.24 | 13.08.24 | Shakti Construction |  | Shyamal Sil | Complete
252 | 10 | 66/1 | DA+3 | DRY | 10.08.24 | 12.08.24 | 13.08.24 | Shree Shyam Const. |  | Shyamal Sil | Complete
253 | 11 | 68/5 | DA+3 | DRY | 09.08.24 | 12.08.24 | 14.08.24 | Shakti Construction |  | Shyamal Sil | Complete
254 | 12 | 69/7 | DA+0 | DRY | 09.08.24 | 13.08.24 | 17.08.24 | Mahadev engg. |  | Shyamal Sil | Complete
255 | 13 | 69/4 | DA+0 | DRY | 15.07.24 | 13.08.24 | 18.01.24 | Bhati Const. |  | Shyamal Sil | Complete
256 | 14 | 67/1 | DB1+9 | DRY | 02.08.24 | 11.8.24 | 19.08.24 | Awadh Const. |  | Shyamal Sil | Complete
257 | 15 | 63/0 | DD45+0 | DRY | 12.08.24 | 21.08.24 | 24.08.24 | Mahadev engg. |  | Shyamal Sil | Complete
258 | 16 | 68/6 | DA+3 | DRY | 11.8.24 | 21.08.24 | 24.08.24 | Shakti Construction |  | Shyamal Sil | Complete
259 | 17 | 50/1 | DA+0 RC | DFR | 13.07.24 | 26.08.24 | 29.08.24 | Mahadev engg. |  | RT Sing | Complete
260 | 18 | 69/5 | DA+0 | DRY | 14.08.24 | 22.08.24 | 29.08.24 | Bhati Const. |  | Shyamal Sil | Complete
261 | 19 | 68/2 | DA+3 | DRY | 19.8.24 | 28.08.24 | 29.08.24 | Shakti Construction |  | Shyamal Sil | Complete
262 | 20 | 43/0 | DB2+9 RC | SANDY | 10.8.24 | 25.08.24 | 30.08.24 | Om Const |  | RT Sing | Complete
263 | 21 | 66/4 | DA+3 | DRY | 02.08.24 | 14.08.24 | 31.08.24 | Shree Shyam Const. |  | Shyamal Sil | Complete
264 | 22 | 11/10 | DB1+0 | DRY |  | 2024-07-27 | 2024-08-04 | R.K. Construction |  | Bipin Kumar | Complete
265 | 23 | 32/8 | DA+9 | Sandy |  | 2024-07-29 | 2024-08-04 | N.R. Enterprises |  | Kuntal Debnath | Complete
266 | 24 | 19/13 | DA+0 | Sandy |  | 2024-07-23 | 2024-08-09 | RBM |  | Jeetu Sachan | Complete
267 | 25 | 11/7 | DA+3 | DRY |  | 2024-08-02 | 2024-08-11 | R.K. Construction |  | Bipin Kumar | Complete
268 | 26 | 11/5 | DA+3 | DRY |  | 2024-07-27 | 2024-08-11 | MCI |  | Bipin Kumar | Complete
269 | 27 | 15/2 | DA+9 | DRY |  | 2024-07-25 | 2024-08-12 | OM Enterprise |  | Jeetu Sachan | Complete
270 | 28 | 19/14 | DA+9+2 | DRY |  | 2024-07-23 | 2024-08-14 | RBM |  | Jeetu Sachan | Complete
271 | 29 | 26/6 | DA+0 | Sandy |  | 2024-07-28 | 2024-08-16 | Departmental Gang |  | Kuntal Debnath | Complete
272 | 30 | 21/2 | DA+3 | DRY |  | 2024-08-10 | 2024-08-21 | RBM |  | Jeetu Sachan | Complete
273 | 31 | 16/0 | DB2+0 | DRY |  | 2024-08-19 | 2024-08-24 | J.P. Infra |  | Jeetu Sachan | Complete
274 | 32 | 21/1 | DA+3 | DRY |  | 2024-08-13 | 2024-08-25 | RBM |  | Jeetu Sachan | Complete
275 | 33 | 10/8 | DA+0 | DRY |  | 2024-08-13 | 2024-08-26 | A.B. Construction |  | Abhijeet Dutta | Complete
276 | 34 | 15/4 | DA+3 | DRY |  | 2024-08-14 | 2024-08-28 | Majisa Construction |  | Jeetu Sachan | Complete
277 | 35 | 21/3 | DA+0 | DRY |  | 2024-08-19 | 2024-08-28 | RBM |  | Jeetu Sachan | Complete
278 | 36 | 11/15 | DA+0 | DRY |  | 2024-08-24 | 2024-08-28 | Punia Construction |  | Abhijeet Dutta | Complete
Sept'24
279 | 1 | 67/0 | DD45+0 | DRY | 14.08.24 | 27.08.24 | 02.09.24 | Awadh Const. |  | Shyamal Sil | Complete
280 | 2 | 69/1 | DA+0 | DRY | 22.08.24 | 01.09.24 | 03.09.24 | Bhati Const. |  | Shyamal Sil | Complete
281 | 3 | 73/0 | DD45+9 | DFR | 31.07.24 | 01.09.24 | 03.09.24 | Mahadev engg. |  | Shyamal Sil | Complete
282 | 4 | 68/1 | DA+3 | DRY | 14.08.24 | 02.09.24 | 04.09.24 | Shakti Construction |  | Shyamal Sil | Complete
283 | 5 | 66/3 | DA+3 | DRY | 13.08.24 | 02.09.24 | 04.09.24 | Shree Shyam Const. |  | Shyamal Sil | Complete
284 | 6 | 35/5 | DA+0 RC | SANDY | 30.08.24 | 03.09.24 | 09.09.24 | Om Const |  | Shyamal Sil | Complete
285 | 7 | 69/0 | DB1+0 | DRY | 20.08.24 | 05.09.24 | 12.09.24 | Bhati Const. |  | Shyamal Sil | Complete
286 | 8 | 35/6 | DA+9 RC | SANDY | 08.09.24 | 11.09.24 | 15.09.24 | Om Const |  |  | Complete | Classification submitted
287 | 9 | 68/3 | DA+0 | DRY | 11.09.24 | 13.09.24 | 15.09.24 | Shakti Construction |  | Shyamal Sil | Complete
288 | 10 | 65/7 | DA+0 | DRY | 18.09.24 | 20.09.24 | 21.09.24 | Shree Shyam Const. |  | Shyamal Sil | Complete
289 | 11 | 35/4 | DA+3 RC | SANDY | 15.09.24 | 19.09.24 | 23.09.24 | Om Const |  | RT Singh | Complete | Classification submitted
290 | 12 | 68/0 | DD45+0 | DRY | 14.09.24 | 18.09.24 | 29.09.24 | Shakti Construction |  | Shyamal Sil | Complete | Today received
291 | 13 | 35/7 | DA+3 RC | SANDY | 19.09.24 | 24.09.24 | 30.09.24 | Om Const |  | RT Singh | Complete | Classification submitted
292 | 14 | 10/11 | DA+0 | DRY |  | 2024-08-16 | 2024-08-31 | A.B. Construction |  | Abhijeet Dutta | Complete
293 | 15 | 11/12 | DA+0+1 | Sandy |  | 2024-08-10 | 2024-08-31 | R.K. Construction |  | Abhijeet Dutta | Complete
294 | 16 | 11/8 | DA+0 | DRY |  | 2024-08-24 | 2024-08-31 | R.K. Construction |  | Abhijeet Dutta | Complete
295 | 17 | 21/4 | DA+9 | DRY |  | 2024-08-15 | 2024-09-01 | RBM |  | Jeetu Sachan | Complete
296 | 18 | 11/9 | DA+3 | DRY |  | 2024-08-30 | 2024-09-06 | R.K. Construction |  | Abhijeet Dutta | Complete
297 | 19 | 19/5 | DA+3 | DRY |  | 2024-08-30 | 2024-09-08 | Om construction Company |  | Jeetu Sachan | Complete
298 | 20 | 21/5 | DA+3 | Sandy |  | 2024-08-30 | 2024-09-10 | RBM |  | Jeetu Sachan | Complete
299 | 21 | 14/0 | DC2+0 | Sandy |  | 2024-09-03 | 2024-09-11 | OM Enterprise |  | Jeetu Sachan | Complete
300 | 22 | 19/6 | DA+3 | DRY |  | 2024-09-05 | 2024-09-12 | Vibe Infra |  | Jeetu Sachan | Complete
301 | 23 | 13/2 | DA+3 | Sandy |  | 2024-09-07 | 2024-09-15 | Punia Construction |  | Jeetu Sachan | Complete
302 | 24 | 21/6 | DA+0 | DRY |  | 2024-09-05 | 2024-09-16 | RBM |  | Jeetu Sachan | Complete
303 | 25 | 19/4 | DA+0 | DRY |  | 2024-09-06 | 2024-09-19 | Om Construction Company |  | Jeetu Sachan | Complete
304 | 26 | 11/6 | DA+3 | DRY |  | 2024-09-12 | 2024-09-20 | R.K. Construction |  | Abhijeet Dutta | Complete
305 | 27 | 13/1 | DA+3 | DRY |  | 2024-09-15 | 2024-09-21 | Punia Construction |  | Abhijeet Dutta | Complete
306 | 28 | 10/22 | DA+0 | Sandy |  | 2024-09-07 | 2024-09-22 | Hadhbuji Construction Company |  | Abhijeet Dutta | Complete
307 | 29 | 21/7 | DB1+0 | DRY |  | 2024-09-13 | 2024-09-23 | RBM |  | Jeetu Sachan | Complete
308 | 30 | 19/3 | DA+6 | DRY |  | 2024-09-06 | 2024-09-25 | Om Construction Company |  | Jeetu Sachan | Complete
309 | 31 | 19/7 | DA+9 | DRY |  | 2024-09-12 | 2024-09-28 | Vibe Infra |  | Jeetu Sachan | Complete
310 | 32 | 15/6 | DA+0 | DRY |  | 2024-09-28 | 2024-09-30 | OM Enterprise |  | Jeetu Sachan | Complete
311 | 33 | 17/1 | DA+3 | DRY |  | 2024-09-19 | 2024-09-30 | Sidhi Vinayak |  | Jeetu Sachan | Complete
Oct'24
312 | 1 | 66/0 | DD45+0 | DRY | 25.09.24 | 28.09.24 | 01.10.24 | Shree Shyam Const. |  | Shyamal Sil | Complete
313 | 2 | 35/8 | DA+0 RC | SANDY | 25.09.24 | 30.09.24 | 03.10.14 | Om Const |  | RT Singh | Complete
314 | 3 | 62/0 | DC2+0 | DRY | 29.09.24 | 01.10.24 | 04.10.24 | Mahadev engg. |  | Shyamal Sil | Complete
315 | 4 | 35/1 | DA+0 RC | SANDY | 04.10.24 | 05.10.24 | 08.10.24 | Om Const |  | RT Singh | Complete
316 | 5 | 35/0 | DB2+0 RC | SANDY | 08.10.24 | 10.10.24 | 17.10.24 | Om Const |  | RT Singh | Complete
317 | 6 | 71/0 | DD60+0 | FS | 19.09.24 | 09.10.24 | 22.10.24 | Mahadev engg. |  | Shyamal Sil | Complete
318 | 7 | 35/2 | DA+0 (RC) | SANDY | 14.10.24 |  | 22.10.24 | Om Const |  | RT Singh | Complete
319 | 8 | 69/9 | DA+0 | DFR | 08.10.24 | 23.10.24 | 24.10.24 | Mahadev engg. |  | Shyamal Sil | Complete
320 | 9 | 64/0 | DB2+0 | DRY | 14.10.24 | 23.10.24 | 25.10.24 | Bhati Const. |  | Shyamal Sil | Complete
321 | 10 | 35/3 | DA+0 (RC) | SANDY | 21.10.24 | 24.10.24 | 29.10.24 | Om Const |  | RT Singh | Complete
322 | 11 | 39/0 | DC2+3 RC | SANDY | 12.10.24 |  | 30.10.24 | Shakti Construction |  | RT Sing | Complete
323 | 12 | 30/3 | DA+6 | Sandy |  | 2024-09-28 | 2024-10-05 | D.R. Construction |  | Kuntal Debnath | Complete
324 | 13 | 11/13 | DA+0 | Sandy |  | 2024-09-25 | 2024-10-07 | R.K. Construction |  | Abhijeet Dutta | Complete
325 | 14 | 17/3 | DA+3 | DRY |  | 2024-09-28 | 2024-10-08 | Vibe Infra |  | Jeetu Sachan | Complete
326 | 15 | 19/2 | DA+3 | DRY |  | 2024-10-06 | 2024-10-11 | Vibe Infra |  | Bipin Kumar | Complete
327 | 16 | 13/0 | DD60+0 | DRY |  | 2024-09-28 | 2024-10-15 | Punia Construction |  | Abhijeet Dutta | Complete
328 | 17 | 19/9 | DA+3 | Sandy |  | 2024-10-12 | 2024-10-20 | Vibe Infra |  | Jeetu Sachan | Complete
329 | 18 | 31/0 | DD45+3 | Sandy |  | 2024-10-06 | 2024-10-20 | D.R. Construction |  | Jeetu Sachan | Complete
330 | 19 | 21/11 | DA+9 | DRY |  | 2024-10-08 | 2024-10-22 | Sidhi Vinayak |  | Bipin Kumar | Complete
Nov'24
331 | 1 | 34/4 | DA+6 RC | SANDY | 29.10.24 | 02.11.24 | 07.11.24 | Om Const |  | RT Singh | Complete
332 | 2 | 38/9 | DB1+6 RC | SANDY | 24.10.24 | 26.10.24 | 09.11.24 | Shakti Construction |  | RT Sing | Complete
333 | 3 | 34/5 | DCT+0 | SANDY | 07.11.24 | 12.11.24 | 15.11.24 | Om Const |  | RT Singh | Complete
334 | 4 | 34/6 | DA+6 RC | SANDY | 14.11.24 | 15.11.24 | 20.11.24 | Om Const |  | RT Singh | Complete
335 | 5 | 41/2 | DA+0 RC | SANDY | 17.11.24 | 18.11.24 | 24.11.24 | Nadeem rasool |  | RT Singh | Complete
336 | 6 | 58/13 | DA+0 | DRY | 14.11.24 | 24.11.24 | 26.11.24 | Bhati Const. |  | Shyamal Sil | Complete
337 | 7 | 41/3 | DA+0 RC | SANDY | 21.11.24 | 22.11.24 | 26.11.24 | Nadeem rasool |  | RT Singh | Complete
338 | 8 | 39/5 | DA+3 RC | SANDY | 23.11.24 | 26.11.24 | 30.11.24 | Meer Construction |  | RT Singh | Complete
339 | 9 | 41/1 | DA+3 RC | SANDY | 25.11.24 | 26.11.24 | 30.11.24 | Nadeem rasool |  | RT Sing | Complete
340 | 10 | 69/8 | DA+0 | DFR | 21.11.24 | 30.11.24 | 30.11.24 | Mahadev engg. |  | Shyamal Sil | Complete | 9
341 | 11 | 13/3 | DA+0 | sandy |  | 2024-10-26 | 2024-11-05 | Punia Construction |  | Jeetu Sachan | Complete
342 | 12 | 2/4 | DA+3 | Sandy |  | 2024-11-16 | 2024-11-20 | Laxmi Enterprises |  | Ashutosh Kumar | Complete
343 | 13 | 24/2 | DA+0 | DRY |  | 2024-11-18 | 2024-11-20 | Parsuram Sahi |  | Kuntal Debnath | Complete
344 | 14 | 27/2 | DA+0 | Sandy |  | 2024-11-07 | 2024-11-24 | prasuram sai |  | Kuntal Debnath | Complete
345 | 15 | 12/0 | DD60+0 | DRY |  | 2024-11-07 | 2024-11-24 | Vibe Infra |  | Ashutosh Kumar | Complete
346 | 16 | 14/6 | DA+0 | DRY |  | 2024-11-11 | 2024-11-25 | Punia Construction |  | Ashutosh Kumar | Complete
Dec'24
347 | 1 | 41/0 | DB1+0 RC | SANDY | 27.11.24 | 27.11.24 | 02.12.24 | Nadeem rasool |  | RT Sing | Complete | 15
348 | 2 | 34/3 | DA+9 RC | SANDY | 23.11.24 | 27.11.24 | 04.12.24 | Om Const |  | RT Singh | Complete | 13
349 | 3 | 64/8 | DA+0 | DRY | 25.11.24 | 04.12.24 | 05.12.24 | Bhati Const. |  | Shyamal Sil | Complete
350 | 4 | 39/6 | DA+0 RC | SANDY | 25.11.24 | 01.12.24 | 06.12.24 | Meer Construction |  | RT Singh | Complete | 15
351 | 5 | 40/7 | DA+3 RC | SANDY | 30.11.24 | 01.12.24 | 06.12.24 | Tantray Construction |  | RT Sing | Complete
352 | 6 | 40/12 | DA+0 RC | SANDY | 02.12.24 | 02.12.24 | 08.12.24 | Nadeem rasool |  | RT Sing | Complete
353 | 7 | 64/7 | DA+3 | DRY | 26.11.24 | 07.12.24 | 08.12.24 | Bhati Const. |  | Shyamal Sil | Complete | Pit colaps
354 | 8 | 64/4 | DA+3 | DRY | 28.11.24 | 08.12.24 | 09.12.24 | Tantray Construction |  | Shyamal Sil | Complete
355 | 9 | 39/7 | DA+0 RC | SANDY | 04.12.24 | 07.12.24 | 09.12.24 | Meer Construction |  | RT Singh | Complete
356 | 10 | 37/8 | DA+0 | SANDY | 07.12.24 | 07.12.24 | 09.12.24 | Nadeem rasool |  | RT Sing | Complete |  | 38/0
357 | 11 | 64/6 | DA+3 | DRY | 06.12.24 | 09.12.24 | 10.12.24 | Bhati Const. |  | Shyamal Sil | Complete
358 | 12 | 64/5 | DA+3 | DRY | 27.11.24 | 10.12.24 | 11.12.24 | Tantray Construction |  | Shyamal Sil | Complete | 20
359 | 13 | 40/9 | DA+0 RC | SANDY | 22.11.24 | 25.11.24 | 12.12.24 | Tantray Construction |  | RT Singh | Complete | 15
360 | 14 | 37/7 | DA+3 RC | SANDY | 07.12.24 | 09.12.24 | 12.12.24 | Iqbal |  | RT Singh | Complete
361 | 15 | 34/2 | DA+9 RC | SANDY | 03.12.24 | 07.12.24 | 13.12.24 | Om Const |  | RT Singh | Complete
362 | 16 | 64/3 | DA+0 | DRY | 05.12.24 | 12.12.24 | 13.12.24 | Tantray Construction |  | Shyamal Sil | Complete
363 | 17 | 64/1 | DA+6 | DRY | 27.11.24 | 13.12.24 | 14.12.24 | Bhati Const. |  | Shyamal Sil | Complete | 17
364 | 18 | 70/0 | DD60+0 | FS | 09.11.24 | 06.12.24 | 14.12.24 | Mahadev engg. |  | Shyamal Sil | Complete | 12
365 | 19 | 64/2 | DA+0 | DRY | 06.12.24 | 13.12.24 | 15.12.24 | Tantray Construction |  | Shyamal Sil | Complete
366 | 20 | 37/6 | DA+6 RC | SANDY | 12.12.24 | 12.12.24 | 15.12.24 | Iqbal |  | RT Singh | Complete
367 | 21 | 64/9 | DA+0 | DRY | 23.11.24 | 15.12.24 | 16.12.24 | Bhati Const. |  | Shyamal Sil | Complete
368 | 22 | 40/8 | DA+0 RC | SANDY | 12.12.24 | 12.12.24 | 16.12.24 | Tantray Construction |  | RT Singh | Complete
369 | 23 | 37/5 | DA+3 RC | SANDY | 14.12.24 | 15.12.24 | 18.12.24 | Iqbal |  | RT Singh | Complete
370 | 24 | 34/1 | DA+3 RC | SANDY | 13.12.24 | 14.12.24 | 20.12.24 | Om Const |  | RT Singh | Complete | Umesh
371 | 25 | 63/3 | DA+3 | DRY | 15.12.24 | 19.12.24 | 20.12.24 | Bhati Const. |  | Shyamal Sil | Complete
372 | 26 | 40/0 | DC2+0 RC | SANDY | 09.12.24 | 10.12.24 | 21.12.24 | Meer Construction |  | RT Singh | Complete | Rajiv Ji
373 | 27 | 40/1 | DA+0 RC | SANDY | 16.12.24 | 17.12.24 | 22.12.24 | Meer Construction |  | RT Singh | Complete |  | 39/2
374 | 28 | 38/0 | DC1+0 | SANDY | 18.12.24 | 19.12.24 | 23.12.24 | Nadeem rasool |  | RT Singh | Complete | Samiul | 38/4,5,7
375 | 29 | 63/4 | DA+0 | DRY | 17.12.24 | 24.12.24 | 25.12.24 | Bhati Const. |  | Shyamal Sil | Complete | sand
376 | 30 | 39/2 | DA+0 RC | SANDY | 22.12.24 | 23.12.24 | 25.12.24 | Meer Construction |  | RT Singh | Complete
377 | 31 | 59/4 | DA+0 | DRY | 20.12.24 | 27.12.24 | 28.12.24 | Bhati Const. |  | Shyamal Sil | Complete | 6
378 | 32 | 38/4 | DA+0 RC | SANDY | 23.12.24 | 24.12.24 | 28.12.24 | Iqbal |  | RT Singh | Complete | 4
379 | 33 | 34/0 | DB1+6 RC | SANDY | 19.12.24 | 21.12.24 | 28.12.24 | Om Const |  | RT Singh | Complete | 5 | 15
380 | 34 | 38/5 | DA+0 RC | SANDY | 25.12.25 | 26.12.24 | 30.12.24 | Iqbal |  | RT Singh | Complete | 3
381 | 35 | 63/1 | DA+6 | DRY | 21.12.24 | 30.12.24 | 31.12.24 | Bhati Const. |  | Shyamal Sil | Complete | 7
382 | 36 | 38/7 | DA+0 RC | SANDY | 28.12.24 | 29.12.24 | 31.12.24 | Iqbal |  | RT Singh | Complete
383 | 37 | 24/1 | #REF! | DRY |  | 2024-11-29 | 2024-12-04 | prasuram sai |  | Kuntal Debnath | Complete
384 | 38 | 15/7 | #REF! | DRY |  | 2024-12-04 | 2024-12-07 | Punia Construction |  | Jitendra Yadav | Complete
385 | 39 | 2/5 | #REF! | Sandy |  | 2024-11-07 | 2024-12-08 | Sri Nagana ray Enterprise |  | Jitendra Yadav | Complete
386 | 40 | 25/6 | #REF! | DRY |  | 2024-12-05 | 2024-12-08 | prasuram sai |  | Kuntal Debnath | Complete
387 | 41 | 2/3 | #REF! | Sandy |  | 2024-12-05 | 2024-12-10 | Laxmi Enterprises |  | Jitendra Yadav | Complete
388 | 42 | 6/1 | #REF! | DFR |  | 2024-12-05 | 2024-12-10 | HS Engineering |  | Jitendra Yadav | Complete
389 | 43 | 25/5 | #REF! | Sandy |  | 2024-12-11 | 2024-12-16 | prasuram sai |  | Kuntal Debnath | Complete
390 | 44 | 24/6 | #REF! | DRY |  | 2024-12-14 | 2024-12-16 | Vishwakarma Construction |  | Kuntal Debnath | Complete
391 | 45 | 24/5 | #REF! | Sandy |  | 2024-12-16 | 2024-12-18 | Vishwakarma Construction |  | Kuntal Debnath | Complete
392 | 46 | 2/2 | #REF! | Sandy |  | 2024-12-14 | 2024-12-19 | Laxmi Enterprises |  | Jitendra Yadav | Complete
393 | 47 | 24/4 | #REF! | DRY |  | 2024-12-19 | 2024-12-20 | Vishwakarma Construction |  | Kuntal Debnath | Complete
394 | 48 | 27/3 | #REF! | Sandy |  | 2024-12-10 | 2024-12-20 | Prasuram sai |  | Kuntal Debnath | Complete
395 | 49 | 25/11 | #REF! | DRY |  | 2024-12-22 | 2024-12-23 | YMK Construction |  | Kuntal Debnath | Complete
396 | 50 | 24/0 | #REF! | DRY |  | 2024-12-19 | 2024-12-24 | Vishwakarma Construction |  | Kuntal Debnath | Complete
397 | 51 | 21/13 | #REF! | DRY |  | 2024-12-19 | 2024-12-26 | JSR Infrastructure |  | Bipin Kumar | Complete
398 | 52 | 23/11 | #REF! | Sandy |  | 2024-12-19 | 2024-12-27 | Vishwakarma Construction |  | Kuntal Debnath | Complete
399 | 53 | 23/10 | #REF! | DFR |  | 2024-12-23 | 2024-12-28 | Vishwakarma Construction |  | Kuntal Debnath | Complete
400 | 54 | 26/0 | #REF! | DRY |  | 2024-12-23 | 2024-12-28 | YMK Construction |  | Kuntal Debnath | Complete
401 | 55 | 27/0 | #REF! | Sandy |  | 2024-12-15 | 2024-12-29 | D.R. Construction |  | Kuntal Debnath | Complete
402 | 56 | 23/8 | #REF! | Sandy |  | 2024-12-25 | 2024-12-31 | Vishwakarma Construction |  | Bipin Kumar | Complete
Jan'25
403 | 1 | 33/8 | DA+3 RC | SANDY | 27.12.24 | 30.12.24 | 04.01.25 | Om Const |  | RT Singh | Complete
404 | 2 | 60/0 | DC2+3 | DRY | 27.12.24 | 04.01.25 | 06.01.25 | Bhati Const. |  | Shyamal Sil | Complete
405 | 3 | 33/7 | DA+9 RC | SANDY | 04.01.25 | 06.01.25 | 09.01.25 | Om Const |  | RT Singh | Complete
406 | 4 | 61/0 | DB1+6 | DRY | 03.01.25 | 07.01.25 | 10.01.25 | Bhati Const. |  | Shyamal Sil | Complete
407 | 5 | 2/1 | #REF! | Sandy |  | 2024-12-25 | 2025-01-01 | Laxmi Enterprises |  | Sumit | Complete
408 | 6 | 2/6 | #REF! | Sandy |  | 2024-12-25 | 2025-01-02 | Naganaray Enterprise |  | Sumit | Complete
409 | 7 | 8/9 | #REF! | DFR |  | 2024-12-27 | 2025-01-04 | JSR Infrastructure |  | Sumit | Complete
410 | 8 | 26/2 | #REF! | Sandy |  | 2024-12-28 | 2025-01-04 | YMK Construction |  | Kuntal Debnath | Complete
411 | 9 | 23/7 | #REF! | DFR |  | 2024-12-28 | 2025-01-05 | Vishwakarma Construction |  | Bipin Kumar | Complete
412 | 10 | 26/3 | #REF! | Sandy |  | 2025-01-02 | 2025-01-07 | YMK Construction |  | Kuntal Debnath | Complete
413 | 11 | 25/0 | #REF! | Sandy |  | 2025-01-02 | 2025-01-08 | Vishwakarma Construction |  | Bipin Kumar | Complete
414 | 12 | 25/1 | #REF! | Sandy |  | 2025-01-05 | 2025-01-11 | Vishwakarma Construction |  | Bipin Kumar | Complete
415 | 13 | 25/3 | #REF! | DRY |  | 2025-01-07 | 2025-01-13 | Vishwakarma Construction |  | Bipin Kumar | Complete
416 | 14 | 27/1 | #REF! | Sandy |  | 2024-12-31 | 2025-01-16 | D.R. Construction |  | Kuntal Debnath | Complete
417 | 15 | 25/4 | #REF! | Sandy |  | 2025-01-09 | 2025-01-17 | Vishwakarma Construction |  | Bipin Kumar | Complete
418 | 16 | 25/7 | #REF! | Sandy |  | 2025-01-12 | 2025-01-22 | Vishwakarma Construction |  | Bipin Kumar | Complete
419 | 17 | 26/5 | #REF! | Sandy |  | 2025-01-13 | 2025-01-22 | YMK Construction |  | Kuntal Debnath | Complete
420 | 18 | 1A/0 | #REF! | DFR |  | 2025-01-15 | 2025-01-24 | JSR Infrastructure |  | Sumit | Complete
421 | 19 | 22/7 | #REF! | DFR |  | 2025-01-18 | 2025-01-28 | D.R. Construction |  | Bipin Kumar | Complete
422 | 20 | 1A/3 | #REF! | Sandy |  | 2025-01-24 | 2025-01-30 | Naganaray Enterprise |  | Sumit | Complete
Feb'25
423 | 1 | 37/1 | DB1+9 RC | SANDY | 23.01.25 | 27.01.25 | 02.02.25 | Om Const |  | RT Singh | Complete
424 | 2 | 33/0 | DB2+3 RC | SANDY | 29.01.25 | 30.01.25 | 03.02.25 | Nadeem rasool |  | RT Singh | Complete
425 | 3 | 44/5 | DA+6 | WFR | 28.01.25 | 31.01.25 | 04.02.25 | Bhati Const. |  | RT Singh | Complete
426 | 4 | 35/9 | DA+3 RC | SANDY | 01.02.25 | 04..02.25 | 07.02.25 | Om Const |  | RT Singh | Complete
427 | 5 | 33/3 | DA+0 (RC) | SANDY | 01.02.25 | 02.02.25 | 07.02.25 | Tantray Construction |  | RT Singh | Complete
428 | 6 | 33/2 | DA+0 RC | SANDY | 03.02.25 | 05.02.25 | 10.2.25 | Iqbal |  | RT Singh | Complete
429 | 7 | 33/4 | DA+0 (RC) | SANDY | 05.02.25 | 08.02.25 | 13.02.25 | Tantray Construction |  | RT Singh | Complete
430 | 8 | 33/6 | DA+6 RC | SANDY | 04.02.25 | 05.02.25 | 14.02.25 | Iqbal |  | RT Singh | Complete
431 | 9 | 46/1 | DA+6 RC | SANDY | 06.02.25 | 10.02.25 | 14.02.25 | Bhati Const. |  | RT Singh | Complete
432 | 10 | 33/5 | DA+0 | SANDY | 11.02.25 | 13.01.25 | 15.02.25 | Tantray Construction |  | RT Singh | Complete
433 | 11 | 2/0 | #REF! | DRY |  | 2025-01-21 | 2025-02-05 | Laxmi Enterprises |  | Sumit | Complete
434 | 12 | 1A/5 | #REF! | Sandy |  | 2025-02-04 | 2025-02-12 | Laxmi Enterprises |  | Sumit | Complete
435 | 13 | 1A/1 | #REF! | DRY |  | 2025-02-01 | 2025-02-14 | JSR Infrastructure |  | Sumit | Complete
436 | 14 | 1A/2 | #REF! | DRY |  | 2025-02-06 | 2025-02-15 | JSR Infrastructure |  | Sumit | Complete
437 | 15 | 1A/4 | #REF! | DRY |  | 2025-02-17 | 2025-02-23 | Naganaray Enterprise |  | Sumit | Complete
438 | 16 | 1/0 | #REF! | DRY |  | 2025-02-18 | 2025-02-26 | JSR Infrastructure |  | Sumit | Complete
439 | 17 | 1A/6 | #REF! | SANDY |  | 2025-02-16 | 2025-02-27 | Laxmi Enterprises |  | Sumit | Complete
440 | 18 | 26/1 | #REF! | SANDY |  | 2025-02-19 | 2025-02-25 | YMK Construction |  | Kuntal Debnath | Complete
Mar'25
441 | 1 | 45/0 | DD60+25 RC | SANDY | 18.02.25 | 01.03.25 | 08.03.25 | Bhati Const. | Ganesh Ji | RT Singh | Complete
442 | 2 | 37/0 | DD60+25 RC | SANDY | 26.02.25 | 03.03.25 | 17.03.25 | OM Const | Umesh, Nayak , Manikant | RT Singh | Complete
443 | 3 | 46/0 | DD60+25 RC | SANDY | 06.3.25 | 09.03.25 | 19.03.25 | Bhati Const. |  | RT Singh | Complete
444 | 4 | 36/0 | DD60+25 RC | SANDY | 10.03.25 | 18.03.25 | 26.03.25 | OM Const |  | RT Singh | Complete
445 | 5 | 65/0 | DB2+3 | SANDY | 18.10.24 | 25.03.25 | 27.03.25 | Bhati Const. |  | Shyamal Sil | Complete | ROW since - 10.10.24 to 08.03.25
446 | 6 | 2/9 | #REF! | DRY |  | 2025-03-04 | 2025-03-11 | JSR |  | Sumit | Complete
447 | 7 | 28/2 | #REF! | SANDY |  | 2025-02-21 | 2025-03-12 | Parsuram Sahi |  | Kuntal Debnath | Complete
448 | 8 | 23/6 | #REF! | DFR |  | 2025-03-08 | 2025-03-13 | Vishwakarma Construction |  | Bipin Kumar | Complete
449 | 9 | 23/0 | #REF! | SANDY |  | 2025-03-13 | 2025-03-19 | Vishwakarma Construction |  | Bipin Kumar | Complete
450 | 10 | 22/6 | #REF! | SANDY |  | 2025-03-17 | 2025-03-22 | Vishwakarma Construction |  | Bipin Kumar | Complete
451 | 11 | 28/9 | #REF! | Sandy |  |  | 2025-03-27 | Vishwakarma Construction |  | Bipin Kumar | Complete
452 | 12 | 21/14 | #REF! | DFR |  | 2025-03-20 | 2025-03-27 | JSR |  | Bipin Kumar | Complete
453 | 13 | 2/7 | #REF! | Sandy |  | 2025-03-18 | 2025-03-31 | JSR |  | Sumit | Complete
April'25
454 | 1 | 29/2 | #REF! | Sandy | 31.03.25 | 02.04.25 | 2025-04-06 | Vishwakarma Construction |  | Kuntal Debnath | Complete
455 | 2 | 29/4 | #REF! | DRY | 04.04.25 | 08.04.25 | 2025-04-08 | Vishwakarma Construction |  | Kuntal Debnath | Complete
456 | 3 | 28/8 | DA+3 | SANDY | 31.03.25 | 02.04.25 | 04.04.25 | Vishwakarma Construction |  | Bipin Kumar | Complete
457 | 4 | 4/0 | DD60+6 | DRY | 2025-03-13 |  | 12.04.25 | JSR |  | Sumit | Complete | 11
458 | 5 | 29/1 | DA+6 RC | Sandy | 15.04.25 | 16.04.25 | 18.04.25 | Vishwakarma Construction |  | Kuntal Debnath | Complete
459 | 6 | 4/1 | DA+0 | DRY | 21.04.25 | 26.04.25 | 27.04.25 | JSR |  | Sumit | Complete
May'25
460 | 1 | 22/1 | DA+0 | DFR | 23.04.25 | 29.04.25 | 04.05.25 | YMK Construction | Kuntal Debnath |  | Complete
461 | 2 | 1A/7 | DA+3 | Sandy | 2025-03-30 |  | 08.05.25 | JSR |  | Sumit | Complete | Flori breakdown | 6
462 | 3 | 29/0 | DB2+0 | Sandy | 03.05.25 | 10.05.25 | 13.05.25 | Vishwakarma Construction |  | Kuntal Debnath | Complete | 24
463 | 4 | 4/3 | DA+0 | DRY | 08.05.25 | 20.05.25 | 23.05.25 | Nice security & Service |  | Sumit | Complete | 7
464 | 5 | 3/0 | DD60+3 | DRY | 2025-03-30 | 23.04.25 | 25.05.25 | JSR |  | Sumit | Complete | 18
465 | 6 | 15/5 | DA+3 | DFR | 15.05.25 | 23.04.25 | 29.05.25 | BR const. |  | Vivek sukla | Complete | 10
466 | 7 | 17/4 | DA+3 | DFR | 15.05.25 | 26.05.25 | 30.05.25 | Shree Ram Enterprises |  | Vivek sukla | Complete | 11
467 | 8 | 22/3 | DA+3 | DFR | 17.04.25 | 30.05.25 | 31.05.25 | YMK Construction |  | Kuntal Debnath | Complete | 16
June'25
468 | 1 | 17/5 | DA+3 | DRY | 23.04.25 | 31.05.25 | 02.06.25 | Shree Ram Enterprises |  | Vivek sukla | Complete
469 | 2 | 2/8 | DA+0 | Sandy |  | 31.05.25 | 03.06.25 | JSR |  | Sumit | Complete
470 | 3 | 11/3 | DA+9 | Sandy | 31.05.25 | 08.06.25 | 10.06.25 | BR const. |  | Vivek sukla | Complete | 10
471 | 4 | 10/0 | DD60+18 | DRY | 15.05.25 | 03.06.25 | 10.06.25 | Bhati Const. |  | Sumit | Complete | 6 |  | 25/2,24/9,4
472 | 5 | 28/3 | DA+0 RC | Sandy | 29.05.25 | 08.06.25 | 11.06.25 | Vishwakarma Construction |  | Kuntal Debnath | Complete | 24
473 | 6 | 5/0 | DB1+9 RC | DRY | 16.05.25 | 02.06.25 | 13.06.25 | Nice security & Service |  | Sumit | Complete | 9
474 | 7 | 28/4 | DA+9 RC | Sandy |  | 15.06.25 | 18.06.25 | Vishwakarma Construction |  | Kuntal Debnath | Complete
475 | 8 | 22/0 | DC2+9 | DFR | 30.04.25 | 14.06.25 | 19.06.25 | YMK Construction |  | Kuntal Debnath | Complete | 16
476 | 9 | 28/5 | DA+9 | SANDY |  | 22.06.25 | 26.06.25 | Vishwakarma Construction |  | Kuntal Debnath | Complete | 30 | Rahul Sharma
477 | 10 | 4/4 | DA+0 | DRY |  | 18.06.25 | 27.06.25 | Nice security & Service |  | Sumit | Complete | 12 | Vaibhav
478 | 11 | 11/2 | DA+9 | Sandy | 14.06.25 | 21.06.25 | 27.06.25 | BR const. |  | Sumit | Complete | 20
2025-07-25
479 | 1 | 25/2 | DA+0 | DRY |  | 22.06.25 | 03.07.25 | Rabit Brite |  | Kuntal Debnath | Complete
480 | 2 | 28/6 | DA+9 RC | SANDY | 27.06.25 | 01.07.25 | 05.07.25 | Vishwakarma Construction |  | Sil | Complete | 30
481 | 3 | 23/4 | DA+3 | DFR | 03.06.25 | 22.06.25 | 05.07.25 | Rabit Brite/YMK |  | Kuntal Debnath | Complete | 15 | Pritish Pradhan
482 | 4 | 8/2 | DA+3 | DRY | 17.06.25 | 02.07.25 | 05.07.25 | Dhakad Enter. |  |  | Complete | 10
483 | 5 | 18/1 | DA+0 | DRY | 30.06.25 | 04.05.25 | 07.07.25 | Vishwakarma Construction |  | Vivek sukla | Complete
484 | 6 | 21/0 | DD45+3 | DRY | 06.06.25 | 01.07.25 | 08.07.25 | Shree Ram Enterprises |  | Vivek sukla | Complete | 11 | Rahjiv Kumar
485 | 7 | 20/0 | DD45+3 RC | DRY | 13.06.25 | 08.07.25 | 13.07.25 | Shree Ram Enterprises |  | Vivek sukla | Complete
486 | 8 | 18/0 | DB2+0 | SANDY |  | 09.07.25 | 14.07.25 | MR Choudary |  | Vivek sukla | Complete | 7
487 | 9 | 18/2 | DA+3 | DRY |  | 14.07.25 | 17.07.25 | Vishwakarma Construction |  |  | Complete
488 | 10 | 9/0 | DD60+18 | DRY |  | 07.07.25 | 17.07.25 | JSR |  |  | Complete
489 | 11 | 8/12 | DA+0 | DRY | 04.07.26 | 07.07.25 | 17.07.25 | JSR |  |  | Complete
490 | 12 | 28/7 | DA+0 | Sandy | 14.07.25 | 15.07.25 | 18.07.25 | Vishwakarma Construction |  |  | Complete
491 | 13 | 18/3 | DA+3 | DRY |  | 18.07.25 | 20.07.25 | Vishwakarma Construction |  |  | Complete
492 | 14 | 8/0 | DA+3 | DRY | 04.07.26 | 15.07.25 | 23.07.25 | Dhakad Enter. |  |  | Complete
493 | 15 | 18/8 | DA+3 | DRY | 04.07.26 | 18.07.25 | 25.07.25 | MR Choudary |  |  | Complete
494 | 16 | 18/9 | DA+0 | DRY |  |  | 26.07.25 | MR Choudary |  |  | Complete
495 | 17 | 8/5 | DA+3 | DRY | 17.06.25 | 23.07.25 | 28.07.25 | Yes Infra |  | Sumit | Complete |  | Vaibhav
496 | 18 | 8/4 | DA+0 | DRY | 14.06.25 | 23.07.25 | 29.07.25 | JSR |  | Sumit | Complete |  | Pradep
497 | 19 | 10/1 | DA+3 | DRY | 20.07.25 |  | 31.07.25 | JSR |  |  | Complete |  | Vaibhav
498 | 20 | 6/0 | DB2+9 | DRY | 04.07.26 | 08.07.25 | 31.07.25 | Nice security & Service |  |  | 3 pit done & 1 pit RC wip |  | 4 |  | PKG-F 6/0
2025-08-25
499 | 1 | 19/0 | DC1+0 | DFR |  | 29.07.25 | 02.08.25 | MR Choudary |  |  | Complete
500 | 2 | 11/1 | DA+6 | SANDY | 18.06.25 | 10.08.25 | 14.08.25 | Chandrapal (Om const.) |  | Sumit | Complete | 15 | Pradeep
501 | 3 | 10/17 | DA+3 | DRY | 08.08.25 | 16.08.25 | 18.08.25 | JSR |  | Sumit | Complete | Chandra bhan
502 | 4 | 23/9 | DA+6 | DRY | 16.08.25 | 18.08.25 | 19.08.25 | YMK Construction |  | S K Sil | Complete | 20 | Vaibhav |  |  | 19/14 | Final checking
503 | 5 | 18/4 | DA+3 | Sandy | 20.08.25 | 23.08.25 | 24.08.25 | Vishwakarma Construction |  |  | Complete
504 | 6 | 18/6 | DA+3 | DRY | 23.08.25 | 26.08.25 | 27.08.25 | Vishwakarma Construction |  |  | Complete
505 | 7 | 18/5 | DA+3 | DRY | 27.08.25 | 28.08.25 | 31.08.25 | Vishwakarma Construction |  | Rajiv | Complete
2025-09-25
506 | 1 | 10/16 | DA+3 | DRY | 29.08.25 | 30.08.25 | 01.09.25 | JSR |  |  | Complete
507 | 2 | 18/10 | DA+3 | SANDY |  | 31.08.25 | 02.09.25 | Vishwakarma Construction |  | Rajiv | Complete
508 | 3 | 11/0 | DB1+0 | Sandy | 24.08.25 | 25.08.25 | 05.09.25 | Om Const |  | Sumit | Complete | Pradeep Kumar
509 | 4 | 19/1 | DA+6 | DRY | 03.09.25 | 06.09.25 | 10.09.25 | Vishwakarma Construction |  | Rajiv | Complete
510 | 5 | 10/15 | DA+3 | DRY | 28.08.25 | 12.09.25 | 14.09.25 | JSR |  | Sumit | Complete | Vaibhav Sharma
511 | 6 | 18/7 | DA+6 | DRY | 18.09.25 | 20.09.25 | 22.09.25 | Vishwakarma Construction |  | Rajiv | Complete
512 | 7 | 7/0 | DB1+0 | DRY |  | 17.09.25 | 22.09.25 | Dhakad Enter. |  |  | Complete
513 | 8 | 4/2 | DA+0 | DRY |  | 18.06.25 | 27.09.25 | JSR |  | Sumit | Foundation completed (ROW period 26 days ) |  |  | 4th pit work done by dhakad interprises
2025-10-25
514 | 1 | 10/23 | DA+9 | Sandy | 22.09.25 | 26.09.25 | 04.10.25 | Om Const |  | Sumit | Complete
515 | 2 | 19/8 | DB1+6 | DRY | 03.10.25 | 05.10.25 | 07.10.25 | Vishwakarma |  |  | Complete
516 | 3 | 19/10 | DA+9 | SANDY | 1.10.25 | 03.13.25 | 10.10.25 | Vishwakarma |  |  | Complete
517 | 4 | 8/3 | DA+3 | DRY | 04.10.25 | 08.10.25 | 13.10.25 | JSR |  | Sumit | Complete
518 | 5 | 17/2 | DA+3 | DRY | 13.10.25 | 15.10.25 | 16.10.25 | Vishwakarma |  |  | Complete
519 | 6 | 19/11 | DA+9 RC | SANDY | 24.05.25 | 21.10.25 | 25.10.25 | Vishwakarma Construction |  | Vivek sukla | work stopped due to ROW resolve on 03.10.25. & Complete
520 | 7 | 19/12 | DB1+3 | SANDY | 18.11.25 | 19.11.25 | 13.12.25 | Vishwakarma Construction |  | Vivek sukla | Complete | 25
Feb'26
521 | 1 | 10/2 | DA+0 | DFR | 01.02.26 | 06.02.26 | 07.02.26 | JSR |  |  | Complete

## Earthing (PKG-G)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Earthing
Cum S No | Sl. No. | Location No. | Tower Type | Classification | Type of Earthing | Earthing | Name of Sub-Contractor | Check list
2023-08-01
1 | 1 | 58/1 | DA+0 | DRY | Pipe Type | 16.08.23 | Mahadev engg. | Check list submitted
2 | 2 | 58/11 | DA+3 | DRY | Pipe Type | 20.08.23 | Mahadev engg. | Check list submitted
3 | 3 | 58/3 | DA+3 | DRY | Pipe Type | 24.8.23 | Mahadev engg. | Check list submitted
4 | 4 | 58/5 | DA+3 | DRY | Pipe Type | 24.8.23 | Mahadev engg. | Check list submitted
5 | 5 | 57/10 | DA+0 | DRY | Pipe Type | 24.8.23 | Manoj Sharma | Check list submitted
6 | 6 | 57/13 | DA+0 | DRY | Pipe Type | 24.8.23 | Manoj Sharma | Check list submitted
7 | 7 | 57/11 | DA+0 | DRY | Pipe Type | 24.8.23 | Manoj Sharma | Check list submitted
8 | 8 | 57/12 | DA+3 | DRY | Pipe Type | 24.8.23 | Manoj Sharma | Check list submitted
9 | 9 | 58/6 | DA+3 | DRY | Pipe Type | 24.8.23 | Mahadev engg. | Check list submitted
10 | 10 | 57/8 | DA+3 | DRY | Pipe Type | 25.08.23 | Manoj Sharma | Check list submitted
11 | 11 | 52/2 | DA+3 | DFR | Counter Poise | 25.08.23 | Khewanjrai Electrical | Check list submitted
12 | 12 | 57/9 | DA+0 | DRY | Pipe Type | 25.08.23 | Manoj Sharma | Check list submitted
13 | 13 | 58/15 | DA+3 | DRY | Pipe Type | 26.08.23 | Mahadev engg. | Check list submitted
14 | 14 | 58/10 | DA+3 | DRY | Pipe Type | 26.08.23 | Mahadev engg. | Check list submitted
15 | 15 | 58/9 | DA+0 | DRY | Pipe Type | 26.08.23 | Mahadev engg. | Check list submitted
16 | 16 | 58/16 | DA+0 | DRY | Pipe Type | 29.08.23 | Mahadev engg. | Check list submitted
17 | 17 | 52/1 | DA+0 | DFR | Counter Poise | 31.08.23 | Khewanjrai Electrical | Check list submitted
18 | 18 | 58/12 | DA+0 | DRY | Pipe Type | 31.08.23 | Mahadev engg. | Check list submitted
19 | 19 | 51/4 | DA+3 | DFR | Counter Poise | 31.08.23 | B S Electrical | Check list submitted
20 | 20 | 58/8 | DA+0 | DRY | Pipe Type | 31.08.23 | Mahadev engg. | Check list submitted
21 | 21 | 51/3 | DA+0 | DFR | Counter Poise | 31.08.23 | B S Electrical | Check list submitted
22 | 22 | 52/4 | DA+0 | DFR | Counter Poise | 31.08.23 | Khewanjrai Electrical | Check list submitted
2023-09-01
23 | 1 | 61/1 | DA+0 | DRY | Pipe Type | 03.09.2023 | Mahadev engg. | Check list submitted
24 | 2 | 59/5 | DA+0 | DRY | Pipe Type | 05.09.23 | Mahadev engg. | Check list submitted
25 | 3 | 61/2 | DA+0 | DRY | Pipe Type | 06.09.23 | Mahadev engg. | Check list submitted
26 | 4 | 58/2 | DA+0 | DRY | Pipe Type | 10.09.23 | Mahadev engg. | Check list submitted
27 | 5 | 59/1 | DA+0 | DRY | Pipe Type | 10.09.23 | Manoj Sharma | Check list submitted
28 | 6 | 59/3 | DA+0 | DRY | Pipe Type | 10.09.23 | Manoj Sharma | Check list submitted
29 | 7 | 59/2 | DA+0 | DRY | Pipe Type | 10.09.23 | Manoj Sharma | Check list submitted
30 | 8 | 59/6 | DA+0 | DRY | Pipe Type | 10.09.23 | Manoj Sharma | Check list submitted
31 | 9 | 53/3 | DA+3 | DRY | Pipe Type | 12.09.23 | Vaishali Const | Check list submitted
32 | 10 | 53/4 | DA+3 | DRY | Pipe Type | 12.09.23 | Vaishali Const | Check list submitted
33 | 11 | 47/3 | DA+0 | DFR | Counter Poise | 18.09.23 | B S Electrical | received
34 | 12 | 47/2 | DA+0 | DFR | Counter Poise | 18.09.23 | B S Electrical | received
35 | 13 | 51/10 | DA+3 | DFR | Counter Poise | 19.09.23 | Nurul Amin | received
36 | 14 | 55/2 | DA+3 | DFR | Counter Poise | 20.09.23 | Amirul Islam | Not received
37 | 15 | 48/1 | DA+0 | DRY | Pipe Type | 21.09.23 | Shri Bhadariyarai Enterprises | received
38 | 16 | 50/4 | DA+3 | DRY | Pipe Type | 21.09.23 | Shri Bhadariyarai Enterprises | received
39 | 17 | 48/2 | DA+3 | DRY | Pipe Type | 22.09.23 | Shri Bhadariyarai Enterprises | received
40 | 18 | 52/5 | DA+3 | DRY | Pipe Type | 23.09.23 | Nurul Amin | received
41 | 19 | 55/3 | DA+0 | DFR | Counter Poise | 24.09.23 | Amirul Islam | Not received
42 | 20 | 56/3 | DA+0 | DFR | Counter Poise | 25.9.23 | Vaishali Const | Not received
43 | 21 | 43/4 | DA+9 | DRY | Pipe Type | 25.09.23 | Shakti Construction | Not received
44 | 22 | 56/6 | DA+3 | DRY | Pipe Type | 26.09.23 | Manoj Sharma | Not received
45 | 23 | 56/7 | DA+3 | DRY | Pipe Type | 26.09.23 | Manoj Sharma | Not received
46 | 24 | 55/4 | DA+3 | DFR | Counter Poise | 27.09.23 | Amirul Islam | Not received
47 | 25 | 43/5 | DA+0 | DFR | Counter Poise | 28.09.23 | Amirul Islam | received
48 | 26 | 51/2 | DA+0 | DRY | Pipe Type | 29.09.23 | B S Electrical | received
49 | 27 | 44/1 | DA+0 | WFR | Counter Poise | 29.09.23 | Shakti Construction | Not received
50 | 28 | 55/10 | DA+3 | DRY | Pipe Type | 29.09.23 | Nurul Amin | Not received
51 | 29 | 44/4 | DA+0 | WFR | Counter Poise | 30.09.23 | B S Electrical
52 | 30 | 44/2 | DA+0 | SANDY | Pipe Type | 30.09.23 | Shakti Construction
2023-10-01
53 | 1 | 50/3 | DA+0 | DFR | Counter Poise | 01.10.23 | Shri Bhadariyarai Enterprises
54 | 2 | 72/3 | DA+0 | DRY | Pipe Type | 01.10.23 | Mahadev engg.
55 | 3 | 72/4 | DA+0 | DRY | Pipe Type | 01.10.23 | Mahadev engg.
56 | 4 | 72/5 | DA+0 | DRY | Pipe Type | 01.10.23 | Mahadev engg.
57 | 5 | 72/2 | DA+0 | DRY | Pipe Type | 03.10.23 | Mahadev engg.
58 | 6 | 71/3 | DA+0 | DRY | Pipe Type | 03.10.23 | Mahadev engg.
59 | 7 | 71/4 | DA+0 | DRY | Pipe Type | 03.10.23 | Mahadev engg.
60 | 8 | 71/1 | DA+0 | DRY | Pipe Type | 03.10.23 | Mahadev engg.
61 | 9 | 57/4 | DA+0 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
62 | 10 | 57/5 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
63 | 11 | 57/2 | DA+0 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
64 | 12 | 57/1 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
65 | 13 | 57/3 | DA+0 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
66 | 14 | 56/9 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
67 | 15 | 56/8 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma
68 | 16 | 56/4 | DA+3 | DFR | Counter Poise | 04.10.23 | Manoj Sharma
69 | 17 | 57/7 | DA+3 | DRY | Pipe Type | 04.10.23 | Manoj Sharma |  | 72/1
70 | 18 | 56/5 | DA+0 | DRY | Pipe Type | 05.10.23 | Manoj Sharma |  | 71/5
71 | 19 | 55/11 | DA+3 | DRY | Pipe Type | 05.10.23 | Nurul Amin
72 | 20 | 55/7 | DA+0 | DRY | Pipe Type | 06.10.23 | Nurul Amin
73 | 21 | 55/8 | DA+3 | DRY | Pipe Type | 06.10.23 | Nurul Amin
74 | 22 | 55/9 | DA+3 | DRY | Pipe Type | 06.10.23 | Nurul Amin
75 | 23 | 55/5 | DA+0 | DFR | Counter Poise | 07.10.23 | Amirul Islam
76 | 24 | 56/1 | DA+3 | DFR | Counter Poise | 08.10.23 | Vaishali Const
77 | 25 | 58/14 | DA+0 | DRY | Pipe Type | 08.10.23 | Mahadev engg.
78 | 26 | 41/7 | DA+3 | SANDY | Pipe Type | 09.10.23 | Om Const
79 | 27 | 41/10 | DA+3 | SANDY | Pipe Type | 09.10.23 | Om Const
80 | 28 | 44/3 | DA+3 | WFR | Counter Poise | 10.10.23 | Shakti Construction
81 | 29 | 41/11 | DA+3 | SANDY | Pipe Type | 12.10.23 | Om Const
82 | 30 | 58/4 | DA+0 | DRY | Pipe Type | 11.10.23 | Mahadev engg.
83 | 31 | 56/2 | DA+3 | DFR | Counter Poise | 17.10.23 | Vaishali Const
84 | 32 | 55/1 | DA+3 | DRY | Pipe Type | 17.10.23 | Amirul Islam
85 | 33 | 58/7 | DB1+0 | DRY | Pipe Type | 19.10.23 | Mahadev engg.
86 | 34 | 57/6 | DB1+0 | DRY | Pipe Type | 22.10.23 | Manoj Sharma
87 | 35 | 51/5 | DA+0 | DRY | Pipe Type | 23.10.23 | Vaishali Const
88 | 36 | 51/7 | DA+3 | DFR | Counter Poise | 23.10.23 | Vaishali Const
89 | 37 | 53/2 | DA+3 | DFR | Counter Poise | 23.10.23 | Vaishali Const
90 | 38 | 59/0 | DB2+0 | DRY | Pipe Type | 26.10.23 | Mahadev engg.
91 | 39 | 57/0 | DB2+0 | DRY | Pipe Type | 28.10.23 | Manoj Sharma
2023-11-01
92 | 1 | 56/0 | DB1+0 | DFR | Counter Poise | 02.11.23 | Vaishali Const
93 | 2 | 51/0 | DB2+0 | DFR | Counter Poise | 02.11.23 | Manoj Sharma
94 | 3 | 48/0 | DB2+0 | SANDY | Pipe Type | 05.11.23 | Om Const
95 | 4 | 55/6 | DA+3 | DRY | Pipe Type | 07.11.23 | Amirul Islam
96 | 5 | 33/1 | DA+0 | SANDY | Pipe Type | 07.11.23 | Shakti Construction
97 | 6 | 52/0 | DB2+0 | DRY | Pipe Type | 08.11.23 | Manoj Sharma
98 | 7 | 43/1 | DA+9 | SANDY | Pipe Type | 08.11.23 | Om Const
99 | 8 | 46/2 | DA+0 | DRY | Pipe Type | 09.11.23 | Bhadariya
100 | 9 | 47/0 | DB1+0 | SANDY | Pipe Type | 09.11.23 | Om Const
101 | 10 | 51/9 | DA+0 | DRY | Pipe Type | 14.11.23 | Om Const
102 | 11 | 32/7 | DA+0 | Sandy | Pipe | 45237 | Shakti Construction
103 | 12 | 32/1 | DA+9 | Sandy | Pipe | 45240 | Shakti Construction
104 | 13 | 32/5 | DA+6 | Sandy | Pipe | 45240 | Shakti Construction
105 | 14 | 30/2 | DA+0 | Sandy | Pipe | 45248 | Shakti Construction
106 | 15 | 32/0 | DB2+6 | Sandy | Pipe | 45258 | Shakti Construction
2023-12-01
107 | 1 | 51/6 | DA+0 | DRY | Pipe Type | 02.12.23 | Om Const
108 | 2 | 46/3 | DA+0 | SANDY | Pipe Type | 09.12.23 | Manoj Sharma
109 | 3 | 51/1 | DA+0 | DFR | Counter Poise | 09.12.23 | Om Const
110 | 4 | 41/5 | DA+0 RC | SANDY | Pipe Type | 13.12.23 | Shakti Construction
111 | 5 | 53/1 | DA+0 RC | DRY | Pipe Type | 17.12.23 | Om Const
112 | 6 | 51/8 | DA+3 | DFR | Counter Poise | 17.12.23 | Om Const
113 | 7 | 52/3 | DA+0 RC | SANDY | Pipe Type | 22.12.23 | Om Const
114 | 8 | 31/3 | DA+0 | Sandy | Pipe | 2023-12-05 | Shakti Construction
115 | 9 | 24/3 | DA+0 | Sandy | Pipe | 2024-03-09 | N.R. Enterprises
116 | 10 | 21/8 | DA+0 | DFR | CP |  | Mehai Construction
117 | 11 | 29/8 | DA+3 | Sandy | Pipe | 2023-12-30 | Bande Bharat Group
118 | 12 | 29/3 | DA+6 | Sandy | Pipe | 2023-12-30 | N.R. Enterprises
119 | 13 | 29/7 | DA+3 | Sandy | Pipe | 2023-12-30 | Bande Bharat Group
120 | 14 | 29/5 | DA+0 | Sandy | Pipe | 2023-12-30 | N.R. Enterprises
121 | 15 | 21/9 | DA+6 | DRY | Pipe |  | Mehai Construction
2024-01-01
122 | 1 | 41/6 | DA+0(RC) | SANDY | Pipe Type | 17.01.24 | Riddhika Tech.
123 | 2 | 41/4 | DA+0(RC) | SANDY | Pipe Type | 17.01.24 | Riddhika Tech.
124 | 3 | 41/12 | DA+3 RC | SANDY | Pipe Type | 27.01.24 | Riddhika Tech.
125 | 4 | 41/8 | DA+0 (RC) | SANDY | Pipe Type | 27.01.24 | Riddhika Tech.
126 | 5 | 41/9 | DA+0(RC) | SANDY | Pipe Type | 28.01.24 | Riddhika Tech.
127 | 6 | 23/2 | DA+0 | DFR | CP | 2024-01-18 | Nagana Rai & Company
128 | 7 | 30/1 | DA+3 | Sandy | Pipe | 2024-01-18 | Bande Bharat Group
129 | 8 | 31/4 | DA+9 | Sandy | Pipe | 2024-01-19 | Bande Bharat Group
130 | 9 | 21/10 | DA+9 | Sandy | Pipe | 2024-01-20 | Mehai Construction
131 | 10 | 32/2 | DA+0 | Sandy | Pipe | 2024-01-30 | Bande Bharat Group
132 | 11 | 23/5 | DA+0 | DFR | CP | 2024-01-31 | A.B. Construction
133 | 12 | 29/6 | DA+6 | Sandy | Pipe | 2024-01-31 | N.R. Enterprises
134 | 13 | 32/3 | DA+3 | Sandy | Pipe | 2024-01-31 | Bande Bharat Group
Feb-24
135 | 1 | 53/0 | DC2+3 | DRY | Pipe Type | 02.02.24 | Om Const
136 | 2 | 55/0 | DC1+0 | DRY | Pipe Type | 06.02.24 | Manoj Sharma
137 | 3 | 58/0 | DC2+0 | DRY | Pipe Type | 19.02.24 | Mahadev engg.
138 | 4 | 65/1 | DA+3 | DRY | Pipe Type | 21.2.24 | Bhati Const.
139 | 5 | 65/4 | DA+0 | DRY | Pipe Type | 21.2.24 | Bhati Const.
140 | 6 | 63/6 | DA+3 | DRY | Pipe Type | 22.2.24 | Bhati Const.
141 | 7 | 65/3 | DA+0 | DRY | Pipe Type | 22.2.24 | Bhati Const.
142 | 8 | 65/5 | DA+0 | DRY | Pipe Type | 22.2.24 | Bhati Const.
143 | 9 | 46/4 | DA+0 (RC) | SANDY | Pipe Type | 20.02.24 | Om Const
144 | 10 | 63/5 | DA+3 | DRY | Pipe Type | 10.02.24 | Bhati Const.
145 | 11 | 40/10 | DB1+6 | SANDY | Pipe Type | 24.02.24 | Riddhika Tech.
146 | 12 | 40/11 | DA+9 RC | SANDY | Pipe Type | 24.02.24 | Riddhika Tech.
147 | 13 | 40/6 | DA+3 RC | SANDY | Pipe Type | 25.02.24 | Riddhika Tech.
148 | 14 | 23/3 | DA+0 | DFR | CP | 2024-02-17 | A.B. Construction
149 | 15 | 22/5 | DA+3 | DFR | CP |  | Mateshwari Const.
150 | 16 | 31/2 | DA+0 | Sandy | Pipe | 2024-02-17 | Bande Bharat Group
151 | 17 | 29/9 | DA+3 | Sandy | Pipe | 2024-02-17 | N.R. Enterprises
152 | 18 | 22/4 | DA+3 | DFR | CP | 2024-02-19 | Jai Bhawani Construction
153 | 19 | 21/12 | DA+9 | Sandy | Pipe | 2024-02-19 | Mehai Construction
154 | 20 | 22/9 | DA+6 | DRY | Pipe | 2024-02-29 | Majisa Construction
155 | 21 | 23/1 | DA+0 | Sandy | Pipe | 2024-02-29 | A.B. Construction
156 | 22 | 31/1 | DA+9+3 | Sandy | Pipe | 2024-03-04 | Bande Bharat Group
157 | 23 | 22/8 | DA+6 | DRY | Pipe | 2024-02-26 | Majisa Construction
158 | 24 | 29/10 | DA+6 | Sandy | Pipe | 2024-02-29 | Bande Bharat Group
159 | 25 | 22/2 | DA+0 | DFR | CP | 2024-03-01 | Jai Bhawani Construction
160 | 26 | 28/1 | DA+6 | Sandy | Pipe | 2024-03-12 | R.D. Enterprises
161 | 27 | 27/4 | DA+0 | Sandy | Pipe | 2024-03-04 | N.R. Enterprises
March'24
162 | 1 | 40/4 | DA+9 RC | SANDY | Pipe Type | 06.03.24 | Riddhika Tech.
163 | 2 | 37/3 | DA+0 | SANDY | Pipe Type | 08.03.24 | Veerteja Enterprises
164 | 3 | 37/2 | DB1+6 | SANDY | Pipe Type | 08.03.24 | Veerteja Enterprises
165 | 4 | 38/1 | DA+3 RC | SANDY | Pipe Type | 12.03.24 | Shakti Construction
166 | 5 | 38/6 | DA+0 RC | SANDY | Pipe Type | 13.03.24 | Shakti Construction
167 | 6 | 37/4 | DA+6 RC | SANDY | Pipe Type | 13.03.24 | Veerteja Enterprises
168 | 7 | 40/3 | DA+3 RC | SANDY | Pipe Type | 14.03.24 | Riddhika Tech.
169 | 8 | 39/1 | DA+6 RC | SANDY | Pipe Type | 14.03.24 | Riddhika Tech.
170 | 9 | 65/2 | DA+0 | SANDY | Pipe Type | 14.03.24 | Bhati Const.
171 | 10 | 63/2 | DA+0 | DRY | Pipe Type | 14.03.24 | Bhati Const.
172 | 11 | 65/6 | DA+0 | Dry | Pipe Type | 14.03.24 | Bhati Const.
173 | 12 | 40/5 | DB1+9 | SANDY | Pipe Type | 14.03.24 | Riddhika Tech.
174 | 13 | 38/2 | DA+6 | SANDY | Pipe Type | 16.03.24 | Veerteja Enterprises
175 | 14 | 38/3 | DA+9 RC | SANDY | Pipe Type | 16.03.24 | Veerteja Enterprises
176 | 15 | 39/3 | DA+3 RC | SANDY | Pipe Type | 21.03.24 | Riddhika Tech.
177 | 16 | 10/12 | DB1+3 | DRY | Pipe | 2024-03-06 | Om Construction
178 | 17 | 27/5 | DA+0 | Sandy | Pipe | 2024-03-09 | N.R. Enterprises
179 | 18 | 30/0 | DC2+0 | Sandy | Pipe | 2024-03-10 | Bande Bharat Group
180 | 19 | 28/0 | DB1+0 | Sandy | Pipe | 2024-03-12 | R.D. Enterprises
181 | 20 | 8/10 | DA+3 | DFR | CP | 2024-03-23 | Mateshwari Const.
182 | 21 | 6/2 | DA+3 | DFR | CP | 2024-03-23 | Majisa Construction
183 | 22 | 8/11 | DA+3 | DFR | CP | 2024-03-23 | Jai Bhawani Construction
184 | 23 | 26/4 | DA+9 | Sandy | Pipe | 2024-03-23 | Bande Bharat Group
185 | 24 | 10/7 | DA+6 | DRY | CP | 2024-04-18 | Shri Degrai Enterprises
April'24
186 | 1 | 38/8 | DA+0 RC | SANDY | Pipe Type | 21.04.24 | Shakti Construction
187 | 2 | 8/8 | DA+6 | DFR | CP | 2024-04-10 | Mateshwari Const.
188 | 3 | 10/14 | DA+3 | DRY | Pipe | 2024-04-18 | Shri Degrai Enterprises
189 | 4 | 8/6 | DA+3 | DRY | Pipe | 2024-04-29 | Mateshwari Const.
190 | 5 | 10/10 | DA+3 | DRY | Pipe | 2024-04-18 | Shri Degrai Enterprises
191 | 6 | 32/4 | DA+0+3 | Sandy | Pipe | 2024-04-18 | Bande Bharat Group
192 | 7 | 10/6 | DA+3 | DFR | CP | 2024-04-29 | Shri Degrai Enterprises
193 | 8 | 8/1 | DA+3 | DRY | Pipe | 2024-04-29 | Mateshwari Const.
194 | 9 | 10/13 | DA+3 | DRY | Pipe | 2024-04-28 | Shri Degrai Enterprises
May'24
195 | 1 | 39/4 | DA+0(RC) | SANDY | Pipe Type | 12.05.24 | SB MEHAR CONST.
196 | 2 | 32/6 | DA+6 | DRY | Pipe | 2024-05-07 | Bande Bharat Group
197 | 3 | 10/9 | DA+3 | DRY | Pipe | 2024-05-03 | Shri Degrai Enterprises
198 | 4 | 8/7 | DB1+0 | DRY | Pipe | 2024-05-23 | Mateshwari Const.
199 | 5 | 10/3 | DA+3 | DFR | CP | 2024-05-08 | Shri Degrai Enterprises
200 | 6 | 10/5 | DA+3 | DFR | CP | 2024-05-12 | Shri Degrai Enterprises
201 | 7 | 13/4 | DA+0 | DRY | Pipe | 2024-05-27 | Majisa Construction
202 | 8 | 15/8 | DA+0 | DRY | Pipe | 2024-05-28 | Brads Infratech
203 | 9 | 14/1 | DA+3 | DRY | Pipe | 2024-05-30 | Mehai Construction
June'24
204 | 1 | 14/2 | DA+3 | DRY | Pipe | 2024-06-03 | Mehai Construction
205 | 2 | 14/3 | DA+0 | DRY | Pipe | 2024-06-05 | Majisa Construction
206 | 3 | 15/9 | DA+9 | DRY | Pipe | 2024-06-13 | Mehai Construction
207 | 4 | 16/3 | DA+0 | DRY | Pipe | 2024-06-17 | Vibe Infra
208 | 5 | 14/4 | DA+0 | DRY | Pipe | 2024-06-15 | Majisa Construction
209 | 6 | 16/4 | DA+3 | DRY | Pipe | 2024-06-19 | Vibe Infra
210 | 7 | 25/10 | DA+0 | Sandy | Pipe | 2024-06-23 | Departmental Gang
211 | 8 | 10/19 | DA+9 | DRY | Pipe | 2024-06-24 | Jai Bhawani Construction
212 | 9 | 14/5 | DA+0 | DRY | Pipe | 2024-06-24 | Majisa Construction
213 | 10 | 15/0 | DC2+0 | DRY | Pipe | 2024-06-25 | Mehai Construction
214 | 11 | 10/20 | DB1+6 | DFR | CP | 2024-07-10 | Jai Bhawani Construction
215 | 12 | 16/5 | DA+3 | DRY | Pipe | 2024-06-25 | Vibe Infra
216 | 13 | 15/1 | DA+6 | DRY | Pipe | 2024-07-03 | Majisa Construction
217 | 14 | 16/6 | DA+0 | DRY | Pipe | 2024-07-04 | Vibe Infra
July'24
218 | 1 | 40/2 | DB1+9 | SANDY | Pipe Type | 15.07.24 | Bhati Const.
219 | 2 | 49/0 | DC1+3 | DFR | Counter Poise | 20.07.24 | Mahadev engg.
220 | 3 | 50/0 | DC2+3 | DFR | Counter Poise | 29.07.24 | Mahadev engg.
221 | 4 | 11/14 | DA+0 | DRY | Pipe | 2024-08-31 | Punia Construction
222 | 5 | 10/21 | DA+0 | DFR | CP | 2024-07-10 | Jai Bhawani Construction
223 | 6 | 25/9 | DA+6 | DRY | Pipe | 2024-07-18 | Krishna Projects India
224 | 7 | 16/2 | DA+3 | DRY | Pipe | 2024-07-10 | Vibe Infra
225 | 8 | 10/18 | DA+0 | DFR | CP | 2024-08-31 | Jai Bhawani Construction
226 | 9 | 25/8 | DA+9+4 | DRY | Pipe | 2024-07-18 | Krishna Projects India
227 | 10 | 16/1 | DA+3 | DRY | Pipe | 2024-07-23 | J.P. Infra
228 | 11 | 11/4 | DA+6 | DFR | CP | 2024-08-31 | MCI
229 | 12 | 11/11 | DA+0 | Sandy | Pipe | 2024-08-26 | R.K. Construction
230 | 13 | 26/7 | DA+3 | Sandy | Pipe | 2024-07-31 | Company Gangs
231 | 14 | 17/0 | DC1+0 | DRY | Pipe | 2024-07-31 | Vibe Infra
232 | 15 | 15/3 | DA+3 | DRY | Pipe | 2024-07-31 | Majisa Construction
233 | 16 | 10/4 | DA+3 | DFR | CP | 2024-08-26 | Jai Bhawani Construction
Aug'24
234 | 1 | 72/0 | DB1+0 | DRY | Pipe Type | 01.08.24 | Mahadev engg.
235 | 2 | 71/2 | DA+0 | DRY | Pipe Type | 01.08.24 | Mahadev engg. |  |  |  | 51
236 | 3 | 43/6 | DA+6 RC | SANDY | Pipe Type | 01.08.24 | Om Const |  |  |  | 22
237 | 4 | 44/0 | DB1+0 | SANDY | Pipe Type | 02.08.24 | Om Const
238 | 5 | 50/2 | DA+0 | DFR | Counter Poise | 11.08.24 | Bhati Const.
239 | 6 | 42/0 | DC2+9 RC | SANDY | Pipe Type | 11.08.24 | Om Const
240 | 7 | 47/1 | DA+0 | DRY | Pipe Type | 14.08.24 | Bhati Const.
241 | 8 | 72/7 | DB1+9 RC | SANDY | Pipe Type | 14.08.24 | Mahadev engg.
242 | 9 | 72/6 | DA+0 RC | SANDY | Pipe Type | 14.08.24 | Mahadev engg. |  |  | 48
243 | 10 | 69/6 | DA+0 | DRY | Pipe Type | 23.08.24 | Mahadev engg. |  |  | 27
244 | 11 | 68/5 | DA+3 | DRY | Pipe Type | 23.08.24 | Shakti Construction
245 | 12 | 63/0 | DD45+0 | DRY | Pipe Type | 24.08.24 | Mahadev engg.
246 | 13 | 43/0 | DB2+9 RC | SANDY | Pipe Type | 31.08.24 | Om Const
247 | 14 | 50/1 | DA+0 RC | DFR | Counter Poise | 31.08.24 | Mahadev engg.
248 | 15 | 11/10 | DB1+0 | DRY | Pipe | 2024-08-18 | R.K. Construction
249 | 16 | 32/8 | DA+9 | Sandy | Pipe | 2024-08-29 | N.R. Enterprises
250 | 17 | 19/13 | DA+0 | Sandy | Pipe | 2024-08-11 | RBM
251 | 18 | 11/7 | DA+3 | DRY | Pipe | 2024-09-08 | R.K. Construction
252 | 19 | 11/5 | DA+3 | DRY | Pipe |  | MCI
253 | 20 | 15/2 | DA+9 | DRY | Pipe | 2024-08-13 | OM Enterprise
254 | 21 | 19/14 | DA+9+2 | DRY | Pipe | 2024-08-16 | RBM
255 | 22 | 26/6 | DA+0 | Sandy | Pipe | 2024-08-18 | Departmental Gang
256 | 23 | 21/2 | DA+3 | DRY | Pipe | 2024-08-22 | RBM
257 | 24 | 16/0 | DB2+0 | DRY | Pipe | 2024-08-24 | J.P. Infra
258 | 25 | 21/1 | DA+3 | DRY | Pipe | 2024-08-31 | RBM
259 | 26 | 10/8 | DA+0 | DRY | Pipe | 2024-09-08 | A.B. Construction
260 | 27 | 15/4 | DA+3 | DRY | Pipe | 2024-08-31 | Majisa Construction
261 | 28 | 21/3 | DA+0 | DRY | Pipe | 2024-08-29 | RBM
262 | 29 | 11/15 | DA+0 | DRY | Pipe | 2024-09-08 | Punia Construction
Sept'24
263 | 1 | 69/2 | DA+0 | DRY | Pipe Type | 02.09.24 | Bhati Const.
264 | 2 | 69/3 | DA+0 | Sandy | Pipe Type | 02.09.24 | Bhati Const.
265 | 3 | 69/4 | DA+0 | DRY | Pipe Type | 02.09.24 | Bhati Const.
266 | 4 | 69/5 | DA+0 | DRY | Pipe Type | 02.09.24 | Bhati Const.
267 | 5 | 68/2 | DA+3 | DRY | Pipe Type | 02.09.24 | Shakti Construction
268 | 6 | 67/0 | DD45+0 | DRY | Pipe Type | 04.09.24 | Awadh Const.
269 | 7 | 69/7 | DA+0 | DRY | Pipe Type | 05.09.24 | Mahadev engg.
270 | 8 | 73/0 | DD45+9 | DFR | Counter Poise | 07.10.24 | Mahadev engg.
271 | 9 | 69/1 | DA+0 | DRY | Pipe Type | 05.09.24 | Bhati Const.
272 | 10 | 67/1 | DB1+9 | DRY | Pipe Type | 05.09.24 | Awadh Const.
273 | 11 | 35/5 | DA+0 RC | SANDY | Pipe Type | 09.09.24 | Om Const
274 | 12 | 68/4 | DA+3 | DRY | Pipe Type | 10.09.24 | Shakti Construction
275 | 13 | 68/6 | DA+3 | DRY | Pipe Type | 10.09.24 | Shakti Construction
276 | 14 | 35/6 | DA+9 RC | SANDY | Pipe Type | 15.09.24 | Om Const
277 | 15 | 66/1 | DA+3 | DRY | Pipe Type | 15.09.24 | Shree Shyam Const.
278 | 16 | 66/2 | DA+0 | DRY | Pipe Type | 15.09.24 | Shree Shyam Const.
279 | 17 | 66/4 | DA+3 | DRY | Pipe Type | 15.09.24 | Shree Shyam Const.
280 | 18 | 69/0 | DB1+0 | DRY | Pipe Type | 16.09.24 | Bhati Const.
281 | 19 | 71/5 | DA+0 | DRY | Pipe Type | 16.09.24 | Mahadev engg.
282 | 20 | 68/3 | DA+0 | DRY | Pipe Type | 22.09.24 | Shakti Construction
283 | 21 | 65/7 | DA+0 | DRY | Pipe Type | 23.09.24 | Shree Shyam Const.
284 | 22 | 35/4 | DA+3 RC | SANDY | Pipe Type | 27.09.24 | Om Const
285 | 23 | 43/2 | DA+9 RC | SANDY | Pipe Type | 27.09.24 | Kalpana
286 | 24 | 43/3 | DA+3 RC | SANDY | Pipe Type | 27.09.24 | Kalpana
287 | 25 | 10/11 | DA+0 | DRY | Pipe | 2024-08-31 | A.B. Construction
288 | 26 | 11/12 | DA+0+1 | Sandy | Pipe | 2024-09-08 | R.K. Construction
289 | 27 | 11/8 | DA+0 | DRY | Pipe | 2024-08-31 | R.K. Construction
290 | 28 | 21/4 | DA+9 | DRY | Pipe | 2024-09-03 | RBM
291 | 29 | 11/9 | DA+3 | DRY | Pipe | 2024-09-23 | R.K. Construction
292 | 30 | 19/5 | DA+3 | DRY | Pipe | 2024-09-24 | Om construction Company
293 | 31 | 21/5 | DA+3 | Sandy | Pipe | 2024-09-23 | RBM
294 | 32 | 14/0 | DC2+0 | Sandy | Pipe | 2024-09-23 | OM Enterprise
295 | 33 | 19/6 | DA+3 | DRY | Pipe | 2024-09-26 | Vibe Infra
296 | 34 | 13/2 | DA+3 | Sandy | Pipe | 2024-09-28 | Punia Construction
297 | 35 | 21/6 | DA+0 | DRY | Pipe | 2024-09-30 | RBM
298 | 36 | 19/4 | DA+0 | DRY | Pipe | 2024-09-24 | Om Construction Company
299 | 37 | 11/6 | DA+3 | DRY | Pipe | 2024-06-26 | R.K. Construction
300 | 38 | 13/1 | DA+3 | DRY | Pipe | 2024-09-23 | Punia Construction
301 | 39 | 10/22 | DA+0 | Sandy | Pipe | 2024-09-23 | Hadhbuji Construction Company
302 | 40 | 21/7 | DB1+0 | DRY | Pipe | 2024-09-30 | RBM
303 | 41 | 19/3 | DA+6 | DRY | Pipe | 2024-09-23 | Om Construction Company
304 | 42 | 19/7 | DA+9 | DRY | Pipe | 2024-09-30 | Vibe Infra
305 | 43 | 15/6 | DA+0 | DRY | Pipe | 2024-09-30 | OM Enterprise
306 | 44 | 17/1 | DA+3 | DRY | Pipe | 2024-09-30 | Sidhi Vinayak
Oct'24
307 | 1 | 35/8 | DA+0 RC | SANDY | Pipe Type | 04.10.24 | Om Const
308 | 2 | 35/7 | DA+3 RC | SANDY | Pipe Type | 04.10.24 | Om Const
309 | 3 | 68/0 | DD45+0 | DRY | Pipe Type | 07.10.23 | Shakti Construction
310 | 4 | 68/1 | DA+3 | DRY | Pipe Type | 07.10.23 | Shakti Construction
311 | 5 | 66/3 | DA+3 | DRY | Pipe Type | 07.10.23 | Shree Shyam Const.
312 | 6 | 66/0 | DD45+0 | DRY | Pipe Type | 07.10.23 | Shree Shyam Const.
313 | 7 | 62/0 | DC2+0 | DRY | Pipe Type | 07.10.23 | Mahadev engg.
314 | 8 | 72/1 | DA+0 | DRY | Pipe Type | 19.10.24 | Mahadev engg.
315 | 9 | 71/0 | DD60+0 | FS | Pipe Type-Leg A | 22.10.24 | Mahadev engg.
316 | 10 | 71/0 | DD60+0 | FS | Pipe Type-Leg C | 22.10.24 | Mahadev engg.
317 | 11 | 35/2 | DA+0 (RC) | SANDY | Pipe Type | 23.10.24 | Om Const
318 | 12 | 69/9 | DA+0 | DFR | Counter Poise | 26.10.24 | Mahadev engg.
319 | 13 | 64/0 | DB2+0 | DRY | Pipe Type | 26.10.24 | Bhati Const.
320 | 14 | 35/1 | DA+0 RC | SANDY | Pipe Type | 17.10.24 | Om Const
321 | 15 | 35/0 | DB2+0 RC | SANDY | Pipe Type | 17.10.24 | Om Const
322 | 16 | 30/3 | DA+6 | Sandy | Pipe |  | D.R. Construction
323 | 17 | 11/13 | DA+0 | Sandy | Pipe | 2025-01-12 | R.K. Construction
324 | 18 | 17/3 | DA+3 | DRY | Pipe | 2024-10-12 | Vibe Infra
325 | 19 | 19/2 | DA+3 | DRY | Pipe | 2024-12-17 | Vibe Infra
326 | 20 | 13/0 | DD60+0 | DRY | Pipe | 2024-10-16 | Punia Construction
327 | 21 | 19/9 | DA+3 | Sandy | Pipe | 2024-12-09 | Vibe Infra
328 | 22 | 31/0 | DD45+3 | Sandy | Pipe | 2024-11-28 | D.R. Construction
329 | 23 | 21/11 | DA+9 | DRY | Pipe | 2025-01-08 | Sidhi Vinayak
Nov'24
330 | 1 | 35/3 | DA+0 (RC) | SANDY | Pipe Type | 06.11.24 | Om Const
331 | 2 | 34/4 | DA+6 RC | SANDY | Pipe Type | 08.11.24 | Om Const
332 | 3 | 34/6 | DA+6 RC | SANDY | Pipe Type | 22.11.24 | Om Const
333 | 4 | 38/9 | DB1+6 RC | SANDY | Pipe Type | 22.11.24 | Om Const
334 | 5 | 39/0 | DC2+3 RC | SANDY | Pipe Type | 22.11.24 | Om Const
335 | 6 | 58/13 | DA+0 | DRY | Pipe Type | 29.11.24 | Bhati Const.
336 | 7 | 13/3 | DA+0 | sandy | Pipe |  | Punia Construction
337 | 8 | 2/4 | DA+3 | Sandy | Pipe | 2024-12-13 | Laxmi Enterprises
338 | 9 | 24/2 | DA+0 | DRY | Pipe | 2024-12-26 | Parsuram Sahi
339 | 10 | 27/2 | DA+0 | Sandy | Pipe | 2024-12-18 | prasuram sai
340 | 11 | 12/0 | DD60+0 | DRY | Pipe | 2024-12-13 | Vibe Infra
341 | 12 | 14/6 | DA+0 | DRY | Pipe |  | Punia Construction
Dec'24
342 | 1 | 34/3 | DA+9 RC | SANDY | Pipe Type | 04.12.24 | Om Const
343 | 2 | 40/12 | DA+0 RC | SANDY | Pipe Type | 06.12.24 | Nadeem rasool
344 | 3 | 69/8 | DA+0 | DFR | Pipe Type | 08.12.24 | Mahadev engg.
345 | 4 | 64/8 | DA+0 | DRY | Pipe Type | 08.12.24 | Bhati Const.
346 | 5 | 64/7 | DA+3 | DRY | Pipe Type | 12.12.24 | Bhati Const.
347 | 6 | 34/2 | DA+9 RC | SANDY | Pipe Type | 17.12.24 | Om Const
348 | 7 | 37/8 | DA+0 | SANDY | Pipe Type | 17.12.24 | Nadeem rasool
349 | 8 | 64/1 | DA+6 | DRY | Pipe Type | 19.12.24 | Bhati Const.
350 | 9 | 64/9 | DA+0 | DRY | Pipe Type | 19.12.24 | Bhati Const.
351 |  | 70/0 | DD60+0 | FS | Pipe Type-Leg A | 19.12.24 | Mahadev engg.
352 | 10 | 70/0 | DD60+0 | FS | Pipe Type-Leg C | 19.12.24 | Mahadev engg.
353 | 11 | 64/6 | DA+3 | DRY | Pipe Type | 28.12.24 | Bhati Const.
354 | 12 | 38/4 | DA+0 RC | SANDY | Pipe Type | 30.12.24 | Nadeem rasool
355 | 13 | 38/0 | DC1+0 | SANDY | Pipe Type | 31.12.24 | Nadeem rasool
356 | 14 | 38/5 | DA+0 RC | SANDY | Pipe Type | 31.12.24 | Nadeem rasool
357 | 15 | 38/7 | DA+0 RC | SANDY | Pipe Type | 31.12.24 | Nadeem/Iqbal
358 | 16 | 24/1 | DA+3 | DRY | Pipe | 2024-12-26 | prasuram sai
359 | 17 | 15/7 | DA+6 | DRY | Pipe | 2024-12-15 | Punia Construction
360 | 18 | 2/5 | DA+3 | Sandy | Pipe | 2024-12-28 | Sri Nagana ray Enterprise
361 | 19 | 25/6 | DA+3 | DRY | Pipe | 2024-12-19 | prasuram sai
362 | 20 | 2/3 | DA+0 | Sandy | Pipe | 2025-01-06 | Laxmi Enterprises
363 | 21 | 6/1 | DA+0 | DFR | CP | 2025-01-02 | HS Engineering
364 | 22 | 25/5 | DA+3 | Sandy | Pipe | 2024-12-19 | prasuram sai
365 | 23 | 24/6 | DA+0 | DRY | Pipe | 2025-01-03 | Vishwakarma Construction
366 | 24 | 24/5 | DA+3 | Sandy | Pipe | 2024-12-25 | Vishwakarma Construction
367 | 25 | 2/2 | DA+0 | Sandy | Pipe |  | Laxmi Enterprises
368 | 26 | 24/4 | DA+0 | DRY | Pipe | 2024-12-25 | Vishwakarma Construction
369 | 27 | 27/3 | DA+0 | Sandy | Pipe | 2024-12-18 | Prasuram sai
370 | 28 | 25/11 | DA+6 | DRY | Pipe | 2025-01-07 | YMK Construction
371 | 29 | 24/0 | DB2+0 | DRY | Pipe | 2025-01-07 | Vishwakarma Construction
372 | 30 | 21/13 | DA+0 | DRY | Pipe | 2025-01-07 | JSR Infrastructure
373 | 31 | 23/11 | DA+6 | Sandy | Pipe | 2025-01-05 | Vishwakarma Construction
374 | 32 | 23/10 | DA+3 | DFR | CP | 2025-01-07 | Vishwakarma Construction
375 | 33 | 26/0 | DB2+0 | DRY | Pipe | 2025-01-08 | YMK Construction
376 | 34 | 27/0 | DC2+9 | Sandy | Pipe | 2025-01-04 | D.R. Construction
377 | 35 | 23/8 | DA+9 | Sandy | Pipe | 2025-01-06 | Vishwakarma Construction
2025-01-25
378 | 1 | 34/5 | DCT+0 | SANDY | Pipe Type | 03.01.25 | Om Const
379 | 2 | 33/8 | DA+3 RC | SANDY | Pipe Type | 04.01.25 | Om Const
380 | 3 | 34/1 | DA+3 RC | SANDY | Pipe Type | 05.01.25 | Om Const
381 | 4 | 63/1 | DA+6 | DRY | Pipe Type | 06.01.25 | Bhati Const.
382 | 5 | 37/7 | DA+3 RC | SANDY | Pipe Type | 07.01.25 | Iqbal
383 | 6 | 37/5 | DA+3 RC | SANDY | Pipe Type | 07.01.25 | Iqbal
384 | 7 | 37/6 | DA+6 RC | SANDY | Pipe Type | 07.01.25 | Iqbal
385 | 8 | 40/1 | DA+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
386 | 9 | 40/0 | DC2+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
387 | 10 | 39/2 | DA+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
388 | 11 | 39/5 | DA+3 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
389 | 12 | 39/6 | DA+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
390 | 13 | 39/7 | DA+0 RC | SANDY | Pipe Type | 10.01.25 | Meer Construction
391 | 14 | 60/0 | DC2+3 | DRY | Pipe Type | 20.01.25 | Bhati Const.
392 | 15 | 41/0 | DB1+0 RC | SANDY | Pipe Type | 23.01.25 | Nadeem rasool
393 | 16 | 41/1 | DA+3 RC | SANDY | Pipe Type | 23.01.25 | Nadeem rasool
394 | 17 | 41/2 | DA+0 RC | SANDY | Pipe Type | 23.01.25 | Nadeem rasool
395 | 18 | 41/3 | DA+0 RC | SANDY | Pipe Type | 23.01.25 | Nadeem rasool
396 | 19 | 2/1 | DA+0 | Sandy | Pipe | 2025-01-06 | Laxmi Enterprises
397 | 20 | 2/6 | DA+6 | Sandy | Pipe | 2025-01-04 | Naganaray Enterprise
398 | 21 | 8/9 | DA+3 | DFR | CP | 2025-01-10 | JSR Infrastructure
399 | 22 | 26/2 | DA+3 | Sandy | Pipe |  | YMK Construction
400 | 23 | 23/7 | DA+9 | DFR | CP |  | Vishwakarma Construction
401 | 24 | 26/3 | DA+0 | Sandy | Pipe |  | YMK Construction
402 | 25 | 25/0 | DC1+0 | Sandy | Pipe |  | Vishwakarma Construction
403 | 26 | 25/1 | DA+3 | Sandy | Pipe |  | Vishwakarma Construction
404 | 27 | 25/3 | DA+0 | DRY | Pipe |  | Vishwakarma Construction
405 | 28 | 27/1 | DB1+9 | Sandy | Pipe |  | D.R. Construction
406 | 29 | 25/4 | DA+0 | Sandy | Pipe |  | Vishwakarma Construction
407 | 30 | 25/7 | DA+9 | Sandy | Pipe |  | Vishwakarma Construction
408 | 31 | 26/5 | DA+9 | Sandy | Pipe |  | YMK Construction
409 | 32 | 1A/0 | DD60+0 | DFR | CP |  | JSR Infrastructure
410 | 33 | 22/7 | DA+6 | DFR | CP |  | D.R. Construction
411 | 34 | 1A/3 | DA+0 | Sandy | Pipe |  | Naganaray Enterprise
Feb'25
412 | 1 | 64/2 | DA+0 | DRY | Pipe Type | 03.02.25 | Tantary Const.
413 | 2 | 64/3 | DA+0 | DRY | Pipe Type | 03.02.25 | Tantary Const.
414 | 3 | 64/4 | DA+3 | DRY | Pipe Type | 03.02.25 | Tantary Const.
415 | 4 | 64/5 | DA+3 | DRY | Pipe Type | 03.02.25 | Tantary Const.
416 | 5 | 33/3 | DA+0 | SANDY | Pipe Type | 07.02.25 | Tantary Const.
417 | 6 | 44/5 | DA+6 | WFR | Counter Poise | 07.02.25 | Bhati Const.
418 | 7 | 33/4 | DA+0 (RC) | SANDY | Pipe Type | 14.02.25 | Tantray Construction
419 | 8 | 33/5 | DA+0 | SANDY | Pipe Type | 15.02.25 | Tantray Construction
420 | 9 | 59/4 | DA+0 | DRY | Pipe Type | 19.02.25 | Bhati Const.
421 | 10 | 61/0 | DB1+6 | DRY | Pipe Type | 19.02.25 | Bhati Const.
422 | 11 | 63/4 | DA+0 | DRY | Pipe Type | 19.02.25 | Bhati Const.
423 | 12 | 40/8 | DA+0 RC | SANDY | Pipe Type | 23.02.25 | Tantray Construction
424 | 13 | 40/9 | DA+0 RC | SANDY | Pipe Type | 23.02.25 | Tantray Construction
425 | 14 | 33/0 | DB2+3 RC | SANDY | Pipe Type | 26.02.25 | Nadeem rasool
426 | 15 | 33/2 | DA+0 RC | SANDY | Pipe Type | 26.02.25 | Iqbal
427 | 16 | 33/6 | DA+6 RC | SANDY | Pipe Type | 26.02.25 | Iqbal
428 | 17 | 2/0 | DC1+0 | DRY | Pipe |  | Laxmi Enterprises
429 | 18 | 1A/5 | DA+6 | Sandy | Pipe |  | Laxmi Enterprises
430 | 19 | 1A/1 | DA+0 | DRY | Pipe |  | JSR Infrastructure
431 | 20 | 1A/2 | DA+6 | DRY | Pipe |  | JSR Infrastructure
432 | 21 | 1A/4 | DA+3 | DRY | Pipe |  | Naganaray Enterprise
433 | 22 | 1/0 | DD60+0 | DRY | Pipe |  | JSR Infrastructure
434 | 23 | 1A/6 | DA+0 | SANDY | Pipe |  | Laxmi Enterprises
435 | 24 | 26/1 | DA+3 | SANDY | Pipe |  | YMK Construction
Mar'25
436 | 1 | 37/0 | DD60+25 RC | SANDY | Pipe Type | 11.03.25 | OM Const
437 | 2 | 37/1 | DB1+9 RC | SANDY | Pipe Type | 11.03.25 | OM Const
438 | 3 | 33/7 | DA+9 RC | SANDY | Pipe Type | 16.03.25 | Om Const
439 | 4 | 45/0 | DD60+25 RC | SANDY | Pipe Type | 19.03.25 | Bhati Const.
440 | 5 | 46/0 | DD60+25 RC | SANDY | Pipe Type | 19.03.25 | Bhati Const.
441 | 6 | 46/1 | DA+6 RC | SANDY | Pipe Type | 19.03.25 | Bhati Const.
442 | 7 | 35/9 | DA+3 RC | SANDY | Pipe Type | 21.03.25 | Om Const
443 | 8 | 34/0 | DB1+6 RC | SANDY | Pipe Type | 21.03.25 | Om Const
444 | 9 | 36/0 | DD60+25 RC | SANDY | Pipe Type | 22.03.25 | OM Const
445 | 10 | 40/7 | DA+3 RC | SANDY | Pipe Type | 06.12.24
446 | 11 | 65/0 | DB2+3 | SANDY | Pipe Type | 28.03.25 | Bhati Const.
447 | 12 | 21/14 | #N/A | DFR | CP | 28.03.25 | JSR
448 | 13 | 63/3 | DA+3 | DRY | Pipe Type | 29.03.25 | Bhati Const.
449 | 14 | 2/9 | DA+0 | DRY | Pipe |  | JSR
450 | 15 | 28/2 | DA+3 | SANDY | Pipe |  | Parsuram Sahi
451 | 16 | 23/6 | DA+6 | DFR | CP |  | Vishwakarma Construction
452 | 17 | 23/0 | DB2+0 | SANDY | Pipe |  | Vishwakarma Construction
453 | 18 | 22/6 | DA+6 | SANDY | Pipe |  | Vishwakarma Construction
April'25
454 | 1 | 29/4 | #REF! | DRY | Pipe | 10.04.25 | Vishwakarma Construction
455 | 2 | 2/7 | #REF! | Sandy | Pipe | 02.04.25 | JSR
456 | 3 | 29/1 | DA+6 RC | Sandy | Pipe | 21.04.25 | Vishwakarma Construction
457 | 4 | 4/0 | DD60+6 | DRY | Pipe | 26.04.25 | JSR
458 | 5 | 4/1 | DA+0 | DRY | Pipe | 28.04.25 | JSR
459 | 6 | 28/8 | DA+3 | Sandy | Pipe | 29.04.25 | Vishwakarma Construction
460 | 7 | 28/9 | DA+0 | Sandy | Pipe | 29.04.25 | Vishwakarma Construction
461 | 8 | 29/2 | DA+9 | Sandy | Pipe | 29.04.25 | Vishwakarma Construction
2025-05-25
462 | 1 | 1A/7 | DA+3 | Sandy | Pipe | 09.05.25 | JSR
463 | 2 | 29/0 | DB2+0 | Sandy | Pipe | 15.05.25 | Vishwakarma Construction
464 | 3 | 22/1 | DA+0 | DFR | CP | 22.05.25 | YMK Construction
465 | 4 | 15/5 | DA+3 | DFR | CP | 30.05.25 | BR const.
466 | 5 | 4/3 | DA+0 | DRY | Pipe | 29.05.25 | Nice Security & Services
467 | 6 | 2026-03-22 | DA+3 | DFR | CP | 31.05.25 | Vishwakarma Construction
2025-06-25
468 | 1 | 17/5 | DA+3 | DRY | Pipe | 05.06.25 | Shree Ram Enterprises
469 | 2 | 2/8 | DA+0 | Sandy | Pipe | 06.06.25 | JSR
470 | 3 | 11/2 | DA+9 | Sandy | Pipe | 27.05.25 | BR const.
471 | 4 | 2026-04-28 | DA+9 RC | Sandy | Pipe | 29.06.25 | Vishwakarma Construction
472 | 5 | 28/5 | DA+9 | SANDY | Pipe | 29.06.25 | Vishwakarma Construction
473 | 6 | 11/3 | DA+9 | Sandy | Pipe | 29.06.25 | BR const.
474 | 7 | 28/3 | DA+0 RC | Sandy | Pipe | 29.06.25 | Vishwakarma Construction
475 | 8 | 3/0 | DD60+3 | DRY | Pipe | 29.06.25 | JSR
476 | 9 | 8/2 | DA+3 | DRY | Pipe | 05.06.25 | Dhakad Ent
477 | 10 | 10/0 | DD60+18 | DRY | Pipe | 15.06.25 | Bhati Const
478 | 11 | 17/4 | DA+3 | DFR | CP | 04.06.25 | Shree Ram Enterprises
July'25
479 | 1 | 25/2 | DA+0 | DRY | Pipe | 04.07.25 | Rabit Brite
480 | 2 | 28/7 | DA+0 | Sandy | Pipe | 19.07.25 | Vishwakarma Construction
481 | 3 | 8/0 | DA+3 | DRY | Pipe | 31.07.25 | Dhakad | Dhakad Enter.
482 | 4 | 18/0 | DB2+0 | SANDY | Pipe | 17.07.25 | MR Choudary
483 | 5 | 18/1 | DA+0 | DRY | Pipe | 29.07.25 | Vishwakarma Construction
484 | 6 | 18/2 | DA+3 | DRY | Pipe | 18.07.25 | Vishwakarma Construction
485 | 7 | 18/3 | DA+3 | DRY | Pipe | 21.07.25 | Vishwakarma Construction
486 | 8 | 8/12 | DA+0 | DRY | Pipe | 18.07.25 | JSR
487 | 9 | 21/0 | DD45+3 | DRY | Pipe | 24.07.25 | Shree Ram Ent
488 | 10 | 4/4 | DA+0 | DRY | Pipe | 08.07.25 | Nice Security & Services
489 | 11 | 5/0 | DB1+9 RC | DRY | Pipe | 08.07.25 | Nice Security & Services
490 | 12 | 18/9 | DA+0 | DRY | Pipe | 29.07.25 | MR Choudary
Aug'25
491 | 1 | 18/8 | DA+3 | DRY | Pipe | 04.08.25 | MR Choudary
492 | 2 | 20/0 | DD45+3 RC | DRY | Pipe | 14.08.25 | Shree Ram Enterprises
493 | 3 | 22/0 | DC2+9 | DFR | CP | 18.08.25 | YMK Construction
494 | 4 | 23/9 | DA+6 | DRY | Pipe | 20.08.25 | YMK Construction
495 | 5 | 10/17 | DA+3 | DRY | Pipe | 19.08.25 | JSR
496 | 6 | 6/0 | DB2+9 | DRY | Pipe | 01.08.25 | Nice security & Service
497 | 7 | 9/0 | DD60+18 | DRY | Pipe | 01.08.25 | JSR
498 | 8 | 23/4 | DA+3 | DFR | CP | 01.08.25 | YMK Construction
499 | 9 | 28/6 | DA+9 RC | SANDY | Pipe | 01.08.25 | Vishwakarma Construction
500 | 10 | 18/4 | DA+3 | Sandy | Pipe | 25.08.25 | Vishwakarma Construction
501 | 11 | 11/1 | DA+6 | SANDY | Pipe | 29.08.25 | OM Const
502 | 12 | 10/1 | DA+3 | DRY | Pipe | 04.08.25 | JSR
503 | 13 | 8/5 | DA+3 | DRY | Pipe | 03.08.25 | Yes Infra
504 | 14 | 8/4 | DA+0 | DRY | Pipe | 03.08.25 | JSR
505 | 15 | 18/6 | DA+3 | DRY | Pipe | 28.08.25 | Vishwakarma Construction
506 | 16 | 18/5 | DA+3 | DRY | Pipe | 31.08.25 | Vishwakarma Construction
Sept'25
507 | 1 | 18/10 | DA+3 | SANDY | Pipe | 02.09.25 | Vishwakarma Construction
508 | 2 | 10/23 | DA+9 | Sandy | Pipe | 29.09.25 | OM Const
509 | 3 | 7/0 | DB1+0 | DRY | Pipe | 24.09.25 | Dhakad Ent
510 | 4 | 10/15 | DA+3 | DRY | Pipe | 24.09.25 | JSR
511 | 5 | 11/0 | DB1+0 | Sandy | Pipe | 24.09.25 | OM Const
512 | 6 | 10/16 | DA+3 | DRY | Pipe | 24.09.25 | JSR
513 | 7 | 19/1 | DA+6 | DRY | Pipe | 09.09.25 | Vishwakarma Construction
514 | 8 | 19/0 | DC1+0 | DFR | CP | 03.09.25 | MR Choudary
515 | 9 | 18/7 | DA+6 | DRY | Pipe | 22.09.25 | Vishwakarma Construction
516 | 10 | 4/2 | DA+0 | DRY | Pipe | 29.09.25 | JSR
Oct'25
517 | 1 | 17/2 | DA+3 | DRY | Pipe | 24.10.25 | Vishwakarama
518 | 2 | 8/3 | DA+3 | DRY | Pipe | 19.10.25 | JSR
519 | 4 | 19/8 | DB1+6 | DRY | Pipe | 11.10.25 | Vishwakarma
520 | 5 | 19/10 | DA+9 | SANDY | Pipe | 12.10.25 | Vishwakarma
521 | 6 | 19/11 | DA+9 RC | SANDY | Pipe | 26.10.25 | Vishwakarma
Dec'25
522 | 1 | 19/12 | DB1+3 | SANDY | Pipe | 14.12.25 | Vishwakarma Construction
Feb'26
523 | 1 | 10/2 | DA+0 | DFR | CP | 08.02.26 | JSR

## Benching Status-G
RC, Benching & Revetment Locations
Sl No. | RC | Loc No. | Tower Type | CP Position Up/Down | Raised Chimney | Chimney Extension |  |  |  | Submitted Benching Volume (Cum) |  | Approved Benching Volume (Cum) |  | Approval Date | JMC NO | JMC Date
[6 empty] | A | B | C | D | Cutting | Filling | Cutting | Filling
1 |  | 1/0 | DE+0 |  | 283.2 |  |  |  | 1 | 111.651 |  | 89.5
2 |  | 1A/0 | DD60+0 |  | 284.927 |  |  |  |  | 270.309 |  | 265.381
3 |  | 1A/1 | DA+0 |  | 292.179 |  |  | 2 | 1 | 46.489 |  | 22.529
4 |  | 1A/3 | DA+0 |  | 281.458 |  |  | 1 |  | 45.554 |  | 45.554
5 |  | 1A/4 | DA+3 |  | 281.508 | 1 |  |  |  | 81.372 |  | 64.075
6 |  | 1A/5 | DA+6 |  | 288.539 |  | 1 |  |  | 88.77 |  | 88.77
7 |  | 2/0 | DC1+0 |  | 277.997 | 1 | 1 |  | 2 | 69.275 |  | 35.55
8 |  | 2/2 | DA+0 |  | 282.591 |  |  | 1 | 1 |  |  | 140.97
9 |  | 2/3 | DA+0 |  | 293.068 | 1 | 1 |  |  |  |  | 22.61
10 |  | 2/4 | DA+3 |  | 294.942 | [6 empty] | 28.01
11 |  | 2/5 | DA+3 |  | 295.491 |  | 1 | 1 |  |  |  | 53.49
12 |  | 2/6 | DA+6 |  | 288.339 |  | 2 |  |  |  |  | 107.54
13 |  | 2/7 | DA+6 |  | 283.557 |  |  | 1 |  |  |  | 209.95
14 |  | 5/0 | DB1+9 |  | 276.283 | 2 | 2 | 2 | 2
15 |  | 6/0 | DB2+9 |  | 278.494 | 2 | 2 | 2 | 2
16 |  | 6/1 | DA+0 |  | 286.666 | 1 | [5 empty] | 53.48
17 |  | 8/3 | DA+3 |  | 273.914 |  |  |  | 1 |  |  | 42.94
18 |  | 8/4 | DA+0 |  | 276.398 | 1 | 1 | 1 | 2 |  |  | 14.89
19 |  | 8/5 | DA+3 |  | 278.586 | [6 empty] | 35.69
20 |  | 8/9 | DA+3 |  | 271.848 | [6 empty] | 42.16
21 |  | 10/1 | DA+3 |  | 260.835 | [6 empty] | 74.8
22 |  | 10/22 | DA+0 |  | 258.665 | 1 | 4 |  |  |  |  | 60.5
23 |  | 10/23 | DA+9 |  | 265.711 | 2 | 6 | 1 | 1 |  |  | 30.7
24 |  | 11/0 | DB1+0 |  | 282.363 | 2 | 4 |  | 3 | 415.644 |  | 213.823
25 |  | 11/1 | DA+6 |  | 280.588 |  | 2 |  |  | 260.613 |  | 159.329
26 |  | 11/2 | DA+9 | +2.0 | 260.522 |  |  | 2 |  | 101.072
27 |  | 11/5 | DA+3 |  | 249.129 | 1 | 1 |  | 1 | 58.783 |  | 58.783
28 |  | 11/7 | DA+3 |  | 244.613 |  |  |  |  | 87.852 |  | 64.41
29 |  | 11/11 | DA+0 |  | 251.55 |  | 1 |  |  | 31.471 |  | 18.401
30 |  | 11/12 | DA+0 |  | 261.411 | 2 | 3 | 1 | 4 | 171.833 |  | 79.75
31 |  | 11/13 | DA+0 |  | 260.743 |  | 2 | 4 | 1 | 146.701 |  | 89.319
32 |  | 15/2 | DA+9 |  | 262.781 |  |  |  | 1 | 251.127
33 |  | 15/4 | DA+3 | -0.26 | 256.602 | 1 |  |  | 1 | 216.018
34 |  | 15/5 | DA+3 | -0.3 | 254.329 |  |  |  |  | 192.519
35 |  | 15/6 | DA+0 |  | 254.201 |  |  |  | 1
36 |  | 15/9 | DA+9 | -0.2 | 244.162 |  |  |  |  | 284.108 |  | 284.108
37 |  | 17/0 | DC1+0 | -0.259 | 233.247 |  |  |  |  | 313.985 |  | 313.985
38 |  | 19/5 | DA+3 | -0.2 | 225.461 |  |  |  |  | 133.718
39 |  | 19/9 | DA+3 |  | 230.844 |  |  |  | 1 | 79.945 |  | 41.176
40 |  | 19/10 | DA+9 | +0.40 | 238.735 |  | 2 | 2 |  | 286.553 |  | 200.737
41 |  | 19/11 | DA+9 |  | 229.954 | 3 | 3 | 4 | 5 | 146.352 |  | 60.478
42 |  | 19/12 | DB1+3 | -0.3 | 232.477 |  |  |  |  | 190.49
43 |  | 19/13 | DA+0 |  | 239.958 | 1 |  | 1 | 3 | 97.224
44 |  | 19/14 | DA+9 |  | 220.157 | 2 | 2 | 2 | 2
45 |  | 20/0 | DD45+3 |  | 219.856 | 2 | 2 | 2 | 2
46 |  | 21/0 | DD45+3 |  | 221.061 | 2 | 2 | 2 | 2
47 |  | 21/2 | DA+3 |  | 220.023 |  |  | 1 |  |  |  | 13.878
48 |  | 21/5 | DA+3 |  | 230.575 |  |  |  | 2 |  |  | 175.845
49 |  | 21/10 | DA+9 |  | 220.959 | 1 | 1 |  |  |  |  | 127.123
50 |  | 21/12 | DA+9 |  | 213.707 |  |  | 1 |  |  |  | 80.099
51 |  | 22/6 | DA+6 |  | 222.31 |  |  | 2 | 1 |  |  | 249.598
52 |  | 22/9 | DA+6 |  | 215.194 |  |  |  | 1 |  |  | 176.873
53 |  | 23/0 | DB2+0 |  | 216.588 |  | 1 |  |  |  |  | 344.386
54 |  | 23/1 | DA+0 |  | 217.383 | [6 empty] | 76.44
55 |  | 23/3 | DA+0 |  | 209.564 | [6 empty] | 33.81
56 |  | 23/6 | DA+6 |  | 209.953 | [6 empty] | 95.149
57 |  | 23/7 | DA+9 |  | 210.067 | 1 |  |  | 2 |  |  | 212.812
58 |  | 23/8 | DA+9 |  | 214.619 | 1 | 1 |  |  |  |  | 119.029
59 |  | 23/11 | DA+6 |  | 205.245 |  |  | 1 |  |  |  | 107.373
60 |  | 24/6 | DA+0 |  | 199.363 | 1 | [5 empty] | 20.536
61 |  | 25/2 | DA+0 |  | 199.276 | [6 empty] | 18.102
62 |  | 25/3 | DA+0 |  | 204.419 |  | 2 | 1 |  |  |  | 35.283
63 |  | 25/4 | DA+0 |  | 211.057 |  | 4 | 1 |  |  |  | 89.487
64 |  | 25/5 | DA+3 |  | 196.919 | 1 | [5 empty] | 4.275
65 |  | 25/7 | DA+9 |  | 197.874 | 4 | 3 | 3 | 3 |  |  | 147.9
66 |  | 25/8 | DA+9 |  | 196.169 | 4 | 4 | 4 | 4
67 |  | 26/1 | DA+3 |  | 194.336 |  | 1 | 1 |  |  |  | 163.295
68 |  | 26/2 | DA+3 |  | 204.39 |  | 2 | 3 |  |  |  | 120.131
69 |  | 26/3 | DA+0 |  | 199.985 | [6 empty] | 96.398
70 |  | 26/4 | DA+9 |  | 211.694 | 3 | 2 |  |  |  |  | 144.135
71 |  | 26/5 | DA+9 |  | 215.139 | 2 |  |  | 2 |  |  | 55.001
72 |  | 26/6 | DA+0 |  | 232.988 | 2 |  |  | 1 |  |  | 19.091
73 |  | 26/7 | DA+3 |  | 226.695 | 1 |  |  | 3 |  |  | 125.856
74 |  | 27/0 | DC2+9 |  | 230.165 | 1 | 1 | 1 | 1
75 |  | 27/1 | DB1+9 |  | 193.814 | 3 | 3 | 4 | 5 |  |  | 101.296
76 |  | 27/2 | DA+0 |  | 195.143 | 1 | 1 |  | 4 |  |  | 14.985
77 |  | 27/3 | DA+0 |  | 200.227 |  | 2 | 1 |  |  |  | 6.861
78 |  | 27/4 | DA+0 |  | 186.708 |  | 1 |  |  |  |  | 59.376
79 |  | 28/2 | DA+3 |  | 188.585 | 3 |  |  | 1 |  |  | 188.65
80 |  | 28/3 | DA+0 |  | 200.905 |  | 4 | 2 |  |  |  | 181.214
81 |  | 28/4 | DA+9 |  | 214.608 | 1 | 2 |  |  |  |  | 254.325
82 |  | 28/5 | DA+9 | +1.50 | 224.16 | 2 | 5 | 1 | 6 |  |  | 47.37
83 |  | 28/6 | DA+9 |  | 231.09 | 1 | 6 | 1 | 6 |  |  | 54.06
84 |  | 28/7 | DA+0 | +1.50 | 227.988 | 3 |  | 1 | 4 |  |  | 37.941
85 |  | 28/8 | DA+3 |  | 215.595 |  | 1 | 5 |  |  |  | 83.417
86 |  | 28/9 | DA+0 |  | 191.987 | 1 | [5 empty] | 55.11
87 |  | 29/1 | DA+6 |  | 188.345 | 1 |  |  | 1 |  |  | 47.646
88 |  | 29/2 | DA+9 |  | 185.168 |  |  | 1 |  |  |  | 62.028
89 |  | 29/3 | DA+6 |  | 193.792 | [6 empty] | 90.346
90 |  | 29/4 | DA+3 |  | 186.212 | [6 empty] | 21.694
91 |  | 29/5 | DA+0 |  | 187.91 |  |  |  | 1 |  |  | 65.361
92 |  | 29/6 | DA+6 |  | 190.634 | 1 | [5 empty] | 134.118
93 |  | 29/7 | DA+3 |  | 190.55 | [6 empty] | 52.112
94 |  | 29/9 | DA+3 | -0.3 | 212.98 | 2 | 2 |  |  |  |  | 160.976
95 |  | 29/10 | DA+6 |  | 209.64 |  | 2 |  |  |  |  | 228.019
96 |  | 30/0 | DC2+0 |  | 198.561 | [6 empty] | 79.968
97 |  | 30/1 | DA+3 |  | 193.604 | 1 | 1 |  |  |  |  | 180.464
98 |  | 30/2 | DA+0 |  | 186.707 | [6 empty] | 18.704
99 |  | 31/1 | DA+9 |  | 192.96 | 3 | 3 | 3 | 3
100 |  | 31/2 | DA+0 |  | 199.667 | 1 | 2 | 1 |  |  |  | 71.277
101 |  | 31/4 | DA+9 |  | 191.583 |  |  |  | 1 |  |  | 24.208
102 |  | 32/2 | DA+0 |  | 188.887 | 1 | [5 empty] | 171.008
103 |  | 32/3 | DA+3 |  | 197.975 |  | 2 |  |  |  |  | 11.533
104 |  | 32/4 | DA+0 |  | 192.965 | 3 | 2 |  | 1
105 |  | 32/8 | DA+9 |  | 190.999 | [6 empty] | 48.832
106 |  | 33/0 | DB2+3 |  | 214.154 | 2 |  |  | 4 |  |  | 222.533
107 |  | 33/1 | DA+0 |  |  | 0 | 0 | 0 | 0 | 352.48 |  | 200.16 |  |  | JMC-1 | 13.03.24
108 | Y | 33/2 | DA+0 |  |  | 1 | 1 | 0 | 0 | 492.78 |  | 226.416
109 | Y | 33/3 | DA+0 |  |  | 2 | 0 | 0 | 2 | 151.2 |  | 77.104
110 | Y | 33/4 | DA+0 | -0.4 |  | 1 | 4 | 0 | 0 | 243.1 |  | 88.432
111 | Y | 33/6 | DA+6 |  |  | 0 | 0 | 4 | 4 | 214.88 |  | 156.032
112 | Y | 33/7 | DA+9 |  |  | 3 | 1 | 0 | 0 | 645.745 |  | 359.696
113 | Y | 33/8 | DA+3 |  |  | 1 | 0 | 1 | 3 | 265.799 |  | 78.225
114 | Y | 34/0 | DB1+6 |  |  | 0 | 0 | 2 | 1 | 564.394 |  | 359.682 |  | 2023-12-29
115 | Y | 34/1 | DA+3 | 0.3 |  | 2 | 0 | 2 | 3 | 256.233 |  | 50.319
116 | Y | 34/2 | DA+9 |  |  | 0 | 0 | 0 | 1 | 32.451 |  | 5.505
117 | Y | 34/3 | DA+9 | 1 |  | 0 | 0 | 3 | 6 | 1134.87 |  | 452.318
118 | Y | 34/4 | DA+6 |  |  | 1 | 3 | 1 | 0 | 313.904 |  | 87.476
119 |  | 34/5 | DCT+0 | -0.5 |  | 0 | 0 | 0 | 0 | 361.8
120 | Y | 34/6 | DA+6 |  |  | 1 | 0 | 0 | 1 | 220.4 |  | 71.358
121 | Y | 35/0 | DB2+0 |  |  | 1 | 3 | 1 | 0 | 467.993 |  | 256.377 |  | 2023-12-29
122 | Y | 35/1 | DA+0 |  |  | 0 | 3 | 0 | 0 | 69.549 |  | 21.863
123 | Y | 35/2 | DA+0 |  |  | 1 | 3 | 0 | 0 | 44.623 |  | 5.323
124 | Y | 35/3 | DA+0 |  |  | 2 | 0 | 0 | 4 | 419.263 |  | 157.798
125 | Y | 35/4 | DA+3 |  |  | 0 | 3 | 2 | 0 | 116.817 |  | 36.068
126 | Y | 35/5 | DA+0 | 0.4 |  | 0 | 3 | 1 | 0 | 703.989 |  | 299.892
127 | Y | 35/6 | DA+9 |  |  | 0 | 2 | 0 | 0 | 401.023 |  | 155.645
128 | Y | 35/7 | DA+3 |  |  | 1 | 0 | 0 | 3 | 368.217 |  | 241.532
129 | Y | 35/8 | DA+0 |  |  | 1 | 3 | 0 | 0 | 39.017 |  | 9.15
130 | Y | 35/9 | DA+0 |  |  | 0 | 2 | 0 | 0 | 147.994 |  | 64.4
131 | Y | 36/0 | DD60+18 |  |  | 2 | 0 | 0 | 0 | 162.61 |  | 84.936
132 | Y | 37/0 | DD60+18 |  | 3 | 3 | 3 | 3 | 3 | 1384.198 |  | 1254.084
133 | Y | 37/1 | DA+9 |  | 2 | 4 | 6 | 2 | 2 | 612.6 |  | 400.141
134 |  | 37/2 | DB1+6 |  |  | 0 | 0 | 0 | 0 | 105.717 |  | 98.297 |  |  | JMC-59 | 29-07-24
135 |  | 37/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 62.64 |  | 28.816 |  |  | JMC-60 | 29-07-24
136 | Y | 37/4 | DA+6 |  |  | 2 | 0 | 0 | 3 | 327.85 |  | 144.213 |  |  | JMC-61 | 29-07-24
137 | Y | 37/5 | DA+3 |  |  | 1 | 0 | 0 | 3 | 163.167 |  | 62.312
138 | Y | 37/6 | DA+6 |  |  | 1 | 0 | 0 | 0 | 284.595 |  | 143.717
139 | Y | 37/7 | DA+3 |  |  | 1 | 1 | 0 | 0 | 360.916 |  | 181.161
140 |  | 37/8 | DA+0 |  |  | 0 | 0 | 0 | 0 | 61.657 |  | 13.36
141 | Y | 38/0 | DC1+0 |  |  | 0 | 2 | 0 | 0 | 547.123 |  | 509.174 |  | 2023-12-29
142 | Y | 38/1 | DA+3 |  |  | 0 | 2 | 0 | 0 | 539.139 |  | 361.314 |  |  | JMC-26 | 29-07-24
143 | Y | 38/3 | DA+9 |  |  | 2 | 0 | 0 | 1 | 297.4957 |  | 152.854 |  |  | JMC-27 | 29-07-24
144 | Y | 38/4 | DA+0 |  |  | 1 | 1 | 0 | 2 | 191.745 |  | 48.406
145 | Y | 38/5 | DA+0 |  |  | 2 | 0 | 1 | 2 | 295.659 |  | 71.81
146 | Y | 38/6 | DA+0 |  |  | 0 | 0 | 0 | 1 | 205.829 |  | 79.449 |  |  | JMC-28 | 29-07-24
147 | Y | 38/7 | DA+0 |  |  | 1 | 0 | 0 | 1 | 100.0663 |  | 42.547
148 | Y | 38/8 | DA+0 |  |  | 0 | 1 | 0 | 1 | 159.4651 |  | 51.758 |  |  | JMC-29 | 29-07-24
149 | Y | 38/9 | DB1+6 |  |  | 0 | 0 | 2 | 2 | 411.929 |  | 272.86
150 | Y | 39/0 | DC2+3 |  |  | 2 | 0 | 0 | 2 | 428.739 |  | 280.711 |  | 2023-12-29
151 | Y | 39/1 | DA+6 |  |  | 1 | 2 | 0 | 0 | 427.017 |  | 264.925 |  |  | JMC-30 | 29-07-24
152 | Y | 39/2 | DA+0 |  |  | 0 | 3 | 0 | 0 | 315.583 |  | 127.368
153 | Y | 39/3 | DA+3 |  |  | 1 | 0 | 0 | 1 | 258.267 |  | 154.272 |  |  | JMC-31 | 29-07-24
154 | Y | 39/4 | DA+0 |  |  | 2 | 3 | 0 | 0 | 446.297 |  | 139.368
155 | Y | 39/5 | DA+3 | -1 |  | 0 | 4 | 0 | 3 | 160.354 |  | 34.435
156 | Y | 39/6 | DA+0 |  |  | 0 | 3 | 0 | 3 | 385.92 |  | 46.854
157 | Y | 39/7 | DA+0 |  |  | 0 | 0 | 0 | 3 | 435.806 |  | 187.109
158 | Y | 40/0 | DC2+0 |  |  | 0 | 5 | 2 | 0 | 1250.246 |  | 997.507 |  | 2023-12-29
159 | Y | 40/1 | DA+0 |  |  | 2 | 4 | 0 | 0 | 401.527 |  | 104.013
160 | Y | 40/2 | DB1+9 |  |  | 0 | 2 | 1 | 0 | 501.187 |  | 408.528
161 | Y | 40/3 | DA+3 |  |  | 0 | 1 | 1 | 0 | 236.907 |  | 113.002 |  |  | JMC-32 | 29-07-24
162 | Y | 40/4 | DA+9 |  |  | 0 | 0 | 0 | 1 | 521.072 |  | 489.056 |  |  | JMC-33 | 29-07-24
163 |  | 40/5 | DB1+9 |  |  | 0 | 0 | 0 | 0 | 354.1 |  | 349.912 |  |  | JMC-4 | 22.03.24
164 | Y | 40/6 | DA+3 |  |  | 1 | 0 | 0 | 2 | 154.883 |  | 79.128 |  |  | JMC-34 | 29-07-24
165 | Y | 40/7 | DA+3 |  |  | 1 | 4 | 1 | 4 | 221.71 |  | 37.48
166 | Y | 40/8 | DA+0 |  |  | 0 | 4 | 0 | 0 | 630.783 |  | 331.389
167 | Y | 40/9 | DA+0 |  |  | 0 | 6 | 1 | 2 | 133.683 |  | 21.333
168 | Y | 40/11 | DA+9 |  |  | 1 | 0 | 0 | 0 | 104.4 |  | 58 |  |  | JMC-5 | 22.03.24
169 | Y | 40/12 | DA+0 |  |  | 2 | 0 | 0 | 5 | 599.16 |  | 200.901
170 | Y | 41/0 | DB1+0 |  |  | 0 | 1 | 1 | 0 | 299.222 |  | 165.175 |  | 2023-12-29
171 | Y | 41/1 | DA+3 |  |  | 0 | 0 | 0 | 3 | 338.21 |  | 51.94 |  | 2023-09-12
172 | Y | 41/2 | DA+0 | -0.5 |  | 1 | 0 | 1 | 3 | 290.62 | 38.76 | 67.854 |  | 2023-09-12
173 | Y | 41/3 | DA+0 |  |  | 0 | 0 | 1 | 1 | 41.922 |  | 41.922 |  | 2023-09-12
174 | Y | 41/4 | DA+0 |  |  | 0 | 1 | 0 | 1 | 38.232 |  | 38.232 |  | 2023-09-12 | JMC-35 | 29-07-24
175 | Y | 41/5 | DA+0 |  |  | 0 | 0 | 1 | 1 | 128.736 | 56.312 | 35 |  | 2023-09-12 | JMC-36 | 29-07-24
176 | Y | 41/6 | DA+0 |  |  | 2 | 0 | 0 | 1 | 213.714 |  | 57.698 |  | 2023-09-12 | JMC-37 | 29-07-24
177 | Y | 41/8 | DA+0 |  |  | 0 | 2 | 1 | 0 | 30.774 |  | 30.774 |  | 2023-09-12 | JMC-6 | 22.03.24
178 | Y | 41/9 | DA+0 |  |  | 0 | 2 | 2 | 2 | 168.2 |  | 45.88 |  | 2023-09-12 | JMC-7 | 22.03.24
179 | Y | 41/12 | DA+3 |  |  | 1 | 0 | 0 | 0 | 152.648 | 28.888 | 66.766 |  | 2023-09-12 | JMC-8 | 22.03.24
180 | Y | 42/0 | DC2+9 |  |  | 0 | 0 | 0 | 1 | 442.886 |  | 408.487 |  | 2023-12-29
181 | Y | 43/0 | DB2+9 |  |  | 0 | 3 | 0 | 3 | 254.434 |  | 132.326 |  | 2023-12-29
182 |  | 43/1 | DA+9 |  |  | 0 | 0 | 0 | 0 | 94.646 |  | 34.848 |  | 2023-09-12 | JMC-2 | 13.03.24
183 | Y | 43/2 | DA+9 |  |  | 1 | 0 | 0 | 1 | 266.086 | 72.72 | 146.712 |  | 2023-09-12 | JMC-38 | 29-07-24
184 | Y | 43/3 | DA+3 | 0.21 |  | 1 | 0 | 1 | 2 | 212.394 |  | 89.962 |  | 2023-09-12 | JMC-39 | 29-07-24
185 | Y | 43/6 | DA+6 |  |  | 1 | 1 | 0 | 2 | 128.022 |  | 56.258 |  | 2023-09-12
186 | Y | 44/0 | DB1+0 |  |  | 0 | 1 | 0 | 0 | 46.923 |  | 23.625 |  | 2023-12-29
187 |  | 45/0 | DD60+18
188 |  | 46/0 | DD60+18
189 | Y | 46/1 | DA+6 |  |  | 0 | 1 | 0 | 0 | 161.416 |  | 48.006 |  | 2023-09-12
190 |  | 46/2 | DA+0 | 0.3 |  | 0 | 0 | 0 | 0 | 226.73 |  | 168.6 |  | 2023-09-12 | JMC-3 | 13.03.24
191 |  | 46/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 113.754 |  | 44.602 |  | 2023-09-12 | JMC-40 | 29-07-24
192 | Y | 46/4 | DA+0 |  |  | 0 | 2 | 0 | 3 | 168.612 |  | 96.296 |  | 2023-09-12 | JMC-41 | 29-07-24
193 | Y | 50/1 | DA+0 |  |  | 2 | 0 | 0 | 0 | 87.804
194 | Y | 51/6 | DA+0 |  |  | 1 | 0 | 0 | 0
195 | Y | 52/3 | DA+0 |  |  | 0 | 3 | 1 | 0 | 866.16 |  |  |  |  | JMC-42 | 29-07-24
196 | Y | 53/1 | DA+0 |  | 1 | 1 | 1 | 1 | 1
197 | Y | 72/6 | DA+0 |  |  | 1 | 1 | 1 | 1
198 | Y | 72/7 | DB1+9 |  |  | 1 | 1 | 1 | 1
Note on G47: ====== ID#AAAByZTrI9A PARMANAND KUMAR (2026-01-08 04:51:09) Loc. Is spoting on Top of Pond Bund (Benching Not Final)

## Revetment Pkg-G
Revetment work
SI. No | Loc No | Tower Type | Dt. of Start | Dt. of complete | Random Rubble stone masonry including excavation (1:5 Cement concrete) | Excavation Volume | Back filling and levelling of volumes enclosed by revetment. | M15 Conc Nominal Mix 1:2:4 for top seal cover | M10 (PEDDING -PCC)
1 | 35/5 | DA+0 RC | 20.11.24 | 24.12.24 | 83 | 17.19 | 282.1 | 0.37 | 2.73
Total |  |  |  |  | 83 |  | 282.1 | 0.37 | 2.73

## Erection Compiled
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Erection
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Starting Date | Completion Date | Gang Name | Status | Tower Weight
2023-09-01
1 | 1 | 57/9 | DA+0 | 13.09.23 | 21.09.23 | Sobha Devi | Complete | 37.504
2 | 2 | 58/12 | DA+0 | 18.09.23 | 25.09.23 | Sunny Const | Complete | 37.504
3 | 3 | 57/11 | DA+0 | 21.09.23 | 26.09.23 | Sobha Devi | Complete | 37.504
| 2023-10-01 | [7 empty] | 112.512
4 | 1 | 58/14 | DA+0 | 25.09.23 | 01.10.23 | Sunny Const | Complete | 37.504
5 | 2 | 57/13 | DA+0 | 26.09.23 | 01.10.23 | Sobha Devi | Complete | 37.504
6 | 3 | 57/10 | DA+0 | 01.10.23 | 06.10.23 | Sobha Devi | Complete | 37.504
7 | 4 | 58/9 | DA+0 | 01.10.23 | 07.10.23 | Sunny Const | Complete | 37.504
8 | 5 | 52/1 | DA+0 | 03.10.23 | 10.10.23 | Suraj const | Complete | 37.504
9 | 6 | 57/12 | DA+3 | 06.10.23 | 11.10.23 | Sobha Devi | Complete | 38.847
10 | 7 | 58/8 | DA+0 | 7.10.23 | 11.10.23 | Sunny Const | Complete | 37.504
11 | 8 | 58/1 | DA+0 | 25.09.23 | 12.10.23 | Ganesh Kr. Sinha | Complete | 37.504
12 | 9 | 57/2 | DA+0 | 10.10.23 | 16.10.23 | Sobha Devi | Complete | 37.504
13 | 10 | 51/2 | DA+0 | 10.10.23 | 15.10.23 | Suraj const | Complete | 37.504
14 | 11 | 58/16 | DA+0 | 10.10.23 | 17.10.23 | Sunny Const | Complete | 37.504
15 | 12 | 57/3 | DA+0 | 15.10.23 | 20.10.23 | Sobha Devi | Complete | 37.504
16 | 13 | 51/4 | DA+3 | 15.10.23 | 21.10.23 | Suraj const | Complete | 38.847
17 | 14 | 58/3 | DA+3 | 12.10.23 | 22.10.23 | Ganesh Kr. Sinha | Complete | 38.847
18 | 15 | 58/10 | DA+3 | 17.10.23 | 23.10.23 | Sunny Const | Complete | 38.847
19 | 16 | 57/4 | DA+0 | 20.10.23 | 26.10.23 | Sobha Devi | Complete | 37.504
20 | 17 | 51/5 | DA+0 | 20.10.23 | 29.10.23 | Suraj const | Complete | 37.504
21 | 18 | 57/5 | DA+3 | 26.10.23 | 30.10.23 | Sobha Devi | Complete | 38.847
22 | 19 | 58/5 | DA+3 | 20.10.23 | 31.10.23 | Ganesh Kr. Sinha | Complete | 38.847
23 | 20 | 58/11 | DA+3 | 23.10.23 | 31.10.23 | Sunny Const | Complete | 38.847
| 2023-11-01 | [7 empty] | 759.481
24 | 1 | 57/8 | DA+3 | 30.10.23 | 03.11.2023 | Sobha Devi | Complete | 38.847
25 | 2 | 51/7 | DA+3 | 29.10.23 | 04.11.2023 | Suraj const | Complete | 38.847
26 | 3 | 59/6 | DA+0 | 31.10.23 | 07.11.2023 | Sunny Const | Complete | 37.504
27 | 4 | 57/7 | DA+3 | 03.11.23 | 07.11.2023 | Sobha Devi | Complete | 38.847
28 | 5 | 51/3 | DA+0 | 04.11.23 | 09.11.2023 | Suraj const | Complete | 37.504
29 | 6 | 58/4 | DA+0 | 31.10.23 | 11.11.2023 | Ganesh Kr. Sinha | Complete | 37.504
30 | 7 | 57/1 | DA+3 | 07.11.23 | 13.11.2023 | Sobha Devi | Complete | 38.847
31 | 8 | 59/5 | DA+0 | 07.11.23 | 13.11.2023 | Sunny Const | Complete | 37.504
32 | 9 | 51/10 | DA+3 | 10.11.23 | 14.11.2023 | Suraj const | Complete | 38.847
33 | 10 | 56/9 | DA+3 | 13.11.23 | 16.11.2023 | Sobha Devi | Complete | 38.847
34 | 11 | 59/3 | DA+0 | 13.11.23 | 18.11.2023 | Sunny Const | Complete | 37.504
35 | 12 | 52/2 | DA+3 | 15.11.23 | 19.11.2023 | Suraj const | Complete | 38.847
36 | 13 | 55/7 | DA+0 | 15.11.23 | 21.11.2023 | Chinta devi | Complete | 37.504
37 | 14 | 58/6 | DA+3 | 13.11.23 | 21.11.2023 | Ganesh Kr. Sinha | Complete | 38.847
38 | 15 | 56/8 | DA+3 | 16.11.23 | 21.11.2023 | Sobha Devi | Complete | 38.847
39 | 16 | 59/2 | DA+0 | 18.11.23 | 24.11.2023 | Sunny Const | Complete | 37.504
40 | 17 | 52/5 | DA+3 | 19.11.23 | 24.11.2023 | Suraj const | Complete | 38.847
41 | 18 | 56/7 | DA+3 | 22.11.23 | 24.11.2023 | Sobha Devi | Complete | 38.847
42 | 19 | 55/5 | DA+0 | 22.11.23 | 26.11.2023 | Chinta devi | Complete | 37.504
43 | 20 | 56/3 | DA+0 | 24.11.23 | 29.11.23 | Sobha Devi | Complete | 37.504
44 | 21 | 53/3 | DA+3 | 24.11.23 | 29.11.23 | Suraj const | Complete | 38.847
45 | 22 | 59/1 | DA+0 | 24.11.23 | 30.11.23 | Sunny Const | Complete | 37.504
| 2023-12-01 | [7 empty] | 841.204
46 | 1 | 50/4 | DA+3 | 22.11.23 | 01.12.23 | Ganesh Kr. Sinha | Complete | 38.847
47 | 2 | 55/4 | DA+3 | 27.11.23 | 02.12.23 | Chinta devi | Complete | 38.847
48 | 3 | 56/4 | DA+3 | 29.11.23 | 02.12.23 | Sobha Devi | Complete | 38.847
49 | 4 | 53/4 | DA+3 | 29.11.23 | 03.12.23 | Suraj const | Complete | 38.847
50 | 5 | 58/15 | DA+3 | 30.11.23 | 06.12.23 | Sunny Const | Complete | 38.847
51 | 6 | 56/2 | DA+3 | 02.12.23 | 06.12.23 | Sobha Devi | Complete | 38.847
52 | 7 | 55/6 | DA+3 | 02.12.23 | 07.12.23 | Chinta devi | Complete | 38.847
53 | 8 | 48/1 | DA+0 | 02.12.23 | 09.12.23 | Ganesh Kr. Sinha | Complete | 37.504
54 | 9 | 55/1 | DA+3 | 03.12.23 | 09.12.23 | Suraj const | Complete | 38.847
55 | 10 | 55/9 | DA+3 | 07.12.23 | 12.12.23 | Chinta devi | Complete | 38.847
56 | 11 | 57/6 | DB+0 | 06.12.23 | 13.12.23 | Sobha Devi | Complete | 57.597
57 | 12 | 61/2 | DA+0 | 06.12.23 | 14.12.23 | Sunny Const | Complete | 37.504
58 | 13 | 55/2 | DA+3 | 09.12.23 | 15.12.23 | Suraj const | Complete | 38.847
59 | 14 | 48/2 | DA+3 | 09.12.23 | 16.12.23 | Ganesh Kr. Sinha | Complete | 38.847
60 | 15 | 55/10 | DA+3 | 12.12.23 | 17.12.23 | Chinta devi | Complete | 38.847
61 | 16 | 57/0 | DB+0 | 13.12.23 | 19.12.23 | Sobha Devi | Complete | 57.597
62 | 17 | 55/3 | DA+0 | 16.12.23 | 19.12.23 | Suraj const | Complete | 37.504
63 | 18 | 61/1 | DA+0 | 14.12.23 | 20.12.23 | Sunny Const | Complete | 37.504
64 | 19 | 50/3 | DA+0 | 16.12.23 | 22.12.23 | Ganesh Kr. Sinha | Complete | 37.504
65 | 20 | 55/11 | DA+3 | 17.12.23 | 22.12.23 | Chinta devi | Complete | 38.847
66 | 21 | 56/5 | DA+0 | 20.12.23 | 24.12.23 | Sobha Devi | Complete | 37.504
67 | 22 | 52/4 | DA+0 | 20.12.23 | 24.12.23 | Suraj const | Complete | 37.504
68 | 23 | 55/8 | DA+3 | 22.12.23 | 28.12.23 | Chinta devi | Complete | 38.847
69 | 24 | 56/6 | DA+3 | 24.12.23 | 28.12.23 | Sobha Devi | Complete | 38.847
70 | 25 | 59/0 | DB+0 | 07.12.23 | 29.12.23 | Sunny Const | Complete | 57.597
71 | 26 | 47/3 | DA+0 | 22.12.23 | 29.12.23 | Ganesh Kr. Sinha | Complete | 37.504
72 | 27 | 51/9 | DA+3 | 24.12.23 | 29.12.23 | Suraj const | Complete | 38.847
| 2024-01-01 | [7 empty] | 1094.375
73 | 1 | 56/0 | DB+0 | 28.12.23 | 05.01.24 | Sobha Devi | Complete | 57.597
74 | 2 | 44/2 | DA+0 | 28.12.23 | 05.01.24 | Chinta devi | Complete | 37.504
75 | 3 | 51/8 | DA+3 | 29.12.23 | 06.01.24 | Suraj const | Complete | 38.847
76 | 4 | 47/2 | DA+0 | 29.12.23 | 07.01.24 | Ganesh Kr. Sinha | Complete | 37.504
77 | 5 | 58/7 | DB+0 | 29.12.23 | 09.01.24 | Sunny Const | Complete | 57.597
78 | 6 | 44/4 | DA+0 | 05.01.24 | 09.01.24 | Chinta devi | Complete | 37.504
79 | 7 | 53/2 | DA+3 | 06.01.24 | 11.01.24 | Suraj const | Complete | 38.847
80 | 8 | 41/11 | DA+3 | 05.01.24 | 12.01.24 | Sobha Devi | Complete | 38.847
81 | 9 | 44/3 | DA+3 | 09.01.24 | 15.01.24 | Chinta devi | Complete | 38.847
82 | 10 | 41/10 | DA+3 | 12.10.23 | 16.01.24 | Sobha Devi | Complete | 38.847
83 | 11 | 48/0 | DB+0 | 07.01.24 | 19.01.24 | Ganesh Kr. Sinha | Complete | 57.597
84 | 12 | 46/3 | DA+0 | 12.01.24 | 19.01.24 | Sunny Const | Complete | 37.504
85 | 13 | 51/6 | DA+0 | 12.01.24 | 19.01.24 | Suraj const | Complete | 37.504
86 | 14 | 41/7 | DA+3 | 16.01.24 | 20.01.24 | Sobha Devi | Complete | 38.847
87 | 15 | 43/4 | DA+9 | 15.01.24 | 22.01.24 | Chinta devi | Complete | 47.184
88 | 16 | 43/5 | DA+0 | 22.1.24 | 27.01.24 | Chinta devi | Complete | 37.504
89 | 17 | 47/0 | DB+0 | 20.01.24 | 28.01.24 | Sunny Const | Complete | 57.597
90 | 18 | 51/0 | DB+0 | 20.01.24 | 28.01.24 | Ganesh Kr. Sinha | Complete | 57.597
91 | 19 | 52/0 | DB+0 | 20.01.24 | 28.01.24 | Suraj const | Complete | 57.597
92 | 20 | 43/1 | DA+9 | 23.01.24 | 28.01.24 | Sobha Devi | Complete | 47.184
93 | 21 | 41/5 | DA+0 | 28.01.24 | 31.01.24 | Sobha Devi | Bottom complete | 37.504
| Feb-24 | [7 empty] | 935.56
94 | 1 | 44/1 | DA+0 | 28.01.24 | 01.02.24 | Chinta devi | Complete | 37.504
95 | 2 | 46/2 | DA+0 | 28.01.24 | 02.02.24 | Sunny Const | Complete | 37.504
96 | 3 | 51/1 | DA+0 | 28.01.24 | 04.02.24 | Ganesh Kr. Sinha | Complete | 37.504
97 | 4 | 41/4 | DA+0 | 01.02.24 | 05.02.24 | Sobha Devi | Complete | 37.504
98 | 5 | 53/1 | DA+0 | 04.02.24 | 09.02.24 | Suraj const | Complete | 37.504
99 | 6 | 41/6 | DA+0 | 07.02.24 | 09.02.24 | Sobha Devi | Complete | 37.504
100 | 7 | 41/8 | DA+0 | 09.02.24 | 13.02.24 | Sobha Devi | Complete | 37.504
101 | 8 | 41/9 | DA+0 | 13.02.24 | 17.02.24 | Sobha Devi | Complete | 37.504
102 | 9 | 29/8 | DA+3 | 2024-02-03 | 2024-02-09 | Tejal Construction | Complete | 38.847
103 | 10 | 29/7 | DA+3 | 2024-02-10 | 2024-02-18 | Tejal Construction | Complete | 38.847
104 | 11 | 29/5 | DA+0 | 2024-02-18 | 2024-02-24 | Tejal Construction | Complete | 37.504
| April'24 | [7 empty] | 415.23
105 | 1 | 55/0 | DC+0 | 28.03.24 | 04.04.24 | Sobha Devi | Complete | 66.381
106 | 2 | 58/0 | DC2+0 | 08.04.24 | 16.04.24 | Sunny Const | Complete | 66.381
107 | 3 | 56/1 | DA+3 | 12.04.24 | 16.04.24 | Sobha Devi | Complete | 38.847
108 | 4 | 53/0 | DC2+3 | 08.04.24 | 18.04.24 | Ganesh Kr. Sinha | Complete | 69.229
| May'24 | [7 empty] | 240.838
109 | 1 | 52/3 | DA+0 | 26.04.24 | 05.05.24 | Ganesh Kr. Sinha | Complete | 37.504
110 | 2 | 58/2 | DA+0 | 05.05.24 | 10.05.24 | Sunny Const | Complete | 37.504
111 | 3 | 65/4 | DA+0 | 10.05.24 | 16.05.24 | Sunny Const | Complete | 37.504
112 | 4 | 65/3 | DA+0 | 16.05.24 | 21.05.24 | Sunny Const | Complete | 37.504
113 | 5 | 65/5 | DA+0 | 16.05.24 | 26.05.24 | Sunny Const | Complete | 37.504
| June'24 | [7 empty] | 187.52
114 | 1 | 29/6 | DA+6 | 2024-05-15 | 2024-06-08 | Departmental Gang |  | 45.413
115 | 2 | 29/9 | DA+3 | 2024-06-10 | 2024-06-24 | Departmental Gang |  | 38.847
| July'24 | [7 empty] | 84.26
116 | 1 | 29/10 | DA+6 | 2024-06-25 | 2024-07-06 | Departmental Gang |  | 45.413
117 | 2 | 31/3 | DA+0 | 2024-07-07 | 2024-07-12 | Departmental Gang |  | 37.504
118 | 3 | 31/2 | DA+0 | 2024-07-13 | 2024-07-22 | Departmental Gang |  | 37.504
| Aug'24 | [7 empty] | 120.421
119 | 1 | 46/4 | DA+0 | 27.08.24 | 30.08.24 | Sobha devi | Complete | 37.504
120 | 2 | 32/5 | DA+6 | 2024-07-22 | 2024-08-01 | Departmental Gang |  | 45.413
121 | 3 | 31/4 | DA+9 | 2024-07-12 | 2024-08-04 | Sanjay Mahto |  | 47.184
122 | 4 | 32/6 | DA+6 | 2024-08-02 | 2024-08-09 | Yogendra Mahto |  | 45.413
123 | 5 | 32/2 | DA+0 | 2024-08-10 | 2024-08-20 | Yogendra Mahto |  | 37.504
| Sept'24 | [7 empty] | 213.018
124 | 1 | 72/3 | DA+0 | 25.08.24 | 01.09.24 | Sunny Const | Complete | 37.504
125 | 2 | 72/4 | DA+0 | 01.09.24 | 06.09.24 | Sunny Const | Complete | 37.504
126 | 3 | 71/5 | DA+0 | 28.08.24 | 06.09.24 | Chinta Devi | Complete | 37.504
127 | 4 | 72/5 | DA+0 | 01.09.24 | 11.09.24 | Sunny Const | Complete | 37.504
128 | 5 | 47/1 | DA+0 | 09.09.24 | 12.09.24 | Sobha devi | Complete | 37.504
129 | 6 | 72/6 | DA+0 | 11.09.24 | 15.09.24 | Sunny Const | Complete | 37.504
130 | 7 | 72/0 | DB1+0 | 06.09.24 | 16.09.24 | Chinta Devi | Complete | 57.597
131 | 8 | 50/2 | DA+0 | 12.09.24 | 16.09.24 | Sobha devi | Complete | 37.504
132 | 9 | 50/1 | DA+0 | 16.09.24 | 20.09.24 | Sobha devi | Complete | 37.504
133 | 10 | 71/4 | DA+0 | 16.09.24 | 22.09.24 | Chinta Devi | Complete | 37.504
134 | 11 | 72/7 | DB1+9 | 15.09.24 | 25.09.24 | Sunny Const | Complete | 70.701
135 | 12 | 43/6 | DA+6 | 09.09.24 | 26.09.24 | Jirwa Devi | Complete | 45.413
136 | 13 | 50/0 | DC+3 | 20.09.24 | 26.09.24 | Sobha devi | Complete | 69.229
137 | 14 | 71/2 | DA+0 | 22.09.24 | 26.09.24 | Chinta Devi | Complete | 37.504
138 | 15 | 72/2 | DA+0 | 25.09.24 | 29.09.24 | Sunny Const | Complete | 37.504
139 | 16 | 15/3 | DA+3 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | Complete | 38.847
140 | 17 | 16/2 | DA+3 | 2024-08-30 | 2024-09-06 | Deglal Mahto | Complete | 38.847
141 | 18 | 14/4 | DA+0 | 2024-08-28 | 2024-09-08 | Jailal Ageria | Complete | 37.504
142 | 19 | 10/3 | DA+3 | 2024-09-07 | 2024-09-11 | Jagdish Mahto | Complete | 38.847
143 | 20 | 16/3 | DA+0 | 2024-09-07 | 2024-09-12 | Deglal Mahto | Complete | 37.504
144 | 21 | 10/4 | #REF! | 2024-09-12 | 2024-09-16 | Jagdish Mahto | Complete | 38.847
145 | 22 | 16/4 | #REF! | 2024-09-12 | 2024-09-16 | Deglal Mahto | Complete | 38.847
146 | 23 | 10/19 | #REF! | 2024-09-06 | 2024-09-19 | Bina Devi | Complete | 47.184
147 | 24 | 10/5 | #REF! | 2024-09-16 | 2024-09-20 | Jagdish Mahto | Complete | 38.847
148 | 25 | 14/5 | #REF! | 2024-09-10 | 2024-09-20 | Jailal Ageria | Complete | 37.504
149 | 26 | 15/2 | #REF! | 2024-09-19 | 2024-09-21 | Nirmal Mahto | Complete | 47.184
150 | 27 | 10/6 | #REF! | 2024-09-21 | 2024-09-25 | Jagdish Mahto | Complete | 38.847
151 | 28 | 10/14 | #REF! | 2024-09-10 | 2024-09-26 | Khublal Mahto | Complete | 38.847
152 | 29 | 15/4 | #REF! | 2024-09-22 | 2024-09-27 | Nirmal Mahto | Complete | 38.847
| Oct'24 | [7 empty] | 1211.987
153 | 1 | 71/1 | DA+0 | 26.09.24 | 01.10.24 | Chinta Devi | Complete | 37.504
154 | 2 | 72/1 | DA+0 | 29.09.24 | 03.10.24 | Sunny Const | Complete | 37.504
155 | 3 | 68/1 | DA+3 | 2.10.24 | 05.10.24 | Chinta Devi | Complete | 38.847
156 | 4 | 43/3 | DA+3 | 27.09.24 | 08.10.24 | Jirwa Devi | Complete | 38.847
157 | 5 | 68/2 | DA+3 | 05.10.24 | 10.10.24 | Chinta Devi | Complete | 38.847
158 | 6 | 66/2 | DA+0 | 30.09.24 | 10.10.24 | Sanjeev Kumar | Complete | 37.504
159 | 7 | 73/0 | DD45+9 | 03.10.24 | 17.10.24 | Sunny Const | Complete | 105.068
160 | 8 | 67/1 | DB1+9 | 10.10.24 | 19.10.24 | Chinta devi | Complete | 70.701
161 | 9 | 43/2 | DA+9 | 08.10.24 | 22.10.24 | Jirwa Devi | Complete | 47.184
162 | 10 | 71/3 | DA+0 | 18.10.24 | 23.10.24 | Sunny Const | Complete | 37.504 |  | 202
163 | 11 | 69/6 | DA+0 | 23.10.24 | 27.10.24 | Sunny Const | Complete | 37.504 |  | 9090
164 | 12 | 68/3 | DA+0 | 24.10.24 | 28.10.24 | Chinta devi | Complete | 37.504
165 | 13 | 40/11 | DA+9 | 23.10.24 | 30.10.24 | Ganesh Kr. Sinha | Complete | 47.184
166 | 14 | 69/7 | DA+0 | 27.10.24 | 31.10.24 | Sunny Const | Complete | 37.504
167 | 15 | 16/5 | #REF! | 2024-09-28 | 2024-10-03 | Deglal Mahto | Complete | 38.847
168 | 16 | 10/21 | #REF! | 2024-09-26 | 2024-10-04 | Yogendra Mahto | Complete | 37.504
169 | 17 | 10/7 | #REF! | 2024-09-30 | 2024-10-04 | Jagdish Mahto | Complete | 45.413
170 | 18 | 11/5 | #REF! | 2024-09-20 | 2024-10-06 | Bina Devi | Complete | 38.847
171 | 19 | 32/4 | DA+0 | 2024-08-30 | 2024-10-09 | Parsuram Sai | Complete | 37.504
172 | 20 | 10/9 | #REF! | 2024-10-08 | 2024-10-11 | Jagdish Mahto | Complete | 38.847
173 | 21 | 19/14 | #REF! | 2024-09-19 | 2024-10-11 | Yogendra Mahto | Complete | 47.184
174 | 22 | 11/7 | #REF! | 2024-10-08 | 2024-10-15 | Rafikul Islam | Complete | 38.847
175 | 23 | 15/0 | #REF! | 2024-10-05 | 2024-10-16 | Jailal Ageria | Complete | 66.381
176 | 24 | 11/8 | #REF! | 2024-10-08 | 2024-10-17 | Rafikul Islam | Complete | 37.504
177 | 25 | 17/0 | #REF! | 2024-10-09 | 2024-10-18 | Deglal Mahto | Complete | 66.381
178 | 26 | 10/18 | #REF! | 2024-10-11 | 2024-10-19 | Bina Devi | Complete | 37.504
179 | 27 | 32/0 | #REF! | 2024-10-13 | 2024-10-28 | Yogendra Mahto | Complete | 67.873
180 | 28 | 11/9 | #REF! | 2024-10-13 | 2024-10-28 | Rafikul Islam | Complete | 38.847
| Nov'24 | [7 empty] | 1286.689
181 | 1 | 68/5 | DA+3 | 28.09.24 | 01.11.24 | Chinta devi | Complete | 38.847
182 | 2 | 68/6 | DA+3 | 01.11.24 | 05.11.24 | Chinta devi | Complete | 38.847
183 | 3 | 69/5 | DA+0 | 01.11.24 | 05.11.24 | Sunny Const | Complete | 37.504
184 | 4 | 68/4 | DA+3 | 05.11.24 | 09.11.24 | Chinta devi | Complete | 38.847
185 | 5 | 69/4 | DA+0 | 05.11.24 | 09.11.24 | Sunny Const | Complete | 37.504
186 | 6 | 40/10 | DB1+6 | 30.10.24 | 11.11.24 | Ganesh Kr. Sinha | Complete | 67.873
187 | 7 | 69/3 | DA+0 | 09.11.24 | 13.11.24 | Sunny Const | Complete | 37.504
188 | 8 | 66/4 | DA+3 | 29.10.24 | 14.11.24 | Sanjeev Kumar | Complete | 38.847
189 | 9 | 69/2 | DA+0 | 13.11.24 | 17.11.24 | Sunny Const | Complete | 37.504 |  | 840
190 | 10 | 69/1 | DA+0 | 18.11.24 | 22.11.24 | Sunny Const | Complete | 37.504 |  | 840
191 | 11 | 68/0 | DD45+0 | 22.11.24 | 29.11.24 | Chinta devi | Complete | 86.129 |  | 840
192 | 12 | 69/0 | DB1+0 | 23.11.24 | 30.11.24 | Sunny Const | Complete | 57.597 |  | 840
193 | 13 | 10/8 | #REF! | 2024-10-24 | 2024-11-01 | Jagdish Mahto | Complete | 37.504
194 | 14 | 15/1 | #REF! | 2024-10-27 | 2024-11-02 | Nirmal Mahto | Complete | 45.413
195 | 15 | 15/9 | #REF! | 2024-10-31 | 2024-11-03 | Deglal Mahto | Complete | 47.184
196 | 16 | 14/2 | #REF! | 2024-10-27 | 2024-11-04 | Jailal Ageria | Complete | 38.847
197 | 17 | 32/3 | #REF! | 2024-11-02 | 2024-11-07 | Yogendra Mahto | Complete | 38.847
198 | 18 | 15/6 | #REF! | 2024-11-04 | 2024-11-09 | Deglal Mahto | Complete | 37.504
199 | 19 | 11/6 | #REF! | 2024-10-20 | 2024-11-10 | Rafikul Islam | Complete | 38.847
200 | 20 | 10/12 | #REF! | 2024-11-06 | 2024-11-10 | Jagdish Mahto | Complete | 60.096
201 | 21 | 32/1 | #REF! | 2024-10-12 | 2024-11-12 | Parsuram Sai | Complete | 47.184
202 | 22 | 11/14 | #REF! | 2024-11-11 | 2024-11-17 | Deglal Mahto | Complete | 37.504
203 | 23 | 10/10 | #REF! | 2024-11-11 | 2024-11-17 | Jagdish Mahto | Complete | 38.847
204 | 24 | 16/0 | #REF! | 2024-11-10 | 2024-11-21 | Bina Devi | Complete | 57.597
205 | 25 | 10/13 | #REF! | 2024-11-18 | 2024-11-21 | Jagdish Mahto | Complete | 38.847
206 | 26 | 11/15 | #REF! | 2024-11-18 | 2024-11-23 | Deglal Mahto | Complete | 37.504
207 | 27 | 13/1 | #REF! | 2024-11-19 | 2024-11-25 | Jailal Ageria | Complete | 38.847
208 | 28 | 19/7 | #REF! | 2024-11-17 | 2024-11-28 | Nirmal Mahto | Complete | 47.184
209 | 29 | 10/11 | #REF! | 2024-11-22 | 2024-11-29 | Jagdish Mahto | Complete | 37.504
| Dec'24 | [7 empty] | 1279.767 | 700
210 | 1 | 69/9 | DA+0 | 01.12.24 | 06.12.24 | Sunny Const | Complete | 37.504 |  | 840
211 | 2 | 67/0 | DD45+0 | 01.12.24 | 08.12.24 | Chinta devi | Complete | 86.129 |  | 4900
212 | 3 | 66/1 | DA+3 | 02.12.24 | 08.12.24 | Sanjeev Kumar | Complete | 38.847
213 | 4 | 38/3 | DA+9 | 10.12.24 | 15.12.24 | Sobha Devi | Complete | 47.184
214 | 5 | 41/12 | DA+3 | 09.12.24 | 17.12.24 | Ganesh Kr. Sinha | Complete | 38.847
215 | 6 | 71/0 | DD+0 | 07.12.24 | 17.12.24 | Sunny Const | Complete | 86.129
216 | 7 | 65/6 | DA+0 | 14.12.24 | 18.12.24 | Chinta devi | Complete | 37.504
217 | 8 | 58/13 | DA+0 | 11.12.24 | 19.12.24 | Sanjeev Kumar | Complete | 37.504
218 | 9 | 38/2 | DA+6 | 15.12.24 | 19.12.24 | Sobha Devi | Complete | 45.413
219 | 10 | 69/8 | DA+0 | 18.12.24 | 22.12.24 | Sunny Const | Complete | 37.504
220 | 11 | 65/7 | DA+0 | 18.12.24 | 22.12.24 | Chinta devi | Complete | 37.504
221 | 12 | 38/1 | DA+3 | 20.12.24 | 24.12.24 | Sobha Devi | Complete | 38.847
222 | 13 | 37/3 | DA+0 | 25.12.24 | 28.12.24 | Sobha Devi | Complete | 37.504
223 | 14 | 41/2 | DA+0 | 21.12.24 | 28.12.24 | Jirwa Devi | Complete | 37.504
224 | 15 | 70/0 | DD60+0 | 22.12.24 | 31.12.24 | Sunny Const | Complete | 86.129
225 | 16 | 42/0 | DC2+9 | 19.12.24 | 31.12.24 | Ganesh Kr. Sinha | Complete | 81.945
226 | 17 | 66/0 | DD45+0 | 22.12.24 | 31.12.24 | Chinta devi | Complete | 86.129
227 | 18 | 31/0 | #REF! | 2024-11-28 | 2024-12-20 | Yogendra Mahto | Complete | 89.909
228 | 19 | 11/12 | #REF! | 2024-12-07 | 2024-12-22 | Bina Devi | Complete | 37.504
229 | 20 | 13/0 | #REF! | 2024-12-07 | 2024-12-24 | Jailal Ageria | Complete | 86.129
230 | 21 | 10/20 | #REF! | 2024-12-11 | 2024-12-24 | Jagdish Mahto | Complete | 67.873
231 | 22 | 11/11 | #REF! | 2024-12-17 | 2024-12-24 | Deglal Mahto | Complete | 37.504
232 | 23 | 11/13 | #REF! | 2024-12-22 | 2024-12-30 | Bina Devi | Complete | 37.504
| Jan'25 | [7 empty] | 1254.55
233 | 1 | 37/4 | DA+6 | 29.12.24 | 03.01.25 | Sobha Devi | Complete | 45.413
234 | 2 | 41/3 | DA+0 | 29.12.24 | 07.01.25 | Jirwa Devi | Complete | 37.504
235 | 3 | 59/4 | DA+0 | 06.01.25 | 10.01.25 | Sanjeev Kumar | Complete | 37.504
236 | 4 | 37/2 | DB1+6 | 04.01.25 | 10.01.25 | Sobha Devi | Complete | 67.873
237 | 5 | 37/5 | DA+3 | 10.01.25 | 16.01.25 | Sobha Devi | Complete | 38.847
238 | 6 | 41/1 | DA+3 | 10.01.25 | 17.01.25 | Jirwa Devi | Complete | 38.847 | 8
239 | 7 | 37/6 | DA+6 | 16.01.25 | 20.01.25 | Sobha Devi | Complete | 45.413
240 | 8 | 37/7 | DA+3 | 20.01.25 | 24.01.25 | Sobha Devi | Complete | 38.847
241 | 9 | 39/1 | DA+6 | 19.01.25 | 28.01.25 | Om Construction | Complete | 45.413
242 | 10 | 37/8 | DA+0 | 25.01.25 | 28.01.25 | Sobha Devi | Complete | 37.504
243 | 11 | 41/0 | DB1+0 | 18.01.25 | 29.01.25 | Jirwa Devi | Complete | 57.597
244 | 12 | 40/2 | DB1+9 | 10.01.25 | 30.01.25 | Sunny Const | Complete | 70.701
245 | 13 | 8/6 | #N/A | 2024-12-25 | 2025-01-06 | Jagdish Mahto | Complete | 38.847
| Feb'25 | [7 empty] | 600.31
246 | 1 | 38/0 | DC1+0 | 29.01.25 | 04.02.25 | Sobha Devi | Complete | 66.381
247 | 2 | 40/12 | DA+0 | 29.01.25 | 08.02.25 | Jirwa Devi | Complete | 37.504
248 | 3 | 43/0 | DB1+9 | 31.01.25 | 18.02.25 | Ganesh Kr. Sinha | Complete | 70.701
249 | 4 | 60/0 | DC2+3 | 07.02.25 | 19.02.25 | Sanjeev kumar | Complete | 69.229
250 | 5 | 40/6 | DA+3 | 15.02.25 | 20.02.25 | Sunny Const | Complete | 38.847
251 | 6 | 49/0 | DC1+3 | 09.02.25 | 23.02.25 | Jirwa Devi | Complete | 69.229
252 | 7 | 40/7 | DA+3 | 21.02.25 | 26.02.25 | Sunny Const | Complete | 38.847
253 | 8 | 44/0 | DB1+0 | 19.02.25 | 28.02.25 | Ganesh Kr. Sinha | Complete | 57.597 |  | Incentive to be paid by SPTL
254 | 9 | 39/0 | DC2+3 | 21.02.25 | 28.02.25 | Sobha Devi | Complete | 69.229 |  | Incentive to be paid by SPTL
| Mar'25 | [7 empty] | 517.564
255 | 1 | 61/0 | DB1+6 | 20.02.25 | 03.03.25 | Sanjeev kumar | Complete | 67.873
256 | 2 | 40/0 | DC2+0 | 27.02.25 | 06.03.25 | Sunny Const | Complete | 66.381
257 | 3 | 38/9 | DB1+6 | 01.03.25 | 07.03.25 | Sobha Devi | Complete | 67.873
258 | 4 | 38/8 | DA+0 | 08.03.25 | 11.03.25 | Sobha Devi | Complete | 37.504
259 | 5 | 40/1 | DA+0 | 08.03.25 | 12.03.25 | Sunny Const | Complete | 37.504
260 | 6 | 38/7 | DA+0 | 13.03.25 | 17.03.25 | Sobha Devi | Complete | 37.504
261 | 7 | 40/4 | DA+9 | 13.03.25 | 20.03.25 | Sunny Const | Complete | 47.184
262 | 8 | 38/6 | DA+0 | 18.03.25 | 21.03.25 | Sobha Devi | Complete | 37.504
263 | 9 | 38/5 | DA+0 | 22.03.25 | 25.03.25 | Sobha Devi | Complete | 37.504 | 436.831
264 | 10 | 40/5 | DB1+9 | 21.03.25 | 28.03.25 | Sunny Const | Complete | 70.701
265 | 11 | 38/4 | DA+0 | 26.03.25 | 29.03.25 | Sobha Devi | Complete | 37.504
266 | 12 | 1A/1 | #REF! | 2025-03-01 | 2025-03-09 | Bina Devi | Complete | 37.504
267 | 13 | 1A/2 | #REF! | 2025-03-10 | 2025-03-27 | Bina Devi | Complete | 45.413
| April'25 | [7 empty] | 627.953
268 | 1 | 35/9 | DA+3 | 06.04.25 | 10.04.25 | Sobha Devi | Complete | 38.847
269 | 2 | 35/8 | DA+0 | 11.04.25 | 14.04.25 | Sobha Devi | Complete | 37.504
270 | 3 | 63/5 | DA+3 | 10.04.25 | 15.04.25 | Chinta Devi | Complete | 38.847
271 | 4 | 63/6 | DA+3 | 15.04.25 | 20.04.25 | Chinta Devi | Complete | 38.847
272 | 5 | 35/7 | DA+3 | 15.04.25 | 20.04.25 | Sobha Devi | Complete | 38.847
273 | 6 | 63/1 | DA+6 | 15.04.25 | 21.04.25 | Sunny Const | Complete | 45.413
274 | 7 | 63/2 | DA+0 | 21.04.25 | 25.04.25 | Sunny Const | Complete | 37.504
275 | 8 | 63/4 | DA+0 | 21.04.25 | 26.04.25 | Chinta Devi | Complete | 37.504
276 | 9 | 35/6 | DA+9 | 21.04.25 | 26.04.25 | Sobha Devi | Complete | 47.184
277 | 10 | 63/3 | DA+3 | 26.04.25 | 30.04.25 | Sunny Const | Complete | 38.847
278 | 11 | 35/5 | DA+0 | 26.04.25 | 30.04.25 | Sobha Devi | Complete | 37.504 |  |  |  | 59
| May'25 | [7 empty] | 436.848
279 | 1 | 44/5 | DA+6 | 30.04.25 | 06.05.25 | Satyam (Manish) | Complete | 45.413 | Ganesh
280 | 2 | 39/3 | DA+3 | 30.04.25 | 06.05.25 | Satyam (Nitish) | Complete | 38.847 | Rajiv
281 | 3 | 62/0 | DC+0 | 30.04.25 | 09.05.25 | Sunny Const | Complete | 66.381 | Manoj | With crane
282 | 4 | 39/2 | DA+0 | 07.05.25 | 11.05.25 | Satyam (Nitish) | Complete | 37.504 | Rajiv/nirala
283 | 5 | 34/4 | DA+6 | 29.04.25 | 13.05.25 | Ganesh Kr. Sinha | Complete | 45.413 | Dinesh |  | 26
284 | 6 | 33/5 | DA+0 | 28.04.25 | 15.05.25 | Annaya Traders | Complete | 37.504 | KP Pal |  | 26
285 | 7 | 39/4 | DA+0 | 12.05.25 | 17.05.25 | Satyam (Nitish) | Complete | 37.504 | Rajiv/nirala |  | 38
286 | 8 | 63/0 | DD45+0 | 12.05.25 | 19.05.25 | Sunny Const | Complete | 86.129 | Manoj | With crane | 36
287 | 9 | 45/0 | DD60+25 | 07.05.25 | 23.05.25 | Satyam (Manish) | Complete | 143.601 | Ganesh | With crane- only 1st Section | 26 |  |  | Bisun
288 | 10 | 64/9 | DA+0 | 12.05.25 | 23.05.25 | Satyam (Trivedi) | Complete | 37.504 | Paplesh |  | 38
289 | 11 | 37/1 | DB1+9 | 17.05.25 | 24.05.25 | Satyam (Nitish) | Complete | 70.701 | Umesh Kumar |  | 35 |  |  | Umesh
290 | 12 | 35/0 | DB2+0 | 13.05.25 | 25.05.25 | Satyam (Mondal) | Complete | 57.597 | Dinesh |  | 27
291 | 13 | 64/6 | DA+3 | 15.05.25 | 27.05.25 | Satyam (Vijay ) | Complete | 38.847 | Manoj Kumar |  | 25
292 | 14 | 64/8 | DA+0 | 24.05.25 | 31.05.25 | Satyam (Trivedi) | Complete | 37.504 | Paplesh |  | 33
June'25
293 | 1 | 46/1 | DA+6 | 24.05.25 | 03.06.25 | Satyam (Manish) | Complete | 45.413 | Bisun |  | 22
294 | 2 | 24/6 | DA+0 | 30.05.25 | 04.06.25 | Pankaj | Complete | 37.504 | rameshwar |  | 25
295 | 3 | 1A/4 | DA+3 | 04.05.25 | 05.06.25 | Bhairo Mahto (Departmental) | Complete | 38.847 | Dhal chand | With crane
296 | 4 | 34/6 | DA+6 | 27.05.25 | 06.06.25 | Satyam (Mondal) | Complete | 45.413 | Dinesh |  | 30
297 | 5 | 64/0 | DB2+0 | 28.05.25 | 06.06.25 | Jwala singh -1 | Complete | 57.597 | Vikash |  | 27
298 | 6 | 64/5 | DA+3 | 29.05.25 | 08.06.25 | Satyam (Vijay ) | Complete | 38.847 | Manikant |  | 24
299 | 7 | 66/3 | DA+3 | 19.01.25 | 09.06.25 | Satyam (Trivedi) | Complete | 38.847 | Mahamaya |  | 33 |  |  |  | ROW cleared on 31.05.25
300 | 8 | 40/8 | DA+0 | 08.06.25 | 13.06.25 | Satyam (Manish) | Complete | 37.504 | Bisun |  | 22
301 | 9 | 36/0 | DD60+25 | 26.05.25 | 15.06.25 | Satyam (Nitish) | Complete | 143.601 | Umesh Kumar | With crane | 36
302 | 10 | 35/1 | DA+0 | 08.06.25 | 15.06.25 | Satyam (Mondal) | Complete | 37.504 | Kamla Prasad |  | 30
303 | 11 | 64/1 | DA+6 | 07.06.25 | 15.06.25 | Jwala Singh -1 | Complete | 45.413 | Vikash |  | 22 | a
304 | 12 | 64/3 | DA+0 | 30.05.25 | 15.06.25 | Satyam (Santosh) | Complete | 37.504 | Pradeep |  | 21
305 | 13 | 1A/3 | DA+0 | 16.05.25 | 15.06.25 | Bhairo Mahto (Departmental) | Complete | 37.504 | Dhal chand | With Crane
306 | 14 | 40/9 | DA+0 | 16.06.25 | 18.06.25 | Satyam (Manish) | Complete | 37.504 | Nirala |  | 22
307 | 15 | 39/5 | DA+3 | 09.06.25 | 18.06.25 | Jwala Singh-2 | Complete | 38.847 | Sakib |  | 21
308 | 16 | 65/0 | DB+3 | 10.06.25 | 19.6.25 | Satyam (Trivedi) | Complete | 60.096 | Manoj |  | 28
309 | 17 | 1A/6 | DA+0 | 30.05.25 | 19.6.25 | Kewat (Departmental) | Complete | 37.504 | Dashrath Mahto | With crane | 32
310 | 18 | 64/7 | DA+3 | 10.06.25 | 22.06.25 | Satyam (Vijay ) | Complete | 38.847 | Paplesh |  | 24 |  | 70/2
311 | 19 | 35/2 | DA+0 | 16.06.25 | 23.06.25 | Satyam (Mondal) | Complete | 37.504 | Kamla Prasad |  | 35 |  |  |  | 560
312 | 20 | 1A/5 | DA+6 | 20.05.25 | 27.06.25 | Bhairo Mahto (Departmental) | Complete | 45.413 | Dhal chand | With Crane | 33 |  |  |  | 16818
313 | 21 | 24/5 | DA+3 | 18.06.25 | 27.06.25 | Poonam | Complete | 38.847 | rameshwar |  | 18
314 | 22 | 8/9 | DA+3 | 24.06.25 | 27.06.25 | Jwala singh -3 | Complete | 38.847 | Umesh |  | 27 |  |  | PKG-F - 8/9
315 | 23 | 65/2 | DA+0 | 23.06.25 | 28.06.25 | Satyam (Trivedi) | Complete | 37.504 | Manoj |  | 38
316 | 24 | 64/2 | DA+0 | 23.06.25 | 28.06.25 | Jwala Singh -1 | Complete | 37.504 | Vikash |  | 25 |  |  | Pkg-f 69/1
317 | 25 | 39/6 | DA+0 | 22.06.25 | 28.06.25 | Jwala Singh-2 | Complete | 37.504 | Sakib |  | 26
318 | 26 | 46/0 | DD60+25 | 18.06.25 | 30.06.25 | Satyam (Manish) | Complete | 143.601 | Ganesh |  | 36
319 | 27 | 37/0 | DD60+25 | 17.06.25 | 30.06.25 | Satyam (Nitish) | Complete | 143.601 | Dineshwar |  | 40
320 | 28 | 35/3 | DA+0 | 25.06.25 | 30.06.25 | Satyam (Mondal) | Complete | 37.504 | Sakib |  | 35
321 | 29 | 40/3 | DA+3 | 10.06.25 | 30.06.25 | Permanand | Complete | 38.847 | Bisun |  | 19
322 | 30 | 25/11 | DA+6 | 27.06.25 | 30.06.25 | Pusplata-1 | Complete | 45.413 | Umesh Kumar |  | 31
323 | 31 | 25/5 | DA+3 | 26.06.25 | 30.06.25 | Pusplata-4 | Complete | 38.847 |  |  | 31
July'25
324 | 1 | 24/4 | DA+0 | 29.06.25 | 02.07.25 | Poonam | Complete | 37.504 | rameshwar |  | 22
325 | 2 | 39/7 | DA+0 | 30.06.25 | 03.07.25 | Jwala Singh-2 | Complete | 37.504 | Vikash |  | 26 |  | Team shift to PKG-F 52/4
326 | 3 | 2/9 | DA+0 | 26.06.25 | 03.07.325 | Arawali Infra.-1 | Complete | 37.504 | Soib Rai |  | 24
327 | 4 | 15/7 | DA+6 | 23.06.25 | 04.07.25 | Priyanka Devi -Sudheer | Complete | 45.413 | Ullas |  | 19
328 | 5 | 21/2 | DA+3 | 27.06.25 | 04.07.25 | Pusplata-5 | Complete | 38.847 |  |  | 30
329 | 6 | 65/1 | DA+3 | 30.06.25 | 05.07.25 | Satyam (Trivedi) | Complete | 38.847 | Manoj |  | 38
330 | 7 | 23/6 | DA+6 | 27.06.25 | 05.07.25 | Pusplata-2 | Complete | 45.413 |  |  | 38
331 | 8 | 24/2 | DA+0 | 28.06.25 | 05.07.25 | Pusplata-3 | Complete | 37.504 |  |  | 39
332 | 9 | 35/4 | DA+3 | 01.07.25 | 06.07.25 | Satyam (Mondal) | Complete | 38.847 | Sakib |  | 35
333 | 10 | 12/0 | DD60+0 | 24.06.25 | 06.07.25 | Arawali Infra.-2 | Complete | 86.129 | Ganga Dhar Sahu |  | 35 |  |  | 10400
334 | 11 | 25/6 | DA+3 | 02.07.25 | 06.07.25 | Pusplata-4 | Complete | 38.847 | Umesh Kumar |  | 30
335 | 12 | 8/10 | DA+3 | 02.07.25 | 06.07.25 | Jwala singh -3 | Complete | 38.847 |  |  | 34
336 | 13 | 1A/7 | DA+3 | 09.06.25 | 07.07.25 | Anil Kumar (Departmental) Kewat | Complete | 38.847 |  | With Crane
337 | 14 | 24/3 | DA+0 | 04.07.25 | 07.07.25 | Poonam | Complete | 37.504 | rameshwar |  | 22
338 | 15 | 64/4 | DA+3 | 21.06.25 | 08.07.25 | Satyam (Manish-2/Santosh) | Complete | 38.847 | Pradeep |  | 17
339 | 16 | 33/6 | DA+6 | 04.07.25 | 08.07.25 | Satyam (Nitish) | Complete | 45.413 | Dineshwar |  | 40
340 | 17 | 22/6 | DA+6 | 28.06.25 | 08.07.25 | Pusplata-6 | Complete | 45.413 |  |  | 36
341 | 18 | 29/2 | DA+9 | 30.06.25 | 08.07.25 | Gourishankar | Complete | 47.184 |  |  | 22
342 | 19 | 34/2 | DA+9 | 23.06.25 | 09.07.25 | Vinay Const. | Complete | 47.184 | Umesh Kumar |  | 30
343 | 20 | 33/0 | DB2+3 | 04.07.25 | 09.07.25 | Satyam (Manish) | Complete | 60.096 | Ganesh |  | 36
344 | 21 | 25/10 | DA+0 | 04.07.25 | 09.07.25 | Pusplata-1 | Complete | 37.504 |  |  | 30
345 | 22 | 2/8 | DA+0 | 05.07.25 | 10.07.25 | Arawali Infra.-1 | Complete | 37.504 | Soib Rai |  | 24
346 | 23 | 21/3 | DA+0 | 05.07.25 | 11.07.25 | Pusplata-5 | Complete | 37.504 |  |  | 32
347 | 24 | 21/6 | DA+0 | 08.07.25 | 11.07.25 | Poonam | Complete | 37.504 | rameshwar |  | 37
348 | 25 | 15/5 | DA+3 | 05.07.25 | 11.07.25 | Priyanka Devi -Sudheer | Complete | 38.847 | Dev Narayan Mahto |  | 29
349 | 26 | 28/9 | DA+0 | 04.07.25 | 12.07.25 | Rahul Kumar | Complete | 37.504 |  |  | 25
350 | 27 | 25/7 | DA+9 | 07.07.25 | 12.07.25 | Pusplata-4 | Complete | 47.184 | Drug Singh |  | 40
351 | 28 | 33/3 | DA+0 | 10.07.25 | 13.07.25 | Satyam (Manish) | Complete | 37.504 | Ganesh |  | 28
352 | 29 | 30/2 | DA+0 | 09.07.25 | 13.07.25 | Satyam (Trivedi) | Complete | 37.504 | Manoj |  | 32
353 | 30 | 23/7 | DA+9 | 06.07.25 | 13.07.25 | Pusplata-2 | Complete | 47.184
354 | 31 | 22/3 | DA+3 | 03.07.25 | 13.07.25 | Pusplata -7 | Complete | 38.847 | Dhannanjay/Ravi |  | 36
355 | 32 | 28/0 | DB1+0 | 06.07.25 | 13.07.25 | Jwala Singh-2 | Complete | 57.597 | Kartik |  | 26
356 | 33 | 33/7 | DA+9 | 09.07.25 | 14.07.25 | Satyam (Nitish) | Complete | 47.184 | Dinesh |  | 30
357 | 34 | 1A/0 | DD60+0 | 18.06.25 | 14.07.25 | Anil Kumar/ Ramayan (Departmental) | Complete | 86.129 | Dashrath Mahto | With crane | 32 |  |  |  | 3493
358 | 35 | 25/9 | DA+6 | 10.07.25 | 15.07.25 | Pusplata-1 | Complete | 45.413 | Umesh |  | 37
359 | 36 | 8/11 | DA+3 | 11.07.25 | 15.07.25 | Jwala singh -3 | Complete | 38.847 | Umesh Kumar |  | 27
360 | 37 | 21/7 | DB1+0 | 12.07.25 | 16.07.25 | Poonam | Complete | 57.597 | rameshwar |  | 37
361 | 38 | 14/1 | DA+3 | 08.07.25 | 16.07.25 | Arawali Infra.-2 | Complete | 38.847 | Ram Kishore |  | 25
362 | 39 | 29/3 | DA+6 | 10.07.25 | 17.07.25 | Gourishankar | Complete | 45.413 | Pramod Sahu |  | 23
363 | 40 | 22/7 | DA+6 | 09.7.25 | 17.07.25 | Pusplata-6 | Complete | 45.413 |  |  | 36
364 | 41 | 33/4 | DA+0 | 15.07.25 | 18.07.25 | Satyam (Manish) | Complete | 37.504 | Ganesh |  | 28 |  | PKG-F 44/3- Body Done
365 | 42 | 25/1 | DA+3 | 13.07.25 | 18.07.25 | Pusplata-4 | Complete | 38.847 | Durg Singh |  | 40
366 | 43 | 28/1 | DA+6 | 14.07.25 | 19.07.25 | Jwala Singh-2 | Complete | 45.413 | Kartik |  | 26
367 | 44 | 15/8 | DA+0 | 13.07.25 | 19.07.25 | Priyanka Devi -Sudheer | Complete | 37.504 | Dev Narayan Mahto |  | 31
368 | 45 | 34/1 | DA+3 | 11.07.25 | 20.07.25 | Vinay Const. | Complete | 38.847 | Umesh Kumar |  | 30
369 | 46 | 21/4 | DA+9 | 12.07.25 | 20.07.25 | Pusplata-5 | Complete | 47.184 | Sudheer Pal |  | 32
370 | 47 | 23/8 | DA+9 | 14.07.25 | 21.07.25 | Pusplata-2 | Complete | 47.184 |  |  | 38
371 | 48 | 21/8 | DA+0 | 17.07.25 | 21.07.25 | Poonam | Complete | 37.504 | rameshwar |  | 50 |  | Team Shift to PKG-F 26/2
372 | 49 | 30/1 | DA+3 | 14.07.25 | 22.07.25 | Satyam (Trivedi/Nitish) | Complete | 38.847 | Pradeep |  | 32
373 | 50 | 29/1 | DA+6 | 13.07.25 | 22.07.25 | Rahul Kumar | Complete | 45.413 | Mahesh Dhaka |  | 25
374 | 51 | 25/3 | DA+0 | 19.07.25 | 22.07.25 | Pusplata-4 | Complete | 37.504 | Durg Singh |  | 40
375 | 52 | 22/4 | DA+3 | 14.07.25 | 22.07.25 | Pusplata-7 | Complete | 38.847 |  |  | 36
376 | 53 | 33/8 | DA+3 | 10.07.25 | 23.07.25 | Vinay Const. -2 | Complete | 38.847 | Bisun |  | 26 |  | 47/7 F
377 | 54 | 34/0 | DB1+6 | 15.07.25 | 23.07.25 | Satyam (Nitish) | Complete | 67.873 | Dinesh |  | 35 |  | 44/4 F
378 | 55 | 24/0 | DB2+0 | 17.07.25 | 23.07.25 | Pusplata-3 | Complete | 57.597
379 | 56 | 26/0 | DB2+0 | 16.07.25 | 23.07.25 | Pusplata -1 | Complete | 57.597 |  |  | 37
380 | 57 | 29/4 | DA+3 | 18.07.25 | 24.07.25 | Gourishankar | Complete | 38.847 | Pramod Sahu |  | 23
381 | 58 | 14/0 | DC2+0 | 18.07.25 | 24.07.25 | Arawali Infra.-2 | Complete | 66.381 | Ram Kishore |  | 25 |  |  | PKG=-F-12/0
382 | 59 | 11/4 | DA+6 | 29.06.25 | 24.07.25 | Anjani Enterprises | Complete | 45.413 | Mukesh |  | 21 | ROW
383 | 60 | 27/5 | DA+0 | 19.07.25 | 24.07.25 | Satyam (Vijay) | Complete | 37.504 |  |  | 35
384 | 61 | 34/5 | DCT | 10.07.25 | 26.07.25 | Satyam (Mondal) | Complete | 94.2225 | Sakib |  | 35 |  |  | PKG-F 44/10
385 | 62 | 23/10 | DA+3 | 22.07.25 | 26.07.25 | Pusplata-2 | Complete | 38.847 | Malik |  | 38
386 | 63 | 23/3 | DA+0 | 24.07.25 | 26.07.25 | Pusplata-4 | Complete | 37.504 | Durg Singh |  | 40
387 | 64 | 22/9 | DA+6 | 18.07.25 | 26.07.25 | Pusplata-6 | Complete | 45.413 | Manoj |  | 36 |  |  | 366
388 | 65 | 26/2 | DA+3 | 12.07.25 | 27.07.25 | Satyam (Santosh) | Complete | 38.847 | Pradeep |  | 25
389 | 66 | 22/5 | DA+3 | 23.07.25 | 27.07.25 | Pusplata-7 | Complete | 38.847 | Rooplal |  | 36
390 | 67 | 21/5 | DA+3 | 22.07.25 | 27.07.25 | Pusplata-5 | Complete | 38.847 | Madan |  | 32
391 | 68 | 18/1 | DA+3 | 22.07.25 | 28.07.25 | Priyanka Devi -Sudheer | Complete | 38.847 | Dev Narayan |  | 25
392 | 69 | 28/8 | DA+3 | 24.07.25 | 29.07.25 | Rahul Kumar | Complete | 38.847 | Mahesh Dhaka |  | 25
393 | 70 | 28/2 | DA+3 | 27.07.25 | 30.07.25 | Pusplata-3 | Complete | 38.847 |  |  | 39
394 | 71 | 27/4 | DA+0 | 25.07.25 | 30.07.25 | Satyam (Vijay) | Complete | 37.504
395 | 72 | 25/8 | DA+9 | 10.07.25 | 30.07.25 | Pusplata-3/Jwala | Complete | 47.184 | Govind |  | 39 |  | PKG-29/1 |  |  |  | Upto 2nd Section done by - pusplata team
396 | 73 | 26/1 | DA+3 | 25.07.25 | 30.07.25 | Pusplata-1 | Complete | 38.847 | Umesh |  | 37
397 | 74 | 17/4 | DA+3 | 24.07.25 | 30.07.25 | Priyanka Devi -Sudheer -2 | Complete | 38.847 | Sahu |  | 30 |  | PKG-F-19/5
398 | 75 | 10/0 | DD60+18 | 16.07.25 | 30.07.25 | Jwala singh -3 | Complete | 129.11 | Umesh Kumar |  | 27
399 | 76 | 34/3 | DA+9 | 24.07.25 | 31.07.25 | Vinay Const. | Complete | 47.184 | Umesh Kumar |  | 30 |  | PKG-F 47/2 |  |  | Body |  | Cage-2
400 | 77 | 29/0 | DB2+0 | 25.07.25 | 31.07.25 | Gourishankar | Complete | 57.597 | Pramod Sahu |  | 23
401 | 78 | 23/11 | DA+6 | 27.07.25 | 31.07.25 | Pusplata-2 | Complete | 45.413 | Malik |  | 38
402 | 79 | 23/1 | DA+0 | 27.07.25 | 31.07.25 | Pusplata-4 | Complete | 37.504 | Durg Singh |  | 40
403 | 80 | 23/4 | DA+3 | 27.07.25 | 31.07.25 | Pusplata-6 | Complete | 38.847 | Manoj |  | 36
404 | 81 | 18/2 | DA+3 | 30.08.25 | 31.07.25 | Priyanka Devi -Sudheer | Complete | 38.847 | Dev Narayan |  | 25
405 | 82 | 1/0 | DE+0 | 25.06.25 | 31.07.25 | Anil Kumar(Departmental)/Ramayan | Complete | 86.129 | Dal chand |  | 35 |  |  |  | 13325
406 | 83 | 2/5 | DA+3 | 11.07.25 | 31.07.25 | Usha Tower | Cross arm | 38.847 | Dashrath Mahto |  | 25 |  | PKG-F 2/5
407 | 84 | 27/3 | DA+0 | 30.07.25 | 31.07.25 | Satyam (Vijay) | Complete | 37.504
408 | 85 | 22/2 | DA+0 | 28.07.25 | 31.07.25 | Poonam | Complete | 37.504
2025-08-25
409 | 1 | 28/3 | DA+0 | 31.07.25 | 04.08.25 | Pusplata-3 | Complete | 37.504 |  |  | 39
410 | 2 | 22/1 | DA+0 | 01.08.25 | 04.08.25 | Poonam | Complete | 37.504
411 | 3 | 8/12 | DA+0 | 31.07.25 | 05.08.25 | Jwala singh -3 | Complete | 37.504 | Sahib Rai |  | 27 |  | PKG-F 8/12
412 | 4 | 25/4 | DA+0 | 01.08.25 | 05.08.25 | Pusplata-4 | Complete | 37.504
413 | 5 | 23/5 | DA+0 | 01.08.25 | 06.08.25 | Pusplata-Deepak | Complete | 37.504
414 | 6 | 33/2 | DA+0 | 04.08.25 | 07.08.25 | Satyam (Manish) | Complete | 37.504
415 | 7 | 23/0 | DB2+0 | 01.08.25 | 08.08.25 | Pusplata-1 | Complete | 57.597 | Umesh |  |  |  | PKG-F 27/4
416 | 8 | 30/0 | DC2+0 | 31.07.25 | 09.08.25 | Rahul Kumar | Complete | 66.381 | Mahesh Dhaka |  | 25 |  | PKG-F 40/3
417 | 9 | 31/1 | DA+9 | 03.08.25 | 09.08.25 | Gourishankar | Complete | 47.184 |  |  |  |  | PKG-F 41/1
418 | 10 | 16/6 | DA+0 | 04.08.25 | 09.08.25 | Priyanka Devi -Sudheer | Complete | 37.504 | Dev Narayan |  | 40
419 | 11 | 23/2 | DA+0 | 04.08.25 | 09.08.25 | Pusplata-6 | Complete | 37.504
420 | 12 | 28/4 | DA+9 | 05.08.25 | 10.08.25 | Pusplata-Santosh | Complete | 47.184 |  |  |  |  | No locs alloted 2/0 reached
421 | 13 | 21/14 | DA+6 | 06.08.25 | 11.08.25 | Pusplata-Ashok | Complete | 45.413 |  |  |  |  | PKG-F 17/4
422 | 14 | 27/2 | DA+0 | 06.08.25 | 11.08.25 | Satyam (Vijay) | Complete | 37.504 |  |  |  |  | 27/1
423 | 15 | 4/0 | DD60+6 | 17.07.25 | 12.08.25 | Bhairo Mahto (Departmental) /Arawali | Complete | 100.96 | Dal chand |  | 40
424 | 16 | 33/1 | DA+0 | 09.08.25 | 12.08.25 | Satyam (Manish) | Complete | 37.504 | Ganesh Ji |  |  |  | PKG-F 44/11
425 | 17 | 26/3 | DA+0 | 29.07,25 | 13.08.25 | Satyam (Santosh) | Complete | 37.504 | Pradeep |  | 25 |  | 26/4
426 | 18 | 17/5 | DA+3 | 05.08.25 | 13.08.25 | Priyanka Devi -2 | Complete | 38.847 |  |  |  |  | 18/8
427 | 19 | 21/12 | DA+9 | 01.08.25 | 14.08.25 | Pusplata -Dharamveer | Complete | 47.184 | Ram Lagan |  | 36 |  |  |  | PKG-F 27/1
428 | 20 | 4/1 | DA+0 | 27.08.25 | 16.08.25 | Bhairo Mahto (Departmental)/Bharo | Complete | 37.504 | Dashrath Mahto |  | 27
429 | 21 | 16/1 | DA+3 | 04.08.25 | 18.08.25 | Arawali Infra.-2 | Complete | 38.847 | Kartik Mahto |  |  |  | no loc
430 | 22 | 24/1 | DA+3 | 16.08.25 | 19.08.25 | Pusplata-Deepak | Complete | 38.847
431 | 23 | 18/8 | DA+3 | 14.08.25 | 19.08.25 | Priyanka Devi -2 | Complete | 38.847 | Gangadhar sahu
432 | 24 | 4/4 | DA+0 | 14.08.25 | 19.08.25 | Pusplata-Ashok | Complete | 37.504 | Rajesh Yadav
433 | 25 | 18/0 | DB2+0 | 11.08.25 | 22.08.25 | Priyanka Devi -Sudheer | Complete | 57.597 | Devnarayan Mahto |  | 26
434 | 26 | 2/7 | DA+6 | 13.08.25 | 22.08.25 | Arawali | Complete | 45.413 | Niteesh Tiwari
435 | 27 | 32/7 | DA+0 | 19.08.25 | 22.08.25 | Satyam(Manish) | Complete | 37.504
436 | 28 | 2/3 | DA+0 | 17.08.25 | 24.08.25 | Sital Singh | Complete | 37.504
437 | 29 | 25/2 | DA+0 | 21.08.25 | 24.08.25 | Pusplata-Deepak | Complete | 37.504 | 30/1 F
438 | 30 | 20/0 | DD45+3 | 10.08.25 | 25.08.25 | Pusplata-Rajaram | Complete | 89.909 | Manoj Rabidas |  | 30
439 | 31 | 21/0 | DD45+3 | 10.08.25 | 25.08.25 | Pusplata-praful | Complete | 89.909
440 | 32 | 18/9 | DA+0 | 21.08.25 | 25.08.25 | Priyanka Devi -2 | Complete | 37.504
441 | 33 | 22/0 | DC2+9 | 14.08.25 | 26.08.25 | Pusplata-ramchander | Complete | 81.494
442 | 34 | 27/1 | DB1+9 | 12.08.25 | 26.08.25 | Satyam (Vijay) | Complete | 70.701 | Vikash |  | 35
443 | 35 | 32/8 | DA+9 | 23.08.25 | 27.08.25 | Satyam(Manish) | Complete | 47.184
444 | 36 | 2/0 | DC1+0 | 14.08.25 | 27.08.25 | Priyanka Devi | Complete | 66.381
445 | 37 | 4/3 | DA+0 | 24.04.25 | 28.08.25 | Pusplata-Ashok | Complete | 37.504
446 | 38 | 8/4 | DA+0 | 21.08.25 | 28.08.25 | Jawala Singh | Complete | 37.504
447 | 39 | 2/6 | DA+6 | 22.08.25 | 29.08.25 | Usha Tower | Complete | 45.413
448 | 40 | 2/4 | DA+3 | 21.08.25 | 30.08.25 | Sital Singh-2 | Complete | 38.847
449 | 41 | 19/0 | DC+0 | 24.08.25 | 30.08.25 | Priyanka Devi -Sudheer | Complete | 66.381
450 | 42 | 23/9 | DA+6 | 25.08.25 | 31.08.25 | Jawala Singh-Suraj | Complete | 45.413 |  |  |  | 28/0
451 | 43 | 26/7 | DA+3 | 27.08.25 | 31.08.25 | Satyam (Vijay) | Complete | 38.847
452 | 44 | 2/1 | DA+0 | 25.08.25 | 31.08.25 | Sital Singh | Complete | 37.504
2025-09-25
453 | 1 | 28/5 | DA+9 | 25.08.25 | 02.09.25 | Rahul Kumar | Complete | 47.184
454 | 2 | 26/6 | DA+0 | 27.08.25 | 03.09.25 | Sanjeev kumar | Complete | 37.504
455 | 3 | 6/2 | DA+3 | 31.08.25 | 05.09.25 | Usha Tower | Complete | 38.847 | Jitendra Section-1 |  | 29 |  |  | 6/2
456 | 4 | 2/2 | DA+0 | 30.08.25 | 08.09.25 | Priyanka Devi | Complete | 37.504 | Jailal Mahto |  | 21 |  |  | 2/2 F
457 | 5 | 28/7 | DA+0 | 05.09.25 | 09.09.25 | Rahul Kumar | Complete | 37.504
458 | 6 | 8/2 | DA+3 | 02.09.25 | 10.09.25 | Bhairo Mahto | Complete | 38.847 | Dashrath Mahto
459 | 7 | 14/3 | DA+0 | 05.09.25 | 10.09.25 | Pusplata-Pankaj | Complete | 37.504 |  | windup
460 | 8 | 8/5 | DA+3 | 06.09.25 | 11.09.25 | Jwala Singh | Complete | 38.847 | [5 empty] | 8/5 F
461 | 9 | 6/0 | DB2+9 | 04.09.25 | 13.09.25 | Pusplata-Ashok | Complete | 70.701 | Rajesh Yadav
462 | 10 | 26/5 | DA+9 | 05.09.25 | 15.09.25 | Sanjeev kumar | Complete | 47.184
463 | 11 | 21/13 | DA+0 | 02.09.25 | 16.09.25 | Pusplata-Deepak | Complete | 37.504 | Durg Singh |  | 38
464 | 12 | 10/17 | DA+3 | 11.09.25 | 20.09.25 | Sital Singh-1 | Complete | 38.847
465 | 13 | 6/1 | DA+0 | 15.09.25 | 23.09.25 | Sital Singh-2 | Complete | 37.504 | [5 empty] | 6/1 F
466 | 14 | 26/4 | DA+9 | 16.09.25 | 27.09.25 | Sanjeev kumar | Complete | 47.184
467 | 15 | 10/16 | DA+3 | 21.09.25 | 29.09.25 | Sital Singh-1 | Complete | 38.847 | Susil |  | 30
2025-10-25
468 | 1 | 10/1 | DA+3 | 23.09.25 | 03.10.25 | Priyanka devi (Subodh) | Complete | 38.847 | Jailal Mahto |  | 24
469 | 2 | 19/2 | DA+3 | 30.09.25 | 04.10.25 | Priyanka devi (Sudheer) | Complete | 38.847
470 | 3 | 28/6 | DA+9 | 29.09.25 | 09.10.25 | Ganesh Sinha | Complete | 47.184 |  |  | 42
471 | 4 | 18/4 | DA+3 | 08.09.25 | 10.10.25 | Priyanka Devi - Santosh | Complete ROW resolve after 26 days letter (ROW since 10.09.25) | 38.847 | [5 empty] | 21/4 F
472 | 5 | 10/15 | DA+3 | 30.09.25 | 11.10.25 | Sital Singh-1 | Complete | 38.847 |  |  | 30
473 | 6 | 8/0 | DB1+0 | 03.10.25 | 13.10.25 | Sital Singh-1 | Complete | 57.597 | Sahib Rai |  | 33
474 | 7 | 27/0 | DC2+9 | 26.09.25 | 15.10.25 | Sanjeev kumar | Complete | 81.495 | Pradep |  | 32 |  |  | 35/0 F
475 | 8 | 17/3 | DA+3 | 06.10.25 | 18.10.25 | Shyam Construction | Complete | 38.847 | Kartik Mahto |  | 27
476 | 9 | 11/3 | DA+9 | 11.10.25 | 18.10.25 | Devi Construction | Complete | 47.184 | Susil Yadav |  | 40 |  |  | 11/4F
477 | 10 | 4/2 | DA+0 | 10.10.25 | 21.10.25 | Priyanka devi (Sudheer) | Complete | 37.504 | Chandra Prakash
478 | 11 | 7/0 | DB1+0 | 14.10.25 | 21.10.25 | Sital Singh-1 | Complete | 57.597
479 | 12 | 18/7 | DA+6 | 09.10.25 | 23.10.25 | Vivek Ganju | Complete | 45.413 | Sahoo Ji
480 | 13 | 9/0 | DD60+18 | 11.08.25 | 25.10.25 | Jwala singh -3/Bhairo Mahto | Complete (ROW) work start with police proctution on date 27.-09.25 | 129.11 | Dashrath Mahto |  | 33
481 | 14 | 8/1 | DA+3 | 30.07.25 | 28.10.25 | Anjani Power/Priyanka devi (Sudheer) | Complete | 38.847 | Chandra Prakash
482 | 15 | 5/0 | DB1+9 | 10.10.25 | 28.10.25 | Kamlesh | Complete | 70.701 | Rahul
483 | 16 | 19/9 | DA+3 | 24.10.25 | 28.10.25 | Sunny Const | Complete | 38.847
484 | 17 | 19/10 | DA+9 | 29.10.25 | 31.10.25 | Sunny Const | Complete | 47.184
2025-11-25
485 | 1 | 18/10 | DA+3 | 27.10.25 | 05.11.25 | Vivek Ganju | Complete | 38.847 | Sahoo Ji
486 | 2 | 25/0 | DC1+0 | 24.10.25 | 05.11.25 | Jirwa Devi | Complete | 66.381 | Dhannanjay
487 | 3 | 19/8 | DB1+6 | 04.11.25 | 10.11.25 | Sunny Const | Complete | 67.873 |  | Next 19/1
488 | 4 | 30/3 | DA+6 | 07.11.25 | 11.11.25 | Sobha Devi | Complete | 45.413
489 | 5 | 8/3 | DA+3 | 31.10.25 | 12.11.25 | Priyanka devi (Sudheer) | Complete | 38.847 |  |  | 28
490 | 6 | 19/3 | DA+6 | 03.11.25 | 16.11.25 | Shri Shyam | Complete | 45.413 |  |  | 25
491 | 7 | 17/2 | DA+3 | 05.11.25 | 16.11.25 | Vivek Ganju | Complete | 38.847 |  |  | 28
492 | 8 | 11/2 | DA+9 | 10.11.25 | 17.11.25 | Nirmal Mahto | Complete | 47.184 |  |  | 33
493 | 9 | 19/11 | DA+9 | 11.11.25 | 19.11.25 | Sunny Const | Complete | 47.184 |  |  | 53
494 | 10 | 21/11 | DA+9 | 17.11.25 | 21.11.25 | Chinta Devi | Complete | 47.184 |  |  | 65
495 | 11 | 18/6 | DA+3 | 17.10.25 | 21.11.25 | Sunny Const | Completed (ROW since 21.10.25 to 21.11.25 ) | 38.847 | Prem Sagar |  |  |  |  | 19/9 G
496 | 12 | 3/0 | DD60+3 | 11.11.25 | 22.11.25 | Panva Devi | Complete | 89.909 |  | 6/0 F | 50
497 | 13 | 10/23 | DA+9 | 14.11.25 | 24.11.25 | Vedanta Const | Complete | 47.184 |  |  | 27
498 | 14 | 17/1 | DA+3 | 18.11.25 | 26.11.25 | Vivek Ganju | Complete | 38.847 |  | 19/1 | 28
499 | 15 | 11/0 | DB1+0 | 18.11.25 | 26.11.25 | Nirmal Mahto | Complete | 57.597 |  | 11/1 | 33
500 | 16 | 14/6 | DA+0 | 21.11.25 | 29.11.25 | Laxmi | Complete | 37.504 |  | 13/4 | 35
501 | 17 | 19/5 | DA+3 | 21.11.25 | 30.11.25 | Sunny Const | Complete | 38.847 |  | 19/4 | 53
502 | 18 | 21/9 | DA+6 | 27.11.25 | 30.11.25 | Chinta Devi | Complete | 45.413 |  | Due to non-avaibility of WF team shift to PKG-F | 65
Dec'25
503 | 1 | 10/22 | DA+0 | 25.11.25 | 02.12.25 | Vedanta Const | Complete | 37.504 |  |  | 27
504 | 2 | 11/10 | DB1+0 | 21.11.25 | 04.12.25 | Sital Singh | Complete | 57.597 |  | PKG-F | 22
505 | 3 | 13/4 | DA+0 | 28.11.25 | 05.12.25 | Vivek Ganju | Complete | 37.504 |  |  | 30
506 | 4 | 11/1 | DA+6 | 27.11.25 | 05.12.25 | Nirmal Mahto | Complete | 45.413 |  | 11/1 -F | 33
507 | 5 | 19/1 | DA+6 | 26.11.25 | 06.12.25 | Poonam | Complete | 45.413 |  |  | 16
508 | 6 | 19/4 | DA+0 | 01.12.25 | 07.12.25 | Sunny Const | Complete | 37.504 |  |  | 53
509 | 7 | 13/2 | DA+3 | 02.12.25 | 10.12.25 | Laxmi | Complete | 38.847 |  | 13/1-F | 35
510 | 8 | 22/8 | DA+6 | 03.12.25 | 12.12.25 | Ganesg Sinha | Complete | 45.413 |  | 27/9 -F | 32
511 | 9 | 21/1 | DA+3 | 05.12.25 | 12.12.25 | Jirwa Devi | Complete | 38.847 |  | 31/0-F | 28
512 | 10 | 19/6 | DA+3 | 09.12.25 | 14.12.25 | Sunny Const | Complete | 38.847 |  |  | 62
513 | 11 | 13/3 | DA+0 | 07.12.25 | 15.12.25 | Vivek Ganju | Complete | 37.504 |  | 13/3-F | 30
514 | 12 | 19/13 | DA+0 | 15.12.25 | 22.12.25 | Vinay Cons | Complete | 37.504 |  |  | 33
515 | 13 | 21/10 | DA+9 | 21.12.25 | 28.12.25 | Jirwa Devi | Complete | 47.184 |  |  | 32
516 | 14 | 19/12 | DB1+3 | 21.12.25 | 27.12.25 | Sobha Devi | Complete | 60.096
Jan'26
517 | 1 | 18/3 | DA+3 | 08.01.26 | 20.01.26 | Vedanta Const | Complete | 38.847
Feb'26
518 | 1 | 8/7 | DB1+0 | 07.02.26 | 12.02.26 | Sobha Devi | Complete | 57.597
519 | 2 | 10/2 | DA+0 | 11.02.26 | 15.02.26 | Sunny Const. | Complete | 37.504
520 | 4 | 8/8 | DA+6 | 12.02.26 | 17.02.26 | Sobha Devi | Complete | 45.413
521 | 3 | 18/5 | DA+3 | 09.01.26 | 21.02.26 | Chinta Devi | Complete | 38.847

## Tack Welding - PKG-G
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Tack Welding
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Dt. of Start | Dt. of Complete | Tack Welding Status | Name of Sub-Contractor | Ramarks
2023-10-01
1 | 1 |  | 57/12 | DA+3 | 24.10.23 | 25.10.23 | Done | Suraja Ram
2 | 2 |  | 57/13 | DA+0 | 24.10.23 | 25.10.23 | Done | Suraja Ram
3 | 3 |  | 57/11 | DA+0 | 25.10.23 | 26.10.23 | Done | Suraja Ram
4 | 4 |  | 57/10 | DA+3 | 26.10.23 | 27.10.23 | Done | Suraja Ram
5 | 5 |  | 57/9 | DA+0 | 27.10.23 | 29.10.23 | Done | Suraja Ram
2023-11-01
6 | 1 |  | 57/4 | DA+0 | 31.10.23 | 01.11.23 | Done | Suraja Ram
7 | 2 |  | 57/3 | DA+0 | 01.11.23 | 02.11.23 | Done | Suraja Ram
8 | 3 |  | 57/2 | DA+0 | 02.11.23 | 03.11.2023 | Done | Suraja Ram
9 | 4 |  | 57/5 | DA+3 | 03.11.2023 | 04.11.2023 | Done | Suraja Ram
10 | 5 |  | 58/8 | DA+0 | 05.11.2023 | 06.111.23 | Done | Suraja Ram
11 | 6 |  | 58/9 | DA+0 | 06.111.23 | 07.11.23 | Done | Suraja Ram
12 | 7 |  | 57/8 | DA+3 | 07.11.23 | 08.11.23 | Done | Suraja Ram
13 | 8 |  | 58/11 | DA+3 | 09.11.23 | 27.11.23 | Done | Suraja Ram
14 | 9 |  | 58/12 | DA+0 | 27.11.23 | 28.11.23 | Done | Suraja Ram
15 | 10 |  | 57/1 | DA+3 | 28.11.23 | 30.11.23 | Done | Suraja Ram
2023-12-01
16 | 1 |  | 56/9 | DA+3 | 30.11.23 | 02.12.23 | Done | Suraja Ram
17 | 2 |  | 56/8 | DA+3 | 02.12.23 | 03.12.23 | Done | Suraja Ram
18 | 3 |  | 56/7 | DA+3 | 06.12.23 | 06.12.23 | Done | Suraja Ram
19 | 4 |  | 58/14 | DA+0 | 07.12.23 | 07.12.23 | Done | Suraja Ram
20 | 5 |  | 58/16 | DA+0 | 13.12.23 | 13.12.23 | Done | Suraja Ram
21 | 6 |  | 58/10 | DA+3 | 14.12.23 | 15.12.23 | Done | Suraja Ram
22 | 7 |  | 59/1 | DA+0 | 18.12.23 | 18.12.23 | Done | Suraja Ram
23 | 8 |  | 59/2 | DA+0 | 19.12.23 | 19.12.23 | Done | Suraja Ram
24 | 9 |  | 59/3 | DA+0 | 20.12.23 | 20.12.23 | Done | Suraja Ram
25 | 10 |  | 59/5 | DA+0 | 21.12.23 | 21.12.23 | Done | Suraja Ram
26 | 11 |  | 59/6 | DA+0 | 22.12.23 | 22.12.23 | Done | Suraja Ram
27 | 12 |  | 56/3 | DA+0 | 23.12.23 | 23.12.23 | Done | Suraja Ram
28 | 13 |  | 56/4 | DA+3 | 24.12.23 | 24.12.23 | Done | Suraja Ram
29 | 14 |  | 55/4 | DA+3 | 25.12.23 | 25.12.23 | Done | Suraja Ram
30 | 15 |  | 55/5 | DA+0 | 26.12.23 | 26.12.23 | Done | Suraja Ram
31 | 16 |  | 51/5 | DA+0 | 21.12.23 | 26.12.23 | Done | Kailash Nath
32 | 17 |  | 51/4 | DA+3 | 21.12.23 | 26.12.23 | Done | Kailash Nath
33 | 18 |  | 51/3 | DA+0 | 26.12.23 | 27.12.23 | Done | Kailash Nath
34 | 19 |  | 51/2 | DA+0 | 27.12.23 | 28.12.23 | Done | Kailash Nath
35 | 20 |  | 55/6 | DA+3 | 29.12.23 | 29.12.23 | Done | Suraja Ram
36 | 21 |  | 51/7 | DA+3 | 29.12.23 | 29.12.23 | Done | Kailash Nath
37 | 22 |  | 51/10 | DA+3 | 29.12.23 | 30.12.23 | Done | Kailash Nath
38 | 23 |  | 52/1 | DA+0 | 30.12.23 | 30.12.23 | Done | Kailash Nath
39 | 24 |  | 55/7 | DA+0 | 30.12.23 | 30.12.23 | Done | Suraja Ram
40 | 25 |  | 55/9 | DA+3 | 31.12.23 | 31.12.23 | Done | Suraja Ram
41 | 26 |  | 52/2 | DA+3 | 31.12.23 | 31.12.23 | Done | Kailash Nath
2024-01-01
42 | 1 |  | 55/10 | DA+3 | 02.01.24 | 02.01.24 | Done | Suraja Ram
43 | 2 |  | 55/11 | DA+3 | 02.01.24 | 02.01.24 | Done | Suraja Ram
44 | 3 |  | 52/5 | DA+3 | 02.01.24 | 02.01.24 | Done | Kailash Nath
45 | 4 |  | 57/7 | DA+3 | 03.01.24 | 03.01.24 | Done | Suraja Ram
46 | 5 |  | 58/5 | DA+3 | 04.01.24 | 05.01.24 | Done | Suraja Ram
47 | 6 |  | 57/6 | DB1+0 | 06.01.24 | 06.01.24 | Done | Suraja Ram
48 | 7 |  | 57/0 | DB2+0 | 07.01.24 | 07.01.24 | Done | Suraja Ram
49 | 8 |  | 56/6 | DA+3 | 08.01.24 | 08.01.24 | Done | Suraja Ram
50 | 9 |  | 56/2 | DA+3 | 11.01.24 | 12.01.24 | Done | Suraja Ram
51 | 10 |  | 56/5 | DA+0 | 13.01.24 | 13.01.24 | Done | Suraja Ram
52 | 11 |  | 56/0 | DB1+0 | 13.01.24 | 13.01.24 | Done | Suraja Ram
53 | 12 |  | 55/8 | DA+3 | 14.1.24 | 14.1.24 | Done | Suraja Ram
54 | 13 |  | 58/1 | DA+0 | 16.01.2024 | 16.01.2024 | Done | Suraja Ram
55 | 14 |  | 58/4 | DA+0 | 17.01.2024 | 17.01.2024 | Done | Suraja Ram
56 | 15 |  | 58/6 | DA+3 | 19.01.24 | 19.01.24 | Done | Suraja Ram
57 | 16 |  | 50/4 | DA+3 | 22.01.24 | 22.01.24 | Done | Ramagora
58 | 17 |  | 50/3 | DA+0 | 24.01.24 | 24.01.24 | Done | Ramagora
59 | 18 |  | 44/4 | DA+0 | 25.01.24 | 25.01.24 | Done | Ramagora
60 | 19 |  | 58/3 | DA+3 | 27.01.24 | 27.01.24 | Done | Suraja Ram
61 | 20 |  | 44/2 | DA+0 | 27.01.24 | 27.01.24 | Done | Ramagora
62 | 21 |  | 41/10 | DA+0 | 28.01.24 | 28.01.24 | Done | Ramagora
63 | 22 |  | 41/11 | DA+3 | 29.01.24 | 29.01.24 | Done | Ramagora
64 | 23 |  | 58/7 | DB+0 | 29.01.24 | 29.01.24 | Done | Suraja Ram
65 | 24 |  | 41/7 | DA+3 | 30.01.24 | 30.01.24 | Done | Ramagora
66 | 25 |  | 58/15 | DA+3 | 30.01.24 | 30.01.24 | Done | Suraja Ram
67 | 26 |  | 47/2 | DA+0 | 31.01.24 | 31.01.24 | Done | Ramagora
Feb-24
68 | 1 |  | 59/0 | DB+0 | 01.02.24 | 01.02.24 | Done | Suraja Ram
69 | 2 |  | 46/3 | DA+0 | 01.02.24 | 01.02.24 | Done | Ramagora
70 | 3 |  | 61/1 | DA+0 | 02.02.24 | 02.02.24 | Done | Suraja Ram
71 | 4 |  | 48/1 | DA+0 | 03.02.24 | 03.02.24 | Done | Ramagora
72 | 5 |  | 51/9 | DA+3 | 04.02.24 | 04.02.24 | Done | Ramagora
73 | 6 |  | 55/1 | DA+3 | 04.02.24 | 04.02.24 | Done | Suraja Ram
74 | 7 |  | 55/2 | DA+3 | 04.02.24 | 05.02.24 | Done | Suraja Ram
75 | 8 |  | 52/4 | DA+0 | 04.02.24 | 05.02.24 | Done | Ramagora
76 | 9 |  | 55/3 | DA+0 | 06.02.24 | 06.02.24 | Done | Suraja Ram
77 | 10 |  | 53/4 | DA+3 | 07..02.24 | 07..02.24 | Done | Suraja Ram
78 | 11 |  | 51/8 | DA+3 | 07..02.24 | 07..02.24 | Done | Ramagora
79 | 12 |  | 53/3 | DA+3 | 08.02.24 | 08.02.24 | Done | Suraja Ram
80 | 13 |  | 51/6 | DA+0 | 09.02.24 | 09.02.24 | Done | Ramagora
81 | 14 |  | 43/1 | DA+9 | 10.02.24 | 10.02.24 | Done | Ramagora
82 | 15 |  | 48/2 | DA+3 | 12.02.24 | 12.02.24 | Done | Suraja Ram
83 | 16 |  | 41/5 | DA+0 | 14.02.24 | 14.02.24 | Done | Ramagora
84 | 17 |  | 47/0 | DB+0 | 16.02.24 | 16.02.24 | Done | Suraja Ram |  | 23
85 | 18 |  | 46/2 | DA+0 | 17.02.24 | 17.02.24 | Done | Suraja Ram |  | 16
86 | 19 |  | 53/1 | DA+0 | 23.02.24 | 23.02.24 | Done | Suraja Ram |  | 7
87 | 20 |  | 52/0 | DB+0 | 24.02.24 | 24.02.24 | Done | Suraja Ram
88 | 21 |  | 44/3 | DA+3 | 27.02.24 | 27.02.24 | Done | Ramagora
89 | 22 |  | 43/5 | DA+0 | 28.02.24 | 28.02.24 | Done | Ramagora
90 | 23 |  | 41/9 | DA+0 | 29.02.24 | 29.02.24 | Done | Ramagora
March'24
91 | 1 |  | 41/8 | DA+0 | 04.03.24 | 04.03.24 | Done | Ramagora
92 | 2 |  | 41/4 | DA+0 | 05.03.24 | 05.03.24 | Done | Ramagora
93 | 3 |  | 41/6 | DA+0 | 07.03.24 | 07.03.24 | Done | Ramagora
94 | 4 |  | 53/2 | DA+3 | 08.03.24 | 08.03.24 | Done | Suraja Ram
95 | 5 |  | 43/4 | DA+9 | 09.03.24 | 09.03.24 | Done | Ramagora
96 | 6 |  | 51/1 | DA+0 | 11.03.24 | 11.03.24 | Done | Ramagora
97 | 7 |  | 51/0 | DB+0 | 28.03.24 | 28.03.24 | Done | Ramagora |  | Sanjay
| April'24 | [8 empty] | Manoj
98 | 1 |  | 47/3 | DA+0 | 20.04.24 | 21.04.24 | Done | Ramagora
99 | 2 |  | 56/1 | DA+3 | 24.04.24 | 24.04.24 | Done | Ramagora |  | publesh
| May'24 | [8 empty] | Pradeep
100 | 1 |  | 58/0 | DC2+0 | 04.05.24 | 04.05.24 | Done | Suraja Ram
101 | 2 |  | 61/2 | DA+0 | 06.05.24 | 06.05.24 | Done | Suraja Ram
102 | 3 |  | 44/1 | DA+0 | 12.05.24 | 12.05.24 | Done | Ramagora
103 | 4 |  | 55/0 | DC+0 | 24.05.24 | 24.05.24 | Done | Suraja Ram
104 | 5 |  | 65/5 | DA+0 | 30.05.24 | 30.05.24 | Done | Suraja Ram
105 | 6 |  | 65/4 | DA+0 | 31.05.24 | 31.05.24 | Done | Suraja Ram
June'24
106 | 1 |  | 58/2 | DA+0 | 02.06.24 | 02.06.24 | Done | Suraja Ram
107 | 2 |  | 65/3 | DA+0 | 02.06.24 | 02.06.24 | Done | Suraja Ram
108 | 3 |  | 53/0 | DC2+3 | 22.06.24 | 22.06.24 | Done | Suraja Ram
109 | 4 |  | 52/3 | DA+0 | 24.06.24 | 24.06.24 | Done | Suraja Ram
July'24
110 | 1 |  | 48/0 | DB+0 | 23.07.24 | 23.07.24 | Done | Suraja Ram
Sept'24
111 | 1 |  | 46/4 | DA+0 | 16.09.24 | 16.09.24 | Done | Suraja Ram
112 | 2 |  | 47/1 | DA+0 | 19.09.24 | 19.09.24 | Done | Suraja Ram
113 | 3 |  | 50/2 | DA+0 | 20.09.24 | 20.09.24 | Done | Suraja Ram
114 | 4 |  | 50/1 | DA+0 | 22.09.24 | 22.09.24 | Done | Suraja Ram
115 | 5 |  | 72/4 | DA+0 | 26.09.24 | 26.09.24 | Done | Suraja Ram
116 | 6 |  | 72/5 | DA+0 | 26.09.24 | 26.09.24 | Done | Suraja Ram
117 | 7 |  | 72/3 | DA+0 | 29.09.24 | 29.09.24 | Done | Suraja Ram
118 | 8 |  | 72/6 | DA+0 | 29.09.24 | 29.09.24 | Done | Suraja Ram
119 | 9 |  | 71/5 | DA+0 | 29.09.24 | 29.09.24 | Done | Suraja Ram
Oct'24
120 | 1 |  | 72/0 | DB1+0 | 04.10.24 | 04.10.24 | Done | Suraja Ram
121 | 2 |  | 50/0 | DC2+3 | 04.10.24 | 05.10.24 | Done | Suraja Ram
122 | 3 |  | 71/4 | DA+0 | 13.10.24 | 13.10.24 | Done | Suraja Ram
123 | 4 |  | 72/2 | DA+0 | 14.10.24 | 14.10.24 | Done | Suraja Ram
124 | 5 |  | 71/2 | DA+0 | 15.10.24 | 15.10.24 | Done | Suraja Ram
125 | 6 |  | 71/1 | DA+0 | 16.10.24 | 16.10.24 | Done | Suraja Ram
126 | 7 |  | 68/1 | DA+3 | 19.10.24 | 19.10.24 | Done | Suraja Ram
127 | 8 |  | 72/1 | DA+0 | 19.10.24 | 19.10.24 | Done | Suraja Ram
128 | 9 |  | 15/2 | #REF! | 2024-10-31 | 2024-10-31 | Done | SB Enterprises | Painting done
129 | 10 |  | 29/5 | #REF! | 2024-10-31 | 2024-10-31 | Done | SB Enterprises
130 | 11 |  | 29/6 | #REF! | 2024-10-31 | 2024-10-31 | Done | SB Enterprises
131 | 12 |  | 29/7 | #REF! | 2024-10-31 | 2024-10-31 | Done | SB Enterprises
132 | 13 |  | 29/8 | #REF! | 2024-10-31 | 2024-10-31 | Done | SB Enterprises | Painting done
133 | 14 |  | 29/10 | #REF! | 2024-10-31 | 2024-10-31 | Done | SB Enterprises | Painting done
Nov'24
134 | 1 | 1 | 69/6 | DA+0 | 04.11.24 | 04.11.24 | Done | Suraja Ram
135 | 2 | 2 | 72/7 | DB1+9 | 09.11.24 | 09.11.24 | Done | Suraja Ram
136 | 3 | 3 | 68/6 | DA+3 | 14.11.24 | 14.11.24 | Done | Suraja Ram
137 | 4 | 4 | 71/3 | DA+0 | 14.11.24 | 14.11.24 | Done | Suraja Ram
138 | 5 | 5 | 68/3 | DA+0 | 14.11.24 | 14.11.24 | Done | Suraja Ram
139 | 6 | 6 | 66/2 | DA+0 | 14.11.24 | 14.11.24 | Done | Suraja Ram
140 | 7 | 7 | 73/0 | DD45+9 | 17.11.24 | 17.11.24 | Done | Suraja Ram
141 | 8 | 8 | 68/4 | DA+3 | 20.11.24 | 20.11.24 | Done | Suraja Ram
142 | 9 | 9 | 68/2 | DA+3 | 20.11.24 | 20.11.24 | Done | Suraja Ram
143 | 10 | 10 | 68/5 | DA+3 | 20.11.24 | 20.11.24 | Done | Suraja Ram
144 | 11 | 11 | 69/7 | DA+0 | 22.11.24 | 22.11.24 | Done | Suraja Ram
145 | 12 |  | 16/5 | #REF! | 2024-11-05 | 2024-11-05 | Done | SB Enterprises | Painting done
146 | 13 |  | 16/3 | #REF! | 2024-11-07 | 2024-11-07 | Done | SB Enterprises | Painting done
147 | 14 |  | 15/4 | #REF! | 2024-11-08 | 2024-11-08 | Done | SB Enterprises | Painting done
148 | 15 |  | 15/3 | #REF! | 2024-11-09 | 2024-11-09 | Done | SB Enterprises | Painting done
149 | 16 |  | 16/4 | #REF! | 2024-11-13 | 2024-11-13 | Done | SB Enterprises | Painting done
Dec'24
150 | 1 |  | 69/5 | DA+0 | 08.12.24 | 08.12.24 | Done | Suraja Ram
151 | 2 |  | 69/1 | DA+0 | 10.12.24 | 10.12.24 | Done | Suraja Ram
152 | 3 |  | 69/2 | DA+0 | 11.12.24 | 11.12.24 | Done | Suraja Ram
153 | 4 |  | 66/4 | DA+3 | 12.12.24 | 12.12.24 | Done | Suraja Ram
154 | 5 |  | 66/1 | DA+3 | 15.12.24 | 15.12.24 | Done | Suraja Ram
155 | 6 |  | 68/0 | DD45+0 | 16.12.24 | 16.12.24 | Done | Suraja Ram
156 | 7 |  | 67/1 | DB1+9 | 20.12.24 | 20.12.24 | Done | Suraja Ram
157 | 8 |  | 43/3 | DA+3 | 21.12.24 | 21.12.24 | Done | Suraja Ram
158 | 9 |  | 69/0 | DB1+0 | 22.12.24 | 22.12.24 | Done | Suraja Ram
159 | 10 |  | 58/13 | DA+0 | 26.12.24 | 26.12.24 | Done | Suraja Ram
160 | 11 |  | 69/3 | DA+0 | 26.12.24 | 26.12.24 | Done | Suraja Ram
161 | 12 |  | 69/4 |  | 27.12.24 | 27.12.24 | Done | Suraja Ram
162 | 14 |  | 38/1 | DA+3 | 29.12.24 | 29.12.24 | Done | Suraja Ram
163 | 15 |  | 38/2 | DA+6 | 30.12.24 | 30.12.24 | Done | Suraja Ram
164 | 16 |  | 69/8 | DA+0 | 31.12.24 | 31.12.24 | Done | Suraja Ram
165 | 17 |  | 69/9 | DA+0 | 31.12.24 | 31.12.24 | Done | Suraja Ram
Jan'25
166 | 1 |  | 37/3 | DA+0 | 02.01.25 | 02.01.25 | Done | Suraja Ram
167 | 2 |  | 38/3 | DA+9 | 04.01.25 | 04.01.25 | Done | Suraja Ram
168 | 3 |  | 37/4 | DA+6 | 09.01.25 | 09.01.25 | Done | Suraja Ram
169 | 4 |  | 67/0 | DD45+0 | 15.01.25 | 15.01.25 | Done | Suraja Ram
170 | 5 |  | 59/4 | DA+0 | 16.01.25 | 16.01.25 | Done | Suraja Ram
171 | 6 |  | 41/2 | DA+0 | 18.01.25 | 18.01.25 | Done | Suraja Ram
172 | 7 |  | 71/0 | DD60+0 | 12.01.25 | 12.01.25 | Done | Suraja Ram
173 | 8 |  | 37/2 | DB1+6 | 20.01.25 | 20.01.25 | Done | Suraja Ram
174 | 9 |  | 70/0 | DD60+0 | 24.01.25 | 24.01.25 | Done | Suraja Ram
Feb'25
175 | 1 |  | 41/12 | DA+3 | 01.02.25 | 01.02.25 | Done | Suraja Ram
176 | 2 |  | 41/3 | DA+0 | 01.02.25 | 01.02.25 | Done | Suraja Ram
177 | 3 |  | 37/5 | DA+3 | 02.02.25 | 02.02.25 | Done | Suraja Ram
178 | 4 |  | 37/6 | DA+6 | 03.02.25 | 04.02.25 | Done | Suraja Ram
179 | 5 |  | 37/7 | DA+3 | 04.02.25 | 04.02.25 | Done | Suraja Ram
180 | 6 |  | 37/8 | DA+0 | 06.02.25 | 06.02.25 | Done | Suraja Ram
181 | 7 |  | 41/1 | DA+3 | 07.02.25 | 07.02.25 | Done | Suraja Ram
182 | 8 |  | 42/0 | DC2+9 | 08.02.25 | 08.02.25 | Done | Suraja Ram
183 | 9 |  | 65/6 | DA+0 | 20.02.25 | 20.02.25 | Done | Suraja Ram
184 | 10 |  | 65/7 | DA+0 | 21.02.25 | 21.02.25 | Done | Suraja Ram
185 | 11 |  | 40/11 | DA+3 | 24.02.25 | 24.02.25 | Done | Suraja Ram
186 | 12 |  | 40/10 | DA+3 | 24.02.25 | 24.02.25 | Done | Suraja Ram
187 | 13 |  | 40/2 |  | 26.02.25 | 26.02.25 | Done | Suraja Ram
188 | 14 |  | 40/3 |  | 28.02.26 | 28.02.26 | Done | Suraja Ram
189 | 15 |  | 41/0 |  | 27.02.25 | 27.02.25 | Done | Suraja Ram
Mar'25
190 | 1 |  | 40/12 |  | 03.03.25 | 03.03.25 | Done | Suraja Ram
191 | 2 |  | 38/0 |  | 06.03.25 | 06.03.25 | Done | Suraja Ram
192 | 3 |  | 40/6 |  | 07.03.25 | 07.03.25 | Done | Suraja Ram
193 | 4 |  | 40/7 |  | 08.03.25 | 08.03.25 | Done | Suraja Ram
194 | 5 |  | 60/0 |  | 13.03.25 | 13.03.25 | Done | Suraja Ram
195 | 6 |  | 39/0 |  | 18.03.25 | 18.03.25 | Done | Suraja Ram
196 | 7 |  | 40/0 |  | 19.03.25 | 19.03.25 | Done | Suraja Ram
197 | 8 |  | 40/1 |  | 20.03.25 | 20.03.25 | Done | Suraja Ram
198 | 9 |  | 38/8 |  | 22.03.25 | 22.03.25 | Done | Suraja Ram
199 | 10 |  | 38/9 |  | 23.03.25 | 23.03.25 | Done | Suraja Ram
200 | 11 |  | 38/7 |  | 24.03.35 | 24.03.35 | Done | Suraja Ram
April'25
201 | 1 |  | 38/6 |  | 07.04.25 | 07.04.25 | Done | Suraja Ram
202 | 2 |  | 38/5 |  | 11.04.25 | 11.04.25 | Done | Suraja Ram
203 | 3 |  | 38/4 |  | 13.04.25 | 13.04.25 | Done | Suraja Ram
204 | 4 |  | 49/0 |  | 17.04.25 | 17.04.25 | Done | Suraja Ram
205 | 5 |  | 44/0 |  | 19.04.25 | 19.04.25 | Done | Suraja Ram
206 | 6 |  | 43/6 |  | 19.04.25 | 19.04.25 | Done | Suraja Ram
207 | 7 |  | 43/2 |  | 20.04.25 | 20.04.25 | Done | Suraja Ram
208 | 8 |  | 40/4 |  | 21.04.25 | 21.04.25 | Done | Suraja Ram
209 | 9 |  | 40/5 |  | 22.04.25 | 22.04.25 | Done | Suraja Ram
210 | 10 |  | 35/9 |  | 24.04.25 | 24.04.25 | Done | Suraja Ram
211 | 11 |  | 35/8 |  | 25.04.25 | 25.04.25 | Done | Suraja Ram
212 | 12 |  | 43/0 |  | 26.04.25 | 26.04.25 | Done | Suraja Ram
213 | 13 |  | 61/0 | DB1+6 | 27.04.25 | 28.04.25 | Done | Suraja Ram
2025-05-25
214 | 1 |  | 63/5 |  | 13.05.25 | 13.05.25 | Done | Suraja Ram
215 | 2 |  | 63/4 |  | 14.05.25 | 14.05.25 | Done | Suraja Ram
216 | 3 |  | 63/1 |  | 15.05.25 | 15.05.25 | Done | Suraja Ram
217 | 4 |  | 63/2 |  | 24.05.25 | 24.05.25 | Done | Suraja Ram
218 | 5 |  | 66/0 |  | 31.05.25 | 31.05.25 | Done | Suraja Ram
2025-06-25
219 | 1 |  | 62/0 | DC+0 | 03.06.25 | 03.06.25 | Done | Suraja Ram
220 | 2 |  | 63/0 |  | 05.06.25 | 05.06.25 | Done | Suraja Ram
221 | 3 |  | 32/0 | DB2+6 | 06.06.25 | 06.06.25 | Done | Chandea Enterprises
222 | 4 |  | 29/9 | DA+3 | 06.06.25 | 06.06.25 | Done | Chandea Enterprises
223 | 5 |  | 32/1 | DA+9 | 06.06.25 | 06.06.25 | Done | Chandea Enterprises
224 | 6 |  | 32/2 |  | 07.06.25 | 07.02.25 | Done | Chandea Enterprises
225 | 7 |  | 63/3 |  | 05.06.25 | 05.06.25 | Done | Suraja Ram
226 | 8 |  | 63/6 |  | 05.06.25 | 05.06.25 | Done | Suraja Ram
227 | 9 |  | 19/14 |  | 15.05.25 | 15.05.25 | Done | Rajesh
228 | 10 |  | 64/9 |  | 11.06.25 | 11.06.25 | Done | Suraja Ram
229 | 11 |  | 64/6 |  | 11.06.25 | 11.06.25 | Done | Suraja Ram
230 | 12 |  | 46/1 | DA+6 | 14.06.25 | 14.06.25 | Done | Suraja Ram
231 | 13 |  | 44/5 | DA+6 | 14.06.25 | 14.06.25 | Done | Suraja Ram
232 | 14 |  | 35/5 |  | 17.06.25 | 17.06.25 | Done | Suraja Ram
233 | 15 |  | 35/7 |  | 17.06.25 | 17.06.25 | Done | Suraja Ram
234 | 16 |  | 35/6 |  | 17.06.25 | 17.06.25 | Done | Suraja Ram
235 | 17 |  | 34/4 | DA+6 | 19.06.25 | 19.06.25 | Done | Suraja Ram
236 | 18 |  | 15/6 |  |  |  | Done | Bajrang
237 | 19 |  | 39/3 |  | 26.06.25 | 26.06.25 | Done | Suraja Ram
238 | 20 |  | 39/1 |  | 30.06.25 | 30.06.25 | Done | Suraja Ram
July'25
239 | 1 |  | 39/2 |  | 05.07.25 | 05.07.25 | Done | Suraja Ram
240 | 2 |  | 40/9 |  | 05.07.25 | 05.07.25 | Done | Suraja Ram
241 | 3 |  | 39/4 |  | 05.07.25 | 05.07.25 | Done | Suraja Ram
242 | 4 |  | 40/8 |  | 07.07.25 | 07.07.25 | Done | Suraja Ram
243 | 5 |  | 39/5 |  | 07.07.25 | 07.07.25 | Done | Suraja Ram
244 | 6 |  | 39/6 |  | 10.7.25 | 10.7.25 | Done | Suraja Ram
245 | 7 |  | 39/7 |  | 12.07.25 | 12.07.25 | Done | Suraja Ram
246 | 8 |  | 45/0 |  | 15.07.25 | 15.07.25 | Done | Suraja Ram
247 | 9 |  | 64/8 |  | 15.07.25 | 15.07.25 | Done | Suraja Ram
248 | 10 |  | 31/4 |  | 22.07.25 | 22.07.25 | Done | Suraja Ram
249 | 11 |  | 31/3 |  | 22.07.25 | 22.07.25 | Done | Suraja Ram
250 | 12 |  | 15/7 |  | 23.07.25 | 23.07.25 | Done | Shiv Power
251 | 13 |  | 15/9 |  | July | July | Done | SB Enterprises
252 | 14 |  | 14/5 |  | July | July | Done | SB Enterprises
253 | 15 |  | 31/2 |  | 23.07.25 | 23.07.25 | Done | Suraja Ram
254 | 16 |  | 10/14 |  | 20.07.25 | 20.07.25 | Done | Shiv Power
255 | 17 |  | 32/3 |  | 24.07.25 | 24.07.25 | Done | Suraja Ram
256 | 18 |  | 32/4 |  | 24.07.25 | 24.07.25 | Done | Suraja Ram
257 | 19 |  | 13/0 |  | 24.07.25 | 24.07.25 | Done | Shiv Power
258 | 20 |  | 15/8 |  | 25.07.25 | 25.07.25 | Done | Shiv Power
259 | 21 |  | 15/1 |  | 26.07.25 | 26.07.25 | Done | Shiv Power
260 | 22 |  | 11/13 |  | 27.07.25 | 27.07.25 | Done | Shiv Power
261 | 23 |  | 11/12 |  | 27.07.25 | 27.07.25 | Done | Shiv Power
262 | 24 |  | 11/15 |  | 27.07.25 | 27.07.25 | Done | Shiv Power
263 | 25 |  | 32/5 |  | 27.07.25 | 27.07.25 | Done | Suraja Ram
264 | 26 |  | 31/0 |  | 28.07.25 | 28.07.25 | Done | Suraja Ram
265 | 27 |  | 64/0 |  | 29.07.25 | 29.07.25 | Done | Suraja Ram
266 | 28 |  | 64/1 |  | 30.07.25 | 30.07.25 | Done | Suraja Ram
267 | 29 |  | 64/4 |  | 31.07.25 | 31.07.25 | Done | Suraja Ram
2025-08-25
268 | 1 |  | 64/7 |  | 01.08.25 | 01.08.25 | Done | Suraja Ram
269 | 2 |  | 64/5 |  | 02.08.25 | 02.08.25 | Done | Suraja Ram
270 | 3 |  | 64/2 |  | 03.08.25 | 03.08.25 | Done | Suraja Ram
271 | 4 |  | 64/3 |  | 04.08.25 | 04.08.25 | Done | Suraja Ram
272 | 5 |  | 46/0 |  | 06.08.25 | 07.08.25 | Done | Suraja Ram
273 | 6 |  | 35/4 |  | 08.08.25 | 08.08.25 | Done | Suraja Ram
274 | 7 |  | 1/0 |  |  |  | Done | B S Infra
275 | 8 |  | 1A/0 |  |  |  | Done | B S Infra
276 | 9 |  | 1A/1 |  |  |  | Done | B S Infra
277 | 10 |  | 1A/2 |  |  |  | Done | Shiv Power
278 | 11 |  | 1A/3 |  |  |  | Done | B S Infra
279 | 12 |  | 1A/7 |  |  |  | Done | B S Infra
280 | 13 |  | 2/0 |  |  |  | Done | B S Infra
281 | 14 |  | 2/1 |  |  |  | Done | Shiv Power
282 | 15 |  | 2/2 |  |  |  | Done | Shiv Power
283 | 16 |  | 2/3 |  |  |  | Done | B S Infra
284 | 17 |  | 8/9 |  |  |  | Done | Shiv Power
285 | 18 |  | 9/0 |  |  |  | Done | Bajrangbali
286 | 19 |  | 10/0 |  |  |  | Done | Bajrangbali
287 | 20 |  | 10/3 |  |  |  | Done | Shiv Power
288 | 21 |  | 10/4 |  |  |  | Done | Shiv Power
289 | 22 |  | 10/6 |  |  |  | Done | Shiv Power
290 | 23 |  | 10/7 |  |  |  | Done | Shiv Power
291 | 24 |  | 10/8 |  |  |  | Done | Shiv Power
292 | 25 |  | 10/9 |  |  |  | Done | Shiv Power
293 | 26 |  | 10/10 |  |  |  | Done | Shiv Power
294 | 27 |  | 10/12 |  |  |  | Done | Shiv Power
295 | 28 |  | 10/13 |  |  |  | Done | Shiv Power
296 | 29 |  | 10/21 |  |  |  | Done | Shiv Power
297 | 30 |  | 11/5 |  |  |  | Done | Shiv Power
298 | 31 |  | 35/2 |  | 11.08.25 | 11.08.25 | Done | Suraja Ram
299 | 32 |  | 35/3 |  | 11.08.25 | 11.08.25 | Done | Suraja Ram
300 | 33 |  | 35/1 |  | 12.08.25 | 12.08.25 | Done | Suraja Ram
301 | 34 |  | 35/0 |  | 18.08.25 | 19.08.25 | Done | Suraja Ram
302 | 35 |  | 37/1 |  | 20.08.25 | 20.08.25 | Done | Suraja Ram
303 | 36 |  | 30/2 |  | 23.08.25 | 23.08.25 | Done | Suraja Ram
304 | 37 |  | 30/1 |  | 24.08.25 | 24.08.25 | Done | Suraja Ram
305 | 38 |  | 31/1 |  | 27.08.25 | 27.08.25 | Done | Suraja Ram
306 | 39 |  | 16/6 |  | 28.08.25 | 28.08.25 | Done | Shiv Power
307 | 40 |  | 16/0 |  | 26.08.25 | 27.08.25 | Done | Shiv Power
308 | 41 |  | 16/1 |  | 28.08.25 | 29.08.25 | Done | Shiv Power
Sept'25
309 | 1 |  | 22/1 |  | 05.09.25 | 05.09.25 | Done | Munotosh
310 | 2 |  | 22/4 |  | 05.09.25 | 05.09.25 | Done | Munotosh
311 | 3 |  | 65/1 |  | 05.09.25 | 05.09.25 | Done | Suraja Ram
312 | 4 |  | 66/3 |  | 05.09.25 | 05.09.25 | Done | Suraja Ram
313 | 5 |  | 22/2 |  | 06.09.25 | 06.09.25 | Done | Munotosh
314 | 6 |  | 23/4 |  | 09.09.25 | 06.09.25 | Done | Munotosh
315 | 7 |  | 2/7 |  | 10.09.25 | 10.09.25 | Done
316 | 8 |  | 33/1 |  | 10.09.25 | 10.09.25 | Done | Suraja Ram
317 | 9 |  | 33/2 |  | 10.09.25 | 10.09.25 | Done | Suraja Ram
318 | 10 |  | 22/3 |  | 12.09.25 | 12.09.25 | Done | Munotosh
319 | 11 |  | 34/5 |  | 18.09.25 | 18.09.25 | Done | Suraja Ram
320 | 12 |  | 32/8 |  | 20.09.25 | 20.09.25 | Done | Suraja Ram
321 | 13 |  | 32/7 |  | 22.09.25 | 22.09.25 | Done | Suraja Ram
322 | 14 |  | 33/8 |  | 29.09.25 | 29.09.25 | Done | Suraja Ram
323 | 15 |  | 32/6 |  | 29.09.25 | 29.09.25 | Done | Suraja Ram
324 | 16 |  | 34/1 |  | 30.09.25 | 30.09.25 | Done | Suraja Ram
2025-10-25
325 | 1 |  | 34/2 |  | 01.10.25 | 01.10.25 | Done | Suraja Ram
326 | 2 |  | 36/0 |  | 03.10.25 | 03.10.25 | Done | Suraja Ram
327 | 3 |  | 33/5 |  | 04.10.25 | 04.10.25 | Done | Suraja Ram
328 | 4 |  | 65/2 |  | 06.10.25 | 06.10.25 | Done | Suraja Ram
329 | 5 |  | 65/0 |  | 08.10.25 | 08.10.25 | Done | Suraja Ram
330 | 6 |  | 33/0 |  | 14.10.25 | 14.10.25 | Done | Suraja Ram
331 | 7 |  | 33/4 |  | 14.10.25 | 14.10.25 | Done | Suraja Ram
332 | 8 |  | 34/0 |  | 16.10.25 | 16.10.25 | Done | Suraja Ram
333 | 9 |  | 33/6 |  | 21.10.25 | 21.10.25 | Done | Suraja Ram
334 | 10 |  | 33/7 |  | 21.10.25 | 21.10.25 | Done | Suraja Ram
335 | 11 |  | 34/3 |  | 22.10.25 | 22.10.25 | Done | Suraja Ram
336 | 12 |  | 25/8 |  | 29.10.25 | 29.10.25 | Done | Jai Bagrang Bali
337 | 13 |  | 25/3 |  | 29.10.25 | 29.10.25 | Done | Jai Bagrang Bali
338 | 14 |  | 25/4 |  | 29.10.25 | 29.10.25 | Done | Jai Bagrang Bali
339 | 15 |  | 25/5 |  | 29.10.25 | 29.10.25 | Done | Jai Bagrang Bali
340 | 16 |  | 25/6 |  | 29.10.25 | 29.10.25 | Done | Jai Bagrang Bali
341 | 17 |  | 22/6 |  | 29.10.25 | 29.10.25 | Done | Jai Bagrang Bali
342 | 18 |  | 25/9 |  | 30.10.25 | 30.10.25 | Done | Jai Bagrang Bali
343 | 19 |  | 25/11 |  | 31.10.25 | 31.10.25 | Done | Jai Bagrang Bali
344 | 20 |  | 18/2 |  | 31.10.25 | 31.10.25 | Done | Shiv Power
345 | 21 |  | 18/4 |  | 31.10.25 | 31.10.25 | Done | Shiv Power
346 | 22 |  | 17/4 |  | 31.10.25 | 31.10.25 | Done | Shiv Power
347 | 23 |  | 17/5 |  | 31.10.25 | 31.10.25 | Done | Shiv Power
348 | 24 |  | 18/9 |  | 31.10.25 | 31.10.25 | Done | Shiv Power
349 | 25 |  | 2/4 |  | 26.10.25 | 26.10.25 | Done | Shiv Power
350 | 26 |  | 2/5 |  | 27.10.25 | 27.10.25 | Done | Shiv Power
351 | 27 |  | 2/6 |  | 28.10.25 | 28.10.25 | Done | Shiv Power
352 | 28 |  | 2/8 |  | 29.10.25 | 29.10.25 | Done | Shiv Power
353 | 29 |  | 2/9 |  | 30.10.25 | 30.10.25 | Done | Shiv Power
354 | 30 |  | 19/0 |  | 31.10.25 | 31.10.25 | Done | Shiv Power
355 | 31 |  | 19/2 |  | 31.10.25 | 31.10.25 | Done | Shiv Power
2025-11-25
356 | 1 |  | 18/7 |  | 01..11.25 | 01..11.25 | Done | Shiv Power
357 | 2 |  | 25/10 |  | 01..11.25 | 01..11.25 | Done | Jai Bagrang Bali
358 | 3 |  | 19/9 |  | 02.11.25 | 02.11.25 | Done | Shiv Power
359 | 4 |  | 18/8 |  | 03.11.25 | 03.11.25 | Done | Shiv Power
360 | 5 |  | 26/0 |  | 03.11.25 | 03.11.25 | Done | Jai Bagrang Bali
361 | 6 |  | 24/1 |  | 08.11.25 | 08.11.25 | Done | Jai Bagrang Bali
362 | 7 |  | 24/5 |  | 08.11.25 | 08.11.25 | Done | Jai Bagrang Bali
363 | 8 |  | 24/6 |  | 08.11.25 | 08.11.25 | Done | Jai Bagrang Bali
364 | 9 |  | 29/1 |  | 08.11.25 | 08.11.25 | Done | Suraja Ram
365 | 10 |  | 29/2 |  | 10.11.25 | 10.11.25 | Done | Suraja Ram
366 | 11 |  | 29/0 |  | 10.11.25 | 10.11.25 | Done | Suraja Ram
367 | 12 |  | 24/4 |  | 08.11.25 | 08.11.25 | Done | Jai Bagrang Bali
368 | 13 |  | 24/2 |  | 11.11.25 | 11.11.25 | Done | Jai Bagrang Bali
369 | 14 |  | 29/3 |  | 12.11.25 | 12.11.25 | Done | Suraja Ram
370 | 15 |  | 29/4 |  | 12.11.25 | 12.11.25 | Done | Suraja Ram
371 | 16 |  | 19/10 |  | 12.11.25 | 12.11.25 | Done | Luxmi Const
372 | 17 |  | 24/3 |  | 12.11.25 | 12.11.25 | Done | Jai Bagrang Bali
373 | 18 |  | 24/0 |  | 13.11.25 | 13.11.25 | Done | Jai Bagrang Bali
374 | 19 |  | 28/9 |  | 17.11.25 | 17.11.25 | Done | Suraja Ram
375 | 20 |  | 15/0 |  | 18.11.25 | 18.11.25 | Done | Krishna Const.
376 | 21 |  | 28/2 |  | 18.11.25 | 18.11.25 | Done | Suraja Ram
377 | 22 |  | 28/3 |  | 18.11.25 | 18.11.25 | Done | Suraja Ram
378 | 23 |  | 19/3 |  | 20.11.25 | 20.11.25 | Done | Krishna Const.
379 | 24 |  | 28/5 |  | 20.11.25 | 20.11.25 | Done | Suraja Ram
380 | 25 |  | 28/7 |  | 20.11.25 | 20.11.25 | Done | Suraja Ram
381 | 26 |  | 22/7 |  | 21.11.25 | 21.11.25 | Done | Jai Bagrang Bali
382 | 27 |  | 28/1 |  | 21.11.25 | 21.11.25 | Done | Suraja Ram
383 | 28 |  | 27/5 |  | 22.11.25 | 22.11.25 | Done | Suraja Ram
384 | 29 |  | 27/4 |  | 23.11.25 | 23.11.25 | Done | Suraja Ram
385 | 30 |  | 28/4 |  | 23.11.25 | 23.11.25 | Done | Suraja Ram
386 | 31 |  | 28/6 |  | 24.11.25 | 24.11.25 | Done | Suraja Ram
387 | 32 |  | 28/8 |  | 25.11.25 | 25.11.25 | Done | Suraja Ram
388 | 33 |  | 4/1 |  | 23.11.25 | 23.11.25 | Done | Shiv Power
389 | 34 |  | 1A/4 |  | 12.11.25 | 12.11.25 | Done | Shiv Power
390 | 35 |  | 1A/5 |  | 13.11.25 | 13.11.25 | Done | Shiv Power
391 | 36 |  | 1A/6 |  | 14.11.25 | 14.11.25 | Done | Shiv Power
392 | 37 |  | 4/2 |  | 25.11.25 | 25.11.25 | Done | Shiv Power
393 | 38 |  | 4/3 |  | 27.11.25 | 27.11.25 | Done | Shiv Power
394 | 39 |  | 4/4 |  | 28.11.25 | 28.11.25 | Done | Shiv Power
395 | 40 |  | 22/9 |  | 22.11.25 | 22.11.25 | Done | Jai Bagrang Bali
396 | 41 |  | 25/1 |  | 06.11.25 | 06.11.25 | Done | Jai Bagrang Bali
397 | 42 |  | 25/2 |  | 05.11.25 | 05.11.25 | Done | Jai Bagrang Bali
398 | 43 |  | 25/7 |  | 07.11.25 | 07.11.25 | Done | Jai Bagrang Bali
399 | 44 |  | 19/8 |  | 26.11.25 | 26.11.25 | Done | Krishna Const.
400 | 45 |  | 23/5 |  | 26.11.25 | 26.11.25 | Done | Jai Bagrang Bali
401 | 1 |  | 34/6 |  | 03.12.25 | 03.12.25 | Done | Suraja Ram
402 | 2 |  | 23/1 |  | 03.12.25 | 03.12.25 | Done | Jai Bagrang Bali
403 | 3 |  | 23/2 |  | 03.12.25 | 03.12.25 | Done | Jai Bagrang Bali
404 | 4 |  | 23/3 |  | 04.12.25 | 04.12.25 | Done | Jai Bagrang Bali
405 | 5 |  | 23/7 |  | 05.12.25 | 05.12.25 | Done | Jai Bagrang Bali
406 | 6 |  | 28/0 |  | 05.12.25 | 05.12.25 | Done | Suraja Ram
407 | 7 |  | 23/8 |  | 07.12.25 | 07.12.25 | Done | Jai Bagrang Bali
408 | 8 |  | 27/3 |  | 07.12.25 | 07.12.25 | Done | Suraja Ram
409 | 9 |  | 27/2 |  | 08.12.25 | 08.12.25 | Done | Suraja Ram
410 | 10 |  | 26/6 |  | 08.12.25 | 08.12.25 | Done | Suraja Ram
411 | 11 |  | 23/9 |  | 08.12.25 | 08.12.25 | Done | Jai Bagrang Bali
412 | 12 |  | 26/3 |  | 10.12.25 | 10.12.25 | Done | Suraja Ram
413 | 13 |  | 26/4 |  | 11.12.25 | 11.12.25 | Done | Suraja Ram
414 | 14 |  | 25/0 |  | 14.12.25 | 14.12.25 | Done | Suraja Ram
415 | 15 |  | 26/5 |  | 15.12.25 | 15.12.25 | Done | Suraja Ram
416 | 16 |  | 30/0 |  | 15.12.25 | 15.12.25 | Done | Suraja Ram
417 | 17 |  | 30/3 |  | 15.12.25 | 15.12.25 | Done | Suraja Ram
418 | 18 |  | 27/1 |  | 17.12.25 | 17.12.25 | Done | Suraja Ram
419 | 19 |  | 27/0 |  | 18.12.25 | 18.12.25 | Done | Suraja Ram
420 | 20 |  | 23/6 |  | 18.12.25 | 18.12.25 | Done | Jai Bagrang Bali
421 | 21 |  | 23/11 |  | 19.12.25 | 19.12.25 | Done | Jai Bagrang Bali
422 | 22 |  | 26/7 |  | 19.12.25 | 19.12.25 | Done | Suraja Ram
423 | 23 |  | 26/2 |  | 19.12.25 | 19.12.25 | Done | Suraja Ram
424 | 24 |  | 26/1 |  | 20.12.25 | 20.12.25 | Done | Suraja Ram
425 | 25 |  | 23/10 |  | 20.12.25 | 20.12.25 | Done | Jai Bagrang Bali
426 | 26 |  | 23/0 |  | 22.12.25 | 22.12.25 | Done | Jai Bagrang Bali
427 | 27 |  | 22/0 |  | 22.12.25 | 22.12.25 | Done | Jai Bagrang Bali
428 | 28 |  | 21/13 |  | 22.12.25 | 22.12.25 | Done | Jai Bagrang Bali
429 | 29 |  | 21/14 |  | 22.12.25 | 22.12.25 | Done | Jai Bagrang Bali
430 | 30 |  | 22/5 |  | 22.12.25 | 22.12.25 | Done | Jai Bagrang Bali
431 | 31 |  | 3/0 |  | 31.12.25 | 01.01.26 | Done | Bajrangbali
432 | 32 |  | 4/0 |  | 30.12.25 | 31.12.25 | Done | Bajrangbali
433 | 33 |  | 5/0 |  | 01.12.25 | 02.12.25 | Done | Shiv Power
434 | 34 |  | 21/1 |  | 23.12.25 | 23.12.25 | Done | Jai Bagrang Bali
435 | 35 |  | 22/8 |  | 26.12.25 | 26.12.25 | Done | Jai Bagrang Bali
436 | 36 |  | 21/2 |  | 26.12.25 | 26.12.25 | Done | Jai Bagrang Bali
437 | 37 |  | 37/0 |  | 26.12.25 | 26.12.25 | Done | Suraja Ram
438 | 38 |  | 33/3 |  | 26.12.25 | 26.12.25 | Done | Suraja Ram
439 | 39 |  | 10/15 |  | 27.12.25 | 27.12.25 | Done | Jai Bagrang Bali
440 | 40 |  | 10/16 |  | 27.12.25 | 27.12.25 | Done | Jai Bagrang Bali
441 | 41 |  | 10/17 |  | 27.12.25 | 27.12.25 | Done | Jai Bagrang Bali
442 | 42 |  | 10/18 |  | 28.12.25 | 28.12.25 | Done | Jai Bagrang Bali
443 | 43 |  | 10/19 |  | 28.12.25 | 28.12.25 | Done | Jai Bagrang Bali
444 | 44 |  | 10/20 |  | 29.12.25 | 29.12.25 | Done | Jai Bagrang Bali
445 | 45 |  | 10/22 |  | 29.12.25 | 29.12.25 | Done | Jai Bagrang Bali
446 | 46 |  | 10/23 |  | 29.12.25 | 29.12.25 | Done | Jai Bagrang Bali
447 | 47 |  | 6/1 |  | 30.12.25 | 30.12.25 | Done | Jai Bagrang Bali
448 | 48 |  | 6/2 |  | 30.12.25 | 30.12.25 | Done | Jai Bagrang Bali
449 | 49 |  | 7/0 |  | 30.12.25 | 30.12.25 | Done | Jai Bagrang Bali
450 | 50 |  | 8/0 |  | 31.12.25 | 31.12.25 | Done | Jai Bagrang Bali
Jan'26
451 | 1 |  | 8/1 |  | 04.01.26 | 04.01.26 | Done | Jai Bagrang Bali
452 | 2 |  | 8/2 |  | 04.01.26 | 04.01.26 | Done | Jai Bagrang Bali
453 | 3 |  | 8/4 |  | 04.01.26 | 04.01.26 | Done | Jai Bagrang Bali
454 | 4 |  | 6/0 |  | 07.01.26 | 07.01.26 | Done | Jai Bagrang Bali
455 | 5 |  | 21/12 |  | 16.01.26 | 16.01.25 | Done | Shraddha Cop
456 | 6 |  | 18/0 |  | 17.01.26 | 17.01.26 | Done | Shiv Power
457 | 7 |  | 17/2 |  | 18.01.25 | 19.01.26 | Done | Shiv Power
458 | 8 |  | 19/13 |  | 20.01.26 | 20.01.26 | Done | Shiv Power
459 | 9 |  | 19/6 |  | 19.01.26 | 20.01.26 | Done | Balaji
460 | 10 |  | 19/7 |  | 20.01.26 | 20.01.26 | Done | Balaji
461 | 11 |  | 11/0 |  |  |  | Done
462 | 12 |  | 11/1 |  |  |  | Done
463 | 13 |  | 11/2 |  |  |  | Done
464 | 15 |  | 13/1 |  |  |  | Done
465 | 16 |  | 13/2 |  |  |  | Done
466 | 17 |  | 13/3 |  |  |  | Done
467 | 18 |  | 13/4 |  |  |  | Done
468 | 19 |  | 15/5 |  |  |  | Done
469 | 20 |  | 17/0 |  |  |  | Done
470 | 21 |  | 19/4 |  |  |  | Done
471 | 22 |  | 19/5 |  |  |  | Done
472 | 23 |  | 19/12 |  |  |  | Done
473 | 24 |  | 21/4 |  | 20.01.26 | 21.01.26 | Done | Shraddha Cop
474 | 25 |  | 18/3 |  | 21.01.26 | 22.01.26 | Done | Balaji
475 | 26 |  | 21/0 |  | 22.01.26 | 22.01.26 | Done | Shiv Power
476 | 27 |  | 21/5 |  | 27.01.26 | 27.01.26 | Done | Balaji
477 | 28 |  | 8/3 |  | 31.01.26 | 31.01.26 | Done | Bajrangbali
478 | 29 |  | 8/5 |  | 04.01.26 | 04.01.26 | Done | Bajrangbali
479 | 30 |  | 21/9 |  | 26.01.26 | 26.01.26 | Done | Shraddha Cop
480 | 31 |  | 21/3 |  | 27.01.26 | 28.01.26 | Done | Shraddha Cop
481 | 32 |  | 11/11 |  | 27.01.26 | 27.01.26 | Done | Shiv Power
482 | 33 |  | 11/14 |  | 24.01.26 | 25.01.26 | Done | Shiv Power
483 | 34 |  | 11/10 |  | 27.01.26 | 28.01.26 | Done | Shiv Power
484 | 35 |  | 21/6 |  | 29.01.26 | 29.01.26 | Done | Shree Balaji
485 | 36 |  | 11/6 |  | 29.01.26 | 30.01.26 | Done | Balaji
486 | 37 |  | 17/3 |  | 19.01.26 | 19.01.26 | Done | Shiv Power
487 | 38 |  | 12/0 |  | 29.01.26 | 29.01.26 | Done | Shiv Power
Feb'26
488 | 1 |  | 21/10 |  | 03.02.26 | 03.02.26 | Done | Shraddha Cop
489 | 2 |  | 8/10 |  | 03.02.26 | 04.02.26 | Done | Bajrangbali
490 | 3 |  | 10/11 |  | 03.02.26 | 04.02.26 | Done | Shiv Power
491 | 4 |  | 14/0 |  | 07.02.26 | 09.02.26 | Done | Shiv Power
492 | 5 |  | 19/11 |  | 08.02.26 | 09.02.26 | Done | Shiv Power
493 | 6 |  | 19/1 |  | 09.02.26 | 09.02.26 | Done | Shiv Power
494 | 7 |  | 14/2 |  | 09.02.26 | 10.02.26 | Done | Shiv Power
495 | 8 |  | 14/3 |  | 11.02.26 | 11.02.26 | Done | Bhawar lal
496 | 9 |  | 14/6 |  | 12.02.26 | 12.02.26 | Done | Bhawar lal
497 | 10 |  | 14/4 |  | 13.02.26 | 13.02.26 | Done | Shiv Power
498 | 11 |  | 11/9 |  | 16.02.26 | 17.02.26 | Done | Shiv Power
499 | 12 |  | 21/8 |  | 10.02.26 | 10.02.26 | Done | Shraddha Cop
500 | 13 |  | 21/11 |  | 09.02.26 | 09.02.26 | Done | Shraddha Cop
501 | 14 |  | 10/1 |  | 23.02.26 | 23.02.26 | Done | Bajrangbali
502 | 15 |  | 10/2 |  | 24.02.26 | 24.02.6 | Done | Bajrangbali
503 | 16 |  | 10/5 |  | 27.02.26 | 27.02.26 | Done | Bajrangbali
504 | 17 |  | 8/6 |  | 18.02.26 | 19.02.26 | Done | Bajrangbali
505 | 18 |  | 8/8 |  | 27.02.26 | 27.02.26 | Done | Bajrangbali
506 | 19 |  | 18/5 |  | 26.02.26 | 26.02.26 | Done | Shiv Power
507 | 20 |  | 20/0 |  | 28.02.26 | 28.02.26 | Done | Shiv Power
Mar'26
508 | 1 |  | 8/11 |  | 02.03.26 | 02.03.26 | Done | Bajrangbali
509 | 2 |  | 8/12 |  | 03.03.26 | 03.03.26 | Done | Bajrangbali

## Stringing - PKG-G
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
STRINGING- PKG-G
S. No | Section |  |  | Paying Out |  |  | Final Sag |  |  | Name of Gang | Remarks
| From | To | Length | Start Date | Finish Date | Month | Start Date | Finish Date | Month
1 | 57/6 | 58/0 | 3.141 | 06.05.2024 | 10.05.24 | 2024-05-24 | 19.05.24 | 24.05.24 | 2024-05-24 | GPJ Const. | Final sag done |  |  |  | 57/6 to 58/0
2 | 57/0 | 57/6 | 2.344 | 16.05.24 | 24.05.24 | 2024-05-24 | 07.06.24 | 12.06.24 | 2024-06-24 | GPJ Const. | Final sag done |  |  |  | 57/0 to 57/6
3 | 56/0 | 57/0 | 4.127 | 04.06.24 | 12.06.24 | 2024-06-24 | 28.06.24 | 04.07.24 | 2024-07-24 | GPJ Const. | Final sag done |  |  |  | 56/0 to 57/0
4 | 55/0 | 56/0 | 4.9 | 25.06.24 | 04.07.24 | 2024-07-24 | 17.07.24 | 22.07.24 | 2024-07-24 | GPJ Const. | 10.883 |  |  |  | 55/0 to 56/0
5 | 53/0 | 55/0 | 2.013 | 16.07.24 | 22.07.24 | 2024-07-24 | 09.08.24 | 10.08.24 | 2024-08-24 | GPJ Const. | 11.112 |  |  |  | 53/0 to 55/0
6 | 52/0 | 53/0 | 2.364 | 19.08.24 | 22.08.24 | 2024-08-24 | 04.09.24 | 09.09.24 | 2024-09-24 | GPJ Const. | Final sag done |  |  |  | 52/0 to 53/0
7 | 51/0 | 52/0 | 4.403 | 01.09.24 | 08.09.24 | 2024-09-24 | 28.09.24 | 05.10.24 | 2024-10-24 | GPJ Const. | Final sag done |  |  |  | 51/0 to 52/0
8 | 50/0 | 51/0 | 1.971 | 26.9.24 | 02.10.24 | 2024-10-24 | 08.10.24 | 10.10.24 | 2024-10-24 | GPJ Const. | Final sag done |  |  |  | 50/0 to 51/0
9 | 72/7 | 73/0 | 0.49623 | 12.11.24 | 15.11.24 | 2024-11-24 | 27.11.24 | 29.11.24 | 2024-11-24 | MR Power | Final sag done |  |  |  | 72/7 to 73/0
10 | 58/0 | 58/7 | 2.797 | 20.11.24 | 23.11.24 | 2024-11-24 | 01.12.245 | 05.12.24 | 2024-12-24 | Kddus Ali | Final sag done |  |  |  | 58/0 to 58/7
11 | 72/0 | 72/7 | 2.589 | 18.11.24 | 23.11.24 | 2024-11-24 | 06.12.24 | 10.12.24 | 2024-12-24 | MR Power | Final sag done |  |  |  | 72/0 to 72/7
12 | 67/1 | 68/0 | 0.42647 | 22.12.24 | 23.12.24 | 2024-12-24 | 23.12.24 | 25.12.25 | 2024-12-24 | Nasruddin | Final sag done |  |  |  | 67/1 to 68/0
13 | 68/0 | 69/0 | 2.855 | 11.12.24 | 20.12.24 | 2024-12-24 | 01.01.25 | 05.01.25 | 2025-01-25 | Nasruddin | Final sag done |  |  |  | 68/0 to 69/0
14 | 58/7 | 59/0 | 3.885 | 27.12.24 | 04.01.25 | 2025-01-25 | 07.01.25 | 09.01.25 | 2025-01-25 | MR Power | Final sag done |  |  |  | 58/7 to 59/0
15 | 71/0 | 72/0 | 2.092 | 03.12.24 | 10.12.24 | 2024-12-24 | 16.01.25 | 19.01.25 | 2025-01-25 | MR Power | Final sag done |  |  | 45 | 71/0 to 72/0
16 | 67/0 | 67/1 | 0.43755 | 21.12.24 | 22.12.24 | 2024-12-24 | 20.01.25 | 21.01.25 | 2025-01-25 | Nasruddin | Final sag done |  |  |  | 67/0 to 67/1
17 | 69/0 | 70/0 | 3.881 | 30.12.24 | 05.01.25 | 2025-01-25 | 27.01.25 | 28.01.25 | 2025-01-25 | Nasruddin | Final sag done |  |  |  | 69/0 to 70/0
18 | 41/0 | 42/0 | 4.981 | 13.02.25 | 20.02.25 | 2025-02-25 | 28.02.25 | 02.03.25 | 2025-03-25 | Nasruddin | Final sag done | 41/0 hoisting done |  |  | 41/0 to 42/0
19 | 59/0 | 60/0 | 2.581 | 20.01.25 | 25.01.25 | 2025-01-25 | 02.05.25 | 04.05.25 | 2025-05-25 | MR Power | Final sag done | Acchelal |  |  | 59/0 to 60/0
20 | 42/0 | 43/0 | 0.489 | 04.05.25 | 11.05.25 | 2025-05-25 | 07.05.25 | 11.05.25 | 2025-05-25 | Indrajeet | Final sag done |  |  |  | 42/0 to 43/0
21 | 49/0 | 50/0 | 0.241 | 15.05.25 | 17.05.25 | 2025-05-25 | 15.05.25 | 17.05.25 | 2025-05-25 | Indrajeet | Final sag done | 47/3 Half side hoisting done |  |  | 49/0 to 50/0
22 | 48/0 | 49/0 | 1.162 | 14.05.25 | 17.05.25 | 2025-05-25 | 19.05.25 | 21.05.25 | 2025-05-25 | Indrajeet | Final sag done |  |  |  | 48/0 to 49/0
23 | 47/0 | 48/0 | 1.274 | 19.05.25 | 21.05.25 | 2025-05-25 | 25.05.25 | 29.05.25 | 2025-05-25 | Indrajeet | Final sag done |  |  |  | 47/0 to 48/0
24 | 37/2 | 38/0 | 2.711 | 24.05.25 | 30.05.25 | 2025-05-25 | 11.06.25 | 15.06.25 | 2025-06-25 | Indrajeet | Final sag done |  |  |  | 37/2 to 38/0
25 | 43/0 | 44/0 | 2.856 | 05.05.25 | 10.05.25 | 2025-05-25 | 20.06.25 | 25.06.25 | 2025-06-25 | Indrajeet | Final sag done | Jainath |  |  | 43/0 to 44/0
26 | 61/0 | 62/0 | 1.028 | 27.06.25 | 29.6.25 | 2025-06-25 | 07.07.25 | 10.07.25 | Jul | GPJ Const. | Final sag done | Clipping 61/0 to 62/0 done |  | 62/0 jumper done | 61/0 to 62/0
27 | 62/0 | 63/0 | 0.221 | 07.07.25 | 10.07.25 | Jul | 07.07.25 | 10.07.25 | Jul | GPJ Const. | Final sag done | Clipping 62/0 to 63/0 done |  |  | 62/0 to 63/0
28 | 38/0 | 38/9 | 3.215 | 04.06.25 | 10.06.25 | 2025-06-25 | 07.07.25 | 13.7.25 | Jul | Indrajeet | Final sag done | 38/1 Clipping |  |  | 38/0 to 38/9
29 | 40/10 | 41/0 | 1.073 | 02.07.25 | 05.07.25 | Jul | 24.07.25 | 28.07.25 | Jul | Indrajeet/Rahim | Final sag done |  |  |  | 40/10 to 41/0
30 | 63/0 | 64/0 | 2.879 | 24.07.25 | 28.07.25 | Jul | 31.07.25 | 02.08.25 | Aug | GPJ Const. | Final sag done |  |  |  | 63/0 to 64/0
31 | 39/0 | 40/0 | 2.744 | 30.07.25 | 06.08.25 | Aug | 09.08.25 | 12.08.25 | Aug | Amir Sheikh | Final sag done | 39/1,39/2.39/4,5,6 Clipping done | 39/0 Jumper |  | 39/0 to 40/0
32 | 40/5 | 40/10 | 1.897 | 11.07.25 | 20.07.25 | Jul | 10.08.25 | 16.08.25 | Aug | Indrajeet/Rahim | Final sag done | 48 |  |  | 40/5 to 40/10
33 | 38/9 | 39/0 | 0.544 | 04.07.25 | 11.07.25 | Jul | 19.08.25 | 23.08.25 | Aug | Indrajeet/Mohan/Amir Sheikh | Final sag done | 50 |  |  | 38/9 to 39/0
34 | 40/0 | 40/2 | 0.652 | 28.07.25 | 01.08.25 | Aug | 23.08.25 | 31.08.25 | Aug | Rahim Khan | Final sag done |  |  |  | 40/0 to 40/2
35 | 40/2 | 40/5 | 1.219 | 08.08.25 | 14.08.25 | Aug | 23.08.25 | 31.08.25 | Aug | Rahim Khan | Final sag done |  |  |  | 40/2 to 40/5
36 | 66/0 | 67/0 | 2.028 | 04.09.25 | 10.09.25 | 2025-09-25 | 13.09.25 | 16.09.25 | sept | MC Const. | Final sag done |  | 50 |  | 66/0 to 67/0
37 | 35/0 | 36/0 | 3.6026 | 07.09.25 | 14.09.25 | 2025-09-25 | 18.09.25 | 23.09.25 | sept | Amir Sheikh | Final sag done |  |  |  | 35/0 to 36/0
38 | 46/0 | 47/0 | 1.728 | 22.06.25 | 27.06.25 | 2025-06-25 | 04.10.25 | 09.10.25 | 2025-10-25 | Indrajeet | Final sag done |  |  |  | 46/0 to 47/0
39 | 31/0 | 32/0 | 1.678 | 18.09.25 | 24.09.25 | 2025-09-25 | 07.10.25 | 14.10.25 | 2025-10-25 | Krishna Const. | Final sag done |  | 31/1,2 , 33/2,5,6,7 Hoisting done |  | 31/0 to 32/0
40 | 44/0 | 45/0 | 2.459 | 13.06.25 | 18.06.25 | 2025-06-25 | 12.10.25 | 17.10.25 | 2025-10-25 | Indrajeet | Final sag done |  |  |  | 44/0 to 45/0
41 | Gantry | 1/0 | 0.12293 | 08.10.25 | 17.10.25 | 2025-10-25 | 09.10.25 | 17.10.25 | 2025-10-25 | Devi Power | Final sag done |  |  |  | Gantry to 1/0
42 | 65/0 | 66/0 | 2.966 | 04.10.25 | 06.10.25 | 2025-10-25 | 13.10.25 | 18.10.25 | 2025-10-25 | MC Const. | Final sag done | 25 |  |  | 65/0 to 66/0
43 | 1/0 | 1A/0 | 0.1 | 04.10.25 | 06.10.25 | 2025-10-25 | 12.10.25 | 21.10.25 | 2025-10-25 | Devi Power | Final sag done |  |  |  | 1/0 to 1A/0
44 | 1A/0 | 2/0 | 3.187 | 10.10.25 | 17.10.25 | 2025-10-25 | 23.10.25 | 25.10.25 | 2025-10-25 | Devi Power | Final sag done | 33 |  |  | 1A/0 to 2/0
45 | 64/0 | 65/0 | 4.079 | 10.10.25 | 18.10.25 | 2025-10-25 | 23.10.25 | 26.10.25 | 2025-10-25 | MC Const. | Final sag done | 55 | 64/9 Done |  | 64/0 to 65/0
46 | 32/0 | 33/0 | 3.747 | 04.10.25 | 13.10.25 | 2025-10-25 | 23.10.25 | 29.10.25 | 2025-10-25 | Krishna Const. | Final sag done | 75 | 32/3,32/5 done Clipping 33/0 & 34/0 Hoisting done |  | 32/0 to 33/0
47 | 33/0 | 34/0 | 3.338 | 21.10.25 | 27.10.25 | 2025-10-25 | 23.10.25 | 29.10.25 | 2025-10-25 | Krishna Const. | Final sag done |  | 34/2 , 34/3 34/4 Hoisting done &33/1 & 33/5 Clipping done |  | 33/0 to 34/0
48 | 36/0 | 37/0 | 0.214 | 30.10.25 | 08.11.25 | 2025-11-25 | 30.10.25 | 08.11.25 | 2025-11-25 | Telegance Power | Final sag done |  |  | 65 | 36/0 to 37/0
49 | 60/0 | 61/0 | 0.206 | 10.11.25 | 11.11.25 | 2025-11-25 | 10.11.25 | 11.11.25 | 2025-11-25 | Indrajeet | Final sag done |  |  |  | 60/0 to 61/0
50 | 34/0 | 34/5 | 2.056 | 01.01.25 | 06.11.25 | 2025-11-25 | 14.11.25 | 18.11.25 | 2025-11-25 | Krishna Const. | Final sag done |  |  | 75 | 34/0 to 34/5
51 | 34/5 | 35/0 | 0.705 | 10.11.25 | 13.11.25 | 2025-11-25 | 14.11.25 | 19.11.25 | 2025-11-25 | Krishna Const. | Final sag done |  | 34/6 Clipping done |  | 34/5 to 35/0
52 | 45/0 | 46/0 | 0.233 | 14.11.25 | 26.11.25 | 2025-11-25 | 14.11.25 | 26.11.25 | 2025-11-25 | Gopal Ji | Final sag done |  |  |  | 45/0 to 46/0
53 | 37/0 | 37/1 | 0.317 | 29.11.25 | 30.11.25 | 2025-11-25 | 29.11.25 | 30.11.25 | 2025-11-25 | Indrajeet | Final sag done | Complete |  | 15 | 37/0 to 37/1
54 | 37/1 | 37/2 | 0.468 | 29.11.25 | 30.11.25 | 2025-11-25 | 29.11.25 | 30.11.25 | 2025-11-25 | Indrajeet | Final sag done | Complete |  | 30 | 37/1 to 37/2
55 | 25/0 | 26/0 | 4.965 | 13.11.25 | 24.11.25 | 2025-11-25 | 29.11.25 | 30.11.25 | 2025-11-25 | Krishna Const. -2 | Final sag done | FS done 12.8.25 | Dhananjay | 50 | 25/0 to 26/0
56 | 2/0 | 3/0 | 3.818 | 30.10.25 | 05.11.25 | 2025-11-25 | 30.11.25 | 30.11.25 | 2025-11-25 | Devi Power | Final sag done | FS done 25.12.25 | 2/9 Clipping done |  | 2/0 to 3/0
57 | 30/0 | 31/0 | 1.325 | 19.11.25 | 24.11.25 | 2025-11-25 | 30.11.25 | 30.11.25 | 2025-11-25 | Krishna Const. | Final sag done | FS done 12.8.25 |  | 83 | 30/0 to 31/0
58 | 5/0 | 6/0 | 0.237 | 05.12.25 | 11.12.25 | 2025-12-25 | 05.12.25 | 11.12.25 | 2025-12-25 | Kunal Kumar | Final sag done |  |  |  | 5/0 to 6/0
59 | 4/0 | 5/0 | 1.867 | 05.12.25 | 08.12.25 | 2025-12-25 | 09.12.25 | 12.12.25 | 2025-12-25 | Devi Power | Final sag done |  |  |  | 4/0 to 5/0
60 | 15/0 | 16/0 | 4.141 | 03.12.25 | 10.12.25 | 2025-12-25 | 11.12.25 | 13.12.25 | 2025-12-25 | Nasir | Final sag done | 20 |  | 20 | 15/0 to 16/0
61 | 29/0 | 30/0 | 4.45 | 01.12.25 | 08.12.25 | 2025-12-25 | 11.12.25 | 15.12.25 | 2025-12-25 | Krishna Const. | Final sag done | Clipping done |  |  | 29/0 to 30/0
62 | 16/0 | 17/0 | 2.818 | 14.12.25 | 17.12.25 | 2025-12-25 | 20.12.25 | 21.12.25 | 2025-12-25 | Nasir | Final sag done | 16/5 Clipping done |  |  | 16/0 to 17/0
63 | 24/0 | 25/0 | 2.69 | 01.12.25 | 08.12.25 | 2025-12-25 | 13.12.25 | 23.12.25 | 2025-12-25 | Krishna Const. -2 | Final sag done |  |  |  | 24/0 to 25/0 | 24/0 hoisting done
64 | 28/0 | 29/0 | 3.914 | 15.12.25 | 21.12.25 | 2025-12-25 | 23.12.25 | 28.12.25 | 2025-12-25 | Krishna Const. | Final sag done |  |  | 80 | 28/0 to 29/0
65 | 23/0 | 24/0 | 4.809 | 12.12.25 | 22.12.25 | 2025-12-25 | 25.12.25 | 28.12.25 | 2025-12-25 | Krishna Const. -2 | Final sag done |  |  | 95 | 23/0 to 24/0
66 | 3/0 | 4/0 | 0.227 | 23.12.25 | 27.12.25 | 2025-12-25 | 23.12.25 | 27.12.25 | 2025-12-25 | Gopal Ji | Final sag done |  |  | 23 | 3/0 to 4/0
67 | 6/0 | 7/0 | 1.175 | 17.12.25 | 18.12.25 | 2025-12-25 | 28.12.25 | 31.12.25 | 2025-12-25 | Devi Power | Final sag done |  |  | 56 | 6/0 to 7/0
68 | 27/1 | 28/0 | 1.752 | 24.12.25 | 28.12.25 | 2025-12-25 | 31.12.25 | 31.12.25 | 2025-12-25 | Krishna Const. | Final sag done |  |  |  | 27/1 to 28/0
69 | 14/0 | 15/0 | 2.624 | 27.12.25 | 31.12.25 | 2025-12-25 | 04.01.26 | 06.01.26 | 2026-01-26 | Nasir | Final sag done |  |  | 46 | 14/0 to 15/0
70 | 10/12 | 10/20 | 3.208 | 29.12.25 | 31.12.25 | 2025-12-25 | 25.01.26 | 29.01.26 | 2026-01-26 | Deepak | Final sag done | 10/23/ hoistin done |  | 40 | 10/12 to 10/20
71 | 9/0 | 10/0 | 0.234 | 03.01.26 | 06.01.26 | 2026-01-26 | 03.01.26 | 06.01.26 | 2026-01-26 | Gopal Ji | Final sag done
72 | 27/0 | 27/1 | 0.372 | 31.12.25 | 05.01.26 | 2026-01-26 | 05.01.26 | 09.01.26 | 2026-01-26 | Krishna Const. | Final sag done
73 | 13/0 | 14/0 | 1.9285 | 02.01.26 | 05.01.25 | 2026-01-26 | 07.01.26 | 09.01.26 | 2026-01-26 | Nasir | Final sag done |  |  |  | 13/0 to 14/0
74 | 26/0 | 27/0 | 3.1451 | 02.01.26 | 09.01.26 | 2026-01-26 | 11.01.26 | 16.01.26 | 2026-01-26 | Krishna Const. | Final sag done
75 | 17/0 | 18/0 | 2.5075 | 11.01.26 | 14.01.26 | 2026-01-26 | 13.01.26 | 15.01.26 | 2026-01-26 | Nasir | Final sag done |  |  |  | 17/0 to 18/0
76 | 22/0 | 23/0 | 4.035 | 06.01.26 | 16.01.26 | 2026-01-26 | 11.01.26 | 17.01.26 | 2026-01-26 | Krishna Const. -2 | Final sag done
77 | 12/0 | 13/0 | 0.217 | 19.01.26 | 28.01.26 | 2026-01-26 | 19.01.26 | 28.01.26 | 2026-01-26 | Gopal Ji | Final sag done
78 | 10/20 | 11/0 | 1.653 | 24.01.26 | 31.01.26 | 2026-01-26 | 25.01.26 | 31.01.26 | 2026-01-26 | Deepak/Devi Power | Final sag done
79 | 19/12 | 20/0 | 1.2 | 29.01.26 | 31.01.26 | 2026-01-26 | 03.01.26 | 07.02.26 | 2026-02-26 | Nasir | Final sag done
80 | 70/0 | 71/0 | 0.258 | 02.02.26 | 07.02.26 | 2026-02-26 | 02.02.26 | 07.02.26 | 2026-02-26 | MC Const./Indrajeet | Final sag done |  |  |  | 70/0 to 71/0
81 | 20/0 | 21/0 | 0.273 | 29.01.26 | 07.02.26 | 2026-02-26 | 29.01.26 | 07.02.26 | 2026-02-26 | Gopal Ji | Final sag done
82 | 7/0 | 8/0 | 0.261 | 11.02.26 | 16.02.26 | 2026-02-26 | 11.02.26 | 16.02.26 | 2026-02-26 | Gopal ji | Final sag done
83 | 11/10 | 12/0 | 2.2798 | 18.01.26 | 21.01.26 | 2026-01-26 | 09.02.26 | 17.02.26 | 2026-02-26 | Devi Power | Final sag done
84 | 11/0 | 11/10 | 4.11 | 09.02.26 | 17.02.26 | 2026-02-26 | 11.02.26 | 17.02.26 | 2026-02-26 | Devi Power | Final sag done
85 | 21/0 | 21/7 | 2.873 | 31.01.26 | 07.02.26 | 2026-02-26 | 11.02.26 | 18.02.26 | 2026-02-26 | Krishna Const. -2 | Final sag done
86 | 19/8 | 19/12 | 1.6785 | 29.01.26 | 31.01.26 | 2026-01-26 | 19.02.26 | 22.02.26 | 2026-02-26 | Nasir | Final sag done
87 | 19/0 | 19/8 | 3.338 | 13.02.26 | 22.02.26 | 2026-02-26 | 22.02.26 | 24.02.26 | 2026-02-26 | Nasir | Final sag done
88 | 10/0 | 10/12 | 4.995 | 19.02.26 | 23.02.26 | 2026-02-26 | 20.02.26 | 24.02.26 | 2026-02-26 | Deepak | Final sag done
89 | 8/7 | 9/0 | 2.441 | 21.02.26 | 24.02.26 | 2026-02-26 | 26.02.26 | 02.03.26 | 2026-03-26 | Devi Power | Final sag done
90 | 8/0 | 8/7 | 2.8765 | 25.02.26 | 02.03.26 | 2026-03-26 | 26.02.26 | 02.03.26 | 2026-03-26 | Devi Power | Final sag done
91 | 21/7 | 22/0 | 3.172 | 09.03.26 | 14.03.26 | 2026-03-26 | 12.03.26 | 16.03.26 | 2026-03-26 | Krishna Const. -2 | Final sag done | 10.02.26-08.03.26 Row
92 | 18/0 | 19/0 | 4.543 | 14.03.26 |  | 2026-03-26 | 16.03.26 |  | 2026-03-26 | Nasir | Top Final Sag Phase & 3rd Phase Payout

## OPGW PKG-G
EXECUTING AGENCY : M/s. KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
OPGW Progress details(Pkg-G)
Sr. No | Section |  | Section length in Kms | OPGW Drum Length (In KMs) | Start date | End date | Splicing | Jointing Details | Agency | OTDR reading status | Splicing done by | Remarks
1 | 51/0 | 52/0 | 4.403 | 4.653 | 11.01.25 | 12.01.25 | Done |  | Congent tech |  |  | Final sag completed | 51/0 to 52/0
2 | 52/0 | 55/0 | 4.377 | 4.627 | 17.01.25 | 18.01.25 | Done |  | Congent tech |  |  | Final sag completed | 52/0 to 55/0
3 | 55/0 | 56/0 | 4.9 | 5.16 | 20.01.25 | 21.01.25 | Done |  | Congent tech |  | Rakesh | Final sag completed | 55/0 to 56/0
4 | 56/0 | 57/0 | 4.127 | 4.372 | 23.01.25 | 24.01.25 | Done |  | Congent tech |  | Rakesh | Final sag completed | 56/0 to 57/0
5 | 57/0 | 57/6 | 2.344 | 2.553 | 27.01.25 | 28.01.25 | Done |  | Congent tech |  | Rakesh | Final sag completed | 57/0 to 57/6
6 | 57/6 | 58/0 | 3.141 | 3.365 | 29.01.25 | 30.01.25 | Done |  | Congent tech |  | Rakesh | Final sag completed | 57/6 to 58/0
7 | 58/0 | 58/7 | 2.797 | 3.015 | 01.02.25 | 02.02.25 | Done |  | Congent tech |  | Rakesh | Final sag completed | 58/0 to 58/7
8 | 58/7 | 59/0 | 3.885 | 4.124 | 04.02.25 | 05.02.25 | Done |  | Congent tech |  | Rakesh | Final sag completed | 58/7 to 59/0
9 | 41/0 | 42/0 | 4.98 | 5.242 | 27.07.25 | 29.07.25 | Done |  | Congent tech |  | Rakesh | Final sag completed | 41/0 to 42/0
10 | 42/0 | 44/0 | 3.345 | 3.574 | 06.08.25 | 06.08.25 | Done |  | Congent tech |  | Rakesh | Final sag completed | 42/0 to 44/0
11 | 48/0 | 51/0 | 3.374 | 3.603 | 10.08.25 | 10.08.25 | Done |  | Congent tech |  | Rakesh | Final sag completed | 48/0 to 51/0
12 | 39/0 | 40/2 | 3.395 | 3.603 | 12.08.25 | 13.08.25 | Done |  | Congent tech |  | Rakesh | Final sag completed | 39/0 to 40/2
13 | 38/0 | 39/0 | 3.759 | 4.006 | 18.08.25 | 18.08.25 | Done |  | Congent tech |  | Rakesh | Final sag completed | 38/0 to 39/0
14 | 63/0 | 64/0 | 2.879 | 2.879 | 27.11.25 | 30.11.25 | Done |  | Congent tech |  | Umesh | Final sag completed | 63/0 to 64/0
15 | 64/0 | 65/0 | 4.079 | 4.322 | 01.12.25 | 03.12.25 | Done |  | Congent tech |  | Umesh | Final sag completed | 64/0 to 65/0
16 | 65/0 | 67/0 | 4.994 | 5.266 | 07.12.25 | 08.12.26 | Done |  | Congent tech |  | Umesh | Final sag completed | 65/0 to 67/0
17 | 67/0 | 69/0 | 3.719 | 3.965 | 10.12.25 | 10.12.25 | Done |  | Congent tech |  | Umesh | Final sag completed | 67/0 to 69/0
18 | 69/0 | 70/0 | 3.881 | 4.131 | 12.12.25 | 13.12.25 | Done |  | Congent tech |  | Umesh | Final sag completed | 69/0 to 70/0
19 | 72/0 | 73/0 | 3.085 | 3.319 | 15.12.25 | 16.12.25 | Done |  | Congent tech |  | Umesh | Final sag completed | 72/0 to 73/0
20 | 30/0 | 32/0 | 3.003 | 3.235 | 27.12.25 | 28.12.25 | Done |  | Congent tech |  | Kamla Prasad | Final sag completed | 30/0 to 32/0
21 | 59/0 | 63/0 | 4.036 | 4.288 | 28.12.25 | 30.12.25 | Done |  | Congent tech |  | Umesh | Final sag completed | 59/0 to 63/0
22 | 32/0 | 33/0 | 3.746 | 3.984 | 30.12.25 | 31.12.25 | Done |  | Congent tech |  | Kamla Prasad | Final sag completed | 32/0 to 33/0
23 | 29/0 | 30/0 | 4.45 | 4.701 | 2.01.26 | 03.01.26 | Done |  | Congent tech |  | Kamla Prasad | Final sag completed | 29/0 to 30/0
24 | 28/0 | 29/0 | 3.914 | 4.156 | 05.01.26 | 06.01.26 | Done |  | Congent tech |  | Kamla Prasad | Final sag completed | 28/0 to 29/0
25 | 27/0 | 28/0 | 2.124 | 2.339 | 07.01.26 | 08.01.26 | Done |  | Congent tech |  | Balwan | Final sag completed | 27/0 to 28/0
26 | 44/0 | 46/0 | 2.692 | 2.941 | 08.01.26 | 09.01.26 | Done |  | Congent tech |  | Umesh | Final sag completed | 44/0 to 46/0
27 | 26/0 | 27/0 | 3.1451 | 3.38 | 09.01.26 | 11.01.26 | Done |  | Congent tech |  | Balwan | Final sag completed | 26/0 to 27/0
28 | 46/0 | 48/0 | 3.002 |  | 10.01.26 | 11.01.26 | Done |  | Congent tech |  | Umesh | Final sag completed
29 | 25/0 | 26/0 | 4.965 |  | 12.01.26 | 15.01.26 | Done |  | Congent tech |  | Balwan | Final sag completed
30 | 40/2 | 41/0 | 4.188 |  | 12.01.26 | 14.01.26 | Done |  | Congent tech |  | Umesh | Final sag completed
31 | 33/0 | 34/0 | 3.338 |  | 15.01.26 | 18.01.26 | Done |  | Congent tech |  | Umesh | Final sag completed
32 | 37/0 | 38/0 | 3.497 |  | 15.01.26 | 16.01.26 | Done |  | Congent tech |  | Umesh | Final sag completed
33 | 34/0 | 35/0 | 2.761 |  | 19.01.26 | 21.01.26 | Done |  | Congent tech |  | Umesh | Final sag completed
34 | 35/0 | 37/0 | 3.816 |  | 17.01.26 | 20.01.26 | Done |  | Congent tech |  | Umesh | Final sag completed
35 | 17/0 | 18/0 | 2.507 |  | 19.01.26 | 24.01.26 | Done |  | Congent tech |  |  | Final sag completed
36 | 24/0 | 25/0 | 2.69 |  | 21.01.26 | 24.01.26 | Done |  | Congent tech |  |  | Final sag completed
37 | 16/0 | 17/0 | 2.818 |  | 25.01.26 | 28.01.26 | Done |  | Congent tech |  |  | Final sag completed
38 | 23/0 | 24/0 | 4.809 |  | 25.01.26 | 29.01.26 | Done |  | Congent tech |  |  | Final sag completed
39 | Gantry | 2/0 | 3.41 |  | 22.01.26 | 29.01.26 |  |  | Jai Bajrang Bali |  |  | Final sag completed
40 | 22/0 | 23/0 | 4.035 |  | 29.01.26 | 31.01.26 | Done |  | Congent tech |  |  | Final sag completed
41 | 19/9 | 21/0 | 2.744 |  | 30.01.26 | 02.02.26 | Done |  | Congent tech |  |  | Final sag completed
42 | 2/0 | 2/9 | 3.408 |  | 29.01.26 | 09.02.26 | Done |  | Jai Bajrang Bali |  |  | Final sag completed
43 | 10/12 | 11/0 | 4.861 |  | 03.02.26 | 05.02.26 | Done |  | Congent tech |  |  | Final sag completed
44 | 70/0 | 72/0 | 2.35 |  | 09.02.26 | 10.02.26 | Done |  | Congent tech |  |  | Final sag completed
45 | 14/0 | 15/0 | 2.624 |  | 11.02.26 | 13.02.26 | Done |  | Congent tech |  |  | Final sag completed
46 | 21/0 | 21/7 | 2.873 |  | 11.02.26 | 13.02.26 | Done |  | Congent tech |  |  | Final sag completed
47 | 21/7 | 22/0 | 3.172 |  | 13.02.26 | 15.02.26 | Done |  | Congent tech |  |  | Final sag completed
48 | 4/0 | 8/0 | 3.54 |  | 09.02.26 | 17.02.26 | Done |  | Jai Bajrang Bali |  |  | Final sag completed
49 | 11/0 | 11/10 | 4.11 |  | 17.02.26 | 19.02.26 | Done |  | Congent tech |  |  | Final sag completed
50 | 11/10 | 13/4 | 4.075 |  | 18.02.26 | 20.02.26 | Done |  | Congent tech |  |  | Final sag completed
51 | 13/4 | 14/0 | 0.35 |  | 18.02.26 | 20.02.26 | Done |  | Congent tech |  |  | Final sag completed
52 | 19/0 | 19/9 | 3.747 |  | 21.02.26 | 24.02.26 | Done |  | Congent tech |  |  | Final sag completed
53 | 10/0 | 10/12 | 4.995 |  | 25.02.26 | 26.02.26 | Done |  | Congent tech |  |  | Final sag completed
54 | 15/0 | 16/0 | 4.141 |  | 26.02.26 | 28.02.26 | Done |  | Congent tech |  |  | Final sag completed
55 | 8/0 | 8/7 | 2.8765 |  | 02.03.26 | 06.03.26 | Done |  | Congent tech |  |  | Final sag completed
56 | 8/7 | 10/0 | 2.675 |  | 02.03.26 | 06.03.26 | Done |  | Congent tech |  |  | Final sag completed
57 | 2/9 | 4/0 | 0.636 |  | 07.03.26 | 08.03.26 | Done |  | Congent tech |  |  | Final sag completed
58 | 18/0 | 19/0 | 4.543 |  | 12.03.26 | 16.03.26 |  |  | Congent tech |  |  | Final sag completed
Total Length in Kms |  |  | 202.1307 | 104.803
Total Length in Km |  |  | 202.1307 | 104.803
-0.000653

## Tower Accessories
Name of Line:- 765 KV Fatehgarh-3 Beawer Transmission Line, Package G
Placement of Accessories & aviation items
Sl No | Twr No. | Tower Type | Danger Plate nos | Number Plate nos | Circuit Plate Set of 2 | Phase Plate Set of 6 | Anti Climbing Device Set | Complete Date | Contractor | Sl No | Twr No. | Tower Type | Bird Guard Set of 6 | Complete Date | Contractor
1 | 51/8 | DA+3 | 1 | 1 | 1 | 1 | 1 | 17.02.26 | Divisha Const. | 1 | 51/8 | DA+3 | 1 | 19.02.26 | Company Gang
2 | 51/9 | DA+3 | 1 | 1 | 1 | 1 | 1 | 18.02.26 | Divisha Const. | 2 | 51/9 | DA+3 | 1 | 19.02.26 | Company Gang
3 | 51/10 | DA+3 | 1 | 1 | 1 | 1 | 1 | 18.02.26 | Divisha Const. | 3 | 51/10 | DA+3 | 1 | 19.02.26 | Company Gang
4 | 51/6 | DA+0 | 1 | 1 | 1 | 1 | 1 | 19.02.26 | Divisha Const. | 4 | 51/6 | DA+0 | 1 | 19.02.26 | Company Gang
5 | 51/7 | DA+3 | 1 | 1 | 1 | 1 | 1 | 19.02.26 | Divisha Const. | 5 | 51/7 | DA+3 | 1 | 19.02.26 | Company Gang
6 | 51/5 | DA+0 | 1 | 1 | 1 | 1 | 1 | 20.02.26 | Divisha Const. | 6 | 51/5 | DA+0 | 1 | 19.02.26 | Company Gang
7 | 51/1 | DA+0 | 1 | 1 | 1 | 1 | 1 | 20.02.26 | Divisha Const. | 7 | 51/1 | DA+0 | 1 | 19.02.26 | Company Gang
8 | 51/2 | DA+0 | 1 | 1 | 1 | 1 | 1 | 20.02.26 | Divisha Const. | 8 | 51/2 | DA+0 | 1 | 19.02.26 | Company Gang
9 | 51/3 | DA+0 | 1 | 1 | 1 | 1 | 1 | 20.02.26 | Divisha Const. | 9 | 51/3 | DA+0 | 1 | 19.02.26 | Company Gang
10 | 51/4 | DA+3 | 1 | 1 | 1 | 1 | 1 | 21.02.26 | Divisha Const. | 10 | 51/4 | DA+3 | 1 | 19.02.26 | Company Gang
11 | 51/0 | DB+0 | 1 | 1 | 1 | 1 | 1 | 21.02.26 | Divisha Const. | 11 | 50/4 | DA+3 | 1 | 19.02.26 | Company Gang
12 | 50/4 | DA+3 | 1 | 1 | 1 | 1 | 1 | 21.02.26 | Divisha Const. | 12 | 34/1 | DA+3 | 1 | 20.02.26 | Company Gang
13 | 50/3 | DA+0 | 1 | 1 | 1 | 1 | 1 | 22.02.26 | Divisha Const. | 13 | 34/2 | DA+9 | 1 | 20.02.26 | Company Gang
14 | 50/2 | DA+0 | 1 | 1 | 1 | 1 | 1 | 22.02.26 | Divisha Const. | 14 | 35/1 | DA+0 | 1 | 20.02.26 | Company Gang
15 | 50/1 | DA+0 | 1 | 1 | 1 | 1 | 1 | 23.02.26 | Divisha Const. | 15 | 35/2 | DA+0 | 1 | 20.02.26 | Company Gang
16 | 50/0 | DC+3 | 1 | 1 | 1 | 1 | 1 | 23.02.26 | Divisha Const. | 16 | 35/3 | DA+0 | 1 | 20.02.26 | Company Gang
17 | 49/0 | DC+3 | 1 | 1 | 1 | 1 | 1 | 23.02.26 | Divisha Const. | 17 | 35/4 | DA+3 | 1 | 20.02.26 | Company Gang
18 | 48/0 | DB+0 | 1 | 1 | 1 | 1 | 1 | 24.02.26 | Divisha Const. | 18 | 35/5 | DA+0 | 1 | 20.02.26 | Company Gang
19 | 48/1 | DA+0 | 1 | 1 | 1 | 1 | 1 | 24.02.26 | Divisha Const. | 19 | 35/6 | DA+9 | 1 | 20.02.26 | Company Gang
20 | 48/2 | DA+3 | 1 | 1 | 1 | 1 | 1 | 24.02.26 | Divisha Const. | 20 | 11/11 | DA+0 | 1 | 20.02.26 | Company Gang
21 | 47/2 | DA+0 | 1 | 1 | 1 | 1 | 1 | 24.02.26 | Divisha Const. | 21 | 11/12 | DA+0 | 1 | 20.02.26 | Company Gang
22 | 47/1 | DB+0 | 1 | 1 | 1 | 1 | 1 | 25.02.26 | Divisha Const. | 22 | 11/13 | DA+0 | 1 | 20.02.26 | Company Gang
23 | 47/0 | DA+0 | 1 | 1 | 1 | 1 | 1 | 25.02.26 | Divisha Const. | 23 | 11/14 | DA+0 | 1 | 20.02.26 | Company Gang
24 | 46/4 | DA+0 | 1 | 1 | 1 | 1 | 1 | 25.02.26 | Divisha Const. | 24 | 11/15 | DA+0 | 1 | 20.02.26 | Company Gang
25 | 46/3 | DA+0 | 1 | 1 | 1 | 1 | 1 | 25.02.26 | Divisha Const. | 25 | 35/7 | DA+3 | 1 | 21.02.26 | Company Gang
26 | 46/2 | DA+6 | 1 | 1 | 1 | 1 | 1 | 26.02.26 | Divisha Const. | 26 | 35/8 | DA+0 | 1 | 21.02.26 | Company Gang
27 | 46/1 | DA+6 | 1 | 1 | 1 | 1 | 1 | 26.02.26 | Divisha Const. | 27 | 35/9 | DA+3 | 1 | 21.02.26 | Company Gang
28 | 44/1 | DA+0 | 1 | 1 | 1 | 1 | 1 | 27.02.26 | Divisha Const. | 28 | 37/3 | DA+0 | 1 | 21.02.26 | Company Gang
29 | 44/2 | DA+0 | 1 | 1 | 1 | 1 | 1 | 27.02.26 | Divisha Const. | 29 | 37/4 | DA+6 | 1 | 21.02.26 | Company Gang
30 | 44/3 | DA+3 | 1 | 1 | 1 | 1 | 1 | 27.02.26 | Divisha Const. | 30 | 37/5 | DA+3 | 1 | 21.02.26 | Company Gang
31 | 44/4 | DA+0 | 1 | 1 | 1 | 1 | 1 | 27.02.26 | Divisha Const. | 31 | 38/1 | DA+3 | 1 | 21.02.26 | Company Gang
32 | 44/5 | DA+6 | 1 | 1 | 1 | 1 | 1 | 27.02.26 | Divisha Const. | 32 | 38/2 | DA+6 | 1 | 21.02.26 | Company Gang
33 | 43/4 | DA+9 | 1 | 1 | 1 | 1 | 1 | 28.02.26 | Divisha Const. | 33 | 34/3 | DA+9 | 1 | 21.02.26 | Company Gang
34 | 43/5 | DA+0 | 1 | 1 | 1 | 1 | 1 | 28.02.26 | Divisha Const. | 34 | 34/4 | DA+6 | 1 | 21.02.26 | Company Gang
35 | 43/6 | DA+6 | 1 | 1 | 1 | 1 | 1 | 28.02.26 | Divisha Const. | 35 | 13/1 | DA+3 | 1 | 21.02.26
36 | 44/0 | DB+0 | 1 | 1 | 1 | 1 | 1 | 28.02.26 | Divisha Const. | 36 | 13/2 | DA+3 | 1 | 21.02.26
37 | 43/3 | DA+3 | 1 | 1 | 1 | 1 | 1 | 01.03.26 | Divisha Const. | 37 | 13/3 | DA+0 | 1 | 21.02.26
38 | 43/2 | DA+9 | 1 | 1 | 1 | 1 | 1 | 13.03.26 | Divisha Const. | 38 | 13/4 | DA+0 | 1 | 21.02.26
39 | 43/1 | DA+9 | 1 | 1 | 1 | 1 | 1 | 13.03.26 | Divisha Const. | 39 | 14/1 | DA+3 | 1 | 21.02.26
40 | 43/0 | DB+9 | 1 | 1 | 1 | 1 | 1 | 13.03.26 | Divisha Const. | 40 | 14/2 | DA+3 | 1 | 21.02.26 |  | 14/3 Row
41 | 42/0 | DC+9 | 1 | 1 | 1 | 1 | 1 | 14.03.26 | Divisha Const. | 41 | 14/4 | DA+0 | 1 | 21.02.26
42 | 41/12 | DA+3 | 1 | 1 | 1 | 1 | 1 | 14.03.26 | Divisha Const. | 42 | 37/6 | DA+6 | 1 | 22.02.26
43 | 41/11 | DA+3 | 1 | 1 | 1 | 1 | 1 | 14.03.26 | Divisha Const. | 43 | 37/7 | DA+3 | 1 | 22.02.26
44 | 41/10 | DB+6 | 1 | 1 | 1 | 1 | 1 | 15.03.26 | Divisha Const. | 44 | 37/8 | DA+0 | 1 | 22.02.26
45 | 41/9 | DA+0 | 1 | 1 | 1 | 1 | 1 | 15.03.26 | Divisha Const. | 45 | 38/3 | DA+9 | 1 | 22.02.26
46 | 41/8 | DA+0 | 1 | 1 | 1 | 1 | 1 | 15.03.26 | Divisha Const. | 46 | 38/4 | DA+0 | 1 | 22.02.26
47 | 41/7 | DA+3 | 1 | 1 | 1 | 1 | 1 | 16.03.26 | Divisha Const. | 47 | 38/5 | DA+0 | 1 | 22.02.26
[10 empty] | 48 | 38/6 | DA+0 | 1 | 22.02.26
[10 empty] | 49 | 38/7 | DA+0 | 1 | 22.02.26
[10 empty] | 50 | 38/8 | DA+0 | 1 | 22.02.26
[10 empty] | 51 | 39/1 | DA+6 | 1 | 23.02.26
[10 empty] | 52 | 39/2 | DA+0 | 1 | 23.02.26
[10 empty] | 53 | 39/3 | DA+3 | 1 | 23.02.26 |  | 39/4 Balance
[10 empty] | 54 | 39/5 | DA+3 | 1 | 23.02.26
[10 empty] | 55 | 39/6 | DA+0 | 1 | 23.02.26
[10 empty] | 56 | 39/7 | DA+0 | 1 | 23.02.26
[10 empty] | 57 | 40/3 | DA+3 | 1 | 24.02.26
[10 empty] | 58 | 40/4 | DA+9 | 1 | 24.02.26
[10 empty] | 59 | 40/6 | DA+3 | 1 | 24.02.26
[10 empty] | 60 | 40/7 | DA+3 | 1 | 24.02.26
[10 empty] | 61 | 40/8 | DA+0 | 1 | 24.02.26
[10 empty] | 62 | 40/9 | DA+0 | 1 | 24.02.26
[10 empty] | 63 | 40/11 | DA+9 | 1 | 24.02.26
[10 empty] | 64 | 44/1 | DA+0 | 1 | 24.02.26
[10 empty] | 65 | 44/2 | DA+0 | 1 | 24.02.26
[10 empty] | 66 | 44/3 | DA+3 | 1 | 24.02.26
[10 empty] | 67 | 44/4 | DA+0 | 1 | 24.02.26
[10 empty] | 68 | 14/3 | DA+0 | 1 | 24.02.26
[10 empty] | 69 | 14/5 | DA+0 | 1 | 24.02.26
[10 empty] | 70 | 14/6 | DA+0 | 1 | 24.02.26
[10 empty] | 71 | 15/3 | DA+3 | 1 | 24.02.26
[10 empty] | 72 | 58/8 | DA+0 | 1 | 25.02.26
[10 empty] | 73 | 58/9 | DA+0 | 1 | 25.02.26
[10 empty] | 74 | 58/10 | DA+3 | 1 | 25.02.26
[10 empty] | 75 | 58/11 | DA+3 | 1 | 25.02.26
[10 empty] | 76 | 58/12 | DA+0 | 1 | 25.02.26
[10 empty] | 77 | 50/1 | DA+0 | 1 | 25.02.26
[10 empty] | 78 | 50/2 | DA+0 | 1 | 25.02.26
[10 empty] | 79 | 50/3 | DA+0 | 1 | 25.02.26
[10 empty] | 80 | 43/1 | DA+9 | 1 | 25.02.26
[10 empty] | 81 | 43/2 | DA+9 | 1 | 25.02.26
[10 empty] | 82 | 43/3 | DA+3 | 1 | 25.02.26
[10 empty] | 83 | 43/4 | DA+9 | 1 | 25.02.26
[10 empty] | 84 | 43/5 | DA+0 | 1 | 25.02.26
[10 empty] | 85 | 43/6 | DA+6 | 1 | 25.02.26
[10 empty] | 86 | 41/9 | DA+0 | 1 | 25.02.26
[10 empty] | 87 | 41/10 | DA+3 | 1 | 25.02.26
[10 empty] | 88 | 41/11 | DA+3 | 1 | 25.02.26
[10 empty] | 89 | 41/12 | DA+3 | 1 | 25.02.26
[10 empty] | 90 | 48/2 | DA+3 | 1 | 25.02.26
[10 empty] | 91 | 15/1 | DA+6 | 1 | 25.02.26
[10 empty] | 92 | 15/2 | DA+9 | 1 | 25.02.26
[10 empty] | 93 | 15/4 | DA+0 | 1 | 25.02.26
[10 empty] | 94 | 15/6 | DA+0 | 1 | 25.02.26
[10 empty] | 95 | 19/7 | DA+9 | 1 | 25.02.26
[10 empty] | 96 | 19/9 | DA+3 | 1 | 25.02.26
[10 empty] | 97 | 19/13 | DA+0 | 1 | 25.02.26
[10 empty] | 98 | 19/14 | DA+9 | 1 | 25.02.26
[10 empty] | 99 | 19/6 | DA+3 | 1 | 26.02.26
[10 empty] | 100 | 19/4 | DA+0 | 1 | 26.02.26
[10 empty] | 101 | 19/5 | DA+3 | 1 | 26.02.26
[10 empty] | 102 | 19/11 | DA+9 | 1 | 26.02.26
[10 empty] | 103 | 15/7 | DA+6 | 1 | 26.02.26
[10 empty] | 104 | 15/8 | DA+0 | 1 | 26.02.26
[10 empty] | 105 | 15/9 | DA+9 | 1 | 26.02.26
[10 empty] | 106 | 41/4 | DA+0 | 1 | 26.02.26
[10 empty] | 107 | 41/5 | DA+0 | 1 | 26.02.26
[10 empty] | 108 | 41/6 | DA+0 | 1 | 26.02.26
[10 empty] | 109 | 41/7 | DA+3 | 1 | 26.02.26
[10 empty] | 110 | 41/8 | DA+9 | 1 | 26.02.26
[10 empty] | 111 | 46/4 | DA+0 | 1 | 26.02.26
[10 empty] | 112 | 47/1 | DA+0 | 1 | 26.02.26
[10 empty] | 113 | 47/2 | DA+0 | 1 | 26.02.26
[10 empty] | 114 | 47/3 | DA+0 | 1 | 26.02.26
[10 empty] | 115 | 48/1 | DA+0 | 1 | 26.02.26
[10 empty] | 116 | 40/12 | DA+9 | 1 | 27.02.26
[10 empty] | 117 | 41/1 | DA+3 | 1 | 27.02.26
[10 empty] | 118 | 41/2 | DA+0 | 1 | 27.02.26
[10 empty] | 119 | 41/3 | DA+0 | 1 | 27.02.26
[10 empty] | 120 | 44/5 | DA+0 | 1 | 27.02.26
[10 empty] | 121 | 46/1 | DA+6 | 1 | 27.02.26
[10 empty] | 122 | 46/2 | DA+0 | 1 | 27.02.26
[10 empty] | 123 | 46/3 | DA+0 | 1 | 27.02.26
[10 empty] | 124 | 17/1 | DA+3 | 1 | 27.02.26
[10 empty] | 125 | 17/3 | DA+3 | 1 | 27.02.26
[10 empty] | 126 | 17/4 | DA+3 | 1 | 27.02.26
[10 empty] | 127 | 15/5 | DA+3 | 1 | 27.02.26
[10 empty] | 128 | 53/1 | DA+0 | 1 | 28.02.26
[10 empty] | 129 | 53/2 | DA+3 | 1 | 28.02.26
[10 empty] | 130 | 53/3 | DA+3 | 1 | 28.02.26
[10 empty] | 131 | 53/4 | DA+3 | 1 | 28.02.26
[10 empty] | 132 | 55/1 | DA+3 | 1 | 28.02.26
[10 empty] | 133 | 55/2 | DA+3 | 1 | 28.02.26
[10 empty] | 134 | 55/3 | DA+0 | 1 | 28.02.26
[10 empty] | 135 | 55/4 | DA+3 | 1 | 28.02.26
[10 empty] | 136 | 55/5 | DA+0 | 1 | 28.02.26
[10 empty] | 137 | 57/10 | DA+0 | 1 | 28.02.26
[10 empty] | 138 | 57/11 | DA+0 | 1 | 28.02.26
[10 empty] | 139 | 57/12 | DA+3 | 1 | 28.02.26
[10 empty] | 140 | 57/13 | DA+0 | 1 | 28.02.26
[10 empty] | 141 | 17/5 | DA+3 | 1 | 28.02.26
[10 empty] | 142 | 11/7 | DA+3 | 1 | 28.02.26
[10 empty] | 143 | 11/2 | DA+9 | 1 | 28.02.26
[10 empty] | 144 | 11/4 | DA+6 | 1 | 28.02.26
[10 empty] | 145 | 55/6 | DA+3 | 1 | 01.03.26
[10 empty] | 146 | 55/7 | DA+0 | 1 | 01.03.26
[10 empty] | 147 | 55/8 | DA+3 | 1 | 01.03.26
[10 empty] | 148 | 55/9 | DA+3 | 1 | 01.03.26
[10 empty] | 149 | 55/10 | DA+3 | 1 | 01.03.26
[10 empty] | 150 | 55/11 | DA+3 | 1 | 01.03.26
[10 empty] | 151 | 58/4 | DA+56 | 1 | 01.03.26
[10 empty] | 152 | 58/5 | DA+3 | 1 | 01.03.26
[10 empty] | 153 | 58/6 | DA+3 | 1 | 01.03.26
[10 empty] | 154 | 19/3 | DA+6 | 1 | 01.03.26
[10 empty] | 155 | 56/1 | DA+3 | 1 | 02.03.26
[10 empty] | 156 | 56/2 | DA+3 | 1 | 02.03.26
[10 empty] | 157 | 56/3 | DA+0 | 1 | 02.03.26
[10 empty] | 158 | 56/4 | DA+3 | 1 | 02.03.26
[10 empty] | 159 | 57/4 | DA+0 | 1 | 02.03.26
[10 empty] | 160 | 57/5 | DA+3 | 1 | 02.03.26
[10 empty] | 161 | 58/1 | DA+0 | 1 | 02.03.26
[10 empty] | 162 | 58/2 | DA+0 | 1 | 02.03.26
[10 empty] | 163 | 58/3 | DA+3 | 1 | 02.03.26
[10 empty] | 164 | 58/13 | DA+6 | 1 | 02.03.26
[10 empty] | 165 | 58/14 | DA=0 | 1 | 02.03.26
[10 empty] | 166 | 58/15 | DA+3 | 1 | 02.03.26
[10 empty] | 167 | 58/16 | DA+3 | 1 | 02.03.26
[10 empty] | 168 | 1A/1 | DA+0 | 1 | 02.03.26
[10 empty] | 169 | 1A/2 | DA+6 | 1 | 02.03.26
[10 empty] | 170 | 1A/3 | DA+0 | 1 | 02.03.26
[10 empty] | 171 | 1A/4 | DA+3 | 1 | 02.03.26
[10 empty] | 172 | 1A/5 | DA+6 | 1 | 02.03.26
[10 empty] | 173 | 1A/6 | DA+0 | 1 | 02.03.26
[10 empty] | 174 | 1A/7 | DA+3 | 1 | 02.03.26
[10 empty] | 175 | 2/1 | DA+0 | 1 | 02.03.26
[10 empty] | 176 | 2/2 | DA+0 | 1 | 02.03.26
[10 empty] | 177 | 2/3 | DA+0 | 1 | 02.03.26
[10 empty] | 178 | 2/4 | DA+3 | 1 | 02.03.26
[10 empty] | 179 | 2/5 | DA+3 | 1 | 02.03.26
[10 empty] | 180 | 2/6 | DA+6 | 1 | 02.03.26
[10 empty] | 181 | 2/7 | DA+6 | 1 | 02.03.26
[10 empty] | 182 | 2/8 | DA+0 | 1 | 02.03.26
[10 empty] | 183 | 2/9 | DA+0 | 1 | 02.03.26
[10 empty] | 184 | 4/1 | DA+0 | 1 | 02.03.26
[10 empty] | 185 | 4/2 | DA+0 | 1 | 02.03.26
[10 empty] | 186 | 4/3 | DA+0 | 1 | 02.03.26
[10 empty] | 187 | 4/4 | DA+0 | 1 | 02.03.26
[10 empty] | 188 | 6/1 | DA+0 | 1 | 02.03.26
[10 empty] | 189 | 6/2 | DA+3 | 1 | 02.03.26
[10 empty] | 190 | 10/15 | DA+3 | 1 | 05.02.26
[10 empty] | 191 | 10/16 | DA+3 | 1 | 05.02.26
[10 empty] | 192 | 10/17 | DA+3 | 1 | 05.02.26
[10 empty] | 193 | 10/18 | DA+0 | 1 | 05.02.26
[10 empty] | 194 | 56/7 | DA+3 | 1 | 05.02.26
[10 empty] | 195 | 56/8 | DA+3 | 1 | 05.02.26
[10 empty] | 196 | 56/9 | DA+3 | 1 | 05.02.26
[10 empty] | 197 | 57/1 | DA+3 | 1 | 05.02.26
[10 empty] | 198 | 57/2 | DA+0 | 1 | 05.02.26
[10 empty] | 199 | 57/3 | DA+0 | 1 | 05.02.26
[10 empty] | 200 | 59/1 | DA+0 | 1 | 05.02.26
[10 empty] | 201 | 59/2 | DA+0 | 1 | 05.02.26
[10 empty] | 202 | 59/3 | DA+0 | 1 | 05.02.26
[10 empty] | 203 | 59/4 | DA+0 | 1 | 05.02.26
[10 empty] | 204 | 59/5 | DA+0 | 1 | 05.02.26
[10 empty] | 205 | 59/6 | DA+0 | 1 | 05.02.26
[10 empty] | 206 | 61/1 | DA+0 | 1 | 05.02.26
[10 empty] | 207 | 61/2 | DA+0 | 1 | 05.02.26
[10 empty] | 208 | 11/1 | DA+6 | 1 | 06.02.26
[10 empty] | 209 | 10/19 | DA+9 | 1 | 06.02.26
[10 empty] | 210 | 10/21 | DA+0 | 1 | 06.02.26
[10 empty] | 211 | 10/22 | DA+0 | 1 | 06.02.26
[10 empty] | 212 | 10/23 | DA+9 | 1 | 06.02.26
[10 empty] | 213 | 71/1 | DA+0 | 1 | 06.02.26
[10 empty] | 214 | 71/2 | DA+0 | 1 | 06.02.26
[10 empty] | 215 | 71/3 | DA+0 | 1 | 06.02.26
[10 empty] | 216 | 71/4 | DA+0 | 1 | 06.02.26
[10 empty] | 217 | 71/5 | DA+0 | 1 | 06.02.26
[10 empty] | 218 | 72/1 | DA+0 | 1 | 06.02.26
[10 empty] | 219 | 72/2 | DA+0 | 1 | 06.02.26
[10 empty] | 220 | 72/3 | DA+0 | 1 | 06.02.26
[10 empty] | 221 | 72/4 | DA+0 | 1 | 06.02.26
[10 empty] | 222 | 72/5 | DA+0 | 1 | 06.02.26
[10 empty] | 223 | 72/6 | DA+0 | 1 | 06.02.26
[10 empty] | 224 | 69/6 | DA+0 | 1 | 06.02.26
[10 empty] | 225 | 69/1 | DA+0 | 1 | 07.03.26
[10 empty] | 226 | 69/2 | DA+0 | 1 | 07.03.26
[10 empty] | 227 | 69/3 | DA+0 | 1 | 07.03.26
[10 empty] | 228 | 69/4 | DA+0 | 1 | 07.03.26
[10 empty] | 229 | 69/5 | DA+0 | 1 | 07.03.26
[10 empty] | 230 | 69/7 | DA+0 | 1 | 07.03.26
[10 empty] | 231 | 69/8 | DA+0 | 1 | 07.03.26
[10 empty] | 232 | 69/9 | DA+0 | 1 | 07.03.26
[10 empty] | 233 | 68/4 | DA+3 | 1 | 07.03.26
[10 empty] | 234 | 68/5 | DA+3 | 1 | 07.03.26
[10 empty] | 235 | 68/6 | DA+3 | 1 | 07.03.26
[10 empty] | 236 | 68/1 | DA+3 | 1 | 08.03.26
[10 empty] | 237 | 68/2 | DA+3 | 1 | 08.03.26 | 68/3
[10 empty] | 238 | 66/1 | DA+3 | 1 | 08.03.26
[10 empty] | 239 | 66/2 | DA+0 | 1 | 08.03.26
[10 empty] | 240 | 66/3 | DA+3 | 1 | 08.03.26
[10 empty] | 241 | 66/4 | DA+3 | 1 | 08.03.26
[10 empty] | 242 | 11/8 | DA+0 | 1 | 08.03.26
[10 empty] | 243 | 11/9 | DA+3 | 1 | 08.03.26
[10 empty] | 244 | 11/5 | DA+3 | 1 | 08.03.26
[10 empty] | 245 | 52/1 | DA+0 | 1 | 09.03.26
[10 empty] | 246 | 52/2 | DA+3 | 1 | 09.03.26
[10 empty] | 247 | 52/3 | DA+0 | 1 | 09.03.26
[10 empty] | 248 | 52/4 | DA+0 | 1 | 09.03.26
[10 empty] | 249 | 52/5 | DA+3 | 1 | 09.03.26
[10 empty] | 250 | 56/5 | DA+0 | 1 | 09.03.26
[10 empty] | 251 | 56/6 | DA+3 | 1 | 09.03.26
[10 empty] | 252 | 16/4 | DA+3 | 1 | 09.03.26
[10 empty] | 253 | 16/5 | DA+3 | 1 | 09.03.26
[10 empty] | 254 | 65/2 | DA+0 | 1 | 10.03.26
[10 empty] | 255 | 65/3 | DA+0 | 1 | 10.03.26
[10 empty] | 256 | 65/4 | DA+0 | 1 | 10.03.26
[10 empty] | 257 | 65/5 | DA+0 | 1 | 10.03.26
[10 empty] | 258 | 65/6 | DA+0 | 1 | 10.03.26
[10 empty] | 259 | 65/7 | DA+0 | 1 | 10.03.26
[10 empty] | 260 | 64/1 | DA+6 | 1 | 11.03.26
[10 empty] | 261 | 64/2 | DA+0 | 1 | 11.03.26
[10 empty] | 262 | 64/3 | DA+0 | 1 | 11.03.26
[10 empty] | 263 | 64/4 | DA+3 | 1 | 11.03.26
[10 empty] | 264 | 64/5 | DA+3 | 1 | 11.03.26
[10 empty] | 265 | 64/6 | DA+3 | 1 | 11.03.26
[10 empty] | 266 | 64/7 | DA+3 | 1 | 11.03.26
[10 empty] | 267 | 64/8 | DA+0 | 1 | 11.03.26
[10 empty] | 268 | 64/9 | DA+0 | 1 | 12.03.25
[10 empty] | 269 | 63/4 | DA+0 | 1 | 12.03.25
[10 empty] | 270 | 63/5 | DA+3 | 1 | 12.03.25
[10 empty] | 271 | 63/6 | DA+3 | 1 | 12.03.25
[10 empty] | 272 | 32/2 | DA+0 | 1 | 12.03.25
[10 empty] | 273 | 32/3 | DA+3 | 1 | 12.03.25
[10 empty] | 274 | 32/4 | DA+6 | 1 | 12.03.25
[10 empty] | 275 | 32/5 | DA+6 | 1 | 12.03.25
[10 empty] | 276 | 32/6 | DA+6 | 1 | 12.03.25
[10 empty] | 277 | 32/7 | DA+0 | 1 | 12.03.25
[10 empty] | 278 | 32/8 | DA+9 | 1 | 12.03.25
[10 empty] | 279 | 57/7 | DA+3 | 1 | 13.03.26
[10 empty] | 280 | 57/8 | DA+0 | 1 | 13.03.26
[10 empty] | 281 | 32/1 | DA+9 | 1 | 13.03.26
[10 empty] | 282 | 31/4 | DA+9 | 1 | 13.03.26
[10 empty] | 283 | 65/1 | DA+3 | 1 | 13.03.26
[10 empty] | 284 | 63/3 | DA+3 | 1 | 13.03.26
[10 empty] | 285 | 33/1 | DA+0 | 1 | 14.03.26
[10 empty] | 286 | 33/2 | DA+0 | 1 | 14.03.26
[10 empty] | 287 | 33/3 | DA+0 | 1 | 14.03.26
[10 empty] | 288 | 33/4 | DA+0 | 1 | 14.03.26
[10 empty] | 289 | 33/7 | DA+9 | 1 | 14.03.26
[10 empty] | 290 | 33/8 | DA+3 | 1 | 14.03.26
[10 empty] | 291 | 19/10 | DA+9 | 1 | 14.03.26
[10 empty] | 292 | 16/3 | DA+0 | 1 | 14.03.26
[10 empty] | 293 | 8/1 | DA+3 | 1 | 15.03.26
[10 empty] | 294 | 8/2 | DA+3 | 1 | 15.03.26
[10 empty] | 295 | 8/3 | DA+3 | 1 | 15.03.26
[10 empty] | 296 | 8/4 | DA+0 | 1 | 15.03.26
[10 empty] | 297 | 8/5 | DA+3 | 1 | 15.03.26
[10 empty] | 298 | 8/6 | DA+3 | 1 | 15.03.26
[10 empty] | 299 | 8/8 | DA+6 | 1 | 15.03.26
[10 empty] | 300 | 8/9 | DA+3 | 1 | 15.03.26
[10 empty] | 301 | 8/10 | DA+3 | 1 | 15.03.26
[10 empty] | 302 | 31/1 | DA+9 | 1 | 15.03.26
[10 empty] | 303 | 31/2 | DA+0 | 1 | 15.03.26
[10 empty] | 304 | 31/3 | DA+0 | 1 | 15.03.26
[10 empty] | 305 | 30/1 | DA+3 | 1 | 15.03.26
[10 empty] | 306 | 30/2 | DA+0 | 1 | 15.03.26
[10 empty] | 307 | 29/9 | DA+3 | 1 | 15.03.26
[10 empty] | 308 | 29/10 | DA+6 | 1 | 15.03.26
[10 empty] | 309 | 16/1 | DA+3 | 1 | 15.03.26
[10 empty] | 310 | 16/2 | DA+3 | 1 | 15.03.26
[10 empty] | 311 | 16/6 | DA+0 | 1 | 15.03.26
[10 empty] | 312 | 8/11 | DA+3 | 1 | 16.03.26
[10 empty] | 313 | 8/12 | DA+0 | 1 | 16.03.26
[10 empty] | 314 | 10/1 | DA+3 | 1 | 16.03.26
[10 empty] | 315 | 10/2 | DA+0 | 1 | 16.03.26
[10 empty] | 316 | 29/8 | DA+3 | 1 | 16.03.26
[10 empty] | 317 | 29/7 | DA+0 | 1 | 16.03.26
[10 empty] | 318 | 29/3 | DA+6 | 1 | 16.03.26
[10 empty] | 319 | 28/1 | DA+6 | 1 | 16.03.26
[10 empty] | 320 | 28/2 | DA+3 | 1 | 16.03.26
[10 empty] | 321 | 28/3 | DA+0 | 1 | 16.03.26
[10 empty] | 322 | 28/4 | DA+9 | 1 | 16.03.26
[10 empty] | 323 | 63/1 | DA+6 | 1 | 16.03.26
| Total Complete(Nos) |  | 47 | 47 | 47 | 47 | 47 |  |  |  | Total Complete(Nos) |  | 323
|  |  | 474 | [9 empty] | 106 |  | 259 | 120 | 50
[15 empty] | 229 | 94 | 0
[15 empty] | 30 | 26 | 50

## Span Marker& Divertor
Name of Line:- 765 KV Fatehgarh-3 Beawer Transmission Line, Package G
Placement of Span Marker & Bird Diverters
Sl No | Span |  | Span Markers Installed | Complete Date | Contractor |  | Sl No | Span |  | No of Bird Flight Divertors nos | Complete Date | Contractor
| From | To | [5 empty] | From | To
1 | 51/7 | 51/8 | 1 | 19.02.26 | OM Const |  | 1 | 27/4 | 27/5 | 31 | 18.02.26 | OM Const.
2 | 51/8 | 51/9 | 1 | 19.02.26 | OM Const |  | 2 | 27/5 | 28/0 | 25 | 18.02.26 | OM Const.
3 | 51/9 | 51/10 | 1 | 19.02.26 | OM Const |  | 3 | 23/11 | 24/0 | 39 | 18.02.26 | OM Const.
4 | 51/10 | 52/0 | 1 | 19.02.26 | OM Const |  | 4 | 24/0 | 24/1 | 38 | 18.02.26 | OM Const.
5 | 52/0 | 52/1 | 1 | 19.02.26 | OM Const |  | 5 | 24/1 | 24/2 | 39 | 18.02.26 | OM Const.
6 | 52/1 | 52/2 | 1 | 19.02.26 | OM Const |  | 6 | 24/2 | 24/3 | 36 | 18.02.26 | OM Const.
7 | 52/2 | 52/3 | 1 | 19.02.26 | OM Const |  | 7 | 24/3 | 24/4 | 37 | 18.02.26 | OM Const.
8 | 52/4 | 52/5 | 1 | 19.02.26 | OM Const |  | 8 | 24/4 | 24/5 | 37 | 18.02.26 | OM Const.
9 | 52/5 | 53/0 | 1 | 19.02.26 | OM Const |  | 9 | 24/5 | 24/6 | 39 | 18.02.26 | OM Const.
10 | 53/0 | 53/1 | 1 | 19.02.26 | OM Const |  | 10 | 24/6 | 25/0 | 36 | 18.02.26 | OM Const.
11 | 53/1 | 53/2 | 1 | 19.02.26 | OM Const |  | 11 | 12/0 | 13/0 | 21 | 19.02.26 | Shiv Raj
12 | 53/2 | 53/3 | 1 | 19.02.26 | OM Const |  | 12 | 13/0 | 13/1 | 39 | 19.02.26 | Shiv Raj
13 | 53/3 | 53/4 | 1 | 19.02.26 | OM Const |  | 13 | 13/1 | 13/2 | 37 | 19.02.26 | Shiv Raj
14 | 53/4 | 55/0 | 1 | 19.02.26 | OM Const |  | 14 | 13/2 | 13/3 | 41 | 19.02.26 | Shiv Raj
15 | 55/0 | 55/1 | 1 | 19.02.26 | OM Const |  | 15 | 13/3 | 13/4 | 37 | 19.02.26 | Shiv Raj
16 | 55/1 | 55/2 | 1 | 19.02.26 | OM Const |  | 16 | 13/4 | 14/0 | 34 | 19.02.26 | Shiv Raj
17 | 47/2 | 47/3 | 1 | 20.02.26 | OM Const |  | 17 | 15/0 | 15/1 | 45 | 19.02.26 | Shiv Raj
18 | 47/3 | 48/0 | 1 | 20.02.26 | OM Const |  | 18 | 15/1 | 15/2 | 33 | 20.02.26 | Shiv Raj
19 | 48/0 | 48/1 | 1 | 20.02.26 | OM Const |  | 19 | 14/0 | 14/1 | 39 | 20.02.26 | Shiv Raj
20 | 48/1 | 48/2 | 1 | 20.02.26 | OM Const |  | 20 | 14/1 | 14/2 | 38 | 20.02.26 | Shiv Raj
21 | 48/2 | 49/0 | 1 | 20.02.26 | OM Const |  | 21 | 14/2 | 14/3 | 37 | 20.02.26 | Shiv Raj
22 | 49/0 | 50/0 | 1 | 20.02.26 | OM Const |  | 22 | 14/3 | 14/4 | 36 | 20.02.26 | Shiv Raj
23 | 50/0 | 50/1 | 1 | 20.02.26 | OM Const |  | 23 | 15/2 | 15/3 | 42 | 21.02.26 | Shiv Raj
24 | 50/1 | 50/2 | 1 | 20.02.26 | OM Const |  | 24 | 15/3 | 15/4 | 40 | 21.02.26 | Shiv Raj
25 | 50/2 | 50/3 | 1 | 20.02.26 | OM Const |  | 25 | 15/4 | 15/5 | 39 | 21.02.26 | Shiv Raj
26 | 50/3 | 50/4 | 1 | 20.02.26 | OM Const |  | 26 | 15/5 | 15/6 | 41 | 21.02.26 | Shiv Raj
27 | 50/4 | 51/0 | 1 | 20.02.26 | OM Const |  | 27 | 15/6 | 15/7 | 41 | 21.02.26 | Shiv Raj
28 | 51/0 | 51/1 | 1 | 20.02.26 | OM Const |  | 28 | 15/7 | 15/8 | 41 | 21.02.26 | Shiv Raj
29 | 51/1 | 51/2 | 1 | 20.02.26 | OM Const |  | 29 | 15/8 | 15/9 | 41 | 21.02.26 | Shiv Raj
30 | 51/2 | 51/3 | 1 | 20.02.26 | OM Const |  | 30 | 15/9 | 16/0 | 40 | 21.02.26 | Shiv Raj
31 | 51/3 | 51/4 | 1 | 20.02.26 | OM Const |  | 31 | 16/0 | 16/1 | 38 | 21.02.26 | Shiv Raj
32 | 51/4 | 51/5 | 1 | 20.02.26 | OM Const |  | 32 | 14/4 | 14/5 | 36 | 22.02.26 | Shiv Raj
33 | 51/5 | 51/6 | 1 | 20.02.26 | OM Const |  | 33 | 14/5 | 14/6 | 37 | 22.02.26 | Shiv Raj
34 | 51/6 | 51/7 | 1 | 20.02.26 | OM Const |  | 34 | 14/6 | 15/0 | 31 | 22.02.26 | Shiv Raj
35 | 44/5 | 45/0 | 1 | 21.02.26 | OM Const |  | 35 | 11/12 | 11/13 | 32 | 22.02.26 | Shiv Raj
36 | 45/0 | 46/0 | 1 | 21.02.26 | OM Const |  | 36 | 11/13 | 11/14 | 39 | 22.02.26 | Shiv Raj
37 | 46/0 | 46/1 | 1 | 21.02.26 | OM Const |  | 37 | 11/14 | 11/15 | 34 | 22.02.26 | Shiv Raj
38 | 46/1 | 46/2 | 1 | 21.02.26 | OM Const |  | 38 | 11/15 | 12/0 | 36 | 22.02.26 | Shiv Raj
39 | 46/2 | 46/3 | 1 | 21.02.26 | OM Const |  | 39 | 17/0 | 17/1 | 40 | 23.02.26 | Shiv Raj
40 | 46/3 | 46/4 | 1 | 21.02.26 | OM Const |  | 40 | 17/1 | 17/2 | 42 | 23.02.26 | Shiv Raj
41 | 46/4 | 47/0 | 1 | 21.02.26 | OM Const |  | 41 | 17/3 | 17/4 | 41 | 24.02.26 | Shiv Raj
42 | 47/0 | 47/1 | 1 | 21.02.26 | OM Const |  | 42 | 17/4 | 17/5 | 41 | 24.02.26 | Shiv Raj
43 | 47/1 | 47/2 | 1 | 21.02.26 | OM Const |  | 43 | 17/5 | 18/0 | 41 | 24.02.26 | Shiv Raj
44 | 55/2 | 55/3 | 1 | 21.02.26 | OM Const |  | 44 | 16/5 | 16/6 | 40 | 24.02.26 | Shiv Raj
45 | 55/3 | 55/4 | 1 | 21.02.26 | OM Const |  | 45 | 16/6 | 17/0 | 36 | 24.02.26 | Shiv Raj
46 | 55/4 | 55/5 | 1 | 21.02.26 | OM Const |  | 46 | 23/0 | 23/1 | 38 | 24.02.26 | OM Const.
47 | 55/5 | 55/6 | 1 | 21.02.26 | OM Const |  | 47 | 23/1 | 23/2 | 41 | 24.02.26 | OM Const.
48 | 55/6 | 55/7 | 1 | 21.02.26 | OM Const |  | 48 | 23/2 | 23/3 | 38 | 24.02.26 | OM Const.
49 | 55/7 | 55/8 | 1 | 21.02.26 | OM Const |  | 49 | 23/3 | 23/4 | 37 | 24.02.26 | OM Const.
50 | 55/8 | 55/9 | 1 | 21.02.26 | OM Const |  | 50 | 23/4 | 23/5 | 40 | 24.02.26 | OM Const.
51 | 55/9 | 55/10 | 1 | 21.02.26 | OM Const |  | 51 | 23/5 | 23/6 | 42 | 24.02.26 | OM Const.
52 | 52/3 | 52/4 | 1 | 21.02.26 | OM Const |  | 52 | 23/6 | 23/7 | 40 | 24.02.26 | OM Const.
53 | 56/0 | 56/1 | 1 | 22.02.26 | OM Const |  | 53 | 23/7 | 23/8 | 32 | 24.02.26 | OM Const.
54 | 56/1 | 56/2 | 1 | 22.02.26 | OM Const |  | 54 | 23/8 | 23/9 | 41 | 24.02.26 | OM Const.
55 | 56/2 | 56/3 | 1 | 22.02.26 | OM Const |  | 55 | 23/9 | 23/10 | 40 | 24.02.26 | OM Const.
56 | 56/3 | 56/4 | 1 | 22.02.26 | OM Const |  | 56 | 23/10 | 23/11 | 41 | 24.02.26 | OM Const.
57 | 56/4 | 56/5 | 1 | 22.02.26 | OM Const |  | 57 | 22/0 | 22/1 | 44 | 25.02.26 | OM Const.
58 | 56/5 | 56/6 | 1 | 22.02.26 | OM Const |  | 58 | 22/1 | 22/2 | 36 | 25.02.26 | OM Const.
59 | 56/6 | 56/7 | 1 | 22.02.26 | OM Const |  | 59 | 22/2 | 22/3 | 39 | 25.02.26 | OM Const.
60 | 56/7 | 56/8 | 1 | 22.02.26 | OM Const |  | 60 | 22/3 | 22/4 | 42 | 25.02.26 | OM Const.
61 | 56/8 | 56/9 | 1 | 22.02.26 | OM Const |  | 61 | 22/4 | 22/5 | 40 | 25.02.26 | OM Const.
62 | 56/9 | 57/0 | 1 | 22.02.26 | OM Const |  | 62 | 22/5 | 22/6 | 40 | 25.02.26 | OM Const.
63 | 57/0 | 57/1 | 1 | 22.02.26 | OM Const |  | 63 | 22/6 | 22/7 | 41 | 25.02.26 | OM Const.
64 | 57/1 | 57/2 | 1 | 22.02.26 | OM Const |  | 64 | 22/7 | 22/8 | 38 | 25.02.26 | OM Const.
65 | 57/2 | 57/3 | 1 | 22.02.26 | OM Const |  | 65 | 22/8 | 22/9 | 41 | 25.02.26 | OM Const.
66 | 57/3 | 57/4 | 1 | 22.02.26 | OM Const |  | 66 | 22/9 | 23/0 | 33 | 25.02.26 | OM Const.
67 | 57/4 | 57/5 | 1 | 22.02.26 | OM Const |  | 67 | 16/2 | 16/3 | 40 | 25.02.26 | Shiv Raj
68 | 57/5 | 57/6 | 1 | 22.02.26 | OM Const |  | 68 | 16/3 | 16/4 | 38 | 25.02.26 | Shiv Raj
69 | 57/6 | 57/7 | 1 | 22.02.26 | OM Const |  | 69 | 16/4 | 16/5 | 40 | 25.02.26 | Shiv Raj
70 | 57/7 | 57/8 | 1 | 23.02.26 | OM Const |  | 70 | 19/6 | 19/7 | 35 | 26.02.26 | Shiv Raj
71 | 57/8 | 57/9 | 1 | 23.02.26 | OM Const |  | 71 | 19/7 | 19/8 | 47 | 26.02.26 | Shiv Raj
72 | 57/9 | 57/10 | 1 | 23.02.26 | OM Const |  | 72 | 19/8 | 19/9 | 40 | 26.02.26 | Shiv Raj
73 | 57/10 | 57/11 | 1 | 23.02.26 | OM Const |  | 73 | 19/9 | 19/10 | 42 | 26.02.26 | Shiv Raj
74 | 57/11 | 57/12 | 1 | 23.02.26 | OM Const |  | 74 | 19/10 | 19/11 | 38 | 26.02.26 | Shiv Raj
75 | 57/12 | 57/13 | 1 | 23.02.26 | OM Const |  | 75 | 19/11 | 19/12 | 44 | 26.02.26 | Shiv Raj
76 | 57/13 | 58/0 | 1 | 23.02.26 | OM Const |  | 76 | 19/12 | 19/13 | 45 | 26.02.26 | Shiv Raj
77 | 58/0 | 58/1 | 1 | 23.02.26 | OM Const |  | 77 | 19/13 | 19/14 | 31 | 26.02.26 | Shiv Raj
78 | 58/1 | 58/2 | 1 | 23.02.26 | OM Const |  | 78 | 19/14 | 20/0 | 42 | 26.02.26 | Shiv Raj
79 | 58/2 | 58/3 | 1 | 23.02.26 | OM Const |  | 79 | 20/0 | 21/0 | 26 | 26.02.26 | Shiv Raj
80 | 58/3 | 58/4 | 1 | 23.02.26 | OM Const |  | 80 | 25/0 | 25/1 | 39 | 26.02.26 | OM Const.
81 | 58/4 | 58/5 | 1 | 23.02.26 | OM Const |  | 81 | 25/1 | 25/2 | 40 | 26.02.26 | OM Const.
82 | 58/5 | 58/6 | 1 | 23.02.26 | OM Const |  | 82 | 25/2 | 25/3 | 42 | 26.02.26 | OM Const.
83 | 58/6 | 58/7 | 1 | 23.02.26 | OM Const |  | 83 | 25/3 | 25/4 | 40 | 26.02.26 | OM Const.
84 | 58/7 | 58/8 | 1 | 23.02.26 | OM Const |  | 84 | 25/4 | 25/5 | 42 | 26.02.26 | OM Const.
85 | 58/8 | 58/9 | 1 | 23.02.26 | OM Const |  | 85 | 25/5 | 25/6 | 40 | 26.02.26 | OM Const.
86 | 58/9 | 58/10 | 1 | 23.02.26 | OM Const |  | 86 | 25/6 | 25/7 | 42 | 26.02.26 | OM Const.
87 | 58/10 | 58/11 | 1 | 23.02.26 | OM Const |  | 87 | 25/7 | 25/8 | 38 | 26.02.26 | OM Const.
88 | 58/11 | 58/12 | 1 | 23.02.26 | OM Const |  | 88 | 25/8 | 25/9 | 41 | 26.02.26 | OM Const.
89 | 58/12 | 58/13 | 1 | 23.02.26 | OM Const |  | 89 | 25/9 | 25/10 | 41 | 26.02.26 | OM Const.
90 | 58/13 | 58/14 | 1 | 24.02.26 | OM Const |  | 90 | 25/10 | 25/11 | 39 | 26.02.26 | OM Const.
91 | 58/14 | 58/15 | 1 | 24.02.26 | OM Const |  | 91 | 25/11 | 26/0 | 41 | 26.02.26 | OM Const.
92 | 58/15 | 58/16 | 1 | 24.02.26 | OM Const |  | 92 | 21/0 | 21/1 | 41 | 27.02.26 | OM Const.
93 | 58/16 | 59/0 | 1 | 24.02.26 | OM Const |  | 93 | 21/1 | 21/2 | 41 | 27.02.26 | OM Const.
94 | 59/0 | 59/1 | 1 | 24.02.26 | OM Const |  | 94 | 21/2 | 21/3 | 40 | 27.02.26 | OM Const.
95 | 59/1 | 59/2 | 1 | 24.02.26 | OM Const |  | 95 | 21/3 | 21/4 | 42 | 27.02.26 | OM Const.
96 | 59/2 | 59/3 | 1 | 24.02.26 | OM Const |  | 96 | 21/4 | 21/5 | 39 | 27.02.26 | OM Const.
97 | 59/3 | 59/4 | 1 | 24.02.26 | OM Const |  | 97 | 21/5 | 21/6 | 39 | 27.02.26 | OM Const.
98 | 59/4 | 59/5 | 1 | 24.02.26 | OM Const |  | 98 | 21/6 | 21/7 | 38 | 27.02.26 | OM Const.
99 | 59/5 | 59/6 | 1 | 24.02.26 | OM Const |  | 99 | 19/2 | 19/3 | 41 | 27.02.26 | Shiv Raj
100 | 59/6 | 60/0 | 1 | 24.02.26 | OM Const |  | 100 | 19/3 | 19/4 | 41 | 27.02.26 | Shiv Raj
101 | 60/0 | 61/0 | 1 | 24.02.26 | OM Const |  | 101 | 19/4 | 19/5 | 39 | 27.02.26 | Shiv Raj
102 | 61/0 | 61/1 | 1 | 24.02.26 | OM Const |  | 102 | 19/5 | 19/6 | 41 | 27.02.26 | Shiv Raj
103 | 61/1 | 61/2 | 1 | 24.02.26 | OM Const |  | 103 | 10/12 | 10/13 | 41 | 27.02.26 | Shiv Raj
104 | 61/2 | 62/0 | 1 | 24.02.26 | OM Const |  | 104 | 10/13 | 10/14 | 41 | 27.02.26 | Shiv Raj
105 | 62/0 | 63/0 | 1 | 24.02.26 | OM Const |  | 105 | 10/14 | 10/15 | 40 | 27.02.26 | Shiv Raj
106 | 63/0 | 63/1 | 1 | 24.02.26 | OM Const | 63/1,2 | 106 | 1/0 | 1A/0 | 9 | 22.02.26 | Bajrang Bali
107 | 63/2 | 63/3 | 1 | 25.02.26 | OM Const |  | 107 | 1A/0 | 1A/1 | 27 | 22.02.26 | Bajrang Bali
108 | 63/3 | 63/4 | 1 | 25.02.26 | OM Const |  | 108 | 1A/1 | 1A/2 | 41 | 22.02.26 | Bajrang Bali
109 | 63/4 | 63/5 | 1 | 25.02.26 | OM Const |  | 109 | 1A/2 | 1A/3 | 40 | 22.02.26 | Bajrang Bali
110 | 63/5 | 63/6 | 1 | 25.02.26 | OM Const |  | 110 | 1A/3 | 1A/4 | 40 | 22.02.26 | Bajrang Bali
111 | 63/6 | 64/0 | 1 | 25.02.26 | OM Const |  | 111 | 1A/4 | 1A/5 | 41 | 23.02.26 | Bajrang Bali
112 | 64/0 | 64/1 | 1 | 25.02.26 | OM Const |  | 112 | 1A/5 | 1A/6 | 41 | 23.02.26 | Bajrang Bali
113 | 64/1 | 64/2 | 1 | 25.02.26 | OM Const |  | 113 | 1A/6 | 1A/7 | 41 | 23.02.26 | Bajrang Bali
114 | 64/2 | 64/3 | 1 | 25.02.26 | OM Const |  | 114 | 1A/7 | 2/0 | 39 | 23.02.26 | Bajrang Bali
115 | 64/3 | 64/4 | 1 | 25.02.26 | OM Const |  | 115 | 2/0 | 2/1 | 38 | 23.02.26 | Bajrang Bali
116 | 64/4 | 64/5 | 1 | 25.02.26 | OM Const |  | 116 | 2/1 | 2/2 | 36 | 23.02.26 | Bajrang Bali
117 | 64/5 | 64/6 | 1 | 25.02.26 | OM Const |  | 117 | 2/2 | 2/3 | 36 | 23.02.26 | Bajrang Bali
118 | 64/6 | 64/7 | 1 | 25.02.26 | OM Const |  | 118 | 2/3 | 2/4 | 43 | 24.02.26 | Bajrang Bali
119 | 64/7 | 64/8 | 1 | 25.02.26 | OM Const |  | 119 | 2/4 | 2/5 | 37 | 24.02.26 | Bajrang Bali
120 | 64/8 | 64/9 | 1 | 25.02.26 | OM Const |  | 120 | 2/5 | 2/6 | 35 | 24.02.26 | Bajrang Bali
121 | 64/9 | 65/0 | 1 | 25.02.26 | OM Const |  | 121 | 2/6 | 2/7 | 29 | 24.02.26 | Bajrang Bali
122 | 65/0 | 65/1 | 1 | 25.02.26 | OM Const |  | 122 | 2/7 | 2/8 | 43 | 24.02.26 | Bajrang Bali
123 | 65/1 | 65/2 | 1 | 26.02.26 | OM Const |  | 123 | 2/8 | 2/9 | 36 | 24.02.26 | Bajrang Bali
124 | 65/2 | 65/3 | 1 | 26.02.26 | OM Const |  | 124 | 2/9 | 3/0 | 38 | 24.02.26 | Bajrang Bali
125 | 65/3 | 65/4 | 1 | 26.02.26 | OM Const |  | 125 | 3/0 | 4/0 | 23 | 24.02.26 | Bajrang Bali
126 | 65/4 | 65/5 | 1 | 26.02.26 | OM Const |  | 126 | 4/0 | 4/1 | 34 | 25.02.26 | Bajrang Bali
127 | 65/5 | 65/6 | 1 | 26.02.26 | OM Const |  | 127 | 4/1 | 4/2 | 35 | 25.02.26 | Bajrang Bali
128 | 65/6 | 65/7 | 1 | 26.02.26 | OM Const |  | 128 | 4/2 | 4/3 | 36 | 25.02.26 | Bajrang Bali
129 | 65/7 | 66/0 | 1 | 26.02.26 | OM Const |  | 129 | 4/3 | 4/4 | 35 | 25.02.26 | Bajrang Bali
130 | 66/0 | 66/1 | 1 | 26.02.26 | OM Const |  | 130 | 4/4 | 5/0 | 42 | 25.02.26 | Bajrang Bali
131 | 66/1 | 66/2 | 1 | 26.02.26 | OM Const |  | 131 | 5/0 | 6/0 | 23 | 25.02.26 | Bajrang Bali
132 | 66/2 | 66/3 | 1 | 26.02.26 | OM Const |  | 132 | 6/0 | 6/1 | 43 | 26.02.25 | Bajrang Bali
133 | 66/3 | 66/4 | 1 | 26.02.26 | OM Const |  | 133 | 6/1 | 6/2 | 39 | 26.02.26 | Bajrang Bali
134 | 66/4 | 67/0 | 1 | 26.02.26 | OM Const |  | 134 | 6/2 | 7/0 | 33 | 26.02.26 | Bajrang Bali
135 | 67/0 | 67/1 | 1 | 26.02.26 | OM Const |  | 135 | 7/0 | 8/0 | 25 | 26.02.26 | Bajrang Bali
136 | 67/1 | 68/0 | 1 | 26.02.26 | OM Const |  | 136 | 26/0 | 26/1 | 37 | 28.02.26 | OM Const.
137 | 68/0 | 68/1 | 1 | 26.02.26 | OM Const |  | 137 | 26/1 | 26/2 | 36 | 28.02.26 | OM Const.
138 | 68/1 | 68/2 | 1 | 26.02.26 | OM Const |  | 138 | 26/2 | 26/3 | 42 | 28.02.26 | OM Const.
139 | 68/2 | 68/3 | 1 | 26.02.26 | OM Const |  | 139 | 26/3 | 26/4 | 40 | 28.02.26 | OM Const.
140 | 68/3 | 68/4 | 1 | 26.02.26 | OM Const |  | 140 | 26/4 | 26/5 | 37 | 28.02.26 | OM Const.
141 | 68/4 | 68/5 | 1 | 26.02.26 | OM Const |  | 141 | 26/5 | 26/6 | 42 | 28.02.26 | OM Const.
142 | 68/5 | 68/6 | 1 | 26.02.26 | OM Const |  | 142 | 26/6 | 26/7 | 30 | 28.02.26 | OM Const.
143 | 68/6 | 69/0 | 1 | 26.02.26 | OM Const |  | 143 | 26/7 | 27/0 | 42 | 28.02.26 | OM Const.
144 | 69/0 | 69/1 | 1 | 27.02.26 | OM Const |  | 144 | 10/15 | 10/16 | 39 | 28.02.26 | Shiv Raj
145 | 69/1 | 69/2 | 1 | 27.02.26 | OM Const |  | 145 | 10/16 | 10/17 | 36 | 28.02.26 | Shiv Raj
146 | 69/2 | 69/3 | 1 | 27.02.26 | OM Const |  | 146 | 10/17 | 10/18 | 39 | 28.02.26 | Shiv Raj
147 | 69/3 | 69/4 | 1 | 27.02.26 | OM Const |  | 147 | 10/18 | 10/19 | 30 | 28.02.26 | Shiv Raj
148 | 69/4 | 69/5 | 1 | 27.02.26 | OM Const |  | 148 | 10/19 | 10/20 | 47 | 28.02.26 | Shiv Raj
149 | 69/5 | 69/6 | 1 | 27.02.26 | OM Const |  | 149 | 10/20 | 10/21 | 40 | 28.02.26 | Shiv Raj
150 | 69/6 | 69/7 | 1 | 27.02.26 | OM Const |  | 150 | 10/21 | 10/22 | 39 | 28.02.26 | Shiv Raj
151 | 69/7 | 69/8 | 1 | 27.02.26 | OM Const |  | 151 | 10/22 | 10/23 | 37 | 28.02.26 | Shiv Raj
152 | 69/8 | 69/9 | 1 | 27.02.26 | OM Const |  | 152 | 10/23 | 11/0 | 45 | 28.02.26 | Shiv Raj
153 | 69/9 | 70/0 | 1 | 27.02.26 | OM Const |  | 153 | 11/0 | 11/1 | 42 | 28.02.26 | Shiv Raj
154 | 70/0 | 71/0 | 1 | 27.02.26 | OM Const |  | 154 | 10/0 | 10/1 | 41 | 01.03.26 | Shiv Raj
155 | 71/0 | 71/1 | 1 | 27.02.26 | OM Const |  | 155 | 10/1 | 10/2 | 41 | 01.03.26 | Shiv Raj
156 | 71/1 | 71/2 | 1 | 27.02.26 | OM Const |  | 156 | 10/2 | 10/3 | 41 | 01.03.26 | Shiv Raj
157 | 71/2 | 71/3 | 1 | 27.02.26 | OM Const |  | 157 | 10/3 | 10/4 | 41 | 01.03.26 | Shiv Raj
158 | 71/3 | 71/4 | 1 | 27.02.26 | OM Const |  | 158 | 10/4 | 10/5 | 41 | 01.03.26 | Shiv Raj
159 | 71/4 | 71/5 | 1 | 27.02.26 | OM Const |  | 159 | 10/5 | 10/6 | 41 | 01.03.26 | Shiv Raj
160 | 71/5 | 72/0 | 1 | 27.02.26 | OM Const |  | 160 | 10/6 | 10/7 | 41 | 01.03.26 | Shiv Raj
161 | 72/0 | 72/1 | 1 | 27.02.26 | OM Const |  | 161 | 10/7 | 10/8 | 41 | 01.03.26 | Shiv Raj
162 | 72/1 | 72/2 | 1 | 27.02.26 | OM Const |  | 162 | 10/8 | 10/9 | 40 | 01.03.26 | Shiv Raj
163 | 72/2 | 72/3 | 1 | 27.02.26 | OM Const |  | 163 | 10/9 | 10/10 | 42 | 01.03.26 | Shiv Raj
164 | 72/3 | 72/4 | 1 | 27.02.26 | OM Const |  | 164 | 10/10 | 10/11 | 40 | 01.03.26 | Shiv Raj
165 | 72/4 | 72/5 | 1 | 27.02.26 | OM Const |  | 165 | 10/11 | 10/12 | 39 | 01.03.26 | Shiv Raj
166 | 72/5 | 72/6 | 1 | 27.02.26 | OM Const |  | 166 | 27/0 | 27/1 | 36 | 01.03.26 | OM Const.
167 | 72/6 | 72/7 | 1 | 27.02.26 | OM Const |  | 167 | 27/1 | 27/2 | 43 | 01.03.26 | OM Const.
168 | 72/7 | 73/0 | 1 | 27.02.26 | OM Const |  | 168 | 27/2 | 27/3 | 32 | 01.03.26 | OM Const.
169 | 55/10 | 55/11 | 1 | 28.02.26 | OM Const |  | 169 | 27/3 | 27/4 | 40 | 01.03.26 | OM Const.
170 | 55/11 | 56/0 | 1 | 28.02.26 | OM Const |  | 170 | 28/0 | 28/1 | 36 | 01.03.26 | OM Const.
171 | 35/9 | 36/0 | 1 | 28.02.26 | OM Const |  | 171 | 28/1 | 28/2 | 45 | 01.03.26 | OM Const.
172 | 36/0 | 37/0 | 1 | 28.02.26 | OM Const |  | 172 | 28/2 | 28/3 | 37 | 01.03.26 | OM Const.
173 | 37/0 | 37/1 | 1 | 28.02.26 | OM Const |  | 173 | 28/3 | 28/4 | 44 | 01.03.26 | OM Const.
174 | 63/1 | 63/2 | 1 | 10.03.26 | OM Const |  | 174 | 28/4 | 28/5 | 38 | 01.03.26 | OM Const.
175 | 10/0 | 10/1 | 1 | 11.03.26 | OM Const |  | 175 | 28/5 | 28/6 | 41 | 01.03.26 | OM Const.
176 | 8/12 | 9/0 | 1 | 12.03.26 | OM Const |  | 176 | 28/6 | 28/7 | 33 | 01.03.26 | OM Const.
177 | 9/0 | 10/0 | 1 | 12.03.26 | OM Const |  | 177 | 28/7 | 28/8 | 32 | 01.03.26 | OM Const.
[7 empty] | 178 | 28/8 | 28/9 | 44 | 01.03.26 | OM Const.
[7 empty] | 179 | 32/2 | 32/3 | 40 | 12.03.26 | OM Const.
[7 empty] | 180 | 32/3 | 32/4 | 42 | 12.03.26 | OM Const.
[7 empty] | 181 | 32/4 | 32/5 | 40 | 12.03.26 | OM Const.
[7 empty] | 182 | 32/5 | 32/6 | 42 | 12.03.26 | OM Const.
[7 empty] | 183 | 32/6 | 32/7 | 39 | 12.03.26 | OM Const.
[7 empty] | 184 | 30/0 | 30/1 | 25 | 13.03.26 | OM Const.
[7 empty] | 185 | 30/1 | 30/2 | 33 | 13.03.26 | OM Const.
[7 empty] | 186 | 30/2 | 30/3 | 36 | 13.03.26 | OM Const.
[7 empty] | 187 | 30/3 | 31/0 | 36 | 13.03.26 | OM Const.
[7 empty] | 188 | 31/0 | 31/1 | 30 | 13.03.26 | OM Const.
[7 empty] | 189 | 31/1 | 31/2 | 38 | 13.03.26 | OM Const.
[7 empty] | 190 | 31/2 | 31/3 | 35 | 13.03.26 | OM Const.
[7 empty] | 191 | 31/3 | 31/4 | 29 | 13.03.26 | OM Const.
[7 empty] | 192 | 31/4 | 32/0 | 30 | 13.03.26 | OM Const.
[7 empty] | 193 | 32/0 | 32/1 | 39 | 13.03.26 | OM Const.
[7 empty] | 194 | 32/1 | 32/2 | 42 | 13.03.26 | OM Const.
[7 empty] | 195 | 32/7 | 32/8 | 42 | 13.03.26 | OM Const.
[7 empty] | 196 | 32/8 | 33/0 | 39 | 13.03.26 | OM Const.
[7 empty] | 197 | 29/6 | 29/7 | 40 | 14.03.26 | OM Const.
[7 empty] | 198 | 29/7 | 29/8 | 42 | 14.03.26 | OM Const.
[7 empty] | 199 | 29/8 | 29/9 | 38 | 14.03.26 | OM Const.
[7 empty] | 200 | 29/9 | 29/10 | 38 | 14.03.26 | OM Const.
[7 empty] | 201 | 29/10 | 30/0 | 38 | 14.03.26 | OM Const.
[7 empty] | 202 | 8/1 | 8/2 | 41 | 16.03.26 | OM Const.
[7 empty] | 203 | 8/2 | 8/3 | 40 | 16.03.26 | OM Const.
[7 empty] | 204 | 8/3 | 8/4 | 42 | 16.03.26 | OM Const.
[7 empty] | 205 | 8/4 | 8/5 | 40 | 16.03.26 | OM Const.
[7 empty] | 206 | 8/5 | 8/6 | 38 | 16.03.26 | OM Const.
[7 empty] | 207 | 8/6 | 8/7 | 40 | 16.03.26 | OM Const.
[7 empty] | 208 | 8/7 | 8/8 | 42 | 16.03.26 | OM Const.
[7 empty] | 209 | 8/8 | 8/9 | 36 | 16.03.26 | OM Const.
[7 empty] | 210 | 8/9 | 8/10 | 40 | 16.03.26 | OM Const.
[7 empty] | 211 | 8/10 | 8/11 | 42 | 16.03.26 | OM Const.
[7 empty] | 212 | 8/11 | 8/12 | 36 | 16.03.26 | OM Const.
| Total Complete |  | 177 |  |  |  |  | Total Complete |  | 8102
|  |  | 0 | [6 empty] | 1738

## Avaition Light & Painting
Name of Line:- 765 KV Fatehgarh-3 Beawer Transmission Line, Package G
Name of Line:- 765 KV Fatehgarh-3 Beawer Transmission Line, Package G
Aviation Lights & Painting of towers
Sl No | Twr No. | Tower Type | Painting height from Top of Tower in mtrs | Complete Date | Contractor | Sl No | Twr No. | Tower Type | Obstruction Light | Obstruction Light | Completion Date | Contractor
[9 empty] | 1 medium intensity+ 2 low intensity | 1 medium intensity+ 4 low intensity
1 | 36/0 | DD25+60 | 50.9 | 19.02.26 | Om Const | 1 | 45/0 | DD25+60 |  | 1 | 25.02.26 | Om Const
2 | 37/0 | DD25+60 | 50.9 | 19.02.26 | Om Const | 2 | 46/0 | DD25+60 |  | 1 | 25.02.26 | Om Const
3 | 45/0 | DD25+60 | 50.9 | 20.02.26 | Om Const | 3 | 36/0 | DD25+60 | 1 |  | 26.02.26 | Om Const
4 | 46/0 | DD25+60 | 50.9 | 21.02.26 | Om Const | 4 | 37/0 | DD25+60 | 1 |  | 26.02.26 | Om Const
5 | 63/4 | DA+0 | 26.86 | 25.02.26 | Om Const | 5 | 57/3 | DA+0 | 1 |  | 27.02.26 | Om Const
6 | 59/4 | DA+0 | 26.86 | 26.02.26 | Om Const | 6 | 57/4 | DA+0 | 1 |  | 27.02.26 | Om Const
7 | 59/5 | DA+0 | 26.86 | 26.02.26 | Om Const | 7 | 57/5 | DA+3 | 1 |  | 27.02.26 | Om Const
8 | 59/6 | DA+0 | 26.86 | 27.02.26 | Om Const | 8 | 57/6 | DB+0 | 1 |  | 27.02.26 | Om Const
9 | 60/0 | DC+3 | 28.7 | 27.02.26 | Om Const | 9 | 57/0 | DB+0 | 1 |  | 28.02.26 | Om Const
10 | 72/1 | DA+0 | 26.86 | 27.02.26 | Om Const | 10 | 57/1 | DA+0 | 1 |  | 28.02.26 | Om Const
11 | 72/2 | DA+0 | 26.86 | 27.02.26 | Om Const | 11 | 57/2 | DA+3 | 1 |  | 28.02.26 | Om Const
12 | 72/3 | DA+0 | 26.86 | 27.02.26 | Om Const | 12 | 56/8 | DA+3 | 1 |  | 28.02.26 | Om Const
13 | 72/4 | DA+0 | 26.86 | 27.02.26 | Om Const | 13 | 56/9 | DA+3 | 1 |  | 28.02.26 | Om Const
14 | 72/5 | DA+0 | 26.86 | 27.02.26 | Om Const | 14 | 57/9 | DA+0 | 1 |  | 01.03.26 | Om Const
15 | 72/6 | DA+0 | 26.86 | 27.02.26 | Om Const | 15 | 57/10 | DA+0 | 1 |  | 01.03.26 | Om Const
16 | 73/0 | DA+0 | 26.86 | 27.02.26 | Om Const | 16 | 57/11 | DA+0 | 1 |  | 01.03.26 | Om Const
17 | 72/0 | DB+0 | 25.5 | 28.02.26 | Om Const | 17 | 57/12 | DA+3 | 1 |  | 01.03.26 | Om Const
18 | 71/1 | DA+0 | 26.86 | 28.02.26 | Om Const | 18 | 57/13 | DA+0 | 1 |  | 01.03.26 | Om Const
19 | 71/2 | DA+0 | 26.86 | 28.02.26 | Om Const | 19 | 58/0 | DC+0 | 1 |  | 01.03.26 | Om Const
20 | 71/3 | DA+0 | 26.86 | 28.02.26 | Om Const | 20 | 61/0 | DB+6 | 1 |  | 01.03.26 | Om Const
21 | 71/4 | DA+0 | 26.86 | 28.02.26 | Om Const | 21 | 61/1 | DA+0 | 1 |  | 01.03.26 | Om Const
22 | 71/5 | DA+0 | 26.86 | 28.02.26 | Om Const | 22 | 61/2 | DA+0 | 1 |  | 01.03.26 | Om Const
23 | 70/0 | DD+0 | 25.9 | 28.02.26 | Om Const | 23 | 63/1 | DA+6 | 1 |  | 01.03.26 | Om Const
24 | 69/9 | DA+0 | 26.86 | 28.02.26 | Om Const | 24 | 63/3 | DA+3 | 1 |  | 01.03.26 | Om Const
25 | 69/8 | DA+0 | 26.86 | 28.02.26 | Om Const | 25 | 64/1 | DA+6 | 1 |  | 01.03.26 | Om Const
26 | 61/0 | DB+6 | 31.5 | 28.02.26 | Om Const | 26 | 64/2 | DA+0 | 1 |  | 01.03.26 | Om Const
27 | 67/0 | DB+9 | 34.5 | 01.03.26 | Om Const | 27 | 63/0 | DD+0 | 1 |  | 01.03.26 | Om Const
28 | 67/1 | DD+0 | 25.9 | 01.03.26 | Om Const | 28 | 58/1 | DA+0 | 1 |  | 02.03.26 | Om Const
29 | 66/3 | DA+3 | 29.86 | 01.03.26 | Om Const | 29 | 58/2 | DA+0 | 1 |  | 02.03.26 | Om Const
30 | 66/4 | DA+3 | 29.86 | 01.03.26 | Om Const | 30 | 58/3 | DA+3 | 1 |  | 02.03.26 | Om Const
31 | 61/1 | DA+0 | 26.86 | 01.03.26 | Om Const | 31 | 58/4 | DA+0 | 1 |  | 02.03.26 | Om Const
32 | 61/2 | DA+0 | 26.86 | 01.03.26 | Om Const | 32 | 58/5 | DA+3 | 1 |  | 02.03.26 | Om Const
33 | 65/1 | DA+3 | 29.86 | 02.03.26 | Om Const | 33 | 58/6 | DA+3 | 1 |  | 02.03.26 | Om Const
34 | 65/2 | DA+0 | 26.86 | 02.03.26 | Om Const | 34 | 63/4 | DA+0 | 1 |  | 02.03.26 | Om Const
35 | 65/3 | DA+0 | 26.86 | 02.03.26 | Om Const | 35 | 63/5 | DA+3 | 1 |  | 02.03.26 | Om Const
36 | 65/4 | DA+0 | 26.86 | 02.03.26 | Om Const | 36 | 63/6 | DA+3 | 1 |  | 02.03.26 | Om Const
37 | 63/0 | DD+0 | 25.9 | 02.03.26 | Om Const | 37 | 64/0 | DB+0 | 1 |  | 02.03.26 | Om Const
38 | 63/1 | DA+6 | 32.86 | 02.03.26 | Om Const | 38 | 64/3 | DA+0 | 1 |  | 02.03.26 | Om Const
39 | 64/0 | DB+0 | 25.5 | 07.03.26 | Om Const | 39 | 58/7 | DB+0 | 1 |  | 03.03.26 | Om Const
40 | 63/6 | DA+3 | 29.86 | 07.03.26 | Om Const | 40 | 58/8 | DA+0 | 1 |  | 03.03.26 | Om Const
41 | 64/1 | DA+6 | 32.86 | 08.03.26 | Om Const | 41 | 58/9 | DA+0 | 1 |  | 03.03.26 | Om Const
42 | 64/2 | DA+0 | 26.86 | 08.03.26 | Om Const | 42 | 58/10 | DA+3 | 1 |  | 03.03.26 | Om Const
43 | 64/3 | DA+0 | 26.86 | 09.03.26 | Om Const | 43 | 58/11 | DA+3 | 1 |  | 03.03.26 | Om Const
44 | 64/4 | DA+3 | 29.86 | 09.03.26 | Om Const | 44 | 58/12 | DA+0 | 1 |  | 03.03.26 | Om Const
45 | 64/5 | DA+3 | 29.86 | 10.03.26 | Om Const | 45 | 58/13 | DA+0 | 1 |  | 04.03.26 | Om Const
46 | 64/6 | DA+3 | 29.86 | 10.03.26 | Om Const | 46 | 58/14 | DA+0 | 1 |  | 04.03.26 | Om Const
47 | 64/7 | DA+3 | 29.86 | 11.03.26 | Om Const | 47 | 58/15 | DA+3 | 1 |  | 04.03.26 | Om Const
48 | 64/8 | DA+0 | 26.86 | 11.03.26 | Om Const | 48 | 58/16 | DA+0 | 1 |  | 04.03.26 | Om Const
49 | 63/3 | DA+3 | 29.86 | 11.03.26 | Om Const | 49 | 59/0 | DB+0 | 1 |  | 04.03.26 | Om Const
50 | 64/9 | DA+0 | 26.86 | 12.03.26 | Om Const | 50 | 59/1 | DA+0 | 1 |  | 04.03.26 | Om Const
51 | 65/0 | DB+3 | 28.5 | 12.03.26 | Om Const | 51 | 59/2 | DA+0 | 1 |  | 05.03.26 | Om Const
52 | 65/5 | DA+0 | 26.86 | 14.03.26 | Om Const | 52 | 59/3 | DA+0 | 1 |  | 05.03.26 | Om Const
53 | 65/6 | DA+0 | 26.86 | 14.03.26 | Om Const | 53 | 59/4 | DA+0 | 1 |  | 05.03.26 | Om Const
54 | 65/7 | DA+0 | 26.86 | 14.03.26 | Om Const | 54 | 59/5 | DA+0 | 1 |  | 05.03.26 | Om Const
55 | 10/0 | DD+18 | 43.9 | 14.03.26 | Om Const | 55 | 59/6 | DA+0 | 1 |  | 05.03.26 | Om Const
56 | 9/0 | DD+18 | 43.9 | 15.03.26 | Om Const | 56 | 60/0 | DC+3 | 1 |  | 05.03.26 | Om Const
57 | 66/1 | DA+3 | 29.86 | 15.03.26 | Om Const | 57 | 64/4 | DA+3 | 1 |  | 06.03.26 | Om Const
58 | 66/2 | DA+0 | 26.86 | 15.03.26 | Om Const | 58 | 64/5 | DA+3 | 1 |  | 06.03.26 | Om Const
59 | 68/1 | DA+3 | 29.86 | 15.03.26 | Om Const | 59 | 64/6 | DA+3 | 1 |  | 06.03.26 | Om Const
60 | 68/2 | DA+3 | 29.86 | 16.03.26 | Om Const | 60 | 64/8 | DA+0 | 1 |  | 06.03.26 | Om Const
61 | 68/3 | DA+0 | 26.86 | 16.03.26 | Om Const | 61 | 65/0 | DB+3 | 1 |  | 06.03.26 | Om Const
62 | 68/4 | DA+3 | 29.86 | 16.03.26 | Om Const | 62 | 65/1 | DA+3 | 1 |  | 06.03.26 | Om Const
[6 empty] | 63 | 65/2 | DA+0 | 1 |  | 06.03.26 | Om Const
[6 empty] | 64 | 65/3 | DA+0 | 1 |  | 06.03.26 | Om Const
[6 empty] | 65 | 65/5 | DA+0 | 1 |  | 06.03.26 | Om Const
[6 empty] | 66 | 65/6 | DA+0 | 1 |  | 06.03.26 | Om Const
[6 empty] | 67 | 65/7 | DA+0 | 1 |  | 06.03.26 | Om Const
[6 empty] | 68 | 56/5 | DA+0 | 1 |  | 06.03.26 | Om Const
[6 empty] | 69 | 56/6 | DA+3 | 1 |  | 06.03.26 | Om Const
[6 empty] | 70 | 56/7 | DA+3 | 1 |  | 06.03.26 | Om Const
[6 empty] | 71 | 71/0 | DD+0 | 1 |  | 07.03.26 | Om Const
[6 empty] | 72 | 71/1 | DA+0 | 1 |  | 07.03.26 | Om Const
[6 empty] | 73 | 71/2 | DA+0 | 1 |  | 07.03.26 | Om Const
[6 empty] | 74 | 71/3 | DA+0 | 1 |  | 07.03.26 | Om Const
[6 empty] | 75 | 71/4 | DA+0 | 1 |  | 07.03.26 | Om Const
[6 empty] | 76 | 71/5 | DA+0 | 1 |  | 07.03.26 | Om Const
[6 empty] | 77 | 66/1 | DA+3 | 1 |  | 07.03.26 | Om Const
[6 empty] | 78 | 66/2 | DA+0 | 1 |  | 07.03.26 | Om Const
[6 empty] | 79 | 66/3 | DA+3 | 1 |  | 07.03.26 | Om Const
[6 empty] | 80 | 66/4 | DA+3 | 1 |  | 07.03.26 | Om Const
[6 empty] | 81 | 67/0 | DD+0 | 1 |  | 07.03.26 | Om Const
[6 empty] | 82 | 67/1 | DB+9 | 1 |  | 07.03.26 | Om Const | 68/0
[6 empty] | 83 | 68/1 | DA+3 | 1 |  | 07.03.26 | Om Const
[6 empty] | 84 | 68/2 | DA+0 | 1 |  | 07.03.26 | Om Const
[6 empty] | 85 | 68/3 | DA+3 | 1 |  | 07.03.26 | Om Const
[6 empty] | 86 | 68/4 | DA+3 | 1 |  | 07.03.26 | Om Const
[6 empty] | 87 | 72/0 | DB+0 | 1 |  | 08.03.26 | Om Const
[6 empty] | 88 | 72/1 | DA+0 | 1 |  | 08.03.26 | Om Const
[6 empty] | 89 | 72/2 | DA+0 | 1 |  | 08.03.26 | Om Const
[6 empty] | 90 | 72/3 | DA+0 | 1 |  | 08.03.26 | Om Const
[6 empty] | 91 | 72/4 | DA+0 | 1 |  | 08.03.26 | Om Const
[6 empty] | 92 | 72/5 | DA+0 | 1 |  | 09.03.26 | Om Const
[6 empty] | 93 | 72/6 | DA+0 | 1 |  | 09.03.26 | Om Const
[6 empty] | 94 | 72/7 | DB+9 | 1 |  | 09.03.26 | Om Const
[6 empty] | 95 | 73/0 | DD+9 | 1 |  | 09.03.26 | Om Const
[6 empty] | 96 | 70/0 | DD+0 | 1 |  | 09.03.26 | Om Const
[6 empty] | 97 | 69/9 | DA+0 | 1 |  | 09.03.26 | Om Const
[6 empty] | 98 | 69/8 | DA+0 | 1 |  | 10.03.26 | Om Const
[6 empty] | 99 | 69/7 | DA+0 | 1 |  | 10.03.26 | Om Const
[6 empty] | 100 | 68/5 | DA+3 | 1 |  | 10.03.26 | Om Const
[6 empty] | 101 | 68/6 | DA+3 | 1 |  | 10.03.26 | Om Const
[6 empty] | 102 | 69/0 | DB+0 | 1 |  | 10.03.26 | Om Const
[6 empty] | 103 | 69/1 | DA+0 | 1 |  | 10.03.26 | Om Const
[6 empty] | 104 | 69/2 | DA+0 | 1 |  | 10.03.26 | Om Const
[6 empty] | 105 | 69/3 | DA+0 | 1 |  | 10.03.26 | Om Const
[6 empty] | 106 | 69/4 | DA+0 | 1 |  | 10.03.26 | Om Const
[6 empty] | 107 | 69/5 | DA+0 | 1 |  | 10.03.26 | Om Const
[6 empty] | 108 | 69/6 | DA+0 | 1 |  | 10.03.26 | Om Const
[6 empty] | 109 | 64/7 | DA+3 | 1 |  | 10.03.26 | Om Const
[6 empty] | 110 | 66/0 | DD+0 | 1 |  | 11.03.26 | Om Const
[6 empty] | 111 | 65/4 | DA+0 | 1 |  | 11.03.26 | Om Const
[6 empty] | 112 | 64/9 | DA+0 | 1 |  | 11.03.26 | Om Const
[6 empty] | 113 | 10/0 | DD+18 | 1 |  | 11.03.26 | Om Const
[6 empty] | 114 | 63/2 | DA+0 | 1 |  | 11.03.26 | Om Const
[6 empty] | 115 | 9/0 | DD+18 | 1 |  | 12.03.26 | Om Const
| Total Complete |  | 62 |  |  |  | Total Complete |  | 113 | 2
|  |  | 17 | [5 empty] | 4

## Visual Chart PKG-G
PKG-G, Section-II
Executing Agency |  | International Limited
Project |  | Fatehgarh-3-Beawar 765kV D/C (2nd) Transmission Line Section 1 & 2 (Hexa AL59 Zebra Conductor)
LEGEND: | [16 empty] | Summary | [7 empty] | 2026-03-16
[13 empty] | Tree Felling Done. Front Clear For Stringing |  |  |  | SR. NO. |  | ACTIVITY |  |  | UNIT | As per Tower Schedule |  | TOTAL COMPLETED |  | BALANCE |  | Earthng | Foundation |  |  | Erection
|  |  |  | Stringing WIP |  |  | STRINGING COMPLETED
[6 empty] | Loc No | P: Prvate Loc
[12 empty] | EREC. U/P | [17 empty] | Total | Fdn Complete | Balance | Total | Complete | Balance
|  |  | EREC. COMP. |  |  |  | SPAN |  | SPAN | [7 empty] | 1 |  | Foundation |  |  | Nos. | 521 |  | 521 |  | 0
FDN. COMP.
|  | Tack Welding | [14 empty] | 2 |  | Earthing |  |  | Nos. | 521 |  | 521 |  | 0
|  |  | LE | Leg Extension(A,B,C,D) |  |  | Earthing Comp. |  | PIT EXCAV. COMP. |  |  | FTR done |  |  |  |  | 3 |  | Erection |  |  | Nos. | 521 |  | 521 |  | 0
|  |  | RC | Raise Chimney (A,B,C,D)
[7 empty] | FTR WIP | [9 empty] | 4 |  | Tackwelding |  |  | Nos. | 521 |  | 509 |  | 12
[17 empty] | 5 |  | Stringing (PayingOut) |  |  | Km. | 202.13 |  | 197.5917 |  | 4.5383
[17 empty] | 6 |  | Stringing (Final Sag) |  |  | Km. | 202.13 |  | 197.5917 |  | 4.5383
|  | NH/SH Xing |  | RAILWAY |  | Powerline Xing |  | 11/33 KV X-ING |  |  | RIVER X-ING |  |  | METAL ROADS |  |  | 7 |  | OPGW |  |  | Km. | 202.13 |  | 202.1307 |  | -0.000653
[21 empty] | 28.7.25 |  | 14.7.25 |  | 2025-03-09 |  | 0 | [6 empty] | 4
[19 empty] | Gty |  | 1/0 |  | 1A/0 |  | 1A/1 |  | 1A/2
[18 empty] | F3BTL | Start
[19 empty] | WELD | 122.933 | 26.2.25 | 100.001 | 24.1.25 | 276.803 | 14.2.25 | 424.392 | 16.2.25 | 0.92413 | 4 | 4 | 4
[21 empty] | DRY |  | DFR |  | DRY |  | DRY
[21 empty] | Done |  | Done |  | Done |  | Done
[21 empty] | DE+0 |  | DD60+0 |  | DA+0 |  | DA+6
[21 empty] | 0,0,0,0 |  |  |  | 0,0,2,1
| 15.6.25 |  | 5.6.25 |  | 27.05.25 |  | 20.6.25 |  | 7.7.25 |  | 27.08.25 |  | 31.08.25 |  | 8.9.25 |  | 24.08.25 |  | 30.08.25 |  | 31.7.25 |  | 29.08.25 |  | 22.08.25 |  | 10.7.25 | [6 empty] | 14
| 1A/3 |  | 1A/4 |  | 1A/5 |  | 1A/6 |  | 1A/7 |  | 2/0 |  | 2/1 |  | 2/2 |  | 2/3 |  | 2/4 |  | 2/5 |  | 2/6 |  | 2/7 |  | 2/8
413.011 | 30.1.25 | 414.527 | 23.2.25 | 421.193 | 12.2.25 | 418.77 | 27.2.25 | 418.233 | 08.5.25 | 400.185 | 5.2.25 | 385.552 | 1.1.25 | 367.841 | 19.12.24 | 369.636 | 10.12.25 | 436.76 | 20.11.24 | 378.497 | 8.12.24 | 363.579 | 2.1.24 | 298.788 | 31.3.24 | 436.305 | 03.6.25 | 5.5229
| Sandy |  | DRY |  | Sandy |  | Sandy |  | Sandy |  | DRY |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
RC | DA+0 |  | DA+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+0 |  |  | 14
| 0,0,1,0 |  | 1,0,0,0 |  | 0,1,0,0 | [5 empty] | 1,1,0,2 |  |  |  | 0,0,1,1 |  | 1,1,0,0 |  |  |  | 0,1,1,0 |  | 0,2,0,0 |  | 0,0,1,0
| 3.7.25 |  | 22.11.25 |  | 12.8.25 |  | 16.8.25 |  | 21.10.25 |  | 28.08.25 |  | 19.08.25 |  | 28.10.25 |  | 13.9.25 |  | 23.9.25 |  | 5.9.25 |  | 21.10.25 |  | 13.10.25 |  | 28.10.25 | [6 empty] | 14
| 2/9 |  | 3/0 |  | 4/0 |  | 4/1 |  | 4/2 |  | 4/3 |  | 4/4 |  | 5/0 |  | 6/0 |  | 6/1 |  | 6/2 |  | 7/0 |  | 8/0 |  | 8/1
371.552 | 12.3.25 | 409.585 | 25.5.25 | 226.687 | 12.4.25 | 348.463 | 28.4.25 | 359.096 | 27.09.25 | 373.733 | 21.5.25 | 355.774 | 27.6.25 | 429.586 | 12.6.25 | 237.146 | 31.7.25 | 438.821 | 10.12.14 | 398.456 | 13.3.24 | 337.532 | 21.09.25 | 261.049 | 23.7.25 | 397.286 | 25.4.24 | 4.9448
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DFR |  | DFR |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DD60+3 |  | DD60+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+9 |  | DB2+9 |  | DA+0 |  | DA+3 |  | DB1+0 |  | DB1+0 |  | DA+3 |  |  | 14
RC | [14 empty] | 2,2,2,2 |  | 2,2,2,2 |  | 1,0,0,0
| 10.9.25 |  | 12.11.25 |  | 28.08.25 |  | 11.9.25 |  | 2025-01-06 |  | 13.02.26 |  | 17.02.26 |  | 27.5.25 |  | 6.7.25 |  | 15.7.25 |  | 5.8.25 |  | 25.10.25 |  | 30.7.25 |  | 03.10.25 | [6 empty] | 14
| 8/2 |  | 8/3 |  | 8/4 |  | 8/5 |  | 8/6 |  | 8/7 |  | 8/8 |  | 8/9 |  | 8/10 |  | 8/11 |  | 8/12 |  | 9/0 |  | 10/0 |  | 10/1
422.812 | 5.7.25 | 407.941 | 13.10.25 | 425.955 | 31.7.25 | 413.13 | 28.7.25 | 391.786 | 12.4.24 | 411.744 | 5.5.24 | 428.276 | 6.4.24 | 373.975 | 4.1.25 | 405.011 | 12.3.24 | 427.02 | 14.3.24 | 366.257 | 17.7.25 | 440.154 | 17.7.25 | 233.899 | 10.6.25 | 418.696 | 31.7.25 | 5.5667
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DFR |  | DFR |  | DFR |  | DFR |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DD60+18 |  | DD60+18 |  | DA+3 |  |  | 14
RC |  |  | 0,0,0,1 |  | 1,1,1,2
| 15.02.26 |  | 2024-09-11 |  | 2024-09-16 |  | 2024-09-20 |  | 2024-09-25 |  | 2024-10-04 |  | 2024-11-01 |  | 2024-10-11 |  | 11.17.24 |  | 29.11.24 |  | 10.11.24 |  | 21.11.24 |  | 2024-09-26 |  | 11.10.25 | [6 empty] | 14
| 10/2 |  | 10/3 |  | 10/4 |  | 10/5 |  | 10/6 |  | 10/7 |  | 10/8 |  | 10/9 |  | 10/10 |  | 10/11 |  | 10/12 |  | 10/13 |  | 10/14 |  | 10/15
418.839 | 7.2.2026 | 419.918 | 5.5.2024 | 418.259 | 7.31.2024 | 419.165 | 5.10.2024 | 419.958 | 4.24.2024 | 419.411 | 3.30.2024 | 419.735 | 8.26.2024 | 406.152 | 5.2.2024 | 427.15 | 4.14.2024 | 407.717 | 8.31.2024 | 400.025 | 3.6.2024 | 420.511 | 4.28.2024 | 416.601 | 4.10.2024 | 414.659 | 14.09.25 | 5.8281
| DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DB1+3 |  | DA+3 |  | DA+3 |  | DA+3 |  |  | 14
| 29.09.25 |  | 20.9.25 |  | 2024-10-19 |  | 2024-09-19 |  | 2024-12-24 |  | 2024-10-04 |  | 02.12.25 |  | 24.11.25 |  | 26.11.25 |  | 5.12.25 |  | 17.11.25 |  | 18.10.25 |  | 24.7.25 |  | 10.6.24 | [6 empty] | 14
| 10/16 |  | 10/17 |  | 10/18 |  | 10/19 |  | 10/20 |  | 10/21 |  | 10/22 |  | 10/23 |  | 11/0 |  | 11/1 |  | 11/2 |  | 11/3 |  | 11/4 |  | 11/5
399.433 | 02.09.25 | 371.529 | 7.16.2024 | 398.234 | 7.16.2024 | 307.655 | 6.20.2024 | 479.821 | 6.29.2024 | 413.628 | 7.4.2024 | 399.619 | 9.22.2024 | 378.191 | 04.10.25 | 461.606 | 5.9.25 | 434.185 | 18.8.25 | 387.892 | 27.6.25 | 446.374 | 10.6.25 | 393.392 | 7.26.2024 | 440.993 | 8.11.2024 | 5.7126
| DRY |  | DRY |  | DFR |  | DRY |  | DFR |  | DFR |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | DFR |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DA+3 |  | DA+0 |  | DA+9 |  | DB1+6 |  | DA+0 |  | DA+0 |  | DA+9 |  | DB1+0 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+6 |  | DA+3 |  |  | 14
[13 empty] | 1,4,0,0 |  | 2,6,1,1 |  | 2,4,0,3 |  | 0,2,0,0 |  | 0,0,2,0 | [5 empty] | 1,1,0,1
| 2024-11-10 |  | 2024-10-15 |  | 2024-10-17 |  | 2024-10-28 |  | 04.12.25 |  | 2024-12-24 |  | 2024-12-22 |  | 2024-12-30 |  | 2024-11-17 |  | 2024-11-23 |  | 6.7.25 |  | 2024-12-24 |  | 2024-11-25 |  | 10.12.25 | [6 empty] | 14
| 11/6 |  | 11/7 |  | 11/8 |  | 11/9 |  | 11/10 |  | 11/11 |  | 11/12 |  | 11/13 |  | 11/14 |  | 11/15 |  | 12/0 |  | 13/0 |  | 13/1 |  | 13/2
398.805 | 9.20.2024 | 431.127 | 8.11.2024 | 404.624 | 8.31.2024 | 401.472 | 9.6.2024 | 373.463 | 8.4.2024 | 420.378 | 7.27.2024 | 405.125 | 8.31.2024 | 334.987 | 10.7.2024 | 401.645 | 7.3.2024 | 349.723 | 8.28.2024 | 367.902 | 24.11.24 | 216.75 | 15.10.24 | 398.236 | 9.21.2024 | 377.076 | 9.15.2024 | 5.2813
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | Sandy |  | Sandy |  | Sandy |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | Sandy |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DD60+0 |  | DD60+0 |  | DA+3 |  | DA+3 |  |  | 14
[11 empty] | 0,1,0,0 |  | 2,3,1,4 |  | 0,2,4,1
| 15.12.25 |  | 5.12.25 |  | 24.7.25 |  | 17.7.25 |  | 2024-11-04 |  | 10.9.25 |  | 2024-09-08 |  | 2024-09-20 |  | 29.11.25 |  | 2024-10-16 |  | 2024-11-02 |  | 2024-09-21 |  | 2024-09-05 |  | 2024-09-27 | [6 empty] | 14
| 13/3 |  | 13/4 |  | 14/0 |  | 14/1 |  | 14/2 |  | 14/3 |  | 14/4 |  | 14/5 |  | 14/6 |  | 15/0 |  | 15/1 |  | 15/2 |  | 15/3 |  | 15/4
424.121 | 11.5.2024 | 378.671 | 5.24.2024 | 350.406 | 9.11.2024 | 399.236 | 5.28.2024 | 392.209 | 6.1.2024 | 384.269 | 6.4.2024 | 374.119 | 6.13.2024 | 374.485 | 6.22.2024 | 390.158 | 25.11.24 | 309.712 | 6.24.2024 | 461.976 | 6.30.2024 | 344.29 | 8.12.2024 | 427.216 | 7.30.2024 | 410.785 | 8.28.2024 | 5.4217
| sandy |  | DRY |  | Sandy |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+0 |  | DC2+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+6 |  | DA+9 |  | DA+3 |  | DA+0 |  |  | 14
[23 empty] | 0,0,0,1 |  |  |  | 1,0,0,1
| 11.7.25 |  | 2024-11-09 |  | 4.7.25 |  | 19.07.25 |  | 2024-11-03 |  | 21.11.24 |  | 18.9.25 |  | 2024-09-06 |  | 2024-09-12 |  | 2024-09-16 |  | 2024-10-03 |  | 9.8.25 |  | 2024-10-18 |  | 25.11.25 | [6 empty] | 14
| 15/5 |  | 15/6 |  | 15/7 |  | 15/8 |  | 15/9 |  | 16/0 |  | 16/1 |  | 16/2 |  | 16/3 |  | 16/4 |  | 16/5 |  | 16/6 |  | 17/0 |  | 17/1
403.558 | 30.5.2025 | 423.982 | 9.30.2024 | 416.641 | 12.7.2024 | 423.501 | 5.27.2024 | 416.615 | 6.10.2024 | 412.709 | 8.24.2024 | 394.321 | 7.21.2024 | 426.527 | 7.8.2024 | 408.116 | 6.13.2024 | 393.32 | 6.15.2024 | 413.356 | 6.25.2024 | 409.517 | 6.30.2024 | 372.985 | 7.30.2024 | 405.05 | 9.30.2024 | 5.7202
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+9 |  | DB2+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DC1+0 |  | DA+3 |  |  | 14
0,0,0,1
| 16.11.25 |  | 18.10.25 |  | 30.7.25 |  | 13.08.25 |  | 22.08.25 |  | 28.7.25 |  | 31.7.25 |  | 20.01.26 |  | 10.10.25 |  | 21.02.26 |  | 21.11.25 |  | 23.10.25 |  | 19.08.25 |  | 25.08.25 | [6 empty] | 14
| 17/2 |  | 17/3 |  | 17/4 |  | 17/5 |  | 18/0 |  | 18/1 |  | 18/2 |  | 18/3 |  | 18/4 |  | 18/5 |  | 18/6 |  | 18/7 |  | 18/8 |  | 18/9
431.24 | 16.10.25 | 409.335 | 10.8.2024 | 421.423 | 30.5.25 | 419.17 | 02.6.25 | 421.282 | 14.7.25 | 406.063 | 7.7.25 | 417.634 | 17.7.25 | 419.948 | 20.7.25 | 399.204 | 24.8.25 | 404.168 | 30.8.25 | 418.913 | 27.8.25 | 418.471 | 21.9.25 | 421.342 | 25.7.25 | 413.923 | 25.7.25 | 5.8221
| DRY |  | DRY |  | DFR |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | Sandy |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+0 |  |  | 14
| 5.11.25 |  | 30.08.25 |  | 7.12.25 |  | 4.10.25 |  | 16.11.25 |  | 7.12.25 |  | 30.11.25 |  | 13.12.25 |  | 28.11.24 |  | 10.11.25 |  | 28.10.25 |  | 31.10.25 |  | 19.11.25 |  | 27.12.25 | [6 empty] | 14
| 18/10 |  | 19/0 |  | 19/1 |  | 19/2 |  | 19/3 |  | 19/4 |  | 19/5 |  | 19/6 |  | 19/7 |  | 19/8 |  | 19/9 |  | 19/10 |  | 19/11 |  | 19/12
v
418.649 | 02.9.25 | 404.993 | 02.8.25 | 420.001 | 15.9.25 | 420 | 11.10.24 | 420 | 9.25.2024 | 419.999 | 9.19.2024 | 401.894 | 9.8.2024 | 426.061 | 9.12.2024 | 350.46 | 9.28.2024 | 479.627 | 07.10.25 | 409.428 | 20.10.24 | 430.387 | 10.10.25 | 388.63 | 15.10.25 | 450.026 | 13.12.25 | 5.8402
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DC1+0 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+9 |  | DB1+6 |  | DA+3 |  | DA+9 |  | DA+9 |  | DB1+3 |  |  | 14
[21 empty] | 0,0,0,1 |  | 0,2,2,0 |  | 3,3,4,5
| 22.12.25 |  | 2024-10-11 |  | 25.08.25 |  | 25.08.25 |  | 12.12.25 |  | 4.7.25 |  | 11.7.25 |  | 20.7.25 |  | 27.7.25 |  | 11.7.25 |  | 16.7.25 |  | 21.7.25 |  | 30.11.25 |  | 28.12.25 | [6 empty] | 14
| 19/13 |  | 19/14 |  | 20/0 |  | 21/0 |  | 21/1 |  | 21/2 |  | 21/3 |  | 21/4 |  | 21/5 |  | 21/6 |  | 21/7 |  | 21/8 |  | 21/9 |  | 21/10
458.749 | 8.9.2024 | 315.064 | 8.14.2024 | 426.284 | 13.7.25 | 272.619 | 8.7.25 | 423 | 8.25.2024 | 417 | 8.21.2024 | 405.941 | 8.28.2024 | 434.059 | 9.1.2024 | 401.287 | 9.10.2024 | 402.125 | 9.16.2024 | 389.76 | 9.23.2024 | 395.819 | 12.29.2023 | 399.538 | 12.31.2023 | 433.987 | 1.25.2024 | 5.5752
| Sandy |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | Sandy |  | DRY |  | DRY |  | DFR |  | DRY |  | Sandy |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+9 |  | DD45+3 |  | DD45+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+9 |  | DA+3 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+6 |  | DA+9 |  |  | 14
| 1,0,1,3 |  | 2,2,2,2 |  | 2,2,2,2 |  | 2,2,2,2 |  |  |  | 0,0,1,0 | [5 empty] | 0,0,0,2 | [9 empty] | 1,1,0,0
| 21.11.25 |  | 14.08.25 |  | 16.9.25 |  | 11.8.25 |  | 26.08.25 |  | 4.8.25 |  | 31.7.25 |  | 4.7.25 |  | 25/3 |  | 27.7.25 |  | 8.7.25 |  | 17.7.25 |  | 12.12.25 |  | 26.7.25 | [6 empty] | 14
| 21/11 |  | 21/12 |  | 21/13 |  | 21/14 |  | 22/0 |  | 22/1 |  | 22/2 |  | 22/3 |  | 22/4 |  | 22/5 |  | 22/6 |  | 22/7 |  | 22/8 |  | 22/9
349.31 | 10.22.2024 | 391.872 | 2.19.2024 | 402.437 | 12.26.2024 | 427.467 | 3.27.2025 | 371.558 | 19.6.25 | 446.309 | 04.05.2025 | 373.882 | 2.29.2024 | 398.056 | 31.5.25 | 429.086 | 2.18.2024 | 410.267 | 2.10.2024 | 411.028 | 3.22.2025 | 417.232 | 1.28.2025 | 388.282 | 2.25.2024 | 424.897 | 2.20.2024 | 5.6417
| DRY |  | Sandy |  | DRY |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | Sandy |  | DFR |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+9 |  | DA+9 |  | DA+0 |  | DA+6 |  | DC2+9 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+6 |  | DA+6 |  |  | 14
|  |  | 0,0,1,0 | [17 empty] | 0,0,2,1 | [5 empty] | 0,0,0,1
| 8.8.25 |  | 31.7.25 |  | 9.8.25 |  | 26.7.25 |  | 31.7.25 |  | 6.8.25 |  | 5.7.25 |  | 13.7.25 |  | 21.7.25 |  | 31.08.25 |  | 26.7.25 |  | 31.7.25 |  | 23.7.25 |  | 19.08.25 | [6 empty] | 14
| 23/0 |  | 23/1 |  | 23/2 |  | 23/3 |  | 23/4 |  | 23/5 |  | 23/6 |  | 23/7 |  | 23/8 |  | 23/9 |  | 23/10 |  | 23/11 |  | 24/0 |  | 24/1
336.374 | 3.19.2025 | 388.918 | 2.22.2024 | 421.996 | 1.13.2024 | 390.817 | 2.5.2024 | 381.8 | 5.7.2024 | 406.288 | 1.30.2024 | 426.868 | 3.13.2025 | 407.72 | 1.5.2025 | 333.511 | 31.12.24 | 418.062 | 19.08.25 | 410.767 | 28.12.24 | 419.73 | 27.12.24 | 402.068 | 24.12.24 | 389.369 | 12.4.2024 | 5.5343
| Sandy |  | Sandy |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | Sandy |  | DRY |  | DFR |  | Sandy |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+6 |  | DB2+0 |  | DA+3 |  |  | 14
| 0,1,0,0 | [13 empty] | 1,0,0,2 |  | 1,1,0,0 | [5 empty] | 0,0,1,0
| 5.7.25 |  | 7.7.25 |  | 2.7.25 |  | 27.5.25 |  | 4.6.25 |  | 5.11.25 |  | 18.7.25 |  | 24.08.25 |  | 22.7.25 |  | 5.8.25 |  | 30.6.25 |  | 6.7.25 |  | 12.7.25 |  | 30.7.25 | [6 empty] | 14
| 24/2 |  | 24/3 |  | 24/4 |  | 24/5 |  | 24/6 |  | 25/0 |  | 25/1 |  | 25/2 |  | 25/3 |  | 25/4 |  | 25/5 |  | 25/6 |  | 25/7 |  | 25/8
402.18 | 11.20.2024 | 368.474 | 12.26.2023 | 379.211 | 20.12.24 | 377.682 | 18.12.24 | 404.417 | 16.12.24 | 369.136 | 1.8.2025 | 396.265 | 1.11.2025 | 408.495 | 3.7.25 | 426.619 | 1.13.2025 | 407.313 | 1.17.2025 | 432.307 | 12.16.2024 | 407.88 | 12.8.2024 | 432.436 | 1.22.2025 | 388.68 | 7.17.2024 | 5.6011
| DRY |  | Sandy |  | DRY |  | Sandy |  | DRY |  | Sandy |  | Sandy |  | DRY |  | DRY |  | Sandy |  | Sandy |  | DRY |  | Sandy |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DC1+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+9 |  |  | 14
[9 empty] | 1,0,0,0 | [7 empty] | 0,2,1,0 |  | 0,4,1,0 |  | 1,0,0,0 |  |  |  | 4,3,3,3 |  | 4,4,4,4
| 15.7.25 |  | 9.7.25 |  | 30.6.25 |  | 23.7.25 |  | 30.7.25 |  | 28.7.25 |  | 13.8.25 |  | 24.9.25 |  | 15.9.25 |  | 3.9.25 |  | 31.08.25 |  | 15.10.25 |  | 26.08.25 |  | 11.8.25 | [6 empty] | 14
| 25/9 |  | 25/10 |  | 25/11 |  | 26/0 |  | 26/1 |  | 26/2 |  | 26/3 |  | 26/4 |  | 26/5 |  | 26/6 |  | 26/7 |  | 27/0 |  | 27/1 |  | 27/2
415.247 | 7.7.2024 | 423.984 | 6.19.2024 | 404.712 | 23.12.24 | 420.885 | 28.12.24 | 383.98 | 2.25.2025 | 374.022 | 1.4.2025 | 427.066 | 1.7.2025 | 412.227 | 3.23.2024 | 379.841 | 1.22.2025 | 428.866 | 8.16.2024 | 309 | 7.27.2024 | 430.122 | 29.12.24 | 371.927 | 1.16.2025 | 440.414 | 24.12.24 | 5.6223
| DRY |  | Sandy |  | DRY |  | DRY |  | DRY |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14 |  | 14
| DA+6 |  | DA+0 |  | DA+6 |  | DB2+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+9 |  | DA+9 |  | DA+0 |  | DA+3 |  | DC2+9 |  | DB1+9 |  | DA+0 |  |  | 14
[9 empty] | 0,1,1,0 |  | 0,2,3,0 |  |  |  | 3,2,0,0 |  | 2,0,0,2 |  | 2,0,0,1 |  | 1,0,0,3 |  | 1,1,1,1 |  | 3,3,4,5 |  | 1,1,0,4
| 31.7.25 |  | 28.7.25 |  | 24.7.25 |  | 13.7.25 |  | 19.7.25 |  | 30.07.25 |  | 4.8.25 |  | 11.8.25 |  | 2.9.25 |  | 9.10.25 |  | 9.9.25 |  | 28.7.25 |  | 2025-01-12 |  | 31.07.25 | [6 empty] | 14
| 27/3 |  | 27/4 |  | 27/5 |  | 28/0 |  | 28/1 |  | 28/2 |  | 28/3 |  | 28/4 |  | 28/5 |  | 28/6 |  | 28/7 |  | 28/8 |  | 28/9 |  | 29/0
330.658 | 12.20.2024 | 407.361 | 2.29.2024 | 317.413 | 3.7.2024 | 256.363 | 3.11.2024 | 374.465 | 2.29.2024 | 464.538 | 3.12.2025 | 375 | 11.6.2025 | 450 | 18.06.25 | 390 | 26.06.25 | 421 | 5.07.25 | 335.385 | 18.07.25 | 334.908 | 10.4.25 | 460.188 | 3.27.2025 | 308.946 | 13.05.25 | 5.2262
| Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+6 |  | DA+3 |  | DA+0 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DB2+0 |  |  | 14
| 0,2,1,0 |  | 0,1,0,0 | [7 empty] | 3,0,0,1 |  | 0,4,2,0 |  | 1,2,0,0 |  | 2,5,1,6 |  | 1,6,1,6 |  | 3,0,1,4 |  | 0,1,5,0 |  | 1,0,0,0
| 22.7.25 |  | 8.7.25 |  | 17.7.25 |  | 24.7.25 |  | 2024-02-24 |  | 2024-06-08 |  | 2024-02-18 |  | 2024-02-09 |  | 2024-06-24 |  | 2024-07-06 |  | 9.8.25 |  | 22.7.25 |  | 13.7.25 |  | 11.11.26 | [6 empty] | 14
| 29/1 |  | 29/2 |  | 29/3 |  | 29/4 |  | 29/5 |  | 29/6 |  | 29/7 |  | 29/8 |  | 29/9 |  | 29/10 |  | 30/0 |  | 30/1 |  | 30/2 |  | 30/3
419.673 | 18.4.25 | 350.699 | 6.2.25 | 427.07 | 30.12.23 | 407.612 | 8.4.25 | 413.161 | 31.12.23 | 422.29 | 1.31.2024 | 414.207 | 30.12.23 | 425.135 | 28.12.23 | 387.241 | 2.12.2024 | 394.858 | 2.27.2024 | 387.904 | 3.9.2024 | 256.947 | 1.14.2024 | 335.986 | 16.11.23 | 366.152 | 10.5.2024 | 5.4089
| Sandy |  | Sandy |  | Sandy |  | DRY |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+6 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+6 |  | DC2+0 |  | DA+3 |  | DA+0 |  | DA+6 |  |  | 14
RC | 1,0,0,1 |  | 0,0,1,0 | [5 empty] | 0,0,0,1 |  | 1,0,0,0 | [5 empty] | 2,2,0,0 |  | 0,2,0,0 |  |  |  | 1,1,0,0
| 2024-12-20 |  | 9.8.25 |  | 2024-07-22 |  | 2024-07-12 |  | 2024-08-04 |  | 2024-10-28 |  | 12.11.24 |  | 2024-08-20 |  | 2024-11-07 |  | 2024-10-09 |  | 2024-08-01 |  | 2024-08-09 |  | 22.08.25 |  | 27.08.25 | [6 empty] | 14
| 31/0 |  | 31/1 |  | 31/2 |  | 31/3 |  | 31/4 |  | 32/0 |  | 32/1 |  | 32/2 |  | 32/3 |  | 32/4 |  | 32/5 |  | 32/6 |  | 32/7 |  | 32/8
365.956 | 10.20.2024 | 309.124 | 2.22.2024 | 392.873 | 2.11.2024 | 358.613 | 12.4.2023 | 303.693 | 1.19.2024 | 314.066 | 11.28.2023 | 400.257 | 11.10.2023 | 434.012 | 1.28.2024 | 405.392 | 1.31.2024 | 433.951 | 4.18.2024 | 405.286 | 11.4.2023 | 432.856 | 5.2.2024 | 402.19 | 10.28.2023 | 429.308 | 8.4.2024 | 5.3876
| Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | DRY |  | Sandy |  | Sandy |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DD45+3 |  | DA+9 |  | DA+0 |  | DA+0 |  | DA+9 |  | DB2+6 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+9 |  |  | 14
RC |  |  | 3,3,3,3 |  | 1,2,1,0 |  |  |  | 0,0,0,1 | [5 empty] | 1,0,0,0 |  | 0,2,0,0 |  | 3,2,0,1
| 9.7.25 |  | 12.8.25 |  | 7.8.25 |  | 13.7.25 |  | 18.7.25 |  | 15.5.25 |  | 8.7.25 |  | 14.7.25 |  | 23.7.25 |  | 23.7.25 |  | 20.7.25 |  | 9.7.25 |  | 31.7.25 |  | 13.5.25 | [6 empty] | 14
| 33/0 |  | 33/1 |  | 33/2 |  | 33/3 |  | 33/4 |  | 33/5 |  | 33/6 |  | 33/7 |  | 33/8 |  | 34/0 |  | 34/1 |  | 34/2 |  | 34/3 |  | 34/4 | [5 empty] | 14
403.692 | 03.02.25 | 391 | 22.10.23 | 412 | 08.02.25 | 411 | 07.02.25 | 325 | 13.02.25 | 432.272 | 154.02.25 | 384.728 | 14.02.25 | 448 | 09.01.25 | 357 | 04.01.25 | 177.09 | 28.12.24 | 459.33 | 20.12.24 | 379.29 | 13.12.24 | 394.37 | 4.12.24 | 419.87 | 07.11.24 | 5.3946
| Sandy |  | SANDY |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DB2+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+9 |  | DA+3 |  | DB1+6 |  | DA+3 |  | DA+9 |  | DA+9 |  | DA+6 |  |  | 14 |  | 0
RC | 2,-,-,4 |  |  |  | 1,1,-,- |  | 2,-,-,2 |  | 1,4,-,- |  |  |  | -,-,4,4 |  | 3,1,-,- |  | 1,-,1,3 |  | -,-,2,1 |  | 2,-,2,3 |  | -,-,-,1 |  | -,-,3,6 |  | 1,3,1,-
[34 empty] | 14 | 0
| 26.7.25 |  | 6.6.25 |  | 25.5.25 |  | 15.6.25 |  | 24.6.25 |  | 30.6.25 |  | 6.7.25 |  | 30.04.25 |  | 26.4.25 |  | 20.4.25 |  | 14.4.25 |  | 10.4.25 |  | 15.6.25 |  | 30.6.25 | [5 empty] | 14
| 34/5 |  | 34/6 |  | 35/0 |  | 35/1 |  | 35/2 |  | 35/3 |  | 35/4 |  | 35/5 |  | 35/6 |  | 35/7 |  | 35/8 |  | 35/9 |  | 36/0 |  | 37/0
4.9263
403.55 | 15.11.24 | 390.38 | 20.11.24 | 314.78 | 17.10.24 | 268.03 | 08.10.24 | 308.85 | 23.10.24 | 411.89 | 29.10.24 | 320.87 | 23.9.24 | 362.6 | 09.9.24 | 428.4 | 15.9.24 | 411.65 | 30.9.24 | 333.07 | 03.10.24 | 326.59 | 07.02.25 | 431.59 | 26.03.25 | 214.02 | 17.03.25 |  |  |  | 14
| Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  |  | 14 |  | 0
| DCT+0 |  | DA+6 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+9 |  | DA+3 |  | DA+0 |  | DA+3 |  | DD60+25 |  | DD60+25
|  |  | 1,-,-,1 |  | 1,3,1,- |  | -,3,-,- |  | 1,3,-,- |  | 2,-,-,4 |  | -,3,2,- |  | -,3,1,- |  | -,2,-,- |  | 1,-,-,3 |  | 1,3,-,- |  | 2,-,-,- |  | 5,3,3,3 |  | 2,2,0,3 | [7 empty] | 0
| 24.5.25 |  | 10.9.25 |  | 28.12.24 |  | 03.01.25 |  | 16.1.25 |  | 20.01.25 |  | 24.01.25 |  | 28.01.25 |  | 04.02.25 |  | 24.12.24 |  | 19.12.24 |  | 15.12.24 |  | 29.3.25 |  | 25.2.25 | [6 empty] | 14
| 37/1 |  | 37/2 |  | 37/3 |  | 37/4 |  | 37/5 |  | 37/6 |  | 37/7 |  | 37/8 |  | 38/0 |  | 38/1 |  | 38/2 |  | 38/3 |  | 38/4 |  | 38/5 | [5 empty] | 14
317.05 | 02.02.25 | 467.94 | 26.2.24 | 426.8 | 29.2.24 | 412.96 | 12.3.24 | 421.96 | 18.12.24 | 372.4 | 15.12.24 | 382.41 | 12.12.24 | 434.06 | 09.12.24 | 261.36 | 23.12.24 | 274.27 | 12.3.24 | 374.16 | 20.2.24 | 355.55 | 17.2.24 | 429 | 28.12.24 | 397 | 30.12.24 | 5.3269
| Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DB1+9 |  | DB1+6 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+0 |  | DC1+0 |  | DA+3 |  | DA+6 |  | DA+9 |  | DA+0 |  | DA+0 |  |  | 14 |  | 0
| 3,5,0,0 | [5 empty] | 2,-,-,3 |  | 1,-,-,3 |  | 1,-,-,- |  | 1,1,-,- |  |  |  | -,2,-,- |  | -,2,-,- |  |  |  | 2,-,-,1 |  | 1,1,-,2 |  | 2,-,1,2
| 21.3.25 |  | 17.3.25 |  | 11.3.25 |  | 7.3.25 |  | 01.03.25 |  | 28.01.25 |  | 11.5.25 |  | 6.5.25 |  | 17.05.25 |  | 18.06.25 |  | 28.6.25 |  | 3.7.25 |  | 6.3.25 |  | 12.3.25 | [6 empty] | 14 | 0
| 38/6 |  | 38/7 |  | 38/8 |  | 38/9 |  | 39/0 |  | 39/1 |  | 39/2 |  | 39/3 |  | 39/4 |  | 39/5 |  | 39/6 |  | 39/7 |  | 40/0 |  | 40/1 | [5 empty] | 14
370.31 | 29.2.24 | 321.69 | 31.12.24 | 349.66 | 6.3.24 | 343.32 | 09.11.24 | 544.03 | 30.10.24 | 231.71 | 12.3.24 | 324.77 | 25.12.24 | 430.52 | 21.3.24 | 387 | 09.5.24 | 391.62 | 30.11.24 | 274.37 | 06.12.24 | 388 | 09.12.24 | 315.78 | 21.12.24 | 301 | 22.12.24 | 4.9738
| Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+0 |  | DA+0 |  | DB1+6 |  | DC2+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+0 |  |  | 14 |  | 0
| -,-,-1 |  | 1,-,-,1 |  | -,1,-,1 |  | -,-,2,2 |  | 2,-,-2 |  | 1,2,-,- |  | -,3,-,- |  | 1,-,-,1 |  | 2,3,-,- |  | -4,-,3 |  | -,3,-,3 |  | -,-,-,3 |  | -,5,2,- |  | 2,4,-,-
| 30.01.25 |  | 30.6.25 |  | 20.3.25 |  | 28.3.25 |  | 20.02.25 |  | 26.02.25 |  | 13.6.25 |  | 18.6.25 |  | 11.11.24 |  | 30.10.24 |  | 08.02.25 |  | 29.01.25 |  | 17.01.25 |  | 28.12.24 | [6 empty] | 14 | 0
| 40/2 |  | 40/3 |  | 40/4 |  | 40/5 |  | 40/6 |  | 40/7 |  | 40/8 |  | 40/9 |  | 40/10 |  | 40/11 |  | 40/12 |  | 41/0 |  | 41/1 |  | 41/2 | [5 empty] | 14
350.53 | 15.7.24 | 383.36 | 21.2.24 | 411.18 | 6.3.24 | 424.93 | 15.2.24 | 456 | 21.2.24 | 311 | 06.12.24 | 290.66 | 16.12.24 | 349.8 | 12.12.24 | 489.079 | 06.2.24 | 403.22 | 01.02.24 | 434.31 | 08.12.24 | 235.55 | 01.12.24 | 332 | 30.11.24 | 332 | 24.11.24 | 5.2036
| Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DB1+9 |  | DA+3 |  | DA+9 |  | DB1+9 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB1+6 |  | DA+9 |  | DA+0 |  | DB1+0 |  | DA+3 |  | DA+0 |  |  | 14 |  | 0
| -,2,1,- |  | -,1,1,- |  | -,-,-,1 |  |  |  | 1,-,-,2 |  | 1,4,1,4 |  | -,4,-,- |  | -,6,1,2 |  |  |  | 1,-,-,- |  | 2,-,-,5 |  | -,1,1- |  | -,-,-,3 |  | 1,-,1,3
| 07.01.25 |  | 05.02.24 |  | 31.01.24 |  | 9.2.24 |  | 20.01.24 |  | 13.2.24 |  | 17.2.24 |  | 16.1.24 |  | 12.01.24 |  | 17.12.24 |  | 31.12.24 |  | 18.2.25 |  | 28.1.24 |  | 22.10.24 | [6 empty] | 14 | 0
| 41/3 |  | 41/4 |  | 41/5 |  | 41/6 |  | 41/7 |  | 41/8 |  | 41/9 |  | 41/10 |  | 41/11 |  | 41/12 |  | 42/0 |  | 43/0 |  | 43/1 |  | 43/2 | [5 empty] | 14
247.72 | 26.11.24 | 463.27 | 06.01.24 | 374.8 | 13.12.23 | 460.2 | 31.12.23 | 375 | 8.10.23 | 416 | 18.1.24 | 338 | 12.01.24 | 401.13 | 25.9.23 | 423.316 | 30.9.23 | 400.39 | 25.1.24 | 416.58 | 11.08.24 | 489.1 | 30.08.24 | 456.24 | 20.10.23 | 377.56 | 30.1.24 | 5.6393
| Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC2+9 |  | DB2+9 |  | DA+9 |  | DA+9 |  |  | 14 |  | 0
| -,-,1,1 |  | -,1,-,1 |  | -,-,1,1 |  | 2,-,-,1 |  |  |  | -,2,1,- |  | -,2,2,2 | [5 empty] | 1,-,-,- |  | -,-,-,1 |  | -,3,-,3 |  |  |  | 1,-,-,1
| 8.10.24 |  | 22.1.24 |  | 27.1.24 |  | 26.9.24 |  | 28.2.25 |  | 01.02.24 |  | 05.01.24 |  | 15.1.24 |  | 09.01.24 |  | 6.5.25 |  | 23.5.25 |  | 30.06.25 |  | 3.6.25 |  | 03.02.24 | [6 empty] | 14 | 0
| 43/3 |  | 43/4 |  | 43/5 |  | 43/6 |  | 44/0 |  | 44/1 |  | 44/2 |  | 44/3 |  | 44/4 |  | 44/5 |  | 45/0 |  | 46/0 |  | 46/1 |  | 46/2 | [5 empty] | 14
381.75 | 05.2.24 | 426.4 | 14.9.23 | 404.86 | 19.9.23 | 430.51 | 31.07.24 | 378.47 | 28.07.24 | 439 | 25.9.23 | 381 | 25.9.23 | 401 | 9.10.23 | 401 | 27.9.23 | 384 | 04.02.25 | 452.98 | 08.03.25 | 233.15 | 19.03.25 | 325 | 14.02.25 | 391 | 29.10.23 | 5.4301
| SANDY |  | DRY |  | SANDY |  | Sandy |  | SANDY |  | WFR |  | SANDY |  | Sandy |  | WFR |  | WFR |  | SANDY |  | SANDY |  | SANDY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DA+9 |  | DA+0 |  | DA+6 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DD60+25 |  | DD60+25 |  | DA+6 |  | DA+0 |  |  | 14 |  | 0
| 1,-,1,2 | [5 empty] | 1,1,-,2 |  | -,1,-,- | [11 empty] | 0,2,0,0 |  | 2,0,3,3 |  | -,1,-,-
| 19.01.24 |  | 31.08.24 |  | 28.1.24 |  | 12.9.24 |  | 07.01.24 |  | 29.12.23 |  | 19.01.24 |  | 9.12.23 |  | 16.12.23 |  | 23.2.25 |  | 26.9.24 |  | 20.9.24 |  | 16.9.245 |  | 22.12.23 | [6 empty] | 14 | 0
| 46/3 |  | 46/4 |  | 47/0 |  | 47/1 |  | 47/2 |  | 47/3 |  | 48/0 |  | 48/1 |  | 48/2 |  | 49/0 |  | 50/0 |  | 50/1 |  | 50/2 |  | 50/3 | [5 empty] | 14
305 | 7.12.23 | 368 | 28.1.24 | 339.07 | 26.10.23 | 321 | 13.08.24 | 312 | 8.9.23 | 320 | 16.9.23 | 321.28 | 6.11.23 | 371 | 6.9.23 | 379 | 11.9.23 | 411.982 | 17.7.24 | 240.77 | 22.7.24 | 425 | 29.08.24 | 320 | 08.08.24 | 416 | 27.9.23 | 4.8501
| SANDY |  | SANDY |  | DRY |  | DRY |  | DRY |  | DFR |  | SANDY |  | DRY |  | DRY |  | SANDY |  | SANDY |  | DFR |  | DFR |  | DFR |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+3 |  | DC1+3 |  | DC2+3 |  | DA+0 |  | DA+0 |  | DA+0 |  |  | 14 |  | 0
| -,-,-,- |  | -,2,-,3 | [19 empty] | 2,-,-,-
| 01.12.23 |  | 28.1.24 |  | 04.2.24 |  | 15.10.23 |  | 09.11.23 |  | 21.10.23 |  | 29.10.23 |  | 19.01.24 |  | 4.11.23 |  | 06.01.24 |  | 29.12.23 |  | 14.11.23 |  | 28.1.24 |  | 10.10.23 | [6 empty] | 14 | 0
| 50/4 |  | 51/0 |  | 51/1 |  | 51/2 |  | 51/3 |  | 51/4 |  | 51/5 |  | 51/6 |  | 51/7 |  | 51/8 |  | 51/9 |  | 51/10 |  | 52/0 |  | 52/1 | [5 empty] | 14
401 | 19.8.23 | 408.86 | 31.10.23 | 348 | 6.12.23 | 383 | 19.8.23 | 385 | 31.8.23 | 426 | 27.8.23 | 405 | 14.8.23 | 401 | 30.11.23 | 417 | 9.8.23 | 418 | 9.12.23 | 408 | 13.11.23 | 428 | 12.9.23 | 383.86 | 6.11.23 | 385 | 25.8.23 | 5.5977
| DRY |  | DFR |  | DFR |  | DRY |  | DFR |  | DFR |  | DRY |  | DRY |  | DFR |  | DFR |  | DRY |  | DFR |  | DRY |  | DFR |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB2+0 |  | DA+0 |  |  | 14 |  | 0
1,-,-,-
| 19.11.23 |  | 05.05.24 |  | 24.12.23 |  | 24.11.23 |  | 18.04.26 |  | 09.2.24 |  | 11.01.24 |  | 29.11.23 |  | 03.12.23 |  | 4.4.24 |  | 9.12.23 |  | 15.12.23 |  | 19.12.23 |  | 02.12.23 | [6 empty] | 14 | 0
| 52/2 |  | 52/3 |  | 52/4 |  | 52/5 |  | 53/0 |  | 53/1 |  | 53/2 |  | 53/3 |  | 53/4 |  | 55/0 |  | 55/1 |  | 55/2 |  | 55/3 |  | 55/4 | [5 empty] | 14
373 | 16.8.23 | 328 | 20.12.23 | 439 | 31.8.23 | 400 | 16.9.23 | 439.09 | 02.02.24 | 393 | 14.12.23 | 399 | 22.8.23 | 410 | 27.8.23 | 410 | 05.9.23 | 401.46 | 05.02.24 | 408 | 29.8.23 | 427 | 16.9.23 | 413 | 20.9.23 | 410 | 24.9.23 | 5.6505
| DFR |  | Sandy |  | DFR |  | DRY |  | DRY |  | DRY |  | DFR |  | DRY |  | DFR |  | DRY |  | DFR |  | DFR |  | DFR |  | DFR |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DC2+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC1+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  |  | 14 |  | 0
|  |  | -,3,1,- | [7 empty] | 1,1,1,1
| 26.11.23 |  | 7.12.23 |  | 21.11.23 |  | 28.12.23 |  | 12.12.23 |  | 17.12.23 |  | 22.12.23 |  | 05.01.24 |  | 16.04.24 |  | 06.12.23 |  | 29.11.23 |  | 02.12.23 |  | 24.12.23 |  | 28.12.23 | [6 empty] | 14 | 0
| 55/5 |  | 55/6 |  | 55/7 |  | 55/8 |  | 55/9 |  | 55/10 |  | 55/11 |  | 56/0 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | 56/6 | [5 empty] | 14
414 | 28.9.23 | 417 | 21.10.23 | 421 | 28.8.23 | 405 | 31.8.23 | 425 | 6.9.23 | 389 | 22.09.23 | 434 | 4.10.23 | 336.65 | 31.10.23 | 404 | 5.10.23 | 433 | 14.10.23 | 407 | 25.9.23 | 400 | 30.9.23 | 408 | 1.10.23 | 399 | 25.9.23 | 5.6926
| DFR |  | DRY |  | DFR |  | DRY |  | DRY |  | DRY |  | DRY |  | DFR |  | DRY |  | DFR |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  |  | 14 |  | 0
| 24.11.23 |  | 21.11.23 |  | 16.11.23 |  | 19.12.23 |  | 13.11.23 |  | 16.10.23 |  | 20.10.23 |  | 26.10.23 |  | 30.10.23 |  | 13.12.23 |  | 7.11.23 |  | 03.11.23 |  | 21.9.23 |  | 6.10.23 | [6 empty] | 14 | 0
| 56/7 |  | 56/8 |  | 56/9 |  | 57/0 |  | 57/1 |  | 57/2 |  | 57/3 |  | 57/4 |  | 57/5 |  | 57/6 |  | 57/7 |  | 57/8 |  | 57/9 |  | 57/10 | [5 empty] | 14
428 | 22.9.23 | 411 | 22.9.23 | 429 | 21.9.23 | 408.45 | 27.10.23 | 404 | 11.9.23 | 401 | 31.8.23 | 374 | 14.9.23 | 384 | 27.8.23 | 390 | 28.8.23 | 391 | 20.10.23 | 383 | 24.8.23 | 379 | 23.8.23 | 408 | 11.8.23 | 387 | 13.8.23 | 5.5774
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DA+3 |  | DA+3 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  |  | 14 |  | 0
| 26.9.23 |  | 11.10.23 |  | 01.10.23 |  | 16.04.24 |  | 12.10.23 |  | 10.5.24 |  | 22.10.23 |  | 11.11.23 |  | 31.10.23 |  | 21.11.23 |  | 09.01.24 |  | 11.10.23 |  | 7.10.23 |  | 23.10.23 | [6 empty] | 14 | 0
| 57/11 |  | 57/12 |  | 57/13 |  | 58/0 |  | 58/1 |  | 58/2 |  | 58/3 |  | 58/4 |  | 58/5 |  | 58/6 |  | 58/7 |  | 58/8 |  | 58/9 |  | 58/10 | [5 empty] | 14
383 | 18.8.23 | 407 | 21.8.23 | 402 | 16.8.23 | 391.56 | 15.2.24 | 364.99 | 4.8.23 | 388.37 | 9.9.23 | 402.91 | 6.8.23 | 407.24 | 10.10.23 | 400.96 | 13.8.23 | 431.19 | 22.8.23 | 394.39 | 19.10.23 | 384.42 | 28.8.23 | 383.12 | 30.7.23 | 407 | 10.8.23 | 5.5481
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+3 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  |  | 14 |  | 0
| 31.10.23 |  | 25.9.23 |  | 19.12.24 |  | 1.10.23 |  | 06.12.23 |  | 17.10.23 |  | 29.12.23 |  | 30.11.23 |  | 24.11.23 |  | 18.11.23 |  | 10.09.24 |  | 07.11.23 |  | 07.11.23 |  | 19.02.25 | [6 empty] | 14 | 0
| 58/11 |  | 58/12 |  | 58/13 |  | 58/14 |  | 58/15 |  | 58/16 |  | 59/0 |  | 59/1 |  | 59/2 |  | 59/3 |  | 59/4 |  | 59/5 |  | 59/6 |  | 60/0 | [5 empty] | 14
427.54 | 17.8.23 | 411.38 | 16.7.23 | 390.06 | 25.11.24 | 385.2 | 20.7.23 | 401.43 | 20.8.23 | 397.87 | 25.8.23 | 296.58 | 26.10.23 | 365.19 | 20.7.23 | 332.69 | 3.8.23 | 371.69 | 29.7.23 | 349.55 | 28.12.24 | 377.59 | 31.8.23 | 386.21 | 6.8.23 | 397.94 | 06.01.25 | 5.2909
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC2+3 |  |  | 14 |  | 0
| 3.3.25 |  | 20.12.23 |  | 14.12.23 |  | 09.05.25 |  | 19.5.25 |  | 21.4.25 |  | 25.4.25 |  | 30.04.25 |  | 25.4.25 |  | 15.4.25 |  | 20.4.25 |  | 6.6.25 |  | 15.6.25 |  | 28.6.25 | [6 empty] | 14 | 0
| 61/0 |  | 61/1 |  | 61/2 |  | 62/0 |  | 63/0 |  | 63/1 |  | 63/2 |  | 63/3 |  | 63/4 |  | 63/5 |  | 63/6 |  | 64/0 |  | 64/1 |  | 64/2 | [5 empty] | 14
205.9 | 10.01.25 | 348.303 | 3.9.23 | 330.06 | 05.9.23 | 349.34 | 04.10.24 | 221.05 | 24.8.24 | 412.37 | 31.12.24 | 424.68 | 12.3.24 | 402.02 | 20.12.24 | 408.6 | 25.12.24 | 403.2 | 30.1.24 | 430.57 | 31.1.24 | 397.67 | 25.10.24 | 427 | 14.12.24 | 395.65 | 15.12.24 | 5.1564
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DB1+6 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DD45+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB2+0 |  | DA+6 |  | DA+0 |  |  | 14 |  | 0
| 15.6.25 |  | 8.7.25 |  | 8.6.25 |  | 27.05.25 |  | 22.6.25 |  | 31.5.25 |  | 23.5.25 |  | 20.6.25 |  | 5.7.25 |  | 28.6.25 |  | 21.05.24 |  | 16.5.24 |  | 26.05.24 |  | 18.12.24 | [6 empty] | 14 | 0
| 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | 64/8 |  | 64/9 |  | 65/0 |  | 65/1 |  | 65/2 |  | 65/3 |  | 65/4 |  | 65/5 |  | 65/6 | [5 empty] | 14
389.12 | 13.12.24 | 406.04 | 09.12.24 | 418.94 | 11.12.24 | 410.64 | 10.12.24 | 418.84 | 08.12.24 | 412.03 | 05.12.24 | 389.3 | 16.12.24 | 411.32 | 27.3.25 | 410.07 | 18.2.24 | 353.17 | 02.3.24 | 391.43 | 22.2.24 | 362.79 | 16.2.24 | 357.3 | 14.2.24 | 355.07 | 9.3.24 | 5.4861
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | Sandy |  | DRY |  | Sandy |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB2+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  |  | 14 |  | 0
| 22.12.24 |  | 31.12.24 |  | 8.12.24 |  | 10.10.24 |  | 9.6.25 |  | 14.11.24 |  | 8.12.24 |  | 19.10.24 |  | 29.11.24 |  | 5.10.24 |  | 10.10.24 |  | 28.10.24 |  | 9.11.24 |  | 1.11.24 | [6 empty] | 14 | 0
| 65/7 |  | 66/0 |  | 66/1 |  | 66/2 |  | 66/3 |  | 66/4 |  | 67/0 |  | 67/1 |  | 68/0 |  | 68/1 |  | 68/2 |  | 68/3 |  | 68/4 |  | 68/5 | [5 empty] | 14
383.72 | 21.09.24 | 352.68 | 01.10.24 | 408.92 | 13.08.24 | 406.68 | 11.08.24 | 401.21 | 04.09.24 | 413.56 | 31.08.24 | 397.39 | 02.09.24 | 437.55 | 19.08.24 | 426.47 | 28.09.24 | 403.01 | 04.09.24 | 413 | 29.08.24 | 415 | 15.09.24 | 202 | 13.08.24 | 418 | 14.08.24 | 5.4792
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DD45+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DD45+0 |  | DB1+9 |  | DD45+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  |  | 14 |  | 0
[34 empty] | 14 | 0
| 05.11.24 |  | 30.11.24 |  | 22.11.24 |  | 17.11.24 |  | 13.11.24 |  | 9.11.24 |  | 05.11.24 |  | 27.10.24 |  | 31.10.24 |  | 22.12.24 |  | 6.12.24 |  | 31.12.24 |  | 17.12.24 |  | 1.10.24 | [5 empty] | 14
| 68/6 |  | 69/0 |  | 69/1 |  | 69/2 |  | 69/3 |  | 69/4 |  | 69/5 |  | 69/6 |  | 69/7 |  | 69/8 |  | 69/9 |  | 70/0 |  | 71/0 |  | 71/1
5.317
413 | 24.8.23 | 398.66 | 12.09.24 | 387.34 | 03.09.24 | 389.99 | 08.08.24 | 386.3 | 10.08.24 | 389.49 | 18.08.24 | 387.8 | 29.08.24 | 383.6 | 13.08.24 | 388.76 | 17.08.24 | 388.6 | 01.12.24 | 390.71 | 25.10.24 | 388.45 | 14.12.24 | 258.18 | 22.10.24 | 366.13 | 22.9.23 |  |  |  | 14
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DFR |  | FS |  | FS |  | DRY |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  |  | 14 |  | 0
| DA+3 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DD60+0 |  | DD60+0 |  | DA+0
| 26.9.24 |  | 23.10.24 |  | 22.09.24 |  | 6.9.24 |  | 16.9.24 |  | 3.10.24 |  | 29.9.24 |  | 1.9.24 |  | 6.9.24 |  | 11.9.24 |  | 15.9.24 |  | 25.9.24 |  | 17.10.24 | [8 empty] | 13 | 0
| 71/2 |  | 71/3 |  | 71/4 |  | 71/5 |  | 72/0 |  | 72/1 |  | 72/2 |  | 72/3 |  | 72/4 |  | 72/5 |  | 72/6 |  | 72/7 |  | 73/0 | [7 empty] | 13
355.347 | 28.08.24 | 378.664 | 29.09.23 | 332.29 | 30.9.23 | 331.44 | 4.10.23 | 327.96 | 27.07.24 | 371.177 | 4.10.23 | 375.36 | 26.9.23 | 369.39 | 14.9.23 | 365.4 | 18.9.23 | 370.61 | 25.9.23 | 376.14 | 31.07.24 | 361.02 | 08.08.24 | 496.23 | 03.09.24 | KPIL |  | 4.811
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | Sandy |  | Sandy |  | DFR | [5 empty] | 13
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  |  |  | 13
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+9 |  | DD45+9 |  |  |  |  | 13 |  | 0
[21 empty] | 1,1,1,1 |  | 1,1,1,1 |  |  |  |  | 201.9337 | 521 | 521 | 521 | 0 | 265 | 521 | -256
50/4
c

## Hindrance
HINDRANCE REGISTER
1 | Name of the Substation/TL/Project | 765 KV Fatehgarh-3 Beawer Transmission Line Part-G |  |  |  | Name of Work |  | Transmission & Power Distribution
3 | Name of the Executing Agency | KEC International Limited |  |  |  | LOA No. & Date |  | LOI/EPC/FBTL/KEC/01 Dated 25.04.2023
Sr. No. | Activity | Total | Open | Close
1 | Survey | 18 | 0 | 18
2 | Foundation | 207 | 32 | 175
3 | Erection | 72 | 40 | 32
4 | Stringing | 0 | 0 | 0
5 | Others | 2 | 0 | 2
Total |  | 299 | 72 | 227
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
| Check Survey in Bhandu area Hold due court case | 62/0 | Check Survey |  | 2023-06-15 | 2023-09-21 | 98
| Check Survey in Bhandu area Hold due court case | 63/0 | Check Survey |  | 2023-06-15 | 2023-09-21 | 98
| Check Survey in Bhandu area Hold due court case | 63/1 | Check Survey |  | 2023-06-15 | 2023-09-21 | 98
| Check Survey in Bhandu area Hold due court case | 63/2 | Check Survey |  | 2023-06-15 | 2023-09-21 | 98
| Check Survey in Bhandu area Hold due court case | 63/3 | Check Survey |  | 2023-06-15 | 2023-09-21 | 98
| Check Survey in Bhandu area Hold due court case | 63/4 | Check Survey |  | 2023-06-15 | 2023-09-21 | 98
| Check Survey in Bhandu area Hold due court case | 63/5 | Check Survey |  | 2023-06-15 | 2023-09-21 | 98
| Check Survey in Bhandu area Hold due court case | 63/6 | Check Survey |  | 2023-06-15 | 2023-09-21 | 98
| Check Survey in Bhandu area Hold due court case | 64/0 | Check Survey |  | 2023-06-15 | 2023-09-21 | 98
| Bhandu area hold due to court case | 64/1 | Pit Marking |  | 2023-06-15 | 2024-10-10 | 483
| Bhandu area hold due to court case | 64/2 | Pit Marking |  | 2023-06-15 | 2024-12-04 | 538
| Bhandu area hold due to court case | 64/3 | Pit Marking |  | 2023-06-15 | 2024-12-04 | 538
| Bhandu area hold due to court case | 64/4 | Pit Marking |  | 2023-06-15 | 2024-12-04 | 538
| Bhandu area hold due to court case | 64/5 | Pit Marking |  | 2023-06-15 | 2024-12-04 | 538
| Bhandu area hold due to court case | 64/6 | Pit Marking |  | 2023-06-15 | 2024-12-04 | 538
| Bhandu area hold due to court case | 64/7 | Pit Marking |  | 2023-06-15 | 2024-12-04 | 538
| Bhandu area hold due to court case | 64/8 | Pit Marking |  | 2023-06-15 | 2024-12-04 | 538
| Bhandu area hold due to court case | 64/9 | Pit Marking |  | 2023-06-15 | 2024-12-04 | 538
| Bhandu area hold due to court case | 65/0 | Pit Marking |  | 2023-06-15 | 2025-10-18 | 856
| Check Survey in Bhandu area Hold due court case | 65/1 | Check Survey |  | 2023-06-15 | 2024-02-07 | 237
| Check Survey in Bhandu area Hold due court case | 65/2 | Check Survey |  | 2023-06-15 | 2024-02-07 | 237
| Check Survey in Bhandu area Hold due court case | 65/3 | Check Survey |  | 2023-06-15 | 2024-02-07 | 237
| Check Survey in Bhandu area Hold due court case | 65/4 | Check Survey |  | 2023-06-15 | 2024-02-07 | 237
| Check Survey in Bhandu area Hold due court case | 65/5 | Check Survey |  | 2023-06-15 | 2024-02-07 | 237
| Check Survey in Bhandu area Hold due court case | 65/6 | Check Survey |  | 2023-06-15 | 2024-02-07 | 237
| Check Survey in Bhandu area Hold due court case | 65/7 | Check Survey |  | 2023-06-15 | 2024-02-07 | 237
| Check Survey in Bhandu area Hold due court case | 66/0 | Check Survey |  | 2023-06-15 | 2024-10-08 | 481
| Check Survey in Bhandu area Hold due court case | 66/1 | Check Survey |  | 2023-06-15 | 2024-10-08 | 481
| Check Survey in Bhandu area Hold due court case | 66/2 | Check Survey |  | 2023-06-15 | 2024-10-08 | 481
| Check Survey in Bhandu area Hold due court case | 66/3 | Check Survey |  | 2023-06-15 | 2024-10-08 | 481
| Check Survey in Bhandu area Hold due court case | 66/4 | Check Survey |  | 2023-06-15 | 2023-09-23 | 100
| Check Survey in Bhandu area Hold due court case | 67/0 | Check Survey |  | 2023-06-30 | 2023-09-21 | 83
| Check Survey in Bhandu area Hold due court case | 67/1 | Check Survey |  | 2023-06-30 | 2023-09-21 | 83
| Check Survey in Bhandu area Hold due court case | 68/0 | Check Survey |  | 2023-06-30 | 2023-09-21 | 83
| Check Survey in Bhandu area Hold due court case | 68/1 | Check Survey |  | 2023-06-30 | 2023-09-21 | 83
| Check Survey in Bhandu area Hold due court case | 68/2 | Check Survey |  | 2023-06-30 | 2023-09-21 | 83
| Check Survey in Bhandu area Hold due court case | 68/3 | Check Survey |  | 2023-06-30 | 2023-09-21 | 83
| Check Survey in Bhandu area Hold due court case | 68/4 | Check Survey |  | 2023-06-30 | 2023-09-21 | 83
| Check Survey in Bhandu area Hold due court case | 68/5 | Check Survey |  | 2023-06-30 | 2023-09-21 | 83
| Check Survey in Bhandu area Hold due court case | 68/6 | Check Survey |  | 2023-06-30 | 2023-09-21 | 83
| Check Survey in Bhandu area Hold due court case | 69/0 | Check Survey |  | 2023-06-30 | 2023-09-21 | 83
| Luni area hold due to court case | 69/0 | Pit Marking |  | 2023-07-23 | 2024-07-14 | 357
| Luni area hold due to court case | 69/1 | Pit Marking |  | 2023-07-23 | 2024-07-14 | 357
| Luni area hold due to court case | 69/2 | Pit Marking |  | 2023-07-23 | 2024-07-14 | 357
| Luni area hold due to court case | 69/3 | Pit Marking |  | 2023-07-23 | 2024-07-14 | 357
| Luni area hold due to court case | 69/4 | Pit Marking |  | 2023-07-23 | 2024-07-14 | 357
| Luni area hold due to court case | 69/5 | Pit Marking |  | 2023-07-23 | 2024-07-14 | 357
| Luni area hold due to court case | 69/6 | Pit Marking |  | 2023-07-23 | 2024-07-14 | 357
| Luni area hold due to court case | 69/7 | Pit Marking |  | 2023-07-23 | 2024-07-14 | 357
| Luni area hold due to court case | 69/8 | Pit Marking |  | 2023-07-23 | 2024-07-14 | 357
| Luni area hold due to court case | 69/9 | Pit Marking |  | 2023-07-23 | 2024-07-14 | 357
| Hold due high compensation | 59/5 | Excavation |  | 2023-08-02 | 2023-08-26 | 24
| Hold due high compensation | 59/04 | Pit Marking |  | 2023-08-06 | 2024-12-20 | 502
| Hold due high compensation | 58/13 | Pit Marking |  | 2023-08-14 | 2024-12-11 | 485
| Hold due high compensation | 58/04 | Excavation |  | 2023-08-14 | 2023-10-06 | 53
| Hold due ROW | 58/2 | Pit Marking |  | 2023-08-06 | 2023-09-04 | 29
| Luni area hold due to court case | 71/2 | Pit Marking |  | 2023-09-24 | 2024-07-14 | 294
| Hold due ROW | 50/2 | Pit Marking |  | 2023-09-09 | 2024-07-14 | 309
| Hold due ROW | 50/3 | Pit Marking |  | 2023-09-09 | 2023-09-18 | 9
| Hold due ROW | 55/3 | Excavation |  | 2023-09-09 | 2023-09-16 | 7
| Hold due ROW | 55/4 | Pit Marking |  | 2023-09-09 | 2023-09-18 | 9
| Hold due ROW | 55/5 | Pit Marking |  | 2023-09-09 | 2023-09-22 | 13
| Hold due ROW | 55/6 | Pit Marking |  | 2023-09-09 | 2023-09-30 | 21
| Hold due ROW | 56/2 | Excavation |  | 2023-09-22 | 2023-10-05 | 13
| Hold due ROW | 56/5 | Excavation |  | 2023-09-23 | 2023-09-29 | 6
| Hold due ROW | 51/8 | Pit Marking |  | 2023-09-09 | 2023-11-20 | 72
| Hold due ROW | 51/9 | Pit Marking |  | 2023-09-09 | 2023-11-06 | 58
| Hold due ROW | 43/1 | Pit Marking |  | 2023-09-22 | 2023-10-11 | 19
| Luni area hold due to court case | 72/0 | Pit Marking |  | 2023-09-22 | 2024-07-14 | 296
| Luni area hold due to court case | 72/01 | Pit Marking |  | 2023-09-22 | 2023-09-29 | 7
| Luni area hold due to court case | 72/6 | Pit Marking |  | 2023-09-22 | 2024-07-14 | 296
| Luni area hold due to court case | 71/01 | Pit Marking |  | 2023-07-26 | 2023-09-05 | 41
| Hold due ROW | 48/0 | Excavation |  | 2023-11-02 | 2023-11-03 | 1
| Luni area hold due to court case | 71/5 | Earthing |  | 2023-11-07 | 2024-07-14 | 250
| Luni area hold due to court case | 72/1 | Earthing |  | 2023-11-07 | 2024-07-14 | 250
| Hold due ROW | 33/1 | Backfilling |  | 2023-11-08 | 2023-12-01 | 23
| Hold due ROW | 58/2 | Tower Erection |  | 2023-11-20 | 2024-05-04 | 166
| Bhandu area Hold due court case | 63/1 | Pit Marking |  | 2023-11-28 | 2024-07-14 | 229
| Bhandu area Hold due court case | 63/2 | Pit Marking |  | 2023-11-28 | 2024-02-02 | 66
| Bhandu area Hold due court case | 63/3 | Pit Marking |  | 2023-11-28 | 2024-07-14 | 229
| Bhandu area Hold due court case | 63/4 | Pit Marking |  | 2023-11-28 | 2024-07-14 | 229
| Bhandu area Hold due court case | 63/5 | Pit Marking |  | 2023-11-28 | 2024-01-22 | 55
| Bhandu area Hold due court case | 63/6 | Pit Marking |  | 2023-11-28 | 2024-01-22 | 55
| Bhandu area Hold due court case | 67/1 | Pit Marking |  | 2023-11-28 | 2024-07-14 | 229
| Luni area hold due to court case | 68/1 | Pit Marking |  | 2023-11-28 | 2024-07-14 | 229
| Luni area hold due to court case | 68/2 | Pit Marking |  | 2023-11-28 | 2024-07-14 | 229
| Luni area hold due to court case | 68/3 | Pit Marking |  | 2023-11-28 | 2024-07-14 | 229
| Luni area hold due to court case | 68/4 | Pit Marking |  | 2023-11-28 | 2024-07-14 | 229
| Luni area hold due to court case | 68/5 | Pit Marking |  | 2023-11-28 | 2024-07-14 | 229
| Luni area hold due to court case | 68/6 | Pit Marking |  | 2023-11-28 | 2024-07-14 | 229
| Luni area hold due to court case | 71/1 | Tower Erection |  | 2023-12-05 | 2024-01-24 | 50
| Luni area hold due to court case | 71/3 | Tower Erection |  | 2023-12-05 | 2024-07-14 | 222
| Luni area hold due to court case | 71/4 | Tower Erection |  | 2023-12-05 | 2024-07-14 | 222
| Luni area hold due to court case | 71/5 | Tower Erection |  | 2023-12-05 | 2024-07-14 | 222
| Luni area hold due to court case | 72/1 | Tower Erection |  | 2023-12-05 | 2024-07-14 | 222
| Luni area hold due to court case | 72/2 | Tower Erection |  | 2023-12-05 | 2024-07-14 | 222
| Luni area hold due to court case | 72/3 | Tower Erection |  | 2023-12-05 | 2024-07-14 | 222
| Luni area hold due to court case | 72/4 | Tower Erection |  | 2023-12-05 | 2024-07-14 | 222
| Luni area hold due to court case | 72/5 | Tower Erection |  | 2023-12-05 | 2024-01-24 | 50
| Check Survey in Bhandu area Hold due court case | 61/1 | Tower Erection |  | 2023-12-07 | 2023-12-09 | 2
| Check Survey in Bhandu area Hold due court case | 61/2 | Tower Erection |  | 2023-12-07 | 2023-12-09 | 2
| Hold due to ROW | 53/1 | Tower Erection |  | 2024-01-18 | 2024-02-02 | 15
| Hold due to ROW | 41/5 | Tower Erection |  | 2024-01-22 | 2024-01-28 | 6
| Hold due to ROW | 43/6 | Excavation |  | 2024-02-08 | 2024-05-10 | 92
| Hold due to ROW | 47/1 | Excavation |  | 2024-02-08 | 2024-07-14 | 157
| Hold due to ROW | 65/3 | Excavation |  | 2024-02-12 | 2024-02-17 | 5
| Hold due to ROW | 52/3 | Tower Erection |  | 2024-03-11 | 2024-04-25 | 45
| Hold due to ROW | 63/1 | Pit Marking |  | 2024-08-21 | 2024-12-15 | 116
| Hold due to ROW | 63/3 | Pit Marking |  | 2024-08-21 | 2024-12-15 | 116
| Hold due to ROW | 63/4 | Pit Marking |  | 2024-08-21 | 2024-12-15 | 116
1 | Hold due to non-finalization of S/S from Gantry to AP 2. | Gty-2 | Survey |  | 2023-04-25 | 2024-07-15 | 448 | Refer KEC letter dated 02-01-24. | Clear
2 | Delay in approval of check survey from AP 29 to AP 29/7. | 29-29/7 | Survey |  | 2023-10-17 | 2023-10-30 | 14 |  | Clear
3 | Delay in approval of check survey from AP 29/7 to AP 33/0. | 29/7-33 | Survey |  | 2023-10-17 | 2023-10-28 | 12 |  | Clear
4 | Check survey could not be done due to ROW From AP 11 to AP 12. | 11-12 | Survey |  | 2023-10-22 | 2024-04-19 | 181 | Refer KEC letter dated 02-01-24. | Clear
5 | Check survey could not be done due to ROW From AP 12 to AP 13. | 12-13 | Survey |  | 2023-10-22 | 2024-01-06 | 77 | Refer KEC letter dated 02-01-24. | Clear
6 | Check survey could not be done due to ROW From AP 13 to AP 14. | 13-14 | Survey |  | 2023-10-22 | 2024-01-12 | 83 | Refer KEC letter dated 02-01-24. | Clear
7 | Check survey could not be done due to ROW From AP 14 to AP 15. | 14-15 | Survey |  | 2023-10-22 | 2024-01-12 | 83 | Refer KEC letter dated 02-01-24. | Clear
8 | Check survey could not be done due to ROW From AP 15 to AP 16. | 15-16 | Survey |  | 2023-10-22 | 2024-01-13 | 84 | Refer KEC letter dated 02-01-24. | Clear
9 | Check survey could not be done due to ROW From AP 16 to AP 17. | 16-17 | Survey |  | 2023-10-22 | 2024-01-06 | 77 | Refer KEC letter dated 02-01-24. | Clear
10 | Check survey could not be done due to ROW From AP 17 to AP 18. | 17-18 | Survey |  | 2023-10-22 | 2024-01-06 | 77 | Refer KEC letter dated 02-01-24. | Clear
11 | Check survey could not be done due to ROW From AP 18 to AP 19. | 18-19 | Survey |  | 2023-10-22 | 2024-01-06 | 77 | Refer KEC letter dated 02-01-24. | Clear
12 | Check survey could not be done due to ROW From AP 19 to AP 20. | 19-20 | Survey |  | 2023-10-22 | 2024-01-06 | 77 | Refer KEC letter dated 02-01-24. | Clear
13 | Delay in approval of check survey from AP 25 to AP 29. | 25-29 | Survey |  | 2023-10-26 | 2024-01-25 | 92 | SPTL D&E team visited the site for removed the higher side RC, we are awaiting the response from SPTL. On dated 14.01.23 Same are Pending from KEC Engg. Refer KEC Letter Dated. 02.01.24. | Clear
14 | Delay in approval of check survey from AP 2 to AP 8. | 2-8 | Survey |  | 2023-11-08 | 2023-11-24 | 17 |  | Clear
15 | Location no 8/6,8/10,10/0 and 10/5 was spotted under Mines Area in approved Detail Survey, Decision pending at SPTL end From AP 8 to AP 11. | 8-11 | Survey |  | 2023-11-08 | 2024-01-11 | 65 | Refer KEC letter dated 02-01-24. | Clear
16 | Delay in approval of check survey from AP 20 to AP 25. | 20-25 | Survey |  | 2023-11-23 | 2023-12-01 | 9 |  | Clear
17 | ROW at location no 21/8 in PKG G. | 21/8 | Foundation | A.B. Construction | 2023-12-16 | 2023-12-17 | 2 | Reference Email dated 16/12/2023. | Clear
18 | Gang Idle for Full day, as Post completion of location no 24/3 in PKG G by M/S NR Enterprises, Gang shifted at location no 24/4 & 24/5 for Excavation and are found under ROW. Then Shifted at 29/4 of PKG F which is also in Severe ROW. Then Gang with Machinary are shifted at 40 Kms distance at 29/3 PKG G from current location i.e. 29/4 (PKG F). |  | Foundation | N.R. Enterprises | 2023-12-26 | 2023-12-29 | 4 | Idled Resources (Highly Skilled manpower-1, Skilled:- 2, Semi Skilled:- 3, Unskilled:- 8, JCB with operator:- 1, Azax flori with operator:- 1, Tracktor with operator:- 1, Tanker with Operator:- 1, Bolero/Camper with Diesel:- 1) | Clear
19 | ROW in Foundation work in sawan Moolraj village at Loc No 23/6 | 23/6 | Foundation |  | 2023-12-26 | 2025-03-07 | 438 | Email reference dated 09-01-2023 | Clear
20 | ROW in Foundation work in sawan Moolraj village at Loc No 23/7 | 23/7 | Foundation |  | 2023-12-26 | 2025-01-01 | 373 | Email reference dated 09-01-2023 | Clear
21 | ROW in Foundation work in sawan Moolraj village at Loc No 23/8 | 23/8 | Foundation |  | 2023-12-26 | 2024-12-15 | 356 | Email reference dated 09-01-2023 | Clear
22 | ROW in Foundation work in sawan Moolraj village at Loc No 23/9 | 23/9 | Foundation |  | 2023-12-26 |  | 812 | Email reference dated 09-01-2023 | ROW
23 | ROW in Foundation work in sawan Moolraj village at Loc No 23/10 | 23/10 | Foundation |  | 2023-12-26 | 2024-12-15 | 356 | Email reference dated 09-01-2023 | Clear
24 | ROW in Foundation work in sawan Moolraj village at Loc No 23/11 | 23/11 | Foundation |  | 2023-12-26 | 2024-12-15 | 356 | Email reference dated 09-01-2023 | Clear
25 | ROW in Foundation work in sawan Moolraj village at Loc No 24/0 | 24/0 | Foundation |  | 2023-12-26 | 2024-12-10 | 351 | Email reference dated 09-01-2023 | Clear
26 | ROW in Foundation work in sawan Moolraj village at Loc No 24/1 | 24/1 | Foundation |  | 2023-12-26 | 2024-12-01 | 342 | Email reference dated 09-01-2023 | Clear
27 | ROW in Foundation work in sawan Moolraj village at Loc No 24/2 | 24/2 | Foundation |  | 2023-12-26 | 2024-11-08 | 319 | Email reference dated 09-01-2023 | Clear
28 | ROW in Foundation work in sawan Moolraj village at Loc No 24/4 | 24/4 | Foundation | N.R. Enterprises | 2023-12-26 | 2024-12-01 | 342 | Reference Email dated 26/12/2023. Excavation not started due to Frequent obstruction by land owner. | Clear
29 | ROW in Foundation work in sawan Moolraj village at Loc No 24/5 | 24/5 | Foundation | N.R. Enterprises | 2023-12-26 | 2024-12-01 | 342 | Reference Email dated 26/12/2023. Excavation not started due to Frequent obstruction by land owner. | Clear
30 | ROW in Foundation work in sawan Moolraj village at Loc No 24/6 | 24/6 | Foundation |  | 2023-12-26 | 2024-12-01 | 342 | Email reference dated 09-01-2023 | Clear
31 | ROW in Foundation work in sawan Moolraj village at Loc No 25/0 | 25/0 | Foundation |  | 2023-12-26 | 2025-01-01 | 373 | Email reference dated 09-01-2023 | Clear
32 | ROW in Foundation work in sawan Moolraj village at Loc No 25/1 | 25/1 | Foundation |  | 2023-12-26 | 2025-01-02 | 374 | Email reference dated 09-01-2023 | Clear
33 | ROW in Foundation work in sawan Moolraj village at Loc No 25/2 | 25/2 | Foundation |  | 2023-12-26 |  | 812 | Email reference dated 09-01-2023 | ROW
34 | ROW in Foundation work in sawan Moolraj village at Loc No 25/3 | 25/3 | Foundation |  | 2023-12-26 | 2025-01-02 | 374 | Email reference dated 09-01-2023 | Clear
35 | ROW in Foundation work in sawan Moolraj village at Loc No 25/4 | 25/4 | Foundation |  | 2023-12-26 | 2024-02-05 | 42 | Email reference dated 09-01-2023 | Clear
36 | ROW in Foundation work in sawan Moolraj village at Loc No 25/5 | 25/5 | Foundation |  | 2023-12-26 | 2024-12-01 | 342 | Email reference dated 09-01-2023 | Clear
37 | ROW in Foundation work in sawan Moolraj village at Loc No 25/6 | 25/6 | Foundation |  | 2023-12-26 | 2024-12-01 | 342 | Email reference dated 09-01-2023 | Clear
38 | ROW in Foundation work in sawan Moolraj village at Loc No 25/7 | 25/7 | Foundation |  | 2023-12-26 | 2024-02-05 | 42 | Email reference dated 09-01-2023 | Clear
39 | ROW in Foundation work in sawan Moolraj village at Loc No 25/8 | 25/8 | Foundation |  | 2023-12-26 | 2024-05-28 | 155 | Email reference dated 09-01-2023 | Clear
40 | ROW in Foundation work in sawan Moolraj village at Loc No 25/9 | 25/9 | Foundation |  | 2023-12-26 | 2024-05-28 | 155 | Email reference dated 09-01-2023 | Clear
41 | ROW in Foundation work in sawan Moolraj village at Loc No 25/10 | 25/10 | Foundation |  | 2023-12-26 | 2024-05-28 | 155 | Email reference dated 09-01-2023 | Clear
42 | ROW in Foundation work in sawan Moolraj village at Loc No 25/11 | 25/11 | Foundation |  | 2023-12-26 | 2024-12-01 | 342 | Email reference dated 09-01-2023 | Clear
43 | ROW in Foundation work in sawan Moolraj village at Loc No 26/0 | 26/0 | Foundation |  | 2023-12-26 | 2024-12-01 | 342 | Email reference dated 09-01-2023 | Clear
44 | ROW in Foundation work in Dhanpura village at Loc No 28/6 | 28/6 | Foundation |  | 2024-01-06 | 2024-02-06 | 32 |  | Clear
45 | ROW in Foundation work in Dhanpura village at Loc No 28/7 | 28/7 | Foundation |  | 2024-01-06 | 2024-02-12 | 38 | Your email dated 12.02.24 regarding workfront | Clear
46 | ROW in Foundation work in Dhanpura village at Loc No 28/8 | 28/8 | Foundation |  | 2024-01-06 | 2024-02-12 | 38 | Your email dated 12.02.24 regarding workfront | Clear
47 | ROW in Foundation work in Dhanpura village at Loc No 28/9 | 28/9 | Foundation |  | 2024-01-06 | 2025-03-15 | 435 | Your email dated 12.02.24 regarding workfront. Reattempted the same on 09.03.23 but the same was still is ROW. Reattempt at this location location on 09.03.2024 communicated on dated 10.03.2024 regarding Gang movement and challenges in PKG G & PKG F apart from DPR. | Clear
48 | ROW in Foundation work in Dhanpura village at Loc No 29/0 | 29/0 | Foundation |  | 2024-01-06 |  | 801 |  | ROW
49 | ROW in Foundation work in Dhanpura village at Loc No 29/1 | 29/1 | Foundation |  | 2024-01-06 | 2025-04-15 | 466 |  | Clear
50 | ROW in Foundation work in Dhanpura village at Loc No 29/2 | 29/2 | Foundation |  | 2024-01-06 | 2025-03-30 | 450 | Reattempt at this location location on 09.03.2024 communicated on dated 10.03.2024 regarding Gang movement and challenges in PKG G & PKG F apart from DPR. | Clear
51 | ROW in Foundation work in Dhanpura village at Loc No 29/6 | 29/6 | Foundation |  | 2024-01-06 | 2024-01-20 | 15 |  | Clear
52 | ROW in Foundation work in Dhanpura village at Loc No 29/9 | 29/9 | Foundation |  | 2024-01-06 | 2024-02-03 | 29 |  | Clear
53 | ROW in Foundation work in Dhanpura village at Loc No 29/10 | 29/10 | Foundation |  | 2024-01-06 | 2024-02-12 | 38 | Your email dated 12.02.24 regarding workfront | Clear
54 | ROW in Foundation work in Dhanpura village at Loc No 30/0 | 30/0 | Foundation |  | 2024-01-06 | 2024-02-12 | 38 | Your email dated 12.02.24 regarding workfront | Clear
55 | ROW due to objection by land owner in Excavation Works. | 29/4 | Foundation | N.R. Enterprises | 2024-01-10 | 2025-04-03 | 450 |  | Clear
56 | ROW due to objection by land owner in Excavation Works. | 30/3 | Foundation | Bande Bharat | 2024-01-10 | 2024-09-26 | 261 | excavation done but afterthat it is in ROW. | Clear
57 | Gang idled since 11th Jan as clear work Front not available. |  | Foundation | N.R. Enterprises | 2024-01-11 | 2024-01-19 | 9 | Idled Resources (Highly Skilled manpower-1, Skilled:- 2, Semi Skilled:- 4, Unskilled:- 9, JCB with operator:- 1, Azax flori with operator:- 1, Tracktor with operator:- 1, Tanker with Operator:- 1, Bolero/Camper with Diesel:- 2) | Clear
58 | Check Survey Team (along with DGPS) is idle for three days as clear workfront not available. Re-attemped at AP 38-AP39 |  | Survey | Contour ventures private Ltd. | 2024-01-09 | 2024-01-11 | 3 | Idled resouces DGPS With 2 Surveyor alongwith 4 Others Members and 1 Vehicle. Email communication dated 16-01-2023. | Clear
59 | Centre Peg not done due to ROW at Loc no 18/2, 18/3, 18/6 & 18/7. |  | Survey |  | 2024-01-15 | 2024-05-20 | 127 | Email dated 16.01.2024 | Clear
60 | Gang idle for Full day, during starting of excavation work ROW found at loc no 22/7. Gang was shifted at next location 22/8. | 22/7 | Foundation | A.B. Construction | 2024-01-22 | 2024-01-22 | 1 | Email dated 22.01.2024, Idled Resources (Manpower-14,JCB with operator:- 1, Azax flori with operator:- 1, Tracktor with operator:- 1, Tanker with Operator:- 1, Bolero/Camper with Diesel:- 2) | Clear
61 | Gang idle for Full day, during starting of excavation work ROW found at loc no 22/8. Gang was shifted at next location 23/5. | 22/8 | Foundation | A.B. Construction | 2024-01-23 | 2024-01-24 | 2 | Email dated 23.01.2024, Idled Resources (Manpower-14,JCB with operator:- 1, Azax flori with operator:- 1, Tracktor with operator:- 1, Tanker with Operator:- 1, Bolero/Camper with Diesel:- 2) on dated 29.01.2024. | Clear
62 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 26/1 | Foundation |  | 2024-02-01 | 2025-02-18 | 384 |  | Clear
63 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 26/2 | Foundation |  | 2024-02-01 | 2024-12-25 | 329 |  | Clear
64 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 26/3 | Foundation |  | 2024-02-01 | 2025-01-01 | 336 |  | Clear
65 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 26/4 | Foundation |  | 2024-02-01 | 2024-02-12 | 12 | Your email dated 12.02.24 regarding workfront | Clear
66 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 26/5 | Foundation |  | 2024-02-01 | 2024-02-12 | 12 | Your email dated 12.02.24 regarding workfront | Clear
67 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 26/6 | Foundation |  | 2024-02-01 | 2024-02-12 | 12 | Your email dated 12.02.24 regarding workfront | Clear
68 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 26/7 | Foundation |  | 2024-02-01 | 2024-02-12 | 12 | Your email dated 12.02.24 regarding workfront | Clear
69 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 27/0 | Foundation |  | 2024-02-01 | 2024-02-12 | 12 | Your email dated 12.02.24 regarding workfront | Clear
70 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 27/1 | Foundation |  | 2024-02-01 | 2024-02-12 | 12 | Your email dated 12.02.24 regarding workfront | Clear
71 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 27/2 | Foundation |  | 2024-02-01 | 2024-02-12 | 12 | Your email dated 12.02.24 regarding workfront | Clear
72 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 27/3 | Foundation |  | 2024-02-01 | 2024-02-12 | 12 | Your email dated 12.02.24 regarding workfront | Clear
73 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 27/4 | Foundation |  | 2024-02-01 | 2024-02-12 | 12 | Your email dated 12.02.24 regarding workfront | Clear
74 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 27/5 | Foundation |  | 2024-02-01 | 2024-02-12 | 12 | Your email dated 12.02.24 regarding workfront | Clear
75 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 28/0 | Foundation |  | 2024-02-01 | 2024-03-01 | 30 | Your email dated 12.02.24 regarding workfront but during pit marking at 13.02.24 location is still in ROW. Same was informed to you on site as well as in weekly meetings on 13th. And email dated 22.02.24 Sterlite's Part G & F 765KV Fategarh -III Beawar TL | Clear
76 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 28/1 | Foundation |  | 2024-02-01 | 2024-02-12 | 12 | Your email dated 12.02.24 regarding workfront | Clear
77 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 28/2 | Foundation |  | 2024-02-01 | 2024-05-28 | 118 |  | Clear
78 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 28/3 | Foundation |  | 2024-02-01 |  | 775 |  | ROW
79 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 28/4 | Foundation |  | 2024-02-01 |  | 775 |  | ROW
80 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 28/5 | Foundation |  | 2024-02-01 |  | 775 |  | ROW
81 | Row in foundation work due to Obstruction by land owner in pareu Village at loc no 32/6. | 32/6 | Foundation |  | 2024-02-01 | 2024-04-20 | 80 |  | Clear
82 | Row in foundation work due to Obstruction by land owner in pareu Village at loc no 32/8. | 32/8 | Foundation |  | 2024-02-01 | 2024-05-28 | 118 |  | Clear
83 | Work could not be started due to ROW during Excavation. Same was attempted at 2 times. | 22/7 | Foundation |  | 2024-02-01 | 2024-05-28 | 118 | Email dated 18.02.23 regarding Site Visit report. | Clear
84 | Work could not be started due to ROW during Excavation. Same was attempted at 2 times. | 22/8 | Foundation |  | 2024-02-01 | 2024-02-18 | 18 | Email dated 18.02.23 regarding Site Visit report. | Clear
85 | ROW in Pit marking as Landowner not allowing for pit marking. | 23/0 | Foundation |  | 2024-02-12 | 2025-03-12 | 395 | Email dated 18.02.23 regarding Site Visit report. | Clear
86 | Gang idled alongwith machinaries due to clear workfront not available after completion of loc no 21/12 PKG G. | 21/12 | Foundation | Mehai Contruction | 2024-02-20 | 2024-02-21 | 2 | Email dated 20.02.23 regarding DPR. | Clear
87 | Next locations allocated 22/4 & 22/5 (PKG-F) which is 13 Kms from from current locations. additional cost inoccured due to this appr. 50K. After completion of 23/1 (G) |  | Others | AB Construction | 2024-02-24 | 2024-02-24 | 1 | Email dated 24.02.23 regarding DPR. | Clear
88 | Excavation work stopped due to obstruction by land owner. | 10/12 | Foundation | Om Construction | 2024-02-25 | 2024-02-26 | 2 | Email dated 25.02.24 regarding Workfront Delays and Local Villager Interruptions in PKG G & PKG F | Clear
89 | Works stopped. Awaited for nearby locations. 2 teams are available to works in simultaneously are two diffident locations. (Despite the challenges our team have ability for work in two locations simultaneously (as usually done in past week). Due to non-allocation of next location his machinaries along with manpower is idle. 22/2 is also in ROW since 25.02.24 | 22/2 | Foundation | Jai Bhawani | 2024-02-25 | 2024-02-27 | 3 | Email dated 25.02.24 regarding Workfront Delays and Local Villager Interruptions in PKG G & PKG F | Clear
90 | Gang is working on 22/8 (G). Further location is not allocated, due to this JCB is also idle and have ability to execute the works in two locations at a time. |  | Foundation | Majisa Construction | 2024-02-25 | 2024-02-28 | 4 | Email dated 25.02.24 regarding Workfront Delays and Local Villager Interruptions in PKG G & PKG F. DPR dated 28.02.2024 | Clear
91 | Machinaries are idled since 25.02.24 as clear workfront not available. |  | Others | Jai Bhawani | 2024-02-25 | 2024-02-29 | 5 | Email dated 28.02.24. Clearance received on 29.02.2024 | Clear
92 | 6/2 Work stopped due to ROW. Gang along with Machinery are idle. | 6/2 | Foundation | Majisa Construction | 2024-03-02 | 2024-03-05 | 4 | Email dated 02/03/24 regarding Survey & Foundation update (Workfront Delay/Interruptions updates in PKG G & PKG F | Clear
93 | 8/10 Excavation Completed. Further location not available machinery is being idle. |  | Foundation | Mateswari Construction | 2024-03-02 | 2024-03-23 | 22 | Email dated 02/03/24 regarding Survey & Foundation update (Workfront Delay/Interruptions updates in PKG G & PKG F), Next location allocated for excavation 8/8 on 12.03.24 but completion of loc no 8/10 on dated 12.03.23, gang alongwith machinery is idled due to ROW. | Clear
94 | 8/11 Excavation WIP. Manpower is idle as the gang is shifted from 22/2 PKG G which was 55 Kms from Previous location. |  | Foundation | Jai Bhawani | 2024-03-02 | 2024-03-08 | 7 | Email dated 02/03/24 regarding Survey & Foundation update (Workfront Delay/Interruptions updates in PKG G & PKG F | Clear
95 | 10/7 Excavation WIP. Gang idled due to ROW by landowner. Manpower along with machinery are idled. | 10/7 | Foundation | Shri Degrai Enterprises | 2024-03-02 | 2024-03-03 | 2 | Email dated 02/03/24 regarding Survey & Foundation update (Workfront Delay/Interruptions updates in PKG G & PKG F | Clear
96 | 10/12 WIP. Further locations not available due to this machinery is not engaged. |  | Foundation | Om Enterprises | 2024-03-02 | 2024-03-07 | 6 | Email dated 02/03/24 regarding Survey & Foundation update (Workfront Delay/Interruptions updates in PKG G & PKG F | Clear
97 | 27/5 work stopped due to obstruction by land owner. cleraed on 03.03 claimed by SPTL. But when attempted locations is still in ROW. | 27/5 | Foundation | N.R. Enterprises | 2024-03-02 | 2024-03-04 | 3 | Email dated 02/03/24 regarding Survey & Foundation update (Workfront Delay/Interruptions updates in PKG G & PKG F. email dated 18.0324 regarding Work Fronts Availability Section-I & II KEC. | Clear
98 | 10/7 Excavation WIP. Gang idled due to ROW by landowner at 10/14. Manpower along with machinery are idled. | 10/14 | Foundation | Shri Degrai Enterprises | 2024-03-08 | 2024-03-16 | 9 | D.P.R. dated 08.03.2024. | Clear
99 | Further locations allocated was 10/14, 10/10 which was attempted on the same day (i.e. 8.03.24 & 09.03.24 respectively), as he has twice excavator machine and ability of work in different locations simultaneously but due to non-clearance of locations his all (JCB, Pocklain & Ajax Fiori) machineries are idled since 07.09.24. previously, he was idled at 10/7 due to ROW post excavation. |  | Foundation | Shri Degrai Enterprises | 2024-03-08 | 2024-03-23 | 16 | Email communication reference dated 10.03.2024 regarding Gang movement and challenges in PKG G & PKG F. | Clear
100 | A. next locations is still not received due to the same gang along with machineries are complete idle. Today we have reattempted locations no 28/9 & 29/2 of PKG G but the same is still in ROW. |  | Foundation | Bande Bharat | 2024-03-09 | 2024-03-13 | 5 | Email communication reference dated 10.03.2024 regarding Gang movement and challenges in PKG G & PKG F. Next locations 26/4 for Excavation works on dated 13.03.2024. Further Gangs still idled. Gang idled ends on dated 13.03.24. | Clear
101 | locations not available due to the same, machineries is idled since last 6 days whereas gang was engaged in loc no 6/2. He is also shifted from 22/8. Post shifting, idled at 6/2 for 3 days. |  | Foundation | Majisa Construction | 2024-03-09 | 2024-03-12 | 4 | Email communication reference dated 10.03.2024 regarding Gang movement and challenges in PKG G & PKG F. | Clear
102 | location is not allocated, due to this JCB is also idle whereas gangs deployed at 8/11. He is shifted from 22/2 approx. 70 Kms from previous locations. Before that manpower was idled for 6 days due to shifting and non-availability of locations. From dated 15/3/24 Manpower is also idled. |  | Foundation | Jai Bhawani | 2024-03-09 | 2024-03-23 | 15 | Email communication reference dated 10.03.2024 regarding Gang movement and challenges in PKG G & PKG F. | Clear
103 | As this is the new gang which mobilization was completed on dated 09.03.2024 after premedical checkup, his new locations was allocated at location no 10/3 but clearance of this locations is still awaited from SPTL. |  | Foundation | Vijay Enterprises | 2024-03-09 | 2024-03-12 | 4 | Email communication reference dated 10.03.2024 regarding Gang movement and challenges in PKG G & PKG F. | Clear
104 | Excavation work stopped due to obstruction by land owner at loc no 10/10. Gang alongwith machineries are completely idled. | 10/10 | Foundation | Shri Degrai Enterprises | 2024-03-09 | 2024-04-08 | 31 | Email communication reference dated 10.03.2024 regarding Gang movement and challenges in PKG G & PKG F. Manpower idle removal on 14.3.24. whereas Machineries idle continious. | Clear
105 | Machinery along with manpower idle due to next location not allocated. |  | Foundation | R.D. Enterprises | 2024-03-11 | 2024-03-15 | 5 | Email dated 11/03/24 regarding DPR. Manpower idled on 11/3/24 whereas from 12/3/24 manpower alongwith machineries are completely idled. Further machinery idled clear on 12.03.24 and Gang is still idle. | Clear
106 | Works stopped due to ROW. Manpower & machinery are idled at 10/3. | 10/3 | Foundation | Vijay Enterprises | 2024-03-14 | 2024-03-18 | 5 | D.P.R. dated 14.03.2024. | Clear
107 | Further Location not available due to the same Gang idle whereas machinery engaged in Excavation at 8/1. |  | Foundation | Majisa Construction | 2024-03-14 | 2024-03-14 | 1 | D.P.R. dated 14.03.2024. | Clear
108 | Works stopped due to ROW at location No 8/1. | 8/1 | Foundation | Majisa Construction | 2024-03-15 | 2024-03-16 | 2 | D.P.R. dated 16.03.2024. | Clear
109 | Foundation works not started due to ROW at 22/3 | 22/3 | Foundation | Majisa Construction | 2024-03-18 | 2025-04-17 | 396 | Email dated 18.03.24 regarding Work Fronts Availability Section-I & II KEC. Gang left the site after attempting of this locations. | Clear
110 | Foundation works stopped by local villegers on regular basis at location no 10/7. On dated 17.03.24 total 2 hours propgress hampered due to the same and 18.03.24, Works contiously stopped after 12:00 P.M.. | 10/7 | Foundation | Shri Degrai Enterprises | 2024-03-17 | 2024-03-22 | 6 | email dated 18.03.23 regarding Work Fronts Availability Section-I & II KEC | Clear
111 | Foundation works stopped by local villegers at location no 10/14. | 10/14 | Foundation | Shri Degrai Enterprises | 2024-03-18 | 2024-03-31 | 14 | email dated 19.03.23 regarding SPTL Work Stopped in both Package G & F. Along with DPR. | Clear
112 | works stopped due to frequent obstruction by local villagers for engagement of vehicle. | 8/1 | Foundation | Mateswari Construction | 2024-04-20 | 2024-04-21 | 2 | Email dated 19.04.2024 regarding Work stoppages by local leaders. | Clear
113 | works stopped due to frequent obstruction by local villagers for engagement of vehicle. | 10/6 | Foundation | Shri Degrai Enterprises | 2024-04-20 | 2024-04-21 | 2 | Email dated 19.04.2024 regarding Work stoppages by local leaders. | Clear
114 | works stopped by 7 local indivisuals due to frequent obstruction by local villagers | 14/1 | Foundation | Majisa Construction | 2024-05-21 | 2024-05-27 | 7 | email dated 21.05.24 regarding Intimation for hindrance occurred at loc no 14/1_PKG G. | Clear
115 | Works stopped due to ROW by land owners. | 14/5 | Foundation | Majisa Construction | 2024-05-31 | 2024-06-10 | 11 | DPR email on regular basis. | Clear
116 | Works stopped due to ROW by land owners. | 14/4 | Foundation | Majisa Construction | 2024-06-10 | 2024-06-10 | 1 | DPR email on regular basis. | Clear
117 | 25/8 Works stopped due to ROW. | 25/8 | Foundation | Departmental Gang | 2024-06-24 | 2024-06-27 | 4 | DPR email on regular basis. | Clear
118 | furthermore 25/9 not started due to ROW. | 25/9 | Foundation | Departmental Gang | 2024-06-24 | 2024-06-25 | 2 | DPR email on regular basis. | Clear
119 | Works not started due to ROW. | 10/8 | Foundation | Jai Bhawani | 2024-07-04 | 2024-09-08 | 67 |  | Clear
120 | Works not started due to ROW. | 10/11 | Foundation | Jai Bhawani | 2024-07-04 | 2024-08-14 | 42 |  | Clear
121 | Works not started due to ROW. | 17/0 | Foundation | Vibe Infra | 2024-07-04 | 2024-07-09 | 6 |  | Clear
122 | Works not started due to ROW. | 17/1 | Foundation | Vibe Infra | 2024-07-04 | 2024-09-10 | 69 |  | Clear
123 | No work-done due to Continuous rain at location | 11/7 | Foundation | R.K. Construction | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis. | Clear
124 | No work-done due to Continuous rain at location | 11/5 | Foundation | MCI | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis. | Clear
125 | No work-done due to Continuous rain at location | 15/2 | Foundation | Om Enterprises | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis. | Clear
126 | No work-done due to Continuous rain at location | 19/13 | Foundation | RBM Construction | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis. | Clear
127 | No work-done due to Continuous rain at location | 19/14 | Foundation | RBM Construction | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis. | Clear
128 | No work-done due to Continuous rain at location | 26/6 | Foundation | Departmental Gang | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis. | Clear
129 | No work-done due to Continuous rain at location | 32/6 | Erection | Yogendra Mahto | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis. | Clear
130 | No work-done due to Continuous rain at location | 31/4 | Erection | Sanjay Mahto | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis. | Clear
131 | Excavation works stopped due to ROW. | 21/2 | Foundation | RBM Construction | 2024-08-10 | 2024-08-11 | 2 | DPR email on regular basis. | Clear
132 | Location not clear for erection worksas this location is in ROW. | 14/3 | Erection |  | 2024-08-25 |  | 569 | DPR email on regular basis. | ROW
133 | Works stopped due to ROW. JCB idle for full day. | 15/6 | Foundation | Majisa Construction | 2024-08-27 | 2024-08-30 | 4 | DPR email on regular basis. | Clear
134 | Works stopped due to ROW. Gang idle. | 10/19 | Erection | Bina Devi | 2024-09-10 | 2024-09-12 | 3 | DPR email on regular basis. | Clear
135 | Works stopped due to ROW. Gang idle. Further gang shifted on next location on dated 14.09.2024. | 11/4 | Erection | Patel Construction | 2024-09-11 |  | 552 | DPR email on regular basis. | ROW
136 | Works not started due to ROW at loc no 19/9. | 19/9 | Foundation | Vibe Infra | 2024-09-15 | 2024-10-03 | 19 | DPR email on regular basis. | Clear
137 | Block Level done. ROW for half day. | 15/6 | Foundation | Om Enterprises | 2024-09-28 | 2024-09-28 | 1 | DPR email on regular basis. | Clear
138 | Full day ROW. 9 nos manpower alongwith JCB (JCB idled since last 6 days). ROW cleared on dated 29.09.2024 after 2nd half. | 17/3 | Foundation | sidhi Vinayak | 2024-08-28 | 2024-09-29 | 33 | DPR email on regular basis. | Clear
139 | Gang (9 Manpower) alongwith poclain/tracktor idled for full day. | 19/8 | Foundation | Vibe Infra | 2024-09-29 |  | 534 | DPR email on regular basis. | ROW
140 | Full day ROW at loc no 12/0 | 12/0 | Foundation | Vibe Infra | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis. | Clear
141 | 11/9 WIP. No work due to ROW. | 11/9 | Erection | Rafikul Islam | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis. | Clear
142 | Work not done due to ROW. | 15/5 | Foundation |  | 2024-11-01 | 2025-06-30 | 242 | DPR email on regular basis. | Clear
143 | Work not done due to ROW. | 15/8 | Erection |  | 2024-11-01 |  | 501 | DPR email on regular basis. | ROW
144 | Work not done due to ROW. | 16/1 | Erection |  | 2024-11-01 |  | 501 | DPR email on regular basis. | ROW
145 | Work not done due to ROW. | 16/6 | Erection |  | 2024-11-01 |  | 501 | DPR email on regular basis. | ROW
146 | Work not done due to ROW. | 14/0 | Erection |  | 2024-11-01 |  | 501 | DPR email on regular basis. | ROW
147 | Work not done due to ROW. | 27/3 | Foundation | Parsuram Sai | 2024-11-21 | 2024-11-20 | 0 | DPR email on regular basis. | Clear
148 | Ereection works stopped due to ROW. At loc no 19/7. Manhandling encountered at this locations. | 19/7 | Erection | Nirmal Mahto | 2024-11-24 | 2024-11-27 | 4 | DPR email on regular basis. | Clear
149 | Works Stopped due to ROW. Location completed but unaable to release T&P due to ROW. | 11/13 | Erection | Bina Devi | 2024-12-30 | 2024-12-30 | 1 | DPR email on regular basis. | Clear
150 | Works can not done due to ROW. | 1/0 | Foundation |  | 2024-12-01 | 2025-02-03 | 65 | DPR email on regular basis. | Clear
151 | Works can not done due to ROW. | 1A/0 | Foundation |  | 2024-12-01 | 2025-01-15 | 46 | DPR email on regular basis. | Clear
152 | Works can not done due to ROW. | 1A/1 | Foundation |  | 2024-12-01 | 2025-01-31 | 62 | DPR email on regular basis. | Clear
153 | Works can not done due to ROW. | 1A/2 | Foundation |  | 2024-12-01 | 2025-03-04 | 94 | DPR email on regular basis. | Clear
154 | Works can not done due to ROW. | 1A/3 | Foundation |  | 2024-12-01 | 2025-01-24 | 55 | DPR email on regular basis. | Clear
155 | Works can not done due to ROW. | 1A/4 | Foundation |  | 2024-12-01 | 2025-01-31 | 62 | DPR email on regular basis. | Clear
156 | Works can not done due to ROW. | 1A/5 | Foundation |  | 2024-12-01 | 2025-03-04 | 94 | DPR email on regular basis. | Clear
157 | Works can not done due to ROW. | 1A/6 | Foundation |  | 2024-12-01 | 2025-02-15 | 77 | DPR email on regular basis. | Clear
158 | Works can not done due to ROW. | 1A/7 | Foundation |  | 2024-12-01 | 2025-03-30 | 120 | DPR email on regular basis. | Clear
159 | Works can not done due to ROW. | 2/0 | Foundation |  | 2024-12-01 | 2025-01-15 | 46 | DPR email on regular basis. | Clear
160 | Works can not done due to ROW. | 2/7 | Foundation |  | 2024-12-05 | 2025-03-17 | 103 | DPR email on regular basis. | Clear
161 | Works can not done due to ROW. | 2/8 | Foundation |  | 2024-12-05 | 2025-05-31 | 178 | DPR email on regular basis. | Clear
162 | Works can not done due to ROW. | 2/9 | Foundation |  | 2024-12-05 | 2025-03-03 | 89 | DPR email on regular basis. After pit marking locations in on ROW on dated 30.01.2025. | Clear
163 | Works can not done due to ROW. | 3/0 | Foundation |  | 2024-12-05 | 2025-03-30 | 116 | DPR email on regular basis. | Clear
164 | Works can not done due to ROW. | 4/0 | Foundation |  | 2024-12-05 | 2025-03-12 | 98 | DPR email on regular basis. | Clear
165 | Works can not done due to ROW. | 4/1 | Foundation |  | 2024-12-05 | 2025-05-25 | 172 | DPR email on regular basis. | Clear
166 | Works can not done due to ROW. | 4/2 | Foundation |  | 2024-12-05 |  | 467 | DPR email on regular basis. | ROW
167 | Works can not done due to ROW. | 4/3 | Foundation |  | 2024-12-05 | 2025-05-08 | 155 | DPR email on regular basis. | Clear
168 | Works can not done due to ROW. | 4/4 | Foundation |  | 2024-12-05 | 2025-06-18 | 196 | DPR email on regular basis. | Clear
169 | Works can not done due to ROW. | 5/0 | Foundation |  | 2024-12-05 | 2025-06-18 | 196 | DPR email on regular basis. | Clear
170 | Works can not done due to ROW. | 6/0 | Foundation |  | 2024-12-06 | 2025-04-09 | 125 | DPR email on regular basis. | Clear
171 | Works can not done due to ROW. | 7/0 | Foundation |  | 2024-12-06 | 2025-04-09 | 125 | DPR email on regular basis. | Clear
172 | Works can not done due to ROW. | 8/0 | Foundation |  | 2024-12-06 | 2025-04-09 | 125 | DPR email on regular basis. | Clear
173 | Works can not done due to ROW. | 8/2 | Foundation |  | 2024-12-06 | 2025-07-02 | 209 | DPR email on regular basis. | Clear
174 | Works can not done due to ROW. | 8/3 | Foundation |  | 2024-12-06 | 2025-06-30 | 207 | DPR email on regular basis. | Clear
175 | Works can not done due to ROW. | 8/4 | Foundation |  | 2024-12-06 | 2025-06-30 | 207 | DPR email on regular basis. | Clear
176 | Works can not done due to ROW. | 8/5 | Foundation |  | 2024-12-06 | 2025-06-30 | 207 | DPR email on regular basis. | Clear
177 | Works can not done due to ROW. | 8/12 | Foundation |  | 2024-12-06 | 2025-04-09 | 125 | DPR email on regular basis. | Clear
178 | Works can not done due to ROW. | 9/0 | Foundation |  | 2024-12-06 | 2025-06-30 | 207 | DPR email on regular basis. | Clear
179 | Works can not done due to ROW. | 10/0 | Foundation |  | 2024-12-06 | 2025-06-30 | 207 | DPR email on regular basis. | Clear
180 | Works can not done due to ROW. | 10/1 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
181 | Works can not done due to ROW. | 10/2 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
182 | Works can not done due to ROW. | 10/15 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
183 | Works can not done due to ROW. | 10/16 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
184 | Works can not done due to ROW. | 10/17 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
185 | Works can not done due to ROW. | 10/23 | Foundation |  | 2024-12-06 | 2025-04-09 | 125 | DPR email on regular basis. | Clear
186 | Works can not done due to ROW. | 11/0 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
187 | Works can not done due to ROW. | 11/1 | Foundation |  | 2024-12-06 | 2025-04-09 | 125 | DPR email on regular basis. | Clear
188 | Works can not done due to ROW. | 11/2 | Foundation |  | 2024-12-06 | 2025-04-09 | 125 | DPR email on regular basis. | Clear
189 | Works can not done due to ROW. | 11/3 | Foundation |  | 2024-12-06 | 2025-05-31 | 177 | DPR email on regular basis. | Clear
190 | Works can not done due to ROW. | 17/2 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
191 | Works can not done due to ROW. | 17/4 | Foundation |  | 2024-12-06 | 2025-05-31 | 177 | DPR email on regular basis. | Clear
192 | Works can not done due to ROW. | 17/5 | Foundation |  | 2024-12-06 | 2025-05-31 | 177 | DPR email on regular basis. | Clear
193 | Works can not done due to ROW. | 18/0 | Foundation |  | 2024-12-06 | 2025-07-09 | 216 | DPR email on regular basis. | Clear
194 | Works can not done due to ROW. | 18/1 | Foundation |  | 2024-12-06 | 2025-07-09 | 216 | DPR email on regular basis. | Clear
195 | Works can not done due to ROW. | 18/2 | Foundation |  | 2024-12-06 | 2025-07-09 | 216 | DPR email on regular basis. | Clear
196 | Works can not done due to ROW. | 18/3 | Foundation |  | 2024-12-06 | 2025-07-09 | 216 | DPR email on regular basis. | Clear
197 | Works can not done due to ROW. | 18/4 | Foundation |  | 2024-12-06 | 2025-07-09 | 216 | DPR email on regular basis. | Clear
198 | Works can not done due to ROW. | 18/5 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
199 | Works can not done due to ROW. | 18/6 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
200 | Works can not done due to ROW. | 18/7 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
201 | Works can not done due to ROW. | 18/8 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
202 | Works can not done due to ROW. | 18/9 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
203 | Works can not done due to ROW. | 18/10 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
204 | Works can not done due to ROW. | 19/0 | Foundation |  | 2024-12-06 | 2025-07-09 | 216 | DPR email on regular basis. | Clear
205 | Works can not done due to ROW. | 19/1 | Foundation |  | 2024-12-06 | 2025-07-09 | 216 | DPR email on regular basis. | Clear
206 | Works can not done due to ROW. | 19/10 | Foundation |  | 2024-12-06 | 2025-04-09 | 125 | DPR email on regular basis. | Clear
207 | Works can not done due to ROW. | 19/11 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
208 | Works can not done due to ROW. | 19/12 | Foundation |  | 2024-12-06 |  | 466 | DPR email on regular basis. | ROW
209 | Works can not done due to ROW. | 20/0 | Foundation |  | 2024-12-06 | 2025-04-09 | 125 | DPR email on regular basis. | Clear
210 | Works can not done due to ROW. | 21/0 | Foundation |  | 2024-12-06 | 2025-04-09 | 125 | DPR email on regular basis. | Clear
211 | Works can not done due to ROW. | 22/0 | Foundation |  | 2024-12-06 | 2025-04-09 | 125 | DPR email on regular basis. | Clear
212 | Works can not done due to ROW. | 22/1 | Foundation |  | 2024-12-06 | 2025-04-09 | 125 | DPR email on regular basis. | Clear
213 | Works can not done due to ROW. | 22/6 | Foundation |  | 2024-12-06 | 2025-01-27 | 53 | DPR email on regular basis. | Clear
214 | Works can not done due to ROW. | 22/7 | Foundation |  | 2024-12-06 | 2025-01-13 | 39 | DPR email on regular basis. | Clear
215 | Works can not done due to ROW. | 23/4 | Foundation |  | 2024-12-06 | 2025-06-03 | 180 | DPR email on regular basis. | Clear
216 | Works can not done due to ROW. | 26/5 | Foundation |  | 2024-12-06 | 2025-01-08 | 34 | DPR email on regular basis. | Clear
217 | Works can not done due to ROW. | 28/2 | Foundation |  | 2024-12-06 | 2025-02-19 | 76 | DPR email on regular basis. | Clear
218 | Works can not done due to ROW. | 28/6 | Foundation |  | 2024-12-06 | 2025-06-27 | 204 | DPR email on regular basis. | Clear
219 | Works can not done due to ROW. | 28/7 | Foundation |  | 2024-12-06 | 2025-06-27 | 204 | DPR email on regular basis. | Clear
220 | Works can not done due to ROW. | 28/8 | Foundation |  | 2024-12-06 | 2025-03-31 | 116 | DPR email on regular basis. | Clear
221 | Work Hold due to unavailabilty of 33kv Shutdown | 66/3 | Erection |  | 2025-01-19 | 2025-06-09 | 142 | DPR email on regular basis. | Clear
222 | ROW since 02.04.25 | 64/9 | Erection |  | 2025-04-02 | 2025-05-23 | 52 | DPR email on regular basis. | Clear
223 | Works can not done due to ROW. | 64/0 | Erection |  | 2025-04-22 | 2025-06-06 | 46 | DPR email on regular basis. | Clear
224 | Works can not done due to ROW. | 64/1 | Erection |  | 2025-04-22 | 2025-06-15 | 55 | DPR email on regular basis. | Clear
225 | Works can not done due to ROW. | 64/2 | Erection |  | 2025-04-22 | 2025-05-12 | 21 | DPR email on regular basis. | Clear
226 | Works can not done due to ROW. | 64/3 | Erection |  | 2025-04-22 | 2025-06-15 | 55 | DPR email on regular basis. | Clear
227 | Works can not done due to ROW. | 64/4 | Erection |  | 2025-04-22 | 2025-07-18 | 88 | DPR email on regular basis. | Clear
228 | Works can not done due to ROW. | 64/5 | Erection |  | 2025-04-22 | 2025-06-08 | 48 | DPR email on regular basis. | Clear
229 | Works can not done due to ROW. | 64/6 | Erection |  | 2025-04-22 | 2025-05-12 | 21 | DPR email on regular basis. | Clear
230 | Works can not done due to ROW. | 64/7 | Erection |  | 2025-04-22 | 2025-06-22 | 62 | DPR email on regular basis. | Clear
231 | Works can not done due to ROW. | 64/8 | Erection |  | 2025-04-22 | 2025-05-31 | 40 | DPR email on regular basis. | Clear
232 | Works can not done due to ROW. | 64/9 | Erection |  | 2025-04-02 | 2025-05-12 | 41 | DPR email on regular basis. | Clear
233 | Works can not done due to ROW. | 65/0 | Erection |  | 2025-04-22 | 2025-06-19 | 59 | DPR email on regular basis. | Clear
234 | Works can not done due to ROW. | 65/1 | Erection |  | 2025-04-22 | 2025-07-05 | 75 | DPR email on regular basis. | Clear
235 | Works can not done due to ROW. | 65/2 | Erection |  | 2025-04-22 | 2025-07-05 | 75 | DPR email on regular basis. | Clear
236 | Works can not done due to ROW. | 8/11 | Erection |  | 2025-07-12 | 2025-07-14 | 3 | DPR email on regular basis. | Clear
237 | Works can not done due to ROW. | 1A/5 | Erection |  | 2025-07-12 | 2025-07-25 | 14 | DPR email on regular basis. | Clear
238 | Works can not done due to ROW. | 25/1 | Erection |  | 2025-07-14 | 2025-07-27 | 14 | DPR email on regular basis. | Clear
239 | Works can not done due to ROW. | 13/4 | Erection |  | 2025-07-14 |  | 246 | DPR email on regular basis. | ROW
240 | Works can not done due to ROW. | 19/0 | Foundation |  | 2025-07-14 | 2025-07-29 | 16 | DPR email on regular basis. | Clear
241 | Works can not done due to ROW. | 19/1 | Foundation |  | 2025-07-14 |  | 246 | DPR email on regular basis. | ROW
244 | Works can not done due to ROW. | 32/8 | Erection | 2025-07-20 | 2025-08-01 | 2025-08-23 | 23 | DPR email on regular basis. | Clear
246 | Works can not done due to ROW. | 30/3 | Erection | 2025-07-20 | 2025-08-01 |  | 228 | DPR email on regular basis. | ROW
247 | Works can not done due to ROW. | 28/7 | Erection | 2025-07-20 | 2025-08-01 | 2025-09-01 | 32 | DPR email on regular basis. | Clear
248 | Works can not done due to ROW. | 27/3 | Erection | 2025-07-20 | 2025-07-01 | 2025-07-30 | 30 | DPR email on regular basis. | Clear
249 | Works can not done due to ROW. | 25/2 | Erection | 2025-07-20 | 2025-07-01 | 2025-08-21 | 52 | DPR email on regular basis. | Clear
250 | Works can not done due to ROW. | 8/4 | Erection | 2025-07-20 | 2025-07-01 | 2025-08-21 | 52 | DPR email on regular basis. | Clear
251 | Works can not done due to ROW. | 8/5 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
252 | Works can not done due to ROW. | 8/7 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
254 | Works can not done due to ROW. | 10/1 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
255 | Works can not done due to ROW. | 10/22 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
258 | Works can not done due to ROW. | 17/1 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
259 | Works can not done due to ROW. | 17/3 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
262 | Works can not done due to ROW. | 21/13 | Erection | 2025-07-20 | 2025-07-01 | 2025-09-01 | 63 | DPR email on regular basis. | Clear
263 | Works can not done due to ROW. | 21/11 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
264 | Works can not done due to ROW. | 21/10 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
265 | Works can not done due to ROW. | 21/9 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
267 | Works can not done due to ROW. | 14/6 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
270 | Works can not done due to ROW. | 14/3 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
271 | Works can not done due to ROW. | 13/3 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
272 | Works can not done due to ROW. | 13/4 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
273 | Works can not done due to ROW. | 13/2 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
274 | Works can not done due to ROW. | 11/10 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
275 | Works can not done due to ROW. | 11/3 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
276 | Works can not done due to ROW. | 11/2 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
277 | Works can not done due to ROW. | 9/0 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
278 | Works can not done due to ROW. | 8/12 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
279 | Works can not done due to ROW. | 8/2 | Erection | 2025-07-20 | 2025-07-01 | 2025-09-02 | 64 | DPR email on regular basis. | Clear
280 | Works can not done due to ROW. | 8/8 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
281 | Works can not done due to ROW. | 2/6 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
282 | Works can not done due to ROW. | 2/7 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
283 | Works can not done due to ROW. | 2/4 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
284 | Works can not done due to ROW. | 2/3 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
286 | Works can not done due to ROW. | 2/1 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
287 | Works can not done due to ROW. | 2/2 | Erection | 2025-07-20 | 2025-07-01 | 2025-09-02 | 64 | DPR email on regular basis. | Clear
288 | Works can not done due to ROW. | 3/0 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
289 | Works can not done due to ROW. | 19/2 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
290 | Works can not done due to ROW. | 19/3 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
291 | Works can not done due to ROW. | 19/4 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
292 | Works can not done due to ROW. | 19/9 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
293 | Works can not done due to ROW. | 19/6 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
294 | Works can not done due to ROW. | 19/5 | Erection | 2025-07-20 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
295 | Works can not done due to ROW. | 8/3 | Foundation | 2024-12-06 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
296 | Works can not done due to ROW. | 10/2 | Foundation | 2024-12-06 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
297 | Works can not done due to ROW. | 10/15 | Foundation | 2024-12-06 | 2025-07-01 | 2025-08-29 | 60 | DPR email on regular basis. | Clear
298 | Works can not done due to ROW. | 10/16 | Foundation | 2024-12-06 | 2025-07-01 | 2025-08-29 | 60 | DPR email on regular basis. | Clear
303 | Works can not done due to ROW. | 17/2 | Foundation | 2024-12-06 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
304 | Works can not done due to ROW. | 18/4 | Foundation | 2024-12-06 | 2025-07-01 | 2025-08-20 | 51 | DPR email on regular basis. | Clear
305 | Works can not done due to ROW. | 18/5 | Foundation | 2024-12-06 | 2025-07-01 | 2025-08-20 | 51 | DPR email on regular basis. | Clear
306 | Works can not done due to ROW. | 18/6 | Foundation | 2024-12-06 | 2025-07-01 | 2025-08-20 | 51 | DPR email on regular basis. | Clear
307 | Works can not done due to ROW. | 18/7 | Foundation | 2024-12-06 | 2025-07-01 | 2025-09-20 | 82 | DPR email on regular basis. | Clear
308 | Works can not done due to ROW. | 18/9 | Foundation | 2024-12-06 | 2025-07-01 | 2025-08-18 | 49 | DPR email on regular basis. | Clear
309 | Works can not done due to ROW. | 18/10 | Foundation | 2024-12-06 | 2025-07-01 | 2025-08-29 | 60 | DPR email on regular basis. | Clear
311 | Works can not done due to ROW. | 19/1 | Foundation | 2024-12-06 | 2025-07-01 | 2025-09-03 | 65 | DPR email on regular basis. | Clear
312 | Works can not done due to ROW. | 19/8 | Foundation | 2024-12-06 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
313 | Works can not done due to ROW. | 19/10 | Foundation | 2024-12-06 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
314 | Works can not done due to ROW. | 19/11 | Foundation | 2024-12-06 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
315 | Works can not done due to ROW. | 19/12 | Foundation | 2024-12-06 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
316 | Works can not done due to ROW. | 23/9 | Foundation | 2024-12-06 | 2025-07-01 |  | 259 | DPR email on regular basis. | ROW
317 | [8 empty] | ROW
318 | [8 empty] | ROW
319 | [8 empty] | ROW
320 | [8 empty] | ROW
321 | [8 empty] | ROW
322 | [8 empty] | ROW
323 | [8 empty] | ROW
324 | [8 empty] | ROW
325 | [8 empty] | ROW
326 | [8 empty] | ROW
327 | [8 empty] | ROW
328 | [8 empty] | ROW
329 | [8 empty] | ROW
330 | [8 empty] | ROW
331 | [8 empty] | ROW
332 | [8 empty] | ROW
333 | [8 empty] | ROW
334 | [8 empty] | ROW
335 | [8 empty] | ROW
336 | [8 empty] | ROW
337 | [8 empty] | ROW
338 | [8 empty] | ROW
339 | [8 empty] | ROW
340 | [8 empty] | ROW
341 | [8 empty] | ROW
342 | [8 empty] | ROW
343 | [8 empty] | ROW
344 | [8 empty] | ROW
345 | [8 empty] | ROW
346 | [8 empty] | ROW
347 | [8 empty] | ROW
348 | [8 empty] | ROW
349 | [8 empty] | ROW
350 | [8 empty] | ROW
351 | [8 empty] | ROW
352 | [8 empty] | ROW
353 | [8 empty] | ROW
354 | [8 empty] | ROW
355 | [8 empty] | ROW
356 | [8 empty] | ROW
357 | [8 empty] | ROW
358 | [8 empty] | ROW
359 | [8 empty] | ROW
360 | [8 empty] | ROW
361 | [8 empty] | ROW
362 | [8 empty] | ROW
363 | [8 empty] | ROW
364 | [8 empty] | ROW
365 | [8 empty] | ROW
366 | [8 empty] | ROW
367 | [8 empty] | ROW
368 | [8 empty] | ROW
369 | [8 empty] | ROW
370 | [8 empty] | ROW
371 | [8 empty] | ROW
372 | [8 empty] | ROW
373 | [8 empty] | ROW
374 | [8 empty] | ROW
375 | [8 empty] | ROW
376 | [8 empty] | ROW
377 | [8 empty] | ROW
378 | [8 empty] | ROW
379 | [8 empty] | ROW
380 | [8 empty] | ROW
381 | [8 empty] | ROW
382 | [8 empty] | ROW
383 | [8 empty] | ROW
384 | [8 empty] | ROW
385 | [8 empty] | ROW
386 | [8 empty] | ROW
387 | [8 empty] | ROW
388 | [8 empty] | ROW
389 | [8 empty] | ROW
390 | [8 empty] | ROW
391 | [8 empty] | ROW
392 | [8 empty] | ROW
393 | [8 empty] | ROW
394 | [8 empty] | ROW
395 | [8 empty] | ROW
396 | [8 empty] | ROW
397 | [8 empty] | ROW
398 | [8 empty] | ROW
399 | [8 empty] | ROW
400 | [8 empty] | ROW
401 | [8 empty] | ROW
402 | [8 empty] | ROW
403 | [8 empty] | ROW
404 | [8 empty] | ROW
405 | [8 empty] | ROW
406 | [8 empty] | ROW
407 | [8 empty] | ROW
408 | [8 empty] | ROW
409 | [8 empty] | ROW
410 | [8 empty] | ROW
411 | [8 empty] | ROW
412 | [8 empty] | ROW
413 | [8 empty] | ROW
414 | [8 empty] | ROW
415 | [8 empty] | ROW
416 | [8 empty] | ROW
417 | [8 empty] | ROW
418 | [8 empty] | ROW
419 | [8 empty] | ROW
420 | [8 empty] | ROW
421 | [8 empty] | ROW
422 | [8 empty] | ROW
423 | [8 empty] | ROW
424 | [8 empty] | ROW
425 | [8 empty] | ROW
426 | [8 empty] | ROW
427 | [8 empty] | ROW
428 | [8 empty] | ROW
429 | [8 empty] | ROW
430 | [8 empty] | ROW
431 | [8 empty] | ROW
432 | [8 empty] | ROW
433 | [8 empty] | ROW
434 | [8 empty] | ROW
435 | [8 empty] | ROW
436 | [8 empty] | ROW
437 | [8 empty] | ROW
438 | [8 empty] | ROW
439 | [8 empty] | ROW
440 | [8 empty] | ROW
441 | [8 empty] | ROW
442 | [8 empty] | ROW
443 | [8 empty] | ROW
444 | [8 empty] | ROW
445 | [8 empty] | ROW
446 | [8 empty] | ROW
447 | [8 empty] | ROW
448 | [8 empty] | ROW
449 | [8 empty] | ROW
450 | [8 empty] | ROW
451 | [8 empty] | ROW
452 | [8 empty] | ROW
453 | [8 empty] | ROW
454 | [8 empty] | ROW
455 | [8 empty] | ROW
456 | [8 empty] | ROW
457 | [8 empty] | ROW
458 | [8 empty] | ROW
459 | [8 empty] | ROW
460 | [8 empty] | ROW
461 | [8 empty] | ROW
462 | [8 empty] | ROW
463 | [8 empty] | ROW
464 | [8 empty] | ROW
465 | [8 empty] | ROW
466 | [8 empty] | ROW
467 | [8 empty] | ROW
468 | [8 empty] | ROW
469 | [8 empty] | ROW
470 | [8 empty] | ROW
471 | [8 empty] | ROW
472 | [8 empty] | ROW
473 | [8 empty] | ROW
474 | [8 empty] | ROW
475 | [8 empty] | ROW
476 | [8 empty] | ROW
477 | [8 empty] | ROW
478 | [8 empty] | ROW
479 | [8 empty] | ROW
480 | [8 empty] | ROW
481 | [8 empty] | ROW
482 | [8 empty] | ROW
483 | [8 empty] | ROW
484 | [8 empty] | ROW
485 | [8 empty] | ROW
486 | [8 empty] | ROW
487 | [8 empty] | ROW
488 | [8 empty] | ROW
489 | [8 empty] | ROW
490 | [8 empty] | ROW
491 | [8 empty] | ROW
492 | [8 empty] | ROW
493 | [8 empty] | ROW
494 | [8 empty] | ROW
495 | [8 empty] | ROW
496 | [8 empty] | ROW
497 | [8 empty] | ROW
498 | [8 empty] | ROW
499 | [8 empty] | ROW
500 | [8 empty] | ROW
501 | [8 empty] | ROW
502 | [8 empty] | ROW
503 | [8 empty] | ROW
504 | [8 empty] | ROW
505 | [8 empty] | ROW
506 | [8 empty] | ROW
507 | [8 empty] | ROW
508 | [8 empty] | ROW
509 | [8 empty] | ROW
510 | [8 empty] | ROW
511 | [8 empty] | ROW
512 | [8 empty] | ROW
513 | [8 empty] | ROW
514 | [8 empty] | ROW
515 | [8 empty] | ROW
516 | [8 empty] | ROW
517 | [8 empty] | ROW
518 | [8 empty] | ROW
519 | [8 empty] | ROW
520 | [8 empty] | ROW
521 | [8 empty] | ROW
522 | [8 empty] | ROW
523 | [8 empty] | ROW
524 | [8 empty] | ROW
525 | [8 empty] | ROW
526 | [8 empty] | ROW
527 | [8 empty] | ROW
528 | [8 empty] | ROW
529 | [8 empty] | ROW
530 | [8 empty] | ROW
531 | [8 empty] | ROW
532 | [8 empty] | ROW
533 | [8 empty] | ROW
534 | [8 empty] | ROW
535 | [8 empty] | ROW
536 | [8 empty] | ROW
537 | [8 empty] | ROW
538 | [8 empty] | ROW
539 | [8 empty] | ROW
540 | [8 empty] | ROW
541 | [8 empty] | ROW
542 | [8 empty] | ROW
543 | [8 empty] | ROW
544 | [8 empty] | ROW
545 | [8 empty] | ROW
546 | [8 empty] | ROW
547 | [8 empty] | ROW
548 | [8 empty] | ROW
549 | [8 empty] | ROW
550 | [8 empty] | ROW
551 | [8 empty] | ROW
552 | [8 empty] | ROW
553 | [8 empty] | ROW
554 | [8 empty] | ROW
555 | [8 empty] | ROW
556 | [8 empty] | ROW
557 | [8 empty] | ROW
558 | [8 empty] | ROW
559 | [8 empty] | ROW
560 | [8 empty] | ROW
561 | [8 empty] | ROW
562 | [8 empty] | ROW
563 | [8 empty] | ROW
564 | [8 empty] | ROW
565 | [8 empty] | ROW
566 | [8 empty] | ROW
567 | [8 empty] | ROW
568 | [8 empty] | ROW
569 | [8 empty] | ROW
570 | [8 empty] | ROW
571 | [8 empty] | ROW
572 | [8 empty] | ROW
573 | [8 empty] | ROW
574 | [8 empty] | ROW
575 | [8 empty] | ROW
576 | [8 empty] | ROW
577 | [8 empty] | ROW
578 | [8 empty] | ROW
579 | [8 empty] | ROW
580 | [8 empty] | ROW
581 | [8 empty] | ROW
582 | [8 empty] | ROW
583 | [8 empty] | ROW
584 | [8 empty] | ROW
585 | [8 empty] | ROW
586 | [8 empty] | ROW
587 | [8 empty] | ROW
588 | [8 empty] | ROW
589 | [8 empty] | ROW
590 | [8 empty] | ROW
591 | [8 empty] | ROW
592 | [8 empty] | ROW
593 | [8 empty] | ROW
594 | [8 empty] | ROW
595 | [8 empty] | ROW
596 | [8 empty] | ROW
597 | [8 empty] | ROW
598 | [8 empty] | ROW
599 | [8 empty] | ROW
600 | [8 empty] | ROW
601 | [8 empty] | ROW
602 | [8 empty] | ROW
603 | [8 empty] | ROW
604 | [8 empty] | ROW
605 | [8 empty] | ROW
606 | [8 empty] | ROW
607 | [8 empty] | ROW
608 | [8 empty] | ROW
609 | [8 empty] | ROW
610 | [8 empty] | ROW
611 | [8 empty] | ROW
612 | [8 empty] | ROW
613 | [8 empty] | ROW
614 | [8 empty] | ROW
615 | [8 empty] | ROW
616 | [8 empty] | ROW
617 | [8 empty] | ROW
618 | [8 empty] | ROW
619 | [8 empty] | ROW
620 | [8 empty] | ROW
621 | [8 empty] | ROW
622 | [8 empty] | ROW
623 | [8 empty] | ROW
624 | [8 empty] | ROW
625 | [8 empty] | ROW
626 | [8 empty] | ROW
627 | [8 empty] | ROW
628 | [8 empty] | ROW
629 | [8 empty] | ROW
630 | [8 empty] | ROW
631 | [8 empty] | ROW
632 | [8 empty] | ROW
633 | [8 empty] | ROW
634 | [8 empty] | ROW
635 | [8 empty] | ROW
636 | [8 empty] | ROW
637 | [8 empty] | ROW
638 | [8 empty] | ROW
639 | [8 empty] | ROW
640 | [8 empty] | ROW
641 | [8 empty] | ROW
642 | [8 empty] | ROW
643 | [8 empty] | ROW
644 | [8 empty] | ROW
645 | [8 empty] | ROW
646 | [8 empty] | ROW
647 | [8 empty] | ROW
648 | [8 empty] | ROW
649 | [8 empty] | ROW
650 | [8 empty] | ROW
651 | [8 empty] | ROW
652 | [8 empty] | ROW
653 | [8 empty] | ROW
654 | [8 empty] | ROW
655 | [8 empty] | ROW
656 | [8 empty] | ROW
657 | [8 empty] | ROW
658 | [8 empty] | ROW
659 | [8 empty] | ROW
660 | [8 empty] | ROW
661 | [8 empty] | ROW
662 | [8 empty] | ROW
663 | [8 empty] | ROW
664 | [8 empty] | ROW
665 | [8 empty] | ROW
666 | [8 empty] | ROW
667 | [8 empty] | ROW
668 | [8 empty] | ROW
669 | [8 empty] | ROW
670 | [8 empty] | ROW
671 | [8 empty] | ROW
672 | [8 empty] | ROW
673 | [8 empty] | ROW
674 | [8 empty] | ROW
675 | [8 empty] | ROW
676 | [8 empty] | ROW
677 | [8 empty] | ROW
678 | [8 empty] | ROW
679 | [8 empty] | ROW
680 | [8 empty] | ROW
681 | [8 empty] | ROW
682 | [8 empty] | ROW
683 | [8 empty] | ROW
684 | [8 empty] | ROW
685 | [8 empty] | ROW
686 | [8 empty] | ROW
687 | [8 empty] | ROW
688 | [8 empty] | ROW
689 | [8 empty] | ROW
690 | [8 empty] | ROW
691 | [8 empty] | ROW
692 | [8 empty] | ROW
693 | [8 empty] | ROW
694 | [8 empty] | ROW
695 | [8 empty] | ROW
696 | [8 empty] | ROW
697 | [8 empty] | ROW
698 | [8 empty] | ROW
699 | [8 empty] | ROW
700 | [8 empty] | ROW
701 | [8 empty] | ROW
702 | [8 empty] | ROW
703 | [8 empty] | ROW
704 | [8 empty] | ROW
705 | [8 empty] | ROW
706 | [8 empty] | ROW
707 | [8 empty] | ROW
708 | [8 empty] | ROW
709 | [8 empty] | ROW
710 | [8 empty] | ROW
711 | [8 empty] | ROW
712 | [8 empty] | ROW
713 | [8 empty] | ROW
714 | [8 empty] | ROW
715 | [8 empty] | ROW
716 | [8 empty] | ROW
717 | [8 empty] | ROW
718 | [8 empty] | ROW
719 | [8 empty] | ROW
720 | [8 empty] | ROW
721 | [8 empty] | ROW
722 | [8 empty] | ROW
723 | [8 empty] | ROW
724 | [8 empty] | ROW
725 | [8 empty] | ROW
726 | [8 empty] | ROW
727 | [8 empty] | ROW
728 | [8 empty] | ROW
729 | [8 empty] | ROW
730 | [8 empty] | ROW
731 | [8 empty] | ROW
732 | [8 empty] | ROW
733 | [8 empty] | ROW
734 | [8 empty] | ROW
735 | [8 empty] | ROW
736 | [8 empty] | ROW
737 | [8 empty] | ROW
738 | [8 empty] | ROW
739 | [8 empty] | ROW
740 | [8 empty] | ROW
741 | [8 empty] | ROW
742 | [8 empty] | ROW
743 | [8 empty] | ROW
744 | [8 empty] | ROW
745 | [8 empty] | ROW
746 | [8 empty] | ROW
747 | [8 empty] | ROW
748 | [8 empty] | ROW
749 | [8 empty] | ROW
750 | [8 empty] | ROW
751 | [8 empty] | ROW
752 | [8 empty] | ROW
753 | [8 empty] | ROW
754 | [8 empty] | ROW
755 | [8 empty] | ROW
756 | [8 empty] | ROW
757 | [8 empty] | ROW
758 | [8 empty] | ROW
759 | [8 empty] | ROW
760 | [8 empty] | ROW
761 | [8 empty] | ROW
762 | [8 empty] | ROW
763 | [8 empty] | ROW
764 | [8 empty] | ROW
765 | [8 empty] | ROW
766 | [8 empty] | ROW
767 | [8 empty] | ROW
768 | [8 empty] | ROW
769 | [8 empty] | ROW
770 | [8 empty] | ROW
771 | [8 empty] | ROW
772 | [8 empty] | ROW
773 | [8 empty] | ROW
774 | [8 empty] | ROW
775 | [8 empty] | ROW
776 | [8 empty] | ROW
777 | [8 empty] | ROW
778 | [8 empty] | ROW
779 | [8 empty] | ROW
780 | [8 empty] | ROW
781 | [8 empty] | ROW
782 | [8 empty] | ROW
783 | [8 empty] | ROW
784 | [8 empty] | ROW
785 | [8 empty] | ROW
786 | [8 empty] | ROW
787 | [8 empty] | ROW
788 | [8 empty] | ROW
789 | [8 empty] | ROW
790 | [8 empty] | ROW
791 | [8 empty] | ROW
792 | [8 empty] | ROW
793 | [8 empty] | ROW
794 | [8 empty] | ROW
795 | [8 empty] | ROW
796 | [8 empty] | ROW
797 | [8 empty] | ROW
798 | [8 empty] | ROW
799 | [8 empty] | ROW
800 | [8 empty] | ROW
801 | [8 empty] | ROW
802 | [8 empty] | ROW
803 | [8 empty] | ROW
804 | [8 empty] | ROW
805 | [8 empty] | ROW
806 | [8 empty] | ROW
807 | [8 empty] | ROW
808 | [8 empty] | ROW
809 | [8 empty] | ROW
810 | [8 empty] | ROW
811 | [8 empty] | ROW
812 | [8 empty] | ROW
813 | [8 empty] | ROW
814 | [8 empty] | ROW
815 | [8 empty] | ROW
816 | [8 empty] | ROW
817 | [8 empty] | ROW
818 | [8 empty] | ROW
819 | [8 empty] | ROW
820 | [8 empty] | ROW
821 | [8 empty] | ROW
822 | [8 empty] | ROW
823 | [8 empty] | ROW
824 | [8 empty] | ROW
825 | [8 empty] | ROW
826 | [8 empty] | ROW
827 | [8 empty] | ROW
828 | [8 empty] | ROW
829 | [8 empty] | ROW
830 | [8 empty] | ROW
831 | [8 empty] | ROW
832 | [8 empty] | ROW
833 | [8 empty] | ROW
834 | [8 empty] | ROW
835 | [8 empty] | ROW
836 | [8 empty] | ROW
837 | [8 empty] | ROW
838 | [8 empty] | ROW
839 | [8 empty] | ROW
840 | [8 empty] | ROW
841 | [8 empty] | ROW
842 | [8 empty] | ROW
Formulas:
Period of hindrance = +(IF([LOA No. & Date]=0,TODAY(),[LOA No. & Date])-[Date of occurrence])+1
Note on F125: ====== ID#AAAByZTrI9E Raghav Ranjan (2026-01-08 04:51:09) LOA Start Date

## Benching Status-F (hidden)
RC, Benching & Revetment Locations
Sl No. | RC | Loc No. | Tower Type | CP Position Up/Down | Raised Chimney | Chimney Extension |  |  |  | Submitted Benching Volume (Cum) |  | Approved Benching Volume (Cum) |  | Approval Date | JMC NO | JMC Date
[6 empty] | A | B | C | D | Cutting | Filling | Cutting | Filling
|  | 47 | [7 empty] | 26947.807 |  | 10818.857 |  |  | 10
1 |  | 40/0 | DC2+0 |  |  | 1 | 1 | 0 | 0 | 91.75
2 | Y | 40/1 | DA+6 |  |  | 1 | 2 | 0 | 0 | 153.267
3 |  | 40/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 48.633
4 | Y | 40/3 | DA+6 |  |  | 1 | 2 | 0 | 0 | 238.433
5 | Y | 41/0 | DC1+6 |  |  | 3 | 1 | 0 | 1 | 249.883
6 | Y | 41/1 | DB1+9 | 4 | 4 | 4 | 1 | 6 | 6 | 120.747
7 | Y | 41/2 | DA+0 |  |  | 0 | 0 | 1 | 1 | 1170.806
8 | Y | 42/0 | DC1+0 |  |  | 1 | 0 | 0 | 2 | 339.457
9 | Y | 42/1 | DA+6 |  |  | 1 | 0 | 0 | 0 | 127.8
10 | Y | 42/2 | DA+6 |  |  | 0 | 0 | 1 | 3 | 91.933
11 |  | 42/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 9.463
12 |  | 42/4 | DA+0 |  |  | 0 | 0 | 0 | 0 | 136.417
13 | Y | 42/5 | DA+9 |  |  | 0 | 0 | 0 | 1 | 106.4
14 | Y | 42/6 | DA+0 |  |  | 2 | 1 | 0 | 2 | 144.417
15 |  | 43/0 | DB1+0 |  |  | 0 | 0 | 0 | 0 | 68.726
16 | Y | 43/1 | DA+6 |  |  | 0 | 0 | 3 | 3 | 199.917
17 | Y | 43/2 | DA+3 |  |  | 1 | 0 | 0 | 1 | 189.737
18 | Y | 43/3 | DA+0 |  |  | 0 | 1 | 0 | 0 | 275.117
19 | Y | 43/4 | DA+3 |  |  | 1 | 1 | 0 | 0 | 108.9
20 |  | 43/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 35.95
21 | Y | 43/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 17.8
22 |  | 43/7 | DA+3 | 0.2 |  | 0 | 0 | 0 | 0 | 46.75
23 | Y | 43/8 | DA+9 |  |  | 1 | 0 | 0 | 0 | 120.65
24 |  | 43/9 | DA+9 |  |  | 0 | 0 | 0 | 0 | 61.583
25 | Y | 43/10 | DA+3 |  |  | 3 | 3 | 0 | 0 | 70.8
26 | Y | 43/11 | DA+3 | 1 |  | 2 | 3 | 0 | 1 | 125.717
27 | Y | 44/0 | DB1+3 |  |  | 0 | 1 | 1 | 0 | 227.366
28 |  | 44/1 | DA+0 |  |  | 0 | 0 | 1 | 0 | 516.62
29 |  | 44/2 | DA+0 |  |  | 0 | 0 | 0 | 0 | 145.7
30 | Y | 44/3 | DA+0 |  |  | 2 | 0 | 0 | 1 | 35.453
31 | Y | 44/4 | DA+9 | 3.3 | 3 | 4 | 3 | 3 | 3 | 62.367
32 | Y | 44/5 | DA+9 |  |  | 1 | 3 | 0 | 0 | 476.6
33 | Y | 44/6 | DB1+3 |  |  | 1 | 0 | 0 | 1 | 263.667
34 |  | 44/7 | DA+9 |  |  | 0 | 0 | 0 | 0 | 107.267
35 | Y | 44/8 | DC1+0 |  |  | 1 | 2 | 0 | 1 | 114.075
36 | Y | 44/9 | DA+9 | 3 |  | 4 | 0 | 2 | 6 | 218.923
37 | Y | 44/10 | DA+9 |  |  | 0 | 1 | 0 | 0 | 68.233
38 | Y | 44/11 | DA+0 |  |  | 0 | 1 | 0 | 0 | 148.233
39 | Y | 45/0 | DC2+0 |  |  | 0 | 1 | 0 | 0 | 104.47
40 | Y | 45/1 | DA+0 |  |  | 0 | 0 | 1 | 2 | 329.483
41 | Y | 46/0 | DD60+18 | 3 |  | 0 | 4 | 4 | 0 | 773.08
42 | Y | 47/0 | DD60+18 |  | 2 | 3 | 2 | 2 | 2 | 333.585
43 | Y | 47/1 | DA+6 |  | 1 | 1 | 1 | 2 | 2 | 334.445 |  | 183.244
44 |  | 47/2 | DA+9 |  |  | 0 | 0 | 0 | 0 | 35.008 |  | 14.894 |  |  | JMC-72
45 | Y | 47/3 | DA+9 |  |  | 1 | 2 | 0 | 0 | 351.248 |  | 198.462 |  |  | JMC-73
46 |  | 47/4 | DA+3
47 | Y | 47/5 | DA+0 |  |  | 0 | 1 | 0 | 0 | 151.406 |  | 50.19 |  |  | JMC-74
48 |  | 47/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 214.683 |  | 105.461 |  |  | JMC-68
49 |  | 47/7 | DA+3 |  |  | 0 | 0 | 0 | 0 | 146.833 |  | 85.356 |  |  | JMC-55 | 31-07-24
50 | Y | 47/8 | DA+0 |  |  | 1 | 0 | 0 | 0 | 186.171 |  | 58.541 |  |  | JMC-56 | 31-07-24
51 |  | 47/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 36.917 |  | 21.243 |  |  | JMC-57 | 31-07-24
52 |  | 47/10 | DA+6 |  |  | 0 | 0 | 0 | 0 | 105.1 |  | 44.208 |  |  | JMC-58 | 31-07-24
53 |  | 48/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 271.371 |  | 121.376
54 |  | 48/1 | DA+9 |  |  | 0 | 0 | 0 | 0 | 83.933 |  | 43.92 |  |  | JMC-64 | 31-07-24
55 |  | 49/1 | DA+0 |  |  | 0 | 0 | 0 | 0 | 28.5 |  | 20.37 |  |  | JMC-65 | 31-07-24
56 |  | 49/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 237.2 |  | 152.093 |  |  | JMC-43 | 31-07-24
57 |  | 49/3 | DA+3 |  |  | 0 | 0 | 0 | 0 | 130.95 |  | 59.392 |  |  | JMC-44 | 31-07-24
58 |  | 49/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 52.95 |  | 27.468 |  |  | JMC-45 | 31-07-24
59 |  | 49/5 | DA+3 | 0.1 |  | 0 | 0 | 0 | 0 | 68.133 |  | 33.446 |  |  | JMC-46 | 31-07-24
60 |  | 49/6 | DA+0 | 0.1 |  | 0 | 0 | 0 | 0 | 29.783 |  | 10.948 |  |  | JMC-47 | 31-07-24
61 | Y | 49/7 | DA+3 |  |  | 0 | 3 | 2 | 2 | 190.733 |  | 89.935
62 | Y | 50/0 | DB2+0 |  |  | 0 | 0 | 0 | 1 | 29.469 |  | 6.775
63 | Y | 50/1 | DA+6 |  |  | 1 | 0 | 0 | 0 | 258.417 |  | 126.731 |  |  | JMC-66 | 31-07-24
64 | Y | 50/2 | DA+9 |  | 2 | 2 | 2 | 2 | 2 | 109.183 |  | 50.596 |  |  | JMC-75
65 | Y | 50/3 | DA+6 |  |  | 0 | 0 | 1 | 0 | 82.817 |  | 40.792
66 | Y | 50/4 | DA+9 |  | 3 | 3 | 3 | 4 | 3 | 90.133 |  | 31.88 |  |  | JMC-76
67 | Y | 50/5 | DA+9 |  | 3 | 4 | 3 | 4 | 3 | 82.717 |  | 13.972
68 | Y | 50/6 | DA+9 |  | 3 | 3 | 4 | 3 | 3 | 266.417 |  | 133.278
69 | Y | 50/7 | DA+0 |  |  | 0 | 0 | 0 | 1 | 58.15 |  | 20.044 |  |  | JMC-67 | 31-07-24
70 |  | 50/8 | DA+9 |  |  | 0 | 0 | 0 | 0 | 379.65 |  | 287.607 |  |  | JMC-69
71 | Y | 50/9 | DA+0 |  |  | 0 | 0 | 1 | 0 | 551.811 |  | 283.026
72 | Y | 50/10 | DA+0 |  |  | 0 | 0 | 1 | 0 | 304.834 |  | 114.598
73 |  | 51/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 119.229 |  | 103.624
74 | Y | 51/1 | DA+0 |  |  | 0 | 0 | 1 | 0 | 74.897 |  | 10.113 |  |  | JMC-70
75 |  | 51/2 | DA+0 | -1 |  | 0 | 0 | 0 | 0 | 73.95 |  | 12.784
76 | Y | 52/0 | DC2+0 |  |  | 0 | 0 | 3 | 3 | 474.917 |  | 226.626 |  | 2024-01-09
77 | Y | 52/1 | DA+6 |  |  | 0 | 4 | 0 | 0 | 95.517 |  | 20.215 |  | 2024-01-09
78 | Y | 52/2 | DA+6 |  |  | 0 | 0 | 0 | 3 | 74.467 |  | 56.535 |  | 2024-01-09
79 | Y | 52/3 | DA+9 |  | 3 | 4 | 3 | 3 | 3 | 54.25 |  | 21.459 |  | 2024-01-09 | JMC-71
80 | Y | 52/4 | DA+9 |  |  | 2 | 2 | 0 | 0 | 35.517 |  | 14.371 |  | 2024-01-09
81 | Y | 52/5 | DA+9 |  |  | 0 | 0 | 0 | 1 | 269.167 |  | 177.797 |  | 2024-01-09 | JMC-9 | 22.03.24
82 |  | 52/6 | DA+6 |  |  | 0 | 0 | 0 | 0 | 343.483 |  | 239.936 |  | 2024-01-09 | JMC-10 | 22.03.24
83 | Y | 52/7 | DA+3 |  |  | 0 | 3 | 1 | 0 | 464.317 |  | 306.372 |  | 2024-01-09 | JMC-11 | 22.03.24
84 |  | 52/8 | DA+6 |  |  | 0 | 0 | 0 | 0 | 644.717 |  | 582.599 |  | 2024-01-09 | JMC-12 | 22.03.24
85 |  | 52/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 192.433 |  | 139.028 |  | 2024-01-09 | JMC-13 | 22.03.24
86 | Y | 52/10 | DA+9 |  | 1 | 1 | 2 | 1 | 1 | 270.567 |  | 123.839 |  | 2024-01-09 | JMC-14 | 22.03.24
87 | Y | 53/0 | DB2+9 |  | 4 | 4 | 4 | 4 | 4 | 102.651 |  | 342.89 |  | 2024-01-09
88 | Y | 53/1 | DA+9 |  | 4 | 4 | 4 | 4 | 4 | 511.767 |  | 302.874 |  | 2024-01-09
89 | Y | 53/2 | DA+0 |  |  | 0 | 0 | 0 | 2 | 121.063 |  | 38.768 |  | 2024-01-09
90 | Y | 53/3 | DA+9 |  |  | 0 | 4 | 1 | 0 | 454.927 |  | 204.813 |  | 2024-01-09
91 | Y | 53/4 | DA+0 |  |  | 0 | 2 | 1 | 0 | 686.16 |  | 280.645 |  | 2024-01-09
92 |  | 53/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 104.9 |  | 76.75 |  | 2024-01-09 | JMC-49 | 31-07-24
93 | Y | 53/6 | DA+6 |  |  | 1 | 1 | 3 | 1 | 111.483 |  | 14.573 |  | 2024-01-09
94 |  | 53/7 | DA+0 |  |  | 0 | 0 | 0 | 0 | 245.537 |  | 112.464 |  | 2024-01-09
95 |  | 53/8 | DA+9 |  | 0 | 0 | 0 | 0 | 0 | 326.55 |  | 334.123 |  | 2024-01-09
96 |  | 54/0 | DB1+6 |  |  | 0 | 0 | 0 | 0 | 400.8 |  | 293.967 |  | 2024-01-09
97 | Y | 54/1 | DA+9 |  |  | 1 | 1 | 0 | 0 | 74.4 |  | 17.753 |  | 2024-01-09
98 |  | 54/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 105.35 |  | 63.16 |  | 2024-01-09
99 | Y | 54/3 | DA+6 |  |  | 0 | 2 | 0 | 0 | 106.517 |  | 71.292 |  | 2024-01-09
100 | Y | 54/4 | DA+9 |  | 0 | 1 | 2 | 0 | 0 | 264 |  | 131.156 |  | 2024-01-09
101 | Y | 54/5 | DA+9 |  | 1 | 1 | 3 | 3 | 1 | 210.2 |  | 91.403 |  | 2024-01-09
102 | Y | 55/0 | DB1+6 |  |  | 0 | 1 | 1 | 0 | 375.874 |  | 244.465 |  | 2024-01-09
103 | Y | 55/4 | DA+0 |  |  | 0 | 0 | 0 | 1 | 248.177 |  | 98.757 |  | 2024-01-09 | JMC-15 | 22.03.24
104 | Y | 55/5 | DA+0 |  |  | 0 | 0 | 1 | 3 | 674.16 |  | 250.709 |  | 2024-01-09 | JMC-16 | 22.03.24
105 | Y | 55/6 | DA+0 |  |  | 0 | 0 | 1 | 2 | 100.954 |  | 24.027 |  | 2024-01-09 | JMC-17 | 22.03.24
106 | Y | 55/7 | DA+0 |  |  | 0 | 0 | 1 | 0 | 551.126 |  | 317.518 |  | 2024-01-09 | JMC-18 | 22.03.24
107 | Y | 55/8 | DA+9 |  |  | 0 | 0 | 1 | 0 | 480.283 |  | 241.51 |  | 2024-01-09
108 | Y | 56/0 | DD60+9 |  | 4 | 4 | 6 | 4 | 4 | 454.562 |  | 387.425 |  | 2024-01-09
109 | Y | 57/0 | DD60+9 |  | 0 | 0 | 1 | 1 | 0 | 715.032 |  | 562.651 |  | 2024-01-09
110 |  | 57/1 | DA+3 |  |  | 0 | 0 | 0 | 0 | 38.65 |  | 24.155 |  | 2024-01-09
111 |  | 57/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 64.033 |  | 20.988 |  | 2024-01-09 | JMC-50 | 31-07-24
112 |  | 57/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 91.063 |  | 39.024 |  | 2024-01-09 | JMC-51 | 31-07-24
113 |  | 57/4 | DA+0 |  |  | 0 | 0 | 0 | 0 | 165.446 |  | 77.472 |  | 2024-01-09 | JMC-52 | 31-07-24
114 | Y | 57/5 | DA+3 |  |  | 0 | 0 | 0 | 1 | 114.817 |  | 54.629 |  | 2024-01-09 | JMC-53 | 31-07-24
115 | Y | 57/6 | DA+3 |  |  | 0 | 1 | 0 | 0 | 118.95 |  | 69.342 |  | 2024-01-09 | JMC-54 | 31-07-24
116 |  | 58/0 | DC1+3 |  |  | 0 | 0 | 0 | 0 | 16.509 |  |  |  | 2023-12-22
117 |  | 59/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 97.629 |  | 97.629 |  | 2023-12-22
118 | Y | 59/1 | DA+3 |  |  | 0 | 0 | 0 | 1 | 30.167 |  |  |  | 2023-12-22
119 |  | 59/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 74.35 |  | 57.328 |  | 2023-12-22
120 | Y | 59/3 | DA+3 |  |  | 0 | 0 | 0 | 1 | 29.783 |  |  |  | 2023-12-22
121 |  | 59/7 | DA+3 |  |  | 0 | 0 | 0 | 0 | 88.917 |  | 67.301 |  | 2023-12-22 | JMC-19 | 31-07-24
122 |  | 59/8 | DB1+3 |  |  | 0 | 0 | 0 | 0 | 30.926 |  |  |  | 2023-12-22
123 |  | 59/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 51.683 |  |  |  | 2023-12-22
124 | Y | 59/11 | DA+6 |  |  | 0 | 0 | 2 | 0 | 609.4 |  | 443.002 |  | 2023-12-22
125 |  | 59/12 | DA+6 |  |  | 0 | 0 | 0 | 0 | 69.983 |  |  |  | 2023-12-22
126 | Y | 60/2 | DA+3 |  |  | 2 | 2 | 0 | 0 | 150.115 |  | 67.99 |  | 2023-12-22 | JMC-20 | 31-07-24
127 |  | 61/1 | DA+6 |  |  | 0 | 0 | 0 | 0 | 130.228 |  | 98.667 |  | 2023-12-22 | JMC-21 | 31-07-24
128 | Y | 61/7 | DA+9 |  |  | 0 | 0 | 0 | 1 | 237.78 |  | 155.449 |  | 2023-12-22 | JMC-22 | 31-07-24
129 | Y | 61/8 | DA+6 |  |  | 1 | 2 | 1 | 0 | 139.242 |  | 18.852 |  | 2023-12-22 | JMC-23 | 31-07-24
130 |  | 62/0 | DB2+0 |  |  | 0 | 0 | 0 | 0 | 50.997 |  | 36.79 |  | 2023-12-22 | JMC-62 | 31-07-24
131 | Y | 62/1 | DA+3 |  |  | 0 | 0 | 1 | 2 | 200.388 |  | 135.911 |  | 2023-12-22 | JMC-24 | 31-07-24
132 | Y | 62/2 | DA+3 |  |  | 0 | 1 | 0 | 0 | 22.433 |  |  |  | 2023-12-22
133 |  | 62/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 27.142 |  |  |  | 2023-12-22
134 |  | 62/5 | DA+0 |  |  | 0 | 0 | 0 | 0 | 109.341 |  | 45.234 |  | 2023-12-22 | JMC-25 | 31-07-24
135 |  | 62/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 23.573 |  |  |  | 2023-12-22
136 |  | 63/0 | DC1+0 |  |  | 0 | 0 | 0 | 0 | 199.633 |  | 199.633 |  | 2023-12-22 | JMC-63 | 31-07-24
137 |  | 63/3 | DA+3 |  |  | 0 | 0 | 0 | 0 | 173.683 |  | 140.624 |  | 2023-12-22 | JMC-48 | 31-07-24
138 |  | 63/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 31.908 |  |  |  | 2023-12-22

## Earthing Pkg -G Ist section (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
FOUNDATION
Sl. No. | Cum S No | Location No. | Tower Type | Classification | Type of Earthing | Earthing | Name of Sub-Contractor
1 | 1 | 32/7 | DA+0 | SANDY | Pipe Type | 07.11.23 | Shakti Construction
2 | 2 | 32/1 | DA+9 | SANDY | Pipe Type | 10.11.23 | Shakti Construction
3 | 3 | 32/5 | DA+6 | SANDY | Pipe Type | 10.11.23 | Shakti Construction
4 | 4 | 30/2 | DA+0 | SANDY | Pipe Type | 18.11.23 | Om Const
5 | 5 | 32/0 | DB2+6 | SANDY | Pipe Type | 28.11.23 | Shakti Construction
6 | 6 | 31/3 | DA+0 | SANDY | Pipe Type | 05.12.23 | Shakti Construction

## Earthing balance (hidden)
S no | PKG- G |  | PKG- F
1 | 72/1 | Mahadev engg. | 50/3 | Kalpana Const.
2 | 71/5 | Mahadev engg. | 73/9 | Shakti Const. -2
3 | 43/2 | Sai Infra | 73/2 | Shree Shyam Const.
4 | 43/3 | Sai Infra | 50/6 | Kalpana Const.
5 | 68/3 | Shakti Const. -2
6 | 73/0 | Mahadev engg. - 2
7 | 68/1 | Shakti Const. -2
8 | 66/3 | Shree Shyam Const.
9 | 69/0 | Bhati Const.-2

## Tack Welding - PKG-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Tack Welding
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Tack Welding Status | Name of Sub-Contractor | Ramarks
Feb-24
1 | 1 |  | 59/13 | DA+3 |  | 20.02.24 | 20.02.24 | Done | Suraja Ram
2 | 2 |  | 59/14 | DA+6 |  | 22.02.24 | 22.02.24 | Done | Suraja Ram
3 | 3 |  | 62/5 | DA+0 |  | 27.02.24 | 27.02.24 | Done | Suraja Ram
4 | 4 |  | 63/6 | DA+3 |  | 28.02.24 | 28.02.24 | Done | Suraja Ram
March'24
5 | 1 |  | 63/8 | DA+3 |  | 01.03.24 | 02.03.24 | Done | Suraja Ram
6 | 2 |  | 62/3 | DA+0 |  | 03.02.24 | 03.02.24 | Done | Suraja Ram
7 | 3 |  | 62/4 | DA+3 |  | 04.03.24 | 04.03.24 | Done | Suraja Ram
8 | 4 |  | 59/12 | DA+6 |  | 05.03.24 | 05.03.24 | Done | Suraja Ram
9 | 5 |  | 59/10 | DA+0 |  | 06.03.24 | 06.03.24 | Done | Suraja Ram
10 | 6 |  | 59/9 | DA+3 |  | 07.03.24 | 07.03.24 | Done | Suraja Ram
11 | 7 |  | 60/7 | DA+3 |  | 09.03.24 | 09.03.24 | Done | Suraja Ram
12 | 8 |  | 62/2 | DA+3 |  | 10.03.24 | 10.03.24 | Done | Suraja Ram
13 | 9 |  | 62/7 | DA+3 |  | 11.03.24 | 11.03.24 | Done | Suraja Ram
14 | 10 |  | 64/1 | DA+0 |  | 12.03.24 | 12.03.24 | Done | Suraja Ram
15 | 11 |  | 59/7 | DA+3 |  | 12.03.24 | 12.03.24 | Done | Ramagora
16 | 12 |  | 64/4 | DA+3 |  | 13.03.24 | 13.03.24 | Done | Suraja Ram
17 | 13 |  | 60/11 | DA+3 |  | 15.03.24 | 15.03.24 | Done | Ramagora
18 | 14 |  | 62/8 | DA+0 |  | 15.03.24 | 15.03.24 | Done | Suraja Ram
19 | 15 |  | 65/2 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Suraja Ram
20 | 16 |  | 60/6 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Ramagora
21 | 17 |  | 65/4 | DA+0 |  | 17.03.24 | 17.03.24 | Done | Suraja Ram
22 | 18 |  | 64/5 | DA+3 |  | 18.03.24 | 18.03.24 | Done | Suraja Ram
23 | 19 |  | 62/9 | DA+3 |  | 19.03.24 | 19.03.24 | Done | Suraja Ram
24 | 20 |  | 60/8 | DA+0 |  | 19.03.24 | 19.03.24 | Done | Ramagora
25 | 21 |  | 62/10 | DA+0 |  | 21.03.24 | 21.03.24 | Done | Suraja Ram
26 | 22 |  | 65/3 | DA+0 |  | 22.03.24 | 22.03.24 | Done | Suraja Ram
27 | 23 |  | 59/6 | DA+3 |  | 22.03.24 | 22.03.24 | Done | Ramagora
28 | 24 |  | 60/10 | DA+0 |  | 24.03.24 | 24.03.24 | Done | Suraja Ram
29 | 25 |  | 61/6 | DA+3 |  | 28.03.24 | 28.03.24 | Done | Suraja Ram
30 | 26 |  | 65/5 | DA+0 |  | 29.03.24 | 29.03.24 | Done | Suraja Ram
Apr'24
31 | 1 |  | 64/6 | DA+0 |  | 01.04.24 | 01.04.24 | Done | Suraja Ram
32 | 2 |  | 61/7 | DA+9 |  | 03.04.24 | 03.04.24 | Done | Suraja Ram
33 | 3 |  | 65/6 | DA+0 |  | 04.04.24 | 04.04.24 | Done | Suraja Ram
34 | 4 |  | 64/7 | DA+3 |  | 06.04.24 | 06.04.24 | Done | Suraja Ram
35 | 5 |  | 63/7 | DA+3 |  | 21.04.24 | 22.04.24 | Done | Suraja Ram
36 | 6 |  | 64/9 | DA+3 |  | 24.04.24 | 24.04.24 | Done | Suraja Ram
37 | 7 |  | 61/0 | DB+0 |  | 25.04.24 | 25.04.24 | Done | Ramagora
38 | 8 |  | 65/9 | DA+0 |  | 27.04.24 | 27.04.24 | Done | Suraja Ram
39 | 9 |  | 65/11 | DA+0 |  | 28.04.24 | 28.04.24 | Done | Suraja Ram
40 | 10 |  | 67/2 | DA+0 |  | 29.04.24 | 29.04.24 | Done | Suraja Ram
41 | 11 |  | 61/2 | DA+6 |  | 29.04.24 | 30.04.24 | Done | Ramagora
May'24
42 | 1 |  | 64/10 | DA+3 |  | 05.05.24 | 05.05.24 | Done | Suraja Ram
43 | 2 |  | 67/1 | DA+0 |  | 07.05.24 | 07.05.24 | Done | Suraja Ram
44 | 3 |  | 64/8 | DA+3 |  | 09.05.24 | 09.05.24 | Done | Suraja Ram
45 | 4 |  | 65/1 | DA+0 |  | 10.05.24 | 10.05.24 | Done | Suraja Ram
46 | 5 |  | 65/0 | DB1+0 |  | 10.05.24 | 10.05.24 | Done | Suraja Ram
47 | 6 |  | 61/1 | DA+6 |  | 10.05.24 | 10.05.24 | Done | Ramagora
48 | 7 |  | 60/9 | DA+3 |  | 11.05.24 | 11.05.24 | Done | Ramagora
49 | 8 |  | 63/4 | DA+0 |  | 14.05.24 | 14.05.24 | Done | Suraja Ram
50 | 9 |  | 63/3 | DA+3 |  | 15.05.24 | 15.05.24 | Done | Suraja Ram
51 | 10 |  | 63/5 | DA+3 |  | 16.05.24 | 16.05.24 | Done | Suraja Ram
52 | 11 |  | 61/3 | DA+6 |  | 17.05.24 | 17.05.24 | Done | Ramagora
53 | 12 |  | 62/11 | DA+3 |  | 19.05.24 | 19.05.24 | Done | Suraja Ram
54 | 13 |  | 61/4 | DA+3 |  | 23.05.24 | 23.05.24 | Done | Suraja Ram
55 | 14 |  | 61/5 | DA+3 |  | 25.05.24 | 25.05.24 | Done | Suraja Ram
Jun'24
56 | 1 |  | 64/2 | DA+3 |  | 03.06.24 | 03.06.24 | Done | Suraja Ram
57 | 2 |  | 64/3 | DA+0 |  | 06.06.24 | 06.06.24 | Done | Suraja Ram |  | 125
58 | 3 |  | 64/0 | DB2+0 |  | 06.06.24 | 06.06.24 | Done | Suraja Ram
59 | 4 |  | 61/10 | DA+9 |  | 07.06.24 | 07.06.24 | Done | Suraja Ram
60 | 5 |  | 61/8 | DA+6 |  | 08.06.24 | 08.06.24 | Done | Ramagora
61 | 6 |  | 63/2 | DA+0 |  | 08.06.24 | 08.06.24 | Done | Suraja Ram
62 | 7 |  | 61/9 | DA+0 |  | 09.06.24 | 09.06.24 | Done | Ramagora
63 | 8 |  | 63/1 | DA+3 |  | 09.06.24 | 09.06.24 | Done | Suraja Ram
64 | 9 |  | 59/5 | DA+3 |  | 10.06.24 | 10.06.24 | Done | Ramagora |  | 59/16
65 | 10 |  | 63/0 | DC1+0 |  | 10.06.24 | 11.06.24 | Done | Suraja Ram |  | 48/0
66 | 11 |  | 60/5 | DA+3 |  | 11.06.24 | 11.06.24 | Done | Ramagora
67 | 12 |  | 60/4 | DA+3 |  | 13.06.24 | 13.06.24 | Done | Ramagora
68 | 13 |  | 60/3 | DA+3 |  | 23.06.24 | 23.06.24 | Done | Ramagora
69 | 14 |  | 60/2 | DA+3 |  | 25.06.24 | 25.06.24 | Done | Ramagora
70 | 15 |  | 60/1 | DA+6 |  | 30.06.24 | 30.06.24 | Done | Ramagora
Jul'24
71 | 1 |  | 59/16 | DA+9 |  | 01.07.24 | 01.07.24 | Done | Suraja Ram
72 | 2 |  | 59/15 | DA+6 |  | 02.07.24 | 02.07.24 | Done | Suraja Ram
73 | 3 |  | 60/0 | DC+0 |  | 24.07.24 | 24.07.24 | Done | Suraja Ram
74 | 4 |  | 59/8 | DB1+3 |  | 27.07.24 | 27.07.24 | Done | Suraja Ram
Aug'24
75 | 1 |  | 55/3 | DA+0 |  | 23.08.24 | 23.08.24 | Done | Suraja Ram
76 | 2 |  | 55/4 | DA+0 |  | 24.08.24 | 24.08.24 | Done | Suraja Ram
77 | 4 |  | 57/6 | DA+3 |  | 27.08.24 | 27.08.24 | Done | Suraja Ram
78 | 5 |  | 57/3 | DA+0 |  | 28.08.24 | 28.08.24 | Done | Suraja Ram
79 | 6 |  | 57/4 | DA+0 |  | 30.08.24 | 30.08.24 | Done | Suraja Ram
80 | 7 |  | 57/5 | DA+3 |  | 30.08.24 | 30.08.24 | Done | Suraja Ram
Sept'24
81 | 1 |  | 62/0 | DB2+0 |  | 15.09.24 | 15.09.24 | Done | Suraja Ram
82 | 2 |  | 62/1 | DA+3 |  | 23.09.24 | 24.09.24 | Done | Suraja Ram
83 | 3 |  | 62/6 | DA+3 |  | 25.09.24 | 26.09.24 | Done | Suraja Ram
Oct'24
84 | 1 |  | 57/7 | DA+3 |  | 05.10.24 | 06.10.24 | Done | Suraja Ram
85 | 2 |  | 50/9 | DA+0 |  | 06.10.24 | 07.10.24 | Done | Suraja Ram
86 | 3 |  | 50/10 | DA+3 |  | 09.10.24 | 09.10.24 | Done | Suraja Ram
87 | 4 |  | 50/0 | DB2+0 |  | 10.10.24 | 10.10.24 | Done | Suraja Ram
88 | 5 |  | 50/3 | DA+6 |  | 24.10.24 | 24.10.24 | Done | Suraja Ram
89 | 6 |  | 50/1 | DA+6 |  | 25.10.24 | 25.10.24 | Done | Suraja Ram
90 | 7 |  | 51/1 | DA+0 |  | 25.10.24 | 25.10.24 | Done | Suraja Ram
91 | 8 |  | 50/2 | DA+9 |  | 28.10.24 | 28.10.24 | Done | Suraja Ram
92 | 9 |  | 64/11 | DA+3 |  | 29.10.24 | 29.10.24 | Done | Suraja Ram
Nov'24
93 | 1 |  | 59/11 | DA+6 |  | 11.11.24 | 11.11.24 | Done | Suraja Ram
94 | 2 |  | 50/7 | DA+0 |  | 14.11.24 | 14.11.24 | Done | Suraja Ram
95 | 3 |  | 73/1 | DA+0 |  | 14.11.24 | 14.11.24 | Done | Suraja Ram
96 | 4 |  | 73/2 | DA+0 |  | 19.11.24 | 19.11.24 | Done | Suraja Ram
97 | 5 |  | 73/9 | DA+0 |  | 20.11.24 | 20.11.24 | Done | Suraja Ram
98 | 6 |  | 52/7 | DA+3 |  | 25.11.24 | 25.11.24 | Done | Suraja Ram
99 | 7 |  | 52/6 | DA+6 |  | 25.11.24 | 25.11.24 | Done | Suraja Ram
100 | 8 |  | 52/8 | DA+6 |  | 26.11.24 | 26.11.24 | Done | Suraja Ram
101 | 9 |  | 48/0 | DC2+0 |  | 27.11.24 | 27.11.24 | Done | Suraja Ram
102 | 10 |  | 49/4 | DA+3 |  | 27.11.24 | 27.11.24 | Done | Suraja Ram
103 | 11 |  | 48/1 | DA+9 |  | 29.11.24 | 29.11.24 | Done | Suraja Ram
104 | 12 |  | 47/10 | DA+6 |  | 29.11.24 | 29.11.24 | Done | Suraja Ram
Dec'24
105 | 1 |  | 49/7 | DA+0 |  | 02.12.24 | 02.12.24 | Done | Suraja Ram
106 | 2 |  | 49/6 | DA+0 |  | 03.12.24 | 03.12.24 | Done | Suraja Ram
107 | 3 |  | 49/5 | DA+3 |  | 04.12.24 | 04.12.24 | Done | Suraja Ram
108 | 4 |  | 59/3 | DA+3 |  | 05.12.24 | 05.12.24 | Done | Suraja Ram |  |  | 05.12.24
109 | 5 |  | 59/4 | DA+3 |  | 06.12.24 | 06.12.24 | Done | Suraja Ram
110 | 6 |  | 73/6 | DA+0 |  | 13.12.24 | 13.12.24 | Done | Suraja Ram
111 | 7 |  | 72/3 | DA+3 |  | 17.12.24 | 17.12.24 | Done | Suraja Ram
112 | 8 |  | 59/1 | DA+3 |  | 18.12.24 | 18.12.24 | Done | Suraja Ram
113 | 9 |  | 59/2 | DA+3 |  | 20.12.24 | 20.12.24 | Done | Suraja Ram
114 | 10 |  | 50/8 | DA+9 |  | 23.12.24 | 23.12.24 | Done | Suraja Ram
115 | 11 |  | 73/8 | DA+0 |  | 25.12.24 | 25.12.24 | Done | Suraja Ram
116 | 12 |  | 51/2 | DA+0 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
117 | 13 |  | 49/2 | DA+0 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
118 | 14 |  | 49/3 | DA+3 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
119 | 15 |  | 49/1 | DA+0 |  | 28.12.24 | 28.12.24 | Done | Suraja Ram
2025-01-25
120 | 1 |  | 50/4 | DA+9 |  | 06.01.25 | 06.01.25 | Done | Suraja Ram
121 | 2 |  | 59/0 | DC2+0 |  | 07.01.25 | 07.01.25 | Done | Suraja Ram
122 | 3 |  | 50/6 | DA+9 |  | 12.01.25 | 12.01.25 | Done | Suraja Ram
123 | 4 |  | 65/7 | DA+0 |  | 17.01.25 | 17.01.25 | Done | Suraja Ram
124 | 5 |  | 65/8 | DA+0 |  | 18.01.25 | 18.01.25 | Done | Suraja Ram
125 | 6 |  | 73/3 | DA+0 |  | 27.01.25 | 27.01.25 | Done | Suraja Ram
126 | 7 |  | 73/4 | DA+0 |  | 28.01.25 | 29.01.25 | Done | Suraja Ram
2025-02-25
127 | 1 |  | 73/7 | DA+0 |  | 13.02.25 | 13.02.25 | Done | Suraja Ram
128 | 2 |  | 74/0 | DB+0 |  | 14.02.25 | 14.02.25 | Done | Suraja Ram
129 | 3 |  | 73/5 | DA+0 |  | 15.02.25 | 15.02.25 | Done | Suraja Ram
130 | 4 |  | 65/10 | DA+0 |  | 17.02.25 | 17.02.25 | Done | Suraja Ram
131 | 5 |  | 66/0 | DC2+6 |  | 19.02.25 | 19.02.25 | Done | Suraja Ram
132 | 6 |  | 51/0 | DC2+0 |  | 26.02.25 | 26.02.25 | Done | Suraja Ram
133 | 1 |  | 50/5 |  |  | 02.03.25 | 02.03.25 | Done | Suraja Ram
134 | 2 |  | 52/0 |  |  | 05.03.25 | 05.03.25 | Done | Suraja Ram
135 | 3 |  | 49/0 |  |  | 10.03.25 | 10.03.25 | Done | Suraja Ram
136 | 4 |  | 52/9 |  |  | 11.03.25 | 11.03.25 | Done | Suraja Ram
137 | 5 |  | 52/10 |  |  | 12.03.25 | 12.03.25 | Done | Suraja Ram
138 | 6 |  | 73/0 |  |  | 13.03.25 | 13.03.25 | Done | Suraja Ram
139 | 7 |  | 52/5 |  |  | 17.3.25 | 17.3.25 | Done | Suraja Ram

## Painting - PKG-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Painting
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Tack Welding Status | Name of Sub-Contractor | Ramarks
1 | 1 |  | 59/14 | DA+6 |  | 26.02.24 | 26.02.24 | Done | Suraja Ram
2 | 2 |  | 63/6 | DA+3 |  | 29.02.24 | 29.02.24 | Done | Suraja Ram
March'24
3 | 1 |  | 62/3 | DA+0 |  | 11.03.24 | 11.03.24 | Done | Suraja Ram
4 | 2 |  | 62/4 | DA+3 |  | 11.03.24 | 11.03.24 | Done | Suraja Ram
5 | 3 |  | 62/2 | DA+3 |  | 11.03.24 | 11.03.24 | Done | Suraja Ram
6 | 4 |  | 59/7 | DA+3 |  | 12.03.24 | 13.03.24 | Done | Ramagora
7 | 5 |  | 59/9 | DA+3 |  | 14.03.24 | 14.03.24 | Done | Suraja Ram
8 | 6 |  | 59/12 | DA+6 |  | 14.03.24 | 14.03.24 | Done | Suraja Ram
9 | 7 |  | 59/10 | DA+0 |  | 14.03.24 | 14.03.24 | Done | Suraja Ram
10 | 8 |  | 63/8 | DA+3 |  | 15.03.24 | 15.03.24 | Done | Suraja Ram
11 | 9 |  | 62/7 | DA+3 |  | 15.03.24 | 15.03.24 | Done | Suraja Ram
12 | 10 |  | 62/8 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Suraja Ram
13 | 11 |  | 64/4 | DA+3 |  | 16.03.24 | 16.03.24 | Done | Suraja Ram
14 | 12 |  | 60/6 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Ramagora
15 | 13 |  | 60/11 | DA+3 |  | 18.03.24 | 18.03.24 | Done | Ramagora
16 | 14 |  | 64/5 | DA+3 |  | 20.03.24 | 20.03.24 | Done | Suraja Ram
17 | 15 |  | 62/9 | DA+3 |  | 20.03.24 | 20.03.24 | Done | Suraja Ram
18 | 16 |  | 60/8 | DA+0 |  | 21.03.24 | 21.03.24 | Done | Ramagora
19 | 17 |  | 65/4 | DA+0 |  | 21.03.24 | 21.03.24 | Done | Suraja Ram
20 | 18 |  | 65/2 | DA+0 |  | 16.03.24 | 16.03.24 | Done | Suraja Ram
21 | 19 |  | 60/7 | DA+3 |  | 23.03.24 | 23.03.24 | Done | Suraja Ram
22 | 20 |  | 59/13 | DA+3 |  | 23.03.24 | 23.03.24 | Done | Suraja Ram
23 | 21 |  | 59/6 | DA+3 |  | 23.03.24 | 23.03.24 | Done | Ramagora
24 | 22 |  | 60/10 | DA+0 |  | 26.03.24 | 26.03.24 | Done | Suraja Ram
25 | 23 |  | 62/10 | DA+0 |  | 26.03.24 | 26.03.24 | Done | Suraja Ram
26 | 24 |  | 61/6 | DA+3 |  | 28.03.24 | 28.03.24 | Done | Suraja Ram
27 | 25 |  | 64/1 | DA+0 |  | 28.03.24 | 28.03.24 | Done | Suraja Ram
28 | 26 |  | 62/5 | DA+0 |  | 28.03.24 | 28.03.24 | Done | Suraja Ram
29 | 27 |  | 65/3 | DA+0 |  | 29.03.24 | 29.03.24 | Done | Suraja Ram
30 | 28 |  | 65/5 | DA+0 |  | 31.03.24 | 31.03.24 | Done | Suraja Ram
April'24
31 | 1 |  | 61/7 | DA+9 |  | 03.04.24 | 03.04.24 | Done | Suraja Ram
32 | 2 |  | 64/6 | DA+0 |  | 06.04.24 | 06.04.24 | Done | Suraja Ram
33 | 3 |  | 65/6 | DA+0 |  | 06.04.24 | 06.04.24 | Done | Suraja Ram
34 | 4 |  | 61/0 | DB+0 |  | 28.04.24 | 28.04.24 | Done | Ramagora
35 | 5 |  | 63/7 | DA+3 |  | 29.04.24 | 30.04.24 | Done | Suraja Ram
May'24
36 | 1 |  | 65/9 | DA+0 |  | 02.05.24 | 02.05.24 | Done | Suraja Ram
37 | 2 |  | 64/7 | DA+3 |  | 02.05.24 | 02.05.24 | Done | Suraja Ram
38 | 3 |  | 61/2 | DA+6 |  | 02.05.24 | 02.05.24 | Done | Ramagora
39 | 4 |  | 64/9 | DA+3 |  | 02.05.24 | 02.05.24 | Done | Suraja Ram
40 | 5 |  | 65/11 | DA+0 |  | 03.05.24 | 03.05.24 | Done | Suraja Ram
41 | 6 |  | 64/8 | DA+3 |  | 11.05.24 | 11.05.24 | Done | Suraja Ram
42 | 7 |  | 65/1 | DA+0 |  | 11.05.24 | 11.05.24 | Done | Suraja Ram
43 | 8 |  | 64/10 | DA+3 |  | 11.05.24 | 11.05.24 | Done | Suraja Ram
44 | 9 |  | 67/1 | DA+0 |  | 12.05.24 | 12.05.24 | Done | Suraja Ram
45 | 10 |  | 67/2 | DA+0 |  | 12.05.24 | 12.05.24 | Done | Suraja Ram
46 | 11 |  | 65/0 | DB1+0 |  | 13.05.24 | 13.05.24 | Done | Suraja Ram
47 | 12 |  | 60/9 | DA+3 |  | 11.05.24 | 11.05.24 | Done | Ramagora
48 | 13 |  | 63/4 | DA+0 |  | 17.05.24 | 17.05.24 | Done | Suraja Ram
49 | 14 |  | 63/3 | DA+3 |  | 17.05.24 | 17.05.24 | Done | Suraja Ram
50 | 15 |  | 61/1 | DA+6 |  | 18.05.24 | 18.05.24 | Done | Ramagora
51 | 16 |  | 61/3 | DA+6 |  | 18.05.24 | 18.05.24 | Done | Ramagora
52 | 17 |  | 63/5 | DA+3 |  | 20.05.24 | 20.05.24 | Done | Suraja Ram
53 | 18 |  | 62/11 | DA+3 |  | 20.05.24 | 20.05.24 | Done | Suraja Ram
54 | 13 |  | 61/4 | DA+3 |  | 23.05.24 | 23.05.24 | Done | Suraja Ram
55 | 1`4 |  | 61/5 | DA+3 |  | 25.05.24 | 25.05.24 | Done | Suraja Ram
June'24
56 | 1 |  | 64/2 | DA+3 |  | 04.06.24 | 04.06.24 | Done | Suraja Ram
57 | 2 |  | 64/0 | DB2+0 |  | 06.06.24 | 06.06.24 | Done | Suraja Ram
58 | 3 |  | 63/0 | DC1+0 |  | 10.06.24 | 11.06.24 | Done | Suraja Ram
59 | 4 |  | 60/5 | DA+3 |  | 12.06.24 | 12.06.24 | Done | Ramagora
60 | 5 |  | 61/10 | DA+9 |  | 12.06.24 | 12.06.24 | Done | Suraja Ram
61 | 6 |  | 63/1 | DA+3 |  | 12.06.24 | 12.06.24 | Done | Suraja Ram
62 | 7 |  | 63/2 | DA+0 |  | 12.06.24 | 12.06.24 | Done | Suraja Ram
63 | 8 |  | 64/3 | DA+0 |  | 12.06.24 | 12.06.24 | Done | Suraja Ram
64 | 9 |  | 60/4 | DA+3 |  | 13.06.24 | 13.06.24 | Done | Ramagora
65 | 10 |  | 59/5 | DA+3 |  | 14.06.24 | 14.06.24 | Done | Ramagora
66 | 11 |  | 61/8 | DA+6 |  | 15.06.24 | 15.06.24 | Done | Ramagora
67 | 12 |  | 61/9 | DA+0 |  | 15.06.24 | 15.06.24 | Done | Ramagora
68 | 13 |  | 60/3 | DA+3 |  | 23.06.24 | 23.06.24 | Done | Ramagora
69 | 14 |  | 60/2 | DA+3 |  | 25.06.24 | 25.06.24 | Done | Ramagora
July'24
70 | 1 |  | 60/1 | DA+6 |  | 01.07.24 | 01.07.24 | Done | Ramagora
71 | 2 |  | 60/0 | DC+0 |  | 24.07.24 | 24.07.24 | Done | Suraja Ram
72 | 3 |  | 59/16 | DA+9 |  | 01.07.24 | 01.07.24 | Done | Suraja Ram
73 | 4 |  | 59/15 | DA+6 |  | 02.07.24 | 02.07.24 | Done | Suraja Ram
74 | 5 |  | 59/8 | DB1+3 |  | 27.07.24 | 27.07.24 | Done | Suraja Ram
Sept'24
75 | 1 |  | 55/3 | DA+0 |  | 01.09.24 | 01.09.24 | Done | Suraja Ram
76 | 2 |  | 55/4 | DA+0 |  | 02.09.24 | 02.09.24 | Done | Suraja Ram
77 | 3 |  | 62/6 | DA+3 |  | 03.09.24 | 03.09.24 | Done | Suraja Ram
78 | 4 |  | 57/6 | DA+3 |  | 04.09.24 | 04.09.24 | Done | Suraja Ram
79 | 5 |  | 57/3 | DA+0 |  | 05.09.24 | 05.09.24 | Done | Suraja Ram
80 | 6 |  | 57/4 | DA+0 |  | 06.09.24 | 06.09.24 | Done | Suraja Ram
81 | 7 |  | 57/5 | DA+3 |  | 07.09.24 | 07.09.24 | Done | Suraja Ram
82 | 8 |  | 62/1 | DA+3 |  | 26.09.24 | 26.09.24 | Done | Suraja Ram
83 | 9 |  | 62/0 | DB2+0 |  | 15.09.24 | 15.09.24 | Done | Suraja Ram
Oct'24
84 | 1 |  | 57/7 | DA+3 |  | 07.10.24 | 07.10.24 | Done | Suraja Ram
85 | 2 |  | 50/9 | DA+0 |  | 08.10.24 | 08.10.24 | Done | Suraja Ram
86 | 3 |  | 50/10 | DA+0 |  | 10.101.24 | 10.10.24 | Done | Suraja Ram
87 | 4 |  | 50/0 | DB2+0 |  | 11.10.24 | 11.10.24 | Done | Suraja Ram
88 | 5 |  | 50/3 | DA+6 |  | 24.10.24 | 24.10.24 | Done | Suraja Ram
89 | 6 |  | 50/1 | DA+6 |  | 25.10.24 | 25.10.24 | Done | Suraja Ram
90 | 7 |  | 51/1 | DA+0 |  | 25.10.24 | 25.10.24 | Done | Suraja Ram
91 | 8 |  | 50/2 | DA+9 |  | 28.10.24 | 28.10.24 | Done | Suraja Ram
Nov'24
92 | 1 |  | 59/11 | DA+6 |  | 11.11.24 | 11.11.24 | Done | Suraja Ram
93 | 2 |  | 50/7 | DA+0 |  | 14.11.24 | 14.11.24 | Done | Suraja Ram
94 | 3 |  | 73/1 | DA+0 |  | 14.11.24 | 14.11.24 | Done | Suraja Ram
95 | 4 |  | 73/9 | DA+0 |  | 20.11.24 | 20.11.24 | Done | Suraja Ram
96 | 5 |  | 64/11 | DA+3 |  | 21.11.24 | 21.11.24 | Done | Suraja Ram
97 | 6 |  | 73/2 | DA+0 |  | 19.11.24 | 19.11.24 | Done | Suraja Ram
98 | 7 |  | 52/6 | DA+6 |  | 25.11.24 | 25.11.24 | Done | Suraja Ram
99 | 8 |  | 52/7 | DA+3 |  | 26.11.24 | 26.11.24 | Done | Suraja Ram
100 | 9 |  | 52/8 | DA+6 |  | 26.11.24 | 26.11.24 | Done | Suraja Ram
101 | 11 |  | 48/1 | DA+9 |  | 30.11.24 | 30.11.24 | Done | Suraja Ram
Dec'24
102 | 1 |  | 49/4 | DA+3 |  | 27.11.24 | 27.11.24 | Done | Suraja Ram
103 | 2 |  | 48/0 | DC2+0 |  | 27.11.24 | 27.11.24 | Done | Suraja Ram
104 | 3 |  | 47/10 | DA+6 |  | 29.11.24 | 29.11.24 | Done | Suraja Ram
105 | 4 |  | 49/6 | DA+0 |  | 03.12.24 | 03.12.24 | Done | Suraja Ram
106 | 5 |  | 49/5 | DA+3 |  | 04.12.24 | 04.12.24 | Done | Suraja Ram
107 | 6 |  | 59/4 | DA+3 |  | 06.12.24 | 06.12.24 | Done | Suraja Ram
108 | 7 |  | 49/7 | DA+0 |  | 02.12.24 | 02.12.24 | Done | Suraja Ram
109 | 8 |  | 73/6 | DA+0 |  | 13.12.24 | 13.12.24 | Done | Suraja Ram
110 | 9 |  | 59/1 | DA+3 |  | 18.12.24 | 18.12.24 | Done | Suraja Ram
111 | 10 |  | 59/2 | DA+3 |  | 20.12.24 | 20.12.24 | Done | Suraja Ram
112 | 11 |  | 59/3 | DA+3 |  | 07.12.24 | 07.12.24 | Done | Suraja Ram
113 | 12 |  | 72/3 | DA+3 |  | 17.12.24 | 17.12.24 | Done | Suraja Ram
114 | 13 |  | 50/8 | DA+9 |  | 23.12.24 | 23.12.24 | Done | Suraja Ram
115 | 14 |  | 51/2 | DA+0 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
116 | 15 |  | 49/2 | DA+0 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
117 | 16 |  | 49/3 | DA+3 |  | 26.12,24 | 26.12,24 | Done | Suraja Ram
118 | 17 |  | 49/1 | DA+0 |  | 29.12.24 | 29.12.24 | Done | Suraja Ram
119 | 18 |  | 73/8 | DA+0 |  | 29.12.24 | 29.12.24 | Done | Suraja Ram
Jan'25
120 | 1 |  | 50/4 | DA+9 |  | 06.01.25 | 06.01.25 | Done | Suraja Ram
121 | 2 |  | 59/0 | DC2+0 |  | 07.01.25 | 07.01.25 | Done | Suraja Ram
122 | 3 |  | 50/6 | DA+9 |  | 12.01.25 | 12.01.25 | Done | Suraja Ram
123 | 4 |  | 65/7 | DA+0 |  | 23.01.25 | 23.01.25 | Done | Suraja Ram
124 | 5 |  | 65/8 | DA+0 |  | 23.01.25 | 23.01.25 | Done | Suraja Ram
125 | 6 |  | 73/3 | DA+0 |  | 28.01.25 | 28.01.25 | Done | Suraja Ram
126 | 7 |  | 73/4 | DA+0 |  | 29.01.25 | 29.01.25 | Done | Suraja Ram
Feb'25
127 | 1 |  | 73/5 | DA+0 |  | 15.02.25 | 15.02.25 | Done | Suraja Ram
128 | 2 |  | 65/10 | DA+0 |  | 17.02.25 | 17.02.25 | Done | Suraja Ram
129 | 3 |  | 66/0 | DC2+6 |  | 19.02.25 | 19.02.25 | Done | Suraja Ram
130 | 4 |  | 51/0 | DC2+0 |  | 26.02.25 | 26.02.25 | Done | Suraja Ram
131 | 5 |  | 74/0 | DB+0 |  | 14.02.25 | 14.02.25 | Done | Suraja Ram
132 | 6 |  | 73/7 | DA+0 |  | 13.02.25 | 13.02.25 | Done | Suraja Ram
Mar'25
133 | 1 |  | 52/0 |  |  | 05.03.25 | 05.03.25 | Done | Suraja Ram
134 | 2 |  | 49/0 |  |  | 10.03.25 | 10.03.25 | Done | Suraja Ram
135 | 5 |  | 52/10 |  |  | 12.03.25 | 12.03.25 | Done | Suraja Ram
136 | 6 |  | 73/0 |  |  | 13.03.25 | 13.03.25 | Done | Suraja Ram
137 | 7 |  | 52/5 |  |  | 17.3.25 | 17.3.25 | Done | Suraja Ram
138 | 4 |  | 52/9 |  |  | 11.03.25 | 11.03.25 | Done | Suraja Ram
139 | 5 |  | 50/5 |  |  | 02.03.25 | 02.03.25 | Done | Suraja Ram

## Painting - PKG-G
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Painting
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Tack Welding Status | Name of Sub-Contractor | Ramarks
15/2
| 2023-12-01 | [10 empty] | 29/5
1 | 1 |  | 56/9 | DA+3 |  | 02.12.23 | 03.12.23 | Done | Suraja Ram |  |  | 29/6
2 | 2 |  | 57/1 | DA+3 |  | 02.12.23 | 03.12.23 | Done | Suraja Ram |  |  | 29/7
3 | 3 |  | 56/8 | DA+3 |  | 03.12.23 | 06.12.23 | Done | Suraja Ram |  |  | 29/8
4 | 4 |  | 57/2 | DA+0 |  | 04.12.23 | 08.12.23 | Done | Suraja Ram |  |  | 29/10
5 | 5 |  | 57/3 | DA+0 |  | 04.12.23 | 08.12.23 | Done | Suraja Ram |  |  | 16/5
6 | 6 |  | 57/4 | DA+0 |  | 04.12.23 | 08.12.23 | Done | Suraja Ram |  |  | 16/3
7 | 7 |  | 57/5 | DA+3 |  | 04.12.23 | 08.12.23 | Done | Suraja Ram |  |  | 15/4
8 | 8 |  | 57/8 | DA+3 |  | 05.12.23 | 09.12.23 | Done | Suraja Ram |  |  | 15/3
9 | 9 |  | 57/9 | DA+0 |  | 05.12.23 | 09.12.23 | Done | Suraja Ram |  |  | 16/4
10 | 10 |  | 57/10 | DA+0 |  | 05.12.23 | 09.12.23 | Done | Suraja Ram
11 | 11 |  | 57/11 | DA+0 |  | 09.12.23 | 10.12.23 | Done | Suraja Ram
12 | 12 |  | 57/12 | DA+3 |  | 10.12.23 | 11.12.23 | Done | Suraja Ram
13 | 13 |  | 58/14 | DA+0 |  | 08.12.23 | 11.12.23 | Done | Suraja Ram
14 | 14 |  | 57/13 | DA+0 |  | 12.12.23 | 16.12.23 | Done | Suraja Ram
15 | 15 |  | 58/8 | DA+0 |  | 12.12.23 | 16.12.23 | Done | Suraja Ram
16 | 16 |  | 58/9 | DA+0 |  | 12.12.23 | 16.12.23 | Done | Suraja Ram
17 | 17 |  | 58/11 | DA+3 |  | 14.12.23 | 17.12.23 | Done | Suraja Ram
18 | 18 |  | 58/10 | DA+3 |  | 15.12.23 | 17.12.23 | Done | Suraja Ram
19 | 19 |  | 58/12 | DA+0 |  | 15.12.23 | 17.12.23 | Done | Suraja Ram
20 | 20 |  | 56/7 | DA+3 |  | 17.12.23 | 17.12.23 | Done | Suraja Ram
21 | 21 |  | 58/16 | DA+0 |  | 18.12.23 | 18.12.23 | Done | Suraja Ram
22 | 22 |  | 59/1 | DA+0 |  | 18.12.23 | 18.12.23 | Done | Suraja Ram
23 | 23 |  | 59/2 | DA+0 |  | 20.12.23 | 20.12.23 | Done | Suraja Ram
24 | 24 |  | 59/3 | DA+0 |  | 21.12.23 | 21.12.23 | Done | Suraja Ram
25 | 25 |  | 59/5 | DA+0 |  | 22.12.23 | 22.12.23 | Done | Suraja Ram
26 | 26 |  | 59/6 | DA+0 |  | 23.12.23 | 24.12.23 | Done | Suraja Ram
27 | 27 |  | 56/3 | DA+0 |  | 25.12.23 | 27.12.23 | Done | Suraja Ram
28 | 28 |  | 56/4 | DA+3 |  | 26.12.23 | 27.12.23 | Done | Suraja Ram
29 | 29 |  | 55/4 | DA+3 |  | 26.12.23 | 27.12.23 | Done | Suraja Ram
30 | 30 |  | 55/5 | DA+0 |  | 28.12.23 | 28.12.23 | Done | Suraja Ram
31 | 31 |  | 55/6 | DA+3 |  | 29.12.23 | 30.12.23 | Done | Suraja Ram
2024-01-01
32 | 1 |  | 55/11 | DA+3 |  | 08.01.24 | 09.01.24 | Done | Suraja Ram
33 | 2 |  | 55/10 | DA+3 |  | 10.01.24 | 10.01.24 | Done | Suraja Ram
34 | 3 |  | 58/1 | DA+0 |  | 18.01.24 | 19.01.24 | Done | Suraja Ram
35 | 4 |  | 58/6 | DA+3 |  | 19.01.24 | 20.01.24 | Done | Suraja Ram
36 | 5 |  | 58/5 | DA+3 |  | 19.01.24 | 20.01.24 | Done | Suraja Ram
37 | 6 |  | 58/4 | DA+0 |  | 20.01.24 | 20.01.24 | Done | Suraja Ram
38 | 7 |  | 57/6 | DB1+0 |  | 21.01.24 | 21.01.24 | Done | Suraja Ram
39 | 8 |  | 57/7 | DA+3 |  | 21.01.24 | 21.01.24 | Done | Suraja Ram
40 | 9 |  | 51/7 | DA+3 |  | 21.01.24 | 21.01.24 | Done | Kailash Nath
41 | 10 |  | 51/5 | DA+0 |  | 22.01.24 | 22.01.24 | Done | Kailash Nath
42 | 11 |  | 57/0 | DB2+0 |  | 22.01.24 | 22.01.24 | Done | Suraja Ram
43 | 12 |  | 56/6 | DA+3 |  | 22.01.24 | 22.01.24 | Done | Suraja Ram
44 | 13 |  | 56/5 | DA+0 |  | 23.01.24 | 23.01.24 | Done | Suraja Ram |  | comp
45 | 14 |  | 56/2 | DA+3 |  | 23.01.24 | 23.01.24 | Done | Suraja Ram
46 | 15 |  | 51/4 | DA+3 |  | 23.01.24 | 23.01.24 | Done | Kailash Nath
47 | 16 |  | 51/3 | DA+0 |  | 23.01.24 | 23.01.24 | Done | Kailash Nath
48 | 17 |  | 51/2 | DA+0 |  | 24.01.24 | 24.01.24 | Done | Kailash Nath
49 | 18 |  | 56/0 | DB1+0 |  | 24.01.24 | 24.01.24 | Done | Suraja Ram
50 | 19 |  | 55/9 | DA+3 |  | 25.01.24 | 25.01.24 | Done | Suraja Ram
51 | 20 |  | 55/8 | DA+3 |  | 25.01.24 | 25.01.24 | Done | Suraja Ram
52 | 21 |  | 52/2 | DA+3 |  | 25.01.24 | 25.01.24 | Done | Kailash Nath
53 | 22 |  | 52/5 | DA+3 |  | 25.01.24 | 25.01.24 | Done | Kailash Nath
54 | 23 |  | 51/10 | DA+3 |  | 27.01.24 | 27.01.24 | Done | Kailash Nath
55 | 24 |  | 52/1 | DA+0 |  | 27.01.24 | 27.01.24 | Done | Kailash Nath
56 | 25 |  | 55/7 | DA+0 |  | 26.01.24 | 26.01.24 | Done | Suraja Ram
57 | 26 |  | 58/3 | DA+3 |  | 30.01.24 | 30.01.24 | Done | Suraja Ram
58 | 27 |  | 58/7 | DB+0 |  | 29.01.24 | 29.01.24 | Done | Suraja Ram
Feb-24
59 | 1 |  | 59/0 | DB+0 |  | 02.02.24 | 02.02.24 | Done | Suraja Ram
60 | 2 |  | 58/15 | DA+3 |  | 02.02.24 | 02.02.24 | Done | Suraja Ram
61 | 3 |  | 61/1 | DA+0 |  | 03.02.24 | 03.02.24 | Done | Suraja Ram
62 | 4 |  | 55/1 | DA+3 |  | 04.02.24 | 04.02.24 | Done | Suraja Ram
63 | 5 |  | 55/3 | DA+0 |  | 06.02.24 | 06.02.24 | Done | Suraja Ram
64 | 6 |  | 55/2 | DA+3 |  | 04.02.24 | 05.02.24 | Done | Suraja Ram |  |  |  | 52/4
65 | 7 |  | 41/5 | DA+0 |  | 15.02.24 | 15.02.24 | Done | Ramagora
66 | 8 |  | 41/7 | DA+3 |  | 15.02.24 | 15.02.24 | Done | Ramagora
67 | 9 |  | 41/10 | DA+3 |  | 28.01.24 | 16.02.24 | Done | Ramagora
68 | 10 |  | 41/11 | DA+3 |  | 29.01.24 | 17.02.24 | Done | Ramagora
69 | 11 |  | 46/2 | DA+0 |  | 17.02.24 | 18.02.24 | Done | Suraja Ram
70 | 12 |  | 43/1 | DA+9 |  | 10.02.24 | 18.02.24 | Done | Ramagora
71 | 13 |  | 44/2 | DA+0 |  | 27.01.24 | 18.02.24 | Done | Ramagora
72 | 14 |  | 47/0 | DB+0 |  | 19.02.24 | 19.02.24 | Done | Suraja Ram
73 | 15 |  | 48/2 | DA+3 |  | 19.02.24 | 19.02.24 | Done | Suraja Ram
74 | 16 |  | 53/3 | DA+3 |  | 19.02.24 | 19.02.24 | Done | Suraja Ram
75 | 17 |  | 44/4 | DA+0 |  | 19.02.24 | 19.02.24 | Done | Ramagora
76 | 18 |  | 46/3 | DA+0 |  | 20.02.24 | 20.02.24 | Done | Ramagora
77 | 19 |  | 47/2 | DA+0 |  | 22.02.24 | 22.02.24 | Done | Ramagora
78 | 20 |  | 50/3 | DA+0 |  | 22.02.24 | 22.02.24 | Done | Ramagora
79 | 21 |  | 48/1 | DA+0 |  | 03.02.24 | 22.02.24 | Done | Ramagora
80 | 22 |  | 50/4 | DA+3 |  | 23.02.24 | 23.02.24 | Done | Ramagora
81 | 23 |  | 51/6 | DA+0 |  | 24.02.24 | 24.02.24 | Done | Ramagora
82 | 24 |  | 51/8 | DA+3 |  | 24.02.24 | 24.02.24 | Done | Ramagora
83 | 25 |  | 51/9 | DA+3 |  | 25.02.24 | 25.02.24 | Done | Ramagora
84 | 26 |  | 53/4 | DA+3 |  | 25.02.24 | 25.02.24 | Done | Suraja Ram
85 | 27 |  | 53/1 | DA+0 |  | 25.02.24 | 25.02.24 | Done | Suraja Ram
86 | 28 |  | 52/0 | DB+0 |  | 26.02.24 | 26.02.24 | Done | Suraja Ram
87 | 29 |  | 52/4 | DA+0 |  | 27.02.24 | 27.02.24 | Done | Ramagora
March'24
88 | 1 |  | 41/8 | DA+0 |  | 08.03.24 | 08.03.24 | Done | Ramagora
89 | 2 |  | 41/4 | DA+0 |  | 08.03.24 | 08.03.24 | Done | Ramagora
90 | 3 |  | 41/6 | DA+0 |  | 08.03.24 | 08.03.24 | Done | Ramagora
91 | 4 |  | 41/9 | DA+0 |  | 08.03.24 | 08.03.24 | Done | Ramagora
92 | 5 |  | 43/4 | DA+9 |  | 10.03.24 | 10.03.24 | Done | Ramagora
93 | 6 |  | 43/5 | DA+0 |  | 10.03.24 | 10.03.24 | Done | Ramagora
94 | 7 |  | 51/1 | DA+0 |  | 14.03.24 | 14.03.24 | Done | Ramagora
95 | 8 |  | 53/2 | DA+3 |  | 23.03.24 | 23.03.24 | Done | Suraja Ram
96 | 9 |  | 51/0 | DB+0 |  | 29.03.24 | 29.03.24 | Done | Ramagora
97 | 10 |  | 44/3 | DA+3 |  | 30.03.24 | 30.03.24 | Done | Ramagora
April'24
98 | 1 |  | 47/3 | DA+0 |  | 23.04.24 | 23.04.24 | Done | Ramagora
99 | 2 |  | 56/1 | DA+3 |  | 29.04.24 | 29.04.24 | Done | Ramagora
May'24
100 | 1 |  | 61/2 | DA+0 | 06.05.24 | 12.05.24 | 12.05.24 | Done | Suraja Ram
101 | 2 |  | 44/1 | DA+0 | 12.05.24 | 13.05.24 | 13.05.24 | Done | Ramagora
102 | 3 |  | 58/0 | DC2+0 | 04.05.24 | 13.05.24 | 13.05.24 | Done | Suraja Ram
103 | 4 |  | 55/0 | DC+0 | 24.05.24 | 26.05.24 | 26.05.24 | Done | Suraja Ram
June'24
104 | 1 |  | 65/5 | DA+0 | 30.05.24 | 02.06.24 | 02.06.24 | Done | Suraja Ram
105 | 2 |  | 65/4 | DA+0 | 31.05.24 | 02.06.24 | 02.06.24 | Done | Suraja Ram
106 | 3 |  | 58/2 | DA+0 | 02.06.24 | 02.06.24 | 02.06.24 | Done | Suraja Ram
107 | 4 |  | 65/3 | DA+0 | 02.06.24 | 03.06.24 | 03.06.24 | Done | Suraja Ram
108 | 5 |  | 52/3 | DA+0 |  | 24.06.24 | 24.06.24 | Done | Suraja Ram
109 | 6 |  | 53/0 | DC2+3 | 22.06.24 | 25.06.24 | 25.06.24 | Done | Suraja Ram
Sept'24
110 | 1 |  | 48/0 | DB+0 | 23.07.24 | 24.07.24 | 24.07.24 | Done | Suraja Ram
111 | 2 |  | 46/4 | DA+0 | 16.09.24 | 21.09.24 | 21.09.24 | Done | Suraja Ram
112 | 3 |  | 47/1 | DA+0 | 19.09.24 | 21.09.24 | 21.09.24 | Done | Suraja Ram
113 | 4 |  | 50/2 | DA+0 | 20.09.24 | 22.09.24 | 22.09.24 | Done | Suraja Ram
114 | 5 |  | 50/1 | DA+0 | 22.09.24 | 24.09.24 | 24.09.24 | Done | Suraja Ram
115 | 6 |  | 72/5 | DA+0 | 26.09.24 | 26.09.24 | 26.09.24 | Done | Suraja Ram
116 | 7 |  | 72/3 | DA+0 |  | 29.09.24 | 29.09.24 | Done | Suraja Ram
117 | 8 |  | 72/4 | DA+0 |  | 29.09.24 | 29.09.24 | Done | Suraja Ram
118 | 9 |  | 72/6 | DA+0 | 29.09.24 | 30.09.24 | 30.09.24 | Done | Suraja Ram
119 | 10 |  | 71/5 | DA+0 | 29.09.24 | 30.09.24 | 30.09.24 | Done | Suraja Ram
Oct'24
120 | 1 |  | 50/0 | DC2+3 | 04.10.24 | 08.10.24 | 08.10.24 | Done | Suraja Ram
121 | 2 |  | 72/0 | DB1+0 | 04.10.24 | 04.10.24 | 16.10.24 | Done | Suraja Ram
122 | 3 |  | 71/4 | DA+0 | 13.10.24 | 13.10.24 | 16.10.24 | Done | Suraja Ram
123 | 4 |  | 72/2 | DA+0 | 14.10.24 | 14.10.24 | 14.10.24 | Done | Suraja Ram
124 | 5 |  | 71/2 | DA+0 | 15.10.24 | 15.10.24 | 17.10.24 | Done | Suraja Ram
125 | 6 |  | 71/1 | DA+0 | 16.10.24 | 16.10.24 | 17.10.24 | Done | Suraja Ram
126 | 7 |  | 68/1 | DA+3 | 19.10.24 | 19.10.24 | 19.10.24 | Done | Suraja Ram
127 | 8 |  | 72/1 | DA+0 | 19.10.24 | 19.10.24 | 19.10.24 | Done | Suraja Ram
Nov'24
128 | 1 |  | 72/7 | DB1+9 | 09.11.24 | 09.11.24 | 09.11.24 | Done | Suraja Ram
129 | 2 |  | 68/6 | DA+3 | 14.11.24 | 15.11.24 | 15.11.24 | Done | Suraja Ram
130 | 3 |  | 71/3 | DA+0 | 14.11.24 | 14.11.24 | 14.11.24 | Done | Suraja Ram
131 | 4 |  | 68/3 | DA+0 | 14.11.24 | 14.11.24 | 14.11.24 | Done | Suraja Ram
132 | 5 |  | 66/2 | DA+0 | 14.11.24 | 14.11.24 | 14.11.24 | Done | Suraja Ram
133 | 6 |  | 73/0 | DD45+9 |  | 18.11.24 | 18.11.24 | Done | Suraja Ram
134 | 7 |  | 68/4 | DA+3 | 20.11.24 | 20.11.24 | 20.11.24 | Done | Suraja Ram
135 | 8 |  | 69/6 | DA+0 | 04.11.24 | 04.11.24 | 04.11.24 | Done | Suraja Ram
136 | 9 |  | 68/2 | DA+3 | 20.11.24 | 20.11.24 | 20.11.24 | Done | Suraja Ram
137 | 10 |  | 68/5 | DA+3 | 20.11.24 | 20.11.24 | 20.11.24 | Done | Suraja Ram
Dec'24
138 | 1 |  | 69/5 | DA+0 | 08.12.24 | 08.12.24 | 08.12.24 | Done | Suraja Ram
139 | 2 |  | 69/1 | DA+0 | 10.12.24 | 10.12.24 | 10.12.24 | Done | Suraja Ram
140 | 3 |  | 69/2 | DA+0 | 11.12.24 | 11.12.24 | 11.12.24 | Done | Suraja Ram
141 | 4 |  | 66/4 | DA+3 | 12.12.24 | 12.12.24 | 12.12.24 | Done | Suraja Ram
142 | 5 |  | 66/1 | DA+3 | 15.12.24 | 15.12.24 | 15.12.24 | Done | Suraja Ram
143 | 6 |  | 68/0 | DD+0 | 16.12.24 | 16.12.24 | 16.12.24 | Done | Suraja Ram
144 | 7 |  | 43/3 | DA+3 | 22.12.24 | 22.12.24 | 22.12.24 | Done | Suraja Ram
145 | 8 |  | 69/7 | DA+0 | 22.11.24 | 22.11.24 | 22.11.24 | Done | Suraja Ram
146 | 9 |  | 69/0 | DB1+0 | 22.12.24 | 25.12.24 | 25.12.24 | Done | Suraja Ram
147 | 10 |  | 69/8 | DA+0 | 31.12.24 | 31.12.24 | 31.12.24 | Done | Suraja Ram
148 | 11 |  | 69/9 | DA+0 | 31.12.24 | 31.12.24 | 31.12.24 | Done | Suraja Ram
2025-01-25
149 | 1 |  | 67/1 | DB1+9 | 20.12.24 | 02.01.25 | 02.01.25 | Done | Suraja Ram
150 | 2 |  | 38/1 | DA+3 | 29.12.24 | 03.01.25 | 03.01.25 | Done | Suraja Ram
151 | 3 |  | 38/2 | DA+6 | 30.12.24 | 03.01.25 | 03.01.25 | Done | Suraja Ram
152 | 4 |  | 69/3 | DA+0 | 26.12.24 | 04.01.25 | 04.01.25 | Done | Suraja Ram
153 | 5 |  | 69/4 |  | 27.12.24 | 04.01.25 | 04.01.25 | Done | Suraja Ram
154 | 6 |  | 37/3 | DA+0 | 02.01.25 | 04.01.25 | 04.01.25 | Done | Suraja Ram
155 | 7 |  | 38/3 | DA+9 | 04.01.25 | 04.01.25 | 04.01.25 | Done | Suraja Ram
156 | 8 |  | 37/4 | DA+6 | 09.01.25 | 09.01.25 | 09.01.25 | Done | Suraja Ram
157 | 9 |  | 41/2 | DA+0 |  | 19.01.25 | 19.01.25 | Done | Suraja Ram
158 | 10 |  | 71/0 | DD60+0 |  | 13.01.25 | 13.01.25 | Done | Suraja Ram
159 | 11 |  | 37/2 | DB1+6 | 20.01.25 | 22.01.25 | 22.01.25 | Done | Suraja Ram
160 | 12 |  | 59/4 | DA+0 | 16.01.25 | 23.01.25 | 23.01.25 | Done | Suraja Ram
161 | 13 |  | 70/0 | DD60+0 |  | 25.01.25 | 25.01.25 | Done | Suraja Ram
162 | 14 |  | 67/0 | DD45+0 |  | 24.01.25 | 24.01.25 | Done | Suraja Ram
Feb'25
163 | 1 |  | 41/12 | DA+3 |  | 02.02.25 | 02.02.25 | Done | Suraja Ram
164 | 2 |  | 41/3 | DA+0 |  | 02.02.25 | 02.02.25 | Done | Suraja Ram
165 | 3 |  | 37/5 | DA+3 |  | 03.02.25 | 03.02.25 | Done | Suraja Ram
166 | 4 |  | 37/6 | DA+6 |  | 04.02.25 | 04.02.25 | Done | Suraja Ram
167 | 5 |  | 37/7 | DA+3 |  | 05.02.25 | 05.02.25 | Done | Suraja Ram
168 | 6 |  | 37/8 | DA+0 |  | 06.02.25 | 06.02.25 | Done | Suraja Ram
169 | 7 |  | 41/1 | DA+3 |  | 08.02.25 | 08.02.25 | Done | Suraja Ram
170 | 8 |  | 42/0 | DC2+9 |  | 09.02.25 | 09.02.25 | Done | Suraja Ram
171 | 9 |  | 65/6 |  | 20.02.25 | 21.02.25 | 21.02.25 | Done | Suraja Ram
172 | 10 |  | 40/11 | DA+3 | 24.02.25 | 28.02.25 | 28.02.25 | Done | Suraja Ram
173 | 11 |  | 40/10 | DA+3 | 24.02.25 | 28.02.25 | 28.02.25 | Done | Suraja Ram
Feb'25
174 | 1 |  | 40/2 |  | 26.02.25 | 01.03.25 | 01.3.25 | Done | Suraja Ram
175 | 2 |  | 41/0 |  | 27.02.25 | 01.03.25 | 01.03.25 | Done | Suraja Ram
176 | 3 |  | 40/12 |  | 03.03.25 | 03.03.25 | 03.03.25 | Done | Suraja Ram
177 | 4 |  | 65/7 | DA+0 | 21.02.25 | 21.02.25 | 21.02.25 | Done | Suraja Ram
178 | 5 |  | 58/13 | DA+0 | 26.12.24 | 26.12.24 | 26.12.24 | Done | Suraja Ram
Mar'25
179 | 1 |  | 40/6 |  | 07.03.25 | 07.03.25 | 07.03.25 | Done | Suraja Ram
180 | 2 |  | 60/0 |  | 13.03.25 | 16.03.25 | 16.03.25 | Done | Suraja Ram
181 | 6 |  | 39/0 |  | 18.03.25 | 18.03.25 | 18.03.25 | Done | Suraja Ram
182 | 7 |  | 40/0 |  | 19.03.25 | 19.03.25 | 19.03.25 | Done | Suraja Ram
183 | 8 |  | 40/1 |  | 20.03.25 | 20.03.25 | 20.03.25 | Done | Suraja Ram
184 | 9 |  | 40/7 |  | 08.03.25 | 08.03.25 | 08.03.25 | Done | Suraja Ram
185 | 10 |  | 38/0 |  | 06.03.25 | 06.03.25 | 06.03.25 | Done | Suraja Ram
186 | 11 |  | 38/7 |  |  | 21.03.25 | 21.03.25 | Done | Suraja Ram
187 | 12 |  | 38/8 |  | 22.03.25 | 22.03.25 | 22.03.25 | Done | Suraja Ram
188 | 13 |  | 38/9 |  | 23.03.25 | 23.03.25 | 23.03.25 | Done | Suraja Ram
April'25
189 | 1 |  | 44/0 | DB1+0 |  | 04.05.25 | 04.05.25 | Done | Suraja Ram
2025-05-25
190 | 1 |  | 63/5 |  | 13.05.25 | 13.05.25 | 13.05.25 | Done | Suraja Ram
191 | 2 |  | 63/4 |  | 14.05.25 | 14.05.25 | 14.05.25 | Done | Suraja Ram
192 | 3 |  | 63/1 |  | 15.05.25 | 15.05.25 | 15.05.25 | Done | Suraja Ram
193 | 4 |  | 63/2 |  | 24.05.25 | 24.05.25 | 24.05.25 | Done | Suraja Ram
2025-06-25
194 | 1 |  | 63/0 |  | 05.06.25 | 05.06.25 | 05.06.25 | Done | Suraja Ram
195 | 2 |  | 64/9 |  | 11.06.25 | 11.06.25 | 11.06.25 | Done | Suraja Ram
196 | 3 |  | 62/0 | DC+0 | 03.06.25 | 11.06.25 | 11.06.25 | Done | Suraja Ram
Jul
197 | 1 |  | 39/4 |  | 05.07.25 | 05.07.25 | 05.07.25 | Done | Suraja Ram
198 | 2 |  | 38/6 |  |  | July | July | Done | Suraja Ram
199 | 3 |  | 38/5 |  |  | July | July | Done | Suraja Ram
200 | 4 |  | 38/4 |  |  | July | July | Done | Suraja Ram
201 | 5 |  | 49/0 |  |  | July | July | Done | Suraja Ram
202 | 6 |  | 43/6 |  |  | July | July | Done | Suraja Ram
203 | 7 |  | 43/2 |  |  | July | July | Done | Suraja Ram
204 | 8 |  | 40/4 |  |  | July | July | Done | Suraja Ram
205 | 9 |  | 40/5 |  |  | July | July | Done | Suraja Ram
206 | 10 |  | 35/9 |  |  | July | July | Done | Suraja Ram
207 | 11 |  | 35/8 |  |  | July | July | Done | Suraja Ram
208 | 12 |  | 43/0 |  |  | July | July | Done | Suraja Ram
209 | 13 |  | 61/0 |  |  | July | July | Done | Suraja Ram
210 | 14 |  | 66/0 |  |  | July | July | Done | Suraja Ram
211 | 15 |  | 32/0 |  |  | July | July | Done | Suraja Ram
212 | 16 |  | 29/9 |  |  | July | July | Done | Suraja Ram
213 | 17 |  | 32/1 |  |  | July | July | Done | Suraja Ram
214 | 18 |  | 63/3 |  |  | July | July | Done | Suraja Ram
215 | 19 |  | 63/6 |  |  | July | July | Done | Suraja Ram
216 | 20 |  | 19/14 |  |  | July | July | Done | Rajesh
217 | 21 |  | 64/6 |  |  | July | July | Done | Suraja Ram
218 | 22 |  | 46/1 |  |  | July | July | Done | Suraja Ram
219 | 23 |  | 44/5 |  |  | July | July | Done | Suraja Ram
220 | 24 |  | 35/5 |  |  | July | July | Done | Suraja Ram
221 | 25 |  | 35/7 |  |  | July | July | Done | Suraja Ram
222 | 26 |  | 35/6 |  |  | July | July | Done | Suraja Ram
223 | 27 |  | 34/4 |  |  | July | July | Done | Suraja Ram
224 | 28 |  | 15/6 |  |  | July | July | Done | Suraja Ram
225 | 29 |  | 39/3 |  |  | July | July | Done | Suraja Ram
226 | 30 |  | 39/1 |  |  | July | July | Done | Suraja Ram
227 | 31 |  | 39/2 |  |  | July | July | Done | Suraja Ram
228 | 32 |  | 40/9 |  |  | July | July | Done | Suraja Ram
229 | 33 |  | 40/8 |  |  | July | July | Done | Suraja Ram
230 | 34 |  | 39/5 |  |  | July | July | Done | Suraja Ram
231 | 35 |  | 39/6 |  |  | July | July | Done | Suraja Ram
232 | 36 |  | 45/0 |  | 15.07.25 | 15.07.25 | 15.07.25 | Done | Suraja Ram
233 | 37 |  | 31/4 |  | 22.07.25 | 22.07.25 | 22.07.25 | Done | Suraja Ram
234 | 38 |  | 31/3 |  | 22.07.25 | 22.07.25 | 22.07.25 | Done | Suraja Ram
235 | 39 |  | 15/7 |  | 23.07.25 | 23.07.25 | 23.07.25 | Done | Shiv Power
236 | 40 |  | 15/9 |  | July | July | July | Done | SB Enterprises
237 | 41 |  | 14/5 |  | July | July | July | Done | SB Enterprises
238 | 42 |  | 31/2 |  | 23.07.25 | 23.07.25 | 23.07.25 | Done | Suraja Ram
239 | 43 |  | 32/5 |  | 27.07.25 | 27.07.25 | 27.07.25 | Done | Suraja Ram
240 | 44 |  | 31/0 |  | 28.07.25 | 28.07.25 | 28.07.25 | Done | Suraja Ram
241 | 45 |  | 64/2 |  | 03.08.25 | 03.08.25 | 03.08.25 | Done | Suraja Ram
242 | 46 |  | 64/3 |  | 04.08.25 | 04.08.25 | 04.08.25 | Done | Suraja Ram
243 | 47 |  | 64/7 |  | 01.08.25 | 01.08.25 | 01.08.25 | Done | Suraja Ram
244 | 48 |  | 64/5 |  | 02.08.25 | 02.08.25 | 02.08.25 | Done | Suraja Ram
245 | 49 |  | 64/0 |  | 29.07.25 | 29.07.25 | 29.07.25 | Done | Suraja Ram
246 | 50 |  | 64/1 |  | 30.07.25 | 30.07.25 | 30.07.25 | Done | Suraja Ram
247 | 51 |  | 64/4 |  | 31.07.25 | 31.07.25 | 31.07.25 | Done | Suraja Ram
248 | 52 |  | 35/1 |  |  | 17.08.25 | 17.08.25 | Done | Suraja Ram
249 | 53 |  | 35/2 |  |  | 13.08.25 | 13.08.25 | Done | Suraja Ram
250 | 54 |  | 35/3 |  |  | 20.08.25 | 21.08.25 | Done | Suraja Ram
251 | 55 |  | 35/4 |  |  | 21.08.25 | 21.08.25 | Done | Suraja Ram
252 | 56 |  | 35/0 |  |  | 22.08.25 | 22.08.25 | Done | Suraja Ram
253 | 57 |  | 37/1 |  |  | 23.08.25 | 23.08.25 | Done | Suraja Ram
254 | 58 |  | 30/2 |  |  | 24.08.25 | 24.08.25 | Done | Suraja Ram
255 | 59 |  | 30/1 |  |  | 25.08.25 | 25.08.25 | Done | Suraja Ram
256 | 60 |  | 31/1 |  |  | 28.08.25 | 28.08.25 | Done | Suraja Ram
257 | 1 |  | 65/1 |  | 05.09.25 | 05.09.25 | 05.09.25 | Done | Suraja Ram
258 | 2 |  | 46/0 |  | 06.08.25 | 05.09.25 | 05.09.25 | Done | Suraja Ram
259 | 3 |  | 66/3 |  | 05.09.25 | 05.09.25 | 05.09.25 | Done | Suraja Ram
260 | 4 |  | 23/4 |  | 09.09.25 | 06.09.25 | 06.09.25 | Done | Munotosh
261 | 5 |  | 22/3 |  | 12.09.25 | 12.09.25 | 12.09.25 | Done | Munotosh
262 | 6 |  | 22/4 |  | 05.09.25 | 05.09.25 | 05.09.25 | Done | Munotosh
263 | 7 |  | 33/1 |  | 10.09.25 | 10.09.25 | 10.09.25 | Done | Suraja Ram
264 | 8 |  | 33/2 |  | 10.09.25 | 10.09.25 | 10.09.25 | Done | Suraja Ram
265 | 15 |  | 32/6 |  | 29.09.25 | 29.09.25 | 29.09.25 | Done | Suraja Ram
266 | 16 |  | 34/1 |  | 30.09.25 | 30.09.25 | 30.09.25 | Done | Suraja Ram
267 | 1 |  | 34/2 |  | 01.10.25 | 01.10.25 | 01.10.25 | Done | Suraja Ram
268 | 2 |  | 36/0 |  | 03.10.25 | 03.10.25 | 03.10.25 | Done | Suraja Ram
269 | 3 |  | 33/5 |  | 04.10.25 | 04.10.25 | 04.10.25 | Done | Suraja Ram
270 | 4 |  | 65/0 |  | 08.10.25 | 08.10.25 | 08.10.25 | Done | Suraja Ram
271 | 5 |  | 65/2 |  | 06.10.25 | 08.10.25 | 08.10.25 | Done | Suraja Ram
272 | 6 |  | 33/4 |  | 14.10.25 | 14.10.25 | 14.10.25 | Done | Suraja Ram
273 | 7 |  | 24/2 |  | 11.11.25 | 13.11.25 | 13.11.25 | Done | Jai Bagrang Bali
274 | 8 |  | 24/3 |  | 12.11.25 | 12.11.25 | 12.11.25 | Done | Jai Bagrang Bali
275 | 9 |  | 24/0 |  | 13.11.25 | 13.11.25 | 13.11.25 | Done | Jai Bagrang Bali
276 | 10 |  | 26/7 |  | 19.12.25 | 19.12.25 | 19.12.25 | Done | Suraja Ram
277 | 11 |  | 26/2 |  | 19.12.25 | 19.12.25 | 19.12.25 | Done | Suraja Ram
278 | 12 |  | 19/4 |  |  | 15.01.26 | 16.01.26 | Done | Balaji
279 | 13 |  | 19/5 |  |  | 15.01.26 | 16.01.26 | Done | Balaji
280 | 14 |  | 26/0 |  |  | 02.01.26 | 02.01.26 | Done | Suraja Ram
281 | 15 |  | 26/1 |  |  | 03.01.26 | 03.01.26 | Done | Suraja Ram
282 | 16 |  | 26/3 |  |  | 04.01.26 | 04.01.26 | Done | Suraja Ram
283 | 17 |  | 26/4 |  |  | 05.01.26 | 05.01.26 | Done | Suraja Ram
284 | 18 |  | 26/5 |  |  | 06.01.26 | 06.01.26 | Done | Suraja Ram
285 | 19 |  | 26/6 |  |  | 07.01.26 | 07.01.26 | Done | Suraja Ram
286 | 20 |  | 33/3 |  |  | 11.01.26 | 11.01.26 | Done | Suraja Ram
287 | 21 |  | 33/6 |  |  | 01.01.26 | 01.01.26 | Done | Suraja Ram
288 | 22 |  | 33/7 |  |  | 03.01.26 | 03.01.26 | Done | Suraja Ram
289 | 23 |  | 33/8 |  |  | 02.01.26 | 02.01.26 | Done | Suraja Ram
290 | 24 |  | 34/0 |  |  | 04.01.26 | 04.01.26 | Done | Suraja Ram
291 | 25 |  | 34/3 |  |  | 05.01.26 | 05.01.26 | Done | Suraja Ram
292 | 26 |  | 34/5 |  |  | 06.01.26 | 06.01.26 | Done | Suraja Ram
293 | 27 |  | 37/0 |  |  | 03.01.26 | 03.01.26 | Done | Suraja Ram | 34/6 Not Done
294 | 28 |  | 27/0 |  |  | 09.01.26 | 09.01.26 | Done | Suraja Ram
295 | 29 |  | 27/1 |  |  | 11.01.26 | 11.01.26 | Done | Suraja Ram
296 | 30 |  | 27/2 |  |  | 15.01.26 | 15.01.26 | Done | Suraja Ram
297 | 31 |  | 27/3 |  |  | 16.01.26 | 16.01.26 | Done | Suraja Ram
298 | 32 |  | 27/4 |  |  | 17.01.26 | 17.01.26 | Done | Suraja Ram
299 | 33 |  | 27/5 |  |  | 19.01.26 | 19.01.26 | Done | Suraja Ram
300 | 34 |  | 28/0 |  |  | 20.01.26 | 20.01.26 | Done | Suraja Ram
301 | 35 |  | 28/1 |  |  | 20.01.26 | 20.01.26 | Done | Suraja Ram
302 | 36 |  | 28/2 |  |  | 21.01.26 | 21.01.26 | Done | Suraja Ram
303 | 37 |  | 28/3 |  |  | 22.01.26 | 22.01.26 | Done | Suraja Ram
304 | 38 |  | 28/4 |  |  | 23.01.26 | 23.01.26 | Done | Suraja Ram
305 | 39 |  | 28/5 |  |  | 24.01.26 | 24.01.26 | Done | Suraja Ram
306 | 40 |  | 28/6 |  |  | 25.01.26 | 25.01.26 | Done | Suraja Ram
307 | 41 |  | 28/7 |  |  | 27.01.26 | 27.01.26 | Done | Suraja Ram
308 | 42 |  | 28/8 |  |  | 28.01.26 | 28.01.26 | Done | Suraja Ram
309 | 43 |  | 28/9 |  |  | 29.01.26 | 29.01.26 | Done | Suraja Ram
310 | 44 |  | 29/0 |  |  | 30.01.26 | 30.01.26 | Done | Suraja Ram
311 | 45 |  | 29/1 |  |  | 30.01.26 | 30.01.26 | Done | Suraja Ram
312 | 46 |  | 29/2 |  |  | 30.01.26 | 30.01.26 | Done | Suraja Ram
313 | 47 |  | 29/3 |  |  | 31.01.26 | 31.01.26 | Done | Suraja Ram
314 | 48 |  | 29/4 |  |  | 01.02.26 | 01.02.26 | Done | Suraja Ram
315 | 49 |  | 29/5 |  |  | 02.02.26 | 02.02.26 | Done | Suraja Ram
316 | 50 |  | 29/6 |  |  | 03.02.26 | 03.02.26 | Done | Suraja Ram
317 | 51 |  | 29/7 |  |  | 04.02.26 | 04.02.26 | Done | Suraja Ram
318 | 52 |  | 29/8 |  |  | 05.02.26 | 05.02.26 | Done | Suraja Ram
319 | 53 |  | 29/10 |  |  | 06.02.26 | 06.02.26 | Done | Suraja Ram
320 | 54 |  | 30/0 |  |  | 07.02.26 | 07.02.26 | Done | Suraja Ram
321 | 55 |  | 30/3 |  |  | 08.02.26 | 08.02.26 | Done | Suraja Ram
322 | 56 |  | 32/2 |  |  | 09.02.26 | 09.02.26 | Done | Suraja Ram
323 | 57 |  | 32/3 |  |  | 10.02.26 | 10.02.26 | Done | Suraja Ram
324 | 58 |  | 32/4 |  |  | 11.02.26 | 11.02.26 | Done | Suraja Ram
325 | 59 |  | 32/7 |  |  | 12.02.26 | 12.02.26 | Done | Suraja Ram
326 | 60 |  | 33/0 |  |  | 13.02.26 | 13.02.26 | Done | Suraja Ram
327 | 61 |  | 32/8 |  |  | 12.03.26 | 12.03.26 | Done | Suraja Ram

## Idling details from Aug
Erection Team idle month of Aug. PKG-G
Sr No | Gang Name | Activity | Location no | PKGs | Time |  |  | Date |  |  | Reason | Photograph attached | Remarks
[5 empty] | Start | End | Total time | Start | End | Total
1 | Pusplata-6 | Erection | 23/2 | G | 12:30 | 20:21 | 7.85 | 2025-07-30 | 2025-07-30 | 0 | ROW | Photos\23-2.jpg
2 | Gourishankar | Erection | 31/1 | G | 8:00 | 12:26 | 4.4333 | 2025-08-02 | 2025-08-02 | 0 | Approch road issue | Photos\31-1.jpg
3 | Bhairo /Arawali | Erection | 4/0 | G | 12:30 | 11:05 | 22.5833 | 2025-08-03 | 2025-08-04 | 1 | Due to non-payment of crop composition | Photos\4-0.png
4 | Gourishankar | Erection | 31/1 | G | 14:52 | 17:06 | 2.2333 | 2025-08-03 | 2025-08-03 | 0 | Due to non-payment of crop composition | Photos\31-1 2nd idle.jpg
5 | Priyanka -Sudheer | Erection | 16/6 | G | 17:31 | 18:02 | 0.51667 | 2025-08-03 | 2025-08-03 | 0 | Due to non-payment of crop composition | Photos\16-6 1st.jpg
6 | Arawali Infra.-2 | Erection | 16/1 | G | 9:16 | 9:27 | 0.18333 | 2025-08-05 | 2025-08-05 | 0 | Due to non-payment of crop composition | Photos\16-1.png
7 | Priyanka -Sudheer | Erection | 16/6 | G | 13:32 | 16:41 | 27.15 | 2025-08-04 | 2025-08-05 | 1 | Due to non-payment of crop composition | Photos\16-6 2nd.png | Team move to other locs due ROW not cleared
8 | Pusplata-4 | Erection | 25/2 | G | 8:00 | 17:45 | 9.75 | 2025-08-05 | 2025-08-05 | 0 | Locs not confirmed by the client; therefore, the loaded vehicle has been retained at the site due to a crop composition issue | Photos\25-2.png | ROW not cleared as team move to 21/14
9 | Priyanka Devi -2 | Erection | 17/5 | G | 12:58 | 17:30 | 4.5333 | 2025-08-05 | 2025-08-05 | 0 | Due to non-payment of crop composition | Photos\17-5.jpg
10 | Pusplata-4 | Erection | 21/14 | G | 9:36 | 10:41 | 1.0833 | 2025-08-06 | 2025-08-06 | 0 | Due to non-payment of crop composition | Photos\21-14.png
11 | Pusplata-6 | Erection | 23/2 | G | 9:50 | 13:43 | 3.8833 | 2025-08-06 | 2025-08-06 | 0 | Due to non-payment of crop composition | Photos\23-2.jpg
12 | Rahim Khan | Stringing | 40/2 | G | 11:28 | 13:58 | 2.5 | 2025-08-06 | 2025-08-06 | 0 | Due to non-payment of crop composition | Photos\40-2 Stringing.png
13 | Priyanka Devi -2 | Erection | 17/5 | G | 7:00 | 19:30 | 12.5 | 2025-08-06 | 2025-08-06 | 0 | Due to non-payment of crop composition | Photos\17-5.jpg
14 | Pusplata-1 | Erection | 23/0 | G | 18:26 | 19:30 | 1.0667 | 2025-08-07 | 2025-08-07 | 0 | Due to non-payment of crop composition
15 | Satyam (Nitish) | Erection | 33/2 | G | 7:30 | 11:32 | 4.0333 | 2025-08-08 | 2025-08-08 | 0 | Due to non-payment of crop composition | Photos\33-2.jpg
16 | Priyanka Devi -2 | Erection | 17/5 | G | 17:42 | 8:28 | 14.7667 | 2025-08-08 | 2025-08-09 | 1 | Due to non-payment of crop composition
17 | Pusplata-5 | Erection | 21/0 | G | 8:44 | 16:57 | 8.2167 | 2025-08-09 | 2025-08-09 | 0 | Due to non-payment of crop composition | Photos\21-0.jpg
18 | Pusplata -Dharamveer | Erection | 21/12 | G | 18:16 | 12:00 | 17.7333 | 2025-08-09 | 2025-08-10 | 1 | Due to non-payment of crop composition | Photos\21-12.png
19 | Pusplata-2 | Erection | 21/13 | G | 12:45 | 19:00 | 162.5 | 2025-08-06 | 2025-09-01 | 26 | Due to non-payment of crop composition | Photos\21-13.png
20 | Arawali Infra.-2 | Erection | 16/1 | G | 10:54 | 13:05 | 2.1833 | 2025-08-12 | 2025-08-12 | 0 | Due to non-payment of crop composition | Photos\16-1.jpg
21 | MC Construction | Stringing | 64/6 | G | 11:30 | 13:00 | 1.5 | 2025-08-12 | 2025-08-12 | 0 | Due to non-payment of crop composition
22 | Priyanka Devi -Sudheer | Erection | 18/0 | G | 10:31 | 16:03 | 5.5333 | 2025-08-12 | 2025-08-12 | 0 | Due to non-payment of crop composition | Photos\18-0.png
23 | Priyanka Devi -2 | Erection | 17/5 | G | 10:44 | 20:55 | 10.1833 | 2025-08-12 | 2025-08-12 | 0 | Due to non-payment of crop composition | Photos\17-5.jpg
24 | Jwala singh -3 | Erection | 9/0 | G | 12:35 | 19:55 | 146.6667 | 2025-08-12 | 2025-09-01 | 20 | Due to non-payment of crop composition | Photos\9-0.png | Due to locs not resolved team shift to other locs
25 | Pusplata (Ramchandra) | Erection | 22/0 | G | 7:30 | 12:43 | 5.2167 | 2025-08-14 | 2025-08-14 | 0 | Due to non-payment of crop composition | D:\TB401-408\TB401 Project\ROW\Photos\22-0.jpg
26 | Pusplata (Ramchandra) | Erection | 22/0 | G | 7:30 | 19:30 | 12 | 2025-08-16 | 2025-08-17 | 1 | Due to non-payment of crop composition
27 | Pusplata-Ashok | Erection | 4/4 | G | 11:17 | 12:18 | 1.0167 | 2025-08-19 | 2025-08-19 | 0 | Due to non-payment of crop composition | Image/WA0038.jpg
28 | Pusplata-5 | Erection | 21/0 | G | 16:56 | 19:30 | 2.5667 | 2025-08-20 | 2025-08-20 | 0 | Due to non-payment of crop composition | D:\TB401-408\TB401 Project\ROW\Photos\20-0 & 21-0 (2).png
29 | Pusplata-Rajaram | Erection | 20/0 | G | 16:56 | 19:30 | 2.5667 | 2025-08-20 | 2025-08-20 | 0 | Due to non-payment of crop composition | D:\TB401-408\TB401 Project\ROW\Photos\20-0 & 21-0 (2).png
30 | Pusplata (Ramchandra) | Erection | 22/0 | G | 7:30 | 15:26 | 7.9333 | 2025-08-22 | 2025-08-22 | 0 | Due to non-payment of crop composition | D:\TB401-408\TB401 Project\ROW\Photos\22-0.png
31 | Pusplata (Ramchandra) | Erection | 22/0 | G | 3:30 | 17:57 | 3.6125 | 2025-08-22 | 2025-08-22 | 0 | Due to non-payment of crop composition
32 | Sanjeev kumar | Erection | 26/6 | G | 9:54 | 19:30 | 9.6 | 2025-09-03 | 2025-09-03 | 0 | Due to non-payment of crop composition | D:\TB401-408\TB401 Project\ROW\Photos\26-6.png
33 | Rahul Kumar | Erection | 28/7 | G | 12:31 | 18:12 | 23.6806 | 2025-09-03 | 2025-09-04 | 1 | Due to non-payment of crop composition | D:\TB401-408\TB401 Project\ROW\Photos\28-7.png
34 | Sanjeev kumar | Erection | 26/5 | G | 16:15 | 18:39 | 2.4 | 2025-09-04 | 2025-09-04 | 0 | Due to non-payment of crop composition | D:\TB401-408\TB401 Project\ROW\Photos\26-5.png
35 | Priyanka Devi - Santosh | Erection | 18/4 | G | 10:35 | 18:39 | 209.7333 | 2025-09-10 | 2025-10-06 | 26 | Due to non-payment of crop composition | D:\TB401-408\TB401 Project\ROW\Photos\18-4.png
36 | Priyanka devi (Subodh) | Erection | 10/1 | G | 17:19 | 18:39 | 1.3333 | 2025-09-26 | 2025-09-26 | 0 | Due to non-payment of crop composition
37 | krishna Const | Stringing | 32/0 to 33/0 | G | 7:30 | 7:00 | 117.5 | 2025-09-24 | 2025-09-29 | 5 | Due to infravision internal issue
38 | krishna Const | Stringing | 32/0 to 33/0 | G | 7:30 | 12:00 | 4.5 | 2025-10-01 | 2025-10-01 | 0 | Due to non-payment of crop composition
39 | Jirwa Devi | Erection | 25/0 | G | 15:30 | 19:30 | 4 | 2025-10-27 | 2025-10-27 | 0 | Due to non-payment of crop composition
40 | Sunny Const | Erection | 18/6 | G | 12:00 | 19:30 | 22.5 | 2025-10-21 | 2025-11-21 | 31 | Due to non-payment of crop composition
41 | Vivek Ganju | Erection | 18/10 | G | 7:30 | 19:30 | 12 | 2025-10-26 | 2025-10-27 | 1 | Due to non-payment of crop composition
42 | Krishna Const | Stringing | 34/0 to 34/1 | G | 13:30 | 18:00 | 4.5 | 2025-11-04 | 2025-11-04 | 0 | ROW
43 | Vivek Ganju | Erection | 17/2 | G | 7:30 | 12:30 | 5 | 2025-11-13 | 2025-11-13 | 0 | ROW
44 | Krishna Const-2 | Stringing | 25/0 to 26/0 | G | 16:00 | 13:00 | 21 | 2025-11-17 | 2025-11-18 | 1 | ROW
45 | Krishna Const | Stringing | 30/0 to 31/0 | G | 7:30 | 19:30 | 60 | 2025-11-12 | 2025-11-17 | 5 | ROW
46 | Krishna Const | Stringing | 29/0 to 30/0 | G | 7:30 | 13:47 | 6.2833 | 2025-11-22 | 2025-11-22 | 0 | ROW
47 | Krishna Const | Stringing | 29/0 to 30/0 | G | 7:30 | 2:46 | 19.2667 | 2025-11-25 | 2025-11-26 | 1 | Due to some issue from Infravision & Stringing team (manhandling)
48 | Nirmal Mahto | Erection | 11/1 | G | 7:30 | 19:30 | 12 | 2025-11-28 | 2025-11-29 | 1 | ROW
49 | Vedanta Const | Erection | 10/22 | G | 7:30 | 19:30 | 12 | 2025-11-28 | 2025-11-29 | 1 | ROW
50 | Sital Singh | Erection | 11/10 | G | 7:30 | 19:30 | 12 | 2025-12-03 | 2025-12-04 | 1 | ROW
51 | Sunny Const | Erection | 19/6 | G | 14:30 | 14:20 | 47.6667 | 2025-12-08 | 2025-12-10 | 2 | ROW
52 | Ganesh Sinha | Erection | 21/10 | G | 7:30 | 14:20 | 20.5 | 2025-12-17 | 2025-12-20 | 3 | ROW
53 | Nasir | Stringing | 17/0 to 18/0 | G | 7:30 | 14:20 | 41 | 2025-12-19 | 2025-12-25 | 6 | ROW at 18/0 (Gang move to 14-15)
54 | Krishna-2 | Stringing | 22/0 to 23/0 | G | 7:30 | 15:15 | 38.75 | 2025-12-31 | 2026-01-05 | 5 | 22/1 & 22/2 ROW
55 | Vedanta Const | Erecrtion | 18/3 | G | 9:20 | 17:40 | 33.3333 | 2026-01-07 | 2026-01-11 | 4 | 18/3 G ROW
56 | Vedanta Const | Erecrtion | 18/3 | G | 8:00 | 18:00 | 10 | 2026-01-16 | 2026-01-17 | 1
Total idle due to ROW issue - (H/Days) | [6 empty] | 1259.0431 |  |  | 146

## Crane Erection PKG-G
S no | Locs | TOT | Crane Using | [5 empty] | Manual Erection |  |  |  |  | Gangs
|  |  | Start Date | Complete Date | No of Days | Weight | Gang | Manpower | Start Date | Complete Date | No of Days | Weight | Manpower
1 | 1A/4 | DA+3 | 04.05.25 | 08.05.25 | 5 | 17.4811 | Anil Kumar | 42 | 01.06.25 | 05.06.25 | 5 | 21.3659 | 30 | Bhairo Mahto (Departmental)
2 | 1A/3 | DA+0 | 14.05.25 | 18.05.25 | 5 | 16.8768 | Anil Kumar | 42 | 12.06.25 | 15.06.25 | 4 | 20.6272 | 30 | Bhairo Mahto (Departmental)
4 | 1A/6 | DA+0 | 01.06.25 | 03.06.25 | 3 | 16.8768 | Anil Kumar | 42 | 14.06.25 | 21.06.25 | 8 | 20.6272 | 30 | Kewat (Departmental)
3 | 1A/5 | DA+6 | 19.05.25 | 27.05.25 | 9 | 20.4358 | Anil Kumar | 42 | 22.06.25 | 27.06.25 | 6 | 24.9771 | 33 | Bhairo Mahto (Departmental)
5 | 1A/7 | DA+3 | 09.06.25 | 12.06.25 | 4 | 17.4811 | Anil Kumar | 42 | 30.06.25 | 07.07.25 | 8 | 21.3659 | 33 | Kewat (Departmental)
6 | 1A/0 | DD60+0 | 18.06.25 | 23.06.24 | 6 | 51.667 | Anil Kumar | 53 | 29.06.25 | 14.07.25 | 15 | 34.462 | 32 | Bhairo Mahto/Ramayan (Departmental)
7 | 1/0 | DE+0 | 22.06.25 | 01.07.25 | 10 | 51.667 | Anil Kumar | 53 | 17.07.25 | 31.07.25 | 13 | 34.462 | 32 | Bhairo Mahto/Ramayan (Departmental)
8 | 4/0 | DD60+6 | 17.07.25 | 24.07.25 | 8 | 35.336 | Bhairo | 33 | 02.08.25 | 12.08.25 | 10 | 65.624 | 33 | Bhairo Mahto (Departmental) | 100.96
9 | 4/1 | DA+0 | 27.08.25 | 30.07.25 | 4 | 16.8768 | Bhairo | 33 | 11.08.25 | 16.08.25 | 6 | 20.6272 | 33 | Bhairo Mahto (Departmental)
Total Weight/Days |  |  |  |  | 54 | 244.6986 |  |  |  |  | 75 | 264.1384
Total Average Weight/Days |  |  |  |  | 4.5315 | [5 empty] | 3.5218

## Erection Productivity (hidden)
Sr no | Item | Unit | Total | Comp Qty
|  |  | Qty | 31.05.25
1 | Erection | Nos | 521 | 292
2 | Stringing | KM | 202 | 61.016
Gang Wise Output ction - Jul'25
Sr. No. | Sub-Contractor Name | WIP |  |  | 01.09.25 | 02.09.25 | 03.09.25 | 05.09.25 | 06.09.25 | 07.09.25 | 08.09.25 | 09.09.25 | 10.09.25 | 11.09.25 | 12.09.25 | 13.09.25 | 14.09.25 | 15.09.25 | 16.09.25 | 18.09.25 | 19.09.25 | 20.09.25 | 22.09.25 | 23.09.25 | 24.09.25 | 25.09.25 | 01.10.25 | 03.10.25 | 04.10.25 | 05.10.25 | 06.10.25 | 07.10.25 | 08.10.25 | 09.10.25 | Cumulative Till dated | Status | Manpower
|  | Loc. No. | Type of Tower | Tower Weight | [32 empty] | Plan | Actual | Shotfall
1 | Priyanka devi (Subodh) | 10/1 | DA+3 | 38.847 | [19 empty] | 4.82 | 4.82 | 4.82 | 11.82 | 12.567 | [6 empty] | 38.847 | Complete |  |  |  | 0
2 | Priyanka devi (Sudheer) | 19/2 | DA+3 | 38.847 | [22 empty] | 12.82 | 12.82 | 12.82 | [5 empty] | 38.46 | Complete
3 | Jwala singh -3 | 9/0 | DD60+18 | 129.11 | [21 empty] | 8.82 | 8.82 | 8.82 | 8.82 | 8.82 | 8.82 | 8.82 | 8.82 |  | 70.56 | 2nd Section |  |  |  | 58.55
4 | Sanjeev kumar | 27/0 | DC2+9 | 81.945 | [21 empty] | 8.82 | 8.82 | 8.82 | 8.82 | 8.82 | 8.82 | 6.82 | 6.82 |  | 66.56 | 1st Section |  |  |  | 15.385
5 | Priyanka Devi - Santosh | 18/4 | DA+3 | 38.847 | [7 empty] | 4.82 | 4.82 | [17 empty] | 6.82 | 6.82 | 6.82 |  | 30.1 | ROW |  |  |  | 8.747
6 | Sital Singh-1 | 10/15 | DA+3 | 38.847 | [22 empty] | 5.82 | 5.82 | 3.82 | 3.82 |  | 2.82 | 2.82 |  | 24.92 | 1st Section |  |  |  | 13.927
7 | Ganesh Sinha | 28/6 | DA+9 | 47.184 | [22 empty] | 5.82 | 5.82 | 5.82 | 5.82 | 5.82 | 5.82 | 5.82 | 6.444 | 47.184 | Complete |  |  |  | 0
8 | Shyam Construction | 17/3 | DA+3 | 38.847 | [26 empty] | 5.82 | 5.82 | 5.82 |  | 17.46 | 1st Section |  |  |  | 21.387
9 | Sital Singh-1 | 8/0 | DB1+0 | 57.597 | [25 empty] | 8.82 | 8.82 | 8.82 | 8.82 |  | 35.28 | 3rd Section |  |  |  | 22.317
| Vivek Ganju | 18/7 | DA+6 | 45.413 | [30 empty] | 0 | Materials Shifting
Total |  |  |  | 555.484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.82 | 4.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 29.28 | 29.28 | 27.28 | 36.1 | 44.92 | 45.74 | 45.74 | 6.444 | 316.631 |  | 0 | 0 | 0
[5 empty] | 14 | 6 | 7 | 8 | 7 | 7 | 6 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68857 | 0.964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4.88 | 4.88 | 4.5467 | 6.0167 | 6.4171 | 6.5343 | 6.5343 | 0.92057

## Eretion - PKG-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Erection PKG-F
Cum Sl. No. | Month Sl. No. | JMC No. | Location No. | Tower Type | Depth of Fdn | Dt. of Start | Dt. of Complete | Name of Sub-Contractor | Ramarks
Feb-24
1 | 1 |  | 60/7 | DA+3 |  | 28.1.24 | 04.02.24 | Suraj const | Complete |  |  |  | 38.847
2 | 2 |  | 59/13 | DA+3 |  | 01.02.24 | 07.02.24 | Chinta Devi | Complete |  |  |  | 38.847
3 | 3 |  | 63/6 | DA+3 |  | 03.02.24 | 10.02.24 | Sunny Const. | Complete |  |  |  | 38.847
4 | 4 |  | 59/5 | DA+3 |  | 05.02.24 | 11.02.24 | Ganesh Const | Complete |  |  |  | 38.847
5 | 5 |  | 59/14 | DA+6 |  | 08.02.24 | 13.02.24 | Chinta Devi | Complete |  |  |  | 45.413
6 | 6 |  | 60/8 | DA+0 |  | 09.02.24 | 15.02.24 | Suraj const | Complete |  |  |  | 37.504
7 | 7 |  | 63/7 | DA+3 |  | 11.02.24 | 15.02.24 | Sunny Const. | Complete |  |  |  | 38.847
8 | 8 |  | 59/6 | DA+3 |  | 12.02.24 | 18.02.24 | Ganesh Const | Complete |  |  |  | 38.847
9 | 9 |  | 59/12 | DA+6 |  | 13.02.24 | 20.02.24 | Chinta Devi | Complete |  |  |  | 45.413
10 | 10 |  | 63/8 | DA+3 |  | 15.02.24 | 20.02.24 | Sunny Const. | Complete |  |  |  | 38.847
11 | 11 |  | 60/10 | DA+0 |  | 15.02.24 | 21.02.24 | Suraj const | Complete |  |  |  | 37.504
12 | 12 |  | 62/5 | DA+0 |  | 17.02.24 | 22.02.24 | Sobha Devi | Complete |  |  |  | 37.504
13 | 13 |  | 59/7 | DA+3 |  | 18.02.24 | 24.02.24 | Ganesh Const | Complete |  |  |  | 38.847
14 | 14 |  | 59/10 | DA+0 |  | 20.02.24 | 24.02.24 | Chinta Devi | Complete |  |  |  | 37.504
15 | 15 |  | 64/1 | DA+0 |  | 20.02.24 | 24.02.24 | Sunny Const. | Complete |  |  |  | 37.504
16 | 16 |  | 60/11 | DA+3 |  | 21.02.24 | 26.02.24 | Suraj const | Complete |  |  |  | 38.847
17 | 17 |  | 62/4 | DA+3 |  | 22.02.24 | 26.02.24 | Sobha Devi | Complete |  |  |  | 38.847
18 | 18 |  | 59//9 | DA+3 |  | 24.02.24 | 28.02.24 | Chinta Devi | Complete |  |  |  | 38.847
19 | 19 |  | 62/3 | DA+0 |  | 26.02.24 | 28.02.24 | Sobha Devi | Complete |  |  |  | 37.504
20 | 20 |  | 59/8 | DB1+3 |  | 24.02.24 | 29.02.24 | Ganesh Const | Complete |  |  |  | 60.097
21 | 21 |  | 64/4 | DA+3 |  | 24.02.24 | 29.02.24 | Sunny Const. | Complete |  |  |  | 38.847
22 | 22 |  | 60/6 | DA+0 |  | 26.02.24 | 29.02.24 | Suraj const | Complete |  |  |  | 37.504
| March'24 | [12 empty] | 879.615
23 | 1 |  | 62/2 | DA+3 |  | 29.02.24 | 03.03.24 | Sobha Devi | Complete |  |  |  | 38.847
24 | 2 |  | 64/5 | DA+3 |  | 29.02.24 | 04.03.24 | Sunny Const. | Complete |  |  |  | 38.847
25 | 3 |  | 65/2 | DA+0 |  | 29.02.24 | 06.03.24 | Chinta Devi | Complete |  |  |  | 37.504
26 | 4 |  | 62/7 | DA+3 |  | 04.03.24 | 07.03.24 | Sobha Devi | Complete |  |  |  | 38.847
27 | 5 |  | 59/16 | DA+9 |  | 29.02.24 | 11.03.24 | Ganesh Const. | Complete |  |  |  | 47.184
28 | 6 |  | 65/4 | DA+0 |  | 06.03.24 | 11.03.24 | Chinta Devi | Complete |  |  |  | 37.504
29 | 7 |  | 62/8 | DA+0 |  | 07.03.24 | 11.03.24 | Sobha Devi | Complete |  |  |  | 37.504
30 | 8 |  | 62/9 | DA+3 |  | 11.03.24 | 15.03.24 | Sobha Devi | Complete |  |  |  | 38.847
31 | 9 |  | 65/3 | DA+3 |  | 11.03.24 | 16.03.24 | Chinta Devi | Complete |  |  |  | 38.847
32 | 10 |  | 60/5 | DA+3 |  | 11.03.24 | 17.03.24 | Ganesh Const. | Complete |  |  |  | 38.847
33 | 11 |  | 62/10 | DA+0 |  | 15.03.24 | 18.03.24 | Sobha Devi | Complete |  |  |  | 37.504
34 | 12 |  | 65/5 | DA+0 |  | 16.03.24 | 20.03.24 | Chinta Devi | Complete |  |  |  | 37.504
35 | 13 |  | 61/6 | DA+3 |  | 18.03.24 | 22.03.24 | Sobha Devi | Complete |  |  |  | 38.847
36 | 14 |  | 60/4 | DA+3 |  | 18.03.24 | 23.03.24 | Ganesh Const. | Complete |  |  |  | 38.847
37 | 15 |  | 65/6 | DA+0 |  | 20.03.24 | 26.03.24 | Chinta Devi | Complete |  |  |  | 37.504
38 | 16 |  | 64/6 | DA+0 |  | 21.03.24 | 26.03.24 | Sunny Const. | Complete |  |  |  | 37.504
39 | 17 |  | 61/7 | DA+9 |  | 22.03.24 | 28.03.24 | Sobha Devi | Complete |  |  |  | 47.184
40 | 18 |  | 64/7 | DA+3 |  | 26.03.24 | 30.03.24 | Sunny Const. | Complete |  |  |  | 38.847
41 | 19 |  | 60/3 | DA+3 |  | 23.03.24 | 31.03.24 | Ganesh Const. | Complete |  |  |  | 38.847
42 | 20 |  | 65/9 | DA+0 |  | 26.03.24 | 31.03.24 | Chinta Devi | Complete |  |  |  | 37.504
| Apr-'24 | [12 empty] | 782.87
43 | 1 |  | 64/8 | DA+3 |  | 30.03.24 | 03.04.24 | Sunny Const. | Complete |  |  |  | 38.847
44 | 2 |  | 65/11 | DA+0 |  | 31.03.24 | 04.04.24 | Chinta Devi | Complete |  |  |  | 37.504
45 | 3 |  | 60/2 | DA+3 |  | 31.03.24 | 07.04.24 | Ganesh Const. | Complete |  |  |  | 38.847
46 | 4 |  | 63/5 | DA+3 |  | 01.04.24 | 07.04.24 | Suraj Const | Complete |  |  |  | 38.847
47 | 5 |  | 64/9 | DA+3 |  | 03.04.24 | 08.04.24 | Sunny Const. | Complete |  |  |  | 38.847
48 | 6 |  | 67/1 | DA+0 |  | 06.04.24 | 10.04.24 | Chinta Devi | Complete |  |  |  | 37.504
49 | 7 |  | 61/0 | DB+0 |  | 06.04.24 | 11.04.24 | Sobha Devi | Complete |  |  |  | 57.598
50 | 8 |  | 63/4 | DA+0 |  | 07.04.24 | 13.04.24 | Suraj Const | Complete |  |  |  | 37.504
51 | 9 |  | 67/2 | DA+0 |  | 10.04.24 | 15.04.24 | Chinta Devi | Complete |  |  |  | 37.504
52 | 10 |  | 63/3 | DA+3 |  | 13.04.24 | 17.04.24 | Suraj Const | Complete |  |  |  | 38.847
53 | 11 |  | 64/10 | DA+3 |  | 15.04.24 | 20.04.24 | Chinta Devi | Complete |  |  |  | 38.847
54 | 12 |  | 64/2 | DA+3 |  | 16.04.243 | 21.04.24 | Sunny Const. | Complete |  |  |  | 38.847
55 | 13 |  | 61/2 | DA+6 |  | 16.04.24 | 22.04.24 | Sobha Devi | Complete |  |  |  | 45.413
56 | 14 |  | 63/2 | DA+0 |  | 17.04.24 | 22.04.24 | Suraj const | Complete |  |  |  | 37.504
57 | 15 |  | 60/1 | DA+6 |  | 18.04.24 | 25.04.24 | Ganesh Const. | Complete |  |  |  | 45.413
58 | 16 |  | 64/3 | DA+0 |  | 21.04.24 | 26.04.24 | Sunny Const. | Complete |  |  |  | 37.504
59 | 17 |  | 65/0 | DB1+0 |  | 21.04.24 | 27.04.24 | Chinta Devi | Complete |  |  |  | 57.598
60 | 18 |  | 63/1 | DA+3 |  | 22.04.24 | 27.04.24 | Suraj const | Complete |  |  |  | 38.847
61 | 19 |  | 61/1 | DA+6 |  | 22.04.24 | 29.04.24 | Sobha Devi | Complete |  |  |  | 45.413
| May'24 | [12 empty] | 787.235
62 | 1 |  | 65/1 | DA+0 |  | 27.04.24 | 03.05.24 | Chinta Devi | Complete |  |  |  | 37.504
63 | 2 |  | 62/11 | DA+3 |  | 27.04.24 | 03.05.24 | Suraj const | Complete |  |  |  | 38.847
64 | 3 |  | 64/0 | DB2+0 |  | 27.04.24 | 05.05.24 | Sunny Const. | Complete |  |  |  | 57.598
65 | 4 |  | 60/9 | DA+3 |  | 29.04.24 | 05.05.24 | Sobha Devi | Complete |  |  |  | 38.847
66 | 5 |  | 61/3 | DA+6 |  | 05.05.24 | 11.5.24 | Sobha Devi | Complete |  |  |  | 45.413
67 | 6 |  | 63/0 | DC1+0 |  | 03.05.24 | 12.5.24 | Suraj const | Complete |  |  |  | 66.381
68 | 7 |  | 61/4 | DA+3 |  | 11.5.24 | 16.05.24 | Sobha Devi | Complete |  |  |  | 38.847
69 | 8 |  | 60/0 | DC+0 |  | 05.05.24 | 18.05.24 | Ganesh | Complete |  |  |  | 66.381
70 | 9 |  | 61/10 | DA+9 |  | 12.5.24 | 19.05.24 | Suraj const | Complete |  |  |  | 47.184
71 | 10 |  | 61/5 | DA+3 |  | 16.05.24 | 22.05.24 | Sobha Devi | Complete |  |  |  | 38.847
72 | 11 |  | 61/9 | DA+0 |  | 19.05.24 | 23.05.24 | Suraj const | Complete |  |  |  | 37.504
73 | 12 |  | 59/15 | DA+6 |  | 18.05.24 | 30.05.24 | Ganesh | Complete |  |  |  | 45.413
74 | 13 |  | 61/8 | DA+6 |  | 23.05.24 | 30.05.24 | Suraj const | Complete |  |  |  | 45.413
75 | 14 |  | 55/3 | DA+0 |  | 12.5.24 | 31.05.24 | Mansukh lal | Complete |  |  |  | 37.504
| June'24 | [12 empty] | 641.683
76 | 1 |  | 57/3 | DA+0 |  | 29.05.24 | 11.06.24 | Bhuvneshwar | Complete |  |  |  | 37.504
77 | 2 |  | 55/4 | DA+0 |  | 01.06.24 | 19.06.24 | Mansukh lal | Complete |  |  |  | 37.504
78 | 3 |  | 57/4 | DA+0 |  | 12.06.24 | 27.06.24 | Bhuvneshwar | Complete |  |  |  | 37.504
| July'24 | [12 empty] | 112.512
79 | 1 |  | 62/1 | DA+3 |  | 04.07.24 | 12.07.24 | Bhuvneshwar | Complete |  |  |  | 38.847
80 | 2 |  | 62/6 | DA+3 |  | 15.07.24 | 26.07.24 | Bhuvneshwar | Complete |  |  |  | 38.847
| Aug'24 | [12 empty] | 77.694
81 | 1 |  | 57/6 | DA+3 |  | 13.08.24 | 20.08.24 | Sobha devi | Complete |  |  |  | 38.847
82 | 2 |  | 57/5 | DA+3 |  | 20.08.24 | 26.08.24 | Sobha devi | Complete |  |  |  | 38.847
| Sept'24 | [12 empty] | 77.694
83 | 1 |  | 62/0 | DB2+0 |  | 31.08.24 | 08.09.24 | Sobha devi | Complete |  |  |  | 57.598
84 | 2 |  | 50/9 | DA+0 |  | 28.08.24 | 09.09.24 | Uma const | Complete |  |  |  | 37.504
85 | 3 |  | 52/5 | DA+9 |  | 27.08.24 | 19.09.24 | Ganesh Sinha | Complete |  |  |  | 47.184
86 | 4 |  | 50/10 | DA+0 |  | 10.09.24 | 19.09.24 | Uma const | Complete |  |  |  | 37.504
87 | 5 |  | 48/1 | DA+9 |  | 08.09.24 | 25.09.24 | Kaushalya const | Complete |  |  |  | 47.184
88 | 6 |  | 51/1 | DA+0 |  | 19.09.24 | 26.09.24 | Uma const | Complete |  |  |  | 37.504
89 | 7 |  | 52/6 | DA+6 |  | 19.09.24 | 30.09.24 | Ganesh Sinha | Complete |  |  |  | 45.413
| Oct'24 | [8 empty] | WT | JMC | FTR |  | 309.891
90 | 1 | 1 | 57/7 | DA+3 |  | 27.09.24 | 01.10.24 | Sobha devi | Complete | 38.847 | Received | Done | 38.847
91 | 2 | 2 | 51/2 | DA+0 |  | 26.09.24 | 04.10.24 | Uma const | Complete | 37.504 | Not received | Not checked | 37.504
92 | 3 | 3 | 50/0 | DB2+0 |  | 02.10.24 | 07.10.24 | Sobha devi | Complete | 57.597 | Received | Done | 57.598
93 | 4 |  | 52/7 | DA+3 |  | 01.10.24 | 07.10.24 | Ganesh Sinha | Complete | 38.847 | Not received | Not checked | 38.847
94 | 5 |  | 50/1 | DA+6 |  | 07.10.24 | 15.10.24 | Sobha Devi | Complete | 45.413 | Not received | Done | 45.413
95 | 6 |  | 50/8 | DA+9 |  | 07.10.24 | 16.10.24 | Uma const | Complete | 47.148 | Not received | Not checked | 47.184
96 | 7 |  | 50/3 | DA+6 |  | 13.10.24 | 18.10.24 | Sobha Devi | Complete | 45.413 | Not received | Done | 45.413
97 | 8 |  | 48/0 | DC2+0 |  | 28.09.24 | 19.10.24 | Kaushalya const | Complete | 66.381 | Not received | Not checked | 66.381
98 | 9 |  | 52/8 | DA+6 |  | 08.10.24 | 19.10.24 | Ganesh Sinha | Complete | 45.413 | Not received | Not checked | 45.413
99 | 10 |  | 73/2 | DA+0 |  | 10.10.24 | 20.10.24 | Sanjeev Kumar | Complete | 37.504 | Not received | Not checked | 37.504
100 | 11 |  | 50/2 | DA+9 |  | 18.10.24 | 24.10.24 | Sobha Devi | Complete | 47.148 | Not received | Erection completed on 24.10.24 | 47.184
101 | 12 |  | 64/11 | DA+3 |  | 20.10.24 | 24.10.24 | Chinta devi | Complete |  | Not received | Erection completed on 24.10.24 | 38.847
102 | 13 |  | 59/11 | DA+6 |  | 17.10.24 | 26.10.24 | Uma const | Complete |  |  |  | 45.413
103 | 14 |  | 73/1 | DA+0 |  | 21.10.24 | 29.10.24 | Sanjeev Kumar | Complete |  |  |  | 37.504
104 | 15 |  | 50/4 | DA+9 |  | 24.10.24 | 30.10.24 | Sobha Devi | Complete |  |  |  | 47.184
| Nov'24 | [12 empty] | 676.236
105 | 1 |  | 55/6 | DA+0 |  | 23.10.24 | 01.11.24 | Jirwa Devi | Complete |  |  |  | 37.504
106 | 2 |  | 59/3 | DA+3 |  | 27.10.24 | 02.11.24 | Uma const | Complete |  |  |  | 38.847
107 | 3 |  | 50/7 | DA+0 |  | 01.11.24 | 04.11.24 | Sobha Devi | Complete |  |  |  | 37.504
108 | 4 |  | 59/4 | DA+3 |  | 01.11.24 | 09.11.24 | Uma const | Complete |  |  |  | 38.847
109 | 5 |  | 50/6 | DA+9 |  | 04.11.24 | 10.11.24 | Sobha Devi | Complete |  |  |  | 47.184
110 | 6 |  | 55/5 | DA+0 |  | 01.11.24 | 12.11.24 | Jirwa Devi | Complete |  |  |  | 37.504
111 | 7 |  | 73/9 | DA+0 |  | 09.11.24 | 13.11.24 | Chinta devi | Complete |  |  |  | 37.504
112 | 8 |  | 49/7 | DA+0 |  | 11.11.24 | 14.11.24 | Sobha Devi | Complete |  |  |  | 37.504
113 | 9 |  | 73/8 | DA+3 |  | 13.11.24 | 17.11.24 | Chinta devi | Complete |  |  |  | 38.847
114 | 10 |  | 49/6 | DA+0 |  | 15.11.24 | 18.11.24 | Sobha Devi | Complete |  |  |  | 37.504
115 | 11 |  | 73/6 | DA+0 |  | 17.11.24 | 20.11.24 | Chinta devi | Complete |  |  |  | 37.504
116 | 12 |  | 47/10 | DA+6 |  | 02.11.24 | 22.11.24 | Kaushalya const | Complete |  |  |  | 45.413
117 | 13 |  | 49/4 | DA+3 |  | 18.11.24 | 22.11.24 | Sobha Devi | Complete |  |  |  | 38.847
118 | 14 |  | 59/2 | DA+3 |  | 12.11.24 | 24.11.24 | Jirwa Devi | Complete |  |  |  | 38.847
119 | 15 |  | 52/10 | DA+9 |  | 13.11.24 | 25.11.24 | Ganesh Sinha | Complete |  |  |  | 47.184
120 | 16 |  | 49/5 | DA+3 |  | 23.11.24 | 27.11.24 | Sobha Devi | Complete |  |  |  | 38.847
121 | 17 |  | 49/2 | DA+3 |  | 27.11.24 | 30.11.24 | Sobha Devi | Complete |  |  |  | 38.847
122 | 18 |  | 72/3 | DA+3 |  | 24.11.24 | 30.11.24 | Sanjeev Kumar | Complete |  |  |  | 38.847
| Dec'24 | [12 empty] | 713.085
123 | 1 | -121 | 59/1 | DA+3 |  | 25.11.24 | 03.12.24 | Jirwa Devi | Complete |  |  |  | 38.847
124 | 2 | -120 | 52/9 | DA+3 |  | 26.11.24 | 05.12.24 | Ganesh Sinha | Complete |  |  |  | 38.847
125 | 3 | -119 | 49/3 | DA+3 |  | 02.12.24 | 05.12.24 | Sobha Devi | Complete |  |  |  | 38.847
126 | 4 |  | 49/1 | DA+0 |  | 06.12.24 | 09.12.24 | Sobha Devi | Complete |  |  |  | 37.504
127 | 5 |  | 73/3 | DA+0 |  | 09.12.24 | 13.12.24 | Chinta devi | Complete |  |  |  | 37.504
128 | 6 |  | 59/0 | DC2+0 |  | 03.12.24 | 16.12.24 | Jirwa Devi | Complete |  |  |  | 66.381
129 | 7 |  | 65/8 | DA+0 |  | 20.12.24 | 27.12.24 | Sanjeev Kumar | Complete |  |  |  | 37.504
| Jan'25 | [12 empty] | 295.434
130 | 1 |  | 65/7 | DA+0 |  | 28.12.24 | 04.01.25 | Sanjeev Kumar | Complete |  |  |  | 37.504
131 | 2 |  | 73/0 | DB2+0 |  | 03.01.25 | 09.01.25 | Chinta devi | Complete |  |  |  | 57.598
132 | 3 |  | 53/8 | DA+3 |  | 04.01.25 | 09.01.25 | Ganesh Sinha | Complete |  |  |  | 38.847
133 | 4 |  | 74/0 | DB2+0 |  | 05.01.25 | 13.01.25 | Sunny Const | Complete |  |  |  | 57.598
134 | 5 |  | 73/4 | DA+0 |  | 10.01.25 | 14.01.25 | Chinta devi | Complete |  |  |  | 37.504
135 | 6 |  | 53/7 | DA+3 |  | 10.01.25 | 18.01.25 | Ganesh Sinha | Complete |  |  |  | 38.847
136 | 7 |  | 73/5 | DA+0 |  | 15.01.25 | 19.01.25 | Chinta devi | Complete |  |  |  | 37.504
137 | 8 |  | 73/7 | DA+0 |  | 14.01.25 | 19.01.25 | Sunny Const | Complete |  |  |  | 37.504
138 | 9 |  | 72/0 | DB2+3 |  | 21.01.25 | 27.01.25 | Chinta Devi | Complete |  |  |  | 60.097
139 | 10 |  | 66/0 | DC+6 |  | 11.01.25 | 29.01.25 | Sanjeev Kumar | Complete |  |  |  | 78.132
140 | 11 |  | 53/6 | DA+6 |  | 19.01.25 | 30.01.25 | Ganesh Sinha | Complete |  |  |  | 45.413
| Feb'25 | [12 empty] | 526.548
141 | 1 |  | 72/1 | DA+3 |  | 28.01.25 | 02.02.25 | Chinta Devi | Complete |  |  |  | 38.847
142 | 2 |  | 65/10 | DA+0 |  | 29.01.25 | 06.02.25 | Sanjeev Kumar | Complete |  |  |  | 37.504
143 | 3 |  | 72/2 | DA+0 |  | 02.02.25 | 06.02.25 | Chinta Devi | Complete |  |  |  | 37.504
144 | 4 |  | 51/0 | DC2+0 |  | 31.01.25 | 07.02.25 | Sunny Const. | Complete |  |  |  | 66.381
145 | 5 |  | 71/8 | DA+3 |  | 07.02.25 | 10.02.25 | Chinta Devi | Complete |  |  |  | 38.847
146 | 6 |  | 52/0 | DC2+0 |  | 08.02.25 | 14.02.25 | Sunny Const. | Complete |  |  |  | 66.381
147 | 7 |  | 49/0 | DD45+0 |  | 05.02.25 | 14.02.25 | Sobha Devi | Complete |  |  |  | 86.129
148 | 8 |  | 71/7 | DA+3 |  | 11.02.25 | 15.02.25 | Chinta Devi | Complete |  |  |  | 38.847
149 | 9 |  | 71/6 | DA+0 |  | 16.02.25 | 19.02.25 | Chinta Devi | Complete |  |  |  | 37.504
150 | 10 |  | 50/5 | DA+9 |  | 15.02.25 | 20.02.25 | Sobha Devi | Complete |  |  |  | 47.184
151 | 11 |  | 71/5 | DA+3 |  | 20.02.25 | 24.02.25 | Chinta Devi | Complete |  |  |  | 38.847
| March'25 | [12 empty] | 533.975
152 | 1 |  | 71/4 | DA+3 |  | 25.02.25 | 01.03.25 | Chinta Devi | Complete |  |  |  | 38.847
153 | 2 |  | 53/5 | DA+3 |  | 01.3.25 | 07.03.25 | Ganesh Sinha | Complete |  |  |  | 38.847
154 | 3 |  | 71/3 | DA+6 |  | 02.03.25 | 07.03.25 | Chinta Devi | Complete |  |  |  | 45.413
155 | 4 |  | 58/0 | DC1+3 |  | 26.02.25 | 10.03.25 | Jirwa Devi | Complete |  |  |  | 69.228
156 | 5 |  | 71/2 | DA+3 |  | 08.03.25 | 12.03.25 | Chinta Devi | Complete |  |  |  | 38.847
157 | 6 |  | 70/3 | DA+3 |  | 08.03.25 | 16.03.25 | Sanjeev kumar | Complete |  |  |  | 38.847
158 | 7 |  | 53/4 | DA+0 |  | 09.03.25 | 17.03.25 | Ganesh Sinha | Complete |  |  |  | 37.504
159 | 8 |  | 71/1 | DA+3 |  | 13.03.25 | 18.03.25 | Chinta Devi | Complete |  |  |  | 38.847
160 | 9 |  | 53/3 | DA+6 |  | 18.03.25 | 25.03.25 | Ganesh Sinha | Complete |  |  |  | 45.413
161 | 10 |  | 71/0 | DB2+3 |  | 19.03.25 | 25.03.25 | Chinta Devi | Complete |  |  |  | 60.097
162 | 11 |  | 70/5 | DA+3 |  | 20.03.25 | 29.03.25 | Sanjeev kumar | Complete |  |  |  | 38.847
163 | 12 |  | 53/2 | DA+0 |  | 26.03.25 | 31.03.25 | Ganesh Sinha | Complete |  |  |  | 37.504 | 451.89
164 | 13 |  | 70/11 | DA+3 |  | 26.03.25 | 31.03.25 | Chinta Devi | Complete |  |  |  | 38.847
April'25
165 | 1 | -163 | 47/9 | DA+3 |  | 31.03.25 | 02.04.25 | Sobha Devi | Complete |  |  |  | 38.847
166 | 2 | -162 | 70/10 | DA+3 |  | 31.03.25 | 04.04.25 | Chinta Devi | Complete |  |  |  | 38.847
167 | 3 | -161 | 47/8 | DA+0 |  | 03.04.25 | 06.03.25 | Sobha Devi | Complete |  |  |  | 37.504
168 | 4 |  | 70/9 | DA+3 |  | 06.04.25 | 09.04.25 | Chinta Devi | Complete |  |  |  | 38.847
169 | 5 |  | 53/1 | DA+9 |  | 02.04.25 |  | Ganesh Sinha | Body wip |  |  |  | 47.184
170 | 6 |  | 68/0 | DD+0 |  | 06.04.25 |  | Sunny Const. | Bottom |  |  |  | 86.129

## Sheet1 (hidden)
S No | Loc No | TOT | Classification
1 | 58/14 | DA+0 | DRY
2 | 51/7 | DA+3 | DFR
3 | 51/5 | DA+0 | DRY
4 | 51/2 | DA+0 | DRY
5 | 53/2 | DA+3 | DFR
6 | 57/7 | DA+3 | DRY
7 | 57/4 | DA+0 | DRY
8 | 55/7 | DA+0 | DRY
9 | 57/5 | DA+3 | DRY
10 | 55/1 | DA+3 | DRY
11 | 55/8 | DA+3 | DRY
12 | 57/2 | DA+0 | DRY
13 | 55/9 | DA+0 | DRY
14 | 57/1 | DA+3 | DRY
15 | 57/3 | DA+0 | DRY
16 | 72/3 | DA+0 | DRY
17 | 43/4 | DA+9 | DRY
18 | 72/4 | DA+0 | DRY
19 | 43/5 | DA+0 | SANDY
20 | 56/9 | DA+3 | DRY
21 | 71/1 | DA+0 | DRY
22 | 56/8 | DA+3 | DRY
23 | 55/10 | DA+3 | DRY
24 | 56/7 | DA+3 | DRY
25 | 55/4 | DA+3 | DFR

## JMC 27.9.23 (hidden)
S no | Locs no | TOT | Classification
1 | 56/3 | DA+0 | DFR | 14.09.23 | 23.09.23 | 25.09.23 | Vaishali Const | JMC required
2 | 44/1 | DA+0 | WFR | 16.09.23 | 20.09.23 | 25.09.23 | Shakti Construction | JMC required
3 | 72/5 | DA+0 | DRY | 19.09.23 | 24.09.23 | 25.09.23 | Mahadev engg. | JMC required
4 | 41/10 | DA+3 | SANDY | 19.09.23 | 22.09.23 | 25.09.23 | Om Const | JMC required
5 | 56/6 | DA+3 | DRY | 21.09.23 | 24.09.23 | 25.09.23 | Manoj Sharma | JMC required
6 | 72/2 | DA+0 | DRY | 15.09.23 | 20.09.23 | 26.09.23 | Mahadev engg. | JMC required
7 | 51/1 | DA+0 | DFR | 10.09.23 |  |  | Amirul Islam | Excavation u/p
8 | 50/3 | DA+0 | DFR | 18.09.23 | 21.09.23 |  | Shri Bhadariyarai Enterprises | Casting
9 | 56/1 | DA+3 | DFR | 21.09.23 |  |  | Vaishali Const | Excavation done
10 | 44/4 | DA+0 | WFR | 19.09.23 | 23.09.23 |  | B S Electrical | Casting
11 | 55/5 | DA+0 | DFR | 22.09.23 |  |  | Amirul Islam | Frustum complete | Manpower | 6
12 | 71/3 | DA+0 | DRY | 21.09.23 |  |  | Mahadev engg. | Block level done
13 | 71/4 | DA+0 | DRY | 23.09.23 |  |  | Mahadev engg. | Excavation complete |  |  | 51
14 | 55/11 | DA+3 | DFR | 22.09.23 |  |  | Nurul Amin | Excavation u/p |  |  | 32
15 | 44/2 | DA+0 | SANDY | 24.9.23 |  |  | Shakti Construction | PCC u/p
16 | 56/4 | DA+3 | DFR | 24.9.23 |  |  | Manoj Sharma | Excavation
17 | 41/11 | DA+3 | SANDY | 23.09.23 |  |  | Om Const | PCC u/p
18 | 56/5 | DA+3 | DRY |  |  |  | Manoj Sharma | Pit marking done
19 | 71/5 | DA+0 |  | 26.09.23 |  |  | Mahadev engg. | Excavation u/p
20 | 46/2 | DA+0 | DRY |  |  |  | Shri Bhadariyarai Enterprises | Excavation u/p
21 | 55/6 | DA+3 |  |  |  |  | Amirul Islam | Excavation u/p

## Jumpering-G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Insulator Hoisting
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Dt. of Jumpering | Name of Sub-Contractor | Ramarks
1 | 1 | 57/6 | DB+0 | 02.06.24 | GPJ Const. | Done
2 | 2 | 57/0 | DB2+0 | 12.07.24 | GPJ Const. | Done
3 | 3 | 56/0 | DB1+0 | 21.07.24 | GPJ Const. | Done
4 | 4 | 55/0 | DC1+0 |  | GPJ Const. | Done
5 | 5 | 52/0 | DB2+0 | 24.10.24 | GPJ Const. | Done
6 | 6 | 53/0 | DC2+3 | 15.09.24 | GPJ Const. | Done
7 | 7 | 51/0 | DB2+0 | 19.10.24 | GPJ Const. | Done
8 | 8 | 58/7 | DB1+0 | 16.12.24 | Kuddus | Done
9 | 9 | 72/7 | DB1+9 | 23.12.24 | MR Power | Done
10 | 10 | 68/0 | DD45+0 | 09.01.25 | Nashruddin | Done
11 | 11 | 67/1 | DB1+9 | 23.01.25 | Nashruddin | Done
12 | 12 | 69/0 | DB1+0 | 05.02.25 | Nashruddin | Done
13 | 13 | 72/0 | DB1+0 | 06.02.25 | MR Power | Done
14 | 14 | 59/0 |  | 17.05.25 | MR Power | Done
15 | 15 | 48/0 |  | 05.06.25 | Indrajeet | Done
16 | 16 | 49/0 |  | 07.06.25 | Indrajeet | Done
17 | 17 | 50/0 |  | 09.06.25 | Indrajeet | Done

## Insulator Hoisting - F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Insulator Hoisting
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Dt. of Start | Dt. of Complete | Name of Sub-Contractor | Ramarks
July'24
1 | 1 | 60/11 | DA+3 | 21.07.24 | 21.07.24 | Kuddus | Complete
2 | 2 | 60/9 | DA+3 | 22.07.24 | 22.07.24 | Kuddus | Complete
3 | 3 | 60/10 | DA+0 | 22.07.24 | 22.07.24 | Kuddus | Complete
4 | 4 | 60/8 | DA+0 | 23.07.24 | 23.07.24 | Kuddus | Complete
5 | 5 | 60/7 | DA+3 | 23.07.24 | 23.07.24 | Kuddus | Complete
6 | 6 | 60/6 | DA+0 | 24.07.24 | 24.07.24 | Kuddus | Complete
7 | 7 | 60/5 | DA+3 | 24.07.24 | 24.07.24 | Kuddus | Complete
8 | 8 | 60/3 | DA+3 | 25.07.24 |  | Kuddus | 5 Phase hoisting done
9 | 9 | 60/4 | DA+3 | 25.07.24 | 25.07.24 | Kuddus | Complete
10 | 10 | 61/0 | DB2+0 | 26.07.24 | 26.07.24 | Kuddus | Complete
11 | 11 | 61/1 | DA+6 | 28.07.24 | 28.07.24 | Kuddus | Complete
12 | 12 | 61/2 | DA+6 | 28.07.24 | 28.07.24 | Kuddus | Complete
13 | 13 | 61/3 | DA+6 | 28.07.24 | 28.07.24 | Kuddus | Complete
14 | 14 | 61/4 | DA+3 | 29.07.24 | 29.07.24 | Kuddus | Complete
15 | 15 | 61/5 | DA+3 | 29.07.24 | 29.07.24 | Kuddus | Complete
16 | 16 | 61/6 | DA+3 | 29.07.24 | 29.07.24 | Kuddus | Complete
17 | 17 | 61/10 | DA+9 | 30.07.24 | 30.07.24 | Kuddus | Complete
18 | 18 | 61/8 | DA+6 | 31.07.24 | 31.07.24 | Kuddus | Complete
19 | 19 | 61/9 | DA+0 | 31.07.24 | 31.07.24 | Kuddus | Complete
Aug'24
20 | 1 | 61/7 | DA+9 | 01.08.24 | 01.08.24 | Kuddus | Complete
21 | 2 | 60/1 | DA+6 | 03.08.24 | 03.08.24 | Kuddus | Complete
22 | 3 | 60/2 | DA+3 | 03.08.24 | 03.08.24 | Kuddus | Complete
Sept'24
23 | 1 | 62/1 | DA+3 | 03.09.24 | 03.09.24 | Kuddus | Complete
24 | 2 | 62/2 | DA+3 | 03.09.24 | 03.09.24 | Kuddus | Complete
25 | 3 | 62/4 | DA+3 | 04.09.24 | 04.09.24 | Kuddus | Complete
26 | 4 | 62/3 | DA+0 | 05.09.24 | 05.09.24 | Kuddus | Complete
27 | 5 | 62/5 | DA+0 | 09.09.24 | 09.09.24 | Kuddus | Complete
28 | 6 | 62/6 | DA+3 | 12.09.24 | 12.09.24 | Kuddus | Complete
29 | 7 | 62/7 | DA+3 | 12.09.24 | 12.09.24 | Kuddus | Complete
30 | 8 | 62/8 | DA+0 | 14.09.24 | 14.09.24 | Kuddus | Complete
31 | 9 | 62/10 | DA+0 | 15.09.24 | 15.09.24 | Kuddus | Complete
32 | 10 | 62/11 | DA+3 | 15.09.24 | 15.09.24 | Kuddus | Complete
33 | 11 | 62/9 |  | 16.09.24 | 16.09.24 | Kuddus | Complete
34 | 1 | 63/4 |  | 05.10.24 | 05.10.24 | Kuddus | Complete
35 | 2 | 63/7 |  | 09.10.24 | 09.10.24 | Kuddus | Complete

## Insulator Hoisting - G (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Insulator Hoisting
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Dt. of Start | Dt. of Complete | Name of Sub-Contractor | Ramarks
Jan'24
1 | 1 | 57/5 | DA+3 | 05.01.24 | 05.01.24 | Mainul Hoque | Complete
2 | 2 | 57/4 | DA+0 | 06.01.24 | 06.01.24 | Mainul Hoque | Complete
3 | 3 | 57/3 | DA+0 | 07.01.24 | 07.01.24 | Mainul Hoque | Complete
4 | 4 | 57/2 | DA+0 | 07.01.24 | 07.01.24 | Mainul Hoque | Complete
April'24
5 | 1 | 57/7 | DA+3 | 08.04.24 | 08.04.24 | GPJ Const. | Complete
6 | 2 | 57/9 | DA+0 | 09.04.24 | 09.04.24 | GPJ Const. | Complete
7 | 3 | 57/11 | DA+0 | 09.04.24 | 09.04.24 | GPJ Const. | Complete
8 | 4 | 57/12 | DA+3 | 10.04.24 | 10.04.24 | GPJ Const. | Complete
9 | 5 | 57/13 | DA+0 | 10.04.24 | 10.04.24 | GPJ Const. | Complete
10 | 6 | 57/1 | DA+3 | 11.04.24 | 11.04.24 | GPJ Const. | Complete
11 | 7 | 57/10 | DA+0 | 11.04.24 | 11.04.24 | GPJ Const. | Complete
12 | 8 | 56/8 | DA+3 | 12.04.24 | 12.04.24 | GPJ Const. | Complete
13 | 9 | 56/9 | DA+3 | 12.04.24 | 12.04.24 | GPJ Const. | Complete
14 | 10 | 56/6 | DA+3 | 13.04.24 | 13.04.24 | GPJ Const. | Complete
15 | 11 | 56/7 | DA+3 | 13.04.24 | 13.04.24 | GPJ Const. | Complete
16 | 12 | 56/4 | DA+3 | 14.04.24 | 14.04.24 | GPJ Const. | Complete
17 | 13 | 56/5 | DA+0 | 14.04.24 | 14.04.24 | GPJ Const. | Complete
18 | 14 | 56/3 | DA+0 | 15.04.24 | 15.04.24 | GPJ Const. | Complete
19 | 15 | 56/2 | DA+3 | 15.04.24 | 15.04.24 | GPJ Const. | Complete
20 | 16 | 55/10 | DA+3 | 16.04.24 | 16.04.24 | GPJ Const. | Complete
21 | 17 | 55/11 | DA+3 | 16.04.24 | 16.04.24 | GPJ Const. | Complete
22 | 18 | 55/9 | DA+3 | 17.04.24 | 17.04.24 | GPJ Const. | Complete
23 | 19 | 55/7 | DA+0 | 17.04.24 | 17.04.24 | GPJ Const. | Complete
24 | 20 | 55/6 | DA+3 | 17.04.24 | 17.04.24 | GPJ Const. | Complete
25 | 21 | 55/1 | DA+3 | 18.04.24 | 18.04.24 | GPJ Const. | Complete
26 | 22 | 55/2 | DA+3 | 18.04.24 | 18.04.24 | GPJ Const. | Complete
27 | 23 | 55/3 | DA+0 | 18.04.24 | 18.04.24 | GPJ Const. | Complete
28 | 24 | 55/5 | DA+0 | 18.04.24 | 18.04.24 | GPJ Const. | Complete
29 | 25 | 55/8 | DA+3 | 19.04.24 | 19.04.24 | GPJ Const. | Complete
30 | 26 | 53/2 | DA+3 | 20.04.24 | 20.04.24 | GPJ Const. | Complete
31 | 27 | 53/3 | DA+3 | 20.04.24 | 20.04.24 | GPJ Const. | Complete
32 | 28 | 53/4 | DA+3 | 20.04.24 | 20.04.24 | GPJ Const. | Complete
33 | 29 | 57/6 | DB+0 | 21.04.24 | 21.04.24 | GPJ Const. | Complete
34 | 30 | 57/0 | DB+0 | 22.04.24 | 22.04.24 | GPJ Const. | Complete
35 | 31 | 51/8 | DA+3 | 23.04.24 | 23.04.24 | GPJ Const. | Complete
36 | 32 | 51/9 | DA+3 | 23.04.24 | 23.04.24 | GPJ Const. | Complete
37 | 33 | 56/1 | DA+3 | 24.04.24 | 24.04.24 | GPJ Const. | Complete
38 | 34 | 56/0 | DB+0 | 26.04.24 | 26.04.24 | GPJ Const. | Complete
39 | 35 | 51/6 | DA+0 | 27.04.24 | 27.04.24 | GPJ Const. | Complete
40 | 36 | 51/7 | DA+3 | 27.04.24 | 27.04.24 | GPJ Const. | Complete
41` | 37 | 57/8 | DA+3 | 28.04.24 | 28.04.24 | GPJ Const. | Complete
May'24
42 | 1 | 58/0 | DC2+0 | 04.05.24 | 19.09.24 | GPJ Const. | Complete
June'24
43 | 1 | 55/0 | DC1+0 | 02.06.24 | 02.06.24 | GPJ Const. | Complete | 07.09.24
July'24
44 | 1 | 53/1 | DA+0 | 08.07.24 | 08.07.24 | GPJ Const. | Complete
45 | 2 | 53/0 | DC2+3 | 10.07.24 | 31.07.24 | GPJ Const. | Complete
46 | 3 | 52/1 | DA+0 | 29.07.24 | 29.07.24 | GPJ Const. | Complete
47 | 4 | 52/2 | DA+3 | 29.07.24 | 29.07.24 | GPJ Const. | Complete
48 | 5 | 52/3 | DA+0 | 30.07.24 | 30.07.24 | GPJ Const. | Complete
Aug'24
49 | 1 | 52/0 | DB2+0 | 14.08.24 | 14.08.24 | GPJ Const. | Complete
50 | 2 | 51/10 | DA+3 | 14.08.24 | 14.08.24 | GPJ Const. | Complete
51 | 3 | 51/1 | DA+0 | 23.08.24 | 23.08.24 | GPJ Const. | Complete
52 | 4 | 51/3 | DA+0 | 24.08.24 | 24.08.24 | GPJ Const. | Complete
53 | 5 | 51/4 | DA+3 | 24.08.24 | 24.08.24 | GPJ Const. | Complete
54 | 6 | 51/5 | DA+0 | 24.08.24 | 24.08.24 | GPJ Const. | Complete
55 | 7 | 51/0 | DB2+0 | 25.08.24 | 25.08.24 | GPJ Const. | Complete
56 | 8 | 51/2 | DA+0 | 25.08.24 | 25.08.24 | GPJ Const. | Complete
Sept'24
57 | 1 | 50/4 | DA+3 | 15.09.24 | 15.09.24 | GPJ Const. | Complete
58 | 2 | 50/3 | DA+0 | 16.09.24 | 16.09.24 | GPJ Const. | Complete
59 | 3 | 58/1 | DA+0 | 19.09.24 | 19.09.24 | GPJ Const. | Complete
60 | 4 | 50/2 | DA+0 | 21.09.24 | 21.09.24 | GPJ Const. | Complete
61 | 5 | 50/0 | DC2+3 | 07.10.24 | 07.10.24 | GPJ Const. | Complete

## Jumpering-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
Insulator Hoisting
Cum Sl. No. | Month Sl. No. | Location No. | Tower Type | Dt. of Jumpering | Name of Sub-Contractor | Ramarks
1 | 1 | 61/0 |  | 23.10.24 | Kuddua Ali
2 | 2 | 62/0 |  | 11.11.24 | Kuddua Ali

## Stringing - PKG-F (hidden)
KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
STRINGING
Stringing - PKG-F
S. No | Section |  |  |  | Paying Out |  |  | Final Sag |  |  | Name of Gang | Remarks
| From | To | Length | Cum | Start Date | Finish Date | Month | Start Date | Finish Date | Month
1 | 60/0 | 61/0 | 4.877 | 4.877 | 21.08.24 | 28.08.24 | 2024-08-24 | 09.09.24 | 16.09.24 | 2024-09-24 | Kuddus ali | Final sag completed
2 | 61/0 | 62/0 | 4.568 | 9.445 | 06.09.24 | 16.09.24 | 2024-09-24 | 26.9.24 | 03.10.24 | 2024-10-24 | Kuddus ali | Final sag completed
3 | 62/0 | 63/0 | 4.863 | 14.308 | 23.09.24 | 02.10.24 | 2024-10-24 | 17.10.24 | 22.10.24 | 2024-10-24 | Kuddus ali | Final sag completed
4 | 63/0 | 64/0 | 3.711 | 18.019 | 14.10.24 | 21.10.24 | 2024-10-24 | 31.10.24 | 06.11.24 | 2024-11-24 | Kuddus ali | Final sag completed
5 | 64/0 | 65/0 | 4.918 | 22.937 | 30.10.24 | 05.11.24 | 2024-11-24 | 13.11.24 | 16.11.24 | 2024-11-24 | Kuddus ali | Final sag completed
6 | 59/8 | 60/0 | 3.778 | 26.715 | 22.12.24 | 27.12.24 | 2024-12-24 | 04.01.25 | 09.01.25 | 2025-01-25 | Gopal Associate | Final sag completed
7 | 59/0 | 59/8 | 3.337 | 30.052 | 02.01.25 | 08.01.25 | 2025-01-25 | 12.01.25 | 15.01.25 | 2025-01-25 | Gopal Associate | Final sag completed
8 | 65/0 | 66/0 | 4.736 | 34.788 | 3.02.25 | 22.03.25 | 2025-03-25 | 10.03.25 | 23.03.25 | 2025-03-25 | MR Power | Final sag completed
9 | 50/0 | 51/0 | 4.444 | 39.232 | 12.03.25 | 23.03.25 | 2025-03-25 | 17.03.25 | 24.03.25 | 2025-03-25 | Gopal Associate | Final sag completed & 50/6 Clipping done | 50/4 &50/6 Hoisting done-23.02.25 | 50/8 &50/9, 50/10 Hoisting done | 51/1 & 51/2 Hoisting done
10 | 51/0 | 52/0 | 1.049 | 40.281 | 02.04.25 | 08.04.25 | 2025-04-25 | 04.04.25 | 09.04.25 | 2025-04-25 | Gopal Associate | Final sag completed | 35
11 | 49/0 | 50/0 | 3.227 | 43.508 | 06.02.25 | 19.02.25 | 2025-03-25 |  |  |  | Gopal Associate | Rough sag done & Earth wire payour rough sag done
12 | 48/0 | 49/0 | 0.832 | 44.34 |  |  | 2025-03-25 |  |  |  | Gopal Associate

## Stringing Productivity (hidden)
TB401 Stringing Status | [11 empty] | Dated 06-05-2025
Sr. No. | Sub-Contractor Name | Completed in April |  |  | Output for the day |  |  | Output Upto Yesterdays(Kms) in May | Cumulative Output till today(Kms) | Start Date | Comp Date | Status | Total Manpower
|  | From | To | Span | From | To | Span Length
1 | MR Power |  |  |  | 59/0 | 60/0 | 2.581 |  |  | 04.05.25 |  | Final sag done
2 | Indrajeet |  |  |  | 42/0 | 43/0 | 0.489 |  |  | 11.05.25 |  | Final sag done
3 | Indrajeet |  |  |  | 49/0 | 50/0 | 0.241 |  |  | 17.05.25 |  | Final sag done
4 | Indrajeet |  |  |  | 48/0 | 49/0 | 1.162 |  |  | 21.05.25 |  | Final sag done
5 | Indrajeet |  |  |  | 43/0 | 44/0 | 2.856 |  |  |  |  | Rought Sag Done
6 | Indrajeet |  |  |  | 47/0 | 48/0 | 1.274 |  |  |  |  | Final sag arrangement wip
7 | Indrajeet |  |  |  | 37/2 | 38/0 | 2.71 |  |  |  |  | 37/2 Hoisting done & pilot payout wip
8
|  | 0 | 0 |  | Total |  | 3.07 | 0 | 0 |  |  |  | 0

## OPGW PKG-F (hidden)
EXECUTING AGENCY : M/s. KEC INTERNATIONAL LIMITED
LILO of 765 Kv DV Fatehgarh 3 Beawar TL
OPGW Progress details(PKG-F)
Sr. No | Section |  | Section length in Kms | OPGW Drum Length (In KMs) | Start date | End date | Splicing | Jointing Details | Agency | OTDR reading status | Splicing done by | Remarks
1 | 59/0 | 59/8 | 3.337 |  | 10.02.25 | 11.02.25 | 05.03.25 |  | Congent tech |  | Revant Sharma | Final Sag Complete
2 | 59/8 | 60/0 | 3.778 |  | 12.02.25 | 13.02.25 | 26.02.25 |  | Congent tech |  | Revant Sharma | Final Sag Complete
3 | 60/0 | 61/0 | 4.877 |  | 15.02.25 | 16.02.25 |  |  | Congent tech |  |  | Final Sag Complete
4 | 61/0 | 62/0 | 4.568 |  | 19.02.25 | 19.02.25 | 27.02.25 |  | Congent tech |  | Revant Sharma | Final Sag Complete
5 | 62/0 | 63/0 | 4.863 |  | 23.02.25 | 24.02.25 |  |  | Congent tech |  |  | Final Sag Complete
6 | 63/0 | 64/0 | 3.711 |  | 01.03.25 | 02.03.25 |  |  | Congent tech |  |  | Final Sag Complete
7 | 64/0 | 65/0 | 4.918 |  | 03.03.25 | 03.03.25 |  |  | Congent tech |  |  | Final Sag Complete
Total Length in Kms |  |  | 30.052 | 0
Total Length in Km |  |  | 30.052 | 0
31.869

## Crossing (hidden)
CROSSING DETAILS FOR 765 KV DC FATEHGARH 3 - BEAWAR T/L (Part-G & Part-F)
Sl No | Crossing Name | PART - G | [6 empty] | PART - F
|  | Section |  | Owner Name | Date of Submission | Date of Site Inspection | Proposal Status | Remarks | Section |  | Owner Name | Date of Submission | Date of Site Inspection | Proposal Status | Remarks
|  | From | To | [5 empty] | From | To
A | Power Line
1 | 400 KV D/C Rajwest - Jodhpur Line | AP 36 | AP 37 | RRVPNL |  |  | Hard copy submitted on - 08/03/24. |  | AP 46 | AP 47 | RRVPNL |  | 2 days |  |  | 5,5,5,5
2 | U/C LILO of 400 KV D/C Rajwest - Jodhpur Line at Newai S/S | AP 45 | AP 46 | RRVPNL | 2023-12-25 |  | Hard copy submitted on - 10/01/24. |  | AP 56 | AP 57 | RRVPNL |  | 1week
3 | 220 KV S/C GSS Boranada - Balotra Line | AP 60 | AP 61 | RRVPNL | 2023-11-13 |  | Approved on dated 18.07.24 |  | AP 66 | AP 67 | RRVPNL | 2024-02-13 |  | Approved on dated 18.07.24
B | Railway
1 | Electrified BG Double Track Line (Jodhpur - Barmer) | AP 70 | AP 71 | NWR |  |  | Hard copy submitted on - 21/02/24.
C | NH/SH
1 | SH - 28 (Bikaner - Barmer) | AP 44 | 44/1 | PWD |  |  | NR |  | AP 55 | 55/1 | PWD
2 | Bharatmala Expressway (Amritsar - Kandla) | AP 49 | AP 50 | NHAI | 2023-11-13 |  | Approved on dated - 01.06.24 |  | AP 58 | AP 59 | NHAI | 2024-01-21 |  | Approved on dated - 01.06.24
3 | SH - 66 (Kalyanpur - Balesar) | 51/7 | 51/8 | PWD |  |  | NR |  | 59/14 | 59/15 | PWD
4 | NH 25 (Jodhpur - Barmer) | AP 62 | AP 63 | NHAI | 2023-12-06 |  | Approved on dated - 24.06.24 |  | AP 68 | AP 69 | NHAI | 2024-02-13 |  | Approved on dated - 24.06.24
5 | SH - 68 (Shikarpura - Luni) | 72/1 | 72/2 | PWD |  |  | NR
D | River
1 | Luni River | 72/7 | AP 73 |  |  |  | NR | NR
E | Pipe Line
1 | Under Ground Oil Pipe Line | 59/2 | 59/3 | HPML |  |  |  | Format awaited from SPTL | 65/7 | 65/8 | HPML
2 | Under Ground Oil Pipe Line (Mundra - Bhatinda) | 72/3 | 72/4 | IOCL

## Visual Chart (Pkg -F.) (hidden)
PKG-F, Section-II
Executing Agency |  | KEC International Limited
Project |  | Fatehgarh-3-Beawar 765kV D/C (2nd) Transmission Line Section 1 & 2 (PKG-F Section -II)
LEGEND: | [16 empty] | Summary | [7 empty] | 2026-03-16
[13 empty] | Tree Felling Done. Front Clear For Stringing |  |  |  | SR. NO. |  | ACTIVITY |  |  | UNIT | As per Tower Schedule |  | TOTAL COMPLETED |  | BALANCE |  | Earthng | Foundation |  |  | Erection
|  |  |  | Stringing WIP |  |  | STRINGING COMPLETED
[6 empty] | Loc No | P: Prvate Loc
[12 empty] | EREC. U/P | [17 empty] | Total | Fdn Complete | Balance | Total | Complete | Balance
|  |  | EREC. COMP. |  |  |  | SPAN |  | SPAN |  |  | PIT EXCAV. U/P |  |  |  |  | 1 |  | Foundation |  |  | Nos. | 223 |  | 221 |  | 2
FDN. COMP.
|  | Tack Welding | [9 empty] | BENCHING U/P |  |  |  |  | 2 |  | Earthing |  |  | Nos. | 223 |  | 219 |  | 4
|  |  | LE | Leg Extension(A,B,C,D) |  |  | Earthing Comp. |  | PIT EXCAV. COMP. | [7 empty] | 3 |  | Erection |  |  | Nos. | 223 |  | 167 |  | 56
|  |  | RC | Raise Chimney (A,B,C,D)
[17 empty] | 4 |  | Tackwelding |  |  | Nos. | 223 |  | 139 |  | 84
[17 empty] | 5 |  | Stringing (PayingOut) |  |  | Km. | 88.4 |  | 26.715 |  | 61.685
[17 empty] | 6 |  | Stringing (Final Sag) |  |  | Km. | 88.4 |  | 39.232 |  | 49.168
|  | NH/SH Xing |  | RAILWAY |  | Powerline Xing |  | 11/33 KV X-ING |  |  | RIVER X-ING |  |  | METAL ROADS |  |  | 7 |  | OPGW |  |  | Km. | 88.4 |  |  |  | 88.4
[34 empty] | 0 | 12
| 44/0 |  | 44/1 |  | 44/2 |  | 44/3 |  | 44/4 |  | 44/5 |  | 44/6 |  | 44/7 |  | 44/8 |  | 44/9 |  | 44/10 |  | 44/11 |  | 45/0 |  | 45/1 | [5 empty] | 12
| 16.02.25 | 384.3 | 06.01.25 | 410 | 07.01.25 | 420.3 | 28.01.25 | 488.9 | 13.01.25 | 311.5 | 19.01.25 | 360.3 | 21.01.25 | 475 | 25.01.25 | 359.8 | 31.01.25 | 408 | 20.01.25 | 427 | 13.01.25 | 352 | 09.01.25 | 260.5 | 09.01.25 | 319 | 09.02.25 | 4.9766
| Sandy |  | Sandy |  | SANDY |  | SANDY |  | Sandy |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | Sandy |  | SANDY |  | SANDY |  | SANDY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DB1+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+9 |  | DB1+3 |  | DA+9 |  | DCT1+0 |  | DA+9 |  | DB1+9 |  | DA+0 |  | DC2+0 |  | DA+9 |  |  | 14
| 0,1,1,0 |  | 0,0,1,0 |  |  |  | 2,0,0,1 |  | 4,3,3,3 |  | 1,3,0,0 |  | 1,0,0,1 |  |  |  | 1,2,0,1 |  | 4,0,2,6 |  | 0,1,0,0 |  | 0,1,0,0 |  | 0,1,0,0 |  | 0,0,6,6
[19 empty] | 6.3.25 |  | 2.4.25 |  | 22.11.24 |  | 19.10.24 |  | 25.09.24 | [6 empty] | 5 | 7
| 46/0 |  | 47/0 |  | 47/1 |  | 47/2 |  | 47/3 |  | 47/4 |  | 47/5 |  | 47/6 |  | 47/7 |  | 47/8 |  | 47/9 |  | 47/10 |  | 48/0 |  | 48/1 | [5 empty] | 12
381 | 09.4.25 | 197.7 |  | 413.2 | 01.02.25 | 395.9 | 26.5.24 | 417.4 | 08.6.24 | 358.4 | 23.01.25 | 461 | 31.5.24 | 377.3 | 18.5.24 | 431.5 | 31.3.24 | 398.8 | 29.3.24 | 405.9 | 23.3.24 | 433.7 | 20.3.24 | 386.2 | 7.4.24 | 428.9 | 15.4.24 | 5.4869
| SANDY |  |  |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  |  |  | 13
[5 empty] | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 12
| DD60+25 |  | DD60+25 |  | DA+3 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC2+0 |  | DA+9 |  |  | 14
| 0,6,6,2 |  | 5,5,5,5 |  | 2,0,2,5 |  |  |  | 1,2,-,- |  |  |  | -,1,-,- | [5 empty] | 1,-,-,-
| 14.2.25 |  | 9.12.24 |  | 30.11.24 |  | 5.12.24 |  | 22.11.24 |  | 27.11.24 |  | 18.11.24 |  | 14.11.24 |  | 07.10.24 |  | 13.10.24 |  | 24.10.24 |  | 18.10.24 |  | 30.10.24 |  | 20.02.25 | [6 empty] | 14 | -2
| 49/0 |  | 49/1 |  | 49/2 |  | 49/3 |  | 49/4 |  | 49/5 |  | 49/6 |  | 49/7 |  | 50/0 |  | 50/1 |  | 50/2 |  | 50/3 |  | 50/4 |  | 50/5 | [5 empty] | 12
402.9 | 03.05.24 | 379.1 | 20.4.24 | 386.6 | 18.2.24 | 390 | 15.3.24 | 421.7 | 19.3.24 | 396.6 | 20.3.24 | 412.8 | 17.3.24 | 340.2 | 20.10.24 | 500.2 | 19.7.24 | 469.1 | 18.5.24 | 367.1 | 31.5.24 | 470.4 | 10.9.24 | 354.8 | 28.5.24 | 442.1 | 23.01.25 | 5.7336
| SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DD45+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+9 |  |  | 14
RC | [14 empty] | -,3,2,2 |  | -,-,-,1 |  | 1,-,-,- |  | 2,2,2,2 |  | -,-,1,- |  | 3,3,4,3 |  | 4,3,4,3
| 11.10.24 |  | 04.11.24 |  | 16.10.24 |  | 9.9.24 |  | 19.9.124 |  | 07.02.25 |  | 26.9.24 |  | 4.10.24 |  | 14.2.25 | [9 empty] | 19.9.124 | [6 empty] | 10 | 2
| 50/6 |  | 50/7 |  | 50/8 |  | 50/9 |  | 50/10 |  | 51/0 |  | 51/1 |  | 51/2 |  | 52/0 |  | 52/1 |  | 52/2 |  | 52/3 |  | 52/4 |  | 52/5 | [5 empty] | 12
364.4 | 28.8.24 | 470.8 | 10.5.24 | 345 | 19.4.24 | 364 | 01.4.24 | 394.6 | 08.4.24 | 401.4 | 10.6.24 | 356.6 | 13.4.24 | 307.1 | 31.5.24 | 385 | 18.1.25 | 402 | 20.12.24 | 402.6 | 25.12.24 | 437 | 25.05.24 | 393.8 | 30.12.24 | 447 | 02.02.24 | 5.4713
| SANDY |  | SANDY |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | SANDY |  | SANDY |  | SANDY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+9 |  | DA+0 |  | DA+9 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+6 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+9 |  |  | 14
| 3,4,3,3 |  | -,-,-,1 |  |  |  | -,-,1,- |  | -,-,1,- |  |  |  | -,-,1,- |  |  |  | -,-3,3 |  | -,4,-,- |  | -,-,-,3 |  | 4,3,3,3 |  | 2,2,-,- |  | -,-,-,1
| 30.09.24 |  | 07.10.24 |  | 19.10.24 |  | 5.12.24 |  | 25.11.24 | [5 empty] | 31.3.25 |  | 25.3.25 |  | 17.3.25 |  | 7.3.25 |  | 30.01.25 |  | 18.1.25 |  | 09.01.25 | [6 empty] | 12 | 0
| 52/6 |  | 52/7 |  | 52/8 |  | 52/9 |  | 52/10 |  | 53/0 |  | 53/1 |  | 53/2 |  | 53/3 |  | 53/4 |  | 53/5 |  | 53/6 |  | 53/7 |  | 53/8 | [5 empty] | 12 |  |  | G | 33
[36 empty] | F | 23
373 | 6.2.24 | 406.8 | 12.2.24 | 433 | 12.2.24 | 399.7 | 19.2.24 | 384.1 | 17.02.24 | 455.9 | 13.01.25 | 433.2 | 08.01.25 | 407.4 | 29.12.24 | 394.5 | 15.01.25 | 410.1 | 18.01.25 | 428.1 | 22.02.24 | 406.6 | 05.09.24 | 411.3 | 15.06.24 | 427.8 | 29.08.24 | 5.7715
| SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  | Sandy |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+6 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+9 |  | DB2+9 |  | DA+9 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+3 |  |  | 14
|  |  | -,3,1,- | [5 empty] | 1,2,1,1 |  | 4,4,4,4 |  | 4,4,4,4 |  | -,-,-,2 |  | -,4,1,- |  | -,2,1,- |  |  |  | 1,1,3,1
[19 empty] | 31.05.24 |  | 19.06.24 |  | 12.11.24 |  | 1.11.24 | [8 empty] | 4 | 8
| 54/0 |  | 54/1 |  | 54/2 |  | 54/3 |  | 54/4 |  | 54/5 |  | 55/0 |  | 55/1 |  | 55/2 |  | 55/3 |  | 55/4 |  | 55/5 |  | 55/6 |  | 55/7 | [5 empty] | 12
371.3 | 21.11.24 | 365.1 | 09.9.24 | 381 | 14.9.24 | 417 | 06.01.25 | 423.3 | 09.01.25 | 401 | 10.02.25 | 424 | 15.02.25 | 404.9 | 21.01.25 | 343.1 | 21.01.25 | 357.7 | 15.1.24 | 365.2 | 17.1.24 | 350.1 | 25.1.24 | 357.7 | 25.1.24 | 337.8 | 29.1.24 | 5.2992
| Sandy |  | Sandy |  | Sandy |  | Sandy |  | SANDY |  | SANDY |  | SANDY |  | WFR |  | WFR |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  | SANDY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DB1+6 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+9 |  | DA+9 |  | DB1+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  |  | 14
|  |  | 1,1,-,- |  |  |  | -,2,-,- |  | 1,2,-,- |  | 1,3,3,1 |  | -,1,1,- | [7 empty] | -,-,-,1 |  | -,-,1,3 |  | -,-,1,2 |  | -,-,1,-
[11 empty] | 11.6.24 |  | 27.06.24 |  | 26.8.24 |  | 20.8.24 |  | 1.10.24 |  | 10.3.25 |  | 17.12.24 |  | 3.12.24 |  | 24.11.24 | [6 empty] | 9 | 3
| 55/8 |  | 56/0 |  | 57/0 |  | 57/1 |  | 57/2 |  | 57/3 |  | 57/4 |  | 57/5 |  | 57/6 |  | 57/7 |  | 58/0 |  | 59/0 |  | 59/1 |  | 59/2 | [5 empty] | 12
422.8 | 30.01.25 | 398.9 |  | 179.9 | 31.03.25 | 404.3 | 27.01.25 | 432.3 | 11.01.24 | 405.4 | 08.01.24 | 418.2 | 14.1.24 | 416.8 | 17.1.24 | 395 | 21.1.24 | 401.8 | 10.8.24 | 433.9 | 29.7.24 | 238.9 | 04.10.24 | 411.33 | 25.9.24 | 418.2 | 23.8.24 | 5.3777
| SANDY |  |  |  | SANDY |  | SANDY |  | DRY |  | DRY |  | DRY |  | SANDY |  | SANDY |  | DFR |  | DFR |  | DFR |  | DRY |  | DFR |  |  |  | 13
| Done | [5 empty] | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 12
| DA+6 |  | DD60+25 |  | DD60+25 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC1+3 |  | DC2+0 |  | DA+3 |  | DA+3 |  |  | 14
| -,-,-,- |  | 3,3,0,2 |  | -,-,-,- | [9 empty] | -,-,-,1 |  | -,1,-,- | [7 empty] | -,-,-,1
| 2.11.24 |  | 09.11.24 |  | 11.2.24 |  | 18.02.24 |  | 24.02.24 |  | 29.2.24 |  | 28.02.24 |  | 24.02.24 |  | 26.10.24 |  | 20.02.24 |  | 07.2.24 |  | 13.2.24 |  | 30.05.24 |  | 11.3.24 | [6 empty] | 14 | -2
| 59/3 |  | 59/4 |  | 59/5 |  | 59/6 |  | 59/7 |  | 59/8 |  | 59/9 |  | 59/10 |  | 59/11 |  | 59/12 |  | 59/13 |  | 59/14 |  | 59/15 |  | 59/16 | [5 empty] | 12
412.3 | 05.01.24 | 420.97 | 19.10.24 | 419.66 | 31.12.23 | 419.11 | 29.12.23 | 408.81 | 30.12.23 | 426.93 | 28.12.23 | 434.73 | 26.12.23 | 400.83 | 24.12.23 | 436.3 | 28.09.24 | 393.11 | 05.01.24 | 447.36 | 21.12.23 | 391.11 | 19.12.23 | 448.59 | 7.2.24 | 388 | 12.02.24 | 5.8478
| DFR |  | DFR |  | DFR |  | DFR |  | DRY |  | DRY |  | DRY |  | DRY |  | DFR |  | DFR |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+9 |  |  | 14
| -,-,-,1 | [15 empty] | -,-,2,-
| 18.5.24 |  | 25.4.24 |  | 7.4.24 |  | 31.03.24 |  | 23.3.24 |  | 17.3.24 |  | 29.2.24 |  | 04.02.24 |  | 15.2.24 |  | 5.5.24 |  | 21.2.24 |  | 26.2.24 |  | 11.4.24 |  | 29.4.24 | [6 empty] | 14 | -2
| 60/0 |  | 60/1 |  | 60/2 |  | 60/3 |  | 60/4 |  | 60/5 |  | 60/6 |  | 60/7 |  | 60/8 |  | 60/9 |  | 60/10 |  | 60/11 |  | 61/0 |  | 61/1 | [5 empty] | 12
437.96 | 19.3.24 | 413.81 | 16.2.24 | 424.2 | 24.2.24 | 414.52 | 28.2.24 | 425.58 | 29.2.24 | 412.27 | 09.01.24 | 374.13 | 11.01.24 | 410.05 | 05.01.24 | 400.36 | 29.12.23 | 409.17 | 27.12.23 | 400.97 | 15.1.24 | 394.54 | 24.1.24 | 397.86 | 19..01.24 | 405.66 | 28.1.24 | 5.7211
| DRY |  | DRY |  | DFR |  | DFR |  | DFR |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DFR |  | DRY |  | DRY |  | DFR |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DC1+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB2+0 |  | DA+6 |  |  | 14
RC |  |  |  |  | 2,2,-,-
| 22.04.24 |  | 11.5.24 |  | 16.5.24 |  | 23.05.24 |  | 22.3.24 |  | 28.3.24 |  | 30.05.24 |  | 23.05.24 |  | 19.05.24 |  | 8.9.24 |  | 12.07.24 |  | 03.02.24 |  | 28.2.24 |  | 26.02.24 | [6 empty] | 14 | -2
| 61/2 |  | 61/3 |  | 61/4 |  | 61/5 |  | 61/6 |  | 61/7 |  | 61/8 |  | 61/9 |  | 61/10 |  | 62/0 |  | 62/1 |  | 62/2 |  | 62/3 |  | 62/4 | [5 empty] | 12
433.16 | 31.1.24 | 400.92 | 14.12.23 | 427.01 | 14.3.24 | 413.93 | 09.02.24 | 426.39 | 11.2.24 | 411.45 | 13.2.24 | 376.25 | 20.02.24 | 433.37 | 16.2.24 | 405.62 | 4.3.24 | 434.25 | 10.3.24 | 418 | 21.2.24 | 386 | 05.01.24 | 400 | 31.12.23 | 401 | 28.12.23 | 5.7674
| DFR |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+6 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+6 |  | DA+0 |  | DA+9 |  | DB2+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  |  | 14
RC | [10 empty] | -,-,-,1 |  | 1,2,1,- | [7 empty] | -,-,1,2 |  | -,1,-,-
| 22.02.24 |  | 26.07.24 |  | 7.3.24 |  | 11.3.24 |  | 15.3.24 |  | 18.03.24 |  | 03.5.24 |  | 12.5.24 |  | 27.4.24 |  | 22.04.24 |  | 17.04.24 |  | 13.04.24 |  | 7.4.24 |  | 10.2.24 | [6 empty] | 14 | -2
| 62/5 |  | 62/6 |  | 62/7 |  | 62/8 |  | 62/9 |  | 62/10 |  | 62/11 |  | 63/0 |  | 63/1 |  | 63/2 |  | 63/3 |  | 63/4 |  | 63/5 |  | 63/6 | [5 empty] | 12
403 | 25.12.23 | 404 | 19.12.23 | 423 | 21.12.23 | 409 | 16.1.24 | 409 | 19..01.24 | 411 | 13.1.24 | 413 | 10.01.24 | 386.11 | 12.2.24 | 400 | 23.1.24 | 416 | 25.1.24 | 411 | 30.1.24 | 399 | 02.02.24 | 413 | 7.2.24 | 426 | 29.12.23 | 5.7231
| DRY |  | DRY |  | DRY |  | DFR |  | DFR |  | DFR |  | DRY |  | DRY |  | DFR |  | DFR |  | DFR |  | DRY |  | DFR |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  |  | 14
RC
| 15.02.27 |  | 20.02.24 |  | 5.5.24 |  | 24.2.24 |  | 21.04.24 |  | 26.4.24 |  | 29.2.24 |  | 04.3.24 |  | 26.3.24 |  | 27.03.24 |  | 03.04.24 |  | 8.4.24 |  | 20.04.24 |  | 24.10.24 | [6 empty] | 14 | -2
| 63/7 |  | 63/8 |  | 64/0 |  | 64/1 |  | 64/2 |  | 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | 64/8 |  | 64/9 |  | 64/10 |  | 64/11 | [5 empty] | 12
413 | 25.1.24 | 425 | 24.12.23 | 408.34 | 08.01.24 | 375.08 | 18.1.24 | 409 | 21.1.24 | 410.74 | 30.1.24 | 408.23 | 14.1.24 | 426.15 | 18.1.24 | 407.72 | 7.2.24 | 401.62 | 02.02.24 | 425.51 | 31.1.24 | 414.35 | 21.1.24 | 410.63 | 10.2.24 | 428.42 | 24.2.24 | 5.7638
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  |  | 14
RC
| 27.4.24 |  | 3.5.24 |  | 06.03.24 |  | 16.3.24 |  | 11.3.24 |  | 20.3.24 |  | 26.3.24 |  | 04.01.25 |  | 27.12.24 |  | 31.03.24 |  | 06.02.25 |  | 4.4.24 |  | 29.01.25 | [8 empty] | 13 | -1
| 65/0 |  | 65/1 |  | 65/2 |  | 65/3 |  | 65/4 |  | 65/5 |  | 65/6 |  | 65/7 |  | 65/8 |  | 65/9 |  | 65/10 |  | 65/11 |  | 66/0 |  | 67/0 | [5 empty] | 12
400.56 | 29.2.24 | 395.38 | 5.3.24 | 393.74 | 10.01.24 | 403.69 | 15.1.24 | 402.93 | 24.1.24 | 376.38 | 21.1.24 | 389.19 | 18.1.24 | 397.58 | 30.11.24 | 394.27 | 28.11.24 | 388.95 | 13.1.24 | 379.1 | 27.01.25 | 387.63 | 10.01.24 | 426.93 | 27.01.24 | 207.8 | 05.10.24 | 5.3441
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DB1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC2+6 |  | DC1+9 |  |  | 14
| 10.04.2024 |  | 15.04.24 | [13 empty] | 16.3.25 |  |  |  | 29.3.25 | [12 empty] | 4 | 8
| 67/1 |  | 67/2 |  | 68/0 |  | 69/0 |  | 69/1 |  | 70/0 |  | 70/1 |  | 70/2 |  | 70/3 |  | 70/4 |  | 70/5 |  | 70/6 |  | 70/7 |  | 70/8 | [5 empty] | 12
347.1 | 9.2.24 | 344.9 | 4.2.24 | 369.2 | 17.1.25 | 200.9 | 09.10.24 | 374.1 | 20.9.24 | 394.9 | 25.01.25 | 388.4 | 21.01.25 | 418.9 | 21.01.25 | 418.6 | 09.01.25 | 414 | 13.01.25 | 419.6 | 15.01.25 | 420.3 | 23.12.24 | 419.6 | 19.12.24 | 418.2 | 17.12.24 | 5.3487
| DRY |  | DRY |  | DRY |  | DFR |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+0 |  | DA+0 |  | DD45+0 |  | DB2+0 |  | DA+3 |  | DC1+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  |  | 14
|  |  | 4.4.25 |  | 31.3.25 |  | 25.3.25 |  | 18.3.25 |  | 12.3.25 |  | 7.3.25 |  | 01.3.25 |  | 24.2.25 |  | 19.02.25 |  | 15.2.25 |  | 10.02.25 |  | 27.01.25 |  | 02.02.25 | [6 empty] | 13 | -1
| 70/9 |  | 70/10 |  | 70/11 |  | 71/0 |  | 71/1 |  | 71/2 |  | 71/3 |  | 71/4 |  | 71/5 |  | 71/6 |  | 71/7 |  | 71/8 |  | 72/0 |  | 72/1 | [5 empty] | 12
414.1 | 21.12.24 | 406.1 | 25.11.24 | 408.6 | 27.11.24 | 420.4 | 31.12.24 | 389.4 | 06.01.25 | 414.3 | 06.01.25 | 413 | 30.12.24 | 367.7 | 25.11.24 | 429.4 | 27.11.24 | 418 | 21.10.24 | 404.9 | 18.10.24 | 431.6 | 20.11.24 | 408.4 | 23.12.24 | 435.3 | 18.12.24 | 5.7612
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | 14
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | 14
| DA+3 |  | DA+3 |  | DA+3 |  | DB2+3 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB2+3 |  | DA+3 |  |  | 14
[34 empty] | 13 | -2
| 06.02.25 |  | 30.11.24 |  | 09.01.25 |  | 29.10.24 |  | 20.10.24 |  | 13.12.24 |  | 14.1.25 |  | 19.01.25 |  | 20.11.24 |  | 19.01.25 |  | 17.11.24 |  | 13.11.24 |  | 16.01.25
| 72/2 |  | 72/3 |  | 73/0 |  | 73/1 |  | 73/2 |  | 73/3 |  | 73/4 |  | 73/5 |  | 73/6 |  | 73/7 |  | 73/8 |  | 73/9 |  | 74/0 | [7 empty] | 11
403.9 | 27.9.24 | 395.2 | 15.10.24 | 400.8 | 10.9.24 | 383.3 | 16.9.24 | 379 | 13.9.24 | 381.2 | 30.9.24 | 384.7 | 09.10.24 | 368.8 | 23.9.24 | 365.5 | 19.9.24 | 392.4 | 4.10.24 | 374.9 | 25.9.24 | 379.5 | 11.9.24 | 378.9 | 10.10.24 |  |  | 4.9881
| DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | SANDY | [5 empty] | 13
| Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  |  |  | 13
| DA+0 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DB2+0 |  |  |  |  | 13
[28 empty] | 88.3821 | 219 | 223 | 221 | 0 | 191 | 167 | 24
cc
c
c
cc
cc
cc
cc
cc
cc
cc
cc
cc
cc
cc
cc
cc
cc
cc
c
cc
cc
cc
cc

## Clear locs shared by client (hidden)
Erection Workfront_shared by SPTL Section II_29.11.2024
SL No. | Location (G) | Current Status | SL No. | Location(F) | Current Status
1 | 33/1 | Untouch | 1 | 47/2 | Untouch | 33/8
2 | 35/0 | Untouch | 2 | 47/3 | Untouch
3 | 35/1 | Untouch | 3 | 47/5 | Untouch
4 | 35/2 | Untouch | 4 | 47/6 | Untouch
5 | 35/3 | Untouch | 5 | 47/7 | Untouch
6 | 35/4 | Untouch | 6 | 47/8 | Untouch
7 | 35/5 | Untouch | 7 | 47/9 | Untouch |  | 137
8 | 35/6 | Untouch | 8 | 49/0 | Untouch
9 | 35/7 | Untouch | 9 | 49/1 | Untouch
10 | 35/8 | Untouch | 10 | 49/3 | WIP (Sobha Devi)
11 | 37/2 | Untouch | 11 | 51/0 | Untouch
12 | 37/3 | Untouch | 12 | 52/3 | Untouch
13 | 37/4 | Untouch | 13 | 53/5 | Untouch
14 | 38/1 | Untouch | 14 | 53/6 | Untouch
15 | 38/2 | Untouch | 15 | 53/7 | Untouch
16 | 38/3 | Untouch | 16 | 53/8 | Untouch
17 | 38/6 | Untouch | 17 | 54/1 | Untouch
18 | 38/8 | Untouch | 18 | 54/2 | Untouch
19 | 39/0 | Untouch | 19 | 55/7 | Untouch
20 | 39/1 | Untouch | 20 | 57/2 | Untouch
21 | 39/4 | Untouch | 21 | 58/0 | Untouch
22 | 40/2 | Untouch | 22 | 59/0 | Materials shifting wip (Jirwa Devi)
23 | 40/3 | Untouch | 23 | 66/0 | Untouch
24 | 40/4 | Untouch | 24 | 67/0 | Untouch
25 | 40/5 | Untouch | 25 | 69/1 | Untouch
26 | 40/6 | Untouch | 26 | 71/6 | Untouch
27 | 41/12 | Untouch | 27 | 71/7 | Untouch
28 | 42/0 | Untouch | 28 | 73/3 | Untouch
29 | 43/0 | Untouch | 29 | 73/4 | Untouch
30 | 44/0 | Untouch | 30 | 73/5 | Untouch
31 | 49/0 | Untouch | 31 | 73/7 | Untouch
32 | 62/0 | Untouch | 32 | 74/0 | Untouch
33 | 63/2 | Untouch
34 | 63/5 | Untouch
35 | 63/6 | Untouch
36 | 64/0 | Untouch
37 | 65/1 | Untouch
38 | 65/2 | Untouch
39 | 65/6 | Untouch
40 | 65/7 | Untouch
41 | 66/0 | Untouch
42 | 66/1 | WIP (Sanjeev Kumar )
43 | 66/3
44 | 67/0 | WIP (Chinta Devi)
45 | 69/9 | WIP (Sunny const)
46 | 71/0