## Executive Summary
topic | finding
Generated on | 2026-05-21 17:55:40
Scope reviewed | 95-slide presentation; 20 TL projects in execution summary; SS slides 24-39 intentionally marked skipped.
DPR coverage | 16 of 20 TL projects have matching current DPRs in Raw Data/DPRs. Missing for TA 514, A920, A-303/304, and A-722/723.
Already automatable | Core execution signals exist for many projects: project details, status/progress, foundation, erection, stringing, stretch readiness/manpower, ROW/crossing/statutory remarks.
Biggest automation gap | Supply status is present in many DPRs but is not normalized by the current pipelines. This is the first new parser needed for deck automation.
Historical gap | Front availability tables with Feb/Mar/Apr values cannot be reliably rebuilt from a single latest DPR. Store every DPR snapshot or backfill archived DPRs.
External data gap | UEOB, commercial claims, pending amendments, and finance closure slides require a commercial/amendment tracker outside raw execution DPRs.
Workbook generated | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Productivity Summaries\CMD_Presentation_DPR_Automation_Scope_2026-05-21.xlsx

## TL Project Scope
project_code | region | tl_ss | project_name | presentation_slides | dpr_present | latest_dpr_file | overall_readiness | existing_automatic_signals | new_work_needed | not_available_from_current_dpr | scheduled_completion_slide | expected_completion_slide | project_value_cr_slide | ueob_cr_slide | presentation_requirements | latest_dpr_date | dpr_open_status | configured_status_sheets_found | configured_erection_sheets_found | configured_stringing_sheets_found | configured_stretch_sheets_found | configured_daily_stringing_found | project_detail_sources | summary_status_sources | foundation_sources | erection_sources | stringing_sources | stretch_sources | supply_sources | row_hindrance_sources | statutory_crossing_sources | visual_l2_sources | commercial_sources_in_dpr
A-303/304 | ER1 | TL | 400 KV D/C Twin Line Latehar- Patraru (A303/304) | 77 | No |  | Blocked - DPR missing |  |  | all slide fields: no matching DPR in Raw Data/DPRs; UEOB/project commercial figures are commercial source, not DPR execution data | -- | -- | 249 | 10 | activity_status, issues_support, manpower, supply_status
A-722/723 | ER2 | TL | Sikkim Tower Pkg TK04 (A-722/723) | 78, 79, 80, 81, 82 | No |  | Blocked - DPR missing |  |  | all slide fields: no matching DPR in Raw Data/DPRs; UEOB/project commercial figures are commercial source, not DPR execution data | -- | -- | 360 | 32 | activity_status, issues_support, monthly_plan, supply_status
A920 | NER | TL | 132 KV D/C Tawang-Lumla Line (A920) | 75, 76 | No |  | Blocked - DPR missing |  |  | all slide fields: no matching DPR in Raw Data/DPRs; UEOB/project commercial figures are commercial source, not DPR execution data | 12/04/27 | 12/04/27 | 90 | 7 | activity_status, front_availability, manpower, monthly_plan, project_contract_header, supply_status
TA 413 | NWR | TL | 765KV D/C Bikaner III - Neemrana II (TA – 413) | 3, 5, 7, 8, 41, 42, 43 | Yes | TA 413 - DPR - 2026-05-20.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 11/12/25 | 30/07/26 | 396 | 9 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | 2026-05-20 | repaired_defined_names (ValueError) | TA413_PBNTL | Erection | Stringing | Stretch readiness | Stringing | Bird Guard ; Check Survey ; Detailed Survey ; Hardware Supply; ROW Tracker; Supply Status; TA413_PBNTL; Tower PRS abstract ; Visual Chart | Final checking; Crossing status; Detailed Survey ; Erection; Foundation Daily Progress; Hardware Supply; JUMPER Details; L2 Plan vs Actual; Location Summary; ROW Tracker; Statutory Proposals; Stretch readiness ; Stretch readiness (2); Stringing; Supply Status; Survey summary; TA413_PBNTL | Final checking; Crossing status; Foundation; Foundation Daily Progress; L2 Plan vs Actual; Location Summary; ROW Tracker; S-Curve FDN; Stretch readiness ; Stretch readiness (2); Visual Chart | Final checking; Erection; Location Summary; S-Curve Erection; Stretch readiness ; Stretch readiness (2); Visual Chart | Final checking; JUMPER Details; OPGW; S-Curve Stringing; Stretch readiness ; Stretch readiness (2); Stringing; Visual Chart | Stretch readiness ; Stretch readiness (2) | Accessories; Foundation; Hardware Supply; L2 Plan vs Actual; Stringing; Supply Status | ROW Tracker; Tower Abstarct ; Visual Chart | Crossing status; Statutory Proposals; Stretch readiness ; Stretch readiness (2); Visual Chart | L2 Plan vs Actual; S-Curve Erection; S-Curve FDN; S-Curve Stringing; Supply Status; TA413_PBNTL; Tower PRS abstract ; Visual Chart
TA 414 | WR2 | TL | 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3, 9, 11, 12, 13 | Yes | TA 414 - DPR - 2026-05-21.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 11/12/25 | 30/10/26 | 656 | 87 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | 2026-05-21 | repaired_defined_names (ValueError) | VNTL - KEC | Erection Compiled | Stringing Compiled |  | Stringing Compiled | 765KV TA 414 VNTL; Erection ; Erection Compiled; Erection Completed ; FDN; FDN Completed; Project Details; Stringing Compiled | 765KV TA 414 VNTL; Crossing; DPR Sheet; Erection ; Erection Compiled; Erection Completed ; FDN; FDN Completed; Soil Inv.; Stringing; Stringing Compiled; Stringing Completed; Survey; VNTL - KEC; Visual chart | FDN; FDN Completed; Pile Fdn; VNTL - KEC; Visual chart | Erection ; Erection Compiled; Erection Completed ; Visual chart | Sheet2; Stringing; Stringing Compiled; Stringing Completed; Visual chart | Stringing Compiled | Stringing; Stringing Compiled; Stringing Completed | FDN; Stringing; Stringing Completed | Crossing; Visual chart | 765KV TA 414 VNTL; Pile Fdn; VNTL - KEC; Visual chart
TA 416 | NR3 | TL | 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 3, 5, 8, 63, 64 | Yes | TA 416 - DPR - 2026-05-17.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 06/11/25 | 31/05/26 | 447 | 2 | activity_status, front_availability, manpower, monthly_plan, project_contract_header, running_project_master, supply_status | 2026-05-17 | ok | MASTER SHEET | Erection Compiled | Stringing compiled |  | Stringing compiled | Erection Compiled ; MASTER SHEET; Project Details; Stringing compiled | Crossing Details; Erection Compiled ; MASTER SHEET; PENDING ERE DETAILS; PENDING FDN DETAILS; Progress.; Stringing compiled | PENDING ERE DETAILS; PENDING FDN DETAILS; Visual chart. | Erection Compiled ; Visual chart. | Stringing compiled; Visual chart. | Stringing compiled | Crossing Details; MASTER SHEET; Progress.; Stringing compiled | PENDING ERE DETAILS; PENDING FDN DETAILS; Visual chart. | Crossing Details; Visual chart. | MASTER SHEET; Progress.; Visual chart.
TA 418 | SR1 | TL | 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 3, 5, 9, 66, 67, 68 | Yes | TA 418 - DPR - 2026-05-21.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 11/12/25 | 30/06/26 | 154 | 5 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | 2026-05-21 | ok | MASTER SHEET | Erection Compiled | Stringing Compiled | Stringing Compiled | Stringing Compiled | Erection Compiled; MASTER SHEET; Project Details; Stringing Compiled | Crossing Details; Erection Compiled; MASTER SHEET; PENDING FDN DETAILS; Progress; Stringing Compiled; Visual Chart | PENDING FDN DETAILS; Progress; TSE-MANUAL-LT-11KV-33KV Details; Visual Chart | Erection Compiled; ROW TRACKER; TSE-MANUAL-LT-11KV-33KV Details; Visual Chart | ROW TRACKER; Stringing Compiled; Visual Chart | Stringing Compiled; TSE-MANUAL-LT-11KV-33KV Details | MASTER SHEET; Progress; Stringing Compiled | PENDING FDN DETAILS; ROW TRACKER | Crossing Details | MASTER SHEET; Progress; Visual Chart
TA 419 | NR1 | TL | 765KV D/C Sikar II – Narela (TA- 419) | 3, 6, 8, 56, 57, 58 | Yes | TA 419 - DPR - 2026-05-20.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 05/05/25 | 30/11/26 | 491 | 51 | activity_status, front_availability, issues_support, manpower, monthly_plan, project_contract_header, running_project_master, supply_status | 2026-05-20 | repaired_defined_names (ValueError) | DPR_TA419 | ERECTION COMPILED |  | Stringing Stretch Readiness |  | Const Revenue; DPR_TA419; ERECTION COMPILED; FDN; PGCIL; Pkg 2_Erection; Pkg 2_Foundation; Project details; Sheet7; Stringing Stretch Readiness; TOWER SUPPLY; Tack Welding | ; Summary; Const Revenue; DPR_TA419; Detailed Survey; ERECTION COMPILED; ERT; Erection Daily Progress; FDN; Foundation Daily Progress; Foundation Daily Progresss; Ins Hosting; PGCIL; Pkg 2_Erection; Pkg 2_Foundation; Pkg2_Stringing; ROW; Soil Inv; Statutory; Stringing Stretch Readiness; Supply Status; TOWER SUPPLY; Tack Welding | ; ; Summary; Const Revenue; FDN; Foundation Daily Progress; Foundation Daily Progresss; Pkg 2_Foundation; RATE; ROW; Sheet8; Sheet9; Statutory; Visual Chart | ; ; Summary; Const Revenue; ERECTION COMPILED; Erection Daily Progress; Erection productivity; Pkg 2_Erection; RATE; Sheet9; Statutory; Visual Chart | Const Revenue; Ins Hosting; Pkg2_Stringing; Statutory; Stringing; Stringing Stretch Readiness; Visual Chart | Stringing Stretch Readiness | DPR_TA419; Erection Daily Progress; Foundation Daily Progress; Foundation Daily Progresss; Ins Hosting; Stock Details; Stringing; Supply; Supply Status; TOWER SUPPLY | PGCIL; Pkg 2_Erection; Pkg 2_Foundation; Pkg2_Stringing; ROW; Visual Chart | Latest Tower Schedule; Pkg2_Stringing; Statutory; Tower Schedule; Tower schedule_07.03.25; Visual Chart | Const Revenue; DPR_TA419; Detailed Survey; L2; Latest Tower Schedule; Pkg 2_Foundation; Stringing Stretch Readiness; Supply; Tower Schedule; Tower schedule_07.03.25; Visual Chart | ERECTION COMPILED; ERT; FDN; TOWER SUPPLY
TA 421 | SR1 | TL | 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 3, 5, 7, 9, 69, 70, 71 | Yes | TA 421 - DPR - 2026-05-20.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 14/11/25 | May’26 | 382 | 4 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | 2026-05-20 | ok | Master Sheet | Erection Compiled | Stringing Compiled | Tack Welding | Stringing Compiled | Erection Compiled ; Master Sheet; Project Details; Stringing Compiled ; Visual Chart | Erection Compiled ; Master Sheet; ProGress Sheet ; Stringing Compiled ; Stubs and Towers ; SuPPLY ; Tower Tightening ; Visual Chart ; X-ing Details | ProGress Sheet ; Visual Chart | Erection Compiled ; Erection Productivity ; ProGress Sheet ; Visual Chart | Stringing Compiled ; Visual Chart | Stringing Compiled | Hardwares & Tower Accessories ; Master Sheet; Stringing Compiled ; Stubs and Towers ; SuPPLY ; Tower Accessories |  | Visual Chart ; X-ing Details | Master Sheet; ProGress Sheet ; Visual Chart
TA 504 | NWR | TL | 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 3, 8, 46, 47, 48 | Yes | TA 504 - DPR - 2026-05-21.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 22/06/26 | 28/09/26 | 255 | 31 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | 2026-05-21 | repaired_defined_names (ValueError) | DPR_TA-504 | Erection compiled | Stringing Compiled | Stringing Compiled | Stringing Compiled | DPR_TA-504; Erection compiled; Project Details; Stringing Compiled; Tightening | DPR_TA-504; Erection compiled; Location Summary; Stringing Compiled; Tightening | DPR_TA-504; Location Summary; VC_Lilo; VC_RMTL | Erection compiled; Location Summary; VC_Lilo; VC_RMTL | Stringing Compiled; VC_Lilo; VC_RMTL | Stringing Compiled | DPR_TA-504; Stringing Compiled | VC_Lilo; VC_RMTL |  | VC_Lilo; VC_RMTL
TA 505 | NWR | TL | 765KV D/C Beawar-Mandsaur TL (TA- 505) | 3, 8, 49, 50, 51 | Yes | TA 505 - DPR - 2026-05-19.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 21/06/26 | 30/09/26 | 561 | 48 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | 2026-05-19 | ok | DPR-Summary | Erection Compiled | Stringing Compiled | Stringing Compiled | Stringing Compiled | DPR-Summary; Earthing Status; Erection Compiled; Foundation; Project Details; Stringing Compiled | Balance Erc-RAJ; DPR-Summary; ERC ROW-MP; Earthing Status; Erection Compiled; Foundation; Stringing Compiled | DPR-Summary; Earthing Status; Foundation; Sheet4; Visual Chart | Balance Erc-RAJ; ERC ROW-MP; Erection Compiled; Erection Productivity | Stringing Compiled | Stringing Compiled | Balance Erc-RAJ; DPR-Summary; Earthing Status; Foundation; Stringing Compiled | DPR-Summary; ERC ROW-MP |  | DPR-Summary; Earthing Status; Foundation; Visual Chart
TA 506 | NWR | TL | 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 3, 7, 8, 52, 53, 54 | Yes | TA 506 - DPR - 2026-05-21.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | Aug’26 | Oct’26 | 592 | 38 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | 2026-05-21 | repaired_defined_names (ValueError) | DPR_TA-506 | Erection compiled | Stringing | Stringing | Stringing | DPR_TA-506; Erection compiled; Project Details; Stringing; Tightening | DPR_TA-506; Erection compiled; Location Summary; Stringing; Tightening | DPR_TA-506; Location Summary; Visual Chart | Erection compiled; Location Summary | Stringing | Stringing | DPR_TA-506; Stringing | Visual Chart |  | Visual Chart
TA 509 | WR2 | TL | 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 3, 9, 14, 15 | Yes | TA 509 - DPR - 2026-05-18.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 25/10/26 | 25/10/26 | 473 | 68 | activity_status, front_availability, issues_support, manpower, project_contract_header, running_project_master, supply_status | 2026-05-18 | ok | SUMMARY | ERECTION |  |  |  | DPR; EARTHING; ERECTION; SUMMARY | DPR; EARTHING; ERECTION; FOUNDATION; SUMMARY; SUPPLY; SURVEY STATUS ; SURVEY SUMMARY; XING | DPR; FDN pivot; FOUNDATION; SUMMARY; Sheet1; VC-765kV MKTL | DPR; ERECTION; Erection productivity; SUMMARY; Sheet1; VC-765kV MKTL | DPR; SUMMARY |  | SUPPLY | DPR; EARTHING; SURVEY STATUS ; SURVEY SUMMARY; XING | CST Gantry To AP 68 Common Poin; SURVEY STATUS ; SURVEY SUMMARY; XING | CST Gantry To AP 68 Common Poin; DPR; SUMMARY; SUPPLY; VC-765kV MKTL
TA 510 | WR2 | TL | 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 3, 9, 16, 17 | Yes | TA 510 - DPR - 2026-05-20.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 25/10/26 | 15/03/27 | 577 | 192 | activity_status, front_availability, issues_support, manpower, pending_amendments, project_contract_header, running_project_master, supply_status | 2026-05-20 | repaired_defined_names (ValueError) | AOTL - KEC | Erection Compiled |  |  |  | 765KV ASOTL; 765KV TA 414 VNTL; Erection ; Erection Compiled ; FDN; Pile Foundation; Project Details; Stringing Compiled | 765KV ASOTL; 765KV TA 414 VNTL; AOTL - KEC; Crossing; DPR Sheet; Erection ; Erection Compiled ; FDN; Pile Foundation; Soil Inv.; String; Stringing Compiled; Survey; Tree Enumeration; Visual chart 1 | AOTL - KEC; FDN; Pile Foundation; Visual chart 1 | Erection ; Erection Compiled ; Visual chart 1 | Sheet2; String; Stringing Compiled; Visual chart 1 | Stringing Compiled | Stringing Compiled | Pile Foundation | Crossing; Survey; Visual chart 1 | 765KV ASOTL; 765KV TA 414 VNTL; AOTL - KEC; Visual chart 1
TA 512 | NWR | TL | 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 3, 7, 8, 44, 45 | Yes | TA 512 - DPR - 2026-05-20.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 02/12/26 | 02/12/26 | 474 | 84 | activity_status, front_availability, issues_support, manpower, pending_amendments, project_contract_header, running_project_master, supply_status | 2026-05-20 | ok | Summary E | Erection Compiled |  | Tack Welding |  | Erection Compiled; L3 Plan; Project Details; Summary E; Summary S; Supply DPR | DPR Sheet ; Erection Compiled; Foundation; Hindrance Record; Power line Crossings ; Statuary clearance; Summary E; Summary S; Supply DPR ; Supply Status; WIP | Foundation; Hindrance Record; L3 Plan; Power line Crossings ; Visual Chart; WIP | Erection Compiled; Hindrance Record; L3 Plan; Power line Crossings ; Visual Chart | L3 Plan; OPGW; Power line Crossings ; Stringing; Visual Chart |  | Accessories; Hardware; Power line Crossings ; Stringing; Summary S; Supply DPR ; Supply Status | Erection Compiled; Foundation; Hindrance Record; Summary E; Visual Chart; WIP | Power line Crossings ; Statuary clearance; TS Gantry - AP47; Visual Chart | Summary E; Summary S; Supply Status; TS Gantry - AP47; Visual Chart
TA 513 | NR2 | TL | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 3, 6, 8, 60, 61 | Yes | TA 513 - DPR - 2026-05-19.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 22/12/26 | -- | 665 | 233 | activity_status, front_availability, issues_support, manpower, project_contract_header, running_project_master, supply_status | 2026-05-19 | ok | Summary | Ere S-P; Ere S-F |  |  |  | Erection Compiled; FDN S-F; FDN S-P; Sheet5; Summary; Summary DPR; Supply | Crossing status; DPR S-F & S-P (2); Erection Compiled; Proposal; Proposal .; ROW S-F; ROW S-P; Sheet5; Summary; Summary DPR; Supply; Supply.; Survey ; T.Marking | Concrete; Crossing status; FDN S-F; FDN S-P; Master SF; Master SP; ROW S-F; ROW S-P; T.Abstract; VC -SF; VC -SP | Ere S-F ; Ere S-P ; Erection Compiled; Master SF; Master SP; VC -SF; VC -SP | VC -SF; VC -SP |  | Supply; Supply.; T.Abstract | Forest; LS; Master SF; Master SP; ROW S-F; ROW S-P; T.Marking; VC -SF; VC -SP | Crossing status; Forest; Master SF; Master SP; Proposal; Proposal .; TS SP ; VC -SF; VC -SP | LS; Master SF; Master SP; Supply.; TS SF; TS SP ; VC -SF; VC -SP | Sheet1
TA 514 | WR2 | TL | 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 3, 6, 9, 18, 19 | No |  | Blocked - DPR missing |  |  | all slide fields: no matching DPR in Raw Data/DPRs; UEOB/project commercial figures are commercial source, not DPR execution data | 22/07/28 | 22/07/28 | 780 | 533 | activity_status, front_availability, issues_support, manpower, pending_amendments, project_contract_header, running_project_master, supply_status
TA 515 | WR2 | TL | 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 3, 6, 9, 20, 21 | Yes | TA 515 - DPR - 2026-05-11.xlsx | Medium - core summary available, detail parsers/config incomplete | project details/header; normalized status sheet configured; erection/source loc data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 11/08/28 | 11/08/28 | 348 | 206 | activity_status, front_availability, issues_support, manpower, pending_amendments, project_contract_header, running_project_master, supply_status | 2026-05-11 | ok | DPR | Erection Compiled |  |  |  | Erection Compiled | DPR; Erection Compiled; Visual chart | DPR; Visual chart | Erection Compiled; Visual chart |  |  | Store Stock | DPR; Erection Compiled | Visual chart | DPR; Visual chart
TA 601 | SR1 | TL | 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 3, 9, 72, 73 | Yes | TA 601 - DPR - 2026-05-20.xlsx | High for core status; supply/issue parser needed | project details/header; normalized status sheet configured; erection/source loc data; stringing/source span data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 12/04/27 | 12/04/27 | 515 | 178 | activity_status, front_availability, issues_support, manpower, project_contract_header, running_project_master, supply_status | 2026-05-20 | ok | Master Sheet | Erection Compiled | Stringing Compiled | STRG Stretch | Stringing Compiled | Foundation & Erection; Master Sheet; Stringing Compiled; Visual Chart; Visual Chart | Erection Compiled; Foundation & Erection; Master Sheet; Progress Sheet ; STRG Stretch ; SUPPLY; Stringing Compiled; Visual Chart; Visual Chart ; X-ing Details | Foundation & Erection; Master Sheet; Progress Sheet ; ROW; STRG Stretch ; Visual Chart; Visual Chart | Erection Compiled; Foundation & Erection; Progress Sheet ; STRG Stretch ; Visual Chart; Visual Chart | STRG Stretch ; Stringing Compiled; Visual Chart; Visual Chart | Stringing Compiled | Foundation & Erection; SUPPLY; Stringing Compiled | Foundation & Erection; Progress Sheet ; ROW; STRG Stretch | STRG Stretch ; Visual Chart; Visual Chart ; X-ing Details | Master Sheet; Progress Sheet ; Visual Chart; Visual Chart
TA 602 | WR2 | TL | 80800 KV HVDC KPS-II to Nagpur (TA- 602) | 3, 6, 9, 22, 23 | Yes | TA 602 - DPR - 2026-05-18.xlsx | Medium - core summary available, detail parsers/config incomplete | project details/header; normalized status sheet configured; erection/source loc data; supply signals; issue/crossing/ROW signals | supply parser; support-issue summarizer from ROW/statutory/crossing; presentation output transformer | UEOB/project commercial figures are commercial source, not DPR execution data; historical monthly front/completed/gang table needs archived DPR snapshots unless already stored elsewhere | 12/11/28 | 12/09/28 | 612 | 436 | activity_status, front_availability, issues_support, manpower, project_contract_header, running_project_master, supply_status | 2026-05-18 | ok | DPR-KEC | Erection |  |  |  | DPR-KEC; Earthing; Erection; Supply Status; WIP | DPR-KEC; Erection; Supply Status; Survey details; WIP; statuary clearance (2) | FDN; WIP | Erection |  |  | Supply Status | Composite-Survey(05-04-2026) | Composite-Survey(05-04-2026); statuary clearance; statuary clearance (2) | DPR-KEC; Visual Chart

## Requirement Mapping
requirement_group | slide_fields | current_dpr_source | current_automation | recommended_action | priority
Project contract header | LOA date, LOA value, contractual completion, planned/target completion | Project Details sheets; sometimes summary/DPR sheet header | Partially available in DPRs; not fully normalized for deck output | Add project master parser and reconcile with slide summary/running-list values | P1
Activity status table | Activity, UoM, LOA qty, revised qty, L2 qty, completed, balance, front, gangs, plan/act, remarks | Configured Status sheets plus Foundation/Erection/Stringing compiled sheets | Status, foundation, erection, stringing already have normalized outputs, but not merged into slide layout | Create project_status_mart with one row per project/activity/month and presentation columns | P1
Supply status | Stub, Tower, Conductor, Earthwire, Hardware, OPGW and plan/balance/remarks | Supply Status, Supply, TOWER SUPPLY, Store Stock, Progress/DPR summary rows | Not normalized today | Build supply parser with sheet-specific templates and item normalization | P1
Front availability history | Feb/Mar/Apr front, completed, gang by Foundation/Erection/Stringing | Latest status/progress sheets and possibly archived DPR snapshots | Current snapshot can be parsed; historical month table is not reconstructable from only latest DPR in many cases | Persist monthly snapshots from every DPR receipt; backfill only where old DPRs are available | P1
Monthly completion plan matrix | Completion Plan, Front Required from POWERGRID, Gangs Planned, Supply plan across May-Mar | L2 Plan vs Actual, summary/progress tabs, supply sheets | Partially present but layouts vary heavily | Build forecast/plan parser after agreeing source-of-truth for reforecast values | P2
Manpower/gangs | Gangs available, gang strength, manual/TSE manpower status | Stringing compiled, erection compiled, manpower audit, progress sheets | Stringing manpower audit exists for some projects; erection gang strength exists in many DPRs | Extend manpower fact to erection/foundation and map to slide gang columns | P2
Issues/support narrative | ROW, forest, railway, shutdown, drawings, amendments, PGCIL support text | ROW, Hindrance, Crossing, Statutory, WIP, remarks columns | Raw signals exist; final executive narrative still needs rule-based summarization and human review | Create issue register extraction first; generate draft bullets with source links/rows | P2
Pending amendments | Pending since, achievement since last discussion, amendment number/date | Some remarks/summary sheets mention amendments; no consistent DPR source | Not reliable from DPR alone | Use a separate amendment tracker or add standardized DPR amendment section | P1 external
Project value and UEOB | Project Value, UEOB as of 1 May 2026 | Project Details may have LOA value; UEOB is commercial/finance data | Not available from raw DPR execution sheets | Connect commercial/finance tracker or keep manual | P1 external
Commercial claims/closures | Claims, pendency, outstanding, BG, closure status | Not part of execution DPRs | Out of DPR scope | Separate commercial claim source required | P1 external
Substation status slides | SS supply/civil/electrical/foundation/erection status | No SS DPRs in current folder per request | Skipped | Add SS DPR/source files later and build separate SS schema | Later

## Issues Log
severity | project_code | issue | impact | recommendation
High | A-303/304 | No matching DPR found in Raw Data/DPRs | Project slides cannot be auto-filled from current DPR files | Add latest DPR/source workbook or mark this project as manually maintained
High | A-722/723 | No matching DPR found in Raw Data/DPRs | Project slides cannot be auto-filled from current DPR files | Add latest DPR/source workbook or mark this project as manually maintained
High | A920 | No matching DPR found in Raw Data/DPRs | Project slides cannot be auto-filled from current DPR files | Add latest DPR/source workbook or mark this project as manually maintained
Medium | TA 413 | Workbook has invalid defined-name metadata | Naive Excel readers fail even though sheets can be read after in-memory repair | Patch loader to strip invalid defined names or save/repair source workbook upstream
Medium | TA 413 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 414 | Workbook has invalid defined-name metadata | Naive Excel readers fail even though sheets can be read after in-memory repair | Patch loader to strip invalid defined names or save/repair source workbook upstream
Medium | TA 414 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 416 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 418 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 419 | Workbook has invalid defined-name metadata | Naive Excel readers fail even though sheets can be read after in-memory repair | Patch loader to strip invalid defined names or save/repair source workbook upstream
Medium | TA 419 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 421 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 504 | Workbook has invalid defined-name metadata | Naive Excel readers fail even though sheets can be read after in-memory repair | Patch loader to strip invalid defined names or save/repair source workbook upstream
Medium | TA 504 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 505 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 506 | Workbook has invalid defined-name metadata | Naive Excel readers fail even though sheets can be read after in-memory repair | Patch loader to strip invalid defined names or save/repair source workbook upstream
Medium | TA 506 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 509 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 510 | Workbook has invalid defined-name metadata | Naive Excel readers fail even though sheets can be read after in-memory repair | Patch loader to strip invalid defined names or save/repair source workbook upstream
Medium | TA 510 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 512 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 513 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
High | TA 514 | No matching DPR found in Raw Data/DPRs | Project slides cannot be auto-filled from current DPR files | Add latest DPR/source workbook or mark this project as manually maintained
Medium | TA 515 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 601 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
Medium | TA 602 | Supply data exists but no normalized supply parser is present | Supply rows on slides remain manual despite DPR signals | Implement supply parser and item normalization
High | ALL | Historical front/completed/gang monthly table needs archived snapshots | Latest DPR alone usually cannot recreate Feb/Mar/Apr values shown in slides | Persist monthly status snapshots from each DPR and backfill from old emails/files where available
High | ALL | UEOB/project value/claims are commercial data, not execution DPR data | Slides 8-9 and 84-94 need a separate source | Connect commercial tracker/ERP export or keep manual tabs in the scope workbook
Medium | ALL | Presentation output requires one canonical project/status mart | Existing normalized outputs are separate by domain and do not match slide table columns directly | Build a presentation data mart that joins project master, status, supply, front, manpower, and issues

## Parser Workplan
phase | priority | work_item | deliverable | notes
1 | P1 | Refresh and validate normalized execution outputs on current May DPRs | Current status/foundation/erection/stringing tables for all configured projects | Existing parquet outputs are useful but were not assumed current.
1 | P1 | Create project master parser | project_master table with LOA date, LOA value, contractual completion, planned/expected completion candidates | Reconcile DPR values vs presentation summary manually at first.
1 | P1 | Create supply parser | supply_status_fact by project, item, total/revised/L2/supplied/balance/monthly plans/remarks | Needs templates for Supply Status, Supply, TOWER SUPPLY, Store Stock, and embedded DPR summary supply rows.
1 | P1 | Create presentation status mart | One table matching status slide columns for Activity and Supply sections | This is the table that should feed slide automation.
2 | P2 | Create issue register extraction | issue_register from ROW, Hindrance, Crossing, Statutory, WIP, remarks | Use source row references; generate draft support bullets for review.
2 | P2 | Persist DPR snapshots over time | monthly_front_history with front/completed/gang by activity/month | Needed for historical front tables and trend slides.
2 | P2 | Add forecast/plan parser | completion_plan_matrix by project/activity/month/plan_type | Requires agreement on source-of-truth for reforecast vs L2.
3 | External | Connect commercial/amendment data | commercial_claims, UEOB, pending_amendments tables | Cannot be reliably derived from execution DPRs alone.
3 | Later | Add substation sources | SS parser/schema when SS DPRs are available | Skipped for now per instruction.

## PPT Slides
slide | title | slide_type | project_codes | requirements | table_count | image_count | text_extract
1 | KEC International Limited | divider |  | issues_support | 0 | 9 | KEC International Limited PGCIL Review – 18th May’26 Power T & D Cables Railways Civil Renewables Oil & Gas Pipelines
2 | Agenda Points | pending_amendments |  | activity_status, front_availability, issues_support, commercial_claims, pending_amendments, manpower | 0 | 0 | Agenda Points Priority projects to be completed Support Required - In terms of ROW, front and Land availability Pending Amendments and Manpower Status Region and Project wise Status with critical issues Commercial Closures and Pending Claims Project wise details under commercial closure Region wise Cost Compensation and L2 revision Finalization of spare supply contract through PESL for South OLPAD and Narendra extension Project. NOA from PGCIL was issued on 26/11/24 for South OLPAD-23 Cr. and for 13/05/25(Narendra- 60.35 Lacs )
3 | Summary of Projects under Execution by KEC (TL Projects) | project_summary | TA 413, TA 414, TA 416, TA 418, TA 419, TA 421, TA 504, TA 505, TA 506, TA 509, TA 510, TA 512, TA 513, TA 514, TA 515, TA 601, TA 602 | supply_status | 1 | 0 | Summary of Projects under Execution by KEC (TL Projects)
4 | Summary of projects under Execution by KEC (SS Projects) | project_summary |  |  | 1 | 0 | Summary of projects under Execution by KEC (SS Projects)
5 | Priority Projects to be completed | project_status | TA 413, TA 416, TA 418, TA 421 | activity_status | 1 | 0 | Priority Projects to be completed
6 | Support Required | project_status | TA 419, TA 513, TA 514, TA 515, TA 602 | activity_status, front_availability, issues_support | 0 | 0 | Support Required Limited Front Availability where work is moving with minimal Progress 800 KV HVDC TL-06 Khavda –Nagpur (TA- 602) 765 KV D/C Sikar Narela TL (TA- 419)- Start of Stringing works, 2 TSEs available at site Finalization of Pile Fdn in South Olpad Ahemdabad TL- Reserve Forest Issues need to be resolved Projects - Non starter 800 KV HVDC TL-02 Khavda-Nagpur (TA- 514) 800 KV HVDC TL-03 Khavda Nagpur (TA- 515) 765 KV South OLPAD GIS – Land still not handed over ( as per L2- Mar’25 )( SA-508) 400 KV D/C Siwani Fatehabad and Sivani Patran (TA- 513)
7 | Pending Amendments | pending_amendments | TA 325, TA 413, TA 421, TA 506, TA 512 | activity_status, pending_amendments, manpower | 1 | 0 | Pending Amendments SS Projects : 1986 ( Civil- 1283 & Electrical- 703) Erection : 1797 Manpower (50 Gangs) Stringing : 970 Manpower(12 TSE & 8 Manual) Total : 4753 Manpower Manpower Status
8 | List of Running Substation & TL Project (Cont..) | running_project_master | TA 413, TA 416, TA 419, TA 504, TA 505, TA 506, TA 512, TA 513 | supply_status, running_project_master | 1 | 0 | List of Running Substation & TL Project (Cont..)
9 | List of Running Substation & TL Project | running_project_master | TA 414, TA 418, TA 421, TA 509, TA 510, TA 514, TA 515, TA 601, TA 602 | running_project_master | 1 | 0 | List of Running Substation & TL Project
10 | Gujarat Region (WR-II) | divider |  |  | 0 | 0 | Gujarat Region (WR-II)
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | project_status | TA 414 | project_contract_header, activity_status, supply_status, front_availability, monthly_plan, pending_amendments, manpower | 3 | 0 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414)
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | project_status | TA 414 | project_contract_header, activity_status, supply_status, front_availability, monthly_plan | 2 | 0 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414)
13 | Issues / Support Required | issues_support | TA 414 | project_contract_header, activity_status, supply_status, front_availability, issues_support | 1 | 0 | Issues / Support Required 1. Fdn:33 loc under hold due to ROW-9, Railway clearance-2, forest-1, Nilgiri tree cutting issues-5, Stub NA-6, Solar plant-2. Additionally, 08 loc under hold, which are falling inside GOPIN Industrial Park. Location availability not available to complete in the month of May, Police Protection required for all locations 2. Erection: Out of balance 134 loc in erection, 56 loc are under ROW as on date, Front available-18 and WIP 14 3. Cable bypass agency needs to be finalized by PGCIL. Shutdown needs to be expedited 4. Hotline stringing approval is required for 66 KV and above, wherever shut down is critical. (Total qty- 48 and in the BOQ, only 01 qty is approved). Tree cutting needs to be expedited for ready stinging stretches (131/3,131/4,131/5,132/2,165/1, 232/1 & 247/0) 5. 02 nos of Railway and 02 PLC Xing approval pending TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414)
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | project_status | TA 509 | project_contract_header, activity_status, supply_status, front_availability, manpower | 2 | 0 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509)
15 | Issues / Support Required | issues_support | TA 509 | project_contract_header, activity_status, issues_support | 1 | 0 | Issues / Support Required 1. Drawings required for Raised Chimney – 10 locations are affected on account of same. This is affecting 9 km of stringing stretch 2. 10 locations under Right of Way 3. Approval of Diversion proposal TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509)
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | project_status | TA 510 | project_contract_header, activity_status, supply_status, front_availability, pending_amendments, manpower | 3 | 0 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510)
17 | Issues / Support Required | issues_support | TA 510 | project_contract_header, activity_status, front_availability, issues_support | 1 | 0 | Issues / Support Required 1. 16 kms Detailed Survey approval pending 2. Pile foundation work stopped due to reserve forest approval pending 3. Continuous Front required to maximize the output TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510)
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | project_status | TA 514 | project_contract_header, activity_status, supply_status, front_availability, issues_support, pending_amendments, manpower | 2 | 0 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514)
19 | Issues / Support Required:- | issues_support | TA 514 | project_contract_header, issues_support | 1 | 0 | Issues / Support Required:- 1. Locations under severe ROW, Land Compensation and crop compensation not yet finalized by committee (DLVC committee) 2. Section -16 pending, this is crucial to use administrative support to clear locations TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514)
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | project_status | TA 515 | project_contract_header, activity_status, supply_status, front_availability, issues_support, pending_amendments, manpower | 2 | 0 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515)
21 | Issues / Support Required | issues_support | TA 515 | project_contract_header, front_availability, issues_support | 1 | 0 | Issues / Support Required 1. Locations under severe ROW, and no front available 2. PGCIL Establishment TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515)
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | project_status | TA 602 | project_contract_header, activity_status, supply_status, front_availability, manpower | 3 | 0 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602)
23 | Issues / Support Required | issues_support | TA 602 | project_contract_header, activity_status, issues_support | 1 | 0 | Issues / Support Required 1. Power Line Crossing Approval. (In which 9 No's Site Visit done) Total-12 No’s ¦ Submitted-11¦ Balance-1¦ Approval Required-11 2. NH Crossing Site Inspection (Submitted-3 No’s) Total-4 No’s ¦ Submitted-3¦ Balance-1¦ Approval Required-3 3. Finalization of river crossing Proposal (Narmada River Crossing) TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602)
24 | SS118 220kV Bay Ext Raigarh GIS Sub-Sation (SA52C) | substation_skipped |  | project_contract_header, activity_status | 2 | 0 | SS118 220kV Bay Ext Raigarh GIS Sub-Sation (SA52C)
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | substation_skipped |  | project_contract_header, activity_status, supply_status, running_project_master, manpower | 2 | 0 | 765/400 kV KPS-2 Ext 39T (SA-503)
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | substation_skipped |  | project_contract_header, activity_status, supply_status, running_project_master | 2 | 0 | 765/400 kV KPS-2 Ext 39T (SA-503)
27 | 765/400 kV KPS-2 Ext 39T (SA-503) | substation_skipped |  | project_contract_header, activity_status, running_project_master | 2 | 0 | 765/400 kV KPS-2 Ext 39T (SA-503)
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | substation_skipped |  | project_contract_header, activity_status, supply_status, issues_support, running_project_master | 2 | 0 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8)
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | substation_skipped |  | project_contract_header, activity_status, supply_status, running_project_master | 2 | 0 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8)
30 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | substation_skipped |  | project_contract_header, activity_status, issues_support, running_project_master | 1 | 0 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) Issues / Support Required The erection of the 80 MVAR reactor by PGCIL is still pending Clamps and connector drawings are yet to be approved
31 | SS33T 765kV GIS South Olpad (SA-508) | substation_skipped |  | project_contract_header, activity_status, supply_status, issues_support, running_project_master | 2 | 0 | SS33T 765kV GIS South Olpad (SA-508)
32 | SS33T 765kV GIS South Olpad (SA-508) | substation_skipped |  | project_contract_header, issues_support, running_project_master | 1 | 0 | SS33T 765kV GIS South Olpad (SA-508) Issues / Support Required Finalization of spare supply contract through PESL for South OLPAD Project. NOA from PGCIL was issued on 26/11/24 for South OLPAD-23 Cr
33 | SS64T 765kV GIS Narendra Extn (SA-603) | substation_skipped |  | project_contract_header, activity_status, supply_status, issues_support, running_project_master | 2 | 0 | SS64T 765kV GIS Narendra Extn (SA-603)
34 | SS64T 765kV GIS Narendra Extn (SA-603) | substation_skipped |  | project_contract_header, activity_status, supply_status, running_project_master | 2 | 0 | SS64T 765kV GIS Narendra Extn (SA-603)
35 | 765KV Bay Extension GIS Sub-Station Narela | substation_skipped |  | project_contract_header, activity_status, supply_status, running_project_master | 2 | 0 | 765KV Bay Extension GIS Sub-Station Narela
36 | 765KV Bay Extension GIS Sub-Station Narela | substation_skipped |  | project_contract_header, activity_status, running_project_master | 2 | 0 | 765KV Bay Extension GIS Sub-Station Narela
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | substation_skipped |  | project_contract_header, activity_status, supply_status, running_project_master | 2 | 0 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8)
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | substation_skipped |  | project_contract_header, activity_status, supply_status, running_project_master | 2 | 0 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8)
39 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | substation_skipped |  | project_contract_header, activity_status, issues_support, running_project_master | 1 | 0 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) Issues / Support Required The erection of the 80 MVAR reactor by PGCIL needs to be completed Clamps and connector drawings are yet to be approved
40 | North Western Region | divider |  |  | 0 | 0 | North Western Region
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | project_status | TA 413 | project_contract_header, activity_status, supply_status, front_availability, manpower | 3 | 0 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413)
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | project_status | TA 413 | project_contract_header, activity_status, supply_status, front_availability, monthly_plan | 2 | 0 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413)
43 | Issues / Support Required | issues_support | TA 413 | project_contract_header, activity_status, issues_support, pending_amendments | 1 | 0 | Issues / Support Required Amendment is pending since Jan’26 Frequent disruption to Stringing work due to ROW TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413)
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | project_status | TA 512 | project_contract_header, activity_status, supply_status, front_availability, issues_support, manpower | 3 | 0 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512)
45 | Issues / Support Required | issues_support | TA 512 | project_contract_header, activity_status, supply_status, issues_support, pending_amendments | 1 | 0 | Issues / Support Required 1. Amendment of BOQ has been pending since 20/02/2026 2. Supply of 48F OPGW cable are delayed due to non-finalization of repeater station locations 3. Foundation work at 8 locations is delayed due to pending statutory clearances (NH – 2 Nos. and PLC – 1 No.) 4. Commencement of tower erection at 37 locations is delayed due to non-disbursement of compensation for completed foundation work TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512)
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | project_status | TA 504 | project_contract_header, activity_status, supply_status, front_availability, pending_amendments, manpower | 3 | 0 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504)
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | project_status | TA 504 | project_contract_header, activity_status, supply_status, front_availability, monthly_plan | 2 | 0 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504)
48 | Issues / Support Required | issues_support | TA 504 | project_contract_header, activity_status, supply_status, front_availability, issues_support, pending_amendments | 1 | 0 | Issues / Support Required 1. No work front for foundation works, 21 locations hold due to crossings 2. Required to expedite the ROW (Erection-10/3, 26/9, 5H/0, 5G/5, 4/1 Foundation- 10/4, 5G/2, 5G/3, 5H/1 Stringing:12/0 - 13/0, 14/0 - 15/0) 3. Amendment submitted on 23rd April and issuance pending 4. Need to Expedite Tower Erection ULE structural drawings 28/1(DB1+0, -1.5M ULE) & 31/2 (DB1+6, -1.5M ULE) 5. NH crossing –02 no's approval pending needs to expedite TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504)
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | project_status | TA 505 | project_contract_header, activity_status, supply_status, front_availability, issues_support, pending_amendments, manpower | 3 | 0 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505)
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | project_status | TA 505 | project_contract_header, activity_status, supply_status, front_availability, monthly_plan | 2 | 0 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505)
51 | Issues / Support Required | issues_support | TA 505 | project_contract_header, issues_support | 1 | 0 | Issues / Support Required Shutdown Bypass Cable Arrangement: Required cables for shutdown bypass arrangement need to be arranged at the earliest to avoid stoppages during execution TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505)
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | project_status | TA 506 | project_contract_header, activity_status, supply_status, front_availability, manpower | 3 | 0 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506)
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | project_status | TA 506 | project_contract_header, activity_status, supply_status, front_availability, monthly_plan | 2 | 0 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506)
54 | Issues / Support Required | issues_support | TA 506 | project_contract_header, issues_support | 1 | 0 | Issues / Support Required 1. Need to expedite clearance of ROW/HOLD locations (Forest HOLD-15 Udaipur Region Nos, Statutory clearences-21, ROW-28, Route change HOLD-4) due to this 21KM affected 2. Required RC/ULE 17 nos affecting 25 locations 3. Design of Strengthening X-Arm locations required (4 out of 15) – details shared with Engg. Dept 4. NH Crossings-08 Nos approval still pending TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506)
55 | Northern Region(NR-I) | divider |  |  | 0 | 0 | Northern Region(NR-I)
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | project_status | TA 419 | project_contract_header, activity_status, supply_status, front_availability, issues_support, manpower | 3 | 0 | TL02 - 765KV D/C Sikar II – Narela (TA- 419)
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | project_status | TA 419 | project_contract_header, activity_status, supply_status, front_availability, monthly_plan | 2 | 0 | TL02 - 765KV D/C Sikar II – Narela (TA- 419)
58 | Issues / Support Required | issues_support | TA 419 | project_contract_header, activity_status, supply_status, front_availability, issues_support | 1 | 0 | Issues / Support Required 1. Clearance of balance foundation locations for taking up works 2. Severe ROW continues to affect opening of fronts in Talao and Charra villages affecting 11 locations 3. Locations are progressively being made clear of ROW and put to work. For water submerged locations approval of shallow design is critical 4. HORCL Approval is still pending affecting release of 6 Towers 5. Clearance of Stringing stretch Stringable sections totaling 18 Kms. in Mahendargarh District is ready which is free from any rectification The Stringing gang has already been remobilized post idling since Jan-2026 due to ROW issues on account of pending MRC in Mahendragarh & Rewari The Pilot pulling started on 20th April for 1st section of B/0 to C/0 however it was stopped due to ROW MRC of Mahendragarh is disputed & for Rewari it is still pending, stringing Workfront is restricted 1 gang & 2 TSEs are idling TL02 - 765KV D/C Sikar II – Narela (TA- 419)
59 | Northern Region (NR-II) | divider |  |  | 0 | 0 | Northern Region (NR-II)
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | project_status | TA 513 | project_contract_header, activity_status, supply_status, front_availability, issues_support, manpower | 3 | 0 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513)
61 | Issues / Support Required | issues_support | TA 513 | project_contract_header, supply_status, front_availability, issues_support | 1 | 0 | Issues / Support Required 1. Market Rate Compensation (MRC) is still pending for finalization 2. Work front availability 3. Approval of the OPGW drum schedule is still pending due to which supply activities could not be initiated. The same was submitted to PGCIL on 10.03.2026 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513)
62 | Northern Region (NR-III) | divider |  |  | 0 | 0 | Northern Region (NR-III)
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | project_status | TA 416 | project_contract_header, activity_status, supply_status, front_availability, manpower | 3 | 0 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416)
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | project_status | TA 416 | project_contract_header, activity_status, supply_status, front_availability, monthly_plan | 2 | 0 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416)
65 | Southern Region (SR-I) | divider |  |  | 0 | 0 | Southern Region (SR-I)
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | project_status | TA 418 | project_contract_header, activity_status, supply_status, front_availability, manpower | 3 | 0 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418)
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | project_status | TA 418 | project_contract_header, activity_status, supply_status, front_availability, monthly_plan | 2 | 0 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418)
68 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | issues_support | TA 418 | project_contract_header, issues_support, pending_amendments | 1 | 0 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) Issues / Support Required 1. Clearance for final checking ROW 4 locations. ROW constraints affecting tack welding activities in 13 Locations 2. Approval of the submitted Amendment–04, pending from 7th Feb’26
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | project_status | TA 421 | project_contract_header, activity_status, supply_status, front_availability, manpower | 3 | 0 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421)
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | project_status | TA 421 | project_contract_header, activity_status, supply_status, front_availability, monthly_plan | 2 | 0 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421)
71 | Issues / Support Required | issues_support | TA 421 | project_contract_header, issues_support, pending_amendments | 1 | 0 | Issues / Support Required 1. Amendment # 4 is pending since from Feb’26 TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421)
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | project_status | TA 601 | project_contract_header, activity_status, supply_status, front_availability, manpower | 3 | 0 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601)
73 | Issues / Support Required | issues_support | TA 601 | project_contract_header, activity_status, issues_support | 1 | 0 | Issues / Support Required 1. All Crossing Proposals (11 proposal:6 PLC, 3 NH and 2 Railway), are submitted but no approval received till date 2. RC Foundation Drawings Required ( DC1, DC2, DD1, DD2)- For 14 Location 3. Two location – 110 /0 and 111/0 has been hold from PGCIL, which is hold due to widening of NH. Consequently 0.4 km of check survey is also hold TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601)
74 | North East Project | divider |  |  | 0 | 0 | North East Project
75 | TW24 - 132kV Tawang-Lumla Line | project_status | A920 | project_contract_header, activity_status, supply_status, front_availability, manpower | 3 | 0 | TW24 - 132kV Tawang-Lumla Line
76 | TW24 - 132kV Tawang-Lumla Line | project_status | A920 | project_contract_header, activity_status, supply_status, front_availability, monthly_plan | 2 | 0 | TW24 - 132kV Tawang-Lumla Line
77 | 400 KV D/C Twin Line Latehar- Patraru | project_status | A-303/304 | activity_status, supply_status, issues_support, manpower | 1 | 0 | 400 KV D/C Twin Line Latehar- Patraru
78 | Sikkim Tower Pkg TK04 | project_status | A-722/723 | activity_status, supply_status, monthly_plan | 1 | 0 | Sikkim Tower Pkg TK04 220 KV D/C Dikchu - Singhik Transmission Line a) The partially completed 132/66kv Singhik Sub-station has been abandon by Powergrid due to rapid sinking of entire 132/66kv Singhik Sub-Station Land b) Based on abandonment of 132/66kv Singhik Sub-Station, the scope of the above said line has been reduced upto AP86/0 from Dikchu SS end and Powergrid suggested for charging of the said line up to AP86/0 from Dikchu SS end i.e. 21.516 KM Line Length against Total Line Length 22.440 KM c) Due to reduction of scope the line from AP 86/0 to Singhik SS Gantry i.e. 0.711KM has been abandon resulting 5 Nos Erected & Strung Tower Location near Singhik SS end i.e. AP87/0 (DCS+9), AP88/0 (DD+18), AP89/0 (DCS+9), AP90/0 (DD+18), AP91/0 (DD+6 DE AUX) has also been abandoned d) Based on Sl No. (a,b,c) above the balance work and its completion timeline are as follows: Conductor Stringing – 4 Span (76/0-77/0 & 79A/0 to 81/0 i.e. 627 Mtr), OPGW Stringing – 12.588KM and Cutting of Soil for obtaining ground clearance in 47/0-48/0 and 51/0 to 52/0
79 | Sikkim Tower Pkg TK04 | project_status | A-722/723 | activity_status, supply_status | 1 | 0 | Sikkim Tower Pkg TK04 2. 220 KV D/C Singhik - Chungthang Transmission Line a) Due to Natural Disaster i.e. Teesta GLOF Flood on 04.10.2023 and subsequent Cloud burst Flash Flood in North Sikkim on 18th Jun'24 & 20th May’25 the portion of above said constructed line i.e. 19.479km from AP28/0 to Chungthang Sub-station completely damage/washout out of total line length of 29.009km. Till date most part of the Line is inaccessible after Natural disaster b) 132/66kv Singhik Sub-Station and 132/66kv Chungthang Sub-Station have been declared as abandoned by Powergrid c) The status of balance work before Natural Disaster is as follows 3. 66 KV D/C Chungthang - Lachen Transmission Line a) Due to Natural Disaster i.e. Teesta GLOF Flood on 04.10.2023 and subsequent Cloud burst Flash Flood in North Sikkim on 18th Jun'24 & 20th May’25 the portion of above said constructed line completely damage/washout. Till date most part of the Line is inaccessible after Natural disaster b) 132/66kv Singhik Sub-Station and 132/66kv Chungthang Sub-Station have been declared as abandoned by Powergrid c) The status of balance work before Natural Disaster is as follows: -
80 | Sikkim Tower Pkg TK04 | project_status | A-722/723 | activity_status, supply_status, monthly_plan, issues_support | 2 | 0 | Sikkim Tower Pkg TK04 4. 66 KV S/C Singhik – Mangan Transmission Line a) Line was Physically Completed on 15.03.2024 (except Mangan Side Gantry Connection due to Non availability of 11kv shutdown) b) Due to Natural Disaster i.e. Cloud burst Flash Flood in North Sikkim on 18th Jun'24 & 20th May’25, 2 Nos erected and Strung Tower Location No. M27/0 & M28/0 near Mangan Sub-station is completely collapsed c) Route diversion proposal near Mangan SS area from M26A/0 to M29/0 by incorporating 1 No 132 KV High Extension Tower is under approval at PG RHQ Kolkata. 2 Nos Foundation, 2 Nos collapsed Erected Tower i.e M27/0 & M28/0 will be abandon in Proposed Route d) The status of balance work before Natural Disaster is as follows:
81 | Sikkim Tower Pkg TK04 | project_status | A-722/723 | activity_status, supply_status, issues_support | 1 | 0 | Sikkim Tower Pkg TK04 5. LILO of 66 kV Rabon - Maltin line at Chungthag e) 132/66kv Singhik Sub-Station have been declared as abandoned by Powergrid resulting 1 No Erected & Strung Tower Location near Singhik SS end i.e. AP- D/E(M TL) (SD+0) has also been abandoned a) Line was Physically Completed on 31.01.2022 (except Chungthang SS Gantry Connection due to Non readiness of Chungthang Gantry and LILO connection due to non-availability of shutdown of 66 KV Existing Rabon – Malting Line) b) Due to Natural Disaster i.e. Teesta GLOF Flood on 04.10.2023 the Line is inaccessible after Natural disaster c) 132/66kv Chungthang Sub-Station has been declared as abandoned by Powergrid d) The status of balance work before Natural Disaster is as follows: - e) De-scope of line by PGCIL after Sikkim Flood on dtd 04/10/2023 vide their letter reference No. ER-II/CSSTDS/GTK/TK-04/1766 dated 08/05/2024
82 | Sikkim Tower Pkg TK04 | project_status | A-722/723 | activity_status, supply_status, monthly_plan | 1 | 0 | Sikkim Tower Pkg TK04 6. 66 KV D/C Singhik – Passidong Transmission Line a) Line was Physically completed on 31/12/2021 (Except Passingdong S/stn Gantry connection due to non-readiness of Passidong Gantry) b) Due to Natural Disaster i.e. Cloud burst Flash Flood in North Sikkim on 18th Jun'24 & 20th May’25 3 Nos Erected and Strung Tower Location No. AP 1B/0 (DD+0), AP 1D/0 (DD+0) & AP 2/0 (DC+0) fully collapsed c) The partial completed 132/66kv Singhik Sub-station has been abandoned by Powergrid due to rapid sinking of entire 132/66kv Singhik Sub-Station Land d) Based on abandonment of Singhik Sub-Station the 22 Nos Erected and Strung Tower Location from AP- DE(PTL) to AP 19/0 may yet to be abandoned i.e. 3.225 KM Line Length will be abandoned against Total Line Length of 4.357 KM e) The status of balance work before Natural Disaster is as follows: - 7. LILO of one circuit of 220 KV D/C Dikchu – Singhik Trans. Line at Sneha Kinetic HEP at Dikchu a) De-scope of line by PGCIL after Sikkim Flood on dtd 04/10/2023 vide their letter reference No. ER-II/CSSTDS/GTK/TK-04/1766 dated 08/05/2024
83 | Commercial Closures and Pending Claims | commercial |  | commercial_claims | 0 | 0 | Commercial Closures and Pending Claims
84 | Summary of Claims submitted at PGCIL(Region Wise) | commercial |  | project_contract_header, supply_status, monthly_plan, issues_support, commercial_claims | 2 | 0 | Summary of Claims submitted at PGCIL(Region Wise)
85 | Pending Claims (ER-II) | commercial |  | project_contract_header, activity_status, supply_status, monthly_plan, commercial_claims | 1 | 0 | Pending Claims (ER-II)
86 | Pending Claims (NR) | commercial |  | project_contract_header, activity_status, supply_status, monthly_plan, commercial_claims | 1 | 0 | Pending Claims (NR)
87 | Pending Claims (Rajasthan Region) | commercial |  | project_contract_header, activity_status, monthly_plan, commercial_claims | 1 | 0 | Pending Claims (Rajasthan Region)
88 | Pending Claims (WR-II) (Cont..) | commercial |  | project_contract_header, activity_status, monthly_plan, commercial_claims, pending_amendments | 1 | 0 | Pending Claims (WR-II) (Cont..)
89 | Pending Claims (WR-II) | commercial |  | project_contract_header, activity_status, monthly_plan, issues_support, commercial_claims | 1 | 0 | Pending Claims (WR-II)
90 | Pending Claims(SR-I and NR-I) | commercial |  | project_contract_header, activity_status, monthly_plan, issues_support, commercial_claims | 1 | 0 | Pending Claims(SR-I and NR-I)
91 | Pending L2 Revision | divider |  | activity_status, commercial_claims | 1 | 0 | Pending L2 Revision
92 | Financial details(Closure Projects) | commercial | TA 119, TA 121, TA 122, TA 123, TA 124, TA 310, TA 325, TA 405 | commercial_claims | 1 | 0 | Financial details(Closure Projects) Total Outstanding 440 Cr : BGs 245 Cr
93 | Commercial closure/ Claims and Intervention sought | commercial |  | issues_support, commercial_claims, pending_amendments | 0 | 0 | Commercial closure/ Claims and Intervention sought Region - Rajasthan and NR 1 Bhadla Sikar Tw 01 - FTE and FA issued. Final Invoice to be processed, Due drawn under Signing Bhadla Sikar Tw 02 – FA and FTE issued. Final Invoice to be processed. Due drawn Signed Bhadla Sikar Tw 03 - FA and FTE issued. Final Invoice to be processed and SAP uploading required Sikar Neemarana Tw 04 – FTE and FA issuance pending. Bikaner SS/Bhiwadi SS/Khetri SS – FA and FTE issued, Final Invoice to be processed, At Faridabad Narela SS – FA issued, FTE to be processed Issuance of TOC for Bhadla 3 SS which was charged on 2nd March’26 and TOC request was submitted on 5th March’26. Cost Compensation Claims JSEB – Finalization of Claim and L2, approx. 77 Cr (Work started but claim not settled till date).ROW and Forest clearance pending. PGCIL-To initiate L2 Amendment and Time over run claim to BGCL Board as this is holding supply of materials. TK – 01 Sikkim – prolongation Claim with CC Gurgaon, 6.74 Cr TK – 04 Sikkim – prolongation Claim with CC Gurgaon, 7 Cr TK – 04 Sikkim 2 – prolongation Claim with Site , 9 Cr TBCB Rajasthan - project delays Claim at Region level , 90 Cr Expediting Cost of Neemuch Chittorgarh T/L and release of CPBG – pending with NR1 BG Release for Banaskantha Chittorgarh project – Pending with NR1
94 | Project Closure Status(Rajasthan) | commercial | TA 120, TA 121, TA 122, TA 123, TA 124, TA 405 | issues_support, commercial_claims | 1 | 0 | Project Closure Status(Rajasthan)
95 | Thank You | divider |  |  | 0 | 0 | Thank You

## PPT Table Raw
slide | slide_title | table_no | row_no | col_1 | col_2 | col_3 | col_4 | col_5 | col_6 | col_7 | col_8 | col_9 | col_10 | col_11 | col_12 | col_13 | col_14 | col_15 | col_16 | col_17 | col_18 | col_19 | col_20 | col_21 | col_22 | col_23
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 1 | Sl. No. | Project Name | Scheduled Completion | Expected Completion
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 2 | 1 | 765KV D/C Bikaner III - Neemrana II (TA – 413) | 11/12/25 | 30/07/26
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 3 | 2 | 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 11/12/25 | 30/10/26
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 4 | 3 | 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 06/11/25 | 31/05/26
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 5 | 4 | 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 11/12/25 | 30/06/26
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 6 | 5 | 765KV D/C Sikar II – Narela (TA- 419) | 05/05/25 | 30/11/26
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 7 | 6 | 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 14/11/25 | May’26
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 8 | 7 | 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 22/06/26 | 28/09/26
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 9 | 8 | 765KV D/C Beawar-Mandsaur TL (TA- 505) | 21/06/26 | 30/09/26
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 10 | 9 | 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | Aug’26 | Oct’26
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 11 | 10 | 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 25/10/26 | 25/10/26
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 12 | 11 | 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 25/10/26 | 15/03/27
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 13 | 12 | 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 02/12/26 | 02/12/26
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 14 | 13 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 22/12/26 | --
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 15 | 14 | 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 22/07/28 | 22/07/28
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 16 | 15 | 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 11/08/28 | 11/08/28
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 17 | 16 | 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 12/04/27 | 12/04/27
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 18 | 17 | 80800 KV HVDC KPS-II to Nagpur (TA- 602) | 12/11/28 | 12/09/28
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 19 | 18 | 132 KV D/C Tawang-Lumla Line (A920) | 12/04/27 | 12/04/27
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 20 | 19 | 400 KV D/C Twin Line Latehar- Patraru (A303/304) | -- | --
3 | Summary of Projects under Execution by KEC (TL Projects) | 1 | 21 | 20 | Sikkim Tower Pkg TK04 (A-722/723) | -- | --
4 | Summary of projects under Execution by KEC (SS Projects) | 1 | 1 | Sl. No. | Project Name | Scheduled Completion | Expected Completion
4 | Summary of projects under Execution by KEC (SS Projects) | 1 | 2 | 1 | SA52C-SS118 220kV Bay Ext Raigarh GIS Sub-Sation (SA – 52C) | 24/05/26 | May’26
4 | Summary of projects under Execution by KEC (SS Projects) | 1 | 3 | 2 | 765/400 kV KPS-2 Ext 39T (SA – 503) | Mar’26 | 400KV- Jun’26, 765KV- Jul’26
4 | Summary of projects under Execution by KEC (SS Projects) | 1 | 4 | 3 | SS33T 765kV GIS South Olpad (SA – 508) | 25/10/26 | Depends on land
4 | Summary of projects under Execution by KEC (SS Projects) | 1 | 5 | 4 | SS33T 765kV AIS Ahmedabad Extn (SA – 5A8) | 25/10/26 | 30/09/26
4 | Summary of projects under Execution by KEC (SS Projects) | 1 | 6 | 5 | SS33T 765kV GIS Vadodara Extn S/S (SA – 5V8) | 25/10/26 | 25/10/26
4 | Summary of projects under Execution by KEC (SS Projects) | 1 | 7 | 6 | SS64T 765kV GIS Narendra Extn (SA – 603) | 12/04/27 | 31/12/26
4 | Summary of projects under Execution by KEC (SS Projects) | 1 | 8 | 7 | 765KV Bay Extension GIS Sub-Station Narela (SA-417) | 21/05/25 | 30/06/26
5 | Priority Projects to be completed | 1 | 1 | S No | Project Name | Type of Project | Estimated Completion
5 | Priority Projects to be completed | 1 | 2 | 1 | 765/400 KV KPS3 Bay Extn (SA-52G) | SS | Charged
5 | Priority Projects to be completed | 1 | 3 | 2 | Narendra Bay Extension SS( 07 T)(SA-420)- Ready for charging | SS | Apr’26
5 | Priority Projects to be completed | 1 | 4 | 3 | 220 KV Raigarh Bay Extn (SA- 52 C) | SS | May’26
5 | Priority Projects to be completed | 1 | 5 | 4 | 765/400 KV Phadge Bay Extn (SA- 52 M) | SS | May’26
5 | Priority Projects to be completed | 1 | 6 | 5 | 765 KV D/C Bidar Maheshwaram (TA-421) | T/L | May’26
5 | Priority Projects to be completed | 1 | 7 | 6 | 765 KV DC Neemrana Bareilly (TA-416) | T/L | May’26
5 | Priority Projects to be completed | 1 | 8 | 7 | 765 /400 KV KPS-II Extension (SA- 503) | SS | 400 KV-May’26
5 | Priority Projects to be completed | 1 | 9 | 8 | 765 KV Narela Bay Extn (SA- 417) | SS | Jun’26
5 | Priority Projects to be completed | 1 | 10 | 9 | 765 KV DC Koppal Raichur TL (TA-418) | T/L | Jun’26
5 | Priority Projects to be completed | 1 | 11 | 10 | 765 KV DC Bikaner Neemrana TL (TA-413) | T/L | July’26
5 | Priority Projects to be completed | 1 | 12 | 11 | 765 KV Bay Extn (16 T)at Navsari for Vataman Line(SA-422) | SS | July’26
7 | Pending Amendments | 1 | 1 | S No | Project Name(SS/ TL) | Type of Project | Pending Since | Achievement Since Last Discussion
7 | Pending Amendments | 1 | 2 | 1 | 400 KV D/C Sirohi Chittorgarh TL (TA-506) | TL | Jun’25
7 | Pending Amendments | 1 | 3 | 2 | 765 KV Ahmedabad- Navsari TL(TA-325) | TL | Sept’25
7 | Pending Amendments | 1 | 4 | 3 | 765KV Bikaner 3 – Neemrana 2 TL(TA-413) | TL |  | Issued on 14th May’26
7 | Pending Amendments | 1 | 5 | 4 | 765kV/400 KV Bhadla 3 SS | SS | Nov’25
7 | Pending Amendments | 1 | 6 | 5 | 765 KV Bidar Maheswaram TL(TA-421) | TL | Feb’26
7 | Pending Amendments | 1 | 7 | 6 | 765 KV Bikaner Siwani TL (TA- 512) | TL | Feb’26
7 | Pending Amendments | 1 | 8 | 7 | 765/400 kV Ramgarh SS (Amendment VI) | SS | Feb’26
7 | Pending Amendments | 1 | 9 | 8 | 765 KV D/C Rishabhdeo – Mandsaur | TL | Apr’26
8 | List of Running Substation & TL Project (Cont..) | 1 | 1 | Sl. No. | Project Code | Region | Project Details | TL/SS | Project Value (Crs) | UEOB As on 1st May'26 (Crs)
8 | List of Running Substation & TL Project (Cont..) | 1 | 2 | 1 | A-303/304 | ER1 | JSEB Lines | TL | 249 | 10
8 | List of Running Substation & TL Project (Cont..) | 1 | 3 | 2 | A-722/723 | ER2 | Sikkim Tower PKg TK-04 | TL | 360 | 32
8 | List of Running Substation & TL Project (Cont..) | 1 | 4 | 3 | A920 | NER | 132 KV D/C Tawang -Lumla Line | TL | 90 | 7
8 | List of Running Substation & TL Project (Cont..) | 1 | 5 | 4 | SA-417 | NR1 | 765kV Narela GIS Extension - SS02 | SS | 123 | 5
8 | List of Running Substation & TL Project (Cont..) | 1 | 6 | 5 | TA-419 | NR1 | 765 kV D/C Sikar II to Narela TL- TL02 | TL | 491 | 51
8 | List of Running Substation & TL Project (Cont..) | 1 | 7 | 6 | TA-513 | NR2 | 400 kv D/C Siwani - Patran, part 3 | TL | 665 | 233
8 | List of Running Substation & TL Project (Cont..) | 1 | 8 | 7 | TA-416 | NR3 | 765 kV D/C Neemrana-II-Bareilly , TL03 | TL | 447 | 2
8 | List of Running Substation & TL Project (Cont..) | 1 | 9 | 8 | SA-410 | NWR | 765/400/220 kV Bhadla SS & Sikar extn. | SS | 223 | 19
8 | List of Running Substation & TL Project (Cont..) | 1 | 10 | 9 | TA-413 | NWR | 765 kV D/C Bikaner-III-Neemrana-II, TL02 | TL | 396 | 9
8 | List of Running Substation & TL Project (Cont..) | 1 | 11 | 10 | TA-504 | NWR | 765 KV D/C Rishabdeo – Mandsaur Line (Part I) & LILO | TL | 255 | 31
8 | List of Running Substation & TL Project (Cont..) | 1 | 12 | 11 | TA-505 | NWR | 765 KV D/C Beowar-Mandsaur TL | TL | 561 | 48
8 | List of Running Substation & TL Project (Cont..) | 1 | 13 | 12 | TA-506 | NWR | 400 KV D/C Sirohi – Chittorgarh Transmission Line | TL | 592 | 38
8 | List of Running Substation & TL Project (Cont..) | 1 | 14 | 13 | TA-512 | NWR | 765 KV D/C Bikaner Siwani | TL | 474 | 84
8 | List of Running Substation & TL Project (Cont..) | 1 | 15 | 14 | SA-420 | SR1 | 765kV Narendra GIS Extn - SS07T | SS | 164 | 6
9 | List of Running Substation & TL Project | 1 | 1 | Sl. No. | Project Code | Region | Project Details | TL/SS | Project Value (Crs) | UEOB As on 1st May'26 (Crs)
9 | List of Running Substation & TL Project | 1 | 2 | 15 | SA-603 | SR1 | 765kV New Narendra GIS extn. Pkg-SS-64T | SS | 98 | 79
9 | List of Running Substation & TL Project | 1 | 3 | 16 | TA-418 | SR1 | 765 KV D/C Kopal 2 - Raichur, TL01 | TL | 154 | 5
9 | List of Running Substation & TL Project | 1 | 4 | 17 | TA-421 | SR1 | 765kV D/C Bidar PS - Maheshwaram | TL | 382 | 4
9 | List of Running Substation & TL Project | 1 | 5 | 18 | TA-601 | SR1 | 765 KV D/C Kurnool IV - Bidar Line | TL | 515 | 178
9 | List of Running Substation & TL Project | 1 | 6 | 19 | SA-502 | WR1/WR2 | SS-118 (Extension of 765/400kV Maheshwaram, 765/400 KPS3, 765/400 Phadge & 220kV Raigarh GIS | SS | 413 | 59
9 | List of Running Substation & TL Project | 1 | 7 | 20 | SA-503 | WR2 | SS-39T - (Extn of 765/400kV KPS-2 GIS) | SS | 390 | 27
9 | List of Running Substation & TL Project | 1 | 8 | 21 | SA-508 | WR2 | SS-33T1) 765kV South Olpad GIS2) Extn. Of 765kV Vadodara GIS3) Extn. Of 765kV Ahmedabad SS | SS | 627 | 250
9 | List of Running Substation & TL Project | 1 | 9 | 22 | TA-414 | WR2 | 765 kV D/C Vataman Navsari Line | TL | 656 | 87
9 | List of Running Substation & TL Project | 1 | 10 | 23 | TA-509 | WR2 | 765 kV D/C Mandsaur - Korawar | TL | 473 | 68
9 | List of Running Substation & TL Project | 1 | 11 | 24 | TA-510 | WR2 | 765 kV D/C South Olpad - Ahmedabad | TL | 577 | 192
9 | List of Running Substation & TL Project | 1 | 12 | 25 | TA-514 | WR2 | 800 KV HVDC TL-02 KPS III Khavda - Nagpur | TL | 780 | 533
9 | List of Running Substation & TL Project | 1 | 13 | 26 | TA-515 | WR2 | 800 KV HVDC TL-03 KPS III Khavda - Nagpur | TL | 348 | 206
9 | List of Running Substation & TL Project | 1 | 14 | 27 | TA-602 | WR2 | 800 KV HVDC TL06 KPS-III Khavda to Nagpur | TL | 612 | 436
9 | List of Running Substation & TL Project | 1 | 15 | Total Amount in Crs |  |  |  |  | 11115 | 2698
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 1 | 1 | LOA DATE: 12/03/2024 | LOA Value in Cr.:- 632 | CONTRACTUAL COMPLETION: 11/12/25 | PLANNED COMPLETION: 30/10/26
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 1 | Front Availability Status
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 4 | Foundation | No | 54 | 54 | 20 | 30 | 30 | 12 | 24 | 24 | 12
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 5 | Tower Erection | No | 45 | 45 | 21 | 50 | 50 | 23 | 50 | 50 | 22
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 6 | Stringing | Km
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 1 | Activity |  | UoM |  | As Per LOA (Qty) |  | Revised |  | As per L2 (April'26) |  | Completed till 30.04.26 |  | Balance As on 01.05.26 |  | Front Availability |  | Gangs Available |  | Plan May-26 |  | Plan Jun-26 | Plan Jul-26 | Remarks
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 2 | [18 empty] | Plan | Act
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 3 | Check Survey |  | Km |  | 128.28 |  | 127.799 |  | 128.28 |  | 127.799 |  | - | [9 empty] | 8 Locations are on hold due to Gopin Industries
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 4 | Foundation |  | No |  | 340 |  | 352 |  | 340 |  | 304 |  | 48 |  | 2 |  | 9 |  | 34 | 8 | 14 | -
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 5 | Erection |  | No |  | 340 |  | 352 |  | 340 |  | 207 |  | 145 |  | 15 |  | 14 |  | 55 | 13 | 52 | 25
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 6 | Stringing |  | Km |  | 128.28 |  | 127.799 |  | 128.28 |  | 10 |  | 117.95 |  | 10 |  | 5 |  | 20 | 3 | 22 | 16
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 7 | OPGW Stringing |  | Km |  | 128.28 |  | 127.799 |  | 128.28 |  | 0 |  | 128.28 |  | 10.3 | [5 empty] | 10 | 5
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 8 | Supply Status:
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 9 | Item | UoM | As Per LOA (Qty) | As Per LOA (Qty) | As Per LOA (Qty) | Revised | Revised | As per L2 | As per L2 | Actual Supplied | Balance | Balance | Plan for May'26 | Plan for May'26 | Plan for Jun'26 | Plan for Jul'26 |  | Remarks | Remarks
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 10 | [5 empty] | (Qty) | (Qty) | (April'26) | (April'26)
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 11 | Stub | Nos | 340 | 340 | 340 | 352 | 352 | 352 | 352 | 347.5 | 11 | 4.5 | 7 | 7 | 3 | - |  | Total 12.5 sets stubs required; where 8 sets were excess/1 Nos Clearnce pending | Total 12.5 sets stubs required; where 8 sets were excess/1 Nos Clearnce pending
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 12 | Tower | Nos | 340 | 340 | 340 | 352 | 352 | 352 | 352 | 341 | 10 | 11 | 4 | 4 | - | 2 |  | 14 Towers balance to supply; DB Type 3 tower excess/ 4 Nos Hold , 2 Nos Plan Jul | 12 Towers balance to supply; DB Type 3 tower excess/ 4 Nos Hold , 2 Nos Plan Jul
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 13 | Conductor | Km | 4664 | 4664 | 4664 | 4647 | 4647 | 4664 | 4664 | 4657 | -10 | -10 | [5 empty] | 10 kms Conductor excess supplied due to route diversion | 10 kms Conductor excess supplied due to route diversion
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 14 | Earthwire | Km | 130 | 130 | 130 | 134 | 134 | 130 | 130 | 130 | 4 | 4 |  |  |  | 4 |  | Qty Confirmation awaited from client. | QCS pending –due to additional earthing /After finalization of location from client
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 15 | 160KN CLR | Nos | 5528 | 5528 | 5528 | 5356 | 5356 | 5528 | 5528 | 4364 | 992 | 992 |  |  |  | 992 |  | Pending due to Amendment from client | Cost proposal approval from PCH awaited
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 16 | 210KN CLR | Nos | 15888 | 15888 | 15888 | 16320 | 16320 | 15888 | 15888 | 15121 | 1199 | 1199 |  |  |  | 1199 |  |  | QCS to be released after amendment ,Cost proposal approval from PCH awaited
11 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 3 | 17 | HW Fittings | % | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 90 | 10 | 10 |  |  |  | 10 |  |  | Cost proposal approval from PCH awaited
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 1 | 1 | LOA DATE: 12/03/2024 | LOA Value in Cr.:- 632 | CONTRACTUAL COMPLETION: 11/12/25 | PLANNED COMPLETION: 30/10/26
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 1 | No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 2 | Activity
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 3 | Foundation | As per L2 | Nos | 340 | 340
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 4 |  | Completion Plan | Nos | 352 | 304 | 14 | 48 | 34 | 14
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 5 |  | Front Required from POWERGRID | Nos |  |  |  |  | 40 | 8
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 6 |  | Gangs Planned | Nos |  |  | 10 |  | 10 | 8
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 7 |  | Stubs Supply as per L2 | Nos |  |  |  |  | 8
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 8 |  | Stub Supply Actual | Nos
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 9
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 10 | Erection | As per L2 | Nos | 340 | 340
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 11 |  | Completion Plan | Nos | 352 | 207 | 35 | 145 | 55 | 52 | 25 | 13
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 12 |  | Front Required from POWERGRID | Nos |  |  |  |  | 65 | 60 | 20
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 13 |  | Gangs Planned | Nos |  |  |  |  | 20 | 20 | 15 | 8
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 14 |  | Tower Supply as per L2 | Nos
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 15 |  | Tower Supply Actual | Nos
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 16
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 17 | Stringing | As per L2 | Kms | 128.28
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 18 |  | Completion Plan | Kms | 128 | 10 | 10 | 118 | 20 | 22 | 16 | 15 | 20 | 25
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 19 |  | Front Required from POWERGRID | Kms
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 20 |  | Gangs Planned | TSE (Nos) |  |  | 2 |  | 2 | 2 | 2 |  | 2 | 3
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 21 |  |  | Manual(Nos) |  |  | 3 |  | 4 | 4 | 4 |  | 5 | 6
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 22 |  | Conductor Supply as per L2 | Nos
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 23 |  | Conductor Supply Actual | Nos | 4664 | 4657
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 24 |  | Insulator Supply as per L2 | Nos
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 25 |  | Insulator Supply Actual | Nos | 21416 | 19458
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 26 |  | Hardware Supply as per L2 | %
12 | TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 2 | 27 |  | Hardware Supply Actual | % | 100 | 90
13 | Issues / Support Required | 1 | 1 | LOA DATE: 12/03/2024 | LOA Value in Cr.:- 632 | CONTRACTUAL COMPLETION: 11/12/25 | PLANNED COMPLETION: 30/10/26
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanApril 26 | PlanApril 26 |  |  | PlanMay 26 | PlanJune 26 | Remarks
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 2 | [10 empty] | Plan | Plan | Act | Act
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 3 | Check Survey | Km | 119.43 | 118.386
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 4 | Foundation | No | 306 | 309 | 306 | 258 | 51 | 6 | 6 | 6 | 19 | 19 | 13 | 13 | 25 | 25 | 10 RC locations
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 5 | Erection | No | 306 | 309 | 270 | 180 | 129 | 11 | 13 | 13 | 42 | 42 | 45 | 45 | 45 | 42
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 6 | Stringing | Km | 119.43 | 118.386 | 84 | - | 118.386 | 24 | 1 | 1 | 0 | - | 0 | - | 12 | 12 | Planned in second week of May'2026
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 7 | OPGW Stringing | Km | [8 empty] | 0 | - | 0 | - | - | -
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 8 | Supply Status:
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for Apr'26 | Plan for May'26 |  | Plan for Jun'26 |  | Remarks
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 10 | Stub | Nos | 306 | 309 | 306 | 281 | 27 | 4 | 3 |  | 21 |  | Raised Chimney: Drawings related issue 10 locations
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 11 | Tower | Nos | 306 | 309 | 306 | 293 | 16 | 6 | 54
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 12 | Conductor | Km | 4343 | 4343 | 4343 | 4300 | 43
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 13 | Earthwire | Km | 121 | 121 | 85 | 84 | 37 |  |  |  | 37
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 14 | 160KN CLR | Nos | 5536 | 5536 | 5536 | 5536 | -
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 15 | 210KN CLR | Nos | 8016 | 8016 | 8016 | 7296 | 720
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 1 | 16 | HW Fittings | % | 100 | 100 | 100 | 88 | 12 |  |  |  | 12
14 | TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 2 | 1 | LOA DATE: 26/11/24 | LOA Value in Cr.:- 474.37 | CONTRACTUAL COMPLETION: 25/10/2026 | PLANNED COMPLETION:25/10/2026
15 | Issues / Support Required | 1 | 1 | LOA DATE: 26/11/24 | LOA Value in Cr.:- 474.37 | CONTRACTUAL COMPLETION: 25/10/2026 | PLANNED COMPLETION:25/10/2026
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 1 | 1 | LOA DATE: 26/11/2024 | LOA Value in Cr.: 578.78 | CONTRACTUAL COMPLETION: 25/10/26 | PLANNED COMPLETION: 15/03/27
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) |  | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  | PlanJune 26 | PlanJul 26 | Remarks
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 2 | [11 empty] | Plan | Plan | Act
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 3 | Check Survey | Km | 111.27 | 114.516 | 111.27 | 90.949 | 23.567 |  |  |  |  | 23.567 | 23.57
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 4 | Foundation | No | 293 | 299 | 293 | 72 | 227 |  | 23 | 4 | 4 | 42 | 42 |  | 25 | 25 | Wip-153/0,157B/1,192/8,194/0
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 5 | Erection | No | 293 | 299 | 270 | 29 | 270 |  | 24 | 1 | 1 | 30 | 30 |  | 25 | 20 | Wip-145/3
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 6 | Stringing | Km | 111.27 | 114.516 | 78 | 00 | 114.516 |  | - |  |  | 00 | 00
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 7 | OPGW Stringing | Km | 111.27 | 114.516 | 45 | 00 | 114.516 |  | - |  |  | 00 | 00
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 8 | Supply Status:
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 | Remarks
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 10 | Stub | Nos | 293 | 299 | 293 | 262 | 37 | 10 |  | 7
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 11 | Tower | Nos | 293 | 299 | 293 | 198 | 101 |  |  | 11 |  | 3
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 12 | Conductor | Km | 4046 | 4046 | 4046 | 4044.441 | 1.559 | [5 empty] | Balance to be supply after final Amendment .
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 13 | Earthwire | Km | 112 | 114.516 | 112 | 112.195 | 2.516
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 14 | 160KN CLR | Nos | 5188 | 5188 | 5188 | 3914 | 1274 | - |  | 500 |  | - | QCS Released -500 Nos & 774 is pending to be released
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 15 | 210KN CLR | Nos | 10800 | 10800 | 10800 | 7980 | 2820 | - |  | 500 |  | - | QCS Released -500 Nos & 2320 is pending to be released
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 2 | 16 | HW Fittings | % | 100 | 100 | 100 | 60 | 40 | [5 empty] | Qty confirmation to be given after approval of Check survey.
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 3 | 1 | Front Availability Status
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 3 | 4 | Foundation | No | 6 | 6 | 5 | 4 | 4 | 2 | 8 | 8 | 4
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 3 | 5 | Tower Erection | No | 8 | 8 | 2 | 8 | 8 | 2 | 4 | 4 | 1
16 | TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 3 | 6 | Stringing | Km
17 | Issues / Support Required | 1 | 1 | LOA DATE: 26/11/2024 | LOA Value in Cr.: 578.78 | CONTRACTUAL COMPLETION: 25/10/26 | PLANNED COMPLETION: 15/03/27
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 1 | 1 | LOA DATE: 23/01/25 | LOA Value in Cr.: 269.93 Cr | CONTRACTUAL COMPLETION: 22/07/28 | PLANNED COMPLETION: 22/07/28
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  |  | PlanJune 26 | PlanJul 26 | Remarks
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 2 | [10 empty] | Plan | Plan | Act | Act
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 3 | Check Survey | Km | 140 | 140 | 140 | 140 | - | - | - | - | - | - | - | - | - | - | All Locations under severe ROW
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 4 | Foundation | No | 361 | 374 | 20 | 25 | 349 | 0 | 10 | 10 | 15 | 15 | 1 | 1 | 20 | 12 | Section -16 pending. This is crucial to use administrative support to clear locations.
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 5 | Erection | No | 361 | 374 | 20 | 0 | 374 | 0 | 3 | 3 | 10 | 10 | 0 | 0 | 10 | 15 | Land Compensation and crop compensation not yet finalized by committee (DLVC committee)
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 6 | Stringing | Km | 142 | 142 | 3 | 0 | 142 | 0 | - | - | - | - | - | - | - | 2 | All Locations under severe ROW
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 7 | OPGW Stringing | Km | 142 | 142 | 3 | 0 | 142 | 0 | - | - | - | - | - | - | - | -
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 8 | Supply Status:
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 10 | Stub | Nos | 361 | 374 | 60 | 222 | 152 | - | - |  | - |  | Due to non approval of Amendment & unavailability of drawings & BOM
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 11 | Tower | Nos | 361 | 374 | 80 | 184 | 190 | - | - |  | - |  | Due to non approval of Amendment & unavailability of drawings & BOM
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 12 | Conductor | Km | 2274 | 2295 | 682 | 1588 | 707 | - | - |  | - |  | Suppled as per L2.Bal: Q2,Q3
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 13 | Earthwire | Km | 145 | 145 | 44 | 102 | 43 | - | - |  | - |  | To be supplied as per L2.
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 14 | 160KN CLR | Nos | 1025 | 1025 | 307 | 0 | 60% | 8% | - |  | - |  | 40 % has been released
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 15 | 210KN CLR | Nos | 1390 | 1390 | 417 | 0 | 60% | 8% | - |  | -
18 | TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 2 | 16 | HW Fittings | % | 100% | 100% | 30 | 0 | 100% | 14% | - |  | - |  | 38 % has been released
19 | Issues / Support Required:- | 1 | 1 | LOA DATE: 23/01/25 | LOA Value in Cr.: 269.93 Cr | CONTRACTUAL COMPLETION: 22/07/28 | PLANNED COMPLETION: 22/07/28
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 1 | 1 | LOA DATE: 12/02/25 | LOA Value in Cr.: 349.3 Cr | CONTRACTUAL COMPLETION: 11/08/28 | PLANNED COMPLETION:11/08/28
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | As per L2(April'26) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(Up to 01.05.26) | Balance(As on 01.05.26) | Balance(Up to 01.05.26) | Front Availability |  | Gangs Available | PlanMay 26 | PlanMay 26 | PlanMay 26 | PlanJune 26 | PlanJul 26 | Remarks
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 2 | [15 empty] | Plan | Plan | Act
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 3 | Check Survey | Km | 83.14 | 83.14 | 83.331 | 83.14 | 83.14 | 83.14 | 83.331 | - | - | - | - |  | - | - | - | - | - | - | Check survey done. Report submitted & approval received for 83.331 km (100%). Land Schedule & Tree enumeration report submitted (100%)
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 4 | Foundation | No | 215 | 215 | 217 | 84 | 84 | 84 | 9 | 208 | 208 | 208 | 2 |  | 0 | 15 | 15 | - | 10 | 10 | Since inception completed - 9 location, WIP - 245/2 (Chimney casting Completed in A,B,C,D), 243/2 (Material Shifting & Pit cleaning U/P.)
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 5 | Erection | No | 215 | 215 | 217 | 60 | 60 | 60 | 2 | 215 | 215 | 215 | 0 |  | 1 | 6 | 6 | 0 | 10 | 6 | All Locations are in ROW and no front available.
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 6 | Stringing | Km | 83.14 | 83.14 | 83.331 | 8 | 8 | 8 | - | 83.331 | 83.331 | 83.331 | 0 |  | - | - | - | - | - | -
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 7 | OPGW Stringing | Km | 83.14 | 83.14 | 83.33 | 8 | 8 | 8 | - | 83.331 | 83.331 | 83.331 | 0 |  | - | - | - | - | - | -
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 8 | Supply Status:
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 9 | Item | UoM |  | As Per LOA (Qty) |  | Revised(Qty) |  | As per L2(April'26) |  | Actual Supplied |  | Balance |  | Plan for May'26 | Plan for June'26 | Plan for Jul'26 |  | Remarks
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 10 | Stub | Nos |  | 215 |  | 217 |  | - |  | 139 |  | 78 |  | - | - | - |  | Due to non approval of Amendment & unavailability of drawings & BOM
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 11 | Tower | Nos |  | 215 |  | 217 |  | 40 |  | 112 |  | 105 |  | - | - | - |  | Due to non approval of Amendment & unavailability of drawings & BOM
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 12 | Conductor | Km |  | 1363.5 |  | 1346.62 |  |  |  | 952.08 |  | 394.54 |  | - | - | - |  | Suppled as per L2.Bal: Q2,Q3
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 13 | Earthwire | Km |  | 88 |  | 88 |  | 30 |  | 61 |  | 27 |  | 27 | - | - |  | To be supplied as per L2.
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 14 | 160KN CLR | Nos |  | 537 |  | 537 |  | 181 |  | - |  | 537 |  | - | - | - |  | 39% has been released, balance to be supplied as per L2.
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 15 | 210KN CLR | Nos |  | 550 |  | 550 |  | 185 |  | - |  | 550 |  | - | - | -
20 | TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 2 | 16 | HW Fittings | % |  | 100% |  | 100% |  | 20% |  | - |  | 100% |  | - | - | - |  | 65% has been released, balance to be supplied as per L2.
21 | Issues / Support Required | 1 | 1 | LOA DATE: 12/02/25 | LOA Value in Cr.: 349.3 Cr | CONTRACTUAL COMPLETION: 11/08/28 | PLANNED COMPLETION:11/08/28
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 1 | 1 | LOA DATE: 13/05/2025 | LOA Value in Cr.: 613 | CONTRACTUAL COMPLETION: 12/11/28 | PLANNED COMPLETION: 12/09/28
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  |  | PlanJune 26 | PlanJul 26 | Remarks
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 2 | [10 empty] | Plan | Plan | Act | Act
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 3 | Check Survey | Km | 186 | 185 | 170 | 136 | 50 | - | - | - | 50 | 50 |  |  | - | - | DS Submitted
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 4 | Foundation | No | 494 | 478 | 142 | 136 | 342 | 19 | 6 | 6 | 35 | 35 | - | - | 35 | 20 | WIP-12
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 5 | Erection | No | 494 | 478 | 77 | 11 | 26 | 5 | 5 | 5 | 40 | 40 | - | - | 35 | 30 | 2 No’s More additional gang
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 6 | Stringing | Km | 186 | 185 | 4 | - | 185 | - | - | - | - | - | - | - | - | - | -
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 7 | OPGW Stringing | Km | 186 | 185 | - | - | - | - | - | - | - | - | - | - | - | - | L2 Schedule from Oct’26
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 8 | Supply Status:
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 10 | Stub | Nos | 494 | 478 | 260 | 225 | 253 | 117
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 11 | Tower | Nos | 494 | 478 | 236 | 152 | 326 | 45 | 60
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 12 | Conductor | Km | 3030 | 3030 | 1212 | 1142 | 1888 | 70 |  |  | 500
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 13 | Earthwire | Km | 192 | 192 | 77 | 77 | 115 |  |  |  | 60
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 14 | 160KN CLR | Nos | 1202 | 1202 | 481 | - | 1202 | - | - |  | - |  | Insulator being delayed due to delay in Design/Type Testing
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 15 | 210KN CLR | Nos | 1438 | 1438 | 575 | - | 1438 | - | - |  | - |  | Insulator being delayed due to delay in Design/Type Testing
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 2 | 16 | HW Fittings | % | 100 | 100 | 40 | - | 100
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 3 | 1 | Front Availability Status
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 3 | 4 | Foundation | No | 12 | 12 | 3 | 5 | 5 | 2 | 40 | 22 | 7
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 3 | 5 | Tower Erection | No | 3 | 3 | 2 | 12 | 12 | 2 | 30 | 10 | 5
22 | TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) | 3 | 6 | Stringing | Km | - | - | - | - | - | - | - | - | -
23 | Issues / Support Required | 1 | 1 | LOA DATE: 13/05/2025 | LOA Value in Cr.: 613 | CONTRACTUAL COMPLETION: 12/11/28 | PLANNED COMPLETION: 12/09/28
24 | SS118 220kV Bay Ext Raigarh GIS Sub-Sation (SA52C) | 1 | 1 | LOA Date: 26.06.2024 | LOA Completion Sch: 23-10-2025 | Target Comp Date: 24-05-2026 | Planned Completion: May’26
24 | SS118 220kV Bay Ext Raigarh GIS Sub-Sation (SA52C) | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
24 | SS118 220kV Bay Ext Raigarh GIS Sub-Sation (SA52C) | 2 | 2 | 1 | Drain | RM | 40 | 600 | 600 | 360 | 240 | 60% | WIP | 15-05-2026
24 | SS118 220kV Bay Ext Raigarh GIS Sub-Sation (SA52C) | 2 | 3 | 2 | Gravel Spreading | M2 | 5000 | 4100 | 4100 | 0 | 4100 | 0% |  | 30-05-2026
24 | SS118 220kV Bay Ext Raigarh GIS Sub-Sation (SA52C) | 2 | 4 | 3 | GIS Equipment and GIB Testing | Nos. | 78 | 78 | 78 | 78 | 0 | 100%
24 | SS118 220kV Bay Ext Raigarh GIS Sub-Sation (SA52C) | 2 | 5 | 4 | HV Testing | Lot | 1 | 1 | 1 | 0.9 | 0.1 | 90% | Y Phase Bus -2 Issue Resolution WIP | 15-05-2026
24 | SS118 220kV Bay Ext Raigarh GIS Sub-Sation (SA52C) | 2 | 6 | 5 | Final Testing and commissioning | % | 100 | 100 | 100 | 10 | 90 | 10% | WIP | 24-05-2026
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 1 | 1 | LOA Date: July’24 | LOA Completion Sch: March’26 | Target Comp Date: 400 kV : June/765kV :July | Project Value: 390 Crs.
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 2 | 1 | Stone Column Work | RM | 56512 | 56512 | 56512 | 56512 | - | 100 | Civil Manpower-130 nos. | Completed | Scope yet to be finalized
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 3 | 2 | ICT Foundation | Nos. | 12 | 12 | 12 | 12 | - | 100 |  | Completed
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 4 | 3 | Fire Wall | Nos. | 10 | 10 | 10 | 10 | - | 100 |  | Painting balance
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 5 | 4 | 400kV Tower Foundation | Nos. | 8 | 8 | 8 | 8 | - | 100 |  | Completed
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 6 | 5 | 765kV GIS Building-A | LS | 100% | 100% | 100% | 95% | 5% | 95
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 7 | 5 | 765kV GIS Building-A | LS | 100% | 100% | 100% | 95% | 5% | 95
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 8 | 6 | 400kV GIS Building-B | LS | 100% | 100% | 100% | 97% | 3% | 97
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 9 | 7 | 400kV GIS Building-C | LS | 100% | 100% | 100% | 97% | 3% | 97
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 10 | 8 | 765 kV GIS Building-D | LS | 100% | 100% | 100% | 80% | 20% | 80 |  | 15/05/2026 , Grade Slab WIP
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 11 | 9 | Equipment foundation | Nos. | 307 | 307 | 307 | 248 | 59 | 80
25 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 12 | 10 | Bus duct foundation | Nos. | 215 | 215 | 215 | 105 | 110 | 48 |  | 20/06/2026
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 1 | 1 | LOA Date: July’24 | LOA Completion Sch: March’26 | Target Comp Date: 400 kV : June/765kV :July | Project Value: 390 Crs.
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 2 | 1 | 400kV GIS-B Bay Erection | Nos | 9 | 9 | 9 | 9 | - | 100 | Electrical:85 | Completed
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 3 |  | 400kV GIS-C Bay Erection | Nos. | 6 | 6 | 6 | 6 | - | 100 |  | Completed
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 4 | 2 | 400kV Tower Erection | Nos | 8 | 8 | 8 | 8 | - | 100 |  | Completed
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 5 | 3 | Outdoor Earthing - Main Mat Laying | RM | 4620 | 4620 | 4620 | 1723 | 2897 | 37 |  | 30.06.2026
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 6 | 4 | 400kV Sec 1 :- GIB ( Outside Building) | RM | 1,343 | 1,343 | 1,343 | 950 | 393 | 70 |  | May
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 7 | 5 | 400kV Sec 1 :- GIB Length ( Inside Building) | RM | 50 | 50 | 50 | 50 | - | 100 |  | May
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 8 | 6 | 400kV Sec 1 :- Main Bus ( Outside Building) BHEL TO C Building | RM | 439 | 439 | 439 | - | 439 | 0 |  | May
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 9 | 7 | 400kV Sec 2 :- GIB ( Outside Building) B Buliding | RM | 884 | 884 | 884 |  | 884 | 0 |  | May
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 10 | 8 | 400kV Sec 2 :- GIB ( Inside Building) | RM | 81 | 81 | 81 | 0 | 81 | 0 |  | May
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 11 | 9 | 400kV Sec 2 :- Main Bus ( Outside Building) BHEL to B Building | RM | 451 | 451 | 451 | 0 | 451 | 0 |  | May
26 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 12 | 10 | 400kV Sec 1 C :Cable Laying & Termination:- C building | Runs | 695 | 695 | 695 | 400 | 295 | 58 |  | May
27 | 765/400 kV KPS-2 Ext 39T (SA-503) | 1 | 1 | LOA Date: July’24 | LOA Completion Sch: March’26 | Target Comp Date: 400 kV : June/765kV :July | Project Value: 390 Crs.
27 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
27 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 2 | 1 | 765kV GIS-A Bay Erection | Nos | 4 | 4 | 4 | 0 | 4 | 0 |  | June’26 | To be Commence from 15th may
27 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 3 | 2 | 765kV GIS-D Bay Erection | Nos. | 4 | 4 | 4 | 0 | 4 | 0
27 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 4 | 3 | 765kV Sec 2 A :- GIB ( Outside Building) | RM | 190 | 190 | 190 | 0 | 190 | 0
27 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 5 | 4 | 765kV Sec 2 A :- GIB Length ( Inside Building) | RM | 40 | 40 | 40 | 0 | 40 | 0
27 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 6 | 5 | 765kV Sec 1 D :- GIB ( Outside Building) D Buliding To Adani Building | RM | 825 | 825 | 825 | 0 | 825 | 0
27 | 765/400 kV KPS-2 Ext 39T (SA-503) | 2 | 7 | 6 | 765kV Sec 1 D :- GIB ( Inside Building) | RM | 84 | 84 | 84 | 0 | 84 | 0
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 1 | 1 | LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: 25-10-2026 | Project Value: 198.93cr
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t L2 | %Age w.r.t L2 | Target Completion | Remarks
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 2 | A | Supply
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 3 | 1 | Foundation Bolts | Nos | 796 | 796 | 796 | 796 | 0 | 100%
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 4 | 2 | Tower & Equipment structure | MT | 200.3 | 167 | 167 | 156.8 | 10.2 | 94% | Jun'26 | KEC (Balance -NCT-2 Nos , 765kV LA- 4 Nos)
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 5 | 3 | Earthing Materials | Lot | 100 | 100 | 100 | 65 | 35 | 65% | May'26 | 40mm MS Rod Received, Misc Earthing material required (GI Flat, MS Earthing)
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 6 | 4 | PEB Structure & Puff panels | Lot | 100 | 100 | 100 | 0 | 100 | 0% | May to Jun'26 | PEB: Kirby Building syatems (270MT)Puff Panel: Jindal
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 7 | 5 | EOT Crane | Set | 1 | 1 | 1 | 1 | 0 | 100% |  | Reva
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 8 | 6 | GIS Equipments - Indoor | Set | 29 | 29 | 29 | 29 | 0 | 100% |  | Hyosung
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 9 | 7 | GIS Equipments & GIB | RM | 2000 | 1526 | 1526 | 1526 | 0 | 100% | May'26 | Outdoor GIS Support Structure Supply Expected by May'26
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 10 | 8 | 765kV Outdoor Equipments | Nos | 34 | 34 | 34 | 12 | 22 | 35% | May'26 | CVT - 6nos - GE vernova BPI - Moder Company - 28set
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 11 | 9 | 145/36kV Outdoor Equipments | Nos | 62 | 62 | 62 | 2 | 60 | 3% | Jun’26 | BPI - 145kV - Moder Company - 60nos BPI Pending
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 12 | 10 | Erectiopn Hardware | Set | 35 | 35 | 35 | 30 | 5 | 86% | Jun'26 | Vensun - Clamps & Connector - Drawing approval pending
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 13 | 11 | CRP & SAS | EA | 25 | 25 | 25 | 0 | 25 | 0% | Jul'26 | Compliance WIP
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 14 | 12 | PMU, PLCC, Telecom & VMS | Lot | 100 | 100 | 100 | 50 | 50 | 50% | May'26 | PLCC receievd, Commtel (telecom) & Delcom (VMS), GE vernova (PMU) pending to supply
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 15 | 13 | Power & Control Cable | KM | 54 | 54 | 54 | 0 | 54 | 0% | Jul'26 | KEC - (Power & Control Cable schedule approval pending)
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 16 | 14 | HVAC System | Lot | 1 | 1 | 1 | 1 | 0 | 100%
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 17 | 15 | Fire Fighting system | Lot | 100 | 100 | 100 | 100 | 0 | 100%
28 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 18 | 16 | Illumination System | Lot | 100 | 100 | 100 | 60 | 40 | 60% | May'26 | Insta Power - 50% received at site
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 1 | 1 | LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: 25-10-2026 | Project Value: 198.93cr
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 2 | 1 | Contouring and land development | Cum | 48500 | 46000 | 46000 | 42000 | 4000 | 91% | WIP | 10-05-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 3 | 2 | 765kV Towers | Nos. | 8 | 8 | 8 | 8 | 0 | 100%
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 4 | 3 | 765kV Equipment | Nos. | 35 | 35 | 35 | 35 | 0 | 100%
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 5 | 4 | 145kV Equipments | Nos. | 53 | 53 | 53 | 44 | 9 | 83% | WIP | 10-05-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 6 | 5 | Reactor Foundation | Nos. | 6 | 6 | 6 | 6 | 0 | 100%
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 7 | 6 | Firewall | Nos. | 6 | 6 | 6 | 3 | 3 | 50% | WIP | 30-05-2026 | Precast Panel wip
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 8 | 7 | 765kV GIS Building including PEB erection | Lot | 100 | 100 | 100 | 20 | 80 | 20% | WIP | 10-08-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 9 | 8 | Bus Duct Foundation | Nos | 139 | 139 | 139 | 0 | 139 | 0% | WIP | 30-06-2026 | Drawing submitted approval awaited
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 10 | 9 | Cable Trench | RM | 90 | 485 | 485 | 0 | 485 | 0% | WIP | 10-07-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 11 | 10 | Drain, Road and Other misc civil works | % | 100 | 100 | 60 | 0 | 100 | 0% |  | 30-09-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 12 | 11 | Tower and Equipment structure | Nos | 96 | 96 | 96 | 0 | 96 | 0% | WIP | 30-05-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 13 | 12 | Outdoor Equipment | Nos | 88 | 88 | 88 | 0 | 88 | 0% | WIP | 30-06-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 14 | 13 | Earthing works | % | 100 | 100 | 50 | 0 | 100 | 0% | WIP | 30-07-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 15 | 14 | Illumination system | % | 100 | 100 | 50 | 0 | 100 | 0% |  | 20-08-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 16 | 15 | HVAC System | % | 100 | 100 | 100 | 0 | 100 | 0% |  | 10-08-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 17 | 16 | GIS Equipments and GIB Erection | % | 100 | 100 | 60 | 0 | 100 | 0% |  | 30-09-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 18 | 17 | Cable Laying & Termination | KM | 55 | 55 | 25 | 0 | 55 | 0% |  | 10-10-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 19 | 18 | Fire Protection Syatem | % | 100 | 100 | 30 | 0 | 100 | 0% |  | 15-10-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 20 | 19 | CRP & SAS Erection incl. Integration | % | 100 | 100 | 25 | 0 | 100 | 0% |  | 15-10-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 21 | 20 | PLCC, PMU, Telecom and VMS | % | 100 | 100 | 5 | 0 | 100 | 0% |  | 20-10-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 22 | 21 | Indoor & Outdoor Equipment Testing | % | 100 | 100 | 0 | 0 | 100 | #DIV/0! |  | 20-10-2026
29 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 2 | 23 | 22 | Testing & Commissioning | % | 100 | 100 | 0 | 0 | 100 | #DIV/0! |  | 25-10-2026
30 | SS33T 765kV GIS Vadodara Extn S/S (SA5V8) | 1 | 1 | LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: 25-10-2026 | Project Value: 198.93cr
31 | SS33T 765kV GIS South Olpad (SA-508) | 1 | 1 | LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: Depend on Land | Project Value: 370.1cr
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t L2 | %Age w.r.t L2 | Target Completion | Remarks
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 2 | A | Supply
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 3 | 1 | Foundation Bolts | Nos | 1648 | 1648 | 1648 | 1648 | 0 | 100% |  | 145kV Eqp Drawing required for further order process
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 4 | 2 | Tower & Equipment structure | MT | 732 | 732 | 732 | 36 | 696 | 5% | Jul'26 | KEC - Order placed
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 5 | 3 | Earthing Materials | Lot | 100 | 100 | 100 | 0 | 100 | 0% |  | Order Placed
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 6 | 4 | PEB Structure & Puff panels | Lot | 100 | 100 | 100 | 0 | 100 | 0%
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 7 | 5 | EOT Crane | Set | 1 | 1 | 1 | 1 | 0 | 100%
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 8 | 6 | GIS Equipments - Indoor | Set | 14 | 14 | 14 | 14 | 0 | 100%
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 9 | 6 | GIS Equipments - SF6 Air Bhusing | Nos | 33 | 33 | 33 |  | 33 | 0% | May'26 | Hyosung
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 10 | 7 | GIS Equipments & GIB | RM | 2400 | 1947.96 | 1947.6 |  | 1947.6 | 0% | Jul'26 | Hyosung - GIB & structure supply
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 11 | 8 | 765kV Outdoor Equipments | Nos | 88 | 88 | 88 | 41 | 47 | 47% | Jun'26 | CVT - GE, BPI - Modern
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 12 | 9 | 145/36kV Outdoor Equipments | Nos | 29 | 29 | 29 | 8 | 21 | 28% | Jun'26 | Order placed
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 13 | 10 | Erectiopn Hardware | Lot | 100 | 100 | 100 | 0 | 100 | 0% |  | Drawing approval pending
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 14 | 11 | CRP & SAS | EA | 40 | 40 | 40 | 0 | 40 | 0% | Aug'26 | GE Vernova
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 15 | 12 | PMU, PLCC, Telecom & VMS | Lot | 100 | 100 | 100 | 60 | 40 | 60% | Jun'26 | VMS-Delcom, telecom- Commtel, PMU-GE
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 16 | 13 | LT Transformer | Nos | 2 | 2 | 2 | 2 | 0 | 100%
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 17 | 14 | LT Switchgear | Lot | 1 | 1 | 1 |  | 1 | 0% | Aug'26 | Ultima
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 18 | 15 | Battery & Charger and DG set | EA | 5 | 5 | 5 | 1 | 4 | 20% | Aug'26 | DG set received at site, Battary & charger - Exide
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 19 | 16 | Power & Control Cable | KM | 65 | 65 | 65 | 0 | 65 | 0% | Drawing approval pending | KEC
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 20 | 17 | Air conditioning & HVAC System | Lot | 100 | 100 | 100 | 100 | 0 | 100%
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 21 | 18 | Fire Fighting system | Lot | 100 | 100 | 100 | 0 | 100 | 0% | May'26 | BCFSL
31 | SS33T 765kV GIS South Olpad (SA-508) | 2 | 22 | 19 | Illumination System | Lot | 100 | 100 | 100 | 60 | 40 | 60% | May'26 | Avaids
32 | SS33T 765kV GIS South Olpad (SA-508) | 1 | 1 | LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: Depend on Land | Project Value: 370.1cr
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 1 | 1 | LOA Date: 26.05.2025 | LOA Completion Sch: 12-04-27 | Target Comp Date: 31-12-26 | Project Value: 105.65 cr
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t L2 | %Age w.r.t L2 | Target Completion | Remarks
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 2 | A | Supply
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 3 | 1 | 765kV equipment | EA | 81 | 81 | 81 | 81 | 18 | 87% | Sep’26 | BPI, WT, LA delivered, CVT under manufacturing
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 4 | 2 | 145/36kV equipment | EA | 8 | 8 | 8 |  | 8 | 50% | Sep’'26 | 145kV BPI , NCT , CB under manufacturing
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 5 | 3 | 800kV, 3000/3150 A, 50kA, Single phase, SF6 Gas Insulated Bus Duct (GIB | M | 2150 | 1894 | 2150 |  | 0 | 100% | May’26 | Inspection call is expected by mid May. BBU approval is pending.
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 6 | 4 | Structure | MT | 112 | 201 | 112 |  | 201 | 100% | Aug’26 | Under production, Lot 1 Inspection call by 32 May.
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 7 | 5 | Earthing Materials | KM | 2 | 2 | 2 | 2 | 0 | 100% |  | Delivered to site
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 8 | 6 | Erection Hardware | Lot | 1 | 1 | 1 | 1 | 0.5 | 50% | July’'26 | BBU approval pending , partial material delivered , Clamps & connectors are under manufacturing
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 9 | 7 | Power & Control Cable | KM | 54 | 54 | 54 | 0 |  | 0% | Sep’26 | Power cable is under approval
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 10 | 8 | CRP & SAS | EA | 4 | 4 | 4 | 0 | 4 | 0% | May'26 | Inspection call is expected by mid May.
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 11 | 9 | Fire Fighting System | Lot | 1 | 1 | 1 | 1 | 0 | 100% | April’26 | delivered to site
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 12 | 10 | Illumination System | Lot | 1 | 1 | 1 | 1 | 0 | 100% | April’26 | delivered to site
33 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 13 | 11 | VMS | Lot | 1 | 1 | 1 | 1 | 0 | 100% | April’26 | delivered to site
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 1 | 1 | LOA Date: 26.05.2025 | LOA Completion Sch: 12-04-27 | Target Comp Date: 31-12-26 | Project Value: 105.65 cr
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 2 | 1 | 765kV Tower Foundation | Nos | 8 | 8 | 30-04-2026 | 8 | 0 | 100% |  |  | Completed
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 3 | 2 | Reactor Foundation | Nos | 7 | 7 | 31-05-2026 | 6 | 1 | 86% |  | On Hold by PGCIL
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 4 | 3 | Reactor Unloading Platform | Nos | 7 | 7 | 31-05-2026 | 6 | 1 | 86% |  | On Hold by PGCIL
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 5 | 4 | Rail Cum road | Nos | 7 | 7 | 31-05-2026 | 0 | 7 | 0% | 8 | May'26
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 6 | 5 | Firewall | Nos | 6 | 6 | 31-05-2026 | 0 | 6 | 0% | 8 | May'26
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 7 | 6 | AIS Equipment Foundations | Nos | 70 | 70 | 30-04-2026 | 3 | 67 | 4% | 15 | May'26
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 8 | 7 | GIB Bus Duct | Nos | 130 | 130 | 30-04-2026 | 0 | 130 | 0% | 15 | May'26
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 9 | 8 | LM Tower | Nos | 1 | 1 | 30-04-2026 | 0 | 1 | 0% |  | June'26
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 10 | 9 | Cable trench | Mtrs | 240 | 240 | 30-05-2026 | 80 | 160 | 33% |  | July'26
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 11 | 10 | Common Oil Pit | Nos | 1 | 1 | 28-04-2027 | 0 | 1 | 0% |  | June'26
34 | SS64T 765kV GIS Narendra Extn (SA-603) | 2 | 12 | 11 | Drain & Road | Nos | 1 | 1 | 28-04-2027 |  | 1 | 0% |  | Aug'26
35 | 765KV Bay Extension GIS Sub-Station Narela | 1 | 1 | LOA Date: 22.02.2024 | LOA Completion Sch: 21-05-2025 | Target Comp Date: 30-06-2026 | Project Value: 124.30 cr
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t L2 | %Age w.r.t L2 | Target Completion | Remarks
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 2 | A | Supply
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 3 | 1 | GIS Bay Module | Set | 5 | 5 | 5 | 5 | 0 | 100% | Sep’25 | Completed
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 4 | 2 | GIS Bus Duct | M | 1600 | 1600 | 1600 | 1600 | 0 | 100% | Sep’’25 | Completed
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 5 | 3 | Power & Control cables | Km | 12.8 | 12.8 | 12.8 |  |  |  | May’25 | 8 Pair cables inspection call is for 15.5.26
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 6 | 4 | 765KV OD Equipment | Nos | 33 | 33 | 33 | 22 | 11 | 90% | Aug’25 | Completed
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 7 | 5 | 145KV OD Equipment | Nos | 34 | 34 | 34 | 32 | 2 | 98% |  | Completed
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 8 | 6 | Puff Panel | Sq.m | 2650 | 2250 | 2250 | 2250 | 0 | 100% | July’25 | Completed
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 9 | 7 | Erection Hardware | Lot | 1 | 1 | 1 | 1 | 0 |  | Sep’25 | Completed
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 10 | 8 | VMS | Set | 1 | 1 | 1 | 1 | 0 |  | May’25 | Completed
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 11 | 9 | PMU | Nos |  | 2 | 2 | 2 | 0 |  | April’25 | Completed
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 12 | 10 | Control Cable | Km | 15 | 15 | 15 | 11 | 4 | 96% | April’25 | 14C x 2.5 & 2C x 2.5 Cables are still balanced
35 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 13 | 11 | Power Cable | Km | 12.33 | 12.33 | 12.33 | 1 | 11.33 | 10% | April’25 | Completed
36 | 765KV Bay Extension GIS Sub-Station Narela | 1 | 1 | LOA Date: 22.02.2024 | LOA Completion Sch: 21-05-2025 | Target Comp Date: 30-06-2026 | Project Value: 124.30 cr
36 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
36 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 2 | 1 | Earth mat + Riser | Km | 5.7 | 5.7 | 5.7 | 4.847 | 0.853 | 92% |  | Jun'26 | WIP
36 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 3 | 2 | 765KV Equipment Erection | Nos | 33 | 33 | 33 | 22 | 11 | 88% |  | Jun'26 | WIP
36 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 4 | 3 | 145KV Equipment Erection | Nos | 36 | 36 | 36 | 32 | 4 | 96% |  | Jun'26 | WIP
36 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 5 | 4 | GIB Erection | mtrs | 1600 | 1600 | 1600 | 1573.79 | 26.21 | 91% |  | Jun'26 | WIP
36 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 6 | 5 | Power & Control Cable Laying | % | 100% | 100% | 100% | 60% | 40% | 85% |  | May'26 | WIP
36 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 7 | 6 | Testing and comissioning | Lot | 1 | 1 | 1 | 40% | 60% | 40% |  | Jun'26 | WIP
36 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 8 | 7 | Busduct Structure Erection | Nos | 181 | 181 | 181 | 181 | 0 | 100% |  |  | Completed
36 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 9 | 8 | Indoor GIS Bays | Bays | 5 | 5 | 5 | 5 | 5 | 100% |  |  | Completed
36 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 10 | 9 | Yard Levelling | M2 | 7000 | 7000 | 7000 | 4825 | 2175 | 65% |  | Jun'26 | WIP
36 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 11 | 10 | PEB Erection | Lot | 1 | 1 | 1 | 1 | 0 | 100% |  |  | Completed
36 | 765KV Bay Extension GIS Sub-Station Narela | 2 | 12 | 11 | Outdoor Cable trench | RM | 214.75 | 214.75 | 214.75 | 214.75 | 0 | 100% |  |  | Completed
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 1 | 1 | LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: 30-09-2026 | Project Value: 61.27cr
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t L2 | %Age w.r.t L2 | Target Completion | Remarks
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 2 | A | Supply
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 3 | 1 | 765kV equipment | EA | 45 | 45 | 45 | 39 | 6 | 87% | May'26 | CVT order placed to GE
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 4 | 2 | 145/36kV equipment | EA | 8 | 8 | 8 | 2 | 6 | 25% | Jun'26 | 145kV BPI , NCT - Order placed to Modern complany & SCT
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 5 | 3 | Foundation Bolt | Nos. | 2560 | 2560 | 2560 | 2560 | 0 | 100%
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 6 | 4 | Structure | MT | 536 | 601 | 601 | 596.55 | 4.45 | 99% | May'26 | KEC
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 7 | 5 | Earthing Materials | KM | 4 | 3.25 | 3.25 | 3.25 | 0 | 100%
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 8 | 6 | Erection Hardware | Lot | 1 | 0.57 | 1 | 0.57 | 0.43 | 57% | Jun'26 | Vensun
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 9 | 7 | Isolator | EA | 26 | 28 | 28 | 28 | 0 | 100%
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 10 | 9 | Insulator | EA | 216 | 216 | 216 | 60 | 156 | 28% | Jun'26 | Modern Equipments
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 11 | 10 | Power & Control Cable | KM | 87.6 | 68 | 68 | 0 | 68 | 0% | May'26 to Jun'26 | KEC
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 12 | 11 | CRP & SAS | EA | 18 | 18 | 18 | 0 | 18 | 0% | May'26
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 13 | 12 | Wave Trap | EA | 4 | 4 | 4 | 4 | 0 | 100%
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 14 | 13 | FOTE | Lot | 1 | 1 | 1 | 1 | 0 | 100%
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 15 | 14 | Fire Fighting System | Lot | 1 | 1 | 1 | 1 | 0 | 100%
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 16 | 15 | AC System | Lot | 1 | 1 | 1 | 1 | 0 | 100%
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 17 | 16 | Illumination System | Lot | 1 | 1 | 1 | 0.8 | 0.2 | 80% | May'26 | Avaids / Forus
37 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 18 | 18 | VMS | Lot | 1 | 1 | 1 | 0 | 1 | 0% | May'26 | Delcom
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 1 | 1 | LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: 30-09-2026 | Project Value: 61.27cr
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 1 | Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 2 | 1 | Soil filling | Cum | 45000 | 41000 | 41000 | 38000 | 3000 | 93% | WIP | 10-05-2026
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 3 | 2 | 765kV Towers | Nos. | 20 | 20 | 20 | 20 | 0 | 100%
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 4 | 3 | 765kV Equipment | Nos. | 216 | 216 | 216 | 216 | 0 | 100%
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 5 | 4 | 145kV Equipments | Nos. | 36 | 36 | 36 | 36 | 0 | 100%
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 6 | 5 | Reactor Foundation | Nos. | 6 | 6 | 6 | 6 | 0 | 100%
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 7 | 6 | Firewall | Nos. | 4 | 4 | 4 | 4 | 0 | 100%
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 8 | 7 | SPR Complete | Nos. | 1 | 1 | 1 | 0.85 | 0.15 | 85% | Finishing wip | 10-05-2026
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 9 | 8 | Cable Trench | mtr | 1700 | 700 | 700 | 600 | 100 | 86% | WIP | 15-05-2026
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 10 | 9 | Drains, Road | % | 100 | 100 | 100 | 25 | 75 | 25% | WIP | 30-06-2026
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 11 | 10 | Misc Work (Earth Pit, Pull Pit,Yard PCC, Gravel Spreading, Fencing , etc) | % | 100 | 100 | 100 | 10 | 90 | 10% | WIP | 25-06-2026
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 12 | 11 | 145kV Erection Erection | % | 100 | 100 | 100 | 85 | 15 | 85% | WIP | 20-05-2026
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 13 | 12 | 765kV Outdoor Equipment | % | 100 | 100 | 100 | 35 | 65 | 35% | WIP | 15-06-2026
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 14 | 13 | Illumination system | % | 100 | 100 | 50 | 50 | 50 | 100% | WIP | 30-05-2026
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 15 | 14 | Fire Protection system | % | 100 | 100 | 28 | 0 | 100 | 0% |  | 30-06-2026
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 16 | 15 | Cable Laying & Termination | % | 100 | 100 | 50 | 0 | 100 | 0% |  | 10-07-2026
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 17 | 16 | CRP & SAS Erection incl. Integration | % | 100 | 100 | 10 | 0 | 100 | 0% |  | 15-07-2026
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 18 | 17 | PLCC, PMC, Telecom & VMS | % | 100 | 100 | 0 | 0 | 100 | #DIV/0! |  | 15-07-2026
38 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 2 | 19 | 18 | Testing & Commissioning | % | 100 | 100 | 0 | 0 | 100 | #DIV/0! |  | 31-07-2026
39 | SS33T 765kV AIS Ahmedabad Extn (SA-5A8) | 1 | 1 | LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: 30-09-2026 | Project Value: 61.27cr
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 1 | 1 | LOA DATE: 12/03/24 | LOA Value in Cr.:-390 Cr. | CONTRACTUAL COMPLETION: 11/12/25 | PLANNED COMPLETION: 30/07/26
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  |  | PlanJune 26 | PlanJul 26 | Remarks
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 2 | [10 empty] | Plan | Plan | Act | Act
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 3 | Check Survey | Km | 112.611 | 117.851 |  | 118 | -
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 4 | Foundation | No | 287 | 306 |  | 306 | -
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 5 | Erection | No | 287 | 306 | 1 | 302 | 4 | 1 |  |  | 1 | 1 |  |  | 3
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 6 | Stringing | Km | 112.611 | 117.851 | 18 | 69 | 49 | 25 | 2 | 2 | 18 | 18 | 3 | 3 | 20 | 11
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 7 | OPGW Stringing | Km | 112.611 | 117.851 | 20 | 60 | 58 |  |  | - |  | 10 | 10 | 10 | 20 | 28
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 8 | Supply Status:
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 10 | Stub | Nos | 287 | 306 |  | 306 | -
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 11 | Tower | Nos | 287 | 306 |  | 306 | -
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 12 | Conductor | Km | 4095 | 4285 |  | 4285 | -
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 13 | Earthwire | Km | 114 | 121 |  | 121 | -
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 14 | 160KN CLR | Nos | 5968 | 6084 |  | 6084 | -
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 15 | 210KN CLR | Nos | 4512 | 5760 |  | 5760 | -
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 16 | HW Fittings | % | 100% | 100% |  | 100% | -
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 3 | 1 | Front Availability Status
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 3 | 4 | Foundation | No
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 3 | 5 | Tower Erection | No | 1
41 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 3 | 6 | Stringing | Km | 18 | 4.1 | 2T | 20 | 14.2 | 2T | 11 | 4.9 | 2T+
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 1 | 1 | LOA DATE: 12/03/24 | LOA Value in Cr.:-390 Cr. | CONTRACTUAL COMPLETION: 11/12/25 | PLANNED COMPLETION: 30/07/26
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 1 | No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 2 | Activity
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 3 | Foundation | As per L2 | Nos | 306 | Comp
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 4 |  | Completion Plan | Nos |  | Comp
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 5 |  | Front Required from POWERGRID | Nos |  | Comp
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 6 |  | Gangs Planned | Nos |  | Comp
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 7 |  | Stubs Supply as per L2 | Nos | 306 | Comp
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 8 |  | Stub Supply Actual | Nos | 306 | Comp
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 9
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 10 | Erection | As per L2 | Nos | 306 | 302
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 11 |  | Completion Plan | Nos | 306 | 302 |  | 4 | 1 | 3
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 12 |  | Front Required from POWERGRID | Nos
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 13 |  | Gangs Planned | Nos |  |  |  |  | 1 | 2
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 14 |  | Tower Supply as per L2 | Nos | 306 | 303
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 15 |  | Tower Supply Actual | Nos | 306 | 303 |  |  | 3
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 16
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 17 | Stringing | As per L2 | Kms | 117.851 | 117.851 | -
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 18 |  | Completion Plan | Kms | 117.851 | 68.589 | 4.9 | 49 | 18 | 20 | 11
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 19 |  | Front Required from POWERGRID | Kms |  |  |  |  | 18 | 20 | 11
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 20 |  | Gangs Planned | TSE (Nos) | 37 | 21 |  |  | 2 | 2 | 2
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 21 |  |  | Manual (Nos) | 25 | 3 |  |  | 2 | 2 | 2
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 22 |  | Conductor Supply as per L2 | Nos | 4285 | Comp
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 23 |  | Conductor Supply Actual | Nos | 4285 | Comp
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 24 |  | Insulator Supply as per L2 | Nos | 11844 | Comp
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 25 |  | Insulator Supply Actual | Nos | 11844 | Comp
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 26 |  | Hardware Supply as per L2 | % | 100 | Comp
42 | TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) | 2 | 27 |  | Hardware Supply Actual | % | 100 | Comp
43 | Issues / Support Required | 1 | 1 | LOA DATE: 12/03/24 | LOA Value in Cr.:-390 Cr. | CONTRACTUAL COMPLETION: 11/12/25 | PLANNED COMPLETION: 30/07/26
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 1 | 1 | LOA DATE: 03/01/25 | LOA Value in Cr.: 475.26 (Excluding GST) | CONTRACTUAL COMPLETION: 02/12/26 | PLANNED COMPLETION: 02/12/26
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(Up to 01.05.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 | PlanMay 26 |  | PlanJune 26 | PlanJul 26 | Remarks
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 2 | [11 empty] | Plan | Plan | Act | Act
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 3 | Check Survey | Km | 120.9 | 124.6 | 120.9 | 124.6 | 0 | 0
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 4 | Foundation | No | 315 | 319 | 272 | 301 | 18 | 18 | 1 | 2 | 2 | 17 | 17 | 0 | 0 | 1 |  | WIP-4, ROW-5, Hold-8 & Stub balance-1 Loc
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 5 | Erection | No | 315 | 319 | 210 | 214 | 105 | 105 | 10 | 2 | 2 | 45 | 45 | 1 | 1 | 40 | 20 | 11kv diversion-01 loc, 11kv shutdown req.-9 Loc (29/18, 33/1, 34/4,34/5,36/2,38/1,40/2,40/3,40/4) 33kv shutdown req.-2 Loc (33/1, 36/2)
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 6 | Stringing | Km | 120.9 | 124.6 | 60 | - | 124.6 | 124.6 |  | 0 | - |  |  |  |  | 15.7 | 19.9
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 7 | OPGW Stringing | Km | 120.9 | 124.6 | 10 | - | 124.6 | 124.6 |  | 0 | -
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 8 | Supply Status:
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance |  | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 10 | Stub | Nos | 315 | 319 | 315 | 318 | 1 |  | 1
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 11 | Tower | Nos | 315 | 319 | 315 | 298 | 21 |  | 16 | 5
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 12 | Conductor | Km | 4398 | 4530 | 3525 | 3682.1 | 847.9 |  | 425 | 422.9
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 13 | Earthwire | Km | 122 | 128.6 | 104 | 86 | 42.6 |  |  |  |  | 42.6
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 14 | 160KN CLR | Nos | 6366 | 6394 | 5400 | 0 | 6394 |  | - | 1000 |  | 1000 |  | Insulator being delayed due to delay in Design/Type Testing
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 15 | 210KN CLR | Nos | 5906 | 6146 | 5018 | 0 | 6146 |  | - | 500 |  | 500
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 2 | 16 | HW Fittings | % | 100% | 100% | 85% | 85% | 15% |  |  |  |  | 15%
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 3 | 1 | Front Availability Status
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 3 | 4 | Foundation | No | 3 | 3 | 2 | 3 | 3 | 2 | 7 | 7 | 2
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 3 | 5 | Tower Erection | No | 40 | 40 | 18 | 31 | 31 | 9 | 16 | 16 | 5
44 | TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 3 | 6 | Stringing | Km
45 | Issues / Support Required | 1 | 1 | LOA DATE: 03/01/25 | LOA Value in Cr.: 475.26 (Excluding GST) | CONTRACTUAL COMPLETION: 02/12/26 | PLANNED COMPLETION: 02/12/26
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 1 | 1 | LOA DATE: 23/07/24 | LOA Value in Cr.: 255.49 | CONTRACTUAL COMPLETION: 22/06/26 | PLANNED COMPLETION: 28/09/26
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  |  | PlanJune 26 | PlanJul 26 | Remarks
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 2 | [10 empty] | Plan | Plan | Act | Act
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 3 | Check Survey | Km | 66 | 70 | 66 | 70
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 4 | Foundation | No | 166 | 188 | 166 | 139 | 50 | 4 | 3 | 2 | 25 | 5 | 2 | 2 | 25 | 20 | 12 location need to demolish due to change in route
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 5 | Erection | No | 166 | 188 | 166 | 121 | 67 | 6 | 4 | 4 | 28 | 7 |  |  | 15 | 15 | Required expedite Tower supply.
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 6 | Stringing | Km | 66 | 70 | 66 | 14 | 57 | 22 | 2 | 2 | 13 | 8 |  | 3 | 15 | 21 | Additional T&P required.
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 7 | OPGW Stringing | Km | 66 | 70 | 40 |  | 70 | 42 | 1 |  | 20 |  |  |  | 20 | 30
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 8 | Supply Status:
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 10 | Stub | Nos | 166 | 188 | 166 | 175 | 13 |  | 13 |  |  |  | Due to change in route additional stubs supply plan by June’26
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 11 | Tower | Nos | 166 | 188 | 166 | 165 | 23 |  |  |  | 23 |  | Balance supply pending due to amendment
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 12 | Conductor | Km | 2364 | 2526 | 2364 | 2211 | 315 | 109
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 13 | Earthwire | Km | 58 | 63 | 58 | 42 | 21 |  | 16 |  | 5
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 14 | Insulator | Nos | 7708 | 9432 | 7708 | 423 | 2009 |  |  |  | 285
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 15 | HW Fittings | % | 100 | 100 | 100 | 76 |  |  |  |  | 17
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 3 | 1 | Front Availability Status
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 3 | 4 | Foundation | No | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 3 | 5 | Tower Erection | No | 3 | 3 | 1 | 2 | - | - | 2 | 2 | 1
46 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 3 | 6 | Stringing | Km | 8 | 5 | 1 | 6 | 4 | 2 | 8 | 5 | 1
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 1 | 1 | LOA DATE: 23/07/24 | LOA Value in Cr.: 255.49 | CONTRACTUAL COMPLETION: 22/06/26 | PLANNED COMPLETION: 28/09/26
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 1 | No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 2 | Activity
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 3 | Foundation | As per L2 | Nos | 166 | 166
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 4 |  | Completion Plan | Nos | 188 | 139 | 2 | 50 | 5 | 25 | 20
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 5 |  | Front Required from POWERGRID | Nos | 188 | 139 |  |  | 5 | 25 | 20
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 6 |  | Gangs Planned | Nos |  |  | 2 |  | 2 | 6 | 6
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 7 |  | Stubs Supply as per L2 | Nos | 166 | 166
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 8 |  | Stub Supply Actual | Nos | 188 | 175 |  |  |  | 13
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 9
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 10 | Erection | As per L2 | Nos | 166 | 166
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 11 |  | Completion Plan | Nos | 188 | 121 | 2 | 67 | 15 | 15 | 20 | 17
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 12 |  | Front Required from POWERGRID | Nos | 189 | 121 |  |  | 15 | 15 | 20 | 17
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 13 |  | Gangs Planned | Nos | 6 |  | 1 |  | 3 | 3 | 5 | 5
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 14 |  | Tower Supply as per L2 | Nos | 166 | 166
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 15 |  | Tower Supply Actual | Nos | 188 | 166 |  | 23 |  |  | 23
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 16
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 17 | Stringing | As per L2 | Kms | 66 | 66
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 18 |  | Completion Plan | Kms | 70 | 13 | 5 | 57 | 8 | 15 | 15 | 15 | 4
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 19 |  | Front Required from POWERGRID | Kms |  |  |  |  | 8 | 15 | 21 | 15 | 4
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 20 |  | Gangs Planned | TSE (Nos) |  | 1 | 1 |  | 1 | 2 | 2 | 2
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 21 |  |  | Manual (Nos) |  | 1 | 2 |  |  | 2 | 2 | 4 | 4
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 22 |  | Conductor Supply as per L2 | Nos | 2364
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 23 |  | Conductor Supply Actual | Nos | 2211 |  |  | 109 | 109
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 24 |  | Insulator Supply as per L2 | % | 100 | 90 |  | 10 |  | 10
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 25 |  | Insulator Supply Actual | % | 100 | 90 |  | 10 |  | 10
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 26 |  | Hardware Supply as per L2 | % | 100 | 100
47 | TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 2 | 27 |  | Hardware Supply Actual | % | 100 | 76 |  | 24 |  |  | 24
48 | Issues / Support Required | 1 | 1 | LOA DATE: 23/07/24 | LOA Value in Cr.: 477.03 | CONTRACTUAL COMPLETION: 22/06/26 | PLANNED COMPLETION: 28/09/26
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 1 | 1 | LOA DATE: 22.07.2024 | LOA Value in Cr.: 560 Cr | CONTRACTUAL COMPLETION: 21.06.2026 | PLANNED COMPLETION:30.09.26
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  | PlanJune 26 | PlanJul 26 | Remarks
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 2 | [10 empty] | Plan | Plan | Act
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 3 | Check Survey | Km | 137 | 139.591 |  | 139.591 | 0
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 4 | Foundation | No | 356 | 379 | 356 | 372 | 7 | 2 | 2 | 2 | 7 | 7 |  |  |  | WIP-2, ROW-6
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 5 | Erection | No | 356 | 379 | 356 | 347 | 32 | 10 | 5 | 5 | 14 | 14 | 4 | 5 | 13
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 6 | Stringing | Km | 137 | 139.591 | 126 | 14.006 | 125.585 | 80 | 2 | 2 | 23 | 23 |  | 25 | 30
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 7 | OPGW Stringing | Km | 137 | 139.591 | 120 | 8.52 | 131.071 |  | 1 | 1
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 8 | Supply Status:
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 10 | Stub | Nos | 356 | 379 | 356 | 371 | 8 | [5 empty] | 8 Stubs supply in PGCIL Scope
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 11 | Tower | Nos | 356 | 379 | 356 | 361 | 18 | 4 | 5 |  | 1 |  | 8 Towers supply in PGCIL Scope.
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 12 | Conductor | Km | 4981 | 5075 | 4981 | 4981 | 94 | - | - |  | 94 |  | Amd. Required. Qty confirmation letter received recently.
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 13 | Earthwire | Km | 138 | 139.591 | 138 | 138 | 1.591 | [5 empty] | To supply after receipt of Amendment or Confirmation letter required.
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 14 | 160KN CLR | Nos | 6100 | 6100 | 6100 | 6100 | 0
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 15 | 210KN CLR | Nos | 11434 | 10035 | 11434 | 9412 | 623
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 16 | HW Fittings | % | 100 | 100 | 100 | 95 | 5
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 3 | 1 | Front Availability Status
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 3 | 4 | Foundation | No | 12 | 10 | 3 | 11 | 8 | 2 | 9 | 8 | 2
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 3 | 5 | Tower Erection | No | 25 | 24 | 8 | 25 | 21 | 7 | 31 | 26 | 6
49 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 3 | 6 | Stringing | Km | 40 | 6.55 | 1 | 65 | 6.489 | 2 | 80 | 1 | 2
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 1 | 1 | LOA DATE: 22.07.2024 | LOA Value in Cr.: 560 Cr | CONTRACTUAL COMPLETION: 21.06.2026 | PLANNED COMPLETION: 30.09.26
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 1 | No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 2 | Activity
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 3 | Foundation | As per L2 | Nos | 356 | 356
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 4 |  | Completion Plan | Nos | 379 | 372 | 8 | 7 | 7
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 5 |  | Front Required from POWERGRID | Nos |  |  |  |  | 6
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 6 |  | Gangs Planned | Nos |  |  |  |  | 2
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 7 |  | Stubs Supply as per L2 | Nos |  | 358
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 8 |  | Stub Supply Actual | Nos |  | 371
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 9
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 10 | Erection | As per L2 | Nos | 356 | 356
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 11 |  | Completion Plan | Nos | 379 | 347 | 26 | 32 | 14 | 5 | 13
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 12 |  | Front Required from POWERGRID | Nos |  |  |  |  | 14 | 5 | 13
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 13 |  | Gangs Planned | Nos |  |  | 5 |  | 4 | 2 | 4
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 14 |  | Tower Supply as per L2 | Nos |  | 358
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 15 |  | Tower Supply Actual | Nos |  | 361
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 16
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 17 | Stringing | As per L2 | Kms | 126 | 126
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 18 |  | Completion Plan | Kms | 139.6 | 14.006 | 1 | 126 | 23 | 25 | 30 | 32 | 6
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 19 |  | Front Required from POWERGRID | Kms |  |  |  |  | 23 | 25 | 30 | 32 | 6
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 20 |  | Gangs Planned | TSE (Nos) |  |  |  |  | 2 | 3 | 3 | 3 | 2
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 21 |  |  | Manual (Nos) | [5 empty] | 2 | 2 | 2
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 22 |  | Conductor Supply as per L2 | Nos | 4981 | 4981
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 23 |  | Conductor Supply Actual | Nos |  | 4971
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 24 |  | Insulator Supply as per L2 | Nos | 15524 | 15524
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 25 |  | Insulator Supply Actual | Nos |  | 15512
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 26 |  | Hardware Supply as per L2 | % | 100 | 100
50 | TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) | 2 | 27 |  | Hardware Supply Actual | % |  | 95
51 | Issues / Support Required | 1 | 1 | LOA DATE: 22.07.2024 | LOA Value in Cr.: 560 Cr | CONTRACTUAL COMPLETION: 21.06.2026 | PLANNED COMPLETION: 30.09.26
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 1 | 1 | LOA DATE: 23/07/24 | LOA Value in Cr.: 592 | CONTRACTUAL COMPLETION: Aug’26 | PLANNED COMPLETION: Oct’26
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  |  | PlanJune 26 | PlanJul 26 | Remarks
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 2 | [10 empty] | Plan | Plan | Act | Act
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 3 | Check Survey | Km | 211 | 223 | 211 | 223
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 4 | Foundation | No | 583 | 602 | 583 | 479 | 123 |  | 12 | 12 | 40 | 35 |  | 9 | 30 | 30
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 5 | Erection | No | 583 | 602 | 583 | 400 | 202 |  | 2 | 2 | 46 | 39 |  |  | 35 | 35
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 6 | Stringing | Km | 211 | 223 | 205 | 45 | 178 |  | 4 | 4 | 39 | 30 |  | 13 | 30 | 40
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 7 | OPGW Stringing | Km | 211 | 223 | 198 | 0 | 223 | [7 empty] | 30 | 40
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 8 | Supply Status:
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 10 | Stub | Nos | 583 | 602 | 583 | 572 | 30 | [5 empty] | Balance supply due to PRS balance against hold locations.
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 11 | Tower | Nos | 583 | 602 | 583 | 523 | 79 | 3 | 6 |  |  |  | 20 locs PRS balance due to hold locations.
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 12 | Conductor | Km | 5117 | 5400 | 5117 | 5092 | 308
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 13 | Earthwire | Km | 213 | 225 | 213 | 158 | 67
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 14 | Insulator | Nos | 16174 | 18264 | 16174 | 15288 | 3076
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 15 | HW Fittings | % | 100 | 105 | 100 | 90 | 15
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 3 | 1 | Front Availability Status
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 3 | 4 | Foundation | No | 11 | 11 | 5 | 16 | 16 | 5 | 15 | 15 | 12
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 3 | 5 | Tower Erection | No | 19 | 19 | 5 | 10 | 10 | 3 | 4 | 4 | 2
52 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 3 | 6 | Stringing | Km | 18 | 18 | 2 | 7 | 7 | 2 | 17 | 17 | 4
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 1 | 1 | LOA DATE: 08/04/25 | LOA Value in Cr.: 592 | CONTRACTUAL COMPLETION: Aug’26 | PLANNED COMPLETION: Oct’26
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 1 | No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 2 | Activity
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 3 | Foundation | As per L2 | Nos | 583 | 583
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 4 |  | Completion Plan | Nos | 602 | 479 | 15 | 123 | 35 | 30 | 30 | 15 | 13
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 5 |  | Front Required from POWERGRID | Nos | 602 | 479 | 15 |  | 35 | 30 | 30 | 15 | 13
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 6 |  | Gangs Planned | Nos | 12 | 12 | 9 |  | 12 | 12 | 12 | 10 | 10
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 7 |  | Stubs Supply as per L2 | Nos | 602 | 572
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 8 |  | Stub Supply Actual | Nos | 602 | 572
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 9
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 10 | Erection | As per L2 | Nos | 583
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 11 |  | Completion Plan | Nos | 602 | 400 | 4 | 202 | 39 | 35 | 35 | 35 | 40 | 18
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 12 |  | Front Required from POWERGRID | Nos | 602 | 400 | 4 |  | 39 | 35 | 35 | 35 | 40 | 18
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 13 |  | Gangs Planned | Nos | 7 | 2 | 2 |  | 8 | 12 | 12 | 12 | 12 | 12
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 14 |  | Tower Supply as per L2 | Nos | 583 | 583
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 15 |  | Tower Supply Actual | Nos | 523 | 523 |  |  | 3 | 6
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 16
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 17 | Stringing | As per L2 | Kms | 211 | 205 | 17 | 6 | 6
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 18 |  | Completion Plan | Kms | 223 | 45 | 17 | 178 | 30 | 30 | 30 | 30 | 30 | 28
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 19 |  | Front Required from POWERGRID | Kms | 223 | 45 | 17 |  | 30 | 30 | 30 | 30 | 30 | 28
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 20 |  | Gangs Planned | TSE (Nos) | 3 | 3 |  |  | 2 | 2 | 2 | 2 | 2 | 2
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 21 |  |  | Manual (Nos) | 1 | 3 |  |  | 6 | 10 | 12 | 12 | 12 | 12
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 22 |  | Conductor Supply as per L2 | Nos | 5117
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 23 |  | Conductor Supply Actual | Nos | 5092 |  |  | 25 |  | 25
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 24 |  | Insulator Supply as per L2 | Nos | 16174 |  |  | 886 | 500 | 386
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 25 |  | Insulator Supply Actual | Nos | 15288
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 26 |  | Hardware Supply as per L2 | % | 100
53 | TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | 2 | 27 |  | Hardware Supply Actual | % | 100 | 80 |  | 20 | 10 | 10
54 | Issues / Support Required | 1 | 1 | LOA DATE: 08/04/25 | LOA Value in Cr.: 592 | CONTRACTUAL COMPLETION: Aug’26 | PLANNED COMPLETION: Oct’26
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 1 | 1 | LOA DATE: 06/02/2024 | LOA Value in Cr.: 501 | CONTRACTUAL COMPLETION: 05/05/2025 | PLANNED COMPLETION: 30/11/26
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  | PlanJune 26 | PlanJul 26 | Remarks
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 2 | [10 empty] | Plan | Plan | Act
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 3 | Check Survey | Km | 120 | 122.07
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 4 | Foundation | No | 322 | 330 | 330 | 236 | 94 | 4 | 13 | 13 | 35 | 35 | 3 | 35 | 24
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 5 | Erection | No | 322 | 330 | 330 | 195 | 135 | 2 | 7 | 7 | 30 | 30 | 1 | 40 | 40
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 6 | Stringing | Km | 120 | 122 | 122 | 0 | 122 |  | 1 | 1 | 13 | 13 |  | 15 | 20
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 7 | OPGW Stringing | Km
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 8 | Supply Status:
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 10 | Stub | Nos | 322 | 330 | 330 | 328 | 2 | 0 | 2 |  | 0
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 11 | Tower | Nos | 322 | 330 | 330 | 325 | 5 | 0 | 0 |  | 5 |  | HORCL Approval Pending(Tower Type may change)
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 12 | Conductor | Km | 4370 | 4432 | 4432 | 4369 | 63 |  | 63
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 13 | Earthwire | Km | 121 | 122 | 122 | 119 | 3 |  | 3
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 14 | 160KN CLR | Nos | 4944 | 5575 | 5575 | 4944 | 631 |  | 631
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 15 | 210KN CLR | Nos | 14496 | 12908 | 12908 | 12908
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 16 | HW Fittings | % | 100 | 100 | 100 | 95 | 5 |  | 5
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 3 | 1 | Front Availability Status
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 3 | 4 | Foundation | No | 7 | 7 | 7 | 6 | 6 | 5 | 8 | 8 | 11
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 3 | 5 | Tower Erection | No | 2 | 2 | 2 | 1 | 1 | 1 | 12 | 11 | 7
56 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 3 | 6 | Stringing | Km |  |  | 2T |  |  | 2T | 0 | 0 | 2 T
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 1 | 1 | LOA DATE: 06/02/2024 | LOA Value in Cr.: 501 | CONTRACTUAL COMPLETION: 05/05/2025 | PLANNED COMPLETION: 30/11/26
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 1 | No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 2 | Activity
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 3 | Foundation | As per L2 | Nos | 330 | 330
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 4 |  | Completion Plan | Nos | 330 | 236 | 8 | 94 | 35 | 35 | 24
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 5 |  | Front Required from POWERGRID | Nos |  |  |  |  | 35 | 35 | 24
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 6 |  | Gangs Planned | Nos |  |  |  |  | 20 | 20 | 15
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 7 |  | Stubs Supply as per L2 | Nos | 330 | 330
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 8 |  | Stub Supply Actual | Nos | 330 | 328 |  |  |  | 2
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 9
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 10 | Erection | As per L2 | Nos | 330 | 330
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 11 |  | Completion Plan | Nos | 330 | 195 | 11 | 135 | 30 | 40 | 40 | 25
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 12 |  | Front Required from POWERGRID | Nos |  |  |  |  | 30 | 40 | 40 | 25
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 13 |  | Gangs Planned | Nos |  |  |  |  | 15 | 15 | 15 | 10
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 14 |  | Tower Supply as per L2 | Nos | 330 | 330
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 15 |  | Tower Supply Actual | Nos | 330 | 25 |  |  |  |  | 5
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 16
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 17 | Stringing | As per L2 | Kms | 122 | 122
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 18 |  | Completion Plan | Kms | 122 |  |  | 122 | 13 | 15 | 20 | 20 | 20 | 20 | 14
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 19 |  | Front Required from POWERGRID | Kms |  |  |  |  | 13 | 15 | 20 | 20 | 20 | 20 | 14
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 20 |  | Gangs Planned | TSE (Nos) |  |  |  |  | 2 | 2 | 3 | 3 | 3 | 3 | 3
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 21 |  |  | Manual (Nos) | [5 empty] | 3 | 4 | 4 | 4 | 4 | 4
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 22 |  | Conductor Supply as per L2 | Nos | 4432 | 4432
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 23 |  | Conductor Supply Actual | Nos | 4432 | 4369 |  | 63 |  | 63
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 24 |  | Insulator Supply as per L2 | Nos | 18483 | 18483
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 25 |  | Insulator Supply Actual | Nos | 18483 | 17864 |  | 619 |  | 619
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 26 |  | Hardware Supply as per L2 | % | 100 | 100
57 | TL02 - 765KV D/C Sikar II – Narela (TA- 419) | 2 | 27 |  | Hardware Supply Actual | % | 100 | 95 |  | 5 |  | 5
58 | Issues / Support Required | 1 | 1 | LOA DATE: 06/02/2024 | LOA Value in Cr.: 501 | CONTRACTUAL COMPLETION: 05/05/2025 | PLANNED COMPLETION: 30/11/26
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 1 | 1 | LOA DATE: 22.01.2025 | LOA Value in Cr.: 666 | CONTRACTUAL COMPLETION: 22.12.26 | PLANNED COMPLETION:
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  |  | PlanJune 26 | PlanJul 26 | Remarks
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 2 | [10 empty] | Plan | Plan | Act | Act
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 3 | Check Survey | Km | 222.9 | 230.49 | 222.9 | 230.49 | - |  | 0 |  | 0 |  | 0 |  |  |  | 13.4km Check Survey Approval pending .
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 4 | Foundation | No | 597 | 619 | 517 | 72 | 547 | 8 | 4 | 4 | 20 | 20 | 3 | 3 | 50 | 20 | WIP-04
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 5 | Erection | No | 619 | 619 | 425 | 28 | 591 | 6 | 1 | 1 | 9 | 9 | 0 |  | 28 | 55
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 6 | Stringing | Km | 222.93 | 230.93 | 116 | - | 230.93 |  | 0 |  | 0 |  | 0
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 7 | OPGW Stringing | Km | 222.93 | 230.93 | 20 | - | 230.93 |  | 0 |  | 0 |  | 0
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 8 | Supply Status:
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 10 | Stub | Nos | 597 | 619 | 597 | 513 | 106 | 0 | 25 |  | 81 |  | 42 Nos supply pending to C.Survey & 38 Nos Pending due to crossing NOC , Rest Supply under progress
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 11 | Tower | Nos | 597 | 619 | 490 | 467 | 152 | 45 | 47 |  | 60
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 12
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 13 | Conductor | Km | 5403 | 5531 | 3800 | 4884 | 519 | 495 | 24 |  | 0
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 14 | Earthwire | Km | 230 | 230.49 | 196 | 161 | 69 | 35 | 34 |  | 0
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 15 | 120KN CLR | Nos | 5018 | 5018 | 4266 | 700 | 4318 | 600 | 600 |  | 600
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 16 | 160KN CLR | Nos | 10272 | 10272 | 8550 | 4280 | 5992 | 2400 | 2400 |  | 2400
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 2 | 17 | HW Fittings | % | 100 | 100 | 50% | 50% | 50 | 35 | 0 |  | 15
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 3 | 1 | Front Availability Status
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 3 | 4 | Foundation | No | 2 | 2 | 1 | 1 | 1 | 1 | 10 | 1 | 1
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 3 | 5 | Tower Erection | No | 1 | 1 | 1 | 6 | 6 | 1 | 6 | 1 | 1
60 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 3 | 6 | Stringing | Km
61 | Issues / Support Required | 1 | 1 | LOA DATE: 22.01.2025 | LOA Value in Cr.: 666 | CONTRACTUAL COMPLETION: 22.12.26 | PLANNED COMPLETION:
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 1 | 1 | LOA DATE: 07/02/24 | LOA Value in Cr.: 451 | CONTRACTUAL COMPLETION: 06/11/25 | PLANNED COMPLETION: 31/05/26
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(Up to 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  |  | PlanJune 26 | PlanJul 26 | Remarks
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 2 | [10 empty] | Plan | Plan | Act | Act
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 3 | Check Survey | Km | 115 | 115 | 115 | 115 | -
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 4 | Foundation | No | 303 | 302 | 302 | 302 | -
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 5 | Erection | No | 303 | 302 | 302 | 302 | -
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 6 | Stringing | Km | 115 | 115 | 115 | 107 | 8 | 8 | 2 | 2 | 8 | 8 |  |  |  |  | WIP -3.4 Kms
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 7 | OPGW Stringing | Km | 115 | 115 | 115 | 87 | 28 | 12 | 1 | 1 | 28 | 28 | 5 | 5 |  |  | WIP-4 kms
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 8 | Supply Status:
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 10 | Stub | Nos | 303 | 302 | 302 | 302 | -
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 11 | Tower | Nos | 303 | 302 | 302 | 302 | -
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 12 | Conductor | Km | 4200 | 4183 | 4183 | 4183 | -
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 13 | Earthwire | Km | 116 | 116 | 116 | 116 | -
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 14 | Insulator | Nos | 13540 | 13224 | 13224 | 13224 | -
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 15 | HW Fittings | % | 100 | 100 | 100 | 100 | -
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 3 | 1 | Front Availability Status
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 3 | 4 | Foundation | No
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 3 | 5 | Tower Erection | No | 3 | 1 | 1 | 2 | 2 | 2
63 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 3 | 6 | Stringing | Km | 24 | 6 | 5 | 18 | 6 | 7 | 12 | 3.5 | 6
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 1 | 1 | LOA DATE: 07/02/24 | LOA Value in Cr.: 451 | CONTRACTUAL COMPLETION: 06/11/25 | PLANNED COMPLETION: 31/05/26
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 1 | No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 2 | Activity
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 3 | Foundation | As per L2 | Nos | 303 | 302
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 4 |  | Completion Plan | Nos | 302 | 302
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 5 |  | Front Required from POWERGRID | Nos | 302 | 302
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 6 |  | Gangs Planned | Nos
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 7 |  | Stubs Supply as per L2 | Nos | 303 | 303
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 8 |  | Stub Supply Actual | Nos | 302 | 302
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 9
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 10 | Erection | As per L2 | Nos | 303 | 302
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 11 |  | Completion Plan | Nos | 302 | 302
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 12 |  | Front Required from POWERGRID | Nos | 302 | 302
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 13 |  | Gangs Planned | Nos
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 14 |  | Tower Supply as per L2 | Nos | 303 | 303
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 15 |  | Tower Supply Actual | Nos | 302 | 302
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 16
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 17 | Stringing | As per L2 | Kms | 116 | 116
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 18 |  | Completion Plan | Kms | 115 | 107 | 3.5 | 8 | 8
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 19 |  | Front Required from POWERGRID | Kms | 115 | 115
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 20 |  | Gangs Planned | TSE (Nos) | 40 | 36 | 3 |  | 4
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 21 |  |  | Manual (Nos) | 37 | 29 | 1 |  | 8
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 22 |  | Conductor Supply as per L2 | Nos | 4200 | 4200
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 23 |  | Conductor Supply Actual | Nos | 4186 | 4183
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 24 |  | Insulator Supply as per L2 | Nos | 13540 | 13540
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 25 |  | Insulator Supply Actual | % | 13224 | 13224
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 26 |  | Hardware Supply as per L2 | % | 100 | 100
64 | TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 2 | 27 |  | Hardware Supply Actual | % | 100 | 100
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay’ 26 | PlanMay’ 26 |  | PlanJun’26 | PlanJul’26 | Remarks
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 2 | [10 empty] | Plan | Plan | Act
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 3 | Check Survey | Km | 45.72 | 47.84 | 47.84 | 47.84 | - |  | 0 |  | 0
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 4 | Foundation | No | 121 | 127 | 127 | 127 | - |  | 0 |  | 0
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 5 | Erection | No | 121 | 127 | 127 | 127 | - |  | 0 |  | 0
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 6 | Stringing | Km | 45.72 | 47.84 | 47.84 | 22.17 | 25.17 | 1.2 | 1 | 1 | 11.9 | 11.9 | 3.9 | 13.27 | - | Only 1.2km clear front available.
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 7 | OPGW Stringing | Km | 45.72 | 47.84 | 47.84 | 19.03 | 28.81 | - | 0 | - | 10 | 10 | - | 18.81 | - | Only 7km front available.
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 8 | Supply Status:
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for Jun'26 |  | Plan for Jul'26 |  | Remarks
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 10 | Stub | Nos | 121 | 127 | 127 | 127 | -
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 11 | Tower | Nos | 121 | 127 | 127 | 127 | -
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 12 | Conductor | Km | 1662 | 1740 | 1740 | 1739.4 | -
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 13 | Earthwire | Km | 47 | 50.4 | 50.4 | 50.4 | -
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 14 | 160KN CLR | Nos | 2190 | 2224 | 2224 | 2224 | -
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 15 | 210KN CLR | Nos | 3408 | 3781 | 3781 | 3781 | -
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 16 | HW Fittings | % | 100 | 100 | 100 | 100 | -
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 2 | 1 | Front Availability Status
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 2 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 2 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 2 | 4 | Foundation | No | 1 | 1 | 1 | - | - | - | - | - | -
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 2 | 5 | Tower Erection | No | 7 | 7 | 2 | - | - | 1 | 2 | 2 | 1
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 2 | 6 | Stringing | Km | 2.5 | 2.5 | 3 | 4.89 | 4.89 | 2 | 0.49 | 0.49 | 1
66 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 3 | 1 | LOA DATE: 12/03/24 | LOA Value in Cr.:148.6 | CONTRACTUAL COMPLETION: 11/12/25 | PLANNED COMPLETION: 30/06/26
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 1 | No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balnce As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 2 | Activity
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 3 | Foundation | As per L2 | Nos | 127 | 127
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 4 |  | Completion Plan | Nos
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 5 |  | Front Required from POWERGRID | Nos
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 6 |  | Gangs Planned | Nos
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 7 |  | Stubs Supply as per L2 | Nos | 127 | 127
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 8 |  | Stub Supply Actual | Nos |  | 127
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 9
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 10 | Erection | As per L2 | Nos | 127 | 127
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 11 |  | Completion Plan | Nos
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 12 |  | Front Required from POWERGRID | Nos
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 13 |  | Gangs Planned | Nos
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 14 |  | Tower Supply as per L2 | Nos | 127 | 127
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 15 |  | Tower Supply Actual | Nos |  | 127
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 16
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 17 | Stringing | As per L2 | Kms | 47.84 | 47.84 | - |  | -
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 18 |  | Completion Plan | Kms | 47.84 | 22.17 | 11.06 | 25.17 | 11.9 | 13.27
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 19 |  | Front Required from POWERGRID | Kms |  |  |  |  | 9.2 | 13.27
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 20 |  | Gangs Planned | TSE (Nos) |  |  | 2 |  | 2 | 2
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 21 |  |  | Manual (Nos) |  |  | 1 |  | 1 | 1
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 22 |  | Conductor Supply as per L2 | Nos | 1740 | 1740 | - |  | - | -
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 23 |  | Conductor Supply Actual | Nos |  | 1739.4 | - |  | - | -
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 24 |  | Insulator Supply as per L2 | Nos | 6005 | 6005 | - |  | - | -
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 25 |  | Insulator Supply Actual | Nos |  | 6005 | - |  | - | -
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 26 |  | Hardware Supply as per L2 | % | 100 | 100 | - |  | - | -
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 27 |  | Hardware Supply Actual | % |  | 100 | - |  | - | -
67 | TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 2 | 1 | LOA DATE: 12/03/24 | LOA Value in Cr.:148.6 | CONTRACTUAL COMPLETION: 11/12/25 | PLANNED COMPLETION: 30/06/26
68 | TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 1 | 1 | LOA DATE: 12/03/24 | LOA Value in Cr.:148.6 | CONTRACTUAL COMPLETION: 11/12/25 | PLANNED COMPLETION: 30/06/26
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 1 | 1 | LOA DATE: 14/03/24 | LOA Value in Cr.: 370 | CONTRACTUAL COMPLETION: 14/11/25 | PLANNED COMPLETION: May’26
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  | PlanJune 26 | PlanJul 26 | Remarks
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 2 | [10 empty] | Plan | Plan | Act
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 3 | Check Survey | Km | 119.875 | 121.342 | 121.342 | 121.342 | -
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 4 | Foundation | No | 306 | 309 | 309 | 309 | -
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 5 | Erection | No | 306 | 309 | 309 | 309 | -
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 6 | Stringing | Km | 119.875 | 121.342 | 121.342 | 107.149 | 14.19 | 14.19 | 2 | 2 | 14.19 | 14.19 | - | - | - | R/s Completed for 3.9 kms
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 7 | OPGW Stringing | Km | 119.875 | 121.342 | 121.342 | 97.67 | 23.672 | 3.2 |  |  | 23.67 | 23.67 | - | - | -
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 8 | Supply Status:
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 10 | Stub | Nos | 306 | 309 | 309 | 312 | - | [5 empty] | 3Nos stubs in spare
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 11 | Tower | Nos | 306 | 309 | 309 | 312 | - | [5 empty] | 3Nos towers in spare
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 12 | Conductor | Km | 4359 | 4412 | 4412 | 4411.538 | -
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 13 | Earthwire | Km | 122 | 128.70 | 128.70 | 128.692 | -
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 14 | 160KN CLR | Nos | 6188 | 6284 | 6284 | 6284 | -
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 15 | 210KN CLR | Nos | 5568 | 5962 | 5962 | 5962 | -
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 16 | HW Fittings | % | 100 | 100 | 100 | 100 | -
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 3 | 1 | Front Availability Status
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 3 | 4 | Foundation | No
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 3 | 5 | Tower Erection | No
69 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 3 | 6 | Stringing | Km | 25.401 | 7.884 | 3 | 25.685 | 16.697 | 3 | 22.01 | 7.818 | 2
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 1 | 1 | LOA DATE: 14/03/24 | LOA Value in Cr.: 370 | CONTRACTUAL COMPLETION: 14/11/25 | PLANNED COMPLETION: May’26
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 1 | No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 2 | Activity
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 3 | Foundation | As per L2 | Nos | 309 | 309
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 4 |  | Completion Plan | Nos | 309 | 309
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 5 |  | Front Required from POWERGRID | Nos
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 6 |  | Gangs Planned | Nos
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 7 |  | Stubs Supply as per L2 | Nos | 309 | 309
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 8 |  | Stub Supply Actual | Nos | 309 | 309
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 9
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 10 | Erection | As per L2 | Nos | 309 | 309
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 11 |  | Completion Plan | Nos | 309 | 309
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 12 |  | Front Required from POWERGRID | Nos
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 13 |  | Gangs Planned | Nos
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 14 |  | Tower Supply as per L2 | Nos | 309 | 309
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 15 |  | Tower Supply Actual | Nos | 309 | 309
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 16
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 17 | Stringing | As per L2 | Kms | 121.342 | 121.342
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 18 |  | Completion Plan | Kms | 121.342 | 107.149 | 3.608 | 14.19 | 14.19
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 19 |  | Front Required from POWERGRID | Kms
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 20 |  | Gangs Planned | TSE (Nos) | 2 | 2 |  |  | 2
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 21 |  |  | Manual (Nos) | 1 | 1 |  |  | 1
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 22 |  | Conductor Supply as per L2 | KM | 4412 | 4412
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 23 |  | Conductor Supply Actual | KM | 4412 | 4412
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 24 |  | Insulator Supply as per L2 | Nos | 12246 | 12246
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 25 |  | Insulator Supply Actual | Nos | 12246 | 12246
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 26 |  | Hardware Supply as per L2 | % | 100% | 100%
70 | TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 2 | 27 |  | Hardware Supply Actual | % | 100% | 100%
71 | Issues / Support Required | 1 | 1 | LOA DATE: 14/03/24 | LOA Value in Cr.: 370 | CONTRACTUAL COMPLETION: 14/11/25 | PLANNED COMPLETION: May’26
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 1 | 1 | LOA DATE: 13/05/25 | LOA Value in Cr.: 517.07 | CONTRACTUAL COMPLETION: 12/04/27 | PLANNED COMPLETION: 12/04/27
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  |  | PlanJun’26 | PlanJul 26 | Remarks
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 2 | [10 empty] | Plan | Plan | Act | Act
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 3 | Check Survey | Km | 118.6 | 113.286 | 113.286 | 112.886 | 0.400 | - | - | - | 0.400 | 0.400 | - | - | - | NA | Hold from PGCIL due to widening of NH
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 4 | Foundation | No | 316 | 292 | 252 | 113 | 179 | 20 | 03 | 03 | 40 | 40 | - | 03 | 40 | 20
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 5 | Erection | No | 316 | 292 | 190 | 70 | 222 | 30 | 01 | 01 | 35 | 35 | - | 01 | 35 | 20
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 6 | Stringing | Km | 118.6 | 113.286 | 17 | - | 113.286 | - | 00 | - | 00 | - | 00 | - | 05 | 06 | Planned to Start in June’2026
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 7 | OPGW Stringing | Km
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 8 | Supply Status:
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 10 | Stub | Nos | 316 | 292 | 292 | 235 | 57 | 55 | 02 |  | - |  | To completed in May(02 Loc under hold)
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 11 | Tower | Nos | 316 | 292 | 230 | 230 | 62 | 09 | 26 |  | 25 |  | 02 loc Under hold by PGCIL
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 12 | Conductor | Km | 4314 | 4118 | 3000 | 3285 | 833 | 300 | 300 |  | 233
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 13 | Earthwire | Km | 121 | 114 | 85 | 86 | 35 | - | 35 |  | -
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 14 | 160KN CLR | Nos | 6146 | 6146 | 4300 | - | 6146 | - | 1000 |  | 1500
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 15 | 210KN CLR | Nos | 7200 | 7200 | 4900 | - | 7200 | - | 1000 |  | 1500
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 2 | 16 | HW Fittings | % | 100 | 100 | 70 | 70 | 30 | - | - |  | 30
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 3 | 1 | Front Availability Status
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 3 | 4 | Foundation | No | 30 | 17 | 04 | 25 | 15 | 04 | 22 | 12 | 03
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 3 | 5 | Tower Erection | No | 40 | 29 | 06 | 33 | 13 | 05 | 35 | 04 | 02
72 | TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 3 | 6 | Stringing | Km | - | - | - | - | - | - | - | - | -
73 | Issues / Support Required | 1 | 1 | LOA DATE: 13/05/25 | LOA Value in Cr.: 517.07 | CONTRACTUAL COMPLETION: 12/04/27 | PLANNED COMPLETION: 12/04/27
75 | TW24 - 132kV Tawang-Lumla Line | 1 | 1 | LOA DATE: 13/05/25 | LOA Value in Cr.: 517.07 | CONTRACTUAL COMPLETION: 12/04/27 | PLANNED COMPLETION: 12/04/27
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 1 | Activity | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Completed(Till 30.04.26) | Balance(As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | PlanMay 26 | PlanMay 26 |  |  | PlanJun’26 | PlanJul 26 | Remarks
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 2 | [10 empty] | Plan | Plan | Act | Act
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 3 | Check Survey | Km | 40 | 26.250 | 26.250 | 26.250 |  |  | - |  | 0.400 |  | -
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 4 | Foundation | No | 97 | 90 | 90 | 85 | 5 | 5 | 03 | 3 | 40 | 3 | - | 0 | 2 | 0
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 5 | Erection | No | 97 | 90 | 90 | 76 | 14 | 14 | 01 | 1 | 35 | 6 | - | 0 | 6 | 2
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 6 | Stringing | Km | 26.250 | 25.47 | 25.47 | 18.448 | 7.024 | 7.024 | 00 | 1 | 00 | 1.5 | 00 | 0 | 2.5 | 3.024
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 7 | OPGW Stringing | Km | 26.250 | 25.47 | 25.47 | 0 | 25.47 | [7 empty] | 13.472 | 12
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 8 | Supply Status:
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 9 | Item | UoM | As Per LOA (Qty) | Revised(Qty) | As per L2(April'26) | Actual Supplied | Balance | Plan for May'26 | Plan for June'26 |  | Plan for Jul'26 |  | Remarks
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 10 | Stub | Nos | 97 | 90 | 90 | 90 | 0
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 11 | Tower | Nos | 97 | 90 | 90 | 90 | 0
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 12 | Conductor | Km | 122 | 81.351 | 81.351 | 81.351 | 0
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 13 | Earthwire | Km
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 14 | 160KN CLR | Nos | 856 | 856 | 580 | 580 | 0
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 15 | 210KN CLR | Nos
75 | TW24 - 132kV Tawang-Lumla Line | 2 | 16 | HW Fittings | % | 100 | 100 | 70 | 70 | 30 | - | - |  | 30
75 | TW24 - 132kV Tawang-Lumla Line | 3 | 1 | Front Availability Status
75 | TW24 - 132kV Tawang-Lumla Line | 3 | 2 | Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26
75 | TW24 - 132kV Tawang-Lumla Line | 3 | 3 |  |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
75 | TW24 - 132kV Tawang-Lumla Line | 3 | 4 | Foundation | No | 8 | 0 |  | 8 | 0 |  | 7 | 1 | 1
75 | TW24 - 132kV Tawang-Lumla Line | 3 | 5 | Tower Erection | No | 20 | 0 |  | 20 | 2 | 1 | 18 | 3 | 1
75 | TW24 - 132kV Tawang-Lumla Line | 3 | 6 | Stringing | Km | 4 | 0 |  | 4 | 0.632 | 1 | 3.4 | 1.2 | 1
76 | TW24 - 132kV Tawang-Lumla Line | 1 | 1 | LOA DATE: 13/05/25 | LOA Value in Cr.: 517.07 | CONTRACTUAL COMPLETION: 12/04/27 | PLANNED COMPLETION: 12/04/27
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 1 | No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 2 | Activity
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 3 | Foundation | As per L2 | Nos | 90 | 90
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 4 |  | Completion Plan | Nos | 90 | 85 | 5 | 3 | 2
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 5 |  | Front Required from POWERGRID | Nos |  |  |  | 3 | 2
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 6 |  | Gangs Planned | Nos |  |  |  | 3 | 2
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 7 |  | Stubs Supply as per L2 | Nos | 90 | 90
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 8 |  | Stub Supply Actual | Nos | 90 | 90
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 9
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 10 | Erection | As per L2 | Nos | 90 | 90
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 11 |  | Completion Plan | Nos | 90 | 76 | 14 | 6 | 6 | 2
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 12 |  | Front Required from POWERGRID | Nos |  |  |  | 6 | 6 | 2
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 13 |  | Gangs Planned | Nos |  |  |  | 3 | 3 | 1
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 14 |  | Tower Supply as per L2 | Nos | 90 | 90
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 15 |  | Tower Supply Actual | Nos | 90 | 90
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 16
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 17 | Stringing | As per L2 | Kms | 25.472 | 25.472
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 18 |  | Completion Plan | Kms | 25.472 | 18.448 | 7 | 1.5 | 2.5 | 3
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 19 |  | Front Required from POWERGRID | Kms |  |  |  | 1.5 | 2.5 | 3
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 20 |  | Gangs Planned | TSE (Nos)
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 21 |  |  | Manual (Nos) |  |  |  | 1 | 2 | 2
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 22 |  | Conductor Supply as per L2 | Nos | 81.361 | 81.361
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 23 |  | Conductor Supply Actual | Nos | 81.361 | 76.454
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 24 |  | Insulator Supply as per L2 | Nos | 580 | 580
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 25 |  | Insulator Supply Actual | Nos | 580 | 580
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 26 |  | Hardware Supply as per L2 | % | 100 | 100
76 | TW24 - 132kV Tawang-Lumla Line | 2 | 27 |  | Hardware Supply Actual | % | 100 | 90
77 | 400 KV D/C Twin Line Latehar- Patraru | 1 | 1 | Particulars | UoM | Total Qty | Completed(Till 30.04.26) | Balance(As on 01.05.26) | May 26 |  | Cu. Progress upto date | WIP | Remarks
77 | 400 KV D/C Twin Line Latehar- Patraru | 1 | 2 | [5 empty] | Plan | Act
77 | 400 KV D/C Twin Line Latehar- Patraru | 1 | 3 | Foundation | Loc | 304 | 275 | 29 |  |  | 275 |  | Forest approval awaited. 29 Loc in Forest
77 | 400 KV D/C Twin Line Latehar- Patraru | 1 | 4
77 | 400 KV D/C Twin Line Latehar- Patraru | 1 | 5 | Stub Rectification work | Leg | 514 | 323 | 193 | 66 | 32 | 355 | 16 | Forest -115 Leg (32 Loc)
77 | 400 KV D/C Twin Line Latehar- Patraru | 1 | 6 | No. of Gangs |  |  |  |  | 5 | 2
77 | 400 KV D/C Twin Line Latehar- Patraru | 1 | 7 | Gang Strength | [5 empty] | 16
77 | 400 KV D/C Twin Line Latehar- Patraru | 1 | 8 | Tower Erection | Loc | 304 | 266 | 38 |  |  | 266 |  | Forest approval awaited. 38 Loc in Forest
77 | 400 KV D/C Twin Line Latehar- Patraru | 1 | 9 | Tower Erection work against Theft & Collapsed Portion | Loc | 156 |  | 156
77 | 400 KV D/C Twin Line Latehar- Patraru | 1 | 10 | Partial Tower Rectification due to Theft | Loc | 110 |  | 110
77 | 400 KV D/C Twin Line Latehar- Patraru | 1 | 11 | Stringing | KM | 107.51 | 2.190 | 105.32 |  |  | 2.190
77 | 400 KV D/C Twin Line Latehar- Patraru | 1 | 12 | OPGW Stringing | KM | 107.51 |  | 107.51
78 | Sikkim Tower Pkg TK04 | 1 | 1 | Activity | UoM | Revised Line Qty | Completedas on May-26 | Balanceas on May-26 | Completion Timeline
78 | Sikkim Tower Pkg TK04 | 1 | 2 | [5 empty] | Jun-26 | July-26 | Aug-26
78 | Sikkim Tower Pkg TK04 | 1 | 3 | Foundation | NOS | 132 | 132 | NIL
78 | Sikkim Tower Pkg TK04 | 1 | 4 | Tower Erection | NOS | 132 | 132 | NIL
78 | Sikkim Tower Pkg TK04 | 1 | 5 | Stringing | KM | 22.420 | 21.793 | 0.627 | 0.279 | 0.348
78 | Sikkim Tower Pkg TK04 | 1 | 6 | OPGW Stringing | KM | 21.517 | 8.929 | 12.588 | 3.799 | 6.033 | 2.756
78 | Sikkim Tower Pkg TK04 | 1 | 7 | Cutting of Soil | Cum | 1589 | 1379 | 210 | 210
78 | Sikkim Tower Pkg TK04 | 1 | 8 | Dismantling of Erected Tower | MT | 96.059 | 0 | 96.059 |  | 58.743 | 37.316
78 | Sikkim Tower Pkg TK04 | 1 | 9 | De-Stringing | KM | 0.428 | 0 | 0.428 | 0.428
79 | Sikkim Tower Pkg TK04 | 1 | 1 | Activity | UoM | Revised Line Qty | Completedas on Sep-23 | Balanceas on Sep-23 | Completion Timeline
79 | Sikkim Tower Pkg TK04 | 1 | 2 | [5 empty] | Jan-26 | Feb-26 | Mar-26
79 | Sikkim Tower Pkg TK04 | 1 | 3 | Foundation | NOS | 123 | 108 | 15 | Applied for Short Clouser of Line on as is where is basis vide letter Ref. PG/TK 04/CSSTDS/Descoping/1274 Dt. 30.01.26
79 | Sikkim Tower Pkg TK04 | 1 | 4 | Tower Erection | NOS | 123 | 108 | 15
79 | Sikkim Tower Pkg TK04 | 1 | 5 | Stringing | KM | 29.010 | 21.973 | 7.037
79 | Sikkim Tower Pkg TK04 | 1 | 6 | OPGW Stringing | KM | 29.010 | 6.534 | 22.476
80 | Sikkim Tower Pkg TK04 | 1 | 1 | Activity | UoM | Line Qty | Completedas on Sep-23 | Balanceas on Sep-23 | Completion Timeline
80 | Sikkim Tower Pkg TK04 | 1 | 2 | [5 empty] | Jan-26 | Feb-26 | Mar-26
80 | Sikkim Tower Pkg TK04 | 1 | 3 | Foundation | NOS | 37 | 37 | NIL | Applied for Short Clouser of Line on as is where is basis vide letter Ref. PG/TK 04/CSSTDS/Descoping/1274 Dt. 30.01.26
80 | Sikkim Tower Pkg TK04 | 1 | 4 | Tower Erection | NOS | 37 | 36 | 1 (37/0)
80 | Sikkim Tower Pkg TK04 | 1 | 5 | Stringing | KM | 7.242 | 7.106 | 0.136
80 | Sikkim Tower Pkg TK04 | 1 | 6 | OPGW Stringing | KM | 7.242 | 0 | 7.242
80 | Sikkim Tower Pkg TK04 | 2 | 1 | Activity | UoM | Revised Line Qty | Completedas on May-26 | Balanceas on May-26 | Completion Timeline
80 | Sikkim Tower Pkg TK04 | 2 | 2 | [5 empty] | Jun-26 | July-26 | Aug-26
80 | Sikkim Tower Pkg TK04 | 2 | 3 | Foundation | NOS | 13 (+1) | 13 | NIL (+1) |  | 1
80 | Sikkim Tower Pkg TK04 | 2 | 4 | Tower Erection | NOS | 13 (+1) | 13 | NIL (+1) |  |  | 1
80 | Sikkim Tower Pkg TK04 | 2 | 5 | Stringing | KM | 1.423 (+0.323) | 1.395 | 0.028 (+0.323) |  |  | 0.323
80 | Sikkim Tower Pkg TK04 | 2 | 6 | OPGW Stringing | KM | 1.346 | 0 | 1.346 |  |  | 1.346
81 | Sikkim Tower Pkg TK04 | 1 | 1 | Activity | UoM | Revised Line Qty | Completedas on Sep-23 | Balanceas on Sep-23 | Completion Timeline
81 | Sikkim Tower Pkg TK04 | 1 | 2 | [5 empty] | Jan-26 | Feb-26 | Mar-26
81 | Sikkim Tower Pkg TK04 | 1 | 3 | Foundation | NOS | 5 | 5 | NIL | Line de-scope by Powergrid on 08/05/2024 vide letter ref no. ER-II/CSSTDS/GTK/TK-04/1766
81 | Sikkim Tower Pkg TK04 | 1 | 4 | Tower Erection | NOS | 5 | 5 | NIL
81 | Sikkim Tower Pkg TK04 | 1 | 5 | Stringing | KM | 0.326 | 0.247 | 0.079
81 | Sikkim Tower Pkg TK04 | 1 | 6 | OPGW Stringing | KM | 0.326 | 0 | 0.326
82 | Sikkim Tower Pkg TK04 | 1 | 1 | Activity | UoM | Revised Line Qty | Completedas on May-26) | Balanceas on May-26 | Completion Timeline
82 | Sikkim Tower Pkg TK04 | 1 | 2 | [5 empty] | Jun-26 | July-26 | Aug-26
82 | Sikkim Tower Pkg TK04 | 1 | 3 | Foundation | NOS | 32 | 32 | NIL | Needs to be Short Close of Line from AP- DE(PTL) to AP 19/0 i.e. 3.225 KM on as is where is basis
82 | Sikkim Tower Pkg TK04 | 1 | 4 | Tower Erection | NOS | 32 | 32 | NIL
82 | Sikkim Tower Pkg TK04 | 1 | 5 | Stringing | KM | 4.357 | 4.320 | 0.037
82 | Sikkim Tower Pkg TK04 | 1 | 6 | OPGW Stringing | KM | 4.357 | 4.288 | 0.069
84 | Summary of Claims submitted at PGCIL(Region Wise) | 1 | 1 | Sr. No. | Region | Claim raised amount(in Rs Cr)
84 | Summary of Claims submitted at PGCIL(Region Wise) | 1 | 2 | 1 | ER-I(Patna) | 78
84 | Summary of Claims submitted at PGCIL(Region Wise) | 1 | 3 | 2 | ER-II(Kolkata) | 25
84 | Summary of Claims submitted at PGCIL(Region Wise) | 1 | 4 | 3 | ER-II(Kolkata)- Cables | 4
84 | Summary of Claims submitted at PGCIL(Region Wise) | 1 | 5 | 4 | NER(Guwahati) | 3
84 | Summary of Claims submitted at PGCIL(Region Wise) | 1 | 6 | 5 | NER(Itanagar) | 4
84 | Summary of Claims submitted at PGCIL(Region Wise) | 1 | 7 | 6 | Rajasthan | 90
84 | Summary of Claims submitted at PGCIL(Region Wise) | 1 | 8 | 7 | WR-II(Vadodara) | 95
84 | Summary of Claims submitted at PGCIL(Region Wise) | 1 | 9 | 8 | NR-I(Faridabad) | 9
84 | Summary of Claims submitted at PGCIL(Region Wise) | 1 | 10 | 9 | SR-I(Hyderabad) | 2
84 | Summary of Claims submitted at PGCIL(Region Wise) | 1 | 11 | Total |  | 310
84 | Summary of Claims submitted at PGCIL(Region Wise) | 2 | 1 | Pending Claims (ER-I)
84 | Summary of Claims submitted at PGCIL(Region Wise) | 2 | 2 | Sr. No. | Project | Claim Description | LOA Date | LOA Value(Cr) | Contractual Completion | Planned Completion | Claim Raised Amount (Cr) | Pendency | Remarks
84 | Summary of Claims submitted at PGCIL(Region Wise) | 2 | 3 | 1 | JSEB 01Tower package TW-01 associated with implementation of transmission scheme in Jharkhand under consultancy services to JSEB | Prolongation & Interest on outstanding payments | 28-09-2012 | 213.99 | 15 Months | Forest clearance awaited | 77.24 | Pending since April 2022 | Being continuously followed up in corporate for settlement
84 | Summary of Claims submitted at PGCIL(Region Wise) | 2 | 4 |  |  | Idling of Resources |  |  |  |  | 0.50 | Pending since March 2022
84 | Summary of Claims submitted at PGCIL(Region Wise) | 2 | 5 | Claim Raised Amount(Cr) for ER-I | [6 empty] | 77.74
85 | Pending Claims (ER-II) | 1 | 1 | Sr. No. | Project | Claim Description | LOA Date | LOA Value (Cr) | Contractual Completion | Planned Completion | Claim Raised Amount (in Rs Cr) | Pendency | Remarks
85 | Pending Claims (ER-II) | 1 | 2 | 1 | Tower package TK-01 under comprehensive scheme of strengthening of transmission and distribution system in sikkim | TK01-Prolongation | 16-03-2016 | 115.21 | 30 Months | completed | 6.74 | Pending since Nov-2022 | Being continuously followed up in corporate for settlement
85 | Pending Claims (ER-II) | 1 | 3 |  |  | TK01-Prolongation | 16-03-2016 | 115.21 | 30 Months | completed | 2.84 | Submitted in Dec-2022 | Being followed up at site
85 | Pending Claims (ER-II) | 1 | 4 |  | Tower package Tk-04 for various 66/220 kV Transmission lines Under comprehensive scheme of strengthening of transmission and distribution system in sikkim | TK04-Prolongation | 23-06-2016 | 188.07 | 38 Months | Under short closure | 7.00 | Pending since Nov-2022 | Being continuously followed up in corporate for settlement
85 | Pending Claims (ER-II) | 1 | 5 |  |  | TK 04 Prolongation claim | 23-06-2016 | 188.07 | 38 Months | Under short closure | 8.70 | Pending from Aug-2025 | Being followed up in the region
85 | Pending Claims (ER-II) | 1 | 6 | 2 | PGCIL SIKKIM OLD( cabling) | Prolongation | 03-02-2021 | 5.28 | 03-Jun-21 | Under short closure | 2.12 | Submitted in Sept'25 | Yet to be initiated for settlement.
85 | Pending Claims (ER-II) | 1 | 7 | 3 | PGCIL SIKKIM NEW(cabling) | Prolongation | 17-03-2022 | 3.5 | 15-Jul-22 | Client dependency( TOC Applied) | 1.84 | Submitted in Sept'25 | Yet to be initiated for settlement.
85 | Pending Claims (ER-II) | 1 | 8 | Claim Raised Amount(Cr) for ER-II | [6 empty] | 29.24
86 | Pending Claims (NR) | 1 | 1 | Region: Northeast Region (Guwahati)
86 | Pending Claims (NR) | 1 | 2 | Sr. No. | Project | Claim Description | LOA Date | LOA Value(Cr) | Contractual Completion | Planned Completion | Claim Raised Amount(in Rs Cr) | Pendency | Remarks
86 | Pending Claims (NR) | 1 | 3 | 1 | Transmission line package TW7B | Prolongation | 15-01-2021 | 62.88 | 12 Months | Completed | 3.11 | Pending since Sept'22 | Being followed up in the region/site
86 | Pending Claims (NR) | 1 | 4 | Claim Raised Amount(Cr) for NER-Guwahati | [6 empty] | 3.11
86 | Pending Claims (NR) | 1 | 5 | Region: Northeast Region (Itanagar)
86 | Pending Claims (NR) | 1 | 6 | 2 | Tower package TW24 under comprehensive scheme of strengthning of transmission and distribution system in Arunachal Pradesh | Prolongation | 28-09-2018 | 346.05 | 30 Months | 30-07-2026 | 4.00 | Pending since May'23 | Under review with client ,Document verification done.additional document sought (Form -16)
86 | Pending Claims (NR) | 1 | 7 | Claim Raised Amount(Cr) for NER-Itanagar | [6 empty] | 4.00
87 | Pending Claims (Rajasthan Region) | 1 | 1 | Sr. No. | Project | Claim Description | LOA Date | LOA Value(Cr) | Contractual Completion | Planned Completion | Claim Raised Amount (in Rs Cr) | Pendency | Remarks
87 | Pending Claims (Rajasthan Region) | 1 | 2 | 1 | TW02 for 765kV D/C Fatehgarh-Il PS - Bhadla - II PS (2nd) under TBCB | Prolongation (18.3Crs)/Idling (1.1Crs) | 15-02-2021 | 239.75 | 15 Months | Completed | 19.40 | Pending since Feb'24 | Preliminary discussion held on 27.04.26.Next date to be finalized for further taking up the claims
87 | Pending Claims (Rajasthan Region) | 1 | 3 | 2 | TW01 for Bhadla-Il PS- Sikar-II 765kV D/C Line-Part-I under TBCB | Prolongation (11.48Crs)/Idling (0.24Crs) | 15-02-2021 | 228.51 | 15 Months | Completed | 11.72 | Pending since Jan'24 | Preliminary discussion held on 27.04.26.Next date to be finalized for further taking up the claims
87 | Pending Claims (Rajasthan Region) | 1 | 4 | 3 | TW03 for Bhadla-Il PS- Sikar-II 765kV D/C Line-Part-III under TBCB | Prolongation (23.69 Crs)/Idling (1.91Crs) | 15-02-2021 | 241.26 | 15 Months | Completed | 25.60 | Pending since Aug'24 | Preliminary discussion held on 27.04.26.Next date to be finalized for further taking up the claims
87 | Pending Claims (Rajasthan Region) | 1 | 5 | 4 | TW04 for Sikar-ll - Neemrana 400 kV D/C line (Twin HTLS) (Part I) under TBCB | Prolongation (20.36Crs)/Idling (0.37Crs) | 15-02-2021 | 138.35 | 15 Months | Completed | 20.73 | Pending since Nov'24 | Preliminary discussion held on 27.04.26.Next date to be finalized for further taking up the claims
87 | Pending Claims (Rajasthan Region) | 1 | 6 | 5 | Package TW02 for Bhadla-Il PS- Sikar-II 765kV D/C Line-Part-II under TBCB | Prolongation Cost | 15-02-2021 | 238.75 | 15 Months | Completed | 12.81 | Submitted in Jan'25 | Preliminary discussion held on 27.04.26.Next date to be finalized for further taking up the claims
87 | Pending Claims (Rajasthan Region) | 1 | 7 | Claim Raised Amount(Cr) for RJ Region | [6 empty] | 90.26
88 | Pending Claims (WR-II) (Cont..) | 1 | 1 | Sr. No. | Project | Claim Description | LOA Date | LOA Value( Cr) | Contractual Completion | Planned Completion | Claim Raised Amount (in Rs Cr) | Pendency | Remarks
88 | Pending Claims (WR-II) (Cont..) | 1 | 2 | 1 | Navsari Magarwada TL | Prolongation (7.21Crs)/Idling (0.8 Crs) | 11-08-2022 | 285.66 | 10-11-23 & 10-9-24 | 02-04-2026 | 8.32 | Pending since April'23, Latest submission was made in Jan'25 | Idling -As per Powergrid meeting, revisions were made after addressing Finance queries and routing via PESM and C&M—is presently under review with Finance (HoD level committee).Prolongation - Revised L2 finalized after joint discussions with PG & KEC; consent and PV implications submitted, and the case is currently under review with Finance.
88 | Pending Claims (WR-II) (Cont..) | 1 | 3 | 2 | Ahmedabad Navsari TL 02 | Idling | 21-03-2023 | 838.55 | 20-12-2024 | 29-01-2026 | 1.82 | Pending since Dec'23 | PG asked to arrange certain documents in support of idling claimed. Supporting documents submitted. Notesheet fwded from site to PESM on 06.04.2026. Under review with PESM dept. and queries being resolved as required .
88 | Pending Claims (WR-II) (Cont..) | 1 | 4 |  |  | Prologation | 21-03-2023 |  | 20-12-2024 | 29-01-2026 | 8.70 | Pending since Sept'25 | Revised L2 under process with PGCIL RHQ PESM team. Supporting documents for FTE submitted and under review with PG. Revised L2 to be finalized in line with FTE. Delay analysis for FTE is being prepared and worked upon jointly with Powergrid.
88 | Pending Claims (WR-II) (Cont..) | 1 | 5 |  |  | Foundation and erection dismatling work | 21-03-2023 |  | 20-12-2024 | 29-01-2026 | 1.10 | Submitted in Dec '25 | Non-BoQ item. Amendment submitted and under review at RHQ.
88 | Pending Claims (WR-II) (Cont..) | 1 | 6 |  |  | Surge costs for expediting project completion | 21-03-2023 |  | 20-12-2024 | 29-01-2026 | 46.30 | Submitted in Apr '26 | Submitted on 06 April 2026 with PGCIL site.
89 | Pending Claims (WR-II) | 1 | 1 | Sr. No. | Project | Claim Description | LOA Date | LOA Value(Cr) | Contractual Completion | Planned Completion | Claim Raised Amount(in Rs Cr) | Pendency | Remarks
89 | Pending Claims (WR-II) | 1 | 2 | 3 | Railway Electrification works Package- PUNE-SATARA (Railways) | Prolongation | 21-06-2018 | 344.65 | 06-02-2022 | 17-06-2025 | 20.09 | Pending since May'23 | Currently at RHQ
89 | Pending Claims (WR-II) | 1 | 3 | 4 | Ahmedabad SS | Prolongation | 17-03-2023 | 184.51 | 16-12-2024 | 02-01-2026 | 3.17 | Submitted in Sept'25 | Revised proposal submitted on 07.03.2026; further revisions and supporting documents requested by Powergrid in meeting dated 23.04.2026 are under preparation, and updated proposal will be submitted by end of Week 2. May 26
89 | Pending Claims (WR-II) | 1 | 4 | 5 | KPS 2 SS | Prolongation | 18-03-2023 | 359.33 | 17-12-2024 | 05-12-2025 | 5.10 | Submitted in Sept'25 | Submitted on 22-Sep-25; As per discussion with Powergrid, revised proposal is under preparation and will be submitted by end of Week 2 May'26
89 | Pending Claims (WR-II) | 1 | 5 | Claim Raised Amount(Cr) for WR -II | [6 empty] | 94.60
90 | Pending Claims(SR-I and NR-I) | 1 | 1 | Sr. No. | Project | Claim Description | LOA Date | LOA Value(Cr) | Contractual Completion | Planned Completion | Claim Raised Amount(Cr) | Pendency | Remarks
90 | Pending Claims(SR-I and NR-I) | 1 | 2 | 1 | Koppal Raichur | Idling | 12-03-2024 | 148.6 | 11-12-2025 | 30-06-2026 | 1.70 | Submitted in Apr'26 | Submittedd on 15 april 2026 under review with PGCIL site.
90 | Pending Claims(SR-I and NR-I) | 1 | 3 | Claim Raised Amount(Cr) for SR -I | [6 empty] | 1.70
90 | Pending Claims(SR-I and NR-I) | 1 | 4 | Sr. No. | Project | Claim Description | LOA Date | LOA Value(Cr) | Contractual Completion | Planned Completion | Claim Raised Amount(Cr) | Pendency | Remarks
90 | Pending Claims(SR-I and NR-I) | 1 | 5 | 1 | Bikaner Sub Station pkg-01 | Delay in land handover | 02-03-2021 | 106.09 | 15 Month | Completed | 2.00 | Pending since June'22 | Partially settled
90 | Pending Claims(SR-I and NR-I) | 1 | 6 | 2 | Neemuch PS – Chittorgarh (PG)TL01- 400kV D/C | Project was fast tracked for completion based on Employer's request to expedite and recoup for the delays on account of Forest clearance. Yet to be concluded. Claim with complete details of additional expenses on account of expediting submitted. | 12-09-2022 | 254.77 | 15 Month | Completed | 7.00 | Pending Since May'24 | Being followed up in the region
90 | Pending Claims(SR-I and NR-I) | 1 | 7 | Claim Raised Amount(Cr) for NR –I | [6 empty] | 9.00
90 | Pending Claims(SR-I and NR-I) | 1 | 8 | Total Claim Raised Amount(Cr) | [6 empty] | 309.65
91 | Pending L2 Revision | 1 | 1 | SL No | Project | Region | Pendency | Reason for Pendency
91 | Pending L2 Revision | 1 | 2 | 1 | JSEB Pkg – 01 TL | ER1 | Pending since April’23. | Proposal at corporate for approval. To be expedited.
91 | Pending L2 Revision | 1 | 3 |  |  |  |  | Out of 10 lines 9 lines have already been completed. 10th line rectification work has been started. (339/516 Leg completed and 24 Leg WIP).
91 | Pending L2 Revision | 1 | 4 | 2 | TW07B Assam TL | NER | Pending since May’23 | Project completed. To be expedited
91 | Pending L2 Revision | 1 | 5 | 3 | Navsari Magarwada TL | WR2 | Pending since July’25 | Project completed. Revised L2 finalized after joint discussions with PG & KEC; consent and PV implications submitted, and the case is currently under review with Finance.
91 | Pending L2 Revision | 1 | 6 | 4 | Ahmedabad Navsari TL | WR2 | Submitted on 11-11-25 | Project completed. Revised L2 under process with PGCIL RHQ PESM team. Supporting documents for FTE submitted and under review with PG. Revised L2 to be finalized in line with FTE. Delay analysis for FTE is being prepared and worked upon jointly with Powergrid. To be expedited.
92 | Financial details(Closure Projects) | 1 | 1 | Project Code | Project Name | SBU | Region | Pending from which date | O/s Amount (Cr) | CPBG & Retention Value(Cr) | Adv Bank Guarantee Cr)
92 | Financial details(Closure Projects) | 1 | 2 | A303/304 | JSEB Lines | TL | ER-I | Jan'25 | 13 | 32 | -
92 | Financial details(Closure Projects) | 1 | 3 | A920 | Khupi-Bomdila TL SS | TL | NER | Sept'24 | 10 | 4 | -
92 | Financial details(Closure Projects) | 1 | 4 | TA-119 | TL Package TW7B Assam | TL | NER | June'24 | 1 | 6 | -
92 | Financial details(Closure Projects) | 1 | 5 | TA-121 | TW01 for Bhadla-II PS- Sikar-II 765kV D/C Line-Part-I | TL | RJ | Dec'24 | 6 | 7 | 0.3
92 | Financial details(Closure Projects) | 1 | 6 | TA-122 | TW02 for Bhadla-II PS- Sikar-II 765kV D/C Line-Part-II | TL | RJ | Dec'24 | 17 | 10 | -
92 | Financial details(Closure Projects) | 1 | 7 | TA-123 | TW03 for Bhadla-II PS- Sikar-II 765kV D/C Line-Part-III | TL | RJ | Dec'24 | 22 | 8 | -
92 | Financial details(Closure Projects) | 1 | 8 | TA-124 | Package TW04 for Sikar-II – Neemrana 400 kV D/C line (Twin HTLS) | TL | RJ | Dec'24 | 19 | 5 | 2
92 | Financial details(Closure Projects) | 1 | 9 | A775 | PG Aligarh | SS | NR-III | Aug'22 |  | 0.3 | -
92 | Financial details(Closure Projects) | 1 | 10 | SA-008 | Guna | SS | WR-II | Jan'23 | 5 | - | -
92 | Financial details(Closure Projects) | 1 | 11 | SA-126 | 400 KV Bikaner S/S | SS | NR-I | June'23 | 4 | 3 | 3
92 | Financial details(Closure Projects) | 1 | 12 | SA-127 | 400 Khetri S/S | SS | NR-I | June'23 | 2 | - | -
92 | Financial details(Closure Projects) | 1 | 13 | SA-128 | 400 Bhiwadi S/S | SS | NR-I | Mar'23 | 2 | - | -
92 | Financial details(Closure Projects) | 1 | 14 | SA-213 | 764 KV Khetri | SS | NR-I | Sept'24 | 5 | - | -
92 | Financial details(Closure Projects) | 1 | 15 | XA-104 | PGCIL Pithoragarh | Cable | NR-III | Dec'22 | 4 | 1 | -
92 | Financial details(Closure Projects) | 1 | 16 | XA- 107 | PGCIL Sikkim -New | Cable | ER-II | Jul'24 | 1 | 0.2 | -
92 | Financial details(Closure Projects) | 1 | 17 | XB-012 | PGCIL Sikkim -Old | Cable | ER-II | Aug'24 | - | 0.2 | -
92 | Financial details(Closure Projects) | 1 | 18 | A820 | PGCIL TW-09 | TL | NER | Dec'25 | 3 | 0.8 | -
92 | Financial details(Closure Projects) | 1 | 19 | SA-212 | Narela SS | SS |  | Dec'25 | 16 | 9 | -
92 | Financial details(Closure Projects) | 1 | 20 | SA-307 | Navsari-DL | SS |  | Apr'25 | 40 | 13 | 5
92 | Financial details(Closure Projects) | 1 | 21 | SA-308 | Phadghe-DL | SS |  | Apr'25 | 16 | -
92 | Financial details(Closure Projects) | 1 | 22 | SA-322 | Ahembdabad SS | SS |  | Jan'26 | 23 | 6 | 7
92 | Financial details(Closure Projects) | 1 | 23 | SA-323 | KPS 2 | SS |  | Dec'25 | 42 | 10 | 4
92 | Financial details(Closure Projects) | 1 | 24 | SA-324 | Navsari GIS Extn | SS |  | Jan'26 | 27 | 5 | 7
92 | Financial details(Closure Projects) | 1 | 25 | SA-409 | Ramgarh SS | SS |  | Dec'25 | 22 | 8 | 2
92 | Financial details(Closure Projects) | 1 | 26 | TA-325 | Ahmedabad-Navsari (South Gujarat) Line | TL |  | Jan'26 | 61 | 25 | 18
92 | Financial details(Closure Projects) | 1 | 27 | TA-405 | Bhadla-II to Sikar-II | TL |  | Dec'25 | 30 | 11 | 9
92 | Financial details(Closure Projects) | 1 | 28 | TA-310 | Navsari Kala T/L | TL |  | Mar'26 | 47 | 22
92 | Financial details(Closure Projects) | 1 | 29 |  | Total |  |  |  | 439 | 186 | 57
94 | Project Closure Status(Rajasthan) | 1 | 1 | Sr. No | Project Name | TL/SS | Date of Commissioning | Pending Outstanding Value(Crs.) | Claims (Crs.) | Remarks
94 | Project Closure Status(Rajasthan) | 1 | 2 | 1 | Package TW01 for Badla-Il PS- Sikar-II 765kV D/C Line-Part-I (TA 121) | TL | 17.12.24 | 6 | 11.72 | Final Bill check at RHQ finance WIP
94 | Project Closure Status(Rajasthan) | 1 | 3 | 2 | Package TW02 for Bhadla-ps- Sikar-lt 765kv D/cline-part-Il (TA 122) | TL | 17.12.24 | 16.9 | 12.81 | Final Bill check at RHQ finance WIP
94 | Project Closure Status(Rajasthan) | 1 | 4 | 3 | Package TW03 for Badla-Il PS- Sikar-II 765kV D/C Line-Part-III(TA 123) | TL | 17.12.24 | 21.9 | 25.6 | FTE approved & FA in SAP uploading pending ,Final bill processing pending
94 | Project Closure Status(Rajasthan) | 1 | 5 | 4 | Package TW04 for Sikar-ll - Neemrana 400 kV D/C line (Twin HTLS(TA124) | TL | 11.10.24 | 19.3 | 20.7 | FTE & FA approval pending . RA billing processing pending
94 | Project Closure Status(Rajasthan) | 1 | 6 | 5 | Package TW02 for Badla-III Ps- Sikar-II 765kv D/cline-part-Il (TA405) | TL | 12.02.26 | 25.0 |  | FA & FTE issuance pending
94 | Project Closure Status(Rajasthan) | 1 | 7 | 6 | 765/400/220kV Ramgarh PS New | SS | 23.02.26 | 22.2 |  | FA & FTE issuance pending
94 | Project Closure Status(Rajasthan) | 1 | 8 | 7 | 765/400/220kV Badla III PS | SS | 03.03.26 | 36 |  | TOC issuance pending
94 | Project Closure Status(Rajasthan) | 1 | 9 | 8 | TW02: Fathegargh -II PS - Badla -II PS 765 KV D/c Line (2 nd) Part B (TA -120) | TL | 18.08.24 |  | 19.4
94 | Project Closure Status(Rajasthan) | 1 | 10 | 9 | Substation projects: (Bikaner/Khetri & Bhiwadi) | SS |  | 7.67 |  | Final bill processing pending
94 | Project Closure Status(Rajasthan) | 1 | 11 |  |  |  | Total | 155 | 90

## Presentation Summary Rows
project_code | tl_ss | region | project_name_from_summary | scheduled_completion | expected_completion | running_project_details | project_value_cr | ueob_cr | presentation_slides | presentation_requirements | presentation_slide_types | presentation_slide_titles
TA 413 | TL | NWR | 765KV D/C Bikaner III - Neemrana II (TA – 413) | 11/12/25 | 30/07/26 | 765 kV D/C Bikaner-III-Neemrana-II, TL02 | 396 | 9 | 3, 5, 7, 8, 41, 42, 43 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | issues_support, pending_amendments, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 5: Priority Projects to be completed 7: Pending Amendments 8: List of Running Substation & TL Project (Cont..) 41: TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) 42: TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413) 43: Issues / Support Required
TA 414 | TL | WR2 | 765KV D/C Vataman - Navsari Transmission Line (TA- 414) | 11/12/25 | 30/10/26 | 765 kV D/C Vataman Navsari Line | 656 | 87 | 3, 9, 11, 12, 13 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | issues_support, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 9: List of Running Substation & TL Project 11: TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) 12: TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414) 13: Issues / Support Required
TA 416 | TL | NR3 | 765 KV D/C Neemrana II Bareilly Line (TA- 416) | 06/11/25 | 31/05/26 | 765 kV D/C Neemrana-II-Bareilly , TL03 | 447 | 2 | 3, 5, 8, 63, 64 | activity_status, front_availability, manpower, monthly_plan, project_contract_header, running_project_master, supply_status | project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 5: Priority Projects to be completed 8: List of Running Substation & TL Project (Cont..) 63: TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416) 64: TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416)
TA 418 | TL | SR1 | 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) | 11/12/25 | 30/06/26 | 765 KV D/C Kopal 2 - Raichur, TL01 | 154 | 5 | 3, 5, 9, 66, 67, 68 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | issues_support, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 5: Priority Projects to be completed 9: List of Running Substation & TL Project 66: TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) 67: TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) 68: TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418)
TA 419 | TL | NR1 | 765KV D/C Sikar II – Narela (TA- 419) | 05/05/25 | 30/11/26 | 765 kV D/C Sikar II to Narela TL- TL02 | 491 | 51 | 3, 6, 8, 56, 57, 58 | activity_status, front_availability, issues_support, manpower, monthly_plan, project_contract_header, running_project_master, supply_status | issues_support, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 6: Support Required 8: List of Running Substation & TL Project (Cont..) 56: TL02 - 765KV D/C Sikar II – Narela (TA- 419) 57: TL02 - 765KV D/C Sikar II – Narela (TA- 419) 58: Issues / Support Required
TA 421 | TL | SR1 | 765KV D/C Bidar Ps – Maheshwaram (TA- 421) | 14/11/25 | May’26 | 765kV D/C Bidar PS - Maheshwaram | 382 | 4 | 3, 5, 7, 9, 69, 70, 71 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | issues_support, pending_amendments, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 5: Priority Projects to be completed 7: Pending Amendments 9: List of Running Substation & TL Project 69: TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) 70: TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421) 71: Issues / Support Required
TA 504 | TL | NWR | 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) | 22/06/26 | 28/09/26 | 765 KV D/C Rishabdeo – Mandsaur Line (Part I) & LILO | 255 | 31 | 3, 8, 46, 47, 48 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | issues_support, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 8: List of Running Substation & TL Project (Cont..) 46: TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) 47: TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) 48: Issues / Support Required
TA 505 | TL | NWR | 765KV D/C Beawar-Mandsaur TL (TA- 505) | 21/06/26 | 30/09/26 | 765 KV D/C Beowar-Mandsaur TL | 561 | 48 | 3, 8, 49, 50, 51 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | issues_support, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 8: List of Running Substation & TL Project (Cont..) 49: TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) 50: TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505) 51: Issues / Support Required
TA 506 | TL | NWR | 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) | Aug’26 | Oct’26 | 400 KV D/C Sirohi – Chittorgarh Transmission Line | 592 | 38 | 3, 7, 8, 52, 53, 54 | activity_status, front_availability, issues_support, manpower, monthly_plan, pending_amendments, project_contract_header, running_project_master, supply_status | issues_support, pending_amendments, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 7: Pending Amendments 8: List of Running Substation & TL Project (Cont..) 52: TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) 53: TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) 54: Issues / Support Required
TA 509 | TL | WR2 | 765KV D/C Mandsaur – Kurawar Part I (TA- 509) | 25/10/26 | 25/10/26 | 765 kV D/C Mandsaur - Korawar | 473 | 68 | 3, 9, 14, 15 | activity_status, front_availability, issues_support, manpower, project_contract_header, running_project_master, supply_status | issues_support, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 9: List of Running Substation & TL Project 14: TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509) 15: Issues / Support Required
TA 510 | TL | WR2 | 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) | 25/10/26 | 15/03/27 | 765 kV D/C South Olpad - Ahmedabad | 577 | 192 | 3, 9, 16, 17 | activity_status, front_availability, issues_support, manpower, pending_amendments, project_contract_header, running_project_master, supply_status | issues_support, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 9: List of Running Substation & TL Project 16: TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) 17: Issues / Support Required
TA 512 | TL | NWR | 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) | 02/12/26 | 02/12/26 | 765 KV D/C Bikaner Siwani | 474 | 84 | 3, 7, 8, 44, 45 | activity_status, front_availability, issues_support, manpower, pending_amendments, project_contract_header, running_project_master, supply_status | issues_support, pending_amendments, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 7: Pending Amendments 8: List of Running Substation & TL Project (Cont..) 44: TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) 45: Issues / Support Required
TA 513 | TL | NR2 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) | 22/12/26 | -- | 400 kv D/C Siwani - Patran, part 3 | 665 | 233 | 3, 6, 8, 60, 61 | activity_status, front_availability, issues_support, manpower, project_contract_header, running_project_master, supply_status | issues_support, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 6: Support Required 8: List of Running Substation & TL Project (Cont..) 60: 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) 61: Issues / Support Required
TA 514 | TL | WR2 | 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) | 22/07/28 | 22/07/28 | 800 KV HVDC TL-02 KPS III Khavda - Nagpur | 780 | 533 | 3, 6, 9, 18, 19 | activity_status, front_availability, issues_support, manpower, pending_amendments, project_contract_header, running_project_master, supply_status | issues_support, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 6: Support Required 9: List of Running Substation & TL Project 18: TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) 19: Issues / Support Required:-
TA 515 | TL | WR2 | 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) | 11/08/28 | 11/08/28 | 800 KV HVDC TL-03 KPS III Khavda - Nagpur | 348 | 206 | 3, 6, 9, 20, 21 | activity_status, front_availability, issues_support, manpower, pending_amendments, project_contract_header, running_project_master, supply_status | issues_support, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 6: Support Required 9: List of Running Substation & TL Project 20: TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) 21: Issues / Support Required
TA 601 | TL | SR1 | 765kV D/C Kurnool IV – Bidar Line (TA- 601) | 12/04/27 | 12/04/27 | 765 KV D/C Kurnool IV - Bidar Line | 515 | 178 | 3, 9, 72, 73 | activity_status, front_availability, issues_support, manpower, project_contract_header, running_project_master, supply_status | issues_support, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 9: List of Running Substation & TL Project 72: TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601) 73: Issues / Support Required
TA 602 | TL | WR2 | 80800 KV HVDC KPS-II to Nagpur (TA- 602) | 12/11/28 | 12/09/28 | 800 KV HVDC TL06 KPS-III Khavda to Nagpur | 612 | 436 | 3, 6, 9, 22, 23 | activity_status, front_availability, issues_support, manpower, project_contract_header, running_project_master, supply_status | issues_support, project_status, project_summary, running_project_master | 3: Summary of Projects under Execution by KEC (TL Projects) 6: Support Required 9: List of Running Substation & TL Project 22: TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602) 23: Issues / Support Required
A920 | TL | NER | 132 KV D/C Tawang-Lumla Line (A920) | 12/04/27 | 12/04/27 | 132 KV D/C Tawang -Lumla Line | 90 | 7 | 75, 76 | activity_status, front_availability, manpower, monthly_plan, project_contract_header, supply_status | project_status | 75: TW24 - 132kV Tawang-Lumla Line 76: TW24 - 132kV Tawang-Lumla Line
A-303/304 | TL | ER1 | 400 KV D/C Twin Line Latehar- Patraru (A303/304) | -- | -- | JSEB Lines | 249 | 10 | 77 | activity_status, issues_support, manpower, supply_status | project_status | 77: 400 KV D/C Twin Line Latehar- Patraru
A-722/723 | TL | ER2 | Sikkim Tower Pkg TK04 (A-722/723) | -- | -- | Sikkim Tower PKg TK-04 | 360 | 32 | 78, 79, 80, 81, 82 | activity_status, issues_support, monthly_plan, supply_status | project_status | 78: Sikkim Tower Pkg TK04 79: Sikkim Tower Pkg TK04 80: Sikkim Tower Pkg TK04 81: Sikkim Tower Pkg TK04 82: Sikkim Tower Pkg TK04
SA-417 | SS | NR1 |  |  |  | 765kV Narela GIS Extension - SS02 | 123 | 5
SA-410 | SS | NWR |  |  |  | 765/400/220 kV Bhadla SS & Sikar extn. | 223 | 19
SA-420 | SS | SR1 |  |  |  | 765kV Narendra GIS Extn - SS07T | 164 | 6
SA-603 | SS | SR1 |  |  |  | 765kV New Narendra GIS extn. Pkg-SS-64T | 98 | 79
SA-502 | SS | WR1/WR2 |  |  |  | SS-118 (Extension of 765/400kV Maheshwaram, 765/400 KPS3, 765/400 Phadge & 220kV Raigarh GIS | 413 | 59
SA-503 | SS | WR2 |  |  |  | SS-39T - (Extn of 765/400kV KPS-2 GIS) | 390 | 27
SA-508 | SS | WR2 |  |  |  | SS-33T1) 765kV South Olpad GIS2) Extn. Of 765kV Vadodara GIS3) Extn. Of 765kV Ahmedabad SS | 627 | 250

## Skipped SS Scope
project_code | tl_ss | region | running_project_details | project_value_cr | ueob_cr | presentation_slides | presentation_requirements | project_name_from_summary | scheduled_completion | expected_completion | presentation_slide_types | presentation_slide_titles
SA-417 | SS | NR1 | 765kV Narela GIS Extension - SS02 | 123 | 5
SA-410 | SS | NWR | 765/400/220 kV Bhadla SS & Sikar extn. | 223 | 19
SA-420 | SS | SR1 | 765kV Narendra GIS Extn - SS07T | 164 | 6
SA-603 | SS | SR1 | 765kV New Narendra GIS extn. Pkg-SS-64T | 98 | 79
SA-502 | SS | WR1/WR2 | SS-118 (Extension of 765/400kV Maheshwaram, 765/400 KPS3, 765/400 Phadge & 220kV Raigarh GIS | 413 | 59
SA-503 | SS | WR2 | SS-39T - (Extn of 765/400kV KPS-2 GIS) | 390 | 27
SA-508 | SS | WR2 | SS-33T1) 765kV South Olpad GIS2) Extn. Of 765kV Vadodara GIS3) Extn. Of 765kV Ahmedabad SS | 627 | 250

## DPR File Inventory
project_code | dpr_file | dpr_date | open_status | sheet_count | categories | sheet_names | path
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | ok | 13 | earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, statutory_crossing, stringing, summary_status, supply, survey_soil, visual_l2 | NKTL DPR PGCIL; Visual Chart NKTL; NKTL DPR; Sheet2; Sheet1; Visual Chart-Old; Location wise status; Survey Status; Soil investigation; Crossing Details; Line Scenario; Sheet3; Supply Status | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 310 - DPR - 2026-01-12.xlsx
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | ok | 21 | earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, statutory_crossing, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | 101-276 FINAL 11-07-2025; 765KV TA 325 ANTL; Project Details; Visual chart Compiled; Soil Invst.; Foundation-Compliled; FDN-VDRA; FDN-NVSR; Erection-Compiled; EREC-VDRA; EREC-NAV; Stringing Compiled; Striging-VDRA; String-Nav; Visual chart NAVSARI Revised; Crossing Vadodara; Crossing Navsari ; Gangs; OPGW; Splicing; Add. Earthing | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 325 - DPR - 2026-01-19.xlsx
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | repaired_defined_names (ValueError) | 32 | earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, statutory_crossing, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | TA413_PBNTL; Visual Chart; Stretch readiness ; Stringing; Erection; L2 Plan vs Actual; Survey summary; Detailed Survey ; Check Survey ; Earthing; Tack Welding; Final checking; Bird Guard ; Accessories; OPGW; Foundation; JUMPER Details; ROW Tracker; S-Curve FDN; S-Curve Erection; S-Curve Stringing; Supply Status; Hardware Supply; Crossing status; Tower Abstract sheet; Statutory Proposals; Tower Abstarct ; Location Summary; Foundation Daily Progress; Tower PRS abstract ; Stretch readiness (2); Area | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 413 - DPR - 2026-05-20.xlsx
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | repaired_defined_names (ValueError) | 25 | earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, statutory_crossing, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | Project Details; 765KV TA 414 VNTL; VNTL - KEC; Sheet5; Sheet3; Sheet1; DPR Sheet; FDN; FDN Completed; Erection ; Erection Completed ; Erection Compiled; Stringing; Stringing Completed; Stringing Compiled; Sheet6; Sheet4; Sheet7; Visual chart; Pile Fdn; Crossing; Sheet2; Survey; Soil Inv.; Survey Anx | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 414 - DPR - 2026-05-21.xlsx
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | ok | 12 | earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, statutory_crossing, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | Project Details; MASTER SHEET; Erection Compiled ; Stringing compiled; Progress.; Visual chart.; PENDING FDN DETAILS; PENDING ERE DETAILS; TSE-MANUAL-LT-11KV-33KV Details; Crossing Details; TS; TS (2) | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 416 - DPR - 2026-05-17.xlsx
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | ok | 12 | earthing_tack, erection, foundation, project_details, row_hindrance, statutory_crossing, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | MASTER SHEET; Progress; Erection Compiled; Stringing Compiled; Visual Chart; ROW TRACKER; PENDING FDN DETAILS; TSE-MANUAL-LT-11KV-33KV Details; Crossing Details; Project Details; TS; TS (2) | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 418 - DPR - 2026-05-21.xlsx
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | repaired_defined_names (ValueError) | 41 | commercial, earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, statutory_crossing, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | Const Revenue; DPR_TA419; Soil Inv; TOWER SUPPLY; RATE; Tack Welding; Ins Hosting; Stringing; L2; Supply Status; ROW; Tower Schedule; FDN; Latest Tower Schedule; Sheet8; Sheet7; Erection productivity; Foundation Daily Progress; Sheet9; Summary; Sheet10; Visual Chart; Tower schedule_07.03.25; ERT; ERECTION COMPILED; Stringing Stretch Readiness; Project details; Detailed Survey; Supply; Stock Details; PGCIL; ; ; dont change; TOWER ABSTRACT; Pkg 2_Foundation; Foundation Daily Progresss; Erection Daily Progress; Statutory; Pkg 2_Erection; Pkg2_Stringing | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 419 - DPR - 2026-05-20.xlsx
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | ok | 15 | earthing_tack, erection, foundation, opgw_accessories, project_details, statutory_crossing, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | Project Details; Master Sheet; ProGress Sheet ; Erection Compiled ; Stringing Compiled ; Erection Productivity ; Visual Chart ; Stubs and Towers ; SuPPLY ; X-ing Details ; Tack Welding ; Tower Accessories ; Tower Tightening ; Hardwares & Tower Accessories ; Sheet1 | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 421 - DPR - 2026-05-20.xlsx
TA 504 | TA 504 - DPR - 2026-05-21.xlsx | 2026-05-21 | repaired_defined_names (ValueError) | 8 | earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | DPR_TA-504; Erection compiled; Tightening; Stringing Compiled; VC_RMTL; VC_Lilo; Project Details; Location Summary | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 504 - DPR - 2026-05-21.xlsx
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | ok | 15 | earthing_tack, erection, foundation, project_details, row_hindrance, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | DPR-Summary; Sheet1; Project Details; Sheet5; Foundation; Balance Erc-RAJ; ERC ROW-MP; Erection Compiled; Stringing Compiled; Visual Chart; Erection Productivity; Earthing Status; Sheet4; Sheet3; Sheet2 | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 505 - DPR - 2026-05-19.xlsx
TA 506 | TA 506 - DPR - 2026-05-21.xlsx | 2026-05-21 | repaired_defined_names (ValueError) | 7 | earthing_tack, erection, foundation, project_details, row_hindrance, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | DPR_TA-506; Erection compiled; Tightening; Stringing; Visual Chart; Project Details; Location Summary | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 506 - DPR - 2026-05-21.xlsx
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | ok | 15 | earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, statutory_crossing, stringing, summary_status, supply, survey_soil, visual_l2 | VC-765kV MKTL; SUMMARY; FDN pivot; Erc pivot; ERECTION; FOUNDATION; XING; EARTHING; DPR; SUPPLY; CST Gantry To AP 68 Common Poin; Sheet1; SURVEY SUMMARY; SURVEY STATUS ; Erection productivity | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 509 - DPR - 2026-05-18.xlsx
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | repaired_defined_names (ValueError) | 25 | earthing_tack, erection, foundation, project_details, row_hindrance, statutory_crossing, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | 765KV TA 414 VNTL; 765KV ASOTL; Project Details; AOTL - KEC; DPR Sheet; Sheet5; Sheet3; Sheet1; Survey Anx; Soil Inv.; Survey; FDN; Erection ; Erection Compiled ; Visual chart 1 ; Pile Foundation; Sheet6; Sheet4; Sheet7; Tack welding; Stringing Compiled; String; Crossing; Tree Enumeration; Sheet2 | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 510 - DPR - 2026-05-20.xlsx
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | ok | 25 | earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, statutory_crossing, stringing, summary_status, supply, survey_soil, visual_l2 | Summary S; Supply Status; Summary E; DPR Sheet ; DS; CS; Hindrance Record; Earthing; Foundation; Erection Compiled; Tack Welding; Visual Chart; WIP; Statuary clearance; Stringing; OPGW; Accessories; Shield Wire Earthing; TS Gantry - AP47; Project Details; Sheet1; L3 Plan; Supply DPR ; Power line Crossings ; Hardware | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 512 - DPR - 2026-05-20.xlsx
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | ok | 34 | commercial, earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, statutory_crossing, stringing, summary_status, supply, survey_soil, visual_l2 | Concrete; Summary DPR; DPR S-F & S-P (2); Summary; ERT; LS; Survey ; T.Marking; VC -SF; VC -SP; Ere S-P ; Ere S-F ; FDN S-F; FDN S-P; T.Abstract; Supply.; Crossing status; Erection Compiled; Sheet5; Earthing S-P; Supply; Earthing S-F; ROW S-F; Proposal; Proposal .; ROW S-P; Master SP; Master SF; TS SP ; TS SF; Sheet4; Sheet2; Sheet1; Forest | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 513 - DPR - 2026-05-19.xlsx
TA 515 | TA 515 - DPR - 2026-05-11.xlsx | 2026-05-11 | ok | 4 | earthing_tack, erection, foundation, project_details, row_hindrance, statutory_crossing, summary_status, supply, survey_soil, visual_l2 | DPR; Store Stock; Visual chart; Erection Compiled | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 515 - DPR - 2026-05-11.xlsx
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | 2026-05-20 | ok | 11 | earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, statutory_crossing, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | Visual Chart ; Master Sheet; Progress Sheet ; ROW; SUPPLY; Erection Compiled; X-ing Details ; Visual Chart; Foundation & Erection; STRG Stretch ; Stringing Compiled | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 601 - DPR - 2026-05-20.xlsx
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | ok | 13 | earthing_tack, erection, foundation, project_details, row_hindrance, statutory_crossing, summary_status, supply, survey_soil, visual_l2 | DPR-KEC; Survey details; Visual Chart ; Detail Survey; Check Survey ; FDN; Composite-Survey(05-04-2026); Erection; Earthing; WIP; statuary clearance; statuary clearance (2); Supply Status | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TA 602 - DPR - 2026-05-18.xlsx
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | ok | 42 | commercial, earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, statutory_crossing, stringing, summary_status, supply, survey_soil, visual_l2 | TB401 DPR.....; Eng.; Fdn (Pkg -G Section -I); TB401 DPR; Foundation (Pkg-F) ; Earthing (PKG-F); Project Details; Progress; Hindrance; Foundation (Pkg-G); Earthing (PKG-G); Benching Status-F; Revetment Pkg-G; Benching Status-G; Earthing Pkg -G Ist section; Earthing balance; Tack Welding - PKG-F; Tack Welding - PKG-G; Painting - PKG-F; Painting - PKG-G; Idling details from Aug; Erection Compiled; Crane Erection PKG-G; Erection Productivity; Eretion - PKG-F; Sheet1; JMC 27.9.23; Jumpering-G; Insulator Hoisting - F; Insulator Hoisting - G; Jumpering-F; Stringing - PKG-F; Stringing Productivity; Stringing - PKG-G; OPGW PKG-G; OPGW PKG-F; Crossing; Visual Chart (Pkg -F.); Clear locs shared by client; Visual Chart PKG-G; Sheet3; Sheet2 | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TB 401 - DPR - 2025-12-25.xlsx
TB 408 | TB 408 - DPR - 2026-05-11.xlsx | 2026-05-11 | repaired_defined_names (ValueError) | 3 | erection, project_details, stretch_readiness, stringing, summary_status, supply | Project Details; Erection Compiled ; Stringing Compiled | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TB 408 - DPR - 2026-05-11.xlsx
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | ok | 14 | earthing_tack, erection, foundation, opgw_accessories, project_details, statutory_crossing, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | Detail Survey-220kV; Check Survey-220kV; Detail Survey-132kV; Check Survey-132kV; Summary; Statutory; Progress-132kV; Progress-220kV; Stringing-220kV; Stringing-132KV; VC-220kV; VC-132kV; Supply; Mail Body | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TB 501 - DPR - 2026-05-20.xlsx
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | ok | 33 | earthing_tack, erection, foundation, project_details, row_hindrance, statutory_crossing, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | 765kV Summery; Check Survey Status; Check Survey; Sheet8; Sheet2; Sheet1; VC 51-96; VC; ROW; June; Check survey Loop out; Check survey Loop In; Foundation; Royalty; Sheet14; Sheet7; Project Details; Erection ; Completion date; Erection Compiled ; Earthing; Stringing Compiled ; Soil Investigation; Sheet9; VC ; Sheet6; VC 51-121; Sheet5; Sheet3; Tower Schedule; Visual Chart; L2 Vs Actual Progress Chart (2); Sheet4 | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TB 507 - DPR - 2026-05-20.xlsx
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | ok | 37 | earthing_tack, erection, foundation, project_details, row_hindrance, statutory_crossing, stretch_readiness, stringing, summary_status, supply, survey_soil, visual_l2 | 400kV Summery; Check Survey ; Check Survey Status; Check Survey; Sheet8; Sheet2; Project Details; Statutory Clearence; Crossing Proposal; Sheet1; VC 51-96; VC; ROW; June; Foundation; Royalty; Sheet14; Sheet7; Erection ; Completion date; Erection Compiled ; Earthing; Final Check In And Tack Welding; Sheet10; Stringing Compiled ; Soil Investigation; Sheet9; VC ; Sheet6; VC 51-121; Sheet5; Sheet3; Tower Schedule; Visual Chart; L2 Vs Actual Progress Chart; L2 Vs Actual Progress Chart (2); Sheet4 | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TB 507 [MAIN] - DPR - 2026-05-20.xlsx
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | ok | 75 | commercial, earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, statutory_crossing, stringing, summary_status, supply, survey_soil, visual_l2 | TB401 DPR.....; Eng.; Fdn (Pkg -G Section -I); Sheet2; Sheet3; Sheet4; Sheet5; ROW; Sheet13 (2); TB-605; Sheet19; Sheet16; Sheet14; Sheet12; Sheet13; Sheet15; TB401 DPR; Survey-Summary; Sheet6; Approved Survey; Approved CS J-S Line; Approved CS K-S Line; Foundation JS-Line -Jammu; Sheet10; Erection -Jammu; Vertical Chart -JS Line Jammu ; Sheet17; Erection -SK; Sheet7; Sheet8; LILO; Erection-Punjab; Vertical Chart -JS Line Punjab; Foundation -JS Line- Punjab; Sheet9; ROW Front vs Progress; Hindrance; Foundation -KS Line; Manpower; Sum; Sheet18; JS-Supply Stubs; JS Supply Towers; SK Supply Stubs; SK Supply Towers; Sheet11; Planned Vs Actual -FDN; Supply Status; Material Status-Jammu-Punjab; Material Status-Punjab; Earthing (PKG-F); Earthing (PKG-G); Revetment Pkg-G; Benching Status-F; Benching Status-G; Earthing Pkg -G Ist section; Earthing balance; Tack Welding - PKG-G; Tack Welding - PKG-F; Painting - PKG-G; Painting - PKG-F; Eretion - PKG-G; Eretion - PKG-F; Sheet1; JMC 27.9.23; Jumpering-G; Insulator Hoisting - F; Insulator Hoisting - G; Jumpering-F; Stringing - PKG-F; Stringing - PKG-G; OPGW PKG-G; OPGW PKG-F; Crossing; Clear locs shared by client | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TB 605 - DPR - 2026-05-20.xlsx
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | ok | 12 | earthing_tack, erection, foundation, project_details, row_hindrance, statutory_crossing, stringing, summary_status, supply, survey_soil, visual_l2 | Master Sheet; DPR Sum.; Master Sheet ; WIP-FDN; Gang Movement; Support Required; WIP-ERC; Line Details; Visual_Chart; Foundation Activity; Supply; Sheet2 | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\DPRs\TB 608 - DPR - 2026-04-05.xlsm

## DPR Sheet Inventory
project_code | dpr_file | dpr_date | sheet_name | max_row | max_col | categories | header_candidates | sample_lines | open_status
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | NKTL DPR PGCIL | 33 | 11 | summary_status, survey_soil |  | KEC INTERNATIONAL LIMITED DAILY PROGRESS REPORT : SUBMISSION STATUS AS ON ¦ 2026-01-12 00:00:00 Name of the Project: ¦ TW02: 400kV M/c Navasari-Kala Transmission Line. NOA Ref.No: ¦ 5002002222/Tower/DOM/A02-CC CS -3/NOA-II/WR2-400010 ROUTE ALIGNMENT PROGRESS SUMMARY TOTAL QTY (Tentative) ¦ COMPLETED UP TO PREV MONTH ¦ COMP. IN CURRENT MONTH ¦ CUMULATIVE ¦ BAL.QTY 8.572 ¦ 8.572 ¦ 8.572 SOIL INVESTIGATION PROGRESS SUMMARY | ok
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | Visual Chart NKTL | 55 | 25 | earthing_tack, erection, foundation, row_hindrance, statutory_crossing, stringing, summary_status, visual_l2 | R4: Sl.No ¦ Type of Work ¦ Unit ¦ Scope ¦ ROW ¦ Drawing Req. ¦ Comp. ¦ Balance ¦ WIP ¦ Front Available ¦ Remark R5: Erection Progress ¦ 220 KV Line X-Ing ¦ National Highway Crossing ¦ 01 ¦ Tower Foundation ¦ Nos. ¦ 29 ¦ 4 ¦ 22 ¦ 7 ¦ 2 ¦ 1 R7: Excavation Progress ¦ Stringing Progress ¦ 02 ¦ Monopole Foundation ¦ Nos. ¦ 8 ¦ 1 ¦ 3 ¦ 5 ¦ 1 ¦ 1 ¦ 2 waterlogged R9: Stringing Complete ¦ 03 ¦ Tower Erection ¦ Nos. ¦ 29 R11: 66 KV Line X-Ing ¦ Railway Crossing. ¦ 04 ¦ Monopole Erection. ¦ Nos. ¦ 8 | Name of Line :- TW02: 400KV D/C Navsari-Kala Transmission Line. Agency: M/S KEC International Limited ¦ Date:- ¦ 2026-01-12 00:00:00 LEGENDS ¦ ABSTRACT Sl.No ¦ Type of Work ¦ Unit ¦ Scope ¦ ROW ¦ Drawing Req. ¦ Comp. ¦ Balance ¦ WIP ¦ Front Available ¦ Remark Erection Progress ¦ 220 KV Line X-Ing ¦ National Highway Crossing ¦ 01 ¦ Tower Foundation ¦ Nos. ¦ 29 ¦ 4 ¦ 22 ¦ 7 ¦ 2 ¦ 1 Foundation Progress Excavation Progress ¦ Stringing Progress ¦ 02 ¦ Monopole Foundation ¦ Nos. ¦ 8 ¦ 1 ¦ 3 ¦ 5 ¦ 1 ¦ 1 ¦ 2 waterlogged 132 KV Line X-Ing | ok
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | NKTL DPR | 141 | 26 | project_details, summary_status, survey_soil, visual_l2 | R1: Project Code ¦ TA 310 ¦ Date:- ¦ 2026-01-12 00:00:00 ¦ LOA Start Date ¦ 2022-08-11 00:00:00 ¦ President - T&D ¦ Ganesh Srinivasan R3: Client Name ¦ Power Grid Corporation of India Limited (PGCIL) ¦ LOA Value ¦ Amndt-11 ¦ LOA End Date ¦ 2023-11-10 00:00:00 ¦ Vice President ¦ Arun Felbin R R4: LOAValue / LE Value ¦ Ex-Work Price component ¦ 208.3623222 ¦ 242.5046924 ¦ Regional Manager ¦ Nitin Bendale R5: Local Transportation, In-transit insurance, loading-unloading Charges etc. (CR) ¦ 3.1806198 ¦ 4.2274925 ¦ Time Extn ¦ 2026-03-31 00:00:00 ¦ Chief Manager R9: Activity ¦ Unit ¦ LOA Qty. ¦ Final Estimated Quantity ¦ Cumulative L2 till Dec-2025 ¦ Cumulative Progress till Dec'2025 ¦ Balance ¦ L2 for Jan'26 ¦ Plan for Jan'2026 ¦ Today's Progress ¦ Progress till for Jan'2026 ¦ WIP ¦ Gangs at Present ¦ Cumulative Progress till date ¦ Balance Work ¦ Remarks | Project Code ¦ TA 310 ¦ Date:- ¦ 2026-01-12 00:00:00 ¦ LOA Start Date ¦ 2022-08-11 00:00:00 ¦ President - T&D ¦ Ganesh Srinivasan Project Name ¦ TW02: 400kV M/c Navasari-Kala Transmission Line. ¦ Chief Executive - T&D ¦ Rajinder Gupta Client Name ¦ Power Grid Corporation of India Limited (PGCIL) ¦ LOA Value ¦ Amndt-11 ¦ LOA End Date ¦ 2023-11-10 00:00:00 ¦ Vice President ¦ Arun Felbin R LOAValue / LE Value ¦ Ex-Work Price component ¦ 208.3623222 ¦ 242.5046924 ¦ Regional Manager ¦ Nitin Bendale Local Transportation, In-transit insurance, loading-unloading Charges etc. (CR) ¦ 3.1806198 ¦ 4.2274925 ¦ Time Extn ¦ 2026-03-31 00:00:00 ¦ Chief Manager Installation Charges (CR) ¦ 74.1209972 ¦ 124.7376651 ¦ Project Manager ¦ Vivek Kumar Gupta Total Contract Value ( CR) ¦ 285.66393919999996 ¦ 371.46985 ¦ Planning Engineer ¦ Dillip Kumar Jena Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | ok
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | Sheet2 | 34 | 11 | row_hindrance | R4: Row Labels ¦ DFR ¦ DRY ¦ PS ¦ WBC ¦ WET ¦ WET PADDY ¦ WFR ¦ WFR(3M RC) ¦ WFR,3M RC ¦ Grand Total | Count of Classification ¦ Column Labels Row Labels ¦ DFR ¦ DRY ¦ PS ¦ WBC ¦ WET ¦ WET PADDY ¦ WFR ¦ WFR(3M RC) ¦ WFR,3M RC ¦ Grand Total QA+0 ¦ 2 ¦ 7 ¦ 3 ¦ 1 ¦ 13 QA+3 ¦ 2 ¦ 2 ¦ 3 ¦ 3 ¦ 10 QA+6 ¦ 2 ¦ 7 ¦ 4 ¦ 1 ¦ 14 QA+9 ¦ 3 ¦ 3 ¦ 11 ¦ 1 ¦ 18 QB1+0 ¦ 1 ¦ 1 QB1+6 ¦ 1 ¦ 1 ¦ 2 | ok
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | Sheet1 | 32 | 12 | row_hindrance | R2: Row Labels ¦ DFR ¦ DRY ¦ PS ¦ WBC ¦ WET ¦ WET PADDY ¦ WFR ¦ WFR(3M RC) ¦ WFR,3M RC ¦ Grand Total | Row Labels ¦ DFR ¦ DRY ¦ PS ¦ WBC ¦ WET ¦ WET PADDY ¦ WFR ¦ WFR(3M RC) ¦ WFR,3M RC ¦ Grand Total QA+0 ¦ 2 ¦ 7 ¦ 3 ¦ 1 ¦ 13 QA+3 ¦ 2 ¦ 2 ¦ 3 ¦ 3 ¦ 10 QA+6 ¦ 2 ¦ 7 ¦ 4 ¦ 1 ¦ 14 QA+9 ¦ 3 ¦ 3 ¦ 11 ¦ 1 ¦ 18 QB1+0 ¦ 1 ¦ 1 QB1+6 ¦ 1 ¦ 1 ¦ 2 QB2+0 ¦ 1 ¦ 1 ¦ 2 | ok
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | Visual Chart-Old | 287 | 44 | earthing_tack, erection, foundation, project_details, row_hindrance, statutory_crossing, stringing, summary_status, visual_l2 | R5: 5 ¦ Sl.No ¦ Type of Work ¦ Unit ¦ Scope ¦ L2 Till Date ¦ Completion ¦ Balance ¦ WIP ¦ ROW ¦ Front Available ¦ Sl.No ¦ Type of Work ¦ Unit ¦ Scope ¦ L2 Till Date ¦ Completion ¦ Balance R6: 6 ¦ Erection Progress ¦ 01 ¦ Foundation ¦ Nos. ¦ 152 ¦ 134 ¦ 25 ¦ 127 ¦ 2 ¦ 123 ¦ 2 ¦ 01 ¦ Foundation ¦ Nos. ¦ 151 ¦ 134 ¦ 118 ¦ 33 R7: 7 ¦ Foundation Progress ¦ National Highway Crossing R8: 8 ¦ Excavation Progress ¦ 02 ¦ Erection ¦ Nos. ¦ 152 ¦ 134 ¦ 152 ¦ 2 ¦ 149 ¦ 1 ¦ 02 ¦ Erection ¦ Nos. ¦ 151 ¦ 134 ¦ 68 ¦ 83 R10: 10 ¦ 03 ¦ Stringing ¦ Km. ¦ 52.821033 ¦ 52.39 ¦ 52.821033 ¦ 03 ¦ Stringing ¦ Km. ¦ 52.816 ¦ 39 ¦ 52.816 | 1 ¦ VISUAL CHART 2 ¦ Name of Line :- TW02: 400KV M/C Navsari-Magarwada Transmission Line. 3 ¦ Agency: M/S KEC International Limited ¦ Date:- ¦ 2026-01-12 00:00:00 4 ¦ LEGENDS ¦ ABSTRACT ¦ Name of Line :- TW02: 400KV M/C Navsari-Magarwada Transmission Line. 5 ¦ Sl.No ¦ Type of Work ¦ Unit ¦ Scope ¦ L2 Till Date ¦ Completion ¦ Balance ¦ WIP ¦ ROW ¦ Front Available ¦ Sl.No ¦ Type of Work ¦ Unit ¦ Scope ¦ L2 Till Date ¦ Completion ¦ Balance 6 ¦ Erection Progress ¦ 01 ¦ Foundation ¦ Nos. ¦ 152 ¦ 134 ¦ 25 ¦ 127 ¦ 2 ¦ 123 ¦ 2 ¦ 01 ¦ Foundation ¦ Nos. ¦ 151 ¦ 134 ¦ 118 ¦ 33 7 ¦ Foundation Progress ¦ National Highway Crossing 8 ¦ Excavation Progress ¦ 02 ¦ Erection ¦ Nos. ¦ 152 ¦ 134 ¦ 152 ¦ 2 ¦ 149 ¦ 1 ¦ 02 ¦ Erection ¦ Nos. ¦ 151 ¦ 134 ¦ 68 ¦ 83 | ok
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | Location wise status | 23 | 15 | foundation, project_details, row_hindrance, summary_status, supply, survey_soil | R2: Status Summary: ¦ Tower ¦ Monopole ¦ Date:- ¦ 2026-01-07 00:00:00 R6: Work in Progress (WIP): ¦ 4 ¦ 4 R7: Work front Available:- ¦ 2 ¦ 1 ¦ 1 R8: ROW Pending: ¦ 8 ¦ 7 ¦ 1 R9: Sl. No. ¦ Loc. No. ¦ T.O.T ¦ Tower configuration ¦ Balance Location status ¦ Start Date ¦ End Date ¦ Foundation Gang ¦ Present Status ¦ Remark. | Name of the Line:-400kV D/c Navasari-Kala Transmission Line. Status Summary: ¦ Tower ¦ Monopole ¦ Date:- ¦ 2026-01-07 00:00:00 Total Locations: ¦ 37 ¦ 29 ¦ 8 Completed: ¦ 23 ¦ 21 ¦ 2 Balance: ¦ 14 ¦ 8 ¦ 6 Work in Progress (WIP): ¦ 4 ¦ 4 Work front Available:- ¦ 2 ¦ 1 ¦ 1 ROW Pending: ¦ 8 ¦ 7 ¦ 1 | ok
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | Survey Status | 59 | 24 | summary_status, survey_soil | R1: Survey Status for 400Kv M/C New Navsari to Magarwada Transmission Line. ¦ Date ¦ 2026-01-12 00:00:00 R2: Sl. No. ¦ Section ¦ Detail Survey ¦ Check Survey R3: Complited ¦ Submitted Kms with Date ¦ Revised ¦ Approved with Date ¦ Revised ¦ Complited ¦ Submitted Kms with Date ¦ Revised ¦ Approved with Date ¦ Revised ¦ Remarks ¦ Detailed Survey Status R4: 8.882 ¦ 8.822 ¦ 8.822 ¦ Date ¦ Date ¦ 7.212 ¦ Date ¦ Date ¦ 8.822 ¦ Date ¦ Date ¦ Date ¦ AP-19/0 ¦ TO ¦ AP-28/0 ¦ = ¦ 8.564 ¦ Approved 15.10.2022 R5: 1 ¦ 67/3-76/0 ¦ 8.822 ¦ 8.822 ¦ 2025-03-17 00:00:00 ¦ 7.212 ¦ 21.03.2025 ¦ 8.822 ¦ 7.583 ¦ 2025-03-28 00:00:00 ¦ AP-38/0 ¦ TO ¦ AP-44/0 ¦ = ¦ 11.051 ¦ Approved | Survey Status for 400Kv M/C New Navsari to Magarwada Transmission Line. ¦ Date ¦ 2026-01-12 00:00:00 Sl. No. ¦ Section ¦ Detail Survey ¦ Check Survey Complited ¦ Submitted Kms with Date ¦ Revised ¦ Approved with Date ¦ Revised ¦ Complited ¦ Submitted Kms with Date ¦ Revised ¦ Approved with Date ¦ Revised ¦ Remarks ¦ Detailed Survey Status 8.882 ¦ 8.822 ¦ 8.822 ¦ Date ¦ Date ¦ 7.212 ¦ Date ¦ Date ¦ 8.822 ¦ Date ¦ Date ¦ Date ¦ AP-19/0 ¦ TO ¦ AP-28/0 ¦ = ¦ 8.564 ¦ Approved 15.10.2022 1 ¦ 67/3-76/0 ¦ 8.822 ¦ 8.822 ¦ 2025-03-17 00:00:00 ¦ 7.212 ¦ 21.03.2025 ¦ 8.822 ¦ 7.583 ¦ 2025-03-28 00:00:00 ¦ AP-38/0 ¦ TO ¦ AP-44/0 ¦ = ¦ 11.051 ¦ Approved 2 ¦ AP-44/0 ¦ TO ¦ 52/0 ¦ = ¦ 4.087 ¦ Approved 3 ¦ AP-52/0 ¦ TO ¦ AP-76/0 ¦ = ¦ 16.089 ¦ Approved 4 ¦ Total ¦ 39.791 | ok
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | Soil investigation | 20 | 10 | summary_status, survey_soil | R5: SL. No ¦ Loc.No ¦ Type of Tower ¦ RC ¦ Tower Structure ¦ Depth ¦ Start Date ¦ End Date ¦ Status ¦ REMARKS R6: #VALUE! ¦ 79/0 ¦ PDD+6 ¦ Monopole ¦ 20 ¦ 2025-02-19 00:00:00 ¦ 2025-02-22 00:00:00 ¦ Completed R7: #VALUE! ¦ 78A/0 ¦ QDD60+9 ¦ 4 ¦ Danube Tower ¦ 20 ¦ 2025-02-23 00:00:00 ¦ 2025-02-24 00:00:00 ¦ Completed R8: #VALUE! ¦ 75/0 ¦ PDD+18 ¦ MonoPole (with AUX Arm) ¦ 20 ¦ 2025-02-27 00:00:00 ¦ 2025-03-01 00:00:00 ¦ Completed R9: #VALUE! ¦ 74/0 ¦ PDD+9 ¦ Monopole ¦ 20 ¦ 2025-03-02 00:00:00 ¦ 2025-03-04 00:00:00 ¦ Completed | Soil Investigation Letter Ref No. Ref.WRTS-II/Valsad TLC/NMTL Date-09/02/2025 Ref.WRTS-II/Valsad TLC/NMTL Date-17/02/2025 SL. No ¦ Loc.No ¦ Type of Tower ¦ RC ¦ Tower Structure ¦ Depth ¦ Start Date ¦ End Date ¦ Status ¦ REMARKS #VALUE! ¦ 79/0 ¦ PDD+6 ¦ Monopole ¦ 20 ¦ 2025-02-19 00:00:00 ¦ 2025-02-22 00:00:00 ¦ Completed #VALUE! ¦ 78A/0 ¦ QDD60+9 ¦ 4 ¦ Danube Tower ¦ 20 ¦ 2025-02-23 00:00:00 ¦ 2025-02-24 00:00:00 ¦ Completed #VALUE! ¦ 75/0 ¦ PDD+18 ¦ MonoPole (with AUX Arm) ¦ 20 ¦ 2025-02-27 00:00:00 ¦ 2025-03-01 00:00:00 ¦ Completed #VALUE! ¦ 74/0 ¦ PDD+9 ¦ Monopole ¦ 20 ¦ 2025-03-02 00:00:00 ¦ 2025-03-04 00:00:00 ¦ Completed | ok
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | Crossing Details | 29 | 10 | statutory_crossing, summary_status, survey_soil | R4: Sl. No. ¦ Section ¦ NAME OF CROSSING ¦ Check Survey Status ¦ Date of Submission ¦ Status of proposal ¦ Approving Authority ¦ Exp. date of Approval ¦ Remarks R14: Sl. No. ¦ FROM (AP) ¦ TO (AP) ¦ NAME OF CROSSING ¦ Type of Crossing ¦ Date of Submission ¦ Status of proposal ¦ Approving Authority ¦ Exp. date of Approval ¦ Remarks R17: Sl. No. ¦ FROM (AP) ¦ TO (AP) ¦ NAME OF CROSSING ¦ Type of Crossing ¦ Date of Submission ¦ Status of proposal ¦ Approving Authority ¦ Exp. date of Approval ¦ Remarks R20: Sl. No. ¦ FROM (AP) ¦ TO (AP) ¦ NAME OF CROSSING ¦ Type of Crossing ¦ Date of Submission ¦ Status of proposal ¦ Approving Authority ¦ Exp. date of Approval ¦ Remarks R23: Sl. No. ¦ FROM (AP) ¦ TO (AP) ¦ NAME OF CROSSING ¦ Type of Crossing ¦ Date of Submission ¦ Status of proposal ¦ Approving Authority ¦ Exp. date of Approval ¦ Remarks | CROSSINGS PROPOSAL STATUS Transmission Line Tower Package-TW02 400KV D/C Navsari - Kala Transmission line.( Twin HTLS) Power Line Crossings Sl. No. ¦ Section ¦ NAME OF CROSSING ¦ Check Survey Status ¦ Date of Submission ¦ Status of proposal ¦ Approving Authority ¦ Exp. date of Approval ¦ Remarks 1 ¦ 72A/0 ¦ 72B/0 ¦ 400KV M/C Navsari - Magarawada - Kala Transmission line. ¦ Approved ¦ 2025-07-03 00:00:00 ¦ Under Process ¦ PGCIL 2 ¦ 75/0 ¦ 75A/0 ¦ 66KV D/C Dalwada -Dabhel transmission line. ¦ Approved ¦ 2025-07-19 00:00:00 ¦ Under Process ¦ GETCO 3 ¦ 78/0 ¦ 78A/0 ¦ 220KV D/C Magarwada -Ringanwada Transmission line. ¦ Approved ¦ 2025-09-08 00:00:00 ¦ Under Process ¦ PGCIL 4 ¦ 78/0 ¦ 78A/0 ¦ 66KV D/C Ringanwada-Varkund Transmission line. ¦ Approved ¦ 2025-09-08 00:00:00 ¦ Under Process ¦ GETCO | ok
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | Line Scenario | 19 | 18 |  |  | Line Scenario for M/c 400KV New Navsari to Magarwada & 400KV Navsari to Kala transmission line. From MC location 76/0 to 76/0, 8.75kM Navsari to Kala work balance otherwise all work completed. Kala Substation ¦ From CommonPoint 79/0 to Kala Sustation scope by M/s Bajaj ¦ From CommonPoint 19/0 to Navsari Sustation scope by M/s Bajaj ¦ Navsari Substation D/C Navsari - Magarwada (8.822KM) D/c Navsari to Kala Loc-79/0 ¦ Loc-76/0 ¦ Loc-67/3 ¦ Loc-19/0 M/C Navsari-Magarwada ¦ M/C Navsari-Magarwada Magarwada Substation ¦ D/C Navsari- Kala (8.75KM) | ok
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | Sheet3 | 8 | 12 | erection, foundation, row_hindrance, stringing | R2: TA310 ¦ 400 KV M/C NKTL ¦ Unit ¦ Total Project Volume ¦ Compltd. As on Apr'25 ¦ Bal. as on 01.05.25 ¦ Executed for the month of May'25 ¦ Executed for the month of Jun'25 ¦ Bal. as on 01.07.2025 ¦ Remarks R3: Proj. code ¦ Project Name ¦ Foundation ¦ Nos. ¦ 34 ¦ 34 ¦ 34 ¦ 2 ¦ 3 ¦ 29 ¦ Workforce demobilization was necessitated by the unavailability of work fronts and unfavorable weather conditions R5: Erection ¦ Nos. ¦ 34 ¦ 34 ¦ 34 ¦ 34 ¦ No. of gangs R7: Stringing (RS) ¦ Kms. ¦ 8.822 ¦ 8.822 ¦ 8.822 ¦ 8.822 ¦ TSE & Manual gangs R8: Stringing (FS) ¦ Kms. ¦ 8.822 ¦ 8.822 ¦ 8.822 ¦ 8.822 | TA310 ¦ 400 KV M/C NKTL ¦ Unit ¦ Total Project Volume ¦ Compltd. As on Apr'25 ¦ Bal. as on 01.05.25 ¦ Executed for the month of May'25 ¦ Executed for the month of Jun'25 ¦ Bal. as on 01.07.2025 ¦ Remarks Proj. code ¦ Project Name ¦ Foundation ¦ Nos. ¦ 34 ¦ 34 ¦ 34 ¦ 2 ¦ 3 ¦ 29 ¦ Workforce demobilization was necessitated by the unavailability of work fronts and unfavorable weather conditions Cum ¦ 2429 ¦ 2429 ¦ 2429 ¦ 144.03 ¦ 205.2 ¦ 2079.77 Erection ¦ Nos. ¦ 34 ¦ 34 ¦ 34 ¦ 34 ¦ No. of gangs MT ¦ 879.19 ¦ 879.19 ¦ 879.19 ¦ 879.19 Stringing (RS) ¦ Kms. ¦ 8.822 ¦ 8.822 ¦ 8.822 ¦ 8.822 ¦ TSE & Manual gangs Stringing (FS) ¦ Kms. ¦ 8.822 ¦ 8.822 ¦ 8.822 ¦ 8.822 | ok
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | 2026-01-12 | Supply Status | 18 | 12 | opgw_accessories, summary_status, supply | R3: Conductor ¦ TWIN HTLS MOOSE CONDUCTOR ¦ 1265.363112000001 ¦ 40 ¦ 103.90199664000001 ¦ 1409.265108640001 ¦ 1309.984 ¦ 1191.92 ¦ 118.06399999999985 R4: OPGW ¦ 24 FIBRE (DWSM) OPGW FIBRE OPTIC CABLE ¦ 99.11685600000001 ¦ 4 ¦ 8.57 ¦ 111.686856 ¦ 111 ¦ 99.589 ¦ 11.411000000000001 R5: Composite long rod Insulators ¦ 120kN ¦ 1040 ¦ 117 ¦ 117 ¦ 1274 ¦ 68 ¦ 1249 ¦ 1098 ¦ 83 ¦ 93 ¦ Req R7: Hardware Fittings ¦ Twin HTLS Conductor-Single "I" Suspension String(without clamps) ¦ 738 ¦ 19 ¦ 757 ¦ 53 ¦ 851 ¦ 719 ¦ 79 ¦ -41 R8: Twin HTLS Conductor-Single I Suspension String(Pilot) (without clamps)(1x120KN) ¦ 302 ¦ 5 ¦ 117 ¦ 424 ¦ 305 ¦ 305 ¦ 119 ¦ Req | 400KV Navsari To Kala Transmission status, Supply Status:- ¦ 2026-01-12 00:00:00 Description ¦ Line Qty. ¦ Spare Qty ¦ NKTL Req. ¦ Total Req. ¦ Damage Qty. ¦ Received Qty. ¦ Total Issue Qty. ¦ Balance Qty Available at Store. ¦ Balance Qty Required. ¦ Remark Conductor ¦ TWIN HTLS MOOSE CONDUCTOR ¦ 1265.363112000001 ¦ 40 ¦ 103.90199664000001 ¦ 1409.265108640001 ¦ 1309.984 ¦ 1191.92 ¦ 118.06399999999985 OPGW ¦ 24 FIBRE (DWSM) OPGW FIBRE OPTIC CABLE ¦ 99.11685600000001 ¦ 4 ¦ 8.57 ¦ 111.686856 ¦ 111 ¦ 99.589 ¦ 11.411000000000001 Composite long rod Insulators ¦ 120kN ¦ 1040 ¦ 117 ¦ 117 ¦ 1274 ¦ 68 ¦ 1249 ¦ 1098 ¦ 83 ¦ 93 ¦ Req 160kN ¦ 3792 ¦ 271 ¦ 816 ¦ 4879 ¦ 108 ¦ 4267 ¦ 4618 ¦ -1109 ¦ 1370 ¦ Req Hardware Fittings ¦ Twin HTLS Conductor-Single "I" Suspension String(without clamps) ¦ 738 ¦ 19 ¦ 757 ¦ 53 ¦ 851 ¦ 719 ¦ 79 ¦ -41 Twin HTLS Conductor-Single I Suspension String(Pilot) (without clamps)(1x120KN) ¦ 302 ¦ 5 ¦ 117 ¦ 424 ¦ 305 ¦ 305 ¦ 119 ¦ Req | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | 101-276 FINAL 11-07-2025 | 1058 | 39 | visual_l2 | R7: Sl.No ¦ AP NO. ¦ TOWER NO. ¦ TYPE OF TOWER ¦ HT of Tower (Mtr) ¦ SPAN (Mtr) ¦ CUMULATIVE SECTION LENGTH (Mtr) ¦ LEG EXTENSION ¦ RAISED CHIMNEY/PILE ¦ BENCHING VOLUME (Cum) ¦ REVETMENT VOLUME (Cum) ¦ R.L (Mtr) ¦ DEVIATION ANGLE (Deg) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) ¦ UTM Coordinates | KEC INTERNATIONAL LIMITED TRANSMISSION LINE PACKAGE - TL02 FOR 765KV D/C AHMEDABAD - NAVSARI (SOUTH GUJARAT) LINE (PART II) ASSOCIATED WITH “TRANSMISSION SCHEME FOR EVACUATION OF 4.5GW RE INJECTION AT KHAVDA PS UNDER PHASE-II-PART C” PS UNDER PHASE-II-PART C” UNDER TBCB ROUTE 765 kV D/C Ahmedabad-Navsari TL TOWER SCHEDULE - AP101/0 TO AP153/0 W.O.TA325 Client : M/s KHAVDA II-C TRANSMISSION LIMITED (WHOLLY OWNED SUBSIDIARY OF POWERGRID) ¦ DT : ¦ DT :30.07.2020 REV: ¦ REV-02 Sl.No ¦ AP NO. ¦ TOWER NO. ¦ TYPE OF TOWER ¦ HT of Tower (Mtr) ¦ SPAN (Mtr) ¦ CUMULATIVE SECTION LENGTH (Mtr) ¦ LEG EXTENSION ¦ RAISED CHIMNEY/PILE ¦ BENCHING VOLUME (Cum) ¦ REVETMENT VOLUME (Cum) ¦ R.L (Mtr) ¦ DEVIATION ANGLE (Deg) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) ¦ UTM Coordinates A ¦ B ¦ C ¦ D ¦ Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Easting ¦ Northing ¦ Tower Weight MT | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | 765KV TA 325 ANTL | 20 | 17 | project_details, summary_status, survey_soil, visual_l2 | R2: Project Name ¦ 765KV D/C HEXA AHMEDABAD - NAVSARI TL (PKG 02) ¦ NOA Start Date ¦ 2023-03-23 00:00:00 ¦ PCH ¦ Mr. Arun Felbin R3: Client Name ¦ PGKTL ¦ LOA End Date ¦ 2024-12-22 00:00:00 ¦ Regional Manager ¦ Mr. Nitin Bandale R7: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Submitted till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks R8: Rout Alignment ¦ km ¦ 177.35 ¦ 177.35 ¦ 177.35 ¦ 177.35 ¦ 177.35 ¦ Completed R9: Detailed Survey ¦ km ¦ 177.35 ¦ 177.35 ¦ 177.35 ¦ 177.35 ¦ 177.35 ¦ Completed | Project Code ¦ TA 325 ¦ Date ¦ 2026-01-19 00:00:00 ¦ President-T&D ¦ Mr. Ganesh Srinivasan Project Name ¦ 765KV D/C HEXA AHMEDABAD - NAVSARI TL (PKG 02) ¦ NOA Start Date ¦ 2023-03-23 00:00:00 ¦ PCH ¦ Mr. Arun Felbin Client Name ¦ PGKTL ¦ LOA End Date ¦ 2024-12-22 00:00:00 ¦ Regional Manager ¦ Mr. Nitin Bandale Revised End Date ¦ 2025-12-30 00:00:00 ¦ Planning Engineer ¦ Mr. Janvendra Kumar ¦ Project Manger ¦ Mr. Sanjeev Garg Check Survey Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Submitted till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks Rout Alignment ¦ km ¦ 177.35 ¦ 177.35 ¦ 177.35 ¦ 177.35 ¦ 177.35 ¦ Completed Detailed Survey ¦ km ¦ 177.35 ¦ 177.35 ¦ 177.35 ¦ 177.35 ¦ 177.35 ¦ Completed | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Project Details | 48 | 11 | project_details | R1: Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Engineer/Supervisor | Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Engineer/Supervisor TA 325 ¦ 765 KV D/C Hexa Ahmedabad - Navsari Transmission Line ¦ PGCIL ¦ 2023-03-23 00:00:00 ¦ 2024-12-22 00:00:00 ¦ Mr. Janvendra Kumar ¦ Mr. Arun Felbin ¦ Mr. Nitin Bendale ¦ Mr. Sanjeev Garg ¦ Mithun Samui ¦ Sandeep Kumar Milan Mal ¦ Laxman Prasad Nayak Gurveet Singh ¦ Abdul Matin Bibhu Kalyan Das ¦ Khemlal Mahto Sanjeet Singh ¦ Bibek Kumar Choubey Ranjeet Kumar Singh ¦ Birkha Bahadur Ramchandra Prasad | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Visual chart Compiled | 604 | 38 | earthing_tack, erection, foundation, opgw_accessories, statutory_crossing, stringing, summary_status, survey_soil, visual_l2 | R2: Name of the Line : ¦ 765 kV D/C Ahmedabad - Navsari Transmission Line ¦ Completed R3: Name of Project: ¦ Power Grid Khavda-II C Transmission Limited ¦ DS (Aprd) ¦ CS (Aprd) ¦ SOIL INVSTGN ¦ FOUNDATION ¦ TOWER ERECTION ¦ TW ¦ TIG & PUN ¦ STR P/O ¦ STR F/S ¦ OPGW STR R8: Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ Sl. No. ¦ Type of Crossing ¦ No. of X-ing ¦ Approved ¦ Balance R10: 1 ¦ Detailed Survey ¦ Kms ¦ 177.35018100000002 ¦ 177.35018100000002 ¦ 1 ¦ Powerline X-ing ¦ 23 ¦ 22 ¦ 1 R11: 2 ¦ Check Survey ¦ Kms ¦ 177.35018100000002 ¦ 177.35018100000002 ¦ True ¦ 66 kV ¦ 13 ¦ 12 ¦ 1 | Visual Chart - Vadodara + Navsari Section ¦ 2026-01-19 00:00:00 Name of the Line : ¦ 765 kV D/C Ahmedabad - Navsari Transmission Line ¦ Completed Name of Project: ¦ Power Grid Khavda-II C Transmission Limited ¦ DS (Aprd) ¦ CS (Aprd) ¦ SOIL INVSTGN ¦ FOUNDATION ¦ TOWER ERECTION ¦ TW ¦ TIG & PUN ¦ STR P/O ¦ STR F/S ¦ OPGW STR Name of Contractor: ¦ KEC International Limited TOTAL ¦ COMP. ¦ BAL. ¦ EAR ¦ TOTAL ¦ COMP. ¦ BAL. PROGRESS AT A GLANCE : ¦ CROSSING PROPOSAL STATUS : Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ Sl. No. ¦ Type of Crossing ¦ No. of X-ing ¦ Approved ¦ Balance 1 ¦ Detailed Survey ¦ Kms ¦ 177.35018100000002 ¦ 177.35018100000002 ¦ 1 ¦ Powerline X-ing ¦ 23 ¦ 22 ¦ 1 | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Soil Invst. | 31 | 7 | summary_status, survey_soil | R2: Sl. No. ¦ Loc. No. ¦ Work Portion ¦ Status ¦ Classification ¦ Approval Letter Status ¦ Drawing Status R3: 1 ¦ AP101 ¦ Vadodara ¦ Completed ¦ FS ¦ Avail. R4: 2 ¦ AP102 ¦ Vadodara ¦ Completed ¦ Avail. R5: 3 ¦ AP103 ¦ Vadodara ¦ Completed ¦ Avail. R6: 4 ¦ AP104 ¦ Vadodara ¦ Completed ¦ Avail. | ANTL PROJECT - SOIL INVESTIGATION LOCATIONS Sl. No. ¦ Loc. No. ¦ Work Portion ¦ Status ¦ Classification ¦ Approval Letter Status ¦ Drawing Status 1 ¦ AP101 ¦ Vadodara ¦ Completed ¦ FS ¦ Avail. 2 ¦ AP102 ¦ Vadodara ¦ Completed ¦ Avail. 3 ¦ AP103 ¦ Vadodara ¦ Completed ¦ Avail. 4 ¦ AP104 ¦ Vadodara ¦ Completed ¦ Avail. 5 ¦ AP105 ¦ Vadodara ¦ Completed ¦ Avail. 6 ¦ AP120 ¦ Vadodara ¦ Completed ¦ WPS ¦ Avail. | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Foundation-Compliled | 494 | 14 | foundation, project_details, summary_status | R1: Sl. No. ¦ Location No. ¦ Tower Type ¦ RC ¦ Classification ¦ Revenue ¦ Concreting Volume in M3 ¦ Starting Date ¦ Status ¦ Completion Date ¦ Remarks ¦ Gang Name ¦ No. R2: 1 ¦ 101/0 ¦ DD60+35 ¦ 6 ¦ FS ¦ 440.345 ¦ 2025-01-01 00:00:00 ¦ Completed ¦ 2025-02-02 00:00:00 ¦ Rawat Construction ¦ 1 R3: 2 ¦ 102/0 ¦ DD45+35 ¦ 11.84 ¦ Pile ¦ 2025-03-06 00:00:00 ¦ Completed ¦ 2025-06-28 00:00:00 ¦ AK Construction ¦ 1 R4: 3 ¦ 104/0 ¦ DD60+35 ¦ 9.97 ¦ Pile ¦ 861.11 ¦ 2024-11-17 00:00:00 ¦ Completed ¦ 2025-02-28 00:00:00 ¦ Jai Mata Di ¦ 1 R5: 4 ¦ 105/0 ¦ DD60+35 ¦ 6 ¦ Pile ¦ 861.114 ¦ 2024-11-25 00:00:00 ¦ Completed ¦ 2025-01-17 00:00:00 ¦ Jai Mata Di ¦ 1 | Sl. No. ¦ Location No. ¦ Tower Type ¦ RC ¦ Classification ¦ Revenue ¦ Concreting Volume in M3 ¦ Starting Date ¦ Status ¦ Completion Date ¦ Remarks ¦ Gang Name ¦ No. 1 ¦ 101/0 ¦ DD60+35 ¦ 6 ¦ FS ¦ 440.345 ¦ 2025-01-01 00:00:00 ¦ Completed ¦ 2025-02-02 00:00:00 ¦ Rawat Construction ¦ 1 2 ¦ 102/0 ¦ DD45+35 ¦ 11.84 ¦ Pile ¦ 2025-03-06 00:00:00 ¦ Completed ¦ 2025-06-28 00:00:00 ¦ AK Construction ¦ 1 3 ¦ 104/0 ¦ DD60+35 ¦ 9.97 ¦ Pile ¦ 861.11 ¦ 2024-11-17 00:00:00 ¦ Completed ¦ 2025-02-28 00:00:00 ¦ Jai Mata Di ¦ 1 4 ¦ 105/0 ¦ DD60+35 ¦ 6 ¦ Pile ¦ 861.114 ¦ 2024-11-25 00:00:00 ¦ Completed ¦ 2025-01-17 00:00:00 ¦ Jai Mata Di ¦ 1 5 ¦ 106/0 ¦ DD60+9 ¦ WPS ¦ 180.61 ¦ 2024-05-21 00:00:00 ¦ Completed ¦ 2024-07-15 00:00:00 ¦ JMD ¦ 1 6 ¦ 106A/0 ¦ DC2+0 ¦ PS ¦ 168.913 ¦ 2024-11-18 00:00:00 ¦ Completed ¦ 2024-12-18 00:00:00 ¦ Rawat Construction ¦ 1 7 ¦ 106A/1 ¦ DA+6 ¦ PS ¦ 1215596 ¦ 83.812 ¦ 2024-11-23 00:00:00 ¦ Completed ¦ 2024-12-10 00:00:00 ¦ Rawat Construction ¦ 1 | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | FDN-VDRA | 210 | 15 | earthing_tack, foundation, project_details, summary_status | R2: S.L. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Revenue ¦ Concreting Volume in M3 ¦ Starting Date ¦ Status ¦ Cumulative Status ¦ Completion Date ¦ Remarks ¦ Gang Name ¦ Manpower ¦ Earthing Status ¦ Earthing Completion Date R3: 1 ¦ 132/3 ¦ DA+0 ¦ Wet Paddy ¦ 2023-06-12 00:00:00 ¦ Completed ¦ Completed ¦ 2023-06-21 00:00:00 ¦ Dismental ¦ Deep Power ¦ Completed R4: 2 ¦ 132/2 ¦ DA+0 ¦ Wet Paddy ¦ 2023-08-05 00:00:00 ¦ Completed ¦ Completed ¦ 2023-08-14 00:00:00 ¦ Deep Power ¦ Completed R5: 3 ¦ 135A/4 ¦ DA+0 ¦ Wet Paddy ¦ 2023-08-10 00:00:00 ¦ Completed ¦ Completed ¦ 2023-08-23 00:00:00 ¦ Shri Krishna Powergrid ¦ Completed R6: 4 ¦ 127/1 ¦ DA+0 ¦ Wet Paddy ¦ 2023-08-18 00:00:00 ¦ Completed ¦ Completed ¦ 2023-08-29 00:00:00 ¦ Shree Parth Electricals ¦ Completed | Foundation Part-I (VADODARA SECTION) S.L. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Revenue ¦ Concreting Volume in M3 ¦ Starting Date ¦ Status ¦ Cumulative Status ¦ Completion Date ¦ Remarks ¦ Gang Name ¦ Manpower ¦ Earthing Status ¦ Earthing Completion Date 1 ¦ 132/3 ¦ DA+0 ¦ Wet Paddy ¦ 2023-06-12 00:00:00 ¦ Completed ¦ Completed ¦ 2023-06-21 00:00:00 ¦ Dismental ¦ Deep Power ¦ Completed 2 ¦ 132/2 ¦ DA+0 ¦ Wet Paddy ¦ 2023-08-05 00:00:00 ¦ Completed ¦ Completed ¦ 2023-08-14 00:00:00 ¦ Deep Power ¦ Completed 3 ¦ 135A/4 ¦ DA+0 ¦ Wet Paddy ¦ 2023-08-10 00:00:00 ¦ Completed ¦ Completed ¦ 2023-08-23 00:00:00 ¦ Shri Krishna Powergrid ¦ Completed 4 ¦ 127/1 ¦ DA+0 ¦ Wet Paddy ¦ 2023-08-18 00:00:00 ¦ Completed ¦ Completed ¦ 2023-08-29 00:00:00 ¦ Shree Parth Electricals ¦ Completed 5 ¦ 133A/4 ¦ DA+6 ¦ Wet Paddy ¦ 2023-08-11 00:00:00 ¦ Completed ¦ Completed ¦ 2023-08-29 00:00:00 ¦ Dharsinis Const. (HD Engineering) ¦ Completed 6 ¦ 127/2 ¦ DA+0 ¦ Wet Paddy ¦ 2023-08-28 00:00:00 ¦ Completed ¦ Completed ¦ 2023-08-31 00:00:00 ¦ Shree Parth Electricals ¦ Completed | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | FDN-NVSR | 308 | 18 | earthing_tack, foundation, project_details, row_hindrance, summary_status | R2: S.L. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Revenue ¦ Concreting Volume in M3 ¦ Trial pit start date ¦ Starting Date ¦ Status ¦ Cumulative Status ¦ Completion Date ¦ Remarks ¦ Gang Name ¦ Manpower ¦ Earthing Status ¦ Earthing Completed Date ¦ Hindrance total days ¦ Hindance details R3: 1 ¦ 163/2 ¦ DA+0 ¦ WET ¦ 881091 ¦ 63.346000000000004 ¦ 2024-01-24 00:00:00 ¦ Completed ¦ Completed ¦ 2023-01-29 00:00:00 ¦ Completed R4: 2 ¦ 197/3 ¦ DA+0 ¦ PS ¦ 1086615 ¦ 80.771 ¦ 2023-08-18 00:00:00 ¦ Completed ¦ Completed ¦ 2023-08-31 00:00:00 ¦ Completed R5: 3 ¦ 195A/3 ¦ DA+0 ¦ PS ¦ 1086615 ¦ 80.771 ¦ 2023-08-22 00:00:00 ¦ Completed ¦ Completed ¦ 2023-10-01 00:00:00 ¦ Completed R6: 4 ¦ 165/4 ¦ DA+0 ¦ WET ¦ 881091 ¦ 63.346000000000004 ¦ 2023-10-20 00:00:00 ¦ Completed ¦ Completed ¦ 2023-11-03 00:00:00 ¦ Completed | Foundation Part-II (NAVSARI SECTION) S.L. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Revenue ¦ Concreting Volume in M3 ¦ Trial pit start date ¦ Starting Date ¦ Status ¦ Cumulative Status ¦ Completion Date ¦ Remarks ¦ Gang Name ¦ Manpower ¦ Earthing Status ¦ Earthing Completed Date ¦ Hindrance total days ¦ Hindance details 1 ¦ 163/2 ¦ DA+0 ¦ WET ¦ 881091 ¦ 63.346000000000004 ¦ 2024-01-24 00:00:00 ¦ Completed ¦ Completed ¦ 2023-01-29 00:00:00 ¦ Completed 2 ¦ 197/3 ¦ DA+0 ¦ PS ¦ 1086615 ¦ 80.771 ¦ 2023-08-18 00:00:00 ¦ Completed ¦ Completed ¦ 2023-08-31 00:00:00 ¦ Completed 3 ¦ 195A/3 ¦ DA+0 ¦ PS ¦ 1086615 ¦ 80.771 ¦ 2023-08-22 00:00:00 ¦ Completed ¦ Completed ¦ 2023-10-01 00:00:00 ¦ Completed 4 ¦ 165/4 ¦ DA+0 ¦ WET ¦ 881091 ¦ 63.346000000000004 ¦ 2023-10-20 00:00:00 ¦ Completed ¦ Completed ¦ 2023-11-03 00:00:00 ¦ Completed 5 ¦ 167/2 ¦ DA+6 ¦ WET ¦ 986514 ¦ 65.631 ¦ 2023-11-13 00:00:00 ¦ Completed ¦ Completed ¦ 2023-11-30 00:00:00 ¦ Completed 6 ¦ 167/3 ¦ DA+6 ¦ WET PADDY ¦ 623377 ¦ 40.634 ¦ 2023-11-23 00:00:00 ¦ Completed ¦ Completed ¦ 2023-11-30 00:00:00 ¦ Completed | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Erection-Compiled | 539 | 14 | erection, project_details, summary_status | R1: Sl. No. ¦ Location No. ¦ Type ¦ Type of Tower ¦ Starting Date ¦ Revenue ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ No. ¦ District ¦ Remarks ¦ Ageing R2: 1 ¦ 127/1 ¦ DA ¦ DA+0 ¦ 2023-09-30 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-10-15 00:00:00 ¦ Ghanshyam Mahto ¦ 1 ¦ VADODARA ¦ 15 R3: 2 ¦ 127/2 ¦ DA ¦ DA+0 ¦ 2023-10-16 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-10-29 00:00:00 ¦ Ghanshyam Mahto ¦ 1 ¦ VADODARA ¦ 13 R4: 3 ¦ 135A/4 ¦ DA ¦ DA+0 ¦ 2023-11-01 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-11-09 00:00:00 ¦ Ghanshyam Mahto ¦ 1 ¦ BHARUCH ¦ 8 R5: 4 ¦ 135/2 ¦ DA ¦ DA+0 ¦ 2023-11-11 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-11-17 00:00:00 ¦ Ghanshyam Mahto ¦ 1 ¦ BHARUCH ¦ 6 | Sl. No. ¦ Location No. ¦ Type ¦ Type of Tower ¦ Starting Date ¦ Revenue ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ No. ¦ District ¦ Remarks ¦ Ageing 1 ¦ 127/1 ¦ DA ¦ DA+0 ¦ 2023-09-30 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-10-15 00:00:00 ¦ Ghanshyam Mahto ¦ 1 ¦ VADODARA ¦ 15 2 ¦ 127/2 ¦ DA ¦ DA+0 ¦ 2023-10-16 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-10-29 00:00:00 ¦ Ghanshyam Mahto ¦ 1 ¦ VADODARA ¦ 13 3 ¦ 135A/4 ¦ DA ¦ DA+0 ¦ 2023-11-01 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-11-09 00:00:00 ¦ Ghanshyam Mahto ¦ 1 ¦ BHARUCH ¦ 8 4 ¦ 135/2 ¦ DA ¦ DA+0 ¦ 2023-11-11 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-11-17 00:00:00 ¦ Ghanshyam Mahto ¦ 1 ¦ BHARUCH ¦ 6 5 ¦ 135A/7 ¦ DA ¦ DA+0 ¦ 2023-11-19 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-12-01 00:00:00 ¦ Ghanshyam Mahto ¦ 1 ¦ BHARUCH ¦ 12 6 ¦ 133/1 ¦ DA ¦ DA+0 ¦ 2023-12-02 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-12-15 00:00:00 ¦ Ghanshyam Mahto ¦ 1 ¦ VADODARA ¦ 13 7 ¦ 135B/4 ¦ DA ¦ DA+6 ¦ 2024-01-04 00:00:00 ¦ 342192 ¦ 44.728234 ¦ Completed ¦ 2024-01-12 00:00:00 ¦ Poonam Kumari ¦ 1 ¦ BHARUCH ¦ 8 | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | EREC-VDRA | 190 | 14 | earthing_tack, erection, project_details, summary_status | R3: Sl. No. ¦ Location No. ¦ Type of Tower ¦ Starting Date ¦ Revenue ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Remarks ¦ Tackwelding Status ¦ Tackwelding Start date ¦ Tackwelding Completion date ¦ Sub Contractor R4: 1 ¦ 127/1 ¦ DA+0 ¦ 2023-09-30 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-10-15 00:00:00 ¦ Ghansyam matho ¦ Completed ¦ 2024-02-18 00:00:00 ¦ 2024-02-19 00:00:00 ¦ Bharath Const. R5: 2 ¦ 127/2 ¦ DA+0 ¦ 2023-10-16 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-10-29 00:00:00 ¦ Ghansyam matho ¦ Completed ¦ 2024-02-17 00:00:00 ¦ 2024-02-18 00:00:00 ¦ Bharath Const. R6: 3 ¦ 135A/4 ¦ DA+0 ¦ 2023-11-01 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-11-09 00:00:00 ¦ Ghansyam matho ¦ Completed ¦ 2024-02-08 00:00:00 ¦ 2024-02-09 00:00:00 ¦ Bharath Const. R7: 4 ¦ 135/2 ¦ DA+0 ¦ 2023-11-11 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-11-17 00:00:00 ¦ Ghansyam matho ¦ Completed ¦ 2024-02-09 00:00:00 ¦ 2024-02-10 00:00:00 ¦ Bharath Const. | 2025-10-10 00:00:00 Tower Erection Part-I (Vadodara Section) Sl. No. ¦ Location No. ¦ Type of Tower ¦ Starting Date ¦ Revenue ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Remarks ¦ Tackwelding Status ¦ Tackwelding Start date ¦ Tackwelding Completion date ¦ Sub Contractor 1 ¦ 127/1 ¦ DA+0 ¦ 2023-09-30 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-10-15 00:00:00 ¦ Ghansyam matho ¦ Completed ¦ 2024-02-18 00:00:00 ¦ 2024-02-19 00:00:00 ¦ Bharath Const. 2 ¦ 127/2 ¦ DA+0 ¦ 2023-10-16 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-10-29 00:00:00 ¦ Ghansyam matho ¦ Completed ¦ 2024-02-17 00:00:00 ¦ 2024-02-18 00:00:00 ¦ Bharath Const. 3 ¦ 135A/4 ¦ DA+0 ¦ 2023-11-01 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-11-09 00:00:00 ¦ Ghansyam matho ¦ Completed ¦ 2024-02-08 00:00:00 ¦ 2024-02-09 00:00:00 ¦ Bharath Const. 4 ¦ 135/2 ¦ DA+0 ¦ 2023-11-11 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-11-17 00:00:00 ¦ Ghansyam matho ¦ Completed ¦ 2024-02-09 00:00:00 ¦ 2024-02-10 00:00:00 ¦ Bharath Const. 5 ¦ 135A/7 ¦ DA+0 ¦ 2023-11-19 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2023-12-01 00:00:00 ¦ Ghansyam matho ¦ Completed ¦ 2024-02-14 00:00:00 ¦ 2024-02-15 00:00:00 ¦ Bharath Const. | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | EREC-NAV | 303 | 16 | earthing_tack, erection, project_details, summary_status | R3: Sl. No. ¦ Location No. ¦ Type of Tower ¦ Starting Date ¦ Revenue ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Manpower ¦ Hindarnce Days ¦ Remarks ¦ Tackweldng Status ¦ Tackwelding start date ¦ Tackwelding Completion date ¦ Sub Contractor name R4: 1 ¦ 159/3 ¦ DA+0 ¦ 2024-07-08 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2024-07-23 00:00:00 ¦ Sukhridwin R5: 2 ¦ 164/2 ¦ DA+0 ¦ 2024-07-27 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2024-08-13 00:00:00 ¦ Sukhridwin R6: 3 ¦ 255/4 ¦ DA+0 ¦ 2024-07-10 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2024-08-22 00:00:00 ¦ Ghanshyam R7: 4 ¦ 159/0 ¦ DB1+0 ¦ 2024-08-14 00:00:00 ¦ 403998 ¦ 54.417843999999995 ¦ Completed ¦ 2024-09-08 00:00:00 ¦ Sukhridwin | Tower Erection Part-II (Navsari Section) Sl. No. ¦ Location No. ¦ Type of Tower ¦ Starting Date ¦ Revenue ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Manpower ¦ Hindarnce Days ¦ Remarks ¦ Tackweldng Status ¦ Tackwelding start date ¦ Tackwelding Completion date ¦ Sub Contractor name 1 ¦ 159/3 ¦ DA+0 ¦ 2024-07-08 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2024-07-23 00:00:00 ¦ Sukhridwin 2 ¦ 164/2 ¦ DA+0 ¦ 2024-07-27 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2024-08-13 00:00:00 ¦ Sukhridwin 3 ¦ 255/4 ¦ DA+0 ¦ 2024-07-10 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2024-08-22 00:00:00 ¦ Ghanshyam 4 ¦ 159/0 ¦ DB1+0 ¦ 2024-08-14 00:00:00 ¦ 403998 ¦ 54.417843999999995 ¦ Completed ¦ 2024-09-08 00:00:00 ¦ Sukhridwin 5 ¦ 267A/3 ¦ DA+0 ¦ 2024-08-21 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2024-09-13 00:00:00 ¦ Ramjivan-01 6 ¦ 165/2 ¦ DA+0 ¦ 2024-09-09 00:00:00 ¦ 286911 ¦ 37.730482 ¦ Completed ¦ 2024-09-20 00:00:00 ¦ Sukhridwin | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Stringing Compiled | 235 | 25 | foundation, project_details, stretch_readiness, stringing, summary_status | R1: Stringing Part-II (Navsari Section) ¦ 3.6567099999999755 ¦ 3.6567099999999755 R3: S.no ¦ Sec ¦ From AP ¦ ~ ¦ To AP ¦ Span (M) ¦ Method ¦ Balance FDN ¦ Balance ERC ¦ Section Readiness ¦ Starting Date ¦ Completion Date ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Length ¦ Status ¦ Completion Month R4: 1 ¦ JMB ¦ 112/0 ¦ ~ ¦ 113/0 ¦ 375.84 ¦ Manual ¦ Ready ¦ 2024-08-12 00:00:00 ¦ 2024-08-15 00:00:00 ¦ 375.84 ¦ 2024-08-17 00:00:00 ¦ 2024-08-19 00:00:00 ¦ 375.84 ¦ Completed ¦ 2024-08-01 00:00:00 ¦ 1 ¦ Muslehuddin ¦ Vadodara R5: 2 ¦ JMB ¦ 111/0 ¦ ~ ¦ 112/0 ¦ 341.9 ¦ Manual ¦ Ready ¦ 2024-09-23 00:00:00 ¦ 2024-09-24 00:00:00 ¦ 341.9 ¦ 2024-10-02 00:00:00 ¦ 2024-10-04 00:00:00 ¦ 341.9 ¦ Completed ¦ 2024-10-01 00:00:00 ¦ 4 ¦ Gokul Sarkar ¦ Vadodara R6: 3 ¦ JMB ¦ 110/0 ¦ ~ ¦ 111/0 ¦ 312.14 ¦ Manual ¦ Ready ¦ 2024-09-11 00:00:00 ¦ 2024-09-12 00:00:00 ¦ 312.14 ¦ 2024-10-04 00:00:00 ¦ 2024-10-06 00:00:00 ¦ 312.14 ¦ Completed ¦ 2024-10-01 00:00:00 ¦ 3 ¦ Gokul Sarkar ¦ Vadodara | Stringing Part-II (Navsari Section) ¦ 3.6567099999999755 ¦ 3.6567099999999755 177.34405400000003 ¦ 173.68734400000005 ¦ 173.68734400000005 S.no ¦ Sec ¦ From AP ¦ ~ ¦ To AP ¦ Span (M) ¦ Method ¦ Balance FDN ¦ Balance ERC ¦ Section Readiness ¦ Starting Date ¦ Completion Date ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Length ¦ Status ¦ Completion Month 1 ¦ JMB ¦ 112/0 ¦ ~ ¦ 113/0 ¦ 375.84 ¦ Manual ¦ Ready ¦ 2024-08-12 00:00:00 ¦ 2024-08-15 00:00:00 ¦ 375.84 ¦ 2024-08-17 00:00:00 ¦ 2024-08-19 00:00:00 ¦ 375.84 ¦ Completed ¦ 2024-08-01 00:00:00 ¦ 1 ¦ Muslehuddin ¦ Vadodara 2 ¦ JMB ¦ 111/0 ¦ ~ ¦ 112/0 ¦ 341.9 ¦ Manual ¦ Ready ¦ 2024-09-23 00:00:00 ¦ 2024-09-24 00:00:00 ¦ 341.9 ¦ 2024-10-02 00:00:00 ¦ 2024-10-04 00:00:00 ¦ 341.9 ¦ Completed ¦ 2024-10-01 00:00:00 ¦ 4 ¦ Gokul Sarkar ¦ Vadodara 3 ¦ JMB ¦ 110/0 ¦ ~ ¦ 111/0 ¦ 312.14 ¦ Manual ¦ Ready ¦ 2024-09-11 00:00:00 ¦ 2024-09-12 00:00:00 ¦ 312.14 ¦ 2024-10-04 00:00:00 ¦ 2024-10-06 00:00:00 ¦ 312.14 ¦ Completed ¦ 2024-10-01 00:00:00 ¦ 3 ¦ Gokul Sarkar ¦ Vadodara 4 ¦ JMB ¦ 113/0 ¦ ~ ¦ 114/0 ¦ 297.05 ¦ Manual ¦ Ready ¦ 2024-09-26 00:00:00 ¦ 2024-09-29 00:00:00 ¦ 297.05 ¦ 2024-10-01 00:00:00 ¦ 2024-10-06 00:00:00 ¦ 297.05 ¦ Completed ¦ 2024-10-01 00:00:00 ¦ 6 ¦ Muslehuddin ¦ Vadodara 5 ¦ JMB ¦ 109/0 ¦ ~ ¦ 110/0 ¦ 342.42 ¦ Manual ¦ Ready ¦ 2024-09-06 00:00:00 ¦ 2024-09-09 00:00:00 ¦ 342.42 ¦ 2024-10-10 00:00:00 ¦ 2024-10-13 00:00:00 ¦ 342.42 ¦ Completed ¦ 2024-10-01 00:00:00 ¦ 2 ¦ Gokul Sarkar ¦ Vadodara | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Striging-VDRA | 86 | 29 | foundation, project_details, stretch_readiness, stringing, summary_status, supply | R1: Balance ¦ 73.95897999999998 ¦ Balance ¦ 76.11297999999998 R2: Total ¦ 70.49576399999997 ¦ Insulator Hoisting ¦ Paying Out ¦ 68.07905399999997 ¦ Final Sag ¦ 68.07905399999997 ¦ 77 ¦ SD/Cable By pass R3: S.no ¦ From AP ¦ ~ ¦ To AP ¦ Span (M) ¦ Method ¦ Balance FDN ¦ Balance ERC ¦ Section Readiness ¦ Starting Date ¦ Completion Date ¦ Starting Date ¦ Completion Date ¦ P/O ¦ Starting Date ¦ Completion Date ¦ F/S ¦ Status ¦ Completion Month ¦ Gang Name R4: 1 ¦ 112/0 ¦ ~ ¦ 113/0 ¦ 375.84 ¦ Manual ¦ Ready ¦ 2024-08-12 00:00:00 ¦ 2024-08-15 00:00:00 ¦ 375.84 ¦ 2024-08-17 00:00:00 ¦ 2024-08-19 00:00:00 ¦ 375.84 ¦ Completed ¦ 2024-08-01 00:00:00 ¦ Muslehuddin ¦ Vadodara R5: 2 ¦ 111/0 ¦ ~ ¦ 112/0 ¦ 341.9 ¦ Manual ¦ Ready ¦ 2024-09-23 00:00:00 ¦ 2024-09-24 00:00:00 ¦ 341.9 ¦ 2024-10-02 00:00:00 ¦ 2024-10-04 00:00:00 ¦ 341.9 ¦ Completed ¦ 2024-10-01 00:00:00 ¦ Gokul Sarkar ¦ Vadodara | Balance ¦ 73.95897999999998 ¦ Balance ¦ 76.11297999999998 Total ¦ 70.49576399999997 ¦ Insulator Hoisting ¦ Paying Out ¦ 68.07905399999997 ¦ Final Sag ¦ 68.07905399999997 ¦ 77 ¦ SD/Cable By pass S.no ¦ From AP ¦ ~ ¦ To AP ¦ Span (M) ¦ Method ¦ Balance FDN ¦ Balance ERC ¦ Section Readiness ¦ Starting Date ¦ Completion Date ¦ Starting Date ¦ Completion Date ¦ P/O ¦ Starting Date ¦ Completion Date ¦ F/S ¦ Status ¦ Completion Month ¦ Gang Name 1 ¦ 112/0 ¦ ~ ¦ 113/0 ¦ 375.84 ¦ Manual ¦ Ready ¦ 2024-08-12 00:00:00 ¦ 2024-08-15 00:00:00 ¦ 375.84 ¦ 2024-08-17 00:00:00 ¦ 2024-08-19 00:00:00 ¦ 375.84 ¦ Completed ¦ 2024-08-01 00:00:00 ¦ Muslehuddin ¦ Vadodara 2 ¦ 111/0 ¦ ~ ¦ 112/0 ¦ 341.9 ¦ Manual ¦ Ready ¦ 2024-09-23 00:00:00 ¦ 2024-09-24 00:00:00 ¦ 341.9 ¦ 2024-10-02 00:00:00 ¦ 2024-10-04 00:00:00 ¦ 341.9 ¦ Completed ¦ 2024-10-01 00:00:00 ¦ Gokul Sarkar ¦ Vadodara 3 ¦ 110/0 ¦ ~ ¦ 111/0 ¦ 312.14 ¦ Manual ¦ Ready ¦ 2024-09-11 00:00:00 ¦ 2024-09-12 00:00:00 ¦ 312.14 ¦ 2024-10-04 00:00:00 ¦ 2024-10-06 00:00:00 ¦ 312.14 ¦ Completed ¦ 2024-10-01 00:00:00 ¦ Gokul Sarkar ¦ Vadodara 4 ¦ 113/0 ¦ ~ ¦ 114/0 ¦ 297.05 ¦ Manual ¦ Ready ¦ 2024-09-26 00:00:00 ¦ 2024-09-29 00:00:00 ¦ 297.05 ¦ 2024-10-01 00:00:00 ¦ 2024-10-06 00:00:00 ¦ 297.05 ¦ Completed ¦ 2024-10-01 00:00:00 ¦ Muslehuddin ¦ Vadodara 5 ¦ 109/0 ¦ ~ ¦ 110/0 ¦ 342.42 ¦ Manual ¦ Ready ¦ 2024-09-06 00:00:00 ¦ 2024-09-09 00:00:00 ¦ 342.42 ¦ 2024-10-10 00:00:00 ¦ 2024-10-13 00:00:00 ¦ 342.42 ¦ Completed ¦ 2024-10-01 00:00:00 ¦ Gokul Sarkar ¦ Vadodara ¦ Gas Pipe Line | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | String-Nav | 153 | 18 | project_details, stringing, summary_status | R3: Sr. No. ¦ Section ¦ length ¦ Manual/TSE ¦ Engaged Date ¦ Paying Out ¦ P/O Completed ¦ Final Sag ¦ F/S Completed ¦ Status ¦ Cumulative Status ¦ Gang Name ¦ Manpower ¦ Hindarnce Days ¦ Remarks R4: Starting Date ¦ Completion Date ¦ Starting Date ¦ Completion Date R6: 2 ¦ 259/0-260/0 ¦ 0.256 ¦ Hotline ¦ 2025-01-18 00:00:00 ¦ 2025-01-23 00:00:00 ¦ 2025-01-24 00:00:00 ¦ 0.256 ¦ 2025-01-26 00:00:00 ¦ 2025-01-28 00:00:00 ¦ 0.256 ¦ Completed. ¦ Final sag done. ¦ Dharmendra Electrical R7: 3 ¦ 260/0-261/0 ¦ 0.338 ¦ Manual ¦ 2025-01-17 00:00:00 ¦ 2025-01-23 00:00:00 ¦ 2025-01-25 00:00:00 ¦ 0.338 ¦ 2025-01-26 00:00:00 ¦ 2025-01-28 00:00:00 ¦ 0.338 ¦ Completed. ¦ Final sag done. ¦ Monera ¦ 34 R34: 30 ¦ 156/0-157/0 ¦ 0.24 ¦ Manual ¦ 2025-06-03 00:00:00 ¦ 2025-06-03 00:00:00 ¦ 2025-06-04 00:00:00 ¦ 0.24 ¦ 2025-06-03 00:00:00 ¦ 2025-06-04 00:00:00 ¦ 0.24 ¦ Completed ¦ Completed. ¦ Gokul Sarkar | Stringing Part-II (Navsari Section) 109.30800000000005 ¦ 107.68200000000004 ¦ 107.68200000000004 Sr. No. ¦ Section ¦ length ¦ Manual/TSE ¦ Engaged Date ¦ Paying Out ¦ P/O Completed ¦ Final Sag ¦ F/S Completed ¦ Status ¦ Cumulative Status ¦ Gang Name ¦ Manpower ¦ Hindarnce Days ¦ Remarks Starting Date ¦ Completion Date ¦ Starting Date ¦ Completion Date 1 ¦ 155/0-156/0 ¦ 2.733 ¦ TSE ¦ 2025-06-06 00:00:00 ¦ 2025-06-06 00:00:00 ¦ 2025-06-11 00:00:00 ¦ 2.733 ¦ 2025-06-14 00:00:00 ¦ 2024-06-20 00:00:00 ¦ 2.733 ¦ Completed. ¦ Completed. ¦ Gokul & Enamul 2 ¦ 259/0-260/0 ¦ 0.256 ¦ Hotline ¦ 2025-01-18 00:00:00 ¦ 2025-01-23 00:00:00 ¦ 2025-01-24 00:00:00 ¦ 0.256 ¦ 2025-01-26 00:00:00 ¦ 2025-01-28 00:00:00 ¦ 0.256 ¦ Completed. ¦ Final sag done. ¦ Dharmendra Electrical 3 ¦ 260/0-261/0 ¦ 0.338 ¦ Manual ¦ 2025-01-17 00:00:00 ¦ 2025-01-23 00:00:00 ¦ 2025-01-25 00:00:00 ¦ 0.338 ¦ 2025-01-26 00:00:00 ¦ 2025-01-28 00:00:00 ¦ 0.338 ¦ Completed. ¦ Final sag done. ¦ Monera ¦ 34 4 ¦ 164/0-165/0 ¦ 2.981 ¦ TSE ¦ 2025-02-07 00:00:00 ¦ 2025-02-07 00:00:00 ¦ 2025-02-10 00:00:00 ¦ 2.981 ¦ 2025-02-12 00:00:00 ¦ 2025-02-15 00:00:00 ¦ 2.981 ¦ Completed. ¦ Completed. ¦ Gokul Sarkar | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Visual chart NAVSARI Revised | 379 | 38 | erection, foundation, opgw_accessories, statutory_crossing, stringing, summary_status, survey_soil, visual_l2 | R3: Name of the Line : ¦ 765 kV D/C Ahmedabad - Navsari Transmission Line (Navsari Portion) ¦ Completed R4: Name of Project: ¦ Power Grid Khavda-II C Transmission Limited ¦ DS (Aprd) ¦ CS (Aprd) ¦ SOIL INVSTGN ¦ FOUNDATION ¦ EARTH ¦ TOWER ERECTION ¦ TW ¦ TIG & PUN ¦ STR P/O ¦ STR F/S ¦ OPGW STR R10: Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ Sl. No. ¦ Type of Crossing ¦ No. of X-ing ¦ Approved ¦ Balance R12: 1 ¦ Detailed Survey ¦ Kms ¦ 106.85471999999999 ¦ 106.85471999999999 ¦ 1 ¦ Powerline X-ing ¦ 44 ¦ 42 ¦ 2 R13: 2 ¦ Check Survey ¦ Kms ¦ 106.85471999999999 ¦ 106.85471999999999 ¦ True ¦ 66 kV ¦ 18 ¦ 16 ¦ 2 | Visual Chart Visual Chart ¦ 2025-10-11 00:00:00 Name of the Line : ¦ 765 kV D/C Ahmedabad - Navsari Transmission Line (Navsari Portion) ¦ Completed Name of Project: ¦ Power Grid Khavda-II C Transmission Limited ¦ DS (Aprd) ¦ CS (Aprd) ¦ SOIL INVSTGN ¦ FOUNDATION ¦ EARTH ¦ TOWER ERECTION ¦ TW ¦ TIG & PUN ¦ STR P/O ¦ STR F/S ¦ OPGW STR Name of Contractor: ¦ KEC International Limited TOTAL ¦ COMP. ¦ BAL. ¦ TOTAL ¦ COMP. ¦ BAL. PROGRESS AT A GLANCE : ¦ CROSSING PROPOSAL STATUS : Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ Sl. No. ¦ Type of Crossing ¦ No. of X-ing ¦ Approved ¦ Balance | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Crossing Vadodara | 49 | 13 | statutory_crossing | R4: Sl No ¦ AP NO ¦ AP No ¦ Type of Crossings ¦ OWNER ¦ Nos. ¦ Work Portion ¦ Submitted to Client for Review ¦ Revised Submisison due to Route Div. ¦ Confirmation received from Client ¦ Hard Copy Submission Date ¦ Joint Inspection Date ¦ Proposal Currently With R6: 2 ¦ 104 ¦ 105 ¦ Gas Pipe Line ¦ GAIL ¦ 1 ¦ Vadodara ¦ 2024-02-14 00:00:00 ¦ Online proposal submitted R8: 4 ¦ 108 ¦ 109 ¦ Gas Pipe Line ¦ GAIL ¦ 1 ¦ Vadodara ¦ 2024-02-22 00:00:00 ¦ Online proposal submitted R11: 7 ¦ 117 ¦ 118 ¦ Gas Pipe Line ¦ GAIL ¦ 1 ¦ Vadodara ¦ 2024-02-22 00:00:00 ¦ Online proposal submitted R17: 13 ¦ 123 ¦ 123/1 ¦ Gas Pipe Line ¦ ONGC ¦ 1 ¦ Vadodara ¦ 2024-02-26 00:00:00 ¦ Online proposal submitted | 765KV D/C HEXA AHEMDABAD - NAVSARI TL (PKG 02)- CROSSING DETAILS Sl No ¦ AP NO ¦ AP No ¦ Type of Crossings ¦ OWNER ¦ Nos. ¦ Work Portion ¦ Submitted to Client for Review ¦ Revised Submisison due to Route Div. ¦ Confirmation received from Client ¦ Hard Copy Submission Date ¦ Joint Inspection Date ¦ Proposal Currently With 1 ¦ 104 ¦ 105 ¦ 400KV ¦ GETCO ¦ 2 ¦ Vadodara ¦ 2014-02-27 00:00:00 ¦ 2024-05-03 00:00:00 ¦ Approved 30.07.24 2 ¦ 104 ¦ 105 ¦ Gas Pipe Line ¦ GAIL ¦ 1 ¦ Vadodara ¦ 2024-02-14 00:00:00 ¦ Online proposal submitted 3 ¦ 105 ¦ 106 ¦ 220KV ¦ GETCO ¦ 1 ¦ Vadodara ¦ 2024-03-22 00:00:00 ¦ 2024-04-10 00:00:00 ¦ 2024-04-23 00:00:00 ¦ Approved 4 ¦ 108 ¦ 109 ¦ Gas Pipe Line ¦ GAIL ¦ 1 ¦ Vadodara ¦ 2024-02-22 00:00:00 ¦ Online proposal submitted 5 ¦ 109 ¦ 110 ¦ Gas Pipe Line ¦ RELIANCE ¦ 1 ¦ Vadodara ¦ 2024-02-22 00:00:00 ¦ 2024-04-05 00:00:00 ¦ Awaiting DD 6 ¦ 115 ¦ 116 ¦ 220KV ¦ GETCO ¦ 1 ¦ Vadodara ¦ 2023-09-28 00:00:00 ¦ 2024-04-10 00:00:00 ¦ 2023-10-16 00:00:00 ¦ 2024-04-23 00:00:00 ¦ 2023-11-22 00:00:00 ¦ Approved | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Crossing Navsari | 70 | 15 | statutory_crossing, summary_status | R2: Sl No ¦ AP NO ¦ Towe Type ¦ AP No ¦ Tower Type ¦ Type of Crossings ¦ LINE OWNER ¦ Nos. ¦ Work Portion ¦ Status ¦ Submitted to Client for Review ¦ Submission to Line Owner Date ¦ Joint Inspection Date ¦ Proposal Currently With ¦ Remarks R3: 1 ¦ 156/0 ¦ DD60+3 ¦ 157/0 ¦ DD60+6 ¦ DEL - MUM Xpressway (SAKKARPUR - ANKLESHWAR) ¦ NHAI ¦ 1 ¦ Navsari ¦ Submitted ¦ 2024-01-30 00:00:00 ¦ 2024-02-03 00:00:00 ¦ 2024-02-23 00:00:00 ¦ NHAI Kamrej R6: 4 ¦ 159/1 ¦ DA+0 ¦ 159/2 ¦ DA+0 ¦ Gas Pipeline (Avanton) ¦ Navsari ¦ Proposal Not Required ¦ Done R10: 8 ¦ 166/0 ¦ DD60+6 ¦ 167/0 ¦ DD60+0 ¦ RLY Line Haturan - Panoli ¦ Western Railway Vadodara ¦ 1 ¦ Navsari ¦ Submitted ¦ 2023-09-08 00:00:00 ¦ 2023-10-05 00:00:00 ¦ 2024-01-19 00:00:00 ¦ Vadodara GETCO (DRM office) ¦ Approved R17: 15 ¦ 176/0 ¦ DD60+0 ¦ 177/0 ¦ DD60+0 ¦ NH48 (Delhi - Mumbai) - Kosamba ¦ NHAI ¦ 1 ¦ Navsari ¦ Submitted ¦ 2023-10-03 00:00:00 ¦ 2023-10-05 00:00:00 ¦ 2023-11-28 00:00:00 ¦ NHAI Kamrej ¦ Approved | 765KV D/C HEXA AHEMDABAD - NAVSARI TL PKG 02 (NAVSARI PORTION) - CROSSING STATUS Sl No ¦ AP NO ¦ Towe Type ¦ AP No ¦ Tower Type ¦ Type of Crossings ¦ LINE OWNER ¦ Nos. ¦ Work Portion ¦ Status ¦ Submitted to Client for Review ¦ Submission to Line Owner Date ¦ Joint Inspection Date ¦ Proposal Currently With ¦ Remarks 1 ¦ 156/0 ¦ DD60+3 ¦ 157/0 ¦ DD60+6 ¦ DEL - MUM Xpressway (SAKKARPUR - ANKLESHWAR) ¦ NHAI ¦ 1 ¦ Navsari ¦ Submitted ¦ 2024-01-30 00:00:00 ¦ 2024-02-03 00:00:00 ¦ 2024-02-23 00:00:00 ¦ NHAI Kamrej 2 ¦ 158/2 ¦ DA-3 ¦ 158A/0 ¦ DD45+6 ¦ Gas Pipeline ¦ 1 ¦ Navsari ¦ Submitted ¦ Done 3 ¦ 158A/0 ¦ DD45+6 ¦ 158B/0 ¦ DD45+18 ¦ 66KV Hansot - Urban TL ¦ GETCO ¦ 1 ¦ Navsari ¦ Submitted ¦ 2024-06-04 00:00:00 ¦ Approved on 01-08-2024 4 ¦ 159/1 ¦ DA+0 ¦ 159/2 ¦ DA+0 ¦ Gas Pipeline (Avanton) ¦ Navsari ¦ Proposal Not Required ¦ Done 5 ¦ 160/0 ¦ DD60+18 ¦ 161/0 ¦ DD60+25 ¦ 400KV HZR - GDR ¦ EASER POWER ¦ 1 ¦ Navsari ¦ Submitted ¦ 2023-09-07 00:00:00 ¦ 2023-09-15 00:00:00 ¦ 2023-09-30 00:00:00 ¦ Eassar ¦ Approved on 09-09-2024 6 ¦ 161/0 ¦ DD60+25 ¦ 162/0 ¦ DD60+25 ¦ Bullet Train ¦ 1 ¦ Navsari ¦ Submitted ¦ 2024-02-19 00:00:00 ¦ 2024-02-22 00:00:00 ¦ 2024-04-30 00:00:00 ¦ Approved | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Gangs | 27 | 8 | stringing | R2: Sl. No. ¦ Section ¦ Length (Km) ¦ Method ¦ Gang Name ¦ Fitter ¦ Man power | Stringing Gang Sl. No. ¦ Section ¦ Length (Km) ¦ Method ¦ Gang Name ¦ Fitter ¦ Man power 1 ¦ 101/0 - 102/0 ¦ 0.665 ¦ Manual ¦ Kudus Ali 2 ¦ 17 ¦ 55 2 ¦ 166/0 - 167/0 ¦ 0.415 ¦ Manual ¦ Munni Bibi 2 ¦ 13 ¦ 35 3 ¦ 159/2 - 160/0 ¦ 1.152 ¦ TSE ¦ Enamul Haque ¦ 13 ¦ 60 4 ¦ 172/0 - 173/0 ¦ 1.123 ¦ TSE ¦ Alam Construction ¦ 12 ¦ 74 5 ¦ 173/0 - 174/0 ¦ 0.232 ¦ Hotline ¦ Dharmendra 2 ¦ 8 ¦ 25 6 ¦ 104/0 - 105/0 ¦ Hotline ¦ Dharmendra 1 ¦ 8 ¦ 26 | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | OPGW | 55 | 15 | opgw_accessories, project_details, stretch_readiness, stringing, summary_status | R2: S.L. ¦ Drum No. ¦ Section Length ¦ OPGW Drum length ¦ Section Readinesss ¦ Starting Date ¦ Completion Date ¦ Completed Length ¦ Status ¦ Ganag Name R3: Drum No. ¦ From ¦ T.O.T ¦ - ¦ To ¦ T.O.T ¦ M ¦ M ¦ M R5: 2 ¦ AHMD-NVSA-2 ¦ 106A/3 ¦ DA+3 ¦ - ¦ 112/0 ¦ DD45+0 ¦ 3772.138 ¦ 3995 ¦ Ready ¦ 2025-03-05 00:00:00 ¦ 2025-03-06 00:00:00 ¦ 3772.138 ¦ Completed ¦ BK Construction R6: 3 ¦ AHMD-NVSA-3 ¦ 112/0 ¦ DD45+0 ¦ - ¦ 119/3 ¦ DA+0 ¦ 4215.508 ¦ 4442 ¦ Ready ¦ 2025-03-19 00:00:00 ¦ 2025-03-19 00:00:00 ¦ 4215.508 ¦ Completed ¦ BK Construction R7: 4 ¦ AHMD-NVSA-4 ¦ 119/3 ¦ DA+0 ¦ - ¦ 124A/1 ¦ DA+3 ¦ 2974.7690000000002 ¦ 3187 ¦ Ready ¦ 2025-03-12 00:00:00 ¦ 2025-03-12 00:00:00 ¦ 2974.7690000000002 ¦ Completed ¦ BK Construction | OPGW stringing Status for TA-325 Project S.L. ¦ Drum No. ¦ Section Length ¦ OPGW Drum length ¦ Section Readinesss ¦ Starting Date ¦ Completion Date ¦ Completed Length ¦ Status ¦ Ganag Name Drum No. ¦ From ¦ T.O.T ¦ - ¦ To ¦ T.O.T ¦ M ¦ M ¦ M 1 ¦ AHMD-NVSA-1 ¦ 101/0 ¦ DD60+35 ¦ - ¦ 106A/3 ¦ DA+3 ¦ 4309.407999999999 ¦ 4581 ¦ Not Ready 2 ¦ AHMD-NVSA-2 ¦ 106A/3 ¦ DA+3 ¦ - ¦ 112/0 ¦ DD45+0 ¦ 3772.138 ¦ 3995 ¦ Ready ¦ 2025-03-05 00:00:00 ¦ 2025-03-06 00:00:00 ¦ 3772.138 ¦ Completed ¦ BK Construction 3 ¦ AHMD-NVSA-3 ¦ 112/0 ¦ DD45+0 ¦ - ¦ 119/3 ¦ DA+0 ¦ 4215.508 ¦ 4442 ¦ Ready ¦ 2025-03-19 00:00:00 ¦ 2025-03-19 00:00:00 ¦ 4215.508 ¦ Completed ¦ BK Construction 4 ¦ AHMD-NVSA-4 ¦ 119/3 ¦ DA+0 ¦ - ¦ 124A/1 ¦ DA+3 ¦ 2974.7690000000002 ¦ 3187 ¦ Ready ¦ 2025-03-12 00:00:00 ¦ 2025-03-12 00:00:00 ¦ 2974.7690000000002 ¦ Completed ¦ BK Construction 5 ¦ AHMD-NVSA-5 ¦ 124A/1 ¦ DA+3 ¦ - ¦ 129/0 ¦ DD60+6 ¦ 4445.602000000001 ¦ 4684 ¦ Ready ¦ 2025-03-07 00:00:00 ¦ 2025-03-08 00:00:00 ¦ 4445.602000000001 ¦ Completed ¦ BK Construction | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Splicing | 50 | 10 | opgw_accessories, project_details, summary_status | R2: S.L. ¦ Joint Loc. ¦ Tower Type ¦ Suspension / Tension ¦ Joint Box. Nos. ¦ Completion Date ¦ Joint Box Status ¦ Downlead Clamp Qty. ¦ Gang Name ¦ Remarks R5: 3 ¦ 112/0 ¦ DD45+0 ¦ T ¦ 1 ¦ 2025-05-24 00:00:00 ¦ Completed ¦ 32 ¦ Amit Communication R6: 4 ¦ 119/3 ¦ DA+0 ¦ S ¦ 1 ¦ 2025-05-25 00:00:00 ¦ Completed ¦ 32 ¦ Amit Communication R7: 5 ¦ 124A/1 ¦ DA+3 ¦ S ¦ 1 ¦ 2025-05-25 00:00:00 ¦ Completed ¦ 34 ¦ Amit Communication R8: 6 ¦ 129/0 ¦ DD60+6 ¦ T ¦ 1 ¦ 2025-05-26 00:00:00 ¦ Completed ¦ 35 ¦ Amit Communication | OPGW Joint Box Details S.L. ¦ Joint Loc. ¦ Tower Type ¦ Suspension / Tension ¦ Joint Box. Nos. ¦ Completion Date ¦ Joint Box Status ¦ Downlead Clamp Qty. ¦ Gang Name ¦ Remarks 1 ¦ 101/0 ¦ DD60+35 ¦ T ¦ 50 2 ¦ 106A/3 ¦ DA+3 ¦ S ¦ 34 3 ¦ 112/0 ¦ DD45+0 ¦ T ¦ 1 ¦ 2025-05-24 00:00:00 ¦ Completed ¦ 32 ¦ Amit Communication 4 ¦ 119/3 ¦ DA+0 ¦ S ¦ 1 ¦ 2025-05-25 00:00:00 ¦ Completed ¦ 32 ¦ Amit Communication 5 ¦ 124A/1 ¦ DA+3 ¦ S ¦ 1 ¦ 2025-05-25 00:00:00 ¦ Completed ¦ 34 ¦ Amit Communication 6 ¦ 129/0 ¦ DD60+6 ¦ T ¦ 1 ¦ 2025-05-26 00:00:00 ¦ Completed ¦ 35 ¦ Amit Communication | ok
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 | Add. Earthing | 28 | 19 | earthing_tack, project_details, summary_status, supply | R2: Sl. No ¦ Loc No. ¦ Type of Tower ¦ Distance from Previous additional earthing location (M) ¦ Tower Height (M) ¦ Tower Height (M) X 2 ¦ Additional Earthwire Required as per Drawings per Tower (Mtr) ¦ Extra Length Included per Tower for Laying of Earthwire (Mtr) ¦ Requirement of Supply of G.S Earthwire 7/3.66mm (Mtr) ¦ Type of Earthing & Qty. (Set) ¦ Earthing Flat required as per Tower type (Nos) ¦ R14: 11 ¦ AP158A/0 ¦ DD45+6 ¦ 7705.37 ¦ 76.53 ¦ 153.06 ¦ 15 ¦ 5 ¦ 173.06 ¦ Pipe Type ¦ 1 ¦ 64 ¦ 2 ¦ 2 ¦ WIP ¦ Deepak sarkar ¦ Shield wire complete R15: 12 ¦ AP164/0 ¦ DB2+0 ¦ 7094.14 ¦ 70.53 ¦ 141.06 ¦ 15 ¦ 5 ¦ 161.06 ¦ Pipe Type ¦ 1 ¦ 60 ¦ 2 ¦ 2 ¦ WIP ¦ Deepak sarkar ¦ Shield wire complete R16: 13 ¦ AP168/0 ¦ DC1+0 ¦ 7201.86 ¦ 70.53 ¦ 141.06 ¦ 15 ¦ 5 ¦ 161.06 ¦ Pipe Type ¦ 1 ¦ 60 ¦ 2 ¦ 2 ¦ WIP ¦ Deepak sarkar ¦ Shield wire complete R17: 14 ¦ AP182/0 ¦ DD60+0 ¦ 7975.74 ¦ 70.53 ¦ 141.06 ¦ 15 ¦ 5 ¦ 161.06 ¦ Pipe Type ¦ 1 ¦ 60 ¦ 2 ¦ 2 ¦ WIP ¦ Deepak sarkar ¦ Shield wire complete | TL02 for 765kV D/C Ahmedabad-Navsari (South Gujarat) Line ADDITIONAL EARTHING QUANTITIES (APPROVAL LETTER NO. WRTS-II/KHAVDA II-C/TL/KEC/ 661, DATED 18.10.2024) Sl. No ¦ Loc No. ¦ Type of Tower ¦ Distance from Previous additional earthing location (M) ¦ Tower Height (M) ¦ Tower Height (M) X 2 ¦ Additional Earthwire Required as per Drawings per Tower (Mtr) ¦ Extra Length Included per Tower for Laying of Earthwire (Mtr) ¦ Requirement of Supply of G.S Earthwire 7/3.66mm (Mtr) ¦ Type of Earthing & Qty. (Set) ¦ Earthing Flat required as per Tower type (Nos) ¦ Down Lead Clamp (Nos) ¦ P G Clamp (Nos) ¦ Lugs (Nos) ¦ Starting Date ¦ Completion Date ¦ Status ¦ Gang Name ¦ Remarks A ¦ B ¦ C ¦ D ¦ E ¦ F ¦ G ¦ H ¦ I = (F+G+H) 1 ¦ AP111/0 ¦ DC1+0 ¦ 7739.65 ¦ 70.53 ¦ 141.06 ¦ 15 ¦ 5 ¦ 161.06 ¦ Pipe Type ¦ 1 ¦ 60 ¦ 2 ¦ 2 ¦ 2026-01-16 00:00:00 ¦ 2026-01-16 00:00:00 ¦ Complete ¦ Nand Kishor 2 ¦ AP125/0 ¦ DD60+0 ¦ 7735.31 ¦ 70.53 ¦ 141.06 ¦ 15 ¦ 5 ¦ 161.06 ¦ Pipe Type ¦ 1 ¦ 60 ¦ 2 ¦ 2 ¦ 2026-01-03 00:00:00 ¦ 2026-01-03 00:00:00 ¦ Complete ¦ Nand Kishor 3 ¦ AP131/0 ¦ DD45+3 ¦ 7771.24 ¦ 73.53 ¦ 147.06 ¦ 15 ¦ 5 ¦ 167.06 ¦ Pipe Type ¦ 1 ¦ 62 ¦ 2 ¦ 2 ¦ 2025-12-27 00:00:00 ¦ 2025-12-27 00:00:00 ¦ Complete ¦ Nand Kishor 4 ¦ AP135/0 ¦ DC2+25 ¦ 6057.67 ¦ 95.3 ¦ 190.6 ¦ 15 ¦ 5 ¦ 210.6 ¦ Pipe Type ¦ 1 ¦ 77 ¦ 2 ¦ 2 ¦ 2025-12-28 00:00:00 ¦ 2025-12-28 00:00:00 ¦ Complete ¦ Nand Kishor 5 ¦ AP135B/0 ¦ DB1+0 ¦ 6023.7 ¦ 70.53 ¦ 141.06 ¦ 15 ¦ 5 ¦ 161.06 ¦ Pipe Type ¦ 1 ¦ 60 ¦ 2 ¦ 2 ¦ 2025-12-29 00:00:00 ¦ 2025-12-29 00:00:00 ¦ Complete ¦ Nand Kishor | ok
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | TA413_PBNTL | 268 | 256 | project_details, summary_status, survey_soil, visual_l2 | R6: Sl. No. ¦ Activity ¦ LOA Quantity ¦ As per latest Estimate ¦ Cumm. Progress up to last Month ¦ Cumm L2 Schedule till Apr'26 ¦ Plan for this Month ¦ Current Month Achieved (As on dated ) ¦ Today ¦ Cumulative Progress ¦ Balance ¦ No of Gangs ¦ Remarks R7: 1 ¦ Route Alignment (Km) ¦ 112.611 ¦ 117.85085099999999 ¦ 117.85085099999999 ¦ 112.611 ¦ 117.85085099999999 ¦ Completed R8: 2 ¦ Detailed Survey Completed(Km) ¦ 112.611 ¦ 117.85085099999999 ¦ 117.85085099999999 ¦ 112.611 ¦ 117.85085099999999 ¦ Completed R9: 2a) ¦ Detailed Survey Submitted(Km) ¦ 112.611 ¦ 117.85085099999999 ¦ 117.85085099999999 ¦ 112.611 ¦ 117.85085099999999 ¦ Completed R10: 2b) ¦ Detail survey approved (Kms) ¦ 112.611 ¦ 117.85085099999999 ¦ 117.85085099999999 ¦ 112.611 ¦ 117.85085099999999 ¦ Completed | TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 ¦ 20.05.2026 Name of Client: PowerGrid Bikaner Neemrana Transmission Limited (Power Grid Corporation of India) ¦ Project Duration : 21 Month EOT -30/06/2026 Name of Line: 765 KV D/C Bikaner III - Neemrana II TL02 LOA Value: 389.96 Crore NOA No: CC/T/W-TW/DOM/A04/23/10569/NOA-1&2/24-103421/01&02 Date.12/03/2024 Amendment -II Comp Value As on: 390 Crore Office: Hansera, Bikaner, Rajasthan. Sl. No. ¦ Activity ¦ LOA Quantity ¦ As per latest Estimate ¦ Cumm. Progress up to last Month ¦ Cumm L2 Schedule till Apr'26 ¦ Plan for this Month ¦ Current Month Achieved (As on dated ) ¦ Today ¦ Cumulative Progress ¦ Balance ¦ No of Gangs ¦ Remarks 1 ¦ Route Alignment (Km) ¦ 112.611 ¦ 117.85085099999999 ¦ 117.85085099999999 ¦ 112.611 ¦ 117.85085099999999 ¦ Completed 2 ¦ Detailed Survey Completed(Km) ¦ 112.611 ¦ 117.85085099999999 ¦ 117.85085099999999 ¦ 112.611 ¦ 117.85085099999999 ¦ Completed | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Visual Chart | 165 | 72 | earthing_tack, erection, foundation, project_details, row_hindrance, statutory_crossing, stringing, visual_l2 | R4: S. No. ¦ Description ¦ UOM ¦ Total Qty ¦ Completed ¦ Balance ¦ Power Line Crossing ¦ Stringing U/P ¦ Stringing completed R5: 1 ¦ Foundation ¦ Nos ¦ 316 ¦ 316 ¦ Tack Welding U/P ¦ Tack Welding completed R6: 2 ¦ Earthing ¦ Nos ¦ 309 ¦ 307 ¦ 2 ¦ NH / SH Crossing ¦ Erection U/P ¦ 4 ¦ Erection completed R7: 3 ¦ Tower Erection ¦ Nos ¦ 306 ¦ 302 ¦ 4 ¦ 1 ¦ Foundation U/P ¦ Foundation completed R8: 4 ¦ Rough Sag ¦ KM ¦ 117.85085099999999 ¦ 74.641204 ¦ 43.20964699999999 ¦ Railway Crossing ¦ 3 | KEC INTERNATIONAL LIMITED Name of Line: 765 KV D/C Bikaner III - Neemrana II TL02 LOA Value: 389.96 Crore ¦ Visual Chart S. No. ¦ Description ¦ UOM ¦ Total Qty ¦ Completed ¦ Balance ¦ Power Line Crossing ¦ Stringing U/P ¦ Stringing completed 1 ¦ Foundation ¦ Nos ¦ 316 ¦ 316 ¦ Tack Welding U/P ¦ Tack Welding completed 2 ¦ Earthing ¦ Nos ¦ 309 ¦ 307 ¦ 2 ¦ NH / SH Crossing ¦ Erection U/P ¦ 4 ¦ Erection completed 3 ¦ Tower Erection ¦ Nos ¦ 306 ¦ 302 ¦ 4 ¦ 1 ¦ Foundation U/P ¦ Foundation completed 4 ¦ Rough Sag ¦ KM ¦ 117.85085099999999 ¦ 74.641204 ¦ 43.20964699999999 ¦ Railway Crossing ¦ 3 5 ¦ Final Sag ¦ KM ¦ 117.85085099999999 ¦ 74.64099999999999 ¦ 43.209851 ¦ 1 ¦ Excavation U/P ¦ 2 ¦ Excavation completed | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stretch readiness | 298 | 14 | erection, foundation, statutory_crossing, stretch_readiness, stringing, summary_status | R4: Description ¦ Stringing Type ¦ Line length ¦ TSE/Manual Completed ¦ Stringing Compl ¦ Stringing WIP ¦ Balanced ¦ Remarks R5: Stringing ¦ 62 ¦ 117.85605400000003 ¦ 26 ¦ 74.64232 ¦ 43.21373400000003 R9: Sl No. ¦ Section ¦ Section Length (M) ¦ Type ¦ Crossing details ¦ No. of Locations (Including for end twr) ¦ Foundation ¦ Erection ¦ Stringing R10: Completed ¦ Balance ¦ Completed ¦ Balance ¦ Month ¦ Remarks R12: 1 ¦ AP-1 - AP-2A ¦ 290.21 ¦ Manual ¦ 1 ¦ 1 ¦ 1 ¦ Jan'26 ¦ Completed | Stretch Readiness Status - 765 KV D/C Bikaner III - Neemrana II TL02 TA-413 Description ¦ Stringing Type ¦ Line length ¦ TSE/Manual Completed ¦ Stringing Compl ¦ Stringing WIP ¦ Balanced ¦ Remarks Stringing ¦ 62 ¦ 117.85605400000003 ¦ 26 ¦ 74.64232 ¦ 43.21373400000003 TSE ¦ 37 ¦ 109.28515900000002 ¦ 23 ¦ 73.466 ¦ 35.81915900000003 ¦ 2 ¦ 14 ¦ 35.81915900000003 Manual ¦ 25 ¦ 8.570895 ¦ 3 ¦ 1.17632 ¦ 7.394575 ¦ 22 ¦ 7.394575 Sl No. ¦ Section ¦ Section Length (M) ¦ Type ¦ Crossing details ¦ No. of Locations (Including for end twr) ¦ Foundation ¦ Erection ¦ Stringing Completed ¦ Balance ¦ Completed ¦ Balance ¦ Month ¦ Remarks Gantry - AP-1 ¦ 150.014 ¦ Manual ¦ 1 ¦ 1 ¦ 1 ¦ mar'26 ¦ pending due to gantry not yet ready | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing | 40 | 25 | stringing, summary_status, supply | R5: From ¦ To ¦ Length in Km's ¦ Cum. Length in Km's ¦ TSE/Manual ¦ Insulator hoisting Start ¦ Insulator Hoisting Complete ¦ Paying Out Start ¦ Paying Out Completed ¦ Final sag start ¦ Final sag complete ¦ Earthwire Final Sag ¦ Jumpuring ¦ Spacering ¦ Clipping ¦ Revenue ¦ JMC Status ¦ Name of the Contractor ¦ Remarks R6: 1 ¦ 1 ¦ AP-34 ¦ AP-35 ¦ 4.898588 ¦ 4.898588 ¦ TSE ¦ 2025-02-06 00:00:00 ¦ 2025-02-08 00:00:00 ¦ 2025-02-21 00:00:00 ¦ 2025-02-26 00:00:00 ¦ 2025-03-03 00:00:00 ¦ 2025-03-04 00:00:00 ¦ 2025-03-05 00:00:00 ¦ complete ¦ complete ¦ complete ¦ 4696115.5929277195 ¦ Received ¦ SK Infratech R7: 2 ¦ 1 ¦ 37A/0 ¦ AP-38/0 ¦ 2.583589 ¦ 7.482177 ¦ TSE ¦ 2025-03-11 00:00:00 ¦ 2025-03-13 00:00:00 ¦ 2025-03-17 00:00:00 ¦ 2025-03-20 00:00:00 ¦ 2025-04-15 00:00:00 ¦ 2025-04-16 00:00:00 ¦ 2025-04-17 00:00:00 ¦ 2025-04-21 00:00:00 ¦ 2025-05-06 00:00:00 ¦ complete ¦ 2476802.0067449096 ¦ Received ¦ SK Infratech R8: 3 ¦ 2 ¦ AP-38 ¦ AP-39 ¦ 4.163677 ¦ 11.645854 ¦ TSE ¦ 2025-03-26 00:00:00 ¦ 2025-03-28 00:00:00 ¦ 2025-03-29 00:00:00 ¦ 2025-04-05 00:00:00 ¦ 2025-04-15 00:00:00 ¦ 2025-04-16 00:00:00 ¦ 2025-04-17 00:00:00 ¦ complete ¦ complete ¦ complete ¦ 3991580.52965763 ¦ Received ¦ SK Infratech R9: 4 ¦ 3 ¦ AP-39 ¦ AP-40 ¦ 4.716 ¦ 16.361854 ¦ TSE ¦ 2025-04-04 00:00:00 ¦ 2025-04-06 00:00:00 ¦ 2025-04-25 00:00:00 ¦ 2025-04-29 00:00:00 ¦ 2025-04-29 00:00:00 ¦ 2025-04-30 00:00:00 ¦ 2025-05-27 00:00:00 ¦ complete ¦ 2025-12-23 00:00:00 ¦ 2025-12-23 00:00:00 ¦ 4521074.46804 ¦ Received ¦ SK Infratech | KEC International Limited TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Details of Stringing ¦ 20.05.2026 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Section ¦ 7.195548760160239 From ¦ To ¦ Length in Km's ¦ Cum. Length in Km's ¦ TSE/Manual ¦ Insulator hoisting Start ¦ Insulator Hoisting Complete ¦ Paying Out Start ¦ Paying Out Completed ¦ Final sag start ¦ Final sag complete ¦ Earthwire Final Sag ¦ Jumpuring ¦ Spacering ¦ Clipping ¦ Revenue ¦ JMC Status ¦ Name of the Contractor ¦ Remarks 1 ¦ 1 ¦ AP-34 ¦ AP-35 ¦ 4.898588 ¦ 4.898588 ¦ TSE ¦ 2025-02-06 00:00:00 ¦ 2025-02-08 00:00:00 ¦ 2025-02-21 00:00:00 ¦ 2025-02-26 00:00:00 ¦ 2025-03-03 00:00:00 ¦ 2025-03-04 00:00:00 ¦ 2025-03-05 00:00:00 ¦ complete ¦ complete ¦ complete ¦ 4696115.5929277195 ¦ Received ¦ SK Infratech 2 ¦ 1 ¦ 37A/0 ¦ AP-38/0 ¦ 2.583589 ¦ 7.482177 ¦ TSE ¦ 2025-03-11 00:00:00 ¦ 2025-03-13 00:00:00 ¦ 2025-03-17 00:00:00 ¦ 2025-03-20 00:00:00 ¦ 2025-04-15 00:00:00 ¦ 2025-04-16 00:00:00 ¦ 2025-04-17 00:00:00 ¦ 2025-04-21 00:00:00 ¦ 2025-05-06 00:00:00 ¦ complete ¦ 2476802.0067449096 ¦ Received ¦ SK Infratech 3 ¦ 2 ¦ AP-38 ¦ AP-39 ¦ 4.163677 ¦ 11.645854 ¦ TSE ¦ 2025-03-26 00:00:00 ¦ 2025-03-28 00:00:00 ¦ 2025-03-29 00:00:00 ¦ 2025-04-05 00:00:00 ¦ 2025-04-15 00:00:00 ¦ 2025-04-16 00:00:00 ¦ 2025-04-17 00:00:00 ¦ complete ¦ complete ¦ complete ¦ 3991580.52965763 ¦ Received ¦ SK Infratech | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection | 361 | 14 | erection, summary_status | R3: Details of Erection ¦ 14162.895667999981 ¦ 1319.534328754491 ¦ 20.05.2026 R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Start ¦ Complete ¦ Gang name ¦ Weight ¦ Revenue ¦ Name of Supervisor ¦ Remarks ¦ JMC Status R5: 1 ¦ 1 ¦ 29A/2 ¦ DA+6 ¦ 2024-09-12 00:00:00 ¦ 2024-09-21 00:00:00 ¦ Bhagwan construction ¦ 43.804424 ¦ 4.0811880970016 ¦ Manoj Kumar Gupta ¦ Completed ¦ Received R6: 2 ¦ 2 ¦ 29/5 ¦ DA+0 ¦ 2024-09-21 00:00:00 ¦ 2024-09-27 00:00:00 ¦ Bhagwan construction ¦ 36.159755999999994 ¦ 3.3689466109103994 ¦ Manoj Kumar Gupta ¦ Completed ¦ Received R7: 3 ¦ 1 ¦ 29/3 ¦ DA+0 ¦ 2024-09-28 00:00:00 ¦ 2024-10-03 00:00:00 ¦ Bhagwan construction ¦ 36.159755999999994 ¦ 3.3689466109103994 ¦ Manoj Kumar Gupta ¦ Completed ¦ Received | KEC International Limited TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Details of Erection ¦ 14162.895667999981 ¦ 1319.534328754491 ¦ 20.05.2026 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Start ¦ Complete ¦ Gang name ¦ Weight ¦ Revenue ¦ Name of Supervisor ¦ Remarks ¦ JMC Status 1 ¦ 1 ¦ 29A/2 ¦ DA+6 ¦ 2024-09-12 00:00:00 ¦ 2024-09-21 00:00:00 ¦ Bhagwan construction ¦ 43.804424 ¦ 4.0811880970016 ¦ Manoj Kumar Gupta ¦ Completed ¦ Received 2 ¦ 2 ¦ 29/5 ¦ DA+0 ¦ 2024-09-21 00:00:00 ¦ 2024-09-27 00:00:00 ¦ Bhagwan construction ¦ 36.159755999999994 ¦ 3.3689466109103994 ¦ Manoj Kumar Gupta ¦ Completed ¦ Received 3 ¦ 1 ¦ 29/3 ¦ DA+0 ¦ 2024-09-28 00:00:00 ¦ 2024-10-03 00:00:00 ¦ Bhagwan construction ¦ 36.159755999999994 ¦ 3.3689466109103994 ¦ Manoj Kumar Gupta ¦ Completed ¦ Received 4 ¦ 2 ¦ 29/4 ¦ DA+3 ¦ 2024-10-03 00:00:00 ¦ 2024-10-08 00:00:00 ¦ Bhagwan construction ¦ 37.931087999999995 ¦ 3.5339787792191997 ¦ Manoj Kumar Gupta ¦ Completed ¦ Received | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | L2 Plan vs Actual | 50 | 31 | earthing_tack, foundation, summary_status, supply, visual_l2 | R3: Line Length :- 112 KM ¦ Status as on ¦ 20.05.2026 R4: S.No. ¦ Activity / Description ¦ UOM ¦ Qty ¦ Start Date ¦ End Date ¦ L2 ¦ Cumm. Till date ¦ Balance ¦ 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ 9 ¦ 10 ¦ 11 R7: 1 ¦ Line Materials ¦ % ¦ 100 ¦ 2024-03-20 00:00:00 ¦ 2025-03-22 00:00:00 R10: c ¦ Receipt at site of Stubs & Earthing ¦ EA ¦ 287 ¦ 2024-04-18 00:00:00 ¦ 2024-11-20 00:00:00 ¦ 287 ¦ 25 ¦ 50 ¦ 50 ¦ 50 ¦ 80 ¦ 32 R11: Stubs - Actual Status ¦ 313 ¦ -26 ¦ 5 ¦ 130 ¦ 10 ¦ 40 ¦ 16 ¦ 44 ¦ 34 | Project :- TL02 for Bikaner-III - Neemrana-II 765 KV DC Line Part-I associated with Transmission system for excavation of power from Rajasthan REZ Ph-IV (Part-I) (Bikaner Complex: 7.7 GW) Ref. :- CC/T/W-TW/DOM/A04/23/10569/NOA-1 & 2/24-103421/01 & 02 Date. 12/03/2024 Line Length :- 112 KM ¦ Status as on ¦ 20.05.2026 S.No. ¦ Activity / Description ¦ UOM ¦ Qty ¦ Start Date ¦ End Date ¦ L2 ¦ Cumm. Till date ¦ Balance ¦ 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ 9 ¦ 10 ¦ 11 Till date ¦ 2024-03-01 00:00:00 ¦ 2024-04-01 00:00:00 ¦ 2024-05-01 00:00:00 ¦ 2024-06-01 00:00:00 ¦ 2024-07-01 00:00:00 ¦ 2024-08-01 00:00:00 ¦ 2024-09-01 00:00:00 ¦ 2024-10-01 00:00:00 ¦ 2024-11-01 00:00:00 ¦ 2024-12-01 00:00:00 ¦ 2025-01-01 00:00:00 ¦ 2025-02-01 00:00:00 ¦ 2025-03-01 00:00:00 ¦ 2025-04-01 00:00:00 ¦ 2025-05-01 00:00:00 ¦ 2025-06-01 00:00:00 ¦ 2025-07-01 00:00:00 ¦ 2025-08-01 00:00:00 ¦ 2025-09-01 00:00:00 Supplies 1 ¦ Line Materials ¦ % ¦ 100 ¦ 2024-03-20 00:00:00 ¦ 2025-03-22 00:00:00 a ¦ Vendor Finalisation ¦ % ¦ 100 ¦ 2024-03-20 00:00:00 ¦ 2024-04-24 00:00:00 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Survey summary | 2733 | 15 | summary_status, survey_soil | R1: Survey and Profile Drawing Status ¦ Detail Survey ¦ Check Survey R2: S.No. ¦ Section ¦ Length ¦ Detail Survey ¦ Detail Survey data to Engg ¦ Profile by Engg ¦ TS Site Check ¦ Final Profile ¦ Submission to PGCIL ¦ Approval by PGCIL ¦ Check Survey ¦ Re-Profile by Engg. ¦ Submission to PGCIL ¦ Approval R34: Balance ¦ 0.7721540000000005 ¦ 103.08632399999999 ¦ 0.7721540000000005 ¦ 3.335014000000001 | Survey and Profile Drawing Status ¦ Detail Survey ¦ Check Survey S.No. ¦ Section ¦ Length ¦ Detail Survey ¦ Detail Survey data to Engg ¦ Profile by Engg ¦ TS Site Check ¦ Final Profile ¦ Submission to PGCIL ¦ Approval by PGCIL ¦ Check Survey ¦ Re-Profile by Engg. ¦ Submission to PGCIL ¦ Approval 1 ¦ AP 0 - AP 3 ¦ 0.772154 ¦ 2024-05-23 00:00:00 ¦ 2024-05-30 00:00:00 ¦ 2024-05-30 00:00:00 ¦ 2024-05-22 00:00:00 ¦ 2024-08-12 00:00:00 ¦ 2024-08-12 00:00:00 ¦ 2024-08-12 00:00:00 2 ¦ AP 3 - AP 4 ¦ 4.860728 ¦ 2024-05-23 00:00:00 ¦ 2024-05-30 00:00:00 ¦ 2024-05-30 00:00:00 ¦ 2024-05-22 00:00:00 ¦ 2024-05-25 00:00:00 ¦ 2024-05-25 00:00:00 ¦ 2024-08-09 00:00:00 ¦ 2024-08-12 00:00:00 ¦ 2024-08-12 00:00:00 ¦ 2024-08-12 00:00:00 3 ¦ AP 4 - AP 5 ¦ 5.066611 ¦ 2024-05-08 00:00:00 ¦ 2024-05-15 00:00:00 ¦ 2024-05-17 00:00:00 ¦ 2024-05-22 00:00:00 ¦ 2024-05-25 00:00:00 ¦ 2024-05-25 00:00:00 ¦ 2024-05-28 00:00:00 ¦ 2024-08-22 00:00:00 ¦ 2024-08-22 00:00:00 ¦ 2024-07-19 00:00:00 4 ¦ AP 5 - AP 6 ¦ 4.83787 ¦ 2024-05-08 00:00:00 ¦ 2024-05-15 00:00:00 ¦ 2024-05-17 00:00:00 ¦ 2024-06-04 00:00:00 ¦ 2024-06-04 00:00:00 ¦ 2024-06-05 00:00:00 ¦ 2024-06-13 00:00:00 ¦ 2024-07-27 00:00:00 ¦ 1900-01-02 00:00:00 ¦ 2024-07-30 00:00:00 5 ¦ AP 6 - AP 7 ¦ 4.90124 ¦ 2024-05-08 00:00:00 ¦ 2024-05-15 00:00:00 ¦ 2024-05-17 00:00:00 ¦ 2024-05-22 00:00:00 ¦ 2024-05-28 00:00:00 ¦ 2024-05-28 00:00:00 ¦ 2024-05-28 00:00:00 ¦ 2024-08-22 00:00:00 ¦ 2024-08-22 00:00:00 ¦ 2024-08-19 00:00:00 6 ¦ AP 7 - AP 8 ¦ 5.134054 ¦ 2024-05-08 00:00:00 ¦ 2024-05-15 00:00:00 ¦ 2024-05-17 00:00:00 ¦ 2024-05-22 00:00:00 ¦ 2024-05-28 00:00:00 ¦ 2024-05-28 00:00:00 ¦ 2024-05-28 00:00:00 ¦ 2024-07-27 00:00:00 ¦ 2024-07-27 00:00:00 ¦ 2024-07-30 00:00:00 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Detailed Survey | 78 | 10 | project_details, summary_status, survey_soil | R4: Sl.No. ¦ SPAN ¦ Profile Status ¦ Route Length ¦ Section Length (Km) ¦ Submitted For Approval ¦ Approved Date ¦ Profile approval date ¦ Remarks R20: 15 ¦ 11/0 ¦ 12/0 ¦ Submiteed ¦ 0.2468 ¦ 0.2468 ¦ 2024-05-27 00:00:00 ¦ 2024-05-27 00:00:00 ¦ 2024-05-29 00:00:00 ¦ NATIONAL HIGHWAY NH-62 R28: 23 ¦ 19/0 ¦ 20/0 ¦ 0.2795 ¦ 0.2795 ¦ 2024-06-05 00:00:00 ¦ 2024-07-26 00:00:00 ¦ 2024-07-26 00:00:00 ¦ RAILWAY TRACK (SINGLE LINE ) ELECTRTIC | KEC International Limited Name of Line: 765 KV D/C Bikaner III - Neemrana II TL02 LOA Value: 389.96 Crore Detailed Survey ¦ 20.05.2026 Sl.No. ¦ SPAN ¦ Profile Status ¦ Route Length ¦ Section Length (Km) ¦ Submitted For Approval ¦ Approved Date ¦ Profile approval date ¦ Remarks From Section ¦ To Section 1 ¦ Gnatry BKN -III ¦ 1/0 ¦ 0.15 ¦ 0.15 ¦ 2025-02-21 00:00:00 ¦ 2025-02-21 00:00:00 ¦ 2025-02-21 00:00:00 2 ¦ 1/0 ¦ 2A/0 ¦ 0.29021 ¦ 0.29021 ¦ 2025-02-21 00:00:00 ¦ 2025-02-21 00:00:00 ¦ 2025-02-21 00:00:00 3 ¦ 2A/0 ¦ 3A/0 ¦ 2.836992 ¦ 2.836992 ¦ 2025-02-21 00:00:00 ¦ 2025-02-21 00:00:00 ¦ 2025-02-21 00:00:00 ¦ STATE HIGHWAY SH-3 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Check Survey | 60 | 7 | project_details, survey_soil | R4: Sl.No. ¦ SPAN ¦ Section Length (Km) ¦ Submitted For Approval ¦ Approval date ¦ Remarks R20: 15 ¦ 11/0 ¦ 12/0 ¦ 0.2468 ¦ 2024-07-24 00:00:00 ¦ NH - 62 R28: 23 ¦ 19/0 ¦ 20/0 ¦ 0.2795 ¦ 2024-07-24 00:00:00 ¦ Railway Line Electrified SingleTrack R37: 32 ¦ 28/0 ¦ 29/0 ¦ 0.2118 ¦ 2024-07-24 00:00:00 ¦ Expressway Crossing (NH754A) | KEC International Limited Name of Line: 765 KV D/C Bikaner III - Neemrana II TL02 LOA Value: 389.96 Crore Check Survey ¦ 20.05.2026 Sl.No. ¦ SPAN ¦ Section Length (Km) ¦ Submitted For Approval ¦ Approval date ¦ Remarks From Section ¦ To Section 1 ¦ Gnatry BKN -III ¦ 1/0 ¦ 0.15 ¦ 2025-02-21 00:00:00 ¦ 2025-02-21 00:00:00 2 ¦ 1/0 ¦ 2A/0 ¦ 0.29021 ¦ 2025-02-21 00:00:00 ¦ 2025-02-21 00:00:00 3 ¦ 2A/0 ¦ 3A/0 ¦ 2.836992 ¦ 2025-02-21 00:00:00 ¦ 2025-02-21 00:00:00 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Earthing | 313 | 11 | earthing_tack | R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Complete ¦ Name of the Contractor ¦ Name of Supervisor ¦ Rev Month ¦ Remarks R5: 1 ¦ 1 ¦ 8/10 ¦ DA+0 ¦ Sandy ¦ 2024-08-18 00:00:00 ¦ 2024-08-18 00:00:00 ¦ Sanjay Construction ¦ Reshpaul Tyagi ¦ Aug'2024 ¦ Completed R6: 2 ¦ 2 ¦ 8/9 ¦ DA+3 ¦ Sandy ¦ 2024-08-18 00:00:00 ¦ 2024-08-18 00:00:00 ¦ Sanjay Construction ¦ Reshpaul Tyagi ¦ Aug'2024 ¦ Completed R7: 3 ¦ 3 ¦ 8/8 ¦ DA+9 ¦ Sandy ¦ 2024-08-18 00:00:00 ¦ 2024-08-18 00:00:00 ¦ Sanjay Construction ¦ Reshpaul Tyagi ¦ Aug'2024 ¦ Completed R8: 4 ¦ 4 ¦ 8/5 ¦ DA+9 ¦ Sandy ¦ 2024-08-20 00:00:00 ¦ 2024-08-20 00:00:00 ¦ Sanjay Construction ¦ Reshpaul Tyagi ¦ Aug'2024 ¦ Completed | KEC International Limited TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Details of Earthing ¦ 20.05.2026 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Complete ¦ Name of the Contractor ¦ Name of Supervisor ¦ Rev Month ¦ Remarks 1 ¦ 1 ¦ 8/10 ¦ DA+0 ¦ Sandy ¦ 2024-08-18 00:00:00 ¦ 2024-08-18 00:00:00 ¦ Sanjay Construction ¦ Reshpaul Tyagi ¦ Aug'2024 ¦ Completed 2 ¦ 2 ¦ 8/9 ¦ DA+3 ¦ Sandy ¦ 2024-08-18 00:00:00 ¦ 2024-08-18 00:00:00 ¦ Sanjay Construction ¦ Reshpaul Tyagi ¦ Aug'2024 ¦ Completed 3 ¦ 3 ¦ 8/8 ¦ DA+9 ¦ Sandy ¦ 2024-08-18 00:00:00 ¦ 2024-08-18 00:00:00 ¦ Sanjay Construction ¦ Reshpaul Tyagi ¦ Aug'2024 ¦ Completed 4 ¦ 4 ¦ 8/5 ¦ DA+9 ¦ Sandy ¦ 2024-08-20 00:00:00 ¦ 2024-08-20 00:00:00 ¦ Sanjay Construction ¦ Reshpaul Tyagi ¦ Aug'2024 ¦ Completed | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tack Welding | 252 | 11 | earthing_tack | R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Start ¦ Complete ¦ Name of the Contractor ¦ Name of Supervisor ¦ Remarks ¦ Painting R5: 1 ¦ 1 ¦ 34/4 ¦ DA+6 ¦ 2025-01-12 00:00:00 ¦ 2025-01-12 00:00:00 ¦ MB Sharma ¦ Manoj Kumar Gupta ¦ Completed R6: 2 ¦ 2 ¦ 34/7 ¦ DA+0 ¦ 2025-01-13 00:00:00 ¦ 2025-01-13 00:00:00 ¦ MB Sharma ¦ Manoj Kumar Gupta ¦ Completed R7: 3 ¦ 3 ¦ 34/10 ¦ DA-3 ¦ 2025-01-14 00:00:00 ¦ 2025-01-14 00:00:00 ¦ MB Sharma ¦ Manoj Kumar Gupta ¦ Completed R8: 4 ¦ 4 ¦ 34/3 ¦ DA+1.5 ¦ 2025-01-15 00:00:00 ¦ 2025-01-15 00:00:00 ¦ MB Sharma ¦ Manoj Kumar Gupta ¦ Completed | KEC International Limited TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Details of Tack Welding ¦ 20.05.2026 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Start ¦ Complete ¦ Name of the Contractor ¦ Name of Supervisor ¦ Remarks ¦ Painting 1 ¦ 1 ¦ 34/4 ¦ DA+6 ¦ 2025-01-12 00:00:00 ¦ 2025-01-12 00:00:00 ¦ MB Sharma ¦ Manoj Kumar Gupta ¦ Completed 2 ¦ 2 ¦ 34/7 ¦ DA+0 ¦ 2025-01-13 00:00:00 ¦ 2025-01-13 00:00:00 ¦ MB Sharma ¦ Manoj Kumar Gupta ¦ Completed 3 ¦ 3 ¦ 34/10 ¦ DA-3 ¦ 2025-01-14 00:00:00 ¦ 2025-01-14 00:00:00 ¦ MB Sharma ¦ Manoj Kumar Gupta ¦ Completed 4 ¦ 4 ¦ 34/3 ¦ DA+1.5 ¦ 2025-01-15 00:00:00 ¦ 2025-01-15 00:00:00 ¦ MB Sharma ¦ Manoj Kumar Gupta ¦ Completed | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Final checking | 312 | 13 | earthing_tack, erection, foundation, stringing, summary_status | R4: S. No. ¦ No of ¦ Location ¦ Type of ¦ DS Status as on ¦ 306 ¦ 304 ¦ 302 ¦ 247 ¦ 262 ¦ 189 ¦ Remarks R5: AP ¦ Tower No. ¦ Tower ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Tack welding ¦ Final Checking ¦ Stringing R7: 1 ¦ AP-1 ¦ 1/0 ¦ DD60+0 ¦ Approved ¦ Completed ¦ Completed ¦ Completed ¦ Done ¦ Done ¦ Done R8: 2 ¦ AP-2A ¦ 2A/0 ¦ DD45+0 ¦ Approved ¦ Completed ¦ Completed ¦ Completed ¦ Done ¦ Done ¦ Done R9: 3 ¦ AP-3 ¦ 2A/1 ¦ DA+0 ¦ Approved ¦ Completed ¦ Completed ¦ Completed ¦ Done ¦ Done ¦ Done | Client Name : Power Grid Bhadla III Transmission Limited (PGCIL) 765 kV DC BIKANER-III NEEMRANA-II Transmission Line TA-413 ¦ 19 Bal ¦ 2 ¦ 4 ¦ 59 ¦ 40 ¦ 117 S. No. ¦ No of ¦ Location ¦ Type of ¦ DS Status as on ¦ 306 ¦ 304 ¦ 302 ¦ 247 ¦ 262 ¦ 189 ¦ Remarks AP ¦ Tower No. ¦ Tower ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Tack welding ¦ Final Checking ¦ Stringing Gantry ¦ Gantry 1 ¦ AP-1 ¦ 1/0 ¦ DD60+0 ¦ Approved ¦ Completed ¦ Completed ¦ Completed ¦ Done ¦ Done ¦ Done 2 ¦ AP-2A ¦ 2A/0 ¦ DD45+0 ¦ Approved ¦ Completed ¦ Completed ¦ Completed ¦ Done ¦ Done ¦ Done | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Bird Guard | 30 | 9 | project_details | R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Completion date ¦ Bird Guard ¦ Name of the Contractor ¦ Name of Supervisor ¦ Remarks | KEC International Limited TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Details of Bird Guard (Set Of Three) ¦ 20.05.2026 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Completion date ¦ Bird Guard ¦ Name of the Contractor ¦ Name of Supervisor ¦ Remarks 1 ¦ 1 ¦ 2A/1 ¦ DA+0 ¦ 2026-05-15 00:00:00 ¦ DONE ¦ Jetha Ram ¦ Sanjay Kumar 2 ¦ 2 ¦ 2A/2 ¦ DA+3 ¦ 2026-05-15 00:00:00 ¦ DONE ¦ Jetha Ram ¦ Sanjay Kumar 3 ¦ 3 ¦ 2A/3 ¦ DA+3 ¦ 2026-05-16 00:00:00 ¦ DONE ¦ Jetha Ram ¦ Sanjay Kumar 4 ¦ 4 ¦ 2A/4 ¦ DA+3 ¦ 2026-05-16 00:00:00 ¦ DONE ¦ Jetha Ram ¦ Sanjay Kumar | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Accessories | 14 | 12 | opgw_accessories, supply | R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Danger Plate ¦ Number Plate ¦ Phase Plate ¦ Circuit Plate ¦ Anti Climbing device ¦ Name of the Contractor ¦ Name of Supervisor ¦ Remarks | KEC International Limited TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Details of Accessories ¦ 20.05.2026 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Danger Plate ¦ Number Plate ¦ Phase Plate ¦ Circuit Plate ¦ Anti Climbing device ¦ Name of the Contractor ¦ Name of Supervisor ¦ Remarks | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | OPGW | 23 | 14 | opgw_accessories, stringing | R5: Cum. Sr.No. ¦ Month Sr.No. ¦ Section ¦ Paying Out Start ¦ Paying Out Completed ¦ Final sag ¦ Name of the Contractor ¦ Remarks ¦ Joint Box for 24 fibre OPGW R6: From ¦ To ¦ Section Length in Km's ¦ Drum Length in Km's ¦ Cum. Drum Length in Km's R7: 1 ¦ 1 ¦ 34/0 ¦ 34/12 ¦ 4.547 ¦ 4.719 ¦ 4.547 ¦ 2025-04-19 00:00:00 ¦ 2025-04-19 00:00:00 ¦ 2025-04-19 00:00:00 ¦ B K Construction ¦ Completed R8: 2 ¦ 2 ¦ 37A/0 ¦ 38/5 ¦ 4.455 ¦ 4.666 ¦ 9.001999999999999 ¦ 2025-04-21 00:00:00 ¦ 2025-04-21 00:00:00 ¦ 2025-04-21 00:00:00 ¦ B K Construction ¦ Completed R9: 3 ¦ 3 ¦ 38/5 ¦ 39/6 ¦ 4.61 ¦ 5 ¦ 13.611999999999998 ¦ 2025-04-24 00:00:00 ¦ 2025-04-24 00:00:00 ¦ 2025-04-24 00:00:00 ¦ B K Construction ¦ Completed | KEC International Limited TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Details of OPGW Stringing ¦ 20.05.2026 Cum. Sr.No. ¦ Month Sr.No. ¦ Section ¦ Paying Out Start ¦ Paying Out Completed ¦ Final sag ¦ Name of the Contractor ¦ Remarks ¦ Joint Box for 24 fibre OPGW From ¦ To ¦ Section Length in Km's ¦ Drum Length in Km's ¦ Cum. Drum Length in Km's 1 ¦ 1 ¦ 34/0 ¦ 34/12 ¦ 4.547 ¦ 4.719 ¦ 4.547 ¦ 2025-04-19 00:00:00 ¦ 2025-04-19 00:00:00 ¦ 2025-04-19 00:00:00 ¦ B K Construction ¦ Completed 2 ¦ 2 ¦ 37A/0 ¦ 38/5 ¦ 4.455 ¦ 4.666 ¦ 9.001999999999999 ¦ 2025-04-21 00:00:00 ¦ 2025-04-21 00:00:00 ¦ 2025-04-21 00:00:00 ¦ B K Construction ¦ Completed 3 ¦ 3 ¦ 38/5 ¦ 39/6 ¦ 4.61 ¦ 5 ¦ 13.611999999999998 ¦ 2025-04-24 00:00:00 ¦ 2025-04-24 00:00:00 ¦ 2025-04-24 00:00:00 ¦ B K Construction ¦ Completed | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Foundation | 558 | 18 | foundation, supply | R3: Details of Foundation ¦ 8196.920000000002 ¦ 102.2 ¦ 1058.5199999999995 ¦ 56.919 ¦ 25.149999999999995 ¦ 207.32999999999996 ¦ 20.05.2026 R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Complete ¦ Name of the Contractor ¦ Excavation ¦ M10 ¦ M20 ¦ Steel ¦ Stub ¦ Revenue (In Lakhs) ¦ Name of Supervisor ¦ Stub setting ¦ Remarks R5: 1 ¦ 9/4 ¦ DA+6 ¦ Sandy ¦ 2024-05-29 00:00:00 ¦ 2024-06-06 00:00:00 ¦ Sahu Construction ¦ 289.84 ¦ 3.61 ¦ 37.3 ¦ 2.093 ¦ 0.866 ¦ 7.39 ¦ Harshit Kumar ¦ Pradip Das ¦ Completed ¦ 314.284 R6: 2 ¦ 10/1 ¦ DA+3 ¦ Sandy ¦ 2024-05-30 00:00:00 ¦ 2024-06-07 00:00:00 ¦ Choudhary construction ¦ 289.84 ¦ 3.61 ¦ 37.3 ¦ 2.093 ¦ 0.866 ¦ 7.39 ¦ Shuvam Gupta ¦ Pradip Das ¦ Completed ¦ 314.284 R7: 3 ¦ 10/2 ¦ DA+3 ¦ Sandy ¦ 2024-06-07 00:00:00 ¦ 2024-06-09 00:00:00 ¦ Choudhary construction ¦ 289.84 ¦ 3.61 ¦ 37.3 ¦ 2.093 ¦ 0.866 ¦ 7.39 ¦ Shuvam Gupta ¦ Pradip Das ¦ Completed ¦ 314.284 | KEC International Limited TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Details of Foundation ¦ 8196.920000000002 ¦ 102.2 ¦ 1058.5199999999995 ¦ 56.919 ¦ 25.149999999999995 ¦ 207.32999999999996 ¦ 20.05.2026 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Complete ¦ Name of the Contractor ¦ Excavation ¦ M10 ¦ M20 ¦ Steel ¦ Stub ¦ Revenue (In Lakhs) ¦ Name of Supervisor ¦ Stub setting ¦ Remarks 1 ¦ 9/4 ¦ DA+6 ¦ Sandy ¦ 2024-05-29 00:00:00 ¦ 2024-06-06 00:00:00 ¦ Sahu Construction ¦ 289.84 ¦ 3.61 ¦ 37.3 ¦ 2.093 ¦ 0.866 ¦ 7.39 ¦ Harshit Kumar ¦ Pradip Das ¦ Completed ¦ 314.284 2 ¦ 10/1 ¦ DA+3 ¦ Sandy ¦ 2024-05-30 00:00:00 ¦ 2024-06-07 00:00:00 ¦ Choudhary construction ¦ 289.84 ¦ 3.61 ¦ 37.3 ¦ 2.093 ¦ 0.866 ¦ 7.39 ¦ Shuvam Gupta ¦ Pradip Das ¦ Completed ¦ 314.284 3 ¦ 10/2 ¦ DA+3 ¦ Sandy ¦ 2024-06-07 00:00:00 ¦ 2024-06-09 00:00:00 ¦ Choudhary construction ¦ 289.84 ¦ 3.61 ¦ 37.3 ¦ 2.093 ¦ 0.866 ¦ 7.39 ¦ Shuvam Gupta ¦ Pradip Das ¦ Completed ¦ 314.284 4 ¦ 9/11 ¦ DA+3 ¦ Sandy ¦ 2024-06-09 00:00:00 ¦ 2024-06-11 00:00:00 ¦ Choudhary construction ¦ 289.84 ¦ 3.61 ¦ 37.3 ¦ 2.093 ¦ 0.866 ¦ 7.39 ¦ Shuvam Gupta ¦ Pradip Das ¦ Completed ¦ 314.284 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | JUMPER Details | 65 | 8 | stringing, summary_status | R3: SL. No. ¦ Loc No. ¦ Type of Tower ¦ Short name ¦ Jumper length ¦ Jumper status can be completed ¦ Jumper status ¦ Done by R5: 2 ¦ 2A/0 ¦ DD45+0 ¦ DD45 ¦ 918 ¦ Completed ¦ Rahim Khan R6: 3 ¦ 3A/0 ¦ DD45+3 ¦ DD45 ¦ 918 ¦ Completed ¦ Rahim Khan R7: 4 ¦ 3B/0 ¦ DB1+9 ¦ DB1 ¦ 828 ¦ Completed ¦ Rahim Khan R8: 5 ¦ 4/0 ¦ DB2+9 ¦ DB2 ¦ 828 ¦ Completed ¦ Rahim Khan | Jumper details of Project SL. No. ¦ Loc No. ¦ Type of Tower ¦ Short name ¦ Jumper length ¦ Jumper status can be completed ¦ Jumper status ¦ Done by 1 ¦ 1/0 ¦ DD60+0 ¦ DD60 ¦ 918 2 ¦ 2A/0 ¦ DD45+0 ¦ DD45 ¦ 918 ¦ Completed ¦ Rahim Khan 3 ¦ 3A/0 ¦ DD45+3 ¦ DD45 ¦ 918 ¦ Completed ¦ Rahim Khan 4 ¦ 3B/0 ¦ DB1+9 ¦ DB1 ¦ 828 ¦ Completed ¦ Rahim Khan 5 ¦ 4/0 ¦ DB2+9 ¦ DB2 ¦ 828 ¦ Completed ¦ Rahim Khan 6 ¦ 4A/0 ¦ DB1+3 ¦ DB1 ¦ 828 ¦ Completed ¦ Rahim Khan | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | ROW Tracker | 1048554 | 15 | foundation, project_details, row_hindrance, summary_status | R4: S.No ¦ Loc. No. ¦ T/Type ¦ Activity ¦ Date of 1st approach ¦ Date of last approach ¦ Date of Resolution ¦ Duration of ROW (Days) ¦ Nature of hindrance ¦ Brief description on resolution ¦ Name of Farmer ¦ Mobile no. ¦ Vill. Name ¦ Tehsil R5: 1 ¦ 10/1 ¦ DA+3 ¦ Foundation ¦ 2024-06-03 00:00:00 ¦ 2024-06-06 00:00:00 ¦ 2024-06-07 00:00:00 ¦ 4 ¦ Land owner stopped the work and not allowing to work till finalisation of compentation amount. ¦ Resolved ¦ Bhagirath ¦ 9784543356 ¦ Jaisa, Dhirera(PO) ¦ Lunkaransar R6: 2 ¦ 10/2 ¦ DA+3 ¦ Foundation ¦ 2024-06-03 00:00:00 ¦ 2024-06-06 00:00:00 ¦ 2024-06-07 00:00:00 ¦ 4 ¦ Land owner stopped the work and not allowing to work till finalisation of compentation amount. ¦ Resolved ¦ Devi Lal ¦ 9950185902 ¦ Jaisa, Dhirera(PO) ¦ Lunkaransar R7: 3 ¦ 15/2 ¦ DA+3 ¦ Foundation ¦ 2024-06-14 00:00:00 ¦ 2024-06-17 00:00:00 ¦ 2024-06-17 00:00:00 ¦ 3 ¦ Land owner stopped the work and not allowing to work till finalisation of compentation amount. ¦ Resolved ¦ Muniram Moond ¦ 9929783632 ¦ Meharana ¦ Lunkaransar R9: 5 ¦ 15/7 ¦ DA+0 ¦ Foundation ¦ 2024-06-29 00:00:00 ¦ 2024-07-10 00:00:00 ¦ 2024-07-10 00:00:00 ¦ 11 ¦ Area damage measurement isssue ¦ Resolved ¦ Hetram godara ¦ 8003383931 ¦ Dheereran ¦ Lunkaransar | ROW STATUS ¦ 20.05.2026 Name of Line: 765 KV D/C Bikaner III - Neemrana II TL02 LOA Value: 389.96 Crore ROW Details S.No ¦ Loc. No. ¦ T/Type ¦ Activity ¦ Date of 1st approach ¦ Date of last approach ¦ Date of Resolution ¦ Duration of ROW (Days) ¦ Nature of hindrance ¦ Brief description on resolution ¦ Name of Farmer ¦ Mobile no. ¦ Vill. Name ¦ Tehsil 1 ¦ 10/1 ¦ DA+3 ¦ Foundation ¦ 2024-06-03 00:00:00 ¦ 2024-06-06 00:00:00 ¦ 2024-06-07 00:00:00 ¦ 4 ¦ Land owner stopped the work and not allowing to work till finalisation of compentation amount. ¦ Resolved ¦ Bhagirath ¦ 9784543356 ¦ Jaisa, Dhirera(PO) ¦ Lunkaransar 2 ¦ 10/2 ¦ DA+3 ¦ Foundation ¦ 2024-06-03 00:00:00 ¦ 2024-06-06 00:00:00 ¦ 2024-06-07 00:00:00 ¦ 4 ¦ Land owner stopped the work and not allowing to work till finalisation of compentation amount. ¦ Resolved ¦ Devi Lal ¦ 9950185902 ¦ Jaisa, Dhirera(PO) ¦ Lunkaransar 3 ¦ 15/2 ¦ DA+3 ¦ Foundation ¦ 2024-06-14 00:00:00 ¦ 2024-06-17 00:00:00 ¦ 2024-06-17 00:00:00 ¦ 3 ¦ Land owner stopped the work and not allowing to work till finalisation of compentation amount. ¦ Resolved ¦ Muniram Moond ¦ 9929783632 ¦ Meharana ¦ Lunkaransar 4 ¦ 15/6 ¦ DA+9 ¦ Back filling ¦ 2024-06-29 00:00:00 ¦ 2024-07-10 00:00:00 ¦ 2024-07-10 00:00:00 ¦ 11 ¦ Area damage measurement isssue ¦ Resolved ¦ Mukharam ¦ 9950488419 ¦ Dheereran ¦ Lunkaransar | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | S-Curve FDN | 18 | 20 | foundation, visual_l2 | R2: Month ¦ L2-FDN ¦ Act-Foundation ¦ Cum. L2 Fdn ¦ Cum. Fdn Actual | TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Month ¦ L2-FDN ¦ Act-Foundation ¦ Cum. L2 Fdn ¦ Cum. Fdn Actual 2024-05-01 00:00:00 ¦ 6 ¦ 6 2024-06-01 00:00:00 ¦ 18 ¦ 14 ¦ 24 ¦ 14 2024-07-01 00:00:00 ¦ 18 ¦ 20 ¦ 42 ¦ 34 2024-08-01 00:00:00 ¦ 20 ¦ 23 ¦ 62 ¦ 57 2024-09-01 00:00:00 ¦ 22 ¦ 40 ¦ 84 ¦ 97 2024-10-01 00:00:00 ¦ 22 ¦ 36 ¦ 106 ¦ 133 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | S-Curve Erection | 21 | 20 | erection, visual_l2 | R2: Month ¦ L2-Ere ¦ Act-Erection ¦ Cum. L2 Ere ¦ Cum. Ere. Actual | TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Month ¦ L2-Ere ¦ Act-Erection ¦ Cum. L2 Ere ¦ Cum. Ere. Actual 2024-06-01 00:00:00 ¦ 4 ¦ 4 2024-07-01 00:00:00 ¦ 15 ¦ 19 2024-08-01 00:00:00 ¦ 15 ¦ 34 2024-09-01 00:00:00 ¦ 22 ¦ 2 ¦ 56 ¦ 2 2024-10-01 00:00:00 ¦ 20 ¦ 5 ¦ 76 ¦ 7 2024-11-01 00:00:00 ¦ 22 ¦ 2 ¦ 98 ¦ 9 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | S-Curve Stringing | 20 | 20 | stringing, visual_l2 | R2: Month ¦ L2-Str ¦ Act-Str ¦ Cum. L2 Str ¦ Cum. Str Actual | TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Month ¦ L2-Str ¦ Act-Str ¦ Cum. L2 Str ¦ Cum. Str Actual 2024-08-01 00:00:00 ¦ 4 ¦ 4 2024-09-01 00:00:00 ¦ 4 ¦ 8 2024-10-01 00:00:00 ¦ 8 ¦ 16 2024-11-01 00:00:00 ¦ 8 ¦ 24 2024-12-01 00:00:00 ¦ 8 ¦ 32 2025-01-01 00:00:00 ¦ 8 ¦ 40 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Supply Status | 88 | 11 | opgw_accessories, project_details, summary_status, supply, visual_l2 | R4: Sl. No. ¦ Description ¦ UOM ¦ LOA Qty ¦ Final Est. Qty ¦ L2 Sch till Oct'25 ¦ Cum. Completed ¦ Balance R7: 1 ¦ Stubs ¦ Sets ¦ 287 ¦ 316 ¦ 287 ¦ 316 ¦ 1 R9: 3 ¦ Conductor ¦ KM ¦ 4095 ¦ 4285.056 ¦ 4095 ¦ 4285.056 ¦ 1 R10: 4 ¦ Conductor Accessories H/W ¦ % ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 R11: 5 ¦ Earthwire ¦ KM ¦ 114 ¦ 121.471 ¦ 1 ¦ 121.471 ¦ 1 | SUPPLY STATUS SUMMARY ¦ 20.05.2026 Name of Line: 765 KV D/C Bikaner III - Neemrana II TL02 ¦ SUPPLY STATUS Sl. No. ¦ Description ¦ UOM ¦ LOA Qty ¦ Final Est. Qty ¦ L2 Sch till Oct'25 ¦ Cum. Completed ¦ Balance Qty. ¦ % ¦ Qty. I ¦ SUPPLY 1 ¦ Stubs ¦ Sets ¦ 287 ¦ 316 ¦ 287 ¦ 316 ¦ 1 2 ¦ Towers ¦ Nos ¦ 287 ¦ 306 ¦ 287 ¦ 306 ¦ 1 3 ¦ Conductor ¦ KM ¦ 4095 ¦ 4285.056 ¦ 4095 ¦ 4285.056 ¦ 1 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Hardware Supply | 53 | 15 | opgw_accessories, project_details, summary_status, supply | R5: Sl.No. ¦ Description ¦ Unit ¦ As per LOA ¦ As per Latest Estimate ¦ Receipt Qty. ¦ Balance Required Qty. ¦ Supplier ¦ REMARKS R7: i ¦ 160 KN Insulator ¦ Nos ¦ 5968 ¦ 6084 ¦ 6084 ¦ DECCAN ENTERPRISES ¦ 1 ¦ 10480 R8: ii ¦ 210 KN Insulator ¦ Nos ¦ 4512 ¦ 5760 ¦ 5760 ¦ DECCAN ENTERPRISES ¦ 1 R9: B ¦ AL-59 Zebra Conductor ¦ Kms ¦ 4095 ¦ 4285.056 ¦ 4285 ¦ 0.05599999999958527 ¦ APAR INDUSTRIES LTD ¦ 0.9999869313259852 ¦ Drum ¦ 0.05599999999958527 R10: C ¦ G S Earthwire 7/3.66mm size ¦ Kms ¦ 114 ¦ 121.471 ¦ 121.471 ¦ GEEKAY WIRES PVT. LTD ¦ 1 ¦ Drum | KEC International Limited TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Status of Line Materials, conductor and Tower Accessories Sl.No. ¦ Description ¦ Unit ¦ As per LOA ¦ As per Latest Estimate ¦ Receipt Qty. ¦ Balance Required Qty. ¦ Supplier ¦ REMARKS A ¦ Insulator i ¦ 160 KN Insulator ¦ Nos ¦ 5968 ¦ 6084 ¦ 6084 ¦ DECCAN ENTERPRISES ¦ 1 ¦ 10480 ii ¦ 210 KN Insulator ¦ Nos ¦ 4512 ¦ 5760 ¦ 5760 ¦ DECCAN ENTERPRISES ¦ 1 B ¦ AL-59 Zebra Conductor ¦ Kms ¦ 4095 ¦ 4285.056 ¦ 4285 ¦ 0.05599999999958527 ¦ APAR INDUSTRIES LTD ¦ 0.9999869313259852 ¦ Drum ¦ 0.05599999999958527 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Crossing status | 64 | 12 | foundation, statutory_crossing, summary_status | R2: Sl. ¦ From ¦ To ¦ Sections in (mtrs) ¦ Name of Crossing ¦ Owner ¦ Approval status ¦ Status ¦ Remarks R3: No ¦ FDN ¦ ERE ¦ STR R12: 7 ¦ AP 11 ¦ AP 12 ¦ 242.893 ¦ NH - 62 ¦ Approved ¦ AP-11-Completed AP 12-Completed ¦ AP-11-Completed AP 12-Completed R13: 8 ¦ AP 28 ¦ AP 29 ¦ 211.209 ¦ Amristar - Jamnagar Expressway NH-754 A ¦ Approved ¦ AP-28-Completed AP 29-Completed ¦ AP-28-Completed AP 29-Completed | TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 Sl. ¦ From ¦ To ¦ Sections in (mtrs) ¦ Name of Crossing ¦ Owner ¦ Approval status ¦ Status ¦ Remarks No ¦ FDN ¦ ERE ¦ STR Power Line Crossing–5 nos 1 ¦ AP 12 ¦ AP 13 ¦ 329.728 ¦ 132 KV S/C BKN-LKS T/L ¦ RVPN ¦ Approved ¦ AP12-Completed AP13-Completed ¦ AP12-Completed AP13-Completed 2 ¦ AP 14 ¦ AP 15 ¦ 223.816 ¦ 400 KV D/C SUR-BKN ¦ ADANI ¦ Approved ¦ AP14-Completed AP15-Completed ¦ AP14-Completed AP15-Completed 3 ¦ AP 22 ¦ AP 23 ¦ 259.048 ¦ 220 KV S/C SUR-BKN ¦ RVPN ¦ Approved ¦ AP22-Completed AP23-Completed ¦ AP22-Completed AP23-Completed 4 ¦ AP 24 ¦ AP 25 ¦ 244.029 ¦ 400 KV S/C STP-BKN T/L ¦ RVPN ¦ Approved ¦ AP24-Completed AP25-Completed ¦ AP24-Completed AP25-Completed | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tower Abstract sheet | 314 | 16 |  | R2: S. No. ¦ Location ¦ Type of ¦ Structure details tower for tower qty ¦ S. No. ¦ Location ¦ Type of ¦ Structure details tower for tower qty | Overall Tower location details As per Previous Estimate ¦ Overall Tower location details As per Latest Estimate S. No. ¦ Location ¦ Type of ¦ Structure details tower for tower qty ¦ S. No. ¦ Location ¦ Type of ¦ Structure details tower for tower qty Tower No. ¦ Tower ¦ TOT ¦ Tower Qty ¦ Total Qty ¦ Tower No. ¦ Tower ¦ TOT ¦ Tower Qty ¦ Total Qty (after oilpipe line diversion) ¦ Total Qty (before oilpipe line diversion) Gantry ¦ Gantry ¦ DA+0 ¦ 30 ¦ 241 ¦ Gantry ¦ Gantry ¦ DA+0 ¦ 33 ¦ 244 ¦ 246 1 ¦ 1/0 ¦ DD60+0 ¦ DA+1.5 ¦ 24 ¦ 1 ¦ 1/0 ¦ DD60+0 ¦ DA-1.5 ¦ 12 2 ¦ 2/0 ¦ DD45+0 ¦ DA+3 ¦ 66 ¦ 2 ¦ 2A/0 ¦ DD45+0 ¦ DA-3 ¦ 12 3 ¦ 3/0 ¦ DB2+0 ¦ DA+4.5 ¦ 1 ¦ 3 ¦ 2A/1 ¦ DA+0 ¦ DA+1.5 ¦ 24 4 ¦ 3/1 ¦ DA+3 ¦ DA+6 ¦ 49 ¦ 4 ¦ 2A/2 ¦ DA+3 ¦ DA+3 ¦ 69 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Statutory Proposals | 1279 | 15 | statutory_crossing, summary_status | R5: Sl.No ¦ Description of Crossing ¦ Crossing Authority ¦ Proposal Submission Status ¦ Present status ¦ Contact Details ¦ Remarks R7: 1 ¦ AP-12 ¦ AP-13 ¦ 132 KV S/C BKN-LKS T/L ¦ RVPN ¦ SUBMITTED ON DT: 24.07.2024 ¦ Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 ¦ Proposal Submitted to RVPN Authority on dated 21.10.2024 Site Joint visit done on date 12.11.2024 NOC obtained - 06.12.2024 R8: 2 ¦ AP-14 ¦ AP-15 ¦ 400 KV D/C SUR-BKN ¦ Adani Power ¦ SUBMITTED ON DT: 24.07.2024 ¦ Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 ¦ Proposal Submitted to Concern Adani Authority and soft copy on dated 28.10.2024 Site Joint visit done on dtd 26.11.2024 NOC obtained on dtd: 21.01.2025 R9: 3 ¦ AP-22 ¦ AP-23 ¦ 220 KV S/C SUR-BKN ¦ RVPN ¦ SUBMITTED ON DT: 24.07.2024 ¦ Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 ¦ Proposal Submitted to RVPN Authority on dated 21.10.2024 Site joint visit done on date-13.11.2024 NOC obtained - 06.12.2024 R10: 4 ¦ AP-24 ¦ AP-25 ¦ 400 KV S/C STP-BKN T/L ¦ RVPN ¦ SUBMITTED ON DT: 24.07.2024 ¦ Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 ¦ Proposal Submitted to RVPN Authority on dated 21.10.2024 Site joint visit done on date-13.11.2024 NOC obtained - 06.12.2024 | OWNER: M/S. M/S. POWERGRID BIKANER NEEMRANA TRANSMISSION LIMITED (POWER GRID CORPORATION OF INDIA) CONTRACTOR: M/S. KEC INTERNATIONAL LIMITED. PROJECT: CONSTRUCTION OF 765KV D/C Bikaner III to Neemrana II Transmission Line STATUTORY PROPOSALS STATUS Sl.No ¦ Description of Crossing ¦ Crossing Authority ¦ Proposal Submission Status ¦ Present status ¦ Contact Details ¦ Remarks POWER LINE CROSSINGS 1 ¦ AP-12 ¦ AP-13 ¦ 132 KV S/C BKN-LKS T/L ¦ RVPN ¦ SUBMITTED ON DT: 24.07.2024 ¦ Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 ¦ Proposal Submitted to RVPN Authority on dated 21.10.2024 Site Joint visit done on date 12.11.2024 NOC obtained - 06.12.2024 2 ¦ AP-14 ¦ AP-15 ¦ 400 KV D/C SUR-BKN ¦ Adani Power ¦ SUBMITTED ON DT: 24.07.2024 ¦ Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 ¦ Proposal Submitted to Concern Adani Authority and soft copy on dated 28.10.2024 Site Joint visit done on dtd 26.11.2024 NOC obtained on dtd: 21.01.2025 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tower Abstarct | 303 | 13 | row_hindrance, survey_soil | R3: S. No. ¦ No of ¦ Location ¦ Type of ¦ Approved details survey ¦ Remarks R6: 2 ¦ AP-1 ¦ 1/0 ¦ DD60+0 ¦ Hold R7: 3 ¦ AP-2 ¦ 2/0 ¦ DD45+0 ¦ Hold | Over all Tower Location details S. No. ¦ No of ¦ Location ¦ Type of ¦ Approved details survey ¦ Remarks AP ¦ Tower No. ¦ Tower ¦ 20.05.2026 1 ¦ AP-0 ¦ Gantry ¦ Gantry ¦ Approved 2 ¦ AP-1 ¦ 1/0 ¦ DD60+0 ¦ Hold 3 ¦ AP-2 ¦ 2/0 ¦ DD45+0 ¦ Hold 4 ¦ AP-3 ¦ 3/0 ¦ DB2+0 ¦ Approved 5 ¦ 3/1 ¦ DA+3 ¦ Approved | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Location Summary | 782 | 21 | earthing_tack, erection, foundation, summary_status | R2: S. No. ¦ No of ¦ Location ¦ Type of ¦ RC ¦ Span ¦ Cumm. ¦ DS Status as on ¦ 306 ¦ 303 ¦ 303 ¦ 116 ¦ 26 ¦ Remarks R3: AP ¦ Tower No. ¦ Tower ¦ Length (m) ¦ Span (km) ¦ 2025-11-15 00:00:00 ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Tack welding ¦ SPT R6: 1 ¦ AP-1 ¦ 1/0 ¦ DD60+0 ¦ T ¦ 0.15 ¦ Approved ¦ Completed ¦ Completed ¦ Completed R8: 2 ¦ AP-2A ¦ 2A/0 ¦ DD45+0 ¦ T ¦ 0.44020000000000004 ¦ Approved ¦ Completed ¦ Completed ¦ Completed R10: 3 ¦ AP-3 ¦ 2A/1 ¦ DA+0 ¦ 0.8182 ¦ Approved ¦ Completed ¦ Completed ¦ Completed | Over all Tower Location details S. No. ¦ No of ¦ Location ¦ Type of ¦ RC ¦ Span ¦ Cumm. ¦ DS Status as on ¦ 306 ¦ 303 ¦ 303 ¦ 116 ¦ 26 ¦ Remarks AP ¦ Tower No. ¦ Tower ¦ Length (m) ¦ Span (km) ¦ 2025-11-15 00:00:00 ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Tack welding ¦ SPT Gantry ¦ Gantry Gantry ¦ 150.014 1 ¦ AP-1 ¦ 1/0 ¦ DD60+0 ¦ T ¦ 0.15 ¦ Approved ¦ Completed ¦ Completed ¦ Completed 1/0 ¦ 290.21 2 ¦ AP-2A ¦ 2A/0 ¦ DD45+0 ¦ T ¦ 0.44020000000000004 ¦ Approved ¦ Completed ¦ Completed ¦ Completed | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Foundation Daily Progress | 1340 | 37 | foundation, summary_status | R1: Foundation Daily Progress Register ¦ A ¦ B ¦ C ¦ D | Foundation Daily Progress Register ¦ A ¦ B ¦ C ¦ D As on ¦ 20.05.2026 ¦ Sub-Total ¦ 309 ¦ 310 ¦ 313 ¦ 316 ¦ 309 ¦ 312 ¦ 313 ¦ 309 ¦ 313 ¦ 311 ¦ 310 ¦ 314 S.No. ¦ Date ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Competed ¦ F ¦ P ¦ C ¦ F ¦ P ¦ C ¦ F ¦ P ¦ C ¦ F ¦ P ¦ C ¦ Slump ¦ Test Cube 1 ¦ 2024-05-30 00:00:00 ¦ 9/4 ¦ DA+6 ¦ Sandy ¦ Competed ¦ 1 ¦ 1 ¦ 55 ¦ F(D) ¦ F(A) ¦ F(A) ¦ 2024-05-30 00:00:00 ¦ 2024-06-27 00:00:00 ¦ 55 ¦ 11.054 ¦ 11.054 ¦ DA-3 ¦ 4.726 ¦ 2.755 2 ¦ 2024-06-01 00:00:00 ¦ 10/1 ¦ DA+3 ¦ Sandy ¦ Competed ¦ 1 ¦ 1 ¦ 55 ¦ Pit-A(F) ¦ Pit-A(F) ¦ Pit-A(F) ¦ 2024-06-01 00:00:00 ¦ 2024-06-29 00:00:00 ¦ 55 ¦ 11.054 ¦ 11.054 ¦ DA-1.5 ¦ 4.726 ¦ 2.755 3 ¦ 2024-06-02 00:00:00 ¦ 10/1 ¦ DA+3 ¦ Sandy ¦ Competed ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 50 ¦ Pit-C(P) ¦ Pit-C(P) ¦ Pit-C(P) ¦ 2024-06-02 00:00:00 ¦ 2024-06-30 00:00:00 ¦ 40 ¦ 11.054 4 ¦ 2024-06-03 00:00:00 ¦ 9/4 ¦ DA+6 ¦ Sandy ¦ Competed ¦ 1 ¦ 1 ¦ 1 ¦ 52 ¦ F(B) ¦ P(A) ¦ P(D) ¦ 2024-06-03 00:00:00 ¦ 2024-07-01 00:00:00 ¦ 52 ¦ 5.527 ¦ 5.51 ¦ 11.036999999999999 ¦ DA+1.5 5 ¦ 2024-06-04 00:00:00 ¦ 9/4 ¦ DA+6 ¦ Sandy ¦ Competed ¦ 1 ¦ 1 ¦ 40 ¦ C(A) ¦ C(D) ¦ C(D) ¦ 2024-06-04 00:00:00 ¦ 2024-07-02 00:00:00 ¦ 40 ¦ 2.086 ¦ 2.086 ¦ DA+3 ¦ 5.527 ¦ 2.755 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tower PRS abstract | 43 | 11 | project_details, survey_soil, visual_l2 | R4: S.No. ¦ Type of Structure ¦ As per LOA ¦ As per Previous Estimate ¦ As per Latest Estimate ¦ Detail survey ¦ PR released ¦ Balance ¦ Approved ¦ PR released ¦ Balance | TA-413 Tower Schedule Total ¦ 287 ¦ 298 ¦ 306 ¦ 306 ¦ 309 ¦ -3 ¦ 306 ¦ 309 ¦ -3 As per approved Detail survey TS ¦ As per Approved Detail survey TS S.No. ¦ Type of Structure ¦ As per LOA ¦ As per Previous Estimate ¦ As per Latest Estimate ¦ Detail survey ¦ PR released ¦ Balance ¦ Approved ¦ PR released ¦ Balance 1 ¦ DA-3 ¦ 241 ¦ 241 ¦ 246 ¦ 12 ¦ 12 ¦ 12 ¦ 12 2 ¦ DA-1.5 ¦ 12 ¦ 12 ¦ 12 ¦ 12 3 ¦ DA+0 ¦ 33 ¦ 33 ¦ 33 ¦ 33 4 ¦ DA+1.5 ¦ 24 ¦ 24 ¦ 24 ¦ 24 | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stretch readiness (2) | 75 | 19 | erection, foundation, statutory_crossing, stretch_readiness, stringing, summary_status | R4: Description ¦ Line length ¦ Section ready for stringing ¦ Completed ¦ Balance Available section ¦ Balance Work R9: Section ¦ Section Length ¦ Type ¦ Crossing details ¦ No. of Locations (Including for end twr) ¦ Foundation ¦ Erection ¦ Stringing ¦ Remarks ¦ Stretch Ready ¦ Stringing status R10: Balance ¦ Balance ¦ Paying out ¦ Final Sag R11: Completed ¦ Balance ¦ Bal. Loc. ¦ Completed ¦ Balance ¦ Bal. Loc. ¦ Completed ¦ Balance ¦ Completed ¦ Balance R28: 17 ¦ AP-11/0 - AP-12/0 ¦ 242.893 ¦ Manual ¦ NH-62 ¦ 1 ¦ 1 ¦ 12/0 ¦ 1 | Stretch Readiness Status - 765 KV D/C Bikaner III - Neemrana II TL02 TA-413 Description ¦ Line length ¦ Section ready for stringing ¦ Completed ¦ Balance Available section ¦ Balance Work Stringing ¦ 117.85083100000003 TSE ¦ 110.17009600000003 Manual ¦ 7.680734999999999 Section ¦ Section Length ¦ Type ¦ Crossing details ¦ No. of Locations (Including for end twr) ¦ Foundation ¦ Erection ¦ Stringing ¦ Remarks ¦ Stretch Ready ¦ Stringing status Balance ¦ Balance ¦ Paying out ¦ Final Sag Completed ¦ Balance ¦ Bal. Loc. ¦ Completed ¦ Balance ¦ Bal. Loc. ¦ Completed ¦ Balance ¦ Completed ¦ Balance | repaired_defined_names (ValueError)
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | 2026-05-20 | Area | 30 | 20 |  |  | Location no ¦ TOT ¦ Span ¦ Area (m^2) ¦ Span Area A ¦ B ¦ C=Span*67 mtr ¦ WORKING SHEET 4A/0 ¦ DB1+3 ¦ 34895460.788644 ¦ DA+6 TOWER ¦ DA+9 TOWER 340 ¦ 22780 ¦ Length ¦ Length 4A/1 ¦ DA+6 ¦ 1163.422274012 ¦ J1 ¦ 30.46624 ¦ J1 ¦ 31.921.63 419.999 ¦ 28139.933 ¦ G1 ¦ 4.55 ¦ G1 ¦ 4.55 4A/2 ¦ DA+6 ¦ 1163.422274012 ¦ K=(+1M EXTENSION BOTH SIDE) ¦ 2 ¦ K=(+1M EXTENSION BOTH SIDE) ¦ 2 415 ¦ 27805 ¦ Total (G1+K+JI) ¦ 37.016239999999996 ¦ Total (G1+K+JI) ¦ 6.55 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Project Details | 14 | 11 | project_details | R1: Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manager ¦ Section Incharge ¦ Supervisor | Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manager ¦ Section Incharge ¦ Supervisor TA 414 ¦ 765kV D/C VATAMAN NAVSARI TL04 ¦ Powergrid Vataman Transmission Limited ¦ 2024-03-12 00:00:00 ¦ 2025-12-11 00:00:00 ¦ Mr. Pawan Shrivastava ¦ Mr Arun Felbin ¦ Mr. Nitin Ashok Bendale ¦ Mr Vivek Kumar Gupta ¦ Mr. Sanjay Tiwari ¦ Mr. Noton Ghosh Mr. Vivekanand Bera ¦ Mr. Kalicharan Patel Mr. Vipin Chandra Deshmukh ¦ Mr. Ishwar Mahto Mr. Raju Mahto Mr. Shankar Mahto Mr. Doulat Mahto Mr. Atul kumar | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | 765KV TA 414 VNTL | 20 | 15 | project_details, summary_status, survey_soil, visual_l2 | R2: Project Name ¦ 765KV D/C HEXA VATAMAN - NAVSARI TL (PKG 04) ¦ NOA Start Date ¦ 2024-03-12 00:00:00 ¦ PCH ¦ Mr. Arun Felbin R3: Client Name ¦ Powergrid Vataman Transmission Ltd ¦ LOA End Date ¦ 2025-12-11 00:00:00 ¦ Regional Manager ¦ Mr. Nitin Bandale R7: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Submitted till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks R8: Rout Alignment ¦ km ¦ 127.799 ¦ 127.799 ¦ 127.799 ¦ 127.799 ¦ 127.799 ¦ Completed R9: Detailed Survey ¦ km ¦ 127.799 ¦ 127.799 ¦ 127.799 ¦ 127.799 ¦ 127.799 ¦ Completed | Project Code ¦ TA 414 ¦ Date ¦ 2026-05-20 00:00:00 ¦ President-T&D ¦ Mr. Ganesh Srinivasan Project Name ¦ 765KV D/C HEXA VATAMAN - NAVSARI TL (PKG 04) ¦ NOA Start Date ¦ 2024-03-12 00:00:00 ¦ PCH ¦ Mr. Arun Felbin Client Name ¦ Powergrid Vataman Transmission Ltd ¦ LOA End Date ¦ 2025-12-11 00:00:00 ¦ Regional Manager ¦ Mr. Nitin Bandale Revised End Date ¦ 2026-05-11 00:00:00 ¦ Planning Engineer ¦ Mr. Pawan Shrivastava ¦ Project Manger ¦ Mr. Vivek Kumar Gupta \ Check Survey Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Submitted till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks Rout Alignment ¦ km ¦ 127.799 ¦ 127.799 ¦ 127.799 ¦ 127.799 ¦ 127.799 ¦ Completed | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | VNTL - KEC | 19 | 13 | foundation, summary_status, survey_soil, visual_l2 | R5: Sr No. ¦ Activity ¦ Estimated Quantity ¦ Cumm. Progress up to till last Month (Apr'26) ¦ Target as per L2 Schedule Cummulative (upto May'26) ¦ L3 Plan for the month (May'26 ) ¦ Today's Progress ¦ Progress in this month ¦ Cumm. Progress till date ¦ Cumm. Balance ¦ WIP ¦ No of Gangs ¦ Remark R6: 1 ¦ Route Alignment (Km) ¦ 127.799 ¦ 127.799 ¦ 130 ¦ 127.799 R7: 2 ¦ Detailed Survey (Km) ¦ 127.799 ¦ 127.799 ¦ 130 ¦ 127.799 R9: 4 ¦ Check Survey (Km) ¦ 127.799 ¦ 127.799 ¦ 130 ¦ 127.799 R10: 5 ¦ Soil Investigation (Nos.) ¦ 28 ¦ 28 ¦ 28 | KEC INTERNATIONAL LIMITED ¦ 2026-05-20 00:00:00 Name of Client: Powergrid Vataman Transmission Limited Name of Line:Tl-04 , 765 kV D/C Vataman - Navsari Transmission Line NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 Sr No. ¦ Activity ¦ Estimated Quantity ¦ Cumm. Progress up to till last Month (Apr'26) ¦ Target as per L2 Schedule Cummulative (upto May'26) ¦ L3 Plan for the month (May'26 ) ¦ Today's Progress ¦ Progress in this month ¦ Cumm. Progress till date ¦ Cumm. Balance ¦ WIP ¦ No of Gangs ¦ Remark 1 ¦ Route Alignment (Km) ¦ 127.799 ¦ 127.799 ¦ 130 ¦ 127.799 2 ¦ Detailed Survey (Km) ¦ 127.799 ¦ 127.799 ¦ 130 ¦ 127.799 3 ¦ Profiling (Km) ¦ 127.799 ¦ 127.799 ¦ 130 ¦ 127.799 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Sheet5 | 77 | 2 |  |  | 127/1 135/0 139/1 139/2 139/3 140/0 167/0 173/0 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Sheet3 | 26 | 4 |  |  | A 127/2 ¦ 127/2128/0135/0139/0139/2141/1141/2145/5145/6148/3161/0166/0175/1182/0183/0183/1183/3194/0214/3214/6217/4225/3244/0244/2250/2 128/0 135/0 139/0 ¦ 127/2128/0135/0139/0139/2141/1141/2145/5145/6148/3161/0166/0175/1182/0183/0183/1183/3194/0214/3214/6217/4225/3244/0244/2250/2 139/2 141/1 141/2 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Sheet1 | 5 | 7 |  |  | District ¦ Till Dec'24 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 Bharuch ¦ 14 ¦ 9 ¦ 14 ¦ 4 ¦ 1 Surat ¦ 4 ¦ 17 ¦ 4 Navsari ¦ 4 ¦ 7 ¦ 6 ¦ 2 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | DPR Sheet | 33 | 7 | summary_status, survey_soil |  | KEC INTERNATIONAL LIMITED DAILY PROGRESS REPORT : SUBMISSION STATUS AS ON ¦ 2026-05-20 00:00:00 Name of the Project: ¦ TL-04 , 765 kV D/C Vataman - Navsari Transmission Line Contract No. & Date : ¦ CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 ROUTE ALIGNMENT PROGRESS SUMMARY TOTAL QTY (Tentative) ¦ COMPLETED UP TO PREV MONTH ¦ COMP. IN CURRENT MONTH ¦ CUMULATIVE ¦ BAL.QTY 127.799 ¦ 127.799 ¦ 127.799 SOIL INVESTIGATION PROGRESS SUMMARY | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | FDN | 329 | 18 | earthing_tack, foundation, project_details, row_hindrance, summary_status | R2: Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Concreting Volume in M3 ¦ Starting Date ¦ Todays Status ¦ Pit A ¦ Pit B ¦ Pit C ¦ Pit D ¦ Cumulative Status ¦ Completion Date ¦ Remarks ¦ Gang name ¦ Earthing Status ¦ Earthing Completion Date R3: 1 ¦ 241/2 ¦ DA+0 ¦ Wet ¦ 2024-05-15 00:00:00 ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ Completed ¦ 2024-05-25 00:00:00 ¦ Suraj Construction ¦ Completed ¦ 2024-05-26 00:00:00 R4: 2 ¦ 241/0 ¦ DD60+0 ¦ Wet Paddy ¦ 2024-05-21 00:00:00 ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ Completed ¦ 2024-05-30 00:00:00 ¦ Suraj Construction ¦ Completed ¦ 2024-05-31 00:00:00 R5: 3 ¦ 241/1 ¦ DA+0 ¦ WPS ¦ 2024-05-28 00:00:00 ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ Completed ¦ 2025-12-31 00:00:00 ¦ ROW Cleared On 28-12-25 ¦ Suraj Construction R6: 4 ¦ 235/3 ¦ DA+0 ¦ PS ¦ 2024-08-31 00:00:00 ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ Completed ¦ 2026-02-13 00:00:00 ¦ Unnati Construction | VNTL Foundation Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Concreting Volume in M3 ¦ Starting Date ¦ Todays Status ¦ Pit A ¦ Pit B ¦ Pit C ¦ Pit D ¦ Cumulative Status ¦ Completion Date ¦ Remarks ¦ Gang name ¦ Earthing Status ¦ Earthing Completion Date 1 ¦ 241/2 ¦ DA+0 ¦ Wet ¦ 2024-05-15 00:00:00 ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ Completed ¦ 2024-05-25 00:00:00 ¦ Suraj Construction ¦ Completed ¦ 2024-05-26 00:00:00 2 ¦ 241/0 ¦ DD60+0 ¦ Wet Paddy ¦ 2024-05-21 00:00:00 ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ Completed ¦ 2024-05-30 00:00:00 ¦ Suraj Construction ¦ Completed ¦ 2024-05-31 00:00:00 3 ¦ 241/1 ¦ DA+0 ¦ WPS ¦ 2024-05-28 00:00:00 ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ Completed ¦ 2025-12-31 00:00:00 ¦ ROW Cleared On 28-12-25 ¦ Suraj Construction 4 ¦ 235/3 ¦ DA+0 ¦ PS ¦ 2024-08-31 00:00:00 ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ Completed ¦ 2026-02-13 00:00:00 ¦ Unnati Construction 5 ¦ 118/0 ¦ DB2+0 ¦ Wet ¦ 2024-09-20 00:00:00 ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ Completed ¦ 2024-10-31 00:00:00 ¦ Anya Infra 6 ¦ 121/5 ¦ DA-3 ¦ Wet ¦ 2024-11-02 00:00:00 ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ RCC Complete ¦ Completed ¦ 2024-11-19 00:00:00 ¦ Adhyey Brothers | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | FDN Completed | 318 | 12 | earthing_tack, foundation, project_details, summary_status | R2: Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Cumulative Status ¦ Completion Date ¦ Remarks ¦ Gang name ¦ Earthing Status ¦ Earthing Completion Date R3: 1 ¦ 241/2 ¦ DA+0 ¦ Wet ¦ 2024-05-15 00:00:00 ¦ Completed ¦ 2024-05-25 00:00:00 ¦ Suraj Construction ¦ Completed ¦ 2024-05-26 00:00:00 R4: 2 ¦ 241/0 ¦ DD60+0 ¦ Wet Paddy ¦ 2024-05-21 00:00:00 ¦ Completed ¦ 2024-05-30 00:00:00 ¦ Suraj Construction ¦ Completed ¦ 2024-05-31 00:00:00 R5: 3 ¦ 118/0 ¦ DB2+0 ¦ Wet ¦ 2024-09-20 00:00:00 ¦ Completed ¦ 2024-10-31 00:00:00 ¦ Anya Infra R6: 4 ¦ 120/3 ¦ DA+6 ¦ Wet Paddy ¦ 2024-11-04 00:00:00 ¦ Completed ¦ 2024-11-12 00:00:00 ¦ Anya Infra | VNTL Foundation Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Cumulative Status ¦ Completion Date ¦ Remarks ¦ Gang name ¦ Earthing Status ¦ Earthing Completion Date 1 ¦ 241/2 ¦ DA+0 ¦ Wet ¦ 2024-05-15 00:00:00 ¦ Completed ¦ 2024-05-25 00:00:00 ¦ Suraj Construction ¦ Completed ¦ 2024-05-26 00:00:00 2 ¦ 241/0 ¦ DD60+0 ¦ Wet Paddy ¦ 2024-05-21 00:00:00 ¦ Completed ¦ 2024-05-30 00:00:00 ¦ Suraj Construction ¦ Completed ¦ 2024-05-31 00:00:00 3 ¦ 118/0 ¦ DB2+0 ¦ Wet ¦ 2024-09-20 00:00:00 ¦ Completed ¦ 2024-10-31 00:00:00 ¦ Anya Infra 4 ¦ 120/3 ¦ DA+6 ¦ Wet Paddy ¦ 2024-11-04 00:00:00 ¦ Completed ¦ 2024-11-12 00:00:00 ¦ Anya Infra 5 ¦ 121/5 ¦ DA-3 ¦ Wet ¦ 2024-11-02 00:00:00 ¦ Completed ¦ 2024-11-19 00:00:00 ¦ Adhyey Brothers 6 ¦ 120/2 ¦ DA+0 ¦ wet ¦ 2024-11-09 00:00:00 ¦ Completed ¦ 2024-11-22 00:00:00 ¦ Anya Infra | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Erection | 245 | 15 | earthing_tack, erection, project_details, summary_status | R3: Sl. No. ¦ Location Number ¦ Type of Tower ¦ Starting Date ¦ Tower Weight (MT) ¦ Status ¦ Completion Date ¦ Gang Name ¦ Manpower ¦ Hindarnce Days ¦ Remarks ¦ Tackweldng Status ¦ Tackwelding start date ¦ Tackwelding Completion date ¦ Sub Contractor name R4: 1 ¦ 117/2 ¦ DA+6 ¦ 2025-08-19 00:00:00 ¦ 44.794098 ¦ Tower Erection Completed ¦ 2025-08-28 00:00:00 ¦ M/S Sakkurddin ¦ 32 R5: 2 ¦ 118/0 ¦ DB2+0 ¦ 2025-05-31 00:00:00 ¦ 54.417843999999995 ¦ Tower Erection Completed ¦ 2025-06-15 00:00:00 ¦ M/s MGR ¦ 24 R6: 3 ¦ 119/0 ¦ DD60+0 ¦ 2025-08-10 00:00:00 ¦ 80.408017 ¦ Tower Erection Completed ¦ 2025-08-30 00:00:00 ¦ M/S Midhun ¦ 42 R7: 4 ¦ 119/2 ¦ DA-3 ¦ 2025-08-07 00:00:00 ¦ 36.044833999999994 ¦ Tower Erection Completed ¦ 2025-08-14 00:00:00 ¦ M/S Sakkurddin ¦ 32 | VNTL Tower Erection Sl. No. ¦ Location Number ¦ Type of Tower ¦ Starting Date ¦ Tower Weight (MT) ¦ Status ¦ Completion Date ¦ Gang Name ¦ Manpower ¦ Hindarnce Days ¦ Remarks ¦ Tackweldng Status ¦ Tackwelding start date ¦ Tackwelding Completion date ¦ Sub Contractor name 1 ¦ 117/2 ¦ DA+6 ¦ 2025-08-19 00:00:00 ¦ 44.794098 ¦ Tower Erection Completed ¦ 2025-08-28 00:00:00 ¦ M/S Sakkurddin ¦ 32 2 ¦ 118/0 ¦ DB2+0 ¦ 2025-05-31 00:00:00 ¦ 54.417843999999995 ¦ Tower Erection Completed ¦ 2025-06-15 00:00:00 ¦ M/s MGR ¦ 24 3 ¦ 119/0 ¦ DD60+0 ¦ 2025-08-10 00:00:00 ¦ 80.408017 ¦ Tower Erection Completed ¦ 2025-08-30 00:00:00 ¦ M/S Midhun ¦ 42 4 ¦ 119/2 ¦ DA-3 ¦ 2025-08-07 00:00:00 ¦ 36.044833999999994 ¦ Tower Erection Completed ¦ 2025-08-14 00:00:00 ¦ M/S Sakkurddin ¦ 32 5 ¦ 119/3 ¦ DA+9 ¦ 2025-07-26 00:00:00 ¦ 46.68935799999999 ¦ Tower Erection Completed ¦ 2025-08-05 00:00:00 ¦ M/S Sakkurddin ¦ 32 6 ¦ 120/7 ¦ DA+3 ¦ 2025-12-28 00:00:00 ¦ 39.45891400000001 ¦ Tower Erection Completed ¦ 2026-01-09 00:00:00 ¦ Subhash ¦ 26 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Erection Completed | 354 | 12 | erection, project_details, summary_status | R1: SL No. ¦ Location No. ¦ Tower Type ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Tower Tightening ¦ Remark R2: 1 ¦ 117/2 ¦ DA+6 ¦ 2025-08-19 00:00:00 ¦ 44.794098 ¦ COMPLETED ¦ 2025-08-28 00:00:00 ¦ M/S Sakkurddin ¦ 32 ¦ Yes R3: 2 ¦ 118/0 ¦ DB2+0 ¦ 2025-05-31 00:00:00 ¦ 54.417843999999995 ¦ COMPLETED ¦ 2025-06-15 00:00:00 ¦ M/s MGR ¦ 24 ¦ Yes R4: 3 ¦ 119/0 ¦ DD60+0 ¦ 2025-08-10 00:00:00 ¦ 80.408017 ¦ COMPLETED ¦ 2025-08-30 00:00:00 ¦ M/S Midhun ¦ 42 ¦ Yes R5: 4 ¦ 119/2 ¦ DA-3 ¦ 2025-08-07 00:00:00 ¦ 36.044833999999994 ¦ COMPLETED ¦ 2025-08-14 00:00:00 ¦ M/S Sakkurddin ¦ 32 ¦ Yes | SL No. ¦ Location No. ¦ Tower Type ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Tower Tightening ¦ Remark 1 ¦ 117/2 ¦ DA+6 ¦ 2025-08-19 00:00:00 ¦ 44.794098 ¦ COMPLETED ¦ 2025-08-28 00:00:00 ¦ M/S Sakkurddin ¦ 32 ¦ Yes 2 ¦ 118/0 ¦ DB2+0 ¦ 2025-05-31 00:00:00 ¦ 54.417843999999995 ¦ COMPLETED ¦ 2025-06-15 00:00:00 ¦ M/s MGR ¦ 24 ¦ Yes 3 ¦ 119/0 ¦ DD60+0 ¦ 2025-08-10 00:00:00 ¦ 80.408017 ¦ COMPLETED ¦ 2025-08-30 00:00:00 ¦ M/S Midhun ¦ 42 ¦ Yes 4 ¦ 119/2 ¦ DA-3 ¦ 2025-08-07 00:00:00 ¦ 36.044833999999994 ¦ COMPLETED ¦ 2025-08-14 00:00:00 ¦ M/S Sakkurddin ¦ 32 ¦ Yes 5 ¦ 119/3 ¦ DA+9 ¦ 2025-07-26 00:00:00 ¦ 46.68935799999999 ¦ COMPLETED ¦ 2025-08-05 00:00:00 ¦ M/S Sakkurddin ¦ 32 ¦ Yes 6 ¦ 120/7 ¦ DA+3 ¦ 2025-12-28 00:00:00 ¦ 39.45891400000001 ¦ COMPLETED ¦ 2026-01-09 00:00:00 ¦ Subhash ¦ 26 ¦ Yes 7 ¦ 120/2 ¦ DA+0 ¦ 2025-06-02 00:00:00 ¦ 37.796346 ¦ COMPLETED ¦ 2025-06-07 00:00:00 ¦ M/S Rahul ¦ 26 ¦ Yes | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Erection Compiled | 353 | 12 | erection, project_details, summary_status | R1: SL No. ¦ Location No. ¦ Tower Type ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Tower Tightening ¦ Remark R2: 1 ¦ 117/1 ¦ DA-3 ¦ 2026-01-15 00:00:00 ¦ 36.044833999999994 ¦ Completed ¦ 2026-01-21 00:00:00 ¦ Subhash ¦ 26 ¦ Yes R3: 2 ¦ 117/2 ¦ DA+6 ¦ 2025-08-19 00:00:00 ¦ 44.794098 ¦ Completed ¦ 2025-08-28 00:00:00 ¦ M/S Sakkurddin ¦ 32 ¦ Yes R4: 3 ¦ 118/0 ¦ DB2+0 ¦ 2025-05-31 00:00:00 ¦ 54.417843999999995 ¦ Completed ¦ 2025-06-15 00:00:00 ¦ M/s MGR ¦ 24 ¦ Yes R5: 4 ¦ 119/0 ¦ DD60+0 ¦ 2025-08-10 00:00:00 ¦ 80.408017 ¦ Completed ¦ 2025-08-30 00:00:00 ¦ M/S Midhun ¦ 42 ¦ Yes | SL No. ¦ Location No. ¦ Tower Type ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Tower Tightening ¦ Remark 1 ¦ 117/1 ¦ DA-3 ¦ 2026-01-15 00:00:00 ¦ 36.044833999999994 ¦ Completed ¦ 2026-01-21 00:00:00 ¦ Subhash ¦ 26 ¦ Yes 2 ¦ 117/2 ¦ DA+6 ¦ 2025-08-19 00:00:00 ¦ 44.794098 ¦ Completed ¦ 2025-08-28 00:00:00 ¦ M/S Sakkurddin ¦ 32 ¦ Yes 3 ¦ 118/0 ¦ DB2+0 ¦ 2025-05-31 00:00:00 ¦ 54.417843999999995 ¦ Completed ¦ 2025-06-15 00:00:00 ¦ M/s MGR ¦ 24 ¦ Yes 4 ¦ 119/0 ¦ DD60+0 ¦ 2025-08-10 00:00:00 ¦ 80.408017 ¦ Completed ¦ 2025-08-30 00:00:00 ¦ M/S Midhun ¦ 42 ¦ Yes 5 ¦ 119/1 ¦ DA-3 ¦ 2026-01-09 00:00:00 ¦ 36.044833999999994 ¦ Completed ¦ 2026-01-15 00:00:00 ¦ Subhash ¦ 26 ¦ Yes 6 ¦ 119/2 ¦ DA-3 ¦ 2025-08-07 00:00:00 ¦ 36.044833999999994 ¦ Completed ¦ 2025-08-14 00:00:00 ¦ M/S Sakkurddin ¦ 32 ¦ Yes 7 ¦ 119/3 ¦ DA+9 ¦ 2025-07-26 00:00:00 ¦ 46.68935799999999 ¦ Completed ¦ 2025-08-05 00:00:00 ¦ M/S Sakkurddin ¦ 32 ¦ Yes | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Stringing | 24 | 19 | row_hindrance, stringing, summary_status, supply | R1: VNTL Stringing ¦ 12.979649000000002 ¦ 445 R2: Sr. No. ¦ Section ¦ No of Towers ¦ length( km) ¦ Manual/TSE ¦ Insulator and hardware fitting done ¦ Engaged Date ¦ Paying Out ¦ Final Sag ¦ P/O Completed ¦ F/S Completed ¦ Stringing Status As on Today ¦ Cumulative Status ¦ Sub Contractor name ¦ Manpower ¦ Hindarnce Days ¦ Remarks R4: 1 ¦ 175/1-176/0 ¦ 2 ¦ 0.445528 ¦ Manual ¦ 2/2 done ¦ 2026-03-26 00:00:00 ¦ 2026-04-06 00:00:00 ¦ 2026-04-12 00:00:00 ¦ 2026-04-07 00:00:00 ¦ 2026-04-12 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-12 00:00:00 ¦ 6 phase final sag complete ¦ Completed ¦ Maa Singhvasini ¦ 27 R5: 2 ¦ 176/0-177/0 ¦ 4 ¦ 1.043334 ¦ TSE ¦ 1/4 done ¦ 2026-04-02 00:00:00 ¦ 2026-04-24 00:00:00 ¦ 2026-04-27 00:00:00 ¦ 2026-04-24 00:00:00 ¦ 2026-04-28 00:00:00 ¦ 2026-04-27 00:00:00 ¦ 2026-04-28 00:00:00 ¦ 6 phase final sag done ¦ Completed ¦ Maa Singhvasini ¦ 27 R6: 3 ¦ 180/2-182/0 ¦ 7 ¦ 2.41262 ¦ TSE ¦ 7/7 done ¦ 2026-04-02 00:00:00 ¦ 2026-04-06 00:00:00 ¦ 2026-04-13 00:00:00 ¦ 2026-04-14 00:00:00 ¦ 2026-04-16 00:00:00 ¦ 2026-04-13 00:00:00 ¦ 2026-04-16 00:00:00 ¦ cliping done spacer u/p ¦ Completed ¦ Alam Construction ¦ 68 ¦ 5 ¦ Gang idle due to 180/3 to 182/0 corridor area row | VNTL Stringing ¦ 12.979649000000002 ¦ 445 Sr. No. ¦ Section ¦ No of Towers ¦ length( km) ¦ Manual/TSE ¦ Insulator and hardware fitting done ¦ Engaged Date ¦ Paying Out ¦ Final Sag ¦ P/O Completed ¦ F/S Completed ¦ Stringing Status As on Today ¦ Cumulative Status ¦ Sub Contractor name ¦ Manpower ¦ Hindarnce Days ¦ Remarks Start Date ¦ End Date ¦ Start Date ¦ End Date 1 ¦ 175/1-176/0 ¦ 2 ¦ 0.445528 ¦ Manual ¦ 2/2 done ¦ 2026-03-26 00:00:00 ¦ 2026-04-06 00:00:00 ¦ 2026-04-12 00:00:00 ¦ 2026-04-07 00:00:00 ¦ 2026-04-12 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-12 00:00:00 ¦ 6 phase final sag complete ¦ Completed ¦ Maa Singhvasini ¦ 27 2 ¦ 176/0-177/0 ¦ 4 ¦ 1.043334 ¦ TSE ¦ 1/4 done ¦ 2026-04-02 00:00:00 ¦ 2026-04-24 00:00:00 ¦ 2026-04-27 00:00:00 ¦ 2026-04-24 00:00:00 ¦ 2026-04-28 00:00:00 ¦ 2026-04-27 00:00:00 ¦ 2026-04-28 00:00:00 ¦ 6 phase final sag done ¦ Completed ¦ Maa Singhvasini ¦ 27 3 ¦ 180/2-182/0 ¦ 7 ¦ 2.41262 ¦ TSE ¦ 7/7 done ¦ 2026-04-02 00:00:00 ¦ 2026-04-06 00:00:00 ¦ 2026-04-13 00:00:00 ¦ 2026-04-14 00:00:00 ¦ 2026-04-16 00:00:00 ¦ 2026-04-13 00:00:00 ¦ 2026-04-16 00:00:00 ¦ cliping done spacer u/p ¦ Completed ¦ Alam Construction ¦ 68 ¦ 5 ¦ Gang idle due to 180/3 to 182/0 corridor area row 4 ¦ 182/0-183/0 ¦ 2 ¦ 0.208909 ¦ Hotline ¦ 2/2 done ¦ 2026-04-01 00:00:00 ¦ 2026-04-05 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-05 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 6 phase final sag complete ¦ Completed ¦ Sanjay Singh ¦ 20 ¦ Hotline 5 ¦ 119/0-120/0 ¦ 5 ¦ 1.421595 ¦ TSE ¦ 5/5 done ¦ 2026-04-02 00:00:00 ¦ 2026-04-16 00:00:00 ¦ 2026-05-18 00:00:00 ¦ 2026-05-18 00:00:00 ¦ 00:00:00 ¦ 119/3-120/0 6 phase paying out done,ew paying out done ¦ EW paying out, 6 phase paying out 119/0-119/3 ¦ Enamul Haque 119/0-119/3,Dharmendra singh 119/3-120/0 ¦ 63 ¦ 22 ¦ Gang idle due to 66kv shutdown till 30.04.26 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Stringing Completed | 15 | 18 | row_hindrance, stringing, summary_status, supply | R3: Sr. No. ¦ Section ¦ No of Towers ¦ length( km) ¦ Manual/TSE ¦ Insulator and hardware fitting done ¦ Engaged Date ¦ Paying Out ¦ Final Sag ¦ P/O Completed ¦ F/S Completed ¦ Cumulative Status ¦ Sub Contractor name ¦ Manpower ¦ Hindarnce Days ¦ Remarks R6: 2 ¦ 175/1-176/0 ¦ 2 ¦ 0.445528 ¦ Manual ¦ 2/2 done ¦ 2026-03-26 00:00:00 ¦ 2026-04-06 00:00:00 ¦ 2026-04-12 00:00:00 ¦ 2026-04-07 00:00:00 ¦ 2026-04-12 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-12 00:00:00 ¦ Completed ¦ Maa Singhvasini ¦ 27 R7: 3 ¦ 245/0-246/0 ¦ 3 ¦ 0.7916259999999999 ¦ Manual ¦ 3/3 Done ¦ 2026-04-09 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-14 00:00:00 ¦ 2026-04-14 00:00:00 ¦ 2026-04-15 00:00:00 ¦ 2026-04-14 00:00:00 ¦ 2026-04-15 00:00:00 ¦ Completed ¦ Bhola Prasad+ Deepak Sarkar ¦ 27 R8: 4 ¦ 180/2-182/0 ¦ 7 ¦ 2.41262 ¦ TSE ¦ 7/7 done ¦ 2026-04-02 00:00:00 ¦ 2026-04-06 00:00:00 ¦ 2026-04-13 00:00:00 ¦ 2026-04-14 00:00:00 ¦ 2026-04-16 00:00:00 ¦ 2026-04-13 00:00:00 ¦ 2026-04-16 00:00:00 ¦ Complete ¦ Alam Construction ¦ 68 ¦ 5 ¦ Gang idle due to 180/3 to 182/0 corridor area row R9: 5 ¦ 183/0-184/0 ¦ 5 ¦ 1.4794100000000001 ¦ TSE ¦ 5/5 done ¦ 2026-04-09 00:00:00 ¦ 2026-04-18 00:00:00 ¦ 2026-04-21 00:00:00 ¦ 2026-04-20 00:00:00 ¦ 2026-04-22 00:00:00 ¦ 2026-04-21 00:00:00 ¦ 2026-04-22 00:00:00 ¦ Complete ¦ Alam Construction ¦ 40 ¦ 1 ¦ Row due to 40 workers remain idle,shutdown cable 11kv removed 24-4-26 | VNTL Stringing 10.396016 Sr. No. ¦ Section ¦ No of Towers ¦ length( km) ¦ Manual/TSE ¦ Insulator and hardware fitting done ¦ Engaged Date ¦ Paying Out ¦ Final Sag ¦ P/O Completed ¦ F/S Completed ¦ Cumulative Status ¦ Sub Contractor name ¦ Manpower ¦ Hindarnce Days ¦ Remarks Start Date ¦ End Date ¦ Start Date ¦ End Date 1 ¦ 182/0-183/0 ¦ 2 ¦ 0.208909 ¦ Hotline ¦ 2/2 done ¦ 2026-04-01 00:00:00 ¦ 2026-04-05 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-05 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-11 00:00:00 ¦ Complete ¦ Sanjay Singh ¦ 20 ¦ Hotline 2 ¦ 175/1-176/0 ¦ 2 ¦ 0.445528 ¦ Manual ¦ 2/2 done ¦ 2026-03-26 00:00:00 ¦ 2026-04-06 00:00:00 ¦ 2026-04-12 00:00:00 ¦ 2026-04-07 00:00:00 ¦ 2026-04-12 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-12 00:00:00 ¦ Completed ¦ Maa Singhvasini ¦ 27 3 ¦ 245/0-246/0 ¦ 3 ¦ 0.7916259999999999 ¦ Manual ¦ 3/3 Done ¦ 2026-04-09 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-14 00:00:00 ¦ 2026-04-14 00:00:00 ¦ 2026-04-15 00:00:00 ¦ 2026-04-14 00:00:00 ¦ 2026-04-15 00:00:00 ¦ Completed ¦ Bhola Prasad+ Deepak Sarkar ¦ 27 4 ¦ 180/2-182/0 ¦ 7 ¦ 2.41262 ¦ TSE ¦ 7/7 done ¦ 2026-04-02 00:00:00 ¦ 2026-04-06 00:00:00 ¦ 2026-04-13 00:00:00 ¦ 2026-04-14 00:00:00 ¦ 2026-04-16 00:00:00 ¦ 2026-04-13 00:00:00 ¦ 2026-04-16 00:00:00 ¦ Complete ¦ Alam Construction ¦ 68 ¦ 5 ¦ Gang idle due to 180/3 to 182/0 corridor area row | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Stringing Compiled | 174 | 24 | project_details, stretch_readiness, stringing, summary_status, supply | R2: S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos. ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name R6: 4 ¦ 120/0 ¦ 121/0 ¦ 120/1,120/2,120/3,120/4,120/5,120/6,120/7 ¦ 2861.678 ¦ TSE ¦ Complete ¦ Done ¦ 2026-05-03 00:00:00 ¦ 2026-05-08 00:00:00 ¦ Completed ¦ 2026-05-10 00:00:00 ¦ 2026-05-15 00:00:00 ¦ Enamul Haque ¦ 49 R74: 72 ¦ 175/0 ¦ 175/1 ¦ 468.001 ¦ Hotline ¦ Complete ¦ Done ¦ 2026-05-02 00:00:00 ¦ 2026-05-07 00:00:00 ¦ Completed ¦ 2026-05-03 00:00:00 ¦ 2026-05-07 00:00:00 ¦ Alam Construction ¦ 40 ¦ Hotline R75: 73 ¦ 175/1 ¦ 176/0 ¦ 445.528 ¦ Manual ¦ Complete ¦ Done ¦ 2026-04-06 00:00:00 ¦ 2026-04-12 00:00:00 ¦ Completed ¦ 2026-04-07 00:00:00 ¦ 2026-04-12 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ Maa Singhvahini ¦ 27 R76: 74 ¦ 176/0 ¦ 177/0 ¦ 176/1,176/2 ¦ 1043.334 ¦ TSE ¦ Complete ¦ Done ¦ 2026-04-24 00:00:00 ¦ 2026-04-27 00:00:00 ¦ Completed ¦ 2026-04-24 00:00:00 ¦ 2026-04-28 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ Alam Construction ¦ 40 | Number of TSE ¦ 2 ¦ 9.319214999999998 S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos. ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name 1 ¦ 117/0 ¦ 118/0 ¦ 117/1,117/2 ¦ 1142.762 ¦ TSE ¦ Ready 2 ¦ 118/0 ¦ 119/0 ¦ 243.824 ¦ Manual ¦ WIP ¦ Done 3 ¦ 119/0 ¦ 120/0 ¦ 119/1,119/2,119/3 ¦ 1421.595 ¦ TSE ¦ WIP ¦ Done ¦ Enamul Haque ¦ 49 4 ¦ 120/0 ¦ 121/0 ¦ 120/1,120/2,120/3,120/4,120/5,120/6,120/7 ¦ 2861.678 ¦ TSE ¦ Complete ¦ Done ¦ 2026-05-03 00:00:00 ¦ 2026-05-08 00:00:00 ¦ Completed ¦ 2026-05-10 00:00:00 ¦ 2026-05-15 00:00:00 ¦ Enamul Haque ¦ 49 5 ¦ 121/0 ¦ 121/1 ¦ 276.141 ¦ Hotline ¦ Ready ¦ Enamul Haque ¦ 49 6 ¦ 121/1 ¦ 121/7 ¦ 121/2,121/3,121/4,121/5,121/6 ¦ 2284 ¦ TSE ¦ Ready ¦ Done | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Sheet6 | 47 | 5 |  | R2: Sr No. ¦ Location ¦ TOT ¦ Start ¦ End | Sr No. ¦ Location ¦ TOT ¦ Start ¦ End 1 ¦ 117/1 ¦ DA-3 ¦ 2026-01-15 00:00:00 ¦ 2026-01-21 00:00:00 2 ¦ 119/1 ¦ DA-3 ¦ 2026-01-09 00:00:00 ¦ 2026-01-15 00:00:00 3 ¦ 120/0 ¦ DD60+3 ¦ 2026-01-21 00:00:00 ¦ 2026-01-31 00:00:00 4 ¦ 120/4 ¦ DA+0 ¦ 2025-12-28 00:00:00 ¦ 2026-01-02 00:00:00 5 ¦ 120/7 ¦ DA+3 ¦ 2025-12-28 00:00:00 ¦ 2026-01-09 00:00:00 6 ¦ 121/2 ¦ DA+9 ¦ 2025-12-30 00:00:00 ¦ 2026-01-19 00:00:00 7 ¦ 121/3 ¦ DA+0 ¦ 2026-01-19 00:00:00 ¦ 2026-01-30 00:00:00 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Sheet4 | 940 | 353 |  |  | 117/1 ¦ 117/2 ¦ 118/0 ¦ 119/0 ¦ 119/1 ¦ 119/2 ¦ 119/3 ¦ 120/0 ¦ 120/1 ¦ 120/2 ¦ 120/3 ¦ 120/4 ¦ 120/5 ¦ 120/6 ¦ 120/7 ¦ 121/0 ¦ 121/1 ¦ 121/2 ¦ 121/3 ¦ 121/4 DA-3 ¦ DA+6 ¦ DB2+0 ¦ DD60+0 ¦ DA-3 ¦ DA-3 ¦ DA+9 ¦ DD60+3 ¦ DA-3 ¦ DA+0 ¦ DA+6 ¦ DA+0 ¦ DA-3 ¦ DA+0 ¦ DA+3 ¦ DB2+9 ¦ DB1+25 ¦ DA+9 ¦ DA+0 ¦ DA+0 Loc No ¦ Tower Type 118/0 117/1 ¦ DA-3 ¦ 117/1 117/2 ¦ DA+6 ¦ 117/2 118/0 ¦ DB2+0 ¦ 118/0 119/0 ¦ DD60+0 ¦ 119/0 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Sheet7 | 380 | 2 |  |  | kfvnk 117/1 117/2 118/0 119/0 119/1 119/2 119/3 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Visual chart | 438 | 38 | earthing_tack, erection, foundation, opgw_accessories, statutory_crossing, stringing, summary_status, survey_soil, visual_l2 | R2: Name of the Line : ¦ 765 kV D/C Vataman - Navsari Transmission Line ¦ Completed R3: Name of Project: ¦ Powergrid Vataman Transmission Limited ¦ DS (Aprd) ¦ CS (Aprd) ¦ SOIL INVSTGN ¦ FOUNDATION ¦ TOWER ERECTION ¦ TW ¦ TIG & PUN ¦ STR P/O ¦ STR F/S ¦ OPGW STR R8: Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ Sl. No. ¦ Type of Crossing ¦ No. of X-ing ¦ Approved ¦ Balance R10: 1 ¦ Detailed Survey ¦ Kms ¦ 127.799 ¦ 127.799 ¦ 1 ¦ Powerline X-ing ¦ 48 ¦ 46 ¦ 2 R11: 2 ¦ Check Survey ¦ Kms ¦ 127.799 ¦ 127.799 ¦ True ¦ 66 kV ¦ 18 ¦ 18 | Visual Chart ¦ 2026-05-20 00:00:00 Name of the Line : ¦ 765 kV D/C Vataman - Navsari Transmission Line ¦ Completed Name of Project: ¦ Powergrid Vataman Transmission Limited ¦ DS (Aprd) ¦ CS (Aprd) ¦ SOIL INVSTGN ¦ FOUNDATION ¦ TOWER ERECTION ¦ TW ¦ TIG & PUN ¦ STR P/O ¦ STR F/S ¦ OPGW STR Name of Contractor: ¦ KEC International Limited TOTAL ¦ COMP. ¦ BAL. ¦ EAR ¦ TOTAL ¦ COMP. ¦ BAL. PROGRESS AT A GLANCE : ¦ CROSSING PROPOSAL STATUS : Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ Sl. No. ¦ Type of Crossing ¦ No. of X-ing ¦ Approved ¦ Balance 1 ¦ Detailed Survey ¦ Kms ¦ 127.799 ¦ 127.799 ¦ 1 ¦ Powerline X-ing ¦ 48 ¦ 46 ¦ 2 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Pile Fdn | 49 | 9 | foundation, visual_l2 | R1: 129/0 Total Pile Completed: 16/16 ¦ Pile Cap: 4/4 ¦ VISUAL CHART VNTL PILE LOC- 129/0 R2: Leg ¦ PILE NO ¦ PILE COM. DATE ¦ PILE CAP ¦ CH 1ST ¦ CH 2ND ¦ REMARKS ¦ LEG - C ¦ LEG - B R27: 130/0 Total Pile Completed: 16/16 ¦ Pile Cap: 1/4 ¦ VISUAL CHART VNTL PILE LOC- 130/0 R28: Leg ¦ PILE NO ¦ PILE COM. DATE ¦ PILE CAP ¦ CH 1ST ¦ CH 2ND ¦ REMARKS ¦ LEG - C ¦ LEG - B | 129/0 Total Pile Completed: 16/16 ¦ Pile Cap: 4/4 ¦ VISUAL CHART VNTL PILE LOC- 129/0 Leg ¦ PILE NO ¦ PILE COM. DATE ¦ PILE CAP ¦ CH 1ST ¦ CH 2ND ¦ REMARKS ¦ LEG - C ¦ LEG - B C ¦ 1 ¦ 2026-03-23 00:00:00 ¦ Completed on 02.05.26 ¦ Completed on 11.05.26 ¦ Completed on 11.05.26 ¦ Pile Complete 2 ¦ 2026-03-28 00:00:00 ¦ Pile Complete 3 ¦ 2026-03-26 00:00:00 ¦ Pile Complete 4 ¦ 2026-03-11 00:00:00 ¦ Pile Complete B ¦ 5 ¦ 2026-02-24 00:00:00 ¦ Completed on 20.04.26 ¦ Completed on 27.04.26 ¦ Completed on 07.05.26 ¦ Pile Complete 6 ¦ 2026-03-01 00:00:00 ¦ Pile Complete | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Crossing | 72 | 17 | statutory_crossing, summary_status | R2: Sl No ¦ AP NO ¦ Towe Type ¦ AP No ¦ Tower Type ¦ Type of Crossings ¦ Span Length ¦ LINE OWNER ¦ Line Name ¦ Nos. ¦ Work Portion ¦ Status ¦ Submitted to Client for Review ¦ Proposal Submitted (Y/N) ¦ Inspection Status (Y/N) ¦ Remarks R3: 1 ¦ 118/0 ¦ DB2+0 ¦ 119/0 ¦ DD60+0 ¦ Power Line ¦ 243.824 ¦ GETCO ¦ 66 KV S/C NANDEWAR-WAGRA LINE (H FRAME) ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2024-07-10 00:00:00 ¦ Y ¦ Y ¦ Approved R4: 2 ¦ 119/3 ¦ DA+9 ¦ 120/0 ¦ DD60+3 ¦ Power Line ¦ 358.181 ¦ GETCO ¦ 66 KV D/C BHARUCH B TO VAGRA TAP VILAGAT LINE ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2024-07-15 00:00:00 ¦ Y ¦ Y ¦ Approved R5: 3 ¦ 121/0 ¦ DB2+9 ¦ 121/1 ¦ DB1+25 ¦ Power Line ¦ 276.141 ¦ GETCO ¦ 220 kv D/C VAGRA- THAM TSS LINE (U/C) ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2024-09-12 00:00:00 ¦ Y ¦ Y ¦ Approved R6: 4 ¦ 121/11 ¦ DA+9 ¦ 124/0 ¦ DD45+3 ¦ Power Line ¦ 396.394 ¦ GETCO ¦ 66 KV D/C Vilayat - Kukarwada Line ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2024-07-15 00:00:00 ¦ Y ¦ Y ¦ Approved | 765KV D/C HEXA VATAMAN - NAVSARI TL -04 - CROSSING STATUS Sl No ¦ AP NO ¦ Towe Type ¦ AP No ¦ Tower Type ¦ Type of Crossings ¦ Span Length ¦ LINE OWNER ¦ Line Name ¦ Nos. ¦ Work Portion ¦ Status ¦ Submitted to Client for Review ¦ Proposal Submitted (Y/N) ¦ Inspection Status (Y/N) ¦ Remarks 1 ¦ 118/0 ¦ DB2+0 ¦ 119/0 ¦ DD60+0 ¦ Power Line ¦ 243.824 ¦ GETCO ¦ 66 KV S/C NANDEWAR-WAGRA LINE (H FRAME) ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2024-07-10 00:00:00 ¦ Y ¦ Y ¦ Approved 2 ¦ 119/3 ¦ DA+9 ¦ 120/0 ¦ DD60+3 ¦ Power Line ¦ 358.181 ¦ GETCO ¦ 66 KV D/C BHARUCH B TO VAGRA TAP VILAGAT LINE ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2024-07-15 00:00:00 ¦ Y ¦ Y ¦ Approved 3 ¦ 121/0 ¦ DB2+9 ¦ 121/1 ¦ DB1+25 ¦ Power Line ¦ 276.141 ¦ GETCO ¦ 220 kv D/C VAGRA- THAM TSS LINE (U/C) ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2024-09-12 00:00:00 ¦ Y ¦ Y ¦ Approved 4 ¦ 121/11 ¦ DA+9 ¦ 124/0 ¦ DD45+3 ¦ Power Line ¦ 396.394 ¦ GETCO ¦ 66 KV D/C Vilayat - Kukarwada Line ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2024-07-15 00:00:00 ¦ Y ¦ Y ¦ Approved 5 ¦ 136/1 ¦ DB1+9 ¦ 137/0 ¦ DB2+3 ¦ Power Line ¦ 455.963 ¦ GETCO ¦ 66 KV S/C Hansot Robban Line ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2024-09-12 00:00:00 ¦ Y ¦ Y ¦ Approved 6 ¦ 140/0 ¦ DD60+25 ¦ 141/0 ¦ DD60+25 ¦ Power Line ¦ 171.929 ¦ ESSAR ¦ 400 KV D/C HZR-GDR ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2024-11-23 00:00:00 ¦ Y ¦ Y ¦ Approved | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Sheet2 | 6 | 9 | stringing | R6: 1 ¦ Hotline Stringing ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 | Hotline Stringing total KM : 17.112 Km Sl NO ¦ Description ¦ Dec'25 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 ¦ June'25 1 ¦ Hotline Stringing ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Survey | 14 | 5 | summary_status, survey_soil | R4: Sl. No. ¦ Particulars ¦ UoM ¦ Qty. ¦ Remarks R6: 2 ¦ Detail Survey Submitted ¦ Kms. ¦ 127.816066 R8: 4 ¦ Detail Survey Approved ¦ Kms. ¦ 126.93706600000002 R10: 6 ¦ Check Survey Submitted ¦ Kms. ¦ 127.816066 R11: 7 ¦ Check Survey Approved ¦ Kms. ¦ 126.93706600000002 | Date ¦ 2026-05-20 00:00:00 TA414 ¦ VNTL PROJECT ¦ SURVEY STATUS ¦ Sl. No. ¦ Particulars ¦ UoM ¦ Qty. ¦ Remarks 1 ¦ Total Section Length ¦ Kms. ¦ 127.774066 2 ¦ Detail Survey Submitted ¦ Kms. ¦ 127.816066 3 ¦ Balance to Submit ¦ Kms. ¦ -0.04200000000000159 4 ¦ Detail Survey Approved ¦ Kms. ¦ 126.93706600000002 5 ¦ Balance to Approve ¦ Kms. ¦ 0.8789999999999907 | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Soil Inv. | 30 | 7 | summary_status, survey_soil | R2: Sl. No. ¦ Loc. No. ¦ TOT ¦ RC ¦ Status ¦ Classification ¦ Approval Letter Status R6: 4 ¦ 131/0 ¦ DD60+9 ¦ 7 ¦ Done ¦ Sandy Dry Soil ¦ Approved | VNTL PROJECT - SOIL INVESTIGATION LOCATIONS Sl. No. ¦ Loc. No. ¦ TOT ¦ RC ¦ Status ¦ Classification ¦ Approval Letter Status 1 ¦ 121/0 ¦ DB2+9 ¦ Done ¦ WBC ¦ Approved 2 ¦ 129/0 ¦ DD45+25 ¦ Done ¦ PILE ¦ Approved 3 ¦ 130/0 ¦ DD45+25 ¦ Done ¦ PILE ¦ Approved 4 ¦ 131/0 ¦ DD60+9 ¦ 7 ¦ Done ¦ Sandy Dry Soil ¦ Approved 5 ¦ 135/0 ¦ DD60+0 ¦ Done ¦ 2 Mtr WBC & 1.5 Mtr FS ¦ Approved 6 ¦ 140/0 ¦ DD60+25 ¦ Done ¦ WBC ¦ Approved | repaired_defined_names (ValueError)
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | 2026-05-21 | Survey Anx | 27 | 9 | survey_soil | R2: District ¦ Section ¦ Total ¦ Detail Survey ¦ Check Survey R3: Completed ¦ Submitted ¦ Approved ¦ Completed ¦ Submitted ¦ Approved | TL- 04 765 kV D/C Vataman-Navsari Transmission Line District ¦ Section ¦ Total ¦ Detail Survey ¦ Check Survey Completed ¦ Submitted ¦ Approved ¦ Completed ¦ Submitted ¦ Approved Bharuch ¦ AP117-AP127 ¦ 14.513 ¦ 14.513 ¦ 14.513 ¦ 14.513 ¦ 14.513 ¦ 14.513 ¦ 14.513 Bharuch ¦ AP127-AP128 ¦ 1.0489999999999995 ¦ 1.0489999999999995 ¦ 1.0489999999999995 ¦ 1.0489999999999995 ¦ 1.0489999999999995 ¦ 1.0489999999999995 ¦ 1.0489999999999995 Bharuch ¦ AP128-AP131 ¦ 1.775128 ¦ 1.775128 ¦ 1.775128 ¦ 1.775128 ¦ 1.775128 ¦ 1.775128 ¦ 1.775128 Bharuch ¦ AP131-AP132 ¦ 2.201618 ¦ 2.201618 ¦ 2.201618 ¦ 2.201618 ¦ 2.201618 ¦ 2.201618 ¦ 2.201618 Bharuch ¦ AP132-AP137 ¦ 4.5929 ¦ 4.5929 ¦ 4.5929 ¦ 4.5929 ¦ 4.5929 ¦ 4.5929 ¦ 4.5929 | repaired_defined_names (ValueError)
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | Project Details | 16 | 11 | project_details | R1: Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer/Manager ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Supervisor | Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer/Manager ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Supervisor TA 416 ¦ 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 ¦ PGCIL ¦ 2024-02-07 00:00:00 ¦ 2025-11-06 00:00:00 ¦ Sanjib Samantaray ¦ Mr Arun Felbin ¦ Mr Ashok Kumar ¦ Shikhar Pratap ¦ Parshuram Ashok adav Time Extension(3 month) recevied upto 6th Feb 2026 ¦ PTE-II Recevied upto 31st march26 ¦ Rahman Time extension recieved upto 31st May2026 ¦ Saidur Rupsen Somenath Aflaudin | ok
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | MASTER SHEET | 74 | 16 | project_details, summary_status, supply, survey_soil, visual_l2 | R2: Project Name ¦ 765KV D/C NEEMRANA II - BAREILLY TL (Part-3) ¦ NOA Start Date ¦ 07.02.2025 ¦ PCH ¦ Mr. Arun Felbin R9: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Received till Last Month ¦ Balance as per L2 ¦ L2 Plan for Current Month ¦ Plan for Current Month ¦ Progress for the Month ¦ Received till Current Month ¦ Gap between Suppy & Cumm.L2 ¦ Remarks R10: Stub ¦ No's ¦ 302 ¦ 302 ¦ 302 ¦ 302 R15: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Approved in current month ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Survey Progress For current Month ¦ Survey Completed till Current Month ¦ Remarks R16: Detailed Survey ¦ kms ¦ 115.134 ¦ 115.134 ¦ 115.134 ¦ 115.134 ¦ 115.134 | Project Code ¦ TA-416 ¦ Date ¦ 2026-05-14 00:00:00 ¦ SBU Head ¦ Mr. Rajinder Gupta Project Name ¦ 765KV D/C NEEMRANA II - BAREILLY TL (Part-3) ¦ NOA Start Date ¦ 07.02.2025 ¦ PCH ¦ Mr. Arun Felbin Client Name ¦ Power Grid Corporation of India Limited ¦ NOA End Date ¦ 06.11.2025 ¦ Regional Manager ¦ Mr. Rajiv Sharma End Date extension ¦ 2026-03-31 00:00:00 ¦ Planning ¦ Sanjib Samantaray ¦ Project Manger ¦ Mr Ashok kumar Supply Status Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Received till Last Month ¦ Balance as per L2 ¦ L2 Plan for Current Month ¦ Plan for Current Month ¦ Progress for the Month ¦ Received till Current Month ¦ Gap between Suppy & Cumm.L2 ¦ Remarks Stub ¦ No's ¦ 302 ¦ 302 ¦ 302 ¦ 302 Tower ¦ No's ¦ 302 ¦ 302 ¦ 302 ¦ 302 | ok
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | Erection Compiled | 304 | 47 | erection, project_details, summary_status | R1: SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Remark ¦ 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ 9 R2: 1 ¦ 2/8 ¦ DA+0 ¦ 2024-09-01 00:00:00 ¦ 43.77575600000001 ¦ COMPLETED ¦ 2024-09-16 00:00:00 ¦ Dewi Construction(Girendra) R3: 2 ¦ 2/4 ¦ DA+0 ¦ 2024-09-16 00:00:00 ¦ 43.77575600000001 ¦ COMPLETED ¦ 2024-09-29 00:00:00 ¦ Dewi Construction(Girendra) R4: 3 ¦ 39/10 ¦ DA+0 ¦ 2024-09-16 00:00:00 ¦ 43.77575600000001 ¦ COMPLETED ¦ 2024-10-01 00:00:00 ¦ Horil Mahto R5: 4 ¦ 20/8 ¦ DA+0 ¦ 2024-10-01 00:00:00 ¦ 43.77575600000001 ¦ COMPLETED ¦ 2024-10-07 00:00:00 ¦ Dewi Construction(Girendra) | SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Remark ¦ 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ 9 1 ¦ 2/8 ¦ DA+0 ¦ 2024-09-01 00:00:00 ¦ 43.77575600000001 ¦ COMPLETED ¦ 2024-09-16 00:00:00 ¦ Dewi Construction(Girendra) 2 ¦ 2/4 ¦ DA+0 ¦ 2024-09-16 00:00:00 ¦ 43.77575600000001 ¦ COMPLETED ¦ 2024-09-29 00:00:00 ¦ Dewi Construction(Girendra) 3 ¦ 39/10 ¦ DA+0 ¦ 2024-09-16 00:00:00 ¦ 43.77575600000001 ¦ COMPLETED ¦ 2024-10-01 00:00:00 ¦ Horil Mahto 4 ¦ 20/8 ¦ DA+0 ¦ 2024-10-01 00:00:00 ¦ 43.77575600000001 ¦ COMPLETED ¦ 2024-10-07 00:00:00 ¦ Dewi Construction(Girendra) 5 ¦ 39/8 ¦ DA+0 ¦ 2024-10-03 00:00:00 ¦ 43.77575600000001 ¦ COMPLETED ¦ 2024-10-15 00:00:00 ¦ Horil Mahto 6 ¦ 20/6 ¦ DA+0 ¦ 2024-10-08 00:00:00 ¦ 43.77575600000001 ¦ COMPLETED ¦ 2024-10-13 00:00:00 ¦ Dewi Construction(Girendra) 7 ¦ 20/9 ¦ DA+3 ¦ 2024-10-14 00:00:00 ¦ 46.049156 ¦ COMPLETED ¦ 2024-10-19 00:00:00 ¦ Dewi Construction(Girendra) | ok
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | Stringing compiled | 82 | 16369 | project_details, stretch_readiness, stringing, summary_status, supply | R3: S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos. ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name R4: 1 ¦ UP ¦ AP7/0 ¦ AP8/0 ¦ 7/0,1,2,3,4,5,6,7,8,9,10,11,8/0 ¦ 4818.75 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-05-03 00:00:00 ¦ 2025-05-12 00:00:00 ¦ 4818.75 ¦ 2025-05-15 00:00:00 ¦ 2025-05-18 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 4818.75 ¦ Completed ¦ ANARUL ISLAM R5: 2 ¦ UP ¦ AP6/0 ¦ AP7/0 ¦ 6/0,1,2,7/0 ¦ 1234.28 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-05-14 00:00:00 ¦ 2025-05-17 00:00:00 ¦ 1234.28 ¦ 2025-05-19 00:00:00 ¦ 2025-05-21 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 1234.28 ¦ Completed ¦ ANARUL ISLAM R6: 3 ¦ UP ¦ AP35/0 ¦ AP36/0 ¦ 35/0,1,2,3,4,5,6,7,8,9,36/0 ¦ 3957.05 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-05-18 00:00:00 ¦ 2025-05-25 00:00:00 ¦ 3957.05 ¦ 2025-06-27 00:00:00 ¦ 2025-06-30 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 3957.05 ¦ Completed ¦ S K INFRA R7: 4 ¦ UP ¦ AP8/0 ¦ AP8A/0 ¦ 8/0,1,2,3,4,8A/0 ¦ 2016.72 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-05-24 00:00:00 ¦ 2025-05-29 00:00:00 ¦ 2016.72 ¦ 2025-05-30 00:00:00 ¦ 2025-05-31 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 2016.72 ¦ Completed ¦ ANARUL ISLAM | Number of TSE ¦ 1 ¦ RATE/KM 905812 S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos. ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name 1 ¦ UP ¦ AP7/0 ¦ AP8/0 ¦ 7/0,1,2,3,4,5,6,7,8,9,10,11,8/0 ¦ 4818.75 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-05-03 00:00:00 ¦ 2025-05-12 00:00:00 ¦ 4818.75 ¦ 2025-05-15 00:00:00 ¦ 2025-05-18 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 4818.75 ¦ Completed ¦ ANARUL ISLAM 2 ¦ UP ¦ AP6/0 ¦ AP7/0 ¦ 6/0,1,2,7/0 ¦ 1234.28 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-05-14 00:00:00 ¦ 2025-05-17 00:00:00 ¦ 1234.28 ¦ 2025-05-19 00:00:00 ¦ 2025-05-21 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 1234.28 ¦ Completed ¦ ANARUL ISLAM 3 ¦ UP ¦ AP35/0 ¦ AP36/0 ¦ 35/0,1,2,3,4,5,6,7,8,9,36/0 ¦ 3957.05 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-05-18 00:00:00 ¦ 2025-05-25 00:00:00 ¦ 3957.05 ¦ 2025-06-27 00:00:00 ¦ 2025-06-30 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 3957.05 ¦ Completed ¦ S K INFRA 4 ¦ UP ¦ AP8/0 ¦ AP8A/0 ¦ 8/0,1,2,3,4,8A/0 ¦ 2016.72 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-05-24 00:00:00 ¦ 2025-05-29 00:00:00 ¦ 2016.72 ¦ 2025-05-30 00:00:00 ¦ 2025-05-31 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 2016.72 ¦ Completed ¦ ANARUL ISLAM 5 ¦ UP ¦ AP31/0 ¦ AP32/0 ¦ 31/0,1,2,3,4,5,6,7,8,9,10,32/0 ¦ 4283.67 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-06-02 00:00:00 ¦ 2025-06-09 00:00:00 ¦ 4283.67 ¦ 2025-06-22 00:00:00 ¦ 2025-06-26 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 4283.67 ¦ Completed ¦ S K INFRA | ok
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | Progress. | 726 | 16 | summary_status, supply, survey_soil, visual_l2 | R2: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Received till Last Month ¦ Balance as per L2 ¦ L2 Plan for Current Month ¦ Plan for Current Month ¦ Progress for the Month ¦ Received till Current Month ¦ Gap between Suppy & Cumm.L2 ¦ Remarks R3: Stub ¦ No's ¦ 302 ¦ 302 ¦ 302 ¦ 302 R8: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Approved in current month ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Survey Progress For current Month ¦ Survey Completed till Current Month ¦ Remarks R9: Detailed Survey ¦ kms ¦ 115.134 ¦ 115.134 ¦ 115.134 ¦ 115.134 ¦ 115.134 R10: Check Survey ¦ kms ¦ 115.134 ¦ 115.134 ¦ 115.134 ¦ 115.134 ¦ 115.134 | Supply Status Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Received till Last Month ¦ Balance as per L2 ¦ L2 Plan for Current Month ¦ Plan for Current Month ¦ Progress for the Month ¦ Received till Current Month ¦ Gap between Suppy & Cumm.L2 ¦ Remarks Stub ¦ No's ¦ 302 ¦ 302 ¦ 302 ¦ 302 Tower ¦ No's ¦ 302 ¦ 302 ¦ 302 ¦ 302 Survey Status Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Approved in current month ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Survey Progress For current Month ¦ Survey Completed till Current Month ¦ Remarks Detailed Survey ¦ kms ¦ 115.134 ¦ 115.134 ¦ 115.134 ¦ 115.134 ¦ 115.134 Check Survey ¦ kms ¦ 115.134 ¦ 115.134 ¦ 115.134 ¦ 115.134 ¦ 115.134 | ok
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | Visual chart. | 367 | 56 | earthing_tack, erection, foundation, opgw_accessories, row_hindrance, statutory_crossing, stringing, visual_l2 | R7: LEGEND: ¦ OPGW Stringing ¦ Description of Item ¦ Total Line Qty ¦ Total Completed ¦ WIP locations R10: Erection Comp ¦ Stringing WIP ¦ Foundation ¦ 302 ¦ 302 R11: TW ¦ Erection Comp ¦ Earthing ¦ 302 ¦ 302 R12: Foundation Comp ¦ C ¦ B ¦ SPAN ¦ C ¦ B ¦ Erection ¦ 302 ¦ 302 R13: D ¦ A ¦ D ¦ A ¦ Foundation Comp ¦ Tack Welding ¦ 302 ¦ 297 | Visual Chart :- 765kV D/C Neemrana II Bareilly Transmission Line, WZ-05, TL-03 Project Code : TA416 ¦ Dated: LEGEND: ¦ OPGW Stringing ¦ Description of Item ¦ Total Line Qty ¦ Total Completed ¦ WIP locations Stringing Comp ¦ Location No. Erection Comp ¦ Stringing WIP ¦ Foundation ¦ 302 ¦ 302 TW ¦ Erection Comp ¦ Earthing ¦ 302 ¦ 302 Foundation Comp ¦ C ¦ B ¦ SPAN ¦ C ¦ B ¦ Erection ¦ 302 ¦ 302 D ¦ A ¦ D ¦ A ¦ Foundation Comp ¦ Tack Welding ¦ 302 ¦ 297 | ok
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | PENDING FDN DETAILS | 17 | 8 | foundation, row_hindrance, summary_status | R2: Sl. No. ¦ Loc. No. ¦ Type of Tower ¦ Village ¦ Taluk ¦ FDN STATUS ¦ ROW STATUS ¦ REMARKS | 765kV D/C Neemrana II Bareilly Transmission Line, WZ-05, TL-03 ¦ BALANCE WORK DETAILS Sl. No. ¦ Loc. No. ¦ Type of Tower ¦ Village ¦ Taluk ¦ FDN STATUS ¦ ROW STATUS ¦ REMARKS 1 2 3 4 5 6 | ok
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | PENDING ERE DETAILS | 7 | 7 | foundation, row_hindrance, summary_status | R4: Sl. No. ¦ Loc. No. ¦ Type of Tower ¦ FDN STATUS ¦ ERE STATUS ¦ ROW STATUS ¦ REMARKS | Sl. No. ¦ Loc. No. ¦ Type of Tower ¦ FDN STATUS ¦ ERE STATUS ¦ ROW STATUS ¦ REMARKS | ok
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | TSE-MANUAL-LT-11KV-33KV Details | 44 | 15 |  |  | 765kV D/C Neemrana II Bareilly Transmission Line, WZ-05, TL-03 Sl. No ¦ SECTION ¦ Section Length ¦ No. Of Towers B/W Angle Towers ¦ TSE Section (In KM) ¦ Manual Section (In KM) ¦ LT ¦ 11KV ¦ 33KV FROM ¦ TO 1 2 3 4 5 | ok
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | Crossing Details | 53 | 12 | statutory_crossing, summary_status, supply | R7: Name of the Transmission ¦ Voltage Rating in kV ¦ Name of Owner ¦ Name of Nearest switching/ sub-station ¦ (Crossing in Proposed Line Loc.No) ¦ Proposal submission Date ¦ Status ¦ APPROVED Date ¦ Remark R27: Name of the Railway Line ¦ Type of Gauge Broad/Metre/Narrow ¦ Single/ Double Line ¦ Electrified / Non-electrified ¦ Crossing loc no of proposed line ¦ Date of Submission ¦ Status R32: Name of the Highway Line ¦ Type of NH ¦ Nearest town ¦ Nearest Village ¦ Crossing loc no of proposed line ¦ Date of Submission ¦ Status R33: NH-509 ¦ Gunnaur ¦ Kuravar ¦ AP1-AP-2 ¦ Submitted on 20.06.24, at Moradabad ¦ Approved ¦ 2025-04-04 00:00:00 R38: NH-530 ¦ AP44-AP45 ¦ Submitted on 23-08-24 ¦ Approved ¦ 2025-03-25 00:00:00 | KEC INTERNATIONAL LIMITED NOA Supply: CC/T/W-TW/DOM/A10/23/10706/NOA-1/24-101862/01 dated 07.02.24. NOA Services: CC/T/W-TW/DOM/A10/23/10706/NOA-2/24-101862/02 dated 07.02.24. Contract: TL03 for Neemrana-II- Bareilly (PG) 765kV D/C line - Part III associated with “Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-1) (Bikaner Complex : 7.7GW) PART-D” through tariff based competitive bidding (TBCB) route. STATUTORY CLEARANCE POWER LINE CROSSING ¦ 2025-09-30 00:00:00 Name of the Transmission ¦ Voltage Rating in kV ¦ Name of Owner ¦ Name of Nearest switching/ sub-station ¦ (Crossing in Proposed Line Loc.No) ¦ Proposal submission Date ¦ Status ¦ APPROVED Date ¦ Remark Moradabad To Narora ¦ 220kv S/C & 132kv Dismental ¦ UPPTCL ¦ Loc.:-AP3 - AP4 ¦ 2024-04-29 00:00:00 ¦ Approved ¦ 2024-07-19 00:00:00 | ok
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | TS | 264 | 27 |  |  | Name of the Line :765kV D/C KOPPAL II(PS) - RAICHUR (Part-1) TRANSMISSION LINE Sl.No ¦ Loc. No. (Provisional) ¦ Type of Tower ¦ Span (Mtr) 1 ¦ AP32 ¦ 1DC2+6 ¦ 249.635 ¦ 32/0-33/0 -0 ¦ -1.5 ¦ -3 ¦ -4.5 ¦ -6 ¦ +0 ¦ +1.5 ¦ +3 ¦ +4.5 ¦ +6 ¦ +9 ¦ +18 ¦ Total 2 ¦ AP33 ¦ 1DD45+18 ¦ 425 ¦ 1DA ¦ 10 ¦ 7 ¦ 3 ¦ 1 ¦ 26 ¦ 2 ¦ 21 ¦ 2 ¦ 8 ¦ 6 ¦ 86 1DB1 ¦ 6 ¦ 2 ¦ 1 ¦ 5 ¦ 14 ¦ 113 ¦ AP57 ¦ 1DC2+6 ¦ 57/0 ¦ 1DC1+3 ¦ 73.125 3 ¦ 33/1 ¦ 1DA-3 ¦ 425 ¦ 1DB2 ¦ 1 ¦ 2 ¦ 2 ¦ 2 ¦ 7 1DC1 ¦ 3 ¦ 1 ¦ 1 ¦ 1 ¦ 6 ¦ 114 ¦ 57/1 ¦ 1DA+0 ¦ 57/1 ¦ 1DA+0 ¦ 71.43 | ok
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | 2026-05-17 | TS (2) | 264 | 27 |  |  | Name of the Line :765kV D/C KOPPAL II(PS) - RAICHUR (Part-1) TRANSMISSION LINE Sl.No ¦ Loc. No. (Provisional) ¦ Type of Tower ¦ Span (Mtr) 1 ¦ AP32 ¦ 1DC2+6 ¦ 249.635 ¦ 32/0-33/0 -0 ¦ -1.5 ¦ -3 ¦ -4.5 ¦ -6 ¦ +0 ¦ +1.5 ¦ +3 ¦ +4.5 ¦ +6 ¦ +9 ¦ +18 ¦ Total 2 ¦ AP33 ¦ 1DD45+18 ¦ 425 ¦ 1DA ¦ 3 ¦ 18 ¦ 34 ¦ 19 ¦ 7 ¦ 6 ¦ 87 ¦ 2 1DB1 ¦ 1 ¦ 7 ¦ 1 ¦ 1 ¦ 4 ¦ 14 ¦ 113 ¦ AP57 ¦ 1DC2+6 ¦ 57/0 ¦ 1DC1+3 ¦ 73.125 3 ¦ 33/1 ¦ 1DA-3 ¦ 425 ¦ 1DB2 ¦ 1 ¦ 2 ¦ 1 ¦ 4 1DC1 ¦ 1 ¦ 2 ¦ 2 ¦ 2 ¦ 7 ¦ 114 ¦ 57/1 ¦ 1DA+0 ¦ 57/1 ¦ 1DA+0 ¦ 71.43 | ok
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | MASTER SHEET | 80 | 95 | project_details, summary_status, supply, survey_soil, visual_l2 | R2: Project Name ¦ 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1) ¦ NOA Start Date ¦ 12.03.2024 ¦ PCH ¦ Mr. Arun Felbin R8: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Received till Last Month ¦ Balance as per L2 ¦ L2 Plan for Current Month ¦ Plan for Current Month ¦ Progress for the Month ¦ Received till Current Month ¦ Gap between Supply & Cumm.L2 ¦ Remarks R9: Stub ¦ No's ¦ 127 ¦ 127 ¦ 127 ¦ 127 R14: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Approved in current month ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Survey Progress For current Month ¦ Survey Completed till Current Month ¦ Remarks R15: Detailed Survey ¦ kms ¦ 47.84 ¦ 47.84 ¦ 47.84 ¦ 47.839999999999996 ¦ 47.84 | Project Code ¦ TA-418 ¦ Date ¦ 2026-05-20 00:00:00 ¦ SBU Head ¦ Mr. Rajinder Gupta Project Name ¦ 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1) ¦ NOA Start Date ¦ 12.03.2024 ¦ PCH ¦ Mr. Arun Felbin Client Name ¦ Power Grid Corporation of India Limited ¦ NOA End Date ¦ 11.12.2025 ¦ Regional Manager ¦ Mr. Ajith Kumar MG End Date ¦ 2026-06-30 00:00:00 ¦ Planning Engineer ¦ Mr.Ajith Jayasurya ¦ Project Manger ¦ Mr. Tamil Velan Supply Status Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Received till Last Month ¦ Balance as per L2 ¦ L2 Plan for Current Month ¦ Plan for Current Month ¦ Progress for the Month ¦ Received till Current Month ¦ Gap between Supply & Cumm.L2 ¦ Remarks Stub ¦ No's ¦ 127 ¦ 127 ¦ 127 ¦ 127 Tower ¦ No's ¦ 127 ¦ 127 ¦ 127 ¦ 127 | ok
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | Progress | 302 | 16 | foundation, summary_status, supply, survey_soil, visual_l2 | R2: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Received till Last Month ¦ Balance as per L2 ¦ L2 Plan for Current Month ¦ Plan for Current Month ¦ Progress for the Month ¦ Received till Current Month ¦ Gap between Suppy & Cumm.L2 ¦ Remarks R3: Stub ¦ No's ¦ 127 ¦ 127 ¦ 127 ¦ 127 R8: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Approved in current month ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Survey Progress For current Month ¦ Survey Completed till Current Month ¦ Remarks R9: Detailed Survey ¦ kms ¦ 47.84 ¦ 47.84 ¦ 47.84 ¦ 47.839999999999996 ¦ 47.84 R10: Check Survey ¦ kms ¦ 47.84 ¦ 47.84 ¦ 47.84 ¦ 47.839999999999996 ¦ 47.84 | Supply Status Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Received till Last Month ¦ Balance as per L2 ¦ L2 Plan for Current Month ¦ Plan for Current Month ¦ Progress for the Month ¦ Received till Current Month ¦ Gap between Suppy & Cumm.L2 ¦ Remarks Stub ¦ No's ¦ 127 ¦ 127 ¦ 127 ¦ 127 Tower ¦ No's ¦ 127 ¦ 127 ¦ 122 ¦ 5 ¦ 5 ¦ 127 Survey Status Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Approved in current month ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Survey Progress For current Month ¦ Survey Completed till Current Month ¦ Remarks Detailed Survey ¦ kms ¦ 47.84 ¦ 47.84 ¦ 47.84 ¦ 47.839999999999996 ¦ 47.84 Check Survey ¦ kms ¦ 47.84 ¦ 47.84 ¦ 47.84 ¦ 47.839999999999996 ¦ 47.84 | ok
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | Erection Compiled | 129 | 18 | erection, project_details, summary_status | R2: SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Tower Tightening ¦ Remark R3: 1 ¦ 34/1 ¦ DA+0 ¦ DFR ¦ 2024-10-09 00:00:00 ¦ 27.96 ¦ COMPLETED ¦ 2024-10-27 00:00:00 ¦ Gang-01 (Sanjay) ¦ COMPLETED R4: 2 ¦ 33/12 ¦ DA+0 ¦ DFR ¦ 2024-10-28 00:00:00 ¦ 27.96 ¦ COMPLETED ¦ 2024-11-05 00:00:00 ¦ Gang-01 (Sanjay) ¦ COMPLETED R5: 3 ¦ 35/06 ¦ DA+0 ¦ DFR ¦ 2024-11-05 00:00:00 ¦ 27.96 ¦ COMPLETED ¦ 2024-11-13 00:00:00 ¦ Gang-01 (Sanjay) ¦ COMPLETED R6: 4 ¦ 34/3 ¦ DA+0 ¦ DFR ¦ 2024-11-14 00:00:00 ¦ 27.96 ¦ COMPLETED ¦ 2024-11-19 00:00:00 ¦ Gang-01 (Sanjay) ¦ COMPLETED ¦ 11KV | Erection SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Tower Tightening ¦ Remark 1 ¦ 34/1 ¦ DA+0 ¦ DFR ¦ 2024-10-09 00:00:00 ¦ 27.96 ¦ COMPLETED ¦ 2024-10-27 00:00:00 ¦ Gang-01 (Sanjay) ¦ COMPLETED 2 ¦ 33/12 ¦ DA+0 ¦ DFR ¦ 2024-10-28 00:00:00 ¦ 27.96 ¦ COMPLETED ¦ 2024-11-05 00:00:00 ¦ Gang-01 (Sanjay) ¦ COMPLETED 3 ¦ 35/06 ¦ DA+0 ¦ DFR ¦ 2024-11-05 00:00:00 ¦ 27.96 ¦ COMPLETED ¦ 2024-11-13 00:00:00 ¦ Gang-01 (Sanjay) ¦ COMPLETED 4 ¦ 34/3 ¦ DA+0 ¦ DFR ¦ 2024-11-14 00:00:00 ¦ 27.96 ¦ COMPLETED ¦ 2024-11-19 00:00:00 ¦ Gang-01 (Sanjay) ¦ COMPLETED ¦ 11KV 5 ¦ 35/4 ¦ DA+0 ¦ DFR ¦ 2024-11-19 00:00:00 ¦ 27.96 ¦ COMPLETED ¦ 2024-11-24 00:00:00 ¦ Gang-01 (Sanjay) ¦ COMPLETED ¦ LT 6 ¦ 40/1 ¦ DA+0 ¦ DFR ¦ 2024-11-26 00:00:00 ¦ 27.96 ¦ COMPLETED ¦ 2024-12-01 00:00:00 ¦ Gang-01 (Sanjay) ¦ COMPLETED | ok
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | Stringing Compiled | 46 | 25 | earthing_tack, project_details, stretch_readiness, stringing, summary_status, supply | R3: S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos. ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Tackwelding Status ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status R4: 1 ¦ KA ¦ AP32 ¦ AP33 ¦ 32/0, 33/0 ¦ 249.635 ¦ HotLine ¦ Ready ¦ Completed ¦ 2026-02-14 00:00:00 ¦ 2026-02-16 00:00:00 ¦ 2026-02-22 00:00:00 ¦ 2026-02-16 00:00:00 ¦ 2026-02-22 00:00:00 ¦ 2026-02-24 00:00:00 ¦ 2026-02-23 00:00:00 ¦ 2026-02-23 00:00:00 ¦ 249.635 ¦ Completed ¦ Ramawat R5: 2 ¦ KA ¦ AP33 ¦ 33/5 ¦ 33/0, 33/1, 33/2, 33/3, 33/4, 33/5 ¦ 2015 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-12-20 00:00:00 ¦ 2026-02-05 00:00:00 ¦ 2026-02-09 00:00:00 ¦ 2026-02-07 00:00:00 ¦ 2026-02-09 00:00:00 ¦ 2026-02-12 00:00:00 ¦ 2026-02-13 00:00:00 ¦ 2026-02-11 00:00:00 ¦ 2015 ¦ Completed ¦ SUFIYAN / Haque R6: 3 ¦ KA ¦ 33/5 ¦ 33/6 ¦ 33/5, 33/6 ¦ 380 ¦ HotLine ¦ Ready ¦ Completed ¦ 2025-12-21 00:00:00 ¦ 2026-01-19 00:00:00 ¦ 2026-01-30 00:00:00 ¦ 2026-01-26 00:00:00 ¦ 2026-01-30 00:00:00 ¦ 2026-01-31 00:00:00 ¦ 2026-01-31 00:00:00 ¦ 2026-01-30 00:00:00 ¦ 380 ¦ Completed ¦ Ramawat R7: 4 ¦ KA ¦ 33/6 ¦ 34/0 ¦ 33/6, 33/7, 33/8, 33/9, 33/10, 33/11, 33/12, 34/0 ¦ 2537.42 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-12-21 00:00:00 ¦ 2026-01-18 00:00:00 ¦ 2026-01-27 00:00:00 ¦ 2026-01-26 00:00:00 ¦ 2026-01-28 00:00:00 ¦ 2026-02-01 00:00:00 ¦ 2026-02-02 00:00:00 ¦ 2026-02-01 00:00:00 ¦ 2537.42 ¦ Completed ¦ SUFIYAN / Haque | Number of TSE ¦ 1 S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos. ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Tackwelding Status ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status 1 ¦ KA ¦ AP32 ¦ AP33 ¦ 32/0, 33/0 ¦ 249.635 ¦ HotLine ¦ Ready ¦ Completed ¦ 2026-02-14 00:00:00 ¦ 2026-02-16 00:00:00 ¦ 2026-02-22 00:00:00 ¦ 2026-02-16 00:00:00 ¦ 2026-02-22 00:00:00 ¦ 2026-02-24 00:00:00 ¦ 2026-02-23 00:00:00 ¦ 2026-02-23 00:00:00 ¦ 249.635 ¦ Completed ¦ Ramawat 2 ¦ KA ¦ AP33 ¦ 33/5 ¦ 33/0, 33/1, 33/2, 33/3, 33/4, 33/5 ¦ 2015 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-12-20 00:00:00 ¦ 2026-02-05 00:00:00 ¦ 2026-02-09 00:00:00 ¦ 2026-02-07 00:00:00 ¦ 2026-02-09 00:00:00 ¦ 2026-02-12 00:00:00 ¦ 2026-02-13 00:00:00 ¦ 2026-02-11 00:00:00 ¦ 2015 ¦ Completed ¦ SUFIYAN / Haque 3 ¦ KA ¦ 33/5 ¦ 33/6 ¦ 33/5, 33/6 ¦ 380 ¦ HotLine ¦ Ready ¦ Completed ¦ 2025-12-21 00:00:00 ¦ 2026-01-19 00:00:00 ¦ 2026-01-30 00:00:00 ¦ 2026-01-26 00:00:00 ¦ 2026-01-30 00:00:00 ¦ 2026-01-31 00:00:00 ¦ 2026-01-31 00:00:00 ¦ 2026-01-30 00:00:00 ¦ 380 ¦ Completed ¦ Ramawat 4 ¦ KA ¦ 33/6 ¦ 34/0 ¦ 33/6, 33/7, 33/8, 33/9, 33/10, 33/11, 33/12, 34/0 ¦ 2537.42 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-12-21 00:00:00 ¦ 2026-01-18 00:00:00 ¦ 2026-01-27 00:00:00 ¦ 2026-01-26 00:00:00 ¦ 2026-01-28 00:00:00 ¦ 2026-02-01 00:00:00 ¦ 2026-02-02 00:00:00 ¦ 2026-02-01 00:00:00 ¦ 2537.42 ¦ Completed ¦ SUFIYAN / Haque 5 ¦ KA ¦ 34/0 ¦ AP35 ¦ 34/0, 34/1, 34/2, 34/3, 34/4, 35/0 ¦ 1983.46 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-10-29 00:00:00 ¦ 2025-11-26 00:00:00 ¦ 2025-11-30 00:00:00 ¦ 2025-12-05 00:00:00 ¦ 2025-12-09 00:00:00 ¦ 2025-12-11 00:00:00 ¦ 2025-12-13 00:00:00 ¦ 2025-12-12 00:00:00 ¦ 1983.46 ¦ Completed ¦ SUFIYAN 6 ¦ KA ¦ AP35 ¦ AP36 ¦ 35/0, 35/1, 35/2,35/3,35/4, 35/5, 35/6,35/7,35/8, 35/9, 35/10,35/11,36/0 ¦ 4480.02 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-10-24 00:00:00 ¦ 2025-11-07 00:00:00 ¦ 2025-11-17 00:00:00 ¦ 2025-12-05 00:00:00 ¦ 2025-12-09 00:00:00 ¦ 2025-12-13 00:00:00 ¦ 2025-12-19 00:00:00 ¦ 2025-12-18 00:00:00 ¦ 4480.02 ¦ Completed ¦ SUFIYAN | ok
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | Visual Chart | 180 | 37 | earthing_tack, erection, foundation, stringing, summary_status, survey_soil, visual_l2 | R5: Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed ¦ Balance R6: 1 ¦ Detailed Survey ¦ Kms ¦ 47.84 ¦ 47.84 R7: 2 ¦ Check Survey ¦ Kms ¦ 47.84 ¦ 47.84 R8: 3 ¦ Foundation ¦ Nos ¦ 127 ¦ 127 ¦ DATE: ¦ 2026-05-20 00:00:00 R9: 4 ¦ Earthing ¦ Nos ¦ 127 ¦ 127 | VISUAL CHART - 765kV D/C KOPPAL II(PS) - RAICHUR TRANSMISSION LINE Name of Contractor : M/s KEC International Ltd Progress at a Glance : Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed ¦ Balance 1 ¦ Detailed Survey ¦ Kms ¦ 47.84 ¦ 47.84 2 ¦ Check Survey ¦ Kms ¦ 47.84 ¦ 47.84 3 ¦ Foundation ¦ Nos ¦ 127 ¦ 127 ¦ DATE: ¦ 2026-05-20 00:00:00 4 ¦ Earthing ¦ Nos ¦ 127 ¦ 127 | ok
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | ROW TRACKER | 96 | 34 | erection, row_hindrance, stringing | R5: Sl.No ¦ GANG NAME ¦ ACTIVITY ¦ 2026-05-01 00:00:00 ¦ 2026-05-02 00:00:00 ¦ 2026-05-03 00:00:00 ¦ 2026-05-04 00:00:00 ¦ 2026-05-05 00:00:00 ¦ 2026-05-06 00:00:00 ¦ 2026-05-07 00:00:00 ¦ 2026-05-08 00:00:00 ¦ 2026-05-09 00:00:00 ¦ 2026-05-10 00:00:00 ¦ 2026-05-11 00:00:00 ¦ 2026-05-12 00:00:00 ¦ 2026-05-13 00:00:00 ¦ 2026-05-14 00:00:00 ¦ 2026-05-15 00:00:00 ¦ 2026-05-16 00:00:00 ¦ 2026-05-17 00:00: R6: 1 ¦ M/s SUFIYAN ¦ STRINGING ¦ 55/0 - 56/0 PO ¦ 55/0 - 56/0 PO ¦ 55/0 - 56/0 PO ¦ 55/0 - 56/0 FS ¦ 55/0 - 56/0 CLP ¦ 55/0 - 56/0 CLP ¦ 55/0 - 56/0 CLP ¦ 55/0 - 56/0 SPR ¦ 55/0 - 56/0 SPR ¦ 37/0-38/0 PO ¦ 37/0-38/0 PO ¦ 37/0-38/0 PO ¦ 38/0-39/0 CBL BYP ¦ 38/0-39/0 IH ¦ 38/0-39/0 IH ¦ IDLE ¦ IDLE R7: 2 ¦ HotLine Gang ¦ STRINGING ¦ Mobilized ¦ IDLE R12: Sl.No ¦ GANG NAME ¦ ACTIVITY ¦ 2026-04-01 00:00:00 ¦ 2026-04-02 00:00:00 ¦ 2026-04-03 00:00:00 ¦ 2026-04-04 00:00:00 ¦ 2026-04-05 00:00:00 ¦ 2026-04-06 00:00:00 ¦ 2026-04-07 00:00:00 ¦ 2026-04-08 00:00:00 ¦ 2026-04-09 00:00:00 ¦ 2026-04-10 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-12 00:00:00 ¦ 2026-04-13 00:00:00 ¦ 2026-04-14 00:00:00 ¦ 2026-04-15 00:00:00 ¦ 2026-04-16 00:00:00 ¦ 2026-04-17 00:00: R13: 1 ¦ M/s MDPL ¦ ERECTION ¦ 38/0 ¦ 46/1 ¦ 46/1 ¦ 46/1 ¦ 46/1 ¦ 46/1 ¦ 46/1 ¦ 46/1 ¦ 46/1 ¦ ERECTION COMPLETED | 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1) ROW TRACKER -May' 2026 Sl.No ¦ GANG NAME ¦ ACTIVITY ¦ 2026-05-01 00:00:00 ¦ 2026-05-02 00:00:00 ¦ 2026-05-03 00:00:00 ¦ 2026-05-04 00:00:00 ¦ 2026-05-05 00:00:00 ¦ 2026-05-06 00:00:00 ¦ 2026-05-07 00:00:00 ¦ 2026-05-08 00:00:00 ¦ 2026-05-09 00:00:00 ¦ 2026-05-10 00:00:00 ¦ 2026-05-11 00:00:00 ¦ 2026-05-12 00:00:00 ¦ 2026-05-13 00:00:00 ¦ 2026-05-14 00:00:00 ¦ 2026-05-15 00:00:00 ¦ 2026-05-16 00:00:00 ¦ 2026-05-17 00:00:00 1 ¦ M/s SUFIYAN ¦ STRINGING ¦ 55/0 - 56/0 PO ¦ 55/0 - 56/0 PO ¦ 55/0 - 56/0 PO ¦ 55/0 - 56/0 FS ¦ 55/0 - 56/0 CLP ¦ 55/0 - 56/0 CLP ¦ 55/0 - 56/0 CLP ¦ 55/0 - 56/0 SPR ¦ 55/0 - 56/0 SPR ¦ 37/0-38/0 PO ¦ 37/0-38/0 PO ¦ 37/0-38/0 PO ¦ 38/0-39/0 CBL BYP ¦ 38/0-39/0 IH ¦ 38/0-39/0 IH ¦ IDLE ¦ IDLE 2 ¦ HotLine Gang ¦ STRINGING ¦ Mobilized ¦ IDLE 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1) ROW TRACKER -April' 2026 Sl.No ¦ GANG NAME ¦ ACTIVITY ¦ 2026-04-01 00:00:00 ¦ 2026-04-02 00:00:00 ¦ 2026-04-03 00:00:00 ¦ 2026-04-04 00:00:00 ¦ 2026-04-05 00:00:00 ¦ 2026-04-06 00:00:00 ¦ 2026-04-07 00:00:00 ¦ 2026-04-08 00:00:00 ¦ 2026-04-09 00:00:00 ¦ 2026-04-10 00:00:00 ¦ 2026-04-11 00:00:00 ¦ 2026-04-12 00:00:00 ¦ 2026-04-13 00:00:00 ¦ 2026-04-14 00:00:00 ¦ 2026-04-15 00:00:00 ¦ 2026-04-16 00:00:00 ¦ 2026-04-17 00:00:00 | ok
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | PENDING FDN DETAILS | 4 | 8 | foundation, row_hindrance, summary_status | R2: Sl. No. ¦ Loc. No. ¦ Type of Tower ¦ Village ¦ Taluk ¦ FDN STATUS ¦ ROW STATUS ¦ REMARKS | 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1) ¦ BALANCE WORK DETAILS Sl. No. ¦ Loc. No. ¦ Type of Tower ¦ Village ¦ Taluk ¦ FDN STATUS ¦ ROW STATUS ¦ REMARKS | ok
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | TSE-MANUAL-LT-11KV-33KV Details | 44 | 18 | erection, foundation, stretch_readiness | R3: Sl. No ¦ SECTION ¦ Section Length ¦ Foundation Balance ¦ Erection Balance ¦ Stretch Readiness ¦ No. Of Towers B/W Angle Towers ¦ TSE Section (In KM) ¦ Manual Section (In KM) ¦ LT ¦ 11KV ¦ 33KV | 765kV D/C KOPPAL II(PS) - RAICHUR TRANSMISSION LINE Sl. No ¦ SECTION ¦ Section Length ¦ Foundation Balance ¦ Erection Balance ¦ Stretch Readiness ¦ No. Of Towers B/W Angle Towers ¦ TSE Section (In KM) ¦ Manual Section (In KM) ¦ LT ¦ 11KV ¦ 33KV FROM ¦ TO 1 ¦ AP32 ¦ AP33 ¦ 249.635 ¦ - ¦ - ¦ Ready ¦ 249.635 ¦ 1 ¦ 1 2 ¦ AP33 ¦ 33/5 ¦ 2015 ¦ - ¦ - ¦ Ready ¦ 4 ¦ 2015 ¦ 1 ¦ 1 ¦ 1 3 ¦ 33/5 ¦ 33/6 ¦ 380 ¦ - ¦ - ¦ Ready ¦ 380 4 ¦ 33/6 ¦ 34/0 ¦ 2537.42 ¦ - ¦ - ¦ Ready ¦ 6 ¦ 2537.42 ¦ 2 ¦ 6 ¦ 2 5 ¦ 34/0 ¦ AP35 ¦ 1983.46 ¦ - ¦ - ¦ Ready ¦ 4 ¦ 1983.46 ¦ 5 ¦ 3 | ok
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | Crossing Details | 27 | 10 | statutory_crossing, summary_status | R5: Crossing Type ¦ 110kV ¦ 220kV ¦ 400kV ¦ 765kV ¦ SH-Xing ¦ NH-Xing ¦ Railway Xing ¦ Total ¦ Remarks R12: Sl. No. ¦ FROM (AP) ¦ TO (AP) ¦ Name of the Line ¦ NAME OF CROSSING ¦ Date of First Submission ¦ Joint Inspection Status ¦ Provisional approval status ¦ Remarks R13: 1 ¦ 33/5 ¦ 33/6 ¦ 110 KV S/C NAVALI KPTCL SS TO MULLUR SOLAR PLANT TL. ¦ Power line ¦ 2024-10-11 00:00:00 ¦ Completed ¦ Submitted ¦ Formal Approval Awaited R14: 2 ¦ 36/1 ¦ AP37 ¦ 110 KV S/C SULEKAL-TAVARGERA TL ON D/C TOWERS. ¦ Power line ¦ 2024-10-11 00:00:00 ¦ Completed ¦ Submitted ¦ Formal Approval Awaited R15: 3 ¦ AP45 ¦ 45/1 ¦ 110kV S/C KUSHTAGI-KANAKAGIRI TL ON D/C TOWERS. ¦ Power line ¦ 2024-10-11 00:00:00 ¦ Completed ¦ Submitted ¦ Formal Approval Awaited | CROSSINGS PROPOSAL STATUS 765kV D/c Koppal II (PS)-Raichur (Part-1) transmission line project Crossing Type ¦ 110kV ¦ 220kV ¦ 400kV ¦ 765kV ¦ SH-Xing ¦ NH-Xing ¦ Railway Xing ¦ Total ¦ Remarks Total Nos ¦ 6 ¦ 3 ¦ 4 ¦ 1 ¦ 14 Submitted Till Date Completed Till Date Balance to Execute ¦ 4 ¦ 14 Crossings Details | ok
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | Project Details | 20 | 11 | project_details | R1: Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer / Manager ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Engineer/Supervisor | Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer / Manager ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Engineer/Supervisor TA 418 ¦ 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1) ¦ PGCIL ¦ 12.03.2024 ¦ 30.06.2026 (EOT) ¦ Mr. Ajith Jayasurya ¦ Mr. Arun Felbin ¦ Mr. Ajith Kumar MG ¦ Mr. Tamil Velan ¦ Mr. Ajith Jayasurya ¦ Prathab DK Prabhu Prasad Ashok Prasad Basudev Mahato Ajay Kumar Durai swamy | ok
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | TS | 264 | 27 |  |  | Name of the Line :765kV D/C KOPPAL II(PS) - RAICHUR (Part-1) TRANSMISSION LINE Sl.No ¦ Loc. No. (Provisional) ¦ Type of Tower ¦ Span (Mtr) 1 ¦ AP32 ¦ 1DC2+6 ¦ 249.635 ¦ 32/0-33/0 -0 ¦ -1.5 ¦ -3 ¦ -4.5 ¦ -6 ¦ +0 ¦ +1.5 ¦ +3 ¦ +4.5 ¦ +6 ¦ +9 ¦ +18 ¦ Total 2 ¦ AP33 ¦ 1DD45+18 ¦ 425 ¦ 1DA ¦ 10 ¦ 7 ¦ 3 ¦ 1 ¦ 26 ¦ 2 ¦ 21 ¦ 2 ¦ 8 ¦ 6 ¦ 86 1DB1 ¦ 6 ¦ 2 ¦ 1 ¦ 5 ¦ 14 ¦ 113 ¦ AP57 ¦ 1DC2+6 ¦ 57/0 ¦ 1DC1+3 ¦ 73.125 3 ¦ 33/1 ¦ 1DA-3 ¦ 425 ¦ 1DB2 ¦ 1 ¦ 2 ¦ 2 ¦ 2 ¦ 7 1DC1 ¦ 3 ¦ 1 ¦ 1 ¦ 1 ¦ 6 ¦ 114 ¦ 57/1 ¦ 1DA+0 ¦ 57/1 ¦ 1DA+0 ¦ 71.43 | ok
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | 2026-05-21 | TS (2) | 264 | 27 |  |  | Name of the Line :765kV D/C KOPPAL II(PS) - RAICHUR (Part-1) TRANSMISSION LINE Sl.No ¦ Loc. No. (Provisional) ¦ Type of Tower ¦ Span (Mtr) 1 ¦ AP32 ¦ 1DC2+6 ¦ 249.635 ¦ 32/0-33/0 -0 ¦ -1.5 ¦ -3 ¦ -4.5 ¦ -6 ¦ +0 ¦ +1.5 ¦ +3 ¦ +4.5 ¦ +6 ¦ +9 ¦ +18 ¦ Total 2 ¦ AP33 ¦ 1DD45+18 ¦ 425 ¦ 1DA ¦ 3 ¦ 18 ¦ 34 ¦ 19 ¦ 7 ¦ 6 ¦ 87 ¦ 2 1DB1 ¦ 1 ¦ 7 ¦ 1 ¦ 1 ¦ 4 ¦ 14 ¦ 113 ¦ AP57 ¦ 1DC2+6 ¦ 57/0 ¦ 1DC1+3 ¦ 73.125 3 ¦ 33/1 ¦ 1DA-3 ¦ 425 ¦ 1DB2 ¦ 1 ¦ 2 ¦ 1 ¦ 4 1DC1 ¦ 1 ¦ 2 ¦ 2 ¦ 2 ¦ 7 ¦ 114 ¦ 57/1 ¦ 1DA+0 ¦ 57/1 ¦ 1DA+0 ¦ 71.43 | ok
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Const Revenue | 89 | 74 | erection, foundation, project_details, stringing, summary_status, visual_l2 | R7: ACTIVITY ¦ UNIT ¦ L2 Vs Actual ¦ LOA/Final Quantity ¦ 2021-02-28 00:00:00 ¦ 2021-03-31 00:00:00 ¦ 2021-04-01 00:00:00 ¦ 2021-05-01 00:00:00 ¦ 2021-06-01 00:00:00 ¦ 2021-07-01 00:00:00 ¦ 2021-08-01 00:00:00 ¦ 2021-09-01 00:00:00 ¦ 2021-10-01 00:00:00 ¦ 2021-11-01 00:00:00 ¦ 2021-12-01 00:00:00 ¦ 2022-01-01 00:00:00 ¦ 2022-02-01 00:00:00 ¦ 2022-03-01 00:00:00 ¦ 2022-04-01 00:00:00 ¦ 2022-05-01 00:00 R8: Foundation ¦ Loc ¦ L2 ¦ 263 ¦ 17 ¦ 23 ¦ 26 ¦ 30 ¦ 29 ¦ 32 ¦ 31 ¦ 20 ¦ 28 ¦ 24 ¦ 260 R11: Erection ¦ Loc ¦ L2 ¦ 271 ¦ 2 ¦ 4 ¦ 24 ¦ 27 ¦ 27 ¦ 27 ¦ 27 ¦ 18 ¦ 27 ¦ 27 ¦ 27 ¦ 23 ¦ 260 R14: Stringing ¦ Km ¦ L2 ¦ 100 ¦ 2 ¦ 3 ¦ 10 ¦ 12 ¦ 12 ¦ 8 ¦ 11 ¦ 12 ¦ 12 ¦ 10 ¦ 8 ¦ 100 | L2 Vs Actual Activities 765KV D/C Bhadla-II PS- Sikar-II (Part C) TW 03 NOA:TBCB/765 KV/Phase-II/Rajasthan part-C/TW-03/G4/NOA-II/6 Dt.15/02/2021 MONTHLY CONSTRUCTION REVENUE STATUS 20-May-26 ACTIVITY ¦ UNIT ¦ L2 Vs Actual ¦ LOA/Final Quantity ¦ 2021-02-28 00:00:00 ¦ 2021-03-31 00:00:00 ¦ 2021-04-01 00:00:00 ¦ 2021-05-01 00:00:00 ¦ 2021-06-01 00:00:00 ¦ 2021-07-01 00:00:00 ¦ 2021-08-01 00:00:00 ¦ 2021-09-01 00:00:00 ¦ 2021-10-01 00:00:00 ¦ 2021-11-01 00:00:00 ¦ 2021-12-01 00:00:00 ¦ 2022-01-01 00:00:00 ¦ 2022-02-01 00:00:00 ¦ 2022-03-01 00:00:00 ¦ 2022-04-01 00:00:00 ¦ 2022-05-01 00:00:00 Foundation ¦ Loc ¦ L2 ¦ 263 ¦ 17 ¦ 23 ¦ 26 ¦ 30 ¦ 29 ¦ 32 ¦ 31 ¦ 20 ¦ 28 ¦ 24 ¦ 260 Actual ¦ 239 Revenue INR (Crs.) ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! ¦ #VALUE! | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | DPR_TA419 | 72 | 18 | project_details, summary_status, supply, survey_soil, visual_l2 | R3: TA-419 ¦ DAILY PROGRESS REPORT ¦ 2026-05-20 00:00:00 R4: Contractual Start Date ¦ 2024-02-06 00:00:00 ¦ Project ¦ 765 KV D/C Sikar II - Narela TL02 R5: Contractual Finish Date ¦ 2025-05-05 00:00:00 ¦ Client ¦ Power Grid Corporation of India R6: Total Days ¦ 454 ¦ NOA (Supply) ¦ CC/T/W-TW/DOM/A06/24/01867/NOA-I & II /24-101806/01 dated 06.02.2024 R9: Sr ¦ Activity ¦ Quantity ¦ Cumulative till Last Month ¦ Plan for the Month ¦ Progress for the Month ¦ Cumulative Progress ¦ Balance Progress ¦ Gangs working May-26 ¦ Remarks | TA-419 ¦ DAILY PROGRESS REPORT ¦ 2026-05-20 00:00:00 Contractual Start Date ¦ 2024-02-06 00:00:00 ¦ Project ¦ 765 KV D/C Sikar II - Narela TL02 Contractual Finish Date ¦ 2025-05-05 00:00:00 ¦ Client ¦ Power Grid Corporation of India Total Days ¦ 454 ¦ NOA (Supply) ¦ CC/T/W-TW/DOM/A06/24/01867/NOA-I & II /24-101806/01 dated 06.02.2024 Completed Days ¦ 834 ¦ NOA (Service) ¦ CC/T/W-TW/DOM/A06/24/01867/NOA-I & II /24-101806/02 dated 06.02.2024 2026-05-20 00:00:00 Sr ¦ Activity ¦ Quantity ¦ Cumulative till Last Month ¦ Plan for the Month ¦ Progress for the Month ¦ Cumulative Progress ¦ Balance Progress ¦ Gangs working May-26 ¦ Remarks LOA ¦ Estimated ¦ L2 ¦ Progress ¦ L2 ¦ May'26 ¦ Till Date | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Soil Inv | 34 | 6 | summary_status, survey_soil | R2: SL No. ¦ LOC. No. ¦ Tower Type ¦ Soil Investigation date ¦ Recommended Soil classification ¦ Remarks | SOIL INVESTIGATION STATUS ¦ 2026-05-20 00:00:00 SL No. ¦ LOC. No. ¦ Tower Type ¦ Soil Investigation date ¦ Recommended Soil classification ¦ Remarks 1 ¦ AP1 ¦ 2024-06-16 00:00:00 ¦ Wet 2 ¦ AP6 ¦ 2024-06-16 00:00:00 ¦ Wet 3 ¦ AP10 ¦ 2024-06-16 00:00:00 ¦ Wet 4 ¦ AP14 ¦ 2024-06-16 00:00:00 ¦ PS 5 ¦ AP19 ¦ 2024-06-15 00:00:00 ¦ Dry 6 ¦ AP22 ¦ 2024-06-15 00:00:00 ¦ Dry | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | TOWER SUPPLY | 63 | 13 | commercial, project_details, summary_status, supply | R2: Sl. ¦ Description ¦ UNIT WEIGHT ¦ LOA QTY ¦ AMD-2 QTY ¦ LE ¦ Supplied ¦ Billed ¦ Bal Supply ¦ Bal Billing ¦ Remarks ¦ PRS Releasable ¦ Bilable | TOWER SUPPLY STATUS OF TW03 Sl. ¦ Description ¦ UNIT WEIGHT ¦ LOA QTY ¦ AMD-2 QTY ¦ LE ¦ Supplied ¦ Billed ¦ Bal Supply ¦ Bal Billing ¦ Remarks ¦ PRS Releasable ¦ Bilable A ¦ STUBS-3.5 M Depth 1 ¦ DA ¦ 0.8177399999999999 ¦ 179 ¦ 185 ¦ 166 ¦ 142 ¦ 142 ¦ 24 2 ¦ DB1 ¦ 1.554903 ¦ 18 ¦ 12 ¦ 14 ¦ 6 ¦ 6 ¦ 8 3 ¦ DB2 ¦ 1.554903 ¦ 19 ¦ 17 ¦ 18 ¦ 9 ¦ 9 ¦ 9 4 ¦ DB2+18/25 ¦ 1.71 ¦ 1 5 ¦ DC1 ¦ 1.890319 ¦ 11 ¦ 10 ¦ 10 ¦ 10 ¦ 10 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | RATE | 112 | 11 | erection, foundation | R2: TOWER TYPE ¦ Classification ¦ Rate ¦ UNIT RATE ¦ TOWER TYPE ¦ CLASSIFICATION ¦ UNIT RATE | TOWER ERECTION ¦ FOUNDATION TOWER TYPE ¦ Classification ¦ Rate ¦ UNIT RATE ¦ TOWER TYPE ¦ CLASSIFICATION ¦ UNIT RATE DA-3 ¦ Dry ¦ 431682.441 ¦ DA-3 ¦ Dry ¦ DA-3Dry ¦ 431682.441 DA-1.5 ¦ DA-1.5 ¦ Dry ¦ DA-1.5Dry ¦ 431682.441 DA+0 ¦ DA+0 ¦ Dry ¦ DA+0Dry ¦ 431682.441 DA+1.5 ¦ DA+1.5 ¦ Dry ¦ DA+1.5Dry ¦ 502330.438 DA+3 ¦ DA+3 ¦ Dry ¦ DA+3Dry ¦ 502330.438 DA+4.5 ¦ DA+4.5 ¦ Dry ¦ DA+4.5Dry ¦ 502330.438 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tack Welding | 98 | 8 | earthing_tack, project_details, summary_status | R2: S.No ¦ Loc No ¦ Tower Type ¦ Completion Date ¦ Agency ¦ Status ¦ Painting ¦ Remarks | TACKWELDING ¦ 2026-05-20 00:00:00 S.No ¦ Loc No ¦ Tower Type ¦ Completion Date ¦ Agency ¦ Status ¦ Painting ¦ Remarks 1 ¦ 13/0 2 ¦ 14/0 3 ¦ 14/1 4 ¦ 15/0 5 ¦ 15A/0 6 ¦ 16/0 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Ins Hosting | 97 | 8 | stringing, summary_status, supply | R2: Sr ¦ Section ¦ Tower No. ¦ Status ¦ Date of hoisting ¦ Rough Sag ¦ Final Sag ¦ Remarks | INSULATOR HOISTING DETAILS ¦ 2026-05-20 00:00:00 Sr ¦ Section ¦ Tower No. ¦ Status ¦ Date of hoisting ¦ Rough Sag ¦ Final Sag ¦ Remarks 1 ¦ 13/0 2 ¦ 14/0 3 ¦ 14/1 4 ¦ 15/0 5 ¦ 15A/0 6 ¦ 16/0 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing | 104 | 10 | stringing, supply | R2: Sl. ¦ Section Details ¦ Section Length (Mtr) ¦ Insulator Hoisting ¦ Paying Out Started ¦ Paying Out Completed ¦ Final Sag Started ¦ Final Sag Completed ¦ Agency ¦ Remarks | Stringing ¦ 2026-05-21 00:00:00 Sl. ¦ Section Details ¦ Section Length (Mtr) ¦ Insulator Hoisting ¦ Paying Out Started ¦ Paying Out Completed ¦ Final Sag Started ¦ Final Sag Completed ¦ Agency ¦ Remarks 1 2 3 4 5 6 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | L2 | 98 | 83 | visual_l2 |  |  | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Supply Status | 110 | 10 | summary_status, supply |  |  | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | ROW | 184 | 11 | foundation, row_hindrance, summary_status | R4: SL No. ¦ Location / Stretch ¦ Activity ¦ Date of 1st approach/ ROW start date ¦ Date of last approach/ Cleared on ¦ Duration of ROW (Days) ¦ Status ¦ Nature of hindrance ¦ Brief description on resolution R5: 1 ¦ 04/1 ¦ Foundation ¦ 2024-07-13 00:00:00 ¦ 2024-07-29 00:00:00 ¦ 16 ¦ Resolved R6: 2 ¦ 05/4 ¦ Foundation ¦ 2024-07-13 00:00:00 ¦ 676 R7: 3 ¦ 06/1 ¦ Foundation ¦ 2024-07-16 00:00:00 ¦ 2024-07-29 00:00:00 ¦ 13 ¦ Resolved R8: 4 ¦ 06/11 ¦ Foundation ¦ 2024-07-06 00:00:00 ¦ 2024-07-30 00:00:00 ¦ 24 ¦ Resolved ¦ Compensation | ROW STATUS: 765KV D/C Sikar II to Narela TL02 ¦ 2026-05-20 00:00:00 SL No. ¦ Location / Stretch ¦ Activity ¦ Date of 1st approach/ ROW start date ¦ Date of last approach/ Cleared on ¦ Duration of ROW (Days) ¦ Status ¦ Nature of hindrance ¦ Brief description on resolution 1 ¦ 04/1 ¦ Foundation ¦ 2024-07-13 00:00:00 ¦ 2024-07-29 00:00:00 ¦ 16 ¦ Resolved 2 ¦ 05/4 ¦ Foundation ¦ 2024-07-13 00:00:00 ¦ 676 3 ¦ 06/1 ¦ Foundation ¦ 2024-07-16 00:00:00 ¦ 2024-07-29 00:00:00 ¦ 13 ¦ Resolved 4 ¦ 06/11 ¦ Foundation ¦ 2024-07-06 00:00:00 ¦ 2024-07-30 00:00:00 ¦ 24 ¦ Resolved ¦ Compensation 5 ¦ 06/12 ¦ Foundation ¦ 2024-07-06 00:00:00 ¦ 2024-07-15 00:00:00 ¦ 9 ¦ Resolved | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tower Schedule | 636 | 32 | statutory_crossing, survey_soil, visual_l2 | R5: Sl.No ¦ AP No. ¦ Tower No. ¦ Type of Tower ¦ HT of Tower (Mtr) ¦ Span (Mtr) ¦ Cumulative Span (Mtr) ¦ Raised Chimney ¦ R.L (Mtr) ¦ Deviation Angle (Deg) ¦ Sum of Adjacent Spans ¦ Wind Span (Mtr) ¦ Weight Span in Mtr (Cold) ¦ Weight Span in Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) ¦ UTM Coordinates ¦ Crossing Details ¦ NAME OF VILLAGE ¦ NAME OF TEHSIL R51: 23 ¦ AP3 ¦ 3/0 ¦ DD45+18 ¦ 88.72 ¦ 8415.585000000001 ¦ 2 ¦ 280.384 ¦ 35° 45' 23"LT ¦ 645.826 ¦ 322.913 ¦ 167 ¦ 274 ¦ 440 ¦ 150 ¦ 249 ¦ 399 ¦ 617830.087 ¦ 3122276.028 ¦ With 2M RC/To Maintain Electrical Clearance | KEC INTERNATION LIMITED INDIA TRANSMISSION LINE PACKAGE TL02 FOR 765 kV D/C TRANSMISSION LINE ASSOCIATED WITH TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM REZ IN RAJASTHAN (20 GW) UNDER PH-III (PART-D) UNDER TBCB ROUTE. 765kV D/C SIKAR II – NARELA TRANSMISSION LINE PART II - CHECK SURVEY - AP0A TO AP91 (WZ4) (WZ5) CLIENT : POWERGRID SIKAR-KHETRI TRANSMISSION LIMITED. [A 100% WHOLLY OWNED SUBSIDIARY OF POWERGRID] Sl.No ¦ AP No. ¦ Tower No. ¦ Type of Tower ¦ HT of Tower (Mtr) ¦ Span (Mtr) ¦ Cumulative Span (Mtr) ¦ Raised Chimney ¦ R.L (Mtr) ¦ Deviation Angle (Deg) ¦ Sum of Adjacent Spans ¦ Wind Span (Mtr) ¦ Weight Span in Mtr (Cold) ¦ Weight Span in Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) ¦ UTM Coordinates ¦ Crossing Details ¦ NAME OF VILLAGE ¦ NAME OF TEHSIL Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Easting ¦ Northing 1 ¦ AP0A ¦ 0A/0 (CT) ¦ DD60+3 ¦ 73.72 ¦ 282.288 ¦ 447.467 ¦ 223.7335 ¦ 210 ¦ 210 ¦ 214 ¦ 214 ¦ 611960.328 ¦ 3117570.879 447.467 ¦ METAL ROAD | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | FDN | 340 | 18 | commercial, foundation, project_details, summary_status | R1: FOUNDATION ¦ Completed: ¦ 249 ¦ WIP: ¦ 21 ¦ 2026-05-20 00:00:00 R2: Sr ¦ Location ¦ TOT ¦ RC ¦ Classification ¦ Start Date ¦ Completion Date ¦ Agency ¦ Status ¦ RA Bill No. ¦ Remarks ¦ Revenue ¦ LS Detail R4: 1 ¦ 0A/0 (CT) ¦ DD60+3 ¦ Wet ¦ 2024-12-02 00:00:00 ¦ 2024-12-24 00:00:00 ¦ Shyam Ent ¦ Completed ¦ Submitted R5: 2 ¦ 0B/0 ¦ DC1+6 ¦ Wet ¦ 2024-10-20 00:00:00 ¦ 2024-11-08 00:00:00 ¦ Shyam Ent ¦ Completed ¦ Submitted R6: 3 ¦ 0B/1 ¦ DA+3 ¦ Wet ¦ 2024-09-18 00:00:00 ¦ 2024-10-22 00:00:00 ¦ NV Infra ¦ Completed ¦ 757160 ¦ Submitted | FOUNDATION ¦ Completed: ¦ 249 ¦ WIP: ¦ 21 ¦ 2026-05-20 00:00:00 Sr ¦ Location ¦ TOT ¦ RC ¦ Classification ¦ Start Date ¦ Completion Date ¦ Agency ¦ Status ¦ RA Bill No. ¦ Remarks ¦ Revenue ¦ LS Detail 249 ¦ 299 1 ¦ 0A/0 (CT) ¦ DD60+3 ¦ Wet ¦ 2024-12-02 00:00:00 ¦ 2024-12-24 00:00:00 ¦ Shyam Ent ¦ Completed ¦ Submitted 2 ¦ 0B/0 ¦ DC1+6 ¦ Wet ¦ 2024-10-20 00:00:00 ¦ 2024-11-08 00:00:00 ¦ Shyam Ent ¦ Completed ¦ Submitted 3 ¦ 0B/1 ¦ DA+3 ¦ Wet ¦ 2024-09-18 00:00:00 ¦ 2024-10-22 00:00:00 ¦ NV Infra ¦ Completed ¦ 757160 ¦ Submitted 4 ¦ 0B/2 ¦ DA+3 ¦ Wet ¦ 2024-09-11 00:00:00 ¦ 2024-09-28 00:00:00 ¦ NV Infra ¦ Completed ¦ 757160 ¦ Submitted 5 ¦ 0B/3 ¦ DA+6 ¦ Wet ¦ 2024-09-30 00:00:00 ¦ 2024-10-07 00:00:00 ¦ NV Infra ¦ Completed ¦ 757160 ¦ Submitted | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Latest Tower Schedule | 675 | 48 | statutory_crossing, survey_soil, visual_l2 | R5: Sl.No ¦ AP No. ¦ Tower No. ¦ Type of Tower ¦ HT of Tower (Mtr) ¦ Span (Mtr) ¦ Cumulative Span (Mtr) ¦ Raised Chimney ¦ R.L (Mtr) ¦ Deviation Angle (Deg) ¦ Sum of Adjacent Spans ¦ Wind Span (Mtr) ¦ Weight Span in Mtr (Cold) ¦ Weight Span in Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) ¦ UTM Coordinates ¦ Crossing Details ¦ Name of District ¦ Name of Tehsil | KEC INTERNATION LIMITED INDIA TRANSMISSION LINE PACKAGE TL02 FOR 765 kV D/C TRANSMISSION LINE ASSOCIATED WITH TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM REZ IN RAJASTHAN (20 GW) UNDER PH-III (PART-D) UNDER TBCB ROUTE. 765kV D/C SIKAR II – NARELA TRANSMISSION LINE PART II - CHECK SURVEY - AP0A TO GANTRY (WZ4) (WZ5) CLIENT : POWERGRID SIKAR-KHETRI TRANSMISSION LIMITED. [A 100% WHOLLY OWNED SUBSIDIARY OF POWERGRID] Sl.No ¦ AP No. ¦ Tower No. ¦ Type of Tower ¦ HT of Tower (Mtr) ¦ Span (Mtr) ¦ Cumulative Span (Mtr) ¦ Raised Chimney ¦ R.L (Mtr) ¦ Deviation Angle (Deg) ¦ Sum of Adjacent Spans ¦ Wind Span (Mtr) ¦ Weight Span in Mtr (Cold) ¦ Weight Span in Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) ¦ UTM Coordinates ¦ Crossing Details ¦ Name of District ¦ Name of Tehsil Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Easting ¦ Northing 1 ¦ AP0A ¦ 0A/0 (CT) ¦ DD60+3 ¦ 73.72 ¦ 282.288 ¦ 447.467 ¦ 223.7335 ¦ 210 ¦ 210 ¦ 214 ¦ 214 ¦ 611960.328 ¦ 3117570.879 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat 447.467 ¦ METAL ROAD | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet8 | 332 | 9 | foundation | R2: Loc ¦ fdn ¦ er R3: 0A/0 (CT) ¦ Completed ¦ Completed R4: 0B/0 ¦ Completed ¦ Completed R5: 0B/1 ¦ Completed ¦ Completed R6: 0B/2 ¦ Completed ¦ Completed | Loc ¦ fdn ¦ er 0A/0 (CT) ¦ Completed ¦ Completed 0B/0 ¦ Completed ¦ Completed 0B/1 ¦ Completed ¦ Completed 0B/2 ¦ Completed ¦ Completed 0B/3 ¦ Completed ¦ Completed 0C/0 ¦ Completed ¦ Completed 0C/1 ¦ Completed ¦ Completed | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet7 | 8 | 10 | project_details | R2: Sl No. ¦ Location ¦ Tower Type ¦ Classification ¦ Start Date ¦ Completion Date ¦ Agency | Sl No. ¦ Location ¦ Tower Type ¦ Classification ¦ Start Date ¦ Completion Date ¦ Agency 1 ¦ 25/0 ¦ DB2+18 ¦ Wet ¦ 2025-05-12 00:00:00 ¦ 2025-05-19 00:00:00 ¦ Garg Energy 2 ¦ 29/0 ¦ DB1+6 ¦ Wet ¦ 2025-06-09 00:00:00 ¦ 2025-06-15 00:00:00 ¦ Garg Energy 3 ¦ 34/0 ¦ DD60+0 ¦ Wet ¦ 2025-03-25 00:00:00 ¦ 2025-03-29 00:00:00 ¦ Garg Energy 4 ¦ 40/3 ¦ DA+3 ¦ FS ¦ 2025-03-27 00:00:00 ¦ 2025-04-11 00:00:00 ¦ Garg Energy 5 ¦ 40/5 ¦ DA+1.5 ¦ FS ¦ 2025-04-12 00:00:00 ¦ 2025-04-17 00:00:00 ¦ Garg Energy 6 ¦ 62/4 ¦ 5DA-3 ¦ PS ¦ 2025-03-01 00:00:00 ¦ 2025-03-05 00:00:00 ¦ Garg energy | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection productivity | 111 | 41 | erection | R3: Sr. No. ¦ Sub-Contractor Name ¦ Loc. No. ¦ Type of Tower ¦ Tower Weight (MT) ¦ 01.11.25 (MT) ¦ 02.11.25 (MT) ¦ 03.11.25 (MT) ¦ 04.11.25 (MT) ¦ 05.11.25 (MT) ¦ 06.11.25 (MT) ¦ 07.11.25 (MT) ¦ 08.11.25 (MT) ¦ 09.11.25 (MT) ¦ 10.11.25 (MT) ¦ 11.11.25 (MT) ¦ 12.11.25 (MT) ¦ 13.11.25 (MT) ¦ 14.11.25 (MT) ¦ 15.11.25 (MT) R4: Plan ¦ Actual ¦ Shotfall R5: 1 ¦ Infinidea ¦ 0B/0 ¦ DC1+6 ¦ 72.474 ¦ 10 ¦ 10 ¦ 10 ¦ 10 ¦ 10 ¦ 50 ¦ Completed R6: 2 ¦ Jwala Singh ¦ 36/8 ¦ DA+0 ¦ 36.16 ¦ 4.52 ¦ 4.52 ¦ 4.52 ¦ 4.52 ¦ 4.52 ¦ 4.52 ¦ 4.52 ¦ 4.52 ¦ 36.16 ¦ Completed R7: 41/5 ¦ DA+1.5 ¦ 37.138 ¦ 6.189666666666667 ¦ 6.189666666666667 ¦ 6.189666666666667 ¦ 6.189666666666667 ¦ 6.189666666666667 ¦ 6.189666666666667 ¦ 37.138 ¦ Completed | KEC International Limited - Gurgaon. Erection Productivity Gang wise - Nov'25 Sr. No. ¦ Sub-Contractor Name ¦ Loc. No. ¦ Type of Tower ¦ Tower Weight (MT) ¦ 01.11.25 (MT) ¦ 02.11.25 (MT) ¦ 03.11.25 (MT) ¦ 04.11.25 (MT) ¦ 05.11.25 (MT) ¦ 06.11.25 (MT) ¦ 07.11.25 (MT) ¦ 08.11.25 (MT) ¦ 09.11.25 (MT) ¦ 10.11.25 (MT) ¦ 11.11.25 (MT) ¦ 12.11.25 (MT) ¦ 13.11.25 (MT) ¦ 14.11.25 (MT) ¦ 15.11.25 (MT) Plan ¦ Actual ¦ Shotfall 1 ¦ Infinidea ¦ 0B/0 ¦ DC1+6 ¦ 72.474 ¦ 10 ¦ 10 ¦ 10 ¦ 10 ¦ 10 ¦ 50 ¦ Completed 2 ¦ Jwala Singh ¦ 36/8 ¦ DA+0 ¦ 36.16 ¦ 4.52 ¦ 4.52 ¦ 4.52 ¦ 4.52 ¦ 4.52 ¦ 4.52 ¦ 4.52 ¦ 4.52 ¦ 36.16 ¦ Completed 41/5 ¦ DA+1.5 ¦ 37.138 ¦ 6.189666666666667 ¦ 6.189666666666667 ¦ 6.189666666666667 ¦ 6.189666666666667 ¦ 6.189666666666667 ¦ 6.189666666666667 ¦ 37.138 ¦ Completed 41/4 ¦ DA+6 ¦ 43.804 ¦ 6 ¦ 6 ¦ 6 ¦ 6 ¦ 6 ¦ 3 ¦ 4 ¦ 37 ¦ WIP | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Foundation Daily Progress | 1319 | 51 | foundation, summary_status, supply | R4: F ¦ Frustum ¦ 1 ¦ Completed R10: Foundation Daily Progress Register ¦ Pit ¦ A ¦ B ¦ C ¦ D R12: S.No. ¦ Date ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Remarks ¦ Competed ¦ D ¦ S ¦ St ¦ F ¦ P ¦ C ¦ D ¦ S ¦ ST ¦ F ¦ P ¦ C ¦ D R42: 30 ¦ 2025-12-20 00:00:00 ¦ 65/0 ¦ 5DD60+6 ¦ ROW R59: 47 ¦ 2025-12-21 00:00:00 ¦ 65/0 ¦ 5DD60+6 ¦ ROW | Identification ¦ Mark D ¦ Dewatering ¦ U/P F ¦ Frustum ¦ 1 ¦ Completed P ¦ Pyramid C ¦ Chimney S ¦ Stub Seetting St ¦ Steel Binding Foundation Daily Progress Register ¦ Pit ¦ A ¦ B ¦ C ¦ D | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet9 | 331 | 8 | erection, foundation | R1: Loc ¦ TOT ¦ Foundation ¦ Erection R2: 0A/0 (CT) ¦ DD60+3 ¦ Completed ¦ Completed R3: 0B/0 ¦ DC1+6 ¦ Completed ¦ Completed R4: 0B/1 ¦ DA+3 ¦ Completed ¦ Completed R5: 0B/2 ¦ DA+3 ¦ Completed ¦ Completed | Loc ¦ TOT ¦ Foundation ¦ Erection 0A/0 (CT) ¦ DD60+3 ¦ Completed ¦ Completed 0B/0 ¦ DC1+6 ¦ Completed ¦ Completed 0B/1 ¦ DA+3 ¦ Completed ¦ Completed 0B/2 ¦ DA+3 ¦ Completed ¦ Completed 0B/3 ¦ DA+6 ¦ Completed ¦ Completed 0C/0 ¦ DD45+0 ¦ Completed ¦ Completed 0C/1 ¦ DA+3 ¦ Completed ¦ Completed | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Summary | 398 | 22 | erection, foundation, summary_status | R2: Sl No. ¦ Tower No. ¦ Type of Tower ¦ Village ¦ District ¦ Tehsil ¦ Span ¦ WZ ¦ Foundation Status ¦ Rectification ¦ Rectification Status ¦ Erection Status ¦ Submission Status ¦ Submission Status ¦ Market Rate filled ¦ Market Rate/Circle Rate ¦ Verification Status ¦ Rates ¦ Printed R3: 1 ¦ 0A/0 (CT) ¦ DD60+3 ¦ Derolijat ¦ Mahendragarh ¦ Mahendragarh ¦ 447.467 ¦ WZ-4 ¦ Completed ¦ Completed ¦ Submission 7 ¦ Submitted ¦ Yes ¦ 2087250 ¦ Verified R4: 2 ¦ 0B/0 ¦ DC1+6 ¦ Derolijat ¦ Mahendragarh ¦ Mahendragarh ¦ 362.533 ¦ WZ-4 ¦ Completed ¦ Completed ¦ Submitted ¦ Yes ¦ 2087250 ¦ L3-Ere R5: 3 ¦ 0B/1 ¦ DA+3 ¦ Derolijat ¦ Mahendragarh ¦ Mahendragarh ¦ 420 ¦ WZ-4 ¦ Completed ¦ Completed ¦ Submission 7 ¦ Submitted ¦ Yes ¦ 2087250 ¦ Verified ¦ L3-Fdn R6: 4 ¦ 0B/2 ¦ DA+3 ¦ Derolijat ¦ Mahendragarh ¦ Mahendragarh ¦ 395 ¦ WZ-4 ¦ Completed ¦ Completed ¦ Submission 7 ¦ Submitted ¦ Yes ¦ 2087250 ¦ Verified | 225 ¦ 184 ¦ 300 ¦ 206 ¦ 127Verified Sl No. ¦ Tower No. ¦ Type of Tower ¦ Village ¦ District ¦ Tehsil ¦ Span ¦ WZ ¦ Foundation Status ¦ Rectification ¦ Rectification Status ¦ Erection Status ¦ Submission Status ¦ Submission Status ¦ Market Rate filled ¦ Market Rate/Circle Rate ¦ Verification Status ¦ Rates ¦ Printed 1 ¦ 0A/0 (CT) ¦ DD60+3 ¦ Derolijat ¦ Mahendragarh ¦ Mahendragarh ¦ 447.467 ¦ WZ-4 ¦ Completed ¦ Completed ¦ Submission 7 ¦ Submitted ¦ Yes ¦ 2087250 ¦ Verified 2 ¦ 0B/0 ¦ DC1+6 ¦ Derolijat ¦ Mahendragarh ¦ Mahendragarh ¦ 362.533 ¦ WZ-4 ¦ Completed ¦ Completed ¦ Submitted ¦ Yes ¦ 2087250 ¦ L3-Ere 3 ¦ 0B/1 ¦ DA+3 ¦ Derolijat ¦ Mahendragarh ¦ Mahendragarh ¦ 420 ¦ WZ-4 ¦ Completed ¦ Completed ¦ Submission 7 ¦ Submitted ¦ Yes ¦ 2087250 ¦ Verified ¦ L3-Fdn 4 ¦ 0B/2 ¦ DA+3 ¦ Derolijat ¦ Mahendragarh ¦ Mahendragarh ¦ 395 ¦ WZ-4 ¦ Completed ¦ Completed ¦ Submission 7 ¦ Submitted ¦ Yes ¦ 2087250 ¦ Verified 5 ¦ 0B/3 ¦ DA+6 ¦ Derolijat ¦ Mahendragarh ¦ Mahendragarh ¦ 418.563 ¦ WZ-4 ¦ Completed ¦ Completed ¦ Submission 7 ¦ Submitted ¦ Yes ¦ 2087250 ¦ Verified 6 ¦ 0C/0 ¦ DD45+0 ¦ Derolijat ¦ Mahendragarh ¦ Mahendragarh ¦ 379.997 ¦ WZ-4 ¦ Completed ¦ Completed ¦ Submission 7 ¦ Submitted ¦ Yes ¦ 2087250 ¦ Verified | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet10 | 1 | 1 |  |  |  | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Visual Chart | 147 | 46 | earthing_tack, erection, foundation, row_hindrance, statutory_crossing, stringing, visual_l2 | R3: Sr ¦ Description ¦ Unit ¦ Scope ¦ Completed ¦ Balance ¦ Foundation ROW R4: WZ4 ¦ WZ5 ¦ Total ¦ WZ4 ¦ WZ5 ¦ Total ¦ WZ4 ¦ WZ5 ¦ Total ¦ Stringing WIP R5: 1 ¦ Foundation ¦ Nos ¦ 174 ¦ Nos ¦ 156 ¦ 330 ¦ 170 ¦ 79 ¦ 249 ¦ 4 ¦ 77 ¦ 81 ¦ Erection ROW ¦ Tack Weld WIP R6: 2 ¦ Earthing ¦ Nos ¦ 174 ¦ Nos ¦ 156 ¦ 330 ¦ 170 ¦ 79 ¦ 249 ¦ 4 ¦ 77 ¦ 81 ¦ Erection WIP R7: 3 ¦ Tower Erection ¦ Nos ¦ 174 ¦ Nos ¦ 156 ¦ 330 ¦ 154 ¦ 49 ¦ 203 ¦ 20 ¦ 107 ¦ 127 ¦ Power Line Crossing ¦ Foundation WIP | KEC INTERNATIONAL LIMITED ¦ Completed TA-419, 765kV D/C Sikar II - Narela TL02 ¦ Project Visual Chart Sr ¦ Description ¦ Unit ¦ Scope ¦ Completed ¦ Balance ¦ Foundation ROW WZ4 ¦ WZ5 ¦ Total ¦ WZ4 ¦ WZ5 ¦ Total ¦ WZ4 ¦ WZ5 ¦ Total ¦ Stringing WIP 1 ¦ Foundation ¦ Nos ¦ 174 ¦ Nos ¦ 156 ¦ 330 ¦ 170 ¦ 79 ¦ 249 ¦ 4 ¦ 77 ¦ 81 ¦ Erection ROW ¦ Tack Weld WIP 2 ¦ Earthing ¦ Nos ¦ 174 ¦ Nos ¦ 156 ¦ 330 ¦ 170 ¦ 79 ¦ 249 ¦ 4 ¦ 77 ¦ 81 ¦ Erection WIP 3 ¦ Tower Erection ¦ Nos ¦ 174 ¦ Nos ¦ 156 ¦ 330 ¦ 154 ¦ 49 ¦ 203 ¦ 20 ¦ 107 ¦ 127 ¦ Power Line Crossing ¦ Foundation WIP 4 ¦ Tackwelding ¦ Nos ¦ 174 ¦ Nos ¦ 156 ¦ 330 ¦ 174 ¦ 156 ¦ 330 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tower schedule_07.03.25 | 675 | 32 | statutory_crossing, survey_soil, visual_l2 | R5: Sl.No ¦ AP No. ¦ Tower No. ¦ Type of Tower ¦ HT of Tower (Mtr) ¦ Span (Mtr) ¦ Cumulative Span (Mtr) ¦ Raised Chimney ¦ R.L (Mtr) ¦ Deviation Angle (Deg) ¦ Sum of Adjacent Spans ¦ Wind Span (Mtr) ¦ Weight Span in Mtr (Cold) ¦ Weight Span in Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) ¦ UTM Coordinates ¦ Crossing Details ¦ NAME OF VILLAGE ¦ NAME OF TEHSIL R51: 23 ¦ AP3 ¦ 3/0 ¦ DD45+18 ¦ 88.72 ¦ 8415.585000000001 ¦ 2 ¦ 280.384 ¦ 35° 45' 23"LT ¦ 645.826 ¦ 322.913 ¦ 167 ¦ 274 ¦ 440 ¦ 150 ¦ 249 ¦ 399 ¦ 617830.087 ¦ 3122276.028 ¦ With 2M RC/To Maintain Electrical Clearance | KEC INTERNATION LIMITED INDIA TRANSMISSION LINE PACKAGE TL02 FOR 765 kV D/C TRANSMISSION LINE ASSOCIATED WITH TRANSMISSION SYSTEM FOR EVACUATION OF POWER FROM REZ IN RAJASTHAN (20 GW) UNDER PH-III (PART-D) UNDER TBCB ROUTE. 765kV D/C SIKAR II – NARELA TRANSMISSION LINE PART II - CHECK SURVEY - AP0A TO GANTRY (WZ4) (WZ5) CLIENT : POWERGRID SIKAR-KHETRI TRANSMISSION LIMITED. [A 100% WHOLLY OWNED SUBSIDIARY OF POWERGRID] Sl.No ¦ AP No. ¦ Tower No. ¦ Type of Tower ¦ HT of Tower (Mtr) ¦ Span (Mtr) ¦ Cumulative Span (Mtr) ¦ Raised Chimney ¦ R.L (Mtr) ¦ Deviation Angle (Deg) ¦ Sum of Adjacent Spans ¦ Wind Span (Mtr) ¦ Weight Span in Mtr (Cold) ¦ Weight Span in Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) ¦ UTM Coordinates ¦ Crossing Details ¦ NAME OF VILLAGE ¦ NAME OF TEHSIL Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Easting ¦ Northing 1 ¦ AP0A ¦ 0A/0 (CT) ¦ DD60+3 ¦ 73.72 ¦ 282.288 ¦ 447.467 ¦ 223.7335 ¦ 210 ¦ 210 ¦ 214 ¦ 214 ¦ 611960.328 ¦ 3117570.879 447.467 ¦ METAL ROAD | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | ERT | 333 | 18 | commercial, earthing_tack, summary_status | R1: EARTHING ¦ 163 ¦ 2026-05-20 00:00:00 R2: Sl. No. ¦ Location Number ¦ Tower Type ¦ Earthing Type ¦ Date of Earthing ¦ Agency ¦ Status ¦ RA Bill No. ¦ Remarks ¦ Revenue ¦ 6901 R3: 1 ¦ 0A/0 (CT) ¦ DD60+3 ¦ Pipe Type ¦ 2024-12-25 00:00:00 ¦ Shyam Ent ¦ Completed R4: 2 ¦ 0B/0 ¦ DC1+6 ¦ Pipe Type ¦ 2024-11-09 00:00:00 ¦ Shyam ¦ Completed R5: 3 ¦ 0B/1 ¦ DA+3 ¦ Pipe Type ¦ 2024-10-23 00:00:00 ¦ NV Infra ¦ Completed | EARTHING ¦ 163 ¦ 2026-05-20 00:00:00 Sl. No. ¦ Location Number ¦ Tower Type ¦ Earthing Type ¦ Date of Earthing ¦ Agency ¦ Status ¦ RA Bill No. ¦ Remarks ¦ Revenue ¦ 6901 1 ¦ 0A/0 (CT) ¦ DD60+3 ¦ Pipe Type ¦ 2024-12-25 00:00:00 ¦ Shyam Ent ¦ Completed 2 ¦ 0B/0 ¦ DC1+6 ¦ Pipe Type ¦ 2024-11-09 00:00:00 ¦ Shyam ¦ Completed 3 ¦ 0B/1 ¦ DA+3 ¦ Pipe Type ¦ 2024-10-23 00:00:00 ¦ NV Infra ¦ Completed 4 ¦ 0B/2 ¦ DA+3 ¦ Pipe Type ¦ 2024-10-03 00:00:00 ¦ NV Infra ¦ Completed 5 ¦ 0B/3 ¦ DA+6 ¦ Pipe Type ¦ 2024-10-10 00:00:00 ¦ NV Infra ¦ Completed 6 ¦ 0C/0 ¦ DD45+0 ¦ Pipe Type ¦ 2024-10-26 00:00:00 ¦ NV Infra ¦ Completed | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | ERECTION COMPILED | 346 | 15 | commercial, earthing_tack, erection, project_details, summary_status | R1: TOWER ERECTION ¦ Completed ¦ 203 ¦ WIP ¦ 11 ¦ 2026-05-20 00:00:00 R2: S.No ¦ Location No ¦ Tower Type ¦ Tower Weight ¦ Starting Date ¦ Completion Date ¦ Gang Name ¦ Status ¦ Remarks ¦ Tower Tightening ¦ Tack Welding ¦ Report Status ¦ RA Bill No. ¦ Revenue (in Cr) R3: 1 ¦ 0A/0 (CT) ¦ DD60+3 ¦ 87.02134 ¦ 2025-01-27 00:00:00 ¦ 2025-02-12 00:00:00 ¦ Radha Enterprises ¦ Completed ¦ Done R4: 2 ¦ 0B/0 ¦ DC1+6 ¦ 72.474 ¦ 2025-09-23 00:00:00 ¦ 2025-11-05 00:00:00 ¦ Infinidea ¦ Completed ¦ Done R5: 3 ¦ 0B/1 ¦ DA+3 ¦ 37.931088 ¦ 2025-02-19 00:00:00 ¦ 2025-03-04 00:00:00 ¦ Pinki Devi ¦ Completed ¦ Done | TOWER ERECTION ¦ Completed ¦ 203 ¦ WIP ¦ 11 ¦ 2026-05-20 00:00:00 S.No ¦ Location No ¦ Tower Type ¦ Tower Weight ¦ Starting Date ¦ Completion Date ¦ Gang Name ¦ Status ¦ Remarks ¦ Tower Tightening ¦ Tack Welding ¦ Report Status ¦ RA Bill No. ¦ Revenue (in Cr) 1 ¦ 0A/0 (CT) ¦ DD60+3 ¦ 87.02134 ¦ 2025-01-27 00:00:00 ¦ 2025-02-12 00:00:00 ¦ Radha Enterprises ¦ Completed ¦ Done 2 ¦ 0B/0 ¦ DC1+6 ¦ 72.474 ¦ 2025-09-23 00:00:00 ¦ 2025-11-05 00:00:00 ¦ Infinidea ¦ Completed ¦ Done 3 ¦ 0B/1 ¦ DA+3 ¦ 37.931088 ¦ 2025-02-19 00:00:00 ¦ 2025-03-04 00:00:00 ¦ Pinki Devi ¦ Completed ¦ Done 4 ¦ 0B/2 ¦ DA+3 ¦ 37.931088 ¦ 2024-12-04 00:00:00 ¦ 2024-12-23 00:00:00 ¦ Radha Enterprises ¦ Completed ¦ Done 5 ¦ 0B/3 ¦ DA+6 ¦ 43.804424 ¦ 2025-01-19 00:00:00 ¦ 2025-01-27 00:00:00 ¦ Radha Enterprises ¦ Completed ¦ Done 6 ¦ 0C/0 ¦ DD45+0 ¦ 73.244548 ¦ 2025-11-15 00:00:00 ¦ 2025-12-08 00:00:00 ¦ Dhruv Enterprises ¦ Completed ¦ Done | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing Stretch Readiness | 427 | 20 | project_details, stretch_readiness, stringing, summary_status, visual_l2 | R3: LINE NAME: 765KV Sikar II- Narela TL ¦ Balance ¦ 0.3400000000000176 R9: Total ¦ Ready ¦ Balance R14: Activity ¦ Foundation ¦ Tower Erection ¦ Stringing R15: Sl. No. ¦ Loc. No. ¦ Type of Tower ¦ Span (in mtrs.) ¦ Work Portion ¦ Foundation ¦ Plan for the Month ¦ TSE/ Manual ¦ Erection ¦ Stringing ¦ Section Length ¦ Plan for the Month ¦ Gang Details ¦ No Of Towers ¦ Completed ¦ Balance ¦ Balance R18: 1 ¦ 0A/0 (CT) ¦ DD60+3 ¦ WZ-4 ¦ Completed ¦ Mar ¦ Manual ¦ Completed ¦ 0A/0-0B/0 ¦ 447.467 ¦ Dec'25 ¦ M-1 ¦ 2 ¦ 2 ¦ 0F to 0G | KEC INTERNATIONAL LIMITED CONSTRUCTION PLAN UPTO COMPLETION ¦ Completed LINE NAME: 765KV Sikar II- Narela TL ¦ Balance ¦ 0.3400000000000176 Contractual Completion: 31 May'25 ¦ Expected Completion: May'26 -0.3400000000000176 765KV D/C HEXA SIKAR II- NARELA TL (PGCIL PROJECT) ¦ BALANCE WORK COMPLETION PLAN Summary (122.07Km) | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Project details | 24 | 11 | project_details | R1: Project Code ¦ Project Name ¦ Client Name ¦ LOA start date ¦ LOA end Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manager ¦ Section Incharge ¦ Supervisor/Engineer | Project Code ¦ Project Name ¦ Client Name ¦ LOA start date ¦ LOA end Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manager ¦ Section Incharge ¦ Supervisor/Engineer TA-419 ¦ 765 KV D/C Sikar II - Narela TL02 ¦ Power Grid Corporation of India ¦ 2024-02-06 00:00:00 ¦ 2025-05-05 00:00:00 ¦ Mr.Suraj Chaudhary ¦ Mr. Sanjay Gupta ¦ Mr. Tushar Grover ¦ Mr. Shashi Bhusan ¦ Mr. Shiv Kumar Singh ¦ Mr. Naval Singh Mr. Hasibur Rehman ¦ Mr.Ravindra nath Tyagi ¦ Mr. Sunil Kumar Shetty Mr. Yogendra Singh Mr. PD Sharma Mr. Bishswar Behera Mr. Suresh Ram Mr. Manoj Yadav | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Detailed Survey | 51 | 36 | summary_status, survey_soil, visual_l2 | R4: Daily Progress - Detailed Survey ¦ as on ¦ 2026-05-20 00:00:00 ¦ Daily Progress - Check Survey ¦ 2026-05-20 00:00:00 ¦ Data Sent to Engineering for Profiling ¦ Submission) ¦ Approval R5: Sr ¦ Date ¦ Location ¦ Completed Length (Km) ¦ Cummulative Completed Length (Km) ¦ Remarks ¦ Date ¦ Location ¦ Completed Length (Km) ¦ Cummulative Completed Length (Km) ¦ Remarks ¦ Sr ¦ Date ¦ Location ¦ Length (Km) ¦ Cummulative Length (Km) ¦ Remarks ¦ Date ¦ Location ¦ Submitted Length (Km) R6: From ¦ To ¦ From ¦ To ¦ From ¦ To ¦ From ¦ To ¦ From ¦ To R20: 14 ¦ 2024-05-15 00:00:00 ¦ AP56 ¦ AP62 ¦ 2.947 ¦ 73.41 ¦ 2024-06-07 00:00:00 ¦ 6/0 ¦ 1/0 ¦ 5.635 ¦ 36.103 ¦ Check Survey (Plan Profile & Tower Schedule): R22: 16 ¦ 2024-05-23 00:00:00 ¦ AP63 ¦ AP64 ¦ 2.4459999999999997 ¦ 80.856 ¦ 2024-06-10 00:00:00 ¦ 36/0 ¦ 37/0 ¦ 4.407 ¦ 42.241 ¦ Date ¦ Location ¦ Submitted in (Km) ¦ Reviewed Date ¦ Date ¦ Location ¦ Approved in (Km) ¦ Remarks | KEC International Ltd 765KV D/C Sikar II - Narela TL02 ¦ 27.45 Detailed Survey (Plan Profile & Tower Schedule): Daily Progress - Detailed Survey ¦ as on ¦ 2026-05-20 00:00:00 ¦ Daily Progress - Check Survey ¦ 2026-05-20 00:00:00 ¦ Data Sent to Engineering for Profiling ¦ Submission) ¦ Approval Sr ¦ Date ¦ Location ¦ Completed Length (Km) ¦ Cummulative Completed Length (Km) ¦ Remarks ¦ Date ¦ Location ¦ Completed Length (Km) ¦ Cummulative Completed Length (Km) ¦ Remarks ¦ Sr ¦ Date ¦ Location ¦ Length (Km) ¦ Cummulative Length (Km) ¦ Remarks ¦ Date ¦ Location ¦ Submitted Length (Km) From ¦ To ¦ From ¦ To ¦ From ¦ To ¦ From ¦ To ¦ From ¦ To 1 ¦ 2024-04-25 00:00:00 ¦ AP38 ¦ AP42 ¦ 12.701 ¦ 12.701 ¦ 2024-05-11 00:00:00 ¦ 18/0 ¦ 20/0 ¦ 2.679 ¦ 2.679 ¦ 1 ¦ 2024-05-01 00:00:00 ¦ AP14 ¦ AP20 ¦ 5.469 ¦ 5.469 ¦ 2024-05-03 00:00:00 ¦ KEC Engineering to Site Team and to PGCIL ¦ 2024-05-03 00:00:00 2 ¦ 2024-04-26 00:00:00 ¦ AP42 ¦ AP44 ¦ 2.842 ¦ 15.543000000000001 ¦ 2024-05-12 00:00:00 ¦ 17/0 ¦ 18/0 ¦ 1.083 ¦ 3.7619999999999996 ¦ 2 ¦ 2024-05-03 00:00:00 ¦ AP20 ¦ AP38 ¦ 20.436 ¦ 25.905 ¦ 2024-05-05 00:00:00 ¦ KEC Engineering to Site Team and to PGCIL ¦ 2024-05-05 00:00:00 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Supply | 111 | 27 | opgw_accessories, supply, visual_l2 | R3: Sr ¦ Description ¦ UOM ¦ Estimated Qty ¦ L2 Sch till APR'25 ¦ Received ¦ % ¦ Balance ¦ Remarks R6: 1 ¦ Stubs ¦ Nos ¦ 330 ¦ 322 ¦ 328 ¦ 0.9939393939393939 ¦ 2 R8: 3 ¦ Conductor ¦ KM ¦ 4432 ¦ 4370 ¦ 4369 ¦ 0.9857851985559567 ¦ 63 R9: 4 ¦ Insulator ¦ Nos ¦ 18483 ¦ 19440 ¦ 17864 ¦ 0.9665097657306714 ¦ 619 R11: 6 ¦ OPGW H/W fittings ¦ % ¦ 1 ¦ 1 ¦ 0.1 ¦ 0.1 ¦ 0.9 | 765kV D/C Sikar II - Narela Transmission Line (TL02) ¦ as on ¦ 2026-05-21 00:00:00 ¦ SCHEME FOLLOWED: Sr ¦ Description ¦ UOM ¦ Estimated Qty ¦ L2 Sch till APR'25 ¦ Received ¦ % ¦ Balance ¦ Remarks Qty. ¦ Received ¦ Qty. I ¦ SUPPLY 1 ¦ Stubs ¦ Nos ¦ 330 ¦ 322 ¦ 328 ¦ 0.9939393939393939 ¦ 2 2 ¦ Towers ¦ Nos ¦ 330 ¦ 322 ¦ 325 ¦ 0.9848484848484849 ¦ 5 3 ¦ Conductor ¦ KM ¦ 4432 ¦ 4370 ¦ 4369 ¦ 0.9857851985559567 ¦ 63 4 ¦ Insulator ¦ Nos ¦ 18483 ¦ 19440 ¦ 17864 ¦ 0.9665097657306714 ¦ 619 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stock Details | 23 | 5 | supply | R4: Sr.No ¦ Description ¦ Unit ¦ Balance Qty ¦ Remark | 765kV D/C Sikar II - Narela Transmission Line (TL02) Store - Stock Details as on ¦ 2026-05-20 00:00:00 Sr.No ¦ Description ¦ Unit ¦ Balance Qty ¦ Remark 1 ¦ Cement ¦ Bag ¦ 3163 2 ¦ Re-Bar-8 mm ¦ MT ¦ 7.331 3 ¦ Re-Bar-10 mm ¦ MT ¦ 85.604 4 ¦ Re-Bar-12 mm ¦ MT ¦ 96.956 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | PGCIL | 19 | 13 | project_details, row_hindrance, summary_status, survey_soil | R6: Sr ¦ Particulars ¦ Unit ¦ LOA Ǫty ¦ Estimated Qty ¦ Completed Quantity ¦ In_Progress ¦ Balance ¦ Forest/ROW ¦ Gangs ¦ Remark R14: 3 ¦ Foundations ¦ Nos ¦ 322 ¦ 307 ¦ 2 ¦ 2 ¦ 2 ¦ 305 ¦ 2 ¦ 1 R15: 4 ¦ Tower Earthing ¦ Nos ¦ 322 ¦ 307 ¦ 2 ¦ 2 ¦ 305 R16: 5 ¦ Tower Erection ¦ Nos ¦ 322 ¦ 307 ¦ 307 R17: 6 ¦ Tack Welding ¦ Nos ¦ 322 ¦ 307 ¦ 307 | POWERGRID SIKAR KHETRI TRANSMISSION LIMITED (100% subsidiary of Power Grid Corporation of India Limited) Project : 765kV D/C Sikar II - Narela Transimission Line (TW02) Executing Agency : KEC International Ltd Project Start Date : 06-Feb-24. Contractual Completion Date: 05-May-25. EOT: NA 2026-05-20 00:00:00 Sr ¦ Particulars ¦ Unit ¦ LOA Ǫty ¦ Estimated Qty ¦ Completed Quantity ¦ In_Progress ¦ Balance ¦ Forest/ROW ¦ Gangs ¦ Remark Previous Month ¦ This Month ¦ Cummulatie 1 ¦ Detail Survey | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 |  | 17 | 4 | erection, foundation |  | FDNEREERTINSRSFS FDNWIPEREERTINSRSFS FDNComEREERTINSRSFS FDNComEREERTComINSRSFS FDNComEREWIPERTINSRSFS FDNComEREWIPERTComINSRSFS FDNComEREComERTINSRSFS FDNComEREComERTComINSRSFS | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 |  | 549 | 16 | erection, foundation, summary_status | R5: SL NO. ¦ SPAN ¦ LOC NO ¦ TOWER ¦ SPAN LENGTH (Mtr.) ¦ FDN ¦ ERE ¦ ERT ¦ INS ¦ RS ¦ FS ¦ DPR R7: #REF! ¦ #REF! ¦ #REF! ¦ Com ¦ Com ¦ FDNComEREComERTINSRSFS R9: 1 ¦ #REF! ¦ #REF! ¦ #REF! ¦ FDNEREERTINSRSFS R11: 2 ¦ #REF! ¦ #REF! ¦ #REF! ¦ FDNEREERTINSRSFS R13: 3 ¦ #REF! ¦ #REF! ¦ #REF! ¦ FDNEREERTINSRSFS | SL NO. ¦ SPAN ¦ LOC NO ¦ TOWER ¦ SPAN LENGTH (Mtr.) ¦ FDN ¦ ERE ¦ ERT ¦ INS ¦ RS ¦ FS ¦ DPR #REF! ¦ #REF! ¦ #REF! ¦ Com ¦ Com ¦ FDNComEREComERTINSRSFS #REF! ¦ #REF! ¦ #REF! ¦ #REF! 1 ¦ #REF! ¦ #REF! ¦ #REF! ¦ FDNEREERTINSRSFS #REF! ¦ #REF! ¦ #REF! ¦ #REF! 2 ¦ #REF! ¦ #REF! ¦ #REF! ¦ FDNEREERTINSRSFS #REF! ¦ #REF! ¦ #REF! ¦ #REF! 3 ¦ #REF! ¦ #REF! ¦ #REF! ¦ FDNEREERTINSRSFS | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | dont change | 332 | 5 |  | R1: Sr ¦ Loc ¦ Tower Type ¦ Span Length | Sr ¦ Loc ¦ Tower Type ¦ Span Length 1 ¦ 0A/0 (CT) ¦ DD60+3 ¦ 447.467 2 ¦ 0B/0 ¦ DC1+6 ¦ 362.533 3 ¦ 0B/1 ¦ DA+3 ¦ 420 4 ¦ 0B/2 ¦ DA+3 ¦ 395 5 ¦ 0B/3 ¦ DA+6 ¦ 418.563 6 ¦ 0C/0 ¦ DD45+0 ¦ 379.997 7 ¦ 0C/1 ¦ DA+3 ¦ 413.34 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | TOWER ABSTRACT | 336 | 47 |  | R4: SLNO. ¦ LOCATION ¦ TOWER TYPE ¦ SL NO. ¦ TOWER TYPE ¦ TOWER QUANTITY ¦ Total Quantity ¦ SL NO. ¦ TOWER TYPE ¦ TOWER QUANTITY ¦ Total Quantity ¦ SL NO. ¦ TOWER TYPE ¦ SL No ¦ Tower Type ¦ Per Tower Unit Weight (As per approved BOM) | OVERALL TOWER LOCATIONS AS PER LATEST ESTIMATE ¦ NUMBER OF TOWER TYPEWISE ¦ NUMBER OF TOWER TYPEWISE ¦ WEIGHT OF TOWER TYPEWISE ¦ WEIGHT OF TOWER TYPEWISE(WZ4) SLNO. ¦ LOCATION ¦ TOWER TYPE ¦ SL NO. ¦ TOWER TYPE ¦ TOWER QUANTITY ¦ Total Quantity ¦ SL NO. ¦ TOWER TYPE ¦ TOWER QUANTITY ¦ Total Quantity ¦ SL NO. ¦ TOWER TYPE ¦ SL No ¦ Tower Type ¦ Per Tower Unit Weight (As per approved BOM) 1 ¦ 0A/0 (CT) ¦ DD60+3 ¦ 1 ¦ DA-3 ¦ 15 ¦ 116 ¦ 1 ¦ DA-3 ¦ 15 ¦ 116 ¦ 1 ¦ DA-3 ¦ HT Steel (MT) ¦ Mild Steel (MT) ¦ PW (MT) ¦ Bolts & Nuts (MT) ¦ Bolt ¦ Total Weight of Tower (MT) ¦ Construction Revenue 2 ¦ 0B/0 ¦ DC1+6 ¦ 2 ¦ DA-1.5 ¦ 12 ¦ 2 ¦ DA-1.5 ¦ 12 ¦ 2 ¦ DA-1.5 ¦ Tower with extensions Up to +9M ¦ 5DB2+0 ¦ 64.482237 3 ¦ 0B/1 ¦ DA+3 ¦ 3 ¦ DA+0 ¦ 35 ¦ 3 ¦ DA+0 ¦ 35 ¦ 3 ¦ DA+0 ¦ 1 ¦ DA+0 ¦ 24.697672 ¦ 9.926688 ¦ 0.030435 ¦ 1.504961 ¦ 1.535396 ¦ 36.159756 ¦ 336894.66109104 4 ¦ 0B/2 ¦ DA+3 ¦ 4 ¦ DA+1.5 ¦ 14 ¦ 4 ¦ DA+1.5 ¦ 14 ¦ 4 ¦ DA+1.5 ¦ 2 ¦ DA+3 ¦ 25.51881 ¦ 10.831932 ¦ 0.030628999999999997 ¦ 1.5497169999999998 ¦ 1.5803459999999998 ¦ 37.931087999999995 ¦ 353397.87792192 5 ¦ 0B/3 ¦ DA+6 ¦ 5 ¦ DA+3 ¦ 24 ¦ 5 ¦ DA+3 ¦ 24 ¦ 5 ¦ DA+3 ¦ 3 ¦ DA+6 ¦ 29.451642 ¦ 12.621458 ¦ 0.030759 ¦ 1.700565 ¦ 1.731324 ¦ 43.804424 ¦ 408118.80970016 6 ¦ 0C/0 ¦ DD45+0 ¦ 6 ¦ DA+6 ¦ 12 ¦ 6 ¦ DA+6 ¦ 12 ¦ 6 ¦ DA+6 ¦ 4 ¦ DA+9 ¦ 30.247434 ¦ 13.658548000000001 ¦ 0.031055 ¦ 1.7599850000000001 ¦ 1.7910400000000002 ¦ 45.697022000000004 ¦ 425751.84245048004 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Pkg 2_Foundation | 338 | 172 | foundation, project_details, row_hindrance, summary_status, visual_l2 | R3: Master S No ¦ District ¦ Tehsil ¦ Village ¦ Loc No ¦ Package ¦ Tower Type ¦ Foundation Completion Satus (Completed,No,WIP) ¦ Foundation Start Date ¦ Foundation End Date ¦ Gang Allocated ¦ L3 schedule (Dec 25) ¦ Gang Manpower ¦ Foundation Location Current Status - 21 May 2026 ¦ Foundation Location Yesterday's Status - 20 May 2026 ¦ POWERGRID Employee / Contact No ¦ RoW (Yes/No) ¦ Front available ¦ R4: 1 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0A/0 ¦ TL02 ¦ DD60+3 ¦ Completed ¦ 2024-12-02 00:00:00 ¦ 2024-12-23 00:00:00 ¦ Shyam Ent ¦ 21 R5: 2 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/0 ¦ TL02 ¦ DC1+6 ¦ Completed ¦ 2024-10-20 00:00:00 ¦ 2024-11-08 00:00:00 ¦ Shyam Ent ¦ 19 R6: 3 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/1 ¦ TL02 ¦ DA+3 ¦ Completed ¦ 2024-09-18 00:00:00 ¦ 2024-10-22 00:00:00 ¦ NV Infra ¦ 34 R7: 4 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/2 ¦ TL02 ¦ DA+3 ¦ Completed ¦ 2024-09-11 00:00:00 ¦ 2024-09-28 00:00:00 ¦ NV Infra ¦ 17 | Master S No ¦ District ¦ Tehsil ¦ Village ¦ Loc No ¦ Package ¦ Tower Type ¦ Foundation Completion Satus (Completed,No,WIP) ¦ Foundation Start Date ¦ Foundation End Date ¦ Gang Allocated ¦ L3 schedule (Dec 25) ¦ Gang Manpower ¦ Foundation Location Current Status - 21 May 2026 ¦ Foundation Location Yesterday's Status - 20 May 2026 ¦ POWERGRID Employee / Contact No ¦ RoW (Yes/No) ¦ Front available ¦ Surface Dewatering ¦ Boring Status 1 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0A/0 ¦ TL02 ¦ DD60+3 ¦ Completed ¦ 2024-12-02 00:00:00 ¦ 2024-12-23 00:00:00 ¦ Shyam Ent ¦ 21 2 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/0 ¦ TL02 ¦ DC1+6 ¦ Completed ¦ 2024-10-20 00:00:00 ¦ 2024-11-08 00:00:00 ¦ Shyam Ent ¦ 19 3 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/1 ¦ TL02 ¦ DA+3 ¦ Completed ¦ 2024-09-18 00:00:00 ¦ 2024-10-22 00:00:00 ¦ NV Infra ¦ 34 4 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/2 ¦ TL02 ¦ DA+3 ¦ Completed ¦ 2024-09-11 00:00:00 ¦ 2024-09-28 00:00:00 ¦ NV Infra ¦ 17 5 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/3 ¦ TL02 ¦ DA+6 ¦ Completed ¦ 2024-09-30 00:00:00 ¦ 2024-10-07 00:00:00 ¦ NV Infra ¦ 7 6 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0C/0 ¦ TL02 ¦ DD45+0 ¦ Completed ¦ 2024-10-07 00:00:00 ¦ 2024-10-25 00:00:00 ¦ NV Infra ¦ 18 7 ¦ Mahendragarh ¦ Mahendragarh ¦ Nanagwas ¦ 0C/1 ¦ TL02 ¦ DA+3 ¦ Completed ¦ 2024-10-19 00:00:00 ¦ 2024-10-25 00:00:00 ¦ TDCL ¦ 6 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Foundation Daily Progresss | 1442 | 192 | foundation, summary_status, supply | R2: Sl. No ¦ Distirct ¦ Village ¦ Loc ¦ Type ¦ Classification ¦ Excavation Volume ¦ M10 ¦ M20 ¦ Steel(MT) ¦ Stub(MT) ¦ Present Status ¦ L3 Month ¦ Start Date ¦ End Date ¦ Agency ¦ Status ¦ 2025-12-27 00:00:00 ¦ 2025-12-28 00:00:00 ¦ 2025-12-29 00:00:00 R3: 1 ¦ 13/0 ¦ DD60+3 ¦ 00:00:00 ¦ 2026-03-20 00:00:00 ¦ D&V ¦ Completed R4: 2 ¦ 14/0 ¦ DD60+0 ¦ 00:00:00 ¦ 2026-01-18 00:00:00 ¦ GRD 1 ¦ Completed R5: 3 ¦ 14/1 ¦ DA+0 ¦ 00:00:00 ¦ 2026-04-23 00:00:00 ¦ GRD 1 ¦ Completed R6: 4 ¦ 32/0 ¦ DD60+3 ¦ 00:00:00 ¦ 2026-03-25 00:00:00 ¦ Ravindra ¦ Completed | Foundation Daily Progress Sl. No ¦ Distirct ¦ Village ¦ Loc ¦ Type ¦ Classification ¦ Excavation Volume ¦ M10 ¦ M20 ¦ Steel(MT) ¦ Stub(MT) ¦ Present Status ¦ L3 Month ¦ Start Date ¦ End Date ¦ Agency ¦ Status ¦ 2025-12-27 00:00:00 ¦ 2025-12-28 00:00:00 ¦ 2025-12-29 00:00:00 1 ¦ 13/0 ¦ DD60+3 ¦ 00:00:00 ¦ 2026-03-20 00:00:00 ¦ D&V ¦ Completed 2 ¦ 14/0 ¦ DD60+0 ¦ 00:00:00 ¦ 2026-01-18 00:00:00 ¦ GRD 1 ¦ Completed 3 ¦ 14/1 ¦ DA+0 ¦ 00:00:00 ¦ 2026-04-23 00:00:00 ¦ GRD 1 ¦ Completed 4 ¦ 32/0 ¦ DD60+3 ¦ 00:00:00 ¦ 2026-03-25 00:00:00 ¦ Ravindra ¦ Completed 5 ¦ 33/0 ¦ DD60+0 ¦ 00:00:00 ¦ 2026-02-04 00:00:00 ¦ Utkarsh Const ¦ Completed 6 ¦ 36/3 ¦ DA+6 ¦ 00:00:00 ¦ 2025-12-24 00:00:00 ¦ GRD 1 ¦ Completed ¦ Dewatering ¦ Dewatering ¦ Pit Marking ¦ Dewatering ¦ Dewatering WL upto 4.5 ft ¦ No Work ¦ Dewatering WL upto 5 ft ¦ Stub Setting ¦ Stub Setting ¦ B pit Frustum ¦ Pit A Frustum, Pit B Chimney ¦ Pit C and D Chimney | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection Daily Progress | 1048576 | 400 | erection, summary_status, supply | R2: Sl No. ¦ Location No ¦ Tower Type ¦ Tower Weight ¦ Start Date ¦ End Date ¦ Agency ¦ Status ¦ Cumm ¦ Cumm ¦ 2025-12-27 00:00:00 ¦ MT ¦ 2025-12-28 00:00:00 ¦ MT ¦ 2025-12-29 00:00:00 ¦ MT ¦ 2025-12-30 00:00:00 ¦ MT ¦ 2025-12-31 00:00:00 ¦ MT R3: 1 ¦ 2/0 ¦ DB2+18 ¦ 58.882297 ¦ 2026-02-13 00:00:00 ¦ 2026-03-15 00:00:00 ¦ Dhruv Enterprises 1 ¦ Completed R4: 2 ¦ 3/0 ¦ DD45+18 ¦ 78.777228 ¦ 2026-03-21 00:00:00 ¦ 2026-03-30 00:00:00 ¦ Madhu Sah ¦ Completed R5: 3 ¦ 7/0 ¦ DB1+3 ¦ 57.963 ¦ 2025-12-24 00:00:00 ¦ 2026-01-31 00:00:00 ¦ Bhairo Mahato ¦ Completed ¦ Material Shifting ¦ - ¦ Material Shifting ¦ - ¦ Ground Assembly ¦ #REF! ¦ No Work ¦ Second Section Completed ¦ 6 ¦ Third Section U/P ¦ 2 ¦ Third Section U/P R7: 5 ¦ 9/0 ¦ DC2+9 ¦ 81.828 ¦ 2025-12-13 00:00:00 ¦ 2025-12-31 00:00:00 ¦ Bhairo Mahato ¦ Completed ¦ 40 ¦ 50 ¦ Third Section Completed ¦ 5 ¦ Bottom Section Completed ¦ 7 ¦ Top Body U/P ¦ 10 ¦ Tower Completed | Sl No. ¦ Location No ¦ Tower Type ¦ Tower Weight ¦ Start Date ¦ End Date ¦ Agency ¦ Status ¦ Cumm ¦ Cumm ¦ 2025-12-27 00:00:00 ¦ MT ¦ 2025-12-28 00:00:00 ¦ MT ¦ 2025-12-29 00:00:00 ¦ MT ¦ 2025-12-30 00:00:00 ¦ MT ¦ 2025-12-31 00:00:00 ¦ MT 1 ¦ 2/0 ¦ DB2+18 ¦ 58.882297 ¦ 2026-02-13 00:00:00 ¦ 2026-03-15 00:00:00 ¦ Dhruv Enterprises 1 ¦ Completed 2 ¦ 3/0 ¦ DD45+18 ¦ 78.777228 ¦ 2026-03-21 00:00:00 ¦ 2026-03-30 00:00:00 ¦ Madhu Sah ¦ Completed 3 ¦ 7/0 ¦ DB1+3 ¦ 57.963 ¦ 2025-12-24 00:00:00 ¦ 2026-01-31 00:00:00 ¦ Bhairo Mahato ¦ Completed ¦ Material Shifting ¦ - ¦ Material Shifting ¦ - ¦ Ground Assembly ¦ #REF! ¦ No Work ¦ Second Section Completed ¦ 6 ¦ Third Section U/P ¦ 2 ¦ Third Section U/P 4 ¦ 8/0 ¦ DB2+18 ¦ 58.882297 ¦ 00:00:00 ¦ 00:00:00 5 ¦ 9/0 ¦ DC2+9 ¦ 81.828 ¦ 2025-12-13 00:00:00 ¦ 2025-12-31 00:00:00 ¦ Bhairo Mahato ¦ Completed ¦ 40 ¦ 50 ¦ Third Section Completed ¦ 5 ¦ Bottom Section Completed ¦ 7 ¦ Top Body U/P ¦ 10 ¦ Tower Completed 6 ¦ 13/0 ¦ DD60+3 ¦ 83.134 ¦ 2026-05-10 00:00:00 ¦ 00:00:00 ¦ Madhu Sh ¦ WIP 7 ¦ 14/0 ¦ DD60+0 ¦ 83.134 ¦ 2026-04-30 00:00:00 ¦ 2026-05-12 00:00:00 ¦ Madhu Sah ¦ Completed | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Statutory | 91 | 13 | erection, foundation, statutory_crossing, stringing, summary_status | R1: Sr ¦ Crossing Span ¦ Type ¦ Description ¦ Under/ OH X-ing ¦ Approving Authority ¦ Proposal Status ¦ FDN Completed (0) ¦ Erection Completed (0) ¦ Stringing Completed ¦ Remarks R2: A ¦ Power Line Crossings ¦ PGCIL ¦ UTILITY R37: 5 ¦ AP85A/0 to AP86 ¦ Rly ¦ Double Track Ele. (Bahadurgarh-Rohtak) ¦ Over head ¦ Rly ¦ 2025-12-18 00:00:00 ¦ Hold ¦ HOCL CONSTRUCTION LEVEL UP & NEW HVPNL 220 KV LINE U/C R40: 1 ¦ 0H/0 to AP01 ¦ NH ¦ NH-152D Expressway Ambala-Narnaul Road ¦ Over head ¦ NHAI ¦ 2024-08-30 00:00:00 ¦ Approved R41: 2 ¦ AP53 to AP54 ¦ NH ¦ NH-334B Jhajjar-Charkhi Dadri Road ¦ Over head ¦ NHAI ¦ 2024-08-30 00:00:00 ¦ Awaited for NOC | Sr ¦ Crossing Span ¦ Type ¦ Description ¦ Under/ OH X-ing ¦ Approving Authority ¦ Proposal Status ¦ FDN Completed (0) ¦ Erection Completed (0) ¦ Stringing Completed ¦ Remarks A ¦ Power Line Crossings ¦ PGCIL ¦ UTILITY 1 ¦ 0F to 0G ¦ P/L ¦ 132KV S/C TL MGM-MKA ¦ Over head ¦ HVPN ¦ 2024-09-27 00:00:00 ¦ Approved 2 ¦ AP02 to AP03 ¦ P/L ¦ 220 KV D/C (DHA-DER) HVPN ¦ Over head ¦ HVPN ¦ 2024-09-27 00:00:00 ¦ Approved 3 ¦ AP08 to AP09 ¦ P/L ¦ 132 KV D/C (GUD-KML) HVPN TL ¦ Over head ¦ HVPN ¦ 2024-09-27 00:00:00 ¦ Approved 4 ¦ AP10 to AP11 ¦ P/L ¦ 132 KV D/C (DND-NGM) HVPN, 400 KV D/C (NIM-DHD) GPTL ¦ Over head ¦ HVPN ¦ 2024-09-27 00:00:00 ¦ Approved 5 ¦ AP10 to AP11 ¦ P/L ¦ 400 KV D/C (NIM-DHD) GPTL ¦ Over head ¦ GPTL ¦ 2024-09-27 00:00:00 ¦ Approved 6 ¦ AP15A to AP16 ¦ P/L ¦ 132 KV S/C Kanina-Dahina TL HVPN ¦ Over head ¦ HVPN ¦ 2024-09-27 00:00:00 ¦ Approved | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Pkg 2_Erection | 349 | 27 | erection, project_details, row_hindrance, summary_status | R2: Master S No ¦ District ¦ Tehsil ¦ Village ¦ Loc No ¦ Package ¦ Tower Type ¦ Erection Completion Satus (Completed,WIP,No ) ¦ Erection Start Date ¦ Erection End Date ¦ Gang Allocated ¦ Gang Manpower ¦ POWERGRID Employee/ Contact No ¦ ROW YES/NO ¦ Front available ¦ Tower Weight (Ton) ¦ Erection Location Current Status - 21 May 2026 ¦ Erection Lifted Current Status in MT - 21 May 2026 ¦ Erection Locat R3: 1 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0A/0 ¦ TL02 ¦ DD60+3 ¦ Completed ¦ 27-01-2025 ¦ 2025-12-02 00:00:00 ¦ Radha Enterprises ¦ 87.021 ¦ 87.021 R4: 2 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/0 ¦ TL02 ¦ DC1+6 ¦ Completed ¦ 23-09-2025 ¦ 2025-05-11 00:00:00 ¦ Infinidea ¦ 72.474 ¦ 72.474 R5: 3 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/1 ¦ TL02 ¦ DA+3 ¦ Completed ¦ 19-02-2025 ¦ 2025-04-03 00:00:00 ¦ Radha 2 ¦ 37.931 ¦ 37.931 R6: 4 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/2 ¦ TL02 ¦ DA+3 ¦ Completed ¦ 2024-04-12 00:00:00 ¦ 23-12-24 ¦ Radha Enterprises ¦ 37.931 ¦ 37.931 | ERECTION STATUS Master S No ¦ District ¦ Tehsil ¦ Village ¦ Loc No ¦ Package ¦ Tower Type ¦ Erection Completion Satus (Completed,WIP,No ) ¦ Erection Start Date ¦ Erection End Date ¦ Gang Allocated ¦ Gang Manpower ¦ POWERGRID Employee/ Contact No ¦ ROW YES/NO ¦ Front available ¦ Tower Weight (Ton) ¦ Erection Location Current Status - 21 May 2026 ¦ Erection Lifted Current Status in MT - 21 May 2026 ¦ Erection Location Yesterday's Status - 20 May 2026 ¦ Erection Lifted Current Status in MT - 20 May 2026 1 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0A/0 ¦ TL02 ¦ DD60+3 ¦ Completed ¦ 27-01-2025 ¦ 2025-12-02 00:00:00 ¦ Radha Enterprises ¦ 87.021 ¦ 87.021 2 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/0 ¦ TL02 ¦ DC1+6 ¦ Completed ¦ 23-09-2025 ¦ 2025-05-11 00:00:00 ¦ Infinidea ¦ 72.474 ¦ 72.474 3 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/1 ¦ TL02 ¦ DA+3 ¦ Completed ¦ 19-02-2025 ¦ 2025-04-03 00:00:00 ¦ Radha 2 ¦ 37.931 ¦ 37.931 4 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/2 ¦ TL02 ¦ DA+3 ¦ Completed ¦ 2024-04-12 00:00:00 ¦ 23-12-24 ¦ Radha Enterprises ¦ 37.931 ¦ 37.931 5 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0B/3 ¦ TL02 ¦ DA+6 ¦ Completed ¦ 19-01-2025 ¦ 27-01-25 ¦ Radha Enterprises ¦ 43.804 ¦ 43.804 6 ¦ Mahendragarh ¦ Mahendragarh ¦ Derolijat ¦ 0C/0 ¦ TL02 ¦ DD45+0 ¦ Completed ¦ 15-11-2025 ¦ 2025-08-12 00:00:00 ¦ GRD ¦ 73.245 ¦ 73.245 | repaired_defined_names (ValueError)
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | 2026-05-20 | Pkg2_Stringing | 157 | 35 | row_hindrance, statutory_crossing, stringing, summary_status | R2: S.No ¦ Pkg ¦ Section ¦ Section Length In Mtr ¦ Type of Section ¦ No. of Towers in the Section ¦ Status (WIP/COMP, N0) ¦ Status Readyness - 21 May 2026 ¦ State ¦ District ¦ Village ¦ Gang details ¦ ROW YES/NO ¦ Crop Compensation Disbursed YES/NO ¦ Land Compensation Disbursed YES/NO ¦ LT, 11 & 33kV Crossings ¦ Stringing Sections Current Status - 21 May 2026 ¦ Stringing Sections Yesterday Status - 20 | STRINGING WORKS ¦ 2026-05-21 00:00:00 S.No ¦ Pkg ¦ Section ¦ Section Length In Mtr ¦ Type of Section ¦ No. of Towers in the Section ¦ Status (WIP/COMP, N0) ¦ Status Readyness - 21 May 2026 ¦ State ¦ District ¦ Village ¦ Gang details ¦ ROW YES/NO ¦ Crop Compensation Disbursed YES/NO ¦ Land Compensation Disbursed YES/NO ¦ LT, 11 & 33kV Crossings ¦ Stringing Sections Current Status - 21 May 2026 ¦ Stringing Sections Yesterday Status - 20 May 2026 ¦ Whether any Gang available Yes/No ¦ Gang Type (PG/KEC) 1 ¦ TW02 ¦ 0A/0 - 0B/0 ¦ 0.447467 ¦ Manual ¦ 2 ¦ HARYANA ¦ Mahendragarh 2 ¦ TW02 ¦ 0B/0-0C/0 ¦ 1.596096 ¦ TSE ¦ 4 ¦ HARYANA ¦ Mahendragarh 3 ¦ TW02 ¦ 0C/0-0D/0 ¦ 0.793337 ¦ TSE ¦ 2 ¦ HARYANA ¦ Mahendragarh 4 ¦ TW02 ¦ 0D/0-0D/5 ¦ 2.099 ¦ TSE ¦ 5 ¦ HARYANA ¦ Mahendragarh 5 ¦ TW02 ¦ 0D/5-0E/0 ¦ 0.449716 ¦ Manual ¦ 1 ¦ HARYANA ¦ Mahendragarh 6 ¦ TW02 ¦ 0E/0-0F/0 ¦ 1.238287 ¦ TSE ¦ 3 ¦ HARYANA ¦ Mahendragarh | repaired_defined_names (ValueError)
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | Project Details | 14 | 12 | project_details | R2: Project Code ¦ Project Name ¦ Client Name ¦ LOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Supervisor/Engineer | Project Code ¦ Project Name ¦ Client Name ¦ LOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Supervisor/Engineer TA 421 ¦ 765KV D/C HEXA BIDAR PS - MAHESHWARAM (PG) TL ¦ Power Grid Bidar ¦ 2024-02-15 00:00:00 ¦ 2025-11-14 00:00:00 ¦ Mr. Bharath A D ¦ Mr.Arun Felbin ¦ Mr. Ajith Kumar ¦ Mr. Appala Naidu ¦ Mr.Godvin/Susanthpal ¦ Mr. Ramasish (PKG 01) ¦ Transmission Limited ¦ Mr. MadhuNair/Ram Asish ¦ Mr. Godvin John Mr. Susanthpal Mr. Srinivasan Mr. Bhim Mahto Mr. Ganesan Mr. Ballu Thakur | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | Master Sheet | 51 | 18 | project_details, summary_status, supply, survey_soil, visual_l2 | R3: Project Name ¦ 765kV D/C Bidar - Maheshwaram TL ¦ LOA Start Date ¦ 15.02.2024 ¦ PCH ¦ Mr. Arun Felbin R4: Client Name ¦ Power Grid Corporation of India Limited ¦ LOA End Date ¦ 14.11.2025 ¦ Regional Manager ¦ Mr. Ajith Kumar MG R7: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Balance ¦ L2 Plan for Current Month ¦ Plan for Current Month ¦ Progress for the Month ¦ Completed till Current Month ¦ Gap between Suppy & Cumm.L2 ¦ Remarks R13: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks R14: Detailed Survey ¦ kms ¦ 121.342 ¦ 121.342 ¦ 121.342 ¦ 121.342 ¦ 121.342 | Project Code ¦ TA-421 ¦ Date ¦ 2026-05-21 00:00:00 ¦ SBU Head ¦ Mr. Rajinder Gupta Project Name ¦ 765kV D/C Bidar - Maheshwaram TL ¦ LOA Start Date ¦ 15.02.2024 ¦ PCH ¦ Mr. Arun Felbin Client Name ¦ Power Grid Corporation of India Limited ¦ LOA End Date ¦ 14.11.2025 ¦ Regional Manager ¦ Mr. Ajith Kumar MG Revised End Date ¦ 15.06.2026 ¦ Planning Engineer ¦ Mr. Bharath A D ¦ Project Manger ¦ Mr. Appala Naidu Supply Status Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Balance ¦ L2 Plan for Current Month ¦ Plan for Current Month ¦ Progress for the Month ¦ Completed till Current Month ¦ Gap between Suppy & Cumm.L2 ¦ Remarks Stub ¦ No's Tower ¦ No's | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | ProGress Sheet | 1013 | 17 | erection, foundation, summary_status, survey_soil, visual_l2 | R3: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks R4: Detailed Survey ¦ kms ¦ 121.342 ¦ 121.342 ¦ 121.342 ¦ 121.342 ¦ 121.342 R5: Check Survey ¦ kms ¦ 121.342 ¦ 121.342 ¦ 121.342 ¦ 121.342 ¦ 121.342 R8: S.No ¦ Location No. ¦ Tower Type ¦ Classification ¦ Start Date ¦ Conc Volume ¦ Foundation Status ¦ End Date ¦ Gang Name ¦ Erection Status ¦ Gang Strength ¦ Remarks R9: 1 ¦ 24/4 ¦ 3DA+0 ¦ DFR ¦ 2024-05-03 00:00:00 ¦ 25.578 ¦ COMPLETED ¦ 2024-05-22 00:00:00 ¦ ATK CONSTRUCTIONS ¦ Completed ¦ 13 | Survey Status Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks Detailed Survey ¦ kms ¦ 121.342 ¦ 121.342 ¦ 121.342 ¦ 121.342 ¦ 121.342 Check Survey ¦ kms ¦ 121.342 ¦ 121.342 ¦ 121.342 ¦ 121.342 ¦ 121.342 PROGRESS - FDN & EREC S.No ¦ Location No. ¦ Tower Type ¦ Classification ¦ Start Date ¦ Conc Volume ¦ Foundation Status ¦ End Date ¦ Gang Name ¦ Erection Status ¦ Gang Strength ¦ Remarks 1 ¦ 24/4 ¦ 3DA+0 ¦ DFR ¦ 2024-05-03 00:00:00 ¦ 25.578 ¦ COMPLETED ¦ 2024-05-22 00:00:00 ¦ ATK CONSTRUCTIONS ¦ Completed ¦ 13 2 ¦ 24/2 ¦ 3DA+3 ¦ DFR ¦ 2024-05-23 00:00:00 ¦ 25.578 ¦ COMPLETED ¦ 2024-06-02 00:00:00 ¦ ATK CONSTRUCTIONS ¦ Completed ¦ 13 | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection Compiled | 311 | 12 | erection, project_details, summary_status | R2: SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Tower Tightening R3: 1 ¦ 25/4 ¦ 3DA+0 ¦ DFR ¦ 10-07-2024 ¦ 36.37 ¦ Completed ¦ 2024-07-19 00:00:00 ¦ Khatan ¦ 25 ¦ Completed ¦ Tower Erection activity Completed 0n Jan 2nd week 2026 R4: 2 ¦ 26/1 ¦ 3DA+0 ¦ DFR ¦ 18-07-2024 ¦ 36.37 ¦ Completed ¦ 2024-07-28 00:00:00 ¦ Khatan ¦ 25 ¦ Completed R5: 3 ¦ 26/4 ¦ 3DA+0 ¦ DFR ¦ 27-07-2024 ¦ 36.37 ¦ Completed ¦ 2024-08-03 00:00:00 ¦ Khatan ¦ 25 ¦ Completed R6: 4 ¦ 25/1 ¦ 3DA+0 ¦ DFR ¦ 02-08-2024 ¦ 36.37 ¦ Completed ¦ 2024-08-09 00:00:00 ¦ Khatan ¦ 25 ¦ Completed | Erection SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Tower Tightening 1 ¦ 25/4 ¦ 3DA+0 ¦ DFR ¦ 10-07-2024 ¦ 36.37 ¦ Completed ¦ 2024-07-19 00:00:00 ¦ Khatan ¦ 25 ¦ Completed ¦ Tower Erection activity Completed 0n Jan 2nd week 2026 2 ¦ 26/1 ¦ 3DA+0 ¦ DFR ¦ 18-07-2024 ¦ 36.37 ¦ Completed ¦ 2024-07-28 00:00:00 ¦ Khatan ¦ 25 ¦ Completed 3 ¦ 26/4 ¦ 3DA+0 ¦ DFR ¦ 27-07-2024 ¦ 36.37 ¦ Completed ¦ 2024-08-03 00:00:00 ¦ Khatan ¦ 25 ¦ Completed 4 ¦ 25/1 ¦ 3DA+0 ¦ DFR ¦ 02-08-2024 ¦ 36.37 ¦ Completed ¦ 2024-08-09 00:00:00 ¦ Khatan ¦ 25 ¦ Completed 5 ¦ 26/2 ¦ 3DA+0 ¦ DFR ¦ 09-08-2024 ¦ 36.37 ¦ Completed ¦ 2024-08-14 00:00:00 ¦ Khatan ¦ 25 ¦ Completed 6 ¦ 26/3 ¦ 3DA+0 ¦ DFR ¦ 2024-08-16 00:00:00 ¦ 36.37 ¦ Completed ¦ 2024-08-18 00:00:00 ¦ Khatan ¦ 25 ¦ Completed | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing Compiled | 79 | 24 | project_details, stretch_readiness, stringing, summary_status, supply | R3: S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hosting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name R4: 1 ¦ Telangana ¦ 23/0 ¦ 24/0 ¦ 23/0,1,2,3 & 24/0 ¦ 1.826 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-02-12 00:00:00 ¦ 2025-02-16 00:00:00 ¦ 1.826 ¦ 2025-02-27 00:00:00 ¦ 2025-03-04 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 1.826 ¦ Completed ¦ M R Constructions R5: 2 ¦ Telangana ¦ 24/0 ¦ 25/0 ¦ 24/0,1,2,3,4,5,6,7,8 & 25/0 ¦ 3.406 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-02-24 00:00:00 ¦ 2025-03-04 00:00:00 ¦ 3.406 ¦ 2025-03-09 00:00:00 ¦ 2025-03-16 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 3.406 ¦ Completed ¦ M R Constructions R6: 3 ¦ Telangana ¦ 25/0 ¦ 26/0 ¦ 25/0,1,2,3,4,5 & 26/0 ¦ 2.279 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-03-08 00:00:00 ¦ 2025-03-13 00:00:00 ¦ 2.279 ¦ 2025-03-24 00:00:00 ¦ 2025-03-29 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 2.279 ¦ Completed ¦ M R Constructions R7: 4 ¦ Telangana ¦ 26/0 ¦ 27/0 ¦ 26/0,1,2,3,4 & 27/0 ¦ 1.914 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-03-23 00:00:00 ¦ 2025-03-28 00:00:00 ¦ 1.914 ¦ 2025-04-18 00:00:00 ¦ 2025-04-20 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 1.914 ¦ Completed ¦ M R Constructions | Number of TSE ¦ 2 S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hosting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name 1 ¦ Telangana ¦ 23/0 ¦ 24/0 ¦ 23/0,1,2,3 & 24/0 ¦ 1.826 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-02-12 00:00:00 ¦ 2025-02-16 00:00:00 ¦ 1.826 ¦ 2025-02-27 00:00:00 ¦ 2025-03-04 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 1.826 ¦ Completed ¦ M R Constructions 2 ¦ Telangana ¦ 24/0 ¦ 25/0 ¦ 24/0,1,2,3,4,5,6,7,8 & 25/0 ¦ 3.406 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-02-24 00:00:00 ¦ 2025-03-04 00:00:00 ¦ 3.406 ¦ 2025-03-09 00:00:00 ¦ 2025-03-16 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 3.406 ¦ Completed ¦ M R Constructions 3 ¦ Telangana ¦ 25/0 ¦ 26/0 ¦ 25/0,1,2,3,4,5 & 26/0 ¦ 2.279 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-03-08 00:00:00 ¦ 2025-03-13 00:00:00 ¦ 2.279 ¦ 2025-03-24 00:00:00 ¦ 2025-03-29 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 2.279 ¦ Completed ¦ M R Constructions 4 ¦ Telangana ¦ 26/0 ¦ 27/0 ¦ 26/0,1,2,3,4 & 27/0 ¦ 1.914 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-03-23 00:00:00 ¦ 2025-03-28 00:00:00 ¦ 1.914 ¦ 2025-04-18 00:00:00 ¦ 2025-04-20 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 1.914 ¦ Completed ¦ M R Constructions 5 ¦ Telangana ¦ 22/0 ¦ 23/0 ¦ 22/0,1,2,3,4,5 & 23/0 ¦ 2.338 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-04-07 00:00:00 ¦ 2025-04-11 00:00:00 ¦ 2.338 ¦ 2025-04-22 00:00:00 ¦ 2025-04-24 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 2.338 ¦ Completed ¦ M R Constructions 6 ¦ Telangana ¦ 29/0 ¦ 29/9 ¦ 29/0,1,2,3,4,5,6,7,8,9 ¦ 3.555 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-05-05 00:00:00 ¦ 2025-05-16 00:00:00 ¦ 3.555 ¦ 2025-07-06 00:00:00 ¦ 11-07-2025 ¦ Completed ¦ Completed ¦ Completed ¦ 3.555 ¦ Completed ¦ M R Constructions | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection Productivity | 33 | 41 | erection | R3: SI. No. ¦ Sub-Contractor Name ¦ Loc. No. ¦ Type of Tower ¦ Tower Weight (MT) ¦ 01.01.26 (MT) ¦ 02.01.26 (MT) ¦ 03.01.26 (MT) ¦ 04.01.26 (MT) ¦ 05.01.26 (MT) ¦ 06.01.26 (MT) ¦ 07.01.26 (MT) ¦ 08.01.26 (MT) ¦ 09.01.26 (MT) ¦ 10.01.26 (MT) ¦ 11.01.26 (MT) ¦ 12.01.26 (MT) ¦ 013.01.26 (MT) ¦ 014.01.26 (MT) ¦ 015.01.26 (MT) R5: 1 ¦ D k Verma ¦ 4/22 ¦ 2DA+6(3mRc ) ¦ 37.72 ¦ 7.544 ¦ 8 ¦ 8 ¦ 23.544 ¦ Completed ¦ 25 ¦ 20 R6: 2 ¦ Subash ¦ 2/0 ¦ 2DB2+6 ¦ 58.94 ¦ 12 ¦ 12 ¦ 12 ¦ 12 ¦ 48 ¦ Completed ¦ 30 ¦ 35 R7: 3 ¦ Khatun ¦ 4/8 ¦ 2DA+3 ¦ 33.38 ¦ 8.345 ¦ 8 ¦ 8 ¦ 9.038 ¦ 33.38 ¦ Completed ¦ 30 ¦ 32 R8: 4 ¦ Gauri Shankar Mahto ¦ 43A/1 ¦ 3DB1+3 ¦ 57.14 ¦ 6.348888888888889 ¦ 6 ¦ 6 ¦ 6 ¦ 7 ¦ 7 ¦ 7 ¦ 45 ¦ Completed ¦ 30 ¦ 46 | KEC International Limited - Gurgaon. Erection Productivity Gang wise - Jan'26 SI. No. ¦ Sub-Contractor Name ¦ Loc. No. ¦ Type of Tower ¦ Tower Weight (MT) ¦ 01.01.26 (MT) ¦ 02.01.26 (MT) ¦ 03.01.26 (MT) ¦ 04.01.26 (MT) ¦ 05.01.26 (MT) ¦ 06.01.26 (MT) ¦ 07.01.26 (MT) ¦ 08.01.26 (MT) ¦ 09.01.26 (MT) ¦ 10.01.26 (MT) ¦ 11.01.26 (MT) ¦ 12.01.26 (MT) ¦ 013.01.26 (MT) ¦ 014.01.26 (MT) ¦ 015.01.26 (MT) Plan ¦ Actual 1 ¦ D k Verma ¦ 4/22 ¦ 2DA+6(3mRc ) ¦ 37.72 ¦ 7.544 ¦ 8 ¦ 8 ¦ 23.544 ¦ Completed ¦ 25 ¦ 20 2 ¦ Subash ¦ 2/0 ¦ 2DB2+6 ¦ 58.94 ¦ 12 ¦ 12 ¦ 12 ¦ 12 ¦ 48 ¦ Completed ¦ 30 ¦ 35 3 ¦ Khatun ¦ 4/8 ¦ 2DA+3 ¦ 33.38 ¦ 8.345 ¦ 8 ¦ 8 ¦ 9.038 ¦ 33.38 ¦ Completed ¦ 30 ¦ 32 4 ¦ Gauri Shankar Mahto ¦ 43A/1 ¦ 3DB1+3 ¦ 57.14 ¦ 6.348888888888889 ¦ 6 ¦ 6 ¦ 6 ¦ 7 ¦ 7 ¦ 7 ¦ 45 ¦ Completed ¦ 30 ¦ 46 | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | Visual Chart | 198 | 32 | earthing_tack, erection, foundation, project_details, statutory_crossing, stringing, summary_status, visual_l2 | R3: Foundation (Nos.):- ¦ 309 ¦ / 309 ¦ Erection (Nos.):- ¦ 309 ¦ / 309 ¦ Earthing (Nos.):- ¦ 303 ¦ / 309 ¦ Rough Sag (Kms):- ¦ 113.35975000000002 ¦ /121.342 ¦ Final Sag (Kms):- ¦ 113.36000000000001 ¦ /121.342 ¦ Date:- ¦ 2026-05-21 00:00:00 R4: COMPLETION CHART ¦ -3 ¦ +0 ¦ +3 ¦ +6 ¦ +9 ¦ Total ¦ Line Qty R5: ERECTION ¦ Rough Sag ¦ SH / NH Road Crossing R8: DB1 ¦ 8 ¦ 1 ¦ 4 ¦ 5 ¦ 18 ¦ 18 ¦ FOUNDATION R9: DB2 ¦ 11 ¦ 2 ¦ 1 ¦ 14 ¦ 15 ¦ Final Sag | VISUAL PROGRESS CHART 765 KV D/C Bidar - Maheshwaram Transmission Line TL-01 Foundation (Nos.):- ¦ 309 ¦ / 309 ¦ Erection (Nos.):- ¦ 309 ¦ / 309 ¦ Earthing (Nos.):- ¦ 303 ¦ / 309 ¦ Rough Sag (Kms):- ¦ 113.35975000000002 ¦ /121.342 ¦ Final Sag (Kms):- ¦ 113.36000000000001 ¦ /121.342 ¦ Date:- ¦ 2026-05-21 00:00:00 COMPLETION CHART ¦ -3 ¦ +0 ¦ +3 ¦ +6 ¦ +9 ¦ Total ¦ Line Qty ERECTION ¦ Rough Sag ¦ SH / NH Road Crossing DA ¦ 1 ¦ 2 ¦ 3 ¦ 4 ¦ WIP ¦ River DA ¦ 6 ¦ 130 ¦ 78 ¦ 24 ¦ 11 ¦ 249 ¦ 249 ¦ Type ¦ Angle Tower ¦ Gas Pipeline DB1 ¦ 8 ¦ 1 ¦ 4 ¦ 5 ¦ 18 ¦ 18 ¦ FOUNDATION | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stubs and Towers | 65 | 9 | summary_status, supply | R4: SL No ¦ Description ¦ Unit ¦ Line Qty ¦ Received ¦ Balance R5: 1 ¦ 3DA Stub ¦ Set ¦ 190 ¦ 190 R6: 2 ¦ 3DB Stub ¦ Set ¦ 23 ¦ 23 R7: 3 ¦ 3DC Stub ¦ Set ¦ 13 ¦ 13 R8: 4 ¦ 3D45 Stub ¦ Set ¦ 7 ¦ 7 | Supply Status - Stubs & Towers Stub Details SL No ¦ Description ¦ Unit ¦ Line Qty ¦ Received ¦ Balance 1 ¦ 3DA Stub ¦ Set ¦ 190 ¦ 190 2 ¦ 3DB Stub ¦ Set ¦ 23 ¦ 23 3 ¦ 3DC Stub ¦ Set ¦ 13 ¦ 13 4 ¦ 3D45 Stub ¦ Set ¦ 7 ¦ 7 5 ¦ 3D6o Stub ¦ Set ¦ 1 ¦ 1 | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | SuPPLY | 628 | 13 | summary_status, supply | R3: SL No ¦ Description ¦ Unit ¦ Line Qty ¦ Received ¦ Balance ¦ Telangana ¦ Karnataka R4: 1 ¦ 3DA Stub ¦ Set ¦ 190 ¦ 190 ¦ 169 ¦ 21 R5: 2 ¦ 3DB Stub ¦ Set ¦ 23 ¦ 23 ¦ 22 ¦ 1 R6: 3 ¦ 3DC Stub ¦ Set ¦ 13 ¦ 13 ¦ 12 ¦ 1 R7: 4 ¦ 3D45 Stub ¦ Set ¦ 7 ¦ 7 ¦ 6 ¦ 1 | Supply Status - Stubs & Towers Stub Details SL No ¦ Description ¦ Unit ¦ Line Qty ¦ Received ¦ Balance ¦ Telangana ¦ Karnataka 1 ¦ 3DA Stub ¦ Set ¦ 190 ¦ 190 ¦ 169 ¦ 21 2 ¦ 3DB Stub ¦ Set ¦ 23 ¦ 23 ¦ 22 ¦ 1 3 ¦ 3DC Stub ¦ Set ¦ 13 ¦ 13 ¦ 12 ¦ 1 4 ¦ 3D45 Stub ¦ Set ¦ 7 ¦ 7 ¦ 6 ¦ 1 5 ¦ 3D6o Stub ¦ Set ¦ 1 ¦ 1 ¦ 1 | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | X-ing Details | 28 | 11 | statutory_crossing, summary_status | R6: Crossing Type ¦ 110kV ¦ 132 KV ¦ 400kV ¦ 765kV ¦ SH-Xing ¦ NH-Xing ¦ Gas Pipeline Xing ¦ Total ¦ Remarks R13: Sl. No. ¦ FROM (AP) ¦ TO (AP) ¦ Name of the Line ¦ NAME OF CROSSING ¦ Date of First Submission ¦ Joint Inspection Status ¦ Provisional approval status R14: 1 ¦ 1C/0 ¦ 2/0 ¦ 110kV S/C (D/C Towers) Dongargoan SS to Kamalnagar SS - T/L ¦ Power line ¦ 2025-03-29 00:00:00 ¦ Completed ¦ Approval obtained R15: 2 ¦ 5/0 ¦ 6/0 ¦ 110kV S/C (D/C Towers) Santhpur - Dongargoan SS ¦ Power line ¦ 2025-03-29 00:00:00 ¦ Completed ¦ Approval obtained R16: 3 ¦ 8/1 ¦ 8/2 ¦ 110kV S/C OHTL Santhpur - Solarplant ¦ Power line ¦ 2024-09-17 00:00:00 ¦ Completed ¦ Approval obtained | CROSSINGS PROPOSAL STATUS : 765 KV D/C Bidar PS - Maheshwaram (PG) TL01 Crossing Type ¦ 110kV ¦ 132 KV ¦ 400kV ¦ 765kV ¦ SH-Xing ¦ NH-Xing ¦ Gas Pipeline Xing ¦ Total ¦ Remarks Total Nos ¦ 4 ¦ 1 ¦ 3 ¦ 1 ¦ 9 Submitted Till Date ¦ 4 ¦ 1 ¦ 3 ¦ 1 ¦ 9 Approved Till Date ¦ 4 ¦ 1 ¦ 3 ¦ 1 ¦ 9 Balance to Execute Crossings Details Sl. No. ¦ FROM (AP) ¦ TO (AP) ¦ Name of the Line ¦ NAME OF CROSSING ¦ Date of First Submission ¦ Joint Inspection Status ¦ Provisional approval status | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tack Welding | 277 | 9 | earthing_tack | R2: SL. NO. ¦ LOCATION NO. ¦ TYPE OF TOWER ¦ DATE OF TACKWELDING ¦ Gang Name ¦ Gang Strength ¦ NUMBER OF BOLT & NUT | SL. NO. ¦ LOCATION NO. ¦ TYPE OF TOWER ¦ DATE OF TACKWELDING ¦ Gang Name ¦ Gang Strength ¦ NUMBER OF BOLT & NUT 1 ¦ 23/0 ¦ 3DB2+0 ¦ 2025-05-01 00:00:00 ¦ Ram Reddy & Sons ¦ 4 ¦ 4920 2 ¦ 23/1 ¦ 3DA+6 ¦ 2025-07-01 00:00:00 ¦ Ram Reddy & Sons ¦ 4 ¦ 5972 3 ¦ 23/2 ¦ 3DA+0 ¦ 2025-09-01 00:00:00 ¦ Ram Reddy & Sons ¦ 4 ¦ 4618 4 ¦ 23/3 ¦ 3DA+0 ¦ 2025-11-01 00:00:00 ¦ Ram Reddy & Sons ¦ 4 ¦ 4618 5 ¦ 23/4 ¦ 3DA+0 ¦ 13/1/2025 ¦ Ram Reddy & Sons ¦ 4 ¦ 4618 6 ¦ 24/0 ¦ 3DB1+0 ¦ 15/1/2025 ¦ Ram Reddy & Sons ¦ 4 ¦ 4920 7 ¦ 24/3 ¦ 3DA+0 ¦ 17/1/2025 ¦ Ram Reddy & Sons ¦ 4 ¦ 4618 | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tower Accessories | 312 | 10 | opgw_accessories, supply |  | TOWER NO. ¦ TYPE OF TOWER ¦ Number Plate ¦ Phase Plate ¦ Circuit Plate ¦ Danger Plate ¦ ACD ¦ Coping Bidar Gantry ¦ Gantry 1/0 ¦ 2DD60+0 1A/0 ¦ 2DD45+0 1B/0 ¦ 2DB2+3 1B/1 ¦ 2DA+6 1B/2 ¦ 2DA+3 1B/3 ¦ 2DA+0 | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tower Tightening | 317 | 12 | summary_status | R2: TOWER NO. ¦ TYPE OF TOWER ¦ Tower Tightening Status ¦ Gang Name ¦ Manpower ¦ Column1 ¦ Column2 R4: 1/0 ¦ 2DD60+0 ¦ Completed ¦ Dasharath ¦ 14 R5: 1A/0 ¦ 2DD45+0 ¦ Completed ¦ Dasharath ¦ 14 R6: 1B/0 ¦ 2DB2+3 ¦ Completed ¦ Dasharath ¦ 14 R7: 1B/1 ¦ 2DA+6 ¦ Completed ¦ Dasharath ¦ 14 | TOWER NO. ¦ TYPE OF TOWER ¦ Tower Tightening Status ¦ Gang Name ¦ Manpower ¦ Column1 ¦ Column2 Bidar Gantry ¦ Gantry 1/0 ¦ 2DD60+0 ¦ Completed ¦ Dasharath ¦ 14 1A/0 ¦ 2DD45+0 ¦ Completed ¦ Dasharath ¦ 14 1B/0 ¦ 2DB2+3 ¦ Completed ¦ Dasharath ¦ 14 1B/1 ¦ 2DA+6 ¦ Completed ¦ Dasharath ¦ 14 1B/2 ¦ 2DA+3 ¦ Completed ¦ Dasharath ¦ 15 1B/3 ¦ 2DA+0 ¦ Completed ¦ Dasharath ¦ 14 | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | Hardwares & Tower Accessories | 35 | 8 | opgw_accessories, supply | R2: LOI Item No. ¦ Activity Description ¦ Description of Work ¦ UOM ¦ Line Quantity ¦ SUPPLY RECEIVED ¦ Balance R3: 47 ¦ CONDUCTOR ¦ ACSR/AL59/AAAC ZEBRA CONDUCTOR ¦ KM ¦ 4412 ¦ 4411.538 ¦ 0.46200000000044383 R4: 62 ¦ HARDWARE FITTINGS ¦ Double ISuspension String ¦ SET ¦ 1506 ¦ 1506 R5: 63 ¦ HARDWARE FITTINGS ¦ Single ISuspension String (Pilot) ¦ SET ¦ 95 ¦ 95 R6: 64 ¦ HARDWARE FITTINGS ¦ Quadruple Tension String ¦ SET ¦ 738 ¦ 738 | LOI Item No. ¦ Activity Description ¦ Description of Work ¦ UOM ¦ Line Quantity ¦ SUPPLY RECEIVED ¦ Balance 47 ¦ CONDUCTOR ¦ ACSR/AL59/AAAC ZEBRA CONDUCTOR ¦ KM ¦ 4412 ¦ 4411.538 ¦ 0.46200000000044383 62 ¦ HARDWARE FITTINGS ¦ Double ISuspension String ¦ SET ¦ 1506 ¦ 1506 63 ¦ HARDWARE FITTINGS ¦ Single ISuspension String (Pilot) ¦ SET ¦ 95 ¦ 95 64 ¦ HARDWARE FITTINGS ¦ Quadruple Tension String ¦ SET ¦ 738 ¦ 738 65 ¦ HARDWARE FITTINGS ¦ SingleTension String ¦ SET ¦ 4 ¦ 4 70 ¦ CONDUCTOR ACCESSORIES ¦ HEXAGONAL RIGID SPACER ¦ EA ¦ 1945 ¦ 1945 71 ¦ CONDUCTOR ACCESSORIES ¦ MID SPAN COMPRESSION JOINT ¦ EA ¦ 2102 ¦ 2102 | ok
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet1 | 1 | 1 |  |  |  | ok
TA 504 | TA 504 - DPR - 2026-05-21.xlsx | 2026-05-21 | DPR_TA-504 | 27 | 13 | foundation, project_details, summary_status, supply, survey_soil | R5: NOA Date :- 15-July-2024 ¦ Completion Date :- 14-June-2026 ¦ Date:- 20 May 2026 R6: SUPPLY VALUE = 212.95 Cr. ¦ SERVICE VALUE = 37.28 Cr. ¦ F&I VALUE = 5.26 Cr. R7: PARTICULARS ¦ UOM ¦ Total ¦ Comp ¦ Balance ¦ 2026-05-01 00:00:00 ¦ WIP ¦ Cumulative ¦ 2026-06-01 00:00:00 ¦ 2026-07-02 00:00:00 ¦ Remarks R8: Qty ¦ Till ¦ as on ¦ Plan ¦ Actual ¦ Plan ¦ Plan R10: Detail Survey ¦ KM ¦ 70 ¦ 69 ¦ 1 ¦ 69 | LINE NAME- : 765 KV D/C Rishabdeo - Mandsaur & Lilo CLIENT-Rajasthan IVE Mewar Transmission Limited (POWER GRID CORPORATION OF INDIA) DAILY PROGRESS REPORT (TA-504) NOA Date :- 15-July-2024 ¦ Completion Date :- 14-June-2026 ¦ Date:- 20 May 2026 SUPPLY VALUE = 212.95 Cr. ¦ SERVICE VALUE = 37.28 Cr. ¦ F&I VALUE = 5.26 Cr. PARTICULARS ¦ UOM ¦ Total ¦ Comp ¦ Balance ¦ 2026-05-01 00:00:00 ¦ WIP ¦ Cumulative ¦ 2026-06-01 00:00:00 ¦ 2026-07-02 00:00:00 ¦ Remarks Qty ¦ Till ¦ as on ¦ Plan ¦ Actual ¦ Plan ¦ Plan 2026-04-01 00:00:00 ¦ 1 May'26 | repaired_defined_names (ValueError)
TA 504 | TA 504 - DPR - 2026-05-21.xlsx | 2026-05-21 | Erection compiled | 765 | 12 | earthing_tack, erection, project_details, summary_status | R3: Details of Erection ¦ 3384.8591189999984 ¦ 356.7641511426 ¦ 2026-05-19 00:00:00 ¦ Tack Welding R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Location No ¦ Type of Tower ¦ Starting Date ¦ Completion date ¦ Gang name ¦ Tower Weight ¦ Revenue ¦ Name of Supervisor ¦ Status R5: 1 ¦ 11/0 ¦ DB2+0 ¦ 2025-09-03 00:00:00 ¦ 2025-09-22 00:00:00 ¦ Sainik Traders ¦ 59.500628000000006 ¦ 6.2713661912 ¦ Teklal Mahto ¦ Completed R6: 2 ¦ 11/1 ¦ DA+0 ¦ 2025-07-21 00:00:00 ¦ 2025-07-30 00:00:00 ¦ Sainik Traders ¦ 36.15975600000001 ¦ 3.811238282400001 ¦ Teklal Mahto ¦ Completed ¦ Completed R7: 3 ¦ 11/2 ¦ DA+0 ¦ 2025-08-01 00:00:00 ¦ 2025-08-13 00:00:00 ¦ Sainik Traders ¦ 36.15975600000001 ¦ 3.811238282400001 ¦ Teklal Mahto ¦ Completed ¦ Completed | KEC International Limited TA-504 - 765 KV D/C Rishabdeo - Mandsaur & Lilo Details of Erection ¦ 3384.8591189999984 ¦ 356.7641511426 ¦ 2026-05-19 00:00:00 ¦ Tack Welding CUMM. SR.NO ¦ MONTH SR.NO. ¦ Location No ¦ Type of Tower ¦ Starting Date ¦ Completion date ¦ Gang name ¦ Tower Weight ¦ Revenue ¦ Name of Supervisor ¦ Status 1 ¦ 11/0 ¦ DB2+0 ¦ 2025-09-03 00:00:00 ¦ 2025-09-22 00:00:00 ¦ Sainik Traders ¦ 59.500628000000006 ¦ 6.2713661912 ¦ Teklal Mahto ¦ Completed 2 ¦ 11/1 ¦ DA+0 ¦ 2025-07-21 00:00:00 ¦ 2025-07-30 00:00:00 ¦ Sainik Traders ¦ 36.15975600000001 ¦ 3.811238282400001 ¦ Teklal Mahto ¦ Completed ¦ Completed 3 ¦ 11/2 ¦ DA+0 ¦ 2025-08-01 00:00:00 ¦ 2025-08-13 00:00:00 ¦ Sainik Traders ¦ 36.15975600000001 ¦ 3.811238282400001 ¦ Teklal Mahto ¦ Completed ¦ Completed 4 ¦ 11/3 ¦ DA+3 ¦ 2025-08-14 00:00:00 ¦ 2025-08-31 00:00:00 ¦ Sainik Traders ¦ 37.931088 ¦ 3.9979366752 ¦ Teklal Mahto ¦ Completed | repaired_defined_names (ValueError)
TA 504 | TA 504 - DPR - 2026-05-21.xlsx | 2026-05-21 | Tightening | 177 | 13 | project_details, summary_status | R1: SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Tower Tightening ¦ Remark R2: 1 ¦ 11/0 ¦ DB2+0 ¦ 2025-09-03 00:00:00 ¦ 59.500628000000006 ¦ COMPLETED ¦ 2025-09-22 00:00:00 ¦ Sainik Traders ¦ 32 ¦ 13 ¦ 2026-04-25 00:00:00 R3: 2 ¦ 11/1 ¦ DA+0 ¦ 2025-07-21 00:00:00 ¦ 36.15975600000001 ¦ COMPLETED ¦ 2025-07-30 00:00:00 ¦ Sainik Traders ¦ 32 ¦ 13 ¦ 2026-05-04 00:00:00 R4: 3 ¦ 11/2 ¦ DA+0 ¦ 2025-08-01 00:00:00 ¦ 36.15975600000001 ¦ COMPLETED ¦ 2025-08-13 00:00:00 ¦ Sainik Traders ¦ 32 ¦ 13 ¦ 2026-04-28 00:00:00 R5: 4 ¦ 11/3 ¦ DA+3 ¦ 2025-08-14 00:00:00 ¦ 37.931088 ¦ COMPLETED ¦ 2025-08-31 00:00:00 ¦ Sainik Traders ¦ 32 ¦ 13 ¦ 2026-05-03 00:00:00 | SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Tower Tightening ¦ Remark 1 ¦ 11/0 ¦ DB2+0 ¦ 2025-09-03 00:00:00 ¦ 59.500628000000006 ¦ COMPLETED ¦ 2025-09-22 00:00:00 ¦ Sainik Traders ¦ 32 ¦ 13 ¦ 2026-04-25 00:00:00 2 ¦ 11/1 ¦ DA+0 ¦ 2025-07-21 00:00:00 ¦ 36.15975600000001 ¦ COMPLETED ¦ 2025-07-30 00:00:00 ¦ Sainik Traders ¦ 32 ¦ 13 ¦ 2026-05-04 00:00:00 3 ¦ 11/2 ¦ DA+0 ¦ 2025-08-01 00:00:00 ¦ 36.15975600000001 ¦ COMPLETED ¦ 2025-08-13 00:00:00 ¦ Sainik Traders ¦ 32 ¦ 13 ¦ 2026-04-28 00:00:00 4 ¦ 11/3 ¦ DA+3 ¦ 2025-08-14 00:00:00 ¦ 37.931088 ¦ COMPLETED ¦ 2025-08-31 00:00:00 ¦ Sainik Traders ¦ 32 ¦ 13 ¦ 2026-05-03 00:00:00 5 ¦ 11/4 ¦ DA+0 ¦ 2025-07-07 00:00:00 ¦ 36.15975600000001 ¦ COMPLETED ¦ 2025-07-21 00:00:00 ¦ Sainik Traders ¦ 32 ¦ 13 ¦ 2026-04-27 00:00:00 6 ¦ 12/0 ¦ DB2+0 ¦ 2025-09-22 00:00:00 ¦ 59.500628000000006 ¦ COMPLETED ¦ 2025-10-08 00:00:00 ¦ Sainik Traders ¦ 32 ¦ 13 ¦ 2026-04-30 00:00:00 7 ¦ 12/1 ¦ DA-3 ¦ 2025-06-16 00:00:00 ¦ 34.78981 ¦ COMPLETED ¦ 2025-06-20 00:00:00 ¦ pankaj-2 ¦ 32 ¦ 12 ¦ 2026-05-01 00:00:00 | repaired_defined_names (ValueError)
TA 504 | TA 504 - DPR - 2026-05-21.xlsx | 2026-05-21 | Stringing Compiled | 71 | 16369 | project_details, stretch_readiness, stringing, summary_status, supply | R2: S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos. ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name R29: 27 ¦ Bhinder ¦ 15/0 ¦ 16/0 ¦ 15/1, 15/2, 15/3, 15/4, 15/5, 15/6, 15/7, 16/0 ¦ 3229.725 ¦ TSE ¦ Ready ¦ 2026-03-25 00:00:00 ¦ 2026-03-29 00:00:00 ¦ 3229.73 ¦ 2026-04-01 00:00:00 ¦ 2026-04-04 00:00:00 ¦ Completed ¦ Completed ¦ 3229.725 ¦ Completed ¦ Lamba Construction ¦ 50 ¦ 13 R30: 28 ¦ Bhinder ¦ 16/0 ¦ 16/3 ¦ 16/1, 16/2, 16/3 ¦ 1245.996 ¦ TSE ¦ Ready ¦ 2026-04-01 00:00:00 ¦ 2026-04-04 00:00:00 ¦ 1246 ¦ 2026-04-06 00:00:00 ¦ 2026-04-09 00:00:00 ¦ Completed ¦ Completed ¦ 1245.996 ¦ Completed ¦ Lamba Construction ¦ 50 ¦ 13 R31: 29 ¦ Bhinder ¦ 16/3 ¦ 17/0 ¦ 16/4, 16/5, 16/6, 17/0 ¦ 1466.604 ¦ TSE ¦ Ready ¦ 2026-02-04 00:00:00 ¦ 2026-02-07 00:00:00 ¦ 1466.6 ¦ 2026-02-19 00:00:00 ¦ 2026-02-19 00:00:00 ¦ Completed ¦ Completed ¦ 1466.604 ¦ Completed ¦ Lamba Construction ¦ 50 ¦ 13 R32: 30 ¦ Bhinder ¦ 17/0 ¦ 17/4 ¦ 17/1, 17/2, 17/3, 17/4 ¦ 1646.996 ¦ TSE ¦ Ready ¦ 2026-02-11 00:00:00 ¦ 2026-02-14 00:00:00 ¦ 1647 ¦ 2026-02-19 00:00:00 ¦ 2026-02-22 00:00:00 ¦ Completed ¦ Completed ¦ 1646.996 ¦ Completed ¦ Lamba Construction ¦ 50 ¦ 13 | Number of TSE ¦ 1 S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos. ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name 1 ¦ 1/0 ¦ 2/0 ¦ 1/0 ¦ 108.186 ¦ Manual 2 ¦ 2/0 ¦ 3/0 ¦ 2/0 ¦ 216.27 ¦ Manual 3 ¦ 3/0 ¦ 4/0 ¦ 3/0, 3/1, 3/2, 3/3 ¦ 1438.33 ¦ TSE 4 ¦ 4/0 ¦ 5/0 ¦ 4/1 ¦ 561.94 ¦ TSE 5 ¦ 5/0 ¦ 5A/0 ¦ 5/0, 5/1 ¦ 755.7 ¦ TSE 6 ¦ 5A/0 ¦ 5B/0 ¦ 5A/0 ¦ 233.636 ¦ Manual | repaired_defined_names (ValueError)
TA 504 | TA 504 - DPR - 2026-05-21.xlsx | 2026-05-21 | VC_RMTL | 151 | 56 | earthing_tack, erection, foundation, opgw_accessories, row_hindrance, stringing, survey_soil, visual_l2 | R3: Description of Item ¦ UOM ¦ Total Line Qty ¦ Total Completed ¦ WIP locations ¦ Total Balance R6: Stringing Comp ¦ Location No. ¦ Route Alignment ¦ Kms ¦ 62.499 ¦ 62.499 R7: Detail Survey ¦ Kms ¦ 62.499 ¦ 62.499 ¦ #REF! R8: Erection Comp ¦ Stringing WIP ¦ Check Survey ¦ Kms ¦ 62.499 ¦ 60.7 ¦ #REF! ¦ 1.7989999999999995 R9: Erection Comp ¦ Foundation ¦ Nos ¦ 165 ¦ 140 ¦ 3 ¦ 25 | Visual Chart :- 765kV D/C Rishabdeo Mandsaur Transmission Line, WZ-04 Project Code : TA504 ¦ Dated: Description of Item ¦ UOM ¦ Total Line Qty ¦ Total Completed ¦ WIP locations ¦ Total Balance LEGEND: ¦ OPGW Stringing Stringing Comp ¦ Location No. ¦ Route Alignment ¦ Kms ¦ 62.499 ¦ 62.499 Detail Survey ¦ Kms ¦ 62.499 ¦ 62.499 ¦ #REF! Erection Comp ¦ Stringing WIP ¦ Check Survey ¦ Kms ¦ 62.499 ¦ 60.7 ¦ #REF! ¦ 1.7989999999999995 Erection Comp ¦ Foundation ¦ Nos ¦ 165 ¦ 140 ¦ 3 ¦ 25 | repaired_defined_names (ValueError)
TA 504 | TA 504 - DPR - 2026-05-21.xlsx | 2026-05-21 | VC_Lilo | 54 | 56 | earthing_tack, erection, foundation, opgw_accessories, row_hindrance, stringing, survey_soil, visual_l2 | R3: Description of Item ¦ UOM ¦ Total Line Qty ¦ Total Completed ¦ WIP locations ¦ Total Balance R6: Stringing Comp ¦ Location No. ¦ Route Alignment ¦ Kms ¦ 7.08 ¦ 7.08 R7: Detail Survey ¦ Kms ¦ 7.08 ¦ 7.08 R8: Erection Comp ¦ Stringing WIP ¦ Check Survey ¦ Kms ¦ 7.08 ¦ 7.08 R9: Erection Comp ¦ Foundation ¦ Nos ¦ 23 ¦ 2 ¦ 1 ¦ 21 | Visual Chart :- 765 KV DC LILO CHITTORGARH-RISHABDEO T/L Project Code : TA504 ¦ Dated: Description of Item ¦ UOM ¦ Total Line Qty ¦ Total Completed ¦ WIP locations ¦ Total Balance LEGEND: ¦ OPGW Stringing Stringing Comp ¦ Location No. ¦ Route Alignment ¦ Kms ¦ 7.08 ¦ 7.08 Detail Survey ¦ Kms ¦ 7.08 ¦ 7.08 Erection Comp ¦ Stringing WIP ¦ Check Survey ¦ Kms ¦ 7.08 ¦ 7.08 Erection Comp ¦ Foundation ¦ Nos ¦ 23 ¦ 2 ¦ 1 ¦ 21 | repaired_defined_names (ValueError)
TA 504 | TA 504 - DPR - 2026-05-21.xlsx | 2026-05-21 | Project Details | 21 | 11 | project_details | R1: Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Engineer/Supervisor | Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Engineer/Supervisor TA 504 ¦ 765 KV D/C Rishabdeo - Mandsaur & Lilo ¦ PGCIL ¦ 2024-07-15 00:00:00 ¦ 2026-06-14 00:00:00 ¦ Mr. Abir Kumar Das ¦ Mr. Nabajit Baruah ¦ Mr. Rajiv Sharma ¦ Prasant Kumar ¦ Khemchand Ashutosh Prakash Teklal Mahto Rameswar Mahto Rajesh Singh | repaired_defined_names (ValueError)
TA 504 | TA 504 - DPR - 2026-05-21.xlsx | 2026-05-21 | Location Summary | 782 | 21 | earthing_tack, erection, foundation, summary_status | R2: S. No. ¦ No of ¦ Location ¦ Type of ¦ RC ¦ Span ¦ Cumm. ¦ DS Status as on ¦ 306 ¦ 292 ¦ 257 ¦ 102 ¦ 26 ¦ Remarks R3: AP ¦ Tower No. ¦ Tower ¦ Length (m) ¦ Span (km) ¦ 2025-11-01 00:00:00 ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Tack welding ¦ SPT R6: 3 ¦ AP-1 ¦ 1/0 ¦ DD60+0 ¦ T ¦ 0.15 ¦ Approved ¦ Completed ¦ Completed ¦ Completed R8: 2 ¦ AP-2A ¦ 2A/0 ¦ DD45+0 ¦ T ¦ 0.44020000000000004 ¦ Approved ¦ Completed ¦ Completed R10: 3 ¦ AP-3 ¦ 2A/1 ¦ DA+0 ¦ 0.8182 ¦ Approved ¦ Completed ¦ Completed ¦ Completed | Over all Tower Location details S. No. ¦ No of ¦ Location ¦ Type of ¦ RC ¦ Span ¦ Cumm. ¦ DS Status as on ¦ 306 ¦ 292 ¦ 257 ¦ 102 ¦ 26 ¦ Remarks AP ¦ Tower No. ¦ Tower ¦ Length (m) ¦ Span (km) ¦ 2025-11-01 00:00:00 ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Tack welding ¦ SPT Gantry ¦ Gantry Gantry ¦ 150.014 3 ¦ AP-1 ¦ 1/0 ¦ DD60+0 ¦ T ¦ 0.15 ¦ Approved ¦ Completed ¦ Completed ¦ Completed 1/0 ¦ 290.21 2 ¦ AP-2A ¦ 2A/0 ¦ DD45+0 ¦ T ¦ 0.44020000000000004 ¦ Approved ¦ Completed ¦ Completed | repaired_defined_names (ValueError)
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | DPR-Summary | 28 | 14 | foundation, project_details, row_hindrance, summary_status, supply, survey_soil, visual_l2 | R5: NOA Date :- 22-July-2024 ¦ Schedule Completion Date :- 21-June-2026 ¦ Date:- 19th MAY 2026. R6: SUPPLY VALUE = 458.32 Cr. ¦ SERVICE VALUE = 94.23 Cr. ¦ F&I VALUE = 9.48 Cr. R7: PARTICULARS ¦ UOM ¦ Total ¦ Comp ¦ Balance ¦ May'26 ¦ WIP ¦ Cumulative ¦ June'26 ¦ July'26 ¦ Remarks R8: Qty ¦ Till ¦ as on ¦ Plan ¦ Actual ¦ Plan ¦ Plan R10: Detail Survey ¦ KM ¦ 139.6 ¦ 139.6 | LINE NAME- 765 kV D/C HEXA BEAWAR MANDSAUR TRANSMISSION LINE CLIENT-POWERGRID BEAWAR MANDSAUR TRANSMISSION LIMITED DAILY PROGRESS REPORT (TA-505) NOA Date :- 22-July-2024 ¦ Schedule Completion Date :- 21-June-2026 ¦ Date:- 19th MAY 2026. SUPPLY VALUE = 458.32 Cr. ¦ SERVICE VALUE = 94.23 Cr. ¦ F&I VALUE = 9.48 Cr. PARTICULARS ¦ UOM ¦ Total ¦ Comp ¦ Balance ¦ May'26 ¦ WIP ¦ Cumulative ¦ June'26 ¦ July'26 ¦ Remarks Qty ¦ Till ¦ as on ¦ Plan ¦ Actual ¦ Plan ¦ Plan 2026-04-01 00:00:00 ¦ 1st May-26 | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Sheet1 | 32 | 3 |  |  | TYPE OF TOWERS ¦ NO OF TOWERS DA+0 DFR ¦ 24 DA+0 DRY ¦ 13 DA+0 WET ¦ 4 DA+0 WFR ¦ 18 DA+3/6/9 DRY ¦ 11 DA+3/6/9 DFR ¦ 25 DA+3/6/9 WET ¦ 5 | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Project Details | 22 | 11 | project_details | R1: Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Supervisor | Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Supervisor TA 505 ¦ 765 Kv D/C Beawar-Mandsaur T/L ¦ PBMTL ¦ 22-07-2024 ¦ 21-06-2026 ¦ Mr. Partha Pratim Pal ¦ Mr. Nabajit Baruah ¦ Mr. Nabajit Baruah ¦ Mr. Sushil Kr Tiwari ¦ Mr.Deepak Anand ¦ Nunuchand Mahto Mr.Bapan Mandal ¦ Birkha Subba Mr.Panneri Satish ¦ Dilip Kumar Mr. Varun Mishra ¦ Teklal Mahato Munid Meena Mortuj Ali Devdas Malik | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Sheet5 | 91 | 4 | earthing_tack | R1: Loc NO ¦ TOT ¦ Classification ¦ Type of Earthing | Loc NO ¦ TOT ¦ Classification ¦ Type of Earthing 100/0 ¦ DD45+0 ¦ WET ¦ Pipe Type 101/0 ¦ DC1+3 ¦ DFR ¦ Counter Poise 101/1 ¦ DA+3 ¦ WFR ¦ Counter Poise 101/2 ¦ DA+9 ¦ WFR ¦ Counter Poise 101/3 ¦ DA+3 ¦ WFR ¦ Counter Poise 101/4 ¦ DA+6 ¦ WFR ¦ Counter Poise 101/5 ¦ DA+0 ¦ WFR ¦ Counter Poise | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Foundation | 403 | 24 | earthing_tack, foundation, project_details, summary_status, supply, survey_soil, visual_l2 | R3: NOA Date: 22-July-2024 ¦ Completion Date : 21-June-2026 ¦ Date : 27-05-25 R4: SUPPLY VALUE = 458 Cr. ¦ SERVICE VALUE = 94.23 Cr. ¦ F&I VALUE = 9.48 Cr. ¦ 561.71 R5: Sr. No. ¦ Activity ¦ UOM ¦ Total Qty. ¦ L2 Qty. ¦ Completed ¦ Balance ¦ Submitted ¦ WIP ¦ Remarks R6: 1 ¦ Details Survey ¦ Kms ¦ 136.705 ¦ 126 ¦ 126.32400000000001 ¦ 10.381 ¦ 10.381 R7: 2 ¦ Check Survey ¦ Kms ¦ 136.705 ¦ 126 ¦ 108.679 ¦ 28.02600000000001 | 765 kV D/C BEAWAR MANDSAUR TRANSMISSION LINE PROGRESS SUMMARY DETAIL NOA Date: 22-July-2024 ¦ Completion Date : 21-June-2026 ¦ Date : 27-05-25 SUPPLY VALUE = 458 Cr. ¦ SERVICE VALUE = 94.23 Cr. ¦ F&I VALUE = 9.48 Cr. ¦ 561.71 Sr. No. ¦ Activity ¦ UOM ¦ Total Qty. ¦ L2 Qty. ¦ Completed ¦ Balance ¦ Submitted ¦ WIP ¦ Remarks 1 ¦ Details Survey ¦ Kms ¦ 136.705 ¦ 126 ¦ 126.32400000000001 ¦ 10.381 ¦ 10.381 2 ¦ Check Survey ¦ Kms ¦ 136.705 ¦ 126 ¦ 108.679 ¦ 28.02600000000001 3 ¦ Soil Testing ¦ Nos ¦ 34 ¦ 34 | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Balance Erc-RAJ | 38 | 6 | erection, summary_status, supply | R2: SL No ¦ Loc No ¦ TOT ¦ Tower Availability ¦ Current Status ¦ Remarks R3: 1 ¦ 99/1 ¦ DA+6 ¦ NO ¦ Erectable ¦ Tower Parts not available-Supply in PGCIL Scope. R4: 2 ¦ 99/2 ¦ DA+6 ¦ NO ¦ Erectable R5: 3 ¦ 99/3 ¦ DA+0 ¦ NO ¦ Erectable R6: 4 ¦ 99/4 ¦ DA+0 ¦ NO ¦ Erectable | Balance Erection Status (Rajasthan) SL No ¦ Loc No ¦ TOT ¦ Tower Availability ¦ Current Status ¦ Remarks 1 ¦ 99/1 ¦ DA+6 ¦ NO ¦ Erectable ¦ Tower Parts not available-Supply in PGCIL Scope. 2 ¦ 99/2 ¦ DA+6 ¦ NO ¦ Erectable 3 ¦ 99/3 ¦ DA+0 ¦ NO ¦ Erectable 4 ¦ 99/4 ¦ DA+0 ¦ NO ¦ Erectable 5 ¦ 99/5 ¦ DA+0 ¦ NO ¦ Erectable 6 ¦ 99/6 ¦ DA+0 ¦ NO ¦ Erectable | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | ERC ROW-MP | 79 | 6 | erection, row_hindrance, summary_status | R2: SL No ¦ Loc No ¦ TOT ¦ Tower Availability ¦ Current Status ¦ Remarks R23: 21 ¦ 170/4 ¦ DA-3 ¦ Yes ¦ ROW ¦ Tower Erectable after Crop Harvesting. R25: 23 ¦ 170/6 ¦ DA-3 ¦ Yes ¦ ROW ¦ Tower Erectable after Crop Harvesting. R31: 29 ¦ 171/3 ¦ DA+0 ¦ Yes ¦ ROW ¦ Tower Erectable after Crop Harvesting. R32: 30 ¦ 171/4 ¦ DA+0 ¦ Yes ¦ ROW ¦ Tower Erectable after Crop Harvesting. | Balance Erection Status (MP) SL No ¦ Loc No ¦ TOT ¦ Tower Availability ¦ Current Status ¦ Remarks 1 ¦ 159/3 ¦ DA+0 ¦ Yes ¦ Shutdown Issue 2 ¦ 161/1 ¦ DA+3 ¦ Yes ¦ Opium Planted 3 ¦ 161/5 ¦ DA+6 4 ¦ 164/2 ¦ DA+0 ¦ Yes ¦ Shutdown Issue 5 ¦ 164/3 ¦ DA+3 6 ¦ 164/4 ¦ DA+0 ¦ Yes ¦ Shutdown Issue | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Erection Compiled | 364 | 19 | erection, project_details, summary_status | R4: Sr. No ¦ Location No. ¦ Tower Type ¦ Tower Weight ¦ Rev(Inr) ¦ Month of Execution ¦ Gang Name ¦ Status ¦ Starting Date ¦ Completion Date ¦ No of Compl. Days ¦ Region ¦ Tower Tightening ¦ Remarks R6: 1 ¦ 101/2 ¦ DA+9 ¦ 45.697022000000004 ¦ 499925.42068000004 ¦ 2025-01-01 00:00:00 ¦ Jwala Singh ¦ Completed ¦ 2025-01-14 00:00:00 ¦ 2025-01-19 00:00:00 ¦ 5 ¦ Raj ¦ OK R7: 2 ¦ 101/1 ¦ DA+3 ¦ 37.931087999999995 ¦ 414966.10271999997 ¦ 2025-01-01 00:00:00 ¦ Jwala Singh ¦ Completed ¦ 2025-01-21 00:00:00 ¦ 2025-01-24 00:00:00 ¦ 3 ¦ Raj ¦ OK R8: 3 ¦ 101/3 ¦ DA+3 ¦ 37.931087999999995 ¦ 414966.10271999997 ¦ 2025-01-01 00:00:00 ¦ Jwala Singh ¦ Completed ¦ 2025-01-24 00:00:00 ¦ 2025-01-27 00:00:00 ¦ 3 ¦ Raj ¦ OK R9: 4 ¦ 101/4 ¦ DA+6 ¦ 43.804424 ¦ 479220.39855999994 ¦ 2025-01-01 00:00:00 ¦ Jwala Singh ¦ Completed ¦ 2025-01-27 00:00:00 ¦ 2025-01-31 00:00:00 ¦ 4 ¦ Raj ¦ OK | 2026-05-19 00:00:00 Sr. No ¦ Location No. ¦ Tower Type ¦ Tower Weight ¦ Rev(Inr) ¦ Month of Execution ¦ Gang Name ¦ Status ¦ Starting Date ¦ Completion Date ¦ No of Compl. Days ¦ Region ¦ Tower Tightening ¦ Remarks 16782.191551999986 ¦ 354 ¦ 177 1 ¦ 101/2 ¦ DA+9 ¦ 45.697022000000004 ¦ 499925.42068000004 ¦ 2025-01-01 00:00:00 ¦ Jwala Singh ¦ Completed ¦ 2025-01-14 00:00:00 ¦ 2025-01-19 00:00:00 ¦ 5 ¦ Raj ¦ OK 2 ¦ 101/1 ¦ DA+3 ¦ 37.931087999999995 ¦ 414966.10271999997 ¦ 2025-01-01 00:00:00 ¦ Jwala Singh ¦ Completed ¦ 2025-01-21 00:00:00 ¦ 2025-01-24 00:00:00 ¦ 3 ¦ Raj ¦ OK 3 ¦ 101/3 ¦ DA+3 ¦ 37.931087999999995 ¦ 414966.10271999997 ¦ 2025-01-01 00:00:00 ¦ Jwala Singh ¦ Completed ¦ 2025-01-24 00:00:00 ¦ 2025-01-27 00:00:00 ¦ 3 ¦ Raj ¦ OK 4 ¦ 101/4 ¦ DA+6 ¦ 43.804424 ¦ 479220.39855999994 ¦ 2025-01-01 00:00:00 ¦ Jwala Singh ¦ Completed ¦ 2025-01-27 00:00:00 ¦ 2025-01-31 00:00:00 ¦ 4 ¦ Raj ¦ OK 5 ¦ 101/5 ¦ DA+0 ¦ 36.159755999999994 ¦ 395587.73063999997 ¦ 2025-02-01 00:00:00 ¦ Jwala Singh ¦ Completed ¦ 2025-02-01 00:00:00 ¦ 2025-02-04 00:00:00 ¦ 3 ¦ Raj ¦ OK | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Stringing Compiled | 236 | 16286 | project_details, stretch_readiness, stringing, summary_status, supply | R4: S.no ¦ Sec ¦ From AP ¦ To AP ¦ Span (M) ¦ Towers in Section ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name | Number of TSE ¦ 1 S.no ¦ Sec ¦ From AP ¦ To AP ¦ Span (M) ¦ Towers in Section ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name 1 ¦ 100/0 To 101/0 ¦ 100/0 ¦ 101/0 ¦ 419 ¦ 100/0, 101/0 ¦ Manual ¦ Ready ¦ Done ¦ 2026-01-20 00:00:00 ¦ 2026-01-25 00:00:00 ¦ Done ¦ 2026-02-05 00:00:00 ¦ 2026-02-07 00:00:00 ¦ 419 ¦ Done ¦ Alimuddin ¦ 30 2 ¦ 101/0 To 102/0 ¦ 101/0 ¦ 102/0 ¦ 3470 ¦ 101/0,101/1, 101/2, 101/3, 101/4, 101/5, 101/6, 101/7, 101/8 & 102/0 ¦ TSE ¦ Ready ¦ Done ¦ 2026-01-27 00:00:00 ¦ 2026-02-02 00:00:00 ¦ Done ¦ 2026-02-10 00:00:00 ¦ 2026-02-15 00:00:00 ¦ 3470 ¦ Done ¦ Alimuddin ¦ 30 3 ¦ 102/0 To 103/0 ¦ 102/0 ¦ 103/0 ¦ 461 ¦ 102/0 & 103/0 ¦ Manual ¦ Ready ¦ Done ¦ 2026-02-08 00:00:00 ¦ 2026-02-12 00:00:00 ¦ Done ¦ 2026-02-18 00:00:00 ¦ 2026-02-22 00:00:00 ¦ 461 ¦ Done ¦ Alimuddin ¦ 30 4 ¦ 103/0 To 103/5A ¦ 103/0 ¦ 103/5A ¦ 2200 ¦ 103/0, 103/1, 103/2, 103/4, 103/5 & 103/5A ¦ TSE ¦ Ready ¦ Done ¦ 2026-02-16 00:00:00 ¦ 2026-02-22 00:00:00 ¦ Done ¦ 2026-02-26 00:00:00 ¦ 2026-02-28 00:00:00 ¦ 2200 ¦ Done ¦ Alimuddin ¦ 30 5 ¦ 103/5A To 103/6A ¦ 103/5A ¦ 103/6A ¦ 567 ¦ 103/5A,103/5A1 & 103/6A ¦ TSE ¦ Ready ¦ Done ¦ 2026-02-24 00:00:00 ¦ 2026-02-26 00:00:00 ¦ Done ¦ 2026-03-12 00:00:00 ¦ 2026-03-16 00:00:00 ¦ 567 ¦ Done ¦ Alimuddin ¦ 30 6 ¦ 103/6A To 104/0 ¦ 103/6A ¦ 104/0 ¦ 1403 ¦ 103/6A ,103/7, 103/8, 103/9 & 104/0. ¦ TSE ¦ Ready ¦ Done ¦ 2026-03-12 00:00:00 ¦ 2026-03-16 00:00:00 ¦ Done ¦ 2026-03-17 00:00:00 ¦ 2026-03-20 00:00:00 ¦ 1403 ¦ Done ¦ Alimuddin ¦ 30 | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Visual Chart | 504 | 38 | foundation, visual_l2 | R9: FDN ¦ Ear ¦ ERE ¦ TW ¦ STR R27: Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed R38: X ¦ Completed ¦ Completed ¦ Completed R49: Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed R59: Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed | V I S U A L C H A R T DATE : ¦ 2026-05-19 00:00:00 Name of Line : ¦ 765 KV D/C HEXA BEAWAR MANDSAUR T/L Project Code: ¦ TA505 Name of Executing Agency: ¦ M/s. KEC INTERNATIONAL LTD. FDN ¦ Ear ¦ ERE ¦ TW ¦ STR COMMON TOWER 99/0 ¦ 99/1 ¦ 99/2 ¦ 99/3 ¦ 99/4 ¦ 4 ¦ 4 | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Erection Productivity | 5 | 28 | erection | R3: TA-505 ¦ PGCIL_Part-D - TL02_for 765kV TL Beawar ¦ Partha Pratim Pal ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan | Project Code ¦ Project Name ¦ SPOC ¦ Apr'25 ¦ May'25 ¦ Jun'25 ¦ Jul'25 ¦ Aug'25 ¦ Sep'25 ¦ Oct'25 ¦ Nov'25 ¦ Dec'25 ¦ Jan'26 ¦ Feb'26 ¦ Mar'26 TA-505 ¦ PGCIL_Part-D - TL02_for 765kV TL Beawar ¦ Partha Pratim Pal ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan ¦ Actual ¦ Plan (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) ¦ (in MT) 1352 ¦ 698 ¦ 1742 ¦ 922 ¦ 1188 ¦ 641 ¦ 752 ¦ 379 ¦ 770 ¦ 435 ¦ 2414 ¦ 1533 ¦ 2482 ¦ 1491 ¦ 3021 ¦ 1502 ¦ 3205 ¦ 2344 ¦ 2616 ¦ 2039 | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Earthing Status | 425 | 29 | earthing_tack, foundation, project_details, summary_status, supply, survey_soil, visual_l2 | R3: NOA Date: 22-July-2024 ¦ Completion Date : 21-June-2026 ¦ Date : 27-05-25 R4: SUPPLY VALUE = 458 Cr. ¦ SERVICE VALUE = 94.23 Cr. ¦ F&I VALUE = 9.48 Cr. ¦ 561.71 R5: Sr. No. ¦ Activity ¦ UOM ¦ Total Qty. ¦ L2 Qty. ¦ Completed ¦ Balance ¦ Submitted ¦ WIP ¦ Remarks R6: 1 ¦ Details Survey ¦ Kms ¦ 136.705 ¦ 126 ¦ 126.32400000000001 ¦ 10.381 ¦ 10.381 R7: 2 ¦ Check Survey ¦ Kms ¦ 136.705 ¦ 126 ¦ 108.679 ¦ 28.02600000000001 | 765 kV D/C BEAWAR MANDSAUR TRANSMISSION LINE PROGRESS SUMMARY DETAIL NOA Date: 22-July-2024 ¦ Completion Date : 21-June-2026 ¦ Date : 27-05-25 SUPPLY VALUE = 458 Cr. ¦ SERVICE VALUE = 94.23 Cr. ¦ F&I VALUE = 9.48 Cr. ¦ 561.71 Sr. No. ¦ Activity ¦ UOM ¦ Total Qty. ¦ L2 Qty. ¦ Completed ¦ Balance ¦ Submitted ¦ WIP ¦ Remarks 1 ¦ Details Survey ¦ Kms ¦ 136.705 ¦ 126 ¦ 126.32400000000001 ¦ 10.381 ¦ 10.381 2 ¦ Check Survey ¦ Kms ¦ 136.705 ¦ 126 ¦ 108.679 ¦ 28.02600000000001 3 ¦ Soil Testing ¦ Nos ¦ 34 ¦ 34 | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Sheet4 | 504 | 38 | foundation | R9: FDN ¦ Ear ¦ ERE ¦ STR R25: 338 ¦ 370 ¦ 380 ¦ 400 ¦ 418 ¦ 418.579 ¦ 425 ¦ Completed ¦ 312 ¦ Completed ¦ 381 ¦ Completed ¦ 455 ¦ Completed ¦ 376 ¦ Completed ¦ 401 ¦ Completed ¦ 428 ¦ Completed R27: Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed R36: 461.164 ¦ 373 ¦ 334.67 ¦ 321.15 ¦ 391 ¦ 388 ¦ 392 ¦ 293 ¦ 274 ¦ 218 ¦ Completed ¦ 422 ¦ 339 ¦ 423.633 ¦ Completed ¦ 335.192 ¦ Completed ¦ 326.577 ¦ Completed ¦ 15 R38: X ¦ Completed ¦ Completed ¦ Completed | V I S U A L C H A R T DATE : ¦ 2025-11-20 00:00:00 Name of Line : ¦ 765 KV D/C HEXA BEAWAR MANDSAUR T/L Project Code: ¦ TA505 Name of Executing Agency: ¦ M/s. KEC INTERNATIONAL LTD. FDN ¦ Ear ¦ ERE ¦ STR COMMON TOWER 99/0 ¦ 99/1 ¦ 99/2 ¦ 99/3 ¦ 99/4 ¦ 4 | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Sheet3 | 23 | 10 |  | R1: SL ¦ Loc No ¦ TOT ¦ SL ¦ Loc No ¦ TOT ¦ SL ¦ Loc No ¦ TOT | SL ¦ Loc No ¦ TOT ¦ SL ¦ Loc No ¦ TOT ¦ SL ¦ Loc No ¦ TOT 1 ¦ 103/5 ¦ DA+0 ¦ 1 ¦ 126/1 ¦ DA+9 (RC) ¦ 1 ¦ 178/2 ¦ DA+6 2 ¦ 99/4 ¦ DA+0 ¦ 2 ¦ 149B/1 ¦ DB2+15 ¦ 2 ¦ 165/0 ¦ DB1+6 3 ¦ 99/5 ¦ DA+0 ¦ 3 ¦ 149B/2 ¦ DA+6 ¦ 3 ¦ 168/0 ¦ DC2+0 4 ¦ 99/3 ¦ DA+0 ¦ 4 ¦ 100/0 ¦ DD45+0 ¦ 4 ¦ 180/0 ¦ DC2+15 5 ¦ 99/2 ¦ DA+6 ¦ 5 ¦ 155/0 ¦ DC2+0 ¦ 5 ¦ 178/4 ¦ DA-3 6 ¦ 99/1 ¦ DA+6 ¦ 6 ¦ 99/8 ¦ DA+6 ¦ 6 ¦ 178/5 ¦ DA+0 7 ¦ 99/7 ¦ DA+0 ¦ 7 ¦ 149B/4 ¦ DA+0 (RC) ¦ 7 ¦ 179/1 ¦ DA+3 | ok
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | 2026-05-19 | Sheet2 | 1 | 1 |  |  |  | ok
TA 506 | TA 506 - DPR - 2026-05-21.xlsx | 2026-05-21 | DPR_TA-506 | 27 | 17 | foundation, project_details, summary_status, supply, survey_soil | R5: NOA Date :- 23-July-2024 ¦ Completion Date :- 22-June-2026 ¦ Date :- 20 May 2026. R6: SUPPLY VALUE = 477.03 Cr. ¦ SERVICE VALUE = 105.43 Cr. ¦ F&I VALUE = 11.45 Cr. R7: PARTICULARS ¦ UOM ¦ Total ¦ Comp ¦ Balance ¦ 2026-04-01 00:00:00 ¦ WIP ¦ Cumulative ¦ 2026-06-01 00:00:00 ¦ 2026-07-02 00:00:00 ¦ Remarks R8: Qty ¦ Till ¦ as on ¦ Plan ¦ Actual ¦ Plan ¦ Plan R10: Detail Survey ¦ KM ¦ 223 ¦ 223 ¦ 223 | LINE NAME- : 400 KV D/C Sirohi - Chittorgarh TL CLIENT-POWERGRID SIROHI TRANSMISSION LIMITED (POWER GRID CORPORATION OF INDIA) DAILY PROGRESS REPORT (TA-506) NOA Date :- 23-July-2024 ¦ Completion Date :- 22-June-2026 ¦ Date :- 20 May 2026. SUPPLY VALUE = 477.03 Cr. ¦ SERVICE VALUE = 105.43 Cr. ¦ F&I VALUE = 11.45 Cr. PARTICULARS ¦ UOM ¦ Total ¦ Comp ¦ Balance ¦ 2026-04-01 00:00:00 ¦ WIP ¦ Cumulative ¦ 2026-06-01 00:00:00 ¦ 2026-07-02 00:00:00 ¦ Remarks Qty ¦ Till ¦ as on ¦ Plan ¦ Actual ¦ Plan ¦ Plan 2026-04-01 00:00:00 ¦ 1 May'26 | repaired_defined_names (ValueError)
TA 506 | TA 506 - DPR - 2026-05-21.xlsx | 2026-05-21 | Erection compiled | 694 | 12 | earthing_tack, erection, project_details, summary_status | R3: Details of Erection ¦ 6686.852281000004 ¦ 898.2448669067312 ¦ 2026-05-19 00:00:00 ¦ Tack Welding R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Location No ¦ Type of Tower ¦ Starting Date ¦ Completion date ¦ Gang name ¦ Tower Weight ¦ Revenue ¦ Name of Supervisor ¦ Status R5: 105 ¦ 137/2 ¦ DA+0 ¦ 2025-08-27 00:00:00 ¦ 2025-09-01 00:00:00 ¦ TEJAL ¦ 16.966724 ¦ 2.2791400349199997 ¦ Sahadeb Gope ¦ Completed R6: 106 ¦ 13/2 ¦ DA+9 ¦ 2025-09-01 00:00:00 ¦ 2025-09-05 00:00:00 ¦ Shri Karni Construction ¦ 16.966724 ¦ 2.2791400349199997 ¦ Anil Kumar ¦ Completed R7: 107 ¦ 33/0 ¦ DC1+6 ¦ 2025-08-27 00:00:00 ¦ 2025-09-05 00:00:00 ¦ Shri Karni Construction ¦ 37.205740999999996 ¦ 4.99784718853 ¦ Anil Kumar ¦ Completed | KEC International Limited TA506 : 400 KV D/C Sirohi - Chittorgarh TL Details of Erection ¦ 6686.852281000004 ¦ 898.2448669067312 ¦ 2026-05-19 00:00:00 ¦ Tack Welding CUMM. SR.NO ¦ MONTH SR.NO. ¦ Location No ¦ Type of Tower ¦ Starting Date ¦ Completion date ¦ Gang name ¦ Tower Weight ¦ Revenue ¦ Name of Supervisor ¦ Status 105 ¦ 137/2 ¦ DA+0 ¦ 2025-08-27 00:00:00 ¦ 2025-09-01 00:00:00 ¦ TEJAL ¦ 16.966724 ¦ 2.2791400349199997 ¦ Sahadeb Gope ¦ Completed 106 ¦ 13/2 ¦ DA+9 ¦ 2025-09-01 00:00:00 ¦ 2025-09-05 00:00:00 ¦ Shri Karni Construction ¦ 16.966724 ¦ 2.2791400349199997 ¦ Anil Kumar ¦ Completed 107 ¦ 33/0 ¦ DC1+6 ¦ 2025-08-27 00:00:00 ¦ 2025-09-05 00:00:00 ¦ Shri Karni Construction ¦ 37.205740999999996 ¦ 4.99784718853 ¦ Anil Kumar ¦ Completed 108 ¦ 183/4 ¦ DA+9 ¦ 2025-08-31 00:00:00 ¦ 2025-09-04 00:00:00 ¦ PANKAJ -1 ¦ 16.966724 ¦ 2.2791400349199997 ¦ Bhola Karmakar ¦ Completed | repaired_defined_names (ValueError)
TA 506 | TA 506 - DPR - 2026-05-21.xlsx | 2026-05-21 | Tightening | 465 | 38 | project_details, summary_status | R1: SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Tower Tightening ¦ Remark R2: 1 ¦ 1/0 ¦ DD60+0 ¦ 2025-12-02 00:00:00 ¦ 39.59669499999999 ¦ COMPLETED ¦ 2025-12-11 00:00:00 ¦ Karni Const. 1 ¦ 31 ¦ 10 R3: 2 ¦ 1/1 ¦ DA+3 ¦ 2025-10-16 00:00:00 ¦ 18.118816 ¦ COMPLETED ¦ 2025-10-18 00:00:00 ¦ Gulab Mahto ¦ 31 ¦ 11 R4: 3 ¦ 1/10 ¦ DA+0 ¦ 2025-11-05 00:00:00 ¦ 16.966724 ¦ COMPLETED ¦ 2025-11-07 00:00:00 ¦ Gulab Mahto ¦ 31 ¦ 11 R5: 4 ¦ 1/2 ¦ DA+3 ¦ 2025-10-19 00:00:00 ¦ 18.118816 ¦ COMPLETED ¦ 2025-10-21 00:00:00 ¦ Gulab Mahto ¦ 31 ¦ 11 | SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Tower Tightening ¦ Remark 1 ¦ 1/0 ¦ DD60+0 ¦ 2025-12-02 00:00:00 ¦ 39.59669499999999 ¦ COMPLETED ¦ 2025-12-11 00:00:00 ¦ Karni Const. 1 ¦ 31 ¦ 10 2 ¦ 1/1 ¦ DA+3 ¦ 2025-10-16 00:00:00 ¦ 18.118816 ¦ COMPLETED ¦ 2025-10-18 00:00:00 ¦ Gulab Mahto ¦ 31 ¦ 11 3 ¦ 1/10 ¦ DA+0 ¦ 2025-11-05 00:00:00 ¦ 16.966724 ¦ COMPLETED ¦ 2025-11-07 00:00:00 ¦ Gulab Mahto ¦ 31 ¦ 11 4 ¦ 1/2 ¦ DA+3 ¦ 2025-10-19 00:00:00 ¦ 18.118816 ¦ COMPLETED ¦ 2025-10-21 00:00:00 ¦ Gulab Mahto ¦ 31 ¦ 11 5 ¦ 1/3 ¦ DA+0 ¦ 2025-10-22 00:00:00 ¦ 16.966724 ¦ COMPLETED ¦ 2025-10-25 00:00:00 ¦ Gulab Mahto ¦ 31 ¦ 11 6 ¦ 1/4 ¦ DA-3 ¦ 2025-12-11 00:00:00 ¦ 15.857766 ¦ COMPLETED ¦ 2025-12-18 00:00:00 ¦ Karni Const. 1 ¦ 31 ¦ 10 7 ¦ 1/5 ¦ DA+3 ¦ 2025-12-12 00:00:00 ¦ 18.118816 ¦ COMPLETED ¦ 2025-12-22 00:00:00 ¦ Karni Const. 1 ¦ 31 ¦ 10 | repaired_defined_names (ValueError)
TA 506 | TA 506 - DPR - 2026-05-21.xlsx | 2026-05-21 | Stringing | 232 | 16368 | project_details, stretch_readiness, stringing, summary_status, supply | R2: S.no ¦ Sec ¦ From AP ¦ To AP ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name ¦ Gang Strength R3: 1 ¦ Sirohi ¦ 1/0 ¦ 2/0 ¦ 4424.083 ¦ TSE ¦ Ready ¦ 2026-01-18 00:00:00 ¦ 2026-01-22 00:00:00 ¦ 4424.083 ¦ 2026-01-26 00:00:00 ¦ 2026-01-31 00:00:00 ¦ Completed ¦ 4424.083 ¦ Completed ¦ National Construction ¦ 40 ¦ 12 R4: 2 ¦ Sirohi ¦ 5/0 ¦ 6/0 ¦ 4949.33 ¦ TSE ¦ Ready ¦ 2026-01-22 00:00:00 ¦ 2026-01-27 00:00:00 ¦ 4949.33 ¦ 2026-01-27 00:00:00 ¦ 2026-02-05 00:00:00 ¦ Completed ¦ 4949.33 ¦ Completed ¦ National Construction ¦ 40 ¦ 12 R5: 3 ¦ Sirohi ¦ 48/0 ¦ 50/0 ¦ 688.47 ¦ TSE ¦ Ready ¦ 2025-12-19 00:00:00 ¦ 2025-12-30 00:00:00 ¦ 688.47 ¦ 2026-01-15 00:00:00 ¦ 2026-01-20 00:00:00 ¦ Completed ¦ 688.47 ¦ Completed ¦ Jahangir Alam ¦ 39 ¦ 16 R6: 4 ¦ Sirohi ¦ 50/0 ¦ 51/0 ¦ 1160.08 ¦ TSE ¦ Ready ¦ 2025-12-19 00:00:00 ¦ 2025-12-30 00:00:00 ¦ 1160.08 ¦ 2026-01-17 00:00:00 ¦ 2026-01-22 00:00:00 ¦ Completed ¦ 1160.08 ¦ Completed ¦ Jahangir Alam ¦ 39 ¦ 16 | Number of TSE ¦ 2 S.no ¦ Sec ¦ From AP ¦ To AP ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name ¦ Gang Strength 1 ¦ Sirohi ¦ 1/0 ¦ 2/0 ¦ 4424.083 ¦ TSE ¦ Ready ¦ 2026-01-18 00:00:00 ¦ 2026-01-22 00:00:00 ¦ 4424.083 ¦ 2026-01-26 00:00:00 ¦ 2026-01-31 00:00:00 ¦ Completed ¦ 4424.083 ¦ Completed ¦ National Construction ¦ 40 ¦ 12 2 ¦ Sirohi ¦ 5/0 ¦ 6/0 ¦ 4949.33 ¦ TSE ¦ Ready ¦ 2026-01-22 00:00:00 ¦ 2026-01-27 00:00:00 ¦ 4949.33 ¦ 2026-01-27 00:00:00 ¦ 2026-02-05 00:00:00 ¦ Completed ¦ 4949.33 ¦ Completed ¦ National Construction ¦ 40 ¦ 12 3 ¦ Sirohi ¦ 48/0 ¦ 50/0 ¦ 688.47 ¦ TSE ¦ Ready ¦ 2025-12-19 00:00:00 ¦ 2025-12-30 00:00:00 ¦ 688.47 ¦ 2026-01-15 00:00:00 ¦ 2026-01-20 00:00:00 ¦ Completed ¦ 688.47 ¦ Completed ¦ Jahangir Alam ¦ 39 ¦ 16 4 ¦ Sirohi ¦ 50/0 ¦ 51/0 ¦ 1160.08 ¦ TSE ¦ Ready ¦ 2025-12-19 00:00:00 ¦ 2025-12-30 00:00:00 ¦ 1160.08 ¦ 2026-01-17 00:00:00 ¦ 2026-01-22 00:00:00 ¦ Completed ¦ 1160.08 ¦ Completed ¦ Jahangir Alam ¦ 39 ¦ 16 5 ¦ Sirohi ¦ 2/0 ¦ 2A/0 ¦ 3318.603 ¦ TSE ¦ Ready ¦ 2026-02-15 00:00:00 ¦ 2026-02-19 00:00:00 ¦ 3318.603 ¦ 2026-02-22 00:00:00 ¦ 2026-02-23 00:00:00 ¦ Completed ¦ 3318.603 ¦ Completed ¦ National Construction ¦ 40 ¦ 12 6 ¦ Sirohi ¦ 51/0 ¦ 51A/0 ¦ 1244.855 ¦ TSE ¦ Ready ¦ 2026-01-17 00:00:00 ¦ 2026-01-20 00:00:00 ¦ 1244.855 ¦ 2026-01-27 00:00:00 ¦ 2026-01-31 00:00:00 ¦ Completed ¦ 1244.855 ¦ Completed ¦ Jahangir Alam ¦ 39 ¦ 16 | repaired_defined_names (ValueError)
TA 506 | TA 506 - DPR - 2026-05-21.xlsx | 2026-05-21 | Visual Chart | 477 | 41 | foundation, row_hindrance, visual_l2 | R9: FDN ¦ EAR ¦ ERE ¦ STR R14: SS Land ¦ 175 ¦ Completed ¦ 396 ¦ Completed ¦ 427 ¦ Completed ¦ 408 ¦ Completed ¦ 356 ¦ Completed ¦ 380 ¦ Completed ¦ 433 ¦ Completed ¦ 409 ¦ Completed ¦ 429 ¦ Completed ¦ 403 R16: Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed ¦ Completed R20: #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ Completed R22: 420 ¦ Completed ¦ 402 ¦ Completed ¦ 371 ¦ Completed ¦ 341 ¦ Completed ¦ 354 ¦ Completed ¦ 358 ¦ Completed ¦ 342 ¦ Completed ¦ 352.603 ¦ Completed ¦ 351 ¦ Completed ¦ 390 ¦ ROW | V I S U A L C H A R T DATE : ¦ 2026-05-19 00:00:00 Name of Line : ¦ 400 kV D/C Sirohi Chittorgarh TL Project Code: ¦ TA 506 Name of Contractor: ¦ M/s. KEC INTERNATIONAL LTD. FDN ¦ EAR ¦ ERE ¦ STR SIROHI GANTRY ¦ 1/0 ¦ 1/1 ¦ 1/2 ¦ 1/3 ¦ 1/4 ¦ 1/5 ¦ 1/6 ¦ 1/7 ¦ 1/8 ¦ 1/9 ¦ 1/10 ¦ 2/0 ¦ 2/1 #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! ¦ #REF! | repaired_defined_names (ValueError)
TA 506 | TA 506 - DPR - 2026-05-21.xlsx | 2026-05-21 | Project Details | 21 | 11 | project_details | R1: Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Engineer/Supervisor | Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Engineer/Supervisor TA 506 ¦ 400 KV D/C Sirohi - Chittorgarh Line ¦ PGCIL ¦ 2024-07-23 00:00:00 ¦ 2026-06-22 00:00:00 ¦ Mr. Abir Kumar Das ¦ Mr. Nabajit Baruah ¦ Mr. Rajiv Sharma ¦ Dharmendra Pandey ¦ Anil Kumar Rajkumar Tomar ¦ Bipattaran Dolui Rajib Biswas ¦ Sahadeo Gope Abhishek Kumar ¦ Sunil Kumar Krishna Prasad ¦ Mrityunjay Thakur Bhola Karmakat Ram Sekhar | repaired_defined_names (ValueError)
TA 506 | TA 506 - DPR - 2026-05-21.xlsx | 2026-05-21 | Location Summary | 782 | 21 | earthing_tack, erection, foundation, summary_status | R2: S. No. ¦ No of ¦ Location ¦ Type of ¦ RC ¦ Span ¦ Cumm. ¦ DS Status as on ¦ 306 ¦ 292 ¦ 257 ¦ 102 ¦ 26 ¦ Remarks R3: AP ¦ Tower No. ¦ Tower ¦ Length (m) ¦ Span (km) ¦ 2025-11-01 00:00:00 ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Tack welding ¦ SPT R6: 3 ¦ AP-1 ¦ 1/0 ¦ DD60+0 ¦ T ¦ 0.15 ¦ Approved ¦ Completed ¦ Completed ¦ Completed R8: 2 ¦ AP-2A ¦ 2A/0 ¦ DD45+0 ¦ T ¦ 0.44020000000000004 ¦ Approved ¦ Completed ¦ Completed R10: 3 ¦ AP-3 ¦ 2A/1 ¦ DA+0 ¦ 0.8182 ¦ Approved ¦ Completed ¦ Completed ¦ Completed | Over all Tower Location details S. No. ¦ No of ¦ Location ¦ Type of ¦ RC ¦ Span ¦ Cumm. ¦ DS Status as on ¦ 306 ¦ 292 ¦ 257 ¦ 102 ¦ 26 ¦ Remarks AP ¦ Tower No. ¦ Tower ¦ Length (m) ¦ Span (km) ¦ 2025-11-01 00:00:00 ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Tack welding ¦ SPT Gantry ¦ Gantry Gantry ¦ 150.014 3 ¦ AP-1 ¦ 1/0 ¦ DD60+0 ¦ T ¦ 0.15 ¦ Approved ¦ Completed ¦ Completed ¦ Completed 1/0 ¦ 290.21 2 ¦ AP-2A ¦ 2A/0 ¦ DD45+0 ¦ T ¦ 0.44020000000000004 ¦ Approved ¦ Completed ¦ Completed | repaired_defined_names (ValueError)
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | VC-765kV MKTL | 0 | 0 | erection, foundation, visual_l2 | R2: Visual Chart of 765kV Line ¦ Date ¦ 2026-05-18 00:00:00 ¦ FDN ¦ EARTH ¦ EREC ¦ T/W ¦ Strng ¦ Length in MTR R125: RC ¦ ROW ¦ ROW R146: Gas Pipe Line BPCL ¦ Power Line Crossing ¦ Route Finalization pending on account of daiversion due to solar plant R154: Route Finalization pending on account of daiversion due to solar plant ¦ NH Crossinng ¦ Water Pipe Line ¦ Power Line Crossing R165: ROW ¦ ROW ¦ RC | #ERROR! Visual Chart of 765kV Line ¦ Date ¦ 2026-05-18 00:00:00 ¦ FDN ¦ EARTH ¦ EREC ¦ T/W ¦ Strng ¦ Length in MTR 264 ¦ 232 ¦ 198 ¦ 0 ¦ 0 ¦ 118387.007 RC ¦ RC 9.0 ¦ 7.0 ¦ 2.0 ¦ 5498.422 107.961 ¦ DD60+0 ¦ 148.478 ¦ DD60+0 ¦ 408.832 ¦ DD45+3 ¦ 380.0 ¦ DA(-)1.5 ¦ 422.0 ¦ DA+6 ¦ 408.352 ¦ DC1+0 ¦ 419.453 ¦ DA+9 ¦ 381.0 ¦ DA+9 ¦ 417.0 ¦ DA(-)3 ¦ 417.0 ¦ DA+6 1/0 ¦ 2/0 ¦ 3/0 ¦ 3/1 ¦ 3/2 ¦ 4/0 ¦ 4/1 ¦ 4/2 ¦ 4/3 ¦ 4/4 ¦ 4/5 ¦ 4/6 ¦ 5/0 ¦ 5/1 MP ¦ MP ¦ MP ¦ MP ¦ MP ¦ MP ¦ MP ¦ MP ¦ MP ¦ MP ¦ MP ¦ MP ¦ MP ¦ MP | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | SUMMARY | 0 | 0 | earthing_tack, erection, foundation, project_details, stringing, summary_status, survey_soil, visual_l2 | R5: Activity ¦ LOA Quantity ¦ Final Estimated Quantity ¦ Cum. L2 till Last Month ¦ Cum Progress till Last Month ¦ L2 for present Month ¦ Plan for the Month ¦ Progress for Today ¦ Progress for the Month ¦ Cum. L2 till date ¦ Cum. Progress till date ¦ Balance Work ¦ Under Progress ¦ Gangs at Present ¦ Completed LOC. (Today) ¦ Remarks R7: Foundation (Loc) ¦ 309.0 ¦ 309.0 ¦ 306.0 ¦ 258.0 ¦ 25.0 ¦ 6 ¦ 306 ¦ 264 ¦ 45 ¦ 2/0, 3/2, 47/0, 47/5, 47/10, 51/0, 63/0 ¦ 4.0 R8: Earthing (Loc) ¦ 309.0 ¦ 309.0 ¦ 262.0 ¦ 228.0 ¦ 25.0 ¦ 25.0 ¦ 4 ¦ 287 ¦ 232 ¦ 77 R9: Erection (Loc) ¦ 309.0 ¦ 309.0 ¦ 270.0 ¦ 180.0 ¦ 20.0 ¦ 45.0 ¦ 18 ¦ 290 ¦ 198 ¦ 111 ¦ 23/1, 28/0, 41/0, 41/3, 46A/2, 48/1, 49/2, 67/1 ¦ 8.0 R10: Stringing (Km) ¦ Rough Sag ¦ 118.397 ¦ 118.397 ¦ 0 ¦ 0 ¦ 118.4 | Name of Line: 765 kV D/C Mandsaur - Kurawar (Part-1)Transmission Line(WZ-4) Agency: - M/s KEC INTERNATIONAL LIMITED NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 Date: ¦ 2026-05-18 00:00:00 Activity ¦ LOA Quantity ¦ Final Estimated Quantity ¦ Cum. L2 till Last Month ¦ Cum Progress till Last Month ¦ L2 for present Month ¦ Plan for the Month ¦ Progress for Today ¦ Progress for the Month ¦ Cum. L2 till date ¦ Cum. Progress till date ¦ Balance Work ¦ Under Progress ¦ Gangs at Present ¦ Completed LOC. (Today) ¦ Remarks Foundation (Loc) ¦ 309.0 ¦ 309.0 ¦ 306.0 ¦ 258.0 ¦ 25.0 ¦ 6 ¦ 306 ¦ 264 ¦ 45 ¦ 2/0, 3/2, 47/0, 47/5, 47/10, 51/0, 63/0 ¦ 4.0 Earthing (Loc) ¦ 309.0 ¦ 309.0 ¦ 262.0 ¦ 228.0 ¦ 25.0 ¦ 25.0 ¦ 4 ¦ 287 ¦ 232 ¦ 77 Erection (Loc) ¦ 309.0 ¦ 309.0 ¦ 270.0 ¦ 180.0 ¦ 20.0 ¦ 45.0 ¦ 18 ¦ 290 ¦ 198 ¦ 111 ¦ 23/1, 28/0, 41/0, 41/3, 46A/2, 48/1, 49/2, 67/1 ¦ 8.0 | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | FDN pivot | 0 | 0 | foundation |  |  | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | Erc pivot | 0 | 0 |  |  |  | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | ERECTION | 0 | 0 | erection, project_details, summary_status | R2: SL NO. ¦ LOC No. ¦ Tower Type ¦ District wise section ¦ STATUS ¦ STARTING DATE ¦ ENDING DATE ¦ Work starting month ¦ Work completion Month ¦ Sub-Contractor ¦ JMC R3: 1.0 ¦ 16/4 ¦ DA+0 ¦ Gantry - AP39/0 ¦ COMPLETED ¦ 22/08/2025 ¦ 2025-09-03 00:00:00 ¦ DEVI CONST.-I R4: 2.0 ¦ 13/2 ¦ DA+0 ¦ Gantry - AP39/0 ¦ COMPLETED ¦ 22/08/2025 ¦ 15.09.2025 ¦ DEONATH MAHATO R5: 3.0 ¦ 8/5 ¦ DA+0 ¦ Gantry - AP39/0 ¦ COMPLETED ¦ 25/08/2025 ¦ 08.09.2025 ¦ JAWALA SINGH R6: 4.0 ¦ 12/6 ¦ DA+0 ¦ Gantry - AP39/0 ¦ COMPLETED ¦ 25/08/2025 ¦ 18.09.2025 ¦ MODINA INDIA | ERECTION-STATUS SL NO. ¦ LOC No. ¦ Tower Type ¦ District wise section ¦ STATUS ¦ STARTING DATE ¦ ENDING DATE ¦ Work starting month ¦ Work completion Month ¦ Sub-Contractor ¦ JMC 1.0 ¦ 16/4 ¦ DA+0 ¦ Gantry - AP39/0 ¦ COMPLETED ¦ 22/08/2025 ¦ 2025-09-03 00:00:00 ¦ DEVI CONST.-I 2.0 ¦ 13/2 ¦ DA+0 ¦ Gantry - AP39/0 ¦ COMPLETED ¦ 22/08/2025 ¦ 15.09.2025 ¦ DEONATH MAHATO 3.0 ¦ 8/5 ¦ DA+0 ¦ Gantry - AP39/0 ¦ COMPLETED ¦ 25/08/2025 ¦ 08.09.2025 ¦ JAWALA SINGH 4.0 ¦ 12/6 ¦ DA+0 ¦ Gantry - AP39/0 ¦ COMPLETED ¦ 25/08/2025 ¦ 18.09.2025 ¦ MODINA INDIA 5.0 ¦ 12/1 ¦ DA+3 ¦ Gantry - AP39/0 ¦ COMPLETED ¦ 02.09.2025 ¦ 23.09.2025 ¦ OM CONSTRUCTION 6.0 ¦ 15/2 ¦ DA+3 ¦ Gantry - AP39/0 ¦ COMPLETED ¦ 02.09.2025 ¦ 12.09.2025 ¦ HEMLAL MAHATO-I (Anita Devi) | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | FOUNDATION | 0 | 0 | earthing_tack, foundation, summary_status | R2: SL NO. ¦ LOC No. ¦ District wise section ¦ TOWER-TYPE ¦ CLASSIFICATION ¦ STATUS ¦ Man. P ¦ STARTING DATE ¦ ENDING DATE ¦ Work started month ¦ Completed month ¦ Sub-Contractor ¦ JMC ¦ EARTHING ¦ TFR R3: 1.0 ¦ 8/1 ¦ Gantry - AP39/0 ¦ DA+0 ¦ DFR ¦ COMPLETED ¦ 2025-01-01 00:00:00 ¦ JSC Enterprises ¦ DONE ¦ COMPLETED R4: 2.0 ¦ 8/3 ¦ Gantry - AP39/0 ¦ DA+3 ¦ DFR ¦ COMPLETED ¦ 2025-01-01 00:00:00 ¦ JSC Enterprises ¦ DONE ¦ COMPLETED R5: 3.0 ¦ 8/4 ¦ Gantry - AP39/0 ¦ DA+3 ¦ DFR ¦ COMPLETED ¦ 2025-01-01 00:00:00 ¦ JSC Enterprises ¦ DONE ¦ COMPLETED R6: 4.0 ¦ 8/6 ¦ Gantry - AP39/0 ¦ DA+0 ¦ DFR ¦ COMPLETED ¦ 2025-01-01 00:00:00 ¦ Afflux Construction ¦ DONE ¦ COMPLETED | FOUNDATION-STATUS SL NO. ¦ LOC No. ¦ District wise section ¦ TOWER-TYPE ¦ CLASSIFICATION ¦ STATUS ¦ Man. P ¦ STARTING DATE ¦ ENDING DATE ¦ Work started month ¦ Completed month ¦ Sub-Contractor ¦ JMC ¦ EARTHING ¦ TFR 1.0 ¦ 8/1 ¦ Gantry - AP39/0 ¦ DA+0 ¦ DFR ¦ COMPLETED ¦ 2025-01-01 00:00:00 ¦ JSC Enterprises ¦ DONE ¦ COMPLETED 2.0 ¦ 8/3 ¦ Gantry - AP39/0 ¦ DA+3 ¦ DFR ¦ COMPLETED ¦ 2025-01-01 00:00:00 ¦ JSC Enterprises ¦ DONE ¦ COMPLETED 3.0 ¦ 8/4 ¦ Gantry - AP39/0 ¦ DA+3 ¦ DFR ¦ COMPLETED ¦ 2025-01-01 00:00:00 ¦ JSC Enterprises ¦ DONE ¦ COMPLETED 4.0 ¦ 8/6 ¦ Gantry - AP39/0 ¦ DA+0 ¦ DFR ¦ COMPLETED ¦ 2025-01-01 00:00:00 ¦ Afflux Construction ¦ DONE ¦ COMPLETED 5.0 ¦ 16/4 ¦ Gantry - AP39/0 ¦ DA+0 ¦ DFR ¦ COMPLETED ¦ 2025-01-01 00:00:00 ¦ JSC Enterprises ¦ DONE 6.0 ¦ 8/5 ¦ Gantry - AP39/0 ¦ DA+0 ¦ DFR ¦ COMPLETED ¦ 2025-02-01 00:00:00 ¦ JSC Enterprises ¦ DONE ¦ COMPLETED | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | XING | 0 | 0 | row_hindrance, statutory_crossing, summary_status, survey_soil | R2: Sl. No. ¦ Location No. ¦ Affected Towers/ Locations (Nos) ¦ Area of concern ¦ Name of Transmission Line/Section in between stations ¦ Authority ¦ Type ¦ Proposal Submission date ¦ Status as on date ¦ Place of follow up ¦ Expected date for Work Permission ¦ Responsibility KEC ¦ Responsibility Power Grid ¦ Remarks R4: i) ¦ 11/0-12/0 ¦ 2.0 ¦ Power Line Crossing of Power Grid ¦ EXISTING 400 KV DC NEEMUCH-MANDSAUR TRANSMISSION LINE ¦ Power Grid ¦ OH ¦ 22.05.2025 ¦ Joint inspection Done date on- 04.06.25 ¦ Power Grid Vadodara (RHQ), Neemuch Sub-station of Powergrid ¦ Approved On 21.07.2025 ¦ Devesh ¦ Onkar singh Bharti(DGM) R5: ii) ¦ 25/0-26/0 ¦ 2.0 ¦ Power Line Crossing of MPPTCL ¦ 220 KV DC MANDSAUR - NIPANIA TL ¦ Power Grid ¦ OH ¦ 22.05.2025 (Revised submission on 12.06 25) ¦ Joint inspection Done date on- 04.06.25 ¦ Office of Chief Enginneer, MPPTCL, Jabalpur ¦ Approved On 18.08.2025 R9: vi) ¦ 54/0-55/0 ¦ 2.0 ¦ 220kV D/C Badod-Nalkheda T/Line ¦ Power Grid ¦ OH ¦ Submission on 18.09.2025 ¦ pending due to finalization of survey for avoiding forest in between section 52/0 - 58/0 ¦ - ¦ - ¦ - ¦ - R11: viii) ¦ 42/0-43/0 ¦ 2.0 ¦ Power Line Crossing of RVPNL ¦ 132 KV SC BHAWANI MANDI - DAG T/L (RRVPNL) ¦ Power Grid ¦ OH ¦ 22.05.2025 ¦ Approved on 04.07.2025 ¦ Office of Chief Enginneer, RVPNL, Jaipur ¦ Approved on 04.07.2025 ¦ Devesh ¦ Onkar singh Bharti(DGM) | Sl. No. ¦ Location No. ¦ Affected Towers/ Locations (Nos) ¦ Area of concern ¦ Name of Transmission Line/Section in between stations ¦ Authority ¦ Type ¦ Proposal Submission date ¦ Status as on date ¦ Place of follow up ¦ Expected date for Work Permission ¦ Responsibility KEC ¦ Responsibility Power Grid ¦ Remarks 1.0 ¦ Power Line Crossing i) ¦ 11/0-12/0 ¦ 2.0 ¦ Power Line Crossing of Power Grid ¦ EXISTING 400 KV DC NEEMUCH-MANDSAUR TRANSMISSION LINE ¦ Power Grid ¦ OH ¦ 22.05.2025 ¦ Joint inspection Done date on- 04.06.25 ¦ Power Grid Vadodara (RHQ), Neemuch Sub-station of Powergrid ¦ Approved On 21.07.2025 ¦ Devesh ¦ Onkar singh Bharti(DGM) ii) ¦ 25/0-26/0 ¦ 2.0 ¦ Power Line Crossing of MPPTCL ¦ 220 KV DC MANDSAUR - NIPANIA TL ¦ Power Grid ¦ OH ¦ 22.05.2025 (Revised submission on 12.06 25) ¦ Joint inspection Done date on- 04.06.25 ¦ Office of Chief Enginneer, MPPTCL, Jabalpur ¦ Approved On 18.08.2025 iii) ¦ 28/0-29/0 ¦ 2.0 ¦ 220 KV DC SITAMAU-SUWASRA OHTL MPPTCL ¦ Power Grid ¦ OH ¦ 22.05.2025 (Revised submission on 12.06 25, 04.07.2025) ¦ Joint inspection Done date on- 04.06.25 ¦ Approved On 18.08.2025 iv) ¦ 33/0-34/0 ¦ 2.0 ¦ 132KV D/C SUWASARA - BADOD TL (Joint joint inspection Done) ¦ Power Grid ¦ OH ¦ 22.05.2025 (Revised submission on 12.06 25) ¦ Joint inspection Done date on- 04.06.25 ¦ Approved On 18.08.2025 v) ¦ 37/0-38/0 ¦ 2.0 ¦ 220 KV OHTL DC BHANPUR-BAROD MPPTCL ¦ Power Grid ¦ OH ¦ 22.05.2025 (Revised submission on 12.06 25) ¦ Joint inspection Done date on- 04.06.25 ¦ Approved On 18.08.2025 vi) ¦ 54/0-55/0 ¦ 2.0 ¦ 220kV D/C Badod-Nalkheda T/Line ¦ Power Grid ¦ OH ¦ Submission on 18.09.2025 ¦ pending due to finalization of survey for avoiding forest in between section 52/0 - 58/0 ¦ - ¦ - ¦ - ¦ - | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | EARTHING | 0 | 0 | earthing_tack, project_details, row_hindrance, summary_status | R2: SL NO. ¦ LOC NO. ¦ TYPE OF TOWER ¦ TODAY'S PLAN ¦ TODAY'S PROGRESS ¦ TOMMOROW'S PLAN ¦ START DATE ¦ COMPLETION DATE ¦ GANG R3: 1.0 ¦ 8/1 ¦ DA+0 ¦ COMPLETED ¦ 13.05.2025 ¦ 13.05.2025 ¦ JSC CONST. R4: 2.0 ¦ 8/2 ¦ DA+3 ¦ COMPLETED ¦ 13.05.2025 ¦ 13.05.2025 ¦ JSC CONST. R5: 3.0 ¦ 8/3 ¦ DA+3 ¦ COMPLETED ¦ 13.05.2025 ¦ 13.05.2025 ¦ JSC CONST. R6: 4.0 ¦ 20/1 ¦ DA(-)3 ¦ COMPLETED ¦ 13.05.2025 ¦ 13.05.2025 ¦ YATHATHART | EARTHING SL NO. ¦ LOC NO. ¦ TYPE OF TOWER ¦ TODAY'S PLAN ¦ TODAY'S PROGRESS ¦ TOMMOROW'S PLAN ¦ START DATE ¦ COMPLETION DATE ¦ GANG 1.0 ¦ 8/1 ¦ DA+0 ¦ COMPLETED ¦ 13.05.2025 ¦ 13.05.2025 ¦ JSC CONST. 2.0 ¦ 8/2 ¦ DA+3 ¦ COMPLETED ¦ 13.05.2025 ¦ 13.05.2025 ¦ JSC CONST. 3.0 ¦ 8/3 ¦ DA+3 ¦ COMPLETED ¦ 13.05.2025 ¦ 13.05.2025 ¦ JSC CONST. 4.0 ¦ 20/1 ¦ DA(-)3 ¦ COMPLETED ¦ 13.05.2025 ¦ 13.05.2025 ¦ YATHATHART 5.0 ¦ 20/2 ¦ DA(-)3 ¦ COMPLETED ¦ 13.05.2025 ¦ 13.05.2025 ¦ YATHATHART 6.0 ¦ 5/3 ¦ DA+3 ¦ COMPLETED ¦ 14.05.2025 ¦ 14.05.2025 ¦ GM CONST. | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | DPR | 0 | 0 | earthing_tack, erection, foundation, opgw_accessories, project_details, row_hindrance, stringing, summary_status, survey_soil, visual_l2 | R3: Project Name- ¦ 765KV D/C Mandsaur-Kurawar TL line ¦ Effective Date ¦ 26/11/24 ¦ End Date ¦ 25/10/26 ¦ LOA Value ¦ Rs 474. Cr ¦ 'X-ing Status'!A1 R4: Sr. No. ¦ Activity ¦ As per L2 (till May'26) ¦ Cumm. Progress up to last Month ¦ Opening Balance (L2) ¦ Plan for this Month ¦ Today Progress ¦ MTD (Loc) ¦ WIP (Loc) ¦ Cumulative Progress ¦ Balance ¦ Gangs at present ¦ Remarks ¦ Support Required ¦ % Completion ¦ 'L2 Schedule'!A1 R5: 1.0 ¦ Check Survey (Kms) ¦ 118.397 ¦ 118.397 ¦ 0.0 ¦ 0 ¦ 118 ¦ 0 ¦ - ¦ 100% ¦ 'Hindrance Register (Row)'!A1 R6: 2.0 ¦ Foundation (Nos.) ¦ 306.0 ¦ 258.0 ¦ 48 ¦ 25.0 ¦ 6 ¦ 3.0 ¦ 264 ¦ 42 ¦ 3.0 ¦ WIP- 2/0, 3/2, 47/0, 47/5, 47/10 51/0, 63/0 Today Completed - ¦ ROW- 37/10, 61/1, 59/1, 47/0, 41/6, 61/0, 60/0, 65/6 ¦ 86% ¦ Survey!A1 R7: 3.0 ¦ Earthing (Nos.) ¦ 306.0 ¦ 228.0 ¦ 78 ¦ 4 ¦ 1.0 ¦ 232 ¦ 74 ¦ WIP- Today Completed - 4/0 ¦ 76% ¦ Foundation!A1 | Project Code - ¦ TA-509 ¦ Date ¦ 2026-05-18 00:00:00 ¦ Head - T&D ¦ Rajinder Gupta ¦ Head T&D-Central ¦ Nabajit Baruah ¦ Shortcut for previous of Full description Client Name- ¦ PGCIL ¦ Project Manager ¦ Prithviraj Dutta Choudhury ¦ Planning Engineer ¦ Shuvayu Das ¦ Link for go through Project Name- ¦ 765KV D/C Mandsaur-Kurawar TL line ¦ Effective Date ¦ 26/11/24 ¦ End Date ¦ 25/10/26 ¦ LOA Value ¦ Rs 474. Cr ¦ 'X-ing Status'!A1 Sr. No. ¦ Activity ¦ As per L2 (till May'26) ¦ Cumm. Progress up to last Month ¦ Opening Balance (L2) ¦ Plan for this Month ¦ Today Progress ¦ MTD (Loc) ¦ WIP (Loc) ¦ Cumulative Progress ¦ Balance ¦ Gangs at present ¦ Remarks ¦ Support Required ¦ % Completion ¦ 'L2 Schedule'!A1 1.0 ¦ Check Survey (Kms) ¦ 118.397 ¦ 118.397 ¦ 0.0 ¦ 0 ¦ 118 ¦ 0 ¦ - ¦ 100% ¦ 'Hindrance Register (Row)'!A1 2.0 ¦ Foundation (Nos.) ¦ 306.0 ¦ 258.0 ¦ 48 ¦ 25.0 ¦ 6 ¦ 3.0 ¦ 264 ¦ 42 ¦ 3.0 ¦ WIP- 2/0, 3/2, 47/0, 47/5, 47/10 51/0, 63/0 Today Completed - ¦ ROW- 37/10, 61/1, 59/1, 47/0, 41/6, 61/0, 60/0, 65/6 ¦ 86% ¦ Survey!A1 3.0 ¦ Earthing (Nos.) ¦ 306.0 ¦ 228.0 ¦ 78 ¦ 4 ¦ 1.0 ¦ 232 ¦ 74 ¦ WIP- Today Completed - 4/0 ¦ 76% ¦ Foundation!A1 4.0 ¦ Tower Erection (Nos) ¦ 290.0 ¦ 180.0 ¦ 110 ¦ 45.0 ¦ 18 ¦ 10.0 ¦ 198 ¦ 92 ¦ 10.0 ¦ WIP- 23/1, 28/0, 41/0, 41/3, 46A/2, 48/1, 49/2, 67/1 Today Completed - 34/2 ¦ 68% ¦ Earthing!A1 | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | SUPPLY | 0 | 0 | summary_status, supply, visual_l2 | R7: S. No. ¦ Item Name ¦ Supplier Name ¦ Anticipated Qty ¦ UPTO Dec-25 L2 Schedule ¦ Supplied Qty ¦ Supply In progress ¦ Balance supply ¦ Remarks R8: 1.0 ¦ Stub ¦ KEC Int'l Ltd. ¦ 309.0 ¦ 306.0 ¦ 281 ¦ 28 R10: 3.0 ¦ Conductor ¦ Sterlite ¦ 4343.0 ¦ 3900.0 ¦ 4300.418 ¦ 43 ¦ Conductor Qty in KM R12: 5.0 ¦ Insulator ¦ Aditya Birla ¦ 13552.0 ¦ 11388.0 ¦ 12832.0 ¦ 720 ¦ Insulator Qty in Nos ¦ 160KN=5536 ¦ 210KN=7296 R14: 7.0 ¦ OPGW ¦ Nirmal Wire Pvt. Ltd. ¦ 126.0 ¦ 63.0 ¦ 126.0 ¦ OPGW Qty in KM. | Line Name: ¦ 765KV D/C Mandsaur- Kurawar Transmission Line Package: ¦ TA-509 Agency: ¦ M/s KEC International Limited Status as on: ¦ 2026-03-26 00:00:00 Supply Status S. No. ¦ Item Name ¦ Supplier Name ¦ Anticipated Qty ¦ UPTO Dec-25 L2 Schedule ¦ Supplied Qty ¦ Supply In progress ¦ Balance supply ¦ Remarks 1.0 ¦ Stub ¦ KEC Int'l Ltd. ¦ 309.0 ¦ 306.0 ¦ 281 ¦ 28 2.0 ¦ Tower ¦ KEC Int'l Ltd. ¦ 309.0 ¦ 230.0 ¦ 271.0 ¦ 38 | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | CST Gantry To AP 68 Common Poin | 0 | 0 | statutory_crossing, visual_l2 | R6: Sl.No ¦ AP NO. ¦ TOWER NO. ¦ TYPE OF TOWER ¦ DEVIATION ANGLE (Deg) ¦ SPAN (Mtr) ¦ Section Length (m) ¦ CUMULATIVE SPAN ¦ R.L (Mtr) ¦ HT of Tower (Mtr) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ Spherical Coordinate ¦ UTM Coordinates ¦ CROSSING DETAILS ¦ NAME OF VILLAGE ¦ NAME OF TEHSIL ¦ NAME OF STATAT | CLIENT :- POWER GRID CORPORATION OF INDIA LIMITED NAME OF PROJECT :- 765 KV D/C Mandsaur - Kurawar (Part 1) Transmission Line M/s. KEC INTERNATIONAL LIMITED TOWER SCHEDULE SECTION:- GANTRY TO AP 68 LENGTH:- 118.386 KM KEC/TA509/MKTL/CS/AS ON Dt-06.03.2026 Sl.No ¦ AP NO. ¦ TOWER NO. ¦ TYPE OF TOWER ¦ DEVIATION ANGLE (Deg) ¦ SPAN (Mtr) ¦ Section Length (m) ¦ CUMULATIVE SPAN ¦ R.L (Mtr) ¦ HT of Tower (Mtr) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ Spherical Coordinate ¦ UTM Coordinates ¦ CROSSING DETAILS ¦ NAME OF VILLAGE ¦ NAME OF TEHSIL ¦ NAME OF STATAT Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Longitude (Easting) ¦ Latitude (Northing) ¦ Easting ¦ Northing ¦ A ¦ B ¦ C ¦ D Mandsur Gantry ¦ Gantry ¦ 435.03 ¦ 46.3 ¦ 107.961 ¦ 53.9805 ¦ 6.0 ¦ 6.0 ¦ 11.0 ¦ 11.0 ¦ 75°10'24.829"E ¦ 24°12'17.524"N ¦ 517625.299 ¦ 2676919.49 | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | Sheet1 | 0 | 0 | earthing_tack, erection, foundation |  | 'VC-765kV MKTL'!A1 FOUNDATION!A1 EARTHING!A1 ERECTION!A1 TS!A1 | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | SURVEY SUMMARY | 0 | 0 | row_hindrance, statutory_crossing, summary_status, survey_soil | R1: Original Route alignment ¦ KM ¦ 118.288 ¦ 106.341 ¦ 106.341 R2: Detailed Survey ¦ KM ¦ 118.288 ¦ 106.341 ¦ 106.341 R3: Diverted Route Alignment ¦ KM ¦ 1.558 ¦ Pending ¦ True R4: Check Survey ¦ KM ¦ 118.288 ¦ 106.341 ¦ 106.341 R6: Power line Crossings ¦ Nos ¦ 9.0 ¦ 8.0 ¦ 8.0 | Original Route alignment ¦ KM ¦ 118.288 ¦ 106.341 ¦ 106.341 Detailed Survey ¦ KM ¦ 118.288 ¦ 106.341 ¦ 106.341 Diverted Route Alignment ¦ KM ¦ 1.558 ¦ Pending ¦ True Check Survey ¦ KM ¦ 118.288 ¦ 106.341 ¦ 106.341 Crossing Proposals Power line Crossings ¦ Nos ¦ 9.0 ¦ 8.0 ¦ 8.0 NH Crossing ¦ Nos ¦ 3.0 ¦ 1.0 ¦ 1.0 Railway crossing ¦ Nos ¦ 1.0 ¦ 1.0 ¦ NOC Received | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | SURVEY STATUS | 0 | 0 | row_hindrance, statutory_crossing, summary_status, survey_soil | R2: Sl No ¦ SL NO. ¦ AP NO ¦ Towe Type ¦ AP No ¦ Tower Type ¦ Type of Crossings ¦ Line Name ¦ LINE OWNER ¦ Status ¦ Proposal Submitted (Y/N) ¦ Inspection Status (Y/N) ¦ Remarks R3: 1.0 ¦ 1.0 ¦ 11/0 ¦ DD60+25 ¦ 12/0 ¦ DD60+25 (1 MRC) ¦ POWERLINE-XING ¦ EXISTING 400 KV DC NEEMUCH-MANDSAUR TRANSMISSION LINE ¦ Power Grid ¦ APPROVAL-AWAITED ¦ SUBMITTED ¦ JOINT INSPECTION DONE BY 04.06.2025 R4: 2 ¦ 2.0 ¦ 25/0 ¦ DC2+1 ¦ 26/0 ¦ DC2+12 ¦ POWERLINE-XING ¦ 220 KV DC MANDSAUR - NIPANIA TL ¦ MPPTCL ¦ APPROVAL-AWAITED ¦ SUBMITTED ¦ JOINT INSPECTION DONE BY 04.06.2025 R5: 3 ¦ 3.0 ¦ 28/0 ¦ DD45+6 ¦ 29/0 ¦ DD45+18 ¦ POWERLINE-XING ¦ 220 KV DC SITAMAU-SUWASRA OHTL MPPTCL ¦ MPPTCL ¦ APPROVAL-AWAITED ¦ SUBMITTED ¦ JOINT INSPECTION DONE BY 04.06.2025 R6: 4 ¦ 4.0 ¦ 33/0 ¦ DD45+9 ¦ 34/0 ¦ DC1+3 ¦ POWERLINE-XING ¦ 132KV D/C SUWASARA - BADOD TL (Joint joint inspection Done) ¦ MPPTCL ¦ APPROVAL-AWAITED ¦ SUBMITTED ¦ JOINT INSPECTION DONE BY 04.06.2025 | TA-509 765 KV D/C Mandsaur - Kurawar (Part-1)Transmission Line(WZ-4) Sl No ¦ SL NO. ¦ AP NO ¦ Towe Type ¦ AP No ¦ Tower Type ¦ Type of Crossings ¦ Line Name ¦ LINE OWNER ¦ Status ¦ Proposal Submitted (Y/N) ¦ Inspection Status (Y/N) ¦ Remarks 1.0 ¦ 1.0 ¦ 11/0 ¦ DD60+25 ¦ 12/0 ¦ DD60+25 (1 MRC) ¦ POWERLINE-XING ¦ EXISTING 400 KV DC NEEMUCH-MANDSAUR TRANSMISSION LINE ¦ Power Grid ¦ APPROVAL-AWAITED ¦ SUBMITTED ¦ JOINT INSPECTION DONE BY 04.06.2025 2 ¦ 2.0 ¦ 25/0 ¦ DC2+1 ¦ 26/0 ¦ DC2+12 ¦ POWERLINE-XING ¦ 220 KV DC MANDSAUR - NIPANIA TL ¦ MPPTCL ¦ APPROVAL-AWAITED ¦ SUBMITTED ¦ JOINT INSPECTION DONE BY 04.06.2025 3 ¦ 3.0 ¦ 28/0 ¦ DD45+6 ¦ 29/0 ¦ DD45+18 ¦ POWERLINE-XING ¦ 220 KV DC SITAMAU-SUWASRA OHTL MPPTCL ¦ MPPTCL ¦ APPROVAL-AWAITED ¦ SUBMITTED ¦ JOINT INSPECTION DONE BY 04.06.2025 4 ¦ 4.0 ¦ 33/0 ¦ DD45+9 ¦ 34/0 ¦ DC1+3 ¦ POWERLINE-XING ¦ 132KV D/C SUWASARA - BADOD TL (Joint joint inspection Done) ¦ MPPTCL ¦ APPROVAL-AWAITED ¦ SUBMITTED ¦ JOINT INSPECTION DONE BY 04.06.2025 5 ¦ 5.0 ¦ 37/0 ¦ DD45+12 ¦ 38/0 ¦ DD45+9 ¦ POWERLINE-XING ¦ 220 KV OHTL DC BHANPUR-BAROD MPPTCL ¦ MPPTCL ¦ APPROVAL-AWAITED ¦ SUBMITTED ¦ JOINT INSPECTION DONE BY 04.06.2025 8 ¦ 6.0 ¦ 42/0 ¦ DC1+3 ¦ 43/0 ¦ DC1+6 ¦ POWERLINE-XING ¦ 132 KV SC BHAWANI MANDI - DAG T/L (RRVPNL) ¦ RVPNL ¦ APPROVAL-AWAITED ¦ SUBMITTED ¦ JOINT INSPECTION DONE BY 26.06.2025 | ok
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | 2026-05-18 | Erection productivity | 0 | 0 | erection | R3: Sr. No. ¦ Sub-Contractor Name ¦ Loc. No. ¦ Type of Tower ¦ Tower Weight (MT) ¦ Previous Month ¦ 01.11.25 (MT) ¦ 02.11.25 (MT) ¦ 03.11.25 (MT) ¦ 04.11.25 (MT) ¦ 05.11.25 (MT) ¦ 06.11.25 (MT) ¦ 07.11.25 (MT) ¦ 08.11.25 (MT) ¦ 09.11.25 (MT) ¦ 10.11.25 (MT) ¦ 11.11.25 (MT) ¦ 12.11.25 (MT) ¦ 13.11.25 (MT) ¦ 14.11.25 (MT) R4: Plan ¦ Actual ¦ Shotfall R5: 1.0 ¦ Devi Construction ¦ 9/2 ¦ DA+0 ¦ 36.159756 ¦ 27.12 ¦ 4.519 ¦ 4.519 ¦ 9.038 ¦ Completed ¦ 10.0 ¦ 5.0 ¦ 6.0 R6: 2.0 ¦ Devi Construction ¦ 8/4 ¦ DA+3 ¦ 37.931088 ¦ 7.0 ¦ 8.0 ¦ 7.0 ¦ 7.5 ¦ 7.7 ¦ 37.200 ¦ Completed R7: 3.0 ¦ Devi Construction ¦ 10/2 ¦ DA(-)3 ¦ 34.78981 ¦ 6.78 ¦ 11.0 ¦ 9.0 ¦ 8.0 ¦ 34.780 ¦ Completed | KEC International Limited - Gurgaon. Erection Productivity Gang wise - Nov'25 Sr. No. ¦ Sub-Contractor Name ¦ Loc. No. ¦ Type of Tower ¦ Tower Weight (MT) ¦ Previous Month ¦ 01.11.25 (MT) ¦ 02.11.25 (MT) ¦ 03.11.25 (MT) ¦ 04.11.25 (MT) ¦ 05.11.25 (MT) ¦ 06.11.25 (MT) ¦ 07.11.25 (MT) ¦ 08.11.25 (MT) ¦ 09.11.25 (MT) ¦ 10.11.25 (MT) ¦ 11.11.25 (MT) ¦ 12.11.25 (MT) ¦ 13.11.25 (MT) ¦ 14.11.25 (MT) Plan ¦ Actual ¦ Shotfall 1.0 ¦ Devi Construction ¦ 9/2 ¦ DA+0 ¦ 36.159756 ¦ 27.12 ¦ 4.519 ¦ 4.519 ¦ 9.038 ¦ Completed ¦ 10.0 ¦ 5.0 ¦ 6.0 2.0 ¦ Devi Construction ¦ 8/4 ¦ DA+3 ¦ 37.931088 ¦ 7.0 ¦ 8.0 ¦ 7.0 ¦ 7.5 ¦ 7.7 ¦ 37.200 ¦ Completed 3.0 ¦ Devi Construction ¦ 10/2 ¦ DA(-)3 ¦ 34.78981 ¦ 6.78 ¦ 11.0 ¦ 9.0 ¦ 8.0 ¦ 34.780 ¦ Completed 4.0 ¦ Devi Construction ¦ 12/3 ¦ DA(-)3 ¦ 34.78981 ¦ 5.78 ¦ 7.0 ¦ 8.0 ¦ 7.0 ¦ 7.0 ¦ 34.780 ¦ Completed | ok
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | 765KV TA 414 VNTL | 20 | 15 | project_details, summary_status, survey_soil, visual_l2 | R2: Project Name ¦ 765KV D/C HEXA VATAMAN - NAVSARI TL (PKG 04) ¦ NOA Start Date ¦ 2024-03-12 00:00:00 ¦ PCH ¦ Mr. Arun Felbin R3: Client Name ¦ Powergrid Vataman Transmission Ltd ¦ LOA End Date ¦ 2025-12-11 00:00:00 ¦ Regional Manager ¦ Mr. Nitin Bandale R7: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Submitted till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks R8: Rout Alignment ¦ km ¦ 127.854 ¦ 127.854 ¦ 127.854 ¦ 127.854 ¦ 127.854 ¦ Completed R9: Detailed Survey ¦ km ¦ 127.854 ¦ 127.854 ¦ 127.854 ¦ 127.854 ¦ 127.854 ¦ Completed | Project Code ¦ TA 414 ¦ Date ¦ 2026-05-19 00:00:00 ¦ President-T&D ¦ Mr. Ganesh Srinivasan Project Name ¦ 765KV D/C HEXA VATAMAN - NAVSARI TL (PKG 04) ¦ NOA Start Date ¦ 2024-03-12 00:00:00 ¦ PCH ¦ Mr. Arun Felbin Client Name ¦ Powergrid Vataman Transmission Ltd ¦ LOA End Date ¦ 2025-12-11 00:00:00 ¦ Regional Manager ¦ Mr. Nitin Bandale Revised End Date ¦ 2026-05-11 00:00:00 ¦ Planning Engineer ¦ Nishant Giri ¦ Project Manger ¦ Mr. Vivek Kumar Gupta \ Check Survey Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Submitted till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks Rout Alignment ¦ km ¦ 127.854 ¦ 127.854 ¦ 127.854 ¦ 127.854 ¦ 127.854 ¦ Completed | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | 765KV ASOTL | 20 | 15 | project_details, summary_status, survey_soil, visual_l2 | R2: Project Name ¦ 765KV D/C Ahmedabad to South Olpad TL-04 ¦ NOA Start Date ¦ 2024-11-26 00:00:00 ¦ PCH ¦ Mr. Arun Felbin R3: Client Name ¦ PGKTL ¦ LOA End Date ¦ 2026-10-25 00:00:00 ¦ Regional Manager ¦ Mr. Nitin Bendale R7: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Submitted till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks R8: Rout Alignment ¦ Km ¦ 114.516 ¦ 114.516 ¦ 114.516 ¦ 114.516 ¦ 114.516 ¦ Completed R9: Detailed Survey ¦ Km ¦ 114.516 ¦ 114.516 ¦ 107.585 ¦ 97.677 ¦ 6.931000000000012 ¦ 16.839 ¦ 97.677 | Project Code ¦ TA 510 ¦ Date ¦ 2026-05-20 00:00:00 ¦ President-T&D ¦ Mr. Ganesh Srinivasan Project Name ¦ 765KV D/C Ahmedabad to South Olpad TL-04 ¦ NOA Start Date ¦ 2024-11-26 00:00:00 ¦ PCH ¦ Mr. Arun Felbin Client Name ¦ PGKTL ¦ LOA End Date ¦ 2026-10-25 00:00:00 ¦ Regional Manager ¦ Mr. Nitin Bendale Revised End Date ¦ Planning Engineer ¦ Mr.Jayant Vaishnav ¦ Project Manger ¦ Mr. Subash .S Survey Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Submitted till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks Rout Alignment ¦ Km ¦ 114.516 ¦ 114.516 ¦ 114.516 ¦ 114.516 ¦ 114.516 ¦ Completed Detailed Survey ¦ Km ¦ 114.516 ¦ 114.516 ¦ 107.585 ¦ 97.677 ¦ 6.931000000000012 ¦ 16.839 ¦ 97.677 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Project Details | 11 | 11 | project_details | R1: Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manager ¦ Section Incharge ¦ Supervisor | Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manager ¦ Section Incharge ¦ Supervisor TA 510 ¦ 765kV D/C Ahmedabad South Olpad TL04 ¦ Powergrid South Olpad Transmission Limited ¦ 2024-03-12 00:00:00 ¦ 2025-12-11 00:00:00 ¦ Mr.Jayant Vaishnav ¦ Mr.Arun Felbin ¦ Mr. Nitin Ashok Bendale ¦ Mr. Subash.S ¦ Mr.Sahil Khan ¦ Mr.B Nagarajan Mr.Praveen Singh Rathore Mr.Vidhya Saker upadya Mr.Mohan Kumar Mr.Mohit Kumar Mahto Mr.Dhananjay Kumar Srivastava Mr.Ajay Mahato | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | AOTL - KEC | 22 | 15 | foundation, summary_status, survey_soil, visual_l2 | R5: Sr No. ¦ Activity ¦ Estimated Quantity ¦ Cumm. Progress up to till last Month (Mar'26) ¦ Target as per L2 Schedule Cummulative (upto April'26) ¦ L3 Plan for the month (April'26 ) ¦ Today's Progress ¦ Progress in this month ¦ Cumm. Progress till date ¦ Cumm. Balance ¦ WIP ¦ No of Gangs ¦ Remark R6: 1 ¦ Route Alignment (Km) ¦ 114.516 ¦ 114.516 ¦ 114.516 R7: 2 ¦ Detailed Survey (Km) ¦ 114.516 ¦ 97.677 ¦ 16.839 ¦ 97.677 ¦ 16.839 R9: 4 ¦ Check Survey (Km) ¦ 114.516 ¦ 90.94900000000001 ¦ 23.566999999999993 ¦ 90.94900000000001 ¦ 23.566999999999993 R10: 5 ¦ Soil Investigation (Nos.) ¦ 30 ¦ 22 ¦ 8 ¦ 22 ¦ 8 | KEC INTERNATIONAL LIMITED ¦ 2026-05-20 00:00:00 Name of Client: ¦ Powergrid South Olpad Transmission Limited Name of Line: ¦ TL-04 , 765 kV D/C Ahmedabad - South Olpad Transmission Line NOA Ref. No.: ¦ CC/T/W-TW/DOM/A10/23/12603/NOA-2/24-114169/01, Dt.26-11-24 Sr No. ¦ Activity ¦ Estimated Quantity ¦ Cumm. Progress up to till last Month (Mar'26) ¦ Target as per L2 Schedule Cummulative (upto April'26) ¦ L3 Plan for the month (April'26 ) ¦ Today's Progress ¦ Progress in this month ¦ Cumm. Progress till date ¦ Cumm. Balance ¦ WIP ¦ No of Gangs ¦ Remark 1 ¦ Route Alignment (Km) ¦ 114.516 ¦ 114.516 ¦ 114.516 2 ¦ Detailed Survey (Km) ¦ 114.516 ¦ 97.677 ¦ 16.839 ¦ 97.677 ¦ 16.839 3 ¦ Profiling (Km) ¦ 114.516 ¦ 107.58699999999999 ¦ 6.929000000000016 ¦ 107.58699999999999 ¦ 6.929000000000016 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | DPR Sheet | 33 | 11 | summary_status, survey_soil |  | KEC INTERNATIONAL LIMITED DAILY PROGRESS REPORT : SUBMISSION STATUS AS ON ¦ 2026-05-20 00:00:00 Name of the Project: ¦ TL-04 , 765 kV D/C Ahmedabad - South Olpad Transmission Line Contract No. & Date : ¦ CC/T/W-TW/DOM/A10/23/12603/NOA-2/24-114169/01, Dt.26-11-24 ROUTE ALIGNMENT PROGRESS SUMMARY TOTAL QTY (Tentative) ¦ COMPLETED UP TO PREV MONTH ¦ COMP. IN CURRENT MONTH ¦ CUMULATIVE ¦ BAL.QTY 114.516 ¦ 114.516 ¦ 114.516 SOIL INVESTIGATION PROGRESS SUMMARY | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet5 | 77 | 2 |  |  | 127/1 135/0 139/1 139/2 139/3 140/0 167/0 173/0 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet3 | 26 | 4 |  |  | A 127/2 ¦ 127/2128/0135/0139/0139/2141/1141/2145/5145/6148/3161/0166/0175/1182/0183/0183/1183/3194/0214/3214/6217/4225/3244/0244/2250/2 128/0 135/0 139/0 ¦ 127/2128/0135/0139/0139/2141/1141/2145/5145/6148/3161/0166/0175/1182/0183/0183/1183/3194/0214/3214/6217/4225/3244/0244/2250/2 139/2 141/1 141/2 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet1 | 5 | 7 |  |  | District ¦ Till Dec'24 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 Bharuch ¦ 14 ¦ 9 ¦ 14 ¦ 4 ¦ 1 Surat ¦ 4 ¦ 17 ¦ 4 Navsari ¦ 4 ¦ 7 ¦ 6 ¦ 2 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Survey Anx | 154 | 10 | survey_soil | R2: District ¦ Section ¦ Total ¦ Detail Survey ¦ Check Survey R3: Completed ¦ Submitted ¦ Approved ¦ Completed ¦ Submitted ¦ Approved | TL-04 , 765 kV D/C Ahmedabad - South Olpad Transmission Line District ¦ Section ¦ Total ¦ Detail Survey ¦ Check Survey Completed ¦ Submitted ¦ Approved ¦ Completed ¦ Submitted ¦ Approved Anand ¦ 117/0-119/0 ¦ 0.62 ¦ 0.62 ¦ 0.62 ¦ 0.62 ¦ 0.62 ¦ 0.62 ¦ 0.62 Anand ¦ 119/0-124/0 ¦ 1.572 ¦ 1.572 ¦ 1.572 ¦ 1.572 ¦ 1.572 ¦ 1.572 ¦ 1.572 Anand ¦ 124/0-124/3 ¦ 1.228 ¦ 1.228 ¦ 1.228 ¦ 1.228 ¦ 1.228 ¦ 1.228 ¦ 1.228 Anand ¦ 124/3-131/0 ¦ 3.994 ¦ 3.994 ¦ 3.994 ¦ 3.994 ¦ 3.994 ¦ 3.994 ¦ 3.994 Vadodara ¦ 131/0-133/0 ¦ 2.694 ¦ 2.694 ¦ 2.694 ¦ 2.694 ¦ 2.694 ¦ 2.694 ¦ 2.694 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Soil Inv. | 35 | 11 | summary_status, survey_soil | R2: Sl. No. ¦ Loc. No. ¦ TOT ¦ RC ¦ Depth In Mtr ¦ Status ¦ Classification ¦ Approval Letter Status ¦ Remarks ¦ Agency ¦ PO | ASOTL PROJECT - SOIL INVESTIGATION LOCATIONS Sl. No. ¦ Loc. No. ¦ TOT ¦ RC ¦ Depth In Mtr ¦ Status ¦ Classification ¦ Approval Letter Status ¦ Remarks ¦ Agency ¦ PO 1 ¦ AP118 ¦ 5DD60+25 ¦ 10 ¦ Approved ¦ Sandy Dry ¦ 2025-05-25 00:00:00 ¦ Geo Design ¦ Done. 2 ¦ 124/0 ¦ 5DD60+9 ¦ 20 ¦ SI done ,Repoert Awaited ¦ Instead of 127/0 ¦ Geo Design ¦ To be Done. 3 ¦ 124/3 ¦ 5DB1+0 ¦ 20 ¦ SI done ,Repoert Awaited ¦ Newly Location ¦ Geo Design ¦ To be Done. 4 ¦ 124/7 ¦ 5DB1+0 ¦ 20 ¦ SI done ,Repoert Awaited ¦ Instead of 130/0 ¦ Geo Design ¦ To be Done. 5 ¦ 124/10 ¦ 5DA+0 ¦ 20 ¦ SI done ,Repoert Awaited ¦ Newly Location ¦ Geo Design ¦ To be Done. 6 ¦ AP127 ¦ 10 ¦ Approved ¦ Sandy Dry ¦ 2025-05-25 00:00:00 ¦ Eliminated ¦ Geo Design ¦ Done. | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Survey | 45 | 6 | statutory_crossing, summary_status, survey_soil | R4: Sl. No. ¦ Particulars ¦ UoM ¦ Qty. ¦ Remarks R6: 2 ¦ Detail Survey Submitted ¦ Kms. ¦ 107.585 R8: 4 ¦ Detail Survey Approved ¦ Kms. ¦ 97.677 R10: 6 ¦ Check Survey Submitted ¦ Kms. ¦ 97.677 R11: 7 ¦ Check Survey Approved ¦ Kms. ¦ 90.94900000000001 | Date ¦ 2026-05-20 00:00:00 TA-510 ¦ ASOTL PROJECT ¦ SURVEY STATUS ¦ Sl. No. ¦ Particulars ¦ UoM ¦ Qty. ¦ Remarks 1 ¦ Total Line Length ¦ Kms. ¦ 114.31499999999998 2 ¦ Detail Survey Submitted ¦ Kms. ¦ 107.585 3 ¦ Balance to Submit ¦ Kms. ¦ 6.72999999999999 ¦ AP171/0-175/0 GETCO- SS 4 ¦ Detail Survey Approved ¦ Kms. ¦ 97.677 5 ¦ Balance to Approve ¦ Kms. ¦ 16.839 ¦ AP175-177 & 184-185 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | FDN | 330 | 24 | earthing_tack, foundation, project_details, summary_status | R1: ASOTL Foundation ¦ 2026-05-20 00:00:00 ¦ ` R2: Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Concreting Volume in M3 ¦ Starting Date ¦ Todays Status ¦ Cumulative Status ¦ Completion Date ¦ Remarks ¦ Gang name ¦ Earthing Status ¦ Earthing Completion Date ¦ Manpower R3: 1 ¦ 155/3 ¦ DA+0 ¦ WPS ¦ 39.126000000000005 ¦ 2025-02-18 00:00:00 ¦ Completed ¦ 2025-02-25 00:00:00 ¦ Arya Enterprises ¦ Done ¦ 2025-02-27 00:00:00 R4: 2 ¦ 155/4 ¦ DA+0 ¦ WPS ¦ 39.126000000000005 ¦ 2025-02-18 00:00:00 ¦ Completed ¦ 2025-02-22 00:00:00 ¦ B.K.Traders ¦ Done ¦ 2025-03-01 00:00:00 R5: 3 ¦ 155/5 ¦ DA+3 ¦ WPS ¦ 40.634 ¦ 2025-02-23 00:00:00 ¦ Completed ¦ 2025-02-27 00:00:00 ¦ B.K.Traders ¦ Done ¦ 2025-03-01 00:00:00 | ASOTL Foundation ¦ 2026-05-20 00:00:00 ¦ ` Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Concreting Volume in M3 ¦ Starting Date ¦ Todays Status ¦ Cumulative Status ¦ Completion Date ¦ Remarks ¦ Gang name ¦ Earthing Status ¦ Earthing Completion Date ¦ Manpower 1 ¦ 155/3 ¦ DA+0 ¦ WPS ¦ 39.126000000000005 ¦ 2025-02-18 00:00:00 ¦ Completed ¦ 2025-02-25 00:00:00 ¦ Arya Enterprises ¦ Done ¦ 2025-02-27 00:00:00 2 ¦ 155/4 ¦ DA+0 ¦ WPS ¦ 39.126000000000005 ¦ 2025-02-18 00:00:00 ¦ Completed ¦ 2025-02-22 00:00:00 ¦ B.K.Traders ¦ Done ¦ 2025-03-01 00:00:00 3 ¦ 155/5 ¦ DA+3 ¦ WPS ¦ 40.634 ¦ 2025-02-23 00:00:00 ¦ Completed ¦ 2025-02-27 00:00:00 ¦ B.K.Traders ¦ Done ¦ 2025-03-01 00:00:00 4 ¦ 155/1 ¦ DA+0 ¦ WET ¦ 63.346000000000004 ¦ 2025-02-12 00:00:00 ¦ Completed ¦ 2025-02-17 00:00:00 ¦ Arya Enterprises ¦ Done ¦ 2025-03-04 00:00:00 5 ¦ 156/2 ¦ DA+0 ¦ WPS ¦ 39.126000000000005 ¦ 2025-03-26 00:00:00 ¦ Completed ¦ 2025-03-30 00:00:00 ¦ Arya Enterprises ¦ Done ¦ 2025-04-03 00:00:00 6 ¦ 156/1 ¦ DA+3 ¦ WET ¦ 65.631 ¦ 2025-03-05 00:00:00 ¦ Completed ¦ 2025-03-13 00:00:00 ¦ Arya Enterprises ¦ Done ¦ 2025-03-15 00:00:00 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection | 185 | 24 | earthing_tack, erection, project_details, summary_status | R3: Sl. No. ¦ Location Number ¦ Type of Tower ¦ Starting Date ¦ Tower Weight (MT) ¦ Status ¦ Completion Date ¦ Gang Name ¦ Manpower ¦ Hindarnce Days ¦ Remarks ¦ Tackweldng Status ¦ Tackwelding start date ¦ Tackwelding Completion date ¦ Sub Contractor name R4: 1 ¦ 141/1 ¦ DA+0 ¦ 2026-01-01 00:00:00 ¦ 37.73 ¦ Completed ¦ 2026-01-07 00:00:00 ¦ Dhaneshwar Mahato R5: 2 ¦ 139/2 ¦ DA+3 ¦ 2026-01-05 00:00:00 ¦ 39.458 ¦ Completed ¦ 2026-01-12 00:00:00 ¦ Lalan Mehta R6: 3 ¦ 141/0 ¦ DB2+0 ¦ 2026-01-08 00:00:00 ¦ 54.418 ¦ Completed ¦ 2026-01-13 00:00:00 ¦ Dhaneshwar Mahato R7: 5 ¦ 140/1 ¦ DA+3 ¦ 2026-01-14 00:00:00 ¦ 39.458 ¦ Completed ¦ 2026-01-21 00:00:00 ¦ Dhaneshwar Mahato | AOTL Tower Erection ¦ 2026-05-20 00:00:00 Sl. No. ¦ Location Number ¦ Type of Tower ¦ Starting Date ¦ Tower Weight (MT) ¦ Status ¦ Completion Date ¦ Gang Name ¦ Manpower ¦ Hindarnce Days ¦ Remarks ¦ Tackweldng Status ¦ Tackwelding start date ¦ Tackwelding Completion date ¦ Sub Contractor name 1 ¦ 141/1 ¦ DA+0 ¦ 2026-01-01 00:00:00 ¦ 37.73 ¦ Completed ¦ 2026-01-07 00:00:00 ¦ Dhaneshwar Mahato 2 ¦ 139/2 ¦ DA+3 ¦ 2026-01-05 00:00:00 ¦ 39.458 ¦ Completed ¦ 2026-01-12 00:00:00 ¦ Lalan Mehta 3 ¦ 141/0 ¦ DB2+0 ¦ 2026-01-08 00:00:00 ¦ 54.418 ¦ Completed ¦ 2026-01-13 00:00:00 ¦ Dhaneshwar Mahato 5 ¦ 140/1 ¦ DA+3 ¦ 2026-01-14 00:00:00 ¦ 39.458 ¦ Completed ¦ 2026-01-21 00:00:00 ¦ Dhaneshwar Mahato 4 ¦ 135/0 ¦ DB1+6 ¦ 2026-01-13 00:00:00 ¦ 63.509 ¦ Completed ¦ 2026-01-25 00:00:00 ¦ Lalan Mehta 7 ¦ 145/4 ¦ DA+0 ¦ 2026-01-18 00:00:00 ¦ 37.73 ¦ Completed ¦ 2026-01-28 00:00:00 ¦ Lalan Mehta | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection Compiled | 35 | 14 | erection, project_details, summary_status | R1: SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Remark R2: 11 ¦ 134/0 ¦ DC2+0 ¦ 2026-02-01 00:00:00 ¦ 64.254 ¦ Completed ¦ 2026-02-07 00:00:00 ¦ Dhaneshwar Mahato R3: 4 ¦ 135/0 ¦ DB1+6 ¦ 2026-01-13 00:00:00 ¦ 63.509 ¦ Completed ¦ 2026-01-25 00:00:00 ¦ Lalan Mehta R4: 2 ¦ 139/2 ¦ DA+3 ¦ 2026-01-05 00:00:00 ¦ 39.458 ¦ Completed ¦ 2026-01-12 00:00:00 ¦ Lalan Mehta R5: 22 ¦ 140/0 ¦ DD45+0 ¦ 2026-03-16 00:00:00 ¦ 72.234 ¦ Completed ¦ 2026-03-24 00:00:00 ¦ Dhaneshwar Mahato | SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Remark 11 ¦ 134/0 ¦ DC2+0 ¦ 2026-02-01 00:00:00 ¦ 64.254 ¦ Completed ¦ 2026-02-07 00:00:00 ¦ Dhaneshwar Mahato 4 ¦ 135/0 ¦ DB1+6 ¦ 2026-01-13 00:00:00 ¦ 63.509 ¦ Completed ¦ 2026-01-25 00:00:00 ¦ Lalan Mehta 2 ¦ 139/2 ¦ DA+3 ¦ 2026-01-05 00:00:00 ¦ 39.458 ¦ Completed ¦ 2026-01-12 00:00:00 ¦ Lalan Mehta 22 ¦ 140/0 ¦ DD45+0 ¦ 2026-03-16 00:00:00 ¦ 72.234 ¦ Completed ¦ 2026-03-24 00:00:00 ¦ Dhaneshwar Mahato 5 ¦ 140/1 ¦ DA+3 ¦ 2026-01-14 00:00:00 ¦ 39.458 ¦ Completed ¦ 2026-01-21 00:00:00 ¦ Dhaneshwar Mahato 12 ¦ 140/2 ¦ DA+0 ¦ 2026-02-08 00:00:00 ¦ 37.73 ¦ Completed ¦ 2026-02-13 00:00:00 ¦ Dhaneshwar Mahato 3 ¦ 141/0 ¦ DB2+0 ¦ 2026-01-08 00:00:00 ¦ 54.418 ¦ Completed ¦ 2026-01-13 00:00:00 ¦ Dhaneshwar Mahato | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Visual chart 1 | 832 | 129 | earthing_tack, erection, foundation, statutory_crossing, stringing, summary_status, survey_soil, visual_l2 | R3: Client ¦ Power Grid Corporation of India Limited ¦ FOUNDATION ¦ TOWER ERECTION ¦ STR P/O ¦ STR F/S R8: Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ Sl. No. ¦ Type of Crossing ¦ No. of X-ing ¦ Apprd. ¦ Bal R10: 1 ¦ Detailed Survey ¦ Kms ¦ 114.516 ¦ 97.677 ¦ 16.839 ¦ 1 ¦ PL X-ing R11: 2 ¦ Check Survey ¦ Kms ¦ 114.516 ¦ 90.94900000000001 ¦ 23.566999999999993 ¦ 2 ¦ 66 kV R12: 3 ¦ Soil Investigation ¦ Nos. ¦ 30 ¦ 30 ¦ 3 ¦ 132 kV | Visual Chart Name of the Line : ¦ TL04 765 kV D/C Ahmedabad - South Olpad Transmission Line Client ¦ Power Grid Corporation of India Limited ¦ FOUNDATION ¦ TOWER ERECTION ¦ STR P/O ¦ STR F/S Agency ¦ KEC International Limited ¦ TOTAL ¦ COMP. ¦ BAL. ¦ TOTAL ¦ COMP. ¦ BAL. Date ¦ 2026-05-20 00:00:00 PROGRESS AT A GLANCE : ¦ CROSSING PROPOSAL STATUS : Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ Sl. No. ¦ Type of Crossing ¦ No. of X-ing ¦ Apprd. ¦ Bal 1 ¦ Detailed Survey ¦ Kms ¦ 114.516 ¦ 97.677 ¦ 16.839 ¦ 1 ¦ PL X-ing | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Pile Foundation | 3 | 14 | earthing_tack, foundation, project_details, row_hindrance, summary_status | R2: Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Concreting Volume in M3 ¦ Starting Date ¦ Todays Status ¦ Cumulative Status ¦ Completion Date ¦ Remarks ¦ Gang name ¦ Earthing Status ¦ Earthing Completion Date ¦ Manpower R3: 1 ¦ 131/1 ¦ DD45+9 ¦ Pile ¦ 2026-04-13 00:00:00 ¦ work hampered due to forest dept. approval pending ¦ Chowdhary Const. ¦ 25 | ASOTL Pile ¦ 2026-05-17 00:00:00 Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Concreting Volume in M3 ¦ Starting Date ¦ Todays Status ¦ Cumulative Status ¦ Completion Date ¦ Remarks ¦ Gang name ¦ Earthing Status ¦ Earthing Completion Date ¦ Manpower 1 ¦ 131/1 ¦ DD45+9 ¦ Pile ¦ 2026-04-13 00:00:00 ¦ work hampered due to forest dept. approval pending ¦ Chowdhary Const. ¦ 25 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet6 | 47 | 5 |  | R2: Sr No. ¦ Location ¦ TOT ¦ Start ¦ End | Sr No. ¦ Location ¦ TOT ¦ Start ¦ End 1 ¦ 117/1 ¦ DA-3 ¦ 2026-01-15 00:00:00 ¦ 2026-01-21 00:00:00 2 ¦ 119/1 ¦ DA-3 ¦ 2026-01-09 00:00:00 ¦ 2026-01-15 00:00:00 3 ¦ 120/0 ¦ DD60+3 ¦ 2026-01-21 00:00:00 ¦ 2026-01-31 00:00:00 4 ¦ 120/4 ¦ DA+0 ¦ 2025-12-28 00:00:00 ¦ 2026-01-02 00:00:00 5 ¦ 120/7 ¦ DA+3 ¦ 2025-12-28 00:00:00 ¦ 2026-01-09 00:00:00 6 ¦ 121/2 ¦ DA+9 ¦ 2025-12-30 00:00:00 ¦ 2026-01-19 00:00:00 7 ¦ 121/3 ¦ DA+0 ¦ 2026-01-19 00:00:00 ¦ 2026-01-30 00:00:00 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet4 | 940 | 353 |  |  | 117/1 ¦ 117/2 ¦ 118/0 ¦ 119/0 ¦ 119/1 ¦ 119/2 ¦ 119/3 ¦ 120/0 ¦ 120/1 ¦ 120/2 ¦ 120/3 ¦ 120/4 ¦ 120/5 ¦ 120/6 ¦ 120/7 ¦ 121/0 ¦ 121/1 ¦ 121/2 ¦ 121/3 ¦ 121/4 DA-3 ¦ DA+6 ¦ DB2+0 ¦ DD60+0 ¦ DA-3 ¦ DA-3 ¦ DA+9 ¦ DD60+3 ¦ DA-3 ¦ DA+0 ¦ DA+6 ¦ DA+0 ¦ DA-3 ¦ DA+0 ¦ DA+3 ¦ DB2+9 ¦ DB1+25 ¦ DA+9 ¦ DA+0 ¦ DA+0 Loc No ¦ Tower Type 118/0 117/1 ¦ DA-3 ¦ 117/1 117/2 ¦ DA+6 ¦ 117/2 118/0 ¦ DB2+0 ¦ 118/0 119/0 ¦ DD60+0 ¦ 119/0 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet7 | 380 | 2 |  |  | kfvnk 117/1 117/2 118/0 119/0 119/1 119/2 119/3 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tack welding | 1 | 1 | earthing_tack |  | Sr. No. | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing Compiled | 6 | 23 | project_details, stretch_readiness, stringing, summary_status, supply | R3: S.no ¦ Sec ¦ From AP ¦ To AP ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name ¦ Gang Strength | Number of TSE S.no ¦ Sec ¦ From AP ¦ To AP ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name ¦ Gang Strength Total | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | String | 13 | 17 | stringing, summary_status | R2: Sr. No. ¦ Section ¦ length ¦ Manual/TSE ¦ Engaged Date ¦ Paying Out ¦ Final Sag ¦ P/O Completed ¦ F/S Completed ¦ Stringing Status As on Today ¦ Cumulative Status ¦ Sub Contractor name ¦ Manpower ¦ Hindarnce Days ¦ Remarks | ASOTL Stringing Sr. No. ¦ Section ¦ length ¦ Manual/TSE ¦ Engaged Date ¦ Paying Out ¦ Final Sag ¦ P/O Completed ¦ F/S Completed ¦ Stringing Status As on Today ¦ Cumulative Status ¦ Sub Contractor name ¦ Manpower ¦ Hindarnce Days ¦ Remarks Start Date ¦ End Date ¦ Start Date ¦ End Date | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Crossing | 50 | 16 | statutory_crossing, summary_status | R2: Sl No ¦ AP NO ¦ Towe Type ¦ AP No ¦ Tower Type ¦ Type of Crossings ¦ Span Length ¦ LINE OWNER ¦ Line Name ¦ Nos. ¦ Work Portion ¦ Status ¦ Submitted to Client for Review ¦ Proposal Submitted (Y/N) ¦ Inspection Status (Y/N) ¦ Remarks R3: 1 ¦ 118/0 ¦ 5DD60+25 ¦ 119/0 ¦ DD60+25 ¦ Powerline crossing ¦ 225.97 ¦ GETCO ¦ 400 kV D/C Twin Chorniya/Pancham To Kosamba TL ¦ 1 ¦ Anand ¦ Submitted ¦ 2026-04-17 00:00:00 ¦ Y ¦ Approval Not Received from PGCIL R4: 2 ¦ 120/0 ¦ CDDN+55 ¦ 121/0 ¦ CDDN+25 ¦ Powerline crossing ¦ 284.73 ¦ PGCIL ¦ 765 kV D/C Ahmedabad-Navsari ¦ 1 ¦ Anand ¦ Submitted ¦ 2026-04-17 00:00:00 ¦ Y ¦ Approval Not Received from PGCIL R5: 3 ¦ 122/0 ¦ CDDN+55 ¦ 123/0 ¦ CDDN+25 ¦ Powerline crossing ¦ 164.96 ¦ PGCIL ¦ 765 kV D/C Vataman-Navsari ¦ 1 ¦ Anand ¦ Submitted ¦ 2026-04-17 00:00:00 ¦ Y ¦ Approval Not Received from PGCIL R6: 4 ¦ 145/1 ¦ DB1+9 ¦ 145/2 ¦ DA+3 ¦ Powerline crossing ¦ 448 ¦ GETCO ¦ 66 kV D/C Gavasad-Sterling/Sarod ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2025-07-21 00:00:00 ¦ Y ¦ Y ¦ Approval Not Received from PGCIL | TL-04 , 765 kV D/C Ahmedabad - South Olpad Transmission Line Sl No ¦ AP NO ¦ Towe Type ¦ AP No ¦ Tower Type ¦ Type of Crossings ¦ Span Length ¦ LINE OWNER ¦ Line Name ¦ Nos. ¦ Work Portion ¦ Status ¦ Submitted to Client for Review ¦ Proposal Submitted (Y/N) ¦ Inspection Status (Y/N) ¦ Remarks 1 ¦ 118/0 ¦ 5DD60+25 ¦ 119/0 ¦ DD60+25 ¦ Powerline crossing ¦ 225.97 ¦ GETCO ¦ 400 kV D/C Twin Chorniya/Pancham To Kosamba TL ¦ 1 ¦ Anand ¦ Submitted ¦ 2026-04-17 00:00:00 ¦ Y ¦ Approval Not Received from PGCIL 2 ¦ 120/0 ¦ CDDN+55 ¦ 121/0 ¦ CDDN+25 ¦ Powerline crossing ¦ 284.73 ¦ PGCIL ¦ 765 kV D/C Ahmedabad-Navsari ¦ 1 ¦ Anand ¦ Submitted ¦ 2026-04-17 00:00:00 ¦ Y ¦ Approval Not Received from PGCIL 3 ¦ 122/0 ¦ CDDN+55 ¦ 123/0 ¦ CDDN+25 ¦ Powerline crossing ¦ 164.96 ¦ PGCIL ¦ 765 kV D/C Vataman-Navsari ¦ 1 ¦ Anand ¦ Submitted ¦ 2026-04-17 00:00:00 ¦ Y ¦ Approval Not Received from PGCIL 4 ¦ 145/1 ¦ DB1+9 ¦ 145/2 ¦ DA+3 ¦ Powerline crossing ¦ 448 ¦ GETCO ¦ 66 kV D/C Gavasad-Sterling/Sarod ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2025-07-21 00:00:00 ¦ Y ¦ Y ¦ Approval Not Received from PGCIL 5 ¦ 147/0 ¦ DD60+0 ¦ 147/1 ¦ DA-3 ¦ GAS PIPELINE ¦ 323 ¦ ONGC ¦ GGS Jambusar-GGS Dabka ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2025-08-18 00:00:00 ¦ Y ¦ Y ¦ Approval Not Received from PGCIL 6 ¦ 148A/0 ¦ DC2+0 ¦ 148B/0 ¦ DC1+0 ¦ GAS PIPELINE ¦ 259.34 ¦ GAIL ¦ Dabka-Gandhar ¦ 1 ¦ Bharuch ¦ Submitted ¦ 2025-09-15 00:00:00 ¦ Y ¦ Y ¦ Approval Not Received from PGCIL | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tree Enumeration | 21 | 3 | summary_status | R1: Sr.No. ¦ Location Details ¦ Status R2: 1 ¦ 133/0 to 171/1 ¦ completed R4: 3 ¦ 188/0 to 194/0 ¦ completed | Sr.No. ¦ Location Details ¦ Status 1 ¦ 133/0 to 171/1 ¦ completed 2 ¦ 171/2 to 187/0 3 ¦ 188/0 to 194/0 ¦ completed 4 ¦ 194/1 to 196/0 5 6 7 | repaired_defined_names (ValueError)
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet2 | 6 | 9 | stringing | R6: 1 ¦ Hotline Stringing ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 | Hotline Stringing total KM : 17.112 Km Sl NO ¦ Description ¦ Dec'25 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 ¦ June'25 1 ¦ Hotline Stringing ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 ¦ 2.4445714285714284 | repaired_defined_names (ValueError)
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Summary S | 1000 | 10 | earthing_tack, opgw_accessories, project_details, summary_status, supply, visual_l2 | R4: Sr. No. ¦ Item Description ¦ Finalized Vendor ¦ Unit ¦ Start Date as per Approved L2 Schedule ¦ FInish Date as per Approved L2 Schedule ¦ Total Qty as per LOA ¦ Received Till Date ¦ Balance ¦ Remarks R5: 1 ¦ Tower Stub ¦ KEC ¦ Nos. ¦ 2025-02-20 00:00:00 ¦ 2025-10-25 00:00:00 ¦ 315 ¦ 319 ¦ -4 R6: 2 ¦ Tower Earthing ¦ KEC ¦ Nos. ¦ 2025-02-20 00:00:00 ¦ 2025-10-25 00:00:00 ¦ 315 ¦ 319 ¦ -4 R8: 4 ¦ Conductor ¦ KEC Cables ¦ Km ¦ 2025-07-15 00:00:00 ¦ 2026-06-20 00:00:00 ¦ 4398 ¦ 3682.104 ¦ 715.8960000000002 R9: 5 ¦ Insulator ¦ Aditya Birla ¦ Nos. ¦ 2025-07-15 00:00:00 ¦ 2026-06-20 00:00:00 ¦ 12272 ¦ 12272 | KEC International Limited Supply Status ¦ 2026-05-20 00:00:00 Name of Line _ 765 kV Bikaner-IV PS – Siwani (2nd) line - Part-I Sr. No. ¦ Item Description ¦ Finalized Vendor ¦ Unit ¦ Start Date as per Approved L2 Schedule ¦ FInish Date as per Approved L2 Schedule ¦ Total Qty as per LOA ¦ Received Till Date ¦ Balance ¦ Remarks 1 ¦ Tower Stub ¦ KEC ¦ Nos. ¦ 2025-02-20 00:00:00 ¦ 2025-10-25 00:00:00 ¦ 315 ¦ 319 ¦ -4 2 ¦ Tower Earthing ¦ KEC ¦ Nos. ¦ 2025-02-20 00:00:00 ¦ 2025-10-25 00:00:00 ¦ 315 ¦ 319 ¦ -4 3 ¦ Tower Structure ¦ KEC ¦ Nos. ¦ 2025-04-10 00:00:00 ¦ 2026-03-20 00:00:00 ¦ 315 ¦ 298 ¦ 17 ¦ DA+0/+3/+6/+9/-1.5/-3 Extn - 51/71/54/44/18/12 Nos. DB1+0/+3/+6/+9 Extn - 9/3/1/2 Nos. DB2+0/+3/+6/+9 Extn - 6/3/1/1 Nos. DC1+0/+3/+6 Extn - 3/1/1Nos. DC2+0/+3/+9 Extn - 3/1/1 Nos. DC2+0 - 1 Nos.(TP Tower) DD1+0/+9 Extn - 2/2 Nos. DD2+0/+3/+18/+25/+35 Extn - 1/1/1/1/2 Nos. (12937.29 MT received) 4 ¦ Conductor ¦ KEC Cables ¦ Km ¦ 2025-07-15 00:00:00 ¦ 2026-06-20 00:00:00 ¦ 4398 ¦ 3682.104 ¦ 715.8960000000002 | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Supply Status | 1000 | 13 | earthing_tack, opgw_accessories, summary_status, supply, visual_l2 | R5: Sl. No. ¦ Activity Description ¦ Item Description ¦ Supplier ¦ Unit ¦ Total Quantity ¦ Supplies as per L2 ¦ Actual as on date ¦ Balance ¦ Present status of balance supplies ¦ Expected date of supply R6: 1 ¦ EARTHING OF TOWERS ¦ Supply of Pipe Type Earthing ¦ KEC ¦ EA ¦ 297 ¦ 319 ¦ -22 ¦ 1.0740740740740742 R7: 2 ¦ EARTHING OF TOWERS ¦ Supply of Counterpoise type earthing (120 mlength) ¦ KEC ¦ EA ¦ 15 ¦ 15 R8: 3 ¦ EARTHING OF TOWERS ¦ ROD TYPE EARTHING ¦ KEC ¦ EA ¦ 297 ¦ 319 ¦ -22 ¦ 1.0740740740740742 R9: 4 ¦ EARTHING OF TOWERS ¦ Supply of Shieldwire EarthingincludingPG clamps, downlead clampsbutexcluding Earthwire bits for Pipetypeearthing ¦ KEC ¦ EA ¦ 14 ¦ 14 | SUPPLY STATUS AS PER BOQ Name of Line _ 765 kV Bikaner-IV PS – Siwani (2nd) line - Part-I Agency: KEC INTERNATIONAL Limited Status as on ¦ 2026-05-20 00:00:00 Sl. No. ¦ Activity Description ¦ Item Description ¦ Supplier ¦ Unit ¦ Total Quantity ¦ Supplies as per L2 ¦ Actual as on date ¦ Balance ¦ Present status of balance supplies ¦ Expected date of supply 1 ¦ EARTHING OF TOWERS ¦ Supply of Pipe Type Earthing ¦ KEC ¦ EA ¦ 297 ¦ 319 ¦ -22 ¦ 1.0740740740740742 2 ¦ EARTHING OF TOWERS ¦ Supply of Counterpoise type earthing (120 mlength) ¦ KEC ¦ EA ¦ 15 ¦ 15 3 ¦ EARTHING OF TOWERS ¦ ROD TYPE EARTHING ¦ KEC ¦ EA ¦ 297 ¦ 319 ¦ -22 ¦ 1.0740740740740742 | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Summary E | 1000 | 26 | project_details, row_hindrance, summary_status, survey_soil, visual_l2 | R7: S.No. ¦ Activity ¦ LOA Qty ¦ Estimated Quantity ¦ Cumm. Progress up to Last Month (Apr'26) ¦ Target as per L2 Schedule Cummulative (upto Apr'26) ¦ Month's Plan as per L2 Schedule ¦ Progress of Month ¦ Today ¦ Cumulative Progress Till Date ¦ Balance ¦ No of Gangs/MP ¦ Remarks R8: 1 ¦ Route Alignment (Km) ¦ 120.944 ¦ 124.568 ¦ 124.568 ¦ 124.568 ¦ 124.568 R9: 2 ¦ Detailed Survey (Km) ¦ 120.944 ¦ 124.568 ¦ 124.568 ¦ 124.568 ¦ 124.568 R11: 4 ¦ Check Survey (Km) ¦ 120.944 ¦ 124.568 ¦ 124.568 ¦ 124.568 ¦ 124.568 R12: 5 ¦ Land Scheduling (Km) ¦ 120.944 ¦ 124.568 ¦ 123.174 ¦ 123.174 ¦ 1.3939999999999912 ¦ Approved ROW Corridor - 123.174 Km Tower Base - 315 Nos. | KEC International Limited ¦ 2026-05-20 00:00:00 Name of Client: Bikaner B Power Transmission Limited Name of Line: 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL NOA No. CC/T/W-TW/DOM/A00/24/09582/NOA-1 & 2/25-10174/01 & 02, Dated 03/01/2025 Office : Hansera, Lunkaransar S.No. ¦ Activity ¦ LOA Qty ¦ Estimated Quantity ¦ Cumm. Progress up to Last Month (Apr'26) ¦ Target as per L2 Schedule Cummulative (upto Apr'26) ¦ Month's Plan as per L2 Schedule ¦ Progress of Month ¦ Today ¦ Cumulative Progress Till Date ¦ Balance ¦ No of Gangs/MP ¦ Remarks 1 ¦ Route Alignment (Km) ¦ 120.944 ¦ 124.568 ¦ 124.568 ¦ 124.568 ¦ 124.568 2 ¦ Detailed Survey (Km) ¦ 120.944 ¦ 124.568 ¦ 124.568 ¦ 124.568 ¦ 124.568 | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | DPR Sheet | 1000 | 7 | summary_status, survey_soil |  | KEC International Limited DAILY PROGRESS REPORT : STATUS AS ON ¦ 2026-05-20 00:00:00 Name of the Project: ¦ 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Contract No. & Date : ¦ CC/T/W-TW/DOM/A00/24/09582/CA-1&2/25-100174/01 & 02 Dtd. 21.01.2025 ROUTE ALIGNMENT PROGRESS SUMMARY TOTAL QTY (Tentative) ¦ COMPLETED UP TO PREV MONTH ¦ COMP. IN CURRENT MONTH ¦ CUMULATIVE ¦ BAL.QTY 124.568 ¦ 124.568 ¦ 124.568 DETAILED SURVEY PROGRESS SUMMARY | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | DS | 1000 | 26 | survey_soil | R4: Sl.No. ¦ SPAN ¦ Detail Survey Section Length (Km) ¦ Submitted For Approval ¦ Approved Date ¦ Remarks R17: 12 ¦ GSS Gantry ¦ AP1A ¦ Hold By Power Grid | KEC International Limited 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Detailed Survey ¦ 2026-05-20 00:00:00 Sl.No. ¦ SPAN ¦ Detail Survey Section Length (Km) ¦ Submitted For Approval ¦ Approved Date ¦ Remarks From Section ¦ To Section 1 ¦ AP8 ¦ AP19 ¦ 16.984 ¦ 2025-02-12 00:00:00 ¦ 2025-02-13 00:00:00 ¦ Approved 2 ¦ AP6 ¦ AP8 ¦ 9.313 ¦ 2025-02-21 00:00:00 ¦ 2025-02-22 00:00:00 ¦ Approved 3 ¦ AP4 ¦ AP6 ¦ 11.121 ¦ 2025-03-10 00:00:00 ¦ 2025-03-15 00:00:00 ¦ Approved | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | CS | 1000 | 26 | survey_soil | R4: Sl.No. ¦ SPAN ¦ Section Length (Km) ¦ Submitted for Approval on Dated ¦ Approved on Dated ¦ Remarks R19: 14 ¦ GSS Gantry ¦ AP1A ¦ Hold By Power Grid | KEC International Limited 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Check Survey ¦ 2026-05-20 00:00:00 Sl.No. ¦ SPAN ¦ Section Length (Km) ¦ Submitted for Approval on Dated ¦ Approved on Dated ¦ Remarks From Section ¦ To Section 1 ¦ AP8 ¦ AP10 ¦ 5.532 ¦ 2025-02-12 00:00:00 ¦ 2025-02-13 00:00:00 ¦ Approved 2 ¦ AP6 ¦ AP8 ¦ 9.313 ¦ 2025-03-03 00:00:00 ¦ 2025-02-25 00:00:00 ¦ Approved 3 ¦ AP10 ¦ AP19 ¦ 11.452 ¦ 2025-03-03 00:00:00 ¦ 2025-02-25 00:00:00 ¦ Approved | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Hindrance Record | 1000 | 20 | erection, foundation, row_hindrance, summary_status | R3: Sr. No ¦ Loc No ¦ Tower Type ¦ Foundation Status ¦ Hindrance During Foundation Work ¦ Start Date ¦ End Date ¦ Effected Days ¦ Farmer Name ¦ Village Name ¦ Contact No. ¦ Tower Erection Status ¦ Hindrance During Tower Erection Work ¦ Start Date ¦ End Date ¦ Effected Days ¦ Farmer Name ¦ Village Name ¦ Contact No. R8: 5 ¦ 1A/1 ¦ DA-1.5 ¦ Completed ¦ Completed R9: 6 ¦ 1A/2 ¦ DA-1.5 ¦ Completed ¦ Completed R10: 7 ¦ 1A/3 ¦ DA-3 ¦ Completed ¦ ROW ¦ 2026-02-15 00:00:00 ¦ -46068 R11: 8 ¦ 2/0 ¦ DD60+3 ¦ Completed ¦ Resolved ¦ 2026-01-03 00:00:00 ¦ 2026-01-07 00:00:00 ¦ 4 ¦ ROW ¦ 2026-02-15 00:00:00 ¦ -46068 | Hindrance Record Balance >> ¦ 17 ¦ 4 ¦ 102 ¦ 32 Sr. No ¦ Loc No ¦ Tower Type ¦ Foundation Status ¦ Hindrance During Foundation Work ¦ Start Date ¦ End Date ¦ Effected Days ¦ Farmer Name ¦ Village Name ¦ Contact No. ¦ Tower Erection Status ¦ Hindrance During Tower Erection Work ¦ Start Date ¦ End Date ¦ Effected Days ¦ Farmer Name ¦ Village Name ¦ Contact No. 1 ¦ 1/0 ¦ DD60+3 2 ¦ 1/1 ¦ DB1+18 3 ¦ 1/2 ¦ DA+0 4 ¦ 1A/0 ¦ DD45+0 ¦ WIP 5 ¦ 1A/1 ¦ DA-1.5 ¦ Completed ¦ Completed | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Earthing | 1000 | 26 | earthing_tack | R4: Sr. No. ¦ Month ¦ Month Sr. No. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Complete ¦ Name of the Contractor ¦ Name of Supervisor ¦ PGCIL Person /Quest ¦ Remarks | KEC International Limited 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Details of Earthing ¦ 2026-05-20 00:00:00 Sr. No. ¦ Month ¦ Month Sr. No. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Complete ¦ Name of the Contractor ¦ Name of Supervisor ¦ PGCIL Person /Quest ¦ Remarks 1 ¦ June'25 ¦ 1 ¦ 8/1 ¦ DA-1.5 ¦ Sandy ¦ 2025-06-26 00:00:00 ¦ 2025-06-26 00:00:00 ¦ M/s. Sanjay Construction ¦ Saddam 2 ¦ June'25 ¦ 2 ¦ 8/2 ¦ DA+3 ¦ Sandy ¦ 2025-06-26 00:00:00 ¦ 2025-06-26 00:00:00 ¦ M/s. Sanjay Construction ¦ Saddam 3 ¦ June'25 ¦ 3 ¦ 8/3 ¦ DA+6 ¦ Sandy ¦ 2025-06-26 00:00:00 ¦ 2025-06-26 00:00:00 ¦ M/s. Sanjay Construction ¦ Saddam 4 ¦ June'25 ¦ 4 ¦ 8/4 ¦ DA+3 ¦ Sandy ¦ 2025-06-26 00:00:00 ¦ 2025-06-26 00:00:00 ¦ M/s. Sanjay Construction ¦ Saddam | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Foundation | 1000 | 26 | foundation, row_hindrance, summary_status | R4: Sr. No. ¦ Month ¦ Month Sr. No. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Completed ¦ Name of the Contractor ¦ Name of Supervisor ¦ State ¦ Village ¦ Tehsil ¦ District ¦ ROW Status (Yes/No) ¦ Action Taken for ROW (To Be Filled By POWERGRID) ¦ Start Date ¦ End Date ¦ PGCIL Person /Quest ¦ Remarks | KEC International Limited 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Details of Foundation ¦ 2026-05-20 00:00:00 Sr. No. ¦ Month ¦ Month Sr. No. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Completed ¦ Name of the Contractor ¦ Name of Supervisor ¦ State ¦ Village ¦ Tehsil ¦ District ¦ ROW Status (Yes/No) ¦ Action Taken for ROW (To Be Filled By POWERGRID) ¦ Start Date ¦ End Date ¦ PGCIL Person /Quest ¦ Remarks 1 ¦ Feb'25 ¦ 1 ¦ 8/1 ¦ DA-1.5 ¦ Sandy ¦ 2025-02-12 00:00:00 ¦ 2025-02-23 00:00:00 ¦ M/s. Sanwariya Technical Developers ¦ Monu Kumar ¦ Rajasthan ¦ DOODIMUKLERA ¦ LUNKARANSAR ¦ BIKANER 2 ¦ Feb'25 ¦ 2 ¦ 8/3 ¦ DA+6 ¦ Sandy ¦ 2025-02-17 00:00:00 ¦ 2025-02-26 00:00:00 ¦ M/s. Sanwariya Technical Developers ¦ Monu Kumar ¦ Rajasthan ¦ JAISAN ¦ LUNKARANSAR ¦ BIKANER 3 ¦ Feb'25 ¦ 3 ¦ 8/6 ¦ DA+0 ¦ Sandy ¦ 2025-02-20 00:00:00 ¦ 2025-02-28 00:00:00 ¦ M/s. MS Construction ¦ Sher Singh Rana ¦ Rajasthan ¦ SADHERAN ¦ LUNKARANSAR ¦ BIKANER 4 ¦ Mar'25 ¦ 1 ¦ 8/5 ¦ DA+0 ¦ Sandy ¦ 2025-02-27 00:00:00 ¦ 2025-03-05 00:00:00 ¦ M/s. MS Construction ¦ Sher Singh Rana ¦ Rajasthan ¦ SADHERAN ¦ LUNKARANSAR ¦ BIKANER | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection Compiled | 1002 | 27 | erection, project_details, row_hindrance, summary_status | R4: Sr. No. ¦ Month ¦ Month Sr. No. ¦ Location No. ¦ Type of Tower ¦ Tower Weight ¦ Starting Date ¦ Completion Date ¦ Gang Name ¦ Name of Supervisor ¦ State ¦ Village ¦ Tehsil ¦ District ¦ ROW Status (Yes/No) ¦ Action Taken for ROW (To Be Filled By POWERGRID) ¦ Start Date ¦ End Date ¦ PGCIL Person /Quest ¦ Remarks | KEC International Limited 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Details of Erection ¦ 2026-05-20 00:00:00 Sr. No. ¦ Month ¦ Month Sr. No. ¦ Location No. ¦ Type of Tower ¦ Tower Weight ¦ Starting Date ¦ Completion Date ¦ Gang Name ¦ Name of Supervisor ¦ State ¦ Village ¦ Tehsil ¦ District ¦ ROW Status (Yes/No) ¦ Action Taken for ROW (To Be Filled By POWERGRID) ¦ Start Date ¦ End Date ¦ PGCIL Person /Quest ¦ Remarks 1 ¦ Aug'25 ¦ 1 ¦ 8/3 ¦ DA+6 ¦ 43.804 ¦ 2025-07-25 00:00:00 ¦ 2025-08-10 00:00:00 ¦ M/s. Kavya Enterprises ¦ Narayan Mahto ¦ Rajasthan ¦ JAISAN ¦ LUNKARANSAR ¦ BIKANER 2 ¦ Aug'25 ¦ 2 ¦ 8/8 ¦ DA+0 ¦ 36.16 ¦ 2025-08-11 00:00:00 ¦ 2025-08-20 00:00:00 ¦ M/s. Kavya Enterprises ¦ Narayan Mahto ¦ Rajasthan ¦ DHEERERAN ¦ LUNKARANSAR ¦ BIKANER 3 ¦ Aug'25 ¦ 3 ¦ 7/9 ¦ DA+3 ¦ 37.931 ¦ 2025-08-13 00:00:00 ¦ 2025-08-20 00:00:00 ¦ M/s. Punam Kumari ¦ Choturam Meena ¦ Rajasthan ¦ DUDIWALI ¦ LUNKARANSAR ¦ BIKANER 4 ¦ Aug'25 ¦ 4 ¦ 18/5 ¦ DA+0 ¦ 36.16 ¦ 2025-08-18 00:00:00 ¦ 2025-08-25 00:00:00 ¦ M/s. Jwala Singh ¦ Monu Kumar ¦ Rajasthan ¦ SURANA ¦ LUNKARANSAR ¦ BIKANER | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tack Welding | 1000 | 26 | earthing_tack | R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Start ¦ Complete ¦ Name of the Gang ¦ Name of Supervisor ¦ Remarks | KEC International Limited 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Details of Tack Welding ¦ 2026-05-20 00:00:00 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Start ¦ Complete ¦ Name of the Gang ¦ Name of Supervisor ¦ Remarks 1 ¦ Mar'26 ¦ 20/5 ¦ DA+0 ¦ 2026-03-23 00:00:00 ¦ 2026-03-23 00:00:00 ¦ RK Construction ¦ Mantu Biswas 2 ¦ Mar'26 ¦ 20/6 ¦ DA+9 ¦ 2026-03-23 00:00:00 ¦ 2026-03-23 00:00:00 ¦ RK Construction ¦ Mantu Biswas 3 ¦ Mar'26 ¦ 20/7 ¦ DA+0 ¦ 2026-03-24 00:00:00 ¦ 2026-03-24 00:00:00 ¦ RK Construction ¦ Mantu Biswas 4 ¦ Mar'26 ¦ 20/4 ¦ DA+0 ¦ 2026-03-24 00:00:00 ¦ 2026-03-24 00:00:00 ¦ RK Construction ¦ Mantu Biswas | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Visual Chart | 1000 | 51 | earthing_tack, erection, foundation, row_hindrance, statutory_crossing, stringing, survey_soil, visual_l2 | R4: S. No. ¦ Description ¦ UOM ¦ Total Qty ¦ Completed ¦ Balance ¦ Power Line Crossing ¦ Stringing U/P ¦ Stringing completed R5: 1 ¦ Foundation ¦ Nos ¦ 319 ¦ 302 ¦ 17 ¦ Tack Welding U/P ¦ Tack Welding completed R6: 2 ¦ Earthing Rod Type ¦ Nos ¦ 319 ¦ 302 ¦ 17 ¦ NH / SH Crossing ¦ Erection U/P ¦ 4 ¦ Erection completed R7: 3 ¦ Earthing Pipe/Counter Poise ¦ Nos ¦ 319 ¦ 269 ¦ 50 ¦ 1 ¦ Foundation U/P ¦ Foundation completed R8: 4 ¦ Tower Erection ¦ Nos ¦ 319 ¦ 217 ¦ 102 ¦ Railway Crossing ¦ Angle Tower ¦ 3 ¦ Angle Tower | KEC INTERNATIONAL LIMITED TA-512 : 765kV D/C Bikaner IV PS to Siwani II (Part-1) TL ¦ Visual Chart S. No. ¦ Description ¦ UOM ¦ Total Qty ¦ Completed ¦ Balance ¦ Power Line Crossing ¦ Stringing U/P ¦ Stringing completed 1 ¦ Foundation ¦ Nos ¦ 319 ¦ 302 ¦ 17 ¦ Tack Welding U/P ¦ Tack Welding completed 2 ¦ Earthing Rod Type ¦ Nos ¦ 319 ¦ 302 ¦ 17 ¦ NH / SH Crossing ¦ Erection U/P ¦ 4 ¦ Erection completed 3 ¦ Earthing Pipe/Counter Poise ¦ Nos ¦ 319 ¦ 269 ¦ 50 ¦ 1 ¦ Foundation U/P ¦ Foundation completed 4 ¦ Tower Erection ¦ Nos ¦ 319 ¦ 217 ¦ 102 ¦ Railway Crossing ¦ Angle Tower ¦ 3 ¦ Angle Tower 5 ¦ Tack Welding ¦ Nos ¦ 319 ¦ 76 ¦ 243 ¦ 1 ¦ Excavation U/P ¦ 2 ¦ Excavation completed | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | WIP | 1003 | 26 | foundation, row_hindrance, summary_status | R6: S.NO. ¦ GANG NAME ¦ LOC. NO. ¦ TYPE ¦ CLASSIFICATION ¦ D.O.S ¦ D.O.C ¦ REMARKS R7: 1 ¦ M/s. Shree Shyam Construction ¦ 1A/0 ¦ DD45+0 ¦ Sandy ¦ Excavation Complete R10: 4 ¦ M/s. Choudhary Construction ¦ 16/0 ¦ DB2+0 ¦ Sandy ¦ 2026-04-13 00:00:00 ¦ No Work Due to ROW R17: S.NO ¦ GANG ¦ LOC. NO. ¦ T.O.T ¦ D.O.S ¦ D.O.C ¦ Remarks R18: 1 ¦ 32/5 ¦ DA+0 ¦ 2026-01-30 00:00:00 ¦ ROW since 03/02/2026 | KEC International Limited DAILY PROGRESS REPORT : STATUS AS ON ¦ 2026-05-20 00:00:00 Name of the Project: ¦ 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Contract No. & Date : ¦ CC/T/W-TW/DOM/A00/24/09582/CA-1&2/25-100174/01 & 02 Dtd. 21.01.2025 FOUNDATION S.NO. ¦ GANG NAME ¦ LOC. NO. ¦ TYPE ¦ CLASSIFICATION ¦ D.O.S ¦ D.O.C ¦ REMARKS 1 ¦ M/s. Shree Shyam Construction ¦ 1A/0 ¦ DD45+0 ¦ Sandy ¦ Excavation Complete 2 ¦ M/s. Shree Shyam Construction ¦ 1/2 ¦ DA+0 ¦ Sandy | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Statuary clearance | 1000 | 26 | statutory_crossing, summary_status | R5: S. No. ¦ Name of NH Being crossed ¦ Between AP nos. ¦ Proposal submitted by M/s KEC International Ltd on dated ¦ Owning Authority ¦ Present status ¦ Target date for submission R6: 1 ¦ NH-62 (Bikaner to Shri Ganga Nagar) ¦ AP-14 to AP-15 ¦ 2025-04-23 00:00:00 ¦ Executive Engineer, NHAI, Bikaner ¦ 1. Online Submission 04/08/2025, Proposal Submitted NHAI OFFICE Bikaner 10/12/2025 R7: 2 ¦ NH-754A (Amritsar to Jam Nagar Expressway) ¦ AP-24 to AP-25 ¦ 2025-06-11 00:00:00 ¦ NHAI, PIU - Hanumangarh ¦ 1. Online Submission to the PGCIL Office on 25/12/2025, R10: S. No. ¦ Name of Railway line being crossed ¦ Between AP nos. ¦ Proposal submitted by M/s KEC International Ltd on dated ¦ Owning Authority ¦ Present status ¦ Target date for submission R11: 1 ¦ Lunkaransar (LKS) to Dulmera (DLC) Railway Station ¦ AP-17 to AP-18 ¦ 2025-04-23 00:00:00 ¦ DRM, Bikaner ¦ 1. Approved By Power Grid RHQ (Engineering). 2. Submitted through online on 02/07/2025. 3. Site Inspection done by concern authority on 23/07/25. 4. Approval Optained Power Grid by Railway Authority. | KEC International Limited 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Details of NH, River, Railway Line & Power Line crossing Proposals of 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL NH Crossings S. No. ¦ Name of NH Being crossed ¦ Between AP nos. ¦ Proposal submitted by M/s KEC International Ltd on dated ¦ Owning Authority ¦ Present status ¦ Target date for submission 1 ¦ NH-62 (Bikaner to Shri Ganga Nagar) ¦ AP-14 to AP-15 ¦ 2025-04-23 00:00:00 ¦ Executive Engineer, NHAI, Bikaner ¦ 1. Online Submission 04/08/2025, Proposal Submitted NHAI OFFICE Bikaner 10/12/2025 2 ¦ NH-754A (Amritsar to Jam Nagar Expressway) ¦ AP-24 to AP-25 ¦ 2025-06-11 00:00:00 ¦ NHAI, PIU - Hanumangarh ¦ 1. Online Submission to the PGCIL Office on 25/12/2025, Railway Line Crossings | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing | 1000 | 26 | stringing, supply | R5: From ¦ To ¦ Length in Km's ¦ Cum. Length in Km's ¦ Insulator Hoisting ¦ Paying Out Start ¦ Paying Out Completed ¦ Final sag ¦ Name of the Contractor ¦ Remarks | KEC International Limited 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Details of Stringing ¦ 2026-05-20 00:00:00 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Section From ¦ To ¦ Length in Km's ¦ Cum. Length in Km's ¦ Insulator Hoisting ¦ Paying Out Start ¦ Paying Out Completed ¦ Final sag ¦ Name of the Contractor ¦ Remarks 1 2 3 | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | OPGW | 1000 | 26 | opgw_accessories, stringing | R4: Cum. Sr.No. ¦ Month Sr.No. ¦ Section ¦ Paying Out Start ¦ Paying Out Completed ¦ Final sag ¦ Name of the Contractor ¦ Remarks R5: From ¦ To ¦ Section Length in Km's ¦ Drum Length in Km's ¦ Cum. Drum Length in Km's | KEC International Limited 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Details of OPGW Stringing ¦ 2026-05-20 00:00:00 Cum. Sr.No. ¦ Month Sr.No. ¦ Section ¦ Paying Out Start ¦ Paying Out Completed ¦ Final sag ¦ Name of the Contractor ¦ Remarks From ¦ To ¦ Section Length in Km's ¦ Drum Length in Km's ¦ Cum. Drum Length in Km's 1 2 3 | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Accessories | 1000 | 26 | opgw_accessories, supply | R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Danger Plate ¦ Number Plate ¦ Phase Plate ¦ Circuit Plate ¦ Anti Climbing device ¦ Start Date ¦ End Date ¦ Name of the Contractor ¦ Name of Supervisor ¦ Remarks | KEC International Limited 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Details of Accessories ¦ 2026-05-20 00:00:00 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Danger Plate ¦ Number Plate ¦ Phase Plate ¦ Circuit Plate ¦ Anti Climbing device ¦ Start Date ¦ End Date ¦ Name of the Contractor ¦ Name of Supervisor ¦ Remarks 1 2 3 4 | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Shield Wire Earthing | 752 | 26 | earthing_tack, opgw_accessories | R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Complete ¦ Name of the Contractor ¦ Name of Supervisor ¦ PGCIL Person /Quest ¦ Remarks | KEC International Limited 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL Details of Shield Wire Earthing ¦ 2026-05-20 00:00:00 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Complete ¦ Name of the Contractor ¦ Name of Supervisor ¦ PGCIL Person /Quest ¦ Remarks 1 ¦ 3/0 ¦ DC2+9 ¦ SANDY 2 ¦ 4/7 ¦ DB1+0 ¦ SANDY 3 ¦ 5/7 ¦ DB1+3 ¦ SANDY 4 ¦ 7/0 ¦ DB1+3 ¦ SANDY | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | TS Gantry - AP47 | 1000 | 29 | statutory_crossing, survey_soil, visual_l2 | R6: Sr. No. ¦ AP No. ¦ TOWER No. ¦ TYPE OF TOWER ¦ For Visual Chart ¦ RAISED CHIMNEY ¦ Section Length (m) ¦ SPAN (Mtr) ¦ CUMULATIVE SPAN ¦ R.L (Mtr) ¦ DEVIATION ANGLE (Deg) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ UTM Coordinates(43) ¦ CROSSING DETAILS ¦ HT of Tower (Mtr) ¦ Village Name ¦ Tehsil Name | CLIENT :- POWERGRID SIWANI TRANSMISSION LIMITED NAME OF PROJECT :- Bikaner-IV PS TO Siwani 765KV D/C (2nd) Transmission Line Part-01 M/s. KEC INTERNATIONAL LIMITED CHECK SURVEY TOWER SCHEDULE SECTION:- PS GANTRY TO AP44 LENGTH :- 123.174 KM KEC/TA512/BSTL/TS/ REV.0 Sr. No. ¦ AP No. ¦ TOWER No. ¦ TYPE OF TOWER ¦ For Visual Chart ¦ RAISED CHIMNEY ¦ Section Length (m) ¦ SPAN (Mtr) ¦ CUMULATIVE SPAN ¦ R.L (Mtr) ¦ DEVIATION ANGLE (Deg) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ UTM Coordinates(43) ¦ CROSSING DETAILS ¦ HT of Tower (Mtr) ¦ Village Name ¦ Tehsil Name Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Easting (m) ¦ Y Northing (m) Gantry ¦ Gantry ¦ 146 ¦ 325896.991 ¦ 3145660.004 ¦ KELAN ¦ CHHATARGARH ¦ BIKANER | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Project Details | 1000 | 11 | project_details | R1: Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer/Manager ¦ PCH ¦ Regional Manager ¦ Project Manager ¦ Section Incharge ¦ Supervisor | Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer/Manager ¦ PCH ¦ Regional Manager ¦ Project Manager ¦ Section Incharge ¦ Supervisor TA 512 ¦ 765KV D/C Bikaner IV PS - Siwani II TL ¦ PGCIL ¦ 2025-01-03 00:00:00 ¦ 2026-12-03 00:00:00 ¦ Saurabh Katiyar ¦ Mr Sanjay Kumar Gupta ¦ Mr Atul Kumar Gupta ¦ Tamojit Bandyopadhyay ¦ Dhiraj kumar Suraji Kumar ¦ Rajkishor muni Babasaheb Kushare ¦ Mahendra Vishvakarma Dular chand Monu Kumar Sher singh Rana Deepak Kumar Mahata | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet1 | 1000 | 1 |  |  |  | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | L3 Plan | 1000 | 26 | earthing_tack, erection, foundation, opgw_accessories, project_details, stringing, survey_soil | R4: SL- No- ¦ New AP NO ¦ Type of Tower ¦ Angle of Deviation ¦ Span ¦ Sectional Length ¦ Detail survey Approval date ¦ Check survey completion date ¦ Foundation classification ¦ Soil investigation date ¦ Foundation dates ¦ Tower erection dates ¦ Earthing ¦ Tac welding ¦ Stringing ¦ OPGW ¦ Final checking offer date R5: Start ¦ Completion ¦ Start ¦ Completion ¦ Start ¦ Completion ¦ Start ¦ Completion ¦ Start ¦ Completion ¦ Start ¦ Completion | CONTRACTOR: Kalpataru Power Transmission Limited Proposed 765kV D/C Sikar II S/S - Aligarh S/S Transmission Line ,Part-3 AS PER APPROVED CHECK SURVEY SL- No- ¦ New AP NO ¦ Type of Tower ¦ Angle of Deviation ¦ Span ¦ Sectional Length ¦ Detail survey Approval date ¦ Check survey completion date ¦ Foundation classification ¦ Soil investigation date ¦ Foundation dates ¦ Tower erection dates ¦ Earthing ¦ Tac welding ¦ Stringing ¦ OPGW ¦ Final checking offer date Start ¦ Completion ¦ Start ¦ Completion ¦ Start ¦ Completion ¦ Start ¦ Completion ¦ Start ¦ Completion ¦ Start ¦ Completion 1 ¦ AP-183/0 ¦ DD60+3 ¦ LT 50° 52' 49" ¦ 2021-06-01 00:00:00 383.176 ¦ 383.176 2 ¦ AP-184/0 ¦ DD60+9 ¦ LT 53° 56' 30" ¦ 2021-06-01 00:00:00 | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Supply DPR | 1000 | 37 | project_details, summary_status, supply, survey_soil | R5: SL NO ¦ DESCRIPTION ¦ UNIT ¦ Total LOA Qty. ¦ Cumulative Qty. as per Check Survey ¦ Cumulative Released for Supply ¦ Unit ¦ RECEIVED Qty. ¦ TOTAL RECEIVED ¦ Total Received ¦ Issued From Store ¦ Consumed ¦ Balance at Store ¦ Balance Req. from Plant ¦ Remarks R9: 1 ¦ DA TYPE NORMAL STUB ¦ Sets ¦ 153 ¦ 100 ¦ 100 ¦ 59 ¦ 56 ¦ 41 R10: 2 ¦ +1M RC STUB ¦ Nos. R11: 3 ¦ .+1.5 M RC Stub Extenssion ¦ Nos. R12: 4 ¦ .+2.5 M RC Stub Extenssion ¦ Nos. | KEC International Limited Name of Line: 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL ¦ 2026-05-20 00:00:00 STORE :- 1: Kosi Kalan, Uttar Pradesh, 2: Hodal, Haryana STUBS & TOWER PARTS (RECEIVED) ¦ 2026-05-20 00:00:00 SL NO ¦ DESCRIPTION ¦ UNIT ¦ Total LOA Qty. ¦ Cumulative Qty. as per Check Survey ¦ Cumulative Released for Supply ¦ Unit ¦ RECEIVED Qty. ¦ TOTAL RECEIVED ¦ Total Received ¦ Issued From Store ¦ Consumed ¦ Balance at Store ¦ Balance Req. from Plant ¦ Remarks HT ¦ MS STUBS A ¦ DA-TYPE | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Power line Crossings | 1000 | 26 | erection, foundation, statutory_crossing, stringing, summary_status, supply | R3: Sr. No. ¦ Crossing Location ¦ Crossing Span ¦ Details of crossing ¦ Owner ¦ Status of proposal ¦ Foundation ¦ Erection ¦ Stringing ¦ Remarks/Critical Needs R4: Target ¦ Requirement ¦ Target ¦ Material Availability ¦ Target ¦ Material Availability R5: From ¦ To ¦ Submission ¦ Approval ¦ Start ¦ End ¦ Stub ¦ Steel ¦ Cement ¦ Gang ¦ Start ¦ End ¦ Tower ¦ BNA ¦ Gang ¦ Start ¦ End ¦ Conductor ¦ Insulator ¦ H/ware | DETAILS OF POWER LINE CROSSING Sr. No. ¦ Crossing Location ¦ Crossing Span ¦ Details of crossing ¦ Owner ¦ Status of proposal ¦ Foundation ¦ Erection ¦ Stringing ¦ Remarks/Critical Needs Target ¦ Requirement ¦ Target ¦ Material Availability ¦ Target ¦ Material Availability From ¦ To ¦ Submission ¦ Approval ¦ Start ¦ End ¦ Stub ¦ Steel ¦ Cement ¦ Gang ¦ Start ¦ End ¦ Tower ¦ BNA ¦ Gang ¦ Start ¦ End ¦ Conductor ¦ Insulator ¦ H/ware 1 ¦ AP 187 ¦ AP 188 ¦ 241 ¦ 66kV D/C 2 ¦ AP 189 ¦ AP 190 ¦ 239 ¦ 220kV D/C 3 ¦ AP 191 ¦ AP 192 ¦ 236 ¦ 220kV S/C 4 ¦ AP 193 ¦ AP 194 ¦ 244 ¦ 400kV S/C | ok
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | 2026-05-20 | Hardware | 1000 | 26 | supply | R3: Sl.No. ¦ Name of the Item ¦ Unit ¦ Required Qty. ¦ Receipt Qty. ¦ Balance Required Qty. ¦ Consumed ¦ Balance R8: 2 ¦ Conductor (AL59 Moose) ¦ KM ¦ 946.35384 ¦ 946.208 ¦ 0.14584000000002106 ¦ 806.6759999999999 ¦ 139.53200000000004 R13: VD for Moose Conductor ¦ No's ¦ 8964 ¦ 8964 ¦ 6552 ¦ 2412 R16: MSJ for Conductor ¦ No's ¦ 336 ¦ 336 ¦ 249 ¦ 87 R18: 4 ¦ Earthwire ¦ KM ¦ 78.082 ¦ 80 ¦ -1.9180000000000064 ¦ 67.223 ¦ 12.777000000000001 | 400KV DC Khetri Sikar Transmission Line Hardware and Conductor Supply and Consumption ¦ 2026-05-20 00:00:00 Sl.No. ¦ Name of the Item ¦ Unit ¦ Required Qty. ¦ Receipt Qty. ¦ Balance Required Qty. ¦ Consumed ¦ Balance 1 ¦ Insulators 120KN Long rod ¦ No's ¦ 648 ¦ 812 ¦ -164 ¦ 540 ¦ 170 160KN Long rod ¦ No's ¦ 2400 ¦ 2397 ¦ 3 ¦ 1596 ¦ 801 120KN Pilot ¦ No's ¦ 129 ¦ 129 ¦ 102 ¦ 102 2 ¦ Conductor (AL59 Moose) ¦ KM ¦ 946.35384 ¦ 946.208 ¦ 0.14584000000002106 ¦ 806.6759999999999 ¦ 139.53200000000004 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Concrete | 134 | 33 | foundation | R4: Sr/No ¦ Tower Type ¦ Tower Extention ¦ Type of Foundation ¦ Concrete Qty (CuM) ¦ Cement Bags in PCC & RCC ¦ As per DrawingTMT-Bar Qty in Kg | KEC International Ltd Date -30.05.2025 Quantities of Concrete, Cement and TMT for Different Types of Tower Foundation WZ4 Sr/No ¦ Tower Type ¦ Tower Extention ¦ Type of Foundation ¦ Concrete Qty (CuM) ¦ Cement Bags in PCC & RCC ¦ As per DrawingTMT-Bar Qty in Kg PCC 1:3:6 ¦ RCC 1:1.5:3 ¦ PCC ¦ RCC ¦ Total Cement Bags ¦ 8mm ¦ 10mm ¦ 12mm ¦ 16mm ¦ 20mm ¦ 25mm ¦ 28mm ¦ 32mm ¦ Total TMT Bar / Each Drg ¦ Plan Location ¦ Cement ¦ 8mm ¦ 10mm ¦ 12mm ¦ 16mm 1 ¦ DA ¦ -3M to 0M ¦ Dry ¦ 1.52 ¦ 15.212 ¦ 6.688000000000001 ¦ 121.696 ¦ 128.384 ¦ 84.11 ¦ 344.18 ¦ 202.75 ¦ 247.66 ¦ 878.6999999999999 2 ¦ DA ¦ -3M to 0M ¦ Sandy ¦ 2.381 ¦ 19.472 ¦ 10.4764 ¦ 155.776 ¦ 166.25240000000002 ¦ 72.968 ¦ 1000.9619999999999 ¦ 312.618 ¦ 244.189 ¦ 1630.7369999999999 ¦ 2 ¦ 332.50480000000005 ¦ 145.936 ¦ 2001.9239999999998 ¦ 625.236 ¦ 488.378 3 ¦ DA ¦ -3M to 0M ¦ Wet ¦ 3.2 ¦ 24.212 ¦ 14.080000000000002 ¦ 193.696 ¦ 207.776 ¦ 84.19 ¦ 599.15 ¦ 858.87 ¦ 311.91 ¦ 243.63 ¦ 2097.75 ¦ 9 ¦ 1869.9840000000002 ¦ 757.71 ¦ 5392.349999999999 ¦ 7729.83 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Summary DPR | 19 | 13 | project_details, summary_status, survey_soil | R5: Sl. No. ¦ Activity ¦ Unit ¦ LOA QTY ¦ Latest Survey Qty ¦ Cumm. Progress up to last Month May25 ¦ Current Month Achieved (As on date ) ¦ Today ¦ Total Status ¦ As per L-2 ¦ Balance ¦ No of Gangs ¦ Remarks R7: 1 ¦ Detailed Survey Completed(Km) ¦ KM ¦ 222.93 ¦ 230.387 ¦ 230.37800000000001 ¦ 230.37800000000001 ¦ 222.93 ¦ 0.00899999999998613 ¦ Physically Done R8: a) ¦ Submission of Detailed Survey ¦ KM ¦ 222.93 ¦ 230.387 ¦ 230.371 ¦ 230.371 ¦ 222.93 ¦ 0.015999999999991132 R9: b) ¦ Approval of Detailed Survey ¦ KM ¦ 222.93 ¦ 230.387 ¦ 230.37 ¦ 230.37 ¦ 222.93 ¦ 0.016999999999995907 R10: 2 ¦ Check Survey ¦ KM ¦ 222.93 ¦ 230.387 ¦ 230.37 ¦ 230.37 ¦ 222.93 ¦ 0.016999999999995907 | TA-513 :400 KV D/C Quad ¦ 2025-07-20 00:00:00 Name of Client: Power Grid Corporation of India Name of Line: 400 KV D/C Siwani To Patran TL + 400 KV D/C Siwani To Fatehabad TL Office: Agroha (Hisar) Sl. No. ¦ Activity ¦ Unit ¦ LOA QTY ¦ Latest Survey Qty ¦ Cumm. Progress up to last Month May25 ¦ Current Month Achieved (As on date ) ¦ Today ¦ Total Status ¦ As per L-2 ¦ Balance ¦ No of Gangs ¦ Remarks 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7=4+5+6 ¦ 8 ¦ 9=3-7 ¦ 10 ¦ 11 1 ¦ Detailed Survey Completed(Km) ¦ KM ¦ 222.93 ¦ 230.387 ¦ 230.37800000000001 ¦ 230.37800000000001 ¦ 222.93 ¦ 0.00899999999998613 ¦ Physically Done a) ¦ Submission of Detailed Survey ¦ KM ¦ 222.93 ¦ 230.387 ¦ 230.371 ¦ 230.371 ¦ 222.93 ¦ 0.015999999999991132 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | DPR S-F & S-P (2) | 65 | 19 | summary_status, survey_soil | R10: 1 ¦ Detailed Survey Completed(Km) ¦ KM ¦ 144.2 ¦ 147.69 ¦ 147.69 ¦ 147.69 ¦ 144.2 R11: a) ¦ Submission of Detailed Survey ¦ KM ¦ 144.2 ¦ 147.69 ¦ 140.74 ¦ 140.74 ¦ 144.2 ¦ 6.949999999999989 ¦ Pending Due to route Alingement Approval ¦ AP101-119 ¦ 14.92 ¦ Balanced To Approve R12: b) ¦ Approval of Detailed Survey ¦ KM ¦ 144.2 ¦ 147.69 ¦ 140.74 ¦ 140.74 ¦ 144.2 ¦ 6.949999999999989 ¦ AP5 To AP14 ¦ 13.34 ¦ Balanced To Submitted R13: 2 ¦ Check Survey ¦ KM ¦ 144.2 ¦ 147.69 ¦ 126.678 ¦ 14.06 ¦ 140.738 ¦ 125 ¦ 6.951999999999998 ¦ AP33 To AP35 ¦ 0.72 R14: a) ¦ Check Survey Submision ¦ KM ¦ 144.2 ¦ 147.69 ¦ 126.678 ¦ 14.06 ¦ 140.738 ¦ 125 ¦ 6.951999999999998 ¦ AP119-Gantry ¦ 0.36 | TA-513 :400 KV D/C Quad ¦ 2025-08-13 00:00:00 Name of Client: Power Grid Corporation of India Name of Line: 400 KV D/C Siwani To Patran TL Office: Agroha (Hisar) 400 KV Siwani To Patran TL ¦ 2025-08-13 00:00:00 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7=4+5+6 ¦ 8 ¦ 9=3-7 ¦ 10 ¦ 11 1 ¦ Detailed Survey Completed(Km) ¦ KM ¦ 144.2 ¦ 147.69 ¦ 147.69 ¦ 147.69 ¦ 144.2 a) ¦ Submission of Detailed Survey ¦ KM ¦ 144.2 ¦ 147.69 ¦ 140.74 ¦ 140.74 ¦ 144.2 ¦ 6.949999999999989 ¦ Pending Due to route Alingement Approval ¦ AP101-119 ¦ 14.92 ¦ Balanced To Approve | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Summary | 41 | 14 | project_details, summary_status, survey_soil | R7: Sl. No. ¦ Activity ¦ Unit ¦ LOA QTY ¦ Latest Survey Qty ¦ Cumm. Progress up to last Month April-26 ¦ Current Month Achieved (As on date ) ¦ Today ¦ Total Status ¦ As per L-2 till (May-2026) ¦ Balance ¦ No of Gangs ¦ Remarks R9: 1 ¦ Detailed Survey Completed ¦ KM ¦ 144.2 ¦ 147.584 ¦ 147.57500000000002 ¦ 147.57500000000002 ¦ 144.2 ¦ 0.00899999999998613 R10: a) ¦ Submission of Detailed Survey ¦ KM ¦ 144.2 ¦ 147.584 ¦ 147.57500000000002 ¦ 147.57500000000002 ¦ 144.2 ¦ 0.00899999999998613 R11: b) ¦ Approval of Detailed Survey ¦ KM ¦ 144.2 ¦ 147.584 ¦ 147.57500000000002 ¦ 147.57500000000002 ¦ 144.2 ¦ 0.00899999999998613 R12: 2 ¦ Check Survey ¦ KM ¦ 144.2 ¦ 147.584 ¦ 147.57500000000002 ¦ 147.57500000000002 ¦ 144.2 ¦ 0.00899999999998613 | TA-513 :400 KV D/C Quad ¦ 2026-05-19 00:00:00 Name of Client : Powergrid Bikaner IV Transmission limited Name of Line : 400 KV D/C Siwani To Patran TL & 400 KV Siwani to Fatehabad TL NOA No: CC/T/W-TW/DOM/A04/24/10225/NOA-2/25-100881/02 dated-22.01.2025 Project Completion Date : 21.12.2026 400 KV Siwani To Patran TL Sl. No. ¦ Activity ¦ Unit ¦ LOA QTY ¦ Latest Survey Qty ¦ Cumm. Progress up to last Month April-26 ¦ Current Month Achieved (As on date ) ¦ Today ¦ Total Status ¦ As per L-2 till (May-2026) ¦ Balance ¦ No of Gangs ¦ Remarks 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7=4+5+6 ¦ 8 ¦ 9=3-7 ¦ 10 ¦ 11 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | ERT | 70 | 13 | survey_soil | R6: S.No ¦ Approx. Distance (3Kms) ¦ Chainage in Kms ¦ Instrument Reading (R) (Ohm) ¦ S.R. Value (P=2πARX1) (ohm-m) ¦ Remarks ¦ S.No ¦ Approx. Distance (3Kms) ¦ Chainage in Kms ¦ Instrument Reading (R) (Ohm) ¦ S.R. Value (P=2πARX1) (ohm-m) ¦ Remarks R7: 1 ¦ AP1A/0 ¦ 0.2 ¦ 0.07500000000000001 ¦ 23.571428571428573 ¦ Completed ¦ 1 ¦ GANTY SS SIWANI R8: 2 ¦ AP1B/0 ¦ 1.219 ¦ 0.185 ¦ 58.14285714285714 ¦ Completed ¦ 2 ¦ 1C/0 ¦ 1.349 ¦ 0.0655 ¦ 20.58571428571429 ¦ Completed R9: 3 ¦ 2C/0 ¦ 4.009 ¦ 0.14 ¦ 44.00000000000001 ¦ Completed ¦ 3 ¦ 2A/0 ¦ 4.337 ¦ 0.01 ¦ 3.142857142857143 ¦ Completed R10: 4 ¦ 3/0 ¦ 6.527 ¦ 0.13 ¦ 40.857142857142854 ¦ Completed ¦ 4 ¦ 2D/0 ¦ 6.47 ¦ 0.11 ¦ 34.57142857142857 ¦ Completed | Client-Powergrid Bikaner IV Tranmission Limited Project-Siwani-Patran TL & Siwani-Fatehabad TL Soil Resistivity Details Soil Resitivity-Siwani-Fatehabad TL ¦ Soil Resitivity-Siwani-Patran TL S.No ¦ Approx. Distance (3Kms) ¦ Chainage in Kms ¦ Instrument Reading (R) (Ohm) ¦ S.R. Value (P=2πARX1) (ohm-m) ¦ Remarks ¦ S.No ¦ Approx. Distance (3Kms) ¦ Chainage in Kms ¦ Instrument Reading (R) (Ohm) ¦ S.R. Value (P=2πARX1) (ohm-m) ¦ Remarks 1 ¦ AP1A/0 ¦ 0.2 ¦ 0.07500000000000001 ¦ 23.571428571428573 ¦ Completed ¦ 1 ¦ GANTY SS SIWANI 2 ¦ AP1B/0 ¦ 1.219 ¦ 0.185 ¦ 58.14285714285714 ¦ Completed ¦ 2 ¦ 1C/0 ¦ 1.349 ¦ 0.0655 ¦ 20.58571428571429 ¦ Completed 3 ¦ 2C/0 ¦ 4.009 ¦ 0.14 ¦ 44.00000000000001 ¦ Completed ¦ 3 ¦ 2A/0 ¦ 4.337 ¦ 0.01 ¦ 3.142857142857143 ¦ Completed | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | LS | 26 | 10 | row_hindrance, visual_l2 |  | Client-Powergrid Bikaner IV Tranmission Limited Project-Siwani-Patran TL & Siwani-Fatehabad TL Land Schedule Data Land Schedule Verified State ¦ District ¦ Tehsil ¦ Line Length (Km) ¦ Total Locations ¦ Corridor Data Submitted (Km) ¦ Verified from Patwari ¦ Sketch Prepared ¦ Balance Sketch Siwani-Patran ¦ Haryana ¦ Bhiwani ¦ Siwani ¦ 22.072 ¦ 60 ¦ 22.072 ¦ 59 ¦ 39 ¦ 21 Hisar ¦ Balsamand ¦ 4.048 ¦ 10 ¦ 4.048 ¦ 10 ¦ 10 Hisar ¦ 41.98 ¦ 110 ¦ 41.98 ¦ 110 ¦ 106 ¦ 4 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Survey | 43 | 18 | summary_status, survey_soil | R4: Sl.No. ¦ SPAN ¦ Section Length (Km) ¦ Submitted For Approval ¦ Approved Date ¦ Approved Status ¦ Remarks ¦ Sl.No. ¦ SPAN ¦ Section Length (Km) ¦ Submitted For Approval ¦ PGCIL Letter Date ¦ PGCIL Aprroval Mail Date ¦ Approved Status R21: Sl.No. ¦ SPAN ¦ Section Length (Km) ¦ Submitted For Approval ¦ Approval Date ¦ Status ¦ Remarks ¦ Sl.No. ¦ SPAN ¦ Section Length (Km) ¦ Submitted For Approval ¦ PGCIL Letter Date ¦ PGCIL Aprroval Mail Date ¦ Approval Date R38: Sl.No. ¦ SPAN ¦ Submitted For Approval ¦ Status ¦ Remarks | KEC International Limited ¦ KEC International Limited 400 KV D/C Siwani To Fatehabad ¦ 400 KV D/C Siwani To Patran Detailed Survey ¦ Detailed Survey Sl.No. ¦ SPAN ¦ Section Length (Km) ¦ Submitted For Approval ¦ Approved Date ¦ Approved Status ¦ Remarks ¦ Sl.No. ¦ SPAN ¦ Section Length (Km) ¦ Submitted For Approval ¦ PGCIL Letter Date ¦ PGCIL Aprroval Mail Date ¦ Approved Status From Section ¦ To Section ¦ From Section ¦ To Section 1 ¦ 3/0 ¦ 14/0 ¦ 26.427 ¦ 24.05.2025 ¦ 26.05.2025 ¦ Approved ¦ 1 ¦ 3/0 ¦ 5/0 ¦ 6.312 ¦ 15.05.2025 ¦ 17.05.2025 ¦ Approved 2 ¦ 14/0 ¦ 24/0 ¦ 16.986 ¦ 03.04.2025 ¦ 01.05.2025 ¦ Approved ¦ 2 ¦ 14/0 ¦ 29/0 ¦ 22.093 ¦ 10.04.2025 ¦ 17.05.2025 ¦ Approved 3 ¦ 24/0 ¦ 30/0 ¦ 5.64 ¦ 07.03.2025 ¦ 05.4.2025 ¦ Approved ¦ 3 ¦ 29/0 ¦ 33/0 ¦ 8.699 ¦ 10.04.2025 ¦ 17.05.2025 ¦ Approved | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | T.Marking | 20 | 11 | row_hindrance, summary_status | R1: Client-Powergrid Bikaner IV Tranmission Limited ¦ Line ¦ Line Length ¦ Compl ¦ ROW R6: S.NO ¦ Section ¦ Section Length (KM) ¦ Status ¦ S.NO ¦ Section ¦ Section Length (KM) ¦ Status R7: From ¦ To ¦ From ¦ To R8: 1 ¦ S.Gantry ¦ AP-5 ¦ 13.157 ¦ The farmer has refused to allow the commencement of work due to ROW ¦ 1 ¦ S.Gantry ¦ AP-3 ¦ 6.528 ¦ The farmer has refused to allow the commencement of work due to ROW R9: 2 ¦ AP-5 ¦ AP-7 ¦ 2.616 ¦ Completed ¦ 2 ¦ AP-3 ¦ 5/1 ¦ 7.398 ¦ Completed | Client-Powergrid Bikaner IV Tranmission Limited ¦ Line ¦ Line Length ¦ Compl ¦ ROW Project-Siwani-Patran TL & Siwani-Fatehabad TL ¦ SP ¦ 147.586 ¦ 103.806 ¦ 43.780000000000015 Tree Marking Details ¦ SF ¦ 82.798 ¦ 61.251999999999995 ¦ 21.546000000000006 400 Kv Siwani-Patran TL ¦ 400 Kv Siwani-fatehabad TL S.NO ¦ Section ¦ Section Length (KM) ¦ Status ¦ S.NO ¦ Section ¦ Section Length (KM) ¦ Status From ¦ To ¦ From ¦ To 1 ¦ S.Gantry ¦ AP-5 ¦ 13.157 ¦ The farmer has refused to allow the commencement of work due to ROW ¦ 1 ¦ S.Gantry ¦ AP-3 ¦ 6.528 ¦ The farmer has refused to allow the commencement of work due to ROW 2 ¦ AP-5 ¦ AP-7 ¦ 2.616 ¦ Completed ¦ 2 ¦ AP-3 ¦ 5/1 ¦ 7.398 ¦ Completed | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | VC -SF | 110 | 50 | earthing_tack, erection, foundation, row_hindrance, statutory_crossing, stringing, visual_l2 | R4: S. No. ¦ Description ¦ UOM ¦ Total qty ¦ Completed ¦ Balance ¦ Power Line Crossing ¦ Stringing U/P ¦ Stringing completed R5: 1 ¦ Foundation ¦ Nos ¦ 222 ¦ 24 ¦ 198 ¦ Tack Welding U/P ¦ Tack Welding completed R6: 2 ¦ Earthing ¦ Nos ¦ 222 ¦ 10 ¦ 212 ¦ NH / SH Crossing ¦ Erection U/P ¦ 4 ¦ Erection completed R7: 3 ¦ Tower Erection ¦ Nos ¦ 222 ¦ 7 ¦ 215 ¦ 1 ¦ Foundation U/P ¦ 2 ¦ Foundation completed R8: 4 ¦ Rough Sag ¦ KM ¦ 82.97 ¦ 82.97 ¦ Railway Crossing | KEC INTERNATIONAL LIMITED Visual Chart(400 KV D/C Siwani-Fatehabad TL ) S. No. ¦ Description ¦ UOM ¦ Total qty ¦ Completed ¦ Balance ¦ Power Line Crossing ¦ Stringing U/P ¦ Stringing completed 1 ¦ Foundation ¦ Nos ¦ 222 ¦ 24 ¦ 198 ¦ Tack Welding U/P ¦ Tack Welding completed 2 ¦ Earthing ¦ Nos ¦ 222 ¦ 10 ¦ 212 ¦ NH / SH Crossing ¦ Erection U/P ¦ 4 ¦ Erection completed 3 ¦ Tower Erection ¦ Nos ¦ 222 ¦ 7 ¦ 215 ¦ 1 ¦ Foundation U/P ¦ 2 ¦ Foundation completed 4 ¦ Rough Sag ¦ KM ¦ 82.97 ¦ 82.97 ¦ Railway Crossing 5 ¦ Final Sag ¦ KM ¦ 82.97 ¦ 82.97 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | VC -SP | 182 | 48 | earthing_tack, erection, foundation, row_hindrance, statutory_crossing, stringing, visual_l2 | R4: S. No. ¦ Description ¦ UOM ¦ Total qty ¦ Completed ¦ Balance ¦ Power Line Crossing ¦ Stringing U/P ¦ Stringing completed R5: 1 ¦ Foundation ¦ Nos ¦ 399 ¦ 57 ¦ 342 ¦ Tack Welding U/P ¦ Tack Welding completed R6: 2 ¦ Earthing ¦ Nos ¦ 399 ¦ 7 ¦ 392 ¦ NH / SH Crossing ¦ Erection U/P ¦ 4 ¦ Erection completed R7: 3 ¦ Tower Erection ¦ Nos ¦ 399 ¦ 22 ¦ 377 ¦ 1 ¦ Foundation U/P ¦ 2 ¦ Foundation completed R8: 4 ¦ Rough Sag ¦ KM ¦ 147.69 ¦ 147.69 ¦ Railway Crossing | KEC INTERNATIONAL LIMITED Visual Chart(400 KV D/C Siwani-Patran TL ) S. No. ¦ Description ¦ UOM ¦ Total qty ¦ Completed ¦ Balance ¦ Power Line Crossing ¦ Stringing U/P ¦ Stringing completed 1 ¦ Foundation ¦ Nos ¦ 399 ¦ 57 ¦ 342 ¦ Tack Welding U/P ¦ Tack Welding completed 2 ¦ Earthing ¦ Nos ¦ 399 ¦ 7 ¦ 392 ¦ NH / SH Crossing ¦ Erection U/P ¦ 4 ¦ Erection completed 3 ¦ Tower Erection ¦ Nos ¦ 399 ¦ 22 ¦ 377 ¦ 1 ¦ Foundation U/P ¦ 2 ¦ Foundation completed 4 ¦ Rough Sag ¦ KM ¦ 147.69 ¦ 147.69 ¦ Railway Crossing 5 ¦ Final Sag ¦ KM ¦ 147.69 ¦ 147.69 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Ere S-P | 38 | 7 | erection | R5: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Start ¦ Complete ¦ Remarks | KEC International Limited 400 KV D/C (Quad) Siwani-Patran TL Details of Tower Erection CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Start ¦ Complete ¦ Remarks 2025-10-01 00:00:00 1 ¦ 1 ¦ 28/3 ¦ DA+6 ¦ 25.10.2025 ¦ 31.10.2025 ¦ Compl 2025-11-01 00:00:00 2 ¦ 1 ¦ 28/2 ¦ DA+3 ¦ 31.10.2025 ¦ 03.11.2025 ¦ Compl | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Ere S-F | 15 | 7 | erection | R5: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Start ¦ Complete ¦ Remarks | KEC International Limited 400 KV D/C (Quad) Siwani-Fatehabad TL Details of Tower Erection CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Start ¦ Complete ¦ Remarks 2025-09-01 00:00:00 1 ¦ 1 ¦ 25/2 ¦ DA+0 ¦ 17.09.2025 ¦ 22.09.2025 ¦ Compl 2 ¦ 2 ¦ 25/1 ¦ DA+1.5 ¦ 23.09.2025 ¦ 29.09.2025 ¦ Compl 2025-10-01 00:00:00 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | FDN S-F | 36 | 10 | foundation, project_details | R5: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Location No. ¦ Type of Tower ¦ Type of Classification ¦ Starting Date ¦ Completion Date ¦ Remarks ¦ Village ¦ Tehsil | KEC International Limited 400 KV D/C (Quad) Siwani-Fatehabad TL Details of Foundations CUMM. SR.NO ¦ MONTH SR.NO. ¦ Location No. ¦ Type of Tower ¦ Type of Classification ¦ Starting Date ¦ Completion Date ¦ Remarks ¦ Village ¦ Tehsil 1 ¦ 1 ¦ 25/1 ¦ DA+1.5 ¦ WET ¦ 22.03.2025 ¦ 28.03.2025 ¦ Prop ¦ Kaijlan ¦ Adampur 2025-04-01 00:00:00 2 ¦ 1 ¦ 25/2 ¦ DA+0 ¦ WET ¦ 25.03.2025 ¦ 01.04.2025 ¦ Prop ¦ Ashrawan ¦ Adampur 3 ¦ 2 ¦ 24/2 ¦ DA+0 ¦ WET ¦ 30.03.2025 ¦ 04.04.2025 ¦ Prop ¦ Mallapur ¦ Adampur | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | FDN S-P | 75 | 23 | foundation, project_details | R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Location No. ¦ Type of Tower ¦ Type of Classification ¦ Starting Date ¦ Completion Date ¦ Remarks ¦ Village ¦ Tehsil R42: 34 ¦ 2 ¦ 36/3 ¦ 5DA+0 ¦ Dry ¦ 2025-07-26 00:00:00 ¦ 20.08.2025 ¦ Prop ¦ Landhari sukh nambran ¦ Hisar R45: 36 ¦ 1 ¦ 36/4 ¦ 5DA-3 ¦ Dry ¦ 21.08.2025 ¦ 01.09.2025 ¦ Prop ¦ Landhari sukh nambran ¦ Hisar | KEC International Limited ¦ WET ¦ WP ¦ SANDY ¦ PS ¦ DRY 400 KV D/C (Quad) Siwani-Patran TL ¦ 3 ¦ 1 ¦ 9 Details of Foundation CUMM. SR.NO ¦ MONTH SR.NO. ¦ Location No. ¦ Type of Tower ¦ Type of Classification ¦ Starting Date ¦ Completion Date ¦ Remarks ¦ Village ¦ Tehsil 1 ¦ 1 ¦ 30/3 ¦ DA-3 ¦ WET ¦ 21.04.2025 ¦ 22.04.2025 ¦ Template ¦ Durjanpur ¦ Hisar 2 ¦ 2 ¦ 30/1 ¦ DA+3 ¦ WET ¦ 22.04.2025 ¦ 25.04.2025 ¦ Template ¦ Durjanpur ¦ Hisar ¦ S.NO ¦ Tower ¦ Type ¦ Windzone ¦ Classification( Excecuted Locations) 3 ¦ 3 ¦ 30/2 ¦ DA+3 ¦ WET ¦ 24.04.2025 ¦ 28.04.2025 ¦ Template ¦ Durjanpur ¦ Hisar ¦ WET ¦ WP ¦ SANDY ¦ PS ¦ DRY ¦ Total 2025-05-01 00:00:00 ¦ 1 ¦ DA ¦ -3M TO 0M ¦ 4 ¦ 13 ¦ 1 ¦ 4 ¦ 2 ¦ 20 ¦ 8 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | T.Abstract | 55 | 30 | foundation, supply | R3: TOT ¦ Tower qty ¦ TOT ¦ Tower qty ¦ TOT ¦ Tower qty ¦ TOT ¦ Tower qty ¦ TOT ¦ Tower qty ¦ TOT ¦ Tower qty ¦ Foundation ¦ Stub ¦ BOM ¦ Tower ¦ BOM ¦ Prop ¦ Template ¦ Foundation | Siwani-Fatehabad TL ¦ Siwani-Patran TL ¦ Total ¦ WZ-04-Drawing Availability ¦ WZ-05-Drawing Availability TOT ¦ Tower qty ¦ TOT ¦ Tower qty ¦ TOT ¦ Tower qty ¦ TOT ¦ Tower qty ¦ TOT ¦ Tower qty ¦ TOT ¦ Tower qty ¦ Foundation ¦ Stub ¦ BOM ¦ Tower ¦ BOM ¦ Prop ¦ Template ¦ Foundation DA+0 ¦ 52 ¦ 5DA+0 ¦ 2 ¦ DA+0 ¦ 47 ¦ 5DA+0 ¦ 48 ¦ DA+0 ¦ 99 ¦ 5DA+0 ¦ 50 ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A DA+1.5 ¦ 4 ¦ 5DA+1.5 ¦ DA+1.5 ¦ 1 ¦ 5DA+1.5 ¦ DA+1.5 ¦ 5 ¦ 5DA+1.5 ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A DA+3 ¦ 27 ¦ 5DA+3 ¦ 4 ¦ DA+3 ¦ 38 ¦ 5DA+3 ¦ 39 ¦ DA+3 ¦ 65 ¦ 5DA+3 ¦ 43 ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A DA+4.5 ¦ 5DA+4.5 ¦ DA+4.5 ¦ 5DA+4.5 ¦ DA+4.5 ¦ 5DA+4.5 ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A DA+6 ¦ 22 ¦ 5DA+6 ¦ 6 ¦ DA+6 ¦ 15 ¦ 5DA+6 ¦ 47 ¦ DA+6 ¦ 37 ¦ 5DA+6 ¦ 53 ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A DA+9 ¦ 8 ¦ 5DA+9 ¦ 6 ¦ DA+9 ¦ 5 ¦ 5DA+9 ¦ 19 ¦ DA+9 ¦ 13 ¦ 5DA+9 ¦ 25 ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A ¦ A | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Supply. | 186 | 16382 | opgw_accessories, summary_status, supply, visual_l2 | R2: Sl. No. ¦ Description ¦ UOM ¦ LE ¦ Final LE ¦ L2 Sch till March''26 ¦ Receipt Material ¦ Reciept Qty ¦ Balance ¦ Remarks R5: 1 ¦ Stubs ¦ Sets ¦ 220 ¦ 399 ¦ 619 ¦ 597 ¦ 189 ¦ 324 ¦ 513 ¦ 106 R6: Wind zone -04 -Stub ¦ Sets ¦ 173 ¦ 152 ¦ 325 ¦ 153 ¦ 118 ¦ 271 ¦ 54 ¦ Supply Underprogress R7: Wind Zone -05-Stub ¦ Sets ¦ 47 ¦ 247 ¦ 294 ¦ 36 ¦ 206 ¦ 242 ¦ 52 R11: 3 ¦ Conductor ¦ KM ¦ 1908 ¦ 3495 ¦ 5403 ¦ 3800 ¦ 1908 ¦ 2976 ¦ 4884 ¦ 519 | SUPPLY STATUS SUMMARY (Siwani-Patran TL & Siwani-Fatehabad TL Sl. No. ¦ Description ¦ UOM ¦ LE ¦ Final LE ¦ L2 Sch till March''26 ¦ Receipt Material ¦ Reciept Qty ¦ Balance ¦ Remarks SF ¦ SP ¦ SF ¦ SP ¦ Qty. I ¦ SUPPLY 1 ¦ Stubs ¦ Sets ¦ 220 ¦ 399 ¦ 619 ¦ 597 ¦ 189 ¦ 324 ¦ 513 ¦ 106 Wind zone -04 -Stub ¦ Sets ¦ 173 ¦ 152 ¦ 325 ¦ 153 ¦ 118 ¦ 271 ¦ 54 ¦ Supply Underprogress Wind Zone -05-Stub ¦ Sets ¦ 47 ¦ 247 ¦ 294 ¦ 36 ¦ 206 ¦ 242 ¦ 52 2 ¦ Towers ¦ Nos ¦ 220 ¦ 399 ¦ 619 ¦ 490 ¦ 167 ¦ 300 ¦ 467 ¦ 152 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Crossing status | 96 | 12 | foundation, statutory_crossing, summary_status | R2: Sl. ¦ Line ¦ From ¦ To ¦ Name of Crossing ¦ Owner ¦ Approval status ¦ Status ¦ Remarks R3: No ¦ FDN ¦ ERE ¦ STR R5: 1 ¦ SP ¦ 2B ¦ 2C ¦ 132 KV S/C HISAR-RAJGARH TL ¦ HVPNL ¦ In Progress R9: 5 ¦ SP ¦ 49/0 ¦ 50/0 ¦ 400 KV D/C KHEDAR-FATEHABAD TL HVPNL ¦ HVPNL ¦ In Progress R11: 7 ¦ SP ¦ 57/0 ¦ 58/0 ¦ 400 KV D/C MOGA-HISAR TL ¦ PGCIL ¦ In Progress | Crossing Status Sl. ¦ Line ¦ From ¦ To ¦ Name of Crossing ¦ Owner ¦ Approval status ¦ Status ¦ Remarks No ¦ FDN ¦ ERE ¦ STR Power Line Crossing–26 nos 1 ¦ SP ¦ 2B ¦ 2C ¦ 132 KV S/C HISAR-RAJGARH TL ¦ HVPNL ¦ In Progress 2 ¦ SP ¦ 35/0 ¦ 36/0 ¦ 132 KV D/C HISAR-FATEHABAD TL HVPNL ¦ HVPNL ¦ Approved ¦ NOC Received on date : 24.12.2025 3 ¦ SP ¦ 38/0 ¦ 39/0 ¦ 132 KV S/C KIROR-ADAMPUR TL HVPNL ¦ HVPNL ¦ Approved ¦ NOC Received on date : 24.12.2025 4 ¦ SP ¦ 40/0 ¦ 41/0 ¦ 220 kV D/C MAYAR - FATEHABAD TL HVPNL ¦ HVPNL ¦ Approved ¦ NOC Received on date : 02.04.2026 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Erection Compiled | 31 | 10 | erection, project_details, summary_status | R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Line ¦ Location No. ¦ Type of Tower ¦ Starting Date ¦ Completion Date ¦ Tower Weight(MT) ¦ Gang Name ¦ Status R6: 1 ¦ 1 ¦ Siwani-Fatehabad TL ¦ 25/2 ¦ DA+0 ¦ 17.09.2025 ¦ 22.09.2025 ¦ 16.966724000000003 ¦ Anil Construction ¦ Completed R7: 2 ¦ 2 ¦ Siwani-Fatehabad TL ¦ 25/1 ¦ DA+1.5 ¦ 23.09.2025 ¦ 29.09.2025 ¦ 17.633662 ¦ Anil Construction ¦ Completed R9: 3 ¦ 1 ¦ Siwani-Fatehabad TL ¦ 24/4 ¦ DA+1.5 ¦ 29.09.2025 ¦ 03.10.2025 ¦ 17.633662 ¦ Anil Construction ¦ Completed R10: 4 ¦ 2 ¦ Siwani-Fatehabad TL ¦ 26/2 ¦ DA+6 ¦ 03.10.2025 ¦ 09.10.2025 ¦ 21.096916000000004 ¦ Anil Construction ¦ Completed | KEC International Limited 400 KV D/C (Quad) Siwani-fatehabad TL & Siwani-Patran TL Details of Tower Erection CUMM. SR.NO ¦ MONTH SR.NO. ¦ Line ¦ Location No. ¦ Type of Tower ¦ Starting Date ¦ Completion Date ¦ Tower Weight(MT) ¦ Gang Name ¦ Status 2025-09-01 00:00:00 1 ¦ 1 ¦ Siwani-Fatehabad TL ¦ 25/2 ¦ DA+0 ¦ 17.09.2025 ¦ 22.09.2025 ¦ 16.966724000000003 ¦ Anil Construction ¦ Completed 2 ¦ 2 ¦ Siwani-Fatehabad TL ¦ 25/1 ¦ DA+1.5 ¦ 23.09.2025 ¦ 29.09.2025 ¦ 17.633662 ¦ Anil Construction ¦ Completed 2025-10-01 00:00:00 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Sheet5 | 1 | 9 | project_details, summary_status | R1: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Location No ¦ Type of Tower ¦ Tower Weight ¦ Gang Name ¦ Starting date ¦ Completion Date ¦ Status | CUMM. SR.NO ¦ MONTH SR.NO. ¦ Location No ¦ Type of Tower ¦ Tower Weight ¦ Gang Name ¦ Starting date ¦ Completion Date ¦ Status | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Earthing S-P | 13 | 11 | earthing_tack | R5: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Complete ¦ Type of Earthing ¦ Before Earthing Value ¦ After Earthing Value ¦ Remarks | KEC International Limited 400 KV D/C (Quad) Siwani-Patran TL Details of Earthing TFR CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Complete ¦ Type of Earthing ¦ Before Earthing Value ¦ After Earthing Value ¦ Remarks 1 ¦ 1 ¦ 29/1 ¦ DA+0 ¦ Sandy ¦ 2025-08-11 00:00:00 ¦ 2025-08-11 00:00:00 ¦ Pipe type ¦ 1.33 ¦ 0.99 2 ¦ 2 ¦ 28/2 ¦ DA+3 ¦ Sandy ¦ 2025-08-11 00:00:00 ¦ 2025-08-11 00:00:00 ¦ Pipe type ¦ 1.31 ¦ 0.78 3 ¦ 3 ¦ 28/3 ¦ DA+6 ¦ Sandy ¦ 2025-08-11 00:00:00 ¦ 2025-08-11 00:00:00 ¦ Pipe type ¦ 4.07 ¦ 3.44 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Supply | 53 | 16 | opgw_accessories, project_details, summary_status, supply | R3: Sl. No. ¦ Description ¦ Supplier ¦ UOM ¦ LOA Qty ¦ Total LOA Qty ¦ Received Qty ¦ Balance To Received ¦ Remarks R6: 1 ¦ Stubs ¦ KEC ¦ Sets ¦ 210 ¦ 387 ¦ 597 ¦ 189 ¦ 324 ¦ 513 ¦ 84 R8: 3 ¦ Conductor ¦ APAR ¦ KM ¦ 1908 ¦ 3495 ¦ 5403 ¦ 1597 ¦ 2200 ¦ 3797 ¦ 1606 ¦ Supply Under progress(1008KM) R9: 4 ¦ Conductor Accessories H/W ¦ MOSDORFER ¦ % ¦ 1 ¦ 1 ¦ 1 ¦ 0.5 ¦ 0.5 ¦ 0.5 ¦ 0.5 R10: 5 ¦ Earthwire ¦ Nirmal Wire ¦ KM ¦ 80 ¦ 150 ¦ 230 ¦ 57 ¦ 105 ¦ 162 ¦ 68 | SUPPLY STATUS SUMMARY ¦ 2026-05-19 00:00:00 Name of Line-400 KV D/C Siwani To Fatehabad TL & 400 KV D/C Siwani To Patran TL. Sl. No. ¦ Description ¦ Supplier ¦ UOM ¦ LOA Qty ¦ Total LOA Qty ¦ Received Qty ¦ Balance To Received ¦ Remarks S-F ¦ S-P ¦ S-F ¦ S-P ¦ Total I ¦ SUPPLY 1 ¦ Stubs ¦ KEC ¦ Sets ¦ 210 ¦ 387 ¦ 597 ¦ 189 ¦ 324 ¦ 513 ¦ 84 2 ¦ Towers ¦ KEC ¦ Nos ¦ 210 ¦ 387 ¦ 597 ¦ 165 ¦ 297 ¦ 462 ¦ 135 3 ¦ Conductor ¦ APAR ¦ KM ¦ 1908 ¦ 3495 ¦ 5403 ¦ 1597 ¦ 2200 ¦ 3797 ¦ 1606 ¦ Supply Under progress(1008KM) | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Earthing S-F | 15 | 11 | earthing_tack | R5: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Type of Earthing ¦ Start ¦ Complete ¦ Before Earthing Value ¦ After Earthing Value ¦ Remarks | KEC International Limited 400 KV D/C (Quad) Siwani-Fatehabad TL Details of Earthing TFR CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Type of Earthing ¦ Start ¦ Complete ¦ Before Earthing Value ¦ After Earthing Value ¦ Remarks 1 ¦ 1 ¦ 24/2 ¦ DA+0 ¦ WET ¦ Pipe Type ¦ 2025-08-05 00:00:00 ¦ 2025-08-05 00:00:00 ¦ 1.56 ¦ 1.39 2 ¦ 2 ¦ 24/3 ¦ DA+0 ¦ Sandy ¦ Pipe Type ¦ 2025-08-04 00:00:00 ¦ 2025-08-04 00:00:00 ¦ 2.73 ¦ 2.4 3 ¦ 3 ¦ 24/4 ¦ DA+1.5 ¦ Sandy ¦ Pipe Type ¦ 2025-08-05 00:00:00 ¦ 2025-08-05 00:00:00 ¦ 0.94 ¦ 0.85 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | ROW S-F | 72 | 15 | foundation, row_hindrance, summary_status | R3: S.No ¦ Loc. No. ¦ Tower/Type ¦ Activity ¦ Date of Approach ¦ Date of Resolution ¦ Duration of ROW (Days) ¦ Nature of hindrance ¦ Status of Resolution ¦ Name of Farmer ¦ Father Name ¦ Mobile no. ¦ Vill. Name ¦ Tehsil R4: 1 ¦ 19/1 ¦ DA+3 ¦ Foundation ¦ 2025-04-27 00:00:00 ¦ 389 ¦ Demanding Compensation before work & (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh Ramkumar ¦ Sh. Tularam ¦ 9416927655/8199991624 ¦ Mattrasham ¦ Hisar ¦ 1 R5: 2 ¦ 19/2 ¦ DA-3 ¦ Foundation ¦ 2025-04-27 00:00:00 ¦ 389 ¦ Demanding Compensation before work & (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh.Amardeep ¦ Sh. Omprakash ¦ 7206313374/9466052316 ¦ Mattrasham ¦ Hisar ¦ 1 R6: 3 ¦ 21/1 ¦ DA+0 ¦ Foundation ¦ 2025-04-27 00:00:00 ¦ 2025-07-01 00:00:00 ¦ 389 ¦ Demanding Compensation before work & (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh.Bhup Singh Nain ¦ 9467874974 ¦ Mattrasham ¦ Hisar ¦ 1 R7: 4 ¦ 21/2 ¦ DA-3 ¦ Foundation ¦ 2025-04-27 00:00:00 ¦ 389 ¦ Demanding Compensation before work & (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh.Sube Singh Nain(Pappu) ¦ 9416123004 ¦ Mattrasham ¦ Hisar ¦ 1 | ROW Status(Siwani-Fatehabad TL) ¦ 2026-05-20 00:00:00 S.No ¦ Loc. No. ¦ Tower/Type ¦ Activity ¦ Date of Approach ¦ Date of Resolution ¦ Duration of ROW (Days) ¦ Nature of hindrance ¦ Status of Resolution ¦ Name of Farmer ¦ Father Name ¦ Mobile no. ¦ Vill. Name ¦ Tehsil 1 ¦ 19/1 ¦ DA+3 ¦ Foundation ¦ 2025-04-27 00:00:00 ¦ 389 ¦ Demanding Compensation before work & (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh Ramkumar ¦ Sh. Tularam ¦ 9416927655/8199991624 ¦ Mattrasham ¦ Hisar ¦ 1 2 ¦ 19/2 ¦ DA-3 ¦ Foundation ¦ 2025-04-27 00:00:00 ¦ 389 ¦ Demanding Compensation before work & (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh.Amardeep ¦ Sh. Omprakash ¦ 7206313374/9466052316 ¦ Mattrasham ¦ Hisar ¦ 1 3 ¦ 21/1 ¦ DA+0 ¦ Foundation ¦ 2025-04-27 00:00:00 ¦ 2025-07-01 00:00:00 ¦ 389 ¦ Demanding Compensation before work & (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh.Bhup Singh Nain ¦ 9467874974 ¦ Mattrasham ¦ Hisar ¦ 1 4 ¦ 21/2 ¦ DA-3 ¦ Foundation ¦ 2025-04-27 00:00:00 ¦ 389 ¦ Demanding Compensation before work & (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh.Sube Singh Nain(Pappu) ¦ 9416123004 ¦ Mattrasham ¦ Hisar ¦ 1 5 ¦ 21/3 ¦ DA-3 ¦ Foundation ¦ 2025-04-27 00:00:00 ¦ 389 ¦ Demanding Compensation before work & (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh.Rajbir Singh Nain ¦ 7015457214 ¦ Mattrasham ¦ Hisar ¦ 1 6 ¦ 23/2 ¦ DA+3 ¦ Foundation ¦ 2025-04-04 00:00:00 ¦ 412 ¦ Demanding Compensation before work & (MRC is not fixed by PGCIL) ¦ Pending ¦ Suresh mund ¦ Ramchandra ¦ 9812365010 ¦ Neoli Khurd ¦ Adampur ¦ 1 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Proposal | 168 | 52 | statutory_crossing, summary_status | R5: Sl.No ¦ Crossing ¦ Line ¦ Total Nos ¦ Proposal Submitted ¦ Balance Submission' ¦ Remarks R7: Siwani-Fatehabad ¦ 4 ¦ 4 ¦ Description ¦ Crossing ¦ Authority ¦ Description ¦ Total Crossing R8: 2 ¦ NH ¦ Siwani-Patran ¦ 5 ¦ 4 ¦ 1 ¦ SF ¦ SP ¦ SF ¦ SP R26: Sl.No ¦ Line Name ¦ Type of crossing ¦ Description of Crossing ¦ Crossing Authority ¦ Status R28: 1 ¦ Siwani-Patran ¦ PL Xing ¦ 2B ¦ DD45 ¦ 2C ¦ DD45 ¦ 132KV ¦ S/C ¦ 132 KV S/C HISAR-RAJGARH TL ¦ HVPNL ¦ Detailed Survey Approval Pending | Client : PowerGrid Bikaner IV Transmission Limited. KEC International Limited Name of Line: 400 KV D/C Siwani To Fatehabad + 400 KV D/C Siwani To Patran TL Summary of crossing Details Sl.No ¦ Crossing ¦ Line ¦ Total Nos ¦ Proposal Submitted ¦ Balance Submission' ¦ Remarks 1 ¦ PL ¦ Siwani-Patran ¦ 22 ¦ 21 ¦ 1 ¦ Resubmission AP53-AP54,AP75-AP76,AP82-AP83,AP88-AP89,AP91-AP92 ON 4.12.2025 Siwani-Fatehabad ¦ 4 ¦ 4 ¦ Description ¦ Crossing ¦ Authority ¦ Description ¦ Total Crossing 2 ¦ NH ¦ Siwani-Patran ¦ 5 ¦ 4 ¦ 1 ¦ SF ¦ SP ¦ SF ¦ SP | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Proposal . | 165 | 51 | statutory_crossing, summary_status | R5: Sl.No ¦ Crossing ¦ Line ¦ Total Nos ¦ Proposal Submitted ¦ Balance Submission' ¦ NOC Received ¦ Remarks R7: Siwani-Fatehabad ¦ 4 ¦ 4 ¦ 3 ¦ Description ¦ Total Crossing R8: 2 ¦ NH ¦ Siwani-Patran ¦ 5 ¦ 5 ¦ 3 ¦ Description ¦ Crossing ¦ Authority ¦ SF ¦ SP ¦ Total R20: 8 ¦ Civil Aviation ¦ Siwani-Patran ¦ 1 ¦ 1 ¦ Online Portal uploading Under progress R21: Siwani-Fatehabad ¦ 1 ¦ 1 ¦ Online Portal uploading Under progress | Client : PowerGrid Bikaner IV Transmission Limited. KEC International Limited Name of Line: 400 KV D/C Siwani To Fatehabad + 400 KV D/C Siwani To Patran TL Summary of crossing Details Sl.No ¦ Crossing ¦ Line ¦ Total Nos ¦ Proposal Submitted ¦ Balance Submission' ¦ NOC Received ¦ Remarks 1 ¦ PL ¦ Siwani-Patran ¦ 22 ¦ 22 ¦ 15 Siwani-Fatehabad ¦ 4 ¦ 4 ¦ 3 ¦ Description ¦ Total Crossing 2 ¦ NH ¦ Siwani-Patran ¦ 5 ¦ 5 ¦ 3 ¦ Description ¦ Crossing ¦ Authority ¦ SF ¦ SP ¦ Total | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | ROW S-P | 123 | 14 | foundation, row_hindrance, summary_status | R2: S.No ¦ Loc. No. ¦ Tower/Type ¦ Activity ¦ Date of 1st Approach ¦ Date of Resolution ¦ Duration of ROW (Days) ¦ Nature of hindrance ¦ Status of Resolution ¦ Name of Farmer ¦ Father Name ¦ Mobile no. ¦ Vill. Name ¦ Tehsil R3: 1 ¦ 30/4 ¦ DA+3 ¦ Foundation ¦ 2025-04-18 00:00:00 ¦ -45764 ¦ Demanding Tower Shifting & Before Compensation ¦ Pending ¦ Sh.Janakraj ¦ Sh. Mulchand ¦ 9255500551/8168456965 ¦ Durjanpur ¦ Hisar R4: 2 ¦ 30/5 ¦ DA+0 ¦ Foundation ¦ 2025-04-15 00:00:00 ¦ -45761 ¦ Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh.Suresh / Sh.Mela Ram ¦ Sh.Kisanlal/Sh.Nandram ¦ 8307632460/9812843445 ¦ Chikanwas ¦ Hisar R5: 3 ¦ 30/6 ¦ DA+3 ¦ Foundation ¦ 2025-04-16 00:00:00 ¦ -45762 ¦ Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh. Amit Kumar ¦ 9992828789 ¦ Durjanpur ¦ Hisar R6: 4 ¦ 30/7 ¦ DA+3 ¦ Foundation ¦ 2025-04-25 00:00:00 ¦ -45771 ¦ Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh.Kuldeep Beniwal ¦ Sh.Jaibeer Singh ¦ 9416251922 ¦ Chikanwas ¦ Hisar | ROW Status (Siwani-Patran TL) ¦ 00:00:00 S.No ¦ Loc. No. ¦ Tower/Type ¦ Activity ¦ Date of 1st Approach ¦ Date of Resolution ¦ Duration of ROW (Days) ¦ Nature of hindrance ¦ Status of Resolution ¦ Name of Farmer ¦ Father Name ¦ Mobile no. ¦ Vill. Name ¦ Tehsil 1 ¦ 30/4 ¦ DA+3 ¦ Foundation ¦ 2025-04-18 00:00:00 ¦ -45764 ¦ Demanding Tower Shifting & Before Compensation ¦ Pending ¦ Sh.Janakraj ¦ Sh. Mulchand ¦ 9255500551/8168456965 ¦ Durjanpur ¦ Hisar 2 ¦ 30/5 ¦ DA+0 ¦ Foundation ¦ 2025-04-15 00:00:00 ¦ -45761 ¦ Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh.Suresh / Sh.Mela Ram ¦ Sh.Kisanlal/Sh.Nandram ¦ 8307632460/9812843445 ¦ Chikanwas ¦ Hisar 3 ¦ 30/6 ¦ DA+3 ¦ Foundation ¦ 2025-04-16 00:00:00 ¦ -45762 ¦ Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh. Amit Kumar ¦ 9992828789 ¦ Durjanpur ¦ Hisar 4 ¦ 30/7 ¦ DA+3 ¦ Foundation ¦ 2025-04-25 00:00:00 ¦ -45771 ¦ Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) ¦ Pending ¦ Sh.Kuldeep Beniwal ¦ Sh.Jaibeer Singh ¦ 9416251922 ¦ Chikanwas ¦ Hisar 5 ¦ 31/1 ¦ DA+0 ¦ Foundation ¦ 2025-05-03 00:00:00 ¦ -45779 ¦ Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) ¦ Pending ¦ Kashabil Das ¦ Sh.Ram Karan ¦ 9992718781 ¦ Chikanwas ¦ Hisar 6 ¦ 31/2 ¦ DA+3 ¦ Foundation ¦ 2025-05-03 00:00:00 ¦ -45779 ¦ Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) ¦ Pending ¦ Mahavir(Vinod Son) ¦ Sh.Bagdawat ¦ 9992915495 ¦ Chikanwas ¦ Hisar | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Master SP | 404 | 17 | earthing_tack, erection, foundation, row_hindrance, statutory_crossing, survey_soil, visual_l2 | R3: S. No. ¦ Location ¦ Type of ¦ Approved survey ¦ Wind Zone ¦ Span ¦ District ¦ Tehsil ¦ Village ¦ PL ¦ NH ¦ RL ¦ Land Schedule ¦ Location Sketch ¦ Foundation compl ¦ Earthing Complete ¦ Erection Compl R4: Tower No. ¦ Tower ¦ Foundation ¦ Foundation | 396 LS Approved Over all Tower Location details (Siwani-Patran TL) ¦ 41 ¦ 10 ¦ 8 ¦ 396 ¦ 371 ¦ 49 ¦ 8 ¦ 21 S. No. ¦ Location ¦ Type of ¦ Approved survey ¦ Wind Zone ¦ Span ¦ District ¦ Tehsil ¦ Village ¦ PL ¦ NH ¦ RL ¦ Land Schedule ¦ Location Sketch ¦ Foundation compl ¦ Earthing Complete ¦ Erection Compl Tower No. ¦ Tower ¦ Foundation ¦ Foundation 1 ¦ 1/0 ¦ DD60+0 ¦ Approved ¦ 4 ¦ 100.36 ¦ Bhiwani ¦ Siwani ¦ Jhuppa Kalan ¦ 1 2 ¦ 1A/0 ¦ DD60+25 ¦ Approved ¦ 4 ¦ 268.44 ¦ Bhiwani ¦ Siwani ¦ Jhuppa Kalan ¦ 1 3 ¦ 1B/0 ¦ DD60+25 ¦ Approved ¦ 4 ¦ 161.36 ¦ Bhiwani ¦ Siwani ¦ Jhuppa Kalan ¦ 1 4 ¦ 1B/1 ¦ DA+9 ¦ Approved ¦ 4 ¦ 400 ¦ Bhiwani ¦ Siwani ¦ Jhuppa Kalan ¦ 1 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Master SF | 231 | 17 | earthing_tack, erection, foundation, row_hindrance, statutory_crossing, survey_soil, visual_l2 | R3: S. No. ¦ Location ¦ Type of ¦ Approved survey ¦ Wind Zone ¦ Span ¦ District ¦ Tehsil ¦ Village ¦ PL ¦ NH ¦ RL ¦ Land Schedule ¦ Location Sketch ¦ Foundation compl ¦ Earthing Complete ¦ Erection compl R4: Tower No. ¦ Tower ¦ Foundation ¦ Foundation | 220 LS Approved Over all Tower Location details (Siwani-Fatehabad TL) ¦ 8 ¦ 6 ¦ 4 ¦ 220 ¦ 199 ¦ 23 ¦ 10 ¦ 7 S. No. ¦ Location ¦ Type of ¦ Approved survey ¦ Wind Zone ¦ Span ¦ District ¦ Tehsil ¦ Village ¦ PL ¦ NH ¦ RL ¦ Land Schedule ¦ Location Sketch ¦ Foundation compl ¦ Earthing Complete ¦ Erection compl Tower No. ¦ Tower ¦ Foundation ¦ Foundation 1 ¦ 1/0 ¦ DD60+0 ¦ Approved ¦ 4 ¦ 151.994 ¦ Bhiwani ¦ Siwani ¦ Jhuppa Kalan ¦ 1 2 ¦ 1/1 ¦ DA+6 ¦ Approved ¦ 4 ¦ 410 ¦ Bhiwani ¦ Siwani ¦ Jhuppa Kalan ¦ 1 3 ¦ 1A/0 ¦ DD60+0 ¦ Approved ¦ 4 ¦ 429.494 ¦ Bhiwani ¦ Siwani ¦ Jhuppa Kalan ¦ 1 ¦ 1 4 ¦ 1B/0 ¦ DD60+6 ¦ Approved ¦ 4 ¦ 228.257 ¦ Bhiwani ¦ Siwani ¦ Jhuppa Kalan ¦ 1 ¦ 1 ¦ 1 | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | TS SP | 813 | 34 | statutory_crossing, visual_l2 | R6: Sl.No ¦ AP NO. ¦ TOWER NO. ¦ TYPE OF TOWER ¦ HT of Tower (Mtr) ¦ SPAN (Mtr) ¦ CUMULATIVE SPAN ¦ R.L (Mtr) ¦ DEVIATION ANGLE (Deg) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) ¦ UTM Coordinates ¦ CROSSING DETAILS ¦ NAME OF VILLAGE ¦ NAME OF TEHSIL ¦ NAME OF POLICE STATION | KEC INTERNATIONAL LIMITED Transmission Line Package TL03 for (a) Siwani– Fatehabad (PG) 400kV D/c line (Quad); (b) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) associated with “Transmission System for evacuation of power from Rajasthan REZ Ph-IV (Part 3: 6 GW) (Bikaner Complex) : Part A” through Tariff Based Competitive Bidding Package TL03 for (b)400 KV DC Quad Siwani to Patran Transmission Line TOWER SCHEDULE - S.Gantry to PATRAN GANTRY WZ-4 & WZ-5 Client :POWERGRID BIKANER IV TRANSMISSION LIMITED (A 100% WHOLLY OWNED SUBSIDIARY OF POWER GRID) ¦ DT :30.07.2020 Sl.No ¦ AP NO. ¦ TOWER NO. ¦ TYPE OF TOWER ¦ HT of Tower (Mtr) ¦ SPAN (Mtr) ¦ CUMULATIVE SPAN ¦ R.L (Mtr) ¦ DEVIATION ANGLE (Deg) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) ¦ UTM Coordinates ¦ CROSSING DETAILS ¦ NAME OF VILLAGE ¦ NAME OF TEHSIL ¦ NAME OF POLICE STATION Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Easting (m) ¦ Northing (m) 1 ¦ Shiwani Gantry ¦ Gantry ¦ 22.8 ¦ 215.65 ¦ 100.363 ¦ 50.1815 ¦ 16 ¦ 16 ¦ 18 ¦ 18 ¦ 75d33'0.794"E ¦ 28d47'34.369"N ¦ 553698.378 ¦ 3185163.056 ¦ Jhumpa kalan | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | TS SF | 496 | 36 | visual_l2 | R6: Sl.No ¦ AP NO. ¦ TOWER NO. ¦ TYPE OF TOWER ¦ HT of Tower (Mtr) ¦ SPAN (Mtr) ¦ SECTION LENGTH (Mtr) ¦ CUMULATIVE SPAN ¦ LEG EXTENSION ¦ RAISED CHIMNEY ¦ BENCHING VOLUME (Cum) ¦ REVETMENT VOLUME (Cum) ¦ R.L (Mtr) ¦ DEVIATION ANGLE (Deg) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) | KEC INTERNATIONAL LIMITED Transmission Line Package TL03 for (a) Siwani– Fatehabad (PG) 400kV D/c line (Quad); (b) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) associated with “Transmission System for evacuation of power from Rajasthan REZ Ph-IV (Part 3: 6 GW) (Bikaner Complex) : Part A” through Tariff Based Competitive Bidding Package TL03 for (a) Siwani– Fatehabad (PG) 400kV D/C Transmission Line TOWER SCHEDULE - SIWANI GANTRY to FATEHABAD GANTRY (WZ-4 & WZ-5) Client : POWERGRID BIKANER IV TRANSMISSION LIMITED (A 100% WHOLLY OWNED SUBSIDIARY OF POWER GRID) ¦ DT. Sl.No ¦ AP NO. ¦ TOWER NO. ¦ TYPE OF TOWER ¦ HT of Tower (Mtr) ¦ SPAN (Mtr) ¦ SECTION LENGTH (Mtr) ¦ CUMULATIVE SPAN ¦ LEG EXTENSION ¦ RAISED CHIMNEY ¦ BENCHING VOLUME (Cum) ¦ REVETMENT VOLUME (Cum) ¦ R.L (Mtr) ¦ DEVIATION ANGLE (Deg) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) A ¦ B ¦ C ¦ D ¦ Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Easting (m) ¦ Y Northing (m) 1 ¦ Shiwani Gantry ¦ S/S GANTRY ¦ 29.9 ¦ 215.049 ¦ 151.994 ¦ 75.997 ¦ 42 ¦ 42 ¦ 45 ¦ 45 ¦ 75º 32' 54.538" E ¦ 28º 47' 32.703" N ¦ 553529.005 ¦ 3185111.006 ¦ Jhumpa Kalan ¦ No count | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Sheet4 | 1 | 1 |  |  |  | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Sheet2 | 35 | 1 |  |  |  | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Sheet1 | 12 | 14 | commercial | R12: Service bill ¦ 28mm steel ¦ 32mm | Section ¦ Name of Line ¦ Section Incharge ¦ Minimum Target for June AP 3 - AP 7 ¦ S-F ¦ Rakesh Kumar & Naval Singh ¦ 3 AP 12 - AP 19 ¦ S-P ¦ Rakesh Kumar & Naval Singh ¦ 7 AP 19 - AP 50 ¦ S-P ¦ Naveen Ray ¦ 15 AP 18 - AP 40 ¦ S-F ¦ Lavkush Pachauri ¦ 5 AP 57 - AP 50 ¦ S-P ¦ Bharat Jadon ¦ 5 Total ¦ 35 Service bill ¦ 28mm steel ¦ 32mm | ok
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | 2026-05-19 | Forest | 43 | 12 | row_hindrance, statutory_crossing | R3: Sl.No ¦ Activity ¦ Line ¦ Total Nos ¦ Proposal Submitted ¦ Approval/NOC Obtained ¦ Remarks R4: 1 ¦ POWERLINE CROSSINGS ¦ Siwani-Fatehabad TL ¦ 4 R6: 2 ¦ NATIONAL HIGHWAY CROSSINGS ¦ Siwani-Fatehabad TL ¦ 3 R8: 3 ¦ RAILWAY CROSSING ¦ Siwani-Fatehabad TL ¦ 2 R12: 4 ¦ FOREST CLEARANCE ¦ Siwani-Fatehabad TL ¦ 8.312 | Sl.No ¦ Activity ¦ Line ¦ Total Nos ¦ Proposal Submitted ¦ Approval/NOC Obtained ¦ Remarks 1 ¦ POWERLINE CROSSINGS ¦ Siwani-Fatehabad TL ¦ 4 Siwani-Patran TL ¦ 21 2 ¦ NATIONAL HIGHWAY CROSSINGS ¦ Siwani-Fatehabad TL ¦ 3 Siwani-Patran TL ¦ 3 3 ¦ RAILWAY CROSSING ¦ Siwani-Fatehabad TL ¦ 2 Siwani-Patran TL ¦ 4 4 ¦ OIL Pipeline ¦ Siwani-Fatehabad TL | ok
TA 515 | TA 515 - DPR - 2026-05-11.xlsx | 2026-05-11 | DPR | 22 | 14 | foundation, row_hindrance, summary_status, survey_soil, visual_l2 | R4: Sl. ¦ Description ¦ L2 / Actual ¦ UOM ¦ Total Qty ¦ Progress upto Apr'26 ¦ Todays Progress ¦ Progress for current month (May'26) ¦ Total Cum. progress since inception ¦ Remarks R6: 1 ¦ Route Alignment ¦ L2 (Plan) ¦ KM ¦ 83.14 ¦ 83.14 ¦ - ¦ - ¦ 83.14 ¦ Route Alignment approved (100%) R8: 2 ¦ Detailed Survey ¦ L2 (Plan) ¦ KM ¦ 83.14 ¦ 83.14 ¦ - ¦ - ¦ 83.14 ¦ Detail survey completed. Profile submitted & approval received of 83.331 KM (100%) R10: 3 ¦ Check Survey ¦ L2 (Plan) ¦ KM ¦ 83.14 ¦ 83.14 ¦ - ¦ - ¦ 83.14 ¦ Check survey done. Report submitted & approval received for 83.331 km (100%). Land Schedule & Tree enumeration report submitted (100%) R12: 4 ¦ Soil Investigation ¦ L2 (Plan) ¦ Nos ¦ 17 ¦ 17 ¦ - ¦ - ¦ 17 ¦ Activity completed - 12 nos (100%), Report submitted - 12 nos (100%) | 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) ¦ 2026-05-11 00:00:00 Daily Progress Report Sl. ¦ Description ¦ L2 / Actual ¦ UOM ¦ Total Qty ¦ Progress upto Apr'26 ¦ Todays Progress ¦ Progress for current month (May'26) ¦ Total Cum. progress since inception ¦ Remarks 1 ¦ Route Alignment ¦ L2 (Plan) ¦ KM ¦ 83.14 ¦ 83.14 ¦ - ¦ - ¦ 83.14 ¦ Route Alignment approved (100%) Actual ¦ 83.331 ¦ 83.331 ¦ - ¦ - ¦ 83.331 2 ¦ Detailed Survey ¦ L2 (Plan) ¦ KM ¦ 83.14 ¦ 83.14 ¦ - ¦ - ¦ 83.14 ¦ Detail survey completed. Profile submitted & approval received of 83.331 KM (100%) Actual ¦ 83.331 ¦ 83.331 ¦ - ¦ - ¦ 83.331 3 ¦ Check Survey ¦ L2 (Plan) ¦ KM ¦ 83.14 ¦ 83.14 ¦ - ¦ - ¦ 83.14 ¦ Check survey done. Report submitted & approval received for 83.331 km (100%). Land Schedule & Tree enumeration report submitted (100%) | ok
TA 515 | TA 515 - DPR - 2026-05-11.xlsx | 2026-05-11 | Store Stock | 18 | 8 | earthing_tack, supply | R4: Sl. ¦ Description ¦ UOM ¦ Received ¦ Consumed ¦ Balance in stock ¦ Remarks R5: 1 ¦ Counterpoise Earthing ¦ Nos ¦ 114 ¦ 8 ¦ 106 R6: 2 ¦ Rod Type Earthing ¦ Nos ¦ 36 ¦ 1 ¦ 35 R7: 3 ¦ Pipe Type Earthing ¦ Nos ¦ 36 ¦ 1 ¦ 35 R9: 4 ¦ "A" Type Stub WZ-5NC ¦ Set ¦ 112 ¦ 9 ¦ 103 | 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) ¦ 2026-05-11 00:00:00 Stores Stock Balance Sl. ¦ Description ¦ UOM ¦ Received ¦ Consumed ¦ Balance in stock ¦ Remarks 1 ¦ Counterpoise Earthing ¦ Nos ¦ 114 ¦ 8 ¦ 106 2 ¦ Rod Type Earthing ¦ Nos ¦ 36 ¦ 1 ¦ 35 3 ¦ Pipe Type Earthing ¦ Nos ¦ 36 ¦ 1 ¦ 35 STUB 4 ¦ "A" Type Stub WZ-5NC ¦ Set ¦ 112 ¦ 9 ¦ 103 | ok
TA 515 | TA 515 - DPR - 2026-05-11.xlsx | 2026-05-11 | Visual chart | 201 | 59 | earthing_tack, erection, foundation, statutory_crossing, summary_status, survey_soil, visual_l2 | R6: PROGRESS AT A GLANCE : ¦ CROSSING PROPOSAL STATUS : ¦ LEGEND: R7: Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ Sl. No. ¦ Type of Crossing ¦ No. of X-ing ¦ Apprd ¦ Balance R9: 1 ¦ Detailed Survey ¦ Kms ¦ 83.33094 ¦ 83.33094 ¦ 1 ¦ Powerline ¦ 17 ¦ 11 ¦ 6 R10: 2 ¦ Check Survey ¦ Kms ¦ 83.33094 ¦ 83.33094 ¦ a. ¦ 66 kV ¦ 9 ¦ 8 ¦ 1 R11: 3 ¦ Soil Investigation ¦ Nos. ¦ 12 ¦ 12 ¦ b. ¦ 132 kV ¦ - | Visual Chart Project : ¦ ±800kV HVDC BIPOLE LINE (HEX LAPWING) BETWEEN KPS2 (HVDC) & NAGPUR (HVDC) (WITH DMR), TRANSMISSION LINE PACKAGE- 03 Client: ¦ M/s POWERGRID WEST CENTRAL TRANSMISSION LIMITED Executive Agency: ¦ KEC INTERNATIONAL LIMITED PROGRESS AT A GLANCE : ¦ CROSSING PROPOSAL STATUS : ¦ LEGEND: Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ Sl. No. ¦ Type of Crossing ¦ No. of X-ing ¦ Apprd ¦ Balance 1 ¦ Detailed Survey ¦ Kms ¦ 83.33094 ¦ 83.33094 ¦ 1 ¦ Powerline ¦ 17 ¦ 11 ¦ 6 2 ¦ Check Survey ¦ Kms ¦ 83.33094 ¦ 83.33094 ¦ a. ¦ 66 kV ¦ 9 ¦ 8 ¦ 1 | ok
TA 515 | TA 515 - DPR - 2026-05-11.xlsx | 2026-05-11 | Erection Compiled | 62 | 14 | erection, project_details, row_hindrance, summary_status | R2: Sl ¦ Location No. ¦ Type ¦ Type of Tower ¦ Starting Date ¦ Revenue (Lac.) ¦ Tower Weight (MT) ¦ Status ¦ Completion Date ¦ Gang Name ¦ No. ¦ District ¦ Remarks ¦ Ageing R3: 1 ¦ 232/3 ¦ A ¦ A+0 ¦ 2026-02-27 00:00:00 ¦ 5.461134159999999 ¦ 30.826 ¦ Completed ¦ 2026-03-08 00:00:00 ¦ Rupesh Kumar ¦ Surendranagar ¦ 9 R4: 2 ¦ 232/4 ¦ A ¦ A+0 ¦ 5.461134159999999 ¦ 30.826 ¦ Surendranagar ¦ Shutdown Needed+ROW R6: 4 ¦ 217/6 ¦ A ¦ A+0 ¦ 5.461134159999999 ¦ 30.826 ¦ Surendranagar ¦ Compensation not received to Land Owner R8: 6 ¦ 198/1 ¦ A ¦ A+0 ¦ 5.461134159999999 ¦ 30.826 ¦ Surendranagar ¦ Private land + Crop Damage | Tower Erection Sl ¦ Location No. ¦ Type ¦ Type of Tower ¦ Starting Date ¦ Revenue (Lac.) ¦ Tower Weight (MT) ¦ Status ¦ Completion Date ¦ Gang Name ¦ No. ¦ District ¦ Remarks ¦ Ageing 1 ¦ 232/3 ¦ A ¦ A+0 ¦ 2026-02-27 00:00:00 ¦ 5.461134159999999 ¦ 30.826 ¦ Completed ¦ 2026-03-08 00:00:00 ¦ Rupesh Kumar ¦ Surendranagar ¦ 9 2 ¦ 232/4 ¦ A ¦ A+0 ¦ 5.461134159999999 ¦ 30.826 ¦ Surendranagar ¦ Shutdown Needed+ROW 3 ¦ 217/5 ¦ A ¦ A+3 ¦ 5.87303116 ¦ 33.151 ¦ Surendranagar ¦ We do not have tower part of A+3 4 ¦ 217/6 ¦ A ¦ A+0 ¦ 5.461134159999999 ¦ 30.826 ¦ Surendranagar ¦ Compensation not received to Land Owner 5 ¦ 205/1 ¦ A ¦ A+3 ¦ 5.87303116 ¦ 33.151 ¦ Surendranagar ¦ We do not have tower part of A+3 / Shutdown Needed 6 ¦ 198/1 ¦ A ¦ A+0 ¦ 5.461134159999999 ¦ 30.826 ¦ Surendranagar ¦ Private land + Crop Damage | ok
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | 2026-05-20 | Visual Chart | 1000 | 32 | earthing_tack, erection, foundation, project_details, statutory_crossing, stringing, summary_status, visual_l2 | R3: Foundation (Nos.):- ¦ / 297 ¦ Erection (Nos.):- ¦ / 297 ¦ Earthing (Nos.):- ¦ / 297 ¦ Rough Sag (Kms):- ¦ 113.292 ¦ Final Sag (Kms):- ¦ 113.292 ¦ Date:- ¦ 46162 R4: COMPLETION CHART ¦ -3 ¦ +0 ¦ +3 ¦ +6 ¦ +9 ¦ Total ¦ Line Qty R5: ERECTION ¦ Rough Sag ¦ SH / NH Road Crossing R13: DD45 ¦ Section Tower ¦ SC ¦ Crossing ¦ 110-800 KV R14: DD60 ¦ TP ¦ TT ¦ Earthing ¦ OPGW ¦ Line | VISUAL PROGRESS CHART TL-02 765 KV D/C Kurnool IV - Bidar Transmission Line Foundation (Nos.):- ¦ / 297 ¦ Erection (Nos.):- ¦ / 297 ¦ Earthing (Nos.):- ¦ / 297 ¦ Rough Sag (Kms):- ¦ 113.292 ¦ Final Sag (Kms):- ¦ 113.292 ¦ Date:- ¦ 46162 COMPLETION CHART ¦ -3 ¦ +0 ¦ +3 ¦ +6 ¦ +9 ¦ Total ¦ Line Qty ERECTION ¦ Rough Sag ¦ SH / NH Road Crossing WIP ¦ River DA ¦ Type ¦ Angle Tower ¦ Gas Pipeline DB1 ¦ FOUNDATION | ok
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | 2026-05-20 | Master Sheet | 999 | 24 | earthing_tack, foundation, project_details, summary_status, survey_soil, visual_l2 | R3: Project Name ¦ 765kV D/C Kurnool IV - Bidar trnasmission line (Part II) ¦ LOA Start Date ¦ 13.05.2025 ¦ PCH ¦ Mr. Arun Felbin R R4: Client Name ¦ POWERGRID KURNOOL IV TRANSMISSION LIMITED ¦ LOA End Date ¦ 12.04.2027 ¦ Regional Manager ¦ Mr. Ajith Kumar MG R9: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Plan for Current Month ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Approved till Current Month ¦ Remarks R10: Detailed Survey ¦ kms ¦ 113.286 ¦ 113.286 ¦ 113.286 ¦ 113.286 ¦ 113.286 R11: Check Survey ¦ kms ¦ 113.286 ¦ 113.286 ¦ 113.286 ¦ 113.266 ¦ 0.398 ¦ 0.4 ¦ 112.266 | Project Code ¦ TA-601 ¦ Date as on ¦ 2026-05-20 00:00:00 ¦ SBU Head ¦ Mr. Rajinder Gupta Project Name ¦ 765kV D/C Kurnool IV - Bidar trnasmission line (Part II) ¦ LOA Start Date ¦ 13.05.2025 ¦ PCH ¦ Mr. Arun Felbin R Client Name ¦ POWERGRID KURNOOL IV TRANSMISSION LIMITED ¦ LOA End Date ¦ 12.04.2027 ¦ Regional Manager ¦ Mr. Ajith Kumar MG Duration ¦ 23 Months ¦ Planning Engineer ¦ Mr. Appala Swamy ¦ Chief Manger ¦ Mr. Senthil Jayaraman Survey Status Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Plan for Current Month ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Approved till Current Month ¦ Remarks Detailed Survey ¦ kms ¦ 113.286 ¦ 113.286 ¦ 113.286 ¦ 113.286 ¦ 113.286 Check Survey ¦ kms ¦ 113.286 ¦ 113.286 ¦ 113.286 ¦ 113.266 ¦ 0.398 ¦ 0.4 ¦ 112.266 | ok
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | 2026-05-20 | Progress Sheet | 1201 | 108 | erection, foundation, row_hindrance, summary_status, survey_soil, visual_l2 | R3: Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks R4: Detailed Survey ¦ kms ¦ 113.286 ¦ 113.286 ¦ 113.286 ¦ 113.286 ¦ 113.286 R5: Check Survey ¦ kms ¦ 113.286 ¦ 113.286 ¦ 113.286 ¦ 113.266 ¦ 0.4 ¦ 20 ¦ 0.398 ¦ 112.266 R8: S.No ¦ Section ¦ Length ¦ Check survey status R12: S.No ¦ Location No. ¦ Tower Type ¦ Classification ¦ ROW cleared date ¦ Start Date ¦ Conc Volume ¦ Foundation Status ¦ End Date ¦ Gang Name ¦ Erection Status ¦ Gang Strength ¦ Remarks | Survey Status Activity ¦ Unit ¦ Final Est. Qty ¦ L2 till Last Month ¦ Completed till Last Month ¦ Approved till Last Month ¦ Balance to Submit ¦ Balance to Approve ¦ L2 Submission Plan for Current Month ¦ Progress For Month ¦ Approved till Current Month ¦ Remarks Detailed Survey ¦ kms ¦ 113.286 ¦ 113.286 ¦ 113.286 ¦ 113.286 ¦ 113.286 Check Survey ¦ kms ¦ 113.286 ¦ 113.286 ¦ 113.286 ¦ 113.266 ¦ 0.4 ¦ 20 ¦ 0.398 ¦ 112.266 PROGRESS - Check Survey S.No ¦ Section ¦ Length ¦ Check survey status 120 PROGRESS - FDN & EREC | ok
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | 2026-05-20 | ROW | 1006 | 4 | foundation, row_hindrance |  | TL-02 765kV Kurnool IV - Bidar line Foundation Sr. No. ¦ Location no. ¦ Type of tower ¦ ISSUE 1 ¦ 50/0 ¦ DC2+0 2 ¦ 51/1 ¦ DA+3 3 ¦ 51/0 ¦ DC2+0 4 ¦ 51/5 ¦ DA+0 5 ¦ 52/2 ¦ DA+0 | ok
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | 2026-05-20 | SUPPLY | 1001 | 26 | summary_status, supply | R3: SL No ¦ Description ¦ Unit ¦ Line Qty ¦ Received ¦ Balance R4: 1 ¦ 3DA Stub ¦ Set ¦ 181 R5: 2 ¦ 3DB Stub ¦ Set ¦ 27 R6: 3 ¦ 3DC Stub ¦ Set ¦ 17 R7: 4 ¦ 3D45 Stub ¦ Set ¦ 6 | Supply Status - Stubs & Towers Stub Details SL No ¦ Description ¦ Unit ¦ Line Qty ¦ Received ¦ Balance 1 ¦ 3DA Stub ¦ Set ¦ 181 2 ¦ 3DB Stub ¦ Set ¦ 27 3 ¦ 3DC Stub ¦ Set ¦ 17 4 ¦ 3D45 Stub ¦ Set ¦ 6 5 ¦ 3D60 Stub ¦ Set ¦ 4 | ok
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection Compiled | 73 | 20 | erection, summary_status | R2: SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Start Date ¦ MT ¦ Status ¦ End Date ¦ Gang Name ¦ Gang Strength R3: 1 ¦ 56/7 ¦ DA+0 ¦ DFR ¦ 2025-12-15 00:00:00 ¦ 35.089 ¦ Erection Completed. ¦ 2025-12-20 00:00:00 ¦ NASIRUDDIN ¦ 35 R4: 2 ¦ 59/2 ¦ DA+0 ¦ DRY ¦ 2025-12-22 00:00:00 ¦ 35.089 ¦ Erection Completed. ¦ 2025-12-27 00:00:00 ¦ NASIRUDDIN ¦ 35 R5: 3 ¦ 77/3 ¦ DA+0 ¦ DFR ¦ 2025-12-22 00:00:00 ¦ 35.089 ¦ Erection Completed. ¦ 2025-12-31 00:00:00 ¦ CRANE ¦ 49 R6: 4 ¦ 58/2 ¦ DA+0 ¦ DRY ¦ 2025-12-25 00:00:00 ¦ 35.089 ¦ Erection Completed. ¦ 2026-01-10 00:00:00 ¦ NASIRUDDIN ¦ 35 | SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Start Date ¦ MT ¦ Status ¦ End Date ¦ Gang Name ¦ Gang Strength 1 ¦ 56/7 ¦ DA+0 ¦ DFR ¦ 2025-12-15 00:00:00 ¦ 35.089 ¦ Erection Completed. ¦ 2025-12-20 00:00:00 ¦ NASIRUDDIN ¦ 35 2 ¦ 59/2 ¦ DA+0 ¦ DRY ¦ 2025-12-22 00:00:00 ¦ 35.089 ¦ Erection Completed. ¦ 2025-12-27 00:00:00 ¦ NASIRUDDIN ¦ 35 3 ¦ 77/3 ¦ DA+0 ¦ DFR ¦ 2025-12-22 00:00:00 ¦ 35.089 ¦ Erection Completed. ¦ 2025-12-31 00:00:00 ¦ CRANE ¦ 49 4 ¦ 58/2 ¦ DA+0 ¦ DRY ¦ 2025-12-25 00:00:00 ¦ 35.089 ¦ Erection Completed. ¦ 2026-01-10 00:00:00 ¦ NASIRUDDIN ¦ 35 5 ¦ 77/2 ¦ DA+0 ¦ DRY ¦ 2025-12-25 00:00:00 ¦ 35.089 ¦ Erection Completed. ¦ 2026-01-08 00:00:00 ¦ CRANE ¦ 49 6 ¦ 58/1 ¦ DA+6 ¦ DRY ¦ 2026-01-02 00:00:00 ¦ 41.88 ¦ Erection Completed. ¦ 2026-01-10 00:00:00 ¦ NASIRUDDIN ¦ 35 7 ¦ 77/1 ¦ DA+0 ¦ DRY ¦ 2026-01-01 00:00:00 ¦ 35.089 ¦ Erection Completed. ¦ 2026-01-13 00:00:00 ¦ CRANE ¦ 49 | ok
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | 2026-05-20 | X-ing Details | 1000 | 11 | statutory_crossing, summary_status | R6: Crossing Type ¦ 132 KV ¦ 220kV ¦ SH-Xing ¦ NH-Xing ¦ Railway-Xing ¦ Total R13: Sl. No. ¦ FROM (AP) ¦ TO (AP) ¦ Name of the Line ¦ NAME OF CROSSING ¦ Date of First Submission ¦ Joint Inspection Status ¦ Provisional approval status R14: 1 ¦ AP54 ¦ AP55 ¦ Railway crossing (Tandur - Vikarabad) ¦ Railway crossing ¦ 2025-11-26 00:00:00 R15: 2 ¦ AP57 ¦ AP58 ¦ 220kV D/C transmission line Tandur - Gachibowli (HYD) ¦ Power line ¦ 2025-10-16 00:00:00 R16: 3 ¦ AP61 ¦ AP62 ¦ NATIONAL HIGHWAY-163 (Kodangal - Hyderabad) ¦ National highway crossing ¦ 2025-11-28 00:00:00 | CROSSINGS PROPOSAL STATUS : 765 KV D/C Kurnool IV - Bidar TL (Part-2) Crossing Type ¦ 132 KV ¦ 220kV ¦ SH-Xing ¦ NH-Xing ¦ Railway-Xing ¦ Total Total Nos ¦ 4 ¦ 2 ¦ 1 ¦ 3 ¦ 2 ¦ 12 Submitted Till Date ¦ 4 ¦ 2 ¦ 3 ¦ 2 ¦ 11 Approved Till Date Balance to Execute ¦ 1 Crossings Details Sl. No. ¦ FROM (AP) ¦ TO (AP) ¦ Name of the Line ¦ NAME OF CROSSING ¦ Date of First Submission ¦ Joint Inspection Status ¦ Provisional approval status | ok
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | 2026-05-20 | Visual Chart | 1063 | 39 | earthing_tack, erection, foundation, project_details, statutory_crossing, stringing, summary_status, visual_l2 | R3: Foundation (Nos.):- ¦ 120 ¦ /292 ¦ Erection (Nos.):- ¦ 71 ¦ /292 ¦ Earthing (Nos.):- ¦ 98 ¦ /292 ¦ Rough Sag (Kms):- ¦ 0 / ¦ 113.292 ¦ Final Sag (Kms):- ¦ 0 / ¦ 113.292 ¦ Date:- ¦ 2026-05-20 00:00:00 R4: COMPLETION CHART ¦ Unit ¦ +3 ¦ 6 ¦ +9 ¦ Total ¦ Line Qty R5: ERECTION ¦ Rough Sag ¦ SH / NH Road Crossing R7: DA ¦ Nos ¦ 135 ¦ 48 ¦ 21 ¦ 12 ¦ 216 ¦ 216 ¦ FOUNDATION ¦ Type ¦ Angle Tower ¦ Gas Pipeline R9: DB2 ¦ Nos ¦ 13 ¦ 2 ¦ 4 ¦ 2 ¦ 21 ¦ 21 ¦ Final Sag | VISUAL PROGRESS CHART 765 kV DC Kurnool IV - Bidar Transmission Line (TL-02) Foundation (Nos.):- ¦ 120 ¦ /292 ¦ Erection (Nos.):- ¦ 71 ¦ /292 ¦ Earthing (Nos.):- ¦ 98 ¦ /292 ¦ Rough Sag (Kms):- ¦ 0 / ¦ 113.292 ¦ Final Sag (Kms):- ¦ 0 / ¦ 113.292 ¦ Date:- ¦ 2026-05-20 00:00:00 COMPLETION CHART ¦ Unit ¦ +3 ¦ 6 ¦ +9 ¦ Total ¦ Line Qty ERECTION ¦ Rough Sag ¦ SH / NH Road Crossing WIP ¦ River DA ¦ Nos ¦ 135 ¦ 48 ¦ 21 ¦ 12 ¦ 216 ¦ 216 ¦ FOUNDATION ¦ Type ¦ Angle Tower ¦ Gas Pipeline DB1 ¦ Nos ¦ 5 ¦ 3 ¦ 1 ¦ 8 ¦ 17 ¦ 17 | ok
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | 2026-05-20 | Foundation & Erection | 295 | 19 | earthing_tack, erection, foundation, project_details, row_hindrance, summary_status, supply | R1: Description ¦ FOUNDATION DETAILS ¦ EARTHING DETAILS ¦ Erection Details R2: SL. No ¦ Loc No. ¦ Type of Tower ¦ Type of FDN ¦ RC Fdn Y/N ¦ RC Drawing Status ¦ Stub Availbility Y/N ¦ Fdn ROW ¦ Date of Starting ¦ Date of Completion ¦ Gang Name ¦ Type of Earthing Cp/Pipe ¦ Date of Earthing Completed ¦ Tower Parts Availbility ¦ Tonnage MT ¦ Erection ROW ¦ Date of Starting ¦ Date of Completion ¦ Gang Name R6: 4 ¦ 48/3 ¦ 3DA+6 ¦ DFR ¦ No ¦ Yes ¦ Yes ¦ Completed ¦ 2026-05-11 00:00:00 ¦ 2026-05-19 00:00:00 ¦ Balaji Services ¦ Yes ¦ 41.88 R9: 7 ¦ 48/6 ¦ 3DA+3 ¦ DFR ¦ No ¦ Yes ¦ Yes ¦ Pit A&B Row ¦ Yes ¦ 36.771 R19: 17 ¦ 49/8 ¦ 3DA+0 ¦ DFR ¦ No ¦ Yes ¦ Yes ¦ Completed ¦ 2026-04-24 00:00:00 ¦ 2026-04-30 00:00:00 ¦ VEER TEJA CONSTRUCTION ¦ C P ¦ 2026-04-30 00:00:00 ¦ Yes ¦ 35.089 | Description ¦ FOUNDATION DETAILS ¦ EARTHING DETAILS ¦ Erection Details SL. No ¦ Loc No. ¦ Type of Tower ¦ Type of FDN ¦ RC Fdn Y/N ¦ RC Drawing Status ¦ Stub Availbility Y/N ¦ Fdn ROW ¦ Date of Starting ¦ Date of Completion ¦ Gang Name ¦ Type of Earthing Cp/Pipe ¦ Date of Earthing Completed ¦ Tower Parts Availbility ¦ Tonnage MT ¦ Erection ROW ¦ Date of Starting ¦ Date of Completion ¦ Gang Name 1 ¦ 48/0 ¦ 3DCT+0 ¦ DFR ¦ No ¦ - 2 ¦ 48/1 ¦ 3DA+6 ¦ DFR ¦ No ¦ Yes ¦ Yes ¦ Excavated ¦ Yes ¦ 41.88 3 ¦ 48/2 ¦ 3DA+0 ¦ DFR ¦ No ¦ Yes ¦ Yes ¦ Steel Binding ¦ Yes ¦ 35.089 4 ¦ 48/3 ¦ 3DA+6 ¦ DFR ¦ No ¦ Yes ¦ Yes ¦ Completed ¦ 2026-05-11 00:00:00 ¦ 2026-05-19 00:00:00 ¦ Balaji Services ¦ Yes ¦ 41.88 5 ¦ 48/4 ¦ 3DA+3 ¦ DFR ¦ No ¦ Yes ¦ Yes ¦ Excavated ¦ Yes ¦ 36.771 6 ¦ 48/5 ¦ 3DA+3 ¦ DFR ¦ No ¦ Yes ¦ Yes ¦ Wip ¦ Yes ¦ 36.771 | ok
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | 2026-05-20 | STRG Stretch | 82 | 21 | erection, foundation, opgw_accessories, row_hindrance, statutory_crossing, stringing, summary_status | R2: Stringing Stretches ¦ Legend ¦ FS Completed ¦ RS Completed ¦ WIP ¦ Row R3: S.No ¦ Section From ¦ Section TO ¦ LENGTH (km) ¦ T(T) / M(M) ¦ Total Fdns ¦ Fdn completed ¦ Pending Fdns ¦ Fdn WIP ¦ Total erection ¦ Erection completed ¦ Pending erection ¦ Erection WIP ¦ Stringing Status ¦ Streach Ready Y/N ¦ OPGW Status ¦ District ¦ POWER/ NH/ Railway crossings ¦ 11kV ¦ 33kV R10: 7 ¦ AP54 ¦ AP55 ¦ 0.23843999999999999 ¦ T ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ Vikarabad ¦ Railway Crossing LOC-54/0 ¦ 1 R11: 8 ¦ AP55 ¦ AP56 ¦ 1.436452 ¦ M ¦ 4 ¦ 2 ¦ 2 ¦ 4 ¦ 2 ¦ 2 ¦ Vikarabad ¦ Railway Crossing LOC-55/0 R13: 10 ¦ AP57 ¦ AP58 ¦ 0.214742 ¦ T ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ Vikarabad ¦ Power Line Crossing LOC-57/0 | 765KV D/C K4 - Bidar TL Package -II Stringing Stretches ¦ Legend ¦ FS Completed ¦ RS Completed ¦ WIP ¦ Row S.No ¦ Section From ¦ Section TO ¦ LENGTH (km) ¦ T(T) / M(M) ¦ Total Fdns ¦ Fdn completed ¦ Pending Fdns ¦ Fdn WIP ¦ Total erection ¦ Erection completed ¦ Pending erection ¦ Erection WIP ¦ Stringing Status ¦ Streach Ready Y/N ¦ OPGW Status ¦ District ¦ POWER/ NH/ Railway crossings ¦ 11kV ¦ 33kV 1 ¦ AP48 ¦ AP49 ¦ 3.30661 ¦ M ¦ 8 ¦ 8 ¦ 8 ¦ 8 ¦ Vikarabad 2 ¦ AP49 ¦ AP50 ¦ 4.581770000000001 ¦ M ¦ 12 ¦ 4 ¦ 8 ¦ 12 ¦ 12 ¦ Vikarabad 3 ¦ AP50 ¦ AP51 ¦ 1.51904 ¦ M ¦ 4 ¦ 4 ¦ AP51 ¦ 4 ¦ 4 ¦ Vikarabad 4 ¦ AP51 ¦ AP52 ¦ 4.30037 ¦ M ¦ 11 ¦ 6 ¦ 5 ¦ 11 ¦ 1 ¦ 10 ¦ Y ¦ Vikarabad 5 ¦ AP52 ¦ AP53 ¦ 1.995949 ¦ M ¦ 5 ¦ 2 ¦ 3 ¦ 5 ¦ 1 ¦ 4 ¦ Vikarabad | ok
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing Compiled | 1 | 23 | project_details, stretch_readiness, stringing, summary_status, supply | R1: S.no ¦ Sec ¦ From AP ¦ To AP ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name ¦ Gang Strength | S.no ¦ Sec ¦ From AP ¦ To AP ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name ¦ Gang Strength | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | DPR-KEC | 53 | 22 | project_details, summary_status, survey_soil, visual_l2 | R8: Activity ¦ LOA Quantity ¦ Final Estimated Quantity ¦ Cum. L2 till Last Month ¦ Cum Progress till Last Month ¦ L2 for present Month (May'26) ¦ Plan for the Month ¦ Plan for this Month (May'26) ¦ Progress for Today ¦ Progress for the Month (May'26) ¦ Cum. L2 till date ¦ Cum. Progress till date ¦ Balance Work ¦ Under Progress ¦ Gangs at Present R10: Route Alignment (Km) ¦ 186.3 ¦ 184.963 ¦ 184.963 ¦ 184.963 ¦ 184.963 ¦ 184.963 R11: Soil Investigation (Loc) ¦ 36 ¦ 31 ¦ 31 R18: Foundation (Loc) ¦ 494 ¦ 478 ¦ 142 ¦ 136 ¦ 25 ¦ 30 ¦ 35 ¦ 7 ¦ 167 ¦ 143 ¦ 335 ¦ 10 ¦ 5 R19: Earthing ¦ 494 ¦ 478 ¦ 142 ¦ 89 ¦ 25 ¦ 30 ¦ 35 ¦ 4 ¦ 167 ¦ 93 ¦ 385 | DAILY PROGRESS REPORT TL (602) Name of Line: Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line Agency: - M/s KEC International Limited NOA No.: CC/T/W-TW/DOM/A06/24/04774/NOA-2/25-105721/02 Dt:13-05-2025 Revenue:613.3 CR ¦ Date: ¦ 2026-05-19 09:24:24.870000 Activity ¦ LOA Quantity ¦ Final Estimated Quantity ¦ Cum. L2 till Last Month ¦ Cum Progress till Last Month ¦ L2 for present Month (May'26) ¦ Plan for the Month ¦ Plan for this Month (May'26) ¦ Progress for Today ¦ Progress for the Month (May'26) ¦ Cum. L2 till date ¦ Cum. Progress till date ¦ Balance Work ¦ Under Progress ¦ Gangs at Present Route Alignment (Km) ¦ 186.3 ¦ 184.963 ¦ 184.963 ¦ 184.963 ¦ 184.963 ¦ 184.963 Soil Investigation (Loc) ¦ 36 ¦ 31 ¦ 31 | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | Survey details | 37 | 16 | summary_status, survey_soil | R1: Survey Status ¦ Date: 04-05-2026 ¦ 2026-03-11 00:00:00 R3: Sl No ¦ Section ¦ Kms ¦ Detailed Survey ¦ Check Survey R4: Completed ¦ Submitted ¦ Approved ¦ Remarks ¦ Surveyor ¦ Completed ¦ Submitted ¦ Approved ¦ Remarks ¦ Surveyor R22: 18 ¦ AP94 to AP99 ¦ 6.622 ¦ 6.622 ¦ 6.622 ¦ Narmada River Crossing ¦ Hemanta Malik/Tapas Das | Survey Status ¦ Date: 04-05-2026 ¦ 2026-03-11 00:00:00 Project Name & Code ¦ TA-602 Sl No ¦ Section ¦ Kms ¦ Detailed Survey ¦ Check Survey Completed ¦ Submitted ¦ Approved ¦ Remarks ¦ Surveyor ¦ Completed ¦ Submitted ¦ Approved ¦ Remarks ¦ Surveyor 1 ¦ AP0 to AP16 ¦ 11.823 ¦ 11.823 ¦ 11.823 ¦ Submitted to PGCIL(25-04-2026) ¦ Mr. Tapas Das 2 ¦ AP16 to AP29 ¦ 7.454 ¦ 7.454 ¦ 7.454 ¦ 7.454 ¦ Approved ¦ Mr. Hemanta/Mr. Tapas Das 3 ¦ AP29 to AP35 ¦ 4.653 ¦ 4.653 ¦ 4.653 ¦ 4.653 ¦ Approved ¦ Mr. Hemanta/Mr. Tapas Das 4 ¦ AP35 to AP 40 ¦ 6.557 ¦ 6.557 ¦ 6.557 ¦ 6.557 ¦ Approved ¦ Mr. Hemanta/Mr. Tapas Das | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | Visual Chart | 441 | 64 | visual_l2 | R41: 13/2 ¦ 13/3 ¦ 14/0 ¦ 15/0 ¦ 15/1 ¦ 16/0 ¦ 17/0 ¦ 18/0 ¦ NH-56 ¦ 19/0 ¦ 20/0 ¦ 21/0 ¦ 22/0 ¦ 23/0 | KEC INTERNATIONAL LIMITED l Name of Line: ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line CLIENT : M/S Powergrid West Central Transmission Ltd. Date of Commencemen : 13-05-2025 VISUAL CHART Route Diversion Proposed ¦ No Diversion DS Submitted ¦ Route Diversion Proposed C ¦ B ¦ C ¦ B ¦ C ¦ B ¦ C ¦ B ¦ C ¦ B ¦ C ¦ B ¦ C ¦ B ¦ C ¦ B ¦ C ¦ B ¦ C ¦ B | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | Detail Survey | 29 | 14 | survey_soil | R22: 16 ¦ AP118 to AP 123 ¦ 6.502 ¦ RA-01 ¦ 2025-09-10 00:00:00 ¦ KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/18 ¦ 6.502 ¦ 2025-09-13 00:00:00 ¦ WR-II/Khargone/HVDC/TLC/TL-06/Detail Survey R23: 17 ¦ AP123 to AP126 ¦ 6.516 ¦ RA-01 ¦ 2025-08-25 00:00:00 ¦ KEC/PGCIL800kV HVDC /KPS2 & NGP/TL06/011 ¦ 6.516 ¦ 2025-08-28 00:00:00 ¦ WR-II/Khargone/HVDC/TLC/TL-06/Detail Survey R24: 18 ¦ AP126 to Ap127 ¦ 4.34 ¦ RA-01 ¦ 2025-09-22 00:00:00 ¦ KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/20 ¦ 1 ¦ 4.34 ¦ 2025-09-26 00:00:00 ¦ WR-II/Khargone/HVDC/TLC/TL-06/Detail Survey R27: 21 ¦ AP130 to AP134 ¦ 4.122 ¦ RA-01 ¦ 2025-09-22 00:00:00 ¦ KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/20 ¦ 1 ¦ 4.122 ¦ 2025-09-26 00:00:00 ¦ WR-II/Khargone/HVDC/TLC/TL-06/Detail Survey ¦ R-1 CS | KEC International Limited Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line Detail Survey ¦ 2026-05-19 09:24:24.870000 Sl.No ¦ Section ¦ As Per Letter ¦ Section Length KMS ¦ Revenue ¦ Submission Date ¦ Submission Reference No. ¦ Revision ¦ As Per Approved Letter ¦ Approved ¦ Approval date ¦ Approval reference No. ¦ Remark's ¦ Balance to be Approved 1 ¦ AP0 to AP23 ¦ 14.432 ¦ 2025-12-13 00:00:00 ¦ KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/69 2 ¦ AP33 to AP38A ¦ 5.575 ¦ 2026-01-12 00:00:00 ¦ KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/94 3 ¦ AP38 to AP51 ¦ 14.458 ¦ 2025-12-16 00:00:00 ¦ KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/73 4 ¦ AP51 to AP62 ¦ 8.345 ¦ 8.344 ¦ Feb'26 ¦ 2026-01-19 00:00:00 ¦ KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/100 ¦ 8.344 ¦ 2026-02-16 00:00:00 ¦ WR-II/Khargone/HVDC/TLC/TL-06/58 | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | Check Survey | 29 | 13 | survey_soil | R17: 13 ¦ AP123 to AP126 ¦ 6.516 ¦ 2025-08-30 00:00:00 ¦ KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/14 ¦ 6.516 ¦ 6.516 ¦ 2025-09-01 00:00:00 ¦ WR-II/Khargone/HVDC/TLC/TL-06/Checksurvey ¦ RA-01 R18: 14 ¦ AP126 to AP127 ¦ 4.34 ¦ 2025-09-26 00:00:00 ¦ KEC/PGCILt 800KV HVDC /KPS2&NGP/TL-06/ 22 ¦ 1 ¦ 4.241 ¦ 4.34 ¦ 2025-09-26 00:00:00 ¦ WR-II/Khargone/HVDC/TLC/TL-06/DetailSurvey ¦ Approval needed R22: 18 ¦ AP130 to AP134 ¦ 1.685 ¦ 2025-09-26 00:00:00 ¦ KEC/PGCILt 800KV HVDC /KPS2&NGP/TL-06/ 22 ¦ 1.685 ¦ 2025-09-26 00:00:00 ¦ WR-II/Khargone/HVDC/TLC/TL-06/DetailSurvey | KEC International Limited Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line Check Survey ¦ 2026-05-19 09:24:24.870000 Sl.No ¦ Section ¦ Section Length ¦ Submission Date ¦ Submission Reference No. ¦ Revision ¦ As Per Approved Letter ¦ Approved ¦ Approval date ¦ Letter Refference no. ¦ Remark's 1 ¦ AP51 to AP64 ¦ 11.959 ¦ 2026-02-17 00:00:00 ¦ KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/99 ¦ 11.959 ¦ 2026-02-17 00:00:00 ¦ WR-II/Khargone/HVDC/TLC/TL-06/61 2 ¦ AP64 to AP71 ¦ 9.709 ¦ 2026-01-16 00:00:00 ¦ KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/99 ¦ 9.71 ¦ 9.71 ¦ 2026-02-06 00:00:00 ¦ WR-II/Khargone/HVDC/TLC/TL-06/56 3 ¦ AP71 to AP 76 ¦ 4.965 ¦ 2026-02-17 00:00:00 ¦ KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/121 ¦ 4.965 ¦ 2026-02-17 00:00:00 ¦ WR-II/Khargone/HVDC/TLC/TL-06/61 4 ¦ AP76 to AP83 ¦ 7.242 ¦ 2026-01-03 00:00:00 ¦ KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/90 ¦ 7.242 ¦ 7.242 ¦ 2026-01-03 00:00:00 ¦ WR-II/Khargone/HVDC/TLC/TL-06/48 | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | FDN | 155 | 17 | foundation | R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Complete ¦ Days ¦ Name of the Gang ¦ Name of Section In-charge ¦ Name of Engineer/Supervisor ¦ No. ¦ Remarks | KEC International Limited Name of Line: Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line Details of Foundation ¦ 2026-05-19 09:24:24.870000 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Complete ¦ Days ¦ Name of the Gang ¦ Name of Section In-charge ¦ Name of Engineer/Supervisor ¦ No. ¦ Remarks 1 ¦ 1 ¦ 125/2 ¦ A+3 ¦ DFR ¦ 2025-09-02 00:00:00 ¦ 2025-09-15 00:00:00 ¦ 13 ¦ Balaji Enterprises ¦ Mr. Arindam Das ¦ Mr. Arindam Das ¦ 1 ¦ SEP'25 ¦ 1 2 ¦ 1 ¦ 125/3 ¦ A+6 ¦ DFR ¦ 2025-09-09 00:00:00 ¦ 2025-10-03 00:00:00 ¦ 24 ¦ Balaji Enterprises ¦ Mr. Arindam Das ¦ Mr. Wahajuddin Biswas ¦ 9 ¦ Oct'25 ¦ 2 3 ¦ 2 ¦ 123/1 ¦ A+0 ¦ WFR ¦ 2025-10-01 00:00:00 ¦ 2025-10-07 00:00:00 ¦ 6 ¦ R.K . Enterprises ¦ Mr. Arindam Das ¦ Mr. Wahajuddin Biswas ¦ 3 4 ¦ 3 ¦ 124/1 ¦ A+6 ¦ WET Paddy ¦ 2025-09-21 00:00:00 ¦ 2025-10-08 00:00:00 ¦ 17 ¦ Balaji Enterprises ¦ Mr. Arindam Das ¦ Mr. Wahajuddin Biswas ¦ 4 | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | Composite-Survey(05-04-2026) | 1029 | 34 | row_hindrance, statutory_crossing, survey_soil | R6: Sl.No ¦ AP NO. ¦ TOWER NO. ¦ TYPE OF TOWER ¦ DEVIATION ANGLE (Deg) ¦ SPAN (Mtr) ¦ Section Length (m) ¦ HT of Tower (Mtr) ¦ CUMULATIVE SPAN ¦ R.L (Mtr) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) ¦ UTM Coordinates ¦ CROSSING DETAILS/ REMARKS ¦ Detail Survey ¦ Check Survey | CLIENT :- M/s POWERGRID WEST CENTRAL TRANSMISSION LIMITED NAME OF PROJECT :- Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line M/s. KEC INTERNATIONAL LIMITED Composite TS Detail and Check Survey KEC/TA602/800 KV/TS/ REV.0 Sl.No ¦ AP NO. ¦ TOWER NO. ¦ TYPE OF TOWER ¦ DEVIATION ANGLE (Deg) ¦ SPAN (Mtr) ¦ Section Length (m) ¦ HT of Tower (Mtr) ¦ CUMULATIVE SPAN ¦ R.L (Mtr) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ LONGITUDE (E) ¦ LATITUDE (N) ¦ UTM Coordinates ¦ CROSSING DETAILS/ REMARKS ¦ Detail Survey ¦ Check Survey Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Easting ¦ Northing ¦ Submitted ¦ Approved ¦ Submitted ¦ Approved 1 ¦ AP 0 ¦ 0/0 ¦ D60+9 ¦ 0° 0' 0" ¦ 57.32 ¦ 399.684 ¦ 337 ¦ 168.5 ¦ 209 ¦ 209 ¦ 197 ¦ 197 ¦ 74°13'43.053" ¦ 22°35'55.261" ¦ 420714.94 ¦ 2499300.38 ¦ Common Point ¦ No ¦ No | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | Erection | 335 | 15 | earthing_tack, erection, project_details, summary_status | R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Start ¦ Complete ¦ Name of the Gang ¦ Name of Supervisor/Engineer ¦ STATUS ¦ Tack welding Status ¦ Zinc Paint status ¦ Tower Weight(MT) ¦ Completion Month ¦ Revenue R5: 1 ¦ 1 ¦ 125/2 ¦ A+3 ¦ 2026-02-18 00:00:00 ¦ 2026-02-22 00:00:00 ¦ M/S Ratani Devi ¦ Mr. Mijanur ¦ Completed ¦ Feb'26 ¦ 434444.11 ¦ 24.042 R6: 2 ¦ 2 ¦ 130/1 ¦ A+0 ¦ 2026-02-22 00:00:00 ¦ 2026-02-28 00:00:00 ¦ M/S Jwala ¦ Mr.Saddam' ¦ Completed ¦ Feb'26 ¦ 22.925 R7: 3 ¦ 3 ¦ 122/2 ¦ A+0 ¦ 2026-02-25 00:00:00 ¦ 2026-02-28 00:00:00 ¦ M/S Ratani Devi ¦ Mr. Mijanur ¦ Completed ¦ Feb'26 ¦ 22.925 R9: 4 ¦ 1 ¦ 126/10 ¦ A+0 ¦ 2026-03-07 00:00:00 ¦ M/s Ratani Devi ¦ Mr. Saddam ¦ Completed ¦ Mar'26 ¦ 412920.1 ¦ 22.925 | M/s. KEC INTERNATIONAL LIMITED Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line Details of Erection ¦ 2026-05-19 09:24:24.870000 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Start ¦ Complete ¦ Name of the Gang ¦ Name of Supervisor/Engineer ¦ STATUS ¦ Tack welding Status ¦ Zinc Paint status ¦ Tower Weight(MT) ¦ Completion Month ¦ Revenue 1 ¦ 1 ¦ 125/2 ¦ A+3 ¦ 2026-02-18 00:00:00 ¦ 2026-02-22 00:00:00 ¦ M/S Ratani Devi ¦ Mr. Mijanur ¦ Completed ¦ Feb'26 ¦ 434444.11 ¦ 24.042 2 ¦ 2 ¦ 130/1 ¦ A+0 ¦ 2026-02-22 00:00:00 ¦ 2026-02-28 00:00:00 ¦ M/S Jwala ¦ Mr.Saddam' ¦ Completed ¦ Feb'26 ¦ 22.925 3 ¦ 3 ¦ 122/2 ¦ A+0 ¦ 2026-02-25 00:00:00 ¦ 2026-02-28 00:00:00 ¦ M/S Ratani Devi ¦ Mr. Mijanur ¦ Completed ¦ Feb'26 ¦ 22.925 4 ¦ 1 ¦ 126/10 ¦ A+0 ¦ 2026-03-07 00:00:00 ¦ M/s Ratani Devi ¦ Mr. Saddam ¦ Completed ¦ Mar'26 ¦ 412920.1 ¦ 22.925 | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | Earthing | 407 | 15 | earthing_tack, project_details | R4: CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Completion Date ¦ Type ¦ Name of the Gang ¦ Name of Supervisor ¦ No. ¦ Remarks ¦ Revenue | KEC International Limited Name of Line: Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line Details of Earthing ¦ 2026-05-19 09:24:24.870000 CUMM. SR.NO ¦ MONTH SR.NO. ¦ Loc. No. ¦ Type of Tower ¦ Type of Classification ¦ Start ¦ Completion Date ¦ Type ¦ Name of the Gang ¦ Name of Supervisor ¦ No. ¦ Remarks ¦ Revenue 1 ¦ 1 ¦ 123/1 ¦ A+0 ¦ WFR ¦ 2025-10-10 00:00:00 ¦ CP ¦ R.K . Enterprises ¦ SUOMEN KHAN & AASISH SHARMA ¦ 4 ¦ Oct'25 ¦ RA-1 ¦ CP 2 ¦ 2 ¦ 121/2 ¦ A+6 ¦ DFR ¦ 2025-10-20 00:00:00 ¦ CP ¦ Balaji Enterprises ¦ MADHUSUDHAN PRASAD ¦ RA-1 ¦ RA-3 ¦ CP 3 ¦ 3 ¦ 124/2 ¦ A+6 ¦ WFR ¦ 2025-10-20 00:00:00 ¦ CP ¦ Jai Shri Ram Enterprises ¦ UTTAM KUMAR DAS ¦ RA-1 ¦ RA-3 ¦ CP 4 ¦ 4 ¦ 123/3 ¦ A+9 ¦ DFR ¦ 2025-10-22 00:00:00 ¦ CP ¦ R.K . Enterprises ¦ JAYANTA GHOSH ¦ RA-1 ¦ CP | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | WIP | 888 | 12 | foundation, project_details, summary_status | R6: S.NO. ¦ LOC. NO. ¦ Tower Type ¦ Type of FDN ¦ GANG NAME ¦ Man power ¦ Start Date ¦ Completion Date ¦ Section Incharge ¦ Engineer/Supervisor ¦ REMARKS R7: 1 ¦ 68/1 ¦ A+0 ¦ DFR ¦ Afflux ¦ 2026-02-08 00:00:00 ¦ Mr. Ajay ¦ Mr. vishnu Nair ¦ Excavation WIP R8: 2 ¦ 70/0 ¦ C2-3 ¦ DFR ¦ Soham Entp ¦ 2026-05-03 00:00:00 ¦ Mr. Ajay ¦ Mr. vishnu Nair ¦ Excavation WIP R12: 6 ¦ 90/0 ¦ C1+0 ¦ 2026-05-17 00:00:00 ¦ Mr. Ajay ¦ Mr. vishnu Nair ¦ Excavation WIP R13: 7 ¦ 104/0 ¦ B2+3 ¦ Wet Paddy ¦ Pawan ¦ 2026-04-18 00:00:00 ¦ Mr. Tanmay ¦ Mr. Wahijuddin Biswas ¦ Excavation Completed ¦ Labour Unvailble | xz DAILY PROGRESS REPORT (Activity Wise WIP ) ¦ 2026-05-19 09:24:24.870000 Name of Line: Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line FOUNDATION S.NO. ¦ LOC. NO. ¦ Tower Type ¦ Type of FDN ¦ GANG NAME ¦ Man power ¦ Start Date ¦ Completion Date ¦ Section Incharge ¦ Engineer/Supervisor ¦ REMARKS 1 ¦ 68/1 ¦ A+0 ¦ DFR ¦ Afflux ¦ 2026-02-08 00:00:00 ¦ Mr. Ajay ¦ Mr. vishnu Nair ¦ Excavation WIP 2 ¦ 70/0 ¦ C2-3 ¦ DFR ¦ Soham Entp ¦ 2026-05-03 00:00:00 ¦ Mr. Ajay ¦ Mr. vishnu Nair ¦ Excavation WIP 3 ¦ 71/5 ¦ A+3 ¦ WFR ¦ Soham Entp ¦ 04/05/226 ¦ Mr. Ajay ¦ Mr. vishnu Nair ¦ Pit B& D Frsutum Completed | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | statuary clearance | 26 | 9 | statutory_crossing | R5: S.No. ¦ Type of Proposal ¦ Tower No. ¦ Name of Existing Line ¦ Voltage Level ¦ Proposal Subitted by KEC to PGCIL. ¦ Joint Inspection Done on ¦ Plan To Submit R7: 1 ¦ PLC ¦ AP46 TO AP47 ¦ 400KV D/C XING ¦ 400KV ¦ Submitted(07/05/2026) R8: 2 ¦ PLC ¦ AP59 TO AP60 ¦ 132KV D/C ¦ 132KV ¦ Submitted(03/04/2026) ¦ Done R9: 3 ¦ PLC ¦ AP74 TO AP75 ¦ 132KV S/C ¦ 132KV ¦ Submitted(03/04/2026) ¦ Done R10: 4 ¦ PLC ¦ AP80 TO AP81 ¦ 132KV S/C ON H POLE ¦ 132KV ¦ Subbmitted (20/01/2026) ¦ Done | Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line Details of Crossing S.No. ¦ Type of Proposal ¦ Tower No. ¦ Name of Existing Line ¦ Voltage Level ¦ Proposal Subitted by KEC to PGCIL. ¦ Joint Inspection Done on ¦ Plan To Submit 1 ¦ PLC ¦ AP46 TO AP47 ¦ 400KV D/C XING ¦ 400KV ¦ Submitted(07/05/2026) 2 ¦ PLC ¦ AP59 TO AP60 ¦ 132KV D/C ¦ 132KV ¦ Submitted(03/04/2026) ¦ Done 3 ¦ PLC ¦ AP74 TO AP75 ¦ 132KV S/C ¦ 132KV ¦ Submitted(03/04/2026) ¦ Done 4 ¦ PLC ¦ AP80 TO AP81 ¦ 132KV S/C ON H POLE ¦ 132KV ¦ Subbmitted (20/01/2026) ¦ Done 5 ¦ PLC ¦ AP86 TO AP87 ¦ 132KV S/C ¦ 132KV ¦ Subbmitted (20/01/2026) ¦ Done | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | statuary clearance (2) | 32 | 15 | statutory_crossing, summary_status | R5: S.No. ¦ Type of Proposal ¦ Tower No. ¦ Name of Existing Line ¦ Owner of the existing Line ¦ Voltage Level ¦ Tower No of existing Line ¦ Village Name ¦ Proposal Subitted by KEC to PGCIL. ¦ Status ¦ Concerned person Name & Mobile No. ¦ Latest Status ¦ Plan To Submit R6: Proposal Submitted to Concerned agency ¦ Joint Inspection Done on ¦ Approved ¦ Plan To Submit R7: 1 ¦ PLC ¦ AP46 TO AP47 ¦ 400KV D/C XING ¦ 400KV ¦ Submitted(07/05/2026) R8: 2 ¦ PLC ¦ AP59 TO AP60 ¦ 132KV D/C ¦ 132KV ¦ Submitted(03/04/2026) ¦ Done R9: 3 ¦ PLC ¦ AP74 TO AP75 ¦ 132KV S/C ¦ 132KV ¦ Submitted(03/04/2026) ¦ Done | KEC INTERNATIONAL LIMITED Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line Details of Crossing S.No. ¦ Type of Proposal ¦ Tower No. ¦ Name of Existing Line ¦ Owner of the existing Line ¦ Voltage Level ¦ Tower No of existing Line ¦ Village Name ¦ Proposal Subitted by KEC to PGCIL. ¦ Status ¦ Concerned person Name & Mobile No. ¦ Latest Status ¦ Plan To Submit Proposal Submitted to Concerned agency ¦ Joint Inspection Done on ¦ Approved ¦ Plan To Submit 1 ¦ PLC ¦ AP46 TO AP47 ¦ 400KV D/C XING ¦ 400KV ¦ Submitted(07/05/2026) 2 ¦ PLC ¦ AP59 TO AP60 ¦ 132KV D/C ¦ 132KV ¦ Submitted(03/04/2026) ¦ Done 3 ¦ PLC ¦ AP74 TO AP75 ¦ 132KV S/C ¦ 132KV ¦ Submitted(03/04/2026) ¦ Done | ok
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | 2026-05-18 | Supply Status | 142 | 41 | project_details, summary_status, supply, survey_soil | R5: SL NO ¦ DESCRIPTION ¦ UNIT ¦ Total LOA Qty. ¦ Cumulative Qty. as per Check Survey ¦ Cumulative Released for Supply (PR) ¦ Unit ¦ RECEIVED Qty. ¦ TOTAL RECEIVED ¦ Total Received ¦ Issued From Store ¦ Consumed ¦ Balance at Store ¦ Balance Req. from Plant ¦ Remarks R9: 1 ¦ A TYPE NORMAL STUB ¦ Sets ¦ 313 ¦ 313 ¦ 250 ¦ Set ¦ 2272.944 ¦ 180 ¦ 115 ¦ 112 ¦ 65 ¦ 70 R11: 1 ¦ B TYPE NORMAL STUB(Up to +9 M Extension) ¦ Sets ¦ 64 ¦ 38 ¦ 26 ¦ Set ¦ 26 ¦ 1 ¦ 25 R16: 1 ¦ C TYPE NORMAL STUB ¦ Sets ¦ 60 ¦ 31 ¦ 19 ¦ Set ¦ 19 ¦ 19 | KEC International Limited Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line SUPPLY STATUS 2026-05-19 09:24:24.870000 SL NO ¦ DESCRIPTION ¦ UNIT ¦ Total LOA Qty. ¦ Cumulative Qty. as per Check Survey ¦ Cumulative Released for Supply (PR) ¦ Unit ¦ RECEIVED Qty. ¦ TOTAL RECEIVED ¦ Total Received ¦ Issued From Store ¦ Consumed ¦ Balance at Store ¦ Balance Req. from Plant ¦ Remarks HT ¦ MS STUBS A ¦ A-TYPE | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | TB401 DPR..... | 24 | 263 | earthing_tack, erection, foundation, project_details, row_hindrance, summary_status, supply, survey_soil, visual_l2 | R1: Project Code ¦ TB-401 ¦ Date ¦ 2025-12-26 00:00:00 ¦ LOA Start Date ¦ 2023-04-25 00:00:00 ¦ Business Head (T&D)- India & Sri Lanka ¦ Rajinder Gupta R2: Project Name ¦ 765KV D/C Fategarh-III Beawar Transmission Line ¦ LOA End Date ¦ 2024-07-25 00:00:00 ¦ PCH ¦ Sivaraman Nataraajan R4: LE Value ¦ Rs 312 Cr -Supply -Rs 227.5 Cr.; Service.-Rs 84.4 Cr ¦ Planning ¦ Shah Ali Khan ¦ Project Manager ¦ Virender Gupta R5: Activity ¦ Unit ¦ LOA Qty. ¦ LE Qty ¦ Progress till Last Month ¦ Balance ¦ L2 for Dec'23 ¦ Plan for Dec.'23 ¦ Today's Progress ¦ Month Progress ¦ WIP ¦ Gangs at Present ¦ L2 Till Month-Dec.23 ¦ Progress Till Date ¦ Balance Work ¦ Remarks R6: Route Alignment ¦ km ¦ 215 ¦ 202 ¦ 167 ¦ 35 ¦ 35 ¦ 215 ¦ 167 ¦ 35 ¦ 35 Km is hold due to ROW issues | Project Code ¦ TB-401 ¦ Date ¦ 2025-12-26 00:00:00 ¦ LOA Start Date ¦ 2023-04-25 00:00:00 ¦ Business Head (T&D)- India & Sri Lanka ¦ Rajinder Gupta Project Name ¦ 765KV D/C Fategarh-III Beawar Transmission Line ¦ LOA End Date ¦ 2024-07-25 00:00:00 ¦ PCH ¦ Sivaraman Nataraajan Client Name ¦ Strelite Power ¦ Time Extn ¦ 2024-07-25 00:00:00 ¦ Regional Manager ¦ Sandeep Singh Kumar LE Value ¦ Rs 312 Cr -Supply -Rs 227.5 Cr.; Service.-Rs 84.4 Cr ¦ Planning ¦ Shah Ali Khan ¦ Project Manager ¦ Virender Gupta Activity ¦ Unit ¦ LOA Qty. ¦ LE Qty ¦ Progress till Last Month ¦ Balance ¦ L2 for Dec'23 ¦ Plan for Dec.'23 ¦ Today's Progress ¦ Month Progress ¦ WIP ¦ Gangs at Present ¦ L2 Till Month-Dec.23 ¦ Progress Till Date ¦ Balance Work ¦ Remarks Route Alignment ¦ km ¦ 215 ¦ 202 ¦ 167 ¦ 35 ¦ 35 ¦ 215 ¦ 167 ¦ 35 ¦ 35 Km is hold due to ROW issues Detailed Survey ¦ km ¦ 215 ¦ 202 ¦ 202 ¦ 215 ¦ 202 ¦ SPTL Approved -202/202-Kms Check Survey ¦ km ¦ 215 ¦ 202 ¦ 92.704 ¦ 109.296 ¦ 20 ¦ 50 ¦ 17.852 ¦ 160 ¦ 110.556 ¦ 91.444 ¦ 1. Total 7.854 Km is under review of SPTL. 2. Total check survey completed (Field work) 167 Km. 3. Total 60 Km check survey is hold due to row issues & Other issues. | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Eng. | 9 | 11 | foundation, summary_status, supply | R2: Tower ¦ Tower Design ¦ Test Tower ¦ Balance Structural Drawing. ¦ Tower ¦ Stub & Template Drawings ¦ Foundation R4: Target ¦ Status ¦ Target ¦ Status ¦ Target ¦ Status ¦ Target ¦ Status R5: DA Tower ¦ 2023-05-12 00:00:00 ¦ Approved ¦ 2023-06-04 00:00:00 ¦ Approved ¦ 2023-06-24 00:00:00 ¦ Approved for proto ¦ Completed ¦ Approved ¦ 15-July ¦ Approved R6: DB Tower ¦ 2023-05-30 00:00:00 ¦ Approved ¦ 2023-07-30 00:00:00 ¦ Approved ¦ 2023-07-19 00:00:00 ¦ Approvedin Cat-B ¦ Completed ¦ Approved for Proto ¦ DB all Fdn. By 25 -July ¦ Approved R8: DD Tower ¦ 2023-06-21 00:00:00 ¦ Approved ¦ 30-Sept. ¦ Approved in Cat -B ¦ 2023-08-20 00:00:00 ¦ Approved in Cat -B ¦ Completed ¦ Approved in Cat -B ¦ 2023-07-31 00:00:00 ¦ Approved | Tower ¦ Tower Design ¦ Test Tower ¦ Balance Structural Drawing. ¦ Tower ¦ Stub & Template Drawings ¦ Foundation Types ¦ Structural Drawing(BTB+0) ¦ (3M/6M/9M) ¦ Testing ¦ Design/Drg Target ¦ Status ¦ Target ¦ Status ¦ Target ¦ Status ¦ Target ¦ Status DA Tower ¦ 2023-05-12 00:00:00 ¦ Approved ¦ 2023-06-04 00:00:00 ¦ Approved ¦ 2023-06-24 00:00:00 ¦ Approved for proto ¦ Completed ¦ Approved ¦ 15-July ¦ Approved DB Tower ¦ 2023-05-30 00:00:00 ¦ Approved ¦ 2023-07-30 00:00:00 ¦ Approved ¦ 2023-07-19 00:00:00 ¦ Approvedin Cat-B ¦ Completed ¦ Approved for Proto ¦ DB all Fdn. By 25 -July ¦ Approved DD Tower ¦ 2023-06-21 00:00:00 ¦ Approved ¦ 30-Sept. ¦ Approved in Cat -B ¦ 2023-08-20 00:00:00 ¦ Approved in Cat -B ¦ Completed ¦ Approved in Cat -B ¦ 2023-07-31 00:00:00 ¦ Approved DC Tower ¦ 2023-07-16 00:00:00 ¦ Approved ¦ 2023-10-08 00:00:00 ¦ Approved in Cat -B ¦ 2023-09-19 00:00:00 ¦ Approved in Cat -B ¦ Completed ¦ Approved in Cat -B ¦ 2023-08-25 00:00:00 ¦ Approved | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Fdn (Pkg -G Section -I) | 32 | 13 | foundation | R4: Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Excavation Start ¦ Dt. of Start ¦ Dt. of Concrete ¦ Name of Sub-Contractor ¦ KEC representative ¦ KEC Section In-Charge ¦ Remarks | KEC INTERNATIONAL LIMITED ¦ Date: ¦ 2025-12-26 00:00:00 LILO of 765 Kv DV Fatehgarh 3 Beawar TL FOUNDATION Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Excavation Start ¦ Dt. of Start ¦ Dt. of Concrete ¦ Name of Sub-Contractor ¦ KEC representative ¦ KEC Section In-Charge ¦ Remarks 1 ¦ 1 ¦ 32/7 ¦ DA+0 ¦ SANDY ¦ 23.10.23 ¦ 25.10.23 ¦ 28.10.23 ¦ Shakti Construction ¦ Kumar Nayak ¦ Jish C Verghese ¦ Complete 2 ¦ 2 ¦ 32/5 ¦ DA+6 ¦ SANDY ¦ 29.10.23 ¦ 31.10.23 ¦ 04.11.2023 ¦ Shakti Construction ¦ Kumar Nayak ¦ Jish C Verghese ¦ Complete 3 ¦ 3 ¦ 32/1 ¦ DA+9 ¦ SANDY ¦ 03.11.23 ¦ 06.11.23 ¦ 10.11.23 ¦ Shakti Construction ¦ Kumar Nayak ¦ Jish C Verghese ¦ Complete 4 ¦ 4 ¦ 30/2 ¦ DA+0 ¦ SANDY ¦ 13.11.23 ¦ 15.11.23 ¦ 16.11.23 ¦ Shakti Construction ¦ Kumar Nayak ¦ Jish C Verghese ¦ Complete | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | TB401 DPR | 32 | 22 | project_details, summary_status, survey_soil, visual_l2 | R2: 765KV D/C Fategarh-III Beawar Transmission Line ¦ TB-401 ¦ LOA Date ¦ Pkg-G -26.04.23 ¦ Completion Period ¦ 2025-03-31 00:00:00 ¦ Date: ¦ 2025-12-26 00:00:00 R3: TB-408 ¦ Pkg-F - 11.09.23 ¦ Completion Period ¦ 2025-03-31 00:00:00 R5: Activity ¦ Qty as per LOA ¦ Qty Received ¦ L2 ¦ Overall Progress ¦ Mar'25 ¦ Balance ¦ Apr'25 ¦ Plan ¦ Remarks R6: 2024-12-30 00:00:00 ¦ Till Mar-25 ¦ As on date ¦ Till Mar-25 ¦ Plan ¦ Actual ¦ As on date ¦ Plan ¦ WIP ¦ Today comp ¦ Actual ¦ 2024-09-01 00:00:00 ¦ 2024-07-01 00:00:00 R7: Details Survey ¦ 215 ¦ 189.53 ¦ 203 ¦ 199.841 ¦ 199.841 | Project Progress for TB-401/408,Section-II 765KV D/C Fategarh-III Beawar Transmission Line ¦ TB-401 ¦ LOA Date ¦ Pkg-G -26.04.23 ¦ Completion Period ¦ 2025-03-31 00:00:00 ¦ Date: ¦ 2025-12-26 00:00:00 TB-408 ¦ Pkg-F - 11.09.23 ¦ Completion Period ¦ 2025-03-31 00:00:00 . Activity ¦ Qty as per LOA ¦ Qty Received ¦ L2 ¦ Overall Progress ¦ Mar'25 ¦ Balance ¦ Apr'25 ¦ Plan ¦ Remarks 2024-12-30 00:00:00 ¦ Till Mar-25 ¦ As on date ¦ Till Mar-25 ¦ Plan ¦ Actual ¦ As on date ¦ Plan ¦ WIP ¦ Today comp ¦ Actual ¦ 2024-09-01 00:00:00 ¦ 2024-07-01 00:00:00 Details Survey ¦ 215 ¦ 189.53 ¦ 203 ¦ 199.841 ¦ 199.841 Pkg-G (Section-II) ¦ 101.1 ¦ 107.5 ¦ 101.1 ¦ 101.1 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Foundation (Pkg-F) | 246 | 27 | foundation | R4: Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Excavation Start ¦ Dt. of Start ¦ Dt. of Concrete ¦ Name of Sub-Contractor ¦ KEC representative ¦ KEC Section In-Charge ¦ Remarks R17: 11 ¦ 11 ¦ 62/4 ¦ DA+3 ¦ DRY ¦ 08.12.23 ¦ 26.12.23 ¦ 28.12.23 ¦ Shakti Construction ¦ sanjay ¦ Rakesh Pathak ¦ Complete ¦ Excavation & Rod binding - Amirul | KEC INTERNATIONAL LIMITED ¦ Date: ¦ 2025-12-26 00:00:00 LILO of 765 Kv DV Fatehgarh 3 Beawar TL FOUNDATION Pkg -F (Section -II) Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Excavation Start ¦ Dt. of Start ¦ Dt. of Concrete ¦ Name of Sub-Contractor ¦ KEC representative ¦ KEC Section In-Charge ¦ Remarks 2023-12-01 00:00:00 1 ¦ 1 ¦ 61/3 ¦ DA+6 ¦ DRY ¦ 11.12.23 ¦ 13.12.23 ¦ 14.12.23 ¦ Manoj Sharma ¦ Dipesh ¦ RT Singh ¦ Complete 2 ¦ 2 ¦ 62/6 ¦ DA+3 ¦ DRY ¦ 08.12.23 ¦ 16.12.23 ¦ 18.12.23 ¦ Shakti Construction ¦ sanjay ¦ Rakesh Pathak ¦ Complete 3 ¦ 3 ¦ 59/14 ¦ DA+6 ¦ DRY ¦ 13.12.23 ¦ 17.12.23 ¦ 18.12.23 ¦ Manoj Sharma ¦ Dipesh ¦ RT Singh ¦ Complete | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Earthing (PKG-F) | 244 | 13 | earthing_tack | R4: Sl. No. ¦ Cum S No ¦ Location No. ¦ Tower Type ¦ Classification ¦ Type of Earthing ¦ Earthing ¦ Name of Sub-Contractor ¦ Check list | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Earthing Sl. No. ¦ Cum S No ¦ Location No. ¦ Tower Type ¦ Classification ¦ Type of Earthing ¦ Earthing ¦ Name of Sub-Contractor ¦ Check list 2023-12-01 00:00:00 1 ¦ 1 ¦ 61/3 ¦ DA+6 ¦ DRY ¦ Pipe Type ¦ 18.12.23 ¦ Manoj Sharma 2 ¦ 2 ¦ 62/4 ¦ DA+3 ¦ DRY ¦ Pipe Type ¦ 31.12.23 ¦ Shakti Const. 2024-01-01 00:00:00 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Project Details | 40 | 11 | project_details | R1: Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Supervisor | Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Supervisor TB401 ¦ 765 KV Fatehgarh III to Beawer 2nd Transmission Line, PKG G ¦ Resonia Limited ¦ 26/4/2023 ¦ 2025-12-31 00:00:00 ¦ Mr Santosh Pandey ¦ Mr. Sanjay Kumar Gupta ¦ Mr. Sandeep Singh Kumar ¦ Mr. Virender Gupta ¦ Sumit Kumar ¦ Pradeep Kumar Rajeev Kumar ¦ Vikas Kumar Vivek Shukla ¦ Ganesh Singh Vijay Yadav ¦ Dineshwar Mahto Ram Tirath Singh ¦ Kamla Pal Prasad Jitendra Saini ¦ Bisun Saw Shakib Hussain | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Progress | 12 | 16 | earthing_tack, erection, foundation, opgw_accessories, project_details, stringing, summary_status, visual_l2 | R1: Project Code ¦ TB401 ¦ LOA Start Date ¦ 26.04.23 ¦ SBU Head ¦ Mr. Rajender Gupta ¦ Head T&D-North ¦ Sanjay K. Gupta R2: Project Name ¦ 765KV DC Fateggarh III to Beawar (2nd) TL ¦ LOA Completion Date ¦ 31.03.25 ¦ Regional Manager ¦ Mr Sandeep Kumar Singh ¦ Planning Engineer ¦ Santosh Pandey R3: Client Name ¦ RESONIA LIMITED ¦ Expected Completion ¦ 31.12.25 ¦ Project Manager ¦ Mr Virender Gupta ¦ Date ¦ 2025-12-26 00:00:00 R4: Activity ¦ Final Estimated Quantity ¦ Cumulative L2 Till Last Month ¦ Cumulative Progress Till last Month ¦ L2 For Present Month ¦ Plan for the Month ¦ Today's Progress ¦ Progress till Date for the Month ¦ L2 Till Current Month ¦ Completed Till Date ¦ Balance Work ¦ Under Progress ¦ Gangs at present ¦ Remarks R5: FOUNDATION ¦ 521 ¦ 521 ¦ 519 ¦ 2 ¦ 1 ¦ 520 ¦ 1 ¦ 0.9980806142034548 | Project Code ¦ TB401 ¦ LOA Start Date ¦ 26.04.23 ¦ SBU Head ¦ Mr. Rajender Gupta ¦ Head T&D-North ¦ Sanjay K. Gupta Project Name ¦ 765KV DC Fateggarh III to Beawar (2nd) TL ¦ LOA Completion Date ¦ 31.03.25 ¦ Regional Manager ¦ Mr Sandeep Kumar Singh ¦ Planning Engineer ¦ Santosh Pandey Client Name ¦ RESONIA LIMITED ¦ Expected Completion ¦ 31.12.25 ¦ Project Manager ¦ Mr Virender Gupta ¦ Date ¦ 2025-12-26 00:00:00 Activity ¦ Final Estimated Quantity ¦ Cumulative L2 Till Last Month ¦ Cumulative Progress Till last Month ¦ L2 For Present Month ¦ Plan for the Month ¦ Today's Progress ¦ Progress till Date for the Month ¦ L2 Till Current Month ¦ Completed Till Date ¦ Balance Work ¦ Under Progress ¦ Gangs at present ¦ Remarks FOUNDATION ¦ 521 ¦ 521 ¦ 519 ¦ 2 ¦ 1 ¦ 520 ¦ 1 ¦ 0.9980806142034548 EARTHING ¦ 521 ¦ 521 ¦ 494 ¦ 27 ¦ 1 ¦ 495 ¦ 26 ERECTION ¦ 521 ¦ 521 ¦ 502 ¦ 19 ¦ 12 ¦ 514 ¦ 7 ¦ 2 ¦ 2 ¦ 0.9865642994241842 TACK WELDING ¦ 521 ¦ 521 ¦ 356 ¦ 35 ¦ 31 ¦ 387 ¦ 134 ¦ 3 ¦ 3 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Hindrance | 949 | 10 | erection, foundation, project_details, row_hindrance, stringing, survey_soil | R3: 3 ¦ Name of the Executing Agency ¦ KEC International Limited ¦ LOA No. & Date ¦ LOI/EPC/FBTL/KEC/01 Dated 25.04.2023 R5: Sr. No. ¦ Activity ¦ Total ¦ Open ¦ Close R6: 1 ¦ Survey ¦ 18 ¦ 18 R7: 2 ¦ Foundation ¦ 207 ¦ 32 ¦ 175 R8: 3 ¦ Erection ¦ 72 ¦ 40 ¦ 32 | HINDRANCE REGISTER 1 ¦ Name of the Substation/TL/Project ¦ 765 KV Fatehgarh-3 Beawer Transmission Line Part-G ¦ Name of Work ¦ Transmission & Power Distribution 3 ¦ Name of the Executing Agency ¦ KEC International Limited ¦ LOA No. & Date ¦ LOI/EPC/FBTL/KEC/01 Dated 25.04.2023 Sr. No. ¦ Activity ¦ Total ¦ Open ¦ Close 1 ¦ Survey ¦ 18 ¦ 18 2 ¦ Foundation ¦ 207 ¦ 32 ¦ 175 3 ¦ Erection ¦ 72 ¦ 40 ¦ 32 4 ¦ Stringing | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Foundation (Pkg-G) | 565 | 19 | foundation | R4: Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Excavation Start ¦ Dt. of Start ¦ Dt. of complete ¦ Name of Sub-Contractor ¦ KEC representative ¦ KEC Section In-Charge ¦ Remarks | KEC INTERNATIONAL LIMITED ¦ Date: ¦ 2025-12-26 00:00:00 LILO of 765 Kv DV Fatehgarh 3 Beawar TL FOUNDATION Pkg -G (Section -II) Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Excavation Start ¦ Dt. of Start ¦ Dt. of complete ¦ Name of Sub-Contractor ¦ KEC representative ¦ KEC Section In-Charge ¦ Remarks July-23 1 ¦ 1 ¦ 58/12 ¦ DA+0 ¦ DRY ¦ 14.07.2023 ¦ 15.07.2023 ¦ Mahadev engg. ¦ Mr. Mahamaya ¦ Mr. Shah Ali Khan ¦ Complete 2 ¦ 2 ¦ 59/1 ¦ DA+0 ¦ DRY ¦ 19.07.2023 ¦ 20.07.2023 ¦ Manoj Sharma ¦ Mr Manoj ¦ Mr. Shah Ali Khan ¦ Complete 3 ¦ 3 ¦ 58/14 ¦ DA+0 ¦ DRY ¦ 17.07.2023 ¦ 20.07.2023 ¦ Mahadev engg. ¦ Mr Manoj ¦ Mr. Shah Ali Khan ¦ Complete | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Earthing (PKG-G) | 527 | 14 | earthing_tack | R4: Cum S No ¦ Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Type of Earthing ¦ Earthing ¦ Name of Sub-Contractor ¦ Check list | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Earthing Cum S No ¦ Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Type of Earthing ¦ Earthing ¦ Name of Sub-Contractor ¦ Check list 2023-08-01 00:00:00 1 ¦ 1 ¦ 58/1 ¦ DA+0 ¦ DRY ¦ Pipe Type ¦ 16.08.23 ¦ Mahadev engg. ¦ Check list submitted 2 ¦ 2 ¦ 58/11 ¦ DA+3 ¦ DRY ¦ Pipe Type ¦ 20.08.23 ¦ Mahadev engg. ¦ Check list submitted 3 ¦ 3 ¦ 58/3 ¦ DA+3 ¦ DRY ¦ Pipe Type ¦ 24.8.23 ¦ Mahadev engg. ¦ Check list submitted | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Benching Status-F | 144 | 23 | summary_status | R2: Sl No. ¦ RC ¦ Loc No. ¦ Tower Type ¦ CP Position Up/Down ¦ Raised Chimney ¦ Chimney Extension ¦ Submitted Benching Volume (Cum) ¦ Approved Benching Volume (Cum) ¦ Approval Date ¦ JMC NO ¦ JMC Date | RC, Benching & Revetment Locations Sl No. ¦ RC ¦ Loc No. ¦ Tower Type ¦ CP Position Up/Down ¦ Raised Chimney ¦ Chimney Extension ¦ Submitted Benching Volume (Cum) ¦ Approved Benching Volume (Cum) ¦ Approval Date ¦ JMC NO ¦ JMC Date A ¦ B ¦ C ¦ D ¦ Cutting ¦ Filling ¦ Cutting ¦ Filling 47 ¦ 26947.807 ¦ 10818.857 ¦ 10 1 ¦ 40/0 ¦ DC2+0 ¦ 1 ¦ 1 ¦ 91.75 2 ¦ Y ¦ 40/1 ¦ DA+6 ¦ 1 ¦ 2 ¦ 153.267 3 ¦ 40/2 ¦ DA+3 ¦ 48.633 4 ¦ Y ¦ 40/3 ¦ DA+6 ¦ 1 ¦ 2 ¦ 238.433 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Revetment Pkg-G | 13 | 12 | foundation | R5: SI. No ¦ Loc No ¦ Tower Type ¦ Dt. of Start ¦ Dt. of complete ¦ Random Rubble stone masonry including excavation (1:5 Cement concrete) ¦ Excavation Volume ¦ Back filling and levelling of volumes enclosed by revetment. ¦ M15 Conc Nominal Mix 1:2:4 for top seal cover ¦ M10 (PEDDING -PCC) | Revetment work SI. No ¦ Loc No ¦ Tower Type ¦ Dt. of Start ¦ Dt. of complete ¦ Random Rubble stone masonry including excavation (1:5 Cement concrete) ¦ Excavation Volume ¦ Back filling and levelling of volumes enclosed by revetment. ¦ M15 Conc Nominal Mix 1:2:4 for top seal cover ¦ M10 (PEDDING -PCC) 1 ¦ 35/5 ¦ DA+0 RC ¦ 20.11.24 ¦ 24.12.24 ¦ 83 ¦ 17.19 ¦ 282.1 ¦ 0.37 ¦ 2.73 Total ¦ 83 ¦ 282.1 ¦ 0.37 ¦ 2.73 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Benching Status-G | 204 | 17 | summary_status | R2: Sl No. ¦ RC ¦ Loc No. ¦ Tower Type ¦ CP Position Up/Down ¦ Raised Chimney ¦ Chimney Extension ¦ Submitted Benching Volume (Cum) ¦ Approved Benching Volume (Cum) ¦ Approval Date ¦ JMC NO ¦ JMC Date | RC, Benching & Revetment Locations Sl No. ¦ RC ¦ Loc No. ¦ Tower Type ¦ CP Position Up/Down ¦ Raised Chimney ¦ Chimney Extension ¦ Submitted Benching Volume (Cum) ¦ Approved Benching Volume (Cum) ¦ Approval Date ¦ JMC NO ¦ JMC Date A ¦ B ¦ C ¦ D ¦ Cutting ¦ Filling ¦ Cutting ¦ Filling 1 ¦ 1/0 ¦ DE+0 ¦ 283.2 ¦ 1 ¦ 111.651 ¦ 89.5 2 ¦ 1A/0 ¦ DD60+0 ¦ 284.927 ¦ 270.309 ¦ 265.381 3 ¦ 1A/1 ¦ DA+0 ¦ 292.179 ¦ 2 ¦ 1 ¦ 46.489 ¦ 22.529 4 ¦ 1A/3 ¦ DA+0 ¦ 281.458 ¦ 1 ¦ 45.554 ¦ 45.554 5 ¦ 1A/4 ¦ DA+3 ¦ 281.508 ¦ 1 ¦ 81.372 ¦ 64.075 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Earthing Pkg -G Ist section | 11 | 8 | earthing_tack, foundation | R4: Sl. No. ¦ Cum S No ¦ Location No. ¦ Tower Type ¦ Classification ¦ Type of Earthing ¦ Earthing ¦ Name of Sub-Contractor | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL FOUNDATION Sl. No. ¦ Cum S No ¦ Location No. ¦ Tower Type ¦ Classification ¦ Type of Earthing ¦ Earthing ¦ Name of Sub-Contractor 1 ¦ 1 ¦ 32/7 ¦ DA+0 ¦ SANDY ¦ Pipe Type ¦ 07.11.23 ¦ Shakti Construction 2 ¦ 2 ¦ 32/1 ¦ DA+9 ¦ SANDY ¦ Pipe Type ¦ 10.11.23 ¦ Shakti Construction 3 ¦ 3 ¦ 32/5 ¦ DA+6 ¦ SANDY ¦ Pipe Type ¦ 10.11.23 ¦ Shakti Construction 4 ¦ 4 ¦ 30/2 ¦ DA+0 ¦ SANDY ¦ Pipe Type ¦ 18.11.23 ¦ Om Const | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Earthing balance | 14 | 8 | earthing_tack |  | S no ¦ PKG- G ¦ PKG- F 1 ¦ 72/1 ¦ Mahadev engg. ¦ 50/3 ¦ Kalpana Const. 2 ¦ 71/5 ¦ Mahadev engg. ¦ 73/9 ¦ Shakti Const. -2 3 ¦ 43/2 ¦ Sai Infra ¦ 73/2 ¦ Shree Shyam Const. 4 ¦ 43/3 ¦ Sai Infra ¦ 50/6 ¦ Kalpana Const. 5 ¦ 68/3 ¦ Shakti Const. -2 6 ¦ 73/0 ¦ Mahadev engg. - 2 7 ¦ 68/1 ¦ Shakti Const. -2 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Tack Welding - PKG-F | 158 | 16384 | earthing_tack, foundation, summary_status | R4: Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Tack Welding Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks Feb-24 1 ¦ 1 ¦ 59/13 ¦ DA+3 ¦ 20.02.24 ¦ 20.02.24 ¦ Done ¦ Suraja Ram 2 ¦ 2 ¦ 59/14 ¦ DA+6 ¦ 22.02.24 ¦ 22.02.24 ¦ Done ¦ Suraja Ram 3 ¦ 3 ¦ 62/5 ¦ DA+0 ¦ 27.02.24 ¦ 27.02.24 ¦ Done ¦ Suraja Ram | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Tack Welding - PKG-G | 418 | 16084 | earthing_tack, summary_status | R4: Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Tack Welding Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks 2023-10-01 00:00:00 1 ¦ 1 ¦ 57/12 ¦ DA+3 ¦ 24.10.23 ¦ 25.10.23 ¦ Done ¦ Suraja Ram 2 ¦ 2 ¦ 57/13 ¦ DA+0 ¦ 24.10.23 ¦ 25.10.23 ¦ Done ¦ Suraja Ram 3 ¦ 3 ¦ 57/11 ¦ DA+0 ¦ 25.10.23 ¦ 26.10.23 ¦ Done ¦ Suraja Ram | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Painting - PKG-F | 156 | 16085 | earthing_tack, foundation, summary_status | R4: Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Painting Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks 1 ¦ 1 ¦ 59/14 ¦ DA+6 ¦ 26.02.24 ¦ 26.02.24 ¦ Done ¦ Suraja Ram 2 ¦ 2 ¦ 63/6 ¦ DA+3 ¦ 29.02.24 ¦ 29.02.24 ¦ Done ¦ Suraja Ram March'24 3 ¦ 1 ¦ 62/3 ¦ DA+0 ¦ 11.03.24 ¦ 11.03.24 ¦ Done ¦ Suraja Ram | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Painting - PKG-G | 303 | 16084 | earthing_tack, foundation, summary_status | R4: Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Painting Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks 15/2 2023-12-01 00:00:00 ¦ 29/5 1 ¦ 1 ¦ 56/9 ¦ DA+3 ¦ 02.12.23 ¦ 03.12.23 ¦ Done ¦ Suraja Ram ¦ 29/6 2 ¦ 2 ¦ 57/1 ¦ DA+3 ¦ 02.12.23 ¦ 03.12.23 ¦ Done ¦ Suraja Ram ¦ 29/7 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Idling details from Aug | 62 | 14 | commercial, erection, project_details, row_hindrance | R2: Sr No ¦ Gang Name ¦ Activity ¦ Location no ¦ PKGs ¦ Time ¦ Date ¦ Reason ¦ Photograph attached ¦ Remarks R4: 1 ¦ Pusplata-6 ¦ Erection ¦ 23/2 ¦ G ¦ 12:30:00 ¦ 20:21:00 ¦ 7.849999999999999 ¦ 2025-07-30 00:00:00 ¦ 2025-07-30 00:00:00 ¦ ROW ¦ Photos\23-2.jpg R5: 2 ¦ Gourishankar ¦ Erection ¦ 31/1 ¦ G ¦ 08:00:00 ¦ 12:26:00 ¦ 4.433333333333335 ¦ 2025-08-02 00:00:00 ¦ 2025-08-02 00:00:00 ¦ Approch road issue ¦ Photos\31-1.jpg R6: 3 ¦ Bhairo /Arawali ¦ Erection ¦ 4/0 ¦ G ¦ 12:30:00 ¦ 11:05:00 ¦ 22.583333333333332 ¦ 2025-08-03 00:00:00 ¦ 2025-08-04 00:00:00 ¦ 1 ¦ Due to non-payment of crop composition ¦ Photos\4-0.png R7: 4 ¦ Gourishankar ¦ Erection ¦ 31/1 ¦ G ¦ 14:52:00 ¦ 17:06:00 ¦ 2.2333333333333334 ¦ 2025-08-03 00:00:00 ¦ 2025-08-03 00:00:00 ¦ Due to non-payment of crop composition ¦ Photos\31-1 2nd idle.jpg | Erection Team idle month of Aug. PKG-G Sr No ¦ Gang Name ¦ Activity ¦ Location no ¦ PKGs ¦ Time ¦ Date ¦ Reason ¦ Photograph attached ¦ Remarks Start ¦ End ¦ Total time ¦ Start ¦ End ¦ Total 1 ¦ Pusplata-6 ¦ Erection ¦ 23/2 ¦ G ¦ 12:30:00 ¦ 20:21:00 ¦ 7.849999999999999 ¦ 2025-07-30 00:00:00 ¦ 2025-07-30 00:00:00 ¦ ROW ¦ Photos\23-2.jpg 2 ¦ Gourishankar ¦ Erection ¦ 31/1 ¦ G ¦ 08:00:00 ¦ 12:26:00 ¦ 4.433333333333335 ¦ 2025-08-02 00:00:00 ¦ 2025-08-02 00:00:00 ¦ Approch road issue ¦ Photos\31-1.jpg 3 ¦ Bhairo /Arawali ¦ Erection ¦ 4/0 ¦ G ¦ 12:30:00 ¦ 11:05:00 ¦ 22.583333333333332 ¦ 2025-08-03 00:00:00 ¦ 2025-08-04 00:00:00 ¦ 1 ¦ Due to non-payment of crop composition ¦ Photos\4-0.png 4 ¦ Gourishankar ¦ Erection ¦ 31/1 ¦ G ¦ 14:52:00 ¦ 17:06:00 ¦ 2.2333333333333334 ¦ 2025-08-03 00:00:00 ¦ 2025-08-03 00:00:00 ¦ Due to non-payment of crop composition ¦ Photos\31-1 2nd idle.jpg 5 ¦ Priyanka -Sudheer ¦ Erection ¦ 16/6 ¦ G ¦ 17:31:00 ¦ 18:02:00 ¦ 0.5166666666666675 ¦ 2025-08-03 00:00:00 ¦ 2025-08-03 00:00:00 ¦ Due to non-payment of crop composition ¦ Photos\16-6 1st.jpg | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Erection Compiled | 560 | 16076 | erection, project_details, summary_status | R4: Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Starting Date ¦ Completion Date ¦ Gang Name ¦ Status ¦ Tower Weight R18: 11 ¦ 8 ¦ 58/1 ¦ DA+0 ¦ 25.09.23 ¦ 12.10.23 ¦ Ganesh Kr. Sinha ¦ Complete ¦ 37.504 R24: 17 ¦ 14 ¦ 58/3 ¦ DA+3 ¦ 12.10.23 ¦ 22.10.23 ¦ Ganesh Kr. Sinha ¦ Complete ¦ 38.847 R29: 22 ¦ 19 ¦ 58/5 ¦ DA+3 ¦ 20.10.23 ¦ 31.10.23 ¦ Ganesh Kr. Sinha ¦ Complete ¦ 38.847 R37: 29 ¦ 6 ¦ 58/4 ¦ DA+0 ¦ 31.10.23 ¦ 11.11.2023 ¦ Ganesh Kr. Sinha ¦ Complete ¦ 37.504 | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Erection Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Starting Date ¦ Completion Date ¦ Gang Name ¦ Status ¦ Tower Weight 2023-09-01 00:00:00 1 ¦ 1 ¦ 57/9 ¦ DA+0 ¦ 13.09.23 ¦ 21.09.23 ¦ Sobha Devi ¦ Complete ¦ 37.504 2 ¦ 2 ¦ 58/12 ¦ DA+0 ¦ 18.09.23 ¦ 25.09.23 ¦ Sunny Const ¦ Complete ¦ 37.504 3 ¦ 3 ¦ 57/11 ¦ DA+0 ¦ 21.09.23 ¦ 26.09.23 ¦ Sobha Devi ¦ Complete ¦ 37.504 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Crane Erection PKG-G | 21 | 16 | erection | R3: S no ¦ Locs ¦ TOT ¦ Crane Using ¦ Manual Erection ¦ Gangs | S no ¦ Locs ¦ TOT ¦ Crane Using ¦ Manual Erection ¦ Gangs Start Date ¦ Complete Date ¦ No of Days ¦ Weight ¦ Gang ¦ Manpower ¦ Start Date ¦ Complete Date ¦ No of Days ¦ Weight ¦ Manpower 1 ¦ 1A/4 ¦ DA+3 ¦ 04.05.25 ¦ 08.05.25 ¦ 5 ¦ 17.48115 ¦ Anil Kumar ¦ 42 ¦ 01.06.25 ¦ 05.06.25 ¦ 5 ¦ 21.365850000000002 ¦ 30 ¦ Bhairo Mahto (Departmental) 2 ¦ 1A/3 ¦ DA+0 ¦ 14.05.25 ¦ 18.05.25 ¦ 5 ¦ 16.8768 ¦ Anil Kumar ¦ 42 ¦ 12.06.25 ¦ 15.06.25 ¦ 4 ¦ 20.6272 ¦ 30 ¦ Bhairo Mahto (Departmental) 4 ¦ 1A/6 ¦ DA+0 ¦ 01.06.25 ¦ 03.06.25 ¦ 3 ¦ 16.8768 ¦ Anil Kumar ¦ 42 ¦ 14.06.25 ¦ 21.06.25 ¦ 8 ¦ 20.6272 ¦ 30 ¦ Kewat (Departmental) 3 ¦ 1A/5 ¦ DA+6 ¦ 19.05.25 ¦ 27.05.25 ¦ 9 ¦ 20.43585 ¦ Anil Kumar ¦ 42 ¦ 22.06.25 ¦ 27.06.25 ¦ 6 ¦ 24.977149999999998 ¦ 33 ¦ Bhairo Mahto (Departmental) 5 ¦ 1A/7 ¦ DA+3 ¦ 09.06.25 ¦ 12.06.25 ¦ 4 ¦ 17.48115 ¦ Anil Kumar ¦ 42 ¦ 30.06.25 ¦ 07.07.25 ¦ 8 ¦ 21.365850000000002 ¦ 33 ¦ Kewat (Departmental) 6 ¦ 1A/0 ¦ DD60+0 ¦ 18.06.25 ¦ 23.06.24 ¦ 6 ¦ 51.667 ¦ Anil Kumar ¦ 53 ¦ 29.06.25 ¦ 14.07.25 ¦ 15 ¦ 34.462 ¦ 32 ¦ Bhairo Mahto/Ramayan (Departmental) | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Erection Productivity | 102 | 41 | erection, row_hindrance, stringing | R1: Sr no ¦ Item ¦ Unit ¦ Total ¦ Comp Qty R3: 1 ¦ Erection ¦ Nos ¦ 521 ¦ 292 R4: 2 ¦ Stringing ¦ KM ¦ 202 ¦ 61.016 R8: Sr. No. ¦ Sub-Contractor Name ¦ WIP ¦ 01.09.25 ¦ 02.09.25 ¦ 03.09.25 ¦ 05.09.25 ¦ 06.09.25 ¦ 07.09.25 ¦ 08.09.25 ¦ 09.09.25 ¦ 10.09.25 ¦ 11.09.25 ¦ 12.09.25 ¦ 13.09.25 ¦ 14.09.25 ¦ 15.09.25 ¦ 16.09.25 ¦ 18.09.25 ¦ 19.09.25 R9: Loc. No. ¦ Type of Tower ¦ Tower Weight ¦ Plan ¦ Actual ¦ Shotfall | Sr no ¦ Item ¦ Unit ¦ Total ¦ Comp Qty Qty ¦ 31.05.25 1 ¦ Erection ¦ Nos ¦ 521 ¦ 292 2 ¦ Stringing ¦ KM ¦ 202 ¦ 61.016 Gang Wise Output ction - Jul'25 Sr. No. ¦ Sub-Contractor Name ¦ WIP ¦ 01.09.25 ¦ 02.09.25 ¦ 03.09.25 ¦ 05.09.25 ¦ 06.09.25 ¦ 07.09.25 ¦ 08.09.25 ¦ 09.09.25 ¦ 10.09.25 ¦ 11.09.25 ¦ 12.09.25 ¦ 13.09.25 ¦ 14.09.25 ¦ 15.09.25 ¦ 16.09.25 ¦ 18.09.25 ¦ 19.09.25 Loc. No. ¦ Type of Tower ¦ Tower Weight ¦ Plan ¦ Actual ¦ Shotfall 1 ¦ Priyanka devi (Subodh) ¦ 10/1 ¦ DA+3 ¦ 38.847 ¦ 4.82 ¦ 4.82 ¦ 4.82 ¦ 11.82 ¦ 12.567 ¦ 38.847 ¦ Complete | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Eretion - PKG-F | 190 | 16083 | erection, foundation | R4: Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Erection PKG-F Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks Feb-24 1 ¦ 1 ¦ 60/7 ¦ DA+3 ¦ 28.1.24 ¦ 04.02.24 ¦ Suraj const ¦ Complete ¦ 38.847 2 ¦ 2 ¦ 59/13 ¦ DA+3 ¦ 01.02.24 ¦ 07.02.24 ¦ Chinta Devi ¦ Complete ¦ 38.847 3 ¦ 3 ¦ 63/6 ¦ DA+3 ¦ 03.02.24 ¦ 10.02.24 ¦ Sunny Const. ¦ Complete ¦ 38.847 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Sheet1 | 27 | 4 |  | R2: S No ¦ Loc No ¦ TOT ¦ Classification | S No ¦ Loc No ¦ TOT ¦ Classification 1 ¦ 58/14 ¦ DA+0 ¦ DRY 2 ¦ 51/7 ¦ DA+3 ¦ DFR 3 ¦ 51/5 ¦ DA+0 ¦ DRY 4 ¦ 51/2 ¦ DA+0 ¦ DRY 5 ¦ 53/2 ¦ DA+3 ¦ DFR 6 ¦ 57/7 ¦ DA+3 ¦ DRY 7 ¦ 57/4 ¦ DA+0 ¦ DRY | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | JMC 27.9.23 | 24 | 15 | foundation | R9: 7 ¦ 51/1 ¦ DA+0 ¦ DFR ¦ 10.09.23 ¦ Amirul Islam ¦ Excavation u/p R11: 9 ¦ 56/1 ¦ DA+3 ¦ DFR ¦ 21.09.23 ¦ Vaishali Const ¦ Excavation done R15: 13 ¦ 71/4 ¦ DA+0 ¦ DRY ¦ 23.09.23 ¦ Mahadev engg. ¦ Excavation complete ¦ 51 R16: 14 ¦ 55/11 ¦ DA+3 ¦ DFR ¦ 22.09.23 ¦ Nurul Amin ¦ Excavation u/p ¦ 32 R18: 16 ¦ 56/4 ¦ DA+3 ¦ DFR ¦ 24.9.23 ¦ Manoj Sharma ¦ Excavation | S no ¦ Locs no ¦ TOT ¦ Classification 1 ¦ 56/3 ¦ DA+0 ¦ DFR ¦ 14.09.23 ¦ 23.09.23 ¦ 25.09.23 ¦ Vaishali Const ¦ JMC required 2 ¦ 44/1 ¦ DA+0 ¦ WFR ¦ 16.09.23 ¦ 20.09.23 ¦ 25.09.23 ¦ Shakti Construction ¦ JMC required 3 ¦ 72/5 ¦ DA+0 ¦ DRY ¦ 19.09.23 ¦ 24.09.23 ¦ 25.09.23 ¦ Mahadev engg. ¦ JMC required 4 ¦ 41/10 ¦ DA+3 ¦ SANDY ¦ 19.09.23 ¦ 22.09.23 ¦ 25.09.23 ¦ Om Const ¦ JMC required 5 ¦ 56/6 ¦ DA+3 ¦ DRY ¦ 21.09.23 ¦ 24.09.23 ¦ 25.09.23 ¦ Manoj Sharma ¦ JMC required 6 ¦ 72/2 ¦ DA+0 ¦ DRY ¦ 15.09.23 ¦ 20.09.23 ¦ 26.09.23 ¦ Mahadev engg. ¦ JMC required 7 ¦ 51/1 ¦ DA+0 ¦ DFR ¦ 10.09.23 ¦ Amirul Islam ¦ Excavation u/p | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Jumpering-G | 22 | 7 | stringing, supply | R4: Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Jumpering ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Insulator Hoisting Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Jumpering ¦ Name of Sub-Contractor ¦ Ramarks 1 ¦ 1 ¦ 57/6 ¦ DB+0 ¦ 02.06.24 ¦ GPJ Const. ¦ Done 2 ¦ 2 ¦ 57/0 ¦ DB2+0 ¦ 12.07.24 ¦ GPJ Const. ¦ Done 3 ¦ 3 ¦ 56/0 ¦ DB1+0 ¦ 21.07.24 ¦ GPJ Const. ¦ Done 4 ¦ 4 ¦ 55/0 ¦ DC1+0 ¦ GPJ Const. ¦ Done | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Insulator Hoisting - F | 44 | 8 | supply | R4: Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Insulator Hoisting Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks July'24 1 ¦ 1 ¦ 60/11 ¦ DA+3 ¦ 21.07.24 ¦ 21.07.24 ¦ Kuddus ¦ Complete 2 ¦ 2 ¦ 60/9 ¦ DA+3 ¦ 22.07.24 ¦ 22.07.24 ¦ Kuddus ¦ Complete 3 ¦ 3 ¦ 60/10 ¦ DA+0 ¦ 22.07.24 ¦ 22.07.24 ¦ Kuddus ¦ Complete | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Insulator Hoisting - G | 73 | 9 | supply | R4: Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Insulator Hoisting Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks Jan'24 1 ¦ 1 ¦ 57/5 ¦ DA+3 ¦ 05.01.24 ¦ 05.01.24 ¦ Mainul Hoque ¦ Complete 2 ¦ 2 ¦ 57/4 ¦ DA+0 ¦ 06.01.24 ¦ 06.01.24 ¦ Mainul Hoque ¦ Complete 3 ¦ 3 ¦ 57/3 ¦ DA+0 ¦ 07.01.24 ¦ 07.01.24 ¦ Mainul Hoque ¦ Complete | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Jumpering-F | 12 | 7 | stringing, supply | R4: Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Jumpering ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Insulator Hoisting Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Jumpering ¦ Name of Sub-Contractor ¦ Ramarks 1 ¦ 1 ¦ 61/0 ¦ 23.10.24 ¦ Kuddua Ali 2 ¦ 2 ¦ 62/0 ¦ 11.11.24 ¦ Kuddua Ali | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Stringing - PKG-F | 22 | 19 | stringing | R5: S. No ¦ Section ¦ Paying Out ¦ Final Sag ¦ Name of Gang ¦ Remarks R6: From ¦ To ¦ Length ¦ Cum ¦ Start Date ¦ Finish Date ¦ Month ¦ Start Date ¦ Finish Date ¦ Month R7: 1 ¦ 60/0 ¦ 61/0 ¦ 4.877 ¦ 4.877 ¦ 21.08.24 ¦ 28.08.24 ¦ 2024-08-24 00:00:00 ¦ 09.09.24 ¦ 16.09.24 ¦ 2024-09-24 00:00:00 ¦ Kuddus ali ¦ Final sag completed R8: 2 ¦ 61/0 ¦ 62/0 ¦ 4.568 ¦ 9.445 ¦ 06.09.24 ¦ 16.09.24 ¦ 2024-09-24 00:00:00 ¦ 26.9.24 ¦ 03.10.24 ¦ 2024-10-24 00:00:00 ¦ Kuddus ali ¦ Final sag completed R9: 3 ¦ 62/0 ¦ 63/0 ¦ 4.863 ¦ 14.308 ¦ 23.09.24 ¦ 02.10.24 ¦ 2024-10-24 00:00:00 ¦ 17.10.24 ¦ 22.10.24 ¦ 2024-10-24 00:00:00 ¦ Kuddus ali ¦ Final sag completed | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL STRINGING Stringing - PKG-F S. No ¦ Section ¦ Paying Out ¦ Final Sag ¦ Name of Gang ¦ Remarks From ¦ To ¦ Length ¦ Cum ¦ Start Date ¦ Finish Date ¦ Month ¦ Start Date ¦ Finish Date ¦ Month 1 ¦ 60/0 ¦ 61/0 ¦ 4.877 ¦ 4.877 ¦ 21.08.24 ¦ 28.08.24 ¦ 2024-08-24 00:00:00 ¦ 09.09.24 ¦ 16.09.24 ¦ 2024-09-24 00:00:00 ¦ Kuddus ali ¦ Final sag completed 2 ¦ 61/0 ¦ 62/0 ¦ 4.568 ¦ 9.445 ¦ 06.09.24 ¦ 16.09.24 ¦ 2024-09-24 00:00:00 ¦ 26.9.24 ¦ 03.10.24 ¦ 2024-10-24 00:00:00 ¦ Kuddus ali ¦ Final sag completed | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Stringing Productivity | 29 | 14 | stringing, summary_status | R2: Sr. No. ¦ Sub-Contractor Name ¦ Completed in April ¦ Output for the day ¦ Output Upto Yesterdays(Kms) in May ¦ Cumulative Output till today(Kms) ¦ Start Date ¦ Comp Date ¦ Status ¦ Total Manpower R3: From ¦ To ¦ Span ¦ From ¦ To ¦ Span Length R4: 1 ¦ MR Power ¦ 59/0 ¦ 60/0 ¦ 2.581 ¦ 04.05.25 ¦ Final sag done R5: 2 ¦ Indrajeet ¦ 42/0 ¦ 43/0 ¦ 0.489 ¦ 11.05.25 ¦ Final sag done R6: 3 ¦ Indrajeet ¦ 49/0 ¦ 50/0 ¦ 0.241 ¦ 17.05.25 ¦ Final sag done | TB401 Stringing Status ¦ Dated 06-05-2025 Sr. No. ¦ Sub-Contractor Name ¦ Completed in April ¦ Output for the day ¦ Output Upto Yesterdays(Kms) in May ¦ Cumulative Output till today(Kms) ¦ Start Date ¦ Comp Date ¦ Status ¦ Total Manpower From ¦ To ¦ Span ¦ From ¦ To ¦ Span Length 1 ¦ MR Power ¦ 59/0 ¦ 60/0 ¦ 2.581 ¦ 04.05.25 ¦ Final sag done 2 ¦ Indrajeet ¦ 42/0 ¦ 43/0 ¦ 0.489 ¦ 11.05.25 ¦ Final sag done 3 ¦ Indrajeet ¦ 49/0 ¦ 50/0 ¦ 0.241 ¦ 17.05.25 ¦ Final sag done 4 ¦ Indrajeet ¦ 48/0 ¦ 49/0 ¦ 1.162 ¦ 21.05.25 ¦ Final sag done 5 ¦ Indrajeet ¦ 43/0 ¦ 44/0 ¦ 2.856 ¦ Rought Sag Done | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Stringing - PKG-G | 82 | 17 | stringing | R4: S. No ¦ Section ¦ Paying Out ¦ Final Sag ¦ Name of Gang ¦ Remarks R5: From ¦ To ¦ Length ¦ Start Date ¦ Finish Date ¦ Month ¦ Start Date ¦ Finish Date ¦ Month R6: 1 ¦ 57/6 ¦ 58/0 ¦ 3.141 ¦ 06.05.2024 ¦ 10.05.24 ¦ 2024-05-24 00:00:00 ¦ 19.05.24 ¦ 24.05.24 ¦ 2024-05-24 00:00:00 ¦ GPJ Const. ¦ Final sag done ¦ 57/6 to 58/0 R7: 2 ¦ 57/0 ¦ 57/6 ¦ 2.344 ¦ 16.05.24 ¦ 24.05.24 ¦ 2024-05-24 00:00:00 ¦ 07.06.24 ¦ 12.06.24 ¦ 2024-06-24 00:00:00 ¦ GPJ Const. ¦ Final sag done ¦ 57/0 to 57/6 R8: 3 ¦ 56/0 ¦ 57/0 ¦ 4.127 ¦ 04.06.24 ¦ 12.06.24 ¦ 2024-06-24 00:00:00 ¦ 28.06.24 ¦ 04.07.24 ¦ 2024-07-24 00:00:00 ¦ GPJ Const. ¦ Final sag done ¦ 56/0 to 57/0 | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL STRINGING- PKG-G S. No ¦ Section ¦ Paying Out ¦ Final Sag ¦ Name of Gang ¦ Remarks From ¦ To ¦ Length ¦ Start Date ¦ Finish Date ¦ Month ¦ Start Date ¦ Finish Date ¦ Month 1 ¦ 57/6 ¦ 58/0 ¦ 3.141 ¦ 06.05.2024 ¦ 10.05.24 ¦ 2024-05-24 00:00:00 ¦ 19.05.24 ¦ 24.05.24 ¦ 2024-05-24 00:00:00 ¦ GPJ Const. ¦ Final sag done ¦ 57/6 to 58/0 2 ¦ 57/0 ¦ 57/6 ¦ 2.344 ¦ 16.05.24 ¦ 24.05.24 ¦ 2024-05-24 00:00:00 ¦ 07.06.24 ¦ 12.06.24 ¦ 2024-06-24 00:00:00 ¦ GPJ Const. ¦ Final sag done ¦ 57/0 to 57/6 3 ¦ 56/0 ¦ 57/0 ¦ 4.127 ¦ 04.06.24 ¦ 12.06.24 ¦ 2024-06-24 00:00:00 ¦ 28.06.24 ¦ 04.07.24 ¦ 2024-07-24 00:00:00 ¦ GPJ Const. ¦ Final sag done ¦ 56/0 to 57/0 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | OPGW PKG-G | 39 | 14 | opgw_accessories, stringing, summary_status | R4: Sr. No ¦ Section ¦ Section length in Kms ¦ OPGW Drum Length (In KMs) ¦ Start date ¦ End date ¦ Splicing ¦ Jointing Details ¦ Agency ¦ OTDR reading status ¦ Splicing done by ¦ Remarks R5: 1 ¦ 51/0 ¦ 52/0 ¦ 4.403 ¦ 4.653 ¦ 11.01.25 ¦ 12.01.25 ¦ Congent tech ¦ Final sag completed ¦ 51/0 to 52/0 R6: 2 ¦ 52/0 ¦ 55/0 ¦ 4.377 ¦ 4.627 ¦ 17.01.25 ¦ 18.01.25 ¦ Congent tech ¦ Final sag completed ¦ 52/0 to 55/0 R7: 3 ¦ 55/0 ¦ 56/0 ¦ 4.9 ¦ 5.16 ¦ 20.01.25 ¦ 21.01.25 ¦ Done ¦ Congent tech ¦ Rakesh ¦ Final sag completed ¦ 55/0 to 56/0 R8: 4 ¦ 56/0 ¦ 57/0 ¦ 4.127 ¦ 4.372 ¦ 23.01.25 ¦ 24.01.25 ¦ Done ¦ Congent tech ¦ Rakesh ¦ Final sag completed ¦ 56/0 to 57/0 | EXECUTING AGENCY : M/s. KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL OPGW Progress details(Pkg-G) Sr. No ¦ Section ¦ Section length in Kms ¦ OPGW Drum Length (In KMs) ¦ Start date ¦ End date ¦ Splicing ¦ Jointing Details ¦ Agency ¦ OTDR reading status ¦ Splicing done by ¦ Remarks 1 ¦ 51/0 ¦ 52/0 ¦ 4.403 ¦ 4.653 ¦ 11.01.25 ¦ 12.01.25 ¦ Congent tech ¦ Final sag completed ¦ 51/0 to 52/0 2 ¦ 52/0 ¦ 55/0 ¦ 4.377 ¦ 4.627 ¦ 17.01.25 ¦ 18.01.25 ¦ Congent tech ¦ Final sag completed ¦ 52/0 to 55/0 3 ¦ 55/0 ¦ 56/0 ¦ 4.9 ¦ 5.16 ¦ 20.01.25 ¦ 21.01.25 ¦ Done ¦ Congent tech ¦ Rakesh ¦ Final sag completed ¦ 55/0 to 56/0 4 ¦ 56/0 ¦ 57/0 ¦ 4.127 ¦ 4.372 ¦ 23.01.25 ¦ 24.01.25 ¦ Done ¦ Congent tech ¦ Rakesh ¦ Final sag completed ¦ 56/0 to 57/0 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | OPGW PKG-F | 21 | 13 | opgw_accessories, stringing, summary_status | R4: Sr. No ¦ Section ¦ Section length in Kms ¦ OPGW Drum Length (In KMs) ¦ Start date ¦ End date ¦ Splicing ¦ Jointing Details ¦ Agency ¦ OTDR reading status ¦ Splicing done by ¦ Remarks R5: 1 ¦ 59/0 ¦ 59/8 ¦ 3.337 ¦ 10.02.25 ¦ 11.02.25 ¦ 05.03.25 ¦ Congent tech ¦ Revant Sharma ¦ Final Sag Complete R6: 2 ¦ 59/8 ¦ 60/0 ¦ 3.778 ¦ 12.02.25 ¦ 13.02.25 ¦ 26.02.25 ¦ Congent tech ¦ Revant Sharma ¦ Final Sag Complete R7: 3 ¦ 60/0 ¦ 61/0 ¦ 4.877 ¦ 15.02.25 ¦ 16.02.25 ¦ Congent tech ¦ Final Sag Complete R8: 4 ¦ 61/0 ¦ 62/0 ¦ 4.568 ¦ 19.02.25 ¦ 19.02.25 ¦ 27.02.25 ¦ Congent tech ¦ Revant Sharma ¦ Final Sag Complete | EXECUTING AGENCY : M/s. KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL OPGW Progress details(PKG-F) Sr. No ¦ Section ¦ Section length in Kms ¦ OPGW Drum Length (In KMs) ¦ Start date ¦ End date ¦ Splicing ¦ Jointing Details ¦ Agency ¦ OTDR reading status ¦ Splicing done by ¦ Remarks 1 ¦ 59/0 ¦ 59/8 ¦ 3.337 ¦ 10.02.25 ¦ 11.02.25 ¦ 05.03.25 ¦ Congent tech ¦ Revant Sharma ¦ Final Sag Complete 2 ¦ 59/8 ¦ 60/0 ¦ 3.778 ¦ 12.02.25 ¦ 13.02.25 ¦ 26.02.25 ¦ Congent tech ¦ Revant Sharma ¦ Final Sag Complete 3 ¦ 60/0 ¦ 61/0 ¦ 4.877 ¦ 15.02.25 ¦ 16.02.25 ¦ Congent tech ¦ Final Sag Complete 4 ¦ 61/0 ¦ 62/0 ¦ 4.568 ¦ 19.02.25 ¦ 19.02.25 ¦ 27.02.25 ¦ Congent tech ¦ Revant Sharma ¦ Final Sag Complete | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Crossing | 21 | 19 | statutory_crossing, summary_status | R2: Sl No ¦ Crossing Name ¦ PART - G ¦ PART - F R3: Section ¦ Owner Name ¦ Date of Submission ¦ Date of Site Inspection ¦ Proposal Status ¦ Remarks ¦ Section ¦ Owner Name ¦ Date of Submission ¦ Date of Site Inspection ¦ Proposal Status ¦ Remarks R4: From ¦ To ¦ From ¦ To R13: 2 ¦ Bharatmala Expressway (Amritsar - Kandla) ¦ AP 49 ¦ AP 50 ¦ NHAI ¦ 2023-11-13 00:00:00 ¦ Approved on dated - 01.06.24 ¦ AP 58 ¦ AP 59 ¦ NHAI ¦ 2024-01-21 00:00:00 ¦ Approved on dated - 01.06.24 R15: 4 ¦ NH 25 (Jodhpur - Barmer) ¦ AP 62 ¦ AP 63 ¦ NHAI ¦ 2023-12-06 00:00:00 ¦ Approved on dated - 24.06.24 ¦ AP 68 ¦ AP 69 ¦ NHAI ¦ 2024-02-13 00:00:00 ¦ Approved on dated - 24.06.24 | CROSSING DETAILS FOR 765 KV DC FATEHGARH 3 - BEAWAR T/L (Part-G & Part-F) Sl No ¦ Crossing Name ¦ PART - G ¦ PART - F Section ¦ Owner Name ¦ Date of Submission ¦ Date of Site Inspection ¦ Proposal Status ¦ Remarks ¦ Section ¦ Owner Name ¦ Date of Submission ¦ Date of Site Inspection ¦ Proposal Status ¦ Remarks From ¦ To ¦ From ¦ To A ¦ Power Line 1 ¦ 400 KV D/C Rajwest - Jodhpur Line ¦ AP 36 ¦ AP 37 ¦ RRVPNL ¦ Hard copy submitted on - 08/03/24. ¦ AP 46 ¦ AP 47 ¦ RRVPNL ¦ 2 days ¦ 5,5,5,5 2 ¦ U/C LILO of 400 KV D/C Rajwest - Jodhpur Line at Newai S/S ¦ AP 45 ¦ AP 46 ¦ RRVPNL ¦ 2023-12-25 00:00:00 ¦ Hard copy submitted on - 10/01/24. ¦ AP 56 ¦ AP 57 ¦ RRVPNL ¦ 1week 3 ¦ 220 KV S/C GSS Boranada - Balotra Line ¦ AP 60 ¦ AP 61 ¦ RRVPNL ¦ 2023-11-13 00:00:00 ¦ Approved on dated 18.07.24 ¦ AP 66 ¦ AP 67 ¦ RRVPNL ¦ 2024-02-13 00:00:00 ¦ Approved on dated 18.07.24 | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Visual Chart (Pkg -F.) | 167 | 48 | earthing_tack, erection, foundation, row_hindrance, stringing, summary_status, visual_l2 | R4: LEGEND: ¦ Summary ¦ 2025-12-26 00:00:00 R5: Tree Felling Done. Front Clear For Stringing ¦ SR. NO. ¦ ACTIVITY ¦ UNIT ¦ As per Tower Schedule ¦ TOTAL COMPLETED ¦ BALANCE ¦ Earthng ¦ Foundation ¦ Erection R9: EREC. U/P ¦ Total ¦ Fdn Complete ¦ Balance ¦ Total ¦ Complete ¦ Balance R10: EREC. COMP. ¦ SPAN ¦ SPAN ¦ PIT EXCAV. U/P ¦ 1 ¦ Foundation ¦ Nos. ¦ 223 ¦ 221 ¦ 2 R12: Tack Welding ¦ BENCHING U/P ¦ 2 ¦ Earthing ¦ Nos. ¦ 223 ¦ 219 ¦ 4 | PKG-F, Section-II Executing Agency ¦ KEC International Limited Project ¦ Fatehgarh-3-Beawar 765kV D/C (2nd) Transmission Line Section 1 & 2 (PKG-F Section -II) LEGEND: ¦ Summary ¦ 2025-12-26 00:00:00 Tree Felling Done. Front Clear For Stringing ¦ SR. NO. ¦ ACTIVITY ¦ UNIT ¦ As per Tower Schedule ¦ TOTAL COMPLETED ¦ BALANCE ¦ Earthng ¦ Foundation ¦ Erection Stringing WIP ¦ STRINGING COMPLETED Loc No ¦ P: Prvate Loc EREC. U/P ¦ Total ¦ Fdn Complete ¦ Balance ¦ Total ¦ Complete ¦ Balance | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Clear locs shared by client | 51 | 13 | erection, row_hindrance, summary_status | R5: SL No. ¦ Location (G) ¦ Current Status ¦ SL No. ¦ Location(F) ¦ Current Status R27: 22 ¦ 40/2 ¦ Untouch ¦ 22 ¦ 59/0 ¦ Materials shifting wip (Jirwa Devi) | Erection Workfront_shared by SPTL Section II_29.11.2024 SL No. ¦ Location (G) ¦ Current Status ¦ SL No. ¦ Location(F) ¦ Current Status 1 ¦ 33/1 ¦ Untouch ¦ 1 ¦ 47/2 ¦ Untouch ¦ 33/8 2 ¦ 35/0 ¦ Untouch ¦ 2 ¦ 47/3 ¦ Untouch 3 ¦ 35/1 ¦ Untouch ¦ 3 ¦ 47/5 ¦ Untouch 4 ¦ 35/2 ¦ Untouch ¦ 4 ¦ 47/6 ¦ Untouch 5 ¦ 35/3 ¦ Untouch ¦ 5 ¦ 47/7 ¦ Untouch 6 ¦ 35/4 ¦ Untouch ¦ 6 ¦ 47/8 ¦ Untouch | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Visual Chart PKG-G | 367 | 37 | earthing_tack, erection, foundation, row_hindrance, stringing, summary_status, supply, visual_l2 | R4: LEGEND: ¦ Summary ¦ 2025-12-26 00:00:00 R5: Tree Felling Done. Front Clear For Stringing ¦ SR. NO. ¦ ACTIVITY ¦ UNIT ¦ As per Tower Schedule ¦ TOTAL COMPLETED ¦ BALANCE ¦ Earthng ¦ Foundation ¦ Erection R9: EREC. U/P ¦ Total ¦ Fdn Complete ¦ Balance ¦ Total ¦ Complete ¦ Balance R10: EREC. COMP. ¦ SPAN ¦ SPAN ¦ 1 ¦ Foundation ¦ Nos. ¦ 521 ¦ 520 ¦ 1 R12: Tack Welding ¦ 2 ¦ Earthing ¦ Nos. ¦ 521 ¦ 501 ¦ 20 | PKG-G, Section-II Executing Agency ¦ International Limited Project ¦ Fatehgarh-3-Beawar 765kV D/C (2nd) Transmission Line Section 1 & 2 (Hexa AL59 Zebra Conductor) LEGEND: ¦ Summary ¦ 2025-12-26 00:00:00 Tree Felling Done. Front Clear For Stringing ¦ SR. NO. ¦ ACTIVITY ¦ UNIT ¦ As per Tower Schedule ¦ TOTAL COMPLETED ¦ BALANCE ¦ Earthng ¦ Foundation ¦ Erection Stringing WIP ¦ STRINGING COMPLETED Loc No ¦ P: Prvate Loc EREC. U/P ¦ Total ¦ Fdn Complete ¦ Balance ¦ Total ¦ Complete ¦ Balance | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Sheet3 | 1 | 1 |  |  |  | ok
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | 2025-12-25 | Sheet2 | 1 | 1 |  |  |  | ok
TB 408 | TB 408 - DPR - 2026-05-11.xlsx | 2026-05-11 | Project Details | 21 | 11 | project_details | R1: Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer/Manager ¦ PCH ¦ Regional Manager ¦ Project Manager ¦ Section Incharge ¦ Supervisor | Project Code ¦ Project Name ¦ Client Name ¦ NOA Start Date ¦ LOA End Date ¦ Planning Engineer/Manager ¦ PCH ¦ Regional Manager ¦ Project Manager ¦ Section Incharge ¦ Supervisor TB-408 ¦ 765 KV Fathegarh -3 Beawer Transmission Line, PKG F ¦ Resonia Limited ¦ 2023-12-06 00:00:00 ¦ 2025-10-30 00:00:00 ¦ Mr. Raghav Ranjan ¦ Mr. N. K. Gupta ¦ Mr. Rajnish Pandey ¦ Mr. Virendra Gupta ¦ Dev Saran Swarakar ¦ Ganesh Singh Mr. Dhiraj Adhikari ¦ Rajeev Kumar ¦ Umesh Prashad Vivek Shukla ¦ Rajesh Paul Ram Tirath Singh ¦ Aslam Ansari Jitendra Saini ¦ Lal Babu Patel V Challe Durai Vimal Chandra | repaired_defined_names (ValueError)
TB 408 | TB 408 - DPR - 2026-05-11.xlsx | 2026-05-11 | Erection Compiled | 486 | 48 | erection, project_details, summary_status | R1: SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Tower Tightening ¦ Remark R2: 1 ¦ 1/0 ¦ DD60+0 ¦ DRY ¦ 2025-07-07 00:00:00 ¦ 86.129279 ¦ COMPLETED ¦ 2025-08-20 00:00:00 ¦ Bhairo Mahto+Kewat ¦ Yes R3: 2 ¦ 1A/0 ¦ DD60+0 ¦ DRY ¦ 2025-07-01 00:00:00 ¦ 86.129279 ¦ COMPLETED ¦ 2025-07-29 00:00:00 ¦ Bhairo Mahto+Priyanka Devi (Subodh) ¦ Yes R4: 3 ¦ 1A/1 ¦ DA+6 ¦ DFR ¦ 2025-01-31 00:00:00 ¦ 45.413028000000004 ¦ COMPLETED ¦ 2025-02-10 00:00:00 ¦ Bina Devi ¦ Yes R5: 4 ¦ 1A/2 ¦ DA+0 ¦ DRY ¦ 2025-02-11 00:00:00 ¦ 37.504372000000004 ¦ COMPLETED ¦ 2025-02-18 00:00:00 ¦ Bina Devi ¦ Yes | SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Number of Fitters ¦ Tower Tightening ¦ Remark 1 ¦ 1/0 ¦ DD60+0 ¦ DRY ¦ 2025-07-07 00:00:00 ¦ 86.129279 ¦ COMPLETED ¦ 2025-08-20 00:00:00 ¦ Bhairo Mahto+Kewat ¦ Yes 2 ¦ 1A/0 ¦ DD60+0 ¦ DRY ¦ 2025-07-01 00:00:00 ¦ 86.129279 ¦ COMPLETED ¦ 2025-07-29 00:00:00 ¦ Bhairo Mahto+Priyanka Devi (Subodh) ¦ Yes 3 ¦ 1A/1 ¦ DA+6 ¦ DFR ¦ 2025-01-31 00:00:00 ¦ 45.413028000000004 ¦ COMPLETED ¦ 2025-02-10 00:00:00 ¦ Bina Devi ¦ Yes 4 ¦ 1A/2 ¦ DA+0 ¦ DRY ¦ 2025-02-11 00:00:00 ¦ 37.504372000000004 ¦ COMPLETED ¦ 2025-02-18 00:00:00 ¦ Bina Devi ¦ Yes 5 ¦ 1A/3 ¦ DA+0 ¦ DRY ¦ 2025-02-19 00:00:00 ¦ 37.504372000000004 ¦ COMPLETED ¦ 2025-02-28 00:00:00 ¦ Bina Devi ¦ Yes 6 ¦ 1A/4 ¦ DA+3 ¦ DFR ¦ 2025-05-10 00:00:00 ¦ 38.84760599999999 ¦ COMPLETED ¦ 2025-06-11 00:00:00 ¦ Bhairo Mahto ¦ Yes 7 ¦ 1A/5 ¦ DA+0 ¦ DRY ¦ 2025-07-10 00:00:00 ¦ 37.504372000000004 ¦ COMPLETED ¦ 2025-07-26 00:00:00 ¦ Bhairo Mahto+Kewat ¦ Yes | repaired_defined_names (ValueError)
TB 408 | TB 408 - DPR - 2026-05-11.xlsx | 2026-05-11 | Stringing Compiled | 93 | 24 | project_details, stretch_readiness, stringing, summary_status, supply | R3: S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos. ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name R4: Section-1 ¦ Gty ¦ 1/0 ¦ 1/0 ¦ 0.122 ¦ M ¦ Ready ¦ Completed ¦ 2026-03-27 00:00:00 ¦ 2026-03-30 00:00:00 ¦ 0.122 ¦ 2026-03-27 00:00:00 ¦ 2026-03-30 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 0.122 ¦ Completed ¦ Devi Power R5: Section-1 ¦ 1/0 ¦ 1A/0 ¦ 1A/0 ¦ 0.09 ¦ M ¦ Ready ¦ Completed ¦ 2026-03-24 00:00:00 ¦ 2026-03-31 00:00:00 ¦ 0.09 ¦ 2026-03-24 00:00:00 ¦ 2026-03-31 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 0.09 ¦ Completed ¦ Devi Power R6: Section-1 ¦ 1A/0 ¦ 2/0 ¦ 1/1, 1/2, 1/3, 1/4, 1/5, 1/6, 1/7, 1/8, 2/0 ¦ 3.426 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-11-21 00:00:00 ¦ 2025-11-28 00:00:00 ¦ 3.426 ¦ 2025-11-28 00:00:00 ¦ 2025-11-30 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 3.426 ¦ Completed ¦ Devi Power R7: Section-1 ¦ 2/0 ¦ 3/0 ¦ 2/1, 2/2, 2/3, 2/4, 2/5, 2/6, 2/7, 2/8, 2/9, 3/0 ¦ 3.8236 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-11-13 00:00:00 ¦ 2025-11-18 00:00:00 ¦ 3.8236 ¦ 2025-12-30 00:00:00 ¦ 2026-01-14 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 3.8236 ¦ Completed ¦ Devi Power | Number of TSE S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos. ¦ Span (M) ¦ Method ¦ Section Readiness ¦ Insulator Hoisting ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Spacering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name Section-1 ¦ Gty ¦ 1/0 ¦ 1/0 ¦ 0.122 ¦ M ¦ Ready ¦ Completed ¦ 2026-03-27 00:00:00 ¦ 2026-03-30 00:00:00 ¦ 0.122 ¦ 2026-03-27 00:00:00 ¦ 2026-03-30 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 0.122 ¦ Completed ¦ Devi Power Section-1 ¦ 1/0 ¦ 1A/0 ¦ 1A/0 ¦ 0.09 ¦ M ¦ Ready ¦ Completed ¦ 2026-03-24 00:00:00 ¦ 2026-03-31 00:00:00 ¦ 0.09 ¦ 2026-03-24 00:00:00 ¦ 2026-03-31 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 0.09 ¦ Completed ¦ Devi Power Section-1 ¦ 1A/0 ¦ 2/0 ¦ 1/1, 1/2, 1/3, 1/4, 1/5, 1/6, 1/7, 1/8, 2/0 ¦ 3.426 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-11-21 00:00:00 ¦ 2025-11-28 00:00:00 ¦ 3.426 ¦ 2025-11-28 00:00:00 ¦ 2025-11-30 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 3.426 ¦ Completed ¦ Devi Power Section-1 ¦ 2/0 ¦ 3/0 ¦ 2/1, 2/2, 2/3, 2/4, 2/5, 2/6, 2/7, 2/8, 2/9, 3/0 ¦ 3.8236 ¦ TSE ¦ Ready ¦ Completed ¦ 2025-11-13 00:00:00 ¦ 2025-11-18 00:00:00 ¦ 3.8236 ¦ 2025-12-30 00:00:00 ¦ 2026-01-14 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 3.8236 ¦ Completed ¦ Devi Power Section-1 ¦ 3/0 ¦ 4/0 ¦ 4/0 ¦ 0.227 ¦ M ¦ Ready ¦ Completed ¦ 2026-01-10 00:00:00 ¦ 2026-01-16 00:00:00 ¦ 0.227 ¦ 2026-01-11 00:00:00 ¦ 2026-01-16 00:00:00 ¦ Completed ¦ Completed ¦ 0.227 ¦ Completed ¦ Gopal Associate, Hotline Section-1 ¦ 4/0 ¦ 5/0 ¦ 4/1, 4/2, 4/3, 4/4, 5/0 ¦ 1.8731 ¦ TSE ¦ Ready ¦ Balance ¦ Balance | repaired_defined_names (ValueError)
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | Detail Survey-220kV | 648 | 26 | project_details, summary_status, survey_soil | R3: Sl. No. ¦ LOC NO ¦ TowerType ¦ Deviation of Angle ¦ CP ¦ Leg Extension ¦ RC ¦ Chimney Extension ¦ Span Length (m) ¦ Section Length ¦ Detail Survey completion status ¦ Detail Survey Report Submision ¦ Detail Survey Approval ¦ Remarks R4: DMS ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ m ¦ Surveyed ¦ DOC ¦ Re-survey ¦ Submitted ¦ Date ¦ Re-submitted ¦ Approved R5: GANTRY ¦ GANTRY ¦ Completed R7: 1 ¦ 0/0 ¦ DD+0 ¦ 16° 50' 9"RT ¦ 126.19 ¦ Completed R9: 2 ¦ 0/1 ¦ DA+3 ¦ Completed | 220kV - Detailed Survey Progress Sl. No. ¦ LOC NO ¦ TowerType ¦ Deviation of Angle ¦ CP ¦ Leg Extension ¦ RC ¦ Chimney Extension ¦ Span Length (m) ¦ Section Length ¦ Detail Survey completion status ¦ Detail Survey Report Submision ¦ Detail Survey Approval ¦ Remarks DMS ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ m ¦ Surveyed ¦ DOC ¦ Re-survey ¦ Submitted ¦ Date ¦ Re-submitted ¦ Approved GANTRY ¦ GANTRY ¦ Completed 126.19 ¦ Completed 1 ¦ 0/0 ¦ DD+0 ¦ 16° 50' 9"RT ¦ 126.19 ¦ Completed 292 ¦ Completed 2 ¦ 0/1 ¦ DA+3 ¦ Completed | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | Check Survey-220kV | 646 | 28 | project_details, summary_status, survey_soil | R3: Sl. No. ¦ LOC NO ¦ TowerType ¦ Deviation of Angle ¦ CP ¦ Leg Extension ¦ RC ¦ Chimney Extension ¦ Span Length (m) ¦ Section Length ¦ Detail Survey completion status ¦ Detail Survey Report Submision ¦ Detail Survey Approval ¦ Remarks R4: DMS ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ m ¦ Surveyed ¦ DOC ¦ Re-survey ¦ Submitted ¦ Date ¦ Re-submitted ¦ Approved R75: 34 ¦ 5/0 ¦ DB+6 ¦ 11° 47' 59"RT ¦ Completed ¦ 2024-08-28 00:00:00 ¦ Approved R76: 383 ¦ Completed ¦ 2024-08-28 00:00:00 ¦ Approved R77: 35 ¦ 5/1 ¦ DB+3 ¦ 383 ¦ Completed ¦ 2024-08-28 00:00:00 ¦ Approved | Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc 220kV - Check Survey Progress Sl. No. ¦ LOC NO ¦ TowerType ¦ Deviation of Angle ¦ CP ¦ Leg Extension ¦ RC ¦ Chimney Extension ¦ Span Length (m) ¦ Section Length ¦ Detail Survey completion status ¦ Detail Survey Report Submision ¦ Detail Survey Approval ¦ Remarks DMS ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ m ¦ Surveyed ¦ DOC ¦ Re-survey ¦ Submitted ¦ Date ¦ Re-submitted ¦ Approved GANTRY ¦ GANTRY 47 1 ¦ 0/0 ¦ DD+0 ¦ 16° 50' 9"RT ¦ 126.19 196 | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | Detail Survey-132kV | 331 | 26 | project_details, summary_status, survey_soil | R3: Sl. No. ¦ LOC NO ¦ TowerType ¦ Deviation of Angle ¦ CP ¦ Leg Extension ¦ RC ¦ Chimney Extension ¦ Span Length (m) ¦ Section Length ¦ Detail Survey completion status ¦ Detail Survey Report Submision ¦ Detail Survey Approval ¦ Remarks R4: DMS ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ m ¦ Surveyed ¦ DOC ¦ Re-survey ¦ Submitted ¦ Date ¦ Re-submitted ¦ Approved R5: Tapping Tower ¦ DD+0 ¦ 2° 10' 33"LT ¦ Completed R7: 1 ¦ DE ¦ DD+0 ¦ 44° 51' 5"RT ¦ 25.92 ¦ Completed R9: 2 ¦ 1/0 ¦ DB+0 ¦ 6° 49' 55"RT ¦ 261.99 ¦ Completed | Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc 132kV - Detailed Survey Progress Sl. No. ¦ LOC NO ¦ TowerType ¦ Deviation of Angle ¦ CP ¦ Leg Extension ¦ RC ¦ Chimney Extension ¦ Span Length (m) ¦ Section Length ¦ Detail Survey completion status ¦ Detail Survey Report Submision ¦ Detail Survey Approval ¦ Remarks DMS ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ m ¦ Surveyed ¦ DOC ¦ Re-survey ¦ Submitted ¦ Date ¦ Re-submitted ¦ Approved Tapping Tower ¦ DD+0 ¦ 2° 10' 33"LT ¦ Completed 25.917 ¦ Completed 1 ¦ DE ¦ DD+0 ¦ 44° 51' 5"RT ¦ 25.92 ¦ Completed 261.985 ¦ Completed | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | Check Survey-132kV | 122 | 26 | project_details, summary_status, survey_soil | R3: Sl. No. ¦ LOC NO ¦ TowerType ¦ Deviation of Angle ¦ CP ¦ Leg Extension ¦ RC ¦ Chimney Extension ¦ Span Length (m) ¦ Section Length ¦ Detail Survey completion status ¦ Detail Survey Report Submision ¦ Detail Survey Approval ¦ Remarks R4: DMS ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ m ¦ Surveyed ¦ DOC ¦ Re-survey ¦ Submitted ¦ Date ¦ Re-submitted ¦ Approved R18: #REF! ¦ 5/0 ¦ DD+3 ¦ 488.63 ¦ Completed ¦ Approved R19: 40 ¦ Completed ¦ Approved R20: #REF! ¦ 5/1 ¦ GANTRY UC (+2M) ¦ 40 ¦ Completed ¦ Approved | Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc 220kV - Check Survey Progress Sl. No. ¦ LOC NO ¦ TowerType ¦ Deviation of Angle ¦ CP ¦ Leg Extension ¦ RC ¦ Chimney Extension ¦ Span Length (m) ¦ Section Length ¦ Detail Survey completion status ¦ Detail Survey Report Submision ¦ Detail Survey Approval ¦ Remarks DMS ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ A ¦ B ¦ C ¦ D ¦ m ¦ m ¦ Surveyed ¦ DOC ¦ Re-survey ¦ Submitted ¦ Date ¦ Re-submitted ¦ Approved GANTRY ¦ GANTRY #REF! ¦ 1/0 ¦ DE+0 ¦ 42° 49' 3"RT ¦ 699.9200000000001 230.15 #REF! ¦ 2/0 ¦ DB+0 ¦ 27° 13' 43"RT ¦ 356.66 | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | Summary | 31 | 43 | earthing_tack, erection, foundation, project_details, summary_status, survey_soil, visual_l2 | R2: Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc ¦ Contractual Start Date : ¦ 2024-06-06 00:00:00 R3: Name of Document : Daily Progress Report (DPR) ¦ Contractual Completion Date: ¦ 2025-05-25 00:00:00 R4: Office: Neemuch ¦ Revised Completion Date : ¦ 2026-06-15 00:00:00 R5: Progress of 220kV Line ¦ Date: ¦ 2026-05-20 00:00:00 R6: Sr. No. ¦ Activity ¦ UoM ¦ Total Quantity ¦ As per L2 ¦ Cumm. Progress up to last Month ¦ Progress of Current Month (May'26) ¦ Cumulative till current month ¦ Resources Status ¦ Critical Issues, if any & Remark | Client: M/S STERLITE POWER TRANSMISSION LIMITED Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc ¦ Contractual Start Date : ¦ 2024-06-06 00:00:00 Name of Document : Daily Progress Report (DPR) ¦ Contractual Completion Date: ¦ 2025-05-25 00:00:00 Office: Neemuch ¦ Revised Completion Date : ¦ 2026-06-15 00:00:00 Progress of 220kV Line ¦ Date: ¦ 2026-05-20 00:00:00 Sr. No. ¦ Activity ¦ UoM ¦ Total Quantity ¦ As per L2 ¦ Cumm. Progress up to last Month ¦ Progress of Current Month (May'26) ¦ Cumulative till current month ¦ Resources Status ¦ Critical Issues, if any & Remark Start Date ¦ End Date ¦ L2 ¦ Actual ¦ Plan ¦ Today ¦ Progress in Month ¦ Target (L2) ¦ Completed ¦ Balance ¦ Targeted Gang ¦ Available Gang ¦ Shortfall Gang 1 ¦ Detailed Survey ¦ Kms ¦ 64 ¦ 2024-06-18 00:00:00 ¦ 2024-08-31 00:00:00 ¦ 64 ¦ 64.178 ¦ 64 ¦ 64.178 ¦ -0.17799999999999727 | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | Statutory | 38 | 19 | statutory_crossing | R2: SI No ¦ Name of Existing Line/Croccing ¦ Name of the owner of existing line ¦ Crossing Type ¦ Existing Crossing Span (M) ¦ Existing Tower/K MP No ¦ AP ¦ Tower Type ¦ RC if any ¦ Crossing Angle ¦ Crossing Span Length ¦ Electrical Clearance ¦ Proposal Preparation ¦ Proposal Submission to Sterlite on ¦ Submission to concerned office ¦ Joint site inspection ¦ Submission of charges (if any) ¦ NOC Recei R4: 1 ¦ NH-27 ¦ NHAI ¦ NH ¦ 1B/0-1C/0 ¦ 1B/0(DD+3)-1C/0(DD+3) ¦ - ¦ 248 R5: 2 ¦ NH-27 ¦ NHAI ¦ NH ¦ 3/0-4/0 ¦ 3/0(DD+3)-4/0(DB+9) ¦ - ¦ 229.73 R6: 3 ¦ 220KV S/C LINE ¦ PGCIL ¦ PLC ¦ 179-180 ¦ 24/0-25/0 ¦ 24/0(DD+9)-25/0(DD+18) ¦ 3M & 2M ¦ 190.52 R7: 4 ¦ 220KV D/C RPB-CGH LINE ¦ PGCIL ¦ PLC ¦ 179-180 ¦ 26/0-27/0 ¦ 26/0(DD+18)-27/0(DD+18) ¦ 3M & 0M ¦ 142.38 | Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc SI No ¦ Name of Existing Line/Croccing ¦ Name of the owner of existing line ¦ Crossing Type ¦ Existing Crossing Span (M) ¦ Existing Tower/K MP No ¦ AP ¦ Tower Type ¦ RC if any ¦ Crossing Angle ¦ Crossing Span Length ¦ Electrical Clearance ¦ Proposal Preparation ¦ Proposal Submission to Sterlite on ¦ Submission to concerned office ¦ Joint site inspection ¦ Submission of charges (if any) ¦ NOC Received on ¦ Remarks Statutory/Crossing Tracker - 220KV D/C Line 1 ¦ NH-27 ¦ NHAI ¦ NH ¦ 1B/0-1C/0 ¦ 1B/0(DD+3)-1C/0(DD+3) ¦ - ¦ 248 2 ¦ NH-27 ¦ NHAI ¦ NH ¦ 3/0-4/0 ¦ 3/0(DD+3)-4/0(DB+9) ¦ - ¦ 229.73 3 ¦ 220KV S/C LINE ¦ PGCIL ¦ PLC ¦ 179-180 ¦ 24/0-25/0 ¦ 24/0(DD+9)-25/0(DD+18) ¦ 3M & 2M ¦ 190.52 4 ¦ 220KV D/C RPB-CGH LINE ¦ PGCIL ¦ PLC ¦ 179-180 ¦ 26/0-27/0 ¦ 26/0(DD+18)-27/0(DD+18) ¦ 3M & 0M ¦ 142.38 5 ¦ 400KV T/L ¦ PLC ¦ 28/1-28/2 ¦ 28/1(Gantry)-28/2(Gantry) ¦ - ¦ 44 | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | Progress-132kV | 93 | 53 | earthing_tack, foundation, summary_status, supply | R3: 220 KV D/C Neemuch - TS ¦ Foundation ¦ Earthing R4: Sl. No. ¦ LOC NO ¦ Tower Type ¦ Tower Weight ¦ Stub Weight ¦ Chimney Extension ¦ Span Length(m) ¦ Classification ¦ Excavation Volume (m3) ¦ Concreting Volume ¦ 8mm Steel ¦ 10mm Steel ¦ 12mm Steel ¦ 16mm Steel ¦ 20mm Steel ¦ 25mmSteel ¦ Total Steel (MT) ¦ Status (C/WIP) ¦ Excavation ¦ Concreting | Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc Progress of 220kV Line 220 KV D/C Neemuch - TS ¦ Foundation ¦ Earthing Sl. No. ¦ LOC NO ¦ Tower Type ¦ Tower Weight ¦ Stub Weight ¦ Chimney Extension ¦ Span Length(m) ¦ Classification ¦ Excavation Volume (m3) ¦ Concreting Volume ¦ 8mm Steel ¦ 10mm Steel ¦ 12mm Steel ¦ 16mm Steel ¦ 20mm Steel ¦ 25mmSteel ¦ Total Steel (MT) ¦ Status (C/WIP) ¦ Excavation ¦ Concreting HT ¦ MS ¦ BnA ¦ Total ¦ HT ¦ MS ¦ BnA ¦ Total ¦ A ¦ B ¦ C ¦ D ¦ m ¦ M10 (1:3:6) (m3) ¦ M20 (1:1.5:3) (m3) ¦ Total ¦ DOS ¦ DOC ¦ DOS ¦ DOC Existing Tower Sc-5 ¦ DD+9(220KV) 1 ¦ SC-4 ¦ DD+9 (220KV) ¦ 11.987 ¦ 47.948 ¦ 383.584 ¦ 6.058 ¦ 5.874 ¦ 0.0077 ¦ 0.563 ¦ 12.502699999999999 ¦ 0.557 ¦ 0.01 ¦ 0.5670000000000001 ¦ DFR ¦ 119.36 ¦ 2.05 ¦ 18.37 ¦ 20.42 ¦ 157.16420000000002 | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | Progress-220kV | 413 | 68 | foundation, summary_status, supply | R4: 220 KV D/C Neemuch - TS ¦ RC Portion ¦ Tower Weight ¦ Stub Weight ¦ Foundation R6: Sl. No. ¦ LOC NO ¦ Tower Type ¦ A ¦ B ¦ C ¦ D ¦ HT ¦ MS ¦ pack Washar ¦ BnA ¦ Total Tower Weight ¦ HT ¦ BnA ¦ Total Stub Weight ¦ Deviation of Angle ¦ State ¦ Span Length(m) ¦ Classification ¦ Excavation Volume (m3) | 280.91600000000034 ¦ 2556.3350000000005 ¦ 2837.2509999999966 ¦ 19254.080599999983 ¦ 850780.4699999997 ¦ 16158.36999999998 ¦ 75630.58000000002 ¦ 33623.100000000006 ¦ 34567.34999999993 ¦ 14833.600000000008 ¦ 3104.4 ¦ 177917.4000000003 ¦ 177.82742999999996 Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc Progress of 220kV Line 220 KV D/C Neemuch - TS ¦ RC Portion ¦ Tower Weight ¦ Stub Weight ¦ Foundation 1367.3216000000032 ¦ 72.17300000000009 ¦ 64047.148999999976 ¦ 17952.97 ¦ 280.91600000000034 ¦ 2556.3350000000005 ¦ 2837.2509999999966 ¦ 19254.080599999983 ¦ 179.18973999999994 Sl. No. ¦ LOC NO ¦ Tower Type ¦ A ¦ B ¦ C ¦ D ¦ HT ¦ MS ¦ pack Washar ¦ BnA ¦ Total Tower Weight ¦ HT ¦ BnA ¦ Total Stub Weight ¦ Deviation of Angle ¦ State ¦ Span Length(m) ¦ Classification ¦ Excavation Volume (m3) B2B ¦ B2B x 4 ¦ Barbed Wire ¦ RC Portion ¦ MT ¦ MT ¦ MT ¦ MT ¦ MT ¦ MT ¦ MT ¦ MT ¦ DMS ¦ m ¦ M10 (1:3:6) (m3) ¦ M20 (1:1.5:3) (m3) ¦ Total ¦ nos of bags ¦ in kg ¦ 8mm GANTRY ¦ GANTRY ¦ 13 ¦ 70.93 ¦ 1040.06 ¦ 98.08 ¦ 153.24 ¦ 1362.31 ¦ 1.36231 | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing-220kV | 231 | 25 | opgw_accessories, stretch_readiness, stringing, summary_status, supply | R2: Progress of 220kV Line ¦ Stringing Progress (Conductor & Earthwire) ¦ OPGW Progress R3: Stringing Section ¦ 2026-05-20 00:00:00 ¦ 61.199262999999995 ¦ 61.199262999999995 ¦ 61.199262999999995 ¦ 62.24921599999998 ¦ 62.24921599999998 R4: Sl. No. ¦ Section ¦ Section Length (m) ¦ Stretch Readiness ¦ Insulator Hoisting ¦ Conductor Paying Out ¦ Final Sag ¦ Clipping ¦ Jumper ¦ Sub-Contractor Name ¦ MP ¦ Remarks ¦ OPGW Paying Out ¦ OPGW Final Sag ¦ Sub-Contractor Name R5: From ¦ To ¦ Status ¦ DOS ¦ DOC ¦ Status ¦ DOS ¦ DOC ¦ Status ¦ Status ¦ Status ¦ DOS ¦ DOC ¦ Status ¦ DOS ¦ DOC R74: 69 ¦ AP-24 ¦ AP-25 ¦ 190.524 ¦ C ¦ C ¦ C ¦ 2025-10-04 00:00:00 ¦ 2025-10-04 00:00:00 ¦ C ¦ 2025-10-04 00:00:00 ¦ 2025-10-04 00:00:00 ¦ C ¦ C ¦ National Construction ¦ PLC ¦ C ¦ 2025-12-10 00:00:00 ¦ 2025-12-13 00:00:00 ¦ C | Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc Progress of 220kV Line ¦ Stringing Progress (Conductor & Earthwire) ¦ OPGW Progress Stringing Section ¦ 2026-05-20 00:00:00 ¦ 61.199262999999995 ¦ 61.199262999999995 ¦ 61.199262999999995 ¦ 62.24921599999998 ¦ 62.24921599999998 Sl. No. ¦ Section ¦ Section Length (m) ¦ Stretch Readiness ¦ Insulator Hoisting ¦ Conductor Paying Out ¦ Final Sag ¦ Clipping ¦ Jumper ¦ Sub-Contractor Name ¦ MP ¦ Remarks ¦ OPGW Paying Out ¦ OPGW Final Sag ¦ Sub-Contractor Name From ¦ To ¦ Status ¦ DOS ¦ DOC ¦ Status ¦ DOS ¦ DOC ¦ Status ¦ Status ¦ Status ¦ DOS ¦ DOC ¦ Status ¦ DOS ¦ DOC 1 ¦ Gnty ¦ 0/0 ¦ 0.047 ¦ C ¦ C ¦ C ¦ 2026-01-31 00:00:00 ¦ 2026-02-02 00:00:00 ¦ C ¦ 2026-01-31 00:00:00 ¦ 2026-02-02 00:00:00 ¦ Harshvivek ¦ C ¦ 2026-05-05 00:00:00 ¦ 2026-05-07 00:00:00 ¦ C ¦ 2026-05-08 00:00:00 ¦ 2026-05-08 00:00:00 2 ¦ 0/0 ¦ 1/0 ¦ 439.47 ¦ C ¦ C ¦ C ¦ 2025-05-19 00:00:00 ¦ 2025-05-24 00:00:00 ¦ C ¦ 2025-05-26 00:00:00 ¦ 2025-05-28 00:00:00 ¦ C ¦ C ¦ National Construction ¦ C ¦ 2026-05-05 00:00:00 ¦ 2026-05-07 00:00:00 ¦ C ¦ 2026-05-08 00:00:00 3 ¦ 1/0 ¦ 1A/0 ¦ 1037.32 ¦ C ¦ C ¦ C ¦ 2025-05-19 00:00:00 ¦ 2025-05-24 00:00:00 ¦ C ¦ 2025-05-26 00:00:00 ¦ 2025-05-28 00:00:00 ¦ C ¦ C ¦ National Construction ¦ C ¦ 2026-05-05 00:00:00 ¦ 2026-05-07 00:00:00 ¦ C ¦ 2026-05-08 00:00:00 | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing-132KV | 62 | 26 | opgw_accessories, stretch_readiness, stringing, summary_status, supply | R2: Progress of 220kV Line ¦ Stringing Progress (Conductor & Earthwire) ¦ OPGW Progress R3: Stringing Section ¦ 2026-05-20 00:00:00 ¦ 6.231326 ¦ 6.231326 ¦ 6.231326 ¦ 6.231326 ¦ 6.231326 R4: Sl. No. ¦ Section ¦ Section Length (m) ¦ Stretch Readiness ¦ Insulator Hoisting ¦ Conductor Paying Out ¦ Final Sag ¦ Clipping ¦ Spacer ¦ Jumper ¦ Sub-Contractor Name ¦ MP ¦ Remarks ¦ OPGW Paying Out ¦ OPGW Final Sag ¦ Sub-Contractor Name R5: From ¦ To ¦ Status ¦ DOS ¦ DOC ¦ Status ¦ DOS ¦ DOC ¦ Status ¦ Status ¦ Status ¦ Status ¦ DOS ¦ DOC ¦ Status ¦ DOS ¦ DOC | Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc Progress of 220kV Line ¦ Stringing Progress (Conductor & Earthwire) ¦ OPGW Progress Stringing Section ¦ 2026-05-20 00:00:00 ¦ 6.231326 ¦ 6.231326 ¦ 6.231326 ¦ 6.231326 ¦ 6.231326 Sl. No. ¦ Section ¦ Section Length (m) ¦ Stretch Readiness ¦ Insulator Hoisting ¦ Conductor Paying Out ¦ Final Sag ¦ Clipping ¦ Spacer ¦ Jumper ¦ Sub-Contractor Name ¦ MP ¦ Remarks ¦ OPGW Paying Out ¦ OPGW Final Sag ¦ Sub-Contractor Name From ¦ To ¦ Status ¦ DOS ¦ DOC ¦ Status ¦ DOS ¦ DOC ¦ Status ¦ Status ¦ Status ¦ Status ¦ DOS ¦ DOC ¦ Status ¦ DOS ¦ DOC 1 ¦ Hydro GTY ¦ Existing Tower-1 ¦ 58.79 2 ¦ Existing Tower-1 ¦ Exting Tower-2 ¦ 149.12 3 ¦ Exting Tower-2 ¦ Exting Tower-3 ¦ 128.1 | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | VC-220kV | 155 | 55 | visual_l2 | R2: Visual Chart of 220kV Line ¦ Date ¦ 2026-05-20 00:00:00 | Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc Visual Chart of 220kV Line ¦ Date ¦ 2026-05-20 00:00:00 0/0 ¦ 0/1 ¦ 1/0 ¦ 1/1 ¦ 1/2 ¦ 1A/0 ¦ 1A/1 ¦ 1A/2 ¦ 1B/0 ¦ 1C/0 ¦ 1C/1 ¦ 1D/0 ¦ 1D/1 DD+0 ¦ DA+3 ¦ DC+0 ¦ DA+0 ¦ DA+3 ¦ DC+3 ¦ DA+3 ¦ DC+0 ¦ DD+3 ¦ DD+9 ¦ DA+6 ¦ DC+0 ¦ DA+0 196 ¦ 196.7 ¦ 334 ¦ 319 ¦ 384.3 ¦ 329 ¦ 280 ¦ 232.1 ¦ 237.8 ¦ 334 ¦ 341.2 ¦ 306 ¦ 393.9 RJ ¦ RJ ¦ RJ ¦ RJ ¦ RJ ¦ RJ ¦ RJ ¦ RJ ¦ RJ ¦ RJ ¦ RJ ¦ RJ 2/0 ¦ 3/0 ¦ 4/0 ¦ 4/1 ¦ 4/2 ¦ 4/3 ¦ 4/4 ¦ 4/5 ¦ 4/6 ¦ 4/7 ¦ 4/8 ¦ 4/9 ¦ 4/10 DC+6 ¦ DD+3 ¦ DB+9 ¦ DA+6 ¦ DA+3 ¦ DA+6 ¦ DA+3 ¦ DB+0 ¦ DB+9 ¦ DB+9 ¦ DB+9 ¦ DB+6 ¦ DB+6 | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | VC-132kV | 52 | 60 | visual_l2 | R2: Visual Chart of 132kV Line ¦ Date ¦ 2026-05-20 00:00:00 R37: Legend ¦ Crossing ¦ Progress at a Glance (132kV Line) ¦ Date: R39: Tack-Welding ¦ final sag ¦ rough sag ¦ LT Line ¦ NH/SH ¦ Sl. No. ¦ Activity ¦ Unit ¦ Total Qty ¦ Completed ¦ Balance ¦ Remarks R40: 1 ¦ Detailed Survey ¦ Kms ¦ 9.23 ¦ 9.23 R41: Erection ¦ 11kV Line ¦ 2 ¦ Check Survey ¦ Kms ¦ 9.23 ¦ 9.23 | Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc Visual Chart of 132kV Line ¦ Date ¦ 2026-05-20 00:00:00 Hydro 58.79 ¦ 149.12 ¦ 128.1 ¦ 252.72 ¦ 146.74 ¦ 190.05 ¦ 83.39 ¦ 120.53 ¦ 259.51 ¦ 256.61 ¦ 277.95 Exiting Tower-7 ¦ Exiting Tower-6 ¦ Exiting Tower-5 ¦ Exiting Tower-4 ¦ Exiting Tower-3 ¦ Exiting Tower-2 ¦ Exiting Tower-1 ¦ SC-5 ¦ SC-4 ¦ SC-3 DD+9 ¦ DD+9 ¦ DD+9 CPP 62.76 ¦ 48 ¦ 230.15 ¦ 234.56 ¦ 249.04 ¦ 256 ¦ 226.52 ¦ 43.62 ¦ 52 ¦ 47.06 ¦ 286.44 ¦ 317 ¦ 328 | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | Supply | 36 | 8 | summary_status, supply | R3: Sl. No. ¦ Item ¦ UoM ¦ Scope ¦ MFC Given ¦ Received ¦ Balance ¦ Remarks R4: 1 ¦ Stub ¦ Nos. ¦ 199 ¦ 202 ¦ 202 R18: 3 ¦ Insulator ¦ % ¦ 1 ¦ 1 R19: 4 ¦ Hardware Fittings ¦ % ¦ 1 ¦ 1 R20: 5 ¦ OPGW ¦ % ¦ 1 ¦ 1 | Name of the Line: 220KV DC AL59 line from Neemuch - Chanderiya + 132KV DC ACSS Line from Chanderiya to Hindustan Zinc Supply Progress of 220kV Line ¦ 2026-05-20 00:00:00 Sl. No. ¦ Item ¦ UoM ¦ Scope ¦ MFC Given ¦ Received ¦ Balance ¦ Remarks 1 ¦ Stub ¦ Nos. ¦ 199 ¦ 202 ¦ 202 DA ¦ Nos. ¦ 117 ¦ 117 DB ¦ Nos. ¦ 39 ¦ 39 DC ¦ Nos. ¦ 20 ¦ 20 DD ¦ Nos. ¦ 18 ¦ 18 | ok
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | 2026-05-20 | Mail Body | 27 | 18 | earthing_tack, erection, foundation, stringing, summary_status, survey_soil, visual_l2 | R1: Progress of 220kV Line ¦ Date : ¦ 2026-05-20 00:00:00 R2: Sr. No. ¦ Description ¦ UoM ¦ Total Qty. ¦ Previous month ¦ Progress of Current Month (May'26) ¦ Cumulative till current month ¦ Resources Status ¦ Remarks R3: Cum. Target as per L2 ¦ Cum. Progress ¦ Target as per L2 ¦ Today's Progress ¦ Progress ¦ Target as per L2 ¦ Completed ¦ Balance ¦ Targeted Gang ¦ Available Gang ¦ Shortfall Gang R4: 1 ¦ Detailed Survey ¦ KM ¦ 64 ¦ 64 ¦ 64.178 ¦ - ¦ 64 ¦ 64.178 ¦ -0.17799999999999727 ¦ - ¦ - R5: 2 ¦ Check Survey ¦ KM ¦ 64 ¦ 64 ¦ 62.39 ¦ 64 ¦ 62.39 ¦ -0.17799999999999727 | Progress of 220kV Line ¦ Date : ¦ 2026-05-20 00:00:00 Sr. No. ¦ Description ¦ UoM ¦ Total Qty. ¦ Previous month ¦ Progress of Current Month (May'26) ¦ Cumulative till current month ¦ Resources Status ¦ Remarks Cum. Target as per L2 ¦ Cum. Progress ¦ Target as per L2 ¦ Today's Progress ¦ Progress ¦ Target as per L2 ¦ Completed ¦ Balance ¦ Targeted Gang ¦ Available Gang ¦ Shortfall Gang 1 ¦ Detailed Survey ¦ KM ¦ 64 ¦ 64 ¦ 64.178 ¦ - ¦ 64 ¦ 64.178 ¦ -0.17799999999999727 ¦ - ¦ - 2 ¦ Check Survey ¦ KM ¦ 64 ¦ 64 ¦ 62.39 ¦ 64 ¦ 62.39 ¦ -0.17799999999999727 3 ¦ Foundation ¦ Nos ¦ 199 ¦ 199 ¦ 198 ¦ 1 ¦ 1 ¦ 199 ¦ 199 ¦ 1 ¦ 1 4 ¦ Earthing ¦ Nos ¦ 199 ¦ 199 ¦ 198 ¦ 1 ¦ 1 ¦ 199 ¦ 199 5 ¦ Tower Erection ¦ Nos ¦ 199 ¦ 199 ¦ 195 ¦ 4 ¦ 2 ¦ 199 ¦ 197 ¦ 2 ¦ 2 ¦ 2 ¦ 34/0 erection under progress | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | 765kV Summery | 30 | 18 | project_details, summary_status, supply, survey_soil | R3: TB-507 ¦ DAILY PROGRESS REPORT ¦ 2026-05-20 10:32:58.300000 R4: CONTRACTUAL START DATE: ¦ 2024-12-06 00:00:00 ¦ FATEGARH III-BEAWAR 765KV D/C TRANSMISSION LILO LINE R10: Sl No. ¦ Activity ¦ LOA Quantity ¦ Estimated Line Quantity ¦ Cumm. Progress till Last Month ¦ Plan For MAY'25 ¦ Progress in MAY'25 ¦ WIP ¦ Today's Progress ¦ Cumulative progress till date ¦ Balance ¦ Gangs working May-26 ¦ Manpower ¦ Remarks R11: A.i ¦ Route Alignment (Kms) ¦ 15.478 ¦ 15.478 ¦ 15.478 ¦ 15.478 R12: ii ¦ Detailed Survey (Kms) ¦ 15.478 ¦ 15.478 ¦ 15.478 ¦ 15.478 | TB-507 ¦ DAILY PROGRESS REPORT ¦ 2026-05-20 10:32:58.300000 CONTRACTUAL START DATE: ¦ 2024-12-06 00:00:00 ¦ FATEGARH III-BEAWAR 765KV D/C TRANSMISSION LILO LINE CONTRACTUAL FINISH DATE: ¦ 2026-06-05 00:00:00 REPORTING DATE ¦ Client Name : RAJASTHAN IV A POWER TRANSMISSION LTD TOTAL DAYS ¦ NOA Ref No(Supply): RIVA/LOA-KEC(SUP)/AUG 24/405 COMP. DAYS ¦ NOA Ref No(Service): RIVA/LOA-KEC(SER)/AUG 24/406 Progress Summary ¦ 2026-05-20 10:32:58.300000 Sl No. ¦ Activity ¦ LOA Quantity ¦ Estimated Line Quantity ¦ Cumm. Progress till Last Month ¦ Plan For MAY'25 ¦ Progress in MAY'25 ¦ WIP ¦ Today's Progress ¦ Cumulative progress till date ¦ Balance ¦ Gangs working May-26 ¦ Manpower ¦ Remarks | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Check Survey Status | 118 | 19 | summary_status, survey_soil | R5: SL No ¦ Section ¦ Section Length ¦ Submission Date ¦ Approval Date ¦ Remarks R67: Sr. no ¦ Action by ¦ Section AP To AP ¦ Section length ¦ Approved by Client ¦ Pending by Client ¦ Remarks R68: 1 ¦ KEC ¦ S/S Gantry To AP-7/0 ¦ 10.373 ¦ Details Survey Completed. Profile Preperation in process with KEC Engg. | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED 400 KV CHECK SURVEY SL No ¦ Section ¦ Section Length ¦ Submission Date ¦ Approval Date ¦ Remarks 1 ¦ AP 51- AP 54 ¦ 2.653 ¦ 2025-01-27 00:00:00 ¦ 2025-02-03 00:00:00 ¦ Approved 2 ¦ AP 54- AP 60 ¦ 5.31 ¦ Approved 3 ¦ AP 60- AP 75 ¦ 19.672 ¦ 15.02.2025 , 24-02-2025 25-02-2025 ¦ 2025-02-25 00:00:00 ¦ Approved ¦ Required Change | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Check Survey | 115 | 31 | survey_soil | R5: SL No ¦ Section ¦ Section Length ¦ Submission Date ¦ Approval Date ¦ Remarks R44: SL. No. ¦ Section ¦ Date of submission ¦ Section Length in kms ¦ Letter Reference Number ¦ Date of Approval ¦ Section Length in kms ¦ Approved By ¦ Remarks R67: Action by ¦ Sr.no ¦ Section AP To AP ¦ Section length ¦ Approved by Client ¦ Pending by Client ¦ Remarks ¦ Apraava Comments R68: Apraava ¦ 1 ¦ AP-1/0 To AP-7/0 ¦ 9.4 ¦ Details Survey Completed ¦ Discussion and coordination with Statcraft are ongoing. Awaiting their response R70: KEC ¦ 3 ¦ AP-10/0 To AP-21/0 ¦ 19.57 ¦ YES ¦ Approved ¦ KEC was to submit a proposal avoiding the shifting of the 11 kV line; their response is still awaited. The rest of the profile is acceptable—awaiting a hard-signed copy along with revised tower schdule from the KEC team for official release | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED 400 KV CHECK SURVEY SL No ¦ Section ¦ Section Length ¦ Submission Date ¦ Approval Date ¦ Remarks 1 ¦ AP 51- AP 54 ¦ 2.653 ¦ 2025-01-27 00:00:00 ¦ 2025-02-03 00:00:00 ¦ Approved 2 ¦ AP 54- AP 60 ¦ 5.31 ¦ Approved 3 ¦ AP 60- AP 75 ¦ 19.672 ¦ 15.02.2025 , 24-02-2025 25-02-2025 ¦ 2025-02-25 00:00:00 ¦ Approved ¦ Required Change ¦ Approved ¦ 97.59 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet8 | 30 | 5 | project_details, statutory_crossing, summary_status, survey_soil | R1: S No. ¦ MOM as on 11/6/25 ¦ Timeline ¦ Responsibility ¦ Status as on 19/6/25 R3: a ¦ Apraava will give clearance for further proceeding of Detail Survey ¦ 2025-06-13 00:00:00 ¦ M/S Apraava ¦ Clearance provided for Detail Survey R4: b ¦ Completion of Detail Survey ¦ 2025-06-25 00:00:00 ¦ M/S KEC ¦ Detail Survey work under progress R5: c ¦ Detail Survey of 765 kV is submitted by KEC, observation raised by Apraava, KEC has to re-submitted according to observation ¦ 2025-06-16 00:00:00 ¦ M/S KEC ¦ Reobservation mail by Engg. Team on dt. 19.06.25 R8: b ¦ Pending Section of 21 km will be approved ¦ 2025-06-20 00:00:00 ¦ M/S Apraava & KEC ¦ Under Progress | S No. ¦ MOM as on 11/6/25 ¦ Timeline ¦ Responsibility ¦ Status as on 19/6/25 1 ¦ 400kv Detail Survey from AP 01 to AP 10 a ¦ Apraava will give clearance for further proceeding of Detail Survey ¦ 2025-06-13 00:00:00 ¦ M/S Apraava ¦ Clearance provided for Detail Survey b ¦ Completion of Detail Survey ¦ 2025-06-25 00:00:00 ¦ M/S KEC ¦ Detail Survey work under progress c ¦ Detail Survey of 765 kV is submitted by KEC, observation raised by Apraava, KEC has to re-submitted according to observation ¦ 2025-06-16 00:00:00 ¦ M/S KEC ¦ Reobservation mail by Engg. Team on dt. 19.06.25 2 ¦ Check Survey a ¦ 50 km will be approved ¦ 2025-06-12 00:00:00 ¦ M/S Apraava & KEC ¦ 33 km Approved & 15 km submitted by KEC b ¦ Pending Section of 21 km will be approved ¦ 2025-06-20 00:00:00 ¦ M/S Apraava & KEC ¦ Under Progress | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet2 | 20 | 6 | survey_soil | R4: Sl No ¦ Section AP To AP ¦ Section length ¦ Remarks R16: Sl No ¦ Section AP To AP ¦ Section length ¦ Route Allignment,Detail Survey,Check survey | 400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line Sl No ¦ Section AP To AP ¦ Section length ¦ Remarks 1 ¦ AP-21/0 To AP-24/0 ¦ 2.618 2 ¦ AP-24/0 To AP-27/0 ¦ 1.428 3 ¦ AP-27/0 To AP-40/0 ¦ 16.76 4 ¦ AP-45/0 To AP-48/0 ¦ 3.187 5 ¦ AP-153/0 To AP-154/0 ¦ 0.732 6 ¦ AP-154/0 To AP-155/0 ¦ 0.218 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet1 | 29 | 12 | foundation, project_details, row_hindrance, summary_status | R2: SL. No. ¦ Location Number ¦ Span ¦ Tower Type ¦ RC ¦ Foundation type R3: Starting date ¦ Completion Date ¦ Agency ¦ Remark ¦ Remarks R5: 2 ¦ 81/4 ¦ 81/4 ¦ DA+0 ¦ Sandy ¦ 2025-01-18 00:00:00 ¦ ROW ¦ Mahadeep Company ¦ ROW LOC HOLD ¦ Row Since 20-01-2025, Gang Domobilized R18: 15 ¦ 86/2 ¦ DA+0 ¦ Sandy ¦ 2025-02-10 00:00:00 ¦ Kalpana Enterprises ¦ Pit A , Pit B RCC Done , Pit C -Stub setting. R19: 16 ¦ 66/1 ¦ DA+9 ¦ Sandy ¦ 2025-02-17 00:00:00 ¦ Siyag Construction ¦ Excavation WIP, ROW,Material Shifting WIP | FOUNDATION STATUS ¦ 18 SL. No. ¦ Location Number ¦ Span ¦ Tower Type ¦ RC ¦ Foundation type Starting date ¦ Completion Date ¦ Agency ¦ Remark ¦ Remarks 1 ¦ 83/1 ¦ 83/1 ¦ DA+3 ¦ Sandy ¦ 2025-01-08 00:00:00 ¦ 2025-01-17 00:00:00 ¦ Mahadeep Company ¦ 2025-01-17 00:00:00 ¦ Complete 2 ¦ 81/4 ¦ 81/4 ¦ DA+0 ¦ Sandy ¦ 2025-01-18 00:00:00 ¦ ROW ¦ Mahadeep Company ¦ ROW LOC HOLD ¦ Row Since 20-01-2025, Gang Domobilized 3 ¦ 75/7 ¦ 75/7 ¦ DA+0 ¦ Sandy ¦ 2025-01-18 00:00:00 ¦ 2025-01-27 00:00:00 ¦ AR PATEL ¦ RCC Complete 4 ¦ 75/6 ¦ DA+0 ¦ Sandy ¦ 2025-01-28 00:00:00 ¦ 2025-02-02 00:00:00 ¦ AR PATEL ¦ RCC Complete, Backfilling Done 5 ¦ 75/5 ¦ DA+0 ¦ Sandy ¦ 2025-01-28 00:00:00 ¦ 2025-02-05 00:00:00 ¦ AR PATEL ¦ RCC Complete. | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | VC 51-96 | 212 | 22 | earthing_tack, erection, foundation, stringing, summary_status, visual_l2 | R4: DPR- ¦ District ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing | TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line DPR and VISUAL CHART DPR- ¦ District ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing Com ¦ WIP ¦ Bal ¦ Com ¦ Com ¦ WIP ¦ Bal ¦ Com ¦ WIP ¦ Bal 163 ¦ 50.886 ¦ 16 ¦ 5 ¦ 142 ¦ 10 ¦ 163 ¦ 50.886 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ 9 465.03 ¦ 375.98 ¦ 414.86 ¦ 381.02 ¦ 353.63 ¦ 351.4 ¦ 433.26 ¦ 396.56 ¦ 408.11 ¦ 3579.85 AP51 ¦ 51/1 ¦ 51/2 ¦ 51/3 ¦ AP52 ¦ 52/1 ¦ AP53 ¦ AP54 ¦ 54/1 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | VC | 451 | 32 | earthing_tack, erection, foundation, row_hindrance, stringing, summary_status, visual_l2 | R5: DPR- ¦ District ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing R11: 97.4 ¦ 139.42 ¦ 484.04 ¦ 398 ¦ 443.16 ¦ 399.53 ¦ 402.87 ¦ 437.15 ¦ 381.84 ¦ 416.91 ¦ 3600.32 ¦ FDN ¦ TE ¦ Earthing ¦ Stringing ¦ Tack Welding ¦ 3600.32 R14: GE ¦ AP1 ¦ AP2 ¦ AP3 ¦ 03/1 ¦ 3/2 ¦ 3/3 ¦ 3/4 ¦ 3/5 ¦ 3/6 ¦ ROW R22: 3/7 ¦ 3/8 ¦ AP4 ¦ 4/1 ¦ AP5 ¦ 5/1 ¦ 5/2 ¦ AP6 ¦ AP7 ¦ 7/1 ¦ ROW R30: 7/2 ¦ 7/3 ¦ 7/4 ¦ 7/5 ¦ 7/6 ¦ '7/7 ¦ AP8 ¦ 08/01 ¦ 08/2 ¦ 08/3 ¦ ROW | TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line DPR and VISUAL CHART DPR- ¦ District ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing Com ¦ WIP ¦ Bal ¦ Com ¦ Com ¦ WIP ¦ Bal ¦ Com ¦ WIP ¦ Bal 495 ¦ 187.175 ¦ 9 ¦ 5 ¦ 481 ¦ 3 ¦ 495 ¦ 187.175 r 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ 9 ¦ 10 97.4 ¦ 139.42 ¦ 484.04 ¦ 398 ¦ 443.16 ¦ 399.53 ¦ 402.87 ¦ 437.15 ¦ 381.84 ¦ 416.91 ¦ 3600.32 ¦ FDN ¦ TE ¦ Earthing ¦ Stringing ¦ Tack Welding ¦ 3600.32 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | ROW | 40 | 16117 | foundation, row_hindrance, summary_status | R7: SL. No. ¦ Location Number ¦ Span ¦ Tower Type ¦ AS PER RAPTL ROW CLEARED ON ¦ WORK COMMENCED KEC ¦ STATUS R10: 2 ¦ 66/4 ¦ ROW R11: 3 ¦ 89/1 ¦ ROW R15: 7 ¦ 90/1 ¦ ROW | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED FOUNDATION STATUS SL. No. ¦ Location Number ¦ Span ¦ Tower Type ¦ AS PER RAPTL ROW CLEARED ON ¦ WORK COMMENCED KEC ¦ STATUS 1 ¦ 80/0 2 ¦ 66/4 ¦ ROW 3 ¦ 89/1 ¦ ROW | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | June | 26 | 8 | project_details | R1: Sl No ¦ Loc No ¦ TOT ¦ Classification ¦ Starting Date ¦ Completion | Sl No ¦ Loc No ¦ TOT ¦ Classification ¦ Starting Date ¦ Completion 1 ¦ 81/3 ¦ DA+0 ¦ Sandy ¦ 2025-05-22 00:00:00 ¦ 2025-06-04 00:00:00 2 ¦ 120/1 ¦ DA+6 ¦ Sandy ¦ 2025-05-30 00:00:00 ¦ 2025-06-05 00:00:00 3 ¦ 96/0 ¦ DC+0 ¦ DFR ¦ 2025-05-28 00:00:00 ¦ 2025-06-06 00:00:00 4 ¦ 75/0 ¦ DC+0 ¦ Sandy ¦ 2025-06-01 00:00:00 ¦ 2025-06-07 00:00:00 5 ¦ 147/2 ¦ DA+0 ¦ Sandy ¦ 2025-06-02 00:00:00 ¦ 2025-06-08 00:00:00 6 ¦ 82/2 ¦ DA+0 ¦ Sandy ¦ 2025-06-02 00:00:00 ¦ 2025-06-10 00:00:00 7 ¦ 79/0 ¦ DD+0 ¦ Sandy ¦ 2025-08-08 00:00:00 ¦ 2025-06-12 00:00:00 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Check survey Loop out | 89 | 26 | survey_soil, visual_l2 | R7: Sl. No ¦ Twr No. ¦ Tower Type ¦ Deviation Angle ¦ Span (mtr) ¦ Section Length (mtr) ¦ Sl.No ¦ Tower No. ¦ TYPE OF TOWER ¦ HT of Tower (Mtr) ¦ SPAN (Mtr) ¦ Section ¦ CUMULATIVE SPAN ¦ R.L (Mtr) ¦ DEVIATION ANGLE (Deg) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ UTM Coordinates R62: SURVEYED BY: ¦ CHECKED BY: ¦ SURVEY & CHACKED BY: ¦ SUBMITTED BY: ¦ CHECKED BY: ¦ CHECKED BY: ¦ APPROVED BY: | CLIENT :- RAJASTHAN IV A POWER TRANSMISSION LTD. NAME OF PROJECT :- Lilo of 765 kv D/C Fathegarh III -Beawar at Fathegarh-IV Transmission Line CONTRACTOR : KEC INTERNATIONAL LTD Detail Survey Tower Schedule : GANTRY TO Existing 10/6 (Loop Out) (Rev-06) AS PER DETAILED SURVEY ¦ AS PER DETAIL SURVEY Sl. No ¦ Twr No. ¦ Tower Type ¦ Deviation Angle ¦ Span (mtr) ¦ Section Length (mtr) ¦ Sl.No ¦ Tower No. ¦ TYPE OF TOWER ¦ HT of Tower (Mtr) ¦ SPAN (Mtr) ¦ Section ¦ CUMULATIVE SPAN ¦ R.L (Mtr) ¦ DEVIATION ANGLE (Deg) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ UTM Coordinates Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Easting (m) ¦ Y Northing (m) 1 ¦ Gantry ¦ Gantry ¦ 174.263 ¦ 1 ¦ Gantry 1 ¦ Gantry ¦ 46.3 ¦ 143.312 ¦ 253.455 ¦ 143.312 ¦ 73 ¦ 75 ¦ 75 ¦ 75 ¦ 75 ¦ 723713 ¦ 2905256 ¦ Existing Fathegarh-IV S/S | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Check survey Loop In | 81 | 26 | survey_soil, visual_l2 | R7: Sl. No ¦ Twr No. ¦ Tower Type ¦ Deviation Angle ¦ Span (mtr) ¦ Section Length (mtr) ¦ Sl.No ¦ Tower No. ¦ TYPE OF TOWER ¦ HT of Tower (Mtr) ¦ SPAN (Mtr) ¦ Section ¦ CUMULATIVE SPAN ¦ R.L (Mtr) ¦ DEVIATION ANGLE (Deg) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ UTM Coordinates R55: SURVEYED BY: ¦ CHECKED BY: ¦ SURVEY & CHACKED BY: ¦ SUBMITTED BY: ¦ CHECKED BY: ¦ CHECKED BY: ¦ APPROVED BY: | CLIENT :- RAJASTHAN IV A POWER TRANSMISSION LTD. NAME OF PROJECT :- Lilo of 765 kv D/C Fathegarh III -Beawar at Fathegarh-IV Transmission Line CONTRACTOR : KEC INTERNATIONAL LIMITED CHECK SURVEY REPORT Detail Survey Tower Schedule : Existing 10/4 TO GANTRY (Loop in) (Rev-06) Check Survey Tower Schedule : GANTRY TO Existing 10/6 (Loop Out) (Rev-0) ¦ AS PER DETAIL SURVEY Sl. No ¦ Twr No. ¦ Tower Type ¦ Deviation Angle ¦ Span (mtr) ¦ Section Length (mtr) ¦ Sl.No ¦ Tower No. ¦ TYPE OF TOWER ¦ HT of Tower (Mtr) ¦ SPAN (Mtr) ¦ Section ¦ CUMULATIVE SPAN ¦ R.L (Mtr) ¦ DEVIATION ANGLE (Deg) ¦ Sum of Adjacent Spans ¦ WIND SPAN (Mtr) ¦ WEIGHT SPAN IN Mtr (Cold) ¦ WEIGHT SPAN IN Mtr (Hot) ¦ UTM Coordinates Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Easting (m) ¦ Y Northing (m) | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Foundation | 42 | 16129 | foundation, project_details, summary_status, supply | R6: SL. No. ¦ Location Number ¦ Span ¦ Tower Type ¦ M10 ¦ M20 ¦ Excavation ¦ Reinforcement ¦ Stub ¦ RC ¦ Foundation type R7: LI / LO ¦ Starting date ¦ Completion Date ¦ Agency ¦ Remark ¦ Remarks R40: 33 ¦ 4/3 ¦ LO ¦ DA+0 ¦ DFR ¦ 2026-05-15 00:00:00 ¦ Karni Mata Construction Company ¦ 10 ¦ Block Level/ROW R41: 34 ¦ 5/0 ¦ LO ¦ DD45+0 ¦ DFR ¦ Karni Mata Construction Company ¦ 15 ¦ Excavation/ Under Cutting R42: 35 ¦ 3A/1 ¦ LI ¦ DB1+6 ¦ DFR ¦ Karni Mata Construction Company ¦ 5 ¦ Excavation/ Under Cutting | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED FOUNDATION STATUS SL. No. ¦ Location Number ¦ Span ¦ Tower Type ¦ M10 ¦ M20 ¦ Excavation ¦ Reinforcement ¦ Stub ¦ RC ¦ Foundation type LI / LO ¦ Starting date ¦ Completion Date ¦ Agency ¦ Remark ¦ Remarks 1 ¦ 7/0 ¦ LI ¦ DE+9 (Aux. X-arm) ¦ DFR ¦ 2026-02-06 00:00:00 ¦ 2026-02-11 00:00:00 ¦ Karni Mata Construction Company ¦ RCC Complete, Backfilling Done 2 ¦ 1/1 ¦ LO ¦ DA-3 ¦ DFR ¦ 2026-02-11 00:00:00 ¦ 2026-02-14 00:00:00 ¦ Karni Mata Construction Company ¦ RCC Complete, Backfilling Done | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Royalty | 33 | 21 |  | R4: Loc No ¦ TOT ¦ M-10 ¦ M-20 R29: 26.220000000000002 ¦ 185.35 ¦ Balance | OM Construction Loc No ¦ TOT ¦ M-10 ¦ M-20 120/1 ¦ DA+6 ¦ 1.86 ¦ 12.47 ¦ 75/0 ¦ DC+0 ¦ 1.6 ¦ 13.129999999999999 119/0 ¦ DD+3 ¦ 2.93 ¦ 20.34 ¦ 79/0 ¦ DD+0 ¦ 2.93 ¦ 20.34 CUM ¦ 4.79 ¦ 32.81 ¦ ROYALTY ISSUED ¦ 78/0 ¦ DC+0 ¦ 1.6 ¦ 13.129999999999999 CUM ¦ 20MM ¦ 4.42596 ¦ 27.560400000000005 ¦ 31.986360000000005 ¦ 20MM ¦ 74/0 ¦ DB+9 ¦ 1.68 ¦ 12.41 CUM ¦ SAND ¦ 2.04479352 ¦ 11.575368000000003 ¦ 13.620161520000003 ¦ 18.48 ¦ 73/0 ¦ DB+0 ¦ 1.68 ¦ 12.41 MT ¦ 20MM ¦ 51.17817600000001 ¦ Required ¦ 14.67 ¦ 72/2 ¦ DA+3 ¦ 1.86 ¦ 12.47 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet14 | 51 | 9 |  |  | 1 ¦ 95/1 ¦ DB+0 ¦ DFR ¦ 2025-06-23 00:00:00 ¦ 2025-07-04 00:00:00 ¦ Baba Ramdev Construction ¦ RCC Complete, Backfilling Done 2 ¦ 148/3 ¦ DA+0 ¦ Sandy ¦ 2025-06-27 00:00:00 ¦ 2025-07-05 00:00:00 ¦ AR Patel ¦ RCC Complete, Backfilling Done 3 ¦ 106/0 ¦ DC+6 ¦ Sandy ¦ 2025-06-25 00:00:00 ¦ 2025-07-06 00:00:00 ¦ Mundhan Trading Company ¦ RCC Complete, Backfilling Done 4 ¦ 148/1 ¦ DA+0 ¦ Sandy ¦ 2025-07-04 00:00:00 ¦ 2025-07-08 00:00:00 ¦ AR Patel ¦ RCC Complete, Backfilling Done 5 ¦ 146/0 ¦ DC+0 ¦ Sandy ¦ 2025-07-03 00:00:00 ¦ 2025-07-08 00:00:00 ¦ JP Enterprises ¦ RCC Complete, Backfilling Done 6 ¦ 80/0 ¦ DB+3 ¦ 1MRC ¦ Sandy ¦ 2025-06-28 00:00:00 ¦ 2025-07-10 00:00:00 ¦ Mahadev Enterprises ¦ RCC Complete, Backfilling Done 7 ¦ 114/1 ¦ DA+9 ¦ Sandy ¦ 2025-07-04 00:00:00 ¦ 2025-07-10 00:00:00 ¦ Goswami and Company ¦ RCC Complete, Backfilling Done 8 ¦ 148/2 ¦ DA+0 ¦ Sandy ¦ 2025-07-07 00:00:00 ¦ 2025-07-10 00:00:00 ¦ AR Patel ¦ RCC Complete, Backfilling Done | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet7 | 34 | 10 | project_details | R4: SL ¦ Loc ¦ TOT ¦ Gang ¦ Starting Date ¦ Completion R5: 1 ¦ 148/3 ¦ DA+0 ¦ Gokul Sarkar ¦ 2025-08-29 00:00:00 ¦ 2025-09-04 00:00:00 ¦ Completed R6: 2 ¦ 81/2 ¦ DA+3 ¦ Dipak ¦ 2025-09-01 00:00:00 ¦ 2025-09-05 00:00:00 ¦ Completed R7: 3 ¦ 145/1 ¦ DA+3 ¦ Ayansh Const ¦ 2025-08-27 00:00:00 ¦ 2025-09-09 00:00:00 ¦ Completed R8: 4 ¦ 81/4 ¦ DA+0 ¦ Dipak ¦ 2025-09-05 00:00:00 ¦ 2025-09-09 00:00:00 ¦ Completed | SL ¦ Loc ¦ TOT ¦ Gang ¦ Starting Date ¦ Completion 1 ¦ 148/3 ¦ DA+0 ¦ Gokul Sarkar ¦ 2025-08-29 00:00:00 ¦ 2025-09-04 00:00:00 ¦ Completed 2 ¦ 81/2 ¦ DA+3 ¦ Dipak ¦ 2025-09-01 00:00:00 ¦ 2025-09-05 00:00:00 ¦ Completed 3 ¦ 145/1 ¦ DA+3 ¦ Ayansh Const ¦ 2025-08-27 00:00:00 ¦ 2025-09-09 00:00:00 ¦ Completed 4 ¦ 81/4 ¦ DA+0 ¦ Dipak ¦ 2025-09-05 00:00:00 ¦ 2025-09-09 00:00:00 ¦ Completed 5 ¦ 148/2 ¦ DA+0 ¦ Gokul Sarkar ¦ 2025-09-05 00:00:00 ¦ 2025-09-10 00:00:00 ¦ Completed 6 ¦ 83/1 ¦ DA+3 ¦ Ahmed Construction ¦ 2025-08-29 00:00:00 ¦ 2025-09-11 00:00:00 ¦ Completed 7 ¦ 97/0 ¦ DC+0 ¦ Ajay Kumar1 ¦ 2025-09-01 00:00:00 ¦ 2025-09-11 00:00:00 ¦ Completed | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Project Details | 13 | 11 | project_details, statutory_crossing | R1: Project Code ¦ Project Name ¦ Client Name ¦ LOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Supervisor/Engineer R2: TB 507 ¦ 400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line ¦ RAJASTHAN IV A POWER TRANSMISSION LTD ¦ 2024-12-06 00:00:00 ¦ 2026-06-05 00:00:00 ¦ Mr.Amartya sarkar ¦ Mr. N K Gupta ¦ Mr.ALOK SINHA ¦ Mr.ALOK JANA Mr.VARUN TYAGI | Project Code ¦ Project Name ¦ Client Name ¦ LOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Supervisor/Engineer TB 507 ¦ 400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line ¦ RAJASTHAN IV A POWER TRANSMISSION LTD ¦ 2024-12-06 00:00:00 ¦ 2026-06-05 00:00:00 ¦ Mr.Amartya sarkar ¦ Mr. N K Gupta ¦ Mr.ALOK SINHA ¦ Mr.ALOK JANA Mr.VARUN TYAGI | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection | 309 | 30 | erection, project_details | R5: SL. No. ¦ Location No. ¦ Tower Type ¦ Tower Weight ¦ Gang Name ¦ Starting Date ¦ Completion Date ¦ Remarks R6: 1 ¦ 77/2 ¦ DA+3 ¦ 11.145 ¦ Dipak ¦ 2025-06-23 00:00:00 ¦ 2025-06-28 00:00:00 ¦ Completed R7: 2 ¦ 77/4 ¦ DA+3 ¦ 11.997 ¦ Dipak ¦ 2025-06-28 00:00:00 ¦ 2025-07-02 00:00:00 ¦ Completed R8: 3 ¦ 75/7 ¦ DA+0 ¦ 11.145 ¦ Srikarni ¦ 2025-06-29 00:00:00 ¦ 2025-07-05 00:00:00 ¦ Completed R9: 4 ¦ 77/5 ¦ DA+6 ¦ 13.072 ¦ Dipak ¦ 2025-07-03 00:00:00 ¦ 2025-07-05 00:00:00 ¦ Completed | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED SL. No. ¦ Location No. ¦ Tower Type ¦ Tower Weight ¦ Gang Name ¦ Starting Date ¦ Completion Date ¦ Remarks 1 ¦ 77/2 ¦ DA+3 ¦ 11.145 ¦ Dipak ¦ 2025-06-23 00:00:00 ¦ 2025-06-28 00:00:00 ¦ Completed 2 ¦ 77/4 ¦ DA+3 ¦ 11.997 ¦ Dipak ¦ 2025-06-28 00:00:00 ¦ 2025-07-02 00:00:00 ¦ Completed 3 ¦ 75/7 ¦ DA+0 ¦ 11.145 ¦ Srikarni ¦ 2025-06-29 00:00:00 ¦ 2025-07-05 00:00:00 ¦ Completed 4 ¦ 77/5 ¦ DA+6 ¦ 13.072 ¦ Dipak ¦ 2025-07-03 00:00:00 ¦ 2025-07-05 00:00:00 ¦ Completed | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Completion date | 509 | 12 | earthing_tack, erection, foundation, project_details | R1: Location no ¦ Tower type ¦ FDN TYPE ¦ FDN CMP date ¦ Erection CMP Date ¦ Earthing CMP Date | Location no ¦ Tower type ¦ FDN TYPE ¦ FDN CMP date ¦ Erection CMP Date ¦ Earthing CMP Date GANTRY ¦ GE ¦ #N/A ¦ #N/A ¦ #N/A ¦ #N/A 1/0 ¦ DE+0 ¦ 00:00:00 ¦ 2026-02-11 00:00:00 ¦ #N/A ¦ #N/A 1A/0 ¦ DD+0 ¦ #N/A ¦ #N/A ¦ #N/A ¦ #N/A 2/0 ¦ DD+0 ¦ 00:00:00 ¦ 2026-02-28 00:00:00 ¦ #N/A ¦ #N/A 2/1 ¦ Gantry UCS ¦ 00:00:00 ¦ 08-03-226 ¦ 00:00:00 ¦ #N/A 3/0 ¦ Gantry UCS ¦ #N/A ¦ #N/A ¦ #N/A ¦ #N/A 3/1 ¦ DD+3 ¦ 00:00:00 ¦ 2026-03-27 00:00:00 ¦ #N/A ¦ #N/A | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection Compiled | 383 | 50 | erection, project_details, summary_status | R1: Sl. No. ¦ Location No. ¦ LI / LO ¦ Tower Type ¦ Weight ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Remark | Sl. No. ¦ Location No. ¦ LI / LO ¦ Tower Type ¦ Weight ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ Remark 1 ¦ 1/1 ¦ LO ¦ DA-3 ¦ 36.421 ¦ DFR ¦ 2026-03-27 00:00:00 ¦ COMPLETE ¦ 2026-04-06 00:00:00 ¦ Priyanka Debi ¦ 28 2 ¦ 1/2 ¦ LO ¦ DA-3 ¦ 36.421 ¦ DFR ¦ 2026-04-07 00:00:00 ¦ COMPLETE ¦ 2026-04-15 00:00:00 ¦ Priyanka Debi ¦ 28 3 ¦ 2/1 ¦ lo ¦ DA+0 ¦ 38.002 ¦ DFR ¦ 2026-04-15 00:00:00 ¦ COMPLETE ¦ 2026-04-26 00:00:00 ¦ Priyanka Debi ¦ 28 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Earthing | 9 | 8 | earthing_tack, foundation, project_details | R5: SL. No. ¦ Location Number ¦ LI / LO ¦ Tower Type ¦ Foundation type ¦ Completion Date ¦ Remarks | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED SL. No. ¦ Location Number ¦ LI / LO ¦ Tower Type ¦ Foundation type ¦ Completion Date ¦ Remarks 1 ¦ 1/1 ¦ LO ¦ DA-3 ¦ DFR ¦ 2026-02-20 00:00:00 2 ¦ 1/2 ¦ LO ¦ DA-3 ¦ DFR ¦ 2026-02-20 00:00:00 3 ¦ 6/2 ¦ LI ¦ DA+0 ¦ DFR ¦ 2026-02-20 00:00:00 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing Compiled | 5 | 17 | project_details, row_hindrance, stretch_readiness, stringing, summary_status | R3: S.no ¦ Sec ¦ From AP ¦ To AP ¦ Span (M) ¦ Method ¦ Section Readiness ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Length ¦ Status ¦ Gang Name ¦ Hindrance ¦ Remarks | Number of TSE S.no ¦ Sec ¦ From AP ¦ To AP ¦ Span (M) ¦ Method ¦ Section Readiness ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Length ¦ Status ¦ Gang Name ¦ Hindrance ¦ Remarks Total | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Soil Investigation | 3 | 19 | survey_soil |  | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet9 | 319 | 45 | earthing_tack, erection, foundation, statutory_crossing, stringing, summary_status, survey_soil, visual_l2 | R5: Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed ¦ Balance ¦ River Crossing R7: 1 ¦ Detail survey ¦ Kms. ¦ 188.444 ¦ 188.444 R8: 2 ¦ Check survey ¦ Kms. ¦ 188.444 ¦ 178.075 ¦ 10.369 R10: 4 ¦ Soil Investigation ¦ Loc ¦ 73 ¦ 73 R11: 5 ¦ Foundation ¦ Loc ¦ 512 ¦ 208 ¦ 304 ¦ Erection WIP | 400 KV D/C (TWIN) FATEHGARH IV - BHINMAL (PG) TRANSMISSION LINE (VISUAL CHART) Name of Contractor:M/S KEC INTERNATIONAL LIMITED ¦ AS ON ¦ 2026-05-20 10:32:58.300000 PROGRESS AT A GLANCE : Stringing WIP ¦ Stringing Completed Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed ¦ Balance ¦ River Crossing 1 ¦ Detail survey ¦ Kms. ¦ 188.444 ¦ 188.444 2 ¦ Check survey ¦ Kms. ¦ 188.444 ¦ 178.075 ¦ 10.369 3 ¦ CS Approval ¦ Kms. ¦ 188.444 ¦ 178.075 ¦ 10.369 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | VC | 314 | 37 | earthing_tack, erection, foundation, statutory_crossing, stringing, summary_status, survey_soil | R6: Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ River Crossing R8: 1 ¦ Detail survey ¦ Kms. ¦ 187.175 ¦ 187.175 ¦ Oil pipeline R9: 2 ¦ Check survey ¦ Kms. ¦ 187.175 ¦ 169.168 ¦ 18.007000000000005 ¦ Gas pipeline R10: 3 ¦ Soil Investigation ¦ Loc ¦ 73 ¦ 73 R11: 4 ¦ Foundation ¦ Loc ¦ 495 ¦ 79 ¦ 416 ¦ Erection WIP | 52 2026-05-20 10:32:58.300000 Name of Contractor:M/S KEC INTERNATIONAL LIMITED PROGRESS AT A GLANCE : Stringing WIP ¦ Stringing Completed Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ River Crossing 1 ¦ Detail survey ¦ Kms. ¦ 187.175 ¦ 187.175 ¦ Oil pipeline 2 ¦ Check survey ¦ Kms. ¦ 187.175 ¦ 169.168 ¦ 18.007000000000005 ¦ Gas pipeline | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet6 | 42 | 9 |  | R3: SL No ¦ Loc No ¦ TOT ¦ Classificatin ¦ M-10 ¦ M-20 | SL No ¦ Loc No ¦ TOT ¦ Classificatin ¦ M-10 ¦ M-20 1 ¦ 83/1 ¦ DA+3 ¦ Sandy ¦ 1.86 ¦ 12.47 2 ¦ 75/7 ¦ DA+0 ¦ Sandy ¦ 1.57 ¦ 11.05 3 ¦ 75/6 ¦ DA+0 ¦ Sandy ¦ 1.57 ¦ 11.05 4 ¦ 75/5 ¦ DA+0 ¦ Sandy ¦ 1.57 ¦ 11.05 5 ¦ 75/4 ¦ DA+0 ¦ Sandy ¦ 1.57 ¦ 11.05 6 ¦ 75/3 ¦ DA+3 ¦ Sandy ¦ 1.86 ¦ 12.47 7 ¦ 75/1 ¦ DA+0 ¦ Sandy ¦ 1.57 ¦ 11.05 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | VC 51-121 | 225 | 44 | earthing_tack, erection, foundation, stringing, summary_status, survey_soil, visual_l2 | R4: DPR- ¦ As per Approved Check Survey ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing | TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line DPR and VISUAL CHART DPR- ¦ As per Approved Check Survey ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing Com ¦ WIP ¦ Bal ¦ Com ¦ Com ¦ WIP ¦ Bal ¦ Com ¦ WIP ¦ Bal AP 51- AP 121 ¦ 196 ¦ 74.398 ¦ 39 ¦ 4 ¦ 153 ¦ 25 ¦ 196 ¦ 74.398 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ 9 DA ¦ DB ¦ DC 465.03 ¦ 375.98 ¦ 414.86 ¦ 381.02 ¦ 353.63 ¦ 351.4 ¦ 433.26 ¦ 396.56 ¦ 408.11 ¦ 3579.8500000000004 ¦ +0 ¦ +3 ¦ +6 ¦ +9 ¦ +0 ¦ +3 ¦ +6 ¦ +9 ¦ +0 ¦ +3 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet5 | 38 | 10 |  | R3: Sl.No. ¦ Loc.No. ¦ Tower Type ¦ Tower Leg ¦ Remarks | Sl.No. ¦ Loc.No. ¦ Tower Type ¦ Tower Leg ¦ Remarks A ¦ B ¦ C ¦ D 1 ¦ AP52 ¦ DB+0 ¦ 2 ¦ 3 ¦ 3 ¦ 3 ¦ 3 2 ¦ 52/1 ¦ DA+6 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 3 ¦ 54/2 ¦ DA+6 ¦ Benching & RC Required ¦ - ¦ - ¦ 1 ¦ - 4 ¦ 54/3 ¦ DA+3 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 5 ¦ AP55 ¦ DD+18 ¦ 3 ¦ 3 ¦ 3 ¦ 3 ¦ 3 6 ¦ AP56 ¦ DB+9 ¦ Benching & RC Required ¦ 3 ¦ 3 ¦ 3 ¦ 3 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet3 | 242 | 22 | earthing_tack, erection, foundation, stringing, summary_status, survey_soil, visual_l2 | R4: DPR- ¦ As per Approved Check Survey ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing | TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line DPR and VISUAL CHART DPR- ¦ As per Approved Check Survey ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing Com ¦ WIP ¦ Bal ¦ Com ¦ Com ¦ WIP ¦ Bal ¦ Com ¦ WIP ¦ Bal AP 51- AP 121 ¦ 171 ¦ 74 ¦ 34 ¦ 3 ¦ 134 ¦ 21 ¦ 171 ¦ 74 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ 9 465.03 ¦ 375.98 ¦ 414.86 ¦ 381.02 ¦ 353.63 ¦ 351.4 ¦ 433.26 ¦ 396.56 ¦ 408.11 ¦ 3579.8500000000004 AP51 ¦ 51/1 ¦ 51/2 ¦ 51/3 ¦ AP52 ¦ 52/1 ¦ AP53 ¦ AP54 ¦ 54/1 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tower Schedule | 142 | 29 | statutory_crossing, survey_soil, visual_l2 | R7: Sl. No ¦ Twr No. ¦ Tower Type ¦ Raise Chimney ¦ Deviation Angle (DMS) ¦ Span (m) ¦ Section Length (M) ¦ Sl. No ¦ Twr No. ¦ Tower Type ¦ Raise Chimney ¦ Ground Cutting Length X Height ¦ Deviation Angle (DMS) ¦ Span (m) ¦ Section Length (M) ¦ Sum of Adjacent Span ¦ Wind Span (m) ¦ Weight Span (Cold) ¦ Weight Span (Hot) ¦ Major Crossings /Remarks | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED CHECK SURVEY Tower Schedule from AP-75/0 to AP-92/0 (Section Length = 20.273 kms) AS PER DETAILED SURVEY ¦ AS PER CHECK SURVEY Sl. No ¦ Twr No. ¦ Tower Type ¦ Raise Chimney ¦ Deviation Angle (DMS) ¦ Span (m) ¦ Section Length (M) ¦ Sl. No ¦ Twr No. ¦ Tower Type ¦ Raise Chimney ¦ Ground Cutting Length X Height ¦ Deviation Angle (DMS) ¦ Span (m) ¦ Section Length (M) ¦ Sum of Adjacent Span ¦ Wind Span (m) ¦ Weight Span (Cold) ¦ Weight Span (Hot) ¦ Major Crossings /Remarks Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Easting ¦ Northing ¦ Elevation | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Visual Chart | 71 | 38 | earthing_tack, foundation, summary_status, survey_soil, visual_l2 | R4: PROGRESS AT A GLANCE ¦ AS ON ¦ 2026-05-20 10:32:58.300000 R6: Sl. No. ¦ Activity ¦ UoM ¦ LOOP IN ¦ LOOP OUT ¦ Total Quantity ¦ Total Balance ¦ Remarks R7: Final Quantity ¦ Completed ¦ Balance ¦ Final Quantity ¦ Completed ¦ Balance ¦ LOOP IN WIP R8: 1 ¦ Detail survey ¦ Kms. ¦ 7.556 ¦ 7.556 ¦ 7.922 ¦ 7.922 ¦ 15.478 ¦ FDN WIP LI : 4/0, 4/1, 4/3 R9: 2 ¦ Check survey ¦ Kms. ¦ 7.556 ¦ 7.556 ¦ 7.922 ¦ 7.922 ¦ 15.478 | NAME OF PROJECT : FATEGARH III-BEAWAR 765KV D/C TRANSMISSION LILO LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. AGENCY : KEC INTERNATIONAL LIMITED PROGRESS AT A GLANCE ¦ AS ON ¦ 2026-05-20 10:32:58.300000 Sl. No. ¦ Activity ¦ UoM ¦ LOOP IN ¦ LOOP OUT ¦ Total Quantity ¦ Total Balance ¦ Remarks Final Quantity ¦ Completed ¦ Balance ¦ Final Quantity ¦ Completed ¦ Balance ¦ LOOP IN WIP 1 ¦ Detail survey ¦ Kms. ¦ 7.556 ¦ 7.556 ¦ 7.922 ¦ 7.922 ¦ 15.478 ¦ FDN WIP LI : 4/0, 4/1, 4/3 2 ¦ Check survey ¦ Kms. ¦ 7.556 ¦ 7.556 ¦ 7.922 ¦ 7.922 ¦ 15.478 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | L2 Vs Actual Progress Chart (2) | 25 | 27 | foundation, row_hindrance, statutory_crossing, summary_status, survey_soil, visual_l2 | R3: Sl. No. ¦ ACTIVITY ¦ Responsibility ¦ Sch. Start date ¦ Sch. Finish date ¦ Days ¦ Unit ¦ Quantity ¦ Dec'24 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 ¦ Jun'25 ¦ Jul'25 ¦ Aug'25 ¦ Sep'25 ¦ Oct'25 ¦ Nov'25 R8: Check Survey Submission & Approval ¦ KEC & Apraava ¦ 2025-01-05 00:00:00 ¦ 2025-04-15 00:00:00 ¦ 100 ¦ Kms. ¦ 184 ¦ 20 ¦ 60 ¦ 60 ¦ 44 R9: 5.a ¦ ROW clearance and front avaibility for Civil foundation ¦ Apraava ¦ 25.12.24 ¦ 30.12.25 ¦ #VALUE! ¦ Loc. ¦ 508 ¦ 5 ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 45 ¦ 48 ¦ 50 R10: 5.b ¦ Foundation Work execution ¦ KEC ¦ 2025-01-07 00:00:00 ¦ 2026-01-26 00:00:00 ¦ 384 ¦ Loc. ¦ 508 ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 30 ¦ 25 ¦ 25 ¦ 48 ¦ 45 ¦ 50 R18: Sl. No. ¦ ACTIVITY ¦ Responsibility ¦ Sch. Start date ¦ Sch. Finish date ¦ Days ¦ Unit ¦ Quantity ¦ Dec'24 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 ¦ Jun'25 ¦ Jul'25 ¦ Aug'25 ¦ Sep'25 ¦ Oct'25 ¦ Nov'25 | NAME OF LINE: 400kV Transmisison Line Fatehgarh IV to Bhinmal As Per L2 Sl. No. ¦ ACTIVITY ¦ Responsibility ¦ Sch. Start date ¦ Sch. Finish date ¦ Days ¦ Unit ¦ Quantity ¦ Dec'24 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 ¦ Jun'25 ¦ Jul'25 ¦ Aug'25 ¦ Sep'25 ¦ Oct'25 ¦ Nov'25 M0 ¦ M1 ¦ M2 ¦ M3 ¦ M4 ¦ M5 ¦ M6 ¦ M7 ¦ M8 ¦ M9 ¦ M10 ¦ M11 ¦ M12 ¦ M13 ¦ M14 ¦ M15 ¦ M16 ¦ M17 ¦ M18 1 ¦ Notice of Award ¦ KEC & Apraava ¦ 2024-12-06 00:00:00 ¦ 2026-06-05 00:00:00 ¦ 546 Services 1 ¦ Establishment of site office ¦ KEC ¦ 2024-12-16 00:00:00 ¦ 2025-01-15 00:00:00 ¦ 30 ¦ LS Check Survey Submission & Approval ¦ KEC & Apraava ¦ 2025-01-05 00:00:00 ¦ 2025-04-15 00:00:00 ¦ 100 ¦ Kms. ¦ 184 ¦ 20 ¦ 60 ¦ 60 ¦ 44 | ok
TB 507 | TB 507 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet4 | 13 | 21 | foundation, row_hindrance, summary_status, survey_soil, visual_l2 | R6: Check Survey (Kms) ¦ 20 ¦ 60 ¦ 60 ¦ 44 R8: Foundation (Nos) ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 30 ¦ 25 ¦ 25 ¦ 48 ¦ 45 ¦ 50 ¦ 48 R9: ROW Front Clearence ¦ 5 ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 45 ¦ 48 ¦ 50 ¦ 45 | Activity ¦ As Per L2 Dec'24 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 ¦ Jun'25 ¦ Jul'25 ¦ Aug'25 ¦ Sep'25 ¦ Oct'25 ¦ Nov'25 ¦ Dec'25 ¦ Jan'26 ¦ Feb'26 ¦ Mar'26 ¦ Apr'26 ¦ May'26 ¦ June'26 Check Survey (Kms) ¦ 20 ¦ 60 ¦ 60 ¦ 44 Actual Progress ¦ 28 Foundation (Nos) ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 30 ¦ 25 ¦ 25 ¦ 48 ¦ 45 ¦ 50 ¦ 48 ROW Front Clearence ¦ 5 ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 45 ¦ 48 ¦ 50 ¦ 45 Actual Foundation Completed (Nos) ¦ 3 WIP ¦ 2 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | 400kV Summery | 29 | 19 | project_details, summary_status, supply, survey_soil | R3: TB-507 ¦ DAILY PROGRESS REPORT ¦ 2026-05-20 10:56:36.900000 R4: CONTRACTUAL START DATE: ¦ 2024-12-06 00:00:00 ¦ 400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line R10: Sl No. ¦ Activity ¦ LOA Quantity ¦ Estimated Line Quantity ¦ Cumm. Progress till Last Month ¦ Plan For MAY'25 ¦ Progress in MAY'25 ¦ WIP ¦ Today's Progress ¦ Cumulative progress till date ¦ Balance ¦ Gangs working May-26 ¦ Manpower ¦ Remarks R11: A.i ¦ Route Alignment (Kms) ¦ 184 ¦ 188.678 ¦ 188.678 ¦ 188.678 ¦ In the Scope of Rajasthan IV A Power Transmission Ltd R12: ii ¦ Detailed Survey (Kms) ¦ 184 ¦ 188.678 ¦ 188.678 ¦ 188.678 ¦ 188.678 Kms Approved | TB-507 ¦ DAILY PROGRESS REPORT ¦ 2026-05-20 10:56:36.900000 CONTRACTUAL START DATE: ¦ 2024-12-06 00:00:00 ¦ 400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line CONTRACTUAL FINISH DATE: ¦ 2026-06-05 00:00:00 REPORTING DATE ¦ Client Name : RAJASTHAN IV A POWER TRANSMISSION LTD TOTAL DAYS ¦ NOA Ref No(Supply): RIVA/LOA-KEC(SUP)/AUG 24/405 COMP. DAYS ¦ NOA Ref No(Service): RIVA/LOA-KEC(SER)/AUG 24/406 Progress Summary ¦ 2026-05-20 10:56:36.900000 Sl No. ¦ Activity ¦ LOA Quantity ¦ Estimated Line Quantity ¦ Cumm. Progress till Last Month ¦ Plan For MAY'25 ¦ Progress in MAY'25 ¦ WIP ¦ Today's Progress ¦ Cumulative progress till date ¦ Balance ¦ Gangs working May-26 ¦ Manpower ¦ Remarks | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Check Survey | 124 | 8 | survey_soil | R5: SL No ¦ Section ¦ Section Length ¦ Submission Date ¦ Approval Date ¦ Remarks R67: Sr. no ¦ Action by ¦ Section AP To AP ¦ Section length ¦ Approved by Client ¦ Pending by Client ¦ Remarks ¦ JMC | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED 400 KV CHECK SURVEY SL No ¦ Section ¦ Section Length ¦ Submission Date ¦ Approval Date ¦ Remarks 1 ¦ AP 51- AP 54 ¦ 2.653 ¦ 2025-01-27 00:00:00 ¦ 2025-02-03 00:00:00 ¦ Approved 2 ¦ AP 54- AP 60 ¦ 5.31 ¦ Approved 3 ¦ AP 60- AP 75 ¦ 19.672 ¦ 15.02.2025 , 24-02-2025 25-02-2025 ¦ 2025-02-25 00:00:00 ¦ Approved ¦ Required Change | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Check Survey Status | 118 | 19 | summary_status, survey_soil | R5: SL No ¦ Section ¦ Section Length ¦ Submission Date ¦ Approval Date ¦ Remarks R67: Sr. no ¦ Action by ¦ Section AP To AP ¦ Section length ¦ Approved by Client ¦ Pending by Client ¦ Remarks R68: 1 ¦ KEC ¦ S/S Gantry To AP-7/0 ¦ 10.373 ¦ Details Survey Completed. Profile Preperation in process with KEC Engg. | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED 400 KV CHECK SURVEY SL No ¦ Section ¦ Section Length ¦ Submission Date ¦ Approval Date ¦ Remarks 1 ¦ AP 51- AP 54 ¦ 2.653 ¦ 2025-01-27 00:00:00 ¦ 2025-02-03 00:00:00 ¦ Approved 2 ¦ AP 54- AP 60 ¦ 5.31 ¦ Approved 3 ¦ AP 60- AP 75 ¦ 19.672 ¦ 15.02.2025 , 24-02-2025 25-02-2025 ¦ 2025-02-25 00:00:00 ¦ Approved ¦ Required Change | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Check Survey | 115 | 31 | survey_soil | R5: SL No ¦ Section ¦ Section Length ¦ Submission Date ¦ Approval Date ¦ Remarks R44: SL. No. ¦ Section ¦ Date of submission ¦ Section Length in kms ¦ Letter Reference Number ¦ Date of Approval ¦ Section Length in kms ¦ Approved By ¦ Remarks R67: Action by ¦ Sr.no ¦ Section AP To AP ¦ Section length ¦ Approved by Client ¦ Pending by Client ¦ Remarks ¦ Apraava Comments R68: Apraava ¦ 1 ¦ AP-1/0 To AP-7/0 ¦ 9.4 ¦ Details Survey Completed ¦ Discussion and coordination with Statcraft are ongoing. Awaiting their response R70: KEC ¦ 3 ¦ AP-10/0 To AP-21/0 ¦ 19.57 ¦ YES ¦ Approved ¦ KEC was to submit a proposal avoiding the shifting of the 11 kV line; their response is still awaited. The rest of the profile is acceptable—awaiting a hard-signed copy along with revised tower schdule from the KEC team for official release | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED 400 KV CHECK SURVEY SL No ¦ Section ¦ Section Length ¦ Submission Date ¦ Approval Date ¦ Remarks 1 ¦ AP 51- AP 54 ¦ 2.653 ¦ 2025-01-27 00:00:00 ¦ 2025-02-03 00:00:00 ¦ Approved 2 ¦ AP 54- AP 60 ¦ 5.31 ¦ Approved 3 ¦ AP 60- AP 75 ¦ 19.672 ¦ 15.02.2025 , 24-02-2025 25-02-2025 ¦ 2025-02-25 00:00:00 ¦ Approved ¦ Required Change ¦ Approved ¦ 97.59 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet8 | 30 | 5 | project_details, statutory_crossing, summary_status, survey_soil | R1: S No. ¦ MOM as on 11/6/25 ¦ Timeline ¦ Responsibility ¦ Status as on 19/6/25 R3: a ¦ Apraava will give clearance for further proceeding of Detail Survey ¦ 2025-06-13 00:00:00 ¦ M/S Apraava ¦ Clearance provided for Detail Survey R4: b ¦ Completion of Detail Survey ¦ 2025-06-25 00:00:00 ¦ M/S KEC ¦ Detail Survey work under progress R5: c ¦ Detail Survey of 765 kV is submitted by KEC, observation raised by Apraava, KEC has to re-submitted according to observation ¦ 2025-06-16 00:00:00 ¦ M/S KEC ¦ Reobservation mail by Engg. Team on dt. 19.06.25 R8: b ¦ Pending Section of 21 km will be approved ¦ 2025-06-20 00:00:00 ¦ M/S Apraava & KEC ¦ Under Progress | S No. ¦ MOM as on 11/6/25 ¦ Timeline ¦ Responsibility ¦ Status as on 19/6/25 1 ¦ 400kv Detail Survey from AP 01 to AP 10 a ¦ Apraava will give clearance for further proceeding of Detail Survey ¦ 2025-06-13 00:00:00 ¦ M/S Apraava ¦ Clearance provided for Detail Survey b ¦ Completion of Detail Survey ¦ 2025-06-25 00:00:00 ¦ M/S KEC ¦ Detail Survey work under progress c ¦ Detail Survey of 765 kV is submitted by KEC, observation raised by Apraava, KEC has to re-submitted according to observation ¦ 2025-06-16 00:00:00 ¦ M/S KEC ¦ Reobservation mail by Engg. Team on dt. 19.06.25 2 ¦ Check Survey a ¦ 50 km will be approved ¦ 2025-06-12 00:00:00 ¦ M/S Apraava & KEC ¦ 33 km Approved & 15 km submitted by KEC b ¦ Pending Section of 21 km will be approved ¦ 2025-06-20 00:00:00 ¦ M/S Apraava & KEC ¦ Under Progress | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet2 | 20 | 6 | survey_soil | R4: Sl No ¦ Section AP To AP ¦ Section length ¦ Remarks R16: Sl No ¦ Section AP To AP ¦ Section length ¦ Route Allignment,Detail Survey,Check survey | 400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line Sl No ¦ Section AP To AP ¦ Section length ¦ Remarks 1 ¦ AP-21/0 To AP-24/0 ¦ 2.618 2 ¦ AP-24/0 To AP-27/0 ¦ 1.428 3 ¦ AP-27/0 To AP-40/0 ¦ 16.76 4 ¦ AP-45/0 To AP-48/0 ¦ 3.187 5 ¦ AP-153/0 To AP-154/0 ¦ 0.732 6 ¦ AP-154/0 To AP-155/0 ¦ 0.218 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Project Details | 13 | 11 | project_details, statutory_crossing | R1: Project Code ¦ Project Name ¦ Client Name ¦ LOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Supervisor/Engineer R2: TB 507 ¦ 400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line ¦ RAJASTHAN IV A POWER TRANSMISSION LTD ¦ 23.08.2024 ¦ 22.02.2026 ¦ Mr. Amartya sarkar ¦ Mr. N K Gupta ¦ Mr.ALOK SINHA ¦ Mr.ALOK JANA Mr. VARUN TYAGI | Project Code ¦ Project Name ¦ Client Name ¦ LOA Start Date ¦ LOA End Date ¦ Planning Engineer ¦ PCH ¦ Regional Manager ¦ Project Manger ¦ Section Incharge ¦ Supervisor/Engineer TB 507 ¦ 400kV D/C Fatehgarh IV (Section-2)PS - Bhinmal (PG) Transmission Line ¦ RAJASTHAN IV A POWER TRANSMISSION LTD ¦ 23.08.2024 ¦ 22.02.2026 ¦ Mr. Amartya sarkar ¦ Mr. N K Gupta ¦ Mr.ALOK SINHA ¦ Mr.ALOK JANA Mr. VARUN TYAGI | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Statutory Clearence | 54 | 14 | statutory_crossing, summary_status, survey_soil | R3: S N ¦ Loc No. ¦ Line Crossing ¦ Asset Owner ¦ Submission by KEC ¦ Submission to Asset Owner ¦ Date of Joint site visit ¦ Demand letter from Asset Owner ¦ Letter submission/ Demand fulfillment ¦ Date of NOC/ Approval ¦ Target date for NOC ¦ Status as on 31-03-2026 ¦ Remarks R5: 1 ¦ AP 2 - 3/1 ¦ 400KV D/C ¦ APRAAVA ¦ 01.02.2026 ¦ 01.02.2026 ¦ Approved ¦ PL crossing Apraava's Line. Technical team approved during check survey R18: 1 ¦ AP 43 - AP 44 ¦ Barmer-Jodhpur National Highway-25 ¦ NHAI ¦ 14.07.2025 ¦ 14.07.2025 ¦ 06.10.2025 ¦ 15.04.2026 ¦ Demand letter expected by 7th April R19: 2 ¦ AP 121 - AP 122 ¦ Jamnagar-Amritsar Bharat Mala Expressway NH -754 ¦ NHAI ¦ 14.07.2025 ¦ 14.07.2025 ¦ 08.09.2025 ¦ 28.10.2025 ¦ 21.11.2025 ¦ 06.12.2025 R33: 2 ¦ AP 36A - AP 37 ¦ OIL Line ¦ Mangla Crude Oil Pipeline ¦ 28.05.2025 ¦ 11.06.2025 ¦ 10.07.2025 ¦ 17.11.2025 ¦ 31.12.2025 ¦ 2026-03-30 00:00:00 ¦ Hard copies submitted on 06.03.2026 ¦ 1. Joint agreement to be signed 2. Special contingency insurance policy (5cr) to be taken and policy shall be valid till one month after completion of work. 3. Supervision charges (E-payment mode) : Rs. 50,000 + 18% | Rajasthan IV A 400 KV LINE - STATUTORY APPROVAL STATUS KEC RESPONSIBILITY ¦ APRAAVA RESPONSIBILITY S N ¦ Loc No. ¦ Line Crossing ¦ Asset Owner ¦ Submission by KEC ¦ Submission to Asset Owner ¦ Date of Joint site visit ¦ Demand letter from Asset Owner ¦ Letter submission/ Demand fulfillment ¦ Date of NOC/ Approval ¦ Target date for NOC ¦ Status as on 31-03-2026 ¦ Remarks Power Line Crossing for Line (12 Nos) 1 ¦ AP 2 - 3/1 ¦ 400KV D/C ¦ APRAAVA ¦ 01.02.2026 ¦ 01.02.2026 ¦ Approved ¦ PL crossing Apraava's Line. Technical team approved during check survey 2 ¦ AP4-AP5 ¦ 220KV D/C ¦ AMPIN ¦ 01.04.2026 ¦ 30.04.2026 3 ¦ AP 5D - AP 5E ¦ 132KV S/C ¦ RRVPNL ¦ 21.02.2026 ¦ 06.03.2026 ¦ 15.04.2026 ¦ Joint Site visit planned by 7th April 4 ¦ AP 6D/5 - AP 7/0 ¦ 132KV D/C ¦ RRVPNL ¦ 21.02.2026 ¦ 06.03.2026 ¦ 15.04.2026 ¦ Joint Site visit planned by 7th April | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Crossing Proposal | 303 | 29 | statutory_crossing, summary_status, survey_soil | R1: Sl No. ¦ Crossing Span ¦ Type ¦ Description ¦ Proposal Status ¦ Remarks R3: 1 ¦ AP2/1 - AP3 ¦ 400KV D/C Fatehgarh III Fatehgarh IV T/L ¦ Apraava Energy PVT. LTD. ¦ 10.07.2025 ¦ Subject to Approval of CS ¦ Survey Report Submitted to Apraava Engg, R4: 2 ¦ AP4 - AP5 ¦ 220 KV S/C PSS To FS IV Ampin CKT-1. ¦ RRVPNL ¦ 10.07.2025 ¦ Subject to Approval of CS ¦ Survey Report Submitted to Apraava Engg, R5: 3 ¦ AP5D - AP5E ¦ 132 KV S/C Sheo to Undoo Line. ¦ RRVPNL ¦ 10.07.2025 ¦ Subject to Approval of CS ¦ Survey Report Submitted to Apraava Engg, R6: 4 ¦ AP25 - 26 ¦ 400kV D/C Rajwest to Jodhpur TL & Rajwest to Pancpadra ¦ RRVPNL ¦ 07.07.2025 ¦ Crossing Proposal Hardcopy submitted to Apraava ¦ Proposal Submitted to Apraava | Sl No. ¦ Crossing Span ¦ Type ¦ Description ¦ Proposal Status ¦ Remarks A ¦ Power Line Crossings 1 ¦ AP2/1 - AP3 ¦ 400KV D/C Fatehgarh III Fatehgarh IV T/L ¦ Apraava Energy PVT. LTD. ¦ 10.07.2025 ¦ Subject to Approval of CS ¦ Survey Report Submitted to Apraava Engg, 2 ¦ AP4 - AP5 ¦ 220 KV S/C PSS To FS IV Ampin CKT-1. ¦ RRVPNL ¦ 10.07.2025 ¦ Subject to Approval of CS ¦ Survey Report Submitted to Apraava Engg, 3 ¦ AP5D - AP5E ¦ 132 KV S/C Sheo to Undoo Line. ¦ RRVPNL ¦ 10.07.2025 ¦ Subject to Approval of CS ¦ Survey Report Submitted to Apraava Engg, 4 ¦ AP25 - 26 ¦ 400kV D/C Rajwest to Jodhpur TL & Rajwest to Pancpadra ¦ RRVPNL ¦ 07.07.2025 ¦ Crossing Proposal Hardcopy submitted to Apraava ¦ Proposal Submitted to Apraava 5 ¦ A 27- A 27A ¦ 220kV S/C BALOTARA TO GIRAL T/ Lin ¦ RRVPNL ¦ Submitted on 24.05.25 ¦ AE will forward proposal for NOC to Chief Zonal by 10.10.2025 6 ¦ AP50-AP51 ¦ 220kV S/C BALOTARA TO BARMER T/ Line ¦ RRVPNL ¦ Submitted on 24.05.25 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet1 | 29 | 12 | foundation, project_details, row_hindrance, summary_status | R2: SL. No. ¦ Location Number ¦ Span ¦ Tower Type ¦ RC ¦ Foundation type R3: Starting date ¦ Completion Date ¦ Agency ¦ Remark ¦ Remarks R5: 2 ¦ 81/4 ¦ 81/4 ¦ DA+0 ¦ Sandy ¦ 2025-01-18 00:00:00 ¦ ROW ¦ Mahadeep Company ¦ ROW LOC HOLD ¦ Row Since 20-01-2025, Gang Domobilized R18: 15 ¦ 86/2 ¦ DA+0 ¦ Sandy ¦ 2025-02-10 00:00:00 ¦ Kalpana Enterprises ¦ Pit A , Pit B RCC Done , Pit C -Stub setting. R19: 16 ¦ 66/1 ¦ DA+9 ¦ Sandy ¦ 2025-02-17 00:00:00 ¦ Siyag Construction ¦ Excavation WIP, ROW,Material Shifting WIP | FOUNDATION STATUS ¦ 18 SL. No. ¦ Location Number ¦ Span ¦ Tower Type ¦ RC ¦ Foundation type Starting date ¦ Completion Date ¦ Agency ¦ Remark ¦ Remarks 1 ¦ 83/1 ¦ 83/1 ¦ DA+3 ¦ Sandy ¦ 2025-01-08 00:00:00 ¦ 2025-01-17 00:00:00 ¦ Mahadeep Company ¦ 2025-01-17 00:00:00 ¦ Complete 2 ¦ 81/4 ¦ 81/4 ¦ DA+0 ¦ Sandy ¦ 2025-01-18 00:00:00 ¦ ROW ¦ Mahadeep Company ¦ ROW LOC HOLD ¦ Row Since 20-01-2025, Gang Domobilized 3 ¦ 75/7 ¦ 75/7 ¦ DA+0 ¦ Sandy ¦ 2025-01-18 00:00:00 ¦ 2025-01-27 00:00:00 ¦ AR PATEL ¦ RCC Complete 4 ¦ 75/6 ¦ DA+0 ¦ Sandy ¦ 2025-01-28 00:00:00 ¦ 2025-02-02 00:00:00 ¦ AR PATEL ¦ RCC Complete, Backfilling Done 5 ¦ 75/5 ¦ DA+0 ¦ Sandy ¦ 2025-01-28 00:00:00 ¦ 2025-02-05 00:00:00 ¦ AR PATEL ¦ RCC Complete. | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | VC 51-96 | 212 | 22 | earthing_tack, erection, foundation, stringing, summary_status, visual_l2 | R4: DPR- ¦ District ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing | TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line DPR and VISUAL CHART DPR- ¦ District ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing Com ¦ WIP ¦ Bal ¦ Com ¦ Com ¦ WIP ¦ Bal ¦ Com ¦ WIP ¦ Bal 163 ¦ 50.886 ¦ 16 ¦ 5 ¦ 142 ¦ 10 ¦ 163 ¦ 50.886 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ 9 465.03 ¦ 375.98 ¦ 414.86 ¦ 381.02 ¦ 353.63 ¦ 351.4 ¦ 433.26 ¦ 396.56 ¦ 408.11 ¦ 3579.85 AP51 ¦ 51/1 ¦ 51/2 ¦ 51/3 ¦ AP52 ¦ 52/1 ¦ AP53 ¦ AP54 ¦ 54/1 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | VC | 451 | 32 | earthing_tack, erection, foundation, row_hindrance, stringing, summary_status, visual_l2 | R5: DPR- ¦ District ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing R11: 97.4 ¦ 139.42 ¦ 484.04 ¦ 398 ¦ 443.16 ¦ 399.53 ¦ 402.87 ¦ 437.15 ¦ 381.84 ¦ 416.91 ¦ 3600.32 ¦ FDN ¦ TE ¦ Earthing ¦ Stringing ¦ Tack Welding ¦ 3600.32 R14: GE ¦ AP1 ¦ AP2 ¦ AP3 ¦ 03/1 ¦ 3/2 ¦ 3/3 ¦ 3/4 ¦ 3/5 ¦ 3/6 ¦ ROW R22: 3/7 ¦ 3/8 ¦ AP4 ¦ 4/1 ¦ AP5 ¦ 5/1 ¦ 5/2 ¦ AP6 ¦ AP7 ¦ 7/1 ¦ ROW R30: 7/2 ¦ 7/3 ¦ 7/4 ¦ 7/5 ¦ 7/6 ¦ '7/7 ¦ AP8 ¦ 08/01 ¦ 08/2 ¦ 08/3 ¦ ROW | TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line DPR and VISUAL CHART DPR- ¦ District ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing Com ¦ WIP ¦ Bal ¦ Com ¦ Com ¦ WIP ¦ Bal ¦ Com ¦ WIP ¦ Bal 495 ¦ 187.175 ¦ 9 ¦ 5 ¦ 481 ¦ 3 ¦ 495 ¦ 187.175 r 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ 9 ¦ 10 97.4 ¦ 139.42 ¦ 484.04 ¦ 398 ¦ 443.16 ¦ 399.53 ¦ 402.87 ¦ 437.15 ¦ 381.84 ¦ 416.91 ¦ 3600.32 ¦ FDN ¦ TE ¦ Earthing ¦ Stringing ¦ Tack Welding ¦ 3600.32 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | ROW | 40 | 16117 | foundation, row_hindrance, summary_status | R7: SL. No. ¦ Location Number ¦ Span ¦ Tower Type ¦ AS PER RAPTL ROW CLEARED ON ¦ WORK COMMENCED KEC ¦ STATUS R10: 2 ¦ 66/4 ¦ ROW R11: 3 ¦ 89/1 ¦ ROW R15: 7 ¦ 90/1 ¦ ROW | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED FOUNDATION STATUS SL. No. ¦ Location Number ¦ Span ¦ Tower Type ¦ AS PER RAPTL ROW CLEARED ON ¦ WORK COMMENCED KEC ¦ STATUS 1 ¦ 80/0 2 ¦ 66/4 ¦ ROW 3 ¦ 89/1 ¦ ROW | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | June | 26 | 8 | project_details | R1: Sl No ¦ Loc No ¦ TOT ¦ Classification ¦ Starting Date ¦ Completion | Sl No ¦ Loc No ¦ TOT ¦ Classification ¦ Starting Date ¦ Completion 1 ¦ 81/3 ¦ DA+0 ¦ Sandy ¦ 2025-05-22 00:00:00 ¦ 2025-06-04 00:00:00 2 ¦ 120/1 ¦ DA+6 ¦ Sandy ¦ 2025-05-30 00:00:00 ¦ 2025-06-05 00:00:00 3 ¦ 96/0 ¦ DC+0 ¦ DFR ¦ 2025-05-28 00:00:00 ¦ 2025-06-06 00:00:00 4 ¦ 75/0 ¦ DC+0 ¦ Sandy ¦ 2025-06-01 00:00:00 ¦ 2025-06-07 00:00:00 5 ¦ 147/2 ¦ DA+0 ¦ Sandy ¦ 2025-06-02 00:00:00 ¦ 2025-06-08 00:00:00 6 ¦ 82/2 ¦ DA+0 ¦ Sandy ¦ 2025-06-02 00:00:00 ¦ 2025-06-10 00:00:00 7 ¦ 79/0 ¦ DD+0 ¦ Sandy ¦ 2025-08-08 00:00:00 ¦ 2025-06-12 00:00:00 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Foundation | 319 | 16134 | foundation, project_details, summary_status, supply | R6: SL. No. ¦ Location Number ¦ Span ¦ Tower Type ¦ M10 ¦ M20 ¦ Excavation ¦ Reinforcement ¦ Stub ¦ RC ¦ Foundation type R7: Starting date ¦ Completion Date ¦ Agency ¦ Remark ¦ Working Manpower ¦ Remarks | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED FOUNDATION STATUS SL. No. ¦ Location Number ¦ Span ¦ Tower Type ¦ M10 ¦ M20 ¦ Excavation ¦ Reinforcement ¦ Stub ¦ RC ¦ Foundation type Starting date ¦ Completion Date ¦ Agency ¦ Remark ¦ Working Manpower ¦ Remarks 1 ¦ 83/1 ¦ 83/1 ¦ DA+3 ¦ 1.86 ¦ 12.47 ¦ 134.7 ¦ 1.115 ¦ 0.299 ¦ Sandy ¦ 2025-01-08 00:00:00 ¦ 2025-01-17 00:00:00 ¦ Mahadeep Company ¦ 2025-01-17 00:00:00 ¦ RCC Complete, Backfilling Done 2 ¦ 75/7 ¦ 75/7 ¦ DA+0 ¦ 1.57 ¦ 11.05 ¦ 115.3 ¦ 0.919 ¦ 0.299 ¦ Sandy ¦ 2025-01-18 00:00:00 ¦ 2025-01-27 00:00:00 ¦ AR Patel Contractor ¦ RCC Complete, Backfilling Done | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Royalty | 33 | 21 |  | R4: Loc No ¦ TOT ¦ M-10 ¦ M-20 R29: 26.220000000000002 ¦ 185.35 ¦ Balance | OM Construction Loc No ¦ TOT ¦ M-10 ¦ M-20 120/1 ¦ DA+6 ¦ 1.86 ¦ 12.47 ¦ 75/0 ¦ DC+0 ¦ 1.6 ¦ 13.129999999999999 119/0 ¦ DD+3 ¦ 2.93 ¦ 20.34 ¦ 79/0 ¦ DD+0 ¦ 2.93 ¦ 20.34 CUM ¦ 4.79 ¦ 32.81 ¦ ROYALTY ISSUED ¦ 78/0 ¦ DC+0 ¦ 1.6 ¦ 13.129999999999999 CUM ¦ 20MM ¦ 4.42596 ¦ 27.560400000000005 ¦ 31.986360000000005 ¦ 20MM ¦ 74/0 ¦ DB+9 ¦ 1.68 ¦ 12.41 CUM ¦ SAND ¦ 2.04479352 ¦ 11.575368000000003 ¦ 13.620161520000003 ¦ 18.48 ¦ 73/0 ¦ DB+0 ¦ 1.68 ¦ 12.41 MT ¦ 20MM ¦ 51.17817600000001 ¦ Required ¦ 14.67 ¦ 72/2 ¦ DA+3 ¦ 1.86 ¦ 12.47 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet14 | 51 | 9 |  |  | 1 ¦ 95/1 ¦ DB+0 ¦ DFR ¦ 2025-06-23 00:00:00 ¦ 2025-07-04 00:00:00 ¦ Baba Ramdev Construction ¦ RCC Complete, Backfilling Done 2 ¦ 148/3 ¦ DA+0 ¦ Sandy ¦ 2025-06-27 00:00:00 ¦ 2025-07-05 00:00:00 ¦ AR Patel ¦ RCC Complete, Backfilling Done 3 ¦ 106/0 ¦ DC+6 ¦ Sandy ¦ 2025-06-25 00:00:00 ¦ 2025-07-06 00:00:00 ¦ Mundhan Trading Company ¦ RCC Complete, Backfilling Done 4 ¦ 148/1 ¦ DA+0 ¦ Sandy ¦ 2025-07-04 00:00:00 ¦ 2025-07-08 00:00:00 ¦ AR Patel ¦ RCC Complete, Backfilling Done 5 ¦ 146/0 ¦ DC+0 ¦ Sandy ¦ 2025-07-03 00:00:00 ¦ 2025-07-08 00:00:00 ¦ JP Enterprises ¦ RCC Complete, Backfilling Done 6 ¦ 80/0 ¦ DB+3 ¦ 1MRC ¦ Sandy ¦ 2025-06-28 00:00:00 ¦ 2025-07-10 00:00:00 ¦ Mahadev Enterprises ¦ RCC Complete, Backfilling Done 7 ¦ 114/1 ¦ DA+9 ¦ Sandy ¦ 2025-07-04 00:00:00 ¦ 2025-07-10 00:00:00 ¦ Goswami and Company ¦ RCC Complete, Backfilling Done 8 ¦ 148/2 ¦ DA+0 ¦ Sandy ¦ 2025-07-07 00:00:00 ¦ 2025-07-10 00:00:00 ¦ AR Patel ¦ RCC Complete, Backfilling Done | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet7 | 34 | 10 | project_details | R4: SL ¦ Loc ¦ TOT ¦ Gang ¦ Starting Date ¦ Completion R5: 1 ¦ 148/3 ¦ DA+0 ¦ Gokul Sarkar ¦ 2025-08-29 00:00:00 ¦ 2025-09-04 00:00:00 ¦ Completed R6: 2 ¦ 81/2 ¦ DA+3 ¦ Dipak ¦ 2025-09-01 00:00:00 ¦ 2025-09-05 00:00:00 ¦ Completed R7: 3 ¦ 145/1 ¦ DA+3 ¦ Ayansh Const ¦ 2025-08-27 00:00:00 ¦ 2025-09-09 00:00:00 ¦ Completed R8: 4 ¦ 81/4 ¦ DA+0 ¦ Dipak ¦ 2025-09-05 00:00:00 ¦ 2025-09-09 00:00:00 ¦ Completed | SL ¦ Loc ¦ TOT ¦ Gang ¦ Starting Date ¦ Completion 1 ¦ 148/3 ¦ DA+0 ¦ Gokul Sarkar ¦ 2025-08-29 00:00:00 ¦ 2025-09-04 00:00:00 ¦ Completed 2 ¦ 81/2 ¦ DA+3 ¦ Dipak ¦ 2025-09-01 00:00:00 ¦ 2025-09-05 00:00:00 ¦ Completed 3 ¦ 145/1 ¦ DA+3 ¦ Ayansh Const ¦ 2025-08-27 00:00:00 ¦ 2025-09-09 00:00:00 ¦ Completed 4 ¦ 81/4 ¦ DA+0 ¦ Dipak ¦ 2025-09-05 00:00:00 ¦ 2025-09-09 00:00:00 ¦ Completed 5 ¦ 148/2 ¦ DA+0 ¦ Gokul Sarkar ¦ 2025-09-05 00:00:00 ¦ 2025-09-10 00:00:00 ¦ Completed 6 ¦ 83/1 ¦ DA+3 ¦ Ahmed Construction ¦ 2025-08-29 00:00:00 ¦ 2025-09-11 00:00:00 ¦ Completed 7 ¦ 97/0 ¦ DC+0 ¦ Ajay Kumar1 ¦ 2025-09-01 00:00:00 ¦ 2025-09-11 00:00:00 ¦ Completed | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection | 309 | 30 | erection, project_details | R5: SL. No. ¦ Location No. ¦ Tower Type ¦ Tower Weight ¦ Gang Name ¦ Starting Date ¦ Completion Date ¦ Remarks R6: 1 ¦ 77/2 ¦ DA+3 ¦ 11.145 ¦ Dipak ¦ 2025-06-23 00:00:00 ¦ 2025-06-28 00:00:00 ¦ Completed R7: 2 ¦ 77/4 ¦ DA+3 ¦ 11.997 ¦ Dipak ¦ 2025-06-28 00:00:00 ¦ 2025-07-02 00:00:00 ¦ Completed R8: 3 ¦ 75/7 ¦ DA+0 ¦ 11.145 ¦ Srikarni ¦ 2025-06-29 00:00:00 ¦ 2025-07-05 00:00:00 ¦ Completed R9: 4 ¦ 77/5 ¦ DA+6 ¦ 13.072 ¦ Dipak ¦ 2025-07-03 00:00:00 ¦ 2025-07-05 00:00:00 ¦ Completed | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED SL. No. ¦ Location No. ¦ Tower Type ¦ Tower Weight ¦ Gang Name ¦ Starting Date ¦ Completion Date ¦ Remarks 1 ¦ 77/2 ¦ DA+3 ¦ 11.145 ¦ Dipak ¦ 2025-06-23 00:00:00 ¦ 2025-06-28 00:00:00 ¦ Completed 2 ¦ 77/4 ¦ DA+3 ¦ 11.997 ¦ Dipak ¦ 2025-06-28 00:00:00 ¦ 2025-07-02 00:00:00 ¦ Completed 3 ¦ 75/7 ¦ DA+0 ¦ 11.145 ¦ Srikarni ¦ 2025-06-29 00:00:00 ¦ 2025-07-05 00:00:00 ¦ Completed 4 ¦ 77/5 ¦ DA+6 ¦ 13.072 ¦ Dipak ¦ 2025-07-03 00:00:00 ¦ 2025-07-05 00:00:00 ¦ Completed | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Completion date | 509 | 12 | earthing_tack, erection, foundation, project_details | R1: Location no ¦ Tower type ¦ FDN TYPE ¦ FDN CMP date ¦ Erection CMP Date ¦ Earthing CMP Date | Location no ¦ Tower type ¦ FDN TYPE ¦ FDN CMP date ¦ Erection CMP Date ¦ Earthing CMP Date GANTRY ¦ GE ¦ #N/A ¦ #N/A ¦ #N/A ¦ #N/A 1/0 ¦ DE+0 ¦ #N/A ¦ #N/A ¦ #N/A ¦ #N/A 1A/0 ¦ DD+0 ¦ #N/A ¦ #N/A ¦ #N/A ¦ #N/A 2/0 ¦ DD+0 ¦ DFR ¦ 2026-05-02 00:00:00 ¦ #N/A ¦ #N/A 2/1 ¦ Gantry UCS ¦ #N/A ¦ #N/A ¦ #N/A ¦ #N/A 3/0 ¦ Gantry UCS ¦ #N/A ¦ #N/A ¦ #N/A ¦ #N/A 3/1 ¦ DD+3 ¦ DFR ¦ 2026-04-07 00:00:00 ¦ #N/A ¦ #N/A | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection Compiled | 240 | 50 | erection, project_details, summary_status | R1: SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ No of Fitters ¦ Tower Tightning ¦ Remark | SL No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Starting Date ¦ Tower Weight ¦ Status ¦ Completion Date ¦ Gang Name ¦ Gang Strength ¦ No of Fitters ¦ Tower Tightning ¦ Remark 1 ¦ 77/2 ¦ DA+3 ¦ 2025-06-23 00:00:00 ¦ 11.997 ¦ COMPLETE ¦ 2025-06-28 00:00:00 ¦ Dipak 2 ¦ 77/4 ¦ DA+3 ¦ 2025-06-28 00:00:00 ¦ 11.997 ¦ COMPLETE ¦ 2025-07-02 00:00:00 ¦ Dipak 3 ¦ 75/7 ¦ DA+0 ¦ 2025-06-29 00:00:00 ¦ 11.145 ¦ COMPLETE ¦ 2025-07-05 00:00:00 ¦ Srikarni 4 ¦ 77/5 ¦ DA+6 ¦ 2025-07-03 00:00:00 ¦ 13.687 ¦ COMPLETE ¦ 2025-07-05 00:00:00 ¦ Dipak 5 ¦ 77/3 ¦ DA+0 ¦ 2025-07-07 00:00:00 ¦ 11.145 ¦ COMPLETE ¦ 2025-07-10 00:00:00 ¦ Dipak 6 ¦ 77/1 ¦ DA+0 ¦ 2025-07-11 00:00:00 ¦ 11.145 ¦ COMPLETE ¦ 2025-07-14 00:00:00 ¦ Dipak 7 ¦ 75/6 ¦ DA+0 ¦ 2025-07-15 00:00:00 ¦ 11.145 ¦ COMPLETE ¦ 2025-07-18 00:00:00 ¦ Dipak | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Earthing | 277 | 23 | earthing_tack, foundation, project_details | R5: SL. No. ¦ Location Number ¦ Tower Type ¦ Foundation type ¦ Completion Date ¦ Remarks | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED SL. No. ¦ Location Number ¦ Tower Type ¦ Foundation type ¦ Completion Date ¦ Remarks 1 ¦ 75/7 ¦ DA+0 ¦ Sandy ¦ 2025-01-28 00:00:00 ¦ Complete ¦ RA-2 2 ¦ 75/6 ¦ DA+0 ¦ Sandy ¦ 2025-02-03 00:00:00 ¦ Complete ¦ RA-2 3 ¦ 75/3 ¦ DA+3 ¦ Sandy ¦ 2025-02-09 00:00:00 ¦ Complete ¦ RA-2 4 ¦ 77/5 ¦ DA+6 ¦ Sandy ¦ 2025-02-20 00:00:00 ¦ Complete ¦ RA-2 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Final Check In And Tack Welding | 145 | 11 | earthing_tack | R4: SL No ¦ Loc No ¦ TOT ¦ Final Checking ¦ Tack Welding ¦ NB Qty R29: 25 ¦ 86/0 ¦ DD+0 ¦ ROW R56: 52 ¦ 131/0 ¦ DD+0 ¦ DONE ¦ ROW R57: 53 ¦ 131/1 ¦ DA+3 ¦ DONE ¦ ROW R80: 76 ¦ 135/1 ¦ DA+0 ¦ DONE ¦ ROW | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED SL No ¦ Loc No ¦ TOT ¦ Final Checking ¦ Tack Welding ¦ NB Qty 1 ¦ 65/0 ¦ DD+0 ¦ DONE 2 ¦ 65/1 ¦ DB+9 ¦ DONE 3 ¦ 66/0 ¦ DD+0 ¦ DONE 4 ¦ 75/1 ¦ DA+0 ¦ WIP | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet10 | 23 | 16 | project_details, statutory_crossing, stringing | R2: S.no ¦ From AP ¦ To AP ¦ Section Length(M) ¦ Method ¦ P/O Completion Date ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Specering ¦ Clipping ¦ Gang Name ¦ Remarks R3: 1 ¦ 134/0 ¦ 133/0 ¦ 3486 ¦ TSE ¦ 2026-05-13 00:00:00 ¦ 2026-05-15 00:00:00 ¦ Pending ¦ Pending ¦ Completed ¦ Mahadev Enterprises ¦ Final Sag Complete R4: 2 ¦ 144/0 ¦ 143/0 ¦ 3275 ¦ TSE ¦ 2026-04-04 00:00:00 ¦ 2026-04-04 00:00:00 ¦ Pending ¦ Completed ¦ Completed ¦ Mahadev Enterprises ¦ Final Sag Complete R5: 3 ¦ 145/0 ¦ 144/0 ¦ 232 ¦ Manual ¦ 2026-04-10 00:00:00 ¦ Pending ¦ Completed ¦ Completed ¦ Mahadev Enterprises ¦ Final Sag Complete (132 kv PLC ) R6: 4 ¦ 146/0 ¦ 145/0 ¦ 1970 ¦ TSE ¦ Ready ¦ 2026-02-14 00:00:00 ¦ 2026-02-16 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ Mahadev Enterprises | S/C Name: Mahadev Construction S.no ¦ From AP ¦ To AP ¦ Section Length(M) ¦ Method ¦ P/O Completion Date ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Specering ¦ Clipping ¦ Gang Name ¦ Remarks 1 ¦ 134/0 ¦ 133/0 ¦ 3486 ¦ TSE ¦ 2026-05-13 00:00:00 ¦ 2026-05-15 00:00:00 ¦ Pending ¦ Pending ¦ Completed ¦ Mahadev Enterprises ¦ Final Sag Complete 2 ¦ 144/0 ¦ 143/0 ¦ 3275 ¦ TSE ¦ 2026-04-04 00:00:00 ¦ 2026-04-04 00:00:00 ¦ Pending ¦ Completed ¦ Completed ¦ Mahadev Enterprises ¦ Final Sag Complete 3 ¦ 145/0 ¦ 144/0 ¦ 232 ¦ Manual ¦ 2026-04-10 00:00:00 ¦ Pending ¦ Completed ¦ Completed ¦ Mahadev Enterprises ¦ Final Sag Complete (132 kv PLC ) 4 ¦ 146/0 ¦ 145/0 ¦ 1970 ¦ TSE ¦ Ready ¦ 2026-02-14 00:00:00 ¦ 2026-02-16 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ Mahadev Enterprises 5 ¦ 149A/0 ¦ 149/0 ¦ 188 ¦ Manual ¦ 2026-03-03 00:00:00 ¦ 2026-03-03 00:00:00 ¦ 2026-03-03 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ Mahadev Enterprises ¦ Final Sag Complete 6 ¦ 149/0 ¦ 148/0 ¦ 3031 ¦ TSE ¦ 2026-02-06 00:00:00 ¦ 2026-03-16 00:00:00 ¦ 2026-03-18 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ Mahadev Enterprises ¦ Final Sag Complete | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing Compiled | 28 | 23 | project_details, statutory_crossing, stretch_readiness, stringing, summary_status | R3: S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos. ¦ Span (M) ¦ Method ¦ Section Readiness ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Specering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name ¦ Manpower R4: 1 ¦ Bhinmal ¦ 146/0 ¦ 145/0 ¦ 145/1,2,3,4,5 ¦ 1970 ¦ TSE ¦ Ready ¦ 2026-02-14 00:00:00 ¦ 2026-02-16 00:00:00 ¦ 2026-02-20 00:00:00 ¦ 2026-02-22 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 1970 ¦ complete ¦ Mahadev Enterprises ¦ Final Sag Complete R5: 2 ¦ Bhinmal ¦ 149A/0 ¦ 149/0 ¦ 149/0 ¦ 188 ¦ Manual ¦ Ready ¦ 2026-03-01 00:00:00 ¦ 2026-03-03 00:00:00 ¦ 2026-03-03 00:00:00 ¦ 2026-03-03 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 188 ¦ complete ¦ Mahadev Enterprises ¦ Final Sag Complete R6: 3 ¦ Bhinmal ¦ 149/0 ¦ 148/0 ¦ 148/1,2,3,4,5,6,7 ¦ 3031 ¦ TSE ¦ Ready ¦ 2026-02-01 00:00:00 ¦ 2026-02-06 00:00:00 ¦ 2026-03-16 00:00:00 ¦ 2026-03-18 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 3031 ¦ complete ¦ Mahadev Enterprises ¦ Final Sag Complete R7: 4 ¦ Bhinmal ¦ 150/0 ¦ 149B/3 ¦ 149B/3 ¦ 489 ¦ Manual ¦ Ready ¦ 2026-02-26 00:00:00 ¦ 2026-02-27 00:00:00 ¦ 2026-03-08 00:00:00 ¦ 2026-03-08 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 489 ¦ complete ¦ Mahadev Enterprises ¦ Final Sag Complete | Number of TSE ¦ 1 S.no ¦ Sec ¦ From AP ¦ To AP ¦ Location Nos. ¦ Span (M) ¦ Method ¦ Section Readiness ¦ P/O Starting Date ¦ P/O Completion Date ¦ P/O ¦ F/S Starting Date ¦ F/S/ Completion Date ¦ Jumpering ¦ Specering ¦ Clipping ¦ Length ¦ Status ¦ Gang Name ¦ Manpower 1 ¦ Bhinmal ¦ 146/0 ¦ 145/0 ¦ 145/1,2,3,4,5 ¦ 1970 ¦ TSE ¦ Ready ¦ 2026-02-14 00:00:00 ¦ 2026-02-16 00:00:00 ¦ 2026-02-20 00:00:00 ¦ 2026-02-22 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 1970 ¦ complete ¦ Mahadev Enterprises ¦ Final Sag Complete 2 ¦ Bhinmal ¦ 149A/0 ¦ 149/0 ¦ 149/0 ¦ 188 ¦ Manual ¦ Ready ¦ 2026-03-01 00:00:00 ¦ 2026-03-03 00:00:00 ¦ 2026-03-03 00:00:00 ¦ 2026-03-03 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 188 ¦ complete ¦ Mahadev Enterprises ¦ Final Sag Complete 3 ¦ Bhinmal ¦ 149/0 ¦ 148/0 ¦ 148/1,2,3,4,5,6,7 ¦ 3031 ¦ TSE ¦ Ready ¦ 2026-02-01 00:00:00 ¦ 2026-02-06 00:00:00 ¦ 2026-03-16 00:00:00 ¦ 2026-03-18 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 3031 ¦ complete ¦ Mahadev Enterprises ¦ Final Sag Complete 4 ¦ Bhinmal ¦ 150/0 ¦ 149B/3 ¦ 149B/3 ¦ 489 ¦ Manual ¦ Ready ¦ 2026-02-26 00:00:00 ¦ 2026-02-27 00:00:00 ¦ 2026-03-08 00:00:00 ¦ 2026-03-08 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 489 ¦ complete ¦ Mahadev Enterprises ¦ Final Sag Complete 5 ¦ Bhinmal ¦ 149B/0 ¦ 149A/0 ¦ 149A/0 ¦ 396 ¦ Manual ¦ Ready ¦ 2026-03-05 00:00:00 ¦ 2026-03-05 00:00:00 ¦ 2026-03-10 00:00:00 ¦ 2026-03-10 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 396 ¦ complete ¦ Mahadev Enterprises ¦ Final Sag Complete 6 ¦ Bhinmal ¦ 149B/3 ¦ 149B/0 ¦ 149B/0,1,2 ¦ 1265 ¦ TSE ¦ Ready ¦ 2026-03-05 00:00:00 ¦ 2026-03-09 00:00:00 ¦ 2026-03-08 00:00:00 ¦ 2026-03-10 00:00:00 ¦ Completed ¦ Completed ¦ Completed ¦ 1265 ¦ complete ¦ Mahadev Enterprises ¦ Final Sag Complete | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Soil Investigation | 79 | 19 | summary_status, survey_soil | R5: SL No. ¦ LOC. No. ¦ Tower Type ¦ Soil Investigation date ¦ Recommended Soil classification ¦ Remarks R61: 56 ¦ 133/1 ¦ DC+0 ¦ 2025-01-18 00:00:00 ¦ River Crossing R62: 57 ¦ 133/2 ¦ DA+0 ¦ 2025-01-18 00:00:00 ¦ River Crossing | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED SOIL INVESTIGATION STATUS SL No. ¦ LOC. No. ¦ Tower Type ¦ Soil Investigation date ¦ Recommended Soil classification ¦ Remarks 1 ¦ 3/0 ¦ DD+25 ¦ 2025-02-01 00:00:00 2 ¦ 4/0 ¦ DC+0 ¦ 2025-02-01 00:00:00 3 ¦ 6/0 ¦ DD+18 ¦ 2025-01-31 00:00:00 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet9 | 319 | 45 | earthing_tack, erection, foundation, statutory_crossing, stringing, summary_status, survey_soil, visual_l2 | R5: Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed ¦ Balance ¦ River Crossing R7: 1 ¦ Detail survey ¦ Kms. ¦ 188.444 ¦ 188.444 R8: 2 ¦ Check survey ¦ Kms. ¦ 188.444 ¦ 178.075 ¦ 10.369 R10: 4 ¦ Soil Investigation ¦ Loc ¦ 73 ¦ 73 R11: 5 ¦ Foundation ¦ Loc ¦ 512 ¦ 208 ¦ 304 ¦ Erection WIP | 400 KV D/C (TWIN) FATEHGARH IV - BHINMAL (PG) TRANSMISSION LINE (VISUAL CHART) Name of Contractor:M/S KEC INTERNATIONAL LIMITED ¦ AS ON ¦ 2026-05-20 10:56:36.910000 PROGRESS AT A GLANCE : Stringing WIP ¦ Stringing Completed Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed ¦ Balance ¦ River Crossing 1 ¦ Detail survey ¦ Kms. ¦ 188.444 ¦ 188.444 2 ¦ Check survey ¦ Kms. ¦ 188.444 ¦ 178.075 ¦ 10.369 3 ¦ CS Approval ¦ Kms. ¦ 188.444 ¦ 178.075 ¦ 10.369 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | VC | 314 | 37 | earthing_tack, erection, foundation, statutory_crossing, stringing, summary_status, survey_soil | R6: Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ River Crossing R8: 1 ¦ Detail survey ¦ Kms. ¦ 187.175 ¦ 187.175 ¦ Oil pipeline R9: 2 ¦ Check survey ¦ Kms. ¦ 187.175 ¦ 169.168 ¦ 18.007000000000005 ¦ Gas pipeline R10: 3 ¦ Soil Investigation ¦ Loc ¦ 73 ¦ 73 R11: 4 ¦ Foundation ¦ Loc ¦ 495 ¦ 79 ¦ 416 ¦ Erection WIP | 52 2026-05-20 10:56:36.910000 Name of Contractor:M/S KEC INTERNATIONAL LIMITED PROGRESS AT A GLANCE : Stringing WIP ¦ Stringing Completed Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed Till Date ¦ Balance ¦ River Crossing 1 ¦ Detail survey ¦ Kms. ¦ 187.175 ¦ 187.175 ¦ Oil pipeline 2 ¦ Check survey ¦ Kms. ¦ 187.175 ¦ 169.168 ¦ 18.007000000000005 ¦ Gas pipeline | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet6 | 42 | 9 |  | R3: SL No ¦ Loc No ¦ TOT ¦ Classificatin ¦ M-10 ¦ M-20 | SL No ¦ Loc No ¦ TOT ¦ Classificatin ¦ M-10 ¦ M-20 1 ¦ 83/1 ¦ DA+3 ¦ Sandy ¦ 1.86 ¦ 12.47 2 ¦ 75/7 ¦ DA+0 ¦ Sandy ¦ 1.57 ¦ 11.05 3 ¦ 75/6 ¦ DA+0 ¦ Sandy ¦ 1.57 ¦ 11.05 4 ¦ 75/5 ¦ DA+0 ¦ Sandy ¦ 1.57 ¦ 11.05 5 ¦ 75/4 ¦ DA+0 ¦ Sandy ¦ 1.57 ¦ 11.05 6 ¦ 75/3 ¦ DA+3 ¦ Sandy ¦ 1.86 ¦ 12.47 7 ¦ 75/1 ¦ DA+0 ¦ Sandy ¦ 1.57 ¦ 11.05 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | VC 51-121 | 225 | 44 | earthing_tack, erection, foundation, stringing, summary_status, survey_soil, visual_l2 | R4: DPR- ¦ As per Approved Check Survey ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing | TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line DPR and VISUAL CHART DPR- ¦ As per Approved Check Survey ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing Com ¦ WIP ¦ Bal ¦ Com ¦ Com ¦ WIP ¦ Bal ¦ Com ¦ WIP ¦ Bal AP 51- AP 121 ¦ 196 ¦ 74.398 ¦ 39 ¦ 4 ¦ 153 ¦ 25 ¦ 196 ¦ 74.398 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ 9 DA ¦ DB ¦ DC 465.03 ¦ 375.98 ¦ 414.86 ¦ 381.02 ¦ 353.63 ¦ 351.4 ¦ 433.26 ¦ 396.56 ¦ 408.11 ¦ 3579.8500000000004 ¦ +0 ¦ +3 ¦ +6 ¦ +9 ¦ +0 ¦ +3 ¦ +6 ¦ +9 ¦ +0 ¦ +3 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet5 | 38 | 10 |  | R3: Sl.No. ¦ Loc.No. ¦ Tower Type ¦ Tower Leg ¦ Remarks | Sl.No. ¦ Loc.No. ¦ Tower Type ¦ Tower Leg ¦ Remarks A ¦ B ¦ C ¦ D 1 ¦ AP52 ¦ DB+0 ¦ 2 ¦ 3 ¦ 3 ¦ 3 ¦ 3 2 ¦ 52/1 ¦ DA+6 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 3 ¦ 54/2 ¦ DA+6 ¦ Benching & RC Required ¦ - ¦ - ¦ 1 ¦ - 4 ¦ 54/3 ¦ DA+3 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 5 ¦ AP55 ¦ DD+18 ¦ 3 ¦ 3 ¦ 3 ¦ 3 ¦ 3 6 ¦ AP56 ¦ DB+9 ¦ Benching & RC Required ¦ 3 ¦ 3 ¦ 3 ¦ 3 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet3 | 242 | 22 | earthing_tack, erection, foundation, stringing, summary_status, survey_soil, visual_l2 | R4: DPR- ¦ As per Approved Check Survey ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing | TB-507 400 KV (Twin) D/C Fatehgarh IV - Bhinmal Transmission Line DPR and VISUAL CHART DPR- ¦ As per Approved Check Survey ¦ No.Of Towers ¦ Length ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Stringing Com ¦ WIP ¦ Bal ¦ Com ¦ Com ¦ WIP ¦ Bal ¦ Com ¦ WIP ¦ Bal AP 51- AP 121 ¦ 171 ¦ 74 ¦ 34 ¦ 3 ¦ 134 ¦ 21 ¦ 171 ¦ 74 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ 9 465.03 ¦ 375.98 ¦ 414.86 ¦ 381.02 ¦ 353.63 ¦ 351.4 ¦ 433.26 ¦ 396.56 ¦ 408.11 ¦ 3579.8500000000004 AP51 ¦ 51/1 ¦ 51/2 ¦ 51/3 ¦ AP52 ¦ 52/1 ¦ AP53 ¦ AP54 ¦ 54/1 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Tower Schedule | 142 | 29 | statutory_crossing, survey_soil, visual_l2 | R7: Sl. No ¦ Twr No. ¦ Tower Type ¦ Raise Chimney ¦ Deviation Angle (DMS) ¦ Span (m) ¦ Section Length (M) ¦ Sl. No ¦ Twr No. ¦ Tower Type ¦ Raise Chimney ¦ Ground Cutting Length X Height ¦ Deviation Angle (DMS) ¦ Span (m) ¦ Section Length (M) ¦ Sum of Adjacent Span ¦ Wind Span (m) ¦ Weight Span (Cold) ¦ Weight Span (Hot) ¦ Major Crossings /Remarks | NAME OF PROJECT : FARHEGARH IV-BHINMAL 400KV D/C TRANSMISSION LINE Client : RAJASTHAN IV A POWER TRANSMISSION LTD. CONTRACTOR : KEC INTERNATIONAL LIMITED CHECK SURVEY Tower Schedule from AP-75/0 to AP-92/0 (Section Length = 20.273 kms) AS PER DETAILED SURVEY ¦ AS PER CHECK SURVEY Sl. No ¦ Twr No. ¦ Tower Type ¦ Raise Chimney ¦ Deviation Angle (DMS) ¦ Span (m) ¦ Section Length (M) ¦ Sl. No ¦ Twr No. ¦ Tower Type ¦ Raise Chimney ¦ Ground Cutting Length X Height ¦ Deviation Angle (DMS) ¦ Span (m) ¦ Section Length (M) ¦ Sum of Adjacent Span ¦ Wind Span (m) ¦ Weight Span (Cold) ¦ Weight Span (Hot) ¦ Major Crossings /Remarks Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Left ¦ Right ¦ Total ¦ Easting ¦ Northing ¦ Elevation | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Visual Chart | 472 | 39 | earthing_tack, erection, foundation, statutory_crossing, stringing, summary_status, survey_soil, visual_l2 | R5: Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed ¦ Balance R7: 1 ¦ Detail survey ¦ Kms. ¦ 188.678 ¦ 188.678 ¦ Rly. X-ing R8: 2 ¦ Check survey ¦ Kms. ¦ 188.678 ¦ 188.678 ¦ Erection WIP R10: 4 ¦ Soil Investigation ¦ Loc ¦ 73 ¦ 73 ¦ River Crossing ¦ Span R11: 5 ¦ Foundation ¦ Loc ¦ 513 ¦ 304 ¦ 209 | 400 KV D/C (TWIN) FATEHGARH IV - BHINMAL (PG) TRANSMISSION LINE (VISUAL CHART) Name of Contractor:M/S KEC INTERNATIONAL LIMITED ¦ AS ON ¦ 2026-05-20 10:56:36.900000 PROGRESS AT A GLANCE : Stringing WIP ¦ Stringing Completed Sl. No. ¦ Activity ¦ UoM ¦ Total Qty ¦ Completed ¦ Balance SH ¦ NH 1 ¦ Detail survey ¦ Kms. ¦ 188.678 ¦ 188.678 ¦ Rly. X-ing 2 ¦ Check survey ¦ Kms. ¦ 188.678 ¦ 188.678 ¦ Erection WIP | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | L2 Vs Actual Progress Chart | 308 | 29 | foundation, row_hindrance, statutory_crossing, summary_status, survey_soil, visual_l2 | R3: Sl. No. ¦ ACTIVITY ¦ Responsibility ¦ Sch. Start date ¦ Sch. Finish date ¦ Days ¦ Unit ¦ Quantity ¦ Dec'24 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 ¦ Jun'25 ¦ Jul'25 ¦ Aug'25 ¦ Sep'25 ¦ Oct'25 ¦ Nov'25 R8: Check Survey Submission & Approval ¦ KEC & Apraava ¦ 2025-01-05 00:00:00 ¦ 2025-04-15 00:00:00 ¦ 100 ¦ Kms. ¦ 184 ¦ 20 ¦ 60 ¦ 60 ¦ 44 R9: 5.a ¦ ROW clearance and front avaibility for Civil foundation ¦ Apraava ¦ 25.12.24 ¦ 30.12.25 ¦ #VALUE! ¦ Loc. ¦ 508 ¦ 5 ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 45 ¦ 48 ¦ 50 R10: 5.b ¦ Foundation Work execution ¦ KEC ¦ 2025-01-07 00:00:00 ¦ 2026-01-26 00:00:00 ¦ 384 ¦ Loc. ¦ 508 ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 30 ¦ 25 ¦ 25 ¦ 48 ¦ 45 ¦ 50 R11: Note ¦ ROW / Way leave clearance / Forest clearance / Tree Cutting clearance / any other Statutory clearance to be arranged suitably ahead of respective work schedule by ¦ 185 | NAME OF LINE: 400kV Transmisison Line Fatehgarh IV to Bhinmal As Per L2 Sl. No. ¦ ACTIVITY ¦ Responsibility ¦ Sch. Start date ¦ Sch. Finish date ¦ Days ¦ Unit ¦ Quantity ¦ Dec'24 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 ¦ Jun'25 ¦ Jul'25 ¦ Aug'25 ¦ Sep'25 ¦ Oct'25 ¦ Nov'25 M0 ¦ M1 ¦ M2 ¦ M3 ¦ M4 ¦ M5 ¦ M6 ¦ M7 ¦ M8 ¦ M9 ¦ M10 ¦ M11 ¦ M12 ¦ M13 ¦ M14 ¦ M15 ¦ M16 ¦ M17 ¦ M18 1 ¦ Notice of Award ¦ KEC & Apraava ¦ 2024-12-06 00:00:00 ¦ 2026-06-05 00:00:00 ¦ 546 Services 1 ¦ Establishment of site office ¦ KEC ¦ 2024-12-16 00:00:00 ¦ 2025-01-15 00:00:00 ¦ 30 ¦ LS Check Survey Submission & Approval ¦ KEC & Apraava ¦ 2025-01-05 00:00:00 ¦ 2025-04-15 00:00:00 ¦ 100 ¦ Kms. ¦ 184 ¦ 20 ¦ 60 ¦ 60 ¦ 44 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | L2 Vs Actual Progress Chart (2) | 25 | 27 | foundation, row_hindrance, statutory_crossing, summary_status, survey_soil, visual_l2 | R3: Sl. No. ¦ ACTIVITY ¦ Responsibility ¦ Sch. Start date ¦ Sch. Finish date ¦ Days ¦ Unit ¦ Quantity ¦ Dec'24 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 ¦ Jun'25 ¦ Jul'25 ¦ Aug'25 ¦ Sep'25 ¦ Oct'25 ¦ Nov'25 R8: Check Survey Submission & Approval ¦ KEC & Apraava ¦ 2025-01-05 00:00:00 ¦ 2025-04-15 00:00:00 ¦ 100 ¦ Kms. ¦ 184 ¦ 20 ¦ 60 ¦ 60 ¦ 44 R9: 5.a ¦ ROW clearance and front avaibility for Civil foundation ¦ Apraava ¦ 25.12.24 ¦ 30.12.25 ¦ #VALUE! ¦ Loc. ¦ 508 ¦ 5 ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 45 ¦ 48 ¦ 50 R10: 5.b ¦ Foundation Work execution ¦ KEC ¦ 2025-01-07 00:00:00 ¦ 2026-01-26 00:00:00 ¦ 384 ¦ Loc. ¦ 508 ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 30 ¦ 25 ¦ 25 ¦ 48 ¦ 45 ¦ 50 R18: Sl. No. ¦ ACTIVITY ¦ Responsibility ¦ Sch. Start date ¦ Sch. Finish date ¦ Days ¦ Unit ¦ Quantity ¦ Dec'24 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 ¦ Jun'25 ¦ Jul'25 ¦ Aug'25 ¦ Sep'25 ¦ Oct'25 ¦ Nov'25 | NAME OF LINE: 400kV Transmisison Line Fatehgarh IV to Bhinmal As Per L2 Sl. No. ¦ ACTIVITY ¦ Responsibility ¦ Sch. Start date ¦ Sch. Finish date ¦ Days ¦ Unit ¦ Quantity ¦ Dec'24 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 ¦ Jun'25 ¦ Jul'25 ¦ Aug'25 ¦ Sep'25 ¦ Oct'25 ¦ Nov'25 M0 ¦ M1 ¦ M2 ¦ M3 ¦ M4 ¦ M5 ¦ M6 ¦ M7 ¦ M8 ¦ M9 ¦ M10 ¦ M11 ¦ M12 ¦ M13 ¦ M14 ¦ M15 ¦ M16 ¦ M17 ¦ M18 1 ¦ Notice of Award ¦ KEC & Apraava ¦ 2024-12-06 00:00:00 ¦ 2026-06-05 00:00:00 ¦ 546 Services 1 ¦ Establishment of site office ¦ KEC ¦ 2024-12-16 00:00:00 ¦ 2025-01-15 00:00:00 ¦ 30 ¦ LS Check Survey Submission & Approval ¦ KEC & Apraava ¦ 2025-01-05 00:00:00 ¦ 2025-04-15 00:00:00 ¦ 100 ¦ Kms. ¦ 184 ¦ 20 ¦ 60 ¦ 60 ¦ 44 | ok
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet4 | 13 | 21 | foundation, row_hindrance, summary_status, survey_soil, visual_l2 | R6: Check Survey (Kms) ¦ 20 ¦ 60 ¦ 60 ¦ 44 R8: Foundation (Nos) ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 30 ¦ 25 ¦ 25 ¦ 48 ¦ 45 ¦ 50 ¦ 48 R9: ROW Front Clearence ¦ 5 ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 45 ¦ 48 ¦ 50 ¦ 45 | Activity ¦ As Per L2 Dec'24 ¦ Jan'25 ¦ Feb'25 ¦ Mar'25 ¦ Apr'25 ¦ May'25 ¦ Jun'25 ¦ Jul'25 ¦ Aug'25 ¦ Sep'25 ¦ Oct'25 ¦ Nov'25 ¦ Dec'25 ¦ Jan'26 ¦ Feb'26 ¦ Mar'26 ¦ Apr'26 ¦ May'26 ¦ June'26 Check Survey (Kms) ¦ 20 ¦ 60 ¦ 60 ¦ 44 Actual Progress ¦ 28 Foundation (Nos) ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 30 ¦ 25 ¦ 25 ¦ 48 ¦ 45 ¦ 50 ¦ 48 ROW Front Clearence ¦ 5 ¦ 35 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 40 ¦ 45 ¦ 48 ¦ 50 ¦ 45 Actual Foundation Completed (Nos) ¦ 3 WIP ¦ 2 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | TB401 DPR..... | 14 | 263 | earthing_tack, erection, foundation, project_details, row_hindrance, summary_status, supply, survey_soil, visual_l2 | R1: Project Code ¦ TB-401 ¦ Date ¦ 2026-05-21 00:00:00 ¦ LOA Start Date ¦ 2023-04-25 00:00:00 ¦ Business Head (T&D)- India & Sri Lanka ¦ Rajinder Gupta R2: Project Name ¦ 765KV D/C Fategarh-III Beawar Transmission Line ¦ LOA End Date ¦ 2024-07-25 00:00:00 ¦ PCH ¦ Sivaraman Nataraajan R4: LE Value ¦ Rs 312 Cr -Supply -Rs 227.5 Cr.; Service.-Rs 84.4 Cr ¦ Planning ¦ Shah Ali Khan ¦ Project Manager ¦ Virender Gupta R5: Activity ¦ Unit ¦ LOA Qty. ¦ LE Qty ¦ Progress till Last Month ¦ Balance ¦ L2 for Dec'23 ¦ Plan for Dec.'23 ¦ Today's Progress ¦ Month Progress ¦ WIP ¦ Gangs at Present ¦ L2 Till Month-Dec.23 ¦ Progress Till Date ¦ Balance Work ¦ Remarks R6: Route Alignment ¦ km ¦ 215 ¦ 202 ¦ 167 ¦ 35 ¦ 35 ¦ 215 ¦ 167 ¦ 35 ¦ 35 Km is hold due to ROW issues | Project Code ¦ TB-401 ¦ Date ¦ 2026-05-21 00:00:00 ¦ LOA Start Date ¦ 2023-04-25 00:00:00 ¦ Business Head (T&D)- India & Sri Lanka ¦ Rajinder Gupta Project Name ¦ 765KV D/C Fategarh-III Beawar Transmission Line ¦ LOA End Date ¦ 2024-07-25 00:00:00 ¦ PCH ¦ Sivaraman Nataraajan Client Name ¦ Strelite Power ¦ Time Extn ¦ 2024-07-25 00:00:00 ¦ Regional Manager ¦ Sandeep Singh Kumar LE Value ¦ Rs 312 Cr -Supply -Rs 227.5 Cr.; Service.-Rs 84.4 Cr ¦ Planning ¦ Shah Ali Khan ¦ Project Manager ¦ Virender Gupta Activity ¦ Unit ¦ LOA Qty. ¦ LE Qty ¦ Progress till Last Month ¦ Balance ¦ L2 for Dec'23 ¦ Plan for Dec.'23 ¦ Today's Progress ¦ Month Progress ¦ WIP ¦ Gangs at Present ¦ L2 Till Month-Dec.23 ¦ Progress Till Date ¦ Balance Work ¦ Remarks Route Alignment ¦ km ¦ 215 ¦ 202 ¦ 167 ¦ 35 ¦ 35 ¦ 215 ¦ 167 ¦ 35 ¦ 35 Km is hold due to ROW issues Detailed Survey ¦ km ¦ 215 ¦ 202 ¦ 202 ¦ 215 ¦ 202 ¦ SPTL Approved -202/202-Kms Check Survey ¦ km ¦ 215 ¦ 202 ¦ 92.704 ¦ 109.296 ¦ 20 ¦ 50 ¦ 17.852 ¦ 160 ¦ 110.556 ¦ 91.444 ¦ 1. Total 7.854 Km is under review of SPTL. 2. Total check survey completed (Field work) 167 Km. 3. Total 60 Km check survey is hold due to row issues & Other issues. | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Eng. | 9 | 11 | foundation, summary_status, supply | R2: Tower ¦ Tower Design ¦ Test Tower ¦ Balance Structural Drawing. ¦ Tower ¦ Stub & Template Drawings ¦ Foundation R4: Target ¦ Status ¦ Target ¦ Status ¦ Target ¦ Status ¦ Target ¦ Status R5: DA Tower ¦ 2023-05-12 00:00:00 ¦ Approved ¦ 2023-06-04 00:00:00 ¦ Approved ¦ 2023-06-24 00:00:00 ¦ Approved for proto ¦ Completed ¦ Approved ¦ 15-July ¦ Approved R6: DB Tower ¦ 2023-05-30 00:00:00 ¦ Approved ¦ 2023-07-30 00:00:00 ¦ Approved ¦ 2023-07-19 00:00:00 ¦ Approvedin Cat-B ¦ Completed ¦ Approved for Proto ¦ DB all Fdn. By 25 -July ¦ Approved R8: DD Tower ¦ 2023-06-21 00:00:00 ¦ Approved ¦ 30-Sept. ¦ Approved in Cat -B ¦ 2023-08-20 00:00:00 ¦ Approved in Cat -B ¦ Completed ¦ Approved in Cat -B ¦ 2023-07-31 00:00:00 ¦ Approved | Tower ¦ Tower Design ¦ Test Tower ¦ Balance Structural Drawing. ¦ Tower ¦ Stub & Template Drawings ¦ Foundation Types ¦ Structural Drawing(BTB+0) ¦ (3M/6M/9M) ¦ Testing ¦ Design/Drg Target ¦ Status ¦ Target ¦ Status ¦ Target ¦ Status ¦ Target ¦ Status DA Tower ¦ 2023-05-12 00:00:00 ¦ Approved ¦ 2023-06-04 00:00:00 ¦ Approved ¦ 2023-06-24 00:00:00 ¦ Approved for proto ¦ Completed ¦ Approved ¦ 15-July ¦ Approved DB Tower ¦ 2023-05-30 00:00:00 ¦ Approved ¦ 2023-07-30 00:00:00 ¦ Approved ¦ 2023-07-19 00:00:00 ¦ Approvedin Cat-B ¦ Completed ¦ Approved for Proto ¦ DB all Fdn. By 25 -July ¦ Approved DD Tower ¦ 2023-06-21 00:00:00 ¦ Approved ¦ 30-Sept. ¦ Approved in Cat -B ¦ 2023-08-20 00:00:00 ¦ Approved in Cat -B ¦ Completed ¦ Approved in Cat -B ¦ 2023-07-31 00:00:00 ¦ Approved DC Tower ¦ 2023-07-16 00:00:00 ¦ Approved ¦ 2023-10-08 00:00:00 ¦ Approved in Cat -B ¦ 2023-09-19 00:00:00 ¦ Approved in Cat -B ¦ Completed ¦ Approved in Cat -B ¦ 2023-08-25 00:00:00 ¦ Approved | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Fdn (Pkg -G Section -I) | 12 | 13 | foundation | R4: Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Excavation Start ¦ Dt. of Start ¦ Dt. of Concrete ¦ Name of Sub-Contractor ¦ KEC representative ¦ KEC Section In-Charge ¦ Remarks | KEC INTERNATIONAL LIMITED ¦ Date: ¦ 2026-05-21 00:00:00 LILO of 765 Kv DV Fatehgarh 3 Beawar TL FOUNDATION Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Excavation Start ¦ Dt. of Start ¦ Dt. of Concrete ¦ Name of Sub-Contractor ¦ KEC representative ¦ KEC Section In-Charge ¦ Remarks 1 ¦ 1 ¦ 32/7 ¦ DA+0 ¦ SANDY ¦ 23.10.23 ¦ 25.10.23 ¦ 28.10.23 ¦ Shakti Construction ¦ Kumar Nayak ¦ Jish C Verghese ¦ Complete 2 ¦ 2 ¦ 32/5 ¦ DA+6 ¦ SANDY ¦ 29.10.23 ¦ 31.10.23 ¦ 04.11.2023 ¦ Shakti Construction ¦ Kumar Nayak ¦ Jish C Verghese ¦ Complete 3 ¦ 3 ¦ 32/1 ¦ DA+9 ¦ SANDY ¦ 03.11.23 ¦ 06.11.23 ¦ 10.11.23 ¦ Shakti Construction ¦ Kumar Nayak ¦ Jish C Verghese ¦ Complete 4 ¦ 4 ¦ 30/2 ¦ DA+0 ¦ SANDY ¦ 13.11.23 ¦ 15.11.23 ¦ 16.11.23 ¦ Shakti Construction ¦ Kumar Nayak ¦ Jish C Verghese ¦ Complete | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet2 | 23 | 21 | foundation, project_details, row_hindrance, survey_soil, visual_l2 | R2: S.No ¦ Line ¦ Activity ¦ UOM ¦ LOA Qty ¦ L2 till Sep'25 ¦ Completed till Date ¦ Balance ¦ WIP ¦ Gangs ¦ Remarks R3: 1 ¦ Samba- Jalandhar ¦ Survey ¦ Km ¦ 144 ¦ 70 ¦ 129.35999999999999 ¦ 14.640000000000015 ¦ 2 R4: Foundation ¦ Nos ¦ 434 ¦ 17 ¦ 2 ¦ 432 ¦ 4 ¦ 3 R5: 2 ¦ Kishepur- Samba ¦ Survey ¦ Km ¦ 33.103 ¦ 20 ¦ 8.56 ¦ 24.543 ¦ 0.3 ¦ 1 R6: Foundation ¦ Nos ¦ 129 ¦ 129 | S.No ¦ Line ¦ Activity ¦ UOM ¦ LOA Qty ¦ L2 till Sep'25 ¦ Completed till Date ¦ Balance ¦ WIP ¦ Gangs ¦ Remarks 1 ¦ Samba- Jalandhar ¦ Survey ¦ Km ¦ 144 ¦ 70 ¦ 129.35999999999999 ¦ 14.640000000000015 ¦ 2 Foundation ¦ Nos ¦ 434 ¦ 17 ¦ 2 ¦ 432 ¦ 4 ¦ 3 2 ¦ Kishepur- Samba ¦ Survey ¦ Km ¦ 33.103 ¦ 20 ¦ 8.56 ¦ 24.543 ¦ 0.3 ¦ 1 Foundation ¦ Nos ¦ 129 ¦ 129 3 ¦ LILO-Kisthwar ¦ Survey ¦ Km ¦ 2.18 ¦ 2.18 ¦ 2.18 Foundation ¦ Nos ¦ 14 ¦ 6 ¦ 14 Total ¦ Survey ¦ Km ¦ 179.28300000000002 ¦ 92.18 ¦ 140.1 ¦ 39.18300000000002 ¦ 0.3 ¦ 3 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet3 | 12 | 12 | foundation, row_hindrance, visual_l2 | R2: Line ¦ Activity ¦ Section ¦ L2 Oct'25 ¦ Plan Oct'25 ¦ L2 Nov'25 ¦ Plan Nov'25 ¦ L2 Dec'25 ¦ Plan Dec'25 ¦ L2 (Oct'25-Dec'25) ¦ Plan (Oct'25-Dec'25) R3: Samba-Jalandhar ¦ FDN ¦ Jammu ¦ 25 ¦ 10 ¦ 35 ¦ 10 ¦ 40 ¦ 20 ¦ 100 ¦ 110 R5: FDN ¦ Punjab ¦ 15 ¦ 25 ¦ 30 R7: Kishenpur-Samba ¦ FDN ¦ Jammu ¦ 2 ¦ 7 ¦ 5 ¦ 10 ¦ 8 ¦ 19 ¦ 13 R9: LILO-Kishtwar ¦ FDN ¦ Kishtwar ¦ 2 ¦ 2 ¦ 1 ¦ 1 ¦ 4 ¦ 2 | Line ¦ Activity ¦ Section ¦ L2 Oct'25 ¦ Plan Oct'25 ¦ L2 Nov'25 ¦ Plan Nov'25 ¦ L2 Dec'25 ¦ Plan Dec'25 ¦ L2 (Oct'25-Dec'25) ¦ Plan (Oct'25-Dec'25) Samba-Jalandhar ¦ FDN ¦ Jammu ¦ 25 ¦ 10 ¦ 35 ¦ 10 ¦ 40 ¦ 20 ¦ 100 ¦ 110 Gangs ¦ 3 ¦ 3 ¦ 6 FDN ¦ Punjab ¦ 15 ¦ 25 ¦ 30 Gangs ¦ 5 ¦ 6 ¦ 6 Kishenpur-Samba ¦ FDN ¦ Jammu ¦ 2 ¦ 7 ¦ 5 ¦ 10 ¦ 8 ¦ 19 ¦ 13 Gangs ¦ 3 ¦ 4 LILO-Kishtwar ¦ FDN ¦ Kishtwar ¦ 2 ¦ 2 ¦ 1 ¦ 1 ¦ 4 ¦ 2 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet4 | 12 | 10 | row_hindrance | R6: Line ¦ Portion ¦ Section ¦ Length ¦ ROW Lead ¦ ROW Team ¦ Remarks R8: Samba-Jalandhar ¦ Jammu ¦ Gantry-AP52 ¦ 47 ¦ Karmanya Pathania ¦ ROW Team-1 Akhil S ( Engineer) / Radhe Shyam (Supervisor) ¦ At site since the works are in initial phase , hence we have engaged site engineer/supervisor for ROW document collection for time being , further we can engage separate ROW team as per requirement R9: Punjab ¦ AP52 - AP115 ¦ 47 ¦ ROW Team -2 K Govind ( Section In charge) / Kuldeep Singh ( DET) R10: AP115 - AP187 ¦ 48 ¦ ROW Team -3 Manish Nirala (Section In charge) / Govardhan (DET) R11: Kishenpur-Samba ¦ Gantry- AP109 ¦ 33 ¦ ROW Team -4 Mukesh ( Admin) /Yadhuveer (Supervisor) ¦ Due to heavy rains/landslides local administration blocked the roads | Line ¦ Portion ¦ Section ¦ Length ¦ ROW Lead ¦ ROW Team ¦ Remarks Km ¦ Currently Working Samba-Jalandhar ¦ Jammu ¦ Gantry-AP52 ¦ 47 ¦ Karmanya Pathania ¦ ROW Team-1 Akhil S ( Engineer) / Radhe Shyam (Supervisor) ¦ At site since the works are in initial phase , hence we have engaged site engineer/supervisor for ROW document collection for time being , further we can engage separate ROW team as per requirement Punjab ¦ AP52 - AP115 ¦ 47 ¦ ROW Team -2 K Govind ( Section In charge) / Kuldeep Singh ( DET) AP115 - AP187 ¦ 48 ¦ ROW Team -3 Manish Nirala (Section In charge) / Govardhan (DET) Kishenpur-Samba ¦ Gantry- AP109 ¦ 33 ¦ ROW Team -4 Mukesh ( Admin) /Yadhuveer (Supervisor) ¦ Due to heavy rains/landslides local administration blocked the roads LILO ¦ Kishtewar ¦ AP1-Tapping Point ¦ 2.1 ¦ Due to heavy rains/landslides local administration blocked the roads | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet5 | 1 | 1 |  |  |  | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | ROW | 247 | 7 | foundation, project_details, row_hindrance, summary_status | R6: S.No ¦ Tower ¦ TOT ¦ Foundation Completion Status ¦ Crop ¦ Land ¦ Remarks | KEC INTERNATIONAL LIMITED ¦ Date ¦ 2026-03-02 00:00:00 400kv D/C Samba-Jalandhar T/L-Punjab Portion Submitted ¦ 109 ¦ 90 File Ready ¦ 10 ¦ 8 S.No ¦ Tower ¦ TOT ¦ Foundation Completion Status ¦ Crop ¦ Land ¦ Remarks 1 ¦ AP53 ¦ DC+0 2 ¦ AP54 ¦ DC+6 3 ¦ AP55 ¦ DD+3 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet13 (2) | 4 | 5 |  |  | Paticulars ¦ Plain Terrain ¦ Hilly Terrain Line Length (KM) ¦ 137 KM ¦ 36 KM 0.791907514450867 ¦ 0.20809248554913296 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | TB-605 | 53 | 23 | earthing_tack, erection, foundation, project_details, stringing, summary_status, survey_soil, visual_l2 | R2: Project Name ¦ Transmission Line Portion for “Transmission scheme for evacuation of power from Ratle HEP (850 MW) & Kiru HEP (624 MW): Part-A” ¦ LOA Start Date ¦ 2025-05-16 00:00:00 ¦ SBU Head- T&D ¦ Rajinder Gupta R3: Client Name ¦ Ratle Kiru Power Transmission Ltd ¦ LOA End Date ¦ 2027-03-15 00:00:00 ¦ PCH ¦ NK Gupta R6: Activity ¦ Final Estimated Qty ¦ Cumulative L2 till Last Month ¦ Cumulative Progress till Last Month ¦ L2 for present Month ¦ Plan for the Month ¦ Today's Progress ¦ Progress till Date for the Month ¦ L2 till Current Month ¦ Completed till Date ¦ Balance Work ¦ Under Progress ¦ Gangs at Present ¦ Remarks R7: Check Survey ¦ 173.43800000000002 ¦ 179.203 ¦ 173.43800000000002 ¦ 179.203 ¦ 173.43800000000002 ¦ 3 R8: Foundation ¦ 523 ¦ 370 ¦ 306 ¦ 55 ¦ 72 ¦ 1 ¦ 34 ¦ 425 ¦ 340 ¦ 183 ¦ 36 ¦ 36 | s ¦ Project Code ¦ TB-605 ¦ Date ¦ 2026-05-20 00:00:00 ¦ President-T & D ¦ Ganesh Srinivasan Project Name ¦ Transmission Line Portion for “Transmission scheme for evacuation of power from Ratle HEP (850 MW) & Kiru HEP (624 MW): Part-A” ¦ LOA Start Date ¦ 2025-05-16 00:00:00 ¦ SBU Head- T&D ¦ Rajinder Gupta Client Name ¦ Ratle Kiru Power Transmission Ltd ¦ LOA End Date ¦ 2027-03-15 00:00:00 ¦ PCH ¦ NK Gupta Revised End Date ¦ Planning ¦ Aditya.M ¦ Project Manager ¦ Mithu Dutta Progress Summary - Ratle Kiru Power Transmission Ltd Activity ¦ Final Estimated Qty ¦ Cumulative L2 till Last Month ¦ Cumulative Progress till Last Month ¦ L2 for present Month ¦ Plan for the Month ¦ Today's Progress ¦ Progress till Date for the Month ¦ L2 till Current Month ¦ Completed till Date ¦ Balance Work ¦ Under Progress ¦ Gangs at Present ¦ Remarks Check Survey ¦ 173.43800000000002 ¦ 179.203 ¦ 173.43800000000002 ¦ 179.203 ¦ 173.43800000000002 ¦ 3 Foundation ¦ 523 ¦ 370 ¦ 306 ¦ 55 ¦ 72 ¦ 1 ¦ 34 ¦ 425 ¦ 340 ¦ 183 ¦ 36 ¦ 36 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet19 | 12 | 12 |  |  | DA+3PS SD 1MR ¦ 1 ¦ 56/4 DB+9 WET ¦ 1 ¦ 164/0 ¦ Tap ¦ 56 ¦ 56/4 ¦ 55 DD+18/25 PS ¦ 1 ¦ 78/0 ¦ Suf ¦ 1 ¦ 57/1 ¦ 59/1 ¦ 57/2 DA+3 FS ¦ 1 ¦ 144/1 ¦ Suf ¦ 2 ¦ 64/1 ¦ 62/1 ¦ 62/2 DA+0 WET ¦ 3 ¦ 159/1,2,3 ¦ Suf ¦ 3 ¦ 82 ¦ 83 ¦ 84 DD+0 WET ¦ 1 ¦ 110/0 ¦ KDR ¦ 65/4 ¦ 65/5 ¦ AP66 DD+3PS SD 1MRC ¦ 1 ¦ 57/0 ¦ Aman Enter ¦ 61/1 DD 18/25 PS 2MRC ¦ 1 ¦ 84/0 ¦ Ramesh | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet16 | 6 | 6 | row_hindrance | R2: S.No ¦ Gang ¦ Line ¦ Remarks R3: 1 ¦ Pawan Kumar Sharma ¦ J-S (Jammu) ¦ Gang idle since 4-4-26 at Loc: 40/3 due to ROW R4: 2 ¦ Md. Ikrar ¦ J-S(Punjab) ¦ Loc: 144/4 completed on 5-4-2026 and no work front available due to crop harvesting R5: 3 ¦ Ms. Hussain ¦ J-S(Punjab) ¦ Loc: 144/3 will be completed on 6-4-2026 and no work front availabl due to crop harvesting | S.No ¦ Gang ¦ Line ¦ Remarks 1 ¦ Pawan Kumar Sharma ¦ J-S (Jammu) ¦ Gang idle since 4-4-26 at Loc: 40/3 due to ROW 2 ¦ Md. Ikrar ¦ J-S(Punjab) ¦ Loc: 144/4 completed on 5-4-2026 and no work front available due to crop harvesting 3 ¦ Ms. Hussain ¦ J-S(Punjab) ¦ Loc: 144/3 will be completed on 6-4-2026 and no work front availabl due to crop harvesting 4 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet14 | 12 | 13 | erection, foundation | R1: S.No ¦ Month ¦ Concreting ¦ Cement ¦ TMT R7: 4 ¦ 2025-12-01 00:00:00 ¦ 415.90302000000014 ¦ 3983.99603 ¦ 33702 ¦ 264.63 ¦ Concreting (M3) ¦ Tower Erection(MT) | S.No ¦ Month ¦ Concreting ¦ Cement ¦ TMT M10 ¦ M20 M3 ¦ M3 ¦ Bags ¦ MT 1 ¦ 2025-09-01 00:00:00 ¦ 14.664000000000001 ¦ 135.088 ¦ 1145 ¦ 8.44 2 ¦ 2025-10-01 00:00:00 ¦ 76.13199999999999 ¦ 667.0039999999999 ¦ 5671 ¦ 47.8 3 ¦ 2025-11-01 00:00:00 ¦ 283.93300000000005 ¦ 2687.36 ¦ 22748 ¦ 176.38 4 ¦ 2025-12-01 00:00:00 ¦ 415.90302000000014 ¦ 3983.99603 ¦ 33702 ¦ 264.63 ¦ Concreting (M3) ¦ Tower Erection(MT) 5 ¦ 2026-01-01 00:00:00 ¦ 411.19739999999996 ¦ 4750.400000000002 ¦ 39812 ¦ 164.07 ¦ 21381 ¦ 2332 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet12 | 45 | 15 | erection, foundation, row_hindrance, stringing, summary_status, supply, survey_soil, visual_l2 | R2: S.No ¦ Material ¦ UOM ¦ BOQ Qty ¦ Final Estimated Qty ¦ L2 till Mar'26 ¦ Supplied Qty ¦ Balance to Supply R3: 1 ¦ Stubs ¦ EA ¦ 434 ¦ 389 ¦ 434 ¦ 353 ¦ 36 R7: S.No ¦ Activity ¦ UOM ¦ BOQ Qty ¦ Final Estimated Qty ¦ L2 till Feb'26 ¦ Completed till Feb'26 ¦ L2 Mar'26 ¦ Progress in Mar'26 ¦ Cumm L2 till Mar'26 ¦ Cumm. Progress till Mar'26 ¦ Balance ¦ Remarks R9: 1 ¦ Survey ¦ Km ¦ 143 ¦ 137 ¦ 143 ¦ 136 ¦ 143 ¦ 136 ¦ 1 R10: 2 ¦ Foundation ¦ EA ¦ 434 ¦ 389 ¦ 207 ¦ 202 ¦ 45 ¦ 28 ¦ 252 ¦ 230 ¦ 159 ¦ 19 Gangs | Supply Portion S.No ¦ Material ¦ UOM ¦ BOQ Qty ¦ Final Estimated Qty ¦ L2 till Mar'26 ¦ Supplied Qty ¦ Balance to Supply 1 ¦ Stubs ¦ EA ¦ 434 ¦ 389 ¦ 434 ¦ 353 ¦ 36 2 ¦ Towers ¦ EA ¦ 434 ¦ 389 ¦ 216 ¦ 314 ¦ 75 S.No ¦ Activity ¦ UOM ¦ BOQ Qty ¦ Final Estimated Qty ¦ L2 till Feb'26 ¦ Completed till Feb'26 ¦ L2 Mar'26 ¦ Progress in Mar'26 ¦ Cumm L2 till Mar'26 ¦ Cumm. Progress till Mar'26 ¦ Balance ¦ Remarks 400 kV D/C Samba - Jalandhar TL 1 ¦ Survey ¦ Km ¦ 143 ¦ 137 ¦ 143 ¦ 136 ¦ 143 ¦ 136 ¦ 1 2 ¦ Foundation ¦ EA ¦ 434 ¦ 389 ¦ 207 ¦ 202 ¦ 45 ¦ 28 ¦ 252 ¦ 230 ¦ 159 ¦ 19 Gangs | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet13 | 4 | 5 |  |  | Paticulars ¦ Jammu Portion ¦ Punjab Portion Line Length (KM) ¦ 83 KM ¦ 90 KM 0.4797687861271676 ¦ 0.5202312138728323 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet15 | 17 | 10 | commercial, project_details, row_hindrance, supply, visual_l2 | R3: S.No ¦ Line ¦ LOA Cr ¦ Billed till date Cr ¦ Balance Cr R4: 1 ¦ 400 kV Samba- Jalandhar D/C line (Quad) ¦ 155.09 ¦ 88.06 ¦ 67.03 R10: S.No ¦ Line ¦ LOA Cr ¦ Billed till date Cr ¦ Balance Cr R11: 1 ¦ 400 kV Samba- Jalandhar D/C line (Quad) ¦ 119.32272599519798 ¦ 30.5299128 ¦ 88.79281319519798 R14: 4 ¦ Unit Rate Schedule for Services ¦ 6.465411912766016 ¦ 6.465411912766016 | Supply Portion S.No ¦ Line ¦ LOA Cr ¦ Billed till date Cr ¦ Balance Cr 1 ¦ 400 kV Samba- Jalandhar D/C line (Quad) ¦ 155.09 ¦ 88.06 ¦ 67.03 2 ¦ 400 kV Kishenpur-Samba D/C line (Quad) ¦ 67.47 ¦ 17.6387266 ¦ 49.8312734 3 ¦ LILO of 400 kV Kishenpur- Dulhasti line (Twin) at Kishtwar S/s ¦ 6.43 ¦ 0.1439185 ¦ 6.2860815 Total ¦ 228.99 ¦ 105.8426451 ¦ 123.1473549 Service Portion S.No ¦ Line ¦ LOA Cr ¦ Billed till date Cr ¦ Balance Cr | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | TB401 DPR | 29 | 20 | project_details, summary_status, survey_soil, visual_l2 | R2: 765KV D/C Fategarh-III Beawar Transmission Line ¦ TB-401 ¦ LOA Date ¦ Pkg-G -26.04.23 ¦ Completion Period ¦ 2025-03-31 00:00:00 ¦ Date: ¦ 2026-05-21 00:00:00 R3: TB-408 ¦ Pkg-F - 11.09.23 ¦ Completion Period ¦ 2025-03-31 00:00:00 R5: Activity ¦ Qty as per LOA ¦ Qty Received ¦ L2 ¦ Overall Progress ¦ Mar'25 ¦ Balance ¦ Apr'25 ¦ Plan ¦ Remarks R6: 2024-12-30 00:00:00 ¦ Till Mar-25 ¦ As on date ¦ Till Mar-25 ¦ Plan ¦ Actual ¦ As on date ¦ Plan ¦ WIP ¦ Today comp ¦ Actual ¦ 2024-09-01 00:00:00 ¦ 2024-07-01 00:00:00 R7: Details Survey ¦ 215 ¦ 189.53 ¦ 203 ¦ 199.841 ¦ 199.841 | Project Progress for TB-401/408,Section-II 765KV D/C Fategarh-III Beawar Transmission Line ¦ TB-401 ¦ LOA Date ¦ Pkg-G -26.04.23 ¦ Completion Period ¦ 2025-03-31 00:00:00 ¦ Date: ¦ 2026-05-21 00:00:00 TB-408 ¦ Pkg-F - 11.09.23 ¦ Completion Period ¦ 2025-03-31 00:00:00 . Activity ¦ Qty as per LOA ¦ Qty Received ¦ L2 ¦ Overall Progress ¦ Mar'25 ¦ Balance ¦ Apr'25 ¦ Plan ¦ Remarks 2024-12-30 00:00:00 ¦ Till Mar-25 ¦ As on date ¦ Till Mar-25 ¦ Plan ¦ Actual ¦ As on date ¦ Plan ¦ WIP ¦ Today comp ¦ Actual ¦ 2024-09-01 00:00:00 ¦ 2024-07-01 00:00:00 Details Survey ¦ 215 ¦ 189.53 ¦ 203 ¦ 199.841 ¦ 199.841 Pkg-G (Section-II) ¦ 101.1 ¦ 107.5 ¦ 101.1 ¦ 101.1 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Survey-Summary | 59 | 27 | row_hindrance, statutory_crossing, summary_status, survey_soil | R1: PROJECT NAME ¦ INDIGRID - 400kV D/C QUAD WZ-5 SAMBA-JALANDHAR & KISHENPUR-SAMBA TL ¦ COMP ¦ APPROVED R8: Portion ¦ SURVEY LEAD ¦ TEAM MEMBERS ¦ MACHINE ¦ LINE NAME ¦ SECTION LENGTH ¦ COMPLETED ¦ BALANCE ¦ SUBMITTED ¦ APPROVED ¦ APPROVAL PENDING ¦ REMARK R9: Jammu ¦ 1)BIPPAN SHARMA ¦ 2) Shiv Kumar( Asst Surveyor) ¦ DGPS-1 TS-02 ¦ 400kV D/C Jalandar - Samba T/L (GANTRY TO AP 52) ¦ 46.915 ¦ 46.44 ¦ 0.4750000000000014 ¦ 46.053 ¦ 46.053 ¦ 0.48 km is from Sambha Gantyry to AP 4 R10: 3) Sahil Raj(Asst Surveyor) ¦ 400kV D/C Samba - Kishenpur T/L ¦ 33 ¦ 27.138 ¦ 5.861999999999998 ¦ 19.6 ¦ 19.6 ¦ AP4-AP14, AP24-AP55, AP55-AP70, AP70-AP86,AP95-AP109 C/S Completed AP15-AP24 - Re-routing required due to landsliding (Hold) AP86-AP95 - Hold due to under powerline crossing R11: 4) Sunil (Survey Helper) ¦ LILO at Kistwar ¦ 2.18 ¦ 2.18 ¦ 2.18 ¦ 2.18 ¦ Contour completed 12 Locations out of 13 location AP 11 conturing not done due to ROW since 29th Jul'25 | PROJECT NAME ¦ INDIGRID - 400kV D/C QUAD WZ-5 SAMBA-JALANDHAR & KISHENPUR-SAMBA TL ¦ COMP ¦ APPROVED START DATE (NOA DATE) ¦ 16-MAY-2025 ¦ PENDING ¦ UNDER REVIEW KEC PROJECT ¦ TB-605 ¦ PENDING NAME OF CLIENT ¦ RATLE KIRU POWER TRANSMISSION LIMITED TITLE ¦ SITE SURVEY STATUS TEAM FORMATION ¦ CHECK SURVEY SUMMARY (KM) Portion ¦ SURVEY LEAD ¦ TEAM MEMBERS ¦ MACHINE ¦ LINE NAME ¦ SECTION LENGTH ¦ COMPLETED ¦ BALANCE ¦ SUBMITTED ¦ APPROVED ¦ APPROVAL PENDING ¦ REMARK Jammu ¦ 1)BIPPAN SHARMA ¦ 2) Shiv Kumar( Asst Surveyor) ¦ DGPS-1 TS-02 ¦ 400kV D/C Jalandar - Samba T/L (GANTRY TO AP 52) ¦ 46.915 ¦ 46.44 ¦ 0.4750000000000014 ¦ 46.053 ¦ 46.053 ¦ 0.48 km is from Sambha Gantyry to AP 4 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet6 | 16 | 10 | survey_soil | R3: Line ¦ Portion ¦ Scope ¦ Completed ¦ Submitted ¦ Approved | Survey Line ¦ Portion ¦ Scope ¦ Completed ¦ Submitted ¦ Approved S-J ¦ Jammu ¦ 46.92 ¦ 46.44 ¦ 46.44 ¦ 46.44 S-J ¦ Punjab ¦ 95.06 ¦ 95.06 ¦ 84.936 ¦ 72.85 K-S ¦ 33.103 ¦ 23.393 ¦ 16.04 ¦ 10.6 LILO ¦ 2.18 ¦ 2.18 ¦ 2.18 ¦ 2.18 Total ¦ 177.26300000000003 ¦ 167.073 ¦ 149.596 ¦ 132.07 16.04 ¦ 10.58 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Approved Survey | 116 | 10 | row_hindrance, survey_soil | R11: 7 ¦ Jammu ¦ AP11-AP12 ¦ 0.206593 ¦ Approved Check Survey Sections | KEC INTERNATIONAL LIMITED 400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5 ¦ 400 kV Samba- Kishenpur D/C Line(Quad) - Wind Zone - 5 Approved Check Survey Sections ¦ Approved Check Survey Sections S.No ¦ Portion ¦ Section ¦ Length Km ¦ S.No ¦ Section ¦ Length Km 1 ¦ Jammu ¦ AP5-AP6 ¦ 0.119059 ¦ 1 ¦ AP78-AP86 ¦ 1.945 2 ¦ Jammu ¦ AP6-AP7 ¦ 0.092496 ¦ 2 ¦ AP95-AP109 ¦ 3.13 3 ¦ Jammu ¦ AP7-AP8 ¦ 0.134988 ¦ 3 ¦ AP24-AP39 ¦ 5.5 4 ¦ Jammu ¦ AP8-AP9 ¦ 0.365176 ¦ Total ¦ 10.575 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Approved CS J-S Line | 577 | 27 | row_hindrance, statutory_crossing, survey_soil, visual_l2 | R4: Sr. No. ¦ Tower No. ¦ Type of Tower ¦ Span Length (m) ¦ Section Length (m) ¦ Angle of Deviation ¦ UTM Coordinates ¦ Sr. No. ¦ Tower No. ¦ Type of Tower ¦ Raised Chimney ¦ Leg Extension ¦ Span Length (m) ¦ Section Length (m) ¦ Reduced Level ¦ Angle of Deviation ¦ UTM Coordinates ¦ Crossing/Remarks R7: 119.059 ¦ 119.059 ¦ 2 nos 11 KV,Road Crossing R11: 134.989 ¦ 134.988 ¦ 400 KV(JAL-SAM) line Crossing R13: 365.175 ¦ 365.176 ¦ Nalla Crossing R15: 236.697 ¦ 236.697 ¦ 2 nos 25KV,Railway Crossing | Line: 400 kV D/C Quad Jalandhar-Samba TL Approved Check Survey Tower Schedule AS PER DETAIL SURVEY ¦ AS PER CHECK SURVEY Sr. No. ¦ Tower No. ¦ Type of Tower ¦ Span Length (m) ¦ Section Length (m) ¦ Angle of Deviation ¦ UTM Coordinates ¦ Sr. No. ¦ Tower No. ¦ Type of Tower ¦ Raised Chimney ¦ Leg Extension ¦ Span Length (m) ¦ Section Length (m) ¦ Reduced Level ¦ Angle of Deviation ¦ UTM Coordinates ¦ Crossing/Remarks Easting ¦ Northing ¦ LEG A ¦ LEG B ¦ LEG C ¦ LEG D ¦ LEG A ¦ LEG B ¦ LEG C ¦ LEG D ¦ Easting ¦ Northing 1 ¦ AP 5/0 ¦ DD+18 ¦ 47°01'57"L ¦ 516661.837 ¦ 3596578.147 ¦ 1 ¦ AP 5/0 ¦ DD+0 ¦ 384.3 ¦ 47°01'59"LT ¦ 516472.785 ¦ 3598642.658 119.059 ¦ 119.059 ¦ 2 nos 11 KV,Road Crossing 2 ¦ AP 6/0 ¦ DA+0 ¦ 119.059 ¦ 40°54'41"R ¦ 516805.332 ¦ 3596183.208 ¦ 2 ¦ AP 6/0 ¦ DD+9 ¦ 119.059 ¦ 384.202 ¦ 40°54'42"RT ¦ 516557.855 ¦ 3598559.362 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Approved CS K-S Line | 53 | 27 | statutory_crossing, survey_soil, visual_l2 | R4: Sr. No. ¦ Tower No. ¦ Type of Tower ¦ Span Length (m) ¦ Section Length (m) ¦ Angle of Deviation ¦ UTM Coordinates ¦ Sr. No. ¦ Tower No. ¦ Type of Tower ¦ Raised Chimney ¦ Leg Extension ¦ Span Length (m) ¦ Section Length (m) ¦ Reduced Level ¦ Angle of Deviation ¦ UTM Coordinates ¦ Crossing/Remarks R9: 374.114 ¦ 392.251 ¦ NALLA CROSSING R13: 195.926 ¦ 195.926 ¦ 220 KV S/C CROSSING(KSN-SRN) R15: 194.627 ¦ 194.623 ¦ 220 D/C CROSSING(KSN-SRN) R21: 195.995 ¦ 195.99 ¦ LT LINE,2 NOS 11 KV CROSSING | Line: 400 kV D/C Quad Kishenpur-Samba TL Approved Check Survey Tower Schedule AS PER DETAIL SURVEY ¦ AS PER CHECK SURVEY Sr. No. ¦ Tower No. ¦ Type of Tower ¦ Span Length (m) ¦ Section Length (m) ¦ Angle of Deviation ¦ UTM Coordinates ¦ Sr. No. ¦ Tower No. ¦ Type of Tower ¦ Raised Chimney ¦ Leg Extension ¦ Span Length (m) ¦ Section Length (m) ¦ Reduced Level ¦ Angle of Deviation ¦ UTM Coordinates ¦ Crossing/Remarks Easting ¦ Northing ¦ LEG A ¦ LEG B ¦ LEG C ¦ LEG D ¦ LEG A ¦ LEG B ¦ LEG C ¦ LEG D ¦ Easting ¦ Northing 1 ¦ AP 78/0 ¦ DC+9 ¦ 28°55'39"L ¦ 515334.466 ¦ 3621567.153 ¦ 1 ¦ AP 78/0 ¦ DC+9 ¦ 1 ¦ 3 ¦ 3 ¦ 524.77 ¦ 29°55'53"L ¦ 515334.47 ¦ 3621567.15 361.044 ¦ 340.277 2 ¦ AP 79/0 ¦ DD+9 ¦ 361.044 ¦ 31°39'03"R ¦ 515034.271 ¦ 3621767.742 ¦ 2 ¦ AP 79/0 ¦ DD+9 ¦ 1 ¦ 340.277 ¦ 524.982 ¦ 30°11'47"R ¦ 515048.273 ¦ 3621751.214 ¦ LT LINE TO BE SHIFTED | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Foundation JS-Line -Jammu | 110 | 17 | earthing_tack, foundation, project_details, row_hindrance, summary_status, supply | R5: S.No ¦ Loc No. ¦ Tower Type ¦ Classification ¦ Conc Volume ¦ Start Date ¦ Foundation ¦ Earthing ¦ FDN Status ¦ Gang Name ¦ Gang Strength ¦ Remark R6: Excavation ¦ Stub Setting ¦ PCC ¦ Rebar Placing ¦ RCC ¦ Completion Date R7: 1 ¦ 29/5 ¦ DA+0 ¦ WET ¦ 34.389 ¦ 2025-07-28 00:00:00 ¦ 2025-08-07 00:00:00 ¦ 2025-08-10 00:00:00 ¦ 2025-08-10 00:00:00 ¦ 2025-08-10 00:00:00 ¦ 2025-08-11 00:00:00 ¦ 2025-08-11 00:00:00 ¦ 2025-12-03 00:00:00 ¦ Completed ¦ Rakesh ¦ 8 R8: 2 ¦ 29/4 ¦ DA+0 ¦ DRY ¦ 21.318 ¦ 2025-08-11 00:00:00 ¦ 2025-08-21 00:00:00 ¦ 2025-08-21 00:00:00 ¦ 2025-08-22 00:00:00 ¦ 2025-08-22 00:00:00 ¦ 2025-09-06 00:00:00 ¦ 2025-09-06 00:00:00 ¦ 2025-12-03 00:00:00 ¦ Completed ¦ Rakesh ¦ 5 R9: 3 ¦ 29/3 ¦ DA+0 ¦ DRY ¦ 21.318 ¦ 2025-08-31 00:00:00 ¦ 2025-09-21 00:00:00 ¦ 2025-09-21 00:00:00 ¦ 2025-09-22 00:00:00 ¦ 2025-09-22 00:00:00 ¦ 2025-09-24 00:00:00 ¦ 2025-09-24 00:00:00 ¦ Completed ¦ Adishiv ¦ 12 ¦ Completed & 1 leg 1.5 M RC pending | KEC INTERNATIONAL LIMITED ¦ Date: ¦ 2026-05-20 00:00:00 400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Jammu Portion FOUNDATION S.No ¦ Loc No. ¦ Tower Type ¦ Classification ¦ Conc Volume ¦ Start Date ¦ Foundation ¦ Earthing ¦ FDN Status ¦ Gang Name ¦ Gang Strength ¦ Remark Excavation ¦ Stub Setting ¦ PCC ¦ Rebar Placing ¦ RCC ¦ Completion Date 1 ¦ 29/5 ¦ DA+0 ¦ WET ¦ 34.389 ¦ 2025-07-28 00:00:00 ¦ 2025-08-07 00:00:00 ¦ 2025-08-10 00:00:00 ¦ 2025-08-10 00:00:00 ¦ 2025-08-10 00:00:00 ¦ 2025-08-11 00:00:00 ¦ 2025-08-11 00:00:00 ¦ 2025-12-03 00:00:00 ¦ Completed ¦ Rakesh ¦ 8 2 ¦ 29/4 ¦ DA+0 ¦ DRY ¦ 21.318 ¦ 2025-08-11 00:00:00 ¦ 2025-08-21 00:00:00 ¦ 2025-08-21 00:00:00 ¦ 2025-08-22 00:00:00 ¦ 2025-08-22 00:00:00 ¦ 2025-09-06 00:00:00 ¦ 2025-09-06 00:00:00 ¦ 2025-12-03 00:00:00 ¦ Completed ¦ Rakesh ¦ 5 3 ¦ 29/3 ¦ DA+0 ¦ DRY ¦ 21.318 ¦ 2025-08-31 00:00:00 ¦ 2025-09-21 00:00:00 ¦ 2025-09-21 00:00:00 ¦ 2025-09-22 00:00:00 ¦ 2025-09-22 00:00:00 ¦ 2025-09-24 00:00:00 ¦ 2025-09-24 00:00:00 ¦ Completed ¦ Adishiv ¦ 12 ¦ Completed & 1 leg 1.5 M RC pending | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet10 | 55 | 15 |  |  | S.No ¦ Loc ¦ TOT ¦ Classification ¦ M10 ¦ M20 1 ¦ 29/2 ¦ DA+3 ¦ PS (SD) ¦ 7.812 ¦ 51.824 2 ¦ 33/2 ¦ DA+0 ¦ PS ¦ 4.822 ¦ 35.692 3 ¦ 46/5 ¦ DA+6 ¦ FS ¦ 6.138 ¦ 43.392 4 ¦ 50A/3 ¦ DA+3 ¦ PS (SD) ¦ 7.812 ¦ 51.824 5 ¦ AP14 ¦ DB+9 ¦ DFR ¦ 4.177 ¦ 46.652 6 ¦ AP24 ¦ DC+3 ¦ PS ¦ 10.31 ¦ 107.913 7 ¦ 43/3 ¦ DA+3 ¦ PS ¦ 4.822 ¦ 35.692 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection -Jammu | 86 | 11 | erection, project_details, row_hindrance, summary_status | R5: S.No ¦ Loc No. ¦ Tower Type ¦ Weight MT ¦ Conc Volume ¦ Starting Date ¦ Completion Date ¦ Status ¦ Gang Name ¦ Gang Strength ¦ Remark R7: 1 ¦ 29/5 ¦ DA+0 ¦ 18.339 ¦ 34.389 ¦ 2025-11-27 00:00:00 ¦ 2025-12-03 00:00:00 ¦ Completed ¦ Raj Labour Suppliers ¦ 23 R8: 2 ¦ 29/4 ¦ DA+0 ¦ 18.339 ¦ 21.318 ¦ 2025-12-05 00:00:00 ¦ 2025-12-10 00:00:00 ¦ Completed ¦ Raj Labour Suppliers ¦ 23 R9: 3 ¦ 27/0 ¦ DB+0 ¦ 27.92 ¦ 21.318 ¦ 2025-12-11 00:00:00 ¦ 2025-11-21 00:00:00 ¦ Completed ¦ Raj Labour Suppliers ¦ 23 R10: 4 ¦ 29/6 ¦ DA+3 ¦ 19.44 ¦ 2025-12-22 00:00:00 ¦ 2025-12-29 00:00:00 ¦ Completed ¦ Raj Labour Suppliers ¦ 20 | KEC INTERNATIONAL LIMITED ¦ Date: ¦ 2026-05-20 00:00:00 400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Jammu Portion TOWER ERECTION S.No ¦ Loc No. ¦ Tower Type ¦ Weight MT ¦ Conc Volume ¦ Starting Date ¦ Completion Date ¦ Status ¦ Gang Name ¦ Gang Strength ¦ Remark 1 ¦ 29/5 ¦ DA+0 ¦ 18.339 ¦ 34.389 ¦ 2025-11-27 00:00:00 ¦ 2025-12-03 00:00:00 ¦ Completed ¦ Raj Labour Suppliers ¦ 23 2 ¦ 29/4 ¦ DA+0 ¦ 18.339 ¦ 21.318 ¦ 2025-12-05 00:00:00 ¦ 2025-12-10 00:00:00 ¦ Completed ¦ Raj Labour Suppliers ¦ 23 3 ¦ 27/0 ¦ DB+0 ¦ 27.92 ¦ 21.318 ¦ 2025-12-11 00:00:00 ¦ 2025-11-21 00:00:00 ¦ Completed ¦ Raj Labour Suppliers ¦ 23 4 ¦ 29/6 ¦ DA+3 ¦ 19.44 ¦ 2025-12-22 00:00:00 ¦ 2025-12-29 00:00:00 ¦ Completed ¦ Raj Labour Suppliers ¦ 20 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Vertical Chart -JS Line Jammu | 263 | 18 | earthing_tack, erection, foundation, row_hindrance, stringing, visual_l2 | R6: S.No ¦ Tower ¦ TOT ¦ Angle of Deviation ¦ Raised Chimney ¦ FDN Classification ¦ Span Length (Mtr) ¦ Section Length (m) ¦ ROW ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Tack Welding ¦ Stringing ¦ Remarks | KEC INTERNATIONAL LIMITED 400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Jammu Portion Vertical Chart Complete ¦ 95 ¦ 83 ¦ 73 ¦ 59 WIP ¦ 9 ¦ 3 S.No ¦ Tower ¦ TOT ¦ Angle of Deviation ¦ Raised Chimney ¦ FDN Classification ¦ Span Length (Mtr) ¦ Section Length (m) ¦ ROW ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Tack Welding ¦ Stringing ¦ Remarks LEG A ¦ LEG B ¦ LEG C ¦ LEG D 1 ¦ AP5 ¦ DD+0 ¦ 47°01'59"LT | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet17 | 6 | 11 | erection, foundation, row_hindrance, supply | R2: S.No ¦ Line ¦ Portion ¦ Line Qty ¦ Foundation Completed ¦ Tower Erection Completed ¦ Tower Erection WIP ¦ Gap between Foundation & Erection ¦ Tower Erection Gangs Available at Site ¦ Remarks R3: 1 ¦ Samba-Jalandhar ¦ Jammu ¦ 137 ¦ 81 ¦ 51 ¦ 4 ¦ 26 ¦ 5 ¦ 10 locations ROW clear - Work front for 5 gangs i.e; 2 loc per gang 2 Locations -supply of DD18/25/30 Extensions required 5 locations -Crop harvesting required 4 locations under ROW R4: 2 ¦ Samba-Jalandhar ¦ Punjab ¦ 262 ¦ 154 ¦ 66 ¦ 6 ¦ 82 ¦ 7 ¦ 4 locations - ROW Clear 9 Locations - Supply of DD 18/25/30 extensions required 1 locations - Transposition tower supply required Due to standing crop (wheat) at maximum locations farmers are not allowing for tower erection work . Expected for crop harvesting in next 1 week time R5: 3 ¦ Samba-Kishenpur ¦ 116 ¦ 44 ¦ 2 ¦ 1 ¦ 41 ¦ 1 ¦ 8 locations - ROW Clear 27 locations - supply of unequal leg extensions required / DD18/25/30 M extension required 5 locations under ROW | S.No ¦ Line ¦ Portion ¦ Line Qty ¦ Foundation Completed ¦ Tower Erection Completed ¦ Tower Erection WIP ¦ Gap between Foundation & Erection ¦ Tower Erection Gangs Available at Site ¦ Remarks 1 ¦ Samba-Jalandhar ¦ Jammu ¦ 137 ¦ 81 ¦ 51 ¦ 4 ¦ 26 ¦ 5 ¦ 10 locations ROW clear - Work front for 5 gangs i.e; 2 loc per gang 2 Locations -supply of DD18/25/30 Extensions required 5 locations -Crop harvesting required 4 locations under ROW 2 ¦ Samba-Jalandhar ¦ Punjab ¦ 262 ¦ 154 ¦ 66 ¦ 6 ¦ 82 ¦ 7 ¦ 4 locations - ROW Clear 9 Locations - Supply of DD 18/25/30 extensions required 1 locations - Transposition tower supply required Due to standing crop (wheat) at maximum locations farmers are not allowing for tower erection work . Expected for crop harvesting in next 1 week time 3 ¦ Samba-Kishenpur ¦ 116 ¦ 44 ¦ 2 ¦ 1 ¦ 41 ¦ 1 ¦ 8 locations - ROW Clear 27 locations - supply of unequal leg extensions required / DD18/25/30 M extension required 5 locations under ROW | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection -SK | 9 | 11 | erection, project_details, summary_status | R5: S.No ¦ Loc No. ¦ Tower Type ¦ Weight MT ¦ Conc Volume ¦ Starting Date ¦ Completion Date ¦ Status ¦ Gang Name ¦ Gang Strength ¦ Remark R7: 1 ¦ 30/1 ¦ DA+0 ¦ 18.34 ¦ 2026-03-18 00:00:00 ¦ 2026-03-24 00:00:00 ¦ Completed ¦ Anvi Construction ¦ 18 R8: 2 ¦ AP27A ¦ DB+6 ¦ 34.578 ¦ 2026-03-24 00:00:00 ¦ 2026-03-31 00:00:00 ¦ Completed ¦ Anvi Construction ¦ 23 | KEC INTERNATIONAL LIMITED ¦ Date: ¦ 2026-05-20 00:00:00 400kV D/C Samba -Kishenpur TL TOWER ERECTION S.No ¦ Loc No. ¦ Tower Type ¦ Weight MT ¦ Conc Volume ¦ Starting Date ¦ Completion Date ¦ Status ¦ Gang Name ¦ Gang Strength ¦ Remark 1 ¦ 30/1 ¦ DA+0 ¦ 18.34 ¦ 2026-03-18 00:00:00 ¦ 2026-03-24 00:00:00 ¦ Completed ¦ Anvi Construction ¦ 18 2 ¦ AP27A ¦ DB+6 ¦ 34.578 ¦ 2026-03-24 00:00:00 ¦ 2026-03-31 00:00:00 ¦ Completed ¦ Anvi Construction ¦ 23 3 ¦ AP31 ¦ DB+9 ¦ 2026-04-09 00:00:00 ¦ Body Completed ¦ Anvi Construction ¦ 18 ¦ Work restart from 16-05-2026 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet7 | 59 | 9 |  |  | S.No ¦ Loc ¦ TOT ¦ RC ¦ RC ¦ RC ¦ RC 1 ¦ AP144 ¦ DB+0 2 3 4 ¦ 1 ¦ 1 ¦ 1 ¦ 1 5 6 ¦ AP145 ¦ DB+0 ¦ 2 ¦ 2 ¦ 2 ¦ 2 7 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet8 | 29 | 12 | supply | R2: Tower ¦ Structure ¦ Supplied Qty till date ¦ Material DI received and will dispatch in 1 week ¦ Total ¦ Tower ¦ Supplied Qty ¦ Material Under Transit ¦ Total | Tower ¦ Structure ¦ Supplied Qty till date ¦ Material DI received and will dispatch in 1 week ¦ Total ¦ Tower ¦ Supplied Qty ¦ Material Under Transit ¦ Total DA ¦ Basic Tower Body ¦ 87 ¦ 87 ¦ DA+0 ¦ 34 ¦ 34 +0MBE ¦ 48 ¦ 48 ¦ DA+3 ¦ 39 ¦ 39 +3MBE ¦ 39 ¦ 39 ¦ DA+6 ¦ 12 ¦ 12 +6MBE ¦ 12 ¦ 12 ¦ DA+9 ¦ 2 ¦ 2 +9MBE ¦ 2 ¦ 2 DB ¦ Basic Tower Body ¦ 13 ¦ 16 ¦ 29 ¦ DB+0 ¦ 10 ¦ 14 ¦ 24 +0MBE ¦ 11 ¦ 16 ¦ 27 ¦ DB+3 ¦ 2 ¦ 2 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | LILO | 12 | 16 | foundation, project_details, summary_status, supply | R5: S.No ¦ Loc No. ¦ Tower Type ¦ Classification ¦ Conc Volume ¦ Start Date ¦ Foundation ¦ Completion Date ¦ Status ¦ Gang Name ¦ Gang Strength ¦ Remark R6: Excavation ¦ Stub Setting ¦ PCC ¦ Rebar Placing ¦ RCC R7: 1 ¦ AP7 ¦ DDM+E0+0 ¦ DFR ¦ 36.108999999999995 ¦ 2026-04-09 00:00:00 ¦ WIP ¦ Zaffar ¦ 12 ¦ Pit D-Casting upto 1st part chimney Pit C - Casting upto 1st part chimney Pit A - Casting Completed Pit B- Excavation R9: 3 ¦ AP9 ¦ DDM+E0+0 ¦ DFR ¦ 36.108999999999995 ¦ 2026-03-29 00:00:00 ¦ WIP ¦ Bhat Const. ¦ 7 ¦ Excavation WIP R10: 4 ¦ AP10 ¦ DDM+E6+3 ¦ DFR ¦ 36.108999999999995 ¦ 2026-04-28 00:00:00 ¦ WIP ¦ Bhat Const. ¦ 7 ¦ Excavation WIP | KEC INTERNATIONAL LIMITED ¦ Date: ¦ 2026-05-20 00:00:00 LILO Kishtwar - Wind Zone - 2 FOUNDATION S.No ¦ Loc No. ¦ Tower Type ¦ Classification ¦ Conc Volume ¦ Start Date ¦ Foundation ¦ Completion Date ¦ Status ¦ Gang Name ¦ Gang Strength ¦ Remark Excavation ¦ Stub Setting ¦ PCC ¦ Rebar Placing ¦ RCC 1 ¦ AP7 ¦ DDM+E0+0 ¦ DFR ¦ 36.108999999999995 ¦ 2026-04-09 00:00:00 ¦ WIP ¦ Zaffar ¦ 12 ¦ Pit D-Casting upto 1st part chimney Pit C - Casting upto 1st part chimney Pit A - Casting Completed Pit B- Excavation 2 ¦ AP8 ¦ DDM+E6+3 ¦ DFR ¦ 36.108999999999995 ¦ 2026-03-28 00:00:00 ¦ WIP ¦ Bittu ¦ 8 ¦ Pit A - Casting upto frustrum Pit C - Block Level 3 ¦ AP9 ¦ DDM+E0+0 ¦ DFR ¦ 36.108999999999995 ¦ 2026-03-29 00:00:00 ¦ WIP ¦ Bhat Const. ¦ 7 ¦ Excavation WIP | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Erection-Punjab | 120 | 11 | erection, project_details, row_hindrance, summary_status | R5: S.No ¦ Loc No. ¦ Tower Type ¦ Weight MT ¦ Conc Volume ¦ Starting Date ¦ Completion Date ¦ Status ¦ Gang Name ¦ Gang Strength ¦ Remark R7: 1 ¦ 89/1 ¦ DA+3 ¦ 19.44 ¦ 34.389 ¦ 2026-02-02 00:00:00 ¦ 2026-02-06 00:00:00 ¦ Completed ¦ Saritha Devi ¦ 30 R8: 2 ¦ 117/3 ¦ DA+0 ¦ 18.339 ¦ 2026-02-03 00:00:00 ¦ 2026-02-07 00:00:00 ¦ Completed ¦ Poonam Kumari ¦ 34 R9: 3 ¦ 95/3 ¦ DA+0 ¦ 18.339 ¦ 2026-02-06 00:00:00 ¦ 2026-02-08 00:00:00 ¦ Completed ¦ Saritha Devi ¦ 30 R10: 4 ¦ 97/2 ¦ DA+0 ¦ 18.339 ¦ 2026-02-05 00:00:00 ¦ 2026-02-09 00:00:00 ¦ Completed ¦ Jwala Singh ¦ 22 | KEC INTERNATIONAL LIMITED ¦ Date: ¦ 2026-05-20 00:00:00 400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5- Punjab Portion TOWER ERECTION S.No ¦ Loc No. ¦ Tower Type ¦ Weight MT ¦ Conc Volume ¦ Starting Date ¦ Completion Date ¦ Status ¦ Gang Name ¦ Gang Strength ¦ Remark 1 ¦ 89/1 ¦ DA+3 ¦ 19.44 ¦ 34.389 ¦ 2026-02-02 00:00:00 ¦ 2026-02-06 00:00:00 ¦ Completed ¦ Saritha Devi ¦ 30 2 ¦ 117/3 ¦ DA+0 ¦ 18.339 ¦ 2026-02-03 00:00:00 ¦ 2026-02-07 00:00:00 ¦ Completed ¦ Poonam Kumari ¦ 34 3 ¦ 95/3 ¦ DA+0 ¦ 18.339 ¦ 2026-02-06 00:00:00 ¦ 2026-02-08 00:00:00 ¦ Completed ¦ Saritha Devi ¦ 30 4 ¦ 97/2 ¦ DA+0 ¦ 18.339 ¦ 2026-02-05 00:00:00 ¦ 2026-02-09 00:00:00 ¦ Completed ¦ Jwala Singh ¦ 22 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Vertical Chart -JS Line Punjab | 573 | 18 | earthing_tack, erection, foundation, row_hindrance, stringing, visual_l2 | R6: S.No ¦ Tower ¦ TOT ¦ Angle of Deviation ¦ Raised Chimney ¦ FDN Classification ¦ Span Length (Mtr) ¦ Section Length (m) ¦ ROW ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Tack Welding ¦ Stringing ¦ Remarks | KEC INTERNATIONAL LIMITED 400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Punjab Portion Vertical Chart Complete ¦ 207 ¦ 194 ¦ 169 ¦ 111 WIP ¦ 13 ¦ 3 S.No ¦ Tower ¦ TOT ¦ Angle of Deviation ¦ Raised Chimney ¦ FDN Classification ¦ Span Length (Mtr) ¦ Section Length (m) ¦ ROW ¦ Foundation ¦ Earthing ¦ Tower Erection ¦ Tack Welding ¦ Stringing ¦ Remarks LEG A ¦ LEG B ¦ LEG C ¦ LEG D 1 ¦ AP53 ¦ DC+0 ¦ 29°2'38"RT | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Foundation -JS Line- Punjab | 214 | 18 | earthing_tack, foundation, project_details, row_hindrance, summary_status, supply | R5: S.No ¦ Loc No. ¦ Tower Type ¦ Classification ¦ Conc Volume ¦ Start Date ¦ Foundation ¦ Completion Date ¦ FDN Status ¦ Earthing ¦ Gang Name ¦ Gang Strength ¦ Remark R6: Excavation ¦ Stub Setting ¦ PCC ¦ Rebar Placing ¦ RCC R7: 1 ¦ 90/1 ¦ DA+3 ¦ WET ¦ 36.108999999999995 ¦ 2025-09-25 00:00:00 ¦ 2026-01-11 00:00:00 ¦ 2026-01-11 00:00:00 ¦ 2026-01-11 00:00:00 ¦ 2026-01-11 00:00:00 ¦ 2026-01-11 00:00:00 ¦ 2026-01-11 00:00:00 ¦ Completed ¦ Anchal Singh ¦ 25 ¦ 3 pits casting completed on 24.10.25. After clearence of ROW on 09.01.26, Work resumed since 10.01.26 in the 4th pit and work completed on 11.01.26 R8: 2 ¦ 117/1 ¦ DA+0 ¦ WET ¦ 2025-10-13 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-19 00:00:00 ¦ 2025-10-19 00:00:00 ¦ 2025-10-20 00:00:00 ¦ 2025-10-20 00:00:00 ¦ Completed ¦ Sakrala Material ¦ 10 R9: 3 ¦ 92/3 ¦ DA+0 ¦ WET ¦ 2025-10-16 00:00:00 ¦ 2025-10-25 00:00:00 ¦ 2025-10-25 00:00:00 ¦ 2025-10-25 00:00:00 ¦ 2025-10-26 00:00:00 ¦ 2025-10-27 00:00:00 ¦ 2025-10-27 00:00:00 ¦ Completed ¦ MS Constructions ¦ 9 | KEC International Ltd ¦ Date: ¦ 2026-05-20 00:00:00 400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5-Punjab Portion FOUNDATION S.No ¦ Loc No. ¦ Tower Type ¦ Classification ¦ Conc Volume ¦ Start Date ¦ Foundation ¦ Completion Date ¦ FDN Status ¦ Earthing ¦ Gang Name ¦ Gang Strength ¦ Remark Excavation ¦ Stub Setting ¦ PCC ¦ Rebar Placing ¦ RCC 1 ¦ 90/1 ¦ DA+3 ¦ WET ¦ 36.108999999999995 ¦ 2025-09-25 00:00:00 ¦ 2026-01-11 00:00:00 ¦ 2026-01-11 00:00:00 ¦ 2026-01-11 00:00:00 ¦ 2026-01-11 00:00:00 ¦ 2026-01-11 00:00:00 ¦ 2026-01-11 00:00:00 ¦ Completed ¦ Anchal Singh ¦ 25 ¦ 3 pits casting completed on 24.10.25. After clearence of ROW on 09.01.26, Work resumed since 10.01.26 in the 4th pit and work completed on 11.01.26 2 ¦ 117/1 ¦ DA+0 ¦ WET ¦ 2025-10-13 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-19 00:00:00 ¦ 2025-10-19 00:00:00 ¦ 2025-10-20 00:00:00 ¦ 2025-10-20 00:00:00 ¦ Completed ¦ Sakrala Material ¦ 10 3 ¦ 92/3 ¦ DA+0 ¦ WET ¦ 2025-10-16 00:00:00 ¦ 2025-10-25 00:00:00 ¦ 2025-10-25 00:00:00 ¦ 2025-10-25 00:00:00 ¦ 2025-10-26 00:00:00 ¦ 2025-10-27 00:00:00 ¦ 2025-10-27 00:00:00 ¦ Completed ¦ MS Constructions ¦ 9 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet9 | 47 | 16 |  |  | S.No ¦ Loc ¦ TOT ¦ Classification ¦ Start Date ¦ End Darte ¦ JMC 1 ¦ 153/0 ¦ DC+0 ¦ WET ¦ 2026-01-17 00:00:00 ¦ 2026-02-05 00:00:00 ¦ 105 ¦ OK 2 ¦ AP139 ¦ DB+0 ¦ WET ¦ 2026-01-20 00:00:00 ¦ 2026-02-06 00:00:00 ¦ 106 ¦ OK 3 ¦ 151/2 ¦ DA+3 ¦ WET ¦ 2026-02-03 00:00:00 ¦ 2026-02-07 00:00:00 ¦ 107 ¦ OK 4 ¦ AP97 ¦ DD+3 ¦ WET ¦ 2026-01-29 00:00:00 ¦ 2026-02-08 00:00:00 ¦ 108 ¦ OK 5 ¦ AP155 ¦ DD+0 ¦ WET ¦ 2026-01-31 00:00:00 ¦ 2026-02-09 00:00:00 ¦ 109 ¦ OK 6 ¦ 136/2 ¦ DA+3 ¦ WET ¦ 2026-01-22 00:00:00 ¦ 2026-02-11 00:00:00 ¦ 110 ¦ OK 7 ¦ AP130 ¦ DD+18 ¦ PS ¦ 2026-01-18 00:00:00 ¦ 2026-02-12 00:00:00 ¦ 111 ¦ OK | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | ROW Front vs Progress | 38 | 7 | row_hindrance, summary_status | R2: S.No ¦ Line ¦ ROW Clearence Work Front ¦ Completed ¦ WIP ¦ Balance R3: 1 ¦ Samba-Jalandhar (Jammu Portion) ¦ 95 ¦ 84 ¦ 7 ¦ 4 R4: 2 ¦ Samba-Jalandhar (Punjab Portion) ¦ 181 ¦ 158 ¦ 10 ¦ 13 | S.No ¦ Line ¦ ROW Clearence Work Front ¦ Completed ¦ WIP ¦ Balance 1 ¦ Samba-Jalandhar (Jammu Portion) ¦ 95 ¦ 84 ¦ 7 ¦ 4 2 ¦ Samba-Jalandhar (Punjab Portion) ¦ 181 ¦ 158 ¦ 10 ¦ 13 3 ¦ Samba-Kishenpur ¦ 56 ¦ 46 ¦ 7 ¦ 3 4 ¦ LILO-Kishtwar ¦ 4 ¦ 3 ¦ 1 Total ¦ 336 ¦ 288 ¦ 27 ¦ 21 2026-03-17 00:00:00 ¦ 3 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Hindrance | 47 | 11 | foundation, row_hindrance, summary_status, supply, survey_soil | R2: S.No ¦ Line ¦ From ¦ To ¦ Days ¦ Status ¦ Impact Location / Work ¦ Hindrance Details ¦ Remarks R3: 1 ¦ 400 kV D/C Samba-Jalandhar ¦ 2025-07-29 00:00:00 ¦ 2025-07-30 00:00:00 ¦ 2 ¦ Closed ¦ Loc: 29/5 (Foundation) ¦ Due to heavy rains at site excavated Pits (B,C,D) collapsed and site works are hampered R4: 2 ¦ 400 kV D/C Samba-Jalandhar ¦ 2025-08-01 00:00:00 ¦ 2025-08-01 00:00:00 ¦ 1 ¦ Closed ¦ Loc: 29/5 (Foundation) ¦ Due to heavy rains PCC, Steel Binding, RCC work in Pit B R5: 3 ¦ 400 kV D/C Kishenpur-Samba ¦ 2025-08-06 00:00:00 ¦ 2025-08-06 00:00:00 ¦ 1 ¦ Closed ¦ Check Survey Work ¦ Due to landslides, road blocked and at site unable to carry out the survey work R6: 4 ¦ 400 kV D/C Samba-Jalandhar ¦ 2025-08-07 00:00:00 ¦ 2025-08-07 00:00:00 ¦ 1 ¦ Closed ¦ Loc: 29/5 (Foundation) ¦ Due to heavy rains at site , RCC work hampered in Pit A | Hindrance Details. S.No ¦ Line ¦ From ¦ To ¦ Days ¦ Status ¦ Impact Location / Work ¦ Hindrance Details ¦ Remarks 1 ¦ 400 kV D/C Samba-Jalandhar ¦ 2025-07-29 00:00:00 ¦ 2025-07-30 00:00:00 ¦ 2 ¦ Closed ¦ Loc: 29/5 (Foundation) ¦ Due to heavy rains at site excavated Pits (B,C,D) collapsed and site works are hampered 2 ¦ 400 kV D/C Samba-Jalandhar ¦ 2025-08-01 00:00:00 ¦ 2025-08-01 00:00:00 ¦ 1 ¦ Closed ¦ Loc: 29/5 (Foundation) ¦ Due to heavy rains PCC, Steel Binding, RCC work in Pit B 3 ¦ 400 kV D/C Kishenpur-Samba ¦ 2025-08-06 00:00:00 ¦ 2025-08-06 00:00:00 ¦ 1 ¦ Closed ¦ Check Survey Work ¦ Due to landslides, road blocked and at site unable to carry out the survey work 4 ¦ 400 kV D/C Samba-Jalandhar ¦ 2025-08-07 00:00:00 ¦ 2025-08-07 00:00:00 ¦ 1 ¦ Closed ¦ Loc: 29/5 (Foundation) ¦ Due to heavy rains at site , RCC work hampered in Pit A 5 ¦ 400 kV D/C Samba-Jalandhar ¦ 2025-08-09 00:00:00 ¦ 2025-08-09 00:00:00 ¦ 1 ¦ Closed ¦ Loc: 29/5 (Foundation) ¦ Due to heavy rains at site , RCC work hampered in Pit C 6 ¦ 400 kV D/C Samba-Jalandhar ¦ 2025-08-12 00:00:00 ¦ 2025-08-14 00:00:00 ¦ 3 ¦ Closed ¦ Loc: 29/4 (Foundation) ¦ Due to heavy rains for continous 3 days site excavation work hampered | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Foundation -KS Line | 66 | 16 | earthing_tack, foundation, project_details, summary_status, supply | R5: S.No ¦ Loc No. ¦ Tower Type ¦ Classification ¦ Start Date ¦ Foundation ¦ Completion Date ¦ Status ¦ Earthing ¦ Gang Name ¦ Gang Strength ¦ Remark R6: Excavation ¦ Stub Setting ¦ PCC ¦ Rebar Placing ¦ RCC R7: 1 ¦ 85/0 ¦ DC+0 ¦ DFR ¦ 2025-10-01 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-23 00:00:00 ¦ 2025-10-23 00:00:00 ¦ 2025-10-24 00:00:00 ¦ 2025-10-26 00:00:00 ¦ 2025-10-26 00:00:00 ¦ Completed ¦ 2025-11-09 00:00:00 ¦ Ankush Sharma ¦ 8 R8: 2 ¦ 86/0 ¦ DD+0 ¦ DFR ¦ 2025-10-24 00:00:00 ¦ 2025-11-06 00:00:00 ¦ 2025-11-07 00:00:00 ¦ 2025-11-09 00:00:00 ¦ 2025-11-09 00:00:00 ¦ 2025-11-10 00:00:00 ¦ 2025-11-10 00:00:00 ¦ Completed ¦ 2025-11-11 00:00:00 ¦ Ankush Sharma ¦ 13 R9: 3 ¦ 106/0 ¦ DB+0 ¦ DFR ¦ 2025-10-14 00:00:00 ¦ 2025-10-23 00:00:00 ¦ 2025-10-30 00:00:00 ¦ 2025-10-30 00:00:00 ¦ 2025-10-31 00:00:00 ¦ 2025-10-31 00:00:00 ¦ 2025-10-31 00:00:00 ¦ Completed ¦ 2025-11-20 00:00:00 ¦ Naresh ¦ 8 | KEC INTERNATIONAL LIMITED ¦ Date: ¦ 2026-05-20 00:00:00 400 kV Kishenpur -Samba T/L FOUNDATION S.No ¦ Loc No. ¦ Tower Type ¦ Classification ¦ Start Date ¦ Foundation ¦ Completion Date ¦ Status ¦ Earthing ¦ Gang Name ¦ Gang Strength ¦ Remark Excavation ¦ Stub Setting ¦ PCC ¦ Rebar Placing ¦ RCC 1 ¦ 85/0 ¦ DC+0 ¦ DFR ¦ 2025-10-01 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-23 00:00:00 ¦ 2025-10-23 00:00:00 ¦ 2025-10-24 00:00:00 ¦ 2025-10-26 00:00:00 ¦ 2025-10-26 00:00:00 ¦ Completed ¦ 2025-11-09 00:00:00 ¦ Ankush Sharma ¦ 8 2 ¦ 86/0 ¦ DD+0 ¦ DFR ¦ 2025-10-24 00:00:00 ¦ 2025-11-06 00:00:00 ¦ 2025-11-07 00:00:00 ¦ 2025-11-09 00:00:00 ¦ 2025-11-09 00:00:00 ¦ 2025-11-10 00:00:00 ¦ 2025-11-10 00:00:00 ¦ Completed ¦ 2025-11-11 00:00:00 ¦ Ankush Sharma ¦ 13 3 ¦ 106/0 ¦ DB+0 ¦ DFR ¦ 2025-10-14 00:00:00 ¦ 2025-10-23 00:00:00 ¦ 2025-10-30 00:00:00 ¦ 2025-10-30 00:00:00 ¦ 2025-10-31 00:00:00 ¦ 2025-10-31 00:00:00 ¦ 2025-10-31 00:00:00 ¦ Completed ¦ 2025-11-20 00:00:00 ¦ Naresh ¦ 8 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Manpower | 45 | 28 | commercial, erection, foundation, row_hindrance, survey_soil | R4: Team ¦ Foundation ¦ Team ¦ Tower Erection ¦ JCB ¦ 15 ¦ 15 ¦ 2 ¦ 2 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 10 R6: ROW Lead ¦ 2 ¦ 3 ¦ Thakur Const ¦ J-S (Jammu) ¦ 11 ¦ 2 ¦ Saritha Devi ¦ J-S (Punjab) ¦ 24 ¦ Water Tanker ¦ 12 ¦ 12 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 5 R7: ROWOfficer /Patwari ¦ 5 ¦ 4 ¦ Anil Sharma ¦ J-S (Jammu) ¦ 12 ¦ 3 ¦ Jwala Singh ¦ J-S (Punjab) ¦ 25 ¦ Dewatering Pump ¦ 13 ¦ 13 R9: Commercial Incharge/ Officer ¦ 2 ¦ 11 ¦ MS Constructions ¦ J-S (Punjab) ¦ 16 ¦ 5 ¦ ASC Infra ¦ J-S (Jammu) ¦ 24 ¦ Mixer Machine ¦ 12 ¦ 12 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 R12: Sr. Surveyor ¦ 3 ¦ 14 ¦ Ganesh ¦ K-S ¦ 10 ¦ 2 ¦ 1 ¦ 4 ¦ 4 ¦ 11 | Date ¦ 2026-05-20 00:00:00 MAN POWER & MACHINERY RESOURCES Type of Staff ¦ M/s. KEC ¦ Manpower in Gangs ¦ Line ¦ Qty ¦ Manpower in Gangs ¦ Line ¦ Qty ¦ CIVIL Machinery & Plant ¦ Working ¦ Idle ¦ Total ¦ Adhshiv ¦ Vishal ¦ Md S ¦ Bal ¦ Zaff ¦ KK ¦ Anchal ¦ Ramesh Team ¦ Foundation ¦ Team ¦ Tower Erection ¦ JCB ¦ 15 ¦ 15 ¦ 2 ¦ 2 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 10 Project Manager ¦ 1 ¦ 1&2 ¦ Pawan Kumar Sharma ¦ J-S (Jammu) ¦ 22 ¦ 1 ¦ Kushboo Devi-1 ¦ J-S (Jammu) ¦ 20 ¦ Ajax Flori ¦ 18 ¦ 18 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 6 ROW Lead ¦ 2 ¦ 3 ¦ Thakur Const ¦ J-S (Jammu) ¦ 11 ¦ 2 ¦ Saritha Devi ¦ J-S (Punjab) ¦ 24 ¦ Water Tanker ¦ 12 ¦ 12 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ 5 ROWOfficer /Patwari ¦ 5 ¦ 4 ¦ Anil Sharma ¦ J-S (Jammu) ¦ 12 ¦ 3 ¦ Jwala Singh ¦ J-S (Punjab) ¦ 25 ¦ Dewatering Pump ¦ 13 ¦ 13 Planning/Cons. Manager ¦ 3 ¦ 5,6,7,8,9&10 ¦ Sufiyan Ali ¦ J-S (Punjab) ¦ 69 ¦ 4 ¦ Vijay Kumar Bhagat-2 ¦ J-S (Punjab) ¦ 20 ¦ Tractor ¦ 11 ¦ 11 ¦ 1 ¦ 2 ¦ 5 ¦ 2 ¦ 2 ¦ 1 ¦ 13 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sum | 21 | 7 | erection, foundation, row_hindrance | R5: 1 ¦ Samba-Jalandhar ¦ 18 ¦ 1 ¦ 4 ¦ 23 R13: 1 ¦ Samba-Jalandhar ¦ 9 ¦ 3 ¦ 4 ¦ 16 R20: 1 ¦ Samba-Jalandhar ¦ 1 ¦ 1 | Foundation S.No ¦ Line ¦ Gangs Available ¦ Additional Gangs ¦ Total Gangs Planned by 3rd May ¦ Planned by 10th May 1 ¦ Samba-Jalandhar ¦ 18 ¦ 1 ¦ 4 ¦ 23 2 ¦ Samba-Kishenpur ¦ 6 ¦ 6 3 ¦ LILO-Kisthwar ¦ 3 ¦ 3 27 ¦ 1 ¦ 4 ¦ 32 Tower Erection | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet18 | 51 | 18 | erection, foundation, row_hindrance, stringing | R1: Foundation ¦ Tower Erection ¦ Stringing R2: Samba- Jalandhar TL-Jammu ¦ Samba- Jalandhar TL-Jammu ¦ Samba- Jalandhar TL R3: S.No ¦ Sub Vendor ¦ Available ¦ Mobilization Planned ¦ Remarks ¦ S.No ¦ Sub Vendor ¦ Available ¦ Mobilization Planned ¦ Remarks ¦ S.No ¦ Sub Vendor ¦ Available ¦ Mobilization Planned ¦ Remarks R16: S.No ¦ Sub Vendor ¦ Available ¦ Mobilization Planned ¦ Remarks ¦ S.No ¦ Sub Vendor ¦ Available ¦ Mobilization Planned ¦ Remarks R33: Samba-Kishenpur ¦ S.No ¦ Sub Vendor ¦ Available ¦ Mobilization Planned ¦ Remarks | Foundation ¦ Tower Erection ¦ Stringing Samba- Jalandhar TL-Jammu ¦ Samba- Jalandhar TL-Jammu ¦ Samba- Jalandhar TL S.No ¦ Sub Vendor ¦ Available ¦ Mobilization Planned ¦ Remarks ¦ S.No ¦ Sub Vendor ¦ Available ¦ Mobilization Planned ¦ Remarks ¦ S.No ¦ Sub Vendor ¦ Available ¦ Mobilization Planned ¦ Remarks 1 ¦ Balwant Singh-1 ¦ 11 ¦ 1 ¦ Kushboo Devi-1 ¦ 20 ¦ 1 ¦ Jiyaul Hoque ¦ 10 ¦ Mob Planned by 10th May 2 ¦ Balwant Singh-2 ¦ 10 ¦ 2 ¦ Kushboo Devi-2 ¦ 22 ¦ Total ¦ 10 3 ¦ Pawan Sharma-1 ¦ 12 ¦ 3 ¦ ASIC Infra ¦ 23 4 ¦ Pawan Sharma-2 ¦ 10 ¦ 4 ¦ Niva Sarkar Mandal ¦ 20 ¦ Mob Planned by 3rd May 5 ¦ Anil Sharma ¦ 10 ¦ Total ¦ 65 ¦ 20 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | JS-Supply Stubs | 30 | 15 | supply, survey_soil | R2: Tower ¦ Structure ¦ UOM ¦ Qty as per Approved C/S Jammu ¦ Qty as per Approved C/S Punjab ¦ Total Qty as per approved C/S ¦ Material Received in Jammu ¦ Material Received in Punjab ¦ Total Received ¦ Balance ¦ Remarks R3: DA ¦ STUB(UPTO+9M) ¦ Set ¦ 74 ¦ 124 ¦ 198 ¦ 80 ¦ 116 ¦ 196 ¦ 2 R9: DB ¦ STUB(UPTO+9M) ¦ Set ¦ 17 ¦ 38 ¦ 55 ¦ 20 ¦ 33 ¦ 53 ¦ 2 ¦ DB ¦ 5 R12: 2M RC ¦ Legs ¦ 1 ¦ 1 ¦ 1 ¦ 4 ¦ 5 ¦ -4 ¦ Qty recived as per approved survey , but due to revison of survey qty became excess R13: DC ¦ STUB(UPTO+9M) ¦ Set ¦ 13 ¦ 33 ¦ 46 ¦ 20 ¦ 24 ¦ 44 ¦ 2 | Stubs - SJ Line Tower ¦ Structure ¦ UOM ¦ Qty as per Approved C/S Jammu ¦ Qty as per Approved C/S Punjab ¦ Total Qty as per approved C/S ¦ Material Received in Jammu ¦ Material Received in Punjab ¦ Total Received ¦ Balance ¦ Remarks DA ¦ STUB(UPTO+9M) ¦ Set ¦ 74 ¦ 124 ¦ 198 ¦ 80 ¦ 116 ¦ 196 ¦ 2 1M RC ¦ Legs ¦ 8 ¦ 4 ¦ 12 ¦ 8 ¦ 4 ¦ 12 1.5M RC ¦ Legs ¦ 5 ¦ 12 ¦ 17 ¦ 5 ¦ 10 ¦ 15 ¦ 2 2M RC ¦ Legs 2M RC ¦ Legs 2.5M RC ¦ Legs ¦ 1 ¦ 1 ¦ 1 ¦ 1 ¦ DA ¦ 5 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | JS Supply Towers | 32 | 11 | supply | R2: Tower ¦ Structure ¦ Qty as per Approved C/S Jammu ¦ Qty as per Approved C/S Punjab ¦ Total Qty as per approved C/S ¦ Material Received in Jammu ¦ Material Received in Punjab ¦ Total Received ¦ Inspection Completed on 18th Mar'26 and Material under transit ¦ Balance ¦ Remarks | TOWERS - SJ Line Tower ¦ Structure ¦ Qty as per Approved C/S Jammu ¦ Qty as per Approved C/S Punjab ¦ Total Qty as per approved C/S ¦ Material Received in Jammu ¦ Material Received in Punjab ¦ Total Received ¦ Inspection Completed on 18th Mar'26 and Material under transit ¦ Balance ¦ Remarks DA ¦ Basic Tower Body ¦ 76 ¦ 125 ¦ 201 ¦ 84 ¦ 98 ¦ 182 ¦ 19 +0MBE ¦ 52 ¦ 88 ¦ 140 ¦ 62 ¦ 59 ¦ 121 ¦ 19 +3MBE ¦ 24 ¦ 37 ¦ 61 ¦ 22 ¦ 39 ¦ 61 +6MBE ¦ 10 ¦ 14 ¦ 24 ¦ 10 ¦ 14 ¦ 24 +9MBE ¦ 2 ¦ 5 ¦ 7 ¦ 2 ¦ 3 ¦ 5 ¦ 2 DB ¦ Basic Tower Body ¦ 17 ¦ 39 ¦ 56 ¦ 7 ¦ 39 ¦ 46 ¦ 10 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | SK Supply Stubs | 44 | 12 | supply, survey_soil | R2: Tower ¦ Structure ¦ UOM ¦ Qty as per C/S. Approved ¦ Material Received ¦ Balance ¦ Remarks R3: DA ¦ STUB(UPTO+9M) ¦ Set ¦ 1 ¦ 2 ¦ -1 ¦ Qty recived as per approved survey , but due to revison of survey qty became excess R5: 1.5M RC ¦ Leg ¦ 2 ¦ -2 ¦ Qty recived as per approved survey , but due to revison of survey qty became excess R8: DB ¦ STUB(UPTO+9M) ¦ Set ¦ 33.5 ¦ 31 ¦ 2.5 ¦ 1.5 R17: DC ¦ STUB(UPTO+9M) ¦ Set ¦ 33.25 ¦ 31 ¦ 2.25 | Stubs - SK Line Tower ¦ Structure ¦ UOM ¦ Qty as per C/S. Approved ¦ Material Received ¦ Balance ¦ Remarks DA ¦ STUB(UPTO+9M) ¦ Set ¦ 1 ¦ 2 ¦ -1 ¦ Qty recived as per approved survey , but due to revison of survey qty became excess 1M RC ¦ Leg 1.5M RC ¦ Leg ¦ 2 ¦ -2 ¦ Qty recived as per approved survey , but due to revison of survey qty became excess 2M RC ¦ Leg 2.5M RC ¦ Leg DB ¦ STUB(UPTO+9M) ¦ Set ¦ 33.5 ¦ 31 ¦ 2.5 ¦ 1.5 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | SK Supply Towers | 52 | 7 | supply | R2: Tower ¦ Structure ¦ Qty as per C/S. Approved ¦ Material Supplied till date (21st Feb'26) ¦ Inspection Completed on 18th Mar'26 and Material under transit ¦ Balance ¦ Remarks | Tower SK Line Tower ¦ Structure ¦ Qty as per C/S. Approved ¦ Material Supplied till date (21st Feb'26) ¦ Inspection Completed on 18th Mar'26 and Material under transit ¦ Balance ¦ Remarks DA ¦ Basic Tower Body ¦ 1 ¦ 1 +0MBE ¦ 1 ¦ 1 DB ¦ Basic Tower Body ¦ 35 ¦ 14 ¦ 7 ¦ 14 +0MBE ¦ 13 ¦ 14 ¦ -1 ¦ Will be used in JS line +3MBE ¦ 3 ¦ 2 ¦ 1 +6MBE ¦ 1 ¦ 1 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet11 | 17 | 7 | project_details, row_hindrance | R7: 400 kV Samba- Jalandhar D/C line (Quad) ¦ 137 ¦ 20 ¦ 2027-01-15 00:00:00 | Project Name ¦ Transmission Scheme for Evacuation of Power From Ratle HEP (850 MW) & Kiru HEP (624MW): Part-A Client ¦ RATLE KIRU POWER TRANSMISSION EMPLOYER LIMITED LOA DATE (Start Date) ¦ 16th MAY 2025 Name of the Line ¦ KM ¦ Months ¦ Comp Date 400 kV Samba- Jalandhar D/C line (Quad) ¦ 137 ¦ 20 ¦ 2027-01-15 00:00:00 400 kV Kishenpur-Samba D/C line (Quad) ¦ 33 ¦ 22 ¦ 2027-03-15 00:00:00 LILO of 400 kV Kishenpur- Dulhasti line (Twin) at Kishtwar S/s ¦ 3.4 ¦ 18 ¦ 2026-11-15 00:00:00 173.4 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Planned Vs Actual -FDN | 54 | 16 | foundation, row_hindrance, summary_status, visual_l2 | R9: Sr. No. ¦ Section ¦ Loc. No. ¦ Tower Type ¦ Classification ¦ Status ¦ Planned ¦ Actual ¦ Remark R10: Loc. No. ¦ Tower Type ¦ Classification ¦ Status ¦ Start ¦ End ¦ Start ¦ End ¦ Start ¦ End ¦ Start ¦ End R12: 1 ¦ Jammu ¦ 29/3 ¦ DA+0 ¦ Dry ¦ ROW Clear ¦ 2025-08-31 00:00:00 ¦ 2025-09-04 00:00:00 ¦ 2025-09-02 00:00:00 ¦ 2025-09-05 00:00:00 ¦ 2025-09-04 00:00:00 ¦ 2025-09-09 00:00:00 ¦ 2025-08-31 00:00:00 ¦ 2025-09-24 00:00:00 R13: 2 ¦ AP27 ¦ DB+0 ¦ Wet ¦ ROW Clear ¦ 2025-09-09 00:00:00 ¦ 2025-09-14 00:00:00 ¦ 2025-09-12 00:00:00 ¦ 2025-09-16 00:00:00 ¦ 2025-09-14 00:00:00 ¦ 2025-09-20 00:00:00 ¦ 2025-09-07 00:00:00 ¦ 2025-09-20 00:00:00 R14: 3 ¦ 30/3 ¦ DA+6 ¦ PS ¦ ROW Clear ¦ 2025-09-20 00:00:00 ¦ 2025-09-24 00:00:00 ¦ 2025-09-22 00:00:00 ¦ 2025-09-25 00:00:00 ¦ 2025-09-24 00:00:00 ¦ 2025-09-27 00:00:00 ¦ 2025-09-30 00:00:00 ¦ Boring u/p | KEC INTERNATIONAL LIMITED 400 kV Samba- Jalandhar D/C Line(Quad) - Wind Zone - 5 FOUNDATION -Plan Vs Actual Week ¦ W1 (1-7) ¦ W2 (8-14) ¦ W3 (15-21) ¦ W4 (22-30) ¦ Total Planned ¦ 1 ¦ 3 ¦ 7 ¦ 8 ¦ 19 Actual ¦ 1 ¦ 1 ¦ 1 ¦ 3 Sr. No. ¦ Section ¦ Loc. No. ¦ Tower Type ¦ Classification ¦ Status ¦ Planned ¦ Actual ¦ Remark Loc. No. ¦ Tower Type ¦ Classification ¦ Status ¦ Start ¦ End ¦ Start ¦ End ¦ Start ¦ End ¦ Start ¦ End | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Supply Status | 46 | 22 | row_hindrance, summary_status, supply, survey_soil, visual_l2 | R1: Samba-Jalandhar (Stubs) ¦ Samba-Kishenpur (Stubs) ¦ LILO-Kishtwar (Stubs) R2: S.No ¦ Stub ¦ Qty asper approved Survey ¦ L2 till Feb'26 ¦ Supplied Qty till date ¦ Supply u/p ¦ Remarks ¦ S.No ¦ Stub ¦ Qty asper approved Survey ¦ L2 till Feb'26 ¦ Supplied Qty till date ¦ Supply u/p ¦ Remarks ¦ S.No ¦ Stub ¦ Qty asper Survey ¦ L2 till Feb'26 ¦ Supplied Qty till date R10: Samba-Jalandhar (Stubs) ¦ Samba-Kishenpur(Towers) ¦ LILO-Kishtwar (Tower) R11: S.No ¦ Tower ¦ Qty asper approved Survey ¦ L2 till Feb'26 ¦ Supplied Qty till date ¦ Supply u/p ¦ Remarks ¦ S.No ¦ Tower ¦ Qty asper approved Survey ¦ L2 till Feb'26 ¦ Supplied Qty till date ¦ Supply u/p ¦ Remarks ¦ S.No ¦ Tower ¦ Qty asper Survey ¦ L2 till Feb'26 ¦ Supplied Qty till date R37: 400 kV D/C Samba-Jalandhar Punjab Portion ¦ 2026-03-09 00:00:00 ¦ 2026-03-09 00:00:00 ¦ 36 ¦ 130/2- Due to ROW , Tower Erection Work Hampered ¦ BTB ¦ 15 | Samba-Jalandhar (Stubs) ¦ Samba-Kishenpur (Stubs) ¦ LILO-Kishtwar (Stubs) S.No ¦ Stub ¦ Qty asper approved Survey ¦ L2 till Feb'26 ¦ Supplied Qty till date ¦ Supply u/p ¦ Remarks ¦ S.No ¦ Stub ¦ Qty asper approved Survey ¦ L2 till Feb'26 ¦ Supplied Qty till date ¦ Supply u/p ¦ Remarks ¦ S.No ¦ Stub ¦ Qty asper Survey ¦ L2 till Feb'26 ¦ Supplied Qty till date 1 ¦ DA ¦ 201 ¦ 434 ¦ 186 ¦ 1 ¦ DA ¦ 1 ¦ 129 ¦ 2 ¦ 1 ¦ DDM ¦ 13 ¦ 14 ¦ 10 2 ¦ DB ¦ 57 ¦ 49 ¦ 2 ¦ DB ¦ 20 ¦ 18.75 ¦ Total ¦ 13 ¦ 14 ¦ 10 3 ¦ DC ¦ 44 ¦ 38 ¦ 3 ¦ DC ¦ 21 ¦ 16.75 4 ¦ DD ¦ 63 ¦ 54 ¦ 4 ¦ DD ¦ 29 ¦ 26 Total ¦ 365 ¦ 434 ¦ 327 ¦ Total ¦ 71 ¦ 129 ¦ 63.5 Samba-Jalandhar (Stubs) ¦ Samba-Kishenpur(Towers) ¦ LILO-Kishtwar (Tower) | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Material Status-Jammu-Punjab | 57 | 20 | summary_status, supply | R8: Sl No. ¦ Description of Material ¦ Unit ¦ Receipt of Material ¦ Material Issued to Site ¦ Stock Avaialbilty ¦ Remarks R9: Receipt through Direct Supply ¦ Transfer In ¦ Transfer Out ¦ Net Receipt R23: 3 ¦ STUBS ¦ Set R39: 5.2 ¦ Pipe Type Earthing ¦ Nos ¦ 130 ¦ 130 ¦ 46 ¦ 46 ¦ 84 ¦ 84 ¦ 4 ¦ 4 ¦ 80 R44: Sl No. ¦ Description of Material ¦ Unit ¦ Receipt of Material ¦ Material Issued to Site ¦ Stock Avaialbilty ¦ Remarks | CLIENT :- Ratle Kiru Power Transmission Ltd EXECUTING AGENCY:- KEC INTERNATIONAL LTD. Name of Project :- ''Transmission Line Portion for “Transmission scheme for evacuation of power from Ratle HEP (850 MW) & Kiru HEP (624 MW): Part-A” Project Code :- TB605 ¦ Date :- ¦ 2026-05-20 00:00:00 Jammu MATERIAL STATUS AS ON DATE Sl No. ¦ Description of Material ¦ Unit ¦ Receipt of Material ¦ Material Issued to Site ¦ Stock Avaialbilty ¦ Remarks Receipt through Direct Supply ¦ Transfer In ¦ Transfer Out ¦ Net Receipt | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Material Status-Punjab | 30 | 20 | summary_status, supply | R7: Sl No. ¦ Description of Material ¦ Unit ¦ Receipt of Material ¦ Material Issued to Site ¦ Balance in stock ¦ Remarks R8: Receipt through Direct Supply ¦ Transfer In ¦ Transfer Out ¦ Net Receipt R22: 3 ¦ STUBS ¦ Set R30: 4.2 ¦ Pipe Type Earthing ¦ Nos ¦ 46 ¦ 46 ¦ 46 ¦ 46 ¦ 11 ¦ 11 ¦ 35 | CLIENT :- Ratle Kiru Power Transmission Ltd EXECUTING AGENCY:- KEC INTERNATIONAL LTD. ¦ *Material supply updated / Consumption to beupdated Name of Project :- ''Transmission Line Portion for “Transmission scheme for evacuation of power from Ratle HEP (850 MW) & Kiru HEP (624 MW): Part-A” Project Code :- TB605 ¦ Date :- ¦ 2026-05-20 00:00:00 MATERIAL STATUS AS ON DATE Sl No. ¦ Description of Material ¦ Unit ¦ Receipt of Material ¦ Material Issued to Site ¦ Balance in stock ¦ Remarks Receipt through Direct Supply ¦ Transfer In ¦ Transfer Out ¦ Net Receipt Since Previous ¦ On Date ¦ Total as on Date ¦ Since Previous ¦ On Date ¦ Total as on Date ¦ Since Previous ¦ On Date ¦ Total as on Date ¦ Since Previous ¦ On Date ¦ Total as on Date ¦ Since Previous ¦ On Date ¦ Total as on Date | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Earthing (PKG-F) | 241 | 13 | earthing_tack | R4: Sl. No. ¦ Cum S No ¦ Location No. ¦ Tower Type ¦ Classification ¦ Type of Earthing ¦ Earthing ¦ Name of Sub-Contractor ¦ Check list | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Earthing Sl. No. ¦ Cum S No ¦ Location No. ¦ Tower Type ¦ Classification ¦ Type of Earthing ¦ Earthing ¦ Name of Sub-Contractor ¦ Check list 2023-12-01 00:00:00 1 ¦ 1 ¦ 61/3 ¦ DA+6 ¦ DRY ¦ Pipe Type ¦ 18.12.23 ¦ Manoj Sharma 2 ¦ 2 ¦ 62/4 ¦ DA+3 ¦ DRY ¦ Pipe Type ¦ 31.12.23 ¦ Shakti Const. 2024-01-01 00:00:00 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Earthing (PKG-G) | 339 | 13 | earthing_tack | R4: Cum S No ¦ Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Type of Earthing ¦ Earthing ¦ Name of Sub-Contractor ¦ Check list | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Earthing Cum S No ¦ Sl. No. ¦ Location No. ¦ Tower Type ¦ Classification ¦ Type of Earthing ¦ Earthing ¦ Name of Sub-Contractor ¦ Check list 2023-08-01 00:00:00 1 ¦ 1 ¦ 58/1 ¦ DA+0 ¦ DRY ¦ Pipe Type ¦ 16.08.23 ¦ Mahadev engg. ¦ Check list submitted 2 ¦ 2 ¦ 58/11 ¦ DA+3 ¦ DRY ¦ Pipe Type ¦ 20.08.23 ¦ Mahadev engg. ¦ Check list submitted 3 ¦ 3 ¦ 58/3 ¦ DA+3 ¦ DRY ¦ Pipe Type ¦ 24.8.23 ¦ Mahadev engg. ¦ Check list submitted | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Revetment Pkg-G | 13 | 11 | foundation | R5: SI. No ¦ Loc No ¦ Tower Type ¦ Dt. of Start ¦ Dt. of complete ¦ Random Rubble stone masonry including excavation (1:5 Cement concrete) ¦ Excavation Volume ¦ Back filling and levelling of volumes enclosed by revetment. ¦ M15 Conc Nominal Mix 1:2:4 for top seal cover ¦ M10 (PEDDING -PCC) | Revetment work SI. No ¦ Loc No ¦ Tower Type ¦ Dt. of Start ¦ Dt. of complete ¦ Random Rubble stone masonry including excavation (1:5 Cement concrete) ¦ Excavation Volume ¦ Back filling and levelling of volumes enclosed by revetment. ¦ M15 Conc Nominal Mix 1:2:4 for top seal cover ¦ M10 (PEDDING -PCC) 1 ¦ 35/5 ¦ DA+0 RC ¦ 20.11.24 Total | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Benching Status-F | 143 | 23 | summary_status | R2: Sl No. ¦ RC ¦ Loc No. ¦ Tower Type ¦ CP Position Up/Down ¦ Raised Chimney ¦ Chimney Extension ¦ Submitted Benching Volume (Cum) ¦ Approved Benching Volume (Cum) ¦ Approval Date ¦ JMC NO ¦ JMC Date | RC, Benching & Revetment Locations Sl No. ¦ RC ¦ Loc No. ¦ Tower Type ¦ CP Position Up/Down ¦ Raised Chimney ¦ Chimney Extension ¦ Submitted Benching Volume (Cum) ¦ Approved Benching Volume (Cum) ¦ Approval Date ¦ JMC NO ¦ JMC Date A ¦ B ¦ C ¦ D ¦ Cutting ¦ Filling ¦ Cutting ¦ Filling 47 ¦ 26947.807 ¦ 10818.857 ¦ 10 1 ¦ 40/0 ¦ DC2+0 ¦ 1 ¦ 1 ¦ 91.75 2 ¦ Y ¦ 40/1 ¦ DA+6 ¦ 1 ¦ 2 ¦ 153.267 3 ¦ 40/2 ¦ DA+3 ¦ 48.633 4 ¦ Y ¦ 40/3 ¦ DA+6 ¦ 1 ¦ 2 ¦ 238.433 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Benching Status-G | 188 | 17 | summary_status | R2: Sl No. ¦ RC ¦ Loc No. ¦ Tower Type ¦ CP Position Up/Down ¦ Raised Chimney ¦ Chimney Extension ¦ Submitted Benching Volume (Cum) ¦ Approved Benching Volume (Cum) ¦ Approval Date ¦ JMC NO ¦ JMC Date | RC, Benching & Revetment Locations Sl No. ¦ RC ¦ Loc No. ¦ Tower Type ¦ CP Position Up/Down ¦ Raised Chimney ¦ Chimney Extension ¦ Submitted Benching Volume (Cum) ¦ Approved Benching Volume (Cum) ¦ Approval Date ¦ JMC NO ¦ JMC Date A ¦ B ¦ C ¦ D ¦ Cutting ¦ Filling ¦ Cutting ¦ Filling 28 ¦ 36249.3290380952 ¦ 13738.234 ¦ 8 1 ¦ 2/0 ¦ DC1+0 2 ¦ 2/2 ¦ DA+0 ¦ 1 ¦ 1 ¦ 141.89 ¦ 140.97 ¦ 24-11-23 3 ¦ 2/3 ¦ DA+0 ¦ 1 ¦ 1 ¦ 33.32 ¦ 22.61 ¦ 24-11-23 4 ¦ 2/4 ¦ DA+3 ¦ 28.01 ¦ 28.01 ¦ 24-11-23 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Earthing Pkg -G Ist section | 11 | 8 | earthing_tack, foundation | R4: Sl. No. ¦ Cum S No ¦ Location No. ¦ Tower Type ¦ Classification ¦ Type of Earthing ¦ Earthing ¦ Name of Sub-Contractor | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL FOUNDATION Sl. No. ¦ Cum S No ¦ Location No. ¦ Tower Type ¦ Classification ¦ Type of Earthing ¦ Earthing ¦ Name of Sub-Contractor 1 ¦ 1 ¦ 32/7 ¦ DA+0 ¦ SANDY ¦ Pipe Type ¦ 07.11.23 ¦ Shakti Construction 2 ¦ 2 ¦ 32/1 ¦ DA+9 ¦ SANDY ¦ Pipe Type ¦ 10.11.23 ¦ Shakti Construction 3 ¦ 3 ¦ 32/5 ¦ DA+6 ¦ SANDY ¦ Pipe Type ¦ 10.11.23 ¦ Shakti Construction 4 ¦ 4 ¦ 30/2 ¦ DA+0 ¦ SANDY ¦ Pipe Type ¦ 18.11.23 ¦ Om Const | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Earthing balance | 14 | 8 | earthing_tack |  | S no ¦ PKG- G ¦ PKG- F 1 ¦ 72/1 ¦ Mahadev engg. ¦ 50/3 ¦ Kalpana Const. 2 ¦ 71/5 ¦ Mahadev engg. ¦ 73/9 ¦ Shakti Const. -2 3 ¦ 43/2 ¦ Sai Infra ¦ 73/2 ¦ Shree Shyam Const. 4 ¦ 43/3 ¦ Sai Infra ¦ 50/6 ¦ Kalpana Const. 5 ¦ 68/3 ¦ Shakti Const. -2 6 ¦ 73/0 ¦ Mahadev engg. - 2 7 ¦ 68/1 ¦ Shakti Const. -2 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tack Welding - PKG-G | 210 | 16084 | earthing_tack, summary_status | R4: Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Tack Welding Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks 2023-10-01 00:00:00 1 ¦ 1 ¦ 57/12 ¦ DA+3 ¦ 24.10.23 ¦ 25.10.23 ¦ Done ¦ Suraja Ram 2 ¦ 2 ¦ 57/13 ¦ DA+0 ¦ 24.10.23 ¦ 25.10.23 ¦ Done ¦ Suraja Ram 3 ¦ 3 ¦ 57/11 ¦ DA+0 ¦ 25.10.23 ¦ 26.10.23 ¦ Done ¦ Suraja Ram | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Tack Welding - PKG-F | 158 | 16384 | earthing_tack, foundation, summary_status | R4: Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Tack Welding Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks Feb-24 1 ¦ 1 ¦ 59/13 ¦ DA+3 ¦ 20.02.24 ¦ 20.02.24 ¦ Done ¦ Suraja Ram 2 ¦ 2 ¦ 59/14 ¦ DA+6 ¦ 22.02.24 ¦ 22.02.24 ¦ Done ¦ Suraja Ram 3 ¦ 3 ¦ 62/5 ¦ DA+0 ¦ 27.02.24 ¦ 27.02.24 ¦ Done ¦ Suraja Ram | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Painting - PKG-G | 207 | 16084 | earthing_tack, foundation, summary_status | R4: Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Painting Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks 2023-12-01 00:00:00 1 ¦ 1 ¦ 56/9 ¦ DA+3 ¦ 02.12.23 ¦ 03.12.23 ¦ Done ¦ Suraja Ram 2 ¦ 2 ¦ 57/1 ¦ DA+3 ¦ 02.12.23 ¦ 03.12.23 ¦ Done ¦ Suraja Ram 3 ¦ 3 ¦ 56/8 ¦ DA+3 ¦ 03.12.23 ¦ 06.12.23 ¦ Done ¦ Suraja Ram | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Painting - PKG-F | 156 | 16085 | earthing_tack, foundation, summary_status | R4: Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Painting Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Tack Welding Status ¦ Name of Sub-Contractor ¦ Ramarks 1 ¦ 1 ¦ 59/14 ¦ DA+6 ¦ 26.02.24 ¦ 26.02.24 ¦ Done ¦ Suraja Ram 2 ¦ 2 ¦ 63/6 ¦ DA+3 ¦ 29.02.24 ¦ 29.02.24 ¦ Done ¦ Suraja Ram March'24 3 ¦ 1 ¦ 62/3 ¦ DA+0 ¦ 11.03.24 ¦ 11.03.24 ¦ Done ¦ Suraja Ram | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Eretion - PKG-G | 225 | 16078 | erection, foundation | R4: Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Erection Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks 2023-09-01 00:00:00 1 ¦ 1 ¦ 57/9 ¦ DA+0 ¦ 13.09.23 ¦ 21.09.23 ¦ Sobha Devi ¦ Complete ¦ 37.504 2 ¦ 2 ¦ 58/12 ¦ DA+0 ¦ 18.09.23 ¦ 25.09.23 ¦ Sunny Const ¦ Complete ¦ 37.504 3 ¦ 3 ¦ 57/11 ¦ DA+0 ¦ 21.09.23 ¦ 26.09.23 ¦ Sobha Devi ¦ Complete ¦ 37.504 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Eretion - PKG-F | 190 | 16083 | erection, foundation | R4: Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Erection PKG-F Cum Sl. No. ¦ Month Sl. No. ¦ JMC No. ¦ Location No. ¦ Tower Type ¦ Depth of Fdn ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks Feb-24 1 ¦ 1 ¦ 60/7 ¦ DA+3 ¦ 28.1.24 ¦ 04.02.24 ¦ Suraj const ¦ Complete ¦ 38.847 2 ¦ 2 ¦ 59/13 ¦ DA+3 ¦ 01.02.24 ¦ 07.02.24 ¦ Chinta Devi ¦ Complete ¦ 38.847 3 ¦ 3 ¦ 63/6 ¦ DA+3 ¦ 03.02.24 ¦ 10.02.24 ¦ Sunny Const. ¦ Complete ¦ 38.847 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Sheet1 | 27 | 4 |  | R2: S No ¦ Loc No ¦ TOT ¦ Classification | S No ¦ Loc No ¦ TOT ¦ Classification 1 ¦ 58/14 ¦ DA+0 ¦ DRY 2 ¦ 51/7 ¦ DA+3 ¦ DFR 3 ¦ 51/5 ¦ DA+0 ¦ DRY 4 ¦ 51/2 ¦ DA+0 ¦ DRY 5 ¦ 53/2 ¦ DA+3 ¦ DFR 6 ¦ 57/7 ¦ DA+3 ¦ DRY 7 ¦ 57/4 ¦ DA+0 ¦ DRY | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | JMC 27.9.23 | 23 | 15 | foundation | R9: 7 ¦ 51/1 ¦ DA+0 ¦ DFR ¦ 10.09.23 ¦ Amirul Islam ¦ Excavation u/p R11: 9 ¦ 56/1 ¦ DA+3 ¦ DFR ¦ 21.09.23 ¦ Vaishali Const ¦ Excavation done R15: 13 ¦ 71/4 ¦ DA+0 ¦ DRY ¦ 23.09.23 ¦ Mahadev engg. ¦ Excavation complete ¦ 51 R16: 14 ¦ 55/11 ¦ DA+3 ¦ DFR ¦ 22.09.23 ¦ Nurul Amin ¦ Excavation u/p ¦ 32 R18: 16 ¦ 56/4 ¦ DA+3 ¦ DFR ¦ 24.9.23 ¦ Manoj Sharma ¦ Excavation | S no ¦ Locs no ¦ TOT ¦ Classification 1 ¦ 56/3 ¦ DA+0 ¦ DFR ¦ 14.09.23 ¦ 23.09.23 ¦ 25.09.23 ¦ Vaishali Const ¦ JMC required 2 ¦ 44/1 ¦ DA+0 ¦ WFR ¦ 16.09.23 ¦ 20.09.23 ¦ 25.09.23 ¦ Shakti Construction ¦ JMC required 3 ¦ 72/5 ¦ DA+0 ¦ DRY ¦ 19.09.23 ¦ 24.09.23 ¦ 25.09.23 ¦ Mahadev engg. ¦ JMC required 4 ¦ 41/10 ¦ DA+3 ¦ SANDY ¦ 19.09.23 ¦ 22.09.23 ¦ 25.09.23 ¦ Om Const ¦ JMC required 5 ¦ 56/6 ¦ DA+3 ¦ DRY ¦ 21.09.23 ¦ 24.09.23 ¦ 25.09.23 ¦ Manoj Sharma ¦ JMC required 6 ¦ 72/2 ¦ DA+0 ¦ DRY ¦ 15.09.23 ¦ 20.09.23 ¦ 26.09.23 ¦ Mahadev engg. ¦ JMC required 7 ¦ 51/1 ¦ DA+0 ¦ DFR ¦ 10.09.23 ¦ Amirul Islam ¦ Excavation u/p | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Jumpering-G | 13 | 7 | stringing, supply | R4: Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Jumpering ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Insulator Hoisting Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Jumpering ¦ Name of Sub-Contractor ¦ Ramarks 1 ¦ 1 ¦ 57/6 ¦ DB+0 ¦ 02.06.24 ¦ GPJ Const. ¦ Done 2 ¦ 2 ¦ 57/0 ¦ DB2+0 ¦ 12.07.24 ¦ GPJ Const. ¦ Done 3 ¦ 3 ¦ 56/0 ¦ DB1+0 ¦ 21.07.24 ¦ GPJ Const. ¦ Done 4 ¦ 4 ¦ 55/0 ¦ DC1+0 ¦ GPJ Const. ¦ Done | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Insulator Hoisting - F | 44 | 8 | supply | R4: Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Insulator Hoisting Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks July'24 1 ¦ 1 ¦ 60/11 ¦ DA+3 ¦ 21.07.24 ¦ 21.07.24 ¦ Kuddus ¦ Complete 2 ¦ 2 ¦ 60/9 ¦ DA+3 ¦ 22.07.24 ¦ 22.07.24 ¦ Kuddus ¦ Complete 3 ¦ 3 ¦ 60/10 ¦ DA+0 ¦ 22.07.24 ¦ 22.07.24 ¦ Kuddus ¦ Complete | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Insulator Hoisting - G | 73 | 9 | supply | R4: Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Insulator Hoisting Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Start ¦ Dt. of Complete ¦ Name of Sub-Contractor ¦ Ramarks Jan'24 1 ¦ 1 ¦ 57/5 ¦ DA+3 ¦ 05.01.24 ¦ 05.01.24 ¦ Mainul Hoque ¦ Complete 2 ¦ 2 ¦ 57/4 ¦ DA+0 ¦ 06.01.24 ¦ 06.01.24 ¦ Mainul Hoque ¦ Complete 3 ¦ 3 ¦ 57/3 ¦ DA+0 ¦ 07.01.24 ¦ 07.01.24 ¦ Mainul Hoque ¦ Complete | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Jumpering-F | 7 | 7 | stringing, supply | R4: Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Jumpering ¦ Name of Sub-Contractor ¦ Ramarks | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL Insulator Hoisting Cum Sl. No. ¦ Month Sl. No. ¦ Location No. ¦ Tower Type ¦ Dt. of Jumpering ¦ Name of Sub-Contractor ¦ Ramarks 1 ¦ 1 ¦ 61/0 ¦ 23.10.24 ¦ Kuddua Ali 2 ¦ 2 ¦ 62/0 ¦ 11.11.24 ¦ Kuddua Ali | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing - PKG-F | 22 | 19 | stringing | R5: S. No ¦ Section ¦ Paying Out ¦ Final Sag ¦ Name of Gang ¦ Remarks R6: From ¦ To ¦ Length ¦ Cum ¦ Start Date ¦ Finish Date ¦ Month ¦ Start Date ¦ Finish Date ¦ Month R7: 1 ¦ 60/0 ¦ 61/0 ¦ 4.877 ¦ 4.877 ¦ 21.08.24 ¦ 28.08.24 ¦ 2024-08-24 00:00:00 ¦ 09.09.24 ¦ 16.09.24 ¦ 2024-09-24 00:00:00 ¦ Kuddus ali ¦ Final sag completed R8: 2 ¦ 61/0 ¦ 62/0 ¦ 4.568 ¦ 9.445 ¦ 06.09.24 ¦ 16.09.24 ¦ 2024-09-24 00:00:00 ¦ 26.9.24 ¦ 03.10.24 ¦ 2024-10-24 00:00:00 ¦ Kuddus ali ¦ Final sag completed R9: 3 ¦ 62/0 ¦ 63/0 ¦ 4.863 ¦ 14.308 ¦ 23.09.24 ¦ 02.10.24 ¦ 2024-10-24 00:00:00 ¦ 17.10.24 ¦ 22.10.24 ¦ 2024-10-24 00:00:00 ¦ Kuddus ali ¦ Final sag completed | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL STRINGING Stringing - PKG-F S. No ¦ Section ¦ Paying Out ¦ Final Sag ¦ Name of Gang ¦ Remarks From ¦ To ¦ Length ¦ Cum ¦ Start Date ¦ Finish Date ¦ Month ¦ Start Date ¦ Finish Date ¦ Month 1 ¦ 60/0 ¦ 61/0 ¦ 4.877 ¦ 4.877 ¦ 21.08.24 ¦ 28.08.24 ¦ 2024-08-24 00:00:00 ¦ 09.09.24 ¦ 16.09.24 ¦ 2024-09-24 00:00:00 ¦ Kuddus ali ¦ Final sag completed 2 ¦ 61/0 ¦ 62/0 ¦ 4.568 ¦ 9.445 ¦ 06.09.24 ¦ 16.09.24 ¦ 2024-09-24 00:00:00 ¦ 26.9.24 ¦ 03.10.24 ¦ 2024-10-24 00:00:00 ¦ Kuddus ali ¦ Final sag completed | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Stringing - PKG-G | 24 | 13 | stringing | R4: S. No ¦ Section ¦ Paying Out ¦ Final Sag ¦ Name of Gang ¦ Remarks R5: From ¦ To ¦ Length ¦ Start Date ¦ Finish Date ¦ Month ¦ Start Date ¦ Finish Date ¦ Month R6: 1 ¦ 57/6 ¦ 58/0 ¦ 3.141 ¦ 06.05.2024 ¦ 10.05.24 ¦ 2024-05-24 00:00:00 ¦ 19.05.24 ¦ 24.05.24 ¦ 2024-05-24 00:00:00 ¦ GPJ Const. ¦ Final sag done R7: 2 ¦ 57/0 ¦ 57/6 ¦ 2.344 ¦ 16.05.24 ¦ 24.05.24 ¦ 2024-05-24 00:00:00 ¦ 07.06.24 ¦ 12.06.25 ¦ 2024-06-24 00:00:00 ¦ GPJ Const. ¦ Final sag done R8: 3 ¦ 56/0 ¦ 57/0 ¦ 4.127 ¦ 04.06.24 ¦ 12.06.24 ¦ 2024-06-24 00:00:00 ¦ 28.06.24 ¦ 04.07.24 ¦ 2024-07-24 00:00:00 ¦ GPJ Const. ¦ Final sag done | KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL STRINGING- PKG-G S. No ¦ Section ¦ Paying Out ¦ Final Sag ¦ Name of Gang ¦ Remarks From ¦ To ¦ Length ¦ Start Date ¦ Finish Date ¦ Month ¦ Start Date ¦ Finish Date ¦ Month 1 ¦ 57/6 ¦ 58/0 ¦ 3.141 ¦ 06.05.2024 ¦ 10.05.24 ¦ 2024-05-24 00:00:00 ¦ 19.05.24 ¦ 24.05.24 ¦ 2024-05-24 00:00:00 ¦ GPJ Const. ¦ Final sag done 2 ¦ 57/0 ¦ 57/6 ¦ 2.344 ¦ 16.05.24 ¦ 24.05.24 ¦ 2024-05-24 00:00:00 ¦ 07.06.24 ¦ 12.06.25 ¦ 2024-06-24 00:00:00 ¦ GPJ Const. ¦ Final sag done 3 ¦ 56/0 ¦ 57/0 ¦ 4.127 ¦ 04.06.24 ¦ 12.06.24 ¦ 2024-06-24 00:00:00 ¦ 28.06.24 ¦ 04.07.24 ¦ 2024-07-24 00:00:00 ¦ GPJ Const. ¦ Final sag done | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | OPGW PKG-G | 15 | 13 | opgw_accessories, stringing, summary_status | R4: Sr. No ¦ Section ¦ Section length in Kms ¦ OPGW Drum Length (In KMs) ¦ Start date ¦ End date ¦ Splicing ¦ Jointing Details ¦ Agency ¦ OTDR reading status ¦ Splicing done by ¦ Remarks R5: 1 ¦ 51/0 ¦ 52/0 ¦ 4.403 ¦ 4.653 ¦ 11.01.25 ¦ 12.01.25 ¦ Congent tech ¦ Final sag completed R6: 2 ¦ 52/0 ¦ 55/0 ¦ 4.377 ¦ 4.627 ¦ 17.01.25 ¦ 18.01.25 ¦ Congent tech ¦ Final sag completed R7: 3 ¦ 55/0 ¦ 56/0 ¦ 4.9 ¦ 5.16 ¦ 20.01.25 ¦ 21.01.25 ¦ Congent tech ¦ Final sag completed R8: 4 ¦ 56/0 ¦ 57/0 ¦ 4.127 ¦ 4.372 ¦ 23.01.25 ¦ 24.01.25 ¦ Congent tech ¦ Final sag completed | EXECUTING AGENCY : M/s. KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL OPGW Progress details(Pkg-G) Sr. No ¦ Section ¦ Section length in Kms ¦ OPGW Drum Length (In KMs) ¦ Start date ¦ End date ¦ Splicing ¦ Jointing Details ¦ Agency ¦ OTDR reading status ¦ Splicing done by ¦ Remarks 1 ¦ 51/0 ¦ 52/0 ¦ 4.403 ¦ 4.653 ¦ 11.01.25 ¦ 12.01.25 ¦ Congent tech ¦ Final sag completed 2 ¦ 52/0 ¦ 55/0 ¦ 4.377 ¦ 4.627 ¦ 17.01.25 ¦ 18.01.25 ¦ Congent tech ¦ Final sag completed 3 ¦ 55/0 ¦ 56/0 ¦ 4.9 ¦ 5.16 ¦ 20.01.25 ¦ 21.01.25 ¦ Congent tech ¦ Final sag completed 4 ¦ 56/0 ¦ 57/0 ¦ 4.127 ¦ 4.372 ¦ 23.01.25 ¦ 24.01.25 ¦ Congent tech ¦ Final sag completed | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | OPGW PKG-F | 17 | 13 | opgw_accessories, stringing, summary_status | R4: Sr. No ¦ Section ¦ Section length in Kms ¦ OPGW Drum Length (In KMs) ¦ Start date ¦ End date ¦ Splicing ¦ Jointing Details ¦ Agency ¦ OTDR reading status ¦ Splicing done by ¦ Remarks R5: 1 ¦ 59/0 ¦ 59/8 ¦ 3.337 ¦ 10.02.25 ¦ 11.02.25 ¦ 05.03.25 ¦ Congent tech ¦ Revant Sharma ¦ Final Sag Complete R6: 2 ¦ 59/8 ¦ 60/0 ¦ 3.778 ¦ 12.02.25 ¦ 13.02.25 ¦ 26.02.25 ¦ Congent tech ¦ Revant Sharma ¦ Final Sag Complete R7: 3 ¦ 60/0 ¦ 61/0 ¦ 4.877 ¦ 15.02.25 ¦ 16.02.25 ¦ Congent tech ¦ Final Sag Complete R8: 4 ¦ 61/0 ¦ 62/0 ¦ 4.568 ¦ 19.02.25 ¦ 19.02.25 ¦ 27.02.25 ¦ Congent tech ¦ Revant Sharma ¦ Final Sag Complete | EXECUTING AGENCY : M/s. KEC INTERNATIONAL LIMITED LILO of 765 Kv DV Fatehgarh 3 Beawar TL OPGW Progress details(PKG-F) Sr. No ¦ Section ¦ Section length in Kms ¦ OPGW Drum Length (In KMs) ¦ Start date ¦ End date ¦ Splicing ¦ Jointing Details ¦ Agency ¦ OTDR reading status ¦ Splicing done by ¦ Remarks 1 ¦ 59/0 ¦ 59/8 ¦ 3.337 ¦ 10.02.25 ¦ 11.02.25 ¦ 05.03.25 ¦ Congent tech ¦ Revant Sharma ¦ Final Sag Complete 2 ¦ 59/8 ¦ 60/0 ¦ 3.778 ¦ 12.02.25 ¦ 13.02.25 ¦ 26.02.25 ¦ Congent tech ¦ Revant Sharma ¦ Final Sag Complete 3 ¦ 60/0 ¦ 61/0 ¦ 4.877 ¦ 15.02.25 ¦ 16.02.25 ¦ Congent tech ¦ Final Sag Complete 4 ¦ 61/0 ¦ 62/0 ¦ 4.568 ¦ 19.02.25 ¦ 19.02.25 ¦ 27.02.25 ¦ Congent tech ¦ Revant Sharma ¦ Final Sag Complete | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Crossing | 21 | 19 | statutory_crossing, summary_status | R2: Sl No ¦ Crossing Name ¦ PART - G ¦ PART - F R3: Section ¦ Owner Name ¦ Date of Submission ¦ Date of Site Inspection ¦ Proposal Status ¦ Remarks ¦ Section ¦ Owner Name ¦ Date of Submission ¦ Date of Site Inspection ¦ Proposal Status ¦ Remarks R4: From ¦ To ¦ From ¦ To R13: 2 ¦ Bharatmala Expressway (Amritsar - Kandla) ¦ AP 49 ¦ AP 50 ¦ NHAI ¦ 2023-11-13 00:00:00 ¦ Approved on dated - 01.06.24 ¦ AP 58 ¦ AP 59 ¦ NHAI ¦ 2024-01-21 00:00:00 ¦ Approved on dated - 01.06.24 R15: 4 ¦ NH 25 (Jodhpur - Barmer) ¦ AP 62 ¦ AP 63 ¦ NHAI ¦ 2023-12-06 00:00:00 ¦ Approved on dated - 24.06.24 ¦ AP 68 ¦ AP 69 ¦ NHAI ¦ 2024-02-13 00:00:00 ¦ Approved on dated - 24.06.24 | CROSSING DETAILS FOR 765 KV DC FATEHGARH 3 - BEAWAR T/L (Part-G & Part-F) Sl No ¦ Crossing Name ¦ PART - G ¦ PART - F Section ¦ Owner Name ¦ Date of Submission ¦ Date of Site Inspection ¦ Proposal Status ¦ Remarks ¦ Section ¦ Owner Name ¦ Date of Submission ¦ Date of Site Inspection ¦ Proposal Status ¦ Remarks From ¦ To ¦ From ¦ To A ¦ Power Line 1 ¦ 400 KV D/C Rajwest - Jodhpur Line ¦ AP 36 ¦ AP 37 ¦ RRVPNL ¦ Hard copy submitted on - 08/03/24. ¦ AP 46 ¦ AP 47 ¦ RRVPNL ¦ 2 days ¦ 5,5,5,5 2 ¦ U/C LILO of 400 KV D/C Rajwest - Jodhpur Line at Newai S/S ¦ AP 45 ¦ AP 46 ¦ RRVPNL ¦ 2023-12-25 00:00:00 ¦ Hard copy submitted on - 10/01/24. ¦ AP 56 ¦ AP 57 ¦ RRVPNL ¦ 1week 3 ¦ 220 KV S/C GSS Boranada - Balotra Line ¦ AP 60 ¦ AP 61 ¦ RRVPNL ¦ 2023-11-13 00:00:00 ¦ Approved on dated 18.07.24 ¦ AP 66 ¦ AP 67 ¦ RRVPNL ¦ 2024-02-13 00:00:00 ¦ Approved on dated 18.07.24 | ok
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | 2026-05-20 | Clear locs shared by client | 51 | 13 | erection, row_hindrance, summary_status | R5: SL No. ¦ Location (G) ¦ Current Status ¦ SL No. ¦ Location(F) ¦ Current Status R27: 22 ¦ 40/2 ¦ Untouch ¦ 22 ¦ 59/0 ¦ Materials shifting wip (Jirwa Devi) | Erection Workfront_shared by SPTL Section II_29.11.2024 SL No. ¦ Location (G) ¦ Current Status ¦ SL No. ¦ Location(F) ¦ Current Status 1 ¦ 33/1 ¦ Untouch ¦ 1 ¦ 47/2 ¦ Untouch ¦ 33/8 2 ¦ 35/0 ¦ Untouch ¦ 2 ¦ 47/3 ¦ Untouch 3 ¦ 35/1 ¦ Untouch ¦ 3 ¦ 47/5 ¦ Untouch 4 ¦ 35/2 ¦ Untouch ¦ 4 ¦ 47/6 ¦ Untouch 5 ¦ 35/3 ¦ Untouch ¦ 5 ¦ 47/7 ¦ Untouch 6 ¦ 35/4 ¦ Untouch ¦ 6 ¦ 47/8 ¦ Untouch | ok
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | Master Sheet | 659 | 59 | earthing_tack, erection, foundation, project_details, row_hindrance, summary_status, survey_soil, visual_l2 | R1: SL No. ¦ Activity ¦ LOA Scope ¦ L2 Schedule Quantity ¦ Revised Scope ¦ Completed ¦ WIP ¦ Balance ¦ Route Alignemnt Details ¦ Detailed Survey details ¦ Check Survey details R2: 1 ¦ Route Alignment ¦ 126.4 ¦ 126.4 ¦ 120.29824099999993 ¦ 120.29824099999993 ¦ Approved ¦ 120.29824099999993 ¦ Approved By PGCIL ¦ 111.65962999999994 ¦ Approved By PGCIL ¦ 108.45636599999993 R3: 2 ¦ Detailed Survey ¦ 126.4 ¦ 126.4 ¦ 120.29824099999993 ¦ 120.29824099999993 ¦ Hold By PGCIL ¦ Data Sent to KPIL Engg ¦ Data Sent to KPIL Engg R4: 3 ¦ Check Survey ¦ 126.4 ¦ 126.4 ¦ 120.29824099999993 ¦ 111.65962999999994 ¦ 8.638610999999997 ¦ Submitted to PGCIL ¦ 8.638611000000001 ¦ Submitted to PGCIL ¦ 3.2032640000000003 R5: 4 ¦ Soil Investigation ¦ 20 ¦ 20 ¦ 17 ¦ 17 ¦ Data to be Sent ¦ Data to be Sent | SL No. ¦ Activity ¦ LOA Scope ¦ L2 Schedule Quantity ¦ Revised Scope ¦ Completed ¦ WIP ¦ Balance ¦ Route Alignemnt Details ¦ Detailed Survey details ¦ Check Survey details 1 ¦ Route Alignment ¦ 126.4 ¦ 126.4 ¦ 120.29824099999993 ¦ 120.29824099999993 ¦ Approved ¦ 120.29824099999993 ¦ Approved By PGCIL ¦ 111.65962999999994 ¦ Approved By PGCIL ¦ 108.45636599999993 2 ¦ Detailed Survey ¦ 126.4 ¦ 126.4 ¦ 120.29824099999993 ¦ 120.29824099999993 ¦ Hold By PGCIL ¦ Data Sent to KPIL Engg ¦ Data Sent to KPIL Engg 3 ¦ Check Survey ¦ 126.4 ¦ 126.4 ¦ 120.29824099999993 ¦ 111.65962999999994 ¦ 8.638610999999997 ¦ Submitted to PGCIL ¦ 8.638611000000001 ¦ Submitted to PGCIL ¦ 3.2032640000000003 4 ¦ Soil Investigation ¦ 20 ¦ 20 ¦ 17 ¦ 17 ¦ Data to be Sent ¦ Data to be Sent 5 ¦ Normal Foundation ¦ 316 ¦ 316 ¦ 336 ¦ 25 ¦ 311 6 ¦ Pile Foundation ¦ 4 ¦ 4 ¦ 3 ¦ 3 7 ¦ Pipe Earthing ¦ 320 ¦ 320 ¦ 339 ¦ 15 ¦ 324 | ok
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | DPR Sum. | 96 | 25 | project_details, summary_status, survey_soil, visual_l2 | R6: Sl. No. ¦ Description ¦ Unit ¦ LOA Qty ¦ Revised Qty ¦ As Per Approved L2 ¦ As Per Actual ¦ Balance ¦ Target for the month ¦ Target for the week ¦ During the week ¦ Today's progress ¦ Gang ¦ WIP ¦ Remarks R9: a ¦ Route Alignment - Main Line ¦ Kms ¦ 87.47 ¦ 87.90790000000005 ¦ 87.90790000000005 ¦ 87.90790000000005 ¦ 87.90790000000005 ¦ 87.90790000000005 R10: b ¦ Route Alignment - Loop In ¦ Kms ¦ 13.6 ¦ 8.0518 ¦ 8.0518 ¦ 8.0518 ¦ 8.0518 ¦ 8.0518 R11: c ¦ Route Alignment - Loop Out ¦ Kms ¦ 13.52 ¦ 8.013399999999999 ¦ 8.013399999999999 ¦ 8.013399999999999 ¦ 8.013399999999999 ¦ 8.013399999999999 R13: a ¦ Detailed Survey - Main Line ¦ Kms ¦ 87.47 ¦ 87.90790000000005 ¦ 87.90790000000005 ¦ 87.90790000000005 ¦ 87.90790000000005 ¦ 87.90790000000005 | CLIENT ¦ Resonia CONTRACTOR ¦ KEC INTERNATIONAL LIMITED PROJECT ¦ 400kV DC AL59 Quad Alipurduar PGCIL -Bornagar ¦ Loop In 400kV DC line at Bornagar ¦ Loop Out 400kV DC line at Bornagar LOA ¦ LOI/EPC/ NERES_XXV/KEC/01, Dated- 29th July 2025 PROJECT STATUS AS ON ¦ 2026-05-04 00:00:00 Sl. No. ¦ Description ¦ Unit ¦ LOA Qty ¦ Revised Qty ¦ As Per Approved L2 ¦ As Per Actual ¦ Balance ¦ Target for the month ¦ Target for the week ¦ During the week ¦ Today's progress ¦ Gang ¦ WIP ¦ Remarks Upto Last Month ¦ This Month ¦ Cum. Till This Month ¦ Upto Last Month ¦ This Month till date ¦ Cum. till date ¦ Week 1 (1-7) ¦ Week 2 (8-15) ¦ Week 3 (16-23) ¦ Week 4 (24-End) ¦ Week 1 (1-7) ¦ Week 2 (8-15) ¦ Week 3 (16-23) ¦ Week 4 (24-End) 1 ¦ Route Alignment | ok
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | Master Sheet | 770 | 63 | earthing_tack, erection, foundation, project_details, row_hindrance, summary_status, survey_soil, visual_l2 | R1: SL No. ¦ Activity ¦ LOA Scope ¦ L2 Schedule Quantity ¦ Revised Scope ¦ Completed ¦ WIP ¦ Balance ¦ Route Alignemnt Details ¦ Detailed Survey details ¦ Check Survey details R2: 1 ¦ Route Alignment ¦ 87.47 ¦ 87.47 ¦ 87.90790000000005 ¦ 87.90790000000005 ¦ Approved ¦ 87.90790000000005 ¦ Approved ¦ 87.90790000000005 ¦ Approved ¦ 84.60460000000002 R3: 2 ¦ Detailed Survey ¦ 87.47 ¦ 87.47 ¦ 87.90790000000005 ¦ 87.90790000000005 ¦ Hold ¦ Hold ¦ Hold ¦ 3.3033 R4: 3 ¦ Check Survey ¦ 87.47 ¦ 87.47 ¦ 87.90790000000005 ¦ 87.90790000000005 ¦ Submitted ¦ Submitted ¦ Submitted R5: 4 ¦ Soil Investigation ¦ 37 ¦ 37 ¦ Others ¦ Others ¦ Others | SL No. ¦ Activity ¦ LOA Scope ¦ L2 Schedule Quantity ¦ Revised Scope ¦ Completed ¦ WIP ¦ Balance ¦ Route Alignemnt Details ¦ Detailed Survey details ¦ Check Survey details 1 ¦ Route Alignment ¦ 87.47 ¦ 87.47 ¦ 87.90790000000005 ¦ 87.90790000000005 ¦ Approved ¦ 87.90790000000005 ¦ Approved ¦ 87.90790000000005 ¦ Approved ¦ 84.60460000000002 2 ¦ Detailed Survey ¦ 87.47 ¦ 87.47 ¦ 87.90790000000005 ¦ 87.90790000000005 ¦ Hold ¦ Hold ¦ Hold ¦ 3.3033 3 ¦ Check Survey ¦ 87.47 ¦ 87.47 ¦ 87.90790000000005 ¦ 87.90790000000005 ¦ Submitted ¦ Submitted ¦ Submitted 4 ¦ Soil Investigation ¦ 37 ¦ 37 ¦ Others ¦ Others ¦ Others 5 ¦ Normal Foundation ¦ 256 ¦ 256 ¦ 266 ¦ 124 ¦ 6 ¦ 142 ¦ Total ¦ 87.90790000000005 ¦ Total ¦ 87.90790000000005 ¦ Total ¦ 87.90790000000001 6a ¦ Pile ¦ 5 ¦ 5 ¦ 2 ¦ 1 ¦ 1 6b ¦ Pile Cap ¦ 5 ¦ 5 ¦ 2 ¦ 1 ¦ 2 | ok
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | WIP-FDN | 346 | 17 | earthing_tack, foundation, project_details, summary_status | R7: S.NO. ¦ LOC. NO. ¦ Tower Type ¦ Classification ¦ GANG NAME ¦ Man power ¦ Start Date ¦ Completion Date ¦ Section Incharge ¦ Engineer/Supervisor ¦ Foundation Status ¦ Start Date ¦ End Date ¦ GANG NAME ¦ Earthing Status ¦ CTQ R8: 1 ¦ 69/2 ¦ A(00-02)+06 ¦ SANDY PS ¦ Prabir Bala ¦ 13 ¦ 2025-10-06 00:00:00 ¦ 2025-10-18 00:00:00 ¦ Anjan Chakravarty ¦ Subrata Panigrahi ¦ Location Completed. ¦ 2026-01-05 00:00:00 ¦ 2026-01-05 00:00:00 ¦ PRABIR BALA ¦ Completed ¦ Completed R9: 2 ¦ 65/3 ¦ A(00-02)+00 ¦ SANDY PS ¦ Bipul Debnath ¦ 14 ¦ 2025-10-07 00:00:00 ¦ 2025-10-18 00:00:00 ¦ Anjan Chakravarty ¦ Asadul Laskar ¦ Location Completed. ¦ 2025-12-21 00:00:00 ¦ 2025-12-21 00:00:00 ¦ Bipul Debnath ¦ Completed ¦ Completed R10: 3 ¦ 131/2 ¦ A(00-02)+06 ¦ SANDY PS ¦ Mohar Ali ¦ 12 ¦ 2025-10-15 00:00:00 ¦ 2025-11-09 00:00:00 ¦ Virendra Kumar ¦ Debashis Konar ¦ Location Completed. ¦ 2026-02-07 00:00:00 ¦ 2026-02-07 00:00:00 ¦ Mohar Ali ¦ Completed ¦ Completed R11: 4 ¦ 58/1 ¦ A(00-02)+09 ¦ SANDY PS ¦ Bipul Debnath ¦ 16 ¦ 2025-10-21 00:00:00 ¦ 2025-11-10 00:00:00 ¦ Anjan Chakravarty ¦ Lalit Saikia ¦ Location Completed. ¦ 2025-12-24 00:00:00 ¦ 2025-12-24 00:00:00 ¦ Bipul Debnath ¦ Completed ¦ Completed | KEC INTERNATIONAL LIMITED WORK IN PROGRESS LOCATION DETAILS - FOUNDATION & EARTHING 400kV DC AL59 Quad Alipurduar PGCIL -Bornagar Status as on : ¦ 2026-05-04 00:00:00 FOUNDATION ¦ Earthing S.NO. ¦ LOC. NO. ¦ Tower Type ¦ Classification ¦ GANG NAME ¦ Man power ¦ Start Date ¦ Completion Date ¦ Section Incharge ¦ Engineer/Supervisor ¦ Foundation Status ¦ Start Date ¦ End Date ¦ GANG NAME ¦ Earthing Status ¦ CTQ 1 ¦ 69/2 ¦ A(00-02)+06 ¦ SANDY PS ¦ Prabir Bala ¦ 13 ¦ 2025-10-06 00:00:00 ¦ 2025-10-18 00:00:00 ¦ Anjan Chakravarty ¦ Subrata Panigrahi ¦ Location Completed. ¦ 2026-01-05 00:00:00 ¦ 2026-01-05 00:00:00 ¦ PRABIR BALA ¦ Completed ¦ Completed 2 ¦ 65/3 ¦ A(00-02)+00 ¦ SANDY PS ¦ Bipul Debnath ¦ 14 ¦ 2025-10-07 00:00:00 ¦ 2025-10-18 00:00:00 ¦ Anjan Chakravarty ¦ Asadul Laskar ¦ Location Completed. ¦ 2025-12-21 00:00:00 ¦ 2025-12-21 00:00:00 ¦ Bipul Debnath ¦ Completed ¦ Completed | ok
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | Gang Movement | 310 | 30 | foundation, project_details, summary_status | R2: S.NO. ¦ LOC. NO. ¦ Tower Type ¦ Type of FDN ¦ GANG NAME ¦ Start Date ¦ Expected Completion Date ¦ Progress Details ¦ Next Location ¦ Gang Name ¦ Monthly Plan R10: 8 ¦ AP-109/0 ¦ 2026-05-04 00:00:00 ¦ Tower Foundation ¦ 73/0, Vataman Reach R11: 9 ¦ AP-11A/0 ¦ 2026-05-04 00:00:00 ¦ A.G.Foundation ¦ 11/3, 11/4, 11/5 | 2026-05-04 00:00:00 S.NO. ¦ LOC. NO. ¦ Tower Type ¦ Type of FDN ¦ GANG NAME ¦ Start Date ¦ Expected Completion Date ¦ Progress Details ¦ Next Location ¦ Gang Name ¦ Monthly Plan 1 ¦ 81/1 ¦ 2026-05-04 00:00:00 ¦ Thota Ashok ¦ 12/5, 12/6, 13/6 2 ¦ 10/9 ¦ 2026-05-04 00:00:00 ¦ Ambani Insfrastructure ¦ 82/1, 80/2 3 ¦ 79/2 ¦ 2026-05-04 00:00:00 ¦ Civil Transmission & construction ¦ 80/3, 82/0, 80/4 4 ¦ AP-82/0 ¦ 2026-05-04 00:00:00 ¦ Sekh sahalam ¦ 105/0, 106/0, 109/0 5 ¦ 80/1 ¦ 2026-05-04 00:00:00 ¦ Harjeet Construction ¦ AP-69/0, AP-70/0 6 ¦ AP-103/0 ¦ 2026-05-04 00:00:00 ¦ Guru Kripa Infra & Engineering ¦ 103/0, 11A/0, 11A/1 | ok
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | Support Required | 15 | 5 |  | R3: Sl No ¦ Description ¦ Remarks | Support Required Sl No ¦ Description ¦ Remarks | ok
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | WIP-ERC | 347 | 14 | earthing_tack, erection, foundation, project_details, summary_status | R7: S.NO. ¦ LOC. NO. ¦ Tower Type ¦ Type of FDN ¦ GANG NAME ¦ Man power ¦ Start Date ¦ Completion Date ¦ Section Incharge ¦ Engineer/Supervisor ¦ REMARKS ¦ Tower Weight R19: 12 ¦ 91/8 ¦ A(00-02)+03 ¦ SANDY WET & Boulder Soiling ¦ Aahana Construction ¦ 21 ¦ 2026-03-17 00:00:00 ¦ 2026-03-25 00:00:00 ¦ Virendra Kumar ¦ Debashis Konar ¦ Location Completed ¦ 18.359862 ¦ DA+3 R20: 13 ¦ 81/0 ¦ C(15-30)+09 ¦ SANDY PS & Boulder Soiling ¦ Ratul Ali ¦ 23 ¦ 2026-03-22 00:00:00 ¦ 2026-04-09 00:00:00 ¦ Anjan Chakravarty ¦ Jay Sankar Jha ¦ Location Completed ¦ 35.667293 ¦ DC2+9 R21: 14 ¦ 88/0 ¦ B(00-07)+00 ¦ SANDY PS with Boulder Soiling ¦ Aahana Construction ¦ 25 ¦ 2026-03-25 00:00:00 ¦ 2026-04-11 00:00:00 ¦ Virendra Kumar ¦ Debashis Konar ¦ Location Completed ¦ 24.488255 ¦ DB1+0 R28: 21 ¦ 89/0 ¦ C(15-30)+00 ¦ SANDY WET with Boulder Soiling ¦ Aahana Construction ¦ 25 ¦ 2026-04-11 00:00:00 ¦ Virendra Kumar ¦ Debashis Konar ¦ Ground Assembly u/p. ¦ 27.433928999999996 ¦ DC2+0 | KEC INTERNATIONAL LIMITED WORK IN PROGRESS LOCATION DETAILS - ERECTION & TACK WELDING 400kV DC AL59 Quad Alipurduar PGCIL -Bornagar Status as on ¦ 2026-05-04 00:00:00 ERECTION S.NO. ¦ LOC. NO. ¦ Tower Type ¦ Type of FDN ¦ GANG NAME ¦ Man power ¦ Start Date ¦ Completion Date ¦ Section Incharge ¦ Engineer/Supervisor ¦ REMARKS ¦ Tower Weight 1 ¦ 58/1 ¦ A(00-02)+09 ¦ SANDY PS ¦ Adhi ¦ 2025-12-27 00:00:00 ¦ 2026-01-10 00:00:00 ¦ Anjan Chakravarty ¦ Location Completed ¦ 22.107179999999993 ¦ DA+9 2 ¦ 71/1 ¦ A(00-02)+03 ¦ SANDY WET ¦ Ratul Ali ¦ 23 ¦ 2025-12-28 00:00:00 ¦ 2026-01-23 00:00:00 ¦ Anjan Chakravarty ¦ Location Completed ¦ 18.359862 ¦ DA+3 | ok
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | Line Details | 558 | 30 | earthing_tack, erection, foundation, statutory_crossing, stringing, summary_status, visual_l2 | R6: Sl No ¦ Tower No ¦ Type Of Tower ¦ Span ¦ Section Length ¦ Foundation ¦ Earthing ¦ ERECTION ¦ Stringing ¦ Village Name ¦ Division ¦ Crossing Details ¦ 11KV ¦ 33KV ¦ 66KV ¦ 132KV ¦ 220KV ¦ 400KV ¦ 500kv ¦ NH R7: Existing Tapping Tower ¦ C(15-30)+06 ¦ - ¦ - ¦ - ¦ Status R8: 1 ¦ 1/0 ¦ D(45-60)+00 ¦ 141.1 ¦ - ¦ - ¦ - ¦ FDN ¦ 124 R12: 5 ¦ 4/0 ¦ D(30-52)+35 ¦ 223.9 ¦ - ¦ - ¦ - ¦ 400kV ¦ 1 ¦ 1 ¦ Erec WIP ¦ 5 R49: 42 ¦ 25/1 ¦ A(00-02)+06 ¦ 400.2 ¦ FDN ¦ P ¦ - ¦ SANDY WET | KEC INTERNATIONAL LIMITED 400kV DC AL59 Quad Alipurduar PGCIL -Bornagar LOI/EPC/ NERES_XXV/KEC/01, Dated- 29th July 2025 Visual Chart Updatation Details Sheet. TB-608 PROJECT ¦ Major Crossing Details Sl No ¦ Tower No ¦ Type Of Tower ¦ Span ¦ Section Length ¦ Foundation ¦ Earthing ¦ ERECTION ¦ Stringing ¦ Village Name ¦ Division ¦ Crossing Details ¦ 11KV ¦ 33KV ¦ 66KV ¦ 132KV ¦ 220KV ¦ 400KV ¦ 500kv ¦ NH Existing Tapping Tower ¦ C(15-30)+06 ¦ - ¦ - ¦ - ¦ Status 1 ¦ 1/0 ¦ D(45-60)+00 ¦ 141.1 ¦ - ¦ - ¦ - ¦ FDN ¦ 124 | ok
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | Visual_Chart | 447 | 23 | earthing_tack, erection, foundation, stringing, summary_status, visual_l2 | R3: 400kV DC AL59 Quad Alipurduar PGCIL -Bornagar ¦ LEGEND ¦ STATUS R4: Progress Status as on dated ¦ 2026-05-04 00:00:00 ¦ Paying Out ¦ Final Sag ¦ FDN ¦ 124 R5: Sr. No. ¦ Description ¦ UOM ¦ Revised Scope ¦ Completed ¦ Balance ¦ WIP ¦ Erec WIP ¦ STNG WIP ¦ Erec Completed ¦ TW Completed ¦ WIP ¦ 6 R6: 1 ¦ Foundation ¦ Nos ¦ 268 ¦ 124 ¦ 144 ¦ 6 ¦ ERE ¦ 21 R7: 2 ¦ Earthing ¦ Nos ¦ 268 ¦ 116 ¦ 152 ¦ FDN WIP ¦ Fdn Completed ¦ P ¦ 116 | 400kV DC AL59 Quad Alipurduar PGCIL -Bornagar VISUAL CHART ¦ 2026-05-04 00:00:00 400kV DC AL59 Quad Alipurduar PGCIL -Bornagar ¦ LEGEND ¦ STATUS Progress Status as on dated ¦ 2026-05-04 00:00:00 ¦ Paying Out ¦ Final Sag ¦ FDN ¦ 124 Sr. No. ¦ Description ¦ UOM ¦ Revised Scope ¦ Completed ¦ Balance ¦ WIP ¦ Erec WIP ¦ STNG WIP ¦ Erec Completed ¦ TW Completed ¦ WIP ¦ 6 1 ¦ Foundation ¦ Nos ¦ 268 ¦ 124 ¦ 144 ¦ 6 ¦ ERE ¦ 21 2 ¦ Earthing ¦ Nos ¦ 268 ¦ 116 ¦ 152 ¦ FDN WIP ¦ Fdn Completed ¦ P ¦ 116 3 ¦ Tower Erection ¦ Nos ¦ 268 ¦ 22 ¦ 246 ¦ 5 ¦ Earthing Completed ¦ Erec WIP ¦ 5 | ok
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | Foundation Activity | 720 | 30 | foundation, supply | R1: Sl No ¦ Loc No ¦ Type of Tower ¦ PIT ¦ Classification ¦ S/C Name ¦ Manpower ¦ Section Incharge ¦ Engineer/ Supervisor ¦ Location Start Date ¦ Pit Marking ¦ Excavation ¦ Stub Setting ¦ PCC ¦ Steel Binding ¦ FS Concreting ¦ Pyramid Concreting ¦ Chimney Concreting ¦ Backfilling ¦ Location End Date R58: 12 ¦ 90/0 ¦ D(30-45)+00 ¦ SANDY WET with Boulder Soiling ¦ Mohar Ali ¦ 12 ¦ Virendra Kumar ¦ Debashis Konar ¦ 2025-11-09 00:00:00 ¦ 2025-11-22 00:00:00 ¦ Location Completed. R78: 16 ¦ 88/0 ¦ B(00-07)+00 ¦ SANDY PS with Boulder Soiling ¦ Mohar Ali ¦ 15 ¦ Virendra Kumar ¦ Debashis Konar ¦ 2025-11-13 00:00:00 ¦ 2025-11-28 00:00:00 ¦ Location Completed. | Sl No ¦ Loc No ¦ Type of Tower ¦ PIT ¦ Classification ¦ S/C Name ¦ Manpower ¦ Section Incharge ¦ Engineer/ Supervisor ¦ Location Start Date ¦ Pit Marking ¦ Excavation ¦ Stub Setting ¦ PCC ¦ Steel Binding ¦ FS Concreting ¦ Pyramid Concreting ¦ Chimney Concreting ¦ Backfilling ¦ Location End Date Start ¦ End ¦ Start ¦ End ¦ Start ¦ End ¦ Start ¦ End ¦ Start ¦ End ¦ Start ¦ End ¦ Start ¦ End ¦ Start ¦ End ¦ Start ¦ End 1 ¦ 69/2 ¦ A(00-02)+06 ¦ SANDY PS ¦ Prabir Bala ¦ 13 ¦ Anjan Chakravarty ¦ Subrata Panigrahi ¦ 2025-10-06 00:00:00 ¦ 2025-10-18 00:00:00 ¦ Location Completed. A(00-02)+06 ¦ Pit-1 ¦ 2025-10-06 00:00:00 ¦ 2025-10-06 00:00:00 ¦ 2025-10-07 00:00:00 ¦ 2025-10-09 00:00:00 ¦ 2025-10-11 00:00:00 ¦ 2025-10-11 00:00:00 ¦ 2025-10-11 00:00:00 ¦ 2025-10-11 00:00:00 ¦ 2025-10-11 00:00:00 ¦ 2025-10-11 00:00:00 ¦ 2025-10-11 00:00:00 ¦ 2025-10-11 00:00:00 ¦ 2025-10-14 00:00:00 ¦ 2025-10-14 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-17 00:00:00 ¦ 2025-10-18 00:00:00 A(00-02)+06 ¦ Pit-2 ¦ 2025-10-06 00:00:00 ¦ 2025-10-06 00:00:00 ¦ 2025-10-13 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-15 00:00:00 ¦ 2025-10-17 00:00:00 ¦ 2025-10-18 00:00:00 A(00-02)+06 ¦ Pit-3 ¦ 2025-10-06 00:00:00 ¦ 2025-10-06 00:00:00 ¦ 2025-09-23 00:00:00 ¦ 2025-09-25 00:00:00 ¦ 2025-09-29 00:00:00 ¦ 2025-09-29 00:00:00 ¦ 2025-09-29 00:00:00 ¦ 2025-09-29 00:00:00 ¦ 2025-09-29 00:00:00 ¦ 2025-09-29 00:00:00 ¦ 2025-09-29 00:00:00 ¦ 2025-09-29 00:00:00 ¦ 2025-09-29 00:00:00 ¦ 2025-09-29 00:00:00 ¦ 2025-10-11 00:00:00 ¦ 2025-10-11 00:00:00 ¦ 2025-10-14 00:00:00 ¦ 2025-10-15 00:00:00 A(00-02)+06 ¦ Pit-4 ¦ 2025-10-06 00:00:00 ¦ 2025-10-06 00:00:00 ¦ 2025-10-16 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-18 00:00:00 ¦ 2025-10-20 00:00:00 ¦ 2025-10-21 00:00:00 2 ¦ 65/3 ¦ A(00-02)+00 ¦ SANDY PS ¦ Bipul Debnath ¦ 14 ¦ Anjan Chakravarty ¦ Asadul Laskar ¦ 2025-10-07 00:00:00 ¦ 2025-10-18 00:00:00 ¦ Location Completed. | ok
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | Supply | 89 | 7 | supply | R5: Sr.No. ¦ Description of material ¦ unit ¦ Received Qty. ¦ Issued Qty. ¦ Balance Qty. ¦ Remarks R9: 1 ¦ STUB FOR DA TYPE NORMAL ¦ SET ¦ 120 ¦ 69 ¦ 51 R10: 2 ¦ STUB FOR DA 1 M RC ¦ SET ¦ 13 ¦ 7 ¦ 6 R11: 3 ¦ STUB FOR DA 2 M RC ¦ SET ¦ 4 ¦ 4 R12: 4 ¦ STUB FOR DB TYPE NORMAL ¦ SET ¦ 15 ¦ 6 ¦ 9 | KEC International Limited 400KV D/C ALIPURDUAR - BORNAGAR T/L (TB-608) RAKHALDUBI HAPACHARA, BONGAIGAON Stock Statement Sr.No. ¦ Description of material ¦ unit ¦ Received Qty. ¦ Issued Qty. ¦ Balance Qty. ¦ Remarks A ¦ B ¦ C ¦ D ¦ E ¦ F= D-E 3 ¦ STUB 1 ¦ STUB FOR DA TYPE NORMAL ¦ SET ¦ 120 ¦ 69 ¦ 51 | ok
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | 2026-04-05 | Sheet2 | 31 | 8 |  |  | DA+0 ¦ 16.512828 ¦ 0.607242 ¦ 17.12007 DA+3 ¦ 17.723764 ¦ 0.6360979999999999 ¦ 18.359862 DA+6 ¦ 20.088851999999996 ¦ 0.7116939999999999 ¦ 20.800545999999997 DA+9 ¦ 21.364541999999993 ¦ 0.7426379999999999 ¦ 22.107179999999993 DB1+0 ¦ 23.417116 ¦ 1.071139 ¦ 24.488255 DB1+3 ¦ 24.806958 ¦ 1.1363910000000002 ¦ 25.943349 DB1+6 ¦ 28.45777 ¦ 1.226491 ¦ 29.684261 DB1+9 ¦ 30.36126 ¦ 1.2844550000000001 ¦ 31.645715000000003 | ok

## DPR Config Coverage
project_code | dpr_file | open_status | status_configured | status_found | status_missing | erection_configured | erection_found | erection_missing | stringing_configured | stringing_found | stringing_missing | stretch_configured | stretch_found | stretch_missing | daily_stringing_configured | daily_stringing_found | daily_stringing_missing | manpower_expected | status_template_check | stretch_template_check
TB 605 | TB 605 - DPR - 2026-05-20.xlsx | ok | TB-605 | TB-605 |  | Erection -Jammu; Erection -SK; Erection-Punjab | Erection -Jammu; Erection -SK; Erection-Punjab | [10 empty] | Unknown | Yes
TA 414 | TA 414 - DPR - 2026-05-21.xlsx | repaired_defined_names (ValueError) | VNTL - KEC | VNTL - KEC |  | Erection Compiled | Erection Compiled |  | Stringing Compiled | Stringing Compiled |  |  |  |  | Stringing Compiled | Stringing Compiled |  | Unknown | Yes
TA 504 | TA 504 - DPR - 2026-05-21.xlsx | repaired_defined_names (ValueError) | DPR_TA-504 | DPR_TA-504 |  | Erection compiled | Erection compiled |  | Stringing Compiled | Stringing Compiled |  | Stringing | Stringing Compiled |  | Stringing | Stringing Compiled |  | Yes | Yes | Yes
TA 506 | TA 506 - DPR - 2026-05-21.xlsx | repaired_defined_names (ValueError) | DPR_TA-506 | DPR_TA-506 |  | Erection compiled | Erection compiled |  | Stringing Compiled | Stringing |  | Stringing | Stringing |  | Stringing | Stringing |  | Yes | Yes | Yes
TB 507 | TB 507 [MAIN] - DPR - 2026-05-20.xlsx | ok | 400kV Summery; 765kV Summery | 400kV Summery | 765kV Summery | Erection Compiled | Erection Compiled |  | Stringing Compiled | Stringing Compiled |  | Final Check In And Tack Welding | Final Check In And Tack Welding |  | Stringing Compiled | Stringing Compiled |  | No | Yes | Yes
TA 512 | TA 512 - DPR - 2026-05-20.xlsx | ok | Summary E | Summary E |  | Erection Compiled | Erection Compiled |  |  |  |  | Tack Welding | Tack Welding |  |  |  |  | Unknown | Yes | Yes
TA 413 | TA 413 - DPR - 2026-05-20.xlsx | repaired_defined_names (ValueError) | TA413_PBNTL | TA413_PBNTL |  | Erection | Erection |  | Stringing | Stringing |  | Stretch readiness | Stretch readiness |  | Stringing | Stringing |  | No | Yes | Yes
TA 419 | TA 419 - DPR - 2026-05-20.xlsx | repaired_defined_names (ValueError) | DPR_TA419 | DPR_TA419 |  | ERECTION COMPILED | ERECTION COMPILED |  |  |  |  | Stringing Stretch Readiness | Stringing Stretch Readiness |  |  |  |  | Unknown | Yes | Yes
TA 418 | TA 418 - DPR - 2026-05-21.xlsx | ok | MASTER SHEET | MASTER SHEET |  | Erection Compiled | Erection Compiled |  | Stringing Compiled | Stringing Compiled |  | Stringing Compiled | Stringing Compiled |  | Stringing Compiled | Stringing Compiled |  | Yes | Yes | Yes
TA 421 | TA 421 - DPR - 2026-05-20.xlsx | ok | Master Sheet | Master Sheet |  | Erection Compiled | Erection Compiled |  | Stringing Compiled | Stringing Compiled |  | Tack Welding | Tack Welding |  | Stringing Compiled | Stringing Compiled |  | Yes | Yes | Yes
TA 416 | TA 416 - DPR - 2026-05-17.xlsx | ok | MASTER SHEET | MASTER SHEET |  | Erection Compiled | Erection Compiled |  | Stringing compiled | Stringing compiled |  |  |  |  | Stringing compiled | Stringing compiled |  | No | Yes
TA 505 | TA 505 - DPR - 2026-05-19.xlsx | ok | DPR-Summary | DPR-Summary |  | Erection Compiled | Erection Compiled |  | Stringing Compiled | Stringing Compiled |  | Stringing Compiled | Stringing Compiled |  | Stringing Compiled | Stringing Compiled |  | Yes | Yes | Yes
TB 408 | TB 408 - DPR - 2026-05-11.xlsx | repaired_defined_names (ValueError) | Progress Summary |  | Progress Summary | Erection Compiled | Erection Compiled |  | Stringing | Stringing Compiled |  | Tackwelding |  | Tackwelding | Stringing | Stringing Compiled |  | No | Yes | Yes
TB 401 | TB 401 - DPR - 2025-12-25.xlsx | ok | Progress | Progress |  | Erection Compiled | Erection Compiled |  | Stringing - PKG-G | Stringing - PKG-G |  | Tack Welding - PKG-G | Tack Welding - PKG-G |  | Stringing - PKG-G | Stringing - PKG-G |  | Unknown | Yes | Yes
TA 325 | TA 325 - DPR - 2026-01-19.xlsx | ok | 765KV TA 325 ANTL | 765KV TA 325 ANTL |  | Erection-Compiled | Erection-Compiled |  | Stringing Compiled | Stringing Compiled |  |  |  |  | Stringing Compiled | Stringing Compiled |  | Unknown | Yes
TA 509 | TA 509 - DPR - 2026-05-18.xlsx | ok | SUMMARY | SUMMARY |  | ERECTION | ERECTION | [10 empty] | Unknown | Yes
TA 601 | TA 601 - DPR - 2026-05-20.xlsx | ok | Master Sheet | Master Sheet |  | Erection Compiled | Erection Compiled |  | Stringing Compiled | Stringing Compiled |  | STRG Stretch | STRG Stretch |  | Stringing Compiled | Stringing Compiled |  | Unknown | Yes | Yes
TB 501 | TB 501 - DPR - 2026-05-20.xlsx | ok | Summary | Summary |  | Progress-132kV; Progress-220kV | Progress-132kV; Progress-220kV |  | Stringing-132KV; Stringing-220kV | Stringing-132KV; Stringing-220kV |  |  |  |  | Stringing-132KV; Stringing-220kV | Stringing-132KV; Stringing-220kV |  | No | Yes
TA 310 | TA 310 - DPR - 2026-01-12.xlsx | ok | NKTL DPR | NKTL DPR | [13 empty] | Unknown | Yes
TA 513 | TA 513 - DPR - 2026-05-19.xlsx | ok | Summary | Summary |  | Ere S-P ; Ere S-F | Ere S-P; Ere S-F | [10 empty] | Unknown | Yes
TA 602 | TA 602 - DPR - 2026-05-18.xlsx | ok | DPR-KEC | DPR-KEC |  | Erection | Erection | [11 empty] | Yes
TB 608 | TB 608 - DPR - 2026-04-05.xlsm | ok | DPR Sum. | DPR Sum. |  | WIP-ERC | WIP-ERC | [11 empty] | Yes
TA 510 | TA 510 - DPR - 2026-05-20.xlsx | repaired_defined_names (ValueError) | AOTL - KEC | AOTL - KEC |  | Erection Compiled | Erection Compiled | [11 empty] | Yes
TA 515 | TA 515 - DPR - 2026-05-11.xlsx | ok | DPR | DPR |  | Erection Compiled | Erection Compiled | [11 empty] | Yes

## Existing Outputs
parquet | rows | column_count | columns | status
Parquets\Erection\MicroPlanIndex.parquet | 19 | 7 | file_path, project_name, project_key, rows_cleaned, status, error, plan_month | ok
Parquets\Erection\MicroPlanResponsibilities.parquet | 1950 | 17 | project_key, project_name, plan_month, entity_type, entity_name, location_no, revenue_planned, revenue_realised, tower_weight, tower_type, manpower, power_tools_issued, material_feeding, starting_date, completion_date, tack_welding, final_checking | ok
Parquets\Erection\ProdDailyExpandedSingles.parquet | 38801 | 14 | Work Date, Start Date, Complete Date, Gang name, Tower Weight, Tower Type, Productivity, Project Code, Line Name, Project Name, Project Display, Project Scope Key, Location No., Status | ok
Parquets\Erection\ProjectBaselines.parquet | 12 | 2 | project_name, baseline_mt_per_day | ok
Parquets\Erection\ProjectBaselinesMonthly.parquet | 183 | 3 | project_name, month, baseline_mt_per_day | ok
Parquets\Erection\ProjectDetails.parquet | 12 | 13 | project_code, project_name, client_name, noa_start, loa_end, project_mgr, regional_mgr, planning_eng, pch, section_inch, supervisor, _source_file, Project Name | ok
Parquets\Erection\RawData.parquet | 5400 | 17 | Start Date, Complete Date, Gang name, Tower Weight, Tower Type, Productivity, Project Code, Line Name, Project Name, Project Display, Project Scope Key, Source File, Source Sheet, Location No., Tower Tightening Raw, Tower Tightening, Status | ok
Parquets\Foundation\Coverage.parquet | 21 | 18 | project_code, project_display, status, reason_code, reason, source_used, snapshot_limited, workbook, configured_sheet, resolved_sheet, detail_rows, detail_completions, snapshot_rows, first_event_date, last_event_date, first_report_date, last_report_date, available_sheets | ok
Parquets\Foundation\Diagnostics.parquet | 24 | 16 | Workbook, Project, Sheet, ConfiguredSheet, LineName, LineNameSource, Rows, DetailRows, Completions, ParserMode, FallbackNote, Status, Reason, TemplateSheet, TemplateApplied, TemplateChanges | ok
Parquets\Foundation\FoundationCompletions.parquet | 5110 | 17 | project_code, project_display, project_scope_key, line_name, line_name_source, report_date, event_date, period_week_start, period_month, source_file, source_sheet, configured_sheet, source_type, quality_flag, location_no, event_value, cumulative_foundation | ok
Parquets\Foundation\FoundationRaw.parquet | 5631 | 16 | project_code, project_display, project_scope_key, line_name, line_name_source, report_date, event_date, source_file, source_sheet, configured_sheet, source_type, quality_flag, location_no, status_text, cumulative_foundation, fallback_note | ok
Parquets\Foundation\Issues.parquet | 4 | 8 | Workbook, Project, Sheet, ConfiguredSheet, LineName, LineNameSource, Issue, Reason | ok
Parquets\ProgressStatus\Coverage.parquet | 22 | 13 | project_code, project_display, status, reason_code, reason, workbook, configured_sheet, resolved_sheet, rows, filename_date, internal_date, date_quality, available_sheets | ok
Parquets\ProgressStatus\Diagnostics.parquet | 20 | 18 | Workbook, Project, Sheet, ConfiguredSheet, LineName, LineNameSource, TemplateSheet, TemplateApplied, TemplateChanges, FallbackNote, SectionsDetected, HeadersDetected, Rows, FilenameDate, InternalDate, DateQuality, Status, Reason | ok
Parquets\ProgressStatus\Issues.parquet | 2 | 8 | Workbook, Project, Sheet, ConfiguredSheet, LineName, LineNameSource, Issue, Reason | ok
Parquets\ProgressStatus\RawData.parquet | 249 | 27 | project_code, project_display, project_scope_key, line_name, line_name_source, section_label, report_date, source_file, source_sheet, configured_sheet, template_sheet, stringing_resolution_policy, header_row_number, source_row_number, activity_raw, activity_norm, quantity_loa, quantity_estimated_or_total, quantity_primary, cumulative_last_month, plan_for_month, progress_for_month, today_progress, cumulative_progress, balance_progress, gangs_working, remarks | ok
Parquets\StretchReadiness\Coverage.parquet | 31 | 11 | project_code, project_display, category, status, reason_code, reason, workbook, configured_sheet, resolved_sheet, rows, available_sheets | ok
Parquets\StretchReadiness\Diagnostics.parquet | 24 | 16 | Workbook, Project, Category, Sheet, ConfiguredSheet, LineName, LineNameSource, TemplateSheet, TemplateApplied, TemplateChanges, FallbackNote, SectionsDetected, HeadersDetected, Rows, Status, Reason | ok
Parquets\StretchReadiness\Issues.parquet | 5 | 9 | Workbook, Project, Category, Sheet, ConfiguredSheet, LineName, LineNameSource, Issue, Reason | ok
Parquets\StretchReadiness\ManpowerAudit.parquet | 15 | 19 | project_code, project_display, project_scope_key, line_name, line_name_source, source_file, source_sheet, configured_sheet, header_row_number, manpower_fields, readiness_fields, readiness_column_present, signal_type, non_empty_count, sample_values, expected_manpower, expected_match, status, reason | ok
Parquets\StretchReadiness\RawData.parquet | 1170 | 35 | project_code, project_display, project_scope_key, line_name, line_name_source, section_label, source_file, source_sheet, configured_sheet, template_sheet, report_date, header_row_number, source_row_number, stretch_identifier, from_ap, to_ap, length_m_raw, length_km, readiness_raw, final_check_raw, tack_welding_raw, balance_towers, readiness_state, remarks, readiness_source, source_tag, location_nos_raw, location_parse_status, location_parse_issue, required_location_count, matched_location_count, unmatched_location_count, required_locations, matched_locations, unmatched_locations | ok
Parquets\StretchReadiness\Summary.parquet | 10 | 19 | project_code, project_display, project_scope_key, line_name, line_name_source, report_date, source_files, source_sheets, total_count, ready_count, partial_count, not_ready_count, unknown_count, balance_count, total_km, ready_km, balance_km, readiness_pct, basis | ok
Parquets\Stringing\MicroPlanIndex.parquet | 19 | 7 | file_path, project_name, project_key, rows_cleaned, status, error, plan_month | ok
Parquets\Stringing\MicroPlanResponsibilities.parquet | 63 | 17 | project_key, project_name, plan_month, entity_type, entity_name, location_no, revenue_planned, revenue_realised, tower_weight, tower_type, manpower, power_tools_issued, material_feeding, starting_date, completion_date, tack_welding, final_checking | ok
Parquets\Stringing\StringingCompiled.parquet | 993 | 64 | S.no, Sec, from_ap, to_ap, length_m, unnamed_col_6, method, unnamed_col_8, Insulator Hoisting, po_start_date, po_completion_date, fs_starting_date, fs_complete_date, unnamed_col_14, Jumpering, Spacering, Clipping, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet, method_inferred, method_inference_reason, erection_locations_for_method, number_of_tse, s no, sec_1, location nos, section_readiness, insulator hoisting_1, po | ok
Parquets\Stringing\StringingCoverage.parquet | 24 | 15 | project_code, project_display, status, reason_code, reason, workbook, configured_sheet, resolved_sheet, available_sheets, compiled_rows, daily_rows, fallback_used, template_fallback_used, method_inference_rows, assumption_notes | ok
Parquets\Stringing\StringingDaily.parquet | 4011 | 18 | project, gang_name, date, month, from_ap, to_ap, method, method_inferred, method_inference_reason, section_readiness, po_id, fs_start_date, fs_complete_date, status, length_km, po_km, daily_km, row_id | ok
Parquets\StringingSummary\Coverage.parquet | 84 | 11 | project_code, project_display, project_scope_key, category, status, reason_code, reason, workbook, configured_sheet, resolved_sheet, rows | ok
Parquets\StringingSummary\Diagnostics.parquet | 7 | 5 | component, status, rows, distinct_report_dates, distinct_months | ok
Parquets\StringingSummary\Issues.parquet | 0 | 4 | severity, component, code, message | ok
Parquets\StringingSummary\ManpowerProductivityFact.parquet | 4011 | 22 | project_code, project_display, project_scope_key, line_name, date, month, gang_name, from_ap, to_ap, span_key, method, section_readiness, daily_km, po_km, manpower_gang_strength, manpower_fitters, manpower_signal_type, manpower_status, expected_manpower, expected_match, availability, availability_reason | ok
Parquets\StringingSummary\StatusActivityFact.parquet | 242 | 25 | project_code, project_display, project_scope_key, line_name, report_date, month, section_label, activity_raw, activity_norm, activity_group, core_activity, quantity_primary, cumulative_last_month, plan_for_month, progress_for_month, today_progress, cumulative_progress, balance_progress, gangs_working, remarks, source_file, source_sheet, configured_sheet, template_sheet, stringing_resolution_policy | ok
Parquets\StringingSummary\StatusSnapshotOverall.parquet | 2 | 15 | month, projects_total, activities_total, quantity_primary_sum, cumulative_last_month_sum, plan_for_month_sum, progress_for_month_sum, today_progress_sum, cumulative_progress_sum, balance_progress_sum, foundation_cumulative_progress, tower_erection_cumulative_progress, stringing_cumulative_progress, opgw_stringing_cumulative_progress, completion_pct | ok
Parquets\StringingSummary\StatusSnapshotProject.parquet | 21 | 19 | project_code, project_display, project_scope_key, line_name, month, report_date_max, activities_total, quantity_primary_sum, cumulative_last_month_sum, plan_for_month_sum, progress_for_month_sum, today_progress_sum, cumulative_progress_sum, balance_progress_sum, completion_pct, foundation_cumulative_progress, tower_erection_cumulative_progress, stringing_cumulative_progress, opgw_stringing_cumulative_progress | ok
Parquets\StringingSummary\StretchSectionFact.parquet | 1170 | 22 | project_code, project_display, project_scope_key, line_name, report_date, month, section_label, section_id, from_ap, to_ap, length_km, readiness_state, is_ready, is_partial, is_not_ready, is_unknown, balance_towers, remarks, source_file, source_sheet, configured_sheet, template_sheet | ok