## ES Delay Summary
ES Delay Summary
Scope Type | Scope Name | Method Split | Spans Considered | Spans With Computable Lag | Lag Coverage % | Average Lag Days | Median Lag Days | % Lag >60 Days | Negative Lag Excluded | Fallback Rows | Fallback %
OVERALL | All Projects | All | 260 | 206 | 79.2 | 150.7 | 146 | 81.3 | 3 | 212 | 81.5
OVERALL | All Projects | TSE | 21 | 21 | 100 | 110.6 | 107 | 68.4 | 2 | 12 | 57.1
OVERALL | All Projects | Others | 28 | 26 | 92.9 | 113.8 | 91 | 80 | 1 | 19 | 67.9
PROJECT | TA 413 | All | 23 | 23 | 100 | 185.3 | 204 | 95.7 | 0 | 23 | 100
PROJECT | TA 414 | All | 26 | 26 | 100 | 67.7 | 64 | 54.2 | 2 | 13 | 50
PROJECT | TA 416 | All | 16 | 16 | 100 | 175.9 | 187 | 100 | 0 | 1 | 6.2
PROJECT | TA 418 | All | 21 | 0 | 0 |  |  |  | 0 | 21 | 100
PROJECT | TA 419 | All | 2 | 2 | 100 | 316 | 316 | 100 | 0 | 2 | 100
PROJECT | TA 421 | All | 13 | 13 | 100 | 217.5 | 182 | 100 | 0 | 13 | 100
PROJECT | TA 504 | All | 5 | 5 | 100 | 110 | 136 | 80 | 0 | 0 | 0
PROJECT | TA 505 | All | 21 | 21 | 100 | 175.4 | 182 | 85.7 | 0 | 21 | 100
PROJECT | TA 506 | All | 44 | 41 | 93.2 | 133 | 131.5 | 77.5 | 1 | 44 | 100
PROJECT | TB 408 | All | 22 | 22 | 100 | 158.5 | 155 | 77.3 | 0 | 22 | 100
PROJECT | TB 412 | All | 20 | 0 | 0 |  |  |  | 0 | 20 | 100
PROJECT | TB 501 - 132kV | All | 8 | 8 | 100 | 36.5 | 11.5 | 25 | 0 | 8 | 100
PROJECT | TB 501 - 220kV | All | 10 | 8 | 80 | 184.8 | 167.5 | 75 | 0 | 10 | 100
PROJECT | TB 507 - MAIN | All | 21 | 21 | 100 | 172.3 | 190 | 100 | 0 | 6 | 28.6
PROJECT | TB 605 | All | 8 | 0 | 0 |  |  |  | 0 | 8 | 100
SERIES | 4xx | All | 158 | 117 | 74.1 | 155.7 | 150 | 84.2 | 3 | 130 | 82.3
SERIES | 5xx | All | 94 | 89 | 94.7 | 144.3 | 139 | 77.5 | 0 | 74 | 78.7
SERIES | 6xx | All | 8 | 0 | 0 |  |  |  | 0 | 8 | 100
CLIENT_TYPE | TA | All | 174 | 149 | 85.6 | 150.7 | 144.5 | 82.9 | 3 | 141 | 81
CLIENT_TYPE | TB | All | 86 | 57 | 66.3 | 150.7 | 150 | 77.2 | 0 | 71 | 82.6

## ES Delay Coverage
ES Delay Coverage
Scope Type | Scope Name | Method Split | Spans Considered | Spans With Computable Lag | Lag Coverage % | Fallback Rows | Fallback % | LOCATION_NOS Rows | HYBRID_PARTIAL_FALLBACK Rows | ALPHABETIC_FALLBACK Rows | Parse EMPTY Rows | Parse OK Rows | Parse PARTIAL_PARSE Rows | Parse SHORTHAND_NO_ANCHOR Rows | Negative Lag Excluded | Average Lag Days | Median Lag Days
OVERALL | All Projects | All | 260 | 206 | 79.2 | 212 | 81.5 | 48 | 2 | 210 | 189 | 69 | 1 | 1 | 3 | 150.7 | 146
OVERALL | All Projects | TSE | 21 | 21 | 100 | 12 | 57.1 | 9 | 0 | 12 | 12 | 9 | 0 | 0 | 2 | 110.6 | 107
OVERALL | All Projects | Others | 28 | 26 | 92.9 | 19 | 67.9 | 9 | 0 | 19 | 18 | 10 | 0 | 0 | 1 | 113.8 | 91
PROJECT | TA 413 | All | 23 | 23 | 100 | 23 | 100 | 0 | 0 | 23 | 23 | 0 | 0 | 0 | 0 | 185.3 | 204
PROJECT_METHOD | TA 413 | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TA 413 | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TA 414 | All | 26 | 26 | 100 | 13 | 50 | 13 | 0 | 13 | 13 | 13 | 0 | 0 | 2 | 67.7 | 64
PROJECT_METHOD | TA 414 | TSE | 10 | 10 | 100 | 6 | 60 | 4 | 0 | 6 | 6 | 4 | 0 | 0 | 1 | 52.3 | 34
PROJECT_METHOD | TA 414 | Others | 13 | 13 | 100 | 5 | 38.5 | 8 | 0 | 5 | 5 | 8 | 0 | 0 | 1 | 63.8 | 64
PROJECT | TA 416 | All | 16 | 16 | 100 | 1 | 6.2 | 15 | 1 | 0 | 0 | 15 | 0 | 1 | 0 | 175.9 | 187
PROJECT_METHOD | TA 416 | TSE | 5 | 5 | 100 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 198 | 232
PROJECT_METHOD | TA 416 | Others | 1 | 1 | 100 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 200 | 200
PROJECT | TA 418 | All | 21 | 0 | 0 | 21 | 100 | 0 | 0 | 21 | 0 | 21 | 0 | 0 | 0
PROJECT_METHOD | TA 418 | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TA 418 | Others | 1 | 0 | 0 | 1 | 100 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
PROJECT | TA 419 | All | 2 | 2 | 100 | 2 | 100 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 316 | 316
PROJECT_METHOD | TA 419 | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TA 419 | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TA 421 | All | 13 | 13 | 100 | 13 | 100 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 217.5 | 182
PROJECT_METHOD | TA 421 | TSE | 1 | 1 | 100 | 1 | 100 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 138 | 138
PROJECT_METHOD | TA 421 | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TA 504 | All | 5 | 5 | 100 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 110 | 136
PROJECT_METHOD | TA 504 | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TA 504 | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TA 505 | All | 21 | 21 | 100 | 21 | 100 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 175.4 | 182
PROJECT_METHOD | TA 505 | TSE | 3 | 3 | 100 | 3 | 100 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 121 | 166
PROJECT_METHOD | TA 505 | Others | 3 | 3 | 100 | 3 | 100 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 239.3 | 245
PROJECT | TA 506 | All | 44 | 41 | 93.2 | 44 | 100 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 1 | 133 | 131.5
PROJECT_METHOD | TA 506 | TSE | 2 | 2 | 100 | 2 | 100 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 140 | 140
PROJECT_METHOD | TA 506 | Others | 7 | 7 | 100 | 7 | 100 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 125.1 | 118
PROJECT | TB 408 | All | 22 | 22 | 100 | 22 | 100 | 0 | 0 | 22 | 22 | 0 | 0 | 0 | 0 | 158.5 | 155
PROJECT_METHOD | TB 408 | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TB 408 | Others | 2 | 2 | 100 | 2 | 100 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 142.5 | 142.5
PROJECT | TB 412 | All | 20 | 0 | 0 | 20 | 100 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0
PROJECT_METHOD | TB 412 | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TB 412 | Others | 1 | 0 | 0 | 1 | 100 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
PROJECT | TB 501 - 132kV | All | 8 | 8 | 100 | 8 | 100 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 36.5 | 11.5
PROJECT_METHOD | TB 501 - 132kV | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TB 501 - 132kV | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TB 501 - 220kV | All | 10 | 8 | 80 | 10 | 100 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 184.8 | 167.5
PROJECT_METHOD | TB 501 - 220kV | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TB 501 - 220kV | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TB 507 - MAIN | All | 21 | 21 | 100 | 6 | 28.6 | 15 | 1 | 5 | 5 | 15 | 1 | 0 | 0 | 172.3 | 190
PROJECT_METHOD | TB 507 - MAIN | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TB 507 - MAIN | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TB 605 | All | 8 | 0 | 0 | 8 | 100 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0
PROJECT_METHOD | TB 605 | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TB 605 | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SERIES | 4xx | All | 158 | 117 | 74.1 | 130 | 82.3 | 28 | 1 | 129 | 108 | 49 | 0 | 1 | 3 | 155.7 | 150
SERIES | 5xx | All | 94 | 89 | 94.7 | 74 | 78.7 | 20 | 1 | 73 | 73 | 20 | 1 | 0 | 0 | 144.3 | 139
SERIES | 6xx | All | 8 | 0 | 0 | 8 | 100 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0
CLIENT_TYPE | TA | All | 174 | 149 | 85.6 | 141 | 81 | 33 | 1 | 140 | 119 | 54 | 0 | 1 | 3 | 150.7 | 144.5
CLIENT_TYPE | TB | All | 86 | 57 | 66.3 | 71 | 82.6 | 15 | 1 | 70 | 70 | 15 | 1 | 0 | 0 | 150.7 | 150

## ES Delay Anomalies
ES Delay Anomalies
Project | Project Scope Key | Series | Client Type | Method Split | Span Key | From AP | To AP | PO Start Date | Last Erection Completion Date | Gap Days | Issue | Lag Inference Mode | Location Parse Status | Required Location Count | Matched Location Count | Unmatched Location Count | Fallback Used
TA 414 | ta413 | 4xx | TA | TSE | ta414¦121/1¦121/7 | 121/1 | 121/7 | 2026-04-13 | 2026-05-07 | -24 | NEGATIVE_LAG_EXCLUDED | LOCATION_NOS | OK | 7 | 7 | 0 | FALSE
TA 414 | ta413 | 4xx | TA | Others | ta414¦174/0¦175/0 | 174/0 | 175/0 | 2026-05-03 | 2026-05-16 | -13 | NEGATIVE_LAG_EXCLUDED | LOCATION_NOS | OK | 8 | 8 | 0 | FALSE
TA 418 |  | 4xx | TA |  | ta418¦36/1¦37/0 | 36/1 | 37/0 | 2026-05-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 2 | 0 | 2 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦37/0¦38 | 37/0 | AP38 | 2026-05-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 5 | 0 | 5 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦38¦39 | AP38 | AP39 | 2026-05-20 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 6 | 0 | 6 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦46¦46/7 | AP46 | 46/7 | 2026-07-17 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 9 | 0 | 9 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦47/0¦48 | AP47/0 | AP48 | 2026-07-09 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 4 | 0 | 4 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦48A/0¦49/0 | 48A/0 | 49/0 | 2026-06-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 4 | 0 | 4 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦49/0¦50 | 49/0 | AP50 | 2026-07-09 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 3 | 0 | 3 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦50¦51 | AP50 | AP51 | 2026-07-09 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 4 | 0 | 4 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦51¦52 | AP51 | AP52 | 2026-06-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 4 | 0 | 4 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦52¦53 | AP52 | AP53 | 2026-06-03 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 6 | 0 | 6 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦53¦54 | AP53 | AP54 | 2026-06-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 4 | 0 | 4 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦54¦55 | AP54 | AP55 | 2026-06-14 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 8 | 0 | 8 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦55¦56 | AP55 | AP56 | 2026-04-28 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 10 | 0 | 10 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦56/3¦57/0 | 56/3 | 57/0 | 2026-06-04 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 2 | 0 | 2 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦57/0¦58/0 | 57/0 | 58/0 | 2026-06-17 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 5 | 0 | 5 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦58/0¦59/0 | 58/0 | 59/0 | 2026-06-24 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 2 | 0 | 2 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦59/0¦60/0 | 59/0 | 60/0 | 2026-06-24 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 3 | 0 | 3 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦60/0¦61/0 | 60/0 | 61/0 | 2026-07-01 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 6 | 0 | 6 | TRUE
TA 418 | ta414 | 4xx | TA | Others | ta418¦61/0¦62/0 | 61/0 | 62/0 | 2026-04-08 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | OK | 2 | 0 | 2 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦62/0¦63/0 | 62/0 | 63/0 | 2026-05-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 2 | 0 | 2 | TRUE
TA 418 |  | 4xx | TA |  | ta418¦63/0¦GNTY | 63/0 | GNTY | 2026-04-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | OK | 3 | 0 | 3 | TRUE
TA 506 | ta414 | 4xx | TA | TSE | ta506¦17/0¦18/0 | 17/0 | 18/0 | 2026-04-06 | 2026-04-10 | -4 | NEGATIVE_LAG_EXCLUDED | ALPHABETIC_FALLBACK | EMPTY | 2 | 2 | 0 | TRUE
TA 506 |  | 5xx | TA |  | ta506¦38/0¦39/0 | 38/0 | 39/0 | 2026-05-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 506 |  | 5xx | TA |  | ta506¦200/0¦201/0 | 200/0 | 201/0 | 2026-07-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 506 |  | 5xx | TA |  | ta506¦201/0¦202/0 | 201/0 | 202/0 | 2026-08-06 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦7/0¦DB+0 | 7/0 | DB+0 | 2026-08-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦46/0¦DD+3 | 46/0 | DD+3 | 2026-08-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦33/0¦DD+0 | 33/0 | DD+0 | 2026-08-08 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦143/0¦DC+3 | 143/0 | DC+3 | 2026-07-14 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦74/0¦DD+3 | 74/0 | DD+3 | 2026-07-09 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦70/2¦DA+3 1MRC | 70/2 | DA+3 1MRC | 2026-07-13 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦61/2¦DA+9 | 61/2 | DA+9 | 2026-07-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦151/2¦DA+6 | 151/2 | DA+6 | 2026-08-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦106/0¦DD+9 | 106/0 | DD+9 | 2026-08-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦152/3¦DA+6 | 152/3 | DA+6 | 2026-08-05 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦104/5¦DA+3 | 104/5 | DA+3 | 2026-08-05 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦132/5¦DA+3 | 132/5 | DA+3 | 2026-08-06 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 | ta414 | 4xx | TA | Others | tb412¦104/3¦DA+3 | 104/3 | DA+3 | 2026-08-05 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦104/4¦DA+0 | 104/4 | DA+0 | 2026-08-07 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦104/2¦DA+6 | 104/2 | DA+6 | 2026-08-08 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦150/0¦DD+0 | 150/0 | DD+0 | 2026-08-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦104/1¦DA+3 | 104/1 | DA+3 | 2026-08-09 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦3/0¦2TNMD+0 | 3/0 | 2TNMD+0 | 2026-08-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦8/0¦DD+0 | 8/0 | DD+0 | 2026-08-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 412 |  | 4xx | TB |  | tb412¦132/3¦DA+6 | 132/3 | DA+6 | 2026-08-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 501 - 220kV |  | 5xx | TB |  | tb501220kv¦33/0¦34/0 | 33/0 | 34/0 | 2026-06-01 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 501 - 220kV |  | 5xx | TB |  | tb501220kv¦34/0¦35/0 | 34/0 | 35/0 | 2026-06-08 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 605 |  | 6xx | TB |  | tb605¦25¦26 | AP25 | AP26 | 2026-06-17 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 605 |  | 6xx | TB |  | tb605¦26¦27 | AP26 | AP27 | 2026-06-14 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 605 |  | 6xx | TB |  | tb605¦18¦19 | AP18 | AP19 | 2026-07-07 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 605 |  | 6xx | TB |  | tb605¦24¦25 | AP24 | AP25 | 2026-06-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 605 |  | 6xx | TB |  | tb605¦20¦21 | AP20 | AP21 | 2026-07-01 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 605 |  | 6xx | TB |  | tb605¦27¦28 | AP27 | AP28 | 2026-07-11 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 605 |  | 6xx | TB |  | tb605¦19¦20 | AP19 | AP20 | 2026-07-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 605 |  | 6xx | TB |  | tb605¦28¦29 | AP28 | AP29 | 2026-07-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE

## ES Delay Detail
ES Delay Detail
Project | Project Code | Project Display | Project Scope Key | Join Project Key | Base Project Code | Series | Client Type | Method Split | Section | Span | Span Key | Gang Name | From AP | To AP | PO Start Date | Last Erection Completion Date | Gap Days | Gap Days Non-Negative | Lag Inference Mode | Fallback Used | Location Parse Status | Location Parse Issue | Required Location Count | Matched Location Count | Unmatched Location Count | Required Locations | Matched Locations | Unmatched Locations | Location Nos Raw | Project Key In Erection Map
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 29A/0-30/0 | ta413¦29A/0¦30/0 |  | 29A/0 | 30/0 | 2026-04-22 | 2026-01-06 | 106 | 106 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 29A/0, 30/0 | 29A/0, 30/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 10/0-11/0 | ta413¦10/0¦11/0 |  | 10/0 | 11/0 | 2026-04-07 | 2025-11-26 | 132 | 132 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 10/0, 11/0 | 10/0, 11/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 29/0-29A/0 | ta413¦29/0¦29A/0 |  | 29/0 | 29A/0 | 2026-05-08 | 2025-12-20 | 139 | 139 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 29/0, 29A/0 | 29/0, 29A/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 27/0-28/0 | ta413¦27/0¦28/0 |  | 27/0 | 28/0 | 2026-05-20 | 2025-12-14 | 157 | 157 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 27/0, 28/0 | 27/0, 28/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 11/0-12/0 | ta413¦11/0¦12/0 |  | 11/0 | 12/0 | 2026-06-05 | 2025-11-26 | 191 | 191 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 11/0, 12/0 | 11/0, 12/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 14/0-15/0 | ta413¦14/0¦15/0 |  | 14/0 | 15/0 | 2026-06-07 | 2025-12-17 | 172 | 172 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 14/0, 15/0 | 14/0, 15/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 13/0-13A/0 | ta413¦13/0¦13A/0 |  | 13/0 | 13A/0 | 2026-06-19 | 2026-01-20 | 150 | 150 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 13/0, 13A/0 | 13/0, 13A/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 13A/0-14/0 | ta413¦13A/0¦14/0 |  | 13A/0 | 14/0 | 2026-06-19 | 2026-01-20 | 150 | 150 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 13A/0, 14/0 | 13A/0, 14/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 18/0-19/0 | ta413¦18/0¦19/0 |  | 18/0 | 19/0 | 2026-06-13 | 2025-10-28 | 228 | 228 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 18/0, 19/0 | 18/0, 19/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 35/0-36/0 | ta413¦35/0¦36/0 |  | 35/0 | 36/0 | 2026-06-13 | 2026-02-16 | 117 | 117 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 35/0, 36/0 | 35/0, 36/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 24/0-25/0 | ta413¦24/0¦25/0 |  | 24/0 | 25/0 | 2026-06-21 | 2025-11-29 | 204 | 204 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 24/0, 25/0 | 24/0, 25/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 23A/0-24/0 | ta413¦23A/0¦24/0 |  | 23A/0 | 24/0 | 2026-06-22 | 2025-11-27 | 207 | 207 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 23A/0, 24/0 | 23A/0, 24/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 28/0-29/0 | ta413¦28/0¦29/0 |  | 28/0 | 29/0 | 2026-07-01 | 2025-11-12 | 231 | 231 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 28/0, 29/0 | 28/0, 29/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 23/0-23A/0 | ta413¦23/0¦23A/0 |  | 23/0 | 23A/0 | 2026-07-01 | 2025-11-27 | 216 | 216 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 23/0, 23A/0 | 23/0, 23A/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 36/0-36A/0 | ta413¦36/0¦36A/0 |  | 36/0 | 36A/0 | 2026-07-09 | 2026-02-04 | 155 | 155 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 36/0, 36A/0 | 36/0, 36A/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 25/0-26/0 | ta413¦25/0¦26/0 |  | 25/0 | 26/0 | 2026-07-01 | 2025-11-29 | 214 | 214 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 25/0, 26/0 | 25/0, 26/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 15/0-16/0 | ta413¦15/0¦16/0 |  | 15/0 | 16/0 | 2026-07-09 | 2026-06-19 | 20 | 20 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 15/0, 16/0 | 15/0, 16/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 40/0-40A/0 | ta413¦40/0¦40A/0 |  | 40/0 | 40A/0 | 2026-07-15 | 2025-10-19 | 269 | 269 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 40/0, 40A/0 | 40/0, 40A/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 22/0-23/0 | ta413¦22/0¦23/0 |  | 22/0 | 23/0 | 2026-07-27 | 2025-11-13 | 256 | 256 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 22/0, 23/0 | 22/0, 23/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 20/0-21/0 | ta413¦20/0¦21/0 |  | 20/0 | 21/0 | 2026-07-25 | 2025-11-06 | 261 | 261 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 20/0, 21/0 | 20/0, 21/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 26/0-27/0 | ta413¦26/0¦27/0 |  | 26/0 | 27/0 | 2026-08-01 | 2025-11-29 | 245 | 245 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 26/0, 27/0 | 26/0, 27/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 12/0-13/0 | ta413¦12/0¦13/0 |  | 12/0 | 13/0 | 2026-08-07 | 2025-12-31 | 219 | 219 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 12/0, 13/0 | 12/0, 13/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 43A/0-44/0 | ta413¦43A/0¦44/0 |  | 43A/0 | 44/0 | 2026-08-01 | 2025-12-21 | 223 | 223 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 43A/0, 44/0 | 43A/0, 44/0 |  |  | FALSE
TA 414 |  |  |  |  | TA 414 | 4xx | TA |  | Unassigned | 118/0-119/0 | ta414¦118/0¦119/0 | Dharmendra | 118/0 | 119/0 | 2026-05-23 | 2025-08-30 | 266 | 266 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 118/0, 119/0 | 118/0, 119/0 |  |  | FALSE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 119/0-120/0 | ta414¦119/0¦120/0 | Enamul Haque | 119/0 | 120/0 | 2026-04-16 | 2026-01-31 | 75 | 75 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 119/0, 120/0, 119/1, 119/2, 119/3 | 119/0, 120/0, 119/1, 119/2, 119/3 |  | 119/1,119/2,119/3 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 120/0-121/0 | ta414¦120/0¦121/0 | Enamul Haque | 120/0 | 121/0 | 2026-05-03 | 2026-04-19 | 14 | 14 | LOCATION_NOS | FALSE | OK |  | 9 | 9 | 0 | 120/0, 121/0, 120/1, 120/2, 120/3, 120/4, 120/5, 120/6, 120/7 | 120/0, 121/0, 120/1, 120/2, 120/3, 120/4, 120/5, 120/6, 120/7 |  | 120/1,120/2,120/3,120/4,120/5,120/6,120/7 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 121/1-121/7 | ta414¦121/1¦121/7 | Enamul Haque | 121/1 | 121/7 | 2026-04-13 | 2026-05-07 | -24 |  | LOCATION_NOS | FALSE | OK |  | 7 | 7 | 0 | 121/1, 121/7, 121/2, 121/3, 121/4, 121/5, 121/6 | 121/1, 121/7, 121/2, 121/3, 121/4, 121/5, 121/6 |  | 121/2,121/3,121/4,121/5,121/6 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 124/0-125/0 | ta414¦124/0¦125/0 | Enamul Haque | 124/0 | 125/0 | 2026-06-09 | 2026-05-28 | 12 | 12 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 124/0, 125/0, 124/1, 124/2, 124/3 | 124/0, 125/0, 124/1, 124/2, 124/3 |  | 124/1,124/2,124/3 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 126/0-127/0 | ta414¦126/0¦127/0 | Enamul Haque | 126/0 | 127/0 | 2026-05-24 | 2026-04-03 | 51 | 51 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 126/0, 127/0, 126/1, 126/2, 126/3 | 126/0, 127/0, 126/1, 126/2, 126/3 |  | 126/1,126/2,126/3 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 143/0-144/0 | ta414¦143/0¦144/0 |  | 143/0 | 144/0 | 2026-06-08 | 2026-03-29 | 71 | 71 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 143/0, 144/0 | 143/0, 144/0 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 148/0-148/5 | ta414¦148/0¦148/5 |  | 148/0 | 148/5 | 2026-06-18 | 2026-02-21 | 117 | 117 | LOCATION_NOS | FALSE | OK |  | 6 | 6 | 0 | 148/0, 148/5, 148/1, 148/2, 148/3, 148/4 | 148/0, 148/5, 148/1, 148/2, 148/3, 148/4 |  | 148/1,148/2,148/3,148/4 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 174/0-175/0 | ta414¦174/0¦175/0 | Alam Construction | 174/0 | 175/0 | 2026-05-03 | 2026-05-16 | -13 |  | LOCATION_NOS | FALSE | OK |  | 8 | 8 | 0 | 174/0, 175/0, 174/1, 174/2, 174/3, 174/4, 174/5, 174/6 | 174/0, 175/0, 174/1, 174/2, 174/3, 174/4, 174/5, 174/6 |  | 174/1,174/2,174/3,174/4,174/5,174/6 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 175/0-175/1 | ta414¦175/0¦175/1 | Alam Construction | 175/0 | 175/1 | 2026-05-02 | 2026-01-15 | 107 | 107 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 175/0, 175/1 | 175/0, 175/1 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 175/1-176/0 | ta414¦175/1¦176/0 | Maa Singhvahini | 175/1 | 176/0 | 2026-04-06 | 2026-01-06 | 90 | 90 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 175/1, 176/0 | 175/1, 176/0 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 176/0-177/0 | ta414¦176/0¦177/0 | Alam Construction | 176/0 | 177/0 | 2026-04-24 | 2026-02-20 | 63 | 63 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 176/0, 177/0, 176/1, 176/2 | 176/0, 177/0, 176/1, 176/2 |  | 176/1,176/2 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 177/0-178/0 | ta414¦177/0¦178/0 | Sanjay singh 2 | 177/0 | 178/0 | 2026-05-15 | 2026-04-04 | 41 | 41 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 177/0, 178/0 | 177/0, 178/0 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 178/0-179/0 | ta414¦178/0¦179/0 |  | 178/0 | 179/0 | 2026-05-14 | 2026-04-04 | 40 | 40 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 178/0, 179/0, 178/1, 178/2, 178/3 | 178/0, 179/0, 178/1, 178/2, 178/3 |  | 178/1,178/2,178/3 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 180/2-182/0 | ta414¦180/2¦182/0 | Alam Construction | 180/2 | 182/0 | 2026-04-06 | 2026-02-13 | 52 | 52 | LOCATION_NOS | FALSE | OK |  | 7 | 7 | 0 | 180/2, 182/0, 180/3, 180/4, 180/5, 180/6, 180/7 | 180/2, 182/0, 180/3, 180/4, 180/5, 180/6, 180/7 |  | 180/3,180/4,180/5,180/6,180/7 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 182/0-183/0 | ta414¦182/0¦183/0 | Sanjay Singh | 182/0 | 183/0 | 2026-04-05 | 2026-01-29 | 66 | 66 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 182/0, 183/0 | 182/0, 183/0 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 183/0-184/0 | ta414¦183/0¦184/0 | Alam Construction | 183/0 | 184/0 | 2026-04-18 | 2026-03-21 | 28 | 28 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 183/0, 184/0, 183/1, 183/2, 183/3 | 183/0, 184/0, 183/1, 183/2, 183/3 |  | 183/1,183/2,183/3 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 184/0-185/0 | ta414¦184/0¦185/0 | Sanjay Singh 1 | 184/0 | 185/0 | 2026-05-06 | 2026-04-20 | 16 | 16 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 184/0, 185/0 | 184/0, 185/0 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 185/0-186/0 | ta414¦185/0¦186/0 | Sanjay Singh 2 | 185/0 | 186/0 | 2026-05-24 | 2026-04-20 | 34 | 34 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 185/0, 186/0 | 185/0, 186/0 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 186/0-187/0 | ta414¦186/0¦187/0 |  | 186/0 | 187/0 | 2026-06-05 | 2026-03-17 | 80 | 80 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 186/0, 187/0 | 186/0, 187/0 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 190/0-191/0 | ta414¦190/0¦191/0 |  | 190/0 | 191/0 | 2026-05-28 | 2026-02-20 | 97 | 97 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 190/0, 191/0 | 190/0, 191/0 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 197/0-198/0 | ta414¦197/0¦198/0 | Abdul adut | 197/0 | 198/0 | 2026-05-18 | 2026-02-16 | 91 | 91 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 197/0, 198/0, 197/1, 197/2 | 197/0, 198/0, 197/1, 197/2 |  | 197/1,197/2 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 198/0-199/0 | ta414¦198/0¦199/0 |  | 198/0 | 199/0 | 2026-04-17 | 2026-02-11 | 65 | 65 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 198/0, 199/0 | 198/0, 199/0 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 221/0-222/0 | ta414¦221/0¦222/0 | Sanjay Singh 1 | 221/0 | 222/0 | 2026-06-19 | 2026-05-24 | 26 | 26 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 221/0, 222/0 | 221/0, 222/0 |  |  | TRUE
TA 414 |  |  |  |  | TA 414 | 4xx | TA |  | Unassigned | 222/0-223/0 | ta414¦222/0¦223/0 | Sanjay Singh 2 | 222/0 | 223/0 | 2026-06-19 | 2026-04-02 | 78 | 78 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 222/0, 223/0 | 222/0, 223/0 |  |  | FALSE
TA 414 |  |  |  |  | TA 414 | 4xx | TA |  | Unassigned | 245/0-246/0 | ta414¦245/0¦246/0 | Bhola prasad+ Deepak Sarkar | 245/0 | 246/0 | 2026-04-11 | 2026-02-25 | 45 | 45 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 245/0, 246/0, 245/1 | 245/0, 246/0, 245/1 |  | 245/1 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Unassigned | 62/0-63/0 | ta416¦62/0¦63/0 | Khosibur Ali(Company) | AP62/0 | AP63/0 | 2026-04-14 | 2025-12-04 | 131 | 131 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 62/0, 63/0 | 62/0, 63/0 |  | 62/0,63/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Unassigned | 54/0-55/0 | ta416¦54/0¦55/0 | Jahangir(Company) | AP54/0 | AP55/0 | 2026-04-02 | 2025-11-07 | 146 | 146 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 54/0, 55/0, 54/1, 54/2 | 54/0, 55/0, 54/1, 54/2 |  | 54/0,1,2,55/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Unassigned | 61/0-62/0 | ta416¦61/0¦62/0 | (Kunal Hot line | AP61/0 | AP62/0 | 2026-04-15 | 2025-12-04 | 132 | 132 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 61/0, 62/0 | 61/0, 62/0 |  | 61/0,62/0 | FALSE
TA 416 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 64/0-65/0 | ta416¦64/0¦65/0 | Astharul (company) | AP64/0 | AP65/0 | 2026-04-10 | 2025-09-22 | 200 | 200 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 64/0, 65/0 | 64/0, 65/0 |  | 64/0,65/0 | TRUE
TA 416 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 55/0-56/0 | ta416¦55/0¦56/0 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 2026-04-12 | 2025-11-17 | 146 | 146 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 55/0, 56/0, 55/1 | 55/0, 56/0, 55/1 |  | 55/0,1,56/0 | TRUE
TA 416 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 47/0-48/0 | ta416¦47/0¦48/0 | Kunal Hot line | AP47/0 | AP48/0 | 2026-05-20 | 2025-09-22 | 240 | 240 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 47/0, 48/0 | 47/0, 48/0 |  | 47/0,48/0 | TRUE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Unassigned | 56/0-57/0 | ta416¦56/0¦57/0 | ANARUL ISLAM | AP56/0 | AP57/0 | 2026-05-10 | 2026-03-09 | 62 | 62 | LOCATION_NOS | FALSE | OK |  | 10 | 10 | 0 | 56/0, 57/0, 56/1, 56/2, 56/3, 56/4, 56/5, 56/6, 56/7, 56/8 | 56/0, 57/0, 56/1, 56/2, 56/3, 56/4, 56/5, 56/6, 56/7, 56/8 |  | 56/0,1,2,3,4,5,6,7,8,57/0 | FALSE
TA 416 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 57/0-58/0 | ta416¦57/0¦58/0 | ANARUL ISLAM | AP57/0 | AP58/0 | 2026-05-17 | 2026-01-17 | 120 | 120 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 57/0, 58/0, 57/1 | 57/0, 58/0, 57/1 |  | 57/0,1,58/0 | TRUE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Unassigned | 59/0-60/0 | ta416¦59/0¦60/0 | RK Enterprise | AP59/0 | AP60/0 | 2026-06-03 | 2025-12-04 | 181 | 181 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 59/0, 60/0 | 59/0, 60/0 |  | 59/0, 60/0 | FALSE
TA 416 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 63/0-64/0 | ta416¦63/0¦64/0 | ANARUL ISLAM | AP63/0 | AP64/0 | 2026-06-01 | 2025-10-12 | 232 | 232 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 63/0, 64/0 | 63/0, 64/0 |  | 63/0,64/0 | TRUE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Unassigned | 58/0-59/0 | ta416¦58/0¦59/0 | Dharmendra Hot line | AP58/0 | AP59/0 | 2026-06-01 | 2026-01-17 | 135 | 135 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 58/0, 59/0 | 58/0, 59/0 |  | 58/0,59/0 | FALSE
TA 416 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 51/0-52/0 | ta416¦51/0¦52/0 | Kunal Hot line | AP51/0 | AP52/0 | 2026-06-01 | 2025-09-22 | 252 | 252 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 51/0, 52/0 | 51/0, 52/0 |  | 51/0,52/0 | TRUE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Unassigned | 48/0-49/0 | ta416¦48/0¦49/0 | ANARUL ISLAM | AP48/0 | AP49/0 | 2026-06-11 | 2025-11-30 | 193 | 193 | HYBRID_PARTIAL_FALLBACK | TRUE | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | 2 | 2 | 0 | 48/0, 49/0 | 48/0, 49/0 |  | 48/0-49/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Unassigned | 49/0-50/0 | ta416¦49/0¦50/0 | Dharmendra Hot line | AP49/0 | AP50/0 | 2026-06-12 | 2025-11-30 | 194 | 194 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 49/0, 50/0 | 49/0, 50/0 |  | 49/0,50/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Unassigned | 60/0-61/0 | ta416¦60/0¦61/0 | ANARUL ISLAM | AP60/0 | AP61/0 | 2026-06-10 | 2025-11-29 | 193 | 193 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 60/0, 61/0 | 60/0, 61/0 |  | 60/0,61/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Unassigned | 50/0-51/0 | ta416¦50/0¦51/0 | SADIK Con(company) | AP50/0 | AP51/0 | 2026-06-29 | 2025-10-14 | 258 | 258 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 50/0, 51/0 | 50/0, 51/0 |  | 50/0,51/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 36/1-37/0 | ta418¦36/1¦37/0 | Dharmendar | 36/1 | 37/0 | 2026-05-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 2 | 0 | 2 | 36/1, 37/0 |  | 36/1, 37/0 | 36/1, 37/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 37/0-38 | ta418¦37/0¦38 | SUFIYAN | 37/0 | AP38 | 2026-05-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 5 | 0 | 5 | 37/0, 38, 37/1, 37/2, 38/0 |  | 37/0, 38, 37/1, 37/2, 38/0 | 37/0, 37/1, 37/2, 38/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 38-39 | ta418¦38¦39 | SUFIYAN | AP38 | AP39 | 2026-05-20 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 6 | 0 | 6 | 38, 39, 38/0, 38/1, 38/2, 39/0 |  | 38, 39, 38/0, 38/1, 38/2, 39/0 | 38/0, 38/1, 38/2, 39/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 46-46/7 | ta418¦46¦46/7 |  | AP46 | 46/7 | 2026-07-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 9 | 0 | 9 | 46, 46/7, 46/0, 46/1, 46/2, 46/3, 46/4, 46/5, 46/6 |  | 46, 46/7, 46/0, 46/1, 46/2, 46/3, 46/4, 46/5, 46/6 | 46/0,46/1,46/2,46/3,46/4,46/5,46/6,46/7 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 47/0-48 | ta418¦47/0¦48 |  | AP47/0 | AP48 | 2026-07-09 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 4 | 0 | 4 | 47/0, 48, 47/1, 48/0 |  | 47/0, 48, 47/1, 48/0 | 47/0,47/1,48/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 48A/0-49/0 | ta418¦48A/0¦49/0 |  | 48A/0 | 49/0 | 2026-06-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 4 | 0 | 4 | 48A/0, 49/0, 48A/1, 48A/2 |  | 48A/0, 49/0, 48A/1, 48A/2 | 48A/0,48A/1,48A/2,49/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 49/0-50 | ta418¦49/0¦50 |  | 49/0 | AP50 | 2026-07-09 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 3 | 0 | 3 | 49/0, 50, 50/0 |  | 49/0, 50, 50/0 | 49/0,50/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 50-51 | ta418¦50¦51 |  | AP50 | AP51 | 2026-07-09 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 4 | 0 | 4 | 50, 51, 50/0, 51/0 |  | 50, 51, 50/0, 51/0 | 50/0,51/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 51-52 | ta418¦51¦52 | M/s Akram | AP51 | AP52 | 2026-06-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 4 | 0 | 4 | 51, 52, 51/0, 52/0 |  | 51, 52, 51/0, 52/0 | 51/0,52/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 52-53 | ta418¦52¦53 | M/s Ranveer | AP52 | AP53 | 2026-06-03 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 6 | 0 | 6 | 52, 53, 52/0, 52/1, 52/2, 53/0 |  | 52, 53, 52/0, 52/1, 52/2, 53/0 | 52/0,52/1,52/2,53/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 53-54 | ta418¦53¦54 |  | AP53 | AP54 | 2026-06-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 4 | 0 | 4 | 53, 54, 53/0, 54/0 |  | 53, 54, 53/0, 54/0 | 53/0,54/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 54-55 | ta418¦54¦55 | M/s Akram | AP54 | AP55 | 2026-06-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 8 | 0 | 8 | 54, 55, 54/0, 54/1, 54/2, 54/3, 54/4, 55/0 |  | 54, 55, 54/0, 54/1, 54/2, 54/3, 54/4, 55/0 | 54/0,54/1,54/2,54/3,54/4,55/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 55-56 | ta418¦55¦56 | SUFIYAN | AP55 | AP56 | 2026-04-28 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 10 | 0 | 10 | 55, 56, 55/0, 55/1, 55/2, 55/3, 55/4, 55/5, 55/6, 56/0 |  | 55, 56, 55/0, 55/1, 55/2, 55/3, 55/4, 55/5, 55/6, 56/0 | 55/0,55/1,55/2,55/3,55/4,55/5,55/6,56/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 56/3-57/0 | ta418¦56/3¦57/0 | M/s Dharmander | 56/3 | 57/0 | 2026-06-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 2 | 0 | 2 | 56/3, 57/0 |  | 56/3, 57/0 | 56/3,57/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 57/0-58/0 | ta418¦57/0¦58/0 | M/s Kamrudhin | 57/0 | 58/0 | 2026-06-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 5 | 0 | 5 | 57/0, 58/0, 57/1, 57/2, 57/3 |  | 57/0, 58/0, 57/1, 57/2, 57/3 | 57/0,57/1,57/2,57/3,58/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 58/0-59/0 | ta418¦58/0¦59/0 |  | 58/0 | 59/0 | 2026-06-24 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 2 | 0 | 2 | 58/0, 59/0 |  | 58/0, 59/0 | 58/0,59/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 59/0-60/0 | ta418¦59/0¦60/0 |  | 59/0 | 60/0 | 2026-06-24 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 3 | 0 | 3 | 59/0, 60/0, 59/1 |  | 59/0, 60/0, 59/1 | 59/0,59/1,60/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 60/0-61/0 | ta418¦60/0¦61/0 |  | 60/0 | 61/0 | 2026-07-01 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 6 | 0 | 6 | 60/0, 61/0, 60/1, 60/2, 60/3, 60/4 |  | 60/0, 61/0, 60/1, 60/2, 60/3, 60/4 | 60/0,60/1,60/2,60/3,60/4,61/0 | FALSE
TA 418 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 61/0-62/0 | ta418¦61/0¦62/0 | M/s Kamrudhin | 61/0 | 62/0 | 2026-04-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 2 | 0 | 2 | 61/0, 62/0 |  | 61/0, 62/0 | 61/0,62/0 | TRUE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 62/0-63/0 | ta418¦62/0¦63/0 | M/s Kamrudhin | 62/0 | 63/0 | 2026-05-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 2 | 0 | 2 | 62/0, 63/0 |  | 62/0, 63/0 | 62/0,63/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Unassigned | 63/0-GNTY | ta418¦63/0¦GNTY | M/s Kamrudhin | 63/0 | GNTY | 2026-04-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | OK |  | 3 | 0 | 3 | 63/0, GNTY, 63/GNTY |  | 63/0, GNTY, 63/GNTY | 63/0,GNTY | FALSE
TA 419 |  |  |  |  | TA 419 | 4xx | TA |  | TSE 1 | 0D/0-0D/5 | ta419¦0D/0¦0D/5 | Saheb Enterprises | 0D/0 | 0D/5 | 2026-06-12 | 2025-02-27 | 470 | 470 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 0D/0, 0D/5 | 0D/0, 0D/5 |  |  | FALSE
TA 419 |  |  |  |  | TA 419 | 4xx | TA |  | TSE 2 | 6/0-7/0 | ta419¦6/0¦7/0 | Mussoluddin | 6/0 | 7/0 | 2026-07-12 | 2026-01-31 | 162 | 162 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 6/0, 7/0 | 6/0, 7/0 |  |  | FALSE
TA 421 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | 36/0 - 37/0 | 36/0-37/0 | ta421¦36/0¦37/0 | Kamruddin | 36/0 | 37/0 | 2026-04-13 | 2025-11-26 | 138 | 138 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 36/0, 37/0 | 36/0, 37/0 |  |  | TRUE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | 42/0 - 43/0 | 42/0-43/0 | ta421¦42/0¦43/0 | Nasiruddin | 42/0 | 43/0 | 2026-04-30 | 2025-12-09 | 142 | 142 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 42/0, 43/0 | 42/0, 43/0 |  |  | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | 43/0 - 43A/0 | 43/0-43A/0 | ta421¦43/0¦43A/0 | Nasiruddin | 43/0 | 43A/0 | 2026-05-14 | 2025-12-09 | 156 | 156 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 43/0, 43A/0 | 43/0 | 43A/0 |  | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | 34/2-35/0 | 34/2-35/0 | ta421¦34/2¦35/0 | Ramavath | 34/2 | 35/0 | 2026-05-18 | 2025-08-03 | 288 | 288 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 34/2, 35/0 | 34/2, 35/0 |  |  | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | 35/0 - 36/0 | 35/0-36/0 | ta421¦35/0¦36/0 | Kamruddin | 35/0 | 36/0 | 2026-05-18 | 2025-11-19 | 180 | 180 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 35/0, 36/0 | 35/0, 36/0 |  |  | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | 34/1 - 34/2 | 34/1-34/2 | ta421¦34/1¦34/2 | Pankaj | 34/1 | 34/2 | 2026-06-02 | 2025-08-12 | 294 | 294 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 34/1, 34/2 | 34/1, 34/2 |  |  | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | 34/0 - 34/1 | 34/0-34/1 | ta421¦34/0¦34/1 | Ramavath | 34/0 | 34/1 | 2026-06-02 | 2025-08-12 | 294 | 294 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 34/0, 34/1 | 34/0, 34/1 |  |  | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | 33/0 - 34/0 | 33/0-34/0 | ta421¦33/0¦34/0 | Pankaj | 33/0 | 34/0 | 2026-05-26 | 2025-06-25 | 335 | 335 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 33/0, 34/0 | 33/0, 34/0 |  |  | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | 43A/0 - 43A/1 | 43A/0-43A/1 | ta421¦43A/0¦43A/1 | Nasiruddin | 43A/0 | 43A/1 | 2026-06-10 | 2026-01-07 | 154 | 154 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 43A/0, 43A/1 | 43A/1 | 43A/0 |  | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | 43A/1 - 43B/0 | 43A/1-43B/0 | ta421¦43A/1¦43B/0 | Nasiruddin | 43A/1 | 43B/0 | 2026-05-31 | 2026-01-12 | 139 | 139 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 43A/1, 43B/0 | 43A/1, 43B/0 |  |  | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | 43B/0 - 44/0 | 43B/0-44/0 | ta421¦43B/0¦44/0 | Nasiruddin | 43B/0 | 44/0 | 2026-06-20 | 2025-12-20 | 182 | 182 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 43B/0, 44/0 | 43B/0, 44/0 |  |  | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | 40/0 - 41/0 | 40/0-41/0 | ta421¦40/0¦41/0 | Pankaj | 40/0 | 41/0 | 2026-06-24 | 2025-09-13 | 284 | 284 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 40/0, 41/0 | 40/0, 41/0 |  |  | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | 41/0 - 42/0 | 41/0-42/0 | ta421¦41/0¦42/0 | Pankaj | 41/0 | 42/0 | 2026-06-24 | 2025-10-25 | 242 | 242 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 41/0, 42/0 | 41/0, 42/0 |  |  | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Unassigned | 11/0-12/0 | ta504¦11/0¦12/0 | Tanjira Bibi | 11/0 | 12/0 | 2026-05-09 | 2026-04-15 | 24 | 24 | LOCATION_NOS | FALSE | OK |  | 8 | 8 | 0 | 11/0, 12/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6 | 11/0, 12/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6 |  | 11/1, 11/2, 11/3, 11/4, 11/5, 11/6, 12/0 | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Unassigned | 12/0-13/0 | ta504¦12/0¦13/0 | Tanjira Bibi | 12/0 | 13/0 | 2026-05-16 | 2025-11-17 | 180 | 180 | LOCATION_NOS | FALSE | OK |  | 7 | 7 | 0 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5 |  | 12/1, 12/2, 12/3, 12/4, 12/5, 13/0 | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Unassigned | 16/0-16/3 | ta504¦16/0¦16/3 | Lamba Construction | 16/0 | 16/3 | 2026-04-01 | 2026-01-24 | 67 | 67 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 16/0, 16/3, 16/1, 16/2 | 16/0, 16/3, 16/1, 16/2 |  | 16/1, 16/2, 16/3 | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Unassigned | 19/0-20/0 | ta504¦19/0¦20/0 | Lamba Construction | 19/0 | 20/0 | 2026-05-23 | 2025-12-31 | 143 | 143 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 19/0, 20/0, 19/1, 19/2, 19/3 | 19/0, 20/0, 19/1, 19/2, 19/3 |  | 19/1, 19/2, 19/3, 20/0 | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Unassigned | 20/0-21/0 | ta504¦20/0¦21/0 | Lamba Construction | 20/0 | 21/0 | 2026-05-16 | 2025-12-31 | 136 | 136 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 20/0, 21/0 | 20/0, 21/0 |  | 21/0 | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 114/0-115/0 | ta505¦114/0¦115/0 | Jahangir Alam | 114/0 | 115/0 | 2026-05-22 | 2025-11-24 | 179 | 179 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 114/0, 115/0 | 114/0, 115/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 110A/0-111/0 | ta505¦110A/0¦111/0 | Alimuddin | 110A/0 | 111/0 | 2026-05-14 | 2025-09-30 | 226 | 226 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 110A/0, 111/0 | 110A/0, 111/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 110/0-110A/0 | ta505¦110/0¦110A/0 | Nasiruddin | 110/0 | 110A/0 | 2026-06-08 | 2026-01-31 | 128 | 128 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 110/0, 110A/0 | 110/0, 110A/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 112/0-113/0 | ta505¦112/0¦113/0 | Ram Singh | 112/0 | 113/0 | 2026-05-24 | 2026-01-19 | 125 | 125 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 112/0, 113/0 | 112/0, 113/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 126/0-127/0 | ta505¦126/0¦127/0 | Jahangir Alam | 126/0 | 127/0 | 2026-07-10 | 2025-11-16 | 236 | 236 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 126/0, 127/0 | 126/0, 127/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 127/0-128/0 | ta505¦127/0¦128/0 | Jahangir Alam | 127/0 | 128/0 | 2026-06-30 | 2025-10-12 | 261 | 261 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 127/0, 128/0 | 127/0, 128/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 108/0-109/0 | ta505¦108/0¦109/0 | Nasiruddin | 108/0 | 109/0 | 2026-06-24 | 2025-11-18 | 218 | 218 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 108/0, 109/0 | 108/0, 109/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 109/0-110/0 | ta505¦109/0¦110/0 | Nasiruddin | 109/0 | 110/0 | 2026-06-18 | 2026-01-31 | 138 | 138 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 109/0, 110/0 | 109/0, 110/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 115/0-116/0 | ta505¦115/0¦116/0 | Ram Singh | 115/0 | 116/0 | 2026-06-01 | 2025-10-13 | 231 | 231 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 115/0, 116/0 | 115/0, 116/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 105/0-106/0 | ta505¦105/0¦106/0 |  | 105/0 | 106/0 | 2026-07-09 | 2025-09-28 | 284 | 284 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 105/0, 106/0 | 105/0, 106/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 106/0-108/0 | ta505¦106/0¦108/0 | Nasiruddin | 106/0 | 108/0 | 2026-07-09 | 2025-08-22 | 321 | 321 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 106/0, 108/0 | 106/0, 108/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 117/0-118/0 | ta505¦117/0¦118/0 | Ram Singh | 117/0 | 118/0 | 2026-06-15 | 2026-05-28 | 18 | 18 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 117/0, 118/0 | 117/0, 118/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 175/0-176/0 | ta505¦175/0¦176/0 | Sk infra | 175/0 | 176/0 | 2026-07-18 | 2026-04-15 | 94 | 94 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 175/0, 176/0 | 175/0, 176/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 176/0-177/0 | ta505¦176/0¦177/0 | Sk infra | 176/0 | 177/0 | 2026-06-19 | 2026-04-26 | 54 | 54 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 176/0, 177/0 | 176/0, 177/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Unassigned | 177/0-178/0 | ta505¦177/0¦178/0 | Sk infra | 177/0 | 178/0 | 2026-07-01 | 2026-04-03 | 89 | 89 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 177/0, 178/0 | 177/0, 178/0 |  |  | FALSE
TA 505 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 116/0-117/0 | ta505¦116/0¦117/0 | Jahangir Alam | 116/0 | 117/0 | 2026-06-12 | 2026-05-28 | 15 | 15 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 116/0, 117/0 | 116/0, 117/0 |  |  | TRUE
TA 505 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 120/0-121/0 | ta505¦120/0¦121/0 | Jahangir Alam | 120/0 | 121/0 | 2026-06-23 | 2025-10-21 | 245 | 245 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 120/0, 121/0 | 120/0, 121/0 |  |  | TRUE
TA 505 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 119/0-120/0 | ta505¦119/0¦120/0 | Ram Singh | 119/0 | 120/0 | 2026-06-26 | 2025-09-18 | 281 | 281 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 119/0, 120/0 | 119/0, 120/0 |  |  | TRUE
TA 505 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 118/0-119/0 | ta505¦118/0¦119/0 | Ram Singh | 118/0 | 119/0 | 2026-06-21 | 2025-12-21 | 182 | 182 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 118/0, 119/0 | 118/0, 119/0 |  |  | TRUE
TA 505 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 99/0-100/0 | ta505¦99/0¦100/0 |  | 99/0 | 100/0 | 2026-07-16 | 2026-01-05 | 192 | 192 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 99/0, 100/0 | 100/0 | 99/0 |  | TRUE
TA 505 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 125/0-126/0 | ta505¦125/0¦126/0 |  | 125/0 | 126/0 | 2026-07-16 | 2026-01-31 | 166 | 166 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 125/0, 126/0 | 125/0, 126/0 |  |  | TRUE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 11/0-11/3 | ta506¦11/0¦11/3 | National Construction | 11/0 | 11/3 | 2026-04-03 | 2025-12-02 | 122 | 122 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 11/0, 11/3 | 11/0, 11/3 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 213/0-214/0 | ta506¦213/0¦214/0 | Bilkish Rehena | 213/0 | 214/0 | 2026-04-01 | 2025-10-16 | 167 | 167 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 213/0, 214/0 | 213/0, 214/0 |  |  | FALSE
TA 506 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 17/0-18/0 | ta506¦17/0¦18/0 | Jahangir Alam | 17/0 | 18/0 | 2026-04-06 | 2026-04-10 | -4 |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 17/0, 18/0 | 17/0, 18/0 |  |  | TRUE
TA 506 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 9/0-10/0 | ta506¦9/0¦10/0 | National Construction | 9/0 | 10/0 | 2026-04-09 | 2025-10-28 | 163 | 163 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 9/0, 10/0 | 9/0, 10/0 |  |  | TRUE
TA 506 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 139/0-139A/0 | ta506¦139/0¦139A/0 | Rejaul Sekh | 139/0 | 139A/0 | 2026-05-20 | 2025-12-31 | 140 | 140 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 139/0, 139A/0 | 139/0, 139A/0 |  |  | TRUE
TA 506 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 139A/0-140/0 | ta506¦139A/0¦140/0 | Rejaul Sekh | 139A/0 | 140/0 | 2026-05-16 | 2026-01-18 | 118 | 118 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 139A/0, 140/0 | 139A/0, 140/0 |  |  | TRUE
TA 506 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 212/0-213/0 | ta506¦212/0¦213/0 | Bilkish Rehena | 212/0 | 213/0 | 2026-04-13 | 2025-12-17 | 117 | 117 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 212/0, 213/0 | 212/0, 213/0 |  |  | TRUE
TA 506 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 12/0-13/0 | ta506¦12/0¦13/0 | National Construction | 12/0 | 13/0 | 2026-04-11 | 2025-11-04 | 158 | 158 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 12/0, 13/0 | 12/0, 13/0 |  |  | TRUE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 65/0-65A/0 | ta506¦65/0¦65A/0 | Taimoor Ali | 65/0 | 65A/0 | 2026-04-12 | 2025-10-27 | 167 | 167 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 65/0, 65A/0 | 65/0, 65A/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 65A/0-65A/3 | ta506¦65A/0¦65A/3 | Taimoor Ali | 65A/0 | 65A/3 | 2026-04-15 | 2025-12-02 | 134 | 134 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 65A/0, 65A/3 | 65A/0, 65A/3 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 15/0-16/0 | ta506¦15/0¦16/0 | Jahangir Alam | 15/0 | 16/0 | 2026-04-16 | 2025-11-13 | 154 | 154 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 15/0, 16/0 | 15/0, 16/0 |  |  | FALSE
TA 506 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 64/0-64A/0 | ta506¦64/0¦64A/0 | Taimoor Ali | 64/0 | 64A/0 | 2026-04-22 | 2025-12-29 | 114 | 114 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 64/0, 64A/0 | 64/0, 64A/0 |  |  | TRUE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 211/0-212/0 | ta506¦211/0¦212/0 | Bilkish Rehena | 211/0 | 212/0 | 2026-04-23 | 2026-02-11 | 71 | 71 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 211/0, 212/0 | 211/0, 212/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 63/0-64/0 | ta506¦63/0¦64/0 | Taimoor Ali | 63/0 | 64/0 | 2026-04-24 | 2025-12-16 | 129 | 129 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 63/0, 64/0 | 63/0, 64/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 13/0-14/0 | ta506¦13/0¦14/0 | National Construction | 13/0 | 14/0 | 2026-05-11 | 2026-04-14 | 27 | 27 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 13/0, 14/0 | 13/0, 14/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 64A/0-65/0 | ta506¦64A/0¦65/0 | Taimoor Ali | 64A/0 | 65/0 | 2026-05-13 | 2025-12-29 | 135 | 135 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 64A/0, 65/0 | 64A/0, 65/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 38/0-39/0 | ta506¦38/0¦39/0 | Jahangir Alam | 38/0 | 39/0 | 2026-05-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 38/0, 39/0 |  | 38/0, 39/0 |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 37/0-38/0 | ta506¦37/0¦38/0 | Jahangir Alam | 37/0 | 38/0 | 2026-05-29 | 2025-11-12 | 198 | 198 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 37/0, 38/0 | 37/0 | 38/0 |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 14/0-15/0 | ta506¦14/0¦15/0 | National Construction | 14/0 | 15/0 | 2026-06-08 | 2025-11-08 | 212 | 212 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 14/0, 15/0 | 14/0, 15/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 61/0-62/0 | ta506¦61/0¦62/0 | Taimoor Ali | 61/0 | 62/0 | 2026-06-10 | 2026-02-12 | 118 | 118 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 61/0, 62/0 | 61/0, 62/0 |  |  | FALSE
TA 506 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 140/0-141/0 | ta506¦140/0¦141/0 | Rejaul Sekh | 140/0 | 141/0 | 2026-06-10 | 2026-01-18 | 143 | 143 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 140/0, 141/0 | 140/0, 141/0 |  |  | TRUE
TA 506 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 16/0-17/0 | ta506¦16/0¦17/0 | National Construction | 16/0 | 17/0 | 2026-06-12 | 2026-04-10 | 63 | 63 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 16/0, 17/0 | 16/0, 17/0 |  |  | TRUE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 141/0-142/0 | ta506¦141/0¦142/0 | Rejaul Sekh | 141/0 | 142/0 | 2026-06-16 | 2025-10-14 | 245 | 245 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 141/0, 142/0 | 141/0, 142/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 60/0-61/0 | ta506¦60/0¦61/0 | Taimoor Ali | 60/0 | 61/0 | 2026-06-18 | 2026-02-12 | 126 | 126 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 60/0, 61/0 | 60/0, 61/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 210/0-211/0 | ta506¦210/0¦211/0 | National Construction | 210/0 | 211/0 | 2026-06-24 | 2026-05-18 | 37 | 37 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 210/0, 211/0 | 210/0, 211/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 223/0-224/0 | ta506¦223/0¦224/0 | Samirul Sekh | 223/0 | 224/0 | 2026-06-24 | 2025-10-10 | 257 | 257 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 223/0, 224/0 | 223/0, 224/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 138/0-139/0 | ta506¦138/0¦139/0 | Rejaul Sekh | 138/0 | 139/0 | 2026-06-28 | 2026-05-27 | 32 | 32 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 138/0, 139/0 | 138/0, 139/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 137/0-138/0 | ta506¦137/0¦138/0 | Rejaul Sekh | 137/0 | 138/0 | 2026-07-02 | 2026-06-17 | 15 | 15 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 137/0, 138/0 | 137/0, 138/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 40/0-41/0 | ta506¦40/0¦41/0 | Taimoor Ali | 40/0 | 41/0 | 2026-07-06 | 2026-06-18 | 18 | 18 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 40/0, 41/0 | 40/0 | 41/0 |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 39/0-40/0 | ta506¦39/0¦40/0 | Taimoor Ali | 39/0 | 40/0 | 2026-07-07 | 2026-06-18 | 19 | 19 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 39/0, 40/0 | 40/0 | 39/0 |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 200/0-201/0 | ta506¦200/0¦201/0 | National Construction | 200/0 | 201/0 | 2026-07-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 200/0, 201/0 |  | 200/0, 201/0 |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 187A/0-188/0 | ta506¦187A/0¦188/0 | Samirul Sekh | 187A/0 | 188/0 | 2026-07-11 | 2026-06-21 | 20 | 20 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 187A/0, 188/0 | 188/0 | 187A/0 |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 41/0-42/0 | ta506¦41/0¦42/0 | Taimoor Ali | 41/0 | 42/0 | 2026-07-14 | 2025-10-24 | 263 | 263 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 41/0, 42/0 | 42/0 | 41/0 |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 199/0-200/0 | ta506¦199/0¦200/0 | National Construction | 199/0 | 200/0 | 2026-07-17 | 2026-03-20 | 119 | 119 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 199/0, 200/0 |  | 199/0, 200/0 |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 187/0-187A/0 | ta506¦187/0¦187A/0 | Samirul Sekh | 187/0 | 187A/0 | 2026-07-23 | 2025-10-11 | 285 | 285 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 187/0, 187A/0 | 187/0 | 187A/0 |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 59/0-60/0 | ta506¦59/0¦60/0 | Taimoor Ali | 59/0 | 60/0 | 2026-07-26 | 2026-07-08 | 18 | 18 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 59/0, 60/0 | 59/0, 60/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 134/0-135/0 | ta506¦134/0¦135/0 | Rejaul Sekh | 134/0 | 135/0 | 2026-07-27 | 2026-02-25 | 152 | 152 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 134/0, 135/0 | 134/0, 135/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 25/0-26/0 | ta506¦25/0¦26/0 | MA Traders | 25/0 | 26/0 | 2026-08-01 | 2025-11-29 | 245 | 245 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 25/0, 26/0 | 25/0, 26/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 202/0-203/0 | ta506¦202/0¦203/0 | National Construction | 202/0 | 203/0 | 2026-08-04 | 2026-04-13 | 113 | 113 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 202/0, 203/0 | 203/0 | 202/0 |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 35/0-35A/0 | ta506¦35/0¦35A/0 | Afajal hossain | 35/0 | 35A/0 | 2026-08-04 | 2026-01-10 | 206 | 206 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 35/0, 35A/0 | 35A/0 | 35/0 |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 201/0-202/0 | ta506¦201/0¦202/0 | National Construction | 201/0 | 202/0 | 2026-08-06 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 201/0, 202/0 |  | 201/0, 202/0 |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 26/0-27/0 | ta506¦26/0¦27/0 | MA Traders | 26/0 | 27/0 | 2026-08-07 | 2025-11-23 | 257 | 257 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 26/0, 27/0 | 26/0, 27/0 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 135/0-135/2 | ta506¦135/0¦135/2 | Rejaul Sekh | 135/0 | 135/2 | 2026-08-07 | 2026-01-31 | 188 | 188 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 135/0, 135/2 | 135/0, 135/2 |  |  | FALSE
TA 506 |  |  |  |  | TA 506 | 5xx | TA |  | Unassigned | 36/0-37/0 | ta506¦36/0¦37/0 | Afajal hossain | 36/0 | 37/0 | 2026-08-09 | 2026-06-14 | 56 | 56 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 36/0, 37/0 | 36/0, 37/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 9/0-10/0 | tb408¦9/0¦10/0 | Gopal Associate, Hotline | 9/0 | 10/0 | 2026-04-03 | 2026-03-25 | 9 | 9 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 9/0, 10/0 | 9/0, 10/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 54/0-55/0 | tb408¦54/0¦55/0 | MC Power | 54/0 | 55/0 | 2026-04-03 | 2025-10-11 | 174 | 174 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 54/0, 55/0 | 54/0, 55/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 8/0-8/7 | tb408¦8/0¦8/7 | Devi Power | 8/0 | 8/7 | 2026-04-06 | 2026-03-07 | 30 | 30 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8/0, 8/7 | 8/0, 8/7 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 43/0-44/0 | tb408¦43/0¦44/0 | Krishna-1 | 43/0 | 44/0 | 2026-04-08 | 2025-12-10 | 119 | 119 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 43/0, 44/0 | 43/0, 44/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 5/0-6/0 | tb408¦5/0¦6/0 | Gopal Associate, Hotline | 5/0 | 6/0 | 2026-04-24 | 2025-12-07 | 138 | 138 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 5/0, 6/0 | 5/0, 6/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 14A/0-15/0 | tb408¦14A/0¦15/0 | Nasiruddin | 14A/0 | 15/0 | 2026-04-25 | 2026-03-31 | 25 | 25 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 14A/0, 15/0 | 14A/0, 15/0 |  |  | FALSE
TB 408 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 52/0-53/0 | tb408¦52/0¦53/0 | MC Power | 52/0 | 53/0 | 2026-05-10 | 2025-09-30 | 222 | 222 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 52/0, 53/0 | 52/0, 53/0 |  |  | TRUE
TB 408 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 11A/0-12/0 | tb408¦11A/0¦12/0 | Nasiruddin | 11A/0 | 12/0 | 2026-05-18 | 2026-03-16 | 63 | 63 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 11A/0, 12/0 | 11A/0, 12/0 |  |  | TRUE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 12/0-13/0 | tb408¦12/0¦13/0 | Gopal Associate, Hotline | 12/0 | 13/0 | 2026-05-26 | 2026-03-05 | 82 | 82 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 12/0, 13/0 | 12/0, 13/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 23/0-24/0 | tb408¦23/0¦24/0 | Gopal Associate, Hotline | 23/0 | 24/0 | 2026-06-09 | 2026-05-10 | 30 | 30 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 23/0, 24/0 | 23/0, 24/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 24/0-25/0 | tb408¦24/0¦25/0 | MC Power | 24/0 | 25/0 | 2026-06-21 | 2026-01-30 | 142 | 142 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 24/0, 25/0 | 24/0, 25/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 11/0-11A/0 | tb408¦11/0¦11A/0 | Nasiruddin | 11/0 | 11A/0 | 2026-06-17 | 2025-12-31 | 168 | 168 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 11/0, 11A/0 | 11/0, 11A/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 27/0-27/7 | tb408¦27/0¦27/7 | Mohammad Construction / Furkhan | 27/0 | 27/7 | 2026-06-22 | 2026-01-05 | 168 | 168 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 27/0, 27/7 | 27/0, 27/7 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 22/8-23/0 | tb408¦22/8¦23/0 | MC Power | 22/8 | 23/0 | 2026-06-30 | 2026-05-10 | 51 | 51 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 22/8, 23/0 | 22/8, 23/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 29/0-30/0 | tb408¦29/0¦30/0 | Jamera Bibi | 29/0 | 30/0 | 2026-06-23 | 2025-11-26 | 209 | 209 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 29/0, 30/0 | 29/0, 30/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 15/0-16/0 | tb408¦15/0¦16/0 | Nasiruddin | 15/0 | 16/0 | 2026-07-04 | 2026-03-31 | 95 | 95 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 15/0, 16/0 | 15/0, 16/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 4/0-5/0 | tb408¦4/0¦5/0 | Nasiruddin | 4/0 | 5/0 | 2026-07-17 | 2025-11-16 | 243 | 243 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/0, 5/0 | 4/0, 5/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 27/7-28/0 | tb408¦27/7¦28/0 | Mohammad Construction / Furkhan | 27/7 | 28/0 | 2026-07-11 | 2026-01-07 | 185 | 185 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 27/7, 28/0 | 27/7, 28/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 30/0-31/0 | tb408¦30/0¦31/0 | Jamera Bibi | 30/0 | 31/0 | 2026-07-11 | 2025-12-30 | 193 | 193 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 30/0, 31/0 | 30/0, 31/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 16/0-17/0 | tb408¦16/0¦17/0 | Nasiruddin | 16/0 | 17/0 | 2026-07-11 | 2024-11-14 | 604 | 604 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 16/0, 17/0 | 16/0, 17/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 28/0-29/0 | tb408¦28/0¦29/0 | Mohammad Construction / Furkhan | 28/0 | 29/0 | 2026-07-27 | 2026-01-08 | 200 | 200 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 28/0, 29/0 | 28/0, 29/0 |  |  | FALSE
TB 408 |  |  |  |  | TB 408 | 4xx | TB |  | Unassigned | 17/0-18/0 | tb408¦17/0¦18/0 | Nasiruddin | 17/0 | 18/0 | 2026-07-27 | 2025-08-25 | 336 | 336 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 17/0, 18/0 | 17/0, 18/0 |  |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 7/0-DB+0 | tb412¦7/0¦DB+0 | Rajeshwar | 7/0 | DB+0 | 2026-08-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 7/0, DB+0 |  | 7/0, DB+0 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 46/0-DD+3 | tb412¦46/0¦DD+3 | Nav Durga Traders | 46/0 | DD+3 | 2026-08-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 46/0, DD+3 |  | 46/0, DD+3 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 33/0-DD+0 | tb412¦33/0¦DD+0 | Rajeshwar | 33/0 | DD+0 | 2026-08-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 33/0, DD+0 |  | 33/0, DD+0 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 143/0-DC+3 | tb412¦143/0¦DC+3 | Anmol | 143/0 | DC+3 | 2026-07-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 143/0, DC+3 |  | 143/0, DC+3 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 74/0-DD+3 | tb412¦74/0¦DD+3 | Dharmendra Mishra | 74/0 | DD+3 | 2026-07-09 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 74/0, DD+3 |  | 74/0, DD+3 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 70/2-DA+3 1MRC | tb412¦70/2¦DA+3 1MRC | MAA | 70/2 | DA+3 1MRC | 2026-07-13 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 70/2, DA+31MRC |  | 70/2, DA+31MRC |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 61/2-DA+9 | tb412¦61/2¦DA+9 | Shakti | 61/2 | DA+9 | 2026-07-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 61/2, DA+9 |  | 61/2, DA+9 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 151/2-DA+6 | tb412¦151/2¦DA+6 | Sonakshi Mobile | 151/2 | DA+6 | 2026-08-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 151/2, DA+6 |  | 151/2, DA+6 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 106/0-DD+9 | tb412¦106/0¦DD+9 | Sanjeev Kumar | 106/0 | DD+9 | 2026-08-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 106/0, DD+9 |  | 106/0, DD+9 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 152/3-DA+6 | tb412¦152/3¦DA+6 | Sonakshi Mobile | 152/3 | DA+6 | 2026-08-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 152/3, DA+6 |  | 152/3, DA+6 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 104/5-DA+3 | tb412¦104/5¦DA+3 | Sanjeev Kumar | 104/5 | DA+3 | 2026-08-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 104/5, DA+3 |  | 104/5, DA+3 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 132/5-DA+3 | tb412¦132/5¦DA+3 | Asfak Ahmad | 132/5 | DA+3 | 2026-08-06 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 132/5, DA+3 |  | 132/5, DA+3 |  | FALSE
TB 412 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 104/3-DA+3 | tb412¦104/3¦DA+3 | Sanjeev Kumar | 104/3 | DA+3 | 2026-08-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 104/3, DA+3 |  | 104/3, DA+3 |  | TRUE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 104/4-DA+0 | tb412¦104/4¦DA+0 | Sanjeev Kumar | 104/4 | DA+0 | 2026-08-07 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 104/4, DA+0 |  | 104/4, DA+0 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 104/2-DA+6 | tb412¦104/2¦DA+6 | Sanjeev Kumar | 104/2 | DA+6 | 2026-08-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 104/2, DA+6 |  | 104/2, DA+6 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 150/0-DD+0 | tb412¦150/0¦DD+0 | Sonakshi Mobile | 150/0 | DD+0 | 2026-08-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 150/0, DD+0 |  | 150/0, DD+0 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 104/1-DA+3 | tb412¦104/1¦DA+3 | Sanjeev Kumar | 104/1 | DA+3 | 2026-08-09 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 104/1, DA+3 |  | 104/1, DA+3 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 3/0-2TNMD+0 | tb412¦3/0¦2TNMD+0 | Yashoda Devi | 3/0 | 2TNMD+0 | 2026-08-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 3/0, 2TNMD+0 |  | 3/0, 2TNMD+0 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 8/0-DD+0 | tb412¦8/0¦DD+0 | Rang | 8/0 | DD+0 | 2026-08-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 8/0, DD+0 |  | 8/0, DD+0 |  | FALSE
TB 412 |  |  |  |  | TB 412 | 4xx | TB |  | Unassigned | 132/3-DA+6 | tb412¦132/3¦DA+6 | Asfak Ahmad | 132/3 | DA+6 | 2026-08-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 132/3, DA+6 |  | 132/3, DA+6 |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | CPP-1/0 | tb501132kv¦CPP¦1/0 |  | CPP | 1/0 | 2026-06-29 | 2026-06-23 | 6 | 6 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | CPP, 1/0 | 1/0 | CPP |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 1/0-2/0 | tb501132kv¦1/0¦2/0 |  | 1/0 | 2/0 | 2026-06-29 | 2026-06-23 | 6 | 6 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 1/0, 2/0 | 1/0, 2/0 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 2/0-2/1 | tb501132kv¦2/0¦2/1 |  | 2/0 | 2/1 | 2026-06-27 | 2026-06-19 | 8 | 8 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 2/0, 2/1 | 2/0 | 2/1 |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 2/1-3/0 | tb501132kv¦2/1¦3/0 |  | 2/1 | 3/0 | 2026-06-27 | 2026-04-30 | 58 | 58 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 2/1, 3/0 | 3/0 | 2/1 |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 3/0-3/1 | tb501132kv¦3/0¦3/1 | Sammirul Sekh | 3/0 | 3/1 | 2026-05-07 | 2026-04-30 | 7 | 7 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 3/0, 3/1 | 3/0, 3/1 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 3/1-4/0 | tb501132kv¦3/1¦4/0 | Sammirul Sekh | 3/1 | 4/0 | 2026-05-07 | 2026-04-22 | 15 | 15 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 3/1, 4/0 | 3/1, 4/0 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 11/0-12/0 | tb501132kv¦11/0¦12/0 | Sammirul Sekh | 11/0 | 12/0 | 2026-05-10 | 2026-01-17 | 113 | 113 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 11/0, 12/0 | 11/0, 12/0 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 14/0-15/0 | tb501132kv¦14/0¦15/0 | Sammirul Sekh | 14/0 | 15/0 | 2026-05-14 | 2026-02-24 | 79 | 79 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 14/0, 15/0 | 14/0, 15/0 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 1B/0-1C/0 | tb501220kv¦1B/0¦1C/0 | National Construction | 1B/0 | 1C/0 | 2026-04-09 | 2026-03-25 | 15 | 15 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 1B/0, 1C/0 | 1B/0, 1C/0 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 1C/0-1D/0 | tb501220kv¦1C/0¦1D/0 | National Construction | 1C/0 | 1D/0 | 2026-04-11 | 2026-03-25 | 17 | 17 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 1C/0, 1D/0 | 1C/0, 1D/0 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 3/0-4/0 | tb501220kv¦3/0¦4/0 | National Construction | 3/0 | 4/0 | 2026-04-06 | 2025-05-30 | 311 | 311 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 3/0, 4/0 | 3/0, 4/0 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 4/6-4/7 | tb501220kv¦4/6¦4/7 |  | 4/6 | 4/7 | 2026-06-27 | 2026-01-23 | 155 | 155 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/6, 4/7 | 4/6, 4/7 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 4/7-4/8 | tb501220kv¦4/7¦4/8 |  | 4/7 | 4/8 | 2026-06-22 | 2026-01-23 | 150 | 150 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/7, 4/8 | 4/7, 4/8 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 4/8-4/9 | tb501220kv¦4/8¦4/9 |  | 4/8 | 4/9 | 2026-06-22 | 2025-12-24 | 180 | 180 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/8, 4/9 | 4/8, 4/9 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 31-32 | tb501220kv¦31¦32 | GKFS Enterprises | AP-31 | AP-32 | 2026-06-04 | 2025-07-16 | 323 | 323 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 31, 32 | 31, 32 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 32-33/0 | tb501220kv¦32¦33/0 |  | AP-32 | 33/0 | 2026-06-08 | 2025-07-16 | 327 | 327 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 32, 33/0 | 32 | 33/0 |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 33/0-34/0 | tb501220kv¦33/0¦34/0 | Ram singh | 33/0 | 34/0 | 2026-06-01 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 33/0, 34/0 |  | 33/0, 34/0 |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | Unassigned | 34/0-35/0 | tb501220kv¦34/0¦35/0 |  | 34/0 | 35/0 | 2026-06-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 34/0, 35/0 |  | 34/0, 35/0 |  | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 145/0-144/0 | tb507main¦145/0¦144/0 | Mahadev Enterprises | 145/0 | 144/0 | 2026-04-09 | 2025-11-17 | 143 | 143 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 145/0, 144/0 | 145/0, 144/0 |  | 144/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 113/0-112/0 | tb507main¦113/0¦112/0 | Mahadev Maan Construction | 113/0 | 112/0 | 2026-04-09 | 2026-01-17 | 82 | 82 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 113/0, 112/0 | 113/0, 112/0 |  | 113/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 153/0-152/0 | tb507main¦153/0¦152/0 | Mahadev Enterprises | 153/0 | 152/0 | 2026-04-16 | 2026-01-04 | 102 | 102 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 153/0, 152/0 | 153/0, 152/0 |  | 152/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 113A/0-113/0 | tb507main¦113A/0¦113/0 | Mahadev Maan Construction | 113A/0 | 113/0 | 2026-04-10 | 2026-01-17 | 83 | 83 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 113A/0, 113/0 | 113A/0, 113/0 |  | 113A/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 148/0-147/0 | tb507main¦148/0¦147/0 | Mahadev Enterprises | 148/0 | 147/0 | 2026-04-09 | 2025-11-21 | 139 | 139 | LOCATION_NOS | FALSE | OK |  | 11 | 11 | 0 | 148/0, 147/0, 147/1, 147/2, 147/3, 147/4, 147/5, 147/6, 147/7, 147/8, 147/9 | 148/0, 147/0, 147/1, 147/2, 147/3, 147/4, 147/5, 147/6, 147/7, 147/8, 147/9 |  | 147/0,1,2,3,4,5,6,7,8,9 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 151/0-150/0 | tb507main¦151/0¦150/0 | Mahadev Enterprises | 151/0 | 150/0 | 2026-04-27 | 2025-12-14 | 134 | 134 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 151/0, 150/0 | 151/0, 150/0 |  | 150/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 152/0-151/0 | tb507main¦152/0¦151/0 | Mahadev Enterprises | 152/0 | 151/0 | 2026-04-28 | 2025-12-14 | 135 | 135 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 152/0, 151/0 | 152/0, 151/0 |  | 151/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 134/0-133/0 | tb507main¦134/0¦133/0 | Mahadev Enterprises | 134/0 | 133/0 | 2026-04-29 | 2025-11-20 | 160 | 160 | LOCATION_NOS | FALSE | OK |  | 10 | 10 | 0 | 134/0, 133/0, 133/1, 133/2, 133/3, 133/4, 133/5, 133/6, 133/7, 133/8 | 134/0, 133/0, 133/1, 133/2, 133/3, 133/4, 133/5, 133/6, 133/7, 133/8 |  | 133/1,2,3,4,5,6,7,8 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 134/0-134A/0 | tb507main¦134/0¦134A/0 | SK Tajirul | 134/0 | 134A/0 | 2026-05-12 | 2025-10-29 | 195 | 195 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 134/0, 134A/0 | 134/0, 134A/0 |  |  | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 114/0-113A/0 | tb507main¦114/0¦113A/0 | SK Tajirul | 114/0 | 113A/0 | 2026-05-13 | 2026-01-24 | 109 | 109 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 114/0, 113A/0 | 114/0, 113A/0 |  |  | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 115/0-115/1 | tb507main¦115/0¦115/1 | SK Tajirul | 115/0 | 115/1 | 2026-05-25 | 2025-11-02 | 204 | 204 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 115/0, 115/1 | 115/0, 115/1 |  |  | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 75/0-76/0 | tb507main¦75/0¦76/0 | SK Tajirul | 75/0 | 76/0 | 2026-06-10 | 2025-10-31 | 222 | 222 | LOCATION_NOS | FALSE | OK |  | 9 | 9 | 0 | 75/0, 76/0, 75/1, 75/2, 75/3, 75/4, 75/5, 75/6, 75/7 | 75/0, 76/0, 75/1, 75/2, 75/3, 75/4, 75/5, 75/6, 75/7 |  | 75/1,2,3,4,5,6,7 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 76/0-77/0 | tb507main¦76/0¦77/0 | SK Tajirul | 76/0 | 77/0 | 2026-06-24 | 2025-11-05 | 231 | 231 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 76/0, 77/0, 76/1 | 76/0, 77/0, 76/1 |  | 76/1 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 132/0-133/0 | tb507main¦132/0¦133/0 | KP Group | 132/0 | 133/0 | 2026-07-19 | 2026-02-18 | 151 | 151 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 3.4 | 4 | 4 | 0 | 132/0, 133/0, 132/1, 132/2 | 132/0, 133/0, 132/1, 132/2 |  | 132/1,2,3.4 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 82/0-83/0 | tb507main¦82/0¦83/0 | SK Tajirul | 82/0 | 83/0 | 2026-08-09 | 2026-01-07 | 214 | 214 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 82/0, 83/0, 82/1, 82/2 | 82/0, 83/0, 82/1, 82/2 |  | 82/1,82/2 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 83/0-84/0 | tb507main¦83/0¦84/0 | SK Tajirul | 83/0 | 84/0 | 2026-07-16 | 2026-01-07 | 190 | 190 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 83/0, 84/0, 83/1 | 83/0, 84/0, 83/1 |  | 83/1 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 84/0-85/0 | tb507main¦84/0¦85/0 | SK Tajirul | 84/0 | 85/0 | 2026-07-09 | 2025-12-21 | 200 | 200 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 84/0, 85/0 | 84/0, 85/0 |  |  | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 85/0-86/0 | tb507main¦85/0¦86/0 | SK Tajirul | 85/0 | 86/0 | 2026-07-27 | 2025-12-31 | 208 | 208 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 85/0, 86/0, 85/1 | 85/0, 86/0, 85/1 |  | 85/1 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 134A/0-135/0 | tb507main¦134A/0¦135/0 | Mahadev Enterprises | 134A/0 | 135/0 | 2026-07-14 | 2025-11-25 | 231 | 231 | LOCATION_NOS | FALSE | OK |  | 6 | 6 | 0 | 134A/0, 135/0, 134A/1, 134A/2, 134A/3, 134A/4 | 134A/0, 135/0, 134A/1, 134A/2, 134A/3, 134A/4 |  | 134A/1,2,3,4 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 135/0-136/0 | tb507main¦135/0¦136/0 | Mahadev Enterprises | 135/0 | 136/0 | 2026-07-26 | 2025-11-30 | 238 | 238 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 135/0, 136/0, 135/1, 135/2, 135/3 | 135/0, 136/0, 135/1, 135/2, 135/3 |  | 135/1,2,3 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Unassigned | 136/0-137/0 | tb507main¦136/0¦137/0 | Mahadev Enterprises | 136/0 | 137/0 | 2026-07-18 | 2025-11-12 | 248 | 248 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 136/0, 137/0 | 136/0, 137/0 |  |  | FALSE
TB 605 |  |  |  |  | TB 605 | 6xx | TB |  | AP25-AP26 | 25-26 | tb605¦25¦26 | Tariq | AP25 | AP26 | 2026-06-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 25, 26 |  | 25, 26 |  | FALSE
TB 605 |  |  |  |  | TB 605 | 6xx | TB |  | AP26-AP27 | 26-27 | tb605¦26¦27 | Tariq | AP26 | AP27 | 2026-06-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 26, 27 |  | 26, 27 |  | FALSE
TB 605 |  |  |  |  | TB 605 | 6xx | TB |  | AP18-AP19 | 18-19 | tb605¦18¦19 | Janual Sheik | AP18 | AP19 | 2026-07-07 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 18, 19 |  | 18, 19 |  | FALSE
TB 605 |  |  |  |  | TB 605 | 6xx | TB |  | AP24-AP25 | 24-25 | tb605¦24¦25 | Tariq | AP24 | AP25 | 2026-06-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 24, 25 |  | 24, 25 |  | FALSE
TB 605 |  |  |  |  | TB 605 | 6xx | TB |  | AP20-AP21 | 20-21 | tb605¦20¦21 | Janual Sheik | AP20 | AP21 | 2026-07-01 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 20, 21 |  | 20, 21 |  | FALSE
TB 605 |  |  |  |  | TB 605 | 6xx | TB |  | AP27-AP28 | 27-28 | tb605¦27¦28 | Tariq | AP27 | AP28 | 2026-07-11 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 27, 28 |  | 27, 28 |  | FALSE
TB 605 |  |  |  |  | TB 605 | 6xx | TB |  | AP19-AP20 | 19-20 | tb605¦19¦20 | Janual Sheik | AP19 | AP20 | 2026-07-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 19, 20 |  | 19, 20 |  | FALSE
TB 605 |  |  |  |  | TB 605 | 6xx | TB |  | AP28-AP29 | 28-29 | tb605¦28¦29 | Tariq | AP28 | AP29 | 2026-07-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 28, 29 |  | 28, 29 |  | FALSE

## POFS Delay Summary
POFS Delay Summary
Scope Type | Scope Name | Method Split | Spans Considered | Spans With Computable Lag | Lag Coverage % | Average Lag Days | Median Lag Days | % Lag >15 Days | Negative Lag Excluded
OVERALL | All Projects | All | 224 | 208 | 92.9 | 10.3 | 3 | 16.8 | 59
OVERALL | All Projects | TSE | 130 | 120 | 92.3 | 10.3 | 3.5 | 13.2 | 14
OVERALL | All Projects | Others | 94 | 88 | 93.6 | 10.4 | 3 | 25.6 | 45
PROJECT | TA 413 | All | 24 | 23 | 95.8 | 5.1 | 1 | 9.1 | 12
PROJECT | TA 414 | All | 26 | 26 | 100 | 10 | 4 | 27.3 | 15
PROJECT | TA 416 | All | 16 | 16 | 100 | 12.4 | 3 | 23.1 | 3
PROJECT | TA 418 | All | 22 | 20 | 90.9 | 14.5 | 10 | 25 | 8
PROJECT | TA 419 | All | 2 | 1 | 50 | 1 | 1 | 0 | 0
PROJECT | TA 504 | All | 5 | 5 | 100 | 19 | 24 | 60 | 0
PROJECT | TA 505 | All | 19 | 19 | 100 | 3.8 | 3 | 0 | 7
PROJECT | TA 506 | All | 43 | 40 | 93 | 7.7 | 4 | 20 | 0
PROJECT | TB 408 | All | 26 | 26 | 100 | 6.2 | 3 | 6.7 | 11
PROJECT | TB 501 - 132kV | All | 8 | 4 | 50 | 0.5 | 0.5 | 0 | 0
PROJECT | TB 501 - 220kV | All | 10 | 10 | 100 | 4 | 1 | 10 | 0
PROJECT | TB 507 - MAIN | All | 15 | 10 | 66.7 | 49.5 | 3 | 12.5 | 2
PROJECT | TB 605 | All | 8 | 8 | 100 | 8.7 | 4 | 14.3 | 1
SERIES | 4xx | All | 116 | 112 | 96.6 | 9.4 | 4 | 17.5 | 49
SERIES | 5xx | All | 100 | 88 | 88 | 11.2 | 3 | 16.5 | 9
SERIES | 6xx | All | 8 | 8 | 100 | 8.7 | 4 | 14.3 | 1
CLIENT_TYPE | TA | All | 157 | 150 | 95.5 | 9 | 4 | 20 | 45
CLIENT_TYPE | TB | All | 67 | 58 | 86.6 | 13.5 | 2 | 9.1 | 14

## POFS Delay Coverage
POFS Delay Coverage
Scope Type | Scope Name | Method Split | Spans Considered | Spans With Computable Lag | Lag Coverage % | Negative Lag Excluded | Negative Gap Flag Rows | Missing PO Completion Rows | Missing FS Start Rows | Average Lag Days | Median Lag Days
OVERALL | All Projects | All | 224 | 208 | 92.9 | 59 | 59 | 0 | 16 | 10.3 | 3
OVERALL | All Projects | TSE | 130 | 120 | 92.3 | 14 | 14 | 0 | 10 | 10.3 | 3.5
OVERALL | All Projects | Others | 94 | 88 | 93.6 | 45 | 45 | 0 | 6 | 10.4 | 3
PROJECT | TA 413 | All | 24 | 23 | 95.8 | 12 | 12 | 0 | 1 | 5.1 | 1
PROJECT_METHOD | TA 413 | TSE | 11 | 10 | 90.9 | 0 | 0 | 0 | 1 | 5.6 | 1.5
PROJECT_METHOD | TA 413 | Others | 13 | 13 | 100 | 12 | 12 | 0 | 0 | 0 | 0
PROJECT | TA 414 | All | 26 | 26 | 100 | 15 | 15 | 0 | 0 | 10 | 4
PROJECT_METHOD | TA 414 | TSE | 11 | 11 | 100 | 3 | 3 | 0 | 0 | 10.2 | 5.5
PROJECT_METHOD | TA 414 | Others | 15 | 15 | 100 | 12 | 12 | 0 | 0 | 9.3 | 0
PROJECT | TA 416 | All | 16 | 16 | 100 | 3 | 3 | 0 | 0 | 12.4 | 3
PROJECT_METHOD | TA 416 | TSE | 7 | 7 | 100 | 1 | 1 | 0 | 0 | 16.8 | 6.5
PROJECT_METHOD | TA 416 | Others | 9 | 9 | 100 | 2 | 2 | 0 | 0 | 8.6 | 1
PROJECT | TA 418 | All | 22 | 20 | 90.9 | 8 | 8 | 0 | 2 | 14.5 | 10
PROJECT_METHOD | TA 418 | TSE | 12 | 10 | 83.3 | 2 | 2 | 0 | 2 | 7.2 | 7.5
PROJECT_METHOD | TA 418 | Others | 10 | 10 | 100 | 6 | 6 | 0 | 0 | 29 | 27.5
PROJECT | TA 419 | All | 2 | 1 | 50 | 0 | 0 | 0 | 1 | 1 | 1
PROJECT_METHOD | TA 419 | TSE | 1 | 1 | 100 | 0 | 0 | 0 | 0 | 1 | 1
PROJECT_METHOD | TA 419 | Others | 1 | 0 | 0 | 0 | 0 | 0 | 1
PROJECT | TA 504 | All | 5 | 5 | 100 | 0 | 0 | 0 | 0 | 19 | 24
PROJECT_METHOD | TA 504 | TSE | 4 | 4 | 100 | 0 | 0 | 0 | 0 | 17.2 | 15
PROJECT_METHOD | TA 504 | Others | 1 | 1 | 100 | 0 | 0 | 0 | 0 | 26 | 26
PROJECT | TA 505 | All | 19 | 19 | 100 | 7 | 7 | 0 | 0 | 3.8 | 3
PROJECT_METHOD | TA 505 | TSE | 13 | 13 | 100 | 1 | 1 | 0 | 0 | 3.8 | 3
PROJECT_METHOD | TA 505 | Others | 6 | 6 | 100 | 6 | 6 | 0 | 0
PROJECT | TA 506 | All | 43 | 40 | 93 | 0 | 0 | 0 | 3 | 7.7 | 4
PROJECT_METHOD | TA 506 | TSE | 23 | 22 | 95.7 | 0 | 0 | 0 | 1 | 7.6 | 4
PROJECT_METHOD | TA 506 | Others | 20 | 18 | 90 | 0 | 0 | 0 | 2 | 7.8 | 3
PROJECT | TB 408 | All | 26 | 26 | 100 | 11 | 11 | 0 | 0 | 6.2 | 3
PROJECT_METHOD | TB 408 | TSE | 20 | 20 | 100 | 5 | 5 | 0 | 0 | 6.2 | 3
PROJECT_METHOD | TB 408 | Others | 6 | 6 | 100 | 6 | 6 | 0 | 0
PROJECT | TB 501 - 132kV | All | 8 | 4 | 50 | 0 | 0 | 0 | 4 | 0.5 | 0.5
PROJECT_METHOD | TB 501 - 132kV | TSE | 8 | 4 | 50 | 0 | 0 | 0 | 4 | 0.5 | 0.5
PROJECT_METHOD | TB 501 - 132kV | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TB 501 - 220kV | All | 10 | 10 | 100 | 0 | 0 | 0 | 0 | 4 | 1
PROJECT_METHOD | TB 501 - 220kV | TSE | 10 | 10 | 100 | 0 | 0 | 0 | 0 | 4 | 1
PROJECT_METHOD | TB 501 - 220kV | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TB 507 - MAIN | All | 15 | 10 | 66.7 | 2 | 2 | 0 | 5 | 49.5 | 3
PROJECT_METHOD | TB 507 - MAIN | TSE | 7 | 5 | 71.4 | 2 | 2 | 0 | 2 | 123.7 | 4
PROJECT_METHOD | TB 507 - MAIN | Others | 8 | 5 | 62.5 | 0 | 0 | 0 | 3 | 5 | 2
PROJECT | TB 605 | All | 8 | 8 | 100 | 1 | 1 | 0 | 0 | 8.7 | 4
PROJECT_METHOD | TB 605 | TSE | 3 | 3 | 100 | 0 | 0 | 0 | 0 | 3.3 | 4
PROJECT_METHOD | TB 605 | Others | 5 | 5 | 100 | 1 | 1 | 0 | 0 | 12.8 | 9
SERIES | 4xx | All | 116 | 112 | 96.6 | 49 | 49 | 0 | 4 | 9.4 | 4
SERIES | 5xx | All | 100 | 88 | 88 | 9 | 9 | 0 | 12 | 11.2 | 3
SERIES | 6xx | All | 8 | 8 | 100 | 1 | 1 | 0 | 0 | 8.7 | 4
CLIENT_TYPE | TA | All | 157 | 150 | 95.5 | 45 | 45 | 0 | 7 | 9 | 4
CLIENT_TYPE | TB | All | 67 | 58 | 86.6 | 14 | 14 | 0 | 9 | 13.5 | 2

## POFS Delay Anomalies
POFS Delay Anomalies
Project | Project Scope Key | Series | Client Type | Method Split | Span Key | From AP | To AP | PO Completion Date | FS Starting Date | Gap Days | Issue | Negative Gap Flag
TA 413 | ta413 | 4xx | TA | Others | ta413¦14/0¦15/0 | 14/0 | 15/0 | 2026-06-12 | 2026-06-07 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | Others | ta413¦13/0¦13A/0 | 13/0 | 13A/0 | 2026-06-23 | 2026-06-19 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | Others | ta413¦13A/0¦14/0 | 13A/0 | 14/0 | 2026-06-23 | 2026-06-19 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | Others | ta413¦24/0¦25/0 | 24/0 | 25/0 | 2026-06-26 | 2026-06-22 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | Others | ta413¦23A/0¦24/0 | 23A/0 | 24/0 | 2026-06-26 | 2026-06-22 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | Others | ta413¦28/0¦29/0 | 28/0 | 29/0 | 2026-07-02 | 2026-07-01 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | Others | ta413¦23/0¦23A/0 | 23/0 | 23A/0 | 2026-07-04 | 2026-07-01 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | Others | ta413¦36/0¦36A/0 | 36/0 | 36A/0 | 2026-07-11 | 2026-07-09 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | Others | ta413¦25/0¦26/0 | 25/0 | 26/0 | 2026-07-16 | 2026-07-14 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | Others | ta413¦22/0¦23/0 | 22/0 | 23/0 | 2026-07-28 | 2026-07-27 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | Others | ta413¦26/0¦27/0 | 26/0 | 27/0 | 2026-08-07 | 2026-08-01 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | Others | ta413¦12/0¦13/0 | 12/0 | 13/0 | 2026-08-08 | 2026-08-07 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | TSE | ta413¦43A/0¦44/0 | 43A/0 | 44/0 | 2026-08-04 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦118/0¦119/0 | 118/0 | 119/0 | 2026-05-29 | 2026-05-23 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦143/0¦144/0 | 143/0 | 144/0 | 2026-06-13 | 2026-06-08 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦175/0¦175/1 | 175/0 | 175/1 | 2026-05-07 | 2026-05-03 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦175/1¦176/0 | 175/1 | 176/0 | 2026-04-12 | 2026-04-07 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦176/0¦177/0 | 176/0 | 177/0 | 2026-04-27 | 2026-04-24 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦178/0¦179/0 | 178/0 | 179/0 | 2026-05-26 | 2026-05-17 | -9 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦182/0¦183/0 | 182/0 | 183/0 | 2026-04-11 | 2026-04-05 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦183/0¦184/0 | 183/0 | 184/0 | 2026-04-21 | 2026-04-20 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦184/0¦185/0 | 184/0 | 185/0 | 2026-05-13 | 2026-05-06 | -7 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦185/0¦186/0 | 185/0 | 186/0 | 2026-05-31 | 2026-05-24 | -7 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦186/0¦187/0 | 186/0 | 187/0 | 2026-06-12 | 2026-06-05 | -7 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦190/0¦191/0 | 190/0 | 191/0 | 2026-06-01 | 2026-05-28 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦198/0¦199/0 | 198/0 | 199/0 | 2026-04-23 | 2026-04-17 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦221/0¦222/0 | 221/0 | 222/0 | 2026-06-25 | 2026-06-19 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦222/0¦223/0 | 222/0 | 223/0 | 2026-06-25 | 2026-06-19 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 416 | ta416 | 4xx | TA | Others | ta416¦47/0¦48/0 | AP47/0 | AP48/0 | 2026-05-25 | 2026-05-21 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 416 | ta416 | 4xx | TA | Others | ta416¦49/0¦50/0 | AP49/0 | AP50/0 | 2026-06-15 | 2026-06-14 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 416 | ta416 | 4xx | TA | TSE | ta416¦50/0¦51/0 | AP50/0 | AP51/0 | 2026-07-10 | 2026-07-06 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦46¦46/7 | AP46 | 46/7 | 2026-07-21 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦47/0¦48 | AP47/0 | AP48 | 2026-07-12 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | Others | ta418¦49/0¦50 | 49/0 | AP50 | 2026-07-12 | 2026-07-09 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | Others | ta418¦50¦51 | AP50 | AP51 | 2026-07-12 | 2026-07-09 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | Others | ta418¦53¦54 | AP53 | AP54 | 2026-06-20 | 2026-06-15 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦55¦56 | AP55 | AP56 | 2026-05-03 | 2026-05-02 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | Others | ta418¦56/3¦57/0 | 56/3 | 57/0 | 2026-06-09 | 2026-06-05 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | Others | ta418¦58/0¦59/0 | 58/0 | 59/0 | 2026-06-28 | 2026-06-24 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦60/0¦61/0 | 60/0 | 61/0 | 2026-07-04 | 2026-07-02 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | Others | ta418¦63/0¦GNTY | 63/0 | GNTY | 2026-04-18 | 2026-04-16 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 419 | ta419 | 4xx | TA | Others | ta419¦1/0¦2/0 | 1/0 | 2/0 | 2026-07-28 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | Others | ta505¦112/0¦113/0 | 112/0 | 113/0 | 2026-05-30 | 2026-05-24 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 505 | ta505 | 5xx | TA | Others | ta505¦115/0¦116/0 | 115/0 | 116/0 | 2026-06-12 | 2026-06-01 | -11 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 505 | ta505 | 5xx | TA | Others | ta505¦106/0¦108/0 | 106/0 | 108/0 | 2026-07-11 | 2026-07-09 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 505 | ta505 | 5xx | TA | Others | ta505¦117/0¦118/0 | 117/0 | 118/0 | 2026-06-19 | 2026-06-15 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 505 | ta505 | 5xx | TA | TSE | ta505¦120/0¦121/0 | 120/0 | 121/0 | 2026-06-26 | 2026-06-24 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 505 | ta505 | 5xx | TA | Others | ta505¦119/0¦120/0 | 119/0 | 120/0 | 2026-06-30 | 2026-06-26 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 505 | ta505 | 5xx | TA | Others | ta505¦118/0¦119/0 | 118/0 | 119/0 | 2026-07-02 | 2026-06-21 | -11 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 506 | ta506 | 5xx | TA | Others | ta506¦35/0¦35A/0 | 35/0 | 35A/0 | 2026-08-05 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 506 | ta506 | 5xx | TA | Others | ta506¦26/0¦27/0 | 26/0 | 27/0 | 2026-08-07 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 506 | ta506 | 5xx | TA | TSE | ta506¦36/0¦37/0 | 36/0 | 37/0 | 2026-08-11 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 408 | tb408 | 4xx | TB | Others | tb408¦14/0¦14A/0 | 14/0 | 14A/0 | 2026-04-06 | 2026-04-05 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 408 | tb408 | 4xx | TB | Others | tb408¦9/0¦10/0 | 9/0 | 10/0 | 2026-04-09 | 2026-04-03 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 408 | tb408 | 4xx | TB | TSE | tb408¦54/0¦55/0 | 54/0 | 55/0 | 2026-04-09 | 2026-04-08 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 408 | tb408 | 4xx | TB | TSE | tb408¦8/0¦8/7 | 8/0 | 8/7 | 2026-04-09 | 2026-04-08 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 408 | tb408 | 4xx | TB | TSE | tb408¦6/0¦7/0 | 6/0 | 7/0 | 2026-04-15 | 2026-03-24 | -22 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 408 | tb408 | 4xx | TB | Others | tb408¦5/0¦6/0 | 5/0 | 6/0 | 2026-04-30 | 2026-04-24 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 408 | tb408 | 4xx | TB | TSE | tb408¦14A/0¦15/0 | 14A/0 | 15/0 | 2026-05-04 | 2026-05-02 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 408 | tb408 | 4xx | TB | Others | tb408¦12/0¦13/0 | 12/0 | 13/0 | 2026-05-31 | 2026-05-26 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 408 | tb408 | 4xx | TB | Others | tb408¦23/0¦24/0 | 23/0 | 24/0 | 2026-06-16 | 2026-06-09 | -7 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 408 | tb408 | 4xx | TB | Others | tb408¦24/0¦25/0 | 24/0 | 25/0 | 2026-06-26 | 2026-06-21 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 408 | tb408 | 4xx | TB | TSE | tb408¦22/0¦22/8 | 22/0 | 22/8 | 2026-07-26 | 2026-07-23 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦CPP¦1/0 | CPP | 1/0 | 2026-06-29 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦1/0¦2/0 | 1/0 | 2/0 | 2026-06-29 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦2/0¦2/1 | 2/0 | 2/1 | 2026-06-28 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦2/1¦3/0 | 2/1 | 3/0 | 2026-06-28 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | tb507main¦144/0¦143/0 | 144/0 | 143/0 | 2026-04-04 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | Others | tb507main¦113/0¦112/0 | 113/0 | 112/0 | 2026-04-10 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | Others | tb507main¦113A/0¦113/0 | 113A/0 | 113/0 | 2026-04-10 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | tb507main¦148/0¦147/0 | 148/0 | 147/0 | 2026-04-20 | 2026-04-19 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | tb507main¦134/0¦133/0 | 134/0 | 133/0 | 2026-05-13 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | tb507main¦135/0¦136/0 | 135/0 | 136/0 | 2026-07-30 | 2026-07-27 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 507 - MAIN | tb507main | 5xx | TB | Others | tb507main¦136/0¦137/0 | 136/0 | 137/0 | 2026-07-21 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 605 | tb605 | 6xx | TB | Others | tb605¦24¦25 | AP24 | AP25 | 2026-07-05 | 2026-07-04 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE

## POFS Delay Detail
POFS Delay Detail
Project | Project Code | Project Display | Project Scope Key | Join Project Key | Base Project Code | Series | Client Type | Method Split | Section | Span | Span Key | Gang Name | From AP | To AP | PO Completion Date | FS Starting Date | Gap Days | Gap Days Non-Negative | Negative Gap Flag | Has PO Completion Date | Has FS Starting Date
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 9/0-10/0 | ta413¦9/0¦10/0 |  | 9/0 | 10/0 | 2026-04-02 | 2026-04-06 | 4 | 4 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 29A/0-30/0 | ta413¦29A/0¦30/0 |  | 29A/0 | 30/0 | 2026-04-28 | 2026-04-30 | 2 | 2 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 10/0-11/0 | ta413¦10/0¦11/0 |  | 10/0 | 11/0 | 2026-04-09 | 2026-05-12 | 33 | 33 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 29/0-29A/0 | ta413¦29/0¦29A/0 |  | 29/0 | 29A/0 | 2026-05-12 | 2026-05-13 | 1 | 1 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 27/0-28/0 | ta413¦27/0¦28/0 |  | 27/0 | 28/0 | 2026-05-23 | 2026-05-24 | 1 | 1 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 11/0-12/0 | ta413¦11/0¦12/0 |  | 11/0 | 12/0 | 2026-06-05 | 2026-06-05 | 0 | 0 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 14/0-15/0 | ta413¦14/0¦15/0 |  | 14/0 | 15/0 | 2026-06-12 | 2026-06-07 | -5 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 13/0-13A/0 | ta413¦13/0¦13A/0 |  | 13/0 | 13A/0 | 2026-06-23 | 2026-06-19 | -4 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 13A/0-14/0 | ta413¦13A/0¦14/0 |  | 13A/0 | 14/0 | 2026-06-23 | 2026-06-19 | -4 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 18/0-19/0 | ta413¦18/0¦19/0 |  | 18/0 | 19/0 | 2026-06-18 | 2026-06-25 | 7 | 7 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 35/0-36/0 | ta413¦35/0¦36/0 |  | 35/0 | 36/0 | 2026-06-26 | 2026-06-26 | 0 | 0 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 24/0-25/0 | ta413¦24/0¦25/0 |  | 24/0 | 25/0 | 2026-06-26 | 2026-06-22 | -4 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 23A/0-24/0 | ta413¦23A/0¦24/0 |  | 23A/0 | 24/0 | 2026-06-26 | 2026-06-22 | -4 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 28/0-29/0 | ta413¦28/0¦29/0 |  | 28/0 | 29/0 | 2026-07-02 | 2026-07-01 | -1 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 23/0-23A/0 | ta413¦23/0¦23A/0 |  | 23/0 | 23A/0 | 2026-07-04 | 2026-07-01 | -3 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 36/0-36A/0 | ta413¦36/0¦36A/0 |  | 36/0 | 36A/0 | 2026-07-11 | 2026-07-09 | -2 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 25/0-26/0 | ta413¦25/0¦26/0 |  | 25/0 | 26/0 | 2026-07-16 | 2026-07-14 | -2 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 15/0-16/0 | ta413¦15/0¦16/0 |  | 15/0 | 16/0 | 2026-07-17 | 2026-07-17 | 0 | 0 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 40/0-40A/0 | ta413¦40/0¦40A/0 |  | 40/0 | 40A/0 | 2026-07-22 | 2026-07-23 | 1 | 1 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 22/0-23/0 | ta413¦22/0¦23/0 |  | 22/0 | 23/0 | 2026-07-28 | 2026-07-27 | -1 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 20/0-21/0 | ta413¦20/0¦21/0 |  | 20/0 | 21/0 | 2026-07-29 | 2026-08-05 | 7 | 7 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 26/0-27/0 | ta413¦26/0¦27/0 |  | 26/0 | 27/0 | 2026-08-07 | 2026-08-01 | -6 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 12/0-13/0 | ta413¦12/0¦13/0 |  | 12/0 | 13/0 | 2026-08-08 | 2026-08-07 | -1 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 43A/0-44/0 | ta413¦43A/0¦44/0 |  | 43A/0 | 44/0 | 2026-08-04 |  |  |  | FALSE | TRUE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 118/0-119/0 | ta414¦118/0¦119/0 | Dharmendra | 118/0 | 119/0 | 2026-05-29 | 2026-05-23 | -6 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 119/0-120/0 | ta414¦119/0¦120/0 | Enamul Haque | 119/0 | 120/0 | 2026-05-18 | 2026-05-29 | 11 | 11 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 120/0-121/0 | ta414¦120/0¦121/0 | Enamul Haque | 120/0 | 121/0 | 2026-05-08 | 2026-05-10 | 2 | 2 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 121/1-121/7 | ta414¦121/1¦121/7 | Enamul Haque | 121/1 | 121/7 | 2026-04-16 | 2026-05-19 | 33 | 33 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 124/0-125/0 | ta414¦124/0¦125/0 | Enamul Haque | 124/0 | 125/0 | 2026-06-13 | 2026-06-16 | 3 | 3 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 126/0-127/0 | ta414¦126/0¦127/0 | Enamul Haque | 126/0 | 127/0 | 2026-05-27 | 2026-06-03 | 7 | 7 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 143/0-144/0 | ta414¦143/0¦144/0 |  | 143/0 | 144/0 | 2026-06-13 | 2026-06-08 | -5 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 148/0-148/5 | ta414¦148/0¦148/5 |  | 148/0 | 148/5 | 2026-06-22 | 2026-06-26 | 4 | 4 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 174/0-175/0 | ta414¦174/0¦175/0 | Alam Construction | 174/0 | 175/0 | 2026-05-09 | 2026-05-30 | 21 | 21 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 175/0-175/1 | ta414¦175/0¦175/1 | Alam Construction | 175/0 | 175/1 | 2026-05-07 | 2026-05-03 | -4 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 175/1-176/0 | ta414¦175/1¦176/0 | Maa Singhvahini | 175/1 | 176/0 | 2026-04-12 | 2026-04-07 | -5 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 176/0-177/0 | ta414¦176/0¦177/0 | Alam Construction | 176/0 | 177/0 | 2026-04-27 | 2026-04-24 | -3 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 177/0-178/0 | ta414¦177/0¦178/0 | Sanjay singh 2 | 177/0 | 178/0 | 2026-05-20 | 2026-05-20 | 0 | 0 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 178/0-179/0 | ta414¦178/0¦179/0 |  | 178/0 | 179/0 | 2026-05-26 | 2026-05-17 | -9 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 180/2-182/0 | ta414¦180/2¦182/0 | Alam Construction | 180/2 | 182/0 | 2026-04-13 | 2026-04-14 | 1 | 1 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 182/0-183/0 | ta414¦182/0¦183/0 | Sanjay Singh | 182/0 | 183/0 | 2026-04-11 | 2026-04-05 | -6 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Unassigned | 183/0-184/0 | ta414¦183/0¦184/0 | Alam Construction | 183/0 | 184/0 | 2026-04-21 | 2026-04-20 | -1 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 184/0-185/0 | ta414¦184/0¦185/0 | Sanjay Singh 1 | 184/0 | 185/0 | 2026-05-13 | 2026-05-06 | -7 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 185/0-186/0 | ta414¦185/0¦186/0 | Sanjay Singh 2 | 185/0 | 186/0 | 2026-05-31 | 2026-05-24 | -7 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 186/0-187/0 | ta414¦186/0¦187/0 |  | 186/0 | 187/0 | 2026-06-12 | 2026-06-05 | -7 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 190/0-191/0 | ta414¦190/0¦191/0 |  | 190/0 | 191/0 | 2026-06-01 | 2026-05-28 | -4 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 197/0-198/0 | ta414¦197/0¦198/0 | Abdul adut | 197/0 | 198/0 | 2026-06-01 | 2026-06-29 | 28 | 28 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 198/0-199/0 | ta414¦198/0¦199/0 |  | 198/0 | 199/0 | 2026-04-23 | 2026-04-17 | -6 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 221/0-222/0 | ta414¦221/0¦222/0 | Sanjay Singh 1 | 221/0 | 222/0 | 2026-06-25 | 2026-06-19 | -6 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 222/0-223/0 | ta414¦222/0¦223/0 | Sanjay Singh 2 | 222/0 | 223/0 | 2026-06-25 | 2026-06-19 | -6 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Unassigned | 245/0-246/0 | ta414¦245/0¦246/0 | Bhola prasad+ Deepak Sarkar | 245/0 | 246/0 | 2026-04-14 | 2026-04-14 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 62/0-63/0 | ta416¦62/0¦63/0 | Khosibur Ali(Company) | AP62/0 | AP63/0 | 2026-04-15 | 2026-04-15 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 54/0-55/0 | ta416¦54/0¦55/0 | Jahangir(Company) | AP54/0 | AP55/0 | 2026-04-06 | 2026-04-08 | 2 | 2 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 61/0-62/0 | ta416¦61/0¦62/0 | (Kunal Hot line | AP61/0 | AP62/0 | 2026-04-20 | 2026-06-11 | 52 | 52 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 64/0-65/0 | ta416¦64/0¦65/0 | Astharul (company) | AP64/0 | AP65/0 | 2026-04-17 | 2026-06-07 | 51 | 51 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 55/0-56/0 | ta416¦55/0¦56/0 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 2026-04-14 | 2026-05-16 | 32 | 32 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 47/0-48/0 | ta416¦47/0¦48/0 | Kunal Hot line | AP47/0 | AP48/0 | 2026-05-25 | 2026-05-21 | -4 |  | TRUE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 56/0-57/0 | ta416¦56/0¦57/0 | ANARUL ISLAM | AP56/0 | AP57/0 | 2026-05-14 | 2026-05-19 | 5 | 5 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 57/0-58/0 | ta416¦57/0¦58/0 | ANARUL ISLAM | AP57/0 | AP58/0 | 2026-05-18 | 2026-05-26 | 8 | 8 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 59/0-60/0 | ta416¦59/0¦60/0 | RK Enterprise | AP59/0 | AP60/0 | 2026-06-05 | 2026-06-11 | 6 | 6 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 63/0-64/0 | ta416¦63/0¦64/0 | ANARUL ISLAM | AP63/0 | AP64/0 | 2026-06-02 | 2026-06-03 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 58/0-59/0 | ta416¦58/0¦59/0 | Dharmendra Hot line | AP58/0 | AP59/0 | 2026-06-03 | 2026-06-03 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 51/0-52/0 | ta416¦51/0¦52/0 | Kunal Hot line | AP51/0 | AP52/0 | 2026-06-03 | 2026-06-03 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 48/0-49/0 | ta416¦48/0¦49/0 | ANARUL ISLAM | AP48/0 | AP49/0 | 2026-06-15 | 2026-06-18 | 3 | 3 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 49/0-50/0 | ta416¦49/0¦50/0 | Dharmendra Hot line | AP49/0 | AP50/0 | 2026-06-15 | 2026-06-14 | -1 |  | TRUE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 60/0-61/0 | ta416¦60/0¦61/0 | ANARUL ISLAM | AP60/0 | AP61/0 | 2026-06-13 | 2026-06-14 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 50/0-51/0 | ta416¦50/0¦51/0 | SADIK Con(company) | AP50/0 | AP51/0 | 2026-07-10 | 2026-07-06 | -4 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Unassigned | 36/1-37/0 | ta418¦36/1¦37/0 | Dharmendar | 36/1 | 37/0 | 2026-05-29 | 2026-05-29 | 0 | 0 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | 37/0-38 | ta418¦37/0¦38 | SUFIYAN | 37/0 | AP38 | 2026-05-12 | 2026-05-22 | 10 | 10 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | 38-39 | ta418¦38¦39 | SUFIYAN | AP38 | AP39 | 2026-05-26 | 2026-05-30 | 4 | 4 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | 46-46/7 | ta418¦46¦46/7 |  | AP46 | 46/7 | 2026-07-21 |  |  |  | FALSE | TRUE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | 47/0-48 | ta418¦47/0¦48 |  | AP47/0 | AP48 | 2026-07-12 |  |  |  | FALSE | TRUE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | 48-48A/0 | ta418¦48¦48A/0 |  | AP48 | 48A/0 | 2026-07-05 | 2026-07-15 | 10 | 10 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | 48A/0-49/0 | ta418¦48A/0¦49/0 |  | 48A/0 | 49/0 | 2026-06-26 | 2026-07-09 | 13 | 13 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Unassigned | 49/0-50 | ta418¦49/0¦50 |  | 49/0 | AP50 | 2026-07-12 | 2026-07-09 | -3 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Unassigned | 50-51 | ta418¦50¦51 |  | AP50 | AP51 | 2026-07-12 | 2026-07-09 | -3 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Unassigned | 51-52 | ta418¦51¦52 | M/s Akram | AP51 | AP52 | 2026-06-06 | 2026-07-09 | 33 | 33 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | 52-53 | ta418¦52¦53 | M/s Ranveer | AP52 | AP53 | 2026-06-05 | 2026-06-15 | 10 | 10 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Unassigned | 53-54 | ta418¦53¦54 |  | AP53 | AP54 | 2026-06-20 | 2026-06-15 | -5 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | 54-55 | ta418¦54¦55 | M/s Akram | AP54 | AP55 | 2026-06-19 | 2026-06-24 | 5 | 5 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | 55-56 | ta418¦55¦56 | SUFIYAN | AP55 | AP56 | 2026-05-03 | 2026-05-02 | -1 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Unassigned | 56/3-57/0 | ta418¦56/3¦57/0 | M/s Dharmander | 56/3 | 57/0 | 2026-06-09 | 2026-06-05 | -4 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | 57/0-58/0 | ta418¦57/0¦58/0 | M/s Kamrudhin | 57/0 | 58/0 | 2026-06-23 | 2026-06-24 | 1 | 1 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Unassigned | 58/0-59/0 | ta418¦58/0¦59/0 |  | 58/0 | 59/0 | 2026-06-28 | 2026-06-24 | -4 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | 59/0-60/0 | ta418¦59/0¦60/0 |  | 59/0 | 60/0 | 2026-06-27 | 2026-07-02 | 5 | 5 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | 60/0-61/0 | ta418¦60/0¦61/0 |  | 60/0 | 61/0 | 2026-07-04 | 2026-07-02 | -2 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Unassigned | 61/0-62/0 | ta418¦61/0¦62/0 | M/s Kamrudhin | 61/0 | 62/0 | 2026-04-15 | 2026-06-15 | 61 | 61 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Unassigned | 62/0-63/0 | ta418¦62/0¦63/0 | M/s Kamrudhin | 62/0 | 63/0 | 2026-05-24 | 2026-06-15 | 22 | 22 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Unassigned | 63/0-GNTY | ta418¦63/0¦GNTY | M/s Kamrudhin | 63/0 | GNTY | 2026-04-18 | 2026-04-16 | -2 |  | TRUE | TRUE | TRUE
TA 419 | TA 419 | TA 419 | ta419 | ta419 | TA 419 | 4xx | TA | TSE | TSE 1 | 0D/0-0D/5 | ta419¦0D/0¦0D/5 | Saheb Enterprises | 0D/0 | 0D/5 | 2026-06-18 | 2026-06-19 | 1 | 1 | FALSE | TRUE | TRUE
TA 419 | TA 419 | TA 419 | ta419 | ta419 | TA 419 | 4xx | TA | Others | Manual 2 | 1/0-2/0 | ta419¦1/0¦2/0 | Enamul | 1/0 | 2/0 | 2026-07-28 |  |  |  | FALSE | TRUE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 11/0-12/0 | ta504¦11/0¦12/0 | Tanjira Bibi | 11/0 | 12/0 | 2026-05-12 | 2026-06-18 | 37 | 37 | FALSE | TRUE | TRUE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 12/0-13/0 | ta504¦12/0¦13/0 | Tanjira Bibi | 12/0 | 13/0 | 2026-05-20 | 2026-06-13 | 24 | 24 | FALSE | TRUE | TRUE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 16/0-16/3 | ta504¦16/0¦16/3 | Lamba Construction | 16/0 | 16/3 | 2026-04-04 | 2026-04-06 | 2 | 2 | FALSE | TRUE | TRUE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 19/0-20/0 | ta504¦19/0¦20/0 | Lamba Construction | 19/0 | 20/0 | 2026-05-27 | 2026-06-02 | 6 | 6 | FALSE | TRUE | TRUE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 20/0-21/0 | ta504¦20/0¦21/0 | Lamba Construction | 20/0 | 21/0 | 2026-05-17 | 2026-06-12 | 26 | 26 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 114/0-115/0 | ta505¦114/0¦115/0 | Jahangir Alam | 114/0 | 115/0 | 2026-06-05 | 2026-06-06 | 1 | 1 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 110A/0-111/0 | ta505¦110A/0¦111/0 | Alimuddin | 110A/0 | 111/0 | 2026-05-18 | 2026-05-25 | 7 | 7 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 110/0-110A/0 | ta505¦110/0¦110A/0 | Nasiruddin | 110/0 | 110A/0 | 2026-06-12 | 2026-06-13 | 1 | 1 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | Others | Unassigned | 112/0-113/0 | ta505¦112/0¦113/0 | Ram Singh | 112/0 | 113/0 | 2026-05-30 | 2026-05-24 | -6 |  | TRUE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 126/0-127/0 | ta505¦126/0¦127/0 | Jahangir Alam | 126/0 | 127/0 | 2026-07-14 | 2026-07-18 | 4 | 4 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 127/0-128/0 | ta505¦127/0¦128/0 | Jahangir Alam | 127/0 | 128/0 | 2026-07-05 | 2026-07-14 | 9 | 9 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 108/0-109/0 | ta505¦108/0¦109/0 | Nasiruddin | 108/0 | 109/0 | 2026-06-29 | 2026-07-03 | 4 | 4 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 109/0-110/0 | ta505¦109/0¦110/0 | Nasiruddin | 109/0 | 110/0 | 2026-06-21 | 2026-06-24 | 3 | 3 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | Others | Unassigned | 115/0-116/0 | ta505¦115/0¦116/0 | Ram Singh | 115/0 | 116/0 | 2026-06-12 | 2026-06-01 | -11 |  | TRUE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 105/0-106/0 | ta505¦105/0¦106/0 |  | 105/0 | 106/0 | 2026-07-11 | 2026-07-12 | 1 | 1 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | Others | Unassigned | 106/0-108/0 | ta505¦106/0¦108/0 | Nasiruddin | 106/0 | 108/0 | 2026-07-11 | 2026-07-09 | -2 |  | TRUE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | Others | Unassigned | 117/0-118/0 | ta505¦117/0¦118/0 | Ram Singh | 117/0 | 118/0 | 2026-06-19 | 2026-06-15 | -4 |  | TRUE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 175/0-176/0 | ta505¦175/0¦176/0 | Sk infra | 175/0 | 176/0 | 2026-07-21 | 2026-07-24 | 3 | 3 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 176/0-177/0 | ta505¦176/0¦177/0 | Sk infra | 176/0 | 177/0 | 2026-06-23 | 2026-07-03 | 10 | 10 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 177/0-178/0 | ta505¦177/0¦178/0 | Sk infra | 177/0 | 178/0 | 2026-07-11 | 2026-07-12 | 1 | 1 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 116/0-117/0 | ta505¦116/0¦117/0 | Jahangir Alam | 116/0 | 117/0 | 2026-06-15 | 2026-06-16 | 1 | 1 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | 120/0-121/0 | ta505¦120/0¦121/0 | Jahangir Alam | 120/0 | 121/0 | 2026-06-26 | 2026-06-24 | -2 |  | TRUE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | Others | Unassigned | 119/0-120/0 | ta505¦119/0¦120/0 | Ram Singh | 119/0 | 120/0 | 2026-06-30 | 2026-06-26 | -4 |  | TRUE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | Others | Unassigned | 118/0-119/0 | ta505¦118/0¦119/0 | Ram Singh | 118/0 | 119/0 | 2026-07-02 | 2026-06-21 | -11 |  | TRUE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 11/0-11/3 | ta506¦11/0¦11/3 | National Construction | 11/0 | 11/3 | 2026-04-04 | 2026-04-15 | 11 | 11 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 213/0-214/0 | ta506¦213/0¦214/0 | Bilkish Rehena | 213/0 | 214/0 | 2026-04-04 | 2026-04-06 | 2 | 2 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 17/0-18/0 | ta506¦17/0¦18/0 | Jahangir Alam | 17/0 | 18/0 | 2026-04-09 | 2026-04-13 | 4 | 4 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 9/0-10/0 | ta506¦9/0¦10/0 | National Construction | 9/0 | 10/0 | 2026-04-09 | 2026-04-09 | 0 | 0 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 139/0-139A/0 | ta506¦139/0¦139A/0 | Rejaul Sekh | 139/0 | 139A/0 | 2026-05-23 | 2026-05-26 | 3 | 3 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 139A/0-140/0 | ta506¦139A/0¦140/0 | Rejaul Sekh | 139A/0 | 140/0 | 2026-05-19 | 2026-06-11 | 23 | 23 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 212/0-213/0 | ta506¦212/0¦213/0 | Bilkish Rehena | 212/0 | 213/0 | 2026-04-15 | 2026-04-16 | 1 | 1 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 12/0-13/0 | ta506¦12/0¦13/0 | National Construction | 12/0 | 13/0 | 2026-04-14 | 2026-04-18 | 4 | 4 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 65/0-65A/0 | ta506¦65/0¦65A/0 | Taimoor Ali | 65/0 | 65A/0 | 2026-04-12 | 2026-05-13 | 31 | 31 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 65A/0-65A/3 | ta506¦65A/0¦65A/3 | Taimoor Ali | 65A/0 | 65A/3 | 2026-04-17 | 2026-05-10 | 23 | 23 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 15/0-16/0 | ta506¦15/0¦16/0 | Jahangir Alam | 15/0 | 16/0 | 2026-04-18 | 2026-05-12 | 24 | 24 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 64/0-64A/0 | ta506¦64/0¦64A/0 | Taimoor Ali | 64/0 | 64A/0 | 2026-04-23 | 2026-05-21 | 28 | 28 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 211/0-212/0 | ta506¦211/0¦212/0 | Bilkish Rehena | 211/0 | 212/0 | 2026-04-29 | 2026-05-02 | 3 | 3 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 63/0-64/0 | ta506¦63/0¦64/0 | Taimoor Ali | 63/0 | 64/0 | 2026-05-03 | 2026-05-27 | 24 | 24 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 13/0-14/0 | ta506¦13/0¦14/0 | National Construction | 13/0 | 14/0 | 2026-05-14 | 2026-05-16 | 2 | 2 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 64A/0-65/0 | ta506¦64A/0¦65/0 | Taimoor Ali | 64A/0 | 65/0 | 2026-05-16 | 2026-05-18 | 2 | 2 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 38/0-39/0 | ta506¦38/0¦39/0 | Jahangir Alam | 38/0 | 39/0 | 2026-05-24 | 2026-06-10 | 17 | 17 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 37/0-38/0 | ta506¦37/0¦38/0 | Jahangir Alam | 37/0 | 38/0 | 2026-06-02 | 2026-06-03 | 1 | 1 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 14/0-15/0 | ta506¦14/0¦15/0 | National Construction | 14/0 | 15/0 | 2026-06-08 | 2026-06-08 | 0 | 0 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 61/0-62/0 | ta506¦61/0¦62/0 | Taimoor Ali | 61/0 | 62/0 | 2026-06-12 | 2026-06-22 | 10 | 10 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 140/0-141/0 | ta506¦140/0¦141/0 | Rejaul Sekh | 140/0 | 141/0 | 2026-06-13 | 2026-06-17 | 4 | 4 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 16/0-17/0 | ta506¦16/0¦17/0 | National Construction | 16/0 | 17/0 | 2026-06-12 | 2026-06-12 | 0 | 0 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 141/0-142/0 | ta506¦141/0¦142/0 | Rejaul Sekh | 141/0 | 142/0 | 2026-06-19 | 2026-06-22 | 3 | 3 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 60/0-61/0 | ta506¦60/0¦61/0 | Taimoor Ali | 60/0 | 61/0 | 2026-06-21 | 2026-06-25 | 4 | 4 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 210/0-211/0 | ta506¦210/0¦211/0 | National Construction | 210/0 | 211/0 | 2026-06-29 | 2026-07-01 | 2 | 2 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 223/0-224/0 | ta506¦223/0¦224/0 | Samirul Sekh | 223/0 | 224/0 | 2026-06-28 | 2026-06-30 | 2 | 2 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 138/0-139/0 | ta506¦138/0¦139/0 | Rejaul Sekh | 138/0 | 139/0 | 2026-07-02 | 2026-07-10 | 8 | 8 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 137/0-138/0 | ta506¦137/0¦138/0 | Rejaul Sekh | 137/0 | 138/0 | 2026-07-07 | 2026-07-09 | 2 | 2 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 40/0-41/0 | ta506¦40/0¦41/0 | Taimoor Ali | 40/0 | 41/0 | 2026-07-06 | 2026-07-15 | 9 | 9 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 39/0-40/0 | ta506¦39/0¦40/0 | Taimoor Ali | 39/0 | 40/0 | 2026-07-08 | 2026-07-09 | 1 | 1 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 200/0-201/0 | ta506¦200/0¦201/0 | National Construction | 200/0 | 201/0 | 2026-07-11 | 2026-07-19 | 8 | 8 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 187A/0-188/0 | ta506¦187A/0¦188/0 | Samirul Sekh | 187A/0 | 188/0 | 2026-07-11 | 2026-08-01 | 21 | 21 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 41/0-42/0 | ta506¦41/0¦42/0 | Taimoor Ali | 41/0 | 42/0 | 2026-07-14 | 2026-07-15 | 1 | 1 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 199/0-200/0 | ta506¦199/0¦200/0 | National Construction | 199/0 | 200/0 | 2026-07-20 | 2026-07-24 | 4 | 4 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 187/0-187A/0 | ta506¦187/0¦187A/0 | Samirul Sekh | 187/0 | 187A/0 | 2026-07-25 | 2026-08-03 | 9 | 9 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 59/0-60/0 | ta506¦59/0¦60/0 | Taimoor Ali | 59/0 | 60/0 | 2026-07-27 | 2026-07-28 | 1 | 1 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 134/0-135/0 | ta506¦134/0¦135/0 | Rejaul Sekh | 134/0 | 135/0 | 2026-08-01 | 2026-08-10 | 9 | 9 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 25/0-26/0 | ta506¦25/0¦26/0 | MA Traders | 25/0 | 26/0 | 2026-08-04 | 2026-08-09 | 5 | 5 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 202/0-203/0 | ta506¦202/0¦203/0 | National Construction | 202/0 | 203/0 | 2026-08-06 | 2026-08-07 | 1 | 1 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 35/0-35A/0 | ta506¦35/0¦35A/0 | Afajal hossain | 35/0 | 35A/0 | 2026-08-05 |  |  |  | FALSE | TRUE | FALSE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 201/0-202/0 | ta506¦201/0¦202/0 | National Construction | 201/0 | 202/0 | 2026-08-06 | 2026-08-07 | 1 | 1 | FALSE | TRUE | TRUE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | Others | Unassigned | 26/0-27/0 | ta506¦26/0¦27/0 | MA Traders | 26/0 | 27/0 | 2026-08-07 |  |  |  | FALSE | TRUE | FALSE
TA 506 | TA 506 | TA 506 | ta506 | ta506 | TA 506 | 5xx | TA | TSE | Unassigned | 36/0-37/0 | ta506¦36/0¦37/0 | Afajal hossain | 36/0 | 37/0 | 2026-08-11 |  |  |  | FALSE | TRUE | FALSE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | Others | Unassigned | 14/0-14A/0 | tb408¦14/0¦14A/0 | Nasiruddin | 14/0 | 14A/0 | 2026-04-06 | 2026-04-05 | -1 |  | TRUE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 8/7-9/0 | tb408¦8/7¦9/0 | Deepak Sarkar | 8/7 | 9/0 | 2026-04-03 | 2026-04-06 | 3 | 3 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | Others | Unassigned | 9/0-10/0 | tb408¦9/0¦10/0 | Gopal Associate, Hotline | 9/0 | 10/0 | 2026-04-09 | 2026-04-03 | -6 |  | TRUE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 54/0-55/0 | tb408¦54/0¦55/0 | MC Power | 54/0 | 55/0 | 2026-04-09 | 2026-04-08 | -1 |  | TRUE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 8/0-8/7 | tb408¦8/0¦8/7 | Devi Power | 8/0 | 8/7 | 2026-04-09 | 2026-04-08 | -1 |  | TRUE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 43/0-44/0 | tb408¦43/0¦44/0 | Krishna-1 | 43/0 | 44/0 | 2026-04-15 | 2026-04-16 | 1 | 1 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 6/0-7/0 | tb408¦6/0¦7/0 | Deepak Sarkar / Nasiruddin | 6/0 | 7/0 | 2026-04-15 | 2026-03-24 | -22 |  | TRUE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 53/0-54/0 | tb408¦53/0¦54/0 | MC Power | 53/0 | 54/0 | 2026-04-26 | 2026-04-30 | 4 | 4 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | Others | Unassigned | 5/0-6/0 | tb408¦5/0¦6/0 | Gopal Associate, Hotline | 5/0 | 6/0 | 2026-04-30 | 2026-04-24 | -6 |  | TRUE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 14A/0-15/0 | tb408¦14A/0¦15/0 | Nasiruddin | 14A/0 | 15/0 | 2026-05-04 | 2026-05-02 | -2 |  | TRUE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 13/0-14/0 | tb408¦13/0¦14/0 | Nasiruddin | 13/0 | 14/0 | 2026-04-04 | 2026-05-12 | 38 | 38 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 52/0-53/0 | tb408¦52/0¦53/0 | MC Power | 52/0 | 53/0 | 2026-05-16 | 2026-05-18 | 2 | 2 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 11A/0-12/0 | tb408¦11A/0¦12/0 | Nasiruddin | 11A/0 | 12/0 | 2026-05-16 | 2026-05-27 | 11 | 11 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | Others | Unassigned | 12/0-13/0 | tb408¦12/0¦13/0 | Gopal Associate, Hotline | 12/0 | 13/0 | 2026-05-31 | 2026-05-26 | -5 |  | TRUE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | Others | Unassigned | 23/0-24/0 | tb408¦23/0¦24/0 | Gopal Associate, Hotline | 23/0 | 24/0 | 2026-06-16 | 2026-06-09 | -7 |  | TRUE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | Others | Unassigned | 24/0-25/0 | tb408¦24/0¦25/0 | MC Power | 24/0 | 25/0 | 2026-06-26 | 2026-06-21 | -5 |  | TRUE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 11/0-11A/0 | tb408¦11/0¦11A/0 | Nasiruddin | 11/0 | 11A/0 | 2026-06-22 | 2026-06-23 | 1 | 1 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 27/0-27/7 | tb408¦27/0¦27/7 | Mohammad Construction / Furkhan | 27/0 | 27/7 | 2026-06-29 | 2026-07-01 | 2 | 2 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 22/8-23/0 | tb408¦22/8¦23/0 | MC Power | 22/8 | 23/0 | 2026-07-04 | 2026-07-05 | 1 | 1 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 29/0-30/0 | tb408¦29/0¦30/0 | Jamera Bibi | 29/0 | 30/0 | 2026-06-29 | 2026-07-02 | 3 | 3 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 15/0-16/0 | tb408¦15/0¦16/0 | Nasiruddin | 15/0 | 16/0 | 2026-07-06 | 2026-07-11 | 5 | 5 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 4/0-5/0 | tb408¦4/0¦5/0 | Nasiruddin | 4/0 | 5/0 | 2026-07-19 | 2026-07-20 | 1 | 1 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 27/7-28/0 | tb408¦27/7¦28/0 | Mohammad Construction / Furkhan | 27/7 | 28/0 | 2026-07-16 | 2026-07-20 | 4 | 4 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 22/0-22/8 | tb408¦22/0¦22/8 | MC Power | 22/0 | 22/8 | 2026-07-26 | 2026-07-23 | -3 |  | TRUE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 30/0-31/0 | tb408¦30/0¦31/0 | Jamera Bibi | 30/0 | 31/0 | 2026-07-22 | 2026-07-26 | 4 | 4 | FALSE | TRUE | TRUE
TB 408 | TB 408 | TB 408 | tb408 | tb408 | TB 408 | 4xx | TB | TSE | Unassigned | 16/0-17/0 | tb408¦16/0¦17/0 | Nasiruddin | 16/0 | 17/0 | 2026-07-15 | 2026-07-28 | 13 | 13 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | CPP-1/0 | tb501132kv¦CPP¦1/0 |  | CPP | 1/0 | 2026-06-29 |  |  |  | FALSE | TRUE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | 1/0-2/0 | tb501132kv¦1/0¦2/0 |  | 1/0 | 2/0 | 2026-06-29 |  |  |  | FALSE | TRUE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | 2/0-2/1 | tb501132kv¦2/0¦2/1 |  | 2/0 | 2/1 | 2026-06-28 |  |  |  | FALSE | TRUE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | 2/1-3/0 | tb501132kv¦2/1¦3/0 |  | 2/1 | 3/0 | 2026-06-28 |  |  |  | FALSE | TRUE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | 3/0-3/1 | tb501132kv¦3/0¦3/1 | Sammirul Sekh | 3/0 | 3/1 | 2026-05-08 | 2026-05-08 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | 3/1-4/0 | tb501132kv¦3/1¦4/0 | Sammirul Sekh | 3/1 | 4/0 | 2026-05-08 | 2026-05-08 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | 11/0-12/0 | tb501132kv¦11/0¦12/0 | Sammirul Sekh | 11/0 | 12/0 | 2026-05-11 | 2026-05-12 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | 14/0-15/0 | tb501132kv¦14/0¦15/0 | Sammirul Sekh | 14/0 | 15/0 | 2026-05-14 | 2026-05-15 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 1B/0-1C/0 | tb501220kv¦1B/0¦1C/0 | National Construction | 1B/0 | 1C/0 | 2026-04-09 | 2026-04-10 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 1C/0-1D/0 | tb501220kv¦1C/0¦1D/0 | National Construction | 1C/0 | 1D/0 | 2026-04-13 | 2026-04-14 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 3/0-4/0 | tb501220kv¦3/0¦4/0 | National Construction | 3/0 | 4/0 | 2026-04-06 | 2026-04-07 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 4/6-4/7 | tb501220kv¦4/6¦4/7 |  | 4/6 | 4/7 | 2026-06-27 | 2026-07-28 | 31 | 31 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 4/7-4/8 | tb501220kv¦4/7¦4/8 |  | 4/7 | 4/8 | 2026-06-23 | 2026-06-24 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 4/8-4/9 | tb501220kv¦4/8¦4/9 |  | 4/8 | 4/9 | 2026-06-23 | 2026-06-24 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 31-32 | tb501220kv¦31¦32 | GKFS Enterprises | AP-31 | AP-32 | 2026-06-05 | 2026-06-06 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 32-33/0 | tb501220kv¦32¦33/0 |  | AP-32 | 33/0 | 2026-06-08 | 2026-06-09 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 33/0-34/0 | tb501220kv¦33/0¦34/0 | Ram singh | 33/0 | 34/0 | 2026-06-05 | 2026-06-06 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 34/0-35/0 | tb501220kv¦34/0¦35/0 |  | 34/0 | 35/0 | 2026-06-08 | 2026-06-09 | 1 | 1 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | 144/0-143/0 | tb507main¦144/0¦143/0 | Mahadev Enterprises | 144/0 | 143/0 | 2026-04-04 |  |  |  | FALSE | TRUE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Unassigned | 113/0-112/0 | tb507main¦113/0¦112/0 | Mahadev Maan Construction | 113/0 | 112/0 | 2026-04-10 |  |  |  | FALSE | TRUE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Unassigned | 113A/0-113/0 | tb507main¦113A/0¦113/0 | Mahadev Maan Construction | 113A/0 | 113/0 | 2026-04-10 |  |  |  | FALSE | TRUE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | 148/0-147/0 | tb507main¦148/0¦147/0 | Mahadev Enterprises | 148/0 | 147/0 | 2026-04-20 | 2026-04-19 | -1 |  | TRUE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | 134/0-133/0 | tb507main¦134/0¦133/0 | Mahadev Enterprises | 134/0 | 133/0 | 2026-05-13 |  |  |  | FALSE | TRUE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Unassigned | 134/0-134A/0 | tb507main¦134/0¦134A/0 | SK Tajirul | 134/0 | 134A/0 | 2026-05-13 | 2026-05-23 | 10 | 10 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Unassigned | 114/0-113A/0 | tb507main¦114/0¦113A/0 | SK Tajirul | 114/0 | 113A/0 | 2026-05-20 | 2026-05-21 | 1 | 1 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | 75/0-76/0 | tb507main¦75/0¦76/0 | SK Tajirul | 75/0 | 76/0 | 2026-06-24 | 2026-06-25 | 1 | 1 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | 132/0-133/0 | tb507main¦132/0¦133/0 | KP Group | 132/0 | 133/0 | 2026-07-22 | 2027-07-23 | 366 | 366 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Unassigned | 83/0-84/0 | tb507main¦83/0¦84/0 | SK Tajirul | 83/0 | 84/0 | 2026-07-18 | 2026-07-20 | 2 | 2 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Unassigned | 84/0-85/0 | tb507main¦84/0¦85/0 | SK Tajirul | 84/0 | 85/0 | 2026-07-09 | 2026-07-20 | 11 | 11 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Unassigned | 85/0-86/0 | tb507main¦85/0¦86/0 | SK Tajirul | 85/0 | 86/0 | 2026-08-03 | 2026-08-04 | 1 | 1 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | 134A/0-135/0 | tb507main¦134A/0¦135/0 | Mahadev Enterprises | 134A/0 | 135/0 | 2026-07-18 | 2026-07-22 | 4 | 4 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | 135/0-136/0 | tb507main¦135/0¦136/0 | Mahadev Enterprises | 135/0 | 136/0 | 2026-07-30 | 2026-07-27 | -3 |  | TRUE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Unassigned | 136/0-137/0 | tb507main¦136/0¦137/0 | Mahadev Enterprises | 136/0 | 137/0 | 2026-07-21 |  |  |  | FALSE | TRUE | FALSE
TB 605 | TB 605 | TB 605 | tb605 | tb605 | TB 605 | 6xx | TB | TSE | AP25-AP26 | 25-26 | tb605¦25¦26 | Tariq | AP25 | AP26 | 2026-06-21 | 2026-06-23 | 2 | 2 | FALSE | TRUE | TRUE
TB 605 | TB 605 | TB 605 | tb605 | tb605 | TB 605 | 6xx | TB | Others | AP26-AP27 | 26-27 | tb605¦26¦27 | Tariq | AP26 | AP27 | 2026-06-16 | 2026-06-17 | 1 | 1 | FALSE | TRUE | TRUE
TB 605 | TB 605 | TB 605 | tb605 | tb605 | TB 605 | 6xx | TB | TSE | AP18-AP19 | 18-19 | tb605¦18¦19 | Janual Sheik | AP18 | AP19 | 2026-07-12 | 2026-07-16 | 4 | 4 | FALSE | TRUE | TRUE
TB 605 | TB 605 | TB 605 | tb605 | tb605 | TB 605 | 6xx | TB | Others | AP24-AP25 | 24-25 | tb605¦24¦25 | Tariq | AP24 | AP25 | 2026-07-05 | 2026-07-04 | -1 |  | TRUE | TRUE | TRUE
TB 605 | TB 605 | TB 605 | tb605 | tb605 | TB 605 | 6xx | TB | Others | AP20-AP21 | 20-21 | tb605¦20¦21 | Janual Sheik | AP20 | AP21 | 2026-07-02 | 2026-08-03 | 32 | 32 | FALSE | TRUE | TRUE
TB 605 | TB 605 | TB 605 | tb605 | tb605 | TB 605 | 6xx | TB | Others | AP27-AP28 | 27-28 | tb605¦27¦28 | Tariq | AP27 | AP28 | 2026-07-14 | 2026-07-17 | 3 | 3 | FALSE | TRUE | TRUE
TB 605 | TB 605 | TB 605 | tb605 | tb605 | TB 605 | 6xx | TB | TSE | AP19-AP20 | 19-20 | tb605¦19¦20 | Janual Sheik | AP19 | AP20 | 2026-07-19 | 2026-07-23 | 4 | 4 | FALSE | TRUE | TRUE
TB 605 | TB 605 | TB 605 | tb605 | tb605 | TB 605 | 6xx | TB | Others | AP28-AP29 | 28-29 | tb605¦28¦29 | Tariq | AP28 | AP29 | 2026-07-16 | 2026-07-31 | 15 | 15 | FALSE | TRUE | TRUE

## Stringing Monitoring Numeric
Stringing Monitoring Numeric
project_code | row_type | gang_name | report_month | project_total_scope_km | monthly_plan_km | fs_achieved_month_km | %_achieved | wip_km | rough_sag_completed_km | rough_sag_balance_km | final_sag_completed_km | final_sag_balance_km | stretch_readiness_pct | existing_manpower | fitter_count
TA 413 | project |  | 2026-08 | 707.1051 | 115.944 | 9.452 | 0.081522 | 17.16 | 617.774 | 89.3311 | 600.614 | 106.4911 | 0
TA 414 | project |  | 2026-08 | 638.995 | 15 |  |  | 0 | 139.835 | 499.16 | 139.835 | 499.16
TA 414 | gang | Dharmendra | 2026-08 | [10 empty] | 24
TA 414 | gang | Enamul Haque | 2026-08 | [10 empty] | 45
TA 414 | gang | Alam Construction | 2026-08 | [10 empty] | 40
TA 414 | gang | Maa Singhvahini | 2026-08 | [10 empty] | 27
TA 414 | gang | Sanjay singh 2 | 2026-08 | [10 empty] | 33
TA 414 | gang | Sanjay Singh | 2026-08 | [10 empty] | 20
TA 414 | gang | Sanjay Singh 1 | 2026-08 | [10 empty] | 20
TA 414 | gang | Sanjay Singh 2 | 2026-08 | [10 empty] | 33
TA 414 | gang | Abdul adut | 2026-08
TA 414 | gang | Bhola prasad+ Deepak Sarkar | 2026-08 | [10 empty] | 30
TA 416 | project |  | 2026-07 | 460.536 | 16 | 7.994 | 0.49962 |  |  |  | 459.188 | 1.348 |  | 16 | 6
TA 416 | gang | ANARUL ISLAM | 2026-07 | [10 empty] | 40 | 12
TA 416 | gang | S K INFRA | 2026-07
TA 416 | gang | J PG CON | 2026-07
TA 416 | gang | AE Solution | 2026-07
TA 416 | gang | Jahangir(Company) | 2026-07
TA 416 | gang | Babloo Haque/Anarul-2 | 2026-07
TA 416 | gang | Ramawat-Hot line | 2026-07
TA 416 | gang | AE Solution(Company) | 2026-07
TA 416 | gang | Bhola prasad(Company)+Sing Bahini | 2026-07
TA 416 | gang | Bhola+Sing bahini(Company) | 2026-07
TA 416 | gang | Astharul (company) | 2026-07
TA 416 | gang | SADIK Con(company) | 2026-07 |  |  | 0.57369 | [7 empty] | 16 | 6
TA 416 | gang | Dharmendra Hot line | 2026-07 | [10 empty] | 20 | 12
TA 416 | gang | Anarul-2 | 2026-07
TA 416 | gang | Khosibur Ali(Company) | 2026-07
TA 416 | gang | (Kunal Hot line | 2026-07
TA 416 | gang | Jahangir(Company)FS-Anarul | 2026-07
TA 416 | gang | Kunal Hot line | 2026-07
TA 416 | gang | RK Enterprise | 2026-07
TA 418 | project |  | 2026-07 | 287.04 | 65.85 | 18.089 | 0.2747 |  |  |  | 239.279 | 47.761
TA 418 | gang | Ramawat | 2026-07 | [10 empty] | 22
TA 418 | gang | SUFIYAN / Haque | 2026-07 | [10 empty] | 73
TA 418 | gang | SUFIYAN | 2026-07 | [10 empty] | 31
TA 418 | gang | Dharmendar | 2026-07 | [10 empty] | 30
TA 418 | gang | Haque | 2026-07 | [10 empty] | 33
TA 418 | gang | M/s Akram | 2026-07 |  |  | 0.097639 | [7 empty] | 30
TA 418 | gang | M/s Ranveer | 2026-07 | [10 empty] | 18
TA 418 | gang | M/s Dharmander | 2026-07 | [10 empty] | 24
TA 418 | gang | M/s Kamrudhin | 2026-07 |  |  | 0.019907 | [7 empty] | 22
TA 419 | project |  | 2026-08 | 611.03 | 145 | 3.703 | 0.025538 | 25.565 | 76.768 | 534.262 | 51.203 | 559.827 | 0 | 50
TA 419 | gang | Saheb Enterprises | 2026-08 | [10 empty] | 50
TA 419 | gang | Alimuddin | 2026-08
TA 419 | gang | Dharmendra | 2026-08
TA 419 | gang | Enamul | 2026-08
TA 419 | gang | Mussoluddin | 2026-08
TA 421 | project |  | 2026-07 | 728.052 | [6 empty] | 702.957 | 25.095 | 0 | 40
TA 421 | gang | M.R. Const | 2026-07 | [10 empty] | 17
TA 421 | gang | Nasiruddin | 2026-07 | [10 empty] | 34
TA 421 | gang | Ramvath | 2026-07 | [10 empty] | 20
TA 421 | gang | Kamruddin | 2026-07 | [10 empty] | 25
TA 421 | gang | Ramvath - 02 | 2026-07 | [10 empty] | 20
TA 421 | gang | Ramavath | 2026-07 | [10 empty] | 17
TA 421 | gang | Pankaj | 2026-07 | [10 empty] | 80
TA 504 | project |  | 2026-08 | 552 | [7 empty] | 469.756 | 0 | 40 | 10
TA 504 | gang | Tanjira Bibi | 2026-08 | [10 empty] | 40 | 10
TA 504 | gang | Lamba Construction | 2026-08 | [10 empty] | 50 | 13
TA 505 | project |  | 2026-07 | 1814.8 | [6 empty] | 440.059 | 1489.461 | 0 | 65
TA 505 | gang | Alimuddin | 2026-07 | [10 empty] | 35
TA 505 | gang | Jahangir Alam | 2026-07 |  |  | 4.0613 | [7 empty] | 55
TA 505 | gang | Nasiruddin | 2026-07 |  |  | 0.98185 | [7 empty] | 50
TA 505 | gang | Ram Singh | 2026-07 |  |  | 0.070167 | [7 empty] | 41
TA 505 | gang | Sk infra | 2026-07 |  |  | 5.6173 | [7 empty] | 65
TA 506 | project |  | 2026-08 | 1816 |  | 37.972 |  |  |  |  | 415.904 |  | 100 | 26
TA 506 | gang | National Construction | 2026-08 |  |  | 1.7182 | [7 empty] | 70
TA 506 | gang | Jahangir Alam | 2026-08 | [10 empty] | 39
TA 506 | gang | Taimoor Ali | 2026-08 | [10 empty] | 25
TA 506 | gang | Bilkish Rehena | 2026-08 | [10 empty] | 33
TA 506 | gang | Rejaul Sekh | 2026-08 | [10 empty] | 30
TA 506 | gang | Samirul Sekh | 2026-08 |  |  | 0.44354 | [7 empty] | 35
TA 506 | gang | MA Traders | 2026-08 |  |  | 1.1681 | [7 empty] | 26
TA 506 | gang | Afajal hossain | 2026-08
TA 509 | project |  | 2026-08 | 476.712 | 48 | 0 | 0 |  |  |  | 43.808 | 432.904
TA 510 | project |  | 2026-08 | 458.064 | 428.984 |  |  | 0 | 0 | 458.064 | 0 | 458.064
TA 512 | project |  | 2026-08 | 622.84 |  | 0 |  | 10.045 | 10.045 | 612.795 | 0 | 622.84 | 100
TA 513 | project |  | 2026-06 | 2306.6 | [5 empty] | 2306.6 |  | 2306.6
TA 601 | project |  | 2026-08 | 2039.148 | 41.628 | 0 | 0 |  |  |  | 0 | 2039.148
TA 602 | project |  | 2026-08 | 739.944 | 0 | 0 |  |  |  |  | 0 | 739.944
TB 408 | project |  | 2026-07 | 191.392 | 43.4645 | 18.0969 | 0.41636 | 2.3436 | 168.368 | 23.024 | 166.0244 | 25.3676 | 100
TB 408 | gang | Kuddus ali | 2026-07
TB 408 | gang | Gopal Associate | 2026-07
TB 408 | gang | MR Power | 2026-07
TB 408 | gang | JPJ Construction/MC Power | 2026-07
TB 408 | gang | Devi Power | 2026-07
TB 408 | gang | MC Power | 2026-07 |  |  | 2.0716
TB 408 | gang | Gopal Associate, Hotline | 2026-07
TB 408 | gang | Deepak Sarkar | 2026-07
TB 408 | gang | Krishna-1 | 2026-07
TB 408 | gang | Nasiruddin | 2026-07 |  |  | 2.691
TB 408 | gang | Deepak Sarkar / Nasiruddin | 2026-07
TB 408 | gang | Mohammad Construction / Furkhan | 2026-07 |  |  | 3.3906
TB 408 | gang | Jamera Bibi | 2026-07 |  |  | 3.581
TB 408 | gang | Gang Not Allocated | 2026-07
TB 408 | gang | Tata Projects Limited | 2026-07
TB 412 | project |  | 2026-08 | 905.646 | 9.57 | 0 | 0 |  |  |  | 16.188 | 889.458
TB 412 | gang | Rajeshwar | 2026-08
TB 412 | gang | Nav Durga Traders | 2026-08
TB 412 | gang | Anmol | 2026-08
TB 412 | gang | Dharmendra Mishra | 2026-08
TB 412 | gang | MAA | 2026-08
TB 412 | gang | Shakti | 2026-08
TB 412 | gang | GANG | 2026-08
TB 412 | gang | Sonakshi Mobile | 2026-08
TB 412 | gang | Sanjeev Kumar | 2026-08
TB 412 | gang | Asfak Ahmad | 2026-08
TB 412 | gang | Yashoda Devi | 2026-08
TB 412 | gang | Rang | 2026-08
TB 412 | gang | Kumkum Devi | 2026-08
TB 501 | project |  | 2026-07 | 732.7 | 58.09 | 35.6275 | 0.61332 | 0 | 709.9375 | 22.7625 | 709.9375 | 22.7625
TB 501 | gang | Sammirul Sekh | 2026-07
TB 501 | gang | National Construction | 2026-07
TB 501 | gang | Sawariya seth | 2026-07
TB 501 | gang | SK Basirul | 2026-07
TB 501 | gang | Harshvivek | 2026-07
TB 501 | gang | Dilruba Bibi | 2026-07
TB 501 | gang | Nemchand | 2026-07
TB 501 | gang | Kohinoor | 2026-07
TB 501 | gang | GKFS Enterprises | 2026-07
TB 501 | gang | Ram singh | 2026-07
TB 507 | project |  | 2026-08 | 1020.78 | 155.94 | 4.013 | 0.025734 | 5.377 | 162.895 | 1801.275 | 157.518 | 863.262 | 0
TB 507 | gang | Mahadev Enterprises | 2026-08
TB 507 | gang | Mahadev Maan Construction | 2026-08
TB 507 | gang | SK Tajirul | 2026-08 |  |  | 0.44311
TB 507 | gang | KP Group | 2026-08
TB 507 | gang | Mahadev Enterprises-2 | 2026-08
TB 605 | project |  | 2026-08 | 527.157 | 33 | 2.856 | 0.086545 |  |  |  | 17.001 | 510.156
TB 605 | gang | Tariq | 2026-08 |  |  | 0.046947
TB 605 | gang | Janual Sheik | 2026-08 |  |  | 0.0675
TB 605 | gang | Musludin | 2026-08
TB 605 | gang | Gopal Associates (Hot Line Gang) | 2026-08
TB 608 | project |  | 2026-08 | 16.0268 | 0 | 0 |  |  |  |  | 0 | 16.0268

## Stringing Monitoring Audit
Stringing Monitoring Audit
project_code | status_activity_available | status_final_sag_available | status_paying_out_available | stretch_readiness_available | manpower_available | fitter_available | location_nos_available | status_activity_fill_pct | status_final_sag_fill_pct | status_paying_out_fill_pct | stretch_readiness_fill_pct | manpower_fill_pct | fitter_fill_pct | location_nos_fill_pct | missing_data_tags
TA 413 | Yes | Yes | Yes | Yes | No | No | No | 94.4 | 100 | 100 | 100 | 0 | 0 | 0 | MISSING_MANPOWER;MISSING_FITTER;MISSING_LOCATION_NOS;MISSING_STRETCH_MANPOWER_SIGNAL
TA 414 | Yes | Yes | Yes | No | Yes | No | Yes | 72.9 | 80 | 100 | 0 | 71.1 | 0 | 39 | MISSING_STRETCH_READINESS;MISSING_FITTER
TA 416 | Yes | Yes | No | No | Yes | Yes | Yes | 100 | 100 | 0 | 0 | 4.1 | 4.1 | 98.7 | MISSING_STATUS_PAYING_OUT;MISSING_STRETCH_READINESS
TA 418 | Yes | Yes | No | No | Yes | No | Yes | 100 | 100 | 0 | 0 | 74.4 | 0 | 97.5 | MISSING_STATUS_PAYING_OUT;MISSING_STRETCH_READINESS;MISSING_FITTER
TA 419 | Yes | Yes | Yes | Yes | Yes | No | No | 80 | 100 | 100 | 100 | 100 | 0 | 0 | MISSING_FITTER;MISSING_LOCATION_NOS
TA 421 | Yes | Yes | No | Yes | Yes | No | No | 68.1 | 76.7 | 0 | 100 | 100 | 0 | 0 | MISSING_STATUS_PAYING_OUT;MISSING_FITTER;MISSING_LOCATION_NOS
TA 504 | Yes | Yes | No | Yes | Yes | Yes | Yes | 73.3 | 60 | 0 | 100 | 100 | 100 | 100 | MISSING_STATUS_PAYING_OUT
TA 505 | Yes | Yes | No | Yes | Yes | No | No | 65.6 | 96.9 | 0 | 100 | 98.4 | 0 | 0 | MISSING_STATUS_PAYING_OUT;MISSING_FITTER;MISSING_LOCATION_NOS
TA 506 | Yes | Yes | No | Yes | Yes | No | No | 79.2 | 80 | 0 | 100 | 100 | 0 | 0 | MISSING_STATUS_PAYING_OUT;MISSING_FITTER;MISSING_LOCATION_NOS
TA 509 | Yes | Yes | No | No | No | No | No | 100 | 100 | 0 | 0 | 0 | 0 | 0 | MISSING_STATUS_PAYING_OUT;MISSING_STRETCH_READINESS;MISSING_MANPOWER;MISSING_FITTER;MISSING_LOCATION_NOS
TA 510 | Yes | Yes | Yes | No | No | No | No | 80 | 80 | 100 | 0 | 0 | 0 | 0 | MISSING_STRETCH_READINESS;MISSING_MANPOWER;MISSING_FITTER;MISSING_LOCATION_NOS
TA 512 | Yes | Yes | Yes | Yes | No | No | No | 85 | 80 | 100 | 100 | 0 | 0 | 0 | MISSING_MANPOWER;MISSING_FITTER;MISSING_LOCATION_NOS
TA 513 | Yes | Yes | Yes | No | No | No | No | 65.6 | 50 | 50 | 0 | 0 | 0 | 0 | MISSING_STRETCH_READINESS;MISSING_MANPOWER;MISSING_FITTER;MISSING_LOCATION_NOS
TA 601 | Yes | Yes | No | No | No | No | No | 69.1 | 100 | 0 | 0 | 0 | 0 | 0 | MISSING_STATUS_PAYING_OUT;MISSING_STRETCH_READINESS;MISSING_MANPOWER;MISSING_FITTER;MISSING_LOCATION_NOS
TA 602 | Yes | Yes | No | No | No | No | No | 96.7 | 100 | 0 | 0 | 0 | 0 | 0 | MISSING_STATUS_PAYING_OUT;MISSING_STRETCH_READINESS;MISSING_MANPOWER;MISSING_FITTER;MISSING_LOCATION_NOS
TB 408 | Yes | Yes | Yes | Yes | No | No | No | 94.3 | 100 | 100 | 100 | 0 | 0 | 0 | MISSING_MANPOWER;MISSING_FITTER;MISSING_LOCATION_NOS;MISSING_STRETCH_MANPOWER_SIGNAL
TB 412 | Yes | Yes | No | No | No | No | No | 100 | 100 | 0 | 0 | 0 | 0 | 0 | MISSING_STATUS_PAYING_OUT;MISSING_STRETCH_READINESS;MISSING_MANPOWER;MISSING_FITTER;MISSING_LOCATION_NOS
TB 501 | Yes | Yes | Yes | No | No | No | No | 97.8 | 100 | 100 | 0 | 0 | 0 | 0 | MISSING_STRETCH_READINESS;MISSING_MANPOWER;MISSING_FITTER;MISSING_LOCATION_NOS
TB 507 | Yes | Yes | Yes | Yes | No | No | Yes | 93 | 100 | 100 | 100 | 0 | 0 | 76.3 | MISSING_MANPOWER;MISSING_FITTER
TB 605 | Yes | Yes | No | No | No | No | No | 96.7 | 100 | 0 | 0 | 0 | 0 | 0 | MISSING_STATUS_PAYING_OUT;MISSING_STRETCH_READINESS;MISSING_MANPOWER;MISSING_FITTER;MISSING_LOCATION_NOS
TB 608 | Yes | Yes | No | No | No | No | No | 68.6 | 100 | 0 | 0 | 0 | 0 | 0 | MISSING_STATUS_PAYING_OUT;MISSING_STRETCH_READINESS;MISSING_MANPOWER;MISSING_FITTER;MISSING_LOCATION_NOS