## Movement Summary
Metric | Q1 Value | Q2-to-date Value | Movement | Direction
Foundation-Erection cumulative gap (count) | 1490 | 1262 | -228 | Narrowed
Foundation->Erection average delay days | 32.8 | 12.3 | -20.5 | Reduced
Foundation->Erection median delay days | 25.5 | 11.5 | -14 | Reduced
Erection->Stringing average gap days | 137.8 | 191.1 | 53.3 | Increased
Erection->Stringing median gap days | 137 | 206 | 69 | Increased

## FE Cumulative Gap Monthly
Month | Gap Eligible Project Count | Snapshot-Limited Project Count | Foundations Cumulative | Erections Cumulative | Gap Cumulative | MoM Gap Movement
2026-04 | 16 | 0 | 4353 | 3211 | 1142 | -44
2026-05 | 17 | 1 | 4810 | 3580 | 1230 | 88
2026-06 | 18 | 2 | 5330 | 3840 | 1490 | 260
2026-07 | 18 | 2 | 5308 | 4025 | 1283 | -207
2026-08 | 18 | 2 | 5340 | 4078 | 1262 | -21

## FE Delay Quarter
Period | Foundation Locations | Matched Non-Negative | Match % | Average Delay Days | Median Delay Days | P90 Delay Days | Negative Excluded | Unmatched
Q1 2026 (Apr-Jun) | 466 | 204 | 43.8 | 32.8 | 25.5 | 70.7 | 6 | 256
Q2 2026 to date (Jul-Aug 12) | 114 | 28 | 24.6 | 12.3 | 11.5 | 20.8 | 0 | 86

## FE Delay Monthly
Period | Foundation Locations | Matched Non-Negative | Match % | Average Delay Days | Median Delay Days | P90 Delay Days | Negative Excluded | Unmatched
2026-04 | 117 | 65 | 55.6 | 45.3 | 31 | 91.2 | 1 | 51
2026-05 | 179 | 77 | 43 | 30.6 | 26 | 66.8 | 2 | 100
2026-06 | 170 | 62 | 36.5 | 22.4 | 18.5 | 41.9 | 3 | 105
2026-07 | 94 | 28 | 29.8 | 12.3 | 11.5 | 20.8 | 0 | 66
2026-08 | 20 | 0 | 0 |  |  |  | 0 | 20

## ES Gap Quarter
Period | Spans Considered | Spans With Computable Lag | Lag Coverage % | Average Gap Days | Median Gap Days | % Gap >60 Days | Negative Lag Excluded | Fallback Rows | Fallback %
Q1 2026 (Apr-Jun) | 179 | 157 | 87.7 | 137.8 | 137 | 79.9 | 3 | 136 | 76
Q2 2026 to date (Jul-Aug 12) | 81 | 49 | 60.5 | 191.1 | 206 | 85.7 | 0 | 76 | 93.8

## ES Gap Monthly
Period | Spans Considered | Spans With Computable Lag | Lag Coverage % | Average Gap Days | Median Gap Days | % Gap >60 Days | Negative Lag Excluded | Fallback Rows | Fallback %
2026-04 | 51 | 48 | 94.1 | 111.7 | 125.5 | 82.6 | 2 | 31 | 60.8
2026-05 | 48 | 43 | 89.6 | 126 | 122.5 | 76.2 | 1 | 36 | 75
2026-06 | 80 | 66 | 82.5 | 163.6 | 170 | 80.3 | 0 | 69 | 86.2
2026-07 | 54 | 39 | 72.2 | 189.7 | 200 | 84.6 | 0 | 50 | 92.6
2026-08 | 27 | 10 | 37 | 196.6 | 216.5 | 90 | 0 | 26 | 96.3

## FE Project Movement
Project | Jun Gap | Aug Gap | Movement
TA 602 | 246 | 81 | -165
TA 601 | 147 | 188 | 41
TA 512 | 70 | 33 | -37
TB 605 | 104 | 80 | -24
TB 507 | 126 | 102 | -24
TA 414 | 69 | 55 | -14
TA 513 | 65 | 74 | 9
TA 419 | 50 | 41 | -9
TB 608 | 116 | 109 | -7
TA 418 | 161 | 167 | 6
TA 510 | 50 | 47 | -3
TA 416 | 328 | 331 | 3
TA 505 | 15 | 13 | -2
TA 413 | 12 | 11 | -1
TB 408 | -453 | -454 | -1
TA 509 | 54 | 53 | -1
TB 501 | 1 | 2 | 1
TA 421 | 329 | 329 | 0

## Latest Source Files
File | Modified | Size Bytes
TA 504 - DPR - 2026-08-11.xlsx | 2026-08-12 06:20:18 | 2717802
TA 506 - DPR - 2026-08-11.xlsx | 2026-08-12 06:20:18 | 4298007
TA 512 - DPR - 2026-08-11.xlsx | 2026-08-12 05:22:36 | 1811186
TB 412 - DPR - 2026-08-11.xlsx | 2026-08-12 05:15:01 | 671774
TA 413 - DPR - 2026-08-11.xlsx | 2026-08-12 04:55:42 | 1242351
TB 507 [MAIN] - DPR - 2026-08-11.xlsx | 2026-08-12 04:21:55 | 1994627
TB 507 - DPR - 2026-08-11.xlsx | 2026-08-12 04:21:55 | 1699512
TA 513 - DPR - 2026-08-11.xlsx | 2026-08-12 04:18:28 | 2604362
TA 414 - DPR - 2026-08-11.xlsx | 2026-08-11 17:51:38 | 2527607
TB 605 - DPR - 2026-08-11.xlsx | 2026-08-11 17:43:46 | 1842346
TA 601 - DPR - 2026-08-11.xlsx | 2026-08-11 16:44:32 | 685208
TA 510 - DPR - 2026-08-11.xlsx | 2026-08-11 15:30:59 | 623872
TA 602 - DPR - 2026-08-10.xlsx | 2026-08-11 11:21:49 | 195126
TA 505 - DPR - 2026-07-29.xlsx | 2026-08-11 11:09:44 | 651726
TA 419 - DPR - 2026-08-10.xlsx | 2026-08-11 05:53:06 | 18381257
TA 509 - DPR - 2026-08-09.xlsx | 2026-08-10 07:31:23 | 2982594
TB 608 - DPR - 2026-08-09.xlsm | 2026-08-10 04:35:48 | 1083755
TB 501 - DPR - 2026-07-30.xlsx | 2026-07-30 13:10:48 | 728274
TB 408 - DPR - 2026-07-30.xlsx | 2026-07-30 10:54:43 | 1363571
TA 418 - DPR - 2026-07-21.xlsx | 2026-07-21 18:32:12 | 2198705
TA 416 - DPR - 2026-07-16.xlsx | 2026-07-16 12:59:02 | 5923315
TA 421 - DPR - 2026-07-11.xlsx | 2026-07-11 18:47:05 | 2294705
TA 515 - DPR - 2026-06-18.xlsx | 2026-06-19 05:07:09 | 1707206
TA 310 - DPR - 2026-01-12.xlsx | 2026-05-11 10:56:42 | 267127
TA 325 - DPR - 2026-01-19.xlsx | 2026-01-19 14:17:10 | 6635426

## Notes
Note
Q1 is Apr-Jun 2026. Q2-to-date is Jul 1-Aug 12 2026, using latest local DPR data through Aug 11 where available.
Foundation cumulative gap uses non-null Gap Cumulative from the existing Foundation Gap Monthly sheet as authoritative; blank foundation snapshots are excluded until computable.
Foundation delay days use Mechanism Evidence Audit and exclude negative delays from averages/medians.
Erection->Stringing gap uses ES Delay Detail, grouped by PO Start Date, and excludes negative lags from averages/medians.
git fetch origin failed with connection reset, so remote freshness could not be verified; local artifacts were rebuilt today after the latest raw DPR files.