## DailyExpanded
Work Date | Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name
2024-09-01 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-02 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-03 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-04 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-05 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-06 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-07 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-08 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-09 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-10 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-11 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-12 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-13 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-14 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-15 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-16 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-16 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-16 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-17 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-17 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-18 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-18 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-19 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-19 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-20 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-20 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-21 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-21 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-22 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-22 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-23 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-23 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-24 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-24 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-25 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-25 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-26 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-26 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-27 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-27 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-28 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-28 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-29 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-29 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-09-30 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-10-01 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-01 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-10-02 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-03 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-03 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-04 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-04 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-05 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-05 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-06 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-06 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-07 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-07 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-08 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-08 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-09 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-09 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-10 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-10 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-11 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-11 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-12 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-12 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-13 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-13 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-14 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-14 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-15 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-15 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-15 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-16 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-16 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-17 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-17 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-18 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-18 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-19 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-19 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-20 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2024-10-20 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-21 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2024-10-21 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-22 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2024-10-22 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-23 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2024-10-23 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-24 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2024-10-24 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-24 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-24 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-25 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-25 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-26 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-26 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-27 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-27 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-28 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-28 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-29 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-29 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-30 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-10-31 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-11-01 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2024-11-01 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-02 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2024-11-02 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-03 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2024-11-03 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-04 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2024-11-04 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-05 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-05 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-06 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-06 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-07 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-07 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-08 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-08 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-09 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-09 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-10 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-10 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-10 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-10 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-10 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-10 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-11 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-11 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-11 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-11 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-11 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-12 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-12 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-12 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-12 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-12 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-13 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-13 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-13 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-13 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-13 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-14 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-14 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-14 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-14 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-14 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-15 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-15 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-15 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-15 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-16 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-16 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-16 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-16 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-17 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-17 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-17 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-17 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-17 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-18 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-18 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-18 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-18 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-19 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-19 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-19 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-19 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-20 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-20 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-20 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-20 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-21 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-21 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-21 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-21 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-22 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-22 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-22 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-22 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-22 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-23 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-23 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-23 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-23 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-24 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-24 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-24 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-24 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-25 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-25 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-25 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-26 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-26 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-26 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-11-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-26 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-27 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-27 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-27 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-11-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-28 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-28 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-28 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-11-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-28 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-11-28 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-11-29 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-29 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-11-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-29 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-11-29 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-11-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-29 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-11-29 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-11-30 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-11-30 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-11-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-30 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-11-30 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-11-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-30 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-11-30 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-01 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-01 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-01 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-01 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-12-01 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-01 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-12-01 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-02 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-02 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-02 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-02 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-12-02 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-02 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-12-02 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-03 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-03 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-03 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-03 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-12-03 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-03 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-12-03 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-04 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-04 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-04 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-04 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-04 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-12-04 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-05 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-05 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-05 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-05 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-05 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-12-05 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-06 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-06 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-06 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-06 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-06 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-06 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-06 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-07 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-07 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-07 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-07 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-07 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-07 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-08 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-08 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-08 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-08 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-08 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-08 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-09 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-09 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-09 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-09 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-12-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-09 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-09 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-10 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-10 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-10 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-10 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-10 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-10 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-10 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-11 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-11 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-11 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-11 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-11 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-11 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-12 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-12 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-12 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-12 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-12 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-12 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-12 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2024-12-12 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-13 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-13 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-13 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-13 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-13 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2024-12-13 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-13 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-14 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-14 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-14 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-14 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-14 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2024-12-14 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-15 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-15 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-15 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-15 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-15 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2024-12-15 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-16 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-16 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-16 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-16 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-16 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2024-12-16 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-17 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-17 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-17 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-17 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-17 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-18 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-18 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-18 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-18 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-18 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-18 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-19 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-19 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-19 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-19 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-19 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-19 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-20 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-20 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-20 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-20 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-20 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-20 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-21 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-21 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-21 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-21 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-21 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-21 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-22 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-22 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-22 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-22 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-22 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-22 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-23 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-23 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-23 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-23 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-23 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-24 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-24 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-24 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-24 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-24 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-24 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2024-12-24 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-25 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-25 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-25 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-25 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-25 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-25 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2024-12-25 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-26 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-26 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-26 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-26 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-26 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-26 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2024-12-26 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-27 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-27 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-27 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-27 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-27 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-27 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2024-12-27 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-28 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2024-12-28 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-28 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-28 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-28 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-28 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2024-12-28 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2024-12-29 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2024-12-29 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-29 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-29 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-29 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-29 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2024-12-29 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2024-12-30 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2024-12-30 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-30 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-30 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-30 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-30 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2024-12-30 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2024-12-31 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2024-12-31 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-31 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-12-31 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-31 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2024-12-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-12-31 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2024-12-31 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-01 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2025-01-01 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2025-01-01 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-01 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-01 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-01 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-02 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2025-01-02 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2025-01-02 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-02 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-02 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-02 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-03 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2025-01-03 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2025-01-03 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-03 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-03 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-03 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-03 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-04 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2025-01-04 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-04 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-04 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-04 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-04 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-05 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-05 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-05 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-05 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-05 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-06 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-06 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-06 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-06 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-06 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-07 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-07 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-07 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-07 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-07 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-07 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-07 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-08 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-08 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-08 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-08 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-08 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-08 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-08 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-09 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-09 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-09 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-09 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-09 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-09 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-09 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-10 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-10 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-10 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-10 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-10 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-10 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-10 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-10 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-10 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-11 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-11 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-11 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-11 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-11 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-11 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-11 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-11 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-11 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-12 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-12 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-12 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-12 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-12 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-12 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-12 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-12 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-13 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-13 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-13 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-13 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-13 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-13 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-13 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-13 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-14 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-14 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-14 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-14 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-14 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-14 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-14 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-14 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-15 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-15 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-15 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-15 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-15 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-15 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-15 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-15 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-16 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-16 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-16 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-16 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-16 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-16 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-16 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-16 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-17 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-17 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-17 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-17 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-17 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-17 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-17 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-17 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-18 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-18 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-18 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-18 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-18 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-18 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-18 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-18 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-19 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-19 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-19 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-19 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-19 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-19 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-19 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-19 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-20 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-20 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-20 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-20 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-20 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-20 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-20 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-21 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-21 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-21 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-21 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-21 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-21 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-21 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-22 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-22 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-22 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-22 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-22 | 2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2025-01-22 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-22 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-23 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-23 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-23 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-23 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-23 | 2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2025-01-23 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-23 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-24 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-24 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-24 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-24 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-24 | 2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2025-01-24 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-24 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-25 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-25 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-25 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-25 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-25 | 2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2025-01-25 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-25 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-26 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-26 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-26 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-26 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-26 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-26 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-26 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-26 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-27 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-27 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-27 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-27 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-27 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-27 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-27 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-27 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-28 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-28 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-28 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-28 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-28 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-28 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-28 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-01-28 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-29 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-29 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-29 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-29 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-01-29 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-29 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-29 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-01-29 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-30 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-30 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-30 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-01-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-30 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-01-30 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-30 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-30 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-01-30 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-31 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-31 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-01-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-01-31 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-01-31 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-01-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-01-31 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-31 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-01-31 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-02-01 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-01 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-02-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-01 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-01 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-01 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-01 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-02 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-02-02 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-02 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-02-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-02 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-02 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-02 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-02 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-03 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-02-03 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-03 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-02-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-03 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-03 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-03 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-03 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-04 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-02-04 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-04 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-02-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-04 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-04 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-04 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-04 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-05 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-02-05 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-05 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-02-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-05 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-05 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-05 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-05 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-06 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-02-06 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-06 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-06 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-06 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-06 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-07 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-02-07 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-07 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-07 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-07 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-08 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-08 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-08 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-08 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-09 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-09 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-09 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-09 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-10 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-02-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-10 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-02-10 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-10 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-11 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-11 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-12 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-12 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-12 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-12 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-13 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-13 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-13 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-13 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-14 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-14 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-14 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-14 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-14 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-14 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-15 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-15 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-15 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-15 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-15 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-15 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-16 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-16 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-16 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-16 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-16 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-16 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-16 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-17 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-17 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-17 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-17 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-17 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-17 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-17 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-18 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-18 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-18 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-18 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-18 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-18 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-18 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-19 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-19 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-19 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-19 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-19 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-19 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-19 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-20 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-20 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-20 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-20 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-20 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-20 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-20 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-21 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-21 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-21 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416
2025-02-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-21 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-21 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-21 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-21 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-22 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-22 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416
2025-02-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-22 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-22 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-22 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-23 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-23 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416
2025-02-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-23 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-23 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-23 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-24 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-24 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416
2025-02-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-24 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-24 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-25 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-25 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416
2025-02-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-25 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-25 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-26 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-26 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-02-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-27 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-27 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416
2025-02-27 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-02-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-27 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-02-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-27 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-02-28 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-02-28 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416
2025-02-28 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-02-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-02-28 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-02-28 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-02-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-02-28 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-01 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-01 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416
2025-03-01 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-01 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-01 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-01 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-01 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-01 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-01 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416
2025-03-01 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-02 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-02 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416
2025-03-02 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-02 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-02 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-02 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-02 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-02 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-02 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416
2025-03-02 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-03 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-03 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416
2025-03-03 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-03 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-03 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-03 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-03 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-03 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-03 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416
2025-03-03 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-04 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-04 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-04 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-04 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-04 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-04 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-04 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-04 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416
2025-03-04 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-05 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-05 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-05 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-05 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-05 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-05 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-05 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-05 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416
2025-03-05 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-06 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-06 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-06 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-06 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-06 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-06 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-06 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-06 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-07 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-07 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-07 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-03-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-07 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-07 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-07 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-07 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-07 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-08 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-08 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-08 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2025-03-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-08 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-08 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-08 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-03-08 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2025-03-08 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-08 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-09 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-09 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-09 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2025-03-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-09 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-09 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2025-03-09 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-09 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-10 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-10 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-10 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2025-03-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-10 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-10 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-10 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2025-03-10 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-10 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-11 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-11 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-11 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2025-03-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-11 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-11 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-11 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2025-03-11 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-11 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-12 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-12 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-12 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-12 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-12 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-12 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2025-03-12 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-13 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-13 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-13 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-13 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-13 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-13 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-13 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-14 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-14 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-14 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-14 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-14 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-14 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-15 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-15 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-15 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-15 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-15 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-15 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-16 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-16 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-16 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-16 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-16 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-16 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-16 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-16 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-17 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-17 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-17 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-17 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-17 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-17 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-17 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-18 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-18 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-18 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-18 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-18 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-18 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-18 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-19 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-19 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-19 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-03-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-19 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-19 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-19 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-20 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-20 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-20 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-03-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-20 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-20 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-20 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-20 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-21 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-21 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-21 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-03-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-21 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-21 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-21 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-21 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-22 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-22 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-22 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-03-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-22 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-22 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-23 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-23 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-23 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-23 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-03-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-23 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-23 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-23 | 2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416
2025-03-23 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-24 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-24 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-24 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-24 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-24 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-24 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-24 | 2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416
2025-03-24 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-25 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-25 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-25 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-25 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-25 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-25 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-25 | 2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416
2025-03-25 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-26 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-26 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-26 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-26 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-26 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-26 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-26 | 2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416
2025-03-26 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-27 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-27 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-27 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-27 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-27 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-27 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-27 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-28 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-28 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-28 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-28 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-28 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-28 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-28 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-03-28 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-03-29 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-29 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-29 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-29 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-29 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-29 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-29 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-03-29 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-03-30 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-30 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-30 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-30 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-30 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-30 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-30 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-03-30 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-03-31 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-03-31 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-31 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-03-31 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-03-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-03-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-03-31 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-31 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-03-31 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-04-01 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-01 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-01 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-01 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-01 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-01 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-01 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-01 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-01 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-01 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-04-02 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-02 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-02 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-02 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-02 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-02 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-02 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-02 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-02 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-02 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-04-03 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-03 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-03 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-03 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-03 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-03 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-03 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-03 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-03 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-03 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-03 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-03 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-04-04 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-04 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-04 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-04 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-04 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-04 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-04 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-04 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-04 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-04 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-04 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-04 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-04-05 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-05 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-05 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-05 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-05 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-05 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-05 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-05 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-05 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-05 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-05 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-05 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-04-06 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-06 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-06 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-06 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-06 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-06 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-06 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-06 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-06 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-06 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-06 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-06 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-07 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-07 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-07 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-07 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-07 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-07 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-07 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-07 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-07 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-07 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-07 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-07 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-08 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-08 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-08 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-08 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-08 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-08 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-08 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-08 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-08 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-08 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-08 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-09 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-09 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-09 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-09 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-09 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-09 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-09 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-09 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-09 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-09 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-09 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-10 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-10 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-10 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-10 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-10 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-10 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-10 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-10 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-10 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-10 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-10 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-11 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-11 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-11 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-11 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-11 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-04-11 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-04-11 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-11 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-11 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-11 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-12 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-12 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-12 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-12 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-12 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-12 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-12 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-12 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-12 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-12 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-12 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-12 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-12 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-12 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-13 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-13 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-13 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-13 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-13 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-13 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-13 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-13 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-13 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-13 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-13 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-13 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-13 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-14 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-14 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-14 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-14 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-14 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-14 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-14 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-14 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-14 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-14 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-14 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-14 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-14 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-15 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-15 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-15 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-15 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-15 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-15 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-15 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-15 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-15 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-15 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-15 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-16 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-16 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-16 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-16 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-16 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-16 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-16 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-16 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-16 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-16 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-16 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-17 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-17 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-17 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-17 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-17 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-17 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-17 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-17 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-17 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-17 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-17 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-17 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-17 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-18 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-18 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-18 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-18 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-18 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-18 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-18 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-18 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-18 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-18 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-19 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-19 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-19 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-19 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-19 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-19 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-19 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-19 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-19 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-19 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-20 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-20 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-20 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-20 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-20 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-20 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-20 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-20 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-20 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-20 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-21 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-21 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-21 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-21 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-21 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-21 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-21 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-21 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-21 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-21 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-22 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-22 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-22 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-22 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-22 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-22 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-22 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-04-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-22 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-22 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-23 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-23 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-23 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-23 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-23 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-23 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-23 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-23 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-23 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-23 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-24 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-24 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-24 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-24 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-24 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-24 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-24 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-24 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-24 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-25 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-25 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-25 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-25 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-25 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-25 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-25 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-25 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-25 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-26 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-26 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-26 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416
2025-04-26 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-26 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-26 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-26 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-26 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-26 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-27 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-27 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-04-27 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416
2025-04-27 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-27 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-27 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-27 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-27 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-27 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-27 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-04-28 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-28 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-04-28 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416
2025-04-28 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-28 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-28 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-28 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-28 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-28 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-28 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-04-29 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-04-29 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-04-29 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416
2025-04-29 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-04-29 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-29 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-29 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-29 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-04-30 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-04-30 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-04-30 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-04-30 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-04-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-04-30 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-30 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-01 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-05-01 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-01 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-01 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-05-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-01 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-02 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-05-02 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-02 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416
2025-05-02 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-02 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-05-02 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416
2025-05-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-02 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-03 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-05-03 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-03 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416
2025-05-03 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-03 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-05-03 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416
2025-05-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-03 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-04 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-05-04 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-04 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416
2025-05-04 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-04 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416
2025-05-04 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-04 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-04 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-05 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-05-05 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-05 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416
2025-05-05 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-05 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416
2025-05-05 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-05 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-05 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-05 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-06 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-06 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416
2025-05-06 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-06 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416
2025-05-06 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-05-06 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-06 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-06 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-06 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-07 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-07 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-07 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-07 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-07 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-07 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-05-07 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-07 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-07 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-07 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-08 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-08 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-08 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-08 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-08 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-08 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-05-08 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-08 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-08 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-09 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-09 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-09 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-09 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-09 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-09 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-05-09 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-09 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-09 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-10 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-10 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-10 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-10 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-10 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-10 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-10 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-10 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-10 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-11 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-11 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-11 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-11 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-11 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-11 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416
2025-05-11 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-11 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-11 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-11 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-12 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-12 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-12 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-12 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-12 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-12 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-12 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416
2025-05-12 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-12 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-12 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-12 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-13 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-13 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-13 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-13 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-13 | 2025-05-13 | 2025-05-15 | Ananya Traders 2 | 42.3742 | 14.1247 | TA416
2025-05-13 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-13 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-13 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416
2025-05-13 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-13 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-13 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-13 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-14 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-14 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-14 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-14 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-14 | 2025-05-13 | 2025-05-15 | Ananya Traders 2 | 42.3742 | 14.1247 | TA416
2025-05-14 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-14 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-14 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-14 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416
2025-05-14 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-14 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-14 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-14 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-15 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-15 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-15 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-15 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-15 | 2025-05-13 | 2025-05-15 | Ananya Traders 2 | 42.3742 | 14.1247 | TA416
2025-05-15 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-15 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-15 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416
2025-05-15 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-15 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-15 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-15 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-16 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-16 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-16 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-16 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-16 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-16 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-16 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-16 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-16 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-16 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-16 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-16 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-17 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-17 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-17 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-17 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-17 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-17 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-17 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-17 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-17 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-17 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-17 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-17 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-18 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-18 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-18 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-18 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-18 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-18 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-18 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-18 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-18 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-18 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-18 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-18 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-19 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-19 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-19 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-19 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-19 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-19 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-19 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-19 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-19 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-19 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-19 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-19 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-20 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416
2025-05-20 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-20 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-20 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-20 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-20 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-20 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-20 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-20 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-20 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-20 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-21 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416
2025-05-21 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-21 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-21 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-21 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-21 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-21 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-21 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-21 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-21 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-21 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-22 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416
2025-05-22 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-22 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-22 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-22 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-22 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-22 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-22 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-22 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-22 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-22 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-23 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416
2025-05-23 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-23 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-23 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-23 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-23 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-23 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-23 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-23 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-24 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416
2025-05-24 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-24 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-24 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-24 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-24 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-24 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-24 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-24 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-24 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-24 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-25 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-25 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-25 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-25 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-25 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-25 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-25 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-25 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-25 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-25 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-26 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-26 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-26 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-26 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-26 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-26 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-26 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-26 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-27 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-27 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-27 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-05-27 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-27 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-27 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-27 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-27 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-27 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-28 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-28 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-05-28 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-05-28 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-28 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-28 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-05-28 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-28 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-28 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-05-28 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-28 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-29 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-29 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-05-29 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-05-29 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-29 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-05-29 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-29 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-05-29 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-29 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-30 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-30 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-05-30 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-05-30 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-05-30 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-30 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-05-30 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-05-30 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-30 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-05-30 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-30 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-31 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-31 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-05-31 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-05-31 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-05-31 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-05-31 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-05-31 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-05-31 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-05-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-05-31 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-05-31 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-06-01 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-01 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-06-01 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-01 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-01 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-06-01 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-01 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-06-01 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-06-02 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-02 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-06-02 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-02 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-02 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-06-02 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-02 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-06-02 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-06-03 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-03 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-03 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-03 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-03 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-03 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-06-03 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-03 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-06-03 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-06-04 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-04 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-04 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-04 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-04 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-04 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-06-04 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-04 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416
2025-06-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-04 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-06-05 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-05 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-05 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-05 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-05 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-05 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-05 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416
2025-06-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-05 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-05 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-06 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-06 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-06 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-06 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-06 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-06 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-06 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-06 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416
2025-06-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-06 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-06 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-07 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-07 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-07 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-07 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-07 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-07 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-07 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-07 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416
2025-06-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-07 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-07 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-08 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-08 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-08 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-08 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416
2025-06-08 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-08 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-08 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-08 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416
2025-06-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-08 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-08 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-09 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-09 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-09 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-09 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416
2025-06-09 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-09 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-09 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-09 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-09 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-09 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-10 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-10 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-10 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-10 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416
2025-06-10 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-10 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-10 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-10 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-10 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-10 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-11 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-11 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-11 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-11 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416
2025-06-11 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-11 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-11 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-11 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-11 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-12 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-12 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-12 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-12 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416
2025-06-12 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-12 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-12 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-12 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-12 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-13 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-13 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-13 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-13 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-13 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-13 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-13 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-13 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-14 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-14 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-14 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-14 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-14 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-14 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-14 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-14 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-15 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-15 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-15 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-15 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-15 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-15 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-15 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-15 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-16 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-16 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-16 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-16 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-16 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-16 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-16 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-16 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-17 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-06-17 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-17 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-17 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-17 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-17 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-17 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-17 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-18 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-18 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-18 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-18 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-18 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-18 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-19 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-19 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-19 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-19 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-19 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-06-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-19 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-20 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-20 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-20 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-20 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-20 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-20 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-20 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-21 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-21 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-21 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-21 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-21 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-21 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-21 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-22 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-22 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-22 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-22 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-22 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-22 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-22 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-23 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-23 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-23 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-23 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-23 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-23 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-23 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-24 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-24 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-24 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-24 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-24 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-24 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-24 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-25 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-25 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-25 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-25 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-25 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-25 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-25 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-26 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-26 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-26 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-26 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-26 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-26 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-26 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-27 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-27 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-27 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-27 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-27 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-28 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-28 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-28 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-28 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-28 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-29 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-29 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-29 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-29 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-06-29 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-30 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-06-30 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-06-30 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-06-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-01 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-01 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-07-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-02 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-02 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-07-02 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-02 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-02 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-03 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-03 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-07-03 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-03 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-03 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-04 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-04 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-07-04 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-04 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-04 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-05 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-05 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-05 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-07-05 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-05 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-05 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-06 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-06 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-06 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-06 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-06 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-07 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-07 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-07 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-07 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-07 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-08 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-08 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-08 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-08 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-09 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-09 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-09 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-09 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-10 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-10 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-10 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-10 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-11 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-11 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-11 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-11 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-12 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-12 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-12 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-12 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-13 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-13 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-13 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-13 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-14 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-14 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-14 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-14 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-15 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-15 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-15 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-15 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-16 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-16 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-16 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-16 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-17 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-17 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-17 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-17 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-18 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-18 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-07-18 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-18 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-19 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-19 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-19 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-19 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-20 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-20 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-20 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-20 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-21 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-21 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-21 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-21 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-22 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-22 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-22 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-22 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-23 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-23 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-23 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-24 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-24 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-24 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-25 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-25 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-25 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-26 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-26 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-26 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-27 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-27 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-27 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-28 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-28 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-28 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-07-28 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-29 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-29 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-29 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-07-29 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-30 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-30 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-30 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-07-30 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-31 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-31 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-07-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-07-31 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-07-31 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-08-01 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-01 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-01 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-02 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-02 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-02 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-03 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-03 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-03 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-04 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-04 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-04 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-05 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-05 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-05 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-06 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-06 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-06 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-07 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-07 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-07 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-08 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-08-08 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-08 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-09 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-09 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-10 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-10 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-11 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-08-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-11 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-12 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-12 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-13 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-13 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-14 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-14 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-15 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-15 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-16 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-16 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-16 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-17 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-17 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-17 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-18 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-18 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-18 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-19 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-19 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-19 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-20 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-20 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-20 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-21 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-21 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-21 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-22 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-22 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-22 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-23 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-23 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-23 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-24 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-24 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-24 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-25 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-25 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-25 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-26 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-26 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-26 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-27 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-27 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-27 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-28 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-28 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-28 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-29 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-29 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-29 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-30 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-30 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-30 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-08-31 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-31 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-08-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-08-31 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-09-01 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-01 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-09-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-01 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-09-02 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-02 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-09-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-02 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-09-03 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-03 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-09-04 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-04 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-09-05 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-06 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-07 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-08 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-09 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-10 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-11 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-12 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-13 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-14 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-09-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-09-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-09-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-10-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-10-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-11-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-11-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2025-12-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2025-12-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-01-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-01-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-02-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-02-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-03-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-03-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-04-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-04-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-05-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-05-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-06-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-06-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-07-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-07-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-08-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-08-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-09-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-09-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-26 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-26 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-27 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-27 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-28 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-28 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-29 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-29 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-30 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-30 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-10-31 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-10-31 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-01 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-01 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-02 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-02 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-03 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-03 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-04 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-04 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-05 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-05 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-06 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-06 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-07 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-07 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-08 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-08 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-09 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-09 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-10 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-10 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-11 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-11 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-12 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-12 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-13 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-13 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-14 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-14 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-15 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-15 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-16 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-16 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-17 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-17 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-18 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-18 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-19 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-19 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-20 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-20 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-21 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-21 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-22 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-22 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-23 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-23 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-24 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-24 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2026-11-25 | 2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2026-11-25 | 2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-01-28 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-01-29 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-01-30 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-01-31 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-01 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-01 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-02 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-02 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-03 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-03 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-03 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-04 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-04 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-04 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-05 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-05 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-05 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-06 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-06 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-06 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-07 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-07 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-07 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-08 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-08 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-08 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-09 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-09 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-09 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-09 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-10 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-10 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-10 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-10 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-11 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-11 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-11 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-11 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-12 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-12 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-12 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-12 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-13 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-13 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-13 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-13 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-13 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-14 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-14 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-14 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-14 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-15 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-15 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-15 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-15 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-15 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-15 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-16 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-16 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-16 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-16 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-17 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-17 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-17 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-17 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-17 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-18 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-18 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-18 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-18 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-18 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-18 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-19 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-19 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-19 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-19 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-19 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-20 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-20 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-20 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-20 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-20 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-20 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-20 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-21 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-21 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-21 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-21 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-21 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-21 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-22 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-22 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-22 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-22 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-22 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-22 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-23 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-23 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-23 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-23 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-23 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-24 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-24 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-24 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-24 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-24 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-24 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-24 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-24 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-25 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-25 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-25 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-25 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-25 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-26 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-26 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-26 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-26 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408
2024-02-26 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-26 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-26 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-02-27 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-27 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-27 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408
2024-02-27 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-27 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-02-28 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-28 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-28 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408
2024-02-28 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-28 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-02-29 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-02-29 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-29 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-02-29 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-02-29 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-29 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-29 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-03-01 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-01 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-01 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-01 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-02 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-02 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-02 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-02 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-03 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-03 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-03 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-03 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-04 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-04 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-04 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-04 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-05 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-05 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-05 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-06 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-06 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-06 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-06 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-07 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-07 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-07 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-03-07 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-08 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-08 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-08 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-09 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-09 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-09 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-10 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-10 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-10 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-11 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-11 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-11 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-11 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-11 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-11 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-12 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-12 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-12 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-13 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-13 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-13 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-14 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-14 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-14 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-15 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-15 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-15 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-15 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-16 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-16 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-16 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-16 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-17 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-17 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-17 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-18 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-18 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-18 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-18 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-19 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-19 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-19 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-20 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-20 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-20 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-20 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-21 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-21 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-21 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-21 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-22 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-22 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-22 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-22 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-22 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-23 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-23 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-23 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-23 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-23 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-24 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-24 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-24 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-24 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-25 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-25 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-25 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-25 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-26 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-26 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-26 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-26 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-26 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-26 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-27 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-27 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-27 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-27 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-28 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-28 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-28 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-28 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-29 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-29 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-29 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-30 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-30 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-30 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-30 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-31 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-31 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-31 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-31 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-03-31 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-04-01 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-01 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-01 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-04-01 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-02 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-02 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-02 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-04-02 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-03 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-03 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-03 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-04-03 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-03 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-04 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-04 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-04 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-04 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-05 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-05 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-05 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-06 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-06 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-06 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-06 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-06 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-07 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-07 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-07 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-07 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-07 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-07 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-08 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-08 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-08 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-08 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-09 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-09 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-09 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-10 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-10 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-10 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-10 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-11 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-11 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-11 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-12 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-12 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-13 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-13 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-13 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-14 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-14 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-15 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-15 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-15 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-16 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-16 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-16 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-16 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-17 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-17 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-17 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-17 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-17 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-18 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-18 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-18 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-18 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-18 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-19 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-19 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-19 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-19 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-19 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-20 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-20 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-20 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-20 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-20 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-21 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-21 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-21 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-21 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-21 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-21 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-22 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-22 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-22 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-22 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-22 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-22 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-22 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-23 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-23 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-23 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-23 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-23 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-24 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-24 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-24 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-24 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-24 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-25 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-25 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-25 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-25 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-25 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-26 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-26 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-26 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-26 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-27 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-27 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-27 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-27 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-27 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-27 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-28 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-28 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-28 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-28 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-29 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-29 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-29 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-04-29 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-29 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-30 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-30 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-04-30 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-30 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-05-01 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-05-01 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-01 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-01 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-05-02 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-05-02 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-02 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-02 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-05-03 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-05-03 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-03 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-03 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-05-03 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-04 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-04 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-04 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-05 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-05 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-05 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-05 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-05-05 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-06 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-06 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-06 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-07 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-07 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-07 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-08 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-08 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-08 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-09 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-09 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-09 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-10 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-10 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-10 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-11 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-11 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-11 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-11 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-12 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-12 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-12 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-12 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-12 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-13 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-13 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-13 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-13 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-14 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-14 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-14 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-14 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-15 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-15 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-15 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-15 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-16 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-16 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-16 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-16 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-16 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-17 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-17 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-17 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-17 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-18 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-18 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-18 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-18 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-18 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-19 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-19 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-19 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-19 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-19 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-20 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-20 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-20 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-20 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-21 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-21 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-21 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-21 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-22 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-22 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-22 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-22 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-23 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-23 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-23 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-23 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-24 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-24 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-24 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-25 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-25 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-25 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-26 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-26 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-26 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-27 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-27 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-27 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-28 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-28 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-28 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-29 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-05-29 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-29 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-29 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-30 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-05-30 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-30 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-30 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-31 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-05-31 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-06-01 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-01 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-02 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-02 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-03 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-03 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-04 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-04 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-05 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-05 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-06 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-06 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-07 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-07 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-08 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-08 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-09 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-09 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-10 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-10 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-11 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-11 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-12 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-12 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-13 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-13 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-14 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-14 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-15 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-15 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-16 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-16 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-17 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-17 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-18 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-18 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-19 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-19 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-20 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-21 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-22 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-23 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-24 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-25 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-26 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-06-27 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-07-04 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-05 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-06 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-07 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-08 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-09 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-10 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-11 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-12 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-15 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-16 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-17 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-18 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-19 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-20 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-21 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-22 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-23 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-24 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-25 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-07-26 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-08-13 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-14 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-15 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-16 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-17 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-18 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-19 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-20 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-20 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-21 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-22 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-23 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-23 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-24 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-24 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-25 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-25 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-26 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-26 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-27 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-27 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-28 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-28 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-28 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-08-28 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-29 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-29 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-29 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-08-29 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-30 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-30 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-30 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-08-30 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-30 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-08-31 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-08-31 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-31 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-08-31 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-08-31 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-01 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-01 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-01 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-01 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-01 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-02 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-02 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-02 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-02 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-02 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-03 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-03 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-03 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-03 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-03 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-04 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-04 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-04 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-04 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-04 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-05 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-05 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-05 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-05 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-05 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-06 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-06 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-09-06 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-06 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-06 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-06 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-07 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-07 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-07 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-07 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-07 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-08 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-08 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-08 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-08 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-09-08 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-08 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-09-09 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-09 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-09 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-09 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-09 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-10 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-10 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-10 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-10 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-10 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-11 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-11 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-11 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-11 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-11 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-12 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-12 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-12 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-12 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-12 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-13 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-13 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-13 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-13 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-13 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-14 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-14 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-14 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-14 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-15 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-15 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-15 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-15 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-16 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-16 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-16 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-16 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-17 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-17 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-17 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-17 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-18 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-18 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-18 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-18 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-18 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-09-19 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-19 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-19 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-19 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-19 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-19 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-19 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-20 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-20 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-20 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-20 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-20 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-21 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-21 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-21 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-21 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-21 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-21 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-22 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-22 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-22 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-22 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-22 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-22 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-23 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-23 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-23 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-23 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-23 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-23 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-24 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-24 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-24 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-24 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-24 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-24 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-25 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-25 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-25 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-25 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-25 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-25 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-25 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-26 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-26 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-26 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-26 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-26 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-26 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-27 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-27 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-27 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-27 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-09-27 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-27 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-28 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-28 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-28 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-28 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-09-28 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-09-28 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-09-28 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-28 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-29 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-29 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-29 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-29 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-09-29 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-09-29 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-09-29 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-29 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-30 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-30 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-30 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-09-30 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-09-30 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-09-30 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-30 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-01 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-01 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-10-01 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-01 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-10-01 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-01 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-10-01 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-02 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-02 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-10-02 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-02 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-10-02 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-02 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-02 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-03 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-03 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-10-03 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-03 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-10-03 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-03 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-03 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-04 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-04 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-04 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-04 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-04 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-04 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-10-05 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-05 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-05 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-05 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-05 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-05 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-05 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-06 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-06 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-06 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-06 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-06 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-06 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-06 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-07 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-07 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-07 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-07 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-07 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-07 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-07 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-07 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-07 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-07 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-08 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-08 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-08 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-08 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-08 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-08 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-08 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-08 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-09 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-09 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-09 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-09 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-09 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-09 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-10 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-10 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-10 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-10 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-10 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-10 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-10 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-11 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-11 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-11 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-11 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-11 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-11 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-12 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-12 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-12 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-12 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-12 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-12 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-12 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-13 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-13 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-13 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-13 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-13 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-13 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-13 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-13 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-14 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-14 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-14 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-14 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-14 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-14 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-14 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-14 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-15 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-15 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-15 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-15 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-15 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-15 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-15 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-15 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-16 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-16 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-16 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-16 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-16 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-16 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-16 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-16 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-17 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-17 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-17 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-17 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-17 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-17 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-17 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-17 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-18 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-18 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-18 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-18 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-18 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-18 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-18 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-18 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-18 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-18 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-19 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-19 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-19 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-19 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-19 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-19 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-10-19 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-19 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-19 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-19 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-19 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-20 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-20 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-20 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-20 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-20 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-20 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-20 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-20 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-20 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-20 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-21 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-21 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-21 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-21 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-21 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-21 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-21 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-21 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-21 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-21 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-21 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-22 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-22 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-22 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-22 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-22 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-22 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-22 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-22 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-22 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-22 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-22 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-23 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-23 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-23 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-23 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-23 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-23 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-23 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-23 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-23 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-23 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-23 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-24 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-24 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-24 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-24 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-24 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-24 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-24 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-24 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-24 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-24 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-24 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-24 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-25 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-25 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-25 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-25 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-25 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-25 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-25 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-25 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-25 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-25 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-26 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-26 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-26 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-26 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-26 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-26 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-26 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-26 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-26 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-26 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-27 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-27 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-27 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-27 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-27 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-27 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-27 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-27 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-10-28 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-28 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-28 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-28 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-28 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-28 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-10-29 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-29 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-29 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-29 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-29 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-29 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-10-30 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-30 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-30 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-30 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-30 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-10-31 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-31 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-31 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-10-31 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-11-01 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-11-01 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-01 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-11-01 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-01 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-01 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-11-01 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-02 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-11-02 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-02 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-02 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-11-02 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-02 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-02 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-11-02 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-03 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-03 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-11-03 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-03 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-03 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-03 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-03 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-04 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-04 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-11-04 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-04 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-04 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-04 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-04 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-04 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-04 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-05 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-05 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-11-05 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-05 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-05 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-05 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-05 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-05 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-05 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-06 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-06 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-06 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-06 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-06 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-06 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-06 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-06 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-07 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-07 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-07 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-07 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-07 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-07 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-07 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-07 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-07 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-08 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-08 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-08 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-08 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-08 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-08 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-08 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-08 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-08 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-09 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-09 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-09 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-09 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-09 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-09 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-09 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-09 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-09 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-10 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-10 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-10 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-10 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-10 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-10 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-10 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-11 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-11 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-11 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-11 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-11 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-11 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-11 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-11 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-12 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-12 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-12 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-12 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-12 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-12 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-12 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-12 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-12 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-13 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-13 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-13 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-13 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-13 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-13 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-13 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-13 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-13 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-13 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-14 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-14 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-14 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-14 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-14 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-14 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-14 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-14 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-14 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-15 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-15 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-15 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-15 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-15 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-15 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-15 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-15 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-16 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-16 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-16 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-16 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-16 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-16 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-16 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-16 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-17 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-17 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-17 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-17 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-17 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-17 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-17 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-17 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-17 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-18 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-18 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-18 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-18 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-18 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-18 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-18 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-18 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-18 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-19 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-19 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-19 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-19 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-19 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-19 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-20 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-20 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-20 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-20 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-20 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-20 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-21 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-21 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-21 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-21 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-21 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-22 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-22 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-22 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-22 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-22 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-22 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-23 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-23 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-23 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-23 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-23 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-24 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-24 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-24 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-24 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-24 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-24 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-24 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-25 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-25 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-25 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-25 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-25 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-25 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-25 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-26 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-26 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-26 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-26 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-26 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-26 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-26 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-27 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-27 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-27 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-27 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-27 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-27 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-27 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-27 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-28 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-28 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-28 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-28 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-11-28 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-28 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-28 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-29 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-29 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-29 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-29 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-11-29 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-29 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-29 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-30 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-30 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-30 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-11-30 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-11-30 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-11-30 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-30 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-30 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-01 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-01 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-01 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-01 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-01 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-12-02 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-02 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-02 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-02 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-02 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-12-02 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-03 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-03 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-03 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-03 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-03 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-12-03 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-03 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-04 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-04 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-04 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-04 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-04 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-04 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-05 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-05 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-05 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-05 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-05 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-05 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-12-06 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-06 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-06 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-06 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-06 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-12-07 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-07 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-07 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-07 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-12-08 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-08 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-08 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-12-09 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-09 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-09 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-09 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-09 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-12-10 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-10 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-10 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-10 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-11 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-11 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-11 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-11 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-12 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-12 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-12 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-13 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-13 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-13 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-14 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-14 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-15 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-15 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-16 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-16 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-20 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-21 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-22 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-23 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-24 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-25 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-25 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-25 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-26 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-26 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-26 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-27 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-27 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-27 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-28 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-28 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-28 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-29 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-29 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-29 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-30 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-30 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-30 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2024-12-31 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-31 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-31 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-01 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2025-01-01 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2025-01-01 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-02 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2025-01-02 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2025-01-02 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-03 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-03 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2025-01-03 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2025-01-03 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-04 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-04 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2025-01-04 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-04 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2025-01-04 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-05 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-05 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-05 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-05 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-06 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-06 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-06 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-06 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-07 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-07 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-07 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-07 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-08 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-08 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-08 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-08 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-09 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-09 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-09 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-09 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-10 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-10 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-10 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-10 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-11 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-11 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-11 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-11 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-11 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-11 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-12 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-12 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-12 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-12 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-12 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-12 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-13 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-13 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-13 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-13 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-13 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-13 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-14 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-14 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-14 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-14 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-14 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-14 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-15 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-15 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-15 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-15 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-15 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-15 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-16 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-16 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-16 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-16 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-16 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-16 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-17 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-17 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-17 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-17 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-17 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-17 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-18 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-18 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-18 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-18 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-18 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-19 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-19 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-19 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-19 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-19 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-20 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-20 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-20 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-21 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-21 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-21 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-21 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-22 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-22 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-22 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-22 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-23 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-23 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-23 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-23 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-24 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-24 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-24 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-24 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-25 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-25 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-25 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-25 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-26 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-26 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-26 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-26 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-27 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-27 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-27 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-27 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-28 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-28 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-28 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-28 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-29 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-29 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-29 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-29 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-29 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-01-30 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-30 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-30 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-01-31 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-01-31 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-31 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-01-31 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-01 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-01 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-02-01 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-01 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-02 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-02 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-02-02 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-02 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-02 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-03 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-03 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-03 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-03 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-04 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-04 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-04 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-04 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-05 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-05 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-05 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-05 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-05 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-06 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-06 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-02-06 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-06 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-06 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-07 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-07 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-07 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-07 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-02-08 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-08 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-08 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-08 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-09 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-09 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-09 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-09 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-10 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-10 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-10 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-10 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-11 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-11 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-11 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-11 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-12 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-12 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-12 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-12 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-13 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-13 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-13 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-13 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-14 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-14 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-14 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-14 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-15 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-15 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-15 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-16 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-16 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-16 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-17 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-17 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-17 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-18 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-18 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-18 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-19 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-19 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-19 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-20 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-20 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-20 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-21 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-21 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-22 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-22 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-23 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-23 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-24 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-24 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-25 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-25 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-26 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-26 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-26 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-02-27 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-27 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-27 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-02-28 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-28 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-28 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-01 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-01 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-01 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-02 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-02 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-02 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-03 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-03 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-03 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-04 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-04 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-04 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-05 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-05 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-05 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-06 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-06 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-06 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-07 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-03-07 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-07 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-08 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-08 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-08 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-09 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-09 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-09 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-09 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-10 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-10 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-10 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-10 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-11 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-11 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-11 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-12 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-12 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-12 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-13 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-13 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-13 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-13 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-14 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-14 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-14 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-14 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-15 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-15 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-15 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-15 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-16 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-16 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-16 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-16 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-17 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-17 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-17 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-18 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-18 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-18 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-19 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-19 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-19 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-20 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-20 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-20 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-20 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-21 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-21 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-21 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-21 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-22 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-22 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-22 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-22 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-23 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-23 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-23 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-23 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-24 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-24 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-24 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-24 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-25 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-25 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-25 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-25 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-26 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-26 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-26 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-26 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-27 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-27 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-27 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-27 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-28 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-28 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-28 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-28 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-29 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-29 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-29 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-29 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-30 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-30 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-30 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-03-31 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-31 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-31 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-31 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408
2025-03-31 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-01 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-01 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408
2025-04-01 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-02 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-02 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-02 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408
2025-04-02 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-03 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-03 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-03 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-03 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-04 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-04 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-04 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-04 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-05 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-05 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-05 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-06 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-06 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-06 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-06 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-07 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-07 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-07 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-08 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-08 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-08 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-09 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-09 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-09 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-10 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-10 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-11 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-04-11 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-12 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-12 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-13 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-13 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-14 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-14 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-15 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-16 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-17 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-18 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-19 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-20 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-21 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-22 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-23 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-24 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-25 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-26 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-27 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-04-27 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-28 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-04-28 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-29 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-04-30 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-05-01 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-05-02 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-07-10 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-11 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-12 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-13 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-14 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-15 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-16 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-17 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-18 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-18 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-19 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-19 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-20 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-21 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-22 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-23 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-24 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-25 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-26 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-27 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-27 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-07-28 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-28 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-07-29 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-07-30 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-07-31 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-08-01 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-08-02 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-08-02 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-03 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-08-03 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-04 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-05 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-06 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-07 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-08 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-09 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-09 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-10 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-11 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-12 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-13 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-14 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-16 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421
2024-08-17 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421
2024-08-18 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421
2024-08-19 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-20 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-21 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-22 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-22 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-23 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-23 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-24 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-24 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-25 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-26 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-27 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-28 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-29 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-29 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-08-29 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-08-30 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-08-30 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-08-31 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-08-31 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-01 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-09-01 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-02 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-09-02 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-03 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-09-03 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-04 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-09-04 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-05 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-09-05 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-06 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-09-06 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-07 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-08 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-09 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-09 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-10 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-10 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-11 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-11 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-12 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-12 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-13 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-14 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-14 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-14 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-15 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-15 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-15 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-16 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-16 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-16 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-17 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-17 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-17 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-18 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-18 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-18 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-19 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-19 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421
2024-09-19 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-19 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-20 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421
2024-09-20 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-20 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-21 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421
2024-09-21 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-21 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-22 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421
2024-09-22 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-23 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421
2024-09-23 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-24 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421
2024-09-24 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-25 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421
2024-09-25 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-26 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421
2024-09-26 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-26 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-09-27 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421
2024-09-27 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-27 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-09-28 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421
2024-09-28 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-28 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-09-29 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421
2024-09-29 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-29 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-09-30 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421
2024-09-30 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-30 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-10-01 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-01 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421
2024-10-01 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-01 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-01 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-10-02 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-02 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421
2024-10-02 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-02 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-02 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-10-03 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-03 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421
2024-10-03 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421
2024-10-03 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-03 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-03 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-10-04 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-04 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421
2024-10-04 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-04 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-05 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-05 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421
2024-10-05 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-05 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-05 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-05 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-06 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-06 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421
2024-10-06 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-06 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-06 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-06 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-07 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-07 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421
2024-10-07 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-07 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-07 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-07 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-08 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-08 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-08 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-08 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-08 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-09 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-09 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-09 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-09 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-09 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-10 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-10 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-10 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-10 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-10 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-11 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-11 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-11 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-11 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-11 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-12 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-12 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-12 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-12 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-12 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-13 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-13 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-13 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-13 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-13 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-14 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-14 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-14 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-14 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-14 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-15 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-15 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-15 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-16 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-16 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-16 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-16 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-16 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-17 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-17 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-17 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-17 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-17 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-17 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-18 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-18 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-18 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-18 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-18 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-18 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-19 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-19 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-19 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-19 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-19 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-19 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-19 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-20 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-20 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-20 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-20 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-20 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-20 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-21 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-21 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-21 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-21 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-21 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-21 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-21 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-22 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-22 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-22 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-22 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-22 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-22 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-23 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-23 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-23 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-23 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-23 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-23 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-24 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-24 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-24 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-24 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-24 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-24 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-25 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-25 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-25 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-25 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-25 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-25 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-26 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-26 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-26 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-26 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-26 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-26 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-27 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-27 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-10-27 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-27 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-10-27 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-27 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-28 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-10-28 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-28 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-10-28 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-29 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-10-29 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-29 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-10-29 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-30 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-10-30 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-30 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-10-30 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-31 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-10-31 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-10-31 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-11-01 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-11-01 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-01 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-01 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-11-02 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-11-02 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-02 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-02 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-03 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-11-03 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-03 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-03 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-04 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-11-04 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-04 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-04 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-05 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-05 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-11-05 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-05 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-05 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-06 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-06 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-11-06 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-06 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-06 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-07 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-07 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-11-07 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-07 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-07 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-07 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-08 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-08 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-08 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-08 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-09 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-09 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-09 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-09 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-09 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-10 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-10 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-10 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-10 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-10 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-11 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-11 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-11 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-11 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-11 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-12 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-12 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-12 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-12 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-12 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-12 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-13 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-13 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-13 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-13 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-13 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-13 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-14 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-14 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-14 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-14 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-14 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-14 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-15 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-15 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-15 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-15 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-15 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-16 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-16 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-16 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-16 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-16 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-17 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-17 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-17 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-17 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-17 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-18 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-18 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-18 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-18 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-18 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-19 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-19 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-19 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-19 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-19 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-20 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-20 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-20 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-20 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-20 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-21 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-21 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-21 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-21 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-21 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-22 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-22 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-22 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-22 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-22 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-23 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-23 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-23 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-23 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-23 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-24 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-24 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-24 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-24 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-24 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-24 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-25 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-25 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-25 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-25 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-25 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-26 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-26 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-26 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-26 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-26 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-11-27 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-27 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-27 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-27 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-11-28 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-28 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-28 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-28 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-11-29 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-29 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-29 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-29 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-11-30 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-30 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-30 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-11-30 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-12-01 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-12-01 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-12-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-02 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-12-02 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-12-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-03 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-03 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-12-03 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421
2024-12-03 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-04 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-04 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-12-04 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421
2024-12-04 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-05 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-05 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-12-05 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421
2024-12-05 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-06 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-06 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421
2024-12-06 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-07 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-07 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-07 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-08 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-08 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-08 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-09 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-09 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421
2024-12-09 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-10 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-10 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421
2024-12-10 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-11 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-11 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421
2024-12-11 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-11 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421
2024-12-12 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-12 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421
2024-12-12 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-12 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421
2024-12-13 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-13 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421
2024-12-13 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-13 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421
2024-12-14 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-14 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-14 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421
2024-12-15 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-15 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421
2024-12-15 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-15 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421
2024-12-16 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-16 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421
2024-12-16 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-16 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421
2024-12-17 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-17 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421
2024-12-17 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-17 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421
2024-12-18 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-18 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421
2024-12-18 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-18 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421
2024-12-19 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-19 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421
2024-12-19 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-19 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421
2024-12-20 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-20 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-20 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-20 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421
2024-12-21 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-21 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-21 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-21 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421
2024-12-22 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-22 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-22 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-22 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421
2024-12-23 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-23 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-23 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-23 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421
2024-12-24 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-24 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-24 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-24 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421
2024-12-25 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-25 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-25 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-25 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421
2024-12-26 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-26 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-26 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-26 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421
2024-12-27 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-27 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-27 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-27 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421
2024-12-27 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2024-12-28 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-28 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-28 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-28 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421
2024-12-28 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2024-12-28 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2024-12-29 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-29 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-29 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2024-12-29 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2024-12-30 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-30 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-30 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2024-12-30 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2024-12-31 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2024-12-31 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-31 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2024-12-31 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-01 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-01 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2025-01-01 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-02 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-02 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2025-01-02 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-03 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-03 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2025-01-03 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-03 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2025-01-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-04 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-04 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-04 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-04 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2025-01-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-05 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-05 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-05 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-05 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2025-01-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-06 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-06 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-06 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-06 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2025-01-07 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-07 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-07 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-07 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2025-01-08 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-08 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-08 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-08 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2025-01-09 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-09 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-09 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-10 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-10 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-10 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-11 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-11 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-11 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-12 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-12 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-12 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-13 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-13 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-13 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-14 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-14 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-14 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421
2025-01-15 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-15 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-15 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421
2025-01-16 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421
2025-01-16 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-16 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421
2025-01-17 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421
2025-01-17 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-17 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421
2025-01-18 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421
2025-01-18 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-18 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421
2025-01-18 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421
2025-01-19 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421
2025-01-19 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421
2025-01-19 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-19 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421
2025-01-20 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421
2025-01-20 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-20 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421
2025-01-21 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421
2025-01-21 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-21 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421
2025-01-22 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421
2025-01-22 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-22 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421
2025-01-22 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-22 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-23 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421
2025-01-23 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-23 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-23 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-23 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-24 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-24 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-24 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-24 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-25 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-25 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-25 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-25 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-26 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-26 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-26 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-26 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-27 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-27 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-27 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-27 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-28 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-28 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-01-28 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-28 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-29 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-01-29 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-29 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-30 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-01-30 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-30 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-01-30 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-30 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421
2025-01-31 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-01-31 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-01-31 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421
2025-02-01 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-02-01 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-01 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421
2025-02-02 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-02-02 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-02 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421
2025-02-03 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-02-03 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-03 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421
2025-02-04 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-02-04 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-04 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421
2025-02-05 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-02-05 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-05 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421
2025-02-06 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-02-06 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-06 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421
2025-02-07 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-02-07 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-07 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421
2025-02-08 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-02-08 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-08 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421
2025-02-09 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-02-09 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-09 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421
2025-02-10 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-10 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421
2025-02-10 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-10 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421
2025-02-11 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-11 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421
2025-02-11 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-11 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421
2025-02-12 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-12 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421
2025-02-12 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-12 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421
2025-02-13 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-13 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421
2025-02-13 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-13 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-14 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-14 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421
2025-02-14 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-14 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-15 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-15 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-15 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-15 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-16 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-16 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-16 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-16 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-17 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-17 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-17 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-17 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-18 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-18 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-18 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-18 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-19 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-19 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-19 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-19 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-19 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421
2025-02-20 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-20 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-20 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-20 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421
2025-02-21 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-21 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421
2025-02-21 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-21 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421
2025-02-22 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-22 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421
2025-02-22 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-22 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421
2025-02-23 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-23 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421
2025-02-23 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-23 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421
2025-02-24 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-24 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421
2025-02-24 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-24 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421
2025-02-25 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-25 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421
2025-02-25 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-25 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421
2025-02-26 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421
2025-02-26 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421
2025-02-26 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-26 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421
2025-02-27 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421
2025-02-27 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421
2025-02-27 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-27 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421
2025-02-28 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421
2025-02-28 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421
2025-02-28 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-28 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421
2025-03-01 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421
2025-03-01 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-01 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421
2025-03-01 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-03-01 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421
2025-03-02 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421
2025-03-02 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-02 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-02 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421
2025-03-03 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-03 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-03 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-03 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-03 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421
2025-03-04 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-04 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-04 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-04 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-04 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421
2025-03-05 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-05 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-05 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-05 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-05 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421
2025-03-06 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-06 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-06 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-06 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-06 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421
2025-03-07 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-07 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-07 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-07 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-07 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421
2025-03-08 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-08 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-08 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421
2025-03-08 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-08 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421
2025-03-09 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-09 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-09 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421
2025-03-09 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-09 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421
2025-03-10 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-10 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-10 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421
2025-03-10 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-10 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421
2025-03-11 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-11 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-11 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421
2025-03-11 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-11 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421
2025-03-12 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-12 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-12 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421
2025-03-12 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-12 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421
2025-03-13 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-13 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-13 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421
2025-03-13 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-13 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421
2025-03-14 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-14 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421
2025-03-14 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-14 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421
2025-03-15 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421
2025-03-15 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-15 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421
2025-03-15 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-15 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421
2025-03-16 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421
2025-03-16 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-16 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421
2025-03-16 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-16 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421
2025-03-16 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421
2025-03-17 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421
2025-03-17 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-17 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421
2025-03-17 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-17 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-17 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421
2025-03-18 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421
2025-03-18 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-18 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-18 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-18 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421
2025-03-19 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421
2025-03-19 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-19 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-19 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-19 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421
2025-03-20 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-20 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-20 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-20 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-20 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421
2025-03-21 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-21 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-21 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-21 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-21 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421
2025-03-22 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-22 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-22 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-22 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-22 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421
2025-03-23 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-23 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-23 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-23 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421
2025-03-23 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-23 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421
2025-03-24 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-24 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-24 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421
2025-03-24 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-24 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421
2025-03-25 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-25 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-25 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421
2025-03-25 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-25 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421
2025-03-26 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-26 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-26 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421
2025-03-26 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-26 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421
2025-03-27 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-27 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-27 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421
2025-03-27 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-27 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421
2025-03-28 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-28 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-28 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421
2025-03-28 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-03-28 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421
2025-03-29 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-29 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-03-29 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-29 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421
2025-03-29 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-03-29 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421
2025-03-29 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421
2025-03-30 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-03-30 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-30 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-03-30 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421
2025-03-30 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-03-30 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421
2025-03-31 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-03-31 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-03-31 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421
2025-03-31 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-03-31 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421
2025-04-01 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-01 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-04-01 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421
2025-04-01 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-01 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421
2025-04-02 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-02 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-04-02 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-02 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-02 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421
2025-04-03 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-03 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-04-03 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-03 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-03 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-04 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-04 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-04-04 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-04 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-04 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-05 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-05 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-04-05 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-05 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-05 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-06 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-06 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-06 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-06 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-06 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-07 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-07 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-07 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-07 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-07 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-08 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-08 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-08 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-08 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-08 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-09 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-09 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-09 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-09 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-09 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-10 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-10 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-10 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421
2025-04-10 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-10 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-04-11 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-11 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-11 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421
2025-04-11 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-11 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421
2025-04-12 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-12 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-12 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421
2025-04-12 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-12 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421
2025-04-13 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-13 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-13 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421
2025-04-13 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-13 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421
2025-04-14 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-14 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-14 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421
2025-04-14 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-14 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421
2025-04-15 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-15 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-15 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421
2025-04-15 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-15 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421
2025-04-16 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-16 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-16 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421
2025-04-16 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-16 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421
2025-04-17 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-17 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-17 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421
2025-04-17 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-17 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421
2025-04-18 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-18 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-18 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421
2025-04-18 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-18 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421
2025-04-19 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-19 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-19 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421
2025-04-19 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-19 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421
2025-04-19 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421
2025-04-20 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-20 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-20 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421
2025-04-20 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-20 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421
2025-04-21 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-21 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-21 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421
2025-04-21 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-21 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421
2025-04-22 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-22 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-22 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421
2025-04-22 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-22 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421
2025-04-23 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-23 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-23 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421
2025-04-23 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-23 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421
2025-04-24 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-24 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-24 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421
2025-04-24 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-24 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421
2025-04-25 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-25 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-25 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421
2025-04-25 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-25 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421
2025-04-26 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-26 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-26 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421
2025-04-26 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-26 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421
2025-04-27 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-27 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-27 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421
2025-04-27 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-04-27 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421
2025-04-28 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-28 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421
2025-04-28 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-04-28 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421
2025-04-29 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-29 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421
2025-04-29 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-04-29 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421
2025-04-30 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-30 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421
2025-04-30 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-04-30 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421
2025-05-01 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421
2025-05-01 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-01 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421
2025-05-02 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421
2025-05-02 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421
2025-05-02 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-02 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421
2025-05-03 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421
2025-05-03 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-05-03 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-03 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421
2025-05-04 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421
2025-05-04 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-05-04 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-04 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421
2025-05-05 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421
2025-05-05 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-05-05 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-05 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421
2025-05-06 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421
2025-05-06 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-05-06 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-06 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421
2025-05-07 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421
2025-05-07 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-05-07 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-07 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421
2025-05-08 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-08 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421
2025-05-08 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-05-08 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-08 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421
2025-05-09 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-09 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421
2025-05-09 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-09 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421
2025-05-10 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-10 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421
2025-05-10 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421
2025-05-10 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-10 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421
2025-05-10 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421
2025-05-11 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-11 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-11 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-11 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421
2025-05-11 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-11 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421
2025-05-12 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-12 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-12 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-12 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421
2025-05-12 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-12 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421
2025-05-13 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-13 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-13 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-13 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421
2025-05-13 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-13 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421
2025-05-14 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-14 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-14 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-14 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421
2025-05-14 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-14 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421
2025-05-15 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-15 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-15 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-15 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-15 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-15 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421
2025-05-16 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-16 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-16 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-16 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-16 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-16 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421
2025-05-17 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-17 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-17 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-17 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-17 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421
2025-05-18 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-18 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-18 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-18 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-18 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421
2025-05-19 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-19 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-19 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-19 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-19 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421
2025-05-20 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-20 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-20 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-20 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-20 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421
2025-05-21 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-21 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-21 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-21 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-21 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-22 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-22 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-22 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-22 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-22 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-23 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-23 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-23 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-23 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-24 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-24 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-24 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-24 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-25 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-25 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-25 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-26 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-26 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-26 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-27 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-27 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-27 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-28 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-28 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-28 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-29 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-29 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-29 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421
2025-05-30 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-30 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-30 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421
2025-05-31 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-31 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-05-31 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421
2025-06-01 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-01 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-06-01 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421
2025-06-02 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-02 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-06-02 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421
2025-06-03 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-03 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-06-03 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-04 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-04 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-06-04 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-05 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-05 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-05 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-05 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-06 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-06 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-06 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-06 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-06 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-07 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-07 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-07 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-07 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-08 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-08 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-08 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-08 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-09 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-09 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-09 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-09 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-10 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-10 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-10 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-10 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-11 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-11 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-11 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-11 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-12 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-12 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-12 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-13 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-13 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-13 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-14 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-14 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-14 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-15 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-15 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-15 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-16 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-16 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-16 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-17 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-17 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-17 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-18 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-18 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-18 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-19 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-19 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-19 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-20 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-20 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-20 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-21 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-21 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-21 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-22 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-22 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-22 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-23 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-23 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-23 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-24 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-24 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-24 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-24 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-24 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-25 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-25 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-25 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-25 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-25 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-25 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421
2025-06-26 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-26 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-26 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-26 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-26 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421
2025-06-27 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-27 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-27 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-27 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-27 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421
2025-06-28 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-28 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-28 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-28 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-28 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421
2025-06-29 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-29 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-29 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-29 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-29 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421
2025-06-30 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-30 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-30 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-30 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-06-30 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421
2025-07-01 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-07-01 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-07-01 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-07-01 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-01 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421
2025-07-02 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-07-02 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-07-02 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-07-02 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-02 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421
2025-07-03 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-07-03 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-07-03 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-07-03 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-03 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421
2025-07-04 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-07-04 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-07-04 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-04 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-07-04 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-04 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421
2025-07-05 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-05 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-07-05 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-05 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-05 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421
2025-07-06 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-06 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-06 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-06 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-06 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421
2025-07-07 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-07 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-07 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-07 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-07 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421
2025-07-08 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-08 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-08 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-08 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-09 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-09 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-09 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-09 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-10 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-10 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-10 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
2025-07-10 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-11 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-11 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-11 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421
2025-07-11 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-12 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-12 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-12 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
2025-07-12 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421
2025-07-12 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-13 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-13 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-13 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-13 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421
2025-07-13 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-13 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421
2025-07-14 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-14 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-14 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-14 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421
2025-07-14 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-14 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-14 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421
2025-07-15 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-15 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-15 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-15 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421
2025-07-15 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421
2025-07-15 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-15 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-15 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421
2025-07-16 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-16 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-16 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-16 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421
2025-07-16 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-16 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-16 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421
2025-07-17 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-17 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-17 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-17 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421
2025-07-17 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-17 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-17 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421
2025-07-18 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-18 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-18 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-18 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421
2025-07-18 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-18 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-18 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421
2025-07-19 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-19 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-19 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-19 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421
2025-07-19 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-19 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-19 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421
2025-07-20 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-20 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-20 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-20 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421
2025-07-20 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-20 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-20 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421
2025-07-21 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-21 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-21 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-21 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421
2025-07-21 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-21 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-21 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421
2025-07-22 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-22 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-22 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-22 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-22 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-22 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-22 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421
2025-07-23 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-23 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-23 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-23 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-23 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-23 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-23 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421
2025-07-24 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-24 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-24 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-24 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-24 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-24 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-24 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421
2025-07-25 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-25 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-25 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-25 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-25 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-25 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-25 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421
2025-07-26 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-26 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-26 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-26 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-26 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-26 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-26 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-07-27 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-27 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-27 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-27 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-27 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-27 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-27 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-07-28 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-28 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-28 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-28 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-28 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-28 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-28 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-07-29 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-29 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-29 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-29 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421
2025-07-29 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-29 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-29 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-07-30 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-07-30 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-30 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-30 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421
2025-07-30 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421
2025-07-30 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-30 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-07-31 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-07-31 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-07-31 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421
2025-07-31 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421
2025-07-31 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-31 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-08-01 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-08-01 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-08-01 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421
2025-08-01 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421
2025-08-01 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-08-01 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-02 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-08-02 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-08-02 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421
2025-08-02 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421
2025-08-02 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-08-02 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-03 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-08-03 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-08-03 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421
2025-08-03 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421
2025-08-03 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-04 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-08-04 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-04 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421
2025-08-04 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421
2025-08-04 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-05 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-05 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-05 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421
2025-08-05 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421
2025-08-05 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-06 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-06 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-06 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421
2025-08-06 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421
2025-08-06 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-07 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-07 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-07 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421
2025-08-07 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421
2025-08-07 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-08 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-08 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-08 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421
2025-08-08 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-08 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-09 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-09 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-09 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421
2025-08-09 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-09 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-09 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-10 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-10 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-10 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421
2025-08-10 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-10 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-10 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-11 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-11 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-11 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421
2025-08-11 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-11 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-11 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-12 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-12 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-12 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-12 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-12 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-12 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-13 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-13 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-13 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-13 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-13 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-13 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-14 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-14 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-14 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-14 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-14 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-14 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-15 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-15 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-15 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-15 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-15 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-16 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-16 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-16 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-16 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-16 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-16 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-17 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-17 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-17 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-17 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-17 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-17 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-18 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-18 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-18 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-18 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-18 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-18 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-19 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-19 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-19 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-19 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-19 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-19 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-20 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-20 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-20 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-20 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-20 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-20 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-21 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-21 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-21 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-21 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-21 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-21 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-22 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-22 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-22 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-22 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-22 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-22 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-23 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-23 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-23 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-23 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-23 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-23 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-23 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-24 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-24 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-24 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-24 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-24 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-24 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-24 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-25 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-25 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-25 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-25 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-25 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-25 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-25 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-26 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-26 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-26 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-26 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-26 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-26 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-26 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-27 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-27 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-27 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-27 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-27 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-27 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-27 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-28 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-28 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-28 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-28 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-28 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-28 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-28 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-29 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-29 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-29 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-29 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-29 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-29 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-29 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-30 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-30 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-08-30 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-30 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-30 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-30 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-31 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-31 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-08-31 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-08-31 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-08-31 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421
2025-08-31 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-09-01 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-09-01 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-09-01 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-01 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-01 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421
2025-09-01 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421
2025-09-02 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-09-02 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-09-02 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-02 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-02 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421
2025-09-02 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421
2025-09-03 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-09-03 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-09-03 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-03 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-03 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421
2025-09-03 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421
2025-09-04 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-09-04 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-09-04 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-04 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-04 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421
2025-09-05 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-09-05 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-09-05 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-05 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-05 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421
2025-09-05 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421
2025-09-06 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-09-06 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-06 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-06 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-06 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421
2025-09-06 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421
2025-09-07 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421
2025-09-07 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-07 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-07 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-07 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421
2025-09-07 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421
2025-09-08 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421
2025-09-08 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-08 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-08 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421
2025-09-08 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421
2025-09-09 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421
2025-09-09 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-09 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-09 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-09 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421
2025-09-10 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421
2025-09-10 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-10 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-10 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-10 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421
2025-09-11 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-11 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-11 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-11 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421
2025-09-12 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-12 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-12 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-12 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421
2025-09-13 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-13 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-13 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-13 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-13 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421
2025-09-14 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-14 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-14 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-14 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421
2025-09-14 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-15 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-15 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-15 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-15 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-16 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-16 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-16 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-16 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-17 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-17 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-17 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-18 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-18 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-18 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-19 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-19 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-19 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-20 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-20 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-20 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-21 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-21 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-21 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-21 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421
2025-09-22 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-22 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-22 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-22 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421
2025-09-23 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-23 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-23 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-23 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421
2025-09-24 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-24 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-24 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-24 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421
2025-09-25 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-25 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-25 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-25 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2025-09-26 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-26 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-26 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2025-09-27 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-27 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-27 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2025-09-28 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-28 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-28 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2025-09-29 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-29 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-29 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2025-09-30 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-30 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2023-09-30 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-01 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-02 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-03 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-04 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-05 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-06 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-07 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-08 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-09 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-10 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-11 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-12 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-13 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-14 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-15 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-16 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-17 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-18 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-19 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-20 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-21 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-22 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-23 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-24 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-25 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-26 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-27 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-28 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-10-29 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-11-01 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-02 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-03 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-04 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-05 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-06 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-07 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-08 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-09 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2023-11-11 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-12 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-13 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-14 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-15 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-16 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-17 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2023-11-19 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-20 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-21 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-22 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-23 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-24 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-25 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-26 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-27 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-28 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-29 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-11-30 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-12-01 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2023-12-02 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-03 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-04 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-05 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-06 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-07 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-08 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-09 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-10 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-11 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-12 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-13 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-14 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2023-12-15 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-01-04 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-05 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-06 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-07 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-08 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-09 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-10 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-11 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-12 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-12 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-13 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-14 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-15 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-16 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-17 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-18 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-18 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-19 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-20 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-21 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-22 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-23 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-23 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-24 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-25 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-26 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-27 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-28 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-28 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-29 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-30 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-31 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-01 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-02 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-02 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-03 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-04 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-04 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-04 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-05 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-05 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-05 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-06 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-06 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-06 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-07 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-07 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-07 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-08 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-08 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-08 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-09 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-09 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-09 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-10 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-10 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-11 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-11 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-12 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-12 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-13 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-02-13 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-13 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-14 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-14 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-15 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-15 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-02-15 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-16 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-16 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-17 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-17 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-18 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-18 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-19 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-19 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-20 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-20 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-20 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-20 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-21 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2024-02-21 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-21 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-22 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-22 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-23 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-23 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-24 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-24 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-25 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-25 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-26 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-26 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-02-26 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-27 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-27 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-02-27 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-28 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-02-28 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-02-28 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-29 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-02-29 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-03-01 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-01 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-03-02 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-02 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-03-02 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-03 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-03 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-03 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-04 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-04 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-05 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-05 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-06 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-06 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-07 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-07 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-08 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-08 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-08 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-09 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-09 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-10 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-10 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-11 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-11 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-12 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-12 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-13 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-13 | 2024-03-13 | 2024-03-13 | Lalan Mahto | 37.73 | 37.73 | TA325
2024-03-13 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-14 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-15 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-16 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-17 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-18 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-19 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-20 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-21 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-22 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-23 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-24 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-25 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-26 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-27 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-28 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-29 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-30 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-03-31 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-01 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-02 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-03 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-04 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-05 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-06 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-07 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-08 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-09 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-10 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-11 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2024-04-13 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-14 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-15 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-16 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-17 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-18 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-19 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-04-20 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325
2024-04-21 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325
2024-04-22 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325
2024-04-23 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325
2024-04-24 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325
2024-04-25 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-04-26 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-04-27 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-04-28 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-04-29 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-04-30 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-05-01 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-02 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-02 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-03 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-03 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-04 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-04 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-05 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-05 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-06 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-06 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-07 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-07 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-07 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-07 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-07 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-08 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-08 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-08 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-08 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-09 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-09 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-09 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-09 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-10 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-10 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-10 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-10 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-11 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-11 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-11 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-11 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-12 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-12 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-12 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-12 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-13 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-13 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-13 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-14 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-14 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-14 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-15 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-15 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-15 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-16 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-16 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-16 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-17 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-17 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-17 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-18 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-18 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2024-05-18 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2024-05-19 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2024-05-19 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-19 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-19 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-20 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-20 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-20 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-21 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-21 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-21 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-22 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-22 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-22 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-23 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-23 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-23 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-24 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-24 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-24 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-25 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-25 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-25 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-05-26 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-26 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-26 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-05-27 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-27 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-27 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-05-28 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-28 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-28 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-05-29 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-29 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-29 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-05-30 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-30 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-30 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-05-31 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-31 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-05-31 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-31 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-05-31 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-06-01 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-01 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-02 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-02 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-03 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-03 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-04 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-04 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-05 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-05 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-05 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-06 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-06 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-06 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-07 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-07 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-07 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-08 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-08 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-08 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-09 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-09 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-09 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-10 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-10 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-06-10 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2024-06-11 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-11 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-12 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-12 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-12 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-13 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-06-13 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-13 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-13 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325
2024-06-14 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-14 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-14 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-14 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325
2024-06-15 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-15 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-15 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-15 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325
2024-06-16 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-16 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-16 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-17 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-17 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-17 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-18 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-18 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-06-18 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-19 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-19 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-20 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-20 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-21 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-21 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-22 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-22 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-23 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-23 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-24 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-06-24 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-25 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-25 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-26 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-26 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-27 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-28 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-29 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-30 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-30 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-01 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-07-01 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-02 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-07-02 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-02 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-03 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-03 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-04 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-04 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-05 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-05 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-06 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-07 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-08 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-08 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-08 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-07-08 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-09 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-09 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-09 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-07-09 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-10 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-10 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-10 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-10 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-07-10 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-11 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-11 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-11 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-11 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-07-11 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-12 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-12 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-12 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-12 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-07-12 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-13 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-13 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-13 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-13 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-13 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-14 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-14 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-14 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-14 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-14 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-15 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-15 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-15 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-15 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-15 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-16 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-16 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-16 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-16 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-16 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-17 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-17 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-17 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-17 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-17 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-18 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-18 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-18 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-18 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-07-18 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-19 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-19 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-19 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-19 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-20 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-20 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-20 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-20 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-20 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-21 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-21 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-21 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-21 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-21 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-22 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-22 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-22 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-22 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-22 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-23 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-23 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-23 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-23 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-23 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2024-07-24 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-24 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-24 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-24 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-25 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-07-25 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-25 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-25 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-26 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-26 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-26 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-27 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-27 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-27 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-27 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-07-28 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-07-28 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-28 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-28 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-28 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-07-29 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-07-29 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-29 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-07-29 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-29 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-07-30 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-07-30 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-30 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-07-30 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-30 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-07-31 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-07-31 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-07-31 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-07-31 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-07-31 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-01 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-01 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-01 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-01 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-01 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-02 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-02 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-02 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-02 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-02 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-03 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-03 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-03 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-03 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-03 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-04 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-04 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-04 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-04 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-04 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-05 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-05 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-05 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-05 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-05 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-06 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-06 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-06 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-06 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-06 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-07 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-07 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-07 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-07 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-07 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-08 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-08-08 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-08 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-08 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-08 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-08 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-09 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-09 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-09 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-09 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-09 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-10 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-10 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-10 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-10 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-10 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-11 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-11 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-08-11 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-11 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-11 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-11 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-12 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-12 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-12 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-12 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-12 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-13 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-13 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-13 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-13 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-13 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-08-14 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-14 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-14 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-14 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-14 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-15 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-15 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-15 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-15 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-15 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-16 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-16 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-16 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-16 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-16 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-17 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-17 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-17 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-17 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-17 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-18 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-18 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-18 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-18 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-18 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-18 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-19 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-19 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-19 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-19 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-19 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-19 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-20 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-20 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-20 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-08-20 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-20 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-20 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-21 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-21 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-21 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-21 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-21 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-21 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-22 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-22 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-22 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-22 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-22 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-22 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-23 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-23 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-23 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-23 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-23 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-24 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-08-24 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-24 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-24 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-25 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-25 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-25 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-26 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-26 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-26 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-27 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-27 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-27 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-28 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-28 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-28 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-29 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-29 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-29 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-30 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-08-30 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-30 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-30 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-08-31 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-08-31 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-08-31 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-08-31 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-01 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-01 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-01 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-02 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-02 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-02 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-02 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-03 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-03 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-03 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-03 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-04 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-04 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-04 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-04 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-05 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-05 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-05 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-05 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-06 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-06 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-06 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-06 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-07 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-07 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-07 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-07 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-08 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-08 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-08 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-08 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2024-09-09 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-09 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-09 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-09 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-09 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-10 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-10 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-10 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-10 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-10 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-10 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-11 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-11 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-11 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-11 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-11 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-11 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-11 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-12 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-12 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-12 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-12 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-12 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-12 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-12 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-12 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-13 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-13 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-13 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-13 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-09-13 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-13 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-09-13 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-13 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-14 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-14 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-14 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-14 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-14 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-14 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-14 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-14 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-15 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-15 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-15 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-15 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-15 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-15 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-15 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-15 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-16 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-16 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-16 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-16 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-16 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-16 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-16 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-16 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-16 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-16 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-17 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-17 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-17 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-17 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-17 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-17 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-17 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-17 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-17 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-17 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-18 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-18 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-18 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-18 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-18 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-18 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-18 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-18 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-18 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-18 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-19 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-19 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-19 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-19 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-19 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-19 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-19 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-19 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-19 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-19 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-20 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-20 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-20 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-20 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-20 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-20 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-20 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-20 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-20 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-20 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-21 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-21 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-21 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-21 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-21 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-21 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-09-21 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-21 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-21 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-22 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-22 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-22 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-22 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-22 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-22 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-22 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-22 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-22 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-23 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-23 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-23 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-23 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2024-09-23 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-23 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-09-23 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-23 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-23 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-23 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-23 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-24 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-24 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-24 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-24 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-24 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-24 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-24 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-24 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-24 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-24 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-25 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-25 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-25 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-25 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-25 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-25 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-25 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-25 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-25 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-26 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-09-26 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-26 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-26 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-26 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-26 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-26 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-26 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-26 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-26 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-27 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-09-27 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-09-27 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-27 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-09-27 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-27 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-27 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-27 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-27 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-27 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-28 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-09-28 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-09-28 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-28 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-09-28 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-28 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-28 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-28 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-28 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-28 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-29 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-09-29 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-09-29 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-29 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-09-29 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-29 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-29 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-29 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-29 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-29 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-30 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-09-30 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-09-30 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-09-30 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-09-30 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-09-30 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-09-30 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-09-30 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-09-30 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-09-30 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-09-30 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-01 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-01 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-01 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-01 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-01 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-01 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-01 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-01 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-01 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-01 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-01 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-02 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-02 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-02 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-02 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-02 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-02 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-02 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-02 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-02 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-02 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-02 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-03 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-03 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-03 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-03 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-03 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-03 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-03 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-03 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-03 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-03 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-03 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-04 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-04 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-04 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-04 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-04 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-04 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-04 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-04 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-04 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-04 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-04 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-04 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-05 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-05 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-05 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-05 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-05 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-05 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-05 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-05 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-05 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-05 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-05 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-05 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-06 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-06 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-06 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-06 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-06 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-06 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-06 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-06 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-06 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-06 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-06 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-06 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-07 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-07 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-07 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-07 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-07 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-07 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-07 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-07 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-07 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-07 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-07 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-07 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-08 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-08 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-08 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-08 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-08 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-08 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-08 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-08 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-08 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-08 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-08 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-08 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-08 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-09 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-09 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-09 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-09 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-09 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-09 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-09 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-09 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-09 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-09 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-09 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-09 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-09 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-09 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-09 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-10 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-10 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-10 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-10 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-10 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-10 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-10 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-10 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-10 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-10 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-10 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-10 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-10 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-10 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-11 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-11 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-11 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-11 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-11 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-11 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-11 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-11 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-11 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-11 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-11 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-11 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-12 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-12 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-12 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-12 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-12 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-12 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-12 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-10-12 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-12 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-12 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-12 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-12 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-13 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-13 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-13 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-10-13 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-13 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-13 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-13 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-13 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-13 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-13 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-13 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-13 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-14 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-14 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-14 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-14 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-14 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-14 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-14 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-14 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-14 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-14 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-14 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-15 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-15 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-15 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-15 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-15 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-15 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-10-15 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-15 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-15 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-15 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-15 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-15 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-15 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-16 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-16 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-16 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-16 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-16 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-16 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-16 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-16 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-16 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-16 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-16 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-16 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-17 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-17 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-17 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-17 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-17 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-17 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-17 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-17 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-17 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-17 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-17 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-17 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-17 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-18 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-18 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-18 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-18 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-18 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-18 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-18 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-18 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-18 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-18 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-18 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-18 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-18 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-19 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-19 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-19 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-19 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-19 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-19 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-19 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-19 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-19 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-19 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-19 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-19 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-19 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-20 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-20 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-20 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-20 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-20 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-20 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-20 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-20 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-20 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-20 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-20 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-20 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-20 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-21 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-21 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-21 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-21 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-21 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-21 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-21 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-21 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-21 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-21 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-21 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-21 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-21 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-22 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-22 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-22 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-22 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-22 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-22 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-22 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-22 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-22 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-22 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-22 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-22 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-22 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-23 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-23 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-23 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-23 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-23 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-23 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-23 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-23 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-23 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-23 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-23 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-23 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-23 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-23 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-24 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-24 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-24 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-24 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-10-24 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-10-24 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-24 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-24 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-10-24 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-24 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-24 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-24 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-24 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-24 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-25 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-25 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-25 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-25 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-25 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-25 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-25 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-25 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-25 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-25 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-25 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-25 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-25 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-26 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-26 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-26 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-26 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-26 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-26 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-26 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-26 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-26 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-26 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-26 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-26 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-26 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-27 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-27 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-27 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-27 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-27 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-27 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-27 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-27 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-27 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-27 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-27 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-27 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-27 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-28 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-28 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-10-28 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-28 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-28 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-28 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-28 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-28 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-28 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-28 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-28 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2024-10-28 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-28 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2024-10-28 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-29 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-29 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-10-29 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-29 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-29 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-29 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-29 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-29 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-29 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-29 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-29 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-29 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-29 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-10-30 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-30 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-10-30 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-30 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-30 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-30 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-30 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-30 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-30 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-30 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-30 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-30 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-10-30 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-30 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-10-31 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-10-31 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-10-31 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-10-31 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-10-31 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-10-31 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-31 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-10-31 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-10-31 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-10-31 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-10-31 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-31 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-10-31 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-10-31 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-01 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-01 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-11-01 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-01 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-01 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-01 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-01 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-01 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-01 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-02 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-02 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-11-02 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-02 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-02 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-02 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-02 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2024-11-02 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-02 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-02 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-02 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-03 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-03 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-11-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-03 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-03 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-03 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-03 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2024-11-03 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-03 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-03 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-03 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-04 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-04 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-04 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-04 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-04 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2024-11-04 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-04 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-04 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-04 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-04 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-05 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-05 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325
2024-11-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-05 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-05 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-05 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-05 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2024-11-05 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-05 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-05 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-05 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-05 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-06 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-06 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325
2024-11-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-06 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-06 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-06 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-06 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2024-11-06 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-06 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-06 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-06 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-06 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-07 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-07 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325
2024-11-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-07 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-11-07 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-07 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-07 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2024-11-07 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-07 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-07 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-11-07 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-07 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-08 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-08 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325
2024-11-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-08 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-08 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-08 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-08 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-08 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-08 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-09 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-09 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325
2024-11-09 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-09 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-09 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-09 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-09 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-09 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-09 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-10 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-10 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-10 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325
2024-11-10 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-10 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-10 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-10 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-10 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-10 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-10 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-10 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-10 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-11 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-11-11 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-11 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325
2024-11-11 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-11 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-11 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-11 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-11 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-11 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-11 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-11 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-11 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-12 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-12 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325
2024-11-12 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-12 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-12 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-12 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-12 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-12 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-12 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-12 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-12 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-13 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-13 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-13 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325
2024-11-13 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-13 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-11-13 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-13 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-13 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-13 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-13 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-13 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-13 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-13 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-14 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-14 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-14 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325
2024-11-14 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-14 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-14 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-14 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-14 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-14 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-14 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-14 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-14 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-15 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-15 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-15 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325
2024-11-15 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-15 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-15 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-15 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-15 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-15 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-15 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-15 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2024-11-15 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-16 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-16 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-16 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325
2024-11-16 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-16 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-16 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-16 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-11-16 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-16 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-16 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-16 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-16 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-16 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-16 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-16 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-17 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-17 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-17 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325
2024-11-17 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-17 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-17 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-17 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-17 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-17 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-17 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-17 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-17 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-17 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-17 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-18 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-18 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-18 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325
2024-11-18 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-18 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-18 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-18 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-18 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-18 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-18 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-18 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-18 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-18 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-18 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-18 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-18 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-19 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-19 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-19 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325
2024-11-19 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-19 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-19 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-19 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-19 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-19 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-19 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-19 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-19 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-19 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-19 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-19 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-19 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-20 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-20 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-20 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325
2024-11-20 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325
2024-11-20 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-20 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-20 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-20 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-20 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-20 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-20 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-20 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-20 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-20 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-20 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-20 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-20 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-20 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-21 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-21 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-21 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325
2024-11-21 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-21 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-21 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-21 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-21 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-21 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-21 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-21 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-21 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-21 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-21 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-21 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-21 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-21 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-22 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-22 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-22 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-22 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325
2024-11-22 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-22 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-22 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325
2024-11-22 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-22 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-22 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-22 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-22 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-22 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-22 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-22 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2024-11-22 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-22 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-22 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-22 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-23 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-23 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-23 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-23 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325
2024-11-23 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-23 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-23 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-23 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325
2024-11-23 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-23 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-23 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-23 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-23 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-23 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-23 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-23 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-23 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-23 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-23 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-24 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-24 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-24 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-24 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325
2024-11-24 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-24 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-24 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-24 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325
2024-11-24 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-24 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-24 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-24 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-24 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-24 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-24 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-24 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-24 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-24 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-24 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-25 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-25 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-25 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-25 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325
2024-11-25 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-25 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-25 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-25 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325
2024-11-25 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-25 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-25 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-25 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-25 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-25 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-25 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-25 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-25 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-25 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-26 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-11-26 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-26 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-26 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325
2024-11-26 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-26 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-26 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-26 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325
2024-11-26 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-26 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-26 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-26 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-26 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-26 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-26 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-26 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-26 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-26 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-27 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-11-27 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-27 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-27 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325
2024-11-27 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-27 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-27 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-27 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-11-27 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-27 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-27 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-27 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-27 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-27 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-27 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-27 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-11-27 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-27 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-27 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-28 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-11-28 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-28 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-28 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325
2024-11-28 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-28 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-28 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-28 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-11-28 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-28 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-28 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-28 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-28 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-11-28 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-11-28 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-28 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-28 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-28 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-11-28 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-28 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-11-28 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-29 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-11-29 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-29 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-29 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325
2024-11-29 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-29 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-29 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-29 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-11-29 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-29 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-29 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-29 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-29 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-11-29 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-11-29 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-29 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-29 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-29 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-11-29 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-29 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-11-29 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-11-30 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-11-30 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-11-30 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-11-30 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325
2024-11-30 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-11-30 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-11-30 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-11-30 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-11-30 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-11-30 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2024-11-30 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-11-30 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-11-30 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-11-30 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-11-30 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-30 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-30 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-11-30 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-11-30 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-11-30 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-11-30 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-01 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-01 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-01 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-01 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325
2024-12-01 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-01 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-01 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-12-01 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-01 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-01 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-12-01 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-01 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-01 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-01 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-01 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-01 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-01 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-12-01 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-01 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-02 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-02 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-02 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-02 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325
2024-12-02 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-02 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-02 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-12-02 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-02 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-02 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-02 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-12-02 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-02 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-02 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-02 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-02 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-02 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-02 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2024-12-02 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-02 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-03 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-03 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-03 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-03 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325
2024-12-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-03 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-03 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-12-03 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-03 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-03 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-03 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-03 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-03 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-03 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-03 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-03 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-03 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-03 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-03 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-03 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-04 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-04 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-04 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-04 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-04 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-04 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-04 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-04 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-04 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-04 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-04 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-04 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-04 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-04 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-04 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-04 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-04 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-04 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-04 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-05 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-05 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-05 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-05 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-05 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-05 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-05 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-05 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-05 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-05 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-05 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-05 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-05 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-05 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-05 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-05 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-05 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-05 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-05 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-06 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-06 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-06 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-06 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-06 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-06 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-06 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-06 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-06 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-06 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-06 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-06 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-06 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-06 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-06 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-06 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-06 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-06 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-06 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-07 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-12-07 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-07 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2024-12-07 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-07 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-07 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-07 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-07 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-07 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-07 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-07 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-07 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-07 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-07 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-07 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-07 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-07 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-07 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-07 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-08 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-08 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-08 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-08 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-08 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-08 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-08 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-08 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-08 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2024-12-08 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-08 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-08 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-08 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-08 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-08 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-08 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-08 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-08 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-09 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-09 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-09 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-09 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-09 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-09 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-09 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-09 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-09 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-09 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-09 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-09 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-09 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-09 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-09 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-09 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-09 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-09 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-09 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-09 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-10 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-10 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-10 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-10 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-10 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-10 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-12-10 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-10 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-10 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-10 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-10 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-10 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-10 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-10 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-10 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-10 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-10 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-10 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-10 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-10 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-10 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-12-11 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-11 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-11 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-11 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-11 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-11 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-11 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-11 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-11 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-11 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-11 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-11 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-11 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-11 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-11 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-11 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-11 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-11 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-11 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-11 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-11 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-11 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-12 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-12 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-12 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-12 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-12 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-12 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-12 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-12 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-12 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-12 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-12 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-12 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-12 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-12 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-12 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-12 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-12 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-12 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-12 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-12 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-12 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-12 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-13 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-13 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-13 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-13 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-13 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-13 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-13 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-13 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-13 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-13 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-13 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-13 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-13 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-13 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-13 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-13 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-13 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-13 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-13 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-13 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-13 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-14 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2024-12-14 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-14 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-14 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-14 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-14 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-14 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-14 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-14 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-14 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-14 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-14 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-14 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-14 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-14 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-14 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-14 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-14 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-14 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-14 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-14 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-14 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-15 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-15 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-15 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-15 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-15 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-15 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-15 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-15 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-15 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-15 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-15 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-15 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-15 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-15 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-15 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-15 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-15 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-15 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-15 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-15 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-16 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-16 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-16 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-16 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-16 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-16 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-16 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-16 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-16 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2024-12-16 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-16 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-16 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-16 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-16 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-16 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-16 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-16 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-16 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-16 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-16 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-17 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-17 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-17 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-17 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-17 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-17 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-17 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-17 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-17 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-17 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-17 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-17 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-17 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-17 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-17 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-17 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-17 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-17 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-17 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-18 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-18 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-18 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-18 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-18 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-18 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-18 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-18 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-18 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-18 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-18 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-18 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-18 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2024-12-18 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-18 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-18 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-18 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-18 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-18 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-19 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-19 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-19 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-19 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-19 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-19 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-19 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-19 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-19 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-19 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-19 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-19 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-19 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-19 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-19 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-19 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-19 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-19 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-19 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-20 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-20 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-20 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2024-12-20 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-20 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-20 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-12-20 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-20 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-20 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-20 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-20 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-20 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-20 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-20 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-20 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-20 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-20 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-20 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-20 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-21 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-21 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-21 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2024-12-21 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-12-21 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-21 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-21 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-21 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2024-12-21 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-21 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-21 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-21 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-21 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-21 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-21 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-21 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2024-12-21 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-21 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-21 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-21 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-22 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-22 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-22 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2024-12-22 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-22 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-22 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-22 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-22 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-22 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-22 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-22 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2024-12-22 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-22 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-22 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-22 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-22 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-22 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-22 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-22 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-22 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-23 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-23 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-23 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2024-12-23 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-23 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-23 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-23 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-23 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-23 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-12-23 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2024-12-23 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-23 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-23 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-23 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-12-23 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-23 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-23 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-23 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-23 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-23 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-23 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-24 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-24 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-12-24 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2024-12-24 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-24 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-24 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-24 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-24 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-24 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-24 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-24 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-24 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-24 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-24 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-24 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-24 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-24 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-24 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-24 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-25 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-25 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2024-12-25 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-25 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-25 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-25 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-25 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-25 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-25 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-25 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-25 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-25 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-25 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-25 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-25 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-25 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-25 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-12-25 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-26 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-26 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2024-12-26 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-26 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-26 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-26 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-26 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-26 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-12-26 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-12-26 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-26 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-26 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-26 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-26 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-26 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-26 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-26 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-26 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-27 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-27 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325
2024-12-27 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-27 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-27 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-27 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-12-27 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-27 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-12-27 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-12-27 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-27 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-27 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-27 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-27 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-27 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-27 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-27 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-27 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-28 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-12-28 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2024-12-28 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325
2024-12-28 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-28 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2024-12-28 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-28 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-28 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-12-28 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-12-28 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-28 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-28 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2024-12-28 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-28 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-28 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-28 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2024-12-28 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2024-12-28 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-28 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-28 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2024-12-28 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-29 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2024-12-29 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325
2024-12-29 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2024-12-29 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-29 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2024-12-29 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-12-29 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-12-29 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-29 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-29 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2024-12-29 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-29 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-12-29 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-29 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2024-12-29 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-29 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-29 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2024-12-29 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-30 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2024-12-30 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2024-12-30 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325
2024-12-30 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2024-12-30 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-30 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-12-30 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-12-30 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-30 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-30 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2024-12-30 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-30 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2024-12-30 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-12-30 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2024-12-30 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-30 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-12-30 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2024-12-30 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-31 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2024-12-31 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2024-12-31 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325
2024-12-31 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2024-12-31 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2024-12-31 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-12-31 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2024-12-31 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-12-31 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-12-31 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-12-31 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2024-12-31 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2024-12-31 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2024-12-31 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2024-12-31 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2024-12-31 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2024-12-31 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2024-12-31 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2024-12-31 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2025-01-01 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-01 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-01 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325
2025-01-01 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2025-01-01 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-01 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2025-01-01 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-01 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2025-01-01 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2025-01-01 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2025-01-01 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-01-01 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-01 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2025-01-01 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-01 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-01 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-01 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-01 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-01 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-02 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-02 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-02 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325
2025-01-02 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2025-01-02 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-02 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2025-01-02 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-02 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2025-01-02 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2025-01-02 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2025-01-02 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-01-02 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-02 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2025-01-02 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-02 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-02 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-02 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-02 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-02 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-03 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-03 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-03 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325
2025-01-03 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2025-01-03 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-03 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2025-01-03 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-03 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-03 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2025-01-03 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2025-01-03 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-01-03 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-03 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2025-01-03 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-03 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-03 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-03 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-03 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-03 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-04 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-04 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-04 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325
2025-01-04 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-04 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2025-01-04 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-04 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-04 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2025-01-04 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2025-01-04 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-01-04 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-04 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-04 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-04 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-04 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-04 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-04 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-04 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-05 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-05 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-05 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-05 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2025-01-05 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-05 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-05 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2025-01-05 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-01-05 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-05 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-05 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-05 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-05 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-05 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-05 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-05 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-06 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-06 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-06 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-06 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-06 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-06 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-01-06 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-06 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-06 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-06 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-06 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-06 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-06 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-06 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-07 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-07 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-07 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-07 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-07 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-07 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-07 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-07 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-07 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-07 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-07 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-07 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-07 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-07 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-08 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-08 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-08 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-08 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-08 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-08 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-08 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-08 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-08 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-08 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-08 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-08 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-08 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-09 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-09 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-09 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-09 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-09 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-09 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-09 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-09 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-09 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-09 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-09 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-09 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-09 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-09 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-09 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-09 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-10 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-10 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-10 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-10 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-10 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-10 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-10 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-10 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2025-01-10 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-10 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-10 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-10 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-10 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-01-10 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2025-01-10 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-10 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-10 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-10 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-11 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-11 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-11 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-11 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-11 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-11 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-11 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-11 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-11 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-11 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-11 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-11 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-11 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-11 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-11 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-11 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2025-01-12 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-12 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-12 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-12 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-12 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-12 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-12 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-12 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-12 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-12 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-12 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-12 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-12 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-12 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-12 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-12 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-12 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2025-01-13 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-13 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-13 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-13 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-13 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-01-13 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-13 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2025-01-13 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-13 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-13 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-13 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-13 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-13 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-13 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-13 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-13 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-13 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-13 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-14 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-14 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-14 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-14 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-14 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-01-14 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-14 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-14 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-14 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-14 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-14 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-14 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-14 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-14 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-14 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-14 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-14 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-15 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-15 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-15 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-15 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-15 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-01-15 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-15 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-15 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-15 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-15 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-15 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-15 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-15 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-15 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-15 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-15 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-15 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-16 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-16 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-16 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-16 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-16 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-01-16 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-16 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-16 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-16 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-16 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-16 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-16 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2025-01-16 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-16 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-16 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-16 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-16 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-16 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-16 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-17 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-17 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-17 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-17 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-01-17 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-01-17 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-17 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-17 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-17 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-17 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-17 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-17 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-17 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-17 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-17 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-17 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-17 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-17 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-17 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-18 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2025-01-18 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-18 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-18 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-01-18 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-18 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-18 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-18 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-18 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-18 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-18 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2025-01-18 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-18 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-18 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-18 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-18 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-18 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-18 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-18 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-19 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-19 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-19 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-19 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-19 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-19 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-19 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-19 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-01-19 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-19 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2025-01-19 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-19 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-19 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-19 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-19 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-19 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-19 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-20 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-20 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-20 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-20 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325
2025-01-20 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-20 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-20 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-20 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-20 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-20 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-20 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2025-01-20 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-20 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-20 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-20 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-20 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-20 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-21 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-21 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-21 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-21 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-21 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325
2025-01-21 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-21 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-21 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-21 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-21 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-21 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-21 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-21 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-21 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-21 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-21 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-21 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-21 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-21 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-21 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-21 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-22 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-22 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-22 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-22 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-22 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325
2025-01-22 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-22 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-22 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-22 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-01-22 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-22 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-22 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-22 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-22 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-22 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-22 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-22 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-22 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-22 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-22 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-23 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-23 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-23 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-23 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-23 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325
2025-01-23 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-23 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-23 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-23 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-23 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-23 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-23 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-23 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-23 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-23 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2025-01-23 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-23 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-23 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-23 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-01-24 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-24 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-24 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-24 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-24 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325
2025-01-24 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-24 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-24 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-24 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-24 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-24 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-24 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-24 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-24 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-24 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-24 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-24 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-24 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-25 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2025-01-25 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-25 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-25 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-25 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-25 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-25 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-01-25 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-25 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-25 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-25 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-25 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-25 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-25 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-25 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-25 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-25 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-25 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-25 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-26 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-26 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-26 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-26 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-26 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-26 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-26 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-26 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-26 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-26 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-26 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-26 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-26 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-26 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-26 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-26 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-26 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-27 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-01-27 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-27 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-27 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-27 | 2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.728 | 14.9093 | TA325
2025-01-27 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-27 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-27 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-01-27 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-27 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-27 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-01-27 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-27 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-27 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-27 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-27 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-27 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-27 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-01-27 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-27 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-27 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-28 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-01-28 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-28 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-28 | 2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.728 | 14.9093 | TA325
2025-01-28 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-28 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-28 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-01-28 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-28 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-28 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-28 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-28 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-28 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-28 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-01-28 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-28 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-28 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-01-28 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-28 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-28 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-29 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-01-29 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-29 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-29 | 2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.728 | 14.9093 | TA325
2025-01-29 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-29 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-29 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-01-29 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-29 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-29 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-29 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-29 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-29 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-29 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-29 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-01-29 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-01-29 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-29 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-01-29 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-29 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-29 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-30 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-01-30 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-30 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-30 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-01-30 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325
2025-01-30 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-01-30 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-30 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-01-30 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-01-30 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-30 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-30 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-30 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-30 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-30 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-01-30 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-30 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-01-30 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-30 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-31 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-01-31 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-31 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-01-31 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-01-31 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325
2025-01-31 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-01-31 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-01-31 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-01-31 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-01-31 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-01-31 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-31 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-31 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-01-31 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-01-31 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-31 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-01-31 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-31 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-02-01 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-01 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-01 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-02-01 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-02-01 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325
2025-02-01 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-02-01 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-01 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-02-01 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-02-01 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-01 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-01 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-02-01 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-01 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-01 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-01 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-01 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-01 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-01 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-02-01 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-02-02 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-02 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-02 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-02-02 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-02-02 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325
2025-02-02 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-02-02 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-02 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-02-02 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-02 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-02 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-02-02 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-02 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-02 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-02 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-02 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-02 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-02 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-02-02 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-02-03 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-03 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-03 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-02-03 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-02-03 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325
2025-02-03 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-02-03 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-03 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-03 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-02-03 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-03 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-03 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-02-03 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-03 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-03 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-03 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-03 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-03 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-03 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-02-04 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-04 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-04 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-02-04 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-02-04 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325
2025-02-04 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-02-04 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-04 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-04 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-02-04 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-04 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-04 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-04 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-04 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-04 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-04 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-04 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-04 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-04 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-02-04 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-05 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-05 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-05 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2025-02-05 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-05 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325
2025-02-05 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-05 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-05 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-05 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325
2025-02-05 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-05 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-05 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-05 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-05 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-05 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-05 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-05 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-05 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-05 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-02-05 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-06 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-06 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-06 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-06 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325
2025-02-06 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-06 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-06 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-06 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325
2025-02-06 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-06 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-06 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-06 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-06 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-06 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-06 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-06 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-06 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-06 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-02-06 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-07 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-07 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-07 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-07 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325
2025-02-07 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-07 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-07 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-07 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325
2025-02-07 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-07 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-02-07 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-07 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-07 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-07 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-07 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-07 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-07 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-02-07 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-08 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-08 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-08 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-08 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-08 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-08 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-08 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325
2025-02-08 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-08 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-08 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-08 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-08 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-08 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-08 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-08 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-09 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-09 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-09 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-09 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325
2025-02-09 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-09 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-09 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-09 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325
2025-02-09 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-09 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-09 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-02-09 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-09 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-09 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-09 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-02-09 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-09 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-10 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-10 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-10 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-10 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325
2025-02-10 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-10 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-10 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325
2025-02-10 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-10 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-10 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-10 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-10 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-10 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-10 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-10 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-11 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-11 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-11 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-11 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325
2025-02-11 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-02-11 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2025-02-11 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325
2025-02-11 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-11 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-11 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-11 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-11 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-11 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-11 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-11 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-11 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-11 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-12 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-12 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-12 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-12 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325
2025-02-12 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-12 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325
2025-02-12 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-02-12 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-12 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-12 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2025-02-12 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-12 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-12 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-12 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-12 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-12 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-13 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-13 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-13 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-13 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325
2025-02-13 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-13 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325
2025-02-13 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-13 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-13 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-13 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-13 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-13 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-13 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-13 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-13 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-13 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-02-14 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-14 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-14 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-14 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325
2025-02-14 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-14 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-14 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325
2025-02-14 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-14 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-14 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-14 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-14 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-14 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-14 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-14 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-14 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-14 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-14 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-15 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-15 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-15 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-15 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-15 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-15 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-15 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-15 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2025-02-15 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-15 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-15 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-15 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-15 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-15 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-15 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-15 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-16 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-16 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-16 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325
2025-02-16 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-16 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-16 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-16 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-16 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-16 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-16 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-16 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-16 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-16 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-16 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-16 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-16 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-17 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-17 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-17 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-17 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325
2025-02-17 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-17 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-17 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-17 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-17 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-17 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-17 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-17 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2025-02-17 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-17 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-17 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-17 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-17 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-18 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2025-02-18 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-18 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-18 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325
2025-02-18 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-18 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-18 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-18 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-18 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-18 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-18 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-18 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-18 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-18 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-18 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-19 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-19 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-19 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325
2025-02-19 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-19 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-19 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-19 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-19 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-19 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-19 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-19 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-19 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-19 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-19 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-20 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-02-20 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-20 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325
2025-02-20 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-20 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-20 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-20 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-20 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-20 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-20 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-20 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-20 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-20 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-20 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-20 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-21 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-21 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325
2025-02-21 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-21 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-21 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-21 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-21 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-21 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-21 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-21 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-02-21 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-21 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-21 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-21 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-21 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2025-02-22 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-22 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-22 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325
2025-02-22 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-22 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-22 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-22 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-22 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-22 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-22 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-22 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-22 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-22 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-22 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-22 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-22 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-02-23 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-23 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-02-23 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-23 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-23 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-23 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-23 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
2025-02-23 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-23 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-23 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-23 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-23 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-23 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-23 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-23 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-23 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-02-24 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-24 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-02-24 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325
2025-02-24 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-24 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2025-02-24 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325
2025-02-24 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-24 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-24 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-24 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-24 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-24 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-24 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-24 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-24 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-02-25 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-25 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-02-25 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325
2025-02-25 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-25 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-25 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325
2025-02-25 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-25 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-25 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-25 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-25 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-25 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-25 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325
2025-02-25 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-25 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-25 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-02-26 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-26 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-02-26 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325
2025-02-26 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-26 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-26 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325
2025-02-26 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-02-26 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-26 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-26 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-02-26 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-26 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-26 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325
2025-02-26 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-02-26 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-26 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-26 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-02-27 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-27 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-02-27 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-02-27 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325
2025-02-27 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-27 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-27 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325
2025-02-27 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-27 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2025-02-27 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-02-27 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-27 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-27 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325
2025-02-27 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-02-27 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-27 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-27 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-02-28 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-02-28 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-02-28 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-02-28 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325
2025-02-28 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-28 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-28 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325
2025-02-28 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-28 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-02-28 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-02-28 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-28 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325
2025-02-28 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-02-28 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-02-28 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-02-28 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-01 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-01 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-01 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-03-01 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325
2025-03-01 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-03-01 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-03-01 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-01 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-01 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-01 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-01 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-01 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-01 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-01 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-01 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-02 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-02 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-02 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-03-02 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325
2025-03-02 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-03-02 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-03-02 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325
2025-03-02 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-02 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-02 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-02 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-02 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-02 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-02 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-02 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-02 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-02 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-03 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-03 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-03 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-03-03 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-03-03 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-03-03 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325
2025-03-03 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-03 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-03 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-03 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-03 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-03 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-03 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-03 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-03 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-03 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-03 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-04 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-04 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-04 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-03-04 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-04 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-03-04 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325
2025-03-04 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-04 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-04 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-04 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-04 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-04 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-04 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-04 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-04 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-04 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-05 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-05 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-05 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-03-05 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-05 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2025-03-05 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-05 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325
2025-03-05 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-05 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-05 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-05 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-05 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-05 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-05 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-05 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-05 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-05 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-06 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-06 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-06 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-06 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2025-03-06 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-06 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325
2025-03-06 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-06 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-06 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-06 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-06 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-06 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-06 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-06 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-06 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-06 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-07 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-07 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-07 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-07 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-07 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2025-03-07 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-07 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325
2025-03-07 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-07 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-07 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-07 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-07 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-07 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-07 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-07 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-07 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-07 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-03-08 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-08 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-08 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-08 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-08 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2025-03-08 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-08 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325
2025-03-08 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-08 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-08 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-08 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-08 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-08 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-08 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-08 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-08 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-08 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-09 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-09 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-09 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-09 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-09 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2025-03-09 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-09 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325
2025-03-09 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-09 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-09 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-09 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-09 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-09 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-03-09 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-09 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-09 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-09 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-09 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-10 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-10 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-10 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-10 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-10 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2025-03-10 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-10 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325
2025-03-10 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-10 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-10 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-10 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-10 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-10 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-10 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-10 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-10 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-11 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-11 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-03-11 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-11 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-11 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-11 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-11 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-11 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-11 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-11 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-11 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-11 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-11 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-11 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-12 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-12 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-12 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-12 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-12 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-12 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-12 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-12 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-12 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-12 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-12 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-12 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-12 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-12 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-13 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-13 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-13 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-13 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-13 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-13 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-13 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-13 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-13 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-13 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-13 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-03-13 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-13 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-13 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-13 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-14 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-14 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-14 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-14 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-14 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-14 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-14 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-14 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-14 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-14 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-14 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-03-14 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-14 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-14 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-14 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-15 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-15 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-15 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2025-03-15 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-15 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-15 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-15 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-15 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-15 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-15 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-15 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-15 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-15 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-03-15 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-15 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-15 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-15 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-16 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2025-03-16 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-16 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-16 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-16 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325
2025-03-16 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-16 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-16 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-16 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-16 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-16 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-16 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-16 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-03-16 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-16 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-16 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-16 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-17 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-17 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-17 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-17 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325
2025-03-17 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325
2025-03-17 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-17 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-17 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-17 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-17 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-17 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-17 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-03-17 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-17 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-17 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-17 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-18 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-18 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-18 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-18 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325
2025-03-18 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325
2025-03-18 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-18 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-18 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-18 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-18 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-18 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-18 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-03-18 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-03-18 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-18 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-18 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325
2025-03-18 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-19 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-19 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-19 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-19 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-19 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325
2025-03-19 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325
2025-03-19 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-19 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-19 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-19 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-19 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-19 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-19 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-19 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-19 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325
2025-03-19 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-19 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-19 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-20 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-20 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-20 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-20 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-20 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325
2025-03-20 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325
2025-03-20 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-20 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-20 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-20 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-20 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-20 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-20 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-20 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-20 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-20 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325
2025-03-20 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-20 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-20 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-21 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-21 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-21 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-21 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-21 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-21 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325
2025-03-21 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-21 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-21 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-21 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-21 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-21 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-21 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-21 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-21 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-21 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325
2025-03-21 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-21 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-21 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-22 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-22 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-22 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-22 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325
2025-03-22 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-22 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-22 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325
2025-03-22 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-22 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-22 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-22 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-22 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-03-22 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-22 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-22 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-22 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-22 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-22 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325
2025-03-22 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-22 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-22 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-23 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-23 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-23 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-23 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325
2025-03-23 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-23 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325
2025-03-23 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-23 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-23 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-23 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-23 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-23 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-23 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-23 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-23 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-23 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-23 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-23 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-24 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-24 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-24 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325
2025-03-24 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-24 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-24 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325
2025-03-24 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-24 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-24 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-24 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-24 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-24 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-24 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-24 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-24 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-24 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-24 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-24 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-25 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-25 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-25 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325
2025-03-25 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-25 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-25 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325
2025-03-25 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-25 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-25 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-25 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-25 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-25 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-25 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-25 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-25 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-25 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-25 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-25 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-25 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-26 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-26 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-03-26 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-26 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325
2025-03-26 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-26 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-26 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-03-26 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-26 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-26 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-26 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-26 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-26 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-26 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-26 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-26 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-26 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-26 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-26 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-26 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-27 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-27 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-03-27 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-27 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325
2025-03-27 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-27 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2025-03-27 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-03-27 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-27 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-27 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-27 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-27 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-03-27 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-27 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-27 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-27 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-27 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-27 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-27 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-27 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-28 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-28 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-03-28 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-03-28 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-28 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325
2025-03-28 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-28 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-03-28 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-28 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-03-28 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-03-28 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-28 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-28 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-28 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-28 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-28 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-28 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-29 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-29 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-03-29 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-03-29 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-29 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325
2025-03-29 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-29 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-03-29 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-29 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-29 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-29 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-29 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-29 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-03-30 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-30 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-03-30 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-03-30 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-03-30 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325
2025-03-30 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-30 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-03-30 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-30 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-30 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-03-30 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-30 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-30 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-31 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-03-31 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-03-31 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-03-31 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325
2025-03-31 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-03-31 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-03-31 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-03-31 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-31 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-03-31 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-03-31 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-31 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-01 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-01 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-04-01 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-01 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2025-04-01 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2025-04-01 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-01 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-01 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-01 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-04-01 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-01 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-01 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-04-01 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-01 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-01 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-02 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-02 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-04-02 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-02 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-02 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-02 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-02 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-04-02 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-02 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-02 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-02 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-02 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-02 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-02 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-02 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-03 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-03 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2025-04-03 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-03 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-03 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-03 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-03 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-04-03 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-03 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-03 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-03 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-03 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-03 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-03 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-03 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-03 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-03 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-04 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-04 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-04 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-04 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-04-04 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-04 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-04 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-04 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-04-04 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-04 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-04 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-04 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-04 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-04 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-04 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-04 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-04 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-04 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-05 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-05 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-05 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-05 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325
2025-04-05 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-04-05 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-05 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-05 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-05 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-04-05 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-05 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-05 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-05 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-05 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-05 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-05 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-05 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-05 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-05 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-06 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-06 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-06 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-06 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325
2025-04-06 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-06 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-06 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-04-06 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-06 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-06 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-06 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-04-06 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-06 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-06 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-06 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-06 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-06 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-06 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-04-06 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-06 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-06 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-06 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-07 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-07 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-07 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-07 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325
2025-04-07 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-07 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-07 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-04-07 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-07 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-07 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-07 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-07 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-07 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-07 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-07 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-07 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-07 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-07 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-07 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-07 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-08 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-08 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-08 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-08 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-08 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325
2025-04-08 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-08 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-08 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-04-08 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-08 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-08 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-08 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2025-04-08 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-08 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-08 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-08 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-08 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-08 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-08 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-08 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-08 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-09 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-09 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-09 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-09 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-09 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325
2025-04-09 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-09 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-09 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-04-09 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-09 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-09 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-09 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-09 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-09 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-09 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-09 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-09 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-09 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-09 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-09 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-10 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-10 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-10 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-10 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-10 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325
2025-04-10 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-10 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-10 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-10 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-10 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-10 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-10 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-10 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-10 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-10 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-10 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-10 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-10 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-10 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-11 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-04-11 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-11 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-11 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-11 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325
2025-04-11 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-11 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-11 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-04-11 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-11 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-11 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-11 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-11 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2025-04-11 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-04-11 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-11 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-11 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-11 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-11 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-11 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-12 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-12 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-12 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-12 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-12 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-12 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-04-12 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-04-12 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-04-12 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-12 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-12 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-12 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-12 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-12 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-12 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-12 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2025-04-13 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-13 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-13 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-13 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-13 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-04-13 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-13 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-13 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-13 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-13 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-13 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-13 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-13 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-13 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-14 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-14 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-14 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-14 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-14 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-04-14 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-14 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-14 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-14 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-14 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-14 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-14 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-14 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-14 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-15 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-15 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-15 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-15 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-15 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-04-15 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-04-15 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-15 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-15 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-15 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-15 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-15 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-04-15 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-15 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-15 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-16 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-16 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-16 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-16 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-16 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-16 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-04-16 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-16 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-16 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-16 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-16 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-16 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-04-16 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-16 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-16 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-16 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-17 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-17 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-17 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-17 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-17 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-17 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-17 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-17 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-17 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-17 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-17 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-17 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-17 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-17 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-17 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-17 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-18 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-18 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-18 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-04-18 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-18 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-18 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-18 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-18 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-18 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-18 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-18 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-18 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-18 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-18 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-18 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-18 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-18 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-18 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-18 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-18 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-18 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-19 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-19 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-19 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-19 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-19 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-19 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-19 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-19 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-19 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-19 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-19 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-19 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-19 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-19 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-19 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-19 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-19 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-19 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-19 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-19 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-20 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-20 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-20 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-20 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-20 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-20 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-20 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-20 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-20 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-20 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-20 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-20 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-20 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-20 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-20 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-20 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-20 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-20 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-20 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-20 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-20 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-21 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-21 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-21 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-21 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-21 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-21 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-21 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-21 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-21 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-21 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-21 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-21 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-21 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-21 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-21 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-21 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-21 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-21 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-21 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-21 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-21 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-22 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-22 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-22 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-22 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-22 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-22 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-22 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-22 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-22 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-22 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-22 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-22 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-22 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-22 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-04-22 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-22 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2025-04-22 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-22 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-22 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2025-04-22 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-22 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-22 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-23 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-23 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-23 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-23 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-23 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-23 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-23 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-23 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-23 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-23 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-23 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-23 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-23 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325
2025-04-23 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-23 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-23 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-23 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-23 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-24 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-24 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-24 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-24 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-24 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-24 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-24 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-24 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-24 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-24 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-24 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-24 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-24 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-24 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-24 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-24 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325
2025-04-24 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-24 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-24 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-24 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-24 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-25 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-25 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-04-25 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-25 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-25 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-25 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-25 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-25 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-25 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-25 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-25 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-25 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-25 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-25 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-25 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-25 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325
2025-04-25 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-25 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-25 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-25 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-25 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-26 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-26 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-26 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-26 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-26 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-26 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-26 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-26 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-26 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-26 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-26 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-26 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-26 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-26 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325
2025-04-26 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-26 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-04-26 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-26 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-26 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-27 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-27 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-27 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-27 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-27 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-27 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-27 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-27 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-27 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-27 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-27 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-27 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-27 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-27 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325
2025-04-27 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-27 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-27 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-27 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-28 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-28 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-28 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-28 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-28 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-04-28 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-28 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-28 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-28 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-04-28 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2025-04-28 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-28 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-28 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-28 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-28 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-28 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-28 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-04-28 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-04-28 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-29 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-29 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-29 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-04-29 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-29 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-29 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-04-29 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-29 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-29 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-29 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-04-29 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-29 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-29 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-29 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-29 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-04-29 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-29 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-04-29 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-04-29 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-04-30 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-04-30 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-04-30 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-30 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-04-30 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-04-30 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-30 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-04-30 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-04-30 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-30 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-30 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-30 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-30 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-04-30 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-04-30 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-04-30 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-04-30 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-05-01 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-01 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-01 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-05-01 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-05-01 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-05-01 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-01 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-01 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-05-01 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-01 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-01 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-05-01 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-05-01 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-01 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-02 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-02 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-02 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-05-02 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-05-02 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-05-02 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-02 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-02 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-02 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-05-02 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-02 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-02 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-05-02 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-05-02 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-02 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-02 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-02 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-03 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-03 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-03 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-05-03 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-05-03 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-05-03 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-03 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-03 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-03 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-05-03 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-03 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-03 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-03 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-05-03 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-05-03 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-03 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-03 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-03 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-04 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-04 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-04 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-04 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-05-04 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-05-04 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-04 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-04 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-04 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-05-04 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-04 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-04 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-04 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-04 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-05-04 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-05-04 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-04 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-04 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-04 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-05 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-05 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-05 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-05 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-05-05 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-05-05 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-05 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-05 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-05 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-05-05 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-05 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-05 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-05 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-05 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-05-05 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-05 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-05 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-05 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-06 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-06 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-06 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-06 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2025-05-06 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-05-06 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-06 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-06 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-06 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-06 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-06 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-06 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-06 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-06 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-06 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-06 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-06 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-06 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-07 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-07 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-07 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-07 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-07 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-07 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-07 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-07 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-07 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-07 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-07 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-07 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-07 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-07 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-07 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-07 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-08 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-08 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-08 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-08 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-08 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-08 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-08 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-08 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-08 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-08 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-08 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-08 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-08 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-08 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-08 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-08 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-08 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-09 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-09 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-09 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-09 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-09 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-09 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-09 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-09 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-09 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-09 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-09 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-05-09 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-09 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-09 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-09 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-05-09 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-09 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-09 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-10 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-10 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-10 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-10 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-10 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-10 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-10 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-10 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-10 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-10 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-10 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-10 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-10 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-10 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-10 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-10 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-11 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-05-11 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-11 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-11 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-11 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-11 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-05-11 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-11 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-05-11 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-11 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-11 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-05-11 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-11 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-11 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-05-11 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-05-11 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-11 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-12 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-12 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-12 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-12 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-12 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-12 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-12 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-12 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-12 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-12 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-13 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-13 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-13 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-05-13 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-13 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-13 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-13 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-13 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-13 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-13 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-13 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-13 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-14 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-14 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-14 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-05-14 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-14 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-14 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-14 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-14 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-14 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-14 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-14 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-14 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-15 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-15 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-15 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-05-15 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-15 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-15 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-15 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-15 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-05-15 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-15 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-15 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-15 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-15 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-16 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-16 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-16 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-16 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-05-16 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-16 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-16 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-16 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-16 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-16 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-16 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-16 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-16 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-17 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-17 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-17 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-17 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-05-17 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-17 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-17 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-17 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-17 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-17 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-17 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-17 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-18 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-18 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-18 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-05-18 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-05-18 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-05-18 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-05-18 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-18 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-18 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-18 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-18 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-18 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-19 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-05-19 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-19 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-19 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-19 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-19 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-19 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-19 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-05-20 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-20 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-20 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-20 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-20 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-05-20 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-21 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-21 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-21 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-21 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-22 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-22 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-22 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-23 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-23 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-24 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-24 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-24 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-25 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2025-05-25 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-26 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-27 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-28 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-28 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-05-29 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-29 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-05-29 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-05-30 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-30 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-05-30 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-05-31 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-05-31 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-05-31 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-01 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-01 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-06-01 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-02 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-02 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-06-02 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-03 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-03 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-06-03 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-04 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-04 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-06-04 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-05 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-05 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
2025-06-05 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-06 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-06 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-06 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-07 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-07 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-08 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-06-08 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-09 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-10 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-11 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-11 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-12 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-12 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-13 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-13 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-06-14 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-15 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-16 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-17 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-18 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-19 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-20 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-21 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-22 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-23 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-24 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-25 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-26 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-27 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-28 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-29 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-06-30 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-07-01 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-07-02 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-07-03 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-07-04 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325

## RawData
Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name
2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416
2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416
2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416
2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416
2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416
2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416
2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416
2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416
2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416
2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416
2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416
2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416
2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416
2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416
2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416
2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416
2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416
2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416
2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416
2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416
2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416
2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416
2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416
2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416
2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416
2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416
2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416
2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416
2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416
2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416
2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416
2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416
2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416
2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416
2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416
2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416
2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416
2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416
2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416
2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416
2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416
2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416
2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416
2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416
2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416
2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416
2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416
2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416
2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416
2025-10-20 | 2025-01-25 | Asc Heights | 46.0492 |  | TA416
2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416
2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416
2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416
2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416
2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416
2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416
2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416
2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416
2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416
2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416
2025-02-02 |  | Rudra Construction | 46.0492 |  | TA416
2025-02-06 |  | Dewi Construction | 64.482 |  | TA416
2025-02-07 |  | Reeta Bharti | 43.7758 |  | TA416
2025-02-08 |  | Amar Singh | 46.0492 |  | TA416
2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416
2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416
2025-02-11 |  | Horil Mahto | 46.049 |  | TA416
2025-02-11 |  | Asc Heights | 46.049 |  | TA416
2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416
2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416
2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416
2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416
2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416
2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416
2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416
2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416
|  | Reeta Bharti |  |  | TA416
|  | Dewi Construction |  |  | TA416
|  | Pankaj |  |  | TA416
|  | Pinky Dewi |  |  | TA416
2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416
2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416
2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416
2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416
2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416
2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416
2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416
2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416
2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416
2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416
2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416
2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416
2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416
2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416
2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416
2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416
2025-03-22 |  | Reeta Bharti | 64.482 |  | TA416
2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416
2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416
2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416
2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416
2025-03-22 |  | Mk Infra | 46.0492 |  | TA416
2025-03-24 | 2025-03-31 | Ananya Traders | 46.0492 | 5.7561 | TA416
2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416
2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416
2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416
2025-03-31 | 2025-04-11 | Anand Const | 46.0492 | 3.8374 | TA416
2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416
2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416
2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416
2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416
2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416
2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416
2025-04-08 | 2025-04-12 | Pinky Dewi 1 | 42.3742 | 8.4748 | TA416
2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416
2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416
2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416
2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416
2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416
2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416
2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416
2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416
2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416
2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416
2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416
2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416
2025-02-12 18:37 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416
2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416
2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416
2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416
2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416
2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416
2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416
2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416
2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416
2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416
2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416
2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416
2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416
2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416
2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416
2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416
2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416
2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416
2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416
2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416
2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416
2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416
2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416
2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416
2025-05-13 | 2025-05-15 | Ananya Traders 2 | 42.3742 | 14.1247 | TA416
2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416
2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416
2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416
2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416
2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416
2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416
2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416
2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416
2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416
2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416
2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416
2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416
2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416
2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416
2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416
2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416
2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416
2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416
2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416
2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416
2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416
2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416
2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416
2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416
2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416
2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416
2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416
2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416
2025-06-02 | 2025-06-12 | Devine | 42.374 | 3.8522 | TA416
2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416
2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416
2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416
2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416
2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416
2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416
2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416
2025-06-14 | 1935-06-28 | Ananya Traders 2 | 104.867 |  | TA416
2025-06-20 | 1935-06-28 | Amit Const | 42.374 |  | TA416
1935-06-27 | 2025-06-29 | Pinki Dewi | 42.374 | 0.0012889 | TA416
2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416
2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416
2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416
2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416
2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416
2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416
2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416
2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416
2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416
2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416
2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416
2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416
2025-08-14 | 2025-08-26 | Kajal Const | 46.049 | 3.5422 | TA416
2025-07-26 | 2025-08-27 | Kangresh 1 | 161.355 | 4.8895 | TA416
2025-08-09 | 2025-08-30 | Radha Const | 78.073 | 3.5488 | TA416
2025-08-04 | 2025-08-30 | Sainik Ent | 75.85 | 2.8093 | TA416
2025-08-02 | 2025-08-30 | Kangresh 2 | 97.229 | 3.3527 | TA416
2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416
2025-08-10 | 2025-09-07 | Ananya | 118.43 | 4.0838 | TA416
2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416
2025-09-08 |  | Ananya | 90.125 |  | TA416
2025-08-18 |  | Mk Infra | 42.374 |  | TA416
2025-08-18 |  | Spotify Pvt Ltd 2 | 53.324 |  | TA416
2025-08-18 |  | Spotify Pvt Ltd 3 | 42.374 |  | TA416
2025-08-31 |  | Sainik Ent | 87.01 |  | TA416
2025-08-31 |  | Kangresh 2 | 73.426 |  | TA416
2025-08-31 |  | Radha Const | 89.7 |  | TA416
2025-08-24 | 2025-09-14 | Gouri Shankar | 97.65 | 4.4386 | TA416
2025-09-04 |  | Gagan |  |  | TA416
2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416
2025-08-28 |  | Kangresh 1 | 161.355 |  | TA416
2025-08-06 |  | Reeta Bharti | 161.355 |  | TA416
2025-09-08 |  | Punam Kumari |  |  | TA416
2025-09-11 |  | Maa Const |  |  | TA416
|  | Nan |  |  | TA408
|  | Nan |  |  | TA408
|  | Nan |  |  | TA408
2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408
2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408
2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408
2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408
2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408
2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408
2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408
2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408
2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408
2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408
2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408
2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408
2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408
2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408
2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408
2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408
2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408
2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408
2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408
2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408
2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408
2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408
2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408
2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408
2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408
2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408
2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408
2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408
2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408
2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408
2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408
2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408
2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408
2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408
2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408
2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408
2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408
2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408
2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408
2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408
2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408
2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408
2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408
2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408
2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408
2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408
2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408
2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408
2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408
2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408
2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408
2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408
2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408
2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408
2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408
2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408
2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408
2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408
2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408
2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408
2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408
2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408
2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TA408
2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408
2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408
2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408
2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408
2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408
2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408
2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408
2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408
2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408
2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408
2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408
2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408
2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408
2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408
2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408
2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408
2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408
2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408
2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408
2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408
2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408
2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408
2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408
2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408
2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408
2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408
2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408
2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408
2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408
2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408
2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408
2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408
2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408
2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408
2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408
2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408
2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408
2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408
2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408
2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408
2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408
2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408
2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408
2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408
2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408
2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408
2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408
2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408
2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408
2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408
2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408
2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408
2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408
2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408
2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408
2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408
2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408
2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408
2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408
2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408
2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408
2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408
2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408
2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408
2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408
2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408
2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408
2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408
2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408
2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408
2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408
2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408
2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408
2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408
2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408
2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408
2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408
2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408
2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408
2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408
2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408
2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408
2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408
2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408
2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408
2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408
2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408
2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408
2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408
2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408
2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408
2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408
|  | Nan |  |  | TA408
2025-05-10 |  | Bhairo Mahto |  |  | TA408
2025-05-19 |  | Sonakshi Manish 2 |  |  | TA408
2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421
2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421
2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421
2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421
2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421
2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421
2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421
2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421
2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421
2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421
2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421
2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421
2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421
2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421
2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421
2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421
2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421
2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421
2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421
2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421
2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421
2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421
2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421
2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421
2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421
2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421
2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421
2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421
2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421
2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421
2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421
2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421
2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421
2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421
2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421
2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421
2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421
2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421
2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421
2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421
2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421
2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421
2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421
2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421
2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421
2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421
2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421
2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421
2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421
2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421
2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421
2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421
2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421
2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421
2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421
2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421
2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421
2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421
2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421
2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421
2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421
2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421
2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421
2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421
2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421
2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421
2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421
2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421
2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421
2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421
2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421
2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421
2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421
2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421
2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421
2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421
2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421
2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421
2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421
2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421
2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421
2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421
2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421
2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421
2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421
2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421
2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421
2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421
2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421
2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421
2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421
2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421
2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421
2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421
2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421
2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421
2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421
2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421
2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421
2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421
2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421
2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421
2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421
2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421
2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421
2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421
2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421
2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421
2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421
2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421
2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421
2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421
2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421
2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421
2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421
2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421
2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421
2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421
2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421
2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421
2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421
2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421
2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421
2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421
2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421
2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421
2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421
2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421
2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421
2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421
2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421
2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421
2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421
2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421
2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421
2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421
2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421
2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421
2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421
2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421
2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421
2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421
2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421
2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421
2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421
2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421
2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421
2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421
2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421
2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421
2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421
2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421
2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421
2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421
2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421
2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421
2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421
2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421
2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421
2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421
2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421
2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421
2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421
2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421
2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421
2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421
2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421
2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421
2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421
2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421
2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421
2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421
2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421
| 2025-07-12 | Subash | 33.38 |  | TA421
2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421
| 2025-07-13 | Naziruddin | 71.706 |  | TA421
2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421
2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421
2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421
2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421
2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421
2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421
2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421
2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421
2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421
2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421
2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421
2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421
2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421
2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421
2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421
2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421
2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421
2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421
2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421
2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421
2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421
2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421
2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421
2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421
2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421
2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421
2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421
2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421
2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421
2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421
2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421
2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421
2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421
2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421
2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421
2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421
2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421
2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421
2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421
2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421
2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421
2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421
2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421
2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421
2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421
2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421
2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421
2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421
2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421
2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421
2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421
2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421
2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421
2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421
2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421
2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421
2025-09-13 |  | Praveen | 36.37 |  | TA421
2025-09-21 |  | Yadhav | 37.931 |  | TA421
2025-09-27 |  | Hassan | 36.37 |  | TA421
2025-09-28 |  | Khatun | 31.99 |  | TA421
2025-10-01 |  | Subash |  |  | TA421
2025-10-01 |  | D K Verma |  |  | TA421
| 2025-08-13 | Nan | 172.151 |  | TA325
2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325
2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325
2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325
2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325
2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325
2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325
2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325
2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325
2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325
2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325
2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325
2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325
2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325
2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325
2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325
2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325
2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325
2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325
2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325
2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325
2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325
2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325
2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325
2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325
2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325
2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325
2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325
2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325
2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325
2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325
2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325
2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325
2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325
2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325
2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325
2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325
2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325
2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325
2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325
2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325
2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325
2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325
2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325
2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325
2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325
2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325
2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325
2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325
2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325
2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325
2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325
2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325
2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325
2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325
2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325
2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325
2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325
2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325
2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325
2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325
2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325
2024-03-13 | 2024-03-13 | Lalan Mahto | 37.73 | 37.73 | TA325
2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325
2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325
2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325
2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325
2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325
2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325
2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325
2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325
2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325
2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325
2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325
2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325
2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325
2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325
2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325
2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325
2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325
2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325
2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325
2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325
2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325
2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325
2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325
2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325
2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325
2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325
2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325
2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325
2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325
2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325
2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.728 | 14.9093 | TA325
2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325
2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325
2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325
2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325
2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325
2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325
2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325
2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325
2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325
2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325
2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325
2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325
2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325
2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325
2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325
2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325
2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325
2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325
2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325
2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325
2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325
2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325
2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325
2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325
2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325
2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325
2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325
2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325
2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325
2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325
2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325
2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325
2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325
2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325
2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325
2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325
2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325
2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325
2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325
2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325
2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325
2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325
2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325
2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325
2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325
2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325
2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325
2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325
2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325
2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325
2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325
2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325
2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325
2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325
2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325
2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325
2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325
2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325
2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325
2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325
2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325
2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325
2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325
2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325
2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325
2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325
2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325
2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325
| 2025-08-08 | Nan | 141.874 |  | TA325
2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325
2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325
2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325
2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325
2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325
2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325
2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325
2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325
2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325
2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325
2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325
2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325
2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325
2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325
2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325
2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325
2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325
2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325
2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325
2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325
2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325
2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325
2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325
2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325
2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325
2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325
2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325
2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325
2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325
2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325
2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325
2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325
2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325
2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325
2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325
2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325
2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325
2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325
2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325
2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325
2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325
2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325
2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325
2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325
2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325
2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325
2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325
2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325
2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325
2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325
2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325
2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325
2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325
2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325
2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325
| 2025-07-20 | Nan | 37.73 |  | TA325
2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325
2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325
2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325
2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325
2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325
2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325
2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325
2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325
2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325
2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325
2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325
2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325
2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325
2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325
2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325
2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325
2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325
2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325
2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325
2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325
2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325
2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325
2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325
2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325
2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325
2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325
2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325
2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325
2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325
2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325
2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325
2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325
2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325
2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325
2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325
2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325
2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325
2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325
2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325
2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325
2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325
2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325
2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325
2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325
2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325
2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325
2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325
2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325
2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325
2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325
2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325
2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325
2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325
2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325
2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325
2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325
2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325
2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325
2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325
2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325
2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325
2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325
2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325
2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325
2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325
2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325
2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325
2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325
2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325
2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325
2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325
2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325
2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325
2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325
2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325
2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325
2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325
2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325
2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325
2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325
2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325
2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325
2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325
2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325
2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325
2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325
2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325
2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325
2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325
2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325
2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325
2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325
2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325
2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325
2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325
2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325
2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325
2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325
2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325
2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325
2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325
2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325
2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325
2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325
2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325
2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325
2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325
2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325
2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325
2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325
2035-03-04 | 2025-03-11 | Thanu Mahto | 36.045 |  | TA325
2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325
2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325
2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325
2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325
2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325
2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325
2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325
2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325
2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325
2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325
2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325
2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325
2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325
2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325
2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325
2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325
2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325
2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325
2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325
2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325
2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325
|  | Nan | 20361.708 |  | TA325
|  | Nan |  |  | TA325
|  | Nan |  |  | TA325
|  | Nan | 40 |  | TA325
|  | Nan | 146 |  | TA325
|  | Nan | 40 |  | TA325
|  | Nan | 30 |  | TA325
|  | Nan | 11 |  | TA325
|  | Nan | 267 |  | TA325
|  | Nan | 25 |  | TA325
|  | Nan | 6 |  | TA325
|  | Nan | 8 |  | TA325
|  | Nan | 9 |  | TA325
|  | Nan | 6 |  | TA325
|  | Nan | 1 |  | TA325
|  | Nan | 55 |  | TA325
|  | Nan | 26 |  | TA325
|  | Nan | 3 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 7 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 3 |  | TA325
|  | Nan | 47 |  | TA325
|  | Nan | 16 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 3 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 6 |  | TA325
|  | Nan | 5 |  | TA325
|  | Nan | 2 |  | TA325
|  | Nan | 40 |  | TA325
|  | Nan | 19 |  | TA325
|  | Nan | 8 |  | TA325
|  | Nan | 11 |  | TA325
|  | Nan | 7 |  | TA325
|  | Nan | 7 |  | TA325
|  | Nan | 15 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 2 |  | TA325
|  | Nan | 73 |  | TA325
|  | Nan | 1 |  | TA325
|  | Nan | 1 |  | TA325
|  | Nan | 483 |  | TA325

## Data Issues
Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Issues
2025-02-02 |  | Rudra Construction | 46.0492 |  | TA416 | Missing start/end date (not expanded)
2025-02-06 |  | Dewi Construction | 64.482 |  | TA416 | Missing start/end date (not expanded)
2025-02-07 |  | Reeta Bharti | 43.7758 |  | TA416 | Missing start/end date (not expanded)
2025-02-08 |  | Amar Singh | 46.0492 |  | TA416 | Missing start/end date (not expanded)
2025-02-11 |  | Horil Mahto | 46.049 |  | TA416 | Missing start/end date (not expanded)
2025-02-11 |  | Asc Heights | 46.049 |  | TA416 | Missing start/end date (not expanded)
|  | Reeta Bharti |  |  | TA416 | Missing start/end date (not expanded)
|  | Dewi Construction |  |  | TA416 | Missing start/end date (not expanded)
|  | Pankaj |  |  | TA416 | Missing start/end date (not expanded)
|  | Pinky Dewi |  |  | TA416 | Missing start/end date (not expanded)
2025-03-22 |  | Reeta Bharti | 64.482 |  | TA416 | Missing start/end date (not expanded)
2025-03-22 |  | Mk Infra | 46.0492 |  | TA416 | Missing start/end date (not expanded)
2025-09-08 |  | Ananya | 90.125 |  | TA416 | Missing start/end date (not expanded)
2025-08-18 |  | Mk Infra | 42.374 |  | TA416 | Missing start/end date (not expanded)
2025-08-18 |  | Spotify Pvt Ltd 2 | 53.324 |  | TA416 | Missing start/end date (not expanded)
2025-08-18 |  | Spotify Pvt Ltd 3 | 42.374 |  | TA416 | Missing start/end date (not expanded)
2025-08-31 |  | Sainik Ent | 87.01 |  | TA416 | Missing start/end date (not expanded)
2025-08-31 |  | Kangresh 2 | 73.426 |  | TA416 | Missing start/end date (not expanded)
2025-08-31 |  | Radha Const | 89.7 |  | TA416 | Missing start/end date (not expanded)
2025-09-04 |  | Gagan |  |  | TA416 | Missing start/end date (not expanded)
2025-08-28 |  | Kangresh 1 | 161.355 |  | TA416 | Missing start/end date (not expanded)
2025-08-06 |  | Reeta Bharti | 161.355 |  | TA416 | Missing start/end date (not expanded)
2025-09-08 |  | Punam Kumari |  |  | TA416 | Missing start/end date (not expanded)
2025-09-11 |  | Maa Const |  |  | TA416 | Missing start/end date (not expanded)
2025-10-20 | 2025-01-25 | Asc Heights | 46.0492 |  | TA416 | Non-positive duration (Start > End or 0) (not expanded)
2025-06-14 | 1935-06-28 | Ananya Traders 2 | 104.867 |  | TA416 | Non-positive duration (Start > End or 0) (not expanded)
2025-06-20 | 1935-06-28 | Amit Const | 42.374 |  | TA416 | Non-positive duration (Start > End or 0) (not expanded)
1935-06-27 | 2025-06-29 | Pinki Dewi | 42.374 | 0.0012889 | TA416 | Start before 2021-01-01 (not expanded)
2025-03-24 | 2025-03-31 | Ananya Traders | 46.0492 | 5.7561 | TA416 | Single-occurrence gang (not expanded)
2025-03-31 | 2025-04-11 | Anand Const | 46.0492 | 3.8374 | TA416 | Single-occurrence gang (not expanded)
2025-04-08 | 2025-04-12 | Pinky Dewi 1 | 42.3742 | 8.4748 | TA416 | Single-occurrence gang (not expanded)
2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | Single-occurrence gang (not expanded)
2025-06-02 | 2025-06-12 | Devine | 42.374 | 3.8522 | TA416 | Single-occurrence gang (not expanded)
2025-08-14 | 2025-08-26 | Kajal Const | 46.049 | 3.5422 | TA416 | Single-occurrence gang (not expanded)
2025-07-26 | 2025-08-27 | Kangresh 1 | 161.355 | 4.8895 | TA416 | Single-occurrence gang (not expanded)
2025-08-09 | 2025-08-30 | Radha Const | 78.073 | 3.5488 | TA416 | Single-occurrence gang (not expanded)
2025-08-04 | 2025-08-30 | Sainik Ent | 75.85 | 2.8093 | TA416 | Single-occurrence gang (not expanded)
2025-08-02 | 2025-08-30 | Kangresh 2 | 97.229 | 3.3527 | TA416 | Single-occurrence gang (not expanded)
2025-08-10 | 2025-09-07 | Ananya | 118.43 | 4.0838 | TA416 | Single-occurrence gang (not expanded)
2025-08-24 | 2025-09-14 | Gouri Shankar | 97.65 | 4.4386 | TA416 | Single-occurrence gang (not expanded)
|  | Nan |  |  | TA408 | Missing start/end date (not expanded)
|  | Nan |  |  | TA408 | Missing start/end date (not expanded)
|  | Nan |  |  | TA408 | Missing start/end date (not expanded)
|  | Nan |  |  | TA408 | Missing start/end date (not expanded)
2025-05-10 |  | Bhairo Mahto |  |  | TA408 | Missing start/end date (not expanded)
2025-05-19 |  | Sonakshi Manish 2 |  |  | TA408 | Missing start/end date (not expanded)
2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TA408 | Single-occurrence gang (not expanded)
2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408 | Single-occurrence gang (not expanded)
| 2025-07-12 | Subash | 33.38 |  | TA421 | Missing start/end date (not expanded)
| 2025-07-13 | Naziruddin | 71.706 |  | TA421 | Missing start/end date (not expanded)
2025-09-13 |  | Praveen | 36.37 |  | TA421 | Missing start/end date (not expanded)
2025-09-21 |  | Yadhav | 37.931 |  | TA421 | Missing start/end date (not expanded)
2025-09-27 |  | Hassan | 36.37 |  | TA421 | Missing start/end date (not expanded)
2025-09-28 |  | Khatun | 31.99 |  | TA421 | Missing start/end date (not expanded)
2025-10-01 |  | Subash |  |  | TA421 | Missing start/end date (not expanded)
2025-10-01 |  | D K Verma |  |  | TA421 | Missing start/end date (not expanded)
2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | Single-occurrence gang (not expanded)
2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | Single-occurrence gang (not expanded)
2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | Single-occurrence gang (not expanded)
2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | Single-occurrence gang (not expanded)
| 2025-08-13 | Nan | 172.151 |  | TA325 | Missing start/end date (not expanded)
| 2025-08-08 | Nan | 141.874 |  | TA325 | Missing start/end date (not expanded)
| 2025-07-20 | Nan | 37.73 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 20361.708 |  | TA325 | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 40 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 146 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 40 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 30 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 11 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 267 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 25 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 6 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 8 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 9 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 6 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 1 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 55 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 26 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 3 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 7 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 3 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 47 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 16 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 3 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 6 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 5 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 2 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 40 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 19 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 8 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 11 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 7 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 7 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 15 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 2 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 73 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 1 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 1 |  | TA325 | Missing start/end date (not expanded)
|  | Nan | 483 |  | TA325 | Missing start/end date (not expanded)
2035-03-04 | 2025-03-11 | Thanu Mahto | 36.045 |  | TA325 | Non-positive duration (Start > End or 0) (not expanded)
|  | Nan | 20361.708 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 267 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 6 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 8 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 9 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 6 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 1 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 3 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 7 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 3 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 3 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 6 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 5 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 2 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 8 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 7 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 7 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 2 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 1 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 1 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 483 |  | TA325 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325 | Single-occurrence gang (not expanded)
2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | Single-occurrence gang (not expanded)
2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | Single-occurrence gang (not expanded)

## Issues
file | issue
TA413-PBNTL-20.08.2025.xlsx | Excel open error: Unable to read workbook: could not assign names from C:\Users\kaushikb\Documents\Work\Git\Office-work-\Test\TA413-PBNTL-20.08.2025.xlsx. This is most probably because the workbook source files contain some invalid XML. Please see the exception for more details.

## Diagnostics
file | project | sheet | detected_header_row | columns_detected
DPR TA-416,14-09-25.xlsx | TA416 | Erection Compiled | 0 | sl no, location no, tower type, tower weight, starting date, completion date, work status, gang name, gang strength, gang type(subcontractor/company), nan, tac welding, remark
TA 408.xlsx | TA408 | Erection Compiled | 3 | sl.no, month sl.no, location no, type of tower, starting date, completion date, gang name, staff's engaged, tower weight, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan
TA 421 Latest BMTL-30-09-2025.xlsx | TA421 | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, nan, nan, nan, completion date, gang name, gang strength, remark, tackwelding, tower tightening
TA325 ANTL KEC DPR_18-08-2025.xlsx | TA325 | Erection Compiled | 0 | sl. no, location no, type, type of tower, starting date, revenue, tower weight, todays status, completion date, gang name
TA413-PBNTL-20.08.2025.xlsx | TA413

## README_Assumptions
Notes
Assumptions & Cleaning Rules:
- Start date cutoff: rows with Start Date before 2021-01-01 are not expanded and logged in 'Data Issues'.
- Tower Weight range: only [10, 200] MT is considered valid for expansion; out-of-range rows go to 'Data Issues'.
- Missing or non-positive durations (Start/End missing or Start > End or 0) are logged to 'Data Issues' and not expanded.
- Gangs that performed erection only once (per Project+Gang) are not expanded and are logged in 'Data Issues'.
- Gang name normalization: remove special characters (digits kept), Title Case words, and insert a space before trailing digits (e.g., 'xyz4' → 'Xyz 4').
- Sheets:
• DailyExpanded : per-day expanded rows used by the dashboard
• RawData : per-erection rows (unexpanded), for traceability
• Data Issues : row-level data problems (reason in 'Issues' column)
• Issues : file-level problems (missing sheet/headers, read/open errors, etc.)
• Diagnostics : which sheet used, detected header row, and normalized header text
- Dashboard note: a 15-day productivity loss cap is used in downstream analytics.