## Stringing-132KV
unnamed_col_1 | from | to | unnamed_col_4 | unnamed_col_5 | unnamed_col_6 | Status | dos | doc | status__2 | dos__2 | doc__2 | status__3 | status__4 | status__5 | unnamed_col_16 | unnamed_col_17 | unnamed_col_18 | unnamed_col_19 | status__6 | dos__3 | doc__3 | status__7 | dos__4 | doc__4 | project_code | line_name | project_name | project_display | project_scope_key | project | _source_file | source_sheet
1 | Hydro GTY | Existing Tower-1 | 58.79 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
2 | Existing Tower-1 | Exting Tower-2 | 149.12 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
3 | Exting Tower-2 | Exting Tower-3 | 128.1 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
4 | Exting Tower-3 | Exting Tower-4 | 252.72 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
5 | Exting Tower-4 | Exting Tower-5 | 146.74 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
6 | Exting Tower-5 | Exting Tapping Tower-6 | 190.05 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
7 | Exting Tapping Tower-6 | Exting Tower-7 | 83.39 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
8 | Exting Tower-7 | SC-5 | 120.53 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
9 | SC-5 | SC-4 | 259.51 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
10 | SC-4 | Sc-3 | 256.61 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
11 | Sc-3 | SC-2 | 277.95 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
12 | SC-2 | SC-1 | 202.25 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
13 | SC-1 | 1/0 | 62.76 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
14 | 1/0 | 2/0 | 278.15 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
15 | 2/0 | 2/1 | 234.56 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
16 | 2/1 | 3/0 | 249.04 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
17 | 3/0 | 3/1 | 256 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
18 | 3/1 | 4/0 | 226.52 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
19 | 4/0 | 4/1 | 43.62 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
20 | 4/1 | 4/2 | 52 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
21 | 4/2 | 5/0 | 47.06 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
22 | 5/0 | 6/0 | 286.44 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
23 | 6/0 | 6/1 | 317 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
24 | 6/1 | 6/2 | 328 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
25 | 6/2 | 6/3 | 297 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
26 | 6/3 | 6/4 | 251 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
27 | 6/4 | 7/0 | 308.23 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
28 | 7/0 | 8/0 | 278.12 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
29 | 8/0 | 9/0 | 385.96 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
30 | 9/0 | 10/0 | 259.92 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
31 | 10/0 | 11/0 | 215.13 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
32 | 11/0 | 12/0 | 316.15 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
33 | 12/0 | 12/1 | 274 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
34 | 12/1 | 13/0 | 293.28 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
35 | 13/0 | 13/1 | 48.42 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
36 | 13/1 | 13/2 | 58.24 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
37 | 13/2 | 14/0 | 70.13 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
38 | 14/0 | 15/0 | 220.7 | [21 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
39 | 15/0 | 15/1 | 262.95 | C | C | C | 2026-03-07 | 2026-03-09 | C | 2026-03-08 | 2026-03-09 | [13 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
40 | 15/1 | 15/2 | 251.57 | C | C | C | 2026-03-07 | 2026-03-09 | C | 2026-03-08 | 2026-03-09 | [13 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
41 | 15/2 | 15/3 | 271.76 | C | C | C | 2026-03-07 | 2026-03-09 | C | 2026-03-08 | 2026-03-09 | [13 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
42 | 15/3 | 16/0 | 261.04 | C | C | C | 2026-03-07 | 2026-03-09 | C | 2026-03-08 | 2026-03-09 | [13 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
43 | 16/0 | 16/1 | 37.42 | C | C | C | 2026-03-05 | 2026-03-06 | C | 2026-03-05 | 2026-03-06 | [13 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
44 | 16/1 | 16/2 | 71 | C | C | C | 2026-03-03 | 2026-03-03 | C | 2026-03-03 | 2026-03-03 | [13 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
45 | 16/2 | 17/0 | 37.52 | C | C | C | 2026-02-23 | 2026-02-23 | C | 2026-02-23 | 2026-02-23 |  |  |  | SK Basirul | [9 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
46 | 17/0 | 18/0 | 165.147 | C | C | C | 2026-03-02 | 2026-03-03 | C | 2026-03-02 | 2026-03-03 | [13 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
47 | 18/0 | Gantry | 39.999 | C | C | C | 2026-02-20 | 2026-02-21 | C | 2026-02-20 | 2026-02-21 |  |  |  | SK Basirul | [9 empty] | TEST 000 | Stringing 132kV | TEST 000 - Stringing 132kV | TEST 000 - Stringing 132kV | test000stringing132kv | TEST 000 - Stringing 132kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-132KV
1 | Gnty | 0/0 | 0.047 | C | C | C | 2026-01-31 | 2026-02-02 | C | 2026-01-31 | 2026-02-02 |  |  |  | Harshvivek | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
2 | 0/0 | 1/0 | 439.47 | C | C | C | 2025-05-19 | 2025-05-24 | C | 2025-05-26 | 2025-05-28 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
3 | 1/0 | 1A/0 | 1037.32 | C | C | C | 2025-05-19 | 2025-05-24 | C | 2025-05-26 | 2025-05-28 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
4 | 1A/0 | 1A/2 | 609 | C | C | C | 2025-06-29 | 2025-06-29 | C | 2025-06-30 | 2025-06-30 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
5 | 1A/2 | 1B/0 | 232.098 | C | C | C | 2025-06-29 | 2025-06-29 | C | 2025-06-29 | 2025-06-29 | C | C |  | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
6 | 1B/0 | 1C/0 | 237.783 | [21 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
7 | 1C/0 | 1D/0 | 675.21 | [21 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
8 | 1D/0 | 1E/0 | 699.92 | C | C | C | 2025-08-01 | 2025-08-02 | C | 2025-08-04 | 2025-08-07 | C | C | C | Dilruba Bibi | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
9 | 1E/0 | 2/0 | 356.664 | C | C | C | 2025-07-26 | 2025-07-29 | C | 2025-07-31 | 2025-08-03 | C | C |  | Dilruba Bibi | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
10 | 2/0 | 3/0 | 174.205 | [21 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
11 | 3/0 | 4/0 | 229.73 | [21 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
12 | 4/0 | 4/5 | 1733 | C | C | C | 2025-07-11 | 2025-07-14 | C | 2025-07-16 | 2025-07-18 | C | C | C | Dilruba Bibi | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
13 | 4/5 | 4/6 | 349 | C | C | C | 2025-07-11 | 2025-07-14 | C | 2025-07-16 | 2025-07-18 | C | C |  | Dilruba Bibi | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
14 | 4/6 | 4/7 | 360 | [21 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
15 | 4/7 | 4/8 | 460 | [21 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
16 | 4/8 | 4/9 | 230 | [21 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
17 | 4/9 | 4/10 | 371.51 | C | C | C | 2025-08-22 | 2025-08-25 | C | 2025-09-19 | 2025-09-21 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
18 | 4/10 | 4/11 | 332.471 | C | C | C | 2025-08-22 | 2025-08-25 | C | 2025-09-19 | 2025-09-21 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
19 | 4/11 | 4/15 | 1335.05 | C | C | C | 2025-08-22 | 2025-08-25 | C | 2025-09-10 | 2025-09-13 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
20 | 4/15 | 4/16 | 415 | C | C | C | 2025-08-22 | 2025-08-25 | C | 2025-08-31 | 2025-09-03 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
21 | 4/16 | 4/17 | 237 | C | C | C | 2025-08-22 | 2025-08-25 | C | 2025-09-16 | 2025-09-17 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
22 | 4/17 | 5/0 | 188.454 | C | C | C | 2025-08-28 | 2025-08-31 | C | 2025-09-07 | 2025-09-10 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
23 | 5/0 | 5/1 | 383 | C | C | C | 2025-08-28 | 2025-08-31 | C | 2025-09-08 | 2025-09-11 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
24 | 5/1 | 5A/0 | 952 | C | C | C | 2025-10-16 | 2025-10-16 | C | 2025-10-17 | 2025-10-19 | C | C |  | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
25 | 5A/0 | 5A/1 | 322 | C | C | C | 2026-02-10 | 2026-02-12 | C | 2026-02-13 | 2026-02-14 | C | C |  | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
26 | 5A/1 | 5A/2 | 284 | C | C | C | 2026-02-09 | 2026-02-10 | C | 2026-02-14 | 2026-02-15 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
27 | 5A/2 | 5B/0 | 282.74 | C | C | C | 2026-02-06 | 2026-02-09 | C | 2026-02-09 | 2026-02-10 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
28 | 5B/0 | 6/0 | 462.06 | C | C | C | 2026-01-28 | 2026-02-04 | C | 2026-02-07 | 2026-02-09 | C | C |  | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
29 | 6/0 | 7/0 | 318.04 | C | C | C | 2026-01-28 | 2026-02-04 | C | 2026-02-04 | 2026-02-06 | C | C |  | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
30 | 7/0 | 8/0 | 1147.05 | C | C | C | 2025-09-22 | 2025-09-24 | C | 2025-09-25 | 2025-09-27 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
31 | 8/0 | 8A/0 | 173.57 | C | C | C | 2025-10-01 | 2025-10-01 | C | 2025-10-04 | 2025-10-05 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
32 | 8A/0 | 8B/0 | 336.5 | C | C | C | 2025-10-03 | 2025-10-03 | C | 2025-10-08 | 2025-10-09 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
33 | 8B/0 | 8C/0 | 900.14 | C | C | C | 2025-10-04 | 2025-10-04 | C | 2025-10-08 | 2025-10-09 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
34 | 8C/0 | 8D/0 | 318.76 | [21 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
35 | 8D/0 | 8D/1 | 436.1 | C | C | C | 2026-03-05 | 2026-03-06 | C | 2026-03-07 | 2026-03-08 |  | C |  | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
36 | 8D/1 | 8D/3 | 657.08 | C | C | C | 2026-03-02 | 2026-03-05 | C | 2026-03-08 | 2026-03-09 |  | C |  | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
37 | 8D/3 | 8D/4 | 459 | C | C | C | 2026-02-15 | 2026-02-19 | C | 27/2/2026 | 27/2/2026 | C | C |  | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
38 | 8D/4 | 8D/5 | 195 | C | C | C | 2026-02-15 | 2026-02-19 | C | 28/2/2026 | 28/2/2026 | C | C |  | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
39 | 8D/5 | 8D/6 | 295 | C | C | C | 2026-02-15 | 2026-02-19 | [16 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
40 | 8D/6 | 8E/0 | 380.25 | C |  | C | 2026-02-15 | 2026-02-19 | [16 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
41 | 8E/0 | 8E/1 | 428 | C |  | C | 2026-02-15 | 2026-02-19 | [16 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
42 | 8E/1 | 8E/2 | 419 | C | C | C | 2025-11-11 | 2025-11-14 | C | 2025-11-15 | 2025-11-18 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
43 | 8E/2 | 8E/5 | 900 | C | C | C | 2025-11-11 | 2025-11-14 | C | 2025-11-15 | 2025-11-18 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
44 | 8E/5 | 8E/6 | 343.87 | C | C | C | 2025-11-11 | 2025-11-14 | C | 2025-11-15 | 2025-11-18 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
45 | 8E/6 | 8E/7 | 499.13 | C | C | C | 2026-02-20 | 2026-02-22 | C | 2026-02-24 | 2026-02-24 | C | C | C | [10 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
46 | 8E/7 | 8E/8 | 434 | C | C | C | 2026-02-20 | 2026-02-23 | C | 2026-02-25 | 2026-02-25 | C | C | C | [10 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
47 | 8E/8 | 8E/11 | 919 | C | C | C | 2025-11-17 | 2025-11-19 | C | 2025-11-22 | 2025-11-23 | C | C | C | National | [9 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
48 | 8E/11 | 8E/12 | 489 | C | C | C | 2025-11-05 | 2025-11-09 | C | 2025-11-11 | 2025-11-13 | C | C | C | National |  |  |  | C | 2025-12-17 | 2025-12-20 | C | 2025-12-21 | 2025-12-21 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
49 | 8E/12 | AP-9 | 382.48 | C | C | C | 2025-11-05 | 2025-11-09 | C | 2025-11-09 | 2025-11-11 | C | C | C | National |  |  |  | C | 2025-12-17 | 2025-12-20 | C | 2025-12-21 | 2025-12-21 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
50 | AP-9 | 9/4 | 1250.32 | C | C | C | 2025-11-05 | 2025-11-09 | C | 2025-11-09 | 2025-11-11 | C | C | C | National |  |  |  | C | 2025-12-17 | 2025-12-20 | C | 2025-12-21 | 2025-12-21 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
51 | 9/4 | 9/5 | 246.76 | C | C | C | 2025-10-26 | 2025-10-27 | C | 2025-10-28 | 2025-10-29 | C | C | C | National |  |  |  | C | 2025-12-17 | 2025-12-20 | C | 2025-12-21 | 2025-12-21 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
52 | 9/5 | AP-10 | 1697.24 | C | C | C | 2025-09-26 | 2025-09-30 | C | 2025-10-26 | 2025-10-27 | C | C | C | National |  |  |  | C | 2025-12-17 | 2025-12-20 | C | 2025-12-21 | 2025-12-21 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
53 | AP-10 | AP-11 | 1600.078 | C | C | C | 2025-10-10 | 2025-10-12 | C | 2025-10-12 | 2025-10-14 | C | C | C | National |  |  |  | C | 2025-12-26 | 2025-12-27 | C | 2025-12-28 | 2025-12-28 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
54 | AP-11 | AP-12 | 525.89 | C | C | C | 2025-10-10 | 2025-10-12 | C | 2025-10-12 | 2025-10-14 | C | C | C | National |  |  |  | C | 2025-12-26 | 2025-12-27 | C | 2025-12-28 | 2025-12-28 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
55 | AP-12 | AP-13 | 356.279 | C | C | C | 2025-10-01 | 2025-10-01 | C | 2025-10-08 | 2025-10-10 | C | C | C | National |  |  |  | C | 2025-12-26 | 2025-12-27 | C | 2025-12-28 | 2025-12-28 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
56 | AP-13 | AP-14 | 667.59 | C | C | C | 2025-12-18 | 2025-12-20 | C | 2025-12-24 | 2025-12-27 | C | C | C | National |  |  |  | C | 2025-12-26 | 2025-12-27 | C | 2025-12-28 | 2025-12-28 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
57 | AP-14 | 14/1 | 362 | C | C | C | 2025-12-18 | 2025-12-20 | C | 2025-12-24 | 2025-12-27 | C | C | C | National |  |  |  | C | 2025-12-26 | 2025-12-27 | C | 2025-12-28 | 2025-12-28 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
58 | 14/1 | 14/3 | 752 | C | C | C | 2025-12-18 | 2025-12-20 | C | 2025-12-21 | 2025-12-27 | C | C | C | National |  |  |  | C | 2025-12-26 | 2025-12-27 | C | 2025-12-28 | 2025-12-28 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
59 | 14/3 | AP-15 | 2536.18 | C | C | C | 2025-12-13 | 2025-12-15 | C | 2025-12-22 | 2025-12-23 | C | C |  | National |  |  |  | C | 2025-12-22 | 2025-12-24 | C | 2025-12-25 | 2025-12-25 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
60 | AP-15 | AP-16 | 3422.45 | C | C | C | 2025-06-17 | 2025-06-25 | C | 2025-06-20 | 2025-06-29 | C | C | C | Nemchand |  |  |  | C | 2025-09-28 | 2025-09-30 | C | 2025-10-01 | 2025-10-02 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
61 | AP-16 | AP-17 | 1307.65 | C | C | C | 2025-06-30 | 2025-07-06 | C | 2025-07-08 | 2025-07-11 | C | C | C | National |  |  |  | C | 2025-09-30 | 2025-10-02 | C | 2025-10-03 | 2025-10-04 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
62 | AP-17 | AP-18 | 1435.97 | C | C | C | 2025-06-30 | 2025-07-06 | C | 2025-07-08 | 2025-07-11 | C | C | C | National |  |  |  | C | 2025-10-02 | 2025-10-04 | C | 2025-10-05 | 2025-10-07 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
63 | AP-18 | AP-19 | 4210.131 | C | C | C | 2025-07-14 | 2025-07-15 | C | 2025-07-16 | 2025-07-18 | C | C | C | National |  |  |  | C | 2025-10-08 | 2025-10-09 | C | 2025-10-10 | 2025-10-11 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
64 | AP-19 | AP-20 | 1946.55 | C | C | C | 2025-07-20 | 2025-07-21 | C | 2025-07-21 | 2025-07-22 | C | C | C | National |  |  |  | C | 2025-12-07 | 2025-12-08 | C | 2025-12-08 | 2025-12-09 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
65 | AP-20 | AP-21 | 2994.77 | C | C | C | 2025-07-22 | 2025-07-24 | C |  |  | C | C | C | National |  |  |  | C | 2025-12-07 | 2025-12-08 | C | 2025-12-08 | 2025-12-09 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
66 | AP-21 | AP-22 | 4974.78 | C | C | C | 2025-08-04 | 2025-08-12 | C | 2025-08-18 | 2025-08-22 | C | C | C | National |  |  |  | C | 2025-11-26 | 2025-11-27 | C | 2025-11-27 | 2025-11-27 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
67 | AP-22 | AP-23 | 947.23 | C | C | C | 2025-08-08 | 2025-08-12 | C | 2025-09-07 | 2025-09-08 | C | C | C | National |  |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
68 | AP-23 | AP-24 | 1926.75 | C | C | C | 2025-09-04 | 2025-09-06 | C | 2025-09-07 | 2025-09-08 | C | C | C | National |  |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
69 | AP-24 | AP-25 | 190.524 | C | C | C | 2025-10-04 | 2025-10-04 | C | 2025-10-04 | 2025-10-04 | C | C | C | National |  | PLC |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
70 | AP-25 | AP-26 | 173.541 | C | C | C | 2025-09-13 | 2025-09-15 | C | 2025-09-15 | 2025-09-16 | C | C | C | National |  |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
71 | AP-26 | AP-27 | 142.384 | C | C | C | 2025-10-06 | 2025-10-06 | C | 2025-10-06 | 2025-10-06 | C | C | C | National |  | PLC |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
72 | AP-27 | AP-28 | 77.015 | C | C | C | 2025-11-02 | 2025-11-02 | C | 2025-12-03 | 2025-12-05 | C | C | C | National |  | PLC |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
73 | AP-28 | 28/1 | 42.266 | C | C | C | 2025-11-02 | 2025-11-02 | C | 2025-12-03 | 2025-12-05 | C | C | C | National |  |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
74 | 28/1 | 28/2 | 54.573 | C | C | C | 2025-11-02 | 2025-11-02 | C | 2025-12-03 | 2025-12-05 | C | C | C | National |  |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
75 | 28/2 | AP-29 | 41.886 | C | C | C | 2025-09-16 | 2025-09-16 | C | 2025-09-17 | 2025-09-17 | C | C | C | National |  |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
76 | AP-29 | 29A/0 | 353.284 | C | C | C | 2025-09-15 | 2025-09-15 | C | 2025-09-16 | 2025-09-16 | C | C | C | National |  |  |  | C | 2025-12-10 | 2025-12-13 | C | 2025-12-14 | 2025-12-15 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
77 | 29A/0 | AP-30 | 1860.55 | C | C | C | 2025-07-16 | 2025-07-20 | C | 2025-08-28 | 2025-08-31 | C | C | C | National |  |  |  | C | 2025-11-28 | 2025-12-01 | C | 2025-11-28 | 2025-12-01 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
78 | AP-30 | AP-31 | 2332.92 | C | C | C | 2025-07-08 | 2025-07-13 | C | 2025-07-16 | 2025-07-22 | C | C |  | Kohinoor |  |  |  | C | 2025-11-28 | 2025-12-01 | C | 2025-11-28 | 2025-12-01 | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
79 | AP-31 | AP-32 | 743.35 | [21 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
80 | AP-32 | 33/0 | 909.22 | [21 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
81 | 33/0 | 34/0 | 209 | [21 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
82 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
83 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
84 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
85 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
86 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
87 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
88 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
89 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
90 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
91 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
92 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
93 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
94 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
95 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
96 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
97 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
98 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
99 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
100 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
101 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
102 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
103 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
104 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
105 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
106 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
107 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
108 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
109 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
110 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
111 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
112 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
113 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
114 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
115 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
116 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
117 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
118 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
119 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
120 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
121 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
122 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
123 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
124 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
125 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
126 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
127 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
128 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
129 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
130 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
131 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
132 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
133 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
134 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
135 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
136 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
137 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
138 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
139 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
140 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
141 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
142 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
143 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
144 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
145 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
146 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
147 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
148 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
149 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
150 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
151 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
152 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
153 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
154 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
155 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
156 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
157 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
158 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
159 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
160 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
161 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
162 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
163 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
164 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
165 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
166 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
178 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
179 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
180 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
181 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
182 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
183 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
184 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
185 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
186 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
187 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
188 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
189 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
190 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
191 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
192 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
193 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
194 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
195 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
196 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
197 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
198 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
199 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
200 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
201 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
202 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
203 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
204 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
205 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
206 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
207 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
208 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
209 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
210 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
211 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
212 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
213 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
214 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
215 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
216 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
217 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
218 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
219 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
220 | [24 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[25 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[25 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[25 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[25 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[7 empty] | 4 | [17 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[7 empty] | 16 |  |  |  | 1.1033 | [13 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[7 empty] | 7 | [17 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[6 empty] | 952 | 0.952 | [17 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[6 empty] | 173.57 | 0.17357 | [17 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[6 empty] | 336.5 | 0.3365 | [17 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[6 empty] | 900.14 | 0.90014 | [17 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[6 empty] | 1697.24 | 1.6972 | [17 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[6 empty] | 1600.078 | 1.6001 | [17 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[6 empty] | 525.89 | 0.52589 | [17 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[6 empty] | 356.279 | 0.35628 | [17 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[6 empty] | 190.524 | 0.19052 | [17 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV
[6 empty] | 142.384 | 0.14238 | [17 empty] | TEST 000 | Stringing 220kV | TEST 000 - Stringing 220kV | TEST 000 - Stringing 220kV | test000stringing220kv | TEST 000 - Stringing 220kV | TEST 000 - DPR - 2026-03-09.xlsx | Stringing-220kV

## Diagnostics
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | DetectedHeaderRow | ColumnsDetected | NormalizedColumnsOk | PresentColumns | MissingColumns | AppliedMap | Rows | DailyRows | Status | FallbackNote | TemplateSheet | TemplateApplied | TemplateChanges
TEST 000 - DPR - 2026-03-09.xlsx | TEST 000 | Stringing-132KV | Stringing-132KV | Stringing 132kV | config | 4 | unnamed_col_1, from, to, unnamed_col_4, unnamed_col_5, unnamed_col_6, Status, dos, doc, status__2, dos__2, doc__2, status__3, status__4, status__5, unnamed_col_16, unnamed_col_17, unnamed_col_18, unnamed_col_19, status__6, dos__3, doc__3, status__7, dos__4, doc__4 | FALSE | Status | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Gang Name | Status->status | 47 | 0 | NO_DAILY |  |  | FALSE
TEST 000 - DPR - 2026-03-09.xlsx | TEST 000 | Stringing-220kV | Stringing-220kV | Stringing 220kV | config | 4 | unnamed_col_1, from, to, unnamed_col_4, unnamed_col_5, unnamed_col_6, Status, dos, doc, status__2, dos__2, doc__2, status__3, status__4, status__5, unnamed_col_16, unnamed_col_17, unnamed_col_18, unnamed_col_19, status__6, dos__3, doc__3, status__7, dos__4, doc__4 | FALSE | Status | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Gang Name | Status->status | 226 | 0 | NO_DAILY |  |  | FALSE

## Issues
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | Issue | MissingColumns | Rows | DailyRows
TEST 000 - DPR - 2026-03-09.xlsx | TEST 000 | Stringing-132KV | Stringing-132KV | Stringing 132kV | config | MISSING_REQUIRED_COLUMNS | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Gang Name | 47 | 0
TEST 000 - DPR - 2026-03-09.xlsx | TEST 000 | Stringing-132KV | Stringing-132KV | Stringing 132kV | config | NO_DAILY |  | 47 | 0
TEST 000 - DPR - 2026-03-09.xlsx | TEST 000 | Stringing-220kV | Stringing-220kV | Stringing 220kV | config | MISSING_REQUIRED_COLUMNS | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Gang Name | 226 | 0
TEST 000 - DPR - 2026-03-09.xlsx | TEST 000 | Stringing-220kV | Stringing-220kV | Stringing 220kV | config | NO_DAILY |  | 226 | 0

## README_Assumptions
Note | Rules
Compiled from DPR files: stringing sheet consolidation. | Preserve raw columns; diagnostics include column presence and date parsing; configured stringing sheets are processed independently with per-sheet line identity before concatenation; PO start to F/S complete inclusive for daily expansion.