## Foundation
Project Code |  |  | TA-418
Name of Line |  |  | 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1)
Activity |  |  | Foundation | Qty
|  |  | Total | 127
|  |  | Completed (Oct-25) | 115
|  |  | Balance | 12
Micro Plan for month |  |  | 2025-11-01 | 12 | Nos | 76.27 | Rs. Cr.
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
Actual for the Month |  |  | Total | 0 | 0 | 0 | 0
Sl | Loc No. | Tower type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont | Work Plan | [7 empty] | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[7 empty] | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[7 empty] | Start | End | Start | End | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 55/6 | 1DA-3 | DFR | 11.42 | 0.62 | Gang- 01 | 2025-11-01 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-04 | 2025-11-06 | 2025-11-08 | 2025-11-07 | 2.86 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.86
2 | AP57 | 1DC1+6 | DFR | 28.1 | 1.46 | Gang- 01 | 2025-11-06 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-09 | 2025-11-11 | 2025-11-13 | 2025-11-12 | 8.33 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8.33
3 | 59/1 | 1DA-3 | DFR | 11.42 | 0.62 | Gang- 01 | 2025-11-11 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-17 | 2025-11-16 | 2.86 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.86
4 | 60/3 | 1DA+0 | DFR | 11.42 | 0.62 | Gang- 01 | 2025-11-15 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-21 | 2025-11-20 | 2.86 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.86
5 | 63/0 | 1DD60+0 | DFR | 72.19 | 3.42 | Gang- 01 | 2025-11-19 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-22 | 2025-11-25 | 2025-11-27 | 2025-11-26 | 14.15 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.15
6 | AP38 | 1DD60+6 | DFR | 72.19 | 3.49 | Gang- 01 | 2025-11-25 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-28 | 2025-12-01 | 2025-12-03 | 2025-12-02 | 14.23 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.23
7 | 55/5 | 1DA+0 | DFR | 11.42 | 0.62 | Gang-02 | 2025-11-04 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-07 | 2025-11-09 | 2025-11-11 | 2025-11-10 | 2.86 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.86
8 | 48A/1 | 1DA+9 | DFR | 11.73 | 0.63 | Gang-02 | 2025-11-09 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-11 | 2025-11-13 | 2025-11-15 | 2025-11-14 | 3.08 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.86
9 | 48A/2 | 1DA-1.5 | DFR | 11.42 | 0.62 | Gang-02 | 2025-11-13 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-15 | 2025-11-17 | 2025-11-19 | 2025-11-18 | 2.86 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.86
10 | AP49 | 1DC1+3 | DFR | 28.1 | 1.46 | Gang-02 | 2025-11-17 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-20 | 2025-11-22 | 2025-11-24 | 2025-11-23 | 8.33 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.33
11 | AP50 | 1DC1+0 | DFR | 28.07 | 1.44 | Gang-02 | 2025-11-22 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-25 | 2025-11-27 | 2025-11-29 | 2025-11-28 | 8.29 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.29
12 | AP51 | 1DB1-3 | DFR | 32.22 | 1.51 | Gang-02 | 2025-11-27 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-30 | 2025-12-02 | 2025-12-04 | 2025-12-03 | 5.56 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.56
13 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 329.7 | 16.51 | [9 empty] | 76.27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.05
[13 empty] | STUB Setting- |  | 0.6
[13 empty] | Earthing- |  | 1.5
[13 empty] | Total Reve |  | 78.37
Formulas:
End = [Work Plan]+2
End = [Stub-setting]
Stub-setting = [End]
Concreting = [End]+1
Earthing = [End]+2
Backfilling = [End]+1
Work Plan = [End, row above]

## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## Erection
Project Code |  |  | TA-418
Name of Line |  |  | 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1)
Activity |  |  | Erection | Qty
|  |  | Total | 127
|  |  | Completed (Oct-25) | 89
|  |  | Balance | 38
Micro Plan for month |  |  | 2025-11-01 | 20 | Nos | 91.415 | Rs. Cr
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 0 | 0% | 0 | 0%
Sl | Loc No. | Tower type | Tonnage (MT) | Sub-Cont | Work Plan |  |  |  |  | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Matl feeding | Erection |  | Tack-welding | Final checking |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[6 empty] | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 33/0 | DD45+18 | 89.029 | Team-01 | 2025-10-16 | 2025-10-19 | 2025-11-06 |  |  | 11.505 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.505
2 | 33/4 | DA+3 | 29.122 |  | 2025-11-05 | 2025-11-06 | 2025-11-10 |  |  | 3.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6
3 | 43/2 | DA+0 | 27.963 |  | 2025-11-10 | 2025-11-11 | 2025-11-14 |  |  | 3.08 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.08
4 | 43/3 | DA-3 | 26.846 |  | 2025-11-14 | 2025-11-15 | 2025-11-18 |  |  | 2.95 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95
5 | 44/1 | DA+0 | 27.963 |  | 2025-11-18 | 2025-11-19 | 2025-11-23 |  |  | 3.08 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.08
6 | 38/0 | DD60+6 | 73.176 |  | 2025-11-23 | 2025-11-24 | 2025-11-30 |  |  | 8.09 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.09
7 | 46/10 | DA-3 | 26.846 | Team-02 | 2025-10-29 | 2025-10-30 | 2025-11-05 |  |  | 2.95 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95
8 | 46/6 | DA+0 | 27.963 |  | 2025-11-05 | 2025-11-06 | 2025-11-10 |  |  | 3.08 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.08
9 | 46/11 | DA-1.5 | 27.601 |  | 2025-11-11 | 2025-11-12 | 2025-11-16 |  |  | 3.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04
10 | 46/1 | DA-3 | 26.846 |  | 2025-11-16 | 2025-11-17 | 2025-11-21 |  |  | 2.95 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95
11 | 48/0 | DB2+0 | 45.136 |  | 2025-11-22 | 2025-11-23 | 2025-11-29 |  |  | 4.88 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.88
12 | 39/0 | DD45+18 | 89.029 | Team- 03 | 2025-10-16 | 2025-10-19 | 2025-11-07 |  |  | 11.51 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.51
13 | 47/0 | DC1+0 | 51.673 |  | 2025-11-07 | 2025-11-08 | 2025-11-14 |  |  | 5.62 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.62
14 | 47/1 | DA+3 | 29.122 |  | 2025-11-14 | 2025-11-15 | 2025-11-19 |  |  | 3.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6
15 | 54/2 | DA-3 | 26.846 |  | 2025-11-19 | 2025-11-20 | 2025-11-24 |  |  | 2.95 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95
16 | 52/1 | DA-3 | 26.846 |  | 2025-11-24 | 2025-11-25 | 2025-11-29 |  |  | 2.95 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95
17 | 52/2 | DA-3 | 26.846 | Team - 04 | 2025-11-08 | 2025-11-09 | 2025-11-13 |  |  | 2.95 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95
18 | 56/1 | DA+6 | 33.304 |  | 2025-11-13 | 2025-11-14 | 2025-11-18 |  |  | 3.74 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.74
19 | 56/2 | DA-3 | 26.846 |  | 2025-11-18 | 2025-11-19 | 2025-11-23 |  |  | 2.95 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95
20 | 56/3 | DB1+6 | 52.141 |  | 2025-11-23 | 2025-11-24 | 2025-11-30 |  |  | 5.94 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.94
|  |  | 791.144 | [6 empty] | 91.415 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.415
Formulas:
Erection = [Work Plan]+3

## Stringing
Project Code |  |  | TA-418
Name of Line |  |  | 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1)
Activity |  |  | Stringing | Qty |  |  |  |  | Rate | 11.5055
|  |  | Total | 47.84
|  |  | Completed (Oct-25) | 3.579
|  |  | Balance | 44.261
Micro Plan for month |  |  | 2025-11-01 | 9.4 | km | 108.1514 | Rs. Cr
Achievement for Month |  |  | Wk-1 | 0.48 | 5.106% | 5.5226 | 5.106%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 0.48 | 5.106% | 5.5226 | 5.106%
Sl | Section | Section Length (km) | Manual/TSE | Sub-Cont | Work Plan |  |  |  |  | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Matl feeding | Pay-Out |  | Final Sag |  |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[6 empty] | Start | End | Start | End | Rs. Cr. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 36/0 - 36/1 | 0.48 | MANUAL | GANG - 01 | 2025-10-31 | 2025-11-01 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 5.5226 | 2025-11-03 | 0.48 |  |  |  |  | 0.48 | 5.5226 | 0 | 0 | 0 | 0 | 5.5226 | 0
2 | 35/0 - 36/0 | 4.48 | TSE |  | ROW | 2025-11-05 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 51.5445 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.5445
3 | 34/0 - 35/0 | 1.98 | TSE |  | 2025-11-13 | 2025-11-15 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 22.7808 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7808
4 | 40/0 - 41/0 | 2.46 | TSE |  | ROW | 2025-11-23 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 28.3035 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.3035
5 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9.4 | [7 empty] | 108.1514 |  | 0.48 | 0 | 0 | 0 | 0 | 0.48 | 5.5226 | 0 | 0 | 0 | 0 | 5.5226 | 102.6288
Formulas:
End = [Pay-Out]+2
Final Sag = [End]+1
Rate = [Final Sag]+1
Pay-Out = [Rate, row above]
Work Plan = [Pay-Out]-2