## FDN-June25 (hidden)
Project Code |  |  | TA-416
Name of Line |  |  | NEEMRANA-II-BAREILLY (PG) 765KV D/C LINE,WZ-5 (Part-III)
Activity |  |  | Foundation | Qty
|  |  | Total | 302
|  |  | Completed (May-25) | 301
|  |  | Balance | 1
Micro Plan for month |  |  | 2025-06-01 | 1 | Nos | 4925228.89 | Rs. Cr.
Achievement for Month |  |  | Wk-1 | 1 | 100% | 4925228.89 | 100%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
Actual for the Month |  |  | Total | 1 | 1 | 4925228.89 | 1
Sl | Loc No. | Tower type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont | Work Plan | [7 empty] | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[7 empty] | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[7 empty] | Start | End | Start | End | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 38/0 | DC2+18 | FS | 261.196 | 15.029 | AVI | 2025-05-21 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 4925228.89 | 2025-06-03 | 1 |  |  |  |  | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
2 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0
3 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 261.196 | 15.029 | [9 empty] | 4925228.89 |  | 1 | 0 | 0 | 0 | 0 | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
[13 empty] | STUB Setting-1 |  | 7224.33
[13 empty] | Earthing-1 |  | 7782.57
[13 empty] | Total Reve |  | 4940235.79

## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## Erection-Nov25
Sl | Location No. | Tower type | Tower Weight | Gang Name | Manpower | Section Incharge | Supervisor | Power Tools Issued (YES/NO) | Material Feeding | Starting Date | Completion Date | Tack-welding | Final checking | Revenue Planned | Revenue Realised
1 | 20/3 | DA+1.5 | 37.1383 | Govind Mahto-01 | 28 | Shuvam Gupta | Rudra Prasad |  | 2025-10-29 | 2025-10-30 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 346011.8226
2 | 21/2 | DA+6 | 43.8044 | Govind Mahto-01 | 28 | Shuvam Gupta | Rudra Prasad |  | 2025-11-05 | 2025-11-06 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 408118.8097
3 | 21/3 | DA+6 | 43.8044 | Govind Mahto-01 | 28 | Shuvam Gupta | Rudra Prasad |  | 2025-11-12 | 2025-11-13 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 408118.8097
4 | 10/2 | DA+3 | 37.9311 | Jawla Singh-1 | 20 | Shuvam Gupta | Akil Hussain |  | 2025-10-31 | 2025-11-01 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 353397.8779
5 | 14/0 | DD60+18 | 124.95 | Jawla Singh-1 | 20 | Shuvam Gupta | Akil Hussain |  | 2025-11-08 | 2025-11-09 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 1164138.7108
6 | 28/0 | DC2-3 | 64.8843 | Jwala Singh -2 | 26 | Shuvam Gupta | Haridasn |  | 2025-10-30 | 2025-10-31 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 604516.623
7 | 27/6 | DA-3 | 34.7898 | Jwala Singh -2 | 26 | Shuvam Gupta | Haridasn |  | 2025-11-07 | 2025-11-08 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 324131.0934
8 | 23A/0 | DB1+9 | 66.7809 | Jwala Singh -2 | 26 | Shuvam Gupta | Haridasn |  | 2025-11-16 | 2025-11-17 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 622186.9697
9 | 29/2 | DA+0 | 36.1598 | Jwala Singh -2 | 26 | Shuvam Gupta | Haridasn |  | 2025-11-28 | 2025-11-29 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 336894.6611
10 | 9/10 | DA+3 | 37.9311 | Govind Mahto-02 | 25 | Shuvam Gupta | Aman Kr Singh |  | 2025-10-30 | 2025-10-31 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 353397.8779
11 | 9/9 | DA+0 | 36.1598 | Govind Mahto-02 | 25 | Shuvam Gupta | Aman Kr Singh |  | 2025-11-07 | 2025-11-08 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 336894.6611
12 | 9/8 | DA+0 | 36.1598 | Govind Mahto-02 | 25 | Shuvam Gupta | Aman Kr Singh |  | 2025-11-14 | 2025-11-15 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 336894.6611
13 | 22/0 | DC2+15 | 96.8799 | Bhairaw Mahto | 41 | Shuvam Gupta | Dhalchand Mahto |  | 2025-10-27 | 2025-10-28 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 902614.5275
14 | 11/0 | DD45+0 | 73.2445 | Bhairaw Mahto | 41 | Shuvam Gupta | Dhalchand Mahto |  | 2025-11-07 | 2025-11-08 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 682407.7346
15 | 13/0 | DD60+9 | 101.9526 | Bhairaw Mahto | 41 | Shuvam Gupta | Dhalchand Mahto |  | 2025-11-18 | 2025-11-19 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 949875.9872
16 | 13A/0 | DB1+9 | 66.7809 | Bhairaw Mahto | 41 | Shuvam Gupta | Dhalchand Mahto |  | 2025-11-28 | 2025-11-29 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 622186.9697
17 | 27/4 | DA+1.5 | 37.1383 | Pritam Enterprises-3 | 25 | Shuvam Gupta | Nabirul Islam |  | 2025-11-04 | 2025-11-05 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 346011.8226
18 | 27/3 | DA+1.5 | 37.1383 | Pritam Enterprises-3 | 25 | Shuvam Gupta | Nabirul Islam |  | 2025-11-10 | 2025-11-11 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 346011.8226
19 | 27/2 | DA-1.5 | 35.6018 | Pritam Enterprises-3 | 25 | Shuvam Gupta | Nabirul Islam |  | 2025-11-16 | 2025-11-17 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 331695.9203
20 | 27/1 | DA+9 | 45.697 | Pritam Enterprises-3 | 25 | Shuvam Gupta | Nabirul Islam |  | 2025-10-29 | 2025-10-30 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 425751.8425
21 | 3B/3 | DA+6 | 43.8044 | Pritam Enterprises-4 | 24 | Shuvam Gupta | Abhaiya Ojha |  | 2025-11-05 | 2025-11-06 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 408118.8097
22 | 2A/0 | DD45+0 | 73.2445 | Pritam Enterprises-4 | 24 | Shuvam Gupta | Abhaiya Ojha |  | 2025-11-16 | 2025-11-17 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 682407.7346
23 | 35/10 | DA+3 | 37.9311 | Pritam Enterprises-4 | 24 | Kartik Jhorar | Abhaiya Ojha |  | 2025-11-23 | 2025-11-24 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 353397.8779
24 | 35/3 | DA-3 | 34.7898 | Pritam Enterprises-4 | 24 | Kartik Jhorar | Abhaiya Ojha |  | 2025-10-31 | 2025-11-01 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 324131.0934
25 | 20/4 | DA+3 | 37.9311 | Punam kumari-1 | 36 | Shuvam Gupta | Manoj Kr choudhary |  | 2025-11-07 | 2025-11-08 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 353397.8779
26 | 15/9 | DA+0 | 36.1598 | Punam kumari-1 | 36 | Shuvam Gupta | Manoj Kr choudhary |  | 2025-11-14 | 2025-11-15 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 336894.6611
27 | 15/10 | DA-1.5 | 35.6018 | Punam kumari-1 | 36 | Shuvam Gupta | Manoj Kr choudhary |  | 2025-11-21 | 2025-11-22 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 331695.9203
28 | 24/0 | DD60+18 | 124.95 | Fouzi Ratto | 18 | Kartik Jhorar | Manoj Gupta |  | 2025-10-12 | 2025-10-13 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 1164138.7108
29 | 25/0 | DD60+18 | 124.95 | Fouzi Ratto | 18 | Shuvam Gupta | Manoj Gupta |  | 2025-11-10 | 2025-11-11 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 1164138.7108
30 | 26/0 | DD60+35 | 173.5609 | Sherra Const. | 38 | Shuvam Gupta | Khooblal |  | 2025-10-10 | 2025-10-11 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 1617039.2474
31 | 27/0 | DD60+35 | 173.5609 | Sherra Const. | 38 | Shuvam Gupta | Khooblal |  | 2025-10-31 | 2025-11-01 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 1617039.2474
32 | 37/2 | DA+3 | 37.9311 | Amit kumar singh | 28 | Kartik Jhorar | Akabr Ali |  | 2025-11-08 | 2025-11-09 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 353397.8779
33 | 37/3 | DA-1.5 | 35.6018 | Amit kumar singh | 28 | Kartik Jhorar | Akabr Ali |  | 2025-11-14 | 2025-11-15 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 331695.9203
34 | 37/0 | DB2+3 | 62.1162 | Amit kumar singh | 28 | Kartik Jhorar | Akabr Ali |  | 2025-11-20 | 2025-11-21 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 578726.2869
35 | 37/1 | DA+3 | 37.9311 | Amit kumar singh | 28 | Kartik Jhorar | Akabr Ali |  | 2025-11-26 | 2025-11-27 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 353397.8779
36 | 29A/3 | DA+6 | 43.8044 | Vikas kumar Singh | 30 | Shuvam Gupta | Rahul Ravidas |  | 2025-11-11 | 2025-11-12 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 408118.8097
37 | 30/5 | DA+0 | 36.1598 | Vikas kumar Singh | 30 | Kartik Jhorar | Rahul Ravidas |  | 2025-11-17 | 2025-11-18 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 336894.6611
38 | 36/0 | DB2+3 | 62.1162 | Vikas kumar Singh | 30 | Kartik Jhorar | Rahul Ravidas |  | 2025-11-22 | 2025-11-23 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 578726.2869
39 | 16/0 | DC2+0 | 67.2617 | Ramji Structure | 30 | Shuvam Gupta | Kamal Ravidas |  | 2025-11-09 | 2025-11-10 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 626666.7579
40 | 17/0 | DC1+3 | 65.8725 | Ramji Structure | 30 | Shuvam Gupta | Kamal Ravidas |  | 2025-11-20 | 2025-11-21 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 613723.3938
41 | 43/0 | DB1+0 | 55.4509 | Punam kumari-2 | 30 | Kartik Jhorar | Sanjay Kumar |  | 2025-11-09 | 2025-11-10 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 516626.7066
42 | 43/1 | DA-1.5 | 35.6018 | Punam kumari-2 | 30 | Kartik Jhorar | Sanjay Kumar |  | 2025-11-18 | 2025-11-19 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 331695.9203
43 | 43/5 | DC2+0 | 67.2617 | Punam kumari-2 | 30 | Kartik Jhorar | Sanjay Kumar |  | 2025-12-04 | 2025-12-05 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 626666.7579
44 | 15/1 | DA+6 | 43.8044 | Kartik Mahto | 30 | Shuvam Gupta | Tarique |  | 2025-11-09 | 2025-11-10 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 408118.8097
45 | 15/7 | DA+0 | 36.1598 | Kartik Mahto | 30 | Shuvam Gupta | Tarique |  | 2025-11-17 | 2025-11-18 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 336894.6611
46 | 15/11 | DA+0 | 36.1598 | Kartik Mahto | 30 | Shuvam Gupta | Tarique |  | 2025-11-23 | 2025-11-24 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 336894.6611
47 | 21/4 | DA+0 | 36.1598 | SK. Samiul-2 | 28 | Shuvam Gupta | Raju Mahto |  | 2025-11-10 | 2025-11-11 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 336894.6611
48 | 21/5 | DA+0 | 36.1598 | SK. Samiul-2 | 28 | Shuvam Gupta | Raju Mahto |  | 2025-11-17 | 2025-11-18 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 336894.6611
49 | 15/12 | DA+6 | 43.8044 | SK. Samiul-2 | 36 | Shuvam Gupta | Raju Mahto |  | 2025-11-23 | 2025-11-24 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 408118.8097
Formulas:
Material Feeding = [Starting Date]-1
Tack-welding = [Completion Date]+1
Final checking = [Tack-welding]+1
Starting Date = [Completion Date, row above]+1
Completion Date = [Starting Date]+6

## Stringing- Nov25
Name of the line : 765 KV D/C Bikaner III - Neemrana II TL02
Powergrid Bikaner Neemrana Transmission Limited (Power Grid Corporation of India)
Executing Agency:- KEC International Limited
Datewise Stringing planning for the month of November 2025
Micro Plan - Stringing
Sr no | Section Name | Section Length Miter | Tower Erection Status | Tower in section | Insulator Hoisting | Paying Out Start | Paying Out Completed | Final sag complete | Gang Name
1 | AP-6 - AP-7/0 | 4901.236 | Complete | 13 | 2025-11-06 | 2025-11-07 | 2025-11-11 | 2025-11-13 | Rahim Khan
2 | AP-5 - AP-5A/0 | 4418.389 | Complete | 11 | 2025-11-16 | 2025-11-17 | 2025-11-20 | 2025-11-22
3 | AP-5A/0 - AP-6 | 419.48 | Complete | 1 | 2025-11-23 | 2025-11-24 | 2025-11-27 | 2025-11-29
4 | AP-32A/0 - AP-33/0 | 840.439 | Complete | 2 | 2025-11-10 | 2025-11-12 | 2025-11-15 | 2025-11-18 | Tanjira Bibi
5 | AP-32/0 - AP-32A/0 | 3283.51 | Complete | 8 | 2025-11-22 | 2025-11-23 | 2025-11-26 | 2025-11-28
6 | AP-33/0 - AP-34/0 | 4049.764 | Complete | 10 | 2025-11-27 | 2025-11-28 | 2025-11-30 | 2025-12-04
Total length (KM) |  | 17.9128 |  | 45
Formulas:
Paying Out Start = [Insulator Hoisting]+1

## STG-Sep25 (hidden)
Project Code
Name of Line
Activity |  |  | Stringing | Qty |  |  |  |  | Rate @Kms | 905812
|  |  | Total | 115
|  |  | Completed (Aug-25) | 32.6
|  |  | Balance | 82.4
Micro Plan for month |  |  | 2025-09-01 | 23.985 | km | 21725900.82 | Rs. Cr
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 0 | 0% | 0 | 0%
Sl | Section | Section Length (km) | Manual/TSE | Sub-Cont | Work Plan |  |  |  |  | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Matl feeding | Pay-Out |  | Final Sag |  |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[6 empty] | Start | End | Start | End | Rs. Cr. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 14/0-15/0 | 3.611 | TSE | Anarul | 2025-08-30 | 2025-09-01 | 2025-09-08 | 2025-09-09 | 2025-09-12 | 3270887.132 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3270887.132
2 | 12/0-13/0 | 3.92 | TSE |  | 2025-09-13 | 2025-09-14 | 2025-09-19 | 2025-09-20 | 2025-09-22 | 3550783.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550783.04
3 | 3/0-4/0 | 0.28 | Manual-1 |  | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 253627.36 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253627.36
4 | 11/0-12/0 | 0.313 | Manual-1 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 283519.156 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283519.156
5 | 13/0-14/0 | 0.319 | Manual-1 |  | 2025-09-15 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 288954.028 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288954.028
6 | 20/0-21/0 | 4.958 | TSE | Pankaj | 2025-09-03 | 2025-09-04 | 2025-09-09 | 2025-09-10 | 2025-09-13 | 4491015.896 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491015.896
7 | 21/0-22/0 | 1.606 | TSE |  | 2025-09-14 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 1454734.072 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454734.072
8 | 18/0-19/0 | 0.323 | Manual-1 |  | 2025-09-20 | 2025-09-21 | 2025-09-26 | 2025-09-27 | 2025-09-30 | 292577.276 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292577.276
9 | 36/0-37/0 | 4.947 | TSE |  | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-07 | 2025-09-10 | 4481051.964 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4481051.964
10 | 30/0-31/0 | 2.75 | TSE |  | 2025-09-11 | 2025-09-12 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2490983 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490983
11 | 29/0-30/0 | 0.27 | TSE |  | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-22 | 2025-09-22 | 244569.24 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244569.24
12 | 28/0-29/0 | 0.688 | Manual-2 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 623198.656 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623198.656
13 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 23.985 | [7 empty] | 21725900.82 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21725900.82