## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## Erection - Nov'25
Sl | Location No. | Tower type | Tower Weight | Gang Name | Manpower | Section Incharge | Supervisor | Power Tools Issued (YES/NO) | Material Feeding | Starting Date | Completion Date | Tack-welding | Final checking | Revenue Planned | Revenue Realised
1 | 2/0 | DB2+18 | 85 | Infineda 1 | 20 | Mr. Tanay Kumar | Mr. P.D Sharma |  | 2025-11-02 | 2025-11-03 | 2025-11-12 | 2025-11-22 | 2025-11-17 | 651015
2 | 3/0 | DD45+18 | 105 | Infineda 1 | 20 | Mr. Tanay Kumar | Mr. P.D Sharma |  | 2025-11-13 | 2025-11-14 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 804195
3 | 38/8 | DA+3 | 37.9311 | Radha Enterpises 1 | 25 | Mr. Tanay Kumar | Mr. Prince |  | 2025-10-31 | 2025-11-01 | 2025-11-07 | 2025-11-17 | 2025-11-12 | 290514.203
4 | 38/9 | DA-1.5 | 35.6018 | Radha Enterpises 1 | 25 | Mr. Tanay Kumar | Mr. Prince |  | 2025-11-07 | 2025-11-08 | 2025-11-14 | 2025-11-24 | 2025-11-19 | 272673.8952
5 | 38/10 | DA+0 | 36.1598 | Radha Enterpises 1 | 25 | Mr. Tanay Kumar | Mr. Prince |  | 2025-11-14 | 2025-11-15 | 2025-11-21 | 2025-12-01 | 2025-11-26 | 276947.5712
6 | 38/11 | DA+0 | 36.1598 | Radha Enterpises 1 | 25 | Mr. Tanay Kumar | Mr. Prince |  | 2025-11-21 | 2025-11-22 | 30-11-225 | #VALUE! | #VALUE! | 276947.5712
7 | 35/0 | DD45+3 | 77.0769 | Poonam Kumari 1 | 27 | Mr. Tanay Kumar | Mr. Shivbrat |  | 2025-10-26 | 2025-10-27 | 2025-11-06 | 2025-11-16 | 2025-11-11 | 590332.2222
8 | 36/0 | DC1+9 | 75.27 | Poonam Kumari 1 | 27 | Mr. Tanay Kumar | Mr. Shivbrat |  | 2025-11-06 | 2025-11-07 | 2025-11-16 | 2025-11-26 | 2025-11-21 | 576492.93
9 | 41/1 | DA-3 | 34.7898 | Poonam Kumari 1 | 27 | Mr. Tanay Kumar | Mr. Shivbrat |  | 2025-11-16 | 2025-11-17 | 2025-11-22 | 2025-12-02 | 2025-11-27 | 266455.1548
10 | 41/3 | DA+0 | 36.1598 | Poonam Kumari 1 | 27 | Mr. Tanay Kumar | Mr. Shivbrat |  | 2025-11-22 | 2025-11-23 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 276947.5712
11 | 30/0 | DD45+0 | 73.2445 | Poonam kumari 2 | 26 | Mr. Tanay Kumar | Mr. Suresh Ram |  | 2025-10-25 | 2025-10-26 | 2025-11-08 | 2025-11-18 | 2025-11-13 | 560979.9931
12 | 38/0 | DD60+25 | 137.0461 | Poonam kumari 2 | 26 | Mr. Tanay Kumar | Mr. Suresh Ram |  | 2025-11-09 | 2025-11-10 | 2025-11-23 | 2025-12-03 | 2025-11-28 | 1049636.1718
13 | 43/1 | DA+9 | 45.697 | Poonam kumari 2 | 26 | Mr. Tanay Kumar | Mr. Suresh Ram |  | 2025-11-23 | 2025-11-24 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 349993.4915
14 | 36/8 | DA+0 | 36.1598 | Jwala Singh | 22 | Mr. Tanay Kumar | Mr. Satyaprakash |  | 2025-11-01 | 2025-11-02 | 2025-11-08 | 2025-11-18 | 2025-11-13 | 276947.5712
15 | 38/5 | DA+6 | 43.8044 | Jwala Singh | 22 | Mr. Tanay Kumar | Mr. Satyaprakash |  | 2025-11-08 | 2025-11-09 | 2025-11-14 | 2025-11-24 | 2025-11-19 | 335498.0834
16 | 38/6 | DA+1.5 | 37.1383 | Jwala Singh | 22 | Mr. Tanay Kumar | Mr. Satyaprakash |  | 2025-11-14 | 2025-11-15 | 2025-11-21 | 2025-12-01 | 2025-11-26 | 284442.4235
17 | 38/7 | DA+3 | 37.9311 | Jwala Singh | 22 | Mr. Tanay Kumar | Mr. Satyaprakash |  | 2025-11-21 | 2025-11-22 | 2025-11-29 | 2025-12-09 | 2025-12-04 | 290514.203
18 | 40/2 | DA+3 | 37.9311 | Madhu Sah | 24 | Mr. Tanay Kumar |  |  | 2025-10-31 | 2025-11-01 | 2025-11-07 | 2025-11-17 | 2025-11-12 | 290514.203
19 | 40/3 | DA+3 | 37.9311 | Madhu Sah | 24 | Mr. Tanay Kumar |  |  | 2025-11-07 | 2025-11-08 | 2025-11-14 | 2025-11-24 | 2025-11-19 | 290514.203
20 | 40/4 | DA+1.5 | 37.1383 | Madhu Sah | 24 | Mr. Tanay Kumar |  |  | 2025-11-14 | 2025-11-15 | 2025-11-21 | 2025-12-01 | 2025-11-26 | 284442.4235
21 | 40/5 | DA+1.5 | 37.1383 | Madhu Sah | 24 | Mr. Tanay Kumar |  |  | 2025-11-21 | 2025-11-22 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 284442.4235
22 | 9/0 | DC2+9 | 81.828 | Dasrath Mahato | 33 | Mr. Tanay Kumar |  |  | 2025-10-31 | 2025-11-01 | 2025-11-12 | 2025-11-22 | 2025-11-17 | 626720.652
23 | 11/0 | DD60+30 | 160.944 | Dasrath Mahato | 33 | Mr. Tanay Kumar |  |  | 2025-11-12 | 2025-11-13 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 1232670.096
24 | 62/1 | 5DA+6 | 53.324 | Infineda 2 | 27 | Mr. R.N Tyagi |  |  | 2025-10-31 | 2025-11-01 | 2025-11-07 | 2025-11-17 | 2025-11-12 | 408408.516
25 | 62/2 | 5DA+6 | 53.324 | Infineda 2 | 27 | Mr. R.N Tyagi |  |  | 2025-11-07 | 2025-11-08 | 2025-11-14 | 2025-11-24 | 2025-11-19 | 408408.516
26 | 62/3 | 5DB1+6 | 75.866 | Infineda 2 | 27 | Mr. R.N Tyagi |  |  | 2025-11-14 | 2025-11-15 | 1900-01-22 | 1900-02-01 | 1900-01-27 | 581057.694
27 | 62/4 | 5DA-3 | 42.374 | Infineda 2 | 27 | Mr. R.N Tyagi |  |  | 2025-11-23 | 2025-11-24 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 324542.466
28 | 46/1 | 5DA+0 | 43.776 | GRD 1 | 23 | Mr. R.N Tyagi |  |  | 2025-11-05 | 2025-11-06 | 2025-11-13 | 2025-11-23 | 2025-11-18 | 335280.384
29 | 46/2 | 5DA+3 | 46.049 | GRD 1 | 23 | Mr. R.N Tyagi |  |  | 2025-11-13 | 2025-11-14 | 2025-11-22 | 2025-12-02 | 2025-11-27 | 352689.291
30 | 46/3 | 5DA+0 | 43.776 | GRD 1 | 23 | Mr. R.N Tyagi |  |  | 2025-11-22 | 2025-11-23 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 335280.384
31 | 78/1 | 5DA+0 | 43.776 | Sanjeev | 28 | Mr. R.N Tyagi |  |  | 2025-11-05 | 2025-11-06 | 2025-11-13 | 2025-11-23 | 2025-11-18 | 335280.384
32 | 78/3 | 5DA+0 | 43.776 | Sanjeev | 28 | Mr. R.N Tyagi |  |  | 2025-11-13 | 2025-11-14 | 2025-11-22 | 2025-12-02 | 2025-11-27 | 335280.384
33 | 76/3 | 5DA+3 | 46.049 | Sanjeev | 28 | Mr. R.N Tyagi |  |  | 2025-11-22 | 2025-11-23 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 352689.291
34 | 83/5 | 5DA-3 | 42.374 | Samuel | 30 | Mr. R.N Tyagi |  |  | 2025-11-09 | 2025-11-10 | 2025-11-19 | 2025-11-29 | 2025-11-24 | 324542.466
35 | 83/6 | 5DA-3 | 42.374 | Samuel | 30 | Mr. R.N Tyagi |  |  | 2025-11-19 | 2025-11-20 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 324542.466
36 | 84/1 | 5DA+0 | 43.776 | Mukhilal 1 | 26 | Mr. R.N Tyagi |  |  | 2025-11-09 | 2025-11-10 | 2025-11-19 | 2025-11-29 | 2025-11-24 | 335280.384
37 | 84/4 | 5DA-3 | 42.374 | Mukhilal 1 | 26 | Mr. R.N Tyagi |  |  | 2025-11-19 | 2025-11-20 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 324542.466
38 | 41/4 | DA+6 | 43.8044 | Nandlal | 29 | Mr. Tanay Kumar |  |  | 2025-11-09 | 2025-11-10 | 2025-11-19 | 2025-11-29 | 2025-11-24 | 335498.0834
39 | 41/5 | DA+1.5 | 37.1383 | Nandlal | 29 | Mr. Tanay Kumar |  |  | 2025-11-19 | 2025-11-20 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 284442.4235
40 | 40/6 | DA+1.5 | 37.1383 | Jagdish | 24 | Mr. Tanay Kumar |  |  | 2025-11-09 | 2025-11-10 | 2025-11-20 | 2025-11-30 | 2025-11-25 | 284442.4235
41 | 40/7 | DA-1.5 | 35.6018 | Jagdish | 24 | Mr. Tanay Kumar |  |  | 2025-11-20 | 2025-11-21 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 272673.8952
42 | 41/6 | DA+3 | 37.9311 | GRD 2 | 27 | Mr. Tanay Kumar |  |  | 1900-01-10 | 1900-01-11 | 2025-11-21 | 2025-12-01 | 2025-11-26 | 290514.203
43 | 41/7 | DA+0 | 36.1598 | GRD 2 | 27 | Mr. Tanay Kumar |  |  | 2025-11-21 | 2025-11-22 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 276947.5712
44 | 45/0 | 5DD60+9 | 118.43 | Radha Enterpises 2 | 28 | Mr. R.N Tyagi |  |  | 2025-11-11 | 2025-11-12 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 907055.37
45 | 83/7 | 5DA+0 | 43.776 | Mukhilal 2 | 25 | Mr. R.N Tyagi |  |  | 2025-11-11 | 2025-11-12 | 2025-11-20 | 2025-11-30 | 2025-11-25 | 335280.384
46 | 83/1 | 5DA+9 | 55.339 | Mukhilal 2 | 25 | Mr. R.N Tyagi |  |  | 2025-11-20 | 2025-11-21 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 423841.401
47 | 40/0 | DD60+18 | 124.95 | Sanjeet | 29 | Mr. Tanay Kumar |  |  | 2025-11-12 | 2025-11-13 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 956991.6824
48 | 41/0 | DD60+0 | 83.1335 | Lillo Mahato | 29 | Mr. Tanay Kumar |  |  | 2025-11-12 | 2025-11-13 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 636719.6756
49 | 43/0 | DD60+18 | 124.95 | Jwala Singh 2 | 30 | Mr. Tanay Kumar |  |  | 2025-11-14 | 2025-11-15 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 956991.6824
50 | 46/0 | 5DD60+18 | 143.462 | Punam Kumari 3 | 29 | Mr. R.N Tyagi |  |  | 2025-11-14 | 2025-11-15 | 2025-11-30 | 2025-12-10 | 2025-12-05 | 1098775.458
Formulas:
Material Feeding = [Starting Date]-1
Tack-welding = [Completion Date]+10
Final checking = [Completion Date]+5