## Summary
765 kV D/C BEAWAR MANDSAUR TRANSMISSION LINE
Revenue Cost (November-2025)
Sr. No. | Description | UOM | Locations (As per Micro Plan) | Locations (To be Achieved) | Amount in Rs. (As per Micro Plan) | Amount in Rs (To be Achieved)
1 | Foundation | Nos | 30 | 0 | 20607390.2706 | 0
2 | Erection | Nos | 60 | 0 | 33002807.4 | 0
3 | Stringing | Kms | - |  | -
| Total Amount (Rs) = |  |  |  | 53610197.6706 | 0

## FDN
Project Code |  |  | TA-505
Name of Line |  |  | 765KV D/C BEAWAR MANDSAUR (PKG-TL02)
Activity |  |  | Foundation | Qty
|  |  | Total | 379
|  |  | Completed (Till Oct-25) | 295
|  |  | Balance | 84
Micro Plan for month |  |  | 2025-11-01 | 30 | Nos | 20291220.2706 | Rs. Cr. |  |  |  | Total Cost with Earthing |  | 316170 | 20607390.2706
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
Actual for the Month |  |  | Total | 0 | 0 | 0 | 0 |  |  |  | Actual Cost with Earthing |  | 0 | 0
SL | Loc No. | Tower Type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont | KEC Responsibility | Section | Work Plan | [7 empty] | Revenue | Remarks/ Current Status | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[9 empty] | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling |  |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[9 empty] | Start | End | Start | End | Start | End |  |  | Rs. Lacs. |  | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 169/8 | DA+0 | DRY | 26.39 | 1.979 | Saktawat | P. Satish | MP | 2025-11-01 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-10 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 485697.6 | RoW | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
2 | 169/9 | DA-3 | DRY | 26.39 | 1.979 | Saktawat | P. Satish | MP | 2025-11-04 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-16 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 485697.6 | RoW | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
3 | 169/0 | DC1+3 | DFR | 83.13 | 3.855 | Saktawat | P. Satish | MP | 2025-11-07 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-22 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 1235682.7 | WIP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235682.7
4 | 165/2 | DA+0 | DRY | 26.39 | 1.979 | Garg Const. | P. Satish | MP | 2025-11-01 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-10 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 485697.6 | WIP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
5 | 162/1 | DA+0 | DRY | 26.39 | 1.979 | Garg Const. | P. Satish | MP | 2025-11-04 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-17 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 485697.6 | RoW | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
6 | 162/2 | DA+0 | DRY | 26.39 | 1.979 | Garg Const. | P. Satish | MP | 2025-11-07 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-24 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 485697.6 | RoW | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
7 | 162/0 | DB2+0 | DFR | 76.03 | 3.4 | RESHMI DEVI | P. Satish | MP | 2025-11-01 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-10 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 922043.6526 | RoW | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 922043.6526
8 | 182B/0 | DD60+0 | DFR | 134.53 | 10.94 | RESHMI DEVI | P. Satish | MP | 2025-11-04 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-16 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 1268583.84 | Active Front | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268583.84
9 | 179/3 | DA+0 | DRY | 26.39 | 1.979 | RESHMI DEVI | P. Satish | MP | 2025-11-07 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-22 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 485697.6 | RoW | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
10 | 182/0 | DD60+6 | DFR | 137.34 | 11.51 | RESHMI DEVI | P. Satish | MP | 2025-11-10 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-26 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 1268583.84 | Active Front | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268583.84
11 | 171/5 | DA+0 | DRY | 26.39 | 1.979 | INFINITY CONST. | P. Satish | MP | 2025-11-01 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-10 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 485697.6 | Active Front | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
12 | 179/9 | DA+3 | DRY | 29.42 | 2.473 | INFINITY CONST. | P. Satish | MP | 2025-11-04 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-16 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 564041.6 | WIP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564041.6
13 | 181/1 | DA+0 | DRY | 26.39 | 1.979 | INFINITY CONST. | P. Satish | MP | 2025-11-07 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-22 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 485697.6 | RoW | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
14 | 181/2 | DA-3 | DRY | 26.39 | 1.979 | INFINITY CONST. | P. Satish | MP | 2025-11-10 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-26 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 485697.6 | RoW | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
15 | 181/3 | DA-3 | DRY | 26.39 | 1.979 | New Gang-MP | P. Satish | MP | 2025-11-01 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-10 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 485697.6 | RoW | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
16 | 181/4 | DA-3 | DRY | 26.39 | 1.979 | New Gang-MP | P. Satish | MP | 2025-11-04 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-16 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 485697.6 | RoW | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
17 | 181/5 | DA-3 | DRY | 26.39 | 1.979 | New Gang-MP | P. Satish | MP | 2025-11-07 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-22 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 485697.6 | RoW | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
18 | 181/6 | DA+0 | DRY | 26.39 | 1.979 | New Gang-MP | P. Satish | MP | 2025-11-10 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-26 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 485697.6 | Active Front | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
19 | 99/7 | DA+0 | DFR | 30.22 | 1.45 | Sumit Const. | Deepak Anand | RAJ | 2025-11-01 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-10 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 485697.6 | WIP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
20 | 99/5 | DA+0 | DFR | 30.22 | 1.45 | Sumit Const. | Deepak Anand | RAJ | 2025-11-04 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-13 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 485697.6 | WIP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
21 | 99/4 | DA+0 | DFR | 30.22 | 1.45 | Sumit Const. | Deepak Anand | RAJ | 2025-11-07 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-16 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 485697.6 | Active Front | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
22 | 99/3 | DA+0 | DFR | 30.22 | 1.45 | Sumit Const. | Deepak Anand | RAJ | 2025-11-10 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-19 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 485697.6 | Active Front | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485697.6
23 | 99/2 | DA+6 | DFR | 34.29 | 1.802 | Sumit Const. | Deepak Anand | RAJ | 2025-11-13 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-22 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 564041.6 | Active Front | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564041.6
24 | 99/1 | DA+6 | DFR | 34.29 | 1.802 | Sumit Const. | Deepak Anand | RAJ | 2025-11-16 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-25 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 564041.6 | Active Front | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564041.6
25 | 103/5 | DA+3 (RC) | DFR | 34.29 | 1.802 | Sumit Const. | Deepak Anand | RAJ | 2025-11-19 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-28 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 564041.6 | Active Front | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564041.6
26 | 153/0 | DB1+6 | DFR | 63.78 | 2.692 | Vikash Const. | Deepak Anand | RAJ | 2025-11-01 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-10 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 812044.6526 | WIP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812044.6526
27 | 154/0 | DB2+9 | DFR | 76.69 | 3.466 | Vikash Const. | Deepak Anand | RAJ | 2025-11-04 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-21 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 922043.6526 | Active Front | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 922043.6526
28 | 138/0 | DB1+3 (RC) | DFR | 63.78 | 2.692 | RST | Deepak Anand | RAJ | 2025-11-01 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-10 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 812044.6526 | WIP | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812044.6526
29 | 122/0 | DD60+3 | DFR | 137.34 | 11.51 | RST | Deepak Anand | RAJ | 2025-11-04 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-16 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 1268583.84 | Active Front | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268583.84
30 | 123/0 | DD60+6 | DFR | 137.34 | 11.51 | RST | Deepak Anand | RAJ | 2025-11-07 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-22 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 1268583.84 | Active Front | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268583.84
|  |  |  | 1506.2 | 100.981 | [11 empty] | 20291220.2706 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20291220.2706
Formulas:
End = [Work Plan]+2
End = [Stub-setting]+1
Stub-setting = [End]+1
Concreting = [End]+5
Concreting = [End, row above]+1
Earthing = [End]+1
Backfilling = [Earthing]+1
Work Plan = [End, row above]+1

## Erection-Nov25
Project Code |  |  | TA-505
Name of Line |  |  | 765KV D/C BEAWAR MANDSAUR (PKG-TL-02)
Activity |  |  | Erection | Qty
|  |  | Total | 379
|  |  | Completed (Till -Oct 25) | 153
|  |  | Balance | 226
Micro Plan for month |  |  | 2025-11-01 | 60 | Nos | 33002807.4 | Rs. Cr
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 0 | 0% | 0 | 0%
[5 empty] | Work Plan | [11 empty] | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[6 empty] | Erection | [11 empty] | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Revenue Realised
SL | Location No. | Tower type | Tower Weight | Gang Name | Material Feeding | Starting Date | Completion Date | Tack-welding | Final checking | SECTION | Supervisor | Manpower | Power Tools Issued (YES/NO) | Section Incharge | Revenue Planned | Revenue Realised | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 110/0 | DC2+3 | 70.745 | Jwala Singh | 2025-11-01 | 2025-11-02 | 2025-11-07 | 2025-11-08 | 2025-11-10 | RAJ |  |  |  | Deepak Anand | 773950.3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773950.3
2 | 103/4 | DA+0 | 36.16 | Jwala Singh | 2025-11-07 | 2025-11-08 | 2025-11-11 | 2025-11-12 | 2025-11-14 | RAJ |  |  |  | Deepak Anand | 395590.4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
3 | 109/0 | DC1+0 | 62.444 | Jwala Singh | 2025-11-11 | 2025-11-12 | 2025-11-17 | 2025-11-18 | 2025-11-19 | RAJ |  |  |  | Deepak Anand | 683137.36 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 683137.36
4 | 100/0 | DD45+0 | 73.245 | Jwala Singh | 2025-11-17 | 2025-11-18 | 2025-11-23 | 2025-11-24 | 2025-11-25 | RAJ |  |  |  | Deepak Anand | 801300.3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801300.3
5 | 118/0 | DD60+6 | 97.168 | Jwala Singh | 2025-11-23 | 2025-11-24 | 2025-11-30 | 2025-12-01 | 2025-12-02 | RAJ |  |  |  | Deepak Anand | 1063017.92 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063017.92
6 | 135/1 | DA+3 | 37.931 | Jhemon Mahto | 2025-11-01 | 2025-11-02 | 2025-11-07 | 2025-11-08 | 2025-11-10 | RAJ |  |  |  | Deepak Anand | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
7 | 135/3 | DA+9 | 45.697 | Jhemon Mahto | 2025-11-07 | 2025-11-08 | 2025-11-11 | 2025-11-12 | 2025-11-14 | RAJ |  |  |  | Deepak Anand | 499925.18 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499925.18
8 | 144A/3 | DB1+3 | 57.963 | Jhemon Mahto | 2025-11-11 | 2025-11-12 | 2025-11-17 | 2025-11-18 | 2025-11-19 | RAJ |  |  |  | Deepak Anand | 634115.22 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634115.22
9 | 114/4 | DA+3 | 37.931 | Jhemon Mahto | 2025-11-17 | 2025-11-18 | 2025-11-23 | 2025-11-24 | 2025-11-25 | RAJ |  |  |  | Deepak Anand | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
10 | 144A/2 | DA+3 | 37.931 | Jhemon Mahto | 2025-11-23 | 2025-11-24 | 2025-11-30 | 2025-12-01 | 2025-12-02 | RAJ |  |  |  | Deepak Anand | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
11 | 126/3 | DA+3 | 37.931 | Sheela Devi | 2025-11-01 | 2025-11-02 | 2025-11-06 | 2025-11-07 | 2025-11-09 | RAJ |  |  |  | Deepak Anand | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
12 | 141/0 | DD45+0 | 73.245 | Sheela Devi | 2025-11-06 | 2025-11-07 | 2025-11-15 | 2025-11-16 | 2025-11-18 | RAJ |  |  |  | Deepak Anand | 801300.3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801300.3
13 | 130/2 | DA-1.5 | 35.602 | Sheela Devi | 2025-11-15 | 2025-11-16 | 2025-11-20 | 2025-11-21 | 2025-11-22 | RAJ |  |  |  | Deepak Anand | 389485.88 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389485.88
14 | 145/0 | DD60+18 | 124.95 | Sheela Devi | 2025-11-20 | 2025-11-21 | 2025-11-29 | 2025-11-30 | 2025-12-01 | RAJ |  |  |  | Deepak Anand | 1366953 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366953
15 | 147/0 | DB2+6 | 69.376 | Toushan Mahto | 2025-11-01 | 2025-11-02 | 2025-11-07 | 2025-11-08 | 2025-11-10 | RAJ |  |  |  | Deepak Anand | 758973.44 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 758973.44
16 | 132/0 | DD60+6 | 97.168 | Toushan Mahto | 2025-11-07 | 2025-11-08 | 2025-11-18 | 2025-11-19 | 2025-11-21 | RAJ |  |  |  | Deepak Anand | 1063017.92 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063017.92
17 | 148A/0 | DB1+6 | 65.028 | Toushan Mahto | 2025-11-18 | 2025-11-19 | 2025-11-24 | 2025-11-25 | 2025-11-26 | RAJ |  |  |  | Deepak Anand | 711406.32 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711406.32
18 | 149B/2 | DA+6 | 43.804 | Toushan Mahto | 2025-11-24 | 2025-11-25 | 2025-11-30 | 2025-12-01 | 2025-12-02 | RAJ |  |  |  | Deepak Anand | 479215.76 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479215.76
19 | 99/8 | DA+6 | 43.804 | Deglal Mahto | 2025-11-01 | 2025-11-02 | 2025-11-10 | 2025-11-11 | 2025-11-13 | RAJ |  |  |  | Deepak Anand | 479215.76 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479215.76
20 | 136/2 | DA+3 | 37.931 | Deglal Mahto | 2025-11-10 | 2025-11-11 | 2025-11-19 | 2025-11-20 | 2025-11-22 | RAJ |  |  |  | Deepak Anand | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
21 | 136/5 | DA+3 | 37.931 | Deglal Mahto | 2025-11-19 | 2025-11-20 | 2025-11-28 | 2025-11-29 | 2025-11-30 | RAJ |  |  |  | Deepak Anand | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
22 | 149B/3 | DA+3 | 37.931 | Jyoti Enterprises | 2025-11-01 | 2025-11-02 | 2025-11-06 | 2025-11-07 | 2025-11-09 | RAJ |  |  |  | Deepak Anand | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
23 | 140/0 | DC1+9 | 75.279 | Jyoti Enterprises | 2025-11-06 | 2025-11-07 | 2025-11-13 | 2025-11-14 | 2025-11-16 | RAJ |  |  |  | Bapan Mandal | 823552.26 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823552.26
24 | 149B/4 | DA+0 | 36.16 | Jyoti Enterprises | 2025-11-13 | 2025-11-14 | 2025-11-18 | 2025-11-19 | 2025-11-20 | RAJ |  |  |  | Bapan Mandal | 395590.4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
25 | 151/0 | DD45+3 | 77.077 | Jyoti Enterprises | 2025-11-18 | 2025-11-19 | 2025-11-29 | 2025-11-30 | 2025-12-01 | RAJ |  |  |  | Bapan Mandal | 843222.38 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843222.38
26 | 135/3 | DA+9 | 45.697 | Sandeep Singh | 2025-11-01 | 2025-11-02 | 2025-11-10 | 2025-11-11 | 2025-11-13 | RAJ |  |  |  | Bapan Mandal | 499925.18 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499925.18
27 | 142/0 | DD45+3 | 77.077 | Sandeep Singh | 2025-11-10 | 2025-11-11 | 2025-11-19 | 2025-11-20 | 2025-11-22 | RAJ |  |  |  | Bapan Mandal | 843222.38 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843222.38
28 | 152/0 | DD60+6 | 97.168 | Sandeep Singh | 2025-11-19 | 2025-11-20 | 2025-11-28 | 2025-11-29 | 2025-11-30 | RAJ |  |  |  | Bapan Mandal | 1063017.92 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063017.92
29 | 152/1 | DA+6 | 43.804 | Prayag Shah | 2025-11-01 | 2025-11-02 | 2025-11-10 | 2025-11-11 | 2025-11-13 | RAJ |  |  |  | Bapan Mandal | 479215.76 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479215.76
30 | 152/2 | DA+0 | 36.16 | Prayag Shah | 2025-11-10 | 2025-11-11 | 2025-11-19 | 2025-11-20 | 2025-11-22 | MP |  |  |  | Sujit Roy | 395590.4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
31 | 152/3 | DA-1.5 | 35.602 | Prayag Shah | 2025-11-19 | 2025-11-20 | 2025-11-28 | 2025-11-29 | 2025-11-30 | MP |  |  |  | Sujit Roy | 389485.88 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389485.88
32 | 152A/0 | DB1+0 | 55.451 | Anil Kumar | 2025-11-01 | 2025-11-02 | 2025-11-10 | 2025-11-11 | 2025-11-13 | MP |  |  |  | Sujit Roy | 606633.94 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606633.94
33 | 152A/6 | DA+0 | 36.16 | Anil Kumar | 2025-11-10 | 2025-11-11 | 2025-11-19 | 2025-11-20 | 2025-11-22 | MP |  |  |  | Sujit Roy | 395590.4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
34 | 159/3 | DA+0 | 36.16 | Anil Kumar | 2025-11-19 | 2025-11-20 | 2025-11-28 | 2025-11-29 | 2025-11-30 | MP |  |  |  | Sujit Roy | 395590.4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
35 | 161/0 | DB2+3 | 62.116 | Parmanand | 2025-11-01 | 2025-11-02 | 2025-11-10 | 2025-11-11 | 2025-11-13 | MP |  |  |  | Sujit Roy | 679549.04 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679549.04
36 | 159/0 | DB2+0 | 59.501 | Jagannath Mahto | 2025-11-01 | 2025-11-02 | 2025-11-10 | 2025-11-11 | 2025-11-13 | MP |  |  |  | Sujit Roy | 650940.94 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650940.94
37 | 164/2 | DA+0 | 36.16 | Jagannath Mahto | 2025-11-10 | 2025-11-11 | 2025-11-19 | 2025-11-20 | 2025-11-22 | MP |  |  |  | Sujit Roy | 395590.4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
38 | 164/3 | DA+3 | 37.931 | Jagannath Mahto | 2025-11-19 | 2025-11-20 | 2025-11-28 | 2025-11-29 | 2025-11-30 | MP |  |  |  | Sujit Roy | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
39 | 159/3 | DA+0 | 36.16 | Parmanand | 2025-11-10 | 2025-11-11 | 2025-11-19 | 2025-11-20 | 2025-11-22 | MP |  |  |  | Sujit Roy | 395590.4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
40 | 161/1 | DA+3 | 37.931 | Parmanand | 2025-11-19 | 2025-11-20 | 2025-11-28 | 2025-11-29 | 2025-11-30 | MP |  |  |  | Sujit Roy | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
41 | 167/1 | DA+0 | 36.16 | Pankaj Singh | 2025-11-01 | 2025-11-02 | 2025-11-10 | 2025-11-11 | 2025-11-13 | MP |  |  |  | Sujit Roy | 395590.4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
42 | 164/5 | DA+6 | 43.804 | Pankaj Singh | 2025-11-10 | 2025-11-11 | 2025-11-19 | 2025-11-20 | 2025-11-22 | MP |  |  |  | Sujit Roy | 479215.76 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479215.76
43 | 161/5 | DA+6 | 43.804 | Pankaj Singh | 2025-11-19 | 2025-11-20 | 2025-11-28 | 2025-11-29 | 2025-11-30 | MP |  |  |  | Sujit Roy | 479215.76 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479215.76
44 | 164/6 | DA+3 | 37.931 | Deglal Mahto (MP) | 2025-11-01 | 2025-11-02 | 2025-11-06 | 2025-11-07 | 2025-11-09 | MP |  |  |  | Sujit Roy | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
45 | 164/7 | DA+3 | 37.931 | Deglal Mahto (MP) | 2025-11-06 | 2025-11-07 | 2025-11-13 | 2025-11-14 | 2025-11-16 | MP |  |  |  | Sujit Roy | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
46 | 164/8 | DA+6 | 43.804 | Deglal Mahto (MP) | 2025-11-13 | 2025-11-14 | 2025-11-18 | 2025-11-19 | 2025-11-20 | MP |  |  |  | Sujit Roy | 479215.76 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479215.76
47 | 165/0 | DB1+6 | 65.028 | Deglal Mahto (MP) | 2025-11-18 | 2025-11-19 | 2025-11-29 | 2025-11-30 | 2025-12-01 | MP |  |  |  | Sujit Roy | 711406.32 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711406.32
48 | 172/5 | DA+3 | 37.931 | CRANE TEAM | 2025-10-31 | 2025-11-01 | 2025-11-04 | 2025-11-05 | 2025-11-06 | MP |  |  |  | P.Sathish | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
49 | 172/6 | DA+0 | 36.16 | CRANE TEAM | 2025-11-01 | 2025-11-02 | 2025-11-05 | 2025-11-06 | 2025-11-07 | MP |  |  |  | P.Sathish | 395590.4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
50 | 173/0 | DB2+0 | 59.501 | CRANE TEAM | 2025-11-02 | 2025-11-03 | 2025-11-06 | 2025-11-07 | 2025-11-08 | MP |  |  |  | P.Sathish | 650940.94 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650940.94
51 | 173/1 | DA-3 | 34.79 | CRANE TEAM | 2025-11-04 | 2025-11-05 | 2025-11-08 | 2025-11-09 | 2025-11-10 | MP |  |  |  | P.Sathish | 380602.6 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380602.6
52 | 173/2 | DA+3 | 37.931 | CRANE TEAM | 2025-11-07 | 2025-11-08 | 2025-11-11 | 2025-11-12 | 2025-11-13 | MP |  |  |  | P.Sathish | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
53 | 173/3 | DA+3 | 37.931 | CRANE TEAM | 2025-11-09 | 2025-11-10 | 2025-11-13 | 2025-11-14 | 2025-11-15 | MP |  |  |  | P.Sathish | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
54 | 173/4 | DA+3 | 37.931 | CRANE TEAM | 2025-11-12 | 2025-11-13 | 2025-11-16 | 2025-11-17 | 2025-11-18 | MP |  |  |  | P.Sathish | 414965.14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414965.14
55 | 174A/0 | DC1+3 | 65.873 | CRANE TEAM | 2025-11-14 | 2025-11-15 | 2025-11-18 | 2025-11-19 | 2025-11-20 | MP |  |  |  | P.Sathish | 720650.62 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720650.62
56 | 174A/1 | DA-3 | 34.79 | CRANE TEAM | 2025-11-18 | 2025-11-19 | 2025-11-22 | 2025-11-23 | 2025-11-24 | MP |  |  |  | P.Sathish | 380602.6 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380602.6
57 | 174A/2 | DA+0 | 36.16 | CRANE TEAM | 2025-11-20 | 2025-11-21 | 2025-11-24 | 2025-11-25 | 2025-11-26 | MP |  |  |  | P.Sathish | 395590.4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
58 | 174A/3 | DA+0 | 36.16 | CRANE TEAM | 2025-11-22 | 2025-11-23 | 2025-11-26 | 2025-11-27 | 2025-11-28 | MP |  |  |  | P.Sathish | 395590.4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395590.4
59 | 174A/4 | DA-3 | 34.79 | CRANE TEAM | 2025-11-24 | 2025-11-25 | 2025-11-28 | 2025-11-29 | 2025-11-30 | MP |  |  |  | P.Sathish | 380602.6 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380602.6
60 | 174A/5 | DA-3 | 34.79 | CRANE TEAM | 2025-11-28 | 2025-11-29 | 2025-12-01 | 2025-12-02 | 2025-12-03 | MP |  |  |  | P.Sathish | 380602.6 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380602.6
|  |  | 3016.71 | [11 empty] | 33002807.4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33002807.4
Formulas:
Erection = [Work Plan]+1
Erection = [Completion Date, row above]+1
Completion Date = [Erection]+5
Tack-welding = [Completion Date]+1
Final checking = [Tack-welding]+2
Work Plan = [Completion Date, row above]
Work Plan = [Erection]-1