## ProdDailyExpandedSingles
Work Date | Start Date | Complete Date | Gang name | Tower Weight | Tower Type | Productivity | Project Code | Line Name | Project Name | Project Display | Project Scope Key | Location No. | Status
2026-01-27 | 2026-01-27 | 2026-01-31 | S R Enterprises | 8.334 | DA+3 | 1.6668 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/1 | Completed
2026-01-28 | 2026-01-27 | 2026-01-31 | S R Enterprises | 8.334 | DA+3 | 1.6668 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/1 | Completed
2026-01-29 | 2026-01-27 | 2026-01-31 | S R Enterprises | 8.334 | DA+3 | 1.6668 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/1 | Completed
2026-01-30 | 2026-01-27 | 2026-01-31 | S R Enterprises | 8.334 | DA+3 | 1.6668 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/1 | Completed
2026-01-31 | 2026-01-27 | 2026-01-31 | S R Enterprises | 8.334 | DA+3 | 1.6668 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/1 | Completed
2026-02-03 | 2026-02-03 | 2026-02-06 | S R Enterprises | 8.334 | DA+3 | 2.0835 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/2 | Completed
2026-02-04 | 2026-02-03 | 2026-02-06 | S R Enterprises | 8.334 | DA+3 | 2.0835 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/2 | Completed
2026-02-05 | 2026-02-03 | 2026-02-06 | S R Enterprises | 8.334 | DA+3 | 2.0835 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/2 | Completed
2026-02-06 | 2026-02-03 | 2026-02-06 | S R Enterprises | 8.334 | DA+3 | 2.0835 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/2 | Completed
2026-02-07 | 2026-02-07 | 2026-02-14 | S R Enterprises | 13.664 | DD+0 | 1.708 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/0 | Completed
2026-02-08 | 2026-02-07 | 2026-02-14 | S R Enterprises | 13.664 | DD+0 | 1.708 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/0 | Completed
2026-02-09 | 2026-02-07 | 2026-02-14 | S R Enterprises | 13.664 | DD+0 | 1.708 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/0 | Completed
2026-02-10 | 2026-02-07 | 2026-02-14 | S R Enterprises | 13.664 | DD+0 | 1.708 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/0 | Completed
2026-02-11 | 2026-02-07 | 2026-02-14 | S R Enterprises | 13.664 | DD+0 | 1.708 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/0 | Completed
2026-02-12 | 2026-02-07 | 2026-02-14 | S R Enterprises | 13.664 | DD+0 | 1.708 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/0 | Completed
2026-02-13 | 2026-02-07 | 2026-02-14 | S R Enterprises | 13.664 | DD+0 | 1.708 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/0 | Completed
2026-02-14 | 2026-02-07 | 2026-02-14 | S R Enterprises | 13.664 | DD+0 | 1.708 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 10/0 | Completed
2026-02-14 | 2026-02-14 | 2026-02-16 | S R Enterprises | 8.334 | DA+3 | 2.778 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 11/1 | Completed
2026-02-15 | 2026-02-14 | 2026-02-16 | S R Enterprises | 8.334 | DA+3 | 2.778 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 11/1 | Completed
2026-02-16 | 2026-02-14 | 2026-02-16 | S R Enterprises | 8.334 | DA+3 | 2.778 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 11/1 | Completed
2026-02-16 | 2026-02-16 | 2026-02-18 | S R Enterprises | 6.808 | DA+0 | 2.2693 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 11/3 | Completed
2026-02-17 | 2026-02-16 | 2026-02-18 | S R Enterprises | 6.808 | DA+0 | 2.2693 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 11/3 | Completed
2026-02-18 | 2026-02-16 | 2026-02-18 | S R Enterprises | 6.808 | DA+0 | 2.2693 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 11/3 | Completed
2026-02-18 | 2026-02-18 | 2026-02-18 | S R Enterprises | 8.334 | DA+3 | 8.334 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 11/2 | Completed
2026-05-19 | 2026-05-19 | 2026-05-21 | K2 Kumar | 8.334 | DA+3 | 2.778 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/1 | Completed
2026-05-20 | 2026-05-19 | 2026-05-21 | K2 Kumar | 8.334 | DA+3 | 2.778 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/1 | Completed
2026-05-21 | 2026-05-19 | 2026-05-21 | K2 Kumar | 8.334 | DA+3 | 2.778 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/1 | Completed
2026-05-26 | 2026-05-26 | 2026-05-28 | K2 Kumar | 6.809 | DA+0 | 2.2697 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 7/1 | Completed
2026-05-27 | 2026-05-26 | 2026-05-28 | K2 Kumar | 6.809 | DA+0 | 2.2697 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 7/1 | Completed
2026-05-28 | 2026-05-26 | 2026-05-28 | K2 Kumar | 6.809 | DA+0 | 2.2697 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 7/1 | Completed
2026-02-07 | 2026-02-07 | 2026-02-14 | Pinki Devi | 20.631 | DA+6 | 2.5789 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 32/1 | Completed
2026-02-08 | 2026-02-07 | 2026-02-14 | Pinki Devi | 20.631 | DA+6 | 2.5789 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 32/1 | Completed
2026-02-09 | 2026-02-07 | 2026-02-14 | Pinki Devi | 20.631 | DA+6 | 2.5789 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 32/1 | Completed
2026-02-10 | 2026-02-07 | 2026-02-14 | Pinki Devi | 20.631 | DA+6 | 2.5789 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 32/1 | Completed
2026-02-11 | 2026-02-07 | 2026-02-14 | Pinki Devi | 20.631 | DA+6 | 2.5789 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 32/1 | Completed
2026-02-12 | 2026-02-07 | 2026-02-14 | Pinki Devi | 20.631 | DA+6 | 2.5789 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 32/1 | Completed
2026-02-13 | 2026-02-07 | 2026-02-14 | Pinki Devi | 20.631 | DA+6 | 2.5789 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 32/1 | Completed
2026-02-14 | 2026-02-07 | 2026-02-14 | Pinki Devi | 20.631 | DA+6 | 2.5789 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 32/1 | Completed
2026-02-14 | 2026-02-14 | 2026-02-17 | Pinki Devi | 16.922 | DA+0 | 4.2305 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 27/4 | Completed
2026-02-15 | 2026-02-14 | 2026-02-17 | Pinki Devi | 16.922 | DA+0 | 4.2305 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 27/4 | Completed
2026-02-16 | 2026-02-14 | 2026-02-17 | Pinki Devi | 16.922 | DA+0 | 4.2305 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 27/4 | Completed
2026-02-17 | 2026-02-14 | 2026-02-17 | Pinki Devi | 16.922 | DA+0 | 4.2305 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 27/4 | Completed
2026-02-17 | 2026-02-17 | 2026-02-25 | Pinki Devi | 37.87 | DD+0 | 4.2078 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 29/0 | Completed
2026-02-17 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-02-18 | 2026-02-17 | 2026-02-25 | Pinki Devi | 37.87 | DD+0 | 4.2078 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 29/0 | Completed
2026-02-18 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-02-19 | 2026-02-17 | 2026-02-25 | Pinki Devi | 37.87 | DD+0 | 4.2078 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 29/0 | Completed
2026-02-19 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-02-20 | 2026-02-17 | 2026-02-25 | Pinki Devi | 37.87 | DD+0 | 4.2078 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 29/0 | Completed
2026-02-20 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-02-21 | 2026-02-17 | 2026-02-25 | Pinki Devi | 37.87 | DD+0 | 4.2078 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 29/0 | Completed
2026-02-21 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-02-22 | 2026-02-17 | 2026-02-25 | Pinki Devi | 37.87 | DD+0 | 4.2078 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 29/0 | Completed
2026-02-22 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-02-23 | 2026-02-17 | 2026-02-25 | Pinki Devi | 37.87 | DD+0 | 4.2078 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 29/0 | Completed
2026-02-23 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-02-24 | 2026-02-17 | 2026-02-25 | Pinki Devi | 37.87 | DD+0 | 4.2078 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 29/0 | Completed
2026-02-24 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-02-25 | 2026-02-17 | 2026-02-25 | Pinki Devi | 37.87 | DD+0 | 4.2078 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 29/0 | Completed
2026-02-25 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-02-26 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-02-27 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-02-28 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-03-01 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-03-02 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-03-03 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-03-04 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-03-05 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-03-06 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-03-07 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-03-08 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-03-08 | 2026-03-08 | 2026-03-15 | Rang Construction | 28.063 | DB+3 | 3.5079 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/0 | Completed
2026-03-09 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-03-09 | 2026-03-08 | 2026-03-15 | Rang Construction | 28.063 | DB+3 | 3.5079 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/0 | Completed
2026-03-10 | 2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 28/0 | Completed
2026-03-10 | 2026-03-08 | 2026-03-15 | Rang Construction | 28.063 | DB+3 | 3.5079 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/0 | Completed
2026-03-11 | 2026-03-08 | 2026-03-15 | Rang Construction | 28.063 | DB+3 | 3.5079 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/0 | Completed
2026-03-12 | 2026-03-08 | 2026-03-15 | Rang Construction | 28.063 | DB+3 | 3.5079 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/0 | Completed
2026-03-13 | 2026-03-08 | 2026-03-15 | Rang Construction | 28.063 | DB+3 | 3.5079 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/0 | Completed
2026-03-14 | 2026-03-08 | 2026-03-15 | Rang Construction | 28.063 | DB+3 | 3.5079 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/0 | Completed
2026-03-15 | 2026-03-08 | 2026-03-15 | Rang Construction | 28.063 | DB+3 | 3.5079 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/0 | Completed
2026-03-21 | 2026-03-21 | 2026-03-30 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 24/0 | Completed
2026-03-22 | 2026-03-21 | 2026-03-30 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 24/0 | Completed
2026-03-23 | 2026-03-21 | 2026-03-30 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 24/0 | Completed
2026-03-24 | 2026-03-21 | 2026-03-30 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 24/0 | Completed
2026-03-25 | 2026-03-21 | 2026-03-30 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 24/0 | Completed
2026-03-25 | 2026-03-25 | 2026-03-31 | Rang Construction | 38.079 | DC+6 | 5.4399 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/0 | Completed
2026-03-26 | 2026-03-21 | 2026-03-30 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 24/0 | Completed
2026-03-26 | 2026-03-25 | 2026-03-31 | Rang Construction | 38.079 | DC+6 | 5.4399 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/0 | Completed
2026-03-27 | 2026-03-21 | 2026-03-30 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 24/0 | Completed
2026-03-27 | 2026-03-25 | 2026-03-31 | Rang Construction | 38.079 | DC+6 | 5.4399 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/0 | Completed
2026-03-28 | 2026-03-21 | 2026-03-30 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 24/0 | Completed
2026-03-28 | 2026-03-25 | 2026-03-31 | Rang Construction | 38.079 | DC+6 | 5.4399 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/0 | Completed
2026-03-29 | 2026-03-21 | 2026-03-30 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 24/0 | Completed
2026-03-29 | 2026-03-25 | 2026-03-31 | Rang Construction | 38.079 | DC+6 | 5.4399 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/0 | Completed
2026-03-30 | 2026-03-21 | 2026-03-30 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 24/0 | Completed
2026-03-30 | 2026-03-25 | 2026-03-31 | Rang Construction | 38.079 | DC+6 | 5.4399 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/0 | Completed
2026-03-31 | 2026-03-25 | 2026-03-31 | Rang Construction | 38.079 | DC+6 | 5.4399 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/0 | Completed
2026-04-03 | 2026-04-03 | 2026-04-09 | Pinki Devi | 37.87 | DD+0 | 5.41 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 25/0 | Completed
2026-04-03 | 2026-04-03 | 2026-04-09 | Rang Construction | 16.922 | DA+0 | 2.4174 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/1 | Completed
2026-04-04 | 2026-04-03 | 2026-04-09 | Pinki Devi | 37.87 | DD+0 | 5.41 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 25/0 | Completed
2026-04-04 | 2026-04-03 | 2026-04-09 | Rang Construction | 16.922 | DA+0 | 2.4174 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/1 | Completed
2026-04-05 | 2026-04-03 | 2026-04-09 | Pinki Devi | 37.87 | DD+0 | 5.41 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 25/0 | Completed
2026-04-05 | 2026-04-03 | 2026-04-09 | Rang Construction | 16.922 | DA+0 | 2.4174 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/1 | Completed
2026-04-06 | 2026-04-03 | 2026-04-09 | Pinki Devi | 37.87 | DD+0 | 5.41 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 25/0 | Completed
2026-04-06 | 2026-04-03 | 2026-04-09 | Rang Construction | 16.922 | DA+0 | 2.4174 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/1 | Completed
2026-04-07 | 2026-04-03 | 2026-04-09 | Pinki Devi | 37.87 | DD+0 | 5.41 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 25/0 | Completed
2026-04-07 | 2026-04-03 | 2026-04-09 | Rang Construction | 16.922 | DA+0 | 2.4174 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/1 | Completed
2026-04-07 | 2026-04-07 | 2026-04-13 | Rang Construction | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/2 | Completed
2026-04-08 | 2026-04-03 | 2026-04-09 | Pinki Devi | 37.87 | DD+0 | 5.41 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 25/0 | Completed
2026-04-08 | 2026-04-03 | 2026-04-09 | Rang Construction | 16.922 | DA+0 | 2.4174 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/1 | Completed
2026-04-08 | 2026-04-07 | 2026-04-13 | Rang Construction | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/2 | Completed
2026-04-09 | 2026-04-03 | 2026-04-09 | Pinki Devi | 37.87 | DD+0 | 5.41 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 25/0 | Completed
2026-04-09 | 2026-04-03 | 2026-04-09 | Rang Construction | 16.922 | DA+0 | 2.4174 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/1 | Completed
2026-04-09 | 2026-04-07 | 2026-04-13 | Rang Construction | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/2 | Completed
2026-04-09 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-10 | 2026-04-07 | 2026-04-13 | Rang Construction | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/2 | Completed
2026-04-10 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-11 | 2026-04-07 | 2026-04-13 | Rang Construction | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/2 | Completed
2026-04-11 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-12 | 2026-04-07 | 2026-04-13 | Rang Construction | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/2 | Completed
2026-04-12 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-13 | 2026-04-07 | 2026-04-13 | Rang Construction | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/2 | Completed
2026-04-13 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-13 | 2026-04-13 | 2026-04-18 | Rang Construction | 18.405 | DA+3 | 3.0675 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/1 | Completed
2026-04-14 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-14 | 2026-04-13 | 2026-04-18 | Rang Construction | 18.405 | DA+3 | 3.0675 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/1 | Completed
2026-04-15 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-15 | 2026-04-13 | 2026-04-18 | Rang Construction | 18.405 | DA+3 | 3.0675 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/1 | Completed
2026-04-16 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-16 | 2026-04-13 | 2026-04-18 | Rang Construction | 18.405 | DA+3 | 3.0675 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/1 | Completed
2026-04-17 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-17 | 2026-04-13 | 2026-04-18 | Rang Construction | 18.405 | DA+3 | 3.0675 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/1 | Completed
2026-04-18 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-18 | 2026-04-13 | 2026-04-18 | Rang Construction | 18.405 | DA+3 | 3.0675 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 18/1 | Completed
2026-04-19 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-20 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-21 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-22 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-23 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-23 | 2026-04-23 | 2026-04-26 | Rang Construction | 16.922 | DA+0 | 4.2305 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/4 | Completed
2026-04-23 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-04-24 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-24 | 2026-04-23 | 2026-04-26 | Rang Construction | 16.922 | DA+0 | 4.2305 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/4 | Completed
2026-04-24 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-04-25 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-25 | 2026-04-23 | 2026-04-26 | Rang Construction | 16.922 | DA+0 | 4.2305 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/4 | Completed
2026-04-25 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-04-26 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-26 | 2026-04-23 | 2026-04-26 | Rang Construction | 16.922 | DA+0 | 4.2305 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/4 | Completed
2026-04-26 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-04-27 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-27 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-04-28 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-28 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-04-29 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-29 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-04-30 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-04-30 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-01 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-05-01 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-02 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-05-02 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-03 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-05-03 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-04 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-05-04 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-05 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-05-05 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-06 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-05-06 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-07 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-05-07 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-08 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-05-08 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-09 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-05-09 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-10 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-05-10 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-11 | 2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/3 | Completed
2026-05-11 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-12 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-13 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-14 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-15 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-16 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-17 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-18 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-19 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-20 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-21 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-22 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-23 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-24 | 2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 19/2 | Completed
2026-05-31 | 2026-05-31 | 2026-05-31 | Pinki Devi | 20.631 | DA+6 | 20.631 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 26/2 | Completed
2026-03-10 | 2026-03-10 | 2026-03-20 | Rang Construction | 20.631 | DA+6 | 1.8755 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/1 | Completed
2026-03-11 | 2026-03-10 | 2026-03-20 | Rang Construction | 20.631 | DA+6 | 1.8755 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/1 | Completed
2026-03-12 | 2026-03-10 | 2026-03-20 | Rang Construction | 20.631 | DA+6 | 1.8755 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/1 | Completed
2026-03-13 | 2026-03-13 | 2026-03-22 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/0 | Completed
2026-03-13 | 2026-03-10 | 2026-03-20 | Rang Construction | 20.631 | DA+6 | 1.8755 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/1 | Completed
2026-03-14 | 2026-03-13 | 2026-03-22 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/0 | Completed
2026-03-14 | 2026-03-10 | 2026-03-20 | Rang Construction | 20.631 | DA+6 | 1.8755 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/1 | Completed
2026-03-15 | 2026-03-13 | 2026-03-22 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/0 | Completed
2026-03-15 | 2026-03-10 | 2026-03-20 | Rang Construction | 20.631 | DA+6 | 1.8755 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/1 | Completed
2026-03-15 | 2026-03-15 | 2026-03-24 | Rang Construction | 16.922 | DA+0 | 1.6922 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/2 | Completed
2026-03-16 | 2026-03-13 | 2026-03-22 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/0 | Completed
2026-03-16 | 2026-03-10 | 2026-03-20 | Rang Construction | 20.631 | DA+6 | 1.8755 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/1 | Completed
2026-03-16 | 2026-03-15 | 2026-03-24 | Rang Construction | 16.922 | DA+0 | 1.6922 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/2 | Completed
2026-03-17 | 2026-03-13 | 2026-03-22 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/0 | Completed
2026-03-17 | 2026-03-10 | 2026-03-20 | Rang Construction | 20.631 | DA+6 | 1.8755 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/1 | Completed
2026-03-17 | 2026-03-15 | 2026-03-24 | Rang Construction | 16.922 | DA+0 | 1.6922 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/2 | Completed
2026-03-18 | 2026-03-13 | 2026-03-22 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/0 | Completed
2026-03-18 | 2026-03-10 | 2026-03-20 | Rang Construction | 20.631 | DA+6 | 1.8755 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/1 | Completed
2026-03-18 | 2026-03-15 | 2026-03-24 | Rang Construction | 16.922 | DA+0 | 1.6922 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/2 | Completed
2026-03-19 | 2026-03-13 | 2026-03-22 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/0 | Completed
2026-03-19 | 2026-03-10 | 2026-03-20 | Rang Construction | 20.631 | DA+6 | 1.8755 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/1 | Completed
2026-03-19 | 2026-03-15 | 2026-03-24 | Rang Construction | 16.922 | DA+0 | 1.6922 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/2 | Completed
2026-03-20 | 2026-03-13 | 2026-03-22 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/0 | Completed
2026-03-20 | 2026-03-10 | 2026-03-20 | Rang Construction | 20.631 | DA+6 | 1.8755 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/1 | Completed
2026-03-20 | 2026-03-15 | 2026-03-24 | Rang Construction | 16.922 | DA+0 | 1.6922 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/2 | Completed
2026-03-21 | 2026-03-13 | 2026-03-22 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/0 | Completed
2026-03-21 | 2026-03-15 | 2026-03-24 | Rang Construction | 16.922 | DA+0 | 1.6922 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/2 | Completed
2026-03-22 | 2026-03-13 | 2026-03-22 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/0 | Completed
2026-03-22 | 2026-03-15 | 2026-03-24 | Rang Construction | 16.922 | DA+0 | 1.6922 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/2 | Completed
2026-03-23 | 2026-03-15 | 2026-03-24 | Rang Construction | 16.922 | DA+0 | 1.6922 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/2 | Completed
2026-03-24 | 2026-03-15 | 2026-03-24 | Rang Construction | 16.922 | DA+0 | 1.6922 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/2 | Completed
2026-03-31 | 2026-03-31 | 2026-04-03 | Pinki Devi | 21.756 | DA+9 | 5.439 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/1 | Completed
2026-03-31 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-01 | 2026-03-31 | 2026-04-03 | Pinki Devi | 21.756 | DA+9 | 5.439 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/1 | Completed
2026-04-01 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-02 | 2026-03-31 | 2026-04-03 | Pinki Devi | 21.756 | DA+9 | 5.439 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/1 | Completed
2026-04-02 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-03 | 2026-03-31 | 2026-04-03 | Pinki Devi | 21.756 | DA+9 | 5.439 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 34/1 | Completed
2026-04-03 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-03 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-03 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-04 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-04 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-04 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-05 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-05 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-05 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-06 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-06 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-06 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-07 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-07 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-07 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-07 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-08 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-08 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-08 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-08 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-09 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-09 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-09 | 2026-04-09 | 2026-04-16 | Pinki Devi | 40.17 | DD+3 | 5.0213 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 29/0 | Completed
2026-04-09 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-09 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-10 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-10 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-10 | 2026-04-09 | 2026-04-16 | Pinki Devi | 40.17 | DD+3 | 5.0213 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 29/0 | Completed
2026-04-10 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-10 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-11 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-11 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-11 | 2026-04-09 | 2026-04-16 | Pinki Devi | 40.17 | DD+3 | 5.0213 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 29/0 | Completed
2026-04-11 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-11 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-12 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-12 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-12 | 2026-04-09 | 2026-04-16 | Pinki Devi | 40.17 | DD+3 | 5.0213 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 29/0 | Completed
2026-04-12 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-12 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-13 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-13 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-13 | 2026-04-09 | 2026-04-16 | Pinki Devi | 40.17 | DD+3 | 5.0213 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 29/0 | Completed
2026-04-13 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-13 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-13 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-14 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-14 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-14 | 2026-04-09 | 2026-04-16 | Pinki Devi | 40.17 | DD+3 | 5.0213 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 29/0 | Completed
2026-04-14 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-14 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-14 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-15 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-15 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-15 | 2026-04-09 | 2026-04-16 | Pinki Devi | 40.17 | DD+3 | 5.0213 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 29/0 | Completed
2026-04-15 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-15 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-15 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-16 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-16 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-16 | 2026-04-09 | 2026-04-16 | Pinki Devi | 40.17 | DD+3 | 5.0213 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 29/0 | Completed
2026-04-16 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-16 | 2026-04-16 | 2026-04-22 | Pinki Devi | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/1 | Completed
2026-04-16 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-16 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-16 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-17 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-17 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-17 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-17 | 2026-04-16 | 2026-04-22 | Pinki Devi | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/1 | Completed
2026-04-17 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-17 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-17 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-18 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-18 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-18 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-18 | 2026-04-16 | 2026-04-22 | Pinki Devi | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/1 | Completed
2026-04-18 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-18 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-18 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-18 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-18 | 2026-04-18 | 2026-04-22 | Rang Construction | 16.922 | DA+0 | 3.3844 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/3 | Completed
2026-04-19 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-19 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-19 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-19 | 2026-04-16 | 2026-04-22 | Pinki Devi | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/1 | Completed
2026-04-19 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-19 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-19 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-19 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-19 | 2026-04-18 | 2026-04-22 | Rang Construction | 16.922 | DA+0 | 3.3844 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/3 | Completed
2026-04-20 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-20 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-20 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-20 | 2026-04-16 | 2026-04-22 | Pinki Devi | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/1 | Completed
2026-04-20 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-20 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-20 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-20 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-20 | 2026-04-18 | 2026-04-22 | Rang Construction | 16.922 | DA+0 | 3.3844 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/3 | Completed
2026-04-21 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-21 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-21 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-21 | 2026-04-16 | 2026-04-22 | Pinki Devi | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/1 | Completed
2026-04-21 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-21 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-21 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-21 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-21 | 2026-04-18 | 2026-04-22 | Rang Construction | 16.922 | DA+0 | 3.3844 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/3 | Completed
2026-04-22 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-22 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-22 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-22 | 2026-04-16 | 2026-04-22 | Pinki Devi | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/1 | Completed
2026-04-22 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-22 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-22 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-22 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-22 | 2026-04-18 | 2026-04-22 | Rang Construction | 16.922 | DA+0 | 3.3844 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 24/3 | Completed
2026-04-23 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-23 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-23 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-23 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-23 | 2026-04-23 | 2026-04-28 | Pinki Devi | 37.87 | DD+0 | 6.3117 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 30/0 | Completed
2026-04-23 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-23 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-23 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-24 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-24 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-24 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-24 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-24 | 2026-04-23 | 2026-04-28 | Pinki Devi | 37.87 | DD+0 | 6.3117 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 30/0 | Completed
2026-04-24 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-24 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-24 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-25 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-25 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-25 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-25 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-25 | 2026-04-23 | 2026-04-28 | Pinki Devi | 37.87 | DD+0 | 6.3117 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 30/0 | Completed
2026-04-25 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-25 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-25 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-26 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-26 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-26 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-26 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-26 | 2026-04-23 | 2026-04-28 | Pinki Devi | 37.87 | DD+0 | 6.3117 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 30/0 | Completed
2026-04-26 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-26 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-26 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-27 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-27 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-27 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-27 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-27 | 2026-04-23 | 2026-04-28 | Pinki Devi | 37.87 | DD+0 | 6.3117 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 30/0 | Completed
2026-04-27 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-27 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-27 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-28 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-28 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-28 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-28 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-28 | 2026-04-23 | 2026-04-28 | Pinki Devi | 37.87 | DD+0 | 6.3117 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 30/0 | Completed
2026-04-28 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-28 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-28 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-29 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-29 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-29 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-29 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-29 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-29 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-29 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-04-30 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-04-30 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-04-30 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-04-30 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-04-30 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-04-30 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-04-30 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-01 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-05-01 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-05-01 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-01 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-01 | 2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/1 | Completed
2026-05-01 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-05-01 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-02 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-05-02 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-05-02 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-02 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-02 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-05-02 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-03 | 2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 25/0 | Completed
2026-05-03 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-05-03 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-03 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-03 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-05-03 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-04 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-05-04 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-04 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-04 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-05-04 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-05 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-05-05 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-05 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-05 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-05-05 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-06 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-05-06 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-06 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-06 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-05-06 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-07 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-05-07 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-07 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-07 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-05-07 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-08 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-05-08 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-08 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-08 | 2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 26/0 | Completed
2026-05-08 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-09 | 2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 35/0 | Completed
2026-05-09 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-09 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-09 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-10 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-10 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-10 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-11 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-11 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-11 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-12 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-12 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-12 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-13 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-13 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-13 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-14 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-14 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-14 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-15 | 2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/0 | Completed
2026-05-15 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-15 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-16 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-16 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-17 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-17 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-18 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-18 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-19 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-19 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-20 | 2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 33/1 | Completed
2026-05-20 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-21 | 2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 28/0 | Completed
2026-05-31 | 2026-05-31 | 2026-05-31 | Pinki Devi | 37.87 | DD+0 | 37.87 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 36/0 | Completed
2026-03-16 | 2026-03-16 | 2026-03-18 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 96/1 | Completed
2026-03-17 | 2026-03-16 | 2026-03-18 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 96/1 | Completed
2026-03-18 | 2026-03-16 | 2026-03-18 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 96/1 | Completed
2026-03-18 | 2026-03-18 | 2026-03-20 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 96/2 | Completed
2026-03-19 | 2026-03-18 | 2026-03-20 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 96/2 | Completed
2026-03-20 | 2026-03-18 | 2026-03-20 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 96/2 | Completed
2026-03-20 | 2026-03-20 | 2026-03-25 | Sanjiv Kumar | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/0 | Completed
2026-03-21 | 2026-03-20 | 2026-03-25 | Sanjiv Kumar | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/0 | Completed
2026-03-22 | 2026-03-20 | 2026-03-25 | Sanjiv Kumar | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/0 | Completed
2026-03-23 | 2026-03-20 | 2026-03-25 | Sanjiv Kumar | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/0 | Completed
2026-03-24 | 2026-03-20 | 2026-03-25 | Sanjiv Kumar | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/0 | Completed
2026-03-25 | 2026-03-20 | 2026-03-25 | Sanjiv Kumar | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/0 | Completed
2026-03-25 | 2026-03-25 | 2026-03-27 | Sanjiv Kumar | 8.086 | DC+3 | 2.6953 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 98/0 | Completed
2026-03-26 | 2026-03-25 | 2026-03-27 | Sanjiv Kumar | 8.086 | DC+3 | 2.6953 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 98/0 | Completed
2026-03-27 | 2026-03-25 | 2026-03-27 | Sanjiv Kumar | 8.086 | DC+3 | 2.6953 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 98/0 | Completed
2026-03-27 | 2026-03-27 | 2026-03-29 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/3 | Completed
2026-03-28 | 2026-03-27 | 2026-03-29 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/3 | Completed
2026-03-29 | 2026-03-27 | 2026-03-29 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/3 | Completed
2026-03-29 | 2026-03-29 | 2026-03-30 | Sanjiv Kumar | 5.713 | DA+6 | 2.8565 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/2 | Completed
2026-03-30 | 2026-03-29 | 2026-03-30 | Sanjiv Kumar | 5.713 | DA+6 | 2.8565 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/2 | Completed
2026-03-30 | 2026-03-30 | 2026-03-31 | Sanjiv Kumar | 4.378 | DA+0 | 2.189 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/1 | Completed
2026-03-31 | 2026-03-30 | 2026-03-31 | Sanjiv Kumar | 4.378 | DA+0 | 2.189 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 99/1 | Completed
2026-03-31 | 2026-03-31 | 2026-04-02 | Sanjiv Kumar | 6.563 | DC+0 | 2.1877 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/0 | Completed
2026-04-01 | 2026-03-31 | 2026-04-02 | Sanjiv Kumar | 6.563 | DC+0 | 2.1877 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/0 | Completed
2026-04-02 | 2026-04-02 | 2026-04-12 | Druvika | 9.791 | DD+3 | 0.89009 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 65/0 | Completed
2026-04-02 | 2026-03-31 | 2026-04-02 | Sanjiv Kumar | 6.563 | DC+0 | 2.1877 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/0 | Completed
2026-04-02 | 2026-04-02 | 2026-04-04 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/1 | Completed
2026-04-02 | 2026-04-02 | 2026-04-07 | Zfapl | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 118/0 | Completed
2026-04-03 | 2026-04-02 | 2026-04-12 | Druvika | 9.791 | DD+3 | 0.89009 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 65/0 | Completed
2026-04-03 | 2026-04-02 | 2026-04-04 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/1 | Completed
2026-04-03 | 2026-04-02 | 2026-04-07 | Zfapl | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 118/0 | Completed
2026-04-04 | 2026-04-02 | 2026-04-12 | Druvika | 9.791 | DD+3 | 0.89009 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 65/0 | Completed
2026-04-04 | 2026-04-02 | 2026-04-04 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/1 | Completed
2026-04-04 | 2026-04-04 | 2026-04-06 | Sanjiv Kumar | 5.167 | DA+3 | 1.7223 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/4 | Completed
2026-04-04 | 2026-04-02 | 2026-04-07 | Zfapl | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 118/0 | Completed
2026-04-05 | 2026-04-02 | 2026-04-12 | Druvika | 9.791 | DD+3 | 0.89009 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 65/0 | Completed
2026-04-05 | 2026-04-04 | 2026-04-06 | Sanjiv Kumar | 5.167 | DA+3 | 1.7223 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/4 | Completed
2026-04-05 | 2026-04-02 | 2026-04-07 | Zfapl | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 118/0 | Completed
2026-04-06 | 2026-04-02 | 2026-04-12 | Druvika | 9.791 | DD+3 | 0.89009 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 65/0 | Completed
2026-04-06 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-06 | 2026-04-04 | 2026-04-06 | Sanjiv Kumar | 5.167 | DA+3 | 1.7223 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/4 | Completed
2026-04-06 | 2026-04-06 | 2026-04-08 | Sanjiv Kumar | 5.167 | DA+3 | 1.7223 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/3 | Completed
2026-04-06 | 2026-04-02 | 2026-04-07 | Zfapl | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 118/0 | Completed
2026-04-07 | 2026-04-02 | 2026-04-12 | Druvika | 9.791 | DD+3 | 0.89009 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 65/0 | Completed
2026-04-07 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-07 | 2026-04-06 | 2026-04-08 | Sanjiv Kumar | 5.167 | DA+3 | 1.7223 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/3 | Completed
2026-04-07 | 2026-04-02 | 2026-04-07 | Zfapl | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 118/0 | Completed
2026-04-07 | 2026-04-07 | 2026-04-15 | Zfapl | 6.325 | DA+9 | 0.70278 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/4 | Completed
2026-04-08 | 2026-04-02 | 2026-04-12 | Druvika | 9.791 | DD+3 | 0.89009 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 65/0 | Completed
2026-04-08 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-08 | 2026-04-06 | 2026-04-08 | Sanjiv Kumar | 5.167 | DA+3 | 1.7223 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/3 | Completed
2026-04-08 | 2026-04-08 | 2026-04-10 | Sanjiv Kumar | 5.167 | DA+3 | 1.7223 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/2 | Completed
2026-04-08 | 2026-04-07 | 2026-04-15 | Zfapl | 6.325 | DA+9 | 0.70278 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/4 | Completed
2026-04-09 | 2026-04-02 | 2026-04-12 | Druvika | 9.791 | DD+3 | 0.89009 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 65/0 | Completed
2026-04-09 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-09 | 2026-04-08 | 2026-04-10 | Sanjiv Kumar | 5.167 | DA+3 | 1.7223 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/2 | Completed
2026-04-09 | 2026-04-07 | 2026-04-15 | Zfapl | 6.325 | DA+9 | 0.70278 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/4 | Completed
2026-04-10 | 2026-04-02 | 2026-04-12 | Druvika | 9.791 | DD+3 | 0.89009 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 65/0 | Completed
2026-04-10 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-10 | 2026-04-08 | 2026-04-10 | Sanjiv Kumar | 5.167 | DA+3 | 1.7223 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 100/2 | Completed
2026-04-10 | 2026-04-10 | 2026-04-12 | Sanjiv Kumar | 6.563 | DC+0 | 2.1877 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/0 | Completed
2026-04-10 | 2026-04-07 | 2026-04-15 | Zfapl | 6.325 | DA+9 | 0.70278 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/4 | Completed
2026-04-11 | 2026-04-02 | 2026-04-12 | Druvika | 9.791 | DD+3 | 0.89009 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 65/0 | Completed
2026-04-11 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-11 | 2026-04-10 | 2026-04-12 | Sanjiv Kumar | 6.563 | DC+0 | 2.1877 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/0 | Completed
2026-04-11 | 2026-04-07 | 2026-04-15 | Zfapl | 6.325 | DA+9 | 0.70278 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/4 | Completed
2026-04-12 | 2026-04-02 | 2026-04-12 | Druvika | 9.791 | DD+3 | 0.89009 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 65/0 | Completed
2026-04-12 | 2026-04-12 | 2026-04-20 | Druvika | 9.791 | DD+3 | 1.0879 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 66/0 | Completed
2026-04-12 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-12 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-12 | 2026-04-10 | 2026-04-12 | Sanjiv Kumar | 6.563 | DC+0 | 2.1877 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/0 | Completed
2026-04-12 | 2026-04-12 | 2026-04-14 | Sanjiv Kumar | 4.378 | DA+0 | 1.4593 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/1 | Completed
2026-04-12 | 2026-04-07 | 2026-04-15 | Zfapl | 6.325 | DA+9 | 0.70278 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/4 | Completed
2026-04-13 | 2026-04-12 | 2026-04-20 | Druvika | 9.791 | DD+3 | 1.0879 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 66/0 | Completed
2026-04-13 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-13 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-13 | 2026-04-12 | 2026-04-14 | Sanjiv Kumar | 4.378 | DA+0 | 1.4593 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/1 | Completed
2026-04-13 | 2026-04-07 | 2026-04-15 | Zfapl | 6.325 | DA+9 | 0.70278 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/4 | Completed
2026-04-14 | 2026-04-12 | 2026-04-20 | Druvika | 9.791 | DD+3 | 1.0879 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 66/0 | Completed
2026-04-14 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-14 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-14 | 2026-04-12 | 2026-04-14 | Sanjiv Kumar | 4.378 | DA+0 | 1.4593 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/1 | Completed
2026-04-14 | 2026-04-14 | 2026-04-15 | Sanjiv Kumar | 5.167 | DA+3 | 2.5835 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 97/2 | Completed
2026-04-14 | 2026-04-07 | 2026-04-15 | Zfapl | 6.325 | DA+9 | 0.70278 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/4 | Completed
2026-04-15 | 2026-04-12 | 2026-04-20 | Druvika | 9.791 | DD+3 | 1.0879 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 66/0 | Completed
2026-04-15 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-15 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-15 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-15 | 2026-04-14 | 2026-04-15 | Sanjiv Kumar | 5.167 | DA+3 | 2.5835 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 97/2 | Completed
2026-04-15 | 2026-04-15 | 2026-04-19 | Sanjiv Kumar | 8.086 | DD+0 | 1.6172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 107/0 | Completed
2026-04-15 | 2026-04-07 | 2026-04-15 | Zfapl | 6.325 | DA+9 | 0.70278 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/4 | Completed
2026-04-16 | 2026-04-12 | 2026-04-20 | Druvika | 9.791 | DD+3 | 1.0879 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 66/0 | Completed
2026-04-16 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-16 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-16 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-16 | 2026-04-15 | 2026-04-19 | Sanjiv Kumar | 8.086 | DD+0 | 1.6172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 107/0 | Completed
2026-04-17 | 2026-04-12 | 2026-04-20 | Druvika | 9.791 | DD+3 | 1.0879 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 66/0 | Completed
2026-04-17 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-17 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-17 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-17 | 2026-04-15 | 2026-04-19 | Sanjiv Kumar | 8.086 | DD+0 | 1.6172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 107/0 | Completed
2026-04-18 | 2026-04-12 | 2026-04-20 | Druvika | 9.791 | DD+3 | 1.0879 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 66/0 | Completed
2026-04-18 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-18 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-18 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-18 | 2026-04-15 | 2026-04-19 | Sanjiv Kumar | 8.086 | DD+0 | 1.6172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 107/0 | Completed
2026-04-18 | 2026-04-18 | 2026-04-21 | Sanjiv Kumar | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 108/0 | Completed
2026-04-19 | 2026-04-12 | 2026-04-20 | Druvika | 9.791 | DD+3 | 1.0879 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 66/0 | Completed
2026-04-19 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-19 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-19 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-19 | 2026-04-15 | 2026-04-19 | Sanjiv Kumar | 8.086 | DD+0 | 1.6172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 107/0 | Completed
2026-04-19 | 2026-04-18 | 2026-04-21 | Sanjiv Kumar | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 108/0 | Completed
2026-04-20 | 2026-04-12 | 2026-04-20 | Druvika | 9.791 | DD+3 | 1.0879 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 66/0 | Completed
2026-04-20 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-20 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-20 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-20 | 2026-04-18 | 2026-04-21 | Sanjiv Kumar | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 108/0 | Completed
2026-04-21 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-21 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-21 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-21 | 2026-04-21 | 2026-04-22 | Sanjeev Kumar | 5.167 | DA+3 | 2.5835 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 107/1 | Completed
2026-04-21 | 2026-04-18 | 2026-04-21 | Sanjiv Kumar | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 108/0 | Completed
2026-04-22 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-22 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-22 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-22 | 2026-04-21 | 2026-04-22 | Sanjeev Kumar | 5.167 | DA+3 | 2.5835 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 107/1 | Completed
2026-04-23 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-23 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-23 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-23 | 2026-04-23 | 2026-04-25 | Sanjeev Kumar | 9.791 | DD+3 | 3.2637 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/0 | Completed
2026-04-23 | 2026-04-23 | 2026-04-28 | Sanjeev Kumar | 5.713 | DA+6 | 0.95217 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 115/1 | Completed
2026-04-24 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-24 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-24 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-24 | 2026-04-23 | 2026-04-25 | Sanjeev Kumar | 9.791 | DD+3 | 3.2637 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/0 | Completed
2026-04-24 | 2026-04-23 | 2026-04-28 | Sanjeev Kumar | 5.713 | DA+6 | 0.95217 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 115/1 | Completed
2026-04-25 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-25 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-25 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-25 | 2026-04-23 | 2026-04-25 | Sanjeev Kumar | 9.791 | DD+3 | 3.2637 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/0 | Completed
2026-04-25 | 2026-04-23 | 2026-04-28 | Sanjeev Kumar | 5.713 | DA+6 | 0.95217 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 115/1 | Completed
2026-04-26 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-26 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-26 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-26 | 2026-04-23 | 2026-04-28 | Sanjeev Kumar | 5.713 | DA+6 | 0.95217 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 115/1 | Completed
2026-04-27 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-27 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-27 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-27 | 2026-04-23 | 2026-04-28 | Sanjeev Kumar | 5.713 | DA+6 | 0.95217 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 115/1 | Completed
2026-04-28 | 2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 56/0 | Completed
2026-04-28 | 2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/0 | Completed
2026-04-28 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-28 | 2026-04-23 | 2026-04-28 | Sanjeev Kumar | 5.713 | DA+6 | 0.95217 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 115/1 | Completed
2026-04-29 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/1 | Completed
2026-04-29 | 2026-04-29 | 2026-05-02 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 114/1 | Completed
2026-04-30 | 2026-04-30 | 2026-05-03 | Dhuvika | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 55/1 | Completed
2026-04-30 | 2026-04-29 | 2026-05-02 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 114/1 | Completed
2026-04-30 | 2026-04-30 | 2026-04-30 | Sanjeev Kumar | 9.791 | DD+3 | 9.791 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 115/0 | Completed
2026-05-01 | 2026-04-30 | 2026-05-03 | Dhuvika | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 55/1 | Completed
2026-05-01 | 2026-04-29 | 2026-05-02 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 114/1 | Completed
2026-05-02 | 2026-04-30 | 2026-05-03 | Dhuvika | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 55/1 | Completed
2026-05-02 | 2026-04-29 | 2026-05-02 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 114/1 | Completed
2026-05-03 | 2026-04-30 | 2026-05-03 | Dhuvika | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 55/1 | Completed
2026-05-03 | 2026-05-03 | 2026-05-06 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/2 | Completed
2026-05-04 | 2026-05-04 | 2026-05-07 | Dhuvika | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 55/0 | Completed
2026-05-04 | 2026-05-03 | 2026-05-06 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/2 | Completed
2026-05-05 | 2026-05-04 | 2026-05-07 | Dhuvika | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 55/0 | Completed
2026-05-05 | 2026-05-03 | 2026-05-06 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/2 | Completed
2026-05-06 | 2026-05-04 | 2026-05-07 | Dhuvika | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 55/0 | Completed
2026-05-06 | 2026-05-03 | 2026-05-06 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 116/2 | Completed
2026-05-07 | 2026-05-04 | 2026-05-07 | Dhuvika | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 55/0 | Completed
2026-05-07 | 2026-05-07 | 2026-05-10 | Sanjeev Kumar | 5.97 | DB+0 | 1.4925 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 89/0 | Completed
2026-05-08 | 2026-05-07 | 2026-05-10 | Sanjeev Kumar | 5.97 | DB+0 | 1.4925 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 89/0 | Completed
2026-05-09 | 2026-05-07 | 2026-05-10 | Sanjeev Kumar | 5.97 | DB+0 | 1.4925 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 89/0 | Completed
2026-05-09 | 2026-05-09 | 2026-05-12 | Sanjeev Kumar | 8.086 | DC+3 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 88/0 | Completed
2026-05-10 | 2026-05-10 | 2026-05-13 | Dhuvika | 4.378 | DA+0 | 1.0945 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/3 | Completed
2026-05-10 | 2026-05-07 | 2026-05-10 | Sanjeev Kumar | 5.97 | DB+0 | 1.4925 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 89/0 | Completed
2026-05-10 | 2026-05-09 | 2026-05-12 | Sanjeev Kumar | 8.086 | DC+3 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 88/0 | Completed
2026-05-10 | 2026-05-10 | 2026-05-13 | Sanjeev Kumar | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 88/1 | Completed
2026-05-11 | 2026-05-10 | 2026-05-13 | Dhuvika | 4.378 | DA+0 | 1.0945 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/3 | Completed
2026-05-11 | 2026-05-09 | 2026-05-12 | Sanjeev Kumar | 8.086 | DC+3 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 88/0 | Completed
2026-05-11 | 2026-05-10 | 2026-05-13 | Sanjeev Kumar | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 88/1 | Completed
2026-05-12 | 2026-05-10 | 2026-05-13 | Dhuvika | 4.378 | DA+0 | 1.0945 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/3 | Completed
2026-05-12 | 2026-05-09 | 2026-05-12 | Sanjeev Kumar | 8.086 | DC+3 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 88/0 | Completed
2026-05-12 | 2026-05-10 | 2026-05-13 | Sanjeev Kumar | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 88/1 | Completed
2026-05-12 | 2026-05-12 | 2026-05-15 | Sanjeev Kumar | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 87/2 | Completed
2026-05-13 | 2026-05-10 | 2026-05-13 | Dhuvika | 4.378 | DA+0 | 1.0945 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/3 | Completed
2026-05-13 | 2026-05-10 | 2026-05-13 | Sanjeev Kumar | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 88/1 | Completed
2026-05-13 | 2026-05-12 | 2026-05-15 | Sanjeev Kumar | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 87/2 | Completed
2026-05-13 | 2026-05-13 | 2026-05-16 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 87/1 | Completed
2026-05-14 | 2026-05-14 | 2026-05-17 | Exel Power | 11.469 | DD+9 | 2.8672 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 82/0 | Completed
2026-05-14 | 2026-05-12 | 2026-05-15 | Sanjeev Kumar | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 87/2 | Completed
2026-05-14 | 2026-05-13 | 2026-05-16 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 87/1 | Completed
2026-05-15 | 2026-05-14 | 2026-05-17 | Exel Power | 11.469 | DD+9 | 2.8672 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 82/0 | Completed
2026-05-15 | 2026-05-12 | 2026-05-15 | Sanjeev Kumar | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 87/2 | Completed
2026-05-15 | 2026-05-13 | 2026-05-16 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 87/1 | Completed
2026-05-15 | 2026-05-15 | 2026-05-18 | Sanjeev Kumar | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 87/0 | Completed
2026-05-16 | 2026-05-14 | 2026-05-17 | Exel Power | 11.469 | DD+9 | 2.8672 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 82/0 | Completed
2026-05-16 | 2026-05-13 | 2026-05-16 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 87/1 | Completed
2026-05-16 | 2026-05-15 | 2026-05-18 | Sanjeev Kumar | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 87/0 | Completed
2026-05-17 | 2026-05-14 | 2026-05-17 | Exel Power | 11.469 | DD+9 | 2.8672 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 82/0 | Completed
2026-05-17 | 2026-05-15 | 2026-05-18 | Sanjeev Kumar | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 87/0 | Completed
2026-05-17 | 2026-05-17 | 2026-05-20 | Sanjeev Kumar | 4.378 | DA+0 | 1.0945 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/1 | Completed
2026-05-18 | 2026-05-18 | 2026-05-21 | Exel Power | 8.086 | DD+0 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 84/0 | Completed
2026-05-18 | 2026-05-15 | 2026-05-18 | Sanjeev Kumar | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 87/0 | Completed
2026-05-18 | 2026-05-17 | 2026-05-20 | Sanjeev Kumar | 4.378 | DA+0 | 1.0945 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/1 | Completed
2026-05-19 | 2026-05-18 | 2026-05-21 | Exel Power | 8.086 | DD+0 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 84/0 | Completed
2026-05-19 | 2026-05-17 | 2026-05-20 | Sanjeev Kumar | 4.378 | DA+0 | 1.0945 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/1 | Completed
2026-05-20 | 2026-05-18 | 2026-05-21 | Exel Power | 8.086 | DD+0 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 84/0 | Completed
2026-05-20 | 2026-05-17 | 2026-05-20 | Sanjeev Kumar | 4.378 | DA+0 | 1.0945 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 83/1 | Completed
2026-05-20 | 2026-05-20 | 2026-05-23 | Sanjeev Kumar | 11.469 | DD+9 | 2.8672 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 85/0 | Completed
2026-05-21 | 2026-05-18 | 2026-05-21 | Exel Power | 8.086 | DD+0 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 84/0 | Completed
2026-05-21 | 2026-05-20 | 2026-05-23 | Sanjeev Kumar | 11.469 | DD+9 | 2.8672 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 85/0 | Completed
2026-05-22 | 2026-05-22 | 2026-05-25 | Dhuvika | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/2 | Completed
2026-05-22 | 2026-05-20 | 2026-05-23 | Sanjeev Kumar | 11.469 | DD+9 | 2.8672 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 85/0 | Completed
2026-05-23 | 2026-05-22 | 2026-05-25 | Dhuvika | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/2 | Completed
2026-05-23 | 2026-05-23 | 2026-05-26 | Exel Power | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 85/1 | Completed
2026-05-23 | 2026-05-20 | 2026-05-23 | Sanjeev Kumar | 11.469 | DD+9 | 2.8672 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 85/0 | Completed
2026-05-23 | 2026-05-23 | 2026-05-26 | Sanjeev Kumar | 8.086 | DD+0 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 86/0 | Completed
2026-05-24 | 2026-05-22 | 2026-05-25 | Dhuvika | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/2 | Completed
2026-05-24 | 2026-05-23 | 2026-05-26 | Exel Power | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 85/1 | Completed
2026-05-24 | 2026-05-23 | 2026-05-26 | Sanjeev Kumar | 8.086 | DD+0 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 86/0 | Completed
2026-05-25 | 2026-05-22 | 2026-05-25 | Dhuvika | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/2 | Completed
2026-05-25 | 2026-05-23 | 2026-05-26 | Exel Power | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 85/1 | Completed
2026-05-25 | 2026-05-23 | 2026-05-26 | Sanjeev Kumar | 8.086 | DD+0 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 86/0 | Completed
2026-05-26 | 2026-05-23 | 2026-05-26 | Exel Power | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 85/1 | Completed
2026-05-26 | 2026-05-23 | 2026-05-26 | Sanjeev Kumar | 8.086 | DD+0 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 86/0 | Completed
2026-05-28 | 2026-05-28 | 2026-05-31 | Dhuvika | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/1 | Completed
2026-05-28 | 2026-05-28 | 2026-05-31 | Exel Power | 6.325 | DA+9 | 1.5813 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 118/3 | Completed
2026-05-29 | 2026-05-28 | 2026-05-31 | Dhuvika | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/1 | Completed
2026-05-29 | 2026-05-28 | 2026-05-31 | Exel Power | 6.325 | DA+9 | 1.5813 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 118/3 | Completed
2026-05-30 | 2026-05-28 | 2026-05-31 | Dhuvika | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/1 | Completed
2026-05-30 | 2026-05-28 | 2026-05-31 | Exel Power | 6.325 | DA+9 | 1.5813 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 118/3 | Completed
2026-05-31 | 2026-05-28 | 2026-05-31 | Dhuvika | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/1 | Completed
2026-05-31 | 2026-05-28 | 2026-05-31 | Exel Power | 6.325 | DA+9 | 1.5813 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 118/3 | Completed
2026-05-31 | 2026-05-31 | 2026-06-05 | Dhruvika | 6.8389 | DD+3 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/0 | COMPLETED
2026-05-31 | 2026-05-31 | 2026-06-05 | Sanjeev | 6.8389 | DD+0 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/0 | COMPLETED
2026-06-01 | 2026-05-31 | 2026-06-05 | Dhruvika | 6.8389 | DD+3 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/0 | COMPLETED
2026-06-01 | 2026-05-31 | 2026-06-05 | Sanjeev | 6.8389 | DD+0 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/0 | COMPLETED
2026-06-02 | 2026-05-31 | 2026-06-05 | Dhruvika | 6.8389 | DD+3 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/0 | COMPLETED
2026-06-02 | 2026-05-31 | 2026-06-05 | Sanjeev | 6.8389 | DD+0 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/0 | COMPLETED
2026-06-03 | 2026-05-31 | 2026-06-05 | Dhruvika | 6.8389 | DD+3 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/0 | COMPLETED
2026-06-03 | 2026-05-31 | 2026-06-05 | Sanjeev | 6.8389 | DD+0 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/0 | COMPLETED
2026-06-04 | 2026-05-31 | 2026-06-05 | Dhruvika | 6.8389 | DD+3 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/0 | COMPLETED
2026-06-04 | 2026-06-04 | 2026-06-11 | Dhruvika | 6.8389 | DC+0 | 0.85486 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 58/0 | COMPLETED
2026-06-04 | 2026-06-04 | 2026-06-07 | Exel Power | 6.8389 | DD+3 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 119/0 | COMPLETED
2026-06-04 | 2026-06-04 | 2026-06-14 | Exel Power | 6.8389 | DD+0 | 0.62172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/0 | COMPLETED
2026-06-04 | 2026-05-31 | 2026-06-05 | Sanjeev | 6.8389 | DD+0 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/0 | COMPLETED
2026-06-04 | 2026-06-04 | 2026-06-07 | Sanjeev | 6.8389 | DA+3 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/1 | COMPLETED
2026-06-04 | 2026-06-04 | 2026-06-10 | Sanjeev | 6.8389 | DA+3 | 0.97699 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/2 | COMPLETED
2026-06-05 | 2026-05-31 | 2026-06-05 | Dhruvika | 6.8389 | DD+3 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 54/0 | COMPLETED
2026-06-05 | 2026-06-04 | 2026-06-11 | Dhruvika | 6.8389 | DC+0 | 0.85486 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 58/0 | COMPLETED
2026-06-05 | 2026-06-04 | 2026-06-07 | Exel Power | 6.8389 | DD+3 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 119/0 | COMPLETED
2026-06-05 | 2026-06-04 | 2026-06-14 | Exel Power | 6.8389 | DD+0 | 0.62172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/0 | COMPLETED
2026-06-05 | 2026-05-31 | 2026-06-05 | Sanjeev | 6.8389 | DD+0 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/0 | COMPLETED
2026-06-05 | 2026-06-04 | 2026-06-07 | Sanjeev | 6.8389 | DA+3 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/1 | COMPLETED
2026-06-05 | 2026-06-04 | 2026-06-10 | Sanjeev | 6.8389 | DA+3 | 0.97699 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/2 | COMPLETED
2026-06-06 | 2026-06-04 | 2026-06-11 | Dhruvika | 6.8389 | DC+0 | 0.85486 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 58/0 | COMPLETED
2026-06-06 | 2026-06-04 | 2026-06-07 | Exel Power | 6.8389 | DD+3 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 119/0 | COMPLETED
2026-06-06 | 2026-06-04 | 2026-06-14 | Exel Power | 6.8389 | DD+0 | 0.62172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/0 | COMPLETED
2026-06-06 | 2026-06-04 | 2026-06-07 | Sanjeev | 6.8389 | DA+3 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/1 | COMPLETED
2026-06-06 | 2026-06-04 | 2026-06-10 | Sanjeev | 6.8389 | DA+3 | 0.97699 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/2 | COMPLETED
2026-06-07 | 2026-06-04 | 2026-06-11 | Dhruvika | 6.8389 | DC+0 | 0.85486 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 58/0 | COMPLETED
2026-06-07 | 2026-06-04 | 2026-06-07 | Exel Power | 6.8389 | DD+3 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 119/0 | COMPLETED
2026-06-07 | 2026-06-04 | 2026-06-14 | Exel Power | 6.8389 | DD+0 | 0.62172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/0 | COMPLETED
2026-06-07 | 2026-06-07 | 2026-06-10 | Reyansh | 6.8389 | DA+0 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/2 | COMPLETED
2026-06-07 | 2026-06-04 | 2026-06-07 | Sanjeev | 6.8389 | DA+3 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/1 | COMPLETED
2026-06-07 | 2026-06-04 | 2026-06-10 | Sanjeev | 6.8389 | DA+3 | 0.97699 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/2 | COMPLETED
2026-06-08 | 2026-06-04 | 2026-06-11 | Dhruvika | 6.8389 | DC+0 | 0.85486 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 58/0 | COMPLETED
2026-06-08 | 2026-06-04 | 2026-06-14 | Exel Power | 6.8389 | DD+0 | 0.62172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/0 | COMPLETED
2026-06-08 | 2026-06-07 | 2026-06-10 | Reyansh | 6.8389 | DA+0 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/2 | COMPLETED
2026-06-08 | 2026-06-04 | 2026-06-10 | Sanjeev | 6.8389 | DA+3 | 0.97699 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/2 | COMPLETED
2026-06-09 | 2026-06-04 | 2026-06-11 | Dhruvika | 6.8389 | DC+0 | 0.85486 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 58/0 | COMPLETED
2026-06-09 | 2026-06-04 | 2026-06-14 | Exel Power | 6.8389 | DD+0 | 0.62172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/0 | COMPLETED
2026-06-09 | 2026-06-07 | 2026-06-10 | Reyansh | 6.8389 | DA+0 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/2 | COMPLETED
2026-06-09 | 2026-06-04 | 2026-06-10 | Sanjeev | 6.8389 | DA+3 | 0.97699 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/2 | COMPLETED
2026-06-10 | 2026-06-04 | 2026-06-11 | Dhruvika | 6.8389 | DC+0 | 0.85486 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 58/0 | COMPLETED
2026-06-10 | 2026-06-04 | 2026-06-14 | Exel Power | 6.8389 | DD+0 | 0.62172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/0 | COMPLETED
2026-06-10 | 2026-06-07 | 2026-06-10 | Reyansh | 6.8389 | DA+0 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/2 | COMPLETED
2026-06-10 | 2026-06-04 | 2026-06-10 | Sanjeev | 6.8389 | DA+3 | 0.97699 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/2 | COMPLETED
2026-06-11 | 2026-06-04 | 2026-06-11 | Dhruvika | 6.8389 | DC+0 | 0.85486 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 58/0 | COMPLETED
2026-06-11 | 2026-06-11 | 2026-06-13 | Dhruvika | 6.8389 | DA+3 | 2.2796 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 58/1 | COMPLETED
2026-06-11 | 2026-06-04 | 2026-06-14 | Exel Power | 6.8389 | DD+0 | 0.62172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/0 | COMPLETED
2026-06-11 | 2026-06-11 | 2026-06-13 | Reyansh | 6.8389 | DA+0 | 2.2796 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/3 | COMPLETED
2026-06-11 | 2026-06-11 | 2026-06-13 | Sanjeev | 6.8389 | DA+6 | 2.2796 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/3 | COMPLETED
2026-06-12 | 2026-06-11 | 2026-06-13 | Dhruvika | 6.8389 | DA+3 | 2.2796 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 58/1 | COMPLETED
2026-06-12 | 2026-06-04 | 2026-06-14 | Exel Power | 6.8389 | DD+0 | 0.62172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/0 | COMPLETED
2026-06-12 | 2026-06-11 | 2026-06-13 | Reyansh | 6.8389 | DA+0 | 2.2796 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/3 | COMPLETED
2026-06-12 | 2026-06-11 | 2026-06-13 | Sanjeev | 6.8389 | DA+6 | 2.2796 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/3 | COMPLETED
2026-06-13 | 2026-06-11 | 2026-06-13 | Dhruvika | 6.8389 | DA+3 | 2.2796 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 58/1 | COMPLETED
2026-06-13 | 2026-06-04 | 2026-06-14 | Exel Power | 6.8389 | DD+0 | 0.62172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/0 | COMPLETED
2026-06-13 | 2026-06-11 | 2026-06-13 | Reyansh | 6.8389 | DA+0 | 2.2796 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/3 | COMPLETED
2026-06-13 | 2026-06-13 | 2026-06-14 | Reyansh | 6.8389 | DA+3 | 3.4195 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/4 | COMPLETED
2026-06-13 | 2026-06-11 | 2026-06-13 | Sanjeev | 6.8389 | DA+6 | 2.2796 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 59/3 | COMPLETED
2026-06-14 | 2026-06-04 | 2026-06-14 | Exel Power | 6.8389 | DD+0 | 0.62172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 117/0 | COMPLETED
2026-06-14 | 2026-06-13 | 2026-06-14 | Reyansh | 6.8389 | DA+3 | 3.4195 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | 101/4 | COMPLETED
2026-06-04 | 2026-06-04 | 2026-06-13 | Sgse India Pvt Ltd | 8.6189 | DC+0 | 0.86189 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/0 | COMPLETED
2026-06-05 | 2026-06-04 | 2026-06-13 | Sgse India Pvt Ltd | 8.6189 | DC+0 | 0.86189 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/0 | COMPLETED
2026-06-06 | 2026-06-04 | 2026-06-13 | Sgse India Pvt Ltd | 8.6189 | DC+0 | 0.86189 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/0 | COMPLETED
2026-06-07 | 2026-06-04 | 2026-06-13 | Sgse India Pvt Ltd | 8.6189 | DC+0 | 0.86189 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/0 | COMPLETED
2026-06-08 | 2026-06-04 | 2026-06-13 | Sgse India Pvt Ltd | 8.6189 | DC+0 | 0.86189 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/0 | COMPLETED
2026-06-09 | 2026-06-04 | 2026-06-13 | Sgse India Pvt Ltd | 8.6189 | DC+0 | 0.86189 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/0 | COMPLETED
2026-06-10 | 2026-06-04 | 2026-06-13 | Sgse India Pvt Ltd | 8.6189 | DC+0 | 0.86189 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/0 | COMPLETED
2026-06-11 | 2026-06-04 | 2026-06-13 | Sgse India Pvt Ltd | 8.6189 | DC+0 | 0.86189 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/0 | COMPLETED
2026-06-12 | 2026-06-04 | 2026-06-13 | Sgse India Pvt Ltd | 8.6189 | DC+0 | 0.86189 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/0 | COMPLETED
2026-06-13 | 2026-06-04 | 2026-06-13 | Sgse India Pvt Ltd | 8.6189 | DC+0 | 0.86189 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | 8/0 | COMPLETED
2026-05-31 | 2026-05-31 | 2026-06-04 | Pinki | 25.8087 | DB+3 | 5.1617 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 27/0 | COMPLETED
2026-05-31 | 2026-05-31 | 2026-06-05 | Rang | 25.8087 | DA+6 | 4.3014 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 20/1 | COMPLETED
2026-06-01 | 2026-05-31 | 2026-06-04 | Pinki | 25.8087 | DB+3 | 5.1617 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 27/0 | COMPLETED
2026-06-01 | 2026-05-31 | 2026-06-05 | Rang | 25.8087 | DA+6 | 4.3014 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 20/1 | COMPLETED
2026-06-02 | 2026-05-31 | 2026-06-04 | Pinki | 25.8087 | DB+3 | 5.1617 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 27/0 | COMPLETED
2026-06-02 | 2026-05-31 | 2026-06-05 | Rang | 25.8087 | DA+6 | 4.3014 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 20/1 | COMPLETED
2026-06-03 | 2026-05-31 | 2026-06-04 | Pinki | 25.8087 | DB+3 | 5.1617 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 27/0 | COMPLETED
2026-06-03 | 2026-05-31 | 2026-06-05 | Rang | 25.8087 | DA+6 | 4.3014 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 20/1 | COMPLETED
2026-06-04 | 2026-05-31 | 2026-06-04 | Pinki | 25.8087 | DB+3 | 5.1617 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 27/0 | COMPLETED
2026-06-04 | 2026-05-31 | 2026-06-05 | Rang | 25.8087 | DA+6 | 4.3014 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 20/1 | COMPLETED
2026-06-05 | 2026-05-31 | 2026-06-05 | Rang | 25.8087 | DA+6 | 4.3014 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 20/1 | COMPLETED
2026-06-06 | 2026-06-06 | 2026-06-10 | Rang | 25.8087 | DA+0 | 5.1617 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 11/3 | COMPLETED
2026-06-07 | 2026-06-06 | 2026-06-10 | Rang | 25.8087 | DA+0 | 5.1617 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 11/3 | COMPLETED
2026-06-08 | 2026-06-06 | 2026-06-10 | Rang | 25.8087 | DA+0 | 5.1617 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 11/3 | COMPLETED
2026-06-09 | 2026-06-06 | 2026-06-10 | Rang | 25.8087 | DA+0 | 5.1617 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 11/3 | COMPLETED
2026-06-10 | 2026-06-06 | 2026-06-10 | Rang | 25.8087 | DA+0 | 5.1617 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | 11/3 | COMPLETED
2026-05-20 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-05-21 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-05-22 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-05-23 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-05-24 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-05-25 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-05-26 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-05-27 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-05-28 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-05-28 | 2026-05-28 | 2026-06-01 | Rang | 29.486 | DD+0 | 5.8972 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 20/0 | COMPLETED
2026-05-29 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-05-29 | 2026-05-28 | 2026-06-01 | Rang | 29.486 | DD+0 | 5.8972 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 20/0 | COMPLETED
2026-05-30 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-05-30 | 2026-05-28 | 2026-06-01 | Rang | 29.486 | DD+0 | 5.8972 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 20/0 | COMPLETED
2026-05-31 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-05-31 | 2026-05-28 | 2026-06-01 | Rang | 29.486 | DD+0 | 5.8972 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 20/0 | COMPLETED
2026-06-01 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-06-01 | 2026-05-28 | 2026-06-01 | Rang | 29.486 | DD+0 | 5.8972 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 20/0 | COMPLETED
2026-06-02 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-06-03 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-06-04 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-06-05 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-06-06 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-06-07 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-06-08 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-06-09 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED
2026-06-10 | 2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | 43/0 | COMPLETED

## RawData
Start Date | Complete Date | Gang name | Tower Weight | Tower Type | Productivity | Project Code | Line Name | Project Name | Project Display | Project Scope Key | Source File | Source Sheet | Location No. | Tower Tightening Raw | Tower Tightening | Status
2026-01-27 | 2026-01-31 | S R Enterprises | 8.334 | DA+3 | 1.6668 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | TB 412 - DPR - 2026-06-14.xlsx | Erection | 10/1 |  |  | Completed
2026-02-03 | 2026-02-06 | S R Enterprises | 8.334 | DA+3 | 2.0835 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | TB 412 - DPR - 2026-06-14.xlsx | Erection | 10/2 |  |  | Completed
2026-02-07 | 2026-02-14 | S R Enterprises | 13.664 | DD+0 | 1.708 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | TB 412 - DPR - 2026-06-14.xlsx | Erection | 10/0 |  |  | Completed
2026-02-14 | 2026-02-16 | S R Enterprises | 8.334 | DA+3 | 2.778 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | TB 412 - DPR - 2026-06-14.xlsx | Erection | 11/1 |  |  | Completed
2026-02-16 | 2026-02-18 | S R Enterprises | 6.808 | DA+0 | 2.2693 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | TB 412 - DPR - 2026-06-14.xlsx | Erection | 11/3 |  |  | Completed
2026-02-18 | 2026-02-18 | S R Enterprises | 8.334 | DA+3 | 8.334 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | TB 412 - DPR - 2026-06-14.xlsx | Erection | 11/2 |  |  | Completed
2026-05-19 | 2026-05-21 | K2 Kumar | 8.334 | DA+3 | 2.778 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | TB 412 - DPR - 2026-06-14.xlsx | Erection | 8/1 |  |  | Completed
2026-05-26 | 2026-05-28 | K2 Kumar | 6.809 | DA+0 | 2.2697 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | TB 412 - DPR - 2026-06-14.xlsx | Erection | 7/1 |  |  | Completed
2026-02-07 | 2026-02-14 | Pinki Devi | 20.631 | DA+6 | 2.5789 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 32/1 |  |  | Completed
2026-02-14 | 2026-02-17 | Pinki Devi | 16.922 | DA+0 | 4.2305 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 27/4 |  |  | Completed
2026-02-17 | 2026-02-25 | Pinki Devi | 37.87 | DD+0 | 4.2078 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 29/0 |  |  | Completed
2026-02-17 | 2026-03-10 | Pinki Devi | 40.17 | DD+3 | 1.8259 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 28/0 |  |  | Completed
2026-03-08 | 2026-03-15 | Rang Construction | 28.063 | DB+3 | 3.5079 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 19/0 |  |  | Completed
2026-03-21 | 2026-03-30 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 24/0 |  |  | Completed
2026-03-25 | 2026-03-31 | Rang Construction | 38.079 | DC+6 | 5.4399 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 18/0 |  |  | Completed
2026-04-03 | 2026-04-09 | Rang Construction | 16.922 | DA+0 | 2.4174 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 19/1 |  |  | Completed
2026-04-03 | 2026-04-09 | Pinki Devi | 37.87 | DD+0 | 5.41 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 25/0 |  |  | Completed
2026-04-07 | 2026-04-13 | Rang Construction | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 18/2 |  |  | Completed
2026-04-13 | 2026-04-18 | Rang Construction | 18.405 | DA+3 | 3.0675 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 18/1 |  |  | Completed
2026-04-23 | 2026-04-26 | Rang Construction | 16.922 | DA+0 | 4.2305 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 19/4 |  |  | Completed
2026-04-09 | 2026-05-11 | Rang Construction | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 19/3 |  |  | Completed
2026-04-23 | 2026-05-24 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 19/2 |  |  | Completed
2026-05-31 | 2026-05-31 | Pinki Devi | 20.631 | DA+6 | 20.631 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | Erection | 26/2 |  |  | Completed
2026-03-10 | 2026-03-20 | Rang Construction | 20.631 | DA+6 | 1.8755 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 24/1 |  |  | Completed
2026-03-13 | 2026-03-22 | Pinki Devi | 40.17 | DD+3 | 4.017 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 34/0 |  |  | Completed
2026-03-15 | 2026-03-24 | Rang Construction | 16.922 | DA+0 | 1.6922 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 24/2 |  |  | Completed
2026-03-31 | 2026-04-03 | Pinki Devi | 21.756 | DA+9 | 5.439 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 34/1 |  |  | Completed
2026-04-09 | 2026-04-16 | Pinki Devi | 40.17 | DD+3 | 5.0213 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 29/0 |  |  | Completed
2026-04-18 | 2026-04-22 | Rang Construction | 16.922 | DA+0 | 3.3844 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 24/3 |  |  | Completed
2026-04-16 | 2026-04-22 | Pinki Devi | 20.631 | DA+6 | 2.9473 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 28/1 |  |  | Completed
2026-04-23 | 2026-04-28 | Pinki Devi | 37.87 | DD+0 | 6.3117 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 30/0 |  |  | Completed
2026-03-31 | 2026-05-01 | Rang Construction | 16.922 | DA+0 | 0.52881 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 26/1 |  |  | Completed
2026-04-03 | 2026-05-03 | Pinki Devi | 37.87 | DD+0 | 1.2216 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 25/0 |  |  | Completed
2026-04-03 | 2026-05-08 | Rang Construction | 31.21 | DC+0 | 0.86694 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 26/0 |  |  | Completed
2026-04-07 | 2026-05-09 | Pinki Devi | 40.17 | DD+3 | 1.2173 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 35/0 |  |  | Completed
2026-04-13 | 2026-05-15 | Pinki Devi | 37.87 | DD+0 | 1.1476 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 33/0 |  |  | Completed
2026-04-18 | 2026-05-20 | Pinki Devi | 16.922 | DA+0 | 0.51279 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 33/1 |  |  | Completed
2026-04-16 | 2026-05-21 | Rang Construction | 37.87 | DD+0 | 1.0519 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 28/0 |  |  | Completed
2026-05-31 | 2026-05-31 | Pinki Devi | 37.87 | DD+0 | 37.87 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | Erection | 36/0 |  |  | Completed
2026-03-16 | 2026-03-18 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 96/1 |  |  | Completed
2026-03-18 | 2026-03-20 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 96/2 |  |  | Completed
2026-03-20 | 2026-03-25 | Sanjiv Kumar | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 99/0 |  |  | Completed
2026-03-25 | 2026-03-27 | Sanjiv Kumar | 8.086 | DC+3 | 2.6953 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 98/0 |  |  | Completed
2026-03-27 | 2026-03-29 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 99/3 |  |  | Completed
2026-03-29 | 2026-03-30 | Sanjiv Kumar | 5.713 | DA+6 | 2.8565 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 99/2 |  |  | Completed
2026-03-30 | 2026-03-31 | Sanjiv Kumar | 4.378 | DA+0 | 2.189 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 99/1 |  |  | Completed
2026-03-31 | 2026-04-02 | Sanjiv Kumar | 6.563 | DC+0 | 2.1877 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 100/0 |  |  | Completed
2026-04-02 | 2026-04-04 | Sanjiv Kumar | 5.713 | DA+6 | 1.9043 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 100/1 |  |  | Completed
2026-04-04 | 2026-04-06 | Sanjiv Kumar | 5.167 | DA+3 | 1.7223 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 100/4 |  |  | Completed
2026-04-02 | 2026-04-07 | Zfapl | 8.086 | DC+3 | 1.3477 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 118/0 |  |  | Completed
2026-04-06 | 2026-04-08 | Sanjiv Kumar | 5.167 | DA+3 | 1.7223 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 100/3 |  |  | Completed
2026-04-08 | 2026-04-10 | Sanjiv Kumar | 5.167 | DA+3 | 1.7223 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 100/2 |  |  | Completed
2026-04-02 | 2026-04-12 | Druvika | 9.791 | DD+3 | 0.89009 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 65/0 |  |  | Completed
2026-04-10 | 2026-04-12 | Sanjiv Kumar | 6.563 | DC+0 | 2.1877 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 101/0 |  |  | Completed
2026-04-12 | 2026-04-14 | Sanjiv Kumar | 4.378 | DA+0 | 1.4593 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 101/1 |  |  | Completed
2026-04-07 | 2026-04-15 | Zfapl | 6.325 | DA+9 | 0.70278 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 116/4 |  |  | Completed
2026-04-14 | 2026-04-15 | Sanjiv Kumar | 5.167 | DA+3 | 2.5835 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 97/2 |  |  | Completed
2026-04-15 | 2026-04-19 | Sanjiv Kumar | 8.086 | DD+0 | 1.6172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 107/0 |  |  | Completed
2026-04-12 | 2026-04-20 | Druvika | 9.791 | DD+3 | 1.0879 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 66/0 |  |  | Completed
2026-04-18 | 2026-04-21 | Sanjiv Kumar | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 108/0 |  |  | Completed
2026-04-21 | 2026-04-22 | Sanjeev Kumar | 5.167 | DA+3 | 2.5835 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 107/1 |  |  | Completed
2026-04-23 | 2026-04-25 | Sanjeev Kumar | 9.791 | DD+3 | 3.2637 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 116/0 |  |  | Completed
2026-04-23 | 2026-04-28 | Sanjeev Kumar | 5.713 | DA+6 | 0.95217 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 115/1 |  |  | Completed
2026-04-12 | 2026-04-28 | Druvika | 6.563 | DC+0 | 0.38606 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 56/0 |  |  | Completed
2026-04-06 | 2026-04-28 | Exel Power | 9.791 | DD+3 | 0.4257 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 83/0 |  |  | Completed
2026-04-15 | 2026-04-29 | Sanjeev Kumar | 6.325 | DA+9 | 0.42167 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 117/1 |  |  | Completed
2026-04-30 | 2026-04-30 | Sanjeev Kumar | 9.791 | DD+3 | 9.791 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 115/0 |  |  | Completed
2026-04-29 | 2026-05-02 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 114/1 |  |  | Completed
2026-04-30 | 2026-05-03 | Dhuvika | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 55/1 |  |  | Completed
2026-05-03 | 2026-05-06 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 116/2 |  |  | Completed
2026-05-04 | 2026-05-07 | Dhuvika | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 55/0 |  |  | Completed
2026-05-07 | 2026-05-10 | Sanjeev Kumar | 5.97 | DB+0 | 1.4925 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 89/0 |  |  | Completed
2026-05-09 | 2026-05-12 | Sanjeev Kumar | 8.086 | DC+3 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 88/0 |  |  | Completed
2026-05-10 | 2026-05-13 | Dhuvika | 4.378 | DA+0 | 1.0945 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 54/3 |  |  | Completed
2026-05-10 | 2026-05-13 | Sanjeev Kumar | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 88/1 |  |  | Completed
2026-05-12 | 2026-05-15 | Sanjeev Kumar | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 87/2 |  |  | Completed
2026-05-13 | 2026-05-16 | Sanjeev Kumar | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 87/1 |  |  | Completed
2026-05-14 | 2026-05-17 | Exel Power | 11.469 | DD+9 | 2.8672 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 82/0 |  |  | Completed
2026-05-15 | 2026-05-18 | Sanjeev Kumar | 9.791 | DD+3 | 2.4478 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 87/0 |  |  | Completed
2026-05-17 | 2026-05-20 | Sanjeev Kumar | 4.378 | DA+0 | 1.0945 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 83/1 |  |  | Completed
2026-05-18 | 2026-05-21 | Exel Power | 8.086 | DD+0 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 84/0 |  |  | Completed
2026-05-20 | 2026-05-23 | Sanjeev Kumar | 11.469 | DD+9 | 2.8672 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 85/0 |  |  | Completed
2026-05-22 | 2026-05-25 | Dhuvika | 5.713 | DA+6 | 1.4283 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 54/2 |  |  | Completed
2026-05-23 | 2026-05-26 | Sanjeev Kumar | 8.086 | DD+0 | 2.0215 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 86/0 |  |  | Completed
2026-05-23 | 2026-05-26 | Exel Power | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 85/1 |  |  | Completed
2026-05-28 | 2026-05-31 | Dhuvika | 5.167 | DA+3 | 1.2917 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 54/1 |  |  | Completed
2026-05-28 | 2026-05-31 | Exel Power | 6.325 | DA+9 | 1.5813 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | Erection | 118/3 |  |  | Completed
2026-05-28 | 2026-06-01 | Rang | 29.486 | DD+0 | 5.8972 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | WIP | 20/0 |  |  | COMPLETED
2026-05-31 | 2026-06-04 | Pinki | 25.8087 | DB+3 | 5.1617 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | WIP | 27/0 |  |  | COMPLETED
2026-05-31 | 2026-06-05 | Rang | 25.8087 | DA+6 | 4.3014 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | WIP | 20/1 |  |  | COMPLETED
2026-05-31 | 2026-06-05 | Sanjeev | 6.8389 | DD+0 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 59/0 |  |  | COMPLETED
2026-05-31 | 2026-06-05 | Dhruvika | 6.8389 | DD+3 | 1.1398 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 54/0 |  |  | COMPLETED
2026-06-04 | 2026-06-07 | Exel Power | 6.8389 | DD+3 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 119/0 |  |  | COMPLETED
2026-06-04 | 2026-06-07 | Sanjeev | 6.8389 | DA+3 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 59/1 |  |  | COMPLETED
2026-06-06 | 2026-06-10 | Rang | 25.8087 | DA+0 | 5.1617 | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | WIP | 11/3 |  |  | COMPLETED
2026-05-20 | 2026-06-10 | Nirajan | 29.486 | DD+3 | 1.3403 | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | WIP | 43/0 |  |  | COMPLETED
2026-06-04 | 2026-06-10 | Sanjeev | 6.8389 | DA+3 | 0.97699 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 59/2 |  |  | COMPLETED
2026-06-07 | 2026-06-10 | Reyansh | 6.8389 | DA+0 | 1.7097 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 101/2 |  |  | COMPLETED
2026-06-04 | 2026-06-11 | Dhruvika | 6.8389 | DC+0 | 0.85486 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 58/0 |  |  | COMPLETED
2026-06-04 | 2026-06-13 | Sgse India Pvt Ltd | 8.6189 | DC+0 | 0.86189 | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | TB 412 - DPR - 2026-06-14.xlsx | WIP | 8/0 |  |  | COMPLETED
2026-06-11 | 2026-06-13 | Sanjeev | 6.8389 | DA+6 | 2.2796 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 59/3 |  |  | COMPLETED
2026-06-11 | 2026-06-13 | Dhruvika | 6.8389 | DA+3 | 2.2796 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 58/1 |  |  | COMPLETED
2026-06-11 | 2026-06-13 | Reyansh | 6.8389 | DA+0 | 2.2796 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 101/3 |  |  | COMPLETED
2026-06-04 | 2026-06-14 | Exel Power | 6.8389 | DD+0 | 0.62172 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 117/0 |  |  | COMPLETED
2026-06-13 | 2026-06-14 | Reyansh | 6.8389 | DA+3 | 3.4195 | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 101/4 |  |  | COMPLETED
2026-06-04 |  | Pinki | 29.486 | DD+6 |  | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | WIP | 38/0 |  |  | Bottom Section WIP
2026-06-06 |  | Rang | 25.8087 | DA+0 |  | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | WIP | 11/2 |  |  | Bottom Section WIP
2026-06-04 |  | Rabish | 8.6189 | DD+0 |  | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | TB 412 - DPR - 2026-06-14.xlsx | WIP | 7/0 |  |  | Ground Assembly WIP
2026-06-14 |  | Dhruvika | 6.8389 | DC+0 |  | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 81/0 |  |  | Ground Assembly WIP
2026-06-11 |  | Nirajan | 29.486 | DD+0 |  | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | WIP | 42/0 |  |  | Ground Assembly WIP
2026-06-14 |  | Sanjeev | 6.8389 | DA+6 |  | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 59/4 |  |  | Material Shifting WIP
2026-06-14 |  | Reyansh | 6.8389 | DA+3 |  | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 102/1 |  |  | Material Shifting WIP
2026-06-09 |  | Sgse India Pvt Ltd | 25.8087 | DA+0 |  | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | WIP | 27/3 |  |  | 2nd Section WIP

## Data Issues
Start Date | Complete Date | Gang name | Tower Weight | Tower Type | Productivity | Project Code | Line Name | Project Name | Project Display | Project Scope Key | Source File | Source Sheet | Location No. | Tower Tightening Raw | Tower Tightening | Status | Issues
2026-06-04 |  | Pinki | 29.486 | DD+6 |  | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | WIP | 38/0 |  |  | Bottom Section WIP | Missing start/end date (not expanded)
2026-06-06 |  | Rang | 25.8087 | DA+0 |  | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | WIP | 11/2 |  |  | Bottom Section WIP | Missing start/end date (not expanded)
2026-06-04 |  | Rabish | 8.6189 | DD+0 |  | TB 412 | 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | TB 412 - 220 TM Chapra-Amnour | tb412220tmchapraamnour | TB 412 - DPR - 2026-06-14.xlsx | WIP | 7/0 |  |  | Ground Assembly WIP | Missing start/end date (not expanded)
2026-06-14 |  | Dhruvika | 6.8389 | DC+0 |  | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 81/0 |  |  | Ground Assembly WIP | Missing start/end date (not expanded)
2026-06-11 |  | Nirajan | 29.486 | DD+0 |  | TB 412 | 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | TB 412 - 400 KV LOOP OUT | tb412400kvloopout | TB 412 - DPR - 2026-06-14.xlsx | WIP | 42/0 |  |  | Ground Assembly WIP | Missing start/end date (not expanded)
2026-06-14 |  | Sanjeev | 6.8389 | DA+6 |  | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 59/4 |  |  | Material Shifting WIP | Missing start/end date (not expanded)
2026-06-14 |  | Reyansh | 6.8389 | DA+3 |  | TB 412 | 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | TB 412 - 220 SZ Chapra-Gopalganj | tb412220szchapragopalganj | TB 412 - DPR - 2026-06-14.xlsx | WIP | 102/1 |  |  | Material Shifting WIP | Missing start/end date (not expanded)
2026-06-09 |  | Sgse India Pvt Ltd | 25.8087 | DA+0 |  | TB 412 | 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | TB 412 - 400 KV LOOP IN | tb412400kvloopin | TB 412 - DPR - 2026-06-14.xlsx | WIP | 27/3 |  |  | 2nd Section WIP | Missing start/end date (not expanded)

## Issues
file | sheet | issue
TB 412 - DPR - 2026-06-14.xlsx | Erection | Duplicate columns detected after header mapping; kept first occurrence for: nan
TB 412 - DPR - 2026-06-14.xlsx | Erection | Duplicate columns detected after header mapping; kept first occurrence for: nan
TB 412 - DPR - 2026-06-14.xlsx | Erection | Duplicate columns detected after header mapping; kept first occurrence for: nan
TB 412 - DPR - 2026-06-14.xlsx | WIP | 'tower weight' header missing in configured section; will use same-file line averages where available
TB 412 - DPR - 2026-06-14.xlsx | WIP | Assumed Tower Weight from same-file historical line averages: 220 SZ Chapra-Gopalganj=6.839 MT for 15 row(s); 220 TM Chapra-Amnour=8.619 MT for 2 row(s); 400 KV LOOP IN=25.809 MT for 5 row(s); 400 KV LOOP OUT=29.486 MT for 4 row(s)

## Diagnostics
file | project | sheet | line_name | line_name_source | detected_header_row | columns_detected | section_start_text | section_end_text | section_start_row | section_end_row | configured_sheet | template_mapping_sheet | template_mapping_applied | template_mapping_changes | blank_location_rows_dropped | tower_weight_assumed_mt | tower_weight_assumption_rows | date_repairs_applied | line_filter_column | line_filter_value | line_filter_rows | line_column | tower_weight_line_average_rows
TB 412 - DPR - 2026-06-14.xlsx | TB 412 - 220 TM Chapra-Amnour | Erection | 220 TM Chapra-Amnour | config | 1 | sr, location no, tower type, tower weight, start date, completion date, agency, completion month, cumm, status, remarks | 220 KV Chhapra(NEW) to Amnour | LILO of 400 KV Barh | 2 | 17 | Erection | TB 412 Erection | TRUE | C1:sr->sl no; C5:start date->starting date; C7:agency->gang name | 6 |  | 0 | 0
TB 412 - DPR - 2026-06-14.xlsx | TB 412 - 400 KV LOOP IN | Erection | 400 KV LOOP IN | config | 1 | sr, location no, tower type, tower weight, start date, completion date, agency, nan, nan, status, remarks | LILO of 400 KV Barh | 220 KV D/C Chapra -Gopalganj | 18 | 54 | Erection | TB 412 Erection | TRUE | C1:sr->sl no; C5:start date->starting date; C7:agency->gang name | 0 |  | 0 | 0 | remarks | LOOP IN | 15
TB 412 - DPR - 2026-06-14.xlsx | TB 412 - 400 KV LOOP OUT | Erection | 400 KV LOOP OUT | config | 1 | sr, location no, tower type, tower weight, start date, completion date, agency, nan, nan, status, remarks | LILO of 400 KV Barh | 220 KV D/C Chapra -Gopalganj | 18 | 54 | Erection | TB 412 Erection | TRUE | C1:sr->sl no; C5:start date->starting date; C7:agency->gang name | 0 |  | 0 | 0 | remarks | LOOP OUT | 16
TB 412 - DPR - 2026-06-14.xlsx | TB 412 - 220 SZ Chapra-Gopalganj | Erection | 220 SZ Chapra-Gopalganj | config | 1 | sr, location no, tower type, tower weight, start date, completion date, agency, nan, nan, status, remarks | 220 KV D/C Chapra -Gopalganj |  | 55 |  | Erection | TB 412 Erection | TRUE | C1:sr->sl no; C5:start date->starting date; C7:agency->gang name | 2 |  | 0 | 0
TB 412 - DPR - 2026-06-14.xlsx | TB 412 | WIP |  | column | 1 | t l name, sr no, gang, location no, t o t, d o s, d o c, mp, remarks, nan | ERECTION | STRINGING | 59 | 87 | WIP | TB 412 WIP Erection | TRUE | C1:t l name->line name; C2:sr no->sl no; C3:gang->gang name; C5:t o t->tower type; C6:d o s->starting date; C7:d o c->completion date; C9:remarks->status | 1 |  | 26 | 0 |  |  |  | line name | 26

## README_Assumptions
Notes
Assumptions & Cleaning Rules:
- Start date cutoff: rows with Start Date before 2021-01-01 are not expanded and logged in 'Data Issues'.
- Completion date must be before 2026-06-16 (future completions go to 'Data Issues').
- Tower Weight range: only [0, 500] MT is considered valid for expansion; out-of-range rows go to 'Data Issues'.
- Missing or non-positive durations (Start/End missing or Start > End or 0) are logged to 'Data Issues' and not expanded.
- Ambiguous numeric dates (e.g., 1/12/2025) that initially parse as Start > End are retried with month-first before being marked invalid.
- Gang name normalization: remove special characters (digits kept), Title Case words, and insert a space before trailing digits (e.g., 'xyz4' â†’ 'Xyz 4').
- If 'Tower Weight' header is missing in a sheet, Tower Weight is assumed as 45 MT for all rows in that sheet (noted in 'Issues').
- If some Tower Weight values are present and some are blank in a sheet, blank rows are filled with the average of available in-range tower weights for that sheet (noted in 'Issues').
- If a sheet has no usable in-range Tower Weight values at all, blank rows fall back to 45 MT (noted in 'Issues').
- DPR_Config support: when multiple erection sheet names are configured for a project, each listed sheet is processed independently, assigned its own line identity, and then concatenated.
- DPR_Config template mapping: for projects with discipline-specific template check marked Yes, column-wise mapping from the discipline template tab is applied before required-field validation.
- DPR_Config section mapping: optional '<Project> Erection Sections' tabs can split a physical sheet by marker text, filter rows, derive line names from a column, and use section-specific template tabs.
- Sectioned rows with missing Tower Weight first use same-file historical averages for the same Line Name before falling back to the default assumption.
- Sheets:
â€¢ ProdDailyExpanded : per-day expanded rows used by the dashboard
â€¢ ProdDailyExpandedSingles : per-day expanded rows including single-occurrence gangs
â€¢ RawData : per-erection rows (unexpanded), for traceability
â€¢ Data Issues : row-level data problems (reason in 'Issues' column)
â€¢ Issues : file-level problems (missing sheet/headers, read/open errors, etc.)
â€¢ Diagnostics : which sheet used, detected header row, and normalized header text
- Dashboard note: a 15-day productivity loss cap is used in downstream analytics.