## Slide 1
KEC International Limited
PGCIL Review – 18th May’26
Power T & D
Cables
Railways
Civil
Renewables
Oil & Gas Pipelines

## Slide 2: Agenda Points
Priority projects to be completed
Support Required - In terms of ROW, front and Land availability
Pending Amendments and Manpower Status
Region and Project wise Status with critical issues
Commercial Closures and Pending Claims
  Project wise details under commercial closure
  Region wise Cost Compensation and L2 revision
Finalization of spare supply contract through PESL for South OLPAD and Narendra extension Project. NOA from PGCIL was issued on 26/11/24 for South OLPAD-23 Cr. and for 13/05/25(Narendra- 60.35 Lacs )

## Slide 3: Summary of Projects under Execution by KEC (TL Projects)
Sl. No. | Project Name | Scheduled Completion | Expected Completion
1 | 765KV D/C Bikaner III - Neemrana II (TA – 413) | 11/12/25 | 30/07/26
2 | 765KV D/C Vataman - Navsari Transmission Line (TA- 414) |  | 
3 | 765 KV D/C Neemrana II Bareilly Line (TA- 416) |  | 
4 | 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418) |  | 
5 | 765KV D/C Sikar II – Narela (TA- 419) |  | 
6 | 765KV D/C Bidar Ps – Maheshwaram (TA- 421) |  | 
7 | 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504) |  | 
8 | 765KV D/C Beawar-Mandsaur TL (TA- 505) |  | 
9 | 400 KV D/C Sirohi - Chittorgarh TL (TA- 506) |  | 
10 | 765KV D/C Mandsaur – Kurawar Part I (TA- 509) |  | 
11 | 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510) |  | 
12 | 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512) |  | 
13 | 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513) |  | 
14 | 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514) |  | 
15 | 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515) |  | 
16 | 765kV D/C Kurnool IV – Bidar Line (TA- 601) |  | 
17 | 80800 KV HVDC KPS-II to Nagpur (TA- 602) |  | 
18 | 132 KV D/C Tawang-Lumla Line (A920) |  | 
19 | 400 KV D/C Twin Line Latehar- Patraru (A303/304) |  | 
20 | Sikkim Tower Pkg TK04 (A-722/723) |  | 

## Slide 4: Summary of projects under Execution by KEC (SS Projects)
Sl. No. | Project Name | Scheduled Completion | Expected Completion
1 | SA52C-SS118 220kV Bay Ext Raigarh GIS Sub-Sation (SA – 52C) | 24/05/26 | May’26
2 | 765/400 kV KPS-2 Ext 39T (SA – 503) |  | 
3 | SS33T 765kV GIS South Olpad (SA – 508) |  | 
4 | SS33T 765kV AIS Ahmedabad Extn (SA – 5A8) |  | 
5 | SS33T 765kV GIS Vadodara Extn S/S (SA – 5V8) |  | 
6 | SS64T 765kV GIS Narendra Extn (SA – 603) |  | 
7 | 765KV Bay Extension GIS Sub-Station Narela (SA-417) |  | 

## Slide 5: Priority Projects to be completed
S No | Project Name | Type of Project | Estimated Completion
1 | 765/400 KV KPS3 Bay Extn (SA-52G) | SS | Charged
2 | Narendra Bay Extension SS( 07 T)(SA-420)- Ready for charging | SS | 
3 | 220 KV Raigarh Bay Extn (SA- 52 C) | SS | 
4 | 765/400 KV Phadge Bay Extn (SA- 52 M) | SS | 
5 | 765 KV D/C Bidar Maheshwaram (TA-421) | T/L | 
6 | 765 KV DC Neemrana Bareilly (TA-416) | T/L | 
7 | 765 /400 KV KPS-II Extension (SA- 503) | SS | 
8 | 765 KV Narela Bay Extn (SA- 417) | SS | 
9 | 765 KV DC Koppal Raichur TL (TA-418) | T/L | 
10 | 765 KV DC Bikaner Neemrana TL (TA-413) | T/L | 
11 | 765 KV Bay Extn (16 T)at Navsari for Vataman Line(SA-422) | SS | 

## Slide 6: Support Required
Limited Front Availability where work is moving with minimal Progress
800 KV HVDC TL-06 Khavda –Nagpur (TA- 602)
765 KV D/C Sikar Narela TL (TA- 419)- Start of Stringing works, 2 TSEs available at site
Finalization of Pile Fdn in South Olpad Ahemdabad TL- Reserve Forest Issues need to be resolved
Projects - Non starter
800 KV HVDC TL-02 Khavda-Nagpur (TA- 514)
800 KV HVDC TL-03 Khavda Nagpur (TA- 515)
765 KV South OLPAD GIS – Land still not handed over ( as per L2- Mar’25 )( SA-508)
400 KV D/C Siwani Fatehabad and Sivani Patran (TA- 513)

## Slide 7: Pending Amendments
S No | Project Name(SS/ TL) | Type of Project | Pending Since | Achievement Since Last Discussion
1 | 400 KV D/C Sirohi Chittorgarh TL (TA-506) | TL | Jun’25 | 
2 | 765 KV Ahmedabad- Navsari TL(TA-325) | TL |  | 
3 | 765KV Bikaner 3 – Neemrana 2 TL(TA-413) | TL |  | 
4 | 765kV/400 KV Bhadla 3 SS | SS |  | 
5 | 765 KV Bidar Maheswaram TL(TA-421) | TL |  | 
6 | 765 KV Bikaner Siwani TL (TA- 512) | TL |  | 
7 | 765/400 kV Ramgarh SS (Amendment VI) | SS |  | 
8 | 765 KV D/C Rishabhdeo – Mandsaur | TL |  | 
SS Projects : 1986 ( Civil- 1283 & Electrical- 703)
Erection : 1797 Manpower (50 Gangs)
Stringing : 970 Manpower(12 TSE & 8 Manual)
Total : 4753 Manpower
Manpower Status

## Slide 8: List of Running Substation & TL Project (Cont..)
Sl. No. | Project Code | Region | Project Details | TL/SS | Project Value (Crs) | UEOB As on 1st May'26 (Crs)
1 | A-303/304 | ER1 | JSEB Lines | TL |  | 
2 | A-722/723 | ER2 | Sikkim Tower PKg TK-04 | TL |  | 
3 | A920 | NER | 132 KV D/C Tawang -Lumla Line | TL |  | 
4 | SA-417 | NR1 | 765kV Narela GIS Extension - SS02 | SS |  | 
5 | TA-419 | NR1 | 765 kV D/C Sikar II to Narela TL- TL02 | TL |  | 
6 | TA-513 | NR2 | 400 kv D/C Siwani - Patran, part 3 | TL |  | 
7 | TA-416 | NR3 | 765 kV D/C Neemrana-II-Bareilly , TL03 | TL |  | 
8 | SA-410 | NWR | 765/400/220 kV Bhadla SS & Sikar extn. | SS |  | 
9 | TA-413 | NWR | 765 kV D/C Bikaner-III-Neemrana-II, TL02 | TL |  | 
10 | TA-504 | NWR | 765 KV D/C Rishabdeo – Mandsaur Line (Part I) & LILO | TL |  | 
11 | TA-505 | NWR | 765 KV D/C Beowar-Mandsaur TL | TL |  | 
12 | TA-506 | NWR | 400 KV D/C Sirohi – Chittorgarh Transmission Line | TL |  | 
13 | TA-512 | NWR | 765 KV D/C Bikaner Siwani | TL |  | 
14 | SA-420 | SR1 | 765kV Narendra GIS Extn - SS07T | SS |  | 

## Slide 9: List of Running Substation & TL Project
Sl. No. | Project Code | Region | Project Details | TL/SS | Project Value (Crs) | UEOB As on 1st May'26 (Crs)
15 | SA-603 | SR1 | 765kV New Narendra GIS extn. Pkg-SS-64T | SS |  | 
16 | TA-418 | SR1 | 765 KV D/C Kopal 2 - Raichur, TL01 | TL |  | 
17 | TA-421 | SR1 | 765kV D/C Bidar PS - Maheshwaram | TL |  | 
18 | TA-601 | SR1 | 765 KV D/C Kurnool IV - Bidar Line | TL |  | 
19 | SA-502 | WR1/WR2 | SS-118 (Extension of 765/400kV Maheshwaram, 765/400 KPS3, 765/400 Phadge & 220kV Raigarh GIS | SS |  | 
20 | SA-503 | WR2 | SS-39T - (Extn of 765/400kV KPS-2 GIS) | SS |  | 
21 | SA-508 | WR2 | SS-33T 1) 765kV South Olpad GIS 2) Extn. Of 765kV Vadodara GIS 3) Extn. Of 765kV Ahmedabad SS | SS |  | 
22 | TA-414 | WR2 | 765 kV D/C Vataman Navsari Line | TL |  | 
23 | TA-509 | WR2 | 765 kV D/C Mandsaur - Korawar | TL |  | 
24 | TA-510 | WR2 | 765 kV D/C South Olpad - Ahmedabad | TL |  | 
25 | TA-514 | WR2 | 800 KV HVDC TL-02 KPS III Khavda - Nagpur | TL |  | 
26 | TA-515 | WR2 | 800 KV HVDC TL-03 KPS III Khavda - Nagpur | TL |  | 
27 | TA-602 | WR2 | 800 KV HVDC TL06 KPS-III Khavda to Nagpur | TL |  | 
Total Amount in Crs |  |  |  |  |  | 

## Slide 10: Gujarat Region (WR-II)

## Slide 11: TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414)
LOA DATE: 12/03/2024 |  | CONTRACTUAL COMPLETION: 11/12/2025 | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 
Activity |  | UoM |  | As Per LOA (Qty) |  | Revised |  | As per L2 (April'26) |  | Completed till 30.04.26 |  | Balance As on 01.05.26 |  | Front Availability |  | Gangs Available |  | Plan May-26 |  | Plan Jun-26 | Plan Jul-26 | Remarks
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Plan | Act |  |  | 
Check Survey |  | Km |  |  |  | 127.799 |  |  |  | 127.799 |  | 0 |  |  |  |  |  |  |  |  |  | 
Foundation |  | No |  |  |  | 352 |  |  |  | 316 |  | 36 |  |  |  | 9.0 |  | 34 | 8 | 14 | - | 
Erection |  | No |  |  |  | 352 |  |  |  | 225 |  | 127 |  |  |  | 15.0 |  | 55 | 13 | 52 | 25 | 
Stringing |  | Km |  |  |  | 127.799 |  |  |  | 10.396 |  | 117.403 |  |  |  | 7.0 |  | 20 | 3 | 22 | 16 | 
OPGW Stringing |  | Km |  |  |  | 127.799 |  |  |  | 0 |  | 127.799 |  |  |  |  |  | 20 |  | 10 | 5 | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item |  | As Per LOA (Qty) |  | As Per LOA (Qty) |  | Revised |  | As per L2 |  | Balance |  | Plan for May'26 |  |  |  |  | Remarks | Remarks |  |  |  | 
 |  |  |  |  |  | (Qty) |  | (April'26) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stub |  | 340 |  | 340 |  | 352 |  | 352 |  | 11 |  | 7 |  |  |  |  | Total 12.5 sets stubs required; where 8 sets were excess/1 Nos Clearnce pending | Total 12.5 sets stubs required; where 8 sets were excess/1 Nos Clearnce pending |  |  |  | 
Tower |  | 340 |  | 340 |  | 352 |  | 352 |  | 10 |  | 4 |  |  |  |  | 14 Towers balance to supply; DB Type 3 tower excess/ 4 Nos Hold , 2 Nos Plan Jul | 12 Towers balance to supply; DB Type 3 tower excess/ 4 Nos Hold , 2 Nos Plan Jul |  |  |  | 
Conductor |  | 4664 |  | 4664 |  | 4647 |  | 4664 |  | -10 |  |  |  |  |  |  | 10 kms Conductor excess supplied due to route diversion | 10 kms Conductor excess supplied due to route diversion |  |  |  | 
Earthwire |  | 130 |  | 130 |  | 134 |  | 130 |  | 4 |  |  |  |  |  |  | Qty Confirmation awaited from client. | QCS pending –due to additional earthing /After finalization of location from client |  |  |  | 
160KN CLR |  | 5528 |  | 5528 |  | 5356 |  | 5528 |  | 992 |  |  |  |  |  |  | Pending due to Amendment from client | Cost proposal approval from PCH awaited |  |  |  | 
210KN CLR |  | 15888 |  | 15888 |  | 16320 |  | 15888 |  | 1199 |  |  |  |  |  |  |  | QCS to be released after amendment ,Cost proposal approval from PCH awaited |  |  |  | 
HW Fittings |  | 100 |  | 100 |  | 100 |  | 100 |  | 10 |  |  |  |  |  |  |  | Cost proposal approval from PCH awaited |  |  |  | 

## Slide 12: TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414)
LOA DATE: 12/03/2024 |  | CONTRACTUAL COMPLETION: 11/12/2025 | 
No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stubs Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stub Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Erection | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stringing | As per L2 | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | TSE (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Manual(Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply as per L2 | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply Actual | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 13: TL04 - 765KV D/C Vataman - Navsari Transmission Line (TA- 414)
Issues / Support Required
1. Fdn:33 loc under hold due to ROW-9, Railway clearance-2, forest-1, Nilgiri tree cutting issues-5, Stub NA-6, Solar plant-2. Additionally, 08 loc under hold, which are falling inside GOPIN Industrial Park. Location availability not available to complete in the month of May, Police Protection required for all locations
2. Erection: Out of balance 134 loc in erection, 56 loc are under ROW as on date, Front available-18 and WIP 14
3. Cable bypass agency needs to be finalized by PGCIL. Shutdown needs to be expedited
4. Hotline stringing approval is required for 66 KV and above, wherever shut down is critical. (Total qty- 48 and in the BOQ, only 01 qty is approved). Tree cutting needs to be expedited for ready stinging stretches (131/3,131/4,131/5,132/2,165/1, 232/1 & 247/0)
5. 02 nos of Railway and 02 PLC Xing approval pending
LOA DATE: 12/03/2024 | LOA Value in Cr.:- 632 | CONTRACTUAL COMPLETION: 11/12/25 | PLANNED COMPLETION: 30/10/26

## Slide 14: TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509)
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan April 26 | Plan April 26 |  |  | Plan May 26 | Plan June 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act | Act |  |  | 
Check Survey | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | No | 309 | 309 |  | 264 | 45 |  | 6 | 4.0 | 19 | 19 | 13 | 13 | 25 | 25 | 
Erection | No |  |  |  |  |  |  | 13 |  | 42 | 42 | 45 | 45 |  | 42 | 
Stringing | Km | 118.397 | 118.397 |  | 0 | 118.4 |  | 1 | 0.0 | 0 | - | 0 | - |  | 12 | 
OPGW Stringing | Km |  |  |  |  |  |  |  |  | 0 | - | 0 | - |  | - | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  | Remarks |  |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  | Raised Chimney: Drawings related issue 10 locations |  |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
210KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 15: TL01 - 765KV D/C Mandsaur – Kurawar Part I (TA- 509)
Issues / Support Required
1. Drawings required for Raised Chimney – 10 locations are affected on account of same. This is affecting 9 km of stringing stretch
2. 10 locations under Right of Way
3. Approval of Diversion proposal
LOA DATE: 26/11/24 | LOA Value in Cr.:- 474.37 | CONTRACTUAL COMPLETION: 25/10/2026 | PLANNED COMPLETION:25/10/2026

## Slide 16: TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510)
LOA DATE: 26/11/2024 |  | CONTRACTUAL COMPLETION: 25/10/26 | 
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) |  | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  |  | Plan | Plan | Act |  |  | 
Check Survey | Km |  | 114.516 |  | 90.949 | 23.567 |  |  |  | 23.567 | 23.567 | 23.567 |  |  |  | 
Foundation | No |  | 293 |  | 79 | 214 |  |  | 4 | 42 | 42 | 42 |  | 25 | 25 | 
Erection | No |  | 293 |  | 36 | 257 |  |  | 1 | 18 | 30 | 18 |  | 25 | 20 | 
Stringing | Km |  | 114.516 |  | 0 | 114.516 |  |  |  | 0 | 00 | 0 |  |  |  | 
OPGW Stringing | Km |  | 114.516 |  | 0 | 114.516 |  |  |  | 0 | 00 | 0 |  |  |  | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  | Plan for May'26 |  |  |  | Remarks |  |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  | Balance to be supply after final Amendment . |  |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos |  |  |  |  |  |  |  |  |  |  | QCS Released -500 Nos & 774 is pending to be released |  |  |  | 
210KN CLR | Nos |  |  |  |  |  |  |  |  |  |  | QCS Released -500 Nos & 2320 is pending to be released |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  | Qty confirmation to be given after approval of Check survey. |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 17: TL04- 765 kV D/C Ahmedabad - South Olpad Transmission Line (TA- 510)
Issues / Support Required
1. 16 kms Detailed Survey approval pending
2. Pile foundation work stopped due to reserve forest approval pending
3. Continuous Front required to maximize the output
LOA DATE: 26/11/2024 | LOA Value in Cr.: 578.78 | CONTRACTUAL COMPLETION: 25/10/26 | PLANNED COMPLETION: 15/03/27

## Slide 18: TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514)
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  |  | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act | Act |  |  | 
Check Survey | Km |  |  |  |  |  |  | - |  | - |  | - |  |  |  | 
Foundation | No |  |  |  |  |  |  | 10 |  | 15 |  | 1 |  |  |  | 
Erection | No |  |  |  |  |  |  | 3 |  | 10 |  | 0 |  |  |  | 
Stringing | Km |  |  |  |  |  |  | - |  | - |  | - |  |  |  | 
OPGW Stringing | Km |  |  |  |  |  |  | - |  | - |  | - |  |  |  | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
210KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 19: TL02 - 800kV HVDC Bipole Line between KPS2 (HVDC) & Nagpur (HVDC) (TA- 514)
Issues / Support Required:-
1. Locations under severe ROW, Land Compensation and crop compensation not yet finalized by committee (DLVC committee)
2. Section -16 pending, this is crucial to use administrative support to clear locations
LOA DATE: 23/01/25 | LOA Value in Cr.: 269.93 Cr | CONTRACTUAL COMPLETION: 22/07/28 | PLANNED COMPLETION: 22/07/28

## Slide 20: TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515)
Activity | UoM | As Per LOA (Qty) | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | As per L2 (April'26) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (Up to 01.05.26) | Balance (As on 01.05.26) | Balance (Up to 01.05.26) | Front Availability |  | Gangs Available | Plan May 26 | Plan May 26 | Plan May 26 | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Plan | Plan | Act |  |  | 
Check Survey | Km |  | 83.14 |  | 83.14 |  | 83.14 |  | - |  | - |  |  |  | - |  |  | - | - | 
Foundation | No |  | 215 |  | 84 |  | 84 |  | 208 |  | 208 |  |  |  | 15 |  |  | 10 | 10 | 
Erection | No |  | 215 |  | 60 |  | 60 |  | 215 |  | 215 |  |  |  | 6 |  |  | 10 | 6 | 
Stringing | Km |  | 83.14 |  | 8 |  | 8 |  | 83.331 |  | 83.331 |  |  |  | - |  |  | - | - | 
OPGW Stringing | Km |  | 83.14 |  | 8 |  | 8 |  | 83.331 |  | 83.331 |  |  |  | - |  |  | - | - | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Remarks |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Due to non approval of Amendment & unavailability of drawings & BOM |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Due to non approval of Amendment & unavailability of drawings & BOM |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Suppled as per L2.Bal: Q2,Q3 |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | To be supplied as per L2. |  |  | 
160KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 39% has been released, balance to be supplied as per L2. |  |  | 
210KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 65% has been released, balance to be supplied as per L2. |  |  | 

## Slide 21: TL03 - 800 kV HVDC KPS2 - Nagpur T/L Project (Part -3) (TA- 515)
Issues / Support Required
1. Locations under severe ROW, and no front available
2. PGCIL Establishment
LOA DATE: 12/02/25 | LOA Value in Cr.: 349.3 Cr | CONTRACTUAL COMPLETION: 11/08/28 | PLANNED COMPLETION:11/08/28

## Slide 22: TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602)
 |  | CONTRACTUAL COMPLETION: 12/11/28 | 
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  |  | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act | Act |  |  | 
Check Survey | Km |  |  |  |  |  |  | - |  | 50 |  |  |  | - | - | 
Foundation | No | 494 | 478 |  | 145 | 333 |  | 6 | 35 | 35 | 35 | - | - | 35 | 20 | 
Erection | No | 494 | 478 |  | 44 | 434 |  | 5 | 40 | 40 | 40 | - | - | 35 | 30 | 
Stringing | Km | 0 | 0 |  | 0 | 0 |  | - |  | - |  | - | - | - | - | 
OPGW Stringing | Km | 0 | 0 |  | 0 | 0 |  | - |  | - |  | - | - | - | - | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  | Remarks |  |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  |  | 51.715 |  |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos |  |  |  | 4144 |  |  |  |  |  |  | Insulator being delayed due to delay in Design/Type Testing |  |  |  | 
210KN CLR | Nos |  |  |  |  |  |  |  |  |  |  | Insulator being delayed due to delay in Design/Type Testing |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 23: TL06 - 800 KV HVDC KPS-II to Nagpur (TA- 602)
Issues / Support Required
1. Power Line Crossing Approval. (In which 9 No's Site Visit done) Total-12 No’s | Submitted-11| Balance-1| Approval Required-11
2. NH Crossing Site Inspection (Submitted-3 No’s) Total-4 No’s | Submitted-3| Balance-1| Approval Required-3
3. Finalization of river crossing Proposal (Narmada River Crossing)
LOA DATE: 13/05/2025 | LOA Value in Cr.: 613 | CONTRACTUAL COMPLETION: 12/11/28 | PLANNED COMPLETION: 12/09/28

## Slide 24: SS118 220kV Bay Ext Raigarh GIS Sub-Sation (SA52C)
LOA Date: 26.06.2024 | LOA Completion Sch: 23-10-2025 | Target Comp Date: 24-05-2026 | Planned Completion: May’26
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
1 | Drain | RM | 40 | 600 | 600 | 360 | 240 | 60% | WIP | 15-05-2026 | 
2 | Gravel Spreading | M2 | 5000 | 4100 | 4100 | 0 | 4100 | 0% |  | 30-05-2026 | 
3 | GIS Equipment and GIB Testing | Nos. | 78 | 78 | 78 | 78 | 0 | 100% |  |  | 
4 | HV Testing | Lot | 1 | 1 | 1 | 0.9 | 0.1 | 90% | Y Phase Bus -2 Issue Resolution WIP | 15-05-2026 | 
5 | Final Testing and commissioning | % | 100 | 100 | 100 | 10 | 90 | 10% | WIP | 24-05-2026 | 

## Slide 25: 765/400 kV KPS-2 Ext 39T (SA-503)
LOA Date: July’24 | LOA Completion Sch: March’26 | Target Comp Date: 400 kV : June/765kV :July | Project Value: 390 Crs.
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
1 | Stone Column Work | RM | 56512 | 56512 | 56512 | 56512 | - | 100 | Civil Manpower-130 nos. | Completed | Scope yet to be finalized
2 | ICT Foundation | Nos. | 12 | 12 | 12 | 12 | - | 100 |  | Completed | 
3 | Fire Wall | Nos. | 10 | 10 | 10 | 10 | - | 100 |  | Painting balance | 
4 | 400kV Tower Foundation | Nos. | 8 | 8 | 8 | 8 | - | 100 |  | Completed | 
5 | 765kV GIS Building-A | LS | 100% | 100% | 100% | 95% | 5% | 95 |  |  | 
5 | 765kV GIS Building-A | LS | 100% | 100% | 100% | 95% | 5% | 95 |  |  | 
6 | 400kV GIS Building-B | LS | 100% | 100% | 100% | 97% | 3% | 97 |  |  | 
7 | 400kV GIS Building-C | LS | 100% | 100% | 100% | 97% | 3% | 97 |  |  | 
8 | 765 kV GIS Building-D | LS | 100% | 100% | 100% | 80% | 20% | 80 |  | 15/05/2026 , Grade Slab WIP | 
9 | Equipment foundation | Nos. | 307 | 307 | 307 | 248 | 59 | 80 |  |  | 
10 | Bus duct foundation | Nos. | 215 | 215 | 215 | 105 | 110 | 48 |  | 20/06/2026 | 

## Slide 26: 765/400 kV KPS-2 Ext 39T (SA-503)
LOA Date: July’24 | LOA Completion Sch: March’26 | Target Comp Date: 400 kV : June/765kV :July | Project Value: 390 Crs.
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
1 | 400kV GIS-B Bay Erection | Nos | 9 | 9 | 9 | 9 | - | 100 | Electrical:85 | Completed | 
 | 400kV GIS-C Bay Erection | Nos. | 6 | 6 | 6 | 6 | - | 100 |  | Completed | 
2 | 400kV Tower Erection | Nos | 8 | 8 | 8 | 8 | - | 100 |  | Completed | 
3 | Outdoor Earthing - Main Mat Laying | RM | 4620 | 4620 | 4620 | 1723 | 2897 | 37 |  | 30.06.2026 | 
4 | 400kV Sec 1 :- GIB ( Outside Building) | RM | 1,343 | 1,343 | 1,343 | 950 | 393 | 70 |  | May | 
5 | 400kV Sec 1 :- GIB Length ( Inside Building) | RM | 50 | 50 | 50 | 50 | - | 100 |  | May | 
6 | 400kV Sec 1 :- Main Bus ( Outside Building) BHEL TO C Building | RM | 439 | 439 | 439 | - | 439 | 0 |  | May | 
7 | 400kV Sec 2 :- GIB ( Outside Building) B Buliding | RM | 884 | 884 | 884 |  | 884 | 0 |  | May | 
8 | 400kV Sec 2 :- GIB ( Inside Building) | RM | 81 | 81 | 81 | 0 | 81 | 0 |  | May | 
9 | 400kV Sec 2 :- Main Bus ( Outside Building) BHEL to B Building | RM | 451 | 451 | 451 | 0 | 451 | 0 |  | May | 
10 | 400kV Sec 1 C :Cable Laying & Termination:- C building | Runs | 695 | 695 | 695 | 400 | 295 | 58 |  | May | 

## Slide 27: 765/400 kV KPS-2 Ext 39T (SA-503)
LOA Date: July’24 | LOA Completion Sch: March’26 | Target Comp Date: 400 kV : June/765kV :July | Project Value: 390 Crs.
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
1 | 765kV GIS-A Bay Erection | Nos | 4 | 4 | 4 | 0 | 4 | 0 |  | June’26 | To be Commence from 15th may
2 | 765kV GIS-D Bay Erection | Nos. | 4 | 4 | 4 | 0 | 4 | 0 |  |  | 
3 | 765kV Sec 2 A :- GIB ( Outside Building) | RM | 190 | 190 | 190 | 0 | 190 | 0 |  |  | 
4 | 765kV Sec 2 A :- GIB Length ( Inside Building) | RM | 40 | 40 | 40 | 0 | 40 | 0 |  |  | 
5 | 765kV Sec 1 D :- GIB ( Outside Building) D Buliding To Adani Building | RM | 825 | 825 | 825 | 0 | 825 | 0 |  |  | 
6 | 765kV Sec 1 D :- GIB ( Inside Building) | RM | 84 | 84 | 84 | 0 | 84 | 0 |  |  | 

## Slide 28: SS33T 765kV GIS Vadodara Extn S/S (SA5V8)
LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: 25-10-2026 | Project Value: 198.93cr
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t L2 | %Age w.r.t L2 | Target Completion | Remarks
A | Supply |  |  |  |  |  |  |  |  | 
1 | Foundation Bolts | Nos | 796 | 796 | 796 | 796 | 0 | 100% |  | 
2 | Tower & Equipment structure | MT | 200.3 | 167 | 167 | 156.8 | 10.2 | 94% | Jun'26 | KEC (Balance -NCT-2 Nos , 765kV LA- 4 Nos)
3 | Earthing Materials | Lot | 100 | 100 | 100 | 65 | 35 | 65% | May'26 | 40mm MS Rod Received, Misc Earthing material required (GI Flat, MS Earthing)
4 | PEB Structure & Puff panels | Lot | 100 | 100 | 100 | 0 | 100 | 0% | May to Jun'26 | PEB: Kirby Building syatems (270MT) Puff Panel: Jindal
5 | EOT Crane | Set | 1 | 1 | 1 | 1 | 0 | 100% |  | Reva
6 | GIS Equipments - Indoor | Set | 29 | 29 | 29 | 29 | 0 | 100% |  | Hyosung
7 | GIS Equipments & GIB | RM | 2000 | 1526 | 1526 | 1526 | 0 | 100% | May'26 | Outdoor GIS Support Structure Supply Expected by May'26
8 | 765kV Outdoor Equipments | Nos | 34 | 34 | 34 | 12 | 22 | 35% | May'26 | CVT - 6nos - GE vernova BPI - Moder Company - 28set
9 | 145/36kV Outdoor Equipments | Nos | 62 | 62 | 62 | 2 | 60 | 3% | Jun’26 | BPI - 145kV - Moder Company - 60nos BPI Pending
10 | Erectiopn Hardware | Set | 35 | 35 | 35 | 30 | 5 | 86% | Jun'26 | Vensun - Clamps & Connector - Drawing approval pending
11 | CRP & SAS | EA | 25 | 25 | 25 | 0 | 25 | 0% | Jul'26 | Compliance WIP
12 | PMU, PLCC, Telecom & VMS | Lot | 100 | 100 | 100 | 50 | 50 | 50% | May'26 | PLCC receievd, Commtel (telecom) & Delcom (VMS), GE vernova (PMU) pending to supply
13 | Power & Control Cable | KM | 54 | 54 | 54 | 0 | 54 | 0% | Jul'26 | KEC - (Power & Control Cable schedule approval pending)
14 | HVAC System | Lot | 1 | 1 | 1 | 1 | 0 | 100% |  | 
15 | Fire Fighting system | Lot | 100 | 100 | 100 | 100 | 0 | 100% |  | 
16 | Illumination System | Lot | 100 | 100 | 100 | 60 | 40 | 60% | May'26 | Insta Power - 50% received at site

## Slide 29: SS33T 765kV GIS Vadodara Extn S/S (SA5V8)
LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: 25-10-2026 | Project Value: 198.93cr
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
1 | Contouring and land development | Cum | 48500 | 46000 | 46000 | 42000 | 4000 | 91% | WIP | 10-05-2026 | 
2 | 765kV Towers | Nos. | 8 | 8 | 8 | 8 | 0 | 100% |  |  | 
3 | 765kV Equipment | Nos. | 35 | 35 | 35 | 35 | 0 | 100% |  |  | 
4 | 145kV Equipments | Nos. | 53 | 53 | 53 | 44 | 9 | 83% | WIP | 10-05-2026 | 
5 | Reactor Foundation | Nos. | 6 | 6 | 6 | 6 | 0 | 100% |  |  | 
6 | Firewall | Nos. | 6 | 6 | 6 | 3 | 3 | 50% | WIP | 30-05-2026 | Precast Panel wip
7 | 765kV GIS Building including PEB erection | Lot | 100 | 100 | 100 | 20 | 80 | 20% | WIP | 10-08-2026 | 
8 | Bus Duct Foundation | Nos | 139 | 139 | 139 | 0 | 139 | 0% | WIP | 30-06-2026 | Drawing submitted approval awaited
9 | Cable Trench | RM | 90 | 485 | 485 | 0 | 485 | 0% | WIP | 10-07-2026 | 
10 | Drain, Road and Other misc civil works | % | 100 | 100 | 60 | 0 | 100 | 0% |  | 30-09-2026 | 
11 | Tower and Equipment structure | Nos | 96 | 96 | 96 | 0 | 96 | 0% | WIP | 30-05-2026 | 
12 | Outdoor Equipment | Nos | 88 | 88 | 88 | 0 | 88 | 0% | WIP | 30-06-2026 | 
13 | Earthing works | % | 100 | 100 | 50 | 0 | 100 | 0% | WIP | 30-07-2026 | 
14 | Illumination system | % | 100 | 100 | 50 | 0 | 100 | 0% |  | 20-08-2026 | 
15 | HVAC System | % | 100 | 100 | 100 | 0 | 100 | 0% |  | 10-08-2026 | 
16 | GIS Equipments and GIB Erection | % | 100 | 100 | 60 | 0 | 100 | 0% |  | 30-09-2026 | 
17 | Cable Laying & Termination | KM | 55 | 55 | 25 | 0 | 55 | 0% |  | 10-10-2026 | 
18 | Fire Protection Syatem | % | 100 | 100 | 30 | 0 | 100 | 0% |  | 15-10-2026 | 
19 | CRP & SAS Erection incl. Integration | % | 100 | 100 | 25 | 0 | 100 | 0% |  | 15-10-2026 | 
20 | PLCC, PMU, Telecom and VMS | % | 100 | 100 | 5 | 0 | 100 | 0% |  | 20-10-2026 | 
21 | Indoor & Outdoor Equipment Testing | % | 100 | 100 | 0 | 0 | 100 | #DIV/0! |  | 20-10-2026 | 
22 | Testing & Commissioning | % | 100 | 100 | 0 | 0 | 100 | #DIV/0! |  | 25-10-2026 | 

## Slide 30: SS33T 765kV GIS Vadodara Extn S/S (SA5V8)
LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: 25-10-2026 | Project Value: 198.93cr
Issues / Support Required
The erection of the 80 MVAR reactor by PGCIL is still pending
Clamps and connector drawings are yet to be approved

## Slide 31: SS33T 765kV GIS South Olpad (SA-508)
LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: Depend on Land | Project Value: 370.1cr
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t L2 | %Age w.r.t L2 | Target Completion | Remarks
A | Supply |  |  |  |  |  |  |  |  | 
1 | Foundation Bolts | Nos | 1648 | 1648 | 1648 | 1648 | 0 | 100% |  | 145kV Eqp Drawing required for further order process
2 | Tower & Equipment structure | MT | 732 | 732 | 732 | 36 | 696 | 5% | Jul'26 | KEC - Order placed
3 | Earthing Materials | Lot | 100 | 100 | 100 | 0 | 100 | 0% |  | Order Placed
4 | PEB Structure & Puff panels | Lot | 100 | 100 | 100 | 0 | 100 | 0% |  | 
5 | EOT Crane | Set | 1 | 1 | 1 | 1 | 0 | 100% |  | 
6 | GIS Equipments - Indoor | Set | 14 | 14 | 14 | 14 | 0 | 100% |  | 
6 | GIS Equipments - SF6 Air Bhusing | Nos | 33 | 33 | 33 |  | 33 | 0% | May'26 | Hyosung
7 | GIS Equipments & GIB | RM | 2400 | 1947.96 | 1947.6 |  | 1947.6 | 0% | Jul'26 | Hyosung - GIB & structure supply
8 | 765kV Outdoor Equipments | Nos | 88 | 88 | 88 | 41 | 47 | 47% | Jun'26 | CVT - GE, BPI - Modern
9 | 145/36kV Outdoor Equipments | Nos | 29 | 29 | 29 | 8 | 21 | 28% | Jun'26 | Order placed
10 | Erectiopn Hardware | Lot | 100 | 100 | 100 | 0 | 100 | 0% |  | Drawing approval pending
11 | CRP & SAS | EA | 40 | 40 | 40 | 0 | 40 | 0% | Aug'26 | GE Vernova
12 | PMU, PLCC, Telecom & VMS | Lot | 100 | 100 | 100 | 60 | 40 | 60% | Jun'26 | VMS-Delcom, telecom- Commtel, PMU-GE
13 | LT Transformer | Nos | 2 | 2 | 2 | 2 | 0 | 100% |  | 
14 | LT Switchgear | Lot | 1 | 1 | 1 |  | 1 | 0% | Aug'26 | Ultima
15 | Battery & Charger and DG set | EA | 5 | 5 | 5 | 1 | 4 | 20% | Aug'26 | DG set received at site, Battary & charger - Exide
16 | Power & Control Cable | KM | 65 | 65 | 65 | 0 | 65 | 0% | Drawing approval pending | KEC
17 | Air conditioning & HVAC System | Lot | 100 | 100 | 100 | 100 | 0 | 100% |  | 
18 | Fire Fighting system | Lot | 100 | 100 | 100 | 0 | 100 | 0% | May'26 | BCFSL
19 | Illumination System | Lot | 100 | 100 | 100 | 60 | 40 | 60% | May'26 | Avaids

## Slide 32: SS33T 765kV GIS South Olpad (SA-508)
LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: Depend on Land | Project Value: 370.1cr
Issues / Support Required
Finalization of spare supply contract through PESL for South OLPAD Project. NOA from PGCIL was issued on 26/11/24 for South OLPAD-23 Cr

## Slide 33: SS64T 765kV GIS Narendra Extn (SA-603)
LOA Date: 26.05.2025 | LOA Completion Sch: 12-04-27 | Target Comp Date: 31-12-26 | Project Value: 105.65 cr
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t L2 | %Age w.r.t L2 | Target Completion | Remarks
A | Supply |  |  |  |  |  |  |  |  | 
1 | 765kV equipment | EA | 81 | 81 | 81 | 81 | 18 | 87% | Sep’26 | BPI, WT, LA delivered, CVT under manufacturing
2 | 145/36kV equipment | EA | 8 | 8 | 8 |  | 8 | 50% | Sep’'26 | 145kV BPI , NCT , CB under manufacturing
3 | 800kV, 3000/3150 A, 50kA, Single phase, SF6 Gas Insulated Bus Duct (GIB | M | 2150 | 1894 | 2150 |  | 0 | 100% | May’26 | Inspection call is expected by mid May. BBU approval is pending.
4 | Structure | MT | 112 | 201 | 112 |  | 201 | 100% | Aug’26 | Under production, Lot 1 Inspection call by 32 May.
5 | Earthing Materials | KM | 2 | 2 | 2 | 2 | 0 | 100% |  | Delivered to site
6 | Erection Hardware | Lot | 1 | 1 | 1 | 1 | 0.5 | 50% | July’'26 | BBU approval pending , partial material delivered , Clamps & connectors are under manufacturing
7 | Power & Control Cable | KM | 54 | 54 | 54 | 0 |  | 0% | Sep’26 | Power cable is under approval
8 | CRP & SAS | EA | 4 | 4 | 4 | 0 | 4 | 0% | May'26 | Inspection call is expected by mid May.
9 | Fire Fighting System | Lot | 1 | 1 | 1 | 1 | 0 | 100% | April’26 | delivered to site
10 | Illumination System | Lot | 1 | 1 | 1 | 1 | 0 | 100% | April’26 | delivered to site
11 | VMS | Lot | 1 | 1 | 1 | 1 | 0 | 100% | April’26 | delivered to site

## Slide 34: SS64T 765kV GIS Narendra Extn (SA-603)
LOA Date: 26.05.2025 | LOA Completion Sch: 12-04-27 | Target Comp Date: 31-12-26 | Project Value: 105.65 cr
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
1 | 765kV Tower Foundation | Nos | 8 | 8 | 30-04-2026 | 8 | 0 | 100% |  |  | Completed
2 | Reactor Foundation | Nos | 7 | 7 | 31-05-2026 | 6 | 1 | 86% |  | On Hold by PGCIL | 
3 | Reactor Unloading Platform | Nos | 7 | 7 | 31-05-2026 | 6 | 1 | 86% |  | On Hold by PGCIL | 
4 | Rail Cum road | Nos | 7 | 7 | 31-05-2026 | 0 | 7 | 0% | 8 | May'26 | 
5 | Firewall | Nos | 6 | 6 | 31-05-2026 | 0 | 6 | 0% | 8 | May'26 | 
6 | AIS Equipment Foundations | Nos | 70 | 70 | 30-04-2026 | 3 | 67 | 4% | 15 | May'26 | 
7 | GIB Bus Duct | Nos | 130 | 130 | 30-04-2026 | 0 | 130 | 0% | 15 | May'26 | 
8 | LM Tower | Nos | 1 | 1 | 30-04-2026 | 0 | 1 | 0% |  | June'26 | 
9 | Cable trench | Mtrs | 240 | 240 | 30-05-2026 | 80 | 160 | 33% |  | July'26 | 
10 | Common Oil Pit | Nos | 1 | 1 | 28-04-2027 | 0 | 1 | 0% |  | June'26 | 
11 | Drain & Road | Nos | 1 | 1 | 28-04-2027 |  | 1 | 0% |  | Aug'26 | 

## Slide 35: 765KV Bay Extension GIS Sub-Station Narela
LOA Date: 22.02.2024 | LOA Completion Sch: 21-05-2025 | Target Comp Date: 30-06-2026 | Project Value: 124.30 cr
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t L2 | %Age w.r.t L2 | Target Completion | Remarks
A | Supply |  |  |  |  |  |  |  |  | 
1 | GIS Bay Module | Set | 5 | 5 | 5 | 5 | 0 | 100% | Sep’25 | Completed
2 | GIS Bus Duct | M | 1600 | 1600 | 1600 | 1600 | 0 | 100% | Sep’’25 | Completed
3 | Power & Control cables | Km | 12.8 | 12.8 | 12.8 |  |  |  | May’25 | 8 Pair cables inspection call is for 15.5.26
4 | 765KV OD Equipment | Nos | 33 | 33 | 33 | 22 | 11 | 90% | Aug’25 | Completed
5 | 145KV OD Equipment | Nos | 34 | 34 | 34 | 32 | 2 | 98% |  | Completed
6 | Puff Panel | Sq.m | 2650 | 2250 | 2250 | 2250 | 0 | 100% | July’25 | Completed
7 | Erection Hardware | Lot | 1 | 1 | 1 | 1 | 0 |  | Sep’25 | Completed
8 | VMS | Set | 1 | 1 | 1 | 1 | 0 |  | May’25 | Completed
9 | PMU | Nos |  | 2 | 2 | 2 | 0 |  | April’25 | Completed
10 | Control Cable | Km | 15 | 15 | 15 | 11 | 4 | 96% | April’25 | 14C x 2.5 & 2C x 2.5 Cables are still balanced
11 | Power Cable | Km | 12.33 | 12.33 | 12.33 | 1 | 11.33 | 10% | April’25 | Completed

## Slide 36: 765KV Bay Extension GIS Sub-Station Narela
LOA Date: 22.02.2024 | LOA Completion Sch: 21-05-2025 | Target Comp Date: 30-06-2026 | Project Value: 124.30 cr
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
1 | Earth mat + Riser | Km | 5.7 | 5.7 | 5.7 | 4.847 | 0.853 | 92% |  | Jun'26 | WIP
2 | 765KV Equipment Erection | Nos | 33 | 33 | 33 | 22 | 11 | 88% |  | Jun'26 | WIP
3 | 145KV Equipment Erection | Nos | 36 | 36 | 36 | 32 | 4 | 96% |  | Jun'26 | WIP
4 | GIB Erection | mtrs | 1600 | 1600 | 1600 | 1573.79 | 26.21 | 91% |  | Jun'26 | WIP
5 | Power & Control Cable Laying | % | 100% | 100% | 100% | 60% | 40% | 85% |  | May'26 | WIP
6 | Testing and comissioning | Lot | 1 | 1 | 1 | 40% | 60% | 40% |  | Jun'26 | WIP
7 | Busduct Structure Erection | Nos | 181 | 181 | 181 | 181 | 0 | 100% |  |  | Completed
8 | Indoor GIS Bays | Bays | 5 | 5 | 5 | 5 | 5 | 100% |  |  | Completed
9 | Yard Levelling | M2 | 7000 | 7000 | 7000 | 4825 | 2175 | 65% |  | Jun'26 | WIP
10 | PEB Erection | Lot | 1 | 1 | 1 | 1 | 0 | 100% |  |  | Completed
11 | Outdoor Cable trench | RM | 214.75 | 214.75 | 214.75 | 214.75 | 0 | 100% |  |  | Completed

## Slide 37: SS33T 765kV AIS Ahmedabad Extn (SA-5A8)
LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: 30-09-2026 | Project Value: 61.27cr
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t L2 | %Age w.r.t L2 | Target Completion | Remarks
A | Supply |  |  |  |  |  |  |  |  | 
1 | 765kV equipment | EA | 45 | 45 | 45 | 39 | 6 | 87% | May'26 | CVT order placed to GE
2 | 145/36kV equipment | EA | 8 | 8 | 8 | 2 | 6 | 25% | Jun'26 | 145kV BPI , NCT - Order placed to Modern complany & SCT
3 | Foundation Bolt | Nos. | 2560 | 2560 | 2560 | 2560 | 0 | 100% |  | 
4 | Structure | MT | 536 | 601 | 601 | 596.55 | 4.45 | 99% | May'26 | KEC
5 | Earthing Materials | KM | 4 | 3.25 | 3.25 | 3.25 | 0 | 100% |  | 
6 | Erection Hardware | Lot | 1 | 0.57 | 1 | 0.57 | 0.43 | 57% | Jun'26 | Vensun
7 | Isolator | EA | 26 | 28 | 28 | 28 | 0 | 100% |  | 
9 | Insulator | EA | 216 | 216 | 216 | 60 | 156 | 28% | Jun'26 | Modern Equipments
10 | Power & Control Cable | KM | 87.6 | 68 | 68 | 0 | 68 | 0% | May'26 to Jun'26 | KEC
11 | CRP & SAS | EA | 18 | 18 | 18 | 0 | 18 | 0% | May'26 | 
12 | Wave Trap | EA | 4 | 4 | 4 | 4 | 0 | 100% |  | 
13 | FOTE | Lot | 1 | 1 | 1 | 1 | 0 | 100% |  | 
14 | Fire Fighting System | Lot | 1 | 1 | 1 | 1 | 0 | 100% |  | 
15 | AC System | Lot | 1 | 1 | 1 | 1 | 0 | 100% |  | 
16 | Illumination System | Lot | 1 | 1 | 1 | 0.8 | 0.2 | 80% | May'26 | Avaids / Forus
18 | VMS | Lot | 1 | 1 | 1 | 0 | 1 | 0% | May'26 | Delcom

## Slide 38: SS33T 765kV AIS Ahmedabad Extn (SA-5A8)
LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: 30-09-2026 | Project Value: 61.27cr
Sl. No. | Particulars | UOM | Qty as per LOA | Qtys as per Actual | As per L2 Schedule up as on date | Completed as on date | Balance w.r.t Actual | %Age w.r.t L2 | Gang Available | Target Completion | Remarks
1 | Soil filling | Cum | 45000 | 41000 | 41000 | 38000 | 3000 | 93% | WIP | 10-05-2026 | 
2 | 765kV Towers | Nos. | 20 | 20 | 20 | 20 | 0 | 100% |  |  | 
3 | 765kV Equipment | Nos. | 216 | 216 | 216 | 216 | 0 | 100% |  |  | 
4 | 145kV Equipments | Nos. | 36 | 36 | 36 | 36 | 0 | 100% |  |  | 
5 | Reactor Foundation | Nos. | 6 | 6 | 6 | 6 | 0 | 100% |  |  | 
6 | Firewall | Nos. | 4 | 4 | 4 | 4 | 0 | 100% |  |  | 
7 | SPR Complete | Nos. | 1 | 1 | 1 | 0.85 | 0.15 | 85% | Finishing wip | 10-05-2026 | 
8 | Cable Trench | mtr | 1700 | 700 | 700 | 600 | 100 | 86% | WIP | 15-05-2026 | 
9 | Drains, Road | % | 100 | 100 | 100 | 25 | 75 | 25% | WIP | 30-06-2026 | 
10 | Misc Work (Earth Pit, Pull Pit,Yard PCC, Gravel Spreading, Fencing , etc) | % | 100 | 100 | 100 | 10 | 90 | 10% | WIP | 25-06-2026 | 
11 | 145kV Erection Erection | % | 100 | 100 | 100 | 85 | 15 | 85% | WIP | 20-05-2026 | 
12 | 765kV Outdoor Equipment | % | 100 | 100 | 100 | 35 | 65 | 35% | WIP | 15-06-2026 | 
13 | Illumination system | % | 100 | 100 | 50 | 50 | 50 | 100% | WIP | 30-05-2026 | 
14 | Fire Protection system | % | 100 | 100 | 28 | 0 | 100 | 0% |  | 30-06-2026 | 
15 | Cable Laying & Termination | % | 100 | 100 | 50 | 0 | 100 | 0% |  | 10-07-2026 | 
16 | CRP & SAS Erection incl. Integration | % | 100 | 100 | 10 | 0 | 100 | 0% |  | 15-07-2026 | 
17 | PLCC, PMC, Telecom & VMS | % | 100 | 100 | 0 | 0 | 100 | #DIV/0! |  | 15-07-2026 | 
18 | Testing & Commissioning | % | 100 | 100 | 0 | 0 | 100 | #DIV/0! |  | 31-07-2026 | 

## Slide 39: SS33T 765kV AIS Ahmedabad Extn (SA-5A8)
LOA Date: 26.11.2024 | LOA Completion Sch: 25-10-2026 | Target Comp Date: 30-09-2026 | Project Value: 61.27cr
Issues / Support Required
The erection of the 80 MVAR reactor by PGCIL needs to be completed
Clamps and connector drawings are yet to be approved

## Slide 40: North Western Region

## Slide 41: TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413)
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  |  | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act | Act |  |  | 
Check Survey | Km | 112.611 | 117.851 |  | 117.851 | 0 |  |  |  |  |  |  |  |  |  | 
Foundation | No | 287 | 316 |  | 316 | 0 |  |  | 0 |  | 0 |  |  |  |  | 
Erection | No | 287 | 306 |  | 302 | 4 |  |  | 1 | 1 | 1 |  |  | 3 |  | 
Stringing | Km | 112.611 | 117.851 |  | 74.641 | 43.21 |  | 2 | 18 | 18 | 18 | 3 | 3 | 20 | 11 | 
OPGW Stringing | Km | 112.611 | 117.851 |  | 59.762 | 58.089 |  |  |  |  | 25 | 10 | 10 | 20 | 28 | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  | Remarks |  |  |  | 
Stub | Nos | 287 | 316 | 287 | 316 | 0 |  |  |  |  |  |  |  |  |  | 
Tower | Nos | 287 | 306 | 287 | 306 | 0 |  |  |  |  |  |  |  |  |  | 
Conductor | Km | 4095 | 4285.056 | 4095 | 4285.056 | 0 |  |  |  |  |  |  |  |  |  | 
Earthwire | Km | 114 | 121.471 | 1 | 121.471 | 0 |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos | 5968 | 6084 |  | 6084 | 0 |  |  |  |  |  |  |  |  |  | 
210KN CLR | Nos | 4512 | 5760 |  | 5760 | 0 |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 42: TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413)
No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stubs Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stub Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Erection | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stringing | As per L2 | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | TSE (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Manual (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply as per L2 | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply Actual | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 43: TL01 - 765KV D/C Bikaner III - Neemrana II (TA- 413)
Issues / Support Required
Amendment is pending since Jan’26
Frequent disruption to Stringing work due to ROW
LOA DATE: 12/03/24 | LOA Value in Cr.:-390 Cr. | CONTRACTUAL COMPLETION: 11/12/25 | PLANNED COMPLETION: 30/07/26

## Slide 44: TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512)
LOA DATE: 03/01/2025 |  | CONTRACTUAL COMPLETION: 02/12/26 | 
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (Up to 01.05.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 | Plan May 26 |  | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  |  | Plan | Plan | Act | Act |  |  | 
Check Survey | Km |  | 120.944 |  | 124.568 | 0 | 124.568 |  |  | 124.568 |  | 124.568 |  |  |  |  | 
Foundation | No |  | 315 |  | 303 | 18 | 303 |  | 2 | 272 | 17 | 272 | 0 | 0 | 1 |  | 
Erection | No |  | 315 |  | 217 | 105 | 217 |  | 2 | 210 | 45 | 210 | 1 | 1 | 40 | 20 | 
Stringing | Km |  | 120.944 |  | 0 | 124.6 | 0 |  | 0 |  |  | 60 |  |  | 15.7 | 19.9 | 
OPGW Stringing | Km |  | 120.944 |  |  | 124.6 | 0 |  | 0 |  |  | 10 |  |  |  |  | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  |  | Remarks |  |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos | 6316 |  |  |  | 6316 |  |  |  |  |  |  | Insulator being delayed due to delay in Design/Type Testing |  |  |  | 
210KN CLR | Nos | 5856 |  |  |  | 5856 |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 45: TL02 - 765KV D/C Bikaner – IV To Siwani (2nd) Tr. Line (Part – 1) (TA- 512)
Issues / Support Required
1. Amendment of BOQ has been pending since 20/02/2026
2. Supply of 48F OPGW cable are delayed due to non-finalization of repeater station locations
3. Foundation work at 8 locations is delayed due to pending statutory clearances (NH – 2 Nos. and PLC – 1 No.)
4. Commencement of tower erection at 37 locations is delayed due to non-disbursement of compensation for completed foundation work
LOA DATE: 03/01/25 | LOA Value in Cr.: 475.26 (Excluding GST) | CONTRACTUAL COMPLETION: 02/12/26 | PLANNED COMPLETION: 02/12/26

## Slide 46: TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504)
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  |  | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act | Act |  |  | 
Check Survey | Km |  | 70 |  | 67 | 3 |  |  | 2 |  | 2 |  |  |  |  | 
Foundation | No |  | 188 |  | 142 | 49 |  | 3 |  | 25 | 29 | 2 | 2 | 25 | 20 | 
Erection | No |  | 188 |  | 121 | 67 |  | 4 |  | 28 | 17 |  |  | 15 | 15 | 
Stringing | Km |  | 69 |  | 13.422 | 55.578 |  | 2 |  | 13 | 14 |  | 3 | 15 | 21 | 
OPGW Stringing | Km |  | 70 |  | 0 | 70 |  | 1 |  | 20 |  |  |  | 20 | 30 | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Insulator | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 47: TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504)
No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stubs Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stub Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Erection | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stringing | As per L2 | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | TSE (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Manual (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply as per L2 | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply Actual | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply as per L2 | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply Actual | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 48: TL01 - 765kV D/C Rishabdeo Mandsaur Transmission Line & Lilo (TA- 504)
Issues / Support Required
1. No work front for foundation works, 21 locations hold due to crossings
2. Required to expedite the ROW (Erection-10/3, 26/9, 5H/0, 5G/5, 4/1 Foundation- 10/4, 5G/2, 5G/3, 5H/1 Stringing:12/0 - 13/0, 14/0 - 15/0)
3. Amendment submitted on 23rd April and issuance pending
4. Need to Expedite Tower Erection ULE structural drawings 28/1(DB1+0, -1.5M ULE) & 31/2 (DB1+6, -1.5M ULE)
5. NH crossing –02 no's approval pending needs to expedite
LOA DATE: 23/07/24 | LOA Value in Cr.: 477.03 | CONTRACTUAL COMPLETION: 22/06/26 | PLANNED COMPLETION: 28/09/26

## Slide 49: TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505)
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act |  |  | 
Check Survey | Km |  | 139.6 |  |  | 0 |  |  |  |  |  |  |  |  | 
Foundation | No |  | 379 |  | 374 | 7 |  | 2 |  | 7 | 7 |  |  |  | 
Erection | No |  | 379 |  | 354 | 32 |  | 5 |  | 14 | 14 | 4 | 5 | 13 | 
Stringing | Km |  | 139.6 |  | 14.973 | 125.594 |  | 2 |  | 23 | 23 |  | 25 | 30 | 
OPGW Stringing | Km |  |  |  |  |  |  | 1 |  |  |  |  |  |  | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
210KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 50: TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505)
No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stubs Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stub Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Erection | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stringing | As per L2 | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | TSE (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Manual (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply as per L2 | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply Actual | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 51: TL01 - 765KV D/C Beawar-Mandsaur TL (TA- 505)
Issues / Support Required
Shutdown Bypass Cable Arrangement: Required cables for shutdown bypass arrangement need to be arranged at the earliest to avoid stoppages during execution
LOA DATE: 22.07.2024 | LOA Value in Cr.: 560 Cr | CONTRACTUAL COMPLETION: 21.06.2026 | PLANNED COMPLETION: 30.09.26

## Slide 52: TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506)
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  |  | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act | Act |  |  | 
Check Survey | Km |  | 223 |  | 223 | 0 |  |  |  |  |  |  |  |  |  | 
Foundation | No |  | 602 |  | 485 | 123 |  | 12 |  | 40 | 40 |  | 9 | 30 | 30 | 
Erection | No |  | 602 |  | 401 | 202 |  | 2 |  | 46 | 46 |  |  | 35 | 35 | 
Stringing | Km |  | 223 |  | 53.725 | 179.432 |  | 4 |  | 39 | 38 |  | 13 | 30 | 40 | 
OPGW Stringing | Km |  | 231 |  |  |  |  |  |  |  |  |  |  | 30 | 40 | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Insulator | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 53: TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506)
No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stubs Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stub Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Erection | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stringing | As per L2 | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | TSE (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Manual (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply as per L2 | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply Actual | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 54: TL01 - 400 KV D/C Sirohi - Chittorgarh TL (TA- 506)
Issues / Support Required
1. Need to expedite clearance of ROW/HOLD locations (Forest HOLD-15 Udaipur Region Nos, Statutory clearences-21, ROW-28, Route change HOLD-4) due to this 21KM affected
2. Required RC/ULE 17 nos affecting 25 locations
3. Design of Strengthening X-Arm locations required (4 out of 15) – details shared with Engg. Dept
4. NH Crossings-08 Nos approval still pending
LOA DATE: 08/04/25 | LOA Value in Cr.: 592 | CONTRACTUAL COMPLETION: Aug’26 | PLANNED COMPLETION: Oct’26

## Slide 55: Northern Region(NR-I)

## Slide 56: TL02 - 765KV D/C Sikar II – Narela (TA- 419)
LOA DATE: 06/02/2024 |  | CONTRACTUAL COMPLETION: 05/05/2025 | 
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act |  |  | 
Check Survey | Km | 120.21 | 122.071 |  | 1 | 121.071 |  |  |  |  |  |  |  |  | 
Foundation | No | 322 | 330 |  | 249 | 81 |  | 13 | 45 | 35 | 45 | 3 | 35 | 24 | 
Erection | No | 322 | 330 |  | 203 | 127 |  | 7 | 40 | 30 | 40 | 1 | 40 | 40 | 
Stringing | Km | 120.21 | 122.071 |  |  | 122.071 |  | 1 |  | 13 |  |  | 15 | 20 | 
OPGW Stringing | Km | 120.21 | 122.071 |  | 0 | 122.071 |  |  |  |  |  |  |  |  | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  | Remarks |  |  | 
Stub | Nos |  | 330 | 322 | 328 | 2 |  |  |  |  |  |  |  |  | 
Tower | Nos |  | 330 | 322 | 325 | 5 |  |  |  |  |  | HORCL Approval Pending(Tower Type may change) |  |  | 
Conductor | Km |  | 4432 | 4370 | 4369 | 63 |  |  |  |  |  |  |  |  | 
Earthwire | Km |  | 122 | 120.6 | 120.75 |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
210KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 57: TL02 - 765KV D/C Sikar II – Narela (TA- 419)
LOA DATE: 06/02/2024 |  | CONTRACTUAL COMPLETION: 05/05/2025 | 
No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stubs Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stub Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Erection | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stringing | As per L2 | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | TSE (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Manual (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply as per L2 | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply Actual | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 58: TL02 - 765KV D/C Sikar II – Narela (TA- 419)
Issues / Support Required
1. Clearance of balance foundation locations for taking up works
2. Severe ROW continues to affect opening of fronts in Talao and Charra villages affecting 11 locations
3. Locations are progressively being made clear of ROW and put to work. For water submerged locations approval of shallow design is critical
4. HORCL Approval is still pending affecting release of 6 Towers
5. Clearance of Stringing stretch
  Stringable sections totaling 18 Kms. in Mahendargarh District is ready which is free from any rectification
  The Stringing gang has already been remobilized post idling since Jan-2026 due to ROW issues on account of pending MRC in Mahendragarh & Rewari
  The Pilot pulling started on 20th April for 1st section of B/0 to C/0 however it was stopped due to ROW
  MRC of Mahendragarh is disputed & for Rewari it is still pending, stringing Workfront is restricted 1 gang & 2 TSEs are idling
LOA DATE: 06/02/2024 | LOA Value in Cr.: 501 | CONTRACTUAL COMPLETION: 05/05/2025 | PLANNED COMPLETION: 30/11/26

## Slide 59: Northern Region (NR-II)

## Slide 60: 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513)
 |  | CONTRACTUAL COMPLETION: 22.12.26 | 
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  |  | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act | Act |  |  | 
Check Survey | Km | 144.2 | 147.584 |  | 147.575 | 0.009 |  | 0 | 144.2 | 0 | 144.2 | 0 |  |  |  | 
Foundation | No | 387 | 399 |  | 59 | 340 |  | 4 | 350 | 20 | 350 | 3 | 3 | 50 | 20 | 
Erection | No | 387 | 399 |  | 22 | 377 |  | 1 | 310 | 9 | 310 | 0 |  | 28 | 55 | 
Stringing | Km | 144.2 | 147.584 |  |  | 147.584 |  | 0 | 100 | 0 | 100 | 0 |  |  |  | 
OPGW Stringing | Km | 144.2 | 147.69 |  |  | 147.69 |  | 0 | 35 | 0 | 35 | 0 |  |  |  | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  | Remarks |  |  |  | 
Stub | Nos |  |  | 597 |  | 106 |  |  |  |  |  | 42 Nos supply pending to C.Survey & 38 Nos Pending due to crossing NOC , Rest Supply under progress |  |  |  | 
Tower | Nos |  |  | 490 |  | 146 |  |  |  |  |  |  |  |  |  | 
Conductor | Km |  |  | 3800 |  | 519 |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  | 161 |  | 69 |  |  |  |  |  |  |  |  |  | 
120KN CLR | Nos | 5424 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos |  |  | 8000 |  | 5772 |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 61: 400 KV Siwani-Fatehabad TL & Siwani-Patran TL (TA- 513)
Issues / Support Required
1. Market Rate Compensation (MRC) is still pending for finalization
2. Work front availability
3. Approval of the OPGW drum schedule is still pending due to which supply activities could not be initiated. The same was submitted to PGCIL on 10.03.2026
LOA DATE: 22.01.2025 | LOA Value in Cr.: 666 | CONTRACTUAL COMPLETION: 22.12.26 | PLANNED COMPLETION:

## Slide 62: Northern Region (NR-III)

## Slide 63: TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416)
LOA DATE: 07/02/2024 |  | CONTRACTUAL COMPLETION: 06/11/2025 | 
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (Up to 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  |  | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act | Act |  |  | 
Check Survey | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | No |  | 302 |  | 302 | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 
Erection | No |  | 302 |  | 302 | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 
Stringing | Km |  | 115.134 |  | 110.774 | 4.36 |  | 2 | 8.4 | 8 | 8.4 |  |  |  |  | 
OPGW Stringing | Km |  |  |  |  |  |  | 1 |  | 28 |  | 5 | 5 |  |  | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  | Remarks |  |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Insulator | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 64: TL03 - 765 KV D/C Neemrana II Bareilly Line (TA- 416)
LOA DATE: 07/02/2024 |  | CONTRACTUAL COMPLETION: 06/11/2025 | 
No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stubs Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stub Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Erection | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stringing | As per L2 | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | TSE (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Manual (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply Actual | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply as per L2 | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply Actual | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 65: Southern Region (SR-I)

## Slide 66: TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418)
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May’ 26 | Plan May’ 26 |  | Plan Jun’26 | Plan Jul’26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act |  |  | 
Check Survey | Km |  |  |  |  |  |  | 0 |  | 0 |  |  |  |  | 
Foundation | No |  | 127 |  | 127 | 0 | 0.0 | 0 | 0 | 0 | 0 |  |  |  | 
Erection | No |  | 127 |  | 127 | 0 | 0.0 | 0 | 0 | 0 | 0 |  |  |  | 
Stringing | Km |  | 47.84 |  | 27.705 | 20.135 |  | 1 | 11.89 | 11.9 | 11.89 | 3.9 | 13.27 | - | 
OPGW Stringing | Km |  |  |  |  |  |  | 0 |  | 10 |  | - | 18.81 | - | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  | Remarks |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
210KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 
LOA DATE: 12/03/24 |  | CONTRACTUAL COMPLETION: 11/12/25 | 

## Slide 67: TL01 - 765kV D/C Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418)
No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balnce As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stubs Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stub Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Erection | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stringing | As per L2 | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | TSE (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Manual (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply as per L2 | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply Actual | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LOA DATE: 12/03/24 |  | CONTRACTUAL COMPLETION: 11/12/25 | 

## Slide 68: TL01 - 765kV D/c Koppal II (PS)-Raichur (Part-1) TL Line (TA- 418)
Issues / Support Required
1. Clearance for final checking ROW 4 locations. ROW constraints affecting tack welding activities in 13 Locations
2. Approval of the submitted Amendment–04, pending from 7th Feb’26
LOA DATE: 12/03/24 | LOA Value in Cr.:148.6 | CONTRACTUAL COMPLETION: 11/12/25 | PLANNED COMPLETION: 30/06/26

## Slide 69: TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421)
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  | Plan June 26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act |  |  | 
Check Survey | Km |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | No |  | 309 |  | 309 | 0 |  |  |  |  |  |  |  |  | 
Erection | No |  | 309 |  | 309 | 0 |  |  |  |  |  |  |  |  | 
Stringing | Km |  | 121.342 |  | 113.361 | 7.981 |  | 2 | 14.192 | 14.19 | 14.192 | - | - | - | 
OPGW Stringing | Km |  | 121.342 |  | 97.672 | 23.67 |  |  | 23.67 | 23.67 | 23.67 | - | - | - | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  | Remarks |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  | 3Nos stubs in spare |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  | 3Nos towers in spare |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
210KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 70: TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421)
No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stubs Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stub Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Erection | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stringing | As per L2 | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | TSE (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Manual (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply as per L2 | KM |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply Actual | KM |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply as per L2 | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply Actual | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 71: TL01 - 765KV D/C Bidar Ps – Maheshwaram (TA- 421)
Issues / Support Required
1. Amendment # 4 is pending since from Feb’26
LOA DATE: 14/03/24 | LOA Value in Cr.: 370 | CONTRACTUAL COMPLETION: 14/11/25 | PLANNED COMPLETION: May’26

## Slide 72: TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601)
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  |  | Plan Jun’26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act | Act |  |  | 
Check Survey | Km |  |  |  |  |  |  | - |  | 0.400 |  | - | - | - | NA | 
Foundation | No |  | 292 |  | 120 | 172 |  | 03 | 40 | 40 | 40 | - | 03 | 40 | 20 | 
Erection | No |  | 292 |  | 71 | 221 |  | 01 | 35 | 35 | 35 | - | 01 | 35 | 20 | 
Stringing | Km |  | 113.286 |  | 0 | 113.286 |  | 00 |  | 00 | 0 | 00 | - | 05 | 06 | 
OPGW Stringing | Km |  | 113.286 |  | 0 | 113.286 |  |  | 0 |  | 0 |  |  |  |  | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  | Remarks |  |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  | To completed in May(02 Loc under hold) |  |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  | 02 loc Under hold by PGCIL |  |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
210KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 73: TL02 - 765kV D/C Kurnool IV – Bidar Line (TA- 601)
Issues / Support Required
1. All Crossing Proposals (11 proposal:6 PLC, 3 NH and 2 Railway), are submitted but no approval received till date
2. RC Foundation Drawings Required ( DC1, DC2, DD1, DD2)- For 14 Location
3. Two location – 110 /0 and 111/0 has been hold from PGCIL, which is hold due to widening of NH. Consequently 0.4 km of check survey is also hold
LOA DATE: 13/05/25 | LOA Value in Cr.: 517.07 | CONTRACTUAL COMPLETION: 12/04/27 | PLANNED COMPLETION: 12/04/27

## Slide 74: North East Project

## Slide 75: TW24 - 132kV Tawang-Lumla Line
Activity | UoM | As Per LOA (Qty) | Revised (Qty) | As per L2 (April'26) | Completed (Till 30.04.26) | Balance (As on 01.05.26) | Front Availability | Gangs Available | Gangs Available | Plan May 26 | Plan May 26 |  |  | Plan Jun’26 | Plan Jul 26 | Remarks
 |  |  |  |  |  |  |  |  |  | Plan | Plan | Act | Act |  |  | 
Check Survey | Km |  |  |  |  |  |  | - |  | 0.400 |  | - |  |  |  | 
Foundation | No |  |  |  |  |  |  | 03 |  | 40 |  | - |  |  |  | 
Erection | No |  |  |  |  |  |  | 01 |  | 35 |  | - |  |  |  | 
Stringing | Km |  |  |  |  |  |  | 00 |  | 00 |  | 00 |  |  |  | 
OPGW Stringing | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Supply Status: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Item | UoM |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stub | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tower | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conductor | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Earthwire | Km |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
160KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
210KN CLR | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HW Fittings | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front Availability Status |  |  |  |  |  |  |  |  |  | 
Activity | UoM | Feb’26 |  |  | Mar’26 |  |  | Apr’26 |  | 
 |  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No |  |  |  |  |  |  |  |  | 
Tower Erection | No |  |  |  |  |  |  |  |  | 
Stringing | Km |  |  |  |  |  |  |  |  | 

## Slide 76: TW24 - 132kV Tawang-Lumla Line
No. of month from NOA |  | UoM | Qty. | Upto Apr-26 | Balance As on 01.05.26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Foundation | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stubs Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Stub Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Erection | As per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Tower Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stringing | As per L2 | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completion Plan | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Front Required from POWERGRID | Kms |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gangs Planned | TSE (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Manual (Nos) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Conductor Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply as per L2 | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Insulator Supply Actual | Nos |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply as per L2 | % |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hardware Supply Actual | % |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 77: 400 KV D/C Twin Line Latehar- Patraru
Particulars | UoM | Total Qty | Completed (Till 30.04.26) | Balance (As on 01.05.26) | May 26 |  | Cu. Progress upto date | WIP | Remarks
 |  |  |  |  | Plan | Act |  |  | 
Foundation | Loc | 304 | 275 | 29 |  |  | 275 |  | Forest approval awaited. 29 Loc in Forest
Stub Rectification work | Leg | 514 | 323 | 193 | 66 | 32 | 355 | 16 | Forest -115 Leg (32 Loc)
No. of Gangs |  |  |  |  | 5 | 2 |  |  | 
Gang Strength |  |  |  |  |  | 16 |  |  | 
Tower Erection | Loc | 304 | 266 | 38 |  |  | 266 |  | Forest approval awaited. 38 Loc in Forest
Tower Erection work against Theft & Collapsed Portion | Loc | 156 |  | 156 |  |  |  |  | 
Partial Tower Rectification due to Theft | Loc | 110 |  | 110 |  |  |  |  | 
Stringing | KM | 107.51 | 2.190 | 105.32 |  |  | 2.190 |  | 
OPGW Stringing | KM | 107.51 |  | 107.51 |  |  |  |  | 

## Slide 78: Sikkim Tower Pkg TK04
220 KV D/C Dikchu - Singhik Transmission Line
a) The partially completed 132/66kv Singhik Sub-station has been abandon by Powergrid due to rapid sinking of entire 132/66kv Singhik Sub-Station Land
b) Based on abandonment of 132/66kv Singhik Sub-Station, the scope of the above said line has been reduced upto AP86/0 from Dikchu SS end and Powergrid suggested for charging of the said line up to AP86/0 from Dikchu SS end i.e. 21.516 KM Line Length against Total Line Length 22.440 KM
c) Due to reduction of scope the line from AP 86/0 to Singhik SS Gantry i.e. 0.711KM has been abandon resulting 5 Nos Erected & Strung Tower Location near Singhik SS end i.e. AP87/0 (DCS+9), AP88/0 (DD+18), AP89/0 (DCS+9), AP90/0 (DD+18), AP91/0 (DD+6 DE AUX) has also been abandoned
d) Based on Sl No. (a,b,c) above the balance work and its completion timeline are as follows:
Conductor Stringing – 4 Span (76/0-77/0 & 79A/0 to 81/0 i.e. 627 Mtr), OPGW Stringing – 12.588KM and Cutting of Soil for obtaining ground clearance in 47/0-48/0 and 51/0 to 52/0
Activity | UoM | Revised Line Qty | Completed as on May-26 | Balance as on May-26 | Completion Timeline |  | 
 |  |  |  |  | Jun-26 | July-26 | Aug-26
Foundation | NOS |  |  |  |  |  | 
Tower Erection | NOS |  |  |  |  |  | 
Stringing | KM |  |  |  |  |  | 
OPGW Stringing | KM |  |  |  |  |  | 
Cutting of Soil | Cum |  |  |  |  |  | 
Dismantling of Erected Tower | MT |  |  |  |  |  | 
De-Stringing | KM |  |  |  |  |  | 

## Slide 79: Sikkim Tower Pkg TK04
2. 220 KV D/C Singhik - Chungthang Transmission Line
a) Due to Natural Disaster i.e. Teesta GLOF Flood on 04.10.2023 and subsequent Cloud burst Flash Flood in North Sikkim on 18th Jun'24 & 20th May’25 the portion of above said constructed line i.e. 19.479km from AP28/0 to Chungthang Sub-station completely damage/washout out of total line length of 29.009km. Till date most part of the Line is inaccessible after Natural disaster
b) 132/66kv Singhik Sub-Station and 132/66kv Chungthang Sub-Station have been declared as abandoned by Powergrid
c) The status of balance work before Natural Disaster is as follows
Activity | UoM | Revised Line Qty | Completed as on Sep-23 | Balance as on Sep-23 | Completion Timeline |  | 
 |  |  |  |  | Jan-26 | Feb-26 | Mar-26
Foundation | NOS |  |  |  |  |  | 
Tower Erection | NOS |  |  |  |  |  | 
Stringing | KM |  |  |  |  |  | 
OPGW Stringing | KM |  |  |  |  |  | 
3. 66 KV D/C Chungthang - Lachen Transmission Line
a) Due to Natural Disaster i.e. Teesta GLOF Flood on 04.10.2023 and subsequent Cloud burst Flash Flood in North Sikkim on 18th Jun'24 & 20th May’25 the portion of above said constructed line completely damage/washout. Till date most part of the Line is inaccessible after Natural disaster
b) 132/66kv Singhik Sub-Station and 132/66kv Chungthang Sub-Station have been declared as abandoned by Powergrid
c) The status of balance work before Natural Disaster is as follows: -

## Slide 80: Sikkim Tower Pkg TK04
Activity | UoM | Line Qty | Completed as on Sep-23 | Balance as on Sep-23 | Completion Timeline |  | 
 |  |  |  |  | Jan-26 | Feb-26 | Mar-26
Foundation | NOS |  |  |  |  |  | 
Tower Erection | NOS |  |  |  |  |  | 
Stringing | KM |  |  |  |  |  | 
OPGW Stringing | KM |  |  |  |  |  | 
4. 66 KV S/C Singhik – Mangan Transmission Line
a) Line was Physically Completed on 15.03.2024 (except Mangan Side Gantry Connection due to Non availability of 11kv shutdown)
b) Due to Natural Disaster i.e. Cloud burst Flash Flood in North Sikkim on 18th Jun'24 & 20th May’25, 2 Nos erected and Strung Tower Location No. M27/0 & M28/0 near Mangan Sub-station is completely collapsed
c) Route diversion proposal near Mangan SS area from M26A/0 to M29/0 by incorporating 1 No 132 KV High Extension Tower is under approval at PG RHQ Kolkata. 2 Nos Foundation, 2 Nos collapsed Erected Tower i.e M27/0 & M28/0 will be abandon in Proposed Route
d) The status of balance work before Natural Disaster is as follows:
Activity | UoM | Revised Line Qty | Completed as on May-26 | Balance as on May-26 | Completion Timeline |  | 
 |  |  |  |  | Jun-26 | July-26 | Aug-26
Foundation | NOS |  |  |  |  |  | 
Tower Erection | NOS |  |  |  |  |  | 
Stringing | KM |  |  |  |  |  | 
OPGW Stringing | KM |  |  |  |  |  | 

## Slide 81: Sikkim Tower Pkg TK04
5. LILO of 66 kV Rabon - Maltin line at Chungthag
Activity | UoM | Revised Line Qty | Completed as on Sep-23 | Balance as on Sep-23 | Completion Timeline |  | 
 |  |  |  |  | Jan-26 | Feb-26 | Mar-26
Foundation | NOS |  |  |  |  |  | 
Tower Erection | NOS |  |  |  |  |  | 
Stringing | KM |  |  |  |  |  | 
OPGW Stringing | KM |  |  |  |  |  | 
e) 132/66kv Singhik Sub-Station have been declared as abandoned by Powergrid resulting 1 No Erected & Strung Tower Location near Singhik SS end i.e. AP- D/E(M TL) (SD+0) has also been abandoned
a) Line was Physically Completed on 31.01.2022 (except Chungthang SS Gantry Connection due to Non readiness of Chungthang Gantry and LILO connection due to non-availability of shutdown of 66 KV Existing Rabon – Malting Line)
b) Due to Natural Disaster i.e. Teesta GLOF Flood on 04.10.2023 the Line is inaccessible after Natural disaster
c) 132/66kv Chungthang Sub-Station has been declared as abandoned by Powergrid
d) The status of balance work before Natural Disaster is as follows: -
e) De-scope of line by PGCIL after Sikkim Flood on dtd 04/10/2023 vide their letter reference No. ER-II/CSSTDS/GTK/TK-04/1766 dated 08/05/2024

## Slide 82: Sikkim Tower Pkg TK04
6. 66 KV D/C Singhik – Passidong Transmission Line
a) Line was Physically completed on 31/12/2021 (Except Passingdong S/stn Gantry connection due to non-readiness of Passidong Gantry)
b) Due to Natural Disaster i.e. Cloud burst Flash Flood in North Sikkim on 18th Jun'24 & 20th May’25 3 Nos Erected and Strung Tower Location No. AP 1B/0 (DD+0), AP 1D/0 (DD+0) & AP 2/0 (DC+0) fully collapsed
c) The partial completed 132/66kv Singhik Sub-station has been abandoned by Powergrid due to rapid sinking of entire 132/66kv Singhik Sub-Station Land
d) Based on abandonment of Singhik Sub-Station the 22 Nos Erected and Strung Tower Location from AP- DE(PTL) to AP 19/0 may yet to be abandoned i.e. 3.225 KM Line Length will be abandoned against Total Line Length of 4.357 KM
e) The status of balance work before Natural Disaster is as follows: -
7. LILO of one circuit of 220 KV D/C Dikchu – Singhik Trans. Line at Sneha Kinetic HEP at Dikchu
Activity | UoM | Revised Line Qty | Completed as on May-26) | Balance as on May-26 | Completion Timeline |  | 
 |  |  |  |  | Jun-26 | July-26 | Aug-26
Foundation | NOS |  |  |  |  |  | 
Tower Erection | NOS |  |  |  |  |  | 
Stringing | KM |  |  |  |  |  | 
OPGW Stringing | KM |  |  |  |  |  | 
a) De-scope of line by PGCIL after Sikkim Flood on dtd 04/10/2023 vide their letter reference No. ER-II/CSSTDS/GTK/TK-04/1766 dated 08/05/2024

## Slide 83: Commercial Closures and Pending Claims

## Slide 84: Summary of Claims submitted at PGCIL(Region Wise)
Sr. No. | Region | Claim raised amount(in Rs Cr)
1 | ER-I(Patna) | 78
2 | ER-II(Kolkata) | 25
3 | ER-II(Kolkata)- Cables | 4
4 | NER(Guwahati) | 3
5 | NER(Itanagar) | 4
6 | Rajasthan | 90
7 | WR-II(Vadodara) | 95
8 | NR-I(Faridabad) | 9
9 | SR-I(Hyderabad) | 2
Total |  | 310
Pending Claims (ER-I) |  |  |  |  |  |  |  |  | 
Sr. No. | Project | Claim Description | LOA Date | LOA Value(Cr) | Contractual Completion | Planned Completion | Claim Raised Amount (Cr) | Pendency | Remarks
1 | JSEB 01 Tower package TW-01 associated with implementation of transmission scheme in Jharkhand under consultancy services to JSEB | Prolongation & Interest on outstanding payments | 28-09-2012 |  |  |  |  |  | 
 |  | Idling of Resources |  |  |  |  |  |  | 
Claim Raised Amount(Cr) for ER-I |  |  |  |  |  |  |  |  | 

## Slide 85: Pending Claims (ER-II)
Sr. No. | Project | Claim Description | LOA Date | LOA Value (Cr) | Contractual Completion | Planned Completion | Claim Raised Amount (in Rs Cr) | Pendency | Remarks
1 | Tower package TK-01 under comprehensive scheme of strengthening of transmission and distribution system in sikkim | TK01-Prolongation | 16-03-2016 | 115.21 | 30 Months | completed | 6.74 | Pending since Nov-2022 | Being continuously followed up in corporate for settlement
 |  | TK01-Prolongation | 16-03-2016 |  |  |  |  |  | 
 | Tower package Tk-04 for various 66/220 kV Transmission lines Under comprehensive scheme of strengthening of transmission and distribution system in sikkim | TK04-Prolongation | 23-06-2016 |  |  |  |  |  | 
 |  | TK 04 Prolongation claim | 23-06-2016 |  |  |  |  |  | 
2 | PGCIL SIKKIM OLD( cabling) | Prolongation | 03-02-2021 |  |  |  |  |  | 
3 | PGCIL SIKKIM NEW(cabling) | Prolongation | 17-03-2022 |  |  |  |  |  | 
Claim Raised Amount(Cr) for ER-II |  |  |  |  |  |  |  |  | 

## Slide 86: Pending Claims (NR)
Region: Northeast Region (Guwahati) |  |  |  |  |  |  |  |  | 
Sr. No. | Project | Claim Description | LOA Date | LOA Value(Cr) | Contractual Completion | Planned Completion | Claim Raised Amount(in Rs Cr) | Pendency | Remarks
1 | Transmission line package TW7B | Prolongation | 15-01-2021 |  |  |  |  |  | 
Claim Raised Amount(Cr) for NER-Guwahati |  |  |  |  |  |  |  |  | 
Region: Northeast Region (Itanagar) |  |  |  |  |  |  |  |  | 
2 | Tower package TW24 under comprehensive scheme of strengthning of transmission and distribution system in Arunachal Pradesh | Prolongation | 28-09-2018 |  |  |  |  |  | 
Claim Raised Amount(Cr) for NER-Itanagar |  |  |  |  |  |  |  |  | 

## Slide 87: Pending Claims (Rajasthan Region)
Sr. No. | Project | Claim Description | LOA Date | LOA Value(Cr) | Contractual Completion | Planned Completion | Claim Raised Amount (in Rs Cr) | Pendency | Remarks
1 | TW02 for 765kV D/C Fatehgarh-Il PS - Bhadla - II PS (2nd) under TBCB | Prolongation (18.3Crs)/Idling (1.1Crs) | 15-02-2021 | 239.75 | 15 Months | Completed | 19.40 | Pending since Feb'24 | Preliminary discussion held on 27.04.26.Next date to be finalized for further taking up the claims
2 | TW01 for Bhadla-Il PS- Sikar-II 765kV D/C Line-Part-I under TBCB | Prolongation (11.48Crs)/Idling (0.24Crs) | 15-02-2021 |  |  |  |  |  | 
3 | TW03 for Bhadla-Il PS- Sikar-II 765kV D/C Line-Part-III under TBCB | Prolongation (23.69 Crs)/Idling (1.91Crs) | 15-02-2021 |  |  |  |  |  | 
4 | TW04 for Sikar-ll - Neemrana 400 kV D/C line (Twin HTLS) (Part I) under TBCB | Prolongation (20.36Crs)/Idling (0.37Crs) | 15-02-2021 |  |  |  |  |  | 
5 | Package TW02 for Bhadla-Il PS- Sikar-II 765kV D/C Line-Part-II under TBCB | Prolongation Cost | 15-02-2021 |  |  |  |  |  | 
Claim Raised Amount(Cr) for RJ Region |  |  |  |  |  |  |  |  | 

## Slide 88: Pending Claims (WR-II) (Cont..)
Sr. No. | Project | Claim Description | LOA Date | LOA Value( Cr) | Contractual Completion | Planned Completion | Claim Raised Amount (in Rs Cr) | Pendency | Remarks
1 | Navsari Magarwada TL | Prolongation (7.21Crs)/Idling (0.8 Crs) | 11-08-2022 | 285.66 | 10-11-23 & 10-9-24 | 02-04-2026 | 8.32 | Pending since April'23, Latest submission was made in Jan'25 | Idling -As per Powergrid meeting, revisions were made after addressing Finance queries and routing via PESM and C&M—is presently under review with Finance (HoD level committee). Prolongation - Revised L2 finalized after joint discussions with PG & KEC; consent and PV implications submitted, and the case is currently under review with Finance.
2 | Ahmedabad Navsari TL 02 | Idling | 21-03-2023 |  |  |  |  |  | 
 |  | Prologation | 21-03-2023 |  |  |  |  |  | 
 |  | Foundation and erection dismatling work | 21-03-2023 |  |  |  |  |  | 
 |  | Surge costs for expediting project completion | 21-03-2023 |  |  |  |  |  | 

## Slide 89: Pending Claims (WR-II)
Sr. No. | Project | Claim Description | LOA Date | LOA Value(Cr) | Contractual Completion | Planned Completion | Claim Raised Amount(in Rs Cr) | Pendency | Remarks
3 | Railway Electrification works Package- PUNE-SATARA (Railways) | Prolongation | 21-06-2018 | 344.65 | 06-02-2022 | 17-06-2025 | 20.09 | Pending since May'23 | Currently at RHQ
4 | Ahmedabad SS | Prolongation | 17-03-2023 |  |  |  |  |  | 
5 | KPS 2 SS | Prolongation | 18-03-2023 |  |  |  |  |  | 
Claim Raised Amount(Cr) for WR -II |  |  |  |  |  |  |  |  | 

## Slide 90: Pending Claims(SR-I and NR-I)
Sr. No. | Project | Claim Description | LOA Date | LOA Value(Cr) | Contractual Completion | Planned Completion | Claim Raised Amount(Cr) | Pendency | Remarks
1 | Koppal Raichur | Idling | 12-03-2024 | 148.6 | 11-12-2025 | 30-06-2026 | 1.70 | Submitted in Apr'26 | Submittedd on 15 april 2026 under review with PGCIL site.
Claim Raised Amount(Cr) for SR -I |  |  |  |  |  |  |  |  | 
Sr. No. | Project | Claim Description | LOA Date |  |  |  |  |  | 
1 | Bikaner Sub Station pkg-01 | Delay in land handover | 02-03-2021 |  |  |  |  |  | 
2 | Neemuch PS – Chittorgarh (PG)TL01- 400kV D/C | Project was fast tracked for completion based on Employer's request to expedite and recoup for the delays on account of Forest clearance. Yet to be concluded. Claim with complete details of additional expenses on account of expediting submitted. | 12-09-2022 |  |  |  |  |  | 
Claim Raised Amount(Cr) for NR –I |  |  |  |  |  |  |  |  | 
Total Claim Raised Amount(Cr) |  |  |  |  |  |  |  |  | 

## Slide 91: Pending L2 Revision
SL No | Project | Region | Pendency | Reason for Pendency
1 | JSEB Pkg – 01 TL | ER1 | Pending since April’23. | Proposal at corporate for approval. To be expedited.
 |  |  |  | Out of 10 lines 9 lines have already been completed. 10th line rectification work has been started. (339/516 Leg completed and 24 Leg WIP).
2 | TW07B Assam TL | NER | Pending since May’23 | Project completed. To be expedited
3 | Navsari Magarwada TL | WR2 | Pending since July’25 | Project completed. Revised L2 finalized after joint discussions with PG & KEC; consent and PV implications submitted, and the case is currently under review with Finance.
4 | Ahmedabad Navsari TL | WR2 | Submitted on 11-11-25 | Project completed. Revised L2 under process with PGCIL RHQ PESM team. Supporting documents for FTE submitted and under review with PG. Revised L2 to be finalized in line with FTE. Delay analysis for FTE is being prepared and worked upon jointly with Powergrid. To be expedited.

## Slide 92: Financial details(Closure Projects)
Project Code | Project Name | SBU | Region | Pending from which date | O/s Amount (Cr) | CPBG & Retention Value(Cr) | Adv Bank Guarantee Cr)
A303/304 | JSEB Lines | TL | ER-I |  |  |  | 
A920 | Khupi-Bomdila TL SS | TL | NER |  |  |  | 
TA-119 | TL Package TW7B Assam | TL | NER |  |  |  | 
TA-121 | TW01 for Bhadla-II PS- Sikar-II 765kV D/C Line-Part-I | TL | RJ |  |  |  | 
TA-122 | TW02 for Bhadla-II PS- Sikar-II 765kV D/C Line-Part-II | TL | RJ |  |  |  | 
TA-123 | TW03 for Bhadla-II PS- Sikar-II 765kV D/C Line-Part-III | TL | RJ |  |  |  | 
TA-124 | Package TW04 for Sikar-II – Neemrana 400 kV D/C line (Twin HTLS) | TL | RJ |  |  |  | 
A775 | PG Aligarh | SS | NR-III |  |  |  | 
SA-008 | Guna | SS | WR-II |  |  |  | 
SA-126 | 400 KV Bikaner S/S | SS | NR-I |  |  |  | 
SA-127 | 400 Khetri S/S | SS | NR-I |  |  |  | 
SA-128 | 400 Bhiwadi S/S | SS | NR-I |  |  |  | 
SA-213 | 764 KV Khetri | SS | NR-I |  |  |  | 
XA-104 | PGCIL Pithoragarh | Cable | NR-III |  |  |  | 
XA- 107 | PGCIL Sikkim -New | Cable | ER-II |  |  |  | 
XB-012 | PGCIL Sikkim -Old | Cable | ER-II |  |  |  | 
A820 | PGCIL TW-09 | TL | NER |  |  |  | 
SA-212 | Narela SS | SS |  |  |  |  | 
SA-307 | Navsari-DL | SS |  |  |  |  | 
SA-308 | Phadghe-DL | SS |  |  |  |  | 
SA-322 | Ahembdabad SS | SS |  |  |  |  | 
SA-323 | KPS 2 | SS |  |  |  |  | 
SA-324 | Navsari GIS Extn | SS |  |  |  |  | 
SA-409 | Ramgarh SS | SS |  |  |  |  | 
TA-325 | Ahmedabad-Navsari (South Gujarat) Line | TL |  |  |  |  | 
TA-405 | Bhadla-II to Sikar-II | TL |  |  |  |  | 
TA-310 | Navsari Kala T/L | TL |  |  |  |  | 
 | Total |  |  |  |  |  | 
Total Outstanding 440 Cr : BGs 245 Cr

## Slide 93: Commercial closure/ Claims and Intervention sought
Region - Rajasthan and NR 1
Bhadla Sikar Tw 01 - FTE and FA issued. Final Invoice to be processed, Due drawn under Signing
Bhadla Sikar Tw 02 – FA and FTE issued. Final Invoice to be processed. Due drawn Signed
Bhadla Sikar Tw 03 - FA and FTE issued. Final Invoice to be processed and SAP uploading required
Sikar Neemarana Tw 04 – FTE and FA issuance pending.
Bikaner SS/Bhiwadi SS/Khetri SS – FA and FTE issued, Final Invoice to be processed, At Faridabad
Narela SS – FA issued, FTE to be processed
Issuance of TOC for Bhadla 3 SS which was charged on 2nd March’26 and TOC request was submitted on 5th March’26.
Cost Compensation Claims
JSEB – Finalization of Claim and L2, approx. 77 Cr (Work started but claim not settled till date).ROW and Forest clearance pending.
PGCIL-To initiate L2 Amendment and Time over run claim to BGCL Board as this is holding supply of materials.
TK – 01 Sikkim – prolongation Claim with CC Gurgaon, 6.74 Cr
TK – 04 Sikkim – prolongation Claim with CC Gurgaon, 7 Cr
TK – 04 Sikkim 2 – prolongation Claim with Site , 9 Cr
TBCB Rajasthan - project delays Claim at Region level , 90 Cr
Expediting Cost of Neemuch Chittorgarh T/L and release of CPBG – pending with NR1
BG Release for Banaskantha Chittorgarh project – Pending with NR1

## Slide 94: Project Closure Status(Rajasthan)
Sr. No | Project Name | TL/SS | Date of Commissioning | Pending Outstanding Value(Crs.) | Claims (Crs.) | Remarks
1 | Package TW01 for Badla-Il PS- Sikar-II 765kV D/C Line-Part-I (TA 121) | TL | 17.12.24 |  |  | 
2 | Package TW02 for Bhadla-ps- Sikar-lt 765kv D/cline-part-Il (TA 122) | TL | 17.12.24 |  |  | 
3 | Package TW03 for Badla-Il PS- Sikar-II 765kV D/C Line-Part-III(TA 123) | TL | 17.12.24 |  |  | 
4 | Package TW04 for Sikar-ll - Neemrana 400 kV D/C line (Twin HTLS(TA124) | TL | 11.10.24 |  |  | 
5 | Package TW02 for Badla-III Ps- Sikar-II 765kv D/cline-part-Il (TA405) | TL | 12.02.26 |  |  | 
6 | 765/400/220kV Ramgarh PS New | SS | 23.02.26 |  |  | 
7 | 765/400/220kV Badla III PS | SS | 03.03.26 |  |  | 
8 | TW02: Fathegargh -II PS - Badla -II PS 765 KV D/c Line (2 nd) Part B (TA -120) | TL | 18.08.24 |  |  | 
9 | Substation projects: (Bikaner/Khetri & Bhiwadi) | SS |  |  |  | 
 |  |  | Total |  |  | 

## Slide 95: Thank You