## Summary S
KEC International Limited
Supply Status | [8 empty] | 2026-05-20
Name of Line _ 765 kV Bikaner-IV PS – Siwani (2nd) line - Part-I
Sr. No. | Item Description | Finalized Vendor | Unit | Start Date as per Approved L2 Schedule | FInish Date as per Approved L2 Schedule | Total Qty as per LOA | Received Till Date | Balance | Remarks
1 | Tower Stub | KEC | Nos. | 2025-02-20 | 2025-10-25 | 315 | 319 | -4
2 | Tower Earthing | KEC | Nos. | 2025-02-20 | 2025-10-25 | 315 | 319 | -4
3 | Tower Structure | KEC | Nos. | 2025-04-10 | 2026-03-20 | 315 | 298 | 17 | DA+0/+3/+6/+9/-1.5/-3 Extn - 51/71/54/44/18/12 Nos. DB1+0/+3/+6/+9 Extn - 9/3/1/2 Nos. DB2+0/+3/+6/+9 Extn - 6/3/1/1 Nos. DC1+0/+3/+6 Extn - 3/1/1Nos. DC2+0/+3/+9 Extn - 3/1/1 Nos. DC2+0 - 1 Nos.(TP Tower) DD1+0/+9 Extn - 2/2 Nos. DD2+0/+3/+18/+25/+35 Extn - 1/1/1/1/2 Nos. (12937.29 MT received)
4 | Conductor | KEC Cables | Km | 2025-07-15 | 2026-06-20 | 4398 | 3682.104 | 715.896
5 | Insulator | Aditya Birla | Nos. | 2025-07-15 | 2026-06-20 | 12272 | 0 | 12272
6 | H/w Fittings | Tag | % | 2025-07-15 | 2026-06-20 | 100% | 0 | 100%
7 | OPGW Cable | Apar Industries | Km | 2025-11-20 | 2026-05-20 | 127 | 0 | 127

## Supply Status
SUPPLY STATUS AS PER BOQ
Name of Line _ 765 kV Bikaner-IV PS – Siwani (2nd) line - Part-I
Agency: KEC INTERNATIONAL Limited
Status as on | [9 empty] | 2026-05-20
Sl. No. | Activity Description | Item Description | Supplier | Unit | Total Quantity | Supplies as per L2 | Actual as on date | Balance | Present status of balance supplies | Expected date of supply
1 | EARTHING OF TOWERS | Supply of Pipe Type Earthing | KEC | EA | 297 |  | 319 | -22 |  |  | 107.4%
2 | EARTHING OF TOWERS | Supply of Counterpoise type earthing (120 mlength) | KEC | EA | 15 |  |  | 15 |  |  | 0%
3 | EARTHING OF TOWERS | ROD TYPE EARTHING | KEC | EA | 297 |  | 319 | -22 |  |  | 107.4%
4 | EARTHING OF TOWERS | Supply of Shieldwire EarthingincludingPG clamps, downlead clampsbutexcluding Earthwire bits for Pipetypeearthing | KEC | EA | 14 |  |  | 14 |  |  | 0%
5 | EARTHING OF TOWERS | Supply of Shieldwire Earthing Counterpoise (4X30M) Type including PGclamps, downlead clamps but excluding Earthwire bits. | KEC | EA | 3 |  |  | 3 |  |  | 0%
6 | EARTHING OF TOWERS | Counterpoise type (280 m length) | KEC | EA | 3 |  |  | 3 |  |  | 0%
7 | TOWER ACCESSORIES | Danger Plate for 765kV | KEC | EA | 315 |  |  | 315 |  |  | 0%
8 | TOWER ACCESSORIES | Number Plate for 765kV | KEC | EA | 315 |  |  | 315 |  |  | 0%
9 | TOWER ACCESSORIES | Phase Plate (Set of three) | KEC | SET | 630 |  |  | 630 |  |  | 0%
10 | TOWER ACCESSORIES | Circuit Plate (Set of two) | KEC | SET | 315 |  |  | 315 |  |  | 0%
11 | TOWER ACCESSORIES | Supply of Anti-Climbing Devices ofBarbedWire Type | KEC | SET | 315 |  |  | 315 |  |  | 0%
12 | TOWER ACCESSORIES | Bird Guard (Set of Three) | KEC | SET | 510 |  |  | 510 |  |  | 0%
13 | CONDUCTOR | AL59 ZEBRA CONDUCTOR (KM) | KEC Cables | KM | 4398 |  | 3682.104 | 715.896 |  |  | 83.72%
14 | Earthwire | 7/3.66 G.S. EARTHWIRE | Nirmal Wires | KM | 122 |  | 86 | 36 |  |  | 70.49%
15 | HARDWARE FITTINGS | Hardware Fittings for 765kV AC with Hexagonal Zebra Conductor-Double ISuspension String | TAG | SET | 1530 |  | 1298 | 232 |  |  | 84.84%
16 | HARDWARE FITTINGS | Hardware Fittings for 765kV AC with Hexagonal Zebra Conductor-Single ISuspension String (Pilot) | TAG | SET | 94 |  | 85 | 9 |  |  | 90.43%
17 | HARDWARE FITTINGS | Hardware Fittings for 765kV AC with Hexagonal ZebraConductor-Quadruple Tension String | TAG | SET | 732 |  | 633 | 99 |  |  | 86.48%
18 | HARDWARE FITTINGS | Hardware Fittings for 765kV AC with Hexagonal Zebra Conductor-SingleTension String | TAG | SET | 4 |  |  | 4 |  |  | 0%
19 | HARDWARE FITTINGS | Hardware Fittings for 765kV AC with Hexagonal Zebra Conductor-Double ISuspension String | TAG | SET | 25 |  |  | 25 |  |  | 0%
20 | HARDWARE FITTINGS | Hardware Fittings for 765kV AC with Hexagonal Zebra Conductor-Single ISuspension String (Pilot) | TAG | SET | 5 |  |  | 5 |  |  | 0%
21 | HARDWARE FITTINGS | Hardware Fittings for 765kV AC with Hexagonal ZebraConductor-Quadruple Tension String | TAG | SET | 10 |  |  | 10 |  |  | 0%
22 | HARDWARE FITTINGS | Hardware Fittings for 765kV AC with Hexagonal Zebra Conductor-SingleTension String | TAG | SET | 1 |  |  | 1 |  |  | 0%
23 | CONDUCTOR ACCESSORIES | MID SPAN COMPRESSION JOINT FOR AL59 ZEBRA CONDUCTOR | TAG | EA | 2199 |  | 1880 | 319 |  |  | 85.49%
24 | CONDUCTOR ACCESSORIES | REPAIR SLEEVE FOR AL59 ZEBRA CONDUCTOR | TAG | EA | 733 |  | 632 | 101 |  |  | 86.22%
25 | CONDUCTOR ACCESSORIES | T-CONNECTOR-765KV AC WITH AL59 HEXA ZEBRA | TAG | EA | 96 |  | 91 | 5 |  |  | 94.79%
26 | CONDUCTOR ACCESSORIES | PREFORMED RETAINING ROD TYPE SPACER DAMPER SUITABLE FOR HEXA AL59ZEBRA CONDUCTOR | TAG | EA | 13230 |  | 11280 | 1950 |  |  | 85.26%
27 | CONDUCTOR ACCESSORIES | HEXAGONAL RIGID SPACER-765KV AC WITH AL59 HEX ZEBRA | TAG | EA | 1800 |  | 1540 | 260 |  |  | 85.56%
28 | CONDUCTOR ACCESSORIES | MID SPAN COMPRESSION JOINT FOR AL59 ZEBRA CONDUCTOR | TAG | EA | 10 |  |  | 10 |  |  | 0%
29 | CONDUCTOR ACCESSORIES | REPAIR SLEEVE FOR AL59 ZEBRA CONDUCTOR | TAG | EA | 10 |  |  | 10 |  |  | 0%
30 | CONDUCTOR ACCESSORIES | T-CONNECTOR-765KV AC WITH AL59 HEXA ZEBRA | TAG | EA | 10 |  |  | 10 |  |  | 0%
31 | CONDUCTOR ACCESSORIES | PREFORMED RETAINING ROD TYPE SPACER DAMPER SUITABLE FOR HEXA AL59ZEBRA CONDUCTOR | TAG | EA | 40 |  |  | 40 |  |  | 0%
32 | CONDUCTOR ACCESSORIES | HEXAGONAL RIGID SPACER-765KV AC WITH AL59 HEX ZEBRA | TAG | EA | 10 |  |  | 10 |  |  | 0%
33 | Earthwire Accessories | Mid Span Compression Joint -7/3.66mmEarth Wire | TAG | EA | 67 |  | 59 | 8 |  |  | 88.06%
34 | Earthwire Accessories | FLEXIBLE AL BOND-7/3.66MM E/W | TAG | EA | 377 |  | 305 | 72 |  |  | 80.9%
35 | Earthwire Accessories | Vibration damper -7/3.66mm Earth Wire | TAG | EA | 754 |  | 647 | 107 |  |  | 85.81%
36 | Earthwire Accessories | Suspension clamp assembly -7/3.66mmEarth Wire | TAG | EA | 255 |  | 220 | 35 |  |  | 86.27%
37 | Earthwire Accessories | Tension clamp assembly-7/3.66mm EarthWire | TAG | EA | 120 |  | 104 | 16 |  |  | 86.67%
38 | Earthwire Accessories | Mid Span Compression Joint -7/3.66mmEarth Wire | TAG | EA | 2 |  |  | 2 |  |  | 0%
39 | Earthwire Accessories | FLEXIBLE AL BOND-7/3.66MM E/W | TAG | EA | 5 |  |  | 5 |  |  | 0%
40 | Earthwire Accessories | Vibration damper -7/3.66mm Earth Wire | TAG | EA | 6 |  |  | 6 |  |  | 0%
41 | Earthwire Accessories | Suspension clamp assembly -7/3.66mmEarth Wire | TAG | EA | 3 |  |  | 3 |  |  | 0%
42 | Earthwire Accessories | Tension clamp assembly-7/3.66mm EarthWire | TAG | EA | 2 |  |  | 2 |  |  | 0%
43 | INSULATOR (CLR) | Composite long rod Insulators for 765kV Transmission Line-160 KN (Length-2975 mm, Creepage-12400 mm) | Aditya Birla | EA | 6316 |  |  | 6316 |  |  | 0%
44 | INSULATOR (CLR) | Composite long rod Insulators for 765kV Transmission Line-210 KN (Length-2975 mm, Creepage-12400 mm) | Aditya Birla | EA | 5856 |  |  | 5856 |  |  | 0%
45 | INSULATOR (CLR) | Composite long rod Insulators for 765kV Transmission Line-160 KN (Length-2975 mm, Creepage-12400 mm) | Aditya Birla | EA | 50 |  |  | 50 |  |  | 0%
46 | INSULATOR (CLR) | Composite long rod Insulators for 765kV Transmission Line-210 KN (Length-2975 mm, Creepage-12400 mm) | Aditya Birla | EA | 50 |  |  | 50 |  |  | 0%
47 | AVIATION REQUIREMENTS | Supply of Span Marker for Aviation |  | EA | 345 |  |  | 345 |  |  | 0%
48 | AVIATION REQUIREMENTS | Supply of Obstruction Lights (as perIS5613)-1 Medium Intensity + 2LowIntensity |  | SET | 311 |  |  | 311 |  |  | 0%
49 | AVIATION REQUIREMENTS | Supply of Obstruction Lights (as per IS5613)-1 Medium Intensity + 4 LowIntensity |  | SET | 4 |  |  | 4 |  |  | 0%
50 | Sleeves | INSULATION SLEEVE FOR CONDUCTOR | TAG | M | 240 |  |  | 240 |  |  | 0%
51 | FABRICATION AND SUPPLY (MT) | Fabrication, galvanising & supply ofvarious types of towers & towerparts,tower/leg extensions (complete)excluding step bolt, stubs andbolts &nuts but including hangers, D-Shackles,pack washers etc.-HTSteel for NormalTowers | KEC | MT | 10052 |  | 9344.96 | 707.04 |  |  | 92.97%
52 | FABRICATION AND SUPPLY (MT) | Fabrication, galvanising & supply ofvarious types of towers & towerparts,tower/leg extensions (complete)excluding step bolt, stubs andbolts &nuts but including hangers, D-Shackles,pack washers etc.-MSSteel for NormalTowers | KEC | MT | 3855 |  | 3592.33 | 262.67 |  |  | 93.19%
53 | FABRICATION AND SUPPLY (MT) | Fabrication, galvanising & supply ofstubs with cleats for varioustypes oftowers and tower extensions(complete)with packwashers excluding supply ofbolts & nuts-HT Steel for Normal Towers | KEC | MT | 377 |  | 348 | 29 |  |  | 92.31%
54 | FABRICATION AND SUPPLY (MT) | Supply of Hexagonal Bolts & Nuts fortowers including Step Bolts,SpringWashers etc. | KEC | MT | 579 |  | 540.295 | 38.705 |  |  | 93.32%
55 | FABRICATION AND SUPPLY (MT) | Supply of Bolts & Nuts for Stubsincluding Spring Washers etc. | KEC | MT | 8.29 |  | 8.29 | 0 |  |  | 100%
56 | OPGW Supply | 24 FIBRE (DWSM) OPGW FIBRE OPTIC CABLE | Apar Industries | KM | 127 |  |  | 127 |  |  | 0%
57 | OPGW Supply | Suspension clamp assembly for 24 fibreOPGW |  | EA | 245 |  |  | 245 |  |  | 0%
58 | OPGW Supply | TENSION FITTINGS ASSEMBLY ON SUSPENSIONTOWER FOR 24F OPGW INCLUDINGALLACCESSORIES AT JOINT BOX (SPLICING)LOCATION |  | SET | 10 |  |  | 10 |  |  | 0%
59 | OPGW Supply | TENSION FITTINGS ASSEMBLY FOR 24F OPGWINCLUDING ALL ACCESSORIES FORJOINT BOX(SPLICING) LOCATION |  | SET | 16 |  |  | 16 |  |  | 0%
60 | OPGW Supply | TENSION ASSEMBLY - DOUBLE TENSION PASSTHROUGH ASSEMBLY FOR 24 FIBEROPGW |  | SET | 44 |  |  | 44 |  |  | 0%
61 | OPGW Supply | TENSION ASSEMBLY - DEAD END FOR 24 FIBEROPGW |  | SET | 1 |  |  | 1 |  |  | 0%
62 | OPGW Supply | Vibration Damper for 24 fibre OPGW |  | EA | 1384 |  |  | 1384 |  |  | 0%
63 | OPGW Supply | Down Lead clamp Assembly for 24 fibreOPGW |  | EA | 1350 |  |  | 1350 |  |  | 0%
64 | OPGW Supply | Joint Box for 24 fibre OPGW |  | EA | 27 |  |  | 27 |  |  | 0%
65 | OPGW Supply | 48 FIBRE (DWSM) OPGW FIBRE OPTIC CABLE | Apar Industries | KM | 20 |  |  | 20 |  |  | 0%
66 | OPGW Supply | Suspension clamp assembly for 48 fibre OPGW |  | EA | 51 |  |  | 51 |  |  | 0%
67 | OPGW Supply | TENSION ASSEMBLY - DEAD END FOR 48 FIBER OPGW |  | SET | 1 |  |  | 1 |  |  | 0%
68 | OPGW Supply | TENSION FITTINGS ASSEMBLY FOR 48F OPGW INCLUDING ALL ACCESSORIES FORJOINT BOX (SPLICING) LOCATION |  | SET | 3 |  |  | 3 |  |  | 0%
69 | OPGW Supply | TENSION ASSEMBLY - DOUBLE TENSION PASS THROUGH ASSEMBLY FOR 48 FIBEROPGW |  | SET | 4 |  |  | 4 |  |  | 0%
70 | OPGW Supply | TENSION ASSEMBLY FOR JOINTING AT SUSPENSION TOWER FOR 48 FIBER OPGW |  | SET | 1 |  |  | 1 |  |  | 0%
71 | OPGW Supply | Vibration Damper for 48 fibre OPGW |  | EA | 136 |  |  | 136 |  |  | 0%
72 | OPGW Supply | Down Lead clamp Assembly for 48 fibre OPGW |  | EA | 167 |  |  | 167 |  |  | 0%
73 | OPGW Supply | Joint Box for 48 fibre OPGW |  | EA | 5 |  |  | 5 |  |  | 0%
74 | OPGW Supply | OPGW Fibre Optic Distribution Panel (FODP): Indoor Type: 96F |  | EA | 1 |  |  | 1 |  |  | 0%
75 | OPGW Supply | GI PIPE INSTALLATION HARDWARE FOR APPROACH CABLING |  | KM | 0.5 |  |  | 0.5 |  |  | 0%
76 | OPGW Supply | GI ELBOW INSTALLATION HARDWARE FOR APPROAH CABLING |  | EA | 10 |  |  | 10 |  |  | 0%
77 | OPGW Supply | GI FLEXIBLE CONDUIT INSTALLATION HARDWARE FOR APPROAH CABLING |  | EA | 7 |  |  | 7 |  |  | 0%
78 | OPGW Supply | 48F (DWSM) APPROACH FIBRE OPTIC CABLE | Apar Industries | KM | 0.5 |  |  | 0.5 |  |  | 0%
79 | Bird Diverter | BIRD DIVERTER |  | EA | 200 |  |  | 200 |  |  | 0%
80 | OPGW mandatory spares | 24 FIBRE (DWSM) OPGW FIBRE OPTIC CABLE | Apar Industries | KM | 3 |  |  | 3 |  |  | 0%
81 | OPGW mandatory spares | Suspension clamp assembly for 24 fibreOPGW |  | EA | 6 |  |  | 6 |  |  | 0%
82 | OPGW mandatory spares | TENSION FITTINGS ASSEMBLY ON SUSPENSIONTOWER FOR 24F OPGW INCLUDINGALLACCESSORIES AT JOINT BOX (SPLICING)LOCATION |  | SET | 1 |  |  | 1 |  |  | 0%
83 | OPGW mandatory spares | TENSION FITTINGS ASSEMBLY FOR 24F OPGWINCLUDING ALL ACCESSORIES FORJOINT BOX(SPLICING) LOCATION |  | SET | 1 |  |  | 1 |  |  | 0%
84 | OPGW mandatory spares | TENSION ASSEMBLY - DOUBLE TENSION PASSTHROUGH ASSEMBLY FOR 24 FIBEROPGW |  | SET | 1 |  |  | 1 |  |  | 0%
85 | OPGW mandatory spares | TENSION ASSEMBLY - DEAD END FOR 24 FIBEROPGW |  | SET | 1 |  |  | 1 |  |  | 0%
86 | OPGW mandatory spares | Vibration Damper for 24 fibre OPGW |  | EA | 6 |  |  | 6 |  |  | 0%
87 | OPGW mandatory spares | Down Lead clamp Assembly for 24 fibreOPGW |  | EA | 6 |  |  | 6 |  |  | 0%
88 | OPGW mandatory spares | Joint Box for 24 fibre OPGW |  | EA | 1 |  |  | 1 |  |  | 0%
89 | OPGW mandatory spares | 48 FIBRE (DWSM) OPGW FIBRE OPTIC CABLE | Apar Industries | KM | 1.5 |  |  | 1.5 |  |  | 0%
90 | OPGW mandatory spares | Suspension clamp assembly for 48 fibre OPGW |  | EA | 3 |  |  | 3 |  |  | 0%
91 | OPGW mandatory spares | TENSION ASSEMBLY - DEAD END FOR 48 FIBER OPGW |  | SET | 1 |  |  | 1 |  |  | 0%
92 | OPGW mandatory spares | TENSION FITTINGS ASSEMBLY FOR 48F OPGW INCLUDING ALL ACCESSORIES FORJOINT BOX (SPLICING) LOCATION |  | SET | 1 |  |  | 1 |  |  | 0%
93 | OPGW mandatory spares | TENSION ASSEMBLY - DOUBLE TENSION PASS THROUGH ASSEMBLY FOR 48 FIBEROPGW |  | SET | 1 |  |  | 1 |  |  | 0%
94 | OPGW mandatory spares | TENSION ASSEMBLY FOR JOINTING AT SUSPENSION TOWER FOR 48 FIBER OPGW |  | SET | 1 |  |  | 1 |  |  | 0%
95 | OPGW mandatory spares | Vibration Damper for 48 fibre OPGW |  | EA | 6 |  |  | 6 |  |  | 0%
96 | OPGW mandatory spares | Down Lead clamp Assembly for 48 fibre OPGW |  | EA | 1 |  |  | 1 |  |  | 0%
97 | OPGW mandatory spares | Joint Box for 48 fibre OPGW |  | EA | 1 |  |  | 1 |  |  | 0%
98 | OPGW mandatory spares | GI PIPE INSTALLATION HARDWARE FOR APPROACH CABLING |  | KM | 0.018 |  |  | 0.018 |  |  | 0%
99 | OPGW mandatory spares | GI ELBOW INSTALLATION HARDWARE FOR APPROAH CABLING |  | EA | 5 |  |  | 5 |  |  | 0%
100 | OPGW mandatory spares | GI FLEXIBLE CONDUIT INSTALLATION HARDWARE FOR APPROAH CABLING |  | EA | 2 |  |  | 2 |  |  | 0%
101 | OPGW mandatory spares | 48F (DWSM) APPROACH FIBRE OPTIC CABLE |  | KM | 0.5 |  |  | 0.5 |  |  | 0%

## Summary E
KEC International Limited | [11 empty] | 2026-05-20
Name of Client: Bikaner B Power Transmission Limited
Name of Line: 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
NOA No. CC/T/W-TW/DOM/A00/24/09582/NOA-1 & 2/25-10174/01 & 02, Dated 03/01/2025
Office : Hansera, Lunkaransar
S.No. | Activity | LOA Qty | Estimated Quantity | Cumm. Progress up to Last Month (Apr'26) | Target as per L2 Schedule Cummulative (upto Apr'26) | Month's Plan as per L2 Schedule | Progress of Month | Today | Cumulative Progress Till Date | Balance | No of Gangs/MP | Remarks
1 | Route Alignment (Km) | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
2 | Detailed Survey (Km) | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
3 | Profiling (Km) | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
4 | Check Survey (Km) | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
5 | Land Scheduling (Km) | 120.944 | 124.568 | 123.174 | 0 | 0 | 0 | 0 | 123.174 | 1.394 |  | Approved ROW Corridor - 123.174 Km Tower Base - 315 Nos.
6 | Soil Investigation (Nos.) | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 28 | 0
7 | Excavation | 315 | 319 | 302 | 272 | 25 | 3 | 1 | 305 | 14
8 | Foundation (Nos.) | 315 | 319 | 301 | 272 | 25 | 1 | 0 | 302 | 17 | 03/38
9 | Earthing (Nos.) | 315 | 319 | 269 |  |  |  |  | 269 | 50
10 | Tower Erection (Nos) | 315 | 319 | 213 | 210 | 30 | 4 | 0 | 217 | 102 | 02/48
11 | Tack Welding | 315 | 319 | 53 | 0 |  | 23 | 1 | 76 | 243
12 | Stringing (Km) | 120.944 | 124.568 | 0 | 60 | 12 |  | 0 | 0 | 124.568
13 | Paying Out | 120.944 | 124.568 | 0 | 0 |  | 0 | 0 | 0 | 124.568
14 | Final Sag | 120.944 | 124.568 | 0 | 0 |  | 0 | 0 | 0 | 124.568
15 | OPGW (Km) | 120.944 | 124.568 | 0 | 10 | 20 | 0 |  | 0 | 124.568

## DPR Sheet (hidden)
KEC International Limited
DAILY PROGRESS REPORT : STATUS AS ON |  |  |  |  | 2026-05-20
Name of the Project: |  | 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Contract No. & Date : |  | CC/T/W-TW/DOM/A00/24/09582/CA-1&2/25-100174/01 & 02 Dtd. 21.01.2025
ROUTE ALIGNMENT PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
124.568 | 124.568 | 0 | 124.568 | 0
DETAILED SURVEY PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
124.568 | 124.568 | 0 | 124.568 | 0
CHECK SURVEY PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
124.568 | 124.568 | 0 | 124.568 | 0
FOUNDATION PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
319 | 301 | 1 | 302 | 17
EARTHING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
319 | 269 |  |  | 319
TOWER ERECTION PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
319 | 213 | 0 | 0 | 319
STRINGING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY(KM)
124.568 | 0 | 0 | 0 | 124.568
OPGW STRINGING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
124.568 | 0 | 0 | 0 | 124.568
TACK WELDING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
319 | 53 | 24 | 0 | 319
SHIELD WIRE EARTHING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
0

## DS
KEC International Limited
765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Detailed Survey | [5 empty] | 2026-05-20
Sl.No. | SPAN |  | Detail Survey Section Length (Km) | Submitted For Approval | Approved Date | Remarks
| From Section | To Section
1 | AP8 | AP19 | 16.984 | 2025-02-12 | 2025-02-13 | Approved
2 | AP6 | AP8 | 9.313 | 2025-02-21 | 2025-02-22 | Approved
3 | AP4 | AP6 | 11.121 | 2025-03-10 | 2025-03-15 | Approved
4 | AP28 | AP29 | 3.179 | 2025-03-10 | 2025-03-15 | Approved
5 | AP19 | AP28 | 11.409 | 2025-03-11 | 2025-03-15 | Approved
6 | AP29 | AP32 | 28.482 | 2025-03-11 | 2025-03-15 | Approved
7 | AP32 | AP35 | 11.16 | 2025-04-02 | 2025-04-03 | Approved
8 | AP36 | AP44 | 14.759 | 2025-04-02 | 2025-04-03 | Approved
9 | AP35 | AP36 | 4.095 | 2025-06-13 | 2025-06-24 | Approved
10 | AP1A | AP4 | 11.446 | 2025-06-13 | 2025-06-20 | Approved
11 | AP44 | AP47 | 1.483 |  |  | Approved
12 | GSS Gantry | AP1A |  |  |  | Hold By Power Grid
13
14
15
Total |  |  | 123.431

## CS
KEC International Limited
765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Check Survey | [5 empty] | 2026-05-20
Sl.No. | SPAN |  | Section Length (Km) | Submitted for Approval on Dated | Approved on Dated | Remarks
| From Section | To Section
1 | AP8 | AP10 | 5.532 | 2025-02-12 | 2025-02-13 | Approved
2 | AP6 | AP8 | 9.313 | 2025-03-03 | 2025-02-25 | Approved
3 | AP10 | AP19 | 11.452 | 2025-03-03 | 2025-02-25 | Approved
4 | AP4 | AP6 | 11.121 | 2025-03-10 | 2025-03-15 | Approved
5 | AP28 | AP29 | 3.179 | 2025-03-10 | 2025-03-15 | Approved
6 | AP19 | AP20 | 3.224 | 2025-03-10 | 2025-03-15 | Approved
7 | AP20 | AP28 | 8.185 | 2025-03-17 | 2025-03-18 | Approved
8 | AP29 | AP31 | 17.041 | 2025-03-20 | 2025-03-21 | Approved
9 | AP31 | AP32 | 11.441 | 2025-04-16 | 2025-04-17 | Approved
10 | AP1A | AP4 | 11.446 |  |  | Approved
11 | AP34 | AP44 | 23.386 |  |  | Approved
12 | AP32 | AP34 | 6.628 |  |  | Approved
13 | AP44 | AP47 | 1.483 |  |  | Approved
14 | GSS Gantry | AP1A |  |  |  | Hold By Power Grid
15
Total |  |  | 123.431

## Hindrance Record
Hindrance Record
|  | Balance >> | 17 | 4 | [6 empty] | 102 | 32
Sr. No | Loc No | Tower Type | Foundation Status | Hindrance During Foundation Work | Start Date | End Date | Effected Days | Farmer Name | Village Name | Contact No. | Tower Erection Status | Hindrance During Tower Erection Work | Start Date | End Date | Effected Days | Farmer Name | Village Name | Contact No.
1 | 1/0 | DD60+3 |  |  |  |  | 0 | [7 empty] | 0
2 | 1/1 | DB1+18 |  |  |  |  | 0 | [7 empty] | 0
3 | 1/2 | DA+0 |  |  |  |  | 0 | [7 empty] | 0
4 | 1A/0 | DD45+0 | WIP |  |  |  | 0 | [7 empty] | 0
5 | 1A/1 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
6 | 1A/2 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
7 | 1A/3 | DA-3 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-02-15 |  | -46068
8 | 2/0 | DD60+3 | Completed | Resolved | 2026-01-03 | 2026-01-07 | 4 |  |  |  |  | ROW | 2026-02-15 |  | -46068
9 | 2/1 | DA+6 | Completed | Resolved | 2025-07-25 | 2025-08-08 | 14 |  |  |  |  | ROW | 2026-02-15 |  | -46068
10 | 2/2 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
11 | 2/3 | DA+9 | Completed | Resolved | 2025-07-25 | 2025-12-30 | 158 |  |  |  | Completed | Resolved | 2026-03-10 | 2026-03-19 | 9
12 | 2/4 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
13 | 2/5 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
14 | 2/6 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-03-10 | 23
15 | 2A/0 | DB2+3 | Completed |  |  |  | 0 |  |  |  |  | Resolved | 2026-02-15 | 2026-04-22 | 66
16 | 2A/1 | DA+9 | Completed |  |  |  | 0 |  |  |  |  | Resolved | 2026-02-15 | 2026-04-22 | 66
17 | 2A/2 | DA-1.5 | Completed |  |  |  | 0 |  |  |  |  | Resolved | 2026-02-15 | 2026-04-22 | 66
18 | 2A/3 | DA+3 | Completed |  |  |  | 0 | [7 empty] | 0
19 | 2A/4 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-04-05 | 49
20 | 2A/5 | DA+9 | Completed |  |  |  | 0 |  |  |  |  | Resolved | 2026-02-15 | 2026-04-22 | 66
21 | 3/0 | DC2+9 | Completed |  |  |  | 0 | [7 empty] | 0
22 | 3/1 | DB1+9 | Completed |  |  |  | 0 | [7 empty] | 0
23 | 3/2 | DA+9 | Completed |  |  |  | 0 |  |  |  |  | Resolved | 2026-02-15 | 2026-04-22 | 66
24 | 3/3 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
25 | 3/4 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
26 | 3/5 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
27 | 3/6 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
28 | 3/7 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
29 | 3A/0 | DD45+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
30 | 3A/1 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
31 | 3A/2 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
32 | 3A/3 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
33 | 4/0 | DB2+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
34 | 4/1 | DA-3 | Completed | Resolved | 2025-08-13 | 2025-12-11 | 120 |  |  |  |  | ROW | 2026-02-15 |  | -46068
35 | 4/2 | DA+6 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-02-15 |  | -46068
36 | 4/3 | DA-3 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-02-15 |  | -46068
37 | 4/4 | DA+9 | Completed | Resolved | 2025-08-13 | 2025-12-04 | 113 |  |  |  | Completed |  |  |  | 0
38 | 4/5 | DA+9 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-02-15 |  | -46068
39 | 4/6 | DA+3 | Completed | Resolved | 2025-08-13 | 2025-09-11 | 29 |  |  |  | Completed |  |  |  | 0
40 | 4/7 | DB1+0 | Completed | Resolved | 2025-08-13 | 2025-10-04 | 52 |  |  |  | Completed |  |  |  | 0
41 | 4/8 | DA+9 | Completed | Resolved | 2025-08-13 | 2025-09-18 | 36 |  |  |  | Completed |  |  |  | 0
42 | 4/9 | DA+3 | Completed | Resolved | 2025-08-13 | 2025-09-23 | 41 |  |  |  | Completed |  |  |  | 0
43 | 4/10 | DA-1.5 | Completed | Resolved | 2025-08-13 | 2025-09-29 | 47 |  |  |  | Completed |  |  |  | 0
44 | 4/11 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2026-03-06 | 2026-04-10 | 35
45 | 4/12 | DA+3 | Completed | Resolved | 2025-07-01 | 2025-07-08 | 7 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-03-21 | 34
46 | 4/13 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-03-07 | 20
47 | 4/14 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-03-24 | 37
48 | 5/0 | DB1+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
49 | 5/1 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-02-26 | 11
50 | 5/2 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
51 | 5/3 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
52 | 5/4 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
53 | 5/5 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
54 | 5/6 | DA+6 | Completed | Resolved | 2025-06-15 | 2025-12-15 | 183 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-03-10 | 23
55 | 5/7 | DB1+3 | Completed | Resolved | 2025-06-15 | 2025-12-15 | 183 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-03-14 | 27
56 | 5/8 | DA+6 | Completed | Resolved | 2025-05-15 | 2025-05-16 | 1 |  |  |  |  | Resolved | 2025-09-03 | 2026-04-14 | 223
57 | 5/9 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-03 | 2025-12-08 | 96
58 | 5/10 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-03 | 2025-12-14 | 102
59 | 5/11 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
60 | 6/0 | DB1+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
61 | 6/1 | DA+3 | Completed | Resolved | 2025-04-20 | 2025-05-09 | 19 | Mohit/ Nanu Ram | Winjharwali | 7877597229 | Completed |  |  |  | 0
62 | 6/2 | DA+3 | Completed | Resolved | 2025-04-20 | 2025-05-09 | 19 |  |  |  | Completed | Resolved | 2025-08-24 | 2025-12-29 | 127
63 | 6/3 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-24 | 2026-01-18 | 147
64 | 6/4 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-24 | 2026-01-29 | 158
65 | 6/5 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-24 | 2026-02-09 | 169
66 | 6/6 | DB1+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
67 | 6/7 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-24 | 2026-02-14 | 174
68 | 6/8 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-24 | 2025-12-11 | 109
69 | 6/9 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-24 | 2026-02-26 | 186
70 | 6/10 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
71 | 7/0 | DB1+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
72 | 7/1 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-03 | 2025-09-04 | 1
73 | 7/2 | DA-1.5 | Completed |  |  |  | 0 |  |  |  |  | Resolved | 2026-02-15 | 2026-04-14 | 58
74 | 7/3 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
75 | 7/4 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
76 | 7/5 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
77 | 7/6 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
78 | 7/7 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
79 | 7/8 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
80 | 7/9 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
81 | 7/10 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-24 | 2025-11-26 | 94
82 | 7/11 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-24 | 2025-11-23 | 91
83 | 8/0 | DC1+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
84 | 8/1 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
85 | 8/2 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-24 | 2026-03-07 | 195
86 | 8/3 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
87 | 8/4 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-24 | 2026-02-04 | 164
88 | 8/5 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
89 | 8/6 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
90 | 8/7 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
91 | 8/8 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
92 | 9/0 | DB1+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
93 | 9/1 | DA+0 | Completed | Resolved | 2025-03-01 | 2025-08-17 | 169 | Ratna Ram Siyag | Dhirera | 9001397114 | Completed | Resolved | 2025-08-24 | 2025-12-01 | 99
94 | 9/2 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
95 | 9/3 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
96 | 9/4 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
97 | 10/0 | DD60+25 | Completed |  |  |  | 0 |  |  |  |  | Resolved | 2026-02-15 | 2026-04-22 | 66
98 | 11/0 | DD60+18 | WIP |  |  |  | 0 | [7 empty] | 0
99 | 11/1 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
100 | 11/2 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-25 | 2025-12-25 | 91
101 | 11/3 | DA+0 | Completed | Resolved | 2025-03-03 | 2025-05-18 | 76 | Ram Pratap Godara | Sahajarasar | 9660746637 | Completed | Resolved | 2025-09-25 | 2025-12-14 | 80
102 | 11/4 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-25 | 2025-12-04 | 70
103 | 11/5 | DA-1.5 | Completed | Resolved | 2025-03-03 | 2025-05-15 | 73 | Jay Kishan Jiyani | Hansera | 9602652541 | Completed | Resolved | 2025-09-25 | 2025-11-27 | 63
104 | 11/6 | DA+3 | Completed | Resolved | 2025-03-03 | 2025-05-15 | 73 | Jay Kishan Jiyani | Hansera | 9602652541 | Completed | Resolved | 2025-09-25 | 2025-12-30 | 96
105 | 11/7 | DA+3 | Completed | Resolved | 2025-03-03 | 2026-05-07 | 430 | Narayan Ram Sharma | Surnana | 9979296799 |  |  |  |  | 0
106 | 11/8 | DA+3 | Completed | Resolved | 2025-03-03 | 2025-11-14 | 256 | Kumbha Ram | Khiyrera | 9057224958 | Completed |  |  |  | 0
107 | 12/0 | DC2+0 | Completed | Resolved | 2025-03-03 | 2025-10-17 | 228 | Magga Ram | Hansera | 9799651670 |  | ROW | 2026-02-15 |  | -46068
108 | 12/1 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
109 | 12/2 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2026-01-10 | 2026-03-07 | 56
110 | 12/3 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
111 | 12/4 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
112 | 12/5 | DA+9 | Completed | Resolved | 2025-03-03 | 2025-07-01 | 120 | Manful | Dhirera | 7597493243 | Completed |  |  |  | 0
113 | 13/0 | DC1+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
114 | 13/1 | DA+6 | Completed |  |  |  | 0 |  |  |  |  | Resolved | 2026-02-15 | 2026-04-22 | 66
115 | 14/0 | DC1+0 |  |  |  |  | 0 | [7 empty] | 0
116 | 15/0 | DC1+0 |  |  |  |  | 0 | [7 empty] | 0
117 | 16/0 | DB2+0 | WIP | ROW | 2026-05-01 |  | -46143 | [7 empty] | 0
118 | 16/1 | DA+3 | Completed | Resolved | 2025-10-31 | 2025-11-06 | 6 |  |  |  |  | Resolved | 2026-02-15 | 2026-04-22 | 66
119 | 16/2 | DA+0 | Completed |  |  |  | 0 |  |  |  |  | Resolved | 2026-02-15 | 2026-04-22 | 66
120 | 16/3 | DA+0 | Completed |  |  |  | 0 |  |  |  |  | Resolved | 2026-02-15 | 2026-04-22 | 66
121 | 17/0 | DD60+0 | Completed |  |  |  | 0 | [7 empty] | 0
122 | 18/0 | DD60+0 | Completed |  |  |  | 0 | [7 empty] | 0
123 | 18/1 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
124 | 18/2 | DA+3 | Completed | Resolved | 2025-03-17 | 2025-10-14 | 211 | Lal Chand Tarad | Hansera | 9001457191 | Completed |  |  |  | 0
125 | 18/3 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-24 | 2025-11-23 | 91
126 | 18/4 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-24 | 2025-11-16 | 84
127 | 18/5 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
128 | 19/0 | DC2+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
129 | 19/1 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-08-30 | 2025-09-01 | 2
130 | 19/2 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
131 | 19/3 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
132 | 19/4 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
133 | 19/5 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
134 | 19/6 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
135 | 19/7 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
136 | 20/0 | DC1+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
137 | 20/1 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
138 | 20/2 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
139 | 20/3 | DA-3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
140 | 20/4 | DA+0 | Completed | Resolved | 2025-03-17 | 2025-09-26 | 193 | Lal Chand Tarad | Hansera | 9001457191 | Completed |  |  |  | 0
141 | 20/5 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
142 | 20/6 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
143 | 20/7 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
144 | 20A/0 | DD45+9 | Completed |  |  |  | 0 | [7 empty] | 0
145 | 21/0 | DC2+3 | Completed |  |  |  | 0 | [7 empty] | 0
146 | 22/0 | DD60+6 | Completed |  |  |  | 0 | [7 empty] | 0
147 | 23/0 | DD60+9 | Completed |  |  |  | 0 | [7 empty] | 0
148 | 23/1 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
149 | 23/2 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
150 | 23/3 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
151 | 23/4 | DA+0 |  |  |  |  | 0 | [7 empty] | 0
152 | 24/0 | DC2+0 |  |  |  |  | 0 | [7 empty] | 0
153 | 25/0 | DC2+0 |  |  |  |  | 0 | [7 empty] | 0
154 | 25/1 | DA+9 |  |  |  |  | 0 | [7 empty] | 0
155 | 26/0 | DD60+35 |  | ROW | 2026-04-28 |  | -46140 | [7 empty] | 0
156 | 27/0 | DD60+35 | WIP | Resolved | 2026-04-28 | 2026-05-02 | 4 | [7 empty] | 0
157 | 27/1 | DB1+9 | Completed |  |  |  | 0 |  |  |  |  | Resolved | 2026-02-15 | 2026-04-22 | 66
158 | 27/2 | DA-1.5 | Completed | Resolved | 2025-04-06 | 2025-06-11 | 66 | Sundar Lal Nath | Lunkaransar | 8290384169 |  | ROW | 2026-02-15 |  | -46068
159 | 27/3 | DA-3 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-02-15 |  | -46068
160 | 28/0 | DB2+0 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2026-01-29 | 2026-02-15 | 17
161 | 28/1 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2025-09-24 | 13
162 | 28/2 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2025-10-13 | 32
163 | 28/3 | DA+0 | Completed | Resolved | 2025-03-27 | 2025-05-31 | 65 | Saraswati W/o Shri Ram | Kalu | 9825157515 | Completed | Resolved | 2025-09-11 | 2026-02-02 | 144
164 | 28/4 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2025-11-01 | 51
165 | 28/5 | DA+0 | Completed | Resolved | 2025-03-26 | 2025-06-05 | 71 |  | Kalu |  | Completed | Resolved | 2025-09-11 | 2025-10-03 | 22
166 | 28/6 | DA+0 | Completed | Resolved | 2025-03-28 | 2025-05-27 | 60 | Rajendra Kumar S/o Nanu Ram | Kalu |  | Completed | Resolved | 2025-09-11 | 2025-11-05 | 55
167 | 28/7 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2025-10-26 | 45
168 | 29/0 | DB2+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
169 | 29/1 | DA+6 | Completed | Resolved | 2025-04-01 | 2025-06-18 | 78 | Nagaraj S/o Bhikhamchand | Kalu | 9830281543 | Completed |  |  |  | 0
170 | 29/2 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
171 | 29/3 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
172 | 29/4 | DA+0 | Completed | Resolved | 2025-04-01 | 2025-06-30 | 90 | Saraswati W/o Pemaram | Gopalyan | 9680269112 | Completed |  |  |  | 0
173 | 29/5 | DA+3 | Completed | Resolved | 2025-04-02 | 2025-07-10 | 99 | Omprakash S/o Ramuram Kailash S/o Ramuram | Kalu |  | Completed |  |  |  | 0
174 | 29/6 | DA+0 | Completed | Resolved | 2025-04-02 | 2025-06-26 | 85 | Sumitra Devi W/o Ram Pratap | Kalu |  | Completed |  |  |  | 0
175 | 29/7 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
176 | 29/8 | DA+0 | Completed | Resolved | 2025-04-03 | 2025-07-07 | 95 | Girdhari Ram S/o Ramdhan | Kalu | 9509760995 | Completed |  |  |  | 0
177 | 29/9 | DA+0 | Completed | Resolved | 2025-04-03 | 2025-07-15 | 103 | Thakshiram S/o Arjanram | Kalu |  | Completed |  |  |  | 0
178 | 29/10 | DA+0 | Completed | Resolved | 2025-04-03 | 2025-07-18 | 106 | Hariram S/o Ram Narayan | Kalu | 8010007741 | Completed |  |  |  | 0
179 | 29/11 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
180 | 29/12 | DB1+0 | Completed | Resolved | 2025-04-04 | 2025-07-25 | 112 | Satyanarayan S/o Jagmalaram | Kalu | 9694151197 | Completed |  |  |  | 0
181 | 29/13 | DA+0 | Completed | Resolved | 2025-08-01 | 2025-10-16 | 76 |  |  |  | Completed |  |  |  | 0
182 | 29/14 | DA+0 | Completed | Resolved | 2025-08-01 | 2025-09-03 | 33 |  |  |  | Completed |  |  |  | 0
183 | 29/15 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
184 | 29/16 | DA+0 | Completed | Resolved | 2025-08-01 | 2025-11-09 | 100 |  |  |  |  | ROW | 2026-01-29 |  | -46051
185 | 29/17 | DA+0 | Completed | Resolved | 2025-08-01 | 2025-10-29 | 89 |  |  |  | Completed |  |  |  | 0
186 | 29/18 | DA+3 | Completed | Resolved | 2025-08-01 | 2025-08-28 | 27 |  |  |  |  | ROW | 2026-01-29 |  | -46051
187 | 29/19 | DA+3 | Completed | Resolved | 2025-08-01 | 2025-09-24 | 54 |  |  |  |  | ROW | 2026-01-29 |  | -46051
188 | 29/20 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
189 | 29/21 | DA+3 | Completed | Resolved | 2025-08-01 | 2025-10-24 | 84 |  |  |  | Completed |  |  |  | 0
190 | 29/22 | DA+3 | Completed | Resolved | 2025-08-01 | 2025-12-25 | 146 |  |  |  | Completed |  |  |  | 0
191 | 30/0 | DB2+0 | Completed | Resolved | 2025-08-01 | 2025-10-04 | 64 |  |  |  |  | ROW | 2026-01-29 |  | -46051
192 | 30/1 | DA+3 | Completed | Resolved | 2025-04-04 | 2025-11-10 | 220 |  |  |  |  | ROW | 2026-01-29 |  | -46051
193 | 30/2 | DA+6 | Completed | Resolved | 2025-04-05 | 2025-08-01 | 118 |  |  |  | Completed |  |  |  | 0
194 | 30/3 | DA+0 | Completed | Resolved | 2025-04-05 | 2025-11-24 | 233 |  |  |  | Completed |  |  |  | 0
195 | 30/4 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2026-01-20 | 131
196 | 30/5 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2026-01-11 | 122
197 | 30/6 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2026-01-02 | 113
198 | 30/7 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2025-09-26 | 15
199 | 30/8 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2025-12-24 | 104
200 | 30/9 | DB1+0 | Completed | Resolved | 2025-04-06 | 2025-05-26 | 50 | Sarita Devi D/o Kanhailal | Chhattasar | 9950511787 | Completed | Resolved | 2026-01-29 | 2026-02-21 | 23
201 | 30/10 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2025-12-14 | 94
202 | 30/11 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2026-02-13 | 155
203 | 30/12 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2025-12-03 | 83
204 | 30/13 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2026-02-07 | 149
205 | 30/14 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2025-11-22 | 72
206 | 30/15 | DA+3 |  | ROW | 2025-05-02 |  | -45779 | Rajendra S/o Mamraj | Chhattasar | 9829064703 9752095071 |  |  |  |  | 0
207 | 30/16 | DA+6 | Completed | Resolved | 2025-05-02 | 2025-08-14 | 104 | Kamladevi W/o Chetanram Miradevi W/o Jaypal | Chhattasar |  |  | ROW | 2025-09-12 |  | -45912
208 | 30/17 | DC2+0 | Completed | Resolved | 2025-05-05 | 2025-10-26 | 174 | Kesaram S/o Shriram Chhunilal S/o Shriram | Chhattasar | 9879134181 982893117 | Completed | Resolved | 2026-01-29 | 2026-03-07 | 37
209 | 30/18 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2025-09-20 | 9
210 | 31/0 | DB2+0 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-01-29 |  | -46051
211 | 31/1 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
212 | 31/2 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
213 | 31/3 | DA-3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
214 | 31/4 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2026-02-08 | 150
215 | 31/5 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2026-01-11 | 122
216 | 31/6 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2026-01-19 | 130
217 | 31/7 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2026-01-27 | 138
218 | 31/8 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2026-02-01 | 143
219 | 31/9 | DB1+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
220 | 31/10 | DA+6 | WIP | Resolved | 2025-05-28 | 2026-05-02 | 339 | Gorakharam S/o Bhuraram | Kagasar | 9057204350 |  |  |  |  | 0
221 | 31/11 | DA+6 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2025-09-11 |  | -45911
222 | 31/12 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-11 | 2026-02-13 | 155
223 | 31/13 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2025-09-12 | 2026-02-07 | 148
224 | 31/14 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
225 | 31/15 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
226 | 31/16 | DA+6 | Completed | Resolved | 2025-07-25 | 2025-07-31 | 6 |  |  |  | Completed |  |  |  | 0
227 | 31/17 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
228 | 31/18 | DB1+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
229 | 31/19 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-03-02 | 15
230 | 31/20 | DA-1.5 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
231 | 31/21 | DA+3 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-02-15 |  | -46068
232 | 31/22 | DA+6 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-02-15 |  | -46068
233 | 31/23 | DA+6 | Completed | Resolved | 2025-07-25 | 2025-07-30 | 5 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-03-14 | 27
234 | 31/24 | DA+9 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-02-15 |  | -46068
235 | 31/25 | DA-3 | Completed | Resolved | 2025-07-25 | 2025-11-05 | 103 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-03-21 | 34
236 | 31/26 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
237 | 31/27 | DA+3 | Completed | Resolved | 2025-07-25 | 2025-11-10 | 108 |  |  |  | Completed | Resolved | 2026-01-19 | 2026-01-21 | 2
238 | 32/0 | DB2+3 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-01-30 |  | -46052
239 | 32/1 | DA+9 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-01-30 |  | -46052
240 | 32/2 | DA+3 | Completed | Resolved | 2025-12-20 | 2026-03-12 | 82 |  |  |  | Completed | Resolved | 2026-03-29 | 2026-04-04 | 6
241 | 32/3 | DA+9 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-01-30 |  | -46052
242 | 32/4 | DA+6 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-01-30 |  | -46052
243 | 32/5 | DA+0 | Completed |  |  |  | 0 |  |  |  | WIP | ROW | 2026-02-03 |  | -46056
244 | 32/6 | DA+3 | Completed |  |  |  | 0 |  |  |  |  | ROW | 2026-01-30 |  | -46052
245 | 32/7 | DA+6 | Completed | Resolved | 2025-12-03 | 2025-12-08 | 5 |  |  |  |  | ROW | 2026-01-30 |  | -46052
246 | 32/8 | DA+6 | Completed | Resolved | 2025-12-03 | 2026-02-15 | 74 | [7 empty] | 0
247 | 32/9 | DA+9 | Completed | Resolved | 2025-12-03 | 2026-02-15 | 74 | [7 empty] | 0
248 | 32/10 | DA+9 |  | ROW | 2025-11-18 |  | -45979 | [7 empty] | 0
249 | 33/0 | DB2+3 | Completed | Resolved | 2025-11-18 | 2026-02-24 | 98 | [7 empty] | 0
250 | 33/1 | DA+9 | Completed | Resolved | 2025-12-03 | 2026-01-28 | 56 |  |  |  |  | ROW | 2026-02-15 |  | -46068
251 | 33/2 | DA+3 | Completed | Resolved | 2025-12-03 | 2025-12-11 | 8 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-02-27 | 12
252 | 33/3 | DA+9 | Completed | Resolved | 2025-12-03 | 2026-01-15 | 43 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-04-18 | 62
253 | 33/4 | DA+9 | Completed | Resolved | 2025-12-03 | 2025-12-20 | 17 |  |  |  | Completed | Resolved | 2026-02-15 | 2026-04-24 | 68
254 | 33A/0 | DC2+0 | Completed | Resolved | 2025-12-03 | 2025-12-30 | 27 |  |  |  |  | ROW | 2026-02-15 |  | -46068
255 | 34/0 | DD45+9 | Completed | Resolved | 2025-12-03 | 2026-01-04 | 32 |  |  |  |  | ROW | 2026-02-15 |  | -46068
256 | 34/1 | DA+6 | Completed | Resolved | 2025-06-24 | 2026-04-14 | 294 | [7 empty] | 0
257 | 34/2 | DA+6 | Completed | Resolved | 2025-06-24 | 2025-08-01 | 38 |  |  |  |  | ROW | 2026-04-30 |  | -46142
258 | 34/3 | DA+0 | Completed | Resolved | 2025-06-24 | 2025-08-01 | 38 |  |  |  | Completed |  |  |  | 0
259 | 34/4 | DA+9 | Completed |  |  |  | 0 |  |  |  | WIP | Resolved | 2026-04-30 | 2026-05-17 | 17
260 | 34/5 | DA+6 | Completed | Resolved | 2025-06-24 | 2025-07-13 | 19 |  |  |  | WIP | Resolved | 2026-04-30 | 2026-05-20 | 20
261 | 34/6 | DA-3 | Completed | Resolved | 2025-06-24 | 2025-07-13 | 19 |  |  |  | Completed |  |  |  | 0
262 | 34/7 | DA+6 | Completed | Resolved | 2025-06-24 | 2025-08-16 | 53 |  |  |  | Completed |  |  |  | 0
263 | 34/8 | DA+9 | Completed | Resolved | 2025-06-24 | 2025-11-21 | 150 |  |  |  | Completed | Resolved | 2026-04-30 | 2026-05-06 | 6
264 | 34/9 | DA+9 | Completed | Resolved | 2025-09-20 | 2025-09-28 | 8 |  |  |  | Completed |  |  |  | 0
265 | 34/10 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
266 | 35/0 | DB1+9 | Completed | Resolved | 2025-09-20 | 2025-09-26 | 6 |  |  |  | Completed |  |  |  | 0
267 | 35/1 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
268 | 35/2 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
269 | 35/3 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
270 | 35/4 | DA+3 | Completed | Resolved | 2025-11-30 | 2025-12-03 | 3 |  |  |  | Completed |  |  |  | 0
271 | 35/5 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
272 | 35/6 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
273 | 35/7 | DA-3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
274 | 35/8 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
275 | 35/9 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
276 | 36/0 | DB1+6 | Completed | Resolved | 2025-08-27 | 2025-12-20 | 115 | [7 empty] | 0
277 | 36/1 | DA+6 | Completed | Resolved | 2025-08-27 | 2025-12-26 | 121 | [7 empty] | 0
278 | 36/2 | DA+9 | Completed | Resolved | 2025-08-27 | 2025-09-26 | 30 | [7 empty] | 0
279 | 36/3 | DA+9 | Completed | Resolved | 2025-08-27 | 2025-09-26 | 30 |  |  |  | Completed |  |  |  | 0
280 | 36/4 | DA+9 | Completed | Resolved | 2025-08-27 | 2025-09-23 | 27 | [7 empty] | 0
281 | 36/5 | DA+6 | Completed |  |  |  | 0 | [7 empty] | 0
282 | 36/6 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
283 | 36/7 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
284 | 36/8 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
285 | 36/9 | DA+6 | Completed |  |  |  | 0 | [7 empty] | 0
286 | 37/0 | DB1+0 | Completed | Resolved | 2025-08-27 | 2025-09-15 | 19 |  |  |  | Completed |  |  |  | 0
287 | 37/1 | DA+0 | Completed | Resolved | 2025-08-27 | 2025-10-28 | 62 | [7 empty] | 0
288 | 37/2 | DA+3 | Completed | Resolved | 2025-08-27 | 2025-10-05 | 39 |  |  |  | Completed |  |  |  | 0
289 | 37/3 | DA+3 | Completed | Resolved | 2025-08-27 | 2025-10-05 | 39 |  |  |  | Completed |  |  |  | 0
290 | 37/4 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
291 | 37/5 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
292 | 37/6 | DA+6 | Completed |  |  |  | 0 | [7 empty] | 0
293 | 37/7 | DA-3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
294 | 37/8 | DA+9 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
295 | 37/9 | DA-3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
296 | 37/10 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
297 | 38/0 | DB2+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
298 | 38/1 | DA+0 | Completed | Resolved | 2025-11-16 | 2025-11-23 | 7 | [7 empty] | 0
299 | 38/2 | DA-3 | Completed |  |  |  | 0 | [7 empty] | 0
300 | 39/0 | DB2+9 | Completed |  |  |  | 0 | [7 empty] | 0
301 | 40/0 | DC1+9 | Completed |  |  |  | 0 | [7 empty] | 0
302 | 40/1 | DA+3 | Completed |  |  |  | 0 | [7 empty] | 0
303 | 40/2 | DA+9 | Completed |  |  |  | 0 | [7 empty] | 0
304 | 40/3 | DA+3 | Completed |  |  |  | 0 |  |  |  | WIP |  |  |  | 0
305 | 40/4 | DA+6 | Completed |  |  |  | 0 | [7 empty] | 0
306 | 41/0 | DC1+0 | Completed |  |  |  | 0 | [7 empty] | 0
307 | 41/1 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
308 | 41/2 | DA+0 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
309 | 41/3 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
310 | 41/4 | DA+6 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
311 | 41/5 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
312 | 41/6 | DA+3 | Completed |  |  |  | 0 |  |  |  | Completed |  |  |  | 0
313 | 42/0 | DB1+0 | Completed |  |  |  | 0 | [7 empty] | 0
314 | 43/0 | DC1+0 | Completed |  |  |  | 0 | [7 empty] | 0
315 | 44/0 | DB2+6 | Completed |  |  |  | 0 | [7 empty] | 0
316 | 44/1 | DA-3 | Completed | Resolved | 2026-02-20 | 2026-04-11 | 50 | [7 empty] | 0
317 | 45/0 | DC2+9 | Completed | Resolved | 2026-02-20 | 2026-04-14 | 53 | [7 empty] | 0
318 | 46/0 | DD60+18 | Completed | Resolved | 2026-02-20 | 2026-04-11 | 50 | [7 empty] | 0
319 | 47/0 | DD60+18 | Completed | Resolved | 2026-02-20 | 2026-03-27 | 35 | [7 empty] | 0

## Earthing
KEC International Limited
765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Details of Earthing | [10 empty] | 2026-05-20
Sr. No. | Month | Month Sr. No. | Loc. No. | Type of Tower | Type of Classification | Start | Complete | Name of the Contractor | Name of Supervisor | PGCIL Person /Quest | Remarks
1 | June'25 | 1 | 8/1 | DA-1.5 | Sandy | 2025-06-26 | 2025-06-26 | M/s. Sanjay Construction | Saddam
2 | June'25 | 2 | 8/2 | DA+3 | Sandy | 2025-06-26 | 2025-06-26 | M/s. Sanjay Construction | Saddam
3 | June'25 | 3 | 8/3 | DA+6 | Sandy | 2025-06-26 | 2025-06-26 | M/s. Sanjay Construction | Saddam
4 | June'25 | 4 | 8/4 | DA+3 | Sandy | 2025-06-26 | 2025-06-26 | M/s. Sanjay Construction | Saddam
5 | June'25 | 5 | 8/5 | DA+0 | Sandy | 2025-06-27 | 2025-06-27 | M/s. Sanjay Construction | Saddam
6 | June'25 | 6 | 8/6 | DA+0 | Sandy | 2025-06-27 | 2025-06-27 | M/s. Sanjay Construction | Saddam
7 | June'25 | 7 | 8/7 | DA+3 | Sandy | 2025-06-27 | 2025-06-27 | M/s. Sanjay Construction | Saddam
8 | June'25 | 8 | 8/8 | DA+0 | Sandy | 2025-06-27 | 2025-06-27 | M/s. Sanjay Construction | Saddam
9 | June'25 | 9 | 7/7 | DA-1.5 | Sandy | 2025-06-28 | 2025-06-28 | M/s. Sanjay Construction | Saddam
10 | June'25 | 10 | 7/8 | DA+3 | Sandy | 2025-06-28 | 2025-06-28 | M/s. Sanjay Construction | Saddam
11 | June'25 | 11 | 7/9 | DA+3 | Sandy | 2025-06-28 | 2025-06-28 | M/s. Sanjay Construction | Saddam
12 | June'25 | 12 | 7/10 | DA+0 | Sandy | 2025-06-28 | 2025-06-28 | M/s. Sanjay Construction | Saddam
13 | June'25 | 13 | 7/11 | DA+3 | Sandy | 2025-06-28 | 2025-06-28 | M/s. Sanjay Construction | Saddam
14 | June'25 | 14 | 7/3 | DA+0 | Sandy | 2025-06-29 | 2025-06-29 | M/s. Sanjay Construction | Saddam
15 | June'25 | 15 | 7/5 | DA-1.5 | Sandy | 2025-06-29 | 2025-06-29 | M/s. Sanjay Construction | Saddam
16 | June'25 | 16 | 7/1 | DA+6 | Sandy | 2025-06-30 | 2025-06-30 | M/s. Sanjay Construction | Saddam
17 | June'25 | 17 | 7/2 | DA-1.5 | Sandy | 2025-06-30 | 2025-06-30 | M/s. Sanjay Construction | Saddam
18 | June'25 | 18 | 7/4 | DA+0 | Sandy | 2025-06-30 | 2025-06-30 | M/s. Sanjay Construction | Saddam
19 | June'25 | 19 | 7/6 | DA+0 | Sandy | 2025-06-30 | 2025-06-30 | M/s. Sanjay Construction | Saddam
20 | June'25 | 20 | 6/10 | DA+6 | Sandy | 2025-06-30 | 2025-06-30 | M/s. Sanjay Construction | Saddam
21 | July'25 | 1 | 6/7 | DA+0 | Sandy | 2025-07-01 | 2025-07-01 | M/s. Sanjay Construction | Saddam
22 | July'25 | 2 | 6/9 | DA+3 | Sandy | 2025-07-01 | 2025-07-01 | M/s. Sanjay Construction | Saddam
23 | July'25 | 3 | 6/8 | DA+6 | Sandy | 2025-07-02 | 2025-07-02 | M/s. Sanjay Construction | Saddam
24 | July'25 | 4 | 6/6 | DB1+3 | Sandy | 2025-07-02 | 2025-07-02 | M/s. Sanjay Construction | Saddam
25 | July'25 | 5 | 6/5 | DA+9 | Sandy | 2025-07-02 | 2025-07-02 | M/s. Sanjay Construction | Saddam
26 | July'25 | 6 | 6/4 | DA+3 | Sandy | 2025-07-02 | 2025-07-02 | M/s. Sanjay Construction | Saddam
27 | July'25 | 7 | 6/3 | DA+6 | Sandy | 2025-07-02 | 2025-07-02 | M/s. Sanjay Construction | Saddam
28 | July'25 | 8 | 6/2 | DA+3 | Sandy | 2025-07-02 | 2025-07-02 | M/s. Sanjay Construction | Saddam
29 | July'25 | 9 | 6/1 | DA+3 | Sandy | 2025-07-03 | 2025-07-03 | M/s. Sanjay Construction | Saddam
30 | July'25 | 10 | 6/0 | DB1+0 | Sandy | 2025-07-03 | 2025-07-03 | M/s. Sanjay Construction | Saddam
31 | July'25 | 11 | 5/11 | DA+9 | Sandy | 2025-07-03 | 2025-07-03 | M/s. Sanjay Construction | Saddam
32 | July'25 | 12 | 5/10 | DA+3 | Sandy | 2025-07-03 | 2025-07-03 | M/s. Sanjay Construction | Saddam
33 | July'25 | 13 | 5/9 | DA+3 | Sandy | 2025-07-03 | 2025-07-03 | M/s. Sanjay Construction | Saddam
34 | July'25 | 14 | 11/2 | DA+3 | Sandy | 2025-07-04 | 2025-07-04 | M/s. Sanjay Construction | Saddam
35 | July'25 | 15 | 11/5 | DA-1.5 | Dry | 2025-07-04 | 2025-07-04 | M/s. Sanjay Construction | Saddam
36 | July'25 | 16 | 12/1 | DA+3 | Sandy | 2025-07-05 | 2025-07-05 | M/s. Sanjay Construction | Saddam
37 | July'25 | 17 | 12/2 | DA-1.5 | Sandy | 2025-07-05 | 2025-07-05 | M/s. Sanjay Construction | Saddam
38 | July'25 | 18 | 12/3 | DA+9 | Sandy | 2025-07-05 | 2025-07-05 | M/s. Sanjay Construction | Saddam
39 | July'25 | 19 | 12/4 | DA+9 | Sandy | 2025-07-05 | 2025-07-05 | M/s. Sanjay Construction | Saddam
40 | July'25 | 20 | 19/1 | DA+3 | Sandy | 2025-07-06 | 2025-07-06 | M/s. Sanjay Construction | Saddam
41 | July'25 | 21 | 19/2 | DA+6 | Sandy | 2025-07-06 | 2025-07-06 | M/s. Sanjay Construction | Saddam
42 | July'25 | 22 | 19/3 | DA-1.5 | Sandy | 2025-07-06 | 2025-07-06 | M/s. Sanjay Construction | Saddam
43 | July'25 | 23 | 19/4 | DA+9 | Sandy | 2025-07-06 | 2025-07-06 | M/s. Sanjay Construction | Saddam
44 | July'25 | 24 | 18/5 | DA+0 | Sandy | 2025-07-06 | 2025-07-06 | M/s. Sanjay Construction | Saddam
45 | July'25 | 25 | 19/5 | DA+3 | Sandy | 2025-07-07 | 2025-07-07 | M/s. Sanjay Construction | Saddam
46 | July'25 | 26 | 19/7 | DA+6 | Sandy | 2025-07-07 | 2025-07-07 | M/s. Sanjay Construction | Saddam
47 | July'25 | 27 | 20/0 | DC1+6 | Sandy | 2025-07-07 | 2025-07-07 | M/s. Sanjay Construction | Saddam
48 | July'25 | 28 | 20/1 | DA+6 | Sandy | 2025-07-07 | 2025-07-07 | M/s. Sanjay Construction | Saddam
49 | July'25 | 29 | 20/2 | DA+6 | Sandy | 2025-07-07 | 2025-07-07 | M/s. Sanjay Construction | Saddam
50 | July'25 | 30 | 20/3 | DA-3 | Sandy | 2025-07-07 | 2025-07-07 | M/s. Sanjay Construction | Saddam
51 | July'25 | 31 | 27/2 | DA-1.5 | Sandy | 2025-07-08 | 2025-07-08 | M/s. Sanjay Construction | Saddam
52 | July'25 | 32 | 27/3 | DA-3 | Sandy | 2025-07-08 | 2025-07-08 | M/s. Sanjay Construction | Saddam
53 | July'25 | 33 | 28/4 | DA+0 | Sandy | 2025-07-08 | 2025-07-08 | M/s. Sanjay Construction | Saddam
54 | July'25 | 34 | 28/5 | DA+0 | Sandy | 2025-07-08 | 2025-07-08 | M/s. Sanjay Construction | Saddam
55 | July'25 | 35 | 28/6 | DA+0 | Sandy | 2025-07-08 | 2025-07-08 | M/s. Sanjay Construction | Saddam
56 | July'25 | 36 | 28/7 | DA+6 | Sandy | 2025-07-09 | 2025-07-09 | M/s. Sanjay Construction | Saddam
57 | July'25 | 37 | 29/1 | DA+6 | Sandy | 2025-07-09 | 2025-07-09 | M/s. Sanjay Construction | Saddam
58 | July'25 | 38 | 29/2 | DA+3 | Sandy | 2025-07-09 | 2025-07-09 | M/s. Sanjay Construction | Saddam
59 | July'25 | 39 | 29/7 | DA+6 | Sandy | 2025-07-09 | 2025-07-09 | M/s. Sanjay Construction | Saddam
60 | July'25 | 40 | 29/6 | DA+0 | Sandy | 2025-07-11 | 2025-07-11 | M/s. Sanjay Construction | Saddam
61 | July'25 | 41 | 31/1 | DA+3 | Sandy | 2025-07-11 | 2025-07-11 | M/s. Sanjay Construction | Saddam
62 | July'25 | 42 | 31/2 | DA+3 | Sandy | 2025-07-11 | 2025-07-11 | M/s. Sanjay Construction | Saddam
63 | July'25 | 43 | 31/3 | DA-3 | Sandy | 2025-07-12 | 2025-07-12 | M/s. Sanjay Construction | Saddam
64 | July'25 | 44 | 30/18 | DA+0 | Sandy | 2025-07-12 | 2025-07-12 | M/s. Sanjay Construction | Saddam
65 | July'25 | 45 | 30/8 | DA+3 | Sandy | 2025-07-12 | 2025-07-12 | M/s. Sanjay Construction | Saddam
66 | July'25 | 46 | 30/9 | DB1+0 | Sandy | 2025-07-12 | 2025-07-12 | M/s. Sanjay Construction | Saddam
67 | July'25 | 47 | 30/10 | DA+3 | Sandy | 2025-07-12 | 2025-07-12 | M/s. Sanjay Construction | Saddam
68 | July'25 | 48 | 30/11 | DA+0 | Sandy | 2025-07-12 | 2025-07-12 | M/s. Sanjay Construction | Saddam
69 | July'25 | 49 | 30/12 | DA+6 | Sandy | 2025-07-12 | 2025-07-12 | M/s. Sanjay Construction | Saddam
70 | July'25 | 50 | 30/13 | DA+6 | Sandy | 2025-07-12 | 2025-07-12 | M/s. Sanjay Construction | Saddam
71 | July'25 | 51 | 30/14 | DA+3 | Sandy | 2025-07-12 | 2025-07-12 | M/s. Sanjay Construction | Saddam
72 | July'25 | 52 | 30/4 | DA+3 | Sandy | 2025-07-13 | 2025-07-13 | M/s. Sanjay Construction | Saddam
73 | July'25 | 53 | 30/5 | DA+3 | Sandy | 2025-07-13 | 2025-07-13 | M/s. Sanjay Construction | Saddam
74 | July'25 | 54 | 30/6 | DA+0 | Sandy | 2025-07-13 | 2025-07-13 | M/s. Sanjay Construction | Saddam
75 | July'25 | 55 | 30/7 | DA+3 | Sandy | 2025-07-13 | 2025-07-13 | M/s. Sanjay Construction | Saddam
76 | July'25 | 56 | 31/4 | DA+0 | Sandy | 2025-07-13 | 2025-07-13 | M/s. Sanjay Construction | Saddam
77 | July'25 | 57 | 31/5 | DA+6 | Sandy | 2025-07-13 | 2025-07-13 | M/s. Sanjay Construction | Saddam
78 | July'25 | 58 | 31/6 | DA+6 | Sandy | 2025-07-14 | 2025-07-14 | M/s. Sanjay Construction | Saddam
79 | July'25 | 59 | 28/1 | DA+6 | Sandy | 2025-07-14 | 2025-07-14 | M/s. Sanjay Construction | Saddam
80 | July'25 | 60 | 4/11 | DA+0 | Sandy | 2025-07-16 | 2025-07-16 | M/s. Sanjay Construction | Saddam
81 | July'25 | 61 | 4/12 | DA+3 | Sandy | 2025-07-16 | 2025-07-16 | M/s. Sanjay Construction | Saddam
82 | July'25 | 62 | 4/13 | DA+0 | Sandy | 2025-07-16 | 2025-07-16 | M/s. Sanjay Construction | Saddam
83 | July'25 | 63 | 4/14 | DA+3 | Sandy | 2025-07-17 | 2025-07-17 | M/s. Sanjay Construction | Saddam
84 | July'25 | 64 | 5/3 | DA+3 | Sandy | 2025-07-17 | 2025-07-17 | M/s. Sanjay Construction | Saddam
85 | July'25 | 65 | 5/4 | DA+3 | Sandy | 2025-07-17 | 2025-07-17 | M/s. Sanjay Construction | Saddam
86 | July'25 | 66 | 5/5 | DA+6 | Sandy | 2025-07-17 | 2025-07-17 | M/s. Sanjay Construction | Saddam
87 | July'25 | 67 | 5/8 | DA+6 | Sandy | 2025-07-17 | 2025-07-17 | M/s. Sanjay Construction | Saddam
88 | July'25 | 68 | 11/3 | DA+0 | Sandy | 2025-07-18 | 2025-07-18 | M/s. Sanjay Construction | Saddam
89 | July'25 | 69 | 11/4 | DA+3 | Sandy | 2025-07-18 | 2025-07-18 | M/s. Sanjay Construction | Saddam
90 | July'25 | 70 | 11/6 | DA+3 | Sandy | 2025-07-18 | 2025-07-18 | M/s. Sanjay Construction | Saddam
91 | July'25 | 71 | 12/5 | DA+9 | Sandy | 2025-07-18 | 2025-07-18 | M/s. Sanjay Construction | Saddam
92 | July'25 | 72 | 31/15 | DA+9 | Sandy | 2025-07-23 | 2025-07-23 | M/s. Sanjay Construction | Saddam
93 | July'25 | 73 | 31/14 | DA+3 | Sandy | 2025-07-23 | 2025-07-23 | M/s. Sanjay Construction | Saddam
94 | July'25 | 74 | 31/13 | DA+0 | Sandy | 2025-07-23 | 2025-07-23 | M/s. Sanjay Construction | Saddam
95 | July'25 | 75 | 31/9 | DB1+0 | Sandy | 2025-07-23 | 2025-07-23 | M/s. Sanjay Construction | Saddam
96 | July'25 | 76 | 31/11 | DA+6 | Sandy | 2025-07-23 | 2025-07-23 | M/s. Sanjay Construction | Saddam
97 | July'25 | 77 | 29/5 | DA+3 | Sandy | 2025-07-24 | 2025-07-24 | M/s. Sanjay Construction | Saddam
98 | July'25 | 78 | 29/8 | DA+0 | Sandy | 2025-07-24 | 2025-07-24 | M/s. Sanjay Construction | Saddam
99 | July'25 | 79 | 29/9 | DA+0 | Sandy | 2025-07-24 | 2025-07-24 | M/s. Sanjay Construction | Saddam
100 | July'25 | 80 | 16/2 | DA+0 | Sandy | 2025-07-24 | 2025-07-24 | M/s. Sanjay Construction | Saddam
101 | July'25 | 81 | 41/1 | DA+0 | Sandy | 2025-07-25 | 2025-07-25 | M/s. Sanjay Construction | Saddam
102 | July'25 | 82 | 41/2 | DA+0 | Sandy | 2025-07-25 | 2025-07-25 | M/s. Sanjay Construction | Saddam
103 | July'25 | 83 | 41/3 | DA+6 | Sandy | 2025-07-25 | 2025-07-25 | M/s. Sanjay Construction | Saddam
104 | July'25 | 84 | 41/4 | DA+6 | Sandy | 2025-07-25 | 2025-07-25 | M/s. Sanjay Construction | Saddam
105 | July'25 | 85 | 41/5 | DA+3 | Sandy | 2025-07-25 | 2025-07-25 | M/s. Sanjay Construction | Saddam
106 | July'25 | 86 | 41/6 | DA+3 | Sandy | 2025-07-25 | 2025-07-25 | M/s. Sanjay Construction | Saddam
107 | July'25 | 87 | 37/10 | DA+6 | Sandy | 2025-07-26 | 2025-07-26 | M/s. Sanjay Construction | Saddam
108 | July'25 | 88 | 37/9 | DA-3 | Sandy | 2025-07-26 | 2025-07-26 | M/s. Sanjay Construction | Saddam
109 | July'25 | 89 | 34/4 | DA+9 | Sandy | 2025-07-26 | 2025-07-26 | M/s. Sanjay Construction | Saddam
110 | July'25 | 90 | 31/26 | DA+3 | Sandy | 2025-07-26 | 2025-07-26 | M/s. Sanjay Construction | Saddam
111 | July'25 | 91 | 1A/1 | DA-1.5 | Sandy | 2025-07-28 | 2025-07-28 | M/s. Sanjay Construction | Saddam
112 | July'25 | 92 | 1A/2 | DA-1.5 | Sandy | 2025-07-28 | 2025-07-28 | M/s. Sanjay Construction | Saddam
113 | July'25 | 93 | 1A/3 | DA-3 | Sandy | 2025-07-28 | 2025-07-28 | M/s. Sanjay Construction | Saddam
114 | July'25 | 94 | 4/3 | DA-3 | Sandy | 2025-07-28 | 2025-07-28 | M/s. Sanjay Construction | Saddam
115 | Nov'25 | 1 | 9/0 | DB1+0 | Sandy | 2025-11-07 | 2025-11-07 | M/s. Sanjay Construction | Dinesh Kr. Mahto
116 | Nov'25 | 2 | 9/1 | DA+0 | Sandy | 2025-11-07 | 2025-11-07 | M/s. Sanjay Construction | Dinesh Kr. Mahto
117 | Nov'25 | 3 | 9/2 | DA+6 | Sandy | 2025-11-07 | 2025-11-07 | M/s. Sanjay Construction | Dinesh Kr. Mahto
118 | Nov'25 | 4 | 29/10 | DA+0 | Sandy | 2025-11-08 | 2025-11-08 | M/s. Sanjay Construction | Dinesh Kr. Mahto
119 | Nov'25 | 5 | 29/11 | DA+0 | Sandy | 2025-11-08 | 2025-11-08 | M/s. Sanjay Construction | Dinesh Kr. Mahto
120 | Nov'25 | 6 | 29/12 | DB1+0 | Sandy | 2025-11-08 | 2025-11-08 | M/s. Sanjay Construction | Dinesh Kr. Mahto
121 | Nov'25 | 7 | 29/14 | DA+0 | Sandy | 2025-11-08 | 2025-11-08 | M/s. Sanjay Construction | Dinesh Kr. Mahto
122 | Nov'25 | 8 | 29/15 | DA+0 | Sandy | 2025-11-09 | 2025-11-09 | M/s. Sanjay Construction | Dinesh Kr. Mahto
123 | Nov'25 | 9 | 29/17 | DA+0 | Sandy | 2025-11-09 | 2025-11-09 | M/s. Sanjay Construction | Dinesh Kr. Mahto
124 | Nov'25 | 10 | 29/18 | DA+3 | Sandy | 2025-11-09 | 2025-11-09 | M/s. Sanjay Construction | Dinesh Kr. Mahto
125 | Nov'25 | 11 | 29/19 | DA+3 | Sandy | 2025-11-09 | 2025-11-09 | M/s. Sanjay Construction | Dinesh Kr. Mahto
126 | Nov'25 | 12 | 29/20 | DA+0 | Sandy | 2025-11-09 | 2025-11-09 | M/s. Sanjay Construction | Dinesh Kr. Mahto
127 | Nov'25 | 13 | 29/21 | DA+3 | Sandy | 2025-11-10 | 2025-11-10 | M/s. Sanjay Construction | Dinesh Kr. Mahto
128 | Nov'25 | 14 | 30/0 | DB2+0 | Sandy | 2025-11-10 | 2025-11-10 | M/s. Sanjay Construction | Dinesh Kr. Mahto
129 | Nov'25 | 15 | 30/2 | DA+6 | Sandy | 2025-11-10 | 2025-11-10 | M/s. Sanjay Construction | Dinesh Kr. Mahto
130 | Nov'25 | 16 | 30/16 | DA+6 | Sandy | 2025-11-10 | 2025-11-10 | M/s. Sanjay Construction | Dinesh Kr. Mahto
131 | Nov'25 | 17 | 30/17 | DC2+0 | Sandy | 2025-11-10 | 2025-11-10 | M/s. Sanjay Construction | Dinesh Kr. Mahto
132 | Nov'25 | 18 | 31/0 | DB2+0 | Sandy | 2025-11-10 | 2025-11-10 | M/s. Sanjay Construction | Dinesh Kr. Mahto
133 | Nov'25 | 19 | 31/7 | DA+0 | Sandy | 2025-11-11 | 2025-11-11 | M/s. Sanjay Construction | Dinesh Kr. Mahto
134 | Nov'25 | 20 | 31/8 | DA+6 | Sandy | 2025-11-11 | 2025-11-11 | M/s. Sanjay Construction | Dinesh Kr. Mahto
135 | Nov'25 | 21 | 31/12 | DA+6 | Sandy | 2025-11-11 | 2025-11-11 | M/s. Sanjay Construction | Dinesh Kr. Mahto
136 | Nov'25 | 22 | 31/16 | DA+6 | Sandy | 2025-11-11 | 2025-11-11 | M/s. Sanjay Construction | Dinesh Kr. Mahto
137 | Nov'25 | 23 | 31/17 | DA+9 | Sandy | 2025-11-11 | 2025-11-11 | M/s. Sanjay Construction | Dinesh Kr. Mahto
138 | Nov'25 | 24 | 31/18 | DB1+9 | Sandy | 2025-11-11 | 2025-11-11 | M/s. Sanjay Construction | Dinesh Kr. Mahto
139 | Nov'25 | 25 | 31/19 | DA+3 | Sandy | 2025-11-13 | 2025-11-13 | M/s. Sanjay Construction | Dinesh Kr. Mahto
140 | Nov'25 | 26 | 31/20 | DA-1.5 | Sandy | 2025-11-13 | 2025-11-13 | M/s. Sanjay Construction | Dinesh Kr. Mahto
141 | Nov'25 | 27 | 31/22 | DA+6 | Sandy | 2025-11-13 | 2025-11-13 | M/s. Sanjay Construction | Dinesh Kr. Mahto
142 | Nov'25 | 28 | 31/23 | DA+6 | Sandy | 2025-11-13 | 2025-11-13 | M/s. Sanjay Construction | Dinesh Kr. Mahto
143 | Nov'25 | 29 | 31/24 | DA+9 | Sandy | 2025-11-14 | 2025-11-14 | M/s. Sanjay Construction | Dinesh Kr. Mahto
144 | Nov'25 | 30 | 31/25 | DA-3 | Sandy | 2025-11-14 | 2025-11-14 | M/s. Sanjay Construction | Dinesh Kr. Mahto
145 | Nov'25 | 31 | 35/0 | DB1+9 | Sandy | 2025-11-15 | 2025-11-15 | M/s. Sanjay Construction | Dinesh Kr. Mahto
146 | Nov'25 | 32 | 35/1 | DA+9 | Sandy | 2025-11-15 | 2025-11-15 | M/s. Sanjay Construction | Dinesh Kr. Mahto
147 | Nov'25 | 33 | 35/2 | DA+9 | Sandy | 2025-11-15 | 2025-11-15 | M/s. Sanjay Construction | Dinesh Kr. Mahto
148 | Nov'25 | 34 | 36/2 | DA+9 | Sandy | 2025-11-15 | 2025-11-15 | M/s. Sanjay Construction | Dinesh Kr. Mahto
149 | Nov'25 | 35 | 37/7 | DA-3 | Sandy | 2025-11-16 | 2025-11-16 | M/s. Sanjay Construction | Dinesh Kr. Mahto
150 | Nov'25 | 36 | 39/0 | DB2+9 | Sandy | 2025-11-16 | 2025-11-16 | M/s. Sanjay Construction | Dinesh Kr. Mahto
151 | Nov'25 | 37 | 40/0 | DC1+9 | Sandy | 2025-11-16 | 2025-11-16 | M/s. Sanjay Construction | Dinesh Kr. Mahto
152 | Nov'25 | 38 | 13/0 | DC1+3 | Sandy | 2025-11-17 | 2025-11-17 | M/s. Sanjay Construction | Dinesh Kr. Mahto
153 | Nov'25 | 39 | 16/1 | DA+3 | Sandy | 2025-11-17 | 2025-11-17 | M/s. Sanjay Construction | Dinesh Kr. Mahto
154 | Nov'25 | 40 | 18/2 | DA+3 | Sandy | 2025-11-17 | 2025-11-17 | M/s. Sanjay Construction | Dinesh Kr. Mahto
155 | Nov'25 | 41 | 18/3 | DA+6 | Sandy | 2025-11-17 | 2025-11-17 | M/s. Sanjay Construction | Dinesh Kr. Mahto
156 | Nov'25 | 42 | 18/4 | DA+6 | Sandy | 2025-11-17 | 2025-11-17 | M/s. Sanjay Construction | Dinesh Kr. Mahto
157 | Nov'25 | 43 | 20/5 | DA+0 | Sandy | 2025-11-24 | 2025-11-24 | M/s. Sanjay Construction | Dinesh Kr. Mahto
158 | Nov'25 | 44 | 20/7 | DA+0 | Sandy | 2025-11-24 | 2025-11-24 | M/s. Sanjay Construction | Dinesh Kr. Mahto
159 | Nov'25 | 45 | 23/2 | DA+3 | Sandy | 2025-11-24 | 2025-11-24 | M/s. Sanjay Construction | Dinesh Kr. Mahto
160 | Nov'25 | 46 | 19/0 | DC2+0 | Sandy | 2025-11-24 | 2025-11-24 | M/s. Sanjay Construction | Dinesh Kr. Mahto
161 | Nov'25 | 47 | 4/6 | DA+3 | Sandy | 2025-11-25 | 2025-11-25 | M/s. Sanjay Construction | Dinesh Kr. Mahto
162 | Nov'25 | 48 | 4/8 | DA+9 | Sandy | 2025-11-25 | 2025-11-25 | M/s. Sanjay Construction | Dinesh Kr. Mahto
163 | Nov'25 | 49 | 4/9 | DA+3 | Sandy | 2025-11-25 | 2025-11-25 | M/s. Sanjay Construction | Dinesh Kr. Mahto
164 | Nov'25 | 50 | 4/10 | DA-1.5 | Sandy | 2025-11-25 | 2025-11-25 | M/s. Sanjay Construction | Dinesh Kr. Mahto
165 | Nov'25 | 51 | 3/5 | DA+6 | Sandy | 2025-11-26 | 2025-11-26 | M/s. Sanjay Construction | Dinesh Kr. Mahto
166 | Nov'25 | 52 | 3A/1 | DA+0 | Sandy | 2025-11-26 | 2025-11-26 | M/s. Sanjay Construction | Dinesh Kr. Mahto
167 | Nov'25 | 53 | 3A/2 | DA-1.5 | Sandy | 2025-11-26 | 2025-11-26 | M/s. Sanjay Construction | Dinesh Kr. Mahto
168 | Nov'25 | 54 | 3A/3 | DA-1.5 | Sandy | 2025-11-26 | 2025-11-26 | M/s. Sanjay Construction | Dinesh Kr. Mahto
169 | Nov'25 | 55 | 4/0 | DB2+0 | Sandy | 2025-11-26 | 2025-11-26 | M/s. Sanjay Construction | Dinesh Kr. Mahto
170 | Nov'25 | 56 | 2/5 | DA+0 | Sandy | 2025-11-27 | 2025-11-27 | M/s. Sanjay Construction | Dinesh Kr. Mahto
171 | Nov'25 | 57 | 2/4 | DA+9 | Sandy | 2025-11-27 | 2025-11-27 | M/s. Sanjay Construction | Dinesh Kr. Mahto
172 | Nov'25 | 58 | 2/2 | DA+9 | Sandy | 2025-11-27 | 2025-11-27 | M/s. Sanjay Construction | Dinesh Kr. Mahto
173 | Nov'25 | 59 | 2/1 | DA+6 | Sandy | 2025-11-27 | 2025-11-27 | M/s. Sanjay Construction | Dinesh Kr. Mahto
174 | Nov'25 | 60 | 3A/0 | DD45+0 | Sandy | 2025-11-28 | 2025-11-28 | M/s. Sanjay Construction | Dinesh Kr. Mahto
175 | Nov'25 | 61 | 3/6 | DA+3 | Sandy | 2025-11-28 | 2025-11-28 | M/s. Sanjay Construction | Dinesh Kr. Mahto
176 | Nov'25 | 62 | 3/7 | DA+3 | Sandy | 2025-11-28 | 2025-11-28 | M/s. Sanjay Construction | Dinesh Kr. Mahto
177 | Nov'25 | 63 | 20/4 | DA+0 | Sandy | 2025-11-30 | 2025-11-30 | M/s. Sanjay Construction | Dinesh Kr. Mahto
178 | Nov'25 | 64 | 19/6 | DA+3 | Sandy | 2025-11-30 | 2025-11-30 | M/s. Sanjay Construction | Dinesh Kr. Mahto
179 | Nov'25 | 65 | 11/8 | DA+3 | Sandy | 2025-12-01 | 2025-12-01 | M/s. Sanjay Construction | Dinesh Kr. Mahto
180 | Nov'25 | 66 | 12/0 | DC2+0 | Sandy | 2025-12-01 | 2025-12-01 | M/s. Sanjay Construction | Dinesh Kr. Mahto
181 | Jan'26 | 1 | 13/1 | DA+6 | Sandy | 2026-01-15 | 2026-01-15 | M/s. Sanjay Construction | Saddam
182 | Jan'26 | 2 | 18/1 | DA+6 | Sandy | 2026-01-15 | 2026-01-15 | M/s. Sanjay Construction | Saddam
183 | Jan'26 | 3 | 9/3 | DA+0 | Sandy | 2026-01-15 | 2026-01-15 | M/s. Sanjay Construction | Saddam
184 | Jan'26 | 4 | 20A/0 | DD45+9 | Sandy | 2026-01-15 | 2026-01-15 | M/s. Sanjay Construction | Saddam
185 | Jan'26 | 5 | 21/0 | DC2+3 | Sandy | 2026-01-15 | 2026-01-15 | M/s. Sanjay Construction | Saddam
186 | Jan'26 | 6 | 22/0 | DD60+6 | Sandy | 2026-01-15 | 2026-01-15 | M/s. Sanjay Construction | Saddam
187 | Jan'26 | 7 | 23/0 | DD60+9 | Sandy | 2026-01-15 | 2026-01-15 | M/s. Sanjay Construction | Saddam
188 | Jan'26 | 8 | 23/1 | DA-1.5 | Sandy | 2026-01-15 | 2026-01-15 | M/s. Sanjay Construction | Saddam
189 | Jan'26 | 9 | 4/1 | DA-3 | Sandy | 2026-01-16 | 2026-01-16 | M/s. Sanjay Construction | Saddam
190 | Jan'26 | 10 | 4/2 | DA+6 | Sandy | 2026-01-16 | 2026-01-16 | M/s. Sanjay Construction | Saddam
191 | Jan'26 | 11 | 4/4 | DA+9 | Sandy | 2026-01-16 | 2026-01-16 | M/s. Sanjay Construction | Saddam
192 | Jan'26 | 12 | 4/5 | DA+9 | Sandy | 2026-01-16 | 2026-01-16 | M/s. Sanjay Construction | Saddam
193 | Jan'26 | 13 | 4/7 | DB1+0 | Sandy | 2026-01-16 | 2026-01-16 | M/s. Sanjay Construction | Saddam
194 | Jan'26 | 14 | 2/3 | DA+9 | Sandy | 2026-01-17 | 2026-01-17 | M/s. Sanjay Construction | Saddam
195 | Jan'26 | 15 | 2/6 | DA+9 | Sandy | 2026-01-17 | 2026-01-17 | M/s. Sanjay Construction | Saddam
196 | Jan'26 | 16 | 2A/0 | DB2+3 | Sandy | 2026-01-17 | 2026-01-17 | M/s. Sanjay Construction | Saddam
197 | Jan'26 | 17 | 2A/1 | DA+9 | Sandy | 2026-01-17 | 2026-01-17 | M/s. Sanjay Construction | Saddam
198 | Jan'26 | 18 | 2A/2 | DA-1.5 | Sandy | 2026-01-17 | 2026-01-17 | M/s. Sanjay Construction | Saddam
199 | Jan'26 | 19 | 2A/3 | DA+3 | Sandy | 2026-01-17 | 2026-01-17 | M/s. Sanjay Construction | Saddam
200 | Jan'26 | 20 | 2A/4 | DA+9 | Sandy | 2026-01-17 | 2026-01-17 | M/s. Sanjay Construction | Saddam
201 | Jan'26 | 21 | 2A/5 | DA+9 | Sandy | 2026-01-17 | 2026-01-17 | M/s. Sanjay Construction | Saddam
202 | Jan'26 | 22 | 3/0 | DC2+9 | Sandy | 2026-01-18 | 2026-01-18 | M/s. Sanjay Construction | Saddam
203 | Jan'26 | 23 | 3/1 | DB1+9 | Sandy | 2026-01-18 | 2026-01-18 | M/s. Sanjay Construction | Saddam
204 | Jan'26 | 24 | 3/2 | DA+9 | Sandy | 2026-01-18 | 2026-01-18 | M/s. Sanjay Construction | Saddam
205 | Jan'26 | 25 | 3/3 | DA+9 | Sandy | 2026-01-18 | 2026-01-18 | M/s. Sanjay Construction | Saddam
206 | Jan'26 | 26 | 3/4 | DA-1.5 | Sandy | 2026-01-18 | 2026-01-18 | M/s. Sanjay Construction | Saddam
207 | Jan'26 | 27 | 5/0 | DB1+0 | Sandy | 2026-01-18 | 2026-01-18 | M/s. Sanjay Construction | Saddam
208 | Jan'26 | 28 | 5/1 | DA+6 | Sandy | 2026-01-18 | 2026-01-18 | M/s. Sanjay Construction | Saddam
209 | Jan'26 | 29 | 5/2 | DA+0 | Sandy | 2026-01-18 | 2026-01-18 | M/s. Sanjay Construction | Saddam
210 | Jan'26 | 30 | 5/6 | DA+6 | Sandy | 2026-01-19 | 2026-01-19 | M/s. Sanjay Construction | Saddam
211 | Jan'26 | 31 | 5/7 | DB1+3 | Sandy | 2026-01-19 | 2026-01-19 | M/s. Sanjay Construction | Saddam
212 | Jan'26 | 32 | 8/0 | DC1+0 | Sandy | 2026-01-19 | 2026-01-19 | M/s. Sanjay Construction | Saddam
213 | Jan'26 | 33 | 11/1 | DA-1.5 | Sandy | 2026-01-19 | 2026-01-19 | M/s. Sanjay Construction | Saddam
214 | Jan'26 | 34 | 23/3 | DA+0 | Sandy | 2026-01-20 | 2026-01-20 | M/s. Sanjay Construction | Saddam
215 | Jan'26 | 35 | 27/1 | DB1+9 | Sandy | 2026-01-20 | 2026-01-20 | M/s. Sanjay Construction | Saddam
216 | Jan'26 | 36 | 28/0 | DB2+0 | Sandy | 2026-01-20 | 2026-01-20 | M/s. Sanjay Construction | Saddam
217 | Jan'26 | 37 | 28/2 | DA+3 | Sandy | 2026-01-20 | 2026-01-20 | M/s. Sanjay Construction | Saddam
218 | Jan'26 | 38 | 28/3 | DA+0 | Sandy | 2026-01-20 | 2026-01-20 | M/s. Sanjay Construction | Saddam
219 | Jan'26 | 39 | 29/0 | DB2+0 | Sandy | 2026-01-20 | 2026-01-20 | M/s. Sanjay Construction | Saddam
220 | Jan'26 | 40 | 29/4 | DA+0 | Sandy | 2026-01-20 | 2026-01-20 | M/s. Sanjay Construction | Saddam
221 | Jan'26 | 41 | 29/16 | DA+0 | Sandy | 2026-01-21 | 2026-01-21 | M/s. Sanjay Construction | Saddam
222 | Jan'26 | 42 | 29/22 | DA+3 | Sandy | 2026-01-21 | 2026-01-21 | M/s. Sanjay Construction | Saddam
223 | Jan'26 | 43 | 30/1 | DA+3 | Sandy | 2026-01-21 | 2026-01-21 | M/s. Sanjay Construction | Saddam
224 | Jan'26 | 44 | 30/3 | DA+0 | Sandy | 2026-01-21 | 2026-01-21 | M/s. Sanjay Construction | Saddam
225 | Jan'26 | 45 | 31/27 | DA+3 | Sandy | 2026-01-21 | 2026-01-21 | M/s. Sanjay Construction | Saddam
226 | Jan'26 | 46 | 32/0 | DB2+3 | Sandy | 2026-01-21 | 2026-01-21 | M/s. Sanjay Construction | Saddam
227 | Jan'26 | 47 | 32/1 | DA+9 | Sandy | 2026-01-21 | 2026-01-21 | M/s. Sanjay Construction | Saddam
228 | Jan'26 | 48 | 32/3 | DA+9 | Sandy | 2026-01-22 | 2026-01-22 | M/s. Sanjay Construction | Saddam
229 | Jan'26 | 49 | 32/5 | DA+0 | Sandy | 2026-01-22 | 2026-01-22 | M/s. Sanjay Construction | Saddam
230 | Jan'26 | 50 | 32/6 | DA+3 | Sandy | 2026-01-22 | 2026-01-22 | M/s. Sanjay Construction | Saddam
231 | Jan'26 | 51 | 32/7 | DA+6 | Sandy | 2026-01-22 | 2026-01-22 | M/s. Sanjay Construction | Saddam
232 | Jan'26 | 52 | 33/2 | DA+3 | Sandy | 2026-01-22 | 2026-01-22 | M/s. Sanjay Construction | Saddam
233 | Jan'26 | 53 | 33/3 | DA+9 | Sandy | 2026-01-22 | 2026-01-22 | M/s. Sanjay Construction | Saddam
234 | Jan'26 | 54 | 33A/0 | DC2+0 | Sandy | 2026-01-22 | 2026-01-22 | M/s. Sanjay Construction | Saddam
235 | Jan'26 | 55 | 33/4 | DA+9 | Sandy | 2026-01-23 | 2026-01-23 | M/s. Sanjay Construction | Saddam
236 | Jan'26 | 56 | 34/0 | DD45+9 | Sandy | 2026-01-23 | 2026-01-23 | M/s. Sanjay Construction | Saddam
237 | Jan'26 | 57 | 34/2 | DA+6 | Sandy | 2026-01-23 | 2026-01-23 | M/s. Sanjay Construction | Saddam
238 | Jan'26 | 58 | 34/3 | DA+0 | Sandy | 2026-01-23 | 2026-01-23 | M/s. Sanjay Construction | Saddam
239 | Jan'26 | 59 | 34/6 | DA-3 | Sandy | 2026-01-23 | 2026-01-23 | M/s. Sanjay Construction | Saddam
240 | Jan'26 | 60 | 34/7 | DA+6 | Sandy | 2026-01-24 | 2026-01-24 | M/s. Sanjay Construction | Saddam
241 | Jan'26 | 61 | 34/8 | DA+9 | Sandy | 2026-01-24 | 2026-01-24 | M/s. Sanjay Construction | Saddam
242 | Jan'26 | 62 | 34/9 | DA+9 | Sandy | 2026-01-24 | 2026-01-24 | M/s. Sanjay Construction | Saddam
243 | Jan'26 | 63 | 34/10 | DA+9 | Sandy | 2026-01-24 | 2026-01-24 | M/s. Sanjay Construction | Saddam
244 | Jan'26 | 64 | 35/4 | DA+3 | Sandy | 2026-01-24 | 2026-01-24 | M/s. Sanjay Construction | Saddam
245 | Jan'26 | 65 | 35/6 | DA+9 | Sandy | 2026-01-24 | 2026-01-24 | M/s. Sanjay Construction | Saddam
246 | Jan'26 | 66 | 36/6 | DA+9 | Sandy | 2026-01-27 | 2026-01-27 | M/s. Sanjay Construction | Saddam
247 | Jan'26 | 67 | 36/7 | DA+3 | Sandy | 2026-01-27 | 2026-01-27 | M/s. Sanjay Construction | Saddam
248 | Jan'26 | 68 | 36/8 | DA+3 | Sandy | 2026-01-27 | 2026-01-27 | M/s. Sanjay Construction | Saddam
249 | Jan'26 | 69 | 35/7 | DA-3 | Sandy | 2026-01-28 | 2026-01-28 | M/s. Sanjay Construction | Ramshankar
250 | Jan'26 | 70 | 35/8 | DA+3 | Sandy | 2026-01-28 | 2026-01-28 | M/s. Sanjay Construction | Ramshankar
251 | Jan'26 | 71 | 35/9 | DA+9 | Sandy | 2026-01-28 | 2026-01-28 | M/s. Sanjay Construction | Ramshankar
252 | Jan'26 | 72 | 36/0 | DB1+6 | Sandy | 2026-01-28 | 2026-01-28 | M/s. Sanjay Construction | Ramshankar
253 | Jan'26 | 73 | 36/1 | DA+6 | Sandy | 2026-01-28 | 2026-01-28 | M/s. Sanjay Construction | Ramshankar
254 | Jan'26 | 74 | 40/1 | DA+3 | Sandy | 2026-01-29 | 2026-01-29 | M/s. Sanjay Construction | Ramshankar
255 | Jan'26 | 75 | 40/2 | DA+9 | Sandy | 2026-01-29 | 2026-01-29 | M/s. Sanjay Construction | Ramshankar
256 | Jan'26 | 76 | 38/1 | DA+0 | Sandy | 2026-01-29 | 2026-01-29 | M/s. Sanjay Construction | Ramshankar
257 | Jan'26 | 77 | 38/2 | DA-3 | Sandy | 2026-01-29 | 2026-01-29 | M/s. Sanjay Construction | Ramshankar
258 | Jan'26 | 78 | 37/3 | DA+3 | Sandy | 2026-01-30 | 2026-01-30 | M/s. Sanjay Construction | Ramshankar
259 | Jan'26 | 79 | 37/4 | DA+3 | Sandy | 2026-01-30 | 2026-01-30 | M/s. Sanjay Construction | Ramshankar
260 | Jan'26 | 80 | 37/6 | DA+6 | Sandy | 2026-01-30 | 2026-01-30 | M/s. Sanjay Construction | Ramshankar
261 | Jan'26 | 81 | 37/8 | DA+9 | Sandy | 2026-01-30 | 2026-01-30 | M/s. Sanjay Construction | Ramshankar
262 | Jan'26 | 82 | 38/0 | DB2+0 | Sandy | 2026-01-30 | 2026-01-30 | M/s. Sanjay Construction | Ramshankar
263 | Jan'26 | 83 | 37/0 | DB1+0 | Sandy | 2026-01-31 | 2026-01-31 | M/s. Sanjay Construction | Ramshankar
264 | Jan'26 | 84 | 37/1 | DA+0 | Sandy | 2026-01-31 | 2026-01-31 | M/s. Sanjay Construction | Ramshankar
265 | Jan'26 | 85 | 37/2 | DA+3 | Sandy | 2026-01-31 | 2026-01-31 | M/s. Sanjay Construction | Ramshankar
266 | Jan'26 | 86 | 37/5 | DA+6 | Sandy | 2026-01-31 | 2026-01-31 | M/s. Sanjay Construction | Ramshankar
267 | Jan'26 | 87 | 36/9 | DA+6 | Sandy | 2026-01-31 | 2026-01-31 | M/s. Sanjay Construction | Ramshankar
268 | Jan'26 | 88 | 42/0 | DB1+0 | Sandy | 2026-02-01 | 2026-02-01 | M/s. Sanjay Construction | Ramshankar
269 | Jan'26 | 89 | 43/0 | DC1+0 | Sandy | 2026-02-01 | 2026-02-01 | M/s. Sanjay Construction | Ramshankar
270 |  | 90
271 |  | 91
272 |  | 92
273 |  | 93
274 |  | 94
275 |  | 95
276 |  | 96
277 |  | 97
278 |  | 98
279 |  | 99
280 |  | 100
281 |  | 101
282 |  | 102
283 |  | 103
284 |  | 104
285 |  | 105
286 |  | 106
287 |  | 107
288 |  | 108
289 |  | 109
290 |  | 110
291 |  | 111
292 |  | 112
293 |  | 113
294 |  | 114
295 |  | 115
296 |  | 116
297 |  | 117
298 |  | 118
299 |  | 119
300 |  | 120
301 |  | 121
302 |  | 122
303 |  | 123
304 |  | 124
305 |  | 125
306 |  | 126
307 |  | 127
308 |  | 128
309 |  | 129
310 |  | 130
311 |  | 131
312 |  | 132
313 |  | 133
314 |  | 134
315 |  | 135

## Foundation
KEC International Limited
765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Details of Foundation | [18 empty] | 2026-05-20
Sr. No. | Month | Month Sr. No. | Loc. No. | Type of Tower | Type of Classification | Start | Completed | Name of the Contractor | Name of Supervisor | State | Village | Tehsil | District | ROW Status (Yes/No) | Action Taken for ROW (To Be Filled By POWERGRID) | Start Date | End Date | PGCIL Person /Quest | Remarks
1 | Feb'25 | 1 | 8/1 | DA-1.5 | Sandy | 2025-02-12 | 2025-02-23 | M/s. Sanwariya Technical Developers | Monu Kumar | Rajasthan | DOODIMUKLERA | LUNKARANSAR | BIKANER
2 | Feb'25 | 2 | 8/3 | DA+6 | Sandy | 2025-02-17 | 2025-02-26 | M/s. Sanwariya Technical Developers | Monu Kumar | Rajasthan | JAISAN | LUNKARANSAR | BIKANER
3 | Feb'25 | 3 | 8/6 | DA+0 | Sandy | 2025-02-20 | 2025-02-28 | M/s. MS Construction | Sher Singh Rana | Rajasthan | SADHERAN | LUNKARANSAR | BIKANER
4 | Mar'25 | 1 | 8/5 | DA+0 | Sandy | 2025-02-27 | 2025-03-05 | M/s. MS Construction | Sher Singh Rana | Rajasthan | SADHERAN | LUNKARANSAR | BIKANER
5 | Mar'25 | 2 | 8/2 | DA+3 | Sandy | 2025-03-01 | 2025-03-05 | M/s. Sanwariya Technical Developers | Monu Kumar | Rajasthan | JAISAN | LUNKARANSAR | BIKANER
6 | Mar'25 | 3 | 12/1 | DA+3 | Sandy | 2025-03-01 | 2025-03-07 | M/s. Choudhari Construction | Jagdamba Prasad | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
7 | Mar'25 | 4 | 8/4 | DA+3 | Sandy | 2025-03-05 | 2025-03-10 | M/s. Sanwariya Technical Developers | Sher Singh Rana | Rajasthan | SADHERAN | LUNKARANSAR | BIKANER
8 | Mar'25 | 5 | 12/2 | DA-1.5 | Sandy | 2025-03-05 | 2025-03-10 | M/s. Choudhari Construction | Jagdamba Prasad | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
9 | Mar'25 | 6 | 8/8 | DA+0 | Sandy | 2025-03-05 | 2025-03-10 | M/s. MS Construction | Sher Singh Rana | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
10 | Mar'25 | 7 | 12/3 | DA+9 | Sandy | 2025-03-05 | 2025-03-10 | M/s. Choudhari Construction | Narayan Mohoto | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
11 | Mar'25 | 8 | 6/7 | DA+0 | Sandy | 2025-03-08 | 2025-03-15 | M/s. ProteK Infra | Sher Singh Rana | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
12 | Mar'25 | 9 | 7/6 | DA+0 | Sandy | 2025-03-10 | 2025-03-17 | M/s. Sanwariya Technical Developers | Sujit Choudhary | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
13 | Mar'25 | 10 | 12/4 | DA+9 | Sandy | 2025-03-09 | 2025-03-13 | M/s. Choudhari Construction | Jagdamba Prasad | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
14 | Mar'25 | 11 | 18/5 | DA+0 | Sandy | 2025-03-11 | 2025-03-17 | M/s. Choudhari Construction | Narayan Mohoto | Rajasthan | SURANA | LUNKARANSAR | BIKANER
15 | Mar'25 | 12 | 8/7 | DA+3 | Sandy | 2025-03-17 | 2025-03-24 | M/s. MS Construction | Ankur Gogoi | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
16 | Mar'25 | 13 | 6/8 | DA+6 | Sandy | 2025-03-14 | 2025-03-20 | M/s. ProteK Infra | Sher Singh Rana | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
17 | Mar'25 | 14 | 18/4 | DA+6 | Sandy | 2025-03-14 | 2025-03-18 | M/s. Choudhari Construction | Jagdamba Prasad | Rajasthan | SURANA | LUNKARANSAR | BIKANER
18 | Mar'25 | 15 | 18/3 | DA+6 | Sandy | 2025-03-16 | 2025-03-21 | M/s. Choudhari Construction | Narayan Mohoto | Rajasthan | SURANA | LUNKARANSAR | BIKANER
19 | Mar'25 | 16 | 7/5 | DA-1.5 | Sandy | 2025-03-16 | 2025-03-21 | M/s. Sanwariya Technical Developers | Sujit Choudhary | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
20 | Mar'25 | 17 | 19/1 | DA+3 | Sandy | 2025-03-18 | 2025-03-23 | M/s. Choudhari Construction | Sher Singh Rana | Rajasthan | SURANA | LUNKARANSAR | BIKANER
21 | Mar'25 | 18 | 19/2 | DA+6 | Sandy | 2025-03-20 | 2025-03-24 | M/s. Choudhari Construction | Jagdamba Prasad | Rajasthan | SURANA | LUNKARANSAR | BIKANER
22 | Mar'25 | 19 | 19/3 | DA-1.5 | Sandy | 2025-03-21 | 2025-03-25 | M/s. Choudhari Construction | Narayan Mohoto | Rajasthan | KAKARICHCHHA | LUNKARANSAR | BIKANER
23 | Mar'25 | 20 | 7/7 | DA-1.5 | Sandy | 2025-03-20 | 2025-03-26 | M/s. Sanwariya Technical Developers | Sujit Choudhary | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
24 | Mar'25 | 21 | 6/10 | DA+6 | Sandy | 2025-03-21 | 2025-03-26 | M/s. ProteK Infra | Sher Singh Rana | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
25 | Mar'25 | 22 | 19/6 | DA+3 | Sandy | 2025-03-23 | 2025-03-27 | M/s. Choudhari Construction | Jagdamba Prasad | Rajasthan | KAKARICHCHHA | LUNKARANSAR | BIKANER
26 | Mar'25 | 23 | 9/2 | DA+6 | Sandy | 2025-03-24 | 2025-03-30 | M/s. MS Construction | Ankur Gogoi | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
27 | Mar'25 | 24 | 19/4 | DA+9 | Sandy | 2025-03-23 | 2025-03-28 | M/s. Choudhari Construction | Sher Singh Rana | Rajasthan | KAKARICHCHHA | LUNKARANSAR | BIKANER
28 | Mar'25 | 25 | 19/7 | DA+6 | Sandy | 2025-03-26 | 2025-03-30 | M/s. Choudhari Construction | Jagdamba Prasad | Rajasthan | KAKARICHCHHA | LUNKARANSAR | BIKANER
29 | Mar'25 | 26 | 20/1 | DA+6 | Sandy | 2025-03-27 | 2025-03-31 | M/s. Choudhari Construction | Sher Singh Rana | Rajasthan | KALKAL MUKLERA | LUNKARANSAR | BIKANER
30 | Apr'25 | 1 | 7/8 | DA+3 | Sandy | 2025-03-26 | 2025-04-01 | M/s. Sanwariya Technical Developers | Sujit Choudhary | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
31 | Apr'25 | 2 | 6/9 | DA+3 | Sandy | 2025-03-25 | 2025-04-02 | M/s. ProteK Infra | Narayan Mohoto | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
32 | Apr'25 | 3 | 9/3 | DA+0 | Sandy | 2025-03-29 | 2025-04-03 | M/s. Choudhari Construction | Jagdamba Prasad | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
33 | Apr'25 | 4 | 20/5 | DA+0 | Sandy | 2025-03-31 | 2025-04-04 | M/s. Choudhari Construction | Sher Singh Rana | Rajasthan | KALKAL MUKLERA | LUNKARANSAR | BIKANER
34 | Apr'25 | 5 | 7/9 | DA+3 | Sandy | 2025-04-01 | 2025-04-06 | M/s. Sanwariya Technical Developers | Sujit Choudhary | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
35 | Apr'25 | 6 | 30/6 | DA+0 | Sandy | 2025-04-03 | 2025-04-07 | M/s. Choudhari Construction | Narayan Mohoto | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
36 | Apr'25 | 7 | 20/2 | DA+6 | Sandy | 2025-04-04 | 2025-04-10 | M/s. Choudhari Construction | Sher Singh Rana | Rajasthan | KALKAL MUKLERA | LUNKARANSAR | BIKANER
37 | Apr'25 | 8 | 7/11 | DA+3 | Sandy | 2025-04-05 | 2025-04-11 | M/s. Sanwariya Technical Developers | Sujit Choudhary | Rajasthan | DOODIMU KLERA | LUNKARANSAR | BIKANER
38 | Apr'25 | 9 | 30/5 | DA+3 | Sandy | 2025-04-07 | 2025-04-13 | M/s. Choudhari Construction | Narayan Mohoto/Sonu Kumar | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
39 | Apr'25 | 10 | 6/4 | DA+3 | Sandy | 2025-04-06 | 2025-04-13 | M/s. MS Construction | Jagdamba Prasad | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
40 | Apr'25 | 11 | 20/3 | DA-3 | Sandy | 2025-04-09 | 2025-04-15 | M/s. Choudhari Construction | Sher Singh Rana | Rajasthan | KALKAL MUKLERA | LUNKARANSAR | BIKANER
41 | Apr'25 | 12 | 30/4 | DA+3 | Sandy | 2025-04-11 | 2025-04-15 | M/s. Choudhari Construction | Narayan Mohoto/Sonu Kumar | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
42 | Apr'25 | 13 | 7/10 | DA+0 | Sandy | 2025-04-10 | 2025-04-16 | M/s. Sanwariya Technical Developers | Sujit Choudhary | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
43 | Apr'25 | 14 | 19/5 | DA+3 | Sandy | 2025-04-14 | 2025-04-19 | M/s. Choudhari Construction | Sher Singh Rana | Rajasthan | KAKARICHCHHA | LUNKARANSAR | BIKANER
44 | Apr'25 | 15 | 30/7 | DA+3 | Sandy | 2025-04-14 | 2025-04-19 | M/s. Choudhari Construction | Narayan Mohoto/Sonu Kumar | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
45 | Apr'25 | 16 | 7/4 | DA+0 | Sandy | 2025-04-16 | 2025-04-21 | M/s. Sanwariya Technical Developers | Sujit Choudhary | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
46 | Apr'25 | 17 | 30/8 | DA+3 | Sandy | 2025-04-19 | 2025-04-23 | M/s. Choudhari Construction | Narayan Mohoto | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
47 | Apr'25 | 18 | 28/2 | DA+3 | Sandy | 2025-04-18 | 2025-04-24 | M/s. Ruhila Brothers | Sujit Choudhary/Ankur Gogoi | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER
48 | Apr'25 | 19 | 20/6 | DA+9 | Sandy | 2025-04-20 | 2025-04-25 | M/s. Choudhari Construction | Sher Singh Rana | Rajasthan | LUNKARANSAR | LUNKARANSAR | BIKANER
49 | Apr'25 | 20 | 30/10 | DA+3 | Sandy | 2025-04-22 | 2025-04-26 | M/s. Choudhari Construction | Narayan Mohoto/Sonu Kumar | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
50 | Apr'25 | 21 | 7/3 | DA+0 | Sandy | 2025-04-21 | 2025-04-28 | M/s. Sanwariya Technical Developers | Jagdamba Prasad | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
51 | Apr'25 | 22 | 28/1 | DA+6 | Sandy | 2025-04-22 | 2025-04-28 | M/s. Ruhila Brothers | Sujit Choudhary/Sonu Kumar | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER
52 | Apr'25 | 23 | 23/3 | DA+0 | Sandy | 2025-04-25 | 2025-04-30 | M/s. Choudhari Construction | Sher Singh Rana | Rajasthan | DHANI BHOPALARAM | LUNKARANSAR | BIKANER
53 | Apr'25 | 24 | 30/12 | DA+6 | Sandy | 2025-04-26 | 2025-04-30 | M/s. Choudhari Construction | Sonu Kumar | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
54 | May'25 | 1 | 7/2 | DA-1.5 | Sandy | 2025-04-28 | 2025-05-04 | M/s. Sanwariya Technical Developers | Ankur Gogoi | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
55 | May'25 | 2 | 23/2 | DA+3 | Sandy | 2025-04-25 | 2025-05-04 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | LUNKARANSAR | LUNKARANSAR | BIKANER
56 | May'25 | 3 | 30/11 | DA+0 | Sandy | 2025-04-29 | 2025-05-04 | M/s. Choudhari Construction | Sonu Kumar | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
57 | May'25 | 4 | 30/13 | DA+6 | Sandy | 2025-05-02 | 2025-05-07 | M/s. Choudhari Construction | Sonu Kumar | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
58 | May'25 | 5 | 30/14 | DA+3 | Sandy | 2025-05-04 | 2025-05-09 | M/s. Choudhari Construction | Sonu Kumar | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
59 | May'25 | 6 | 7/1 | DA+6 | Sandy | 2025-05-05 | 2025-05-10 | M/s. Sanwariya Technical Developers | Ankur Gogoi | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
60 | May'25 | 7 | 30/18 | DA+0 | Sandy | 2025-05-06 | 2025-05-11 | M/s. Choudhari Construction | Narayan Mahto | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
61 | May'25 | 8 | 11/4 | DA+3 | Sandy | 2025-05-05 | 2025-05-12 | M/s. ProteK Infra | Sujit Choudhary | Rajasthan | SHARAH BEECHHARWAS | LUNKARANSAR | BIKANER
62 | May'25 | 9 | 31/1 | DA+3 | Sandy | 2025-05-10 | 2025-05-14 | M/s. Choudhari Construction | Narayan Mahto | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
63 | May'25 | 10 | 31/2 | DA+3 | Sandy | 2025-05-11 | 2025-05-15 | M/s. Choudhari Construction | Rohit Sharma | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
64 | May'25 | 11 | 31/3 | DA-3 | Sandy | 2025-05-12 | 2025-05-17 | M/s. Choudhari Construction | Rohit Sharma | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
65 | May'25 | 12 | 6/1 | DA+3 | Sandy | 2025-05-09 | 2025-05-17 | M/s. Sanwariya Technical Developers | Ankur Gogoi | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
66 | May'25 | 13 | 31/4 | DA+0 | Sandy | 2025-05-14 | 2025-05-18 | M/s. Choudhari Construction | Ajhar Ali | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
67 | May'25 | 14 | 5/8 | DA+6 | Sandy | 2025-05-14 | 2025-05-19 | M/s. Karni Kripa Construction Company | Sher Singh Rana | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
68 | May'25 | 15 | 28/4 | DA+0 | Sandy | 2025-03-27 | 2025-05-19 | M/s. Kamla Traders | Narayan Mahto | Rajasthan | KALOO | LUNKARANSAR | BIKANER
69 | May'25 | 16 | 31/5 | DA+6 | Sandy | 2025-05-16 | 2025-05-20 | M/s. Choudhari Construction | Ajhar Ali | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
70 | May'25 | 17 | 11/2 | DA+3 | Sandy | 2025-05-08 | 2025-05-21 | M/s. ProteK Infra | Ankur Gogoi | Rajasthan | SHARAH BEECHHARWAS | LUNKARANSAR | BIKANER
71 | May'25 | 18 | 5/10 | DA+3 | Sandy | 2025-05-17 | 2025-05-23 | M/s. Karni Kripa Construction Company | Sher Singh Rana | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
72 | May'25 | 19 | 31/6 | DA+6 | Sandy | 2025-05-20 | 2025-05-23 | M/s. Choudhari Construction | Ajhar Ali | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
73 | May'25 | 20 | 6/2 | DA+3 | Sandy | 2025-05-16 | 2025-05-25 | M/s. Sanwariya Technical Developers | Sher Singh Rana | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
74 | May'25 | 21 | 11/3 | DA+0 | Sandy | 2025-05-18 | 2025-05-26 | M/s. Protek Infra | Sujit Choudhary | Rajasthan | SHARAH BEECHHARWAS | LUNKARANSAR | BIKANER
75 | May'25 | 22 | 31/7 | DA+0 | Sandy | 2025-05-22 | 2025-05-26 | M/s. Choudhari Construction | Ajhar Ali | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
76 | May'25 | 23 | 28/7 | DA+6 | Sandy | 2025-05-19 | 2025-05-27 | M/s. Kamla Traders | Narayan Mahto | Rajasthan | KALOO | LUNKARANSAR | BIKANER
77 | June'25 | 1 | 28/6 | DA+0 | Sandy | 2025-05-27 | 2025-06-01 | M/s. Kamla Traders | Ajhar Ali | Rajasthan | KALOO | LUNKARANSAR | BIKANER
78 | June'25 | 2 | 6/3 | DA+6 | Sandy | 2025-05-25 | 2025-06-01 | M/s. Sanwariya Technical Developers | Rohit Sharma | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
79 | June'25 | 3 | 11/5 | DA-1.5 | Dry | 2025-05-22 | 2025-06-04 | M/s. ProteK Infra | Sonu Kumar | Rajasthan | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER
80 | June'25 | 4 | 31/8 | DA+6 | Sandy | 2025-05-31 | 2025-06-04 | M/s. Choudhari Construction | Narayan Mahto | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
81 | June'25 | 5 | 28/3 | DA+0 | Sandy | 2025-06-01 | 2025-06-06 | M/s. Kamla Traders | Ajhar Ali | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER
82 | June'25 | 6 | 31/12 | DA+6 | Sandy | 2025-06-03 | 2025-06-07 | M/s. Choudhari Construction | Narayan Mahto | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
83 | June'25 | 7 | 5/9 | DA+3 | Sandy | 2025-05-21 | 2025-06-08 | M/s. Karni Kripa Construction Company | Sher Singh Rana | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
84 | June'25 | 8 | 31/11 | DA+6 | Sandy | 2025-06-01 | 2025-06-10 | M/s. Choudhari Construction | Narayan Mahto | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
85 | June'25 | 9 | 6/6 | DB1+3 | Sandy | 2025-06-01 | 2025-06-11 | M/s. Sanwariya Technical Developers | Sonu Kumar | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
86 | June'25 | 10 | 31/13 | DA+0 | Sandy | 2025-06-05 | 2025-06-11 | M/s. Choudhari Construction | Narayan Mahto | Rajasthan | KANWALASAR | SARDARSHAHAR | CHURU
87 | June'25 | 11 | 28/5 | DA+0 | Sandy | 2025-06-05 | 2025-06-11 | M/s. Kamla Traders | Ajhar Ali | Rajasthan | KALOO | LUNKARANSAR | BIKANER
88 | June'25 | 12 | 5/11 | DA+9 | Sandy | 2025-06-08 | 2025-06-11 | M/s. Karni Kripa Construction Company | Chetram | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
89 | June'25 | 13 | 5/5 | DA+6 | Sandy | 2025-06-11 | 2025-06-16 | M/s. Karni Kripa Construction Company | Narayan Mahto | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
90 | June'25 | 14 | 6/5 | DA+9 | Sandy | 2025-06-11 | 2025-06-16 | M/s. Sanwariya Technical Developers | Sonu Kumar | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
91 | June'25 | 15 | 31/9 | DB1+0 | Sandy | 2025-06-10 | 2025-06-17 | M/s. Choudhari Construction | Rohit Sharma | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
92 | June'25 | 16 | 27/2 | DA-1.5 | Sandy | 2025-06-11 | 2025-06-17 | M/s. Kamla Traders | Chetram | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER
93 | June'25 | 17 | 30/9 | DB1+0 | Sandy | 2025-06-11 | 2025-06-18 | M/s. Choudhari Construction | Rohit Sharma | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
94 | June'25 | 18 | 5/4 | DA+3 | Sandy | 2025-06-15 | 2025-06-18 | M/s. Karni Kripa Construction Company | Narayan Mahto | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
95 | June'25 | 19 | 27/3 | DA-3 | Sandy | 2025-06-16 | 2025-06-20 | M/s. Kamla Traders | Chetram | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER
96 | June'25 | 20 | 6/0 | DB1+0 | Sandy | 2025-06-15 | 2025-06-22 | M/s. Sanwariya Technical Developers | Sonu Kumar | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
97 | June'25 | 21 | 5/3 | DA+3 | Sandy | 2025-06-16 | 2025-06-23 | M/s. Karni Kripa Construction Company | Sujit Choudhary | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
98 | June'25 | 22 | 19/0 | DC2+0 | Sandy | 2025-06-15 | 2025-06-26 | M/s. Choudhari Construction | Narayan Mahto | Rajasthan | SURANA | LUNKARANSAR | BIKANER
99 | June'25 | 23 | 29/1 | DA+6 | Sandy | 2025-06-18 | 2025-06-26 | M/s. Kuri Construction Company | Chetram | Rajasthan | KALOO | LUNKARANSAR | BIKANER
100 | June'25 | 24 | 4/14 | DA+3 | Sandy | 2025-06-23 | 2025-06-26 | M/s. Sanwariya Technical Developers | Ankur Gogoi | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
101 | June'25 | 25 | 5/2 | DA+0 | Sandy | 2025-06-23 | 2025-06-26 | M/s. Karni Kripa Construction Company | Sujit Choudhary | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
102 | June'25 | 26 | 20/0 | DC1+6 | Sandy | 2025-06-22 | 2025-06-30 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | KAKARICHCHHA | LUNKARANSAR | BIKANER
103 | June'25 | 27 | 34/4 | DA+9 | Sandy | 2025-06-22 | 2025-06-30 | M/s. Kamla Traders | Sonu Kumar | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
104 | July'25 | 1 | 41/6 | DA+3 | Sandy | 2025-06-27 | 2025-07-01 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
105 | July'25 | 2 | 29/2 | DA+3 | Sandy | 2025-06-21 | 2025-07-03 | M/s. Kuri Construction Company | Chetram | Rajasthan | KALOO | LUNKARANSAR | BIKANER
106 | July'25 | 3 | 5/1 | DA+6 | Sandy | 2025-06-26 | 2025-07-03 | M/s. Sanwariya Technical Developers | Sujit Choudhary | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
107 | July'25 | 4 | 29/7 | DA+6 | Sandy | 2025-06-27 | 2025-07-04 | M/s. Om Mahadev | Ajhar Ali | Rajasthan | KALOO | LUNKARANSAR | BIKANER
108 | July'25 | 5 | 12/5 | DA+9 | Sandy | 2025-06-30 | 2025-07-04 | M/s. Choudhari Construction | Ankur Gogoi | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
109 | July'25 | 6 | 4/13 | DA+0 | Sandy | 2025-06-29 | 2025-07-05 | M/s. Sanwariya Technical Developers | Ankur Gogoi | Rajasthan | MAKADASAR | LUNKARANSAR | BIKANER
110 | July'25 | 7 | 41/5 | DA+3 | Sandy | 2025-07-02 | 2025-07-05 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
111 | July'25 | 8 | 11/6 | DA+3 | Sandy | 2025-06-30 | 2025-07-07 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER
112 | July'25 | 9 | 29/3 | DA+6 | Sandy | 2025-06-26 | 2025-07-09 | M/s. Kuri Construction Company | Chetram | Rajasthan | KALOO | LUNKARANSAR | BIKANER
113 | July'25 | 10 | 41/4 | DA+6 | Sandy | 2025-07-06 | 2025-07-09 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
114 | July'25 | 11 | 4/11 | DA+0 | Sandy | 2025-07-06 | 2025-07-09 | M/s. Sanwariya Technical Developers | Ankur Gogoi | Rajasthan | MAKADASAR | LUNKARANSAR | BIKANER
115 | July'25 | 12 | 16/2 | DA+0 | Sandy | 2025-07-06 | 2025-07-10 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | JAKHARWALA | LUNKARANSAR | BIKANER
116 | July'25 | 13 | 29/6 | DA+0 | Sandy | 2025-06-29 | 2025-07-10 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | KALOO | LUNKARANSAR | BIKANER
117 | July'25 | 14 | 29/4 | DA+0 | Sandy | 2025-06-30 | 2025-07-12 | M/s. Kuri Construction Company | Chetram | Rajasthan | KALOO | LUNKARANSAR | BIKANER
118 | July'25 | 15 | 4/12 | DA+3 | Sandy | 2025-07-08 | 2025-07-13 | M/s. Sanwariya Technical Developers | Ankur Gogoi | Rajasthan | MAKADASAR | LUNKARANSAR | BIKANER
119 | July'25 | 16 | 41/3 | DA+6 | Sandy | 2025-07-09 | 2025-07-14 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
120 | July'25 | 17 | 29/8 | DA+0 | Sandy | 2025-07-07 | 2025-07-15 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | KALOO | LUNKARANSAR | BIKANER
121 | July'25 | 18 | 1A/1 | DA-1.5 | Sandy | 2025-07-06 | 2025-07-15 | M/s. Shree Shyam Construction | Sujit Choudhary | Rajasthan | KELAN | CHHATARGARH | BIKANER
122 | July'25 | 19 | 37/10 | DA+6 | Sandy | 2025-07-06 | 2025-07-16 | M/s. Kamla Traders | Sonu Kumar | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
123 | July'25 | 20 | 4/3 | DA-3 | Sandy | 2025-07-13 | 2025-07-17 | M/s. Sanwariya Technical Developers | Sher Singh Rana | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
124 | July'25 | 21 | 31/26 | DA+3 | Sandy | 2025-07-04 | 2025-07-17 | M/s. Veer Tejaji Construction Company | Narayan Mahto | Rajasthan | MALSISAR | SARDARSHAHAR | CHURU
125 | July'25 | 22 | 37/9 | DA-3 | Sandy | 2025-07-11 | 2025-07-18 | M/s. Kamla Traders | Sonu Kumar | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
126 | July'25 | 23 | 41/1 | DA+0 | Sandy | 2025-07-15 | 2025-07-18 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
127 | July'25 | 24 | 29/5 | DA+3 | Sandy | 2025-07-11 | 2025-07-19 | M/s. Kuri Construction Company | Monu Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
128 | July'25 | 25 | 41/2 | DA+0 | Sandy | 2025-07-14 | 2025-07-20 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
129 | July'25 | 26 | 1A/3 | DA-3 | Sandy | 2025-07-15 | 2025-07-20 | M/s. Shree Shyam Construction | Sher Singh Rana | Rajasthan | KELAN | CHHATARGARH | BIKANER
130 | July'25 | 27 | 29/9 | DA+0 | Sandy | 2025-07-15 | 2025-07-20 | M/s. Om Mahadev | Monu Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
131 | July'25 | 28 | 31/14 | DA+3 | Sandy | 2025-07-04 | 2025-07-21 | M/s. Naganaray Construction Company | Chetram | Rajasthan | KANWALASAR | SARDARSHAHAR | CHURU
132 | July'25 | 29 | 1A/2 | DA-1.5 | Sandy | 2025-07-15 | 2025-07-22 | M/s. Shree Shyam Construction | Sher Singh Rana | Rajasthan | KELAN | CHHATARGARH | BIKANER
133 | July'25 | 30 | 31/15 | DA+9 | Sandy | 2025-06-29 | 2025-07-23 | M/s. Naganaray Construction Company | Chetram | Rajasthan | KANWALASAR | SARDARSHAHAR | CHURU
134 | July'25 | 31 | 29/10 | DA+0 | Sandy | 2025-07-18 | 2025-07-25 | M/s. Om Mahadev | Monu Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
135 | July'25 | 32 | 29/11 | DA+0 | Sandy | 2025-07-19 | 2025-07-25 | M/s. Kuri Construction Company | Sujit Choudhary | Rajasthan | KALOO | LUNKARANSAR | BIKANER
136 | July'25 | 33 | 40/2 | DA+9 | Sandy | 2025-07-21 | 2025-07-25 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
137 | July'25 | 34 | 37/8 | DA+9 | Sandy | 2025-07-17 | 2025-07-26 | M/s. Kamla Traders | Sonu Kumar | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
138 | July'25 | 35 | 31/24 | DA+9 | Sandy | 2025-07-18 | 2025-07-29 | M/s. Veer Tejaji Construction Company | Chetram | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
139 | July'25 | 36 | 2/2 | DA+9 | Sandy | 2025-07-23 | 2025-07-29 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | KELAN | CHHATARGARH | BIKANER
140 | July'25 | 37 | 40/3 | DA+3 | Sandy | 2025-07-25 | 2025-07-29 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
141 | July'25 | 38 | 4/0 | DB2+0 | Sandy | 2025-07-20 | 2025-07-30 | M/s. Sanwariya Technical Developers | Sher Singh Rana | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
142 | July'25 | 39 | 31/20 | DA-1.5 | Sandy | 2025-07-18 | 2025-07-31 | M/s. Shree Krish Construction | Chetram | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
143 | July'25 | 40 | 29/0 | DB2+0 | Sandy | 2025-07-25 | 2025-08-01 | M/s. Om Mahadev | Monu Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
144 | July'25 | 41 | 29/12 | DB1+0 | Sandy | 2025-07-25 | 2025-08-01 | M/s. Kuri Construction Company | Saddam Maliya | Rajasthan | KALOO | LUNKARANSAR | BIKANER
145 | July'25 | 42 | 31/19 | DA+3 | Sandy | 2025-07-25 | 2025-08-01 | M/s. Naganaray Construction Company | Anshu Kumar | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
146 | Aug'25 | 1 | 37/7 | DA-3 | Sandy | 2025-07-25 | 2025-08-02 | M/s. Kamla Traders | Sonu Kumar | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
147 | Aug'25 | 2 | 40/4 | DA+6 | Sandy | 2025-07-27 | 2025-08-03 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
148 | Aug'25 | 3 | 3A/3 | DA-1.5 | Sandy | 2025-07-27 | 2025-08-03 | M/s. Sanwariya Technical Developers | Sher Singh Rana | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
149 | Aug'25 | 4 | 2/4 | DA+9 | Sandy | 2025-07-31 | 2025-08-03 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | KELAN | CHHATARGARH | BIKANER
150 | Aug'25 | 5 | 29/20 | DA+0 | Sandy | 2025-07-31 | 2025-08-05 | M/s. Om Mahadev | Monu Kumar | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
151 | Aug'25 | 6 | 31/16 | DA+6 | Sandy | 2025-07-31 | 2025-08-05 | M/s. Naganaray Construction Company | Chetram | Rajasthan | KANWALASAR | SARDARSHAHAR | CHURU
152 | Aug'25 | 7 | 34/6 | DA-3 | Sandy | 2025-07-21 | 2025-08-06 | M/s. N V Infra | Sujit Choudhary | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
153 | Aug'25 | 8 | 29/15 | DA+0 | Sandy | 2025-07-31 | 2025-08-07 | M/s. Kuri Construction Company | Monu Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
154 | Aug'25 | 9 | 31/21 | DA+3 | Sandy | 2025-07-27 | 2025-08-07 | M/s. Shree Krish Construction | Saddam Maliya | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
155 | Aug'25 | 10 | 31/23 | DA+6 | Sandy | 2025-07-27 | 2025-08-07 | M/s. Veer Tejaji Construction Company | Chetram | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
156 | Aug'25 | 11 | 3A/2 | DA-1.5 | Sandy | 2025-08-03 | 2025-08-07 | M/s. Sanwariya Technical Developers | Sher Singh Rana | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
157 | Aug'25 | 12 | 2/5 | DA+0 | Sandy | 2025-08-03 | 2025-08-08 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | KELAN | CHHATARGARH | BIKANER
158 | Aug'25 | 13 | 30/2 | DA+6 | Sandy | 2025-08-05 | 2025-08-13 | M/s. Om Mahadev | Chetram | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
159 | Aug'25 | 14 | 2/1 | DA+6 | Sandy | 2025-07-22 | 2025-08-13 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | KELAN | CHHATARGARH | BIKANER
160 | Aug'25 | 15 | 3A/1 | DA+0 | Sandy | 2025-08-07 | 2025-08-14 | M/s. Sanwariya Technical Developers | Sher Singh Rana | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
161 | Aug'25 | 16 | 34/5 | DA+6 | Sandy | 2025-08-08 | 2025-08-14 | M/s. N V Infra | Sujit Choudhary | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
162 | Aug'25 | 17 | 9/1 | DA+0 | Sandy | 2025-08-17 | 2025-08-21 | M/s. Sanwariya Technical Developers | Ankur Gogoi | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
163 | Aug'25 | 18 | 30/16 | DA+6 | Sandy | 2025-08-14 | 2025-08-22 | M/s. Choudhari Construction | Saddam Maliya | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
164 | Aug'25 | 19 | 31/22 | DA+6 | Sandy | 2025-08-08 | 2025-08-22 | M/s. Veer Tejaji Construction Company | Chetram | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
165 | Aug'25 | 20 | 34/3 | DA+0 | Sandy | 2025-08-11 | 2025-08-23 | M/s. Shree Krish Construction | Sujit Choudhary | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
166 | Aug'25 | 21 | 9/0 | DB1+0 | Sandy | 2025-08-22 | 2025-08-28 | M/s. Sanwariya Technical Developers | Anshu Kumar | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
167 | Aug'25 | 22 | 41/0 | DC1+0 | Sandy | 2025-08-03 | 2025-08-28 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
168 | Aug'25 | 23 | 34/7 | DA+6 | Sandy | 2025-08-16 | 2025-08-29 | M/s. N V Infra | Sujit Choudhary | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
169 | Sep'25 | 1 | 4/5 | DA+9 | Sandy | 2025-08-22 | 2025-09-03 | M/s. Shree Shyam Construction | Anshu Kumar | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
170 | Sep'25 | 2 | 29/18 | DA+3 | Sandy | 2025-08-27 | 2025-09-03 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
171 | Sep'25 | 3 | 36/9 | DA+6 | Sandy | 2025-08-29 | 2025-09-03 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
172 | Sep'25 | 4 | 37/6 | DA+6 | Sandy | 2025-08-27 | 2025-09-06 | M/s. Kamla Traders | Chetram | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
173 | Sep'25 | 5 | 8/0 | DC1+0 | Sandy | 2025-08-29 | 2025-09-06 | M/s. Sanwariya Technical Developers | Anshu Kumar | Rajasthan | DOODIMUKLERA | LUNKARANSAR | BIKANER
174 | Sep'25 | 6 | 36/8 | DA+3 | Sandy | 2025-09-04 | 2025-09-06 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
175 | Sep'25 | 7 | 34/2 | DA+6 | Sandy | 2025-08-25 | 2025-09-09 | M/s. Shree Krish Construction | Chetram | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
176 | Sep'25 | 8 | 29/14 | DA+0 | Sandy | 2025-09-04 | 2025-09-11 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | KALOO | LUNKARANSAR | BIKANER
177 | Sep'25 | 9 | 36/7 | DA+3 | Sandy | 2025-09-07 | 2025-09-11 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
178 | Sep'25 | 10 | 37/5 | DA+6 | Sandy | 2025-09-07 | 2025-09-16 | M/s. Kamla Traders | Chetram | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
179 | Sep'25 | 11 | 7/0 | DB1+3 | Sandy | 2025-09-07 | 2025-09-16 | M/s. Sanwariya Technical Developers | Anshu Kumar | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
180 | Sep'25 | 12 | 4/6 | DA+3 | Sandy | 2025-09-11 | 2025-09-16 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
181 | Sep'25 | 13 | 36/6 | DA+9 | Sandy | 2025-09-12 | 2025-09-16 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
182 | Sep'25 | 14 | 36/5 | DA+6 | Sandy | 2025-09-18 | 2025-09-21 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
183 | Sep'25 | 15 | 4/8 | DA+9 | Sandy | 2025-09-18 | 2025-09-22 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER | Yes |  | 2025-08-13 | 2025-09-18
184 | Sep'25 | 16 | 13/0 | DC1+3 | Sandy | 2025-09-19 | 2025-09-23 | M/s. Sanwariya Technical Developers | Anshu Kumar | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
185 | Sep'25 | 17 | 4/9 | DA+3 | Sandy | 2025-09-23 | 2025-09-25 | M/s. Shree Shyam Construction | Anshu Kumar | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
186 | Sep'25 | 18 | 36/4 | DA+9 | Sandy | 2025-09-23 | 2025-09-26 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
187 | Sep'25 | 19 | 36/3 | DA+9 | Sandy | 2025-09-26 | 2025-09-29 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
188 | Sep'25 | 20 | 29/19 | DA+3 | Sandy | 2025-09-24 | 2025-10-01 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER | Yes |  | 2025-08-01 | 2025-09-24
189 | Sep'25 | 21 | 4/10 | DA-1.5 | Sandy | 2025-09-27 | 2025-10-01 | M/s. Shree Shyam Construction | Anshu Kumar | Rajasthan | MAKADASAR | CHHATARGARH | BIKANER
190 | Oct'25 | 1 | 34/9 | DA+9 | Sandy | 2025-09-28 | 2025-10-04 | M/s. Kuri Construction Company | Chetram | Rajasthan | LODSAR | SARDARSHAHAR | CHURU
191 | Oct'25 | 2 | 37/0 | DB1+0 | Sandy | 2025-09-29 | 2025-10-04 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
192 | Oct'25 | 3 | 4/7 | DB1+0 | Sandy | 2025-10-04 | 2025-10-09 | M/s. Shree Shyam Construction | Anshu Kumar | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER | Yes |  | 2025-08-13 | 2025-10-04
193 | Oct'25 | 4 | 36/2 | DA+9 | Sandy | 2025-10-04 | 2025-10-12 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU | Yes |  | 2025-08-27 | 2025-09-26
194 | Oct'25 | 5 | 34/10 | DA+9 | Sandy | 2025-10-04 | 2025-10-12 | M/s. Kuri Construction Company | Chetram | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
195 | Oct'25 | 6 | 20/4 | DA+0 | Sandy | 2025-10-09 | 2025-10-12 | M/s. Sanwariya Technical Developers | Sher Singh Rana | Rajasthan | KALKAL MUKLERA | LUNKARANSAR | BIKANER | Yes |  | 2025-03-17 | 2025-09-26
196 | Oct'25 | 7 | 37/2 | DA+3 | Sandy | 2025-10-13 | 2025-10-16 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
197 | Oct'25 | 8 | 30/0 | DB2+0 | Sandy | 2025-10-04 | 2025-10-17 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | RAJPURA HUDAAN | LUNKARANSAR | BIKANER | Yes |  | 2025-08-01 | 2025-10-04
198 | Oct'25 | 9 | 18/2 | DA+3 | Sandy | 2025-10-14 | 2025-10-17 | M/s. Sanwariya Technical Developers | Ankur Gogoi | Rajasthan | SURANA | LUNKARANSAR | BIKANER | Yes
199 | Oct'25 | 10 | 37/3 | DA+3 | Sandy | 2025-10-16 | 2025-10-18 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
200 | Oct'25 | 11 | 31/17 | DA+9 | Sandy | 2025-10-12 | 2025-10-19 | M/s. Choudhari Construction | Raghu Kr. Mahto | Rajasthan | KANWALASAR | SARDARSHAHAR | CHURU
201 | Oct'25 | 12 | 3/1 | DB1+9 | Sandy | 2025-10-10 | 2025-10-23 | M/s. Shree Shyam Construction | Deepak Kr. Mahto | Rajasthan | AMBARAN | CHHATARGARH | BIKANER
202 | Oct'25 | 13 | 29/13 | DA+0 | Sandy | 2025-09-18 | 2025-10-25 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | KALOO | LUNKARANSAR | BIKANER | Yes |  | 2025-08-01 | 2025-10-16
203 | Oct'25 | 14 | 35/0 | DB1+9 | Sandy | 2025-10-13 | 2025-10-25 | M/s. Kuri Construction Company | Narayan Kr. Mahto | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
204 | Oct'25 | 15 | 31/18 | DB1+9 | Sandy | 2025-10-18 | 2025-10-26 | M/s. Choudhari Construction | Raghu Kr. Mahto | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
205 | Oct'25 | 16 | 37/4 | DA+3 | Sandy | 2025-10-23 | 2025-10-26 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
206 | Oct'25 | 17 | 12/0 | DC2+0 | Sandy | 2025-10-17 | 2025-10-27 | M/s. Sanwariya Technical Developers | Montu Biswas | Rajasthan | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER | Yes |  | 2025-03-03 | 2025-10-17
207 | Oct'25 | 18 | 3/2 | DA+9 | Sandy | 2025-10-23 | 2025-10-28 | M/s. Shree Shyam Construction | Deepak Kr. Mahto | Rajasthan | AMBARAN | CHHATARGARH | BIKANER
208 | Oct'25 | 19 | 31/0 | DB2+0 | Sandy | 2025-10-22 | 2025-10-30 | M/s. Choudhari Construction | Raghu Kr. Mahto | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
209 | Oct'25 | 20 | 9/4 | DA+3 | Sandy | 2025-10-27 | 2025-10-30 | M/s. Sanwariya Technical Developers | Montu Biswas | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
210 | Oct'25 | 21 | 3/3 | DA+9 | Sandy | 2025-10-27 | 2025-10-30 | M/s. Shree Shyam Construction | Deepak Kr. Mahto | Rajasthan | AMBARAN | CHHATARGARH | BIKANER
211 | Oct'25 | 22 | 40/1 | DA+3 | Sandy | 2025-10-28 | 2025-10-30 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
212 | Oct'25 | 23 | 29/21 | DA+3 | Sandy | 2025-10-24 | 2025-11-01 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | RAJPURA HUDAAN | LUNKARANSAR | BIKANER
213 | Oct'25 | 24 | 35/1 | DA+9 | Sandy | 2025-10-26 | 2025-11-01 | M/s. Kuri Construction Company | Narayan Kr. Mahto | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
214 | Oct'25 | 25 | 3/4 | DA-1.5 | Sandy | 2025-10-31 | 2025-11-02 | M/s. Shree Shyam Construction | Deepak Kr. Mahto | Rajasthan | AMBARAN | CHHATARGARH | BIKANER
215 | Nov'25 | 1 | 37/1 | DA+0 | Sandy | 2025-10-27 | 2025-11-03 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | HALASAR | SARDARSHAHAR | CHURU | Yes |  | 2025-08-27 | 2025-10-28
216 | Nov'25 | 2 | 30/17 | DC2+0 | Sandy | 2025-10-27 | 2025-11-04 | M/s. Choudhari Construction | Raghu Kr. Mahto | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
217 | Nov'25 | 3 | 11/1 | DA-1.5 | Sandy | 2025-11-01 | 2025-11-05 | M/s. Sanwariya Technical Developers | Sher Singh Rana | Rajasthan | SHARAH BEECHHARWAS | LUNKARANSAR | BIKANER
218 | Nov'25 | 4 | 3/5 | DA+6 | Sandy | 2025-11-02 | 2025-11-06 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | AMBARAN | CHHATARGARH | BIKANER
219 | Nov'25 | 5 | 35/2 | DA+9 | Sandy | 2025-11-01 | 2025-11-07 | M/s. Kuri Construction Company | Narayan Kr. Mahto | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
220 | Nov'25 | 6 | 29/17 | DA+0 | Sandy | 2025-10-30 | 2025-11-09 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
221 | Nov'25 | 7 | 3/6 | DA+3 | Sandy | 2025-11-06 | 2025-11-09 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | AMBARAN | CHHATARGARH | BIKANER
222 | Nov'25 | 8 | 40/0 | DC1+9 | Sandy | 2025-11-04 | 2025-11-10 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
223 | Nov'25 | 9 | 16/1 | DA+3 | Sandy | 2025-11-06 | 2025-11-11 | M/s. Sanwariya Technical Developers | Sher Singh Rana | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
224 | Nov'25 | 10 | 31/25 | DA-3 | Sandy | 2025-11-05 | 2025-11-12 | M/s. Choudhari Construction | Raghu Kr. Mahto | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
225 | Nov'25 | 11 | 3/7 | DA+3 | Sandy | 2025-11-09 | 2025-11-12 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
226 | Nov'25 | 12 | 35/3 | DA+3 | Sandy | 2025-11-08 | 2025-11-13 | M/s. Kuri Construction Company | Narayan Kr. Mahto | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
227 | Nov'25 | 13 | 39/0 | DB2+9 | Sandy | 2025-11-09 | 2025-11-14 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
228 | Nov'25 | 14 | 11/8 | DA+3 | Sandy | 2025-11-14 | 2025-11-16 | M/s. Sanwariya Technical Developers | Sher Singh Rana | Rajasthan | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER
229 | Nov'25 | 15 | 38/2 | DA-3 | Sandy | 2025-11-14 | 2025-11-16 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR
230 | Nov'25 | 16 | 31/27 | DA+3 | Sandy | 2025-11-10 | 2025-11-17 | M/s. Choudhari Construction | Ramesh Kumar Mahto | Rajasthan | MALSISAR | SARDARSHAHAR | CHURU
231 | Nov'25 | 17 | 30/1 | DA+3 | Sandy | 2025-11-10 | 2025-11-18 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
232 | Nov'25 | 18 | 3A/0 | DD45+0 | Sandy | 2025-11-13 | 2025-11-19 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
233 | Nov'25 | 19 | 20/7 | DA+0 | Sandy | 2025-11-18 | 2025-11-21 | M/s. Sanwariya Technical Developers | Deepak Kr. Mahto | Rajasthan | LUNKARANSAR | LUNKARANSAR | BIKANER
234 | Nov'25 | 20 | 38/0 | DB2+0 | Sandy | 2025-11-16 | 2025-11-22 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
235 | Nov'25 | 21 | 29/16 | DA+0 | Sandy | 2025-11-09 | 2025-11-24 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
236 | Nov'25 | 22 | 38/1 | DA+0 | Sandy | 2025-11-23 | 2025-11-24 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
237 | Nov'25 | 23 | 32/0 | DB2+3 | Sandy | 2025-11-14 | 2025-11-25 | M/s. Choudhari Construction | Deepak Kr. Mahto | Rajasthan | MALSISAR | SARDARSHAHAR | CHURU
238 | Nov'25 | 24 | 32/4 | DA+6 | Sandy | 2025-11-24 | 2025-11-28 | M/s. Choudhari Construction | Deepak Kr. Mahto | Rajasthan | KEEKASAR | SARDARSHAHAR | CHURU
239 | Nov'25 | 25 | 3/0 | DC2+9 | Sandy | 2025-11-20 | 2025-11-29 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | KELAN | CHHATARGARH | BIKANER
240 | Nov'25 | 26 | 34/8 | DA+9 | Sandy | 2025-11-25 | 2025-11-29 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
241 | Nov'25 | 27 | 21/0 | DC2+3 | Sandy | 2025-11-24 | 2025-12-01 | M/s. Sanwariya Technical Developers | Mantu Bishvash | Rajasthan | LUNKARANSAR | LUNKARANSAR | BIKANER
242 | Nov'25 | 28 | 32/1 | DA+9 | Sandy | 2025-11-27 | 2025-12-01 | M/s. Choudhari Construction | Deepak Kr. Mahto | Rajasthan | MALSISAR | SARDARSHAHAR | CHURU
243 | Nov'25 | 29 | 32/3 | DA+9 | Sandy | 2025-11-20 | 2025-12-02 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | KEEKASAR | SARDARSHAHAR | CHURU
244 | Nov'25 | 30 | 5/0 | DB1+0 | Sandy | 2025-11-26 | 2025-12-02 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
245 | Nov'25 | 31 | 2A/5 | DA+9 | Sandy | 2025-11-29 | 2025-12-02 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | KELAN | CHHATARGARH | BIKANER
246 | Nov'25 | 32 | 35/5 | DA+9 | Sandy | 2025-11-30 | 2025-12-03 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
247 | Dec'25 | 1 | 32/5 | DA+0 | Sandy | 2025-11-30 | 2025-12-04 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | SONPALSAR | SARDARSHAHAR | CHURU
248 | Dec'25 | 2 | 2A/4 | DA+9 | Sandy | 2025-12-01 | 2025-12-05 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | KELAN | CHHATARGARH | BIKANER
249 | Dec'25 | 3 | 32/6 | DA+3 | Sandy | 2025-12-02 | 2025-12-06 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | SONPALSAR | SARDARSHAHAR | CHURU
250 | Dec'25 | 4 | 35/4 | DA+3 | Sandy | 2025-12-03 | 2025-12-07 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
251 | Dec'25 | 5 | 4/4 | DA+9 | Sandy | 2025-12-04 | 2025-12-07 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
252 | Dec'25 | 6 | 30/3 | DA+0 | Sandy | 2025-11-24 | 2025-12-08 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
253 | Dec'25 | 7 | 2A/3 | DA+3 | Sandy | 2025-12-05 | 2025-12-09 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | KELAN | CHHATARGARH | BIKANER
254 | Dec'25 | 8 | 35/6 | DA+9 | Sandy | 2025-12-07 | 2025-12-10 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
255 | Dec'25 | 9 | 2A/2 | DA-1.5 | Sandy | 2025-12-06 | 2025-12-12 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | KELAN | CHHATARGARH | BIKANER
256 | Dec'25 | 10 | 4/2 | DA+6 | Sandy | 2025-12-06 | 2025-12-12 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
257 | Dec'25 | 11 | 20A/0 | DD45+9 | Sandy | 2025-12-01 | 2025-12-13 | M/s. Sanwariya Technical Developers | Ramesh Kumar Mahto | Rajasthan | LUNKARANSAR | LUNKARANSAR | BIKANER
258 | Dec'25 | 12 | 4/1 | DA-3 | Sandy | 2025-12-11 | 2025-12-14 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
259 | Dec'25 | 13 | 35/8 | DA+3 | Sandy | 2025-12-11 | 2025-12-14 | M/s. Karni Kripa Construction Company | Narayan Kr. Mahto | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
260 | Dec'25 | 14 | 32/7 | DA+6 | Sandy | 2025-12-09 | 2025-12-16 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | SONPALSAR | SARDARSHAHAR | CHURU
261 | Dec'25 | 15 | 2A/1 | DA+9 | Sandy | 2025-12-14 | 2025-12-16 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | KELAN | CHHATARGARH | BIKANER
262 | Dec'25 | 16 | 28/0 | DB2+0 | Sandy | 2025-12-02 | 2025-12-17 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER
263 | Dec'25 | 17 | 33/2 | DA+3 | Sandy | 2025-12-11 | 2025-12-17 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | SONPALSAR | SARDARSHAHAR | CHURU
264 | Dec'25 | 18 | 23/1 | DA-1.5 | Sandy | 2025-12-13 | 2025-12-17 | M/s. Sanwariya Technical Developers | Ramesh Kumar Mahto | Rajasthan | LUNKARANSAR | LUNKARANSAR | BIKANER
265 | Dec'25 | 19 | 35/7 | DA-3 | Sandy | 2025-12-14 | 2025-12-17 | M/s. Karni Kripa Construction Company | Narayan Kr. Mahto | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
266 | Dec'25 | 20 | 5/6 | DA+6 | Sandy | 2025-12-15 | 2025-12-19 | M/s. Shree Shyam Construction | Sonu Kumar | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
267 | Dec'25 | 21 | 35/9 | DA+9 | Sandy | 2025-12-18 | 2025-12-21 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
268 | Dec'25 | 22 | 33/4 | DA+9 | Sandy | 2025-12-20 | 2025-12-23 | M/s. Choudhari Construction | Surjit Choudhary | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
269 | Dec'25 | 23 | 2A/0 | DB2+3 | Sandy | 2025-12-17 | 2025-12-25 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | KELAN | CHHATARGARH | BIKANER
270 | Dec'25 | 24 | 5/7 | DB1+3 | Sandy | 2025-12-19 | 2025-12-26 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
271 | Dec'25 | 25 | 36/0 | DB1+6 | Sandy | 2025-12-21 | 2025-12-26 | M/s. Karni Kripa Construction Company | Rohit Kumar | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
272 | Dec'25 | 26 | 22/0 | DD60+6 | Sandy | 2025-12-18 | 2025-12-27 | M/s. Sanwariya Technical Developers | Ramesh Kumar Mahto | Rajasthan | LUNKARANSAR | LUNKARANSAR | BIKANER
273 | Dec'25 | 27 | 27/1 | DB1+9 | Sandy | 2025-12-18 | 2025-12-27 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER
274 | Dec'25 | 28 | 2/6 | DA+9 | Sandy | 2025-12-25 | 2025-12-30 | M/s. Shree Shyam Construction | Sonu Kumar | Rajasthan | KELAN | CHHATARGARH | BIKANER
275 | Dec'25 | 29 | 36/1 | DA+6 | Sandy | 2025-12-26 | 2025-12-30 | M/s. Karni Kripa Construction Company | Rohit Kumar | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
276 | Dec'25 | 30 | 29/22 | DA+3 | Sandy | 2025-12-25 | 2025-12-31 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | RAJPURA HUDAAN | LUNKARANSAR | BIKANER
277 | Dec'25 | 31 | 23/0 | DD60+9 | Sandy | 2025-12-21 | 2026-01-04 | M/s. Sanwariya Technical Developers | Ramesh Kumar Mahto | Rajasthan | LUNKARANSAR | LUNKARANSAR | BIKANER
278 | Dec'25 | 32 | 2/3 | DA+9 | Sandy | 2025-12-30 | 2026-01-03 | M/s. Shree Shyam Construction | Sonu Kumar | Rajasthan | KELAN | CHHATARGARH | BIKANER
280 | Jan'26 | 1 | 33A/0 | DC2+0 | Sandy | 2025-12-30 | 2026-01-05 | M/s. Choudhari Construction | Surjit Choudhary | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
279 | Jan'26 | 2 | 18/1 | DA+6 | Sandy | 2026-01-05 | 2026-01-11 | M/s. Om Mahadev | Saddam Maliya | Rajasthan | SURANA | LUNKARANSAR | BIKANER
281 | Jan'26 | 3 | 42/0 | DB1+0 | Sandy | 2026-01-04 | 2026-01-11 | M/s. Karni Kripa Construction Company | Raghu Kr. Mahto | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
282 | Jan'26 | 4 | 13/1 | DA+6 | Sandy | 2026-01-05 | 2026-01-12 | M/s. Sanwariya Technical Developers | Dular Chand Mahto | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
283 | Jan'26 | 5 | 34/0 | DD45+9 | Sandy | 2026-01-04 | 2026-01-13 | M/s. Choudhari Construction | Rohit Kumar | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
284 | Jan'26 | 6 | 43/0 | DC1+0 | Sandy | 2026-01-11 | 2026-01-16 | M/s. Karni Kripa Construction Company | Raghu Kr. Mahto | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
285 | Jan'26 | 7 | 2/0 | DD60+3 | Sandy | 2025-12-30 | 2026-01-20 | M/s. Shree Shyam Construction | Ankur Gogoi | Rajasthan | KELAN | CHHATARGARH | BIKANER
286 | Jan'26 | 8 | 33/3 | DA+9 | Sandy | 2026-01-15 | 2026-01-21 | M/s. Choudhari Construction | Rohit Kumar | Rajasthan | SONPALSAR | SARDARSHAHAR | CHURU
287 | Jan'26 | 9 | 33/1 | DA+9 | Sandy | 2026-01-28 | 2026-01-31 | M/s. Choudhari Construction | Rohit Kumar | Rajasthan | SONPALSAR | SARDARSHAHAR | CHURU
288 | Jan'26 | 10 | 10/0 | DD60+25 | Sandy | 2026-01-17 | 2026-02-02 | M/s. Sanwariya Technical Developers | Ankur Gogoi | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
289 | Feb'26 | 1 | 16/3 | DA+0 | Sandy | 2026-02-03 | 2026-02-07 | M/s. Sanwariya Technical Developers | Ankur Gogoi | Rajasthan | JAKHARWALA | LUNKARANSAR | BIKANER
290 | Feb'26 | 2 | 32/8 | DA+6 | Sandy | 2026-02-15 | 2026-02-19 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | SONPALSAR | SARDARSHAHAR | CHURU
291 | Feb'26 | 3 | 32/9 | DA+9 | Sandy | 2026-02-15 | 2026-02-22 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | SONPALSAR | SARDARSHAHAR | CHURU
292 | Mar'26 | 1 | 33/0 | DB2+3 | Sandy | 2026-02-24 | 2026-03-03 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | SONPALSAR | SARDARSHAHAR | CHURU
293 | Mar'26 | 2 | 44/0 | DB2+6 | Sandy | 2026-02-27 | 2026-03-09 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
294 | Mar'26 | 3 | 32/2 | DA+3 | Sandy | 2026-03-12 | 2026-03-15 | M/s. Choudhari Construction | Rohit Sharma | Rajasthan | KEEKASAR | SARDARSHAHAR | CHURU
295 | Mar'26 | 4 | 17/0 | DD60+0 | Sandy | 2026-03-22 | 2026-04-03 | M/s. Choudhari Construction | Ankur Gogoi | Rajasthan | JAKHARWALA | LUNKARANSAR | BIKANER
296 | Mar'26 | 5 | 47/0 | DD60+18 | Sandy | 2026-03-27 | 2026-04-08 | M/s. Karni Kripa Construction Company | Rohit Sharma | Rajasthan | 0 | SARDARSHAHAR | CHURU
297 | Mar'26 | 6 | 18/0 | DD60+0 | Sandy | 2026-04-03 | 2026-04-12 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | JAKHARWALA | LUNKARANSAR | BIKANER
298 | Apr'26 | 1 | 44/1 | DA-3 | Sandy | 2026-04-09 | 2026-04-15 | M/s. Karni Kripa Construction Company | Sujit Choudhary | Rajasthan | 0 | SARDARSHAHAR | CHURU
299 | Apr'26 | 2 | 46/0 | DD60+18 | Sandy | 2026-02-12 | 2026-04-24 | M/s. Choudhari Construction | Sujit Choudhary | Rajasthan | 0 | SARDARSHAHAR | CHURU
300 | Apr'26 | 3 | 45/0 | DC2+9 | Sandy | 2026-04-14 | 2026-04-24 | M/s. Karni Kripa Construction Company | Narayan Kr. Mahto | Rajasthan | #N/A | #N/A | #N/A
301 | Apr'26 | 4 | 34/1 | DA+6 | Sandy | 2026-04-14 | 2026-04-29 | M/s. Choudhari Construction | Rohit Sharma | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
302 | May'26 | 1 | 11/7 | DA+3 | Sandy | 2026-05-02 | 2026-05-09 | M/s. Choudhari Construction | Ankur Gogoi | Rajasthan | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER
303 | May'26 | 2 | 27/0 | DD60+35 | Sandy | 2026-05-02 |  | M/s. Karni Kripa Construction Company |  | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER
304 | May'26 | 3 | 11/0 | DD60+18 | Sandy | 2026-05-14 |  | M/s. Choudhari Construction |  | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
305 | May'26 | 4 | 16/0 | DB2+0 | Sandy | 2026-04-13 |  | M/s. Choudhari Construction |  | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
306 | May'26 | 5 | 1A/0 | DD45+0 | Sandy | 2026-05-20 |  | M/s. Shree Shyam Construction |  | Rajasthan | KELAN | CHHATARGARH | BIKANER
307 | May'26 | 6 | 31/10 | DA+6 | Sandy | 2026-05-18 |  | M/s. Karni Kripa Construction Company |  | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
308 | May'26 | 7 | 25/1 | DA+9 | Sandy |  |  |  |  | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER
309 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
310 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
311 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
312 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
313 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
314 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
315 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
316 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
317 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
318 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
319 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
320 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
321 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
322 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
323 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
324 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
325 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
326 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
327 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
328 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
329 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
330 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
331 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
332 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
333 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
334 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
335 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
336 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
337 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
338 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
339 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
340 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
341 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
342 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
343 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
344 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
345 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
346 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
347 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
348 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
349 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
350 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
351 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
352 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
353 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A

## Erection Compiled
KEC International Limited
765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Details of Erection | [18 empty] | 2026-05-20
Sr. No. | Month | Month Sr. No. | Location No. | Type of Tower | Tower Weight | Starting Date | Completion Date | Gang Name | Name of Supervisor | State | Village | Tehsil | District | ROW Status (Yes/No) | Action Taken for ROW (To Be Filled By POWERGRID) | Start Date | End Date | PGCIL Person /Quest | Remarks
1 | Aug'25 | 1 | 8/3 | DA+6 | 43.804 | 2025-07-25 | 2025-08-10 | M/s. Kavya Enterprises | Narayan Mahto | Rajasthan | JAISAN | LUNKARANSAR | BIKANER
2 | Aug'25 | 2 | 8/8 | DA+0 | 36.16 | 2025-08-11 | 2025-08-20 | M/s. Kavya Enterprises | Narayan Mahto | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
3 | Aug'25 | 3 | 7/9 | DA+3 | 37.931 | 2025-08-13 | 2025-08-20 | M/s. Punam Kumari | Choturam Meena | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
4 | Aug'25 | 4 | 18/5 | DA+0 | 36.16 | 2025-08-18 | 2025-08-25 | M/s. Jwala Singh | Monu Kumar | Rajasthan | SURANA | LUNKARANSAR | BIKANER
5 | Aug'25 | 5 | 7/8 | DA+3 | 37.931 | 2025-08-21 | 2025-08-26 | M/s. Punam Kumari | Ajhar Ali | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
6 | Aug'25 | 6 | 8/7 | DA+3 | 37.931 | 2025-08-21 | 2025-08-27 | M/s. Kavya Enterprises | Narayan Mahto | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
7 | Sep'25 | 1 | 6/1 | DA+3 | 37.931 | 2025-08-21 | 2025-09-01 | M/s. Punam Kumari | Choturam Meena | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
8 | Sep'25 | 2 | 7/6 | DA+0 | 36.16 | 2025-08-26 | 2025-09-01 | M/s. Punam Kumari | Ajhar Ali | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
9 | Sep'25 | 3 | 19/1 | DA+3 | 37.931 | 2025-08-26 | 2025-09-03 | M/s. Jwala Singh | Sonu Kumar | Rajasthan | SURANA | LUNKARANSAR | BIKANER | Yes |  | 2025-08-30 | 2025-09-01
10 | Sep'25 | 4 | 8/6 | DA+0 | 36.16 | 2025-08-27 | 2025-09-03 | M/s. Kavya Enterprises | Narayan Mahto | Rajasthan | SADHERAN | LUNKARANSAR | BIKANER
11 | Sep'25 | 5 | 19/5 | DA+3 | 37.931 | 2025-08-31 | 2025-09-07 | M/s. Jwala Singh | Sonu Kumar | Rajasthan | KAKARICHCHHA | LUNKARANSAR | BIKANER
12 | Sep'25 | 6 | 8/5 | DA+0 | 36.16 | 2025-09-04 | 2025-09-10 | M/s. Kavya Enterprises | Narayan Mahto | Rajasthan | SADHERAN | LUNKARANSAR | BIKANER
13 | Sep'25 | 7 | 7/1 | DA+6 | 43.804 | 2025-09-02 | 2025-09-11 | M/s. Punam Kumari | Ajhar Ali | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER | Yes |  | 2025-09-03 | 2025-09-04
14 | Sep'25 | 8 | 31/2 | DA+3 | 37.931 | 2025-09-02 | 2025-09-12 | M/s. Punam Kumari | Raj Kishor | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
15 | Sep'25 | 9 | 19/4 | DA+9 | 45.697 | 2025-09-08 | 2025-09-13 | M/s. Jwala Singh | Mahendra | Rajasthan | KAKARICHCHHA | LUNKARANSAR | BIKANER
16 | Sep'25 | 10 | 7/4 | DA+0 | 36.16 | 2025-09-12 | 2025-09-16 | M/s. Punam Kumari | Dhiraj Kumar | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
17 | Sep'25 | 11 | 9/2 | DA+6 | 43.804 | 2025-09-11 | 2025-09-19 | M/s. Kavya Enterprises | Narayan Mahto | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
18 | Sep'25 | 12 | 31/1 | DA+3 | 37.931 | 2025-09-13 | 2025-09-20 | M/s. Punam Kumari | Raj Kishor | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
19 | Sep'25 | 13 | 19/7 | DA+6 | 43.804 | 2025-09-14 | 2025-09-22 | M/s. Jwala Singh | Mahendra | Rajasthan | KAKARICHCHHA | LUNKARANSAR | BIKANER
20 | Sep'25 | 14 | 7/3 | DA+0 | 36.16 | 2025-09-18 | 2025-09-23 | M/s. Punam Kumari | Dhiraj Kumar | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
21 | Sep'25 | 15 | 9/3 | DA+0 | 36.16 | 2025-09-20 | 2025-09-24 | M/s. Kavya Enterprises | Narayan Mahto | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
22 | Sep'25 | 16 | 30/18 | DA+0 | 36.16 | 2025-09-21 | 2025-09-27 | M/s. Punam Kumari | Raj Kishor | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
23 | Sep'25 | 17 | 19/6 | DA+3 | 37.931 | 2025-09-23 | 2025-09-27 | M/s. Jwala Singh | Mahendra | Rajasthan | KAKARICHCHHA | LUNKARANSAR | BIKANER
24 | Oct'25 | 1 | 28/1 | DA+6 | 43.804 | 2025-09-24 | 2025-10-03 | M/s. Punam Kumari | Dhiraj Kumar | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER | Yes |  | 2025-09-11 | 2025-09-24
25 | Oct'25 | 2 | 30/7 | DA+3 | 37.931 | 2025-09-28 | 2025-10-04 | M/s. Punam Kumari | Raj Kishor | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER | Yes |  | 2025-09-11 | 2025-09-26
26 | Oct'25 | 3 | 20/1 | DA+6 | 43.804 | 2025-09-28 | 2025-10-04 | M/s. Jwala Singh | Mahendra | Rajasthan | KALKAL MUKLERA | LUNKARANSAR | BIKANER
27 | Oct'25 | 4 | 28/5 | DA+0 | 36.16 | 2025-10-03 | 2025-10-08 | M/s. Punam Kumari | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER | Yes |  | 2025-09-11 | 2025-10-03
28 | Oct'25 | 5 | 9/0 | DB1+0 | 55.451 | 2025-09-25 | 2025-10-09 | M/s. Kavya Enterprises | Narayan Mahto | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
29 | Oct'25 | 6 | 20/2 | DA+6 | 43.804 | 2025-10-05 | 2025-10-12 | M/s. Jwala Singh | Mahendra | Rajasthan | KALKAL MUKLERA | LUNKARANSAR | BIKANER
30 | Oct'25 | 7 | 30/2 | DA+6 | 43.804 | 2025-10-05 | 2025-10-12 | M/s. Punam Kumari | Raj Kishor | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
31 | Oct'25 | 8 | 12/1 | DA+3 | 37.931 | 2025-10-10 | 2025-10-18 | M/s. Kavya Enterprises | Narayan Mahto | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
32 | Oct'25 | 9 | 28/2 | DA+3 | 37.931 | 2025-10-13 | 2025-10-18 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER
33 | Oct'25 | 10 | 29/2 | DA+3 | 37.931 | 2025-10-13 | 2025-10-22 | M/s. Punam Kumari | Raj Kishor | Rajasthan | KALOO | LUNKARANSAR | BIKANER
34 | Oct'25 | 11 | 29/0 | DB2+0 | 59.501 | 2025-10-19 | 2025-10-25 | M/s. Kartik Mahto | Kailash Mahto | Rajasthan | KALOO | LUNKARANSAR | BIKANER
35 | Oct'25 | 12 | 19/0 | DC2+0 | 67.262 | 2025-10-13 | 2025-10-30 | M/s. Jwala Singh | Mahendra | Rajasthan | SURANA | LUNKARANSAR | BIKANER
36 | Oct'25 | 13 | 28/7 | DA+6 | 43.804 | 2025-10-26 | 2025-10-31 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
37 | Nov'25 | 1 | 28/4 | DA+0 | 36.16 | 2025-11-01 | 2025-11-05 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
38 | Nov'25 | 2 | 19/2 | DA+6 | 43.804 | 2025-10-31 | 2025-11-07 | M/s. Jwala Singh | Mahendra | Rajasthan | SURANA | LUNKARANSAR | BIKANER
39 | Nov'25 | 3 | 28/6 | DA+0 | 36.16 | 2025-11-05 | 2025-11-08 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
40 | Nov'25 | 4 | 29/3 | DA+6 | 43.804 | 2025-11-03 | 2025-11-12 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
41 | Nov'25 | 5 | 12/3 | DA+9 | 45.697 | 2025-10-27 | 2025-11-14 | M/s. Kavya Enterprises | Dinesh Kumar Mahto | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
42 | Nov'25 | 6 | 19/3 | DA-1.5 | 35.602 | 2025-11-07 | 2025-11-15 | M/s. Jwala Singh | Mahendra | Rajasthan | KAKARICHCHHA | LUNKARANSAR | BIKANER
43 | Nov'25 | 7 | 29/7 | DA+6 | 43.804 | 2025-11-13 | 2025-11-17 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
44 | Nov'25 | 8 | 29/6 | DA+0 | 36.16 | 2025-11-17 | 2025-11-21 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
45 | Nov'25 | 9 | 18/4 | DA+6 | 43.804 | 2025-11-16 | 2025-11-22 | M/s. Jwala Singh | Mahendra | Rajasthan | SURANA | LUNKARANSAR | BIKANER
46 | Nov'25 | 10 | 29/5 | DA+3 | 37.931 | 2025-11-21 | 2025-11-25 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
47 | Nov'25 | 11 | 12/5 | DA+9 | 45.697 | 2025-11-17 | 2025-11-26 | M/s. Jwala Singh 2 | Dinesh Kumar Mahto | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
48 | Nov'25 | 12 | 12/4 | DA+9 | 45.697 | 2025-11-16 | 2025-11-29 | M/s. Kavya Enterprises | Rakesh Kumar | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
49 | Nov'25 | 13 | 18/3 | DA+6 | 43.804 | 2025-11-23 | 2025-11-29 | M/s. Jwala Singh | Mahendra | Rajasthan | SURANA | LUNKARANSAR | BIKANER
50 | Nov'25 | 14 | 29/4 | DA+0 | 36.16 | 2025-11-25 | 2025-11-29 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
51 | Nov'25 | 15 | 30/14 | DA+3 | 37.931 | 2025-11-22 | 2025-12-02 | M/s. Punam Kumari 3 | Raj Kishor | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
52 | Nov'25 | 16 | 11/5 | DA-1.5 | 35.602 | 2025-11-27 | 2025-12-03 | M/s. Jwala Singh 2 | Narayan Mahto | Rajasthan | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER
53 | Dec'25 | 1 | 29/1 | DA+6 | 43.804 | 2025-11-29 | 2025-12-04 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
54 | Dec'25 | 2 | 8/1 | DA-1.5 | 19.773 | 2025-11-16 | 2025-11-18 | M/s. Company Gang | Rohit Mahto | Rajasthan | DOODIMUKLERA | LUNKARANSAR | BIKANER
54 | Dec'25 | 2 | 8/1 | DA-1.5 | 15.829 | 2025-11-30 | 2025-12-06 | M/s. Kavya Enterprises | Rakesh Kumar | Rajasthan | DOODIMUKLERA | LUNKARANSAR | BIKANER
55 | Dec'25 | 3 | 9/1 | DA+0 | 36.16 | 2025-11-29 | 2025-12-07 | M/s. Company Gang | Rohit Mahto | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
56 | Dec'25 | 4 | 20/3 | DA-3 | 34.79 | 2025-12-01 | 2025-12-07 | M/s. Jwala Singh | Mahendra | Rajasthan | KALKAL MUKLERA | LUNKARANSAR | BIKANER
57 | Dec'25 | 5 | 5/5 | DA+6 | 43.804 | 2025-12-01 | 2025-12-07 | M/s. Govind Mahto | Dinesh Kumar Mahto | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
58 | Dec'25 | 6 | 31/26 | DA+3 | 37.931 | 2025-12-01 | 2025-12-08 | M/s. Punam Kumari 4 | Kailash Mahto | Rajasthan | MALSISAR | SARDARSHAHAR | CHURU
59 | Dec'25 | 7 | 29/15 | DA+0 | 36.16 | 2025-12-05 | 2025-12-09 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
60 | Dec'25 | 8 | 20/4 | DA+0 | 36.16 | 2025-12-07 | 2025-12-12 | M/s. Jwala Singh | Mahendra | Rajasthan | KALKAL MUKLERA | LUNKARANSAR | BIKANER
61 | Dec'25 | 9 | 30/12 | DA+6 | 43.804 | 2025-12-03 | 2025-12-13 | M/s. Punam Kumari 3 | Raj Kishor | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
62 | Dec'25 | 10 | 11/4 | DA+3 | 37.931 | 2025-12-04 | 2025-12-13 | M/s. Jwala Singh 2 | Narayan Mahto | Rajasthan | SHARAH BEECHHARWAS | LUNKARANSAR | BIKANER
63 | Dec'25 | 11 | 5/9 | DA+3 | 37.931 | 2025-12-08 | 2025-12-14 | M/s. Govind Mahto | Dinesh Kumar Mahto | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
64 | Dec'25 | 12 | 29/12 | DB1+0 | 55.451 | 2025-12-09 | 2025-12-16 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
65 | Dec'25 | 13 | 31/20 | DA-1.5 | 35.602 | 2025-12-11 | 2025-12-17 | M/s. Punam Kumari 4 | Kailash Mahto | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
66 | Dec'25 | 14 | 20/5 | DA+0 | 36.16 | 2025-12-14 | 2025-12-18 | M/s. Jwala Singh | Mahendra | Rajasthan | KALKAL MUKLERA | LUNKARANSAR | BIKANER
67 | Dec'25 | 15 | 11/3 | DA+0 | 36.16 | 2025-12-14 | 2025-12-19 | M/s. Jwala Singh 2 | Narayan Mahto | Rajasthan | SHARAH BEECHHARWAS | LUNKARANSAR | BIKANER
68 | Dec'25 | 16 | 5/10 | DA+3 | 37.931 | 2025-12-14 | 2025-12-20 | M/s. Govind Mahto | Dinesh Kumar Mahto | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
69 | Dec'25 | 17 | 29/10 | DA+0 | 36.16 | 2025-12-17 | 2025-12-20 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
70 | Dec'25 | 18 | 8/0 | DC1+0 | 30.489 | 2025-11-20 | 2025-11-22 | M/s. Company Gang | Sonu Kumar | Rajasthan | DOODIMUKLERA | LUNKARANSAR | BIKANER
70 | Dec'25 | 18 | 8/0 | DC1+0 | 31.955 | 2025-12-06 | 2025-12-22 | M/s. Kavya Enterprises | Rakesh Kumar | Rajasthan | DOODIMUKLERA | LUNKARANSAR | BIKANER
71 | Dec'25 | 19 | 30/10 | DA+3 | 37.931 | 2025-12-13 | 2025-12-22 | M/s. Punam Kumari 3 | Kailash Mahto | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
72 | Dec'25 | 20 | 11/1 | DA-1.5 | 35.602 | 2025-12-19 | 2025-12-24 | M/s. Jwala Singh 2 | Narayan Mahto | Rajasthan | SHARAH BEECHHARWAS | LUNKARANSAR | BIKANER
73 | Dec'25 | 21 | 29/9 | DA+0 | 36.16 | 2025-12-20 | 2025-12-24 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
74 | Dec'25 | 22 | 5/11 | DA+9 | 45.697 | 2025-12-21 | 2025-12-27 | M/s. Govind Mahto | Deepak Kumar Mahto | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
75 | Dec'25 | 23 | 29/8 | DA+0 | 36.16 | 2025-12-24 | 2025-12-28 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
76 | Dec'25 | 24 | 31/17 | DA+9 | 45.697 | 2025-12-21 | 2025-12-29 | M/s. Punam Kumari 4 | Dhiraj Kumar | Rajasthan | KANWALASAR | SARDARSHAHAR | CHURU
77 | Dec'25 | 25 | 11/2 | DA+3 | 37.931 | 2025-12-25 | 2025-12-30 | M/s. Jwala Singh 2 | Narayan Mahto | Rajasthan | SHARAH BEECHHARWAS | LUNKARANSAR | BIKANER
78 | Dec'25 | 26 | 30/8 | DA+3 | 37.931 | 2025-12-24 | 2025-12-31 | M/s. Punam Kumari 3 | Kailash Mahto | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
79 | Dec'25 | 27 | 4/6 | DA+3 | 37.931 | 2025-12-25 | 2025-12-31 | M/s. Govind Mahto 2 | Rakesh Kumar | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
80 | Dec'25 | 28 | 6/0 | DB1+0 | 55.451 | 2025-12-16 | 2026-01-02 | M/s. Company Gang | Pradeep Luhar | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
81 | Dec'25 | 29 | 20/0 | DC1+6 | 72.474 | 2025-12-20 | 2026-01-03 | M/s. Jwala Singh | Mahendra | Rajasthan | KAKARICHCHHA | LUNKARANSAR | BIKANER
82 | Dec'25 | 30 | 37/7 | DA-3 | 34.79 | 2025-12-20 | 2026-01-03 | M/s. Karni Construction 1 | Ram Shankar | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
83 | Dec'25 | 31 | 29/11 | DA+0 | 36.16 | 2025-12-29 | 2026-01-03 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | KALOO | LUNKARANSAR | BIKANER
84 | Dec'25 | 32 | 37/10 | DA+6 | 43.804 | 2025-12-22 | 2026-01-04 | M/s. Karni Construction 2 | Narayan Mahto | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
85 | Jan'26 | 1 | 11/6 | DA+3 | 37.931 | 2025-12-31 | 2026-01-07 | M/s. Jwala Singh 2 | Narayan Mahto | Rajasthan | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER
86 | Jan'26 | 2 | 29/20 | DA+0 | 36.16 | 2026-01-02 | 2026-01-08 | M/s. Kartik Mahto | Dheeraj Kumar | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
87 | Jan'26 | 3 | 30/6 | DA+0 | 36.16 | 2025-12-31 | 2026-01-09 | M/s. Punam Kumari 3 | Kailash Mahto | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
88 | Jan'26 | 4 | 31/18 | DB1+9 | 66.776 | 2025-12-30 | 2026-01-12 | M/s. Punam Kumari 4 | Raj Kishor | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
89 | Jan'26 | 5 | 6/8 | DA+6 | 43.804 | 2025-12-12 | 2026-01-13 | M/s. Company Gang | Dhalchand | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
90 | Jan'26 | 6 | 20/6 | DA+9 | 45.697 | 2026-01-04 | 2026-01-13 | M/s. Jwala Singh | Mahendra | Rajasthan | LUNKARANSAR | LUNKARANSAR | BIKANER
91 | Jan'26 | 7 | 29/21 | DA+3 | 37.931 | 2026-01-09 | 2026-01-13 | M/s. Kartik Mahto | Dheeraj Kumar | Rajasthan | RAJPURA HUDAAN | LUNKARANSAR | BIKANER
92 | Jan'26 | 8 | 4/7 | DB1+0 | 55.451 | 2026-01-02 | 2026-01-14 | M/s. Govind Mahto 2 | Rakesh Kumar | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
93 | Jan'26 | 9 | 37/9 | DA-3 | 34.79 | 2026-01-05 | 2026-01-16 | M/s. Karni Construction 2 | Narayan Kr .Mahto | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
94 | Jan'26 | 10 | 31/3 | DA-3 | 34.79 | 2026-01-06 | 2026-01-16 | M/s. Raju Kumar | Ajhar Ali | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
95 | Jan'26 | 11 | 6/2 | DA+3 | 37.931 | 2025-12-29 | 2026-01-17 | M/s. Govind Mahto 2 | Rakesh Kumar | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
96 | Jan'26 | 12 | 29/17 | DA+0 | 36.16 | 2026-01-13 | 2026-01-17 | M/s. Kartik Mahto | Dheeraj Kumar | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
97 | Jan'26 | 13 | 31/5 | DA+6 | 43.804 | 2026-01-11 | 2026-01-18 | M/s. Raju Kumar | Raj Kishor | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
98 | Jan'26 | 14 | 7/10 | DA+0 | 36.16 | 2025-11-26 | 2026-01-19 | M/s. Company Gang | Dhalchand | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
99 | Jan'26 | 15 | 3A/2 | DA-1.5 | 35.602 | 2026-01-15 | 2026-01-19 | M/s. Shobha Debi | Rohit Mahto | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
100 | Jan'26 | 16 | 30/5 | DA+3 | 37.931 | 2026-01-11 | 2026-01-20 | M/s. Punam Kumari 3 | Kailash Mahto | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
101 | Jan'26 | 17 | 20/7 | DA+0 | 36.16 | 2026-01-15 | 2026-01-20 | M/s. Jwala Singh | Mahendra | Rajasthan | LUNKARANSAR | LUNKARANSAR | BIKANER
102 | Jan'26 | 18 | 9/4 | DA+3 | 18.9655 | 2025-12-08 | 2025-12-10 | M/s. Company Gang | Dhalchand | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
102 | Jan'26 | 18 | 9/4 | DA+3 | 18.9655 | 2026-01-13 | 2026-01-21 | M/s. Mohika Costruction | Rohit Mahto | Rajasthan | DHEERERAN | LUNKARANSAR | BIKANER
103 | Jan'26 | 19 | 37/8 | DA+9 | 45.697 | 2026-01-04 | 2026-01-21 | M/s. Karni Construction 1 | Ram Shankar | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
104 | Jan'26 | 20 | 3A/3 | DA-1.5 | 35.602 | 2026-01-15 | 2026-01-21 | M/s. Sunny Construction | Sher Singh | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
105 | Jan'26 | 21 | 29/13 | DA+0 | 36.16 | 2026-01-17 | 2026-01-21 | M/s. Kartik Mahto | Sujit Choudhary | Rajasthan | KALOO | LUNKARANSAR | BIKANER
106 | Jan'26 | 22 | 31/16 | DA+6 | 43.804 | 2026-01-11 | 2026-01-22 | M/s. Punam Kumari 4 | Raj Kishor | Rajasthan | KANWALASAR | SARDARSHAHAR | CHURU
107 | Jan'26 | 23 | 5/4 | DA+3 | 37.931 | 2026-01-15 | 2026-01-24 | M/s. Jirwa Debi | Deepak Kumar Mahto | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
108 | Jan'26 | 24 | 7/11 | DA+3 | 37.931 | 2025-11-23 | 2026-01-27 | M/s. Company Gang | Dalchand Mahto | Rajasthan | DOODIMU KLERA | LUNKARANSAR | BIKANER
109 | Jan'26 | 25 | 2/5 | DA+0 | 36.16 | 2026-01-10 | 2026-01-27 | M/s. Shree Shyam Construction | Dinesh Kumar Mahto | Rajasthan | KELAN | CHHATARGARH | BIKANER
110 | Jan'26 | 26 | 13/0 | DC1+3 | 65.8725 | 2026-01-16 | 2026-01-27 | M/s. Jwala Singh 2 | Dularchand Mahto | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
111 | Jan'26 | 27 | 6/3 | DA+6 | 43.804 | 2026-01-18 | 2026-01-27 | M/s. Govind Mahto 2 | Sher Singh | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
112 | Jan'26 | 28 | 31/6 | DA+6 | 43.804 | 2026-01-19 | 2026-01-27 | M/s. Raju Kumar | Deepak Kumar Mahto | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
113 | Jan'26 | 29 | 3A/1 | DA+0 | 36.16 | 2026-01-22 | 2026-01-27 | M/s. Shobha Debi | Hariram Nai | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
114 | Jan'26 | 30 | 18/2 | DA+3 | 37.931 | 2026-01-22 | 2026-01-27 | M/s. Jwala Singh | Mahendra | Rajasthan | SURANA | LUNKARANSAR | BIKANER
115 | Jan'26 | 31 | 29/14 | DA+0 | 36.16 | 2026-01-22 | 2026-01-27 | M/s. Kartik Mahto | Sujit Choudhary | Rajasthan | KALOO | LUNKARANSAR | BIKANER
116 | Jan'26 | 32 | 7/7 | DA-1.5 | 35.602 | 2026-01-19 | 2026-01-28 | M/s. Ganesh Sinha | Ramesh | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
117 | Jan'26 | 33 | 30/4 | DA+3 | 37.931 | 2026-01-22 | 2026-01-28 | M/s. Punam Kumari 3 | Kailash Mahto | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
118 | Jan'26 | 34 | 31/27 | DA+3 | 37.931 | 2026-01-19 | 2026-01-29 | M/s. Nirmal Mahto | Azhar Ali | Rajasthan | MALSISAR | SARDARSHAHAR | CHURU
119 | Jan'26 | 35 | 3/7 | DA+3 | 37.931 | 2026-01-27 | 2026-01-30 | M/s. Shobha Debi | Deepak Kumar Mahto | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
120 | Jan'26 | 36 | 4/0 | DB2+0 | 59.501 | 2026-01-22 | 2026-01-31 | M/s. Sunny Construction | Sher Singh | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
121 | Jan'26 | 37 | 5/2 | DA+0 | 36.16 | 2026-01-25 | 2026-01-31 | M/s. Jirwa Debi | Rohit Mahto | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
122 | Jan'26 | 38 | 31/7 | DA+0 | 36.16 | 2026-01-27 | 2026-01-31 | M/s. Raju Kumar | Dheeraj Kumar | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
123 | Jan'26 | 39 | 31/15 | DA+9 | 45.697 | 2026-01-22 | 2026-01-31 | M/s. Punam Kumari 4 | Raj Kishor | Rajasthan | KANWALASAR | SARDARSHAHAR | CHURU
124 | Jan'26 | 40 | 37/5 | DA+6 | 43.804 | 2026-01-18 | 2026-02-01 | M/s. Karni Construction 2 | Narayan Kr .Mahto | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
125 | Jan'26 | 41 | 29/22 | DA+3 | 37.931 | 2026-01-27 | 2026-02-01 | M/s. Kartik Mahto | Sujit Choudhary | Rajasthan | RAJPURA HUDAAN | LUNKARANSAR | BIKANER
126 | Jan'26 | 42 | 11/8 | DA+3 | 37.931 | 2026-01-27 | 2026-02-02 | M/s. Jwala Singh 2 | Narayan Mahto | Rajasthan | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER
127 | Jan'26 | 43 | 6/4 | DA+3 | 37.931 | 2026-01-29 | 2026-02-02 | M/s. Govind Mahto 2 | Dularchand Mahto | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
128 | Feb'26 | 1 | 30/3 | DA+0 | 36.16 | 2026-01-28 | 2026-02-04 | M/s. Punam Kumari 3 | Kailash Mahto | Rajasthan | GARABDESAR | LUNKARANSAR | BIKANER
129 | Feb'26 | 2 | 36/8 | DA+3 | 37.931 | 2026-01-29 | 2026-02-04 | M/s. Jwala Singh | Raghu Kumar | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
130 | Feb'26 | 3 | 3/6 | DA+3 | 37.931 | 2026-01-31 | 2026-02-04 | M/s. Shobha Debi | Deepak Kumar Mahto | Rajasthan | AMBARAN | CHHATARGARH | BIKANER
131 | Feb'26 | 4 | 7/5 | DA-1.5 | 35.602 | 2026-01-29 | 2026-02-05 | M/s. Ganesh Sinha | Shankar Lal | Rajasthan | DUDIWALI | LUNKARANSAR | BIKANER
132 | Feb'26 | 5 | 2/4 | DA+9 | 45.697 | 2026-01-27 | 2026-02-06 | M/s. Shree Shyam Construction | Dinesh Kumar Mahto | Rajasthan | KELAN | CHHATARGARH | BIKANER
133 | Feb'26 | 6 | 28/3 | DA+0 | 36.16 | 2026-02-02 | 2026-02-06 | M/s. Kartik Mahto | Sujit Choudhary | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER
134 | Feb'26 | 7 | 31/14 | DA+3 | 37.931 | 2026-02-01 | 2026-02-06 | M/s. Punam Kumari 4 | Raj Kishor | Rajasthan | KANWALASAR | SARDARSHAHAR | CHURU
135 | Feb'26 | 8 | 31/8 | DA+6 | 43.804 | 2026-02-01 | 2026-02-07 | M/s. Raju Kumar | Dheeraj Kumar | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
136 | Feb'26 | 9 | 4/4 | DA+9 | 45.697 | 2026-02-01 | 2026-02-08 | M/s. Sunny Construction | Rakesh Kumar | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
137 | Feb'26 | 10 | 6/6 | DB1+3 | 57.963 | 2026-02-03 | 2026-02-08 | M/s. Govind Mahto 2 | Dularchand Mahto | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
138 | Feb'26 | 11 | 8/4 | DA+3 | 37.931 | 2026-02-04 | 2026-02-09 | M/s. Jwala Singh 2 | Narayan Mahto | Rajasthan | SADHERAN | LUNKARANSAR | BIKANER
139 | Feb'26 | 12 | 5/0 | DB1+0 | 55.451 | 2026-02-01 | 2026-02-10 | M/s. Jirwa Debi | Deepak Kumar Mahto | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
140 | Feb'26 | 13 | 36/6 | DA+9 | 45.697 | 2026-02-06 | 2026-02-11 | M/s. Jwala Singh | Ram Shankar | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
141 | Feb'26 | 14 | 23/2 | DA+3 | 37.931 | 2026-02-07 | 2026-02-11 | M/s. Kartik Mahto | Sujit Choudhary | Rajasthan | LUNKARANSAR | LUNKARANSAR | BIKANER
142 | Feb'26 | 15 | 30/13 | DA+6 | 43.804 | 2026-02-06 | 2026-02-12 | M/s. Punam Kumari3 | Kailash Mahto | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
143 | Feb'26 | 16 | 31/13 | DA+0 | 36.16 | 2026-02-07 | 2026-02-12 | M/s. Punam Kumari4 | Dhiraj Kumar | Rajasthan | KANWALASAR | SARDARSHAHAR | CHURU
144 | Feb'26 | 17 | 6/10 | DA+6 | 43.804 | 2026-02-06 | 2026-02-13 | M/s. Ganesh Sinha | Ramesh | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
145 | Feb'26 | 18 | 31/4 | DA+0 | 36.16 | 2026-02-08 | 2026-02-13 | M/s. Raju Kumar | Azhar Ali | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
146 | Feb'26 | 19 | 6/5 | DA+9 | 45.697 | 2026-02-09 | 2026-02-13 | M/s. Govind Mahto 1 | Dularchand Mahto | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
147 | Feb'26 | 20 | 3/5 | DA+6 | 43.804 | 2026-02-05 | 2026-02-14 | M/s. Nirmal Mahto | Rohit Mahto | Rajasthan | AMBARAN | CHHATARGARH | BIKANER
148 | Feb'26 | 21 | 23/3 | DA+0 | 36.16 | 2026-02-12 | 2026-02-14 | M/s. Kartik Mahto | Mahendra | Rajasthan | DHANI BHOPALARAM | LUNKARANSAR | BIKANER
149 | Feb'26 | 22 | 4/8 | DA+9 | 45.697 | 2026-02-09 | 2026-02-15 | M/s. Govind Mahto 2 | Rakesh Kumar | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
150 | Feb'26 | 23 | 18/1 | DA+6 | 43.804 | 2026-02-10 | 2026-02-16 | M/s. Jwala Singh 2 | Narayan Mahto | Rajasthan | SURANA | LUNKARANSAR | BIKANER
151 | Feb'26 | 24 | 5/3 | DA+3 | 37.931 | 2026-02-11 | 2026-02-16 | M/s. Jirwa Debi | Deepak Kumar Mahto | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
152 | Feb'26 | 25 | 36/7 | DA+3 | 37.931 | 2026-02-12 | 2026-02-16 | M/s. Jwala Singh | Ram Shankar | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
153 | Feb'26 | 26 | 30/11 | DA+0 | 36.16 | 2026-02-13 | 2026-02-19 | M/s. Punam Kumari3 | Kailash Mahto | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
154 | Feb'26 | 27 | 31/12 | DA+6 | 43.804 | 2026-02-13 | 2026-02-20 | M/s. Punam Kumari4 | Raj Kishor | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
155 | Feb'26 | 28 | 6/7 | DA+0 | 36.16 | 2026-02-14 | 2026-02-20 | M/s. Govind Mahto 1 | Dularchand Mahto | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
156 | Feb'26 | 29 | 4/9 | DA+3 | 37.931 | 2026-02-16 | 2026-02-22 | M/s. Govind Mahto 2 | Rakesh Kumar | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
157 | Feb'26 | 30 | 2/2 | DA+9 |  | 2026-02-07 | 2026-02-18 | M/s. Shree Shyam Construction | Dinesh Kumar Mahto | Rajasthan | KELAN | CHHATARGARH | BIKANER
157 | Feb'26 | 30 | 2/2 | DA+9 |  | 2026-02-21 | 2026-02-23 | M/s. Jirwa Debi | Deepak Kumar Mahto | Rajasthan | KELAN | CHHATARGARH | BIKANER
158 | Feb'26 | 31 | 28/0 | DB2+0 | 59.501 | 2026-02-15 | 2026-02-23 | M/s. Kartik Mahto | Dheeraj Kumar | Rajasthan | UCHHRANGDESAR | LUNKARANSAR | BIKANER
159 | Feb'26 | 32 | 3/3 | DA+9 | 45.697 | 2026-02-15 | 2026-02-24 | M/s. Nirmal Mahto | Rohit Mahto | Rajasthan | AMBARAN | CHHATARGARH | BIKANER
160 | Feb'26 | 33 | 7/0 | DB1+3 | 57.963 | 2026-02-14 | 2026-02-25 | M/s. Ganesh Sinha | Ramesh | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
161 | Feb'26 | 34 | 35/0 | DB1+9 | 66.776 | 2026-02-17 | 2026-02-25 | M/s. Jwala Singh | Narayan Mahto | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
162 | Feb'26 | 35 | 4/10 | DA-1.5 | 35.602 | 2026-02-22 | 2026-02-25 | M/s. Govind Mahto 2 | Smriti Ranjan | Rajasthan | MAKADASAR | CHHATARGARH | BIKANER
163 | Feb'26 | 36 | 35/9 | DA+9 | 45.697 | 2026-02-19 | 2026-02-26 | M/s. Jwala Singh 2 | Ram Shankar | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
164 | Feb'26 | 37 | 23/1 | DA-1.5 | 35.602 | 2026-02-24 | 2026-02-26 | M/s. Kartik Mahto | Narayan Mahto | Rajasthan | LUNKARANSAR | LUNKARANSAR | BIKANER
165 | Feb'26 | 38 | 1A/1 | DA-1.5 | 35.602 | 2026-02-23 | 2026-02-28 | M/s. Jirwa Debi | Deepak Kumar Mahto | Rajasthan | KELAN | CHHATARGARH | BIKANER
166 | Feb'26 | 39 | 5/1 | DA+6 | 43.804 | 2026-02-26 | 2026-02-28 | M/s. Govind Mahto | Smriti Ranjan | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
167 | Feb'26 | 40 | 31/9 | DB1+0 | 55.451 | 2026-02-21 | 2026-03-01 | M/s. Punam Kumari4 | Ashok Saran | Rajasthan | KAGASAR | LUNKARANSAR | BIKANER
168 | Mar'26 | 1 | 35/1 | DA+9 | 45.697 | 2026-02-25 | 2026-03-02 | M/s. Jwala Singh | Narayan Mahto | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
169 | Mar'26 | 2 | 3/4 | DA-1.5 | 35.602 | 2026-02-25 | 2026-03-05 | M/s. Nirmal Mahto | Hariram Nai | Rajasthan | AMBARAN | CHHATARGARH | BIKANER
170 | Mar'26 | 3 | 33/2 | DA+3 | 37.931 | 2026-02-27 | 2026-03-05 | M/s. Kartik Mahto | Pradeep Luhar | Rajasthan | SONPALSAR | SARDARSHAHAR | CHURU
171 | Mar'26 | 4 | 30/9 | DB1+0 | 55.451 | 2026-02-21 | 2026-03-06 | M/s. Punam Kumari3 | Azhar Ali | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
172 | Mar'26 | 5 | 35/8 | DA+3 | 37.931 | 2026-02-27 | 2026-03-06 | M/s. Jwala Singh 2 | Ram Shankar | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
173 | Mar'26 | 6 | 6/9 | DA+3 | 37.931 | 2026-02-26 | 2026-03-07 | M/s. Ganesh Sinha | Shankar Lal | Rajasthan | SODHWALI | LUNKARANSAR | BIKANER
174 | Mar'26 | 7 | 1A/2 | DA-1.5 | 35.602 | 2026-03-01 | 2026-03-09 | M/s. Jirwa Debi | Dinesh Kumar Mahto | Rajasthan | KELAN | CHHATARGARH | BIKANER
175 | Mar'26 | 8 | 4/13 | DA+0 | 36.16 | 2026-03-07 | 2026-03-09 | M/s. Govind Mahto | Dularchand Mahto | Rajasthan | MAKADASAR | LUNKARANSAR | BIKANER
176 | Mar'26 | 9 | 34/6 | DA-3 | 34.79 | 2026-03-06 | 2026-03-10 | M/s. Kartik Mahto | Ram Shankar | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
177 | Mar'26 | 10 | 34/10 | DA+9 | 45.697 | 2026-03-06 | 2026-03-10 | M/s. Jwala Singh | Narayan Mahto | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
178 | Mar'26 | 11 | 12/2 | DA-1.5 | 35.602 | 2026-01-07 | 2026-03-11 | M/s. Jwala Singh 2 | Saddam Maliya | Rajasthan | HANSHERA | LUNKARANSAR | BIKANER
179 | Mar'26 | 12 | 31/19 | DA+3 | 37.931 | 2026-03-02 | 2026-03-13 | M/s. Punam Kumari4 | Raj Kishor | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
180 | Mar'26 | 13 | 5/6 | DA+6 | 43.804 | 2026-03-10 | 2026-03-13 | M/s. Govind Mahto | Dularchand Mahto | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
181 | Mar'26 | 14 | 34/3 | DA+0 | 36.16 | 2026-03-10 | 2026-03-14 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
182 | Mar'26 | 15 | 35/3 | DA+3 | 37.931 | 2026-03-10 | 2026-03-16 | M/s. Jwala Singh | Narayan Mahto | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
183 | Mar'26 | 16 | 2/6 | DA+9 | 45.697 | 2026-03-10 | 2026-03-18 | M/s. Jirwa Debi | Dinesh Kumar Mahto | Rajasthan | KELAN | CHHATARGARH | BIKANER
184 | Mar'26 | 17 | 8/2 | DA+3 | 37.931 | 2026-03-08 | 2026-03-20 | M/s. Ganesh Sinha | Rohit Mahto | Rajasthan | JAISAN | LUNKARANSAR | BIKANER
185 | Mar'26 | 18 | 35/7 | DA-3 | 34.79 | 2026-03-12 | 2026-03-20 | M/s. Jwala Singh 2 | Ram Shankar | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
186 | Mar'26 | 19 | 5/7 | DB1+3 | 57.963 | 2026-03-14 | 2026-03-20 | M/s. Govind Mahto | Dularchand Mahto | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
187 | Mar'26 | 20 | 31/23 | DA+6 | 43.804 | 2026-03-14 | 2026-03-21 | M/s. Punam Kumari4 | Raj Kishor | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
188 | Mar'26 | 21 | 36/3 | DA+9 | 45.697 | 2026-03-15 | 2026-03-21 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | MALAKSAR | SARDARSHAHAR | CHURU
189 | Mar'26 | 22 | 35/5 | DA+9 | 45.697 | 2026-03-17 | 2026-03-22 | M/s. Jwala Singh | Kailash Mahto | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
190 | Mar'26 | 23 | 4/12 | DA+3 | 37.931 | 2026-03-21 | 2026-03-23 | M/s. Govind Mahto | Dularchand Mahto | Rajasthan | MAKADASAR | LUNKARANSAR | BIKANER
191 | Mar'26 | 24 | 35/4 | DA+3 | 37.931 | 2026-03-23 | 2026-03-26 | M/s. Jwala Singh | Kailash Mahto | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
192 | Mar'26 | 25 | 4/14 | DA+3 | 37.931 | 2026-03-24 | 2026-03-27 | M/s. Govind Mahto | Mahendra | Rajasthan | BINJHARWALI | LUNKARANSAR | BIKANER
193 | Mar'26 | 26 | 31/25 | DA-3 | 34.79 | 2026-03-22 | 2026-03-27 | M/s. Punam Kumari4 | Raj Kishor | Rajasthan | DHEERASAR | SARDARSHAHAR | CHURU
194 | Mar'26 | 27 | 2/3 | DA+9 | 45.697 | 2026-03-19 | 2026-03-29 | M/s. Jirwa Debi | Deepak Kumar Mahto | Rajasthan | KELAN | CHHATARGARH | BIKANER
195 | Mar'26 | 28 | 37/0 | DB1+0 | 55.451 | 2026-03-22 | 2026-03-29 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
196 | Mar'26 | 29 | 41/2 | DA+0 | 36.16 | 2026-03-23 | 2026-03-30 | M/s. Ganesh Sinha | Narayan Mahto | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
197 | Mar'26 | 30 | 30/17 | DC2+0 | 82.998 | 2026-03-08 | 2026-03-31 | M/s. Punam Kumari3 | Rakesh Kumar | Rajasthan | CHHATASAR | LUNKARANSAR | BIKANER
198 | Mar'26 | 31 | 35/6 | DA+9 | 45.697 | 2026-03-21 | 2026-03-31 | M/s. Jwala Singh 2 | Ram Shankar | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
199 | Mar'26 | 32 | 35/2 | DA+9 | 45.697 | 2026-03-29 | 2026-04-02 | M/s. Jwala Singh | Ram Shankar | Rajasthan | NAHARSARA | SARDARSHAHAR | CHURU
200 | Mar'26 | 33 | 37/2 | DA+3 | 37.931 | 2026-03-30 | 2026-04-02 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
201 | Mar'26 | 34 | 3A/0 | DD45+0 | 73.2445 | 2026-03-29 | 2026-04-04 | M/s. Govind Mahto | Hariram Nai | Rajasthan | RAJASAR BHATIYAN | CHHATARGARH | BIKANER
202 | Mar'26 | 35 | 41/1 | DA+0 | 36.16 | 2026-03-31 | 2026-04-06 | M/s. Ganesh Sinha | Ram Shankar | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
203 | Mar'26 | 36 | 34/9 | DA+9 | 45.697 | 2026-04-03 | 2026-04-07 | M/s. Jwala Singh | Kailash Mahto | Rajasthan | LODSAR | SARDARSHAHAR | CHURU
204 | Mar'26 | 37 | 37/3 | DA+3 | 37.931 | 2026-04-03 | 2026-04-08 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
205 | Mar'26 | 38 | 4/11 | DA+0 | 36.16 | 2026-03-01 | 2026-04-12 | M/s. Govind Mahto | Mahendra | Rajasthan | MAKADASAR | LUNKARANSAR | BIKANER
206 | Mar'26 | 39 | 37/4 | DA+3 | 37.931 | 2026-04-10 | 2026-04-12 | M/s. Kartik Mahto | Dhiraj Kumar | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
207 | Apr'26 | 1 | 32/2 | DA+3 | 37.931 | 2026-03-29 | 2026-04-14 | M/s. Punam Kumari4 | Raj Kishor | Rajasthan | KEEKASAR | SARDARSHAHAR | CHURU
208 | Apr'26 | 2 | 2A/4 | DA+9 | 45.697 | 2026-04-06 | 2026-04-14 | M/s. Govind Mahto | Mahendra | Rajasthan | KELAN | CHHATARGARH | BIKANER
209 | Apr'26 | 3 | 41/5 | DA+3 | 37.931 | 2026-04-07 | 2026-04-14 | M/s. Ganesh Sinha | Ram Shankar | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
210 | Apr'26 | 4 | 38/0 | DB2+0 | 59.501 | 2026-04-08 | 2026-04-17 | M/s. Jwala Singh | Kailash Mahto | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
211 | Apr'26 | 5 | 41/6 | DA+3 | 37.931 | 2026-04-14 | 2026-04-21 | M/s. Ganesh Sinha | Ram Shankar | Rajasthan | HALASAR | SARDARSHAHAR | CHURU
212 | Apr'26 | 6 | 33/3 | DA+9 | 45.697 | 2026-04-18 | 2026-04-23 | M/s. Jwala Singh | Kailash Mahto | Rajasthan | SONPALSAR | SARDARSHAHAR | CHURU
213 | Apr'26 | 7 | 33/4 | DA+9 | 45.697 | 2026-04-24 | 2026-04-29 | M/s. Jwala Singh | Kailash Mahto | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
214 | May'26 | 1 | 41/4 | DA+6 | 43.804 | 2026-04-22 | 2026-05-03 | M/s. Ganesh Sinha | Ram Shankar | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
215 | May'26 | 2 | 34/7 | DA+6 | 43.804 | 2026-04-30 | 2026-05-05 | M/s. Jwala Singh | Kailash Mahto | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
216 | May'26 | 3 | 34/8 | DA+9 | 45.697 | 2026-05-06 | 2026-05-12 | M/s. Jwala Singh | Kailash Mahto | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
217 | May'26 | 4 | 41/3 | DA+6 | 43.804 | 2026-05-04 | 2026-05-15 | M/s. Ganesh Sinha | Narayan Mahto | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
218 | May'26 | 5 | 34/5 | DA+6 |  | 2026-05-13 |  | M/s. Jwala Singh |  | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
219 | May'26 | 6 | 34/4 | DA+9 |  | 2026-05-17 |  | M/s. Jwala Singh |  | Rajasthan | RANGAISAR | SARDARSHAHAR | CHURU
220 | May'26 | 7 | 40/3 | DA+3 |  | 2026-05-16 |  | M/s. Ganesh Sinha |  | Rajasthan | MALSAR | SARDARSHAHAR | CHURU
221 | May'26 | 8 | 32/5 | DA+0 |  | 2026-01-30 |  |  |  | Rajasthan | SONPALSAR | SARDARSHAHAR | CHURU
222 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
223 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
224 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
225 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
226 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
227 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
228 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
229 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
230 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
231 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
232 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
233 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
234 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
235 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
236 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
237 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
238 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
239 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
240 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
241 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
242 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
243 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
244 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
245 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
246 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
247 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
248 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
249 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
250 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
251 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
252 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
253 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
254 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
255 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
256 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
257 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
258 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
259 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
260 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
261 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
262 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
263 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
264 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
265 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
266 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
267 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
268 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
269 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
270 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
271 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
272 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
273 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
274 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
275 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
276 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
277 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
278 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
279 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
280 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
281 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
282 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
283 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
284 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
285 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
286 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
287 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
288 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
289 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
290 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
291 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
292 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
293 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
294 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
295 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
296 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
297 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
298 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
299 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
300 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
301 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
302 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
303 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
304 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
305 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
306 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
307 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
308 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
309 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
310 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
311 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
312 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
313 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
314 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
315 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
316 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
317 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
318 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
319 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
320 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
321 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
322 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
323 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
324 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
325 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
326 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
327 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
328 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
329 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
330 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
331 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
332 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
333 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
334 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
335 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
336 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
337 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
338 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
339 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
340 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
341 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
342 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
343 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
344 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
345 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
346 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
347 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
348 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
349 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
350 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
351 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
352 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
353 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
354 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
355 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
356 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
357 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
358 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
359 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
360 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
361 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
362 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
363 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
364 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
365 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
366 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
367 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A
368 | [9 empty] | Rajasthan | #N/A | #N/A | #N/A

## Tack Welding
KEC International Limited
765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Details of Tack Welding | [7 empty] | 2026-05-20
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Start | Complete | Name of the Gang | Name of Supervisor | Remarks
1 | Mar'26 | 20/5 | DA+0 | 2026-03-23 | 2026-03-23 | RK Construction | Mantu Biswas
2 | Mar'26 | 20/6 | DA+9 | 2026-03-23 | 2026-03-23 | RK Construction | Mantu Biswas
3 | Mar'26 | 20/7 | DA+0 | 2026-03-24 | 2026-03-24 | RK Construction | Mantu Biswas
4 | Mar'26 | 20/4 | DA+0 | 2026-03-24 | 2026-03-24 | RK Construction | Mantu Biswas
5 | Mar'26 | 20/3 | DA-3 | 2026-03-25 | 2026-03-25 | RK Construction | Mantu Biswas
6 | Mar'26 | 20/2 | DA+6 | 2026-03-25 | 2026-03-25 | RK Construction | Mantu Biswas
7 | Mar'26 | 20/1 | DA+6 | 2026-03-26 | 2026-03-26 | RK Construction | Mantu Biswas
8 | Mar'26 | 20/0 | DC1+6 | 2026-03-27 | 2026-03-27 | RK Construction | Mantu Biswas
9 | Mar'26 | 11/1 | DA-1.5 | 2026-03-27 | 2026-03-27 | RK Construction | Mantu Biswas
10 | Mar'26 | 11/2 | DA+3 | 2026-03-28 | 2026-03-28 | RK Construction | Mantu Biswas
11 | Mar'26 | 11/3 | DA+0 | 2026-03-28 | 2026-03-28 | RK Construction | Mantu Biswas
12 | Mar'26 | 11/4 | DA+3 | 2026-03-29 | 2026-03-29 | RK Construction | Mantu Biswas
13 | Mar'26 | 11/5 | DA-1.5 | 2026-03-29 | 2026-03-29 | RK Construction | Mantu Biswas
14 | Mar'26 | 19/3 | DA-1.5 | 2026-03-30 | 2026-03-30 | RK Construction | Mantu Biswas
15 | Mar'26 | 19/5 | DA+3 | 2026-03-31 | 2026-03-31 | RK Construction | Mantu Biswas
16 | Mar'26 | 18/2 | DA+3 | 2026-03-31 | 2026-03-31 | RK Construction | Mantu Biswas
17 | Apr'26 | 18/3 | DA+6 | 2026-04-01 | 2026-04-01 | RK Construction | Mantu Biswas
18 | Apr'26 | 18/4 | DA+6 | 2026-04-01 | 2026-04-01 | RK Construction | Mantu Biswas
19 | Apr'26 | 18/5 | DA+0 | 2026-02-04 | 2026-02-04 | RK Construction | Mantu Biswas
20 | Apr'26 | 19/2 | DA+6 | 2026-02-04 | 2026-02-04 | RK Construction | Mantu Biswas
21 | Apr'26 | 19/6 | DA+3 | 2026-04-03 | 2026-04-03 | RK Construction | Mantu Biswas
22 | Apr'26 | 19/7 | DA+6 | 2026-04-04 | 2026-04-04 | RK Construction | Mantu Biswas
23 | Apr'26 | 19/1 | DA+3 | 2026-04-04 | 2026-04-04 | RK Construction | Mantu Biswas
24 | Apr'26 | 19/4 | DA+9 | 2026-04-05 | 2026-04-05 | RK Construction | Mantu Biswas
25 | Apr'26 | 28/4 | DA+0 | 2026-04-06 | 2026-04-06 | RK Construction | Mantu Biswas
26 | Apr'26 | 28/6 | DA+0 | 2026-04-06 | 2026-04-06 | RK Construction | Mantu Biswas
27 | Apr'26 | 28/7 | DA+6 | 2026-04-07 | 2026-04-07 | RK Construction | Mantu Biswas
28 | Apr'26 | 29/5 | DA+3 | 2026-04-08 | 2026-04-08 | RK Construction | Mantu Biswas
29 | Apr'26 | 29/3 | DA+6 | 2026-04-08 | 2026-04-08 | RK Construction | Mantu Biswas
30 | Apr'26 | 11/6 | DA+3 | 2026-04-09 | 2026-04-09 | RK Construction | Mantu Biswas
31 | Apr'26 | 29/9 | DA+0 | 2026-04-09 | 2026-04-09 | RK Construction | Mantu Biswas
32 | Apr'26 | 29/15 | DA+0 | 2026-04-11 | 2026-04-11 | RK Construction | Mantu Biswas
33 | Apr'26 | 29/20 | DA+0 | 2026-04-11 | 2026-04-11 | RK Construction | Mantu Biswas
34 | Apr'26 | 7/1 | DA+6 | 2026-04-13 | 2026-04-13 | RK Construction | Mantu Biswas
35 | Apr'26 | 7/3 | DA+0 | 2026-04-13 | 2026-04-13 | RK Construction | Mantu Biswas
36 | Apr'26 | 7/4 | DA+0 | 2026-04-14 | 2026-04-14 | RK Construction | Mantu Biswas
37 | Apr'26 | 2/6 | DA+9 | 2026-04-16 | 2026-04-16 | RK Construction | Mantu Biswas
38 | Apr'26 | 7/5 | DA-1.5 | 2026-04-18 | 2026-04-18 | RK Construction | Mantu Biswas
39 | Apr'26 | 7/6 | DA+0 | 2026-04-18 | 2026-04-18 | RK Construction | Mantu Biswas
40 | Apr'26 | 7/7 | DA-1.5 | 2026-04-19 | 2026-04-19 | RK Construction | Mantu Biswas
41 | Apr'26 | 11/8 | DA+3 | 2026-04-22 | 2026-04-22 | RK Construction | Mantu Biswas
42 | Apr'26 | 12/2 | DA-1.5 | 2026-04-22 | 2026-04-22 | RK Construction | Mantu Biswas
43 | Apr'26 | 5/2 | DA+0 | 2026-04-23 | 2026-04-23 | RK Construction | Mantu Biswas
44 | Apr'26 | 5/3 | DA+3 | 2026-04-23 | 2026-04-23 | RK Construction | Mantu Biswas
45 | Apr'26 | 2/3 | DA+9 | 2026-04-24 | 2026-04-24 | RK Construction | Mantu Biswas
46 | Apr'26 | 5/4 | DA+3 | 2026-04-25 | 2026-04-25 | RK Construction | Mantu Biswas
47 | Apr'26 | 7/8 | DA+3 | 2026-04-26 | 2026-04-26 | RK Construction | Mantu Biswas
48 | Apr'26 | 3A/1 | DA+0 | 2026-04-28 | 2026-04-28 | RK Construction | Mantu Biswas
49 | Apr'26 | 3A/2 | DA-1.5 | 2026-04-28 | 2026-04-28 | RK Construction | Mantu Biswas
50 | Apr'26 | 3/6 | DA+3 | 2026-04-29 | 2026-04-29 | RK Construction | Mantu Biswas
51 | Apr'26 | 3/7 | DA+3 | 2026-04-29 | 2026-04-29 | RK Construction | Mantu Biswas
52 | Apr'26 | 3/4 | DA-1.5 | 2026-04-30 | 2026-04-30 | RK Construction | Mantu Biswas
53 | Apr'26 | 3/5 | DA+6 | 2026-04-30 | 2026-04-30 | RK Construction | Mantu Biswas
54 | May'26 | 3/3 | DA+9 | 2026-05-02 | 2026-05-02 | RK Construction | Mantu Biswas
55 | May'26 | 7/9 | DA+3 | 2026-05-03 | 2026-05-03 | RK Construction | Mantu Biswas
56 | May'26 | 7/10 | DA+0 | 2026-05-03 | 2026-05-03 | RK Construction | Mantu Biswas
57 | May'26 | 7/11 | DA+3 | 2026-05-05 | 2026-05-05 | RK Construction | Dular Chand
58 | May'26 | 35/1 | DA+9 | 2026-05-05 | 2026-05-05 | RK Construction | Dular Chand
59 | May'26 | 35/3 | DA+3 | 2026-05-06 | 2026-05-06 | RK Construction | Dular Chand
60 | May'26 | 35/4 | DA+3 | 2026-05-06 | 2026-05-06 | RK Construction | Dular Chand
61 | May'26 | 8/0 | DC1+0 | 2026-05-06 | 2026-05-06 | RK Construction | Mantu Biswas
62 | May'26 | 8/1 | DA-1.5 | 2026-05-07 | 2026-05-07 | RK Construction | Mantu Biswas
63 | May'26 | 35/2 | DA+9 | 2026-05-07 | 2026-05-07 | RK Construction | Mantu Biswas
64 | May'26 | 35/5 | DA+9 | 2026-05-08 | 2026-05-08 | RK Construction | Mantu Biswas
65 | May'26 | 8/2 | DA+3 | 2026-05-08 | 2026-05-08 | RK Construction | Mantu Biswas
66 | May'26 | 29/11 | DA+0 | 2026-05-09 | 2026-05-09 | RK Construction | Dular Chand Mahto
67 | May'26 | 29/8 | DA+0 | 2026-05-10 | 2026-05-10 | RK Construction | Dular Chand Mahto
68 | May'26 | 29/10 | DA+0 | 2026-05-10 | 2026-05-10 | RK Construction | Dular Chand Mahto
69 | May'26 | 29/6 | DA+0 | 2026-05-11 | 2026-05-11 | RK Construction | Dular Chand Mahto
70 | May'26 | 33/4 | DA+9 | 2026-05-11 | 2026-05-11 | RK Construction | Dular Chand Mahto
71 | May'26 | 8/3 | DA+6 | 2026-05-12 | 2026-05-12 | RK Construction | Dular Chand Mahto
72 | May'26 | 29/1 | DA+6 | 2026-05-12 | 2026-05-12 | RK Construction | Dular Chand Mahto
73 | May'26 | 34/9 | DA+9 | 2026-05-15 | 2026-05-15 | RK Construction | Dular Chand Mahto
74 | May'26 | 33/3 | DA+9 | 2026-05-16 | 2026-05-16 | RK Construction | Dular Chand Mahto
75 | May'26 | 36/8 | DA+3 | 2026-05-19 | 2026-05-19 | RK Construction | Dular Chand Mahto
76 | May'26 | 36/7 | DA+3 | 2026-05-20 | 2026-05-20 | RK Construction | Dular Chand Mahto
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219

## Visual Chart
KEC INTERNATIONAL LIMITED
TA-512 : 765kV D/C Bikaner IV PS to Siwani II (Part-1) TL | [19 empty] | Visual Chart | [20 empty] | 2026-05-20
| S. No. |  | Description |  |  |  | UOM |  | Total Qty |  | Completed |  |  | Balance |  |  |  | Power Line Crossing | [8 empty] | Stringing U/P | [8 empty] | Stringing completed
| 1 |  | Foundation |  |  |  | Nos |  | 319 |  | 302 |  |  | 17 | [12 empty] | Tack Welding U/P | [8 empty] | Tack Welding completed
| 2 |  | Earthing Rod Type |  |  |  | Nos |  | 319 |  | 302 |  |  | 17 |  |  |  | NH / SH Crossing | [8 empty] | Erection U/P | [6 empty] | 4 |  | Erection completed
| 3 |  | Earthing Pipe/Counter Poise |  |  |  | Nos |  | 319 |  | 269 |  |  | 50 | [10 empty] | 1 |  | Foundation U/P | [8 empty] | Foundation completed
| 4 |  | Tower Erection |  |  |  | Nos |  | 319 |  | 217 |  |  | 102 |  |  |  | Railway Crossing | [8 empty] | Angle Tower | [6 empty] | 3 |  | Angle Tower
| 5 |  | Tack Welding |  |  |  | Nos |  | 319 |  | 76 |  |  | 243 | [10 empty] | 1 |  | Excavation U/P | [6 empty] | 2 |  | Excavation completed
| 6 |  | Rough Sag |  |  |  | KM |  | 124.657 |  |  |  |  | 124.657 |  |  |  | Canal | [17 empty] | Earthing completed
| 7 |  | Final Sag |  |  |  | KM |  | 124.657 |  |  |  |  | 124.657
[17 empty] | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14
|  | Hold Xing Proposal |  |  |  | Immediate Work Stop By Power Grid | [5 empty] | Check Survey ROW |  |  | Gantry |  | 1/0 |  | 1/1 |  | 1/2 |  | 1A/0 |  | 1A/1 |  | 1A/2 |  | 1A/3 |  | 2/0 |  | 2/1 |  | 2/2 |  | 2/3 |  | 2/4 |  | 2/5 |  | 2/6
220kV
|  | Foundation ROW | [15 empty] | OHTL
[11 empty] | Bikaner-IV Gantry |  |  |  |  | 146 |  | 289 |  | 408 |  | 382.118 |  | 360 | 3 | 384 | 3 | 385 | 3 | 370.347 | 3 | 351 | 3 | 420 | 3 | 419 | 3 | 350 | 3 | 445 | 3 | 384 | 3 | 440.898 | 10
|  | Erection ROW |  |  |  | Stringing ROW | [16 empty] | 1 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
[15 empty] | Gantry |  | DD60+3 |  | DB1+18 |  | DA+0 |  | DD45+0 |  | DA-1.5 |  | DA-1.5 |  | DA-3 |  | DD60+3 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+0 |  | DA+9
ACME
| 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36
| 2A/0 |  | 2A/1 |  | 2A/2 |  | 2A/3 |  | 2A/4 |  | 2A/5 |  | 3/0 |  | 3/1 |  | 3/2 |  | 3/3 |  | 3/4 |  | 3/5 |  | 3/6 |  | 3/7 |  | 3A/0 |  | 3A/1 |  | 3A/2 |  | 3A/3 |  | 4/0 |  | 4/1 |  | 4/2 |  | 4/3
| 3 | 367 | 3 | 412 | 3 | 426 | 3 | 414 | 3 | 400 | 3 | 434.969 | 3 | 480 | 3 | 482 | 3 | 358 | 3 | 325 | 3 | 406 | 3 | 385 | 3 | 404 | 3 | 409.269 | 3 | 359 | 3 | 349 | 3 | 347 | 3 | 378.992 | 3 | 367 | 3 | 406 | 3 | 434 | 3 | 404 | 22
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DB2+3 |  | DA+9 |  | DA-1.5 |  | DA+3 |  | DA+9 |  | DA+9 |  | DC2+9 |  | DB1+9 |  | DA+9 |  | DA+9 |  | DA-1.5 |  | DA+6 |  | DA+3 |  | DA+3 |  | DD45+0 |  | DA+0 |  | DA-1.5 |  | DA-1.5 |  | DB2+0 |  | DA-3 |  | DA+6 |  | DA-3
| 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58
| 4/4 |  | 4/5 |  | 4/6 |  | 4/7 |  | 4/8 |  | 4/9 |  | 4/10 |  | 4/11 |  | 4/12 |  | 4/13 |  | 4/14 |  | 5/0 |  | 5/1 |  | 5/2 |  | 5/3 |  | 5/4 |  | 5/5 |  | 5/6 |  | 5/7 |  | 5/8 |  | 5/9 |  | 5/10
| 3 | 387 | 3 | 442 | 3 | 398 | 3 | 442 | 3 | 376 | 3 | 464 | 3 | 365 | 3 | 406 | 3 | 419 | 3 | 400 | 3 | 379.424 | 3 | 420 | 3 | 419 | 3 | 421 | 3 | 417 | 3 | 419 | 3 | 419 | 3 | 420 | 3 | 419 | 3 | 420 | 3 | 419 | 3 | 419 | 22
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+9 |  | DA+9 |  | DA+3 |  | DB1+0 |  | DA+9 |  | DA+3 |  | DA-1.5 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB1+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+6 |  | DB1+3 |  | DA+6 |  | DA+3 |  | DA+3
| 59 |  | 60 |  | 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80
| 5/11 |  | 6/0 |  | 6/1 |  | 6/2 |  | 6/3 |  | 6/4 |  | 6/5 |  | 6/6 |  | 6/7 |  | 6/8 |  | 6/9 |  | 6/10 |  | 7/0 |  | 7/1 |  | 7/2 |  | 7/3 |  | 7/4 |  | 7/5 |  | 7/6 |  | 7/7 |  | 7/8 |  | 7/9
| 3 | 419.406 | 3 | 403 | 3 | 437 | 3 | 403 | 3 | 437 | 3 | 363 | 3 | 469 | 3 | 403 | 3 | 432 | 3 | 407 | 3 | 427 | 3 | 385.067 | 3 | 444 | 3 | 394 | 3 | 367 | 3 | 388 | 3 | 389 | 3 | 385 | 3 | 389 | 3 | 395 | 3 | 432 | 3 | 371 | 22
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+9 |  | DB1+0 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+9 |  | DB1+3 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+6 |  | DB1+3 |  | DA+6 |  | DA-1.5 |  | DA+0 |  | DA+0 |  | DA-1.5 |  | DA+0 |  | DA-1.5 |  | DA+3 |  | DA+3
| 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100 |  | 101 |  | 102
| 7/10 |  | 7/11 |  | 8/0 |  | 8/1 |  | 8/2 |  | 8/3 |  | 8/4 |  | 8/5 |  | 8/6 |  | 8/7 |  | 8/8 |  | 9/0 |  | 9/1 |  | 9/2 |  | 9/3 |  | 9/4 |  | 10/0 |  | 11/0 |  | 11/1 |  | 11/2 |  | 11/3 |  | 11/4
400kV
OHTL
| 3 | 385 | 3 | 408.062 | 3 | 372 | 3 | 383 | 3 | 427 | 3 | 402 | 3 | 388 | 3 | 365 | 3 | 422 | 3 | 384 | 3 | 380.388 | 3 | 329 | 3 | 429 | 3 | 411 | 3 | 394 | 3 | 445.871 | 3 | 200.429 | 1 | 453 | 3 | 387 | 3 | 383 | 3 | 399 | 3 | 385 | 21
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+0 |  | DA+3 |  | DC1+0 |  | DA-1.5 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DD60+25 |  | DD60+18 |  | DA-1.5 |  | DA+3 |  | DA+0 |  | DA+3
RC - 2M
ADANI
| 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120 |  | 121 |  | 122 |  | 123 |  | 124
| 11/5 |  | 11/6 |  | 11/7 |  | 11/8 |  | 12/0 |  | 12/1 |  | 12/2 |  | 12/3 |  | 12/4 |  | 12/5 |  | 13/0 |  | 13/1 |  | 14/0 |  | 15/0 |  | 16/0 |  | 16/1 |  | 16/2 |  | 16/3 |  | 17/0 |  | 18/0 |  | 18/1 |  | 18/2
132kV
OHTL
| 3 | 389 | 3 | 403 | 3 | 398 | 3 | 402.053 | 3 | 359 | 3 | 381 | 3 | 399 | 3 | 427 | 3 | 413 | 3 | 409.527 | 3 | 311 | 3 | 458.7 |  | 242.447 |  | 226.424 | 1 | 353 | 3 | 365 | 3 | 344 | 3 | 363.585 | 3 | 244.245 | 3 | 432 | 3 | 366 | 3 | 424 | 19
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | [5 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA-1.5 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC2+0 |  | DA+3 |  | DA-1.5 |  | DA+9 |  | DA+9 |  | DA+9 |  | DC1+3 |  | DA+6 |  | DC1+0 |  | DC1+0 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DD60+0 |  | DD60+0 |  | DA+6 |  | DA+3
[29 empty] | RC - 1M | [7 empty] | RC - 1M
[20 empty] | 🌿 | [5 empty] | 🌿 |  | RRVPNL | [9 empty] | Railway track
[20 empty] | CANAL & FOREST | [5 empty] | NH62 & FOREST
| 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146
| 18/3 |  | 18/4 |  | 18/5 |  | 19/0 |  | 19/1 |  | 19/2 |  | 19/3 |  | 19/4 |  | 19/5 |  | 19/6 |  | 19/7 |  | 20/0 |  | 20/1 |  | 20/2 |  | 20/3 |  | 20/4 |  | 20/5 |  | 20/6 |  | 20/7 |  | 20A/0 |  | 21/0 |  | 22/0
[40 empty] | 220kV |  |  |  | 400kV
[40 empty] | OHTL |  |  |  | OHTL
| 3 | 407 | 3 | 373 | 3 | 353.456 | 3 | 380 | 3 | 449 | 3 | 391 | 3 | 397 | 3 | 425 | 3 | 409 | 3 | 381 | 3 | 392.001 | 3 | 420 | 3 | 361 | 3 | 393 | 3 | 384 | 3 | 345 | 3 | 396 | 3 | 370 | 3 | 443.474 | 3 | 226.807 | 3 | 275.25 | 3 | 198.077 | 22
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+6 |  | DA+6 |  | DA+0 |  | DC2+0 |  | DA+3 |  | DA+6 |  | DA-1.5 |  | DA+9 |  | DA+3 |  | DA+3 |  | DA+6 |  | DC1+6 |  | DA+6 |  | DA+6 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+0 |  | DD45+9 |  | DC2+3 |  | DD60+6
[40 empty] | RRVPNL |  |  |  | RRVPNL
| 147 |  | 148 |  | 149 |  | 150 |  | 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168
| 23/0 |  | 23/1 |  | 23/2 |  | 23/3 |  | 23/4 |  | 24/0 |  | 25/0 |  | 25/1 |  | 26/0 |  | 27/0 |  | 27/1 |  | 27/2 |  | 27/3 |  | 28/0 |  | 28/1 |  | 28/2 |  | 28/3 |  | 28/4 |  | 28/5 |  | 28/6 |  | 28/7 |  | 29/0
765kV
OHTL
| 3 | 327.999 | 3 | 318 | 3 | 379 | 3 | 382 |  | 353.645 |  | 247.381 |  | 258 |  | 452.894 |  | 217.368 | 1 | 368 | 3 | 397 | 3 | 332 | 3 | 338.643 | 3 | 421 | 3 | 400 | 3 | 396 | 3 | 378 | 3 | 386 | 3 | 388 | 3 | 393 | 3 | 417.124 | 3 | 424 | 16
| 2 |  | 2 |  | 2 |  | 2 | [11 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DD60+9 |  | DA-1.5 |  | DA+3 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DC2+0 |  | DA+9 |  | DD60+35 |  | DD60+35 |  | DB1+9 |  | DA-1.5 |  | DA-3 |  | DB2+0 |  | DA+6 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DB2+0
[17 empty] | RC - 2M |  | RC - 2M
[12 empty] | NH754A | [5 empty] | POWER GRID | [9 empty] | SH 6A
| 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189 |  | 190
| 29/1 |  | 29/2 |  | 29/3 |  | 29/4 |  | 29/5 |  | 29/6 |  | 29/7 |  | 29/8 |  | 29/9 |  | 29/10 |  | 29/11 |  | 29/12 |  | 29/13 |  | 29/14 |  | 29/15 |  | 29/16 |  | 29/17 |  | 29/18 |  | 29/19 |  | 29/20 |  | 29/21 |  | 29/22
| 3 | 416 | 3 | 424 | 3 | 412 | 3 | 409 | 3 | 396 | 3 | 419 | 3 | 421 | 3 | 415 | 3 | 388 | 3 | 393 | 3 | 371 | 3 | 386 | 3 | 390 | 3 | 385 | 3 | 343 | 3 | 385 | 3 | 445 | 3 | 395 | 3 | 416 | 3 | 411 | 3 | 429 | 3 | 392.643 | 22
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+6 |  | DA+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3
| 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  | 210 |  | 211 |  | 212
| 30/0 |  | 30/1 |  | 30/2 |  | 30/3 |  | 30/4 |  | 30/5 |  | 30/6 |  | 30/7 |  | 30/8 |  | 30/9 |  | 30/10 |  | 30/11 |  | 30/12 |  | 30/13 |  | 30/14 |  | 30/15 |  | 30/16 |  | 30/17 |  | 30/18 |  | 31/0 |  | 31/1 |  | 31/2
| 3 | 400.999 | 3 | 437 | 3 | 403 | 3 | 412 | 3 | 424 | 3 | 416 | 3 | 410 | 3 | 415 | 3 | 412 | 3 | 409 | 3 | 426 | 3 | 414 | 3 | 415 | 3 | 378 | 3 | 417 |  | 346 | 3 | 412 | 3 | 428 | 3 | 400.73 | 3 | 413.999 | 3 | 424 | 3 | 411 | 21
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DB2+0 |  | DA+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+6 |  | DC2+0 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA+3
TP TOWER
| 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220 |  | 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230 |  | 231 |  | 232 |  | 233 |  | 234
| 31/3 |  | 31/4 |  | 31/5 |  | 31/6 |  | 31/7 |  | 31/8 |  | 31/9 |  | 31/10 |  | 31/11 |  | 31/12 |  | 31/13 |  | 31/14 |  | 31/15 |  | 31/16 |  | 31/17 |  | 31/18 |  | 31/19 |  | 31/20 |  | 31/21 |  | 31/22 |  | 31/23 |  | 31/24
| 3 | 427 | 3 | 413 | 3 | 427 | 3 | 408 | 3 | 432 | 3 | 408 | 3 | 409 | 1 | 415 | 3 | 346 | 3 | 342 | 3 | 409 | 3 | 391 | 3 | 437 | 3 | 373 | 3 | 463 | 3 | 431 | 3 | 409 | 3 | 424 | 3 | 395 | 3 | 419 | 3 | 392 | 3 | 408 | 21
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA-3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+6 |  | DB1+0 |  | DA+6 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+9 |  | DA+6 |  | DA+9 |  | DB1+9 |  | DA+3 |  | DA-1.5 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+9
| 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240 |  | 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250 |  | 251 |  | 252 |  | 253 |  | 254 |  | 255 |  | 256
| 31/25 |  | 31/26 |  | 31/27 |  | 32/0 |  | 32/1 |  | 32/2 |  | 32/3 |  | 32/4 |  | 32/5 |  | 32/6 |  | 32/7 |  | 32/8 |  | 32/9 |  | 32/10 |  | 33/0 |  | 33/1 |  | 33/2 |  | 33/3 |  | 33/4 |  | 33A/0 |  | 34/0 |  | 34/1
| 3 | 432 | 3 | 383.001 | 3 | 398.944 | 3 | 372 | 3 | 385 | 3 | 407 | 3 | 412 | 3 | 400 | 3 | 419 | 3 | 404 | 3 | 436 | 3 | 374 | 3 | 384 |  | 360.177 | 3 | 358.001 | 3 | 452 | 3 | 388 | 3 | 452 | 3 | 387.35 | 3 | 237.316 | 3 | 479 | 3 | 361 | 21
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA-3 |  | DA+3 |  | DA+3 |  | DB2+3 |  | DA+9 |  | DA+3 |  | DA+9 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+9 |  | DA+9 |  | DB2+3 |  | DA+9 |  | DA+3 |  | DA+9 |  | DA+9 |  | DC2+0 |  | DD45+9 |  | DA+6
Petrolium Pipeline
| 257 |  | 258 |  | 259 |  | 260 |  | 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270 |  | 271 |  | 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277 |  | 278
| 34/2 |  | 34/3 |  | 34/4 |  | 34/5 |  | 34/6 |  | 34/7 |  | 34/8 |  | 34/9 |  | 34/10 |  | 35/0 |  | 35/1 |  | 35/2 |  | 35/3 |  | 35/4 |  | 35/5 |  | 35/6 |  | 35/7 |  | 35/8 |  | 35/9 |  | 36/0 |  | 36/1 |  | 36/2
| 3 | 459 | 3 | 371 | 3 | 437 | 3 | 369 | 3 | 451 | 3 | 389 | 3 | 385 | 3 | 417 | 3 | 414.575 | 3 | 422 | 3 | 384 | 3 | 428 | 3 | 400 | 3 | 423 | 3 | 387 | 3 | 419 | 3 | 393 | 3 | 404 | 3 | 434.613 | 3 | 307 | 3 | 326 | 3 | 392 | 22
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+6 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA-3 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+9 |  | DB1+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+9 |  | DA-3 |  | DA+3 |  | DA+9 |  | DB1+6 |  | DA+6 |  | DA+9
| 279 |  | 280 |  | 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290 |  | 291 |  | 292 |  | 293 |  | 294 |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | 300
| 36/3 |  | 36/4 |  | 36/5 |  | 36/6 |  | 36/7 |  | 36/8 |  | 36/9 |  | 37/0 |  | 37/1 |  | 37/2 |  | 37/3 |  | 37/4 |  | 37/5 |  | 37/6 |  | 37/7 |  | 37/8 |  | 37/9 |  | 37/10 |  | 38/0 |  | 38/1 |  | 38/2 |  | 39/0
132kV
OHTL
| 3 | 441 | 3 | 399 | 3 | 441 | 3 | 399 | 3 | 432 | 3 | 357 | 3 | 398.258 | 3 | 355 | 3 | 407 | 3 | 303 | 3 | 387 | 3 | 419 | 3 | 389 | 3 | 381 | 3 | 410 | 3 | 430 | 3 | 409 | 3 | 409.505 | 3 | 381 | 3 | 293 | 3 | 354.846 | 3 | 258.435 | 22
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+9 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+3 |  | DA+3 |  | DA+6 |  | DB1+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA-3 |  | DA+9 |  | DA-3 |  | DA+6 |  | DB2+0 |  | DA+0 |  | DA-3 |  | DB2+9
RRPVNL
| 301 |  | 302 |  | 303 |  | 304 |  | 305 |  | 306 |  | 307 |  | 308 |  | 309 |  | 310 |  | 311 |  | 312 |  | 313 |  | 314 |  | 315 |  | 316 |  | 317 |  | 318 |  | 319
| 40/0 |  | 40/1 |  | 40/2 |  | 40/3 |  | 40/4 |  | 41/0 |  | 41/1 |  | 41/2 |  | 41/3 |  | 41/4 |  | 41/5 |  | 41/6 |  | 42/0 |  | 43/0 |  | 44/0 |  | 44/1 |  | 45/0 | 132kV | 46/0 | 400kV | 47/0
[34 empty] | 220kV |  | 2 Nos.
[34 empty] | OHTL |  | OHTL
| 3 | 413.001 | 3 | 371 | 3 | 355 | 3 | 388 | 3 | 384.061 | 3 | 382.001 | 3 | 357 | 3 | 418 | 3 | 422 | 3 | 383 | 3 | 381 | 3 | 352.745 | 3 | 255.321 | 3 | 417.702 | 3 | 340 | 3 | 410.291 | 3 | 364.523 | 3 | 368 | 3 | [7 empty] | 19
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DC1+9 |  | DA+3 |  | DA+9 |  | DA+3 |  | DA+6 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DC1+0 |  | DB2+6 |  | DA-3 |  | DC2+9 |  | DD60+18 |  | DD60+18
[28 empty] | SH 7 | [5 empty] | RRVPNL |  | RRVPNL | CP TOWER
302
Tentative Tower Summary
|  |  | Tower Type |  |  | Qty |  | Tower Type |  |  | Qty |  | Tower Type |  |  | Qty |  | Tower Type |  |  | Qty |  | Tower Type |  |  | Qty |  | Tower Type |  |  | Qty |  | Tower Type |  |  | Qty |  | Tower Type |  |  | Qty
|  |  | DA+0 |  |  | 88 |  | DB1+0 |  |  | 2 |  | DB2+0 |  |  | 6 |  | DC1+0 |  |  | 10 |  | DC2+0 |  |  | 15 |  | DD45+0 |  |  | 18 |  | DD60+0 |  |  | 15 |  | DDH |  |  | 4
|  |  | DA+1.5 |  |  | 7 |  | DB1+18 |  |  | 3 |  | DB2+18 |  |  | 2 |  | DC1+18 |  |  | 2 |  | DC2+18 |  |  | 3 |  | DD45+18 |  |  | 2 |  | DD60+18 |  |  | 2
|  |  | DA+3 |  |  | 63 |  | DB1+9 |  |  | 3 |  | DB2+25 |  |  | 1 |  | DC1+3 |  |  | 1 |  | DC2+3 |  |  | 2 |  | DD45+25 |  |  | 1 |  | DD60+25 |  |  | 3
|  |  | DA+6 |  |  | 25 | [6 empty] | DB2+9 |  |  | 2 |  | DC1+6 |  |  | 2 |  | DC2+9 |  |  | 2 |  | DD45+3 |  |  | 5 |  | DD60+3 |  |  | 2
|  |  | DA+9 |  |  | 20 | [11 empty] | DC1+9 |  |  | 2 |  | DC2-3 |  |  | 1 |  | DD45+6 |  |  | 1 |  | DD60+6 |  |  | 6
|  |  | DA-1.5 |  |  | 26 | [11 empty] | DC1-3 |  |  | 1 | [6 empty] | DD45+9 |  |  | 5 |  | DD60+9 |  |  | 2
|  |  | DA-3 |  |  | 32 | [21 empty] | DD45-1.5 |  |  | 2 |  | DD60-3 |  |  | 4
|  |  | TOTAL |  |  | 261 |  | TOTAL |  |  | 8 |  | TOTAL |  |  | 11 |  | TOTAL |  |  | 18 |  | TOTAL |  |  | 23 |  | TOTAL |  |  | 34 |  | TOTAL |  |  | 34 |  | TOTAL |  |  | 4
|  |  | Total Towers |  |  | 368
[12 empty] | Total |  |  |  |  | 368 | [5 empty] | Tower Erection VS Completed Foundations
[12 empty] | Completed |  |  |  |  | 294 | [5 empty] | Foundation Completed | [8 empty] | 294
[12 empty] | Balance |  |  |  |  | 74 | [5 empty] | Erection Completed | [8 empty] | 271
[12 empty] | Details for balance Locations | [10 empty] | WIP | [8 empty] | 1
[12 empty] | Haryana |  |  |  |  | 4 | [5 empty] | Total | [8 empty] | 272
[12 empty] | Check Survey approval req |  |  |  |  | 14 | [5 empty] | Balance | [8 empty] | 22
[12 empty] | ULE/RC |  |  |  |  | 3
[12 empty] | Forest |  |  |  |  | 7 | [5 empty] | Balance Location Status
[12 empty] | Housing Board | [10 empty] | ROW | [8 empty] | 4
[12 empty] | ROW/Court Case/union |  |  |  |  | 40 | [5 empty] | TP Tower | [8 empty] | 2
[12 empty] | WIP |  |  |  |  | 5 | [5 empty] | H Pole Shifting | [8 empty] | 2
[12 empty] | Total |  |  |  |  | 73 | [5 empty] | Crop compensation pending | [8 empty] | 10
[23 empty] | Stub Damage Butt joint approval | [8 empty] | 1
[12 empty] | Can be taken up |  |  |  |  | 1 | [5 empty] | Deisgn change (112/0) AUX Tower | [8 empty] | 1
[23 empty] | Total | [8 empty] | 20
[23 empty] | Can be taken up | [8 empty] | 2
Progress overview (Tower wise breakups)
| TOT |  | Total Qty in No's |  | FDN |  |  | ERE
[5 empty] | Comp. |  | Bal. | Comp. |  | Balance
| DA-3 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DA-1.5 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DA+0 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DA+1.5 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DA+3 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DA+4.5 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DA+6 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DA+9 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DB1+0 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DB1+3 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DB1+6 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DB1+9 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DB1+12 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DB2+0 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DB2+3 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DB2+6 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DB2+9 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DC1+0 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DC1+3 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DC2+0 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DC2-3 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DC2+15 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DD45+0 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DD60+0 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DD60+3 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DD60+9 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DD60+18 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DD60+25 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| DD60+35 |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!
| Total |  | #VALUE! |  | #VALUE! |  | #VALUE! | #VALUE!

## WIP
KEC International Limited
DAILY PROGRESS REPORT : STATUS AS ON | [6 empty] | 2026-05-20
Name of the Project: |  | 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Contract No. & Date : |  | CC/T/W-TW/DOM/A00/24/09582/CA-1&2/25-100174/01 & 02 Dtd. 21.01.2025
FOUNDATION
S.NO. | GANG NAME | LOC. NO. | TYPE | CLASSIFICATION | D.O.S | D.O.C | REMARKS
1 | M/s. Shree Shyam Construction | 1A/0 | DD45+0 | Sandy |  |  | Excavation Complete
2 | M/s. Shree Shyam Construction | 1/2 | DA+0 | Sandy
3 | M/s. Choudhary Construction | 11/0 | DD60+18 | Sandy | 2026-05-14 |  | Pit A Chimney & Pit B PCC Complete
4 | M/s. Choudhary Construction | 16/0 | DB2+0 | Sandy | 2026-04-13 |  | No Work Due to ROW
5 | M/s. Karni Kripa Construction | 27/0 | DD60+35 | Sandy | 2026-05-02 |  | No Work
6 | M/s. Karni Kripa Construction | 31/10 | DA+6 | Sandy | 2026-05-02 |  | Pit CD PCC & All Pit Frustum Casting Complete
7 | M/s. Karni Kripa Construction | 25/1 | DA+9 | Sandy
8 | M/s. Karni Kripa Construction | 26/0 | DD60+35 | Sandy
9 | M/s. Karni Kripa Construction | 23/4 | DA+0 | Sandy
ERECTION
S.NO | GANG | LOC. NO. | T.O.T | D.O.S | D.O.C | Remarks
1 |  | 32/5 | DA+0 | 2026-01-30 |  |  | ROW since 03/02/2026
2 | M/s. Jwala Singh | 34/5 | DA+6 | 2026-05-13 |  |  | ROW Clear
3 | M/s. Jwala Singh | 34/4 | DA+9 | 2026-05-17 |  |  | 3rd Section u/p
4 | M/s. Ganesh Sinha | 40/3 | DA+3 | 2026-05-16 |  |  | 1st Section u/p
5
6
7
STRINGING
S.NO | GANG | SECTION | LENGTH (KM) | D.O.S | D.O.C | REMARKS
1
2
3
OPGW
SR.NO | GANG | SECTION | LENGTH (KM) | D.O.S | D.O.C | REMARKS
Earthing
SR.NO | GANG | LOC. NO. | T.O.T | T.O.E. | D.O.S | D.O.C | REMARKS
1
2
Tackwelding
SR.NO | GANG | LOC. NO. | T.O.T |  | D.O.S | D.O.C | REMARKS
1
2
Accessories
SR.NO | GANG | LOC. NO. | T.O.T | ACD | NO/PH/DANGER/ CKT PLATE |  | REMARKS
1
2
3

## Statuary clearance
KEC International Limited
765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Details of NH, River, Railway Line & Power Line crossing Proposals of 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
NH Crossings
S. No. | Name of NH Being crossed | Between AP nos. | Proposal submitted by M/s KEC International Ltd on dated | Owning Authority | Present status | Target date for submission
1 | NH-62 (Bikaner to Shri Ganga Nagar) | AP-14 to AP-15 | 2025-04-23 | Executive Engineer, NHAI, Bikaner | 1. Online Submission 04/08/2025, Proposal Submitted NHAI OFFICE Bikaner 10/12/2025
2 | NH-754A (Amritsar to Jam Nagar Expressway) | AP-24 to AP-25 | 2025-06-11 | NHAI, PIU - Hanumangarh | 1. Online Submission to the PGCIL Office on 25/12/2025,
Railway Line Crossings
S. No. | Name of Railway line being crossed | Between AP nos. | Proposal submitted by M/s KEC International Ltd on dated | Owning Authority | Present status | Target date for submission
1 | Lunkaransar (LKS) to Dulmera (DLC) Railway Station | AP-17 to AP-18 | 2025-04-23 | DRM, Bikaner | 1. Approved By Power Grid RHQ (Engineering). 2. Submitted through online on 02/07/2025. 3. Site Inspection done by concern authority on 23/07/25. 4. Approval Optained Power Grid by Railway Authority.
Details of Power Line Crossing Proposals of 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
S. No. | Name of Powerline being crossed | Between AP nos. | Proposal submitted by M/s KEC International Ltd on dated | Owning Authority | Present status | Target date for submission
1 | 765kV D/C Bikaner - Moga OHTL | AP-26 to AP-27 | 2025-04-23 | Power Grid | NOC provided by Power Grid for foundation work.
2 | 400kV D/C Suratgarh - Bikaner (Adani) | AP-10 to AP-11 | 2025-04-23 | Adani | 1. Submitted To State Head Adani Transmission Rajasthan (Bikaner) on 08/07/25. 2. Site Inspection done by concern authority on 16/07/25. 3. NOC obtained by Power Grid from Adani on 25/09/25 and allow for foundation work.
3 | 400kV S/C Suratgarh (Thermal Plant) - Bikaner | AP-22 to AP-23 | 2025-04-23 | RRVPNL, Bikaner | 1. Submitted To SE (T&C), RRVPNL, Bikaner on 23/06/25. 2. Site Inspection done by concern authority on 26/06/25. 3.NOC obtained by Power Grid from RRVPNL on 27/11/25 and allow for foundation work
4 | 220kV S/C SUR - BIK | AP-20A to AP-21 | 2025-04-23 | RRVPNL, Bikaner | 1. Submitted To SE (T&C), RRVPNL, Bikaner on 23/06/25. 2. Site Inspection done by concern authority on 26/06/25. 3. Approved by CE (T&C), RRVPNL, Jodhpur on 17/10/25. 4.NOC obtained by Power Grid from RRVPNL on 01/11/25 and allow for foundation work
5 | 132kV Halasar to Paltisar Fanta | AP-39 to AP-40 | 2025-04-23 | RRVPNL, Churu | NOC obtained by Power Grid from RRVPNL on 09/09/25 and allow for foundation work.
6 | 132kV S/C Bikaner - Lunkaransar | AP-15 to AP-16 | 2025-04-23 | RRVPNL, Bikaner | 1. Submitted To SE (T&C), RRVPNL, Bikaner on 23/06/25. 2. Site Inspection done by concern authority on 26/06/25. 3.NOC obtained by Power Grid from RRVPNL on 27/11/25 and allow for foundation work
7 | 132 KV S/C Halasar-Sardar Shahar | AP 45-AP46 | 2025-11-25 | RRVPNL, Ratangarh | 1.Documents Submission to the PGCIL Office Bikaner 25/11/2025 2.Submittedto SE(T&C), RRVPNL Ratangarh on 2/12/2025 3.Site Inspection Done by Concern Authority on 23/12/2025 4.NOC obtained by Power Grid from RVPN on 13/02/26 and allow for foundation work.
8 | 220 KV D/C Ratangarh- Halasar Line | AP 45-AP46 | 2025-11-25 | RRVPNL, Ratangarh | 1.Documents Submission to the PGCIL Office Bikaner 25/11/2025 2.Submittedto SE(T&C), RRVPNL Ratangarh on 2/12/2025 3.Site Inspection Done by Concern Authority on 23/12/2025 4.NOC obtained by Power Grid from RVPN on 13/02/26 and allow for foundation work.
9 | 400 KV S/C Suratgarh(SSPTT)-Ratangarh | AP 46-AP47 | 2025-11-25 | RRVPNL, Ratangarh | 1.Documents Submission to the PGCIL Office Bikaner 25/11/2025 2.Submittedto SE(T&C), RRVPNL Ratangarh on 2/12/2025 3.Site Inspection Done by Concern Authority on 23/12/2025 4.NOC obtained by Power Grid from RVPN on 13/02/26 and allow for foundation work.
10 | 400 KV S/C Suratgarh(SSPTT)-Ratangarh | AP 46-AP47 | 2025-11-25 | RRVPNL, Ratangarh | 1.Documents Submission to the PGCIL Office Bikaner 25/11/2025 2.Submittedto SE(T&C), RRVPNL Ratangarh on 2/12/2025 3.Site Inspection Done by Concern Authority on 23/12/2025 4.NOC obtained by Power Grid from RVPN on 13/02/26 and allow for foundation work.
11 | 220KVD/C LINE KELAN TO BAJJU TL | 1/0- 1/1 | 24/12/2025 | ACME | 1.Documents Submission to PGCIL Office for Review and Approval Pending by PGCIL Engineering 24/12/2025 2.PGCIL Approved on 03/04/2026 3.Submitted to Concern Authority (220KV Line)ACME & PGCIL on 04/04/2026
Oil & Gas Pipe Line Crossings
S. No. | Name of Oil & Gas Pipe Line being crossed | Between AP nos. | Proposal submitted by M/s KEC International Ltd on dated | Owning Authority | Present status | Target date for submission
1 | HMPL (MUNDRA - BHATINDA) Petrolium Pipe Line | AP-33A to AP-34 | 2025-06-11 | HPCL - Mittal Pipelines Ltd, Bhatinda | 1. Submitted to Power Grid for submission to concern authority on 08/08/25. 2.HMPL Engineer Site Visit 17/10/2025
Canal Crossings
S. No. | Name of Canal being crossed | Between AP nos. | Proposal submitted by M/s KEC International Ltd on dated | Owning Authority | Present status | Target date for submission
1 | Bikaner Lift Canal (Indra Gandhi) | 12/5 to AP-13 | 2025-06-11 | IGNP, Bikaner | NOC obtained by Power Grid from Canal Department on 09/09/25 and allow for foundation work.
PTCC
S. No. | Name of Organization | Between AP nos. | Proposal submitted by M/s KEC International Ltd on dated | Owning Authority | Present status | Target date for submission
1 | PTCC(Power Telecommunication Cordination Committee) | Gantry to AP-47 | 25/02/2026 | PTCC | Submitted to Power Grid on 25/02/26
Civil Aviation
S. No. | Name of Organization | Between AP nos. | Proposal submitted by M/s KEC International Ltd on dated | Owning Authority | Present status | Target date for submission
1 | Airport Authority of India | Gantry to AP-47 |  | AAI | Submitted to Concern Authority by Power Grid

## Stringing (hidden)
KEC International Limited
765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Details of Stringing | [10 empty] | 2026-05-20
CUMM. SR.NO | MONTH SR.NO. | Section
|  | From | To | Length in Km's | Cum. Length in Km's | Insulator Hoisting | Paying Out Start | Paying Out Completed | Final sag | Name of the Contractor | Remarks
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76

## OPGW (hidden)
KEC International Limited
765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Details of OPGW Stringing | [10 empty] | 2026-05-20
Cum. Sr.No. | Month Sr.No. | Section |  |  |  |  | Paying Out Start | Paying Out Completed | Final sag | Name of the Contractor | Remarks
|  | From | To | Section Length in Km's | Drum Length in Km's | Cum. Drum Length in Km's
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16

## Accessories (hidden)
KEC International Limited
765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Details of Accessories | [12 empty] | 2026-05-20
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Danger Plate | Number Plate | Phase Plate | Circuit Plate | Anti Climbing device | Start Date | End Date | Name of the Contractor | Name of Supervisor | Remarks
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44

## Shield Wire Earthing
KEC International Limited
765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL
Details of Shield Wire Earthing | [9 empty] | 2026-05-20
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Type of Classification | Start | Complete | Name of the Contractor | Name of Supervisor | PGCIL Person /Quest | Remarks
1 |  | 3/0 | DC2+9 | SANDY
2 |  | 4/7 | DB1+0 | SANDY
3 |  | 5/7 | DB1+3 | SANDY
4 |  | 7/0 | DB1+3 | SANDY
5 |  | 9/0 | DB1+0 | SANDY
6 |  | 13/0 | DC1+3 | SANDY
7 |  | 20/0 | DC1+6 | SANDY
8 |  | 27/1 | DB1+9 | SANDY
9 |  | 29/12 | DB1+0 | SANDY
10 |  | 30/9 | DB1+0 | SANDY
11 |  | 31/9 | DB1+0 | SANDY
12 |  | 32/0 | DB2+3 | SANDY
13 |  | 34/0 | DD45+9 | SANDY
14 |  | 36/0 | DB1+6 | SANDY
15 |  | 38/0 | DB2+0 | SANDY
16 |  | 47/0 | DD60+18 | SANDY

## TS Gantry - AP47
CLIENT :- POWERGRID SIWANI TRANSMISSION LIMITED
NAME OF PROJECT :- Bikaner-IV PS TO Siwani 765KV D/C (2nd) Transmission Line Part-01
M/s. KEC INTERNATIONAL LIMITED
CHECK SURVEY TOWER SCHEDULE SECTION:- PS GANTRY TO AP44 LENGTH :- 123.174 KM
KEC/TA512/BSTL/TS/ REV.0
Sr. No. | AP No. | TOWER No. | TYPE OF TOWER | For Visual Chart | RAISED CHIMNEY | Section Length (m) | SPAN (Mtr) | CUMULATIVE SPAN | R.L (Mtr) | DEVIATION ANGLE (Deg) | Sum of Adjacent Spans | WIND SPAN (Mtr) | WEIGHT SPAN IN Mtr (Cold) |  |  | WEIGHT SPAN IN Mtr (Hot) |  |  | UTM Coordinates(43) |  | CROSSING DETAILS | HT of Tower (Mtr) | Village Name | Tehsil Name | District Name | REMARKS
[13 empty] | Left | Right | Total | Left | Right | Total | Easting (m) | Y Northing (m)
|  | Gantry | Gantry | 146 | [14 empty] | 325896.991 | 3145660.004 |  |  | KELAN | CHHATARGARH | BIKANER
[7 empty] | 141.914 | 141.914 | [18 empty] | 0.020273
1 | AP-1 | 1/0 | DD60+3 | 289 |  | 141.914 |  |  | 218.44 | 2° 34' 45"LT | 379.604 | 217.5 | 0 | 29 | 29 | 0 | 82 | 82 | 325951.001 | 3145523.99 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 237.69 | 379.604 | [12 empty] | SS BOUNDARY, 11KV, TAR ROAD, NEW 132KV DC LINE KELAN TO BAJJU. | [5 empty] | 0.054229
2 |  | 1/1 | DB1+18 | 408 |  | 237.69 |  |  | 223.415 |  | 617.69 | 348.5 | 261 | 262 | 523 | 208 | 244 | 452 | 326069.638 | 3145260.464 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 380 | 759.604 | [12 empty] | HUT, CT | [5 empty] | 0.10851
3 |  | 1/2 | DA+0 | 382.118 |  |  |  |  | 222.954 |  | 755.728 | 395.059 | 147 | 204 | 351 | 165 | 200 | 365 | 326237.127 | 3144888.426 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 375.728 | 1135.332 | [18 empty] | 0.16219
4 | AP-1A | 1A/0 | DD45+0 | 360 |  | 755.728 |  |  | 219.207 | 44° 22' 1"LT | 735.728 | 371.059 | 179 | 167 | 346 | 183 | 172 | 355 | 326393.99 | 3144539.99 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 360 | 1495.332 | [12 empty] | CT | [5 empty] | 0.21362
5 |  | 1A/1 | DA-1.5 | 384 |  |  |  |  | 222.902 |  | 744 | 372 | 193 | 192 | 385 | 189 | 192 | 381 | 326729.179 | 3144408.657 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 384 | 1879.332 | [12 empty] | CT | [5 empty] | 0.26848
6 |  | 1A/2 | DA-1.5 | 385 |  |  |  |  | 223.024 |  | 769 | 384.5 | 193 | 208 | 401 | 193 | 203 | 396 | 327086.714 | 3144268.568 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 385 | 2264.332 | [12 empty] | CT | [5 empty] | 0.32348
7 |  | 1A/3 | DA-3 | 370.347 |  |  |  |  | 221.868 |  | 755.347 | 377.6735 | 178 | 167 | 345 | 183 | 174 | 357 | 327445.18 | 3144128.115 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 370.347 | 2634.679 | [12 empty] | CT | [5 empty] | 0.37638
8 | AP-2 | 2/0 | DD60+3 | 351 |  | 1499.347 |  |  | 218.955 | 54° 40' 44"LT | 721.347 | 360.6735 | 204 | 144 | 348 | 198 | 154 | 352 | 327790.003 | 3143993.007 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 351 | 2985.679 | [18 empty] | 0.42653
9 |  | 2/1 | DA+6 | 420 |  |  |  |  | 221.224 |  | 771 | 385.5 | 207 | 186 | 393 | 198 | 194 | 392 | 328083.429 | 3144185.626 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 420 | 3405.679 | [12 empty] | CT | [5 empty] | 0.48653
10 |  | 2/2 | DA+9 | 419 |  |  |  |  | 223.074 |  | 839 | 419.5 | 235 | 205 | 440 | 228 | 207 | 435 | 328434.537 | 3144416.11 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 419 | 3824.679 | [18 empty] | 0.54638
11 |  | 2/3 | DA+9 | 350 |  |  |  |  | 224.088 |  | 769 | 384.5 | 215 | 217 | 432 | 214 | 205 | 419 | 328784.81 | 3144646.045 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 350 | 4174.679 | [18 empty] | 0.59638
12 |  | 2/4 | DA+9 | 445 |  |  |  |  | 217.09 |  | 795 | 397.5 | 133 | 267 | 400 | 146 | 254 | 400 | 329077.4 | 3144838.116 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 445 | 4619.679 | [12 empty] | HUT, CT | [5 empty] | 0.65995
13 |  | 2/5 | DA+0 | 384 |  |  |  |  | 216.828 |  | 829 | 414.5 | 179 | 124 | 303 | 193 | 145 | 338 | 329449.407 | 3145082.319 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 384 | 5003.679 | [12 empty] | CT | [5 empty] | 0.71481
14 |  | 2/6 | DA+9 | 440.898 |  |  |  |  | 220.364 |  | 824.898 | 412.449 | 261 | 247 | 508 | 241 | 240 | 481 | 329770.421 | 3145293.048 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 440.898 | 5444.577 | [12 empty] | HUT, CT | [5 empty] | 0.7778
15 | AP-2A | 2A/0 | DB2+3 | 367 |  | 2809.898 |  |  | 220.773 | 14° 28' 44"RT | 807.898 | 403.949 | 194 | 154 | 348 | 203 | 163 | 366 | 330138.999 | 3145535 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 367 | 5811.577 | [12 empty] | HUT | [5 empty] | 0.83023
16 |  | 2A/1 | DA+9 | 412 |  |  |  |  | 220.039 |  | 779 | 389.5 | 213 | 251 | 464 | 205 | 238 | 443 | 330486.411 | 3145653.296 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 412 | 6223.577 | [12 empty] | CT | [5 empty] | 0.88908
17 |  | 2A/2 | DA-1.5 | 426 |  |  |  |  | 221.621 |  | 838 | 419 | 162 | 193 | 355 | 175 | 200 | 375 | 330876.421 | 3145786.096 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 426 | 6649.577 | [12 empty] | HUT | [5 empty] | 0.94994
18 |  | 2A/3 | DA+3 | 414 |  |  |  |  | 221.244 |  | 840 | 420 | 233 | 188 | 421 | 228 | 194 | 422 | 331279.684 | 3145923.409 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 414 | 7063.577 | [18 empty] | 1.0091
19 |  | 2A/4 | DA+9 | 400 |  |  |  |  | 219.129 |  | 814 | 407 | 227 | 176 | 403 | 221 | 183 | 404 | 331671.588 | 3146056.854 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 400 | 7463.577 | [12 empty] | CT | [5 empty] | 1.0662
20 |  | 2A/5 | DA+9 | 434.969 |  |  |  |  | 223.9 |  | 834.969 | 417.4845 | 225 | 226 | 451 | 218 | 224 | 442 | 332050.239 | 3146185.787 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 434.969 | 7898.546 | [18 empty] | 1.1284
21 | AP-3 | 3/0 | DC2+9 | 480 |  | 2453.969 |  |  | 222.183 | 26° 34' 5"LT | 914.969 | 457.4845 | 210 | 244 | 454 | 212 | 244 | 456 | 332461.992 | 3146325.991 |  |  | KELAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 480 | 8378.546 | [12 empty] | CT | [5 empty] | 1.1969
22 |  | 3/1 | DB1+9 | 482 |  | 480 |  |  | 221.23 |  | 962 | 481 | 237 | 212 | 449 | 238 | 222 | 460 | 332799.192 | 3146667.6 |  |  | AMBARAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 482 | 8860.546 | [18 empty] | 1.2658
23 |  | 3/2 | DA+9 | 358 |  |  |  |  | 227.974 |  | 840 | 420 | 271 | 210 | 481 | 263 | 201 | 464 | 333137.797 | 3147010.631 |  |  | AMBARAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 358 | 9218.546 | [18 empty] | 1.3169
24 |  | 3/3 | DA+9 | 325 |  |  |  |  | 222.824 |  | 683 | 341.5 | 149 | 219 | 368 | 158 | 202 | 360 | 333389.291 | 3147265.414 |  |  | AMBARAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 325 | 9543.546 | [18 empty] | 1.3634
25 |  | 3/4 | DA-1.5 | 406 |  |  |  |  | 224.628 |  | 731 | 365.5 | 106 | 176 | 282 | 124 | 184 | 308 | 333617.604 | 3147496.712 |  |  | AMBARAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 406 | 9949.546 | [12 empty] | CT | [5 empty] | 1.4214
26 |  | 3/5 | DA+6 | 385 |  |  |  |  | 222.428 |  | 791 | 395.5 | 231 | 214 | 445 | 223 | 208 | 431 | 333902.818 | 3147785.656 |  |  | AMBARAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 385 | 10334.546 | [18 empty] | 1.4764
27 |  | 3/6 | DA+3 | 404 |  |  |  |  | 221.597 |  | 789 | 394.5 | 172 | 150 | 322 | 178 | 167 | 345 | 334173.281 | 3148059.654 |  |  | AMBARAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 404 | 10738.546 | [18 empty] | 1.5341
28 |  | 3/7 | DA+3 | 409.269 |  |  |  |  | 231.512 |  | 813.269 | 406.6345 | 254 | 227 | 481 | 239 | 220 | 459 | 334457.091 | 3148347.174 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 409.269 | 11147.815 | [18 empty] | 1.5925
29 | AP-3A | 3A/0 | DD45+0 | 359 |  | 2769.269 |  |  | 230.299 | 37° 22' 6"RT | 768.269 | 384.1345 | 183 | 190 | 373 | 190 | 186 | 376 | 334744.602 | 3148638.445 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 359 | 11506.815 | [18 empty] | 1.6438
30 |  | 3A/1 | DA+0 | 349 |  |  |  |  | 228.709 |  | 708 | 354 | 170 | 217 | 387 | 174 | 202 | 376 | 335100.105 | 3148688.433 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 349 | 11855.815 | [18 empty] | 1.6937
31 |  | 3A/2 | DA-1.5 | 347 |  |  |  |  | 223.532 |  | 696 | 348 | 132 | 180 | 312 | 148 | 178 | 326 | 335445.705 | 3148737.028 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 347 | 12202.815 | [18 empty] | 1.7433
32 |  | 3A/3 | DA-1.5 | 378.992 |  |  |  |  | 222.472 |  | 725.992 | 362.996 | 167 | 175 | 342 | 170 | 180 | 350 | 335789.324 | 3148785.345 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 378.992 | 12581.807 | [12 empty] | HOUSE | [5 empty] | 1.7974
33 | AP-4 | 4/0 | DB2+0 | 367 |  | 1433.992 |  |  | 223.529 | 14° 45' 47"RT | 745.992 | 372.996 | 205 | 127 | 332 | 200 | 144 | 344 | 336164.624 | 3148838.116 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 367 | 12948.807 | [12 empty] | Cart track, Hut & Well | [5 empty] | 1.8498
34 |  | 4/1 | DA-3 | 406 |  |  |  |  | 236.481 |  | 773 | 386.5 | 240 | 177 | 417 | 224 | 185 | 409 | 336529.073 | 3148794.922 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 406 | 13354.807 | [18 empty] | 1.9078
35 |  | 4/2 | DA+6 | 434 |  |  |  |  | 232.542 |  | 840 | 420 | 229 | 305 | 534 | 222 | 280 | 502 | 336932.252 | 3148747.138 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 434 | 13788.807 | [18 empty] | 1.9698
36 |  | 4/3 | DA-3 | 404 |  |  |  |  | 223.342 |  | 838 | 419 | 130 | 142 | 272 | 156 | 161 | 317 | 337363.235 | 3148696.059 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 404 | 14192.807 | [18 empty] | 2.0275
37 |  | 4/4 | DA+9 | 387 |  |  |  |  | 222.963 |  | 791 | 395.5 | 263 | 187 | 450 | 245 | 189 | 434 | 337764.427 | 3148648.511 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 387 | 14579.807 | [18 empty] | 2.0828
38 |  | 4/5 | DA+9 | 442 |  |  |  |  | 224.181 |  | 829 | 414.5 | 200 | 261 | 461 | 199 | 250 | 449 | 338148.738 | 3148602.963 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 442 | 15021.807 | [12 empty] | Cart track | [5 empty] | 2.146
39 |  | 4/6 | DA+3 | 398 |  |  |  |  | 221.855 |  | 840 | 420 | 182 | 208 | 390 | 194 | 206 | 400 | 338587.666 | 3148550.943 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 398 | 15419.807 | [18 empty] | 2.2028
40 |  | 4/7 | DB1+0 | 442 |  | 2838 |  |  | 223.214 |  | 840 | 420 | 191 | 143 | 334 | 194 | 166 | 360 | 338982.9 | 3148504.1 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 442 | 15861.807 | [12 empty] | Water tank | [5 empty] | 2.266
41 |  | 4/8 | DA+9 | 376 |  |  |  |  | 231.006 |  | 818 | 409 | 300 | 225 | 525 | 278 | 214 | 492 | 339421.828 | 3148452.08 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 376 | 16237.807 | [18 empty] | 2.3197
42 |  | 4/9 | DA+3 | 464 |  |  |  |  | 230.369 |  | 840 | 420 | 152 | 258 | 410 | 163 | 251 | 414 | 339795.214 | 3148407.827 |  |  | RAJASAR BHATIYAN | CHHATARGARH | BIKANER |  | 0
[7 empty] | 464 | 16701.807 | [12 empty] | Hut | [5 empty] | 2.386
43 |  | 4/10 | DA-1.5 | 365 |  |  |  |  | 229.268 |  | 829 | 414.5 | 207 | 207 | 414 | 215 | 200 | 415 | 340255.99 | 3148353.217 |  |  | MAKADASAR | CHHATARGARH | BIKANER |  | 0
[7 empty] | 365 | 17066.807 | [12 empty] | Hut & Water tank | [5 empty] | 2.4381
44 |  | 4/11 | DA+0 | 406 |  |  |  |  | 223.572 |  | 771 | 385.5 | 159 | 187 | 346 | 166 | 192 | 358 | 340618.453 | 3148310.258 |  |  | MAKADASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 406 | 17472.807 | [12 empty] | Cart track | [5 empty] | 2.4961
45 |  | 4/12 | DA+3 | 419 |  |  |  |  | 223.792 |  | 825 | 412.5 | 220 | 218 | 438 | 215 | 216 | 431 | 341021.631 | 3148262.474 |  |  | MAKADASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 419 | 17891.807 | [12 empty] | Water tank | [5 empty] | 2.556
46 |  | 4/13 | DA+0 | 400 |  |  |  |  | 225.061 |  | 819 | 409.5 | 201 | 178 | 379 | 204 | 185 | 389 | 341437.719 | 3148213.161 |  |  | MAKADASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 400 | 18291.807 | [12 empty] | Water tank | [5 empty] | 2.6131
47 |  | 4/14 | DA+3 | 379.424 |  |  |  |  | 226.339 |  | 779.424 | 389.712 | 223 | 196 | 419 | 216 | 194 | 410 | 341834.939 | 3148166.083 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 379.424 | 18671.231 | [18 empty] | 2.6673
48 | AP-5 | 5/0 | DB1+0 | 420 |  | 3251.424 |  |  | 228.282 | 0° 48' 12"RT | 799.424 | 399.712 | 184 | 185 | 369 | 186 | 192 | 378 | 342211.726 | 3148121.427 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 420 | 19091.231 | [12 empty] | Hut | [5 empty] | 2.7273
49 |  | 5/1 | DA+6 | 419 |  |  |  |  | 227.579 |  | 839 | 419.5 | 236 | 249 | 485 | 229 | 238 | 467 | 342628.073 | 3148066.154 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 419 | 19510.231 | [18 empty] | 2.7872
50 |  | 5/2 | DA+0 | 421 |  |  |  |  | 225.475 |  | 840 | 420 | 171 | 188 | 359 | 182 | 195 | 377 | 343043.429 | 3148011.012 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 421 | 19931.231 | [18 empty] | 2.8473
51 |  | 5/3 | DA+3 | 417 |  |  |  |  | 227.186 |  | 838 | 419 | 234 | 188 | 422 | 228 | 194 | 422 | 343460.767 | 3147955.607 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 417 | 20348.231 | [18 empty] | 2.9069
52 |  | 5/4 | DA+3 | 419 |  |  |  |  | 231.525 |  | 836 | 418 | 230 | 219 | 449 | 224 | 217 | 441 | 343874.14 | 3147900.729 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 419 | 20767.231 | [18 empty] | 2.9667
53 |  | 5/5 | DA+6 | 419 |  |  |  |  | 226.613 |  | 838 | 419 | 201 | 185 | 386 | 204 | 193 | 397 | 344289.496 | 3147845.587 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 419 | 21186.231 | [12 empty] | Water tank | [5 empty] | 3.0266
54 |  | 5/6 | DA+6 | 420 |  |  |  |  | 231.673 |  | 839 | 419.5 | 234 | 229 | 463 | 228 | 224 | 452 | 344704.852 | 3147790.446 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 420 | 21606.231 | [18 empty] | 3.0866
55 |  | 5/7 | DB1+3 | 419 |  | 2935 |  |  | 230.863 |  | 839 | 419.5 | 192 | 199 | 391 | 198 | 202 | 400 | 345121.199 | 3147735.172 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 419 | 22025.231 | [18 empty] | 3.1465
56 |  | 5/8 | DA+6 | 420 |  |  |  |  | 230.207 |  | 839 | 419.5 | 221 | 244 | 465 | 218 | 235 | 453 | 345536.555 | 3147680.031 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 420 | 22445.231 | [12 empty] | Metal road | [5 empty] | 3.2065
57 |  | 5/9 | DA+3 | 419 |  |  |  |  | 226.3 |  | 839 | 419.5 | 177 | 206 | 383 | 187 | 208 | 395 | 345952.902 | 3147624.757 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 419 | 22864.231 | [18 empty] | 3.2663
58 |  | 5/10 | DA+3 | 419 |  |  |  |  | 227.053 |  | 838 | 419 | 214 | 176 | 390 | 213 | 186 | 399 | 346368.257 | 3147569.616 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 419 | 23283.231 | [18 empty] | 3.3262
59 |  | 5/11 | DA+9 | 419.406 |  |  |  |  | 227.996 |  | 838.406 | 419.203 | 243 | 238 | 481 | 234 | 231 | 465 | 346783.613 | 3147514.474 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 419.406 | 23702.637 | [12 empty] | Water tank | [5 empty] | 3.3861
60 | AP-6 | 6/0 | DB1+0 | 403 |  | 2096.406 |  |  | 231.199 | 5° 57' 41"LT | 822.406 | 411.203 | 182 | 201 | 383 | 190 | 201 | 391 | 347199.371 | 3147459.279 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 403 | 24105.637 | [12 empty] | Cart track | [5 empty] | 3.4437
61 |  | 6/1 | DA+3 | 437 |  |  |  |  | 228.452 |  | 840 | 420 | 203 | 200 | 403 | 203 | 206 | 409 | 347602.214 | 3147448.02 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 437 | 24542.637 | [12 empty] | Fencing | [5 empty] | 3.5061
62 |  | 6/2 | DA+3 | 403 |  |  |  |  | 232.51 |  | 840 | 420 | 238 | 192 | 430 | 233 | 195 | 428 | 348039.043 | 3147435.811 |  |  | BINJHARWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 403 | 24945.637 | [18 empty] | 3.5637
63 |  | 6/3 | DA+6 | 437 |  |  |  |  | 231.405 |  | 840 | 420 | 211 | 240 | 451 | 209 | 234 | 443 | 348441.886 | 3147424.552 |  |  | SODHWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 437 | 25382.637 | [18 empty] | 3.6261
64 |  | 6/4 | DA+3 | 363 |  |  |  |  | 229.886 |  | 800 | 400 | 198 | 150 | 348 | 204 | 159 | 363 | 348878.715 | 3147412.343 |  |  | SODHWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 363 | 25745.637 | [18 empty] | 3.6779
65 |  | 6/5 | DA+9 | 469 |  |  |  |  | 229.627 |  | 832 | 416 | 213 | 251 | 464 | 205 | 247 | 452 | 349241.574 | 3147402.202 |  |  | SODHWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 469 | 26214.637 | [18 empty] | 3.7449
66 |  | 6/6 | DB1+3 | 403 |  | 2512 |  |  | 231.872 |  | 872 | 436 | 219 | 218 | 437 | 224 | 213 | 437 | 349710.39 | 3147389.099 |  |  | SODHWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 403 | 26617.637 | [18 empty] | 3.8025
67 |  | 6/7 | DA+0 | 432 |  |  |  |  | 231.766 |  | 835 | 417.5 | 186 | 205 | 391 | 191 | 209 | 400 | 350113.233 | 3147377.84 |  |  | SODHWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 432 | 27049.637 | [12 empty] | Cart track & 11kV | [5 empty] | 3.8642
68 |  | 6/8 | DA+6 | 407 |  |  |  |  | 228.091 |  | 839 | 419.5 | 228 | 214 | 442 | 225 | 212 | 437 | 350545.065 | 3147365.77 |  |  | SODHWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 407 | 27456.637 | [18 empty] | 3.9224
69 |  | 6/9 | DA+3 | 427 |  |  |  |  | 229.003 |  | 834 | 417 | 193 | 178 | 371 | 197 | 189 | 386 | 350951.906 | 3147354.4 |  |  | SODHWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 427 | 27883.637 | [18 empty] | 3.9834
70 |  | 6/10 | DA+6 | 385.067 |  |  |  |  | 233.367 |  | 812.067 | 406.0335 | 250 | 221 | 471 | 240 | 213 | 453 | 351378.739 | 3147342.47 |  |  | SODHWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 385.067 | 28268.704 | [18 empty] | 4.0384
71 | AP-7 | 7/0 | DB1+3 | 444 |  | 2054.067 |  |  | 231.068 | 0° 4' 54"LT | 829.067 | 414.5335 | 165 | 197 | 362 | 173 | 205 | 378 | 351763.656 | 3147331.712 |  |  | SODHWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 444 | 28712.704 | [12 empty] | Cart track | [5 empty] | 4.1018
72 |  | 7/1 | DA+6 | 394 |  |  |  |  | 233.302 |  | 838 | 419 | 248 | 246 | 494 | 240 | 231 | 471 | 352207.5 | 3147319.94 |  |  | SODHWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 394 | 29106.704 | [12 empty] | Cart track | [5 empty] | 4.1581
73 |  | 7/2 | DA-1.5 | 367 |  |  |  |  | 231.851 |  | 761 | 380.5 | 148 | 186 | 334 | 164 | 186 | 350 | 352601.361 | 3147309.493 |  |  | SODHWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 367 | 29473.704 | [18 empty] | 4.2105
74 |  | 7/3 | DA+0 | 388 |  |  |  |  | 229.925 |  | 755 | 377.5 | 181 | 183 | 364 | 182 | 187 | 369 | 352968.232 | 3147299.762 |  |  | SODHWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 388 | 29861.704 | [18 empty] | 4.266
75 |  | 7/4 | DA+0 | 389 |  |  |  |  | 231.926 |  | 777 | 388.5 | 205 | 187 | 392 | 202 | 190 | 392 | 353356.096 | 3147289.475 |  |  | DUDIWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 389 | 30250.704 | [18 empty] | 4.3215
76 |  | 7/5 | DA-1.5 | 385 |  |  |  |  | 234.788 |  | 774 | 387 | 202 | 209 | 411 | 200 | 204 | 404 | 353744.959 | 3147279.161 |  |  | DUDIWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 385 | 30635.704 | [18 empty] | 4.3765
77 |  | 7/6 | DA+0 | 389 |  |  |  |  | 230.468 |  | 774 | 387 | 177 | 202 | 379 | 182 | 200 | 382 | 354129.824 | 3147268.953 |  |  | DUDIWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 389 | 31024.704 | [12 empty] | Cart track | [5 empty] | 4.4321
78 |  | 7/7 | DA-1.5 | 395 |  |  |  |  | 230.607 |  | 784 | 392 | 187 | 146 | 333 | 190 | 163 | 353 | 354518.687 | 3147258.639 |  |  | DUDIWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 395 | 31419.704 | [12 empty] | Hut | [5 empty] | 4.4885
79 |  | 7/8 | DA+3 | 432 |  |  |  |  | 235.609 |  | 827 | 413.5 | 250 | 232 | 482 | 234 | 228 | 462 | 354913.548 | 3147248.165 |  |  | DUDIWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 432 | 31851.704 | [12 empty] | Water tank | [5 empty] | 4.5502
80 |  | 7/9 | DA+3 | 371 |  |  |  |  | 232.435 |  | 803 | 401.5 | 201 | 193 | 394 | 206 | 191 | 397 | 355345.396 | 3147236.711 |  |  | DUDIWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 371 | 32222.704 | [12 empty] | Metal road | [5 empty] | 4.6032
81 |  | 7/10 | DA+0 | 385 |  |  |  |  | 234.171 |  | 756 | 378 | 178 | 175 | 353 | 181 | 181 | 362 | 355716.266 | 3147226.874 |  |  | DUDIWALI | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 385 | 32607.704 | [12 empty] | Cart track | [5 empty] | 4.6582
82 |  | 7/11 | DA+3 | 408.062 |  |  |  |  | 234.34 |  | 793.062 | 396.531 | 210 | 226 | 436 | 205 | 220 | 425 | 356101.131 | 3147216.666 |  |  | DOODIMU KLERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 408.062 | 33015.766 | [18 empty] | 4.7165
83 | AP-8 | 8/0 | DC1+0 | 372 |  | 4747.062 |  |  | 233.164 | 16° 13' 27"LT | 780.062 | 390.031 | 182 | 194 | 376 | 190 | 192 | 382 | 356509.049 | 3147205.847 |  |  | DOODIMUKLERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 372 | 33387.766 | [12 empty] | 11kV line & Cart track | [5 empty] | 4.7697
84 |  | 8/1 | DA-1.5 | 383 |  |  |  |  | 233.352 |  | 755 | 377.5 | 179 | 166 | 345 | 181 | 175 | 356 | 356868.865 | 3147300.275 |  |  | DOODIMUKLERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 383 | 33770.766 | [12 empty] | Metal road | [5 empty] | 4.8244
85 |  | 8/2 | DA+3 | 427 |  |  |  |  | 233.35 |  | 810 | 405 | 217 | 192 | 409 | 209 | 199 | 408 | 357239.32 | 3147397.495 |  |  | JAISAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 427 | 34197.766 | [18 empty] | 4.8854
86 |  | 8/3 | DA+6 | 402 |  |  |  |  | 234.77 |  | 829 | 414.5 | 236 | 211 | 447 | 229 | 208 | 437 | 357652.335 | 3147505.884 |  |  | JAISAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 402 | 34599.766 | [18 empty] | 4.9428
87 |  | 8/4 | DA+3 | 388 |  |  |  |  | 235.976 |  | 790 | 395 | 192 | 208 | 400 | 195 | 204 | 399 | 358041.168 | 3147607.927 |  |  | SADHERAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 388 | 34987.766 | [18 empty] | 4.9983
88 |  | 8/5 | DA+0 | 365 |  |  |  |  | 236.559 |  | 753 | 376.5 | 181 | 190 | 371 | 185 | 188 | 373 | 358416.459 | 3147706.416 |  |  | SADHERAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 365 | 35352.766 | [12 empty] | Cart track | [5 empty] | 5.0504
89 |  | 8/6 | DA+0 | 422 |  |  |  |  | 235.267 |  | 787 | 393.5 | 175 | 197 | 372 | 178 | 202 | 380 | 358769.504 | 3147799.067 |  |  | SADHERAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 422 | 35774.766 | [18 empty] | 5.1107
90 |  | 8/7 | DA+3 | 384 |  |  |  |  | 235.092 |  | 806 | 403 | 226 | 200 | 426 | 222 | 198 | 420 | 359177.683 | 3147906.187 |  |  | DHEERERAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 384 | 36158.766 | [12 empty] | Cart track & Fence | [5 empty] | 5.1655
91 |  | 8/8 | DA+0 | 380.388 |  |  |  |  | 236.644 |  | 764.388 | 382.194 | 184 | 210 | 394 | 187 | 204 | 391 | 359549.105 | 3148003.661 |  |  | DHEERERAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 380.388 | 36539.154 | [18 empty] | 5.2199
92 | AP-9 | 9/0 | DB1+0 | 329 |  | 3523.388 |  |  | 233.267 | 5° 18' 49"RT | 709.388 | 354.694 | 171 | 170 | 341 | 178 | 169 | 347 | 359917.034 | 3148100.218 |  |  | DHEERERAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 329 | 36868.154 | [12 empty] | 11kV line | [5 empty] | 5.2669
93 |  | 9/1 | DA+0 | 429 |  |  |  |  | 232.395 |  | 758 | 379 | 159 | 186 | 345 | 161 | 195 | 356 | 360241.625 | 3148153.903 |  |  | DHEERERAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 429 | 37297.154 | [12 empty] | Metal road & Fence | [5 empty] | 5.3282
94 |  | 9/2 | DA+6 | 411 |  |  |  |  | 232.225 |  | 840 | 420 | 243 | 241 | 484 | 235 | 231 | 466 | 360664.875 | 3148223.905 |  |  | DHEERERAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 411 | 37708.154 | [12 empty] | Fence | [5 empty] | 5.3869
95 |  | 9/3 | DA+0 | 394 |  |  |  |  | 231.281 |  | 805 | 402.5 | 171 | 184 | 355 | 181 | 188 | 369 | 361070.366 | 3148290.97 |  |  | DHEERERAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 394 | 38102.154 | [18 empty] | 5.4432
96 |  | 9/4 | DA+3 | 445.871 |  |  |  |  | 230.872 |  | 839.871 | 419.9355 | 211 | 119 | 330 | 207 | 151 | 358 | 361459.085 | 3148355.262 |  |  | DHEERERAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 445.871 | 38548.025 | [18 empty] | 5.5069
97 | AP-10 | 10/0 | DD60+25 | 200.429 |  | 2008.871 |  |  | 231.125 | 33° 23' 40"RT | 646.3 | 323.15 | 328 | 172 | 500 | 297 | 129 | 426 | 361898.98 | 3148428.017 |  |  | DHEERERAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 200.429 | 38748.454 | [12 empty] | 400 KV DC SURATGARAH - BIKANER OHTL (ADANI) TL | [5 empty] | 5.5355
98 | AP-11 | 11/0 | DD60+18 | 453 | 2 | 200.429 |  |  | 230.888 | 33° 22' 56"LT | 653.429 | 326.7145 | 29 | 334 | 363 | 72 | 301 | 373 | 362082.077 | 3148346.485 |  |  | DHEERERAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 453 | 39201.454 | [18 empty] | 5.6002
99 |  | 11/1 | DA-1.5 | 387 |  |  |  |  | 229.733 |  | 840 | 420 | 121 | 169 | 290 | 154 | 177 | 331 | 362529.021 | 3148420.309 |  |  | SHARAH BEECHHARWAS | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 387 | 39588.454 | [12 empty] | Cart track | [5 empty] | 5.6555
100 |  | 11/2 | DA+3 | 383 |  |  |  |  | 229.778 |  | 770 | 385 | 219 | 214 | 433 | 211 | 207 | 418 | 362910.847 | 3148483.378 |  |  | SHARAH BEECHHARWAS | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 383 | 39971.454 | [18 empty] | 5.7102
101 |  | 11/3 | DA+0 | 399 |  |  |  |  | 228.787 |  | 782 | 391 | 170 | 190 | 360 | 177 | 193 | 370 | 363288.727 | 3148545.794 |  |  | SHARAH BEECHHARWAS | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 399 | 40370.454 | [18 empty] | 5.7672
102 |  | 11/4 | DA+3 | 385 |  |  |  |  | 227.67 |  | 784 | 392 | 210 | 221 | 431 | 207 | 212 | 419 | 363682.393 | 3148610.818 |  |  | SHARAH BEECHHARWAS | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 385 | 40755.454 | [18 empty] | 5.8222
103 |  | 11/5 | DA-1.5 | 389 |  |  |  |  | 227.111 |  | 774 | 387 | 165 | 168 | 333 | 174 | 177 | 351 | 364062.246 | 3148673.56 |  |  | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 389 | 41144.454 | [18 empty] | 5.8778
104 |  | 11/6 | DA+3 | 403 |  |  |  |  | 227.448 |  | 792 | 396 | 221 | 203 | 424 | 213 | 203 | 416 | 364446.046 | 3148736.955 |  |  | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 403 | 41547.454 | [12 empty] | Cart track | [5 empty] | 5.9354
105 |  | 11/7 | DA+3 | 398 |  |  |  |  | 227.233 |  | 801 | 400.5 | 201 | 206 | 407 | 201 | 204 | 405 | 364843.658 | 3148802.63 |  |  | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 398 | 41945.454 | [18 empty] | 5.9922
106 |  | 11/8 | DA+3 | 402.053 |  |  |  |  | 225.969 |  | 800.053 | 400.0265 | 193 | 230 | 423 | 195 | 221 | 416 | 365236.338 | 3148867.491 |  |  | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 402.053 | 42347.507 | [18 empty] | 6.0496
107 | AP-12 | 12/0 | DC2+0 | 359 |  | 3599.053 |  |  | 223.598 | 24° 56' 43"RT | 761.053 | 380.5265 | 173 | 174 | 347 | 182 | 176 | 358 | 365633.016 | 3148933.013 |  |  | SHARAH BOOCHAWAS | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 359 | 42706.507 | [12 empty] | Fence & Cart track | [5 empty] | 6.1009
108 |  | 12/1 | DA+3 | 381 |  |  |  |  | 221.638 |  | 740 | 370 | 186 | 199 | 385 | 184 | 197 | 381 | 365978.848 | 3148836.676 |  |  | HANSHERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 381 | 43087.507 | [18 empty] | 6.1554
109 |  | 12/2 | DA-1.5 | 399 |  |  |  |  | 224.66 |  | 780 | 390 | 182 | 158 | 340 | 185 | 171 | 356 | 366345.874 | 3148734.434 |  |  | HANSHERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 399 | 43486.507 | [18 empty] | 6.2124
110 |  | 12/3 | DA+9 | 427 |  |  |  |  | 221.935 |  | 826 | 413 | 241 | 230 | 471 | 229 | 225 | 454 | 366730.239 | 3148627.363 |  |  | HANSHERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 427 | 43913.507 | [12 empty] | Fence & Cart track | [5 empty] | 6.2734
111 |  | 12/4 | DA+9 | 413 |  |  |  |  | 218.69 |  | 840 | 420 | 198 | 200 | 398 | 203 | 202 | 405 | 367141.578 | 3148512.778 |  |  | HANSHERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 413 | 44326.507 | [18 empty] | 6.3324
112 |  | 12/5 | DA+9 | 409.527 |  |  |  |  | 220.038 |  | 822.527 | 411.2635 | 214 | 233 | 447 | 212 | 225 | 437 | 367539.429 | 3148401.949 |  |  | HANSHERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 409.527 | 44736.034 | [12 empty] | 11kV line, Canel, Fence & Cart track | [5 empty] | 6.3909
113 | AP-13 | 13/0 | DC1+3 | 311 |  | 2388.527 |  |  | 220.704 | 20° 45' 52"RT | 720.527 | 360.2635 | 177 | 136 | 313 | 186 | 142 | 328 | 367933.936 | 3148292.053 |  |  | HANSHERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 311 | 45047.034 | [12 empty] | Fence | [5 empty] | 6.4353
114 |  | 13/1 | DA+6 | 458.7 |  |  |  |  | 220.611 |  | 769.7 | 384.85 | 175 | 247 | 422 | 170 | 242 | 412 | 368184.481 | 3148107.803 |  |  | HANSHERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 458.7 | 45505.734 | [12 empty] | 11kV line & fence | [5 empty] | 6.5008
115 | AP-14 | 14/0 | DC1+0 | 242.447 |  | 769.7 |  |  | 222.908 | 19° 15' 9"RT | 701.147 | 350.5735 | 213 | 109 | 322 | 219 | 116 | 335 | 368554.015 | 3147836.049 |  |  | HANSHERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 242.447 | 45748.181 | [12 empty] | NH-62, 33kV line & 11kV line | [5 empty] | 6.5355
116 | AP-15 | 15/0 | DC1+0 | 226.424 |  | 242.447 |  |  | 224.081 | 20° 44' 43"LT | 468.871 | 234.4355 | 134 | 50 | 184 | 127 | 85 | 212 | 368691.049 | 3147636.043 |  |  | HANSHERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 226.424 | 45974.605 | [12 empty] | Ex. 132 KV SC BIKANER - LUNKARANSAR OHTL TL | [5 empty] | 6.5678
117 | AP-16 | 16/0 | DB2+0 | 353 | 1 | 226.424 |  |  | 229.483 | 12° 18' 16"LT | 579.424 | 289.712 | 176 | 169 | 345 | 141 | 172 | 313 | 368876.892 | 3147506.697 |  |  | HANSHERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 353 | 46327.605 | [18 empty] | 6.6182
118 |  | 16/1 | DA+3 | 365 |  |  |  |  | 227.67 |  | 718 | 359 | 184 | 199 | 383 | 182 | 194 | 376 | 369202.943 | 3147371.42 |  |  | HANSHERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 365 | 46692.605 | [18 empty] | 6.6704
119 |  | 16/2 | DA+0 | 344 |  |  |  |  | 227.954 |  | 709 | 354.5 | 166 | 179 | 345 | 172 | 177 | 349 | 369540.078 | 3147231.545 |  |  | JAKHARWALA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 344 | 47036.605 | [18 empty] | 6.7195
120 |  | 16/3 | DA+0 | 363.585 |  |  |  |  | 226.848 |  | 707.585 | 353.7925 | 165 | 224 | 389 | 168 | 209 | 377 | 369857.816 | 3147099.717 |  |  | JAKHARWALA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 363.585 | 47400.19 | [12 empty] | Fence | [5 empty] | 6.7715
121 | AP-17 | 17/0 | DD60+0 | 244.245 | 1 | 1425.585 |  |  | 219.958 | 19° 7' 45"RT | 607.83 | 303.915 | 140 | 126 | 266 | 155 | 124 | 279 | 370193.644 | 3146960.384 |  |  | JAKHARWALA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 244.245 | 47644.435 | [12 empty] | Railway Crossing | [5 empty] | 6.8063
122 | AP-18 | 18/0 | DD60+0 | 432 |  | 244.245 |  |  | 219.546 | 26° 28' 8"LT | 676.245 | 338.1225 | 118 | 177 | 295 | 120 | 190 | 310 | 370376.113 | 3146798.025 |  |  | JAKHARWALA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 432 | 48076.435 | [12 empty] | Fence | [5 empty] | 6.8681
123 |  | 18/1 | DA+6 | 366 |  |  |  |  | 221.379 |  | 798 | 399 | 255 | 203 | 458 | 243 | 197 | 440 | 370793.014 | 3146684.808 |  |  | SURANA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 366 | 48442.435 | [12 empty] | Fence & Cart track | [5 empty] | 6.9203
124 |  | 18/2 | DA+3 | 424 |  |  |  |  | 221.09 |  | 790 | 395 | 164 | 186 | 350 | 170 | 195 | 365 | 371146.221 | 3146588.887 |  |  | SURANA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 424 | 48866.435 | [12 empty] | Fence & Cart track | [5 empty] | 6.9809
125 |  | 18/3 | DA+6 | 407 |  |  |  |  | 223.299 |  | 831 | 415.5 | 239 | 160 | 399 | 231 | 174 | 405 | 371555.401 | 3146477.767 |  |  | SURANA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 407 | 49273.435 | [12 empty] | Fence | [5 empty] | 7.0391
126 |  | 18/4 | DA+6 | 373 |  |  |  |  | 231.608 |  | 780 | 390 | 248 | 206 | 454 | 234 | 200 | 434 | 371948.175 | 3146371.101 |  |  | SURANA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 373 | 49646.435 | [12 empty] | 11kV line & Cart track | [5 empty] | 7.0923
127 |  | 18/5 | DA+0 | 353.456 |  |  |  |  | 234.197 |  | 726.456 | 363.228 | 167 | 180 | 347 | 174 | 179 | 353 | 372308.137 | 3146273.347 |  |  | SURANA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 353.456 | 49999.891 | [12 empty] | 33kV line & 11kV | [5 empty] | 7.1428
128 | AP-19 | 19/0 | DC2+0 | 380 |  | 2355.456 |  |  | 233.635 | 28° 29' 2"LT | 733.456 | 366.728 | 173 | 173 | 346 | 175 | 178 | 353 | 372649.239 | 3146180.714 |  |  | SURANA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 380 | 50379.891 | [12 empty] | Cart track | [5 empty] | 7.1971
129 |  | 19/1 | DA+3 | 449 |  |  |  |  | 233.804 |  | 829 | 414.5 | 208 | 198 | 406 | 203 | 207 | 410 | 373019.061 | 3146268.072 |  |  | SURANA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 449 | 50828.891 | [12 empty] | Cart track | [5 empty] | 7.2613
130 |  | 19/2 | DA+6 | 391 |  |  |  |  | 236.449 |  | 840 | 420 | 251 | 255 | 506 | 244 | 237 | 481 | 373456.035 | 3146371.293 |  |  | SURANA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 391 | 51219.891 | [12 empty] | Fencing | [5 empty] | 7.3171
131 |  | 19/3 | DA-1.5 | 397 |  |  |  |  | 233.006 |  | 788 | 394 | 137 | 121 | 258 | 155 | 145 | 300 | 373836.563 | 3146461.18 |  |  | KAKARICHCHHA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 397 | 51616.891 | [18 empty] | 7.3738
132 |  | 19/4 | DA+9 | 425 |  |  |  |  | 237.132 |  | 822 | 411 | 277 | 278 | 555 | 253 | 259 | 512 | 374222.93 | 3146552.446 |  |  | KAKARICHCHHA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 425 | 52041.891 | [12 empty] | Cart track | [5 empty] | 7.4346
133 |  | 19/5 | DA+3 | 409 |  |  |  |  | 229.926 |  | 834 | 417 | 147 | 205 | 352 | 168 | 206 | 374 | 374636.547 | 3146650.15 |  |  | KAKARICHCHHA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 409 | 52450.891 | [18 empty] | 7.493
134 |  | 19/6 | DA+3 | 381 |  |  |  |  | 229.822 |  | 790 | 395 | 204 | 146 | 350 | 205 | 160 | 365 | 375034.593 | 3146744.175 |  |  | KAKARICHCHHA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 381 | 52831.891 | [18 empty] | 7.5474
135 |  | 19/7 | DA+6 | 392.001 |  |  |  |  | 234.925 |  | 773.001 | 386.5005 | 236 | 205 | 441 | 222 | 202 | 424 | 375405.388 | 3146831.763 |  |  | KAKARICHCHHA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 392.001 | 53223.892 | [18 empty] | 7.6034
136 | AP-20 | 20/0 | DC1+6 | 420 |  | 3224.001 |  |  | 233.38 | 16° 21' 47"RT | 812.001 | 406.0005 | 188 | 216 | 404 | 191 | 215 | 406 | 375786.89 | 3146921.88 |  |  | KAKARICHCHHA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 420 | 53643.892 | [12 empty] | Cart track | [5 empty] | 7.6634
137 |  | 20/1 | DA+6 | 361 |  |  |  |  | 232.292 |  | 781 | 390.5 | 205 | 167 | 372 | 207 | 172 | 379 | 376206.286 | 3146899.369 |  |  | KALKAL MUKLERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 361 | 54004.892 | [18 empty] | 7.715
138 |  | 20/2 | DA+6 | 393 |  |  |  |  | 234.573 |  | 754 | 377 | 194 | 243 | 437 | 190 | 228 | 418 | 376566.768 | 3146880.021 |  |  | KALKAL MUKLERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 393 | 54397.892 | [18 empty] | 7.7711
139 |  | 20/3 | DA-3 | 384 |  |  |  |  | 235.185 |  | 777 | 388.5 | 151 | 227 | 378 | 166 | 216 | 382 | 376959.203 | 3146858.957 |  |  | KALKAL MUKLERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 384 | 54781.892 | [12 empty] | Cart track | [5 empty] | 7.826
140 |  | 20/4 | DA+0 | 345 |  |  |  |  | 225.963 |  | 729 | 364.5 | 157 | 156 | 313 | 169 | 161 | 330 | 377342.651 | 3146838.375 |  |  | KALKAL MUKLERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 345 | 55126.892 | [12 empty] | 11kV line | [5 empty] | 7.8753
141 |  | 20/5 | DA+0 | 396 |  |  |  |  | 228.692 |  | 741 | 370.5 | 190 | 142 | 332 | 185 | 161 | 346 | 377687.155 | 3146819.884 |  |  | KALKAL MUKLERA | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 396 | 55522.892 | [18 empty] | 7.9318
142 |  | 20/6 | DA+9 | 370 |  |  |  |  | 229.967 |  | 766 | 383 | 254 | 217 | 471 | 237 | 207 | 444 | 378082.586 | 3146798.66 |  |  | LUNKARANSAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 370 | 55892.892 | [18 empty] | 7.9847
143 |  | 20/7 | DA+0 | 443.474 |  |  |  |  | 233.54 |  | 813.474 | 406.737 | 154 | 172 | 326 | 164 | 189 | 353 | 378452.054 | 3146778.829 |  |  | LUNKARANSAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 443.474 | 56336.366 | [12 empty] | 11kV line & Metal road | [5 empty] | 8.0481
144 | AP-20A | 20A/0 | DD45+9 | 226.807 |  | 3112.474 |  |  | 234.82 | 40° 06' 27"RT | 670.281 | 335.1405 | 272 | 156 | 428 | 257 | 132 | 389 | 378894.89 | 3146755.06 |  |  | LUNKARANSAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 226.807 | 56563.173 | [12 empty] | 220 KV S/C LINE SUR-BIK TL | [5 empty] | 8.0805
145 | AP-21 | 21/0 | DC2+3 | 275.25 |  | 226.807 |  |  | 237.18 | 28° 54' 20"LT | 502.057 | 251.0285 | 71 | 146 | 217 | 95 | 142 | 237 | 379060.28 | 3146599.86 |  |  | LUNKARANSAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 275.25 | 56838.423 | [18 empty] | 8.1198
146 | AP-22 | 22/0 | DD60+6 | 198.077 |  | 275.25 |  |  | 233.29 | 21° 33' 56"RT | 473.327 | 236.6635 | 131 | 49 | 180 | 135 | 79 | 214 | 379327.03 | 3146531.99 |  |  | LUNKARANSAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 198.077 | 57036.5 | [12 empty] | 400KV S/C SURATGARH THERMAL PLANT-BIKANER OHTL | [5 empty] | 8.1481
147 | AP-23 | 23/0 | DD60+9 | 327.999 |  | 198.077 |  |  | 233.93 | 26° 10' 47"LT | 526.076 | 263.038 | 150 | 223 | 373 | 119 | 202 | 321 | 379489.02 | 3146418 |  |  | LUNKARANSAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 327.999 | 57364.499 | [18 empty] | 8.1949
148 |  | 23/1 | DA-1.5 | 318 |  |  |  |  | 235.823 |  | 645.999 | 322.9995 | 106 | 132 | 238 | 127 | 142 | 269 | 379813.023 | 3146366.951 |  |  | LUNKARANSAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 318 | 57682.499 | [18 empty] | 8.2404
149 |  | 23/2 | DA+3 | 379 |  |  |  |  | 235.23 |  | 697 | 348.5 | 186 | 234 | 420 | 177 | 218 | 395 | 380127.148 | 3146317.459 |  |  | LUNKARANSAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 379 | 58061.499 | [18 empty] | 8.2945
150 |  | 23/3 | DA+0 | 382 |  |  |  |  | 230.744 |  | 761 | 380.5 | 146 | 194 | 340 | 162 | 193 | 355 | 380501.529 | 3146258.473 |  |  | DHANI BHOPALARAM | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 382 | 58443.499 | [12 empty] | Water Tank | [5 empty] | 8.3491
151 |  | 23/4 | DA+0 | 353.645 |  |  |  |  | 230.33 |  | 735.645 | 367.8225 | 189 | 171 | 360 | 190 | 173 | 363 | 380878.874 | 3146199.02 |  |  | DHANI BHOPALARAM | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 353.645 | 58797.144 | [18 empty] | 8.3996
152 | AP-24 | 24/0 | DC2+0 | 247.381 |  | 1760.644 |  |  | 231.35 | 25° 14' 38"RT | 601.026 | 300.513 | 184 | 88 | 272 | 182 | 107 | 289 | 381228.21 | 3146143.98 |  |  | UCHHRANGDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 247.381 | 59044.525 | [12 empty] | NH 754A-AMRITSAR TO JAMNAGAR EXPRESSWAY & Fencing & 11KV LINE | [5 empty] | 8.4349
153 | AP-25 | 25/0 | DC2+0 | 258 |  | 247.381 |  |  | 234.84 | 28° 25' 33"LT | 505.381 | 252.6905 | 160 | 54 | 214 | 141 | 78 | 219 | 381432.82 | 3146004.94 |  |  | UCHHRANGDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 258 | 59302.525 | [18 empty] | 8.4718
154 |  | 25/1 | DA+9 | 452.894 |  |  |  |  | 234.828 |  | 710.894 | 355.447 | 204 | 100 | 304 | 180 | 141 | 321 | 381689.512 | 3145978.995 |  |  | UCHHRANGDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 452.894 | 59755.419 | [12 empty] | HUT | [5 empty] | 8.5365
155 | AP-26 | 26/0 | DD60+35 | 217.368 | 2 | 710.894 |  |  | 233.63 | 27° 53' 8"RT | 670.262 | 335.131 | 355 | 116 | 471 | 315 | 112 | 427 | 382140.11 | 3145933.45 |  |  | UCHHRANGDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 217.368 | 59972.787 | [12 empty] | 765KV D/C BIKANER -MOGA OHTL (Earthwire removal required) | [5 empty] | 8.5675
156 | AP-27 | 27/0 | DD60+35 | 368 | 2 | 217.368 |  |  | 233.11 | 46° 27' 18"LT | 585.368 | 292.684 | 102 | 339 | 441 | 106 | 285 | 391 | 382321.04 | 3145812.98 |  |  | UCHHRANGDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 368 | 60340.787 | [12 empty] | Water tank | [5 empty] | 8.6201
157 |  | 27/1 | DB1+9 | 397 |  | 368 |  |  | 235.37 |  | 765 | 382.5 | 31 | 260 | 291 | 84 | 238 | 322 | 382679.898 | 3145894.497 |  |  | UCHHRANGDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 397 | 60737.787 | [12 empty] | 11kV line | [5 empty] | 8.6768
158 |  | 27/2 | DA-1.5 | 332 |  |  |  |  | 235.004 |  | 729 | 364.5 | 138 | 194 | 332 | 160 | 185 | 345 | 383067.035 | 3145982.437 |  |  | UCHHRANGDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 332 | 61069.787 | [18 empty] | 8.7243
159 |  | 27/3 | DA-3 | 338.643 |  |  |  |  | 232.261 |  | 670.643 | 335.3215 | 138 | 153 | 291 | 148 | 159 | 307 | 383390.787 | 3146055.979 |  |  | UCHHRANGDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 338.643 | 61408.43 | [12 empty] | Water tank | [5 empty] | 8.7726
160 | AP-28 | 28/0 | DB2+0 | 421 |  | 1067.643 |  |  | 231.759 | 10° 12' 18"LT | 759.643 | 379.8215 | 186 | 169 | 355 | 180 | 182 | 362 | 383721.018 | 3146130.993 |  |  | UCHHRANGDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 421 | 61829.43 | [12 empty] | SH 6A road, 33kV line, 11kV line, Fencing & Water tank | [5 empty] | 8.8328
161 |  | 28/1 | DA+6 | 400 |  |  |  |  | 233.991 |  | 821 | 410.5 | 253 | 211 | 464 | 240 | 208 | 448 | 384108.542 | 3146295.51 |  |  | UCHHRANGDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 400 | 62229.43 | [18 empty] | 8.8899
162 |  | 28/2 | DA+3 | 396 |  |  |  |  | 234.972 |  | 796 | 398 | 189 | 205 | 394 | 193 | 203 | 396 | 384476.736 | 3146451.822 |  |  | UCHHRANGDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 396 | 62625.43 | [12 empty] | Fencing | [5 empty] | 8.9465
163 |  | 28/3 | DA+0 | 378 |  |  |  |  | 236.754 |  | 774 | 387 | 192 | 204 | 396 | 194 | 200 | 394 | 384841.248 | 3146606.57 |  |  | UCHHRANGDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 378 | 63003.43 | [12 empty] | 11kV line & Fencing | [5 empty] | 9.0005
164 |  | 28/4 | DA+0 | 386 |  |  |  |  | 234.19 |  | 764 | 382 | 175 | 208 | 383 | 180 | 204 | 384 | 385189.192 | 3146754.284 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 386 | 63389.43 | [12 empty] | Water tank, Hut & Cart track | [5 empty] | 9.0556
165 |  | 28/5 | DA+0 | 388 |  |  |  |  | 231.46 |  | 774 | 387 | 178 | 197 | 375 | 183 | 197 | 380 | 385544.499 | 3146905.124 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 388 | 63777.43 | [12 empty] | Fencing | [5 empty] | 9.1111
166 |  | 28/6 | DA+0 | 393 |  |  |  |  | 230.935 |  | 781 | 390.5 | 191 | 162 | 353 | 193 | 173 | 366 | 385901.647 | 3147056.746 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 393 | 64170.43 | [12 empty] | Fencing | [5 empty] | 9.1672
167 |  | 28/7 | DA+6 | 417.124 |  |  |  |  | 231.258 |  | 810.124 | 405.062 | 231 | 241 | 472 | 221 | 231 | 452 | 386263.398 | 3147210.321 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 417.124 | 64587.554 | [18 empty] | 9.2268
168 | AP-29 | 29/0 | DB2+0 | 424 |  | 3179.124 |  |  | 230.99 | 7° 39' 26"RT | 841.124 | 420.562 | 177 | 170 | 347 | 187 | 183 | 370 | 386647.354 | 3147373.324 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 424 | 65011.554 | [12 empty] | CART TRACK | [5 empty] | 9.2874
169 |  | 29/1 | DA+6 | 416 |  |  |  |  | 233.672 |  | 840 | 420 | 255 | 237 | 492 | 243 | 229 | 472 | 387056.237 | 3147485.531 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 416 | 65427.554 | [18 empty] | 9.3468
170 |  | 29/2 | DA+3 | 424 |  |  |  |  | 231.05 |  | 840 | 420 | 180 | 199 | 379 | 189 | 203 | 392 | 387457.405 | 3147595.622 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 424 | 65851.554 | [12 empty] | CART TRACK, HOUSE | [5 empty] | 9.4074
171 |  | 29/3 | DA+6 | 412 |  |  |  |  | 230.838 |  | 836 | 418 | 226 | 217 | 443 | 222 | 214 | 436 | 387866.289 | 3147707.829 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 412 | 66263.554 | [18 empty] | 9.4662
172 |  | 29/4 | DA+0 | 409 |  |  |  |  | 234.768 |  | 821 | 410.5 | 196 | 195 | 391 | 199 | 198 | 397 | 388263.6 | 3147816.861 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 409 | 66672.554 | [12 empty] | HUT | [5 empty] | 9.5247
173 |  | 29/5 | DA+3 | 396 |  |  |  |  | 233.669 |  | 805 | 402.5 | 215 | 230 | 445 | 212 | 221 | 433 | 388658.018 | 3147925.099 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 396 | 67068.554 | [12 empty] | CART TRACK | [5 empty] | 9.5812
174 |  | 29/6 | DA+0 | 419 |  |  |  |  | 230.663 |  | 815 | 407.5 | 167 | 180 | 347 | 176 | 189 | 365 | 389039.899 | 3148029.897 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 419 | 67487.554 | [12 empty] | HUT | [5 empty] | 9.6411
175 |  | 29/7 | DA+6 | 421 |  |  |  |  | 230.762 |  | 840 | 420 | 240 | 231 | 471 | 232 | 226 | 458 | 389443.961 | 3148140.781 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 421 | 67908.554 | [12 empty] | CART TRACK, WATER TANK | [5 empty] | 9.7012
176 |  | 29/8 | DA+0 | 415 |  |  |  |  | 232.605 |  | 836 | 418 | 190 | 213 | 403 | 197 | 212 | 409 | 389849.951 | 3148252.195 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 415 | 68323.554 | [12 empty] | CART TRACK | [5 empty] | 9.7605
177 |  | 29/9 | DA+0 | 388 |  |  |  |  | 231.614 |  | 803 | 401.5 | 203 | 196 | 399 | 205 | 196 | 401 | 390250.155 | 3148362.021 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 388 | 68711.554 | [18 empty] | 9.8159
178 |  | 29/10 | DA+0 | 393 |  |  |  |  | 231.203 |  | 781 | 390.5 | 192 | 190 | 382 | 193 | 192 | 385 | 390624.321 | 3148464.701 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 393 | 69104.554 | [18 empty] | 9.8721
179 |  | 29/11 | DA+0 | 371 |  |  |  |  | 232.523 |  | 764 | 382 | 204 | 189 | 393 | 202 | 188 | 390 | 391003.31 | 3148568.705 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 371 | 69475.554 | [12 empty] | CART TRACK, WATER TANK | [5 empty] | 9.9251
180 |  | 29/12 | DB1+0 | 386 |  | 4888 |  |  | 231.96 |  | 757 | 378.5 | 183 | 197 | 380 | 184 | 196 | 380 | 391361.083 | 3148666.887 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 386 | 69861.554 | [18 empty] | 9.9802
181 |  | 29/13 | DA+0 | 390 |  |  |  |  | 231.324 |  | 776 | 388 | 190 | 200 | 390 | 191 | 199 | 390 | 391733.321 | 3148769.038 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 390 | 70251.554 | [12 empty] | WATER TANK, HUT | [5 empty] | 10.0359
182 |  | 29/14 | DA+0 | 385 |  |  |  |  | 230.414 |  | 775 | 387.5 | 190 | 179 | 369 | 192 | 183 | 375 | 392109.416 | 3148872.248 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 385 | 70636.554 | [18 empty] | 10.0909
183 |  | 29/15 | DA+0 | 343 |  |  |  |  | 232.954 |  | 728 | 364 | 207 | 170 | 377 | 203 | 171 | 374 | 392480.69 | 3148974.134 |  |  | KALOO | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 343 | 70979.554 | [18 empty] | 10.1399
184 |  | 29/16 | DA+0 | 385 |  |  |  |  | 233.188 |  | 728 | 364 | 173 | 182 | 355 | 173 | 186 | 359 | 392811.461 | 3149064.906 |  |  | GARABDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 385 | 71364.554 | [18 empty] | 10.1949
185 |  | 29/17 | DA+0 | 445 |  |  |  |  | 235.116 |  | 830 | 415 | 203 | 236 | 439 | 200 | 232 | 432 | 393182.734 | 3149166.792 |  |  | GARABDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 445 | 71809.554 | [12 empty] | CART TRACK, 11KV LINE | [5 empty] | 10.2585
186 |  | 29/18 | DA+3 | 395 |  |  |  |  | 229.412 |  | 840 | 420 | 210 | 190 | 400 | 214 | 193 | 407 | 393611.869 | 3149284.557 |  |  | GARABDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 395 | 72204.554 | [18 empty] | 10.3149
187 |  | 29/19 | DA+3 | 416 |  |  |  |  | 230.786 |  | 811 | 405.5 | 205 | 230 | 435 | 203 | 224 | 427 | 393992.786 | 3149389.09 |  |  | GARABDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 416 | 72620.554 | [12 empty] | CART TRACK, 11KV LINE, WATER TANK | [5 empty] | 10.3744
188 |  | 29/20 | DA+0 | 411 |  |  |  |  | 229.564 |  | 827 | 413.5 | 187 | 188 | 375 | 194 | 194 | 388 | 394393.954 | 3149499.181 |  |  | GARABDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 411 | 73031.554 | [18 empty] | 10.4331
189 |  | 29/21 | DA+3 | 429 |  |  |  |  | 229.901 |  | 840 | 420 | 223 | 211 | 434 | 218 | 213 | 431 | 394790.301 | 3149607.948 |  |  | RAJPURA HUDAAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 429 | 73460.554 | [18 empty] | 10.4944
190 |  | 29/22 | DA+3 | 392.643 |  |  |  |  | 230.601 |  | 821.643 | 410.8215 | 218 | 213 | 431 | 218 | 208 | 426 | 395204.006 | 3149721.479 |  |  | RAJPURA HUDAAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 392.643 | 73853.197 | [18 empty] | 10.5505
191 | AP-30 | 30/0 | DB2+0 | 400.999 |  | 4377.643 |  |  | 230.64 | 9° 18' 50"RT | 793.642 | 396.821 | 181 | 187 | 368 | 186 | 191 | 377 | 395582.65 | 3149825.388 |  |  | RAJPURA HUDAAN | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 400.999 | 74254.196 | [18 empty] | 10.6077
192 |  | 30/1 | DA+3 | 437 |  |  |  |  | 230.441 |  | 837.999 | 418.9995 | 215 | 204 | 419 | 211 | 208 | 419 | 395981.429 | 3149867.524 |  |  | GARABDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 437 | 74691.196 | [12 empty] | CART TRACK, WELL, WATER TANK, HUT, PUMP HOUSE | [5 empty] | 10.6702
193 |  | 30/2 | DA+6 | 403 |  |  |  |  | 230.709 |  | 840 | 420 | 234 | 223 | 457 | 230 | 217 | 447 | 396416.01 | 3149913.444 |  |  | GARABDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 403 | 75094.196 | [18 empty] | 10.7277
194 |  | 30/3 | DA+0 | 412 |  |  |  |  | 232.563 |  | 815 | 407.5 | 181 | 196 | 377 | 187 | 199 | 386 | 396816.779 | 3149955.791 |  |  | GARABDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 412 | 75506.196 | [18 empty] | 10.7866
195 |  | 30/4 | DA+3 | 424 |  |  |  |  | 231.627 |  | 836 | 418 | 217 | 210 | 427 | 214 | 211 | 425 | 397226.498 | 3149999.083 |  |  | GARABDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 424 | 75930.196 | [18 empty] | 10.8472
196 |  | 30/5 | DA+3 | 416 |  |  |  |  | 232.214 |  | 840 | 420 | 215 | 222 | 437 | 215 | 218 | 433 | 397648.151 | 3150043.637 |  |  | GARABDESAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 416 | 76346.196 | [18 empty] | 10.9066
197 |  | 30/6 | DA+0 | 410 |  |  |  |  | 232.479 |  | 826 | 413 | 195 | 192 | 387 | 199 | 196 | 395 | 398061.848 | 3150087.349 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 410 | 76756.196 | [12 empty] | CART TRACK, WATER TANK | [5 empty] | 10.9652
198 |  | 30/7 | DA+3 | 415 |  |  |  |  | 232.248 |  | 825 | 412.5 | 219 | 214 | 433 | 216 | 212 | 428 | 398469.578 | 3150130.432 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 415 | 77171.196 | [18 empty] | 11.0245
199 |  | 30/8 | DA+3 | 412 |  |  |  |  | 231.052 |  | 827 | 413.5 | 202 | 221 | 423 | 204 | 217 | 421 | 398882.28 | 3150174.039 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 412 | 77583.196 | [18 empty] | 11.0833
200 |  | 30/9 | DB1+0 | 409 |  | 3729.999 |  |  | 231.153 |  | 821 | 410.5 | 192 | 195 | 387 | 196 | 198 | 394 | 399292 | 3150217.332 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 409 | 77992.196 | [12 empty] | CART TRACK, WATER TANK | [5 empty] | 11.1417
201 |  | 30/10 | DA+3 | 426 |  |  |  |  | 230.133 |  | 835 | 417.5 | 215 | 208 | 423 | 212 | 210 | 422 | 399698.735 | 3150260.309 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 426 | 78418.196 | [12 empty] | WATER TANK | [5 empty] | 11.2026
202 |  | 30/11 | DA+0 | 414 |  |  |  |  | 234.25 |  | 840 | 420 | 219 | 180 | 399 | 218 | 188 | 406 | 400122.377 | 3150305.072 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 414 | 78832.196 | [12 empty] | WATER TANK | [5 empty] | 11.2617
203 |  | 30/12 | DA+6 | 415 |  |  |  |  | 233.698 |  | 829 | 414.5 | 235 | 210 | 445 | 227 | 210 | 437 | 400534.085 | 3150348.575 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 415 | 79247.196 | [12 empty] | CART TRACK | [5 empty] | 11.321
204 |  | 30/13 | DA+6 | 378 |  |  |  |  | 233.254 |  | 793 | 396.5 | 206 | 199 | 405 | 207 | 196 | 403 | 400946.787 | 3150392.183 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 378 | 79625.196 | [18 empty] | 11.375
205 |  | 30/14 | DA+3 | 417 |  |  |  |  | 234.463 |  | 795 | 397.5 | 179 | 200 | 379 | 183 | 203 | 386 | 401322.695 | 3150431.903 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 417 | 80042.196 | [12 empty] | WATER TANK | [5 empty] | 11.4346
206 |  | 30/15 | DA+3 | 346 |  |  |  |  | 236.174 |  | 763 | 381.5 | 217 | 150 | 367 | 215 | 157 | 372 | 401737.386 | 3150475.72 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 346 | 80388.196 | [12 empty] | CART TRACK | [5 empty] | 11.484
207 |  | 30/16 | DA+6 | 412 |  |  |  |  | 236.936 |  | 758 | 379 | 196 | 219 | 415 | 189 | 215 | 404 | 402081.471 | 3150512.078 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 412 | 80800.196 | [12 empty] | CART TRACK | [5 empty] | 11.5429
208 | TP Tower | 30/17 | DC2+0 | 428 |  |  |  |  | 240.491 |  | 840 | 420 | 194 | 238 | 432 | 198 | 231 | 429 | 402491.19 | 3150555.37 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 428 | 81228.196 | [12 empty] | CART TRACK | [5 empty] | 11.604
209 |  | 30/18 | DA+0 | 400.73 |  |  |  |  | 235.746 |  | 828.73 | 414.365 | 191 | 209 | 400 | 198 | 207 | 405 | 402916.82 | 3150600.344 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 400.73 | 81628.926 | [18 empty] | 11.6613
210 | AP-31 | 31/0 | DB2+0 | 413.999 |  | 4045.73 |  |  | 234.162 | 7° 5' 9"LT | 814.729 | 407.3645 | 192 | 200 | 392 | 195 | 202 | 397 | 403315.332 | 3150642.452 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 413.999 | 82042.925 | [12 empty] | WATER TANK | [5 empty] | 11.7204
211 |  | 31/1 | DA+3 | 424 |  |  |  |  | 232.75 |  | 837.999 | 418.9995 | 215 | 210 | 425 | 213 | 211 | 424 | 403718.529 | 3150736.408 |  |  | CHHATASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 424 | 82466.925 | [18 empty] | 11.781
212 |  | 31/2 | DA+3 | 411 |  |  |  |  | 233.24 |  | 835 | 417.5 | 215 | 223 | 438 | 214 | 219 | 433 | 404131.465 | 3150832.633 |  |  | KAGASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 411 | 82877.925 | [12 empty] | METAL ROAD, WATER TANK | [5 empty] | 11.8397
213 |  | 31/3 | DA-3 | 427 |  |  |  |  | 235.716 |  | 838 | 419 | 188 | 210 | 398 | 194 | 211 | 405 | 404531.741 | 3150925.908 |  |  | KAGASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 427 | 83304.925 | [12 empty] | CART TRACK, 11KV LINE | [5 empty] | 11.9007
214 |  | 31/4 | DA+0 | 413 |  |  |  |  | 233.638 |  | 840 | 420 | 218 | 175 | 393 | 217 | 184 | 401 | 404947.599 | 3151022.815 |  |  | KAGASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 413 | 83717.925 | [12 empty] | CART TRACK, 11KV LINE | [5 empty] | 11.9597
215 |  | 31/5 | DA+6 | 427 |  |  |  |  | 234.099 |  | 840 | 420 | 239 | 220 | 459 | 230 | 219 | 449 | 405349.823 | 3151116.544 |  |  | KAGASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 427 | 84144.925 | [12 empty] | CART TRACK | [5 empty] | 12.0207
216 |  | 31/6 | DA+6 | 408 |  |  |  |  | 232.715 |  | 835 | 417.5 | 207 | 224 | 431 | 210 | 219 | 429 | 405765.681 | 3151213.45 |  |  | KAGASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 408 | 84552.925 | [12 empty] | CART TRACK | [5 empty] | 12.079
217 |  | 31/7 | DA+0 | 432 |  |  |  |  | 234.708 |  | 840 | 420 | 184 | 192 | 376 | 190 | 200 | 390 | 406163.036 | 3151306.044 |  |  | KAGASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 432 | 84984.925 | [12 empty] | WATER TANK | [5 empty] | 12.1407
218 |  | 31/8 | DA+6 | 408 |  |  |  |  | 233.82 |  | 840 | 420 | 240 | 243 | 483 | 234 | 233 | 467 | 406583.763 | 3151404.085 |  |  | KAGASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 408 | 85392.925 | [12 empty] | WATER TANK | [5 empty] | 12.199
219 |  | 31/9 | DB1+0 | 409 |  | 3763.999 |  |  | 231.952 |  | 817 | 408.5 | 165 | 169 | 334 | 177 | 180 | 357 | 406981.118 | 3151496.68 |  |  | KAGASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 409 | 85801.925 | [18 empty] | 12.2574
220 |  | 31/10 | DA+6 | 415 |  |  |  |  | 232.988 |  | 824 | 412 | 241 | 190 | 431 | 230 | 196 | 426 | 407379.446 | 3151589.501 |  |  | KAGASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 415 | 86216.925 | [18 empty] | 12.3167
221 |  | 31/11 | DA+6 | 346 |  |  |  |  | 236.47 |  | 761 | 380.5 | 226 | 169 | 395 | 221 | 170 | 391 | 407783.617 | 3151683.684 |  |  | KAGASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 346 | 86562.925 | [12 empty] | WATER TANK | [5 empty] | 12.3661
222 |  | 31/12 | DA+6 | 342 |  |  |  |  | 237.157 |  | 688 | 344 | 177 | 200 | 377 | 176 | 191 | 367 | 408120.589 | 3151762.207 |  |  | KAGASAR | LUNKARANSAR | BIKANER |  | 0
[7 empty] | 342 | 86904.925 | [18 empty] | 12.415
223 |  | 31/13 | DA+0 | 409 |  |  |  |  | 238.532 |  | 751 | 375.5 | 143 | 167 | 310 | 152 | 179 | 331 | 408453.665 | 3151839.823 |  |  | KANWALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 409 | 87313.925 | [12 empty] | WATER TANK | [5 empty] | 12.4734
224 |  | 31/14 | DA+3 | 391 |  |  |  |  | 242.792 |  | 800 | 400 | 242 | 167 | 409 | 231 | 176 | 407 | 408851.993 | 3151932.645 |  |  | KANWALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 391 | 87704.925 | [12 empty] | CART TRACK | [5 empty] | 12.5293
225 |  | 31/15 | DA+9 | 437 |  |  |  |  | 242.119 |  | 828 | 414 | 225 | 223 | 448 | 216 | 222 | 438 | 409232.791 | 3152021.381 |  |  | KANWALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 437 | 88141.925 | [12 empty] | CART TRACK | [5 empty] | 12.5917
226 |  | 31/16 | DA+6 | 373 |  |  |  |  | 244.275 |  | 810 | 405 | 215 | 136 | 351 | 216 | 152 | 368 | 409658.388 | 3152120.557 |  |  | KANWALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 373 | 88514.925 | [18 empty] | 12.645
227 |  | 31/17 | DA+9 | 463 |  |  |  |  | 250.161 |  | 836 | 418 | 237 | 252 | 489 | 222 | 247 | 469 | 410021.656 | 3152205.208 |  |  | KANWALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 463 | 88977.925 | [18 empty] | 12.7111
228 |  | 31/18 | DB1+9 | 431 |  | 3585 |  |  | 245.74 |  | 894 | 447 | 212 | 245 | 457 | 218 | 237 | 455 | 410472.575 | 3152310.284 |  |  | DHEERASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 431 | 89408.925 | [18 empty] | 12.7727
229 |  | 31/19 | DA+3 | 409 |  |  |  |  | 245.688 |  | 840 | 420 | 187 | 246 | 433 | 196 | 234 | 430 | 410892.329 | 3152408.098 |  |  | DHEERASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 409 | 89817.925 | [18 empty] | 12.8311
230 |  | 31/20 | DA-1.5 | 424 |  |  |  |  | 242.115 |  | 833 | 416.5 | 164 | 196 | 360 | 176 | 201 | 377 | 411290.657 | 3152500.919 |  |  | DHEERASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 424 | 90241.925 | [12 empty] | HUT | [5 empty] | 12.8917
231 |  | 31/21 | DA+3 | 395 |  |  |  |  | 241.022 |  | 819 | 409.5 | 229 | 147 | 376 | 225 | 162 | 387 | 411703.593 | 3152597.145 |  |  | DHEERASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 395 | 90636.925 | [18 empty] | 12.9481
232 |  | 31/22 | DA+6 | 419 |  |  |  |  | 247.768 |  | 814 | 407 | 249 | 213 | 462 | 234 | 213 | 447 | 412088.287 | 3152686.789 |  |  | DHEERASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 419 | 91055.925 | [12 empty] | CART TRACK, 11KV LINE | [5 empty] | 13.008
233 |  | 31/23 | DA+6 | 392 |  |  |  |  | 247.089 |  | 811 | 405.5 | 206 | 205 | 411 | 208 | 203 | 411 | 412496.354 | 3152781.88 |  |  | DHEERASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 392 | 91447.925 | [12 empty] | 11KV LINE | [5 empty] | 13.064
234 |  | 31/24 | DA+9 | 408 |  |  |  |  | 242.388 |  | 800 | 400 | 187 | 287 | 474 | 190 | 263 | 453 | 412878.125 | 3152870.843 |  |  | DHEERASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 408 | 91855.925 | [12 empty] | 11KV LINE, WATER TANK | [5 empty] | 13.1223
235 |  | 31/25 | DA-3 | 432 |  |  |  |  | 238.107 |  | 840 | 420 | 122 | 196 | 318 | 146 | 203 | 349 | 413275.479 | 3152963.437 |  |  | DHEERASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 432 | 92287.925 | [12 empty] | 11KV LINE, BORE WELL | [5 empty] | 13.184
236 |  | 31/26 | DA+3 | 383.001 |  |  |  |  | 236.301 |  | 815.001 | 407.5005 | 237 | 201 | 438 | 231 | 199 | 430 | 413696.207 | 3153061.478 |  |  | MALSISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 383.001 | 92670.926 | [12 empty] | WATER TANK, CART TRACK | [5 empty] | 13.2387
237 |  | 31/27 | DA+3 | 398.944 |  |  |  |  | 234.596 |  | 781.945 | 390.9725 | 183 | 152 | 335 | 186 | 166 | 352 | 414069.215 | 3153148.399 |  |  | MALSISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 398.944 | 93069.87 | [12 empty] | HUT, 11KV LINE | [5 empty] | 13.2957
238 | AP-32 | 32/0 | DB2+3 | 372 |  | 4091.945 |  |  | 246.826 | 8° 3' 32"LT | 770.944 | 385.472 | 264 | 194 | 458 | 245 | 192 | 437 | 414457.749 | 3153238.938 |  |  | MALSISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 372 | 93441.87 | [18 empty] | 13.3488
239 |  | 32/1 | DA+9 | 385 |  |  |  |  | 239.488 |  | 757 | 378.5 | 178 | 256 | 434 | 181 | 236 | 417 | 414804.629 | 3153373.319 |  |  | MALSISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 385 | 93826.87 | [12 empty] | BORE, HUT, 11KV | [5 empty] | 13.4038
240 |  | 32/2 | DA+3 | 407 |  |  |  |  | 234.251 |  | 792 | 396 | 130 | 127 | 257 | 150 | 152 | 302 | 415163.631 | 3153512.397 |  |  | KEEKASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 407 | 94233.87 | [12 empty] | 11KV | [5 empty] | 13.462
241 |  | 32/3 | DA+9 | 412 |  |  |  |  | 242.819 |  | 819 | 409.5 | 281 | 243 | 524 | 257 | 232 | 489 | 415543.148 | 3153659.421 |  |  | KEEKASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 412 | 94645.87 | [12 empty] | 11KV, 33KV, CT | [5 empty] | 13.5208
242 |  | 32/4 | DA+6 | 400 |  |  |  |  | 238.758 |  | 812 | 406 | 169 | 254 | 423 | 181 | 238 | 419 | 415927.326 | 3153808.252 |  |  | KEEKASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 400 | 95045.87 | [18 empty] | 13.578
243 |  | 32/5 | DA+0 | 419 |  |  |  |  | 234.734 |  | 819 | 409.5 | 146 | 174 | 320 | 164 | 186 | 350 | 416300.316 | 3153952.748 |  |  | SONPALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 419 | 95464.87 | [12 empty] | WATER TANK | [5 empty] | 13.6378
244 |  | 32/6 | DA+3 | 404 |  |  |  |  | 238.747 |  | 823 | 411.5 | 246 | 204 | 450 | 235 | 204 | 439 | 416691.022 | 3154104.107 |  |  | SONPALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 404 | 95868.87 | [12 empty] | PH, BORE, 11KV LINE, 11KV TF | [5 empty] | 13.6956
245 |  | 32/7 | DA+6 | 436 |  |  |  |  | 235.357 |  | 840 | 420 | 200 | 222 | 422 | 201 | 221 | 422 | 417067.741 | 3154250.048 |  |  | SONPALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 436 | 96304.87 | [12 empty] | 11KV, METAL ROAD, WATER TANK | [5 empty] | 13.7578
246 |  | 32/8 | DA+6 | 374 |  |  |  |  | 234.683 |  | 810 | 405 | 215 | 143 | 358 | 217 | 157 | 374 | 417474.299 | 3154407.549 |  |  | SONPALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 374 | 96678.87 | [18 empty] | 13.8113
247 |  | 32/9 | DA+9 | 384 |  |  |  |  | 239.36 |  | 758 | 379 | 231 | 221 | 452 | 218 | 213 | 431 | 417823.044 | 3154542.653 |  |  | SONPALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 384 | 97062.87 | [12 empty] | CT, 11KV, WATER TANK | [5 empty] | 13.8661
248 |  | 32/10 | DA+9 | 360.177 |  |  |  |  | 234.144 |  | 744.177 | 372.0885 | 163 | 173 | 336 | 173 | 176 | 349 | 418181.114 | 3154681.369 |  |  | SONPALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 360.177 | 97423.047 | [12 empty] | 11KV, METAL ROAD | [5 empty] | 13.9176
249 | AP-33 | 33/0 | DB2+3 | 358.001 |  | 4353.177 |  |  | 241.337 | 10° 40' 8"RT | 718.178 | 359.089 | 188 | 171 | 359 | 185 | 174 | 359 | 418516.969 | 3154811.479 |  |  | SONPALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 358.001 | 97781.048 | [12 empty] | 11KV, 33KV | [5 empty] | 13.9687
250 |  | 33/1 | DA+9 | 452 |  |  |  |  | 236.74 |  | 810.001 | 405.0005 | 187 | 246 | 433 | 185 | 241 | 426 | 418868.967 | 3154876.766 |  |  | SONPALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 452 | 98233.048 | [12 empty] | CT, 11KV | [5 empty] | 14.0333
251 |  | 33/2 | DA+3 | 388 |  |  |  |  | 238.457 |  | 840 | 420 | 207 | 153 | 360 | 213 | 165 | 378 | 419313.387 | 3154959.194 |  |  | SONPALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 388 | 98621.048 | [12 empty] | 11KV | [5 empty] | 14.0887
252 |  | 33/3 | DA+9 | 452 |  |  |  |  | 240.2 |  | 840 | 420 | 235 | 238 | 473 | 224 | 235 | 459 | 419694.881 | 3155029.952 |  |  | SONPALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 452 | 99073.048 | [18 empty] | 14.1533
253 |  | 33/4 | DA+9 | 387.35 |  |  |  |  | 237.736 |  | 839.35 | 419.675 | 215 | 257 | 472 | 219 | 239 | 458 | 420139.301 | 3155112.38 |  |  | RANGAISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 387.35 | 99460.398 | [12 empty] | WATER TANK | [5 empty] | 14.2086
254 | AP-33A | 33A/0 | DC2+0 | 237.316 |  | 2037.351 |  |  | 234.908 | 33° 38' 31"RT | 624.666 | 312.333 | 131 | 17 | 148 | 150 | 72 | 222 | 420520.156 | 3155183.019 |  |  | RANGAISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 237.316 | 99697.714 | [12 empty] | HMPL (MUNDRA-BHATINDA) PETRLOEUM PIPELINE, 11KV, CT, BORE | [5 empty] | 14.2425
255 | AP-34 | 34/0 | DD45+9 | 479 |  | 237.316 |  |  | 235.255 | 38° 2' 52"LT | 716.316 | 358.158 | 221 | 249 | 470 | 166 | 247 | 413 | 420738.388 | 3155089.78 |  |  | RANGAISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 479 | 100176.714 | [12 empty] | 11KV | [5 empty] | 14.311
256 |  | 34/1 | DA+6 | 361 |  |  |  |  | 236.036 |  | 840 | 420 | 231 | 190 | 421 | 234 | 188 | 422 | 421201.254 | 3155213.054 |  |  | RANGAISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 361 | 100537.714 | [12 empty] | CT, 11KV | [5 empty] | 14.3625
257 |  | 34/2 | DA+6 | 459 |  |  |  |  | 234.308 |  | 820 | 410 | 171 | 234 | 405 | 174 | 233 | 407 | 421550.094 | 3155305.959 |  |  | RANGAISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 459 | 100996.714 | [12 empty] | 11KV | [5 empty] | 14.4281
258 |  | 34/3 | DA+0 | 371 |  |  |  |  | 239.371 |  | 830 | 415 | 226 | 160 | 386 | 227 | 167 | 394 | 421993.634 | 3155424.086 |  |  | RANGAISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 371 | 101367.714 | [12 empty] | 11KV | [5 empty] | 14.4811
259 |  | 34/4 | DA+9 | 437 |  |  |  |  | 235.125 |  | 808 | 404 | 212 | 222 | 434 | 205 | 221 | 426 | 422352.137 | 3155519.565 |  |  | RANGAISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 437 | 101804.714 | [12 empty] | CT, 11KV | [5 empty] | 14.5435
260 |  | 34/5 | DA+6 | 369 |  |  |  |  | 237.529 |  | 806 | 403 | 216 | 216 | 432 | 217 | 207 | 424 | 422774.418 | 3155632.029 |  |  | RANGAISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 369 | 102173.714 | [12 empty] | 11KV, CT | [5 empty] | 14.5962
261 |  | 34/6 | DA-3 | 451 |  |  |  |  | 240.906 |  | 820 | 410 | 154 | 168 | 322 | 163 | 185 | 348 | 423130.988 | 3155726.994 |  |  | RANGAISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 451 | 102624.714 | [12 empty] | 11KV | [5 empty] | 14.6607
262 |  | 34/7 | DA+6 | 389 |  |  |  |  | 244.723 |  | 840 | 420 | 284 | 100 | 384 | 268 | 127 | 395 | 423566.797 | 3155843.061 |  |  | RANGAISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 389 | 103013.714 | [18 empty] | 14.7162
263 |  | 34/8 | DA+9 | 385 |  |  |  |  | 259.829 |  | 774 | 387 | 290 | 286 | 576 | 263 | 260 | 523 | 423942.694 | 3155943.173 |  |  | RANGAISAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 385 | 103398.714 | [18 empty] | 14.7712
264 |  | 34/9 | DA+9 | 417 |  |  |  |  | 242.231 |  | 802 | 401 | 100 | 190 | 290 | 127 | 196 | 323 | 424314.726 | 3156042.255 |  |  | LODSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 417 | 103815.714 | [12 empty] | 11KV | [5 empty] | 14.8308
265 |  | 34/10 | DA+9 | 414.575 |  |  |  |  | 246.103 |  | 831.575 | 415.7875 | 228 | 201 | 429 | 223 | 203 | 426 | 424717.68 | 3156149.573 |  |  | NAHARSARA | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 414.575 | 104230.289 | [18 empty] | 14.89
266 | AP-35 | 35/0 | DB1+9 | 422 |  | 4532.575 |  |  | 247.444 | 3° 37' 34"RT | 836.575 | 418.2875 | 214 | 189 | 403 | 213 | 196 | 409 | 425118.291 | 3156256.266 |  |  | NAHARSARA | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 422 | 104652.289 | [18 empty] | 14.9503
267 |  | 35/1 | DA+9 | 384 |  |  |  |  | 252.114 |  | 806 | 403 | 234 | 209 | 443 | 228 | 204 | 432 | 425532.129 | 3156338.862 |  |  | NAHARSARA | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 384 | 105036.289 | [12 empty] | 11KV | [5 empty] | 15.0052
268 |  | 35/2 | DA+9 | 428 |  |  |  |  | 249.044 |  | 812 | 406 | 176 | 211 | 387 | 181 | 213 | 394 | 425908.702 | 3156414.021 |  |  | NAHARSARA | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 428 | 105464.289 | [12 empty] | CT | [5 empty] | 15.0663
269 |  | 35/3 | DA+3 | 400 |  |  |  |  | 255.67 |  | 828 | 414 | 217 | 216 | 433 | 217 | 212 | 429 | 426328.424 | 3156497.792 |  |  | NAHARSARA | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 400 | 105864.289 | [12 empty] | 11KV, CT | [5 empty] | 15.1235
270 |  | 35/4 | DA+3 | 423 |  |  |  |  | 252.565 |  | 823 | 411.5 | 184 | 220 | 404 | 189 | 218 | 407 | 426720.687 | 3156576.082 |  |  | NAHARSARA | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 423 | 106287.289 | [12 empty] | CT | [5 empty] | 15.1839
271 |  | 35/5 | DA+9 | 387 |  |  |  |  | 244.908 |  | 810 | 405 | 204 | 189 | 393 | 207 | 191 | 398 | 427135.506 | 3156658.874 |  |  | NAHARSARA | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 387 | 106674.289 | [12 empty] | CT | [5 empty] | 15.2392
272 |  | 35/6 | DA+9 | 419 |  |  |  |  | 245.78 |  | 806 | 403 | 198 | 255 | 453 | 197 | 243 | 440 | 427515.021 | 3156734.62 |  |  | NAHARSARA | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 419 | 107093.289 | [18 empty] | 15.299
273 |  | 35/7 | DA-3 | 393 |  |  |  |  | 248.565 |  | 812 | 406 | 164 | 159 | 323 | 178 | 170 | 348 | 427925.917 | 3156816.629 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 393 | 107486.289 | [18 empty] | 15.3552
274 |  | 35/8 | DA+3 | 404 |  |  |  |  | 249.757 |  | 797 | 398.5 | 235 | 199 | 434 | 224 | 200 | 424 | 428311.316 | 3156893.549 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 404 | 107890.289 | [18 empty] | 15.4129
275 |  | 35/9 | DA+9 | 434.613 |  |  |  |  | 244.471 |  | 838.613 | 419.3065 | 206 | 216 | 422 | 205 | 217 | 422 | 428707.502 | 3156972.622 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 434.613 | 108324.902 | [12 empty] | 11KV (2) | [5 empty] | 15.475
276 | AP-36 | 36/0 | DB1+6 | 307 |  | 4094.613 |  |  | 247.886 | 0° 36' 30"RT | 741.613 | 370.8065 | 220 | 151 | 371 | 220 | 152 | 372 | 429133.709 | 3157057.687 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 307 | 108631.902 | [12 empty] | CT | [5 empty] | 15.5188
277 |  | 36/1 | DA+6 | 326 |  |  |  |  | 248.312 |  | 633 | 316.5 | 157 | 215 | 372 | 156 | 199 | 355 | 429435.392 | 3157114.575 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 326 | 108957.902 | [18 empty] | 15.5654
278 |  | 36/2 | DA+9 | 392 |  |  |  |  | 237.471 |  | 718 | 359 | 112 | 219 | 331 | 128 | 212 | 340 | 429755.746 | 3157174.983 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 392 | 109349.902 | [12 empty] | METAL ROAD, 11KV (2), 33KV | [5 empty] | 15.6214
279 |  | 36/3 | DA+9 | 441 |  |  |  |  | 233.338 |  | 833 | 416.5 | 174 | 217 | 391 | 181 | 219 | 400 | 430140.957 | 3157247.622 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 441 | 109790.902 | [12 empty] | 11KV, CT | [5 empty] | 15.6844
280 |  | 36/4 | DA+9 | 399 |  |  |  |  | 234.088 |  | 840 | 420 | 225 | 176 | 401 | 224 | 184 | 408 | 430574.32 | 3157329.34 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 399 | 110189.902 | [18 empty] | 15.7414
281 |  | 36/5 | DA+6 | 441 |  |  |  |  | 241.474 |  | 840 | 420 | 223 | 172 | 395 | 216 | 188 | 404 | 430966.41 | 3157403.276 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 441 | 110630.902 | [12 empty] | CT | [5 empty] | 15.8044
282 |  | 36/6 | DA+9 | 399 |  |  |  |  | 248.458 |  | 840 | 420 | 270 | 242 | 512 | 255 | 229 | 484 | 431399.773 | 3157484.994 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 399 | 111029.902 | [12 empty] | CT (2) | [5 empty] | 15.8614
283 |  | 36/7 | DA+3 | 432 |  |  |  |  | 246.589 |  | 831 | 415.5 | 157 | 215 | 372 | 171 | 216 | 387 | 431791.863 | 3157558.929 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 432 | 111461.902 | [12 empty] | CT, 11KV | [5 empty] | 15.9231
284 |  | 36/8 | DA+3 | 357 |  |  |  |  | 246.834 |  | 789 | 394.5 | 218 | 194 | 412 | 218 | 189 | 407 | 432216.381 | 3157638.98 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 357 | 111818.902 | [12 empty] | HUT | [5 empty] | 15.9741
285 |  | 36/9 | DA+6 | 398.258 |  |  |  |  | 241.294 |  | 755.258 | 377.629 | 163 | 235 | 398 | 168 | 224 | 392 | 432567.198 | 3157705.133 |  |  | MALAKSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 398.258 | 112217.16 | [12 empty] | CT, COW HUT | [5 empty] | 16.031
286 | AP-37 | 37/0 | DB1+0 | 355 |  | 3892.258 |  |  | 240.72 | 4° 21' 52"RT | 753.258 | 376.629 | 164 | 156 | 320 | 176 | 163 | 339 | 432958.559 | 3157778.931 |  |  | HALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 355 | 112572.16 | [18 empty] | 16.0817
287 |  | 37/1 | DA+0 | 407 |  |  |  |  | 244.373 |  | 762 | 381 | 200 | 215 | 415 | 193 | 212 | 405 | 433311.405 | 3157817.974 |  |  | HALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 407 | 112979.16 | [12 empty] | 11KV, BORE | [5 empty] | 16.1399
288 |  | 37/2 | DA+3 | 303 |  |  |  |  | 239.234 |  | 710 | 355 | 192 | 110 | 302 | 196 | 123 | 319 | 433715.936 | 3157862.736 |  |  | HALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 303 | 113282.16 | [18 empty] | 16.1832
289 |  | 37/3 | DA+3 | 387 |  |  |  |  | 245.164 |  | 690 | 345 | 194 | 200 | 394 | 181 | 198 | 379 | 434017.098 | 3157896.061 |  |  | HALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 387 | 113669.16 | [12 empty] | WATER TANK | [5 empty] | 16.2385
290 |  | 37/4 | DA+3 | 419 |  |  |  |  | 244.131 |  | 806 | 403 | 188 | 252 | 440 | 190 | 239 | 429 | 434401.751 | 3157938.623 |  |  | HALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 419 | 114088.16 | [12 empty] | WATER TANK, HUT | [5 empty] | 16.2983
291 |  | 37/5 | DA+6 | 389 |  |  |  |  | 232.97 |  | 808 | 404 | 168 | 188 | 356 | 182 | 190 | 372 | 434818.209 | 3157984.705 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 389 | 114477.16 | [18 empty] | 16.3539
292 |  | 37/6 | DA+6 | 381 |  |  |  |  | 234.265 |  | 770 | 385 | 202 | 200 | 402 | 200 | 198 | 398 | 435204.849 | 3158027.488 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 381 | 114858.16 | [18 empty] | 16.4083
293 |  | 37/7 | DA-3 | 410 |  |  |  |  | 241.575 |  | 791 | 395.5 | 181 | 177 | 358 | 185 | 186 | 371 | 435583.538 | 3158069.39 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 410 | 115268.16 | [12 empty] | WATER TANK, CT, 11KV, 11KV CHOK | [5 empty] | 16.4669
294 |  | 37/8 | DA+9 | 430 |  |  |  |  | 234.975 |  | 840 | 420 | 234 | 266 | 500 | 225 | 250 | 475 | 435991.051 | 3158114.482 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 430 | 115698.16 | [12 empty] | 11KV, CT | [5 empty] | 16.5283
295 |  | 37/9 | DA-3 | 409 |  |  |  |  | 236.874 |  | 839 | 419.5 | 165 | 113 | 278 | 181 | 142 | 323 | 436418.442 | 3158161.774 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 409 | 116107.16 | [12 empty] | 11KV | [5 empty] | 16.5867
296 |  | 37/10 | DA+6 | 409.505 |  |  |  |  | 245.422 |  | 818.505 | 409.2525 | 297 | 234 | 531 | 268 | 225 | 493 | 436824.961 | 3158206.756 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 409.505 | 116516.665 | [12 empty] | LT, CT, 11KV | [5 empty] | 16.6452
297 | AP-38 | 38/0 | DB2+0 | 381 |  | 4299.505 |  |  | 245.961 | 11° 35' 6"LT | 790.505 | 395.2525 | 176 | 282 | 458 | 186 | 249 | 435 | 437231.982 | 3158251.794 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 381 | 116897.665 | [12 empty] | 11KV | [5 empty] | 16.6997
298 |  | 38/1 | DA+0 | 293 |  |  |  |  | 230.411 |  | 674 | 337 | 99 | 117 | 216 | 134 | 128 | 262 | 437594.541 | 3158368.891 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 293 | 117190.665 | [12 empty] | 11KV, CT | [5 empty] | 16.7415
299 |  | 38/2 | DA-3 | 354.846 |  |  |  |  | 237.276 |  | 647.846 | 323.923 | 176 | 99 | 275 | 165 | 128 | 293 | 437873.36 | 3158458.943 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 354.846 | 117545.511 | [12 empty] | 11KV, CT | [5 empty] | 16.7922
300 | AP-39 | 39/0 | DB2+9 | 258.435 |  | 1028.846 |  |  | 237.765 | 8° 36' 50"LT | 613.281 | 306.6405 | 257 | 78 | 335 | 228 | 104 | 332 | 438211.031 | 3158568.002 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 258.435 | 117803.946 | [12 empty] | 132KV D/C HALASAR-PALTISAR FANTA TL, 11KV | [5 empty] | 16.8291
301 | AP-40 | 40/0 | DC1+9 | 413.001 |  | 258.435 |  |  | 243.079 | 19° 32' 59"RT | 671.436 | 335.718 | 181 | 175 | 356 | 155 | 186 | 341 | 438442.287 | 3158683.368 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 413.001 | 118216.947 | [18 empty] | 16.8881
302 |  | 40/1 | DA+3 | 371 |  |  |  |  | 255.122 |  | 784.001 | 392.0005 | 239 | 219 | 458 | 229 | 208 | 437 | 438852.241 | 3158733.437 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 371 | 118587.947 | [12 empty] | 11KV, METAL ROAD | [5 empty] | 16.9411
303 |  | 40/2 | DA+9 | 355 |  |  |  |  | 243.428 |  | 726 | 363 | 152 | 225 | 377 | 164 | 210 | 374 | 439220.505 | 3158778.415 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 355 | 118942.947 | [12 empty] | 11KV | [5 empty] | 16.9918
304 |  | 40/3 | DA+3 | 388 |  |  |  |  | 241.638 |  | 743 | 371.5 | 130 | 207 | 337 | 146 | 203 | 349 | 439572.887 | 3158821.453 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 388 | 119330.947 | [12 empty] | HUT, 11KV | [5 empty] | 17.0473
305 |  | 40/4 | DA+6 | 384.061 |  |  |  |  | 236.292 |  | 772.061 | 386.0305 | 181 | 211 | 392 | 186 | 205 | 391 | 439958.025 | 3158868.491 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 384.061 | 119715.008 | [18 empty] | 17.1021
306 | AP-41 | 41/0 | DC1+0 | 382.001 |  | 1911.062 |  |  | 238.911 | 20° 46' 32"LT | 766.062 | 383.031 | 173 | 153 | 326 | 180 | 165 | 345 | 440339.253 | 3158915.052 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 382.001 | 120097.009 | [18 empty] | 17.1567
307 |  | 41/1 | DA+0 | 357 |  |  |  |  | 245.717 |  | 739.001 | 369.5005 | 230 | 154 | 384 | 217 | 162 | 379 | 440677.354 | 3159092.851 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 357 | 120454.009 | [12 empty] | WATER TANK | [5 empty] | 17.2077
308 |  | 41/2 | DA+0 | 418 |  |  |  |  | 249.747 |  | 775 | 387.5 | 203 | 197 | 400 | 195 | 201 | 396 | 440993.327 | 3159259.014 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 418 | 120872.009 | [12 empty] | CT | [5 empty] | 17.2674
309 |  | 41/3 | DA+6 | 422 |  |  |  |  | 246.108 |  | 840 | 420 | 222 | 186 | 408 | 218 | 194 | 412 | 441363.29 | 3159453.569 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 422 | 121294.009 | [12 empty] | 11KV | [5 empty] | 17.3277
310 |  | 41/4 | DA+6 | 383 |  |  |  |  | 251.087 |  | 805 | 402.5 | 237 | 221 | 458 | 229 | 212 | 441 | 441736.793 | 3159649.985 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 383 | 121677.009 | [18 empty] | 17.3824
311 |  | 41/5 | DA+3 | 381 |  |  |  |  | 248.96 |  | 764 | 382 | 163 | 178 | 341 | 173 | 183 | 356 | 442075.778 | 3159828.249 |  |  | MALSAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 381 | 122058.009 | [18 empty] | 17.4369
312 |  | 41/6 | DA+3 | 352.745 |  |  |  |  | 251.16 |  | 733.745 | 366.8725 | 203 | 258 | 461 | 199 | 232 | 431 | 442412.993 | 3160005.583 |  |  | HALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 352.745 | 122410.754 | [18 empty] | 17.4873
313 | AP-42 | 42/0 | DB1+0 | 255.321 |  | 2695.746 |  |  | 240.928 | 4° 32' 3"RT | 608.066 | 304.033 | 96 | 111 | 207 | 122 | 120 | 242 | 442725.2 | 3160169.765 |  |  | HALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 255.321 | 122666.075 | [12 empty] | 33KV S/C (HALASAR-SARDARSHAHAR TL) T93-94 | [5 empty] | 17.5237
314 | AP-43 | 43/0 | DC1+0 | 417.702 |  | 255.321 |  |  | 242.628 | 19° 16' 20"RT | 673.023 | 336.5115 | 145 | 185 | 330 | 136 | 192 | 328 | 442959.866 | 3160270.366 |  |  | HALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 417.702 | 123083.777 | [12 empty] | SH-7 SARDARSHAHAR-HANUMANGARH, 33KV, DHABA, 11KV | [5 empty] | 17.5834
315 | AP-44 | 44/0 | DB2+6 | 340 |  | 417.702 |  |  | 241.561 | 7° 59' 3"RT | 757.702 | 378.8505 | 233 | 204 | 437 | 227 | 193 | 420 | 443376.584 | 3160299.012 |  |  | HALASAR | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 340 | 123423.777 | [18 empty] | 17.632
316 |  | 44/1 | DA-3 | 410.291 |  |  |  |  | 245.281 |  | 750.291 | 375.1455 | 136 | 125 | 261 | 148 | 152 | 300 | 443715.734 | 3160274.989 |  |  |  | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 410.291 | 123834.068 | [12 empty] | HOUSE | [5 empty] | 17.6906
317 | AP-45 | 45/0 | DC2+9 | 364.523 |  | 750.291 |  |  | 248.489 | 25° 37' 10"LT | 774.814 | 387.407 | 286 | 160 | 446 | 260 | 168 | 428 | 444125 | 3160246 |  |  |  | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 364.523 | 124198.591 | [12 empty] | 132KV S/C Line, 220KV D/C Line, HOUSE | [5 empty] | 17.7427
318 | AP-46 | 46/0 | DD60+18 | 368 |  | 364.523 |  |  | 243.21 | 0° 52' 56"LT | 732.523 | 366.2615 | 205 | 166 | 371 | 197 | 172 | 369 | 444464 | 3160380 |  |  |  | SARDARSHAHAR | CHURU |  | 0
[7 empty] | 368 | 124566.591 | [12 empty] | 400 KV S/C SURATGARH- BIKANER LINE (I), 400 KV S/C SURATGARH- BIKANER LINE(II) | [5 empty] | 17.7952
319 | AP-47 | 47/0 | DD60+18 |  |  | 368 |  |  | 246.69 |  | 368 | 184 | 202 | 0 | 202 | 197 | 0 | 197 | 444804.11 | 3160520.532 |  |  |  | SARDARSHAHAR | CHURU |  | 0
Total | [5 empty] | 124.5666 | 124.5666 | 124.5666
| DA-3 | 13
| DA-1.5 | 18
| DA+0 | 54
| DA+1.5 | 0
| DA+3 | 71
| DA+4.5 | 0
| DA+6 | 55
| DA+9 | 45
| DB1+0 | 9
| DB1+3 | 3
| DB1+6 | 1
| DB1+9 | 4
| DB1+18 | 1
| DB2+0 | 7 | RC 1M (No. - 01)
| DB2+3 | 3
| DB2+6 | 1
| DB2+9 | 1
| DC1+0 | 5
| DC1+3 | 1
| DC1+6 | 1
| DC1+9 | 1
| DC2-3 | 0
| DC2+0 | 6
| DC2+3 | 1
| DC2+6 | 0
| DC2+9 | 2
| DC2+15 | 0
| DD45-3 | 0
| DD45+0 | 2
| DD45+3 | 0
| DD45+6 | 0
| DD45+9 | 2
| DD60+0 | 2 | RC 1M (No. - 01)
| DD60+3 | 2
| DD60+6 | 1
| DD60+9 | 1
| DD60+18 | 3 | RC 2M (No. - 01)
| DD60+25 | 1
| DD60+35 | 2 | RC 2M (No. - 02)
| Total | 319

## Project Details (hidden)
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer/Manager | PCH | Regional Manager | Project Manager | Section Incharge | Supervisor
TA 512 | 765KV D/C Bikaner IV PS - Siwani II TL | PGCIL | 2025-01-03 | 2026-12-03 | Saurabh Katiyar | Mr Sanjay Kumar Gupta |  | Mr Atul Kumar Gupta | Tamojit Bandyopadhyay | Dhiraj kumar
[9 empty] | Suraji Kumar | Rajkishor muni
[9 empty] | Babasaheb Kushare | Mahendra Vishvakarma
Dular chand
Monu Kumar
Sher singh Rana
Deepak Kumar Mahata
Sonu Kumar
Ankur Gogoi
Narayan Mahto 1
Sujit Chowdhury
Rohit Sharma
Chet Ram
Montu Biswas
Ramesh Kumar Mahato
Narayan Kumar Mahto 2
Kailash Mahto
Rohit Kumar Mahto
Raghu Kumar
Dinesh Kumar Mahto
Rakesh Kumar
Ajaru Deen
Sadam

## L3 Plan (hidden)
CONTRACTOR: Kalpataru Power Transmission Limited
Proposed 765kV D/C Sikar II S/S - Aligarh S/S Transmission Line ,Part-3
AS PER APPROVED CHECK SURVEY
SL- No- | New AP NO | Type of Tower | Angle of Deviation | Span | Sectional Length | Detail survey Approval date | Check survey completion date | Foundation classification | Soil investigation date | Foundation dates |  | Tower erection dates |  | Earthing |  | Tac welding |  | Stringing |  | OPGW |  | Final checking offer date
[10 empty] | Start | Completion | Start | Completion | Start | Completion | Start | Completion | Start | Completion | Start | Completion
1 | AP-183/0 | DD60+3 | LT 50° 52' 49" |  |  | 2021-06-01
|  |  |  | 383.176 | 383.176
2 | AP-184/0 | DD60+9 | LT 53° 56' 30" |  |  | 2021-06-01
|  |  |  | 236.888 | 236.888
3 | AP-185/0 | DD45+15 | RT 32° 16' 54" |  |  | 2021-06-01
|  |  |  | 315.04 | 315.04
4 | AP-186/0 | DD45+9 | RT 42° 30' 3" |  |  | 2021-06-01 | 2021-11-10
|  |  |  | 477.307 | 1993.693
5 | 186/1 | DA+0 |  |  |  | 2021-06-01 | 2021-11-10 | DRY |  | 2021-11-27 | 2021-12-07 | 2022-01-12 | 2022-01-19 | 2021-12-14 | 2021-12-14
359.774
6 | 186/2 | DA+0 |  |  |  | 2021-06-01 | 2021-11-10 | WET |  | 2021-11-12 | 2021-11-20 | 2022-01-19 | 2022-01-24 | 2021-12-14 | 2021-12-14
412.081
7 | 186/3 | DA+3 |  |  |  | 2021-06-01 | 2021-11-10 | WET |  | 2021-11-01 | 2021-11-14 | 2022-01-24 | 2022-01-31 | 2021-12-14 | 2021-12-14
397.821
8 | 186/4 | DA+0 |  |  |  | 2021-06-01 | 2021-11-10 | WET |  | 2021-10-24 | 2021-10-31 | 2022-01-12 | 2022-01-17 | 2021-12-14 | 2021-12-14
346.71
9 | AP-187/0 | DB1+0 | RT 0° 11' 28" |  |  | 2021-06-01 | 2021-08-15 | WET |  | 2021-10-15 | 2021-10-23 | 2022-01-17 | 2022-01-25 | 2021-12-14 | 2021-12-14
|  |  |  | 306.449 | 701.889
10 | 187/1 | DA+3 |  |  |  | 2021-06-01 | 2021-08-15 | WET |  | 2021-09-24 | 2021-10-12 | 2022-01-25 | 2022-01-31 | 2021-10-23 | 2021-10-24
395.44
11 | AP-188/0 | DD60+3 | LT 2° 51' 51" |  |  | 2021-06-01 | 2021-08-15
|  |  |  | 249.479 | 249.479
12 | AP-188A/0 | DD60+0 |  |  |  | 2021-06-01 | 2021-08-15
|  |  |  | 298.12 | 665.763
13 | 188A/1 | DA+0 |  |  |  | 2021-06-01 | 2021-08-15
367.643
14 | AP-189/0 | DB1+12 | LT 4° 8' 51" |  |  | 2021-06-01 | 2021-08-15
|  |  |  | 219.385 | 219.385
15 | AP-190/0 | DC2+9 | LT 24° 11' 8" |  |  | 2021-06-01 | 2021-08-15
|  |  |  | 338.683 | 552.674
16 | 190/1 | DA+6 |  |  |  | 2021-06-01 | 2021-08-15
213.991
17 | AP-191/0 | DC1+6 | RT 16° 53' 23" |  |  | 2021-06-01 | 2021-08-15
|  |  |  | 236.516 | 236.516
18 | AP-192/0 | DC2+6 | LT 25° 55' 28" |  |  | 2021-06-01 | 2021-08-15
|  |  |  | 299.577 | 598.62
19 | 192/1 | DA+0 |  |  |  | 2021-06-01 | 2021-08-15 | WET
299.042
20 | AP-193/0 | DD60+3 | RT 18° 42' 41" |  |  | 2021-06-01 | 2021-08-15 | WET |  | 2021-11-07 | 2021-12-05 | 2022-01-11 | 2022-01-22 | 2021-12-08 | 2021-12-08
|  |  |  | 243.594 | 243.594
21 | AP-194/0 | DD60+3 | RT 11° 47' 10" |  |  | 2021-06-01 | 2021-08-15 | WET |  | 2021-10-24 | 2021-10-31 | 2022-01-22 | 2022-01-31
|  |  |  | 358.75 | 1022.714
22 | 194/1 | DA-3 |  |  |  | 2021-06-01 | 2021-09-10 | DRY |  | 2021-10-16 | 2021-10-23 | 2022-01-12 | 2022-01-19 | 2021-11-25 | 2021-11-25
290.222
23 | 194/2 | DA-3 |  |  |  | 2021-06-01 | 2021-09-10 | DRY |  | 2021-10-04 | 2021-10-13 | 2022-01-19 | 2022-01-24
373.742
24 | AP-195/0 | DB1+9 | LT 3° 6' 0" |  |  | 2021-06-01 | 2021-09-10
|  |  |  | 213.295 | 213
25 | AP-196/0 | DB2+12 | LT 7° 20' 59" |  |  | 2021-06-01 | 2021-09-10
|  |  |  | 439.664 | 800.723
26 | 196/1 | DA-3 |  |  |  | 2021-06-01 | 2021-09-10 | WET |  | 2021-10-04 | 2021-10-10 | 2022-01-24 | 2022-01-31 | 2021-10-23 | 2021-10-24
361.059
27 | AP-197/0 | DB2+0 | RT 7° 12' 59" |  |  | 2021-06-01 | 2021-09-10 | WET |  | 2021-10-16 | 2021-10-23 | 2022-01-12 | 2022-01-19 | 2021-11-18 | 2021-11-19
|  |  |  | 372.578 | 2306.685
28 | 197/1 | DA+0 |  |  |  | 2021-06-01 | 2021-09-10 | WET |  | 2021-10-23 | 2021-10-31 | 2022-01-19 | 2022-01-24 | 2021-11-25 | 2021-11-25
379.934
29 | 197/2 | DA+0 |  |  |  | 2021-06-01 | 2021-09-10 | WET |  | 2021-11-07 | 2021-11-28 | 2022-01-24 | 2022-01-31
378.46
30 | 197/3 | DA+0 |  |  |  | 2021-06-01 | 2021-09-10 | WET |  | 2021-11-07 | 2021-11-23 | 2022-01-12 | 2022-01-19
359.685
31 | 197/4 | DA-3 |  |  |  | 2021-06-01 | 2021-09-10 | WET |  | 2021-10-23 | 2021-10-31 | 2022-01-19 | 2022-01-24 | 2021-11-20 | 2021-11-21
383.533
32 | 197/5 | DA+3 |  |  |  | 2021-06-01 | 2021-09-10 | WET |  | 2021-10-24 | 2021-11-10 | 2021-12-17 | 2021-12-26 | 2021-11-25 | 2021-11-25
432.495
33 | AP-198/0 | DD60+3 | RT 4° 55' 28" |  |  | 2021-06-01 | 2021-09-10 | WET |  | 2021-11-17 | 2021-12-08 | 2021-12-26 | 2021-12-31 | 2021-12-09 | 2021-12-09
|  |  |  | 246.376 | 246.376
34 | AP-199/0 | DD60+0 | LT 2° 55' 58" |  |  | 2021-06-01 | 2021-09-10 | WET |  | 2021-12-01 | 2021-12-26
|  |  |  | 368.873 | 752.36
35 | 199/1 | DA+0 |  |  |  | 2021-06-01 | 2021-09-10 | WET |  | 2021-09-25 | 2021-10-04 | 2022-01-24 | 2022-01-31 | 2021-10-06 | 2021-10-07
383.487
36 | 199/2 | DB1+0 |  |  |  | 2021-06-01 | 2021-09-10 | WET |  | 2021-10-05 | 2021-10-10 | 2022-01-12 | 2022-01-20 | 2021-10-23 | 2021-10-24
|  |  |  | 310.716 | 310.716
37 | AP-200/0 | DB2+0 | RT 5° 13' 33" |  |  | 2021-06-01 | 2021-09-10
|  |  |  | 555.763 | 555.763
38 | AP-201/0 | DB2+0 | LT 11° 0' 51" |  |  | 2021-06-01 | 2021-09-10 | WET
|  |  |  | 387.518 | 387.518
39 | AP-202/0 | DB2+9 | LT 14° 6' 30" |  |  | 2021-06-01 | 2021-09-10 | WET |  | 2021-09-16 | 2021-09-22 | 2021-10-27 | 2021-10-31 | 2021-09-27 | 2021-09-27
|  |  |  | 364.589 | 364.589
40 | AP-203/0 | DC1+0 | RT 17° 48' 16" |  |  | 2021-06-01 | 2021-07-20 | WET |  | 2021-08-26 | 2021-09-15 | 2021-12-06 | 2021-12-13 | 2021-09-19 | 2021-09-20 |  |  | 2021-12-10 | 2021-12-28
|  |  |  | 382.628 | 1483.914
41 | 203/1 | DA+0 |  |  |  | 2021-06-01 | 2021-07-20 | DRY |  | 2021-08-11 | 2021-08-21 | 2021-10-03 | 2021-10-11 | 2021-09-19 | 2021-09-20 |  |  | 2021-12-10 | 2021-12-28
349.29
42 | 203/2 | DA+0 |  |  |  | 2021-06-01 | 2021-07-20 | DRY |  | 2021-08-20 | 2021-08-26 | 2021-09-25 | 2021-09-30 | 2021-11-25 | 2021-11-25 |  |  | 2021-12-10 | 2021-12-28
379.079
43 | 203/3 | DA+0 |  |  |  | 2021-06-01 | 2021-07-20 | DRY |  | 2021-08-17 | 2021-08-30 | 2021-09-15 | 2021-09-24 | 2021-10-10 | 2021-10-10 |  |  | 2021-12-10 | 2021-12-28
372.917
44 | AP-204/0 | DC1+0 | LT 21° 18' 44" |  |  | 2021-06-01 | 2021-07-20 | WET |  | 2021-09-11 | 2021-10-03 | 2021-11-16 | 2021-11-26 | 2021-10-23 | 2021-10-24 |  |  | 2021-12-05 | 2021-12-19
|  |  |  | 373.377 | 1935.084
45 | 204/1 | DA+0 |  |  |  | 2021-06-01 | 2021-08-20 | DRY |  | 2021-08-31 | 2021-09-10 | 2021-10-06 | 2021-10-12 | 2021-10-10 | 2021-10-10 |  |  | 2021-12-05 | 2021-12-19
387.205
46 | 204/2 | DA+0 |  |  |  | 2021-06-01 | 2021-08-20 | DRY |  | 2021-08-14 | 2021-08-21 | 2021-10-13 | 2021-10-23 | 2021-09-19 | 2021-09-20 |  |  | 2021-12-05 | 2021-12-19
385.358
47 | AP-204A/0 | DB1+0 |  |  |  | 2021-06-01 | 2021-08-20 | DRY |  | 2021-08-31 | 2021-09-12 | 2021-10-12 | 2021-10-19 | 2021-09-19 | 2021-09-20 |  |  | 2021-12-05 | 2021-12-19
403.579
48 | 204A/1 | DA+3 |  |  |  | 2021-06-01 | 2021-08-20 | DRY |  | 2021-08-31 | 2021-09-08 | 2021-10-21 | 2021-10-26 | 2021-09-19 | 2021-09-20 |  |  | 2021-12-29 | 2021-12-31
385.565
49 | AP-205/0 | DD45+3 | RT 39° 34' 20" |  |  | 2021-06-01 | 2021-08-20 | WET |  | 2021-09-14 | 2021-09-30 | 2021-11-05 | 2021-11-19 | 2021-11-18 | 2021-11-19 |  |  | 2022-01-01 | 2022-01-12
|  |  |  | 393.362 | 785.128
50 | 205/1 | DA+3 |  |  |  | 2021-06-01 | 2021-08-20 | DRY |  | 2021-08-25 | 2021-08-30 | 2021-10-22 | 2021-10-27 | 2021-09-19 | 2021-09-20 |  |  | 2022-01-01 | 2022-01-12
391.766
51 | AP-206/0 | DD45+0 | LT 33° 25' 42" |  |  | 2021-05-06 | 2021-07-20 | WET |  | 2021-09-09 | 2021-09-29 | 2021-10-25 | 2021-10-31 | 2021-10-27 | 2021-10-27 |  |  | 2022-01-01 | 2022-01-12
|  |  |  | 423.216 | 3779.241
52 | 206/1 | DA+6 |  |  |  | 2021-05-06 | 2021-07-20 | DRY |  | 2021-07-14 | 2021-08-05 | 2021-10-07 | 2021-10-13 | 2021-08-28 | 2021-08-28 |  |  | 2022-01-12 | 2022-01-23
415.097
53 | 206/2 | DA+0 |  |  |  | 2021-05-06 | 2021-07-20 | DRY |  | 2021-07-30 | 2021-08-16 | 2021-09-06 | 2021-09-18 | 2021-08-16 | 2021-08-16 |  |  | 2022-01-12 | 2022-01-23
424.618
54 | 206/3 | DA+6 |  |  |  | 2021-05-06 | 2021-07-20 | DRY |  | 2021-08-04 | 2021-08-13 | 2021-10-01 | 2021-10-07 | 2021-08-17 | 2021-08-17 |  |  | 2022-01-12 | 2022-01-23
413.106
55 | 206/4 | DA+0 |  |  |  | 2021-05-06 | 2021-07-20 | DRY |  | 2021-07-15 | 2021-08-05 | 2021-09-20 | 2021-09-29 | 2021-09-19 | 2021-09-20 |  |  | 2022-01-12 | 2022-01-23
424.946
56 | 206/5 | DA+3 |  |  |  | 2021-05-06 | 2021-07-20 | DRY |  | 2021-07-16 | 2021-08-13 | 2021-12-10 | 2021-12-16 | 2021-08-19 | 2021-08-19
|  |  |  | 414.177 | [13 empty] | 2022-01-12 | 2022-01-23
57 | 206/6 | DA+0 |  |  |  | 2021-05-06 | 2021-07-20 | WET |  | 2021-08-13 | 2021-08-19 | 2021-10-20 | 2021-10-31 | 2021-08-19 | 2021-08-19
425.219
58 | 206/7 | DA+3 |  |  |  | 2021-05-06 | 2021-07-20 | FS |  | 2021-10-15 | 2021-10-31 | 2021-11-30 | 2021-12-07 | 2021-11-20 | 2021-11-21 |  |  | 2022-01-12 | 2022-01-23
413.695
59 | 206/8 | DA+0 |  |  |  | 2021-05-06 | 2021-07-20 | WET |  | 2021-09-19 | 2021-09-29 | 2021-11-21 | 2021-11-29 | 2021-10-06 | 2021-10-07 |  |  | 2022-01-12 | 2022-01-23
425.167
60 | AP-207/0 | DD45+9 | RT 38° 57' 27" |  |  | 2021-05-06 | 2021-12-03 | WET |  | 2021-12-01 | 2021-12-13 | 2021-12-25 | 2021-12-31 |  |  |  |  | 2022-01-23 | 2022-01-31
|  |  |  | 290 | 1933.745
61 | AP-207A/0 | DD45+0 | LT 41° 40' 10" |  |  | 2021-05-06 | 2021-12-03 | WET |  | 2021-12-12 | 2021-12-31 | 2022-01-20 | 2022-01-31 |  |  |  |  | 2022-01-23 | 2022-01-31
429.52
62 | 207A/1 | DA+6 |  |  |  | 2021-05-06 | 2021-12-03 | DRY |  | 2021-12-15 | 2021-12-30 | 2022-01-12 | 2022-01-20
409.485
63 | AP-208/0 | DD60+0 | RT 48° 5' 46" |  |  | 2021-05-06 | 2021-12-03 | WET |  | 2021-12-12 | 2021-12-30 | 2022-01-20 | 2022-01-31
377.605
64 | 208/1 | DA+3 |  |  |  | 2021-05-06 | 2021-12-03 | WET |  | 2021-12-01 | 2021-12-10 | 2021-12-17 | 2021-12-26
427.135
65 | AP-209/0 | DB2+3 | LT 10° 43' 58" |  |  | 2021-05-06 | 2021-12-03 |  |  | 2022-01-01 | 2022-01-17
|  |  |  | 377.065 | 1402.828
66 | 209/1 | DA+0 |  |  |  | 2021-05-06 | 2021-12-03 | WET |  | 2021-12-17 | 2021-12-30 | 2022-01-12 | 2022-01-19
341.998
67 | 209/2 | DA-3 |  |  |  | 2021-05-06 | 2021-12-03 |  |  | 2022-01-17 | 2022-01-25
342.162
68 | 209/3 | DA-3 |  |  |  | 2021-05-06 | 2021-12-03 |  |  | 2022-01-25 | 2022-01-31
341.603
69 | AP-209A/0 | DC1+0 | LT 18° 11' 42" |  |  | 2021-05-06 | 2021-12-03 |  |  | 2022-01-01 | 2022-01-17
|  |  |  | 380.565 | 381
70 | AP-210/0 | DD60+25 | LT 42° 25' 7" |  |  | 2021-05-06 | 2021-12-03
|  |  |  | 206.306 | 206.306
71 | AP-211/0 | DD60+18 | RT 24° 51' 11" |  |  | 2021-05-06 | 2021-11-10
|  |  |  | 395.694 | 4618.282
72 | 211/1 | DA+0 |  |  |  | 2021-05-06 | 2021-11-10 | PS
380.421
73 | 211/2 | DA+3 |  |  |  | 2021-05-06 | 2021-11-10 | PS
433.357
74 | 211/3 | DA+3 |  |  |  | 2021-05-06 | 2021-11-10 | PS |  | July'22 | July'22
404.268
75 | 211/4 | DA+3 |  |  |  | 2021-05-06 | 2021-11-10 | PS |  | July'22 | July'22
407.235
76 | 211/5 | DA+0 |  |  |  | 2021-05-06 | 2021-11-10 | FS |  | 2021-12-12 | 2021-12-31 | 2022-01-19 | 2022-01-24
344.747
77 | 211/6 | DA+0 |  |  |  | 2021-05-06 | 2021-11-10 | PS |  | July'22 | July'22
393.392
78 | 211/7 | DA+0 |  |  |  | 2021-05-06 | 2021-11-10 |  |  | 2022-01-25 | 2022-01-31
369.048
79 | 211/8 | DA+0 |  |  |  | 2021-05-06 | 2021-11-10 |  |  | 2022-01-01 | 2022-01-12
376.206
80 | 211/9 | DA+0 |  |  |  | 2021-05-06 | 2021-11-10 | FS |  | 2021-12-12 | 2021-12-26 | 2022-01-24 | 2022-01-31
375.916
81 | 211/10 | DA+0 |  |  |  | 2021-05-06 | 2021-11-10 | WET |  | 2021-12-24 | 2021-12-31 | 2022-01-12 | 2022-01-17
373.444
82 | 211/11 | DA+0 |  |  |  | 2021-05-06 | 2021-11-10 | WET |  | 2021-12-22 | 2021-12-31 | 2022-01-17 | 2022-01-22
364.554
83 | AP-212/0 | DB2+0 | LT 13° 41' 29" |  |  | 2021-05-06 | 2021-11-10 | WET |  | 2021-12-12 | 2021-12-22 | 2022-01-22 | 2022-01-31
|  |  |  | 390.318 | 1123.07
84 | 212/1 | DA+3 |  |  |  | 2021-05-06 | 2021-11-10 | WET |  | 2021-12-26 | 2021-12-31 | 2022-01-12 | 2022-01-17
386.684
85 | 212/2 | DA+0 |  |  |  | 2021-05-06 | 2021-11-10
346.068
86 | AP-213/0 | DD45+6 | LT 38° 26' 14" |  |  | 2021-05-06 |  |  |  | 2022-01-12 | 2022-01-24
|  |  |  | 237.977 | 237.977
87 | 213/1 | DD60+35 |  |  |  | 2021-05-06
|  |  |  | 274.659 | 274.659
88 | AP-214/0 | DD60+25 | RT 54° 31' 38" |  |  | 2021-05-06
|  |  |  | 275.862 | 275.862
89 | 214/1 | DB1+0 |  |  |  | 2021-05-06 |  |  |  | 2022-01-24 | 2022-01-31 | July'22 | July'22
|  |  |  | 424.77 | 3553.307
90 | 214/2 | DA+0 |  |  |  | 2021-05-06 |  |  |  | 2022-01-01 | 2022-01-12
379.167
91 | 214/3 | DA+0 |  |  |  | 2021-05-06 |  |  |  | 2022-01-12 | 2022-01-19
389.756
92 | 214/4 | DA+0 |  |  |  | 2021-05-06 |  |  |  | 2022-01-19 | 2022-01-26 | July'22 | July'22
393.882
93 | 214/5 | DA+0 |  |  |  | 2021-05-06 |  |  |  | 2022-01-26 | 2022-01-31 | July'22 | July'22
390.182
94 | 214/6 | DA+0 |  |  |  | 2021-05-06 |  |  |  | 2022-01-01 | 2022-01-16 | July'22 | July'22
382.91
95 | 214/7 | DA+0 |  |  |  | 2021-05-06 |  |  |  | 2022-01-16 | 2022-01-23 | July'22 | July'22
391.966
96 | 214/8 | DA+0 |  |  |  | 2021-05-06 |  |  |  | 2022-01-23 | 2022-01-30 | July'22 | July'22
410.206
97 | 214/9 | DB1+6 |  |  |  | 2021-05-06 |  |  |  | 2022-01-12 | 2022-01-24 | July'22 | July'22
390.468
98 | AP-215/0 | DB2+0 | RT 9° 53' 57" |  |  | 2021-05-06 | 2021-07-07 | WET |  | 2022-01-24 | 2022-01-31
|  |  |  | 424.47 | 2497.263
99 | 215/1 | DA+6 |  |  |  | 2021-05-06 | 2021-07-07 | WET |  | 2021-09-25 | 2021-10-13 | 2021-12-04 | 2021-12-13 | 2021-11-25 | 2021-11-25
415.008
100 | 215/2 | DA+0 |  |  |  | 2021-05-06 | 2021-07-07 | WET |  | 2021-11-16 | 2021-11-28 | 2021-12-29 | 2021-12-31
424.08
101 | 215/3 | DA+6 |  |  |  | 2021-05-06 | 2021-07-07 | WET |  | 2021-07-10 | 2021-08-06 | 2021-09-28 | 2021-10-05
414.462
102 | 215/4 | DA+3 |  |  |  | 2021-05-06 | 2021-07-07 | WET |  | 2021-07-04 | 2021-07-13 | 2021-09-14 | 2021-09-22 | 2021-09-06 | 2021-09-06
425.338
103 | 215/5 | DA+3 |  |  |  | 2021-05-06 | 2021-07-07 | WET |  | 2021-07-12 | 2021-07-26 | 2021-09-23 | 2021-09-27 | 2021-09-19 | 2021-09-20
393.905
104 | AP-216/0 | DC1+0 | LT 21° 58' 14" |  |  | 2021-04-17 | 2021-06-15 | WET |  | 2021-07-21 | 2021-09-29 | 2022-01-17 | 2022-01-26 |  |  |  |  | 2022-01-01 | 2022-01-12
|  |  |  | 406.918 | 2497.048
105 | 216/1 | DA+3 |  |  |  | 2021-04-17 | 2021-06-15 | WET |  | 2021-06-03 | 2021-06-15 | 2021-08-16 | 2021-08-24 | 2021-06-17 | 2021-06-17 |  |  | 2022-01-01 | 2022-01-12
414.645
106 | 216/2 | DA+0 |  |  |  | 2021-04-17 | 2021-06-15 | WET |  | 2021-06-03 | 2021-06-11 | 2021-08-08 | 2021-08-16 | 2021-06-22 | 2021-06-22 |  |  | 2022-01-01 | 2022-01-12
417.875
107 | 216/3 | DA+3 |  |  |  | 2021-04-17 | 2021-06-15 | PS |  | 2021-06-14 | 2021-06-22 | 2021-09-05 | 2021-09-10 | 2021-08-13 | 2021-08-13 |  |  | 2022-01-01 | 2022-01-12
419.143
108 | 216/4 | DA+0 |  |  |  | 2021-04-17 | 2021-06-15 | PS |  | 2021-06-22 | 2021-06-28 | 2021-10-05 | 2021-10-10 | 2021-08-13 | 2021-08-13 |  |  | 2022-01-01 | 2022-01-12
417.351
109 | 216/5 | DA+3 |  |  |  | 2021-04-17 | 2021-06-15 | WET |  | 2021-07-29 | 2021-07-10 | 2021-08-16 | 2021-08-31 | 2021-08-13 | 2021-08-13 |  |  | 2022-01-01 | 2022-01-12
421.116
110 | 216/6 | DB1+0 |  |  |  | 2021-04-17 | 2021-06-15 | PS |  | 2021-07-10 | 2021-07-26 | 2021-09-23 | 2021-09-30 | 2021-08-28 | 2021-08-28 |  |  | 2022-01-01 | 2022-01-12
|  |  |  | 399.739 | 2833.151
111 | 216/7 | DA+3 |  |  |  | 2021-04-17 | 2021-06-15 | FS |  | 2021-08-21 | 2021-08-31 | 2021-09-18 | 2021-09-22 | 2021-09-03 | 2021-09-03
389.486
112 | 216/8 | DA+0 |  |  |  | 2021-04-17 | 2021-06-15 | WET |  | 2021-06-17 | 2021-06-29 | 2021-09-13 | 2021-09-17 | 2021-07-05 | 2021-07-05
390.991
113 | 216/9 | DA+0 |  |  |  | 2021-04-17 | 2021-06-15 | PS |  | 2021-07-27 | 2021-08-11 | 2021-09-06 | 2021-09-12 | 2021-08-11 | 2021-08-11
406.572
114 | 216/10 | DA+0 |  |  |  | 2021-04-17 | 2021-06-15 | FS |  | 2021-10-27 | 2021-11-14 | 2021-12-10 | 2021-12-20 | 2021-11-30 | 2021-11-30
409.71
115 | 216/11 | DA+3 |  |  |  | 2021-04-17 | 2021-06-15 | FS |  | 2021-11-05 | 2021-11-24 | 2021-12-17 | 2021-12-26 | 2021-11-30 | 2021-11-30
419.068
116 | 216/12 | DA+3 |  |  |  | 2021-04-17 | 2021-06-15 | FS |  | 2021-06-11 | 2021-07-04 | 2021-11-08 | 2021-11-18 | 2021-07-11 | 2021-07-11
417.585
117 | AP-217/0 | DD60+6 | RT 0° 51' 48" |  |  | 2021-04-17 | 2021-06-15 | FS |  | 2021-11-27 | 2021-12-15 | 2021-12-25 | 2021-12-31
|  |  |  | 237.756 | 237.756
118 | AP-218/0 | DD60+3 | LT 23° 26' 54" |  |  | 2021-04-17 | 2021-06-15 | FS |  | 2021-10-28 | 2021-11-29 | 2021-12-25 | 2021-12-30 | 2021-11-27 | 2021-11-27 |  |  | 2022-01-12 | 2022-01-23
|  |  |  | 389.414 | 2020.591
119 | 218/1 | DA+0 |  |  |  | 2021-04-17 | 2021-06-15 | WET |  | 2021-06-11 | 2021-06-21 | 2021-11-08 | 2021-11-16 | 2021-12-06 | 2021-12-06 |  |  | 2022-01-12 | 2022-01-23
410
120 | 218/2 | DA+3 |  |  |  | 2021-04-17 | 2021-06-15 | PS |  | 2021-06-22 | 2021-06-27 | 2021-11-19 | 2021-11-24 | 2021-07-07 | 2021-07-07 |  |  | 2022-01-12 | 2022-01-23
410
121 | 218/3 | DA+0 |  |  |  | 2021-04-17 | 2021-06-15 | PS |  | 2021-06-27 | 2021-07-04 | 2021-10-16 | 2021-10-31 | 2021-07-07 | 2021-07-07 |  |  | 2022-01-12 | 2022-01-23
410
122 | 218/4 | DA+3 |  |  |  | 2021-04-17 | 2021-06-15 | PS |  | 2021-07-05 | 2021-07-15 | 2022-01-26 | 2022-01-31 | 2021-07-18 | 2021-07-18 |  |  | 2022-01-12 | 2022-01-23
401.177
123 | AP-219/0 | DB2+0 | RT 9° 35' 15" |  |  | 2021-04-17 | 2021-06-15 | WET |  | 2021-07-21 | 2021-08-31 | 2021-10-01 | 2021-10-05 | 2021-12-28 | 2021-12-28 |  |  | 2022-01-23 | 2022-01-31
|  |  |  | 373.008 | 1084.941
124 | 219/1 | DA+0 |  |  |  | 2021-04-17 | 2021-08-05 | FS |  | 2021-11-17 | 2021-12-16 | 2021-12-27 | 2021-12-31 | 2021-12-27 | 2021-12-27 |  |  | 2022-01-23 | 2022-01-31
378.87
125 | 219/2 | DA+0 |  |  |  | 2021-04-17 | 2021-08-05 | FS |  | 2021-11-28 | 2021-12-07 | 2021-12-27 | 2021-12-31 | 2021-12-27 | 2021-12-27 |  |  | 2022-01-23 | 2022-01-31
333.063
126 | AP-220/0 | DB2+0 | LT 14° 26' 15" |  |  | 2021-04-17 | 2021-08-05 | FS |  | 2021-10-28 | 2021-11-08 | 2021-11-25 | 2021-12-07 | 2021-11-20 | 2021-11-21 |  |  | 2022-01-23 | 2022-01-31
|  |  |  | 405.779 | 827.278
127 | 220/1 | DA+3 |  |  |  | 2021-04-17 | 2021-11-10 | PS |  | 2021-12-05 | 2021-12-13 | 2022-01-12 | 2022-01-19 | 2021-12-28 | 2021-12-28
421.499
128 | AP-221/0 | DD60+3 | RT 10° 5' 27" |  |  | 2021-04-17 | 2021-11-10 | FS |  | July'22 | July'22
|  |  |  | 239.927 | 239.927
129 | AP-222/0 | DD60+3 | RT 8° 20' 1" |  |  | 2021-04-17 | 2021-11-10 | FS |  | July'22 | July'22
|  |  |  | 195.923 | 195.923
130 | AP-223/0 | DD60+3 | LT 6° 24' 29" |  |  | 2021-04-17 | 2021-11-10 | FS |  | July'22 | July'22
|  |  |  | 239.908 | 239.908
131 | AP-224/0 | DD60+3 | RT 1° 25' 38" |  |  | 2021-04-17 | 2021-05-05 | FS |  | July'22 | July'22
|  |  |  | 448.372 | 448.372
132 | 224A/1 | DA+0 |  |  |  | 2021-04-17 | 2021-05-05 |  |  | 2022-01-01 | 2022-01-12
|  |  |  | 452.352 | 2326.949
133 | 224A/2 | DA+0 |  |  |  | 2021-04-17 | 2021-05-05 |  |  | 2022-01-12 | 2022-01-19
379.722
134 | 224A/3 | DA+0 |  |  |  | 2021-04-17 | 2021-05-05 |  |  | 2022-01-19 | 2022-01-26
365.961
135 | 224A/4 | DA+0 |  |  |  | 2021-04-17 | 2021-05-05 |  |  | 2022-01-26 | 2022-01-31
370.132
136 | 224A/5 | DA+0 |  |  |  | 2021-04-17 | 2021-05-05 |  |  | 2022-01-12 | 2022-01-19
375.345
137 | 224/6 | DA+0 |  |  |  | 2021-04-17 | 2021-05-05
383.437
138 | AP-225/0 | DB2+3 | RT 11° 17' 47" |  |  | 2021-04-17 | 2021-05-05 | FS |  | 2021-12-26 | 2021-12-31
|  |  |  | 411.944 | 3320.723
139 | 225/1 | DA+0 |  |  |  | 2021-04-17 | 2021-05-05 | WET |  | 2022-01-19 | 2022-01-26
409.69
140 | 225/2 | DA+3 |  |  |  | 2021-04-17 | 2021-05-05 | WET |  | 2021-05-24 | 2021-06-03 | 2022-01-19 | 2022-01-24 | 2021-06-09 | 2021-06-09
412.908
141 | 225/3 | DA+0 |  |  |  | 2021-04-17 | 2021-05-05 | WET |  | 2022-01-26 | 2022-01-31
414.411
142 | 225/4 | DA+3 |  |  |  | 2021-04-17 | 2021-05-05 | WET |  | 2022-01-12 | 2022-01-19
420.733
143 | 225/5 | DA+3 |  |  |  | 2021-04-17 | 2021-05-05 | WET |  | 2021-05-24 | 2021-05-31 | 2022-01-24 | 2022-01-31 | 2021-11-25 | 2021-11-25
413.981
144 | 225/6 | DA+0 |  |  |  | 2021-04-17 | 2021-05-05 |  |  | 2022-01-19 | 2022-01-26
424.91
145 | 225/7 | DA+3 |  |  |  | 2021-04-17 | 2021-05-05 | WET |  | July'22 | July'22
412.146
146 | AP-226/0 | DB2+0 | LT 11° 19' 59" |  |  | 2021-04-17 | 2021-05-05 |  |  | 2022-01-12 | 2022-01-19
|  |  |  | 419.811 | 4992.051
147 | 226/1 | DA+3 |  |  |  | 2021-04-17 | 2021-08-05 |  |  | 2022-01-19 | 2022-01-26
418.081
148 | 226/2 | DA+0 |  |  |  | 2021-04-17 | 2021-08-05 | ps |  | July'22 | July'22
415.898
149 | 226/3 | DA+3 |  |  |  | 2021-04-17 | 2021-08-05 |  |  | 2022-01-19 | 2022-01-26
416.232
150 | 226/4 | DA+0 |  |  |  | 2021-04-17 | 2021-08-05 |  |  | 2022-01-26 | 2022-01-31
403.469
151 | 226/5 | DA+6 |  |  |  | 2021-04-17 | 2021-08-05
426.249
152 | 226/6 | DA+0 |  |  |  | 2021-04-17 | 2021-08-05
392.785
153 | 226/7 | DB2+0 |  |  |  | 2021-04-17 | 2021-08-05 | PS |  | July'22 | July'22
428.759
154 | 226/8 | DA+6 |  |  |  | 2021-04-17 | 2021-08-05 | PS |  | July'22 | July'22
410.022
155 | 226/9 | DA+0 |  |  |  | 2021-04-17 | 2021-08-05
427.775
156 | 226/10 | DA+6 |  |  |  | 2021-04-17 | 2021-08-05
411.2
157 | 226/11 | DA+6 |  |  |  | 2021-04-17 | 2021-08-05
421.77
158 | AP-227/0 | DC1+3 | RT 17° 38' 14" |  |  | 2021-06-10 | 2021-08-05 | PS |  | July'22 | July'22 | July'22 | July'22
|  |  |  | 374.914 | 1495.218
159 | 227/1 | DA+3 |  |  |  | 2021-06-10 |  |  |  | 2022-01-12 | 2022-01-19 | July'22 | July'22
342.978
160 | 227/2 | DA+0 |  |  |  | 2021-06-10 |  | FS |  | 2021-12-20 | 2021-12-31 | 2022-01-12 | 2022-01-19
368.14
161 | 227/3 | DA+9 |  |  |  | 2021-06-10 |  | FS |  | 2021-12-21 | 2021-12-28 | July'22 | July'22
409.186
162 | AP-228/0 | DD60+25 | RT 3° 6' 5" |  |  | 2021-06-10 |  |  |  | 2021-12-17 | 2022-01-30 | July'22 | July'22
|  |  |  | 591.008 | 591
163 | AP-229/0 | DD60+25 | LT 0° 34' 29" |  |  | 2021-06-10 | 2021-09-10
|  |  |  | 404.958 | 4889.416
164 | 229/1 | DA+9 |  |  |  | 2021-06-10 | 2021-09-10 | WET |  | 2021-12-17 | 2021-12-30 | July'22 | #VALUE!
420.781
165 | 229/2 | DA+0 |  |  |  | 2021-06-10 | 2021-09-10 | WET |  | 2021-11-20 | 2021-12-03 | 2021-12-18 | 2021-12-27 | 2021-12-08 | 2021-12-08
389.483
166 | 229/3 | DA+3 |  |  |  | 2021-06-10 | 2021-09-10 | WET |  | 2021-10-21 | 2021-10-24 | 2021-11-10 | 2021-11-15 | 2021-11-25 | 2021-11-25
419.493
167 | 229/4 | DA+3 |  |  |  | 2021-06-10 | 2021-09-10 | WET |  | 2021-11-01 | 2021-11-21 | 2021-12-27 | 2021-12-30 | 2021-12-05 | 2021-12-05
407.895
168 | 229/5 | DA+0 |  |  |  | 2021-06-10 | 2021-09-10 | WET |  | 2021-10-11 | 2021-10-26 | 2021-11-19 | 2021-11-24 | 2021-11-20 | 2021-11-21
412.932
169 | 229/6 | DA+3 |  |  |  | 2021-06-10 | 2021-09-10 | WET |  | 2021-09-15 | 2021-09-20 | 2022-01-12 | 2022-01-17 | 2021-10-04 | 2021-10-04
380.209
170 | 229/7 | DA+3 |  |  |  | 2021-06-10 | 2021-09-10 | WET |  | 2021-09-27 | 2021-09-30 | 2021-11-05 | 2021-11-10 | 2021-10-04 | 2021-10-04
406.23
171 | 229/8 | DA+0 |  |  |  | 2021-06-10 | 2021-09-10 | WET |  | 2021-09-21 | 2021-09-27 | 2021-10-13 | 2021-10-19 | 2021-10-27 | 2021-10-27
403.861
172 | 229/9 | DA+0 |  |  |  | 2021-06-10 | 2021-09-10 | WET |  | 2021-09-27 | 2021-10-05 | 2021-10-25 | 2021-10-31 | 2021-10-27 | 2021-10-27
404.445
173 | 229/10 | DA+3 |  |  |  | 2021-06-10 | 2021-09-10 | WET-PADDY |  | 2021-09-10 | 2021-09-26 | 2021-10-19 | 2021-10-24 | 2021-11-18 | 2021-11-19
407.215
174 | 229/11 | DA+0 |  |  |  | 2021-06-10 | 2021-09-10 | WET |  | 2021-10-03 | 2021-10-10 | 2021-11-01 | 2021-11-08 | 2021-10-27 | 2021-10-27
431.914
175 | AP-230/0 | DD60+18 | LT 45° 26' 6" |  |  | 2021-06-10 | 2021-09-10 | WET |  | 2021-10-07 | 2021-10-23 |  |  | 2021-11-18 | 2021-11-19
|  |  |  | 239.804 | 239.804
176 | AP-231/0 | DD60+18 | RT 48° 42' 59" |  |  | 2021-06-10 | 2021-04-20 | WET |  | 2021-10-05 | 2021-10-26 |  |  | 2021-11-18 | 2021-11-19 |  |  | 2021-12-10 | 2021-12-31
|  |  |  | 412.153 | 2488.301
177 | 231/1 | DA+3 |  |  |  | 2021-04-17 | 2021-04-20 | WET |  | 2021-05-24 | 2021-05-31 | 2021-10-03 | 2021-10-10 | 2021-06-22 | 2021-06-22 |  |  | 2021-12-10 | 2021-12-31
426.626
178 | 231/2 | DA+3 |  |  |  | 2021-04-17 | 2021-04-20 | DRY |  | 2021-05-10 | 2021-05-15 | 2021-07-20 | 2021-07-30 | 2021-11-20 | 2021-11-21 |  |  | 2021-12-10 | 2021-12-31
413.16
179 | 231/3 | DA+6 |  |  |  | 2021-04-17 | 2021-04-20 | DRY |  | 2021-04-24 | 2021-05-01 | 2021-07-24 | 2021-08-05 | 2021-09-30 | 2021-09-30 |  |  | 2021-12-10 | 2021-12-31
423.2
180 | 231/4 | DA+0 |  |  |  | 2021-04-17 | 2021-04-20 | DRY |  | 2021-04-30 | 2021-05-05 | 2021-07-06 | 2021-07-11 | 2021-09-30 | 2021-09-30 |  |  | 2021-12-10 | 2021-12-31
404.01
181 | 231/5 | DA+3 |  |  |  | 2021-04-17 | 2021-04-20 | DRY |  | 2021-05-05 | 2021-05-11 | 2021-07-10 | 2021-07-20 | 2021-11-20 | 2021-09-30 |  |  | 2021-12-10 | 2021-12-31
409.152
182 | AP-232/0 | DC1+0 | LT 16° 14' 12" |  |  | 2021-04-17 | 2021-04-20 | WET |  | 2021-07-10 | 2021-08-31 | 2021-11-21 | 2021-11-29 | 2021-09-10 | 2021-09-10 |  |  | 2021-11-30 | 2021-12-13
|  |  |  | 420.714 | 3294.972
183 | 232/1 | DA+6 |  |  |  | 2021-04-17 | 2021-04-20 | DRY |  | 2021-05-17 | 2021-05-27 | 2021-08-17 | 2021-08-29 | 2021-09-30 | 2021-09-30 |  |  | 2021-11-30 | 2021-12-13
418.98
184 | 232/2 | DA+0 |  |  |  | 2021-04-17 | 2021-04-20 | DRY |  | 2021-05-26 | 2021-06-12 | 2021-07-20 | 2021-07-31 | 2021-06-15 | 2021-06-15 |  |  | 2021-11-30 | 2021-12-13
368.189
185 | 232/3 | DA+3 |  |  |  | 2021-04-17 | 2021-04-20 | DRY |  | 2021-05-24 | 2021-06-03 | 2021-08-01 | 2021-08-13 | 2021-09-10 | 2021-09-10 |  |  | 2021-11-30 | 2021-12-13
439.262
186 | 232/4 | DA+3 |  |  |  | 2021-04-17 | 2021-04-20 | DRY |  | 2021-06-26 | 2021-07-06 | 2021-08-09 | 2021-08-22 | 2021-09-10 | 2021-09-10 |  |  | 2021-11-30 | 2021-12-13
392.228
187 | 232/5 | DA+3 |  |  |  | 2021-04-17 | 2021-04-20 | DRY |  | 2021-05-29 | 2021-06-04 | 2021-10-11 | 2021-10-15 | 2021-09-13 | 2021-09-13 |  |  | 2021-11-30 | 2021-12-13
425.66
188 | 232/6 | DA+3 |  |  |  | 2021-04-17 | 2021-04-20 | DRY |  | 2021-06-04 | 2021-06-11 | 2021-08-29 | 2021-09-06 | 2021-09-30 | 2021-09-30 |  |  | 2021-11-30 | 2021-12-13
413.102
189 | 232/7 | DA+3 |  |  |  | 2021-04-17 | 2021-04-20 | DRY |  | 2021-06-03 | 2021-06-22 | 2021-09-24 | 2021-09-30 | 26-06-201 | 2021-06-26 |  |  | 2021-11-30 | 2021-12-13
416.837
190 | AP-233/0 | DD60+0 | LT 12° 38' 53" |  |  | 2021-04-17 | 2021-04-20 | WET |  | 2021-10-06 | 2021-10-10 | 2021-10-26 | 2021-10-31 | 2021-10-23 | 2021-10-24 |  |  | 2021-11-30 | 2021-12-13
|  |  |  | 240.759 | 240.759
191 | AP-234/0 | DD60+0 | RT 5° 54' 51" |  |  |  |  | WET |  | 2021-10-12 | 2021-10-31 | 2021-11-30 | 2021-12-10 | 2021-12-07 | 2021-12-07
|  |  |  | 417.081 | 4916.842 | 2021-05-31 | 2021-06-15
192 | 234/1 | DA+3 | [5 empty] | WET |  | 2021-06-03 | 2021-06-11 | 2021-09-07 | 2021-09-13 | 2021-10-06 | 2021-10-07
|  |  |  | 417.327 |  | 2021-05-31 | 2021-06-15
193 | 234/2 | DA+3 | [5 empty] | WET |  | 2021-07-15 | 2021-07-26 | 2021-09-15 | 2021-09-23
|  |  |  | 418.106 |  | 2021-05-31 | 2021-06-15
194 | 234/3 | DA+0 | [5 empty] | WET |  | 2021-06-17 | 2021-06-22 | 2022-01-17 | 2022-01-22 | 2021-10-06 | 2021-10-07
|  |  |  | 419.903 |  | 2021-05-31 | 2021-06-15
195 | 234/4 | DA+0 | [5 empty] | WET |  | 2021-06-10 | 2021-06-17 | 2021-08-19 | 2021-08-27
|  |  |  | 415.966 |  | 2021-05-31 | 2021-06-15
196 | 234/5 | DA+6 | [5 empty] | WET |  | 2021-06-20 | 2021-06-27 | 2021-10-16 | 2021-10-23 | 2021-10-06 | 2021-10-07
|  |  |  | 417.766 |  | 2021-05-31 | 2021-06-15
197 | 234/6 | DA+0 | [5 empty] | WET |  | 2021-07-04 | 2021-07-13 | 2021-08-13 | 2021-08-20
|  |  |  | 421.039 |  | 2021-05-31 | 2021-06-15
198 | 234/7 | DA+3 | [5 empty] | WET |  | 2021-06-27 | 2021-06-30 | 2021-08-05 | 2021-08-13 | 2021-10-06 | 2021-10-07
|  |  |  | 387.769 |  | 2021-05-31 | 2021-06-15
199 | 234/8 | DA+0 | [5 empty] | WET |  | 2021-06-28 | 2021-07-05 | 2021-08-26 | 2021-09-03 | 2021-10-06 | 2021-10-07
|  |  |  | 449.976 |  | 2021-05-31 | 2021-06-15
200 | 234/9 | DA+9 | [5 empty] | WET |  | 2021-06-27 | 2021-07-07 | 2021-09-06 | 2021-09-18 | 2021-10-27 | 2021-10-27
|  |  |  | 388.975 |  | 2021-05-31 | 2021-06-15
201 | 234/10 | DA+3 | [5 empty] | DRY |  | 2021-06-20 | 2021-06-29 | 2021-11-05 | 2021-11-12 | 2021-07-04 | 2021-07-04
|  |  |  | 423.942 |  | 2021-05-31 | 2021-06-15
202 | 234/11 | DA+0 | [5 empty] | DRY |  | 2021-06-17 | 2021-06-26 | 2021-10-25 | 2021-10-31 | 2021-06-30 | 2021-06-30
|  |  |  | 338.992 |  | 2021-05-31 | 2021-06-15
203 | AP-235/0 | DD60+9 | LT 13° 36' 10" |  |  |  |  | WET |  | 2021-11-17 | 2021-12-14 | 2022-01-22 | 2022-01-31
|  |  |  | 242.528 | 242.528 | 2021-05-31 | 2021-07-15
204 | AP-236/0 | DD60+9 | RT 2° 28' 33" |  |  |  |  | WET |  | 2021-10-27 | 2021-12-28 | 2022-01-19 | 2022-01-31
|  |  |  | 425.318 | 1648.628 | 2021-05-31 | 2021-07-15
205 | 236/1 | DA+0 | [5 empty] | WET |  | 2021-06-14 | 2021-06-24 | 2021-10-19 | 2021-10-24 | 2021-06-30 | 2021-06-30
|  |  |  | 391.053 |  | 2021-05-31 | 2021-07-15
206 | 236/2 | DA+0 | [5 empty] | DRY |  | 2021-06-20 | 2021-06-29 | 2021-09-19 | 2021-09-28 | 2021-07-02 | 2021-07-02
|  |  |  | 393.492 |  | 2021-05-31 | 2021-07-15
207 | 236/3 | DA+3 | [5 empty] | WET |  | 2021-10-06 | 2021-10-11 | July'22 | July'22 | 2021-10-23 | 2021-10-24
|  |  |  | 438.765 |  | 2021-05-31 | 2021-07-15
208 | AP-237/0 | DD60+25 | LT 6° 10' 33" |  |  |  |  | WET |  | 2021-10-12 | 2021-10-31 | July'22 | July'22 | 2021-11-25 | 2021-11-25
|  |  |  | 250.332 | 250.332 | 2021-05-31 | 2021-07-15
209 | AP-238/0 | DD60+25 | RT 42° 22' 40" |  |  |  |  | WET |  | 2021-11-01 | 2021-11-20 |  |  | 2021-11-27 | 2021-11-27
|  |  |  | 419.933 | 1102.655 | 2021-05-31 | 2021-07-15
210 | 238/1 | DA+3 | [5 empty] | WET |  | 2021-07-07 | 2021-07-14 | 2021-11-11 | 2021-11-15 | 2021-09-27 | 2021-09-27
|  |  |  | 278.679 |  | 2021-05-31 | 2021-07-15
211 | 238/2 | DA+0 | [5 empty] | WET |  | 2021-07-02 | 2021-07-10 | 2021-11-17 | 2021-11-21 | 2021-07-15 | 2021-07-15
|  |  |  | 404.043 |  | 2021-05-31 | 2021-07-15
212 | AP-239/0 | DD60+18 | LT 15° 59' 39" |  |  |  |  | WET |  | 2021-11-01 | 2021-11-20 | July'22 | July'22 | 2021-11-25 | 2021-11-25
|  |  |  | 233.384 | 233.384 | 2021-05-31 | 2021-07-15
213 | AP-240/0 | DD60+25 | RT 18° 8' 12" | [6 empty] | 2022-01-11 | 2022-01-31 | July'22 | July'22
|  |  |  | 342.001 | 342.001 | 2021-05-31 | 2021-09-10
214 | AP-241/0 | DD60+6 | LT 48° 57' 31" |  |  |  |  | WET |  | 2021-09-09 | 2021-09-30 | 2021-12-05 | 2021-12-14 | 2021-10-10 | 2021-10-10
|  |  |  | 235.274 | 235.274 | 2021-05-31 | 2021-09-10
215 | AP-242/0 | DD60+9 | RT 45° 0' 27" |  |  |  |  | WET |  | 2021-09-09 | 2021-09-30 | 2021-11-26 | 2021-12-03 | 2021-10-23 | 2021-10-24
|  |  |  | 500.09 | 500.09 | 2021-05-31 | 2021-09-10
216 | AP-243/0 | DD45+12 | LT 36° 12' 37" |  |  |  |  | WET |  | 2021-10-12 | 2021-10-24 |  |  | 2021-11-20 | 2021-11-21
|  |  |  | 380.723 | 1220.349 | 2021-05-31 | 2021-09-10
217 | 243/1 | DA+0 | [5 empty] | WET |  | 2021-10-04 | 2021-10-15 | 2021-12-15 | 2021-12-21 | 2021-11-20 | 2021-11-21
|  |  |  | 418.035 |  | 2021-05-31 | 2021-09-10
218 | 243/2 | DA+3 | [5 empty] | WET |  | 2021-10-03 | 2021-10-23 | 2021-11-16 | 2021-11-21 | 2021-11-20 | 2021-11-21
|  |  |  | 421.591 |  | 2021-05-31 | 2021-09-10
219 | 243/3 | DB1+3 | [5 empty] | WET |  | 2021-12-17 | 2021-12-30
|  |  |  | 416.483 | 416.483 | 2021-05-31 | 2021-09-10
220 | AP-244/0 | DD60(Aux)+3 | LT 93° 2' 19"
|  |  |  | 130.011 | 130.011 | 2021-05-31 | 2021-09-10
221 | Gantry | Gantry
|  |  |  | 83587.359 | 83587.492
Formulas:
Completion = [Tower erection dates]+7
Completion = [Foundation dates]+7
Tower erection dates = [Completion]-8

## Supply DPR (hidden)
KEC International Limited
Name of Line: 765 kV D/C Bikaner IV PS to Siwani II (Part-01) TL | [7 empty] | 2026-05-20
STORE :- 1: Kosi Kalan, Uttar Pradesh, 2: Hodal, Haryana
STUBS & TOWER PARTS (RECEIVED) | [14 empty] | 2026-05-20
SL NO | DESCRIPTION | UNIT | Total LOA Qty. | Cumulative Qty. as per Check Survey | Cumulative Released for Supply | Unit | RECEIVED Qty. |  | TOTAL RECEIVED | Total Received | Issued From Store | Consumed | Balance at Store | Balance Req. from Plant | Remarks
[7 empty] | HT | MS
STUBS
A | DA-TYPE
1 | DA TYPE NORMAL STUB | Sets | 153 |  | 100 |  |  |  |  | 100 | 59 | 56 | 41
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
B | DB-TYPE | [8 empty] | 10 | 3 | 2 | 7
1 | DB1 TYPE NORMAL STUB(Up to +9 M Extension) | Sets | 18 |  | 5 | [8 empty] | 0
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
1 | DB1 TYPE NORMAL STUB( +18 M to +25 M Extension) | Sets | 2 | [10 empty] | 0
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
1 | DB2 TYPE NORMAL STUB(Up to +9 M Extension) | Sets | 4 | 2 | [9 empty] | 2
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
1 | DB2 TYPE NORMAL STUB( +18 M to +25 M Extension) | Sets | [11 empty] | 0
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
C | DC-TYPE | [12 empty] | 0
1 | DC1 TYPE NORMAL STUB(Up to +9 M Extension) | Sets | 10 | 1 | 5 | [5 empty] | 3 | 1 |  | 1
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
1 | DC1 TYPE NORMAL STUB( +18 M to +25 M Extension) | Sets | [11 empty] | 0
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
1 | DC2 TYPE NORMAL STUB(Up to +9 M Extension) | Sets | 5 | [10 empty] | 0
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
1 | DC2 TYPE NORMAL STUB( +18 M to +25 M Extension) | Sets | [11 empty] | 0
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
D | DD-TYPE | [12 empty] | 0
1 | DD45 TYPE NORMAL STUB(Up to +9 M Extension) | Sets | 8 |  | 5 | [5 empty] | 1 |  |  | 0
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
1 | DD45 TYPE NORMAL STUB(+18/25 Extension) | Sets | [11 empty] | 0
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
1 | DD60 TYPE NORMAL STUB(Up to +9 M Extension) | Sets | 14 | 1 | [9 empty] | 1
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
1 | DD60 (+18/25) NORMAL STUB | Sets | 16 | [10 empty] | 0
2 | +1M RC STUB | Nos. | [11 empty] | 0
3 | .+1.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
4 | .+2.5 M RC Stub Extenssion | Nos. | [11 empty] | 0
5 | .+3 M RC Stub Extenssion | Nos. | [11 empty] | 0
0
1 | DD60+30M NORMAL STUB | Nos. | 2 | [10 empty] | 0
2 | DD60+35M NORMAL STUB | Nos. | [11 empty] | 0
TOWER PARTS
A | DA TYPE |  | 153
1 | BASIC BODY | Nos. | 153 | 19 | 132 | [5 empty] | 2 | 1 | 130
2 | -6M EXTENSION ONLY | Nos.
3 | -4.5M EXTENSION ONLY | Nos.
4 | -3M EXTENSION ONLY | Nos.
5 | -1.5M EXTENSION ONLY | Nos.
6 | 0M EXTENSION ONLY | Nos. | 108 |  | 72 | [5 empty] | 2 | 1 | 70
7 | +1.5M EXTENSION ONLY | Nos.
8 | +3M EXTENSION ONLY | Nos. | 37 |  | 43
9 | +4.5M EXTENSION ONLY | Nos.
10 | +6M EXTENSION ONLY | Nos. | 4 |  | 14
11 | +9M EXTENSION ONLY | Nos. | 4 |  | 3
12 | Plan at -3M Level | Nos.
B | DB - TYPE |  | 24
i | DB1 TYPE |  |  | 2
1 | BASIC BODY | Nos. |  |  | 9
2 | -3M EXTENSION ONLY | Nos.
3 | +0M EXTENSION ONLY | Nos. | 12 |  | 6
4 | +3M EXTENSION ONLY | Nos. |  |  | 1
5 | +6M EXTENSION ONLY | Nos. |  |  | 2
6 | +9M EXTENSION ONLY | Nos. | 6
7 | EXTENSION ONLY | Nos. | 2
ii | DB2 TYPE
1 | BASIC BODY | Nos.
2 | -3M EXTENSION ONLY | Nos.
3 | +0M EXTENSION ONLY | Nos.
4 | +3M EXTENSION ONLY | Nos.
5 | +6M EXTENSION ONLY | Nos.
6 | +9M EXTENSION ONLY | Nos.
7 | Plan at -3M Level | Nos.
C | DC - TYPE |  | 15
i | DC1 TYPE |  | 10 | 1 | 4
1 | BASIC BODY | Nos.
2 | -3M EXTENSION ONLY | Nos.
3 | +0M EXTENSION ONLY | Nos. | 7 |  | 3
4 | +3M EXTENSION ONLY | Nos. |  |  | 1
5 | +6M EXTENSION ONLY | Nos. | 1
6 | +9M EXTENSION ONLY | Nos.
7 | .+18M EXTENSION ONLY | Nos. | 2
ii | DC2 TYPE |  | 5
1 | BASIC BODY | Nos.
2 | -3M EXTENSION ONLY | Nos.
3 | +0M EXTENSION ONLY | Nos. | 3
4 | +3M EXTENSION ONLY | Nos. | 1
5 | +6M EXTENSION ONLY | Nos. | 1
6 | +9M EXTENSION ONLY | Nos.
7 | Plan at -3M Level | Nos.
D | DD - TYPE |  | 40
i | DD45 TYPE
1 | BASIC BODY | Nos. |  |  | 13
2 | -3M EXTENSION ONLY | Nos.
3 | +0M EXTENSION ONLY | Nos. | 8
4 | +3M EXTENSION ONLY | Nos.
5 | +6M EXTENSION ONLY | Nos.
6 | +9M EXTENSION ONLY | Nos.
7 | +18M EXTENSION ONLY | Nos.
8 | +25M EXTENSION ONLY | Nos.
9 | Plan at -3M Level | Nos.
ii | DD60 TYPE
1 | BASIC BODY | Nos.
2 | +0M EXTENSION ONLY | Nos. | 3
3 | -3M EXTENSION ONLY | Nos.
4 | +3M EXTENSION ONLY | Nos. | 2
5 | +6M EXTENSION ONLY | Nos. | 8
6 | +9M EXTENSION ONLY | Nos. | 1
7 | +18M EXTENSION ONLY | Nos. | 8
8 | +25M EXTENSION ONLY | Nos. | 8
9 | +30M EXTENSION ONLY | Nos. | 2
10 | Plan at -3M Level | Nos.

## Power line Crossings (hidden)
DETAILS OF POWER LINE CROSSING
Sr. No. | Crossing Location |  | Crossing Span | Details of crossing | Owner | Status of proposal |  | Foundation | [5 empty] | Erection |  |  |  |  | Stringing | [5 empty] | Remarks/Critical Needs
[8 empty] | Target |  | Requirement |  |  |  | Target |  | Material Availability |  |  | Target |  | Material Availability
| From | To |  |  |  | Submission | Approval | Start | End | Stub | Steel | Cement | Gang | Start | End | Tower | BNA | Gang | Start | End | Conductor | Insulator | H/ware | Gang
1 | AP 187 | AP 188 | 241 | 66kV D/C
2 | AP 189 | AP 190 | 239 | 220kV D/C
3 | AP 191 | AP 192 | 236 | 220kV S/C
4 | AP 193 | AP 194 | 244 | 400kV S/C
5 | AP 195 | AP 196 | 240 | 220kV D/C
6 | AP 207 | 207/1 | 246 | 66kV S/C
7 | AP 210 | AP 211 | 206 | 400KV D/C AGR - BWE
8 | AP 213 | AP 214 | 555 | 765KV S/C AGR - JTK
9 | AP 217 | AP 218 | 238 | 400kV S/C
10 | AP 230 | AP 231 | 240 | 765 kV S/C
11 | AP 235 | AP 236 | 242 | 500HVDC LINE BLA - BWD
12 | AP 237 | AP 238 | 250 | 400KV D/C MNP - BCB
13 | AP 239 | AP 240 | 233 | 400KV D/C KNP - BCB
14 | AP 241 | AP 242 | 235 | 400KV S/C KNP - BCB

## Hardware (hidden)
400KV DC Khetri Sikar Transmission Line
Hardware and Conductor Supply and Consumption | [5 empty] | 2026-05-20
Sl.No. | Name of the Item | Unit | Required Qty. | Receipt Qty. | Balance Required Qty. | Consumed | Balance
1 | Insulators
| 120KN Long rod | No's | 648 | 812 | -164 | 540 | 170
| 160KN Long rod | No's | 2400 | 2397 | 3 | 1596 | 801
| 120KN Pilot | No's | 129 |  | 129 | 102 | 102
2 | Conductor (AL59 Moose) | KM | 946.3538 | 946.208 | 0.14584 | 806.676 | 139.532
3 | Hardware for Conductor
| Single "I" Suspension fittings | Set | 648 | 648 | 0 | 534 | 114
| DT fittings | Set | 1200 | 1200 | 0 | 786 | 414
| Single "I" Pilot fittings | Set | 129 | 129 | 0 | 102 | 27
| VD for Moose Conductor | No's | 8964 | 8964 | 0 | 6552 | 2412
| Twin Rigid Spacer | No's | 1770 | 1668 | 102 | 975 | 693
| Twin Bundle Spacer | No's | 7554 | 7552 | 2 | 5718 | 1834
| MSJ for Conductor | No's | 336 | 336 | 0 | 249 | 87
| Repaire Sleeve | No's | 112 | 112 | 0 | 27 | 85
4 | Earthwire | KM | 78.082 | 80 | -1.918 | 67.223 | 12.777
5 | Hardware for Earthwire
| Suspension Clamp for Earthwire | No's | 108 | 108 | 0 | 87 | 21
| Tension Clamp for Earthwire | No's | 200 | 202 | -2 | 131 | 71
| VD for Earthwire | No's | 617 | 620 | -3 | 428 | 192
| MSJ for Eartwire | No's | 28 | 43 | -15 | 9 | 34
| Flexible AL Bond | No's | 306 | 306 | 0 | 213 | 93
6 | OPGW | KM | 81.733 | 81.733 | 0 | 36.715 | 45.018
| VD for OPGW | Set | 966 | 774 | 192 | 397 | 377
| Downlead Clamp Assembly | No's | 559 | 559 | 0 | 361 | 198
| Suspension Clamp Assembly | Set | 101 | 101 | 0 | 52 | 49
| Dead End Tension Clamp Assembly | Set | 2 | 2 | 0 |  | 2
| Tension fittings assemby for Joint box | Set | 8 | 8 | 0 | 4 | 4
| Tenssion fittings assembly for Pas Through | Set | 91 | 91 | 0 | 27 | 64
| Tension fittings assembly on Suspension tower | Set | 7 | 7 | 0 | 6 | 1
| Joint Boxes | Set | 17 | 17 | 0 | 4 | 13
7 | Accessories | [5 empty] | 0
| Number Plate | No's | 207 | 207 | 0 |  | 207
| Danger Plate | No's | 207 | 207 | 0 |  | 207
| Phase Plate - R | No's | 414 | 414 | 0 |  | 414
| Phase Plate - Y | No's | 414 | 414 | 0 |  | 414
| Phase Plate - B | No's | 414 | 414 | 0 |  | 414
| Circuit Plate -1 | No's | 207 | 207 | 0 |  | 207
| Circuit Plate -2 | No's | 207 | 207 | 0 |  | 207
| Bird Guard | Set | 648 | 648 | 0 |  | 648