## Delay Phase - Project
Delay Phase - Project
Project | Phase | Foundation Bucket Start % | Foundation Bucket End % | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Scope Total | Phase Foundations % of Scope | Phase Start Date | Phase End Date | Phase Duration Days | Monsoon Overlap | Monsoon Overlap Days | Monsoon Foundation Count | Source Type | Parser Modes | Coverage Status | Scope Source | Scope Report Date
TA 413 | 0-20 | 0 | 20 | 126 | 120 | 95.24 | 312 | 273.4833 | 438.1 | 0 | 6 | 632 | 19.94 | 2024-06-06 | 2024-10-25 | 142 | Yes | 117 | 97 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 413 | 20-40 | 20 | 40 | 126 | 124 | 98.41 | 193 | 180.3171 | 306 | 1 | 2 | 632 | 19.94 | 2024-10-25 | 2025-02-26 | 125 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 413 | 40-60 | 40 | 60 | 62 | 60 | 96.77 | 163 | 163.3559 | 220.8 | 1 | 2 | 632 | 9.81 | 2025-02-27 | 2026-03-05 | 372 | Yes | 122 | 6 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 414 | 0-20 | 0 | 20 | 70 | 61 | 87.14 | 344 | 351.4333 | 452.2 | 1 | 9 | 352 | 19.89 | 2024-05-15 | 2025-03-24 | 314 | Yes | 122 | 2 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 414 | 20-40 | 20 | 40 | 70 | 61 | 87.14 | 132 | 162.3279 | 301 | 0 | 9 | 352 | 19.89 | 2025-03-24 | 2025-11-27 | 249 | Yes | 122 | 6 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 414 | 40-60 | 40 | 60 | 71 | 53 | 74.65 | 54 | 59.5094 | 99.6 | 0 | 18 | 352 | 20.17 | 2025-11-27 | 2025-12-28 | 32 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 414 | 60-80 | 60 | 80 | 70 | 40 | 57.14 | 54 | 54.2308 | 82.8 | 1 | 30 | 352 | 19.89 | 2025-12-29 | 2026-02-25 | 59 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 414 | 80-100+ | 80 | 100 | 45 | 8 | 17.78 | 28.5 | 25.875 | 35 | 0 | 37 | 352 | 12.78 | 2026-03-01 | 2026-05-14 | 75 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 416 | 0-20 | 0 | 20 | 60 | 60 | 100 | 171 | 184.65 | 288.1 | 0 | 0 | 302 | 19.87 | 2024-04-24 | 2024-09-08 | 138 | Yes | 100 | 51 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 416 | 20-40 | 20 | 40 | 60 | 60 | 100 | 154 | 158.9833 | 244.6 | 0 | 0 | 302 | 19.87 | 2024-09-09 | 2024-10-22 | 44 | Yes | 22 | 21 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 416 | 40-60 | 40 | 60 | 61 | 61 | 100 | 118 | 123.1639 | 190 | 0 | 0 | 302 | 20.2 | 2024-10-24 | 2024-11-30 | 38 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 416 | 60-80 | 60 | 80 | 60 | 60 | 100 | 150.5 | 168.6167 | 287.2 | 0 | 0 | 302 | 19.87 | 2024-11-30 | 2025-01-26 | 58 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 416 | 80-100+ | 80 | 100 | 62 | 62 | 100 | 161.5 | 165.3065 | 258.8 | 0 | 0 | 302 | 20.53 | 2025-01-30 | 2025-12-05 | 310 | Yes | 122 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 418 | 0-20 | 0 | 20 | 25 | 24 | 96 | 167.5 | 168.0417 | 260.2 | 0 | 1 | 127 | 19.69 | 2024-01-07 | 2024-09-02 | 240 | Yes | 94 | 23 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 418 | 20-40 | 20 | 40 | 25 | 24 | 96 | 106.5 | 136.5 | 226 | 0 | 1 | 127 | 19.69 | 2024-09-05 | 2025-01-03 | 121 | Yes | 26 | 7 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 418 | 40-60 | 40 | 60 | 26 | 26 | 100 | 139.5 | 142.1538 | 244 | 0 | 0 | 127 | 20.47 | 2025-01-10 | 2025-04-15 | 96 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 418 | 60-80 | 60 | 80 | 25 | 25 | 100 | 97 | 107.48 | 213.6 | 0 | 0 | 127 | 19.69 | 2025-04-16 | 2025-06-24 | 70 | Yes | 24 | 16 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 418 | 80-100+ | 80 | 100 | 28 | 26 | 92.86 | 84 | 94.7308 | 176.5 | 0 | 2 | 127 | 22.05 | 2025-06-25 | 2026-02-11 | 232 | Yes | 98 | 15 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-17
TA 419 | 0-20 | 0 | 20 | 66 | 66 | 100 | 196 | 214.5231 | 370.4 | 1 | 0 | 330 | 20 | 2024-05-21 | 2024-10-11 | 144 | Yes | 122 | 53 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 419 | 20-40 | 20 | 40 | 66 | 63 | 95.45 | 235 | 214.2698 | 313.4 | 0 | 3 | 330 | 20 | 2024-10-14 | 2025-04-23 | 192 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 419 | 40-60 | 40 | 60 | 66 | 58 | 87.88 | 80 | 107.3684 | 210.8 | 1 | 8 | 330 | 20 | 2025-04-25 | 2025-12-10 | 230 | Yes | 122 | 20 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 419 | 60-80 | 60 | 80 | 66 | 29 | 43.94 | 40 | 59.5172 | 108.6 | 0 | 37 | 330 | 20 | 2025-12-10 | 2026-05-13 | 155 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 419 | 80-100+ | 80 | 100 | 4 | 0 | 0 |  |  |  | 0 | 4 | 330 | 1.21 | 2026-05-16 | 2026-05-17 | 2 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 421 | 0-20 | 0 | 20 | 61 | 61 | 100 | 110 | 131.3443 | 244 | 0 | 0 | 309 | 19.74 | 2024-01-02 | 2024-08-20 | 232 | Yes | 81 | 50 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 421 | 20-40 | 20 | 40 | 62 | 62 | 100 | 118.5 | 145.5323 | 310.9 | 0 | 0 | 309 | 20.06 | 2024-08-24 | 2024-12-09 | 108 | Yes | 38 | 16 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 421 | 40-60 | 40 | 60 | 62 | 62 | 100 | 103 | 125.629 | 283.5 | 0 | 0 | 309 | 20.06 | 2024-12-09 | 2025-02-01 | 55 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 421 | 60-80 | 60 | 80 | 62 | 61 | 98.39 | 145 | 136.4262 | 225 | 0 | 1 | 309 | 20.06 | 2025-02-01 | 2025-04-19 | 78 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 421 | 80-100+ | 80 | 100 | 56 | 55 | 98.21 | 147 | 146.5273 | 206.2 | 0 | 1 | 309 | 18.12 | 2025-04-19 | 2025-12-06 | 232 | Yes | 122 | 27 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 505 | 0-20 | 0 | 20 | 75 | 74 | 98.67 | 142 | 179.5 | 309.1 | 0 | 1 | 379 | 19.79 | 2015-11-27 | 2024-12-31 | 3323 | Yes | 1098 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 505 | 20-40 | 20 | 40 | 76 | 76 | 100 | 222 | 222.5921 | 362.5 | 0 | 0 | 379 | 20.05 | 2025-01-02 | 2025-03-29 | 87 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 505 | 40-60 | 40 | 60 | 76 | 76 | 100 | 212.5 | 220.2763 | 349.5 | 0 | 0 | 379 | 20.05 | 2025-03-30 | 2025-05-16 | 48 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 505 | 60-80 | 60 | 80 | 76 | 76 | 100 | 122.5 | 144.5132 | 289.5 | 0 | 0 | 379 | 20.05 | 2025-05-16 | 2025-11-18 | 187 | Yes | 122 | 28 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 505 | 80-100+ | 80 | 100 | 70 | 54 | 77.14 | 17 | 22.3962 | 46.6 | 1 | 16 | 379 | 18.47 | 2025-11-19 | 2026-05-18 | 181 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 509 | 0-20 | 0 | 20 | 61 | 58 | 95.08 | 266 | 276.5172 | 382.1 | 0 | 3 | 309 | 19.74 | 2025-01-01 | 2025-04-01 | 91 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 509 | 20-40 | 20 | 40 | 62 | 51 | 82.26 | 339 | 309.8431 | 386 | 0 | 11 | 309 | 20.06 | 2025-04-01 | 2025-05-16 | 46 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 509 | 40-60 | 40 | 60 | 62 | 48 | 77.42 | 228.5 | 223.25 | 313.3 | 0 | 14 | 309 | 20.06 | 2025-05-17 | 2025-10-25 | 162 | Yes | 122 | 33 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 509 | 60-80 | 60 | 80 | 62 | 46 | 74.19 | 86.5 | 95.3696 | 163 | 0 | 16 | 309 | 20.06 | 2025-10-26 | 2026-04-05 | 162 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 509 | 80-100+ | 80 | 100 | 17 | 1 | 5.88 | 12 | 12 | 12 | 0 | 16 | 309 | 5.5 | 2026-04-05 | 2026-05-14 | 40 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 510 | 0-20 | 0 | 20 | 58 | 32 | 55.17 | 98.5 | 139.6875 | 288.9 | 0 | 26 | 293 | 19.8 | 2025-01-06 | 2026-02-03 | 394 | Yes | 122 | 7 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 510 | 20-40 | 20 | 40 | 23 | 1 | 4.35 | 57 | 57 | 57 | 0 | 22 | 293 | 7.85 | 2026-02-16 | 2026-05-19 | 93 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 512 | 0-20 | 0 | 20 | 63 | 62 | 98.41 | 219 | 216.7581 | 302.6 | 0 | 1 | 315 | 20 | 2025-02-23 | 2025-05-15 | 82 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 512 | 20-40 | 20 | 40 | 63 | 56 | 88.89 | 208 | 198.3036 | 251 | 0 | 7 | 315 | 20 | 2025-05-17 | 2025-07-20 | 65 | Yes | 50 | 50 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 512 | 40-60 | 40 | 60 | 63 | 48 | 76.19 | 154.5 | 154.1458 | 214.8 | 0 | 15 | 315 | 20 | 2025-07-21 | 2025-10-12 | 84 | Yes | 72 | 57 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 512 | 60-80 | 60 | 80 | 63 | 36 | 57.14 | 99 | 97.6111 | 150 | 0 | 27 | 315 | 20 | 2025-10-12 | 2025-12-13 | 63 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 512 | 80-100+ | 80 | 100 | 45 | 15 | 33.33 | 72 | 67 | 86.2 | 0 | 30 | 315 | 14.29 | 2025-12-14 | 2026-05-09 | 147 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 513 | 0-20 | 0 | 20 | 83 | 29 | 34.94 | 175.5 | 149.6786 | 206.5 | 1 | 54 | 619 | 13.41 | 2025-03-22 | 2026-05-19 | 424 | Yes | 122 | 29 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 601 | 0-20 | 0 | 20 | 58 | 41 | 70.69 | 36 | 58.725 | 102.8 | 1 | 17 | 292 | 19.86 | 2025-05-03 | 2026-01-23 | 266 | Yes | 122 | 4 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 601 | 20-40 | 20 | 40 | 58 | 29 | 50 | 16 | 18.2069 | 26.6 | 0 | 29 | 292 | 19.86 | 2026-01-24 | 2026-05-10 | 107 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 601 | 40-60 | 40 | 60 | 3 | 0 | 0 |  |  |  | 0 | 3 | 292 | 1.03 | 2026-05-13 | 2026-05-19 | 7 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TA 602 | 0-20 | 0 | 20 | 95 | 38 | 40 | 130 | 135 | 181.4 | 1 | 57 | 478 | 19.87 | 2025-09-15 | 2026-01-31 | 139 | Yes | 16 | 1 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TA 602 | 20-40 | 20 | 40 | 48 | 2 | 4.17 | 52.5 | 52.5 | 80.1 | 0 | 46 | 478 | 10.04 | 2026-01-31 | 2026-05-15 | 105 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-18
TB 501 | 0-20 | 0 | 20 | 47 | 47 | 100 | 118 | 124.8298 | 183 | 0 | 0 | 238 | 19.75 | 2024-08-12 | 2024-11-15 | 96 | Yes | 50 | 10 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 501 | 20-40 | 20 | 40 | 48 | 48 | 100 | 63.5 | 71.5625 | 110.6 | 0 | 0 | 238 | 20.17 | 2024-11-15 | 2025-01-10 | 57 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 501 | 40-60 | 40 | 60 | 47 | 47 | 100 | 61 | 72.0426 | 128.8 | 0 | 0 | 238 | 19.75 | 2025-01-12 | 2025-04-15 | 94 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 501 | 60-80 | 60 | 80 | 48 | 48 | 100 | 40 | 45.3958 | 82.5 | 0 | 0 | 238 | 20.17 | 2025-04-17 | 2025-10-17 | 184 | Yes | 122 | 18 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 501 | 80-100+ | 80 | 100 | 41 | 40 | 97.56 | 12.5 | 14.8421 | 26.9 | 2 | 1 | 238 | 17.23 | 2025-10-23 | 2026-04-30 | 190 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 507 | 0-20 | 0 | 20 | 111 | 83 | 74.77 | 134 | 142.1687 | 208.8 | 0 | 28 | 556 | 19.96 | 2025-01-17 | 2025-07-21 | 186 | Yes | 51 | 51 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 507 | 20-40 | 20 | 40 | 111 | 91 | 81.98 | 59 | 68.6556 | 117.6 | 1 | 20 | 556 | 19.96 | 2025-07-21 | 2025-11-12 | 115 | Yes | 72 | 96 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 507 | 40-60 | 40 | 60 | 109 | 46 | 42.2 | 46 | 55.0435 | 120 | 0 | 63 | 556 | 19.6 | 2025-11-14 | 2026-05-19 | 187 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 605 | 0-20 | 0 | 20 | 104 | 84 | 80.77 | 92.5 | 101.4762 | 156.1 | 0 | 20 | 523 | 19.89 | 2025-08-11 | 2025-12-26 | 138 | Yes | 51 | 4 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 605 | 20-40 | 20 | 40 | 105 | 82 | 78.1 | 59 | 61.0854 | 97.8 | 0 | 23 | 523 | 20.08 | 2025-12-26 | 2026-03-09 | 74 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19
TB 605 | 40-60 | 40 | 60 | 79 | 18 | 22.78 | 18 | 20.2778 | 34 | 0 | 61 | 523 | 15.11 | 2026-03-10 | 2026-05-19 | 71 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-05-19

## Delay Phase - Series
Delay Phase - Series
Series | Phase | Foundation Bucket Start % | Foundation Bucket End % | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Scope Total | Phase Foundations % of Scope | Phase Start Date | Phase End Date | Phase Duration Days | Monsoon Overlap | Monsoon Overlap Days | Monsoon Foundation Count
4xx | 0-20 | 0 | 20 | 408 | 392 | 96.08 | 217 | 233.2615 | 416.3 | 2 | 16 | 2052 | 19.88 | 2024-01-02 | 2025-03-24 | 448 | Yes | 122 | 276
4xx | 20-40 | 20 | 40 | 409 | 394 | 96.33 | 159 | 171.5471 | 304 | 1 | 15 | 2052 | 19.93 | 2024-08-24 | 2025-11-27 | 461 | Yes | 160 | 50
4xx | 40-60 | 40 | 60 | 348 | 320 | 91.95 | 110.5 | 119.2138 | 214.2 | 2 | 28 | 2052 | 16.96 | 2024-10-24 | 2026-03-05 | 498 | Yes | 122 | 26
4xx | 60-80 | 60 | 80 | 283 | 215 | 75.97 | 99 | 116.6682 | 235.1 | 1 | 68 | 2052 | 13.79 | 2024-11-30 | 2026-05-13 | 530 | Yes | 122 | 16
4xx | 80-100+ | 80 | 100 | 195 | 151 | 77.44 | 137 | 138.9272 | 240 | 0 | 44 | 2052 | 9.5 | 2025-01-30 | 2026-05-17 | 473 | Yes | 122 | 42
5xx | 0-20 | 0 | 20 | 498 | 385 | 77.31 | 160.5 | 179.9167 | 312.1 | 1 | 113 | 2709 | 18.38 | 2015-11-27 | 2026-05-19 | 3827 | Yes | 1220 | 97
5xx | 20-40 | 20 | 40 | 383 | 323 | 84.33 | 134.5 | 166.1335 | 348.5 | 1 | 60 | 2709 | 14.14 | 2024-11-15 | 2026-05-19 | 551 | Yes | 122 | 146
5xx | 40-60 | 40 | 60 | 357 | 265 | 74.23 | 150 | 153.8642 | 296.4 | 0 | 92 | 2709 | 13.18 | 2025-01-12 | 2026-05-19 | 493 | Yes | 122 | 90
5xx | 60-80 | 60 | 80 | 249 | 206 | 82.73 | 78.5 | 102.2476 | 218 | 0 | 43 | 2709 | 9.19 | 2025-04-17 | 2026-04-05 | 354 | Yes | 122 | 46
5xx | 80-100+ | 80 | 100 | 173 | 110 | 63.58 | 15 | 25.8692 | 69.4 | 3 | 63 | 2709 | 6.39 | 2025-10-23 | 2026-05-18 | 208 | No | 0 | 0
6xx | 0-20 | 0 | 20 | 257 | 163 | 63.42 | 94 | 98.559 | 166 | 2 | 94 | 1293 | 19.88 | 2025-05-03 | 2026-01-31 | 274 | Yes | 122 | 9
6xx | 20-40 | 20 | 40 | 211 | 113 | 53.55 | 44 | 49.9292 | 95 | 0 | 98 | 1293 | 16.32 | 2025-12-26 | 2026-05-15 | 141 | No | 0 | 0
6xx | 40-60 | 40 | 60 | 82 | 18 | 21.95 | 18 | 20.2778 | 34 | 0 | 64 | 1293 | 6.34 | 2026-03-10 | 2026-05-19 | 71 | No | 0 | 0

## Delay Phase - Ownership
Delay Phase - Ownership
Ownership | Phase | Foundation Bucket Start % | Foundation Bucket End % | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Scope Total | Phase Foundations % of Scope | Phase Start Date | Phase End Date | Phase Duration Days | Monsoon Overlap | Monsoon Overlap Days | Monsoon Foundation Count
Government | 0-20 | 0 | 20 | 901 | 726 | 80.58 | 180 | 207.6796 | 376 | 5 | 175 | 4737 | 19.02 | 2015-11-27 | 2026-05-19 | 3827 | Yes | 1220 | 317
Government | 20-40 | 20 | 40 | 739 | 609 | 82.41 | 179 | 184.0987 | 329 | 1 | 130 | 4737 | 15.6 | 2024-08-24 | 2026-05-19 | 634 | Yes | 160 | 100
Government | 40-60 | 40 | 60 | 552 | 492 | 89.13 | 143.5 | 148.502 | 274.1 | 2 | 60 | 4737 | 11.65 | 2024-10-24 | 2026-05-19 | 573 | Yes | 122 | 116
Government | 60-80 | 60 | 80 | 484 | 373 | 77.07 | 101 | 117.879 | 232.9 | 1 | 111 | 4737 | 10.22 | 2024-11-30 | 2026-05-13 | 530 | Yes | 122 | 44
Government | 80-100+ | 80 | 100 | 327 | 221 | 67.58 | 93.5 | 105.3727 | 221.3 | 1 | 106 | 4737 | 6.9 | 2025-01-30 | 2026-05-18 | 474 | Yes | 122 | 42
Private | 0-20 | 0 | 20 | 262 | 214 | 81.68 | 108.5 | 122.3879 | 183.7 | 0 | 48 | 1317 | 19.89 | 2024-08-12 | 2025-12-26 | 502 | Yes | 172 | 65
Private | 20-40 | 20 | 40 | 264 | 221 | 83.71 | 59.5 | 66.4682 | 105.5 | 1 | 43 | 1317 | 20.05 | 2024-11-15 | 2026-03-09 | 480 | Yes | 122 | 96
Private | 40-60 | 40 | 60 | 235 | 111 | 47.23 | 46 | 56.6036 | 114 | 0 | 124 | 1317 | 17.84 | 2025-01-12 | 2026-05-19 | 493 | Yes | 122 | 0
Private | 60-80 | 60 | 80 | 48 | 48 | 100 | 40 | 45.3958 | 82.5 | 0 | 0 | 1317 | 3.64 | 2025-04-17 | 2025-10-17 | 184 | Yes | 122 | 18
Private | 80-100+ | 80 | 100 | 41 | 40 | 97.56 | 12.5 | 14.8421 | 26.9 | 2 | 1 | 1317 | 3.11 | 2025-10-23 | 2026-04-30 | 190 | No | 0 | 0

## Delay Buckets - Project
Delay Buckets - Project
Project | Bucket | Bucket Start Days | Bucket End Days | Foundations In Bucket | % of Foundations Done Till Date | % of Scope | Foundations Done Till Date | Scope Total | Matched Non-Negative | Unmatched | Negative Excluded
TA 413 | 0-30 | 0 | 30 | 3 | 0.96 | 0.47 | 314 | 632 | 302 | 10 | 2
TA 413 | 31-60 | 31 | 60 | 23 | 7.32 | 3.64 | 314 | 632 | 302 | 10 | 2
TA 413 | 61-90 | 61 | 90 | 34 | 10.83 | 5.38 | 314 | 632 | 302 | 10 | 2
TA 413 | 91-120 | 91 | 120 | 24 | 7.64 | 3.8 | 314 | 632 | 302 | 10 | 2
TA 413 | 121-150 | 121 | 150 | 19 | 6.05 | 3.01 | 314 | 632 | 302 | 10 | 2
TA 413 | 151-180 | 151 | 180 | 33 | 10.51 | 5.22 | 314 | 632 | 302 | 10 | 2
TA 413 | 181-210 | 181 | 210 | 28 | 8.92 | 4.43 | 314 | 632 | 302 | 10 | 2
TA 413 | 211-240 | 211 | 240 | 16 | 5.1 | 2.53 | 314 | 632 | 302 | 10 | 2
TA 413 | 241-270 | 241 | 270 | 22 | 7.01 | 3.48 | 314 | 632 | 302 | 10 | 2
TA 413 | 271-300 | 271 | 300 | 21 | 6.69 | 3.32 | 314 | 632 | 302 | 10 | 2
TA 413 | 301-330 | 301 | 330 | 21 | 6.69 | 3.32 | 314 | 632 | 302 | 10 | 2
TA 413 | 331-360 | 331 | 360 | 19 | 6.05 | 3.01 | 314 | 632 | 302 | 10 | 2
TA 413 | 361-390 | 361 | 390 | 10 | 3.18 | 1.58 | 314 | 632 | 302 | 10 | 2
TA 413 | 391-420 | 391 | 420 | 9 | 2.87 | 1.42 | 314 | 632 | 302 | 10 | 2
TA 413 | 421-450 | 421 | 450 | 9 | 2.87 | 1.42 | 314 | 632 | 302 | 10 | 2
TA 413 | 451-480 | 451 | 480 | 2 | 0.64 | 0.32 | 314 | 632 | 302 | 10 | 2
TA 413 | 481-510 | 481 | 510 | 9 | 2.87 | 1.42 | 314 | 632 | 302 | 10 | 2
TA 414 | 0-30 | 0 | 30 | 26 | 7.98 | 7.39 | 326 | 352 | 221 | 103 | 2
TA 414 | 31-60 | 31 | 60 | 45 | 13.8 | 12.78 | 326 | 352 | 221 | 103 | 2
TA 414 | 61-90 | 61 | 90 | 34 | 10.43 | 9.66 | 326 | 352 | 221 | 103 | 2
TA 414 | 91-120 | 91 | 120 | 21 | 6.44 | 5.97 | 326 | 352 | 221 | 103 | 2
TA 414 | 121-150 | 121 | 150 | 7 | 2.15 | 1.99 | 326 | 352 | 221 | 103 | 2
TA 414 | 151-180 | 151 | 180 | 8 | 2.45 | 2.27 | 326 | 352 | 221 | 103 | 2
TA 414 | 181-210 | 181 | 210 | 5 | 1.53 | 1.42 | 326 | 352 | 221 | 103 | 2
TA 414 | 211-240 | 211 | 240 | 6 | 1.84 | 1.7 | 326 | 352 | 221 | 103 | 2
TA 414 | 241-270 | 241 | 270 | 8 | 2.45 | 2.27 | 326 | 352 | 221 | 103 | 2
TA 414 | 271-300 | 271 | 300 | 9 | 2.76 | 2.56 | 326 | 352 | 221 | 103 | 2
TA 414 | 301-330 | 301 | 330 | 12 | 3.68 | 3.41 | 326 | 352 | 221 | 103 | 2
TA 414 | 331-360 | 331 | 360 | 15 | 4.6 | 4.26 | 326 | 352 | 221 | 103 | 2
TA 414 | 361-390 | 361 | 390 | 7 | 2.15 | 1.99 | 326 | 352 | 221 | 103 | 2
TA 414 | 391-420 | 391 | 420 | 6 | 1.84 | 1.7 | 326 | 352 | 221 | 103 | 2
TA 414 | 421-450 | 421 | 450 | 5 | 1.53 | 1.42 | 326 | 352 | 221 | 103 | 2
TA 414 | 451-480 | 451 | 480 | 4 | 1.23 | 1.14 | 326 | 352 | 221 | 103 | 2
TA 414 | 481-510 | 481 | 510 | 0 | 0 | 0 | 326 | 352 | 221 | 103 | 2
TA 414 | 511-540 | 511 | 540 | 0 | 0 | 0 | 326 | 352 | 221 | 103 | 2
TA 414 | 541-570 | 541 | 570 | 1 | 0.31 | 0.28 | 326 | 352 | 221 | 103 | 2
TA 414 | 571-600 | 571 | 600 | 0 | 0 | 0 | 326 | 352 | 221 | 103 | 2
TA 414 | 601-630 | 601 | 630 | 1 | 0.31 | 0.28 | 326 | 352 | 221 | 103 | 2
TA 414 | 631-660 | 631 | 660 | 0 | 0 | 0 | 326 | 352 | 221 | 103 | 2
TA 414 | 661-690 | 661 | 690 | 0 | 0 | 0 | 326 | 352 | 221 | 103 | 2
TA 414 | 691-720 | 691 | 720 | 1 | 0.31 | 0.28 | 326 | 352 | 221 | 103 | 2
TA 416 | 0-30 | 0 | 30 | 7 | 2.31 | 2.32 | 303 | 302 | 303 | 0 | 0
TA 416 | 31-60 | 31 | 60 | 16 | 5.28 | 5.3 | 303 | 302 | 303 | 0 | 0
TA 416 | 61-90 | 61 | 90 | 36 | 11.88 | 11.92 | 303 | 302 | 303 | 0 | 0
TA 416 | 91-120 | 91 | 120 | 56 | 18.48 | 18.54 | 303 | 302 | 303 | 0 | 0
TA 416 | 121-150 | 121 | 150 | 48 | 15.84 | 15.89 | 303 | 302 | 303 | 0 | 0
TA 416 | 151-180 | 151 | 180 | 31 | 10.23 | 10.26 | 303 | 302 | 303 | 0 | 0
TA 416 | 181-210 | 181 | 210 | 30 | 9.9 | 9.93 | 303 | 302 | 303 | 0 | 0
TA 416 | 211-240 | 211 | 240 | 21 | 6.93 | 6.95 | 303 | 302 | 303 | 0 | 0
TA 416 | 241-270 | 241 | 270 | 24 | 7.92 | 7.95 | 303 | 302 | 303 | 0 | 0
TA 416 | 271-300 | 271 | 300 | 18 | 5.94 | 5.96 | 303 | 302 | 303 | 0 | 0
TA 416 | 301-330 | 301 | 330 | 6 | 1.98 | 1.99 | 303 | 302 | 303 | 0 | 0
TA 416 | 331-360 | 331 | 360 | 6 | 1.98 | 1.99 | 303 | 302 | 303 | 0 | 0
TA 416 | 361-390 | 361 | 390 | 2 | 0.66 | 0.66 | 303 | 302 | 303 | 0 | 0
TA 416 | 391-420 | 391 | 420 | 0 | 0 | 0 | 303 | 302 | 303 | 0 | 0
TA 416 | 421-450 | 421 | 450 | 1 | 0.33 | 0.33 | 303 | 302 | 303 | 0 | 0
TA 416 | 451-480 | 451 | 480 | 1 | 0.33 | 0.33 | 303 | 302 | 303 | 0 | 0
TA 418 | 0-30 | 0 | 30 | 12 | 9.3 | 9.45 | 129 | 127 | 125 | 4 | 0
TA 418 | 31-60 | 31 | 60 | 12 | 9.3 | 9.45 | 129 | 127 | 125 | 4 | 0
TA 418 | 61-90 | 61 | 90 | 17 | 13.18 | 13.39 | 129 | 127 | 125 | 4 | 0
TA 418 | 91-120 | 91 | 120 | 17 | 13.18 | 13.39 | 129 | 127 | 125 | 4 | 0
TA 418 | 121-150 | 121 | 150 | 23 | 17.83 | 18.11 | 129 | 127 | 125 | 4 | 0
TA 418 | 151-180 | 151 | 180 | 17 | 13.18 | 13.39 | 129 | 127 | 125 | 4 | 0
TA 418 | 181-210 | 181 | 210 | 8 | 6.2 | 6.3 | 129 | 127 | 125 | 4 | 0
TA 418 | 211-240 | 211 | 240 | 8 | 6.2 | 6.3 | 129 | 127 | 125 | 4 | 0
TA 418 | 241-270 | 241 | 270 | 7 | 5.43 | 5.51 | 129 | 127 | 125 | 4 | 0
TA 418 | 271-300 | 271 | 300 | 0 | 0 | 0 | 129 | 127 | 125 | 4 | 0
TA 418 | 301-330 | 301 | 330 | 3 | 2.33 | 2.36 | 129 | 127 | 125 | 4 | 0
TA 418 | 331-360 | 331 | 360 | 0 | 0 | 0 | 129 | 127 | 125 | 4 | 0
TA 418 | 361-390 | 361 | 390 | 0 | 0 | 0 | 129 | 127 | 125 | 4 | 0
TA 418 | 391-420 | 391 | 420 | 0 | 0 | 0 | 129 | 127 | 125 | 4 | 0
TA 418 | 421-450 | 421 | 450 | 0 | 0 | 0 | 129 | 127 | 125 | 4 | 0
TA 418 | 451-480 | 451 | 480 | 1 | 0.78 | 0.79 | 129 | 127 | 125 | 4 | 0
TA 419 | 0-30 | 0 | 30 | 22 | 8.21 | 6.67 | 268 | 330 | 214 | 52 | 2
TA 419 | 31-60 | 31 | 60 | 22 | 8.21 | 6.67 | 268 | 330 | 214 | 52 | 2
TA 419 | 61-90 | 61 | 90 | 15 | 5.6 | 4.55 | 268 | 330 | 214 | 52 | 2
TA 419 | 91-120 | 91 | 120 | 27 | 10.07 | 8.18 | 268 | 330 | 214 | 52 | 2
TA 419 | 121-150 | 121 | 150 | 20 | 7.46 | 6.06 | 268 | 330 | 214 | 52 | 2
TA 419 | 151-180 | 151 | 180 | 21 | 7.84 | 6.36 | 268 | 330 | 214 | 52 | 2
TA 419 | 181-210 | 181 | 210 | 13 | 4.85 | 3.94 | 268 | 330 | 214 | 52 | 2
TA 419 | 211-240 | 211 | 240 | 17 | 6.34 | 5.15 | 268 | 330 | 214 | 52 | 2
TA 419 | 241-270 | 241 | 270 | 22 | 8.21 | 6.67 | 268 | 330 | 214 | 52 | 2
TA 419 | 271-300 | 271 | 300 | 15 | 5.6 | 4.55 | 268 | 330 | 214 | 52 | 2
TA 419 | 301-330 | 301 | 330 | 7 | 2.61 | 2.12 | 268 | 330 | 214 | 52 | 2
TA 419 | 331-360 | 331 | 360 | 5 | 1.87 | 1.52 | 268 | 330 | 214 | 52 | 2
TA 419 | 361-390 | 361 | 390 | 3 | 1.12 | 0.91 | 268 | 330 | 214 | 52 | 2
TA 419 | 391-420 | 391 | 420 | 2 | 0.75 | 0.61 | 268 | 330 | 214 | 52 | 2
TA 419 | 421-450 | 421 | 450 | 2 | 0.75 | 0.61 | 268 | 330 | 214 | 52 | 2
TA 419 | 451-480 | 451 | 480 | 1 | 0.37 | 0.3 | 268 | 330 | 214 | 52 | 2
TA 421 | 0-30 | 0 | 30 | 17 | 5.61 | 5.5 | 303 | 309 | 301 | 2 | 0
TA 421 | 31-60 | 31 | 60 | 37 | 12.21 | 11.97 | 303 | 309 | 301 | 2 | 0
TA 421 | 61-90 | 61 | 90 | 32 | 10.56 | 10.36 | 303 | 309 | 301 | 2 | 0
TA 421 | 91-120 | 91 | 120 | 64 | 21.12 | 20.71 | 303 | 309 | 301 | 2 | 0
TA 421 | 121-150 | 121 | 150 | 43 | 14.19 | 13.92 | 303 | 309 | 301 | 2 | 0
TA 421 | 151-180 | 151 | 180 | 41 | 13.53 | 13.27 | 303 | 309 | 301 | 2 | 0
TA 421 | 181-210 | 181 | 210 | 24 | 7.92 | 7.77 | 303 | 309 | 301 | 2 | 0
TA 421 | 211-240 | 211 | 240 | 12 | 3.96 | 3.88 | 303 | 309 | 301 | 2 | 0
TA 421 | 241-270 | 241 | 270 | 10 | 3.3 | 3.24 | 303 | 309 | 301 | 2 | 0
TA 421 | 271-300 | 271 | 300 | 8 | 2.64 | 2.59 | 303 | 309 | 301 | 2 | 0
TA 421 | 301-330 | 301 | 330 | 2 | 0.66 | 0.65 | 303 | 309 | 301 | 2 | 0
TA 421 | 331-360 | 331 | 360 | 5 | 1.65 | 1.62 | 303 | 309 | 301 | 2 | 0
TA 421 | 361-390 | 361 | 390 | 2 | 0.66 | 0.65 | 303 | 309 | 301 | 2 | 0
TA 421 | 391-420 | 391 | 420 | 1 | 0.33 | 0.32 | 303 | 309 | 301 | 2 | 0
TA 421 | 421-450 | 421 | 450 | 1 | 0.33 | 0.32 | 303 | 309 | 301 | 2 | 0
TA 421 | 451-480 | 451 | 480 | 0 | 0 | 0 | 303 | 309 | 301 | 2 | 0
TA 421 | 481-510 | 481 | 510 | 0 | 0 | 0 | 303 | 309 | 301 | 2 | 0
TA 421 | 511-540 | 511 | 540 | 1 | 0.33 | 0.32 | 303 | 309 | 301 | 2 | 0
TA 421 | 541-570 | 541 | 570 | 1 | 0.33 | 0.32 | 303 | 309 | 301 | 2 | 0
TA 505 | 0-30 | 0 | 30 | 48 | 12.87 | 12.66 | 373 | 379 | 355 | 17 | 1
TA 505 | 31-60 | 31 | 60 | 28 | 7.51 | 7.39 | 373 | 379 | 355 | 17 | 1
TA 505 | 61-90 | 61 | 90 | 14 | 3.75 | 3.69 | 373 | 379 | 355 | 17 | 1
TA 505 | 91-120 | 91 | 120 | 41 | 10.99 | 10.82 | 373 | 379 | 355 | 17 | 1
TA 505 | 121-150 | 121 | 150 | 50 | 13.4 | 13.19 | 373 | 379 | 355 | 17 | 1
TA 505 | 151-180 | 151 | 180 | 29 | 7.77 | 7.65 | 373 | 379 | 355 | 17 | 1
TA 505 | 181-210 | 181 | 210 | 27 | 7.24 | 7.12 | 373 | 379 | 355 | 17 | 1
TA 505 | 211-240 | 211 | 240 | 28 | 7.51 | 7.39 | 373 | 379 | 355 | 17 | 1
TA 505 | 241-270 | 241 | 270 | 22 | 5.9 | 5.8 | 373 | 379 | 355 | 17 | 1
TA 505 | 271-300 | 271 | 300 | 22 | 5.9 | 5.8 | 373 | 379 | 355 | 17 | 1
TA 505 | 301-330 | 301 | 330 | 12 | 3.22 | 3.17 | 373 | 379 | 355 | 17 | 1
TA 505 | 331-360 | 331 | 360 | 19 | 5.09 | 5.01 | 373 | 379 | 355 | 17 | 1
TA 505 | 361-390 | 361 | 390 | 4 | 1.07 | 1.06 | 373 | 379 | 355 | 17 | 1
TA 505 | 391-420 | 391 | 420 | 3 | 0.8 | 0.79 | 373 | 379 | 355 | 17 | 1
TA 505 | 421-450 | 421 | 450 | 5 | 1.34 | 1.32 | 373 | 379 | 355 | 17 | 1
TA 505 | 451-480 | 451 | 480 | 0 | 0 | 0 | 373 | 379 | 355 | 17 | 1
TA 505 | 481-510 | 481 | 510 | 1 | 0.27 | 0.26 | 373 | 379 | 355 | 17 | 1
TA 505 | 511-540 | 511 | 540 | 0 | 0 | 0 | 373 | 379 | 355 | 17 | 1
TA 505 | 541-570 | 541 | 570 | 0 | 0 | 0 | 373 | 379 | 355 | 17 | 1
TA 505 | 571-600 | 571 | 600 | 0 | 0 | 0 | 373 | 379 | 355 | 17 | 1
TA 505 | 601-630 | 601 | 630 | 0 | 0 | 0 | 373 | 379 | 355 | 17 | 1
TA 505 | 631-660 | 631 | 660 | 2 | 0.54 | 0.53 | 373 | 379 | 355 | 17 | 1
TA 509 | 0-30 | 0 | 30 | 5 | 1.89 | 1.62 | 264 | 309 | 204 | 60 | 0
TA 509 | 31-60 | 31 | 60 | 12 | 4.55 | 3.88 | 264 | 309 | 204 | 60 | 0
TA 509 | 61-90 | 61 | 90 | 11 | 4.17 | 3.56 | 264 | 309 | 204 | 60 | 0
TA 509 | 91-120 | 91 | 120 | 7 | 2.65 | 2.27 | 264 | 309 | 204 | 60 | 0
TA 509 | 121-150 | 121 | 150 | 14 | 5.3 | 4.53 | 264 | 309 | 204 | 60 | 0
TA 509 | 151-180 | 151 | 180 | 14 | 5.3 | 4.53 | 264 | 309 | 204 | 60 | 0
TA 509 | 181-210 | 181 | 210 | 28 | 10.61 | 9.06 | 264 | 309 | 204 | 60 | 0
TA 509 | 211-240 | 211 | 240 | 17 | 6.44 | 5.5 | 264 | 309 | 204 | 60 | 0
TA 509 | 241-270 | 241 | 270 | 17 | 6.44 | 5.5 | 264 | 309 | 204 | 60 | 0
TA 509 | 271-300 | 271 | 300 | 13 | 4.92 | 4.21 | 264 | 309 | 204 | 60 | 0
TA 509 | 301-330 | 301 | 330 | 23 | 8.71 | 7.44 | 264 | 309 | 204 | 60 | 0
TA 509 | 331-360 | 331 | 360 | 21 | 7.95 | 6.8 | 264 | 309 | 204 | 60 | 0
TA 509 | 361-390 | 361 | 390 | 12 | 4.55 | 3.88 | 264 | 309 | 204 | 60 | 0
TA 509 | 391-420 | 391 | 420 | 9 | 3.41 | 2.91 | 264 | 309 | 204 | 60 | 0
TA 509 | 421-450 | 421 | 450 | 1 | 0.38 | 0.32 | 264 | 309 | 204 | 60 | 0
TA 510 | 0-30 | 0 | 30 | 1 | 1.23 | 0.34 | 81 | 293 | 33 | 48 | 0
TA 510 | 31-60 | 31 | 60 | 3 | 3.7 | 1.02 | 81 | 293 | 33 | 48 | 0
TA 510 | 61-90 | 61 | 90 | 10 | 12.35 | 3.41 | 81 | 293 | 33 | 48 | 0
TA 510 | 91-120 | 91 | 120 | 9 | 11.11 | 3.07 | 81 | 293 | 33 | 48 | 0
TA 510 | 121-150 | 121 | 150 | 1 | 1.23 | 0.34 | 81 | 293 | 33 | 48 | 0
TA 510 | 151-180 | 151 | 180 | 2 | 2.47 | 0.68 | 81 | 293 | 33 | 48 | 0
TA 510 | 181-210 | 181 | 210 | 0 | 0 | 0 | 81 | 293 | 33 | 48 | 0
TA 510 | 211-240 | 211 | 240 | 1 | 1.23 | 0.34 | 81 | 293 | 33 | 48 | 0
TA 510 | 241-270 | 241 | 270 | 1 | 1.23 | 0.34 | 81 | 293 | 33 | 48 | 0
TA 510 | 271-300 | 271 | 300 | 2 | 2.47 | 0.68 | 81 | 293 | 33 | 48 | 0
TA 510 | 301-330 | 301 | 330 | 0 | 0 | 0 | 81 | 293 | 33 | 48 | 0
TA 510 | 331-360 | 331 | 360 | 1 | 1.23 | 0.34 | 81 | 293 | 33 | 48 | 0
TA 510 | 361-390 | 361 | 390 | 1 | 1.23 | 0.34 | 81 | 293 | 33 | 48 | 0
TA 510 | 391-420 | 391 | 420 | 0 | 0 | 0 | 81 | 293 | 33 | 48 | 0
TA 510 | 421-450 | 421 | 450 | 1 | 1.23 | 0.34 | 81 | 293 | 33 | 48 | 0
TA 512 | 0-30 | 0 | 30 | 4 | 1.35 | 1.27 | 297 | 315 | 217 | 80 | 0
TA 512 | 31-60 | 31 | 60 | 10 | 3.37 | 3.17 | 297 | 315 | 217 | 80 | 0
TA 512 | 61-90 | 61 | 90 | 22 | 7.41 | 6.98 | 297 | 315 | 217 | 80 | 0
TA 512 | 91-120 | 91 | 120 | 21 | 7.07 | 6.67 | 297 | 315 | 217 | 80 | 0
TA 512 | 121-150 | 121 | 150 | 35 | 11.78 | 11.11 | 297 | 315 | 217 | 80 | 0
TA 512 | 151-180 | 151 | 180 | 44 | 14.81 | 13.97 | 297 | 315 | 217 | 80 | 0
TA 512 | 181-210 | 181 | 210 | 13 | 4.38 | 4.13 | 297 | 315 | 217 | 80 | 0
TA 512 | 211-240 | 211 | 240 | 26 | 8.75 | 8.25 | 297 | 315 | 217 | 80 | 0
TA 512 | 241-270 | 241 | 270 | 21 | 7.07 | 6.67 | 297 | 315 | 217 | 80 | 0
TA 512 | 271-300 | 271 | 300 | 13 | 4.38 | 4.13 | 297 | 315 | 217 | 80 | 0
TA 512 | 301-330 | 301 | 330 | 5 | 1.68 | 1.59 | 297 | 315 | 217 | 80 | 0
TA 512 | 331-360 | 331 | 360 | 2 | 0.67 | 0.63 | 297 | 315 | 217 | 80 | 0
TA 512 | 361-390 | 361 | 390 | 1 | 0.34 | 0.32 | 297 | 315 | 217 | 80 | 0
TA 513 | 0-30 | 0 | 30 | 2 | 2.41 | 0.32 | 83 | 619 | 28 | 54 | 1
TA 513 | 31-60 | 31 | 60 | 3 | 3.61 | 0.48 | 83 | 619 | 28 | 54 | 1
TA 513 | 61-90 | 61 | 90 | 0 | 0 | 0 | 83 | 619 | 28 | 54 | 1
TA 513 | 91-120 | 91 | 120 | 2 | 2.41 | 0.32 | 83 | 619 | 28 | 54 | 1
TA 513 | 121-150 | 121 | 150 | 3 | 3.61 | 0.48 | 83 | 619 | 28 | 54 | 1
TA 513 | 151-180 | 151 | 180 | 6 | 7.23 | 0.97 | 83 | 619 | 28 | 54 | 1
TA 513 | 181-210 | 181 | 210 | 10 | 12.05 | 1.62 | 83 | 619 | 28 | 54 | 1
TA 513 | 211-240 | 211 | 240 | 1 | 1.2 | 0.16 | 83 | 619 | 28 | 54 | 1
TA 513 | 241-270 | 241 | 270 | 1 | 1.2 | 0.16 | 83 | 619 | 28 | 54 | 1
TA 601 | 0-30 | 0 | 30 | 43 | 36.13 | 14.73 | 119 | 292 | 69 | 49 | 1
TA 601 | 31-60 | 31 | 60 | 10 | 8.4 | 3.42 | 119 | 292 | 69 | 49 | 1
TA 601 | 61-90 | 61 | 90 | 9 | 7.56 | 3.08 | 119 | 292 | 69 | 49 | 1
TA 601 | 91-120 | 91 | 120 | 4 | 3.36 | 1.37 | 119 | 292 | 69 | 49 | 1
TA 601 | 121-150 | 121 | 150 | 2 | 1.68 | 0.68 | 119 | 292 | 69 | 49 | 1
TA 601 | 151-180 | 151 | 180 | 0 | 0 | 0 | 119 | 292 | 69 | 49 | 1
TA 601 | 181-210 | 181 | 210 | 0 | 0 | 0 | 119 | 292 | 69 | 49 | 1
TA 601 | 211-240 | 211 | 240 | 0 | 0 | 0 | 119 | 292 | 69 | 49 | 1
TA 601 | 241-270 | 241 | 270 | 0 | 0 | 0 | 119 | 292 | 69 | 49 | 1
TA 601 | 271-300 | 271 | 300 | 0 | 0 | 0 | 119 | 292 | 69 | 49 | 1
TA 601 | 301-330 | 301 | 330 | 0 | 0 | 0 | 119 | 292 | 69 | 49 | 1
TA 601 | 331-360 | 331 | 360 | 1 | 0.84 | 0.34 | 119 | 292 | 69 | 49 | 1
TA 602 | 0-30 | 0 | 30 | 1 | 0.7 | 0.21 | 143 | 478 | 39 | 103 | 1
TA 602 | 31-60 | 31 | 60 | 1 | 0.7 | 0.21 | 143 | 478 | 39 | 103 | 1
TA 602 | 61-90 | 61 | 90 | 3 | 2.1 | 0.63 | 143 | 478 | 39 | 103 | 1
TA 602 | 91-120 | 91 | 120 | 10 | 6.99 | 2.09 | 143 | 478 | 39 | 103 | 1
TA 602 | 121-150 | 121 | 150 | 13 | 9.09 | 2.72 | 143 | 478 | 39 | 103 | 1
TA 602 | 151-180 | 151 | 180 | 6 | 4.2 | 1.26 | 143 | 478 | 39 | 103 | 1
TA 602 | 181-210 | 181 | 210 | 5 | 3.5 | 1.05 | 143 | 478 | 39 | 103 | 1
TB 501 | 0-30 | 0 | 30 | 61 | 26.41 | 25.63 | 231 | 238 | 228 | 1 | 2
TB 501 | 31-60 | 31 | 60 | 60 | 25.97 | 25.21 | 231 | 238 | 228 | 1 | 2
TB 501 | 61-90 | 61 | 90 | 38 | 16.45 | 15.97 | 231 | 238 | 228 | 1 | 2
TB 501 | 91-120 | 91 | 120 | 36 | 15.58 | 15.13 | 231 | 238 | 228 | 1 | 2
TB 501 | 121-150 | 121 | 150 | 19 | 8.23 | 7.98 | 231 | 238 | 228 | 1 | 2
TB 501 | 151-180 | 151 | 180 | 5 | 2.16 | 2.1 | 231 | 238 | 228 | 1 | 2
TB 501 | 181-210 | 181 | 210 | 8 | 3.46 | 3.36 | 231 | 238 | 228 | 1 | 2
TB 501 | 211-240 | 211 | 240 | 0 | 0 | 0 | 231 | 238 | 228 | 1 | 2
TB 501 | 241-270 | 241 | 270 | 1 | 0.43 | 0.42 | 231 | 238 | 228 | 1 | 2
TB 507 | 0-30 | 0 | 30 | 27 | 8.16 | 4.86 | 331 | 556 | 219 | 111 | 1
TB 507 | 31-60 | 31 | 60 | 62 | 18.73 | 11.15 | 331 | 556 | 219 | 111 | 1
TB 507 | 61-90 | 61 | 90 | 42 | 12.69 | 7.55 | 331 | 556 | 219 | 111 | 1
TB 507 | 91-120 | 91 | 120 | 25 | 7.55 | 4.5 | 331 | 556 | 219 | 111 | 1
TB 507 | 121-150 | 121 | 150 | 24 | 7.25 | 4.32 | 331 | 556 | 219 | 111 | 1
TB 507 | 151-180 | 151 | 180 | 22 | 6.65 | 3.96 | 331 | 556 | 219 | 111 | 1
TB 507 | 181-210 | 181 | 210 | 8 | 2.42 | 1.44 | 331 | 556 | 219 | 111 | 1
TB 507 | 211-240 | 211 | 240 | 2 | 0.6 | 0.36 | 331 | 556 | 219 | 111 | 1
TB 507 | 241-270 | 241 | 270 | 2 | 0.6 | 0.36 | 331 | 556 | 219 | 111 | 1
TB 507 | 271-300 | 271 | 300 | 1 | 0.3 | 0.18 | 331 | 556 | 219 | 111 | 1
TB 507 | 301-330 | 301 | 330 | 1 | 0.3 | 0.18 | 331 | 556 | 219 | 111 | 1
TB 507 | 331-360 | 331 | 360 | 2 | 0.6 | 0.36 | 331 | 556 | 219 | 111 | 1
TB 507 | 361-390 | 361 | 390 | 1 | 0.3 | 0.18 | 331 | 556 | 219 | 111 | 1
TB 605 | 0-30 | 0 | 30 | 27 | 9.38 | 5.16 | 288 | 523 | 184 | 104 | 0
TB 605 | 31-60 | 31 | 60 | 41 | 14.24 | 7.84 | 288 | 523 | 184 | 104 | 0
TB 605 | 61-90 | 61 | 90 | 55 | 19.1 | 10.52 | 288 | 523 | 184 | 104 | 0
TB 605 | 91-120 | 91 | 120 | 41 | 14.24 | 7.84 | 288 | 523 | 184 | 104 | 0
TB 605 | 121-150 | 121 | 150 | 10 | 3.47 | 1.91 | 288 | 523 | 184 | 104 | 0
TB 605 | 151-180 | 151 | 180 | 7 | 2.43 | 1.34 | 288 | 523 | 184 | 104 | 0
TB 605 | 181-210 | 181 | 210 | 2 | 0.69 | 0.38 | 288 | 523 | 184 | 104 | 0
TB 605 | 211-240 | 211 | 240 | 1 | 0.35 | 0.19 | 288 | 523 | 184 | 104 | 0

## Delay Buckets - Series
Delay Buckets - Series
Series | Bucket | Bucket Start Days | Bucket End Days | Foundations In Bucket | % of Foundations Done Till Date | % of Scope | Foundations Done Till Date | Scope Total | Matched Non-Negative | Unmatched | Negative Excluded
4xx | 0-30 | 0 | 30 | 87 | 5.3 | 4.24 | 1643 | 2052 | 1466 | 171 | 6
4xx | 31-60 | 31 | 60 | 155 | 9.43 | 7.55 | 1643 | 2052 | 1466 | 171 | 6
4xx | 61-90 | 61 | 90 | 168 | 10.23 | 8.19 | 1643 | 2052 | 1466 | 171 | 6
4xx | 91-120 | 91 | 120 | 209 | 12.72 | 10.19 | 1643 | 2052 | 1466 | 171 | 6
4xx | 121-150 | 121 | 150 | 160 | 9.74 | 7.8 | 1643 | 2052 | 1466 | 171 | 6
4xx | 151-180 | 151 | 180 | 151 | 9.19 | 7.36 | 1643 | 2052 | 1466 | 171 | 6
4xx | 181-210 | 181 | 210 | 108 | 6.57 | 5.26 | 1643 | 2052 | 1466 | 171 | 6
4xx | 211-240 | 211 | 240 | 80 | 4.87 | 3.9 | 1643 | 2052 | 1466 | 171 | 6
4xx | 241-270 | 241 | 270 | 93 | 5.66 | 4.53 | 1643 | 2052 | 1466 | 171 | 6
4xx | 271-300 | 271 | 300 | 71 | 4.32 | 3.46 | 1643 | 2052 | 1466 | 171 | 6
4xx | 301-330 | 301 | 330 | 51 | 3.1 | 2.49 | 1643 | 2052 | 1466 | 171 | 6
4xx | 331-360 | 331 | 360 | 50 | 3.04 | 2.44 | 1643 | 2052 | 1466 | 171 | 6
4xx | 361-390 | 361 | 390 | 24 | 1.46 | 1.17 | 1643 | 2052 | 1466 | 171 | 6
4xx | 391-420 | 391 | 420 | 18 | 1.1 | 0.88 | 1643 | 2052 | 1466 | 171 | 6
4xx | 421-450 | 421 | 450 | 18 | 1.1 | 0.88 | 1643 | 2052 | 1466 | 171 | 6
4xx | 451-480 | 451 | 480 | 9 | 0.55 | 0.44 | 1643 | 2052 | 1466 | 171 | 6
4xx | 481-510 | 481 | 510 | 9 | 0.55 | 0.44 | 1643 | 2052 | 1466 | 171 | 6
4xx | 511-540 | 511 | 540 | 1 | 0.06 | 0.05 | 1643 | 2052 | 1466 | 171 | 6
4xx | 541-570 | 541 | 570 | 2 | 0.12 | 0.1 | 1643 | 2052 | 1466 | 171 | 6
4xx | 571-600 | 571 | 600 | 0 | 0 | 0 | 1643 | 2052 | 1466 | 171 | 6
4xx | 601-630 | 601 | 630 | 1 | 0.06 | 0.05 | 1643 | 2052 | 1466 | 171 | 6
4xx | 631-660 | 631 | 660 | 0 | 0 | 0 | 1643 | 2052 | 1466 | 171 | 6
4xx | 661-690 | 661 | 690 | 0 | 0 | 0 | 1643 | 2052 | 1466 | 171 | 6
4xx | 691-720 | 691 | 720 | 1 | 0.06 | 0.05 | 1643 | 2052 | 1466 | 171 | 6
5xx | 0-30 | 0 | 30 | 148 | 8.92 | 5.46 | 1660 | 2709 | 1284 | 371 | 5
5xx | 31-60 | 31 | 60 | 178 | 10.72 | 6.57 | 1660 | 2709 | 1284 | 371 | 5
5xx | 61-90 | 61 | 90 | 137 | 8.25 | 5.06 | 1660 | 2709 | 1284 | 371 | 5
5xx | 91-120 | 91 | 120 | 141 | 8.49 | 5.2 | 1660 | 2709 | 1284 | 371 | 5
5xx | 121-150 | 121 | 150 | 146 | 8.8 | 5.39 | 1660 | 2709 | 1284 | 371 | 5
5xx | 151-180 | 151 | 180 | 122 | 7.35 | 4.5 | 1660 | 2709 | 1284 | 371 | 5
5xx | 181-210 | 181 | 210 | 94 | 5.66 | 3.47 | 1660 | 2709 | 1284 | 371 | 5
5xx | 211-240 | 211 | 240 | 75 | 4.52 | 2.77 | 1660 | 2709 | 1284 | 371 | 5
5xx | 241-270 | 241 | 270 | 65 | 3.92 | 2.4 | 1660 | 2709 | 1284 | 371 | 5
5xx | 271-300 | 271 | 300 | 51 | 3.07 | 1.88 | 1660 | 2709 | 1284 | 371 | 5
5xx | 301-330 | 301 | 330 | 41 | 2.47 | 1.51 | 1660 | 2709 | 1284 | 371 | 5
5xx | 331-360 | 331 | 360 | 45 | 2.71 | 1.66 | 1660 | 2709 | 1284 | 371 | 5
5xx | 361-390 | 361 | 390 | 19 | 1.14 | 0.7 | 1660 | 2709 | 1284 | 371 | 5
5xx | 391-420 | 391 | 420 | 12 | 0.72 | 0.44 | 1660 | 2709 | 1284 | 371 | 5
5xx | 421-450 | 421 | 450 | 7 | 0.42 | 0.26 | 1660 | 2709 | 1284 | 371 | 5
5xx | 451-480 | 451 | 480 | 0 | 0 | 0 | 1660 | 2709 | 1284 | 371 | 5
5xx | 481-510 | 481 | 510 | 1 | 0.06 | 0.04 | 1660 | 2709 | 1284 | 371 | 5
5xx | 511-540 | 511 | 540 | 0 | 0 | 0 | 1660 | 2709 | 1284 | 371 | 5
5xx | 541-570 | 541 | 570 | 0 | 0 | 0 | 1660 | 2709 | 1284 | 371 | 5
5xx | 571-600 | 571 | 600 | 0 | 0 | 0 | 1660 | 2709 | 1284 | 371 | 5
5xx | 601-630 | 601 | 630 | 0 | 0 | 0 | 1660 | 2709 | 1284 | 371 | 5
5xx | 631-660 | 631 | 660 | 2 | 0.12 | 0.07 | 1660 | 2709 | 1284 | 371 | 5
6xx | 0-30 | 0 | 30 | 71 | 12.91 | 5.49 | 550 | 1293 | 292 | 256 | 2
6xx | 31-60 | 31 | 60 | 52 | 9.45 | 4.02 | 550 | 1293 | 292 | 256 | 2
6xx | 61-90 | 61 | 90 | 67 | 12.18 | 5.18 | 550 | 1293 | 292 | 256 | 2
6xx | 91-120 | 91 | 120 | 55 | 10 | 4.25 | 550 | 1293 | 292 | 256 | 2
6xx | 121-150 | 121 | 150 | 25 | 4.55 | 1.93 | 550 | 1293 | 292 | 256 | 2
6xx | 151-180 | 151 | 180 | 13 | 2.36 | 1.01 | 550 | 1293 | 292 | 256 | 2
6xx | 181-210 | 181 | 210 | 7 | 1.27 | 0.54 | 550 | 1293 | 292 | 256 | 2
6xx | 211-240 | 211 | 240 | 1 | 0.18 | 0.08 | 550 | 1293 | 292 | 256 | 2
6xx | 241-270 | 241 | 270 | 0 | 0 | 0 | 550 | 1293 | 292 | 256 | 2
6xx | 271-300 | 271 | 300 | 0 | 0 | 0 | 550 | 1293 | 292 | 256 | 2
6xx | 301-330 | 301 | 330 | 0 | 0 | 0 | 550 | 1293 | 292 | 256 | 2
6xx | 331-360 | 331 | 360 | 1 | 0.18 | 0.08 | 550 | 1293 | 292 | 256 | 2

## Delay Buckets - Ownership
Delay Buckets - Ownership
Ownership | Bucket | Bucket Start Days | Bucket End Days | Foundations In Bucket | % of Foundations Done Till Date | % of Scope | Foundations Done Till Date | Scope Total | Matched Non-Negative | Unmatched | Negative Excluded
Government | 0-30 | 0 | 30 | 191 | 6.36 | 4.03 | 3003 | 4737 | 2411 | 582 | 10
Government | 31-60 | 31 | 60 | 222 | 7.39 | 4.69 | 3003 | 4737 | 2411 | 582 | 10
Government | 61-90 | 61 | 90 | 237 | 7.89 | 5 | 3003 | 4737 | 2411 | 582 | 10
Government | 91-120 | 91 | 120 | 303 | 10.09 | 6.4 | 3003 | 4737 | 2411 | 582 | 10
Government | 121-150 | 121 | 150 | 278 | 9.26 | 5.87 | 3003 | 4737 | 2411 | 582 | 10
Government | 151-180 | 151 | 180 | 252 | 8.39 | 5.32 | 3003 | 4737 | 2411 | 582 | 10
Government | 181-210 | 181 | 210 | 191 | 6.36 | 4.03 | 3003 | 4737 | 2411 | 582 | 10
Government | 211-240 | 211 | 240 | 153 | 5.09 | 3.23 | 3003 | 4737 | 2411 | 582 | 10
Government | 241-270 | 241 | 270 | 155 | 5.16 | 3.27 | 3003 | 4737 | 2411 | 582 | 10
Government | 271-300 | 271 | 300 | 121 | 4.03 | 2.55 | 3003 | 4737 | 2411 | 582 | 10
Government | 301-330 | 301 | 330 | 91 | 3.03 | 1.92 | 3003 | 4737 | 2411 | 582 | 10
Government | 331-360 | 331 | 360 | 94 | 3.13 | 1.98 | 3003 | 4737 | 2411 | 582 | 10
Government | 361-390 | 361 | 390 | 42 | 1.4 | 0.89 | 3003 | 4737 | 2411 | 582 | 10
Government | 391-420 | 391 | 420 | 30 | 1 | 0.63 | 3003 | 4737 | 2411 | 582 | 10
Government | 421-450 | 421 | 450 | 25 | 0.83 | 0.53 | 3003 | 4737 | 2411 | 582 | 10
Government | 451-480 | 451 | 480 | 9 | 0.3 | 0.19 | 3003 | 4737 | 2411 | 582 | 10
Government | 481-510 | 481 | 510 | 10 | 0.33 | 0.21 | 3003 | 4737 | 2411 | 582 | 10
Government | 511-540 | 511 | 540 | 1 | 0.03 | 0.02 | 3003 | 4737 | 2411 | 582 | 10
Government | 541-570 | 541 | 570 | 2 | 0.07 | 0.04 | 3003 | 4737 | 2411 | 582 | 10
Government | 571-600 | 571 | 600 | 0 | 0 | 0 | 3003 | 4737 | 2411 | 582 | 10
Government | 601-630 | 601 | 630 | 1 | 0.03 | 0.02 | 3003 | 4737 | 2411 | 582 | 10
Government | 631-660 | 631 | 660 | 2 | 0.07 | 0.04 | 3003 | 4737 | 2411 | 582 | 10
Government | 661-690 | 661 | 690 | 0 | 0 | 0 | 3003 | 4737 | 2411 | 582 | 10
Government | 691-720 | 691 | 720 | 1 | 0.03 | 0.02 | 3003 | 4737 | 2411 | 582 | 10
Private | 0-30 | 0 | 30 | 115 | 13.53 | 8.73 | 850 | 1317 | 631 | 216 | 3
Private | 31-60 | 31 | 60 | 163 | 19.18 | 12.38 | 850 | 1317 | 631 | 216 | 3
Private | 61-90 | 61 | 90 | 135 | 15.88 | 10.25 | 850 | 1317 | 631 | 216 | 3
Private | 91-120 | 91 | 120 | 102 | 12 | 7.74 | 850 | 1317 | 631 | 216 | 3
Private | 121-150 | 121 | 150 | 53 | 6.24 | 4.02 | 850 | 1317 | 631 | 216 | 3
Private | 151-180 | 151 | 180 | 34 | 4 | 2.58 | 850 | 1317 | 631 | 216 | 3
Private | 181-210 | 181 | 210 | 18 | 2.12 | 1.37 | 850 | 1317 | 631 | 216 | 3
Private | 211-240 | 211 | 240 | 3 | 0.35 | 0.23 | 850 | 1317 | 631 | 216 | 3
Private | 241-270 | 241 | 270 | 3 | 0.35 | 0.23 | 850 | 1317 | 631 | 216 | 3
Private | 271-300 | 271 | 300 | 1 | 0.12 | 0.08 | 850 | 1317 | 631 | 216 | 3
Private | 301-330 | 301 | 330 | 1 | 0.12 | 0.08 | 850 | 1317 | 631 | 216 | 3
Private | 331-360 | 331 | 360 | 2 | 0.24 | 0.15 | 850 | 1317 | 631 | 216 | 3
Private | 361-390 | 361 | 390 | 1 | 0.12 | 0.08 | 850 | 1317 | 631 | 216 | 3

## Delay Coverage
Delay Coverage
Project | Series | Ownership | Eligible | Coverage Status | Source Type | Parser Modes | Reason | Foundation Locations | Matched Locations | RawData Start-Date Matches | Dropped-by-Daily Recovered | Alias Matches | Negative Excluded | Unmatched Locations | Scope Total | Scope Source | Scope Report Date | Status Rows Considered | Status Rows Used | Duplicate Rows Dropped | Notes
TA 413 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 314 | 304 | 304 | 1 | 1 | 2 | 10 | 632 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 414 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 326 | 223 | 223 | 0 | 0 | 2 | 103 | 352 | status_quantity_primary_latest | 2026-05-19 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 416 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 303 | 303 | 303 | 2 | 2 | 0 | 0 | 302 | status_quantity_primary_latest | 2026-05-17 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 418 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 129 | 125 | 125 | 0 | 0 | 0 | 4 | 127 | status_quantity_primary_latest | 2026-05-17 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 419 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 268 | 216 | 216 | 15 | 0 | 2 | 52 | 330 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 421 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 303 | 301 | 301 | 2 | 0 | 0 | 2 | 309 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 505 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 373 | 356 | 356 | 3 | 0 | 1 | 17 | 379 | status_quantity_primary_latest | 2026-05-19 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 509 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 264 | 204 | 204 | 7 | 0 | 0 | 60 | 309 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 510 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 81 | 33 | 33 | 0 | 0 | 0 | 48 | 293 | status_quantity_primary_latest | 2026-05-19 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 512 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 297 | 217 | 217 | 4 | 0 | 0 | 80 | 315 | status_quantity_primary_latest | 2026-05-19 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 513 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 83 | 29 | 29 | 1 | 0 | 1 | 54 | 619 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 601 | 6xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 119 | 70 | 70 | 3 | 0 | 1 | 49 | 292 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 602 | 6xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 143 | 40 | 40 | 0 | 0 | 1 | 103 | 478 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TB 501 | 5xx | Private | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 231 | 230 | 230 | 0 | 0 | 2 | 1 | 238 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TB 507 | 5xx | Private | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 331 | 220 | 220 | 8 | 0 | 1 | 111 | 556 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TB 605 | 6xx | Private | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 288 | 184 | 184 | 9 | 0 | 0 | 104 | 523 | status_quantity_primary_latest | 2026-05-19 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.

## Delay Anomalies
Delay Anomalies
Project | Series | Ownership | Phase | Location | Foundation Date | Erection Start | Delay Days | Issue | Foundation Line | Erection Line
TA 413 | 4xx | Government | 20-40 | 39/8 | 2025-01-24 | 2024-03-26 | -304 | NEGATIVE_DELAY_EXCLUDED
TA 413 | 4xx | Government | 40-60 | N'37A/0 | 2026-03-05 | 2025-02-28 | -370 | NEGATIVE_DELAY_EXCLUDED
TA 413 | 4xx | Government | 0-20 | 37/1 | 2024-09-23 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 0-20 | 3/8 | 2024-10-05 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 0-20 | 3/9 | 2024-10-09 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 0-20 | 37/0 | 2024-10-14 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 0-20 | 3/7 | 2024-10-19 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 0-20 | 3/6 | 2024-10-22 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 20-40 | 3/4 | 2024-10-29 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 20-40 | 16/0 | 2024-12-28 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 40-60 | 36B/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 40-60 | N'37/0 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 121/4 | 2024-11-19 | 2024-03-27 | -237 | NEGATIVE_DELAY_EXCLUDED
TA 414 | 4xx | Government | 60-80 | 126/0 | 2026-02-18 | 2026-01-17 | -32 | NEGATIVE_DELAY_EXCLUDED
TA 414 | 4xx | Government | 0-20 | 249/1 | 2024-12-19 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 249/0 | 2024-12-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 249/2 | 2024-12-28 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 250/0 | 2025-01-07 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 121/8 | 2025-01-10 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 121/9 | 2025-01-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 243/3 | 2025-02-07 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 172/0 | 2025-03-07 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 165/7 | 2025-03-24 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 165/2 | 2025-05-02 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 130/0 | 2025-05-10 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 221/0 | 2025-10-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 223/2 | 2025-10-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 224/0 | 2025-10-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 135/0 | 2025-11-04 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 219/1 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 225/1 | 2025-11-22 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 225/4 | 2025-11-25 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 127/2 | 2025-12-01 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 194/0 | 2025-12-04 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 225/3 | 2025-12-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 244/0 | 2025-12-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 256/1 | 2025-12-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 225/2 | 2025-12-11 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 210/0 | 2025-12-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 139/3 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 216/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 257/0 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 170/0 | 2025-12-17 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 173/0 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 165/6 | 2025-12-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 193/0 | 2025-12-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 250/1 | 2025-12-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 216/2 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 216/3 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 244/3 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 162/0 | 2025-12-29 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 211/0 | 2026-01-01 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 217/5 | 2026-01-12 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 211/4 | 2026-01-15 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 188/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 212/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 189/0 | 2026-01-18 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 213/0 | 2026-01-18 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 133/1 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 165/4 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 232/4 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 233/0 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 168/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 238/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 235/0 | 2026-01-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 236/0 | 2026-01-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 129/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 163/0 | 2026-01-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 124/2 | 2026-02-01 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 228/0 | 2026-02-01 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 214/0 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 237/0 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 232/0 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 235/1 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 217/0 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 217/1 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 248/0 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 145/1 | 2026-02-14 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 219/0 | 2026-02-17 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 255/1 | 2026-02-25 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 234/0 | 2026-03-11 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 231/0 | 2026-03-12 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 131/0 | 2026-03-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 150/1 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 180/0 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 225/7 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 232/2 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 225/5 | 2026-03-18 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 230/1 | 2026-03-23 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 156/0 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 150/0 | 2026-03-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 230A/0 | 2026-03-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 200/0 | 2026-04-01 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 155/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 156/1 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 159/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 195/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 232/3 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 151/0 | 2026-04-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 164/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 165/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 131/1 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 229B/0 | 2026-04-17 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 151A/0 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 153/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 229A/0 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 235/4 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 169/0 | 2026-04-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 206/0 | 2026-04-27 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 225/6 | 2026-04-27 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 206/1 | 2026-05-02 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 201/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 203/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 203A/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 203B/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 153A/0 | 2026-05-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 229/0 | 2026-05-14 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 0-20 | 35/6 | 2024-08-07 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 20-40 | 45/02 | 2024-12-04 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 46/1 | 2025-06-25 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 59/1 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 0-20 | 6/9 | 2024-07-10 | 2024-01-06 | -186 | NEGATIVE_DELAY_EXCLUDED
TA 419 | 4xx | Government | 40-60 | 26/1 | 2025-11-15 | 2025-03-22 | -238 | NEGATIVE_DELAY_EXCLUDED
TA 419 | 4xx | Government | 20-40 | 15/0 | 2024-12-12 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 20-40 | 39/0 | 2025-03-27 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 20-40 | 41/0 | 2025-04-23 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 78/3 | 2025-06-11 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 8/0 | 2025-07-15 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 46/0 | 2025-08-01 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 63/5 | 2025-11-02 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 83/9 | 2025-11-02 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 36/9 | 2025-11-06 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 43/1 | 2025-11-07 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 43/2 | 2025-11-09 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 52/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 63B/6 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 36/3 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 60/0 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 64/0 | 2025-12-29 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 78A/0 | 2026-01-03 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 38/1 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 82/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 77/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 38/3 | 2026-01-28 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 73/0 | 2026-03-22 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 32/0 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 76/2 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 84/2 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 38/4 | 2026-04-01 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 80/0 | 2026-04-01 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 64/4 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 93B/0 | 2026-04-07 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 71/0 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 41/2 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 69/0 | 2026-04-17 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 70/0 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 66/1 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 67/0 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 37/0 | 2026-04-27 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 53/0 | 2026-04-27 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 52/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 54/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 38/2 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 59/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 87/1 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 87/2 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 65/0 | 2026-05-08 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 72/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 68/0 | 2026-05-11 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 95A/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 76/1 | 2026-05-13 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 66/0 | 2026-05-16 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 75/0 | 2026-05-16 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 76/0 | 2026-05-17 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 96/0 | 2026-05-17 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 60-80 | 8/11 | 2025-04-15 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 4/16 | 2025-04-29 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 177/0 | 2026-05-15 | 2025-12-04 | -162 | NEGATIVE_DELAY_EXCLUDED
TA 505 | 5xx | Government | 0-20 | 171/10 | 2015-11-27 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 138/0 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 149B/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 158/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 174B/0 | 2026-01-22 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 148C/0 | 2026-02-21 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 148B/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 157/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 144/0 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 171/5 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 143/0 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 134/0 | 2026-04-09 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 129/0 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 133/0 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 129/1 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 137/0 | 2026-05-15 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 181/2 | 2026-05-18 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 0-20 | 13/5 | 2025-03-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 0-20 | 24/1 | 2025-03-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 0-20 | 21/3 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 24/2 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 24/4 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 24/5 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 39/7 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 39/8 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 41/1 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 41/2 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 41/5 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 41/8 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 44/2 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 20-40 | 44/3 | 2025-04-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 49/3 | 2025-05-23 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 49/2 | 2025-05-26 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 51/3 | 2025-05-26 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 47/4 | 2025-05-27 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 48/6 | 2025-06-01 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 47/6 | 2025-06-04 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 49/5 | 2025-06-06 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 48/9 | 2025-06-10 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 65/1 | 2025-06-18 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 66/7 | 2025-06-27 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 65/3 | 2025-06-30 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 63/2 | 2025-07-16 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 41/4 | 2025-08-06 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 40-60 | 21/0 | 2025-08-12 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 64/1 | 2025-10-30 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 47/2 | 2025-11-05 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 47/7 | 2025-11-06 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 47/3 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 66/3 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 23/0 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 65/0 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 56/2 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 48/3 | 2026-01-04 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 26/0 | 2026-02-06 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 53A/0 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 39/6 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 41/7 | 2026-03-26 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 53B/0 | 2026-03-30 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 39/10 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 60-80 | 48/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 65/4 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 39/11 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 35/0 | 2026-04-09 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 41/3 | 2026-04-10 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 4/6 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 4/4 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 54/0 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 4/3 | 2026-04-20 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 39/9 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 3/1 | 2026-04-29 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 4/5 | 2026-05-02 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 45/2 | 2026-05-04 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 50/0 | 2026-05-05 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 4/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 3/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TA 509 | 5xx | Government | 80-100+ | 47/9 | 2026-05-14 |  |  | UNMATCHED_LOCATION
TA 510 | 5xx | Government | 0-20 | 144/0 | 2025-01-06 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 155/1 | 2025-02-12 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 155/3 | 2025-02-18 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 155/4 | 2025-02-18 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 155/5 | 2025-02-23 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/0 | 2025-03-05 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/1 | 2025-03-05 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/3 | 2025-03-13 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/4 | 2025-03-21 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 139/1 | 2025-03-26 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/2 | 2025-03-26 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 137/0 | 2025-04-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 138/1 | 2025-04-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 139/5 | 2025-04-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 139/4 | 2025-04-23 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 136/0 | 2025-04-25 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 138/0 | 2025-05-04 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 143/2 | 2025-05-30 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 133/2 | 2025-08-31 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 138/2 | 2025-09-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 138/3 | 2025-11-18 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 147/2 | 2026-01-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 192/7 | 2026-01-09 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 192/12 | 2026-01-16 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 142/0 | 2026-01-27 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 148/0 | 2026-02-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 157B/0 | 2026-02-16 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 157A/0 | 2026-02-17 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 157/2 | 2026-03-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/5 | 2026-03-23 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 139/0 | 2026-04-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 192/8 | 2026-04-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 192/9 | 2026-04-01 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 139/3 | 2026-04-04 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 153/0 | 2026-04-04 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/2 | 2026-04-08 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/1 | 2026-04-12 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 131/1 | 2026-04-13 |  |  | UNMATCHED_LOCATION | Pile
TA 510 | 5xx | Government | 20-40 | 193/0 | 2026-04-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/4 | 2026-04-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 150/2 | 2026-04-22 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 157B/1 | 2026-04-22 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 194/0 | 2026-04-27 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 167/2 | 2026-05-07 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 133/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 167/3 | 2026-05-11 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 167/4 | 2026-05-17 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 133/1 | 2026-05-19 |  |  | UNMATCHED_LOCATION | FDN
TA 512 | 5xx | Government | 0-20 | 7/2 | 2025-05-04 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 5/8 | 2025-05-19 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 31/11 | 2025-06-10 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 27/2 | 2025-06-17 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 27/3 | 2025-06-20 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 16/2 | 2025-07-10 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 4/3 | 2025-07-17 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 1A/3 | 2025-07-20 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 40/2 | 2025-07-25 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 31/24 | 2025-07-29 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 40/4 | 2025-08-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 31/21 | 2025-08-07 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 2/1 | 2025-08-13 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 30/16 | 2025-08-22 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 31/22 | 2025-08-22 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 29/18 | 2025-09-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 36/9 | 2025-09-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 4/5 | 2025-09-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 37/6 | 2025-09-06 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 34/2 | 2025-09-09 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 36/5 | 2025-09-21 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 36/4 | 2025-09-26 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 29/19 | 2025-10-01 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 36/2 | 2025-10-12 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 30/0 | 2025-10-17 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 3/1 | 2025-10-23 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 12/0 | 2025-10-27 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 3/2 | 2025-10-28 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 31/0 | 2025-10-30 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 40/1 | 2025-10-30 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 37/1 | 2025-11-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 40/0 | 2025-11-10 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 16/1 | 2025-11-11 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 39/0 | 2025-11-14 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 38/2 | 2025-11-16 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 30/1 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 29/16 | 2025-11-24 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 38/1 | 2025-11-24 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 32/0 | 2025-11-25 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 32/4 | 2025-11-28 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 3/0 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 21/0 | 2025-12-01 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 32/1 | 2025-12-01 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 2A/5 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 32/3 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 32/6 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 2A/3 | 2025-12-09 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 2A/2 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 4/2 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 20A/0 | 2025-12-13 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 4/1 | 2025-12-14 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 2A/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 32/7 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 2A/0 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 36/0 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 22/0 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 27/1 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 36/1 | 2025-12-30 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 23/0 | 2026-01-04 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 33A/0 | 2026-01-05 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 42/0 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 13/1 | 2026-01-12 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 34/0 | 2026-01-13 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 43/0 | 2026-01-16 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 2/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 33/1 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 10/0 | 2026-02-02 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 16/3 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 32/8 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 32/9 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 33/0 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 44/0 | 2026-03-09 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 17/0 | 2026-04-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 47/0 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 18/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 44/1 | 2026-04-15 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 45/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 46/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 34/1 | 2026-04-29 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 11/7 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 513 | 5xx | Government | 0-20 | 51/2 | 2025-12-06 | 2025-05-10 | -210 | NEGATIVE_DELAY_EXCLUDED | S-P
TA 513 | 5xx | Government | 0-20 | 24/2 | 2025-03-30 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 24/1 | 2025-04-02 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 30/2 | 2025-04-09 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 23/6 | 2025-04-12 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 23/5 | 2025-04-14 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 31/1 | 2025-04-14 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 37/1 | 2025-04-17 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 30/3 | 2025-04-21 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 30/1 | 2025-04-22 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 31/2 | 2025-04-23 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 30/2 | 2025-04-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 24/3 | 2025-04-26 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 52/5 | 2025-05-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/3 | 2025-05-06 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/7 | 2025-05-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 64/2 | 2025-05-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 64/5 | 2025-05-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 3/5 | 2025-05-16 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 3/6 | 2025-05-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/3 | 2025-05-21 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 3/10 | 2025-05-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 32B/1 | 2025-05-25 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 21/6 | 2025-05-30 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 21/7 | 2025-05-30 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/1 | 2025-06-03 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/3 | 2025-06-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/2 | 2025-06-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/4 | 2025-06-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 14/4 | 2025-06-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 18/4 | 2025-06-20 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 26/1 | 2025-06-28 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 14/3 | 2025-07-02 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 56/4 | 2025-07-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 14/2 | 2025-07-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 15B/4 | 2025-07-15 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/0 | 2025-07-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 36/3 | 2025-07-26 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 56/3 | 2025-08-19 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 36/4 | 2025-08-21 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 30/0 | 2025-09-10 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 24/0 | 2025-09-19 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 19/0 | 2025-09-25 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 28/0 | 2025-09-30 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 18/0 | 2025-10-04 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 51/5 | 2025-12-19 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 52/3 | 2026-02-17 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/2 | 2026-03-28 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 52/2 | 2026-04-22 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 52/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/4 | 2026-04-27 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 30/0 | 2026-05-04 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 52/1 | 2026-05-04 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 28/1 | 2026-05-17 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 64/3 | 2026-05-19 |  |  | UNMATCHED_LOCATION | S-P
TA 601 | 6xx | Government | 0-20 | 56/7 | 2026-01-16 | 2025-12-15 | -32 | NEGATIVE_DELAY_EXCLUDED
TA 601 | 6xx | Government | 0-20 | 66/0 | 2025-05-03 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 81/2 | 2025-08-07 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 80/4 | 2025-10-27 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 77/8 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 60/3 | 2025-11-15 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 60/8 | 2025-11-23 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 59/1 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 77/6 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 73/1 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 56/1 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 73/2 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 79/1 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 84/6 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 94/1 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 99/12 | 2026-01-06 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 100/3 | 2026-01-14 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 83/0 | 2026-01-14 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 59/0 | 2026-01-26 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 78/3 | 2026-02-06 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 50/1 | 2026-02-12 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 50/2 | 2026-02-17 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 89/1 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 49/10 | 2026-03-11 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 51/7 | 2026-03-13 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 49/11 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 51/8 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 51/10 | 2026-03-17 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 90/0 | 2026-03-18 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 51/6 | 2026-03-19 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 52/1 | 2026-03-22 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 50/3 | 2026-03-25 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 51/2 | 2026-03-27 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 53/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 70/1 | 2026-04-11 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 53/0 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 70/2 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 50/0 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 70/4 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 70/3 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 66/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 49/9 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 67/0 | 2026-04-26 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 65/3 | 2026-04-29 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 49/8 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 67/1 | 2026-05-05 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 48/7 | 2026-05-10 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 69/0 | 2026-05-13 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 69/2 | 2026-05-16 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 48/3 | 2026-05-19 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 126/5 | 2025-10-28 | 2025-03-01 | -241 | NEGATIVE_DELAY_EXCLUDED
TA 602 | 6xx | Government | 0-20 | 123/1 | 2025-10-07 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 124/1 | 2025-10-08 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 124/2 | 2025-10-15 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 123/3 | 2025-10-19 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 124/3 | 2025-11-04 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 123/4 | 2025-11-06 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 123/2 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 126/10 | 2025-11-14 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 111/3 | 2025-11-19 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 103/2 | 2025-11-20 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 126/2 | 2025-11-21 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 111/4 | 2025-11-23 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 103/3 | 2025-11-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 103/1 | 2025-11-28 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 111/5 | 2025-11-28 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 110/2 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 121/5 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 110/1 | 2025-12-03 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 134/6 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 99/1 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 102/9 | 2025-12-07 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 109/10 | 2025-12-07 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 110/3 | 2025-12-11 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 109/11 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 136/7 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 99/2 | 2025-12-13 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 102/8 | 2025-12-15 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 108/7 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 110/4 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 136/9 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 109/7 | 2025-12-20 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 108/5 | 2025-12-22 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 136/6 | 2025-12-22 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 109/9 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 139/3 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 89/9 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 107/2 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 108/6 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 109/6 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 89/8 | 2025-12-28 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 109/5 | 2025-12-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 89/7 | 2025-12-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 107/1 | 2026-01-03 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 89/6 | 2026-01-04 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 129A/1 | 2026-01-07 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 89/5 | 2026-01-10 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 108/4 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 129A/5 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 108/1 | 2026-01-17 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 76/2 | 2026-01-20 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 77/1 | 2026-01-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 107/4 | 2026-01-25 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 129A/7 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 76/1 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 139/6 | 2026-01-28 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 127/7 | 2026-01-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 0-20 | 129A/2 | 2026-01-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 76/6 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 82/2 | 2026-02-02 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 127/4 | 2026-02-03 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 129A/10 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 82/3 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 127/1 | 2026-02-09 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 127/2 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 70/3 | 2026-02-13 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 129A/6 | 2026-02-16 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 121/10 | 2026-02-17 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 70/1 | 2026-02-23 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 125/1 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 126/7 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 70/2 | 2026-03-07 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 124/5 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 76/5 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 88/2 | 2026-03-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 88/1 | 2026-04-02 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 127/3 | 2026-04-03 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 124/0 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 87/4 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 102/11 | 2026-04-11 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 139/4 | 2026-04-11 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 69/2 | 2026-04-13 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 87/5 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 121/9 | 2026-04-15 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 71/1 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 87/2 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 69/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 109/8 | 2026-04-22 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 125/0 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 136/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 71/2 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 87/3 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 69/3 | 2026-04-28 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 127/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 139/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 71/3 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 88/3 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 108/0 | 2026-05-04 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 139/1 | 2026-05-04 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 71/4 | 2026-05-04 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 107/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 69/4 | 2026-05-08 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 126/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TA 602 | 6xx | Government | 20-40 | 88/0 | 2026-05-15 |  |  | UNMATCHED_LOCATION
TB 501 | 5xx | Private | 80-100+ | 8D/0A | 2025-12-07 | 2025-12-04 | -3 | NEGATIVE_DELAY_EXCLUDED | 220kV | 220kV
TB 501 | 5xx | Private | 80-100+ | 6/0 | 2026-02-19 | 2026-02-17 | -2 | NEGATIVE_DELAY_EXCLUDED | 132kV | 132kV
TB 501 | 5xx | Private | 80-100+ | 34/0 (New) | 2026-04-30 |  |  | UNMATCHED_LOCATION | 220kV
TB 507 | 5xx | Private | 20-40 | 71/2 | 2025-10-30 | 2025-01-14 | -289 | NEGATIVE_DELAY_EXCLUDED | MAIN | MAIN
TB 507 | 5xx | Private | 0-20 | 86/2 | 2025-02-22 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 66/2 | 2025-03-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 64/3 | 2025-03-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 96/2 | 2025-03-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 64/4 | 2025-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 99/1 | 2025-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 66/3 | 2025-03-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 87/1 | 2025-03-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 64/6 | 2025-03-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 87/2 | 2025-03-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 64/5 | 2025-03-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 71/1 | 2025-04-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 91/2 | 2025-04-16 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 51/2 | 2025-04-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 95/2 | 2025-04-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 51/3 | 2025-04-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 99/2 | 2025-04-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 104B/1 | 2025-04-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 62/4 | 2025-04-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 100/1 | 2025-05-18 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 99C/2 | 2025-05-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 105/0 | 2025-05-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 62/5 | 2025-05-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 96/0 | 2025-06-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 119/0 | 2025-06-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 74/0 | 2025-06-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 106/0 | 2025-07-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 125/1 | 2025-07-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 125/0 | 2025-07-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 94/0 | 2025-07-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 99/3 | 2025-07-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 99/0 | 2025-08-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 87/0 | 2025-08-22 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 99/4 | 2025-08-22 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 63/1 | 2025-08-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 56/4 | 2025-08-26 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 56/2 | 2025-08-27 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 56/5 | 2025-08-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 99A/0 | 2025-08-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 57/0 | 2025-09-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 59/0 | 2025-09-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 64/0 | 2025-09-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 58/0 | 2025-09-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 125/2 | 2025-09-18 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 72/1 | 2025-09-19 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 56/1 | 2025-09-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 48/0 | 2025-09-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 89/0 | 2025-11-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 71/0 | 2025-11-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 88/0 | 2025-12-05 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 98B/2 | 2025-12-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 117/0 | 2025-12-13 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 104A/0 | 2025-12-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 124/0 | 2025-12-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 122/2 | 2026-01-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 126/3 | 2026-01-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 69/3 | 2026-01-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 108/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 10/3 | 2026-01-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 109/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 7/0 | 2026-02-11 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 10/12 | 2026-02-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 6/2 | 2026-02-16 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 6/1 | 2026-02-20 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 1/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 117/2 | 2026-02-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 6/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 157/0 | 2026-03-04 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 156/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 98B/1 | 2026-03-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 2/0 | 2026-03-13 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 2/2 | 2026-03-15 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 2/3 | 2026-03-16 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 2/4 | 2026-03-17 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 103/0 | 2026-03-19 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 3/0B | 2026-03-26 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 2/5 | 2026-03-27 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 3/0A | 2026-03-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 5/2 | 2026-03-31 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 5/1 | 2026-04-02 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 3/1 | 2026-04-04 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 3/1 | 2026-04-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 2/1B | 2026-04-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 2/1 A | 2026-04-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 103/1 | 2026-04-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 8/0 | 2026-04-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 5/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 99C/0 | 2026-04-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/5 | 2026-04-16 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 3/3 | 2026-04-18 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 3/2 | 2026-04-21 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 100/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 10/11 | 2026-04-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 3/4 | 2026-04-29 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 2/0 | 2026-05-02 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 155/0 | 2026-05-03 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 3/5 | 2026-05-05 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 154/1B | 2026-05-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 10/13 | 2026-05-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 154/2B | 2026-05-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/2 | 2026-05-08 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 154/1A | 2026-05-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 154/2A | 2026-05-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/4 | 2026-05-10 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 13/2 | 2026-05-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/0 | 2026-05-15 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 8/3 | 2026-05-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/1 | 2026-05-18 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 4/3 | 2026-05-19 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 8/4 | 2026-05-19 |  |  | UNMATCHED_LOCATION | MAIN
TB 605 | 6xx | Private | 0-20 | 18/0 | 2025-10-16 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 22/1 | 2025-10-28 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 21/1 | 2025-10-31 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 22/0 | 2025-10-31 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 74/0 | 2025-11-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 72/0 | 2025-11-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 22/2 | 2025-11-13 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 17/0 | 2025-11-23 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 20/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | AP116 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | AP87 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 40/0 | 2025-12-03 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 23/0 | 2025-12-09 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 29/0 | 2025-12-10 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 85/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 106/1 | 2025-12-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 102/1 | 2025-12-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 135/2 | 2025-12-21 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 139/1 | 2025-12-24 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 138/1 | 2025-12-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 80/1 | 2025-12-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 138/2 | 2025-12-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 137/2 | 2026-01-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP131 | 2026-01-11 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 152/2 | 2026-01-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP154 | 2026-01-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP138 | 2026-01-20 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 153/0 | 2026-02-05 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP139 | 2026-02-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP15 | 2026-02-08 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 20-40 | AP155 | 2026-02-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP130 | 2026-02-12 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP92 | 2026-02-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP150 | 2026-02-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 136/4 | 2026-02-20 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP12 | 2026-02-20 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 20-40 | AP132 | 2026-02-24 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 70/1 | 2026-02-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP137 | 2026-02-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP21 | 2026-02-27 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 20-40 | AP91 | 2026-02-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP159 | 2026-02-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP14 | 2026-03-08 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP149 | 2026-03-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 67/2 | 2026-03-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP127 | 2026-03-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP148 | 2026-03-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP136 | 2026-03-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP71 | 2026-03-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP152 | 2026-03-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP108 | 2026-03-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP124 | 2026-03-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP67 | 2026-03-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 56/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP125 | 2026-04-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 144/3 | 2026-04-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 65/2 | 2026-04-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP109 | 2026-04-12 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP126 | 2026-04-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP1 | 2026-04-18 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP61 | 2026-04-21 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP165 | 2026-04-22 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP86 | 2026-04-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 56/2 | 2026-04-25 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP123 | 2026-04-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP59 | 2026-04-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 55/1 | 2026-04-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP142 | 2026-04-29 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP7 | 2026-04-29 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | 122/1 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP166 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP41 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP6 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP64 | 2026-05-01 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 64/1 | 2026-05-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP144 | 2026-05-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP56 | 2026-05-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 142/1 | 2026-05-08 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 61/1 | 2026-05-08 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP82 | 2026-05-08 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 57/1 | 2026-05-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP161 | 2026-05-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP163 | 2026-05-11 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 56/4 | 2026-05-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 62/2 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 71/1 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP110 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP38 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP57 | 2026-05-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 159/3 | 2026-05-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 40/3 | 2026-05-16 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | 65/4 | 2026-05-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 50A/2 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP162 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP60 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 62/1 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP128 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP143 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP63 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 159/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 23/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | 57/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP112 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP70/3 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab

## Scope Snapshot
Scope Snapshot
Project | Project Rollup Key | Project Base Code | Series | Ownership | Scope Total | Scope Source | Scope Report Date | Status Rows Considered | Status Rows Used | Duplicate Rows Dropped | Quantity Primary Sum | Cumulative Progress Sum | Balance Progress Sum | Fallback Foundation Done Count | Coverage Status | Coverage Reason | Note
TA 413 | ta413 | TA 413 | 4xx | Government | 632 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | 632 | 632 | 0 | 314 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 414 | ta414 | TA 414 | 4xx | Government | 352 | status_quantity_primary_latest | 2026-05-19 | 1 | 1 | 0 | 352 | 314 | 38 | 326 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 416 | ta416 | TA 416 | 4xx | Government | 302 | status_quantity_primary_latest | 2026-05-17 | 1 | 1 | 0 | 302 | 302 | 0 | 303 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 418 | ta418 | TA 418 | 4xx | Government | 127 | status_quantity_primary_latest | 2026-05-17 | 1 | 1 | 0 | 127 | 127 | 0 | 129 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 419 | ta419 | TA 419 | 4xx | Government | 330 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | 330 | 247 | 83 | 268 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 421 | ta421 | TA 421 | 4xx | Government | 309 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | 309 | 309 | 0 | 303 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 505 | ta505 | TA 505 | 5xx | Government | 379 | status_quantity_primary_latest | 2026-05-19 | 1 | 1 | 0 | 379 | 374 | 7 | 373 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 509 | ta509 | TA 509 | 5xx | Government | 309 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | 309 | 264 | 45 | 264 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 510 | ta510 | TA 510 | 5xx | Government | 293 | status_quantity_primary_latest | 2026-05-19 | 1 | 1 | 0 | 293 | 77 | 216 | 81 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 512 | ta512 | TA 512 | 5xx | Government | 315 | status_quantity_primary_latest | 2026-05-19 | 1 | 1 | 0 | 315 | 0 | 302 | 297 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 513 | ta513 | TA 513 | 5xx | Government | 619 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | 619 | 81 | 538 | 83 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 601 | ta601 | TA 601 | 6xx | Government | 292 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | 292 | 119 | 173 | 119 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 602 | ta602 | TA 602 | 6xx | Government | 478 | status_quantity_primary_latest | 2026-05-18 | 1 | 1 | 0 | 478 | 143 | 335 | 143 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TB 501 | tb501 | TB 501 | 5xx | Private | 238 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | 238 | 235 | 3 | 231 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TB 507 | tb507 | TB 507 | 5xx | Private | 556 | status_quantity_primary_latest | 2026-05-19 | 2 | 2 | 0 | 556 | 334 | 222 | 331 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TB 605 | tb605 | TB 605 | 6xx | Private | 523 | status_quantity_primary_latest | 2026-05-19 | 1 | 1 | 0 | 523 | 339 | 184 | 288 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).